NT10BIX5570003 | 2012 | Q2 | Q2 - 2012 | 6960 | 6107 | FALSE | 93 | All remaining Construction activity will be completed in this quarter with remaining invoices being paid following completion of the project. Payments will linger into Q4 2012 with the final report showing 100% completion. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance | 100 | No Variance. | 90 | Final Network Testing will be completed in Q4 2012. | 2012-08-09 11:27 | 2012-08-09 11:27 | 5445 | 5445 | South Dakota Network, LLC
NT10BIX5570003 | 2012 | Q3 | Q3 - 2012 | 7852 | 6630 | FALSE | 100 | No Variance. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2012-11-13 17:24 | 2012-11-13 17:24 | 5445 | 5445 | South Dakota Network, LLC
NT10BIX5570003 | 2012 | Q4 | Q4 - 2012 | 9038 | 7806 | FALSE | 100 | Project has been completed. | 100 |  | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 100 | Project has been completed. | 2013-02-27 16:34 | 2013-02-27 16:34 | 5445 | 5445 | South Dakota Network, LLC
NT10BIX5570004 | 2010 | Q3 | Q3 - 2010 | 300 | 1416 | FALSE | 25 | Project delayed due to pending EA approval | 0 |  | N/A | 100 | N/A | 80 | Middle Mile 80% complete. Last mile 0% complete and can not be completed until middle mile is complete. Middle mile project delayed due to pending EA approval | 80 | Middle Mile 80% complete. Last mile 0% complete and can not be completed until middle mile is complete. Middle mile project delayed due to pending EA approval | 5 | Project delayed due to pending EA approval | 15 | N/A | 15 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 0 | Project delayed due to pending EA approval | 2010-11-01 14:35 | 2010-11-01 14:35 | 5444 | 5444 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2010 | Q4 | Q4 - 2010 | 864 | 1898 | FALSE | 28 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | N/A | N/A | 100 | Final approval received January 3, 2011. | 85 | Middle Mile 95% complete. Last mile 0% complete and can not be completed until middle mile is complete. | 85 | Middle Mile 95% complete. Last mile 0% complete and can not be completed until middle mile is complete. | 42 | N/A | 25 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 42 | N/A | 10 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 5 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 5 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 2011-01-28 17:51 | 2011-01-28 17:51 | 5444 | 5444 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2011 | Q1 | Q1 - 2011 | 1940 | 2715 | FALSE | 10 | Fiber construction will continue during the second quarter. Procurement of equipment expected to continue and implementation of equipment should begin during the second quarter. We will continue to develop and implement testing plans and procedures. With the majority of project completion milestone occurring in the third quarter. | 0 | N/A | N/A | 100 | N/A | 85 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 50 | N/A | 25 | We do anticipate an increase in site preparation in the third quarter of 2011. | 50 | N/A | 15 | Plan for all core and middle mile fiber construction to be completed by third quarter 2011. IRU negotiations should be completed by end of second quarter 2011. | 10 | Equipment deployment will begin in second quarter 2011 and we are projecting to meet our third quarter 2011 milestone.. | 15 | N/A | 2011-05-11 11:41 | 2011-05-11 11:41 | 5751 | 5751 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2011 | Q2 | Q2 - 2011 | 3032 | 3273 | FALSE | 31 | Fiber construction will continue during the third quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should begin during the third quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will begin during third quarter. | 0 | N/A | N/A | 100 | N/A | 85 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 90 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts have been started and last mile construction is projected to begin in third quarter 2011. | 58 | Construction Permits and Other Approvals should be 58 percent complete in third quarter 2011 which meets the baseline milestones. | 58 | We do anticipate an increase in site preparation in the third quarter of 2011. | 58 | Last mile construction will increase during the third quarter of 2011. We do anticipate having equipment procurement at 58 percent complete in the third quarter of 2011 which meets the baseline milestones. | 30 | With the increased last mile deployment and core and middle mile construction completed in two of the three areas we anticipate having the network build 35 percent complete which meets the baseline milestones. | 50 | Equipment deployment will increase during the third quarter of 2011 and we are projecting to meet our third quarter 2011 milestones. | 25 | Network Testing is anticipated to be 25 percent complete and we are projecting to meet our third quarter 2011 milestones. | 2011-08-11 18:25 | 2011-08-11 18:25 | 7129 | 7129 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2011 | Q3 | Q3 - 2011 | 4206 | 3951 | FALSE | 67 | Fiber construction will continue during the fourth quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will continue during fourth quarter. We have budget meetings every two weeks to insure that this spend rate will be achieved prior to the November 30, 2011 deadline. | 0 | N/A | N/A | 100 | N/A | 90 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction is projected to began the last week of September 2011. | 92 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts continued during the third quarter of 2011 and last mile construction began the last week of September 2011. | 67 | Construction Permits and Other Approvals should be 67 percent complete in fourth quarter 2011 which meets the baseline milestones. | 67 | Site Preparation should be 67 percent complete in fourth quarter 2011 which meets the baseline milestones. | 67 | Last mile construction will increase during the fourth quarter of 2011. We do anticipate having equipment procurement at 67 percent complete in the fourth quarter of 2011 which meets the baseline milestones. | 45 | With the increased last mile deployment and core and middle mile construction completed we anticipate having the network build 45 percent complete which meets the baseline milestones. | 60 | Equipment deployment will continue during the fourth quarter of 2011 and we are projecting to meet our fourth quarter 2011 milestones. | 35 | Network Testing is anticipated to be 35 percent complete and we are projecting to meet our fourth quarter 2011 milestones. | 2011-11-21 21:31 | 2011-11-21 21:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2011 | Q4 | Q4 - 2011 | 5204 | 4874 | FALSE | 75 | Meets first quarter milestones | 0 | N/A | N/A | 100 | N/A | 91 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 94 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts continued during the fourth quarter of 2011 and will continue until the end of the project. | 75 | Meets first quarter milestones | 75 | Meets first quarter milestones | 75 | Meets first quarter milestones | 55 | Meets first quarter milestones | 75 | Meets first quarter milestones | 45 | Meets first quarter milestones | 2012-02-23 10:23 | 2012-02-23 10:23 | 5751 | 5751 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2012 | Q1 | Q1 - 2012 | 6318 | 5761 | FALSE | 84 | Meets second quarter milestones | 0 | N/A | N/A | 100 | N/A | 94 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 96 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continued during the second quarter of 2012 and will continue until the end of the project. | 83 | Meets second quarter milestones | 83 | Meets second quarter milestones | 83 | Meets second quarter milestones | 75 | Meets second quarter milestones | 80 | Meets second quarter milestones | 55 | Meets second quarter milestones | 2012-05-29 12:11 | 2012-05-29 12:15 | 7129 | 7129 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2012 | Q2 | Q2 - 2012 | 7100 | 6177 | FALSE | 92 | Meets third quarter milestones | 0 | N/A | N/A | 100 | N/A | 97 | Last mile design will not be completed until the core and middle mile are completed. At that time last mile customer will have been determined. Last mile marketing efforts continued and last mile construction began the last week of September 2011 and will continue until the end of the project. | 99 | Rights of way cannot be completed until core and middle mile construction is finished and last mile design completed. Last mile marketing efforts will continued during the second quarter of 2012 and will continue until the end of the project. | 92 | Meets third quarter milestones | 92 | Meets third quarter milestones | 92 | Meets third quarter milestones | 85 | Meets third quarter milestones | 90 | Meets third quarter milestones | 75 | Meets third quarter milestones | 2012-08-15 18:51 | 2012-08-15 18:51 | 7129 | 7129 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2012 | Q3 | Q3 - 2012 | 7666 | 6512 | FALSE | 100 | Project on schedule for completion as of 11/30/12 | 0 | N/A | N/A | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 100 | Project on schedule for completion as of 11/30/12 | 2012-10-30 19:10 | 2012-10-30 19:10 | 7129 | 7129 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | 2012 | Q4 | Q4 - 2012 | 9176 | 8008 | FALSE | 100 | Project was completed on 11/30/12. | 100 | N/A | N/A | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 100 | Project was completed on 11/30/12. | 2013-04-12 14:31 | 2013-04-12 14:31 | 5751 | 5751 | North Georgia Network Cooperative, Inc.
NT10BIX5570009 | 2010 | Q3 | Q3 - 2010 | 344 | 1438 | FALSE | 30 | Given the previous quarter's challenges we may not be able to catch up at this point but plan to within the next quarter or the quarter after that. | 40 | Staffing | None Noted | 100 | None Noted | 85 | None Noted | 95 | None Noted | 60 | None Noted | 10 | Site preparation is beginning one quarter later than planned due to delays with obtaining permits in Year 1 Q2. | 10 | Merit will have selected a vendor, but we have changed our purchasing strategy to "just in time". Our baseline plan assumed that equipment would be purchased in advance and warehoused. | 2 | None Noted | 5 | None Noted | 5 | None Noted | 2010-11-18 08:37 | 2010-11-18 08:37 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570009 | 2010 | Q4 | Q4 - 2010 | 1346 | 2363 | FALSE | 40 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. Merit anticipates that in the following quarter or the quarter after that Merit will be back up to speed considering the construction and equipment procurement will accelerate quickly after the permitting is complete. | 50 | Staffing | None Noted | 100 | None Noted | 95 | None Noted | 95 | None Noted | 55 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 30 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 30 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 2 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 5 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 5 | Given the struggles in prior quarters we don't feel we will be up to speed with the Baseline Report. | 2011-02-23 15:52 | 2011-02-23 15:52 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570009 | 2011 | Q1 | Q1 - 2011 | 2266 | 2878 | FALSE | 12 | The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 59 |  | We are slightly under budget in this category because engineering staff have not completed the installation training. | 100 | Since our Finding of No Significant Impact (FONSI) was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 400% next quarter), we do not anticipate revising the budget as reported on Form 424C; the EA is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 20 | Engineering has cost significantly less than originally budgeted. This is offset by the EA subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from occasional route changes required by permit kickbacks. The route changes, additional engineering work, and staffing will continue to add between 3% and 5% to the percent complete total on a quarterly basis. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 173% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 173% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution (CAI) builds and route changes necessitated by schedule or engineering. | 0 | We are in the middle of the procurement process for selecting a contractor to perform the site preparation work; we are also still in the process of finalizing central office and CAI routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 18 | Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. However, we will acquire some additional equipment in this quarter. | 4 | We are slightly behind on the network build because we are still waiting for the Davis Bacon Act wage determinations to be issued. We have temporarily secured the services of an underground construction firm so that we could begin some construction, but Merit cannot enter into a contract with a construction firm without attaching the applicable wage determinations. We anticipate bringing on several construction crews and beginning aerial construction in the next quarter. | 4 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. | 3 | Merit has just hired an engineer to deploy and test optical equipment; we anticipate being routinely under budget in this category, since it comprises 36 months of salary. We also have not incurred expense for testing equipment at this time. | 2011-05-24 09:26 | 2011-05-24 09:26 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570009 | 2011 | Q2 | Q2 - 2011 | 3030 | 3272 | FALSE | 29 | The combination of delays in several milestone categories has resulted in significantly less spending than we projected; however, once construction is fully underway, we anticipate closing the gap between our current status and the Baseline Plan. | 75 | Staffing, Misc. | Legal expenses in previous quarters have been signficantly higher than expected. | 100 | Since our Finding of No Significant Impact was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 400% next quarter), we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 41 | Engineering has cost significantly less than originally budgeted. This is offset by the Environmental Assessment subcategory (split out separately for the purpose of reporting), which has cost significant more than anticipated. The percent complete number, when based solely on financials, does not reflect that network design for the fiber optic backbone is complete aside from occasional route changes required by permit kickbacks. The route changes, additional engineering work, and staffing will continue to add between 3% and 5% to the percent complete total on a quarterly basis. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 196% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 196% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 0 | We have selected a contractor to perform the site preparation work; we are also still in the process of finalizing central office and Community Anchor Institution routes. We will be catching up by prepping the site prior to the arrival of the backbone fiber to the anchor, allowing us to get more site preparation complete in a short time frame. Wherever possible, we will save time by purchasing existing entrances to the central office facilities. | 27 | Merit does not want to deploy optical equipment until we are closer to the fiber installation date. Due to a lack of storage capacity in our business office, we feel it is wasteful to order more equipment at this time than we are ready to deploy. However, we will acquire some additional equipment in this quarter. | 22 | We are slightly behind on the network build because of the wait for the Davis Bacon Act wage determinations to be issued. We have temporarily secured the services of an underground construction firm so that we could begin some construction, but Merit cannot enter into a contract with a construction firm without attaching the applicable wage determinations. We anticipate bringing on several construction crews and beginning aerial construction in the next quarter. | 7 | We will have not incurred significant expense for equipment deployment at this time. We are early in the deployment process, but Merit will be most likely be at or close to budget by completion. | 41 | We have procured test equipment, but less testing has been required due to construction delays. Merit will be most likely be at or close to budget by completion. | 2011-08-11 16:39 | 2011-08-11 16:39 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570009 | 2011 | Q3 | Q3 - 2011 | 3948 | 3812 | FALSE | 58 | We expect to have the remaining permits approved by the end of the next quarter. We also expect to deploy more segments for construction once the delays in permitting (both construction and environmental) are resolved. We also anticipate having all funded community anchors signed up by the end of next quarter. Once multiple construction deployments commence (which will occur in the very near future) we anticipate closing the gap between our current status and the Baseline Plan. | 84 |  | Legal expenses in previous quarters have been significantly higher than expected. | 100 | Since our Finding of No Significant Impact was issued, we have needed and will continue to need to work with our environmental consulting firm on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the significant overrun (estimated to be approximately 427%), we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. | 41 | While the engineering expense cost less than anticipated, we have had significant delays in getting our environmental clearances. While the engineering is less than we anticipated, we have had significant delays in getting our environmental clearances from the State of Michigan. We have received our federal clearances but state regulations are more stringent. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. Some re-engineering occurred due to changes required by permitting entities. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 238% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (estimated at 238% for next quarter), however, work still remains to be done. There are several municipalities who have not approved our permit requests. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 25 | We have almost completed the process of finalizing central office and community anchor institution routes. Last quarter we selected a contractor to perform site preparation work and he is diligently conducting site visits. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 30 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field. As we are early in the deployment process, Merit will most likely be at or close to budget by completion. | 64 | We have contracts with seven construction firms, each with multiple construction crews and have begun aerial construction in the Southern region. Other areas of aerial construction are planned to start in the very near future as permits are being approved. We are currently over 60% complete on all Round 1 permits, of which there are 1,256 needed. | 50 | We have not incurred expense for equipment deployment at this time. Merit has not completed enough construction to warrant placing equipment in the field. As we are early in the deployment process, Merit will most likely be at or close to budget by completion. | 26 | We have procured test equipment, but testing hasnâ€™t commenced due to construction delays. Merit will most likely be at or close to budget by completion. | 2011-11-10 07:48 | 2011-11-10 07:52 | 5485 | 5485 | Merit Network Inc.
NT10BIX5570009 | 2011 | Q4 | Q4 - 2011 | 5320 | 4990 | FALSE | 63 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Construction crews will be working at capacity, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 94 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. | 100 | The Environmental Assessment is at 440% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 50 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 33 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 30 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 68 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 52 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-02-27 17:13 | 2012-02-27 17:13 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570009 | 2012 | Q1 | Q1 - 2012 | 6120 | 5662 | FALSE | 64 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Construction crews will be working at capacity, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 96 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. | 100 | The Environmental Assessment is at 440% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 55 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the third and fourth quarters of 2012. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | We have exceeded our budget for rights-of-way permitting (273%), however, some work still remains to be done. We estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, we may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 34 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 64 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 61 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 33 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 68 | Test equipment has been purchased; once more construction is complete, testing will be performed, and the percent complete is projected to be at budget by project completion. | 2012-05-16 09:10 | 2012-05-16 09:10 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570009 | 2012 | Q2 | Q2 - 2012 | 6950 | 6102 | FALSE | 87 | Permitting (both construction and environmental) delays have resulted in less spending than originally projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate closing the gap between our current status and the Baseline Plan in subsequent quarters. | 100 | Staffing, Miscellaneous | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (114%) by project completion, because we will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Category will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with our environmental consulting firm and the Michigan Department of Environmental Quality (MDEQ) on ways to minimize our project's impact in sensitive areas and remain in compliance. Despite the overrun, we do not anticipate revising the budget as reported on Form 424C; the Environmental Assessment is a component of the Engineering budget, and we are significantly under budget in that category at this time. We are confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 78 | Engineering has so far cost far less than anticipated, and we have had significant delays in getting our environmental clearances. The current percent complete does not accurately reflect that network design for fiber optic backbone is complete. The Engineering teams will continued to work on the route and incorporate redlines into Merit's GIS database. Final CADs cannot be produced until construction is complete, so we anticipate seeing a significant portion of the budget funds expended in the fourth quarters of 2012. | 100 | Merit estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 100 | Merit estimate the percentage at completion will be 300%, which will be absorbed by the construction budget. In addition, Merit may need to submit additional permit applications for community anchor institution builds and route changes necessitated by schedule or engineering. | 67 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 89 | Most of the dense wave division multiplex (DWDM) equipment will be invoiced this quarter. The procurement process for routers and switches will be completed, and equipment will be ordered. Merit anticipates being at budget by project completion. | 84 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 67 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 84 | Test equipment has been purchased; once more construction is complete, testing will be performed. However, due to the scheduling and staffing efficiencies achieved by combining deploying equipment, site preparation, and network testing on single runs, this category is projected to be under budget by project completion. | 2012-08-09 09:17 | 2012-08-09 09:17 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570009 | 2012 | Q3 | Q3 - 2012 | 8036 | 6724 | FALSE | 100 | Construction and environmental permitting delays have resulted in less spending than projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress will be made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate being near budget at the end of the fourth quarter with some funding available to cover administrative expenses associated with closing out the grant. | 100 | Staffing, Miscellaneous | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (138%) by project completion. We will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Company will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 70 | To date engineering has cost significantly less than anticipated despite delays in getting our environmental clearances. The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. The engineering teams will continue to work on the route and incorporate redlines into Meritâ€™s Geographic Information System database. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended in the fourth quarter of 2012. Because we are still waiting on engineering and construction drawings of the route, our projection for next quarter has come in lower than what our projection was in the third quarter. | 100 | Merit estimates the percentage at completion will be 301%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit estimates the percentage at completion will be 301%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation form one (1) to four (4) individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 100 | All equipment has been ordered and Merit anticipates paying final invoices during the fourth quarter and finishing at budget upon completion. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit anticipates being at budget by the end of the fourth quarter. | 100 | Merit has been behind our Baseline Projection due to construction start delays. Now that construction is actively underway our engineers will be out in the field deploying equipment. Spending in this category will increase. Merit will be at or close to budget by completion. | 100 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2012-11-26 12:38 | 2012-11-26 12:38 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570009 | 2012 | Q4 | Q4 - 2012 | 8974 | 7754 | FALSE | 100 | Construction and environmental permitting delays have resulted in less spending than projected for this quarter. While the overall project completion in terms of spending is still behind, significant progress was made this quarter in eliminating the variance between the percent complete and the baseline plan. Additional construction will be complete, allowing equipment deployment, site preparation, and network testing, so we anticipate being near budget at the end of the following quarter with some funding available to cover administrative expenses associated with closing out the grant. | 100 |  | Spending in this category has evened out, and is now below the Baseline Projection. We anticipate being over budget (128%) by project completion. We will continue to require administrative staff and incur miscellaneous expenses as long as construction and deployment are underway. Surplus funds from the Network Testing Company will cover the cost overruns for staffing and miscellaneous expenses. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. There will continue to be minimal charges in this category as we work with agencies on environmental permitting and mitigation. | 100 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing a significant portion of the budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs. | 100 | Merit estimates the percentage at completion will be 288%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 100 | Merit estimates the percentage at completion will be 288%. This overrun will be accounted for in the Construction category. Additionally, Merit may need to submit additional permit applications for Community Anchor Institution. | 0 | Based on the way we have been categorizing expenses, site preperation items have been placed in the Network Design category. | 100 | All equipment has been ordered and Merit anticipates paying final invoices. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that are performing aerial and underground construction across the funded network. Merit has almost all construction completed, and will be wrapping up to begin Q1 2013. | 100 | Merit has been behind our Baseline Projection due to construction start delays. Now that construction is actively underway our engineers will be out in the field deploying equipment. Merit is finishing up installing and activating equipment. | 100 | Test equipment has been purchased. As construction is completed testing will be performed. This category is projected to be under budget by project completion due to the scheduling and staffing efficiencies achieved in deploying equipment, site preparation, and testing the network on single runs. | 2013-02-26 14:18 | 2013-02-26 14:18 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570009 | 2013 | Q1 | Q1 - 2013 | 10002 | 8545 | FALSE | 100 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. Merit anticipates project completion by the end of the quarter. | 100 | Staffing, Miscellaneous | Merit anticipates Spending in this category will reach 126% of the budgeted amount. Merit anticipates that there should be minimal expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun Merit does not anticipate revising the budget as reported on Form 424C. The Environmental Assessment is a component of the Engineering budget and Merit is currently under budget in that category. Merit is confident that the Engineering budget will be able to absorb the current overrun. | 46 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs and other overrun costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (288%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. Merit anticipates no further spending. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that performed aerial and underground construction across the funded network. Merit will receive final invoices and pay them over the next quarter. Merit anticipates being at 112% of this budget category at project end. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 100 | Construction is completed and some testing has occurred so far. Additional testing will take place over the following quarter. Merit anticipates being near budget at completion. | 2013-05-30 07:28 | 2013-05-30 07:28 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570009 | 2013 | Q2 | Q2 - 2013 | 10524 | 8915 | FALSE | 100 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in less spending to date than originally projected. Merit has completed construction and is now working on and completing final testing and any repairs that are necessary. Merit anticipates project completion by the end of the quarter. | 100 | Staffing, Miscellaneous | Merit anticipates Spending in this category will reach 187% of the budgeted amount. Merit anticipates that there should be some expenses in this category over the remainder of the project. Surplus funds from the Network Testing and Network Design categories will cover this cost overrun. | 100 | The Environmental Assessment is at 435% of budget. After our Finding of No Significant Impact was issued, we continued to need to work with the environmental consulting firm and the Michigan Department of Environmental Quality on ways to minimize our projectâ€™s impact and remain in compliance. Merit also needed to do additional work to obtain environmental approval from the National Telecommunications & Information Administration for route changes. Despite the overrun, Merit is under budget in other areas and should be able to absorb the overage in those categories. | 51 | The percentage of completion does not accurately reflect that the network design for fiber optic backbone is complete. Final CADs cannot be produced until construction is complete, so Merit anticipates seeing additional budget funds expended as the project wraps up, and will also contain costs relating to site preparation as well as absorb some of the Environmental Assessment costs and other overrun costs. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 100 | Merit has exceeded our budget for the rights-of-way permitting (294%). However, some work may still remain. Merit estimates the percentage at completion will be under 300%. | 1 | Based on the way we have been categorizing expenses, most site preparation items have been placed in the Network Design category. | 100 | All optical hardware has been procured and invoiced, and the procurement process for routers and switches was completed. Merit anticipates no further spending. | 100 | Merit has contracts with seven (7) construction firms. The seven (7) firms have multiple construction crews that performed aerial and underground construction across the funded network. Merit will receive final invoices and pay them over the next quarter. Merit anticipates being at 109% of this budget category at project end. | 100 | Merit is at 129% of the budget amount in this category but anticipates minimal spending in the following quarter as all equipment has been placed. | 79 | Construction is completed and some testing has occurred so far. Testing will be completed by the end of this quarter. | 2013-08-08 14:06 | 2013-08-08 14:06 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570009 | 2013 | Q3 | Q3 - 2013 | 12778 | 11108 | FALSE | 100 | Merit has completed the REACH 3MC Project. | 100 | Staffing, Miscellaneous | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 2015-04-02 10:44 | 2015-04-02 10:44 | 7981 | 7981 | Merit Network Inc.
NT10BIX5570009 | 2013 | Q4 | Q4 - 2013 | 11690 | 9814 | FALSE | 100 | The construction and environmental permit delays Merit experienced at the outset of the project has resulted in delays to the project timeline. Merit has completed construction and is now working to close out the project. | 100 | Admin/Legal/Misc. | Following the REACH-3MC approved re-budget, Merit is in line with the budget for Other/Misc expenses. Minimal Merit-funded expenses may occur during the following quarter as project close out takes place. | 100 | Following the REACH-3MC approved re-budget, Merit is in line with the budget for EA expenses. | 100 | Following the REACH-3MC approved re-budget, Merit is in line with the budget for Network Design/Engineering expenses. | 0 | Following the REACH-3MC approved re-budget, Merit is no longer assigning project expenses to this budget category. All Rights of Way expenses are included in the Construction Permits and Other Approvals category. | 100 | Following the REACH-3MC approved re-budget, Merit is in line with the budget for Construction Permit/Approval expenses. Rights of way have been included in this category. | 0 | Following the REACH-3MC approved re-budget, Merit is no longer assigning project expenses to this budget category. | 100 | Following the REACH-3MC approved re-budget, Merit is in line with the budget for Equipment Procurement expenses. Equipment Deployment expenses have been included in this category. | 100 | Following the REACH-3MC approved re-budget, Merit is in line with the budget for Construction expenses. | 0 | Following the REACH-3MC approved re-budget, Merit is no longer assigning project expenses to this budget category. Deployment expenses have been included in the Equipment Procurement category. | 0 | Following the REACH-3MC approved re-budget, Merit is no longer assigning project expenses to this budget category. Testing expenses have been included in the Construction category. | 2014-01-29 10:01 | 2014-01-29 10:01 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570011 | 2010 | Q3 | Q3 - 2010 | 384 | 1458 | FALSE | 15 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 0 |  | N/A | 100 | N/A | 100 | N/A | 50 | Ahead of schedule due to quicker application of permits. | 50 | Ahead of schedule due to quicker application of permits. | 0 | N/A | 15 | N/A | 15 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 10 | Delay in deployment due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 20 | Delay in start to construction due to delay in receipt of FONSI has set us back about two months. We expect to make this up over the course of 1-2 months. | 2010-11-23 11:38 | 2010-11-23 11:38 | 5748 | 5748 | MCNC
NT10BIX5570011 | 2010 | Q4 | Q4 - 2010 | 1170 | 2204 | FALSE | 35 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Because of our intent to pick up our construction pace, we have changed our approach for permit and encroachment application and expect to submit all before end of next quarter. | 90 | Because of our intent to pick up our construction pace, we have changed our approach for permit and encroachment application and expect to receive a large portion of these approvals back in the quarter and thus ahead of schedule | 0 | N/A | 50 | We will be procuring equipment for two specific spans to correspond with completion of construction efforts to have in hand for when fiber is completed, and thus feel we'll be ahead of pace. | 70 | We have 887 miles of network to deploy as part of the project. As of this quarter we reported 403 complete (7 miles of new, 197 miles of upgrade of existing IRU fibers, 197 miles of newly obtained IRU fibers). We anticipate finalizing IRUâ€™s of new fibers for Balsam West, Plateau LLC, and Morris Broadband within the Y2Q1 quarter that will total 98 miles of the proposed network. We also anticipate building approximately 120 miles of new fiber, amounting to a total of 621 miles of the network out of 887 miles to be deployed. | 40 | N/A | 33 | N/A | 2011-02-16 08:18 | 2011-02-16 08:18 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2011 | Q1 | Q1 - 2011 | 1884 | 2687 | FALSE | 50 | We believe we will begin to be slightly ahead of schedule by end of June quarter and significantly ahead of schedule by end of September quarter due to the pace of construction we're seeing. We're averaging placement of approximately 40 miles of conduit per month. As fiber is ready, equipment will be arriving to be deployed. | 0 | na | N/A to our project | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 75 | Due to the fact we're advancing ahead of schedule with miles of conduit placed, coupled with the lead times reported by Cisco currently on the type of equipment we need to deploy, we anticipate ordering equipment about one quarter in advance at a minimum of when we would deploy. Based on that, we will be ahead of pace to the baseline on this line item going forward. | 68 | Based on where we're at now and with a minimum of 100 miles placed, we would expect to be at 68% (conservatively) by end of June, which would be ahead of our baseline estimate. | 40 | Based on the lighting of completed spans, we would anticipate having about 1/2 of the network elements deployed by June, but to remain conservative, will only forecast 40% for now. | 68 | Based on where we're at now and with a minimum of 100 miles placed, we would expect to be at 68% (conservatively) by end of June, which would be ahead of our baseline estimate. | 2011-05-04 13:28 | 2011-05-04 13:28 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2011 | Q2 | Q2 - 2011 | 2946 | 3230 | FALSE | 75 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | Due to the quicker deployment of the fiber, we anticipate we will have placed orders for all equipment by the end of Y2Q3. | 100 | We are conservatively projecting completion of all fiber builds in the project by end of the quarter unless we experience an unexpected delay. | 50 | We anticipate having all priority segments lit prior to the end of the quarter, which when based on the number of miles in the project, will represent slightly greater than 50% of equipment located in the field. | 100 | Due to quicker than expected construction, we feel we will have all fiber deployed, and thus have all fiber tested. | 2011-08-08 09:45 | 2011-08-08 09:45 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2011 | Q3 | Q3 - 2011 | 4224 | 3960 | FALSE | 81 | We expect to have 95% of the scope of work completed. We expect expenditures by the end of the quarter will be around 81% of the total awarded contract value due to savings realized in executing on the work and timing related to contractor invoices for work completed during the last part of the quarter. | 0 |  | NA | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 80 | We do not anticipate being behind our baseline projection for this quarter. Relative to the number of miles in the project and the amount of equipment deployed to operate that fiber, we feel we will be coming in close to the 60% indication as we are lighting fiber within a close timeframe to completion of the fiber builds. The only thing that may hamper this for completeness in this quarter is lost time due to holiday's and work that we typically do on existing infrastructure during this annual time frame. | 100 | N/A | 2011-11-22 15:05 | 2011-11-22 15:05 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2011 | Q4 | Q4 - 2011 | 4970 | 4645 | FALSE | 78 | We expect to have 100% of the project completed which will correlated to 78% of the original budget. | 0 | NA | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2012-02-13 12:40 | 2012-02-13 12:40 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2012 | Q1 | Q1 - 2012 | 6228 | 5716 | FALSE | 86 | 100% of the original project plan has been completed. We expect that efforts on the additional proposed infrastructure and expenditures realized during Q22012 will increase the overall spend of the project to 86%. | 0 | NA | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 80 | 100% of the original network build has been completed. We expect that efforts on the additional proposed infrastructure and expenditures related to that will increase the overall spend of the network build to 80%. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 2012-05-21 12:48 | 2012-05-21 12:48 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2012 | Q2 | Q2 - 2012 | 7138 | 6196 | FALSE | 92 | The project as originally funded is 100% complete. This level of completeness forecasted for next quarter represents our estimate of how quickly the remaining builds and deployments will execute over this quarter, and the associated spend to do so. We do not forecast greater than 92% here as we don't believe all equipment associated with the 100G upgrade to the core will have arrived by the end of the September quarter to allow us to show the equipment received and thus accounted for within the project. | 0 | N/A | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 98 | We will be full force in our effort to complete the additional funded infrastructure. At the end of the quarter we would expect to 100% complete with the project as initially funded, and 98% complete as it relates to the percent complete relative to the additions to the scope of work. | 95 | We are 100% complete with the equipment elements of the project as originally funded. With the additions, we will be at 95% completion. | 100 | This task is 100% complete. | 2012-08-20 07:32 | 2012-08-20 07:32 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2012 | Q3 | Q3 - 2012 | 8106 | 6760 | FALSE | 96 | We anticipate this task will complete, but relevant to dollars spent, we will still be under budget and thus complete relative to dollars at 96% | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | We anticipate this task completing. | 95 | We anticipate this task completing during the quarter as awarded, but relevant to budget being under that which was anticipated and thus approved to be at 95% complete based on dollars spent. | 100 | We anticipate this task completing. | 100 | We anticipate this task completing. | 2012-11-28 12:24 | 2012-11-28 12:24 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2012 | Q4 | Q4 - 2012 | 9032 | 7802 | FALSE | 98 | The original project is complete. Due to the extension provided by the NTIA we are exploring adding three additional interconnect colocation point and some 100G infrastructure to Research1 CAI's. Most of the efforts in the next quarter related to this effort will be engineering in nature and have little associated cost. | 0 |  | N/A | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task is 100% complete. | 100 | This task will be 100% complete by the end of the next quarter. | 99 | We anticipate this task completing during the quarter as awarded, but relevant to budget being under that which was anticipated and thus approved to be at 95% complete based on dollars spent. | 95 | While we anticipate the equipment being procured, we do not anticipate having it deployed in the next quarter due to the length of time to receive it. | 100 | This task is 100% complete. | 2013-02-27 16:17 | 2013-02-27 16:17 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2013 | Q1 | Q1 - 2013 | 9904 | 8493 | FALSE | 98 | As originally awarded, we are 100% complete. The balance of work left by end of next quarter would be the placement of the telecommunication huts as part of the project modification. | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task will be 100% complete next quarter | 100 | This task will be 100% complete next quarter | 100 | This task will be 100% complete next quarter | 100 | This task is 100% complete | 2013-05-24 15:58 | 2013-05-24 15:58 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2013 | Q2 | Q2 - 2013 | 10540 | 8924 | FALSE | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 100 | This task will be 100% complete by end of the 9/30/13 quarter. | 100 | This task is 100% complete | 2013-08-09 15:12 | 2013-08-09 15:12 | 5479 | 5479 | MCNC
NT10BIX5570011 | 2013 | Q3 | Q3 - 2013 | 10940 | 9176 | FALSE | 100 | This task is 100% complete | 0 |  | N/A | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 100 | This task is 100% complete | 2013-10-25 08:17 | 2013-10-25 08:17 | 5479 | 5479 | MCNC
NT10BIX5570016 | 2010 | Q3 | Q3 - 2010 | 186 | 1359 | FALSE | 20 | No information to add | 0 |  | N/A | 100 | No information to add | 100 | No information to add | 100 | No information to add | 100 | No information to add | 35 | No information to add | 0 | No information to add | 15 | No information to add | 0 | No information to add | 0 | No information to add | 2010-10-28 11:51 | 2010-10-28 11:51 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2010 | Q4 | Q4 - 2010 | 810 | 1845 | FALSE | 20 | Delay in approval of EA & winter weather will hinder construction progress. Plan to add additional construction crews after Y2Q1. | 0 |  | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 35 | Weather will hinder completing site preparation. | 100 | N/A | 15 | Cable construction will be hindered by weather. Electronics & huts will be purchased. | 0 | Zero Variance | 0 | Zero Variance | 2011-01-28 15:52 | 2011-01-28 15:52 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2011 | Q1 | Q1 - 2011 | 2126 | 2808 | FALSE | 24 | Delayed construction start due to lack of approval of final EA and SHPO consultation delay | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Could not start until EA is approved and RFP prepared to send in May 2011 | 100 | N/A | 24 | Delayed construction start. Additional contractors will "catch up" construction schedule. | 0 | N/A | 0 | N/A | 2011-05-18 12:00 | 2011-05-18 12:00 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2011 | Q2 | Q2 - 2011 | 3066 | 3290 | FALSE | 60 | By adding additional construction crews, we hope to complete 60% of the project by end of Y2Q3. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Construction plans are to place approximately 30 miles of cable in Y2Q3. Due to the delay in the start of construction, the network build and equipment deployment dates were shifted forward. MBC is deploying additional crews to "catch up" on the schedule. | 33 | Equipment to be installed in at least one inter-connection point in Y2Q3. Due to the delay in the start of construction, the network build and equipment deployment dates were shifted forward. MBC is deploying additional crews to "catch up" on the schedule. | 25 | Network testing will begin as soon as equipment is installed in at least one node (inter-connection) location. | 2011-08-12 17:32 | 2011-08-12 17:32 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2011 | Q3 | Q3 - 2011 | 4034 | 3857 | FALSE | 61 | Percent completion as projected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 70 | Construction plans are to place 30 miles of cable in Y2Q4 | 33 | Equipment to be installed in at least one interconnection point. | 33 | Network testing to be completed in at least one location. | 2011-11-14 15:43 | 2011-11-14 15:43 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2011 | Q4 | Q4 - 2011 | 4882 | 4574 | FALSE | 82 | Percent completed projected on PIP (budget spent) | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 2 site (AC power) | 100 | Complete | 100 | Place additional 19 miles for a total of 105 miles | 100 | Complete remaining 2 interconnection sites | 80 | Completion of final testing in Y3Q2 | 2012-02-06 12:11 | 2012-02-06 12:11 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2012 | Q1 | Q1 - 2012 | 6078 | 5638 | FALSE | 84 | Became evident during Y3Q1, project would be under budget. A budget modification and route modification to be sent in Y3Q2 for approval. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-15 05:23 | 2012-05-15 05:23 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2012 | Q2 | Q2 - 2012 | 6874 | 6063 | FALSE | 90 | Construction of IRU and node to be completed in Y3Q4 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-06 22:26 | 2012-08-06 22:26 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2012 | Q3 | Q3 - 2012 | 7888 | 6648 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-11-14 21:12 | 2012-11-14 21:12 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2012 | Q4 | Q4 - 2012 | 8660 | 7483 | FALSE | 98 | Project extended to 6/30/13 as projected completion date | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Equipment deployment awaiting completion of new node | 98 | Testing awaiting completion equipment installation | 2013-02-06 20:38 | 2013-02-06 20:38 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2013 | Q1 | Q1 - 2013 | 9652 | 8358 | FALSE | 98 | Project Completion scheduled for 6-30-2013 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-08 23:58 | 2013-05-08 23:58 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | 2013 | Q2 | Q2 - 2013 | 12440 | 10628 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-08-19 15:49 | 2014-08-19 15:49 | 5453 | 5453 | Virginia Tech Foundation, Inc.
NT10BIX5570017 | 2010 | Q3 | Q3 - 2010 | 390 | 1461 | FALSE | 6 | We expect to have issued all of the purchase orders, with the exception of the wireless links as well as complete two microwave hops (or links) between three sites. Project will be on track with baseline plan in Q3 2011. | 50 | Customer Acquisition, Support and Billing | Workshop to identify interfaces as well as billing design documents is planned for Q1 of 2011. Q4 of 2010 will therefore show much of the research and preparation necessary to be prepared for Q1 of 2011. We have also determined that we plan to begin offering services to customers in July of 2011. | 100 | We expect a favorable response from the secondary investigation previously noted resulting from a request from the Wyandotte Tribe. | 90 | High-level and low-level network switching design will be completed. Remaining 10% contingency for additional design of 43 point to point and point to multi-point connections from the middle-mile backbone to customers. Project will be on track with baseline plan in Q3 2011. | 94 | Contingency for a slower than normal response time due to the holidays. Project will be on track with baseline plan by end Q1 2011 with all site permissions finalized for broadband. | 79 | We are currently determining the need for construction permits and or zoning approvals. Should it be determined that we need either for the new towers and shelters that we will be building and installing as part of this project, three fourths will be secured by close of Q4. | 21 | We expect to complete the site preparation on three sites by close of 2010. | 55 | We expect that we will have ordered all equipment with the exception of the 43 wi-max (wireless) links by the close of Q4. Delivery and acceptance of equipment, other than wi-max, is anticipated to begin in Q4. | 3 | We expect to complete the implementation of three sites to the point that they would be able to sustain the 150 Mbps speeds of broadband; however we also plan to return to these sites at a later date in the project to further upgrade them to allow for the traffic/ high-speed internet to pass through these sites via the path of least resistance. Project will be on track with baseline plan in Q3 2011. | 5 | We expect to deploy the equipment to three of our sites which would allow them to pass traffic that could reach speeds up to 150 Mbps by the end of Q4, 2010. Project will be on track with baseline plan in Q1 2011. | 4 | Network Testing is expected to begin in Q1 of 2011. | 2010-11-23 16:29 | 2010-11-23 16:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2010 | Q4 | Q4 - 2010 | 1172 | 2205 | FALSE | 20 | We expect to have the foundations of three of the new towers poured by the close of Q1. We also anticipate the completion of a total of 11 hops of microwave equipment installed. As noted previously, the slight delay that exists in our progress was due to a longer period of time than expected to get all purchase orders through the approval process of the commonwealth. Now that we have issued all of the major procurements, allowing equipment, towers and shelters to be ordered, we expect to catch up to the baseline by Q2 of 2011. | 37 | Customer Acquisition, Support and Billing | By the close of Q1, 2011 we expect to be well on our way to completion of the design of the customer support portion of the system. The asset management final design has already been completed. Training and implementation will follow shortly thereafter and is expected to occur within the 2nd quarter of 2011. | 100 | We have completed this portion of the project. | 90 | Design Documentation for the wireless connections is all that remains at this point. | 76 | The commonwealth is using the Rights of Way milestone indicator to track our completion of "permissions" documents as we currently have "rights-of-way" documents in place for all of our sites as they are pre-existing sites within our network. The permissions that we are seeking vary from site to site but can be anything from a notice that we will be offering broadband services through our equipment already located at that site or a request for permission to add additional equipment/minor modifications to that site. A majority of the permissions that remain outstanding are the type meant to notify the tower owner of our broadband services addition. We expect to complete this milestone within the next few quarters and catch up to the baseline report by Q2 or Q3 of 2011. | 100 | Based upon past experience, we expect to move through the process to obtain all necessary building permits rather quickly and anticipate completing the process within Q1. We are scheduled to begin construction on the towers in late Q1, so this should not cause any delay to the project. | 36 | We expect to have an additional two sites prepared for construction by the close of Q1, 2011. | 75 | While we have ordered all of the equipment deemed necessary for our project prior to the close of Q4 2010, there remains the delivery and invoicing of that equipment for this category to reach 100%. | 8 | We are gaging our network build percentage on the number of sites and hops where equipment is installed as well as the number of towers completed. By close of Q1, we believe that equipment will be deployed to 11 hops (microwave equipment) as well as to 10 sites (MPLS equipment). While no tower builds will be complete within Q1, we expect to have the first towers completed within Q2 of 2011. | 15 | Equipment deployment will begin to ramp up within Q1 of 2011. Within the quarter, we expect to deploy microwave equipment to 11 hops as well as MPLS equipment to 10 sites. | 4 | Network testing is occurring as equipment is deployed and installed. We expect all network testing to be completed within the quarter after each piece is installed, if not sooner. | 2011-02-16 08:29 | 2011-02-16 08:29 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2011 | Q1 | Q1 - 2011 | 2396 | 2943 | FALSE | 16 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 16% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 38% of completion for this milestone within Q2. During Q2 of 2011, we expect to complete construction on five new equipment shelters as well as two new self-supporting towers within Q2. In order to complete the tower construction we will need to finalize the zoning permit process as well as complete the Federal Aviation Administration (FAA) clearance process which we expect to occur within Q2. We also expect to complete installation of a total of 21 microwave connections as well as completed testing on 11 of those connections. While we will still be slightly behind the baseline for this period of time, we expec | 0 | Customer Acquisition, Support and Billing | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 50% of completion for this milestone within Q2. We anticipate the training portion of the asset management system to occur within the second quarter of 2011 as well as the final design of the billing/provisioning systems. The training phase of the billing/provisioning system is expected to occur sometime during the third quarter of the year followed up by implementation of both systems by the end of the quarter. As soon as items are completed to our satisfaction, we will recognize the items as received within the commonwealth's procurement and accounting system and payment will be made to the vendor. | 100 | This milestone has been completed. | 72 | According to the guidance from the NTIA and direction from our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 72% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 95% of completion for this milestone within Q2. By the close of Q2 of 2011, we will have completed the design of our network to include the high and low level documentation for the switching portion of the network as well as the high level design documentation for the wireless connections. The only portion that will remain at that point will be the final low level design documentation for the wireless connections which will largely depend upon our first customers. With the completion of multiple project design elements we will be in a position to begin showing expenditures for them. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is not to be tracked due to the lack of expenditures in this category. Following that guidance, our planned percent complete will remain at 0% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 100% of completion for this milestone within Q2. We anticipate receiving the final permissions documents to be returned around the close of Q2, 2011. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is not to be tracked due to the lack of expenditures in this category. Following that guidance, our planned percent complete will remain at 0% According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 78% of completion for this milestone within Q2. We are using the Construction Permits and other approvals milestone to represent not only building permits and Federal Aviation Administration (FAA) clearances for our five towers but also the zoning permit process that is necessary at two of the towers. All building permits have been waived at the five sites receiving new towers. We expect to have acquired the remaining FAA clearance within the second quarter as well as to have worked through the process to acquire the two necessary zoning permits. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 50% of completion for this milestone within Q2. During the second quarter of 2011, we expect to install a total of five equipment shelters upon their foundations as well as complete installation of two new self supporting radio towers within the quarter. As a result of the completion of these shelters, we will be able to show expenditures for the costs associated with these shelters bringing us to a status of 50% complete. | 15 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 15%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 76% of completion for this milestone within Q2. All equipment has been ordered as of the close of Q4; however, due to the Commonwealth's policy, all equipment must be installed, tested and signed off as being complete by our office, the customer, prior to invoicing. We have included delivery and invoicing within this milestone to fully gauge equipment deployment. With that said, we expect to reach 76% of completion of this milestone by the close of Q2, 2011 with the delivery of equipment to complete a total of 21 project connections as well as the invoicing of that equipment. | 0 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 0%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 30% of completion for this milestone within Q2. By the close of Q2, we expect to have installed 21 of the microwave connections as well as commenced with the installation of switching equipment at ten of the sites. We anticipated the completion of two of our new self supporting radio towers near the end of the second quarter as well. While we are slightly behind the progress predicted by our baseline, we expect to close the gap significantly within the 3rd quarter of 2011 with the build of an additional two towers and five equipment shelters. As the work is completed and connections are quality assurance tested, we will be a | 15 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 15%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 22% of completion for this milestone within Q2. By the close of the second quarter, we expect to have installed equipment at 21 of the total 71 microwave connections as well as 10 of the 68 sites of switching equipment. Once all quality assurance testing is completed, we will show expenditures for these items bringing us to a status of 22% complete. | 23 | According to the guidance from the NTIA and our current Federal Program Officer, our progress on this milestone is to be tracked solely on expenditures. Following that guidance, our expected percent complete is estimated at 23%. According to our own internal methods of tracking progress based upon pre-defined items of accomplishment, we expect to have reached 15% of completion for this milestone within Q2. We expect to have fully tested 11 of the 71 network connections by the close of the second quarter. Once this testing is complete, we will show expenditures for these items. | 2011-05-31 08:55 | 2011-05-31 08:55 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2011 | Q2 | Q2 - 2011 | 3130 | 3322 | FALSE | 18 | We expect to see expenditures for the tower and shelters that were completed near the close of the second quarter of 2011. We also expect to be able to show expenditures for the first pieces of microwave equipment as well. This figure varies from the baseline due to our change in method of gauging progress. Prior to the reporting of Q1, 2011, we used a method other than expenditures to determine our percent of progress completed. | 16 | Customer Acquisition, Support and Billing | By the close of the third quarter of 2011, we expect to be near completion on the work required for the billing and provision portions of this milestone with final completion expected early in the fourth quarter. As we have stated previously, all goods and services must be delivered and quality control inspected prior to submission of an invoice by the vendor. With that in mind, in reporting expenditures, it is likely that we will not catch up to our baseline report until early in 2012. | 100 | This milestone is complete. | 72 | We expect to see expenditures for the network design milestone early in the third quarter which should bring our percentage up to 72 percent complete based upon expenditures. One of the remaining items under this milestone is the design of the wireless links which may depend upon the requirements of the first customers which may delay our ability to catch up to the baseline until early in 2012. | 0 | N/A The rights of way milestone has no cost associated with it as part of our project therefore it's progress will not be tracked within the quarterly PPR. | 0 | N/A The construction permits and other approvals milestone has no cost associated with it as part of our project therefore it will not be tracked within the quarterly PPR. | 21 | We expect to have completed the construction of a total of five new towers and ten new shelters by the close of the third quarter of 2011 and are on track with our own internal schedule of progress. Our percent of progress; however, is based upon expenditures (as requested by the NTIA) which trail the completion of project activities. All goods and/or services procured by the Commonwealth of Pennsylvania are required to be completed or installed and quality assurance tested prior to the submission of an invoice by the vendor. We expect to catch the baseline report by the close of the fourth quarter of 2011. | 12 | As of the close of the third quarter of 2011, we expect to be able to show 12% of progress in the Equipment Procurement milestone as we pay for the first few microwave radio upgrades. We expect to continue to receive invoices for the additional equipment upgrades that have been completed to date and expect to catch our baseline report during the second quarter of 2012. | 27 | The network build milestone includes the expenditures for the construction of our new towers and shelters as part of this project. As of the close of the third quarter, we expect to have expenditures for one tower and five shelters. With the planned construction for the third quarter, we expect to be able to catch our baseline in the fourth quarter of this year. | 6 | We expect that the milestone of Equipment Deployment will be able to show expenditures to move the progress to 6% of completion by the close of the third quarter of 2011. The progress in this milestone is slow due to a lack of invoices to pay at this point. We will continue to encourage our vendors to submit invoices as soon as the work is completed. We expect to catch our baseline report in the early quarters of 2012. | 33 | We will continue to test all equipment installations as they happen. By the close of the third quarter of 2011, we expect to have paid all invoices related to the quality control inspections that occurred prior to the third quarter but are being conservative in our estimated expenditures. While this percent of progress slightly trails that of the baseline report, we expect to catch up in the first quarters of 2012. | 2011-08-16 15:53 | 2011-08-16 16:03 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2011 | Q3 | Q3 - 2011 | 4064 | 3875 | FALSE | 36 | By the close of the fourth quarter of 2011, our project will have completed the tower and shelter construction portion of the project and will have installed a total of 41 of the 71 total microwave radio connections included within the project, if not more. Due to the location of our sites and hunting season starting just after Thanksgiving, our teams will take a break from field work and focus their efforts on other activities to keep the project on schedule. Due to our percent of progress being based upon expenditures and our internal requirements prior to payment of invoices, our numbers are not in agreement with the baseline report. As invoices are received for the completed tower and shelter construction as well as the continued equipment installations, our percent of progress should climb significantly at the close of the 2011 4th quarter as well as the 2012 1st quarter. | 16 | Customer Acquisition, Support and Billing | We are nearing completion of the billing and provisioning portion of our project. This portion was temporarily held up by a slight change in hardware configuration in another aspect of the network. Now that we have moved forward with the hardware changes, our vendor can finalize the work on this portion of the project. Our ability to bring customers onto the network and provide an appropriate bill is not continent upon this portion of the project to be functional; however, billing and provisioning will be facilitated by this item. We now expect that this part of the project will be completed around the close of the first quarter of 2012. | 100 | This milestone is complete. | 76 | The main item remaining under our network design is that of the wireless links to connect the last mile providers and/or community anchor institutions to our network. With the planned launch of a pilot project with a last mile service provider in the fourth quarter, and the valuable knowledge we will gain from that project, we anticipated launching this milestone forward in the first quarter of 2012. | 0 | N/A. The rights of way milestone has no cost associated with it as part of our project; therefore, it's progress will not be tracked within the quarterly PPR. | 0 | n/a The construction permits and other approvals milestone has no cost associated with it as part of our project; therefore, it will not be tracked within the quarterly PPR. | 38 | By the close of the fourth quarter, we expect to have completed all of the tower and shelter work as part of this project with the only remaining element in site preparation to be the compound expenses to finish the grading, seeding, fencing etc. at the site compounds. With a majority of this work coming to a close, we expect to be in the early stages of receiving the remainder of the invoices for site preparation by the close of the fourth quarter which should be paid by the close of the first quarter of 2012. | 23 | As our equipment is installed and tested, our vendor(s) are submitting invoices for payment. Unfortunately, the invoices trail the actual installation by multiple months due to the internal procedures that we have in place. Nonetheless, we will have reached 23 percent of this milestone by the close of the fourth quarter and expect to make significant progress as invoices (for work completed in the fourth quarter) are paid by the close of the first quarter in 2012. | 79 | The network build milestone includes the construction of our towers and shelters of which many other elements were dependant upon. A majority of those structures are complete as of the end of the third quarter with the remainder of them expected to be completed early within the fourth quarter. These expenditures, likely realized in the first quarter of 2012, along with expenditures for the radio and switching equipment will help to boost this milestone in early 2012. | 15 | The progress in this milestone is slow due to a network hardware configuration change that effects our entire network. As a result, a few elements of our project schedule were adjusted to allow for that work to be configured. Now that we have made our adjustments, we expect to roll out switching equipment as well as the provisioning portal which will allow our expenditures in this milestone to increase early in 2012. | 40 | We will continue to test all equipment installations as they occur, as we have from the start of the project. By the close of the fourth quarter of 2011, we expect to have paid all invoices related to the quality control inspections that have occurred prior to the fourth quarter but are being conservative in our estimated expenditures. While this percentage of progress slightly trails that of our baseline report, we expect to catch up in the first quarters of 2012. | 2011-11-16 11:59 | 2011-11-16 11:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2011 | Q4 | Q4 - 2011 | 5296 | 4965 | FALSE | 48 | The project, when measured by expenditure alone, is anticipated to remain behind the baseline due to the safeguards built into the Commonwealth's payment system. Goods and/or services must be provided and approved, then quality assurance checked and invoiced. Project progress based upon completion of work; however, is expected to remain on schedule at approximately 78% complete. The difference between actual progress and that based upon expenditures accounts for the vendor having not invoiced for the installation and integration of equipment until not only the microwave radios have been installed/integrated but also the MPLS switching equipment as well. | 57 | Customer Acquisition, Support and Billing | The Billing portion of the project remains in progress as we await customers to test the application. It is anticipated that payment for the Reporting Analysis Manager and other elements of the operational support system may be realized. It is anticipated that this milestone will catch up to the expenditure based baseline report in the third quarter of 2012. | 100 | This milestone is complete. | 77 | The only remaining element in the network design milestone is in regard to WiMAX. Once the pilot with a last mile service provider begins and the Request for Information (RFI) is completed, it is expected that the engineering for WiMAX will be completed. | 0 | N/A. This milestone does not apply to our project. | 0 | N/A. This milestone does not apply to our project. | 73 | This milestone is on schedule. | 49 | It is anticipated that 67% of microwave equipment expenditures will have been realized. Engineering and configuration of switching equipment will continue allowing for the deployment in Q2, 2012. | 100 | This milestone is anticipated to be complete. | 9 | On this project, the payments for services at the network sites are contingent upon both microwave and switching equipment to be installed prior to payment; therefore, invoices have not been submitted. The roll-out of switching equipment in Q2, 2012 will bring the first invoices for the services of installation of microwave and switching equipment allowing this milestone to show significant progress at that time. | 64 | This milestone is on schedule. | 2012-02-27 15:35 | 2012-02-27 15:35 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2012 | Q1 | Q1 - 2012 | 6006 | 5602 | FALSE | 53 | When measured by expenditures, the overall project percentage complete is anticipated to be only 53%; however, the project is actually on schedule. Due to the structure of our purchasing documents with the main vendor on the project, microwave radio installations as well as switching equipment installations were quoted together per site. As a result, our vendor is unable to invoice us for services rendered until both the microwave radio and the switching equipment have been installed at each site. According to the current project schedule, a majority of the switching equipment installations are scheduled to be completed within the second and early third quarters, as a result, we expect this percent complete to increase exponentially to show agreement with the baseline in the third quarter of 2012. | 82 | Customer Acquisition, Support and Billing | During Q2, we anticipate reaching 82% completion on the Customer Acquisition, Support and Billing portion of the project with payment of signification portions of this milestone during the second quarter. | 100 | This milestone is complete. | 77 | Our Network Design milestone is anticipated to climb to 77% of completion in the second quarter with the payment of invoicing for tower analyses and path surveys associated with multiple minor route changes. It is also anticipated that our team will have determined some of the final engineering to connect to last mile service providers and community anchor institutions. | 0 | N/A. This milestone does not apply to our project. | 0 | N/A. This milestone does not apply to our project. | 100 | This milestone is expected to reach completion for all site preparation known as of the writing of this report; however, it is anticipated that there may be additional site preparation at one or more of the sites newly added to the project through a series of route changes. | 52 | During Q2, our crews will shift their main focus from microwave radio upgrades to the installation and configuration of switching equipment before moving back to the microwave radio upgrades once again. The installation and configuration of the switching equipment during Q2 will enable invoicing and payment of this equipment likely within Q3. These additional expenditures are anticipated to bring the Equipment Procurement milestone into agreement with the baseline report in Q3. | 100 | This milestone is complete. | 10 | As noted above in the Equipment Procurement milestone, according to schedule, our crews will shift their main focus during Q2 from microwave radio upgrades to the installation and configuration of switching equipment before moving back to the microwave radio upgrades once again. With the shift in focus to switching equipment, our crews will complete the "service" tasks at multiple sites allowing for invoicing of the services rendered. The receipt and payment of these invoices will allow our Equipment Deployment milestone progress to come into agreement with the baseline report within Q3. As noted previously, this milestone has been deficient in progress due to the procurement vessel presented by our vendor which tied the payment of services to completion of both microwave radio upgrades and installation /configuration of the switching equipment. | 72 | This milestone is expected to remain on schedule. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2012 | Q2 | Q2 - 2012 | 6936 | 6095 | FALSE | 80 | It is anticipated that our project will reach 80% of overall project completion during the third quarter of 2012 and drastically reduce the gap between the baseline's predicted progress and the actual project progress to date. Much of the gain in progress can be attributed to the roll out of switching equipment upgrades that are scheduled to commence in the third quarter. The completion of this work on a site by site basis will allow our equipment vendor to begin invoicing not only for the equipment that they have installed and configured, but also for the services for equipment installations. | 100 | Customer Acquisition, Support and Billing | We anticipate catching up to our baseline and completing this milestone during the third quarter of 2012 with the payment of invoices for the customer billing solution and provisioning tools. | 100 | This milestone is complete. | 77 | The network design milestone is expected to climb slightly to 77% complete during the third quarter. The remaining elements to complete within this milestone include the design of our connection to last mile and whole sale providers as well as tower analyses and documentation for sites included within a route change that is currently under review. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 90 | It is expected that all site preparation for the current project would be completed in the third quarter; however, due to the submission of an Award Action Request (AAR), we would have a small amount of site preparation to complete at the sites included within this request, which is currently under review. | 83 | With the start of switching equipment installations to occur within the third quarter, it is expected that we will receive invoices for that switching equipment as well as the switching hubs. These expenditures will push the progress of this indicator closer to the baseline's predicted progress. We also expect that the invoices for this work will continue into the fourth quarter where progress for the milestone will come into compliance with the baseline report. | 100 | This milestone is complete. | 60 | We anticipate the equipment deployment milestone to see a large number of expenditures toward the end of the third quarter with the completion of many of the switching equipment upgrades. Completion of this work will allow our equipment vendor to invoice for the services of installing and configuring the microwave radios as well as the MPLS switching equipment on a site by site basis. | 85 | We anticipate this milestone to catch up to the baseline with the payment of invoices for much of the quality assurance work associated with the switching upgrades. | 2012-08-08 16:07 | 2012-08-08 16:07 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2012 | Q3 | Q3 - 2012 | 7822 | 6614 | FALSE | 87 | A large portion of the remaining expenditures on this project remain tied to the completion of our switching equipment upgrades. Those upgrades are expected to wrap up within the fourth quarter of 2012. Once complete, the vendor responsible for installing this equipment as well as the microwave equipment will be able to submit invoices for these deployments since they have quoted the work together on a site by site basis. We believe, by the close of the fourth quarter of 2012, that we will have completed a total of 69 of the 71 microwave radio links. | 99 | Customer Acquisition, Support and Billing | This milestone is expected to be in agreement with our baseline and nearly complete by the close of the fourth quarter. | 100 | This milestone is complete. | 100 | This milestone is complete. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 99 | This milestone is expected to be in agreement with our baseline and nearly complete by the close of the fourth quarter. | 100 | This milestone is complete. | 80 | With the anticipated completion of our switching equipment upgrades during the fourth quarter, it is expected that a large portion of the invoices for equipment installations will be submitted and paid. With the approval of our most recent award action request (AAR), we anticipate the completion of another four microwave radio links and the invoices that would accompany this accomplishment as well. Knowing that the process to review and accept the vendor's work, document the changes to the site and submit an invoice takes time, it is believed that this category will not be completed until January of 2013 or possibly into our close out period. | 90 | This milestone is expected to be in agreement with our baseline by the close of the fourth quarter. | 2012-11-09 15:24 | 2012-11-09 15:24 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2012 | Q4 | Q4 - 2012 | 8778 | 7574 | FALSE | 92 | Our overall project will make significant progress in the first quarter with the anticipated arrival and payment of invoices for work completed in the fourth quarter. The vendor that is supplying our switching and microwave equipment had quoted the services to install both pieces of equipment together on a site by site basis, making them unable to invoice until the switching equipment had been installed and tested. We completed the assurance testing on those upgrades in mid December allowing the invoicing to begin. We also anticipate the receipt of invoices for equipment and the installation of our customer access platforms. Our percent complete will jump significantly to 92% and come close to agreement with the baseline predictions. | 100 | Customer Acquisition, Billing and Support | This milestone is expected to be in agreement with our baseline report and complete by the close of the first quarter. Completion of this milestone is reliant upon final end to end acceptance of the improved network to include billing and asset management. We are scheduled to complete testing of the network backbone in late January 2013. | 100 | This milestone is complete. | 92 | This milestone is on schedule. The network design that remains to be completed is in regard to the connections to our last mile service providers and Community Anchor Institutions. Due to the Commonwealth's requirement for the vendor to complete all work prior to invoicing, this milestone is expected to be complete just beyond the close of the first quarter of 2013. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 97 | The equipment procurement milestone will jump to 97% of completion in the first quarter of 2013 with the receipt of invoices for switching equipment as well as a few links of microwave radios. This progress will bring our project into agreement with the baseline report. | 100 | This milestone is complete. | 98 | The equipment deployment milestone will soar to 98% of completion in the first quarter of 2013 with the receipt of invoices for the installation of microwave and switching equipment. This progress will bring our project into agreement with the baseline report. | 87 | The network testing milestone will increase to 87% of completion in the first quarter of 2013 as invoices are paid for much of the testing involved with the upgrades to the switching equipment. This progress trails that of the baseline report; however, we anticipate closing this gap just beyond the close of the first quarter. | 2013-02-14 14:14 | 2013-02-14 14:14 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2013 | Q1 | Q1 - 2013 | 9774 | 8421 | FALSE | 97 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the end to end testing of the network and connections to last mile service providers and community anchor institutions. | 100 | Customer Acquisition, Support and Billing | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 100 | This milestone is complete. | 100 | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | We plan to complete this milestone within the second quarter of 2013 with the payment of all remaining invoices. | 99 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the connections to last mile service providers or community anchor institutions. | 100 | This milestone is complete. | 98 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the connections to last mile service providers or community anchor institutions. | 92 | We plan to have this milestone nearly complete within the second quarter of 2013. The only expenditures that we anticipate remaining would be associated with the end to end testing of the network. | 2013-05-16 14:59 | 2013-05-16 14:59 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2013 | Q2 | Q2 - 2013 | 10622 | 8971 | FALSE | 100 | This milestone is expected to be complete. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is expected to be complete. | 100 | This milestone is expected to be complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. | 100 | This milestone is expected to be complete. | 2013-08-16 14:28 | 2013-08-16 14:28 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | 2013 | Q3 | Q3 - 2013 | 11304 | 9451 | FALSE | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | Customer Acquisition, Support and Billing | This milestone is complete. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 0 | N/A This milestone does not apply to our project. | 0 | N/A This milestone does not apply to our project. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | This milestone is complete. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 100 | This milestone is expected to be complete. Invoicing during the closeout period will bring this milestone category to 100% completion. | 2013-11-20 10:48 | 2013-11-20 10:48 | 5684 | 5684 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570018 | 2010 | Q3 | Q3 - 2010 | 454 | 1493 | FALSE | 85 | No significant variance | 0 | N/A | N/A | 100 | No significant variance | 35 | No significant variance | 16 | No significant variance | 0 | N/A | 22 | No significant variance | 40 | No significant variance | 99 | Completion of acquisition of FAC for Puerto Rico-Florida span. | 7 | No significant variance | 2 | No significant variance | 2010-11-30 11:27 | 2010-11-30 11:27 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2010 | Q4 | Q4 - 2010 | 1354 | 2369 | FALSE | 89 | No significant variance | 0 |  | N/A | 100 | No significant variance | 57 | No significant variance. | 64 | Contract negotiations for towers to be completed but funds won't be disbursed. | 0 | N/A | 67 | Recruitment delays of Network Analyst reflected in expenditures | 47 | Equipment procurement is proceeding as expected. Initial delays were encountered in delivery of core routing/switching equipment as we received defective equipment that had to be returned. While situation has been resolved and we are on track, fund disbursement will be affected which affects the baseline milestones. | 99 | No significant variance | 11 | Recruitment delays of Network Analyst reflected in expenditures. | 6 | Recruitment delays of Network Analyst reflected in expenditures. | 2011-02-24 08:16 | 2011-02-24 08:16 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2011 | Q1 | Q1 - 2011 | 2412 | 2951 | FALSE | 90 | No significant variance | 0 |  | NA | 100 | No variance | 65 | No significant variance | 64 | Due to delays in contract negotiations for tower sites, disbursement for payment not anticipated in this quarter. | 0 | NA | 80 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures. | 45 | We anticipate completion of procurement selection process for RF equipment, however funds will not be disbursed in this quarter for payment on equipment. | 99 | No significant variance | 18 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures | 11 | Recruitment delays of Network Analyst, RF Engineer reflected in expenditures | 2011-05-31 16:37 | 2011-05-31 16:37 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2011 | Q2 | Q2 - 2011 | 2442 | 2966 | FALSE | 92 | No significant variance | 0 |  | N/A | 100 | No variance | 74 | No significant variance | 94 | We anticipate completion of contracts and dibursement of payment in this quarter. | 0 | N/A | 81 | Equipment will be received at the end of the quarter. | 47 | We anticipate completion of procurement selection process for RF equipment, however funds will not be disbursed in this quarter for payment on equipment. | 99 | No significant variance | 26 | While recruitment has been completed, original delays in staff recruiting continues to be reflected in expenditures | 16 | While recruitment has been completed, original delays in staff recruiting continues to be reflected in expenditures | 2011-07-11 18:21 | 2011-07-11 18:21 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2011 | Q3 | Q3 - 2011 | 4038 | 3859 | FALSE | 96 | 3% variance as a result of site acquisitions, delayed network equipment arrival. | 0 |  | N/A | 100 | No variance | 79 | No significant variance | 100 | Completion of acquisition of all wireless sites. | 0 | N/A | 95 | No variance | 88 | No variance | 99 | No variance | 35 | Wireless network equipment expected to arrive at the end of the quarter. | 19 | Wireless network equipment expected to arrive at the end of the quarter. | 2011-11-14 16:14 | 2011-11-14 16:14 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2011 | Q4 | Q4 - 2011 | 4962 | 4635 | FALSE | 97 | No variance from baseline | 0 |  | NA | 100 | No variance from baseline | 93 | 6% variance from baseline due to redesign and engineering of network and preparation of route change. | 100 | Actual Milestone Value: 101.78%. Exceeded original budget due to expansion of network route in approved route change and acquisition of additional tower sites. Program Income will be used to fund additional costs. | 0 | NA | 95 | 2% variance from baseline. | 100 | Actual Milestone Value 104%. This milestone has exceeded the original budget because of (a) additional equipment costs due to approved route change and (b) increase in valuation of an in-kind contribution as approved by the grants office and will be booked this quarter. Program Income will be used to fund the necessary equipment for the route change. | 99 | No variance from baseline | 45 | Variance of 17% due to route change approval process. Equipment has been procured, and we anticipate the receipt in middle of quarter, and initiation of deployment at end of quarter. | 38 | 8% variance due to route change and delays in equipment deployment. | 2012-02-13 10:38 | 2012-02-13 10:38 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2012 | Q1 | Q1 - 2012 | 6178 | 5691 | FALSE | 98 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 98 | Exceeded baseline due to increased costs associated with route change. | 100 | Actual Milestone Value: 102%. Exceeded original budget due to expansion of network route in approved route change and acquisition of additional tower sites. Program Income will be used to fund additional costs. | 0 | N/A | 96 | Variance of 2% due to delays subject to route change & FCC license delays | 100 | Actual Milestone Value 109%. This milestone has exceeded the original budget because of (a) additional equipment costs due to approved route change and (b) increase in valuation of an in-kind contribution as approved by the grants office and will be booked this quarter. Program Income will be used to fund the necessary equipment for the route change. | 99 | No significant variance from baseline | 54 | 18% variance due to route change, pending FCC licenses | 48 | 9% variance due to route change, pending FCC licenses | 2012-05-18 11:07 | 2012-05-18 11:07 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2012 | Q2 | Q2 - 2012 | 6926 | 6090 | FALSE | 98 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | No significant variance from baseline | 100 | No significant variance from baseline | 0 | N/A | 98 | No significant variance from baseline | 92 | Procurement of licensed wireless equipment delayed due to FCC license issuance delays. | 99 | No significant variance from baseline | 65 | Deployment delayed due to FCC license issuance delays | 59 | Testing delayed due to FCC license issuance delays | 2012-08-08 14:34 | 2012-08-08 14:34 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2012 | Q3 | Q3 - 2012 | 7812 | 6609 | FALSE | 99 | No significant variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 95 | No significant variance from baseline | 100 | Actual 101.99% Exceed budget due to approved network route change and acquisition of additional tower sites. | 0 | N/A | 98 | No significant variance from baseline | 98 | Variance due to final procurement of equipment for last POI as submitted under Route Change | 99 | No variance from baseline | 79 | Deployment delayed because of FCC license issuance delays. | 70 | Testing delays due to deployment delays. | 2012-11-09 11:20 | 2012-11-09 11:20 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2012 | Q4 | Q4 - 2012 | 8716 | 7520 | FALSE | 100 | Actual: 99.7%. Variance due to expenditures pending disbursement related to closeout of project, including audit & legal. | 0 |  | NA | 100 | No variance | 100 | No variance | 100 | No variance | 0 | NA | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-02-12 08:50 | 2013-02-12 08:50 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2013 | Q1 | Q1 - 2013 | 9880 | 8478 | FALSE | 99 | Extension received in February 2013 to permit expansion of project to include PRBI-TU segment | 0 |  | NA | 100 | NA | 100 | Actual 104%, due to final design work of PRBI-TU segment | 100 | No variance | 0 | NA | 100 | We anticipate this will exceed 100% in next quarter, as we will incur costs related to expanded PRBI-TU segment which was not included in original baseline. | 99 | Variance due to expansion of project. | 99 | Variance due to expansion of project. | 89 | Variance due to expansion of project. | 85 | Variance due to expansion of project. | 2013-05-23 08:42 | 2013-05-23 08:42 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2013 | Q2 | Q2 - 2013 | 10708 | 9017 | FALSE | 100 | Extension approved through September 30, 2013. | 0 |  | NA | 100 | No variance | 100 | Project completion date: September 30, 2013 | 100 | No variance | 0 | NA | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 100 | Project completion date: September 30, 2013 | 2013-08-23 11:19 | 2013-08-23 11:19 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570018 | 2013 | Q3 | Q3 - 2013 | 11632 | 9752 | FALSE | 100 | Project Closeout Period End Date: 12/28/2013 | 0 |  | NA | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 0 | NA | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 100 | Project Closeout Period End Date: 12/28/2013 | 2014-01-21 11:27 | 2014-01-21 11:27 | 5487 | 5487 | Critical Hub Networks, Inc
NT10BIX5570019 | 2010 | Q3 | Q3 - 2010 | 298 | 1415 | FALSE | 20 | No Information to add at this time. | 0 |  | N/A | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 100 | No Information to add at this time. | 35 | No Information to add at this time. | 0 | N/A | 15 | No Information to add at this time. | 0 | N/A | 0 | N/A | 2010-11-01 11:20 | 2010-11-01 11:20 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2010 | Q4 | Q4 - 2010 | 1130 | 2168 | FALSE | 20 | Construction delayed due to approval of PA. | 0 |  | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | VMRC permit requires fifteen day comment period. Delay possible. | 45 | EA approval 12-7-10. Weather may delay completion of site preparation. | 0 | Delay in construction which delays start of equipment procurement to Y2Q2. | 15 | Weather ill hinder construction activities. | 0 | Delay in construction delays start of equipment deployment to Y2Q2. | 0 | Zero Variance | 2011-02-14 11:43 | 2011-02-14 11:43 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2011 | Q1 | Q1 - 2011 | 2094 | 2792 | FALSE | 30 | Delay in EA and PA delayed construction start date. Adding more contractors will improve productivity. | 0 |  | N/A | 95 | Awaiting design changes | 100 | N/A | 100 | N/A | 100 | N/A | 40 | Bidding Process delayed start of construction | 100 | N/A | 30 | Construction start delayed by PA approval. Equipment to be received in Y2Q2 & Y2Q3 | 15 | Delay in price quotes delayed procurement. While the deployment has been delayed, equipment deployment can be worked in conjunction with the cable construction component once the site work is completed. We should complete the equipment deployment by the time the cable is available. | 0 | N/A | 2011-05-17 15:09 | 2011-05-17 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2011 | Q2 | Q2 - 2011 | 2990 | 3252 | FALSE | 55 | Construction start delayed until March 2011. Project to be 55% complete by end of Y2Q3. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 50 | Construction on nodes/site preparation started 7-15-11. Should complete 2 of the 4 sites by end of Y2Q3. | 100 | To receive remainder of transport equipment be end of Y2Q3. | 67 | Construction start delayed until March 2011. Equipment delivery, including fiber optic cable and transport equipment, has been delayed by vendors. We expect to begin equipment installation in 8-11 and to place approximately 120 miles of cable in Y2Q3. | 40 | Remainder of equipment to be received in Y2Q3. Installation to begin 8-11 and complete by 11-2011. | 40 | Will begin network testing as nodes (huts) are completed and as network equipment is received and installed. Both should be completed in Y2Q4. | 2011-08-09 16:54 | 2011-08-09 16:54 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2011 | Q3 | Q3 - 2011 | 4004 | 3841 | FALSE | 55 | Project to be 55% complete in Y2Q4. | 0 |  | N/A | 100 | Timely submission of any feedback questions; SHPO consultation report received by 11-3-11.EA submitted to NTIA by 11-15-11 | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Additional resources to make up for loss time due to inclement weather. | 100 | Ensure all equipment is received from vendor and payment is processed. | 84 | Expect to complete nodes and place 95 miles of fiber in Y2Q4. | 50 | Install equipment in 2 node sites. Complete deployment by Y3Q1. | 60 | Test completed backbone cable and 2 node sites. Complete testing by Y3Q1. | 2011-11-14 09:00 | 2011-11-14 09:00 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2011 | Q4 | Q4 - 2011 | 4866 | 4565 | FALSE | 77 | Will complete remaining construction. Final billing & equipment testing to complete Y3Q3. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | To be completed Y3Q3. Delayed due to site preparation delay. | 75 | To be completed Y3Q3 | 2012-02-03 14:37 | 2012-02-03 14:37 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2012 | Q1 | Q1 - 2012 | 5966 | 5582 | FALSE | 71 | Became evident in Y3Q1 that project would be under budget. Submit a budget modification and route modification for approval in Y3Q2. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 21 miles in segment 1, 4 & 5 in Y3Q2 | 85 | To be completed Y3Q3. Delayed due to site preparation delay. | 85 | To be completed Y3Q3 | 2012-05-08 14:24 | 2012-05-08 14:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2012 | Q2 | Q2 - 2012 | 6952 | 6103 | FALSE | 84 | Submitted route modification to expend the remaining budgeted amount by Y3Q4 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete remaining 8 miles in Y3Q3 | 100 | To be completed in Y3Q3; manpower issues | 100 | To be completed in Y3Q3 | 2012-08-09 09:27 | 2012-08-09 09:27 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2012 | Q3 | Q3 - 2012 | 7754 | 6571 | FALSE | 98 | Project to be completed by end of Y3Q4 | 0 |  | N/A | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 100 | Project to be completed by end of Y3Q4 | 2012-11-01 13:35 | 2012-11-01 13:35 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2012 | Q4 | Q4 - 2012 | 8666 | 7487 | FALSE | 93 | Project extension requested to complete route modification to VSU. Delayed due to easements | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Cannot complete until all cable is competed | 98 | Cannot complete until all equipment is installed | 2013-02-07 16:14 | 2013-02-07 16:14 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2013 | Q1 | Q1 - 2013 | 9608 | 8335 | FALSE | 96 | Approved route modification to be completed by approved project extension date of 6-30-13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-06 09:59 | 2013-05-06 09:59 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | 2013 | Q2 | Q2 - 2013 | 12310 | 10483 | FALSE | 100 | Complete; 95% of Grant amount spent | 0 |  | N/A | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 100 | Complete; 95% of Grant amount spent | 2014-07-18 15:24 | 2014-07-18 15:24 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570023 | 2010 | Q3 | Q3 - 2010 | 12014 | 10177 | FALSE | 30 | Final network design (physical layer) complete, equipment procurement and leasing of commercial towers underway. Delay due to engineering re-evaluation has pushed our expectation for negotiation of all leases beyond this quarter. While substantial progress will be made, the percentage complete (based on dollars spent) will be lower than planned in baseline. We will be fully back on schedule in the subsequent quarters. | 35 | In-kind Contributions | On target | 0 | Exempt | 85 | On Target | 0 | N/A | 30 | The Project Management Office will establish permitting procedures for each county and streamline the overall permitting process. However, permitting for deployment of radios and site equipment will only be complete for a limited number of sites. | 30 | Site preparation will remain behind schedule this quarter due to the delays resulting from re-evaluation of engineering design in the previous quarter. Site preparation should be caught up in subsequent quarters. | 50 | RFPs completed, advertised, and distributed, and vendors selected. Evaluation/selection scheduled to be complete by the end of the next quarter. However, contracting (including proof of concept) will not be complete until the following quarter. Again, as a result of engineering delays. | 25 | Slight modification in requirements of Level 3 IRU orders/delivery as a result of revised engineering design have delayed initiation of Level 3 execution of certain orders (by our request). Level 3 will endeavor to accelerate delivery once final design requirements are completed. | 0 | Contracting (including proof of concept) of equipment vendors won't be complete until the following quarter due to delays resulting from revised engineering design as referenced above. | 0 | Network testing follows equipment deployment and has therefore been moved forward to later in the schedule due to delays resulting from revised engineering design as referenced above. | 2014-03-31 22:18 | 2014-03-31 22:18 | 6524 | 6524 | North Florida Broadband Authority
NT10BIX5570023 | 2010 | Q4 | Q4 - 2010 | 1352 | 2367 | FALSE | 50 | As mentioned above, the re-evaluation of the network design approach that began in previous quarters and continued through this reporting quarter resulted in an overall project delay and has impacted most major milestone categories, including site preparation, equipment procurement, network build, equipment deployment, network testing, and in-kind lease agreements, where further progress was originally anticipated according the Baseline Report. While substantial progress continues to be made in regard to network design and equipment deployment, the percentage complete (based on dollars spent) remains lower than planned in the baseline plan for this reporting period. We expect to be fully back on schedule in subsequent quarters, as indicated by the planned completion percentages listed below. | 45 | Commercial Tower Leases | On-target. We will continue the process of checking for previous / duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. | 0 | Exempt | 88 | Network design is expected to remain on schedule, with final structural assessments completed by next quarter. | 0 | N/A | 50 | Permitting for deployment of radios and site equipment will be complete for a limited number of sites. Tower company certification requirements and application procedures will be established, and the application process is expected to be initiated next quarter. | 50 | It is our expectation that site preparation will get back on track with the baseline reportâ€™s scheduled completion percentages in subsequent quarters upon execution of commercial tower leases, which are pending Grants Office review and approval of the tower lease language. | 93 | Equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this current reporting period. Therefore, we anticipate equipment procurement to be on schedule by the end of next quarter. | 89 | Contract with Level 3 is in place. Upstream design configuration is complete, and circuit delivery is on schedule. Installation of data center equipment at Level 3â€™s Tampa and Orlando co-location facilities is expected to get underway next quarter. | 30 | As noted above, revised engineering design is nearly complete, equipment RFPs were released, equipment vendors were selected and approved, and initial equipment purchase orders were executed during this current reporting period. Therefore, we anticipate that equipment deployment should get back on schedule over the next two quarters, notwithstanding any potential delays from pending Davis-Bacon wage decision requests and the Grants Office review and approval of our tower lease agreement language. | 20 | As network testing is closely tied to equipment deployment, we anticipate that this milestone category will be back on schedule over the next two quarters, notwithstanding any potential delays from pending Davis-Bacon wage decision requests and the Grants Office review and approval of our tower lease agreement language. | 2011-02-24 07:24 | 2011-02-24 07:24 | 5502 | 5502 | North Florida Broadband Authority
NT10BIX5570023 | 2011 | Q1 | Q1 - 2011 | 2216 | 2853 | FALSE | 50 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As we continue to make progress with site acquisition and pre-deployment activities, we anticipate that the overall project completion schedule will be back in line with Baseline Plan projections in subsequent quarters. | 5 | In-Kind Tower Licenses | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As part of our efforts to catch up to the Baseline Plan, the North Florida Broadband Authority's General Counsel has been working closely with the Grants Office and the Program Office to finalize the format and acceptable language required in all lease documents for the project, including the in kind leases. | 0 | N/A. Categorically exempt from Environmental Assessment. | 91 | Network design is expected to remain on schedule. | 0 | N/A | 60 | Building permit acquisition is expected to remain on schedule. | 0 | Progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Quotes procurement document for Civil and Electrical Site Work. As noted in Section 1, Item #3, we are in the process of preparing a budget reallocation Award Action Request to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 40 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. Equipment procurement is currently moving forward with purchase orders and invoices being processed for all network equipment categories. Therefore, we anticipate that this milestone category will be back in line with the Baseline Plan over the next two quarters | 65 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We expect the majority of structural assessments and site license agreements to be complete by the end of the next quarter, and therefore we anticipate that Network Build progress will be back in line with the Baseline Plan by the end of the next quarter. | 20 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We anticipate that Equipment Deployment will be on track with the Baseline Plan over the next two to three quarters. | 15 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As Network Testing is coordinated with Equipment Deployment, we expect that this milestone category will also be be back on track with the Baseline Plan over the next two to three quarters. | 2011-05-20 14:13 | 2011-05-20 14:13 | 6621 | 6621 | North Florida Broadband Authority
NT10BIX5570023 | 2011 | Q2 | Q2 - 2011 | 3216 | 3369 | FALSE | 54 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As we continue to make progress with ongoing site acquisition and network deployment activities, we anticipate that the overall project completion schedule will be back in line with Baseline Plan projections in subsequent quarters. | 5 | In-Kind Contributions | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As part of our efforts to catch up to the Baseline Plan, we are re-establishing our efforts to execute in-kind asset leases as lateral site acquisition is being dove-tailed into the beta and early adopter customer acquisition process. | 0 | N/A. Categorically exempt from Environmental Assessment. | 94 | Network design is expected to remain on schedule. | 0 | N/A | 70 | Building and electrical permit acquisition is expected to remain on schedule. | 0 | In previous Performance Progress Reports (submitted prior to the Performance Progress Report for 1st Quarter 2011), progress reported for this milestone category in previous Performance Progress Reports was attributed to the progress of work associated with the development of the Request for Quotes procurement document for Civil and Electrical Site Work. As noted in Section 1, Item #3, we prepared a draft budget reallocation Award Action Request to submit for review and approval to the Program Office to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be re-allocated to other Cost Classification categories. | 57 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. Equipment procurement continues to move forward as purchase orders for network equipment are being executed, invoiced, and paid on an ongoing basis. Microwave radios and antennas are also currently being purchased, received, inventoried, and staged for deployment. | 57 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. We expect final fiber connections and testing to be completed at our four Point of Presence sites and also our two datacenter locations by the end of the next reporting period. We also expect significant expenditures for tower lease payments that were pending modification of site license agreements that had stemmed fro | 70 | This milestone category is currently scheduled to catch up to Baseline Plan projections by the end of next quarter. | 20 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. As Network Testing is follows in closely behind Equipment Deployment, we expect that this milestone category will also be be back on track with the Baseline Plan over the next two quarters. | 2011-08-18 18:34 | 2011-08-18 18:34 | 5502 | 5502 | North Florida Broadband Authority
NT10BIX5570023 | 2011 | Q3 | Q3 - 2011 | 4358 | 4035 | FALSE | 69 | Prior to the suspension of grant funding, planned project progress was expected to be at 89%, based on our estimated projections for expenditures for 4th quarter of 2011. We would have therefore exceeded our original Baseline Plan projection of 87.13% for overall project completion for the next quarter. | 100 | In-Kind Contributions | We confirmed our inventory of committed in-kind contributions for our Federal match requirement. As Federal funding is fully reinstated, we fully expect to make substantial progress toward booking these assets over the next reporting period. | 0 | N/A. Categorically exempt from Environmental Assessment. | 96 | Network design is expected to be on schedule. | 0 | N/A | 80 | Building and electrical permit acquisition is expected to remain on schedule. | 100 | We prepared a draft budget reallocation Award Action Request to submit for review and approval to the Program Office to reconcile or adjust our SF-424C budget categories that were originally based on the turnkey link network design project plan. Upon approval of the Award Action Request, the budget amount originally allocated for Site Preparation will be reallocated to other Cost Classification categories. | 96 | The anticipated progress referenced here would have been the actual progress made in the 3rd Quarter of 2011 had Federal funds not been suspended. Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to reach our Baseline goal for Equipment Procurement by next reporting period. | 94 | Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to reach our Baseline goal for this Milestone category by next reporting period. | 80 | Upon reinstatement of Federal funding (expected to occur in late October 2011), we fully expect to reach our Baseline goal for this Milestone category as site-specific equipment installation resumes next reporting period. | 40 | Upon reinstatement of Federal funding (expected to occur in October 2011), we fully expect to make significant progress toward our original Baseline projection for this Milestone category by next reporting period as network testing will follow closely behind equipment deployment. | 2011-11-30 16:32 | 2011-11-30 16:32 | 6621 | 6621 | North Florida Broadband Authority
NT10BIX5570023 | 2011 | Q4 | Q4 - 2011 | 5384 | 5058 | FALSE | 71 | Most efforts during 4th quarter were to execute the transition plan and reinstate project funding. | 71 | In-kind | NFBA will work to memorialize the terms of individual site licenses with the contributing County governments. | 0 | n/a | 100 | Pending budget reallocation, current design evaluation and adjustments are being documented. | 0 | n/a | 85 | Pending Budget Reallocation currently underway, most permits have been obtained and transferred to Engineering. | 100 | Pending Budget Reallocation currently underway, Site preparation against current baseline shows completion. Once Budget reallocation is complete, this number will be adjusted to represent reality. | 96 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 95 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 70 | Budget Reallocation is currently underway where the budget will be reallocated accordingly. | 40 | Most efforts during the quarter were focused on executing the transition plan and building an organization to provide the necessary project oversight. | 2012-02-29 07:30 | 2012-02-29 07:30 | 7368 | 7368 | North Florida Broadband Authority
NT10BIX5570023 | 2012 | Q1 | Q1 - 2012 | 6076 | 5637 | FALSE | 83 | We are in position to complete core network deployment by the end of next quarter, and we will connect more customers as network sites are activated, tested, and made available for customer access. | 90 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Our core network design is functionally complete. However, we are continuing to work with demand forecasts in order to incorporate an enhancement plan that will address the original limitations in capacity and meet forecasted demand. We anticipate approval of our Budget Reallocation Award Action Request, which will address the cost impacts associated with this process. | 0 | N/A | 100 | All site permits have been obtained and transferred to our new General Contractor. | 100 | We anticipate approval of our Budget Reallocation Award Action Request, which will allow us to adjust the budget number for this category and establish a more accurate benchmark for measuring cost and schedule performance. | 98 | We expect to be on target with our baseline projection for this category. We also anticipate approval of our Budget Reallocation Award Action Request, which will reallocate any budget surplus in this category to other areas of need. | 98 | We expect to be on target with our baseline projection for this category, as we are in position to make a substantial progress payment on our Indefeasible Right of Use for upstream fiber access in the next reporting period. We also anticipate approval of our Budget Reallocation Award Action Request, which will reallocate any budget surplus in this category to other areas of need. | 90 | We expect to be on target with our baseline projection for this category. | 90 | We expect to be on target with our baseline projection for this category. | 2012-05-14 21:46 | 2012-05-14 21:46 | 6621 | 6621 | North Florida Broadband Authority
NT10BIX5570023 | 2012 | Q2 | Q2 - 2012 | 7190 | 6222 | FALSE | 88 | Variance from the baseline plan is due to challenges faced this reporting period in addition to residual effects from transition-related issues that began in previous quarters. Please see Section 3 above for more details. We remain in position to complete our core network deployment by the end of next quarter, and we will continue to connect more customers as more network sites are activated, tested, and made available for customer access. | 95 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 90 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We will continue to work with demand forecasts to drive our network design enhancement plan, which is being implemented in parallel with network deployment as we move outward from our Fiber Access Points, through the core network, and into the communities that will be served by our network. | 0 | N/A | 99 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We expect to be on target with our baseline projection for this category. Approval of resubmitted permit applications from local permitting agencies is expected next quarter. Please see section 3 above for more details. | 99 | Planned progress is projected against our approved revised budget, resulting in the anticipated completion percentage being decreased for this milestone category in comparison to our previous Performance Progress Report. We expect to be on target with our baseline projection for this category. | 99 | We expect to be on target with our baseline projection for this category. | 99 | We expect to be on target with our baseline projection for this category. | 95 | We expect to be on target with our baseline projection for this category. | 95 | We expect to be on target with our baseline projection for this category. | 2012-08-21 14:47 | 2012-08-21 14:47 | 7368 | 7368 | North Florida Broadband Authority
NT10BIX5570023 | 2012 | Q3 | Q3 - 2012 | 7952 | 6681 | FALSE | 95 | Our core network will be fully operational by the end of next quarter, and in that regard we are on target with our baseline projection for core network completion. In order to ensure that our network is capable of meeting customer demand according to Service Level Agreement requirements, we anticipate that our current and planned network enhancement activities will continue beyond the end of next quarter through the end of the federal grant period. | 98 | In-Kind Contributions for Recipient Match | We expect to be on target with our baseline projection for this category. We will continue to memorialize the terms of individual site license agreements with our contributing member governments, and we expect to maintain proportionality with federal expenditures as required. | 0 | N/A. Categorically exempt from Environmental Assessment. | 96 | Core network design is functionally complete. However, we are continuing to address the performance and capacity limitations of our pre-transition period network design. We will therefore continue to work with demand forecasts to drive our network design enhancement plan, and will remain engaged with executing concurrent processes of identifying strategic core network locations for enhancement and finalizing network enhancement equipment specifications. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work will be complete at our last remaining core network tower site by the end of next quarter. | 100 | Core network equipment procurement is complete. However, we anticipate that procurement activities for network enhancement equipment will continue beyond the end of next quarter through the end of the federal grant period. | 99 | Site acquisition is complete for our core network datacenters, fiber access points, and core tower sites. However, as part of our network enhancement effort, we will continue to explore options and conduct cost/benefit analysis for increasing the quantity of fiber access points at strategic areas of our core network. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 96 | Core network equipment installation will be complete at our last remaining core network tower site by the end of next quarter. However, the installation of additional licensed microwave radios and antennas at selected core tower sites is planned as part of our network enhancement effort. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 96 | Core network equipment testing will be complete by the end of next quarter. However, testing of additional licensed microwave radios and antennas at selected core tower sites is planned as part of our network enhancement effort. We expect this activity to continue past the end of next quarter through the end of the federal grant period. | 2012-11-19 10:31 | 2012-11-19 10:31 | 7368 | 7368 | North Florida Broadband Authority
NT10BIX5570023 | 2012 | Q4 | Q4 - 2012 | 9072 | 7846 | FALSE | 100 | Our core network is complete and fully operational. We will continue with our network enhancement activities while building links out from the core network by using our in kind tower sites to create lateral extensions to reach target customers and facilitate connectivity to Community Anchor Institutions. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets into our roll-out schedule as lateral extensions of our core network to reach our target customers and connecting Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is complete. We will continue with ongoing link design and engineering activities as necessary to build out from our new Fiber Access Point and to activate lateral network extensions with our in kind towers. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at all of our core network tower sites. | 100 | Core network equipment procurement is complete. We will continue with equipment procurement activities as necessary to build out our in kind tower sites to reach target customers, as well as to ensure that network capacity and performance are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network datacenters, original fiber access points, and core tower sites. We will continue to explore options and conduct cost/benefit analysis for integrating additional fiber access points at strategic areas of our core network. | 100 | Core network equipment deployment is complete. We will continue to install additional licensed microwave radios and antennas at selected core tower sites as part of our ongoing network enhancement effort. We will also continue to install equipment as necessary to build out our in kind tower sites to reach our target customers and facilitate connectivity to Community Anchor Institutions. | 100 | Core network equipment testing is complete. We will continue with testing and commissioning activities as additional links are brought online to integrate our new Fiber Access Point and our in-kind towers. | 2013-02-28 13:09 | 2013-02-28 13:09 | 7368 | 7368 | North Florida Broadband Authority
NT10BIX5570023 | 2013 | Q1 | Q1 - 2013 | 9748 | 8408 | FALSE | 99 | We will continue to expand our network by using our in kind tower sites as lateral extensions of our core network to reach target customers and facilitate connectivity to Community Anchor Institutions. As noted above, our Award Action Request to extend our grant period to September 30, 2013 was approved, and therefore, milestone percent complete quantities projected for next quarter may vary from our original baseline plan projections, as these were based on percent complete estimates corresponding to the original January 31, 2013 project completion date. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach our target customers and to connect Community Anchor Institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design is complete. We will continue with ongoing link design and engineering activities as necessary to build out from our new fiber access point and to activate lateral network extensions with our in kind towers. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at all of our core network tower sites. | 100 | Core network equipment procurement is complete. We will continue with equipment procurement activities as necessary to build out our in kind tower sites to reach target customers, as well as to ensure that network capacity and performance are aligned with forecasted customer demand. | 100 | Site acquisition is complete for our core network data centers, original fiber access points, our new Palatka fiber access point, and core tower sites. We will continue to explore options for integrating additional fiber access points at strategic areas of our core network as necessary to ensure that network capacity and performance are aligned with forecasted customer demand. | 99 | Core network equipment deployment is complete. We will continue to install additional licensed microwave radios and antennas at selected core tower sites as part of our ongoing network enhancement effort. We will also continue to install equipment as necessary to build out our in kind tower sites to reach our target customers and facilitate connectivity to Community Anchor Institutions. | 99 | Core network equipment testing is complete. We will continue with testing and commissioning activities as additional links are brought online for the integration of our new Fiber Access Point and our in-kind towers. | 2013-05-15 16:39 | 2013-05-15 16:39 | 7368 | 7368 | North Florida Broadband Authority
NT10BIX5570023 | 2013 | Q2 | Q2 - 2013 | 12012 | 10176 | FALSE | 100 | The project will be complete by the end of the next quarter. We will continue to expand our network by building-out in-kind tower infrastructure to reach more customers. We will also continue to develop relationships with last mile providers, utility companies, anchor institutions, and strategic partners to ensure sustainability and growth so that our network will continue to be a source of opportunity for economically distressed businesses in our communities. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach target customers and to enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design and enhancement strategy activities are complete. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil and site electrical work is complete at our core network tower sites and fiber access points. | 100 | Core network equipment procurement is complete. We will continue to reinvest in our network infrastructure and proceed with equipment procurement as necessary to build out our in kind tower sites to reach target customers and to ensure that network capacity and performance are aligned with customer demand forecasts. | 100 | Site acquisition is complete for our core network data centers, fiber access points, and core tower sites. | 100 | Core network equipment deployment is complete. We will continue to reinvest in our network infrastructure and install equipment as necessary to build out our in kind tower sites to reach target customers and facilitate connectivity to community anchor institutions. | 100 | Core network equipment testing is complete. We will continue with testing and commissioning activities as lateral links are brought online through the integration of our in-kind tower infrastructure. | 2014-03-31 22:13 | 2014-03-31 22:13 | 6524 | 6524 | North Florida Broadband Authority
NT10BIX5570023 | 2013 | Q3 | Q3 - 2013 | 11446 | 9564 | FALSE | 100 | The project is 100% complete, as determined by total federal expenditures plus allowable in-kind contributions for recipient match. We will continue to reinvest and expand our network and develop relationships with last mile providers, utility companies, anchor institutions, and strategic partners to ensure the sustainability and growth of our network. | 100 | In-Kind Contributions for Recipient Match | We will continue to incorporate in-kind assets as lateral extensions of our core network to reach target customers and enable connectivity to community anchor institutions. | 0 | N/A. Categorically exempt from Environmental Assessment. | 100 | Core network design and enhancement strategy activities are complete. | 0 | N/A | 100 | Permitting is complete for our core network tower sites. | 100 | Civil site preparation and site electrical work is complete at our core network tower sites and fiber access points. | 100 | Core network equipment procurement is complete. We will continue to reinvest in our network infrastructure and proceed with equipment procurement as necessary to build out our in kind tower sites to reach target customers and enable connectivity to community anchor institutions. | 100 | Site acquisition is complete for our core network data centers, fiber access points, and core tower sites. | 100 | Core network equipment deployment is complete. We will continue to reinvest in our network infrastructure and deploy network access equipment as necessary to build out our in kind tower sites to reach target customers and facilitate connectivity to community anchor institutions. | 100 | Testing is complete for core network equipment. We will continue with testing and commissioning activities as lateral links are brought online through the integration of our in-kind tower infrastructure. | 2013-12-06 14:31 | 2013-12-06 14:31 | 6524 | 6524 | North Florida Broadband Authority
NT10BIX5570024 | 2010 | Q3 | Q3 - 2010 | 334 | 1433 | FALSE | 36 | No variance to Baseline Report | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 0 | No variance to Baseline Report | 2010-11-17 11:08 | 2010-11-17 11:08 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2010 | Q4 | Q4 - 2010 | 1052 | 2090 | FALSE | 45 | No variance to Baseline Report | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 20 | No variance to Baseline Report | 20 | No variance to Baseline Report | 17 | No variance to Baseline Report | 17 | No variance to Baseline Report | 16 | No variance to Baseline Report | 16 | No variance to Baseline Report | 16 | No variance to Baseline Report | 2011-02-10 14:47 | 2011-02-10 14:47 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2011 | Q1 | Q1 - 2011 | 2074 | 2782 | FALSE | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 40 | No variance to Baseline Report | 40 | No variance to Baseline Report | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 34 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete site preparations, network build out and CAI testing and turn up for the forty (40) CAI projects scheduled for completion this quarter. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require pre payment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 15 | The U of U/UEN is projecting this milestone will not meet projected percentage of completion for the upcoming quarter. Although significant project progress will be made the amount of funds spent will be less than projected in the Baseline Report. The higher cost project activities, such as those with significant outside plant construction, are not scheduled to begin until the third quarter of this project year. The U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 2011-05-17 10:15 | 2011-05-17 10:15 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2011 | Q2 | Q2 - 2011 | 3300 | 3412 | FALSE | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 60 | No variance to Baseline Report | 60 | No variance to Baseline Report | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 51 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete site preparations, network build out and CAI installations required to meet project milestones. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 22 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are ahead of schedule with the network construction and build out, the U of U/UEN's billing policy does not require prepayment to sub recipients for work being performed. As such, the draw down of Federal Funds will follow project completion activities and the invoicing of work completed by sub recipients. | 2011-08-24 17:52 | 2011-08-24 17:52 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2011 | Q3 | Q3 - 2011 | 4152 | 3924 | FALSE | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 80 | No variance to Baseline Report | 80 | No variance to Baseline Report | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 68 | This milestone is on schedule. The U of U/UEN will pre-order the equipment and supplies needed to complete the site preparations, network build out and CAI installations required to meet project milestones. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 26 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 2011-11-18 17:35 | 2011-11-18 17:35 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2011 | Q4 | Q4 - 2011 | 4950 | 4628 | FALSE | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 100 | The U of U/UEN is expecting all equipment purchases will be completed during this quarter. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 50 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although we continue to make significant progress and are on schedule with the network construction and build out, the U of U/UEN's billing policy doesn't require prepayment to sub recipients for work being performed. As such, the draw down of federal funds follow project completion activities and the invoicing of work completed by sub recipients. | 2012-02-10 16:38 | 2012-02-10 16:38 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2012 | Q1 | Q1 - 2012 | 6332 | 5768 | FALSE | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 | N/A | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 90 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. The Optronics for the Logan Middle Mile segment is the only outstanding equipment to be procured and cannot be ordered until fiber characterization is completed, which is scheduled for the second quarter. This schedule will permit lighting of the fiber for the Logan Middle Mile segment in the third quarter as projected. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 45 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-05-29 16:00 | 2012-05-29 16:00 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2012 | Q2 | Q2 - 2012 | 6906 | 6079 | FALSE | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 0 |  | N/A | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 100 | No variance to Baseline Report | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 100 | No variance to Baseline Report | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 56 | The U of U/UEN expects this milestone will not meet the projected percentage of completion for the upcoming quarter. Although the project build out and implementation is on schedule the federal funds expended is less than projected. The U of U/UEN billing process does not allow payment to sub-recipients until work is completed. As such, the draw down of federal funds is delayed and will follow the completion of construction and network build out activities. | 2012-08-07 16:40 | 2012-08-07 16:40 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2012 | Q3 | Q3 - 2012 | 7330 | 6294 | FALSE | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 66 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2012-10-12 15:30 | 2012-10-12 15:30 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2012 | Q4 | Q4 - 2012 | 8656 | 7481 | FALSE | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 68 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 1st quarter of 2013. Aside from some invoicing and related payments that may carry over into the close out period, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2013-02-06 18:01 | 2013-02-06 18:01 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2013 | Q1 | Q1 - 2013 | 10034 | 8567 | FALSE | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 0 | N/A | N/A | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 100 | No variance to Baseline Report. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 100 | No variance to Baseline Report. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 93 | The U of U/UEN is projecting that the Utah's Broadband Technologies Program project, Utah Anchors: A Community Broadband Project, will be completed in the 2nd quarter of 2013. Aside from some invoicing and related payments that may carry over into the 3rd quarter of 2013, the projection for overall percentage of completion represents actual expenditures. The actual costs for construction activities were less than budgeted. | 2013-05-31 15:46 | 2013-05-31 15:46 | 5423 | 5423 | University of Utah, The
NT10BIX5570024 | 2013 | Q2 | Q2 - 2013 | 12234 | 10405 | FALSE | 100 | The U of U/UEN completed the Utah's Broadband Technology Opportunities Program project, Utah Anchors: A Community Broadband Project on May 31st, 2013. This percentage for overall completion represents actual expenditures. | 0 | N/A | N/A | 100 | The NTIA approved the U of U/UEN Environmental Assessment and issued a Finding of No Significant Impact (FONSI) in November of 2010. | 100 | All network designs and contracts with Telecommunication Providers have been completed. | 100 | All Rights of Way for this project have been approved and build out is underway. | 100 | All Construction Permits have been granted and build out is completed. | 100 | All Site Preparations for the project are completed. | 100 | All equipment procurement for this project is completed. | 100 | The Network Build Out for the project is completed. | 100 | All project equipment and hardware for the project is installed and in operation. | 100 | All Network Testing was successfully completed prior to production implementation. | 2014-05-23 16:31 | 2014-05-23 16:31 | 5423 | 5423 | University of Utah, The
NT10BIX5570025 | 2010 | Q3 | Q3 - 2010 | 336 | 1434 | FALSE | 2 | This is a variance from our baseline plan based on the additional EA work that needs to happen. This has delayed the issuance of a FONSI and payment to my subcontractors. Because I need to move money between line items on my award, this has caused a delay in engineering which will delay payments to my subcontractors. | 0 |  | N/A | 100 | N/A | 90 | N/A | 90 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-17 12:17 | 2010-11-17 12:17 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570025 | 2010 | Q4 | Q4 - 2010 | 1136 | 2174 | FALSE | 5 | This has been delayed because of the delay with our Archeological Assessment and the weather. We cannot put shovels in the ground when there is snow. | 0 |  | N/A | 100 | N/A | 45 | N/A | 0 | N/A | 0 | N/A | 50 | This has been delayed because of the delay with our Archeological Assessment and the weather. We cannot put shovels in the ground when there is snow. | 50 | This has been delayed because of the delay with our Archeological Assessment and the weather. | 0 | N/A | 50 | Because of the delays with the equipment procurement above, we cannot deploy equipment. | 0 | N/A | 2011-02-14 15:50 | 2011-02-14 15:50 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570025 | 2011 | Q1 | Q1 - 2011 | 1900 | 2695 | FALSE | 12 | This is 5% below our baseline but we should be able to catch up once our permits come in and we start ordering materials and start construction. We plan to be on track by next quarter. | 0 |  | N/A | 100 | N/A | 85 | We should be a little ahead of schedule the way we are moving. | 15 | This should be a little ahead of schedule based on having engineering and permits. | 15 | This should be a little ahead of schedule based on having engineering and permits. | 50 | This is behind because of permitting and acquisition. | 40 | This is behind because of permitting and acquisiton. | 5 | This is behind because of permitting and acquisiton. | 35 | This is behind because of permitting and acquisiton. | 0 | N/A | 2011-05-05 20:35 | 2011-05-05 20:35 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570025 | 2011 | Q2 | Q2 - 2011 | 3400 | 3463 | FALSE | 50 | This is 18% behind our baseline. This is partially because of our route change approval delays and partially because of our cost savings from competitively bidding out our project. | 0 |  | N/A | 100 | N/A | 100 | N/A | 75 | This is 15% ahead of our baseline. | 75 | This is 15% ahead of our baseline. | 60 | This is 40% behind our baseline. We should have our sites identified, purchased and prepped, but I do not think that we will have all of our huts built and up and running. | 60 | This is 40% behind our baseline, but that is because of our permitting and construction schedule. | 50 | This is 20% behind our baseline, but that is because of the delays in permitting. While some permitting offices have been very responsive, some of the larger ones have caused us some delays along with reroutes and site changes requested by our customer. | 50 | This is 50% behind our baseline, but it lines up with our Network Build above. | 5 | This is 5% ahead of our baseline, this is based on our plan to light some of our sites as we go. | 2011-08-31 16:58 | 2011-08-31 16:58 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570025 | 2011 | Q3 | Q3 - 2011 | 4196 | 3946 | FALSE | 41 | This is 57 percent under our baseline plan. Zayo is projecting coming in under budget. Based on our projections, even though we are only going to be at 41% of our baseline budget, we should be close to 85% actual miles complete. | 0 |  | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 100 | This is on target with our baseline. | 54 | This is 56% behind our baseline because of delays in site procurement. | 100 | This is on target with our baseline. | 60 | This is 40% behind our baseline. In actuality, Zayo is projecting coming in under budget, so an accurate reflection of actual miles built would be 90% built. | 60 | This is 40% behind our baseline because of delays in site procurement and hut placement. | 0 | This is 70% under our baseline. This is because of permitting and build delays. | 2011-11-21 17:00 | 2011-11-21 17:00 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570025 | 2011 | Q4 | Q4 - 2011 | 5416 | 5101 | FALSE | 41 | This is 57% under our baseline plan. | 0 |  | This is on target. | 100 | This is on target. | 100 | This is on target. | 100 | This is on target. | 100 | This is on target. | 54 | This is 56 behind our baseline because of delays in site procurement. | 100 | This is on target. | 60 | This is 40% behind our baseline because of delays in procurement. | 60 | This is 40% behind our baseline because of delays in procurement. | 0 | This is 70% under our baseline because of permitting and build delays. | 2012-02-29 16:09 | 2012-02-29 16:10 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570026 | 2010 | Q3 | Q3 - 2010 | 342 | 1437 | FALSE | 5 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 |  | n/a | 100 | . | 25 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | KINBER anticipates completing an RFP process in December 2010 to obtain a new vendor(s) to build the network. This change in Prime Contractor will result in a later construction start date of January 2011. | 0 | . | 0 | . | 0 | . | 0 | . | 0 | . | 2010-11-17 13:22 | 2010-11-17 13:22 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2010 | Q4 | Q4 - 2010 | 1304 | 2332 | FALSE | 5 | . | 0 | n/a | n/a | 100 | . | 50 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in the network design that will continue in Q1, 2011. Agreements, signed in December 2010, delayed the design process. | 17 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in acquiring ROW on the proposed schedule. ROW for overlash will be completed on approximately 300 miles of planned fiber. | 17 | Completing the RFP process in Q3 and selecting a new vendor has resulted in a delay in acquiring permits and approvals on the proposed schedule. It is anticipated that 300 miles of fiber will receive permits and approvals in Q1, 2011. | 30 | It is anticiapted that sites related to approximately 500 fiber miles will be completed. | 0 | . | 0 | . | 0 | . | 0 | . | 2011-02-22 15:28 | 2011-02-22 15:28 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2011 | Q1 | Q1 - 2011 | 1944 | 2717 | FALSE | 27 | KINBER projects $35M in construction related expenses in the next quarter as new fiber is hung in multiple segments along the network route. | 0 | n/a | n/a | 100 | Complete | 100 | Design will be complete in Q2 2011. | 23 | 400 miles of overlash, ROW recieved. Remaining 77% will be submitted. | 25 | 100% of pole permits submitted, awaiting approvals. | 10 | All engineering will be completed. | 0 | RFP for equipment to be awarded in Q2, 2011; procurement in Q3, 2011. | 2 | 50 miles of fiber will be completed | 0 | Project is on time for equipment deployment to begin in Q4 2011. | 0 | Project is on time for a portion of the network to begin testing in Q4 2011. | 2011-05-11 13:25 | 2011-05-11 13:25 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2011 | Q2 | Q2 - 2011 | 3076 | 3295 | FALSE | 29 | Project is slightly behind proposed baseline scheduling due to the realignment of the deliverable schedule when KINBER entered into a revised construction agreement with their replacement vendor (Sunesys). The construction completion schedule and payment schedule shifted but is expected to catch up to projected baseline in Q4, 2011. The slower than anticipated response for ROW and make ready permits from local utilities has also impacted the completion schedule of the project. | 100 | Fiber Procurement | KINBER has received 1,030 miles of fiber and has dedicated factory time and delivery dates for the remaining fiber necessary to construct the PennREN project. | 100 | Completed, except for unanticipated changes that may be made to the route. | 100 | Project on schedule. | 95 | Progress may be impacted by ROW approvals and/or route changes that arise during the construction process. | 50 | All permits will be submitted, KINBER may be subject to delays in the approval process of the various utilities. | 30 | Project on schedule. | 10 | Contract will be awarded to equipment vendor; purchase agreement will be executed and some equipment may be ordered. | 0 | Project on schedule. | 0 | Project is on time for equipment deployment in Q4, 2011. | 0 | Project is on-time for a portion of the network to begin testing in Q4, 2011. | 2011-08-15 10:53 | 2011-08-15 10:53 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2011 | Q3 | Q3 - 2011 | 4048 | 3866 | FALSE | 57 | Percent complete rate, as reported is estimated to be low because there is a lag in the time that work is done and the time KINBER is billed for the work.. This is due to the nature of the construction contract where the vendor is only paid based on completed milestones instead of work as it is done. KINBER expects to catch up in Q1 2012. | 100 | Fiber procurement | KINBER has received 1,030 miles of NZD fiber and has secured dedicated factory time for the production of the remaining fiber necessary to construct the PennREN project. | 100 | Project is on schedule | 95 | Network design was complete as of Q2, 2011 but KINBER was advsies of a potential overlap with another BTOP funded project (Zito Media). KINBER Is currently waiting for resolution of the overlap with Zito Media in Northwestern, PA. If approved, this change to the route could impact portions of the network design. | 45 | 90% of the ROW requests will be submitted. | 45 | The Verizon strike and weather have impacted the time it takes to get approvals from utility companies. | 65 | 40 of the 62 building entrances will be completed; project is on schedule. | 80 | Project is on schedule. | 0 | Weather and construction related delays have impacted the network completion at this time. | 0 | THE RFP evaluation for equipment took longer than anticipated. KINBER expects to have the equipment ordered and some received for testing in Q4, 2011. | 0 | Network is not yet built to be able to test anything. | 2011-11-15 16:11 | 2011-11-15 16:11 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2011 | Q4 | Q4 - 2011 | 5098 | 4768 | FALSE | 69 | Project is reported as slightly behind schedule due to the deliverable-based billing relationship it has with its construction vendor. Work that is incrementally completed may not be paid in full or reported until the segment has been fully completed and this skews the actual project completion reporting. | 100 | Fiber Procurement | KINBER has received over 1,030 miles of NZD fiber and has secured dedicated factory time to manufacture the remaining fiber necessary to build the network. | 100 | Project is on schedule. | 100 | Project is on schedule. | 100 | Project is on schedule. | 100 | Project is on schedule. | 92 | Project is on schedule. | 95 | Project is on schedule. | 50 | Project is on schedule. | 40 | Project is on schedule. | 40 | Project is on schedule. | 2012-02-17 14:38 | 2012-02-17 14:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2012 | Q1 | Q1 - 2012 | 5990 | 5594 | FALSE | 84 | Project is reported as slightly behind schedule due to the deliverable-based billing relationship it has with its construction vendor. Work that is incrementally completed may not be paid in full or reported until the segment has been fully completed and this skews the actual project completion reporting. | 100 | Fiber Procurement | KINBER has received all fiber necessary to build the network. | 100 | Project is on schedule. | 100 | Project is on schedule. | 97 | We anticipate some continuing delays in getting Right of Way approvals. | 97 | We anticipate some delays in getting permits approved. | 95 | Project is on schedule. | 100 | Project is on schedule. | 75 | Project is on schedule. | 70 | Project is on schedule. | 10 | It was decided to hold equipment in intermediary staging facilities rather than deliver it to the various node sites across the state until fiber terminations were available in each location for appropriate setup and testing. Although it has slowed the ability to connect and test equipment on the first few segments, it will allow us to more quickly deploy staff to address multiple segments as they come online. | 2012-05-09 16:18 | 2012-05-09 16:18 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2012 | Q2 | Q2 - 2012 | 6970 | 6112 | FALSE | 85 | This projection is slightly below the targeted baseline of 89% mostly due to anticipated delays in make ready work and the fixed price contract payment schedule. | 100 | Fiber Procurement | KINBER has received all fiber necessary to build the network. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 100 | Milestone complete. | 90 | Milestone is on schedule. | 90 | Milestone is on schedule. | 25 | This milestone is behind schedule due to completion of small portions of fiber segments. Additional crews will be deployed when necessary to ensure the network is complete and tested by the end of the project. | 2012-08-09 13:38 | 2012-08-09 13:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2012 | Q3 | Q3 - 2012 | 7800 | 6602 | FALSE | 88 | Project will be slightly behind the baseline schedule, mostly due to lags in payment related to segment completion and payment terms outlined in the fixed price construction contract. | 100 | FIber | KINBER has received all of the fiber cable necessary to complete the project. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 95 | Although project will be slightly behind for completion in Q4; project will finish on time in Q1 2013. | 100 | Milestone is complete. | 50 | Network testing is projected to be behind schedule due to the construction delays related to small pieces of a few segments that may be awiting final approval (bridges and tunnels). | 2012-11-08 10:14 | 2012-11-08 10:14 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2012 | Q4 | Q4 - 2012 | 8692 | 7505 | FALSE | 95 | All fiber and electronics will be in place in Q1 2013. KINBER will use the additional time to complete splicing and network testing activities. | 100 | Fiber Procurement | KINBER has received all of the fiber optic cable necessary to complete the project. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 100 | Milestone is complete. | 95 | All fiber and electronics will be in place in Q1 2013. | 100 | Milestone is complete. | 80 | All fiber and electronics will be in place in Q1 2013. K | 2013-02-11 07:44 | 2013-02-11 07:44 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2013 | Q1 | Q1 - 2013 | 9610 | 8336 | FALSE | 100 | Project will be complete. | 100 | Fiber procurement | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 100 | Project will be complete. | 2013-05-06 11:38 | 2013-05-06 11:38 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | 2013 | Q2 | Q2 - 2013 | 11788 | 9954 | FALSE | 100 | Milestone and project are complete. | 100 | Fiber Procurement | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 100 | Milestone and project are complete. | 2014-02-03 17:10 | 2014-02-03 17:10 | 5443 | 5443 | Keystone Initiative For Network Based Education and Research
NT10BIX5570027 | 2010 | Q3 | Q3 - 2010 | 222 | 1377 | FALSE | 4 | Based on estimated expenses from inception through the end of the quarter. | 0 | N/A | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A | 100 | Complete. | 10 | Pushed back based on date the FONSI was issued. | 20 | Pushed back based on date the FONSI was issued. | 0 | No new progress. | 0 | Pushed back based on date the FONSI was issued. | 0 | No new progress. | 2010-10-29 12:17 | 2010-10-29 12:17 | 5496 | 5496 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2010 | Q4 | Q4 - 2010 | 566 | 1586 | FALSE | 7 | Based on estimated inception-to-date expenses related to engineering and construction. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 10 | Contractor selection will be completed and work expected to begin by the end of March. | 10 | DWDM and Layer 2/3 equipment vendor selection is expected to be complete with procurement beginning by the end of this quarter or the beginning of the next. | 6 | No variance. | 0 | Pushed back due to equipment procurement schedule. | 0 | Pushed back due to equipment deployment schedule. | 2011-01-26 18:30 | 2011-01-26 18:30 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2011 | Q1 | Q1 - 2011 | 2028 | 2759 | FALSE | 34 | Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 10 | Construction contractor and Auxiliary Equipment vendor was selected on 4/11. Construction is expected to begin by 6/30. | 25 | Finalized contract negotiations with DWDM vendor and received final signed contract on 4/22. Site visits and planning to begin on deployment of DWDM equipment on 4/25. Continuing work on contract negotiations with Access Equipment vendor. Selected Layer 2/3 Equipment vendor on 4/15 and have begun contract negotiations. | 35 | No variance. Construction is progressing on schedule. | 25 | Pushed back due to equipment procurement schedule. | 9 | Pushed back due to equipment deployment schedule. | 2011-05-13 16:17 | 2011-05-13 16:17 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2011 | Q2 | Q2 - 2011 | 3308 | 3416 | FALSE | 60 | No variance. Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 50 | Building construction under way and expected to be completed by quarter 4. | 63 | Increasing efforts to catch up this milestone. Equipment is being procured as the installers are ready to proceed with installation. The installation of the equipment is proceeding very quickly and we anticipate catching up to this milestone very soon. | 53 | No variance. Working on catching up to milestones by increasing efforts and deploying multiple crews in each of our fiber construction locations. | 63 | Equipment deployment is proceeding very quickly and we anticipate catching up to this milestone very soon. | 50 | Network testing is conducted as equipment is installed. | 2011-08-25 10:45 | 2011-08-25 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2011 | Q3 | Q3 - 2011 | 4188 | 3942 | FALSE | 71 | Ahead of baseline projections. Expecting to exceed baseline projections based on completing outside plant construction by the end of Q4 2011. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 75 | Equipment is being procured as we are able to install it. Waiting for completion of buildings in two locations and power equipment upgrades in other locations. Buildings should be complete by the end of Q4 2011, therefore equipment procurement and installation will ramp up and expect to fully complete by Q2 2012. | 69 | No variance. | 75 | Equipment deployment follows equipment procurement. See explanation above. | 75 | Network testing follows equipment deployment. See explanation above. | 2011-11-21 15:54 | 2011-11-21 15:54 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2011 | Q4 | Q4 - 2011 | 4924 | 4604 | FALSE | 92 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 95 | All equipment is anticipated to be procured by the end of Q2 2012. | 89 | Positive variance. | 95 | Equipment deployment follows procurement. | 95 | Network testing follows equipment deployment and network build. | 2012-02-09 11:24 | 2012-02-09 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2012 | Q1 | Q1 - 2012 | 5978 | 5588 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-05-08 17:26 | 2012-05-08 17:26 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2012 | Q2 | Q2 - 2012 | 6934 | 6094 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-08-08 15:47 | 2012-08-08 15:47 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2012 | Q3 | Q3 - 2012 | 7562 | 6439 | FALSE | 100 | Positive variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 100 | Positive variance. | 2012-10-30 11:56 | 2012-10-30 11:56 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2012 | Q4 | Q4 - 2012 | 8990 | 7769 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-02-26 16:59 | 2013-02-26 16:59 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | 2013 | Q1 | Q1 - 2013 | 10022 | 8560 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-05-31 11:04 | 2013-05-31 11:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570028 | 2010 | Q3 | Q3 - 2010 | 388 | 1460 | FALSE | 15 | N/A | 0 | N/A | N/A | 100 | N/A | 5 | N/A | 5 | N/A | 5 | N/A | 5 | N/A | 35 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-23 14:36 | 2010-11-23 14:36 | 5375 | 5375 | Administration, Wisconsin Department of
NT10BIX5570028 | 2010 | Q4 | Q4 - 2010 | 1022 | 2066 | FALSE | 15 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 |  | N/A | 100 | N/A | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 5 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 35 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 0 | Due to delay in starting the project, we are an estimated one quarter behind progress anticipated in the baseline. | 2011-02-09 14:02 | 2011-02-09 14:02 | 5375 | 5375 | Administration, Wisconsin Department of
NT10BIX5570028 | 2011 | Q1 | Q1 - 2011 | 1450 | 2438 | FALSE | 5 | As noted earlier in the report, the project will be terminated for convenience. | 0 |  | N/A | 100 | N/A | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 0 | As noted earlier in the report, the project will be terminated for convenience. | 2011-04-20 11:27 | 2011-04-20 11:27 | 5375 | 5375 | Administration, Wisconsin Department of
NT10BIX5570028 | 2011 | Q2 | Q2 - 2011 | 2470 | 2983 | FALSE | 5 | Project was terminated for convenience | 0 |  | :N/A | 100 | : | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 0 | project terminated | 2011-07-20 09:41 | 2011-07-20 09:41 | 5373 | 5373 | Administration, Wisconsin Department of
NT10BIX5570029 | 2010 | Q3 | Q3 - 2010 | 354 | 1443 | FALSE | 7 | Delay in key vendor contract encountered secondary to new Federal regulations regarding security interest. ENA, vendor and National Telecommunications and Information Administration are currently working to address this issue. | 0 |  | N/A | 0 | N/A | 35 | Vetting Wave 2 sites to verify service need. | 5 | See Item 2a above. | 5 | See Item 2a above. | 5 | See Item 2a above. | 5 | See Item 2a above. | 0 | See Item 2a above. | 0 | See Item 2a above. | 0 | See Item 2a above. | 2010-11-19 13:15 | 2010-11-19 13:15 | 5509 | 5509 | Education Networks of America, Inc.
NT10BIX5570029 | 2010 | Q4 | Q4 - 2010 | 820 | 1854 | FALSE | 7 | Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 |  | N/A | 0 | N/A | 35 | Vetting Wave 2 sites to verify service need. | 5 | See item #2a above. | 5 | See item #2a above. | 5 | See item #2a above. | 5 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 0 | See item #2a above. | 2011-01-28 16:07 | 2011-01-28 16:07 | 5509 | 5509 | Education Networks of America, Inc.
NT10BIX5570029 | 2011 | Q1 | Q1 - 2011 | 1398 | 2411 | FALSE | 0 | N/A - Grant terminated. | 0 |  | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 0 | N/A - Grant terminated. | 2011-03-10 15:57 | 2011-03-10 15:57 | 5508 | 5508 | Education Networks of America, Inc.
NT10BIX5570030 | 2010 | Q3 | Q3 - 2010 | 446 | 1489 | FALSE | 15 | Significant progress in construction and community anchors is expected in Q4. NIU Outreach will start work on Community Anchor Institutions. DeKalb Fiber Optics will operate second plow crew in beginning in April for three months. This should provide the extra resources to get the overall project on schedule | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 75 | Rights-of-Way are in-place for segments to be constructed in Q4. Schedule allows adequate time for acquisition of ROW for center and south routes as construction is underway on north part of project. Target was 100% at this point but delayed in order to concentrate on agreement preparation. | 75 | Permits are in-place for segments to be constructed in Q4. Schedule allows adequate time for acquisition of ROW for center and south routes as construction is underway on north part of project. Target was 100% at this point but delayed in order to concentrate on agreements preparation. | 0 | N/A | 15 | Northern Illinois University Outreach consulting agreement is expected to be in place early in Q4. Their work includes defining the equipment needs of the community anchors and assisting the County in competitively bidding the purchase of the equipment. First phase of their work will concentrate on community anchors located in north part of route. Network build equipment is available and ready for when construction starts. Target was 40% at this point but delayed in order to work on NIU Outreach agreement. | 8 | Represents completion of three segments in DeKalb and Genoa in Q4. Extra plow crew to be added in April to catch up with IRU schedule which is bulk of project. Target was 30% at this point but delayed due to lack of agreements that would allow construction to start. | 13 | Network build equipment is available when construction starts. Premise participant equipment and core equipment is being purchased by competitive bid. The bids are expected to be awarded in Q5 and will be installed as Community Anchors are brought on-line. Target was 40% at this point but delayed due to lack of agreements are needed in order for construction to start and equipment to be deployed. | 8 | For segments installed in Q4. All segments will be tested as they are completed. Adequate resources are in place to assure testing will keep pace with construction. Target was 40% at this point but delayed due to lack of agreements that are needed in order for construction to start and testing to take place. | 2010-11-29 17:52 | 2010-11-29 17:52 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2010 | Q4 | Q4 - 2010 | 1316 | 2341 | FALSE | 25 | Significant project is projected in Q5. Target was 60% complete at this point but construction delayed due to document preparation. | 0 | N/A | N/A | 100 | Previously completed | 100 | Previously completed | 65 | Finalize rights of way on north part of route. Target was 100% at this point but construction was delayed due to document preparation. | 75 | Obtain three rail crossing permits needed for Q5 construction. Target was 100% at this point but construction was delayed due to document preparation. | 0 | N/A | 33 | Purchase premise switching equipment for 10-15 anchors. Target was 75% by Q5 but construction was delayed due to document preparation. Equipment procurement following Network Build. | 11 | 56,000lf of duct and 60,000lf of fiber to be built in Q5. Target was 60% for Q5 but construction was delayed due to document preparation. Contractor will provide additional resources as weather improves to get project on schedule. | 25 | Premise and node equipment for north community anchors to be deployed in Q5. Target was 50% for Q5. Equipment deployment is following network build. | 9 | For north part of route installed fiber and connected CAI's. Target was 50% for Q5 but delayed due to document preparation. Testing is following network build. | 2011-02-22 17:08 | 2011-02-22 17:08 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2011 | Q1 | Q1 - 2011 | 2072 | 2781 | FALSE | 30 | Baseline predicted 80% complete at this point. The project was behind schedule early due to difficulty getting agreements in place. We project project will reach baseline projection of 80% in Quarter 9. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 70 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Work will proceed in Q6 to acquire ROW's for Hinckley, Big Rock, Waterman and Shabbona. | 75 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. | 0 | N/A | 40 | Baseline predicted 100% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to bid backbone equipment and emergency radio equipment in Q6 | 30 | Baseline predicted 80% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 36% of duct and 30% of fiber installed by the end of Q6. | 25 | Baseline predicted 85% at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to place community anchor and backbone equipment for north part of the route in Q6 as well as some 911 tower and repeater equipment. | 12 | Baseline predicted 70% at this point. The project was behind schedule early due to difficulty getting agreement in place. Testing is on schedule and keeping pace with fiber installation. | 2011-05-17 09:18 | 2011-05-17 09:18 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2011 | Q2 | Q2 - 2011 | 2950 | 3232 | FALSE | 53 | Baseline projected 95%. The project was behind schedule early due to difficulty getting agreements in place. Expect to meet baseline in Q10 (10-12 additional months. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 80 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q9. | 100 | Remaining railroad permits should be received. | 0 | N/A | 15 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q10. | 53 | Baseline predicted 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at 100% in Q10. | 1 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at baseline in Q11. | 20 | Baseline projected 100%. The project was behind schedule early due to difficulty getting agreements in place. Project will be at baseline in Q10. | 2011-08-08 11:44 | 2011-08-08 11:44 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2011 | Q3 | Q3 - 2011 | 4020 | 3850 | FALSE | 70 | Baseline predicted 98% complete at this point. Expect to meet baseline in Q10 (10-12 additional months). Expect to have 80.2 network miles installed by end of Q8. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 80 | Baseline predicted 100% at this point. We will continue to acquire ROW where we can but the completion of ROW will depend on route change approval. Assuming ROW will not be 100% until Q9. | 100 | All costs associated with permits should be paid by the end of Q8 | 0 | N/A | 60 | Baseline predicted 100% at this point. We will pay for the backbone equipment in Q8. Will meet baseline in Q10. | 70 | Baseline predicted 100%. We will be 67% complete on constructed network and 100% complete on leased and IRU's by the end of Q8. Due the ROW issues, we probably won't meet baseline until Q10. | 25 | Baseline predicted 100%. By the end of Q8, we plan to have 33% of the backbone equipment and 33% of the community anchor switches deployed. Still need to deploy downtown wireless, fiber back haul and GPON, as well as balance of backbone and community anchor switches. Baseline will be met in Q11. | 40 | Baseline predicted 100%. We will continue test the completed segments in Q8. 70% of the build should be completed by the end of the quarter and approximately 80% should be tested. Baseline will be reached in Q10 | 2011-11-14 12:37 | 2011-11-14 12:37 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2011 | Q4 | Q4 - 2011 | 5116 | 4785 | FALSE | 84 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/11 showing completion percentages for the last three four quarters of 20, 29, 47, and 62% respectively. The project will be substantially complete by 1/31/12. | 0 | N/A | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Route change approval will allow row acquisition to proceed. We intend to acquire all row and 13 of 14 municipal utility agreements by the end of Q9. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. Some expenditures remain to be paid from this line item, primarily for rail crossing expenses. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Some rail crossing expenses remain to be paid as crossings are made in municipalities with which we are still negotiating utility agreements. | 0 | N/A | 70 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Expect to pay for backbone and fiber back haul equipment in Q9. Plan to bid and order City of DeKalb downtown wireless, public library access points and GPON equipment in Q9. | 90 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Plan to be 81% built in duct and fiber by end of Q9. All leases and IRU's are in place which adds 9% to the total network build completion. | 25 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, maintenance and repair agreements with DeKalb Fiber Optics, LLC. Backbone equipment will be deployed as telephone central offices become available. Community anchor equipment will be deployed in north and central parts of route. E-911 equipment will be partially deployed. | 25 | Testing will be completed for another 22 miles of fiber from south of Genoa to the network operations center in DeKalb and in the DeKalb-Sycamore area. | 2012-02-17 17:07 | 2012-02-17 17:07 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2012 | Q1 | Q1 - 2012 | 6038 | 5618 | FALSE | 83 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/12 showing completion percentages for the past five quarters of 20, 29, 47, 62 and 70% respectively. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Remaining municipal utility agreements will either be finalized in Q10 of award or rerouting will be initiated. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Some expenditures remain to be paid from this line item for rail crossing expenses for crossings within municipalities from which we currently are negotiating row access. | 0 | N/A | 44 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC.Expect to pay for backbone equipment in Q10 of award. Plan to bid, order and receive wireless access points for libraries. Plan to bid City of DeKalb downtown wireless/ surveillance project in Q10. Plan to complete evaluation of vendor neutral cabinets and start procurement process. | 95 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. If sufficient row issues are resolved by May 1, we plan to be 93% compete with duct and fiber by June 30. All leases and IRU's are completed. | 40 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Plan to deploy one additional collocation site, CAI equipment for 31 additional connections, E-911 fiber back haul equipment should be complete and wireless access point deployment in libraries should start in Q10 of award. | 58 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. We plan to test an additional 30 miles of fiber in Q10 of award which would make the total tested 73.37 miles by the end of Q10. | 2012-05-11 10:17 | 2012-05-11 10:17 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2012 | Q2 | Q2 - 2012 | 7238 | 6246 | FALSE | 90 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Project has been moving well since 1/1/12 showing completion percentages for the past five quarters of 20, 29, 47, 62, 70 and 75% respectively. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. One remaining municipal utility agreements and one remaining right-of-way issue will be finalized in Q11 of award. Expenditures in this line item will exceed budget due to payments for previously completed duct and fiber not budgeted here but properly paid from this line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Some expenditures remain to be paid from this line item for rail crossing expenses for crossings within municipalities from which we currently are negotiating row access. | 0 | N/A | 70 | Essentially will complete equipment procurement. Only minor equipment purchase will remain at end of Q11. | 98 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. Since right-of-way issues are sunstantially resolved, we plan to be 95% compete with duct and fiber by September 30. All leases and IRU's are completed. | 75 | Plan to complete the deployment of the node site in Sandwich and additional 30 additional CAI's. Deploy fiber back haul equipment. Backbone equipment would be 100% complete and CAI equipment would be 73% deployed by the end of Q11. | 57 | Baseline predicted 100%. Project was behind schedule early due to obtaining indefeasible right to use and locating, repair and maintenance agreements with DeKalb Fiber Optics, LLC. We plan to test an additional 30 miles of fiber in Q10 of award which would make the total tested 73.37 miles by the end of Q10. | 2012-08-24 12:50 | 2012-08-24 12:50 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2012 | Q3 | Q3 - 2012 | 7924 | 6666 | FALSE | 95 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Project has been moving well since 1/1/11 showing completion percentages of 20, 29, 47, 62, 70, 75 and 83 percent respectively. All physical work on the project is expected to be completed by the end of the quarter. We expect final payments to carry over into January, 2013. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All rights-of-way were completed in Q3-12. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Some expenditures remain to be paid from this line item in Q4-12 as expenses for flag men and railroad supervision are paid after crossings are made in Somonauk and Malta. | 0 | N/A | 100 | All remaining equipment for the project should be received and paid in Q4-12 as 10Gb "ring" equipment and firewalls are received and paid. | 99 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction is expected to be complete. However some invoices for completed work may still be unpaid at the end of the quarter. | 100 | Node site in Sandwich will be complete. All Community Anchors locations will be complete for equipment deployment. | 100 | Entire network will be tested by the end of the quarter. | 2012-11-16 14:02 | 2012-11-16 14:02 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2012 | Q4 | Q4 - 2012 | 8742 | 7538 | FALSE | 93 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved infrastructure work on the project is completed. Some additional connections will be completed in January and some additional community anchor engineering can be completed and invoices processed for engineering. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously competed. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All rights-of-way were completed in 2012-Q3. Costs for rights-of-way are expected to exceed budget due to payment for previously completed duct that was budgeted in "Construction" but was properly paid from "Rights-of-Way" line item. In-kind for duct and fiber provided by DeKalb Fiber Optics will exceed budget and be off-set by engineering provided by DeKalb Fiber Optics being less than budgeted. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. Some expenditures remain to be paid from this line item in 2013-Q1 as railroad invoicing for flag men for crossing are made in Malta is lagging behind actual date of occurance. | 0 | N/A | 100 | All remaining equipment for the project should be received and paid in 2013-Q1. Some additional connection equipment may be needed for the community anchors involved with the route changes. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved construction is complete and invoices are paid. 1.526 miles of additional network will need to be built and 2.965 miles of additional network will be acquired from DeKalb Fiber Optics if the route changes are approved. Construction of the additional network can only take place in 2013Q1 if route change is approved in time to construct it and weather conditional allow it. | 100 | All node sites are complete. All Community Anchors locations will be complete for equipment deployment in January, 2013. Additional equipment will be deployed if route changes are approved. The connection of 17 community anchors remains at the end of 2012-Q4. Of those, one is expected to be connected in January, 2013 and the remaining 16 are dependent on route changes. Of the 16 connections dependent on route changes, seven are dependent on construction and will take up to three months to connect after route changes are approved, making it doubtful these locations can be connected next quarter.. The remaining nine connections need equipment, configuration and lighting only and may be able to be connected late in 2013-Q1 if route changes are received in time to allow the remaining tasks to be complete before the end of the quarter. | 100 | Completed in 2012-Q4. Verification of test results continues into 2013-Q1. | 2013-02-13 10:44 | 2013-02-13 10:44 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2013 | Q1 | Q1 - 2013 | 9818 | 8445 | FALSE | 92 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All approved infrastructure work on the project is completed. One approved additional connection can be completed in 2013-Q2. Remaining connections are dependent on approval of prospective route change approval. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed | 92 | Baseline predicted 100%. All right of way costs are paid; additional in-kind to be received dependent on prospective route change approval but not expected in 2013-Q2. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction permits are received and expenses for construction permits are paid, | 0 | N/A | 87 | Baseline predicted 100%. All equipment that has been ordered has been received and paid. Remaining funds are for 100Gig "ring" being constructed with iFiber project. | 98 | When prospective route changes are approved, an additional 1.26 miles of duct and fiber will be constructed and an additional 1.9 miles of network will be acquired by IRU or bill of sale. Neither of those are expected to be completed in 2013-Q2. | 95 | Seven additional locations will need to be deployed when the prospective route changes are approved. | 98 | Testing for 1.26 miles of additional fiber will need to be completed when the prospective route changes are approved and that additional fiber is installed. Not expected to be completed in 2013-Q2. | 2013-05-20 10:44 | 2013-05-20 10:44 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2013 | Q2 | Q2 - 2013 | 10490 | 8896 | FALSE | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All infrastructure and connections for the project will be completed by end of next quarter. | 0 |  | N/A | 100 | Previously completed. | 100 | Previously completed. | 100 | Baseline predicted 100%. All right of way costs are paid; all in-kind fiber and duct provided by DeKalb Finer Optics LLC has been received. | 100 | Baseline predicted 100%. Project was behind schedule early due to negotiations with DeKalb Fiber Optics, LLC on Indefeasible Right to Use agreement and locating, maintenance and repair agreement. All construction permits will be received and expenses for construction permits will be paid by the end of the next quarter, | 0 | N/A | 100 | Baseline predicted 100%. All major equipment that has been ordered has been received and paid. Some miscellaneous equipment needed to connect remaining locations will be ordered, received and paid by the end of the next quarter. | 100 | There remains a small amount of network build (prospective route changes) to be completed in 2013-Q3. Work on that additional build was started in 2012-Q2 and will be completed by the end of the next quarter. All network to be acquired by bill of sale or IRU has been completed. | 100 | Six additional locations remain to be deployed. Those will be completed by the end in 2013-Q3. All other equipment required for the project has been deployed. | 100 | Testing for 1.28 miles of additional fiber to serve locations authorized by prospective route changes will be completed in 2013-Q3. | 2013-08-06 10:52 | 2013-08-06 10:52 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570030 | 2013 | Q3 | Q3 - 2013 | 11466 | 9580 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-12-10 11:08 | 2013-12-10 11:08 | 5512 | 5512 | De Kalb, County of (Inc.)
NT10BIX5570031 | 2010 | Q3 | Q3 - 2010 | 322 | 1427 | FALSE | 35 | N/A | 0 | N/A | N/A | 100 | N/A | 50 | N/A | 60 | N/A | 60 | N/A | 25 | N/A | 45 | N/A | 10 | N/A | 30 | N/A | 15 | N/A | 2010-11-15 16:48 | 2010-11-15 16:48 | 5491 | 5491 | Executive Office State of West Virginia
NT10BIX5570031 | 2010 | Q4 | Q4 - 2010 | 1148 | 2186 | FALSE | 40 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 0 |  | N/A | 100 | Awaiting FONSI for project kick-off/construction to begin. | 70 | The primary backbone network for the tower, Community Anchor, and Radio Observatory (which is the easiest portion) is nearly complete, causing 70% completion. | 85 | The rights of way are in place, simply awaiting construction approval, making them complete upon receipt of FONSI, effectively leaping forward the planned completion of same. | 85 | The construction permits are ready to go, awaiting a start date to complete the administrative portion, effectively leaping forward the planned completion of same. | 30 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 50 | Awaiting FONSI for project kick-off/construction to begin. | 25 | Awaiting FONSI for project kick-off/construction to begin. | 40 | Awaiting FONSI for project kick-off/construction to begin. | 20 | The overall project is behind baseline projections because we do not have the FONSI allowing commencement of construction | 2011-02-15 12:13 | 2011-02-15 12:13 | 5745 | 5745 | Executive Office State of West Virginia
NT10BIX5570031 | 2011 | Q1 | Q1 - 2011 | 2118 | 2804 | FALSE | 40 | Variance is due to problems with acquiring FONSI. With the FONSI and PA in place, these percentages will improve each much and be so reflected in the next quarterly report. | 0 |  | N/A | 80 | The EA will be complete; however, with NTIA approval, we may add additional sites due to cost avoidances, and elimination of CAIs. This will have a direct impact on EA. | 55 | As with 2a., portions of design have been on hold, but with release of FONSI and PA, this effort is gaining great momentum. | 70 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 45 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 50 | Site preparation for twelve towers is underway. Lewis County as sub-recipient, through an efficient contract is expected to move ahead of schedule within the next six months, making 50% realistic. Site preparation for the CAI sites will account for about 25% of the overall project and will rapidly approach the 50% mark as local communications requests are released. | 50 | Routers for the Community Anchors were ordered and received. Radios and antennae for the tower portion of the grant are ordered. Routers for the Radio Observatory to the West Virginia University link have been ordered. After next quarter, we will be ahead of schedule in this area | 20 | While below baseline projections, the release to commence construction and a dynamic construction plan will bring this milestone in line within the next two quarters. | 40 | During the upcoming quarter, routers for the Community Anchors will be delivered and programmed. Coupled with radio installation, the installed and functioned routers, and other devices will be deployed at a minimum of 40%. | 30 | Network, equipment, functionality, and validation testing will directly remain at about 10% behind equipment deployment. The primary testing portion to be complete next quarter involves the tower and microwave portion of execution. As the radios, routers, and antennae are installed, testing will follow directly behind. | 2011-05-18 10:06 | 2011-05-18 10:06 | 5745 | 5745 | Executive Office State of West Virginia
NT10BIX5570031 | 2011 | Q2 | Q2 - 2011 | 2974 | 3244 | FALSE | 60 | Variance is due to delay of FONSI receipt, fiber shortage, invoicing on tower radios, and a wet spring. FONSI has been received and subsequent programmatic agreement is a work in progress, fiber shortage has been mitigated, tower radios will be invoiced in August or September and the summer is hot. During the next two quarters we should rapidly close the gap in this area. | 0 | N/A | N/a | 85 | NTIA may approve addition of community anchors and we may have additional sites or projects due to cost avoidances and elimination of community anchors. This will have a direct impact on environmental. | 75 | As the engineering of the National Radio Astronomy Observatory comes to fruition (likely 3rd quarter), we will close the gap in this area. | 95 | We continue to improve in this area and continuance of a dynamic construction plan will bring this milestone into accord within the next two quarters. | 70 | As with 2nd portions of permits have been on hold; however, as construction commenced, this area gained momentum. | 80 | Site preparation for the twelve towers continues to be ongoing. Through Lewis County as a sub-recipient, our contractor aggressively is working the tower construct. The tower portion will be in line by end of the fiscal year. However, due to noted community anchor delays, mostly due to shortage of fiber, we remain sluggish within the community anchor site preparation, including special construction. Most likely we will be into fiscal year 2012 before this is fully on target. | 60 | The receipt of invoice for the radio towers will rapidly move us to within tolerances within equipment purchased. By end of fiscal year we should be on the mark in this area. | 50 | Although progressing quite nicely, we will remain 5 â€“ 10% behind in this area. After any potential changes and/or new community anchors are identified and approved, this will move to base line goals. The receipt of microwave radios will have an immediate positive impact as they are programmed and installed. | 35 | Network, equipment, functionality, and validation testing will directly remain at 5 â€“ 10% behind equipment deployment. As the noted radios are received and installed, the towers come on line, and the community anchors are installed, proportionally this gap will be removed. | 5 | Network testing remains at 5%. The first large phase of testing/validation begins with the microwave radio testing. Although, the manufacturer indicates they tested radios, the State of WV as directly related to this grant has not started follow on testing. This testing should commence during the week of 8 August 2011 and after complete (about 2 weeks) will move us to approximately 40% complete. Frontier Communications reports six miles of fiber complete with a total subscriber served as 98. Testing is now in process for these sites and will continue as new mileage is complete with new community anchored. When added to the testing of the microwave radios, these new sites as tested will enable compliance with baseline within the next two quarters. | 2011-08-09 13:39 | 2011-08-09 13:39 | 7135 | 7135 | Executive Office State of West Virginia
NT10BIX5570031 | 2011 | Q3 | Q3 - 2011 | 3964 | 3820 | FALSE | 50 | This percentage is highly reflective of the tower and engineering portion of the build out, coupled with actual purchases of equipment. However, it remains imperative that Frontier Communications strictly adhere, with strong monitoring by NTIA and State of West Virginia, their proposed mitigation plan. | 0 | N/A | N/A | 95 | Although this moves to 95%, it remains below the baseline of 100% and until the last engineering process is complete, this will likely remain at 95%. However, we remain confident that we will hit the 95% mark during the last quarter. | 90 | This will move to 90% next quarter and lags behind due to some inherent radio problems. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 95 | This goal will be met next quarter; however, the remaining 5% will likely not be met for the next two quarters due to finalization and compliance of mitigation plan. | 97 | We are rapidly approaching the actual placement of all purchase orders; however after next quarter there likely will be about 3% remaining for any potential unknowns and NTIA possible approval of additional equipment. | 55 | The tower portion of the project will carry a large portion of this percentage. As Frontier is compliant with the proposed mitigation plan, these numbers will increase, but by the end of December, it likely will not move beyond a total of 55%. | 65 | The tower portion of the project will carry a large portion of this percentage. As Frontier is compliant with the proposed mitigation plan, these numbers will increase, but by the end of December, it likely will not move beyond a total of 55%. | 50 | Testing on towers begins in full; however, we cannot begin complete testing of the fiber portion until it is constructed; therefore, we remain dependant on Frontier to meet or exceed the proposed mitigation plan. | 2011-11-10 14:20 | 2011-11-10 14:20 | 7135 | 7135 | Executive Office State of West Virginia
NT10BIX5570031 | 2011 | Q4 | Q4 - 2011 | 5194 | 4861 | FALSE | 58 | Frontier will continue diligently executing their mitigation plan efforts enabling further completion. Tower radios will be 75% installed. We will pay radio invoices of approximately $15,000,000. The fiber build out by sub contractors will be over 50% complete and the National Radio Astronomy Observatory to West Virginia University will be in full construction. | 0 | N/A | N/A | 96 | Environmental Assessments will be complete except for the potential tower replacements. This is necessitated due to structural inhibitors that will delay the environmental progress. However, this will only be minimal delay that will self-correct within six months. | 98 | Network design will be nearly complete. However, there may be glitches that may require revisiting of the overall design. Therefore, we are holding to 98%. | 98 | Rights of way will be virtually complete; however, we may have some minor glitches that require some minor effort. We are on target to meet the overall grant objectives in this area. | 98 | Construction permits will be virtually complete; however, we may have some minor glitches that require some minor effort. We are on target to meet the overall grant objectives in this area. The replacement towers are on existing sites and will require only minimal permitting. | 95 | Site preparation will likely be necessary with the replacement towers and may extend through the next quarter. This will self correct within six months. | 96 | Equipment procurement will be limited only to items that are incidental to the overall project. We expect most, if not all equipment orders to be placed by the end of the first quarter; however, there may be a few items that are â€œhungâ€ within the confines of the purchasing processes. | 60 | As noted within this report, Frontier Communications is behind the overall grant production schedule, but is rapidly increasing the gap by full execution of their approved mitigation plan. We expect this number to decrease dramatically through each quarter enabling satisfactory completion at the end of the grant. | 70 | A major portion of the routers will be delivered/installed as Frontier completes their portion of the mitigation plan (see 2h). As this plan has been jump started, so will the deployment of related equipment. Also, the National Radio Astronomy Observatory to West Virginia University link will have equipment delivered and installed during this quarter. | 60 | In keeping with 2h and 2i, as Frontier develops construction in accord or ahead of their mitigation effort, the testing will be commensurate with construction processes. We are on track to complete | 2012-02-22 15:14 | 2012-02-22 15:14 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2012 | Q1 | Q1 - 2012 | 6320 | 5762 | FALSE | 69 | Frontier continues execution of mitigation plan. We will have factory tested and delivery of all microwave radios. During the next month we will be taking advantage of the summer weather to continue increasing tempo of construction. | 0 | N/A | N/A | 98 | CAI engineering and agency approvals are anticipated to be complete in the 2nd quarter 2012. The remaining 2% represents re-opening of counties for various reasons, or a lagging county approval. | 98 | The remaining 2% allows room for tweaking the network design. | 98 | The remaining 2% allows room for any unknown or not planned efforts in this area. | 96 | Storm water construction inspections for 11 of the 12 towers (92%) has been completed. Then the WVDEP permit can be closed. The remaining 5 tower inspections (0%) will be conducted in 3rd and 4th quarters 2012. Construction inspections for the Community Anchors (2%) will begin in the 2nd quarter 2012 and will continue until end of January 2013. Inspections to close out the WVDEP permits for applicable counties(CIA - 2%) will progress as Frontier completes the construction activities in each county. The last inspections are anticipated to be in January 2013. | 98 | The remaining 2% allows room for tweaking or correcting anything surfacing in this area. | 98 | The remaining 2% allows room for tweaking or correcting anything surfacing in this area. | 85 | As fiber deployment continues, mitigation plan tracker is planned for 85 % completion. | 85 | Most routers will be deployed in this quarter. | 75 | Once all CAI's have routers and all new service is hooked up with fiber. The engineers will be finalizing testing. All CAI's are on schedule to be completed during quarter 4 2012, per Frontiers mitigation plan. | 2012-05-29 12:15 | 2012-05-29 12:15 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2012 | Q2 | Q2 - 2012 | 6998 | 6126 | FALSE | 71 | The difference from the baseline centers on the two significant factors mentioned throughout this and previous reports. First was the time consumed during the environmental assessment process, during which we could not begin construction. Second (coupled with the environmental slowness) was the time required for Frontier Communications to begin construction (much of which was due to a major fiber shortage), but was mitigated by the NTIA approved Frontier Mitigation plan. We are on track to complete the grant by the end of the 3rd year. | 0 | N/A | N/A | 98 | Engineering and agency approvals for the replacement CAI's and FBO's are anticipated to be completed in the 3rd quarter 2012. Anticipated approval of five (5) replacement towers will allow construction to begin. The remaining 5% represents re-opening of counties for FBO's or re-engineering during construction. | 99 | Network design is shown at 99%, leaving 1% for unknown design considerations. We will reach 100% at the end of the upcoming quarter. | 99 | Rights of way are shown at 99%, leaving 1% for unknown design considerations. We will reach 100% at the end of the upcoming quarter. | 98 | The state-wide power outage in early July 2012 caused the inspection process to be behind. Storm water construction inspections for 11 of the 12 towers (92%) will be completed. The remaining tower inspection (0%) will be conducted when the tower is stacked. Then the WVDEP permit can be closed. The five (5) replacement towers (0%) will not involve new ground disturbance and do not require a storm water construction permit. Inspections will be conducted at these five (5) replacement towers as construction progresses. Construction inspections on buried segments for the Community Anchors (another 25% in 3rd quarter) will continue until February 2013. Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (15/30 counties - 50% will progress as Frontier and FBO construction activities are completed in each county. The last inspections are anticipated to be in February 2013. | 98 | Site preparation is shown at 98%. Although virtually complete, the 2% remaining from baseline leaves room for any additional or unforeseen efforts that may surface. | 98 | Equipment procurement is shown at 98%. We will have all approved equipment ordered by end of next quarter. The 2% leaves room for any miscellaneous material that might be required. | 80 | Network Build is shown at 80% for the upcoming quarter. This may be somewhat conservative. We expect Frontier to continue on pace with their mitigation plan; however, the early July 2012 storm caused some delays in projections for catch â€“ up. | 85 | Equipment Deployment at 85% is also somewhat conservative. As the additional radios are received and installed and additional towers are complete, the main effort will parlay to the remaining installations. | 75 | Network Testing will always trail behind equipment deployment. As the deployment develops, the testing will follow proportionally. | 2012-08-10 10:00 | 2012-08-10 10:00 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2012 | Q3 | Q3 - 2012 | 7974 | 6693 | FALSE | 77 | The 77% is including the Match portion of the grant. The Frontier fiber build should be at or near completion, the original twelve towers with associated radios and antenna should be installed, WV NET should be complete and functional, leaving small portions of each of these initiatives for January completion. The five replacement towers are the only activity holding this percent to 77. | 0 | N/A | N/A | 98 | Engineering and agency approvals for the replacement CAIs and FBOs are anticipated to be completed in the 4th quarter 2012. Construction of the 5 replacement towers will begin in 4th Q 2012 with inspection work to follow. The remaining 5% represents re-opening of counties for FBOs or re-engineering during construction. | 99 | Network design remains at 99% due to CAI additions and replacements. Currently, there are two CAI's remaining which require network engineering and design for completion. Once completed, all CAI network designing should be completed. | 99 | With only two CAI's requiring network engineering and design, this remains at 99%. Once completed, this should be finalized by end of the grant period. | 97 | Storm water construction inspections for 11 of the 12 towers (92%) will be completed. The remaining tower inspection (0%) will be conducted when the tower is stacked. The 5 replacement towers (0%) will involve minimal ground disturbance and do not require a storm water construction permit. Inspections will be conducted at these replacement towers as construction is completed and vegetation is up. Then the WVDEP permit can be closed. Construction inspections on buried segments for the Community Anchors (another 25% in 4th quarter) will continue until February 2013. Inspections to close out the WVDEP permits (notice of termination - NOT) for applicable counties (15/30 counties - 50% will progress as Frontier and FBO construction activities are completed in each county. The last inspections are anticipated to be in February 2013. | 98 | Site preparation is shown at 95% which is reduced from last report from 98%. This is solely due to the 5 replacement towers. Site preparation for these towers should be at 100% after 1st quarter 2013. | 98 | The equipment acquisition for the NRAO/WVU portion and K-12 core network upgrade are still pending. This should be completed before January, 2013. | 90 | The 5 replacement towers will hold this number at 90% until such time as the towers are complete. | 90 | Deployment is on-going with a few equipment acquisitions still pending as well as construction and implementation phase still in process. Also, adding CAI replacements/additions requires re-purposing and shipping equipment to their new locations. | 80 | Testing is on-going as CAI locations are completed and verified. This includes fiber termination and router deployments to these locations. This percentage will grow as site locations are completed. Testing has been impacted since there are new CAI replacements/additions to account for. | 2012-11-20 11:58 | 2012-11-20 11:58 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2012 | Q4 | Q4 - 2012 | 8980 | 7758 | FALSE | 80 | The 80% includes the Matching portion of the grant. As the five replacement towers come to fruition, we will begin to see associated vendor construction invoices. Frontier invoicing should increase. As these and other activities begin to come to completion, the actual invoicing and disbursement amounts will grow proportionally. | 0 | N/A | N/A | 99 | As activities begin completion processes and weather improves, actual site validation visits will effectively improve this area to 100. | 99 | Until the grant closes there will remain limited network design and tweaks accounting for the remaining 1%. | 99 | Until the grant closes there will remain limited rights of way initiatives and tweaks accounting for the remaining 1%. | 99 | The five replacement tower permits should be complete and there may remain 1% effort to tweak some areas. | 99 | The five replacement towers should have all site preparation complete; however, there may remain up to 1% effort to finalize some areas. | 99 | We are leaving this percentage at 99% in the event that any equipment is approved to be purchased with residual funding. | 96 | We are leaving this percentage at 96% in the vent to include finalization of the wireless network portion of the five replacement towers. | 90 | This number remains the same. Adding CAI's replacements/additions requires re-purposing and shipping equipment to their new locations. | 95 | As the entire projects begins to come to closure, network testing will be the final stage. We expect this to be about 95% complete by the end of next quarter. | 2013-02-26 14:50 | 2013-02-26 14:50 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2013 | Q1 | Q1 - 2013 | 9934 | 8510 | FALSE | 82 | Billing lags a minimum (specifically fiber build-out) of 90 days. As construction on the grant closes, we will receive invoices accordingly and in two quarters, we should receive and process all construction billing. | 0 | N/A | N/A | 99 | The only remaining environmental effort will be closeout of counties and towers. | 100 | 100 % Complete | 100 | 100 % Complete | 100 | 100 % Complete | 99 | Snow Shoe tower remains problematic and may not be complete next quarter. | 100 | 100 % Complete | 98 | This should be completed by July 2013 for the fiber portion of the grant. The Snow Shoe tower remains problematic and may not be complete next quarter. | 99 | Equipment for Snow Shoe tower may not be deployed by end of next quarter. | 98 | As the entire projects begins to come to closure, network testing will be the final stage. We expect this to be about 98% complete by the end of next quarter. | 2013-05-28 14:15 | 2013-05-28 14:15 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2013 | Q2 | Q2 - 2013 | 10802 | 9073 | FALSE | 92 | Construction will be 100% complete, but we will continue to receive invoices into the last quarter. We will have the last billing by Calendar Year End. | 0 | N/A | N/A | 99 | There will be some environmental validation during the final quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | There will be testing of the wireless links. | 2013-08-29 09:08 | 2013-08-29 09:08 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2013 | Q3 | Q3 - 2013 | 11344 | 9472 | FALSE | 92 | The planned percent completed is based on funding drawn down on ASAP. There remains an inherent administrative delay in payment of Frontier invoices. All of their invoices will be paid either prior to or immediately in the early stages of the close out. When combined with the remaining invoices to receive and the approximately 4% not committed, and approval of a potential residual funds project, we will be at 100% during grant close out. We plan to have spent $146,829,619 of the $159,823,296 by the end of quarter 4. | 0 | N/A | N/A | 100 | Completion of inspections and permit closeout are projected by end of 4Q 2013. closeout documents will be prepared during 1Q 2014. | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-11-22 09:21 | 2013-11-22 09:21 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570031 | 2013 | Q4 | Q4 - 2013 | 12366 | 10547 | FALSE | 100 | We will return $1,950,720.85 of unused funds. | 0 | N/A | N/A | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 100 | COMPLETED | 2014-07-30 13:23 | 2014-07-30 13:23 | 5490 | 5490 | Executive Office State of West Virginia
NT10BIX5570032 | 2010 | Q3 | Q3 - 2010 | 362 | 1447 | FALSE | 15 | Because the environmental assessment has taken longer to complete, we are starting more slowly than planned. We are, however, working on preparatory actions to allow us to catch up. | 0 | NONE | NA | 100 | NA | 100 | NA | 25 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay acquisition of permissions that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 20 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay permits that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 20 | Concentrating on the environmental assessment has delayed other aspects of the project. In addition, the question of ownership that has not been resolved has caused LCOG to delay the site preparations that may not be necessary. When these issues are resolved, LCOG should be able to move quickly to get the project back on track. | 10 | LCOG expects to complete the selection of one wholesale broadband provider this quarter. As a part of that process, LCOG will determine the equipment to be used on a portion of the network and will initiate, if not complete the equipment procurement. | 75 | LCOG will secure the agreements that will secure the bulk of the network planned during this quarter. | 0 | The delay in completion of the environmental assessment has delayed the start of construction and therefore the deployment of equipment has been delayed. When construction is started, it will be a short time before any equipment deployment is justified. | 10 | LCOG expects to complete this portion of the network testing this quarter. | 2010-11-19 16:37 | 2010-11-19 16:37 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2010 | Q4 | Q4 - 2010 | 1096 | 2137 | FALSE | 15 | Because the environmental assessment has taken longer than expected, construction has been delayed. We anticipate that we will be able to get back on track soon. We may be back on schedule within eight to twelve months. | 0 |  | NA | 100 | Completed | 100 | Completed | 25 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 20 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 20 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 10 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 75 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 0 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 10 | Because the environmental assessment has taken longer than expected, construction has been delayed. | 2011-02-11 16:46 | 2011-02-11 16:46 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2011 | Q1 | Q1 - 2011 | 1952 | 2721 | FALSE | 20 | Construction should begin this quarter. | 0 |  | NA | 100 | This has been completed. | 100 | This should be completed this quarter as construction begins. | 30 | This should proceed ahead of construction. | 30 | This should proceed ahead of construction. | 25 | This should proceed ahead of construction. | 10 | With constructin underway, some equipment can be purchased for installation as construction is completed. | 75 | The completion of the IRU for leased fiber should be done this quarter, which will bring the project back to baseline expectations. | 0 | Deployment will start after construction has moved far enough along so that connections to the internet can be accomplished. | 10 | This will proceed as construction is completed. | 2011-05-11 20:18 | 2011-05-11 20:18 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2011 | Q2 | Q2 - 2011 | 3242 | 3383 | FALSE | 14 | The delays in acquiring fiber have slowed progress, but orders are now being received. | 0 |  | NA | 100 | NA | 100 | This should be completed as construction begins. | 40 | This will proceed ahead of construction. | 40 | This will proceed ahead of construction | 30 | This will proceed ahead of construction | 30 | This will proceed as construction moves forward. | 75 | The completion of the IRUs will establish the largest part fothe network. | 5 | Deploymetn will follow construction. As anchor insitutions are connected, equipment will be deployed. | 30 | With the IRUs completed the testing of the network backbone can commence. | 2011-08-19 16:12 | 2011-08-19 16:12 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2011 | Q3 | Q3 - 2011 | 4258 | 3979 | FALSE | 31 | After completion of the environmental review work has progressed on the time consuming preliminary work of final design, permitting and procurement. |  |  |  | 100 | Completed | 95 | This will proceed as construction moves forward. | 65 | This will proceed as construction moves forward. | 65 | This will proceed as construction moves forward. | 25 | This will proceed as construction moves forward. | 30 | This will proceed as construction moves forward. | 60 | This will proceed as construction moves forward. | 5 | This will proceed as construction moves forward. | 30 | This will proceed as construction moves forward. | 2011-11-23 13:44 | 2011-11-23 13:56 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2011 | Q4 | Q4 - 2011 | 5102 | 4771 | FALSE | 54 | The time consuming elements of the project are mostly completed. The environmental review and fiber availability problems delayed the start but we are getting back on the original timeline. We anticipate getting back to the baseline in third quarter 2012. | 0 |  | NA | 100 | Completed. Pursuant to the new guidelines, some route modifications will be requested Q1 2012. No significant changes to the approved Environmental Assessment is expected. | 100 | Completed this quarter. | 100 | Completed this quarter. | 100 | Completed this quarter. | 70 | This will proceed as construction moves forward. We anticipate getting back to the baseline in second quarter 2012. | 70 | We have identified the equipment to be obtained in many cases, and are proceeding to acquire it in advance of readiness for deployment. We anticipate getting back to the baseline in third quarter 2012. | 75 | We are working to get back on schedule, contracting for construction simultaneously in several areas. We anticipate getting back to the baseline in third quarter 2012. | 15 | We have been making arrangements for equipment deployment, so progress has been made in this area, even though little equipment has been deployed yet. We anticipate getting back to the baseline in third quarter 2012. | 35 | This will proceed as construction moves forward. We anticipate getting back to the baseline in third quarter 2012, when construction is back on schedule. | 2012-02-17 14:47 | 2012-02-17 14:47 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2012 | Q1 | Q1 - 2012 | 5956 | 5577 | FALSE | 70 | The time consuming elements of the project are mostly completed. The environmental review and fiber availability problems delayed the start but we are getting back on the original timeline. We anticipate getting back to the baseline in third quarter 2012. | 0 |  | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 90 | Delays in pole attachment permits and Forest Service permits have delayed this somewhat. Projected completion second quarter 2012. | 65 | We have identified the equipment to be obtained in many cases, and are proceeding to acquire it in advance of readiness for deployment where possible. We anticipate getting back to the baseline in third quarter 2012. | 85 | We are working to get back on schedule, contracting for construction simultaneously in several areas. We anticipate getting back to the baseline in third quarter 2012. | 30 | We have been making arrangements for equipment deployment, so progress has been made in this area, even though little equipment has been deployed yet. We anticipate getting back to the baseline in third quarter 2012. | 50 | This will proceed as construction moves forward. We anticipate getting back to the baseline in third quarter 2012. | 2012-05-08 11:05 | 2012-05-08 11:05 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2012 | Q2 | Q2 - 2012 | 7276 | 6265 | FALSE | 73 | This will bring us nearly back to the intended completion. | 0 |  | NA | 100 | This will be in line with projections | 100 | This is already completed | 100 | This will be in line with projections. | 100 | Completed | 100 | Completed | 75 | This will be back on schedule. | 90 | This includes the route changes | 40 | This will be approaching the intended schedule. | 65 | This will be approaching the intended schedule. | 2012-08-29 15:09 | 2012-08-29 15:09 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2012 | Q3 | Q3 - 2012 | 7934 | 6671 | FALSE | 86 | On Schedule | 0 |  | NA | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 100 | On Schedule | 90 | On Schedule | 100 | On Schedule | 90 | On Schedule | 100 | On Schedule | 2012-11-16 16:46 | 2012-11-16 16:46 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2012 | Q4 | Q4 - 2012 | 8710 | 7515 | FALSE | 90 | On schedule | 0 |  | NA | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 95 | On schedule | 99 | On schedule | 85 | On schedule | 100 | On schedule | 2013-02-11 16:54 | 2013-02-11 16:54 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2013 | Q1 | Q1 - 2013 | 10032 | 8566 | FALSE | 98 | We expect that all but a few items will be completed. All eqiupment will be ordered and scheduled for delivery. | 0 |  | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Some late deliveries may still need to be deployed | 100 | Completed | 2013-05-31 15:45 | 2013-05-31 15:45 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2013 | Q2 | Q2 - 2013 | 10824 | 9084 | FALSE | 100 | Completed | 0 | NA | NA | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed This includes a planned connection of an additional four CAIs building an additional 1.5 miles of fiber. | 100 | Completed | 100 | Completed | 2013-08-30 14:20 | 2013-08-30 14:20 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2013 | Q3 | Q3 - 2013 | 12028 | 10191 | FALSE | 100 | This is as planned | 0 | NA | NA | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 100 | This is as planned | 2014-04-08 15:49 | 2014-04-08 15:49 | 5521 | 5521 | Lane Council of Government
NT10BIX5570032 | 2013 | Q4 | Q4 - 2013 | 11780 | 9949 | FALSE | 100 | As planned. | 100 | NA | NA | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 100 | As planned. | 2014-02-03 11:36 | 2014-02-03 11:36 | 5521 | 5521 | Lane Council of Government
NT10BIX5570033 | 2010 | Q3 | Q3 - 2010 | 410 | 1471 | FALSE | 10 | Variance of 7%. Completion of EA "Environmental Assessment" held up due to various issues; including design verification and delay in SHPO comments being received. These issues which have been dealt with. | 0 | Administration and Project Management (10%) Federal Grant Expenditures (7%) | Variance of 17%. Completion of EA held up due to various issues; including design verification and delay in SHPO comments being received. These issues have been dealt with. Variance of 10%. Completion of EA held up due to various issues. Major cost expenditures have not occurred since EA Environmental Assessment has to be approved before procurement activities are awarded. | 100 | No variance from baseline. | 100 | No variance from baseline. | 50 | No variance from baseline. | 20 | Variance of 30%. Delay in completing EA has delayed initiation of construction activities. | 10 | Variance of 10%. Delay in completing EA has delayed site preparation activities. | 5 | No variance from baseline. | 5 | No variance from baseline. | 0 | No variance from baseline. | 0 | No variance from baseline. | 2010-11-24 07:07 | 2010-11-24 07:07 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2010 | Q4 | Q4 - 2010 | 1310 | 2336 | FALSE | 5 | Variance of 23%. Completion of EA "Environmental Assessment" held up | 0 | Administration and Project Management (20%) Federal Grant Expenditures (5%) | Variance of 16%. Variance of 23% due to delay in completing EA "Environmental Assessment". | 100 | No variance from baseline. Done; already completed. | 100 | No variance from baseline. Done; already completed. | 65 | Variance of 15% Due to network redesign | 20 | Variance of 60% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 50% due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%, due to delay in completing EA "Environmental Assessment". | 0 | Variance of 10%, due to delay in completing EA "Environmental Assessment". | 0 | No variance from baseline. | 2011-02-22 15:58 | 2011-02-22 15:58 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2011 | Q1 | Q1 - 2011 | 1986 | 2738 | FALSE | 8 | Due to time to complete network design update and EA " Environmental Assessment". RFP "Request for Proposals", process in full cycle with all major RFP's being worked on in the quarter. | 38 | Management and Administration 38%. | We are very involved in processing Request for Proposals which have required a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 5 | Delay in completing network redesign update and EA process. Have signed contracts for land lease for new build towers sites. Received draft leasing contract or letter of intent for all existing tower sites. Will be accelerating payments on leases. | 43 | Delay in completing network redesign update and EA process. Entity selected for Permits Tower Construction will review new build sites, do terrain study and develop pre-design foundation build. Permits applications being worked on for high priority sites. | 5 | Delay in completing network redesign update and EA process. Complete Site Preparation RFP " Request for Proposals", for existing sites; published, receive proposals, evaluation of proposals, selection and signature of contract. | 3 | Delay in completing network redesign update and EA process. Complete Request for Proposals for Telecom Equipment, for 23 Sites (all sites), published, receive proposals, evaluation of proposals initiated , selection,and acquisition of equipment initiated . Complete FCC licencing agreements for all Point to Point links. | 0 | Delay in process for completion of EA and network designs update. Develop New Tower Construction RFP,"Request for Proposals" for Sites New Towers, final edition, publish. | 0 | Delay in completion of EA and network designs update held up procurement process. | 0 | No variance from baseline. | 2011-05-12 16:48 | 2011-05-12 16:48 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2011 | Q2 | Q2 - 2011 | 3394 | 3460 | FALSE | 22 | Due to time to complete network design update and EA " Environmental Assessment". RFP "Request for Proposals", process in full cycle with all major RFP's being worked on in the quarter. | 58 | Management and Administration 58% | We are very involved in processing RFPs which have required a lot of preparation, we are now executing the RFP's along a strategy of quadrant priorities which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 25 | Delay in completing network redesign update and EA process. Have signed contracts for land lease for new build towers sites. Complete leasing contract for all existing tower sites. | 63 | Delay in completing network redesign update and EA process. Entity selected for Permits Tower Construction will review new build sites, do terrain study and develop pre-design foundation build. Permits applications being worked on for high priority sites. | 31 | Delay in completing network redesign update and EA process. Completed Site Preparation RFP " Request for Proposals", for existing sites, contract to be signed and initiation of work on existing sites with eight sites expected to be completed. | 19 | Delay in completing network redesign update and EA process. Sign contract with selected vendor of Request for Proposal for Telecommunications Equipment, initiate acquisition of equipment. Commence Deployment. | 19 | Delay in process for completion of EA and network designs update. Develop New Tower Construction RFP,"Request for Proposal" for New Tower Sites, final edition, publish. | 19 | Delay in completion of EA and network designs update held up start of procurement process. Initiate deployment of equipment on existing tower sites. | 19 | Delay in completion of EA and network designs update. | 2011-08-31 09:40 | 2011-08-31 09:40 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2011 | Q3 | Q3 - 2011 | 4058 | 3872 | FALSE | 41 | Initial delay due to Time to complete network design update and EA " Environmental Assessment". Currently RFP "Request for Proposals", process in full cycle with the fourth RFP , NOC Equipment , in process . | 53 | Management and Administration 53% | We will complete our 4th major RFP, (Request for Proposals) which require a lot of time for preparation and execution. All major proposals for acquisition of network equipment will be completed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. | 93 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 34 | Initial delay due to completing network redesign update and EA process. Will be completing lease contracts for three additional existing tower sites. Lease payments are meeting approved waiver for matching funds. | 77 | Delay in completing network redesign update and EA process. Continue submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of three new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the RFPâ€™s for construction permits. | 23 | Delay in completing network redesign update and EA process. Completed RFP " Request for Proposals", Site Preparation , for existing sites, continuation of work in twelve existing sites with ten sites expected to be completed in this quarter. RFP for new tower construction to be issued for towers with approved permits. Quadrant strategy is based on initial two quadrants where existing towers sites are majority of sites. | 45 | Delay in completing network redesign update and EA process. We will receive 50% or more of all equipment for Request for Proposal #3 (Telecommunications Equipment). Implemented system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Request for Proposal #4; ''Acquisition and Implementation of the Central Office Equipment for INTECO'S Broadband Network", will be evaluated, awarded and have contract signed. | 45 | Delay in process for completion of EA and network designs update. | 45 | Delay in completion of EA and network designs update held up start of procurement process. Initiate deployment of equipment on existing tower sites. | 45 | Delay in completion of EA and network designs update. | 2011-11-16 10:05 | 2011-11-16 10:05 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2011 | Q4 | Q4 - 2011 | 5062 | 4734 | FALSE | 70 | Initial delay due to Time to complete network design update and Environmental Assessment. Currently Request for Proposals, process in full cycle with the fifth Request for Proposal, New Tower Construction, in process. | 70 | Management and Administration | We will complete our 5th major Request for Proposals which have required a lot of time for preparation and execution. All major proposals for acquisition of telecommunications equipment and network equipment will be completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted the summer of 2012 to initiate the two major quadrants in the network. | 100 | Received FONSI approval (Finding of No Significant Impact) received on Nov 23, 2010 | 100 | Network redesign update completed. | 66 | Initial delay due to completing network redesign update and Environmental Assessment process. Will be completing lease contracts for three additional existing tower sites. Lease payments are meeting approved waiver for matching funds. | 89 | Delay in completing network redesign update and Environmental Assessment process. Complete three additional submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of three new telecommunications towers to be used by the network in underserved areas. We initially underestimated the time it would take to construct new towers and the time to process the Request for Proposals for construction permits. | 26 | Delay in completing network redesign update and Environmental Assessment process. Complete Request for Proposal;Site Preparation, for existing sites, with a total of fifteen sites expected to be completed in this quarter. Request for Proposal for new tower construction to be issued for towers with approved permits. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3 (Telecommunications Equipment). Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 77 | Delay in completing network redesign update and Environmental Assessment process. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 2012-02-16 08:29 | 2012-02-16 08:29 | 5499 | 5499 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2012 | Q1 | Q1 - 2012 | 6048 | 5623 | FALSE | 82 | Initial delay due to Time to complete network design update and Environmental Assessment. New tower construction, in process. | 86 | Management and Administration | We met the expenditures guidelines as per SAC with a 72% expenditures of the project to date. All major proposals for acquisition of telecommunications equipment and network equipment will be completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted the summer of 2012 to initiate the two major quadrants in the network. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 82 | Completed lease contracts for total 16 existing tower sites. Complete land lease contracts for two additional sites. All lease agreements will be completed by Q3 2012. | 83 | Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for three additional sites, We expect these three sites to be approved in this quarter. We have authorization granted for the construction of four new telecommunications towers. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q3 2012. | 63 | Will completed Site Preparation & Construction on 16 existing tower sites. Will complete three new tower construction sites and substantially complete a fourth site. All site prep will be concluded by end of Q4 2012. | 85 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was substantially completed. | 84 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. | 84 | Delay in completing network redesign update and Environmental Assessment process. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment to be received and installed to begin acceptance testing and integration testing. | 84 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed and is now ready for acceptance testing, systems and integration testing. | 2012-05-14 07:11 | 2012-05-14 07:11 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2012 | Q2 | Q2 - 2012 | 7186 | 6220 | FALSE | 91 | Initial delay due to Time to complete network design update and Environmental Assessment. New tower construction, in process. All towers to be completed by Q4 2012. | 89 | Management and Administration | We met the expenditures guidelines as per SAC with a 72% expenditures of the project to date. All major proposals for acquisition of telecommunications equipment and network equipment have been completed and installation initiated with most equipment installed. A strategy of quadrant priorities was implemented which will ensure we meet the expenditures guidelines. We have targeted August 2012 to initiate the largest quadrant in the network. All tower construction will be completed by Q4 2012. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 92 | Completed lease or land lease contracts for 21 sites. All lease agreements will be completed by Q3 2012. | 96 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q4 2012. | 79 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was substantially completed. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was substantially completed. All network build to be completed by Q4 2012. | 92 | We have received all equipment for Request for Proposal#3; Telecommunications Equipment. Request for Proposal #4; Acquisition and Implementation of the Central Office Equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing is underway. All equipment deployment to be completed by Q4 2012. | 92 | The vendor for Request for Proposal #3; Telecommunications Equipment, completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 was completed and is now in acceptance testing, systems and integration testing. | 2012-08-21 12:22 | 2012-08-21 12:22 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2012 | Q3 | Q3 - 2012 | 7844 | 6626 | FALSE | 97 | New tower construction, in process. All towers to be completed by Q4 2012. | 98 | Management and Administration | All telecommunications equipment and network equipment have been completed and final testing underway. A strategy of quadrant priorities was implemented with the largest quadrant activated in August/September 2012. All major tower construction will be completed by October 2012, with four roof-tops being completed in fourth quarter 2012. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 94 | Completed lease or land lease contracts for 23 sites. All lease agreements will be completed by Q4 2012. | 100 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We have pending three sites to receive permits for roof-top installation. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q4 2012. | 94 | Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We will be completing five additional sites, one tower and four roof-tops, in the fourth quarter. | 97 | The vendor for Telecommunications Equipment, has completed the purchase of equipment. We developed a system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network will be completed in this quarter. | 97 | The vendor for Telecommunications Equipment completed the staging of the microwave radios (integration and acceptance testing) at mainland vendor and has completed the purchase of equipment. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q4 2012. | 97 | All equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing and all equipment deployment to be completed in Q4 2012. | 97 | The vendor for Telecommunications Equipment is completing the testing of all microwave radios (integration and acceptance testing). Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q4 2012. | 2012-11-13 13:18 | 2012-11-13 13:18 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2012 | Q4 | Q4 - 2012 | 9138 | 7936 | FALSE | 99 | All 24 sites to be completed by Q1-2013. | 99 | Management and Administration | All telecommunications equipment and network equipment have been completed and final testing.. A strategy of quadrant priorities was implemented with the largest quadrant activated in August/September 2012. All major tower construction has been completed, with two sites being completed in first quarter 2013. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | Submission of permits, including if necessary soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency. We initially underestimated the time it would take to get construction permits for new tower construction. All permits for construction will be completed by Q1-2013. | 99 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. We will be completing two additional sites, in the Q1-2013. | 100 | All Telecommunications Equipment has been acquired. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network was completed. All network build to be completed by Q1-2013. | 100 | All equipment for INTECO's Broadband Network, all equipment has been received and installed. Acceptance, systems and integration testing and all equipment deployment to be completed in Q1-2013. | 100 | The vendor for Telecommunications Equipment is completing equipment installation in last two sites. Acquisition, installation, testing and verification of the NOC Equipment for INTECO's Broadband Network will be completed in Q1 2013. | 2013-03-14 12:33 | 2013-03-14 12:33 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2013 | Q1 | Q1 - 2013 | 9900 | 8491 | FALSE | 100 | All 24 sites to be completed by Q2-2013. | 100 | Management and Administration | All sites completed and operational. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | All permits for construction will be completed by Q2-2013. | 100 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All Telecommunications Equipment completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. All network build to be completed. | 100 | All equipment for INTECO's Broadband Network, all equipment completed. All acceptance, systems and integration testing and all equipment deployment to be completed. | 100 | All acquisition, installation, testing and verification of telecommunications equipment and NOC Equipment for INTECO's Broadband Network completed. | 2013-05-24 11:41 | 2013-05-24 11:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2013 | Q2 | Q2 - 2013 | 10694 | 9008 | FALSE | 100 | All 24 sites to be completed by Q3-2013. | 100 | Management and Adminsitration | All sites completed and operational. | 100 | Received FONSI approval (Finding of No Significant Impact) received on November 23, 2010. | 100 | Network redesign update completed. | 100 | Completed lease or land lease contracts for all 24 sites. | 100 | All permits for construction will be completed by Q3-2013. | 100 | Completion of all site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in twenty four tower sites. | 100 | All Telecommunications Equipment completed. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. | 100 | Acquisition and installation of the NOC Equipment for INTECO's Broadband Network completed. All network build to be completed. | 100 | All equipment for INTECO's Broadband Network, all equipment completed. All acceptance, systems and integration testing and all equipment deployment to be completed. | 100 | All acquisition, installation, testing and verification of telecommunications equipment and NOC Equipment for INTECO's Broadband Network completed. | 2013-08-22 09:41 | 2013-08-22 09:41 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | 2013 | Q3 | Q3 - 2013 | 11634 | 9755 | FALSE | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | Management and Administration | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 100 | End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; before ending date. All closeout activities will be performed in Q3, Q4, before the due date for closeout, 10/29/2013. | 2014-01-21 14:38 | 2014-01-21 14:38 | 5500 | 5500 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570034 | 2010 | Q3 | Q3 - 2010 | 360 | 1446 | FALSE | 43 | Per Baseline Plan | 0 |  | N/A | 100 | FONSI issued on 09/30/2010.Environmental Assessment was deemed a sole-source procurement and was not approved for funding under the grant. | 56 | Per Baseline Plan | 0 | N/A | 9 | Per Baseline Plan | 100 | Per Baseline Plan | 42 | Per Baseline Plan | 47 | Per Baseline Plan | 22 | Per Baseline Plan | 51 | Per Baseline Plan | 2010-11-19 16:00 | 2010-11-19 16:00 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2010 | Q4 | Q4 - 2010 | 1208 | 2241 | FALSE | 67 | On Schedule | 35 |  | Partial contribution of in kind match assets. | 100 | FONSI issued on 09/30/2010. Professional Services fees incurred related to the Environmental Assessment were deemed a sole-source procurement and were not approved for funding under the grant. | 100 | On Schedule | 0 | NA | 75 | On Schedule | 100 | On Schedule | 77 | On Schedule | 82 | On Schedule | 35 | On Schedule | 51 | On Schedule | 2011-02-17 17:02 | 2011-02-17 17:02 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2011 | Q1 | Q1 - 2011 | 2090 | 2790 | FALSE | 78 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | Remaining in-kind assets will be dedicated to the project in second quarter 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 100 | On schedule | 0 | N/A | 45 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | On schedule | 75 | Expenditures for equipment slightly behind schedule due to delayed start. No significant variance to overall baseline budget is anticipated since milestone will be in line with the baseline plan in third quarter 2011. | 78 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in third quarter 2011. | 48 | The baseline plan over run associated with this milestone is due to invoice payment timing. No significant variance to the overall baseline plan is anticipated. This milestone is expected to be complete in third quarter 2011. | 0 | No expenditures anticipated until third quarter 2011.DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds will be required prior to completion of the project. | 2011-05-17 14:44 | 2011-05-17 14:44 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2011 | Q2 | Q2 - 2011 | 2964 | 3239 | FALSE | 82 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the fourth quarter of 2011, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 62 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. Finalization of network drawings, for the newly built network, may require future spend in the fourth quarter of 2011. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Completed | 69 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in the fourth quarter 2011. | 95 | DeltaCom will complete work associated with this milestone category in third and fourth quarter 2011. | 97 | Milestone to be completed by fourth quarter 2011. | 0 | DeltaCom currently has an under run variance against the baseline plan for this milestone. Funds were budgeted for test equipment that have not been required to date. Funds may be required prior to completion of the project. | 2011-08-08 16:37 | 2011-08-08 16:37 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2011 | Q3 | Q3 - 2011 | 3968 | 3822 | FALSE | 85 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the first quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 |  | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | Network design was completed in the first quarter of 2011. Additional invoices are being processed and scheduled to be paid. This milestone currently has an under run variance against the baseline plan. | 0 | N/A | 16 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 74 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in first quarter 2012. | 96 | DeltaCom anticipates a marginal under run variance against the baseline plan for this milestone. DeltaCom will complete work associated with this milestone category in first quarter 2012. | 80 | Milestone is forecast to be 100% complete in first quarter 2012. | 81 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2011-11-10 15:52 | 2011-11-10 15:52 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2011 | Q4 | Q4 - 2011 | 5072 | 4744 | FALSE | 92 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay; however, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | In-Kind Assetts | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 84 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 78 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan in second quarter 2012. | 100 | Expenditures in this milestone are projected to be at 115% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | Milestone is forecast to be 100% complete in second quarter 2012. | 62 | DeltaCom currently has an under run variance against the baseline plan for this milestone | 2012-02-16 15:14 | 2012-02-16 15:14 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2012 | Q1 | Q1 - 2012 | 6004 | 5601 | FALSE | 93 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 84 | To date, costs associated with this milestone have under run projected budget expenditures. | 100 | Complete | 79 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | Expenditures in this milestone are projected to be at 116% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 82 | Milestone is forecast to be 100% complete by the end of the project. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-05-10 11:34 | 2012-05-10 11:34 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2012 | Q2 | Q2 - 2012 | 7026 | 6140 | FALSE | 93 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project is currently projected to complete in the third quarter of 2012, with all expenditures being invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. Additional cost will be incurred for final as-built drawings. | 0 | N/A | 85 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be incurred and invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 79 | Expenditures for equipment are behind schedule due to delayed start. No significant variance to the overall baseline budget is anticipated since this milestone will be in line with the baseline plan by the end of the project. | 100 | Expenditures in this milestone are projected to be at 115% of the baseline category by the end of first quarter 2012. Overall, the project will remain under budget as noted in the SF-424C Budget below. Due to extended negotiations with make-ready and collocation vendors, DeltaCom expects to complete work associated with this milestone category in second quarter 2012. | 90 | Milestone is forecast to be 100% complete by the end of the project. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-08-10 18:01 | 2012-08-10 18:01 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2012 | Q3 | Q3 - 2012 | 8056 | 6734 | FALSE | 96 | Project expenditures are below the baseline plan due to the delayed start associated with Environmental Assessment approval date and a marginal under run in the overall project budget. No action is being taken to off-set the two month delay. Additional delays are due to extended negotiations with make-ready and collocation vendors. However, DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | Complete | 83 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 100 | This milestone is complete and currently expenditures in this milestone are at 118% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2012-11-26 17:05 | 2012-11-26 17:05 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2012 | Q4 | Q4 - 2012 | 8872 | 7658 | FALSE | 93 | Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures will be invoiced by the BTOP deadlines. | 100 | Dark Fiber and Land Assets | In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. | 100 | DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | This milestone currently has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | Complete | 79 | To date, costs associated with this milestone have under run projected budget expenditures. Additional expenditures will be invoiced by the BTOP deadlines. | 100 | This milestone is complete and currently expenditures in this milestone are at 114% of the baseline category. Overall, the project remains under budget as noted in the SF-424C Budget below. Any additional expenditures will be invoiced by the BTOP deadlines. | 89 | This milestone currently has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | DeltaCom currently has an under run variance against the baseline plan for this milestone. | 2013-02-21 11:47 | 2013-02-21 11:47 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570034 | 2013 | Q1 | Q1 - 2013 | 9892 | 8486 | FALSE | 91 | Complete Project expenditures are below the baseline plan due to an under run in the overall project budget. DeltaCom's project was completed in the third quarter of 2012, and all expenditures were invoiced by 05/01/2013. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 100 | Dark Fiber and Land Assets Close Out Activities | Complete In-kind assets comprised of dark fiber and land were dedicated to the project on March 15, 2011 and April 15, 2011. Fees associated with close out activities were expended and reimbursed by 05/01/2013. | 100 | Complete DeltaCom's Environmental Assessment was issued a Finding of No Significant Impacts ("FONSI") on 09/30/2010. Professional Services fees incurred for the Environmental Assessment were deemed a sole-source procurement and were not approved for grant funding. | 68 | Complete This milestone has an under run variance against the baseline plan. Network design was completed in the first quarter of 2011. | 0 | N/A | 93 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete | 79 | Complete This milestone has an under run variance against the baseline plan. | 100 | Complete Expenditures in this milestone are at 107% of the baseline category. Overall, the project remained under budget as noted in the SF-424C Budget below. The decrease in this milestone category is the result of a return of funds to ASAP for expenditures not covered by the grant. | 89 | Complete This milestone has an under run variance against the baseline plan. Equipment deployment was completed in the third quarter of 2012. | 67 | Complete This milestone has an under run variance against the baseline plan. | 2013-05-23 16:38 | 2013-05-23 16:38 | 5523 | 5523 | DeltaCom, Inc.
NT10BIX5570035 | 2010 | Q3 | Q3 - 2010 | 416 | 1474 | FALSE | 10 | Co-first priority security interest confirmed by NTIA as detailed previously. In addition, for site preparation and construction, NTIA grant of limited exclusions to NEPA. | 0 | NA | Same as 2a | 100 | - | 100 | - | 100 | - | 100 | - | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 0 | Same as 2a | 2010-11-24 12:09 | 2010-11-24 12:09 | 5525 | 5525 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2010 | Q4 | Q4 - 2010 | 1264 | 2290 | FALSE | 42 | Network Deployment will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 12 | Network Deployment will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 16 | Equipment procurement in process. Pending Intercreditor Agreement and Historic Preservation Review. | 20 | Network Deployment and other equipment procurement and installation will commence in Q2 pending Intercreditor Agreement and Historic Preservation Review. | 16 | Equipment procurement in process. Pending Intercreditor Agreement and Historic Preservation Review. | 0 | Network not yet deployed, pending Intercreditor Agreement and Historic Preservation Review. | 2011-02-21 17:36 | 2011-02-21 17:36 | 5525 | 5525 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2011 | Q1 | Q1 - 2011 | 2238 | 2864 | FALSE | 78 | -9% Variance. Delays in Fiber-optic cable order fulfillment lead time. Phase 1 Archaeological Survey and shovel testing for 9.3-mile buried section and building placement site. | 0 | Inspection | -100% Variance. Finding of No Significant Impact required before new construction can begin. Issuance expected in early Q2. Fiber-optic order fulfillment lead times will delay construction. | 100 | 466% Budget Variance. Environmental Assessment completed. Phase 1 Archaeological Survey and shovel testing charged to this account. | 73 | -10% Variance. Results of Phase 1 Archeological Survey and shovel testing may impact network design. | 40 | -60% Variance. Baseline forecast included costs of land, structures and appraisals in the Right of Way budget category. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. | 97 | N/A | 0 | -100% Variance. Land clearing and site preparation not allowable until Phase 1 Archaeological Survey and shovel testing completed. | 60 | -40% Variance. Finding of No Significant Impact required before procurement allowable for other than for Management & Administrative Expenditures. Issuance expected in early Q2 2011 at which time contract negotiations and award will be finalized. | 39 | -61% Variance. Finding of No Significant Impact required before new construction can begin. Issuance expected in early Q2. Fiber-optic order fulfillment lead times will delay construction. Buried Placement of 9.3 miles of line cannot begin until Phase 1 Archeological Survey and shovel testing is completed, but less than 10% of the planned network will be buried cable. | 0 | Baseline forecast included equipment installation & testing in Equipment Procurement budget. | 0 | Same as above | 2011-05-20 23:40 | 2011-05-20 23:40 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2011 | Q2 | Q2 - 2011 | 3244 | 3384 | FALSE | 53 | (41)% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 0 | Inspection | (100%) Variance. Same as Network Build. | 100 | 734% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 13% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88)% Variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 81% Variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network design rerouted in connection with Environmental Assessment and completion of Historical and Cultural Preservation Review due to number of archaeological prehistoric and historic sites in Hardy County. | 0 | (100)% Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration. | 12 | (87.7%) Variance. Baseline forecast included Equipment Deployment expenditures in Equipment Procurement budget. Deployment expenditures have been included in this category for consistency. Equipment has been specified and prices negotiated. Delivery dates are established but deferred until two facilities sites are connected over fiber. | 49 | (51)%) Variance. Delays in approval of Intercreditor Agreement and Environmental Assessment prevented procurement of materials and commencement of construction prior to tsecond quarter of 2011. Hardy contributed existing network infrastructure and electronics deployed to Community Anchor Institutions, representing 18% completion. Major materials have been ordered, and construction drawings and requests for proposals documentation completed for all four phases of construction. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-08-19 16:23 | 2011-08-19 16:23 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2011 | Q3 | Q3 - 2011 | 4238 | 3967 | FALSE | 93 | (7%) Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. | 100 | Inspection | No variance | 100 | 880% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and the requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 13% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of the network were rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. | 12 | (88%) Variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. Delays in Environmental Assessment review and completion of Historical and Cultural Preservation Review delayed purchases of land for building placement sites and required easements. Phase 1 archaeological survey and shovel testing required to discover artifacts in 9.3 mile buried section and land for building placement. Land has been purchased for one building site, but site prep and building placement may not proceed until the Phase survey is completed and approvals obtained. | 100 | 154% Variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network design rerouted in connection with Environmental Assessment and completion of Historical and Cultural Preservation Review due to number of archaeological prehistoric and historic sites in Hardy County. | 0 | (100%) Variance. Site preparation may not proceed until completion of Phase 1 archaeological survey and approval by WV Historic Preservice Office and National Telecommunications & Information Administration. | 28 | (72%) Variance. Baseline forecast included Equipment Deployment expenditures in Equipment Procurement budget. Deployment expenditures have been included in this category for consistency. Delivery dates were deferred until two facilities sites could be connected over fiber. Equipment will be installed in five central office sites in Q4 2011. | 100 | 6% Variance. Delays in obtaining historic preservation approvals for buried construction required aerial construction to commence in advance of buried construction, leading to inefficiencies from deploying the network in portions rather than continuously. Backtracking to buried portions increases resource requirements. Cost of fiber increased by approximately 6.75% due to high demand and limited supply. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above. | 2011-11-22 16:57 | 2011-11-22 16:57 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2011 | Q4 | Q4 - 2011 | 5272 | 4940 | FALSE | 77 | (23)% Variance. Delays in Intercreditor Agreement, Environmental Assessment review, and completion of Historic and Cultural Preservation Review prevented draw down of funds until April, 2011. Archaeological shovel testing and Phase 1 Survey report delayed construction until September, 2011. | 100 | Inspection | 66% Variance. Inspection in Network Build but broken out for clarity. Delays in construction expected due to requirement for shovel testing and section 106 review of replacement poles and ground anchors. | 100 | 779% Variance. Cost of environmental assessment and archaeological services ran significantly over budget due to the high number of prehistoric and historic sites in Hardy County, WV and requirement for a Phase 1 archaeological survey and shovel testing. | 100 | 44% Variance. Resources reallocated to completion of environmental/archaeological assessments. Segments of network rerouted and redesigned from buried cable to aerial placement, to avoid identified historic and cultural sites. Route modifications due to R/W acquisition issues. Laterals to anchor institutions will require a Phase 1 survey and shovel testing for buried sections, new poles or replacements, ground anchors and pedestals. | 12 | (88)% variance. The baseline forecast included purchases of land, structures and appraisals, and purchases of land or easements for Rights of Way in this category. Costs associated with obtaining no-cost private Rights of Way were included in Permitting & Other Approvals. | 100 | 141% variance. The baseline forecast included costs of land, structures, appraisals and purchases of land or easements for Rights of Way in the Rights of Way budget category. Costs associated with construction permitting and obtaining no-cost private Rights of Way were included in this category. Network rerouted in some locations due to number of archaeological prehistoric and historic sites in Hardy County. Route modifications required for locations where a private easement could not be obtained. | 0 | (100%) Site prep covered by recipient. | 26 | (74)% variance. Savings obtained through competitive vendor procurements, and purchase of operating equipment from non-award funds. | 70 | (30)% variance. Construction delayed due to delays in intercreditor agreement and archaeological surveys and shovel testing. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | NA. Same as above. | 2012-02-27 01:51 | 2012-02-27 01:51 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2012 | Q1 | Q1 - 2012 | 6242 | 5723 | FALSE | 100 | 0% Variance | 100 | Inspection | 143% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 949% Variance. 911% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 64% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). | 12 | (88)% Variance. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 157% Variance. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100)% Variance. Site preparation costs covered by Recipient. | 41 | (59)% Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 94 | (6)% Variance. Variance is due to negotiated savings in construction costs. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | N/A. Same as above | 2012-05-21 22:14 | 2012-05-21 22:14 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2012 | Q2 | Q2 - 2012 | 7088 | 6171 | FALSE | 100 | 0% Variance | 100 |  | 232% Variance. Utilization of multiple contractors and crews to overcome environmental and historic preservation delays to construction commencement. Delays prevented construction prior to third quarter of 2011. | 100 | 856% Variance. Historic preservation studies and surveys significantly delayed buried construction and materially increased project costs. | 100 | 53% Variance. Network reroutes or changes in deployment methods to avoid potential effects on historic sites; Network redesigned to leverage Hardy AnchorRing Middle Mile backbone network to provide fiber facilities for the Hardy OneNet Last Mile Fiber-to-the-Home ("FTTH") network funded by the Rural Utilities Service ("RUS") of the U.S. Dept. of Agriculture under the Broadband Initiatives Program ("BIP"). | 12 | (88)% Variance. The baseline included costs of land, structures, and appraisals in this category. Private rights of way acquisition costs were included in the Construction Permits and Other Approvals Category. The number of facilities required to transmit services decreased due to the use of long-range optics and availability of fiber-to-the-home in the BIP-funded Hardy OneNet network. | 100 | 157% Variance. Sections of line were rerouted and/or redesigned as aerial placement to avoid potential effects to historic and cultural sites along the route. Private rights of way acquisition costs are included in this category. | 0 | (100)% Variance. Site preparation costs covered by Recipient. | 34 | (66)% Variance. Baseline category included Equipment Deployment. Deployment expenditures have been included for consistency. Equipment deployed in 20 central offices and remote sites. Vendor negotiations produced significant savings on electronics. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced the requirement for electronics at all sites. | 98 | (2)% Variance. Variance is due to negotiated savings in equipment costs. Use of long-range optics and availability of fiber-to-the-home in the BIP funded Hardy OneNet network reduced requirements for electronics at all sites and facilities construction and upfits. | 0 | N/A. Baseline forecast included equipment deployment in Equipment Procurement budget. | 0 | Baseline = 0. Testing included in Architectural and Engineering Services. | 2012-08-15 15:46 | 2012-08-15 15:46 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2012 | Q3 | Q3 - 2012 | 7876 | 6642 | FALSE | 100 | No Variance. | 100 | Inspection | 232% Variance as previously noted. No change from Q3-2012 | 100 | 875% Variance as previously noted. No change from Q3-2012. | 100 | 78% Variance as previously noted. No change from Q3-2012. | 12 | (88)% Variance as previously noted. No change from Q3-2012. | 100 | 157% Variance as previously noted. No change from Q3-2012. | 0 | (100)% Variance as previously noted. No change from Q3-2012 | 34 | (66)% Variance as previously noted. No change from Q3-2012 | 100 | 2% Variance. | 0 | Baseline = 0 | 0 | Baseline = 0 | 2012-11-14 14:47 | 2012-11-14 14:47 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570035 | 2012 | Q4 | Q4 - 2012 | 8792 | 7590 | FALSE | 100 | Award completed in 2012 | 100 |  | Awarded completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 100 | Award completed in 2012 | 2013-02-14 21:31 | 2013-02-14 21:31 | 5526 | 5526 | Hardy Telecommunications, Inc.
NT10BIX5570036 | 2010 | Q3 | Q3 - 2010 | 398 | 1465 | FALSE | 70 | N/A | 0 |  | N/A | 100 | Complete | 50 | On track | 0 | N/A constructions will be on our own property. | 100 | Complete | 100 | N/A | 75 | Delayed from 3Q | 75 | N/A | 75 | N/A | 50 | N/A | 2010-11-23 17:18 | 2010-11-23 17:18 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570036 | 2010 | Q4 | Q4 - 2010 | 1156 | 2196 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | On Track | 0 | N/A - All construction will be on our own property. | 100 | Complete | 50 | Variance from baseline due to delay in construction procurement process. | 80 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 60 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 17:44 | 2011-02-15 17:44 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570036 | 2011 | Q1 | Q1 - 2011 | 2310 | 2900 | FALSE | 35 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 37 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 40 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 2011-05-25 16:37 | 2011-05-25 16:37 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570036 | 2011 | Q2 | Q2 - 2011 | 3378 | 3452 | FALSE | 35 | Next quarter we plan to complete all construction, equipment procurement and deployment. The percent complete is based on projected invoiced expenses in 3Q. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Outside plant construction should be completed. Delays are due to longer construction procurement process than expected. The percent complete is based on projected invoiced expenses in 3Q. | 37 | Most equipment will be purchased by the end of next quarter. The percent complete is based on projected invoiced expenses in 3Q. | 100 | Expected to be completed as there are 4 interconnection points where equipment needs to be installed. | 100 | Expected to be completed as there are 4 interconnection points where equipment needs to be installed. | 95 | Network testing should be completed by early 4Q as there are 4 interconnection points where equipment needs to be tested. | 2011-08-30 13:36 | 2011-08-30 13:36 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570036 | 2011 | Q3 | Q3 - 2011 | 4334 | 4023 | FALSE | 42 | Next quarter we plan to complete our network build and equipment testing. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 45 | Construction will be completed | 43 | We should have the majority equipment purchased. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:38 | 2011-11-30 14:38 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2011 | Q4 | Q4 - 2011 | 5298 | 4968 | FALSE | 43 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:43 | 2012-02-27 15:43 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2012 | Q1 | Q1 - 2012 | 6054 | 5626 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 11:59 | 2012-05-14 11:59 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2012 | Q2 | Q2 - 2012 | 6514 | 5871 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:06 | 2012-07-27 12:06 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2012 | Q3 | Q3 - 2012 | 7692 | 6530 | FALSE | 43 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 22:57 | 2012-10-30 22:57 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2012 | Q4 | Q4 - 2012 | 8528 | 7254 | FALSE | 45 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 61 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:20 | 2013-01-30 16:20 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570036 | 2013 | Q1 | Q1 - 2013 | 11980 | 10138 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-21 16:00 | 2014-03-21 16:00 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570037 | 2010 | Q3 | Q3 - 2010 | 146 | 1339 | FALSE | 20 | Construction delayed due to Environmental Assessment taking longer than anticipated | 0 |  | N/A | 100 | Should be completed | 50 | Network Design is based on electronics selected. | 75 | On-schedule | 75 | On-schedule | 50 | On-schedule | 35 | On-schedule | 5 | Environmental Assessment taking longer than anticipated | 15 | Environmental Assessment taking longer than anticipated | 5 | Environmental Assessment taking longer than anticipated | 2010-10-12 10:07 | 2010-10-12 10:07 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2010 | Q4 | Q4 - 2010 | 500 | 1524 | FALSE | 35 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Completed | 75 | On-schedule | 75 | Working with City of Harlem and Grovetown on rights of way issues. | 65 | Permit process taking longer than anticipated | 30 | Site plans are prepared for each construction phase. | 25 | Dependant upon network design to be completed. | 10 | Environmental Assessment and permit process taking longer than anticipated | 0 | Dependant upon network design to be completed and purchase of equipment. | 0 | Dependant upon network design to be completed and purchase of equipment. | 2011-01-21 07:42 | 2011-01-21 07:42 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2011 | Q1 | Q1 - 2011 | 2068 | 2779 | FALSE | 40 | Environmental Assessment and permit process taking longer than anticipated | 0 |  | N/A | 100 | Completed | 75 | Environmental Assessment and permit process taking longer than anticipated | 100 | Working with City of Harlem and Grovetown on rights of way issues. | 100 | On Target | 100 | On Target | 35 | Dependant upon network design to be completed | 20 | Environmental Assessment and permit process taking longer than anticipated | 0 | Dependant upon network design to be completed. | 0 | Dependant upon network design to be completed. | 2011-05-17 06:22 | 2011-05-17 06:22 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2011 | Q2 | Q2 - 2011 | 2918 | 3216 | FALSE | 50 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 95 | Dependant upon Electronics selected for network | 100 | Our County Attorney is drafting Permanent Easements with the property owners inside the city limits. Once the easements have been completed, our ROW acquisition staff will meet with each property owner to execute the easement. We have identified approximately 25 easements needed in side the cities. | 100 | Working with cities and CSX Transportation on permits and approvals. Our County Attorney is currently reviewing Facility Encroachment Agreements with CSX. We should have all DOT permits and CSX Encroachment Agreements approved by September 30, 2011. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 100 | Working with cities and CSX Transportation on permits and approvals to start construction inside the city limits and railroad crossing construction. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 53 | Issuing electronics RFP by September 1, 2011. Most of expenses are from Columbia County Board of Education in-kind equipment purchased. | 45 | Environmental, permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2 | Issuing electronics RFP by September 1, 2011. | 0 | Dependant upon electronics purchase | 2011-08-02 07:19 | 2011-08-02 07:19 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2011 | Q3 | Q3 - 2011 | 3930 | 3803 | FALSE | 69 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 95 | dependant upon electronics selected for network. | 98 | Actively acquiring permanent easements from home owners inside the cities. | 100 | We should have all permits for Phase VI construction and one final interstate DOT permit by end of quarter. | 98 | We should have all permits for Phase VI construction and one final interstate DOT permit by end of quarter. We are currently installing broadband infrastructure where we have permits and approvals and these delays should not impact our overall schedule. | 40 | Currently the County is seeking network electronics proposals to provide various broadband middle mile services. Once the proposals are submitted, County staff will evaluate the submitted proposals. County staff should recommend a firm for approval by February 2012. | 65 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2 | Dependant upon electronics selected and purchased. | 0 | Dependant upon electronics selected and purchased. | 2011-11-09 06:40 | 2011-11-09 06:40 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2011 | Q4 | Q4 - 2011 | 5342 | 5013 | FALSE | 87 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 100 | Fiber splicing plan to be finalized by February 10, 2012 | 100 | Actively working with County Attorney, City of Harlem and Grovetown and Right of Way Acquisition Department to obtain the final 9 easements needed for the routes inside city limits. | 100 | Submitted the final DOT permit for interstate crossing and waiting approval from Georgia State DOT. | 100 | We have all DOT permits except one final interstate permit. We are currently installing infrastructure where we have permits and approvals. These delays should not impact overall project. | 10 | County staff currently reviewing submitted electronic proposals. | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule | 5 | Dependant upon electronics selected and purchased | 0 | Dependant upon construction, electronics selected and purchased | 2012-02-28 13:00 | 2012-02-28 13:00 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2012 | Q1 | Q1 - 2012 | 5924 | 5561 | FALSE | 90 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 |  | N/A | 100 | Completed | 99 | Fiber splicing plan completed and minor changes may take place after electronics have been selected. | 100 | Completed | 100 | Completed | 100 | Completed | 25 | Equipment will be selected and on order. | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 5 | Dependent upon electronics selected and purchased. | 5 | Dependent upon electronics selected and purchased. | 2012-05-04 07:46 | 2012-05-04 07:46 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2012 | Q2 | Q2 - 2012 | 7126 | 6190 | FALSE | 95 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule | 0 |  | N/A | 100 | Completed | 99 | Minor changes may take place after electronics are being installed. | 100 | Completed | 100 | Completed | 100 | Completed | 95 | Wireless Access Points to be purchased. | 98 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 50 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 100 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 2012-08-17 16:40 | 2012-08-17 16:40 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2012 | Q3 | Q3 - 2012 | 7846 | 6627 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2012-11-13 13:53 | 2012-11-13 13:53 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2012 | Q4 | Q4 - 2012 | 9130 | 7910 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-03-06 15:32 | 2013-03-06 15:32 | 5532 | 5532 | Columbia, County of
NT10BIX5570037 | 2013 | Q1 | Q1 - 2013 | 9178 | 8010 | FALSE | 100 | Completed | 0 |  | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-04-15 08:08 | 2013-04-15 08:08 | 5532 | 5532 | Columbia, County of
NT10BIX5570038 | 2010 | Q3 | Q3 - 2010 | 396 | 1464 | FALSE | 60 | Ahead | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 70 | On track | 60 | On track | 50 | On track | 50 | On track | 40 | On track | 2010-11-23 17:12 | 2010-11-23 17:12 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570038 | 2010 | Q4 | Q4 - 2010 | 1102 | 2143 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 75 | Variance from baseline due to delay in construction procurement process. | 85 | Ahead | 75 | On track | 65 | Variance from baseline due to delay in construction procurement process. | 50 | Variance from baseline due to delay in construction procurement process. | 2011-02-11 17:24 | 2011-02-11 17:24 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570038 | 2011 | Q1 | Q1 - 2011 | 1822 | 2654 | FALSE | 27 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 41 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 26 | Variance from baseline due to delay in construction procurement process. Plan to purchase our support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 40 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 25 | Variance from baseline due to delay in construction procurement process. | 2011-05-02 09:40 | 2011-05-02 09:40 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570038 | 2011 | Q2 | Q2 - 2011 | 3380 | 3453 | FALSE | 28 | The majority of the project will be complete by the end of 3Q. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 13 | Majority of work will be completed by end of 3Q. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 32 | Most equipment should be purchased by next quarter. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 100 | Complete | 100 | Complete | 90 | Network testing should be completed by early 4Q. | 2011-08-30 13:37 | 2011-08-30 13:37 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570038 | 2011 | Q3 | Q3 - 2011 | 4336 | 4024 | FALSE | 37 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 37 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 37 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:40 | 2011-11-30 14:40 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2011 | Q4 | Q4 - 2011 | 5300 | 4970 | FALSE | 39 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:46 | 2012-02-27 15:46 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2012 | Q1 | Q1 - 2012 | 6056 | 5627 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:00 | 2012-05-14 12:00 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2012 | Q2 | Q2 - 2012 | 6516 | 5872 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 53 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:11 | 2012-07-27 12:11 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2012 | Q3 | Q3 - 2012 | 7694 | 6531 | FALSE | 39 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 22:59 | 2012-10-30 22:59 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2012 | Q4 | Q4 - 2012 | 8532 | 7257 | FALSE | 40 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 54 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 37 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:23 | 2013-01-30 16:23 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570038 | 2013 | Q1 | Q1 - 2013 | 12030 | 10194 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | omplete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:10 | 2014-04-14 12:10 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570039 | 2010 | Q3 | Q3 - 2010 | 330 | 1431 | FALSE | 10 | Requirement to issue new RFP has delayed | 75 | Contracts, Audit, Admin. | Requirement to issue new RFPs has delayed | 100 | N/A | 70 | Requirement to issue new RFPs has delayed | 25 | Requirement to issue new RFPs has delayed | 20 | Requirement to issue new RFPs has delayed | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-16 21:38 | 2010-11-16 21:38 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2010 | Q4 | Q4 - 2010 | 1184 | 2217 | FALSE | 15 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 90 |  | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 100 | N/A | 90 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 35 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | N/A | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | N/A | 0 | N/A | 2011-02-16 14:54 | 2011-02-16 14:54 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2011 | Q1 | Q1 - 2011 | 2166 | 2828 | FALSE | 19 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. | 100 | contracts etc. | Due to requirement to issue new RFPs and select new contractors this item was delayed but will be complete in this quarter as contracts with contractors are concluded. | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 100 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. The preliminary design of the microwave, fiber optic, transport, and municipal RAN are near complete. Specific design should be completed this quarter. | 60 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. In addition, the slower than anticipated pace of securing Master Agreements from one utility and the slow pace of permitting with Army Corps of Engineers has slowed this category. It is anticipated that significant progress will be achieved in this quarter with regard to pole and conduit license applications, tower access license applications, and the crossing of the Cape Cod Canal. A decision is also anticipated on the best approach to crossing the Taunton River. | 60 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. Significant progress will be made in this category in Y2Q2. A Construction Manager will be selected to begin renovation of the Regional Collocation Center to code and ADA compliance. An RFP will be issued for the construction of the data center within the Collocation Center. Special Permit applications will be submitted to the Massachusetts DOE, DCR, and other agencies for crossings of roads and rail beds, etc. The FCC 700Mhz waiver will be submitted by Barnstable County. | 0 | N/A | 20 | OpenCapeâ€™s contractor has been engaged with vendors of fiber optics, optronics, and other equipment to determine qualified bidders and issue bid documents. Major equipment purchases are anticipated in Y2Q2 and Y2Q3 of fiber and optronics. | 5 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. In addition, the pace of completion of utility pole and conduit owner license application processing and make ready have slowed this category. OpenCape's contractor will engage and select sub-contractors for the installation of fiber optics and microwave systems in this quarter. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at expected pace. | 0 | Network testing shall keep pace with the construction of segments of the network. | 2011-05-19 11:30 | 2011-05-19 11:30 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2011 | Q2 | Q2 - 2011 | 2934 | 3224 | FALSE | 25 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. OpenCape adjusted to that disruption and established a new normal for its baseline following completion of its contract with CapeNet LLC to design and build the network. Since that time there has been substantial program progress. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. | 100 |  | Complete | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. This process involves OpenCape, its field survey and engineering contractor, and its environmental engineering contractor. Potential deviations from the original EA are identified and will be consolidated into a future submission for amendment of the EA. OpenCape has also engaged the Army Corps of Engineers for the crossing of the Cape Cod Canal and will fulfill the specific EA requirement of their process as stated in the EA and FONSI. | 85 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Network Design specifically has also been delayed by discoveries during site visits and detailed engineering. For example, OpenCape intends to use an existing fire tower on Martha's Vineyard for a microwave link from Cape Cod to the Island. Preliminary analysis indicates this tower is currently overloaded. A detailed engineering evaluation is scheduled to determine if the tower can be altered to accommodate OpenCape equipment while simultaneously evaluating alternative towers. The design of the microwave, fiber optic, transport, and municipal RAN are near complete and expected to be completed well within required parameters to order equipment and perform installation. | 60 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Rights of Way specifically has also been delayed by a far more lengthy process for obtaining rights than was anticipated. OpenCape is fully engaged in the process of submitting special permits, developing the contractual basis of leases to towers to support the microwave component, and applying for access to Verizon Central Offices. The Army Corps of Engineers permitting of critical crossings at the Cape Cod Canal and the Taunton River is very slow and represents a critical element of delay in this category. Obtaining access to towers for the placement of microwave equipment is also a time consuming process because the tower owners must go through a process required by Chapter 30B of the Massachusetts General Laws; however, this process is moving forward at an acceptable pace at this time to | 55 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Apart from the general delay described in Section 3, Construction permits is also delayed by the unexpected slow pace of make ready assessment by utility pole owners with regard to the fiber optic component of the project. OpenCape is focusing on completing make ready work in the NGrid territory where it has more control and confidence in obtaining licenses time coincident with the delivery of fiber. OpenCape is monitoring very closely the performance of NSTAR in performing make ready assessment and requesting improved performance when the pace falls short of requirements. The company has responded to these requests and we will continue to work together to ensure that the pace reaches a level that is acceptable to OpenCape and supportive of its goals. The collocation center portion is progressing appropriately as OpenCape has contracted with Stat | 0 | N/A | 20 | At baseline. OpenCapeâ€™s contractor has engaged vendors of fiber optics, optronics,and other equipment to determine qualified bidders and issue bid documents. The first order of 35 miles of fiber has been placed with an anticipated delivery in September, 2011. The delivery date was 8 weeks after order placement. This is consistent with the timeline of anticipated completed make ready and sub-contractor selection for installation of the fiber beginning in October 2011. | 5 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. The Network Build is significantly delayed, but readily recoverable by compressing the installation of fiber within a more aggressive time line. There is a significant dependency in this category on the make ready assessment and make ready work being completed. OpenCape is focusing its initial network build area on the NGrid territory where it has more control and confidence in obtaining licenses time coincident with the delivery of fiber. This will permit the contractor to begin work as early as possible in 20% of the territory with the anticipation that when that work is complete there will be NSTAR licenses forthcoming for work in that territory. | 0 | The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an appropriate pace. OpenCape expects to have equipment available, rights secured, and construction complete in adequate time for network equipment deployment. | 0 | At baseline. The original baseline submitted by OpenCape was disrupted by the need to issue new RFPs for the project. This is explained in Section 3. Network Testing is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, construction completion, and equipment deployment. It is anticipated that Network Testing will follow at an appropriate pace. OpenCape expects to have equipment available, rights secured, construction complete, and equipment deployed in adequate time for Network Testing to be completed on time. | 2011-08-05 14:21 | 2011-08-05 14:21 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2011 | Q3 | Q3 - 2011 | 3932 | 3804 | FALSE | 31 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. OpenCape continues to adjust to challenges with innovative solutions and aggressive action. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending up to 45% of its funds by January 31, 2012, but anticipates the true project status to be substantially complete at that time based on an assessment of tasks and milestones that will be complete or near complete. | 100 |  | Complete | 100 | OpenCape has a continual process of review to ensure compliance with its EA FONSI. Though the EA Assessment and FONSI are complete,an amendment was necessary to record changes from the original submission. Approval of the EA Amendment is anticipated in the fourth quarter. | 95 | Early delays caused by the transition to a new contractor have been overcome and the design of the microwave, fiber optic, transport, and municipal RAN are near complete. | 65 | Early delays caused by the transition to a new contractor have been overcome and OpenCape has submitted necessary applications to obtain access to two crossings of the Cape Cod Canal. Obtaining access to towers for the placement of microwave equipment is underway but the process is slow as the owners of the towers are public entities that must comply with Commonwealth of Massachusetts procurement laws. | 60 | Early delays caused by the transition to a new contractor have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. Permit applications have been submitted for the renovation of the former Barnstable County Public Safety building with the necessary entities. | 0 | N/A | 30 | OpenCape is on a path for procurement consistent with on time completion of the project. The first fiber delivery of nine reels arrived in September, 2011 and deliveries of 35 miles each month are anticipated. Ciena was selected as the provider of routing and switching equipment and orders will be placed early in the fourth quarter. The completion of the microwave path assessment and start of frequency studies will result in the potential order of radio equipment in the fourth quarter. | 7 | Network Build is greatly dependent on make ready completion. It is therefore delayed. However, sub-contractors for fiber construction have been selected and materials are in hand to begin construction. Make ready has begun in the National Grid territory of the project. Underground work is primed to begin, but awaits a positive Environmental Assessment Amendment review. Microwave construction is dependent on obtaining lease rights from municipal authorities under a complex and slow procurement process required by Commonwealth of Massachusetts Chapter 30B. | 0 | Equipment deployment is dependent on the procurement of equipment, obtaining necessary rights and permits, engineering, and construction completion. It is anticipated equipment deployment will follow at an acceptable pace as the vendor has been selected for switching and routing and configuration of DWDM can be achieved in parallel with construction of the fiber. | 5 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2011-11-09 10:16 | 2011-11-09 10:16 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2011 | Q4 | Q4 - 2011 | 5212 | 4881 | FALSE | 47 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 45% of its funds by the end of this quarter, but anticipates the true project to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 92 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 95 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps are near complete. | 75 | OpenCape expects to secure underlying rights to the Cape Cod Canal and Taunton RIver crossings this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to necessary towers in this quarter and furthering the lease process in parallel. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are expected to begin flowing in this quarter and maintain a pace consistent with the construction plan. | 85 | Early delays have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. Permit applications have been submitted for the renovation of the former Barnstable County Public Safety building with the necessary entities. | 0 | N/A | 77 | OpenCape is on a path for procurement consistent with on time completion of the project. The first fiber delivery of nine reels arrived in September, 2011 and a total of over 200 miles will be on hand by the end of the first quarter with continued delivery of 35 miles each month until all fiber is in hand by June, 2012. Switching, routing, DWDM, and microwave radio equipment will all be delivered early in the first quarter. | 31 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline. Make ready work in National Grid territory will be completed early in this quarter to provide over 40 miles of buildable segments. NSTAR make ready reassessment will be completed early in the quarter, licenses for segments without make ready requirements will be provided early in the quarter. Make ready on the remainder will begin and production will be adequate to support the construction plan. | 25 | All equipment will be on hand in this quarter. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build. | 10 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-02-23 14:34 | 2012-02-23 14:34 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2012 | Q1 | Q1 - 2012 | 5530 | 5359 | FALSE | 62 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 62% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 95 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 99 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 90 | OpenCape expects to secure underlying rights to the Cape Cod Canal and Taunton RIver crossings this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are flowing in this quarter and expected to maintain a pace consistent with the construction plan. | 95 | Early delays have been overcome and OpenCape is fully engaged in the process of submitting applications for and receiving permits locally, with state agencies, railroad owners, and others. | 0 | N/A | 97 | OpenCape is on a path for procurement consistent with on time completion of the project. Nearly all fiber is expected to have been delivered by the end of Q2 2012. Switching, routing, DWDM, and microwave radio equipment is on hand to for installation upon receipt of leases for regeneration sites and towers. | 60 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline, but fast approaching a pace consistent with the projected construction timeline. A complete make ready reassessment in the NSTAR territory was required, but has been completed, all make ready work orders generated, and all invoices paid for make ready to begin. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. | 65 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 20 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-04-26 10:27 | 2012-04-26 10:27 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2012 | Q2 | Q2 - 2012 | 6904 | 6078 | FALSE | 77 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 77% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 99 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 98 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 99 | OpenCape expects to secure remaining underlying rights to the Taunton River crossing this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to all remaining necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. Pole licenses from pole owners are flowing in this quarter and expected to maintain a pace consistent with the construction plan. | 99 | Nearly all permits are in hand with the exception of permits associated with installation of antennas on towers. These final remaining permits are anticipated in Q3. | 0 | N/A | 99 | Nearly all equipment will be received by the end of Q3. | 70 | Network Build is greatly dependent on make ready completion. It is therefore delayed when compared with baseline or PIP. A complete make ready reassessment in the NSTAR territory was required, but has been completed, all make ready work orders generated, and all invoices paid for make ready to begin. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. See section 3. | 55 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is anticipated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 45 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber. | 2012-08-07 15:40 | 2012-08-07 15:40 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2012 | Q3 | Q3 - 2012 | 8166 | 6793 | FALSE | 84 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. However, OpenCape has adjusted and is on target for on time completion based on its revised construction schedule. OpenCape expects to complete the project on time by taking advantage of built in flexibility within its original plan and creating flexibility by compressing certain aspects of the project such as the installation of fiber within a more aggressive timeline. OpenCape anticipates expending in total over 90% of its funds by the end of this quarter, but anticipates the true project progress to be much higher based on an assessment of tasks and milestones that will be complete or near complete. | 99 |  | Additional contract work was required that has necessitated continued work through the fourth quarter. | 100 | Complete | 99 | The design of the microwave, transport, and municipal RAN networks are complete and final fiber strand maps will be nearly completed. | 99 | OpenCape expects to secure remaining underlying rights to the Taunton River crossing this quarter. Obtaining these rights has taken longer than anticipated. OpenCape anticipates obtaining licenses to all remaining necessary towers in this quarter. Obtaining access to municipal towers has proven much more difficult and time consuming than anticipated, largely due to Commonwealth of Massachusetts procurement laws. | 99 | Nearly all permits are in hand with the exception of permits associated with installation of antennas on towers. These final remaining permits are anticipated in Q4. | 9 | N/A | 99 | Nearly all equipment has been received. | 90 | Network Build is greatly dependent on make ready completion and obtaining licenses and permits for microwave construction. It is therefore delayed when compared with baseline or PIP. OpenCape holds weekly conference calls with pole owners to expedite and coordinate on make ready. See section 3. | 75 | Equipment is on hand to support construction and deployment timelines. As underlying rights to facilities are obtained the equipment will be deployed. It is antici | 55 | Network testing shall keep pace with the construction of segments of the network; however, a minor amount is accomplished upon delivery of fiber.pated that equipment deployment will maintain a pace supportive of fiber build, and as rights to regeneration sites and towers are obtained. | 2012-11-30 08:57 | 2012-11-30 08:57 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2012 | Q4 | Q4 - 2012 | 9014 | 7789 | FALSE | 90 | OpenCape remains behind its original baseline for reasons described in Sections 2a and 3 above. For these reasons, OpenCape has requested a no cost extension to allow project completion. Utility company make ready will continue to be the pacing item. | 99 | Misc contract work | Additional contract work requirements will continue to be adjudicated as required to support the project. | 100 | Complete. | 100 | Additional design details for the municipal regional area network will be completed, as well as completion of as-build drawing at the completion of construction. | 100 | All final permits and licenses for both the fiber and microwave networks will be completed. | 100 | All final permits and licenses for both the fiber and microwave networks will be completed. | 0 | N/A | 98 | Only equipment that may not have been received would be final frequency specific microwave equipment, or ancillary equipment for laser tuning on the fiber network uncovered during testing. | 90 | All fiber construction should be complete. Final data center work may be delayed pending utility company power upgrade discussed above. Final microwave sites may lag depending on local jurisdictional approvals. | 95 | All equipment associated with the fiber network should be deployed. Final microwave sites may lag depending on local jurisdictional approvals. | 60 | Network testing involves a 5-8 week process for final configuration and tuning of electronics, and long duration bit error rate testing. The testing will follow construction completion on a segmented basis to allow incremental acceptance of the network. | 2013-02-27 14:14 | 2013-02-27 14:14 | 5535 | 5535 | OpenCape Corporation
NT10BIX5570039 | 2013 | Q1 | Q1 - 2013 | 10054 | 8583 | FALSE | 98 | OpenCape will remain behind its original baseline for reasons described in Sections 2a and 3 above. The network will progress to near completion during this quarter, however. | 95 | Misc contract work | Additional contract work requirements will continue to be adjudicated as required to support the project. | 100 | Complete | 100 | Complete | 96 | All final permits and licenses for the microwave network will have been completed. Rights of way for the additional laterals effectively added new work to this category. | 100 | Construction permits for microwave sites will be in place. These have been delayed by having to work through unique requirements of the 15 individual jurisdictions where the sites are located. | 0 | N/A | 98 | Purchase of equipment for the additional laterals will be substantially completed. | 95 | The initial fiber build will be completed during this period, with the additional laterals representing an increase in work scope that will continue to be worked through this period. | 90 | The delay in microwave system permitting will delay final equipment deployments. | 80 | Network testing can only be accomplished following network completion. As such, it will lag the original schedule for the same reasons that the overall project lags. | 2013-06-05 07:44 | 2013-06-05 07:44 | 7679 | 7679 | OpenCape Corporation
NT10BIX5570039 | 2013 | Q2 | Q2 - 2013 | 10360 | 8805 | FALSE | 99 | All network will be operational. Closeout will be underway. | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-07-30 15:23 | 2013-07-30 15:23 | 7679 | 7679 | OpenCape Corporation
NT10BIX5570039 | 2013 | Q3 | Q3 - 2013 | 11340 | 9470 | FALSE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-11-21 19:58 | 2013-11-21 19:58 | 7679 | 7679 | OpenCape Corporation
NT10BIX5570039 | 2013 | Q4 | Q4 - 2013 | 12278 | 10448 | FALSE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-06-19 15:43 | 2014-06-19 15:43 | 7679 | 7679 | OpenCape Corporation
NT10BIX5570039 | 2014 | Q1 | Q1 - 2014 | 12088 | 10250 | FALSE | 100 | Complete | 100 | Misc contract work | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-26 12:56 | 2014-04-26 12:56 | 7679 | 7679 | OpenCape Corporation
NT10BIX5570040 | 2010 | Q3 | Q3 - 2010 | 400 | 1466 | FALSE | 50 | N/A | 0 |  | N/A | 100 | Complete | 75 | On track | 0 | N/A construction will be on our own property. | 100 | Complete | 100 | N/A | 50 | N/A | 50 | N/A | 50 | N/A | 25 | N/A | 2010-11-23 17:25 | 2010-11-23 17:25 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570040 | 2010 | Q4 | Q4 - 2010 | 1158 | 2197 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Variance from baseline due to delay in construction procurement process.Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process.Plan to be on schedule by the end of Q2. | 50 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 30 | Variance from baseline due to delay in construction procurement process. Plan to be on schedule by the end of Q2. | 2011-02-15 17:55 | 2011-02-15 17:55 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570040 | 2011 | Q1 | Q1 - 2011 | 2364 | 2927 | FALSE | 24 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 22 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Variance from baseline due to delay in construction procurement process. Plan to purchase our support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 30 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 20 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:08 | 2011-05-27 08:08 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570040 | 2011 | Q2 | Q2 - 2011 | 3364 | 3445 | FALSE | 38 | Next quarter we will complete the construction and fiber splicing. The planned percent is strictly based on our budget. | 0 |  | N/A | 100 | Complete. | 100 | Complete. | 0 | N/A - All construction will be on our own property. | 100 | Complete | 31 | Delays are due to longer construction procurement process than expected. The percentage complete is based on projected invoiced expenses in 3Q. | 35 | Delays are due to longer construction procurement process than expected. The percentage complete is based on projected invoiced expenses in 3Q. | 95 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 95 | Delays are due to longer construction procurement process than expected. | 90 | Delays are due to longer construction procurement process than expected. | 2011-08-29 23:57 | 2011-08-29 23:57 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570040 | 2011 | Q3 | Q3 - 2011 | 4304 | 4002 | FALSE | 37 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 35 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 38 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-29 10:36 | 2011-11-29 10:36 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2011 | Q4 | Q4 - 2011 | 5302 | 4972 | FALSE | 37 | Finalizing construction project and begin working on the project close out. Percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:50 | 2012-02-27 15:50 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2012 | Q1 | Q1 - 2012 | 6058 | 5628 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:01 | 2012-05-14 12:01 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2012 | Q2 | Q2 - 2012 | 7150 | 6202 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-20 10:00 | 2012-08-20 10:00 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2012 | Q3 | Q3 - 2012 | 7696 | 6532 | FALSE | 37 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2012 | Q4 | Q4 - 2012 | 8540 | 7269 | FALSE | 38 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 38 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:40 | 2013-01-30 16:40 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570040 | 2013 | Q1 | Q1 - 2013 | 12034 | 10196 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:15 | 2014-04-14 12:15 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2010 | Q3 | Q3 - 2010 | 402 | 1467 | FALSE | 35 | N/A | 0 |  | 0 | 100 | Complete | 50 | . | 0 | N/A constructions will be on our own property. | 100 | Complete | 50 | Reprioritized states | 40 | Reprioritized states | 20 | Reprioritized states | 35 | Reprioritized states | 25 | N/A | 2010-11-23 17:33 | 2010-11-23 17:33 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570041 | 2010 | Q4 | Q4 - 2010 | 908 | 1948 | FALSE | 40 | Slightly behind due to construction RFP. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 35 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 50 | Slightly behind due to construction RFP. | 25 | Slightly behind due to construction RFP. | 2011-01-29 17:13 | 2011-01-29 17:13 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570041 | 2011 | Q1 | Q1 - 2011 | 2366 | 2928 | FALSE | 16 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 32 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 13 | Variance from baseline due to delay in construction procurement process. Plan to purchase the support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 30 | Variance from baseline due to delay in construction procurement process. | 30 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:10 | 2011-05-27 08:10 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570041 | 2011 | Q2 | Q2 - 2011 | 3366 | 3446 | FALSE | 39 | We plan to complete all construction and the majority of equipment deployments in the 3rd quarter. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 26 | Construction is targeted to be completed by end of 3Q. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 42 | The majority of equipment will be procured. The percent complete is based on invoiced expenses in 2Q. Delays are due to longer construction procurement process than expected. | 80 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 80 | Variance from baseline due to delay in construction procurement process. | 75 | Variance from baseline due to delay in construction procurement process. | 2011-08-30 00:11 | 2011-08-30 00:11 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570041 | 2011 | Q3 | Q3 - 2011 | 4302 | 4001 | FALSE | 44 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 68 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 41 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-29 10:33 | 2011-11-29 10:33 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2011 | Q4 | Q4 - 2011 | 5304 | 4974 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 66 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:52 | 2012-02-27 15:52 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2012 | Q1 | Q1 - 2012 | 6060 | 5629 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:02 | 2012-05-14 12:02 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2012 | Q2 | Q2 - 2012 | 7152 | 6203 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 71 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-08-20 10:08 | 2012-08-20 10:08 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2012 | Q3 | Q3 - 2012 | 7698 | 6533 | FALSE | 47 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:00 | 2012-10-30 23:00 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2012 | Q4 | Q4 - 2012 | 8544 | 7276 | FALSE | 48 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 72 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 44 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:51 | 2013-01-30 16:51 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570041 | 2013 | Q1 | Q1 - 2013 | 12032 | 10195 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:13 | 2014-04-14 12:13 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2010 | Q3 | Q3 - 2010 | 404 | 1468 | FALSE | 55 | During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. | 0 |  | N/A | 100 | Complete | 50 | See 2a. | 0 | N/A construction will be on our own property. | 100 | Complete | 25 | See 2a. | 40 | See 2a. | 15 | See 2a. | 15 | See 2a. | 10 | See 2a. | 2010-11-23 17:43 | 2010-11-23 17:43 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570042 | 2010 | Q4 | Q4 - 2010 | 1160 | 2198 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 65 | Variance from baseline due to delay in construction procurement process. | 85 | Variance from baseline due to delay in construction procurement process. | 65 | Variance from baseline due to delay in construction procurement process. | 65 | Variance from baseline due to delay in construction procurement process. | 40 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 18:02 | 2011-02-15 18:02 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570042 | 2011 | Q1 | Q1 - 2011 | 2368 | 2929 | FALSE | 17 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 17 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 18 | Variance from baseline due to delay in construction procurement process. Plan to purchase our ADM and support and management systems for monitoring. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 25 | Variance from baseline due to delay in construction procurement process. | 25 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:13 | 2011-05-27 08:13 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570042 | 2011 | Q2 | Q2 - 2011 | 3370 | 3448 | FALSE | 22 | All construction and fiber splicing will be completed. The majority of equipment deployments should also be completed. Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 25 | Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 22 | Delays are due to longer construction procurement process than expected. The percent complete is based on invoiced expenses in 2Q. | 90 | Our network build will be the deployment of transport equipment (2i) at each of our interconnection sites. | 90 | Variance from baseline due to delay in construction procurement process. | 80 | Variance from baseline due to delay in construction procurement process. | 2011-08-30 00:19 | 2011-08-30 00:19 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570042 | 2011 | Q3 | Q3 - 2011 | 4340 | 4026 | FALSE | 30 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 38 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 29 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 95 | Should be very close to completion by the end of next quarter. | 2011-11-30 14:41 | 2011-11-30 14:41 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2011 | Q4 | Q4 - 2011 | 5308 | 4977 | FALSE | 32 | Fiber assignments at three of the sites have taken a bit longer than expected, but plan on having it completed early in the 1st quarter. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 57 | Complete. Percent complete is strictly based on the budget. We expect to be under budget for this line item. | 28 | Complete. Percent complete is strictly based on the budget. We expect to be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:55 | 2012-02-27 15:55 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2012 | Q1 | Q1 - 2012 | 6062 | 5630 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:03 | 2012-05-14 12:03 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2012 | Q2 | Q2 - 2012 | 6522 | 5875 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 59 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:20 | 2012-07-27 12:20 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2012 | Q3 | Q3 - 2012 | 7700 | 6534 | FALSE | 32 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:01 | 2012-10-30 23:01 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2012 | Q4 | Q4 - 2012 | 8546 | 7278 | FALSE | 33 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 60 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 28 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 16:54 | 2013-01-30 16:54 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570042 | 2013 | Q1 | Q1 - 2013 | 12036 | 10197 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-14 12:17 | 2014-04-14 12:17 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2010 | Q3 | Q3 - 2010 | 406 | 1469 | FALSE | 55 | Ahead | 0 |  | 0 | 100 | Complete | 100 | Ahead | 0 | N/A constructions will be on our own property. | 100 | Complete | 100 | Ahead | 50 | N/A | 50 | Ahead | 50 | Ahead | 25 | Ahead | 2010-11-23 17:50 | 2010-11-23 17:50 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570043 | 2010 | Q4 | Q4 - 2010 | 1162 | 2199 | FALSE | 60 | Variance from baseline due to delay in construction procurement process. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 40 | Variance from baseline due to delay in construction procurement process. | 45 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 35 | Variance from baseline due to delay in construction procurement process. | 20 | Variance from baseline due to delay in construction procurement process. | 2011-02-15 18:09 | 2011-02-15 18:09 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570043 | 2011 | Q1 | Q1 - 2011 | 2370 | 2930 | FALSE | 25 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 25 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 26 | Variance from baseline due to delay in construction procurement process. Per April 19th NTIA guidance, the percent complete is strictly based on the budget. | 15 | Variance from baseline due to delay in construction procurement process. | 15 | Variance from baseline due to delay in construction procurement process. | 10 | Variance from baseline due to delay in construction procurement process. | 2011-05-27 08:17 | 2011-05-27 08:17 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570043 | 2011 | Q2 | Q2 - 2011 | 3372 | 3449 | FALSE | 38 | In the 3rd quarter we expect to complete all equipment deployment and the majority of network testing. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 0 |  | N/A | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 58 | Variance from baseline due to delay in construction procurement process. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 37 | Variance from baseline due to delay in construction procurement process. The percent complete is based on projected invoiced expenses in 3Q. Delays are due to longer construction procurement process than expected. | 100 | Complete | 100 | Complete | 85 | Network testing is dependent upon completion of construction and equipment deployment. The testing should be completed by early 4Q. | 2011-08-30 00:36 | 2011-08-30 00:36 | 5516 | 5516 | Level 3 EON, LLC
NT10BIX5570043 | 2011 | Q3 | Q3 - 2011 | 4342 | 4027 | FALSE | 41 | The majority of the project will be complete by the end of 3Q, but the percent complete is strictly based on the budget. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 49 | The site preparation will be complete, but the percent complete is strictly based on the budget. | 41 | The equipment procurement will be complete, but the percent complete is strictly based on the budget. | 100 | Complete | 100 | Complete | 100 | Complete | 2011-11-30 14:43 | 2011-11-30 14:43 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2011 | Q4 | Q4 - 2011 | 5310 | 4979 | FALSE | 45 | Finalize construction portion of the project and begin working on the project close out. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 69 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-02-27 15:57 | 2012-02-27 15:57 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2012 | Q1 | Q1 - 2012 | 6064 | 5631 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-05-14 12:05 | 2012-05-14 12:05 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2012 | Q2 | Q2 - 2012 | 6524 | 5876 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-07-27 12:22 | 2012-07-27 12:22 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2012 | Q3 | Q3 - 2012 | 7702 | 6535 | FALSE | 44 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2012-10-30 23:02 | 2012-10-30 23:02 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2012 | Q4 | Q4 - 2012 | 8550 | 7285 | FALSE | 46 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 67 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 42 | Complete. Percent complete is strictly based on the budget. We will be under budget for these line items. | 100 | Complete | 100 | Complete | 100 | Complete | 2013-01-30 17:01 | 2013-01-30 17:01 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570043 | 2013 | Q1 | Q1 - 2013 | 11974 | 10135 | FALSE | 100 | Percent complete is strictly based on the budget. We will be under budget for these line items. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 0 | N/A - All construction will be on our own property. | 100 | Complete | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete. Percent complete is strictly based on the budget. We will be under budget for this line item. | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-20 16:23 | 2014-03-20 16:23 | 7224 | 7224 | Level 3 EON, LLC
NT10BIX5570044 | 2010 | Q3 | Q3 - 2010 | 448 | 1490 | FALSE | 3 | This was projected to be at 10%. The length of time needed to complete the Environmental Assessment and hire our engineering firm has put us behind schedule. We are working on ways of expediting the awards of our construction contracts to get us back on schedule. This was projected to be at 10%. | 0 |  | N/A | 100 | Complete | 50 | Projected at 100%. We will have paid some invoices from our engineering firm in the 4th quarter, but most will come in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 50 | Projected at 100%. We will have acquired some of our rights of way in this quarter, but this will be completed in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 50 | Projected at 100%. This will be completed in the 1st Quarter of Year 2. The length of time it took to bid and hire the engineering firm put this category behind schedule. | 0 | N/A | 0 | Projected at 10%. We will have identified our FTTP vendor, which will easily make this category on schedule from an accomplishment perspective, but we will not have purchased any equipment before the end of the 4th quarter. We do not anticipate purchasing much equipment before the 2nd Quarter of Year 2. | 0 | N/A | 0 | N/A | 0 | N/A | 2010-11-29 19:19 | 2010-11-29 19:19 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2010 | Q4 | Q4 - 2010 | 1326 | 2349 | FALSE | 8 | Baseline plan was 15%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that we would have spent 15% of our project budget by the end of the 5th quarter. Based on actual expenditures, it will take until the 4th quarter of 2011 to get back on target, and even that may be difficult. For this category and others below, we were too optimistic that we could move a project of this magnitude through the established processes of the University and two cities as fast as we projected in our revised baseline plan. As mentioned elsewhere, the weatherman has not done us any favors either. | 0 |  | N/A | 100 | Completed | 75 | Baseline plan was 100%.At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the engineering would be complete by the end of the 4th quarter. This will be completed in the second quarter of 2011. | 50 | Baseline plan was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the rights-of-way would be acquired by the end of the 4th quarter. In order to continue to make progress on the construction, an "easement free" design will initially be bid, with the paths that require private easements bid as alternates. That will allow the lengthy process of acquiring the private easements to continue in parallel with the construction bidding. We know that we will have to do some of our construction in 2012, and the areas that will require private easements for rights-of-way will be scheduled for that second year of construction. That should allow a sufficient period of time for the easement negotiation process to be successfully concluded. This milestone may not be completed for yet anot | 50 | Baseline plan was 100%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the construction permits and other approvals would be complete by the end of the 4th quarter. All permits have been applied for and Shive-Hattery will secure all needed permits prior to the release of the construction bid documents in April of 2011. This will be completed in the second quarter of 2011. | 0 | As planned | 10 | As planned- the FTTP electronics RFP will be awarded. | 0 | As planned | 0 | Baseline Plan was 10%. At the time this figure was included in the revised project baseline, we thought that we would complete our Environmental Assessment and hire our engineering firm in a shorter period of time than it actually took. We were overly optimistic in predicting that the equipment deployment would be 10% complete by the end of the next quarter. The fIber-to-the-premise electronics contract will be voted on by the University of Illinois Board of Trustees at their March 23rd meeting. If they approve the contract, it is unlikely that any purchase orders will be issued before the end of the quarter. Assuming the contract is approved, in early April we will order FTTP equipment to test with. FTTP equipment for deployment will not be ordered until the 3rd quarter. | 0 | As planned | 2011-02-23 11:04 | 2011-02-23 11:04 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2011 | Q1 | Q1 - 2011 | 2258 | 2874 | FALSE | 16 | The baseline plan was 45%. The percentage we have been listing for overall project percentage is directly tied to our expenditures. In the coming quarter we will pay the bulk of our engineering fees and will purchase all of our network core equipment and the first wave of our FTTP electronics. Construction may actually start by the end of the next quarter, but there will be little if any contractor expenses on our books by June 30th. With our original Baseline Plan and with each PPR we have attempted to predict the future as requested by NTIA. What we have consistently shown is that we are not very accurate at predicting the future. We are boldly going into the woods where no one has ever gone before. There are no models for us to study and learn from to help in predicting our future progress. There has never been a project quite like UC2B with its mix of Middle-Mile and Last-Mile components, and with two local municipalities and a major university as partners behind the wheel. We | 0 |  | N/A | 100 | This is consistent with our baseline plan. | 100 | This is consistent with our baseline plan. | 80 | The baseline plan was 100%. We do not expect to complete the negotiations for private easements until the 4th quarter of 2011. | 100 | This is consistent with our baseline plan. | 0 | The baseline plan was 100%. Until we start construction there will not be any site preparation. When we did the baseline plan, we predicted (inaccurately) that we would begin fiber construction in the second quarter. It now appears that we will not begin in earnest until the 3rd quarter. | 50 | Baseline was 60%. The Baseline Plan inaccurately predicted that we would have purchased more equipment in the next quarter than it now looks like we will purchase. As network electronics are constantly being updated and improved by the vendors, within reason, there is value in purchasing the electronics â€œjust-in-timeâ€ for when they will be needed for deployment. We will only purchase network equipment as we need it. There will be significant expenditures in the third quarter as we begin to populate the FTTP neighborhood cabinets. We will purchase our core electronics in the coming quarter, but the bulk of our FTTP electronics will not be purchased until the 3rd quarter. We should be back on target in this area by the end of the 3rd quarter. | 2 | The baseline plan was 30%. We are at least 3 months behind where we predicted we would be in terms of construction. Some of that is attributable to the time and effort that was expended on the Environmental Assessment. Some of that is attributable to the complexity of out project and that it has taken our engineering firm more time than they estimated to compete our drawings. Some of that is attributable to time spent on reviewing the fiber backbone design at the request of one of our municipalities. Some of that is attributable to our poor ability to accurately predict the future. We will make significant progress in this area in the third quarter. | 50 | The baseline plan was 60%. We are at least 3 months behind where we predicted we would be in terms of equipment deployment. Some of that is attributable to the time and effort that was expended on the Environmental Assessment. Some of that is attributable to the complexity of our project and that it has taken our engineering firm more time than they predicted to compete our drawings. Some of that is attributable to time spent on reviewing the fiber backbone design at the request of one of our municipalities. Some of that is attributable to our poor ability to accurately predict the future. We will deploy our core electronics in the coming quarter, but the bulk of our FTTP electronics will not be deployed until the 3rd quarter. We should be back on target by in this area by the end of the 3rd quarter. | 0 | Baseline plan was 25%.With the delay in constriction, there will be no network to test until the 3rd quarter. | 2011-05-23 17:22 | 2011-05-23 17:22 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2011 | Q2 | Q2 - 2011 | 3256 | 3390 | FALSE | 20 | Baseline Projection was 75%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. The 20% projection is based on the projection of spending 19.94% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Baseline Projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. This milestone category will be caught up be the end of the 4th quarter of 2011. | 50 | Baseline Projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. Equipment procurement has been further delayed by a conscious decision to wait until after August 21st when the FTTP electronics vendor will be releasing upgraded software and hardware. We will buy much of this equipment up-front to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase | 10 | Baseline projection was 69%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. We expect to conform to the projections in our baseline by the 3rd quarter of 2012. The final Network Build will be completed in January of 2013. | 50 | Baseline projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. Equipment deployment has been further delayed by a conscious decision to wait until after August 21st when the FTTP electronics vendor will be releasing upgraded software and hardware. We do not expect to get back on track with our baseline projections until the 1st quarter of 2013, which is the end of our project. | 0 | Baseline projection was 60%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction will begin with a great deal of urgency in the 3rd quarter. We projected Network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be late in the 3rd quarter or early in the 4th quarter of 2012 instead. | 2011-08-22 11:40 | 2011-08-22 11:40 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2011 | Q3 | Q3 - 2011 | 4278 | 3989 | FALSE | 22 | Baseline projection was 78%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begin with a great deal of urgency in the 3rd quarter. The 22% projection is based on the projection of spending 22.2% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 4th quarter of 2011 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 50 | Baseline projection was 80%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction is progressing with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 4th quarter of 2011. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is inst | 10 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begin with a great deal of urgency in the 4th quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final Network Build will be completed in January of 2013. | 50 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. | 0 | Baseline projection was 70%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected Network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2011-11-27 22:32 | 2011-11-27 22:32 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2011 | Q4 | Q4 - 2011 | 5082 | 4753 | FALSE | 40 | Baseline projection was 85%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter. The 40% projection is based on the projection of spending 40% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 1st quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 95 | A couple of our "last-minute" ROW issues may not be totally resolved by March 31st. | 100 | Complete | 100 | Complete | 39 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction progressed with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 1st quarter of 2012. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installe | 36 | Baseline projection was 92%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 4th quarter. We will receive our fiber during this next quarter and will get a small amount installed this coming quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final network build will be completed in January of 2013. | 50 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 5 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-02-16 23:14 | 2012-02-16 23:14 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2012 | Q1 | Q1 - 2012 | 5932 | 5565 | FALSE | 68 | Baseline projection was 85%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter. The 68% projection is based on the projection of spending 68% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 2nd quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 70 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction progressed with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We will buy much of this equipment up-front to bring up the core network in the 1st quarter of 2012. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installe | 71 | Baseline projection was 92%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 4th quarter. We will receive our fiber during this next quarter and will get a small amount installed this coming quarter. We expect to conform to the projections in our baseline by the 4th quarter of 2012. The final network build will be completed in January of 2013. | 60 | Baseline projection was 90%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 50 | Baseline projection was 80%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency in the 4th quarter. However, our contractors will not receive fiber until the first quarter of 2012, and it may well be the 2nd quarter of 2012 before they have anything ready for testing. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-05-06 14:50 | 2012-05-06 14:50 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2012 | Q2 | Q2 - 2012 | 6902 | 6077 | FALSE | 72 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction began with a great deal of urgency in the 3rd quarter of 2011. The 72% projection is based on the projection of spending 72% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 3rd quarter of 2012 and in the remaining quarters. We believe we can complete the project by our 1/31/2013 end date. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Baseline projection was 90%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. Equipment procurement has been further delayed by a conscious decision to wait until after FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. The core network equipment will all have been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of t | 90 | Baseline projection was 96%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We expect to conform to the projections in our baseline by the 1st quarter of 2013. The final network build will be completed in January of 2013. | 80 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. Equipment procurement has been further delayed by a conscious decision to wait until after our FTTP electronics vendor released a significant upgrade to their product. That upgrade has now been released. We do not expect to get back on track with this baseline projection until the 1st quarter of 2013, which is the end of our project. All of the core network and most of the core FTTP equipment will be deployed by the end of next quarter. | 90 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We projected network testing to be complete by the 2nd quarter of 2012. It now seems likely that the actual date will be in the 4th quarter of 2012 instead. | 2012-08-07 15:29 | 2012-08-07 15:29 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2012 | Q3 | Q3 - 2012 | 8060 | 6736 | FALSE | 73 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle-mile construction will be compete by the end of the 4th quarter. Last-mile construction will continue as long as weather permits. The 73% projection is based on the projection of spending 73% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. There will be significant federal spending in the 4th quarter of 2012 as the contractors process their invoices for work completed in the 3rd and 4th quarters. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. The core network equipment has all been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of this customer-specific equipment in January of 2013. | 85 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has begun with a great deal of urgency. We expect to to complete all of our middle-mile construction in the 4th quarter. We are concerned that we will not be able to complete all of our last-mile construction by February 1st. | 70 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle mile construction will be complete by the end of the 4th quarter. All of the core network equipment will be deployed, but the customer premise equipment will be deployed one location at a time as the customers are connected. | 100 | Complete | 2012-11-26 18:07 | 2012-11-26 18:07 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2012 | Q4 | Q4 - 2012 | 8736 | 7534 | FALSE | 70 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle-mile construction will be compete by the end of the 4th quarter. Last-mile construction will continue as long as weather permits. The 70% projection is based on the projection of spending 70% of our total project budget, not just our federal grant. We are currently top heavy with local matching expenditures, so just measuring the federal spend against the federal grant is not a true representation of where we will be. We will get caught up with pay requests in the next quarter as the contractors process their invoices for work completed in the 3rd and 4th quarters of 2013. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Baseline projection was 100%. All milestones that are projected to be behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and construction has progressed with a great deal of urgency. The core network equipment has all been purchased. However, the equipment that resides at a customer's location and the core components that connect directly to the customers' equipment will be purchased on an as-needed basis. There is typically a one or two-year warranty on the customer equipment, which starts when it is purchased, not when it is installed. If we purchase the customer equipment too far ahead of time, we use up too much of the warranty before it is ever deployed. We expect to purchase the last of this customer-specific equipment in September of 2013. | 85 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We expect to to complete all of our middle-mile construction in the 1st quarter of 2013. Last mile Fiber-to-the-Premise (FTTP) construction will continue through September of2013. | 70 | Baseline projection was 100%. All milestones that are projected to behind are due to the unplanned-for length of time required by the Environmental Assessment, and then the delays in completing our fiber engineering and the delays in hiring our fiber construction contractors. We are now past all of those delays and middle mile construction will be complete by the end of the 1st quarter of 2013. All of the core network equipment is deployed, but the customer premise equipment will be deployed one location at a time as the customers are connected through 9/30/13. | 100 | Complete | 2013-02-12 23:56 | 2013-02-12 23:56 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2013 | Q1 | Q1 - 2013 | 9808 | 8439 | FALSE | 80 | This is consistent with our Extension projections. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | We will accquire the remaining equipment we will need to deliver services. There may be a few cables and smaller items that we pick up in the following quarter as needed. | 92 | We will add some ROW fiber and some FTTP fiber drops in June, but the bulk of the remaining work to be done will happen in the 3rd quarter. | 90 | We will continue to deploy equipment as customers are built to there will still be customers to connect in the 3rd quarter of 2013. | 95 | We will continue to test the network as it is expanded to provide service to the 61 additional Anchor Institutions. | 2013-05-19 18:15 | 2013-05-19 18:15 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2013 | Q2 | Q2 - 2013 | 10722 | 9024 | FALSE | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 0 | N/A | N/A | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 100 | We plan to complete our project by September 30th, which is both the end of the third Quarter and the end of our grant period. | 2013-08-23 18:02 | 2013-08-23 18:02 | 5400 | 5400 | University of Illinois
NT10BIX5570044 | 2013 | Q3 | Q3 - 2013 | 12078 | 10240 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-04-25 15:18 | 2014-04-25 15:18 | 5400 | 5400 | University of Illinois
NT10BIX5570045 | 2010 | Q3 | Q3 - 2010 | 464 | 1498 | FALSE | 20 | Expect to acquire materials for 3 of 6 service areas which comprise 40% of total project. Anticipate FONSI approximately 11/17 leaving 15-30 days (maximum) of fiber construction before winter sets. | 0 | N/A | N/A | 100 | N/A | 100 | Finalizing slack and splice locations in engineering plans for 3 service areas | 25 | N/A | 15 | Didn't receive FONSI such that we are not permitted to take out permits yet | 100 | N/A | 0 | Expecting FONSI in 4Q2010 such that final ordering, receipt and installation will be delayed to 1Q2011 | 0 | N/A | 0 | N/A | 0 | N/A | 2010-12-01 11:50 | 2010-12-01 11:50 | 5201 | 5201 | University of Wisconsin System
NT10BIX5570045 | 2010 | Q4 | Q4 - 2010 | 1262 | 2289 | FALSE | 20 | Expect to acquire materials for 3 of 6 service areas which comprise 40% of total project. FONSI received on 12/23/10 therefore, no fiber construction during 4Q2010. | 0 |  | N/A | 100 | N/A | 100 | N/A | 25 | N/A | 15 | Since we received the FONSI on 12/23/10, there were no permits initiated | 100 | N/A | 10 | FONSI received on 12/23/10. As such, the final ordering, receipt and installation will be delayed to 2Q2011. We have completed an initial design for the first of 2 fiber rings on the East side of Madison. However, we do not have the procurement details worked out yet nor do we have a final design and are not ready to order just yet. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-21 17:12 | 2011-02-21 17:12 | 5201 | 5201 | University of Wisconsin System
NT10BIX5570045 | 2011 | Q1 | Q1 - 2011 | 2024 | 2757 | FALSE | 6 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 4Q2011. | 0 |  | N/A | 95 | Monona Drive service area (Phase 3) will not begin until 2Q2012. Expect to catch in 2Q2012. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 50 | Delaying Monona Drive service area until summer 2012 due to significant road construction. | 38 | Phase 1 permits expected 5/4/11. We plan to submit Phase 2 permits in May 2011 and go before the City of Madison Board of Public Works on 6/8/11. We are also meeting with WisDOT (Wisconsin Department of Transportation) in May 2011 to finalize a permit request. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 2Q2011. | 0 | FONSI timing and engineering resources were used to complete network design. We expect to catch up 3Q2011. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. We expect to complete 40% of this in 4Q2011 and catch up in 4Q2012. Significant delay is due to construction delays in Monona Drive service area due to road construction schedule changes. | 14 | Received Environmental Assessment late 4Q2010 | 0 | FONSI timing. Also, are conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | FONSI timing and weather. We expect to be substantially caught up in 4Q2011. | 2011-05-13 16:08 | 2011-05-13 16:08 | 5201 | 5201 | University of Wisconsin System
NT10BIX5570045 | 2011 | Q2 | Q2 - 2011 | 2968 | 3241 | FALSE | 49 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. We expect to catch up in 4Q2011. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in Spring 2012. | 100 | Our baseline assumed network engineering design could be completed in phases. However, the EA required us to complete all engineering before proceeding with construction. | 69 | Expect to finalize right-of-way with City of Middleton and Dane County | 46 | Anticipate to receive permits in City of Middleton, Town of Madison, Town of Middleton, Dane County and from the WI Dept of Transportation in 3Q2011. | 100 | Expect to complete site prep activities at 525 Science Dr, Madison, WI | 0 | Expect to procure equipment in 4Q2011 once consortium network designs are finalized | 46 | We expect to be one quarter behind our baseline at the end of 3Q2011. This is due to late start due to FONSI and weather. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 0 | FONSI timing. Also, we were conducting CAI needs assessments before procuring hardware which we did not include in our baseline. | 2011-08-09 11:44 | 2011-08-09 11:44 | 5201 | 5201 | University of Wisconsin System
NT10BIX5570045 | 2011 | Q3 | Q3 - 2011 | 4018 | 3849 | FALSE | 54 | MUFN is catching up from 1yr loss due to EA delays. Our 4Q2011 progress will meet our 2Q2011 progress plan. Due to weather, we won't be able to fully catch up with our baseline until 4Q2012. We expect to expend 67% of funds by the end of 2Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 100 | Expect to have optical design work completed by end of 4Q2011. | 75 | Have right-of-ways for all but Monona Drive service area (remaining 25% difference from our baseline with completion (100%) by end of 1Q2012. | 69 | Did not know about EA so plan is 1yr behind. Expect to meet baseline in 2Q2012 | 0 | Filed and (expect to) receive SF-1444 conformance in 4Q2011 and meet 100% baseline in 1Q2012 | 0 | We are redesigning optical transport system due to unexpected CAI demands for redundancy. Will begin procuring hardware in late 4Q2011 after optical network (re)design is complete which we did not include in our baseline as we believed this was already completed. We expect to purchase hardware in 1Q2012 (expend funds). Will be on track with baseline in 1Q2012. | 57 | At the end of 4Q2011, we will be exceeding our baseline at 2Q2011 (46%) but will not be able to catch up to our 4Q2011 projection until 4Q2012 due to weather and road construction delays causing some builds to be delayed to late summer 2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Redesigning optical system now with anticipated 1Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012). | 71 | Lagging 3Q2011 baseline due to dropped sites and road construction delays which we can't resolve until 4Q2012. | 2011-11-14 11:56 | 2011-11-14 11:56 | 5201 | 5201 | University of Wisconsin System
NT10BIX5570045 | 2011 | Q4 | Q4 - 2011 | 5392 | 5071 | FALSE | 64 | MUFN is catching up from 1yr loss due to EA delays. Our 1Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. Due to weather, we won't be able to fully catch up with our baseline until 4Q2012. We expect to expend 67% of funds by the end of 2Q2012. | 0 |  | N/A | 95 | FONSI was received in 4Q2010. We were not aware that an EA was required. We have used funds from SF-424C's architectural and engineering fees to cover the cost of the EA. We expect to expend approximately $1,500 to cover the cost of an on-site archeologist as required during the Monona Drive Service area in 3Q2012. | 100 | EA required us to complete all engineering ahead of time such that we had 100% completed - including optical engineering. However, after network design mtgs with CAIs, we determined MUFN must redesign the optical transport as ALL entities want redundancy. This began in 3Q2011 and will complete by end of 1Q2012. | 100 | N/A | 79 | We are just past 1Q2010 baseline plan but will not catch up with our baseline of 100% completed until 2Q2012 due to road construction changes in University Ave, Monona Dr, Mineral Point and East Washington service areas (can not obtain permits in construction areas until work is nearly complete) | 0 | Expect work to commence in 1Q2012 but not to receive invoice from contractor until 2Q2012. | 0 | Expect to complete optical hardware procurement by 2Q2012. | 77 | Will catch up at 4Q2012. Expect to hit 3Q2011 baseline projection. | 0 | Expect to deploy optical hardware in 2Q2012. | 77 | Will catch up at 4Q2012. Expect to surpass 3Q2011 baseline projection. | 2012-02-29 12:24 | 2012-02-29 12:24 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2012 | Q1 | Q1 - 2012 | 5984 | 5591 | FALSE | 66 | MUFN is catching up from 1yr loss due to EA delays. Our 2Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. We won't be able to fully catch up with our baseline until 4Q2012. | 0 |  | N/A | 97 | We expect to complete 2 route change submission EA work by the end of 2Q2012 with exception of hiring archaeologist to monitor 1 lateral located in phase 3 (Monona Dr service area) | 100 | N/A | 100 | Expect to have all right-of-way though MG&E route change right-of-way will be tight to end of 2nd quarter. | 100 | Expect to have all construction permits. | 0 | Received Davis-Bacon Wage conformance for site preparation at 525 Science Dr on 12/20/12. Expect contractor to begin in 2Q2012 but not finish/invoice for work until 3Q2012. We will meet our baseline in 3Q2012. | 0 | Expect to begin procurement in 2nd quarter but not complete it or place order until 3Q2012 - assuming NTIA programmatic/grants office approval is received. | 77 | We met our planned 3Q2011 baseline but are behind our 1Q2012 due to delayed EA and unanticipated road construction plan changes. Will catch up to at 4Q2012. | 0 | We expected to immediately deploy "North ring" but delayed due to network assessment meetings with CAIs and resulting surprise in demand. Anticipate 3Q2012 deployment to catch up to baseline. Will not catch up to final 100% baseline until 4Q2012 as Monona Drive service area was delayed by 1yr due to road construction (orig. deployment was 1Q2012); can't deploy equipment on fiber until fiber is installed. | 80 | Tested completed laterals in 1Q2011 though due to EA, road construction delays, we will not catch up to baseline until 4Q2012 due to road construction delays delaying fiber installation in Monona Dr service area and 3 in E. Washington Ave and University Ave Service Areas. | 2012-05-09 12:52 | 2012-05-09 12:52 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2012 | Q2 | Q2 - 2012 | 6994 | 6124 | FALSE | 67 | MUFN is catching up from 1yr loss due to EA delays. Our 2Q2012 progress will be between our 2Q2011 and 3Q2011 progress plan. We won't be able to fully catch up with our baseline until 4Q2012. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Anticipate phase 2 (Watts Rd) and phase 3 (Monona Dr) route change approval | 100 | Anticipate approvals from NTIA and expedient permitting. | 100 | Expect 525 Science Dr to be completed. | 100 | Expect optical procurement to be completed | 85 | Anticipate continued construction on road-construction delayed areas as well as finalizing UWHC fiber lease. | 0 | Expect to perform this work in 4Q2012 assuming NTIA approval of rebudget request. | 92 | Will catch up to baseline in 4Q2012 | 2012-08-09 18:32 | 2012-08-09 18:32 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2012 | Q3 | Q3 - 2012 | 7832 | 6619 | FALSE | 99 | Expect to have all fiber and network equipment installation completed by end of 4Q2012. Some invoicing and project closeout work will occur in January 2013. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | Anticipate phase 2 (Watts Rd) and phase 3 (Monona Dr) route change approval | 100 | Anticipate approvals from NTIA | 100 | Expect completion in early November | 100 | Will be done with procurements for optical hardware and DC power systems in early 4Q2012 | 100 | Expect to finalize UWHC fiber lease once consortium agreement is completed and complete all fiber construction | 100 | Expect all DC power and optical equipment installed in 4Q2012 | 100 | Expect to complete in 4Q2012 | 2012-11-13 08:15 | 2012-11-13 08:15 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2012 | Q4 | Q4 - 2012 | 8770 | 7564 | FALSE | 100 | Anticipate completion by 1/31/13 though MUFN has requested an extension from NTIA due to potential delays from Wisconsin winter weather. | 0 |  | N/A | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Anticipate completion by 1/31/13 | 100 | Expect completion by 1/16/13 | 100 | Anticipate completion by 1/31/13 | 2013-02-14 09:10 | 2013-02-14 09:10 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2013 | Q1 | Q1 - 2013 | 9712 | 8389 | FALSE | 100 | Anticipate completion by 6/7/13. | 0 |  | N/A | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Completed in 4Q2012 | 100 | Anticipate completion by 6/7/13 | 100 | Completed in 1Q2013 | 100 | Anticipate completion by 6/7/13 | 2013-05-14 09:02 | 2013-05-14 09:02 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570045 | 2013 | Q2 | Q2 - 2013 | 10844 | 9097 | FALSE | 100 | Grant completed | 0 |  | N/A | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 100 | Grant completed | 2013-09-12 15:23 | 2013-09-12 15:23 | 5183 | 5183 | University of Wisconsin System
NT10BIX5570046 | 2010 | Q3 | Q3 - 2010 | 438 | 1485 | FALSE | 3 | The engineering and combined environment assessment is now under the direction of the State Facility Planning and Control (FP&C). The Board of Regents/LONI is the user agency providing specifications, requirements and needs to FP&C. | 0 |  | N/A | 75 | The contracted firm will be in position to submit the draft EA by 1/31/10. | 8 | Consult with Cisco Systems and other potential vendors on the best technology to deliver the anticipated transport services. | 10 | The contracted firm will have finalized the fiber route in order to process the final right-of-way permits with DOTD and railroads, US FWS, SHPO and US Army Corp of Engineers. | 0 | N/A | 0 | N/A | 2 | It is our intention to follow state procurement statutes, guidelines and guidance and issue a public competitive RFP for equipment purchases above $250,000. For equipment purchases below $250,000 we will utilize existing state contracts and/or other short-term bid response vehicles. | 0 | N/A | 0 | N/A | 1 | Working with our testing vendor, EXFO, in developing a hardware, software and testing methodoloy. | 2010-11-29 14:08 | 2010-11-29 14:08 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570046 | 2010 | Q4 | Q4 - 2010 | 1376 | 2388 | FALSE | 8 | With the EA submitted 1/31 and FONSI received, GEC will be in full strength to finish the design for the end of March 2011. | 0 | N/A | N/A | 90 | Work on the research and data collection for the Existing Environment section of the EA willcontinue. Several sub-sections, including, geology and soils, air quality, water quality, biological resources,land use, aesthetics, cultural resources, infrastructure, noise, socioeconomics, and human health& safety will be finalized. Office coordination with the LA SHPO will continue. Coordination with the U.S. Fish and Wildlife and the U.S. Army Corps of Engineers (New Orleans and Vicksburg Districts) will continue. Draft EA will be submitted on January 31, 2011. | 65 | Communications field crews will survey each project segment (both rural and urban areas) for the purpose of finalizing the OSP route and will identify the placement of conduit (HDD, trench,structure), handholes, and interconnect points. In addition, required permits for construction will be solidified. Field inspection data will be delivered to design personnel for review and incorporation into routemaps. Specification preparation and design details will commence. | 65 | Required permits will be identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | 0 variance | 0 | Construction anticipated to start within the 3rd quarter of 2011. | 0 | 0 variance | 50 | We intent to purchase some of the hardware and software needed to facilitate this phase. | 2011-02-25 14:22 | 2011-02-25 14:22 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570046 | 2011 | Q1 | Q1 - 2011 | 2314 | 2902 | FALSE | 13 | GEC will have submitted the final Environmental Assessment. In addition, GEC will have completed five of their five contracted submittals to advertise for the fiber and interconnect point construction. | 0 | N/A | N/A | 100 | STATEMENT PROVIDED BY GEC. Coordination, for the EA effort, with the U.S. Army Corps of Engineers - Vicksburg District, the Louisiana State Historic Preservation Office (LASHPO), and the United States Forest Service (USFS) will be completed. Final draft EA will be submitted. Coordination, for construction and permitting, with the U.S. Fish and Wildlife Service (USFWS), the U.S. Army Corps of Engineers - New Orleans and Vicksburg Districts, the Louisiana State Historic Preservation Office (LASHPO), the Louisiana Department of Natural Resources (LDNR), and the United States Forest Service (USFS) will continue. | 85 | STATEMENT PROVIDED BY GEC. Communications field crews will complete the survey of each project segment (both rural and urban areas) for the purpose of finalizing the OSP route and identifying the placement of conduit (HDD, trench, structure), handholes, and interconnect points. Identification of permits for construction will be completed. Field inspection / survey data will be delivered to design personnel for review and for Coordination for placement of interconnect points (new standalone building or within existing building) and development of installation details will be completed. Specifics will be incorporated into construction documents. Route maps will be finalized and incorporated into construction documents. Coordination for placement of interconnect points (new standalone pre-fab buildings or with existing buildings) and development of installation details will be completed. Specifics will be incorporated into construction documents. Construction documents suitable for bi | 75 | STATEMENT PROVIDED BY GEC. Required permits will continue to be identified as part of the EA document preparation as well as field inspections. ROW issues, if any, are and will continue to be discovered during the final inspections of the OSP route and interconnect point locations. Permits identified include the United States Army Corps of Engineers - New Orleans and Vicksburg Districts, Louisiana State Historic Preservation Office (LASHPO), Louisiana Department of Natural Resources (LDNR), United States Forest Service (USFS), United States Fish and Wildlife Service (USFWS), Louisiana Department of Transportation and Development (LADOTD), railroads, pipelines, levee districts, and cities / municipalities. Assembly of forms, permit preparation, and coordination with permitting entities will continue. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 1 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | STATEMENT PROVIDED BY GEC. Construction anticipated to begin 3rd quarter of 2011. | 0 | 0 variance | 0 | 0 variance | 2011-05-25 17:02 | 2011-05-25 17:02 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570046 | 2011 | Q2 | Q2 - 2011 | 3156 | 3338 | FALSE | 7 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | N/A | N/A | 100 | STATEMENTS PROVIDED BY GEC: Finding of No Significant Impact (FONSI) was issued by NTIA on June 3, 2011. Preparation of a supplemental EA will be required once the project is complete. This supplemental EA will address route changes subsequent to submission of the draft and final EA documents as well as any route changes that may be required during construction. Documentation for the supplemental EA will be gathered as the project moves forward. | 55 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 35 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 1 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 0 | STATEMENTS PROVIDED BY THE STATE: The State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. | 2011-08-17 14:37 | 2011-08-17 14:37 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570046 | 2011 | Q3 | Q3 - 2011 | 4142 | 3917 | FALSE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2011-11-18 15:00 | 2011-11-18 15:00 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570046 | 2011 | Q4 | Q4 - 2011 | 5192 | 4859 | FALSE | 7 | 0 variance | 0 | N/A | N/A | 100 | 0 variance | 55 | 0 variance | 35 | 0 variance | 0 | 0 variance | 0 | 0 variance | 1 | 0 variance | 0 | 0 variance | 0 | 0 variance | 0 | 0 variance | 2012-02-22 14:58 | 2012-02-22 14:58 | 5537 | 5537 | Louisiana Board of Regents
NT10BIX5570047 | 2010 | Q3 | Q3 - 2010 | 366 | 1449 | FALSE | 5 | Delay in completion of the Environmental Assessment (EA) and subsequent receipt of Finding of No Significant Impact (FONSI) has extended the current overall project timeline into future quarters. Construction is planned to begin in Q4. In addition, permitting issues have hindered progress of some select routes. | 0 | N/A | N/A | 100 | N/A | 40 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 25 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 20 | See narrative in 2a above describing overall project delay from initial projections. | 1 | See narrative in 2a above describing overall project delay from initial projections. | 10 | N/A | 0 | See narrative in 2a above describing overall project delay from initial projections. | 2010-11-19 17:22 | 2010-11-19 17:22 | 5529 | 5529 | Northwest Open Access Network
NT10BIX5570047 | 2010 | Q4 | Q4 - 2010 | 754 | 1787 | FALSE | 10 | Delay in completing the Environmental Assessment and subsequent receipt of finding of No Significant Impact (FONSI) has extended the current overall project timeline into future quarters. Construction is now targeted to begin in the first quarter of 2011. Some permitting issues have hindered progress on select routes but are anticipated to be resolved this quarter as well. Weather has impacted some select routes for preparation, but again hopeful to resolve this quarter. | 0 | N/A | N/A | 100 | N/A | 70 | N/A | 50 | See 2a. above. | 40 | See 2a. above. | 30 | See 2a. above. | 40 | See 2a. above. | 5 | See 2a. above. | 15 | See 2a. above. | 5 | See 2a. above. | 2011-01-28 13:55 | 2011-01-28 13:55 | 5529 | 5529 | Northwest Open Access Network
NT10BIX5570047 | 2011 | Q1 | Q1 - 2011 | 2264 | 2877 | FALSE | 11 | Expenditures are lagging planned milestones, as construction activities were originally forecasted well ahead of current levels. Additional resources are being deployed to meet the three year plan as outlined by the Broadband Technology Opportunities Program guidelines. | 0 | N/A | N/A | 100 | No variance. | 85 | No variance. | 70 | Right of Way acquisition, although progressing against the current milestone gap, should be completed by year end. | 60 | Acquisition of permits continues by acquiring all necessary Federal,State and Local permits. This metric to be completed by the end of calendar year 2011. | 50 | Additional resources have been allocated to this task and its anticipated there will be no gap in this milestone by year end. | 25 | A significant amount of equipment is in the form of In Kind contribution dependant upon acceptance into the project by the Grants Officer. Once approved and 'booked' to the project, this gap will narrow and be brought closer to initial projections. Projection is to meet our Baseline by the end of Quarter 1, 2012. | 10 | Network build will accelerate as weather will hopefully allow us to move forward and all necessary contracts and pre-construction activities have been completed. This metric will be accelerated throughout the year to insure gaps in Baseline are eliminated by end of the year. | 15 | Equipment will be deployed as allowed per the network build progress and procurement process. It is projected to meet our Baseline metric by Quarter 1; 2012. | 10 | Network testing will commence with portions of the network build being completed and brought on line. This metric will be brought up to Baseline projections by the end of Quarter 1, 2012. | 2011-05-24 09:07 | 2011-05-24 09:07 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2011 | Q2 | Q2 - 2011 | 3092 | 3303 | FALSE | 33 | Expenditures are lagging Baseline projections as construction activities were originally forecasted much earlier in the project time line. In Kind assets were included in this calculation and their approval date is not yet known. | 0 | N/A | N/A | 100 | No variance. | 95 | No variance. | 90 | Right of Way acquisition is progressing against the current milestone and should be completed by year end. Minimal acquisition will remain going into the final year of the project. | 80 | Permitting at all levels continues with a completion date of December 31, 2011 anticipated. | 65 | No variance. | 77 | A significant amount of Equipment for this project is in the form of In Kind assets currently under review for acceptance by the Program Office. Once approved we will meet the baseline by the end of this quarter. | 15 | Network build, although currently lagging the milestone compared to the Baseline, this metric will be met by the end of the project. Additional resources as required will added to insure compliance with the guidelines. | 70 | This metric will be exceeded as a result of adding the In Kind assets in this quarter. | 15 | Network testing is anticipated to continue as the Network Build is taking place. | 2011-08-15 16:57 | 2011-08-15 16:57 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2011 | Q3 | Q3 - 2011 | 4218 | 3957 | FALSE | 48 | Expenditures are lagging baseline projections as an aggressive original forecast had construction beginning in year one of the project. This metric will lag into year three of the project life cycle. All available resources along with an expedited construction schedule will allow for an on time completion. | 0 |  | N/A | 100 | 0-98-No Variance. | 100 | No Variance. | 90 | Rights of Way acquisition and permitting near completion as we approach the final year of the project life cycle. Any remaining rights of way and construction permits will be acquired in quarter one of 2012. | 85 | Rights of Way acquisition and permitting near completion as we approach the final year of the project life cycle. Any remaining rights of way and construction permits will be acquired in quarter one of 2012. | 70 | Currently lagging Baseline projections as we enter in the final year of the project. Some additional site preparation is scheduled for projects slated for construction next year. This metric will be met in quarter two of 2012 as routes are being completed. | 85 | No Variance. | 30 | The Network Build metric, although lagging significantly compared to original Baseline projections, will be met as required by the Broadband Technology Opportunities Program guidelines. Additional resources will be deployed to meet the projections during the final year of the project. Northwest Open Access is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. | 45 | Equipment is being deployed as fiber routes are completed. Delayed fiber delivery forces equipment deployment to follow final fiber splicing projected in quarter three of 2012. | 20 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of year three of the project. This metric will again mirror the Network Build schedule. | 2011-11-22 14:19 | 2011-11-22 14:19 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2011 | Q4 | Q4 - 2011 | 5388 | 5064 | FALSE | 64 | Expenditures are lagging baseline projections as an aggressive original forecast had construction beginning in year one of the project. This metric will lag into year three of the project life cycle. All available resources along with an expedited construction schedule will allow for an on time completion. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 95 | Based on the necessity to make changes or to rescope segments of the project scheduled for construction in 2012, pending right of way acquisition may be necessary in the final stages of the project. | 95 | See 'Rights of Way' narrative above. | 75 | Currently lagging Baseline projections as we enter the final year o the project. Some additional site preparation will linger into 2012 as final route preparation is performed prior to construction. | 95 | No Variance. | 50 | Northwest Open Access Network has found it necessary to initiate several route changes or rescopes of segments within the project for a variety of reasons. Pending review and approval has taken additional time and added delays to an already compressed schedule. The Network Build metric, although lagging significantly compared to original Baseline projections, will be met as required by the Broadband Technology Opportunities Program guidelines. Additional resources will be deployed to meet the projections during the final year of the project. Northwest Open Access is taking an aggressive approach to installing conduit so that when the February arrival of fiber is received, it can be expeditiously installed. | 70 | Equipment is being deployed as fiber routes are completed. Delays in Fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter three of 2012. | 30 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of year three of the project. This metric will mirror the Network Build schedule. | 2012-02-29 11:00 | 2012-02-29 11:00 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2012 | Q1 | Q1 - 2012 | 6186 | 5695 | FALSE | 65 | Although lagging for the entire project, this metric continues to keep stride with the current gap. Significant progress is occurring in the construction phase as we surpass our second year of the project. Current projections are to attain the baseline projection for this category in quarter four of 2012. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 98 | The majority of permitting will be completed with minimal approvals remaining for projects that required modifications to the originally designed routes. This metric will attain baseline projections in Q3 2012. | 90 | We are currently lagging Baseline projections as we enter the final year of the project. Some additional site preparation will linger into the second half of 2012 as final route preparation is performed prior to construction. This metric will achieve baseline in Q3 2012. | 95 | Equipment procurement will lag into the final stages of the project with minimal purchasing yet to be completed. We are anticipating finalizing purchases in Q3 2012. | 76 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by Q4 2012. | 80 | Equipment is being deployed as fiber routes are completed. Delays in fiber shipment has forced equipment deployment to follow final fiber splicing projected in quarter four of 2012. | 40 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of 2012 and follow the same metric as Network Build. | 2012-05-18 12:29 | 2012-05-18 12:29 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2012 | Q2 | Q2 - 2012 | 6828 | 6040 | FALSE | 74 | Although lagging for the entire project, this metric continues to keep stride with the current gap. Significant progress is occurring in the construction phase as we surpass our second year of the project. Current projections are to attain the baseline projection for this category in quarter four of 2012. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 96 | Equipment procurement is anticipated to be completed as we approach the end of Q3 2012. Some minimal purchases are expected to be finalized in this quarter. | 86 | The Network Build will continue to lag as construction was scheduled to start much earlier in the project time line. All available resources will continue to be utilized to bring this metric to baseline projections by Q4 2012. | 85 | Equipment deployment will slightly lag procurement with final placement occurring in Q4 2012. | 70 | Network testing will be performed as the build progresses and services are turned up. Current projections indicate this metric will lag until quarter three of 2012 and follow the same metric as Network Build. | 2012-08-01 15:00 | 2012-08-01 15:00 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2012 | Q3 | Q3 - 2012 | 7936 | 6672 | FALSE | 84 | Although lagging for the entire project and nearing completion of the project in this quarter, remaining expenses and invoices will continue into the following month. This metric will not show 100 percent completion as a result of these expenditures. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 97 | A few final clean up and completion of minor lengths of segments will occur during the final month of the project leaving this metric short until the final report is completed. | 95 | Minimal equipment will be deployed as final testing and routes are completed in January. | 90 | Testing will be done in the final month of the project schedule allowing for all remaining segments to be tested. | 2012-11-16 17:01 | 2012-11-16 17:01 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2012 | Q4 | Q4 - 2012 | 8794 | 7591 | FALSE | 92 | This metric will not be reached as we will not be expending 100% of the Budgeted amount. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-02-14 23:12 | 2013-02-14 23:12 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2013 | Q1 | Q1 - 2013 | 9908 | 8495 | FALSE | 98 | Minimal activities remain pertaining primarily to closeout activities. Final invoices for activity still remain to be approved and will continue into the third quarter. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-05-24 17:06 | 2013-05-24 17:06 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2013 | Q2 | Q2 - 2013 | 10690 | 9006 | FALSE | 96 | Final expenditures and invoices are still pending approvals and reimbursement for the project. Originally forecasted to be completed by last quarter, final invoices will be received and paid in Quarter 3 with the exception of closeout costs and any late or disputed invoices for the project. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-21 17:22 | 2013-08-21 17:22 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570047 | 2013 | Q3 | Q3 - 2013 | 12184 | 10367 | FALSE | 100 | Project is complete. | 0 | N/A | N/A | 100 | Project is complete | 100 | Project is complete | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 2014-05-12 17:42 | 2014-05-12 17:42 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570049 | 2010 | Q3 | Q3 - 2010 | 148 | 1340 | FALSE | 15 | No change - project expected to catch up to baseline estimate | 0 | N/A | N/A | 100 | No change | 60 | No change | 75 | No change | 85 | No change | 0 | N/A | 0 | No change | 0 | No change | 0 | No change | 0 | No change | 2010-10-13 10:53 | 2010-10-13 10:53 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2010 | Q4 | Q4 - 2010 | 818 | 1852 | FALSE | 25 | No change | 0 |  | N/A | 100 | No change | 85 | No change | 100 | No change | 60 | Anticipate all applications for permits submitted, but VDOT review (up to 45 days) may delay completion percentage initially estimated. | 0 | N/A | 25 | No change | 0 | No change | 0 | No change | 0 | No change | 2011-01-28 15:58 | 2011-01-28 15:58 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2011 | Q1 | Q1 - 2011 | 1908 | 2699 | FALSE | 40 | Slight variance due to delay in starting make ready work and VDOT permitting. | 0 |  | No variance | 100 | No variance | 95 | Anticipate the potential for minor changes to final design based on network operator selection or changes requested by the department of transportation. | 100 | No variance | 90 | Anticipate all approvals for fiber construction to be secured; tower permitting will not be completed but will be in progress. | 0 | No variance | 40 | Materials for construction will have been ordered but anticipate longer than normal delivery times. Towers will not have been ordered and expect they will not until 2012. | 0 | The construction contractor is expected to have been selected, but due to delays in finalizing VDOT permitting and make ready the construction is expected to start near the beginning of the 3rd quarter. | 0 | No variance | 0 | No variance | 2011-05-06 14:58 | 2011-05-06 14:58 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2011 | Q2 | Q2 - 2011 | 3246 | 3385 | FALSE | 40 | Construction expected to be underway on middle mile fiber, but delayed start. Towers will not be constructed but will be in development for bidding. | 0 |  | N/A | 100 | May have to reconsult if changes to construction method but do not anticipate any problems with receiving approval. | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 50 | All outside plant materials will have been ordered but not anchor or network operating equipment. | 15 | Construction expected to have just begun on fiber network but not on towers. | 0 | Equipment for anchor institutions and network operations will be ordered but not deployed since construction just beginning. | 0 | No variance | 2011-08-19 18:19 | 2011-08-19 18:19 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2011 | Q3 | Q3 - 2011 | 4172 | 3934 | FALSE | 37 | Variance due to delayed construction start. By the end of Qtr 4 approximately 4 miles of fiber is anticipated to have been deployed. The project has been broken into five segments and the contractor will be in process of construction on two segments. VDOT requirements for stop work during holiday periods include the day before, the holiday, and the day following; the Thanksgiving and Christmas holidays will limit construction progress in Qtr 4. Payments for work completed on this project will always lag grant expenditures by approximately one month due to required Board of Supervisor approval prior to issuing payment to contractors and vendors. | 0 |  | N/A | 100 | No variance; expect to have received EA amendment approval. | 100 | No variance | 100 | No variance, VDOT permitting complete | 100 | No variance, expect to receive final water permits and environmental sign off by end of October. | 0 | N/A | 44 | Variance anticipated due to delay in selecting network operator and wholesale providers, and delay in fiber construction. 44% of equipment budget is anticipated to be expended for construction materials by the end of Qtr 4, with an additional $33,000 of materials received but payment not expended until January. Expect specifications and bid documents to be in process in Qtr 4 for bid release and purchase of equipment 1st Qtr of 2012. | 0 | Variance due to delay in construction start. Construction is scheduled to be in progress in November, but expenditures not made until January based on the County's payment process contractual agreement with contractor. | 0 | Variance due to delay in selecting network operator and wholesale providers. Expect to begin deploying equipment approximately 2nd Qtr 2012 when fiber network is completing. | 0 | Variance expected, network testing will not commence until completion approximately 2nd Qtr 2012. | 2011-11-21 09:56 | 2011-11-21 09:56 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2011 | Q4 | Q4 - 2011 | 4412 | 4071 | FALSE | 76 | Construction start delayed approximately 6 months, but contractor working additional crews to complete fiber construction in Qtr 2 2012. | 0 | N/A | N/A | 100 | No variance, but we expect to submit a request for an environmental assessment addendum to deploy additional fiber underground to a revised tower location. | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 78 | Variance due to delayed construction start as well as the delay in fund expenditure. It is anticipated that all outside plant materials will have been purchased by the end of next quarter as well as some of the key network electronics. | 54 | Delayed construction start by approximately 6 months. Expect the majority of the fiber network to be constructed but towers will not be under construction and equipment will not have been deployed. | 0 | Delayed construction start. Network operating and end user equipment will not be deployed until fiber construction complete, anticipated in Qtr 2 of 2012. | 25 | Expect to begin some testing of network circuits | 2012-01-24 13:55 | 2012-01-24 13:55 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2012 | Q1 | Q1 - 2012 | 6130 | 5667 | FALSE | 66 | Expect fiber construction to be 85% complete with testing and equipment deployment in progress. Tower construction firm will have been chosen for Avon and Afton towers with pre-construction tasks prior to tower erection in progress. | 0 |  | N/A | 100 | No variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 90 | Expect the majority of electronics to have been ordered with installation in progress. Miscellaneous server equipment and last minute orders will be pending. | 65 | Construction of the fiber network will be 85% complete with an additional 13 miles constructed by the end of the quarter. Two towers will be nearing construction and planning for construction of the third tower will be underway. | 65 | Expect to have begun deployment of equipment cabinets and interconnection facilities as fiber circuits are complete. | 65 | Testing will begin following construction and turn up of all interconnection points and network operating center equipment. Private provider collocated at network operating center will be testing connection. | 2012-05-16 11:43 | 2012-05-16 11:43 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2012 | Q2 | Q2 - 2012 | 7042 | 6148 | FALSE | 85 | Expect fiber construction to be nearly complete with testing and equipment deployment in progress. Two towers will be under construction. Payments lag completion in accordance with contracts requiring hold back and compliance testing prior to final payments. | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 75 | Expected to have ordered the majority of equipment but payments to lag into the following quarter in accordance with contract and compliance testing. | 80 | Construction of the fiber network will be nearly complete and testing in process. Two towers will be under construction and planning for construction of the third tower will be underway. | 65 | Expect to have begun deployment of equipment cabinets and interconnection facilities as fiber circuits are complete. | 65 | Testing will begin following construction and turn up of all interconnection points and network operating center equipment. Private providers collocated at network operating center will be testing connections. | 2012-08-13 09:13 | 2012-08-13 09:13 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2012 | Q3 | Q3 - 2012 | 7788 | 6595 | FALSE | 96 | Variance due to network construction delayed by approximately six months and difficulty in securing a third tower site in the Massies Mill area. All of the fiber network and operating equipment will have been installed and community anchor institutions receiving services over the new middle mile fiber network. Only the Massies Mill tower construction will remain to be completed in this project by the end of the following quarter, and work well in progress for local approvals and construction procurement. | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 96 | Variance due to network construction delayed by approximately six months and difficulty in securing a third tower site in the Massies Mill area. Construction of the fiber network will be complete and all equipment deployed in the operating center and in the community anchor institutions. Two towers will have been fully constructed and the third in process of securing local approvals and construction procurement. | 100 | No variance | 100 | No variance | 2012-11-07 16:02 | 2012-11-07 16:02 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2012 | Q4 | Q4 - 2012 | 8890 | 7678 | FALSE | 99 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber is complete, turn up and testing will have been completed but deployment of the final tower will be in progress. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 99 | Variance due to delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber is complete, turn up and testing will have been completed but deployment of the final tower will be in progress. | 99 | Variance due to delayed construction start and difficulties in securing an optimum tower location in Massie's Mill. The microwave backhaul equipment will have been received with installation on scheduled following erection of the tower. | 99 | Variance due to a delayed construction start, difficulties in securing an optimum tower location in Massie's Mill, and significant weather events that impacted resources and ground conditions. The backbone fiber construction and community anchor connections are complete, and splicing and close out testing of the fiber network will be completed in this quarter. Testing of the microwave equipment and the microwave to fiber interconnection will follow tower erection and microwave equipment installation. | 2013-02-21 16:51 | 2013-02-21 16:51 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2013 | Q1 | Q1 - 2013 | 9714 | 8391 | FALSE | 100 | No variance | 0 | 0 | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-05-14 13:37 | 2013-05-14 13:37 | 5488 | 5488 | Nelson, County of
NT10BIX5570049 | 2013 | Q2 | Q2 - 2013 | 11986 | 10147 | FALSE | 100 | Project complete. | 0 | N/A | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 2014-03-25 11:12 | 2014-03-25 11:12 | 5488 | 5488 | Nelson, County of
NT10BIX5570050 | 2010 | Q3 | Q3 - 2010 | 194 | 1363 | FALSE | 11 | Due to fiber purchase and make planning ahead of schedule. | 0 |  | N/A | 100 | No Variance from Baseline Report | 90 | Due to fiber purchase and make planning ahead of schedule. | 25 | Due to fiber purchase and make planning ahead of schedule. | 0 | N/A | 10 | No Variance from Baseline Report | 25 | Purchase dark fiber from Conneaut Telephone Company | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 2010-10-28 14:47 | 2010-10-28 14:47 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2010 | Q4 | Q4 - 2010 | 1056 | 2094 | FALSE | 45 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 60 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | No Variance from Baseline Report | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.No Variance from Baseline Report | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 2011-02-10 16:03 | 2011-02-10 16:03 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2011 | Q1 | Q1 - 2011 | 2200 | 2845 | FALSE | 43 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | No Variance from Baseline Report | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 29 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 40 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito expects to be back on schedule by the end of the September 2011 quarter. | 2011-05-20 10:52 | 2011-05-20 10:52 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2011 | Q2 | Q2 - 2011 | 3132 | 3323 | FALSE | 42 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. In addition, percentage is based off of projected expenditures. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 63 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | No Variance from baseline | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 13 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 15 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 40 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 20 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 2011-08-16 17:03 | 2011-08-16 17:03 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2011 | Q3 | Q3 - 2011 | 4086 | 3886 | FALSE | 74 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. In addition, percentage is based off of projected expenditures. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 87 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | No Variance from Baseline | 85 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 61 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 25 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 2011-11-16 16:12 | 2011-11-16 16:12 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2011 | Q4 | Q4 - 2011 | 5064 | 4735 | FALSE | 89 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | N/A | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 97 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | No Variance from Baseline | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 72 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 65 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 50 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 30 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has commenced but is still behind due to make ready delays. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 2012-02-16 09:08 | 2012-02-16 09:08 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2012 | Q1 | Q1 - 2012 | 6112 | 5658 | FALSE | 87 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | No Variance from Baseline | 98 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 84 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 60 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 45 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 2012-05-15 15:54 | 2012-05-15 15:54 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2012 | Q2 | Q2 - 2012 | 7072 | 6163 | FALSE | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 0 | n/a | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 96 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 70 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 55 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 2012-08-15 10:04 | 2012-08-15 10:04 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2012 | Q3 | Q3 - 2012 | 7872 | 6640 | FALSE | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 99 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 95 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's construction progress has been hampered by inconsistent make ready completion. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 2012-11-14 14:05 | 2012-11-14 14:05 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2012 | Q4 | Q4 - 2012 | 8776 | 7569 | FALSE | 100 | No Variance from Baseline | 0 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 2013-02-14 12:05 | 2013-02-14 12:05 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2013 | Q1 | Q1 - 2013 | 9240 | 8059 | FALSE | 100 | No Variance from Baseline | 100 |  | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 2013-04-24 12:28 | 2013-04-24 12:28 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2013 | Q2 | Q2 - 2013 | 10684 | 9003 | FALSE | 100 | No Variance from Baseline Report | 100 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-08-21 15:19 | 2013-08-21 15:19 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570050 | 2013 | Q3 | Q3 - 2013 | 11294 | 9444 | FALSE | 100 | No Variance from Baseline Report | 0 |  | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 0 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 100 | No Variance from Baseline Report | 2013-11-19 14:25 | 2013-11-19 14:25 | 5542 | 5542 | Zito Media Communications II, LLC
NT10BIX5570051 | 2010 | Q3 | Q3 - 2010 | 346 | 1439 | FALSE | 58 | delayed due to Environmental Assessment/Finding of No Significant Impact | 0 |  | n/a | 100 | completed with Finding of No Significant Impact issued | 100 | completed | 0 | n/a | 100 | all permits and approval acquired | 50 | site and tower work underway | 75 | purchasing occurring in accordance with project progress | 30 | network builds occur as towers come online. | 30 | begins with network build | 30 | as deployed | 2010-11-18 10:47 | 2010-11-18 10:47 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2010 | Q4 | Q4 - 2010 | 1138 | 2176 | FALSE | 25 | winter weather and the Environmental assessment slowed the started of the project. First Step should be able to resume procurement and begin construction late Q1. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approval acquired | 10 | winter weather has slowed the start of the project | 25 | winter weather has slowed the start of the project | 25 | network builds occur as towers are built and commissioned | 25 | begins with network build | 25 | as deployed | 2011-02-14 16:09 | 2011-02-14 16:09 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2011 | Q1 | Q1 - 2011 | 1990 | 2740 | FALSE | 25 | Late winter weather continue to provide delays in the beginning of the construction process. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 10 | winter weather delayed start of construction | 25 | tower and communication hut purchases completed. | 25 | network build begins with tower construction | 25 | begins with network build | 25 | as deployed | 2011-05-12 17:59 | 2011-05-12 17:59 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2011 | Q2 | Q2 - 2011 | 3068 | 3291 | FALSE | 48 | winter weather delayed construction start. Additional staff has been trained and deployed to bring the project back in line with estimates | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 50 | 5 major tower sites will be prepped and ready for construction of towers | 50 | Phase two radios will be purchased along with networking equipment necessary | 27 | 150 new microwave miles built out of a total planned 550 | 30 | 21 of 69 new paths built | 30 | 21 of 69 newly built paths tested | 2011-08-12 17:41 | 2011-08-12 17:41 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2011 | Q3 | Q3 - 2011 | 4068 | 3877 | FALSE | 52 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | Completed | 55 | Phase 3 radios will be acquired. The equipment procurement is occurring along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 55 | 36 of 69 microwave paths will be installed. | 55 | 36 paths will be deployed along with switching and routing equipment | 55 | testing of the deployed radios and network will be completed | 2011-11-16 13:36 | 2011-11-16 13:36 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2011 | Q4 | Q4 - 2011 | 5404 | 5084 | FALSE | 60 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | completed | 85 | Phase 4 radios will be acquired. The equipment procurement occurs along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 80 | Continued winter weather combined with the remoteness of many of the remaining paths will slow the deployment through Q1 2012. | 80 | Continued winter weather combined with the remoteness of many of the remaining paths will slow the deployment through Q1 2012. | 80 | testing of the deployed radios and network will be completed | 2012-02-29 13:58 | 2012-02-29 13:58 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2012 | Q1 | Q1 - 2012 | 5914 | 5556 | FALSE | 60 | Winter weather and the Environmental requirements slowed the start of the project. With the additional staff on board, we are working towards bringing the project back in line with projections. First Step has added additional staff to bring the project in line with the baseline indicators. First Step is working directly with NTIA on a Project Improvement Plan to address the initial project delays. Our project timeline shows that the project will have ~77% of the construction completed by the 2 year project award date. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | all permits and approvals acquired | 100 | completed | 90 | Phase 4 radios will be acquired. The equipment procurement occurs along with the construction schedule. With the proposed construction schedule, the equipment procurement schedule will match the construction completed. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. | 86 | Spring weather will allow First Step to begin the construction of the planned paths once again. 6 new paths will be completed in Q2, 2012. The network testing occurs along with the network deployment. | 2012-05-02 16:42 | 2012-05-02 16:42 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2012 | Q2 | Q2 - 2012 | 7288 | 6271 | FALSE | 68 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 10th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 95 | all major equipment will be acquired. The remaining will be miscellaneous and additional concerning the new tower construction. | 95 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. | 100 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. | 95 | Spring weather will allow First Step to begin the construction of the planned paths once again. 16 new paths will be completed in Q3, 2012. The network testing occurs along with the network deployment. | 2012-08-29 23:39 | 2012-08-29 23:39 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2012 | Q3 | Q3 - 2012 | 8020 | 6716 | FALSE | 72 | Our project timeline shows that the project will have ~95% of the construction completed by Q1 of 2013. That projection was based on a shovel ready start date of Q1 2010 with a 2 year window to completion of construction. Due to the project start delays concerning the EA, First Step has only been under construction for 2 actual years, even though we are in the 11th quarter of the 12 quarter project. First Step will still complete the project on time and on budget. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 95 | all major equipment will be acquired. The remaining will be miscellaneous and additional concerning the new tower construction. | 95 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. The remaining 5% will be the final network testing and final turn up of the CAI's. | 100 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. | 95 | final permit release by the US Forest Service will allow First Step to complete the final network building requirements. Network testing occurs along with the network building and equipment deployment. | 2012-11-21 14:27 | 2012-11-21 14:27 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2012 | Q4 | Q4 - 2012 | 8752 | 7548 | FALSE | 75 | First Step anticipates that they will be 100% completed with all key project indicators and planned construction activities. First Step anticipates being under budget with all key project indicators met. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-02-13 13:46 | 2013-02-13 13:46 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2013 | Q1 | Q1 - 2013 | 9226 | 8051 | FALSE | 82 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. If this approval is giving timely, work on the additional paths should be completed within the quarter. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-04-23 14:10 | 2013-04-23 14:10 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2013 | Q2 | Q2 - 2013 | 10586 | 8950 | FALSE | 83 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. If this approval is giving timely, work on the additional paths should be completed within the quarter. | 0 | n/a | n/a | 100 | completed | 100 | completed | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-08-14 17:38 | 2013-08-14 17:38 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2013 | Q3 | Q3 - 2013 | 11320 | 9460 | FALSE | 92 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. | 0 | n/a | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2013-11-21 10:29 | 2013-11-21 10:29 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2013 | Q4 | Q4 - 2013 | 11816 | 9994 | FALSE | 92 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. | 0 | n/a | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2014-02-13 17:22 | 2014-02-13 17:22 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2014 | Q1 | Q1 - 2014 | 12054 | 10213 | FALSE | 85 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-04-21 17:21 | 2014-04-21 17:21 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2014 | Q2 | Q2 - 2014 | 12320 | 10495 | FALSE | 100 | First Step anticipates the final approvals to move forward with the pending AAR for route modifications / additions. This will allow for us to complete the project by the end of Q3. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-07-25 14:41 | 2014-07-25 14:41 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2014 | Q3 | Q3 - 2014 | 12600 | 10869 | FALSE | 88 | First Step anticipates approvals to move forward with the pending AAR for route modifications / additions. This will allow for us to begin work on the requests as winter weather allows. We anticipate being able to make progress through the Quarter with final project completion by 9/30/2015. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-11-15 12:15 | 2014-11-15 12:15 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2014 | Q4 | Q4 - 2014 | 12672 | 10987 | FALSE | 89 | First Step anticipates approvals to move forward with the pending AAR for route modifications / additions. This will allow for us to begin work on the requests as winter weather allows. We anticipate being able to make progress through the Quarter with final project completion by 9/30/2015. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 99 | All network builds will be completed with the exception of the Hemlock Butte and Iron Mountain projects. These projects can not be started until the Spring weather arrives due to the mountain locations. | 99 | All equipment will be deployed with the exception of the Hemlock Butte and Iron Mountain projects. These projects can not be started until the Spring weather arrives due to the mountain locations. | 99 | All network and infrastructure testing will be completed with the exception of the Hemlock Butte and Iron Mountain projects. These projects can not be started until the Spring weather arrives due to the mountain locations. | 2015-02-02 10:54 | 2015-02-02 10:54 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2015 | Q1 | Q1 - 2015 | 12816 | 11195 | FALSE | 99 | First Step anticipates being completed with all aspects of the project by the end of Q2 with the exception of the required closeout. | 0 | n/a | n/a | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2015-05-05 13:27 | 2015-05-05 13:27 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570051 | 2015 | Q2 | Q2 - 2015 | 12890 | 11270 | FALSE | 100 | First Step anticipates being completed with all aspects of the project by the end of Q3 with the exception of the required closeout. | 0 | n/a | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 42220.455 | 42220.455 | 5543 | 5543 | First Step Internet, L.L.C.
NT10BIX5570053 | 2010 | Q3 | Q3 - 2010 | 462 | 1497 | FALSE | 45 | Project Implementation begins for two projects. | 17 | Travel/Training/Conversion Strategy | Inter-island travel due to site inspection and project implementation. | 0 | IT&E has received a Categorical Exclusion. | 74 | Network Design for other projects will continue. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 50 | FCC License is anticipated to be completed. | 57 | Site preparation work will continue. | 38 | Equipment and Materials for other projects will be procured. | 3 | Project Implementation begins. | 0 | N/A | 0 | N/A | 2010-11-30 18:53 | 2010-11-30 18:53 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2010 | Q4 | Q4 - 2010 | 1064 | 2099 | FALSE | 57 | Project Implementation continues for two projects. | 20 | TRAVEL/TRAINING/CONVERSION STRATEGY | Inter-island travel due to project implementation and site survey will continue. | 0 | IT&E has received a Categorical Exclusion. | 95 | Network Design will continue. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 37 | FCC License applications will be submitted for approval. | 40 | Site preparation will commence for two projects. | 45 | Equipment is expected to arrive for two projects. | 26 | Project Implementation continues. | 29 | Equipment Deployment will continue. | 12 | Testing of equipment will continue. | 2011-02-10 18:27 | 2011-02-10 18:27 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2011 | Q1 | Q1 - 2011 | 1996 | 2743 | FALSE | 88 | Project implementation will begin for the 29 Hops Project and the Inter-island Microwave Upgrade. | 41 | Training and Conversion Strategy | Inter-island travel due to project implementation will continue. Off-island training and on-site training will be conducted for different projects. | 0 | IT&E has received a Categorical Exclusion. | 97 | Prepaid Billing System Configuration will begin in June and should be completed by September. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 100 | FCC license approvals are expected to be received within three months. | 52 | Site preparation will continue for the 29 Hops Project and the Inter-island Microwave Project. | 100 | Remaining equipment for NOC and MPLS will be procured Q2 2011 | 29 | Build of 29 Hops Project and Inter-Island Microwave Upgrade will begin Q2 2011 | 30 | Equipment for 29 Hops Project and Inter-Island Microwave Upgrade will start Q2 2011 | 30 | Network testing will begin for 29 Hops Project and Inter-Island Microwave Upgrade as soon as equipment is installed. | 2011-05-13 03:52 | 2011-05-13 03:52 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2011 | Q2 | Q2 - 2011 | 3222 | 3372 | FALSE | 91 | Project Implementation will begin for the Prepaid Billing System. 29 Hops Project is expected to be completed this quarter. Inter-island Microwave Upgrade is anticipated to be at 80% complete. We hope to meet the 91% completion with our actual expenditures by the end of next quarter, but this is not expected since the Prepaid Billing project will not be completed until the end of December. We expect the 29 Hops to be 100% complete and the interisland Microwave Upgrade to be 90% complete by the end of the 3rd quarter, and the Prepaid Billing project to be 50% complete by this date. | 44 |  | Inter-island travel due to project implementation will continue. | 0 | IT&E has a Categorical Exclusion. | 97 | Prepaid Billing System Configuration continues. Postpaid Billing will begin. | 0 | IT&E has received a Categorical Exclusion. No work will be done in the Rights of Way. | 100 | All FCC License will be received. | 57 | Site preparation work will be completed for the Inter-Island Microwave Upgrade. | 100 | Postpaid Billing System RFP is expected to be issued. | 96 | Network Build continues is expected to be completed for the 29 Hops and the Inter-island Microwave Upgrade will be close to completion. | 57 | Equipment Deployment will continue for the 29 Hops and the Inter-island Microwave Upgrade. | 30 | Network Testing will continue for the 29 Hops and Inter-island Microwave Upgrade Projects. | 2011-08-18 23:20 | 2011-08-18 23:20 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2011 | Q3 | Q3 - 2011 | 4114 | 3900 | FALSE | 99 | Award of Postpaid Billing Project will be made. Testing of Prepaid Billing Project will begin late this quarter. These are the two remaining subprojects under this grant. | 89 |  | Interisland travel due to project implementation of the two remaining projects. | 0 | IT&E received a categorical exclusion. | 98 | Kick off of Postpaid Billing Project. | 0 | No work will be done in the Rights of Way. | 100 | FCC Licenses received. | 100 | Postpaid Billing Project will commence. | 100 | All equipment procurement is expected to be initiated. | 100 | Postpaid Billing Project will commence. | 100 | Postpaid Billing Project will commence. | 80 | Network Testing will be conducted for the Prepaid Billing Project. | 2011-11-17 14:57 | 2011-11-17 14:57 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2011 | Q4 | Q4 - 2011 | 4720 | 4369 | FALSE | 96 | Postpaid Billing Project will commence. | 93 |  | Travel inter-island will continue for Postpaid Billing Project and training. | 0 | IT&E received a categorical exclusion. | 98 | Postpaid Billing will commence. | 0 | No work will be done in ROW. | 100 | FCC licenses have been received. | 100 | All Site preparation work is expected to be completed. | 95 | Postpaid Billing Project Equipment required is expected to be procured. | 80 | Postpaid Billing Project will commence. | 95 | Prepaid Triggers expected to be installed. | 81 | Network testing expected to be completed for Prepaid Billing System this quarter. | 2012-01-30 16:13 | 2012-01-30 16:13 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2012 | Q1 | Q1 - 2012 | 5908 | 5553 | FALSE | 96 | Postpaid Billing Project will continue. | 85 |  | User Training will continue for Prepaid Billing Project. | 0 | IT&E received a categorical exclusion. | 100 | Network Design has been completed. | 0 | No work will be done in the ROW. | 100 | FCC licenses applied for have been received. | 100 | Site Preparation has been completed. | 100 | Equipment Procurement has been completed. | 90 | Postpaid Billing project will continue. | 97 | Hardware for Postpaid Billing will be installed. | 87 | User Testing continues for Prepaid Billing Project. | 2012-05-02 01:01 | 2012-05-02 01:01 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2012 | Q2 | Q2 - 2012 | 6844 | 6048 | FALSE | 98 | Postpaid Billing Project will continue. | 90 |  | Training (on-site support) will end this quarter for the Prepaid Billing Project. Travel for Postpaid Billing Projects between the islands. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications will be completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 95 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). | 100 | Hardware for Postpaid Billing Project will be delivered to IT&E and installed at Data Network Operations Center (NOC). | 90 | Postpaid Billing Project software development will continue. | 2012-08-02 21:59 | 2012-08-02 21:59 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2012 | Q3 | Q3 - 2012 | 7854 | 6631 | FALSE | 99 | Postpaid Billing Project will continue. | 99 |  | Training (on-site support) will end this quarter for the Prepaid Billing Project. Travel for Postpaid Billing Projects between the islands. Training will commence. | 0 | IT&E received a categorical exclusion. | 100 | Systems Requirements Specifications completed. | 0 | No work will be done in the Rights of Way. | 100 | FCC licenses applied for have been received. | 100 | All Site Preparation work has been completed. | 100 | All Equipment has been procured. | 99 | Software Development and customization will continue based on the Systems Requirements Specifications (SRS). Data migration will continue. | 100 | All equipment deployed. | 99 | ATP Testing will commence. | 2012-11-13 23:02 | 2012-11-13 23:02 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2012 | Q4 | Q4 - 2012 | 8690 | 7504 | FALSE | 100 | Postpaid Billing Project completed. | 100 |  | Training completed. | 0 | IT&E received a categorical exclusion. | 100 | Network design completed. | 0 | No work done in the rights of way. | 100 | All FCC licenses approved and received. | 100 | Site Preparation completed. | 100 | All Equipment Procured. | 100 | Build completed. | 100 | All Equipment Deployed. | 100 | Testing Completed. | 2013-02-11 01:55 | 2013-02-11 01:55 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | 2013 | Q1 | Q1 - 2013 | 11392 | 9504 | FALSE | 100 | Project Completed. Grant Award expired 2/28/13. | 100 |  | Project Completed. Grant Award expired 2/28/13. | 0 | n/a | 100 | Project Completed. Grant Award expired 2/28/13. | 0 | n/a | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 100 | Project Completed. Grant Award expired 2/28/13. | 2013-11-26 13:24 | 2013-11-26 13:24 | 5550 | 5550 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570054 | 2010 | Q3 | Q3 - 2010 | 226 | 1379 | FALSE | 5 | See comments in #3 below | 0 |  | NA | 98 | See comments in #3 below | 2 | See comments in #3 below | 1 | See comments in #3 below | 0 | See comments in #3 below | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2010-10-29 12:49 | 2010-10-29 12:49 | 5552 | 5552 | Page County Broadband Authority
NT10BIX5570054 | 2010 | Q4 | Q4 - 2010 | 1386 | 2397 | FALSE | 15 | N/A | 0 |  | N/A | 100 | N/A | 25 | N/A | 30 | N/A | 35 | N/A | 0 | N/A | 15 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-28 13:37 | 2011-02-28 13:37 | 5552 | 5552 | Page County Broadband Authority
NT10BIX5570054 | 2011 | Q1 | Q1 - 2011 | 1460 | 2443 | FALSE | 25 | Will not have received permissions from SVEC, Centurylink and VMRC nor railroads. | 0 | NA | NA | 100 | NA | 50 | No variance to baseline anticipated at this time, pending make ready operations in progress and no need for any changes in design. Point of Presence locations will have been approved. | 75 | no variance | 70 | Railroad permits will still be outstanding as well as VMRC permits. | 0 | NA | 40 | no variance | 20 | Will not have permissions to attach or construct anything other than one remote site POP. | 0 | no variance | 0 | no variance | 2011-04-22 14:35 | 2011-04-22 14:35 | 5552 | 5552 | Page County Broadband Authority
NT10BIX5570054 | 2011 | Q2 | Q2 - 2011 | 3232 | 3377 | FALSE | 30 | Extremely high make ready costs will require change in deployment to an estimated 50% underground. Network redesign in progress as well as changes to permitting and environmental assessment. | 0 |  | N/A | 90 | Reinitiation of environmental consultations for areas changed to underground construction, amendment to EA in progress. Anticipated completion of the new EA is anticpated by the end of Q4 (Dec. 31, 2011). | 50 | Redesign of portions of network changing from aerial to underground construction. No change to route or route miles to be deployed. | 75 | Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q4. | 60 | Permitting in progress with VDOT for areas changed to underground deployment. | 0 | No Variance | 15 | Will not procure any more materials or equipment until design is finalized. | 0 | Redesign and permitting in progress, construction will not have started. | 0 | Equipment deployment delayed until after construction of fiber which will not have started in this quarter. | 0 | No Variance | 2011-08-19 13:25 | 2011-08-19 13:25 | 7118 | 7118 | Page County Broadband Authority
NT10BIX5570054 | 2011 | Q3 | Q3 - 2011 | 4236 | 3966 | FALSE | 10 | Variance expected: The original baseline projected 95% completion in Qtr 4. During the next quarter it is anticipated that a revised design will be approved by NTIA and reconsultation for an environmental assessment amendment will be underway along with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | Variance expected: This project's environmental assessment will be amended to remove tower construction, replace fiber backhaul with microwave, and move some areas of fiber construction from aerial to underground. No historic buildings will be modified, no new CAI last mile construction is proposed, and the underground construction will occur within department of transportation or town rights of way. During this quarter reinitiation of environmental consultations will be in progress. Anticipated completion of the new EA is anticipated before the end of Q1 2012. | 100 | No variance anticipated. Pending timely approval by NTIA of the project modification, redesign of portions of network changing from aerial to underground construction will be completed as significant portions of the design completed to date will not change. | 100 | No variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q4. | 100 | No variance: Permitting in progress with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 0 | The baseline projections were developed prior to entering into contract for construction. Variance expected as the current contract for design and construction stipulate payments to contractor to be made at significant construction completion points. Some materials have already been procured by the contractor that would not be affected by the proposed modification. No further equipment will be procured by the contractor until design is complete, anticipate final equipment and materials to be procured by the contractor during Qtr 1 2012. | 1 | Variance: expected: The current unliquidated obligation in the amount of $30,745.91 for the Luray interconnection facility already constructed is expected to be expended in the next quarter. All other preconstruction activities and including reinitiation of consultation for an environmental assessment amendment will be in progress pending timely approval of project design modification. Further construction of network facilities not anticipated until Qtr 1 2012. | 0 | Variance expected: No deployment of equipment or materials will be in progress in the next quarter as preconstruction activities will be in progress pending timely approval of project design modification. | 0 | Variance expected; No network construction anticipated during this quarter due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in October 2011 and anticipates only having the design complete by the end of Q4-2011 with construction slated to begin in Q1-2012. | 2011-11-22 16:56 | 2011-11-22 16:56 | 7118 | 7118 | Page County Broadband Authority
NT10BIX5570054 | 2011 | Q4 | Q4 - 2011 | 5394 | 5077 | FALSE | 29 | Variance: During the next quarter it in anticipated that a revised design will be approved by NTIA and reconsultation for an environmental assessment amendment will be complete with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | Variance expected: This project's environmental assessment will be amended to remove tower construction, replace fiber backhaul with microwave, and move some areas of fiber construction from aerial to underground. No historic buildings will be modified, no new CAI last mile construction is proposed, and the underground construction will occur within department of transportation or town rights of way. During this quarter reinitiation of environmental consultations will be in progress. Anticipated completion of the new EA is anticipated before the end of Q1 2012. | 100 | Variance: Baseline predicted original design at 100% completion by end of Qtr 4. Pending timely approval by NTIA of the project modification, redesign of portions of network changing from aerial to underground construction will be completed as significant portions of the design completed to date will not change. | 100 | No variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT ROW due to a deployment modification. Anticipated completion of these agreements by the end of Q1-2012. | 100 | No variance: Permitting in progress with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 50 | Variance: Some materials have already been procured by the contractor that would not be affected by the proposed modification. No further equipment will be purchased until design is complete, anticipate final procurement to occur Qtr 2 2012. | 1 | Variance: No construction can be started until approval received, anticipate receiving Qtr 1 2012. | 0 | Variance in baseline due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a final project modification to NTIA in December 2011. | 0 | Variance: no network construction anticipated during this quarter due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a final project modification to NTIA in December 2011 and anticipates only having the design complete by the end of Q1-2012 with construction slated to begin in Q2-2012. | 2012-02-29 12:54 | 2012-02-29 12:54 | 7118 | 7118 | Page County Broadband Authority
NT10BIX5570054 | 2012 | Q1 | Q1 - 2012 | 6268 | 5736 | FALSE | 50 | Variance: During the next quarter it is anticipated that a revised design will be complete and the reconsultation for an environmental assessment amendment will be approved with final construction design by the construction contractor Shentel. | 0 |  | N/A | 100 | We anticipate NTIA will approve the supplemental EA. | 100 | Baseline predicted original design at 100% completion by end of Qtr 4. Redesign of portions of network changing from aerial to underground construction will be completed. The microwave design and engineering will also be complete. | 100 | No Variance. Work will be in progress for solidifying pole agreement with electric cooperative and VDOT Right-of-Way (ROW) due to a deployment modification. Anticipated completion of these agreements by the end of Q2-2012. | 100 | No Variance: Permitting complete with VDOT for areas changed to underground deployment, and two railroad crossing permits will be complete. | 0 | No Variance | 75 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. No further equipment will be purchased until design is complete, anticipate procurement to occur Qtr 2 and Qtr 3 2012. | 1 | Variance: No construction can be started until approval of EA amendment and final design is complete. Anticipated completion of these tasks is Q2-2012. Only the facility in Luray has been constructed (facility only no equipment). | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012.The PCBA anticipates only having the design complete by the end of Q2-2012 with construction slated to begin in Q3-2012. | 2012-05-23 14:01 | 2012-05-23 14:01 | 7118 | 7118 | Page County Broadband Authority
NT10BIX5570054 | 2012 | Q2 | Q2 - 2012 | 7144 | 6199 | FALSE | 85 | Variance: During the next quarter it is anticipated that a revised design will be approved, permits secured and rights of way and easements acquired. It is also anticipated that construction and make-ready work will be underway. | 0 |  | N/A | 90 | NTIA and the NOAA Grants Office approved the supplemental EA for the project modification approved in January 2012. A second proposed modification for Segment 4 in the Town of Shenandoah, including the EHP Checklist, will be submitted to NTIA with expected approval in Q3-2012. | 100 | The baseline predicted original design at 100% completion by end of Qtr 2. Redesign of portions of network changing from aerial to underground construction are completed. The microwave design and engineering is also complete. Segments 1-3 and 5 are complete and approved by the PCBA. Design for Segment 4 will be complete during the next quarter. | 100 | No Variance. Work will be complete for VDOT and other necessary Rights-of-Way (ROW). Additional easements are also being secured. Anticipated completion of these agreements by the end of July 2012. | 100 | No Variance: Permitting activities will be complete. | 0 | No Variance. | 100 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. Further equipment will be purchased now that the design is complete, anticipate procurement complete in Qtr 3-2012. | 50 | Variance: Only the facility in Luray has been constructed (facility only no equipment) to date. The PCBA anticipates the network build to get underway in Qtr 3-2012. | 75 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. The PCBA anticipates equipment deployment to begin in Qtr 3-2012. | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012.The PCBA anticipates only having the design approved with initial construction started in Q3-2012. Network testing expected to initiate in Q4-2012. | 2012-08-20 08:57 | 2012-08-20 08:57 | 7393 | 7393 | Page County Broadband Authority
NT10BIX5570054 | 2012 | Q3 | Q3 - 2012 | 8136 | 6776 | FALSE | 89 | Variance: During the next quarter it is anticipated that construction will complete and make-ready work will be complete. Network testing will also be underway. | 0 |  | No Variance | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 0 | No Variance | 100 | Some materials have already been procured by the contractor that would not be affected by the proposed modification approved in January 2012 by NTIA and the NOAA Grants Office. 7 Anticipate procurement complete in Qtr 4-2012. | 95 | Variance: Only the facility in Luray has been constructed (facility only no equipment) to date. Construction and make-ready work are currently underway. The PCBA anticipates the network build to have substantial completion in Q4-2012. | 100 | No Variance. | 50 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. Network testing expected to initiate in Q4-2012 and be complete in Q1-2013. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7393 | 7393 | Page County Broadband Authority
NT10BIX5570054 | 2012 | Q4 | Q4 - 2012 | 9146 | 7962 | FALSE | 95 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-03-25 13:25 | 2013-03-25 13:25 | 7393 | 7393 | Page County Broadband Authority
NT10BIX5570054 | 2013 | Q1 | Q1 - 2013 | 12154 | 10337 | FALSE | 83 | Variance due to project modification and left over funds. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. Project was completed on February 28, 2013. | 0 | N/A | N/A | 59 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 10 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 23 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. | 47 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 100 | No Variance. Actuals from project inception through end of the current reporting period are 200% of the budget figures. Activity complete. | 45 | Variance due to project modification and left over funds. Activity complete, however dollars expended are less than projected in project budget. . | 2014-05-01 09:03 | 2014-05-01 09:03 | 7393 | 7393 | Page County Broadband Authority
NT10BIX5570055 | 2010 | Q3 | Q3 - 2010 | 266 | 1399 | FALSE | 18 | Original projection was set at 15%. Expected construction start date moved ahead of schedule | 0 |  | No Variance | 100 | No Variation | 100 | No Variation | 75 | Projecting completion by next quarter | 100 | Projecting completion by next quarter | 10 | Projecting to begin construction this quarter | 50 | No Variance | 10 | Projecting to begin construction this quarter | 25 | Projecting to begin equipment deployment in conjunction with construction | 0 | No Variance | 2010-10-29 18:18 | 2010-10-29 18:18 | 5554 | 5554 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2010 | Q4 | Q4 - 2010 | 1176 | 2209 | FALSE | 20 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 75 | 100% of ROW has been completed for the Fiber Optic Backbone, Projecting completion of ROW for laterals and towers by end of quarter. | 100 | No Variance | 25 | No Variance | 75 | No Variance | 21 | No Variance | 10 | No Variance | 5 | No Variance | 2011-02-16 11:09 | 2011-02-16 11:09 | 5554 | 5554 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2011 | Q1 | Q1 - 2011 | 2190 | 2840 | FALSE | 18 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 0 |  | No Variance | 95 | Variance is due to changes in the fiber optic route or tower locations which may require an additional environmental assessment | 100 | No Variance | 75 | Variance is due to the potential route changes that may require additional ROW assessment. | 75 | NTUA anticipated 100% completion of permits & approvals however variance will occur due to the delay in obtaining road crossing permits and Indian Allotment issues. In order to remedy the issues, NTUA has hired T&D Surveyors to expedite the road crossing permits and NTUA has hired a consultant to approach the land owners directly for Indian Allotment consent. | 50 | No Variance | 100 | No Variance | 18 | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | 10 | Variance is due to previous delays in RFP process & finalizing service line agreements. | 10 | Variance is due to the previous construction and service line delays. | 2011-05-19 16:41 | 2011-05-19 16:41 | 5554 | 5554 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2011 | Q2 | Q2 - 2011 | 2972 | 3243 | FALSE | 26 | Variance is due to subsequent delays in Make Ready production as well as delays in tower construction. NTUA has acquired additional crews to assist with Make Ready and streamlined the tower RFP process to expedite build out. | 0 |  | - | 95 | Reasons for variance in the EA are due to changes in the location of towers that are outside the original EA. To start construction on the sites the following steps are required. 1. Further environment and cultural studies and final assessment 2. Acquire approvals from Fish & Wildlife 3. Submit changes to the NTIA for approval Formal environmental and cultural studies are currently under way and NTUA anticipates submitting an action award request for NTIA approval once NTUA obtain final results of the studies and approval from U.S. Fish and wildlife. | 100 | No Variance | 75 | Variance is due to changes in original network design which require additional ROW approvals. | 70 | Variance in construction permit approvals is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Furthermore, NTUA hired T&D Contractors to expedite the development of profiles required for permit application in Arizona. NTUA will submit permit applications to the Arizona Department of Transportation in piecemeal fashion as they receive profiles for individual areas from T&D contractors. | 75 | No Variance | 75 | Variance is due to delays in network build out. | 30 | Variance is due to previous delays trickling down to the next quarter. NTUA has developed a process to increase production. | 15 | Variance is due to a lack of signed agreements. NTUA anticipates completion of critical agreements prior to the end of the quarter at which time equipment will be deployed in a phased approach. | 15 | Variance is due to delays in network build out and a lack of signed agreements. NTUA anticipates testing to begin during this quarter. | 2011-08-09 13:10 | 2011-08-09 13:10 | 5554 | 5554 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2011 | Q3 | Q3 - 2011 | 4354 | 4033 | FALSE | 45 | Reasons for variance from the baseline are as follows: 1. Delays in the overall project are due to subsequent delays in Make Ready production. To alleviate the delay, NTUA has hired additional contractors to assist. 2. Delays in obtaining Rural Utilities Service (RUS) approvals for transmission line work. NTUA in conjunction with their consultants are working directly with RUS to expedite the RUS approval process. 3. Delays in acquiring Indian Allotments approvals and Rights of Way. NTUA has taken a proactive approach to resolving the Indian Allotment issue including the various alternatives such as route change, gigabit laser, and utilizing existing microwave system as a temporary measure until approval is obtained. 4. Weather Delays |  |  | - | 95 | NTUA is currently in the process of performing an environmental assessment on 4 tower locations that were not covered in the original Findings of No Significant Impact (FONSI). NTUA anticipates completion of the assessment and submittal of Award Action Request to the NTIA by the end of the quarter. | 100 | No Variance | 75 | Variance in obtaining Rights of Way (ROW) is due to changes in Navajo Nation ROW process. To alleviate the problem, NTUA ROW agents / Government liaisons are working directly with the Navajo Nation & Arizona Department of Transportation to expedite approvals. | 75 | Variance in obtaining construction permits is due to delays in the submittal process. NTUA has submitted all permit applications required for New Mexico. Profiles required for Arizona permits are currently being developed. To expedite the process, NTUA hired T&D Contractors to assist in the development of profiles. T&D is currently working on the crucial, time-sensitive profiles and will submit to NTUA on a piecemeal basis for submission to the Arizona department of transportation. | 90 | No Variance | 85 | Variance is due to delays in microwave equipment deployment. Also, due to rapid changes in technology, NTUA has decided to delay purchase of laptops. | 45 | Variance is due to previous delays in fiber optic construction caused by sluggish Make Ready progress and lack of RUS approvals. | 35 | Variance is due to NTUA decision to delay procurement of last mile customer premise equipment due to technology changes | 40 | Variance is a consequence of previous delays in construction and microwave deployment | 2011-11-30 16:02 | 2011-11-30 16:02 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2011 | Q4 | Q4 - 2011 | 5286 | 4955 | FALSE | 74 | No Variance |  |  | - | 100 | No Variance | 100 | No Variance | 80 | Variance is due to the elongated process for obtaining easement rights for traversing Indian Allotments. NTUA has taken steps to expedite the allotment process including hiring additional consultants to approach the allottees. | 100 | No Variance | 100 | No Variance | 90 | Variance is due to the rapid changes in technology which has prompted NTUA to delay purchases of Netbooks. | 70 | No Variance | 65 | Variance is due to delays in procuring Microwave equipment and last mile customer premise equipment (CPE). | 70 | Variance is a consequence of previous delays in construction and the IRU agreement. | 2012-02-27 13:21 | 2012-02-27 13:21 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2012 | Q1 | Q1 - 2012 | 6314 | 5759 | FALSE | 74 | Variance will be due to the Indian Allotment issues. NTUA has hired a consultant to address the issue. |  |  | N/A | 100 | No Variance | 100 | No Variance | 85 | Variance is due to the elongated process for obtaining easement rights for traversing Indian Allotments. NTUA has taken steps to expedite the allotment process including hiring additional consultants to approach the allottees. | 100 | No Variance | 100 | No Variance | 90 | Variance will be due to delays in procuring the last mile dongles | 85 | Variance will be due to previous delays and potential delays in build out due to Indian Allotments. | 85 | Variance will be due to previous delays and potential delays in build out due to Indian Allotments. Deployment of the wireless links have a potential for delay depending on remaining tower construction. | 85 | Variance is a consequence of previous delays in construction | 2012-05-29 10:27 | 2012-05-29 10:27 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2012 | Q2 | Q2 - 2012 | 6864 | 6058 | FALSE | 90 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. |  |  | - | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. | 95 | Variance might occur due to Indian Allotment Issues and tower construction. NTUA has developed a contingency plan regarding the allotments. | 90 | Variance might occur as a consequence of previous delays in construction. | 2012-08-06 13:36 | 2012-08-06 13:36 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2012 | Q3 | Q3 - 2012 | 8120 | 6767 | FALSE | 97 | NTUA anticipates all construction and testing to be complete. A slight variance may occur due to weather related issues or a protracted approval process for the three towers that require NTIA approval. NTUA plans of utilizing the last quarter for auditing and close out procedures. |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Variance is due a couple of events including the following: 1. WESODI lost several employees due to the clean up efforts for Hurricane Sandy. 2. The accident at the Little Water Tower site will cause a delay of up to six weeks because a new piece of the tower had to be ordered. 3. Approval for the three remaining tower sites has not been acquired: Blue Gap, Houck, and Hole in the Rock. NTUA will require a minimum of 4 weeks to complete each tower. | 90 | Variance is due to delays in the network build. Equipment can not be deployed on towers that are incomplete. Furthermore, NTUA will require time for testing and configuration of the equipment once the network build is complete. | 100 | No Variance | 2012-11-28 15:51 | 2012-11-28 15:51 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2012 | Q4 | Q4 - 2012 | 8908 | 7691 | FALSE | 92 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. |  |  | - | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 97 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. | 96 | Variance is due to previous delays in weather and tower construction which lead to delays in microwave link and 4G LTE installation and testing. | 85 | Variance is due to delays in the equipment deployment | 2013-02-22 14:34 | 2013-02-22 14:34 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2013 | Q1 | Q1 - 2013 | 9940 | 8513 | FALSE | 99 | Variance due to the following: 1. Clean up process 2. Remaining Microwave Link installation at Escrito Mesa. 3. Close out process. |  |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | Variance is anticipated due to an anticipated delay in the Escrito Mesa microwave link. The Escrito Mesa tower is a state funded project however the microwave equipment to be installed on the tower is funded by NTIA. NTUA anticipates the tower to be compete in August with the MW to be installed thereafter. | 100 | No Variance | 98 | Variance due to delayed LTE commissioning | 2013-05-28 15:28 | 2013-05-28 15:28 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2013 | Q2 | Q2 - 2013 | 10512 | 8908 | FALSE | 100 | No Variance |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-08-07 14:03 | 2013-08-07 14:03 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2013 | Q3 | Q3 - 2013 | 11370 | 9490 | FALSE | 100 | No Variance |  |  |  | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-11-25 10:46 | 2013-11-25 10:46 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | 2013 | Q4 | Q4 - 2013 | 12702 | 11029 | FALSE | 100 | No Variance | 100 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2015-02-19 14:23 | 2015-02-19 14:23 | 7302 | 7302 | Navajo Tribal Utility Authority Company
NT10BIX5570056 | 2010 | Q3 | Q3 - 2010 | 456 | 1494 | FALSE | 70 | N/A | 30 |  | Outreach to local libraries and other anchor institutions. | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 70 | N/A | 0 | N/A | 30 | N/A | 30 | N/A | 0 | N/A | 2010-11-30 15:38 | 2010-11-30 15:38 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2010 | Q4 | Q4 - 2010 | 1098 | 2138 | FALSE | 60 | Awaiting approval for tower/route change and winter weather delays--project will not be completed by March 31 as planned. | 30 |  | Awaiting approval for tower/route change and winter weather delays | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 70 | Awaiting approval for tower/route change and winter weather delays | 50 | Awaiting approval for tower/route change and winter weather delays | 50 | Awaiting approval for tower/route change and winter weather delays | 0 | Awaiting approval for tower/route change and winter weather delays | 2011-02-11 17:07 | 2011-02-11 17:07 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2011 | Q1 | Q1 - 2011 | 1876 | 2683 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-02 22:58 | 2011-05-02 22:58 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2011 | Q2 | Q2 - 2011 | 3102 | 3308 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:55 | 2011-08-15 21:55 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2011 | Q3 | Q3 - 2011 | 3566 | 3557 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-10-28 00:54 | 2011-10-28 00:54 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2011 | Q4 | Q4 - 2011 | 5330 | 5002 | FALSE | 1 | Project on hold pending review of progress. | 35 |  | Project on hold pending review of progress. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | N/A | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 0 | Project on hold pending review of progress. | 2012-02-28 08:50 | 2012-02-28 08:50 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570056 | 2012 | Q1 | Q1 - 2012 | 5712 | 5453 | FALSE | 1 | Project has been terminated | 35 |  | Project has been termianted | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been termianted | 0 | Project has been termianted | 0 | N/A | 0 | Project has been termianted | 0 | Project has been termianted | 0 | Project has been termianted | 2012-04-29 21:49 | 2012-04-29 21:49 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2010 | Q3 | Q3 - 2010 | 458 | 1495 | FALSE | 30 | N/A | 30 |  | Outreach to local libraries and other anchor institutions | 100 | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | N/A | 20 | N/A | 0 | N/A | 2010-11-30 15:56 | 2010-11-30 15:56 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2010 | Q4 | Q4 - 2010 | 1114 | 2152 | FALSE | 60 | Will complete network design, rights of way, permitting, and equipment procurement. | 30 | Library outreach | Will continue library outreach and RFP response. | 100 | N/A | 100 | Will complete tower site logistics. | 100 | Will determine and request permits for rights of way. | 100 | Will request necessary permits. | 70 | Will finalize tower sites for construction. | 100 | Will order all equipment necessary for deployment. | 30 | Will commence network build. | 30 | Will commence equipment deployment. | 0 | N/A | 2011-02-11 18:03 | 2011-02-11 18:03 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2011 | Q1 | Q1 - 2011 | 1878 | 2684 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Will continue library outreach and RFP reponse | 100 | N/A | 100 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-02 23:01 | 2011-05-02 23:01 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2011 | Q2 | Q2 - 2011 | 3270 | 3397 | FALSE | 2 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-23 00:10 | 2011-08-23 00:10 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2011 | Q3 | Q3 - 2011 | 4320 | 4010 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-11-29 15:20 | 2011-11-29 15:20 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2011 | Q4 | Q4 - 2011 | 5332 | 5004 | FALSE | 1 | Project on hold pending progress review. | 35 |  | Project on hold pending progress review. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 2012-02-28 08:58 | 2012-02-28 08:58 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570057 | 2012 | Q1 | Q1 - 2012 | 5714 | 5454 | FALSE | 1 | Project has been terminated | 35 |  | Project has been terminated | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 2012-04-29 21:51 | 2012-04-29 21:51 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570058 | 2010 | Q3 | Q3 - 2010 | 374 | 1453 | FALSE | 25 | Delay in drafting of engineering and construction projects have delayed RFQs and other bidding documents. Anticipate holidays to also influence delay in time-lines. | 0 | None | No Variance from baseline | 0 | N/A | 100 | No Variance from baseline | 100 | No Variance from baseline | 100 | No Variance from baseline | 0 | N/A | 100 | No Variance from baseline | 10 | Delay in engineering and construction documents have delayed project as a whole. Anticipate construction and equipment awards by the end of 3rd quarter, however also anticipate holidays to slow mobilization of contractor and delivery of equipment. | 0 | No Variance from baseline | 0 | No Variance from baseline | 2010-11-22 12:33 | 2010-11-22 12:33 | 5557 | 5557 | City of Williamstown
NT10BIX5570058 | 2010 | Q4 | Q4 - 2010 | 1284 | 2309 | FALSE | 60 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 0 |  | No Variance from Baseline | 0 | N/A | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 100 | No Variance from Baseline | 0 | N/A | 95 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 60 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 50 | Projection was estimate of project time line. Previous engineering, contract draft delays, and winter weather have created delays in overall project. Project is expected to proceed quickly, meeting projections as spring weather arrives. | 0 | No Variance from Baseline | 2011-02-22 11:30 | 2011-02-22 11:30 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2011 | Q1 | Q1 - 2011 | 1964 | 2727 | FALSE | 99 | No variance from baseline | 0 |  | N/A | 0 | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 0 | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 70 | No variance from baseline | 2011-05-12 11:48 | 2011-05-12 11:54 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2011 | Q2 | Q2 - 2011 | 3346 | 3436 | FALSE | 100 | No variance from baseline. | 100 |  | By the end of quarter three of 2011 we should be 100 percent complete with the construction and testing, which will leave the customer installs and we should not have any problems meeting the baseline numbers for those. | 0 | n/a | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | n/a | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2011-08-29 11:47 | 2011-08-29 11:47 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2011 | Q3 | Q3 - 2011 | 3990 | 3833 | FALSE | 100 | No variance from baseline. | 100 |  | Ahead of baseline, all equipment for customer registration/installs are purchased and paid for. We are still installing customers. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2011-11-11 12:05 | 2011-11-11 12:05 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2011 | Q4 | Q4 - 2011 | 5412 | 5096 | FALSE | 100 | No variance from baseline. | 100 |  | Slightly ahead of baseline due to being ready to install in earlier quarters that what was projected. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-02-29 15:35 | 2012-02-29 15:35 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2012 | Q1 | Q1 - 2012 | 6104 | 5654 | FALSE | 100 | No variance from base line. | 83 |  | Had 86 customers of the 103 in baseline at the end of reporting period, believe the economy has to do with the lower number. | 0 | N/A | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 0 | N/A | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 100 | No variance from base line. | 2012-05-15 15:09 | 2012-05-15 15:09 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2012 | Q2 | Q2 - 2012 | 6988 | 6121 | FALSE | 100 | No variance from baseline. | 83 | Subscribers | We still are at 86 subscribers however we have added subscribers this quarter the number is unchanged from last quarter due to people moving etc. Plus we feel it has to do with a poor economy and this being a very rural community. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-08-09 17:28 | 2012-08-09 17:28 | 6960 | 6960 | City of Williamstown
NT10BIX5570058 | 2012 | Q3 | Q3 - 2012 | 7784 | 6593 | FALSE | 100 | No variance from baseline. | 100 | Subscribers | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2012-11-07 13:26 | 2012-11-07 13:26 | 6960 | 6960 | City of Williamstown
NT10BIX5570059 | 2010 | Q3 | Q3 - 2010 | 424 | 1478 | FALSE | 2 | Based on grant expenditures for the project, baseline projections were estimated at 5%. Pend Oreille believes the project will be closer to 2% complete based on expenditures only. Expenditures in equipment and Network Build will not occur as anticipated. | 2 | Sales Tax | See narrative for 2a. above. | 100 | N/A | 80 | N/A | 40 | N/A | 70 | N/A | 0 | N/A | 0 | N/A | 0 | Based on potential weather delays, awarding of contracts, and anticipated FONSI receipt late in the quarter, it is not expected that any portion of the Network will be started in the 4th Q of 2010. | 0 | N/A | 0 | N/A | 2010-11-24 15:09 | 2010-11-24 15:09 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2010 | Q4 | Q4 - 2010 | 982 | 2025 | FALSE | 5 | No variance. | 5 | Sales Tax | No variance. | 100 | No variance. | 90 | Network design is near completion with finalization ahead of schedule. | 90 | No variance. | 60 | Some State and county permitting will need to be resolved with outstanding issues currently being completed. Additionally, the State Environmental Protection Act for Washington is currently being addressed for approval, which has extended the permitting process. | 40 | Staking and site preparation is on schedule according to our Baseline Report. | 20 | Equipment purchases, although in process, will be staggered to arrive as needed for project completion. | 2 | Network build may initiate this quarter, but minimally at best scenario. | 0 | No variance. | 0 | No variance. | 2011-02-04 15:49 | 2011-02-04 15:49 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2011 | Q1 | Q1 - 2011 | 2160 | 2825 | FALSE | 13 | 35-Overall expenditures lag baseline as a result of aggressive forecasting on our part when projecting out the anticipated process. | 0 | Sales Tax | 35-Sales tax will be incorporated into the expenditure detail at a future date. | 98 | 100-Environmental process is completed. | 40 | 80-This metric may not meet the expenditures as planned as the process and work appears to be on target. | 95 | 80-Rights of way acquistion process is substantially completed. Some minimal work may be necessary as we progress through the construction phase. | 50 | 95-Permitting work will continue as additional resources are utilized. This category may have been potentially over budgeted and may not meet the expenditures originally called out. | 30 | 40-Site preparation continues to lag as are deploying additional resources, thus expenditures, towards making up some of the lag in this particular metric. | 45 | 80-Preliminary equipment procurement budgets anticipated expenditures earlier in the project timeline, but will not occur until later in this calendar year. Expectations are to meet this metric by end of 2011. | 15 | 35-Network build was originally anticipated beginning earlier on in the project life cycle, and an original forecast of 30% being done over this past quarter. Although we are currently behind the baseline projections, we feel confident that this will be made up and the project completion will occur within the Broadband Technology Opportunities Program timeline. | 10 | 10-No variance. | 0 | 0-No variance. | 2011-05-19 09:44 | 2011-05-19 09:44 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2011 | Q2 | Q2 - 2011 | 2932 | 3223 | FALSE | 17 | Baseline 49-Overall expenditures lag baseline as a result of aggressive forecasting when doing the Baseline Report. A delay in the environmental process and Network design has led to a shortfall versus forecast in expenditures. | 0 | Sales Tax | 49-Sales tax will be incorporated into the expenditure detail at a future date. | 98 | 100- The Environmental process is complete. | 50 | 80-This category may not expend all that was budgeted as design of the network is near completion. | 95 | 80-Right of Way acquisition will be substantially complete by the end of Quarter 3, 2011. | 75 | 95-Permitting for the project will be close to completion by end of year 2011. Budgeted amounts may not be met, as minimal activity will be required next year. | 50 | 60-Site work continues as work towards completion of this metric will be completed by second quarter of 2012. | 9 | 80-Equipment Procurement will lag baseline projections as most equipment will be ordered and arriving late in 2011 or early in 2012. | 20 | 49-An aggressive Baseline projection and later than anticipated constructions start has created the variance in this metric. | 9 | 25-Baseline projections had indicated earlier arrival of equipment than is actually occurring. Equipment will be deployed upon arrival and slightly behind the procurement metric as we progress through the project time line. | 5 | 15- Network testing will commence once the Build is up and operational. As evidenced by the 5% forecast, some testing will occur in this period. | 2011-08-05 12:39 | 2011-08-05 12:39 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2011 | Q3 | Q3 - 2011 | 4062 | 3874 | FALSE | 30 | Baseline 62-LQ 20-The original Baseline projections called for over half of the project completed in first three quarters of year two of the project. Realistically, this was not attainable and current projections show us meeting Baseline at the end of year two. An adjusted project plan has been incorporated to include additional crews being added as necessitated by unforeseen circumstances. | 0 |  | 62-0-Sales tax will be implemented and segregated out at a future date. | 100 | 100-100-No Variance. | 80 | 80-50-No Variance. | 90 | 80-85-Exceeding Baseline. | 75 | 95-70-Permiting continues into the final year of the project with Baseline metrics met during quarter three of 2012. The permitting schedule was extended into year three to accomodate for the underground build section of the project. | 70 | 60-60-Exceeding Baseline. | 10 | 80-7- Original Baseline projections were inaccurate when depicting the timeline for Equipment Procurement. This process will continue into the final year of the project and lag Baseline until quarter two year three of the project. | 35 | 62-20-An aggressive initial start date from the Baseline has caused a lag in this metric. Projections now indicate meeting Baseline during the first half of 2012. Additional crews as well as favorable weather and conditions have allowed for expeditious construction. The current project plan anticipates requiring additional crews and completion on time. | 7 | 40-7-Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project as equipment necessary for the project is utilized closer towards the end of the project life cycle. The revised project plan has this incorporated to this new timeframe. | 0 | 25-0-Network testing will occur once equipment is connected to the network and services are turned up. Attaining this metric will occur sometime during the final phase of the project. This is included as part of a revised project plan. | 2011-11-16 11:51 | 2011-11-16 11:51 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2011 | Q4 | Q4 - 2011 | 4642 | 4286 | FALSE | 36 | Baseline-69-LQ 29 The original Baseline projections called for over half of the project completed in first three quarters of year two of the project. Realistically, this was not attainable and current projections show us meeting Baseline at the end of year two. An adjusted project plan has been incorporated to include additional crews being added as necessitated by unforeseen circumstances. | 10 |  | 69-0 Sales tax is being implemented into the project as a seperate tracking metric. | 100 | 100-100 No Variance. | 90 | 90-65 No Variance. | 90 | 90-90 No Variance. | 85 | 95-80 Permiting continues into the final year of the project with Baseline metrics met during quarter three of 2012. The permitting schedule was extended into year three to accomodate for the underground build section of the project. | 75 | 60-70 Exceeding Baseline. | 15 | 90-10 Original Baseline projections were inaccurate when depicting the timeline for Equipment Procurement. This process will continue into the final year of the project and lag Baseline until quarter two year three of the project. | 55 | 69-30 An aggressive initial start date from the Baseline has caused a lag in this metric. Projections now indicate meeting Baseline during the first half of 2012. Additional crews as well as favorable weather and conditions have allowed for expeditious construction. The current project plan anticipates requiring additional crews and completion on time. | 15 | 50-10 Equipment originally forecasted to be put in service will not be required until 2012. This metric will be attained during the final year of the project as equipment necessary for the project is utilized closer towards the end of the project life cycle. The revised project plan has this incorporated to this new timeframe. | 0 | 30-0 Network testing will occur once equipment is connected to the network and services are turned up. Attaining this metric will occur sometime during the final phase of the project. This is included as part of a revised project plan. | 2012-01-30 11:54 | 2012-01-30 11:54 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2012 | Q1 | Q1 - 2012 | 6114 | 5659 | FALSE | 45 | LQ 32 Baseline 87 By design the last and most costly phase of the project, the underground portion, will be completed in the last three quarters of 2012. Original Baseline projections did not account for this or the equipment purchases late in the project timeline. | 2 |  | 1-87 Sales tax will be incorporated as additional equipment is purchased and | 100 | 100-100 No Variation. | 80 | 70-90 Final design changes or completions will be left at the end of the second quartr of 2012. Minimal design work will remain that needs to be accomplished. | 98 | 95-90 Exceeding Baseline. | 95 | 90-95 No Variance. | 90 | 85-80 Exceeding Baseline. | 20 | 10-90 Equipment projections were inaccurate when depicting the timeline for equipment procurement. This process will continue throughout the 2012 calendar year and likely miss this metric until the final reporting period. | 60 | 45-87 Earlier projections had construction starting earlier than actually occurred. With the delays experienced along the way, the network build has ultimately been delayed and compressed into a shorter time frame. This metric will be met as we approach the final months of the project. | 15 | 10-60 Equipment deployment was originally forecasted to take place much earlier. Due to network and system designs, it wasn't necessary to deploy until the final year of the project time frame. This metric will be attained in the final months of the project. | 0 | 0-40 Network testing will occur once equipment is installed and connected to the network. Services will be offered once this is completed and is part of the revised plan. | 2012-05-15 17:16 | 2012-05-15 17:16 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2012 | Q2 | Q2 - 2012 | 6834 | 6043 | FALSE | 72 | LQ40-BL94 By design the last and most costly phase of the project, the underground build, is in full production now as we approach the quarter of the year 2012. | 1 | Sales Tax | 1-94 Sales tax will be incorporated as additional equipment is purchase | 100 | 100-100 No Variance. | 90 | 90-90 No Variance. | 100 | 98-90 No Variance. | 100 | 95-95 Exceeding Baseline | 95 | 90-90 Exceeding Baseline. | 75 | 40-90 Equipment procurement was intentionally delayed until the final year of the project life cycle. Purchases will not meet this metric until the final reporting quarter for this metric. | 80 | 70-94 Earlier projections had estimated an earlier start to construction, but a prolonged environmental process and fiber shipments has extended out the project completion rate. The aerial build will near completion this quarter as well as the make ready work. Underground construction will forge ahead with completion scheduled for the first quarter of 2013. | 40 | 15-70 Equipment orders placed are scheduled for arrival during the third and fourth quarters of 2012. Equipment will be installed upon arrival and as the network build allows. this metric will be attained in the first quarter of 2013. | 10 | 0-60 Network testing is scheduled to begin as soon as equipment is installed and is anticipated to reach Baseline projections in the fourth quarter of 2012. | 2012-08-02 10:30 | 2012-08-02 10:30 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2012 | Q3 | Q3 - 2012 | 8058 | 6735 | FALSE | 80 | LQ-65 BL-97 By design the last and most costly phase of the project, the underground build, is in full production now as we approach the final quarter of the year 2012. This metric will be attained in Q1 2013. | 1 | Taxes | 1-97 Sales tax will be incorporated as Equipment purchases are booked to the project. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 100-90 No Variance. | 100 | 98-100 No Variance. | 100 | 95-100 No Variance. | 81 | 40-95 Equipment procurement was intentionally delayed until the final year of the project life cycle. This metric will be attained in Q1 2013. | 90 | 70-97 Earlier projections had estimated an earlier start to construction, but a prolonged environmental process and fiber shipments has extended out the project completion rate. The aerial build will near completion this quarter as well as the make ready work. Underground construction will forge ahead with completion scheduled for the first quarter of 2013. | 75 | 70-80 Equipment orders placed are scheduled for arrival during the third and fourth quarters of 2012. Equipment will be installed upon arrival and as the network build allows. This metric will be attained in the first quarter of 2013. | 75 | 70-80 Network testing is scheduled to begin as soon as equipment is installed and is anticipated to reach Baseline projections in the first quarter of 2013. | 2012-11-26 17:52 | 2012-11-26 17:52 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2012 | Q4 | Q4 - 2012 | 8774 | 7567 | FALSE | 95 | LQ-90- BL-100 Lagging in expenditures for the final phase of the project as it is anticipated to hit this metric by the end of Q2 2013. | 1 | Sales Tax | 1-100 Sales tax has been included in the line item in which it pertains to in the above categories. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 100-100 No Variance. | 100 | 99-100 No Variance. | 100 | 98-100 No Variance. | 100 | 91-100 No Variance. | 90 | 85-100 The network build will continue as weather has hampered the underground construction phase this past quarter. It is anticipated to complete end of Q2 2013. | 80 | 65-100 Final equipment deployment is anticipated to be installed during the Q2 2013 timeframe. | 80 | 40-100 Final Network Testing will be completed as we progress through the remaining sections of the Network Build and as remaining equipment is installed. It is anticipated to complete this by the end of Q2 2013. | 2013-02-14 10:33 | 2013-02-14 10:33 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2013 | Q1 | Q1 - 2013 | 9842 | 8457 | FALSE | 98 | With the project extension now in place, the project is anticipated to complete construction well before the end of the third quarter. Final expenditures will be anticipated in quarter 3 of 2013. Closeout activities will be finalized during the fourth quarter of 2013. | 1 |  | 1-100 Sales tax has been included in the line item in which it pertains to in the above categories. | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 98 | 85-100 The network build will continue as weather has hampered the underground construction phase this past quarter. It is anticipated to complete all construction by the end of July. | 90 | 65-100 Final equipment deployment is anticipated to be installed during the Q2 2013 timeframe. | 60 | 40-100 Final Network Testing will be completed as we progress through the remaining sections of the Network Build and as remaining equipment is installed. It is anticipated to complete this by the end of Q2 2013. | 2013-05-21 10:02 | 2013-05-21 10:02 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2013 | Q2 | Q2 - 2013 | 10764 | 9047 | FALSE | 100 | No Variance. | 0 | N/A | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-27 14:21 | 2013-08-27 14:21 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570059 | 2013 | Q3 | Q3 - 2013 | 12080 | 10241 | FALSE | 100 | Project is completed. | 0 | N/A | N/A | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 100 | Project is completed. | 2014-04-25 16:49 | 2014-04-25 16:49 | 5560 | 5560 | Public Utility District of Pend Oreille County
NT10BIX5570060 | 2010 | Q3 | Q3 - 2010 | 324 | 1428 | FALSE | 13 | - | 0 |  | N/A | 100 | Completed and submitted. | 100 | - | 0 | N/A | 100 | - | 13 | - | 56 | - | 13 | - | 13 | - | 13 | - | 2010-11-16 10:29 | 2010-11-16 10:29 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2010 | Q4 | Q4 - 2010 | 1216 | 2247 | FALSE | 18 | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed & approved | 20 | Project was significantly delayed while waiting for FONSI approval | 30 | In Q4, our intention was to order and invoice all the equipment at once. In the 1st Q of 2011, the ordering of all equipment will continue as planned, but it will be invoiced and shipped only as needed, instead of being invoiced and shipped all at once. Therefore, only 30% will be completed next quarter. | 18 | Project was significantly delayed while waiting for FONSI approval | 13 | Project was significantly delayed while waiting for FONSI approval | 13 | Project was significantly delayed while waiting for FONSI approval | 2011-02-18 11:18 | 2011-02-18 11:18 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2011 | Q1 | Q1 - 2011 | 2012 | 2751 | FALSE | 35 | Project was significantly delayed while waiting for FONSI approval | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 40 | Project was significantly delayed while waiting for FONSI approval | 30 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 20 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 10 | Pine Telephone company plans to have 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 2011-05-13 13:35 | 2011-05-13 13:35 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2011 | Q2 | Q2 - 2011 | 3054 | 3284 | FALSE | 25 | The method of calculating next quarter's project completion is based on overall expenditures. Some payment terms with vendors will occur after the system is up and running which will show project completion to be lower than actual completion. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 75 | - | 30 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 25 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 15 | Pine Telephone Company has 80% of the equipment under contract but will be receiving much of the high dollar equipment as needed - instead of paying for and receiving it all up front and having it stored until needed. | 2011-08-12 15:33 | 2011-08-12 15:33 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2011 | Q3 | Q3 - 2011 | 3954 | 3815 | FALSE | 60 | - | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 90 | - | 65 | - | 60 | - | 45 | - | 40 | - | 2011-11-10 11:18 | 2011-11-10 11:18 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2011 | Q4 | Q4 - 2011 | 4968 | 4642 | FALSE | 74 | The reason for overall completion lagging behind milestone completion is because Pine Telephone Company will not pay equipment vendors until after it is up and running. | 0 | true | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 95 | - | 90 | - | 80 | - | 80 | - | 80 | - | 2012-02-13 12:20 | 2012-02-13 12:20 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2012 | Q1 | Q1 - 2012 | 5998 | 5598 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 90 | - | 95 | - | 90 | - | 80 | - | 2012-05-09 17:28 | 2012-05-09 17:28 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2012 | Q2 | Q2 - 2012 | 7064 | 6159 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Completed | 90 | - | 95 | - | 95 | - | 90 | - | 2012-08-14 16:23 | 2012-08-14 16:23 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2012 | Q3 | Q3 - 2012 | 7838 | 6623 | FALSE | 80 | Pine Telephone Company (PTC) expects to be complete, but is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Complete | 90 | - | 95 | - | 95 | - | 90 | - | 2012-11-13 09:48 | 2012-11-13 09:48 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2012 | Q4 | Q4 - 2012 | 8440 | 7144 | FALSE | 87 | Pine Telephone Company (PTC) is running under budget and is seeking permission to add new sites within the proposed funded service areas (PFSAs) to improve service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Complete | 0 | N/A | 100 | Completed and approved | 100 | Complete | 90 | N/A | 95 | N/A | 95 | N/A | 90 | N/A | 2013-01-30 11:57 | 2013-01-30 11:57 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2013 | Q1 | Q1 - 2013 | 9756 | 8412 | FALSE | 100 | Pine Telephone Company has just received approval to add new sites within the proposed funded service areas (PFSAs) for improved service. | 0 |  | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-05-16 09:33 | 2013-05-16 09:33 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570060 | 2013 | Q2 | Q2 - 2013 | 12048 | 10206 | FALSE | 100 | Completed | 0 | true | N/A | 100 | Completed and submitted | 100 | Completed | 0 | N/A | 100 | Completed and approved | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-04-18 13:22 | 2014-04-18 13:22 | 5564 | 5564 | Pine Telephone Company, Inc.
NT10BIX5570062 | 2010 | Q3 | Q3 - 2010 | 460 | 1496 | FALSE | 30 | N/A | 30 |  | Outreach to local libraries and other anchor institutions | 100 | N/A | 30 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 | N/A | 20 | N/A | 0 | N/A | 2010-11-30 15:58 | 2010-11-30 15:58 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2010 | Q4 | Q4 - 2010 | 1108 | 2147 | FALSE | 60 | Will complete network design, rights of way, permitting, and equipment procurement. | 30 | Library outreach | Will continue library outreach and RFP responses. | 100 | N/A | 100 | Will finalize tower site logistics. | 100 | Will determine and request permits for rights of way. | 100 | Will request necessary permits. | 70 | Will finalize tower sites for construction. | 100 | Will order all equipment necessary for deployment. | 30 | Will commence network build. | 30 | Will commence equipment deployment. | 0 | N/A | 2011-02-11 17:44 | 2011-02-11 17:44 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2011 | Q1 | Q1 - 2011 | 2394 | 2942 | FALSE | 1 | Previous Quarter miscalculated | 30 |  | Will continue library outreach and RFP reponse | 100 | N/A | 100 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-05-30 22:26 | 2011-05-30 22:26 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2011 | Q2 | Q2 - 2011 | 3104 | 3309 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | No Variance from Baseline | 35 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-08-15 21:57 | 2011-08-15 21:57 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2011 | Q3 | Q3 - 2011 | 4322 | 4011 | FALSE | 1 | Asset Sale in process | 35 |  | Project on hold until asset sale completed | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | N/A | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 0 | Project on hold until asset sale completed | 2011-11-29 15:23 | 2011-11-29 15:23 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2011 | Q4 | Q4 - 2011 | 5334 | 5007 | FALSE | 1 | Project on hold pending progress review. | 35 |  | Project on hold pending progress review. | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | N/A | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 0 | Project on hold pending progress review. | 2012-02-28 09:01 | 2012-02-28 09:01 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570062 | 2012 | Q1 | Q1 - 2012 | 5716 | 5455 | FALSE | 1 | Project has been terminated | 35 |  | Project has been terminated | 100 | N/A | 100 | N/A | 35 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | N/A | 0 | Project has been terminated | 0 | Project has been terminated | 0 | Project has been terminated | 2012-04-29 21:52 | 2012-04-29 21:52 | 5559 | 5559 | DigitalBridge Communications Corp.
NT10BIX5570065 | 2010 | Q3 | Q3 - 2010 | 160 | 1346 | FALSE | 19 | No variance | 0 | N/A | N/A | 60 | No variance | 100 | No variance | 0 | N/A | 25 | No variance | 0 | No variance | 80 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2010-10-27 09:05 | 2010-10-27 09:05 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2010 | Q4 | Q4 - 2010 | 1320 | 2344 | FALSE | 35 | No variance | 0 | N/A | N/A | 0 | No variance | 84 | No variance | 0 | N/A | 0 | No variance | 48 | No variance | 100 | No variance | 0 | No variance | 6 | No variance | 39 | No variance | 2011-02-23 07:27 | 2011-02-23 07:27 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2011 | Q1 | Q1 - 2011 | 1542 | 2488 | FALSE | 57 | No variance | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | N/A | 0 | No variance | 66 | No variance | 100 | No variance | 44 | No variance | 10 | No variance | 39 | No variance | 2011-04-27 16:44 | 2011-04-27 16:44 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2011 | Q2 | Q2 - 2011 | 3358 | 3442 | FALSE | 32 | The overall project percentage completion has changed due to the reasons stated below. | 0 |  | N/A | 100 | No variance | 32 | There is a variance in this category for next quarter. Airspan, the WiMax vendor procured by BIT for this project has created a propagation map and has completed the site surveys for all of the 35 towers. During the surveys it became apparent that some of the sites are structurally inadequate. BIT is therefore, in the process of changing these five (5) tower locations and securing approval for this change. | 0 | N/A | 0 | There is a variance in this category for next quarter. BIT is currently working on the permits and approvals for the tower sites. The site surveys have been completed by our vendor, Airspan, and BIT has finalized the sites for the WiMax equipment. Until the sites were cleared after the site surveys BIT did not want to begin the permitting process. | 0 | There is a variance in this category for next quarter. BIT is currently working on the site preparation for the tower sites. The site surveys have been completed by our vendor, Airspan, and BIT has finalized the sites for the WiMax equipment. Until the sites were cleared after the site surveys BIT did not want to begin the site preparation. | 100 | No variance | 16 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 1 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 3 | The equipment BIT originally anticipated receiving in quarter 3, 2011 will be sent to BIT's facilities in quarter 4, 2011. Therefore, the percentage completion for this category has been changed for quarter 4, 2011. | 2011-08-29 16:26 | 2011-08-29 16:26 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2011 | Q3 | Q3 - 2011 | 4090 | 3888 | FALSE | 42 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance | 22 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This has not been completed due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT has submitted a request for approval of the sites identified as alternates, but has not yet received approval from NTIA from the Environmental Division. As soon as approval for the alternate sites is granted work will resume on the propagation maps. BIT anticipates receiving approval during this quarter, but the work on the propagation map has been postponed until the approval is obtained. Therefore, the map completion is scheduled for the first quarter in 2012. The percent complete is based on total dollars spent, and therefore won't increase until the maps have been updated. | 0 | N/A | 64 | There is only a slight variance anticipated for construction permits, but this category is expected to meet the baseline projections for quarter one 2012. | 48 | The percent complete per category is based on total dollars spent. However, the billing of the site preparation work will be billed after the work has been completed. BIT anticipates receiving invoices for these services late next quarter, which will be paid early the following quarter. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 100 | No variance | 47 | Since BIT is waiting for environmental approval on the towers that are being switched out this category will be slightly behind next quarter, but will catch up by the first quarter in 2012. BIT has already discussed an expedited process for the network build-out with their contractors, who, in turn, have identified multiple crews that can be pulled in to expedite the build process. | 2 | The percent complete per category is based on total dollars spent. This category is comprised of project management services as well as training, maintenance and installation services. Most of this is invoiced after each of the sites has been commissioned and tested. Since BIT's build-out will begin during this quarter, expenses for this category are not anticipated until the first quarter of 2012. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 6 | The percent complete per category is based on total dollars spent. Since BIT's build-out will begin during this quarter, expenses for this category are not anticipated until the first quarter of 2012. Therefore, the category will not change next quarter since the dollars will not be spent until the first quarter of 2012. | 2011-11-16 16:15 | 2011-11-18 13:37 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2011 | Q4 | Q4 - 2011 | 5180 | 4843 | FALSE | 67 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has not been complete due to the fact that some of the towers are structurally inadequate to hold the WiMax equipment. BIT submitted a request for approval of the sites identified as alternates, but did not receive approval through the Environmental Assessment process until December 27, 2011. Now that the alternative sites are approved work will continue on the propagation maps. Additionally, the As Built drawings will be prepared once each tower has been completed. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 72 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. | 30 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. | 6 | BIT anticipates completing 24 of the total 35 towers by the end of next quarter. Network testing will begin as each tower is completed. | 2012-02-21 17:34 | 2012-02-21 17:34 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2012 | Q1 | Q1 - 2012 | 5962 | 5580 | FALSE | 79 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 75 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. | 89 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. | 54 | Buggs Island Telephone has completed the installation of WiMax equipment on 24 of the 35 towers. The remaining 10 sites will be constructed starting in quarter 3 of 2012. Once that equipment is installed testing will begin on the last 10 sites. | 2012-05-08 12:46 | 2012-05-08 12:46 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2012 | Q2 | Q2 - 2012 | 7118 | 6186 | FALSE | 80 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 45 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 80 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 6 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter four, 2012 equipment will be installed on the remaining 11 sites. | 2012-08-17 16:13 | 2012-08-17 16:13 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2012 | Q3 | Q3 - 2012 | 7342 | 6304 | FALSE | 80 | The projections for percent completion of the overall project are based on expenditures for the below categories. Please see explanations for differences per category below. | 0 | N/A | N/A | 100 | No variance. | 63 | The network has been designed, however, Airspan, the WiMax equipment vendor, is working on a detailed propagation map. This map has been completed for the portion of the network that has been deployed. These maps will not be complete until the remaining sites are installed at the end of 2012 and will be billed together at that time. Until it is invoiced and paid there will be a variance for this category. The projections for percent completion on the Baseline Report and here are based on total dollars spent at the end of the quarter. | 0 | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 78 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 79 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 54 | Buggs Island Telephone completed the installation of WiMax equipment on 24 of the 35 towers at the end of quarter one, 2012. The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012, at which time the 24 site system will be ready for a commercial launch and in quarter one, 2013 equipment will be installed on the remaining 11 sites. | 2012-10-23 08:55 | 2012-10-23 08:55 | 5566 | 5566 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2012 | Q4 | Q4 - 2012 | 9092 | 7864 | FALSE | 80 | Projection of commercially ready to market service and final build-out of the additional 11 sites is undetermined. | 0 |  | N/A | 100 | No Variance | 80 | 3.65 network will be tested and accepted and 700 network will be re-designed. | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 80 | 3.65 network build completed and 700 network optimized. | 80 | 3.65 network build completed and 700 network optimized. | 56 | 3.65 network virtually tested and 700 network being re-configured. | 2013-02-28 15:45 | 2013-02-28 15:45 | 5565 | 5565 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2013 | Q1 | Q1 - 2013 | 10070 | 8593 | FALSE | 82 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in Buggs Island Telephone, in coordination with the grant funding agencies, to abandon the WiMAX system and convert to a compatible LTE system if approved by NTIA. Due to limited grant funds remaining, the LTE build-out will cover a 5-county service area versus the original plans to cover a 15-county service area. Construction is projected to begin in Q3 of 2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. The 3.65 network, consisting of six towers, is fully operational with testing and commercial launch to be implemented in Q2 of 2013. | 58 |  | The costs included in this category include 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The remaining funds in this category will be expended as the project proceeds over the next 6 to 8 months and these activities are implemented. | 100 | The Environmental Assessment is complete. | 77 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the 5-county service area if approved by NTIA. | 0 | Not Applicable | 100 | All construction permits have been acquired for the project. | 100 | It is expected that all costs associated with tower modifications to install the WiMAX equipment will be fully paid in Q2 of 2013. | 85 | Activities associated with the procurement of LTE equipment will be initiated in Q2 of 2013. | 0 | Not Applicable | 84 | The purchase and installation of LTE equipment will begin in Q3 of 2013. | 26 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system if approved by NTIA. The 3.65 testing resulted in a successfully installed system that can be commercially launched. Additional costs are expected in this category to cover costs associated with the WiMAX and 3.65 testing and upcoming LTE testing once deployed. | 2013-06-21 14:50 | 2013-06-21 14:50 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2013 | Q2 | Q2 - 2013 | 10784 | 9061 | FALSE | 83 | WiMAX equipment was installed on 24 tower sites and tested. Extreme interference issues with neighboring companies using LTE technology resulted in Buggs Island Telephone, pending grant funding agency approval, developing plans to abandon the WiMAX system and converting to a compatible LTE system. Due to limited grant funds remaining, the LTE build-out will cover a 5-county service area versus the original plan to cover a 15-county service area. Construction is projected to begin in Q3-2013. The project completion date was extended as a result of WiMAX interference and the need for additional time to deploy LTE. Costs to date reflect actual expenses incurred in constructing the WiMAX and 3.65 networks. | 80 |  | The costs included in this category include 1) Admin and Legal, 2) Engineering -Project Management, 3) Project Inspection, 4) Monthly Tower Lease Payments, and 5) Monthly Backhaul Fees. The remaining funds in this category will be expended as the project proceeds over the next 6 months and these activities are implemented. | 100 | The Environmental Assessment is complete | 81 | The 700 network is being re-designed due to interference issues. The 3.65 network is complete. The remaining funds will be used to design the LTE build-out in the reduced 5-county service area pending NTIA approval. | 0 | Not Applicable | 100 | All construction permits have been acquired for this project. | 100 | No additional site work is anticipated for this project. | 90 | Activities associated with the procurement of LTE equipment have been initiated and a vendor will be selected after receiving authorization from NTIA to proceed. | 0 | Not Applicable | 83 | The purchase and installation of LTE equipment will begin in Q3-2013. | 70 | Network testing was implemented on the WiMAX and 3.65 network. As noted previously, the WiMAX system will be abandoned and replaced with a LTE system, contingent upon NTIA approval. The 3.65 testing resulted in a successfully installed system that has been commercially launched. Additional costs are expected in this category to cover expenses associated with the proposed LTE testing once deployed. | 2013-08-28 10:00 | 2013-08-28 10:00 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2013 | Q3 | Q3 - 2013 | 11336 | 9468 | FALSE | 86 | LTE contracts will be signed with vendors and the equipment order will be placed. The deployment of LTE equipment is projected to begin in Q1 2014 and will not be commercially launched until Q2 or Q3 2014. Decommissioning the WiMAX equipment from the terminated 24 tower sites continue and will be completed in Q4 2013. WiMAX equipment will continue to be put on the market for sale by the consignment company. | 58 | Legal/Admin/Tower Backhaul/Tower Lease/ Engineering Manaagament | Next quarter costs include the removal of WiMAX equipment, legal fees associated with contract reviews, ongoing monthly backhaul & lease fees, and general administrative and engineering activities. | 100 | The Environmental Assessment is complete. | 81 | The remaining funds will be used to design the LTE build-out in the 5-county service area. | 0 | Not Applicable | 99 | Additional permits will need to obtained for the installation of LTE equipment. | 100 | No additional site work is anticipated for this project. | 98 | The percentage increased due to the costs associated with procuring an LTE equipment vendor. | 0 | Not Applicable | 89 | Costs for LTE equipment is expected to occur in Q4-2013, thus the slight increase in percent complete. | 70 | Additional costs are expected in this category to cover expenses associated with LTE testing once deployed. Testing should begin in Q2 2014. | 2013-11-21 16:49 | 2013-11-21 16:49 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2013 | Q4 | Q4 - 2013 | 11794 | 9963 | FALSE | 87 | BIT originally projected that the deployment of the LTE network would be 100% completed by Q1 2014 but lengthy equipment vendor procurement and contract negotiations delayed the build-out time line. The deployment of LTE equipment is now projected to begin in Q2 2014. Because of this delay BIT's projection of signing up and installing beta testers will not begin until early Q3 2014 and will not be commercially launched until late Q3 2014. BIT will start marketing efforts in Q1 2014 in order to do customer pre-sales. | 54 |  | Next quarter costs include the removal of WiMAX equipment from the 10 tower sites, ongoing monthly back haul & lease fees, and general administration, management, and inspection fees. | 100 | BIT anticipates an environmental assessment for a new tower site that will be needed to replace one of the ten existing sites. Q4 2013 showed remaining funds in this category. | 83 | Engineering design fees continue as LTE build-out proceeds in the 5-county service area. | 0 | Not Applicable | 99 | Additional permits will need to obtained for the installation of LTE equipment. | 100 | Actual site preparation was 100% complete by the end of Q4 2013. BIT will have to do a structural analysis for a new tower site that will be needed to replace one of the ten existing sites. No funds remain in this category but a budget modification will be submitted during Q1 2014 where funds will be reallocated to this category. | 90 | Equipment procurement is complete. A budget amendment will be submitted prior to the next reporting period. | 0 | Not Applicable | 90 | Costs for LTE equipment purchase and deployment is expected to occur in Q1-2014. | 70 | Additional costs are expected in this category to cover expenses associated with LTE testing once deployed. | 2014-02-05 13:35 | 2014-02-05 13:35 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2014 | Q1 | Q1 - 2014 | 12174 | 10357 | FALSE | 91 | No Variance | 79 |  | No Variance | 100 | No Variance | 99 | No Variance | 0 | Not Applicable | 97 | No Variance | 100 | No Variance | 82 | No Variance | 0 | Not Applicable | 92 | No Variance | 97 | No Variance | 2014-05-07 15:03 | 2014-05-07 15:03 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2014 | Q2 | Q2 - 2014 | 12336 | 10507 | FALSE | 100 | No Variance | 100 |  | No Variance | 100 | No Variance | 100 | No Variance | 0 | Not Applicable | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | Not Applicable | 100 | No Variance | 100 | No Variance | 2014-07-29 12:14 | 2014-07-29 12:14 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2014 | Q3 | Q3 - 2014 | 12582 | 10822 | FALSE | 96 | BIT was approved for a no-cost nine month extension to install additional equipment on three (Blackstone, Clarksville, South Brunswick) of the ten towers to expand signal strength to additional customers located in the tower service area and enable BIT additional time to capture and install the 1,600 customers that were proposed being served by the end of the grant period in the approved Revised BIT Broadband Plan dated 9/13. | 89 | Community Outreach/Tower Leases/Backhaul | The 9-month extension will allow BIT to use remaining funds to enable BIT additional time to capture and install the 1,600 customers that were proposed being served by the end of the grant period in the approved Revised BIT Broadband Plan dated 9/13. | 100 | No Variance | 99 | The 9-month extension will allow BIT to use remaining funds to install additional equipment on three towers as approved by NTIA. | 0 | Not Applicable | 97 | The 9-month extension will allow BIT to use remaining funds to install additional equipment on three towers as approved by NTIA. | 100 | No Variance | 85 | The 9-month extension will allow BIT to use remaining funds to install additional equipment on three towers as approved by NTIA. | 0 | Not Applicable | 97 | The 9-month extension will allow BIT to use remaining funds to install additional equipment on three towers as approved by NTIA. | 97 | The 9-month extension will allow BIT to use remaining funds to install additional equipment on three towers as approved by NTIA. | 2014-11-05 10:14 | 2014-11-05 10:14 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2014 | Q4 | Q4 - 2014 | 12740 | 11074 | FALSE | 97 | A no-cost nine month extension request was submitted by BIT to complete tower optimization and commercial deployment of the Alberta Tower, to install additional equipment on three of the ten towers to expand signal strength to additional customers located in the tower service area and to capture and install the 1,600 customers as proposed in the Revised Broadband Plan dated 9/2013; the extension request has not been formally approved by the Grants Office. | 91 |  | The budget items included in this category are: 1) Admin and Legal, 2) Demolition & Removal, 3) Project Inspection, 4) Monthly Tower Lease Payments and Back Rent Settlements, 5) Monthly Backhaul Fees, 6) Community Outreach, and 7) Fiber (In-Kind Match). | 100 | No Variance | 100 | No Variance | 0 | Not Applicable | 97 | No Variance | 100 | Not Applicable | 85 | No Variance | 0 | Not Applicable | 98 | No Variance | 97 | No Variance | 2015-03-10 14:13 | 2015-03-10 14:13 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2015 | Q1 | Q1 - 2015 | 12828 | 11207 | FALSE | 99 | No Variance | 99 |  | No Variance | 100 | No Variance | 100 | No Variance | 0 | Not Applicable | 97 | No Variance | 100 | Not Applicable | 86 | No Variance | 0 | Not Applicable | 100 | No Variance | 100 | No Variance | 2015-05-18 10:53 | 2015-05-18 10:53 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570065 | 2015 | Q2 | Q2 - 2015 | 12910 | 11290 | FALSE | 99 | No Variance | 97 |  | No Variance | 100 | No Variance | 100 | No Variance | 0 | Not Applicable | 97 | No Variance | 100 | No Variance | 86 | No Variance | 0 | Not Applicable | 100 | No Variance | 100 | No Variance | 42264.5353 | 42264.5353 | 7685 | 7685 | Buggs Island Telephone Cooperative
NT10BIX5570066 | 2010 | Q4 | Q4 - 2010 | 1128 | 2167 | FALSE | 6 | No variance | 100 | Grant Prep | No variance | 100 | No variance | 23 | No variance | 15 | No variance | 100 | No variance | 7 | No variance | 20 | No variance | 4 | No variance | 15 | No variance | 1 | No variance | 2011-02-14 09:54 | 2011-02-14 09:59 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2011 | Q1 | Q1 - 2011 | 2168 | 2829 | FALSE | 33 | This percent complete is based on weighted amounts for each category, as shown in BVU's baseline report. | 100 | Grant Preparation | N/A | 100 | N/A | 30 | Lag during previous quarter | 65 | Based on changes in engineering, BVU does not expect that any PoP locations will have begun to be constructed by the end of Q2-2011; thus, this category will not change from the current reporting quarter. | 30 | All will be applied for, but not all will be received based on standard wait time and agency delays. National Forest Permits will have begun biological studies, and will hopefully have necessary studies completed by 6/30/2011. As noted in the current quarter's percentages, this category has decreased in percentage complete because of the way BVU is now tracking it. BVU had been tracking by activities complete; however, this does not match with expended dollars. To account for the difference in the two, BVU has decided to allocate 5% of total engineering dollars spent to permitting, since actual work performed by the engineering firm cannot be tracked by hours specifically to permitting. | 32 | Allocation of 0.5% of Construction dollars to Site Prep. | 50 | Lag during previous quarter. Since all money during the previous quarter was in-kind money, progression of this category will be at a slower pace from here on out as NTIA and BVU match funds are charged to it. | 32 | N/A | 46 | Lag in previous quarter. Based on changes in engineering, BVU does not expect that any PoP locations will have begun to be constructed by the end of Q2-2011. | 2 | Based on review of the schedule changes in the project, BVU expects Network Testing to fall behind Network Build by a little more than originally anticipated. | 2011-05-19 11:35 | 2011-05-19 11:35 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2011 | Q2 | Q2 - 2011 | 3402 | 3464 | FALSE | 45 | BVU Authority's project modifications are currently under review by NTIA. While current quarter percentages complete track by the amounts in each budget category as of 6/30/2011, the amounts in some of those categories will change for next quarter. Therefore, our projections for next quarter use the modified amounts. Please see attached baseline tracking spreadsheet for more info on current and projected percent(s) complete. | 98 |  | Since BVU cannot incur any more dollars to grant preparation, this category will remain at 98% complete, unless BVU later decides to transfer its remaining dollars to EA/mapping/Davis Bacon compliance. | 82 | This category will experience an increase in $5,000 budgeted, so the percentage complete will decrease, even after new charges incurred. This category will have $18,281 in it after project modifications are approved. However, since this category was approved at 100% federally-funded, we cannot add in another $5,000 at the same breakdown. Therefore, everything expended in this category after 6/30/2011 will follow the 80% federal/20% match breakdown like the rest of the budget, to keep federal and match dollars the same for the overall budget. | 47 | While this category is slightly below baseline predictions, it is expected to incur about the same amount as it did in Q2-2011. It will still be on track, as its percentage complete is still ahead of construction. This category will have $1,325,417 in it after project modifications are approved. | 68 | This category will not incur any expenses because PoP construction is not expected to start by the end of Q3-2011. However, since the amount in the category will have changed to a lower amount, the planned percentage complete increases. This category will have $938,279 in it after project modifications are approved. | 47 | This category is an allocated 5% of OMB category 4, and will incur proportionately the same amount as Network Design. This category will have $69,759 in it after project modifications are approved. | 45 | This category is an allocated 0.5% of OMB category 9, and will incur proportionately the same amount as Network Build. This category will have $156,832 in it after project modifications are approved. | 52 | After project modifications are approved in July 2011, PoP engineering should begin, as well as equipment procurement. This category will have $908,616 in it after project modifications are approved. | 45 | Network build will continue to remain ahead of schedule in Q3-2011. This category will have $31,209,666 in it after project modifications are approved. | 49 | As of the end of Q3-2011, PoP construction is not expected to have started. However, since project modifications decrease the amount in this category, the percentage complete will still increase. This category will have $908,616 in it after project modifications are approved. | 2 | Network testing will begin in Q3-2011. | 2011-08-31 17:38 | 2011-08-31 17:38 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2011 | Q3 | Q3 - 2011 | 4332 | 4021 | FALSE | 64 | Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars.Percentage shown takes this into account. | 100 | Grant Prep | Completed. | 100 | Complete | 58 | Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars.Percentage shown takes this into account. | 70 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 58 | This category is an allocated 5% of OMB category 4, and will incur proportionately the same amount as Network Design. | 65 | This category is an allocated 0.5% of OMB category 9, and will incur proportionately the same amount as Network Build. Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars. Percentage shown takes this into account. | 60 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 65 | Network build experienced slow down, but is still on original schedule. Projections for next quarter contain the modified in-kind amounts mentioned previously. This will jump the percentages due to the influx of in-kind dollars. Percentage shown takes this into account. | 60 | No actual dollars are expected to be expended to this category during next period, but as noted in last quarter's report, the percentage was expected to increase slightly due to budget changes discussed previously. | 0 | Network testing will begin in Q4-2011. | 2011-11-30 12:05 | 2011-11-30 12:05 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2011 | Q4 | Q4 - 2011 | 5036 | 4708 | FALSE | 55 | Percentage reflects change to in-kind utilization reporting. Also, plan is to bring on more construction resources over the next two quarters to hit the 2/3 complete goal at end of second year. | 100 | Grant Prep | Completed | 100 | Complete. | 75 | Expect that 3/4 of the routes will be fully engineered by end of quarter. | 75 | This category is an allocated in relation to Network Design, and will incur proportionately. | 75 | This category is an allocated 0.5% of Network Design, and will incur proportionately. | 51 | This category is an allocated 0.5% of Network Build, and will incur proportionately. | 23 | As routes are being completed and lit during this quarter, equipment will start to be procured and deployed, as well as, in-kind utilization per miles build out. | 51 | Plan is to bring on more construction resources over the next two quarters to hit the 2/3 complete goal at end of second year. | 3 | First route planned to be lit in quarter | 3 | First route planned to be lit in quarter | 2012-02-15 15:07 | 2012-02-15 15:07 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2012 | Q1 | Q1 - 2012 | 5940 | 5569 | FALSE | 59 | Projected an estimated 55 miles to be build out. | 100 | Grant Prep | Complete | 100 | Complete. | 81 | All routes have had preliminary designs completed. Will continue to finalize routes. | 77 | Based on mileage completed. | 81 | Correlated with Network Design so percentage will concur with that category. | 59 | Correlated with Network Build so percentage will concur with that category. | 49 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that equipment based procurement and deployment will increase significantly. | 59 | Slightly ahead of schedule. | 49 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that equipment based procurement and deployment will increase significantly. | 22 | Expect multiple routes to be completed and lit in 2012-Q2 with an effect that network testing will increase significantly. | 2012-05-07 11:15 | 2012-05-07 11:15 | 5930 | 5930 | BVU Authority
NT10BIX5570066 | 2012 | Q2 | Q2 - 2012 | 6958 | 6106 | FALSE | 81 | Project an estimated 49 miles to be build out. | 100 | Grant management | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 79 | Based on mileage completed. | 98 | Based on expensed vs project dollars. Has been done in conjunction with Network Design on assumption was that permits and easements would be received as design built. This is no longer true due to easement issues. | 79 | Correlated with Network Build so percentage will concur with that category. | 57 | Expect 17 routes to be completed and lit by end of 2012-Q3. | 79 | Slightly ahead of baseline schedule. Baseline estimated at 78% at end of Q3-2012 | 57 | Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 34 | Expect multiple routes to be completed and lit in 2012-Q3 with an effect that network testing will increase significantly. | 2012-08-09 10:41 | 2012-08-09 10:42 | 7556 | 7556 | BVU Authority
NT10BIX5570066 | 2012 | Q3 | Q3 - 2012 | 8030 | 6721 | FALSE | 89 | Project an estimated 40 miles to be build out. | 100 | Grant Management | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 89 | Based on mileage completed. | 95 | We have changed tracking method of this category from expensed versus projected dollars to actual tracking of known outstanding easement and permits versus total needed easements and permits. Original assumption was that easements and permits would be received during engineering phase did not hold, thus the need to change tracking method. | 87 | Correlated with Network Build so percentage will concur with that category. | 80 | Expect 17 routes to be completed and lit by end of 2012-Q4. | 87 | Basically in line with baseline schedule. Baseline estimated at 88% at end of Q4-2012. As noted previously, BVU can bring in additional crews when easements obtained. | 80 | Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 47 | Expect multiple routes to be completed and lit in 2012-Q4 with an effect that network testing will increase significantly. | 2012-11-26 11:34 | 2012-11-26 11:34 | 7556 | 7556 | BVU Authority
NT10BIX5570066 | 2012 | Q4 | Q4 - 2012 | 8700 | 7509 | FALSE | 93 | Note: Change in calculation method per request from Federal Program Officer. Was based on mileage, but now based on expensed/in-kind versus project dollars. | 100 | Grant Prep | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete unless issues found during built out which may cause a very minor adjustment. | 91 | Note: Change in calculation method per request from Federal Program Officer. Was based on mileage, but now based on construction expensed/in-kind versus project dollars. | 100 | Expect all permits and "quick-take" condemnations completed by end of quarter. | 91 | Based on expensed/in-kind versus project dollars for construction. Site prep is allocated of 0.5% of construction dollars, so projection is consistent with [Network Build] percentage. | 80 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Deployment], so percentage is consistent with [Equipment Deployment] percentage. | 91 | Based on expensed/in-kind versus project dollars for construction. Network Build is allocated of 0.5% of construction dollars, so projection is consistent with [Site Preparation] percentage. | 80 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. | 65 | Based on expensed versus project dollars. | 2013-02-11 12:05 | 2013-02-11 12:05 | 7556 | 7556 | BVU Authority
NT10BIX5570066 | 2013 | Q1 | Q1 - 2013 | 9830 | 8451 | FALSE | 100 | Expect project to be complete except for any award closing tasks. | 100 | Grant prep | Complete. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 2013-05-20 14:32 | 2013-05-20 14:32 | 7556 | 7556 | BVU Authority
NT10BIX5570066 | 2013 | Q2 | Q2 - 2013 | 10650 | 8985 | FALSE | 100 | Expect project to be complete except for any award closing tasks. | 100 | Grant Preparation | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 2013-08-20 10:16 | 2013-08-20 10:16 | 7556 | 7556 | BVU Authority
NT10BIX5570066 | 2013 | Q3 | Q3 - 2013 | 12288 | 10459 | FALSE | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Grant Preparation | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 2014-06-24 10:52 | 2014-06-24 10:52 | 5759 | 5759 | BVU Authority
NT10BIX5570067 | 2010 | Q4 | Q4 - 2010 | 1254 | 2284 | FALSE | 27 | Based on overall budget vs planned spend through 3/31/2011. Almost all equipment and materials will have been received by quarter end (>$13mm) | 0 |  | N/A | 100 | The EA will be completed with the FONSI. | 95 | % complete as a % of effort. Estimate to complete is based on initial design being completed after EA approval, and additional ongoing design activities continue as network is built. Most of the matching funds in this category will be expended on the ongoing design optimization activities. | 0 | We do not foresee the need for any new Rights of Way in Q2-2011, as we will just be starting construction. It was assumed for planning purposes some new rights of way might be needed. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We do still anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 71 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. | 11 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q2 2011. | 42 | Percent complete based on: fed funding - receipt of additional equipment shipments from PO's placed in December (for equipment) and January (for fiber); and matching funding from payments by sub-recipients in preparation of their network build outs. | 11 | Percent complete based on ramp up of make ready on aerial routes post-FONSI; commencement of underground where plausible on underground routes. Of 13 overall ring segments we are planning to start work on the top five (5) rings. | 17 | Percent complete based on work at existing core network sites; post-FONSI when deployment can begin. Less than 1% of total project. Plus matching funds spent by sub-recipients on equipment installation. | 0 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 3/31/2011. | 2011-02-20 22:33 | 2011-02-20 22:33 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2011 | Q1 | Q1 - 2011 | 1942 | 2716 | FALSE | 27 | Based on overall budget vs planned spend through 6/30/2011. Almost all equipment and materials will have been received by quarter end (>$13mm). This % complete is based on anticipated spend versus total project funds; it is behind plan, due to elongated payment terms for equipment, fiber, and construction materials. | 0 |  | N/A | 100 | Complete | 100 | The % complete is expressed as a % of budget consumed. | 0 | We do not foresee the need for any new Rights of Way in Q2-2011, as we will just be starting construction. It was assumed for planning purposes some new rights of way might be needed. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We do still anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 50 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. We will still be behind the baseline for the project, as the utility companies have been slow to respond to requests, due to the volume of requests they are dealing with from the federal programs and other requests. NOTE: this is an area where, given current turn around times and fees, we anticipate being significantly over budgeted amounts for "make ready" work. | 60 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q2 2011. | 80 | Percent complete based on: fed funding - receipt of additional equipment shipments from PO's placed in December (for equipment) and January (for fiber); and matching funding from payments by sub-recipients in preparation of their network build outs. | 11 | Percent complete based on ramp up of make ready on aerial routes post-FONSI; commencement of underground where plausible on underground routes. Of 13 overall ring segments we are planning to start work on the top five (5) rings. | 17 | Percent complete is based on percent of budget available vs anticipated spending in the quarter. We anticipate being ahead of baseline in upgrading our exsiting hub sites. | 0 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 6/30/2011, as we will push to complete "make ready" and permitting while ramping up construction | 2011-05-11 13:15 | 2011-05-11 13:15 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2011 | Q2 | Q2 - 2011 | 3186 | 3353 | FALSE | 56 | Based on overall budget vs planned spend through 9/30/2011 at 56% complete as part of total budget (fed and match), with baseline at 48%. | 0 |  | n/a | 100 | complete | 95 | designs will be completed. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We recognize we may need one or two additional new ROW's. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. | 80 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. We will still be behind the baseline for the project - 70% vs 90% baseline - as the utility companies have been slow to respond to requests, due to the volume of requests they are dealing with from the federal programs and other requests. NOTE: this is an area where, given current turn around times and fees, we anticipate being significantly over budgeted amounts for "make ready" work. | 20 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q3 2011. | 92 | Percent complete based on fed funding matching funding from payments by sub-recipients in preparation of their network build outs. | 21 | Percent complete estimated at 12.8% (vs baseline of 15%). | 9 | Percent complete is based on percent of budget available vs anticipated spending in the quarter. We anticipate being ahead of baseline in upgrading our exsiting hub sites (18% vs 10% in baseline) | 6 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 6/30/2011, as we will push to complete "make ready" and permitting while ramping up construction. | 2011-08-18 08:43 | 2011-08-18 08:43 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2011 | Q3 | Q3 - 2011 | 4130 | 3911 | FALSE | 58 | Percentage complete is based on total project budget expended, including federal and matching portions. We are aggressively pursuing make ready and other permitting on over 70% of the network in program scope. We are pushing to have "make ready" paid for and in progress by December 31, 2011, allowing us plenty of time in Q1 and Q2 to finish those ring segments. | 100 | miscellaneous items | Additional planned incidental expenses will be less that 0.5% in total | 100 | complete. Incidental EA costs are incurred as our Special Award Conditions (SACs) are enforced for Environmental Protection Measures to which we committed. | 100 | Complete. Incidental design costs are incurred as route optimization continues during the build phase. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We recognize we may need one or two additional new ROW's. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. | 80 | We are aggressively pursuing make ready and other permitting on over 70% of the network in program scope. We are pushing to have "make ready" paid for and in progress by December 31, 2011, allowing us plenty of time in Q1 and Q2 to finish those ring segments. | 20 | On plan based on location preparations. We are under budget, as we've only had to spend 20% of budgeted funds in order to get sites prepared to move into. I anticipate the remaining budget, however, may be needed for several new locations yet to be identified. With respect to our 2/3 milestone in June, 2013, we have updated all locations required to support that 2/3 build out, so we are on plan but under budget. | 95 | We anticipate having almost all equipment in-house by quarter-end / year-end for the major backbones and laterals for the program. | 9 | We anticipate build phase will continue to expand as pathways are cleared for "make ready". | 70 | We anticipate being able to finish up to 70% of the Equipment Deployment phase, as fiber is run and terminated in our hub sites. This is dependent on the Network Build, however, which is dependent on the Construction Permits for "make ready". | 32 | With the continued deployment of equipment and "lighting" of the fiber, Network Testing will continue on plan. | 2011-11-18 12:09 | 2011-11-18 12:09 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2011 | Q4 | Q4 - 2011 | 5288 | 4956 | FALSE | 54 | Against a baseline of 65%, the project will make significant headway in getting back on track as a result of intense efforts with utility pole owners to complete make ready. Key risk to the project schedule at this point is the weather. | 100 | legal, admin, misc | Additional planned incidental expenses will be less that .5% of total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 80 | Percent complete expressed as a percent of the total core network which has been "cleared" for all make ready and permitting. | 24 | Site preparation will continue as required for core network hub sites. We do not anticipate needing any additional work during the quarter, so we are under budget at this point (i.e., behind baseline of 65% of budget) | 100 | We anticipate receipt of the final shipments of fiber, completing receipt of all equipment and materials for the core network. Equipment purchases going forward will primarily be related to customer premise equipment (CPE) to replenish inventories as CAI's are connected. | 10 | Expressed as a percent of budget. Baseline is at 40%. We are behind due to make ready work, however, we are also seeing favorable actual expenses as compared to budgets for work that has been completed. | 64 | Against a baseline of 40% complete, we will be over 50% complete, as all equipment is staged and awaiting the arrival of fiber at the facilities. | 24 | Against a baseline of 30%, testing activities should begin to ramp up as more hub site locations are reached during the quarter | 2012-02-27 13:29 | 2012-02-27 13:29 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2012 | Q1 | Q1 - 2012 | 6118 | 5661 | FALSE | 58 | Baseline is at 72% of budget. "Two thirds" complete milestone is due at end of Q2 2102, and we anticipate reaching that milestone with over 70% of FEDERAL funds having been invested in 24 counties in northeast Ohio, and 58% of TOTAL funds available (fed funds + match funds / program total funds budgeted). | 100 |  | Additional planned incidental expenses will be less that .5% of the total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 90 | Baseline is at 98% | 24 | Baseline is at 80%. We are trending to be under budget against estimated site prep costs for the program | 100 | Baseline is at 85%. | 25 | Baseline is at 55%. We are trending towards 2/3 completion by 6/30. Two factors are holding down % complete forecast - invoicing for work is lagging production into the following quarter, and we are trending to be under construction cost estimates overall for the project. | 43 | Baseline is at 55% | 24 | Baseline is at 40%. We are trending to be below costs in this category as well. | 2012-05-15 21:01 | 2012-05-15 21:01 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2012 | Q2 | Q2 - 2012 | 7102 | 6178 | FALSE | 60 | Baseline for total funds expended for Q3 is at 72%. We will be behind due to make ready invoicing catching up, and matching funds. | 100 |  | Additional planned incidental expenses will be less that .5% of the total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 92 | We will continue to press utility pole owners to invoice make ready for the fiber deployed and being deployed. % complete is expressed as a percent of make ready work vs. budget. | 24 | Site prep work continues as needed | 100 | Completed. Equipment purchases for customer builds will continue as needed | 20 | Baseline of 70%. We are experiencing some cost savings / reductions here from what was planned. | 36 | Baseline of 75%. We are experiencing some cost savings / reductions here from what was planned. | 25 | Baseline of 50%. We are experiencing some cost savings / reductions here from what was planned. | 2012-08-15 20:04 | 2012-08-15 20:04 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2012 | Q3 | Q3 - 2012 | 8076 | 6744 | FALSE | 68 | Percent complete based on total of funds expended, based on original grant and matching fund amounts. | 100 |  | Additional planned incidental expenses will be less than .5% of total grant. | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 94 | Percent complete is based on poles submitted to utility pole owners for "make ready" versus percent of budget. Achieving this percent complete is dependent on utility pole owners' invoicing for make ready work. | 40 | Site preparation work continues as needed to complete the rings | 100 | Completed. Equipment purchases will continue for customer premise equipment and to support large services contracts. | 30 | Percent complete expressed as a percent of original project budget for grant funds and matching contributions. Based on actual work completed, we anticipate being over 70% complete in Q4 with all original middle mile routes. | 41 | Percent complete expressed as a percent of original project budget (grant funds plus matching contributions). Based on actual work completed we will be over 70% complete in Q4 with all hub site work. | 26 | Percent complete expressed as a percent of original project budget (grant funds plus matching contributions). Based on actual work completed we will be over 50% complete in Q4 with all testing & acceptance work. | 2012-11-27 15:25 | 2012-11-27 15:25 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2012 | Q4 | Q4 - 2012 | 9066 | 7839 | FALSE | 83 | Percent complete based on total of funds expended, based on original grant and matching fund amounts. | 41 |  | Incidental expenses will be less than 0.5% in total for the grant. | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 77 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 77 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 31 | Site preparation work continues as needed to complete the rings | 96 | Equipment purchases will continue for customer premise equipment and to support large services contracts. | 71 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 100 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 49 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 2013-02-28 12:12 | 2013-02-28 12:12 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2013 | Q1 | Q1 - 2013 | 10036 | 8568 | FALSE | 89 | The project will reach 89% completion during Q2 2013, based on total funds expended (federal & matching) against the revised budget. Main expenditures in Q2 will be construction invoices for several large contracts with CAI's which will in turn generate program income which will be reinvested as matching funds, as well as "make ready" expenses. | 100 |  | Incidental expenses will be less than 0.5% in total for the grant. | 100 | Environmental Assessment was completed in Q1 2013, and EA activities continue through the enforcement of our Environmental Protection Measures. | 80 | Network design will be at 80% of revised budget. Network design activities continue as needed for redesign of routes due to EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 83 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 42 | Site preparation work continues as needed to complete the rings | 100 | Equipment purchases will continue for customer premise equipment & OSP materials replenishment, expending all of revised budget funds. | 77 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 94 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 60 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 2013-05-31 16:13 | 2013-05-31 16:13 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2013 | Q2 | Q2 - 2013 | 10814 | 9079 | FALSE | 98 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 100 | miscellaneous | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 100 | Environmental Assessment was completed in Q1 2013, and EA activities continue through the enforcement of our Environmental Protection Measures. | 100 | Network design activities continue as needed for redesign of routes due to EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 100 | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 42 | Site preparation work is expected to continue as needed to complete the rings | 100 | Equipment purchases may continue for customer premise equipment & OSP materials replenishment, but only as needed in order to complete work by 9/30. | 95 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 100 | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 90 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 2013-08-29 17:10 | 2013-08-29 17:10 | 6117 | 6117 | ONECOMMUNITY
NT10BIX5570067 | 2013 | Q3 | Q3 - 2013 | 12792 | 11127 | FALSE | 100 | completed | 100 | miscellaneous | completed | 100 | completed | 100 | completed | 0 | N/A | 100 | completed, however OneCommunity remains responsible for a substantial amount of "make ready", as the incumbent pole owners were NOT able to meet the volumes demanded for the BTOP programs in their areas. | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2015-04-22 15:13 | 2015-04-22 15:13 | 7897 | 7897 | ONECOMMUNITY
NT10BIX5570068 | 2010 | Q3 | Q3 - 2010 | 260 | 1396 | FALSE | 14 | N/A | 0 | N/A | N/A | 100 | Planned completion in early January 2011 | 10 | Engineering Implementation | 10 | Engineering Implementation | 10 | Engineering Implementation | 10 | Engineering Implementation | 0 | Not started | 0 | Not started | 0 | Not started | 0 | Not started | 2010-10-29 16:52 | 2010-10-29 16:52 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2010 | Q4 | Q4 - 2010 | 502 | 1525 | FALSE | 1 | Awaiting EA Approval | 50 | Land | 3 properties under contract | 100 | Submitted draft EA on Dec 22, 2010 | 35 | Awaiting EA Approval | 25 | Awaiting EA Approval | 0 | Awaiting EA Approval | 50 | Awaiting EA Approval | 0 | Awaiting EA Approval | 10 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 2011-01-21 09:02 | 2011-01-21 09:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2011 | Q1 | Q1 - 2011 | 1510 | 2468 | FALSE | 2 | See below | 50 | Land & Buildings | Close on 3 properties under contract in Brownsville, Weslaco and Edinburg | 100 | Obtain EA Approval and FONSI | 35 | Duct search in AT&T service areas; Engineer at participant anchor institutions | 25 | ROW in engineering routes | 0 | Not started | 50 | Brownsville, Weslaco, and Edinburg properties | 0 | Not required | 10 | Start network build at anchor institutions | 0 | Not required | 0 | Not started | 2011-04-27 09:58 | 2011-04-27 09:58 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2011 | Q2 | Q2 - 2011 | 2926 | 3220 | FALSE | 11 | See notes below | 63 | land and buildings | Complete design of buildings in Brownsville, Weslaco and Edinburg | 100 | Final EA on 4/8/11 | 48 | Engineering validating route design | 33 | Engineering soliciting ROW permits (Rio Grande City) | 9 | Soliciting city, county, state and federal permits | 100 | complete site prep for 3 properties | 35 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. | 0 | Awaiting Engineering completition | 0 | Awaiting building construction completition | 0 | Testing will commence as route segments are completed | 2011-08-04 16:57 | 2011-08-04 16:57 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2011 | Q3 | Q3 - 2011 | 4338 | 4025 | FALSE | 14 | See Notes Below | 24 | Land & Building | All land has been purchased. Building design is completed in Brownsville, Weslaco, & Edinburg. RFP's going to contractors for construction. | 100 | FONSI received on April 8, 2011 | 12 | Engineering validating route design | 0 | Engineering soliciting ROW Permits (Rio Grande City) | 0 | Soliciting City, County, State & Federal permits | 0 | Complete site prep for 3 properties | 52 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. Equipment to be purchased due to longer delivery | 7 | Construction in Rio Grande City | 0 | Awaiting building construction completion | 0 | Testing will commence as route segments are completed | 2011-11-30 14:40 | 2011-11-30 14:40 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2011 | Q4 | Q4 - 2011 | 5014 | 4685 | FALSE | 43 | This includes approval of our In-Kind Contribution request of $3,168,194 (includes mainline Urban and Mainline Rural fiber network) See Infrastructure Budget Detail. | 77 | Land & Buildings | Complete design of buildings in Brownsville, Weslaco, & Edinburg & start construction | 100 | FINAL EA on April 8, 2011 | 47 | Engineering: Campuses, Capital Duct Lease, Middle mile from Brownsville-Weslaco-Hidalgo validating route design | 0 | We have received permits but there are no separate budget dollars for this line item so actuals are not reported separately. Engineering obtained ROW Permits (Rio Grande City) | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actuals are not reported separately. Soliciting City, County, State & Federal permits | 100 | Complete site prep for 3 properties | 92 | Equipment purchased due to longer delivery intervals. | 31 | Construction: Complete Rio Grande City Construction; Complete duct routes in Brownsville, Harlingen, Edinburg, McAllen; Complete Building Construction in Brownsville, Weslaco & Edinburg. Start construction on Brownsville-Weslaco-Hidalgo route | 0 | Contingent on building construction completion | 0 | Testing will commence as route segments are completed | 2012-02-14 18:09 | 2012-02-14 18:09 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2012 | Q1 | Q1 - 2012 | 6220 | 5712 | FALSE | 83 | This includes approval of our In-Kind Contribution request of $3,168,194 (includes mainline Urban and Mainline Rural fiber network) See Infrastructure Budget Detail | 77 | Land & Buildings | Complete construction of Brownsville, Weslaco, and Edinburg buildings | 100 | Complete | 80 | Engineering: Campuses, McAllen East and McAllen West metro routes | 0 | We have received permits but there are no separate budget dollars for this line item so actuals are not reported separately | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actuals are not reported separately. Soliciting City, County, State & Federal permits | 100 | Site preparation invoices charged to Land & Building budget (will correct cash allocation in next reporting period) | 100 | Equipment purchased due to longer delivery intervals | 81 | Construction: Complete duct routes in Brownsville, Harlingen, Edinburg, McAllen; complete construction on Brownsville-Weslaco-Hidalgo route, start Brownsville & Harlingen metro routes | 0 | Contingent on building construction completion | 0 | Testing will commence as route segments are completed | 2012-05-21 09:13 | 2012-05-21 09:13 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2012 | Q2 | Q2 - 2012 | 7050 | 6152 | FALSE | 89 | This projection is in line with estimated values for the PIP | 95 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 87 | Engineering P-CAI campuses | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 88 | Construction of McAllen routes | 0 | N/A | 0 | N/A | 2012-08-13 17:28 | 2012-08-13 17:28 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2012 | Q3 | Q3 - 2012 | 8126 | 6770 | FALSE | 90 | This projection is in line with estimated values for the PIP | 95 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 87 | Engineering P-CAI campuses | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 88 | Construction of McAllen routes | 0 | N/A | 0 | N/A | 2012-11-28 17:47 | 2012-11-28 17:47 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2012 | Q4 | Q4 - 2012 | 9086 | 7858 | FALSE | 91 | This projection is in line with estimated values for the PIP | 93 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 89 | Engineering P-CAI campuses and Edinburg routes | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 91 | Construction of McAllen routes, P-CAI campuses, Edinburg route | 0 | N/A | 0 | N/A | 2013-02-28 14:43 | 2013-02-28 14:43 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2013 | Q1 | Q1 - 2013 | 9792 | 8431 | FALSE | 100 | N/A | 100 | Land & Building | Expected completion under budget | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | Expected completion slightly over budget | 100 | N/A | 100 | N/A | 2013-05-17 12:01 | 2013-05-17 12:01 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | 2013 | Q2 | Q2 - 2013 | 11282 | 9435 | FALSE | 100 | N/A | 100 | Land & Building | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2013-11-19 08:02 | 2013-11-19 08:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc.
NT10BIX5570069 | 2010 | Q4 | Q4 - 2010 | 986 | 2031 | FALSE | 4 | Substantive portions contributing to overall project completion in the next reporting period consist of issuance of FONSI, Lamoni to Leon construction, release and processing of all RFPâ€™s, clearance of all Special Award Conditions, including BIP/BTOP overlap analysis, active sub recipient project planning, and mobilization efforts including equipment procurement and staging. | 0 |  | NA | 100 | Pending final approval by NTIA a FONSI should be issued by 2/1/11. | 95 | High level network design will be 100% complete and it is anticipated that substantially all of final network design will be completed prior the end of the next reporting period. | 33 | It is anticipated that Rights of Way related to Lamoni to Leon fiber build will be completed by the next reporting period. | 33 | It is anticipated that Construction Permitting related to Lamoni to Leon fiber build will be completed by the next reporting period | 0 | No variance from revised Baseline Plan | 8 | It is anticipated that equipment orders / procurement will be begin prior to the end of the upcoming reporting period. | 0 | No variance from revised Baseline Plan | 0 | Due to minor delay in RFP release Ethernet site deployment will begin towards the beginning of the Q4 reporting period. | 0 | No variance from revised Baseline Plan | 2011-02-07 11:25 | 2011-02-07 11:25 | 5888 | 5888 | Iowa Communications Network
NT10BIX5570069 | 2011 | Q1 | Q1 - 2011 | 1948 | 2719 | FALSE | 14 | No expected variance from baseline. | 0 |  | N/A | 100 | Completed in First quarter 2011 | 100 | The Iowa Communications Network is 100% complete on network design in | 0 | The Lamoni to Leon fiber build was removed from the project. It is not anticipated that the Sub Recipients will begin work in the next quarter. | 0 | The Lamoni to Leon fiber build was removed from the project. It is not anticipated that the Sub Recipients will begin work in the next quarter. | 3 | Varies from the infrastrucure budget page due to inclusion of EA preparation expenditures to Fuberutilities Group being classified as Site Preparation costs on SF-424. | 15 | It is expected that all equipment contracts will be awarded and the first equipment orders will be placed. | 0 | It is now expected that IRU services will not be contracted until the 3rd quarter of 2011. | 10 | It is expected that work will begin on deployment of the core electronics to the southwest quadrant of Iowa. Expenditures included with Site Preparation on SF-424 | 5 | It is expected that a portion of the core equipment installed in the next quarter will have passed operational testing. Expenditures included with Site Preparation on SF-424 | 2011-05-11 17:19 | 2011-05-11 17:19 | 5888 | 5888 | Iowa Communications Network
NT10BIX5570069 | 2011 | Q2 | Q2 - 2011 | 3248 | 3386 | FALSE | 8 | Variance due to Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Delays in drawing funds due to adminstrative and waiting for vendor invoicing. | 0 |  | NA | 100 | No variance from baseline | 3 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. It is expected that engineering resources will be fully in place by mid quarter. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 13 | Baseline shows 100. In the projections for this quarter it was expected that the approval from the Iowa Legislature to exceed the codified contract limit for the term of this project would be forth coming during the first part of the previous quarter. Legislative approval did not occur until near the end of the previous quarter. No contracts could be awarded or equipment ordered until this had occurred. This has delayed equipment procurement. Equipment procurement expected to pick up in the next quarter with the installation of the DWDM equipment to be completed around the first week of December. Invoicing of DWDM equipment will not occur until after each ring is installed per contract with vendor, this will result in % complete reporting to be behind baseline until the end of the fourth quarter 2011 and possibly into the 1st quarter of 2012, depending on how quickly we are invoiced by the vendor. DWDM equipment makes up 56% of all equipment purchases. Purchasing of edge equipment | 3 | Baseline report shows 15. Variance is due to sub-recipients still in the planning and network design phase. Sub-recipient Decorah expects to have construction RFP issued beginning of 4th quarter with construction to begin in 4th quarter of calendar year 2011. Payments for 15 year IRU's to begin this quarter as contracts are signed and we begin to turn up services. | 3 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Equipment Deployment included on Site work line of Infrastructure Budget Execution Details and 424C. ARRA Contract amendment expected to be signed with current network maintenance provider as well as contract for independent installers to be put into place. | 3 | No specific budget line for network testing. Milestone completion to be tied to site equipment deployment milestone. | 2011-08-20 09:14 | 2011-08-20 09:14 | 5888 | 5888 | Iowa Communications Network
NT10BIX5570069 | 2011 | Q3 | Q3 - 2011 | 4210 | 3953 | FALSE | 28 | Variance due to Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Delays in drawing funds due to adminstrative and waiting for vendor invoicing. | 0 |  | NA | 100 | No variance from baseline. | 28 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 28 | Baseline shows 100. Equipment procurement expected to pick up in the next quarter with the installation of the DWDM equipment to be completed around the first week of December. Invoicing of DWDM equipment will not occur until after each ring is installed per contract with vendor, this will result in % complete reporting to be behind baseline until the end of the fourth quarter 2011 and possibly into the 1st quarter of 2012, depending on how quickly we are invoiced by the vendor. DWDM equipment makes up 56% of all equipment purchases. Purchasing of edge equipment continues. | 5 | Baseline shows 13. Variance is due to sub-recipients still in the planning and network design phase. Sub-recipient Decorah expects to have construction RFP issued beginning of 4th quarter with construction to begin in 4th quarter of calendar year 2011. Payments for 15 year IRU's to begin 4th quarter as contracts are signed and we begin to turn up services. | 28 | Baseline shows 15. Variance from baseline due to baseline milestones being calculated on actual work done versus expenditures. | 0 | No specific budget line for network testing. Milestone completion to be tied to site equipment deployment milestone. | 2011-11-22 10:00 | 2011-11-22 10:00 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2011 | Q4 | Q4 - 2011 | 5420 | 5106 | FALSE | 58 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | NA | 100 | No variance from baseline. | 58 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 85 | Baseline shows 100. The vast majority of equipment for site installations has been purchased. Remaining budget in this category is assigned to IRUs. | 50 | Baseline shows 38. Expect significant progress in IRU installations in coming quarter. | 36 | No variance from baseline. | 25 | No variance from baseline. | 2012-02-29 17:53 | 2012-02-29 17:53 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2012 | Q1 | Q1 - 2012 | 5936 | 5567 | FALSE | 62 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | NA | 100 | No variance from baseline. | 62 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 85 | Baseline shows 100. The vast majority of equipment for site installations has been purchased. Remaining budget in this category is assigned to IRUs. | 50 | No variance from baseline. | 47 | No variance from baseline. | 36 | No variance from baseline. | 2012-05-07 09:13 | 2012-05-07 09:13 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2012 | Q2 | Q2 - 2012 | 6854 | 6053 | FALSE | 71 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 | N/A | N/A | 100 | No variance from baseline. | 71 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 95 | No variance from baseline. | 63 | No variance from baseline. | 60 | No variance from baseline. | 40 | No variance from baseline. | 2012-08-03 16:20 | 2012-08-03 16:20 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2012 | Q3 | Q3 - 2012 | 7956 | 6683 | FALSE | 78 | Baseline shows 95%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | N/A | 100 | No variance from baseline. | 85 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 99 | Baseline shows 100%. Variance from baseline is due to the amount of consumables yet to be purchased. | 75 | No variance from baseline. | 72 | No variance from baseline. | 60 | No variance from baseline. | 2012-11-19 12:55 | 2012-11-19 12:55 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2012 | Q4 | Q4 - 2012 | 9126 | 7907 | FALSE | 88 | Baseline shows 97%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | N/A | 100 | No variance from baseline. | 88 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 88 | Baseline shows 100%. Variance from baseline represents the IRU's that will not be completed by the end of 2013-2Q. | 83 | No variance from baseline. | 85 | No variance from baseline. | 72 | No variance from baseline. | 2013-03-06 08:43 | 2013-03-06 08:43 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2013 | Q1 | Q1 - 2013 | 9776 | 8422 | FALSE | 100 | No variance from baseline. | 0 |  | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2013-05-16 15:25 | 2013-05-16 15:25 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570069 | 2013 | Q2 | Q2 - 2013 | 11840 | 10015 | FALSE | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% or total funds expected to be spent. | 100 | N/A | N/A | 100 | No variance from baseline. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% or total funds expected to be spent. | 100 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. This will result in total spending on equipment being $988,727 less than budgeted. | 100 | All money for IRU's budgeted in the June 2013 budget revision, AAR #2407490 was spent. | 100 | The ICN's dropped 283 total CAI's from ICN's original planned list of 3,101. This will result in total spending on equipment being $988,727 less than budgeted. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. | 2014-02-19 12:52 | 2014-02-19 12:52 | 7309 | 7309 | Iowa Communications Network
NT10BIX5570070 | 2010 | Q4 | Q4 - 2010 | 1010 | 2056 | FALSE | 12 | Planned expenditures for Overall Project for the upcoming quarter are on target with baseline projections. | 63 |  | Planned expenditures for Other for the upcoming quarter are expected to be 5% behind baseline projections due to prior ramp up time of the Federal Compliance Manager position through Q2. | 100 | Planned expenditures for Environmental Assessment for the upcoming quarter are on target with baseline projections. | 30 | Planned expenditures for Network Design for the upcoming quarter are expected to be on target with baseline projections. | 23 | Planned expenditures for Rights of Way for the upcoming quarter are expected to be 4% below baseline projections due to the many complicated pole attachment and conduit agreement negotiations we are involved in and the impact of weather on pole surveying. | 1 | Construction Permits for the upcoming quarter are on target with the baseline projections. | 0 | N/A | 0 | N/A | 14 | Planned expenditures for Network Build for the upcoming quarter are on target with baseline projections. | 0 | N/A | 0 | N/A | 2011-02-08 18:01 | 2011-02-08 18:01 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2011 | Q1 | Q1 - 2011 | 2274 | 2882 | FALSE | 15 | Planned expenditures for Overall Project for the upcoming quarter are 1% behind, but expected to ramp up as the Make Ready work increases to full capacity allowing construction to reach higher production rates. | 94 |  | Planned expenditures are 20% ahead of baseline projections, due to protracted negotiations in procurements and agreements, and the associated costs of legal counsel and outside consultants. | 100 | EA completed. No further expenditures planned. Compliance requirements with environmental mitigation was included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 61 | Planned expenditures are 25% ahead of baseline, but expected to even out as majority of costs will transition into Network Build category as construction approaches. | 43 | Planned expenditures for Rights of Way for the upcoming quarter are on target with baseline projections. | 5 | Planned expenditures for Construction Permits and Other Approvals for the upcoming quarter are 1% behind baseline projections, but expected to ramp up as the Make Ready Work increases to full capacity. | 0 | No expenditures planned for upcoming quarter. | 0 | No expenditures planned for upcoming quarter. | 13 | Planned expenditures for next quarter are 4% behind baseline projections, but expected to ramp up as we enter construction stage. | 0 | No expenditures planned for upcoming quarter. | 0 | No expenditures planned for upcoming quarter. | 2011-05-24 10:50 | 2011-05-24 10:50 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2011 | Q2 | Q2 - 2011 | 3120 | 3317 | FALSE | 24 | Overall project expenditures will ramp up rapidly in the next quarter due to (a) pre-payment of make-ready costs, (b) ordering of fiber and construction materials, (c) finalization of design by network segment including CAI and POI designs, and (d) start of construction. | 97 |  | Expect small increase in total percentage; outside legal and other procurement-related fees are mostly complete | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation was included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 69 | Only a 4% increase off last quarter due to costs shifting from Network Design to Rights of Way | 43 | 16% increase anticipated due to final push in field data collection and increased costs associated with make ready application fees | 29 | Expected to apply for many railroad, environmental and road permits, held because Design-Build firm required to complete construction drawings. Continue with pole applications and make-ready. | 25 | First expenditures in this category anticipated to occur along the projected baseline | 1 | Equipment design will be completed this quarter and sufficient equipment to construct a test lab is planned to be ordered. Prepayment or a deposit may be required. | 19 | Percentage may vary based on timeline for potential IRU acquisitions. Fiber deployment unlikely until the next quarter due to delivery delays and make ready lead time. | 0 | On par with baseline projection | 0 | On par with baseline projection | 2011-08-16 14:16 | 2011-08-16 14:16 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2011 | Q3 | Q3 - 2011 | 3974 | 3825 | FALSE | 37 | Ramp up activities are consistent with last quarter: overall project expenditures will continue to catch up to budgeted expectations next quarter due to (a) prepayment of make-ready costs, (b)ordering fiber and construction materials (c) finalization of design by network segment including CAI and POI designs, and (d) start of construction, | 99 |  | Expected to be ahead on percentage by 19%, however; there are no significant expenditures from this category planned next quarter which aligns with PPR projections and baseline. Costs included in the Other category are as follows: â€¢ Federal Compliance Staff related costs â€¢ BTOP Non-Construction Staffing and Other costs (i.e. NTIA Conference travel, non-construction BTOP related staff time) â€¢ Application and Post Application Submission Costs as allowed under the NOFA and included in our approved budget including staffing and professional services â€¢ Staff, Consulting and Legal Costs associated with the Network Operator Procurement | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation were included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 100 | Expected to be ahead on budgeted expenditures by 52%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants as network design progresses. Costs are now projected to be higher than were projected in original NTIA budget | 100 | Expected to be ahead on budgeted expenditures by 25%. We plan to be close to complete with all make ready and conduit applications as well as complete the majority of expenditures for the pole survey ahead of schedule | 40 | Expected to be ahead of budgeted expenditures by 3% due due make ready costs coming in higher than budgeted in baseline budget | 25 | Expected to be behind on expenditures by 25% due to the activities of this category being pushed out for scheduling reasons | 13 | Expected to continue to be on par with baseline projections | 28 | Expected to remain behind on percentage by 12%. Slower than expected Design Build ramp-up and make ready construction work by utilities have led to expectation of less expenditures to date than initially planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design. | 13 | Equipment likely to be first implemented next quarter | 0 | On par with baseline projections | 2011-11-10 16:49 | 2011-11-10 16:49 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2011 | Q4 | Q4 - 2011 | 5160 | 4824 | FALSE | 55 | Expected ahead on budgeted expenditures by 3% due to anticipation of high expenditures for make ready work, which has been forecast higher than in initial baseline plan | 99 |  | Expected to be ahead on percentage by 16%, however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs included in approved budget â€¢ Staff, Consulting and Legal Costs with procurements | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Expected ahead on budgeted expenditures by 43%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. Costs are now projected to be higher than in original baseline | 100 | Expected to be ahead on budgeted expenditures by 9%. We plan to be complete with all make ready, conduit applications andpole surveying ahead of schedule | 79 | Expected to be ahead of budgeted expenditures by 26% due to the anticipation of high expenditures for make ready work costs, which has been forecast higher than in initial baseline plan | 0 | Behind on percentage by 75% due to activities now being projected to occur in Year2 Quarter4. Costs will be less than baseline projection. | 47 | Expected to be ahead on expenditures by 9% due to procurement scheduling occurring early | 31 | Expected to be behind on percentage by 21%. Slower than expected Design Build ramp-up and make ready construction work by utilities have led to less projected expenditures in quarter. Additionally, some costs of this category are being captured under Network Design. | 46 | Expected to be ahead by 8% due to equipment deployment costs starting to ramp up | 0 | On par with baseline projections | 2012-02-21 09:54 | 2012-02-21 09:54 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2012 | Q1 | Q1 - 2012 | 6036 | 5617 | FALSE | 72 | Ahead on projected expenditures by 5% due to higher than anticipated expenditures for make ready work and network design costs, both of which are higher than initial baseline plan | 100 |  | Ahead on projected expenditures by 12%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs included in approved budget â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 33%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. Costs are projected to be higher than original baseline | 100 | Ahead on projected expenditures by 2% due to being ahead of schedule and complete with aerial and conduit applications and pole surveying work | 100 | Ahead on projected expenditures by 32% due to higher than anticipated for make ready work costs, which has been forecast higher than in initial baseline plan | 14 | Behind on projected expenditures by 86% due to anticipated costs now forecast to be less than baseline projection, with portions captured in Network Design | 99 | Ahead on projected expenditures by 26%. Equipment and materials will be procured and paid for earlier than schedule due to industry-wide lengthened lead times on delivery. Costs are also now projected to be higher than baseline plan. | 31 | Behind on projected expenditures by 34%, due to some projected costs accounted for under Network Design. Design Build costs will continue to rise over remainder of project as construction fully ramps up | 100 | Ahead on projected expenditures by 25% due to higher equipment installation costs than in initial baseline plan. | 0 | On par with baseline and projected expenditures | 2012-05-11 10:14 | 2012-05-11 10:14 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2012 | Q2 | Q2 - 2012 | 7080 | 6167 | FALSE | 86 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 1% | 100 |  | Ahead on projected expenditures by 8%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 24%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | Ahead on projected expenditures by 21% due to higher than anticipated for make ready work costs than in baseline projection | 38 | Behind on projected expenditures by 62% due to costs now forecasted to be less than baseline projection, with portions captured in Network Design. MTC does not anticipate reaching 100% expenditures for this line item | 100 | Ahead on projected expenditures by 2%. Equipment and materials are being procured and paid for earlier than schedule due to industry-wide lengthened lead times on delivery. | 43 | Behind on projected expenditures by 43% due to (a) some projected costs accounted for under Network Design, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) certain work is delayed pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 3 | Behind on projected expenditures by 19% due construction delays which have pushed back the anticipated start of testing | 2012-08-15 14:20 | 2012-08-15 14:20 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2012 | Q3 | Q3 - 2012 | 7962 | 6687 | FALSE | 92 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 1%. Against new budget with extra funds, expected to be at 72% complete | 100 |  | Ahead on projected expenditures by 5%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 15%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | Ahead on projected expenditures by 10% due to higher than anticipated for make ready work costs than in baseline projection | 41 | Behind on projected expenditures by 59% due to costs now forecasted to be less than baseline projection, with portions captured in other categories. MTC does not anticipate reaching 100% expenditures for this line item | 100 | On par with baseline projections | 54 | Behind on projected expenditures by 37% due to (a) some projected costs accounted for under other categories, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 35 | Behind on projected expenditures by 9% due to construction delays which have pushed back the anticipated progress of testing | 2012-11-19 16:55 | 2012-11-19 16:55 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2012 | Q4 | Q4 - 2012 | 9008 | 7781 | FALSE | 100 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 3%. Against new budget with extra funds, expected to be at 79% complete | 100 |  | Ahead on projected expenditures by 2%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 5%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | On par with baseline projections; make ready expected to conclude during quarter | 100 | On par with baseline projections, based on required improvements to Points of Interconnection buildings during installation | 100 | On par with baseline projections | 71 | Behind on projected expenditures by 25% due to (a) some projected costs accounted for under other categories, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 16 | Behind on projected expenditures by 51% due to construction delays which have pushed back the anticipated progress of testing, and the subsequent payment milestones | 2013-02-27 11:23 | 2013-02-27 11:23 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2013 | Q1 | Q1 - 2013 | 9890 | 8485 | FALSE | 100 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 90% complete | 100 |  | On par with baseline percentage no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 79 | Behind on projected expenditures by 21% based on work being categorized in other budget categories | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 87 | Behind on projected expenditures by 13% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 82 | Behind on projected expenditures by 18% due to construction delays which have pushed back the anticipated progress of testing, and the subsequent payment milestones | 2013-05-23 16:07 | 2013-05-23 16:07 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2013 | Q2 | Q2 - 2013 | 10780 | 9059 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 121% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 95% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are 131% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 259% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 133% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 140% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 92 | Behind on projected expenditures by 8% based on work being categorized in other budget categories | 100 | Costs projected to be 131% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 95 | Behind on projected expenditures by 5% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | Costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 137% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2013-08-28 09:06 | 2013-08-28 09:06 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2013 | Q3 | Q3 - 2013 | 11412 | 9524 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 124% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 99% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are projected to be 136% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 259% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 133% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 143% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Site Preparation expected to be completed. Actual projected costs will be 101% of the baseline budget. | 100 | Costs projected to be 145% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 96 | Behind on projected expenditures by 4% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the project delays | 100 | Equipment Deployment expected to be completed. Actual costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 153% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2013-11-26 17:25 | 2013-11-26 17:25 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2013 | Q4 | Q4 - 2013 | 12044 | 10203 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 125% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 100% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are projected to be 139% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 260% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 132% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 143% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Site Preparation expected to be completed. Actual projected costs will be 103% of the baseline budget. | 100 | Costs projected to be 145% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Network Build will be 98% of the baseline budget as some projected costs accounted for under other categories | 100 | Equipment Deployment expected to be completed. Actual costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 162% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2014-04-16 14:15 | 2014-04-16 14:15 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570070 | 2014 | Q1 | Q1 - 2014 | 12714 | 11039 | FALSE | 100 | In this section, we are calculating Percentage Complete with reference to the approved NTIA budget. Actual Costs are now 113% of the approved budget. MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. | 100 |  | Costs included in this category are: -Federal Compliance Staff -BTOP Non-Construction Staffing -Application and Post Application Submission Costs included in approved budget -Staff, Consulting, and legal costs Costs were offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 135% of the baseline budget. | 100 | Compliance requirements with environmental mitigation included in Design-Build RFP and the Owner's Project Manager will oversee work. Complete and actual costs are 159% of baseline budget. | 100 | Some costs included in Network Build are now categorized under Network Design. High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 260% of baseline budget. | 100 | Pole survey work and make ready application costs are complete. Actual costs are 128% of baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 105% of the baseline budget. | 100 | Although some of these costs have been allocated to other categories, actual costs are higher than budgeted. Actual costs are 106% of the baseline budget. Site preparation is essentially complete. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 106% of the baseline budget. | 100 | Actual costs are 95% as some costs included in the baseline report under this category are being captured under Network Design. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 334% of the baseline budget. | 100 | High costs offset by additional matching funds from the Commonwealth of Massachusetts; Actual costs are 162% of the baseline budget. | 2015-02-23 16:46 | 2015-02-23 16:46 | 5934 | 5934 | Massachusetts Technology Park
NT10BIX5570071 | 2010 | Q4 | Q4 - 2010 | 480 | 1506 | FALSE | 13 | N/A | 0 |  | N/A | 95 | N/A | 20 | N/A | 0 | N/A | 0 | N/A | 9 | N/A | 9 | N/A | 9 | N/A | 9 | N/A | 5 | N/A | 2011-01-11 19:35 | 2011-01-11 19:35 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570071 | 2011 | Q1 | Q1 - 2011 | 2362 | 2926 | FALSE | 7 | Zayo be ahead of schedule by 2.30%. This is based on us having our FONSI and being able to proceed. | 0 |  | N/A | 100 | N/A | 60 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A | 0 | N/A | 0 | N/A. | 10 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A | 10 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A. | 2011-05-26 18:45 | 2011-05-26 18:45 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570071 | 2011 | Q2 | Q2 - 2011 | 3184 | 3352 | FALSE | 17 | This is 3.9% ahead of the baseline. Which is based on resolution of the state shutdown soon and us being able to catch up with Equipment Procurement and Equipment Deployment. | 0 | N/A | N/A | 100 | This is 5% ahead of the baseline. | 70 | This is 50% ahead of the baseline. This is an estimate based on a quick resolution to the state shutdown and our engineering contractors being able to maintain the pace that they have set. | 30 | This is 30% ahead of the baseline. This is based on resolution of the state shutdown. | 30 | This is 30% ahead of the baseline. This is based on resolution of the state shutdown. | 0 | This is 9% behind the baseline and that is because of permitting and making sure that we have the official route before we do land acquisition and site preparation. | 9 | N/A | 9 | N/A | 9 | N/A | 5 | N/A | 2011-08-17 22:57 | 2011-08-17 22:57 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570071 | 2011 | Q3 | Q3 - 2011 | 4128 | 3910 | FALSE | 27 | This is 1.7% ahead of baseline. | 0 |  | This is on target with our baseline. | 100 | This is on target with our baseline. | 90 | This is 30% ahead of our baseline based on an early start. | 0 | This is on target with our baseline. | 90 | This is 30% ahead of our baseline. | 23 | This is on target with our baseline. | 81 | This is 58% ahead of our baseline. | 15 | This is 8% behind schedule because of our permitting pole attachment issues discussed in section 3 of this report. | 15 | This is 8% behind schedule because of our permitting pole attachment issues discussed in section 3 of this report. | 0 | This is 20 percent behind our baseline because of our build issues. | 2011-11-18 11:43 | 2011-11-18 11:43 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570071 | 2011 | Q4 | Q4 - 2011 | 5008 | 4680 | FALSE | 27 | This is 1.7% ahead of our baseline. | 0 |  | This is on target with our baseline. | 100 | This is on target. | 90 | This is 30% ahead of our baseline. | 0 | This is on target. | 90 | This is 30% ahead of our baseline. | 23 | This is on target. | 81 | This is 58% ahead of our baseline. | 15 | This is 8% behind schedule because of (build issues) permitting pole attachment issues with providers. | 15 | This is 8% behind schedule because of build issues. | 0 | This is 20% behind our baseline because of build issues. | 2012-02-14 16:19 | 2012-02-14 16:19 | 6743 | 6743 | Zayo Bandwidth, LLC
NT10BIX5570072 | 2010 | Q4 | Q4 - 2010 | 1050 | 2089 | FALSE | 7 | This represents a negative variance of 3% to the Baseline. This is primarily driven by the fact that Com Net originally planned to receive shipment of a full 475,000' of Outside Plant Fiber Optic Cable and other Outside Plant materials. Given the short lead time between award of the OSP materials RFP and the start of construction, Com Net is now planning on a partial release of OSP materials including 100,000' of OSP fiber-optic cable. Furthermore, based on Com Net's decision to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. Com Net's administrative costs continue to run above budgeted expectation and will continue to do so throughout the project based on underestimates of time and project audit expenses | 100 | Pre-Award Acceptance | Other Baseline Items-Percent completions are: Project Management & Administration Reporting -19%, Contractual Sale of Services - 0% and Operation Support Systems - 0%. | 100 | No Variance | 17 | This represent a positive variance of seven (7) percent versus baseline. This positive variance is a carryover from the gains made in the second quarter by having the Route Design Firm pull ahead activities during the drive-out of routes for the Environmental Assessment. | 6 | A negative variance of three percent is reported as Com Net does not project to receive its FONSI until mid-February at the earliest. The finalization of certain Right-of-Way applications dependent on first completing compliance reviews against the final Environmental Assessment report. | 13 | A negative variance of three percent is reported as Com Net does not project to receive its FONSI until mid-February at the earliest. The finalization of certain Construction Permits and other Approvals are dependent on first completing a compliance reviews against the final Environmental Assessment report. | 11 | No Variance | 26 | This represents a six percent positive variance to the baseline. Com Net elected during the RFP process to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. The actual procurment will be completed however the cash requirement will be delayed until the 2nd quarter of 2011. Com Net also plans to make positive gains on equipment procurement by working with sub-recipient OARnet to pull ahead in-kind electronics/optronic match obligation, as well as new equipment procurement within reason.` Com Net and OARnet verified that OARnet as a state agency can purchase using State of Ohio contracts as it satisfies the procurement requirements associated with the project. | 1 | Based on full percentage point reporting no variance is visible, however Com Net originally planned to receive shipment of a full 475,000' of Outside Plant Fiber Optic Cable and other Outside Plant materials in the 1st Quarter of 2011. Given the short lead time between award of the OSP materials RFP and the start of construction, Com Net is now planning on a partial release of OSP materials including 100,000' of OSP fiber-optic cable. | 1 | This represents a 9% negative variance. Com Net elected during the RFP process to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. The actual work of placing the equipment on site may represent a minimum percent completion however the cash requirement will not occur until the 2nd quarter of 2011 after acceptance testing of deployed equipment is completed..` | 1 | No Variance | 2011-02-10 14:39 | 2011-02-10 14:39 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2011 | Q1 | Q1 - 2011 | 2290 | 2890 | FALSE | 11 | Negative Variance of 14% due to Com Net not yet receiving its initial FONSI and original baseline based on receipt of FONSI in early February 2011 and construction commencing by March 1, 2011. This 11% overall project completion is aggressive given that as of the date of submission Com Net had not yet received its FONSI. All projections are based on receipt of FONSI by first day of business May 2011. | 100 | PreAward Acceptance & Application | Other items included in the Baseline report included Project Management and Administration Reporting at 28% complete, Contractual Solution Sales at 3% and Operation Support Systems at 20%. | 100 | Com Net projects submitting its final EA by mid April. Com Net's projection are based on receipt of initial FONSI on the 1st day of business in May 2011 | 28 | Positive Variance of 6%. Com Net was able to ramp ahead of schedule on Route Design activities without FONSI. Com Net plans to expand and maintain design progress ahead of schedule in order to present the opportunity for timeline GAP closure against baseline on long lead time item, fiber plan construction. | 23 | Positive Variance of 2%. Most Road Right of Way applications are non-fee based. Progress in this area is primarily judged against receipt of approval on all applications for occupancy in Road Right of Way including crossing of non-navigable and navigable waterways. Com Net will attempt to balance receipt of Road Right of Way against start of construction to avoid applications and Right of Way expiring. | 6 | Negative Variance of 28%. Many permits and occupancy agreements require work to be completed within 30-120 days of issuance depending on the Authority Having Jurisdiction. Without Com Net's FONSI, tasks have been reprioritized to place priority on design and initial construction of fiber routes that do not involve largest share of RR crossing, navigable waterway crossings, pole attachments/pole make readies. This is a planned variance as part of Com Net's GAP closure measures. | 0 | Negative Variance of 42% due to Com Net not yet in receipt of its initial FONSI, therefore Com Net is placing a lower priority on Site preparation work for Telecommunications Shelter (Huts) while it focuses on the long lead time item of Outside Plant fiber construction. Com Net will place greater emphasis on Site Preparation and Hut Deployment in the 3rd and 4th Quarters of 2011 | 25 | Negative Variance of 1%. Com Net will focus on sub-recipient in-kind equipment being made part of the project on receipt of the FONSI and equipment to be deployed at existing Sites that aren't dependent on 2f above in order to close the GAP on this high value item. | 5 | Negative Variance of 6% due to Com Net not yet receiving its initial FONSI. Com Net originally planned to have crews fully ramped by mid April with significant construction progress being made for over 2/3rds of the Quarter. At this point Com Net projects not being able to begin ramping the deployment of crews on segments until early to mid-May weather permitting. Com Net will attempt to accelerate by securing leases and IRUs where planned ahead of schedule provided the facilities can be put to use. Com Net's initial focus will be on an accelerated ramp to deploy crews and on daily progress rates. This will be dependent on weather due to the fact that year to date weather conditions for outside plant construction have been less than favorable. | 13 | 35% Variance due to CNI not yet receiving FONSI and planning to refocus efforts on long lead time outside plant fiber optic cable construction on receipt of FONSI and delay equipment activities that have a shorter turn around time | 10 | 14% Variance due to CNI not yet receiving FONSI and placing initial emphasis on closing GAP associated with high dollar, long lead time outside plant fiber construction upon receipt of FONSI expected by 1st day of business in May | 2011-05-24 23:23 | 2011-05-24 23:23 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2011 | Q2 | Q2 - 2011 | 3254 | 3389 | FALSE | 16 | Negative Variance of 21% as Com Net continues to ramp efforts to close gap created by delay in ability to commence ground disturbing activities versus the assumptions included in its baseline report | 100 | Preaward Acceptance and Application | Other items included in the baseline report were Project Management and Administration Reporting projected to be at 41% versus a baseline of 38%, Contractual Solution Sales projected to be at 15% versus a baseline of 12% and Operation Support Systems at 14% versus a baseline of 67% based on deferring a decision on a platform for mapping facility assets since route design firm will retain mapping record system until completion of construction and decision to evaluate CYAN CYMS monitoring and management system capabilities before pursing a purchase of a third party Network Management System. | 100 | Initial Assessment completed with receipt of FONSI and lifting of Special Award Conditions in May 2011 | 35 | One percent positive versus baseline. Actual progress will be managed based on implementation time line requirements placed on permits and progress of construction | 33 | Negative Variance of 13% versus baseline but projecting significant progress based on implementing follow-up program with AHJs on permit status | 21 | Negative variance of 25%. Potential to exceed percentage based on financial criteria as permits for the upcoming quarter will be in the vicinity of I-75 where we will encounter more Railroad crossings and pole attachments that carry fees | 7 | Negative Variance of 34%. See comments on current quarter as this is a carry forward on a non-critical path item. Com Net is projecting to make significant progress on site preparation commencing in the Spring of 2012. The site preparation activities are short lead time and low dollar items based on the overall scope of the project. Com Net will progress the work in this area as needed to satisfy commitments with Community Anchor Institutions throughout the balance of 2011 and winter of 2012 | 29 | Negative Variance of 10%. Com Net plans to place delays in forecast of purchases with CYAN based on delays in equipment deployment as described in the current quarter progress reporting | 10 | Negative Variance of 12% projected as Com Net plans to delay purchase of fiber IRU in Columbus market by one quarter based on delay in start of construction. As mentioned in the comments associated with performance for work completed in 2011Q2, Com Net is projecting closure on the gap in network build progress by June of 2012 based on moderate-optimistic and pessimistic projections. | 6 | Negative variance of 62%. This is a carry-forward delay based on explanation provided for 2011Q2 progress reporting. Several sites scheduled for equipment deployment are dependent on the completion of fiber route construction through acceptance, which is projected to occur in September. Com Net, also, projects to complete its power audit and schedule any corrective actions in August of 2011. This will put Com Net in a position to begin deploying equipment, as well as, completing upgrades to existing leased fiber facilities. Once manufacturer personnel is deployed to the field, equipment deployment will progress in an accelerated pace to allow full gap closure against this matrix by August 2012. | 7 | Negative Variance of 30% driven by delays in equipment deployment. Majority of progress on network testing is in the area of passive facility inspection and testing. | 2011-08-22 11:09 | 2011-08-22 11:09 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2011 | Q3 | Q3 - 2011 | 4252 | 3976 | FALSE | 19 | Negative Variance of 30% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. Furthermore, Com Net is projecting limited progress due to moratoriums imposed by carriers and utility providers from mid-December until after the 1st of the year. Com Net projects that unliquidated obligations will increase significantly as we are unable to fully finalize items leaving them as work-in-progress rather than finished goods. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting projected at 60% complete versus a baseline of 44% as Com Net plans to use November and December for budget analysis and route modification activities. Contractual Sales solutions at 12% versus baseline of 14% with community anchor institution term contract sales remaining ahead of projections but Broadband Service Provider contracts lagging behind due to delays in network builds. Operation Support System projected at 11% versus a baseline of 90% as Com Net continues to defer NISC IVUE plant and trouble module implementation, as well as, decision to defer mapping until the end of project when records are transferred from route design firm to Com Net. | 100 | Com Net projects to realize expenditure in this category as it pursues route modifications, as well as, receipt of invoices from EA consultant for EA protocols and measures. | 38 | Negative Variance of 3% versus Baseline as some of the work ahead progress is given up due to limited permitting activity expected in December of 2011 by Authorities Having Jurisdiction. | 35 | Negative Variance of 19% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. | 16 | Negative Variance of 30% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. | 13 | Negative Variance of 52% versus Baseline. Com Net is projecting to satisfy EA Area of Potential Effect concerns, as well as, site surveys and site acquisition activities. Com Net doesn't expect to see significant construction progress until after the 1st of the year. | 34 | Negative Variance of 17% versus baseline. Com Net sees the ability to increase shipment from the factory to Com Net warehouse inventory, but Com Net does not expect Cyan personnel to progress installation of equipment during the month of January so Com Net plans to continue to have inventory held at the factory. | 12 | Negative Variance of 20% versus baseline. Com Net is projecting minimal measurable progress for reporting as we are projecting that very few routes will be fully completed prior to year-end leaving a significant amount of work in progress or as unliquidated obligations. | 8 | Negative Variance of 74% versus baseline. Com Net is projecting to make progress early in the quarter but with limited progress after November 23, 2011 due to holiday vacation time and company cut-backs in travel time as year-end approaches. | 25 | Negative Variance of 23% versus baseline. Network testing will continue to lag as network build and equipment deployment lag behind baseline projections. | 2011-11-23 12:47 | 2011-11-23 12:47 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2011 | Q4 | Q4 - 2011 | 5238 | 4899 | FALSE | 29 | Negative Variance of 27% versus baseline down 3% from prior quarter variance. Com Net is projecting aggressive progress for the 2012 Winter Quarter based on favorable weather during the month of January. Com Net's projections are based on segments that have been a work-in-progress for some time, receiving the necessary authorizations to proceed to completion. Com Net is projecting that it will achieve 67% completion of the overall project by the end of the 3rd Quarter of 2012, full completion by the end of the 2nd Quarter of 2013 and that the gap between baseline and actual will not be closed until the 1st Quarter of 2013. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting projected at 64% versus baseline of 53%. This gap is projected to narrow based on reduced time and expenses with legal counsel on contracts and right-of-way agreements. Contractual Sales Solutions are expected to increase as Com Net is optimistic about converting several bids submitted in December of 2011 into contracts in the 1st Quarter of 2012. This is why Com Net is projecting Contractual Sales Solution increase to 20% complete versus a baseline of 19%. Other Pre-Award Operation Support Systems are projected to show minimal progress at 12% versus baseline projections of 100%. A portion of this is based on Com Net continuing to hold on the purchase of the NISC plant and trouble management modules, as well as our planned delay in the purchasing of a mapping solutions until the end of the project when the CAD drawings will be transferred from the route design firm to Com Net. Com Net is also questioning the need for a Network | 100 | Expenditures with Environment Assessment Consultant are being tracked under Construction Permits and Other Approvals as services are requested on a per segment basis to pursue route modification or to assist in implementation of protocols and measures identified in the project FONSI. | 67 | Positive Variance versus baseline of 12%. This is as planned by Com Net as we pull-ahead design and permitting activities in preparation for an aggressive construction period from the Spring of 2012 thru the Fall of 2012. | 42 | Com Net is expecting to finalize arrangements with several Counties to allow for the direct plow method of construction. This arrangement should allow for the release of over 50 Miles of Right-of-Way in a short time frame. This backlog of right-of-way mileage, along with right-of-way applications submitted with standard lead times, should allow for a substantial amount of mileage to be released for construction by the end of the 1st Quarter of 2012. | 39 | Com Net is projecting a negative variance versus baseline of 26%. From a financial perspective, this gap is expected to close as Com Net's construction moves to more congested areas where authorities will apply more stringent requirements; therefore resulting in higher permitting fees. As Com Net approaches metropolitan areas, pole attachment applications and make ready fees will increase as the planned aerial mileage increases. Com Net will also encounter record and capacity checks as it pursues access to existing conduit routes. Com Net isn't projecting these fees to be liquidated until the 2nd and 3rd Quarters of 2012. | 11 | Projection is based on a negative variance of 62% versus baseline. Com Net will continue to progress surveying, material acquisition and negotiation of leased space during the 1st Quarter of 2012. This work will be in preparation of construction activities at Points-of-Presence Sites in the 2nd and 3rd Quarters of 2012. | 36 | Projection is based on a negative variance of 27% versus baseline. Com Net continues to reassess its plans for MPLS Network Equipment as it becomes more familiar with the capabilities of the Cyan Z-Series equipment. The capabilities of the Cyan and its ability to meet the majority of our service requirements have caused Com Net to reconsider the need for MPLS Network Equipment given its higher on-going cost of ownership. | 24 | Negative Variance of 14% versus baseline down 6% from prior quarter. Com Net views this as positive progress toward gap closure especially for winter quarter construction. | 15 | Negative Variance of 68% versus baseline. Com Net plans to continue to aggressively deploy equipment ahead of the completion of fiber segments in order to be in a position to shorten the lead time from acceptance of passive facilities to active cut over in the network. | 73 | Positive Variance versus baseline of 53% using financial measurements. This is based on Com Net's decision to increase inspection and testing in order to accept portions of segments. This is being done such that Community Anchor Institutions can be cut into service prior to completion and acceptance of an entire segment. Com Net is projecting a budget overrun for Network Testing of ~$150,000, which is less than 0.5% of the overall project budget. | 2012-02-23 18:23 | 2012-02-23 18:23 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2012 | Q1 | Q1 - 2012 | 6234 | 5719 | FALSE | 40 | Negative Variance to baseline of 28% Increase over prior quarter of 13%. Com Net projects construction progress to increase, however due to the lag in the invoicing and payment cycle, the liquidated run rate is projected to remain the same as 2012 Q1. The other factors driving the increase in the overall project progress involve the start of ground disturbing activities at two new construction point-of-presence (hut) sites and site preparation for occupancy at two new point-of-presence sites. In addition, Com Net is projecting an increase in the run rate for equipment procurement and equipment deployment through OARnet's planned receipt and partial deployment of equipment in the May-June 2012 time frame. ZAYO will be active with route design and permitting activities as it implements the ZAYO managed network build through Toledo following an acquired metro route. Com Net projects to be 64% by the end of the third quarter of 2012 and 78% complete by the end of the fourth quar | 100 | Application and Pre-Acceptance Period | Project management and admin reporting at 76%. Contract Sales continue to progress toward baseline goals at a 55% projected completion rate. Operation Support Systems at 23%. Com Net projects it will have connected 58 Community Anchor Institutions and signed agreement with 26 wholesale/last mile providers. | 100 | Initial Environmental Assessment is complete. All future services will be for route modification, which will be recorded as a construction permit and other approval expense or a construction expense depending on point of origination of change order. | 79 | Negative variance to baseline of 1%. Increase over prior quarter of 12%. See overall project narrative and planned activities for upcoming quarter. | 45 | Negative variance to baseline of 33%. Increase over prior quarter of 6%. See overall project narrative and planned activities for upcoming quarter. | 38 | Negative variance to baseline of 46%. Increase over prior quarter of 4%. See overall project narrative and planned activities for upcoming quarter. Highly dependent on invoice timing and final negotiated charges for accessing City of Perrysburg conduit over the Maumee river. | 14 | Negative variance to baseline of 74%. Increase over prior quarter of 5%. See overall project narrative and planned activities for upcoming quarter. | 59 | Negative variance to baseline of 12%. Increase over prior quarter of 20%. See overall project narrative and planned activities for upcoming quarter. | 30 | Negative variance to baseline of 25%. Increase over prior quarter of 9%. See overall project narrative and planned activities for upcoming quarter. Com Net projects to have placed 342 miles of fiber cable by the end of the 2nd Quarter of 2012. | 31 | Negative variance to baseline of 57%. Increase over prior quarter of 13%. See overall project narrative and planned activities for upcoming quarter. | 93 | Positive variance to baseline of 23%. Increase over prior quarter of 33%. See overall project narrative and planned activities for upcoming quarter. | 2012-05-21 15:50 | 2012-05-21 15:50 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2012 | Q2 | Q2 - 2012 | 6924 | 6089 | FALSE | 45 | This projection represents an 8% increase over prior quarter and a negative 31% versus baseline. | 100 | Application and Pre-Acceptance Period | Pre-Award Acceptance and Application is 100% complete from a liquidated obligations perspective, which represents a 0% variance versus baseline. Project Management and Admin Reporting is projected to be 83% complete. Contractual Sales Solutions is projected to be 60% complete, which represents a negative 3% variance to baseline. Operation Support Systems are projected to be 33% complete, which represents a 67% negative variance to baseline. | 100 | Initial Environmental Assessment is complete. All future services will be for route modification, which will be recorded as a construction permit and other approval expense or a construction expense depending on point of origination of change order. | 66 | This projection represents an 4% increase over prior quarter and a negative 25% versus baseline. | 67 | This projection represents an 13% increase over prior quarter and a negative 11% versus baseline. | 56 | This projection represents an 4% increase over prior quarter and a negative 32% versus baseline. | 28 | This projection represents an 17% increase over prior quarter and a negative 60% versus baseline. | 61 | This projection represents an 6% increase over prior quarter and a negative 22% versus baseline. | 37 | This projection represents an 8% increase over prior quarter and a negative 26% versus baseline. | 28 | This projection represents an 10% increase over prior quarter and a negative 64% versus baseline. | 100 | This projection represents an 31% increase over prior quarter and a positive 51% versus baseline. This is consistent with Com Net's project improvement plan whereby we indicated that network testing would exceed budget due to the need to test and accept partial route segments in order to satisfy Community Anchor Institution commitments. | 2012-08-08 12:21 | 2012-08-08 12:21 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2012 | Q3 | Q3 - 2012 | 7964 | 6688 | FALSE | 61 | Com Net is planning an aggressive build-out plan for the final quarter of 2012 with 15% progress over prior quarter. This plan is highly dependent on favorable weather. The aggressive plan is made possible through the additional equipment and labor available to the project through KG Myers sub-contracting efforts along with Com Net's pursuing permits and release to KG Myers on all portions of segments where the Authority Having Jurisdiction is permitting the use of direct plow installation. | 100 |  | Project Management and Administrative Reporting liquidated for a positive variance versus baseline of 7%. The 7% positive variance versus baseline is down from 8% from the prior quarter, which represents further gap closure against baseline projections. Contract Sales is projected to continue to be negatively impacted by the network build posting an 8% gain from the prior quarter for a 5% negative variance versus baseline. Operation Support progress based on liquidated expenses is projected to show no gain for the quarter. This continues to be related to two factors. The first is that Com Net did not draw federal funds for the implementation of plant and trouble on its NISC iVUE billing platform as originally planned. The reason for this was due to the fact that NISC is a cooperative and NISC was requiring additional administrative work prior to entering into a contract with Com Net. Com Net determined that the additional administrative expense negated the benefit of using | 100 | All future activity by environmental consultant shall be considered part of construction and/or as a construction permit or other approval | 86 | Com Net will continue to engage Sigma Technologies in association with route design and permitting activities on its pending route modification, as well as, to work with Authorities Having Jurisdiction to obtain outstanding permits and work through any issues that may arise in order to ensure construction crews have adequate mileage permitted for the scheduling of crews. | 72 | Com Net is projecting the spread between baseline and quarterly projections to remain the same as prior quarter with the bulk of the closure to occur in the 1st and 2nd quarter of 2013. | 64 | Permits and other approvals continue to lag behind baseline as the Authorities continue to issue permits marginally ahead of construction. This measurement against liquidated expenses, also, tends to be impacted by the fact that expenses for construction permits and other approvals continue to run favorable to budget. | 56 | Site Preparation work in the upcoming quarter is projected to be limited to outstanding invoices and clean-up work in association with the Wood County, Findlay and Huntsville new construction sites, as well as finalization of power requirements allowing for the transfer of space at Independents Fiber Networks site in Lima, OH. In addition, Com Net will be finalizing the lease of space in Springfield, OH rather than the construction of a new site moving this site to an unfunded operating expense, as well as a capital lease for space at a remote shelter in West Milton, OH. On completion of these activities, Com Net will have one new construction site remaining for completion in the spring in Greenville, OH. | 70 | Com Net's procurement of MPLS network equipment is pending a route modification, which will reduce the amount of equipment to be procured based on Com Net's election to reduce the number of MPLS Network nodes in the regional network. In addition, the acquisition of equipment for the final hut, as well as for ZAYO to equip its PoP sites on its managed routes, will not occur until the Spring of 2013. | 56 | A 31% negative variance versus baseline, but with an 18% increase over prior quarter, which represents significant progress for the final quarter of the year. This 18% increase from the prior quarter is driven by the fact that, throughout the quarter, KG Myers will have four plow trains with accompanying directional drilling crews, as well as thirteen additional directional drilling crews active on the project. Com Net has, also, secured ~7 miles of existing conduit along with an additional 7 miles of currently placed but unoccupied innerduct for the placement of cable during the quarter. ZAYO is projected to upgrade a portion of its aerial plant in the Toledo metropolitan area during the quarter. Finally, since the baseline is measured against liquidated expenses, the percent of progress will increase at a faster pace per mile of cable placed as construction costs increase with the build approaching the Metropolitan areas of Toledo, Dayton, Springfield and Columbus. | 47 | Com Net is projecting the cut-over of Cyan city-pairs during the upcoming quarter, which will move additional equipment from Work-in-Progress to the active working network. This will result in a 14% progress rate over prior quarter, but a negative variance versus budget of 53% as ZAYO is not expected to deploy its equipment until the Spring of 2013 and the deployment of equipment by OARnet during the quarter remains questionable. | 100 | As disclosed in the prior quarter projections, Com Net is experiencing an overrun in network testing/inspection costs as we release partial segments in order to allow for the activation of service to Community Anchor Institutions prior to full segment completion. The budget overrun for network testing will be offset through savings in the areas of equipment procurement and network build. | 2012-11-19 17:59 | 2012-11-19 17:59 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2012 | Q4 | Q4 - 2012 | 8828 | 7612 | FALSE | 72 | Negative 23 percent variance versus baseline. Variance is reduced by 5 percent when evaluated against CNI's forecasted project expenditure total, which is 8.77 percent under budget. | 100 | Application and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | Application and award acceptance period budget continues to be closed at one-hundred percent complete. Project Management and Administrative Reporting are expected to still run ahead of baseline primarily due to the rate of expenditure early in the project associated with reporting administration. Contractual sales will continue to lag behind with Community Anchor Institutions as we continue to work to secure commitments. Operational support systems will continue to lag behind as CNI continues to have Sigma Technologies maintain mapping records as its Route Design and Permitting Firm with final transfer to occur during the last quarter, as well as, CNI's decision not to utilize federal funds on the NISC plant and trouble module upgrade. | 100 | No Variance. | 99 | Positive 2 percent variance versus baseline. This indicates that network design and supporting permit application expenses may exceed budget by a marginal amount. This is based on route changes being requested by authorities having jurisdiction, as well as, having to address areas where underground construction is encountering rock, preventing cost effective underground construction. | 78 | Negative variance of 20 percent versus baseline. This negative variance based on liquidated expenses is partially offset by the fact that the budget category from an expense perspective is projected to come in under budget. | 70 | Negative variance of 30 percent versus baseline. This negative variance based on liquidated expenses is partially offset by the fact that the budget category from an expense perspective is projected to come in under budget | 80 | Negative variance of 20 percent versus baseline. This budget category will remain open; and therefore, behind baseline until project completion as the Greenville hut site preparation activity is not projected to conclude until the final quarter of the project. | 72 | Negative variance of 28 percent versus baseline. This negative variance will persist through the final quarter of the project as CNI's purchase and deployment of MPLS Network equipment is currently pending NTIA approval of a technology change. In addition, ZAYO has indicated it will not be installing equipment until the final quarter of the project to light the facilities in the GigE PLUS project that ZAYO will be responsible for managing. | 68 | Negative variance of 22 percent versus baseline. This variance will persist as CNI does not project completing construction activities until June 2013. | 55 | Negative variance of 55 percent versus baseline. This variance is driven by CNI's decision to hold on the cut-over of city-pairs on the Cyan DWDM equipment until the next software version is released, as well as, due to the delays in equipment procurement, upon which equipment deployment is dependent. | 100 | No variance, however this is due to unfavorable performance on expenses versus budget as this category is in an overrun state. | 2013-02-15 22:38 | 2013-02-15 22:38 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2013 | Q1 | Q1 - 2013 | 9918 | 8500 | FALSE | 84 | Negative variance of 16 percent versus baseline. This variance is driven by CNI's election not to procure and deploy MPLS network equipment until the Cyan equipped city-pairs were activated, delays in sub-recipients purchasing and deploying equipment on the facilities they will be managing and operating as part of the project, and delays associated with the outstanding route modifications. | 100 | Application and Award Acceptance Period, Project Management and Project Administrative Reporting, Contractual Sales and Operation Support Systems | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones continue to lag behind in direct relationship to construction progress as community anchor institutions continue to withhold firm order commitments. Progress on the Operational Support System milestone was closed to within seven percent of baseline in the first quarter of 2013 and is expected to hold at this level unless software or programming expenditures are required to convert CAD drawings into KML files for as-built mapping records. | 100 | No variance versus baseline for planned completion. Actual expenditures against this milestone are closed with all additional environmental assessment work associated with change orders being reported under the Construction Permits and Other Approvals milestone. Actual expenditures for this milestone ran 4 percent over budget. | 88 | Negative variance of 12 percent versus baseline. Network Design expenditures are projected to close out on this milestone slightly under budget. The route design and permitting firm continues to be engaged in establishing a design that the authority having jurisdiction will issue a permit on within the city of Columbus, city of Springfield, city of West Alexandria and Clark county. The route design and permitting firm will also have time and expense involved in finalizing the permits and construction package for two route segments included in the route modification award action request. | 90 | Negative variance of 10 percent versus baseline. The route design and permitting firm is still working to secure permits with the authority having jurisdiction of the city of Columbus, city of Springfield, city of West Alexandria and Clark county. | 73 | Negative variance of 27 percent versus baseline. The expenditures for Construction permits and other approvals are still outstanding with the environmental assessment firm, several railroad companies, pole owners and one private property owner. | 100 | No variance versus baseline. CNI is projecting aggressive progress against this milestone for the quarter. It is anticipated that although the physical work may be completed by the end of the quarter, outstanding expenditures will cause a shortfall versus planned progress for performance progress reporting purposes. | 94 | Negative variance of 6 percent versus baseline. CNI plans to procure and deploy MPLS network equipment during the 2nd quarter of 2013. Furthermore, CNI plans to increase sub-recipient monitoring activities to ensure sub-recipients are progressing with the purchase of equipment and deployment on facilities the sub-recipient will be responsible for operating and managing as part of the project. | 81 | Negative variance of 19 percent versus baseline. CNI projects to come in under budget on this milestone, however several risk areas for potential cost overruns continue to exist. The major area of concern is in association with the cost to construct the route in the city of Dayton if conduit space is not available and/or can not be secured. Progress toward this milestone is dependent on approval of the route modification by May 10, 2013 to allow adequate time to complete the route segments included in the modification. | 45 | Negative variance of 55 percent versus baseline. This is primarily driven by CNI's decision not to procure and deploy MPLS network equipment until after the Cyan DWDM equipped city-pairs are fully deployed. The other reason for the lack of progress versus the milestone is related to the procurement and deployment of equipment by the sub-recipients on facilities they will be operating and managing as part of the project. | 100 | An overrun of 82 percent is projected on liquidated expenditures with respect to this milestone. The reason for the overrun is related to the up front delay in the project before ground disturbing activities could commence. As a result of this CNI modified its plans to test and accept partial segments rather than fully completed segments, which drove-up the cost. CNI also deviated from its original plan to internalize the network testing and inspection function. This plan was abandoned due to the expertise and training requirements not being conducive to the reduced time frame for construction after receipt of the project FONSI. | 2013-05-28 09:59 | 2013-05-28 09:59 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2013 | Q2 | Q2 - 2013 | 10750 | 9040 | FALSE | 97 | Negative variance of 3 percent versus baseline. This is financial only from a liquidated expenses perspective. CNI fully anticipates completing the project based on the milestones set forth as part of the no-cost increase project extension. The overall favorable financial performance is driven through the favorable financial performance on the network build, construction permitting and network design. | 100 | Applications and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones are expected to be complete at 100% as community anchor institution connectivity goals are met as construction progresses to completion. In the 1stquarter of 2013 progress on the Operational Support System milestone was closed to within seven percent of baseline during the quarter with CNI executing on the purchase of the plant records module for its NISC iVUE customer care system. The liquidated expenditures for this milestone are projected to hold at this level as we do not anticipate the need for software or programming expenditures in order to convert CAD drawings into KML files for as-built mapping records. | 100 | No variance versus baseline for planned completion | 94 | Negative variance of 6 percent versus baseline. The network design milestone variance is financial only from a liquidated expenses perspective. The favorable financial performance was related to the saving in permit and right-of-way applications as well as a favorable mix of rural, urban and metropolitan route mileage. | 94 | Negative variance of 6 percent versus baseline. The variance in rights of way tracks with the variance in network design. | 82 | Negative variance of 18 percent versus baseline. CNI fully expects to complete the project. The variance is strictly financial from a liquidated expenses perspective. CNI constructed the majority of its project underground avoiding expensive make ready fees associated with pole attachments. CNI was also able to avoid the need to cross railroad tracks on private property, which dramatically reduced the cost associated with railroad crossing. | 100 | No variance versus baseline. CNI is actually projecting a slight overrun on this budget category primarily driven by costs associated with completing Area of Potential Effect (APE) studies on its prefabricated hut locations as required as part of the EA FONSI. | 100 | No variance versus baseline. CNI is actually projecting a slight overrun of 2% due to the need to secure additional rectifiers and battery back-up equipment at sites where CNI expanded its Cyan DWDM and packet metro Ethernet capabilities rather than deploying MPLS network equipment. | 95 | Negative variance of 5 percent versus baseline. This variance is strictly from a liquidated expenses perspective. Provided CNI receives approval of its route modifications by August 1, 2013 it fully anticipates completing the network build. The favorable financial performance is related to managements ability to secure approval to proceed with the preferred method of construction in areas it originally did not anticipate being able to. | 49 | Negative variance of 51 percent versus baseline. CNI will successfully complete deployment the variance versus baseline is strictly financial from a liquidated expenses perspective. This may require further analysis of professional expenses booked agains equipment procurement and network testing to determine if they should have been applied against equipment deployment as part of the project closeout. | 100 | No variance versus baseline. From a liquidated expenses perspective this category continue to run over budget based on managements decision to accept partial route segments in order to advance the objectives of the BTOP program. | 2013-08-27 06:55 | 2013-08-27 06:55 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570072 | 2013 | Q3 | Q3 - 2013 | 12062 | 10222 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-04-23 11:03 | 2014-04-23 11:03 | 5924 | 5924 | COM Net, Inc.
NT10BIX5570073 | 2010 | Q4 | Q4 - 2010 | 1060 | 2096 | FALSE | 5 | N/A | 100 | Other | Award of contracts = 100%; | 100 | FONSI is expected with no major changes to design. | 100 | N/A | 88 | Anticipate to obtain more permits / franchises by end of the quarter. | 88 | Anticipate to obtain more permits / franchises by end of the quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-10 16:38 | 2011-02-10 16:38 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2011 | Q1 | Q1 - 2011 | 2312 | 2901 | FALSE | 10 | Behind due to delay in obtaining FONSI. | 0 |  | At this time, no other progress milestones exist. | 100 | Delayed due to various items. We expect to receive FONSI next quarter with our team's follow-up reporting on mitigated items and requested monitoring of construction where necessary. | 5 | Network design of GePON complete. Will work with technology vendors to complete the OTN and MOE network designs. | 80 | We are progressing along with ensuring we have the necessary ROW language in place. | 80 | We are progressing along with obtainment of construction permits. Once we receive FONSI, the remaining federal agency permits should flow through. | 0 | If we are able to receive FONSI next quarter, we will start to build at least one leg depending on the attainment of the one outstanding permit. | 80 | We are receiving equipment for all the builds plus the MOE specific equipment. OTN and GePON specific technology will be ordered closer to installation. | 0 | We estimate construction will start either end of June or beginning of July. | 0 | We will install once the network is built. | 0 | This will be done in a later phase of the project. | 2011-05-25 16:50 | 2011-05-25 16:50 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2011 | Q2 | Q2 - 2011 | 3198 | 3359 | FALSE | 27 | Received FONSI and will begin construction | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Anticipate to be complete | 100 | Anticipate to be complete | 30 | We will begin construction of 3 out of the five legs and five GePON builds. | 90 | We have received all materials except for the specific technologies of OTN and GePON. | 1 | Start construction mid September | 0 | Start construction mid September | 0 | The infrastructure will not be completely constructed yet. | 2011-08-18 12:57 | 2011-08-18 12:57 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2011 | Q3 | Q3 - 2011 | 4274 | 3987 | FALSE | 40 | Based on projected dollars expended. | 0 |  | NA | 100 | Complete | 100 | Complete | 98 | One more ROW to receive from private entity for site that will be built in 2012. Anticipate completing by January 2012. | 100 | Complete | 0 | We estimate that we'll be 30% complete with construction in Q1 2012. | 80 | We will award the two remaining equipment technology in Q4 and purchase in Q12012. | 20 | We will start all our main legs by 12/1/2011. We will be back on track with our baseline in Q2 2012. | 0 | Will start in Q2 2012 and complete in Q3 2012. | 0 | The routes will not be complete until 2012. | 2011-11-25 14:44 | 2011-11-25 14:44 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2011 | Q4 | Q4 - 2011 | 5032 | 4702 | FALSE | 53 | Construction progress | 0 | 0 | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 20 | Construction in progress; target project completion Q3 2012. | 100 | Award RFPs and purchase remaining GePON and OTN equipment. | 12 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 0 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 0 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 2012-02-15 12:53 | 2012-02-15 12:53 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2012 | Q1 | Q1 - 2012 | 5972 | 5585 | FALSE | 70 | Four of five main routes complete and begin construction for GePONs. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Construction in progress; target project completion Q3 2012. | 100 | Award RFPs and purchase GePON and OTN equipment. | 80 | Four of five main routes will be complete. Will complete three GePON builds. Target project completion Q3 2012 | 20 | Will complete three GePON builds. Target project completion of all main routes and GePON builds Q3 2012. | 20 | Network testing of three GePON builds. Target project completion of all main routes and GePON builds Q3 2012. | 2012-05-08 15:52 | 2012-05-08 15:52 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2012 | Q2 | Q2 - 2012 | 7038 | 6146 | FALSE | 90 | Complete except for OTN equipment installation | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 2012-08-11 18:42 | 2012-08-11 18:42 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2012 | Q3 | Q3 - 2012 | 8066 | 6739 | FALSE | 97 | 97% budget wise; 99% complete project wise. Final make ready completion/payments | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-11-27 11:04 | 2012-11-27 11:04 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2012 | Q4 | Q4 - 2012 | 8708 | 7513 | FALSE | 97 | 97% budget wise; 99% project wise. Minimal construction for Community Anchor Institutions as they sign their contracts. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-02-11 16:44 | 2013-02-11 16:44 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2013 | Q1 | Q1 - 2013 | 10010 | 8549 | FALSE | 100 | Complete | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-30 14:38 | 2013-05-30 14:38 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570073 | 2013 | Q2 | Q2 - 2013 | 11368 | 9489 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2013-11-24 19:06 | 2013-11-24 19:06 | 5904 | 5904 | Bend Cable Communications, LLC
NT10BIX5570074 | 2010 | Q4 | Q4 - 2010 | 992 | 2034 | FALSE | 3 | Delay in submission of Environmental Assessment and consequential delay in the receipt of Finding Of No Significant Impact has caused all aspects of the project to be delayed. | 0 |  | No Variance | 100 | No Variance from Baseline | 90 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs which affected network design last quarter and again in this quarter. | 25 | After discussions with several of the entities involved in Rights Of Way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the Rights Of Way are currently being processed. | 25 | Unforeseen variables arose during last quarter that delayed the submittal of the Environmental Assessment. While we were able to submit before the due date, we did not submit as early as planned in the baseline, therefore the FONSI was not received as anticipated when the baseline was submitted. This caused a difference in the category again this quarter. | 15 | No Variance from Baseline | 20 | No Variance from Baseline | 1 | When Finding Of No Significant Impact is received we intend to purchase fiber. This expenditure represents the first fiber purchase assuming receipt of Finding Of No Significant Impact. | 0 | No Variance | 0 | No Variance | 2011-02-07 13:01 | 2011-02-07 13:01 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2011 | Q1 | Q1 - 2011 | 2102 | 2796 | FALSE | 6 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | N/A | 100 | No Variance | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 12 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 11 | Since the baseline report was submitted it has become evident to Contact Network Inc. the equipment procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Due to delays in issuing the Equipment request for proposal we are behind in procurement. We will be placing equipment orders this quarter to somewhat catch up in this category versus our initial baseline projections. | 4 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 2011-05-17 17:44 | 2011-05-17 17:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2011 | Q2 | Q2 - 2011 | 2880 | 3197 | FALSE | 18 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance | 100 | No Variance | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 17 | During this quarter a total of fifteen Community Anchor Institutions were connected to our network. The site preparation was complete for these fifteen entities. Our projects for this quarter were to connect a total of twenty-two Community Anchor Institutions. The construction and site preparation for remaining seven institutions were not complete as of June 30, 2011 causing a variance in our projections. | 35 | No Variance | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 17 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-01 14:58 | 2011-08-01 14:58 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2011 | Q3 | Q3 - 2011 | 4122 | 3904 | FALSE | 28 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline. | 100 | No Variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 21 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 21 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 19 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Equipment is being purchased on an as needed basis. | 29 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 19 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Focus will be on the Institutions that have signed contracts, testing will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2011-11-17 17:27 | 2011-11-17 17:27 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2011 | Q4 | Q4 - 2011 | 5344 | 5017 | FALSE | 33 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline | 100 | No variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 25 | Equipment is being purchased on an as needed basis. | 36 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 21 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-02-28 13:35 | 2012-02-28 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2012 | Q1 | Q1 - 2012 | 5942 | 5570 | FALSE | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline. | 100 | No variance from baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 67 | Equipment is being purchased on an as needed basis. | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-05-07 15:04 | 2012-05-07 15:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2012 | Q2 | Q2 - 2012 | 7132 | 6193 | FALSE | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. |  | N/A | No variance from baseline. | 100 | No variance from baseline | 90 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 84 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 84 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 67 | Equipment is being purchased on an as needed basis. | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-08-17 17:16 | 2012-08-17 17:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2012 | Q3 | Q3 - 2012 | 8014 | 6713 | FALSE | 94 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 95 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 70 | Equipment is being purchased on an as needed basis. | 94 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-11-21 11:07 | 2012-11-21 11:07 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2012 | Q4 | Q4 - 2012 | 8848 | 7630 | FALSE | 96 | This percentage is slightly ahead of our projected baseline report | 0 |  | No variance from baseline | 100 | No variance from baseline | 97 | This percentage is slightly ahead of our projected baseline report | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 92% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 92% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 59 | Equipment is being purchased on an as needed basis. | 96 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2013-02-19 16:12 | 2013-02-19 16:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2013 | Q1 | Q1 - 2013 | 9840 | 8456 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-05-20 16:53 | 2013-05-20 16:53 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2013 | Q2 | Q2 - 2013 | 10762 | 9046 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-08-27 13:37 | 2013-08-27 13:37 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | 2013 | Q3 | Q3 - 2013 | 11486 | 9603 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-12-16 13:35 | 2013-12-16 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570075 | 2010 | Q4 | Q4 - 2010 | 1356 | 2371 | FALSE | 34 | NA | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 33 | The timing of our optical equipment purchase has improved, thus the increase in this estimate over baseline. | 25 | This is a bit low due to delay in signing IRU agreement | 10 | The requirement to upgrade core routers so that the existing core routers can be deployed to the peering service has accelerated this activity over baseline. | 0 | NA | 2011-02-24 08:32 | 2011-02-24 08:32 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2011 | Q1 | Q1 - 2011 | 1974 | 2732 | FALSE | 43 | The overall project, in terms of funds spent, is lagging slightly for this particular quarter due to the length of time required to finalize major contracts, as well as the need to realign our rate of purchases so that we do not incur operations costs for facilities longer than required before they have been put in production. We are, however, making progress on improving this metric and expect to have expenditures be on plan by the end of the year. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 46 | We expect to bring this on plan by end of the year. | 70 | We expect to bring this on plan by end of the year. | 30 | We expect to bring this on plan by end of the year. | 0 | NA | 2011-05-12 14:24 | 2011-05-12 14:24 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2011 | Q2 | Q2 - 2011 | 3298 | 3411 | FALSE | 43 | The overall project is lagging slightly for this particular quarter in expenditures due to the length of time required to finalize major contracts, and the need to realign our purchase rate so that we avoid operations costs for facilities longer than required before they have been put in production. We are making progress in improving this metric and expect expenditures be on plan in the near future. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 45 | At this point the project has caught up and slightly passed the baseline. | 30 | We expect to bring this on plan by the end of the year | 44 | NA | 0 | NA | 2011-08-24 16:37 | 2011-08-24 16:37 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2011 | Q3 | Q3 - 2011 | 4180 | 3938 | FALSE | 54 | Our build-out process continues to be on schedule, even ahead of schedule. The buildout schedule includes designing and engineering the segments of the network installation, ordering equipment, receiving and testing equipment, deploying and installing equipment, and final installation testing. Approval and acceptance of all aspects of this process provides the trigger for releasing final payment to vendors. However, in an effort to make certain all of the details in all segments of the build are addressed to our satisfaction, acceptance is withheld until all questions are answered and all remedial actions taken. Payment (expenditure of project dollars) will catch up but currently lags behind the actual production due to the issues noted above. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 55 | This number is slightly behind baseline because approval and acceptance of the equipment determine when payment is made. | 70 | This metric represents the total % of IRUs paid for against the total IRU budget. All segments required for the current phase have been ordered. | 55 | This number is slightly behind baseline because approval and acceptance of the equipment determine when payment is made. Actual deployment is on schedule. | 0 | NA | 2011-11-21 14:28 | 2011-11-21 14:28 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2011 | Q4 | Q4 - 2011 | 5358 | 5026 | FALSE | 65 | Internet2 is expecting to place orders for its third phase of optical networking equipment in the 3rd Quarter of Year 2. Deployment of that equipment is expected to be largely complete by Year 2, Quarter 4, a full year ahead of the project schedule projections. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 68 | Internet2 expects to procure all remaining Phase 3 equipment in Q12012. | 95 | Network design was completed Year 1, Quarter 1. | 68 | Internet2 expects to procure all remaining Phase 3 equipment in Q12012. | 0 | NA | 2012-02-28 14:46 | 2012-02-28 14:46 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2012 | Q1 | Q1 - 2012 | 6094 | 5649 | FALSE | 81 | Internet2 expects to deploy the remaining Phase 3 equipment in Year 2, Quarter 4, nearly a year ahead of project schedule projections with the exception of the Northern Tier route and the remaining router and switch equipment. | 0 | true | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 85 | Internet2 expects to exceed the baseline for this metric in Year 2, Quarter 4. | 95 | Internet2 has completed procurements and installation is ongoing. Once installation, test, turn up, and billing are complete, this metric will catch up with the baseline. | 85 | Internet2 expects to exceed the baseline for this metric in Year 2, Quarter 4. | 0 | NA | 2012-05-15 13:29 | 2012-05-15 13:29 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2012 | Q2 | Q2 - 2012 | 7052 | 6153 | FALSE | 90 | Internet2 expects to catch up to the baseline next quarter in terms of expenditures. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 0 | NA | 2012-08-14 08:15 | 2012-08-14 08:15 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2012 | Q3 | Q3 - 2012 | 8144 | 6782 | FALSE | 94 | Internet2 expects to meet the baseline for this metric. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2012-11-29 14:39 | 2012-11-29 14:39 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2012 | Q4 | Q4 - 2012 | 8978 | 7756 | FALSE | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 100 | Internet2 expects to meet the baseline for this metric in Year 3, Quarter 2. | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 0 | NA | 2013-02-26 14:21 | 2013-02-26 14:21 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2013 | Q1 | Q1 - 2013 | 9856 | 8465 | FALSE | 100 | Internet2 expects to meet the baseline for this metric. | 0 | true | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2013-05-21 17:57 | 2013-05-21 17:57 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570075 | 2013 | Q2 | Q2 - 2013 | 12040 | 10201 | FALSE | 100 | Internet2 expects to meet the baseline for this metric. | 0 | true | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2014-04-15 15:39 | 2014-04-15 15:39 | 5983 | 5983 | University Corporation For Advanced Internet Development
NT10BIX5570076 | 2010 | Q4 | Q4 - 2010 | 1300 | 2329 | FALSE | 3 | Delayed by overlap issue; working to resolve EA action items. Baseline report estimated 5%. | 0 |  | N/A | 100 | Baseline report estimated 100%. | 15 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 25%. Once the FONSI is received, the schedule will be accelerated. | 0 | N/A - Project uses Public Right of Way | 25 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 30%. Once the FONSI is received, the schedule will be accelerated. | 10 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 20%. Once the FONSI is received, the schedule will be accelerated. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-22 14:53 | 2011-02-22 14:53 | 6614 | 6614 | Vermont Telecommunications Authority
NT10BIX5570076 | 2011 | Q1 | Q1 - 2011 | 2414 | 2952 | FALSE | 6 | Once the FONSI has been received, make ready work will begin and the engineering professional services will ramp up to complete the network design and move the project to the construction phase. This ramp up will bring the project closer to the original target spend and will enable the project to meet the 67% timeline after 8 quarters. Much of the project expense will come from the fiber optic cable and construction costs which will ramp up after the FONSI is received and the project moves into the construction phase. | 0 | N/A | N/A | 100 | Waiting for final approval from National Telecommunications and Information Administration (NTIA) | 19 | The project design on which an engineering firm would work could have been impacted by changes to the project implemented to mitigate environmental impacts. As a result, Sovernet decided to dedicate the time of key staff to completing work on the EA and delay completing the engineering firm RFP process. SFC has selected an engineering firm who is very familiar with our project and has extensive experience with fiber build projects. After consulting with them, we feel confident that we can proceed quickly with network design and reach our original target spend rates by the end of the first quarter of 2012. | 0 | Project uses public rights of way | 40 | SFC has made pole attachment license applications for over 5500 (20%) poles and pole surveys are ongoing. We will continue to pursue additional pole applications once the FONSI is released. SFC expect 30% of pole attachment license applications to be completed by June 2011. | 28 | Previously delayed by overlap issue; working to resolve EA action items. The completion of pole make ready work was held up pending the lifting of the EA SAC, and we do not expect any pole make ready work to be completed by the end of June 2011. | 0 | N/A | 0 | N/A | 4 | Expect to file colocation applications this quarter | 0 | N/A | 2011-05-31 17:24 | 2011-05-31 17:24 | 5890 | 5890 | Vermont Telecommunications Authority
NT10BIX5570076 | 2011 | Q2 | Q2 - 2011 | 3126 | 3320 | FALSE | 8 | Spending on work planned: continue core route surveying, additional make ready work; develop plans, specifications, Request For Questions's and Request For Proposal's for cable, Oust Side Plant construction, and Dense Wavelength Division Multiplexing network equipment. Much of the spending on this project will be for construction and purchase of fiber optic cable. Work on network design will set the stage for further increases in spending in coming quarters as the project moves into the construction phase. Please note that, consistent with NTIA guidance, the overall planned percent complete represents funds spent as a share of total project budget. | 0 |  | N/A | 50 | Our baseline projection stated 100% by the end of the next quarter. The projection is lower because the Finding of No Significant Impact was obtained at less than the cost budgeted. However, we may incur additional expense on the Environmental Assessment relative to archaeological work or route modifications. | 25 | Our baseline projection was 50% by the end of the next quarter. The projection is lower because network design was deferred pending issuance of the Finding of No Significant Impact and resolution of overlap issues that may have affected network design. Network design activities during the next quarter will include developing plans, specifications, RFQ's and RFP's for cable, outside plant construction and Dense Wave Division Multiplexing network equipment. | 0 | N/A | 57 | Our projected spending for the next quarter is ahead of baseline plan. Continue to survey core route and apply for pole attachment licenses. | 28 | Our baseline projection was 50% by the end of the next quarter. The projection is lower because route selection was deferred pending of resolution of overlap issues that may have affected the location of sites in need of preparation. | 1 | Our baseline projection was 20% by the end of the next quarter. The projection is lower because we deferred the selection of an engineer firm pending issuance of the Finding of No Significant Impact and resolution of overlap issues. Dense Wavelength Division Multiplexing testing equipment was ordered in June and will be received in this quarter. | 0 | The baseline projection was 30%. The projection for the next quarter is lower because route selection, network design make-ready requests were deferred pending resolution of overlap issues and issuance of the Finding of No Signficiant Impact. Sovernet Fiber Corp. does not anticipate construction spending before September 30, 2011. However, we anticipate significant spending on construction in subsequent quarters as make-ready work is completed. | 15 | Sovernet Fiber Corp. anticipates additional spending in the next quarter on colocation augments and additional colocation applications. Our baseline projection for the next quarter was 0%. | 0 | The baseline projection was 20%. The projection for the next quarter is lower because construction of the network was deferred pending resolution of overlap issues and issuance of the Finding of No Signficiant Impact. Testing will converge with our baseline projection in coming quarters as network is constructed and lit. | 2011-08-16 14:56 | 2011-08-16 14:56 | 6334 | 6334 | Vermont Telecommunications Authority
NT10BIX5570076 | 2011 | Q3 | Q3 - 2011 | 4148 | 3922 | FALSE | 13 | Make-ready surveys and work will continue during the quarter. Construction of 90 route miles of outside plant will begin during the quarter. Compilation of a bid package for over 200 miles of additional outside plant construction will be started this quarter. In addition, design, permitting, and make-ready that is prerequisite to further construction will continue. No CAI's will be connected during the quarter. Discussion of service arrangements between SFC and broadband wholesalers and last-mile providers will continue. In most cases, service agreements will not be entered until shortly before service can be turned up. Accordingly, no agreements are anticipated during the next quarter. | 48 | Admin & Legal Expenses |  | 46 | Additional expenses will be incurred if route modifications are proposed. | 30 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. SFC will continue to identify parcels for which rights-of-way must be obtained, and where necessary will contact property owners to obtain easements or other consents. | 80 | SFC will continue to request make-ready surveys and apply for pole attachments. Rail permits covering approximately one quarter of the project's total route miles will be submitted during the quarter. | 22 | SFC anticipates applying for attachments to roughly 5,500 utility poles -- slightly over 20% of those required for the project -- in the next quarter. The total applied for by end of quarter will be approximately 77% of those required for the project. | 2 | A primary vendor will be selected and engaged during the quarter to provide the packet optical electronic equipment for the network. RFP's will be released for routing and Operations Support Systems. | 9 | Outside plant construction activity and associated contracts is proceeding in waves, as network design is completed, permits obtained and make-ready completed. Construction of approx. 90 route miles will begin this quarter as well as the fiber service entry to a building that serves as a major network hub for an community anchor institution. We anticipate strand will be attached to poles on approximately 50 route miles by the end of the quarter. A bid package for Outside Plant Construction for over 200 miles should be approximately 80% complete by the end of the quarter. No new network miles will be leased. | 15 | SFC anticipates applying for collocations at most remaining sites during the quarter. Owners of collo sites are expected to take the full 91 days allowed under tariffs to review the applications and perform the build out of the space. Several collo projects already initiated are expected to complete. SFC will begin to install equipment in collo sites when site owners provide notices of completion. | 5 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing was made to reflect anticipated fiber testing and network verification. Other than pre-deployment testing of fiber delivered by vendors, network testing will follow completion of network segments, construction of which was delayed pending resolution of grant overlap issues and issuance of the Finding of No Significant Impact. | 2011-11-18 16:14 | 2011-11-18 16:14 | 6334 | 6334 | Vermont Telecommunications Authority
NT10BIX5570076 | 2011 | Q4 | Q4 - 2011 | 5196 | 4865 | FALSE | 24 | Overall spending should reach 24% of the award by the end of the quarter as fiber-optic cable purchases continue and outside plant construction accelerates. Construction should be complete on roughly 92 miles of outside plant. Contracts will be released and construction in progress for approximately 300 miles of outside plant. Bids requests covering as much as 486 miles of plant will be released. Primary vendors for packet optical equipment and routers will be selected during the quarter. Design and fit-up of collocation facilities will continue. SFC anticipates obtaining additional CAI service commitments, including for libraries and K-12 schools that will close their e-rate open solicitations during the quarter. | 58 | Admin & Legal |  | 74 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work that may be required is not known at present. | 49 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. SFC will continue to identify parcels for which rights-of-way must be obtained, and where necessary will contact property owners to obtain easements or other consents. | 82 | Make-ready surveys will be requested for an additional 2,300 utility poles during the quarter, bringing the total surveyed to roughly 81% of those required for completion of the project. | 32 | Winter weather conditions and shorter work days will reduce make-ready productivity. Accordingly, the pace of make-ready work and expenditures may be slower than in the previous quarter. SFC anticipates authorizing, during the quarter, make-ready work on roughly 3,600 utility poles -- slightly over 15% of those required for the project -- in the next quarter. By end of quarter, make-ready work will have been authorized for approximately 75% of those required for the project. | 16 | Equipment Procurement expenditures are presently expected to increase substantially in 2Q2012 and 3Q2012, as contracts with electronics vendors are executed and equipment ordered. An RFP for IP router equipment will be issued. Vendors will be selected and engaged during the quarter for packet optical equipment and IP routers. A portion of the packet optical network equipment will be purchased. | 19 | Assuming AAR's pending for route revisions are timely approved, the bulk of construction of the first 90 miles awarded will be completed by the end of the quarter. A contract will be entered, and construction started on the second bid package (62 miles). Overall, we estimate construction will be completed by end of quarter on 92 route miles, with strand attached on another 20 to 50 route miles. Six separate outside plant construction bid packages covering all remaining core/backbone routes as well as a large portion of lateral routes, covering over 550 route miles overall, should be released during the quarter. Bids on four of the six packages will be due during the quarter. | 6 | SFC will apply for collocations at the 6 remaining third-party sites during the quarter. We anticipate the 6 collo sites will be turned over to SFC during the quarter. | 0 | Network testing will follow completion of OSP construction. Slower-than-expected completion of make-ready has delayed completion of OSP construction. | 2012-02-22 17:34 | 2012-02-22 17:34 | 6334 | 6334 | Vermont Telecommunications Authority
NT10BIX5570076 | 2012 | Q1 | Q1 - 2012 | 6002 | 5600 | FALSE | 39 | Initial purchase orders for packet optical network equipment and routers will result in a signficant pick-up in spending during the quarter, as will the start of construction for several more bid packages. Overall spending should reach 38% of the award by the end of the quarter. Construction should be complete on roughly 200 miles of outside plant. Contracts will have been released for six bid packages, comprising about 750 miles of outside plant. Design and fit-up of collocation facilities will continue. SFC anticipates obtaining additional CAI service commitments. | 75 | Admin & Legal Expenses | Other expenses are expected to be roughly in line with budget. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 60 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC expects that route surveys for the entire project will be substantially complete by the end of the quarter. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Make-ready surveys will be requested for an additional 1,500 utility poles during the quarter, bringing the total requested to roughly 84% of those required for completion of project. | 46 | "Given mild Spring weather conditions and a substantial queue of pole make-ready requests pending with pole owners, SFC anticipates pole owners wil complete make-ready and issue pole attachment licenses for a substantial number of poles during the quarter. SFC anticipates authorizing, during the quarter, make-ready work on roughly 3,600 utility poles â€“ slightly over 15% of those required for the project. By end of quarter, make-ready work will have been authorized for approximately 19,500 (83)% of poles required for the project. SFC estimates pole-owners will have completed make-ready work and issued attachment licenses for roughly 12,000 poles (51%) by the end of the quarter, though not entirely in contiguous segments." | 28 | Equipment Procurement expenditures are expected to increase substantially in 2Q2012 and 3Q2012. Contracts for both packet optical and router equipment, which comprise substantially all of the budget for this category, should be executed in the quarter, with equipment purchase orders to follow shortly thereafter. | 34 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 175 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs, bringing the cumulative total to approximately 200 miles. Two additional bid packages for all remaining outside plant construction should be released during the quarter, with the goal of starting construction on one before the end of the quarter and on the other early in 3Q2012. | 39 | SFC anticipates three additional collocations will be released to SFC by the end of the quarter. | 20 | Network testing will follow completion of OSP construction. An initial network segment will likely be ready for testing during this quarter. | 2012-05-10 10:30 | 2012-05-10 10:30 | 6334 | 6334 | Vermont Telecommunications Authority
NT10BIX5570076 | 2012 | Q2 | Q2 - 2012 | 7242 | 6248 | FALSE | 44 | Additional purchase orders for packet optical network equipment will result in a significant pick-up in spending during the quarter, as will the start of construction for several more bid packages. Overall spending should reach 43% of the award by the end of the quarter. Construction should be complete on roughly 300 miles of outside plant, with contracts in place for all network segments. Design and fit-up of collocation facilities will continue. Packet electronic equipment, ordered late in 2Q2012, with a cost of $2.4 million, will be installed. Additional equipment orders will be placed. Packet electronic equipment will be installed and turned-up on several core network routes. SFC anticipates obtaining additional CAI service commitments. | 95 | Admin & Legal Expenses | Other expenses are expected to be roughly in line with budget. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 78 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC route surveys for the entire project are substantially complete at the start of of the quarter. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Make-ready surveys will be requested for substantially all remaining utility poles during the quarter. | 53 | SFC anticipates authorizing, during the quarter, make-ready work on roughly 2,500 utility poles. By end of quarter, make-ready work will have been authorized for approximately 20,800 (87%) (another 2,400 during quarter) of poles required for the project. SFC estimates pole-owners will have completed make-ready work and issued attachment licenses for roughly 16,500 (70%) by the end of the quarter, though not entirely in contiguous segments. | 36 | Equipment Procurement expenditures are expected to increase substantially in 3Q2012. The contract for packet optical equipment, the largest dollar equipment contract, was executed late in 2Q2012. The initial $2.4 million service order will be received during the quarter. A contract for router equipment will be entered during the quarter, and purchase orders placed. | 36 | Overall, SFC estimates approximately 200 route miles of cable will be placed during the quarter, depending primarily on the extent to which make-ready is completed on contiguous runs, bringing the cumulative total to approximately 300 route miles. | 43 | SFC anticipates three additional collocations -- all but one -- required for the project -- will be released to SFC by the end of the quarter. | 20 | Select core network routes will be tested during the quarter, once core electronic equipment is installed and continuous network routes are place. | 2012-08-24 16:01 | 2012-08-24 16:01 | 6334 | 6334 | Vermont Telecommunications Authority
NT10BIX5570076 | 2012 | Q3 | Q3 - 2012 | 8146 | 6783 | FALSE | 57 | Overall spending should reach 56% of the award by the end of the quarter. Construction should be complete on roughly 480 miles (cumulative) of outside plant. Additional packet optical and router equipment will be installed, tuned, tested and placed in service. SFC anticipates obtaining additional CAI service commitments. Service over the VFC network to several CAI locations will be initiated during the quarter. | 100 | Admin & Legal Expenses |  | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 92 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC expects that route surveys for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Through the preceding quarter, surveys have been requested for approximately 95% of the utility poles involved in the project. Any remaining surveys are likely to be associated with minor route or design changes. In addition, permit applications will continue to be submitted for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. | 62 | Given the substantial volume of pending make-ready requests pending with pole owners, SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 3,000 poles during the quarter, bringing the total to 19,500 poles (roughly 83% of those required for the project). SFC anticipates authorizing, during the quarter, make-ready work an additional 2,500 utility poles â€“ slightly over 10% of those required for the project. | 66 | During the quarter, additional DWDM nodes will be ordered and installed. Additional network segments will be lit as fiber construction is completed. IP routers are expected to be delivered, and preliminary installs started, during the quarter, with the majority of testing and turn-up occurring in 1Q2013. | 46 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 190 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs and on degree to which winter weather conditions restrict roadside construction. Construction of several core network routes should be completed during the quarter. | 47 | All but one collocation site has been licensed and fitted-up. SFC anticipates obtaining a license for the one additional collocation site during 1Q2013. | 25 | Network testing will follow completion of OSP construction. One or more network segments will likely be tested during this quarter. | 2012-11-29 14:39 | 2012-11-29 14:39 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2012 | Q4 | Q4 - 2012 | 8782 | 7580 | FALSE | 78 | Overall spending should reach 78% of budget by the end of the quarter. Construction should be complete on roughly 610 miles (cumulative) of outside plant. Additional packet optical and router equipment will be installed, tuned, tested and placed in service. SFC anticipates obtaining additional CAI service commitments. Service over the VFC network to additional CAI locations will be initiated during the quarter. | 100 | na | na | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 97 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Route surveys for the entire project are substantially complete, other than for route changes that require NTIA approval. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Most remaining permits, including for railroad crossings, interstate highway crossings, work along municipal and state roadways and land-use permits will be applied for during the quarter. | 73 | SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 2,900 poles during the quarter, bringing the total to 21,000 poles (roughly 89% of those required for the project). SFC will submit the majority of remaining pole applications, primarily in New Hampshire, during the quarter. | 100 | Packet optical equipment will be installed and tested at two additional network notes. IP routers will be tested and turned-up during the quarter. | 59 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 230 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs and on degree to which winter weather conditions restrict roadside construction. Construction of several additional core network routes should be completed during the quarter. | 70 | The one remaining collocation site is likely to be released to SFC and fit-up during 2Q2013. | 35 | Network testing will continue to follow completion of OSP construction. | 2013-02-14 15:52 | 2013-02-14 15:52 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2013 | Q1 | Q1 - 2013 | 9944 | 8515 | FALSE | 83 | With approximately 13% of pole license requests still pending with pole owners at the start of the 2nd quarter, and permits needed for certain network segments, roughly 110 miles of outside plant have yet to be released to construction. Remaining routes will be released for construction as permits and pole attachment licenses allow. The volume of network miles and service locations released to construction will continue remaining pole attachment licenses and permits are obtained. 183 miles of aerial plant will be placed, leaving approximately 150 miles to place to complete the project. Electronics installation is on track for completion before outside plant construction. 30 CAI locations are scheduled be connected, with design and construction continuing on the remaining locations. | 100 | 100 | Administration of the project is in-going. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 100 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Route surveys for the entire project are substantially complete. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Most remaining permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits will be obtained during the quarter. | 77 | SFC had requested make-ready for over 98% of poles as the start of the quarter, and obtained licenses on 87%. SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 2,300 poles during the quarter, bringing the total to 22,800 poles (roughly 97% of those required for the project). | 100 | DWDM nodes will be ordered, received and installed. | 70 | SFC estimates outside plant construction will be completed on 183 network miles, dependant on quantity of pole licenses issued by pole owners, make-ready is completion on contiguous runs, and receipt of permits. 150 miles will remain for completion of the project. | 100 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 45 | Network testing will continue to follow completion of OSP construction. | 2013-05-28 16:27 | 2013-05-28 16:27 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2013 | Q2 | Q2 - 2013 | 10426 | 8855 | FALSE | 95 | Delays have been stated above and in previous PPRs concerning the overall project variances. | 100 | NA | Administration of the project is ongoing. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys for the entire project are substantially complete. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to obtain easements or other consents where required. | 100 | Almost all permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits have been obtained. The remainder are expected to be received during this quarter. | 72 | As of the start of the quarter, SFC had requested make-ready for all poles involved with the project, and obtained licenses on 94%. SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for the remaining 1,360 poles. | 100 | Installation, configuration and launch of all remaining routers and DWDM nodes will be completed during the quarter. | 84 | Core and lateral outside plant will be completed during the quarter on the remaining 159 network miles, although completion requires issuance of attachment licenses issued by pole owners and on obtaining permits and property owner consents. Installation of entrances, drops and electronics for a portion of service locations will carry over into 4Q2013. 260 CAI locations should be ready for service by end of 3Q2013, and all CAI locations are projected to be ready for service by October 31, 2013. | 100 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 55 | Network testing will continue to follow completion of OSP construction. | 2013-07-30 21:15 | 2013-07-30 21:15 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2013 | Q3 | Q3 - 2013 | 11422 | 9532 | FALSE | 100 | The project will be completed during 4Q2013. Construction of the Vermont FiberConnect network, and installation of facilities all remaining community anchor institutions and points of interconnection will be completed. | 100 | Administration | Administration of the project is on-going, and will be completed during the quarter with the exception of award close-out. | 100 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time, but are likely to be insignificant given the late stage of the project. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits will be obtained during the quarter. | 100 | Pole owners will issue pole attachment licenses and complete make-ready for the remaining [5]% of poles. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 100 | The remaining 46 miles of aerial plant will be placed. All remaining core network segments will be lit, tested and configured, as will electronics serving the remaining CAI locations. | 100 | All remaining core network segments will be tested, configured and lit, as will be electronics to the remaining CAI locations. | 100 | Network testing is on-going, and will be completed during the quarter, as OSP construction is completed. | 2013-11-27 12:20 | 2013-11-27 12:20 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2013 | Q4 | Q4 - 2013 | 12638 | 10905 | FALSE | 99 | Construction of the remaining miles of core network routes will be completed. Most permits and land-owner access consents required for construction of the remaining 20 Points of Interconnection will be obtained. Although the network is presently carrying traffic and providing service, installation, testing and configuration of the network will continue to implement its full capabilities. | 100 | Administration | Administration of the project is on-going, and will be completed during the quarter with the exception of award close-out. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time, but are likely to be insignificant given the late stage of the project. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including land-use permits and for interstate highway crossings will be obtained during the quarter. | 75 | Complete. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 83 | The remaining fiber will be placed on core network routes. All remaining core network segments will be lit, tested and configured, as will electronics serving the remaining CAI locations. | 90 | All remaining core network segments will be lit, tested and configured, as will be electronics to the remaining CAI locations. | 0 | This budget category has been included in line 2h above. Network testing continues through this period. Network testing is on-going until all construction is completed and any performance defects identified during contract close-out and testing are corrected. | 2015-01-21 14:19 | 2015-01-21 14:19 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2014 | Q1 | Q1 - 2014 | 12750 | 11084 | FALSE | 99 | Remaining permits and property owner consents will be obtained during 2Q2014 for the remaining 27 points of interconnection, or an Award Action Request will be submitted to move the demarc locations of any remaining points. In most instances, construction will be completed during 2Q2014, although a portion may extend in to 3Q2014. Installation, testing and configuration of network electronics will continue in order to enable the network's full capabilities. Project engineers will continue to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. | 100 | Administration | Administration of the project is on-going, and will be completed during the next two quarters with the exception of award close-out. | 49 | Additional expenses are likely to be insignificant given the late stage of the project. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including land-use permits and for interstate highway crossings will be obtained during the quarter. | 75 | Complete. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 86 | Construction will continue on laterals to reach the remaining POIs. All remaining core network segments will be lit, tested and configured. | 100 | All remaining core network segments will be lit, tested and configured. | 0 | This budget category has been included in line 2h above. Network testing continues through this period . Network testing is on-going until all construction is completed and any performance defects identified during contract close-out and testing are corrected. | 2015-03-20 10:58 | 2015-03-20 10:58 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2014 | Q2 | Q2 - 2014 | 12756 | 11087 | FALSE | 100 | Other than close-out activities, the project is expected to be completed by the end of the quarter (September 30, 2014). | 100 | Administration | Administration of the project is on-going, and will be completed during the quarter with the exception of award close-out. | 100 | Additional expenses are likely to be insignificant given the late stage of the project. | 100 | An engineering firm will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including land-use permits, will be obtained during the quarter. | 100 | Complete. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 100 | The remaining 5 miles of fiber will be placed. All remaining core network segments will be lit, tested and configured, as will electronics serving the remaining CAI locations. | 100 | All remaining core network segments will be lit, tested and configured, as will be electronics to the remaining CAI locations. | 0 | This budget category has been included in line 2h above. Network testing continues through this period . Network testing is on-going until all construction is completed and any performance defects identified during contract close-out and testing are corrected. | 2015-03-20 17:15 | 2015-03-20 17:15 | 5928 | 5928 | Vermont Telecommunications Authority
NT10BIX5570076 | 2014 | Q3 | Q3 - 2014 | 12764 | 11094 | FALSE | 100 | Project complete at 101% of budget. | 100 | Administration & Legal, Miscellaneous | Project complete at 158% of budget. | 100 | Project complete at 49% of budget. | 100 | Project complete at 105% of budget. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. | 100 | Project complete at 121% of budget. | 100 | Project complete at 74% of budget. | 100 | Project complete at 141% of budget. | 100 | Project complete at 90% of budget. | 100 | Project complete at 114% of budget. | 0 | A separate budget for Network Testing was not established, as network testing services were included in Network Build. | 2015-03-26 16:23 | 2015-03-26 16:23 | 5890 | 5890 | Vermont Telecommunications Authority
NT10BIX5570077 | 2010 | Q4 | Q4 - 2010 | 786 | 1823 | FALSE | 4 | No variance | 0 |  | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-28 15:20 | 2011-01-28 15:20 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2011 | Q1 | Q1 - 2011 | 2388 | 2939 | FALSE | 23 | Ahead of projection based on earlier construction start than anticipated. | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 100 | NO VARIANCE | 0 | N/A | 10 | Ahead of the projected 0% based on the accelerated proposed schedule of the acceptable responsive bidder. | 20 | Ahead of the projected 0% based on the accelerated proposed schedule of the acceptable responsive bidder. | 0 | NO VARIANCE | 0 | NO VARIANCE | 2011-05-27 15:19 | 2011-05-27 15:19 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2011 | Q2 | Q2 - 2011 | 3212 | 3367 | FALSE | 60 | Accelerated construction by the Outside Plant Contractor | 0 |  | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 100 | No variance | 0 | No variance | 10 | No variance | 80 | Accelerated construction by the Outside Plant Contractor | 0 | No variance | 0 | No variance | 2011-08-18 17:44 | 2011-08-18 17:44 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2011 | Q3 | Q3 - 2011 | 4040 | 3860 | FALSE | 83 | Accelerated construction schedule | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 20 | Accelerated construction schedule | 68 | Accelerated construction schedule | 20 | No variance | 20 | No variance | 2011-11-14 17:04 | 2011-11-14 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2011 | Q4 | Q4 - 2011 | 5428 | 5114 | FALSE | 86 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 2012-03-01 09:46 | 2012-03-01 09:46 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2012 | Q1 | Q1 - 2012 | 6020 | 5609 | FALSE | 98 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 2012-05-10 15:08 | 2012-05-10 15:08 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2012 | Q2 | Q2 - 2012 | 6992 | 6123 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 2012-08-09 18:31 | 2012-08-09 18:31 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2012 | Q3 | Q3 - 2012 | 8032 | 6722 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 2012-11-26 12:10 | 2012-11-26 12:10 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2012 | Q4 | Q4 - 2012 | 9018 | 7791 | FALSE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-02-27 14:15 | 2013-02-27 14:15 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570077 | 2013 | Q1 | Q1 - 2013 | 10050 | 8581 | FALSE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 2013-06-04 11:50 | 2013-06-04 11:50 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2010 | Q4 | Q4 - 2010 | 1322 | 2347 | FALSE | 5 | No variance | 0 |  | N/a | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-23 10:24 | 2011-02-23 10:24 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2011 | Q1 | Q1 - 2011 | 1760 | 2623 | FALSE | 20 | NO VARIANCE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 100 | NO VARIANCE | 0 | N/A | 0 | NO VARIANCE | 20 | Ahead of the 0% projected based on the construction contractor's accelerated schedule as planned. | 10 | Ahead of the 0% projected based on the construction contractor's accelerated schedule as planned. | 0 | NO VARIANCE | 2011-04-29 18:14 | 2011-04-29 18:14 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2011 | Q2 | Q2 - 2011 | 3214 | 3368 | FALSE | 60 | SLIGHTLY AHEAD OF SCHEDULE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 10 | NO VARIANCE | 20 | NO VARIANCE | 20 | NO VARIANCE | 20 | NO VARIANCE | 2011-08-18 18:10 | 2011-08-18 18:10 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2011 | Q3 | Q3 - 2011 | 4184 | 3940 | FALSE | 54 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | No Variance | 10 | No Variance | 45 | Accelerated construction schedule | 20 | No Variance | 20 | No Variance | 2011-11-21 15:22 | 2011-11-21 15:22 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2011 | Q4 | Q4 - 2011 | 5350 | 5022 | FALSE | 57 | Variance is due to construction halt during winter weather and recipient budget cycle | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 10 | No Variance | 37 | Variance is due to anticipated construction progress | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 2012-02-28 14:08 | 2012-02-28 14:08 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2012 | Q1 | Q1 - 2012 | 6022 | 5610 | FALSE | 61 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 75 | No Variance | 45 | No Variance | 45 | No Variance | 65 | No Variance | 2012-05-10 15:10 | 2012-05-10 15:10 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2012 | Q2 | Q2 - 2012 | 6938 | 6096 | FALSE | 91 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 80 | Variance due to construction progress and anticipation of project completion by year-end | 50 | No Variance | 50 | No Variance | 70 | Variance due to construction progress | 2012-08-08 17:04 | 2012-08-08 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2012 | Q3 | Q3 - 2012 | 8034 | 6723 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Variance due to accelerated construction progress | 2012-11-26 12:14 | 2012-11-26 12:14 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2012 | Q4 | Q4 - 2012 | 9132 | 7914 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Variance due to accelerated construction progress | 2013-03-06 18:29 | 2013-03-06 18:29 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570078 | 2013 | Q1 | Q1 - 2013 | 11432 | 9547 | FALSE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-03 11:30 | 2013-12-03 11:30 | 5935 | 5935 | Silver Star Telephone Company, INC.
NT10BIX5570079 | 2010 | Q4 | Q4 - 2010 | 1000 | 2044 | FALSE | 10 | Consistent with Baseline | 0 | CAI Connection | Consistent with Baseline | 100 | Consistent with Baseline | 39 | Consistent with Baseline | 43 | Consistent with Baseline | 40 | Consistent with Baseline | 15 | Consistent with Baseline | 16 | Consistent with Baseline | 3 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 2011-02-07 19:01 | 2011-02-07 19:01 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2011 | Q1 | Q1 - 2011 | 2064 | 2777 | FALSE | 11 | Under projected 27% Baseline - delays from make-ready, anchor site changes and related design changes, and Railroad permits. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 12 | CAI Connection | Under projected 18% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. This is not based on budget but actual % of connected CAI sites. With several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 0 | Under projected 100% baseline - percentage completed based on grant funding - EA currently funded outside of the grant so 0% grant funding completion. Actual project completion is 85% as the initial FONSI has been received. Current work is monitoring and EA amendments. Future activities may impact this funding. | 39 | Under projected 57% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 0 | Under projected 56% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is expected to be 50% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind. This will adjust when approved to reflect change in ROW accounting. | 0 | Under projected 60% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is estimated to be 40% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind and will cause break out of permitting from design budget. | 12 | Under projected 30% Baseline - delays from make-ready, anchor site changes and related design changes, and building code issues. This is not based on budget as actual site preparation of anchor sites is responsibility of CAI, this is based on the % of anchor sites expected to be connected. | 8 | Under projected 38% Baseline - delays from make-ready, anchor site changes and related design changes, and anticipated vendor delays. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. Award Action Request to adjust In-Kind budget will also adjust this as anchor site equipment will no longer be counted but moved to ROW. | 8 | Under projected 16% Baseline - delays from make-ready, anchor site changes and related design changes, and anticipated vendor delays. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. As a design/build project, this also includes costs of fiber which will incur large procurements over next 2 quarters. | 12 | Under projected 25% Baseline - delays from make-ready, anchor site changes and related design changes, CAI purchasing delays due to budget cuts. This is not based on budget but actual % of connected CAI sites. | 0 | Under projected 10% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. | 2011-05-16 18:36 | 2011-05-16 18:36 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2011 | Q2 | Q2 - 2011 | 3106 | 3310 | FALSE | 33 | Under projected 43% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 12 | CAI Connection | Below the projected 55 of Baseline - currently waiting for FODU installation to connect CAI sites and signing of Service Agreements. Expect next quarter the CAI sites to rapidly begin connection. Once Award Action Request for route change is submitted and approved - expected next quarter - the completion of lateral connections to CAI will progress quickly. | 95 | Next quarter the Award Action Request for route change should be submitted with associated Environmental Amendment - waiting for approval. | 49 | Under projected 76% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 50 | Under projected 68% baseline - recently approved budget Award Action request for change to RoW for matching has caused change in process to recognize RoW. Accounting and approval process for RoW quickly adjusting to document RoW - will soon be at 100%. | 55 | Under projected 80% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 35 | Under projected 45% baseline - This is not based on budget as actual site preparation of anchor sites is responsibility of CAI, this is based on the % of anchor sites expected to be connected. Will quickly escalate as the FODUs are completed and CAI sign the Service Agreement. | 0 | NA | 35 | Consistent with Baseline - total 66 miles of 180 projected miles completed | 0 | NA | 0 | Should commence this next quarter as the FODU installations progress. | 2011-08-16 00:46 | 2011-08-16 00:46 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2011 | Q3 | Q3 - 2011 | 4164 | 3930 | FALSE | 46 | Under projected 56% baseline - due to delays from Portland General Electric make-ready, RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 11 | CAI Connections | Below the projected 68% of Baseline - currently waiting for Fiber Optic Distribution Units (FODU) installation to connect anchor site sites and signing of Service Level Agreements. Once Award Action Request for route change is submitted and approved - the completion of lateral connections to anchor site will progress quickly. Expect to reach baseline projections by 2012 Q1 or Q2. | 97 | The Award Action Request for route change will be submitted with associated Environmental Amendment. | 90 | Over projected 86% baseline â€“ Fiber route through Canby and Highway 26 will be resolved and the design finalized by end of Q4. | 77 | At projected 77% baseline. Project to have 2 more cities in next quarter for total of 7 of 9. | 90 | At projected 90% baseline - due to delays from city RoWâ€™s permitting/franchising. Once these issues are resolved, escalated construction should realign with baseline over next few quarters. | 85 | Over projected 70% baseline - This is not based on budget as actual site preparation of anchor sites is responsibility of anchor site, this is based on the % of anchor sites expected to be connected. Will quickly escalate as the Fiber Optic Distribution Units (FODU) are completed and anchor sites sign the Service Level Agreement. | 0 | N/A | 41 | Under projected 43% Baseline - total 75 miles of 180 projected miles completed. | 0 | N/A | 7 | Under projected 36% baseline-Two of the three Fiber Optic Distribution Units (FODU) installed and tested. Phases 1A and 2 fully tested. Once FODU is installed in Sandy, escalation of testing will realign with baseline. | 2011-11-20 17:37 | 2011-11-20 17:37 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2011 | Q4 | Q4 - 2011 | 5060 | 4730 | FALSE | 68 | Under projected 71% baseline - due to delays regarding RoW permitting/franchising, route changes and related design changes. Construction should realign with baseline over next few quarters. | 31 | CAI Connection | Under projected 82% baseline - Waiting for more signed Service Level Agreements from anchor sites. Once Award Action Request for route change is submitted and approved, the completion of lateral connections to anchor sites will progress quickly. Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 99 | An Award Action Request for route changes will be submitted with associated Environmental Amendments. Excluding the possibility of a re-route around Oregon City, all EA has been completed with the exception of the 2.3 mile section along Highway 26. | 87 | On target with projected 87% baseline â€“ Fiber route from Molalla through Oregon City will be resolved and the design finalized by end of Q2. | 78 | Under projected 82% baseline â€“ Rights of Way still need to be approved through Oregon City and Canby. We expect Rights of Way to realign with projected baseline by the end of Q2 2012 by reaching an agreement with the City of Canby. | 90 | Continue to stay on target with projected 90% baseline. | 90 | Over projected 80% baseline. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 56 | Under projected 61% Baseline â€“ total of 100 miles completed by the end of Q1 out of 180 total project miles. We expect network build to realign with projection during Q2 2012. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 41 | Under projected 52% baseline for reasons previously stated. We expect network testing to realign with projections in Q2 2013. | 2012-02-15 20:37 | 2012-02-15 20:37 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2012 | Q1 | Q1 - 2012 | 5904 | 5551 | FALSE | 79 | Under projected 82% baseline - due to delays regarding RoW permitting/franchising, route changes and related design changes. Construction should realign with baseline by end of Q3 2012. | 71 |  | Under projected 96% baseline - Waiting for more signed Service Level Agreements from anchor sites. Once Award Action Request for route change is submitted and approved, the completion of lateral connections to anchor sites will progress quickly. Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 87 | Under projected 100% baseline - With some difficulties with a couple municipalities, we are exploring a new route for phase 5. The Environmental Assessment is underway for the phase 5 route change and will accompany an Award Action Request by the end of Q3 2012. | 87 | Under projected 89% baseline â€“ Fiber route for phase 5 will be resolved and the design finalized by end of Q3 2012. We plan on submitting an Award Action Request to get approval of the final route. | 88 | Over projected 87% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q3 2012. | 90 | Continue to stay on target with projected 90% baseline | 95 | Continue to stay on target with projected 95% baseline. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 78 | Over projected 74% Baseline â€“ total of 130 miles completed by the end of Q2 2012 out of 167 total project miles. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 61 | Under projected 68% baseline for reasons previously stated. We expect network testing to realign with projections in Q3 2013. | 2012-05-01 20:49 | 2012-05-01 20:49 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2012 | Q2 | Q2 - 2012 | 6830 | 6041 | FALSE | 93 | Meeting projected 93% baseline. | 89 |  | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete | 97 | Over projected 95% baseline. All phases will be designed with the exception of the 4 miles for the Portland General Electric relocation project located on Mt Hood. | 89 | Under projected 94% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q4 2012. | 98 | Continue to stay on target with projected 98% baseline. | 100 | Complete | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 95 | Over projected 87% Baseline â€“ total of 158 miles completed by the end of Q3 2012 out of 167 total project miles. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 93 | Over projected 84% baseline. | 2012-08-01 17:10 | 2012-08-01 17:10 | 5569 | 5569 | Clackamas, County of
NT10BIX5570079 | 2012 | Q3 | Q3 - 2012 | 7894 | 6651 | FALSE | 95 | Under projected 99% baseline. | 98 |  | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete. | 100 | Design will be complete. | 78 | Under projected 100% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q4 2012. | 100 | Complete. | 100 | Complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% Baseline â€“ total of 165 miles completed by the end of Q4 2012 out of 169 total project miles. The last 4 miles will be complete when Portland General Electric finishes their reliability project on Highway 26 to Government Camp. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. Once Portland General Electric finishes their work on HWY 26, we can then install the last 4 miles of the network and test the Government Camp spur. This will complete the testing of the network. We expect the final testing to be complete by the end of Q2 2013. | 2012-11-15 10:31 | 2012-11-15 10:31 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2012 | Q4 | Q4 - 2012 | 8894 | 7682 | FALSE | 97 | Under projected 100% baseline. The project will not realign with baseline until Q2 2013. | 98 | Anchor Site Connection | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete | 98 | Under projected 100% baseline. The project will realign with baseline once PGE finalizes the design on HWY 26. | 78 | Under projected 100% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q2 2013. | 99 | The permitting will realign with baseline when PGE finalizes their design for HWY 26. | 100 | Complete | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% Baseline â€“The last 5 miles will be complete by the end of Q2 2013. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. Once Portland General Electric finishes their work on HWY 26, we can then install the last 4 miles of the network and test the Government Camp spur. This will complete the testing of the network. We expect the final testing to be complete by the end of Q2 2013. | 2013-02-21 20:17 | 2013-02-21 20:17 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2013 | Q1 | Q1 - 2013 | 9854 | 8464 | FALSE | 100 | Project complete. Project completion is actually 101%, but we can only enter up to 100% in the box. We are at 101% because we have booked an additional $134,556 in in-kind match. | 100 |  | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 2013-05-21 17:44 | 2013-05-21 17:44 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2013 | Q2 | Q2 - 2013 | 10682 | 9002 | FALSE | 100 | Project complete. Project completion is actually 101%, but we can only enter up to 100% in the box. We are at 101% because we have booked an additional $134,556 in in-kind match. | 100 |  | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 2013-08-21 15:17 | 2013-08-21 15:17 | 5568 | 5568 | Clackamas, County of
NT10BIX5570079 | 2013 | Q3 | Q3 - 2013 | 11946 | 10111 | FALSE | 100 | N/A. Project is complete. | 100 | N/A | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 2014-03-13 10:03 | 2014-03-13 10:03 | 5569 | 5569 | Clackamas, County of
NT10BIX5570080 | 2010 | Q4 | Q4 - 2010 | 1250 | 2280 | FALSE | 30 | No Deviation from the Baseline | 0 |  | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 2011-02-20 21:39 | 2011-02-20 21:39 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2011 | Q1 | Q1 - 2011 | 2242 | 2866 | FALSE | 11 | Due to the delay in receipt of a FONSI, OnWav's will still be not have been able to begin and expend funds related to components of the deployment which have the FONSI as a prerequisite until more than half way through the quarter. | 26 | OSS-BSS Support | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 6 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 2011-05-23 10:11 | 2011-05-23 10:11 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2011 | Q2 | Q2 - 2011 | 3236 | 3380 | FALSE | 12 | Due to the delay in receipt of a FONSI, OnWav will need to rush to finalize work and contracts to expend funds and begin deployment. OnWav is revising its budget and plan in order to facilitate a faster deployment and funds expenditure. | 0 | BSS-OSS | OnWav's plans for BSS and OSS systems have been demporarily put on hold pending the 3rd party match support. OnWav is working on a plan which will not only bring progress on this category back to schedule, but complete it early. In the meantime, progress will be slow until the new plan can be implemented. OnWav hopes to have this resolved by the end of 2011 if not sooner. | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | OnWav is expecting to experience some delays in this category due to a technology change facilitated by a new relationship with a 3rd party. Once this is complete, OnWav plans to aggressively move forward with deployment. The technology change itself will not impact this category, however the planning associated with it needs to be complete prior to begin. OnWav does not expect delays to last longer than 1 quarter. | 6 | OnWav is expecting to experience some delays in this category due to a technology change facilitated by a new relationship with a 3rd party. Once this is complete, OnWav plans to aggressively move forward with deployment. The technology change itself will not impact this category, however the planning associated with it needs to be complete prior to begin. OnWav does not expect delays to last longer than 1 quarter. | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No Deviation from the Baseline | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No Deviation from the Baseline | 2011-08-19 14:10 | 2011-08-19 14:10 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2011 | Q3 | Q3 - 2011 | 4292 | 3996 | FALSE | 53 | OnWav plans to have completed the entire matching contribution, as well as begun funding many of the more expensive components of its network deployment. | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems were temporarily put on hold pending the 3rd party match support and the pending change in ownership. OnWav has a plan which will not only bring progress on this category back to schedule, but complete it early. OnWav hopes to have this resolved by the end of the next quarter. | 100 | No Deviation from the Baseline | 100 | OnWav anticipates having hired an RF Engineering firm which will have completed work finalizing OnWav's network design based on a newly chosen equipment vendor. | 100 | OnWav anticipates having completed all necessary leasing and land acquisition related to the new towers and collocation sites. | 50 | OnWav anticipates making substantial progress on this category. However, many of the necessary steps may required extensive time durations, and so OnWav will be working to catch up, but may not be successful. This work has been delayed by the process of getting the initial FONSI as well as the delays resulting from the pending change in ownership | 10 | OnWav anticipates beginning work on new tower construction, however only a small portion of the total cost of the tower construction is expected to be paid upfront. There will be substantial opportunity for OnWav to exceed this goal and OnWav will take advantage of that if possible. | 25 | OnWav anticipates choosing an Equipment vendor and making an initial order. While most equipment will not arrive before the end of the next quarter, OnWav anticipates accepting delivery of some equipment immediately, and placing deposits on other orders. | 100 | OnWav anticipates completing acquisition of 100% of IRUs planned for in the network. | 0 | No deviation from the baseline next quarter. OnWav may be able to deploy a very small portion of equipment next quarter, however the majority will not be available for deployment until next year. Some of the delay in getting the 3rd party match funding has propagated to delay this milestone, but OnWav is has made efforts to minimize that effect. | 0 | No Deviation from the Baseline | 2011-11-28 16:41 | 2011-11-28 16:41 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2011 | Q4 | Q4 - 2011 | 5126 | 4792 | FALSE | 54 | OnWav's progress in early 2012 will revolve predominantly around completion of the awarding of the Equipment and Tower construction RFPs and initial work on those fronts. OnWav anticipates that it will be back on schedule in early 3rd Quarter 2012 | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems are pending finalization based on the Equipment Contract award. However, once this is complete, OnWav expects it will not only bring progress on this category back to schedule, but complete it early. | 100 | OnWav's Environmental assessment is complete, however OnWav will be conducting additional environmental work to create an EA amendment covering the additional work related to the planned fiber network. | 100 | OnWav has hired an RF Engineering firm which will be able to complete work finalizing OnWav's network design based on chosen equipment vendor's offering. | 100 | No Variance from baseline | 50 | OnWav anticipates making progress in this category. However, this is dependent on the timing of the award of the tower construction RFP and the completion of the necessary engineering work. | 50 | OnWav anticipates awarding the tower construction RFP as well as completing the engineering work for the new towers. As a result, OnWav should be able to begin work related to site preparation for the new towers. | 25 | OnWav anticipates choosing an Equipment vendor and making an initial order. While most equipment will not arrive before the end of the next quarter, OnWav anticipates accepting delivery of some equipment immediately, and placing deposits on other orders. | 99 | The final portions of the fiber network build will not be finalized until tower construction and site leasing is complete so that all portions of fiber can be constructed and deployed. | 0 | OnWav will deploy a very small portion of equipment next quarter, predominately related to the fiber network and the portion for which the IRU was recently signed. However the majority will not be available for deployment until the equipment vendor is chosen and new equipment arrives, which is likely to be delayed until next quarter. | 0 | No Deviation from the Baseline | 2012-02-17 18:04 | 2012-02-17 18:04 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2012 | Q1 | Q1 - 2012 | 5968 | 5583 | FALSE | 62 | OnWav's progress in Q2 2012 will revolve predominantly around completion of contracts and beginning of work related to Equipment and Tower construction contracts, including the installation of the first site and initial customers. OnWav anticipates that it will be back on schedule in early 3rd Quarter 2012 | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems are pending finalization based on the Equipment Contract award. However, once this is complete, OnWav expects it will not only bring progress on this category back to schedule, but complete it entirely. | 100 | OnWav's Environmental assessment is complete, however OnWav will be conducting additional environmental work to create an EA amendment covering the additional work related to the planned fiber network. OnWav expects to receive the SHPO and FWS concurrences, and submit the EA-Amendment to NTIA in Q2 2012. | 100 | OnWav has hired an RF Engineering firm which will be able to complete work finalizing OnWav's network design based on chosen equipment vendor's offering. | 100 | No Variance from baseline | 50 | OnWav anticipates making progress in this category. However, this is dependent on the timing of the signing of the tower construction contract and the completion of the necessary engineering work. | 50 | OnWav anticipates signing the tower construction Contract as well as completing the engineering work for the new towers. As a result, OnWav should be able to begin work related to site preparation for the new towers. | 25 | OnWav anticipates signing an Equipment contract and making an initial order. OnWav has already arranged with the vendor for the initial equipment and initial site installation to be entirely completed in the next quarter. | 99 | The final portions of the fiber network build will not be finalized until environmental clearance is received. | 15 | OnWav anticipates having the first RAN site up and running with customers active. | 0 | No Deviation from the Baseline | 2012-05-08 14:25 | 2012-05-08 14:25 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2012 | Q2 | Q2 - 2012 | 7070 | 6162 | FALSE | 78 | OnWav expects to show significant progress on this project during the next quarter. OnWav's equipment has already mostly arrived, and should be invoiced soon. Tower construction is expected to make considerable progress on Towers in late Q3. The first two collocation sites should be completed. | 100 | BSS/OSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q3 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | No deviation from baseline | 100 | No Deviation from baseline | 100 | OnWav expects to have permits for all sites by the end of Q3 2012 | 50 | OnWav expects to have begun site preparation on all three new tower constructions, however depending on timing of the remaining construction permits, work may not complete until Q4 2012 | 89 | OnWav expects that all equipment will be delivered and a large fraction of it installed and turned-up in the field by the end of Q3 2012 | 100 | OnWav hopes to have the final tribal clearance completed in time to construction the remaining portion of the fiber network prior to the end of Q3 2012 | 50 | OnWav anticipates having 2 of the 6 sites deployed with 3 more in progress by the end of Q3 2012. | 0 | N/A | 2012-08-15 09:05 | 2012-08-15 09:05 | 6335 | 6335 | ONWAV INC.
NT10BIX5570080 | 2012 | Q3 | Q3 - 2012 | 7938 | 6673 | FALSE | 83 | OnWav expects to show significant progress on this project during the next quarter. Tower construction is expected to make considerable progress on Towers in late Q4. | 100 | BSS/OSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q4 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 100 | OnWav expects to have permits for all sites by the end of Q4 2012 | 100 | OnWav expects to have completed site preparation on all three new tower constructions. | 100 | OnWav expects that the final pieces of equipment (generators) will be delivered and a large fraction of it installed and turned-up in the field by the end of Q4 2012 | 100 | OnWav expects to construct the remaining portion of the fiber network prior to the end of Q4 2012 | 83 | OnWav anticipates having 5 of the 6 sites deployed with the final one to be completed in early 2013. | 0 | N/A | 2012-11-16 17:21 | 2012-11-16 17:21 | 7560 | 7560 | ONWAV INC.
NT10BIX5570080 | 2012 | Q4 | Q4 - 2012 | 8820 | 7608 | FALSE | 87 | OnWav made significant progress on this project during the last quarter, which is not entirely represented by the money spent. OnWav's three new towers are under construction. Foundations are complete and ground work is nearly complete. The CAIs in the first two markets are nearly entirely turned up. Due to the delay between work complete and invoice date, payment for this work will not show up until Q1 2013. | 100 | OSS/BSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q4 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has commenced. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Initial construction has begun at the fully prepared sites. | 100 | OnWav has received the final pieces of equipment (generators) and expects that final payments will be complete in Q1 2013 | 100 | OnWav expects to construct the remaining portion of the fiber network prior to the end of Q1 2013 | 83 | OnWav anticipates having 5 of the 6 sites deployed with the final one to be completed in early 2013. | 0 | N/A | 2013-02-15 16:30 | 2013-02-15 16:30 | 7560 | 7560 | ONWAV INC.
NT10BIX5570080 | 2013 | Q1 | Q1 - 2013 | 9636 | 8350 | FALSE | 93 | OnWav expects to make significant progress on this project during the next quarter, in particular with invoices and payments for work completed. OnWav will make substantial progress towards completion of installation at it's final site. Additionally, OnWav expects to near its target number of CAIs connected | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. OnWav will have completed the final Acceptance and testing Procedure. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers for the the lease agreements for the collocation sites. OnWav has reached agreement with the owner of the final collocation site and expects to sign a lease in early Q2 2013 | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 100 | OnWav expects to have all legal documents complete on the newly constructed fiber. OnWav expects new fiber for the final, 6th, site to be active and lit and be finalizing legal documents for the new fiber. | 100 | OnWav expects to have all 6 of the 6 sites complete with CAIs active on the entire network. | 0 | N/A | 2013-05-08 17:58 | 2013-05-08 17:58 | 7560 | 7560 | ONWAV INC.
NT10BIX5570080 | 2013 | Q2 | Q2 - 2013 | 10758 | 9044 | FALSE | 93 | OnWav expects to make significant progress on this project during the next quarter, in particular with invoices and payments for work completed. OnWav will complete installation at it's final site. Additionally, OnWav expects to reach its target number of CAIs connected. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. OnWav will have completed the final Acceptance and testing Procedure. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that will serve as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 99 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 100 | OnWav expects to have all 6 of the 6 sites complete with CAIs active on the entire network. | 0 | N/A | 2013-08-27 11:02 | 2013-08-27 11:02 | 7560 | 7560 | ONWAV INC.
NT10BIX5570080 | 2013 | Q3 | Q3 - 2013 | 11872 | 10044 | FALSE | 100 | OnWav anticipates completing the closeout process on schedule, including paying all remaining invoices and closing all active contracts. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that serves as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is deployed. | 100 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 100 | OnWav has activated 6 of the 6 sites with CAIs active on the network. | 0 | N/A | 2014-02-24 12:08 | 2014-02-24 12:08 | 7560 | 7560 | ONWAV INC.
NT10BIX5570081 | 2010 | Q4 | Q4 - 2010 | 1092 | 2132 | FALSE | 6 | Consistent with Baseline. | 19 | Project management; financial compliance. | Level-spend project management. | 100 | Consistent with Baseline. | 35 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 9 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2011-02-11 16:22 | 2011-02-11 16:22 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2011 | Q1 | Q1 - 2011 | 2170 | 2830 | FALSE | 28 | Consistent with Baseline. | 28 | Finance, Project Management, Compliance | Consistent with Baseline. | 100 | Complete. | 40 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 48 | Consistent with Baseline. | 7 | Consistent with Baseline. | 14 | Consistent with Baseline. | 7 | Consistent with Baseline. | 2011-05-19 11:46 | 2011-05-19 11:46 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2011 | Q2 | Q2 - 2011 | 3038 | 3276 | FALSE | 37 | Consistent with Baseline. | 37 | Finance, Project Management, Compliance. | Consistent with Baseline. | 100 | Complete. | 50 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 48 | Consistent with Baseline. | 26 | Consistent with Baseline. | 27 | Consistent with Baseline. | 26 | Consistent with Baseline. | 2011-08-12 11:16 | 2011-08-12 11:16 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2011 | Q3 | Q3 - 2011 | 4076 | 3881 | FALSE | 42 | Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 66%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. | 44 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 100 | Completed. | 60 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 58 | Equipment procurement slowed slightly, as DC-CAN could not deploy equipment as quickly as desired, due to a lack of installed fiber to connect to anchors. Original baseline was 90%. OCTO's DC-Net commits to procurement levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 26 | Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 30 | Equipment can only be deployed to new and upgraded anchors, and to megaPOPs, as planned. While we will have procured approximately 50% of equipment, we estimate approximately 30% of DC-CAN project equipment will have been deployed by Dec 2011. Original baseline was 41%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 26 | Network testing can only be completed against installed fiber and anchors. Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 2011-11-16 15:52 | 2011-11-16 15:52 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2011 | Q4 | Q4 - 2011 | 5360 | 5028 | FALSE | 44 | Delays in the DC-CAN project caused by fiber procurement may take longer than next quarter to catch up with the baseline. Revised forecast is 44%; original baseline was 66%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. A new fiber procurement is currently out for public bid, through District's Office of Contracts and Procurement (OCP). A contract is expected to be awarded in early March. | 55 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. OCTO's DC-Net commits to levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. | 100 | Completed. | 70 | Consistent with Baseline Target. | 0 | N/A | 0 | N/A | 0 | N/A | 61 | Original baseline was 90% of total Equipment budget. Revised forecast is 61%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. DC-Net is managing the DC-CAN equipment purchases consistent with the Community Anchor turnup, to support more just-in-time delivery of equipment. | 37 | Original baseline was 51% of total. Revised forecast is 37%. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 44 | Original baseline was 51% of total. Revised forecast is 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 36 | Original baseline was 51% of total. Revised forecast is 36%. Testing efforts are proportional to the amount of fiber installed. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 2012-02-28 15:02 | 2012-02-28 15:02 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2012 | Q1 | Q1 - 2012 | 6166 | 5685 | FALSE | 56 | OCTO's DC-Net commits to spending levels of 56% for the quarter ending June 30, 2012. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for three reasons. First, some CAIs originally proposed have closed. Second, some CAIs have longer-term service contracts in place with their existing service providers, preventing them from signing onto DC-CAN during the grant period. Third, some CAIs are unable to justify the switch to DC-CAN, as the savings from current services are not significant enough to justify the transition costs. To assure a sufficient set of CAIs, we have submitted route modification requests, seeking approval of a modified set of community anchors. Upon approval, DC-CAN anticipates not more than four (4) months to complete deployment of the newly-approved anchors. | 64 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. | 100 | Completed. | 80 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Original baseline was 100% of project total. As earlier committed, OCTO's DC-Net commits to equipment procurement levels of at least 67% for the quarter ending June 30, 2012. | 52 | Original baseline was 64% of project total. DC-CAN target is eighty-seven (87) miles of fiber installed, or 50% of project total. For new CAIs, DC-CAN target is ninety-two (92) CAIs, or 41% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, of 100% of target. Approximately 20 wireless access points (WAPs) will be installed at operational CAIs. DC-CAN target is to install one (1) new point of inter-connection (POI), to bring the total to four (4) operational POIs, or 40% of project total. We have submitted route modification requests, seeking approval of a modified set of community anchors. Upon approval, DC-CAN anticipates not more than four (4) months to complete deployment of the newly-approved anchors. These pending CAI changes will finalize the fiber route plan. With new shipments of fiber being ordered, the earlier shortages of fiber will no longer be a constraint on fiber installation. Fiber network build will be behind th | 67 | Original baseline was 64% of project total. For new Community Anchor Institutions (CAIs), DC-CAN target is ninety-two (92) CAIs, or 41% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, of 100% of target. DC-CAN target is to install one (1) new point of inter-connection (POI), to bring the total to four (4) operational POIs, or 40% of project total. As CAIs and POIs are turned up, equipment will be immediately deployed. Once submitted route modifications are approved, equipment will be deployed as soon as possible to contracted CAIs and committed POIs. | 51 | Original baseline was 64% of project total. Revised forecast is 51%, proportional to the amount of fiber installed (87 miles) of the planned fiber installed for the project (173 miles). | 2012-05-17 18:24 | 2012-05-17 18:24 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2012 | Q2 | Q2 - 2012 | 7202 | 6228 | FALSE | 67 | OCTO's DC-Net commits to spending levels of 67% for the quarter ending September 30, 2012. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for three reasons. First, some CAIs originally proposed have closed. Second, some CAIs have longer-term service contracts in place with their existing service providers, preventing them from signing onto DC-CAN during the grant period. Third, some CAIs are unable to justify the switch to DC-CAN services, as the savings from current services are not significant enough to justify the transition costs and effort. With the route modifications now approved, we have a sufficient set of new CAIs. We anticipate most of those new CAIs will be installed and operational this quarter, with the remainder completed by end October 2012. | 69 | Finance, Project Management, Reporting, Compliance. | Original baseline was 73% of project total. Projected total will be slightly behind baseline target. | 100 | Completed. | 90 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 67% for the quarter ending September 30, 2012. | 64 | Original baseline was 73% of project total. DC-CAN target is one hundred ten (110) miles of fiber installed, or 64% of project total. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to seven (7) operational POIs, or 50% of project total. With the receipt of new fiber, DC-CAN will have installed one hundred ten (110) miles of new fiber by end September, 2012. DC-CAN will be above the two-thirds (2/3) mark of one hundred eighteen (118) miles of fiber installed by December 2012. | 65 | Original baseline was 74% of project total. For new CAIs, DC-CAN target is one hundred thirty-two (132) by quarter end, or 59% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, or 100% of target. Approximately sixty (60) wireless access points (WAPs) will be installed at operational CAIs, representing 21% of target total of 291. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to seven (7) operational POIs, or 50% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 64 | Original baseline was 73% of project total. Revised forecast is 64%, proportional to the amount of fiber installed (110 miles) of the planned fiber installed for the project (173 miles). | 2012-08-21 17:22 | 2012-08-21 17:22 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2012 | Q3 | Q3 - 2012 | 8116 | 6765 | FALSE | 73 | OCTO's DC-Net commits to spending levels of 73% for the quarter ending December 31, 2012. Original baseline had projected project would be 93% complete at this point. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for several reasons (e.g. - planned CAI sites being closed, or CAIs committed to longer-term service contracts with other providers). | 74 |  | Original baseline was 82% of project total. Projected total will be slightly behind baseline target. | 100 | Completed. | 90 | Baseline had indicated project would be 100% complete with Network Design next quarter. Due to selection of final community anchor institutions (CAIs), final route design will not be complete until quarter following next. | 0 | N/A | 0 | N/A | 0 | N/A | 71 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 71% for the quarter ending December 31, 2012. | 72 | Original baseline was 86% of project total. DC-CAN target is one hundred twenty-five (125) miles of fiber installed, or 72% of project total. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to nine (9) operational POIs, or 64% of project total. With the receipt of new fiber, DC-CAN will have installed one hundred twenty-five (125) miles of new fiber by end December 2012. DC-CAN will be just below the three-quarter (3/4) mark for fiber installed. | 72 | Original baseline was 87% of project total. For new CAIs, DC-CAN target is one hundred fifty-five (155) by year end, or 70% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, or 100% of target. Approximately eighty (80) wireless access points (WAPs) will be installed at operational CAIs, representing 27% of target total of 291. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to nine (9) operational POIs, or 64% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 72 | Original baseline was 86% of project total. Revised forecast is 72%, proportional to the amount of fiber installed (125 miles) of the planned fiber installed for the project (173 miles). | 2012-11-28 15:16 | 2012-11-28 15:16 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2012 | Q4 | Q4 - 2012 | 8942 | 7724 | FALSE | 86 | OCTO's DC-Net commits to spending levels of 86% for the quarter ending March 31, 2013. Original baseline had projected project would be 94% complete at this point. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for several reasons (e.g. - planned CAI sites being closed, or CAIs committed to longer-term service contracts with other providers). DC-CAN expects to have just the one existing partner agreement executed by the end of the quarter, with DC Access. | 91 | Finance, Project Management, Compliance, Reporting | Original baseline was 91% of project total. Consistent with Baseline target. | 100 | Completed per Baseline. | 100 | Baseline had indicated project would be 100% complete with Network Design next quarter. Due to selection of final community anchor institutions (CAIs), final route design will not be complete next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 86 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 86% for the quarter ending March 31, 2013. | 85 | Original baseline was 88% of project total. DC-CAN target is one hundred fifty-four (154) miles of fiber installed, or 88% of project total. DC-CAN target is for three (3) additional points of inter-connection (POI), bringing the total to twelve (12) operational POIs, or 86% of project total. | 85 | Original baseline was 87% of project total. For new CAIs, DC-CAN target is one hundred eighty-five (185) by year end, or 83% of project total of 223. All sixty-eight (68) upgraded CAIs are complete. Approximately one hundred one (101) wireless access points (WAPs) will be installed at operational CAIs, representing 45% of target total of two hundred twenty-three (223) new CAIs. WAP installation at upgrade sites is pending NTIA approval. DC-CAN target is for three (3) additional points of inter-connection (POI), bringing the total to twelve (12) operational POIs, or 86% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 88 | Original baseline was 88% of project total. Revised forecast is 88%, proportional to the amount of fiber installed (154 miles) of the planned fiber installed for the project (173 miles). | 2013-02-25 16:17 | 2013-02-25 16:17 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2013 | Q1 | Q1 - 2013 | 9824 | 8448 | FALSE | 88 | Office of the Chief Technology Officer (OCTO) will be applying for a three-month no-cost extension of the grant project through September 30, 2013, to permit completion of two of the committed program goals: for installed community anchor institutions (CAIs) and for rooftop wireless access points (WAPs). Assuming approval of final route modification quickly, DC-CAN will make every effort to meet all its project goals. All equipment will be purchased, all fiber installed, and WAPs will be installed as approved. As per the guidance for PPR reports, overall project progress is measured by the proportion of total program spend. DC-CAN expects to spend all the grant money consistent with the approved end of the grant period. If an extension is approved, that will permit DC-CAN to make all of its WAP goal. | 100 | Finance, Reporting, Compliance, Project Management | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. | 90 | All equipment will be deployed per plan, except that only one hundred fifty (150) wireless access points (WAPs) will be installed, of a planned two hundred ninety-one (291). | 100 | Per Baseline. Network testing includes testing of the fiber, and for all installed equipment. At locations where only fiber is installed (and where equipment is not installed, due to potential customers electing not to receive service at present), testing will obviously not include uninstalled equipment. Everything installed will be tested; hence 100%. | 2013-05-20 12:41 | 2013-05-20 12:41 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2013 | Q2 | Q2 - 2013 | 10688 | 9005 | FALSE | 100 | Office of the Chief Technology Officer (OCTO) commits that the entire federal grant will be spent, along with its recipient match contribution, consistent with the award agreement. All program goals committed in the Baseline will be met. OCTO will start with grant closeout activities. | 100 | Finance, Reporting, Compliance, Project Management | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. Network testing includes testing of the fiber, and for all installed equipment. At locations where only fiber is installed (and where equipment is not installed, due to potential customers electing not to receive service at present), testing will obviously not include uninstalled equipment. Everything installed will be tested, and therefore 100%. | 2013-08-21 15:47 | 2013-08-21 15:47 | 5943 | 5943 | District of Columbia Government
NT10BIX5570081 | 2013 | Q3 | Q3 - 2013 | 11500 | 9623 | FALSE | 100 | Completed as committed. | 100 | Finance, Project Management, Reporting, Compliance | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 2013-12-18 12:26 | 2013-12-18 12:26 | 5943 | 5943 | District of Columbia Government
NT10BIX5570082 | 2010 | Q3 | Q3 - 2010 | 182 | 1357 | FALSE | 8 | RFP selections will be made by Dec 2010; construction contracts drafted | 10 | Project Management | Project reporting and tracking along with outreaching taking place | 47 | Filing for SHPO review and state review will be completed | 56 | RFP responses will solidify pathways and design | 0 | In Progress | 3 | Pole Attachment Agreements will be underway | 0 | In Progress | 7 | Early construction contracts will begin to complete make-ready | 0 | In Progress | 0 | In Progress | 0 | In Progress | 2010-10-28 10:50 | 2010-10-28 10:50 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2010 | Q4 | Q4 - 2010 | 1246 | 2276 | FALSE | 6 | Variance - 2%; Delay in construction start due to RFP negotiations. | 22 | Project Mgmnt. | Consistent with Baseline Plan. | 100 | Consistent with Baseline Plan. | 62 | Consistent with Baseline Plan. | 1 | Consistent with Baseline Plan. | 19 | Consistent with Baseline Plan. | 0 | Delay in vendor contract completion may result in lower than expected progress in Q1 2011. | 8 | Equipment purchases in multiple stages to take advantage of early fiber. | 3 | Delay in vendor contract completion may result in lower than expected progress in Q1 2011. | 5 | Consistent with Baseline Plan. | 0 | Consistent with Baseline Plan. | 2011-02-20 14:39 | 2011-02-20 14:39 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2011 | Q1 | Q1 - 2011 | 2110 | 2800 | FALSE | 9 | -15%; Construction was delayed due to lengthy contract negotiations with vendors. We are planning to be back on baseline by end of Q5. | 19 | Proj. Mngmnt. | -12%; Expect recovery with completed contract negotiations for all project areas in this quarter. | 100 | Consistent with Baseline Plan. | 67 | -13%; Related to construction delay caused by extended contract negotiations with vendors. Anticipate recovery in next quarter. | 0 | -18%; Related to construction delay caused by extended contract negotiations with vendor. Project tasks have been completed in this area that has not yet incurred project funds draw. We anticipate an update in recovery in the next quarterly report. | 21 | -17%; Related to construction delay caused by extended contract negotiations with vendor. Project tasks have been completed in this area that has not yet incurred project funds draw. We anticipate an update in recovery in the next quarterly report. | 0 | -100%; Only the NHDOT project has site prep needs and this is slated to start in the following quarter (Q5/Summer 2011). | 2 | -8%; Purchases being held off until construction vendors are signed. | 0 | -6%; Related to construction delay caused by extended contract negotiations with vendors. Anticipate recovery in next quarter. | 9 | -18%; Purchases being held off until construction vendors are signed. Anticipate moderate gains. | 1 | -2%; Anticipate recovery through next quarter. | 2011-05-17 18:11 | 2011-05-17 18:11 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2011 | Q2 | Q2 - 2011 | 3088 | 3301 | FALSE | 13 | (Baseline 42% - Variance from baseline is -29%. We anticipate accellerated progress as vendor work progresses. | 40 | Project Management | (Baseline 40% - anticipate no variance in baseline) On track to meet baseline | 100 | Complete | 80 | (Baseline 92% - Variance from Baseline is -12%) FastRoads will be hiring a construction vendor (Q5) and once that occurs, it is expected much of the remaining Network Design will be addressed. | 25 | (Baseline 44% Variance from baseline is -19%) Awaiting results of required Make Ready estimates - unknown at this time as to actual costs and timeframes that will be required to complete this work. Anticipate Make-Ready estimates to be returned in earnest in Q5 and Q6. | 10 | (Baseline 53% Variance from baseline is -43%) Dependent on rights of way make ready work. | 0 | (Baseline 100% Variance from baseline is -100%) NHDOT's site preparation will be complete in 2012. Originally planned for 2011. The DOT portion of the project budget is 10%. | 20 | (Baseline 20% - anticipate no variance in baseline) Working with vendors to acquire fiber. There could be challenges in delivery from vendors as current quotes do not offer any commitments to a delivery timeframe. DWDM equipment phase 1 equipment will be invoiced. A substantial portion of the microwave equipment will be ordered. | 5 | (Baseline 15% - Variance from baseline is -10%) Dependent on rights of way make ready work. NH Department of Transportation delay and all project vendor hire delays will push this activity into subsequent quarters. | 0 | (Baseline 35% - Variance from baseline is -35%) Dependent on success in equipment procurement. | 0 | (Baseline 8%- Variance from baseline is -8%) Dependent on success in equipment procurement, make ready work, and construction work. | 2011-08-15 16:29 | 2011-08-15 16:29 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2011 | Q3 | Q3 - 2011 | 4078 | 3882 | FALSE | 26 | Baseline 50% We continue to work with utilities to process payments for Make Ready work in as soon as estimates are received and validated. We are also seeking opportunities to increase throughput on pole licensing requests with utility stakeholders. We will be addressing building entrance connections to CAIs in the coming quarter. | 35 | Project Management | Baseline was estimated at 48% and was based on project plan activity. Our project plan indicates we will be at 44%. Percent of budget expended is projected at 35%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 100 | Complete | 75 | Baseline was estimated at 95% and was based on project plan activity. Our project plan indicates we will be at 80%. Percent of budget expended is projected at 75%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. Once the FastRoads engineering and construction RFP is awarded in October we will work with the vendor to obtain a revised timeline on remaining network design work. | 100 | Baseline was estimated at 68% and was based on project plan activity. Percent of budget expended is N/A as there are no financial expenditures budgeted for Rights of Way. Project activity for this category has been moved to the Site Preparation category. Going forward the projection will continue to be 100. | 48 | Baseline was estimated at 58% and was based on project plan activity. Our project plan indicates we will be at 21%. Percent of budget expended is projected at 48%. Original estimates in this milestone were based on project progress of submitting applications and receiving pole licenses earlier than actually occurred. We continue to work with utilities to accelerate the timelines for licensure. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 52 | Baseline was estimated at 100% and was based on project plan activity. Our project plan indicates we will be at 51%. Percent of budget expended is projected at 52%. Original estimates in this milestone were based on project progress on receiving make ready quotes. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. All NH Pole applications have been submitted, and it is anticipated that we will have received 50% of Make Ready estimates and that we will have received 15% of our pole licenses on the route. | 19 | Baseline was estimated at 25% and was based on project plan activity. Our project plan indicates we will be at 11%. Percent of budget expended is projected at 19%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. Portions of fiber optic cable are expected to be delivered in the next quarter. | 14 | Baseline was estimated at 22% and was based on project plan activity. Our project plan indicates we will be at 8%. Percent of budget expended is projected at 14%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 16 | Baseline was estimated at 42% and was based on project plan activity. Our project plan indicates we will be at 33%. Percent of budget expended is projected at 16%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 0 | Baseline was estimated at 9% and was based on project plan activity. Our project plan indicates we will be at 0%. Percent of budget expended is projected at 0%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 2011-11-16 15:54 | 2011-11-16 15:54 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2011 | Q4 | Q4 - 2011 | 5028 | 4699 | FALSE | 45 | Baseline 59% Delays in hiring engineering and construction vendor are the primary reason for the discrepancy between baseline and next quarter's projected % complete. Anticipate to complete pole applications for the middle mile in the coming quarter and to complete a substantial amount of Make-Ready work and obtain an estimated 25% of pole licenses across the route. DOT anticipated to purchase components for its portion of the project Engineering work continues on last mile. Mountaintop builds continue across NH. | 50 | Project Management | Baseline 57% Project Plan 51% | 100 | Completed | 100 | Baseline 98% Project Plan 85% Actual spend is anticipated be 107% and will include additional engineering and pole application expenses. | 100 | No expenditures scheduled in this milestone | 46 | Baseline 71% Project Plan 30%. Continue to work with Utilities and Third Parties to accelerate licensure of poles. | 61 | Baseline 100% Project Plan 74% Anticipate surveys to be complete on the middle mile and Make Ready expenses to be available for 90% of the route. Last Mile engineering and Make-Ready continues. | 32 | Baseline 38% Project Plan 14% Continue to obtain fiber optic cable. Microwave equipment expected to be invoiced this quarter. | 40 | Baseline 30% Project Plan 2%. Anticipate increased middle mile construction in the coming quarter. | 25 | Baseline 51% Project Plan 34% Anticipate invoice for 3 mountaintop builds from this quarter and expenses for additional mountaintop builds during the coming quarter. | 0 | Baseline 9% Project Plan 0%. Network testing is anticipated to begin in Q3 2012. | 2012-02-15 11:55 | 2012-02-15 11:55 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2012 | Q1 | Q1 - 2012 | 6008 | 5603 | FALSE | 70 | Baseline 74% Delays in hiring engineering and construction vendor are the primary reason for the discrepancy between baseline and next quarter's projected percent completion. Anticipate to complete pole surveys for the Middle Mile in the coming quarter and to complete a substantial amount of Make-Ready work and obtain an estimated 90% of pole licenses across the route. DOT anticipated to purchase components for its portion of the project. Make-Ready work continues on the Last Mile. Mountaintop builds continue across NH. | 60 | Project Management | Baseline 66% | 100 | Completed. | 100 | Baseline 100% Actual is at 122% due to increased Make-Ready costs. | 100 | No expenditures scheduled in this milestone. | 56 | Baseline 87% Anticipate increased middle mile and last mile construction in the coming quarter. | 100 | Baseline 100% Anticipate all Make Ready expenses to be finalized this quarter. | 66 | Baseline 47% Continue to obtain fiber optic cable. Procurement of equipment for FastRoads network and construction and DOT construction will occur this quarter. | 56 | Baseline 57% | 34 | Baseline 59% FastRoads network equipment anticipated to be deployed. | 0 | Baseline 14% Network testing is anticipated to begin in Q3 2012. | 2012-05-10 12:16 | 2012-05-10 12:16 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2012 | Q2 | Q2 - 2012 | 7014 | 6134 | FALSE | 74 | Baseline forecast 85. | 64 | Project Mgmt. | Baseline forecast 75. | 100 | Completed. | 100 | Baseline forecast 100; Forecast to be at 130%. | 100 | No expenditures scheduled in this milestone. | 59 | Baseline forecast 100. | 100 | Baseline forecast 100; Forecast to be 111%. | 67 | Baseline forecast 96. | 63 | Baseline forecast 83. | 40 | Baseline forecast 71. | 0 | Baseline forecast 23. | 2012-08-10 14:20 | 2012-08-10 14:20 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2012 | Q3 | Q3 - 2012 | 7842 | 6625 | FALSE | 80 | Baseline 92 | 70 | Proj. Managment | Baseline 82 | 100 | Completed | 100 | Baseline 100;Actual Q4 PPR forecast 127 | 100 | n/a | 86 | Baseline 100 | 100 | Baseline 100;Actual Q4 PPR forecast 126 | 70 | Baseline 100; Actual Q4 PPR forecast 126 | 66 | Baseline 96 - see item 3 below | 54 | Baseline 87- see item 3 below | 50 | Baseline 55- see item 3 below | 2012-11-13 13:11 | 2012-11-13 13:11 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2012 | Q4 | Q4 - 2012 | 9006 | 7780 | FALSE | 87 | Baseline 97.5 | 84 | Project Management | Baseline 91 | 100 | Completed | 100 | Baseline 100 PPR Actual Q1-2013 forecast 138 | 100 | N/A | 100 | Baseline 100 PPR Actual Q1-2013 forecast 122 | 100 | Baseline 100 PPR Actual Q1-2013 forecast 139 | 75 | Baseline 100 -see item 3 below | 70 | Baseline 97 -see item 3 below | 66 | Baseline 98 -see item 3 below | 50 | Baseline 85 -see item 3 below | 2013-02-27 11:14 | 2013-02-27 11:14 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2013 | Q1 | Q1 - 2013 | 10024 | 8561 | FALSE | 95 | Baseline 100. Requesting an extension to complete remaining work. | 80 | Project Management | Baseline 100. Requesting an extension to complete remaining work. | 100 | Complete. | 100 | Actual 139 Baseline 100. Requesting an extension to complete remaining work. | 100 | No expenditures scheduled in this milestone. | 100 | Actual 116 Baseline 100. Requesting an extension to complete remaining work. | 100 | Actual 140 Baseline 100. Requesting an extension to complete remaining work. | 81 | Baseline 100. Requesting an extension to complete remaining work. | 85 | Baseline 100. Requesting an extension to complete remaining work. | 76 | Baseline 100. Requesting an extension to complete remaining work. | 46 | Baseline 100. Requesting an extension to complete remaining work. | 2013-05-31 11:44 | 2013-05-31 11:44 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2013 | Q2 | Q2 - 2013 | 10734 | 9030 | FALSE | 98 | Baseline 100. Received an extension to complete remaining work. | 96 | Project Mgmnt. | Baseline 100. Ongoing Project Management due to extension. | 100 | Complete. | 100 | Actual 104 Baseline 100. Received an extension to complete remaining work. FastRoads projected to complete additional 1% in Q4 2013. | 100 | No expenditures scheduled in this milestone. | 100 | Baseline 100. This category is projected to be complete in Q3 2013. The project has received an extension to complete remaining work. | 100 | Actual 102 Baseline 100. This category is projected to be complete in Q3 2013. The project has received an extension to complete remaining work. | 95 | Baseline 100. Received an extension to complete remaining work. Datacasting equipment scheduled to be purchased during Q3 2013. | 97 | Baseline 100. Received an extension to complete remaining work. NHOS and NH FastRoads network Build will continue in Q3 2013. | 98 | Baseline 100. Received an extension to complete remaining work. UNH deploying equipment to CAIs. NH FastRoads deploying to CAIs, residences, and businesses. | 78 | Baseline 100. Received an extension to complete remaining work. NH FastRoads testing to occur after final equipment deployment. | 2013-08-26 11:54 | 2013-08-26 11:54 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2013 | Q3 | Q3 - 2013 | 11404 | 9514 | FALSE | 99 | Baseline Projection 100. USNH does not expect cost overruns in the overall project. | 100 | Project Mngmnt. | Baseline Projection 100 Actual spend is projected to be 101%. | 100 | Complete | 100 | Baseline Projection 100 Actual spend is projected to be 106%. | 100 | Baseline Projection 100 | 100 | Baseline Projection 100 | 100 | Baseline Projection 100 Actual spend is projected to be 102%. | 99 | Baseline Projection 100 | 98 | Baseline Projection 100 | 98 | Baseline Projection 100 | 100 | Baseline Projection 100 | 2013-11-26 15:17 | 2013-11-26 15:17 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570082 | 2013 | Q4 | Q4 - 2013 | 12282 | 10452 | FALSE | 100 | Complete | 100 | Project Mngmnt. | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-06-20 12:55 | 2014-06-20 12:55 | 5843 | 5843 | University System of New Hampshire
NT10BIX5570084 | 2010 | Q4 | Q4 - 2010 | 1180 | 2213 | FALSE | 4 | Substantive portions contributing to overall project completion in the next reporting period consist of issuance of FONSI. If EA is delayed based on SHPO and no FONSI is issued, no procurement, no releases of RFPs, or site preparation tasks during the construction season will occur. Project planning is in-process and mobilization efforts including equipment procurement and staging may also be delayed due to the â€œAll or Noneâ€ EA requirements. | 0 |  | No variance from revised Baseline Plan | 100 | Pending final approval by NTIA a FONSI needs to be issued in Q3. Iowa SHPO approval is a major concern to overall project completion process. At this reporting period this benchmark is of great concern and question. | 60 | High level network design will be 100% complete and it is anticipated that substantial portion of final network design will be completed prior the end of the next reporting period. | 0 | It is anticipated that Rights of Way related to all site locations will be in jeopardy due to current FONSI conditional EA requirements. Currently, no variance from project Baseline Plan. | 0 | No Construction or Permitting related activities will begin until land acquisition is completed/secured and OSP engineering RFQâ€™s released. | 0 | No variance from revised Baseline Plan | 10 | It is anticipated that equipment orders / procurement will be begin prior to the end of the upcoming reporting period. Again this is pending EA â€œAll or Noneâ€ conditional approval. Currently, there is No variance from revised Baseline Plan. | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 2011-02-16 14:11 | 2011-02-16 14:11 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2011 | Q1 | Q1 - 2011 | 2086 | 2788 | FALSE | 2 | Due to the project modification, we are not going to meet the milestones or expenditures forecasted. | 0 |  | No variance from Baseline Report | 35 | Due to the project modification, we submitted a request for a Programmatic Agreement. | 45 | Due to the project modification, we have not completed the network design for the previous quarter. | 0 | Due to the project modification, we are not projecting to receive a FONSI until Qtr 2, Year 2. Therefore, we will not begin ROW work next quarter. | 0 | Due to the project modification, we do not project that we will start obtaining construction permits during the next quarter. | 0 | No variance from Baseline Report | 0 | Due to the project modification and not obtaining a FONSI, we do not project that we will be procuring equipment next quarter. | 0 | Due to the project modification and not obtaining a FONSI, we do not project finalizing the Blenco to Logan Fiber Lease and Hut Agreement. | 0 | No variance from Baseline Report | 0 | No variance from Baseline Report | 2011-05-17 12:49 | 2011-05-17 12:49 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2011 | Q2 | Q2 - 2011 | 3086 | 3300 | FALSE | 4 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, during this qrt IHS will finish identifying the hut locations for the Main, North, West, and South Rings. OSP Design for the Main, North, West, and South Rings will be started and in process. ISP Design for the North, West, South, East Long Haul, West Long Haul, and Central Rings will be in process with ISP design completion of the Main Ring. The negotiations for the IRU will be completed and pending finalization on receiving a FONSI. | 0 |  | No variance from the Baseline Report | 45 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, IHS anticipates that the EA/Section 106 for the hut locations will be near completion. IHS anticipates receiving a "no objection" response from USFWS and to correspond with tribes interested in the IHS BTOP project. | 70 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, IHS anticipates the ISP statewide network design will be in process for North, West, East Long Haul, West Long Haul and the Central Ring. The OSP Design will be in process for the Main, North, West, and South Ring. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure stainability. IHS anticipates that the Right of Way work will start qtr 4 (Oct-Dec 2011). | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS anticipates that Construction Permits and Other Approvals will start qtr 4 (Oct-Dec 2011). | 0 | No variance from the Baseline Report. IHS anticipates Site Preparation RFPs to be issued qtr 4 (Oct-Dec 2011). Site work will not actually start until qtr 1 (Jan-Mar 2012) after receiving a FONSI and the ground is ready to dig. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS is working on completing Equipment RFPs currently and next qtr will start procuring after selecting equipment vendors. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IRU Negotiations are under way. IHS anticipates to finalize IRU negotiations in qtr 4 (Oct-Dec 2011). | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS will start the DWDM Development RFP vendor selection to procure equipment. | 0 | No variance from the Baseline Report. IHS anticipates that equipment will be tested during qtr 4 (Oct-Dec 2011). | 2011-08-15 14:13 | 2011-08-15 14:13 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2011 | Q3 | Q3 - 2011 | 3928 | 3802 | FALSE | 60 | IHS anticipates that during the next quarter a Programmatic Agreement will be negotiated and the FONSI signed. The Start Up Support Services Vendor Kick-Off meeting will be scheduled and a middle mile extension interconnection plan in place. IHS will procure the DWDM equipment in December. OSP Engineering for the fiber laterals will be completed and ISP Engineering will be completed as well. The IRU negotiations will be completed. IHS anticipates the land permitting will be underway during this quarter as well. | 0 |  | No variance from baseline report. | 50 | IHS anticipates that during the next quarter a Programmatic Agreement will be negotiated and the FONSI signed. | 75 | OSP Engineering for the fiber laterals will be completed and ISP Engineering will be completed as well. | 0 | IHS anticipates that the Right of Way work will start Quarter 3, Year 2 (Jan-Mar 2012). | 40 | IHS anticipates the permitting for the 9 hut locations will be in process and near completion. | 0 | IHS anticipates the site preparation to being Quarter 3, Year 2 (Jan-Mar 2012) | 25 | IHS anticipates procuring preliminary returnable equipment that can be stored prior to obtaining a FONSI. | 3 | IHS anticipates finalizing the IRU in Quarter 2, Year 2 (Oct-Dec 2011) | 0 | IHS anticipates the equipment installation to be in-process Quarter 3, Year 2 (Jan-Mar 2012). | 0 | IHS anticipates that equipment will begin being tested during Quarter 3, Year 2 (Jan-Mar 2012). | 2011-11-08 17:35 | 2011-11-08 17:35 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2011 | Q4 | Q4 - 2011 | 5100 | 4770 | FALSE | 68 | Iowa Health System (IHS) anticipates that during the next quarter a FONSI will be obtained and it can proceed forward with finalizing the land leases and IRU negotiations for the Moorehead location. IHS also anticipates the OSP and ISP engineering will be completed allowing the construction RFP to be released and a vendor selected to start construction the following quarter. The Router RFP will also be released and a vendor selected. During the next quarter, IHS anticipates that there will be 4 Last Mile Provider agreements. The ISP equipment and material lab testing and staging will be in process. The OSP equipment staging will be in process. Permitting and Right of Way approvals will be obtained and site preparation for the 9 hut installations on all rings will be in process. | 0 |  | No variance from the baseline report. | 60 | IHS anticipates that during the next quarter a FONSI will be obtained and IHS will work towards fulfilling the Programmatic Agreement requirements for reporting and Middle Mile Extensions. | 85 | IHS anticipates that during the next quarter the OSP engineering will be complete for the 9 hut locations and started for the Last Mile Provider connections. | 50 | IHS anticipates that during the next quarter the Rights of Way will be completed for the 9 hut locations and Rights of Way will be started for the Last Mile Provider connections. | 60 | IHS anticipates that during the next quarter, the construction permits will be completed for the 9 hut locations and the Last Mile Provider connections will be started. | 20 | IHS anticipates that the site preparation for the 9 hut locations will be started during this quarter. | 83 | IHS anticipates that the Routers will be procured during the next quarter and the fiber laterals for the 9 hut locations will be procured as well. | 40 | IHS anticipates finalizing the IRU to lease 99.5 miles of fiber during the next quarter. | 10 | IHS anticipates the equipment installation to be started during the next quarter. | 10 | IHS anticipates that network/equipment testing will begin during the next quarter to allow for deployment. | 2012-02-17 14:47 | 2012-02-17 14:47 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2012 | Q1 | Q1 - 2012 | 5938 | 5568 | FALSE | 71 | IHS/BBI anticipates installing the 9 hut locations pending fiber lateral installation upon review of the reroute modification. IHS/BBI anticipate staging the equipment in the huts, finalizing the IRU with Long Lines, and executing customer agreements with at least 3 more customers. | 0 |  | No variance from the baseline report. | 65 | IHS/BBI anticipates that the OSP and ISP engineering will be completed allowing the construction RFQs to be released and a vendor selected to start construction for the 9 hut locations and laterals that have not changed. IHS/BBI anticipates that at least 3 more agreements will be executed and Middle Mile Extensions will be engineered to move forward complying with the Programmatic Agreement. | 90 | IHS/BBI anticipates that during the next quarter the OSP engineering will be complete for the 9 hut locations and started for the middle mile extensions. | 50 | IHS/BBi anticipates that during the next quarter the ROW will be complete for the 9 hut locations and started for the middle mile extensions. | 60 | IHS/BBI anticipates that during the next quarter the construction permits will be complete for the 9 hut locations, underway for the hut laterals, and started for the middle mile extensions. | 50 | IHS/BBI anticipates that during the next quarter the site preparation will be complete for the 9 hut location, underway for the hut laterals, and started for the middle mile extensions. | 80 | IHS/BBI anticipates that the equipment procurement for the Ethernet Switches and Installation Kits will be underway. | 40 | IHS/BBI anticipates the IRU negotiations will be finalized and the fiber lateral builds will begin. | 30 | IHS/BBI anticipates that the equipment deployment will be underway and equipment installation will be started for the 9 hut locations. | 0 | No variance from the baseline report. IHS/BBI anticipates that the Network Testing will begin during Q3 2012 (Jul-Aug). | 2012-05-07 10:41 | 2012-05-07 10:41 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2012 | Q2 | Q2 - 2012 | 7006 | 6130 | FALSE | 77 | IHS anticipates completing the 9 hut and lateral installations dependent up on EA approvals. Staging and deploying equipment will be under way and moving towards bringing up the main ring by end of Q4 2012. IHS anticipates executing customer agreements will at least 3 more customers. | 0 |  | No variance from the baseline report. | 80 | IHS anticipates that the middle mile extension route modifications will be approved in Q3 2012 allowing IHS to start constructing fiber to our newly signed customers. Therefore, the only environmental assessment left will be for the newly signed customers in Q3 2012, Q4 2012, and Q1 2012. | 90 | No variance from baseline report. | 60 | IHS anticipates the ROW will be completed for the 9 hut locations and started for the middle mile extensions. | 70 | IHS anticipates the construction permits and other approvals will be finalized early in Q3 2012 for the 9 hut locations and underway for the middle mile extensions. | 50 | IHS anticipates the site prep will be completed early in Q3 2012 and under way for the middle mile extensions pending EA approval. | 90 | IHS anticipates the ethernet switches for the three last mile providers will be completed during Q3 2012 and the installation kits will continually be ordered as we start deploying equipment. | 80 | IHS anticipates the 9 hut laterals will be completed and the 3 middle mile extensions under way. | 30 | IHS anticipates that the equipment deployment will be underway and equipment installation completed for the 9 hut locations. | 30 | IHS anticipates network testing will be started for the main ring. | 2012-08-10 13:38 | 2012-08-10 13:38 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2012 | Q3 | Q3 - 2012 | 7990 | 6701 | FALSE | 80 | IHS anticipates that the main ring will be activated by end of Q4 2012. IHS anticipates executing customer agreements will at least 4 more customers. | 0 |  | No variance from the baseline report | 90 | IHS anticipates that the middle mile extension route modifications will be approved in Q4 2012 allowing IHS to start constructing fiber to our newly signed customers. Therefore, the only environmental assessment left will be for the newly signed customers in Q1 2012. | 95 | No variance from baseline report. | 75 | IHS anticipates the ROW will be started for the additional middle mile extensions. | 80 | IHS anticipates the construction permits and other approvals will be finalized for the 3 middle mile extensions. | 85 | IHS anticipates the site prep will be started and partially completed for the 3 middle mile extensions pending EA approval. | 95 | IHS anticipates the DWDM equipment will be procured for the western long haul route upgrade and installation kits will continually be ordered as are deploying equipment. | 90 | IHS anticipates the 9th hut laterals will be completed and the 3 middle mile extensions under way. | 50 | IHS anticipates that the equipment deployment will be finalized on the main ring. | 50 | IHS anticipates network testing will be completed for the main ring. | 2012-11-20 16:37 | 2012-11-20 16:37 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2012 | Q4 | Q4 - 2012 | 8836 | 7621 | FALSE | 93 | IHS anticipates the north, wester rings will be activated by end of Q1 2013. IHS anticipates the 4 newly proposed routes will be near approvals from NTIA | 0 |  | No variance from the baseline report | 100 | Complete | 100 | Complete | 95 | IHS anticipates the ROWs will be finalized by end of Q1 2013 | 95 | IHS anticipates the permitting will be finalized by end of Q1 2013 | 95 | IHS anticipates the site prep will remain the same for the next quarter until the 4 newly submitted proposed routes in Q 1 2013 are approved by NTIA | 100 | IHS anticipates all equipment will be procured during the next quarter. | 95 | IHS anticipates the 3 middle mile routes will be completed. | 95 | IHS anticiaptes that the equipment deployment will be finalized on the north and western rings....and start on long haul routes. | 95 | IHS anticipates network testing will be completed on the north and western rings. | 2013-02-19 12:17 | 2013-02-19 12:17 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2013 | Q1 | Q1 - 2013 | 9902 | 8492 | FALSE | 96 | IHS anticipates the 1st group of customer fiber builds will be close to completion and the 2nd group of customer fiber builds will be a third of the way complete by the end of Q2 2013. IHS Anticipates completing the construction activities to build out the fiber network connecting customers due to heavy snowfall and rainfall during end of Q2 2013 and Q3 2013. | 0 | N/A | No variance from the baseline report | 100 | Complete | 100 | Complete | 100 | IHS anticipates the ROWs will be finalized. | 100 | IHS anticipates the construction permits will be completed. | 100 | IHS anticipates the site prep will be completed. | 100 | IHS anticipates the equipment procurement will be completed. | 95 | IHS anticipates the 1st group of customer fiber builds will start up mid May and will be completed by July 2013. The 2nd group of customer fiber builds will be completed July/August 2013. | 95 | IHS anticipates that the equipment deployment for the 1st group of customer will be close to completion and the 2nd group of customer deployments will be a third of the way complete. Delays due to weather dependent construction activities. | 95 | IHS anticipates network testing will be completed on the north and western rings. Delays due to weather dependent construction activities. | 2013-05-24 14:02 | 2013-05-24 14:02 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2013 | Q2 | Q2 - 2013 | 10698 | 9011 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-22 16:21 | 2013-08-22 16:21 | 6985 | 6985 | Iowa Health System
NT10BIX5570084 | 2013 | Q3 | Q3 - 2013 | 11836 | 10012 | FALSE | 100 | Complete | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-02-18 15:32 | 2014-02-18 15:32 | 6985 | 6985 | Iowa Health System
NT10BIX5570085 | 2010 | Q4 | Q4 - 2010 | 1372 | 2385 | FALSE | 2 | Baseline Report 2% | 0 | 0 | N/A | 90 | Baseline Report 90% | 50 | Baseline Report 50% | 10 | Baseline Report 10% | 10 | Baseline Report 10% | 5 | Baseline Report 5% | 12 | Baseline Report 12% | 10 | Baseline Report 10% | 5 | Baseline Report 5% | 5 | Baseline Report 5% | 2011-02-25 08:50 | 2011-02-25 08:50 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2011 | Q1 | Q1 - 2011 | 2336 | 2913 | FALSE | 2 | Baseline 18%. Our original baseline was derived from our awarded project of $17,509,274. The recently-approved overlap resolution and project rescope has changed our project to be $12,861,126. While our percent complete is behind where our original baseline had estimated it is due to the significant project scope change. A new baseline is being developed to be submitted during the next quarter that will more accurately reflect the project schedule going forward. | 100 | Vehicles | VTel purchased two broadband vehicles. | 100 | Baseline 100% | 60 | Baseline 100% Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 1 | Baseline 15%. Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 47%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 23%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 23%. Please see narrative above regarding overall project completion and milestones. | 2011-05-26 11:33 | 2011-05-26 11:33 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2011 | Q2 | Q2 - 2011 | 3250 | 3387 | FALSE | 6 | No variance with updated baseline. | 50 | Vehicles | VTel purchased two broadband vehicles. | 100 | Our environmental assessment has been complete. | 60 | A firm is currently in the field working on the network design. | 10 | No variance with updated baseline. | 10 | No variance with updated baseline. | 10 | No variance with updated baseline. | 55 | No variance with updated baseline. | 0 | No variance with updated baseline. | 1 | No variance with updated baseline. | 1 | No variance with updated baseline. | 2011-08-22 09:07 | 2011-08-22 09:07 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2011 | Q3 | Q3 - 2011 | 4136 | 3914 | FALSE | 46 | No variance with baseline. | 0 | Vehicles | Working with the grants office and BTOP staff we have determined that the vehicles are not an allowable expense. We are working with the staff to determine how these funds can be used/allocated appropriately. | 100 | Our environmental assessment has been completed. | 90 | We expect field engineering to be completed in January 2012, which is 30 days behind our original estimate of 4Q11. Work was delayed due to impact of Hurricane/Tropical Storm Irene. | 40 | No variance with baseline. | 40 | No variance with baseline. | 19 | No variance with baseline. | 75 | No variance with baseline. The equipment has already started to arrive. | 0 | No variance with baseline. | 72 | Site visits are now occurring, and we are scheduled to begin turn-up during this quarter. No variance from baseline. | 72 | The network will be tested as DWDM/Optical sites come online. No variance from baseline. | 2011-11-18 14:12 | 2011-11-18 14:12 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2011 | Q4 | Q4 - 2011 | 5176 | 4840 | FALSE | 50 | Much of our progress will be dictated by the speed at which we are able to receive permits, and make-ready construction schedules. We plan on having the applications submitted, however, we are unable to control the turnaround time by the pole-owning utilities. We are expecting make ready work to take approximately 90 days after make ready payment has been made. | 100 |  | Network testing equipment procurement occurred in Q4 2011. | 100 | Our environmental assessment has been completed. | 100 | Our outside engineer should have all miles staked by the end of Q1 2012 | 60 | No variance with baseline. | 60 | No variance with baseline. | 29 | No variance with baseline. | 95 | No variance with baseline. | 11 | No variance with baseline. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-02-21 17:21 | 2012-02-21 17:21 | 5847 | 5847 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2012 | Q1 | Q1 - 2012 | 6238 | 5721 | FALSE | 60 | Much of our progress will be dictated by the speed at which we are able to receive permits, and make-ready construction schedules. We are also working directly with state officials and the pole-owning utilities to get pole make ready completed in a timely fashion. We are expecting make ready work to take approximately 90 days after make ready payment has been made. We will continue to monitor the progress in this area and address areas of concern. | 90 | N/A | No variance with baseline. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 80 | No variance with baseline | 80 | No variance with baseline. | 79 | No variance with baseline. | 80 | We expect additional deployment of electrical equipment through the end of 2012. | 42 | No variance with baseline. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-05-21 16:28 | 2012-05-21 16:28 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2012 | Q2 | Q2 - 2012 | 7246 | 6250 | FALSE | 60 | Progress continues to be dictated by make-ready construction schedules. We will continue to monitor this and work with pole owners as well as state officials to assure that positive progress continues. | 60 | Testing Equip. | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 75 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved in the 2nd quarter of 2012 and we expect that to continue in the third quarter 2012. | 75 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays have been addressed. | 75 | This category is 25% under baseline, but is expected to meet it by the end of 2012. | 85 | We expect additional deployment of electrical equipment through the end of 2012. | 35 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-08-24 16:25 | 2012-08-24 16:25 | 7374 | 7374 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2012 | Q3 | Q3 - 2012 | 8140 | 6780 | FALSE | 67 | Progress continues to be dictated by make-ready construction schedules. We will continue to monitor this and work with pole owners as well as state officials to assure that positive progress continues. | 90 | Testing Equipment | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 80 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved in the 3rd quarter of 2012 and we expect that to continue in the fourth quarter 2012. | 80 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays have been addressed. | 80 | This category is 25% under baseline, but is expected to meet it by the end of 2012. | 90 | We expect additional deployment of electrical equipment through the end of 2012 and into the first quarter of 2013. | 40 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 80 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 80 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-11-29 14:29 | 2012-11-29 14:29 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2012 | Q4 | Q4 - 2012 | 8734 | 7531 | FALSE | 65 | With make ready problem resolution expected early in the quarter, construction will progress more quickly. The deployment of equipment will also be accelerated in order for us to meet construction deadlines. | 90 | Testing Equipment | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 90 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved upon contracting with an inspector that knows the local contacts and can resolve specific make ready problems as they come up. | 90 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays are being addressed. | 90 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays are being addressed. | 90 | We expect additional deployment of electrical equipment through the first quarter of 2013. | 50 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 85 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 85 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2013-02-12 16:34 | 2013-02-12 16:34 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2013 | Q1 | Q1 - 2013 | 10030 | 8565 | FALSE | 74 | Extension AAR Filed | 95 |  | Extension AAR Filed | 100 | Extension AAR Filed | 75 | Extension AAR Filed | 75 | Extension AAR Filed | 60 | Extension AAR Filed | 96 | Extension AAR Filed | 75 | Extension AAR Filed | 50 | Extension AAR Filed | 85 | Extension AAR Filed | 85 | Extension AAR Filed | 2013-05-31 15:43 | 2013-05-31 15:43 | 7374 | 7374 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2013 | Q2 | Q2 - 2013 | 10714 | 9020 | FALSE | 71 | see AAR & Extension Request | 95 |  | see AAR & Extension Request | 100 | see AAR & Extension Request | 90 | see AAR & Extension Request | 85 | see AAR & Extension Request | 85 | see AAR & Extension Request | 90 | see AAR & Extension Request | 85 | see AAR & Extension Request | 58 | see AAR & Extension Request | 78 | see AAR & Extension Request | 58 | see AAR & Extension Request | 2013-08-23 16:22 | 2013-08-23 16:22 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2013 | Q3 | Q3 - 2013 | 11352 | 9477 | FALSE | 83 | See AAR & Extension Request | 95 | n/a | See AAR & Extension Request | 100 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 85 | See AAR & Extension Request | 68 | See AAR & Extension Request | 78 | See AAR & Extension Request | 68 | See AAR & Extension Request | 2013-11-22 15:35 | 2013-11-22 15:35 | 5849 | 5849 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2013 | Q4 | Q4 - 2013 | 12472 | 10651 | FALSE | 81 | We do not expect to construct much as the winter season is upon us. There will be some expenditures for make ready and permitting but no significant build | 86 | admin & consulting | there should be little or no activity in this category | 97 | Spending remains flat as we have completed FONSI work and do not expect additional costs | 66 | Little work done in this area during the next quarter but expect to see increased activity in Q2 & Q3 | 86 | We have 6 easements left to obtain and hope to have them in hand by the end of Q2 | 90 | The majority of applications have been filed and we now await license issuance and make ready cost true-ups | 73 | We continue to methodically deploy and as such have staggered sites. We will continue this approach throughout the project | 81 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 88 | We are right on track with our permitting costs slightly ahead of network build percentages | 81 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 85 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 2014-08-29 15:57 | 2014-08-29 15:57 | 7797 | 7797 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2014 | Q1 | Q1 - 2014 | 12496 | 10666 | FALSE | 86 | We expect to come out of the winter season and construct 8-10 additional route miles. | 86 | admin & consulting | At this point we do not expect much of anything in this line item other than our final audit. | 97 | Environmental Assessment has been completed, and the project received a Finding Of No Significant Impact (FONSI) in 2Q11. We will be addressing any additional environmental assessments for route changes should they occur | 75 | We are in the final phase of engineering route changes. | 93 | All of the Rights of Way for the initial submission have to obtained and we have a small amount of spending left | 95 | We have applied for all make ready licenses; however, we await final true up and invoicing from the utility companies. Final licenses may not be issued until October of 2014 | 97 | The majority of work is complete for this activity | 94 | Our contract with Alcatel has a retainage clause in it and we will not be billed for the entire equipment purchase until closeout. There are still some optics left to purchase in order for us to be fully operational | 90 | The additional miles in the AAR that was approved in late May of 2014 are all that is left to construct. We have a contract in place with a SDB (small disadvantaged business) | 0 | The costs associated with the deployment of our DWDM equipment is bundled with the procurement costs above. We have no break out from the vendor. | 85 | The final costs for this activity will be spent when the network is fully built. | 2014-09-10 08:55 | 2014-09-10 08:55 | 7797 | 7797 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2014 | Q2 | Q2 - 2014 | 12498 | 10667 | FALSE | 95 | If we are to receive all of the Make Ready licenses related to our AAR that was approved in May we feel that there will be 14 miles to construct during October of 2014 | 86 |  | All administrative costs will be fully spent once construction ceases. | 97 | All spending should be complete; however, a de minimis amount may remain unspent with construction ongoing. | 95 | We anticipate additional spending for route changes from our AAR | 95 | The majority of spending will be done; however, there is a small amount of money left in the budget should we need it for route changes brought on by the AAR | 95 | The majority of spending will be done; however, there is a small amount of money left in the budget should we need it for route changes brought on by the AAR | 99 | The majority of work is complete for this activity | 97 | With 29 miles left to construct there may be a few components not fully paid at the end of the third quarter | 89 | we expect to construct an additional 12 miles during the third quarter which will leave 14 more left to complete in October and early November - the 14 miles remaining relate to Make Ready licenses that may not be issued in the third quarter. We are requesting an extension until December 31, 2014 to complete this project. | 0 | The cost of deployment is bundled with the purchase of equipment. We do not have a breakout from the vendor. | 91 | Testing will be 100% spent once all construction is completed | 2014-09-10 09:03 | 2014-09-10 09:03 | 7797 | 7797 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2014 | Q3 | Q3 - 2014 | 12608 | 10876 | FALSE | 99 | We will complete construction of all 165.22 route miles. | 83 | admin | The final audit will be completed in 1Q15 | 100 | Our project will be completed in 4Q14 | 100 | All engineering and design will be completed as our project will be finished in 4Q14 | 100 | The final three easements will be obtained in 4Q14 | 100 | All construction will be complete as our 165.22 routes miles will be fully contructed in 4Q14 | 100 | All work will be completed in 4Q14 | 100 | The equipment will all be deployed and fully operational in 4Q14. | 100 | The final 3.98 route miles will be built and the network will be completed in 4Q14 | 100 | Our project will be completed in 4Q14 | 100 | The network will be fully tested and operational in 4Q14 | 2014-11-19 12:04 | 2014-11-19 12:04 | 7797 | 7797 | Vermont Telephone Company, Inc.
NT10BIX5570085 | 2014 | Q4 | Q4 - 2014 | 12718 | 11042 | FALSE | 100 | Our project is completed and we will be working on closeout documents. | 100 |  | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 100 | Our project is completed and we will be working on closeout documents. | 0 | N/A | 100 | Our project is completed and we will be working on closeout documents. | 2015-02-24 09:58 | 2015-02-24 09:58 | 7797 | 7797 | Vermont Telephone Company, Inc.
NT10BIX5570086 | 2010 | Q4 | Q4 - 2010 | 580 | 1597 | FALSE | 6 | No variance | 0 |  | N/A | 100 | No variance | 75 | No variance | 75 | No variance | 75 | No variance | 0 | No variance | 10 | We will have started ordering equipment but do not anticipate receipt prior to the end of this quarter. We expect we will be back on track to meet our projected percentage of completion as reported by the next quarter. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-27 09:56 | 2011-01-27 09:56 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2011 | Q1 | Q1 - 2011 | 2058 | 2774 | FALSE | 5 | Continue to be behind due to delays with the Environmental Assessment and other reasons listed below. | 0 |  | N/A | 100 | No variance | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 0 | No Variance | 50 | The remaining OSP materials for the 2nd segment will not be delivered until November for the 2012 construction season. No room for all materials at once. | 0 | No Variance | 0 | The RFP hasn't been completed yet so equipment has not been ordered. We have not received our FONSI yet so we canâ€™t construct until we get that. | 0 | No Variance | 2011-05-16 17:16 | 2011-05-16 17:16 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2011 | Q2 | Q2 - 2011 | 2998 | 3256 | FALSE | 21 | Slightly delayed due to reasons listed below | 0 |  | N/A | 100 | No Variance | 95 | We expect the final design for the Brainerd to Moorhead route to complete one quarter later due to earlier delays. | 90 | We anticipate a continued slight delay due to the State government shutdown | 90 | We anticipate a continued slight delay due to the State government shutdown | 30 | Slight variance due to delay in securing building sites and delay in receiving our FONSI. We have now purchased property and will continue moving forward with this milestone. | 0 | We expect this milestone to continue behind plan as a result of delays in obtaining signed CAI contracts with two of our partners. We expect an equipment ship date in October. | 22 | This will vary from baseline because we included some of the construction materials in the equipment category for the baseline report. This line will track ahead of baseline because of that. | 0 | We expect this milestone to continue behind plan as a result of delays in obtaining signed CAI contracts with two of our partners. We continue pursuing other CAI contracts. | 0 | No variance | 2011-08-10 16:34 | 2011-08-10 16:34 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2011 | Q3 | Q3 - 2011 | 4112 | 3899 | FALSE | 32 | We expect that we will remain behind our planned baseline. We are working on an EA addendum and working diligently to get signed contracts for CAI sites. It has proven difficult to sign contracts for service to CAIs when we do not have an anticipated completion date due to weather and unforeseen hindrances such as the delays in receiving the FONSI and a number of permits. We are hopeful that these efforts will help us get closer to our baseline report estimates. In addition, there is always a timing lag between work completion and the invoicing. Most invoices are being processed now and will increase spending in the next quarter, allowing us to catch up. | 0 |  | N/A | 100 | No variance | 95 | We are working through an EA addendum which will push this milestone out slightly. | 90 | We are working through an EA addendum and need to wait for approval before we can finalize the remaining Rights of Way. | 75 | An EA addendum is being prepared for the remaining route. Permits cannot be applied for until we are cleared for a construction path so we can submit our applications to the various permitting entities. We expect approval of the EA addendum in Year 2, Q3 with permits to follow shortly after that. | 50 | No variance | 40 | This milestone will continue to show a variance from the baseline because this line only references CO and electronics equipment and other materials had been included in the original baseline. We are also experiencing difficulty with getting CAI contracts signed. | 38 | N/A-ahead of baseline | 40 | No variance | 0 | No variance | 2011-11-17 14:44 | 2011-11-17 14:44 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2011 | Q4 | Q4 - 2011 | 4994 | 4667 | FALSE | 54 | This milestone will be slightly behind our baseline since we do not expect to do any construction during the winter months. We continue to work on preparations to allow us to begin construction as soon as weather permits. This will help us to be closer to plan the following quarter. This will not hinder our ability to be 2/3 complete by the end of year 2. | 0 |  | N/A | 100 | N/A | 100 | N/A | 95 | This is just slightly behind our baseline due to work on the EA addendum. We will continue working on these once the EA addendum is approved. | 85 | This is just slightly behind our baseline due to work on the EA addendum. We will continue working on these once the EA addendum is approved. | 50 | N/A | 20 | This milestone will continue to show a variance from the baseline because this line only references CO and electronics equipment. Other materials had been included in the original baseline. We do not anticipate receiving any additional equipment this quarter due to difficulty in getting CAI contracts signed. In addition, we will not need equipment this quarter because there is no construction planned during winter months. | 37 | This is just slightly behind our baseline. We do not expect this number to change this quarter since we are unable to build in winter conditions. | 15 | This milestone will remain the same this quarter since there is no construction planned during winter months. | 5 | This milestone will remain the same this quarter since we do not expect to deploy any equipment this quarter. | 2012-02-14 11:18 | 2012-02-14 11:18 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2012 | Q1 | Q1 - 2012 | 6024 | 5611 | FALSE | 67 | We expect to be just slightly behind our baseline. This will not hinder project completion by July 31, 2013. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 50 | This is just slightly behind baseline and we continue working to catch up. | 31 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. We have started ordering and receiving equiment but due to difficulty in securing CAI's, the amount of equipment ordered is less than anticipated. | 60 | This is slightly behind our baseline but we continue working to catch up. | 15 | This milestone continues to lag due to difficulty with getting CAI contracts signed. We are on schedule for deployment of equipment in the middle mile routes. Once the CAI's are confirmed, we will be working on a schedule for CAI deployments. We do not anticipate this will hinder our ability to be 2/3 complete by the end of year 2. | 20 | No variance | 2012-05-10 15:40 | 2012-05-10 15:40 | 6162 | 6162 | Enventis Telecom, Inc.
NT10BIX5570086 | 2012 | Q2 | Q2 - 2012 | 7010 | 6132 | FALSE | 77 | This is slightly behind baseline but we continue working to catch up. | 0 |  | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 98 | We expect this to be just slightly behind baseline but do not expect this to impact our scheduled completion. | 80 | This is slightly behind our baseline. This includes the building sites and COs only. We do not expect this to impact our scheduled completion. | 35 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. They are actually part of the construction portion of the budget. We have started ordering, receiving and installing equipment but due to difficulty in securing CAIs, the amount of equipment ordered is less than originally anticipated. In addition, the needs of potential CAIs have changed resulting in less equipment. | 80 | No variance | 30 | This milestone continues to lag due to difficulty in securing CAI contracts. We continue working to catch up. | 30 | This milestone will be behind baseline as we work to install and deploy equipment. | 2012-08-10 14:11 | 2012-08-10 14:11 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2012 | Q3 | Q3 - 2012 | 8114 | 6764 | FALSE | 84 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 0 |  | N/A | 100 | No variance | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 90 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 48 | This line only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAIs have changed resulting in less equipment being needed. We do not anticipate any purchases this quarter. | 92 | This number is slightly above baseline. | 23 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 44 | This is slightly behind baseline. We do not plan to do any additional testing until the route construction is complete. We do not expect this to delay completion. | 2012-11-28 14:54 | 2012-11-28 14:54 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2012 | Q4 | Q4 - 2012 | 8784 | 7582 | FALSE | 84 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 0 |  | N/A | 100 | No variance | 67 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 94 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 94 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 80 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 60 | This line only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAIs have changed resulting in less equipment being needed. We do not anticipate any purchases this quarter. | 89 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 19 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 90 | This is slightly ahead of baseline | 2013-02-14 17:10 | 2013-02-14 17:10 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2013 | Q1 | Q1 - 2013 | 10016 | 8554 | FALSE | 90 | This is slightly behind baseline. We continue to work towards completion. | 0 |  | N/A | 100 | No variance | 77 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 100 | No variance | 100 | No variance | 80 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 66 | This line is behind baseline but only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAI's have changed resulting in less equipment being needed. | 93 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 37 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 94 | This is slightly behind baseline. | 2013-05-30 16:55 | 2013-05-30 16:55 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2013 | Q2 | Q2 - 2013 | 10364 | 8808 | FALSE | 89 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 0 |  | N/A | 100 | No variance | 77 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 82 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 71 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 94 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 31 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 94 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 2013-07-30 15:27 | 2013-07-30 15:27 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570086 | 2013 | Q3 | Q3 - 2013 | 11682 | 9803 | FALSE | 100 | All tasks are complete. This is the final report so there is no next quarter | 0 |  | No variance | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 2014-01-28 10:17 | 2014-01-28 10:17 | 6163 | 6163 | Enventis Telecom, Inc.
NT10BIX5570087 | 2010 | Q4 | Q4 - 2010 | 1132 | 2169 | FALSE | 2 | â€¢ Select an Engineering firm to complete the field engineering and submit permits â€¢ Draft and have signed the Engineering Services contract â€¢ Submit the Final EA to the NTIA â€¢ Gain approval of Interconnection point permits (4) â€¢ Submit other required permits â€¢ Compile a list of perspective construction vendors â€¢ Prepare the Construction and Procurement RFP | 0 |  | N/A | 90 | Submit final draft after network design is complete. | 95 | Re-bid delayed design start. Complete in 2011 Q2. | 70 | Re-bid delayed Rights of Way requests. Complete in 2011 Q2. | 70 | Rebid delayed other permit requests. Complete in 2011 Q2 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-14 11:50 | 2011-02-14 11:50 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2011 | Q1 | Q1 - 2011 | 2096 | 2793 | FALSE | 4 | Design changes, moving of one interconnection point and the need for joint-use agreements are delaying the start date of the cable build and expenditures as budgeted. | 0 |  | N/A | 90 | Design changes will delay EA approval until Y2Q1 (3rd qtr 2011) | 100 | N/A | 100 | N/A | 100 | N/A | 0 | Easements have been secured for two of the four sites; RFPs are being prepared for site work. | 0 | N/A | 0 | Construction of cable to begin in Y2Q1. Unforeseen changes in route delayed completion of design and EA; therefore, construction start date is pushed back a quarter. | 0 | N/A | 0 | N/A | 2011-05-17 15:11 | 2011-05-17 15:11 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2011 | Q2 | Q2 - 2011 | 2940 | 3227 | FALSE | 9 | Construction start delayed due to EA approval. Will receive some fiber optic cable, network equipment and huts during quarter. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 30 | Delay in EA approval delayed site preparation activities. | 10 | Received some network equipment ahead of schedule. | 0 | Construction scheduled to start Y2Q2 | 0 | N/A | 0 | N/A | 2011-08-05 16:56 | 2011-08-05 16:56 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2011 | Q3 | Q3 - 2011 | 4002 | 3840 | FALSE | 34 | Construction start delayed until approval of EA(expected11/2011) moving forward with procurement and start construction in 12/2011 | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 20 | Cannot start until approval of EA (expected 11/2011) | 98 | Approximately 20% of cable received, but not invoiced. Awaiting nextowrk build to start in 12/2011 | 5 | Arrival of remainder of transport equipment. Network build to start in 12/2011 | 0 | N/A | 0 | N/A | 2011-11-14 08:21 | 2011-11-14 08:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2011 | Q4 | Q4 - 2011 | 5410 | 5091 | FALSE | 50 | Construction started in January 2012 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Awaiting on utility to place new duct | 25 | Site work to being March 2012 | 100 | Complete | 12 | Will construct 20 miles of cable in Y3Q1 (Y2Q3) | 0 | Equipment deployed after completion of site work | 0 | Network testing to begin after completion of equipment installation | 2012-02-29 15:09 | 2012-02-29 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2012 | Q1 | Q1 - 2012 | 5964 | 5581 | FALSE | 58 | Construction delayed due to delay in EA approval | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Bridge bids to be awarded in Y2Q4 (June 2012 qtr) | 66 | Will complete site work on 3 of 4 hut sites in Y2Q4, June qtr 2012 | 100 | Complete | 33 | Construct 40 miles in Y2Q4, June qtr 2012 for total of 56 miles | 0 | Awaiting completion of cable and site work | 0 | Awaiting completion of equipment installation | 2012-05-08 14:23 | 2012-05-08 14:23 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2012 | Q2 | Q2 - 2012 | 7220 | 6237 | FALSE | 67 | Construction delayed due to delay in EA approval | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 77 | Construct 50 miles in 3rd qtr of 2012 | 0 | Awaiting completion of cable | 0 | Awaiting complettion of equipment installation | 2012-08-23 10:39 | 2012-08-23 10:39 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2012 | Q3 | Q3 - 2012 | 7750 | 6569 | FALSE | 79 | Moved from 64% to 79% completed. Construction delayed due to EA approval delay & permitting with Suffolk & Chesapeake. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 94 | Construct 30 miles in Y3Q4 (Y3Q2) | 15 | To start after completion of huts (nodes) | 0 | Awaiting completion of equipment installation | 2012-11-01 13:31 | 2012-11-01 13:31 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2012 | Q4 | Q4 - 2012 | 8998 | 7776 | FALSE | 75 | Delayed awaiting approval of agreements with Chesapeake and Surry | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 96 | Construct 20 miles in Y3Q3 | 35 | To continue after completion of nodes | 35 | Awaiting completion of equipment installation | 2013-02-27 10:33 | 2013-02-27 10:33 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2013 | Q1 | Q1 - 2013 | 9674 | 8369 | FALSE | 88 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-10 08:38 | 2013-05-10 08:38 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2013 | Q2 | Q2 - 2013 | 10602 | 8958 | FALSE | 86 | Project Complete by 9/30/13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Construction, installation and testing complete by 8/31/13 | 100 | Construction, installation and testing complete by 8/31/13 | 100 | Construction, installation and testing complete by 8/31/13 | 2013-08-15 11:17 | 2013-08-15 11:17 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | 2013 | Q3 | Q3 - 2013 | 12326 | 10499 | FALSE | 100 | Complete: 86% of Grant Funds Spent | 0 |  | N/A | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 2014-07-25 16:21 | 2014-07-25 16:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative
NT10BIX5570088 | 2010 | Q4 | Q4 - 2010 | 520 | 1541 | FALSE | 1 | An additional .5% will be completed for next quarter indicating a 1% completion for next quarter. This is consistent with our baseline. | 25 | Admin, Legal, Arch/ Engr. Fees | Match / Staff Time | 90 | Possible changes to Charlotte's network design approach may change the final EA study required. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-25 08:46 | 2011-01-25 08:46 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2011 | Q1 | Q1 - 2011 | 1892 | 2691 | FALSE | 2 | Due to new RFP Re-issue, overall project will not meet baseline expectations. | 33 | Admin, Legal, Arch/ Engr. Fee | No variance | 90 | Due to new RFP issued E/A will not complete until solution/vendor is determined | 0 | No variance | 2 | EA Draft + New Tech. Contractor + Contractor for Contracting support | 0 | No variance | 0 | N/A | 0 | Due to New RFP issued, no equipment will be purchased in this quarter. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-05-05 09:59 | 2011-05-05 09:59 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2011 | Q2 | Q2 - 2011 | 2930 | 3222 | FALSE | 1 | Not 20% due to restructuring of project and reissued a new RFP. | 85 | Admin, Legal, Arch/Engr. Fee | Not 41% because additional staff time will be spent completing procurement process for a BTOP Vendor. | 90 | Not 100% complete until vendor and solution is selected and design approve. | 0 | Not 100% due to restructuring of project and reissued a new RFP. | 1 | Not 0% because invested in Technical Consultant services to assist in project restructuring. | 0 | No Variance | 0 | N/A | 0 | Not 5% until vendor & solution is selected and approved. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-08-04 17:40 | 2011-08-04 17:40 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2011 | Q3 | Q3 - 2011 | 3478 | 3505 | FALSE | 11 | Not 21%. Charlotte will be about 3 months behind baseline milestones. | 100 | a. Admin. & Legal, d. Arch & Engr. | Not. 50%. Due to additional staff effort needed to re-issue 2nd RFP, evaluation & negotiations processes or a BTOP contractor. | 100 | No Variance - Charlotte will be seeking a categorical exclusion in this quarter. | 100 | No Variance | 1 | Not 14%. Charlotte has not yet recognized tower space opportunity cost and original budget erroneously budget space that was not compliant with OMB. | 0 | No Variance | 0 | N/A | 0 | Not 5%. The re issuance of a 2nd RFP put Charlotte behind schedule. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-10-26 14:14 | 2011-10-26 14:14 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2011 | Q4 | Q4 - 2011 | 4858 | 4555 | FALSE | 20 | Not 59%. Charlotte expects to be back on course by end of Q2 2012. | 52 | a. Admin. & Legal, d. Arch & Engr. | Not 58%. Mostly due to Re-budgeting | 100 | No Variance | 100 | No Variance | 32 | Not 29%. Charlotte expects to be on course by end of Q2 2012. | 75 | Not 100%. Charlotte expects to complete all permitting by June 2012. | 0 | N/A | 13 | Not 100%. Charlotte expects to have all equipment delivered by mid Q2 2012. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-02-01 13:31 | 2012-02-01 13:31 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2012 | Q1 | Q1 - 2012 | 5598 | 5396 | FALSE | 28 | Not 60%. Expect to be back on course in 2012 Q3. | 91 | a.Admin & Legal | Not 60%. More staff and time needed than realized. | 100 | No Variance | 100 | No Variance | 38 | Not 43%. Expect to be back on course in 2012 Q3. | 22 | Not 100%. Permitting may be extended thru July 2012. | 0 | No Variance | 15 | Not 100%. Phase 2 Equipment will be delayed beyond this quarter. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-04-27 09:54 | 2012-04-27 09:54 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2012 | Q2 | Q2 - 2012 | 6922 | 6088 | FALSE | 22 | Not 60%. Project on Suspension | 100 |  | More staff and time was used when re-issue RFP and Project was redefined. | 95 | Suspension | 100 | No Variance | 32 | Not 57%. Due to Suspension | 4 | Not 100%. Due to Suspension. | 0 | No Variance | 13 | Not 100%. Due to Suspension | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-08-08 09:33 | 2012-08-08 09:33 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2012 | Q3 | Q3 - 2012 | 7756 | 6572 | FALSE | 23 | Project Suspension | 100 | a. Admin. Legal, d. Arch & Engr | More staff required when re-issue RFP and Project was redefined. | 95 | Project Suspension | 100 | No Variance | 32 | Project Suspension | 4 | Project Suspension | 0 | No Variance | 13 | Project Suspension | 0 | Project Suspension | 0 | Project Suspension | 0 | Project Suspension | 2012-11-01 14:50 | 2012-11-01 14:50 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2012 | Q4 | Q4 - 2012 | 8652 | 7472 | FALSE | 23 | Project under suspension | 100 | a. Admin & Legal | More staff time on re-issued RFP and redefining Project. | 95 | Project under suspension | 100 | No Variance | 48 | Active tower leases signed before suspension | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-02-04 11:27 | 2013-02-04 11:27 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2013 | Q1 | Q1 - 2013 | 9678 | 8371 | FALSE | 25 | Project under suspension | 100 | a. Admin | More staff time required when original RFP was revised & reissued | 95 | Project under suspension | 100 | No Variance | 61 | Active Tower Leases before suspension. | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-05-10 10:37 | 2013-05-10 10:37 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2013 | Q2 | Q2 - 2013 | 10122 | 8624 | FALSE | 26 | Project is under suspension | 100 | A; Admin & Legal | Extra staff time occurred when RFP process was repeated. | 95 | Project is under suspension | 100 | No variance | 61 | Tower leases obligated before suspension | 4 | Project is under suspension | 0 | No variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-07-23 11:37 | 2013-07-23 11:37 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2013 | Q3 | Q3 - 2013 | 10974 | 9203 | FALSE | 27 | Project is under suspension | 100 | a: Admin & Legal | Extra staff time when repeated RFP process | 95 | Project is under suspension | 100 | No Variance | 61 | Obligated Tower Leases | 4 | Project is under suspension | 0 | No Variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-10-28 16:06 | 2013-10-28 16:06 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2013 | Q4 | Q4 - 2013 | 11850 | 10022 | FALSE | 47 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 100 | a:Admin & Legal | Accrued as a result of repeated RFP process and project suspension Reflects substantial increases from ALU closeout. | 95 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 100 | No Variance | 65 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 4 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 0 | No Variance | 25 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 0 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 0 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 50 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 2014-02-20 09:06 | 2014-02-20 09:06 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2014 | Q1 | Q1 - 2014 | 12208 | 10382 | FALSE | 50 | Suspension due to Middle Class Tax Relief Act delayed progress. | 100 | A; Admin & Legal | Accrued as a result of repeated RFP, Grant extension and Suspension due to Middle Class Tax Relief Act delayed progress. | 95 | Suspension due to Middle Class Tax Relief Act delayed progress. | 100 | No Variance | 49 | Suspension due to Middle Class Tax Relief Act delayed progress. | 4 | Suspension due to Middle Class Tax Relief Act delayed progress. | 33 | Suspension due to Middle Class Tax Relief Act delayed progress. | 31 | Suspension due to Middle Class Tax Relief Act delayed progress. | 0 | Suspension due to Middle Class Tax Relief Act delayed progress. | 0 | Suspension due to Middle Class Tax Relief Act delayed progress. | 30 | Suspension due to Middle Class Tax Relief Act delayed progress. | 2014-05-19 08:45 | 2014-05-19 08:45 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2014 | Q2 | Q2 - 2014 | 12412 | 10602 | FALSE | 55 | Project was restructured and grant extended till 9/30/15. | 84 | a: Admin & legal | Project was restructured and grant extended till 9/30/15. | 100 | Project was restructured with no outside construction planned. | 100 | Project was restructured no longer building LTE network. | 100 | Not a part of restructured project. | 100 | Project was restructured with no outside construction planned. | 72 | Project was restructured and grant extended till 9/30/15. | 36 | Project was restructured and grant extended till 9/30/15. | 0 | Project was restructured no longer building LTE network. | 0 | Project was restructured and grant extended till 9/30/15. | 100 | Project was restructured no longer building LTE network. | 2014-08-14 13:08 | 2014-08-14 13:08 | 7273 | 7273 | Charlotte, City of
NT10BIX5570088 | 2014 | Q3 | Q3 - 2014 | 12586 | 10861 | FALSE | 60 | Project was restructured and grant extended to 9/30/15. | 86 | A: Admin & Legal | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured with no outside construction planned. | 100 | Project was restructured and no longer building LTE network. | 100 | Not a Milestone in the restructured project. | 100 | Project was restructured with no outside construction planned. | 75 | Project was restructured and grant extended to 9/30/15. | 42 | Project was restructured and grant extended to 9/30/15. | 0 | Project was restructured and no longer building LTE network. | 33 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and no longer building LTE network. | 2014-11-11 09:45 | 2014-11-11 09:45 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2014 | Q4 | Q4 - 2014 | 12686 | 11008 | FALSE | 82 | Project was restructured and grant extended to 9/30/15. | 92 | a: Admin & Legal | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and no outside construction planned. | 100 | Project was restructured and no longer building LTE network. | 100 | Not a milestone in the restructured project. | 100 | Project was restructured and no outside construction planned. | 82 | Project was restructured and grant extended to 9/30/15. | 76 | Project was restructured and grant extended to 9/30/15. | 0 | Project was restructured and no longer building LTE network. | 70 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and no longer building LTE network. | 2015-02-11 16:32 | 2015-02-11 16:32 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2015 | Q1 | Q1 - 2015 | 12840 | 11213 | FALSE | 90 | Project was restructured and grant extended to 9/30/15. | 96 | Admin & Legal | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and no construction planned. | 100 | Project was restructured and no longer building LTE network. | 100 | Not a milestone in the restructured project. | 100 | Project was restructured and no construction planned. | 100 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and grant extended to 9/30/15. | 0 | Project was restructured and no longer building LTE network. | 100 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and no longer building LTE network. | 2015-05-26 09:31 | 2015-05-26 09:31 | 6166 | 6166 | Charlotte, City of
NT10BIX5570088 | 2015 | Q2 | Q2 - 2015 | 12894 | 11279 | FALSE | 100 | Project was restructured and grant extended to 9/30/15. | 100 | Admin & Legal | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured with no construction effort. | 100 | Project was restructured, no longer building an LTE network. | 100 | Project was restructured with no construction effort. | 100 | Project was restructured with no construction effort. | 100 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured and grant extended to 9/30/15. | 0 | Project was restructured, no longer building an LTE network. | 100 | Project was restructured and grant extended to 9/30/15. | 100 | Project was restructured, no longer building an LTE network. | 42255.4284 | 42255.4284 | 6166 | 6166 | Charlotte, City of
NT10BIX5570089 | 2010 | Q4 | Q4 - 2010 | 1088 | 2128 | FALSE | 2 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 12 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 51 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 15:38 | 2011-02-11 15:38 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2011 | Q1 | Q1 - 2011 | 2080 | 2785 | FALSE | 3 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 14 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 76 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 18 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | N/A | 2011-05-17 10:38 | 2011-05-17 10:38 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2011 | Q2 | Q2 - 2011 | 2984 | 3249 | FALSE | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 17 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays.165 | 76 | Although SAC #12 was lifted, additional work identified to this milestone is yet to be completed. | 73 | No variance. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2011-08-09 15:46 | 2011-08-09 16:12 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2011 | Q3 | Q3 - 2011 | 3632 | 3599 | FALSE | 4 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 18 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 26 | Fewer SHPO consultations were required at this point in the project. | 80 | No variance. | 0 | N/A | 0 | N/A | 35 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2011-10-28 15:10 | 2011-10-28 15:10 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2011 | Q4 | Q4 - 2011 | 4860 | 4558 | FALSE | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 21 | PMO | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. These Program Management and Project Management resources are projected to be included in future budget amendment. | 41 | Fewer SHPO consultations were required at this point in the project. | 100 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2012-02-02 14:20 | 2012-02-02 14:26 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2012 | Q1 | Q1 - 2012 | 5934 | 5566 | FALSE | 6 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 24 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. These Program Management and Project Management resources are projected to be included in future budget amendments. | 41 | Fewer SHPO consultations were required at this point in the project. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 90% complete by the end of next quarter, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2012-05-07 08:53 | 2012-05-07 08:53 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2012 | Q2 | Q2 - 2012 | 6886 | 6069 | FALSE | 7 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 29 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Although the Project Baseline report indicates that Motorola Solutions should be 90% complete by the end of next quarter, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2012-08-07 13:01 | 2012-08-07 13:03 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2012 | Q3 | Q3 - 2012 | 7804 | 6605 | FALSE | 8 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 34 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2012-11-08 16:23 | 2012-11-08 16:23 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2012 | Q4 | Q4 - 2012 | 8504 | 7225 | FALSE | 9 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 34 | Other | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-01-30 15:29 | 2013-01-30 15:29 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2013 | Q1 | Q1 - 2013 | 9680 | 8372 | FALSE | 10 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 36 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-05-10 12:26 | 2013-05-10 12:26 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2013 | Q2 | Q2 - 2013 | 10166 | 8659 | FALSE | 10 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 37 | Project Mgmt | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 53 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-07-26 09:45 | 2013-07-26 09:45 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2013 | Q3 | Q3 - 2013 | 11206 | 9392 | FALSE | 11 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 40 | Other | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 100 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-11-07 14:58 | 2013-11-07 14:58 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570089 | 2013 | Q4 | Q4 - 2013 | 12170 | 10354 | FALSE | 12 | The indicated variance from the baseline plan is due to the expiration of the Grant. The cost incurred during this quarter are related to the close out of the Grant. | 41 | N/A | Fewer State Historic Preservation Office consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 55 | No further State Historic Preservation Office consultations will be required at this point in the project. See 1 above for further explanation | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements). The network was fully designed, but not implemented due to the partial suspension of the Grant. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2014-05-07 11:23 | 2014-05-07 11:23 | 6531 | 6531 | Motorola Solutions, Inc.
NT10BIX5570090 | 2010 | Q4 | Q4 - 2010 | 1272 | 2298 | FALSE | 20 | On Schedule | 0 |  | N/A | 100 | On Schedule | 50 | On Schedule | 30 | On Schedule | 30 | On Schedule | 0 | N/A | 80 | On Schedule | 0 | On Schedule | 40 | On Schedule | 0 | On Schedule | 2011-02-22 10:09 | 2011-02-22 10:09 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2011 | Q1 | Q1 - 2011 | 2278 | 2884 | FALSE | 15 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline | 0 |  | N/A | 100 | On Schedule | 60 | On Schedule | 30 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 60 | On Schedule | 0 | N/A | 80 | Behind schedule, not an issue at this time. Construction will shift to 2012 but finish before deadline. | 10 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule, not an issue at this time. Construction will shift to 2012 but finish before deadline. | 0 | On Schedule | 2011-05-24 12:39 | 2011-05-24 12:39 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2011 | Q2 | Q2 - 2011 | 3362 | 3444 | FALSE | 24 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline | 0 |  | N/A | 100 | On Schedule | 60 | On Schedule | 60 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 60 | On Schedule | 0 | N/A | 50 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 15 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 0 | On Schedule | 2011-08-29 17:50 | 2011-08-29 17:50 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2011 | Q3 | Q3 - 2011 | 4178 | 3937 | FALSE | 20 | Behind schedule due to EA. Construction will shift to 2012 but will finish before deadline. | 0 |  | N/A | 100 | On schedule | 60 | On schedule | 60 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 60 | On schedule | 0 | N/A | 50 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 20 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 0 | On schedule | 2011-11-21 10:56 | 2011-11-21 10:56 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2011 | Q4 | Q4 - 2011 | 5042 | 4712 | FALSE | 32 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 0 |  | N/A | 100 | On schedule. | 80 | On Schedule | 80 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 80 | On schedule. | 0 | N/A | 90 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 23 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 90 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 20 | On schedule based on fiber miles deployed. | 2012-02-15 15:25 | 2012-02-15 15:25 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2012 | Q1 | Q1 - 2012 | 6294 | 5749 | FALSE | 62 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 90 | On Schedule. | 90 | On Schedule. | 80 | On Schedule. | 0 | N/A | 100 | On Schedule. | 45 | On Schedule. | 95 | On Schedule. | 40 | On schedule based on fiber miles deployed | 2012-05-25 10:08 | 2012-05-25 10:08 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2012 | Q2 | Q2 - 2012 | 7206 | 6230 | FALSE | 82 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 70 | On Schedule. | 95 | On Schedule. | 70 | On schedule based on fiber miles deployed | 2012-08-22 12:45 | 2012-08-22 12:45 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2012 | Q3 | Q3 - 2012 | 8082 | 6747 | FALSE | 87 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 95 | On Schedule. | 80 | On Schedule based on fiber miles deployed. | 2012-11-27 16:23 | 2012-11-27 16:23 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2012 | Q4 | Q4 - 2012 | 9060 | 7835 | FALSE | 90 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 95 | On Schedule. | 80 | On Schedule based on fiber miles deployed. | 2013-02-28 11:47 | 2013-02-28 11:47 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2013 | Q1 | Q1 - 2013 | 9704 | 8385 | FALSE | 96 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 100 | On Schedule. | 100 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 99 | On Schedule. | 95 | On Schedule based on fiber miles deployed. | 2013-05-13 15:55 | 2013-05-13 15:55 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2013 | Q2 | Q2 - 2013 | 10578 | 8945 | FALSE | 100 | On schedule | 0 |  | N/A | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 0 | N/A | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule based on fiber miles deployed | 2013-08-14 11:12 | 2013-08-14 11:12 | 6433 | 6433 | DCN, LLC
NT10BIX5570090 | 2013 | Q3 | Q3 - 2013 | 11936 | 10104 | FALSE | 100 | On Schedule | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-07 16:32 | 2014-03-07 16:32 | 6433 | 6433 | DCN, LLC
NT10BIX5570091 | 2010 | Q4 | Q4 - 2010 | 1154 | 2195 | FALSE | 32 | None | 50 |  | None | 95 | extended EA deadline to 4/1/11 | 100 | Design will be completed by 3/31/11 | 95 | None | 5 | None | 20 | delayed due to route changes relating to exclusive right-of-ways | 20 | includes RFP process, setting up contracts after bids, no expenditures during quarter | 5 | No actual build will be completed, but work will be completed for contracts and all bids will be recieved | 0 | None | 10 | None | 2011-02-15 17:13 | 2011-02-15 17:13 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2011 | Q1 | Q1 - 2011 | 2224 | 2857 | FALSE | 20 | Delayed due to structure of delayed payments to engineering/environmental firms and construction firms. The delay is also caused by proposing route changes during Q1-2011. Actual expenditures during this perion will not be as high as forecasted in our baseline plan. | 50 |  | None | 100 | None | 100 | None | 100 | None | 5 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 20 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 0 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 2011-05-20 16:00 | 2011-05-20 16:00 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2011 | Q2 | Q2 - 2011 | 2970 | 3242 | FALSE | 15 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 25 | OSS Software | Bluebird Media was focused on the route changes and FONSI during Q1 and Q2 2011 delaying the roll out of OSS software. Bluebird plans to work diligently the next two quarters to implement the software. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during the construction period will be the remaining 5 percent to complete. | 100 | None | 100 | None | 55 | The advance of construction permits and other approvals will be caused by completing agreements with state agencies and starting all fiber build routes during this quarter. | 33 | The delay will be caused by the timing to complete agreements with state agencies. This in return delayed the state site selections delaying the site preparation. | 49 | The advance of equipment procurement will be caused by completing several contracts and starting all fiber build routes during this quarter. | 8 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 10 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 0 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 2011-08-09 12:22 | 2011-08-09 12:22 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2011 | Q3 | Q3 - 2011 | 4250 | 3975 | FALSE | 20 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 50 | OSS Software | Bluebird Media was focused on the route changes and FONSI during Q1 and Q2 2011 delaying the roll out of OSS software. Bluebird entered into agreements with software companies during Q3-2011 and plans to implement the OSS software during Q4-2011. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during the construction period will be the remaining 5 percent to complete. | 100 | None | 100 | None | 75 | The advance of construction permits and other approvals will be caused by completing agreements with Railroad companies and continuing all fiber build routes during this quarter. | 55 | None | 45 | Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. One of two of these contracts were finalized during Q3 2011 and purchase orders have been put in place to procure equipment in Q4 2011. The plan is to catch up to the revised baseline during Q1-2012 once another contract is finalized during Q4-2011 and equipment is shipped during Q1-2012. | 28 | The delay was caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 20 | None | 10 | None | 2011-11-23 12:39 | 2011-11-23 12:39 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2011 | Q4 | Q4 - 2011 | 5004 | 4677 | FALSE | 37 | The delay will be caused by not having an independent appraisal completed for the in-kind contribution by the end of the quarter. Currently Bluebird estimated the contribution of $10.5 million. The plan is to catch up to the revised baseline during Q2-2012 once the appraisal of the in-kind contribution has been completed. | 50 | OSS Software | Bluebird entered into agreements with software companies during Q3-2011 and plans to implement the OSS software during Q1-2012. | 95 | None | 100 | None | 100 | None | 85 | The delay will be caused by Bluebird not filling out the appropriate permits until the timing is appropriate. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q2-2012. | 75 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. The plan is to catch up to the revised baseline during Q2-2012. | 63 | Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. The plan is to catch up to the revised baseline during Q2-2012 once equipment is shipped and billed during Q1-2012. | 48 | None | 30 | None | 20 | None | 2012-02-14 15:38 | 2012-02-14 15:38 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2012 | Q1 | Q1 - 2012 | 6116 | 5660 | FALSE | 77 | None | 100 | OSS | None | 95 | None | 100 | None | 100 | None | 95 | The delay will be caused by various permits and other approvals that come up during construction during Q2-2012 that will be unforeseeable. The plan is to catch up to the revised baseline during Q3-2012 completing all permits and approvals. | 100 | None | 90 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q2-2012 with all equipment being in place by end of Q3-2012. | 90 | All projects have deadlines prior to Q2-2012 ending. Bluebird plans to be ahead of the baseline after this quarter with just laterals left to build. | 50 | None | 30 | None | 2012-05-15 17:27 | 2012-05-15 17:27 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2012 | Q2 | Q2 - 2012 | 6734 | 5993 | FALSE | 88 | None | 100 | OSS Software | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 90 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q3-2012 with all equipment being in place by early Q4-2012. | 90 | Ahead of schedule due to several build segments being completed during Q3-2012 along with all fiber IRU being signed. | 60 | None | 50 | None | 2012-07-30 17:46 | 2012-07-30 17:46 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2012 | Q3 | Q3 - 2012 | 7986 | 6699 | FALSE | 95 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 95 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q4-2012 with all equipment being in place by early Q1-2013. | 91 | None | 75 | None | 60 | None | 2012-11-20 16:18 | 2012-11-20 16:18 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2012 | Q4 | Q4 - 2012 | 8456 | 7176 | FALSE | 98 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 98 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q1-2013 with all equipment being in place and invoiced by late Q1-2013. | 95 | None | 90 | None | 75 | None | 2013-01-30 13:36 | 2013-01-30 13:36 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2013 | Q1 | Q1 - 2013 | 9936 | 8511 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2013-05-28 14:24 | 2013-05-28 14:24 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2013 | Q2 | Q2 - 2013 | 10478 | 8887 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2013-08-02 15:24 | 2013-08-02 15:24 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570091 | 2013 | Q3 | Q3 - 2013 | 11584 | 9705 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2014-01-10 14:05 | 2014-01-10 14:05 | 6101 | 6101 | Bluebird Media, L.L.C.
NT10BIX5570093 | 2010 | Q4 | Q4 - 2010 | 894 | 1938 | FALSE | 5 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 90 | No Variance | 100 | No Variance | 100 | No Variance | 0 | No Variance | 13 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-01-29 10:54 | 2011-01-29 10:54 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2011 | Q1 | Q1 - 2011 | 2026 | 2758 | FALSE | 5 | no Variance - With regards to project progression and budget expenditures Citizens and it's contractor have began preliminary Engineering work. Citizens has absorbed all of these costs and will look to get reimbursement for the Federal portion once FONSI has been issued and we can begin drawing down funds. | 0 | N/A | no Variance | 100 | no Variance | 100 | no Variance | 100 | no Variance | 100 | no Variance | 50 | no Variance | 13 | no Variance | 0 | no Variance | 0 | no Variance | 0 | no Variance | 2011-05-13 16:15 | 2011-05-13 16:15 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2011 | Q2 | Q2 - 2011 | 2994 | 3254 | FALSE | 23 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 50 | No Variance | 90 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. | 5 | Construction will be impacted by the long lead time in obtaining fiber and possibly other materials. | 0 | No Variance | 0 | No Variance | 2011-08-10 11:20 | 2011-08-10 11:20 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2011 | Q3 | Q3 - 2011 | 4070 | 3878 | FALSE | 19 | Citizens had anticipated having approximately 71 miles (39%) of aerial and buried fiber construction completed by the end of quarter 6. Start of construction has been delayed due to the unavailability of fiber optic cable and the delay in getting ship dates for the fiber cable. Starting construction on Contract I and Contract II had been delayed 15 weeks by the end of the 5th quarter and will be approximately 23 weeks behind the original planned start dates by the end of the 6th quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 50 | No Variance | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received and paid for during the 6th quarter. | 9 | Citizens had anticipated having 38% of the network construction completed by the end of the 6th quarter. Construction will be impacted by the long lead time in obtaining fiber cable and other materials. | 0 | No Variance | 0 | No Variance | 2011-11-16 14:33 | 2011-11-16 14:33 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2011 | Q4 | Q4 - 2011 | 4638 | 4282 | FALSE | 26 | Citizens had anticipated having approximately 89 miles (47%) of aerial and buried fiber construction complete by the end of quarter 7. Start of construction has been delayed due to the unavailability of fiber optic cable. Starting construction on Contract I and Contract II has been delayed approximately 23 weeks by the end of the 6th quarter. Citizens, Thompson&Litton, and the contractors are exploring options on how to increase production and bring the milestones in line with the original projections. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Citizens had projected having 50% of the site work completed for the two telecommunication huts proposed in the project. The contractor expedited this work in order to beat the winter season. The Pulaski site has a small amount of cleanup work remaining to be completed at the end of the quarter. | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received in the 6th quarter. | 23 | Citizens had anticipated having 47% of the network construction completed by the end of the 7th quarter. Construction has been impacted by the long lead time in obtaining fiber cable and other materials. Citizens had anticipated having 38% of the network construction completed by the end of the 6th quarter. Construction will be impacted by the long lead time in obtaining fiber cable and other materials. | 0 | No Variance | 0 | No Variance | 2012-01-30 10:37 | 2012-01-30 10:37 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2012 | Q1 | Q1 - 2012 | 5812 | 5505 | FALSE | 38 | Citizens had anticipated having 69% of the network construction completed by the end of the 8th quarter. Construction was impacted by the long lead time in obtaining fiber cable and other materials. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 56 | Citizens had anticipated having 68% of the network construction completed by the end of the 8th quarter. Construction was impacted by the long lead time in obtaining fiber cable and other materials. If Network build continues at the current pace, the project will be within 12% of the original projected milestones by the end of the 8th quarter. | 0 | Citizens had anticipated having 60% of the equipment installed at the end of the 8th quarter. Delays in starting construction due to the lead time of fiber cable and waiting for approval of the EA has limited the amount of Equipment Deployment. | 20 | No Variance | 2012-04-30 16:37 | 2012-04-30 16:37 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2012 | Q2 | Q2 - 2012 | 7148 | 6201 | FALSE | 57 | Lag time between construction being completed and invoices being created, verified, and approved represents the difference between the overall project and the Network Build. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 89 | Citizens had projected having approximately 144 miles (77%) of aerial and buried fiber construction complete by the end of quarter 9. At the current pace and schedule, the project should be ahead of the original projections by the end of this quarter. | 60 | No Variance | 68 | No Variance | 2012-08-20 09:57 | 2012-08-20 09:57 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2012 | Q3 | Q3 - 2012 | 7948 | 6679 | FALSE | 84 | Citizens originally projected having 93% of the project complete by the end of the 10th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 100% complete at the end of the 10th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Citizens had projected having approximately 173 miles (93%) of aerial and buried fiber construction complete by the end of quarter 10. At the current pace and schedule of the construction, the project should be ahead of the original projections by the end of this quarter. | 80 | No Variance | 77 | No Variance | 2012-11-19 08:56 | 2012-11-19 08:56 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2012 | Q4 | Q4 - 2012 | 8432 | 7129 | FALSE | 85 | Citizens originally projected having 95% of the project complete by the end of the 11th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 96% complete at the end of the 11th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 96 | No Variance | 80 | No Variance | 96 | All testing should be finished on all completed fiber. Only the construction delayed by make-ready issues will remain. | 2013-01-30 10:52 | 2013-01-30 10:52 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2013 | Q1 | Q1 - 2013 | 10026 | 8563 | FALSE | 94 | Citizens originally projected having 100% of the project complete by the end of the 12th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 100% complete at the end of the 12th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-05-31 14:47 | 2013-05-31 14:47 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2013 | Q2 | Q2 - 2013 | 10774 | 9052 | FALSE | 96 | Citizens originally projected this amount to be 100% by the end of the project. Since this percentage is calculated on actual expenditures and Citizens will be coming in under budget on the project, this amount is lower than 100%. As of the end of the project on July 31, 2013, 100% of the project was complete. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-08-27 16:42 | 2013-08-27 16:42 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570093 | 2013 | Q3 | Q3 - 2013 | 11470 | 9583 | FALSE | 100 | No Variance | 100 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-11 11:40 | 2013-12-11 11:40 | 6099 | 6099 | Citizens' Telephone Co-operative
NT10BIX5570094 | 2010 | Q4 | Q4 - 2010 | 556 | 1575 | FALSE | 22 | N/A | 7 | Engineering Services | N/A | 0 | N/A | 21 | N/A | 0 | N/A | 0 | N/A | 100 | N/A | 20 | N/A | 43 | N/A | 4 | N/A | 0 | N/A | 2011-01-26 16:14 | 2011-01-26 16:14 | 5293 | 5293 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2011 | Q1 | Q1 - 2011 | 2018 | 2754 | FALSE | 15 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 11 | Engineering Services | The State anticipated procurement activities for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 0 | N/A | 13 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 0 | N/A | 0 | N/A | 0 | Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 11 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 9 | No variance from baseline. | 0 | No variance from baseline. | 2011-05-13 14:49 | 2011-05-13 14:49 | 5293 | 5293 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2011 | Q2 | Q2 - 2011 | 3050 | 3282 | FALSE | 32 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 32 |  | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 0 | N/A | 42 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 0 | N/A | 0 | N/A | 100 | Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 25 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 62 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 21 | No variance from baseline. | 13 | No variance from baseline. | 2011-08-12 15:14 | 2011-08-12 15:14 | 5293 | 5293 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2011 | Q3 | Q3 - 2011 | 4368 | 4040 | FALSE | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Planned percentages are based on the negotiated project schedule and payment milestones in the LTE Broadband contract executed on August 11, 2011 with Motorola Solutions, Inc. | 66 |  | Microwave backhaul project management components of payment milestones will occur during the fourth quarter. initial milestones for training of state staff on eNodeBs will also occur during the quarter. | 0 | N/A | 59 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The first contractual payment milestone for the design and provisioning of eNodeBs will occur in the fourth quarter 2011. | 0 | N/A | 0 | N/A | 100 | Site preparation for equipment at UMMC has been delayed until Year 2 Q2. | 28 | The detailed design plan approval milestone for the eNodeBs will be achieved during next quarter. Microwave backhaul installation, integration and acceptance testing milestones will be achieved for the sites in MSWIN Phase 2. MS MedCom is scheduled to complete procurement of a major component of their ambulance data transmission equipment. | 58 | Payment milestones will be met on the design for 5 new MSWIN towers that will be used as BTOP match. Tower lease payments (Cash Match) will continue on leased tower sites. Due Diligence payments on Phase 3 tower sites(cash Match, will be paid during the fourth quarter, 2011. | 16 | Contractual payment milestones for the detailed design on the Core and eNodeB network will be achieved during the fourth quarter. Delivery of eNode B equipment to the tower sites will begin during the fourth quarter. | 0 | Baseline for year 2 quarter 2 is 25%. Network testing will not begin during the next quarter. | 2011-12-02 09:56 | 2011-12-02 09:56 | 5293 | 5293 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2011 | Q4 | Q4 - 2011 | 5044 | 4718 | FALSE | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Planned percentages are based on the negotiated project schedule and payment milestones in the LTE Broadband contract executed on August 11, 2011 with Motorola Solutions, Inc. | 54 |  | Microwave backhaul project management components of payment milestones will occur during the quarter. | 0 | N/A | 7 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The first contractual payment milestone for the design and provisioning of eNodeBs will occur in the first quarter 2012. | 0 | N/A | 0 | N/A | 0 | The site preparation has been delayed for two reasons. First, Mississippi MED-COM is housed in the State of Mississippiâ€™s only Level I Trauma center and there are three large construction projects going on in and around MED-COMâ€™s physical location. Our construction is a component of the three other larger programs in terms of allocation of resources, generator emergency power allocation and to ensure that our current MED-COM operations will not be hampered by loss of electrical, HVAC or other utilities during the three construction projects. The expansion of the equipment room is into physical space currently used by our Cardiovascular Services- a mission critical component of the medical center. We have been waiting re-location of that service for a smaller than originally planned portion of that area. Second- we have been awaiting the final electrical specifications of the PSAP component of the grant- in order to have completed the electrical planning and quotation. Those | 34 | The detailed design plan approval milestone for the Core will be achieved during next quarter. Microwave backhaul installation, integration and acceptance testing milestones will be achieved for the sites in MSWIN Phase 2 C& D. 33 sets of antenna arrays will be installed on MSWIN sites. The eNodeB equipment will be delivered to 45 MSWIN sites. | 46 | Payment milestones will be met on the design for 5 new MSWIN towers that will be used as BTOP match. Tower lease payments (Cash Match) will continue on leased tower sites. | 49 | The detailed design plan approval milestone for the RAN equipment will be achieved during the next quarter. | 0 | Baseline for year 2 quarter 3 is 37.5%. Network testing will begin once the core is delivered to ITS and some of the LTE sites are brought up. This is projected to begin in second quarter 2012. | 2012-02-15 16:36 | 2012-02-15 20:16 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2012 | Q1 | Q1 - 2012 | 5832 | 5515 | FALSE | 46 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. The construction of the Tower Sites in North Mississippi being used by match by the State will be complete. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the | 51 |  | Microwave backhaul project management components of payment milestones will occur during the quarter. Engineering services for training of state staff will be performed. | 0 | N/A | 32 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The system integration for the eNodeBs will continue during the next quarter. | 0 | N/A | 0 | N/A | 0 | As the site preparation construction is completed, the next phase includes the installation of various components of the new infrastructure equipment (console furniture, PSAP system, PTP MSWIN connection). As installation is completed, the next phase will be testing and acceptance of the new hardware and software. Employee training has been scheduled following anticipated equipment acceptance. | 42 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. | 69 | Payment milestones will be met on all of the MSWIN tower sites that are being used as BTOP match. Tower lease payments (cash match) will continue on leased tower sites. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. | 45 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. | 0 | Network testing will begin once the core is delivered to ITS and some of the LTE sites are brought up. This testing is projected to begin in QTR 3, 2012. | 2012-04-30 17:21 | 2012-04-30 17:21 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2012 | Q2 | Q2 - 2012 | 7044 | 6149 | FALSE | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 57 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 52 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 0 | N/A | 3 | As the site construction is completed (approximately $2400.00), the next steps will include testing and acceptance of the new consoles and software. | 45 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 77 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 45 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 2012-08-13 14:36 | 2012-08-13 14:36 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2012 | Q3 | Q3 - 2012 | 7864 | 6636 | FALSE | 54 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites, services related to the LTE core, and microwave services for Phase 2 and Phase 3 tower sites. The State anticipates the microwave backhaul equipment will be installed for 20 MSWIN LTE network links. | 78 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include microwave services for Phase 2 and Phase 3 tower sites. | 0 | N/A | 65 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core, and microwave services for Phase 2 and Phase 3 tower sites. | 0 | N/A | 0 | N/A | 1 | No site work is expected | 46 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include microwave services for Phase 2 and Phase 3 tower sites. | 88 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3 and microwave services for Phase 2 and Phase 3 tower sites. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates the microwave backhaul equipment will be installed for 20 MSWIN LTE network links. | 0 | N/A | 2012-11-14 09:36 | 2012-11-14 09:36 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2012 | Q4 | Q4 - 2012 | 8842 | 7626 | FALSE | 50 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites and services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 61 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 0 | N/A | 4 | No actual work site preparation is expected. Outstanding invoices for smaller portions of the project are pending drawdown completion. Examples of outstanding invoices include but are not limited to additional emergency power switches and fees to relocate work-stations. | 42 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. | 86 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if we are able to resolve issues issues related to the Davis Bacon Act. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates payment milestones being met for the installation of 20 MSWIN LTE network links if Davis Bacon Act compliance issues are resolved during the quarter. | 0 | N/A | 2013-02-19 14:59 | 2013-02-21 10:36 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2013 | Q1 | Q1 - 2013 | 9694 | 8380 | FALSE | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites and services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 61 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 0 | N/A | 4 | LMR installation continues. Two informational meetings were held in north Mississippi for area hospital and emergency service personnel. The meetings outlined the LMR component of the grant project. | 42 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. | 89 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if we are able to resolve issues issues related to the Davis Bacon Act. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates payment milestones being met for the installation of 20 MSWIN LTE network links if Davis Bacon Act compliance issues are resolved during the quarter. | 0 | N/A | 2013-05-13 14:43 | 2013-05-13 14:43 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2013 | Q2 | Q2 - 2013 | 10300 | 8766 | FALSE | 49 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 60 |  | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 38 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 0 | N/A | 2 | Labor and materials for installation of electrical receptacles connected to existing emergency power circuits and fire stop | 43 | WCC:We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. MedCom: - Labor and materials for installation of electrical receptacles connected to existing emergency power circuits and fire stop conduits. | 85 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 43 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 2013-07-30 10:56 | 2013-07-30 10:56 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2013 | Q3 | Q3 - 2013 | 11410 | 9522 | FALSE | 55 | WCC: No additional work/payments expected to be processed this quarter. MedCom: Expected work/payments for: Completion of physical site upgrades to accommodate additional consoles in MedCom, door installation, electrical upgrades and lighting on emergency power circuits, fire-caulking around wall penetrations. Purchase, reconfiguration and integration of Microwave link, purchase and integration of 2 additional consoles, purchase of PSAP phone system with additional hardware and line cards | 78 |  | No additional work/payments expected to be processed this quarter. | 0 | N/A | 61 | No additional work/payments expected to be processed this quarter. | 0 | N/A | 0 | N/A | 6 | MedCom: Completion of physical site upgrades to accommodate additional consoles in MedCom: door installation, electrical upgrades and lighting on emergency power circuits, fire-caulking around wall penetrations. | 47 | WCC: No additional work/payments expected to be processed this quarter. MedCom: Purchase, reconfiguration and integration of Microwave link, purchase and integration of 2 additional consoles, purchase of PSAP phone system with additional hardware and line cards | 95 | No additional work/payments expected to be processed this quarter. | 44 | No additional work/payments expected to be processed this quarter. | 0 | Budget modification removed this category as a tracking component of the Grant reporting. | 2013-11-26 16:50 | 2013-11-26 16:50 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570094 | 2013 | Q4 | Q4 - 2013 | 11708 | 9846 | FALSE | 54 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 78 |  | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | N/A | 61 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | N/A | 0 | N/A | 2 | No construction or site preparation activities are anticipated. | 45 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. MedCom: Installation of land mobile and hospital radios, control station and antenna. | 95 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 44 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | Budget modification removed this category as a tracking component of the Grant reporting. | 2014-01-30 10:45 | 2014-01-30 10:45 | 7345 | 7345 | Executive Office of the State of Mississippi
NT10BIX5570095 | 2010 | Q4 | Q4 - 2010 | 1020 | 2064 | FALSE | 10 | Timing circumstances around FONSI receipt expected to push actual. | 0 | N/A | N/A | 100 | N/A | 75 | RF Propagation redesign(s) required. | 100 | N/A | 100 | N/A | 0 | N/A | 25 | N/A | 25 | N/A | 0 | N/A | 0 | N/A | 2011-02-09 12:25 | 2011-02-09 12:25 | 5990 | 5990 | JKM Consulting, Inc.
NT10BIX5570095 | 2011 | Q1 | Q1 - 2011 | 1924 | 2707 | FALSE | 10 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 |  | N/A | 100 | N/A | 75 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 100 | N/A | 75 | US Forestry Service lost our initial application and generated delays until it was located. | 0 | N/A | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 15 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | N/A | 2011-05-10 11:56 | 2011-05-10 11:56 | 5990 | 5990 | JKM Consulting, Inc.
NT10BIX5570095 | 2011 | Q2 | Q2 - 2011 | 2954 | 3234 | FALSE | 25 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | 0 |  | n/a | 100 | n/a | 85 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 100 | n/a | 75 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | n/a | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 15 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | 0 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. Equipment should begin in 1st qtr 2012. | 0 | n/a | 2011-08-08 13:44 | 2011-08-08 13:44 | 5990 | 5990 | JKM Consulting, Inc.
NT10BIX5570095 | 2011 | Q3 | Q3 - 2011 | 4198 | 3947 | FALSE | 29 | Environmental Assessments, US Forestry permitting and world wide fiber shortages have caused significant variances to our project. Construction will begin in the upcoming quarter, therefore funds will be obligated but not necessarily expensed until the following quarter. | 0 |  | N/A | 100 | Complete | 85 | Low-cost engineering firm was producing incomplete and inaccurate documentation. We were required to release the initial engineering firm and hire a new firm. | 100 | complete | 77 | Delays due to Environmental Assessments and permitting with US Forestry have delayed state approvals. Poor quality engineering with our initial firm is requiring re-work of several permit applications. | 0 | N/A | 0 | All installation of equipment is delayed due to the construction delays releated to receipt of the FONSI last quarter. | 34 | Changes with the networks of two partners have caused significant delays in the proposed leases and IRUs. We anticipate the following quarter, going into 2012 to reflect a percentage change in this category. | 0 | N/A | 0 | N/A | 2011-11-21 17:01 | 2011-11-21 17:01 | 5990 | 5990 | JKM Consulting, Inc.
NT10BIX5570095 | 2011 | Q4 | Q4 - 2011 | 4900 | 4588 | FALSE | 33 | Previous reports detailed the delays with FONSI and tsunami issues for fiber delivery, as well as delays with initial engineering firm. Construction has commenced with fiber placement initiated and connectivity to 3 CAI's in 1Q2012. Outstanding permit issues will be resolved allowing for additional construction crew(s) deployment. Equipment delivery will commence and critical collocation agreements are finalized allowing site preparation and equipment installation. Wireless RF Engineering will be finalized during 1Q2012 for preparation of equipment selection in 2Q2012. | 0 |  | N/A | 100 | complete | 90 | Previous reports detailed the delays with FONSI and tsunami issues. Design is being held open to accommodate changes required by construction issues. Additional changes may be driven by CAI (Community Anchor Institutions) changes (some CAIs have moved or ceased operations) and FCC (Federal Communications Commission) rule changes to the wireless component. | 90 | Previous reports detailed the delays with FONSI and tsunami issues, hindering permit applications. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT; previously unplanned road construction and construction driven changes. | 95 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT; unplanned road construction and construction driven changes. | 0 | N/A | 35 | Network construction has been delayed as noted above, reducing the requirement to purchase equipment earlier. However, responses to Request for Proposals were completed this quarter and narrowed to 3 vendors with final selection due early January. | 40 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT, new previously unplanned road construction and construction driven changes. Acquisition of leased/IRU fibers have been hampered by economic impact of tornadoes to James Cable and the withdrawal of AFO from the project. | 25 | Network construction has been delayed as noted in 2g above, reducing the requirement to purchase equipment earlier. | 5 | Testing for the McClellan campus and Main Campus for Jacksonville State University will be completed this quarter, allowing us to begin testing earlier than expected. | 2012-02-07 12:02 | 2012-02-07 12:02 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2012 | Q1 | Q1 - 2012 | 6262 | 5733 | FALSE | 77 | N/A | 0 | N/A | N/A | 100 | N/A | 95 | N/A | 95 | N/A | 95 | N/A | 100 | N/A | 50 | N/A | 75 | N/A | 70 | N/A | 50 | N/A | 2012-05-23 11:09 | 2012-05-23 11:09 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2012 | Q2 | Q2 - 2012 | 6838 | 6045 | FALSE | 81 | On track with PIP filed in first quarter | 0 |  | n/a | 100 | n/a | 90 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 0 | n/a | 50 | On track with PIP filed in first quarter | 75 | On track with PIP filed in first quarter | 50 | On track with PIP filed in first quarter | 30 | On track with PIP filed in first quarter | 2012-08-02 12:22 | 2012-08-02 12:22 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2012 | Q3 | Q3 - 2012 | 7774 | 6584 | FALSE | 88 | N/A | 0 | N/A | N/A | 100 | N/A | 96 | N/A | 96 | N/A | 96 | N/A | 0 | N/A | 65 | N/A | 80 | N/A | 60 | N/A | 35 | N/A | 2012-11-06 12:02 | 2012-11-06 12:02 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2012 | Q4 | Q4 - 2012 | 8984 | 7762 | FALSE | 98 | N/A | 0 | N/A | N/A | 100 | N/A | 99 | N/A | 99 | N/A | 99 | N/A | 0 | N/A | 99 | N/A | 90 | Negotiations for the planned IRU from Southern Company have become much more difficult that originally envisioned and may be difficult to complete by end of next quarter. | 90 | N/A | 99 | N/A | 2013-02-26 15:09 | 2013-02-26 15:09 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2013 | Q1 | Q1 - 2013 | 9952 | 8520 | FALSE | 99 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 90 | N/A | 100 | N/A | 2013-05-28 20:29 | 2013-05-28 20:29 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2013 | Q2 | Q2 - 2013 | 10550 | 8929 | FALSE | 99 | n/a | 0 |  | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 99 | Selected vender for TVWS RF network has withdrawn from the market and we will need to find alternative manufacturer or alternate technology | 100 | n/a | 2013-08-09 18:22 | 2013-08-09 18:22 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2013 | Q3 | Q3 - 2013 | 11948 | 10117 | FALSE | 100 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-03-13 17:04 | 2014-03-13 17:04 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570095 | 2013 | Q4 | Q4 - 2013 | 11572 | 9696 | FALSE | 100 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-01-03 11:15 | 2014-01-03 11:15 | 5988 | 5988 | JKM Consulting, Inc.
NT10BIX5570096 | 2010 | Q4 | Q4 - 2010 | 1380 | 2392 | FALSE | 2 | Project is on schedule. All field verification will be completed this quarter | 0 |  | N/A | 100 | Enronmental Assessment will be completed. FONSI expected by March 15, 2011. | 25 | We are seeking ways to improve upon this number. | 25 | We may improve upon this number since move FAP sites are on Government owned property. | 30 | We may improve upon this number since move FAP sites are on Government owned property. | 10 | We are on target here but will seek to improve upon it since most of the FAP sites are on Government property. | 5 | We may improve upon this number since we plan to preconfigure the network gear before shipping to the NAP of Americas. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-25 16:57 | 2011-02-25 16:57 | 5238 | 5238 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2011 | Q1 | Q1 - 2011 | 2236 | 2863 | FALSE | 35 | We expect to exceed this number since we anticipate paying up front for our long term IRU agreements. | 15 |  | We anticipate no variance from the the baseline plan. | 100 | We expect no variance from the baseline plan since we fully expect to have received our FONSI. | 100 | We anticipate no variance from the the baseline plan. | 50 | We anticipate no variance from the the baseline plan. The rights of way are primarily on government property; consequently, much of the expenses will be incurred trying to negotiate with private owners. We expect to expend project funds in this category. | 50 | We anticipate no variance from the the baseline plan. Our approach will be combining our permitting applications for as many parts of the construction routes as possible. Road construction represents over 50% of the project permitting requirement. We will be submitting the permits for the road construction by next quarter. We anticipate to receive permitting within the quarter; therefore, we believe we will be at better than 50% completed in this category by the end of June 2011. | 35 | Achievement of this goal by the end of June 2011 is ambitious. Underachievement will not have a dire impact on the project overall since FAPs will be significantly complete before network completion. We will continue permitting en masse and will manage the outcome to overall achievement. | 25 | We anticipate no variance from the the baseline plan. Once the construction of the local FAPs begin we also anticipate that we may exceed this number very easily with the placement of network equipment in our own FAPs and at CAI locations. | 15 | We expect to significantly exceed this number since we expect to complete our IRU negotiations and make up front payments for long term leases and IRUs, filing of applicable and appropriate Award Action Requests notwithstanding. | 10 | We may exceed this number since we expect to deploy network gear in at least three collocation facilities. Also, once the construction of the local FAPs begin we also anticipate that we may exceed this number very easily with the placement of network equipment in our own FAPs and at CAI locations. | 10 | We anticipate no variance from the the baseline plan. | 2011-05-20 22:56 | 2011-05-20 22:56 | 5238 | 5238 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2011 | Q2 | Q2 - 2011 | 3376 | 3451 | FALSE | 43 | No variance from the baseline plan. Despite where we are in the current quarter, we believe we can make up the stagger very quickly with the execution of the IRU contracts and MOA with VIWAPA. Other material purchases for the underground network system and the beginning of major construction for the FAPs and the underground duct bank system will pick up pace over the next three months. | 25 | n/a | No variance from the baseline plan. | 100 | No variance from the baseline plan. | 100 | No variance from the baseline plan. | 50 | We expect to have have a significant reduction in expenditures in this category since a decision has been made to locate over 80% of FAP sites on Government property. this will reduce the need to expend major funds in this category. | 100 | We anticipate being ahead of the baseline plan on this milestone. | 50 | No variance from the baseline plan. | 35 | No variance from the baseline plan. | 25 | No variance from the baseline plan. Execution of the Global Crossing IRU contracts and finalizing the MOA with WAPA will result in over 25% of the network being built. | 25 | No variance from the baseline plan. | 25 | No variance from the baseline plan. | 2011-08-30 12:45 | 2011-08-30 12:45 | 5238 | 5238 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2011 | Q3 | Q3 - 2011 | 4364 | 4038 | FALSE | 12 | Additional progress is expected during Quarter 4, CY 2011, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 4, CY 2011. We do, however,anticipate under performing against this baseline indicator, given the delays in the start of trenching and build-out of the aerial and underground network to date. As we move ahead to initiate and conclude procurements related to these "deliverables" and realign our construction schedule to include parallel construction activities, we anticipate that we will be able to significantly narrow the gap between the baseline indicators and our actual performance by the end of Q2, CY 2012. | 0 |  | Under performance against this baseline indicator is associated with the reasons for the variance from the baseline plan, as noted in 2a. through 2j above. | 100 | No variance from the baseline plan | 90 | Additional progress is expected during Quarter 4, CY 2011, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 4, CY 2011. We do, however,anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs and the finalization of beach manhole landings. Additional design work will be required for the FAP and beach manhole landing relocations. | 95 | Additional progress is expected during Quarter 4, CY 2011, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI) and GVI stakeholders have been very cooperative. We do, however,anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way. | 95 | Additional progress is expected during Quarter 4, CY 2011, given the full cooperation of the governmental entities involved in providing approval. Many of the locations which will be affected during construction are owned by the GVI and are covered by master agreements. We do, however,anticipate slightly under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs and beach manhole landings. | 2 | Projected under performance in this area is based on the fact that construction-related procurements were suspended as a result of the stop work order. The delay in the procurement processes have, in turn, resulted in the delay of construction-related activities. Resumption of all procurement work related to this task will resume during Q4, CY 2011, and revised implementation schedules and related budgets will be finalized during Q4, CY 2011. | 15 | Projected under performance in this area is based on the fact that equipment-related procurements were suspended as a result of the stop work order. The delay in the equipment procurement processes have, in turn, resulted in the delay of construction-related activities. Resumption of all work related to this task will resume during Q4, CY 2011. | 7 | We project under performance against this baseline indicator as a result of the delays in the commencement of construction activities. We, however, have made some progress with our IRU contract negotiations and expect to further advance these negotiations with Global Crossing/Level 3 and AT&T with the lifting of the stop work order. Revised implementation schedules and related budgets will also be finalized during Q4, CY 2011. | 0 | We project under performance against this baseline indicator, given the delays in the commencement of construction activities. With the lifting of the stop work order, contract negotiations will resume, and revised implementation schedules and related budgets will be finalized during Q4, CY 2011. | 10 | We project under performance against this baseline because of delays in the Alpha testing by UDT. We anticipate that this testing can begin and possibly conclude during Q4, CY 2011. | 2011-11-30 22:11 | 2011-11-30 22:11 | 6449 | 6449 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2011 | Q4 | Q4 - 2011 | 5422 | 5108 | FALSE | 31 | Additional progress is expected during Quarter 1, CY 2012, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 1, CY 2012. The team does, however,anticipate under performing against this baseline milestone target, given the delays in the start of excavation, trenching and build-out of the aerial and underground network to date. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and regular FAP construction through Quarter 2, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the e | 0 |  | The VIPFA/viNGN team has mobilized and made progress towards meeting the Baseline Milestone targets. The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 1, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from the baseline plan | 100 | No variance from the baseline plan | 80 | Additional progress is expected during Quarter 1, CY 2012, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI), and GVI stakeholders have been very cooperative. The VIPFA/viNGN team does, however, anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way but still anticipate progress against the previous quarter. | 100 | No variance from the baseline plan | 5 | Additional progress is expected during Quarter 1, CY 2012 with the anticipated finalization of the solicitation for excavation and trenching work. The team does, however,anticipate under performing against this baseline milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 2, CY 2012. | 30 | Additional progress is expected during Quarter 1, CY 2012 with the build out of the network, including the start of construction of the SuperFAPs; the purchase of additional electronics and other technical equipment; and, the purchase of additional fiber. Also, equipment procurements are expected to be accelerated with the hiring of additional staff to support implementation activities. | 15 | Additional progress is expected during Quarter 1, CY 2012 with the anticipated finalization of the solicitation for excavation and trenching work. The team does, however,anticipate under performing against this baseline milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 3 | Additional progress is expected during Quarter 1, CY 2012 with the build out of the network, including the start of construction of the SuperFAPs; the purchase of additional electronics and other technical equipment; and, the purchase of additional fiber. | 10 | Additional progress is expected during Quarter 1, CY 2012 with the purchase of additional electronics and other technical equipment; the build out of the network, including the start of construction of the SuperFAPS; and, the purchase of additional fiber. | 2012-02-29 19:00 | 2012-02-29 19:00 | 7323 | 7323 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2012 | Q1 | Q1 - 2012 | 6350 | 5777 | FALSE | 31 | Additional progress is expected during Quarter 2, CY 2012, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 2, CY 2012. The team does anticipate under performing against this baseline milestone target, given the delays in the start of excavation, trenching and build-out of the aerial and underground network to date. As VIPFA/viNGN begins its excavation, trenching and fiber pulling and splicing activities and continues with the SuperFAP and regular FAP construction through Quarter 3, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 2, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from Baseline Milestone target | 100 | No variance from Baseline Milestone target | 90 | Additional progress is expected during Quarter 2, CY 2012, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI), and GVI stakeholders have been very cooperative. The VIPFA/viNGN team does, however, anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way but still anticipate progress against the previous quarter. | 100 | No variance from Baseline Milestone target | 5 | Additional progress is expected during Quarter 2, CY 2012, with the anticipated finalization of the solicitations for additional FAP construction and excavation and trenching work. The team does, however, anticipate under performing against this Baseline Milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 90 | VIPFA/viNGN anticipates over performing against this Baseline Milestone target. The VIPFA/viNGN team has made significant progress in its equipment procurement activities and currently exceeds the percentage completion against this Baseline Milestone target. The team has purchased more than 90% of the network management equipment needed for the build-out of the network. The team is awaiting delivery and final testing of these routers and switches to begin the staging for the placement of the equipment. Once the SuperFAPs and FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter. | 15 | Additional progress is expected during Quarter 2, CY 2012, with the construction of the two SuperFAPs; completion of the construction of the SuperFAPs is expected during late Quarter 2, CY 2012/early Quarter 3, CY 2012. Once they are completed, progress against this milestone will improve. Delays are anticipated in the core network build out until excavation and trenching and aerial and underground fiber pulling and splicing activities commence during the next two quarters and until the lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix is executed. Based on the status of current negotiations with AT&T, the agreement is expected to be fully executed during Quarter 2, CY 2012. A fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during the past quarter. Alternative plans to illuminate the network are currently being considered, e.g. consideration is being gi | 3 | Additional progress is expected during Quarter 2, CY 2012. Given that 1) VIPFA/viNGN has purchased a large portion of the network management equipment, 2) significant progress has been made with the construction of the two SuperFAPs, 3) the construction of the SuperFAPs is expected to be completed during late Quarter 2, CY 2012/early Quarter 3, CY 2012, 4) construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012, 5) fiber pulling and splicing in underground conduit is expected to begin during Quarter 3, CY 2012, and 6) aerial fiber pulling and splicing is expected to begin during Quarter 3, CY 2012, progress against this milestone will improve during the next two quarters, as the equipment can be deployed with the start and completion of these activities. | 5 | Additional progress is expected during Quarter 2, CY 2012. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. With the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the planned completion of construction of the SuperFAPs by late Quarter 2, CY 2012/early Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during the latter part of Quarter 2, CY 2012 or early in Quarter 3, CY 2012. Once the FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. | 2012-05-30 13:06 | 2012-05-30 13:06 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2012 | Q2 | Q2 - 2012 | 7258 | 6256 | FALSE | 35 | The SuperFAP construction is expected to be completed, and the Team intends to begin the construction of an additional six (6) FAPs during Quarter 3, CY 2012. Additional progress is expected during Quarter 3, CY 2012, based on the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 3, CY 2012. The team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds to initiate and conclude procurements and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 3, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from Baseline Milestone target; The VIPFA/viNGN team does plan to complete additional archeological surveys for FAPs that are located near historical sites during Quarter 3, CY 2012/early Quarter 4, 2012. | 100 | No variance from Baseline Milestone target | 95 | Additional progress is expected during Quarter 3, CY 2012, as additional Rights of Way are obtained for the locations of a few FAPs on private properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). | 100 | No variance from Baseline Milestone target | 80 | Additional progress is expected during Quarter 3, CY 2012 with the anticipated finalization of FAP construction and the posting of RFPs for Excavation and Underground Trenching, Underground Fiber Pulling and Splicing, and Aerial Fiber Pulling and Splicing Construction. As the Team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the Team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 92 | VIPFA/viNGN anticipates over performing against this Baseline Milestone target. The VIPFA/viNGN team has made significant progress in its equipment procurement activities and currently exceeds the percentage completion against this Baseline Milestone target. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Once permanent power is installed in the Super FAPs and the other FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team has purchased all of the needed fiber optic cable and is awaiting delivery of the final order, which is expected during Quarter 3, CY 2012. | 20 | Significant progress has been made with the construction of the two Super FAPs; completion of the construction of the Super FAPs is expected during Quarter 3, CY 2012. Once the SuperFAPs and FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, RFPs for excavation/trenching and aerial and underground fiber pulling and splicing activities are scheduled to be posted during Quarter 3, CY 2012. The VIPFA/viNGN team has also made significant progress in its equipment procurement activities and currently exceeds the percentage completion against the related Baseline Milestone target. The team has purchased all of the fiber required for its network, with the final order expected to be delivered during Quarter 3, CY 2012. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Once permanent power is installed in the Super FAPs and | 10 | When the construction of the two Super FAPs is completed during Quarter 3 CY, 2012, equipment can be deployed. As the regular FAPs are built, the routers and switches and other equipment will be installed to await final connection to the fiber to bring the network on line. | 40 | With the planned completion of construction of the two Super FAPs during Quarter 3, CY 2012, the final testing and staging for placement of the routers and switches will begin during late Quarter 3, CY 2012 or early Quarter 4, CY 2012. Once connection of the FAPs is completed, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. | 2012-08-27 17:33 | 2012-08-27 17:33 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2012 | Q3 | Q3 - 2012 | 8094 | 6754 | FALSE | 41 | The Super FAP construction is completed, and the VIPFA/viNGN intends to begin the construction of additional FAPs during Quarter 4, CY 2012. Additional progress is expected during Quarter 4, CY 2012. At the end of the 3rd quarter, the VIPFA/viNGN team worked to finalize eight (8) construction service contracts for the construction of eight (8) additional FAPs, six on St. Thomas and two on St. Croix. During Quarter 4, CY 2012, VIPFA/viNGN will finalize any environmental, archeological studies and will award contracts for the execution of these FAPs. This will be an aggressive schedule to which most of VIPFA/viNGN project activities will be field bound. The RFPs for the aerial fiber pulling and splicing was issued during Quarter 3, CY 2012. As a result, VIPFA/viNGN and it contractors will begin aeiral fiber installation during Quarter 4, CY 2012. This implies VIPFA/viNGN will have an aggressive schedule of activities to include FAP construction, aerial fiber pulling, underground fiber | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 4, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 96 | No variance from Baseline Milestone target; VIPFA/viNGN team does plan to complete additional archaeological surveys for all FAPs that were relocated. | 100 | Future network will handle security monitoring and utilizing SNMP (Simple Network Management Protocol) enable devices and IP (Internet Protocol). cameras. There are no variances from Baseline Milestone target. | 95 | Additional progress is expected during Quarter 4, CY 2012, as additional Rights of Way are obtained for the locations of a few FAPs on private properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). | 96 | Due to the relocation of a few FAPs, new environmental, archaeological and building permits are required prior to construction. As a result of reapplying for building permits, the percentage was reduce. | 80 | In the first section of Quarter 4 CY 2012, VIPFA/viNGN project team will make a site visit to identify fiber optic trench crossings such as storm drains, sewer lines and any noticeable mechanically laid underground crossing. In addition, a site visit will be conducted with the trench contractor to identify existing underground obstructions and to establish the path of the trench work for the entire trench project. In preparation for FAP construction, site visits will be conducted with construction contractors to identify lay down areas, traffic patterns and any other safety concerns applicable to the particular project site. This will include participation with the current land owner in vetting any concerns that maybe of significance of the project completion. | 94 | During Quarter 4, CY 2012, the team plans to continue to over preform against the Baseline as it will begin to install traffic rated vaults during the trench work on both St. Thomas and St. Croix. Additionally, during Quarter 4, CY 2012, VIPFA/viNGN will procure a stocking equipment for the warehouse team. | 25 | Significant progress has been made with the construction of the two Super FAPs. The Super FAPs were completed during Quarter 3, CY 2012. Permanent power was installed in the Super FAPs. However, once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. No route changes are anticipated. | 11 | Significant progress has been made with the construction of the two Super FAPs. The Super FAPs were completed during Quarter 3, CY 2012. Permanent power was installed in the Super FAPs. However, once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line in the final quarter. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. | 40 | Construction of the two Super FAPs are complete. Once connection of the FAPs are completed, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. In Quarter 2, CY 2013, the final testing and staging for placement of the routers and switches will begin. | 2012-11-28 09:58 | 2012-11-28 09:58 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2012 | Q4 | Q4 - 2012 | 9052 | 7825 | FALSE | 40 | By the end of Quarter 4, CY 2012, VIPFA/viNGN constructed a total of three FAPs and intends to begin the construction of additional FAPs during Quarter 1, CY 2013. Additional progress is expected during Quarter 1, CY 2013. At the end of Quarter 4, CY 2012, the VIPFA/viNGN team worked to finalize construction service contracts for the construction of eight (8) additional FAPs, six on St. Thomas and two on St. Croix. During Quarter 1, CY 2013, VIPFA/viNGN expects to execute contracts for the construction of these FAPs. With the signing of these contracts, the team will be on aggressive schedule with most of its construction activities in process. The contractors for the aerial fiber pulling and splicing were selected during Quarter 4, CY 2012. As a result, VIPFA/viNGN and it contractors expect to begin aerial fiber installation during Quarter 1, CY 2013. With work initiated under these contracts, the team will be engaged in an aggressive schedule of activities to include aerial fibe | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 1, CY 2013 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 96 | There is no variance from the Baseline Milestone target. An addendum to the Phase 1 Archaeological Survey and an addendum to the Environmental Assessment were completed to address ten FAP relocations. During Quarter 1, CY 2013, VIPFA/viNGN will submit the official request to NTIA and NOAA to relocate the ten FAPs, based on the results of the addendum to the Archeological Survey and the Environmental Assessment, both of which identified no significant impact, and in some cases, lesser impact. No potentially significant archeological resources were identified during the Phase I Archaeological Survey for the Fiber Access Point locations on both islands either. Thus, from the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. The VIPFA/viNGN team continues to monitor its construction site during the build-out process for any endangered species that viNGN or its c | 100 | There are no variances from the Baseline Milestone target. | 95 | Additional progress is expected during Quarter 1, CY 2013, as additional Rights of Way are obtained for the locations of a few FAPs on semi-autonomous government agency properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, traffic-rated vault/manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). The VIPFA/viNGN team has an agreement with the U.S. Virgin Islands Department of Public Works for the trenching of four segments of highway, two on St. Thomas and St. Croix. During Quarter 4, CY 2012, VIPFA/viNGN began trenching on both islands, St. Croix and St. Thomas. VIPFA/viNGN will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team will also engaged with the State Historic Preservation office and current land owners to also insure that FAPs are c | 96 | VIPFA/viNGN will continue to work with the local Planning and Natural Resources Department to ensure that VIPFA/viNGN permits are updated and in compliance with the previous permits issued. The team will was also continue to engage with the State Historic Preservation office and current land owners to ensure that FAPs are constructed in the approved rights of way. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN is anticipating that all remaining building permits for FAP construction will be issued by the end of Quarter 1, CY 2013. | 81 | During the first half of Quarter 1, CY 2013, the VIPFA/viNGN project team will rcontinue to conduct site visits to formalize installation procedures for aerial fiber installation; to identify impediments, such as tree branches, sagging power lines, etc.; and to work to address these issues. In preparation for the remaining FAP construction, site visits will be conducted with construction contractors to identify lay down areas, traffic patterns and any other safety concerns applicable to the particular project site. This will include participation with the current land custodians in vetting any concerns that may be of significance to the completion of the project. Silt barriers, fencing, and land clearing measures will be implemented to ensure a smooth transition into the construction process for all future FAPs. VIPFA/viNGN and its contractors will continue to assess the roads on which trench work will be performed. Traffic patterns, road construction and other potential obstructio | 94 | VIPFA/viNGN and its contractors will continue to install underground fiber optic conduits on all four segments of the project. With the aim to reduce traffic interference, conduits will be installed without traffic vaults. Further, aerial installation will begin, and FAP construction and equipping will continue. Traffic-rated vaults are expected to be installed, beginning late Quarter 1, CY 2013/Quarter 2, CY 2013. | 25 | By the end of Quarter 4, CY 2012, VIPFA/viNGN completed a total of three FAPs. The construction of additional FAPs will begin during Quarter 1, CY 2013. Once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN expects to trench the remaining 39 miles with four trenching teams operating simultaneously, two on St. Thomas and two on St. Croix. VIPFA/viNGN also plans to begin the installation of the total 46.6 miles of aerial construction on St. Thomas and St. John and 36.6 miles on St. Croix. | 11 | Under performance against the Baseline Indicator is due to the fact that VIPFA\viNGN has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. At the Global Crossing/Level 3 facility in Miami, the ASR 9006 installation process is complete, with the ASR 9006 powered up and tested. | 40 | During Quarter 1, CY 2013, the aerial installation contractors will begin testing of the fiber optic reels at the warehouse locations prior to installation. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 4, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the construction of the Super FAPs by Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during late Quarter 1, CY 2013. Once connection of the FAPs is complete, the routers and switches will be installed and will await final activation to the fib | 2013-02-28 08:29 | 2013-02-28 08:29 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2013 | Q1 | Q1 - 2013 | 9996 | 8542 | FALSE | 58 | The remaining trenching will be completed during Quarter 2, CY 2013. By the end of the Quarter 4, CY 2012, VIPFA/viNGN completed the construction of a total of three FAPs. VIPFA/viNGN is 90% completed with a fourth FAP as of March 31, 2013 and expects to complete it during Quarter 4, CY 2013. Additional FAP construction will be the main priority during Quarter 2, CY 2013 and Quarter 3, CY 2013. The VIPFA/viNGN team will finalize construction service contracts for the construction of seven (7) additional FAPs on St. Thomas and will make awards for the construction of FAPs on St John. During Quarter 1, CY 2013, a Notice to Proceed was issued to the aerial fiber pulling and splicing contractor for work on St. Thomas, St. John and St. Croix. The contractor began aerial fiber installation during Quarter 1, CY 2013 and will continue installations on an aggressive schedule. Underground fiber installation will also continue on an aggressive schedule during Quarter 2, CY 2013. | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through July 31, 2013 document the management team's commitment to continue to accelerate the implementation of the program, in spite of the challenges outlined in 3 below. Significant progress is expected during Quarter 2, CY 2013. | 98 | An addendum to the Phase 1 Archaeological Survey was completed to address ten FAP relocations. No potentially significant cultural resources were identified during the Phase I Archaeological Survey for the Fiber Access Point locations on both islands. As a result of the archaeological review, VISHPO had no objection to the proposed construction activities. The VIPFA/viNGN team will continue to monitor its construction site during the build-out process for any endangered species that viNGN or its contractors might encounter, such as the Ameiva polops, Epicrates monensis granti, and Eretmochelys imbricata. To date, viNGN and its contractors have not encountered any of the above species and their habitat on any of the construction sites. | 100 | The routing protocol design has been finalized, and redundancy plans have been updated to best utilize new and existing network nodes. Once the FAPs (Fiber Access Points) are built and the network equipment is installed, the network is expected to be ready to "go live". The team has determined that security monitoring of the network will be managed utilizing SNMP (Simple Network Management Protocol)-enabled devices and IP (Internet Protocol) cameras. Awards to contractors to provide and install the required equipment is expected during late Quarter 2, CY 2013 or Quarter 3, CY 2013. | 98 | Additional Rights of Way were obtained for the locations of a few FAPs on semi-autonomous government agency properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). The VIPFA/viNGN team has an agreement with the U.S. Virgin Islands Department of Public Works (DPW) for the trenching of four segments of highway, two on St. Thomas and St. Croix. During Quarter 4, CY 2013, VIPFA/viNGN began trenching on St. Croix and on St. Thomas. VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013 and expects to trench the remaining 12.5 miles during Quarter 2, CY 2013. The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team will also continue to engage with the U.S. Virgin I | 96 | VIPFA/viNGN will continue to work with the local U.S. Virgin Islands Department of Planning and Natural Resources Department to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN is anticipating that all building permits for FAP construction will be issued by late Quarter 2, CY 2013. The team will also continue to engage with the U.S. Virgin Islands Historic Preservation Office and current land owners to ensure that FAPs are constructed in the approved rights of way. | 90 | In preparation for the aerial and innerduct contractor, the VIPFA/viNGN project team conducted site visits to identify the installation precedence for aerial fiber installation to monitor any impediments, such as tree branches, sagging power lines, etc. during Quarter 1, CY 2013. Site visits were also conducted with construction contractors to identify traffic patterns and any other safety concerns applicable to the particular project site. Future site preparation visits may include participation by the current land custodians to address any concerns that may impact the project completion schedule. During Quarter 2, CY 2013, silt barriers, fencing, and land clearing measures will be executed to ensure a smooth transition into the construction process for all the remaining FAPs. VIPFA/viNGN and its contractors will continue to assess the roads on which trench work will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions o | 94 | During Quarter 2, CY 2013, VIPFA/viNGN's contractors will continue to install aerial fiber and pull innerduct and Maxcell linings. Additionally, VIPFA/viNGN will procure any additional needed equipment for the network build out. The team also plans to install traffic rated vaults during the trench work on both St. Thomas and St. Croix. | 60 | By the end of Quarter 4, CY 2012, VIPFA/viNGN completed the construction of a total of three FAPs. VIPFA/viNGN is 90% completed with a fourth FAP as of March 31, 2013 and expects to complete it during Quarter 2, CY 2013. FAP construction on St. Croix is expected to continue, and the construction of seven (7) FAPs on St. Thomas is expected to begin during late Quarter 2, CY 2013. An award for the construction of FAPs on St. John is expected to be issued during Quarter 2, CY 2013. Once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. The AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013. VIPFA/viNGN anticipates 60 days to 90 days for activation; thus, the connection should be available during Quarter 2, CY 2013 or Quarter 3, CY 2013. VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013. VIPFA/viNGN expects to trench the remaining 12.5 m | 50 | Under performance against the Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the additional network segments that will enable additional equipment deployment. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone nodes equipment are installed, the team will be positioned to come in line with the Baseline Indicator targets. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. The AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013. VIPFA/viNGN anticipates 60 days to 90 days for activation; thus, the connection is expected to be available during Quarter 2, CY 2013 or Quarter 3, CY 2013. At the Level 3 facility in M | 45 | During Quarter 2, CY 2013, the aerial installation contractor will continue to test fiber optic reels at the warehouse location prior to installation. Also, network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 4, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the Super FAPs during Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during the latter part of Quarter 2, CY 2013. Once connection of the FAPs is completed, the routers and switches will be installed and will await final activation to the fibe | 2013-05-29 23:15 | 2013-05-29 23:15 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2013 | Q2 | Q2 - 2013 | 10670 | 8996 | FALSE | 59 | The VIPFA/viNGN team made tremendous progress with the construction of its middle mile network during Quarter 2, CY 2013, and the momentum is expected to continue through Quarter 3, CY 2013. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. The aerial backbone, underground backbone and lateral fiber installations will continue on St. Croix, St. Thomas, Water Island and St. John. In addition, the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power installation will continue on St. Croix and St. Thomas. Also, the construction of additional FAPs will begin on St. Thomas and St. John. Further, expenditures are expected to increase significantly, starting in Quarter 3, CY 2013, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and | 0 |  | N/A | 100 | During Quarter 2, CY 2013, an addendum to the Environmental Assessment and an update to the Phase I Archeological Survey were completed to address FAP relocations and aesthetic modifications to FAPs. The FAP relocations and modifications that were addressed in the assessments that were completed during Quarter 2, CY 2013 were deemed to be minor changes, as the new locations or orientations do not result in any significant adverse impacts on the natural environment nor the human environment and, although some do include changes in earth moving activities, all represent equivalent impact or in several cases even a reduction of impact. No potentially significant cultural resources were identified during the archaeological survey for the FAP relocations on St. Thomas or St. Croix. From the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. The team hopes to re | 100 | The core network design is complete. The routing protocol design will continue to be updated to best utilize new and existing network nodes. | 100 | All Rights of Way have been obtained. | 100 | During Quarter 2, CY 2013, VIPFA/viNGN prepared two (2) additional permit applications for FAPs to be constructed on St. John. The two permits are anticipated to be approved during early Quarter 3, CY 2013. The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that FAP construction meets local building codes. | 50 | The VIPFA/viNGN team will continues to conduct site visits to ensure that sites are ready for aerial fiber installation by identifying impediments, such as tree branches, sagging power lines, etc. The team will continue to coordinate with WAPA to address these impediments. Also, for all new and continuing FAP construction, site visits will be conducted, along with construction contractors and current land custodians (as needed), to identify and address traffic patterns, any other safety concerns, any environmental concerns, any concerns that may impact the project completion schedule, etc. For example, in areas where new FAP construction is expected to start, the site will be examined for any preexisting utilities lines, including water lines, sewer lines and electric lines. Further, silt barriers and silt fencing will be monitored on applicable sites to ensure that seepage from the construction zone does not occur. | 98 | The majority of the equipment that is needed for the network build-out has been procured. Any additional equipment procurement will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues and as network connection activities continue. VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities, including fiber, FAP racking equipment, DC power equipment and minor materials like plastic straps, belts, and screws, for example. | 60 | During Quarter 3, CY 2013, the VIPFA/viNGN team plans to install/deploy a cumulative total of 95.3 new fiber miles on St. Croix, St. Thomas, Water Island and St. John and connect 120 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 3, CY 2013: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power on St. Croix and St. Thomas; â€¢ Begin the construction of additional FAPs on St. Thomas, St. Croix and St. John; â€¢ As the FAPs are built, install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; and â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities. Further, the AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013, and the connection is e | 50 | Under performance against the Baseline Indicator is due to VIPFA/viNGN not completing the build-out of the network segments that will enable VIPFA/viNGN to provide new access to Internet Service Providers and other service providers. As FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Equipment will be deployed as FAPs are built and equipment racks are installed. During Quarter 2, CY 2013, VIPFA/viNGN installed a core distribution switch in the Level 3 facilities on St. Croix to provide bandwidth to customers, with the anticipation of providing service on the portion of the network that will be completed as of Quarter 3, CY 2013, as an alternate way for customers to access VIPFA/viNGN's network prior to the complete build-out of the network. Further, the AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 201 | 75 | Under performance against the Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the additional network segments that will enable additional network testing. As the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will begin to bring the network fully on line. Further, the last batch of fiber that was procured will be tested prior to installation, and additional fiber testing will occur prior to connections to the routers and switches being made. | 2013-08-20 19:17 | 2013-08-20 19:17 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2013 | Q3 | Q3 - 2013 | 11300 | 9449 | FALSE | 87 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 3, CY 2013, and the momentum is expected to continue through Quarter 4, CY 2013 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 3, CY 2013 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. The aerial backbone, underground backbone and lateral fiber installations will continue on St. Croix, St. Thomas, Water Island and St. John, as applicable. Also, the construction of FAPs (Fiber/Facility Access Points); the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power; CAI co | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 4, CY 2013, unless a determination is later made that additional work will be required to address any final issues with the right of way on the east end of St. Croix. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. The routing protocol design will continue to be updated to best utilize new and existing network nodes. | 100 | All Rights of Way will be obtained, unless a determination is later made that additional work will be required to address any final issues with the right of way on the east end of St. Croix. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | The VIPFA/viNGN team will continue FAP construction and backfilling activities. Site visits will be conducted along with construction contractors and current land custodians (as needed) to identify and address traffic patterns, any other safety concerns, any environmental concerns, any concerns that may impact the project completion schedule, etc. Further, silt barriers and silt fencing will be monitored on applicable sites to ensure that seepage from the construction zone does not occur. | 100 | VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities. Any additional equipment procurement will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues and as network connection activities continue. | 100 | During Quarter 4, CY 2013, the VIPFA/viNGN team plans to install/deploy a cumulative total of 26 new fiber miles on St. Croix, St. Thomas, Water Island and St. John and connect 315 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 4, CY 2013: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power on St. Croix, St. Thomas and St. John; â€¢ Install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; and â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and coordinate with the construction contractors, NTIA and NOAA to determine whether a | 100 | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, the Community Anchor Institutions are connected and all backbone node equipment is installed, equipment will be deployed, and the team will be positioned to come in line with the Baseline Indicator targets. | 100 | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, Community Anchor Institutions are connected and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will bring the network fully on line. | 2013-11-19 16:37 | 2013-11-19 16:37 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2013 | Q4 | Q4 - 2013 | 11920 | 10084 | FALSE | 88 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 4, CY 2013, and the momentum is expected to continue through Quarter 1, CY 2014 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 4, CY 2013 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. The construction of FAPs (Fiber/Facility Access Points); the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power; CAI connections; and, network testing and monitoring will continue. Also, the aerial backbone, underground backbone and lateral fiber installations will continue, | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 1, CY 2014, unless a determination is later made by the U.S. Virgin Islands State Historic Preservation Office (VISHPO) and/or NTIA that additional work will be required to address any final issues with the proposed underground installation on the east end of St. Croix and the proposed aerial installation on the east end of St. Thomas that were outlined in the above-referenced request for a project modification. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. During Quarter 4, CY 2013, the VIPFA/viNGN team requested approval of the following project modifications for St. Croix and St. Thomas: 1. On St. Croix, approximately 800 feet of aerial network needs to be changed from aerial to underground. This change is necessary because it was determined that the Virgin Islands Water and Power Authority (WAPA) does not have a right of way for aerial installation along this section of the network. Originally, the plan was to span this gap without the use of poles, but the landowner will not approve any aerial plan; and, 2. On St. Thomas, approximately 2,500 feet of underground network needs to be changed to aerial. This modification is temporary to allow for a recently-approved major road repair project by the U.S. Virgin Islands Department of Public Works along this section of the network and because the portion of the conduit that is contributed by WAPA is blocked and cannot be cleared in the near-ter | 100 | All Rights of Way that were needed have been obtained to date. A determination may be made later for additional work to address any issues with the right of way for the proposed underground installation on the east end of St. Croix. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | Site preparation will be complete, with the exception of those that may be related to any remaining CAI connections. | 100 | VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities. Any additional equipment procurements will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues, and as network connection activities continue. | 100 | During Quarter 1, CY 2014, the VIPFA/viNGN team plans to install/deploy a cumulative total of 8 new fiber miles across St. Croix, St. Thomas, St. John and Water Island and connect 314 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 1, CY 2014: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of equipment; Continue the installation of the remaining equipment in the already-constructed FAPS; â€¢ Continue the connections of CAIs and the testing of the connections; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; and â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs. | 100 | As the remaining FAP construction is completed, the remaining equipment is installed in the FAPs, the Community Anchor Institutions are connected, and all backbone node equipment is installed, equipment will be tested and deployed, and the team will be positioned to come in line with the Baseline Indicator target. | 100 | As the remaining FAP construction is completed, the remaining equipment is installed in the FAPs, Community Anchor Institutions are connected, and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator target. Network testing will be ongoing in alignment with network build out and equipment deployment. | 2014-02-28 11:50 | 2014-02-28 11:50 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2014 | Q1 | Q1 - 2014 | 12252 | 10425 | FALSE | 84 | The VIPFA/viNGN team will continue to make progress with the build out of its 100% fiber optic, wholesale, open access network during Quarter 2, CY 2014 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 2, CY 2014 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. During Quarter 4, CY 2013, the VIPFA/viNGN team projected that the "Planned Percent Complete" would be 88% as of the end of Quarter 1, CY 2014; however, after reevaluating the timing of contractor invoicing and the need to close out a number of contracts, the team has lowered the "Planned Percent Complete" expectations. However, the team expects to expend and Dr | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 2, CY 2014, unless a determination is later made by the U.S. Virgin Islands State Historic Preservation Office (VISHPO) and/or NTIA that additional work will be required to address any final issues. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. | 100 | All Rights of Way that are needed are expected to be obtained. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | Site preparation will be complete, with the exception of those that may be related to any remaining CAI connections. | 100 | VIPFA/viNGN will continue to receive materials and tools as a result of prior procurement activities. Any additional equipment procurements will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues, and as network connection activities continue. | 100 | During Quarter 2, CY 2014, the VIPFA/viNGN team plans to complete the network build out on St. Croix, St. Thomas, St. John and Water Island and connect the remaining CAIs to the network. | 100 | VIPFA/viNGN will continue to deploy procured equipment throughout the network build. | 100 | Network testing will continue and be ongoing in alignment with network build out and equipment deployment. All testing is projected to be completed by June 30, 2014. | 2014-05-30 13:22 | 2014-05-30 13:22 | 7316 | 7316 | Virgin Islands Public Finance Authority
NT10BIX5570096 | 2014 | Q2 | Q2 - 2014 | 12818 | 11198 | FALSE | 100 | The VIPFA/viNGN team will continue to make progress with the build out of its 100% fiber optic, wholesale, open access network during Quarter 3, CY 2014 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 2, CY 2014 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 3, CY 2014, unless a determination is later made by the U.S. Virgin Islands State Historic Preservation Office (VISHPO) and/or NTIA that additional work will be required to address any final issues. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. | 100 | All Rights of Way that are needed are expected to be obtained. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | Site preparation will be complete, with the exception of those that may be related to any remaining CAI connections. | 100 | VIPFA/viNGN will continue to receive materials and tools as a result of prior procurement activities. Any additional equipment procurements will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues, and as network connection activities continue. | 100 | During Quarter 3, CY 2014, the VIPFA/viNGN team plans to connect the remaining CAIs to the network on St. Croix, St. Thomas, St. John and Water Island. | 100 | VIPFA/viNGN will continue to deploy procured equipment throughout the network build. | 100 | Network testing will continue and be ongoing in alignment with network build out and equipment deployment. | 2015-05-08 15:43 | 2015-05-08 15:43 | 7324 | 7324 | Virgin Islands Public Finance Authority
NT10BIX5570097 | 2010 | Q4 | Q4 - 2010 | 990 | 2033 | FALSE | 3 | N/A | 0 |  | N/A | 70 | Final contracts will be awarded mid-quarter and the EA's will be started. Given timing and winter weather conditions, the EA's will not be totally completed until Q4. State regulations and the type of contracts will push expenditures into Q4. While they will not be completed a significant amount of information will be gathered for input into the Draft EA which will be submitted early Y1Q4. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-07 11:56 | 2011-02-07 11:56 | 6064 | 6064 | Department of Information Technology
NT10BIX5570097 | 2011 | Q1 | Q1 - 2011 | 1468 | 2447 | FALSE | 11 | N/A | 24 | Administer and oversee performance in all aspects of grant | Contracts negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. | 90 | While funds have been encumbered, some actual expenditures may be pushed into the next quarter due to the timing/completion of tasks required. Also, much of the State is experiencing extremely dry conditions with numerous fires already occurring. This could have an affect on completion due to an inability to access certain areas. | 10 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | The State will be signing the initial contracts for Design and Planning on the DMW sites during this quarter. This will be presented for approval to/by the State's Project Certification Committee in May. However, equipment cannot be purchased until a) the design has been approved for a particular site, and b) the State's Project Certification Committee approves the release of funds for the Project Implementation Phase. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-04-25 17:46 | 2011-04-25 17:46 | 6064 | 6064 | Department of Information Technology
NT10BIX5570097 | 2011 | Q2 | Q2 - 2011 | 3146 | 3333 | FALSE | 20 | no variance | 75 | Administer and oversee performance in all aspects of grant | Contracts will be negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. The $11.6M in-kind match will be allocated. | 100 | The Draft EA was submitted on 07/13 and comments received from NTIA 08/04. DoIT will be addressing the comments and will resubmit the final version during the quarter. Final expenditures for Environmental Assessments will cross into the next quarter due to the timing/completion of tasks required. | 10 | Network design will be started once the DMW contracts have been executed. | 0 | N/A | 20 | Permits and other approvals will be started during the design phase. | 0 | no variance | 10 | The State will process contract for design and planning on the DMW sites next quarter. Equipment cannot be purchased until a) the design has been approved for a particular site, and b) the State's Project Certification Committee approves the release of funds for the Project Implementation Phase. | 5 | no variance | 0 | no variance | 0 | no variance | 2011-08-17 11:36 | 2011-08-17 11:36 | 7092 | 7092 | Department of Information Technology
NT10BIX5570097 | 2011 | Q3 | Q3 - 2011 | 4366 | 4039 | FALSE | 20 | $1.5 million will be awarded in construction contracts. Additional purchase orders will be awarded in the amount of Ten Million dollars. | 75 | Admi nister and oversee performance in all aspects of grant | Contracts will be negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. | 100 | The Draft EA was submitted on 07/13 and comments received from NTIA 08/04. The final EA can not be completed until site design details are coordinated with USFS. Therefore, a Programmatic Agreement (PA) was drafted by NTIA in September 2011 which will allow a conditional FONSI to be issued which allows site design and construction to take place. The PA is being reviewed and signed by all interested parties. | 10 | Three construction contracts will be awarded in Q2-Y2. System design will commence. | 0 | N/A | 0 | Construction Contracts not awarded. Estimate no construction to be completed in Year 2 Quarter 2. | 0 | Construction Contracts not awarded. Estimate no site construction during Year 2 Quarter 2. | 10 | Purchase agreements for major hardware item (Radio Kit, Shelter, Tower and Battery Vendors) will be awarded in Q2-Y2. | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 2011-12-01 12:17 | 2011-12-01 12:17 | 7092 | 7092 | Department of Information Technology
NT10BIX5570097 | 2011 | Q4 | Q4 - 2011 | 4434 | 4083 | FALSE | 18 | 1. Overall hardware acquisition accelerated and hardware delivered 2. Civil construction accelerated at all site where winter weather is not a factor. Other sites will be addressed as weather permits; likely April 2012 and beyond | 55 | Admi nister and oversee performance in all aspects of grant | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | FONSI has been issued. | 54 | Radio Frequency (RF) design completed. Civil design (Professional Engineer Stamped Drawings) 50% to 60% completed. Network Integration and Test Plan drafted. System Transition Plan drafted. | 0 | N/A | 13 | Civil construction commencing at 6 to 10 sites | 13 | Civil construction commencing at 6 to 10 sites | 30 | 1. Procure 10 DMW RF Kits 2. Procure 12 DMW towers 3. Procure 12 DMW shelter 4. Procure 7 DMW battery/rectifier systems 5. Procure 20 DMW network routers | 13 | Civil construction commencing at 6 to 10 sites 1. Towers deployed at 2 sites 2. Shelters deployed at 2 sites 3. Battery/rectifiers deployed at 5 sites | 4 | 1. RF kits deployed at 2 to 5 sites 2. Network routersw deployed at 2 to 5 sites | 4 | Network testing at 2 sites. Limited network testing during factory acceptance testing (FAT) | 2012-01-24 19:50 | 2012-01-24 19:50 | 7092 | 7092 | Department of Information Technology
NT10BIX5570097 | 2012 | Q1 | Q1 - 2012 | 6200 | 5702 | FALSE | 54 | No funds will be expended on 700MHz LTE equipment until directed by NTIA/Firstnet. Middle Mile Percentage Completed is based on: Middle Mile $30,018,996 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $47,018,999 Expended $29,869,280 Percentage 63% 700MHz LTE Percentage Completed is based on: LTE $8,681,001 Cash Match $0.00 Total $8,681,001 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Middle Mile $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $29,869,280 Percentage 54% | 64 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | No Variance | 82 | 100% of the DMW design has been completed, no design for LTE can start until an equipment decision has been made/directed. | 0 | N\A | 95 | Expected delays in getting permits processed through other federal agencies. | 60 | Expected that 20 of the 29 sites will have begun construction. | 50 | All DMW equipment will have been procured and paid for except the Security Systems, which will have been ordered but will not be paid for until delivered and installed. Batteries will have been paid for, but installation will be contingent on construction schedules. We do not expect to expend any funds on LTE equipment this quarter. | 20 | Installation will be in conjunction with the RF installation. Equipment installation will not begin until mid-to-late May. | 50 | Equipment deployment is predicated on the construction and implementation schedules. While all equipment will be received and paid for, actual delivery and installation will be done on a just-in-time basis. | 50 | Limited network testing will be conducted during factory acceptance testing (FAT). Final testing is predicated on construction and implementation schedules over the next eight months. | 2012-05-18 15:39 | 2012-05-18 15:39 | 7310 | 7310 | Department of Information Technology
NT10BIX5570097 | 2012 | Q2 | Q2 - 2012 | 7022 | 6138 | FALSE | 63 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at over 20 sites: Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $35,019,000 Percentage 68% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $35,019,000 Percentage 63% | 72 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | EA's will be completed as needed for the nine out of scope sites that are expected to be approved. | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed, no design for LTE will commence until after approval of the budget amendment. | 0 | N/A | 100 | All permits and approvals will be completed | 90 | Construction should be started at all but one or two sites | 67 | Area New Budget Amount Spent % Spent Remaining % Remaining DMW 17,293,716.00 13,251,129.58 77% 4,042,586.42 23% LTE 2,443,000.00 0 0% 2,443,000.00 100% Overall 19,736,716.00 13,251,129.58 67% 6,485,586.42 33% In the Budget modification an additional $3.4 million has been reallocated from LTE to the DMW in the Equipment Market. Additional equipment will be procured for the proposed Out of Scope sites once the budget modification is approved. We do not expect to expend any funds on LTE equipment this quarter due to the suspension | 10 | Installation will be in conjunction with the RF installation. Equipment installation will not begin until September. | 70 | Equipment deployment is predicated on the construction and implementation schedules. While all equipment will be received and paid for, actual delivery and installation will be done on a just-in-time basis. The majority of the towers and shelter will be installed, deployment of radios and routers will begin in September. | 50 | Limited network testing will be conducted during factory acceptance testing (FAT). Final testing is predicated on construction and implementation schedules over the next eight months. | 2012-08-10 16:56 | 2012-08-10 16:56 | 7310 | 7310 | Department of Information Technology
NT10BIX5570097 | 2012 | Q3 | Q3 - 2012 | 7792 | 6597 | FALSE | 71 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at over 20 sites: Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $39,677,000 Percentage 76% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $39,677,000 Percentage 71% | 83 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | EA's will be completed as needed for the nine out of scope sites that are expected to be approved. | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed. No design for LTE will commence until after approval of the budget amendment. | 0 | N/A | 89 | Waiting on USFS internal process approval of Risk Assessment. ABQ NOAA is on hold pending final determination of use. | 89 | Site prep will be completed at 26 sites. | 74 | Area Budget Spent % Spent DMW $17,293,716 $14,647,500 85 LTE $ 2,443,000 $ 0 0 Overall $19,736,716 $14,647,500 74 Additional equipment will be procured for the proposed Out of Scope sites once the route modification is approved. We do not expect to expend any funds on LTE equipment this quarter due to the suspension. | 10 | Installation will be in conjunction with the RF installation. Equipment installation will continue through the quarter. | 80 | Towers and Shelters will be installed at all but two sites. Antennas, waveguides, and radio/router equipment will be installed at an estimated 40 sites. | 50 | Limited network testing will be done as part of the installation. Final network testing will be completed prior to putting a link into production. | 2012-11-07 16:29 | 2012-11-07 16:29 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2012 | Q4 | Q4 - 2012 | 8338 | 7010 | FALSE | 72 | Final equipment will be ordered, with most of it being accepted and paid for during the quarter. Construction will be completed at 27 of the 29 sites and the other 2 started (weather permitting). Continued installation of all radio/network equipment with additional links brought up for testing. Preparation for implementation. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $40,356,055 Percentage 78% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $40,356,055 | 88 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | No variance | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed. No design for LTE will commence until after the suspension is lifted. | 0 | N/A | 93 | Waiting on insurance to finalize new USFS leases. | 93 | Site prep will be completed at 27 sites | 79 | Area Budget Spent % Spent DMW $17,293,716 $15,624,487.28 90 LTE $ 2,443,000 $ 0 0 Overall $19,736,716 $15,624,487.28 79 Additional equipment will be procured for the proposed Out of Scope sites. We do not expect to expend any funds on LTE equipment this quarter due to the suspension. | 10 | Installation will be in conjunction with the RF installation. Equipment installation will continue through the quarter. | 80 | Towers and Shelters will be installed at all but two sites. Antennas, waveguides, and radio/router equipment will be installed at an estimated 54 sites. | 50 | Limited network testing will be done as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-01-29 12:23 | 2013-01-29 12:23 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2013 | Q1 | Q1 - 2013 | 9190 | 8023 | FALSE | 85 | The DMW portion will be almost complete. The LTE project will be in the early stages of negotiating MOA's/Leases and starting the Design Phase. | 96 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | No Variance | 100 | No Variance | 0 | NA | 100 | USFS leases should be finalized | 96 | Depending on date of lease/permits, site preparation may still be on-going | 100 | All additional equipment will be delivered and paid for. | 65 | Current plans call for 1184 network miles to be going through the "burn in" and testing | 90 | All batteries, waveguides, antennas, radios, and routers will be installed at all but two sites. | 70 | DoIT will still be conducting limited network testing as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-04-18 15:19 | 2013-04-18 15:19 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2013 | Q2 | Q2 - 2013 | 10456 | 8874 | FALSE | 81 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement will be signed, in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, Etc.) and starting developing the 700MHz RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $44,954,149 Percentage 87% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,544,900 Percentage 57% Admin funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Overall Percent | 100 |  | Assumes management, administrative, and legal effort is linear across 38 month grant period ending 09/30/2013. If the extension to 2015 is granted this number will be recalculated to cover the new time frame. | 100 | No variance | 100 | No variance | 0 | NA | 84 | All DMW permits & approvals should be finalized. Final count of permits/approvals for LTE will be for installation at 8 to 13 sites (16%) depending on final design. | 96 | Depending on date of lease/permits, site preparation may still be on-going | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $17,293,715.62 100 LTE $ 2,443,000.00 $ 0.00 0.0 Overall $19,736,715.62 $16,914,463.69 88 100% of the DMW equipment will have been purchased. The remaining 12% of the total is for LTE equipment. The LTE equipment will be purchased in a later quarter. | 90 | All but two DMW links should be up and operational. | 90 | All DMW equipment operational except at two sites being constructed. | 90 | DoIT will still be conducting limited network testing as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-07-31 11:48 | 2013-07-31 11:48 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2013 | Q3 | Q3 - 2013 | 11222 | 9401 | FALSE | 81 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement will be signed, in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, Etc.) and starting developing the 700MHz RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $43,973,387 Percentage 85% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,695,760 Percentage 62% Admin funds have been expended for gen | 70 |  | Assumes management, administrative, and legal effort is linear across the 60 month grant period. This has been recalculated due to the 24 month extension. | 100 | No variance | 100 | No variance | 0 | NA | 84 | Final count of permits/ approvals for LTE will be for installation at 8 to 13 sites (16%) depending on final design. | 93 | 2 of the DMW sites will not begin until Q2CY14. | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $17,293,715.62 100 LTE $ 2,443,000.00 $ 0.00 0.0 Overall $19,736,715.62 $16,914,463.69 88 100% of the DMW equipment will have been purchased. The remaining 12% of the total is for LTE equipment. This will be purchased in a later quarter after design has been completed. | 90 | All links (BTOP/non-BTOP) will be up with a large percentage operational. Only those the new links at Coyote and Eureka will not be completed. | 90 | All DMW equipment operational except at two sites to be constructed. | 90 | Limited network testing as part of installation will be nearly completed. Tinal testing will be completed on many of the links with the links going into a production status. | 2013-11-08 10:59 | 2013-11-08 10:59 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2013 | Q4 | Q4 - 2013 | 11876 | 10046 | FALSE | 83 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement was signed. Still in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, etc. ) and starting developing the 700 LTE RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $44,037,509 Percentage 89.9% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $0 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,423,389 Percentage | 70 |  | Assumes management, administrative, and legal effort is linear across the 60 month grant period. This has been recalculated due to the 24 month extension. | 100 | No variance | 100 | No variance | 0 | NA | 88 | Pending the outcome of the February 24, 2014 CBP meeting, the number of permits and other approvals will be determined. | 93 | 2 of the DMW sites will not begin until Q2CY14. | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715 $16,790,659 97.1 LTE $ 2,443,000 $ 0 0.0 Overall $19,736,715 $16,790,659 85.1 97% of the DMW equipment will have been purchased. The remaining 3% will be purchased the following quarter. The remaining 12% of the total equipment budget is for LTE equipment. This will be purchased in a later quarter after design has been completed. | 64 | All links (BTOP/non-BTOP) will be up with a large percentage operational. Only those the new links at Coyote and Eureka will not be completed due to winter weather and contract issues. | 90 | All DMW equipment operational except at two sites to be constructed. Delay incurred due to winter weather and contract issues. | 90 | Limited network testing as part of installation will be nearly completed. Final testing will be completed on many of the links with the links going into a production status. | 2014-02-24 13:05 | 2014-02-24 13:05 | 7599 | 7599 | Department of Information Technology
NT10BIX5570097 | 2014 | Q1 | Q1 - 2014 | 12246 | 10420 | FALSE | 84 | The second quarter of CY2014 is the spring season; which will allow construction at the two remaining sites. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $44,792,188 Percentage 91.44% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $0 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,953,091 Percentage 72.10% Admin funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Over | 70 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No variance | 100 | No variance | 0 | N/A | 88 | The number of permits and other approvals will be determined pursuant the amount required for LTE. | 93 | Site preparation for the remaining two DMW sites will begin. | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715 $17,401,548 100.62% LTE $ 2,443,000 $0 0.00% Overall $19,736,715 $17,401,548 88.17% The DMW equipment will exceed the original budget by 0.62%; which is less than an one percent increase. The remaining 11.83% of the total equipment budget is for LTE equipment. This will be purchased in a later quarter after design has been completed. | 64 | All links (BTOP/non-BTOP) will be up with a large percentage operational. The new links at Coyote and Eureka will be worked on this quarter. | 90 | All DMW equipment is operational except at two sites. Construction for the two sites will commence this quarter. | 90 | Final testing will be completed on many of the links with the links going into a production status. | 2014-05-29 16:38 | 2014-05-29 16:38 | 7600 | 7600 | Department of Information Technology
NT10BIX5570097 | 2014 | Q2 | Q2 - 2014 | 12418 | 10606 | FALSE | 87 | The CY2014 QTR3 is the fall season; which will allow completion of construction at the two remaining sites. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $45,359,437 Percentage 92.60% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $175,000 Percentage 4.37% Administration & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,503,104 Percentage 92.40% Administration funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotia | 93 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No variance. | 100 | No variance. | 0 | N/A | 93 | The number of permits and other approvals will be determined pursuant the amount required for LTE. | 93 | Site preparation for the remaining two DMW sites have been completed. LTE site preparation is pending. | 88 | Area Budget Amount mount Spent Percent Spent DMW $17,293,715 $17,547,223 101.47% LTE $ 2,443,000 $0 0.00% Overall $19,736,715 $17,547,223 88.91% The DMW equipment will exceed the original budget by 1.47%; which is an increase of less than two percent. The remaining 11.09% of the total equipment budget is for LTE equipment. This will be purchased in a later QTR after the design has been completed. | 90 | The team will continue transitioning service to the new DMW network. | 93 | All DMW equipment is operational except at two sites. | 93 | Final testing will be completed on many of the links with the links going into a production status. | 2014-08-14 15:52 | 2014-08-14 15:52 | 7600 | 7600 | Department of Information Technology
NT10BIX5570097 | 2014 | Q3 | Q3 - 2014 | 12592 | 10865 | FALSE | 88 | The CY2014 QTR4 is the beginning of the winter season; which will allow completion of construction at the two remaining sites weather permitting. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $46,489,576 Percentage 94.91% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $128,500 Percentage 3.21% Administration & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,145,662 Percentage 79.20% Administration funds have been expended for general project support to include legal support fo | 93 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No variance | 100 | No variance | 0 | N/A | 93 | The number of permits and other approvals will be determined pursuant the amount required for LTE. | 93 | LTE site preparation is pending. | 88 | Area Budget Amount Amount Spent Percent Spent DMW $17,293,715 $17,427,088 100.77 LTE $ 2,443,000 $0 0.00% Overall $19,736,715 $17,427,088 88.30% The DMW equipment will exceed the original budget by 0.77%; which is an increase of less than one percent. The remaining 11.70% of the total equipment budget is for LTE equipment. This will be purchased in a later QTR after the design has been completed. | 93 | The team will continue transitioning service to the new DMW network. | 94 | All DMW equipment is operational except at two sites. | 93 | Final testing will be completed on many of the links with the links going into a production status. | 2014-11-13 11:36 | 2014-11-13 11:36 | 7600 | 7600 | Department of Information Technology
NT10BIX5570097 | 2014 | Q4 | Q4 - 2014 | 12712 | 11037 | FALSE | 89 | The CY2015 QTR1 is the middle of the winter season; updates will be dependent upon prevailing weather conditions. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $46,883,704 Percentage 95.71% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $390,406 Percentage 9.74% Administration & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,289, 952 Percentage 84.53% Administration funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreeme | 93 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No variance | 100 | No variance | 0 | N/A | 93 | There are no planned construction permits for LTE since the state will be utilizing existing infrastructure, however approvals for non-state owned sites are pending agreement of the appropriate LTE site owners. | 93 | LTE site preparation is pending. | 89 | Area Budget Amount Amount Spent Percent Spent DMW $17,293,715 $17,717,539 102.45% LTE $ 2,443,000 $0 0.00% Overall $19,736,715 $17,717,539 89.77% The DMW equipment will exceed the original budget by 2.45%; which is an increase of less than three percent. The remaining 10.23% of the total equipment budget is for LTE equipment. This will be purchased in a later QTR after the vendor(s) has been selected. | 96 | The team will continue transitioning service to the new DMW network. | 99 | All DMW equipment is operational with the exception of the microwave link from Eureka to La Mosca. | 99 | Final testing is completed with the exception of the microwave link from Eureka to La Mosca. | 2015-02-20 17:53 | 2015-02-20 17:53 | 7600 | 7600 | Department of Information Technology
NT10BIX5570097 | 2015 | Q1 | Q1 - 2015 | 12846 | 11217 | FALSE | 93 | The CY2015 QTR2 is the middle of the spring season; updates will be dependent upon prevailing weather conditions. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $48,931,442 Percentage 99.89% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $390,406 Percentage 9.74% Administration & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,534,112 Percentage 93.54% Administration funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $51,855,960 Percentage 93.10% | 94 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No variance | 100 | No variance | 0 | N/A | 93 | There are no planned construction permits for LTE since the state will be utilizing existing infrastructure, however approvals for non-state owned sites are pending agreement of the appropriate LTE site owners. | 93 | LTE site preparation is pending. | 93 | Area Budget Amount Amount Spent Percent Spent DMW $17,293,715 $18,023,737 104.22% LTE $ 2,443,000 $240,000 9.82% Overall $19,736,715 $18,263,737 92.54% The DMW equipment will exceed the original budget by 4.22%; which is an increase of less than ten percent. The majority of the remaining 7.46% of the total equipment budget is for LTE equipment. | 96 | The team will continue transitioning service to the new DMW network. | 93 | All DMW equipment is operational with the exception of the microwave link from Eureka to La Mosca. | 99 | Final testing is completed with the exception of the microwave link from Eureka to La Mosca. | 2015-05-26 15:50 | 2015-05-26 15:50 | 8068 | 8068 | Department of Information Technology
NT10BIX5570097 | 2015 | Q2 | Q2 - 2015 | 12904 | 11284 | FALSE | 100 | During CY2015 QTR3 we anticipate completion of middle mile and LTE tasks. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $49,121,898 Percentage 100.28% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $3,806,115 Percentage 95.00% Administration & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,771,987 Percentage 102.33% Administration funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Overall Percentage Compl | 100 |  | With the extension of the grant award the expenses for administrative, financial and legal efforts are also extended; therefore the percent complete to the overall grant time line has been adjusted accordingly. | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | There are no planned construction permits for LTE since the state will be utilizing existing infrastructure, however approvals for non-state owned sites are pending agreement of the appropriate LTE site owners. | 100 | LTE site preparation will be complete. | 100 | Area Budget Amount Amount Spent Percent Spent DMW $17,293,716 $17,732,031 102.53% LTE $ 2,443,000 $2,624,191 107.42% Overall $19,736,716 $20,356,222 103.14% The DMW equipment will exceed the original budget by 2.53%; which is an increase of less than ten percent. The LTE equipment will exceed the original budget by 7.42%; which is also an increase of less than ten percent. | 100 | The team will have transitioned service to the new DMW network. | 100 | All DMW and LTE equipment will be operational. | 100 | Final testing will be completed. | 42255.6823 | 42255.6823 | 8068 | 8068 | Department of Information Technology
NT10BIX5570098 | 2010 | Q4 | Q4 - 2010 | 1206 | 2237 | FALSE | 5 | N/A | 0 | N/A | N/A | 95 | N/A | 21 | N/A | 26 | N/A | 40 | N/A | 0 | N/A | 5 | N/A | 0 | N/A | 5 | N/A | 0 | N/A | 2011-02-17 13:25 | 2011-02-17 13:25 | 6104 | 6104 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2011 | Q1 | Q1 - 2011 | 2084 | 2787 | FALSE | 8 | While there will be an acceleration of spending, overall project will under run next quarter largely due to withholding activities (such as permits and initial materials orders) that are dependent on the issuance of a FONSI. This is expected in early October. | 0 |  | NA | 95 | Revisions to the environmental assessment will extend into June, with agency and public commentary beginning in late June. In addition a new Programmatic agreement will be circulating in May, which will define cultural study parameters to complete field studies. | 37 | No Variance | 25 | We expect the rights-of-way to under run budget due to timeframes for negotiations and documentation with larger federal and state agencies. | 40 | Construction permits from key state and federal agencies will likely follow the issuance of the FONSI in October. Permits that can be issued prior to that are being paid. | 0 | There will be no site preparation until after FONSI is issued in October. | 5 | The baseline plan called for the initial acquisition of Node buildings in Quarter 3. This has been deferred until Quarter 4 since the FONSI date is scheduled in October. There is no need to acquire structures at this time only to store them. Project plan calls for the development of significant RFPs in the next Quarter. | 0 | No Variance | 8 | No Variance | 0 | No Variance | 2011-05-17 11:27 | 2011-05-17 11:27 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2011 | Q2 | Q2 - 2011 | 2992 | 3253 | FALSE | 12 | Although we expect an acceleration of spending in the next quarter, overall project spending will underrun due to delay of EA until October and materials acquisitions in September - October. | 0 |  | NA | 100 | No Variance | 50 | 3% underun. Working drawings for backbone designs 80% complete. 25% distribution area deisigns complete | 89 | No Variance | 60 | 40% underrun. Construction permits will not be available in 3QTR11, since DOT permits will not be issued until after FONSI and Mitigated Negative Declaration is issued. We anticipate Permits in all federal lands. | 6 | 60% underrun, as site preparation will no be allowed prior to FONSI. Aquisition of all sites will be finalized. RFPs will be issued and we will be ready to construct for October once FONSI in place. | 12 | 10% under-run. Due to the anticipated October issuance of FONSI, Electronics RFP process has been deferred until August Timeframe. Equipment purchase is expected 4QTR2011. | 0 | 25% underrun. Construction not started until permits are made available | 8 | 14% underrun. No equipment has been deployed due to delay in FONSI and Construction | 0 | No Variance | 2011-08-09 18:10 | 2011-08-09 18:10 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2011 | Q3 | Q3 - 2011 | 3966 | 3821 | FALSE | 15 | 33% Variance. Delays in receiving environmental permits which has delayed Finding of No Significant Impact and delayed the construction start date. All other gaps in planned progress emanate from this. | 0 |  | NA | 99 | 1% Variance. Request for Proposal issued and awarded for Monitoring Contractor. Monitoring plan initiated. Programmatic Agreement work continues into next Quarter. | 70 | Ahead 7%. Backbone and cable 95% complete. Distribution Engineering 20% complete. Anchor-Points of Interconnection entrance facilities and laterals 10% complete. All Node site engineering complete. | 95 | 5% Variance. Private Right of Way issues, Bureau of Indian Affairs and Tribal issues to be resolved. | 75 | 25% Variance. Backbone in pipeline, pending 30 day review cycle. Some county and city permits remain. | 25 | 75% Variance. Architectural renderings and site engineering complete and site prep Request for Proposal issued. | 12 | 42% Variance. Node Request for Proposal issued. Receiving deliveries of cable, conduit and vaults in northern construction zone. Additional tools, equipment and motor vehicles acquired. | 10 | 34% Variance. Anticipate receiving Finding of No Significant Impact . Material deliveries begun. All depots sites identified. Gardnerville depot fully operational. | 12 | 33% Variance. Receiving deliveries of cable, conduit and vaults in northern construction zone. Additional tools, equipment and motor vehicles acquired. | 0 | 6% Variance. Construction Not Started | 2011-11-10 15:34 | 2011-11-10 15:34 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2011 | Q4 | Q4 - 2011 | 5128 | 4794 | FALSE | 27 | Underrun of baseline by 31% -- while all pre-construction activities for the project are essentially complete, challenges initiating construction account for the underrun, due to delays in FONSI and related permits. | 0 |  | NA | 95 | Under-run by 5% -- While biological issues will resolve and the FONSI be issued, reissuing of the Programmatic Agreement for signature and the review of an additional 110 cultural sites will extend the site reviews into the May timeframe. | 85 | Exceed baseline by 11% -- Working drawings of backbone complete in all sections, 70% of distribution plant finalized, completion of Anchor site surveys | 95 | Under-run of baseline by 5% -- Rights of Way in a 6.4 mile section of Hwy 58 and select tribal lands will require additional time for resolution. Initiatives on the private sections are underway and BIA processes have begun with tribal councils and allotments. | 80 | Underrun of baseline by 20% - Mitigation plans and construction permits will not be issued until just prior to construction in each section of the route. On the whole, major permits will have been obtained from water quality and wildlife monitoring agencies. | 50 | Underrun of baseline by 50% - physical site preparation has been restrained until FONSI issued. Architectural plans and construction awards will complete. Node permits on 9 sites will be issued and 4 special permits will follow in April. Physical site construction will begin mid-March on several sites and accelerating toward 2Qtr12 finish. | 80 | Exceeds baseline by 16% -- all major material procurements for nodes, Outside Plant (cable, conduit, vaults, and apparatus), electronics will complete. | 14 | Underrun of baseline by 38% - due to delays in the issue of FONSI and PA, the project will initiate ground-breaking in several of the 20 segments in Nevada and California devoid of cultural sites | 35 | Underrun of baseline by 21% -- deliveries of materials, (175 miles of cable and 240 trench miles of conduit, nodes and electronics) will not complete until the following quarter. | 0 | Underrun of baseline by 15% -- due to permit delays and placement of cable. | 2012-02-17 18:59 | 2012-02-17 18:59 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2012 | Q1 | Q1 - 2012 | 6334 | 5769 | FALSE | 49 | 26% Variance - delays in Federal and State permits. | 0 |  | NA | 97 | Under-run by 3% - Mitigation Monitoring & Reporting Plan, Finding of No Significant Impact and initial Programmatic Agreement Segment Reports will have been issued. Half of the Programmatic Agreement Segment Reports will have been reviewed and approved according to the NTIA schedule. | 90 | Exceed baseline by 5%, all back bone work drawings to be complete, distribution work drawings will be 90% complete, network electronic architecture design will be 85% complete, all anchor surveys will be completed, and 35% of anchor contracts will be secured. | 100 | No variance - All Right of Ways secured. | 100 | No variance - all permits secured | 70 | 30% variance - all but (5) node sites will have been completed. The remaining (5) are scheduled for completion in July 2012 | 90 | Ahead by 12% - Project equipment secured with exception of NOC equipment and billing systems. | 20 | 55% Variance - Conduit placement underway in all (5) contractor bid zones, most all Node will enclosures installed, some cable placement commencing. | 35 | 39% Variance - Delay in project start will not permit placement of transmission electronics until 7/2012. | 0 | 25% variance - Delayed project start has pushed splicing into end of 3rd and 4th quarter respectively. | 2012-05-29 16:09 | 2012-05-29 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2012 | Q2 | Q2 - 2012 | 6848 | 6050 | FALSE | 48 | 42% Variance - delays due to Programmatic Agreement delayed construction start. | 0 | true | NA | 98 | 2% Variance - The last three groups of Programmatic Agreement Segment Reports remain to be reviewed. | 100 | Exceed baseline by 3% - All distribution engineering will be complete, network electronic architecture will be complete, and most anchor contracts will be secured. Remaining engineering relates to anchor connections and "as-built" validations. | 100 | No Variance - Rights of Way secured. | 85 | 15% Variance - Issuance of Notice to Proceed by the agencies will be based upon the release of the Programmatic Agreement Segment Groups. | 75 | 25% Variance - Half of the Node sites remain until approval of Programmatic Agreement Segment Groups. | 100 | Exceed baseline by 8% - All equipment to be secured. | 30 | 63% Variance - Conduit placement underway in all (5) contractor bid zones, half of the nodes built and cable placement continuing. | 50 | 50% Variance - All transmission electronics dependent on node construction, which are dependant on PA approval. | 0 | 41% Variance - No complete sections of the network available until 4th quarter. | 2012-08-03 12:00 | 2012-08-03 12:00 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2012 | Q3 | Q3 - 2012 | 8124 | 6769 | FALSE | 63 | (32% Variance)Delays due to the Programmatic Agreement | 0 |  | NA | 98 | (2% Variance) Programmatic Agreement Segment Groups 9 and 10 will not be approved until the first quarter of 2013. | 95 | No Variance | 100 | No Variance | 95 | (5% Variance)Programmatic Agreement Segment Groups 9 and 10 and associated Encroachment Permits will not be approved until the first quarter of 2013. Bureau of Indian Affairs will rule on Nevada Allotments. | 80 | (20% Variance) All node sites will be prepared, except for three nodes in areas not approved under Programmatic Agreement. | 97 | No Variance | 30 | (67% Variance) 40% of the backbone construction will be completed, 5% of anchors connected, and 5% of distribution conduit and cable will be deployed. | 60 | (38% Variance) Electronic equipment will be deployed and tested to seven of 11 nodes, including end-nodes (Reno and Barstow) | 30 | (40% Variance) Testing for 2 node spans will be completed in Mono County. | 2012-11-28 16:09 | 2012-11-28 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2012 | Q4 | Q4 - 2012 | 9026 | 7796 | FALSE | 72 | 25% Variance - Due to delayed permits and winter conditions. We will continue to close gap | 0 |  | NA | 100 | No Variance | 99 | No Variance | 100 | No Variance | 100 | No Variance | 85 | 15% under run of target, due to final construction of the Olancha and Independence Nodes sites | 98 | Ahead 1% - Due to acquisition of distribution cable in Q4 2012 | 60 | 40% Variance - All but three nodes will be completed. 75% of backbone to be completed, Ridgecrest distribution to be completed, and connection of 25 anchors and points of interconnection will be complete. | 75 | 24% Variance - Due to electronics not deployed in four nodes | 60 | 25% Variance - Due to inability to end to end test backbone and select potions of the distribution system cable. | 2013-02-27 15:37 | 2013-02-27 15:37 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2013 | Q1 | Q1 - 2013 | 9938 | 8512 | FALSE | 83 | The variance of 17% is due to delays in permits and winter weather impacts in areas where permitting was allowed, largely Mono County. | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 75 | Variance of 25% under run due to final construction of anchors, Points of interconnection, and potential areas where Route Changes are still being approved. | 100 | No Variance | 85 | Variance to of 15% to 100% target due to having sub-system testing completed only. End-to-end network, Operational Support Systems integration testilng and testing of uncompleted anchor connections will continue into the following quarter. | 2013-05-28 15:08 | 2013-05-28 15:08 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2013 | Q2 | Q2 - 2013 | 10536 | 8922 | FALSE | 96 | 4% Variance - Due to late construction start due to Programmatic Agreement requirements and execution, delays in permit issuance and route changes. The latter consist of anchor routes and five changes required on the backbone. | 0 |  | NA | 99 | 1% Variance - Due to environmental studies for anchor route changes and the Inyo National Forest Service. Agency(s) review of planned supplemental surveys in progress. Environmental studies completed for (18) anchor route changes in addition to test pits and supplemental field survey analysis being performed on the last backbone segment required by the Inyo National Forest Service. | 99 | 1% Variance - Due to the special studies needed for the Inyo National Forest Service and anchor route changes. | 100 | All Rights of Way completed | 99 | 1% Variance - Due to pending approval of anchor route changes by the NTIA and approval of supplemental environmental plan for Segment M112 by the Inyo National Forest Service. | 100 | All Site Preparation completed | 100 | No Variance - All equipment procured | 95 | 5% Variance - Due to pending approval of anchor route changes by the NTIA and approval of supplemental environmental plan for Segment M112 by the Inyo National Forest Service. | 100 | No variance - all equipment deployed | 70 | 30% Variance - Due to incomplete end-to-end fiber spans held up by multiple NDOT parallel drainage variance approvals, multiple ESA long bores and delayed P.A. segment approval for M122. | 2013-08-09 11:43 | 2013-08-09 11:43 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2013 | Q3 | Q3 - 2013 | 11326 | 9463 | FALSE | 100 | No Variance | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-11-21 13:02 | 2013-11-21 13:02 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2013 | Q4 | Q4 - 2013 | 11874 | 10045 | FALSE | 100 | We will expend 107% of our overall budget. | 0 | true | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-02-24 12:23 | 2014-02-24 12:23 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2014 | Q1 | Q1 - 2014 | 12204 | 10380 | FALSE | 100 | No Variance | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-05-16 13:45 | 2014-05-16 13:45 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2014 | Q2 | Q2 - 2014 | 12394 | 10588 | FALSE | 100 | Anticipated expenditures include but are not limited to, final software development, mitigation costs required by Department of Fish and Wildlife, finalizing NDOT requirements, insurance premium audits, independent grant audit, and overall closeout costs. | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-08-11 11:30 | 2014-08-11 11:30 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570098 | 2014 | Q3 | Q3 - 2014 | 12610 | 10879 | FALSE | 100 | We have expended 108% of our overall budget as a result of excessive environmental and permitting costs. The overrun to the original budget was augmented with a $9.9MM award by Resolution T-17408, by the California Public Utilities Commission and administered by the California Advanced Services Fund. The additional funds were intended to recover part of the excess costs incurred by state and federal environmental permits and requirements. The funding was allocated by specific distribution components of the project, such as the June Lake, the Benton Paiute and Bridgeport Tribal connections, and the tie-in of the US Marine Corps Mountain Warfare Training Center, as well as outstanding environmental fees. Of the $9.9MM awarded by Resolution T-17408, $7,841,772.03 was used to augment the project. | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-11-24 11:30 | 2014-11-24 11:30 | 6103 | 6103 | California Broadband Cooperative, Inc.
NT10BIX5570099 | 2010 | Q4 | Q4 - 2010 | 1328 | 2350 | FALSE | 1 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall in the 1st quarter of 2011 is expected to cause delay. | 0 |  | N/A | 100 | N/A | 5 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | N/A | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | N/A | 0 | N/A | 2011-02-23 11:36 | 2011-02-23 11:36 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2011 | Q1 | Q1 - 2011 | 1966 | 2728 | FALSE | 6 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 20% completion of the overall project. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant project progress by the end of Quarter 2, 2011. | 0 |  | N/A | 100 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the environmental assessment, therefore this projection is on target with the baseline plan submitted. | 60 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the Network Design. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant network design progress by the end of Quarter 2, 2011. | 50 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Rights of Way. However, as stated previously there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant rights of way progress by the end of Quarter 2, 2011. | 50 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Construction Permits and Other Approvals. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Q1 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant construction permits and other approval progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the Site Preparation. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Q1 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to be back on schedule soon after the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 5% completion of the Equipment Procurement. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to be back on schedule soon after the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 25% completion of the Network Build. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. anticipates the network build to be pushed back two quarters later than initially projected. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the equipment deployment, therefore this projection is on target with the baseline plan submitted. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of network testing, therefore this projection is on target with the baseline plan submitted. | 2011-05-12 12:04 | 2011-05-12 12:04 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2011 | Q2 | Q2 - 2011 | 2980 | 3247 | FALSE | 20 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 40% completion of the overall project. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant overall project progress by the end of Quarter 3 of 2011. | 0 |  | N/A | 100 | Completed. | 95 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the Network Design, therefore this category is expected to be on schedule. | 100 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Rights of Way, therefore this category is expected to be on schedule. | 100 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Construction Permits and Other Approvals, therefore this category is expected to be on schedule. | 75 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Site Preparation. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant site preparation progress in Quarter 3 of 2011. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 90% completion of the Equipment Procurement. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to be back on schedule soon after the outside plant construction contract is awarded. | 25 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the Network Build. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant progress with network build, however it is anticipated to remain pushed back two quarters later than initially projected. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the equipment deployment, therefore this projection is on target with the baseline plan submitted. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 25% completion of network testing. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant progress with network build, however it is anticipated to remain pushed back two quarters later than initially projected as there is an expected fiber shipment delay. | 2011-08-09 14:53 | 2011-08-09 16:50 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2011 | Q3 | Q3 - 2011 | 3908 | 3792 | FALSE | 5 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 |  | N/A | 100 | Completed. | 80 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 90 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 90 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 2011-11-07 14:15 | 2011-11-07 14:15 | 5994 | 5994 | Bloomingdale Communications Inc
NT10BIX5570099 | 2011 | Q4 | Q4 - 2011 | 4988 | 4662 | FALSE | 10 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 |  | N/A | 100 | Completed. | 80 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 95 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 95 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 15 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 2012-02-14 07:58 | 2012-02-14 07:58 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2012 | Q1 | Q1 - 2012 | 6198 | 5701 | FALSE | 35 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 0 |  | N/A | 100 | Completed. | 98 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 98 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the rights of way. Bloomingdale Communications, Inc. anticipates this goal to be met next quarter. | 100 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the construction permits and other approvals. Bloomingdale Communications, Inc. anticipates this goal to be met next quarter. | 50 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the site preparation. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment procurement. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. The equipment Request for Proposal is scheduled to go out by the end of May in next quarter, once the Request for Proposal is released the responses will be reviewed, vendor selected, and then the equipment will be evaluated for the project. This will begin to move forward since construction began this quarter. | 43 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network build. As stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended and will be on target within the 3 year project completion timeline. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment deployment. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. As mentioned previously, the equipment Request for Proposal is anticipated to be released by the end of May 2012, next quarter, therefore there is no equipment deployment anticipated by the end of next quarter as once the Request for Proposal is released the responses will be reviewed, vendor selected, and then the equipment will be evaluated for the project. The project is moving forward rapildly and will be completed within the 3 year project timeline. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network testing. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 2012-05-18 14:13 | 2012-05-18 14:13 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2012 | Q2 | Q2 - 2012 | 6974 | 6114 | FALSE | 69 | The BCI project was initially projected to be completed before Year 3 Quarter 1 which is next quarter (Quarter 3 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed. | 98 | The network design portion of the project is complete until network testing is completed. | 100 | All rights of ways for easements should be completed by the end of next quarter. | 100 | Completed. | 90 | The majority of the site preparation should be complete by the end of next quarter as the huts will be delivered and installed. | 83 | The majority of the equipment procurement should be completed by the end of next quarter as the vendor will be selected and equipment ordered. | 66 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, this project will be completed within the three year timeline of the award period. | 0 | The equipment will not be deployed next quarter, but should be soon after in the following quarter. | 0 | Network testing cannot take place until after the network is constructed and equipment is deployed. The network will be finished prior to the three year award period end. | 2012-08-09 15:03 | 2012-08-09 15:03 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2012 | Q3 | Q3 - 2012 | 8132 | 6773 | FALSE | 88 | The BCI project was initially projected to be completed before Year 3 Quarter 1 which was this quarter (Quarter 3 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 98 | The network design portion of the project is complete until network testing is completed. | 100 | All rights of ways for easements should be completed by the end of next quarter. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | The site preparation should be complete by the end of next quarter. | 83 | The majority of the equipment procurement should be completed by the end of next quarter as the vendor has been selected and some equipment has been ordered. The remaining equipment should be ordered and received this quarter. | 90 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly and the project will be completed within the three year timeline of the award period. | 60 | The equipment will be delivered next quarter and therefore the physical installation will begin. | 75 | Network testing should begin next quarter as fiber and splicing are finalizing and equipment will begin installation. If the weather continues to cooperate, the network testing should move right along next quarter. The network will be finished prior to the three year award period end. | 2012-11-29 10:09 | 2012-11-29 10:09 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2012 | Q4 | Q4 - 2012 | 8996 | 7775 | FALSE | 96 | The BCI project was initially projected to be completed before Year 3 Quarter 2 which was this quarter (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | The network design portion of the project is complete until network testing is completed. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 95 | The majority of the equipment procurement should be completed by the end of next quarter as the majority of the equipment has been received. Installation of the transport equipment will be taking place next quarter. | 95 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly as expected and the project will be completed within the three year timeline of the award period. Much progress is expect on all components of the network next quarter. | 95 | Significant progress of the equipment deployment will be made next quarter as the transport equipment will be installed. The DC power and AC upgrade may not be complete until the following quarter. | 98 | Network Testing should be almost complete by the end of next quarter. The network will be finished prior to the three year award period end. | 2013-02-27 08:29 | 2013-02-27 08:29 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2013 | Q1 | Q1 - 2013 | 9812 | 8441 | FALSE | 99 | The BCI project was initially projected to be completed before Year 3 Quarter 2 (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | The network design portion of the project is complete until network testing is completed. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 97 | The majority of the equipment procurement should be completed by the end of next quarter as the majority of the equipment has been received. Installation of the transport equipment will be taking place next quarter. | 99 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly as expected and the project will be completed within the three year timeline of the award period. Much progress is expect on all components of the network next quarter. | 99 | Significant progress of the equipment deployment will be made next quarter as the transport equipment will be installed. The DC power and AC upgrade may not be complete until the following quarter. | 99 | Network Testing should be almost complete by the end of next quarter. The network will be finished prior to the three year award period end. | 2013-05-20 09:32 | 2013-05-20 09:32 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2013 | Q2 | Q2 - 2013 | 10648 | 8984 | FALSE | 100 | The BCI project was initially projected to be completed before Year 3 Quarter 2 (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is complete and only few items notated above remain for this project. Therefore the project will be 100% completed by the end of next quarter. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 100 | The network design portion of the project will be complete by the end of next quarter. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | The equipment procurement will be complete by the end of next quarter. | 100 | The network build will be complete by the end of next quarter. | 100 | The equipment deployment will be complete by the end of next quarter. | 100 | The network testing will be complete by the end of next quarter. | 2013-08-20 09:36 | 2013-08-20 09:36 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570099 | 2013 | Q3 | Q3 - 2013 | 11908 | 10077 | FALSE | 100 | Although the project is completed, the total budget will not be expended for the project. Overall about 95% of the budget has been expended. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Although the project is completed, the entire Equipment budget will not be expended for the project. About 99% of the Equipment budget has been expended. | 100 | Although the project is completed, the entire Construction budget will not be expended for the project. All construction invoices have been paid in full, therefore about 96% of the Construction budget has been expended. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 2014-02-27 15:46 | 2014-02-27 15:46 | 5995 | 5995 | Bloomingdale Communications Inc
NT10BIX5570100 | 2010 | Q4 | Q4 - 2010 | 1230 | 2259 | FALSE | 25 | Baseline is 21%. Slightly ahead of schedule | 0 | N/A | No variance | 100 | No variance | 100 | No variance | 15 | Baseline is 10%. Slightly ahead of schedule | 15 | Baseline is 10%. Slightly ahead of schedule | 0 | No variance | 50 | No variance | 10 | No variance | 0 | No variance | 0 | No variance | 2011-02-18 16:18 | 2011-02-18 16:18 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2011 | Q1 | Q1 - 2011 | 1932 | 2711 | FALSE | 49 | Baseline is 35. Continued progress on construction should keep us ahead of baseline projections. | 0 |  | N/A | 100 | Completed and in line with baseline | 100 | Completed and in line with baseline | 34 | In line with baseline | 22 | In line with baseline | 0 | N/A | 65 | In line with baseline | 30 | Baseline is 19. Continued progress on construction should keep us ahead of baseline projections. | 10 | In line with baseline | 0 | In line with baseline | 2011-05-10 15:40 | 2011-05-10 15:40 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2011 | Q2 | Q2 - 2011 | 3048 | 3281 | FALSE | 60 | Baseline is 41% | 0 |  | N/A | 100 | In line with Baseline | 100 | In line with Baseline | 63 | Baseline is 47% Staying ahead of what is needed for construction | 46 | Baseline is 34% Staying ahead of what is needed for construction | 0 | N/A | 80 | In line with Baseline | 43 | Baseline is 30%. Continue to be ahead of schedule on network construction. | 23 | In line with Baseline | 20 | In line with Baseline | 2011-08-12 14:36 | 2011-08-12 14:36 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2011 | Q3 | Q3 - 2011 | 4032 | 3856 | FALSE | 74 | Baseline is 52. Weather permitting we will stay ahead of schedule. | 0 | NA | NA | 100 | On Baseline | 100 | On Baseline | 78 | Baseline 62. Staying ahead of schedule | 70 | Baseline 47. Staying ahead of schedule | 0 | NA | 74 | Baseline 100. Continue to stay under budget on equipment | 60 | Baseline 40. Staying ahead of schedule | 50 | Baseline 42. Staying ahead of schedule | 33 | On Baseline | 2011-11-14 15:08 | 2011-11-14 15:08 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2011 | Q4 | Q4 - 2011 | 4974 | 4648 | FALSE | 83 | Remain ahead of baseline which is 60 | 0 | None | N/A | 100 | In line with baseline | 100 | In line with baseline | 88 | Ahead of baseline which is 72 | 82 | Ahead of baseline which is 62 | 0 | N/A | 76 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 71 | Ahead of baseline which is 51 | 75 | Ahead of baseline which is 50 | 55 | Ahead of baseline which is 52 | 2012-02-13 12:44 | 2012-02-13 12:44 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2012 | Q1 | Q1 - 2012 | 5996 | 5597 | FALSE | 97 | Remain ahead of baseline of 68. | 0 |  | N/A | 100 | In line with baseline. | 100 | In line with baseline. | 93 | Ahead of baseline of 84. | 87 | Ahead of baseline of 72. | 0 | N/A | 83 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 90 | Ahead of baseline of 64. | 79 | Ahead of baseline of 63. | 64 | Slightly ahead of baseline of 60. | 2012-05-09 17:12 | 2012-05-09 17:12 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2012 | Q2 | Q2 - 2012 | 7146 | 6200 | FALSE | 100 | 106 Costs have been higher, making up with private money | 0 |  | N/A | 100 | In line | 100 | In line | 96 | In line | 92 | Ahead of baseline of 84 | 0 | N/A | 87 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 100 | 102 Construction costs have been higher than estimated, making up with private money | 84 | Ahead of baseline of 74 | 73 | In line | 2012-08-20 09:44 | 2012-08-20 09:44 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2012 | Q3 | Q3 - 2012 | 7850 | 6629 | FALSE | 100 | Actual will be 115% due to higher engineering cost. Remaining costs are being covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | Slightly behind baseline of 100. | 92 | Ahead of baseline of 96 | 0 | NA | 84 | Baseline is 100. We will still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 95 | Actual will be 111% due to higher engineering cost. Overruns are being covered by private funds. | 82 | Slightly ahead of baseline of 85 | 73 | In line with baseline | 2012-11-13 17:02 | 2012-11-13 17:02 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2012 | Q4 | Q4 - 2012 | 8720 | 7522 | FALSE | 100 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | Actual will be at 100%. Additional amount covered by private funds | 92 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 0 | NA | 84 | Actual will be around 90%. Lower costs than expected | 95 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 82 | Will be completed and additional costs covered by private funds | 73 | Will be completed and additional costs covered by private funds | 2013-02-12 10:13 | 2013-02-12 10:13 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2013 | Q1 | Q1 - 2013 | 9962 | 8525 | FALSE | 100 | Actual spend is 127% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted for. | 0 | NA | 86 | Actual spend is 86% due to lower costs of equipment than originally budgeted. | 100 | Actual spend is 139% as we continue to complete our build. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2013-05-29 14:17 | 2013-05-29 14:17 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2013 | Q2 | Q2 - 2013 | 10760 | 9045 | FALSE | 100 | Actual spend is 127% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual Spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted | 0 | NA | 86 | Lower costs of equipment than originally budgeted. | 100 | Actual spend is 138% due to higher construction costs than expected. | 0 | NA. Costs were included in Network Build | 0 | NA. Costs were included in Network Build | 2013-08-27 11:48 | 2013-08-27 11:48 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570100 | 2013 | Q3 | Q3 - 2013 | 11858 | 10028 | FALSE | 100 | Actual spend is 121% of original budget due to higher costs in engineering and permitting. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted. | 0 | NA | 100 | Actual spend was 86% due to lower costs of equipment than originally budgeted | 100 | Actual spend is 129% due to higher construction costs than budgeted. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2014-02-21 09:24 | 2014-02-21 09:24 | 6055 | 6055 | Delta Communications, L.L.C.
NT10BIX5570101 | 2010 | Q4 | Q4 - 2010 | 976 | 2021 | FALSE | 17 | No variance | 19 | Admin, legal | No variance | 100 | No variance | 40 | Original goal was to complete 81% of network design by the end of March 2011. This may be delayed due to delay in completion of EA. Route refinement for EA purposes must be completed before engineering surveys can commence for those areas. We expect to make up this time and complete 100% by the end of June 2011 as planned. | 44 | No variance | 20 | No variance | 0 | No variance | 88 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-04 14:28 | 2011-02-04 14:28 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2011 | Q1 | Q1 - 2011 | 2176 | 2833 | FALSE | 21 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 8%. | 32 | Admin & Legal | No variance is expected. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 30%. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 25%. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 48 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 0 | N/A | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 1%. | 28 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 4%. | 87 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 28 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 2011-05-19 14:43 | 2011-05-19 14:43 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2011 | Q2 | Q2 - 2011 | 3010 | 3262 | FALSE | 40 | Our baseline % complete for this quarter was 44%. Reasons for this variance are cumulative per the below. | 39 | Admin & Legal | Our baseline % complete for this quarter was 43%. We have been slightly under budget for far for costs in this category, which accounts for the small variance. | 76 | Our baseline % complete for this quarter was 100%. We have struggled to completed our EA, but it has now been submitted and is under review by NTIA. | 72 | Our baseline % complete for this quarter was 100%. We went through extensive route refinement and had all route changes approved this quarter. This caused some delays with our engineering efforts, but we expect to fully recover in the next quarter. | 62 | Our baseline % complete for this quarter was 100%. This is a relatively small portion of our overall budget. While we have not completed 100% of our right of way attainment, our franchise and other processes are proceeding well and we expect to fully recover in the next quarter. We have also been under budget on this item so far, and this does/will affect our attainment percentage (which is based on % of spend). | 18 | Our baseline % complete for this quarter was 77%. This is a relatively small portion of our overall budget. While we have not completed 77% of our right of way attainment, our permitting process is proceeding well and we expect to fully recover in the next quarter. We have also been under budget on this item so far, and this does/will affect our attainment percentage (which is based on % of spend). | 0 | Our baseline % complete for this quarter was 0%. | 45 | Our baseline % complete for this quarter was 100%. This is a relatively small portion of our overall budget. The baseline report was prepared comtemplating all equipment would be paid in full once procured, however, certain equipment will not be paid in full until construction commences. | 35 | Our baseline % complete for this quarter was 38%. This category dominates our overall budget ($20M of the total budget). We have only a small variance in this category, and we expect to be able to fully recover next quarter as we receive our FONSI and construction begins. | 0 | Our baseline % complete for this quarter was 87%. We have $0 allocated to this category and therefore we have no variance. | 0 | Our baseline % complete for this quarter was 38%. We have $0 allocated to this category and therefore we have no variance. | 2011-08-11 10:56 | 2011-08-11 10:56 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2011 | Q3 | Q3 - 2011 | 3922 | 3799 | FALSE | 49 | Our baseline goal was to be 55%. Our overall project was delayed due to our EA. | 48 |  | Our baseline goal was to be 55%. The small variance is due mainly to our general liability insurance costs being lower than expected due to the delay in starting construction. | 78 | Our baseline goal was to be 100%. We completed our environmental assessment under budget. We expect no more costs to be incurred in this category unless issues related to our SAC come up. | 69 | Our baseline goal was to be 100%. Our costs to date have been lower than expected, however we expect additional costs to be incurred as our engineering is completed. | 21 | Our baseline goal was to be 100%. Costs for this category have been lower than expected to date. $548k of the $878k in this category was for joint use (pole attachment) fees. The constraints on setting new poles imposed in our EA SAC has discouraged the use of poles altogether. | 54 | Our baseline goal was to be 100%. Costs have been lower than expected to date, however we expect these costs to increase as we move forward with more expensive permits like our railroad crossings. | 0 | N/A. No costs were allocated for this category. | 71 | Our baseline goal was to be 100%. This is a relatively small portion of our overall budget. These costs are occurring later than expected due to the delay in the start of our construction. | 48 | Our baseline goal was to be 47%. No variance is expected. | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we project $0.00 spend on this category for next quarter, and since our original projection was to spend $0.00, we feel it is appropriate to record that we expect to have "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we project $0.00 spend on this category for next quarter, and since our original projection was to spend $0.00, we feel it is appropriate to record that we expect to have "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 2011-11-08 13:36 | 2011-11-08 13:36 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2011 | Q4 | Q4 - 2011 | 4874 | 4569 | FALSE | 57 | Original baseline goal was 62%. Delayed fiber availability and lower than expected costs in some categories are primary reasons for expected variance. | 57 |  | Original baseline goal was 68%. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 78 | Original baseline goal was 100%. The work related to our EA is essentially complete, but since we ended up under budget from what we original projected to spend on this milestone, we will show a "variance" for the remainder of the program. | 69 | Original baseline goal was 100%. Continued lower than expected costs from NW Georgia Regional Commission is the primary reason for expected variance. | 1 | Original baseline goal was 100%. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 25 | Original baseline goal was 100%. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 87 | Original baseline goal was 100%. Continued lower than expected equipment costs are primary reason for expected variance. | 58 | Original baseline goal was 58%. No variance projected. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 2012-02-05 19:06 | 2012-02-05 19:06 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2012 | Q1 | Q1 - 2012 | 6298 | 5751 | FALSE | 69 | Original baseline goal was to be 75% complete. Delayed fiber availability and lower than expected costs in some categories are the primary reasons for the expected variance. | 61 |  | Original baseline goal was to be 88% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 81 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 70 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 1 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 29 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance | 100 | Original baseline goal was to be 100% complete. No variance. | 71 | Original baseline goal was to be 79% complete. Delayed fiber delivery has been the primary reason for the small variance in this category. We expect to catch up in this category before the end of the program. | 0 | Original baseline goal was to be 90% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-05-25 11:38 | 2012-05-25 11:38 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2012 | Q2 | Q2 - 2012 | 6872 | 6062 | FALSE | 81 | No variance expected. | 65 |  | Original baseline goal was to be 88% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 82 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 83 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 32 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance | 97 | No variance expected. | 85 | No variance. | 0 | Original baseline goal was to be 90% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-08-06 15:58 | 2012-08-06 15:58 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2012 | Q3 | Q3 - 2012 | 8050 | 6731 | FALSE | 86 | No variance expected. | 74 |  | Original baseline goal was to be 90% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 82 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 88 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 56 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 97 | No variance expected. | 89 | No variance expected. | 0 | Original baseline goal was to be 92% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2012-11-26 16:37 | 2012-11-26 16:37 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2012 | Q4 | Q4 - 2012 | 9124 | 7899 | FALSE | 90 | Original baseline goal was to be 94% complete. Delayed permitting in Alabama is the primary reason for the expected variance. | 80 |  | Original baseline goal was to be 100% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 80 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 92 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 68 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 97 | No variance expected. | 93 | No variance expected. | 0 | Original baseline goal was to be 97% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 96% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-03-04 17:30 | 2013-03-04 17:30 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2013 | Q1 | Q1 - 2013 | 9710 | 8388 | FALSE | 95 | Original baseline goal was to be 100% complete. Delayed start of Alabama construction is the primary reason for the expected variance. | 87 |  | Original baseline goal was to be 100% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. Back-loaded legal costs for competion of UCC filings are also a reason. | 83 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to do the route modification for our 7 CAIs, we expect additional spend between now and the end of the program. | 94 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 70 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 98 | Original baseline goal was to be 100% complete. | 98 | Original baseline goal was to be 100% complete. | 0 | Original baseline goal was to be 100% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 100% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-05-13 17:04 | 2013-05-13 17:04 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2013 | Q2 | Q2 - 2013 | 10696 | 9010 | FALSE | 99 | Funds unspent at end of this quarter will be used for eligible close-out costs. | 83 |  | Funds unspent in this category at end of this quarter will be used for eligible close-out costs. | 100 | No variance expected. | 100 | No variance expected. | 0 | No variance expected. | 100 | No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 98 | Funds unspent in this category at end of this quarter will be used for eligible close-out costs. | 100 | No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-08-22 14:51 | 2013-08-22 14:51 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2013 | Q3 | Q3 - 2013 | 11254 | 9417 | FALSE | 100 | Not applicable. Project was completed this quarter. | 100 |  | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 2013-11-14 16:07 | 2013-11-14 16:07 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570101 | 2013 | Q4 | Q4 - 2013 | 11776 | 9942 | FALSE | 100 | Not applicable. Project was completed in previous quarter. | 100 |  | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 100 | Not applicable. Project was completed in previous quarter. | 2014-01-31 15:17 | 2014-01-31 15:17 | 6397 | 6397 | Appalachian Valley Fiber Network
NT10BIX5570102 | 2010 | Q4 | Q4 - 2010 | 626 | 1651 | FALSE | 7 | --- | 3 |  | --- | 100 | --- | 75 | --- | 0 | --- | 0 | --- | 0 | N/A | 4 | --- | 8 | --- | 10 | --- | 0 | --- | 2011-01-27 16:56 | 2011-01-27 16:56 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2011 | Q1 | Q1 - 2011 | 2286 | 2888 | FALSE | 6 | The Environmental Assessment and subsequent FONSI were expected to be completed by the beginning of this year and deployment was expected to be well underway by this quarter. However, we now expect the FONSI to be issued by the end of the quarter, which will allow the project to move into its implementation phase, in which BTOP funding and match are largely concentrated. | 4 |  | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed for huts to be purchased and installed at fiber sites. Fiber hut purchase and installation can commence following the issuance of the FONSI. The 4% completion reported here comprises the payment of salaries and indirect costs. | 84 | The Baseline Report assumed all EA work would be completed once the FONSI was issued; however, the project will now continue to purchase the services of our EA Consultant for on-going site evaluations throughout the implementation of the project, thus reserving a percentage of this category's completion to be distributed over the remaining quarters. | 100 | --- | 0 | N/A | 50 | --- | 0 | N/A | 0 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed the purchase of infrastructure and some telemedicine equipment during the second quarter of 2011. However, since the final EA will be submitted this quarter and consequently no FONSI has been issued to date, equipment will not be procured. The project has elected to minimize the time equipment is "warehoused" while the EA is still under review, as equipment warranties would be active during the warehouse time when this equipment is not being tested or employed. An Equipment RFP, however, is expected to issue this quarter, which will ready the project to purchase and deploy equipment quickly following the issuance of a FONSI. | 8 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011. However, without this expected development, the project will not have the opportunity to install circuits, as planned. The 8% completion reported here comprises the payment of IRU agreements. | 9 | Equipment Deployment to-date largely comprises in-kind match items that are contributed proportionally to the federal funds drawn down for the project. The Baseline Report assumed more federal funds would be drawn down in this quarter; however, for the reasons described in the other sections of this report, fewer funds will be drawn down than projected in the Baseline Report. As such, the "equipment deployment" match reflects the proportional decrease in the federal draw down. | 0 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed for equipment to be purchased and deployed, thus allowing for appropriate network testing. Therefore, network testing can commence following the issuance of the FONSI, at which time equipment can be purchased and deployed. | 2011-05-24 17:32 | 2011-05-24 17:32 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2011 | Q2 | Q2 - 2011 | 2604 | 3050 | FALSE | 20 | --- | 8 | Indirect costs, huts, easements, project management costs | --- | 86 | --- | 100 | --- | 0 | --- | 100 | --- | 0 | N/A | 25 | --- | 18 | --- | 28 | --- | 82 | --- | 2011-07-28 14:51 | 2011-07-28 14:51 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2011 | Q3 | Q3 - 2011 | 4036 | 3858 | FALSE | 29 | --- | 12 | - | --- | 89 | --- | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Year 2 Quarter 1. However, fewer miles of fiber are being constructed; therefore, there are fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. We anticipate permits to be approximately $10,000 per quarter for the remainder of the grant. Budgeted permits amount to $96,000. | 0 | N/A | 37 | --- | 27 | --- | 41 | --- | 82 | --- | 2011-11-14 15:47 | 2011-11-14 15:47 | 6618 | 6618 | University of Arkansas System
NT10BIX5570102 | 2011 | Q4 | Q4 - 2011 | 5026 | 4697 | FALSE | 48 | --- | 21 |  | --- | 92 | --- | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Year 2 Quarter 2. However, fewer miles of fiber are being constructed; therefore, there are fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. We anticipate permits to be approximately $10,000 per quarter for the remainder of the grant. Budgeted permits amount to $96,000. However, no permits were acquired this quarter and we do not anticipate any future acquisitions by our sub-recipient. We anticipate an 81% variance throughout the end of the project. | 0 | N/A | 56 | --- | 47 | --- | 69 | --- | 82 | --- | 2012-02-15 11:00 | 2012-02-15 11:00 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2012 | Q1 | Q1 - 2012 | 6052 | 5625 | FALSE | 72 | --- | 40 | Indirects, huts, easements, project management costs | --- | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +5% variance against the revised Baseline projections. | 100 | --- | 0 | N/A | 9 | --- | 100 | Site preparation for ARE-ON huts are projected to be completed in the next quarter. | 94 | --- | 67 | --- | 93 | --- | 82 | --- | 2012-05-14 09:45 | 2012-05-14 09:45 | 6618 | 6618 | University of Arkansas System
NT10BIX5570102 | 2012 | Q2 | Q2 - 2012 | 7210 | 6232 | FALSE | 87 | We have successfully managed the project and have over-achieved. We expect this to continue resulting in a +3 variance for planned completion by Q3 2012. | 71 | Indirects, huts, easements, project management costs | Fiber hut placement has progressed faster than projected resulting in variance of +7%. | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +3% variance against the revised Baseline projections. | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Q3 2012. Because of the use of IRUs there is a lesser need for railroad crossings and, thus, fewer required permits. We anticipate a -91% variance throughout the end of the project. | 0 | N/A | 97 | --- | 81 | --- | 94 | --- | 66 | We anticipate the optical network to be completed over the next two quarters. Therefore, since network testing cannot occur until completion of the optical network itself, testing will fall short of the revised Baseline figure resulting in a variance of -34% for Q3 2012. | 2012-08-22 13:30 | 2012-08-22 13:30 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2012 | Q3 | Q3 - 2012 | 7988 | 6700 | FALSE | 84 | As instructed by the FPO, the projections were calculated using the Revised PIP of October 2012 resulting from the stop-work order. | 71 | Indirects, huts, easements, project management costs | --- | 100 | The Environmental Assessment was completed in June 2011. No additional costs were anticipated. However, as a result of the CAP, we were directed to enter into new consultations with the State Historic Preservation Office (SHPO). | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 92 | --- | 81 | --- | 93 | --- | 100 | --- | 2012-11-20 16:35 | 2012-11-20 16:35 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2012 | Q4 | Q4 - 2012 | 8810 | 7603 | FALSE | 94 | As instructed by the FPO, the projections were calculated using the Revised PIP of October 2012 resulting from the stop-work order. | 89 | Indirects, huts, easements, project management costs | --- | 100 | --- | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 98 | --- | 92 | --- | 97 | --- | 100 | --- | 2013-02-15 16:00 | 2013-02-15 16:00 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2013 | Q1 | Q1 - 2013 | 9396 | 8189 | FALSE | 94 | As instructed by the FPO, these projections are calculated using the Revised PIP of October 2012 resulting from the Corrective Action Plan (CAP) changes and resulting project delays. a. The CAP affected budget and expenditure timing for the sub-recipient, necessitating a project time extension ending September 30, 2013 instead of July 31, 2013 was approved by FPO. b. The project time extension also required CAP delayed budget expenditures to be shifted within budget categories to compensate for CAP timing delays. NTIA gave guidance for this budget modification. In compliance with NTIA guidelines, the budget shifts do not exceed 10% variance guidelines, and there is no change in scope of work for Q1 2013. FPO approval for budget shifts received in March 2013. c. The PPR quarterly projections use 12 fiscal quarters, however, the CAP and weather-related delays affected project time-lines and budget expenditures by one (1) quarter. To adjust | 82 | Indirects, huts, easements, project management costs | --- | 100 | --- | 99 | --- | 0 | N/A | 83 | --- | 0 | N/A | 99 | --- | 96 | --- | 97 | --- | 79 | --- | 2013-04-29 18:03 | 2013-04-29 18:03 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2013 | Q2 | Q2 - 2013 | 10612 | 8964 | FALSE | 100 | --- | 100 | Indirects, huts, easements, project management costs | --- | 100 | --- | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 100 | --- | 100 | --- | 100 | --- | 100 | --- | 2013-08-15 14:10 | 2013-08-15 14:10 | 6617 | 6617 | University of Arkansas System
NT10BIX5570102 | 2013 | Q3 | Q3 - 2013 | 11520 | 9647 | FALSE | 0 | N/A | 0 |  | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2013-12-23 09:51 | 2013-12-23 09:51 | 6617 | 6617 | University of Arkansas System
NT10BIX5570103 | 2010 | Q4 | Q4 - 2010 | 1228 | 2257 | FALSE | 10 | No variance from Baseline Plan. | 0 | Network Management/Operations | No variance from Baseline Plan. | 50 | Progress pending Final FONSI appoval. | 30 | Progress pending Final EA approval. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | No variance from Baseline Plan. | 2011-02-18 15:54 | 2011-02-18 15:54 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2011 | Q1 | Q1 - 2011 | 2392 | 2941 | FALSE | 10 | Progress limited by project route design timeline and final FONSI approval. | 0 | Network Management/Operations | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | No variance from Baseline Plan. | 2011-05-27 15:47 | 2011-05-27 15:47 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2011 | Q2 | Q2 - 2011 | 2936 | 3225 | FALSE | 11 | Progress limited by project route design timeline and final FONSI approval. | 0 | Network Management/Operations | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 15 | Progress limited by project route design timeline and final FONSI approval. | 5 | Progress limited by project route design timeline and final FONSI approval. | 2 | Progress limited by project route design timeline and final FONSI approval. | 2 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | No variance from Baseline Plan. | 2011-08-05 14:50 | 2011-08-05 14:50 | 6961 | 6961 | Nevada Hospital Association
NT10BIX5570103 | 2011 | Q3 | Q3 - 2011 | 4124 | 3905 | FALSE | 21 | Progress limited by delays in FONSI approval. | 0 | Network Management/Operations | Progress limited by delays in FONSI approval. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 10 | Progress limited by delays in FONSI approval. | 10 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 50 | Procurement schedules accelerated to offset any potential delays associated with supplier inventory. | 0 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 2011-11-17 18:46 | 2011-11-17 18:46 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2011 | Q4 | Q4 - 2011 | 5352 | 5023 | FALSE | 35 | Progress delayed by extended EA and FONSI approval process | 0 | true | N/A | 100 | No variance from Baseline Plan | 100 | No variance from Baseline Plan | 30 | Progress delayed by extended EA and FONSI approval process | 30 | Progress delayed by extended EA and FONSI approval process | 0 | Progress delayed by extended EA and FONSI approval process | 100 | Progress expedited to exceed Baseline Plan projections | 35 | Progress delayed by extended EA and FONSI approval process | 35 | Progress delayed by extended EA and FONSI approval process | 35 | Progress delayed by extended EA and FONSI approval process | 2012-02-28 14:20 | 2012-02-28 14:28 | 7311 | 7311 | Nevada Hospital Association
NT10BIX5570103 | 2012 | Q1 | Q1 - 2012 | 6168 | 5686 | FALSE | 43 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 |  | N/A | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 60 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 60 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 55 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 100 | Accelerated to meet project build time line. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 2012-05-17 19:07 | 2012-05-17 19:07 | 7311 | 7311 | Nevada Hospital Association
NT10BIX5570103 | 2012 | Q2 | Q2 - 2012 | 7084 | 6169 | FALSE | 44 | Progress pending execution of agreements, specifically with utility providers, and completion of fiber delivery. | 0 |  | N/A | 100 | No variance from baseline plan. | 100 | No variance from baseline plan. | 60 | Progress pending approval of Rights of Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 60 | New requirements, such as stationing on drawing and traffic control plans, needed from contractors doing work. Also, ongoing negotiations with landowners, some of which are out of state and slow to respond. | 55 | Pending approval of engineering re-design (route modifications) due to a utility not allowing use of substations for shelter placement. | 80 | Time frame of procurement modified to ensure the extension of equipment warranty period during actual deployment. | 1 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | 25 | Pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 10 | Network testing not feasible until network has been deployed and activated. | 2012-08-15 15:33 | 2012-08-15 15:33 | 7311 | 7311 | Nevada Hospital Association
NT10BIX5570103 | 2012 | Q3 | Q3 - 2012 | 8026 | 6719 | FALSE | 46 | Projected progress meaningfully altered due to previous delay in fiber delivery, as well as agreement with utility providers. However, fiber delivery anticipated to be complete in 4Q12. Right-of-Way agreements with Tribal entities and approval of design modifications also anticipated to be received in 4Q12. | 0 |  | N/A | 100 | No variance from baseline plan. | 100 | No variance from baseline plan. | 60 | Progress pending approval of Rights-of-Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 40 | Progress pending ongoing negotiations with landowners, some of which are out of State and slow to respond. | 20 | Progress pending approval of engineering redesigned (route modifications). | 90 | Timeframe of procurement modified to ensure the extension of equipment warranty period through project deployment. | 10 | Projected progress meaningfully altered due to previous delay in fiber delivery, as well as agreement with utility providers. However, fiber delivery anticipated to be complete in 4Q12. Right-of-Way agreements with Tribal entities and approval of design modifications also anticipated to be received in 4Q12. | 15 | Progress pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 10 | Projected progress meaningfully altered due to delay in network deployment in previous quarter. | 2012-11-23 17:15 | 2012-11-23 17:15 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2012 | Q4 | Q4 - 2012 | 8824 | 7610 | FALSE | 63 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 1Q13 and approval of pending ROW applications are expected to be received. It is also expected that utility providers will approve pending permits. | 0 |  | N/A | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 75 | Progress pending approval of Rights-of-Way from US Forest Service, Bureau of Land Management, Bureau of Reclamation and various Tribal entities. | 70 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 30 | Progress pending approval of engineering redesigned (route modifications). | 90 | Time frame of procurement modified to ensure the extension of equipment warranty period through project deployment. | 40 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications and ROW applications are anticipated in 1Q13. Pending permits from the utility providers are also expected to be released. | 15 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications and ROW applications are anticipated in 1Q13. Pending permits from the utility providers are also expected to be released. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-02-15 16:50 | 2013-02-15 16:50 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2013 | Q1 | Q1 - 2013 | 9930 | 8508 | FALSE | 60 | Projected progress meaningfully altered due to a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 2Q13 and approval of pending ROW applications are expected to be received. | 0 |  | N/A | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 30 | Progress pending approval of engineering redesigned (route modifications). | 90 | Time frame of procurement modified to ensure the extension of equipment warranty period through project deployment. | 20 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 2Q13. | 12 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 2Q13. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-05-28 13:50 | 2013-05-28 13:50 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2013 | Q2 | Q2 - 2013 | 10644 | 8982 | FALSE | 53 | Project progress meaningfully altered due to a delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 3Q13 and approval of pending ROW applications are expected to be received. | 0 |  | N/A | 100 | Project extension will allow completion of redesigned network route. | 100 | Projected extension will allow completion of redesigned network route. | 100 | Project extension and funding will allow time for negotiations and completion of ROW applications. | 100 | Project extension and funding will allow time for acquiring all permits and approvals for redesigned network route. | 30 | Progress pending approval of engineering redesign (route modifications). | 90 | Time frame of procruement modified to ensure the extension of equipment warranty period through project deployment. | 20 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with Federal agencies and Tribal entitiesrelated to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 3Q13. | 12 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 3Q13. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-08-19 19:06 | 2013-08-19 19:06 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2013 | Q3 | Q3 - 2013 | 11244 | 9412 | FALSE | 48 | Upon federal approval we anticipate submission of an in-kind match to rectify grant match ratio; and reimbursement of basic charges to sustain project activity including ROW and construction permit completion | 0 |  | N/A | 100 | Project extension will allow completion of EA | 100 | Project extension will allow completion of redesigned network route | 98 | Due to the additional interruption into project advancement all rights of way are not anticipated until end of January 2014, if project reengages by early November | 100 | Re-engaging utilities and federal/state/tribal agencies to finalize permits in order to begin construction Q1 2014 | 30 | Anticipate further advancement of site prep work towards the end of Q1 2014 | 90 | Will order long lead items to be delivered shortly before construction | 14 | No activity expected based on project and funding hold. If re-engaged in early November, we can anticipate building in Q1 2014. | 8 | No activity expected based on project and funding hold. If re-engaged in early November, we can anticipate further deployment in late Q1 2014. | 20 | No activity expected based on project and funding hold. | 2013-11-13 18:03 | 2013-11-13 18:03 | 6121 | 6121 | Nevada Hospital Association
NT10BIX5570103 | 2013 | Q4 | Q4 - 2013 | 11830 | 10006 | FALSE | 48 | Upon federal approval we anticipate submission of invoices for work completed ; and reimbursement of basic charges to sustain project activity including ROW and construction permit completion. The budget reflects anticipated payment of past due invoices, including fiber, next quarter. | 0 |  | N/A | 100 | CAP approval will allow completion of EA. | 100 | CAP approval will allow completion of redesigned network route. | 98 | Pending CAP approval project advancement on all rights of way are not anticipated until end of May 2014. | 100 | RE-engaging utilities and federal/state/tribal agencies to finalize permits in order to begin construction Q2 2014. | 30 | Anticipate further advancement of site prep work towards the end of Q2 2014. | 90 | Will order long lead items to be delivered shortly before construction. | 14 | No activity expected pending approval of CAP. | 8 | No activity expected until CAP approved. | 20 | No activity pending CAP approval | 2014-02-14 19:27 | 2014-02-14 19:27 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570103 | 2014 | Q1 | Q1 - 2014 | 12226 | 10399 | FALSE | 61 | Variance from baseline plan due to CAP lift late in Q1.Project progress will increase in Q2. | 0 |  | N/A | 98 | EA will continue as route modification processing progresses. | 99 | Network design nears completion in Q2 as route modifications are approved. | 98 | ROW procurement will continue to progress following new network design. | 75 | Permitting and licensing will progress as all parties are re-engaged. | 60 | Site prep work will continue based upon updated project schedule. | 87 | Equipment procurements will continue to track construction in this quarter. | 30 | Construction will commence in this quarter. | 40 | Equipment deployment will track construction resulting in an increase this quarter. | 32 | Newly completed segments will be tested and accepted tracking construction progress. | 2014-05-22 11:23 | 2014-05-22 11:23 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570103 | 2014 | Q2 | Q2 - 2014 | 12444 | 10630 | FALSE | 63 | Q 3 will reflect continued progress in-line with current schedule. | 0 |  | N/A | 100 | With the approval of AAR#6 all EA work will be completed. | 98 | With the exception of the new network segment crossing in the Walker River Paiute tribe, all network design should be complete in Q3. | 99 | A majority of remaining ROW work will be completed in Q3. | 77 | Permits and attachment licenses continue to be issues ahead of construction in Q3. | 50 | Site preparation at Beatty and Lida Junction scheduled for Q3 completion. | 90 | Equipment procurement will occur as POP facilities and CAIs are ready for deployment. | 50 | Continued construction combined with a successful NSHE interconnect will contribute to substantial progress in Q3. | 24 | Yerington and Pahrump POP deployment scheduled for Q3. | 30 | As full segments are completed, testing will continue. | 2014-08-21 08:55 | 2014-08-21 08:55 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570103 | 2014 | Q3 | Q3 - 2014 | 12596 | 10867 | FALSE | 80 | Q4 Progress continues to track project schedule. | 0 |  | N/A | 99 | Assessment completion planned for the majority of outstanding segments in Q4. | 99 | Network Design nears completion. | 99 | Right of Way work activities will begin to decrease in Q4. | 70 | Permits continue to track construction progress. | 50 | POP site preparation continues. | 99 | The majority of outstanding procurements will be completed in Q4. | 60 | Construction continues on-pace with current schedule. | 40 | Pahrump POP equipment deployment projected for Q4. | 25 | Network testing will commence with segment completion. | 2014-11-13 17:29 | 2014-11-13 17:29 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570103 | 2014 | Q4 | Q4 - 2014 | 12706 | 11032 | FALSE | 93 | Q1 2015 progress will continue to track project schedule. | 0 | N/A | N/A | 100 | Environmental assessment will be completed next quarter. | 100 | Network design will be completed next quarter. | 99 | All right of way not involved in the route modification process will be secured. | 90 | Permitting and licensing continue to track construction progress. | 83 | Continued site preparation depends upon route modification approval. | 99 | Small equipment purchase remain as construction continues. | 74 | Construction progress continues as scheduled in Q1 2015. | 83 | Equipment installation will be completed in all constructed POP facilities. | 25 | Network testing will commence with segment completion. | 2015-02-20 11:18 | 2015-02-20 11:18 | 6120 | 6120 | Nevada Hospital Association
NT10BIX5570103 | 2015 | Q1 | Q1 - 2015 | 12836 | 11211 | FALSE | 98 | The project is expected to near completion next quarter. | 0 | N/A | N/A | 100 | Environmental Assessment work completed last quarter. | 100 | Network design will be completed next quarter pending AAR approval. | 100 | All rights of way will be secured next quarter. | 98 | Permitting and licensing will continue to progress with network construction. | 100 | Site preparation will be completed next quarter pending AAR approval. | 100 | All equipment procurement will be completed next quarter. | 89 | Network construction will continue following currently adopted project schedule. | 95 | Network wide equipment deployment will near completion. | 75 | Network testing will track segment completion. | 2015-05-22 14:22 | 2015-05-22 14:22 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570103 | 2015 | Q2 | Q2 - 2015 | 12898 | 11281 | FALSE | 100 | The project is expected to near completion next quarter. 116.26% with additional match | 0 | 0 | N/A | 100 | Environmental Assessment work completed this quarter. | 100 | Network design will be completed next quarter pending AAR approval. | 100 | All rights of way will be secured next quarter. | 100 | Permitting and licensing will complete with project construction. | 100 | Site preparation will be completed next quarter pending AAR approval. | 100 | Equipment Procurement Completed | 100 | Network construction is projected to complete next quarter. | 100 | Equipment deployment is projected to be completed next quarter. | 100 | Network testing will track segment completion. | 42255.472 | 42255.472 | 7786 | 7786 | Nevada Hospital Association
NT10BIX5570104 | 2010 | Q4 | Q4 - 2010 | 994 | 2036 | FALSE | 3 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Therefore spending of funds was delayed in the last quarter thus affecting this quarter as well. | 0 |  | No Variance | 100 | No Variance from Baseline | 90 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs which affected network design last quarter and again in this quarter. | 25 | After discussions with several of the entities involved in Rights Of Way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the Rights Of Way are currently being processed. | 25 | Environmental Assessment submitted during this quarter and Finding Of No Significant Impact is anticipated to be received, however there was a delay in receipt of the response from the Mississippi State Historic Preservation Officer that we anticipate will delay the receipt of Finding Of No Significant Impact. As per the Environmental Assessment Special Awards Condition only allowable funds will be spent prior to receipt of Finding Of No Significant Impact causing the variance from the baseline report. | 15 | No Variance from baseline | 20 | No Variance from baseline | 1 | When Finding Of No Significant Impact is received we intend to purchase fiber. This expenditure represents the first fiber purchase assuming receipt of Finding Of No Significant Impact. | 0 | No Variance | 0 | No Variance | 2011-02-07 13:04 | 2011-02-07 13:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2011 | Q1 | Q1 - 2011 | 2104 | 2797 | FALSE | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | No variance from baseline | 100 | No Variance from baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 20 | Since the baseline report was submitted it has become evident to Contact Network Inc. the equipment procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Due to delays in issuing the Equipment request for proposal we are behind in procurement. We will be placing equipment orders this quarter to somewhat catch up in this category versus our initial baseline projections. | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 2011-05-17 17:46 | 2011-05-17 17:46 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2011 | Q2 | Q2 - 2011 | 2928 | 3221 | FALSE | 27 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. |  |  |  | 100 | No Variance from Baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | During this quarter an additional ten Community Anchor Institutions will be connected to our network. This brings the total to forty seven anchor institutions which exceeds our baseline projections. | 20 | Equipment is being purchased on an as needed basis. We expect significant purchases to be made during the next quarter. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-04 17:12 | 2011-08-04 17:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2011 | Q3 | Q3 - 2011 | 3904 | 3790 | FALSE | 29 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 20 | Equipment is being purchased on an as needed basis. | 31 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2011-11-07 11:44 | 2011-11-07 11:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2011 | Q4 | Q4 - 2011 | 5346 | 5019 | FALSE | 37 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  |  | 100 | No variance from baseline. | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 27 | Equipment is being purchased on an as needed basis. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-02-28 13:42 | 2012-02-28 13:42 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2012 | Q1 | Q1 - 2012 | 5944 | 5571 | FALSE | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance from baseline. | 100 | No variance from baseline. | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report.Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. wil | 67 | Equipment is being purchased on an as needed basis. | 60 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-05-07 15:06 | 2012-05-07 15:06 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2012 | Q2 | Q2 - 2012 | 6740 | 5996 | FALSE | 74 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report.Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. wil | 67 | Equipment is being purchased on an as needed basis. | 74 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-07-30 17:49 | 2012-07-30 17:49 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2012 | Q3 | Q3 - 2012 | 8048 | 6730 | FALSE | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 85 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 50 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 69 | Equipment is being purchased on an as needed basis. | 77 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-11-26 16:11 | 2012-11-26 16:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2012 | Q4 | Q4 - 2012 | 8850 | 7632 | FALSE | 86 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 95 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 55 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 69 | Equipment is being purchased on an as needed basis. | 86 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2013-02-19 16:16 | 2013-02-19 16:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2013 | Q1 | Q1 - 2013 | 9838 | 8455 | FALSE | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2013-05-20 16:52 | 2013-05-20 16:52 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2013 | Q2 | Q2 - 2013 | 10660 | 8990 | FALSE | 100 | No variance from baseline. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2013-08-20 13:11 | 2013-08-20 13:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2013 | Q3 | Q3 - 2013 | 11182 | 9372 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-11-04 14:05 | 2013-11-04 14:05 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2013 | Q4 | Q4 - 2013 | 11906 | 10075 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-02-27 11:17 | 2014-02-27 11:17 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | 2014 | Q1 | Q1 - 2014 | 12124 | 10309 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-04-30 16:18 | 2014-04-30 16:18 | 5678 | 5678 | Contact Network Inc. d/b/a InLine
NT10BIX5570105 | 2010 | Q4 | Q4 - 2010 | 1002 | 2047 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 50 | The compeletion of the network design is dependant upon the awarding of a contract to a qualified vendor. | 25 | N/A | 10 | N/A | 10 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-08 10:11 | 2011-02-08 10:11 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2011 | Q1 | Q1 - 2011 | 2228 | 2859 | FALSE | 10 | In line with baseline report | 0 |  | No Change from baseline | 100 | In line with baseline report | 25 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 25%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 5 | In line with baseline report | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 2011-05-20 16:23 | 2011-05-20 16:23 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2011 | Q2 | Q2 - 2011 | 3224 | 3373 | FALSE | 2 | Overall progress has been revised from 15 to 2% to align with budget expenditure. | 0 |  | In line with baseline report. | 80 | Overall progress has been revised from 100 to 80% to align with budget expenditure. | 5 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised to 5%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 0 | With the removal of the 100 mile backhaul we do not anticipate the need for construction permits at this time. | 0 | Revised 0%. Site prep is expected to begin in following quarter. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 2011-08-19 09:59 | 2011-08-19 09:59 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2011 | Q3 | Q3 - 2011 | 3900 | 3788 | FALSE | 2 | We expect to have a vendor selected and contract negotiations almost complete. The delay in the overall project completion is a result of the change in scope to remove the dark fiber and add additional towers to the design. | 0 |  | In line with baseline report. | 90 | EA's are complete for the 114 sites in the project. However, we have left the percent complete at 90% in case we need to supplement any new sites. | 5 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 5%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 0 | As a result of the re-scoped design the construction requirement has been significantly reduced. The baseline report projected 25% complete by the end of this period. We believe we will catch up in the next two quarters. | 0 | As a result of the re-scoped design the construction requirement has been significantly reduced. The baseline report projected 30% complete by the end of this period. We believe we will catch up in the next two quarters. | 0 | Since we have not secured a vendor we have not been in a position to purchase equipment. We believe we will catch up in the next two quarters. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 2011-11-04 16:15 | 2011-11-04 16:15 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2011 | Q4 | Q4 - 2011 | 4722 | 4370 | FALSE | 5 | By the end of the quarter a contract should be executed and site development work started at tower sites. | 0 |  | N/A | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 25 | A preliminary design should be completed by the vendor. Final approval will occur in the second quarter of 2012 | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor starting in the second quarter of 2012 | 0 | Site preparation has been delayed until contractor selection and contract execution. Site prep should commence is the 2nd quarter | 0 | The State expects to make equipment purchases for Microwave Radios and eNodeB's by the end of the second quarter of 2012. | 0 | The State expects network build to start in the second quarter of 2012. | 0 | Equipment purchases for Microwave Radios and eNodeB's by the end of the second quarter of 2012. Equipment will be deployed in a phased in approach outlined in the project plan. | 10 | Initial testing shall commence with equipment deployment | 2012-01-30 16:15 | 2012-01-30 16:15 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2012 | Q1 | Q1 - 2012 | 5954 | 5576 | FALSE | 1 | See narrative in section 3. | 0 |  | No Change | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in section 3. | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor when the project starts. | 0 | Under the State's revised plan, an RFP will be issued for site evaluation services. Site development services may be included as part of the RFP. The State is working with the NTIA on an agreeable plan. See answer to question (3) for more detail. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 2012-05-08 10:07 | 2012-05-08 10:07 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2012 | Q2 | Q2 - 2012 | 6376 | 5796 | FALSE | 1 | See narrative in (Project Indicators Next Quarter section 1) | 50 | Site identification | See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2012-07-10 16:05 | 2012-07-10 16:05 | 6169 | 6169 | Treasury, New Jersey Department of
NT10BIX5570105 | 2012 | Q3 | Q3 - 2012 | 7870 | 6639 | FALSE | 1 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Site Identification | See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2012-11-14 11:50 | 2012-11-14 11:50 | 7541 | 7541 | Treasury, New Jersey Department of
NT10BIX5570105 | 2012 | Q4 | Q4 - 2012 | 8640 | 7453 | FALSE | 5 | See narrative in (Project Indicators Next Quarter section 1) | 50 | Site Identification/Coverage Design Map | Begin Site Identification of government owned sites and develop initial coverage design map. See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2013-01-31 15:38 | 2013-01-31 15:38 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2013 | Q1 | Q1 - 2013 | 9682 | 8373 | FALSE | 3 | See narrative above in Project Indicators (Next Quarter) | 100 | Site Identification/Coverage Design Map | Onboard site identification resources and begin site identification of government owned sites and develop initial coverage design map. | 90 | Assessments are complete for the 114 sites in the project. Team may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative above in Project Indicators (Next Quarter) | 0 | Rights of Way is no longer needed since the fiber component has been removed from the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 2013-05-10 13:40 | 2013-05-13 12:55 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2013 | Q2 | Q2 - 2013 | 10182 | 8669 | FALSE | 4 | See narrative above in Question 1 | 100 | Site Identification/Initial Coverage Design/Site Assessment | Onboard site assessment resources and begin site assessment activities; finalize site identification activities and update initial coverage design | 90 | Assessments are complete for the 114 sites in the project. Team may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in Question 1 | 0 | Rights of way is no longer needed since the fiber component has been removed from the project. | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 2013-07-26 13:34 | 2013-07-26 13:34 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2013 | Q3 | Q3 - 2013 | 11180 | 9371 | FALSE | 5 | See narrative above in Question 1 | 100 | Site Identification / Initial Coverage Design | Site identification and initial coverage design is complete. | 90 | Assessments are complete for the 114 sites initially defined for the project. Team may need to replace or supplement these sites so the project complete will remain at 90%. | 5 | See narrative above in Question 1 | 0 | Rights of way is no longer needed since the fiber component has been removed from the project. | 0 | See narrative above in Question 1 | 0 | Until project direction is defined, the project team will delay all site preparation activities. | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 2013-11-01 17:43 | 2013-11-01 17:43 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2013 | Q4 | Q4 - 2013 | 11846 | 10019 | FALSE | 4 | See narrative in Question 1 | 100 | Site Identification/Initial Coverage Design | Based on the the previously approved project scope in the UASI region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). | 90 | The project team submitted the revised EHP Pre-Screening list to NTIA; currently under review with NTIA Environmental team. New Jersey anticipates a response from the environmental team. | 30 | Network design activities will continue based on identified deployable locations. | 0 | The newly approved project scope does not call for right of way requirements. | 0 | The newly approved project scope does not call for construction of any new towers. Any permits needed will be obtained by the contractor. | 10 | Potential sites have been identified for deployable assets. The project team will continue to identify locations for the deployable assets and conduct site visits. New Jersey also anticipates collaborating with electrical companies to support providing electrical capacity to the deployable assets once placed. | 0 | See narrative in Question 1. | 0 | Construction of the network has not started and was delayed due to the LTE suspension and change in project scope. | 0 | Equipment deployment is delayed until a vendor has been procured to purchase and integrate equipment and upon construction of Cell on Wheels. | 0 | Network testing will begin upon construction and deployment of Cell on Wheels. | 2014-02-19 14:26 | 2014-02-19 14:26 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2014 | Q1 | Q1 - 2014 | 12178 | 10363 | FALSE | 5 | See narrative in Question 1 | 100 | Site Identification/Initial Coverage Design | Based on the the previously approved project scope in the UASI region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 100 | The project team submitted the revised EHP Pre-Screening list to NTIA and was approved by the Environmental team. | 35 | Network design activities will continue based on identified deployable locations. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | The newly approved project scope does not call for right of way requirements. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | The newly approved project scope does not call for construction of any new towers. Any permits needed will be obtained by the contractor. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 20 | Potential sites have been identified for deployable assets. The project team will continue to identify locations for the deployable assets and conduct site visits. New Jersey also anticipates collaborating with electrical companies to support providing electrical capacity to the deployable assets once placed. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | Upon release of the Statements of Work and final vendor selection, equipment procurement will begin. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | Construction of the network will begin upon final vendor selection, anticipated for summer 2014. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | Equipment deployment is delayed until a vendor has been procured to purchase and integrate equipment and upon construction of Cell on Wheels. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | Network testing will begin upon construction and deployment of Cell on Wheels. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 2014-05-12 10:40 | 2014-05-12 10:40 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2014 | Q2 | Q2 - 2014 | 12404 | 10597 | FALSE | 5 | See narrative above. | 100 | Site identification / Initial Coverage Design | Based on the the previously approved project scope in the Urban Area Security Initiative (UASI) region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 100 | The project team submitted the revised EHP Pre-Screening list to NTIA and was approved by the Environmental team. | 75 | Network design activities will continue based on identified deployable locations. The team anticipates finalizing preliminary locations for deployables prior to final vendor selection. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | The newly approved project scope does not call for right of way requirements. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 0 | The newly approved project scope does not call for construction of any new towers. Any permits needed will be obtained by the contractor. The LTE suspension due to passage of the Middle Class Tax Relief Act delayed progress. | 50 | Potential sites have been identified for deployable assets. The project team continues to identify locations for the deployable assets and conduct site visits. New Jersey also anticipates collaborating with electrical companies to support providing electrical capacity to the deployable assets once placed. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 0 | The Statement of Work was released in June. Upon final vendor selection, equipment procurement will begin. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 0 | Construction of the network will begin upon final vendor selection, anticipated for summer 2014. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 0 | Equipment deployment is delayed until a vendor has been procured to purchase and integrate equipment and upon construction of Cell on Wheels. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 0 | Network testing will begin upon construction and deployment of Cell on Wheels. The LTE suspension, due to passage of the Middle Class Tax Relief Act,delayed progress. | 2014-08-13 09:22 | 2014-08-13 09:22 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2014 | Q3 | Q3 - 2014 | 12594 | 10866 | FALSE | 6 | See narrative above. | 100 | Site identification/Initial Coverage Design | Based on the the previously approved project scope in the Urban Area Security Initiative (UASI) region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 100 | The project team submitted the revised EHP Pre-screening list to NTIA and was approved by the Environmental team. | 75 | Microwave paper studies will be completed and the site surveys will be in process. The deployable trailer prototype will be built and approved. | 0 | The newly approved project scope does not call for right of way requirements. | 0 | The newly approved project does not call for construction of any new towers. Any permits needed will be obtained by the contractor. | 75 | Site surveys will continue and any site preparation will be scoped. | 80 | Bills of materials will be finalized and procurements will be in process. | 10 | Prototypes of the Cell on Wheels and other equipment will begin during the next reporting period. | 0 | Equipment deployment is anticipated to begin in the next reporting period. | 0 | Network testing is anticipated to begin upon construction and deployment of the Cell on Wheels. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 2014-11-13 15:06 | 2014-11-13 15:06 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2014 | Q4 | Q4 - 2014 | 12736 | 11062 | FALSE | 70 | See narrative above. | 0 |  |  | 100 | The project team submitted the revised EHP Pre-screening list to NTIA and was approved by the Environmental team. | 80 | Microwave paper studies will be finalized,site surveys complete, LE's and CD's 50% copmplete. The 25 % of the deployables will be in service. | 0 | The newly approved project scope does not call for right of way requirements. | 0 | The newly approved project does not call for construction of any new towers. Any permits needed will be obtained by the contractor. | 80 | Site surveys will continue and any site preparation will be scoped. | 85 | Bills of materials received and procurements finalized. | 15 | Prototypes of the Cell on Wheels and other equipment will begin during the next reporting period. | 25 | Equipment deployment will start | 0 | Network testing is anticipated to begin upon construction and deployment of the Cell on Wheels. The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 2015-02-27 13:09 | 2015-02-27 13:09 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2015 | Q1 | Q1 - 2015 | 12830 | 11208 | FALSE | 100 | See narrative above. | 100 | N/A | Based on the the previously approved project scope in the Urban Area Security Initiative (UASI) region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). The LTE suspension, due to passage of the Middle Class Tax Relief Act, delayed progress. | 100 | The project has a categorical exclusion | 100 | The remaining network design elements for transport and IP will be finalized | 0 | The approved project scope does not call for right of way requirements. | 0 | The approved project does not call for construction of any new towers. Any permits needed will be obtained by the contractor. | 100 | Site preparation will be completed by the end of second quarter | 90 | The balance of equipment will have been procured. | 90 | Network Build will be substantially complete | 100 | Equipment deployment will be substantially complete | 60 | FAT and SOT testing will have been completed. Only Acceptance Testing will remain. | 2015-05-19 13:26 | 2015-05-19 13:26 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570105 | 2015 | Q2 | Q2 - 2015 | 12900 | 11282 | FALSE | 100 | See narrative above | 100 |  | Based on the previously approved project scope in the Urban Area Security Initiative (UASI) region, site identification was completed in August 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, And Atlantic City regions are complete. The LTE suspension, due to the passage of the Middle Class Tax Relief Act, delayed progress | 100 | The project has a categorical exclusion | 100 | Network acceptance will be complete | 0 | The approved project dues not call for right of way | 0 | Any permits needed will be procured by the contractor | 100 | All sites will be constructed | 100 | The balance of equipment will be procured | 100 | Equipment deployment will for complete | 100 | Equipment deployment will be complete | 100 | Network testing will be complete | 42255.5806 | 42255.5806 | 7645 | 7645 | Treasury, New Jersey Department of
NT10BIX5570106 | 2010 | Q4 | Q4 - 2010 | 1026 | 2070 | FALSE | 5 | No variance from baseline | 75 | IRU acquisition | No variance from baseline | 90 | Slight delay due to SHPO final report resulting in the variance | 60 | No variance from baseline | 20 | Baseline is 10 but we think we may be further ahead by the end of the quarter | 20 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2011-02-09 17:32 | 2011-02-09 17:32 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2011 | Q1 | Q1 - 2011 | 2282 | 2886 | FALSE | 4 | Environmental Assessment and dark fiber lease agreement are causing delays with the project moving forward. We are approximately a quarter behind. We are accelerating the State Historical Preservation Office report by providing them with a preliminary survey report. We are also bringing in a project manager that will help us get more accomplished on the tasks. | 100 |  | No variance from baseline | 100 | NA | 90 | Environmental Assessment delays have delayed final approval of the fiber route. We will move ahead with the network design on the preliminary route because the survey results and initial discussions with the Nevada State Department of Transportaion on their right of ways indicate it should be clear for approval | 50 | No variance from baseline | 40 | The node sites haven't been given final approval, so we are slightly behind in getting construction approvals. We anticipate having most of the permitting documentation ready by the end of the quarter. We will have the realty office expedite the permitting as they review the right of way and easements and site approvals. | 25 | There is no variance from the baseline | 3 | Delays with the environmental assessment, construction contract and hiring of the project manager have us slightly behind schedule on procurement. Our efforts should improve as the new project manager will be hired and on board by the middle of this quarter. Finalizing the contract with our primary contractor will be their primary task. The modified EA/six month budget includes all significant construction material, so that will be the first order of business for the contractor. We will have the contractor prepare the procurement orders as we complete the overall construction contract. | 0 | NA | 0 | NA | 0 | NA | 2011-05-24 15:47 | 2011-05-24 15:47 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2011 | Q2 | Q2 - 2011 | 3208 | 3365 | FALSE | 28 | We will be slightly behind overall on the project by the end of the next quarter. However we are expecting significant improvement in meeting our milestones and bringing the project back to the established schedule. | 100 |  | Fiber agreement and appraisal completed. | 100 | No Variance from baseline | 75 | We should have the network designs completed for the outside plant. We are behind due to the contract issues from the prior quarter, so the final network designs for the connections and nodes might not be completed in time to bring us on schedule during this quarter. We are pressuring the attorneys to resolve these contract issues and initiating design discussions with our contractor prior to the finalization of the contract. | 75 | We will have made significant improvement on the rights of way to bring us close to schedule during this quarter, but because we expect to have the final outside plant designs completed near the end of the quarter, that probably isn't enough time for the department of transportation to review and give the clearance before this quarter ends. | 100 | No Variance from baseline | 0 | Because our environmental assessment will be completed just before this quarter ends, we probably won't be able to begin site preparation until the very end of the quarter. | 1 | Although we will not be on schedule with the procurement, we expect to have all the proposals from the vendors for the outside plant materials and equipment. The orders for the materials and equipment will be in process by the end of this quarter. | 20 | No Variance from baseline | 0 | No Variance from baseline | 0 | No Variance from baseline | 2011-08-18 17:30 | 2011-08-18 17:30 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2011 | Q3 | Q3 - 2011 | 4120 | 3903 | FALSE | 27 | The environmental assessment, Cultural survey, Praxis contract, and IRU agreement with level 3 have put us behind. The EA and cultural survey have been completed and submitted. The praxis contract and IRU contract are going before council in the next quarter. We should be able to start procurement and construction in the next quarter. Once we start construction we will be able to get back on track with our spending and developplan to meet the 2/3 rds spending by August 1st 2012. | 0 | true | No variance from baseline | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the high level design completed within 30 days of the signing. | 100 | Complete | 100 | No variance from baseline | 5 | We have identified the locations and are getting the land appraised. Once the contract with Praxis is signed we will begin preparing the sites. | 5 | We are ready to start the outside plant procurement but are waiting for the Praxis contract to be signed. | 5 | We are looking at starting procurement and construction in this quarter. The IRU will give us 40 network miles deployed. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingenton the signing of the Praxis contract. | 0 | No variance from baseline | 2011-11-17 16:53 | 2011-11-17 16:53 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2011 | Q4 | Q4 - 2011 | 5292 | 4958 | FALSE | 27 | The Contract with Praxis is holding up the project. Praxis as of yet has not been able to secure a bond for the project. They are waiting to hear from anotherbonding agent and preparing the waiver request documentation. We expect this to be cleared up in the next quarter. | 100 |  | We are working on correcting the IRU and expect it to be complete in the next quarter. | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the mid level design completed within 30 days of the signing. | 100 | complete | 100 | Complete | 50 | We expect to have the node sites prepared for construction in the next quarter. If the contract with praxis is signed early in the next quarter then we will have the node sites completed. | 25 | We are ready to start the outside plant procurement but are waiting for the Praxis contract to be signed. Praxis has started the Procurement process and as soon as the contract is signed the equipment will begin to be delivered. | 40 | We are expecting the IRU to be completed in the next quarter equating to 40 leased miles. If a bonding waiver is required we will have no new network mile s constructed and subsequently no CAIs connected. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingent the signing of the Praxis contract. | 0 | No Variance from baseline | 2012-02-27 13:33 | 2012-02-27 13:43 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2012 | Q1 | Q1 - 2012 | 6134 | 5669 | FALSE | 23 | The bonding waiver has prevented us from signing the contract, but we expect it to be cleared up in the next early quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the low level design completed within 30 days of the signing. | 100 | Complete | 100 | Complete | 50 | We expect to have the node sites prepared for construction in the next quarter. If the contract with praxis is signed early in the next quarter then we will have the node sites completed. | 25 | We are ready to start the procurement but are waiting for the Praxis contract to be signed. | 15 | We are expecting the IRU to be completed in the next quarter as well as having the contract with Praxis signed. We should see significant progress over the next two quarters. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingent the signing of the Praxis contract. | 0 | No Variance from baseline | 2012-05-16 13:02 | 2012-05-16 13:02 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2012 | Q2 | Q2 - 2012 | 7092 | 6173 | FALSE | 27 | With construction starting next quarter we expect to be caught up with in 2-4 months. | 100 |  | The IRU will be complete in the next quarter | 100 | Complete | 100 | We expect to have the Network design complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 30 | The request for proposals should come in in the next quarter but not completed until the following quarter | 40 | With construction starting we expect the network build to be at least 40% complete. | 25 | We expect to have at least 24 miles deployed this quarter. | 12 | Testing will start in conjunction with the fiber deployment. | 2012-08-15 15:50 | 2012-08-15 15:50 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2012 | Q3 | Q3 - 2012 | 7960 | 6686 | FALSE | 77 | We expect to be approximately seventy seven percent complete by the end of the next quarter. | 100 |  | The IRU and easement will be complete in the next quarter | 100 | Complete | 100 | The outside plant, fiber route, and node engineering is complete. The request for proposal for the inside plant and electronics have been completed and we are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 75 | We are expecting the equipment procurement to begin in the next quarter. The result of the request for proposals have us using Ericsson equipment and the procurement is dependant on the completion of the detailed network design. | 50 | With construction starting we expect the network build to be at least fifty percent complete. | 40 | We expect to have deployed forty percent of the equipment next quarter. | 12 | Testing will start in conjunction with the fiber deployment. | 2012-11-19 16:49 | 2012-11-19 16:49 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2012 | Q4 | Q4 - 2012 | 8808 | 7601 | FALSE | 63 | The late start in construction have us slightly behind but we expect the back bone, 40 miles, to be completed in the next quarter. We are planning on having all of the CAIs' hooked up in the second quarter of 2013. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 100 | The outside plant, fiber route, and node engineering is complete. We are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | We are expecting to complete this in the next quarter | 100 | We are expecting to complete this in the next quarter | 85 | With the project being delayed by the construction start date we are expecting to have only 85 percent deployed in the next quarter. | 50 | We are expecting fifty percent of the testing to be complete by the end of next quarter. | 2013-02-15 15:10 | 2013-02-15 15:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2013 | Q1 | Q1 - 2013 | 9946 | 8517 | FALSE | 94 | The projects late start still has us behind on our baseline data but we are on track to finish the project within the specified grant period. | 100 |  | The sovereign immunity issue has been resolved | 100 | Complete | 100 | We expect this to be completed and installed in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | We expect this to be completed in the beginning of the next quarter | 100 | We are on track to have this completed in the next quarter | 90 | We expect to have a majority of the equipment deployed in the next quarter. | 65 | We are expecting to start the testing in the next quarter. | 2013-05-28 17:10 | 2013-05-28 17:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2013 | Q2 | Q2 - 2013 | 10606 | 8961 | FALSE | 100 | Complete | 100 |  | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-15 12:00 | 2013-08-15 12:00 | 7227 | 7227 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2013 | Q3 | Q3 - 2013 | 11258 | 9419 | FALSE | 99 | We expect project to be online and operational, with complete testing and resolution of minor issues to be resolved. | 100 | NA | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 80 | We expect operational testing to reveal some minor configuration issues | 2013-11-14 19:13 | 2013-11-14 19:13 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2013 | Q4 | Q4 - 2013 | 11884 | 10051 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-02-25 12:33 | 2014-02-25 12:33 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | 2014 | Q1 | Q1 - 2014 | 12290 | 10460 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-06-24 12:37 | 2014-06-24 12:37 | 6703 | 6703 | Pyramid Lake Paiute Tribe
NT10BIX5570107 | 2010 | Q4 | Q4 - 2010 | 938 | 1985 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 85 | N/A | 15 | N/A | 15 | N/A | 20 | N/A | 46 | N/A | 8 | N/A | 5 | N/A | 5 | N/A | 2011-01-30 16:40 | 2011-01-30 16:40 | 6748 | 6748 | Texas A&M University
NT10BIX5570107 | 2011 | Q1 | Q1 - 2011 | 2318 | 2904 | FALSE | 13 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 70 | No Variance | 70 | No Variance | 8 | No Variance | 30 | No Variance | 8 | No Variance | 2 | No Variance | 8 | No Variance | 2011-05-25 17:47 | 2011-05-25 17:47 | 6973 | 6973 | Texas A&M University
NT10BIX5570107 | 2011 | Q2 | Q2 - 2011 | 3192 | 3356 | FALSE | 19 | No Variance | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 95 | Delays due to TxDOT | 95 | San Antonio aerial construction pending receipt of insurance certificate from Verizon. | 16 | Delay due to FONSI approval 06/07/2011 | 30 | Delay due to FONSI approval 06/07/2011 | 7 | Delay due to FONSI approval 06/07/2011 | 2 | Delay due to FONSI approval 06/07/2011 | 7 | Delay due to FONSI approval 06/07/2011 | 2011-08-18 11:52 | 2011-08-18 11:52 | 6973 | 6973 | Texas A&M University
NT10BIX5570107 | 2011 | Q3 | Q3 - 2011 | 4360 | 4036 | FALSE | 27 | No Variance | 0 |  | N/A | 100 | FONSI received 06/07/2011 No modifications | 100 | No Variance | 95 | See Below | 95 | See Below | 35 | See Below | 60 | Engineering modifications negatively impacted procurement | 13 | Engineering modifications and permitting issues negatively impacted schedule | 10 | Procurement of materials has impacted deployment | 10 | Testing follows Deployment | 2011-11-30 17:55 | 2011-11-30 17:55 | 6973 | 6973 | Texas A&M University
NT10BIX5570107 | 2011 | Q4 | Q4 - 2011 | 5182 | 4845 | FALSE | 30 | We will just begin the start of construction for two of the largest fiber segments of the project in mid February. We anticipate an increase in the overall project percentages for this quarter. | 0 |  | N/A | 100 | FONSI received 6/7/2011. No Modifications anticipated. | 100 | No Variance | 95 | We project that 95 percent of the Lease agreements and permits will be executed by the end of the next quarter. All permitting agencies have been contacted and are working through the process with us as our project goes forward. | 95 | All known permitting entities have been contacted for approval. Some governing authorities, such as county commissioners courts, meet at specific intervals to make permitting decisions and this can impact the schedule. We can only anticipate these processes are swiftly passed through the appropriate channels for approvals. We have done due diligence in reaching out and communicating the benefits of the project. | 35 | With the multitude of project sites across the state site preparation is contingent upon permit approvals. We project this projected percent will increase with the start of construction projected in the next quarter. | 80 | Equipment orders have been placed for the majority but not all deployment sites at this time we are projecting 80 percent will be procured by the end of next quarter. | 13 | Projection remains low based on the current construction schedule. | 10 | This projection is based on the number of fiber miles constructed. The largest fiber construction projects will be starting next quarter. | 10 | We cannot improve the projected network testing percentage until we have fiber placed which is progressing at a slower pace than expected, however, will see improvements with the start of the two larger projects next quarter. | 2012-02-21 18:09 | 2012-02-21 18:09 | 6973 | 6973 | Texas A&M University
NT10BIX5570107 | 2012 | Q1 | Q1 - 2012 | 6364 | 5787 | FALSE | 46 | Two additional TxDOT leases executed has allowed us to improve percentage on the overall project. The remaining outstanding permits both City and TxDOT are a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 98 | The remaining outstanding permits both City and TxDOTare a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 98 | The remaining outstanding permits both City and TxDOTare a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 100 | No variance | 75 | Industry wide manufacturer delays for fiber will impact fiber deployment. | 22 | We intend to be in line with the baseline project schedule by February 1, 2013. | 18 | We intend to be in line with the baseline project schedule by March 1, 2013 | 15 | We intend to be in line with the baseline project schedule by March 1, 2013. | 2012-05-31 14:44 | 2012-05-31 14:44 | 6171 | 6171 | Texas A&M University
NT10BIX5570107 | 2012 | Q2 | Q2 - 2012 | 7098 | 6176 | FALSE | 68 | We anticipate completing the majority of both the Stephenville and Texarkana construction. In addition, the TAMU CIS core routers are being installed, all of the access routers are now on order, and the Campbell generator will be installed. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 100 | We anticipate resolution with City of Waco Franchise Agreement | 100 | Resolution with City of Waco andPermit approvals granted thereafter | 100 | No Variance | 80 | Remaining equipment will continue to be ordered in the 30-60 day window prior to deployment for warranty purposes. | 68 | The 70% completion rate will keep us on track for completing by the revised February 2013 date. | 35 | This remains dependent on fiber terminations, testing and specific interconnections being completed. We are aggressively pursuing our established project goals for deployment. | 25 | Network Testing remains dependent on fiber placing/splicing/terminations and will follow a close schedule behind equipment deployment. | 2012-08-15 17:36 | 2012-08-15 17:36 | 6973 | 6973 | Texas A&M University
NT10BIX5570107 | 2012 | Q3 | Q3 - 2012 | 8162 | 6791 | FALSE | 82 | We anticipate 20 additional miles being constructed by 12/31/2012. We anticipate completing both Stephenville and Texarkana. Midplains has begun construction in Canyon, TX schedule for completion during the 4th quarter 2012. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | We anticipate resolution for City of Waco franchise agreement | 100 | Pending permits should follow City of Waco Franchise agreement resolution | 100 | No varaiance | 90 | Remaining equipment will continue to be ordered in the 30-60 day window prior to deployment for warranty purposes. | 80 | The 80% completion rate will keep us on track for completing by the revised February 2013 date. | 50 | This remains dependent on fiber terminations, testing and specific interconnections being completed. We are aggressively pursuing our established project goals for deployment. | 50 | Network Testing remains dependent on fiber placing/splicing/terminations and will follow a close schedule behind equipment deployment. | 2012-11-29 19:54 | 2012-11-29 19:54 | 6186 | 6186 | Texas A&M University
NT10BIX5570107 | 2012 | Q4 | Q4 - 2012 | 8958 | 7733 | FALSE | 74 | We anticipate a large portion of the construction on the remaining project sites to be completed by the end of Q1 2013. These include Texarkana, Waco, the remainder of West Texas A&M University in Canyon, Tx, (5.6 miles total: 2.7 Waco; 2.96 WTAMU) | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | We anticipate resolution for City of Waco franchise agreement. | 100 | Pending permits should follow City of Waco Franchise agreement resolution. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 40 | No variance | 2013-02-25 19:19 | 2013-02-25 19:19 | 6186 | 6186 | Texas A&M University
NT10BIX5570107 | 2013 | Q1 | Q1 - 2013 | 9920 | 8501 | FALSE | 100 | During Q2 2013 we will place 2.17 miles of fiber in Waco and 1.7 miles in Texarkana, wrapping up all fiber placement for the project. Once fiber is placed, we will pursue completion of network build and network testing. We anticipate 150.82 total miles upon project completion. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | The final rights of way issue, the franchise agreement with Waco will be fully executed during 2nd Qtr 2013, to be immediately following by construction, fiber placement, splicing/ termination. | 100 | Permits follow franchise agreement with City of Waco | 100 | No variance | 100 | No variance | 90 | Delays due to third party dependencies negative 10% variance | 100 | No variance | 90 | Delays due to third party dependencies negative 10% variance | 2013-05-28 11:00 | 2013-05-28 11:00 | 6777 | 6777 | Texas A&M University
NT10BIX5570107 | 2013 | Q2 | Q2 - 2013 | 10812 | 9078 | FALSE | 98 | According to the Budget Execution Details section, we plan to expend 98% of your overall budget by the end of next quarter. The Overall Project Milestone has been updated to reflect planned expenditures. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | The final rights of way issue, and agreements with Waco were fully executed during 2nd Qtr 2013, construction, fiber placement, splicing/ termination to be complete during Q3 2013. | 100 | Permits issued Traffic control plans approved for construction start July 2013. | 100 | No Variance | 100 | No Variance | 100 | There is a negative 10% variance from the baseline. | 100 | No Variance | 100 | There is a negative 10% variance from the baseline. | 2013-08-29 15:39 | 2013-08-30 22:55 | 6186 | 6186 | Texas A&M University
NT10BIX5570107 | 2013 | Q3 | Q3 - 2013 | 12002 | 10166 | FALSE | 100 | No Variance | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-03-28 12:31 | 2014-03-28 12:31 | 6186 | 6186 | Texas A&M University
NT10BIX5570108 | 2010 | Q4 | Q4 - 2010 | 1232 | 2262 | FALSE | 3 | No variance | 6 | Administrative | No variance | 100 | No variance | 15 | No variance | 2 | No variance | 0 | NA - included in 2h Network Build | 1 | No variance | 8 | No variance | 0 | No variance | 0 | No variance | 0 | NA. Using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-02-18 17:08 | 2011-02-18 17:08 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2011 | Q1 | Q1 - 2011 | 1926 | 2708 | FALSE | 8 | Target 6%. CMS anticipates being slightly ahead of schedule as a result of faster than anticipated progress with leased fiber IRUs and Rights of Way. Last quarter CMS secured one leased fiber IRU ahead of schedule and has signed a second that will be recorded as an expenditure in the next quarter. The engineering firm is progressing faster than expected on researching and preparing Rights of Way permits. More details on these two activities are covered below. | 9 |  | Target 10%. Costs for office equipment were lower then expected and project staff started later then expected. | 92 | Target 100%. The final environmental assessment report was submitted in April and a FONSI received was received April 22. We are anticipating the final costs for the environmental report and analysis will be about $70,000 lower then budgeted; however, SHPO has requested unanticipated archeological surveys in select areas. The remaining Environmental Assessment funds plus cost savings from other areas will be needed for the surveys. We are awaiting a final cost estimate before re-budgeting. | 32 | Target 35%. The costs for Network Design are looking to be less than anticipated which is reflected in the 3% difference between the targeted amount in the project baseline and the new projection for the next quarter. We anticipate the difference between the budgeted amount and revised projection to be used for the archeological surveys. We are on track to complete detailed design on 25% of the backbone and 25% of the lateral network miles. | 15 | Target 2%. The project baseline included conservative targets during the first year as we were unsure of the time needed for this milestone. The engineering firm is making better progress than anticipated in researching and preparing right of way/easement requests. | 0 | NA | 11 | Target 11%. Most of the effort for this milestone is focused on preparing network Point of Presence (POP) sites to support the optical equipment. | 25 | Target 26%. The variance is due to equipment costs coming in slightly lower then expected. | 3 | Target 0%. CMS has secured new fiber lease agreements sooner then anticipated. This will allow us to light a major route between Collinsville to Chicago sooner then projected. | 0 | Target 0% | 0 | NA | 2011-05-10 13:45 | 2011-05-10 13:45 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2011 | Q2 | Q2 - 2011 | 3082 | 3298 | FALSE | 10 | Baseline target is 12%. The construction phase has been delayed by about 30 days due to the rebidding of the solicitation. Contracts have been awarded and construction will be starting in this quarter. | 15 |  | Baseline target is 21%. Costs mapped to this milestone will need to be re-budgted as the original budget included costs associated with annual maintenance for leased fiber which is an ineligible cost. | 100 | Baseline target is 100% Actually projecting 109% due to anticipated CAI and tower location changes that will require changes/additions to the approved Environmental Assessment. | 36 | Baseline target is 55%. Actual project activity is tracking as planned; however, we overestimated the rate of spend in the baseline. By the end of next quarter we expect to have completed detailed design for 50% of the network miles. | 27 | Baseline target is 2%. The engineering firm is making faster than anticipated progress on researching and preparing right of way permits. CMS established conservative targets through Y2Q2 with all Rights of way permits to be completed by Y2Q3. As the project is moving forward we have better insight into the time needed for this activity and have adjusted our forecasts accordingly. | 0 | NA | 6 | Baseline target is 36%. The projected milestone target is behind the baseline target due to unanticipated contract amendments with landlords. Since most of the POP sites are leased facilities, the power upgrades need to be performed by the landlords. The current contracts do not address how CMS will pay the landlord for these costs so legal counsel has been working with the landlord to amend the contracts. An engineering assessment is needed at another State facility POP location to determine the overall electrical needs. CMS is working with the engineering firm to initiate that study by the end of the quarter. Actual spend for the electrical upgrades at the leased sites and State facility is not anticipated to occur until 2011Q4. The delay does not have an impact on the overall project timeline as the critical path is the fiber construction. The electrical work will continue in parallel with the fiber construction. | 33 | Baseline target is 26%. We are moving forward with ordering and installing equipment for the leased fiber miles as well as the new construction routes. We are beginning to stage the orders and installations for the optical equipment. | 3 | Baseline target is 5%. The construction phase has been delayed by about 30 days due to the rebidding of the solicitation. Contracts have been awarded and construction will be starting in this quarter. | 0 | 0 | 0 | NA | 2011-08-15 13:49 | 2011-08-15 13:49 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2011 | Q3 | Q3 - 2011 | 4024 | 3852 | FALSE | 13 | Baseline target is 20%. The variance is a combination of delays with Rights of Way, Site Preparation and Network Build activities. More details on the cause of the delays and the impact to the overall project timeline are described in the respective Milestone Categories below. | 35 | Professional services such as Project Management, Web Design, Project Engineering | Baseline target is 31%. The 35% projection reflects the re-budgeting of the easement activities to the Administrative and Legal budget line which is reflected in the Other milestone category. | 100 | Baseline target is 100%. No variance. | 68 | Baseline target is 70%. We are expecting to have all network design activities complete by the end of the quarter; however, all invoices for the complete activity will not be received until January. | 24 | Baseline target is 100%. Permits are taking longer then anticipated; however, they are not impacting construction activities at this time. We will likely be behind this baseline for several quarters as the majority of the budgeted permitting fees will be paid to the Illinois Department of Transportation and are expected to be paid through a single Intergovernmental Agreement. This Agreement will likely not be finalized until after the majority of the permits are issued. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 7 | Baseline target is 36%. As reported earlier, POP site upgrades have been delayed due to contract amendments with the site landlords, contract for electrical upgrades, and an engineering assessment. The POP site amendments and contract for electrical upgrades have been finalized and work is beginning. The engineering assessment is underway. This delay is not impacting the overall schedule as these activities are happening in parallel with the fiber construction. | 45 | Baseline target is 26%. CMS is ahead of schedule in lighting leased fiber. We are working to stage and distribute equipment as POP sites are ready. This approach enables a quicker turn-up of leased and built fiber. We are also able to use in house staff instead of contractors which is resulting in a cost savings. | 4 | Baseline target is 13%. Now that construction contracts are established, we expect to see increased activity for network build. While construction activities will start during this quarter, significant expenditures will likely not be recognized until after the first of the year due to the delay in completing the activity and processing vendor payments. | 5 | Baseline target is 30%. CMS originally anticipated utilizing contractual services for equipment deployment. So far, we are using in-house staff that are not billed to the project. The savings will be rebudgeted to another milestone category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-11-14 13:13 | 2011-11-14 13:13 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2011 | Q4 | Q4 - 2011 | 4996 | 4669 | FALSE | 19 | Baseline target is 42%. The difference is primarily due to the unanticipated time to complete the Environmental Assessment. See details below. | 33 | Professional Services such as Project Management, Web Design, Project Enginer | Baseline target is 40%. The majority of the funds budgeted to this milestone are for contractual resources. The shortfall is due to delays on boarding resources earlier in the project. | 96 | Baseline target is 100%. This past quarter we reallocated money to this budget item to cover future costs associated with an amendment to the Environmental Assessment for necessary route modifications. The budgeted amount increased from $920,322 to $984,627. | 85 | Baseline target is 100%. In working with our sub recipient, we have a identified they will be a little behind schedule. We anticipate completing all design activities by the end of next quarter. Because of the billing cycle we project about $700,000 will not be paid until the following quarter resulting in a 15% shortfall of the baseline. | 38 | Baseline target is 100%. Due to the longer then anticipated time for the Environmental Assessment process, permits and rights of way activities are behind what was targeted in the baseline. Permits and rights of way requests have been requested or approved for 56% of the new construction miles. Right of Way fees are primarily charged by the rail roads. The final costs will likely be less then the budgeted amount. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 9 | Baseline target is 61%. Nearly half of this milestone category is for an in kind contribution of space for network equipment within the sub recipient's portion of the project. CMS originally anticipated this space would be secured and booked to the project at this point in the project; however, in working with the sub we're forecasting this activity will occur in Q2-2012. | 68 | Baseline target is 46%. CMS is ahead of schedule in lighting leased fiber. We have purchased most of the optical equipment and have deployed it to the network node sites. This approach enables a quicker turn-up of leased and built fiber. We have also used in house staff instead of contractors which has resulting in a cost savings that will be reinvested in the project. | 6 | Baseline target is 35%. Construction on the first network span started in November. While construction is starting later then anticipated in the baseline we are forecasting completion in Q4-2012 which would be ahead of schedule. We have condensed the construction schedule by utilizing 4 vendors with multiple crews working simultaneously on the 12 network spans. Most, if not all, network spans will be under construction by the end of the next quarter. | 5 | Baseline target is 40%. CMS originally anticipated utilizing contractual services for equipment deployment. So far, we are using in-house staff that are not billed to the project. We are forecasting a savings of $500,000 of the $1,050,000 budgeted to this milestone. The savings will be re-budgeted to another milestone category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to the project plus contractual resources reported in 2k Other. | 2012-02-14 11:33 | 2012-02-14 11:33 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2012 | Q1 | Q1 - 2012 | 6010 | 5604 | FALSE | 32 | Baseline target is 68%. The revised project schedule set a target of 33%. Fiber deployment is behind for a variety of reasons including unanticipated time needed for the Environmental Assessment, delays finalizing construction contracts, and fiber delivery delays. CMS has developed a revised project schedule considering all these factors. The revised schedule demonstrates completion by year three. The forecast for next quarter is $543,988 less then the revised forecast which is less then 1%. | 49 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 46%. The revised project schedule set a target of 49%. Forecasted cumulative spend is $789,042 of $1,613,923. | 98 | Baseline target is 100%. The revised project schedule set a target of 99%. The forecasted cumulative spend is $984,883 of $1,007,144. The EA is complete and a FONSI received. Any additional spend in this milestone category will be associated with route changes. | 77 | Baseline target is 100%. The revised project schedule set a target of 94%. The forecasted cumulative spend is $3,756,690 of $4,904,937. The network design for outside plant is complete. Spend for two of the three pending route changes is expected to be less then anticipated. | 54 | Baseline target is 100%. The revised project schedule set a target of 88%. The forecasted cumulative spend is $586,449 of $1,076,929. The revised project schedule forecasted spend included $200,000 for A/E on site observations which should have been mapped to the Network Build milestone. Based on this correction, the revised project scheduled target for this quarter is 69%. This leaves a difference of $156,693. Costs for the remaining permit preparation is coming in at a cost lower then expected as are overall permit fees. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 8 | Baseline target is 61%. The revised project schedule set a target of 8%. Forecasted cumulative spend is $308,362 of $3,797,000. | 68 | Baseline target is 46%. The revised project schedule set a target of 71%. Forecasted cumulative spend is $8,041,408 of $11,881,943. The variance is $412,401 and attributable to optical cards that require fiber characterizations for pending fiber leases before ordering. | 23 | Baseline target is 70%. The revised project schedule set a target of 22%. The forecasted cumulative spend is $16,486,416 of $71,400,252. CMS is expecting construction activities to meet or exceed the forecasted target. | 7 | Baseline target is 60%. The revised project schedule set a target of 7%. Forecasted cumulative spend is $51,864 of $699,901. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-05-10 12:49 | 2012-05-10 12:49 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2012 | Q2 | Q2 - 2012 | 7134 | 6194 | FALSE | 47 | Baseline target is 72%. The revised project schedule set a target of 55%.The forecast for next quarter is $7,814,330 less then the revised forecast as a result of costs coming in below budget for network design, rights of way, and construction and delays with construction, inside plant and final equipment purchases. | 58 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 52%. The revised project schedule set a target of 63%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 98 | Baseline target is 100%. The revised project schedule set a target of 99%. The EA is complete and a FONSI received. The remaining funds may be used for EA work associated with pending and future route change requests. | 81 | Baseline target is 100%. The revised project schedule set a target of 98%. All design work for the fiber routes are complete and paid. The sub recipient anticipates completing the design work for wireless towers and inside plant at the end of next quarter, although some of the payments may lag into the following quarter. Any additional spend for this category will be associated with routes changes. | 83 | Baseline target is 100%. The revised project schedule set a target of 97%. 90% of the permits and easements have been secured. Projected cumulative spend for next quarter is $890,796 of $1,076,929. CMS estimates the final costs will be about 10% ($100k) below the budgeted amount. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 20 | Baseline target is 61%. The revised project schedule set a target of 37%. CMS anticipated completing inside plant work for 25 CAIs by this point in the project. The time required to finalize the scope of work, secure vendor quotes, place orders, receive materials and complete the work is taking longer then anticipated. CMS has started placing orders; however, we do not anticipate payments for inside plant work to start until Y3Q2. | 71 | Baseline target is 46%. The revised project schedule set a target of 78%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. We had planned to purchase the remaining 3 optical switches in this quarter but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. The sub recipient anticipates awarding bids for generators, wireless equipment, servers, racks and fiber panels in this quarter but invoices will carry over to the following quarter. | 40 | Baseline target is 75%. The revised project schedule set a target of 48%. The revised project schedule anticipated spending an additional $1.1M for fiber leases and $4M for construction. One of the leases is executed and payment is pending fiber acceptance. Bids have been accepted for three additional leases and contracts are in negotiations. The remaining lease will be with another governmental entity and is in contract review. Construction spending for next quarter will be less then anticipated as work on 3 routes started late. The run rate for these routes will not have reached the forecasted level. Additionally constructions costs are coming in below budget. | 5 | Baseline target is 75%. The revised project schedule set a target of 18%. $600,000 is budgeted to this milestone for fiber characterization by the optical equipment vendor. CMS is waiting to take receipt of a 3 mile leased fiber path from the owner at which time the optical vendor will be deployed to complete the work. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-08-17 17:46 | 2012-08-17 17:46 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2012 | Q3 | Q3 - 2012 | 7930 | 6669 | FALSE | 64 | Baseline target is 81%. The revised project schedule set a target of 70%.The forecast for next quarter is $6.4M less then the revised forecast as a result of delays starting construction, construction costs coming in below budget, and delays starting inside plant. | 69 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 62%. The revised project schedule set a target of 70%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 100 | Baseline target is 100%. The revised project schedule set a target of 99%. The EA is complete and a FONSI received. CMS will have additional costs for EA work associated with a pending route change, if approved. | 81 | Baseline target is 100%. The revised project schedule set a target of 98%. All design work for the fiber routes are complete and paid. The sub recipient anticipates design work for inside plant will continue through the first quarter of 2013. CMS will have additional costs for design work associated with a pending route change, if approved. | 100 | Baseline target is 100%. The revised project schedule set a target of 97%. 95% of the permits have been secured. CMS is forecasting to spend more then originally budgeted for this milestone due to permitting work associated with route changes and higher then anticipated permit fees from railroads. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 44 | Baseline target is 80%. The revised project schedule set a target of 73%. CMS anticipated completing inside plant work for 50% of CMS' CAIs by this point in the project (new target is 30%). The time required to finalize the scope of work, secure vendor quotes, place orders, receive materials and complete the work is taking longer then anticipated. Inside plant work has started and will continue through the remainder of the project. | 71 | Baseline target is 46%. The revised project schedule set a target of 90%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. CMS had planned to purchase the remaining 3 optical switches by now but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. The sub recipient anticipates ordering wireless equipment and generators in this quarter but invoices will carry over to the following quarter. | 62 | Baseline target is 85%. The revised project schedule set a target of 64%. Construction spending for next quarter is approximately $1.7M below the revised target. The difference is partially attributable to delayed starts with several routes, but mainly a result of lower then budgeted construction costs for the early fiber routes. As of the end of September, 76% of the conduit is complete and 30% of the fiber which puts the project on schedule to be completed by the grant deadline. | 6 | Baseline target is 90%. The revised project schedule set a target of 28%. $600,000 of the $699,000 budgeted to this milestone is for fiber characterization by the optical equipment vendor. CMS is waiting to take receipt of a 3 mile leased fiber path from the owner at which time the optical vendor will be deployed to complete the work. In the meantime, CMS is in process of purchasing the tools to perform this work internally. Depending on timing, CMS may not require the services of the optical equipment vendor. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-11-16 15:39 | 2012-11-16 15:39 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2012 | Q4 | Q4 - 2012 | 9056 | 7831 | FALSE | 72 | Baseline target is 81%. The difference between the Baseline and the PPR projection is approximately $22 million which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. | 78 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 81%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient has reassigned these duties to existing resources which will result in overall lower spend for this milestone. | 100 | Baseline target is 100%. The EA is complete and a FONSI received. CMS will have additional costs for EA work associated with a recently approved route change and a pending route exapansion, if approved. | 88 | Baseline target is 100%. All design work for the fiber routes is complete and paid. The sub recipient has completed the design work for wireless towers and inside plant but has not yet received all the invoices. Any additional spend for this category will be associated with routes changes. | 83 | Baseline target is 100%. CMS has secured 99% of the permits. Additional charges will be associated with permit preparation/fees for the pending route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 62 | Baseline target is 100%. Inside plant work started later then originally planned but is underway and making good progress. This milestone category included $1.5M for network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. The sub recipient is completing a third party assessment to validate the value of the space. | 78 | Baseline target is 100%. CMS has purchased and installed about 86% of the optical, switching and routing equipment. The sub recipient has ordered the wireless equipment and generators in this quarter but invoices will carry over to the following quarter. | 71 | Baseline target is 95%. Construction activities started later then expected. Costs of the early routes have been lower then budgeted. By the end of the quarter CMS is forecasting to have 75% of the fiber installed. | 7 | Baseline target is 100%. The money budgeted to this milestone is for fiber characterization by the optical equipment vendor. CMS is in process of purchasing the tools to perform this work internally. CMS anticipates that the remaining money budgeted for Equipment Deployment will be reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-02-28 11:04 | 2013-02-28 11:04 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2013 | Q1 | Q1 - 2013 | 10008 | 8548 | FALSE | 80 | Baseline target is 100%. The difference between the Baseline and the PPR projection is approximately $19M which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. CMS has received approval to add additional routes and will be working on those routes/CAIs through the remainder of the project. | 59 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. | 100 | Actual spend is 120% due to higher engineering costs required to complete the EA. | 90 | Baseline target is 100%. All design work for the original scope is complete and paid. Any additional spend for this category will be associated with design work for the recently approved route changes. | 100 | Actual spend is 107% due to higher engineering costs required to complete permits. Additional charges will be associated with permit preparation/fees for the recently approved route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 52 | Baseline target is 100%. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. | 95 | Baseline target is 100%. CMS will have additional spend for customer premise equipment associated with recently approved route changes/CAI additions; however, we anticipate final costs will be less than budgeted. | 84 | Baseline target is 100%. By the end of the quarter CMS is forecasting to have 99% of the fiber installed; however, vendor payments will continue into the third quarter of 2013. CMS will be requesting an extension to complete the recently approved Chicago reroute and to continue with the approved expansion routes/CAIs. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-05-30 13:24 | 2013-05-30 13:24 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2013 | Q2 | Q2 - 2013 | 10822 | 9083 | FALSE | 95 | Baseline target is 100%. CMS has completed 99% of the construction at the start of the quarter. CMS will complete the remaining scope plus several miles of expansion routes by the end of the quarter. CMS anticipates that some of the construction activity will continue through late September pushing payment of final invoices into the close out period. | 79 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. The remaining funds will be spend in the other milestone categories where expenses have been higher than originally forecasted. | 100 | Actual spend is 123% due to higher engineering costs required to complete the EA. | 100 | Actual spend is 102% as result of design work for route changes and expansion routes. | 100 | Actual spend is 124% due to higher engineering costs required to compelte permits for original scope as well as the additional work for route changes and expansion routes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 73 | Baseline target is 100%. CMS will not spend the amount originally budgeted for Site Preparation. The remaining funds will be spend in the other milestone categories where expenses have been higher than originally forecasted. | 97 | Baseline target is 100%. CMS anticipates a few final invoices received at the end of the quarter which will push the payments into the close out period. | 97 | Baseline target is 100%. CMS anticipates that some of the construction activity will continue through late September pushing payment of final invoices into the close out period. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-08-30 14:13 | 2013-08-30 14:13 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2013 | Q3 | Q3 - 2013 | 11390 | 9503 | FALSE | 99 | Baseline target is 100%. The remaining funds are budgeted for eligible close out expenses that will be incurred after December 2013. | 86 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. The remaining funds will be spent in other milestone categories where expenses have been higher than originally forecasted. | 100 | Final spend is forecasted to be 123% due to higher engineering costs required to complete the EA. | 100 | Final spend is forecasted to be 102% as result of design work for route changes and expansion routes. | 100 | Final spend is forecasted to be 129% due to higher engineering costs required for permits. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 60 | Baseline target is 100%. CMS will not spend the amount originally budgeted for Site Preparation. The remaining funds will be spent in the other milestone categories where expenses have been higher than originally forecasted. | 100 | Final spend is forecasted to be 135% due to upgrading some of the optical equipment from 40G to 100G. | 97 | Baseline target is 100%. Final spend is forecasted to be 97% due to overall lower than originally budgeted construction costs. The remaining funds will be spent in other milestone categories where expenses have been higher than originally forecasted. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and will not have additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-11-26 13:16 | 2013-11-26 13:16 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570108 | 2013 | Q4 | Q4 - 2013 | 12468 | 10647 | FALSE | 100 | None | 100 | Professional Services such as Project Management, Web Design, Project Engineer | None | 100 | None | 100 | None | 100 | None | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 100 | None | 100 | None | 100 | None | 100 | None | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2014-08-28 17:24 | 2014-08-28 17:24 | 6095 | 6095 | Central Management Services, Illinois Department of
NT10BIX5570109 | 2010 | Q4 | Q4 - 2010 | 984 | 2027 | FALSE | 3 | N/A | 0 |  | N/A | 100 | N/A | 50 | N/A | 100 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-04 17:15 | 2011-02-04 17:15 | 6173 | 6173 | Carver, County of
NT10BIX5570109 | 2011 | Q1 | Q1 - 2011 | 1958 | 2724 | FALSE | 8 | N/A |  |  |  | 100 | N/A | 100 | N/A | 100 | N/A | 75 | N/A | 0 | N/A | 0 | N/A | 4 | N/A | 0 | N/A | 0 | N/A | 2011-05-12 07:57 | 2011-05-12 07:57 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2011 | Q2 | Q2 - 2011 | 3382 | 3454 | FALSE | 20 | We will be adding construction crews to the project in efforts to regain lost progress from the previous quarters. We will also be working further into the fourth quarter fall/winter construction season, as weather permits, to regain lost progress. | 0 |  | N/A | 100 | No variance from baseline as this task was completed in the current quarter. | 100 | No variance from baseline. We look to meet this completion percentage by adding engineering resources to the project to regain lost progress from the previous quarter. | 100 | No variance from baseline. We look to meet this completion percentage once we receive final sign off of our EA addendum in this next quarter. | 100 | No variance from baseline. We look to meet this completion percentage by adding engineering resources, which will finalize network design, allowing for permitting to be completed. | 25 | No variance from baseline. We look to meet this completion percentage by beginning initial groundwork for the construction of our first fiber hut. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 0 | With fiber scheduled for delivery in the 4th quarter of 2011, we are currently working to install conduit and once fiber arrives, we will regain lost progress of our network build by blowing in fiber and splicing after the conduit is in place. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 2011-08-30 15:07 | 2011-08-30 15:07 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2011 | Q3 | Q3 - 2011 | 3912 | 3794 | FALSE | 64 | No variance from baseline |  |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 50%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 20 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 20%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2011-11-07 16:10 | 2011-11-07 16:10 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2011 | Q4 | Q4 - 2011 | 4980 | 4654 | FALSE | 60 | Our overall project is at 60%, which is less than our originally stated 63%. This lower percentage is based on our anticipation of not receiving the final shipments of our fiber until April of 2012, at which time the expenditures will be reported. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 75%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 40 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 40%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2012-02-13 15:12 | 2012-02-13 15:12 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2012 | Q1 | Q1 - 2012 | 6266 | 5735 | FALSE | 74 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 85 | Our construction permits and other approvals is at 85%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 50 | Our site preparation is at 50%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 60 | No variance from baseline | 0 | Our equipment deployment is at 0%, which is less than our originally stated 68%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2012-05-23 13:51 | 2012-05-23 13:51 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2012 | Q2 | Q2 - 2012 | 7270 | 6262 | FALSE | 86 | Our overall project is at 86%, which is less than our originally stated 90%. Based on our equipment procurement not taking place until late summer, the expense for equipment will not be fully incurred until 4th quarter 2012. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 80 | No variance from baseline | 84 | No variance from baseline | 80 | No variance from baseline | 0 | No variance from baseline | 2012-08-28 17:17 | 2012-08-28 17:17 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2012 | Q3 | Q3 - 2012 | 8012 | 6712 | FALSE | 90 | Our overall project is at 90%, which is less than our originally stated 99%. This is created by our equipment procurement not taking place until this quarter and the finalizing of the network build out so that we can pay our construction retainage. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 94 | No variance from baseline | 90 | Our overall project is at 90%, which is less than our originally stated 100%. This is created by our equipment procurement not taking place until this quarter. | 0 | No variance from baseline | 2012-11-21 10:52 | 2012-11-21 10:52 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2012 | Q4 | Q4 - 2012 | 9082 | 7855 | FALSE | 96 | Our overall project is at 96%, which is less than our originally stated 99%. This is created by our equipment procurement not taking place until this quarter and the finalizing of the network build out so that we can pay our construction retainage. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 31 | Our equipment procurement is at 31%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid. The equipment will be arriving late this quarter and billing is not anticipated to be received until next quarter when the expenditure will be realized. | 100 | No variance from baseline | 90 | Our overall project is at 90%, which is less than our originally stated 100%. This is created by our equipment procurement not taking place until this quarter. | 50 | No variance from baseline | 2013-02-28 14:29 | 2013-02-28 14:29 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2013 | Q1 | Q1 - 2013 | 9298 | 8102 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-04-26 16:28 | 2013-04-26 16:28 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2013 | Q2 | Q2 - 2013 | 10752 | 9041 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-08-27 09:46 | 2013-08-27 09:46 | 7020 | 7020 | Carver, County of
NT10BIX5570109 | 2013 | Q3 | Q3 - 2013 | 11602 | 9729 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-01-14 10:43 | 2014-01-14 10:43 | 7020 | 7020 | Carver, County of
NT10BIX5570111 | 2010 | Q4 | Q4 - 2010 | 758 | 1792 | FALSE | 2 | Based on anticipation of the Environmental Assessment being completed and progress in the permitting area, Northwest Open Access Network will be closer to 2% complete with the Overall Project Milestone. | 0 | N/A | N/A | 100 | N/A | 35 | N/A | 15 | N/A | 5 | N/A | 5 | N/A | 10 | Equipment expenditures will more than likely fall into the following quarter, therefore not reflected in this baseline milestone. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 14:07 | 2011-01-28 14:07 | 5529 | 5529 | Northwest Open Access Network
NT10BIX5570111 | 2011 | Q1 | Q1 - 2011 | 2000 | 2745 | FALSE | 1 | Expenditures do not meet the anticipated Baseline, since the original forecast included equipment purchases during the early stages of the project. Timeline delays due to finalizing the project budget with the NTIA Program Office has pushed back execution of sub recipient agreements and equipment purchases to better align with plant construction timelines. NoaNet will manage completion of the overall project metrics by increasing resources in the compressed schedule. | 0 | N/A | N/A | 100 | No variance. | 45 | No variance. | 20 | Initial variance to milestone will gradually dissipate as the project progresses. Initial delays in the project caused the milestone to be short of anticipated projections. The project is expected to meet this milestone by end of year two of the project by adding additional resources to the task. | 20 | It is anticipated permitting will achieve the anticipated project timeline included in the baseline by the end of 2011. As stated above, initial delays caused permitting to lag initial projections. Additional resources will be deployed to close the gap by end 2011. | 5 | Site preparation varies from the baseline as the project awaits the receipt of the FONSI (Finding of No Significant Impact). Original projections anticipated this metric to be further along, once again, additional resources will be deployed to gain ground by end of year two of the project timeline. | 10 | Equipment procurement initially planned will be delayed due to initial delays in acceptance of the award. We anticipate this milestone to be attained late in 2011. | 0 | No variance. | 0 | Equipment will not be deployed until the third or fourth quarter. We anticipate reaching our baseline projection by end of 2011. | 0 | No variance. | 2011-05-13 09:27 | 2011-05-13 09:27 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2011 | Q2 | Q2 - 2011 | 2586 | 3041 | FALSE | 20 | When the anticipated approval of the In Kind Asset for Land and Equipment is received, the overall progress of the project will surpass the Baseline projections. | 0 | NA | NA | 100 | No variance. | 60 | No variance. | 25 | Rights of Way will lag an aggressive Baseline projection well into this year. Anticipation was that the Environmental process would not take as much time and the process would have began sooner. | 30 | See comment above in reference to permitting. | 20 | Site preparation is scheduled to start in this quarter with an accelerated timeline. Completion of this particular milestone will fall into the final year of the project and may not attain the Baseline projection until final completion. | 75 | Approval of In Kind assets will drive this metric beyond the original Baseline projections. Assets booked to the project and implemented into the Network will be attributable towards the build. | 0 | Earlier Baseline projections had Network Build starting in the first quarter of year two of the project. However, as a result of the longer than anticipated Environmental process, this metric will not start until the following quarter. | 75 | As In Kind Assets are allowable to the Project, Equipment in place will be deployed. | 0 | Network testing will follow the Network Build Metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by end of year two of the Project. | 2011-07-28 11:02 | 2011-07-28 11:02 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2011 | Q3 | Q3 - 2011 | 4220 | 3958 | FALSE | 21 | With the addition of In Kind assets to the project, the gap in actual to Baseline has shortened, bringing the milestone closer to projection. NoaNet will exercise all available resources to complete the project as outlined in the Broadband Technologies Opportunity Program guidelines. Over 67% of the project budget is in the Construction Category of which has not begun. Spending 1% or $7,799,890 ($650,000 weekly) in one quarter at this stage of the project is difficult to reach. Non ground disturbing activities account for the majority of the work being completed on the project until FONSI is received. It is anticipated that we will be ready to proceed and expenditures will escalate into 2012. | 0 |  | N/A | 100 | No Variance. | 75 | No Variance. | 35 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 40 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 20 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 40 | In Kind asset approval was received and the majority of it has been attributed toward this project last quarter, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the second quarter of 2012 to coincide with the start of construction. | 0 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 0 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2011-11-22 14:42 | 2011-11-22 14:42 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2011 | Q4 | Q4 - 2011 | 5396 | 5079 | FALSE | 22 | With the addition of In Kind assets to the project, the gap in actual to Baseline has shortened, bringing the milestone closer to projection. NoaNet will exercise all available resources to complete the project as outlined in the Broadband Technologies Opportunity Program guidelines. Over 67% of the project budget is in the Construction Category of which has not begun. It is anticipated that we will be ready to proceed and expenditures will escalate in 2012 in order to meet the projected metrics by the end of Q4 2012. | 0 |  | N/A | 100 | Meeting Baseline projection. | 85 | No Variance. | 65 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 35 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 26 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the second quarter of 2012 to coincide with the start of construction. | 5 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 0 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2012-02-29 13:19 | 2012-02-29 13:19 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2012 | Q1 | Q1 - 2012 | 6016 | 5607 | FALSE | 23 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on to the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No variance. | 90 | No variance. | 65 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 45 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 26 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 5 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 10 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2012-05-10 14:01 | 2012-05-10 14:01 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2012 | Q2 | Q2 - 2012 | 6610 | 5922 | FALSE | 32 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on in the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No Variance. | 90 | Network design is nearing completion with final adjustments taking place in Q4 2012. | 70 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of Q1 2013. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter four of year 2012. Once again, additional resources will be deployed to expedite the process. | 60 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter one in 2013. | 32 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 10 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter one 2013. | 32 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter one 2013. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2012-07-30 11:43 | 2012-07-30 11:43 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2012 | Q3 | Q3 - 2012 | 7928 | 6668 | FALSE | 50 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on in the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No Variance. | 95 | No Variance. | 80 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of Q1 2013. | 75 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter four of year 2012. Once again, additional resources will be deployed to expedite the process. | 80 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter one in 2013. | 62 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 34 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter one 2013. | 55 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter one 2013. | 20 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2012-11-16 14:41 | 2012-11-16 14:41 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2012 | Q4 | Q4 - 2012 | 8796 | 7592 | FALSE | 71 | With the two categories of construction and equipment accounting for 87% of the budget, WE WILL SEE A LARGE INCREASE IN THE METRIC AS CONSTRUCTION IS IN FULL OPERATION AND EQUIPMENT PURCHASES ARE BEING COMPLETED. WITH THE TWO METRICS ABOVE EXPENDING LARGER AMOUNTS OF ITS BUDGET, DOUBLE DIGIT INCREASES WILL NOT BE UNCOMMON FOR THIS METRIC. It is projected to meet our baseline metric at the end of Q2 2013. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 90 | Rights of Way are still in process of being secured for some routes and will be forecasted to be complete by Q2 2013. | 85 | A minimal number of permits will need to be obtained going into the final quarter of the project timeline. This metric will be met at the end of Q2 2013. | 90 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter two in 2013. | 64 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q2 2013. | 38 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter two 2013. | 55 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter two 2013. | 50 | Network testing will follow the network build metric now that construction of routes has started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2013-02-14 23:15 | 2013-02-14 23:15 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2013 | Q1 | Q1 - 2013 | 9910 | 8496 | FALSE | 70 | With the two categories of construction and equipment accounting for 87% of the budget, we will continue to see a large increase in the metric as construction is in full operation and equipment purchases are being completed. With the two metrics above expending larger amounts of it's budget,double digit increases will not be uncommon for this metric. It is projected to meet our baseline metric during the final quarter of the project. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | Site preparation will continue into July, the final month of the project, as some remaining work will be needed on the routes finishing up that month. | 51 | With the In Kind equipment having been attributed toward this project in previous quarters, this metric will continue to lag into the remaining quarter of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated meeting our baseline projections at the end of the project timeframe. | 72 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of the project life cycle in July 2013. | 45 | With equipment purchases well underway, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of July 2013. | 55 | Network testing will follow the network build metric now that construction of routes is in full production. It is anticipated that this metric will attain the Baseline projection by the end of July 2013. A compressed schedule will allow this to be completed as required. | 2013-05-24 17:08 | 2013-05-24 17:08 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2013 | Q2 | Q2 - 2013 | 10652 | 8986 | FALSE | 71 | Although construction activities will be completed at the end of the quarter, final invoices will remain to be paid and closeout activities will continue into the final quarter of 2013. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-20 11:23 | 2013-08-20 11:23 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570111 | 2013 | Q3 | Q3 - 2013 | 12322 | 10496 | FALSE | 100 | Project is complete. | 0 | N/A | N/A | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 2014-07-25 14:45 | 2014-07-25 14:45 | 5528 | 5528 | Northwest Open Access Network
NT10BIX5570112 | 2010 | Q4 | Q4 - 2010 | 1198 | 2231 | FALSE | 26 | N/A | 0 |  | N/A | 100 | Complete | 60 | Working with Engineering consultant on Contractor RFP's. | 50 | N/A | 25 | N/A | 10 | N/A | 45 | N/A | 44 | N/A | 45 | N/A | 32 | N/A | 2011-02-17 11:12 | 2011-02-17 11:12 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2011 | Q1 | Q1 - 2011 | 1894 | 2692 | FALSE | 26 | We are behind due to the Environmental Assessment, but do not anticipate any other major project impacts. | 0 |  | N/A | 100 | Complete | 65 | We are currently on target with our project baseline for next quarter. | 45 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 50 | We are currently on target with our project baseline for next quarter. | 15 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 52 | We are currently on target with our project baseline for next quarter for equipment procurement. | 50 | We are currently on target with our project baseline for next quarter for our network build components. | 40 | The variance is due to the delay in receiving our FONSI. | 15 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 2011-05-05 12:38 | 2011-05-05 12:38 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2011 | Q2 | Q2 - 2011 | 3008 | 3261 | FALSE | 32 | We will continue to lag for this quarter due to the delay in starting construction and being able to order equipment needed due to late award of our FONSI as well as the delay in receiving our fiber ordered. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 0 |  | N/A | 100 | Completed | 70 | We are currently on target with our projected baseline for next quarter. | 50 | We will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 50 | NebraskaLink will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 36 | We are currently on target with our projected baseline for next quarter. | 65 | We are currently on target with our projected baseline for next quarter. | 60 | We anticipate being close to our targeted projection for next quarter. We have experienced weather delays at the start of this quarter. | 45 | We anticipate a delay on this milestone due to the late award of our FONSI and we were not able to purchase enclosures for all or our equipment to be deployed as planned. | 40 | We will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 2011-08-11 08:40 | 2011-08-11 08:40 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2011 | Q3 | Q3 - 2011 | 4134 | 3913 | FALSE | 53 | We expect to be on target with our baseline for next quarter. | 0 |  | N/A | 100 | Completed | 75 | We are currently on target with our baseline for next quarter. We continue to work closely with our Engineering firm to map/ stake our routes. | 80 | We expect to be on target with our baseline for next quarter by working closely with our consultants and state agencies to obtain right of way permits. | 80 | We are working closely with our Engineering Consultant to align this closer with our baseline for 1st quarter 2012. | 36 | We are currently on target with our baseline for next quarter. | 70 | We are currently on target with our baseline for next quarter. | 62 | We expect to be slightly behind target with our baseline for next quarter due to our miles of fiber constructed. | 70 | We anticipate being on target with our baseline for next quarter. | 55 | We anticipate being behind target with our baseline for next quarter due to the our miles of fiber constructed. | 2011-11-18 13:41 | 2011-11-18 13:41 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2011 | Q4 | Q4 - 2011 | 4908 | 4592 | FALSE | 52 | NebraskaLink expects to be behind on this target compared to the baseline plan due to the the winter season. | 0 |  | N/A | 100 | Completed | 80 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLink will continue to work closely with our Engineering Consultant to align this with our baseline plan for next quarter. | 50 | NebraskaLInk is on target with our baseline report for next quarter. | 75 | NebraskaLink is on target with our baseline report for next quarter. | 74 | NebraskaLink expects to be on target with our baseline report for next quarter. | 75 | NebraskaLink expects to be on target with our baseline for next quarter. | 60 | We anticipate being slightly behind with our baseline for the next quarter due to our miles of fiber constructed during the peak winter season. | 2012-02-07 15:28 | 2012-02-07 15:28 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2012 | Q1 | Q1 - 2012 | 5910 | 5554 | FALSE | 60 | NebraskaLink expects to be slightly behind on our overall project due to orders / invoices that we expect will be submitted during mid summer for projects and materials. | 0 |  | N/A | 100 | Completed | 85 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLInk expects to be close to target with our baseline plan. We have some areas that will only allow us to obtain our permits inside a 60 day window for construction. | 95 | NebraskaLInk expects to be close to target with our baseline report for this milestone. We have some areas that will only allow us to obtain our permits inside a 60 day window for construction. | 76 | NebraskaLink expects to be on target with our baseline plan. | 80 | NebraskaLink expects to be on target with our baseline plan. | 75 | NebraskaLink expects to catch this milestone up in the upcoming quarter which will coincide with a better construction season. | 80 | NebraskaLink expects to be on target with our baseline plan for this milestone. | 70 | NebraskaLink expects to be close to target with our baseline plan for this milestone for the upcoming quarter. | 2012-05-02 12:12 | 2012-05-02 12:12 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2012 | Q2 | Q2 - 2012 | 7222 | 6238 | FALSE | 86 | NebraskaLink expects to be slightly behind the targeted milestone due to invoices that we expect after the end of the quarter for materials to be delivered toward the end of the quarter. | 0 |  | N/A | 100 | Completed | 90 | NebraskaLink expects to be on target with our baseline for this milestone. | 95 | NebraskaLink expects to be close to target with our baseline plan. We have a few areas that will only allow us a brief period prior to construction to obtain necessary permits. | 97 | NebraskaLink expects to be close to target with our baseline plan. Again there are a few areas that will only allow us a 60 day window to obtain permits to construct in their areas. | 95 | NebraskaLink expects to be close to target with our baseline plan. | 87 | NebraskaLink expects to be close to target with our baseline plan. | 93 | NebraskaLink expects to be on target with our baseline plan for this milestone. | 87 | NebraskaLink expects to be close to target with our baseline plan. | 85 | NebraskaLink expects to be slightly behind target on this milestone for the upcoming quarter. | 2012-08-23 12:11 | 2012-08-23 12:11 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2012 | Q3 | Q3 - 2012 | 7898 | 6653 | FALSE | 88 | NebraskaLink expects to be behind on this milestone as compared to our baseline. NebraskaLink is waiting for an approval from BTOP on an award action request for a possible change in routes in some of our project cities. | 0 |  | N/A | 100 | Completed | 95 | NebraskaLink expects to be on target for this milestone. | 100 | NebraskaLink expects to be on target for this milestone. | 100 | NebraskaLink expects to be on target for this milestone. | 97 | NebraskaLink expects to be close to target for this milestone. | 98 | NebraskaLink expects to be close to target with this milestone for equipment procurement - hoping to receive all invoices by close of quarter. | 97 | NebraskaLink expects to be on target for this milestone. | 95 | NebraskaLink expects to be on target for this milestone. | 92 | NebraskaLink expects to be on target for this milestone. | 2012-11-15 15:21 | 2012-11-15 15:21 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2012 | Q4 | Q4 - 2012 | 8680 | 7496 | FALSE | 93 | NebraskaLink expencts to be behind on this milestone as compared to our baseline. NebraskaLink is waiting for an approval from BTOP on an award action request for a possible change in routes in some of our project cities. | 0 |  | N/A | 100 | Completed | 99 | NebraskaLink expects to be close to target with this milestone | 100 | NebraskaLink expects to be on target with this milestone. | 100 | NebraskaLink expects to be on target with this milestone. | 95 | NebraskaLink expects to be behind on this milestone, completing in 2nd quarter 2013. | 89 | NebraskaLink expects to be close to target with this milestone, completing in 2nd quarter 2013. | 98 | NebraskaLink expects to be close to target with this milestone. | 95 | NebraskaLink expects to be closet to target with this milestone, complete in 2nd quarter 2013. | 95 | NebraskaLink expects to be on target with this milestone. | 2013-02-08 13:56 | 2013-02-08 13:56 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2013 | Q1 | Q1 - 2013 | 9354 | 8136 | FALSE | 98 | NebraskaLink expects to be close to completion of this milestone. | 0 |  | N/A | 100 | Completed | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone | 100 | NebraskaLink expects to be completed with this milestone | 98 | NebraskaLink expects to be close to completion of this milestone. | 2013-04-29 12:51 | 2013-04-29 12:51 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2013 | Q2 | Q2 - 2013 | 10316 | 8775 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-07-30 11:51 | 2013-07-30 11:51 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570112 | 2013 | Q3 | Q3 - 2013 | 11640 | 9761 | FALSE | 100 | Complete | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-01-22 11:41 | 2014-01-22 11:41 | 6001 | 6001 | Nebraskalink, LLC
NT10BIX5570113 | 2010 | Q4 | Q4 - 2010 | 1012 | 2057 | FALSE | 1 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 2 | No variance from Baseline. | 0 | N/A | 54 | No variance from Baseline. | 0 | N/A | 0 | No variance from Baseline. | 1 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-02-09 10:09 | 2011-02-09 10:09 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2011 | Q1 | Q1 - 2011 | 2308 | 2899 | FALSE | 1 | Variance from Baseline. The State has proceeded on segments of the project while awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. Critical segments of the project will be expedited - see narratives in 2e and 2h. | 0 | None | N/A | 100 | No variance from Baseline. | 3 | No variance from Baseline. | 0 | N/A | 54 | Variance from Baseline due to awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State has proceeded with work on this milestone while awaiting the FONSI and is developing required documents for acquiring needed construction permits, railroad permits and other approvals. The State will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. | 0 | Variance from Baseline due to awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the network build into 40-50 mini-projects with multiple construction firms and project partners. The State will release an RFP and will purchase all materials (fiber optic cable, conduit, etc.) directly from suppliers. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-05-25 16:24 | 2011-05-25 16:24 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2011 | Q2 | Q2 - 2011 | 2962 | 3238 | FALSE | 8 | Variance from Baseline. The State proceeded on segments of the project while awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. Critical segments of the project will be expedited - see narratives in 2e and 2h. | 0 | None | N/A | 100 | No variance from Baseline. | 6 | No variance from Baseline. Matching funds expended to date include salaries and fringe for ODOT internal engineering staff and payments to engineering firms for preliminary design work. | 0 | N/A | 81 | Variance from Baseline due to awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State has proceeded with work on this milestone while awaiting the FONSI and has developed required documents for acquiring needed construction permits, railroad permits and other approvals. The State will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. The State will issue RFP(s) and will purchase all materials (fiber optic cable, conduit, communications huts, etc.) directly from multiple suppliers. | 2 | Variance from Baseline due to awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the network build into 40-50 mini-projects with multiple construction firms and project partners. As noted in number 1, the State will evaluate responses to Request for Proposal (RFP) to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN Broadband project construction routes, and will conduct negotiations and sign contracts with selected partners. | 0 | No variance from Baseline. | 0 | No variance from Baseline | 2011-08-08 16:21 | 2011-08-08 16:21 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2011 | Q3 | Q3 - 2011 | 3496 | 3518 | FALSE | 30 | Variance from Baseline. Critical segments of the project are being expedited - see narratives in 2e, 2g and 2h. | 0 |  | N/A | 100 | No variance from Baseline. | 84 | Variance from Baseline. This milestone is ahead of schedule. Projected matching funds expended include salaries and fringe for ODOT internal engineering staff and payments to engineering firms for preliminary design work. | 100 | See narrative in 2d above. | 90 | Variance from Baseline. The State has developed required documents for acquiring needed construction permits, railroad permits and other approvals. The State is expediting this process with the goal of completing this milestone on schedule. It is projected this milestone will be completed under the budgeted amount. | 0 | N/A | 49 | Variance from Baseline. The State has issued a RFP for Fiber Optic Cable for the OCAN project. The RFP was posted on September 28, 2011 with a close date of October 27, 2011. The State will issue RFP(s) for additional required materials (conduit, handholes, etc.). | 13 | Variance from Baseline. The State will complete Indefeasible Right of Use (IRU) Agreements to meet the purpose of the grant on certain segments of the OCAN project. The State will issue Request for Proposal (RFP) packages for construction of the OCAN project on remaining segments. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-10-27 11:36 | 2011-10-27 11:36 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2011 | Q4 | Q4 - 2011 | 4910 | 4594 | FALSE | 32 | Variance from Baseline. Critical segments of the project are being expedited. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone will be completed ahead of the schedule projected in the Baseline. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 49 | Variance from Baseline. The State issued a Request for Proposal (RFP) for Fiber Optic Cable for the OCAN project. Bids have been received and evaluated. Purchase Orders will be issued in January, 2012. A RFP will be issued in January for the additional network equipment needed for the OCAN project. Bids will be evaluated and purchase orders will be issued. | 14 | Variance from Baseline. The State plans to complete Indefeasible Right of Use (IRU) Agreements to meet the purpose of the grant on certain segments of the OCAN project. The State will award the bids for construction of the OCAN project on segments not included in the proposed Indefeasible Right of Use (IRU) Agreements. | 0 | Variance from Baseline. Network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 0 | Variance from Baseline. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-02-07 15:59 | 2012-02-07 15:59 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2012 | Q1 | Q1 - 2012 | 5960 | 5579 | FALSE | 63 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone was completed ahead of schedule. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 64 | Variance from Baseline. All communications huts will be completed and installed. All fiber optic cable will be delivered. Bids for network equipment will be awarded and purchase orders issued. | 50 | Variance from Baseline. The State will execute two additional Indefeasible Right of Use (IRU) Agreements for existing fiber optic facility to meet the purpose of the grant on certain segments of the OCAN project. The State has awarded bids for construction on on all segments of the OCAN project not included in the IRU Agreements. | 20 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 20 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU and will be completed on the network delivered on the two additional IRU Agreements. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-05-08 12:11 | 2012-05-08 12:11 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2012 | Q2 | Q2 - 2012 | 6866 | 6059 | FALSE | 93 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone was completed ahead of schedule. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 100 | No variance from Baseline. All equipment is projected to be purchased by end of next quarter. | 100 | Variance from Baseline. The State will execute two additional Indefeasible Right of Use (IRU) Agreements for existing fiber optic facility to meet the purpose of the grant on certain segments of the OCAN project. The State is projecting to have all OCAN project segments, not included in the IRU's, constructed and fiber pulled. | 40 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 40 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU and will be completed on the network delivered on the two additional IRU Agreements. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-08-06 13:37 | 2012-08-06 13:37 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2012 | Q3 | Q3 - 2012 | 7816 | 6611 | FALSE | 97 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 98 percent project completion milestone by the end of Q2 of year three of the project. | 0 |  | N/A | 100 | No Variance from Baseline. | 100 | No variance from Baseline. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 93 | Variance from Baseline. All equipment is projected to be purchased by end of Q2 of year three of the project. | 93 | Variance from Baseline. The State is projecting to have all OCAN project segments constructed and fiber pulled by the end of the first month in Q3 of year three of the project. | 70 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment is in process of being deployed. | 70 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the executed IRU Agreements and completed segments of the OCAN project. | 2012-11-09 14:49 | 2012-11-09 14:49 | 6060 | 6060 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2012 | Q4 | Q4 - 2012 | 8706 | 7512 | FALSE | 98 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 100 percent project completion milestone by the end of Year3-Q3 of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | Note: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 95 | Variance from Baseline. Remaining network equipment to be purchased has been sent out for bid with a deadline to be procured by Year3-Q4 of the project. | 100 | No variance from Baseline. The State is projecting to have all OCAN project segments constructed and fiber pulled by the end of the first month in Year3-Q3 of the project. | 95 | Variance from Baseline. Remaining network equipment to be purchased has been sent out for bid with a deadline to be procured and deployed by Year3-Q4 of the project. | 100 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the executed IRU Agreements and completed segments of the OCAN project. | 2013-02-11 15:28 | 2013-02-11 15:28 | 7631 | 7631 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2013 | Q1 | Q1 - 2013 | 9626 | 8344 | FALSE | 100 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 2013-05-07 17:23 | 2013-05-07 17:23 | 7631 | 7631 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2013 | Q2 | Q2 - 2013 | 10320 | 8778 | FALSE | 100 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 0 | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 2013-07-30 12:25 | 2013-07-30 12:25 | 7631 | 7631 | Finance, Oklahoma Office of State
NT10BIX5570113 | 2013 | Q3 | Q3 - 2013 | 12516 | 10691 | FALSE | 100 | Project complete. | 0 |  | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 2014-09-22 14:45 | 2014-09-22 14:45 | 7631 | 7631 | Finance, Oklahoma Office of State
NT10BIX5570114 | 2010 | Q4 | Q4 - 2010 | 1366 | 2381 | FALSE | 7 | None Noted | 26 | Staffing | None Noted | 95 | None Noted | 50 | The slow contract negotiations Merit does not feel that we will catch up with Network Design. Weather conditions will also determine the speed at which the engineers will be able to work. Merit feels that next quarter engineering will be up to speed and on track considering the process we have put in place. | 50 | None Noted | 10 | Merit doesn't feel that we will be up to speed in this category considering the contract negotiations. Merit feels that next quarter permitting will be up to speed and on track considering the process we have put in place. | 5 | None Noted | 10 | None Noted | 3 | None Noted | 0 | None Noted | 0 | None Noted | 2011-02-24 13:47 | 2011-02-24 13:47 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570114 | 2011 | Q1 | Q1 - 2011 | 2268 | 2879 | FALSE | 4 | Our overall project spending will be significantly less than the projected 22% as a result of unexpected delays in the issuance of our FONSI. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 8 | Staffing | We have not hired staff at the rate originally projected because we overestimated the staffing levels that would be required for this pre-FONSI stage of the project. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we estimate will be at 385% next quarter. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the EA, we are considering a revision to the budget to incorporate the latest estimate of the EA cost at completion, which will be xx% above the original budget. | 28 | The bulk of network design costs are incurred during field engineering. To avoid wasting federal funds engineering routes that we may be required to change, we are not beginning the detailed engineering work until our route is approved. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 36 | We are able to send out Metropolitan Extension Telecommunications Rights-of-Way Oversight (METRO) permits with our EA route, and are beginning that this quarter. Because other permits require an approved engineered route, our ability to move forward with the remaining ROW permits depends on having our route accepted by the NTIA so the CAD drawings can be finalized. | 10 | Because permits require an approved engineered route, our ability to move forward with the remaining ROW permits depends on having our route accepted by the NTIA so the CAD drawings can be finalized. | 3 | Merit did not receive the FONSI, so we could not begin hut site construction. Sites for the huts have been identified and Merit will continue to negotiate easements. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 0 | Merit did not include equipment in our revised expenditure plan, so we cannot begin procuring equipment until we receive our FONSI. In addition, we are waiting on a determination on using a sole source justification for equipment vendor selection. If we order optical equipment this quarter, it is unlikely that we would pay the invoice during 2011 Quarter 2. | 3 | We anticipated having finalized IRU Agreements in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure. However, construction cannot occur until the FONSI is issued, and will most likely begin in June, towards the end of 2011 Quarter 2. | 0 | With construction and equipment purchase approximately one quarter behind schedule, we do not anticipate incurring any costs for deployment this quarter. | 0 | With construction and equipment purchase approximately one quarter behind schedule, we do not anticipate incurring any costs for deployment this quarter. | 2011-05-24 09:31 | 2011-05-24 09:31 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570114 | 2011 | Q2 | Q2 - 2011 | 3028 | 3271 | FALSE | 6 | Our overall project spending is less than we projected as a result of unexpected delays in the issuance of our Finding of No Significant Impact. Merit believed we would be able to begin field engineering and construction this quarter. Once Merit has clearance to move forward with construction, we believe that we will catch up over the next few quarters. | 17 |  | The construction delays have led to a slower staffing ramp up than originally projected. With the hire of a Project Manager, Environmental Assessor, and several clerks pending, we anticipate a gradually aligning with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 474%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the cost at completion, which will be around 700%. | 27 | We are waiting for our Finding of No Significant Impact to proceed with most of the field engineering, but have attempted to do as much planning as is covered by the revised expenditure plan. Due to weather conditions, pre-construction planning and engineering work wasn't done at the projected pace in the Upper Peninsula. | 66 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted, we have prepped many permits so they can be sent out as soon as the Finding of No Significant Impact is received and the route is finalized. | 23 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted, we have prepped many permits so they can be sent out as soon as the Finding of No Significant ImpactI is received and the route is finalized. | 0 | Merit did not receive the Finding of No Significant Impact, so we could not begin hut site construction. Sites for the huts have been identified and Merit began to negotiate easements. | 5 | Merit did not include equipment in our revised expenditure plan, so we requested a pre-Environmental Assessment budget revision. Our sole source was approved at the end of the quarter, and the order will be placed next quarter. | 5 | We anticipated having finalized Indefeasible Right to Use Agreements and the Finding of No Significant Impact in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure and beginning construction in the next quarter. | 0 | We were waiting for our Environmental Assessment budget approval and sole source approval to order equipment. Equipment has been selected, and will be deployed as soon as it is received and tested. | 0 | Network construction has not begun. | 2011-08-11 16:37 | 2011-08-11 16:37 | 5484 | 5484 | Merit Network Inc.
NT10BIX5570114 | 2011 | Q3 | Q3 - 2011 | 3950 | 3813 | FALSE | 24 | Merit just recently received its notice of our Finding of No Significant Impact and has recently completed all field engineering. Our engineering firm is in the process of drafting the appropriate prints for permit applications. We have submitted all permits for Round 2 based on the prints weâ€™ve received thus far so we anticipate a heavy construction season starting next quarter. | 10 |  | With the hire of a Project Manager, Environmental Assessor and several clerks we anticipate a gradual alignment with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 565%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the cost at completion, which will be around 600%. | 58 | Since receiving our Finding of No Significant Impact we have completed most if not all of our field engineering. Permitting has started and some segments are already ready to go from a construction and environmental permit standpoint. The route has been finalized, engineered and assigned segment numbers that will be released to our selected construction contractors. Much of the pre-construction planning has been completed such as material purchases and route engineering in both the Upper and Lower Peninsula. | 90 | Many permits require an approved engineered route; and with most, if not all, of the field engineering complete we will have completed submission of almost all our Rights-of-way permit applications with the appropriate entities. As these permits are approved, we can then start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most if not all of the engineering work necessary. | 85 | We will have submitted almost all of the permits necessary for Round 2 construction since we received our Finding of No Significant Impact, and will spend this quarter resolving make-ready issues and following up with permitting agencies on permits that have not been issued. | 27 | Sites for the huts have been identified. We have submitted and closed an RFP for the construction of huts and are also in the process of acquiring easement agreements for the placement of said huts. As of today we have almost all of the easement agreements signed and forecast all easement issues resolved by the end of next quarter. We have also started interviewing contractors to construct our huts. | 6 | We anticipate ordering the bulk of our equipment in the next quarter, and being invoiced for that order in the quarter after that. | 33 | We have received our Indefeasible Right of Use Agreements as well as our Finding of No Significant Impact for Round 2. We have begun our negotiations to purchase existing infrastructure in both Michigan and Wisconsin and expect to have those agreements completed by the end of the next quarter. We anticipate doing a significant amount of make-ready work, and beginning underground construction. | 13 | Equipment has been selected and will be deployed as soon as it is received and tested. As of this quarter, since receiving the Environmental Assessment budget approval and sole source approval, the process of purchasing this equipment began this quarter. | 25 | Network construction has not begun, but with small sections of construction being deployed next quarter we anticipate testing to commence next quarter. | 2011-11-10 08:22 | 2011-11-10 08:22 | 5485 | 5485 | Merit Network Inc.
NT10BIX5570114 | 2011 | Q4 | Q4 - 2011 | 5328 | 5000 | FALSE | 26 | Merit anticipates construction moving into full swing. We will select vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind, including new network miles deployed (updated projection: 0), network miles leased (updated projection: 54), and new interconnection points (updated projection: 4). We anticipate having all agreements with broadband wholesalers in place by the end of the next quarter. | 11 |  | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 550%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 79 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 89 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 30 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 23 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 22 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 26 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 26 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-02-28 07:33 | 2012-02-28 07:33 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570114 | 2012 | Q1 | Q1 - 2012 | 6244 | 5724 | FALSE | 33 | Merit anticipates construction moving into full swing. We will select vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind | 29 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 554%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 90 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 88 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 57 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 24 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 22 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 34 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 28 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-05-22 07:48 | 2012-05-22 07:48 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570114 | 2012 | Q2 | Q2 - 2012 | 6948 | 6101 | FALSE | 43 | Merit anticipates construction increasing and continuing at full speed. We have selected vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind | 46 | Staffing | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 556%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 96 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 91 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 62 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 36 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 29 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 47 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 40 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 25 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-08-09 09:13 | 2012-08-09 09:13 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2012 | Q3 | Q3 - 2012 | 8038 | 6725 | FALSE | 58 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 55 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 556% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 100 | While most of the field engineering is completed Merit anticipates continued costs for incorporating redlines and final CADs. | 96 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 71 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 44 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 39 | Merit is ordering additional optical equipment. The procurement process for routers and switches will be completed and router and switch equipment will be ordered. Merit anticipates being at budget by project completion. | 65 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 47 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 34 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-11-26 12:39 | 2012-11-26 12:39 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570114 | 2012 | Q4 | Q4 - 2012 | 9020 | 7792 | FALSE | 76 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 67 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 610% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 620%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 151% of the original budget. Site Prep expenses are being applied to this category as well. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 88 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 58 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 59 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 81 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 74 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-02-27 14:39 | 2013-02-27 14:39 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2013 | Q1 | Q1 - 2013 | 9954 | 8521 | FALSE | 81 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 68 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. 3. Please describe any challenges or issues anticipated during the next quarter that may impact planned progress | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 635% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 641%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticpates spending continuing in the next quarter and will be around 187%. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 118% by the end of next quarter. | 89 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 60 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 60 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 87 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 74 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-05-29 06:10 | 2013-05-29 06:10 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570114 | 2013 | Q2 | Q2 - 2013 | 10732 | 9029 | FALSE | 86 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 50 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 637% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 643%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticpates spending continuing in the next quarter and will be around 212%. Some project salary has been applied to this category. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 137% by the end of next quarter. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 37 | Merit anticipates additional spending in the coming quarter as sites are being completed as backbone fiber passes by. | 39 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 100 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 58 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-08-26 11:00 | 2013-08-26 11:00 | 5993 | 5993 | Merit Network Inc.
NT10BIX5570114 | 2013 | Q3 | Q3 - 2013 | 11342 | 9471 | FALSE | 100 | Merit expects construction to continue be at or near completion. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 60 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. Some staffing costs has been allocated to Network Design rather than this category which is part of the reason our spending is low. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 643% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur minor costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 643%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 231%. Some project salary has been applied to this category. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 214% by the end of next quarter. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being at 124% of budget during the next quarter. | 29 | Merit anticipates additional spending in the coming quarter as sites are being completed as backbone fiber passes by. | 38 | Merit is had ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 100 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 61 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-11-22 09:11 | 2013-11-22 09:11 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2013 | Q4 | Q4 - 2013 | 11898 | 10066 | FALSE | 100 | The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. Merit anticipates completing the project in the next quarter. | 53 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. Some staffing costs has been allocated to Network Design rather than this category which is part of the reason our spending is low. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur minor costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 690%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 261%. Some project salary has been applied to this category. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 180% by the end of next quarter. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 103% by the end of next quarter. | 29 | Site preparation work is esentially complete. Costs have been absorbed in other categories to date. Merit anticipates little spending to occur in this category and will absorb overages from other categories. | 39 | Merit is had ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Construction is nearing completion, as soon as next quarter. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 100 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction near completion, our engineers will be field testing completed fiber and finishing up equipment installs. Merit will be at or close to budget by project completion. | 100 | Merit has been behind our baseline due to delays in starting from construction. However, with construction near complete, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2014-02-26 14:50 | 2014-02-26 14:50 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2014 | Q1 | Q1 - 2014 | 12110 | 10293 | FALSE | 100 | The Finding of No Significant Impact was received approximately two (2) quarters behind. Merit has drawn all ARRA funding and anticipates completing the project in the next quarter. | 57 | Staffing Miscellaneous | Staffing has mostly been covered in the Network Design category and may reallocated back to Other. Expenses will continue in this category and will absorb overrun from other categories. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur minor costs related to the Environmental Assessment, Merit is working on a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 690%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 255%. Some project salary has been applied to this category. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 132% by the end of next quarter. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 106% by the end of next quarter. | 24 | Site preparation work is esentially complete. Costs have been absorbed in other categories to date. Merit anticipates little spending to occur in this category and will absorb overages from other categories. | 46 | Merit has ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Construction is nearing completion, as soon as next quarter. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 100 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. With all equipment placed, there will be minimal spending remaining. | 100 | Testing is continuing across the network with almost all infrastructure completed. | 2014-04-30 11:04 | 2014-04-30 11:04 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2014 | Q2 | Q2 - 2014 | 12464 | 10643 | FALSE | 100 | Merit has drawn all ARRA funding and anticipates completing the project in the next quarter. Merit has currently expended 101% of the total project budget and will be committing additional matching funds to supplement the project, expecting to be around 102% of budget. | 60 | Staffing Miscellaneous | Staffing has mostly been covered in the Network Design category and may reallocated back to Other. Expenses will continue in this category and will absorb overrun from other categories. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Spending in this category should be complete. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 252%. Some project salary has been applied to this category. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 132% by the end of next quarter. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 107% by the end of next quarter. | 24 | Site preparation work is esentially complete. Costs have been absorbed in other categories to date. Merit anticipates little spending to occur in this category and will absorb overages from other categories. | 46 | Merit has ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Construction is nearing completion, as soon as next quarter. Merit anticipates continued spending during the next quarter. The overrun should be able to be absorbed into another category. | 100 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. With all equipment placed, there will be minimal spending remaining. | 100 | Testing is continuing across the network with almost all infrastructure completed. | 2014-08-27 15:36 | 2014-08-27 15:36 | 7498 | 7498 | Merit Network Inc.
NT10BIX5570114 | 2014 | Q3 | Q3 - 2014 | 12624 | 10890 | FALSE | 100 | Merit has drawn all ARRA funding and anticipates completing the project in the next quarter. Merit has currently expended 102% of the total project budget and will be committing additional matching funds to supplement the project. | 61 | Staffing Miscellaneous | Staffing has mostly been covered in the Network Design category and may reallocated back to Other. Expenses will continue in this category and will absorb overrun from other categories. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Spending in this category should be complete. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 256%. Some project salary has been applied to this category. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 132% by the end of next quarter. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 111% by the end of next quarter. | 24 | Site preparation work is esentially complete. Costs have been absorbed in other categories to date. Merit anticipates little spending to occur in this category and will absorb overages from other categories. | 46 | Merit has ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Construction is nearing completion, as soon as next quarter. Merit anticipates some continued spending during the next quarter. The overrun should be able to be absorbed into another category. | 100 | Merit has managed the equipment deployment by ordering, receiving, and placing it as needed. With all equipment placed, there will be minimal spending remaining. | 100 | Testing is continuing across the network with almost all infrastructure completed. | 2014-12-18 12:37 | 2014-12-18 12:37 | 7981 | 7981 | Merit Network Inc.
NT10BIX5570114 | 2014 | Q4 | Q4 - 2014 | 12720 | 11045 | FALSE | 100 | Merit anticipates expending 104% of the total project budget by the end of next quarter and will continue committing additional matching funds to supplement the closeout of the project. | 64 | Staffing Miscellaneous | Merit anticipates expending 64% of the original budget by the end of next quarter and will continue committing additional matching funds to cover spending in this category. | 100 | All spending in this category in complete. | 100 | Merit anticipates expending 261% of the original budget by the end of next quarter and will continue committing additional matching funds to cover spending in this category. | 100 | All spending in this category is complete. | 100 | Merit anticipates expending 149% of the original budget by the end of next quarter and will continue committing additional matching funds to cover spending in this category. | 24 | All spending in this category is complete. | 46 | All spending in this category is complete. | 100 | Merit anticipates expending 129% of the original budget by the end of next quarter and will continue committing additional matching funds to cover spending in this category. | 100 | All spending in this category is complete. | 100 | All spending in this category is complete. | 2015-02-24 10:10 | 2015-02-24 10:10 | 7981 | 7981 | Merit Network Inc.
NT10BIX5570114 | 2015 | Q1 | Q1 - 2015 | 12838 | 11212 | FALSE | 100 | All spending in this category is expected to be complete. | 100 |  | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 100 | All spending in this category is expected to be complete. | 2015-05-22 14:29 | 2015-05-22 14:29 | 7981 | 7981 | Merit Network Inc.
NT10BIX5570114 | 2015 | Q2 | Q2 - 2015 | 12892 | 11275 | FALSE | 100 | Merit has completed the REACH-3MC II project. | 100 |  | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 100 | Merit has completed all spending in this category. | 42250.4135 | 42250.4135 | 7981 | 7981 | Merit Network Inc.
NT10BIX5570115 | 2010 | Q4 | Q4 - 2010 | 1080 | 2116 | FALSE | 3 | No variance from plan. | 0 | Fiscal compliance and project management | Fiscal compliance is expected to be 24% complete and project management is expected to be 19% complete | 100 | No variance from plan. | 16 | No variance from plan. | 1 | No variance from plan. | 77 | No variance from plan. | 0 | No variance from plan. | 0 | No variance from plan. | 0 | No variance from plan. | 7 | No variance from plan. | 0 | No variance from plan. | 2011-02-11 13:57 | 2011-02-11 13:57 | 7018 | 7018 | University of Wisconsin System
NT10BIX5570115 | 2011 | Q1 | Q1 - 2011 | 1962 | 2726 | FALSE | 18 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 30 | Fiscal compliance and project management | Fiscal compliance in baseline is 33% complete and project management is 28% complete. | 100 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 27 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 4 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 80 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 0 | na | 0 | na | 19 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 7 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 100 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 2011-05-12 11:32 | 2011-05-12 11:32 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2011 | Q2 | Q2 - 2011 | 3148 | 3334 | FALSE | 31 | Overall, actual spending of federal and match funds for build was delayed while wainting for the Finding of No Significant Impact. | 25 | Fiscal Compliance and Project Manager | Staff did not start in project as early as initially expected. | 100 | na | 5 | Design activities could not start until after Finding of No Significant Impact was received in late May. | 100 | na | 42 | Majority of permit activities could not start until after Finding of No Significant Impact was received in late May. | 0 | na | 0 | na | 34 | Network build could not start until after Finding of No Significant Impact was received in late May. | 4 | Equipment deployment could not start until after Finding of No Significant Impact was received in late May. | 0 | Network testing cannot begin until fiber is installed later this year. | 2011-08-17 11:49 | 2011-08-17 11:49 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2011 | Q3 | Q3 - 2011 | 4092 | 3889 | FALSE | 47 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect significant spending to continue for extra construction crews with catch up to occur by next quarter. We also have expenditure delays due to payments being cost reimbursement to our sub-recipients. | 30 | Fiscal compliance and Project Manager | Staff did not start in project as early as initially expected so expenses are not likely to equal budget. | 100 | na | 9 | Outside consultants have not been required to the extent originally planned. | 100 | na | 58 | See 2a above. | 0 | na | 0 | na | 50 | See 2a above. | 30 | Now that build has started with receipt of Finding of No Significant Impact, another third of equipment will be ordered. However, actual spending may not occur until next quarter because of the delays in reimbursing sub-recipients. | 50 | Now that build has started with receipt of Finding of No Significant Impact, approximately half the testing equipment has been ordered. We expect equipment delivery and subsequent invoices this quarter. The other half will occur next quarter due to delays with reimbursing sub-recipients. | 2011-11-16 16:24 | 2011-11-16 16:24 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2011 | Q4 | Q4 - 2011 | 5276 | 4945 | FALSE | 45 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect significant spending to continue for extra construction crews with catch up to occur by April to June quarter. We still have expenditure delays due to payments being cost reimbursement to our sub-recipients. | 36 | Fiscal and Project Management | Staff did not start in project as early as initially expected so expenses are not likely to equal budget. | 100 | NA | 12 | Outside consultants have not been required to the extent originally planned. | 100 | NA | 63 | See 2a above. | 0 | NA | 0 | NA | 44 | See 2a above. | 44 | Now that build has started, half of the equipment can be ordered. However payment may not occur until next quarter due to delays with reimbursing sub-recipients. | 97 | Purchase of network testing equipment is complete. | 2012-02-27 09:43 | 2012-02-27 09:43 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2012 | Q1 | Q1 - 2012 | 5946 | 5572 | FALSE | 55 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect a slow start to spring construction activities due to permitting delays, but expect to make up the time with additional crews so fiber installation can be completed by December 2012. Expenditures will be delayed for one quarter since sub-recipients are paid on a cost reimbursement basis. | 43 | Fiscal and Project Management | Since staff did not start in project as early as initially expected, expenses are not likely to equal budget. | 100 | Activity is complete. | 13 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 64 | See 2a explanation above. | 0 | NA | 0 | NA | 52 | See 2a explanation above. | 66 | Now that build has started, equipment orders and related invoices are being processed. There are delays in reporting expenses since sub-recipients are on a cost reimbursement basis. | 97 | Purchase of network testing equipment is complete. | 2012-05-07 16:02 | 2012-05-07 16:02 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2012 | Q2 | Q2 - 2012 | 7062 | 6158 | FALSE | 60 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U.S Fish and Wildlife Service regarding the Karner Blue Butterfly. Plans for catch up spending will be determined once work resumes in full. | 62 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 27 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 71 | See explanation in 2a above. | 0 | NA | 0 | NA | 58 | See explanation in 2a above. | 60 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2012-08-14 14:46 | 2012-08-14 14:46 | 7054 | 7054 | University of Wisconsin System
NT10BIX5570115 | 2012 | Q3 | Q3 - 2012 | 7862 | 6635 | FALSE | 73 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U. S. Fish and Wildlife Service regarding the Karner Blue Butterfly. Plans for catch up will be determined once work resumes in full. | 69 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 28 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 73 | See explanation in 2a above. | 0 | NA | 0 | NA | 75 | See explanation in 2a above. | 62 | See explanation in 2a above. | 97 | Purchase of network testing is complete. | 2012-11-14 09:35 | 2012-11-14 09:35 | 7110 | 7110 | University of Wisconsin System
NT10BIX5570115 | 2012 | Q4 | Q4 - 2012 | 8730 | 7529 | FALSE | 83 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U.S. Fish and Wildlife Services regarding the Karner Blue Butterfly. Given the success with construction catch up last quarter, we plan to complete construction before the end of the grant. | 87 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 31 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 74 | See explanation in 2a above. | 0 | NA | 0 | NA | 87 | See explanation in 2a above. | 62 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2013-02-12 16:02 | 2013-02-12 16:02 | 7110 | 7110 | University of Wisconsin System
NT10BIX5570115 | 2013 | Q1 | Q1 - 2013 | 9624 | 8343 | FALSE | 92 | Actual recorded federal and match spending for network build are lower caused by delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. While actual project work is expected to be completed this quarter. Final invoices will be processed next quarter. | 96 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 34 | Use of outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 74 | See explanation in 2a above. | 0 | NA | 0 | NA | 97 | See explanation in 2a above. | 79 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2013-05-07 15:08 | 2013-05-07 15:08 | 7110 | 7110 | University of Wisconsin System
NT10BIX5570115 | 2013 | Q2 | Q2 - 2013 | 10580 | 8946 | FALSE | 100 | The project will be complete at the end of this quarter. | 100 | Fiscal and Project Management | All federal funds will be expended. Closeout activities will be paid with other cash resources. | 100 | Activity is complete. | 35 | Use of outside consultants have not been required to the extent originally planned | 100 | Activity is complete. | 75 | The need for permit costs was not as great as originally planned. | 0 | NA | 0 | NA | 100 | Activity will be complete at the end of this quarter. | 90 | The need for permit costs was not as great as originally planned. | 97 | The need for permit costs was not as great as originally planned. | 2013-08-14 12:40 | 2013-08-14 12:40 | 7110 | 7110 | University of Wisconsin System
NT10BIX5570115 | 2013 | Q3 | Q3 - 2013 | 11950 | 10120 | FALSE | 100 | Project is complete and final invoices have been paid. | 100 | Fiscal and Project Management | Activity will be completed with other cash resources. | 100 | Activity is complete. | 100 | Use of outside consultants had not been required to the extent originally planned. Activity is complete. | 100 | Activity is complete. | 100 | The need for permit costs was not as great as originally planned. Activity is complete. | 0 | NA | 0 | NA | 100 | Activity is complete. Actual spending exceeded budget. | 100 | Equipment costs were not as great as originally planned. Activity is complete. | 100 | Network testing costs were not as great as originally planned. Activity is complete. | 2014-03-17 11:43 | 2014-03-17 11:43 | 6687 | 6687 | University of Wisconsin System
NT10BIX5570116 | 2010 | Q4 | Q4 - 2010 | 1344 | 2362 | FALSE | 9 | NCNMEDD and its contractors were unable to draw down federal funds until the six month budget was approved in January 2011. With 78.9% of the funds for all activities to come from the BTOP grant, it was difficult to spend all of the money anticipated until federal funds were released. Aggressive work on the construction contract and materials procurement should allow achievement of milestones, depending on the completion of Special Award Conditions and receiving the FONSI or mitigated FONSI. The increase to 9% from the baseline estimate of 7% will be due to advance procurment of materials. | 24 | Project management | This is in line with the original Baseline report. | 100 | The draft EA is on target for submittal, but some of the agencies may not finish their review as fast as others. Particular issues with the Bureau of Indain Affairs have been described elsewhere and in conversation with the FPO. | 71 | The Baseline assumed 85% completion by this time. This variance is due to the time spent in the previous quarter executing the Engineering contract and in obtaining permission to draw down funds for the six month budget. However, all key milestones are anticipated to be completed within this forecasted quarter, including final engineering design, construction prints, pole review, materials and equipment specifications, in line with the Baseline report. | 100 | The JPA governing the network, which was signed by all parties, indicates their willingness to provide rights of way for this project. Some concerns, elsewhere described, have arisen with some of the Pueblos. In the event that this delays activities, a report will be filed immediately. These issues have already been discussed with the FPO. | 75 | Applications will be initiated with all jurisdictions, with maps, descriptions and all information required, with the exception of that which can only be obtained after the execution of the construction contract. In addition, it is not possible to guarantee that all federal agencies will have completed their review of the EA and issued permits, where required. The percent of completion is listed at 75%, not 100%, because of the need to have the contractor in place to complete the application process. | 25 | Site preparation for the POP in Los Alamos will go forward as planned. Site preparation for the POP in Espanola may be delayed, depending on the timing of the FONSI. | 0 | None | 0 | None | 0 | None | 0 | None | 2011-02-23 15:17 | 2011-02-23 15:17 | 6052 | 6052 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2011 | Q1 | Q1 - 2011 | 1842 | 2664 | FALSE | 6 | In addition to the project activities discussed above, major milestones anticipated to be completed in Q4 include completion of engineering design, permits and rights-of-way, and finalizing contracts with a construction contract and materials supplier. Awards have already been made to project finalists and contract negotiations are underway. | 30 | Project Management |  | 100 | The agency accepted the revised Environmental Assessment on April 8, and copies were sent to agencies and tribes for review during the week April 11. The agencies and tribes have been given a two-week review window, which will close out the comment period in early May. Assuming a FONSI is issued in a timely manner, we should be able to begin drawing down construction funds by June 2011. | 90 | A 90% engineering design review meeting is scheduled for April 29, 2011, after which 100% drawings will be finalized. All engineering design is scheduled for completion by the end of May 2011, to enable construction to begin in June. The final engineering prints will become part of the construction contract documents, and serve as a baseline for the final implementation schedule. While engineering work will be 100% complete in Quarter 4, we are reserving 10% of the total engineering budget to cover activities in the construction phase. | 100 | Securing of rights-of-way was 75% complete in Quarter 3, and should be fully complete in Quarter 4. | 100 | Securing of construction permits and approvals was 75% complete in Quarter 3, and should be fully complete in Quarter 4. | 25 | If a FONSI is issued in May 2011, site preparation for the primary and secondary POPs will occur in Quarter 4. | 25 | If a FONSI is issued in May 2011, materials and network equipment procurement will begin in May and early June, in preparation for construction commencement in June. REDI Net has requested funding draw down, pre-FONSI, for qualifying expenses, as lead-times on the fiber cable have been extended due to raw materials shortages. This advance procurement will assist in keeping the overall project timeline on track. | 5 | Assuming construction commences in June, work would begin on the primary backbone fiber routes and primary POP installation. This is only an estimate until contract negotiations conclude in May and the final implementation schedule is set. | 0 | None | 0 | None | 2011-05-02 12:43 | 2011-05-02 12:43 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2011 | Q2 | Q2 - 2011 | 2548 | 3022 | FALSE | 39 | The project is anticipated to remain slightly behind schedule due to delays in receiving the FONSI, which put construction activities one quarter behind schedule. However, we will begin making up for these delays during Quarter 1, Year 2, as construction proceeds. | 45 | Project Management | Construction management and overall project implementation will continue as forecasted in the baseline. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 95 | Construction-related activities are approximately one quarter behind schedule due to delays with the FONSI. However, equipment procurement has been properly planned for, and NCNMEDD is ready to issue a Purchase Order for this milestone. Therefore, we anticipate 95% of our equipment budget will be expended in Quarter 1 of Year 2. | 36 | Construction activities are approximately one quarter behind schedule due to delays with the FONSI. 36% completion was expected in this quarter, and is therefore projected for Quarter 1 of Year 2. | 30 | It is anticipated that customer premise equipment will be installed in 40 of the 118 CAIs that are receiving CPE, along with placing the 2 core routers in the POPs. | 0 | Network testing may commence late in Quarter 1 of Year 2, although the assumption in the Baseline report projected Quarter 2 of Year 2. Therefore, we are still forecasting in-line with the Baseline. | 2011-07-27 12:42 | 2011-07-27 12:42 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2011 | Q3 | Q3 - 2011 | 4208 | 3952 | FALSE | 60 | Construction activity will continue to ramp up through Q4 2011, bringing the project closer to baseline performance goals. | 54 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Local government permits are being phased in closer to initiating the construction activities, so it is feasible that a small number of permits might be applied for after the upcoming reporting period. However, this will not impact overall project delivery. | 100 | Complete | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 43 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction and procurement are now ramping up. We are incrementally catching up on network build and will continue to do so in Q4 2011. Upcoming activities include make-ready, pole replacements, aerial fiber installation, boring, conduit placement, underground fiber installation, and POP construction. | 50 | Core routing equipment and a portion of the CPE will be installed in Q4 2011. | 25 | Field testing will commence on the core routing equipment in Q4 2011. | 2011-11-21 23:38 | 2011-11-21 23:38 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2011 | Q4 | Q4 - 2011 | 5218 | 4885 | FALSE | 67 | Construction activity will continue to ramp up through Q1 2012, bringing the project closer to performance goals. | 58 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Local government permits are being phased in closer to initiating the construction activities, so it is feasible that a small number of permits might be applied for after the upcoming reporting period. However, this will not impact overall project delivery. | 100 | Complete | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 65 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction and procurement are now ramping up. We are incrementally catching up on network build and will continue to do so in the upcoming reporting period. Upcoming activities include significant focus on pole replacements, then resuming aerial fiber installation. Continued progress will be made on boring, conduit placement, underground fiber installation, and POP setup. | 50 | Core routing equipment and a portion of the CPE will be installed in Q1 2012. | 25 | Field testing will commence on the core routing equipment in Q1 2012. | 2012-02-23 15:25 | 2012-02-23 15:25 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2012 | Q1 | Q1 - 2012 | 6098 | 5651 | FALSE | 66 | Construction activity will increase as make-ready ramps up, bringing the project closer to performance goals. | 70 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | We anticipate receiving Certificates of Occupancy (COs) for the Espanola and Santa Fe POPs. The CO for the Los Alamos POP may take additional time due to changes requested in the EA Addendum. | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE, subscriber aggregation equipment) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 62 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there have been some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction is now ramping up and will continue to do so in the upcoming reporting period. Upcoming activities include significant focus on pole replacements, aerial fiber installation, and completing underground construction. | 50 | Core routing equipment and additional CPE will be installed in the upcoming reporting period, to prepare for limited network activation in Q3 2012. | 50 | We forecast that 50% of the network testing will be complete in the upcoming reporting period. | 2012-05-15 13:51 | 2012-05-15 13:51 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2012 | Q2 | Q2 - 2012 | 7252 | 6253 | FALSE | 89 | Construction activity consistently ramping up closer to baseline projections. | 80 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction in now well underway and will continue to meet our revised quarterly projections. Upcoming activities include completing Phase I construction and beginning Phase II (route changes). Phase II construction will be dependent upon approval of the route changes proposed in the EA Addendum. | 75 | CAI equipment deployment will be completed for Phase I locations and the core routing equipment will be installed, tested, and activated in the secondardy POP. | 70 | Network testing will be completed on Phase I construction, which represents approximately 70% of the overall network to be deployed. | 2012-08-27 13:59 | 2012-08-27 13:59 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2012 | Q3 | Q3 - 2012 | 7910 | 6659 | FALSE | 92 | Project close-out draws near as construction activity focuses on routes approved in the EA Addendum. | 90 | Project Management | Project management work should continue as planned, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction in now well underway and will continue to meet our revised quarterly projections. Upcoming activities are focused on building the route changes authorized under the EA Addendum. | 100 | Complete | 80 | The majority of network testing will be completed in the upcoming reporting period, reflective of the route changes completed. | 2012-11-15 19:24 | 2012-11-15 19:24 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2012 | Q4 | Q4 - 2012 | 9034 | 7803 | FALSE | 98 | Per descriptions below | 95 |  | Project management work should continue as planned, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment agreements, applications, and pole replacements. Construction in now near completion and continue to closely meet our revised quarterly projections. Upcoming activities are focused on completing the route changes authorized under the EA Addendum. | 100 | Complete | 90 | The majority of network testing will be completed in the upcoming reporting period, reflective of the route changes completed. | 2013-02-27 16:17 | 2013-02-27 16:17 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2013 | Q1 | Q1 - 2013 | 10046 | 8577 | FALSE | 98 | per description below | 98 | Project Management | Customary Project Management will continue, such as construction oversight, verification, testing, and reporting on completed network segments, with a minimal reserve for the final project close-out activities. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Testing will continue on completed network segments, with a minimal reserve for the final project close-out activities. | 2013-06-03 11:49 | 2013-06-03 11:49 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2013 | Q2 | Q2 - 2013 | 10528 | 8917 | FALSE | 100 | Complete based project activities and reference to budget | 100 | Project Management | Complete based project activities and reference to budget | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities and reference to budget | 100 | Complete based project activities | 100 | Complete based project activities | 2013-08-08 15:14 | 2013-08-08 15:14 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570116 | 2013 | Q3 | Q3 - 2013 | 12058 | 10217 | FALSE | 100 | The overall project is completed at 100%, The actual spent was 102.95% of the original planned budget as NCNMEDD made additional match contributions. | 100 | Project Management | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 2014-04-22 12:23 | 2014-04-22 12:23 | 7089 | 7089 | North Central New Mexico Economic Development District
NT10BIX5570117 | 2010 | Q4 | Q4 - 2010 | 1318 | 2342 | FALSE | 18 | NA | 0 | 0 | NA | 100 | NA | 70 | NA | 70 | NA | 70 | NA | 0 | NA | 20 | NA | 10 | NA | 20 | NA | 10 | NA | 2011-02-22 20:48 | 2011-02-22 20:48 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2011 | Q1 | Q1 - 2011 | 2036 | 2763 | FALSE | 38 | na | 0 |  | na | 100 | na | 90 | na | 90 | na | 90 | na | 0 | na | 35 | na | 30 | na | 35 | na | 25 | na | 2011-05-16 10:39 | 2011-05-16 10:39 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2011 | Q2 | Q2 - 2011 | 3260 | 3392 | FALSE | 38 | We are behind schedule due to the fiber installation RFP being released again. Fiber is in high demand at this time due to all the projects and other various reasons. Fiber demand may play a part in the project being off target. | 0 |  | na | 100 | na | 90 | We are behind schedule due to the fiber installation RFP being released again. We decided to complete our project in phases. The team had to rework network design to best fit phase 1, 2, & 3. | 90 | We are behind schedule due to the fiber installation RFP being released again. We awarded a contract for the permitting & engineering in quarter three. We hope to have all the permitting/drawings completed by the end of the third quarter. The SCDOT will then approve the drawings and then the permits will be issued. We hope to be on target by the end of the fourth quarter. | 90 | We are behind schedule due to the fiber installation RFP being released again. We awarded a contract for the permitting & engineering in quarter three. We hope to have all the permitting/drawings completed by the end of the third quarter. The SCDOT will then approve the drawings and then the permits will be issued. We hope to be on target by the end of the fourth quarter. | 0 | na | 35 | We are behind schedule due to the fiber installation RFP being released again. We are working with Procurement Office to get a Request for Proposal/Bid out to equipment vendors at this time. We hope to have that completed by the end of the third quarter. | 30 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the network build. | 35 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the equipment deployment. | 25 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the network build and equipment deployment, so in turn there is not any network testing necessary at this time. | 2011-08-22 14:17 | 2011-08-22 14:17 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2011 | Q3 | Q3 - 2011 | 4194 | 3945 | FALSE | 37 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 60 | na | 45 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 50 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 40 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 2011-11-21 16:28 | 2011-11-21 16:28 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2011 | Q4 | Q4 - 2011 | 5390 | 5068 | FALSE | 45 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 70 | na | 50 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 45 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 40 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 2012-02-29 11:45 | 2012-02-29 11:45 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2012 | Q1 | Q1 - 2012 | 6050 | 5624 | FALSE | 65 | Right of way issues may cause a slight delay in overall project. Receiving all equipment and materials necessary may cause certain delays of overall project. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 80 | na | 70 | na | 60 | This will depend on the Network Operation Centers being setup and operational. It will also depend on construction of network. | 30 | This will depend on the Network Operation Centers being setup and operational. It will also depend on construction of network. | 2012-05-14 09:09 | 2012-05-14 09:09 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2012 | Q2 | Q2 - 2012 | 7212 | 6233 | FALSE | 90 | na | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 90 | na | 80 | na | 90 | na | 80 | na | 2012-08-22 16:01 | 2012-08-22 16:01 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2012 | Q3 | Q3 - 2012 | 8046 | 6729 | FALSE | 95 | na | 0 |  | na | 100 | na | 100 | na | 95 | na | 95 | na | 0 | na | 100 | na | 90 | na | 100 | na | 85 | na | 2012-11-26 15:09 | 2012-11-26 15:09 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2012 | Q4 | Q4 - 2012 | 9122 | 7894 | FALSE | 95 | Due to installation of fiber and equipment being installed in anchors through the first quarter of 2013, testing may be pushed back til the following quarter. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 100 | na | 100 | na | 100 | na | 95 | Due to installation of fiber and equipment being installed in anchors through the first quarter of 2013, testing may be pushed back til the following quarter. | 2013-03-04 14:02 | 2013-03-04 14:02 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2013 | Q1 | Q1 - 2013 | 9698 | 8382 | FALSE | 99 | The teams feels that we will be so close to our baseline goal, but may need a few more weeks to determine all equipment is operating properly. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 99 | The teams feels that we will be so close to our baseline goal, but will need a few more weeks to determine all equipment is operating properly. | 2013-05-13 14:57 | 2013-05-13 14:57 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2013 | Q2 | Q2 - 2013 | 10656 | 8988 | FALSE | 100 | na | 100 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 100 | na | 100 | na | 100 | na | 100 | na | 2013-08-20 12:18 | 2013-08-20 12:18 | 6058 | 6058 | Oconee County
NT10BIX5570117 | 2013 | Q3 | Q3 - 2013 | 11510 | 9635 | FALSE | 100 | N/A | 100 | NA | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2013-12-20 09:16 | 2013-12-20 09:16 | 6058 | 6058 | Oconee County
NT10BIX5570118 | 2010 | Q4 | Q4 - 2010 | 794 | 1830 | FALSE | 25 | Overall project delayed 45-6- days due to delay in acquisition of engineering services. | 0 | N/A | N/A | 90 | Environmental delayed 45-60 days beyond initial timelines due to re-assignment of engineering contract. Current engineers proceeding ahead of schedule of preparation of draft environmental assessment. | 90 | Engineering design and bid package due this quarter | 90 | Acquisition on schedule | 90 | Acquisition on schedule | 50 | Acquisition of needed sites on schedule | 50 | Engineering design and bid package due this quarter | 10 | Construction expected to begin next quarter (Spring 2011) | 0 | Not planned in current quarter | 0 | Not planned in current quarter | 2011-01-28 15:31 | 2011-01-28 15:31 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2011 | Q1 | Q1 - 2011 | 2342 | 2916 | FALSE | 20 | Environmental review complete; bids released; construction begin by end of quarter. Overall delays due to engineering re-assignment. | 0 |  | N/A | 100 | Environmental review complete. Overall delays due to engineering re-assignment. | 100 | Design complete; bids to be released this quarter. | 90 | Rights of way secured for major segments; railways pending | 90 | Permits secured for major segments; railways pending | 90 | Sites secured; pending delivery of co-location buildings and install of services. | 50 | Network equipment to be ordered; held pending construction schedule. | 20 | Network build to commence by end of quarter; delayed due to environmental assessments. Construction and network build to commence by end of quarter; delayed due to engineering and environmental. | 0 | Not planned in current quarter | 0 | Not planned in current quarter | 2011-05-26 12:50 | 2011-05-26 12:50 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2011 | Q2 | Q2 - 2011 | 3210 | 3366 | FALSE | 50 | Significant construction to be accomplished during quarter. Prior delays due to engineering re-assignment. | 0 |  | N/A | 100 | Environmental review complete. Prior delays due to engineering re-assignment. | 100 | Design complete; equipment to be secured and tested as construction schedule allows. | 100 | Rights of way secured. | 100 | Permits to be completed. Prior delays due to railroad permit demands. | 90 | Sites secured; pending delivery of co-location buildings and install of services | 80 | Network equipment on order; testing and installation pending construction schedule. | 40 | Significant network build to be accomplished by end of quarter; prior delays due to delayed engineering and environmental assessments. | 40 | Equipment deployment and testing to coincide with construction schedule. | 40 | Segments of network to be tested as construction deployment allows. | 2011-08-18 17:38 | 2011-08-18 17:38 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2011 | Q3 | Q3 - 2011 | 4326 | 4013 | FALSE | 72 | Project is on schedule for completion. | 0 |  | N/A | 100 | Environmental review is completed. | 100 | Design modifications, if any, will be completed. | 100 | Rights of way secured | 100 | Kansas City Southern is the only permit remaining; will be completed. | 100 | Sites and colo buildings secured; pending delivery and setup. | 100 | Network switch/router equipment is remaining; will be received | 65 | Construction will be substantially complete with network fiber lighted for northern sections of the route projected. | 65 | Equipment deployment and testing to coincide with construction schedule. | 65 | Segments of network to be tested as construction deployment allows. | 2011-11-29 16:31 | 2011-11-29 16:31 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2011 | Q4 | Q4 - 2011 | 5216 | 4884 | FALSE | 84 | Project is on schedule for completion | 0 | N/A | N/A | 100 | Environmental review is completed | 100 | Design modifications, if any in construction completion, will be completed | 100 | Rights of way secured | 100 | Permits secured | 100 | Co-location buildings projected to be compled | 100 | Network switch/routing equipment to be secured | 90 | Lighted fiber to be in place; remaining percentage completion to be for anchor insitutions | 90 | Remaining percentage completion to be for anchor institutions | 90 | Primary route fiber testing to be completed. Remaining percentage completion to be for anchor institutions. | 2012-02-23 15:06 | 2012-02-23 15:06 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2012 | Q1 | Q1 - 2012 | 6282 | 5743 | FALSE | 72 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 | N/A | N/A | 100 | Original environmental review is complete. Additional environmental review may be required due to project modification being requested. The percent complete is noted at 100% in anticipation there will be no additional environmental requirements. | 95 | Original network design will be completed. Modifications in design may be required due to project modification being requested. | 100 | Rights of way secured for original design and planned project modification | 100 | Permits secured for original design and planned project modification | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement will be completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build will be completed. Planned project modification may require some network build modifications. Nexus has secured permission to add additional critical anchor institutions through cooperative agreement with the State. The additions will incorporate approximately 120 miles additional fiber to the network. These additions will be presented for approval through a project modification during the next quarter. | 90 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-05-24 13:47 | 2012-05-24 13:47 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2012 | Q2 | Q2 - 2012 | 7056 | 6155 | FALSE | 86 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 |  | N/A | 95 | Original environmental review is complete. Additional environmental review may be required due to project modification being requested. The percent complete is noted at 100% based on the original project but proposed project modification may require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification. | 100 | Rights of way secured for original design and planned project modification. | 95 | Permits secured for original design. Note proposed project modification will require permits from Core of Engineers and Levy Board. | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build will be completed. Planned project modification may require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter. | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-08-14 11:49 | 2012-08-14 11:49 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2012 | Q3 | Q3 - 2012 | 8064 | 6738 | FALSE | 92 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 | N/A | N/A | 95 | Original environmental review is complete. Additional environmental review is underway for proposed project modification. The percent complete is noted at 100% based on the original project but proposed project modification will require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification. | 100 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build is completed. Planned project modification will require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter. | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-11-27 09:58 | 2012-11-27 09:58 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2012 | Q4 | Q4 - 2012 | 8930 | 7714 | FALSE | 97 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. Overall project will be completed as scheduled. | 0 | N/A | N/A | 95 | Original environmental review is complete. Additional environmental review is underway for proposed project modification. The percent complete is noted at 100% based on the original project but proposed project modification will require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification | 100 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. Equipment has been staged at vendor warehouse awaiting release from project modification. | 90 | Original fiber network build is completed. Planned project modification will require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification | 2013-02-25 11:34 | 2013-02-25 11:34 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2013 | Q1 | Q1 - 2013 | 9858 | 8466 | FALSE | 97 | Overall project with program modification will be completed as scheduled | 0 | N/A | N/A | 100 | Environmental assessment for original project and program modification is completed | 100 | Network design will be completed at end of period. | 100 | Rights of way are completed. | 100 | Permits will be completed. | 100 | Site preparation will be completed. | 100 | Equipment procurement will be completed. | 100 | Network build will be completed. | 100 | Equipment deployment will be completed. | 95 | Network testing will be essentially completed with possible closeout changes for CAI sites and network providers. | 2013-05-21 18:42 | 2013-05-21 18:42 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2013 | Q2 | Q2 - 2013 | 10748 | 9038 | FALSE | 100 | Overall project with program modification will be completed as scheduled | 0 | N/A | N/A | 100 | Environmental assessment for original project and program modification is completed | 100 | Network design will be completed at end of period. | 100 | Rights of way are completed. | 100 | Permits will be completed. | 100 | Site preparation will be completed. | 100 | Equipment procurement will be completed. | 100 | Network build will be completed. | 100 | Equipment deployment will be completed. | 100 | Network testing will be essentially completed with possible closeout changes for CAI sites and network providers. | 2013-08-26 17:51 | 2013-08-26 17:51 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570118 | 2013 | Q3 | Q3 - 2013 | 12064 | 10226 | FALSE | 100 | Project completed | 0 | N/A | N/A | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 2014-04-24 00:18 | 2014-04-24 00:18 | 6037 | 6037 | Nexus Systems, Inc.
NT10BIX5570119 | 2010 | Q4 | Q4 - 2010 | 1018 | 2063 | FALSE | 25 | n/a | 0 |  | n/a | 100 | n/a | 100 | n/a | 35 | n/a | 30 | n/a | 35 | n/a | 30 | n/a | 5 | n/a | 0 | n/a | 0 | n/a | 2011-02-09 12:21 | 2011-02-09 12:21 | 6072 | 6072 | Horizon Telecom, Inc.
NT10BIX5570119 | 2011 | Q1 | Q1 - 2011 | 2122 | 2806 | FALSE | 5 | Project remains behind due to delays in start of construction from required environmental assessment. | 0 | n/a | n/a | 99 | We expect our FONSI to be issued in this quarter. Per the programmatic agreement with NTIA and the Ohio Historic Preservation Office, there will be continued assessment of POP sites as they are identified. | 10 | Engineering of lateral routes will be finalized as we begin to sign up CAIs. | 98 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 10 | Permits for rail and road crossings have been submitted, so we are farther along than expected. | 10 | Identification and acquisition of POP sites has been faster than projected and will continue this quarter. | 50 | Contracts for fiber materials and electronics were awarded in late Q1. First orders of equipment and fiber will be placed in this quarter. | 2 | Baseline projected 15%; however, we assumed we would be cleared for construction earlier. This assumes begin of construction in June. | 2 | Baseline projected 30%, which is inaccurate. Equipment deployment will run roughly concurrent with network build. | 2 | Baseline projected 30%, which is inaccurate. Equipment deployment will run roughly concurrent with network build. | 2011-05-18 10:24 | 2011-05-18 10:24 | 6072 | 6072 | Horizon Telecom, Inc.
NT10BIX5570119 | 2011 | Q2 | Q2 - 2011 | 3188 | 3354 | FALSE | 19 | Project will remain behind projected schedule due to delays in start of construction by environmental assessment. | 0 | n/a | n/a | 98 | We will continue to assess POP sites and routes as needed. | 25 | Engineering of lateral routes will begin as we begin to sign up CAIs. | 99 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 25 | We will continue to secure permits for rail and road crossings. Permitting is budgeted as part of network design. | 25 | Identification and acquisition of POP sites will continue. | 50 | Large orders for fiber and materials were placed late in the quarter. Continued orders will pace network construction. | 24 | Baseline projected 30%, but that assumed we would be cleared for construction earlier. Construction of the backbone will ramp up in this quarter. | 53 | We expect to have deployed equipment to 18 of 34 POP sites by the end of the Q3. | 53 | Baseline projected 30%, which is inaccurate. Testing will run roughly concurrent with equipment deployment. | 2011-08-18 11:25 | 2011-08-18 11:25 | 6072 | 6072 | Horizon Telecom, Inc.
NT10BIX5570119 | 2011 | Q3 | Q3 - 2011 | 4108 | 3897 | FALSE | 37 | Significant progress will be made this quarter to catch baseline projections. | 0 |  | n/a | 98 | Continued assessment with engineers and Environmental Assessment (EA) consultant as routes are finalized. | 72 | As final backbone routes are completed, engineering will turn toward the lateral build to begin to reach CAIs. | 98 | We continue to be ahead of projections due to our relationship with electric provider. | 72 | Included in network design. | 72 | Included in network design. | 81 | Procurement will see the largest jump in percentage as we receive and approve significant invoices from vendor. | 25 | While our accelerated build schedule will bring us closer to baseline, we will probably have some weather issues keeping us slightly behind.. | 20 | As we have just broken ground on our first PoP the equipment deployment is behind and will pick up. | 20 | Testing will run roughly concurrent with the network build. | 2011-11-17 12:48 | 2011-11-17 12:48 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2011 | Q4 | Q4 - 2011 | 5270 | 4936 | FALSE | 57 | With most hurdles out of the way, Horizon will catch and bypass baseline projections within the next six months. | 0 | n/a | n/a | 98 | Continues assessment with engineers and Environmental Assessment (EA) consultant as routes are finalized. | 78 | The fiber backbone should be complete by the end of this quarter. Work will begin on laterals. | 98 | We have an agreement with an electric provider which has provided permission for us to use their Rights of Way (ROWs). We are experiencing difficulties with another utility when we do need to use their poles. Hopefully that will be resolved soon. | 78 | Included in Network Design. | 78 | Included in Network Design. | 92 | Horizon expect most equipment will be purchased by the end of this quarter. | 50 | Horizon expects to finish the fiber backbone by the end of this quarter. | 45 | Equipment Deployment will pick up as more Points of Presence (POPs) are completed. | 40 | Testing will run fairly concurrent with equipment deployment. | 2012-02-26 14:09 | 2012-02-26 14:09 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2012 | Q1 | Q1 - 2012 | 6174 | 5689 | FALSE | 67 | With our major permitting issue out of the way, Horizon will make significant progress in the next six months. | 0 | n/a | n/a | 98 | Horizon continues the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 98 | Design of the laterals will make significant progress during this term. | 98 | With our largest hurdle resolved most rights-of-way will be perfunctory. | 98 | Included in Network Design. | 98 | Included in Network Design. | 90 | Horizon is only paying for electronics after they have been installed. | 60 | Horizon expects to have 700 miles of the backbone finished and 125 miles of laterals built. | 50 | Equipment Deployments roughly follows network build. | 45 | Testing runs fairly concurrent with equipment deployment. | 2012-05-18 10:47 | 2012-05-18 10:47 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2012 | Q2 | Q2 - 2012 | 7122 | 6188 | FALSE | 76 | Horizon reaches the two-thirds milestone during the first month of this quarter as is required by July 31. | 0 | n/a | n/a | 98 | Horizon continues the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 98 | Distribution laterals are in the final stages of design and engineering. | 98 | Rights-of-way are virtually complete with very few issues remaining. | 98 | Included in Network Design. | 98 | Included in Network Design. | 92 | All electronics have been received and installed, we will pay for them as they are tested and come online. | 60 | Horizon expects to build approximately 200 miles of backbone and another 100 miles of distribution fiber. | 62 | Is jumping ahead of Network Build, but waits for fiber to come online. | 45 | Testing waits for fiber to connect the electronics. | 2012-08-17 16:21 | 2012-08-17 16:21 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2012 | Q3 | Q3 - 2012 | 8170 | 6795 | FALSE | 87 | Our largest hurdle this quarter will be the lack of crews available to do power make-ready due to Hurricane Sandy. | 0 | n/a | n/a | 98 | Horizon will continue the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 96 | Finalizing distribution lateral design. | 98 | Almost complete. | 96 | Included in Network Design. | 96 | Included in Network Design. | 92 | Payment occurs after they are tested and come online. | 70 | We expect the build to reach 900 miles of fiber by the end of the quarter. | 70 | Waits for fiber to come online. | 55 | Waits for fiber for the connections to test. | 2012-11-30 10:30 | 2012-11-30 10:30 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2012 | Q4 | Q4 - 2012 | 8972 | 7752 | FALSE | 93 | Horizon will continue to look for ways to increase our build rate and still minimize costs associated with the build. | 0 | n/a | n/a | 98 | Continues as necessary. | 95 | Reaching final stages. | 98 | Continues as necessary. | 95 | Included in Network Design. | 95 | Included in Network Design. | 92 | In line with baseline. | 75 | As construction continues to make steady progress, we expect to reach the 1200 mile mark in our build. | 70 | Awaits backbone completion to bring online. | 60 | Awaits backbone completion to bring online. | 2013-02-26 13:51 | 2013-02-26 13:51 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2013 | Q1 | Q1 - 2013 | 10012 | 8551 | FALSE | 97 | Expect to serve 20 additional CAIs this quarter. | 0 | n/a | n/a | 100 | Continues as necessary. | 100 | Virtually complete. | 100 | Continues as necessary. | 100 | Included in Network Design. | 100 | Included in Network Design. | 100 | With three additional POPs online this category will go from 106% to 110%. | 85 | Expect to have 1250 miles built by the end of the quarter. | 88 | We have three POPs scheduled to be turned up this quarter. | 75 | Awaits backbone completion to bring online. | 2013-05-30 16:22 | 2013-05-30 16:22 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2013 | Q2 | Q2 - 2013 | 10830 | 9087 | FALSE | 100 | Virtually all construction should be completed and final POPs brought online. AARs will be filed during this quarter. | 0 | n/a | n/a | 100 | Continues as needed. | 100 | Virtually complete. | 100 | Continues as needed. | 100 | Included in Network Design. | 100 | Included in Network Design. | 100 | Currently at 106%, will rise as final POPs are brought online. | 100 | Virtually complete. | 98 | Final POPs are expected to be brought online over the next two quarters. | 95 | Awaits backbone completion to bring online in order to test. | 2013-08-30 16:14 | 2013-08-30 16:14 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2013 | Q3 | Q3 - 2013 | 11362 | 9484 | FALSE | 100 | The final 17.5 miles will be built this quarter as we wrap up network construction. Most, if not all, of these will be in areas where previous issues (make-ready, easement, permit, etc) blocked completion. This quarter will be spent on resolving those issues. | 100 | OARnet | This category is complete. | 100 | Complete upon acceptance of distribution route changes. | 100 | Complete. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | All electronics have been received and installed. | 100 | The vast majority of the network has been completed. All that remains are those small pieces where make-ready, easement, permit, etc issues have blocked sections. This quarter will be spent on resolving those issues. | 100 | When final backbone routes are finished the final provisioning can be completed. | 0 | n/a | 2013-11-22 17:27 | 2013-11-22 17:27 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2013 | Q4 | Q4 - 2013 | 11914 | 10080 | FALSE | 100 | The project is substantially complete and will be at approximately 108% of budget. | 100 | OARnet | This category is complete at 85% of budget. | 100 | This category is complete. | 100 | This category is complete at 113% of budget. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | Equipment procurement will be 118% of budget. | 100 | Construction is complete at 106% of budget | 100 | This category will be complete. | 0 | n/a | 2014-02-27 17:02 | 2014-02-27 17:02 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2014 | Q1 | Q1 - 2014 | 12172 | 10356 | FALSE | 100 | The project will be complete at approximately 110% of budget. The close-out process will continue. | 100 | OARnet | This item is complete at 85% of budget. | 100 | This category is complete. | 100 | This category is complete at 113% of budget. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | This category will be complete at approximately 116% of budget. | 100 | This category is complete and expected to end at 108% of budget. | 100 | This category is complete. | 0 | n/a | 2014-05-07 14:23 | 2014-05-07 14:23 | 6021 | 6021 | Horizon Telecom, Inc.
NT10BIX5570119 | 2014 | Q2 | Q2 - 2014 | 12754 | 11086 | FALSE | 100 | The project is complete at 106% of budget. | 100 | OARnet | This item is complete at 85% of budget. | 100 | The environmental assessment is complete. This was an unrealized requirement when budgeting for the project and was not accounted for in the baseline. Its impact from both a time and monetary perspective was huge, putting our project behind by more than three quarters of a year. | 100 | Network design is complete at 125% of budget. | 100 | Complete. Costs were included in Network design category. | 100 | Complete. Costs were included in Network design category. | 100 | Complete. Costs were included in Network design category. | 100 | Complete at 134% of budget. | 100 | Construction is complete at 98% of budget. | 100 | Final testing is complete at 134% of budget. | 100 | Complete. Costs were included in Equipment Deployment category. | 2015-03-20 16:32 | 2015-03-20 16:32 | 8044 | 8044 | Horizon Telecom, Inc.
NT10BIX5570120 | 2010 | Q4 | Q4 - 2010 | 676 | 1705 | FALSE | 8 | N/A | 0 |  | N/A | 75 | The EA will be completed within the 6 months timeframe required by the grant. We do not note 100% completion though until FONSI is received | 53 | N/A | 53 | Lessons learned from BTOP 1 provided valuable information in applying for ROWs for this award; namely, ensuring that Encroachment Agreements include all required elements and documents, at the time of submission, which we anticipate will expedite the process of ROWs for this grant. | 26 | Lessons learned from BTOP 1 provided valuable information in applying for permits required for this award; namely, ensuring that permit applications include all required elements and documents, at the time of submission, which we anticipate will expedite the processing or permits for this grant. | 10 | The goal is to identify all HUT locations within this quarter. | 0 | N/A | 1 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 08:35 | 2011-01-28 08:35 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2011 | Q1 | Q1 - 2011 | 1886 | 2688 | FALSE | 5 | We overestimated expenses related to engineering to this point. Until procurement of materials commences and construction activities start, it will be difficult to pass our estimates for expenditures. | 0 |  | na | 100 | If we receive the FONSI in the 4th quarter we will meet the projection. | 60 | We potentially will be back on track related to this activity, but given where we're at now, we choose to remain conservative. If behind in 4th quarter, we will be at projection by Y2Q1. | 30 | This activity closely tracks the network design. Given some of the pace of permitting at the start of Q4, we believe we'll be ahead of pace on this activity by end of quarter. | 10 | Construction permits come with successful ROW completion and review by NC DOT in the majority of the cases. Due to applications starting to happen in broader basis by completion of this report in April we believe we'll have closure on some by end of June, but given late start, will still be behind pace. We will recover by end of Y2Q1 we believe. | 5 | Discussions with the community colleges that are providing locations for the project are ongoing. We believe by end of the quarter we will have material agreement with all of these locations which is a small portion of site preparation. The exercised right to locate here from a legal standpoint is a part of the overall activity. | 2 | A small amount of equipment procurement may commence in June to light some of the IRU'd fiber in late summer, but cannot commence until FONSI, so this is not a given. Given this uncertainty, we project we'll be behind pace slightly. | 9 | With execution of IRU's and completion of some of the BTOP1 fiber builds, we believe we'll have approximately 150 of the planned miles secured and thus slightly ahead of schedule. | 0 | Given where we're at in the receipt of the FONSI and design, we don't anticipate deployment by end of June, meaning we're behind. | 9 | With execution of IRU's and completion of some of the BTOP1 fiber builds, we believe we'll have approximately 150 of the planned miles secured. We will test these fibers as we receive/complete them. | 2011-05-04 13:30 | 2011-05-04 13:30 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2011 | Q2 | Q2 - 2011 | 2948 | 3231 | FALSE | 20 | Even with a delay to start of construction, we believe that we will recover enough in the next quarter to be back on schedule. If not next quarter, we have no concerns with this being true by the following quarter. | 0 |  | N/A | 100 | N/A | 100 | N/A | 75 | Based on the timing of getting permits applied for, we expect to be right at schedule on this. | 65 | Due to a slower approval process with permitting agencies (primarily NC DOT), we project we will still be slightly behind the original forecast of around 76% complete. | 15 | We will see some more activity toward placement of huts, but it will take us two quarters to catch up due to a slower start. This does not impact our planned execution of the project as we will prioritize these toward areas where construction will start on the physical fiber. | 13 | If we complete execution of land easements and IRU's we believe we can in the quarter, this will drive some of our equipment procurement needs as it relates to huts. If that occurs, even with the delay to the start of the project, we expect to be right at our projection on this. | 12 | If all IRU's that are planned get executed, we will be able to meet our projection. | 13 | If we complete execution of land easements and IRU's we believe we can in the quarter, this will drive some of our equipment procurement needs as it relates to huts. If that occurs, even with the delay to the start of the project, we expect to be right at our projection on this. | 12 | We will test our fibers that we IRU as we acquire them, and if the IRU's happen, we will meet this projection. With the ramp up start time of our project starting, the projections to the baseline for this and many other areas of the project identified here are a bit fluid. | 2011-08-08 09:47 | 2011-08-08 09:47 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2011 | Q3 | Q3 - 2011 | 4226 | 3961 | FALSE | 20 | Even with a delay to start of construction, we believe that we will recover sufficiently in the next quarter to be back on schedule if we close on IRU's that we anticipate and can realize between 50-75 miles of conduit construction per month as we ramp up our construction efforts. Once at full capacity, we have advised our contractors that we want to meet 100 miles a month if possible. | 0 |  | NA | 100 | N/A | 85 | With some of the reroutes not officially approved to begin formal design work, we likely will have this effort slip in to the following quarter, where we would anticipate it being completed then. | 85 | While this is behind our baseline, with the approach we're now taking, we believe it in line with where we will be in the process. We would anticipate closing all of these activities out in first quarter of FY12. Because the areas not yet applied for are lower in priority for construction, being behind in baseline here is not of material concern to us in completing the project. | 80 | While this is behind our baseline, with the approach we're now taking, we believe it in line with where we will be in the process. We would anticipate closing all of these activities out in first quarter of FY12. Because the areas not yet applied for are lower in priority for construction, being behind in baseline here is not of material concern to us in completing the project. | 50 | We will start placement of huts in this quarter. Our desire is to have all easements required by end of the quarter. Acquisition of the easements is in many cases more than half of the challenge in getting the huts established. As such, if we secure all of them, we will consider this element half completed. We forecast all huts being placed by summer of 2012. | 1 | We anticipate making final selection of the equipment to be utilized in this quarter. We forecasted equipment expenditures too quickly based on how our selection criteria through an RFP and Proof of Concept lab worked out. Due to this, we likely will not procure any equipment in this quarter, but would anticipate making a great deal of orders in the first quarter of 2012, and be fully caught up on orders by summer of 2012, at least in terms of orders committed. | 33 | We anticipate building between 125-150 miles of the conduit during this quarter, and finalizing IRU acquisitions on another approximately 250 miles, which would put us at about 550 miles of our project, or about 33%. If we we are able to realize that amount of rate, we would be ahead of our baseline. | 0 | We anticipate making final selection of the equipment to be utilized in this quarter. We forecasted equipment expenditures too quickly based on how our selection criteria through an RFP and Proof of Concept lab worked out. Due to this, we likely will not procure any equipment in this quarter, but would anticipate making a great deal of orders in the first quarter of 2012, and be fully caught up on orders by summer of 2012, at least in terms of orders committed. | 0 | We test our fibers as we acquire or build, and as such we correspond projection for this line item relative to the project completion to be 67% by July 2012 and 100% by March 2013. We did not have significant budget as part of this line item in the budget as these costs were part of the construction line item and to date have not incurred expense for this. | 2011-11-22 15:07 | 2011-11-22 15:07 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2011 | Q4 | Q4 - 2011 | 4972 | 4647 | FALSE | 34 | We will be behind in expenditures to baseline by approximately 10% for this quarter. The winter months with required shutdowns around holiday's with DOT and slower permitting will impact the amount of work performed in late December and early January, and thus billings that will occur from our contractors. We expect to be back on pace in February and that will allow us to recover from this variance to budget by the 3rd quarter of 2012. Percent completion is based on dollars spent relative to budget. | 0 | NA | NA | 100 | NA | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on acquisition and design of miles relative to approved route. | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on number of rights of way acquired relative to number required for completion. | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on number of construction permits acquired relative to number required for completion. | 22 | We will still be ahead of schedule and expect to have the first 4-6 locations fully implemented per their now completed construction designs. | 50 | Once the vendor has been selected, we anticipate making a large first order so that we can begin receiving the equipment in advance of deployment. We are a bit concerned about potential manufacturing delays and due to that we anticipate making a large order initially for the backbone equipment. | 33 | We anticipate being right at baseline relative to dollars or slightly ahead based on forecasted efforts for the spring. | 15 | We will be behind to baseline for this metric due to a slower than anticipated closing of IRU's and construction start. Deployment of equipment moves fairly briskly, however, and we anticipate recovering in the next 2-3 quarters. | 25 | As more of our constructed fiber is deployed, we anticipate catching up on this metric, but acknowledge we will continue to be behind the baseline for another quarter. | 2012-02-13 12:41 | 2012-02-13 12:41 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2012 | Q1 | Q1 - 2012 | 6102 | 5653 | FALSE | 61 | We anticipate being slightly behind to baseline for the end of June quarter. Some of this relates to slower start and ramping up to full construction. We also have discovered that our ability to forecast payment for the end of quarter for construction contractors trails by several weeks due to confirmation of completeness for what's being billed, all documentation required for Davis-Bacon, lien waivers, etc. such that we can't always book dollars by the end of the quarter. However, we believe from a reporting standpoint this will correct by the September 2012 reporting period to where we're ahead of baseline. | 0 | NA | N/A | 100 | This activity is forecasted to be completed. | 100 | This activity is forecasted to be completed. | 100 | This activity is forecasted to be completed. | 99 | We anticipate to still be working with the US Forest Service on access to the Nantahala by end of next reporting quarter. This is only for about 13 miles of the entire project so is not a concern to us at this time on our ability to deliver on the project. | 100 | This activity is forecasted to be completed. | 66 | We expect to be back above baseline as we will make some fairly significant initial purchases in this current quarter. | 56 | We anticipate being right at baseline relative to dollars or slightly ahead based on forecasted efforts for the spring. | 25 | We will be behind to baseline for this metric due to a slower than anticipated closing of IRU's and construction start. Deployment of equipment moves fairly briskly, however, and we anticipate recovering in the next 2-3 quarters and being behind in this metric is not a concern to us in being able to deliver on the project. Once fiber completes, we can deploy fairly quickly. | 50 | As more of our constructed fiber is deployed, we anticipate catching up on this metric, but acknowledge we will continue to be behind the baseline for another quarter, but are not concerned with it impacting our ability to deliver on the project. | 2012-05-15 14:39 | 2012-05-15 14:39 | 5748 | 5748 | MCNC
NT10BIX5570120 | 2012 | Q2 | Q2 - 2012 | 7140 | 6197 | FALSE | 80 | Based on our baseline projection of 81%, we will be slightly below baseline, but essentially right on schedule. No concerns at this time with being able to deliver fully on the project. | 0 | N/A | N/A | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 77 | We are forecasting at being ahead of baseline (71%) by the end of the next reporting quarter | 33 | While we will still be below baseline, activity will start picking up in the last quarter of the year and we anticipate being back on baseline by Y3Q2. The variance to baseline here is solely tied to the delay in time of ordering equipment to when we forecasted. | 77 | We have tied network testing to network miles acquired or built, and as such we will be slightly ahead of baseline established of 71%. | 2012-08-20 07:34 | 2012-08-20 07:34 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2012 | Q3 | Q3 - 2012 | 7926 | 6667 | FALSE | 87 | We anticipate being slightly behind baseline of 90% as it relates to dollars expended, but ahead in terms of actual effort related to work in the project. | 0 |  | N/A | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | We are forecasting this activity to be 100% complete. | 100 | We are forecasting this activity to be nearly 100% complete. The ordering of customer premise equipment is being performed in close proximity to the need which is a bit different than what was planned initially. | 87 | This activity will nearly be on schedule with baseline of 88%. | 50 | Equipment deployment to CAI's is taking longer than anticipated. We, however, expect to catch up on this when all fiber is in place toward end of the first quarter of 2013. | 90 | We expect to be at or ahead of baseline on this function by end of next quarter. | 2012-11-16 14:22 | 2012-11-16 14:22 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2012 | Q4 | Q4 - 2012 | 9068 | 7840 | FALSE | 93 | Based on dollars spent at the end of the March quarter we anticipate being ahead of baseline of 90%. | 0 |  | N/A | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | We project this activity to be 100% complete next quarter | 99 | We project this activity to be at 99% complete next quarter, the only dependency being the Graham County build referenced above | 95 | We project this activity to be at baseline of 95% | 95 | We project this activity to be 100% complete next quarter | 2013-02-28 12:23 | 2013-02-28 12:23 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2013 | Q1 | Q1 - 2013 | 9752 | 8410 | FALSE | 99 | Dollar percent complete is 99%, but overall project is 100% complete | 0 |  | NA | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-05-16 07:54 | 2013-05-16 07:54 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2013 | Q2 | Q2 - 2013 | 10542 | 8925 | FALSE | 100 | This activity is 100% complete | 0 |  | N/A | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-08-09 15:17 | 2013-08-09 15:17 | 5479 | 5479 | MCNC
NT10BIX5570120 | 2013 | Q3 | Q3 - 2013 | 10998 | 9222 | FALSE | 100 | We came in under budget, so when measured against dollars budgeted, we are 99% complete. | 0 |  | N/A | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 97 | We came in under budget, so when measured against dollars budgeted, we are 97% complete. | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-10-29 11:54 | 2013-10-29 11:54 | 5479 | 5479 | MCNC
NT10BIX5570122 | 2010 | Q4 | Q4 - 2010 | 1236 | 2267 | FALSE | 15 | On target. | 25 | IN-KIND | On target. | 0 | N/A. Exempt. | 50 | On target. | 0 | N/A. This project does not include this activity. | 5 | On target. | 5 | On target. | 30 | On target. RFP development for network and data center equipment should be near completion by the end of next quarter. Vendor selections and approvals are anticipated for next quarter and subsequent quarters. | 5 | On target. IRU negotiations with Level 3 and upstream engineering and provisioning requirements are expected to progress as planned through the next reporting period. | 0 | On target. | 0 | On target. | 2011-02-18 19:34 | 2011-02-18 19:34 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2011 | Q1 | Q1 - 2011 | 2232 | 2861 | FALSE | 16 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports, overall project progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, incorporating both Federal funds and non-Federal share in-kind contributions where applicable in the milestones calculation, per Additional Guidance instructions. | 0 | In-Kind Capital Leases | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, milestone completion percentages for this category were based on work completed instead of actual budget expenditures. Going forward, progress toward this milestone category will be reported against actual expenditures, incorporating non-Federal share in-kind contributions as applicable per the Additional Guidance instructions. As part of our efforts to catch up to the Baseline Plan, the Florida Rural Broadband Alliance's General Counsel has been working closely with the Grants Office and the Program Office to finalize the format and acceptable language required in all lease documents for the project, including the in-kind leases. | 0 | N/A. Categorically exempt from Environmental Assessment. | 12 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. The variance from estimated Baseline Plan progress is the result of additional steps taken this past quarter to validate the preliminary network design against current network-to-network integration plans, and this process impacted subsequent engineering activities. In addition, in previous Performance Progress Reports, network design progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, per Additional Guidance instructions. In order to catch up to the Baseline Plan, we are pushing the design process move forward by synchronizing engineering activities among the two network regions. In addition, the General | 0 | N/A | 0 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In order to catch up with the Baseline Plan, steps have been taken to identify tower company requirements for site access, and permit acquisition procedures will be determined for each county in the core network footprint as the project transitions into its pre-deployment phase. | 0 | N/A. Please see Section #1, Item 2f for an explanation. | 12 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. The variance from estimated Baseline Plan progress is the result of additional steps taken this past quarter to validate the preliminary network design against network-to-network integration plans in order to establish equipment performance specifications. This process impacted the subsequent development of equipment procurement specifications, but as we move forward with remaining engineering tasks, we expect Equipment Procurement progress to get back on track with the Baseline Plan over the next quarter. | 15 | This milestone category is expected to remain on schedule. | 0 | This milestone category is expected to remain on schedule. | 0 | This milestone category is expected to remain on schedule. | 2011-05-20 19:50 | 2011-05-20 19:50 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2011 | Q2 | Q2 - 2011 | 3312 | 3418 | FALSE | 52 | This milestone category is expected to remain on schedule. | 45 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 90 | This milestone category is expected to remain on schedule. | 0 | N/A | 70 | This milestone category is expected to remain on schedule. | 60 | This milestone category is expected to remain on schedule. | 30 | This milestone will be behind plan. The request for bids will be released for materials, equipment, and services. The actual reciept use of the equipment will be in the following quarter, bringing this milestone percentage of completion back on track and in line with expectations for construction. | 30 | This milestone category is expected to remain on schedule. | 10 | This milestone category is expected to remain on schedule. | 10 | This milestone category is expected to remain on schedule. | 2011-08-25 12:45 | 2011-08-25 16:46 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2011 | Q3 | Q3 - 2011 | 4350 | 4031 | FALSE | 63 | The overall project has been redesigned to run in parallel which will begin to show significant progress the first half of 2012 as network deployment accelerates. | 73 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 63 | The network design and equipment selection have been completed. The site engineering and final engineering configurations will begin during the 4th quarter of 2011 and be substantially complete by the end of the 1st quarter of 2012. These efforts are running in parallel with the site selection, permittingand tower agreements and consistent with the revised project plan. | 0 | N/A | 63 | The permits and tower agreements are underway and significant progress is expected over the next two quarters. | 35 | Site preparation will begin for the new locations as tower agreements and construction permits are received. Significant progress this quarter will lead to the acceleration of deployment the 1st and 2nd quarter of 2012. | 48 | The request for Bid and selection will be completed this quarter. The equipment purchase orders and warehousing of equipment during this period will bring the equipment procurement back in line with baseline expectations. | 42 | The network build out and expansion beyond Hardee County will initiate the later part of Q4 2011. It is expected that much of the work this quarter will be in staging and preparation for deployment. | 48 | Although the equipment deployment will begin this quarter, significant progress will not begin until Q1 and Q2 of 2012. It is anticipated that the equipment deployment will come back within baseline by the middle of 2012. | 10 | Most of the network testing to date has come from the deployment of Hardee County. This work effort and spend will increase significantly during the first quarter of 2012 and is anticipated to come back to baseline by the 2nd quarter of 2012. | 2011-11-30 15:45 | 2011-11-30 15:45 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2011 | Q4 | Q4 - 2011 | 5376 | 5046 | FALSE | 74 | This milestone is expected to approach FRBAs original objectives by the end of the 1st Quarter of 2012 as construction kicks off. | 100 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 69 | The network design has been finalized and site/service engineering will bring the estimated percentage of completion back in line with original estimates by the end of the 1st quarter of 2012. | 0 | N/A | 69 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of batching the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 58 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 73 | Equipment procurement is well underway. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 66 | The network build begins in earnest during the first quarter of 2012. Although the project has been accelerated it will lag the original milestone until the end of the second quarter of 2012. | 73 | FRBA has accelerated the equipment deployment and will complete the data center build-out and have substantially completed a large number of towers during the first quarter, bring the equipment installation back in line with the original projections. Much of this equipment will be activated and go live during the second quarter of 2012. | 10 | Testing will begin during the 1st quarter of 2012 as approximate 18 new towers/links will go live. Much of the testing and link certification work will begin in earnest during the second quarter of 2012. | 2012-02-28 18:44 | 2012-02-28 18:44 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2012 | Q1 | Q1 - 2012 | 6316 | 5760 | FALSE | 73 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 82 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 68 | The network design has been finalized and site/service engineering was authorized at the end of the first quarter and expected to accelerate through the second quarter. Some restructuring of the tasking has shifted work effort and the structural engineering of a number of towers is taking longer than expected. However this will not slow down construction since the core routes and towers have been approved and site walk-outs and engineering has begun in earnest. This effort will align with the original milestones during the 3rd quarter of 2012. | 0 | N/A | 68 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 59 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. Approximately 20 towers are ready for permitting and construction to begin during the second quarter of 2012. | 82 | The majority of the equipment has been received with the exception of cabinets and steel. Construction is slated to begin during the second quarter of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 45 | Construction contracts were executed with G4S and rapid Systems during the first quarter. The network build begins in earnest during the second quarter of 2012. Although the project has been accelerated it will lag the original milestone until the end of the second half of 2012. | 82 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for approximately 20 installs during the second quarter of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the second quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Testing of the Sebring extension was completed during the1st quarter of 2012 and approximately 20 new towers/links will go live during the second quarter. Much of the testing and link certification work will begin in earnest during the second half of 2012. | 2012-05-29 11:02 | 2012-05-29 11:02 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2012 | Q2 | Q2 - 2012 | 7284 | 6269 | FALSE | 77 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 100 | In-Kind Capital Leases | This milestone category is expected to remain on schedule. | 0 | N/A | 74 | The network design has been finalized and site/service engineering was authorized at the end of the first quarter and expected to accelerate through the 2nd half of 2012. Some restructuring of the tasking has shifted work effort and the structural engineering of a number of towers is taking longer than expected. However this will not slow down construction since the core routes and towers have been approved and site walk-outs and engineering has begun in earnest. This effort will align with the original milestones during the 3rd quarter of 2012. | 0 | N/A | 74 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 59 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 79 | The majority of the equipment has been received with the exception of steel which is order on a site readiness basis. Construction is slated to begin during the second half of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 67 | Construction contracts were executed with G4S and Rapid Systems during the first quarter. The network build begins in earnest during the 2nd half of 2012. Although the project has been accelerated it will lag the original milestone until the end of the 2nd half of 2012. | 79 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for deployment during the 2nd half of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the next quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Much of the testing and link certification work will begin in earnest during the 2nd half of 2012. | 2012-08-29 17:57 | 2012-08-29 17:57 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2012 | Q3 | Q3 - 2012 | 8154 | 6787 | FALSE | 69 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 76 | In-Kind Capital | this milestone category is expected to remain on schedule. | 0 | N/A | 81 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work during the 3rd quarter of 2012. This work will accelerate throughout the second quarter and expected to be back on target during the 2nd half of 2012. | 0 | N/A | 81 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 64 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 65 | The majority of the equipment has been received with the exception of steel which is order on a site readiness basis. Construction is slated to begin during the second half of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 17 | Construction contracts were executed during the first quarter. The network build begins in earnest during the 2nd half of 2012. Although the project has been accelerated it will lag the original milestone until the end of the 2nd half of 2012. | 65 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for deployment during the 2nd half of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the next quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Much of the testing and link certification work will begin in earnest during the 2nd half of 2012. | 2012-11-29 16:39 | 2012-11-29 16:39 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2012 | Q4 | Q4 - 2012 | 9136 | 7929 | FALSE | 79 | ASSUMPTIONS: 85% of milestones completed on links that have leases and do not require lease amendments + 50% of milestones completed associated with links that do not have lease now or need a lease amendment | 90 |  | In-Kind Capital Leases | 0 | N/A | 85 | ASSUMPTIONS: 15% of designs can not be finalized due to failed permits & approvals on leases secured in quarter 1. | 0 | N/A | 85 | ASSUMPTIONS: Same as 2a | 100 | ASSUMPTIONS: All leases will be executed in quarter 1. | 63 | ASSUMPTIONS: Same as 2a | 42 | ASSUMPTIONS: Construction completed on 85% of links that currently have leases and do not require a lease amendment | 63 | ASSUMPTIONS: Same as 2h | 50 | ASSUMPTIONS: Same as 2h | 2013-03-12 16:17 | 2013-03-12 16:17 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2013 | Q1 | Q1 - 2013 | 9978 | 8533 | FALSE | 80 | Overall incremental progress in 2Q2013 will not be significant due to: (1) transition of work between sub-contractors for North sites, and (2) execution of lease amendments at commercial sites which are expected to be completed in mid-2Q2013. | 90 | In-Kind Assets | In-kind capital leases | 0 | N/A | 75 | Incremental progress in 2Q2013 for Network Design will be limited to sites where lease amendments are executed in early May. Design work for sites where lease amendments are executed in later May will be pushed into 3Q2013 pending completion of dependencies listed above. | 0 | N/A | 75 | Incremental progress in 2Q2013 for Permits will be limited to sites where lease amendments are executed in early May. Permits for sites where lease amendments are executed in later May will be pushed into 3Q2013 pending completion of dependencies listed above. | 0 | N/A | 62 | Minimal incremental Equipment Purchases will be made in 2Q2013 pending executed lease amendments, Design Work, Permits and finalization of IRU re-configuration negotiations, as described in 2c-f. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. | 57 | Incremental progress in 2Q2013 for Network Build will be limited to sites where lease amendments were executed in early May and Permits were secured by the new sub-contractor for North sites. Construction will begin on a broader scale in 3Q2013 pending the completion of the dependencies listed above. | 62 | Minimal incremental Equipment Purchases will be made in 2Q2013 pending executed lease amendments, Design Work, Permits and finalization of IRU re-configuration negotiations, as described in 2c-f. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. | 10 | Minimal incremental Network Testing will be completed in 2Q2013 and will be pushed to 3Q2013 pending the completion of dependent construction activities listed in 2h) above. | 2013-05-29 17:24 | 2013-05-29 17:24 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2013 | Q2 | Q2 - 2013 | 10778 | 9058 | FALSE | 86 | Overall incremental progress in 3Q2013 will be significant with many of our hurdles being cleared. Construction has already seen a significant advance and pathing/integration is scheduled to conclude for the majority of sites by the end of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 90 | In-Kind Assets | In-kind capital leases | 0 | N/A | 75 | Final Network Design will be submitted in 3Q2013 essentially locking the design in place all the way to grant closeout. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 0 | N/A | 75 | Majority of Leases and Lease Amendments have been approved and received; paving the way for remaining building permits to be applied for and received in a timely fashion. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 0 | N/A | 62 | Majority of all required site equipment will be procured during the remainder of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 57 | Construction will commence on a broader scale in 3Q2013. Firm projections of substantial Network Build completion are already targeted for the end of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 62 | Majority of all procured equipment will be deployed in 3Q2013 in correlation with the substantial completion of the Network Build.This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 50 | It is estimated that a significant portion of network testing will begin and possibly conclude in 3Q2013 with any remaining site requiring testing to occur in 4Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 2013-08-28 01:21 | 2013-08-28 01:21 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2013 | Q3 | Q3 - 2013 | 11416 | 9528 | FALSE | 100 | To be completed in full. | 100 |  | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 100 | To be completed in full. | 100 | To be completed in full. | 100 | To be completed in full. | 2013-11-26 20:35 | 2013-11-26 20:35 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2013 | Q4 | Q4 - 2013 | 11918 | 10083 | FALSE | 100 | Completed | 100 |  | Completed | 0 | N/A | 100 | Completed | 0 | N/A | 100 | Completed | 0 | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-02-28 10:44 | 2014-02-28 10:44 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2014 | Q1 | Q1 - 2014 | 12216 | 10387 | FALSE | 100 | Scheduled to be Complete | 100 |  | Scheduled to be Complete | 0 | N/A | 100 | Scheduled to be Complete | 0 | N/A | 100 | Scheduled to be Complete | 0 | N/A | 100 | Scheduled to be Complete | 100 | Scheduled to be Complete | 100 | Scheduled to be Complete | 100 | Scheduled to be Complete | 2014-05-20 10:54 | 2014-05-20 10:54 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | 2014 | Q2 | Q2 - 2014 | 12430 | 10621 | FALSE | 100 | Complete | 100 |  | Complete | 0 | N/A | 100 | Complete | 0 | N/A | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-08-15 18:43 | 2014-08-15 18:43 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC
NT10BIX5570123 | 2010 | Q4 | Q4 - 2010 | 604 | 1622 | FALSE | 15 | N/A | 100 | Tower Site leases | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 75 | N/A | 0 | N/A | 3 | N/A | 10 | N/A | 15 | N/A | 0 | N/A | 2011-01-27 13:41 | 2011-01-27 13:41 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2011 | Q1 | Q1 - 2011 | 2066 | 2778 | FALSE | 25 | During the next quarter (Y1Q4) we anticipate having site development contracts in place; network equipment ordered and installed on existing towers; and deployment of the network where we can connect existing tower equipment to the Tribes network. Construction season is behind approximately one month due to late snow and cold wet spring conditions; site development and construction actives will ramp up during the next two quarters, which will get us back on track. | 100 |  | On track | 100 | On track | 100 | On track | 100 | Expect to have all utility service line agreements with BIA complete and utility corridor rights of way agreements in place with private landowners. | 100 | Expect to be back on track and have permitting completed | 50 | Expect road construction/reconstruction work to be underway for site development and utility installation in progress. | 30 | Expect to have network equipment purchased; tower contracts under negotiations well underway. | 20 | Expect to have network equipment installed on three of the seven existing towers. | 15 | Expect to be on track | 0 | NA too early | 2011-05-16 19:40 | 2011-05-16 19:40 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2011 | Q2 | Q2 - 2011 | 3332 | 3428 | FALSE | 40 | Infrastructure should be 70% procured but installation timing and logistics (concrete dry/set time) will set back the implementation accomplishment rate. Through this next quarter project activities will be strongly tied to site development and construction, where network wireless equipment installation and service capacity will be deployed across the western side of the Reservation. Work on the eastern side of the Reservation will focus on resolving the TU 71 utility access issue. | 100 | Tower Land Leases | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 60 | Contracts for all network wireless equipment, utilities and towers will be awarded. | 40 | Network build out will prioritize the western loop of existing and new towers connected. In the Baseline the projection was based on getting towers erected across the Reservation; the project will focus on sections and get service up in phases that offer redundancy and looped pathways. | 20 | Equipment deployment will mirror network build out; once towers are constructed the equipment can be installed in the prioritized loops. | 10 | Testing will docus on delivery to targeted CAI's along the pathways developed in phases. | 2011-08-26 15:38 | 2011-08-26 15:38 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2011 | Q3 | Q3 - 2011 | 3976 | 3826 | FALSE | 60 | Narrowly lagging behind baseline due to anticipated weather set backs related to last mile equipment deployment. | 100 | Tribe-Prvt agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Wireless equipment procured for all existing towers and six of the new towers | 75 | Six towers constructed; wireless equipment installed on Teaken, Stoney Pt, Hubbard, Peck, TU 17, TU 99-101, Culdesac towers | 60 | Network equipment on line for middle and last mile across the western half of the Reservation. | 25 | Testing complete for Stoney Pt, Hubbard, Peck sites | 2011-11-10 16:57 | 2011-11-10 16:57 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2011 | Q4 | Q4 - 2011 | 5190 | 4856 | FALSE | 72 | Narrowly lagging behind baseline due to anticipated weather set backs related to last mile equipment deployment. | 100 | Tribe-Prvt agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Middle mile complete on 11 of the 13 link paths; Last mile access points installed on 4 of the 11 designated towers. | 65 | Middle mile 85% complete; Last mile 40% complete | 75 | Testing complete for Middle mile ring, Stoney Pt, Hubbard, Peck & Culdesac sites | 2012-02-22 14:32 | 2012-02-22 14:32 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2012 | Q1 | Q1 - 2012 | 6028 | 5613 | FALSE | 85 | Subscriber connection behind the baseline but is NPT-IS tech staff priority during the next quarter. | 100 | Pvt Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Middle & Last mile equipment deployment underway | 95 | Middle mile network equipment installation at Nuxoll, KIYE & TU 64 will be ealy Q2 2012; Last mile access point installation well underway in Q2 2012 | 95 | Testing to be done on Nuxoll - KIYE-TU 64 middle link & at last mile sites: Hubbard, Peck, Beard, TU 60, TU 17 to be initiated in Q2 2012. | 2012-05-10 16:37 | 2012-05-10 16:37 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2012 | Q2 | Q2 - 2012 | 7060 | 6157 | FALSE | 89 | With construction activities complete the project staff and technicians can focus on subscriber connection and marketing. The construction schedule for the project is in line with baseline. | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 97 | The KIYE-TU 64 middle mile link is being troubleshot and should be complete enabling last mile testing to get underway by the end of Q2 | 2012-08-14 13:07 | 2012-08-14 13:07 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2012 | Q3 | Q3 - 2012 | 7980 | 6696 | FALSE | 97 | During Q4 2012 efforts will be focused on subscriber connection and completing the in kind match obligation. | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Deployment of neighborhood solution equipment is underway with 3 of the 4 site lease agreements with landowners approved by tribal Resolution. Tech staff have initiated radio configuration and installations are being scheduled. | 99 | The neighborhood solution equipment will be tested as it gets deployed. Winter weather may become a factor for field technicians. | 2012-11-20 14:03 | 2012-11-20 14:03 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2012 | Q4 | Q4 - 2012 | 9142 | 7957 | FALSE | 100 | Complete | 100 | Site Lease Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-03-22 13:38 | 2013-03-22 13:38 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2013 | Q1 | Q1 - 2013 | 9628 | 8346 | FALSE | 99 | We are line with baseline and will work on project details remaining to reach completion. | 100 | Site Use Agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-08 13:38 | 2013-05-08 13:38 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2013 | Q2 | Q2 - 2013 | 10716 | 9021 | FALSE | 100 | Complete | 100 | Site Use Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-23 16:56 | 2013-08-23 16:56 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570123 | 2013 | Q3 | Q3 - 2013 | 11458 | 9571 | FALSE | 100 | Complete | 100 | Site Use Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-12-09 19:13 | 2013-12-09 19:13 | 6176 | 6176 | Nez Perce Tribe
NT10BIX5570125 | 2010 | Q4 | Q4 - 2010 | 1224 | 2254 | FALSE | 11 | n/a | 47 | Administration | n/a | 82 | n/a | 65 | n/a | 61 | n/a | 24 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-02-18 15:40 | 2011-02-18 15:40 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2011 | Q1 | Q1 - 2011 | 2340 | 2915 | FALSE | 14 | None | 57 | Administration | None | 88 | None | 85 | None | 84 | None | 59 | None | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 2011-05-26 12:33 | 2011-05-26 12:33 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2011 | Q2 | Q2 - 2011 | 3286 | 3405 | FALSE | 36 | No anticipated variance at this time. | 66 | Administration | No anticipated variance at this time. | 100 | No anticipated variance at this time. | 97 | No anticipated variance at this time. | 87 | No anticipated variance at this time. | 77 | No anticipated variance at this time. | 100 | No anticipated variance at this time. | 18 | No anticipated variance at this time. | 34 | No anticipated variance at this time. | 0 | No anticipated variance at this time. | 13 | No anticipated variance at this time. | 2011-08-23 17:38 | 2011-08-23 17:38 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2011 | Q3 | Q3 - 2011 | 4042 | 3861 | FALSE | 23 | Baseline had a forecast of 53%. See below categories to see shifting. All updates provided below are based on information known as of 11/10/11. | 69 | Administration | The baseline had projected 75%. Due to delay in construction beginning, this shifted as well. | 100 | No change. | 100 | Baseline projected 98% we are tracking to have this milestone completed by the end of the quarter. | 27 | The Baseline projected 90%. The variance is largely due to the budgeted $110,000 for node site acquisition, which has not yet occurred. This item is being evaluated. | 49 | The baseline had projected 93%. The variance is due to the delay in receiving FONSI and construction fees that have not yet occurred as construction has not begun. | 0 | The baseline had projected 100%. The variance is due to the delay in receiving FONSI which trickled down to delay in equipment procurement for site preparation work to occur. We do not forsee expending these funds in this quarter. | 26 | The baseline had projected 36%, delay in FONSI created delay in equipment procurement. With the FONSI being projected to be acquired this quarter, material procurement will pick up. | 4 | The baseline had projected 47%. This was delayed due to FONSI not occuring last quarter and construction not being able to begin. With FONSI likely being acquired this quarter, this percent will increase in future quarters, weather depending. | 0 | The baseline had projected 53% based on network build. This has a trickle down effect from network build. | 0 | The baseline had projected 25% based on the network build. The has a trickle down effect from the network build. | 2011-11-14 19:32 | 2011-11-14 19:32 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2011 | Q4 | Q4 - 2011 | 5264 | 4932 | FALSE | 30 | Baseline had a forecast of 67% see below categories to see shifting. | 89 | Administration | The baseline had projected 84%, this will be addressed in the upcoming budget realignment as dollars need to be shifted to be realigned with the current build and scope of the project. | 100 | No change | 100 | Baseline projected 98% we completed this work. | 48 | The Baseline projected 94%. The variance is largely due to a budgeted $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 73 | The baseline had projected 96%. The variance is due to the delay in receiving our FONSI and construction fees that have not yet been incurred as construction related activities are just beginning. | 0 | The baseline had projected 100%. With the delay in FONSI our Node buildings have not yet been acquired. We have completed the RFP but delivery of the item will likely occur in quarter 2 of 2012. | 41 | The baseline had projected 49%. Equipment procurement is occurring and most RFP's and orders are in process. Delivery from vendors is taking longer than anticipated with the demands of the broadband projects occurring along similar timelines. | 6 | The baseline had projected 63% This continues to lag behind due to delay in FONSI and now more recently with delay in material delivery. If the material comes in ahead of current projected delivery dates from the vendor then this percentage would increase. | 0 | The baseline had projected 77% based on network build. This has a trickle down effect from Network Build. | 0 | The baseline had projected 40% based on the network build, this has a trickle down effect from Network Build. | 2012-02-24 20:07 | 2012-02-24 20:07 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2012 | Q1 | Q1 - 2012 | 6096 | 5650 | FALSE | 57 | Baseline had a forecast of 97% see below categories to see shifting. | 100 | Administration | The baseline had projected 93%, this will be addressed in the upcoming budget realignment as dollars need to be shifted to be realigned with the revised project route and scope of the project. | 100 | No change | 100 | Baseline projected 99%; we completed this work. | 46 | Baseline had projected 97%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change | 94 | Baseline had projected 100%. With the delay in FONSI our Node buildings have not yet been acquired. Vendor has been selected and this work will be beginning this quarter. | 100 | Baseline had projected 83%. This number will shift with the upcoming budget realignment. | 24 | Baseline had projected 93%. This continues to lag behind due to the delay in FONSI that occurred and the delay in material delivery. | 12 | The baseline had projected 92% based on the network build. This continues to have a trickle down effect from Network Build. | 27 | The baseline had a projected 63% based on network build projections, this has a trickle down effect. | 2012-05-15 13:37 | 2012-05-15 13:37 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2012 | Q2 | Q2 - 2012 | 7208 | 6231 | FALSE | 81 | Baseline had a forecast of 99%. See categories below for changes. | 100 | Administration | Baseline had projected 97%. This will be addressed in an upcoming budget realignment. Dollars need to be shifted for proper realignment with revised project route and scope of project. | 100 | No change | 100 | No change | 46 | Baseline had projected 100%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 42 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of September. This will be addressed in an upcoming budget realignment. | 30 | Baseline had projected 79%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2012-08-22 13:22 | 2012-08-22 13:22 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2012 | Q3 | Q3 - 2012 | 8164 | 6792 | FALSE | 84 | Baseline had a forecast of 100%. See Categories below for changes. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. Dollars need to be shifted for proper realignment with revised project route and scope of project. | 100 | No change | 100 | No change | 66 | Baseline had projected 100%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 43 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of December. This will be addressed in an upcoming budget realignment | 35 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2012-11-29 23:27 | 2012-11-29 23:27 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2012 | Q4 | Q4 - 2012 | 9152 | 7976 | FALSE | 89 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change | 100 | No change | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 44 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of December. This will be addressed in an upcoming budget realignment | 22 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-03-28 14:00 | 2013-03-28 14:00 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2013 | Q1 | Q1 - 2013 | 9942 | 8514 | FALSE | 96 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No Change | 100 | No Change | 75 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Baseline had projected 100%. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 52 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%.This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 48 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-05-28 16:08 | 2013-05-28 16:08 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2013 | Q2 | Q2 - 2013 | 10630 | 8975 | FALSE | 100 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No Change | 100 | No Change | 77 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Baseline had projected 100%. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 57 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%.This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 20 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-08-19 05:04 | 2013-08-19 05:04 | 7691 | 7691 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | 2013 | Q3 | Q3 - 2013 | 12452 | 10634 | FALSE | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 |  | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 2014-08-22 16:25 | 2014-08-22 16:25 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570126 | 2010 | Q4 | Q4 - 2010 | 1324 | 2348 | FALSE | 1 | N/A | 0 | N/A | N/A | 90 | N/A | 50 | Originally planned to be 15% complete during Q1-2011. This percentage represented preliminary design work only. Detailed engineering was not originally planned to begin until the Environmental Assessment (EA) was complete. We have now moved up detailed engineering efforts ahead of the EA completion and will include in EA extension budget. This equates to a planned 50% complete this quarter. It is expected that Network Design quarterly Percent Complete figures will remain ahead of schedule until eventual completion in Q3-2011 as planned. | 0 | Originally planned to be 15% complete during Q1-2011. Rights-of-Way was originally planned to begin prior to detailed engineering efforts. It will now begin as part of the detailed engineering process which starts this quarter and will extend beyond completion of the detailed engineering process. It is expected to be back in line with the baseline in Q2-2011. | 0 | Originally planned to be 15% complete during Q1-2011. Permitting was originally planned to begin prior to detailed engineering efforts. It will now begin as part of the detailed engineering process which starts this quarter and will extend beyond completion of the detailed engineering process. It is expected to be back in line with the baseline in Q2-2011. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-23 10:48 | 2011-02-23 10:48 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2011 | Q1 | Q1 - 2011 | 2156 | 2823 | FALSE | 12 | No change from the baseline | 0 | N/A | N/A | 100 | No change from the baseline | 75 | No change from the baseline | 35 | No change from the baseline | 35 | No change from the baseline | 10 | No change from the baseline | 15 | No change from the baseline | 10 | No change from the baseline | 10 | No change from the baseline | 0 | No change from the baseline | 2011-05-18 18:37 | 2011-05-18 18:37 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2011 | Q2 | Q2 - 2011 | 2924 | 3219 | FALSE | 15 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 65 | No change from the baseline plan. | 65 | No change from the baseline plan. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 25 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 0 | No change from the baseline plan. | 2011-08-04 13:06 | 2011-08-04 13:06 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2011 | Q3 | Q3 - 2011 | 3984 | 3830 | FALSE | 16 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 0 |  | N/A | 100 | Complete | 100 | Complete | 85 | No change from the baseline. | 85 | No change from the baseline. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 35 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 5 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 2011-11-10 19:19 | 2011-11-10 19:19 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2011 | Q4 | Q4 - 2011 | 5370 | 5038 | FALSE | 30 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 20 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 50 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 30 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 20 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 5 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 2012-02-28 17:15 | 2012-02-28 17:15 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2012 | Q1 | Q1 - 2012 | 6146 | 5675 | FALSE | 60 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 98 | Slightly behind baseline. It is anticipated that everything but Caltrans permits will be complete. | 98 | Slightly behind baseline. It is anticipated that everything but Caltrans permits will be complete. | 30 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 60 | Slightly behind schedule and should be complete next quarter. | 60 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 15 | Behind schedule due to construction delays. | 15 | Behind schedule due to construction delays. | 2012-05-16 19:57 | 2012-05-16 19:57 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2012 | Q2 | Q2 - 2012 | 7082 | 6168 | FALSE | 70 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 50 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 95 | Slightly behind schedule but significant progress from last quarter. Should be complete next quarter. | 70 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 25 | Behind schedule due to construction delays. Significant progress will be made next quarter. | 20 | Behind schedule due to construction delays. | 2012-08-15 14:59 | 2012-08-15 14:59 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2012 | Q3 | Q3 - 2012 | 8044 | 6728 | FALSE | 86 | Significant progress will be made on underground construction and fiber optic cable installation this quarter. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 | N/A | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 75 | Significant progress on underground construction will allow for substantial progress on cabinet and hut site preparation. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 97 | All but the last few equipment items will have been purchased. | 86 | Significant progress will be made on underground construction and fiber optic cable installation this quarter. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 35 | Behind schedule due to construction delays. Significant progress will be made again next quarter. | 35 | Behind schedule due to construction delays. Testing will closely follow equipment deployment. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2012 | Q4 | Q4 - 2012 | 8764 | 7559 | FALSE | 95 | Slightly behind the baseline due to initial underground construction delays. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 85 | Continued progress on underground construction will allow for increased progress on cabinet and hut site preparation. Still slightly behind schedule on baseline. | 100 | No change from the baseline. | 95 | Slightly behind the baseline due to initial underground construction delays. | 60 | Continued progress on site preparation will allow for increased progress on equipment deployment. Still behind schedule on baseline. | 60 | Continued progress on equipment deployment will allow for increased progress on network testing. Still behind schedule on baseline. | 2013-02-13 18:59 | 2013-02-13 18:59 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2013 | Q1 | Q1 - 2013 | 9988 | 8538 | FALSE | 99 | Only last few items to wrap up before end of grant period. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 99 | Only last few items to wrap up before end of grant period. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be a bit of work to be done for these items while the Network Build and Overall Project is still expected to reach 99%. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be a bit of work to be done for these items while the Network Build and Overall Project is still expected to reach 99%. | 2013-05-29 18:50 | 2013-05-29 18:50 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2013 | Q2 | Q2 - 2013 | 10546 | 8927 | FALSE | 100 | Only last few items to wrap up before end of grant period. Anticipated expenditures are expected to be 110% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline | 100 | No change from the baseline. | 99 | Only last few items to wrap up before end of grant period. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be some work to be done for these items while the Network Build and Overall Project are expected to reach higher percentages. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be some work to be done for these items while the Network Build and Overall Project are expected to reach higher percentages. | 2013-08-09 17:38 | 2013-08-09 17:38 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2013 | Q3 | Q3 - 2013 | 11264 | 9423 | FALSE | 100 | Anticipated expenditures are expected to be 111% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 2013-11-15 12:11 | 2013-11-15 12:11 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2013 | Q4 | Q4 - 2013 | 11828 | 10005 | FALSE | 100 | Anticipated expenditures are expected to be 117% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 98 | Final sections of network turn-up and testing left to complete. | 100 | No change from the baseline. | 98 | Final sections of network turn-up and testing left to complete. | 2014-02-14 18:52 | 2014-02-14 18:57 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2014 | Q1 | Q1 - 2014 | 12240 | 10416 | FALSE | 100 | Anticipated expenditures are expected to be 118% of our overall budget. The overage will be funded entirely by additional CVIN matching funds. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 2014-05-27 20:09 | 2014-05-27 20:09 | 6105 | 6105 | CVIN, LLC
NT10BIX5570126 | 2014 | Q2 | Q2 - 2014 | 12620 | 10888 | FALSE | 100 | Actual Expenditures are 118% of overall budget. | 0 | true | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 2014-12-15 12:04 | 2014-12-15 12:04 | 6105 | 6105 | CVIN, LLC
NT10BIX5570127 | 2010 | Q4 | Q4 - 2010 | 1038 | 2077 | FALSE | 2 | See 2g for reason for variance | 0 | Connect Anchors | No Variance | 100 | No Variance, excluding any potential post FONSI activities | 29 | No Variance | 29 | No Variance | 29 | No Variance | 0 | No Variance | 0 | RFP's will be awarded during this QTR for materials and equipment with the initial orders being placed in Q1-2011. The delay in confirming availability of matching funds to pay for the planned equipment and materials delayed the initial RFP release and UTOPIA will not actually incur the initial costs originally planned for the end of Q1-2011 until the first month of Q2-2011. A Waiver for proportional draw down has been requested to allow the project to continue as planned until matching funds are available. Matching funds will be available sometime during YR1-Q4 (Q2-2011). The milestone baseline for equipment procurement should be fully recovered in YR1-Q4 (Q2-2011) | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-10 10:19 | 2011-02-10 10:19 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2011 | Q1 | Q1 - 2011 | 2022 | 2756 | FALSE | 12 | See 2g for reason for variance | 9 |  | No Variance. Community Anchor institutions will be connected during the QTR with progress as planned. This projection anticipates 37 completed community anchor institution connections. | 100 | No Variance, excluding any potential post FONSI activities | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of network design engineering. | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of secured Rights of Way. | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of secured Permitting and other approvals. | 9 | No Variance. Site preparations will begin during the QTR as planned. This projection anticipates site preparations necessary to support 8 miles of fiber network construction. | 27 | As indicated in section 2 above, the delay in Q4-2010 confirming availability of matching funds to pay for the planned equipment also delayed the initial RFP release and UTOPIA will not actually incur the costs originally planned for the end of Q1-2011 until Q2-2011. A Waiver for proportional draw down was approved to allow the project to continue as planned until matching funds are available. Matching funds will be available sometime during YR1-Q4 (Q2-2011).The milestone baseline for equipment procurement will be partially recovered during Q2-2011 and fully recovered by the end of this QTR. This projection anticipates the purchase of Equipment necessary to support 8 miles of fiber network construction this QTR and an additional 31 miles next QTR. | 9 | No Variance. Construction activities will start during the QTR with progress as planned. This projection anticipates 8 miles of fiber network construction. | 9 | No Variance. Equipment will be deployed during the QTR with progress as planned. This projection anticipates equipment deployment necessary to support 8 miles of fiber network construction and connections to 37 anchor institutions. | 9 | No Variance. Network testing will commence during the QTR with progress as planned. This projection anticipates testing as required to support 8 miles of fiber network construction and connections to 37 community anchor institutions | 2011-05-13 15:27 | 2011-05-13 15:27 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2011 | Q2 | Q2 - 2011 | 2976 | 3245 | FALSE | 17 | Milestone baseline will continue into this quarter. Reasons for variance are indicated below. Overall the project continues to track closely with most key indicators, but cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 22 |  | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 70 community anchor institutions will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic Structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, Orem, and West Valley. The construction permits and other approvals are dependent on securing these sites, and completing the network design and detailed route engineering. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 8 | Milestone baseline variance continues due to delays in securing permits and other approvals for the Rights of Way. Six points of interconnection will be completed during this quarter with six additional points of interconnect in process. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 28 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment will be ordered but costs will not be incurred during this quarter as planned. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 2011-08-09 13:55 | 2011-08-09 13:55 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2011 | Q3 | Q3 - 2011 | 4316 | 4008 | FALSE | 27 | Milestone baseline variance will continue into this quarter. Reasons for variance are indicated below. Overall the project continues to track behind with most key indicators as cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q1-2012. | 25 |  | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. An additional 50 community anchor institutions will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent upon securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent upon securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Construction Permits and Other Approvals lags slightly behind the completion of the Network Design. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 20 | Milestone baseline variance continues due to delays in securing permits and other approvals for the Rights of Way. Six additional points of interconnection will be completed during this quarter with six more points of interconnect in process. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 30 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment is ordered and costs will be incurred during this quarter as planned. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 2011-11-29 13:54 | 2011-11-29 13:54 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2011 | Q4 | Q4 - 2011 | 5224 | 4888 | FALSE | 42 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. Overall the project will track closely with most key indicators as cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2012. | 40 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 45 | Milestone baseline will be exceeded during this Quarter. Sixteen additional points of interconnection will be completed during this quarter with six more progress. | 55 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q3-2012. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 2012-02-23 16:14 | 2012-02-23 16:14 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2012 | Q1 | Q1 - 2012 | 6032 | 5615 | FALSE | 52 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q3-2012. | 38 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 51 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. Twenty additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q3-2012 | 35 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 2012-05-10 19:59 | 2012-05-10 19:59 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2012 | Q2 | Q2 - 2012 | 7002 | 6128 | FALSE | 67 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q4-2012. | 38 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q33-2012. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 51 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. Twenty-nine additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q4-2012 | 52 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 2012-08-10 12:15 | 2012-08-10 12:15 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2012 | Q3 | Q3 - 2012 | 8078 | 6745 | FALSE | 67 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q1-2013. | 44 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 14 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q1-2013 | 52 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 2012-11-27 15:31 | 2012-11-27 15:31 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2012 | Q4 | Q4 - 2012 | 8914 | 7696 | FALSE | 76 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2013. | 39 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 6 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q2-2013 | 54 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q2-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 2013-02-22 15:22 | 2013-02-22 15:22 | 6034 | 6034 | Utopia
NT10BIX5570127 | 2013 | Q1 | Q1 - 2013 | 10040 | 8571 | FALSE | 86 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2013. | 45 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of the award period. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 18 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q2-2013 | 54 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 2013-05-31 18:29 | 2013-05-31 18:29 | 6069 | 6069 | Utopia
NT10BIX5570127 | 2013 | Q2 | Q2 - 2013 | 10826 | 9085 | FALSE | 96 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. Project will be completed by September 30, 2013. | 100 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of the award period. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 100 | The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 65 | Site prep for 62 sites will be completed and the project will be completed by September 30, 2013. | 92 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. Project will be completed by September 30, 2013 | 98 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 92 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 98 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 2013-08-30 14:22 | 2013-08-30 14:22 | 6069 | 6069 | Utopia
NT10BIX5570127 | 2013 | Q3 | Q3 - 2013 | 12300 | 10474 | FALSE | 100 | Project has been completed but will continue to see a variance in our baseline as we continue to occur some costs as final inspections and retention are released. | 100 | N/A | Project has been completed. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities were implemented. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The site prep for 62 sites have been completed. Project has been completed. | 100 | All of the equipment has been purchased and deployed. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 2014-07-03 11:28 | 2014-07-03 11:28 | 6069 | 6069 | Utopia
NT10BIX5570128 | 2010 | Q4 | Q4 - 2010 | 1112 | 2151 | FALSE | 24 | N/A | 0 |  | N/A | 100 | N/A | 74 | N/A | 78 | N/A | 78 | N/A | 40 | N/A | 21 | N/A | 17 | N/A | 16 | N/A | 10 | N/A | 2011-02-11 18:03 | 2011-02-11 18:03 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2011 | Q1 | Q1 - 2011 | 2182 | 2836 | FALSE | 45 | Overall project was slowed down by the Environmental Assessment process. |  |  | N/A | 100 | N/A | 92 | N/A | 94 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 94 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 60 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 42 | Overall project was slowed down by the Environmental Assessment process. | 40 | Overall project was slowed down by the Environmental Assessment process. | 16 | N/A | 5 | Overall project was slowed down by the Environmental Assessment process. | 2011-05-19 16:21 | 2011-05-19 16:21 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2011 | Q2 | Q2 - 2011 | 2938 | 3226 | FALSE | 25 | Overall Project was slowed down by the Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 60 | N/A | 60 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 60 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 0 | This section is misleading. Based on discussions with the Project's cash match lender, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. | 21 | Overall Project was slowed down by the Environmental Assessment process. | 25 | Overall Project was slowed down by the Environmental Assessment process. | 17 | Overall Project was slowed down by the Environmental Assessment process. | 5 | Overall Project was slowed down by the Environmental Assessment process. | 2011-08-05 16:22 | 2011-08-05 16:22 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2011 | Q3 | Q3 - 2011 | 3914 | 3795 | FALSE | 27 | Overall Project was slowed down by the Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 90 | Overall Project was slowed down by the Environmental Assessment process. | 90 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 90 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 0 | This section is misleading. Based on discussions with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured but none of those sites have been brought on line. | 67 | Troy Cable will award and contract various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. | 33 | Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of five (5) Aerial Crews and two (2) Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. | 61 | Troy Cable will award and contract various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. | 35 | Network testing is based on fiber deployment and build out. Troy Cable has implemented an aggressive plan to catch up to the projections as outlined in the original baseline. | 2011-11-07 17:00 | 2011-11-07 17:00 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2011 | Q4 | Q4 - 2011 | 5374 | 5044 | FALSE | 48 | Overall Project was delayed from original Baseline due to Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2012. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 90 | Overall Project was delayed from original Baseline due to Environmental Assessment process. | 90 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 90 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Sites with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both Enterprise sites will have the DWDM Network installed next quarter. Next quarter, the following existi | 61 | Troy Cable will launch a Request for Proposal during the First Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and has continued ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (â€œOSS/BSSâ€) is scheduled to go on line March 1, 2012. | 38 | Due to lead times on materials the Project did not get as many miles constructed as projected after receiving the FONSI. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on twenty-eight (28) of the fifty-two (52) job segments. The construction crews consist of three (3) Underground crews and three (3) Aerial crews. The addition of the Underground and Aerial crews reflects the progress Troy Cable is making to catch-up to the Baseline projections. | 56 | Troy Cable will launch a Request for Proposal during the First Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and has continued ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (â€œOSS/BSSâ€) is scheduled to go on line March 1, 2012. | 60 | Network testing is based on fiber deployment and Build Out. Troy Cable has implemented an aggressive plan to catch up to the Baseline projections. | 2012-02-28 17:56 | 2012-02-28 17:56 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2012 | Q1 | Q1 - 2012 | 6014 | 5606 | FALSE | 62 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters Performance Progress Report projection was related to an aggressive | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 88 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-five (45) of the fifty-four (54) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bill of material for current job segments. | 91 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 91 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both Enterprise sites will have the DWDM Network installed next quarter. Next quarter, the following existin | 92 | The Team has awarded contracts and continues to order and receive materials from the awarded Vendors for additional equipment and materials for Request for Proposals released during previous quarters like: DWDM Network; Switches; Routers; Access Gear ("ADTRAN"); Provisioning; Light Meters; Bucket Trucks; and Access Controllers. Troy Cable has ordered and begun receiving equipment for the Headend Upgrade for Fiber Distribution System. The Engineering Team has deployed the following network equipment: DWDM Network Equipment; Routers; Switches; and Access Gear. | 49 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable estimates completing 475 fiber miles of the total 595 mile Project by June 30, 2012. This estimate represents 79.83% completion. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 75 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable estimates completing 475 fiber miles of the total 595 mile Project by June 30, 2012. This estimate represents 79.83% completion. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 63 | SmartBand has tested thirty (30) of the fifty-four (54) job segments. | 2012-05-10 13:27 | 2012-05-10 13:27 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2012 | Q2 | Q2 - 2012 | 6908 | 6080 | FALSE | 67 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. | 0 |  | Not Applicable. | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 89 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-seven (47) of the fifty-five (55) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bills of materials for current job segments. | 92 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 92 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and | 89 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Third Quarter 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 48 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 84 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 62 | SmartBand has tested approximately thirty-four (34) of the fifty-five (55) job segments. | 2012-08-07 18:42 | 2012-08-07 18:42 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2012 | Q3 | Q3 - 2012 | 7972 | 6692 | FALSE | 78 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up fifty-two (52) Community Anchor Institutions. Troy Cable has connected and turned up fifty-eight (58) Businesses. | 0 |  | Not Applicable. | 87 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 94 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-two (52) bills of materials for current job segments. | 94 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 94 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will b | 90 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; Access Gear; Intelligent Policy Management; and Firewall. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Fourth Quarter 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection A | 55 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable projects an aggressive goal of 627 fiber miles constructed through the end of the Fourth Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 85 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable projects an aggressive goal of 627 fiber miles constructed through the end of the Fourth Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 91 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2012-11-20 11:33 | 2012-11-20 11:33 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2012 | Q4 | Q4 - 2012 | 8852 | 7637 | FALSE | 87 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up fifty-one (51) Community Anchor Institutions. Troy Cable has connected and turned-up one hundred fifty-one (151) Businesses. | 0 |  | Not Applicable | 91 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 96 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-four (54) bills of materials for current job segments. | 96 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 98 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. | 96 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrie | 75 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 92 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 92 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2013-02-19 22:50 | 2013-02-19 22:50 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2013 | Q1 | Q1 - 2013 | 9574 | 8314 | FALSE | 88 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up ninety-four (94) Community Anchor Institutions. Troy Cable has connected and turned-up two hundred forty-seven (247) Businesses. | 0 |  | Not Applicable | 90 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 98 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-six (56) bills of materials for current job segments. | 98 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 99 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 99 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 87 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 96 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 95 | SmartBand has tested approximately fifty (50) of the fifty-six (56) job segments. | 2013-04-30 21:20 | 2013-04-30 21:20 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2013 | Q2 | Q2 - 2013 | 10576 | 8944 | FALSE | 96 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up one hundred thirty-nine (139) Community Anchor Institutions. Troy Cable has connected and turned-up three hundred fifty-seven (357) Businesses. Troy Cable anticipates connecting to an additional eight (8) CAI's. | 0 |  | Not Applicable | 90 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 99 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-eight (58) bills of materials for current job segments. | 99 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 99 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 87 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 97 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | SmartBand has tested approximately fifty (58) of the fifty-eight (58) job segments. | 2013-08-13 20:10 | 2013-08-13 20:10 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2013 | Q3 | Q3 - 2013 | 11296 | 9446 | FALSE | 100 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable connected and turned-up one hundred forty-six (146) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred (400) Businesses. Troy Cable anticipates connecting to an additional fifty-two (52) CAI's. | 0 |  | Not Applicable. | 100 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 100 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced approximately eighty (80) bills of materials for current job segments. | 100 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 100 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | SmartBand has will test approximately eighty (80) job segments. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 2013-11-19 16:15 | 2013-11-19 16:15 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570128 | 2013 | Q4 | Q4 - 2013 | 12260 | 10430 | FALSE | 100 | No variance from the Baseline. | 0 |  | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 0 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 2014-06-02 15:01 | 2014-06-02 15:01 | 6116 | 6116 | Troy Cablevision, Inc.
NT10BIX5570129 | 2010 | Q4 | Q4 - 2010 | 1358 | 2373 | FALSE | 3 | Total expenditures for next quarter are anticipated to be 3% of total project budget. The baseline plan anticipated expenditures of 20% total project cost. This variance is due to several factors, including discrepancy of network procurement timeline between baseline data and project plan. Also, site preparation on the data center will not take place during the next quarter, as was anticipated in the plan. | 25 | Grant Administration | N/A | 73 | This is alligned with baseline data and indicates the EA is on schedule for completion by next quarter. | 38 | N/A | 0 | Baseline plan anticipated 5% completion by end of quarter. Due to delay with data center construction, the anticipated draw downs associated with contract award are not anticpated to occur during the quarter. | 9 | This is based on anticipated draw downs for engineering fees pertaining to linear construction. Due to potential route change holdups and data center delay, draw downs for this milestone are 23% less complete than expected. | 0 | The baseline plan anticipated 10% of this milestone completed by the end of the quarter. This is based on the scheduled site preparation activities for the data center. There is a discrepancy between the baseline data and baseline project plan. Baseline project plan calls for the award of contract for data center design and engineering, but no site preparation will occur, as is projected in the baseline data. | 9 | This is based on anticipated purchase of DSLAM equipment. Baseline plan anticipated 19% completion. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-24 09:26 | 2011-02-24 09:26 | 6108 | 6108 | Rockbridge, County of
NT10BIX5570129 | 2011 | Q1 | Q1 - 2011 | 2298 | 2894 | FALSE | 4 | Estimated expenditures of $433,747 represents 4% of total project funds. The data center design procurement is nearly complete, with interviews conducted on May 20th. Contract negotiations have begun, and the design of the data center will be under way before the end of June. Interview with four different firms competing for the design work all indicated that the construction of the facility can be completed in eight months, for an overall start to finish for the data center of no more than one year, or only slightly behind original timeframe. Fiber route survey work will be 100% complete at the end of May, and fiber route engineering is estimated to be 60% complete by the end of June. Issues with rocky soil and aerial pole agreements have slowed engineering. The three localities have agreed on an approach for equitably sharing local match and distribution of fiber connections, and approval is anticipated at the first project review meeting in June. Terms for the Washington and Lee | 34 | Grant Administration | N/A | 100 | N/A | 70 | N/A | 80 | N/A | 66 | N/A | 2 | The baseline plan indicated 30% of milestone complete. Based on estimated expenditure of $60,000 on cabinet site work, 2% of milestone category will be complete. Discrepancy based on data center rebid. | 3 | Purchase of $75,000 of cabinet equipment represent 3% of equipment budget. Baseline plan indicated 43% completion by end of quarter. This is explained by discrepancy in project plan timeline | 0 | The variance from the baseline plan, which anticipated this milestone as 12% complete is due to the decision to rebid the data center. | 0 | N/A | 0 | N/A | 2011-05-25 13:30 | 2011-05-25 13:30 | 6108 | 6108 | Rockbridge, County of
NT10BIX5570129 | 2011 | Q2 | Q2 - 2011 | 3150 | 3335 | FALSE | 9 | Estimated expenditures of $929,820 represents 9% of total project funds. Baseline plan indicated 60% of overall project completion by end of quarter. As has been explained in previous reports, delays to the environmental assessment, data center design, and route engineering have set the project off of its baseline time line. However, data center design firm is now under contract and construction on the data center is likely to be complete is less than one year. Route engineering is complete and fiber construction is on schedule to begin in the fall. | 42 | Grant Administration | No variance | 100 | The environmental assessment final submission was delayed due to the need for a Phase 1 survey on the data center site. This survey has been complete. The environmental assessment is on track for late July submission. | 100 | No variance | 28 | Baseline Plan anticipated 100% percent completion of milestone by end of quarter. Planned completion is approximately 72% lower. Negative variance from baseline plan is attributed to delays to the environmental assessment and route engineering. It is likely that Rights of way will be fully complete by 2011, Q4, only delaying completion of milestone by 1 quarter. | 67 | Baseline Plan anticipated 96% percent completion of milestone by end of quarter. Planned completion is approximately 30% lower. Negative variance from baseline plan is attributed to delays in selection of data center design firm selection and route engineering. Due to these delays, it is anticipated that all relative permits will be drafted and submitted, but approval of all permits is not anticipated until 2011, Q4. | 23 | Planned expenditures of $10,000 for DSL site prep represents 23% of budgeted site prep work. The baseline's anticipated milestone to be 50% complete. Variance is explained by the delay in DSL construction due to the environmental assessment submission delay. | 9 | Planned purchase of $200,000 for cabinet and network equipment represents 9% of equipment budget. Baseline plan indicated 67% completion of milestone by end of quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. | 0 | Baseline Plan anticipated 23% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. | 0 | Baseline Plan anticipated 12% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. Equipment for the DSL cabinets and fiber network will be ordered during the quarter, but no deployment is anticipated during this quarter. | 0 | Baseline Plan anticipated 10% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. Testing cannot take place if equipment is not deployed. | 2011-08-17 12:23 | 2011-08-17 12:23 | 6108 | 6108 | Rockbridge, County of
NT10BIX5570129 | 2011 | Q3 | Q3 - 2011 | 4168 | 3932 | FALSE | 18 | Estimated expenditures of $1,814,820 represents 18% of the total project funds. Baseline plan indicated 69% of overall project completion by the end of the quarter. As has been explained in previous reports, delays to the environmental assessment, data center design, and route engineering have set the project off of its baseline time line. However, data center construction is likely to start during this quarter and be completed by Summer 2012. Route engineering is complete. The fiber construction RFP will be released during the first week of December and will be due back four weeks later. We expect to make an award for that work in January, and work will start in February. | 50 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 49 | 100% of the needed easements have been identified which makes up 15% of this overall milestone and there will be about 40% of the needed easements gathered during 2011, Q4. The combination of the 15% from the completion of the identification of the easements and 40% of the easements being gathered gives the 49% completion of this overall milestone. Baseline plan indicated 100% of the ROW's would have been completed by end of this quarter. This has been delayed by the route engineering and deciding on the placement of some of the DSL sites. Delays have also been because of a legal delay on approving the easement agreements. | 89 | All relative permits should be submitted by the end of the quarter and we will be waiting on some of the approvals. Most of the permit approvals should be granted by the end of the quarter. Baseline plan anticipated 100% completion of milestone by the end of the quarter. Negative variance is attributed to delays in the selection of data center design firm and route engineering. | 23 | Planned expenditures of $10,000 for DSL site prep represents 23% of budgeted site prep work. The baseline plan anticipated a milestone completion of 70%. Variance is explained by the delay in DSL construction due to the environmental assessment submission and approval delay. | 22 | Planned purchase of $500,000 for cabinet and network equipment represents 22% of equipment budget. Baseline plan indicated 89% completion of milestone by end of quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. Also, delays in easement procurement has delayed the ordering of equipment. | 2 | Baseline plan anticipated 33% completion of milestone. Negative variance is due to delays with the environmental assessment. Data Center construction is expected to begin during this quarter. | 0 | Baseline plan anticipated 24% completion of milestone. Due to delays with the environmental assessment, DSL construction is not anticipated to begin during this quarter. Equipment for the DSL cabinets and fiber network will be ordered during the quarter, but no deployment is anticipated. DSL equipment (DSLAMs, UPSes, batteries, patch panels) will be installed in the DSL cabinets as construction in complete at each of the 29 sites. This work will begin in 2012 Q1. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed, so some customers should be receiving service in 2012 Q2. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinet are complete. Portions of the network will be lit and cu | 0 | Baseline plan anticipated 22% completion of milestone. Due to delays with the environmental assessment, DSL construction is not anticipated to begin during this quarter. Testing cannot take place if equipment is not deployed. Network testing will begin as soon as the data center and the first fiber segments are completed in 2012 Q2. Network testing will continue on a rolling basis as additional fiber route segments are completed, with all testing complete in 2012 Q4. | 2011-11-21 09:46 | 2011-11-21 09:46 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2011 | Q4 | Q4 - 2011 | 5226 | 4890 | FALSE | 35 | Estimated expenditures of $3,525,392 represents 35% of the total project funds. Baseline plan indicated 70% of overall project completion by the end of the quarter. As has been explained in previous reports, delays in submission and approval of the environmental assessment, data center design, data center contract negotiations, and route engineering have set the project off of its baseline time line. However, data center construction will start during this quarter and will be completed by Summer 2012. Route engineering has been completed. We are expecting to make an award for the cabinet procurement, fiber procurement, conduit procurement, fiber network construction, and cabinet construction during 2012 Q1. The fiber network construction and the cabinet construction is expected to begin late 2012 Q1 or early 2012 Q2. | 58 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 80 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites. Delays have also come from the delay in the legal review of the easement agreements. The County has been actively getting easement agreements signed and will continue to get the needed easements. The easements that are needed will NOT delay the start of construction as the majority of the route does not need easements or they will have already been gathered. | 96 | All relative permits should be submitted by the end of the quarter and we will only be waiting on the approval of the cabinet construction permit. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is attributed to delays in the submission and approval of the environmental assessment, the selection of the data center design firm, and fiber route engineering. | 27 | Planned expenditures of $10,000 for cabinet site preparation represents 27% of what is budgeted for site preparation work. The baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents. The cabinet construction bid was advertised during 2011 Q4 and is expected to be awarded during 2012 Q1. We are anticipating the cabinet construction to begin in late 2012 Q1 or early 2012 Q2. | 28 | Planned purchase of $641,816 for cabinets, fiber, and conduit represents over 28% of the equipment budget. Baseline plan indicated 100% completion of this milestone by the end of the quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. Also, delays in the legal review of the bid documents has delayed the advertisement of the equipment procurement bids. The bid documents were advertised during 2011 Q4 and are due back early 2012 Q1. We are anticipating issuing a purchase order for the fiber, conduit, and cabinets during 2012 Q1. | 20 | Baseline plan anticipated 45% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with legal review of the network construction bid documents, and lengthy data center contract negotiations. The data center contract has been signed and construction is anticipated to start during 2012 Q1. Also, the fiber network construction and cabinet construction contracts are expected to be awarded during 2012 Q1 with construction beginning late 2012 Q1 or early 2012 Q2. | 0 | Baseline plan anticipated 37% completion of this milestone. Due to delays with the environmental assessment, cabinet construction is not anticipated to begin until late 2012 Q1 or early 2012 Q2. The cabinets, fiber, and conduit will be ordered during this quarter, but no deployment is anticipated. DSL equipment (DSLAMs, UPSes, patch panels) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fib | 0 | Baseline plan anticipated 35% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents, cabinet construction is not anticipated to begin until late 2012 Q1 or early 2012 Q2. The data center contract negotiations also delayed the start of the data center construction, which is anticipated to start 2012 Q1. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-02-23 16:23 | 2012-02-23 16:23 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2012 | Q1 | Q1 - 2012 | 6132 | 5668 | FALSE | 52 | Estimated expenditures of $5,195,512 represents over 52% of the total project funds. Baseline plan indicated 82% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, and delays in the legal review of the network construction bid documents and contracts have set the project off of its baseline time line. However, data center construction has begun and will be completed by Summer 2012. Route engineering has been completed. We have made an award for the cabinet, conduit, and fiber procurements. There has also been an award made for the cabinet and fiber network construction contracts and we expect to have those contracts signed and for construction to begin next quarter. | 66 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 90 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites and in locating the existing Century Link easement. Delays have also come from the delay in the legal review of the easement agreements. A local firm has been hired to locate and pursue these easements. The easements that are needed will NOT delay the start of construction as the majority of the routes do not need easements or they have already been gathered. | 100 | No variance | 27 | Planned expenditures of $10,000 for cabinet site preparation represents 27% of what is budgeted for site preparation work. The baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction is expected to be signed and construction started during the next quarter. | 28 | Planned purchase of $641,816 for cabinets, fiber, and conduit represents over 28% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan timeline and delays resulting from the environmental assessment. Discrepancies in the project plan timeline are due to the lead times on fiber. We have issued the purchase order for the fiber but it will not be invoiced until the fiber is delivered. We are expecting fiber to begin being delivered during 2012 Q3. This delay however will not hold up construction as the contractor will be installing the conduit first. Also, delays in the legal review of the bid documents delayed the advertisement of the equipment procurement bids. The bids were advertised during 2011 Q4 and were due back during 2012 Q1. The awards for Conduit, Fiber, and Cabinets were made in February and we are expecting to receive equipment shipments throughout n | 30 | Baseline plan anticipated 55% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction has begun and is scheduled to be completed during 2012 Q2. The cabinet and fiber network construction will begin during 2012 Q2. | 5 | Baseline plan anticipated 50% completion of this milestone. Due to delays with the environmental assessment, cabinet construction did not begin this quarter, 2012 Q1, but is expected to start during next quarter, 2012 Q2. Cabinets and conduit are expected to begin being placed in the ground and at their location throughout 2012 Q2. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the | 0 | Baseline plan anticipated 48% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is anticipated to begin during 2012 Q2 but no network equipment will be deployed. The data center contract negotiations also delayed the start of the data center construction, which began during 2012 Q1 and is expected to be completed 2012 Q2. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-05-16 12:19 | 2012-05-16 12:19 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2012 | Q2 | Q2 - 2012 | 7130 | 6192 | FALSE | 60 | Estimated expenditures of $5,957,000 represents 60% of the total project funds. Baseline plan indicated 87% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is almost complete and is scheduled for completion during 2012 Q3. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. We are expecting to get the VDOT permits next quarter, 2012 Q3, and the Rockbridge County-City of Lexington agreement has been signed. All of the cabinets and conduit are on site and we are expecting to have | 75 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 90 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites and in locating the existing Century Link easement. Delays have also come from the delay in the legal review of the easement agreements. A local firm has been hired to locate and pursue these easements. The easements that are needed will NOT delay construction as the majority of the routes do not need easements or they have already been gathered. We anticipate to have all of the needed easements for the project before the end of 2012. | 100 | No variance | 30 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction has begun. | 58 | Planned purchase of $1,300,000 for fiber and other equipment represents over 58% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. We are expecting fiber to be delivered during 2012 Q3. Other equipment purchases will be made by the fiber contractor for handholes, splice closures, etc., and will be invoiced for during 2012 Q3. Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders sent out. All of the conduit and cabinets are on site and we are anticipating the entire shipment of fiber to be made next quarter, 2012 Q3. | 45 | Baseline plan anticipated 67% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction has begun and is scheduled to be completed during 2012 Q3. The cabinet and fiber network construction has begun. We expect to have the VDOT permits and the Rockbridge County-City of Lexington agreement next quarter, 2012 Q3, and for the fiber network construction to pick up speed. | 15 | Baseline plan anticipated 62% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction have begun. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q3, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fiber segments are completed. | 0 | Baseline plan anticipated 61% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction has begun but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which has now begun and is expected to be completed 2012 Q3. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-08-17 16:59 | 2012-08-17 16:59 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2012 | Q3 | Q3 - 2012 | 8134 | 6775 | FALSE | 69 | Estimated expenditures of $6,954,000 represents over 69% of the total project funds. Baseline plan indicated 91% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is almost complete and is scheduled for completion and acceptance during 2012 Q4. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site and we are expecting to begin getting the fiber and DSL network equipment shipped throughout the next quarter. | 83 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 62 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is underway. We are currently waiting on CenturyLink to get back on the cabinet placement requirements for the remaining cabinets. We are expecting to being getting those requirements during the next quarter, 2012 Q4. | 67 | Planned purchase of $1,500,000 for fiber and other equipment represents 67% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. Fiber has been delivered and we are expecting to have some of the fiber and DSL network equipment delivered during 2012 Q4.Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders are being sent out as the bids are evaluated. All of the conduit, cabinets, and fiber are on site and we are anticipating shipments of fiber and DSL equipment to be made next quarter, 2012 Q4. | 65 | Baseline plan anticipated 77% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is very close to completion and is scheduled for completion and acceptance during 2012 Q4. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and we are expecting them to make substantial progress now that they have started working in the County. | 25 | Baseline plan anticipated 75% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion and acceptance in 2012 Q4 with W&L installing their equipment over the Thanksgiving holiday. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fiber seg | 5 | Baseline plan anticipated 74% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which has now begun and is expected to be completed 2012 Q4. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2012 | Q4 | Q4 - 2012 | 8944 | 7725 | FALSE | 80 | Estimated expenditures of $7,935,234 represents a little under 80% of the total project funds. Baseline plan indicated 95% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is complete. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site and we have begun getting the fiber and DSL network equipment shipped and will continue to have more delivered during next quarter. We are also expecting the fiber equipment vendors to come and be | 91 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 80 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed to the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is underway. We are expecting CenturyLink to get back to us on the cabinet placement requirements for the remaining cabinets during the next quarter and for the cabinet contractor to be cleared to work in the remaining cabinet sites. | 72 | Planned purchase of $1,600,000 for fiber and other equipment represents 72% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. Fiber has been delivered and we are expecting to to continue to have the fiber and DSL network equipment delivered during 2013 Q1.Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders are being sent out as the bids are evaluated. All of the conduit, cabinets, and fiber are on site and we are anticipating the remaining shipments of fiber and DSL equipment to be made next quarter, 2013 Q1. The fiber equipment vendors will be installing and configuring the core and edge network equipment during next quarter, 2013 Q1. | 80 | Baseline plan anticipated 88% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is complete. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and they are making substantial progress now that they are working in the County. | 60 | Baseline plan anticipated 87% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center construction is complete and W&L has installed their equipment and are operating their network out of the data center. Network equipment in fiber cabinets will begin being installed next quarter, 2013 Q1. Portions of the network will be lit and customers will be connected on a rolling basis throughout next quarter 2013, Q1. | 50 | Baseline plan anticipated 87% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which is now complete. Network testing has begun as the DSL equipment has been delivered. Fiber vendors are expected to conduct the installation and configuration of the core and edge network equipment. Once installation and configuration is complete network testing will begin on the fiber network. The DSL equipment is also expected to be installed in the cabinets that are completed and testing of the DSL network will also be taking place during the next quarter, 2013 Q1. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2013-02-25 16:18 | 2013-02-25 16:18 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2013 | Q1 | Q1 - 2013 | 9884 | 8480 | FALSE | 95 | Estimated expenditures of $9,521,000 represents over 95% of the total project funds. Baseline plan indicated 100% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line, and delays in the approval of the business connections approval by the Environmental Assessment team. However, data center construction is complete. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site as well as the fiber and DSL network equipment. We are also expecting the fiber equipment testing and to be | 95 | Grant Administration | Negative variance is because the grant period extends into 2013 Q3 and that was not reflected in the baseline plan. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | Baseline plan anticipated 100% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, delay in the approval of the business connections approval by the Environmental Assessment team, and lengthy data center contract negotiations. The data center construction is complete. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and other routes throughout the County, and they are making substantial progress now that they are working in the County. | 85 | Baseline plan anticipated 100% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center construction is complete and W&L has installed their equipment and are operating their network out of the data center. Network equipment in fiber cabinets has begun. Portions of the network will be lit and customers will be connected on a rolling basis throughout next quarter 2013, Q2. | 85 | Baseline plan anticipated 100% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway and DSL network equipment deployment has begun. The data center contract negotiations also delayed the start of the data center construction, which is now complete. Network testing has begun on the DSL equipment as well as the fiber equipment. Fiber vendors have completed the installation and configuration of the core and edge network equipment. The DSL equipment is continuing to be installed in the cabinets that are completed and testing of the DSL network will also be taking place during the next quarter, 2013 Q2. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2013-05-23 11:29 | 2013-05-23 11:29 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2013 | Q2 | Q2 - 2013 | 10736 | 9031 | FALSE | 100 | No variance | 100 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-08-26 12:00 | 2013-08-26 12:00 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570129 | 2013 | Q3 | Q3 - 2013 | 11994 | 10155 | FALSE | 100 | No variance | 100 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-03-26 15:36 | 2014-03-26 15:36 | 7215 | 7215 | Rockbridge, County of
NT10BIX5570130 | 2010 | Q4 | Q4 - 2010 | 1292 | 2314 | FALSE | 22 | Awaiting Approval of Environmental Assessment | 70 | Project notification | Project Notifications and Scheduling and General Administration/Oversight | 100 | Complete Environmental Assessment to Begin Construction | 100 | Complete Construction Drawings for Permitting | 45 | Acquire the necessary access permits for City, County, State, Utility, Private and Railroad Right of Way Access | 75 | Acquire the necessary AL DOT Permits for State Highway and Bridge Access Permits | 22 | Stage Materials/Equipment, Clear Easements, and Set-up Construction Management Sites | 24 | Purchase, Stage, Test and Burn-In Equipment | 10 | Install Infrastructure and Terminals | 23 | Deploy Core Routing, Switching at Terminals and Implement Customer Premise Devices | 19 | Test Fiber Connectivity, Network Terminals and Validate Customer Premise Connectivity | 2011-02-22 12:32 | 2011-02-22 12:32 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2011 | Q1 | Q1 - 2011 | 1934 | 2712 | FALSE | 11 | The Trillion team will continue to work out all site mobilization, construction, materials logistics, and systems testing and validation processes. Project timeline has been delayed as FONSI was not received as previously expected. | 55 | Project Notification | The South Central Alabama Broadband Commission authority still enrolling members. Several Municipalities have signed resolutions to join the South Central Alabama Broadband Commission. | 100 | N/A | 96 | The Trillion Team will concentrate on producing the required permit-ready drawings. Each county completed represents a 0.5% completion in the network design. | 50 | The Trillion Team will continue negotiating leases with property owners. However, no leases will be executed for terminals until the end of 2011. | 10 | The Trillion Team has applied for a permit to encompass the entire middle mile portion of the network with the Alabama DOT. The Trillion Team will secure city and county permits 1 month before construction activity starts in that area. | 10 | N/A | 20 | N/A | 5 | Begin to install infrastructure and terminals. Delayed because of FONSI | 15 | N/A | 5 | N/A | 2011-05-10 19:37 | 2011-05-10 19:37 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2011 | Q2 | Q2 - 2011 | 3344 | 3435 | FALSE | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 60 |  | Public Notification will be implemented across eight (8) counties in South Central Alabama. The Notification Program is being developed via a collaboration with the Broadband Authority and Stakeholders. Lowndes County Notification in currently in process. We are entering Wave 2 which will have a direct impact to all anchor institutions, businesses, and residences in the last mile FTTP serving area. | 100 | EA is complete | 97 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 50 | There is no variance | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 13 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 25 | There is no variance | 8 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 10 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 2011-08-29 11:39 | 2011-08-29 11:39 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2011 | Q3 | Q3 - 2011 | 4356 | 4034 | FALSE | 25 | We plan to commence infrastructure construction of phase 1 | 33 | Notification | Public Notification Program & Service Provider Integration: With the commencement of construction, we anticipate a comprehensive public awareness and project notification of all the first phase counties (Lowndes and Dallas) Lowndes County Middle Mile Notification will be 85% completed; Dallas County Middle Mile Notification will be well underway with all anchors and businesses and households. | 100 | N/A | 99 | This task is complete subject to final route design adjustments | 50 | We anticipate getting closer to our baseline in Q4, 2011. Once phase 1 construction begins we can be assured our construction program is streamlined and then put heavy focus on securing future phase Right Of Way (ROW) agreements, permits and etc. | 25 | We plan to have permits for Phase 1 backbone, site surveys complete for anchor institutions and distribution routes in permit phase. | 25 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to ramp up construction operations in a short period of time. However, we have not fully caught up with our baseline and anticipate catching up in the next quarter given that construction will start and we will be able to ramp up site preparation at a quicker pace. | 25 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to hold back on a significant amount of equipment purchases. We have not fully caught up with our baseline and anticipate catching up in the next quarter since construction will start and we can justify ordering more equipment to stay ahead of the construction materials demand. | 8 | We plan to begin construction on phase 1 backbone | 18 | We plan to begin construction on phase 1 backbone | 15 | With construction beginning, there will be a real time testing of fiber and network terminals installed. | 2011-11-30 16:20 | 2011-11-30 16:20 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2011 | Q4 | Q4 - 2011 | 5086 | 4756 | FALSE | 46 | N/A | 37 | Notification | Phase 1 and Phase 2 Notification complete | 100 | N/A | 100 | N/A | 65 | We anticipate having the core local NOC leased | 35 | Based on meetings with ALDOT and Other State Officials we anticipate a significant improvement in the permitting process and timeline | 60 | We should get much closer to baseline in this area as the second A2D construction office is scheduled to be operational in this quarter | 40 | Catching up to baseline will be a direct correlation with construction activities. This area will increase significantly the next quarter as we move into phase 2 backbone and phase one CAI and premise connections. | 35 | We anticipate taking a few quarters to catch up to baseline, however, we plan to mitigate this by commencing more simultaneous construction efforts with more construction crews. | 20 | Related to 2g above. Catching up to baseline will be a direct correlation with construction activities. This area will increase significantly the next quarter as we move into phase 2 backbone and phase one CAI and premise connections. | 20 | Based on the current construction progress we anticipate having the Network lit and several CAI's connected | 2012-02-17 10:44 | 2012-02-17 10:44 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2012 | Q1 | Q1 - 2012 | 6354 | 5779 | FALSE | 23 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 42 | Project/Construction Notification | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-05-30 16:56 | 2012-05-30 16:56 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2012 | Q2 | Q2 - 2012 | 7232 | 6243 | FALSE | 24 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 42 | Project/Construction Notification | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-08-23 14:27 | 2012-08-23 14:27 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2012 | Q3 | Q3 - 2012 | 7718 | 6546 | FALSE | 24 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 |  | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-10-31 00:19 | 2012-10-31 00:19 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2012 | Q4 | Q4 - 2012 | 8602 | 7397 | FALSE | 24 | Work was stopped due to the termination of the Project. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. The Project Closeout is underway. | 42 | Project /Construction Notification | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 100 | N/A | 20 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 57 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 40 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 19 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 12 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 11 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 2013-01-30 20:35 | 2013-01-30 20:35 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2013 | Q1 | Q1 - 2013 | 9592 | 8323 | FALSE | 24 | Work was stopped due to the termination of the Project. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. The Project Closeout is underway. | 42 | Project /Construction Notification | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 100 | N/A | 20 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 57 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 40 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 19 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 12 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 11 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 2013-04-30 23:53 | 2013-04-30 23:53 | 5992 | 5992 | Trillion Communications Corp.
NT10BIX5570130 | 2013 | Q2 | Q2 - 2013 | 11314 | 9456 | FALSE | 24 | Work was stopped due to the termination of the Project. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. The Project Closeout is underway. | 42 | Project / Construction Notification | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 100 | N/A | 20 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 57 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 40 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 19 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 12 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 11 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 18 | Work was cancelled due to the Project's termination and the stop work order initiated by NTIA and NOAA. The Project Closeout is underway. | 2013-11-20 17:23 | 2013-11-20 17:23 | 5991 | 5991 | Trillion Communications Corp.
NT10BIX5570131 | 2010 | Q4 | Q4 - 2010 | 1260 | 2288 | FALSE | 2 | N/A | 26 | land acquisition | N/A | 43 | N/A | 36 | N/A | 0 | N/A | 19 | N/A | 1 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-21 16:26 | 2011-02-21 16:26 | 6061 | 6061 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2011 | Q1 | Q1 - 2011 | 2300 | 2895 | FALSE | 10 | N/A | 32 | Land Acquisition | Environmental delays | 61 | N/A | 41 | Environmental delays | 0 | N/A | 26 | Environmental delays | 0 | Environmental delays | 34 | Environmental delays | 3 | N/A | 6 | N/A | 4 | N/A | 2011-05-25 13:55 | 2011-05-25 13:55 | 6061 | 6061 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2011 | Q2 | Q2 - 2011 | 3280 | 3402 | FALSE | 12 | No Variance | 4 | Land Acquisition | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 68 | No Variance | 37 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | No Variance | 25 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 1 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2 | No Variance | 2 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2011-08-23 16:01 | 2011-08-23 16:01 | 6061 | 6061 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2011 | Q3 | Q3 - 2011 | 4352 | 4032 | FALSE | 21 | No variance | 0 | Land Acquisition | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 100 | No variance | 27 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | No variance | 12 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 5 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 29 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 16 | No variance | 0 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2011-11-30 15:50 | 2011-11-30 15:50 | 6061 | 6061 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2011 | Q4 | Q4 - 2011 | 5254 | 4919 | FALSE | 27 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public right-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 35 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 16 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 10 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 34 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 25 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-02-24 15:24 | 2012-02-24 15:24 | 6061 | 6061 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2012 | Q1 | Q1 - 2012 | 6346 | 5775 | FALSE | 33 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 37 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 13 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 17 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 34 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 32 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-05-30 11:03 | 2012-05-30 11:03 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2012 | Q2 | Q2 - 2012 | 7078 | 6166 | FALSE | 43 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 51 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 13 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 17 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 43 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 42 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-08-15 14:20 | 2012-08-15 14:20 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2012 | Q3 | Q3 - 2012 | 7828 | 6617 | FALSE | 59 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 63 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 18 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 45 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 60 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-11-12 13:22 | 2012-11-12 13:22 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2012 | Q4 | Q4 - 2012 | 9102 | 7873 | FALSE | 70 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 78 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 51 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 73 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-02-28 16:33 | 2013-02-28 16:33 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2013 | Q1 | Q1 - 2013 | 9906 | 8494 | FALSE | 86 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. We anticipate filing for an extension and completing the project by the end of third quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 90 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 18 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 20 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 71 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 94 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-05-24 16:47 | 2013-05-24 16:47 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2013 | Q2 | Q2 - 2013 | 10678 | 9000 | FALSE | 100 | No variance. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 100 | No variance. | 0 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-08-21 10:51 | 2013-08-21 10:51 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | 2013 | Q3 | Q3 - 2013 | 12180 | 10365 | FALSE | 100 | No variance. The project exceeded anticipated budget by .5%, however, the budgeted federal portion of the project is still on-budget. The overrun shows to be in the "percent match" category; in other words, we overspent our own funds. | 0 | Land Acquisition | No variance. | 100 | No variance. | 100 | No variance. | 0 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. The network build milestone exceeded anticipated budget by .5%, however, the budgeted federal portion of the project is still on-budget. The overrun shows to be in the "percent match" category; in other words, we overspent our own funds. | 0 | No variance. | 0 | No variance. | 2014-05-12 11:43 | 2014-05-12 11:43 | 6062 | 6062 | Peoples Telephone Cooperative Inc.
NT10BIX5570132 | 2010 | Q4 | Q4 - 2010 | 1134 | 2171 | FALSE | 0 | Even though the planned percent complete reflects "0" there is progress being made on the project; this is due to the amount that is planned to be complete by the end of this reporting period being so minute compared to the overall size of the project that it reflects a total percentage completion of less than 1. | 0 | N/A | N/A | 90 | The draft Environmental Assessment was submitted to NTIA for review on 1/15/11. NTIA responded with questions on the draft EA, which ENMR-Plateau and the environmental consultants are currently addressing. In order to meet this milestone in this quarter concurrence from NTIA, SHPO, NMDOT, etc. should be in the final stages of completion. | 85 | For this percentage of the milestone to be met in this quarter approximately 85% of the activities associated with this milestone, which is comprised of the designing of the network, must be completed by the engineering consultants. | 50 | For this percentage of the milestone to be met in this quarter approximately half of the activities associated with this milestone, including contacting the governing parties and negotiating agreements with those parties, must be completed. | 50 | For this percentage of the milestone to be met in this quarter approximately half of the activities associated with this milestone, including obtaining all required permits in NMDOT right of ways, must be completed. ENMR-Plateau will be coordinating with the NMDOT in obtaining these permits. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-02-14 12:55 | 2011-02-14 15:38 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2011 | Q1 | Q1 - 2011 | 1518 | 2472 | FALSE | 16 | No variance. | 0 | N/A | N/A | 100 | No variance. The final Environmental Assessment was submitted to NTIA on 4/8 and we expect the FONSI to be issued by 4/30. | 100 | No variance. Network design is expected to be completed by 6/30. | 100 | No variance. | 75 | No variance. | 0 | No variance. | 0 | Pushed back. Waiting on the FONSI to be completed. Contract negotiations, planning, and invoicing must be completed prior to any funds being expensed. At this time we do not anticipate expensing any funds by 6/30. | 0 | Pushed back. Waiting on FONSI to be completed, RFP's must be finalized and submitted to contractors. | 0 | Pushed back due to equipment procurement schedule. | 0 | No variance. | 2011-04-27 11:34 | 2011-04-27 11:34 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2011 | Q2 | Q2 - 2011 | 3252 | 3388 | FALSE | 4 | Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 0 | Please see section #3 below. | 4 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 2011-08-22 10:57 | 2011-08-22 10:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2011 | Q3 | Q3 - 2011 | 4190 | 3943 | FALSE | 17 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 80 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 60 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 52 | No variance. | 14 | Equipment procurement has started in October and is expected to proceed throughout the quarter. | 16 | Outside plant construction started on October 10th and will be progressing throughout the quarter. Based on the efficiency of the contractor and having four construction crews going simultaneously we are expecting to catch up to milestones included in baseline report around the second quarter of next year. | 12 | Equipment installation is expected to begin in Quarter 4. Based on the efficiency of the equipment installers we expect to catch up to milestones included in the baseline report around the second quarter of next year. | 0 | Network testing follows equipment procurement and installation. Once installation has been completed to a point the testing of the network will begin. | 2011-11-21 16:01 | 2011-11-21 16:13 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2011 | Q4 | Q4 - 2011 | 4504 | 4152 | FALSE | 32 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 80 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 80 | CO buildings construction will begin Q1 2012 and is anticipated to be complete by the end of Q2 2012. | 37 | Equipment procurement began in Q4 2011 and is expected to ramp up in Q1 and Q2 of 2012. The majority of the equipment will be procured by July 31st 2012. | 27 | Outside plant construction started on October 10th and will be progressing throughout the next quarter. Based on the efficiency of the contractor and have multiple construction crews going simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 25 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 25 | Network testing follows network build and equipment deployment. | 2012-01-27 11:24 | 2012-01-27 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2012 | Q1 | Q1 - 2012 | 5980 | 5589 | FALSE | 56 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 87 | Positive variance. | 83 | The majority of the equipment is expected to be procured by July 31st 2012. We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 48 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 50 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 50 | Network testing follows network build and equipment deployment. | 2012-05-08 17:31 | 2012-05-08 17:31 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2012 | Q2 | Q2 - 2012 | 6940 | 6097 | FALSE | 74 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 67 | We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 74 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 65 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 65 | Network testing follows network build and equipment deployment. | 2012-08-08 18:07 | 2012-08-08 18:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2012 | Q3 | Q3 - 2012 | 7566 | 6441 | FALSE | 82 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 89 | We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 79 | Outside plant construction began on October 10, 2011 and is progressing quickly. We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 89 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 70 | Network testing follows network build and equipment deployment. | 2012-10-30 11:57 | 2012-10-30 11:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2012 | Q4 | Q4 - 2012 | 9004 | 7779 | FALSE | 90 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 95 | ENMR anticipates completing equipment procurement by the award period end date. | 87 | ENMR anticipates completing the network build by the award period end date. | 95 | ENMR anticipates completing equipment deployment by the award period end date. | 95 | ENMR anticipates completing network testing by the award period end date. | 2013-02-27 11:03 | 2013-02-27 11:03 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2013 | Q1 | Q1 - 2013 | 9968 | 8528 | FALSE | 95 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 95 | ENMR anticipates completing the network build by the award period end date. | 100 | No variance. | 100 | No variance. | 2013-05-29 14:51 | 2013-05-29 14:51 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2013 | Q2 | Q2 - 2013 | 10756 | 9043 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-08-27 10:45 | 2013-08-27 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | 2013 | Q3 | Q3 - 2013 | 11284 | 9438 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-11-19 10:36 | 2013-11-19 10:36 | 5498 | 5498 | E.N.M.R. Telephone Cooperative
NT10BIX5570133 | 2010 | Q3 | Q3 - 2010 | 340 | 1436 | FALSE | 13 | Zero variance | 72 | Grant Administration | Zero variance | 100 | Zero variance | 100 | Zero variance | 30 | Zero variance | 25 | Zero variance | 18 | Zero variance | 14 | Zero variance | 8 | Zero variance | 10 | Zero variance | 9 | Zero variance | 2010-11-17 13:07 | 2010-11-17 13:07 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2010 | Q4 | Q4 - 2010 | 1036 | 2076 | FALSE | 8 | Zero variance | 19 | Grant Administration | Zero variance | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance | 36 | Zero variance | 35 | Zero variance | 1 | Zero variance | 10 | Zero variance | 6 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-02-10 10:13 | 2011-02-10 10:13 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2011 | Q1 | Q1 - 2011 | 2124 | 2807 | FALSE | 15 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 27 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 51 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 48 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 4 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 21 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 12 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 11 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 8 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-05-18 11:22 | 2011-05-18 11:22 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2011 | Q2 | Q2 - 2011 | 3172 | 3346 | FALSE | 22 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 35 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 17 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 24 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 19 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 17 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 10 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-08-17 18:39 | 2011-08-17 18:39 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2011 | Q3 | Q3 - 2011 | 4284 | 3992 | FALSE | 30 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 43 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 33 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 26 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 20 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 20 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-11-28 10:31 | 2011-11-28 10:31 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2011 | Q4 | Q4 - 2011 | 5306 | 4976 | FALSE | 39 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 52 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 49 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 35 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 35 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-02-27 15:55 | 2012-02-28 17:22 | 6712 | 6712 | ION Newco Corp
NT10BIX5570133 | 2012 | Q1 | Q1 - 2012 | 5988 | 5593 | FALSE | 54 | Baseline = 61%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 60 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 64 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 83 | Baseline = 47%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 50 | Baseline = 62%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 36 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 36 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-05-09 15:13 | 2012-05-09 15:13 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2012 | Q2 | Q2 - 2012 | 7192 | 6223 | FALSE | 65 | Baseline = 79%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 68 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 80 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 88 | Baseline = 61%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 63 | Baseline = 82%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 63 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 63 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-08-21 15:00 | 2012-08-21 15:00 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2012 | Q3 | Q3 - 2012 | 7840 | 6624 | FALSE | 74 | Baseline = 88%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 84 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 82 | Baseline = 80%; Variance is immaterial. Non-Federal matching funds will be fully available during the next quarter. | 86 | Baseline = 80%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 70 | Baseline = 90%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 86 | Baseline = 81%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 81 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-11-13 10:01 | 2012-11-13 10:01 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2012 | Q4 | Q4 - 2012 | 8768 | 7563 | FALSE | 82 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 85 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 94 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 96 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 92 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 76 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 2013-02-14 09:07 | 2013-02-14 09:07 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2013 | Q1 | Q1 - 2013 | 9614 | 8338 | FALSE | 94 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 96 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 99 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 92 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Network Testing costs included in Equipment Deployment. | 2013-05-06 16:06 | 2013-05-06 16:06 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2013 | Q2 | Q2 - 2013 | 10582 | 8948 | FALSE | 99 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 89 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Network Testing costs included in Equipment Deployment. | 2013-08-14 14:11 | 2013-08-14 14:11 | 6083 | 6083 | ION Newco Corp
NT10BIX5570133 | 2013 | Q3 | Q3 - 2013 | 11894 | 10063 | FALSE | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 2014-02-26 10:39 | 2014-02-26 10:39 | 6083 | 6083 | ION Newco Corp
NT10BIX5570135 | 2010 | Q4 | Q4 - 2010 | 1082 | 2118 | FALSE | 7 | N/A | 19 | Administration | N/A | 100 | N/A | 3 | N/A | 3 | N/A | 3 | N/A | 17 | N/A | 12 | N/A | 3 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 14:08 | 2011-02-11 14:08 | 6377 | 6377 | Information Technology, Maryland Department of
NT10BIX5570135 | 2011 | Q1 | Q1 - 2011 | 1640 | 2541 | FALSE | 15 | N/A | 28 | Administration | N/A | 100 | N/A | 18 | N/A | 18 | N/A | 18 | N/A | 67 | N/A | 16 | N/A | 9 | N/A | 12 | N/A | 12 | N/A | 2011-04-29 11:04 | 2011-04-29 11:04 | 6377 | 6377 | Information Technology, Maryland Department of
NT10BIX5570135 | 2011 | Q2 | Q2 - 2011 | 3320 | 3422 | FALSE | 18 | Planned is 27%. The FONSI came in a month later then expected which delayed our efforts. | 28 | Administration | We anticipate to recover from the attritions that has occured, we are confident that we will be in line to meeting our projected milestone during the coming quarters. | 100 | Milestone is at a 100% (Completed) | 34 | Preliminary logical diagraming is currently at 90% completion and plant design is currently at 45%. We anticipate that we will meet our milestone projection and exceed projections during the last quarters in 2012. | 20 | We anticipate starting in 9 other counties to come on line early next quarter i.e. Charles, Calvert, Cecil, Kent, Queen Annes, Annarundel, Prince Georges, Montgomary, Annapolis & Hartford counties. Also we anticipate railroad ROW to be approved. | 25 | We anticipate obtaining our construction permits within the 9 counties that are to come online early next quarter. We anticipate achieving our baseline milestone during the next reporting quarters. | 0 | Site visits have been completed for all hut sites, this includes location and path identification. Site preparation will commence in Q4 2011. | 44 | Total equipment procurement is valued at $3.4M of which $1.6M have been procured. | 22 | We anticipate to meet our baseline projections. | 0 | We don't anticipate that equipment deployment will occur until Q4. | 0 | We don't anticipate that the Network Testing will occur until Q4. | 2011-08-26 08:17 | 2011-08-26 08:17 | 6377 | 6377 | Information Technology, Maryland Department of
NT10BIX5570135 | 2011 | Q3 | Q3 - 2011 | 4006 | 3842 | FALSE | 20 | We anticipate our planned percentage to increase as the construction phase is ramping up. | 34 | Administration | We are confident that we will meet our projected milestone during the coming quarters. | 100 | Milestone is at a 100% (Completed) | 26 | Preliminary logical diagraming is currently at 90% completion and plant design is currently at 50%. We anticipate that we will meet our milestone projection and exceed projections during the last quarters in 2012. | 26 | We anticipate starting in 8 other counties early next quarter. Also, we anticipate railroad ROW permits to be approved during the coming reporting quarters. | 26 | We anticipate obtaining our construction permits within the 8 counties that are to come online early next quarter. We anticipate achieving our baseline milestone during 2012. | 0 | Site visits have been completed for all sites, this includes location and path identification, Huts would have been purchased and installation commence within the next reporting quarters. | 23 | Current total equipment procured is valued at $5.7M. We anticipate to come in line with our plan percentage with additional equipment procurement scheduled for the next reporting quarters. | 16 | The Network Build component will increase exponentially as construction continues to ramp up. | 6 | Network architecture designs are ongoing. We anticipate continued equipment deployment during upcoming quarters. | 6 | Network architecture designs are ongoing. We anticipate continued network testing during upcoming quarters. | 2011-11-14 09:54 | 2011-11-14 09:54 | 6377 | 6377 | Information Technology, Maryland Department of
NT10BIX5570135 | 2011 | Q4 | Q4 - 2011 | 5278 | 4946 | FALSE | 28 | We anticipate our planned percentage to increase as the construction phase is ramping up. | 40 | Administration | As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 32 | Preliminary logical diagraming is currently being completed. We anticipate that we will meet our milestone projection and exceed projections reported during this reporting quarter. | 32 | We anticipate receiving ROW permits in all counties in the next reporting quarter. | 32 | We anticipate obtaining our construction permits within the 7 counties that are to come online early next quarter. | 6 | The installation schedule will have us ahead of schedule in Q3. Hut orders were completed in December 2012 with the first delivery in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 22 | Current total equipment procured is valued at $7.1M. We anticipate to come in line with our planned goal during the next reporting quarters. | 12 | Network build component will increase exponentially as construction continues to ramp up. | 13 | Network architecture designs are ongoing, equipment deployment will maintain pace equipment procurement and network build. | 5 | We anticipate network testing during the upcoming quarters as the completion of the network architecture is occurs. | 2012-02-27 10:12 | 2012-02-27 10:12 | 6377 | 6377 | Information Technology, Maryland Department of
NT10BIX5570135 | 2012 | Q1 | Q1 - 2012 | 6300 | 5752 | FALSE | 48 | We anticipate our planned percentage to rapidly increase as the construction phase continues ramping up. | 42 | Administration | As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 48 | Preliminary logical diagraming is currently being completed. Detailed splice engineering begins. Plant infrastructure design will be completed. | 58 | We anticipate receiving ROW permits as needed in all counties in the next reporting quarter. | 58 | We anticipate receiving pole attachment licenses from multiple utilities as well as encroachment agreements from multiple Railroads. | 20 | Hut orders were completed in December 2012 with the first delivery in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 40 | $7M of equipment procurements are currently in process. | 51 | The network build component will increase exponentially as construction continues to ramp up. | 15 | Network architecture designs are ongoing. Equipment deployment will maintain pace with equipment procurement and network build. | 10 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-05-25 11:48 | 2012-05-25 11:48 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2012 | Q2 | Q2 - 2012 | 7164 | 6209 | FALSE | 69 | We anticipate our planned percentage to rapidly increase since the construction phase is well on its way. | 47 | Administration | As construction continues to gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 79 | Preliminary logical diagraming is currently being completed. Detailed splice engineering has begun. Plant infrastructure design to be completed. | 80 | We continue to receive ROW permits as needed in all counties and anticipate continued receipt in the next reporting quarter. | 80 | We anticipate continued receipt of pole attachment licenses from all utility companies as well as encroachment agreements from the various Railroad company. | 55 | The initial 4 Huts received have been installed during Q1. We anticipate the subsequent deliveries and installation during the Q3 and Q4 period., with final installation of all Huts completed in Q1 2013. | 51 | Our projection indicates that we would have procured over $14M of equipment during the next reporting quarter. | 78 | The network build component will increase exponentially as construction continues to ramp up. | 14 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 14 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-08-20 13:01 | 2012-08-20 13:01 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2012 | Q3 | Q3 - 2012 | 7970 | 6691 | FALSE | 77 | We anticipate our planned percentage to rapidly increase since the construction phase is well on its way. | 50 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 80 | Preliminary logical diagraming is currently being completed. Detailed splice engineering has begun. Plant infrastructure design to be completed. | 95 | We continue to receive ROW permits as needed in all counties and anticipate continued receipt in the next reporting quarter. | 95 | We anticipate continued receipt of pole attachment licenses from all utility companies as well as encroachment agreements from the various Railroad company. | 65 | 8 Huts have been received and installed. We anticipate the subsequent deliveries and installation during Q4 period with final installation of all Huts completed in Q1 2013. | 37 | Our projection indicates that we would have procured over $10M of equipment during the next reporting quarter. | 73 | The network build component will increase steadily as construction continues current high rates of production. | 28 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 26 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-11-20 10:51 | 2012-11-20 10:51 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2012 | Q4 | Q4 - 2012 | 9144 | 7958 | FALSE | 84 | Planned is 79% | 55 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 86 | Planned is 95%, logical network design is taking longer than anticipated since we must coordinate with 23 different networks. | 95 | Planned is 95% | 95 | Planned is 95% | 85 | Planned is 87% Three Huts that were scheduled for 4Q 2012 are now to be installed during Q1 2013. In all three cases, easement delays caused the Hut installation schedule to slip into the first quarter. | 52 | Our projection indicates that we would have procured over $8M of equipment during the next reporting quarter. | 73 | Planned is 74%, The network build component will increase steadily as construction continues current high rates of production. | 52 | Planned is 70%, Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 37 | Planned is 70%Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2013-03-22 13:49 | 2013-03-22 13:49 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2013 | Q1 | Q1 - 2013 | 9974 | 8531 | FALSE | 94 | Currently on schedule to completing the project on time. | 57 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 94 | Currently on schedule to completing the Network Design during the remaining months of the project. | 98 | On schedule to obtain all required Rights of Way by the end of Q2. | 98 | On schedule to obtain all required Rights of Way by the end of Q2. | 94 | Hut number 13 will be installed during 2Q 2013. Hut number 14 is awaiting easements from the State. The Hut is currently scheduled to be installed in late 2Q or early 3Q 2013. | 88 | Our projection indicates that we would have cumulatively procured over $16M of equipment during our next reporting quarter. | 94 | Network build will continue to maintain its current build out pace throughout the remaining months of the project. | 56 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 92 | Network Testing is currently on schedule to be completed during the remaining months of the project. | 2013-05-29 16:10 | 2013-05-29 16:10 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2013 | Q2 | Q2 - 2013 | 10702 | 9013 | FALSE | 100 | Small amount funds will remain for the 90 day closeout period. | 99 | Administration | Small amount funds will remain for the 90 day closeout period. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 2013-08-22 17:36 | 2013-08-22 17:36 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570135 | 2013 | Q3 | Q3 - 2013 | 11628 | 9748 | FALSE | 100 | Milestone Completed | 100 | Administration | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 2014-01-20 14:05 | 2014-01-20 14:05 | 6374 | 6374 | Information Technology, Maryland Department of
NT10BIX5570136 | 2010 | Q4 | Q4 - 2010 | 1122 | 2161 | FALSE | 9 | EA completed; mitigations will be necessary after FONSI is issued that may have an impact on progress of project. | 5 | IRU Leases | Legal review delay, and approval time for local board/council at next meetings. | 90 | Draft EA will be submitted prior to SAC deadline of March 1, 2011. | 70 | Early snow caused some outlying node location access issues; on hold to Spring. Several route changes for loss of BLM Backbone site being evaluated. | 30 | Applications filed; waiting for approvals | 0 | Permitting process will be pursued at locations ready to be built upon issuance of 'FONSI', anticipated in April 2011 | 0 | 0 | 6 | Begin purchase of some items in 6-month Environmental Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2011-02-12 11:32 | 2011-02-12 11:32 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2011 | Q1 | Q1 - 2011 | 1498 | 2462 | FALSE | 27 | No variance from baseline plan. | 32 | (in-kind IRU Leases) | No variance from baseline plan. We expect continued progress toward obtaining 316 in-kind IRU leases. | 100 | No variance from baseline plan. | 80 | Slightly behind baseline projections. Completion of network designs in dependent upon the acquisition of all necessary permits and approvals. | 35 | Slightly behind baseline projections based on processing time from gov't entities. | 9 | Slightly behind baseline projections due to delay in approval of Environmental Assessment. | 12 | No variance from baseline plan. We expect to begin construction of the backbone in June 2011. | 25 | No variance from baseline plan; 7-10 RFPs will be released next quarter. | 9 | No variance from baseline plan. | 9 | No variance from baseline plan. | 0 | Slightly behind baseline projections due to delay in approval of Environmental Assessment and subsequent delayed construction start | 2011-04-26 19:21 | 2011-04-26 19:21 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2011 | Q2 | Q2 - 2011 | 3292 | 3408 | FALSE | 15 | Behind baseline projections due to delay in FONSI and inability to construct. | 31 | 203 leases | Slightly behind of baseline plan. We expect continued progress toward obtaining 203 in-kind leases. | 100 | We expect to be slightly over budget on this milestone. | 63 | Slightly behind baseline projections based on actual expenditures for this category. Completion of network node design is dependent upon final FCC licensing, which is on hold until construction is imminent. | 31 | Slightly behind expenditures, but ROWs continue to be secured. | 2 | Slightly behind due to correlation with construction timing. | 1 | Behind baseline projections due to delay in approval of Environmental Assessment. | 2 | Behind baseline projections due to delay in Environmental Assessment. | 25 | Ahead of baseline expenditures as major pieces of the network are being secured. | 1 | Behind baseline projections due to delay in approval of Environmental Assessment and subsequent delayed construction start. | 1 | Behind baseline plan due to no construction, although some network testing has occurred as part of the equipment procurement process. | 2011-08-24 12:10 | 2011-08-24 12:10 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2011 | Q3 | Q3 - 2011 | 3898 | 3787 | FALSE | 36 | Behind baseline projections due to delay in FONSI and late construction start. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4 | 60 | 203 leases | On track with baseline plan. | 100 | Expect receipt of FONSI determination. No deviation from baseline plan. | 62 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 74 | Slightly behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 10 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 30 | Behind baseline projections due to delay in FONSI and late construction start. Locations will be secured and construction will begin next quarter. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 8 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 2011-11-04 15:52 | 2011-11-04 15:52 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2011 | Q4 | Q4 - 2011 | 4904 | 4590 | FALSE | 45 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 66 | 203 in-kind IRU leases | No variance from Baseline Plan. | 73 | GovNET completed its EA and received its FONSI during this reporting period. Additional funding remains in this category to cover any future EA amendments. | 73 | Behind baseline plan due to delay in EA approval, which restricted construction.GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 66 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012.Behind baseline plan due to delay in EA approval, which restricted construction. | 33 | Behind baseline plan due to delay in EA approval, which restricted construction.GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 52 | On track with Baseline Plan. We have secured a significant number of leases and will be purchasing a significant amount of equipment next quarter. We expect to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 25 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 2012-02-07 13:06 | 2012-02-07 13:06 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2012 | Q1 | Q1 - 2012 | 6046 | 5622 | FALSE | 48 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 62 | 203 in-kind IRU leases | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET expects to make continued progress toward obtaining 203 in-kind leases in the next quarter. | 89 | GovNET completed its EA and received its FONSI in Q4 2011. Additional funding remains in this category to cover any future EA amendments. | 85 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 62 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 40 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 53 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 32 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 2012-05-11 16:30 | 2012-05-11 16:30 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2012 | Q2 | Q2 - 2012 | 7262 | 6258 | FALSE | 44 | Project restart anticipated with outstanding unpaid reimbursements received, putting the project % complete numbers more in line since they are based on dollars expended. Multiple crews will be utilized statewide for construction & installations. | 95 | 203 in-kind IRU leases | Ahead of baseline plan projections with expected approval to add CAIs who already signed leases into project. | 95 | GovNET achieved this milestone & received a FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and/or compliance administrative costs. | 85 | Slightly behind baseline plan projections due to review of the project by NTIA in Summer 2012. FCC licenses are held in Prior Coordination Notice (PCN) and are filed as site construction is imminent. | 72 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 34 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. Any construction permits required are filed just prior to imminent work due to limited time frame valid. | 56 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 40 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 37 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 20 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 27 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 2012-08-28 14:53 | 2012-08-28 14:53 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2012 | Q3 | Q3 - 2012 | 8016 | 6714 | FALSE | 47 | Project restart anticipated with outstanding unpaid reimbursements received, putting the project % complete numbers more in line since they are based on dollars expended. Multiple crews will be utilized statewide for expedited construction & installations. | 95 |  | Ahead of baseline plan projections with expected approval to add CAIs who already signed leases into project. | 95 | GovNET achieved this milestone & received a FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and/or compliance administrative costs. | 88 | Slightly behind baseline plan projections due to project suspension by NTIA. FCC licenses are held in Prior Coordination Notice (PCN) and are filed as site construction is imminent. | 72 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a project hold by NTIA. | 34 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. Any construction permits required are filed just prior to imminent work due to limited time frame valid. | 56 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 40 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 37 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 20 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 27 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 2012-11-21 11:14 | 2012-11-21 11:14 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2012 | Q4 | Q4 - 2012 | 8822 | 7609 | FALSE | 49 | Increase in project spending in March if suspension is lifted in February. | 90 | In-Kind Leases | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work if suspension is lifted. | 82 | FCC licenses will be held until site construction is imminent. | 64 | No change due to necessary lead time to re-engage. | 30 | Increase in advance activity. | 40 | No change | 42 | Increase due to outstanding vendor payments | 28 | Increase due to restarting of construction activity | 15 | Increase due to restarting of construction activity | 17 | No change | 2013-02-15 16:31 | 2013-02-15 16:31 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2013 | Q1 | Q1 - 2013 | 9784 | 8426 | FALSE | 49 | Projected increase in funds reimbursed for outstanding vendors. | 90 | In-Kind leases | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work if suspension is lifted. | 82 | FCC licenses will be held until site construction is imminent. | 64 | No change due to necessary lead time to re-engage. | 30 | Increase in advance activity. | 40 | No change. | 42 | Increase due to outstanding vendor invoice payments. | 28 | Increase due to restarting of project activity. | 15 | Increase due to restarting of project activity. | 17 | No change. | 2013-05-16 19:49 | 2013-05-16 19:49 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2013 | Q2 | Q2 - 2013 | 10706 | 9015 | FALSE | 50 | Projected increase in funds reimbursed for outstanding vendors and forward progress on the network build. | 90 |  | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work to progress project. | 82 | FCC licenses will be held until site construction is imminent. | 68 | Increase in advance activity. | 30 | Increase in advance activity. | 42 | Slight increase as construction activity restarts. | 48 | Increase due to outstanding vendor invoice payments and new purchases. | 28 | Increase due to restarting of project activity. | 15 | Increase due to restarting of project activity. | 17 | No change. | 2013-08-22 19:18 | 2013-08-22 19:18 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2013 | Q3 | Q3 - 2013 | 11268 | 9425 | FALSE | 58 | Project increase in funds reimbursed for outstanding vendors and forward progress on the network build. | 65 |  | Additional CAI leases signed and returned. | 90 | Increase in environmental/ cultural work to progress project. | 82 | FCC Licenses will be held until site construction is imminent | 70 | Increase in advance activity | 30 | Increase in advance activity | 42 | Slight Increase as construction activity restarts | 48 | Slight Increase as construction activity restarts; invoicing will be following quarter | 28 | Increase due to restarting of project activity | 18 | Increase due to restarting of project activity | 17 | No Change | 2013-11-15 13:22 | 2013-11-15 13:22 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2013 | Q4 | Q4 - 2013 | 11818 | 9995 | FALSE | 63 | Project increase in funds being spent and reimbursed for equipment and construction items committed for the network build. | 65 |  | Additional CAI & in-kind leases signed and returned | 93 | Increase in environmental/ cultural work to progress project as required. | 82 | FCC Licenses in advance activity | 70 | Increase in activity and signed documents | 30 | Increase in activity | 48 | Increase as construction activity restarts | 52 | Increase as construction activity restarts; sizable invoicing and reimbursement request will be following quarter | 30 | Increase due to restarting of project activity | 18 | Increase due to restarting of project activity | 19 | Increase due to restarting of project activity | 2014-02-13 23:16 | 2014-02-13 23:16 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2014 | Q1 | Q1 - 2014 | 12232 | 10403 | FALSE | 74 | Project increase in funds being spent and reimbursed for equipment and construction items committed for the network build. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. | 75 |  | Additional CAI & in-kind leases signed and returned | 95 | Increase in environmental/ cultural work to progress project as required. | 84 | FCC Licenses filed and PCNs secured for new sites | 75 | Increase in activity and signed documents | 35 | Increase in activity | 52 | Increase as construction activity restarts | 60 | Increase as construction activity restarts; sizable invoicing and reimbursement request will be following quarter | 35 | Increase due to restarting of project activity | 25 | Increase due to restarting of project activity; Ring C active | 25 | Increase due to restarting of project activity; Ring C active | 2014-05-22 19:00 | 2014-05-22 19:00 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2014 | Q2 | Q2 - 2014 | 12434 | 10623 | FALSE | 75 | Significant project increase in funds being spent and reimbursed for equipment and construction items as the network build ramps up. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. | 100 | 203 leases | Exceeded Baseline scope for CAI & in-kind leases signed and recieved | 97 | Increase in environmental/ cultural work to progress project as required. | 94 | Design complete, only need to file FCC Licenses as new sites are brought online. | 80 | Increase in activity to complete process and receive signed documents | 55 | Increase in construction activity. | 70 | Increase as construction activity restarts | 80 | Increase as construction activity continues. Sizable invoicing and reimbursement requests processed. | 55 | Increase due to restarting of project activity | 50 | Increase due to restarting of project activity; Rings C, B & A active | 50 | Increase due to restarting of project activity; Rings C, B & A active | 2014-08-19 01:10 | 2014-08-19 01:10 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2014 | Q3 | Q3 - 2014 | 12612 | 10880 | FALSE | 84 | Significant project construction activity will continue with funds being spent and reimbursed for equipment and construction items necessary to build network. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. | 100 | 203 leases | Exceeded Baseline scope for CAI & in-kind leases signed and received | 97 | Increase in environmental/ cultural work to progress project as required. | 94 | Design complete, only need to file FCC Licenses as new sites are brought online. | 82 | Increase in activity to complete process and receive signed documents | 55 | Increase in construction activity. | 70 | Increase as construction activity begins. | 87 | Increase as construction activity continues. Sizable invoicing and reimbursement requests processed. | 60 | Increase due to restarting of project activity | 57 | Increase due to restarting of project activity; Rings C, B & A active | 50 | Increase due to restarting of project activity; Rings C, B & A active | 2014-11-24 15:18 | 2014-11-24 15:18 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2014 | Q4 | Q4 - 2014 | 12728 | 11054 | FALSE | 90 | Significant project construction activity will continue with funds being spent and reimbursed for equipment and construction items necessary to build network. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. Additional factors affecting progress include getting new contractors up to speed, critical network component delivery delay, and weather issues. | 100 |  | Exceeded Baseline scope for CAI & in-kind leases signed and received | 97 | Increase in environmental/ cultural work to progress project as required. | 95 | Design complete, only need to file FCC Licenses as new sites are brought online | 80 | Increase in activity to complete process and receive signed documents | 60 | Increase in continued construction activity. | 75 | Increase in continued construction activity. | 90 | Increase as construction activity continues. Sizable invoicing and reimbursement requests processed. | 50 | Increase in continued construction activity. | 57 | Increase in continued construction activity.; Rings C, B & A active | 50 | Increase in continued construction activity.; Rings C, B & A active | 2015-02-26 12:21 | 2015-02-26 12:21 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2015 | Q1 | Q1 - 2015 | 12842 | 11214 | FALSE | 99 | Significant project construction activity will continue. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. Additional factors affecting progress include getting new contractors up to speed, critical network component delivery delay, and weather issues. | 100 |  | Exceeded Baseline scope for CAI & in-kind leases signed and received | 98 | Increase in environmental/ cultural work to progress project as required. | 97 | Design complete, only need to file FCC Licenses as new sites are brought online | 80 | Increase in activity to complete process and receive signed documents | 80 | Increase in continued construction activity. | 75 | Increase in continued construction activity. | 90 | Increase as construction activity continues. | 75 | Increase in continued construction activity. | 80 | Increase in continued construction activity.; Rings C, B & A active | 70 | Increase in continued construction activity.; Rings C, B & A active | 2015-05-26 12:49 | 2015-05-26 12:49 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570136 | 2015 | Q2 | Q2 - 2015 | 12908 | 11286 | FALSE | 100 | Significant project construction activity will continue to complete network Backbone. Overall project variance (includes #2b-2k) from baseline plan is due to 16+ month suspension delaying forward progress. Additional factors affecting progress include getting new contractors up to speed, critical network component delivery delay, and weather issues. | 100 |  | Exceeded Baseline scope for CAI & in-kind leases signed and received | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 100 | Completed per construction activity. | 98 | Majority of equipment deployed; any remaining equipment will be deployed at GovNET cost to complete project scope; Rings C, B, A & D all active | 100 | Increase in continued construction activity.; Rings C, B, A & D active | 42256.7495 | 42256.7495 | 6337 | 6337 | GOVNET, INC.
NT10BIX5570138 | 2010 | Q4 | Q4 - 2010 | 708 | 1744 | FALSE | 2 | No variance from baseline | 50 | (Power Pole Make Ready) (HC) | No variance from baseline | 75 | No variance from baseline | 70 | No variance from baseline | 20 | No variance from baseline | 10 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | Construction has not begun as FONSI has not yet been recieved | 0 | No variance from baseline | 0 | No variance from baseline | 2011-01-28 11:57 | 2011-01-28 11:57 | 6339 | 6339 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2011 | Q1 | Q1 - 2011 | 1848 | 2667 | FALSE | 7 | No variance from baseline | 100 |  | Power pole make ready HCTC. | 100 | No variance from baseline | 90 | No variance from baseline | 100 | No variance from baseline | 50 | No variance from baseline | 12 | No variance from baseline | 6 | No variance from baseline | 22 | No variance from baseline | 4 | No variance from baseline | 5 | No variance from baseline | 2011-05-02 14:35 | 2011-05-02 14:35 | 6339 | 6339 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2011 | Q2 | Q2 - 2011 | 3074 | 3294 | FALSE | 15 | -15% Variance due to construction delay. This variance should be eliminated in Q4 of 2011 (Q2 of BTOP Project Year 2). Region 18 is tracking project completion based upon actual work completed not on $ spent. The additional dollars forecast are reflective of two items. 1. An up front payment of $1,000,000 to Dell City Telephone for the purpose of purchasing equipment. 2. The annual up front payment on the contract for Project Management. The amount of this payment will be $220,000. These two items total $1,220,000 which bridges the gap between the projection of 15% of work completed and the projected spending of 22.05%. | 50 | Power Pole Make-Ready | Delay due to FONSI not issued. Expect to move forward this quarter and complete in Q4 of 2011 | 100 | No Variance | 100 | No Variance | 100 | No Variance | 30 | - 45% As stated above, construction permits are valid for 60 days. We expect that 30% will have been requested and approved by the end of the next quarter. | 15 | -55% Site prep will be in line with overall project completion. Some variation due to later start of construction. Also, baseline estimate of 70% completion at this stage not in line with construction time frame of overall project. | 75 | +59% We will be ahead of baseline projection and in line with overall current project projections. Baseline estimate was not in line with construction time frame of overall project. | 5 | -30% Network build will be in line with overall project completion. Some variation due to later start of construction. Also, baseline estimate of 35% was high expectation for this stage of the project. | 6 | No Variance | 0 | -6% Do not expect to have enough CAI's connected to perform network testing prior to end of next quarter. Expect to be back on track by the end of Q4 2011 | 2011-08-15 10:27 | 2011-08-15 10:27 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2011 | Q3 | Q3 - 2011 | 4046 | 3863 | FALSE | 30 | -10% variance to baseline. Delay in start of construction. This gap should be closed by the end of the following reporting quarter (Q1 2012). | 100 | Power Pole make ready (HCTC) | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 50 | -40% variance to baseline. Due to the fact that permits are valid for 60 days and must be acquired closer to the start of each construction route. | 80 | No variance | 80 | No variance | 7 | -38% variance to baseline, due to delay in construction start. Will be closing gap rapidly as construction begins. | 35 | No variance | 7 | -57% variance again due to delay of construction start | 2011-11-15 10:45 | 2011-11-15 10:45 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2011 | Q4 | Q4 - 2011 | 5242 | 4903 | FALSE | 48 | -7% variance to baseline. As noted we anticipate making great progress during this quarter. | 100 | HCTC pole make ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 60 | -40% to baseline. Permits are only valid for 60 days. These are being acquired as needed throughout the project. | 80 | -10% variance to baseline. We anticipated closing the gap to baseline by the end of Q3 2012. | 90 | No variance | 48 | -10% variance to baseline. | 55 | No variance | 35 | -30% variance to baseline. | 2012-02-24 10:32 | 2012-02-24 10:32 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2012 | Q1 | Q1 - 2012 | 6278 | 5741 | FALSE | 71 | This will be on track with our baseline forecast. We expect that with construction moving forward as it has been and with the CAI's planned for connection that we will be able to attain this % complete. | 100 | HCTC Pole make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 80 | -20% variance to baseline. Permits are only valid for 60 days. These are being acquired as needed through the project. | 90 | No variance to baseline | 90 | No variance to baseline | 60 | -10% variance to baseline. | 70 | No variance to baseline | 14 | -54% variance to baseline. We anticipate approximately 14% of our CAI's to be connected and tested by the end of Q2 2012. We will have a much greater % of fiber run but not necessarily connected by the end of Q2. | 2012-05-24 10:14 | 2012-05-24 10:14 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2012 | Q2 | Q2 - 2012 | 7096 | 6175 | FALSE | 90 | This will put us 8% ahead of baseline. At the end of Q3 2012 we forecast that 97% of construction dollars will have been spent with three of five telephone companies having completed their construction phase of the project (Poka Lambro, WesTex and Dell City) though not all CAI connections made. Poka Lambro and WesTex have completed their CAI connections. Hill Country Telephone has 17 of 21 miles completed as of Q2 and we anticipate progress on the remaining miles in Q3. Big Bend will complete the wireless miles as well as several important CAI connections. A total of 90% of program dollars will have been spent. The reason for the 80% planned completion is due to the number of CAI's still to be connected as well as the network testing that will need to be completed. | 100 | HCTC Pole Makeready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10% variance to baseline. Construction permits are only valid for 60 days and are being acquired as needed. Big Bend is more than 60 days from completion of all construction. | 100 | No variance to baseline | 100 | No variance to baseline | 60 | -15% to baseline. We will have 100% of our interconnection (peering) points connected and approximately 90% of our fiber laid with 44% of committed CAI's connected. | 90 | 9% ahead of baseline. Construction moving ahead of plan. | 15 | -55% off baseline. Baseline projections were off. Planned testing to be completed will be in line with the % complete we are forecasting for CAI connections (19.5% of CAI's forecast). | 2012-08-15 17:09 | 2012-08-15 17:09 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2012 | Q3 | Q3 - 2012 | 7856 | 6632 | FALSE | 89 | +15% ahead of baseline. Majority of project $ related to construction. We are ahead of schedule with fiber installation. | 100 | HCTC Pole Make Ready | No variance to baseline | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10 variance to baseline. Construction permits only valid for 60 days. Big Bend is greater than 60 days from project completion. | 100 | No variance | 100 | No variance | 70 | -15% to baseline. We are ahead on construction. We will progress with our build by adding service to additional CAI locations. | 90 | No variance to baseline | 15 | -65% to baseline. Baseline projections were off. Planned testing to be completed on CAI connections receiving service. | 2012-11-13 23:06 | 2012-11-13 23:06 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2012 | Q4 | Q4 - 2012 | 9000 | 7777 | FALSE | 93 | -2% variance to baseline. Slightly off of baseline projection due to stoppage of construction for route change request review. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10% variance to baseline. Construction permits only valid for 60 days. Big Bend is greater than 60 days from project completion. | 95 | Big Bend still has routes to complete | 100 | No variance | 90 | -5% to baseline. Due to work stoppage on Big Bend routes will not complete construction this quarter. | 90 | -10% to baseline. Ongoing service connection and 2 wireless sites still to be connected. | 50 | -45% to baseline. Service connections are ongoing. Due to work stoppage on Big Bend routes cannot plan to have connected by end of Q1. | 2013-02-27 10:56 | 2013-02-27 10:56 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2013 | Q1 | Q1 - 2013 | 9966 | 8527 | FALSE | 95 | -5% to baseline. Delay due to route change requests. Based on program dollars forecast spent to date. | 100 | HCTC pole make ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | -5% to baseline. Delay due to route change requests. Permits only valid for 60 days. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5 to baseline. Delay due to route change requests. | 65 | -35% to baseline. Construction still ongoing. | 2013-05-29 14:34 | 2013-05-29 14:34 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2013 | Q2 | Q2 - 2013 | 10632 | 8976 | FALSE | 100 | No variance | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-08-19 08:47 | 2013-08-19 08:47 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2013 | Q3 | Q3 - 2013 | 11364 | 9487 | FALSE | 97 | Project will complete favorable to planned budget. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | NO variance | 100 | NO variance | 2013-11-22 23:16 | 2013-11-22 23:16 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570138 | 2013 | Q4 | Q4 - 2013 | 12212 | 10384 | FALSE | 100 | project is complete and is 3.3% favorable to budget. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-05-19 15:27 | 2014-05-19 15:27 | 6341 | 6341 | Region 18 Education Svc Ctr.
NT10BIX5570139 | 2010 | Q4 | Q4 - 2010 | 1248 | 2278 | FALSE | 10 | No variance | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 35 | No variance | 25 | No variance | 10 | No variance | 10 | No variance | 10 | No variance | 0 | N/A | 2 | No variance | 2011-02-20 20:05 | 2011-02-20 20:05 | 5742 | 5742 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2011 | Q1 | Q1 - 2011 | 2144 | 2817 | FALSE | 20 | Better than anticipated make-ready completion | 0 |  | N/A | 100 | No variance | 100 | No variance | 45 | No variance | 35 | No variance | 35 | Better than anticipated make-ready completion | 7 | The original baseline listed 10% completion of Equipment Procurement by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion. The calculation error was only discovered on this quarter's PPR. The Equipment Procurement percentage listed for next quarter's PPR is an accurate prediction. | 7 | The original baseline listed 10% completion of Network Build by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion and equipment procurement. The calculation error was only discovered on this quarter's PPR. In this quarter, Network Build followed close enough behind Equipment Procurement to match percentages. Going forward, Network Build may match Equipment Procurement or follow closely behind. The percentage listed for next quarter's PPR is an accurate prediction. | 0 | N/A | 3 | The original baseline listed 10% completion of Network Testing by next quarter's end to match the 15% Overall Project completion also listed. However, that calculation is incorrect as there is a time lag between construction completion and Network Testing. This means that the percentage of Network Testing will track more slowly against the Overall Project rate than the percentages calculated in the original baseline. The calculation error was only discovered on this quarter's PPR. The percentage listed for next quarter's PPR is an accurate prediction. | 2011-05-18 16:16 | 2011-05-18 16:16 | 5742 | 5742 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2011 | Q2 | Q2 - 2011 | 3314 | 3419 | FALSE | 43 | Better than anticipated make-ready completion is moving the project along faster than anticipated | 0 |  | N/A | 100 | No variance | 100 | No variance | 55 | No variance | 55 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 55 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 20 | No variance | 20 | No variance | 0 | N/A | 20 | No variance | 2011-08-25 13:14 | 2011-08-25 13:14 | 5742 | 5742 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2011 | Q3 | Q3 - 2011 | 4328 | 4014 | FALSE | 50 | Better than anticipated make-ready completion is moving the project along faster than anticipated. | 0 |  | N/A | 100 | No variance | 100 | No variance | 65 | No variance | 75 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 75 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 25 | No variance | 25 | No variance | 0 | N/A | 25 | There is an error in the baseline calculation as it lists 30 percent planned completion, but testing cannot happen in advance of network build. | 2011-11-29 18:06 | 2011-11-29 18:06 | 5461 | 5461 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2011 | Q4 | Q4 - 2011 | 5076 | 4748 | FALSE | 70 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 75 | No variance. | 85 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 82 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | In the next quarter, we anticipate executing the contract, ordering the equipment, receiving the equipment and paying for the equipment. This will complete this section. | 55 | Better than anticipated make-ready completion continues to allow for faster than anticipated construction. | 30 | No variance. | 55 | Better than anticipated make-ready and construction completion continues to allow for faster than anticipated network testing. | 2012-02-16 19:08 | 2012-02-16 19:08 | 5461 | 5461 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2012 | Q1 | Q1 - 2012 | 6026 | 5612 | FALSE | 76 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 90 | Better than anticipated make-ready completion will allow for faster than anticipated complete rights of way. | 97 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 92 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | The final materials have shipped and the vendor shall invoice for the equipment; payment will be made in accordance with the contract terms and should complete in the upcoming quarter. | 70 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 | N/A | 65 | Better than anticipated make-ready completion will allow for faster than anticipated network testing. | 2012-05-10 16:22 | 2012-05-10 16:22 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2012 | Q2 | Q2 - 2012 | 6894 | 6073 | FALSE | 85 | Better than anticipated make-ready completion accelerated better than anticipated construction completion. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 99 | Better than anticipated make-ready completion will allow for faster than anticipated complete rights of way. | 99 | Better than anticipated make-ready completion. | 98 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | No variance. | 98 | While the backbone is complete, we are working on the approved route extension and the remaining CAI's. | 0 | N/A | 98 | While the backbone is complete, we are working on the approved route extension and the remaining CAI's; testing follows construction completion. | 2012-08-07 14:40 | 2012-08-07 14:40 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2012 | Q3 | Q3 - 2012 | 8018 | 6715 | FALSE | 86 | We will remain ahead of baseline due to backbone construction completing ahead of schedule. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | All Rights-of-Ways should be complete | 99 | Better than anticipated make-ready completion. | 99 | Continues ahead of schedule progress; the site preparation tracks closely with the construction permits and other approvals. | 100 | All DWDM gear has been received. | 97 | All construction on remaining CAIs and route extensions is expected to be complete, with Regeneration Shelter work to continue into 2013 | 0 | N/A | 100 | All testing on remaining CAIs and route extensions is expected to be complete | 2012-11-21 13:16 | 2012-11-21 13:16 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2012 | Q4 | Q4 - 2012 | 8696 | 7507 | FALSE | 86 | We will remain ahead of baseline due to backbone construction completing ahead of schedule. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | All Rights-of-Ways should be complete | 100 | All permits, including for regeneration shelters, are expected to be complete | 99 | Minimal Site prep work for regeneration shelters may still exist | 100 | All DWDM gear has been received. | 98 | Only Regeneration Shelter work expected to continue into Q2 2013 | 0 | N/A | 100 | All testing on remaining 4 CAIs is expected to be complete | 2013-02-11 10:30 | 2013-02-11 10:30 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2013 | Q1 | Q1 - 2013 | 9864 | 8469 | FALSE | 97 | Anticipates IRUs and regeneration shelters completing in Q2 | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | All known rights of way will be complete | 100 | All known permitting will be complete | 100 | All known Make Ready will be complete | 100 | All DWDM gear has been recived | 99 | Minimal costs may remain for Q3, but work should be substantially complete (this includes regeneration shelters and the approved IRUs) | 0 | n/a | 100 | All known testing will be complete | 2013-05-22 08:25 | 2013-05-22 08:25 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2013 | Q2 | Q2 - 2013 | 10458 | 8875 | FALSE | 100 | All items to be complete, no variance from baseline | 0 |  | n/a | 100 | No variance from baseline | 100 | No variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All DWDM gear received, no variance from baseline | 100 | All items to be complete, no variance from baseline | 0 | n/a | 100 | All items to be complete, no variance from baseline | 2013-07-31 12:12 | 2013-07-31 12:12 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570139 | 2013 | Q3 | Q3 - 2013 | 11614 | 9741 | FALSE | 100 | All items remain complete | 0 |  | n/a | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 0 | n/a | 100 | All items remain complete | 2014-01-16 10:06 | 2014-01-16 10:06 | 7216 | 7216 | Maine Fiber Company, Inc.
NT10BIX5570140 | 2010 | Q4 | Q4 - 2010 | 1168 | 2203 | FALSE | 20 | Since overall completion includes site surveys, detailed planning, engineering, and other pre-construction costs which have no associated matching costs or Federal expenditures in this quarter, the overall completion percentage is greater than the projected total expenditures budgeted in the next quarter. | 0 | 0 | n/a | 100 | per baseline | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 36 | per baseline | 20 | per baseline | 30 | per baseline | 20 | per baseline | 2011-02-15 21:59 | 2011-02-15 21:59 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2011 | Q1 | Q1 - 2011 | 2234 | 2862 | FALSE | 20 | We expect that the overall project will be behind the baseline due to the delays in the FONSI and equipment deliveries. | 0 | 0 | n/a | 100 | Anticipated that the FONSI will be issued during the next quarter, allowing the project to start construction. | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 100 | per baseline | 15 | Network build completion percentage will be lower than baseline, with the actual amount depending upon when the FONSI is issued.. | 25 | We expect the equipment deployment to slow catch up to baseline percentages after all equipment is received next quarter. | 15 | Network testing completion percentage will be lower than baseline, with the actual amount depending upon when the FONSI is issued next quarter, | 2011-05-20 21:01 | 2011-05-20 21:01 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2011 | Q2 | Q2 - 2011 | 3064 | 3289 | FALSE | 20 | Overall project completion percentage will still be below the baseline as the project catches up with delays from the FONSI and equipment deployment. Although closely related, overall project percent completion will not directly correspond to percentage expended and is not expected to do so for this project for a number of reasons including: equipment may be received but not installed in exactly the same quarter, equipment may be received and installed but not paid for or drawn down within the same quarter, work may be done but not yet paid for and drawn down in the same quarter, specific item costs might vary slightly (up or down) from budgeted amounts, etc. In this next quarter, which is our actual project startup from a construction perspective, we expect to buy more equipment than can be deployed within the quarter in order to streamline administrative processing and maximize discounts. | 0 |  | n/a | 100 | FONSI has been issued. No further action on this milestone required. | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 45 | Purchasing of the remainder of equipment has been delayed due to the delay in the construction schedule which could not begin until the FONSI was issued. Partial orders of additional equipment will be done during the next quarter. It is not expected that all of the equipment will be purchased until the end of the 2nd year. | 20 | Network build completion percentage will continue to be lower than Baseline until delays caused by the late issuance of the FONSI (June 2011) can be made up but construction will start during this quarter. . | 25 | Equipment deployment will be lower than the Baseline this quarter since it was not possible to procure all equipment until construction could begin. We expect to ramp up the deployment this quarter but will not catch up to Baseline until later this calendar year due to late issuance of FONSI. | 20 | Network testing will commence as fiber is installed to locations. Network testing percentage will be behind the baseline as the project catches up with installations. | 2011-08-12 16:31 | 2011-08-12 16:31 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2011 | Q3 | Q3 - 2011 | 4314 | 4007 | FALSE | 37 | Previous delays have caused the project to fall behind the baseline. However recent installations and the start of construction is allowing the project to slowly catch up to the baseline numbers. Project should see significant progress in completion percentages over the next quarter with a corresponding increase in matching funds as construction progresses. Although closely related, overall project percent completion will not directly correspond to percentage expended and is not expected to do so for this project for a number of reasons including: equipment may be received but not installed in exactly the same quarter, equipment may be received and installed but not paid for or drawn down within the same quarter, work may be done but not yet paid for and drawn down in the same quarter and specific item costs might vary slightly (up or down) from budgeted amounts. | 0 |  | n/a | 100 | completed per baseline | 100 | completed per baseline | 0 | n/a | 0 | n/a | 100 | completed per baseline | 95 | Almost all equipment in the network design will have been purchased by the end of the quarter. Procurement will be slightly less than the Baseline until construction can progress to the point where the additional equipment will be needed and procured. | 24 | Previous delays have caused the project to fall behind baseline. All interisland links should be completed by this quarter and more CAIs will be connected to the network. | 50 | Although over the next quarter the DOE and HSPLS will be making a push to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands, deployment is not expected to catch up to the Baseline projections during this quarter. | 24 | Network testing will track Network Build and will continue to be behind the Baseline until the project catches up with installations. As sites are connected, the links will be fully tested and then put into production. | 2011-11-29 13:34 | 2011-11-29 13:34 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2011 | Q4 | Q4 - 2011 | 4922 | 4602 | FALSE | 48 | Previous delays due to the late receipt of the FONSI and a decreased construction work schedule during the holidays have caused the project to fall behind the Baseline. Significant progress is expected over the next quarter as sites are being lined up for actual fiber construction and more pole applications are being approved. Overall project percent completion will not directly correspond to percentage expended for a number of reasons, including: equipment may not be installed in exactly the same quarter as received or may be received and installed but not paid or drawn down in the same quarter. Work may be performed but not paid or drawn down in the same quarter and specific item costs may be slightly more or less that budgeted. | 0 |  | n/a | 100 | completed per baseline | 100 | completed per baseline | 0 | n/a | 0 | n/a | 100 | completed per baseline | 98 | Almost all equipment will have been received, inventoried and paid for by the end of this quarter. Procurement will be slightly less than the Baseline until construction can progress to the point where the final equipment is needed and is procured. | 34 | All interisland links will have been completed and activated by the end of this quarter. Significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is below the baseline due to the previous quarters' delays in the EA process and the resulting delay in construction. | 60 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH will be working with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. | 34 | Network testing will track network build and will continue to be behind the baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production. | 2012-02-08 16:54 | 2012-02-08 16:54 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2012 | Q1 | Q1 - 2012 | 6208 | 5706 | FALSE | 52 | Overall completion is still behind the Baseline due to the late receipt of FONSI and resulting construction delays in previous quarters. The process for pole approvals has improved so significant progress in fiber construction is expected over the next quarter. Overall project percent completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and siginifcant construction work completed near the end of the quarter may not be paid until the following quarter. | 0 |  | n/a | 100 | Completed per baseline | 100 | Completed per baseline | 0 | n/a | 0 | n/a | 100 | Completed per baseline | 98 | Almost all equipment will have been received and paid by the end of this quarter. Procurement will be slightly less than the Baseline until construction progresses to the point where final equipment is needed and procured. | 38 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 71 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 38 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 2012-05-18 16:50 | 2012-05-18 16:50 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2012 | Q2 | Q2 - 2012 | 7024 | 6139 | FALSE | 43 | Overall Project percentage reported is based on funds expended (Total funds including match). The actual project based on the fiber construction, equipment installation and site activation is expected to be 61% completed. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 50 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 80 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 50 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2012-08-10 17:41 | 2012-08-10 17:41 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2012 | Q3 | Q3 - 2012 | 7886 | 6647 | FALSE | 52 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at close to 70%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 70 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 85 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 70 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2012-11-14 20:30 | 2012-11-14 20:30 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2012 | Q4 | Q4 - 2012 | 8754 | 7550 | FALSE | 54 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at 75%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 75 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 90 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. Some equipment will be installed when sites are activated due to logistical issues. As such, deployment will not be fully completed until all sites have been activated. | 75 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2013-02-13 14:15 | 2013-02-13 14:15 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2013 | Q1 | Q1 - 2013 | 9806 | 8438 | FALSE | 69 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at 90%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | completed | 90 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 95 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. Some equipment will be installed when sites are activated due to logistical issues. As such, deployment will not be fully completed until all sites have been activated. | 90 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2013-05-17 18:00 | 2013-05-17 18:00 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2013 | Q2 | Q2 - 2013 | 10590 | 8952 | FALSE | 96 | Overall project completion percentage is based on funds expended (total funds including match). The actual construction completion percentage is also estimated at 96%. The initial delay of nearly a year for Environmental Assessment (EA) caused more applications for utility poles and conduits to be submitted than could be processed in that shorter time frame. This is a major reason why completion is less than Baseline and why we are requesting a 6-month no cost extension to complete the remaining sites. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | completed | 96 | All but approximately 19 sites would have been completed. These 19 are part of the requested no cost extension. | 100 | completed | 96 | Network testing will track the Network Build. | 2013-08-14 19:54 | 2013-08-14 19:54 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2013 | Q3 | Q3 - 2013 | 11288 | 9441 | FALSE | 97 | Overall project completion percentage is based on funds expended (total funds including match). The actual construction completion percentage is estimated at 98% as the project continues to work on the extension sites. | 0 | true | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 99 | Almost all equipment will have been purchased by the next quarter. Previous quarter estimation was that all equipment was to be purchased. Due to the extension, some equipment purchases were delayed to wait for fiber build completion of the extension sites. | 98 | Network build will be almost all completed - we are expecting the last few extension sites to still be in construction by the end of next quarter per the extension project plan. | 98 | Almost all equipment will have been deployed to the sites and will be awaiting the fiber build. Previous quarter estimation was that all equipment was to be purchased. Due to the extension, some equipment installations were delayed to wait for fiber build completion of the extension sites. | 98 | Network testing tracks the network build. | 2013-11-19 12:13 | 2013-11-19 12:13 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2013 | Q4 | Q4 - 2013 | 11902 | 10069 | FALSE | 99 | Overall project completion percentage is based on funds expended (total funds including match). Actual construction completion percentage will be 100%. The project will not be able to spend 100% of the funds. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | All equipment for the project will have been purchased. | 100 | Network will be fully built. | 100 | All equipment will have been deployed | 100 | Network will be 100% tested | 2014-02-26 21:15 | 2014-02-26 21:15 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570140 | 2014 | Q1 | Q1 - 2014 | 12224 | 10397 | FALSE | 100 | Project Completed. 99% of the the funding has been expended. 100% of the sites have been completed. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2014-05-21 16:50 | 2014-05-21 16:50 | 6701 | 6701 | University of Hawaii Systems
NT10BIX5570144 | 2010 | Q4 | Q4 - 2010 | 1256 | 2285 | FALSE | 11 | no variance | 0 | n/a | not applicable | 100 | no variance | 14 | no variance | 28 | no variance | 28 | no variance | 0 | no variance | 8 | no variance | 4 | no variance | 2 | no variance | 2 | no variance | 2011-02-21 13:17 | 2011-02-21 13:17 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2011 | Q1 | Q1 - 2011 | 2398 | 2944 | FALSE | 4 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | not applicable | not applicable | 100 | no variance | 2 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 17 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | no variance | 0 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 3 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 13 | no variance | 11 | no variance | 2011-05-31 11:39 | 2011-05-31 11:39 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2011 | Q2 | Q2 - 2011 | 3162 | 3341 | FALSE | 27 | Variance 3% - Construction will begin in mid July with the first contractor. The second contractor will begin construction in mid August. Two contractors on the project will facilitate progress in the next quarter. Permitting and rights of way will be in full gear and should progress in advance of construction. | 0 | n/a | not applicable | 100 | no variance | 31 | Variance -11% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. The core network design will be 65% completed during this quarter. Additionally we anticipate having a majority of CAIs with commitments to the project and will be in the process of finalizing last mile routes and engineering. | 10 | Variance -43% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be little variance from the baseline plan for the project at twelve months and two weeks from initiation. Permitting and rights of way will continue through the quarter to get ahead of construction by 3 - 6 months. We anticipate submitting all applications for rights of way during this quarter. | 10 | Variance -43% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be little variance from the baseline plan for the project at twelve months and two weeks from initiation. Permitting and rights of way will continue through the quarter to get ahead of construction by 3 - 6 months. We anticipate having permits for all submitted applications during this quarter. | 0 | Variance -17% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter which may not generate site preparation expenditures until the following quarter. | 16 | Variance -17% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. The wireless installation and equipment RFP will be released during this quarter. We anticipate the start of equipment procurement however, activities will outpace expenditures during the quarter. | 21 | no variance | 10 | Variance -15% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter. We anticipate the start of equipment deployment however, activities will outpace expenditures during the quarter. | 10 | Variance -15% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter. We anticipate the start of network testing however, activities will outpace expenditures during the quarter. | 2011-08-17 16:53 | 2011-08-17 16:53 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2011 | Q3 | Q3 - 2011 | 3936 | 3806 | FALSE | 24 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 0 | n/a | not applicable | 100 | no variance | 23 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 29 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 50 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 23 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 20 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 25 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 25 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 15 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 2011-11-09 13:39 | 2011-11-09 13:39 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2011 | Q4 | Q4 - 2011 | 5142 | 4808 | FALSE | 37 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. Construction activity will continue despite the winter weather with more activity focused on boring rather than plowing. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. We anticipate reaching over 90% of our CAIs and securing commitments from 60%. The CAI equipment will be received during February with installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 0 | N/A | N/A | 100 | no variance | 40 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having over 95% of the new fiber optic network designed and submitted with 60% of the network permitted. Engineering will begin on 6 of the wireless network links during the quarter. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having 60% of the new fiber optic network permitted during the quarter. | 72 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having 60% of the new fiber optic network permitted during the quarter. | 32 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. | 15 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be received during February with installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 41 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. We anticipate executing IRUs for 60 of the leased miles planned. | 20 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be received during February with deployment/installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 21 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. Network testing will take place on a majority of the completed new fiber miles. | 2012-02-20 05:56 | 2012-02-20 05:56 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2012 | Q1 | Q1 - 2012 | 6152 | 5678 | FALSE | 56 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 60% of conduit completed and 40% of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 0 | N/A | N/A | 100 | no variance | 55 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 80 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 83 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 32 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 24 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 41 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 2012-05-17 11:36 | 2012-05-17 11:36 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2012 | Q2 | Q2 - 2012 | 6928 | 6091 | FALSE | 71 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. The wireless vendor will complete 5 links and begin construction for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 60 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 95% during the next quarter. | 100 | no variance | 100 | no variance | 79 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. | 42 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 71 | no variance | 50 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 51 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. The wireless vendor will complete 5 links and begin construction for another 7 links. | 2012-08-08 15:04 | 2012-08-21 07:35 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2012 | Q3 | Q3 - 2012 | 7830 | 6618 | FALSE | 73 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 95% permitted. We anticipate having more than 90% of conduit completed and 85% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 74 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 95% during the next quarter. | 100 | no variance | 100 | no variance | 94 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 90% of conduit in existing approved routes completed and 85% of fiber blown by the end of the next quarter. | 51 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 78 | no variance | 43 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 35 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 90% of conduit in existing approved routes completed and 85% of fiber blown by the end of the next quarter. The wireless vendor will complete 3 links, the remaining are on hold pending route modifications. | 2012-11-13 06:22 | 2012-11-13 06:22 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2012 | Q4 | Q4 - 2012 | 9156 | 7982 | FALSE | 83 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 95 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown by the end of the next quarter. | 100 | no variance | 90 | no variance | 56 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 68 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 2013-03-29 14:31 | 2013-03-29 14:31 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2013 | Q1 | Q1 - 2013 | 9634 | 8349 | FALSE | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 100% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment will be lit during the next quarter. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 92 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 95% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 95% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 2013-05-08 16:44 | 2013-05-08 16:44 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2013 | Q2 | Q2 - 2013 | 10494 | 8898 | FALSE | 89 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 100 | no variance | 2013-08-06 14:15 | 2013-08-06 14:15 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2013 | Q3 | Q3 - 2013 | 11386 | 9501 | FALSE | 100 | no variance | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 2013-11-26 10:00 | 2013-11-26 10:00 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570144 | 2013 | Q4 | Q4 - 2013 | 12176 | 10359 | FALSE | 100 | N/A | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-05-07 16:46 | 2014-05-07 16:46 | 6512 | 6512 | Northern Illinois University, Inc.
NT10BIX5570145 | 2010 | Q4 | Q4 - 2010 | 1014 | 2059 | FALSE | 30 | If we can get the EA SAC completed the project will be on schedule. | 95 | Grant Prep-Other | N/A | 100 | The EA SAC should be complete. | 90 | Mostly done, just leaving room for unanticipated changes. | 100 | These will be given from the Tribe to the Tribe. | 100 | Permits and Applications will be issued by the Tribe. | 30 | Begin to trench first leg of project. | 30 | We will begin to purchase most of leg one equipment. | 30 | Network build will coincide closely with over project completion. | 30 | All equipment purchased will be deployed. | 30 | Testing will be done before fiber is laid and then again at end of project. | 2011-02-09 10:28 | 2011-02-09 10:28 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2011 | Q1 | Q1 - 2011 | 2354 | 2922 | FALSE | 41 | We believe the project will get back on track. |  |  |  | 100 | The EA SAC is complete. | 90 | Mostly done, just leaving room for unanticipated changes. | 100 | These will be given from the Tribe to the Tribe. | 100 | Permits and Applications will be issued by the Tribe. | 30 | Begin to trench first leg of project. | 30 | We will begin to purchase most of leg one equipment. | 30 | Network build will coincide closely with over project completion. | 30 | All equipment purchased will be deployed. | 30 | Testing will be done before fiber is laid and then again at end of project. | 2011-05-26 14:55 | 2011-05-26 14:55 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2011 | Q2 | Q2 - 2011 | 3108 | 3311 | FALSE | 67 | This will show significant change from last quarter. | 100 |  | The funds in this category will be expended. | 100 | Complete | 90 | Mostly complete | 100 | Complete | 100 | Complete | 30 | We don't see any reason that this can't be accomplished. | 30 | We should meet or exceed this goal during this quarter | 30 | Construction should be well on its way. | 30 | We believe we can accomplish this goal. | 30 | Pretesting will be complete and possibly some of the main loop power meter. | 2011-08-16 10:17 | 2011-08-16 10:17 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2011 | Q3 | Q3 - 2011 | 3892 | 3784 | FALSE | 44 | We are reducing are projections to 44% because we think it more accurately reflect were we will be by the end of next quarter. | 100 | N/A | The funds in this category will be expended | 100 | Complete | 90 | Mostly Complete | 100 | Complete | 100 | Complete | 30 | Weather permitting we will meet this projection | 65 | We have purchased a good portion of our equipment and will configure it and install it so that we can light up the fiber when it is ready. | 30 | Construction will be started, and we hope to get a section of fiber done before we can not dig due to weather. We do not anticipate that we will get it all in, but are hoping on completing the majority of the main fiber run. | 30 | Equipment will configured and deployed and this goal should easily be met. | 30 | Pretesting will be complete and possibly some of the main loop power meter and OCR testing will be completed. | 2011-11-03 21:23 | 2011-11-28 12:38 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2011 | Q4 | Q4 - 2011 | 5018 | 4689 | FALSE | 54 | We don't expect there to be a lot of change in this next quarter, however, we will be ramping up for a big 2nd quarter 2012. | 100 | Misc. | This category should be completed. | 100 | Complete | 90 | Mostly Complete | 100 | Complete | 100 | Complete | 15 | Weather Permitting we will meet this projection | 90 | We will purchase a good portion of the remainder of the needed equipment. | 50 | We believe we should be well on our way to being 50% complete by this quarters end. | 90 | We will be spending a significant portion of our time this quarter on equipment deployment, as it can be done in-doors and is not contingent on weather conditions. | 50 | We will be testing all the runs and equipment as deployed and thus should be about 50% or greater on the testing phase. | 2012-02-14 21:49 | 2012-02-14 21:49 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2012 | Q1 | Q1 - 2012 | 6324 | 5764 | FALSE | 79 | We should complete 3 of the 4 fiber legs on the main fiber loop. We also should be able to connect 9 new CAI during this next quarter. | 100 | n/a | Complete | 100 | Complete | 95 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 76 | We should be well on our way to being over 50 percent done with the main fiber loop, and we will begin construction on some of the lateral connections. | 98 | We will purchase a good portion of the remainder of the needed equipment. | 65 | We believe we should be well on our way to being 65% complete by this quarters end. | 95 | We will continue to spend a significant portion of our time this quarter on equipment deployment, as it can be done in-doors and is not contingent on weather conditions. | 65 | We will be testing all the runs and equipment as deployed and thus should be about 65% or greater on the testing phase. | 2012-05-29 13:58 | 2012-05-29 13:58 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2012 | Q2 | Q2 - 2012 | 6932 | 6093 | FALSE | 83 | We should complete 3 of the 4 fiber legs on the main fiber loop. We also should be able to connect new CAI's during this next quarter. | 100 |  | Complete | 100 | Complete | 95 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 78 | We should be well on our way to being over 60 percent done with the main fiber loop, and we will begin construction on some of the lateral connections. | 100 | Complete | 65 | We believe we should be well on our way to being 65% complete by this quarters end. | 100 | Complete | 65 | We will be testing all the runs and equipment as deployed and thus should be about 65% or greater on the testing phase. | 2012-08-08 15:40 | 2012-08-08 15:40 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2012 | Q3 | Q3 - 2012 | 8090 | 6751 | FALSE | 95 | We will be connecting most of the CAI in this next quarter. | 100 | n/a | Complete | 100 | Complete | 98 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 90 | With the main loop completed and the laterals mostly complete we will be working on connections of main to lateral and laterals to CAI's | 100 | Complete | 80 | We believe we should be well on our way to being 95 complete by this quarters end. We will be terminating at our CAI's this next qrt and completing portions of the network. | 100 | Complete | 85 | Due to weather concerns we chose to deploy the construction elements and forgo the testing so that we could complete that phase. Testing will be implemented during this quarter. | 2012-11-27 19:25 | 2012-11-27 19:25 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2012 | Q4 | Q4 - 2012 | 8786 | 7585 | FALSE | 100 | We should be complete by the end of next quarter. | 100 |  | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We have a few buildings that we were not able to get to last fall. We will have to connect them in the spring, as winter does not allow digging. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 2013-02-14 18:19 | 2013-02-14 18:19 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2013 | Q1 | Q1 - 2013 | 9816 | 8444 | FALSE | 100 | We should be complete by the end of next quarter. | 100 | N/A | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 2013-05-20 10:41 | 2013-05-20 10:41 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2013 | Q2 | Q2 - 2013 | 10084 | 8602 | FALSE | 100 | We will be complete by the end of grant period. | 100 | N/A | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 2013-07-02 12:40 | 2013-07-02 12:40 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570145 | 2013 | Q3 | Q3 - 2013 | 10860 | 9114 | FALSE | 100 | Completed | 100 | N/A | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-09-28 17:47 | 2013-09-28 17:47 | 6429 | 6429 | Ute Indian Tribe
NT10BIX5570146 | 2010 | Q4 | Q4 - 2010 | 1226 | 2255 | FALSE | 12 | No Variance | 27 | Admin | No Variance | 100 | No Variance | 25 | Slight increase due to start of construction phase 1 | 0 | No Variance | 0 | No Variance | 0 | No Variance | 26 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-18 15:49 | 2011-02-18 15:49 | 6425 | 6425 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2011 | Q1 | Q1 - 2011 | 1724 | 2590 | FALSE | 18 | Slight variance below budget 1% due to anticipated fiber procurement delay. | 37 | Admin. | No variance. | 100 | EA delayed but expected to be final in Y1 Q4. | 30 | No variance. | 41 | No variance. | 16 | No variance. | 84 | No variance. | 31 | Slight variance below budget due to anticipated fiber procurement delay. | 4 | No variance. | 10 | No variance. | 0 | Original Category items "test equipment" moved to Procurement and "testing fiber" moved to Network Build. | 2011-04-29 17:07 | 2011-04-29 17:07 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2011 | Q2 | Q2 - 2011 | 2960 | 3237 | FALSE | 32 | Some expenses moved from 2012 to 3rd Qtr 2011 due to expectation that portions of project will occur more quickly than anticipated. | 50 | Admin | Legal expenses are expected to be underbudget, thus a Portion of legal expenses moved to Site Preparation. | 100 | No variance. | 40 | No variance. | 77 | Cable easements are expected to be underbudget, thus a portion of cable easement expense moved to Site Preparation. | 32 | No variance. | 60 | Shelters will be arriving, but will not be invoiced in 3rd Qtr, some budgeted expenses were moved from other categories. | 55 | Cost of DWDM equipment less than budgeted. | 10 | Portion of Carrier Construction labor moved from 2012 to 3rd Qtr 2011 | 30 | No variance. | 0 | N/A | 2011-08-08 15:48 | 2011-08-08 15:48 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2011 | Q3 | Q3 - 2011 | 4256 | 3978 | FALSE | 55 | Fiber delay has caused a slight delay in the Overall Project's progress compared to the baseline projections. However, with the contribution of in-kind fiber and the progress of construction, Sho-Me anticipates catching up to near baseline projections in 4th Qtr 2011. | 58 | Legal, Administrative, Pre-Award Expenses | Above Baseline 2%, however, Legal expenses are expected to be under budget, thus a portion of Legal expenses budgeted were moved to Site Preparation. | 100 | No variance. | 60 | Above Baseline 10% because more time actually devoted prior to construction than will be needed later in project, though Network Design was budgeted evenly throughout project. | 77 | Below Baseline by 6% since cable easements are expected to be under budget, thus a portion of cable easement expense moved to Site Preparation. | 48 | No variance. | 91 | Below Baseline by 9%, however, extended budgeted costs into 2012 to account for work that will be performed throughout the construction process. | 63 | Below Baseline by 5% as cost of DWDM equipment less than budgeted. | 46 | No variance. | 82 | Above Baseline 35% due to the Increased cost of innerduct. The purchase of innerduct is near completion. The increased cost is not anticipated to affect the category budget by more than 10%. | 0 | Below Baseline by 46% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2011-11-23 13:39 | 2011-11-23 13:39 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2011 | Q4 | Q4 - 2011 | 5104 | 4773 | FALSE | 67 | 1% below Baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. However, Sho-Me is catching up to Baseline quickly and anticipates being at the Baseline Projections by the end of 4th Qtr 2012. | 52 | Legal, Administrative, Pre-Award Expenses | 13% below Baseline Due to legal and administrative costs being lower than anticipated. | 88 | 12% below Baseline due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 73 | 13% above Baseline due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | 53% below Baseline due to lower than anticipated rights of way costs | 87 | 23% above Baseline due to Warsaw River Crossing Agreement with MODOT. | 100 | No Variance. | 64 | 11% below Baseline due to lower than anticipated costs relating to DWDM equipment. | 66 | 5% above Budget due to contribution of in-kind fiber. | 100 | 36% above Baseline due to increased costs of innerduct and because Sho-Me chose to buy most of the innerduct up front rather than spreading it throughout the project. | 0 | Below Baseline by 61% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2012-02-17 15:04 | 2012-02-17 15:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2012 | Q1 | Q1 - 2012 | 5928 | 5563 | FALSE | 69 | 6% below baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. However, Sho-Me is catching up to Baseline quickly and anticipates being at the Baseline Projections by the end of 4th Qtr 2012. | 69 | Legal, Administrative, Pre-Award Expenses | 5% below baseline due to legal and administrative costs being lower than anticipated. | 90 | 10% below baseline due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. Sho-Me anticipates catching up to baseline by the end of 2012. | 80 | 10% above baseline due to more engineering and design work being performed at the onset of the project than anticipated. | 75 | 25% below baseline due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 80 | No variance. | 100 | No variance. | 59 | 24% below baseline due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates catching up to baseline by the end of 2012. | 72 | 4% above baseline due to contribution of in-kind fiber. | 100 | 28% above baseline due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 61% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-05-04 11:19 | 2012-05-04 11:19 | 6426 | 6426 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2012 | Q2 | Q2 - 2012 | 6554 | 5891 | FALSE | 76 | Below Baseline by 9% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by the end of 2012. | 67 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 16% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 96 | Below Baseline by 4% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 89 | Above Baseline by 9% due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 96 | Below Baseline by 4% due to costs being lower than anticipated. Sho-Me does anticipate catching up to baseline by the end of 2012 as construction continues. | 100 | No variance. | 74 | Below Baseline by 21% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 76 | Below Baseline by 2% due to the delay in fiber optic cable. However, Sho-Me anticipates it will meet baseline projections by the end of 2012. | 100 | Above Baseline by 17% due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 78% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-07-27 18:15 | 2012-07-27 18:15 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2012 | Q3 | Q3 - 2012 | 7908 | 6658 | FALSE | 87 | Below Baseline by 5% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 1st Quarter 2013. | 73 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 19% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 90 | Below Baseline by 10% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 88 | Below Baseline by 2% due to more engineering and design work being performed at the onset of the project, the costs attributable to Network Design are expected to decrease. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 79 | Below Baseline by 21% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 80 | Below Baseline by 20% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Above Baseline by 13% due to construction costs being greater than anticipated. | 100 | Above Baseline by 8% due to increased cost of innerduct. | 0 | Below Baseline by 84% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-11-15 17:23 | 2012-11-15 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2012 | Q4 | Q4 - 2012 | 8712 | 7516 | FALSE | 97 | Below Baseline by 2% due to unforeseen fiber availability constraints from manufacturers in 2011, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 2nd Quarter 2013. | 81 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 19% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 91 | Below Baseline by 9% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 92 | Below Baseline by 8% due to fewer engineering hours needed than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho- Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 87 | Below Baseline by 13% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 100 | Above Baseline by 3% due to construction costs being greater than anticipated. | 100 | Above Baseline by 3% due to increased cost of innerduct. | 0 | Below Baseline by 97% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-02-11 17:04 | 2013-02-11 17:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2013 | Q1 | Q1 - 2013 | 9210 | 8040 | FALSE | 100 | No variance. | 78 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 22% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Below Baseline by 3% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 94 | Below baseline by 6% due to less engineering hours being needed than expected. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 91 | Below Baseline by 9% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 100 | No variance. | 100 | No variance. | 0 | Below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-04-22 13:14 | 2013-04-22 13:14 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2013 | Q2 | Q2 - 2013 | 10252 | 8728 | FALSE | 100 | No variance. | 87 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 13% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 97 | Below Baseline by 3% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 94 | Below Baseline by 6% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 38 | Below Baseline by 62% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 100 | No variance. | 96 | Below Baseline by 4% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 100 | No variance. | 100 | No variance. | 0 | Below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-07-29 17:23 | 2013-07-29 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | 2013 | Q3 | Q3 - 2013 | 11626 | 9747 | FALSE | 100 | No variance. | 100 | Legal, Administrative,Pre-Award Expenses | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2014-01-17 16:22 | 2014-01-17 16:22 | 7114 | 7114 | SHO-ME Technologies, L.L.C.
NT10BIX5570148 | 2010 | Q4 | Q4 - 2010 | 1210 | 2243 | FALSE | 5 | We projected 30% percent this quarter, based largely on the expenditure for equipment, which was held up with getting the Montana West bank account authorized for drawdown...(which has now happened) We will catch up next quarter, now that we can buy necessary materials and equipment. | 16 | Admin and Match | No Variance | 100 | No Variance..we expect the EA to be done early next quarter. | 0 | No Variance | 37 | We projected to have 54% of the rights of way done by this time. We are encountering complexities related to State Department of Transportation rights of way and easements on the Reservations, which is slowing this process down. We are focusing on the rights of way for the first construction segments so that we can get started on schedule for those parts of the project, and continue on the rest of the rights of way while we are putting installation crews to work. | 10 | We projected to be 16% completed on this by this time...permitting will be slowed down by delays in getting rights of way on the Reservations. | 0 | No Variance | 0 | We projected 94% in the baseline for this quarter, and did not issue RFP's for the equipment until we were assured we have drawdown status for Montana West...we now have that status, and are issuing RFP's for fiber and construction equipment. We will expend these funds in next quarter. | 5 | No Variance | 0 | Projection for this quarter was 12%...this is for the actual build, which was scheduled to start in March. We do not expect to start until next quarter (April) due to delays in the EA and equipment procurement. We will catch up at that time. | 0 | We projected a 12% completion on network testing, however construction startup is being delayed by problems encountered with obtaining rights of way on the Reservations. | 2011-02-17 18:48 | 2011-02-17 18:48 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2011 | Q1 | Q1 - 2011 | 2060 | 2775 | FALSE | 13 | We projected to have 48 percent of the project done based on expenditures by this time. The time to accomplish the EA process has delayed our start date. We now expect to have the EA completed by 11Q2 and to start at the end of 11Q2. | 24 | Admin/Match | No Variance from baseline. | 100 | We expect to have the EA done in 11Q2. | 100 | No Variance from baseline. | 40 | We are working with State and local authorities for rights of way on those portions of State and County roadway rights of way that are not on reservations. We still have challenges obtaining rights of way on the reservations, particularly on the Blackfeet. Planned construction effort is shifting from the Blackfeet reservation to the Flathead reservation in order to focus on areas where we can obtain timely rights of way, while still working with the BIA and the Blackfeet Tribal council. | 20 | We are getting some verbal approvals on county roads, prior to permitting, based on obtaining the FONSI. This will get us a head start on the actual permitting process. | 0 | Projected 52% by this time....This is for preparation for the wireless delivery part of our project, which has been rescheduled later as a result of the overall EA delay. | 95 | No Variance from baseline. | 10 | Projected 37% by this time. We expect to start in June after the FONSI is obtained. | 10 | Projected 26% by this time. We expect to start at the end of 11Q2 after the FONSI is obtained. | 0 | Projected 26% by this time. We expect to start at the end of 11Q2 after the FONSI is obtained. | 2011-05-16 17:46 | 2011-05-16 17:46 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2011 | Q2 | Q2 - 2011 | 3094 | 3304 | FALSE | 54 | Projected 56% | 76 | Admin & Match | Projected 32%--Recording 100% of In Kind Match | 100 | Projected 100%--Fonsi awarded 7/5/11 | 57 | Projected 100%--We plan to purchase the Juniper equipment first and hold off on the Cisco and Occam equipment for a few months. | 60 | Projected 100%--Negotiating with the Blackfeet Tribe | 32 | Projected 32%--No Variance | 0 | Projected 64%--delayed by the EA | 54 | Projected 96%--We are holding off on additional equipment for the Blackfeet route until the Right of Way issues are closer to resolution. | 37 | Projected 45%--We lost a full quarter of construction due to the delay with the EA. | 26 | Projected 41%--We lost a full quarter of construction due to the delay with the EA. | 26 | Projected 41%--We lost a full quarter of construction due to the delay with the EA. | 2011-08-15 17:03 | 2011-08-15 17:03 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2011 | Q3 | Q3 - 2011 | 3918 | 3797 | FALSE | 56 | Projected 63% Put 100% of in Kind Match into the project last quarter. | 78 | Admin & Match | Projected 40%--Put 100% of in Kind Match in project last quarter | 100 | Projected 100% | 85 | Projected 100%--Delays obtaining upstream contracts impacting this item | 55 | Projected 100%-negotiating with the Blackfeet | 25 | Projected 40%--MDOT delays on permitting | 0 | Projected 64%--Overall schedule delays associated with the EA | 54 | Projected 96%--Holding off on some of the equipment until we can start on the Blackfeet Reservation | 46 | Projected 53%--hired a subcontractor to start work on the section from Missoula to Evaro to get us more on schedule. | 32 | Projected 53%--We started late, but are catching up. | 10 | Projected 53%--Lost a full quarter of construction due to the delay with the EA. | 2011-11-07 18:22 | 2011-11-07 18:22 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2011 | Q4 | Q4 - 2011 | 5130 | 4795 | FALSE | 62 | Projected 69%. Late start due to EA. We are in catch-up mode. | 50 | Admin & Legal | Projected 48%-- Audit Expense and Insurance due this quarter | 90 | Projected 100%--Cultural walkthrough taking place on a segmented basis, to allow us to start in parallel with the rest of the walkthrough. We will receive final approval from the Blackfeet Nation when completed. | 100 | Projected 100%--We will purchase all of the Network Hardware | 44 | Projected 100% Still working with the Blackfeet Tribe on Rights of Ways | 80 | Projected 48%--Most of the permits have been obtained. The rest of the project is on State Highway Right of Ways that don't charge for permits. We still need permits on some BIA roadways on the Blackfeet Reservation. | 28 | Projected 64%--The Arlee Building will be completed this quarter and we will start on the other sites in the spring. | 70 | Projected 96%--Will order Wireless Equipment and Radios in the spring. | 39 | Projected 61%--We will purchase the IRU this quarter, once we obtain BTOP approval for our budget realignment. | 62 | Projected 65%. Fiber availability is impacting this parameter. | 0 | Projected 65%--Projected Milestone changed with budget modification. We will perform our own network testing instead of outsourcing this function. None of the wireless equipment has been installed yet and is not ready for testing. | 2012-02-17 18:59 | 2012-02-17 18:59 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2012 | Q1 | Q1 - 2012 | 6100 | 5652 | FALSE | 73 | Projected 82% Construction is going as planned and fiber is here. The Kalispell to Polson section is behind what we had anticipated but will be back on schedule by the end of August. | 52 | Admin and Legal | Projected 58% | 100 | Projected 100% All cultural walk outs will have been completed | 100 | Projected 100% All Electronic Hardware will be purchased | 58 | Projected 58% Engineering will continue as anticipated | 100 | Projected 60% Most of the permits have been obtained | 76 | Projected 76% The main sites will have been completed. Working on tower sites. | 77 | Projected 96% Most of the large equipment needed for the project has been purchased | 54 | Projected 55% Proceeding as anticipated | 77 | Projected 88% We are holding off on the Last Mile deployment for the moment and concentrating on the middle mile | 0 | Projected 22% We are holding off on the Last Mile deployment for the moment and concentrating on the middle mile. | 2012-05-15 14:05 | 2012-05-15 14:05 | 6343 | 6343 | Ronan Telephone Co.
NT10BIX5570148 | 2012 | Q2 | Q2 - 2012 | 7032 | 6143 | FALSE | 79 | Projected 87%..DOT Permitting delays on the Blackfeet Reservation has impacted out schedule. | 60 | Admin & Legal | Projected 66%...delays commensurate with overall project delays. | 100 | Projected 100%...no variance | 100 | Projected 100%...no variance | 80 | Projected 70%...BIA approvals have accelerated the progress for State highways on the reservation. | 100 | Projected 70%...permits are all applied for and waiting approval | 32 | Projected 88%...overall project delays have impacted site preparation | 81 | Projected 98%...some equipment may still be needed on the Blackfeet build | 59 | Projected 68%...Delays on the Blackfeet have contributed to this variance. | 84 | Projected 91% Delayed by permitting issues. | 0 | Projected 38%...final network testing will commence upon completion of the northern route. | 2012-08-10 18:28 | 2012-08-10 18:28 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2012 | Q3 | Q3 - 2012 | 8042 | 6727 | FALSE | 80 | Projected 87%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 72 |  | Projected 72%. No Variance | 95 | Projected 100%. No Variance | 95 | Projected 100%. No Variance | 90 | Projected 100%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 100 | Projected 72%. All construction permits have been obtained | 40 | Projected 88%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 90 | Projected 99%. Some wireless equipment will need to be procured for the remainder of the build on the Blackfeet and other locations. | 65 | Projected 85%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 90 | Projected 90%. No Variance | 50 | Projected 90%. Network testing will have been done on the southern portion of the network. Shortfall due to Blackfeet work stoppages. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2012 | Q4 | Q4 - 2012 | 8992 | 7770 | FALSE | 87 | Projected 92%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 76 | Admin & Legal | Projected 80%--As anticipated. Legal fees are high concerning the Glacier county portion of the build. | 95 | Projected 100%--Some EA work still to be completed in Glacier County | 100 | Projected100% | 92 | Projected 100%--Work still to be completed in Glacier County. | 100 | Projected 80% | 67 | Projected 88%--Engineering work on the wireless portion of the project will continue this quarter. | 87 | Projected 99%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 63 | Projected 93%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 93 | Projected 94%--As anticipated | 44 | Projected 94%--Testing work scheduled to start on the southern portion of the project. | 2013-02-26 17:35 | 2013-02-26 17:35 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2013 | Q1 | Q1 - 2013 | 9736 | 8402 | FALSE | 89 | Projected 97%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 78 | Admin & Legal | Projected 93% Holding In Kind Labor Match to Fund With Program Income Match | 99 | Projected 100%. EA work still unfinished for the CAI's. | 100 | Projected 100% | 93 | Projected 100%. ROW impacted by the Blackfeet work stoppage. | 100 | Projected 100% | 66 | Projected 100% 3.65 Sites will need site preparation and have been slipped to to overall construction slippage. | 95 | Projected 100% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 69 | Projected 89% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 94 | Projected 99% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 100 | Projected 100% | 2013-05-15 13:58 | 2013-05-15 13:58 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2013 | Q2 | Q2 - 2013 | 10668 | 8995 | FALSE | 91 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 81 | Admin & Legal | Projected 100%. Holding in Kind Labor Match to Fund with Program Income Match. | 99 | Projected 100%..Still working on EA review for the new builds for the CAI's. | 100 | Projected 100% | 96 | Projected 100%. ROW impacted by the Blackfeet work stoppage. | 100 | Projected 100% | 33 | Projected 100%. Most site prep is for the final wireless sites and they are at the end of the project which has slipped due to work stoppage on the Blackfeet | 100 | Projected 100% | 64 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 97 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 100 | Projected 100% | 2013-08-20 19:03 | 2013-08-20 19:03 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2013 | Q3 | Q3 - 2013 | 11306 | 9452 | FALSE | 92 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles. | 88 | Admin & Legal | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. We are waiting on EA approval on our CAI builds and project modification regarding route changes. | 100 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles, for which we will need to obtain rights of way. (14% of the miles of the project) | 100 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. The only site prep left is the wireless sites. We have installed two (Arlee and Elmo/Big Arm) of the five wireless sites with three left. (Evaro, Heart Butte and St. Mary) | 100 | Projected 100% | 63 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles. | 97 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles, which when done, will need network testing. (14% of the miles of the network) | 2013-11-20 12:02 | 2013-11-20 12:02 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2013 | Q4 | Q4 - 2013 | 11934 | 10102 | FALSE | 95 | Projected 100. All that remains is to complete the builds on the Blackfeet and build to the CAI's. We are on track to complete within the one-year extension. | 94 | Admin and Legal | Projected 100. We still have some costs in this activity, due to the one year extension we were granted and work that remains on the Blackfeet. | 100 | Projected 100 | 100 | Projected 100 | 100 | Projected 100 | 100 | Projected 100 | 50 | Projected 100. Actual is 38%--this is Wireless Site Prep. Overall project slippage has impacted this schedule. Site prep will be required for the remaining wireless sites...Evaro, Heart Butte, and St. Mary/Babb. | 100 | Projected 100 | 94 | Projected 100. Project slippage due to rights of way and work stoppage by the Blackfeet. All that remains is microwave to Heart Butte and a 43 mile fiber build on the Blackfeet | 99 | Projected 100 | 100 | Projected 100 | 2014-03-06 18:47 | 2014-03-06 18:47 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2014 | Q1 | Q1 - 2014 | 12218 | 10390 | FALSE | 100 | 100% of the original budgeted funds have been spent. The joint build between HIEM and RTC generated additional costs and produced additional program income. The program income was added to the project leaving over $1.5 million in federal funds available to complete the remainder of the project on the Blackfeet Reservation. | 90 | Admin and Legal | The remainder of the Admin & Legal Expenses will be incurred during close out. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | There will still be some Wireless site work to complete in July and August | 100 | Complete | 100 | 100% of the original budgeted funds have been spent. The joint build between HIEM and RTC generated additional costs and produced additional program income. The program income was added to the project leaving over $1.5 million in federal funds available to complete the remainder of the project on the Blackfeet Reservation. | 100 | 100% of the original budgeted funds have been spent. The joint build between HIEM and RTC generated additional costs and produced additional program income. The program income was added to the project leaving over $1.5 million in federal funds available to complete the remainder of the project on the Blackfeet Reservation. | 100 | 100% of the original budgeted funds have been spent. The joint build between HIEM and RTC generated additional costs and produced additional program income. The program income was added to the project leaving over $1.5 million in federal funds available to complete the remainder of the project on the Blackfeet Reservation. | 2014-05-20 15:52 | 2014-05-20 15:52 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2014 | Q2 | Q2 - 2014 | 12438 | 10627 | FALSE | 100 | 100% of the original budgeted funds have been spent. The joint build between HIEM and RTC generated additional costs and produced additional program income. This program income and more has been added to the project leaving $75,000 in federal funds available to complete the close out. | 92 | Admin & Legal | Final Audit and other Closing Costs will remain | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-08-19 14:12 | 2014-08-19 14:12 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2014 | Q3 | Q3 - 2014 | 12602 | 10870 | FALSE | 100 | Complete | 95 | Admin & Legal | Final Audit and Other Closing Costs will remain | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-11-17 11:04 | 2014-11-17 11:04 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2014 | Q4 | Q4 - 2014 | 12734 | 11061 | FALSE | 99 | We are waiting on weather and landowner consents to finish on the Blackfeet reservation. We have received an extension of the construction period to September 30, 2015. | 99 | Admin & Legal | Final Audit and Other Closing Costs will remain | 100 | Complete | 100 | Complete | 100 | Complete | 100 | 7 landowners remain on the Duck Lake Road route to St. Mary and Babb | 99 | Complete | 100 | Complete | 99 | Fiber to St. Mary and Babb remains to do. | 99 | Fiber to St. Mary and Babb remains to do. | 100 | Fiber to St. Mary and Babb remains to do. | 2015-02-27 12:51 | 2015-02-27 12:51 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2015 | Q1 | Q1 - 2015 | 12848 | 11218 | FALSE | 100 | We are waiting on weather and landowner consents to finish on the Blackfeet reservation. We have received an extension of the construction period to September 30, 2015. | 99 | Admin & Legal | Final Audit and Other Closing Costs remain. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | 3 landowners remain on the Duck Lake Road route to St. Mary and Babb | 100 | Complete | 100 | Complete | 100 | Fiber to St. Mary and Babb remains. | 100 | Fiber to St. Mary and Babb remains. | 100 | Fiber to St. Mary and Babb remains. | 2015-05-26 18:59 | 2015-05-26 18:59 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570148 | 2015 | Q2 | Q2 - 2015 | 12876 | 11256 | FALSE | 100 | Project Completed | 100 | Admin & Legal | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 100 | Project Completed | 42214.8208 | 42214.8208 | 6091 | 6091 | Ronan Telephone Co.
NT10BIX5570150 | 2010 | Q4 | Q4 - 2010 | 554 | 1573 | FALSE | 5 | Zero variance | 50 | Professional Services, Fiber route valadation | Zero variance | 100 | Zero variance | 75 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-01-26 15:35 | 2011-01-26 15:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2011 | Q1 | Q1 - 2011 | 1666 | 2554 | FALSE | 25 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 45 | Professional Services, Fiber Route validation | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 100 | Zero Variance | 100 | Zero Varience | 0 | N/A | 0 | N/A | 0 | N/A | 31 | Equipment procurement will be ahead of schedule due to available match funds and desire to insure adequate equipment is on hand to meet deployment scheduling | 21 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 5 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 5 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project on schedule prior to close of 3Q2011. | 2011-04-29 13:35 | 2011-04-29 13:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2011 | Q2 | Q2 - 2011 | 2920 | 3217 | FALSE | 32 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 45 | Professional Services | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 38 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 30 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 15 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 15 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 2011-08-04 08:03 | 2011-08-04 08:03 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2011 | Q3 | Q3 - 2011 | 3958 | 3817 | FALSE | 41 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 12 | Professional Services, Fiber Route validation | On schedule | 100 | Zero Variance from plan | 100 | Zero Variance from plan | 0 | N/A | 0 | N/A | 0 | N/A | 44 | Later than anticipated start of deployment reduced equipment expenditure requirements | 43 | On Schedule | 30 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 30 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 2011-11-10 12:33 | 2011-11-10 12:33 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2011 | Q4 | Q4 - 2011 | 4662 | 4303 | FALSE | 56 | Later than anticipated start of fiber deployment due to delayed FONSI receipt resulted in overall expenditures being less than projected. Additionally, vendor invoice timing reduced total expenditures for this quarter. | 21 |  | Later than anticipated deployment of equipment delayed expenditures in this category. | 100 | Zero variance | 100 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Ahead of schedule | 54 | On schedule | 45 | Later than anticipated start of deployment reduced the number of total projected POI for this quarter | 45 | Later than anticipated start of deployment reduced the number of total projected POI for this quarter | 2012-01-30 12:56 | 2012-01-30 12:56 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2012 | Q1 | Q1 - 2012 | 6018 | 5608 | FALSE | 68 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 35 |  | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 83 | Ahead of schedule | 63 | Physical build will be slightly ahead of schedule but vendor invoice timing and payments will likely reduced reported expenditures | 65 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 65 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-05-10 14:27 | 2012-05-10 14:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2012 | Q2 | Q2 - 2012 | 6878 | 6065 | FALSE | 77 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 46 |  | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 100 | Zero variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 85 | Ahead of schedule | 76 | Physical build will be slightly ahead of schedule but vendor invoice timing and payments will likely reduced reported expenditures | 76 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 76 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-08-07 08:37 | 2012-08-07 08:37 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2012 | Q3 | Q3 - 2012 | 7906 | 6657 | FALSE | 85 | Zero Variance | 64 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 83 | Zero Variance | 88 | Slightly ahead of schedule | 86 | Slightly ahead of schedule | 86 | Slightly ahead of schedule | 2012-11-15 17:06 | 2012-11-15 17:06 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2012 | Q4 | Q4 - 2012 | 9140 | 7940 | FALSE | 93 | Zero Variance | 64 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 97 | Slightly ahead of schedule | 95 | Slightly ahead of schedule | 93 | Slightly ahead of schedule | 93 | Slightly ahead of schedule | 2013-03-15 10:16 | 2013-03-15 10:16 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2013 | Q1 | Q1 - 2013 | 9328 | 8120 | FALSE | 99 | On schedule | 93 | Professional Services | On schedule | 100 | Zero variance | 100 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 100 | On schedule | 100 | On schedule | 99 | On schedule | 99 | On schedule | 2013-04-28 20:41 | 2013-04-28 20:41 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2013 | Q2 | Q2 - 2013 | 10304 | 8769 | FALSE | 100 | Zero Variance | 100 | Professional Services | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/a | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 2013-07-30 11:27 | 2013-07-30 11:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | 2013 | Q3 | Q3 - 2013 | 11642 | 9767 | FALSE | 100 | Zero variance - grant in close-out | 100 | Professional services | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 100 | Zero variance -grant in close-out | 100 | Zero variance - grant in close-out | 2014-01-23 07:32 | 2014-01-23 07:32 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570153 | 2010 | Q4 | Q4 - 2010 | 734 | 1766 | FALSE | 17 | Detail Below | 50 |  | Reimbursement for Eligible Pre-Award Expenses | 0 | N/A | 61 | Hire Field Project Engineer, Field Project Manager, Traffic Systems Management Contractor. Complete Node and Community Anchor Institution Design | 0 | N/A | 0 | N/A | 3 | Begin Site Prep for 4 Massachusetts Nodes | 32 | Receive 10G Network Upgrade Equipment, Issue RFP for Optical Equipment | 42 | Hire Project Manager, Execute IRU with Fiber Vendors; Provide First Payment, Begin Contract Negotiations with Community Anchor Institutions | 25 | Configure and Install 10G Network Upgrade Equipment | 0 | N/A | 2011-01-28 13:17 | 2011-01-28 13:17 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2011 | Q1 | Q1 - 2011 | 2288 | 2889 | FALSE | 25 | See Below. | 21 |  | Limited activity anticipated | 0 | N/A | 77 | Network Design efforts will continue for the additional Community Anchor Institutions. No significant impact on the project time line is anticipated. | 0 | N/A | 0 | N/A | 4 | Site Preparation efforts will continue. However, few associated expenses are anticipated in the next quarter. | 6 | Optical Equipment will be ordered during this quarter, but no payments are scheduled. Payment will be made in 2011 Q3 | 33 | Because of the 20% advance payment and 40% Providence County, RI segment payment, no significant network build expenditure is expected. However, both backbone fiber and CAI lateral installation and will commence in Providence County, RI. 45 backbone miles and 5 CAI sites are projected for completion. | 5 | Optical equipment will be ordered, but no significant deployment is scheduled. | 0 | No Activity. | 2011-05-24 17:41 | 2011-05-24 17:41 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2011 | Q2 | Q2 - 2011 | 3282 | 3403 | FALSE | 31 | See below. | 46 |  | The OMB Circular A-133 audit will occur during this quarter. Community Outreach efforts will continue. | 0 | N/A | 100 | Networkdesign efforts are scheduled for completion. | 0 | N/A | 0 | N/A | 15 | Site preparation for optical node sites is expected to be complete by September 30, 2011. | 51 | OSHEAN will place the order for the Optical Equipment required for Beacon 2.0. Phase I order will include the Optical Node Equipment; Phase II order will include the CAI equipment. | 32 | Because of the IRU payment structure, few payments are scheduled. However, Cox Communications is expected to deploy 100 miles of backbone fiber and commence CAI lateral installations. These efforts remain in line with the overall project plan. | 5 | Deployment of Optical equipment is not expected during this quarter. | 0 | Network testing is not expected during this quarter. | 2011-08-23 16:38 | 2011-08-23 16:38 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2011 | Q3 | Q3 - 2011 | 4232 | 3964 | FALSE | 51 | See Below | 52 |  | No major change from baseline | 0 | N/A | 100 | Network design efforts are scheduled for completion, except for CAI change orders. | 0 | N/A | 0 | N/A | 15 | Site Prep efforts will be complete; total funds expended will be below baseline budget. | 94 | OSHEAN will continue to receive and verify Phase I DWDM optical equipment, and place order for Phase II CPT 50 optical equipment. | 55 | Because of the IRU payment structure, few payments are scheduled. However, Cox Communications is expected to have deployed approximately 200 total miles of backbone fiber and commence CAI lateral installations. These efforts remain in line with the overall project plan. | 100 | Actual % = 179% Because of an alternate valuation of equipment deployment, over 100% of the baseline projected funds will have been expended. However, actual deployment efforts are only approximated at 15% completion. | 14 | Testing of the Providence County IRU fiber is scheduled. | 2011-11-22 16:21 | 2011-11-22 16:21 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2011 | Q4 | Q4 - 2011 | 4948 | 4627 | FALSE | 60 | See Below. | 56 |  | No major change from baseline. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. The only foreseen need for further network design efforts result from any required Change Orders for Community Anchor Institution laterals. | 0 | N/A | 0 | N/A | 15 | All Site Prep requirements are expected to be completed. Preparation efforts are projected to be under budget overall. | 100 | All optical equipment is expected to be ordered and delivered during this quarter. | 59 | Kent County, RI fiber totalling 72 miles is expected to be tested and accepted by OSHEAN. Cox is scheduled to begin the 78 mile build in Washington County, RI. Sidera is scheduled to begin pulling fiber in Bristol and Plymouth Counties, MA. OSHEAN expects 15 Community Anchor Institution laterals to be installed during this quarter. | 100 | Cisco 15454 optical equipment will be installed at the optical node locations. | 25 | The Kent County, RI backbone fiber will be tested. | 2012-02-10 14:39 | 2012-02-10 14:39 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2012 | Q1 | Q1 - 2012 | 6252 | 5728 | FALSE | 67 | Total percent complete is in line with the 68% projected in the baseline. | 60 |  | No major change from baseline | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. | 0 | N/A | 0 | N/A | 100 | All site prep efforts are scheduled for completion | 100 | All equipment is expected to be ordered. | 71 | No major change from baseline | 100 | Cisco 15454 node equipment is scheduled for deployment; OSHEAN will begin the deployment of CAI CPT 50 equipment. | 31 | No major change from baseline | 2012-05-22 15:28 | 2012-05-22 15:28 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2012 | Q2 | Q2 - 2012 | 7142 | 6198 | FALSE | 72 | Per the baseline, the project is behind the 83% projection due to a modification request pending. This variance will have minimal impact on the overall project time line | 73 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. | 0 | N/A | 0 | N/A | 100 | All site preparation efforts are scheduled for completion | 100 | All equipment is expected to be ordered | 87 | Per the baseline, the project is ahead of 81% projection due to ahead of schedule installation efforts | 100 | Installation of CAI optical equipment shall continue | 27 | Network Testing efforts are expected to be under budget. | 2012-08-20 07:50 | 2012-08-20 07:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2012 | Q3 | Q3 - 2012 | 8028 | 6720 | FALSE | 86 | Per the baseline, the project is behind the 97% projection due to a modification request pending. This variance will have minimal impact on the overall project time line. | 79 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 45 | Site Preparation efforts are under budget, but projected to be complete by 12/31/12. | 100 | All equipment is expected to be ordered | 76 | Network build expenses are under budget, but the work performed is consistent with the 94% completion indicated in the baseline. | 100 | Equipment deployment efforts are greater than budget, and shall continue for the installation of CAI optical equipment | 43 | Network testing efforts are projected to be under budget. | 2012-11-26 09:50 | 2012-11-26 09:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2012 | Q4 | Q4 - 2012 | 9040 | 7809 | FALSE | 92 | Baseline = 99% complete. Variance due to slight project delay from a pending route modification request. The route modification was approved in December, 2012. This variance will have minimal impact on the overall project time line. | 75 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 41 | Site Preparation efforts are under budget, but projected to be complete by January, 2013. | 100 | All equipment is expected to be ordered | 98 | Projected completion is only 1% below the baseline. This variance will have little impact on the overall project. | 100 | Equipment deployment efforts are greater than budget, and shall continue for the installation of CAI optical equipment | 50 | Network testing efforts are projected to be under budget. | 2013-02-27 16:53 | 2013-02-27 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2013 | Q1 | Q1 - 2013 | 9738 | 8403 | FALSE | 97 | Baseline = 100% complete. Variance due to slight project delay from a pending route modification request. The route modification was approved in December, 2012. This variance will have minimal impact on the overall project time line. | 72 |  | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Efforts are consistent with key milestones, and are projected to be under budget. | 0 | N/A | 100 | The core network design is complete. | 0 | N/A | 0 | N/A | 97 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 100 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 99 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 100 | Actual % expected to be 103%. Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Equipment deployment is greater than budget due to implementation delays pending the post award modification approval, but will not impact the overall project budget. | 93 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Network testing efforts are projected to be under budget. | 2013-05-15 14:15 | 2013-05-15 14:15 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2013 | Q2 | Q2 - 2013 | 10492 | 8897 | FALSE | 100 | Project will be complete and final budget generated for closeout. | 100 |  | Project will be complete and final budget generated for closeout. | 0 | N/A | 100 | Project will be complete and final budget generated for closeout. | 0 | N/A | 0 | N/A | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 2013-08-06 12:28 | 2013-08-06 12:28 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | 2013 | Q3 | Q3 - 2013 | 11594 | 9724 | FALSE | 100 | All project documentation and final budget submitted for closeout. | 100 |  | All project documentation and final budget submitted for closeout. | 0 | N/A | 100 | All project documentation and final budget submitted for closeout. | 0 | N/A | 0 | N/A | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 2014-01-13 16:53 | 2014-01-13 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570156 | 2010 | Q4 | Q4 - 2010 | 1382 | 2394 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-02-27 16:40 | 2011-02-27 16:40 | 6346 | 6346 | Centennial Board of Cooperative Educational Services
NT10BIX5570156 | 2011 | Q1 | Q1 - 2011 | 3886 | 3781 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-11-01 17:50 | 2011-11-01 17:50 | 6346 | 6346 | Centennial Board of Cooperative Educational Services
NT10BIX5570157 | 2010 | Q4 | Q4 - 2010 | 954 | 1999 | FALSE | 5 | N/A | 0 |  | N/A | 100 | N/A | 40 | N/A | 50 | N/A | 80 | N/A | 0 | N/A | 10 | N/A | 10 | N/A | 10 | N/A | 0 | N/A | 2011-02-01 11:24 | 2011-02-01 11:24 | 6432 | 6432 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2011 | Q1 | Q1 - 2011 | 1612 | 2527 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 60 | N/A | 100 | N/A | 100 | N/A | 30 | N/A | 30 | N/A | 15 | N/A | 15 | N/A | 0 | N/A | 2011-04-28 18:36 | 2011-04-28 18:36 | 6432 | 6432 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2011 | Q2 | Q2 - 2011 | 3062 | 3288 | FALSE | 22 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 80 | No Variance | 70 | Due to changes in the system configuration there were delays in obtaining the Rights of Way (ROW). Now that the design is finalized we will ensure all ROW's are completed. | 80 | Due to changes in site location we were delayed in obtaining all permits. Now that the sites have been finalized we are actively working on all permitting and expect to have all secured by the time site development begins. | 33 | Due to the delays in the EA process and the final site installation schedule the schedule for preparing sites may be adjusted. The overall preparation and installation of sites will remain on schedule. | 31 | With the extended time to finalize the contract for LTE equipment and services the overall procurement will be pushed back, however, we expect to be on schedule by the next reporting period. | 7 | Due to delays in the EA we were not able to begin fiber development when planned. We are currently working on the required RFP's and will have all fiber operational by the time the sites are developed. | 20 | The delays in the LTE contract and EA have caused some delay in deployment. We expect this element to be back on schedule by the next reporting period. | 0 | No Variance | 2011-08-12 16:22 | 2011-08-12 16:22 | 6432 | 6432 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2011 | Q3 | Q3 - 2011 | 4050 | 3868 | FALSE | 40 | No Variance | 0 | true | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 90 | Due to election cycles within local governments we may experience some delay in getting zoning/approval permits completed. | 60 | While we continue to make-up time lost awaiting the FONSI it may take us one more reporting period to be back on schedule. We are currently under contract for renovations at the Cherokee/West tower site and work will begin soon. We have accomplished approximately 70% of the required renovations at the ADCOM 911 facility and have all UPS and generators ordered. The primary site work remaining will be any installation work required (electrical, pads, etc.) for the eNodeB installations which will be performed during the site implementation. | 29 | Procurement is actually on schedule based on revised budget. | 25 | A majority of the network build, eNodeB installations will take place in the Spring/Summer of 2012. | 25 | A majority of fiber-optic equipment for existing fiber will be in place. As stated earlier, a majority of eNodeB installations will take place in Spring/Summer of 2012. | 10 | No Variance | 2011-11-15 17:16 | 2011-11-15 17:16 | 6432 | 6432 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2011 | Q4 | Q4 - 2011 | 5002 | 4676 | FALSE | 60 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Timing is dependant on route modification. All permits may be obtained by the end of March. | 75 | We anticipate all major site work will be completed. The only remaining work will be the specific electrical and mounting work at each site as the eNodeB's are mounted. | 54 | We expect to begin receiving the eNodeB's in March and anticipate a majority of all equipment will be on hand by the end of the quarter. Again, based on contract parameters the financial outlays will not exactly correspond to equipment receipt. | 30 | We anticipate having a majority of the fiber live with the exception of our final run to the Cherokee site and the 6th avenue path. | 25 | As a majority of the remaining equipment is tied to the eNodeB sites the deployment schedule will be concentrated during the 2nd and 3rd quarters of 2012. | 15 | While we can being to test specific elements, the overall testing of the network cannot take place until the eNodeB sites begin to be installed. We anticipate the testing process to increase towards the end of the 2nd quarter of 2012 and ramp up from there. | 2012-02-14 15:37 | 2012-02-14 15:37 | 6432 | 6432 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2012 | Q1 | Q1 - 2012 | 6352 | 5778 | FALSE | 73 | No Variance | 0 | N/A | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 85 | We anticipate all major site work will be completed. The only remaining work will be the specific electrical and mounting work at each site as the eNodeB's are mounted. | 80 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 50 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 50 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 35 | ADCOM 911 has begun testing specific elements of the broadband network. The LTE network has been tested in a limited fashion using the ENodeB located at the ADCOM 911 facility. The overall testing of the network will continue as the eNodeB sites are installed. Additional testing to start in Q2 of 2012. | 2012-05-30 14:19 | 2012-05-30 14:19 | 7504 | 7504 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2012 | Q2 | Q2 - 2012 | 7020 | 6137 | FALSE | 58 | At least one additional CAI link will either be deployed or activated. Some CAI locations are preparing facilities to house the broadband equipment. If their work is completed in the next quarter, then their links can be activated as well. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 55 | Additional site work will be performed for each new CAI link activated, and for any intermediary transport connections that are activated. Some site work performed in the previous quarters took longer, or required more work, than originally anticipated. Therefore, this number is lower than previously reported. If the project plan is re-scoped, the number will need to be adjusted again. | 85 | All of the LTE specific equipment was purchased prior to the suspension notice. A vast majority of that has been received on site today and is currently housed in a roll-off storage unit. Additional network equipment will be purchased to provide links for additional broadband network connectivity. | 55 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 55 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 25 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. These links will be tested before they are placed into production availability. No new LTE site equipment will be tested unless the partial suspension is lifted. | 2012-08-10 16:43 | 2012-08-10 16:43 | 7504 | 7504 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2012 | Q3 | Q3 - 2012 | 7316 | 6287 | FALSE | 62 | At least 4 additional sites will have microwave links upgraded or installed, and the network equipment for each will be installed and configured. This will allow each to serve as an interconnection point back to the overall fiber transport network. | 0 | true | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 60 | We anticipate the site improvement work will be completed at the Cherokee site, allowing us to install and configure additional networking equipment. Construction should begin at the Fire Station 54 monopole tower site. Additional microwave links may be installed to more of the remote sites. | 80 | All of the LTE specific equipment was purchased prior to the suspension notice. A vast majority of that has been received on site today and is currently housed in a roll-off storage unit. We anticipate we will need to purchase additional network transport equipment whether we move forward with LTE or with a Broadband Network only. However, we won't know which equipment until we are advised whether LTE will move forward or not. | 55 | At least four more intermediary transport connections will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 45 | At least one additional microwave link and three additional network switches will be deployed to activate 4 microwave transport paths. | 35 | At least 4 additional interconnection points will be activated. At that time, additional testing will be performed to verify the links will transport end-user data. | 2012-10-04 13:27 | 2012-10-04 13:27 | 7504 | 7504 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2012 | Q4 | Q4 - 2012 | 8684 | 7498 | FALSE | 70 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 65 | We anticipate the construction of the monopole at Fire Station 54 will be completed, and remodel work at the Cherokee site should be completed. | 81 | Some additional network equipment may need to be purchased to activate some of the fiber links being installed. Otherwise, no additional equipment will be purchased until we know if LTE will proceed or we need to re-purpose the grant. | 70 | At least 4 more sites should become active with the deployment of network equipment. If the final work related to the Jefferson County link is completed, a substantial portion of the fiber network will be completed. | 45 | The network equipment required to activate the 4 additional microwave sites should be deployed. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-02-08 16:54 | 2013-02-08 16:54 | 7504 | 7504 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2013 | Q1 | Q1 - 2013 | 9668 | 8366 | FALSE | 71 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 67 | We anticipate going under contract for services to provide security equipment at 3 key sites. | 82 | We anticipate the purchase of new security cameras, and site access equipment to deploy to 3 key sites. Otherwise, no additional equipment will be purchased until we know if LTE will proceed or we need to re-purpose the grant. | 75 | We anticipate the completion of the fiber into our Cherokee site. We are hopeful that we can finalize the links between 2 additional CAI's. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We anticipate placing equipment at the 2 additional CAI's. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-05-09 15:12 | 2013-05-09 15:12 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2013 | Q2 | Q2 - 2013 | 10258 | 8738 | FALSE | 71 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 70 | We anticipate we will have awarded the contract to install security equipment at 3 key sites. Additional electrical work should be completed at additional sites that will house microwave and network equipment. | 85 | We anticipate the purchase of new security cameras, and site access equipment to deploy to 3 key sites. We also plan to purchase and deploy new core network switches which are used to interconnect the CAI locations to the server applications housed at ADCOM911. Otherwise, no additional equipment will be purchased unless we modify the grant. | 75 | We anticipate the completion of the fiber into our Cherokee site. We are hopeful that we can finalize the links with one additional CAI. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We anticipate deployment of equipment at 1 additional CAI. We anticipate installation and activation of at least 3 microwave links to continue the broadband buildout. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-07-29 19:02 | 2013-07-29 19:02 | 7504 | 7504 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2013 | Q3 | Q3 - 2013 | 10918 | 9162 | FALSE | 72 | We anticipate completion of the administrative tasks associated with the grant extension. This includes the formulation of a revised budget, and a route modification. Assuming a timely acceptance of these documents, we anticipate beginning the process of vendor selection to complete portions of the broadband network build out. | 0 |  | N/A | 100 | We anticipate one additional EA, or a modification to our existing EA based upon our plans for network expansion. This additional EA is predicated upon the acceptance of ADCOM911's route modification. | 100 | We anticipate additional network design activities to take place based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Rights of Way for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Construction Permits for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 75 | We anticipate Site Preparation work to take place during the 4th quarter of 2013 once ADCOM911 awards a contract for site security measures, for which we have already obtained competative bids. | 82 | We do not anticipate significant equipment procurement during the 4th quarter of 2013, as much of the planned work will focus on achieving approval for the route modification, and the procurement of competitive bids to complete equipment purchases. | 75 | We have resolved the easement issues with the City of Northglenn related to the Cherokee Site fiber, and anticipate this work to be completed during the 4th quarter of 2013. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We do not anticipate significant equipment deployment during the 4th quarter of 2013, as much of the planned work will focus on achieving approval for the route modification, and the procurement of competitive bids to complete equipment purchases. | 60 | If the Jefferson County link and the Cherokee Site fiber work is completed, a substantial portion of the fiber network will be completed and can be tested. | 2013-10-23 16:29 | 2013-10-23 16:29 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2013 | Q4 | Q4 - 2013 | 11900 | 10067 | FALSE | 72 | We anticipate selecting vendors and awarding contracts to two major components of the overall system, the fiber optic line along E 120th Ave, and the deployment of the LTE gear. We also anticipate the approval of the revised budget and route modification to allow us to complete the project. | 0 |  | N/A | 100 | We anticipate one additional EA, or a modification to our existing EA based upon our plans for network expansion. This additional EA is predicated upon the acceptance of ADCOM911's route modification. | 100 | We anticipate additional network design activities to take place based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Rights of Way for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Construction Permits for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 85 | We anticipate that the site security project will be completed, as well as some tower strengthening which may be necessary. | 85 | We anticipate that the fiber optic equipment will be purchased during the 1st quarter of 2014, related to the 120th ave construction. There may also be some network equipment purchases, routers, switches etc. | 75 | While we anticipate the fiber optic construction to begin in the 1st quarter of 2014, we do not anticipate this work to be significantly completed by the end of the quarter. Other microwave backhaul used in the LTE network will probably not be installed until the 2nd quarter of 2014. | 50 | We do not anticipate significant equipment deployment during the 1st quarter of 2014. | 60 | We do not anticipate significant network testing to take place in the 1st quarter of 2014. | 2014-02-26 15:47 | 2014-02-26 15:47 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2014 | Q1 | Q1 - 2014 | 12222 | 10393 | FALSE | 80 | We anticipate that approximately 1/3 of the LTE sites will be installed and configured, and approximately half of the fiber optic project will be completed. We also hope to have some of the planned site work (electrical, UPS, HVAC etc) completed during the 2nd quarter. | 0 |  | N/A | 100 | No additional EA work is anticipated | 100 | No additional network design is anticipated | 100 | All rights of way for the fiber optic construction have been obtained | 100 | By the end of the 2nd quarter all construction permits should be obtained | 90 | We anticipate that the site security upgrade will be completed, as well as site preparation for a portion of the LTE sites. | 90 | We anticipate the purchase of additional network equipment, network test equipment, and miscellaneous equipment related to the LTE network deployment. | 82 | We anticipate that approximately 1/3 of the LTE sites will be installed and configured, and approximately half of the fiber optic project will be completed. | 70 | We anticipate that approximately 1/3 of the LTE equipment will be deployed. | 70 | In accordance with the SOW from General Dynamics, we anticipate that testing will be completed for the sites installed by the end of Q2. | 2014-05-21 13:19 | 2014-05-21 13:19 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2014 | Q2 | Q2 - 2014 | 12458 | 10639 | FALSE | 90 | We anticipate that all of the LTE sites will be operational by the end of the quarter, and that fiber optic construction will be completed. | 0 |  | N/A | 100 | No additional EA work is anticipated | 100 | No additional Network Design is anticipated | 100 | All rights of way have been obtained | 100 | We anticipate that all construction permits will be issued in the coming weeks. | 100 | We anticipate that all Site Prep activities will be completed. | 93 | The remaining network equipment is on order and will be invoiced during the 3rd quarter. We also anticipate additional LTE UE purchases, and network test equipment, as well as some application hardware purchases. | 92 | We anticipate the fiber optic construction to be completed by the end of the quarter as well as the remaining LTE sites. | 85 | We anticipate that the remainder of the LTE sites will be deployed, as well as a portion of the network equipment for backhaul. We also hope to deploy some UE devices to the public safety users for testing. | 82 | We anticipate that roughly 2/3 of the LTE network will be tested, as well as the fiber optic network currently under construction. | 2014-08-26 17:42 | 2014-08-26 17:42 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2014 | Q3 | Q3 - 2014 | 12598 | 10868 | FALSE | 90 | We anticipate that all currently approved project activities will be completed by the end of the 4th quarter. With the currently approved and scheduled work, the project will be completed under budget. | 0 |  | N/A | 100 | No additional EA work is anticipated | 100 | All network design has been completed. | 100 | All rights of way have been obtained | 100 | All construction permits have been obtained | 100 | All site preparation work will be completed by the end of the 4th quarter. | 100 | All Equipment will be purchased. | 100 | Network Build will be complete by the end of the 4th quarter. | 100 | We anticipate that all equipment will be deployed by the end of the 4th quarter. | 100 | We anticipate that all network testing will be completed by the end of the 4th quarter. | 2014-11-14 13:07 | 2014-11-14 13:07 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2014 | Q4 | Q4 - 2014 | 12692 | 11017 | FALSE | 89 | While Adcom did complete the planned work for Adams County and Denver, the addition of DIA, and the State of New Mexico has expanded the scope of work, so the percentage represents an estimate of where we will be by the end of Q1 2015. | 0 |  | N/A | 100 | Adcom does not anticipate that any additional Environmental Assessment work. | 100 | Adcom anticipates that all network design needed to integrate DIA and the State of New Mexico to be completed by the end of Q1 2015. | 100 | Adcom does not anticipate additional rights of way. | 98 | Adcom anticipates that the majority of the construction permits necessary for DIA will be completed. | 95 | Site preparation cannot begin until construction permits are issued, and we anticipate site prep to begin in force in Q2 2015. | 95 | Adcom will make several network related equipment purchases in the first quarter of 2015. | 100 | Adcom should complete the remaining microwave links during Q1 2015. | 90 | Adcom plans to deploy several key network devices during Q1 2015, as well as continue the deployment of UE devices to our users. | 90 | Adcom anticipates that the last site within Adams County will be tested by the end of Q1 2015. The additional network testing will be focused on the LTE sites at DIA, which we plan to conduct during Q2 and Q3 of 2015. | 2015-02-12 17:58 | 2015-02-12 17:58 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2015 | Q1 | Q1 - 2015 | 12856 | 11226 | FALSE | 100 | Adcom anticipates all project activities will be completed. | 0 |  | N/A | 100 | Adcom does not anticipate that any additional Environmental Assessment work. | 100 | Adcom anticipates that all network design will be completed. | 100 | Adcom does not anticipate additional rights of way. | 100 | Adcom anticipates that all permits will be finalized. | 100 | Adcom anticipates that all site preparation will be completed. | 100 | Adcom anticipates that all equipment will be purchased. | 100 | Adcom anticipates that the network build will be complete. | 100 | Adcom anticipates that all equipment will be deployed. | 100 | Adcom anticipates that all network testing will be completed. | 2015-05-29 14:13 | 2015-05-29 14:13 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570157 | 2015 | Q2 | Q2 - 2015 | 12896 | 11280 | FALSE | 100 | Adcom anticipates all project activities will be completed. | 0 |  | N/A | 100 | Adcom does not anticipate that any additional Environmental Assessment work. | 100 | Adcom anticipates that all network design will be completed. | 100 | Adcom does not anticipate additional rights of way. | 100 | Adcom anticipates that all permits will be finalized. | 100 | Adcom anticipates that all site preparation will be completed. | 100 | Adcom anticipates that all equipment will be purchased. | 100 | Adcom anticipates that the network build will be complete. | 100 | Adcom anticipates that all equipment will be deployed. | 100 | Adcom anticipates that all network testing will be completed. | 42255.4469 | 42255.4469 | 7688 | 7688 | Adams County Communications Center, Inc.
NT10BIX5570158 | 2010 | Q4 | Q4 - 2010 | 974 | 2020 | FALSE | 1 | Zero variance. | 0 |  | N/A | 60 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 10 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 2011-02-04 12:00 | 2011-02-04 12:00 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2011 | Q1 | Q1 - 2011 | 1870 | 2680 | FALSE | 3 | Zero variance | 0 |  | Zero variance | 80 | Zero variance | 0 | Zero variance | 5 | Zero variance | 10 | The Authority has begun outreach to relevant permitting bodies, regulatory agencies, and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until the completion of a draft EA, which occurs mid-way through this quarter, and the conclusion of contract negotiations, which will happen near the end of this quarter. Progress on this milestone will thus be slowed through this calendar year. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-05-02 18:52 | 2011-05-02 18:52 | 6479 | 6479 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2011 | Q2 | Q2 - 2011 | 3020 | 3267 | FALSE | 3 | Pending negotiations resuming, the project schedule will be moving forward. | 0 |  | Zero variance | 90 | We will be soliciting CEQA / Environmental services contract in this quarter to assist with completing the EA. | 50 | Delay in the procurement process has delayed design review. We project this will be underway once negotiations are concluded and the contract is executed. | 15 | Zero variance | 15 | The Authority continues outreach to permitting bodies, regulatory agencies, and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until conclusion of contract negotiations. Progress on this milestone will thus be slowed through this calendar year. | 0 | No site preparation will begin until the FONSI is issued. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-08-11 14:21 | 2011-08-11 14:21 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2011 | Q3 | Q3 - 2011 | 3498 | 3519 | FALSE | 4 | Due to canceled procurement. | 0 |  | N/A | 50 | Due to canceled procurement. | 2 | Due to canceled procurement. | 1 | Due to canceled procurement. | 1 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Zero variance. | 2011-10-27 11:58 | 2011-10-27 11:58 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2011 | Q4 | Q4 - 2011 | 4706 | 4354 | FALSE | 10 | Due to canceled procurement. | 0 |  | N/A | 60 | Due to canceled procurement. | 60 | Due to canceled procurement. | 1 | Due to canceled procurement. | 10 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Zero variance. | 2012-01-30 15:27 | 2012-01-30 15:27 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2012 | Q1 | Q1 - 2012 | 5916 | 5557 | FALSE | 5 | LA-RICS anticipates further progress in site acquisition, environmental assessment. | 0 |  | N/A | 55 | Finalize technical reports, continue environmental analysis, pending initiation of federal consultations. | 25 | No updates until a contract is executed with Telecommunications System vendor. | 10 | Site acquisition and valuation of in-kind land/property contribution. | 10 | Site use agreements | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Zero variance | 2012-05-02 17:19 | 2012-05-02 17:19 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2012 | Q2 | Q2 - 2012 | 6850 | 6051 | FALSE | 6 | LA-RICS anticipates release of addendum or new RFP to address LTE related equipment in proposed specifications. | 0 |  | N/A | 55 | Continue refining the NEPA environmental assessment/CEQA initial study document structure and continue the outreach to key stakeholders, inlcude local land use agencies. | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 2 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and design is finalized. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 2012-08-03 12:29 | 2012-08-03 12:29 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2012 | Q3 | Q3 - 2012 | 7824 | 6615 | FALSE | 7 | Staff will continue to draft the RFP for the LTE system. | 0 |  | N/A | 60 | Continue to evaluate the LTE sites for potential CEQA exemption eligibility | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 4 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2012-11-09 16:03 | 2012-11-09 16:03 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2012 | Q4 | Q4 - 2012 | 8648 | 7468 | FALSE | 8 | The RFP for the LTE system should be substantially complete for FirstNet review by Feb, 2013, and industry review by March, 2013. |  |  | N/A | 60 | Continue to evaluate the LTE sites for potential CEQA exemption eligibility | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 4 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and system design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2013-02-01 12:17 | 2013-02-01 12:17 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2013 | Q1 | Q1 - 2013 | 9706 | 8386 | FALSE | 9 | LA-RICS anticipates more progress on: the environmental front, in the preparation of the RFP-LTE, extension of the BTOP deadline and lifting of partial suspension. | 0 |  | N/A | 61 | Continue CEQA exemption eligibility assessment including additional field surveys; continue to assess a modified approach to NEPA and CEQA documentation to provide more clarity. | 27 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 6 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and system design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2013-05-13 16:09 | 2013-05-13 16:09 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2013 | Q2 | Q2 - 2013 | 10152 | 8642 | FALSE | 3 | Procurement process for the LTE system is expected to start soon |  |  |  | 65 | Provide project information needed to initiate consultation with federal resource agencies. Continue to consult with NTIA on NEPA document approach and methodology. Re-initiate local outreach. | 29 | Complete the RFP for the LTE system and begin the procurement process | 7 | Conduct detailed site and land valuation analysis; will begin site use agreement consultation with cities. | 3 | Working with legal counsel to plan for permitting of LTE sites | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 2013-07-24 15:28 | 2013-07-24 15:28 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2013 | Q3 | Q3 - 2013 | 11192 | 9377 | FALSE | 4 | The procurement process for the LTE contractor should be nearly completed. | 0 |  | N/A | 70 | Complete Chapters 1 and 2 of the preliminary working draft NEPA EA and Chapters 3 and 4 for three resource areas (socioeconomics, human health and safety, and geology and soils). Complete virtual (i.e. desktop) planning level survey to identify National Register of Historic Places (NRHP) eligible sites around proposed project sites and complete windshield surveys for these sites. Continue consultation coordination with California SHPO and federal resource agencies. Start coastal consistency certification process for proposed project sites in the coastal zone. | 29 | Will start immediately after LTE contractor is hired. | 8 | Detailed site and land valuation analysis is being conducted; consultations with potential LTE sites continue on site use agreement. | 3 | Work continues with legal counsel for permitting of LTE sites | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 2013-11-05 13:57 | 2013-11-05 13:57 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2013 | Q4 | Q4 - 2013 | 11912 | 10079 | FALSE | 5 | The initial phase of the project begins. | 0 |  | N/A | 95 | Complete an administrative draft NEPA EA. Continue the resource agency (USFWS and California Office of Historic Preservation (SHPO)) and federal land-administering agencies consultation and coordination processes to completion. | 35 | Will start immediately after LTE system contractor is hired. | 10 | Continue progress on outreach activities and site access agreement preparation. | 5 | Continue legal counsel work on permitting for LTE sites. | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 2014-02-27 15:49 | 2014-02-27 15:49 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2014 | Q1 | Q1 - 2014 | 12230 | 10402 | FALSE | 7 | 14 project management plans are expected to be completed during the next quarter. This includes the project schedule which should become available by April, 2014. Work on preliminary site design and system design will start. | 0 |  | None | 90 | Complete a preliminary working draft Biological Assessment (BA). Continue the resource agency (USFWS and California Office of Historic Preservation (SHPO)) and federal land-administering agencies consultation and coordination processes. In late March, LA-RICS submitted to the FAA its proposed list of 231 towers for registration. | 50 | Preliminary designs for the site network, backhaul, EPC, network management system, inventory management system are expected to be completed during the next quarter. | 80 | Draft site access agreements for LA County facilities are expected to be finalized in two weeks and executed in late June, 2014. Draft site access agreements for cities are expected to be executed in June, 2014. There will be a few independent city site access agreements that will lag. These will be reported upon in the next update. | 35 | Zoning and permitting packages are expected to be completed during the next quarter. | 20 | Review and finalize site sketches, review and finalize site surveys, conduct more site walks. | 10 | Assuming FONSI is received in June, 2014, equipment procurement can start immediately. | 10 | Pending approval of construction permits. | 0 | Pending FONSI | 0 | Pending | 2014-05-22 14:54 | 2014-05-22 14:54 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2014 | Q2 | Q2 - 2014 | 12450 | 10633 | FALSE | 10 | After FONSI is issued, LA-RICS can begin site construction activities and placing orders for microwave equipment. On August 13 an updated schematic backhaul design will be completed for review by the Authority. The backhaul design will utilize backhaul solutions previously presented and fine-tuned by both the design/builder and the Authority. It will be the basis of the formal and final design. The final design will provide connectivity to all PSBN sites through a hybrid of microwave and fiber. The microwave solution will utilize both new and existing links while the fiber deployment will include commercial and private (Member Agency â€“ owned) links. The overall project plan will be completed once the final backhaul design is submitted and approved in August. | 0 |  | None | 97 | Conclude ESA Section 7 informal consultation with USFWS. Complete the final EA incorporating all federal agencies' EA review comments. Continue SHPO consultation and the submittal of FCC 620/621 Forms to California SHPO for review and concurrence. | 100 | All system design activities are expected to be completed 90-100% while site design activities will continue on 45 sites. The final list of potential sites is expected by mid-August which will have all previous Authority design review comments incorporated. This site list will determine the network design because it will be the universe of sites and will also dictate the routing of the backhaul design. The specifics on how the traffic will be routed within the paths will not be finalized until all sites are confirmed. | 90 | Right of Entry. The ROE for the City of Monrovia is expected to be completed. There are 10 ROEs that are currently under review by city attorneys, many of which are expected to be completed. Site Access Agreement. The SAA for the City of Diamond Bar is expected to be executed, while that of the City of Gardena will be presented to their city council. The L.A. County site access agreements will be fully executed by mid-August and the site access agreements by all City of L.A. sites will be executed by September 1. The remaining independent city site access agreement process will be completed without any impact to the project master schedule with the final agreements anticipated no later than the end of January, 2015. Site surveys (inclusive of geo-technical boring) will continue through September and possibly as late as November as the final Right to Enter and/or Site Access Agreements are received and SHPO concurrence is received. A significant number of site surveys will be comple | 80 | All County and City of L.A. sites are exempt from the zoning process. The remaining Independent City sites will have zoning activities on-going through the end of the year. An expedited permit process has been agreed to with the County and City which will allow for building permits within three to four days from submission of each set of plans. Independent City plan review and permitting will take longer and will be in process starting in July and August and completing in the first quarter of 2015 with no impact to the project schedule. There are several Independent Cities who agreed to expedite the process for LA-RICS sites. Outreach efforts will continue through August and September as zoning meetings and presentations take place at independent cities or other locations as necessary. | 100 | Review and approval of site sketches will continue and be followed by site walks/surveys. | 60 | The first equipment order (approximately 35 sites) was placed in July and will see equipment arriving in late August. The next equipment order will be placed mid to late August with subsequent equipment orders placed every few weeks until all equipment has been ordered. The order for towers will continue through the next several months as batches of sites are released for construction. Factory pre-orders are in place and in August the next batch of towers will be released for production and delivery. Fabrication and delivery of each order will take approximately three to four weeks. | 35 | Civil construction activities will begin on a site by site basis. During the next quarter: No new network miles will be deployed. No CAIs will be served Broadband Wholesalers or Last Mile Providers is not applicable for this project. | 35 | Deployment of PSBN components will start on a site by site basis. | 0 | Pending | 2014-08-22 15:17 | 2014-08-22 15:17 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2014 | Q3 | Q3 - 2014 | 12590 | 10863 | FALSE | 18 | Additional independent cities will be added to the permitting process and we will finalize the process of getting sites approved for use in the program. Once we know the final site count, including all participating independent cities, the final equipment orders can be placed and the final stage of backhaul design can be formalized and completed. | 0 |  | None. | 98 | PA anticipated in early October, and FONSI anticipated in mid-October. Provide supplemental support for federal agency-administered sites, and any follow-on environmental work required as a result of Special Award Conditions (SAC) items (i.e. any additional NEPA work required by those agencies). Complete the Section 106 process with SHPO. | 93 | There will likely still be some Site Access Agreements being negotiated with Authority members which would likely impact backhaul design and coverage. | 95 | To-date, 164 Rights of Entry and 91 Site Access Agreements were executed; 78 outreach activities were conducted, and 104 sites released for Geotech drilling. | 75 | Applications for building permits will be on-going with batches of permits submitted weekly until the process completes in mid 2015. | 85 | Projection based on current plan for receipt of permits | 40 | Additional procurement will be based upon receipt of pending Site Access Agreements and final backhaul design. | 5 | The Evolved Pocket Core at FCCF was installed starting in July and consisted of two phases. Phase one was to install and hook system up, phase two is the optimization of the core. Install was completed within two weeks of start and the optimization is on-going and will complete in mid November | 20 | Dependent upon progresss of construction permits and other approvals and site preparation. | 0 | None yet. | 2014-11-12 16:07 | 2014-11-12 16:07 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2014 | Q4 | Q4 - 2014 | 12696 | 11022 | FALSE | 30 | Labor unions identified sites they are concerned with regarding safety of radio frequency emission. To address this and avoid delay, LA-RICS will continue dialogue with the labor unions. | 0 |  | N/A | 99 | LA-RICS will submit route modification requests for sites requiring additional power supply which were not contemplated in the original design. For sites that will require supplemental fiber in lieu of microwave, supplemental EA and route mod will have to be prepared. These will have minor temporary impact while awaiting NTIA approval to commence work on these sites. | 99 | There will likely still be some site access agreements being negotiated with Authority members which would likely impact backhaul design and coverage. System design review has been delayed by the extension of the member opt-out period and multiple tower changes requested as a result of community outreach activities. To avoid further delay in finalizing the system design, member agencies will be given a deadline to decide whether they want potential sites in their areas to be included in the network or not. | 99 | Variance may result from delay in processing of site access agreements. | 60 | Applications for building permits will be on-going with batches of permits submitted weekly until the process completes in mid 2015. | 90 | Variance may result from delays in processing of construction permits. | 80 | Additional procurement will be based upon receipt of pending site access agreements and finalization of the backhaul design. | 30 | Equipment such as generators and equipment cabinets currently in secure storage awaiting deployment will be deployed as sites come on line for construction. | 45 | Progress of construction permits and other approvals and equipment procurement will impact progress for this milestone. | 0 | Delayed site access agreements, rights of entry, SHPO approvals, FONSI will impact special operations test, stress test, staging, wide area tuning, KPI testing, coverage testing. Significant testing of the PSBN will not begin in earnest until site clusters are complete. The first clusters expected to go live for testing will be available in late Q2-2015 | 2015-02-18 15:27 | 2015-02-18 15:27 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2015 | Q1 | Q1 - 2015 | 12844 | 11216 | FALSE | 32 | The NTIA and NOAA placed the project under suspension on April 3, 2015. LA-RICS submitted the required Corrective Action Plan (CAP) on April 13, 2015 for the suspension to be reviewed and lifted. | 0 |  | N/A | 95 | Based on discussions with NTIA through April 15, 2015, LA-RICS will submit two supplemental EAs for sites that were previously contemplated in the Supplemental EA, and route mods 03 and 04. We anticipate finalizing Section 106 requirements during this period. | 99 | The Corrective Action Plan has redefined the PSBN at 67 sites + 15 Cells on Wheels (COW) sites. This redefined PSBN will still require additional Site Access Agreements from independent cities and agencies or Boards. Our planning process is complete regarding site selection with further input on COW locations. | 99 | The redefined PSBN still requires 17 additional Site Access Agreements and an MOU with Caltrans and the California Office of Emergency Services. | 60 | The Authority expects all Building Permit applications to be submitted by the end of April or early May. | 90 | There are few sites that still require geo-technical drilling. Some rooftop and existing towers require the finalization of load studies and structural integrity testing. | 80 | Notices To Proceed have been issued for 25 in-vehicle routers for SOT, 75 TMR cabinets, and backhaul equipment for 79 sites. | 30 | The Authority, if the CAP is accepted, plans on resuming construction immediately on all approved Baseline PSBN Sites. The expectation is that the Authority will complete approximately 15 sites a month during the period. | 45 | The Authority will continue to deploy equipment as sites are completed according to the CAP response. | 99 | If the CAP is approved, the Authority will begin the process of Special Operations Testing during the end of this period. | 2015-05-26 14:58 | 2015-05-26 14:58 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | 2015 | Q2 | Q2 - 2015 | 12906 | 11285 | FALSE | 100 | Complete, pending individual site and cluster testing and turning up of the entire network. | 0 |  | After sites contemplated in fire stations were dropped from system design, it is projected that 606 community anchor institutions (CAIs) could be directly connected by the proposed network. | 100 | We anticipate all environmental permitting and compliance efforts will be completed by the end of this period. This will include finalizing SEA-2, completing consultation with SHPO for the 15 COW sites, and with USFWS for the six sites in the Supplemental BA. Environmental monitoring efforts will continue based on construction activity. | 100 | Potential variance reason could be delay in securing final utility connection | 100 | Potential variance reason could be delay in rights of way for COW sites. | 100 | Potential variance reason could be delay in securing permits for COW sites. | 100 | Potential variance reason could be delay in securing rights of way for COW sites. | 100 | N/A | 100 | Potential variance reason could be delay in securing utility connections. | 100 | Potential variance reason could be delays in COW sites. | 95 | Potential variance reason could be delay in securing utility connections. | 42256.6434 | 42256.6434 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority
NT11BIX5570001 | 2010 | Q3 | Q3 - 2010 | 2430 | 2960 | FALSE | 0 | n/a | 0 | n/a | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-06-27 12:06 | 2011-06-27 12:06 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2010 | Q4 | Q4 - 2010 | 2424 | 2957 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-06-02 10:18 | 2011-06-02 10:18 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2011 | Q1 | Q1 - 2011 | 2040 | 2765 | FALSE | 10 | While this percentage looks high for a pre-FONSI amount, it includes the in-kind match of $8.9 million booked in March. It is still below our baseline projection of 27%. | 0 |  | With no equipment ready for deployment this quarter, we won't have the need to lease warehouse space. Thus, we will not meet our baseline projection of 23%. | 100 | We fully expect the Environmental Assessment to be complete and anticipate approval during this quarter, with a FONSI received by the end of June. This is in line with the baseline completion of 100%. | 10 | The logical network design should be complete, but with the design/build firm hired late in the quarter, The network design will remain behind the baseline projection of 100%. | 92 | This is the same percentage complete as for the first quarter of 2011. It is double the baseline projection of 46%. | 0 | We anticipate that the design/build firm that we engage will complete all permitting, so until that procurement is complete, permitting costs will remain at 0%. This is below the baseline target of 11%. | 0 | We anticipate that the design/build firm that we engage will complete all site preparation, so until that procurement is complete, site preparation costs will remain at 0%. This is below the baseline target of 35%. | 0 | There will be a small spend this quarter, but not enough to reach 1%. The equipment RFP will be complete and possibly a bid selection made, but the dollars won't actually be spent until the next quarter. We will not make the baseline target of 29%. | 4 | The 4% includes project network overhead, which is included in this category. However the actual Network Build won't begin until after the FONSI has been obtained. This is below the baseline target of 23%. | 0 | As we don't anticipate having our FONSI until the very end of the quarter, we won't be able to deploy any of our purchased equipment during this quarter or meet our baseline goal of 26%. However, once the FONSI is received we will deploy equipment to connect 345 community anchor institutions. | 0 | We will not meet our baseline goal of 18% as we will not have network components to start testing yet. | 2011-05-16 11:53 | 2011-05-16 11:53 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2011 | Q2 | Q2 - 2011 | 2908 | 3211 | FALSE | 16 | The overall picture is that we are behind our baseline schedule to the earlier delays caused by the grant transfer. This has resulted in us not receiving our FONSI yet, although we should receive it within days of this report. By the end of the next quarter,we will just be beginning the start of our build process. However, we have planned for accelerated activity with our design/build contractor once the FONSI is issued. So, we anticipate being 16% complete versus our baseline target of 41% complete, but in subsequent quarters we plan to bridge that gap and make significant progress to catch up to our milestones. | 0 |  | With no equipment ready for deployment this quarter, we won't have the need to lease warehouse space. This, we will not meet our baseline projection of 35%. | 100 | Once the FONSI has been issued, we will receive the final invoice from our Environmental contractor, which will take us to 100% complete spend for this category. | 98 | The network design will be substantially complete by the end of the quarter, although there may be a little open cost for possible future changes. The 98% complete will be just slightly behind the baseline target of 100% complete. | 92 | 92% is consistent with the baseline amount. | 0 | The baseline target is 25% complete, but with the physical network design just beginning this quarter, there well be no spend for permits. | 0 | The baseline target is 44% complete, but with the physical network design just beginning this quarter, there well be no spend for permits. | 1 | The baseline target is 40% complete. While we do anticipate the Equipment RFP to be awarded by the end of the quarter, there will probably be no actual spend until the beginning of the subsequent quarter. | 10 | While the baseline target is 44%, we anticipate very little build activity in this quarter as the physical design is completed. However, we will continue with a significant effort in procuring IRUs according to the route parameters. The Legacy network is also purchased during this quarter, which, with some upgraded equipment, will allow us to show improved service to over 400 subscribers. | 0 | Without the large equipment procurement, there will be no deployment. This is below our baseline goal of 37%. | 0 | We will not meet our baseline goal of 29% as we will not have network components to start testing yet. | 2011-08-01 18:02 | 2011-08-01 18:02 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2011 | Q3 | Q3 - 2011 | 4176 | 3936 | FALSE | 26 | Due to the delays caused by the grant transfer and the statewide Environmental Assessment process which resulted in the delay in receiving our FONSI, we are behind our baseline projection of 50% of our dollars spent. Now that the FONSI has been received, we have accelerated our activity with our design/build contractor and have issued two RFIs to help us obtain information for the final decision-making of the lease versus build options for our network design. This process will be substantially completed during this quarter. | 0 |  | The main cost of the baseline projection, which is at 44% complete this quarter, is for warehousing to store and stage equipment. While equipment is being procured this quarter, at this time we won't need outside warehouse space. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, based on the baseline spend projections, this initial logical network and network equipment design category will be complete this quarter | 92 | The Rights of Way baseline projections are at 95%, so we will be slightly behind the activity in this category. The CDOT rights of way will be approved, but negotiations for smaller segments will be ongoing. | 0 | This category will be behind the baseline projection of 35% of the dollars spent because the following quarter will commence with the major construction, and many permitting fees will be paid then. | 0 | This category will be behind the baseline projection of 55% of the dollars spent because the following quarter will commence with the major construction, and many site preparation costs will be paid then. | 22 | While we're behind the baseline projection of 50% of the spend complete, this is a category where we'll quickly catch up. The first major order for layer 2 and 3 equipment will be placed this quarter, putting us at 22% complete on our equipment spending. Please note that in the budget categories (last page of this report) layer 2-3 equipment is part of the Construction category. | 20 | The network build baseline projection is 44% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, activity has now picked up in obtaining IRUs, and as a result of the RFI process, RFPs and direct negotiations will commence this quarter according to the route parameters, and spending should increase dramatically in this category. | 2 | The baseline projection is to have 47% of the spend complete, but with equipment just arriving in this quarter, the spend will be very minor. | 36 | The baseline projection was to have 40% of the testing complete. This 36% estimate is for "lab" and equipment testing costs. With the network build delays described earlier, these costs will mostly be incurred in subsequent quarters. | 2011-11-21 10:31 | 2011-11-21 10:31 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2011 | Q4 | Q4 - 2011 | 5398 | 5080 | FALSE | 33 | Due to the delays caused by the grant transfer and the statewide Environmental Assessment process that resulted in the delay in receiving our FONSI, we are behind our baseline projection of 60% of our dollars spent. During the next quarter, the focus will be on finalizing the remaining IRUs and beginning construction to deploy the peering sites. Then, construction will begin on several routes in the state, with the majority of that activity falling into the second and third quarters of 2012. | 11 |  | The main cost for this category is for warehousing to store and stage equipment. A space will be leased this quarter and equipment verification will begin in this space. However, it is behind the 55% baseline projection for spend. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 92 | This is the same as the current quarter, although discussions are in progress for additional rights of way. This will be behind our baseline projection of 97%. | 27 | The 27% projected completion will be behind the 48% baseline projection as the permitting activities will just start in earnest during this quarter. They will accelerate over the subsequent quarters. | 1 | Site preparation costs are minimal during this quarter will just involve the initial peering sites. This is behind the baseline projection of 70%. | 24 | Equipment Procurement is behind the baseline projection of 63% complete although more layer 2-3 equipment has been ordered this quarter. However, the equipment won't be received or invoiced until the beginning of the next quarter, so the spend remains flat through March 31. Please note that in the budget categories (last page of this report) layer 2-3 equipment is part of the Construction category. | 29 | The Network Build baseline projection is 55% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. During this quarter as RFPs are awarded and the final IRUs are negotiated, construction will begin and will ramp up to full activity over the next couple of quarters. | 14 | As the first layer 2-3 equipment as been delivered, Equipment Deployment has begun, although well behind the 59% baseline projection. | 0 | No spend is anticipated here yet, which is behind the 51% projection. Please note that there was an error in this category in the last quarter, as spend projected here was actually for the Equipment Deployment category above. | 2012-02-29 13:22 | 2012-02-29 13:22 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6072 | 5635 | FALSE | 46 | Due to the previously described delays, we'll still be behind our baseline projection of 74% complete. However, this quarter starts a period of significant build progress for us. As described above, construction is starting in 5 parts of the state simultaneously. | 14 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. We will be behind our 70% spend as we just recently leased the space, and the rent will be static through the remainder of the project. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | Rights of way negotiations and approvals will be completed this quarter. | 34 | Although this is behind our baseline projection of 67% complete, this activity will have more spend as pre-construction work throughout the state is ramping up. | 3 | This category is significantly behind the baseline projection of 85%. Site preparation will be done at the peering site locations and the CAIs that are connected this quarter. Spend should increase significantly during the third quarter as more laterals are built and CAIs are connected. | 48 | We will remain behind the baseline projection of 78% complete, but equipment procurement does continue this quarter as more layer 2-3 equipment is purchased and we begin the procurement of wireless equipment. Please note that in the budget categories (the last page of this report), layer 2-3 equipment is part of the Construction category. | 40 | The Network Build baseline projection is 70% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, during this quarter there will be new IRUs signed as well as the start of physical construction costs. This quarter and the next will be key periods to build in several parts of the state to take advantage of milder weather. | 16 | Equipment deployment has begun, although well behind the 74% baseline projection. Equipment will be deployed as CAIs are connected during the construction phase. | 17 | Network Testing spending begins this quarter, and will accelerate as the network is constructed. We will be behind our baseline projection of 67%, but this category will ramp up in conjunction with the Network Build. | 2012-05-14 18:11 | 2012-05-14 18:11 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7274 | 6264 | FALSE | 64 | Due to the previously described delays, we'll still be behind our baseline projection of 87% complete. However, this quarter will continue with significant construction activity in several parts of the state simultaneously. | 32 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense is behind our 85% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | Although currently at 100%, this category will continue to have activity as we begin construction on additional CDOT rights of way in the next quarter. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the baseline amount was understated. | 9 | This amount is significantly behind the baseline projection of 94% as site preparation activity is just getting underway this quarter as construction continues and the laterals are built. However, some of this activity is being included in the Network Build category as not all Site Preparation costs have been broken out separately. | 68 | Equipment procurement will remain behind the baseline projection of 90% complete despite the second wave of layer 2 and 3 equipment arriving this quarter. Part of the difference is that the equipment total actual cost is lower than the original projection amount, so this category should see a savings that is applied to other categories. Please note that in the budget categories (the last page of this report), layer 2-3 equipment costs are part of the Construction category. | 62 | Although less than the baseline projection, the network build continues to ramp up as construction continues in several parts of the state. Obviously, the build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, with both construction in full swing and the addition of 5 IRU's that will be signed this quarter, our deployed miles will greatly increase throughout the state. | 39 | Equipment deployment continues this quarter as more site builds are completed. However, this category remains behind the baseline projection of 87% complete. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So the roughly $500,000 in total budget will be reallocated to Network Build. | 2012-08-29 14:50 | 2012-08-29 14:50 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8122 | 6768 | FALSE | 67 | Due to the previously described delays as well as the construction invoicing process taking additional time, we will be behind hour 94% baseline projection. However, there will still be continuing construction activities in various parts of the state where weather is less of an issue. | 18 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense will be behind our 94% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | As part of the submitted budget reprogram, we anticipate that the CDOT rights of way spend will be completed. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the baseline amount was understated. | 7 | This amount will be far behind the original baseline projection of 98% complete due to an overstatement in the baseline estimate. These amounts have been corrected in the submitted budget reprogram. | 74 | The Equipment spend amount will be behind the baseline projection of 96% due to both the timing of invoicing as well as an actual cost savings in the equipment purchased versus the original budgeted amount. So, equipment purchases will see savings that are applied to other categories. Please note that in the budget categories (the last page of this report), layer 2-3 equipment costs are part of the Construction category. | 66 | The network build is continuing at full bore through the end of the Fall build season. However, because of the timing of the invoicing of our major contractors, work performed in the Fall will mostly be paid in the first quarter of 2013. So, although physically more than 66% complete, based on payments we will be behind our baseline projections. We also anticipate the signing of one more IRU, but again payment will not occur until January. | 32 | With the delays in construction, equipment deployment will also be behind the baseline projection of 95% complete. However, spending will continue in this category over the next three quarters. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So, the roughly $500,000 in total budget will be reallocated to Network Build. | 2012-11-28 15:56 | 2012-11-28 15:56 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2012 | Q4 | Q4 - 2012 | 9002 | 7778 | FALSE | 58 | Due to the previously described delays including the construction suspension, we will be far below our baseline projection of 98% complete. Again, this calculation is based on actual dollars spent, and not work completed, so once we pay for our completed construction activities, and once we are again actively constructing the network, the percentage complete will be significantly higher. | 22 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense will be below our 98% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | More costs will be incurred in this category due to the required supplemental Environmental Assessment, however, based on dollars spent, this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 92 | Once the submitted budget reprogram has been approved, the CDOT rights of way spend will be completed. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the original baseline estimate was understated. | 8 | This amount will be far behind the original baseline projection of 100% complete due to an overstatement in the baseline estimate. These amounts have been corrected in the submitted budget reprogram. | 49 | The Equipment spend amount will be below the baseline projection of 99% due to the timing of equipment payments, the timing of the ordering of the final equipment, as well as an actual cost savings in the equipment purchased versus the original baseline projection amount. So, this category will result in savings that have been rebudgeted to other categories in the budget reprogram. Please note that in the budget categories (the last page of this report), layer 2 and 3 equipment costs are part of the Construction category. | 56 | Due to the construction suspension and the corresponding hold restrictions on construction payments, the Network Build completion percentage will remain far below its 98% baseline projection. However, once the supplemental Environmental Assessment has been approved and the funds are released to pay for build activities, the completion percentage in this category will quickly accelerate. There are many routes that are nearly complete where activity can promptly resume. | 26 | With the delays in construction, equipment deployment will also be behind the baseline projection of 99% complete. Spending will continue in this category as the network construction is completed and equipment is actually deployed. | 0 | This category is actually being absorbed into the Network Build costs as there expenses are not being specifically broken out. So, the roughly $500,000 in total budget is being reallocated to the Network Build category. | 2013-02-27 10:58 | 2013-02-27 10:58 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2013 | Q1 | Q1 - 2013 | 9986 | 8537 | FALSE | 93 | This total will be behind our original projection of 100% percent complete because of the delays at the beginning of the project as well as the recent temporary construction suspension. However, we anticipate the suspension to be lifted and funds freed up to pay for completed work as well as to begin the work on the final approved routes. | 25 |  | The costs of the outside testing and warehouse facilities will be well behind the baseline projection of 100% as the facilities were obtained later than anticipated and are less expensive than the projected amount. | 100 | More costs will be incurred in this category due to the required supplemental Environmental Assessment, however, based on dollars spent, this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | We anticipate the change in the CDOT match amount to be approved, and the amount on routes already completed or in progress will be booked this quarter. Although this amount will be below our rebudgeted amount, it will far exceed the original baseline projection. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the original baseline estimate was understated. | 9 | This amount is lower than the baseline projection of 100% as some costs that were originally in this category are now part of the Network Build category. We have revised this budget amount in our submitted budget reprogram. | 76 | The Equipment spend amount will be below the baseline projection of 100% due to the timing of equipment payments, the timing of the ordering of the final equipment, as well as an actual cost savings in the equipment purchased versus the original baseline projection amount. So, this category will result in savings that have been rebudgeted to other categories in the budget reprogram. | 76 | The network build amount is behind the projection of 100% complete due to the previously mentioned delays. | 45 | Equipment deployment will be far below the 100% projection as pending the lifting of the suspension during this quarter, construction will be mobilized, but the equipment can only be installed as the routes are completed. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So, the roughly $500,000 in total budget is being reallocated to the Network Build category. | 2013-05-29 17:56 | 2013-05-29 17:56 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2013 | Q2 | Q2 - 2013 | 10788 | 9064 | FALSE | 94 | The project will not be completed by the end of the next quarter, so an extension request will be submitted. The final remaining dollars have been committed to complete builds to 29 CAIs, most of which will be complete by the end of the year, with the exception of the Silverton build, which won't be completed until the latter part of 2014. | 28 |  | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 96 | There will be some new equipment purchases for wireless equipment, but probably not until the 4th quarter. | 74 | Construction will resume in full in July, with much activity during this quarter. However, a lot of the activity is to complete previously started routes and laterals and to splice previously laid fiber. Most of the remaining spend will be in this category. | 30 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 0 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2013-08-28 11:02 | 2013-08-28 11:02 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2013 | Q3 | Q3 - 2013 | 11346 | 9473 | FALSE | 96 | A project extension was approved through December 31, 2014. The final remaining dollars have been committed to complete builds to 29 school district CAIs, with the wireless builds and the Silverton build not completed until their scheduled completion in 2014. | 30 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 97 | Although almost complete, there will be additional purchases for wireless equipment in 2014. | 76 | Most of the remaining spend will be in this category, although it will be reduced during the winter months. The Silverton build is expected to start in the Spring of 2014 and be completed the latter part of that year, so the budgeted money for that build won't be spent until then. | 42 | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 2013-11-22 11:06 | 2013-11-22 11:06 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2013 | Q4 | Q4 - 2013 | 11852 | 10024 | FALSE | 97 | A project extension was approved through December 31, 2014. The final remaining dollars have been will be used in this quarter to continue with the wireless build as well as to start the first steps toward the Silverton build. It's expected that we will connect five new CAIs this quarter. | 33 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although almost complete, there will be additional purchases for wireless equipment in 2014. | 76 | Most of the remaining spend will be in this category, although it will be reduced during the winter months. The Silverton build contractor will be selected and the build will begin this Spring and be completed the latter part of that year, so the budgeted money for that build won't be spent until then. | 42 | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 2014-02-20 13:37 | 2014-02-20 13:37 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2014 | Q1 | Q1 - 2014 | 12202 | 10378 | FALSE | 98 | The main objective for the remaining project spend are wireless connections to five new CAIs as well as beginning the construction on the Silverton Route. Weather permitting, significant progress will be made on both of this in the next quarter. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 97 | There are no anticipated equipment purchases during the next quarter. | 77 | Construction will begin on the Silverton route, as well as some initial payments toward the IRU in this route. There will also be two other smaller IRUs purchased from local providers. Additionally, wireless construction will continue resulting in the connection of five new CAIs. | 42 | There are no anticipated equipment deployment costs during the next quarter. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2014-05-16 12:59 | 2014-05-16 12:59 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2014 | Q2 | Q2 - 2014 | 12406 | 10598 | FALSE | 98 | The main objective for the remaining project spend is to complete the Silverton route, which has both construction and IRU elements. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Some wireless equipment will be purchased for the remaining wireless build completions. | 78 | Activities will include builds in the city of Durango and from there to Cascade Village as part of the Silverton build, work on Highway 550 and on I-25 north. | 42 | There will be some minor costs for wireless equipment deployment in the next quarter. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2014-08-13 11:33 | 2014-08-13 11:33 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2014 | Q3 | Q3 - 2014 | 12614 | 10881 | FALSE | 100 | Although the percentage complete shows 100%, there will actually be a small amount of grant money left. In addition, a contractually committed capital contribution from our Network Operator will allow us to complete the Silverton build, which will be the last grant funded route to complete. Unfortunately, due to weather we will be unable to complete this by December 31, 2014, so we will be asking for an extension to complete it in the Spring of 2015. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although only 98% of the budgeted funds will be spent in this category, all network equipment will have been purchased by December 31. | 80 | At the end of December 31, 2014, there will still be a portion of the build required to complete the Durango to Silverton route in the Spring of 2015. Additional funding will be provided by our network operator to ensure the completion of this route. | 42 | There will some minor spending to complete the wireless equipment installation which should be complete by December 31. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2014-11-24 16:02 | 2014-11-24 16:02 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2014 | Q4 | Q4 - 2014 | 12738 | 11070 | FALSE | 100 | Although the percentage complete shows 100%, there will actually be a small amount of grant money left. This will be used to complete the Custer County route. In addition, a contractually committed capital contribution from our Network Operator will allow us to complete the Silverton build, which will be the last grant funded route to complete. However, it will not be completed until the third quarter of 2015 before the grant extension expires. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although only 98% of the budgeted funds will be spent in this category, all network equipment will have been purchased by March 31. | 80 | This total category amount looks low because the category has changed as part of the approved budget reprogram, and in total the Network build category will be about 99 % complete. Construction will continue to complete the Custer County route, which is fully budgeted, and there will still be a portion of the build required to complete the Durango to Silverton route going into the summer of 2015. Additional funding will be provided by our network operator to ensure the completion of this route. | 42 | There will some minor spending to complete the wireless equipment installation for Custer County. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2015-03-06 15:31 | 2015-03-06 15:31 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2015 | Q1 | Q1 - 2015 | 12858 | 11227 | FALSE | 100 | Although the percentage complete shows 100%, there will actually be a small amount of grant money left. This will be used to complete the Custer County route. In addition, a contractually committed capital contribution from our Network Operator will allow us to complete the Silverton build, which will be the last grant funded route to complete. However, it will not be completed until the third quarter of 2015 before the grant extension expires. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although only 98% of the budgeted funds will be spent in this category, all network equipment will have been purchased by June 30. | 80 | This total category amount looks low because the category has changed as part of the approved budget reprogram, and in total the Network build category will be about 99 % complete. Construction will continue to complete the Custer County route, which is fully budgeted, and there will still be a portion of the build required to complete the Durango to Silverton route going into the summer of 2015. Additional funding will be provided by our network operator to ensure the completion of this route. | 42 | There will some minor spending to complete the wireless equipment installation for Custer County. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2015-05-29 18:38 | 2015-05-29 18:38 | 7044 | 7044 | Eagle-Net Alliance
NT11BIX5570001 | 2015 | Q2 | Q2 - 2015 | 12902 | 11283 | FALSE | 100 | The project will be completed by September 30 with no grant dollars remaining. The three open builds in Durango, Silverton and Custer County will be done by the end of the quarter. | 32 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although only 98% of the budgeted funds will be spent in this category, all network equipment will have been purchased by June 30. | 80 | This total category amount looks low because the category has changed as part of the approved budget reprogram. Construction will continue to complete the Custer County route, which is fully budgeted, and there will still be a portion of the build required to complete the Durango to Silverton route going up to the September 30 deadline. | 42 | There will some minor spending to complete the wireless equipment installation for Custer County. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 42255.6711 | 42255.6711 | 7044 | 7044 | Eagle-Net Alliance
NT12BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6360 | 5782 | FALSE | 74 | This is 26% behind our baseline and this is because of cost savings and delays in permitting and pole attachment. Zayo has requested some route changes that required a revised EA Addendum. | 0 |  | N/A | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 99 | This percentage is based on spend based on the total for both awards. This is 5% behind our baseline. Zayo is currently running way under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. | 88 | This percentage is based on spend based on the total for both awards. This is 22% behind our baseline. Zayo is currently running way under budget. | 100 | This is in line with our baseline. | 73 | This percentage is based on spend based on the total for both awards. This is 27% behind our baseline. Zayo is currently running way under budget. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 100% behind our baseline. | 2012-05-30 19:15 | 2012-05-30 19:15 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7294 | 6274 | FALSE | 74 | This is 26% behind our baseline and this is because of cost savings. | 0 | N/A | N/A | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 96 | This percentage is based on spend based on the total for both awards. This is 4% behind our baseline. Zayo is currently running under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. | 88 | This percentage is based on spend based on the total for both awards. This is 22% behind our baseline. Zayo is currently running way under budget. | 100 | This is in line with our baseline. | 73 | This percentage is based on spend based on the total for both awards. This is 27% behind our baseline. Zayo is currently running way under budget. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 100% behind our baseline. | 2012-08-31 12:32 | 2012-08-31 12:32 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8174 | 6798 | FALSE | 100 | This is based on actual spend as outlined below. | 0 | 0 | N/A | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is based on projected spend. Zayo is way under budget. | 100 | This is based on projected spend. Zayo is way under budget. | 100 | This is based on projected spend. Zayo is way under budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2012-11-30 14:50 | 2012-11-30 14:50 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570001 | 2012 | Q4 | Q4 - 2012 | 8970 | 7751 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | N/A | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-02-26 13:01 | 2013-02-26 13:03 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570001 | 2013 | Q1 | Q1 - 2013 | 10068 | 8592 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 73 | This is in line with our baseline. | 96 | This is in line with our baseline. | 84 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-06-20 18:19 | 2013-06-20 18:19 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2012 | Q1 | Q1 - 2012 | 6358 | 5781 | FALSE | 73 | This percentage is based on spend based on the total for both awards. This is 47.7% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 |  | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 100 | This is based on total dollars spent for both awards. This is 15% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | N/A | 0 | N/A | 0 | This is 38% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 93 | This percentage is based on spend based on the total for both awards. This is 55% ahead of our baseline. This is because Zayo should be ahead of our build as outlined in 2a above and will be preparing to install the equipment.. | 69 | This percentage is based on spend based on the total for both awards. This is 17% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 38% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 17% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-05-30 19:13 | 2012-05-30 19:13 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2012 | Q2 | Q2 - 2012 | 7282 | 6268 | FALSE | 68 | This percentage is based on spend based on the total for both awards. This is 17.8% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | N/A | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 100 | This is based on total dollars spent for both awards. This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is 52% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 93 | This percentage is based on spend based on the total for both awards. This is 41% ahead of our baseline. This is because Zayo should be ahead of our build as outlined in 2a above and will be preparing to install the equipment. | 71 | This percentage is based on spend based on the total for both awards. This is 19% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 52% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 17% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-08-29 17:42 | 2012-08-29 17:42 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2012 | Q3 | Q3 - 2012 | 8176 | 6799 | FALSE | 100 | This is based on the projected spend for the entire project. | 0 | 0 | N/A | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is below our baseline, because Zayo projected building some hut sites that are not required for this build. | 100 | This is based on projected spend. | 100 | This is based on projected spend. | 0 | This is because Zayo included this in our baseline but did not include it in our detailed budget. | 0 | N/A | 2012-11-30 14:53 | 2012-11-30 14:53 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2012 | Q4 | Q4 - 2012 | 8954 | 7730 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | N/A | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is below our baseline, because Zayo projected building some hut sites that are not required for this build. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline but did not include it in our detailed budget. | 0 | N/A | 2013-02-25 18:07 | 2013-02-25 18:07 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2013 | Q1 | Q1 - 2013 | 10062 | 8589 | FALSE | 95 | This is about ~1M under our detailed budget. | 0 |  | This is in line with our detailed budget. | 100 | This is in line with our detailed budget. Zayo plans to move funds from construction to cover the variance from last quarter. | 100 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 9 | This is in line with our detailed budget. | 92 | This is about ~1M under our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 2013-06-18 16:38 | 2013-06-18 16:38 | 6743 | 6743 | Zayo Group, LLC
NT12BIX5570002 | 2013 | Q2 | Q2 - 2013 | 12730 | 11055 | FALSE | 100 | Project is 12% under budget based on actual spend. | 0 | N/A | N/A | 100 | Complete; costs included in 2c. | 100 | Complete; actuals at 156% of budget. | 100 | Complete: costs included in 2c. | 100 | Complete; costs included in 2c. | 100 | Complete; costs included in 2h. | 100 | Complete; actuals at 13.4% of budget | 100 | Completed; actuals at 98.3% of budget. | 100 | Completed; costs included n 2h. | 0 | N/A - It is a dark fiber network only. | 2015-02-26 14:17 | 2015-02-26 14:17 | 7919 | 7919 | Zayo Group, LLC

## CCI_Expenditures
Award_Num | ProjectType_Cd | Year_Desc | Quarter_Cd | YearQuarter | TotCostPlan_Equipmnt_Amt | MatchFundPlan_Equipmnt_Amt | FedFundPlan_Equipmnt_Amt | TotCostActl_Equipmnt_Amt | MatchFundActl_Equipmnt_Amt | FedFundActl_Equipmnt_Amt | TotCostAntcp_Equipmnt_Amt | MatchFundAntcp_Equipmnt_Amt | FedFundAntcp_Equipmnt_Amt | TotCostPlan_Constructn_Amt | MatchFundPlan_Constructn_Amt | FedFundPlan_Constructn_Amt | TotCostActl_Constructn_Amt | MatchFundActl_Constructn_Amt | FedFundActl_Constructn_Amt | TotCostAntcp_Constructn_Amt | MatchFundAntcp_Constructn_Amt | FedFundAntcp_Constructn_Amt | TotCostPlan_LegalExp_Amt | MatchFundPlan_LegalExp_Amt | FedFundPlan_LegalExp_Amt | TotCostActl_LegalExp_Amt | MatchFundActl_LegalExp_Amt | FedFundActl_LegalExp_Amt | TotCostAntcp_LegalExp_Amt | MatchFundAntcp_LegalExp_Amt | FedFundAntcp_LegalExp_Amt | TotCostPlan_LandApprsl_Amt | MatchFundPlan_LandApprsl_Amt | FedFundPlan_LandApprsl_Amt | TotCostActl_LandApprsl_Amt | MatchFundActl_LandApprsl_Amt | FedFundActl_LandApprsl_Amt | TotCostAntcp_LandApprsl_Amt | MatchFundAntcp_LandApprsl_Amt | FedFundAntcp_LandApprsl_Amt | TotCostPlan_RelocExp_Amt | MatchFundPlan_RelocExp_Amt | FedFundPlan_RelocExp_Amt | TotCostActl_RelocExp_Amt | MatchFundActl_RelocExp_Amt | FedFundActl_RelocExp_Amt | TotCostAntcp_RelocExp_Amt | MatchFundAntcp_RelocExp_Amt | FedFundAntcp_RelocExp_Amt | TotCostPlan_ArchFee_Amt | MatchFundPlan_ArchFee_Amt | FedFundPlan_ArchFee_Amt | TotCostActl_ArchFee_Amt | MatchFundActl_ArchFee_Amt | FedFundActl_ArchFee_Amt | TotCostAntcp_ArchFee_Amt | MatchFundAntcp_ArchFee_Amt | FedFundAntcp_ArchFee_Amt | TotCostPlan_OtherArchFee_Amt | MatchFundPlan_OtherArchFee_Amt | FedFundPlan_OtherArchFee_Amt | TotCostActl_OtherArchFee_Amt | MatchFundActl_OtherArchFee_Amt | FedFundActl_OtherArchFee_Amt | TotCostAntcp_OtherArchFee_Amt | MatchFundAntcp_OtherArchFee_Amt | FedFundAntcp_OtherArchFee_Amt | TotCostPlan_ProjInspFee_Amt | MatchFundPlan_ProjInspFee_Amt | FedFundPlan_ProjInspFee_Amt | TotCostActl_ProjInspFee_Amt | MatchFundActl_ProjInspFee_Amt | FedFundActl_ProjInspFee_Amt | TotCostAntcp_ProjInspFee_Amt | MatchFundAntcp_ProjInspFee_Amt | FedFundAntcp_ProjInspFee_Amt | TotCostPlan_SiteWork_Amt | MatchFundPlan_SiteWork_Amt | FedFundPlan_SiteWork_Amt | TotCostActl_SiteWork_Amt | MatchFundActl_SiteWork_Amt | FedFundActl_SiteWork_Amt | TotCostAntcp_SiteWork_Amt | MatchFundAntcp_SiteWork_Amt | FedFundAntcp_SiteWork_Amt | TotCostPlan_Demolitn_Amt | MatchFundPlan_Demolitn_Amt | FedFundPlan_Demolitn_Amt | TotCostActl_Demolitn_Amt | MatchFundActl_Demolitn_Amt | FedFundActl_Demolitn_Amt | TotCostAntcp_Demolitn_Amt | MatchFundAntcp_Demolitn_Amt | FedFundAntcp_Demolitn_Amt | TotCostPlan_OtherMisc_Amt | MatchFundPlan_OtherMisc_Amt | FedFundPlan_OtherMisc_Amt | TotCostActl_OtherMisc_Amt | MatchFundActl_OtherMisc_Amt | FedFundActl_OtherMisc_Amt | TotCostAntcp_OtherMisc_Amt | MatchFundAntcp_OtherMisc_Amt | FedFundAntcp_OtherMisc_Amt | TotCostPlan_DirCh_SubTot_Amt | MatchFundPlan_DirCh_SubTot_Amt | FedFundPlan_DirCh_SubTot_Amt | TotCostActl_DirCh_SubTot_Amt | MatchFundActl_DirCh_SubTot_Amt | FedFundActl_DirCh_SubTot_Amt | TotCostAntcp_DirCh_SubTot_Amt | MatchFundAntcp_DirCh_SubTot_Amt | FedFundAntcp_DirCh_SubTot_Amt | TotCostPlan_Total_Amt | MatchFundPlan_Total_Amt | FedFundPlan_Total_Amt | TotCostActl_Total_Amt | MatchFundActl_Total_Amt | FedFundActl_Total_Amt | TotCostAntcp_Total_Amt | MatchFundAntcp_Total_Amt | FedFundAntcp_Total_Amt | BudgetIncome_Amt | ToDateIncome_Amt | Recipient
NT10BIX5570003 | INF | 2010 | Q3 | Q3 - 2010 | 3513857 | 702770 | 2811087 | 1936723 | 387345 | 1549378 | 2120000 | 424000 | 1696000 | 16511000 | 3302200 | 13208800 | 1458032 | 291606 | 1166426 | 3000000 | 600000 | 2400000 | 75000 | 15000 | 60000 | 30848 | 6170 | 24678 | 35000 | 7000 | 28000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 870673 | 174135 | 696538 | 1100000 | 220000 | 890000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276343 | 1105374 | 78977 | 15795 | 63182 | 90000 | 18000 | 72000 | 25715303 | 5143059 | 20572244 | 4377253 | 875451 | 3501802 | 6350000 | 1270000 | 5090000 | 25715303 | 5143059 | 20572244 | 4377253 | 875451 | 3501802 | 6350000 | 1270000 | 5090000 | 0 | 0 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2010 | Q4 | Q4 - 2010 | 3513850 | 702770 | 2811080 | 2186972 | 437394 | 1749578 | 3000000 | 600000 | 2400000 | 16511000 | 3302200 | 13208800 | 3292868 | 658574 | 2634294 | 4000000 | 800000 | 3200000 | 75000 | 15000 | 60000 | 66332 | 13266 | 53066 | 70000 | 14000 | 56000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 2000 | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1124860 | 224972 | 899888 | 1750000 | 350000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381740 | 276343 | 1105370 | 151379 | 30276 | 121103 | 182000 | 36400 | 145600 | 25715319 | 5143059 | 20572233 | 6824411 | 1364882 | 5459529 | 9004000 | 1800800 | 7203200 | 25715319 | 5143059 | 20572233 | 6824411 | 1364882 | 5459529 | 9004000 | 1800800 | 7203200 | 0 | 0 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2011 | Q1 | Q1 - 2011 | 3513857 | 702771 | 2811086 | 2197168 | 439434 | 1757734 | 2800000 | 560000 | 2240000 | 16511000 | 3302200 | 13208800 | 3533768 | 706752 | 2827016 | 4300000 | 860000 | 3440000 | 75000 | 15000 | 60000 | 101758 | 20352 | 81406 | 140000 | 28000 | 112000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1229983 | 245997 | 983986 | 1600000 | 320000 | 1280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 169449 | 33890 | 135559 | 185000 | 37000 | 148000 | 25715303 | 5143061 | 20572242 | 7234126 | 1446825 | 5787301 | 9125000 | 1825000 | 7300000 | 25715303 | 5143061 | 20572242 | 7234126 | 1446825 | 5787301 | 9125000 | 1825000 | 7300000 | 0 | 0 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2011 | Q2 | Q2 - 2011 | 3513857 | 702771 | 2811086 | 2507102 | 501420 | 2005682 | 3900000 | 780000 | 3120000 | 16511000 | 3302200 | 13208800 | 5919391 | 1183878 | 4735513 | 8500000 | 1700000 | 6800000 | 75000 | 15000 | 60000 | 123835 | 24767 | 99068 | 160000 | 32000 | 128000 | 700000 | 140000 | 560000 | 31086 | 6217 | 24869 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1543591 | 308718 | 1234873 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 318556 | 63711 | 254845 | 350000 | 70000 | 280000 | 25715303 | 5143061 | 20572242 | 10443561 | 2088711 | 8354850 | 15210000 | 3042000 | 12168000 | 25715303 | 5143061 | 20572242 | 10443561 | 2088711 | 8354850 | 15210000 | 3042000 | 12168000 | 0 | 54549 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2011 | Q3 | Q3 - 2011 | 3513857 | 702771 | 2811086 | 3473565 | 694713 | 2778852 | 5500000 | 1100000 | 4400000 | 16511000 | 3302200 | 13208800 | 9161567 | 1832313 | 7329254 | 11000000 | 2200000 | 8800000 | 75000 | 15000 | 60000 | 123835 | 24767 | 99068 | 125000 | 25000 | 100000 | 700000 | 140000 | 560000 | 317329 | 63466 | 253863 | 425000 | 85000 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1817839 | 363568 | 1454271 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 370890 | 74178 | 296712 | 420000 | 84000 | 336000 | 25715303 | 5143061 | 20572242 | 15265025 | 3053005 | 12212020 | 19470000 | 3894000 | 15576000 | 25715303 | 5143061 | 20572242 | 15265025 | 3053005 | 12212020 | 19470000 | 3894000 | 15576000 | 0 | 101966 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2011 | Q4 | Q4 - 2011 | 3513857 | 702771 | 2811086 | 4279896 | 855979 | 3423917 | 4300000 | 860000 | 3440000 | 16511000 | 3302200 | 13208800 | 12218619 | 2443724 | 9774895 | 14000000 | 2800000 | 11200000 | 75000 | 15000 | 60000 | 128320 | 25664 | 102656 | 140000 | 28000 | 112000 | 700000 | 140000 | 560000 | 512980 | 102596 | 410384 | 550000 | 110000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 2020777 | 404156 | 1616621 | 2500000 | 500000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 400942 | 80188 | 320754 | 450000 | 90000 | 360000 | 25715303 | 5143061 | 20572242 | 19561534 | 3912307 | 15649227 | 21940000 | 4388000 | 17552000 | 25715303 | 5143061 | 20572242 | 19561534 | 3912307 | 15649227 | 21940000 | 4388000 | 17552000 | 0 | 216025 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2012 | Q1 | Q1 - 2012 | 3513857 | 702771 | 2811086 | 4578942 | 915788 | 3663154 | 4670000 | 934000 | 3736000 | 16511000 | 3302200 | 13208800 | 13190984 | 2638197 | 10552787 | 14800000 | 2960000 | 11840000 | 75000 | 15000 | 60000 | 129855 | 25971 | 103884 | 131000 | 26200 | 104800 | 700000 | 140000 | 560000 | 512980 | 102596 | 410384 | 520000 | 104000 | 416000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 2125653 | 425131 | 1700522 | 2150000 | 430000 | 1720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 410166 | 82033 | 328133 | 450000 | 90000 | 360000 | 25715303 | 5143061 | 20572242 | 20948580 | 4189716 | 16758864 | 22721000 | 4544200 | 18176800 | 25715303 | 5143061 | 20572242 | 20948580 | 4189716 | 16758864 | 22721000 | 4544200 | 18176800 | 0 | 333405 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2012 | Q2 | Q2 - 2012 | 4670270 | 934054 | 3736216 | 4632892 | 926578 | 3706314 | 4670270 | 934054 | 3736216 | 17558230 | 3511646 | 14046584 | 14609432 | 2921886 | 11687546 | 16000000 | 3200000 | 12800000 | 150000 | 30000 | 120000 | 129913 | 25983 | 103930 | 131000 | 26200 | 104800 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2170610 | 434122 | 1736488 | 2173894 | 434779 | 1739115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 442623 | 88525 | 354098 | 500000 | 100000 | 400000 | 25715303 | 5143061 | 20572242 | 22498450 | 4499690 | 17998760 | 23988144 | 4797629 | 19190515 | 25715303 | 5143061 | 20572242 | 22498450 | 4499690 | 17998760 | 23988144 | 4797629 | 19190515 | 0 | 558600 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2012 | Q3 | Q3 - 2012 | 4670270 | 934054 | 3736216 | 4634383 | 926877 | 3707507 | 4670270 | 934054 | 3736216 | 17558230 | 3511646 | 14046584 | 15392367 | 3078473 | 12313894 | 17625034 | 3525007 | 14100027 | 150000 | 30000 | 120000 | 132484 | 26497 | 105987 | 141984 | 28397 | 113587 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2193075 | 438615 | 1754459 | 2198075 | 439615 | 1758460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 454984 | 90997 | 363987 | 507724 | 101544 | 406180 | 25715303 | 5143061 | 20572242 | 23320273 | 4664055 | 18656218 | 25656067 | 5131213 | 20524854 | 25715303 | 5143061 | 20572242 | 23320273 | 4664055 | 18656218 | 25656067 | 5131213 | 20524854 | 0 | 687905 | South Dakota Network, LLC
NT10BIX5570003 | INF | 2012 | Q4 | Q4 - 2012 | 4670270 | 934054 | 3736216 | 4634384 | 926877 | 3707507 | 4634383 | 926876 | 3707507 | 17558230 | 3511646 | 14046584 | 17843886 | 3667055 | 14176831 | 17843886 | 3667055 | 14176831 | 150000 | 30000 | 120000 | 132484 | 26497 | 105987 | 132484 | 26497 | 105987 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2211716 | 442342 | 1769374 | 2211717 | 442343 | 1769374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 502699 | 100540 | 402159 | 502699 | 100540 | 402159 | 25715303 | 5143061 | 20572242 | 25838149 | 5265907 | 20572242 | 25838149 | 5265907 | 20572242 | 25715303 | 5143061 | 20572242 | 25838149 | 5265907 | 20572242 | 25838149 | 5265907 | 20572242 | 0 | 770923 | South Dakota Network, LLC
NT10BIX5570004 | INF | 2010 | Q3 | Q3 - 2010 | 14660971 | 2932194 | 11728776 | 58508 | 11702 | 46806 | 507860 | 101572 | 406288 | 269450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628750 | 325750 | 1303000 | 428394 | 85679 | 342715 | 884994 | 176999 | 707995 | 4110896 | 822179 | 3288717 | 28500 | 5700 | 22800 | 43500 | 8700 | 34800 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 111400 | 445600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 103410 | 413640 | 0 | 0 | 0 | 0 | 0 | 0 | 20113922 | 4022784 | 16091137 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 37500 | 7500 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42145539 | 8375217 | 33500870 | 515402 | 103081 | 412321 | 1586354 | 317271 | 1269083 | 42145539 | 8375217 | 33500870 | 515402 | 103081 | 412321 | 1586354 | 317271 | 1269083 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2010 | Q4 | Q4 - 2010 | 14660970 | 2932194 | 11728776 | 131919 | 26384 | 105535 | 1000000 | 200000 | 800000 | 269450 | 0 | 0 | 21432 | 4286 | 17146 | 0 | 0 | 0 | 1628750 | 325750 | 1303000 | 741282 | 148256 | 593026 | 250000 | 50000 | 200000 | 4110896 | 822179 | 3288717 | 35700 | 7140 | 28560 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 111400 | 445600 | 5723 | 1145 | 4578 | 125000 | 25000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 103410 | 413640 | 0 | 0 | 0 | 0 | 0 | 0 | 20113922 | 4022784 | 16091137 | 96056 | 19211 | 76845 | 1000000 | 200000 | 800000 | 37500 | 7500 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42145538 | 8375217 | 33500870 | 1032112 | 206422 | 825690 | 2375000 | 475000 | 1900000 | 42145538 | 8375217 | 33500870 | 1032112 | 206422 | 825690 | 2375000 | 475000 | 1900000 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2011 | Q1 | Q1 - 2011 | 14660971 | 3057253 | 11603718 | 415485 | 83097 | 332388 | 3120247 | 624049 | 2496198 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 41432 | 8286 | 33146 | 1628750 | 339643 | 1289107 | 976968 | 195394 | 781575 | 1219010 | 243802 | 975208 | 4110896 | 857245 | 3253651 | 43200 | 8640 | 34560 | 50200 | 10040 | 40160 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 116151 | 440849 | 5723 | 1145 | 4578 | 10723 | 2145 | 8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 20113922 | 4194357 | 15919565 | 225116 | 45023 | 180092 | 411268 | 82254 | 329014 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 0 | 0 | 0 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 1687924 | 337585 | 1350339 | 4902880 | 980576 | 3922304 | 42314349 | 8823812 | 33490537 | 1687924 | 337585 | 1350339 | 4902880 | 980576 | 3922304 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2011 | Q2 | Q2 - 2011 | 14660971 | 3057253 | 11603718 | 1622320 | 324464 | 1297856 | 8750000 | 1750000 | 7000000 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 31500 | 6300 | 25200 | 1628750 | 339643 | 1289107 | 1146587 | 229318 | 917269 | 1500000 | 300000 | 1200000 | 4110896 | 857245 | 3253651 | 86081 | 17216 | 68865 | 266081 | 53216 | 212865 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 557000 | 116151 | 440849 | 5723 | 1145 | 4578 | 25000 | 5000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 20000 | 5000 | 20000 | 20113922 | 4194357 | 15919565 | 541697 | 108339 | 433358 | 2833923 | 566785 | 2267138 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 3423840 | 684768 | 2739072 | 13456504 | 2692301 | 10769203 | 42314349 | 8823812 | 33490537 | 3423840 | 684768 | 2739072 | 13456504 | 2692301 | 10769203 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2011 | Q3 | Q3 - 2011 | 14660971 | 3057253 | 11603718 | 7748777 | 1549756 | 6199021 | 11902121 | 2380424 | 9521697 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 224450 | 44890 | 179560 | 1628750 | 339643 | 1289107 | 1376831 | 275366 | 1101465 | 1550730 | 310146 | 1240584 | 4110896 | 857245 | 3253651 | 98188 | 19638 | 78550 | 4589796 | 917959 | 3671837 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 557000 | 116151 | 440849 | 6051 | 1210 | 4841 | 445694 | 89139 | 356555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 486500 | 97300 | 389200 | 20113922 | 4194357 | 15919565 | 3196245 | 639249 | 2556996 | 8894859 | 1778972 | 7115887 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 37500 | 7500 | 30000 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 12447524 | 2489505 | 9958019 | 28381650 | 5676330 | 22705320 | 42314349 | 8823812 | 33490537 | 12447524 | 2489505 | 9958019 | 28381650 | 5676330 | 22705320 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2011 | Q4 | Q4 - 2011 | 14660971 | 3057253 | 11603718 | 13034983 | 2632865 | 10402118 | 13504983 | 2683331 | 10803986 | 269450 | 56188 | 213262 | 101266 | 20454 | 80812 | 153488 | 30698 | 122790 | 1628750 | 339643 | 1289107 | 1604219 | 323985 | 1280234 | 1936568 | 387314 | 1549254 | 4110896 | 857245 | 3253651 | 4072706 | 863500 | 3209206 | 4233290 | 863500 | 3386632 | 250000 | 52133 | 197867 | 13187 | 2664 | 10524 | 49517 | 9903 | 39614 | 557000 | 116151 | 440849 | 54647 | 11038 | 43609 | 357589 | 71518 | 286071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4283 | 16920 | 26203 | 5241 | 20962 | 20113922 | 4194357 | 15919565 | 8155671 | 1582870 | 6572801 | 11251597 | 2250319 | 9001278 | 37500 | 7820 | 29680 | 11000 | 2222 | 8778 | 16000 | 3200 | 12800 | 168810 | 35202 | 133608 | 207525 | 41917 | 165608 | 207525 | 41917 | 166020 | 42314349 | 8823812 | 33490537 | 27276407 | 5485798 | 21790610 | 31736760 | 6346941 | 25389407 | 42314349 | 8823812 | 33490537 | 27276407 | 5485798 | 21790610 | 31736760 | 6346941 | 25389407 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2012 | Q1 | Q1 - 2012 | 14660971 | 3057253 | 11603718 | 13428633 | 2682441 | 10746192 | 14243985 | 2848797 | 11395188 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 262396 | 52479 | 209917 | 1628750 | 339643 | 1289107 | 1715640 | 343128 | 1372512 | 2138995 | 427799 | 1711196 | 4110896 | 857245 | 3253651 | 4277806 | 863500 | 3414306 | 4576603 | 915321 | 3661282 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 73668 | 14734 | 58934 | 557000 | 116151 | 440849 | 79009 | 15802 | 63207 | 514242 | 102848 | 411393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4241 | 16962 | 28203 | 5641 | 22562 | 20113922 | 4194357 | 15919565 | 8512930 | 1697932 | 6814998 | 13630013 | 2726003 | 10904011 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 28373791 | 5674758 | 22699033 | 35686630 | 7137327 | 28549303 | 42314349 | 8823812 | 33490537 | 28373791 | 5674758 | 22699033 | 35686630 | 7137327 | 28549303 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2012 | Q2 | Q2 - 2012 | 14660971 | 3057253 | 11603718 | 14137676 | 2824250 | 11313426 | 14435596 | 2883834 | 11551762 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 118746 | 23749 | 94997 | 1628750 | 339643 | 1289107 | 1875266 | 375053 | 1500213 | 2527765 | 505553 | 2022212 | 4110896 | 857245 | 3253651 | 4434271 | 894793 | 3539478 | 4596518 | 927242 | 3669276 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 32579 | 6516 | 26063 | 557000 | 116151 | 440849 | 117410 | 23482 | 93928 | 370411 | 74082 | 296327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4241 | 16962 | 21203 | 4241 | 16962 | 20113922 | 4194357 | 15919565 | 10721455 | 2139637 | 8581818 | 16609509 | 3317249 | 13292262 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 31645851 | 6329170 | 25316681 | 38930852 | 7786171 | 31144681 | 42314349 | 8823812 | 33490537 | 31645851 | 6329170 | 25316681 | 38930852 | 7786171 | 31144681 | 0 | 0 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2012 | Q3 | Q3 - 2012 | 14660971 | 3057253 | 11603718 | 14499344 | 2896583 | 11602761 | 16270387 | 3392864 | 12877523 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 209902 | 43771 | 166131 | 1628750 | 339643 | 1289107 | 2140994 | 428199 | 1712795 | 2686025 | 560117 | 2125908 | 4110896 | 857245 | 3253651 | 5867039 | 1181347 | 4685692 | 5997692 | 1250699 | 4746993 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 21625 | 4510 | 17116 | 557000 | 116151 | 440849 | 181355 | 36271 | 145084 | 290257 | 60527 | 229730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 20113922 | 4194357 | 15919565 | 13271019 | 2649550 | 10621469 | 16546688 | 3452969 | 13093718 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 36371569 | 7274314 | 29097255 | 42314349 | 8823812 | 33490537 | 42314349 | 8823812 | 33490537 | 36371569 | 7274314 | 29097255 | 42314349 | 8823812 | 33490537 | 0 | 188730 | North Georgia Network Cooperative, Inc.
NT10BIX5570004 | INF | 2012 | Q4 | Q4 - 2012 | 15460345 | 3092069 | 12368276 | 15359463 | 3071893 | 12287570 | 15359963 | 3071993 | 12287970 | 147875 | 29575 | 118300 | 125729 | 25146 | 100583 | 136929 | 27386 | 109543 | 2731699 | 546339 | 2185360 | 2517847 | 503569 | 2014278 | 2593847 | 518768 | 2075079 | 6033034 | 1206606 | 4826428 | 6064642 | 1212928 | 4851714 | 6065117 | 1213023 | 4852094 | 22589 | 4518 | 18071 | 22589 | 4518 | 18071 | 22589 | 4518 | 18071 | 277062 | 55413 | 221649 | 271854 | 54371 | 217483 | 338354 | 67671 | 270683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 16880394 | 3376079 | 13504315 | 16811131 | 3362226 | 13448905 | 17036199 | 3407240 | 13628959 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 225925 | 45185 | 180740 | 225925 | 45185 | 180740 | 225925 | 45185 | 180740 | 41863171 | 8372634 | 33490537 | 41483428 | 8296686 | 33186742 | 41863171 | 8372634 | 33490537 | 41863171 | 8372634 | 33490537 | 41483428 | 8296686 | 33186742 | 41863171 | 8372634 | 33490537 | 0 | 367490 | North Georgia Network Cooperative, Inc.
NT10BIX5570009 | INF | 2010 | Q3 | Q3 - 2010 | 5485955 | 1097192 | 4388763 | 156 | 31 | 125 | 548751 | 109750 | 439001 | 25357463 | 5071492 | 20285971 | 0 | 0 | 0 | 507149 | 101430 | 405719 | 422027 | 84405 | 337622 | 176369 | 35273 | 141096 | 202512 | 40502 | 162010 | 676200 | 135240 | 540959 | 156546 | 31309 | 125237 | 596076 | 119215 | 476861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 117603 | 23521 | 94082 | 1803778 | 360756 | 1443022 | 1424305 | 284861 | 1139444 | 97158 | 19432 | 77726 | 243205 | 48641 | 194564 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 169690 | 33938 | 135752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 22699 | 4540 | 18159 | 42699 | 8540 | 34159 | 41611527 | 8322306 | 33289222 | 570531 | 114106 | 456425 | 4113860 | 822772 | 3291088 | 41611527 | 8322306 | 33289222 | 570531 | 114106 | 456425 | 4113860 | 822772 | 3291088 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2010 | Q4 | Q4 - 2010 | 5485955 | 1097191 | 4388764 | 0 | 0 | 0 | 1645944 | 329189 | 1316755 | 25357463 | 5071493 | 20285970 | 175546 | 35109 | 140437 | 2539621 | 507924 | 2031697 | 422027 | 84405 | 337622 | 166701 | 33340 | 133361 | 229043 | 45809 | 183234 | 676199 | 135240 | 540959 | 464205 | 92841 | 371364 | 676199 | 135240 | 540959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 400953 | 80191 | 320762 | 2873826 | 574765 | 2299061 | 1424305 | 284861 | 1139444 | 253419 | 50684 | 202735 | 247923 | 49585 | 198338 | 1690497 | 338099 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339379 | 1357518 | 0 | 0 | 0 | 343342 | 68668 | 274674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30966 | 123861 | 72369 | 14474 | 57895 | 88459 | 17692 | 70767 | 41611526 | 8322305 | 33289221 | 1533193 | 306639 | 1226554 | 8644357 | 1728872 | 6915485 | 41611526 | 8322305 | 33289221 | 1533193 | 306639 | 1226554 | 8644357 | 1728872 | 6915485 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2011 | Q1 | Q1 - 2011 | 5485955 | 1097192 | 4388763 | 542069 | 108414 | 433655 | 987472 | 197494 | 789978 | 25357463 | 5071492 | 20285971 | 582841 | 116568 | 466273 | 1081918 | 216384 | 865535 | 422027 | 84405 | 337622 | 136710 | 27342 | 109368 | 159496 | 31899 | 127596 | 676199 | 135240 | 540959 | 1166334 | 233267 | 933067 | 1169824 | 233965 | 935859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 953946 | 190789 | 763156 | 1005946 | 201189 | 804756 | 1424305 | 284861 | 1139444 | 154417 | 30883 | 123533 | 180153 | 36031 | 144122 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 84935 | 16987 | 67948 | 99091 | 19818 | 79273 | 41611526 | 8322306 | 33289222 | 3621252 | 724250 | 2897000 | 4683900 | 936780 | 3747119 | 41611526 | 8322306 | 33289222 | 3621252 | 724250 | 2897000 | 4683900 | 936780 | 3747119 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2011 | Q2 | Q2 - 2011 | 5485955 | 1097192 | 4388763 | 825184 | 165037 | 660147 | 1601979 | 320396 | 1281583 | 25357463 | 5071492 | 20285971 | 2148789 | 429758 | 1719031 | 6016901 | 1203380 | 4813521 | 422027 | 84405 | 337622 | 210923 | 42185 | 168738 | 246107 | 49221 | 196885 | 676199 | 135240 | 540959 | 1324011 | 264802 | 1059209 | 1325702 | 265140 | 1060561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1042322 | 208464 | 833858 | 1652495 | 330499 | 1321996 | 1424305 | 284861 | 1139444 | 112720 | 22544 | 90176 | 331318 | 66264 | 265054 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 281749 | 56350 | 225400 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 282816 | 56563 | 226253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 128957 | 25791 | 103166 | 150450 | 30090 | 120360 | 41611526 | 8322306 | 33289222 | 5792906 | 1158581 | 4634325 | 11889517 | 2377903 | 9511613 | 41611526 | 8322306 | 33289222 | 5792906 | 1158581 | 4634325 | 11889517 | 2377903 | 9511613 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2011 | Q3 | Q3 - 2011 | 5485955 | 1097192 | 4388763 | 825184 | 165037 | 660147 | 1712847 | 342573 | 1370293 | 25357463 | 5071492 | 20285971 | 5116034 | 1023207 | 4092828 | 17686214 | 3537243 | 14148971 | 422027 | 84405 | 337622 | 246967 | 49393 | 197573 | 266832 | 53366 | 213466 | 676199 | 135240 | 540959 | 1604156 | 320831 | 1283325 | 1609156 | 321831 | 1287325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1209895 | 241979 | 967916 | 2038706 | 407741 | 163095 | 1424305 | 284861 | 1139444 | 199857 | 39972 | 159885 | 509677 | 101935 | 407741 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 1545 | 309 | 1236 | 47199 | 9440 | 37759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 134600 | 26920 | 107680 | 266832 | 53366 | 213466 | 41611526 | 8322306 | 33289222 | 9338238 | 1867648 | 7470590 | 24137463 | 4827495 | 17842116 | 41611526 | 8322306 | 33289222 | 9338238 | 1867648 | 7470590 | 24137463 | 4827495 | 17842116 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2011 | Q4 | Q4 - 2011 | 5485955 | 1097192 | 4388763 | 1123892 | 224778 | 899114 | 1712867 | 342573 | 1370294 | 25357463 | 5071492 | 20285971 | 9744308 | 1948862 | 7795446 | 18864952 | 3772990 | 15091961 | 422027 | 84405 | 337622 | 264893 | 52978 | 211915 | 296480 | 59296 | 237184 | 676199 | 135240 | 540959 | 1797399 | 359480 | 1437919 | 1847338 | 369468 | 1477870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1323164 | 264633 | 1058531 | 2463347 | 492669 | 1970678 | 1424305 | 284861 | 1139444 | 298273 | 59655 | 238618 | 615837 | 123167 | 492670 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 1545 | 309 | 1236 | 96208 | 19242 | 76966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 244426 | 48885 | 195541 | 247653 | 49531 | 198122 | 41611526 | 8322306 | 33289222 | 14797900 | 2959580 | 11838320 | 26144682 | 5228936 | 20915745 | 41611526 | 8322306 | 33289222 | 14797900 | 2959580 | 11838320 | 26144682 | 5228936 | 20915745 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2012 | Q1 | Q1 - 2012 | 5485955 | 1097192 | 4388763 | 2545586 | 509117 | 2036469 | 3570430 | 714086 | 2856344 | 25357463 | 5071492 | 20285971 | 11302052 | 2260410 | 9041642 | 16997686 | 3399537 | 13598149 | 422027 | 84405 | 337622 | 278384 | 55677 | 222707 | 304291 | 60858 | 243433 | 676199 | 135240 | 540959 | 1822357 | 364472 | 1457885 | 1859775 | 371955 | 1487820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1713394 | 342679 | 1370715 | 2702571 | 540514 | 2162057 | 1424305 | 284861 | 1139444 | 374950 | 74990 | 299960 | 675643 | 135129 | 540514 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 125745 | 25149 | 100596 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 21419 | 4284 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 284801 | 56960 | 227841 | 302861 | 60572 | 242289 | 41611526 | 8322306 | 33289220 | 18330209 | 3666042 | 14664167 | 26560421 | 5312084 | 21248337 | 41611526 | 8322306 | 33289220 | 18330209 | 3666042 | 14664167 | 26560421 | 5312084 | 21248337 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2012 | Q2 | Q2 - 2012 | 5485955 | 1097192 | 4388763 | 3661640 | 732328 | 2929312 | 4967280 | 993456 | 3973824 | 25357463 | 5071492 | 20285971 | 14411518 | 2882304 | 11529214 | 23884620 | 4776924 | 19107696 | 422027 | 84405 | 337622 | 282459 | 56492 | 225967 | 340728 | 68146 | 272582 | 676199 | 135240 | 540959 | 1871520 | 374304 | 1497216 | 1919926 | 383985 | 1535941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1881506 | 376301 | 1505205 | 3801966 | 760393 | 3041573 | 1424305 | 284861 | 1139444 | 417293 | 83459 | 333835 | 950491 | 190098 | 760393 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 154952 | 30990 | 123962 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 21419 | 4284 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 287452 | 57490 | 229961 | 292153 | 58431 | 233722 | 41611526 | 8322306 | 33289220 | 22822073 | 4564415 | 18257658 | 36333535 | 7266707 | 29066828 | 41611526 | 8322306 | 33289220 | 22822073 | 4564415 | 18257658 | 36333535 | 7266707 | 29066828 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2012 | Q3 | Q3 - 2012 | 5485955 | 1097192 | 4388763 | 5032749 | 1006550 | 4026199 | 5485955 | 1097191 | 4388764 | 25357463 | 5071492 | 20285971 | 19451910 | 3890382 | 15561528 | 25357463 | 5071493 | 20285970 | 422027 | 84405 | 337622 | 282459 | 56492 | 225967 | 400926 | 80185 | 320741 | 676199 | 135240 | 540959 | 1937131 | 387426 | 1549705 | 2037131 | 407426 | 1629705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1970122 | 394024 | 1576098 | 3173453 | 634691 | 2538763 | 1424305 | 284861 | 1139444 | 605456 | 121091 | 484365 | 1424305 | 284861 | 1139444 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 1690497 | 338099 | 1352398 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 1696897 | 339379 | 1357518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 303796 | 60759 | 243037 | 323798 | 64760 | 259037 | 41611526 | 8322306 | 33289220 | 29592308 | 5918461 | 23673847 | 41590425 | 8318085 | 33272340 | 41611526 | 8322306 | 33289220 | 29592308 | 5918461 | 23673847 | 41590425 | 8318085 | 33272340 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2012 | Q4 | Q4 - 2012 | 5485955 | 1097192 | 4388763 | 5588992 | 1117798 | 4471193 | 5640511 | 1128102 | 4512409 | 25357463 | 5071492 | 20285971 | 26521466 | 5304293 | 21217173 | 27147862 | 5429572 | 21718289 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 302876 | 60575 | 242301 | 676199 | 135240 | 540959 | 1956183 | 391237 | 1564946 | 1956183 | 391237 | 1564946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2036199 | 407240 | 1628959 | 4808102 | 961620 | 3846481 | 1424305 | 284861 | 1139444 | 813134 | 162627 | 650507 | 1194511 | 238902 | 955609 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 184160 | 36832 | 147328 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 7140 | 1428 | 5712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 354273 | 70855 | 283419 | 370181 | 74038 | 296143 | 41611526 | 8322306 | 33289220 | 37566588 | 7513318 | 30053270 | 41611526 | 8322306 | 33289218 | 41611526 | 8322306 | 33289220 | 37566588 | 7513318 | 30053270 | 41611526 | 8322306 | 33289218 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2013 | Q1 | Q1 - 2013 | 5485955 | 1097192 | 4388763 | 5757525 | 1151505 | 4606020 | 5757525 | 1151505 | 4606020 | 25357463 | 5071492 | 20285971 | 29158902 | 5831780 | 23327122 | 29915349 | 5983070 | 23932280 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 291325 | 58265 | 233060 | 676199 | 135240 | 540959 | 1486230 | 297246 | 1188984 | 1486230 | 297246 | 1188984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2077535 | 415507 | 1662028 | 2283919 | 456784 | 1827135 | 1424305 | 284861 | 1139444 | 842147 | 168429 | 673717 | 842147 | 168429 | 673717 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 182630 | 36526 | 146104 | 1696897 | 339380 | 1357517 | 10858 | 2172 | 8686 | 10858 | 2172 | 8686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 366340 | 73268 | 293073 | 370777 | 74156 | 296622 | 41611526 | 8322306 | 33289220 | 39988738 | 7997747 | 31990991 | 41140760 | 8228153 | 32912608 | 41611526 | 8322306 | 33289220 | 39988738 | 7997747 | 31990991 | 41140760 | 8228153 | 32912608 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2013 | Q2 | Q2 - 2013 | 5485955 | 1097192 | 4388763 | 5757525 | 1151505 | 4606020 | 5757525 | 1151505 | 4606020 | 25357463 | 5071492 | 20285971 | 29871066 | 5974213 | 23896852 | 29966712 | 5993343 | 23973369 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 287656 | 57531 | 230125 | 676199 | 135240 | 540959 | 1525958 | 305192 | 1220767 | 1525958 | 305192 | 1220767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2105954 | 421191 | 1684763 | 2249423 | 449885 | 1799538 | 1424305 | 284861 | 1139444 | 1206147 | 241229 | 964918 | 1349617 | 269925 | 1079692 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 49368 | 9874 | 39494 | 1696897 | 339380 | 1357517 | 11010 | 2202 | 8808 | 11010 | 2202 | 8808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 366435 | 73287 | 293148 | 414257 | 82849 | 331407 | 41611526 | 8322306 | 33289220 | 41133296 | 8226659 | 32906637 | 41611526 | 8322306 | 33289220 | 41611526 | 8322306 | 33289220 | 41133296 | 8226659 | 32906637 | 41611526 | 8322306 | 33289220 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2013 | Q3 | Q3 - 2013 | 5883232 | 1176646 | 4706586 | 5966394 | 1259808 | 4706586 | 5966394 | 1259808 | 4706586 | 26247504 | 5249501 | 20998003 | 26356259 | 5410923 | 20945336 | 26356259 | 5410923 | 20945336 | 733260 | 146652 | 586608 | 855266 | 268658 | 586608 | 855266 | 268658 | 586608 | 5739050 | 1147810 | 4591240 | 5703683 | 1112443 | 4591240 | 5703683 | 1112443 | 4591240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422664 | 284533 | 1138131 | 1608230 | 470099 | 1138131 | 1608230 | 470099 | 1138131 | 1354550 | 270910 | 1083640 | 1207036 | 123396 | 1083640 | 1207036 | 123396 | 1083640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231266 | 46253 | 185013 | 212403 | 27390 | 185013 | 212403 | 27390 | 185013 | 41611526 | 8322305 | 33289221 | 41909271 | 8672717 | 33236554 | 41909271 | 8672717 | 33236554 | 41611526 | 8322305 | 33289221 | 41909271 | 8672717 | 33236554 | 41909271 | 8672717 | 33236554 | 0 | 0 | Merit Network Inc.
NT10BIX5570009 | INF | 2013 | Q4 | Q4 - 2013 | 5883232 | 1176646 | 4706586 | 5966394 | 1259808 | 4706586 | 5966394 | 1259808 | 4706586 | 26247504 | 5249501 | 20998003 | 26356259 | 5410923 | 20945336 | 26356259 | 5410923 | 20945336 | 733260 | 146652 | 586608 | 855266 | 268658 | 586608 | 855266 | 268658 | 586608 | 5739050 | 1147810 | 4591240 | 5703683 | 1112443 | 4591240 | 5703683 | 1112443 | 4591240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422664 | 284533 | 1138131 | 1608230 | 470099 | 1138131 | 1608230 | 470099 | 1138131 | 1354550 | 270910 | 1083640 | 1207036 | 123396 | 1083640 | 1207036 | 123396 | 1083640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231266 | 46253 | 185013 | 212403 | 27390 | 185013 | 212403 | 27390 | 185013 | 41611526 | 8322305 | 33289221 | 41909271 | 8672717 | 33236554 | 41909271 | 8672717 | 33236554 | 41611526 | 8322305 | 33289221 | 41909271 | 8672717 | 33236554 | 41909271 | 8672717 | 33236554 | 0 | 0 | Merit Network Inc.
NT10BIX5570011 | INF | 2010 | Q3 | Q3 - 2010 | 6415529 | 4346473 | 2069056 | 0 | 0 | 0 | 300000 | 662582 | 233748 | 32081915 | 7084933 | 24996982 | 500 | 111 | 389 | 1424071 | 314490 | 1109581 | 329500 | 72766 | 256734 | 279494 | 61723 | 217771 | 300000 | 66252 | 233748 | 150000 | 33126 | 116874 | 0 | 0 | 0 | 27550 | 6084 | 21466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005142 | 221974 | 783168 | 925509 | 204388 | 721121 | 1005142 | 221974 | 783168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 1205503 | 266222 | 939281 | 3056763 | 1271382 | 2381711 | 39985556 | 11760038 | 28225518 | 1205503 | 266222 | 939281 | 3056763 | 1271382 | 2381711 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2010 | Q4 | Q4 - 2010 | 6415529 | 4346474 | 2069055 | 88 | 20 | 68 | 4105996 | 3621177 | 484819 | 31439915 | 6943153 | 24496762 | 223811 | 49426 | 174385 | 8587467 | 1896446 | 6691021 | 379500 | 83808 | 295692 | 310802 | 68637 | 242165 | 370802 | 81887 | 288915 | 350000 | 77294 | 272706 | 212373 | 46900 | 165473 | 270829 | 59810 | 211019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1438478 | 317672 | 1120806 | 1589341 | 350988 | 1238353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 2185552 | 482655 | 1702897 | 14924435 | 6010308 | 8914127 | 39985556 | 11760038 | 28225518 | 2185552 | 482655 | 1702897 | 14924435 | 6010308 | 8914127 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2011 | Q1 | Q1 - 2011 | 6415529 | 4346474 | 2069055 | 3133472 | 2473601 | 659871 | 3843351 | 2630370 | 1212981 | 31439915 | 6943153 | 24496762 | 3112656 | 687395 | 2425261 | 14728785 | 3252687 | 11476098 | 379500 | 83808 | 295692 | 356718 | 78777 | 277941 | 381718 | 84298 | 297420 | 350000 | 77294 | 272706 | 318428 | 70321 | 248107 | 328428 | 72530 | 255898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1577058 | 348276 | 1228782 | 1696017 | 374546 | 1321471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 8498332 | 3658370 | 4839962 | 20978299 | 6414431 | 14563868 | 39985556 | 11760038 | 28225518 | 8498332 | 3658370 | 4839962 | 20978299 | 6414431 | 14563868 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2011 | Q2 | Q2 - 2011 | 6415529 | 4346474 | 2069055 | 3928115 | 2649089 | 1279026 | 4750000 | 2830593 | 1919407 | 31439915 | 6943153 | 24496762 | 14623077 | 3914995 | 10708082 | 23000000 | 5079292 | 17920708 | 379500 | 83808 | 295692 | 409949 | 98324 | 311625 | 450000 | 99377 | 350623 | 350000 | 77294 | 272706 | 362267 | 80002 | 282265 | 383475 | 84686 | 298789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1750579 | 386596 | 1363983 | 1800000 | 397510 | 1402490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 21073987 | 7129006 | 13944981 | 30383475 | 8491458 | 21892017 | 39985556 | 11760038 | 28225518 | 21073987 | 7129006 | 13944981 | 30383475 | 8491458 | 21892017 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2011 | Q3 | Q3 - 2011 | 6415529 | 4346474 | 2069055 | 4590513 | 2795372 | 1795141 | 4700000 | 2819551 | 1880449 | 31439915 | 6943153 | 24496762 | 16189408 | 3575250 | 12614158 | 21000000 | 4637615 | 16362385 | 379500 | 83808 | 295692 | 416395 | 91956 | 324439 | 420000 | 92752 | 327248 | 350000 | 77294 | 272706 | 361727 | 79883 | 281844 | 395000 | 87231 | 307769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1667908 | 368339 | 1299569 | 1750000 | 386468 | 1363532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 23225951 | 6910800 | 16315151 | 28265000 | 8023617 | 20241383 | 39985556 | 11760038 | 28225518 | 23225951 | 6910800 | 16315151 | 28265000 | 8023617 | 20241383 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2011 | Q4 | Q4 - 2011 | 6415529 | 4346474 | 2069055 | 5059652 | 2898976 | 2160676 | 5119410 | 2912173 | 2207237 | 31439915 | 6943153 | 24496762 | 19342352 | 4271542 | 15070810 | 23457500 | 5180326 | 18277174 | 379500 | 83808 | 295692 | 435768 | 96234 | 339534 | 535000 | 118149 | 416851 | 350000 | 77294 | 272706 | 399108 | 88139 | 310969 | 415000 | 91648 | 323352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1772855 | 391515 | 1381340 | 1813000 | 400381 | 1412619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 3717 | 821 | 2896 | 3717 | 821 | 2896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 27013452 | 7747227 | 19266225 | 31343627 | 8703498 | 22640129 | 39985556 | 11760038 | 28225518 | 27013452 | 7747227 | 19266225 | 31343627 | 8703498 | 22640129 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2012 | Q1 | Q1 - 2012 | 4942064 | 2873009 | 2069055 | 5108820 | 2909835 | 2198985 | 5108820 | 2909835 | 2198985 | 31439915 | 6943153 | 24496762 | 22120396 | 4885042 | 17235354 | 25120396 | 5547558 | 19572838 | 379500 | 83808 | 295692 | 451918 | 99801 | 352117 | 451918 | 99801 | 352117 | 350000 | 77294 | 272706 | 429734 | 94902 | 334832 | 434734 | 96006 | 338728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1784937 | 394183 | 1390754 | 1834937 | 405225 | 1429712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 3717 | 821 | 2896 | 3717 | 821 | 2896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 29899522 | 8384584 | 21514938 | 32954522 | 9059246 | 23895276 | 38512091 | 10286573 | 28225518 | 29899522 | 8384584 | 21514938 | 32954522 | 9059246 | 23895276 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2012 | Q2 | Q2 - 2012 | 8470800 | 3652290 | 4818510 | 5679353 | 2751437 | 2927916 | 6000000 | 2822248 | 3177752 | 27250151 | 6017891 | 21232260 | 23954045 | 5574376 | 18379669 | 26791000 | 6200886 | 20590114 | 476900 | 105318 | 371582 | 460797 | 101762 | 359035 | 469797 | 103749 | 366048 | 430000 | 94961 | 335039 | 435479 | 96171 | 339308 | 440000 | 97169 | 342831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884240 | 416113 | 1468127 | 1795562 | 396530 | 1399032 | 1884240 | 416113 | 1468127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 32325236 | 8920276 | 23404960 | 35585037 | 9640165 | 25944872 | 38512091 | 10286573 | 28225518 | 32325236 | 8920276 | 23404960 | 35585037 | 9640165 | 25944872 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2012 | Q3 | Q3 - 2012 | 8470800 | 3652290 | 4818510 | 8151321 | 3297343 | 4853978 | 8470800 | 3367896 | 5102904 | 27250151 | 6017891 | 21232260 | 24267299 | 5643555 | 18623744 | 25794953 | 5980920 | 19814033 | 476900 | 105318 | 371582 | 463156 | 102283 | 360873 | 468000 | 103353 | 364647 | 430000 | 94961 | 335039 | 440400 | 97258 | 343142 | 441000 | 97390 | 343610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884240 | 416113 | 1468127 | 1863311 | 411491 | 1451820 | 1900000 | 419594 | 1480406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 35185487 | 9551930 | 25633557 | 37074753 | 9969153 | 27105600 | 38512091 | 10286573 | 28225518 | 35185487 | 9551930 | 25633557 | 37074753 | 9969153 | 27105600 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2012 | Q4 | Q4 - 2012 | 8990427 | 3229401 | 5761026 | 8570391 | 3136640 | 5433751 | 8585000 | 3139867 | 5445133 | 26410266 | 6370055 | 20040211 | 26307654 | 6347395 | 19960259 | 26308000 | 6347471 | 19960529 | 466201 | 169207 | 296994 | 463599 | 102381 | 361218 | 465000 | 102690 | 362310 | 740417 | 97261 | 643156 | 445449 | 98372 | 347077 | 450000 | 99377 | 350623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1936082 | 427562 | 1508520 | 1950000 | 430636 | 1519364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 37723175 | 10112350 | 27610825 | 37758000 | 10120041 | 27637959 | 38512091 | 10286573 | 28225518 | 37723175 | 10112350 | 27610825 | 37758000 | 10120041 | 27637959 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2013 | Q1 | Q1 - 2013 | 8990427 | 3229401 | 5761026 | 8585017 | 33139870 | 5445147 | 9285135 | 3294483 | 5990652 | 26410266 | 6370055 | 20040211 | 26625672 | 6417625 | 20208047 | 26300643 | 6345846 | 19954797 | 466201 | 169207 | 296994 | 469390 | 103660 | 365730 | 470000 | 103794 | 366206 | 740417 | 97261 | 643156 | 458212 | 101191 | 357021 | 458212 | 101191 | 357021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1964828 | 433910 | 1530918 | 1985000 | 438365 | 1546635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38103119 | 40196256 | 27906863 | 38498990 | 10283679 | 28215311 | 38512091 | 10286573 | 28225518 | 38103119 | 40196256 | 27906863 | 38498990 | 10283679 | 28215311 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2013 | Q2 | Q2 - 2013 | 8990427 | 3229401 | 5761026 | 8956144 | 3221829 | 5734315 | 8956144 | 3221829 | 5734315 | 26410266 | 6370055 | 20040211 | 26647777 | 6422507 | 20225270 | 26647777 | 6422507 | 20225270 | 466201 | 169207 | 296994 | 472530 | 104353 | 368177 | 472530 | 104353 | 368177 | 740417 | 97261 | 643156 | 460862 | 101776 | 359086 | 460862 | 101776 | 359086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1970902 | 435252 | 1535650 | 1974778 | 436108 | 1538670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38508215 | 10285717 | 28222498 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38508215 | 10285717 | 28222498 | 38512091 | 10286573 | 28225518 | 0 | 0 | MCNC
NT10BIX5570011 | INF | 2013 | Q3 | Q3 - 2013 | 8990427 | 3229401 | 5761026 | 8954245 | 3221410 | 5732835 | 8954245 | 3221410 | 5732835 | 26410266 | 6370055 | 20040211 | 26650831 | 6423181 | 20227650 | 26650831 | 6423181 | 20227650 | 466201 | 169207 | 296994 | 473791 | 104632 | 369159 | 473791 | 104632 | 369159 | 740417 | 97261 | 643156 | 454023 | 100266 | 353757 | 454023 | 100266 | 353757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1979201 | 437084 | 1542117 | 1979201 | 437084 | 1542117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 0 | 0 | MCNC
NT10BIX5570016 | INF | 2010 | Q3 | Q3 - 2010 | 300000 | 60000 | 240000 | 3220 | 0 | 3220 | 54025 | 10805 | 43220 | 5500000 | 1100000 | 4400000 | 0 | 0 | 0 | 996949 | 199390 | 797559 | 150000 | 30000 | 120000 | 47862 | 0 | 47862 | 97328 | 19466 | 77862 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 29359 | 0 | 29359 | 199199 | 39840 | 159359 | 20000 | 4000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 6925000 | 1385000 | 5540000 | 80441 | 0 | 80441 | 1385001 | 277001 | 1108000 | 6925000 | 1385000 | 5540000 | 80441 | 0 | 80441 | 1385001 | 277001 | 1108000 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2010 | Q4 | Q4 - 2010 | 300000 | 60000 | 240000 | 27953 | 20100 | 7853 | 47953 | 40100 | 7853 | 5500000 | 1100000 | 4400000 | 0 | 0 | 0 | 750000 | 0 | 750000 | 150000 | 30000 | 120000 | 51521 | 0 | 51521 | 81521 | 0 | 81521 | 300000 | 60000 | 240000 | 30708 | 30708 | 0 | 130708 | 130708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 192952 | 9819 | 183133 | 203021 | 9819 | 193202 | 20000 | 4000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 13000 | 0 | 13000 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 6925000 | 1385000 | 5540000 | 303134 | 60627 | 242507 | 1248203 | 180627 | 1067576 | 6925000 | 1385000 | 5540000 | 303134 | 60627 | 242507 | 1248203 | 180627 | 1067576 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2011 | Q1 | Q1 - 2011 | 300000 | 60000 | 240000 | 88443 | 88443 | 0 | 309667 | 309667 | 0 | 5500000 | 1100000 | 4400000 | 151323 | 0 | 151323 | 376323 | 0 | 376323 | 150000 | 30000 | 120000 | 85604 | 0 | 85604 | 100604 | 0 | 100604 | 300000 | 60000 | 240000 | 124421 | 110746 | 13675 | 124421 | 110746 | 13675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 580132 | 0 | 580132 | 580132 | 0 | 580132 | 20000 | 4000 | 16000 | 41917 | 0 | 41917 | 50917 | 0 | 50917 | 135000 | 27000 | 108000 | 4337 | 0 | 4337 | 16337 | 0 | 16337 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 53000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 20058 | 20058 | 0 | 20058 | 20058 | 0 | 6925000 | 1385000 | 5540000 | 1096235 | 219247 | 876988 | 1631459 | 493471 | 1137988 | 6925000 | 1385000 | 5540000 | 1096235 | 219247 | 876988 | 1631459 | 493471 | 1137988 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2011 | Q2 | Q2 - 2011 | 300000 | 60000 | 240000 | 173585 | 173585 | 0 | 176585 | 176585 | 0 | 5500000 | 1100000 | 4400000 | 528575 | 51719 | 476856 | 2946618 | 51719 | 2894899 | 150000 | 30000 | 120000 | 108262 | 0 | 108262 | 128262 | 0 | 128262 | 300000 | 60000 | 240000 | 124706 | 110746 | 13960 | 129706 | 115746 | 13960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 580132 | 0 | 580132 | 580132 | 0 | 580132 | 20000 | 4000 | 16000 | 56647 | 0 | 56647 | 71647 | 0 | 71647 | 135000 | 27000 | 108000 | 16992 | 0 | 16992 | 24992 | 0 | 24992 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 77000 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 20058 | 20058 | 0 | 20058 | 20058 | 0 | 6925000 | 1385000 | 5540000 | 1608957 | 356108 | 1252849 | 4155000 | 441108 | 3713892 | 6925000 | 1385000 | 5540000 | 1608957 | 356108 | 1252849 | 4155000 | 441108 | 3713892 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2011 | Q3 | Q3 - 2011 | 436000 | 436000 | 0 | 412571 | 406806 | 5765 | 426571 | 420806 | 5765 | 5113795 | 588565 | 4525230 | 1357611 | 88026 | 1269585 | 2594100 | 518820 | 2075280 | 214963 | 14963 | 200000 | 132946 | 17076 | 115870 | 144946 | 17076 | 127870 | 264041 | 134190 | 129851 | 171523 | 33902 | 137621 | 221523 | 83902 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600454 | 118946 | 481508 | 579453 | 106552 | 472901 | 599453 | 106552 | 492901 | 61948 | 15537 | 46411 | 57897 | 10282 | 47615 | 61897 | 14282 | 47615 | 80867 | 867 | 80000 | 37363 | 896 | 36467 | 54148 | 896 | 53252 | 127000 | 50000 | 77000 | 0 | 0 | 0 | 77000 | 0 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 2775296 | 689472 | 2085824 | 4205570 | 1188266 | 3017304 | 6925000 | 1385000 | 5540000 | 2775296 | 689472 | 2085824 | 4205570 | 1188266 | 3017304 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2011 | Q4 | Q4 - 2011 | 436000 | 436000 | 0 | 414436 | 408671 | 5765 | 422436 | 416671 | 5765 | 5113795 | 588565 | 4525230 | 1912365 | 113502 | 1798863 | 4085343 | 496503 | 3588840 | 214963 | 14963 | 200000 | 144944 | 17076 | 127868 | 169944 | 17076 | 152868 | 264041 | 134190 | 129851 | 174865 | 37244 | 137621 | 179865 | 42244 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600454 | 118946 | 481508 | 581920 | 106552 | 475368 | 585920 | 106552 | 479368 | 61948 | 15537 | 46411 | 57897 | 10282 | 47615 | 57897 | 10282 | 47615 | 80867 | 867 | 80000 | 55563 | 896 | 54667 | 71163 | 896 | 70267 | 127000 | 50000 | 77000 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 3367922 | 720155 | 2647767 | 5678500 | 1136156 | 4542344 | 6925000 | 1385000 | 5540000 | 3367922 | 720155 | 2647767 | 5678500 | 1136156 | 4542344 | 0 | 0 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2012 | Q1 | Q1 - 2012 | 1059170 | 565453 | 493717 | 418726 | 409295 | 9431 | 744658 | 435227 | 309431 | 3815772 | 405788 | 3409984 | 3060636 | 361561 | 2699075 | 3710636 | 393495 | 3317141 | 232913 | 24418 | 208495 | 182920 | 21279 | 161641 | 207920 | 21279 | 186641 | 839327 | 134190 | 705137 | 174865 | 37244 | 137621 | 257865 | 120244 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 579800 | 106127 | 473673 | 598800 | 118127 | 480673 | 80000 | 15536 | 64464 | 57897 | 10282 | 47615 | 76897 | 12433 | 64464 | 92132 | 1186 | 90946 | 64695 | 971 | 63724 | 79695 | 971 | 78724 | 178924 | 93174 | 85750 | 96254 | 18174 | 78080 | 116254 | 38174 | 78080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 4661725 | 990865 | 3670860 | 5818657 | 1165882 | 4652775 | 6925000 | 1385000 | 5540000 | 4661725 | 990865 | 3670860 | 5818657 | 1165882 | 4652775 | 0 | 21840 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2012 | Q2 | Q2 - 2012 | 1059170 | 565453 | 493717 | 426665 | 409352 | 17313 | 868665 | 509352 | 359313 | 3815772 | 405788 | 3409984 | 3420354 | 401090 | 3019264 | 3720354 | 401090 | 3319264 | 232913 | 24418 | 208495 | 215997 | 22957 | 193040 | 221997 | 22957 | 199040 | 839327 | 134190 | 705137 | 174865 | 37244 | 137621 | 504865 | 127244 | 377621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 580021 | 106348 | 473673 | 590021 | 116348 | 473673 | 80000 | 15536 | 64464 | 58942 | 10282 | 48660 | 78942 | 15282 | 63660 | 92132 | 1186 | 90946 | 81537 | 971 | 80566 | 86537 | 971 | 85566 | 178924 | 93174 | 85750 | 96888 | 18174 | 78714 | 146888 | 68174 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 5081201 | 1032350 | 4048851 | 6244201 | 1287350 | 4956851 | 6925000 | 1385000 | 5540000 | 5081201 | 1032350 | 4048851 | 6244201 | 1287350 | 4956851 | 0 | 28800 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2012 | Q3 | Q3 - 2012 | 1059170 | 565453 | 493717 | 1025749 | 532132 | 493617 | 1057617 | 564000 | 493617 | 3815772 | 405788 | 3409984 | 3531455 | 401090 | 3130365 | 3814000 | 404588 | 3409412 | 232913 | 24418 | 208495 | 223624 | 22957 | 200667 | 232600 | 24400 | 208200 | 839327 | 134190 | 705137 | 327300 | 66374 | 260927 | 839150 | 134111 | 705039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 585270 | 106348 | 478922 | 600300 | 118900 | 481400 | 80000 | 15536 | 64464 | 68535 | 10282 | 58253 | 78900 | 15500 | 63400 | 92132 | 1186 | 90946 | 90820 | 971 | 89849 | 92010 | 1180 | 90830 | 178924 | 93174 | 85750 | 96888 | 18174 | 78714 | 178700 | 93100 | 85600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 5975573 | 1184260 | 4791314 | 6919209 | 1381711 | 5537498 | 6925000 | 1385000 | 5540000 | 5975573 | 1184260 | 4791314 | 6919209 | 1381711 | 5537498 | 0 | 40200 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2012 | Q4 | Q4 - 2012 | 1059170 | 565453 | 493717 | 1037871 | 544254 | 493617 | 1057871 | 564254 | 493617 | 3815772 | 405788 | 3409984 | 3650494 | 402732 | 3247762 | 3808494 | 402732 | 3405762 | 232913 | 24418 | 208495 | 231809 | 23510 | 208299 | 232256 | 23957 | 208299 | 839327 | 134190 | 705137 | 679487 | 130217 | 549270 | 699487 | 130217 | 569270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 597800 | 118878 | 478922 | 599487 | 120556 | 478931 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 79535 | 15282 | 64253 | 92132 | 1186 | 90946 | 91014 | 971 | 90043 | 92014 | 971 | 90946 | 178924 | 93174 | 85750 | 104558 | 25844 | 78714 | 169558 | 90844 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 6925000 | 1385000 | 5540000 | 6494887 | 1287998 | 5206889 | 6765012 | 1375123 | 5389792 | 6925000 | 1385000 | 5540000 | 6494887 | 1287998 | 5206889 | 6765012 | 1375123 | 5389792 | 0 | 61852 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2013 | Q1 | Q1 - 2013 | 1059170 | 565453 | 493717 | 1054439 | 555471 | 498968 | 1074421 | 565453 | 508968 | 3815772 | 405788 | 3409984 | 3675739 | 416455 | 3259284 | 3806544 | 417260 | 3389284 | 232913 | 24418 | 208495 | 236939 | 23510 | 213429 | 245838 | 23510 | 222328 | 839327 | 134190 | 705137 | 680005 | 130217 | 549788 | 685005 | 130217 | 554788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 599478 | 120556 | 478922 | 604588 | 120556 | 484032 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 77535 | 15282 | 62253 | 92132 | 1186 | 90946 | 91014 | 971 | 90043 | 92014 | 971 | 91043 | 178924 | 93174 | 85750 | 104558 | 25844 | 78714 | 157558 | 78844 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 6925000 | 1385000 | 5540000 | 6544026 | 1314616 | 5229410 | 6769813 | 1378403 | 5391410 | 6925000 | 1385000 | 5540000 | 6544026 | 1314616 | 5229410 | 6769813 | 1378403 | 5391410 | 0 | 87502 | Virginia Tech Foundation, Inc.
NT10BIX5570016 | INF | 2013 | Q2 | Q2 - 2013 | 1059170 | 565453 | 493717 | 1068159 | 569191 | 498968 | 1068159 | 569191 | 498968 | 3815772 | 405788 | 3409984 | 3838991 | 424518 | 3414473 | 3838991 | 424518 | 3414473 | 232913 | 24418 | 208495 | 271070 | 30092 | 240978 | 271070 | 30092 | 240978 | 839327 | 134190 | 705137 | 743386 | 131337 | 612049 | 743386 | 131337 | 612049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 607739 | 121507 | 486232 | 607739 | 121507 | 486232 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 75544 | 15282 | 60262 | 92132 | 1186 | 90946 | 92310 | 971 | 91339 | 92310 | 971 | 91339 | 178924 | 93174 | 85750 | 136198 | 52732 | 83466 | 136198 | 52732 | 83466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 20310 | 25110 | -4800 | 20310 | 25110 | -4800 | 6925000 | 1385000 | 5540000 | 6853707 | 1370740 | 5482967 | 6853707 | 1370740 | 5482967 | 6925000 | 1385000 | 5540000 | 6853707 | 1370740 | 5482967 | 6853707 | 1370740 | 5482967 | 0 | 92228 | Virginia Tech Foundation, Inc.
NT10BIX5570017 | INF | 2010 | Q3 | Q3 - 2010 | 10895450 | 1332516 | 9562934 | 0 | 0 | 0 | 0 | 0 | 0 | 4995267 | 734493 | 4260774 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 31251 | 30157 | 1093 | 2110065 | 0 | 2110065 | 5323484 | 5128994 | 194490 | 358441 | 358441 | 0 | 512655 | 512655 | 347710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 32795 | 32795 | 0 | 32795 | 32795 | 0 | 495125 | 0 | 495125 | 0 | 0 | 0 | 0 | 0 | 0 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 0 | 0 | 0 | 6628767 | 0 | 6628767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 422487 | 421393 | 1093 | 2655515 | 545450 | 2457775 | 35980017 | 7196003 | 28784014 | 422487 | 421393 | 1093 | 2655515 | 545450 | 2457775 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2010 | Q4 | Q4 - 2010 | 12005450 | 1332516 | 10672934 | 0 | 0 | 0 | 0 | 393743 | 506778 | 2736593 | 560077 | 2176516 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 102708 | 0 | 102708 | 154007 | 0 | 154007 | 5497900 | 5303410 | 194490 | 750077 | 750077 | 0 | 666873 | 666873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 208954 | 208954 | 0 | 398344 | 0 | 398344 | 495125 | 0 | 495125 | 0 | 0 | 0 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 250000 | 0 | 250000 | 7603025 | 0 | 7603025 | 0 | 0 | 0 | 210000 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 1061739 | 959031 | 102708 | 2026934 | 1060616 | 1866839 | 35980017 | 7196003 | 28784014 | 1061739 | 959031 | 102708 | 2026934 | 1060616 | 1866839 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2011 | Q1 | Q1 - 2011 | 12005450 | 1332516 | 10672934 | 0 | 0 | 0 | 1835868 | 393743 | 1442125 | 2736593 | 560077 | 2176516 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 152575 | 0 | 152575 | 191696 | 0 | 191696 | 5497900 | 5303410 | 194490 | 666873 | 666873 | 0 | 821088 | 821088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 305374 | 40234 | 265140 | 848980 | 0 | 848980 | 495125 | 0 | 495125 | 168720 | 0 | 168720 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 343828 | 0 | 343828 | 7603025 | 0 | 7603025 | 0 | 0 | 0 | 1052001 | 0 | 1052001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 1293542 | 707107 | 586435 | 5441171 | 1214831 | 4226340 | 35980017 | 7196003 | 28784014 | 1293542 | 707107 | 586435 | 5441171 | 1214831 | 4226340 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2011 | Q2 | Q2 - 2011 | 12327062 | 1332516 | 10994546 | 383758 | 0 | 383758 | 1451508 | 393741 | 1057767 | 2414984 | 560077 | 1854907 | 0 | 0 | 0 | 475768 | 34961 | 440807 | 2881250 | 0 | 2881250 | 199506 | 0 | 199506 | 566429 | 0 | 566429 | 5497900 | 5303410 | 194490 | 821088 | 821088 | 0 | 2165148 | 2165148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 814600 | 0 | 814600 | 980164 | 0 | 980164 | 495125 | 0 | 495125 | 168720 | 0 | 168720 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 348478 | 0 | 348478 | 492102 | 0 | 492102 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 2736150 | 821088 | 1915062 | 6478829 | 2593850 | 3884979 | 35980017 | 7196003 | 28784014 | 2736150 | 821088 | 1915062 | 6478829 | 2593850 | 3884979 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2011 | Q3 | Q3 - 2011 | 12327062 | 1332516 | 10994546 | 2559751 | 393741 | 2166010 | 2899455 | 475186 | 2424269 | 2414984 | 560077 | 1854907 | 475767 | 34960 | 440807 | 1038413 | 198678 | 839735 | 2881250 | 0 | 2881250 | 623900 | 0 | 623900 | 744989 | 0 | 744988 | 5497900 | 5303410 | 194490 | 2377435 | 2377435 | 0 | 4419350 | 4419350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 814600 | 0 | 814600 | 1837287 | 0 | 1837287 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 365393 | 0 | 365393 | 1489406 | 0 | 1489406 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 7564556 | 2806136 | 4758420 | 12776610 | 5093214 | 7683395 | 35980017 | 7196003 | 28784014 | 7564556 | 2806136 | 4758420 | 12776610 | 5093214 | 7683395 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2011 | Q4 | Q4 - 2011 | 12327062 | 1332516 | 10994546 | 4990307 | 706104 | 4284203 | 6155370 | 1018277 | 5137093 | 2414984 | 560077 | 1854907 | 1523938 | 498463 | 1025475 | 1585551 | 560076 | 1025475 | 2881250 | 0 | 2881250 | 1156039 | 0 | 1156039 | 1976341 | 0 | 1976341 | 5497900 | 5303410 | 194490 | 5125890 | 5125890 | 0 | 5146440 | 5146440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1142536 | 0 | 1142536 | 1315199 | 0 | 1315199 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 742644 | 0 | 742644 | 958412 | 0 | 958412 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 15029064 | 6330457 | 8698607 | 17485023 | 6724793 | 10760230 | 35980017 | 7196003 | 28784014 | 15029064 | 6330457 | 8698607 | 17485023 | 6724793 | 10760230 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2012 | Q1 | Q1 - 2012 | 12327062 | 1332516 | 10994546 | 5217527 | 706104 | 4511424 | 6878126 | 1040449 | 5837677 | 2414984 | 560077 | 1854907 | 1523938 | 498463 | 1025475 | 1754889 | 498463 | 1256426 | 2881250 | 0 | 2881250 | 1231489 | 0 | 1231489 | 2206560 | 0 | 2206560 | 5497900 | 5303410 | 194490 | 5125890 | 5125890 | 0 | 5270367 | 5125890 | 144477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1282624 | 0 | 1282624 | 1532790 | 0 | 1532790 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 381360 | 0 | 381360 | 1763200 | 0 | 1763200 | 910757 | 0 | 910757 | 1075000 | 0 | 1075000 | 7603022 | 0 | 7603022 | 60000 | 0 | 60000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 15699935 | 6330457 | 9369479 | 19159092 | 6664802 | 12494290 | 35980017 | 7196003 | 28784014 | 15699935 | 6330457 | 9369479 | 19159092 | 6664802 | 12494290 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2012 | Q2 | Q2 - 2012 | 12327062 | 1332516 | 10994546 | 6155212 | 946904 | 5208308 | 10238522 | 946904 | 9291618 | 2414984 | 560077 | 1854907 | 1527339 | 498463 | 1028876 | 2276011 | 498463 | 1777548 | 2881250 | 0 | 2881250 | 1316890 | 0 | 1316890 | 2582870 | 0 | 2582871 | 5497900 | 5303410 | 194490 | 5270367 | 5125890 | 144477 | 5270367 | 5125890 | 144477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1422728 | 0 | 1422728 | 2054925 | 0 | 2054925 | 495125 | 0 | 495125 | 374670 | 0 | 374670 | 414345 | 0 | 414345 | 1763200 | 0 | 1763200 | 1026623 | 0 | 1026623 | 1329960 | 0 | 1329960 | 7603022 | 0 | 7603022 | 84520 | 0 | 84520 | 4841608 | 0 | 4841608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 17178349 | 6571257 | 10607092 | 29008608 | 6571257 | 22437352 | 35980017 | 7196003 | 28784014 | 17178349 | 6571257 | 10607092 | 29008608 | 6571257 | 22437352 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2012 | Q3 | Q3 - 2012 | 12327062 | 1332516 | 10994546 | 6912563 | 1042947 | 5869616 | 11783296 | 1332516 | 10450780 | 2414984 | 560077 | 1854907 | 1688138 | 498463 | 1189675 | 1985790 | 498463 | 1487327 | 2881250 | 0 | 2881250 | 2200268 | 0 | 2200268 | 2752335 | 0 | 2752335 | 5497900 | 5303410 | 194490 | 5270367 | 5125890 | 144477 | 5320380 | 5125890 | 194490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1422729 | 0 | 1422729 | 2639783 | 0 | 2639783 | 495125 | 0 | 495125 | 374670 | 0 | 374670 | 414345 | 0 | 414345 | 1763200 | 0 | 1763200 | 1033908 | 0 | 1033908 | 1393544 | 0 | 1393544 | 7603022 | 0 | 7603022 | 131010 | 0 | 131010 | 4845208 | 0 | 4845208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 19033653 | 6667300 | 12366353 | 31134681 | 6956869 | 24177812 | 35980017 | 7196003 | 28784014 | 19033653 | 6667300 | 12366353 | 31134681 | 6956869 | 24177812 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2012 | Q4 | Q4 - 2012 | 12327062 | 1332516 | 10994546 | 7906342 | 1042947 | 6863395 | 11150913 | 1568718 | 9582195 | 2414984 | 560077 | 1854907 | 1754888 | 498463 | 1256425 | 1991789 | 498463 | 1493326 | 2881250 | 0 | 2881250 | 2346182 | 0 | 2346182 | 2780400 | 0 | 2780400 | 5497900 | 5303410 | 194490 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1816150 | 0 | 1816150 | 2891650 | 0 | 2891650 | 495125 | 0 | 495125 | 402620 | 0 | 402620 | 425620 | 0 | 425620 | 1763200 | 0 | 1763200 | 1110712 | 0 | 1110712 | 1398997 | 0 | 1398997 | 7603022 | 0 | 7603022 | 347282 | 0 | 347282 | 6715126 | 0 | 6715126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 21557576 | 6667300 | 14890276 | 33227895 | 7193071 | 26034824 | 35980017 | 7196003 | 28784014 | 21557576 | 6667300 | 14890276 | 33227895 | 7193071 | 26034824 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2013 | Q1 | Q1 - 2013 | 12689105 | 1571649 | 11117456 | 11031931 | 1042947 | 9988984 | 12237998 | 1568718 | 10669280 | 2040021 | 498464 | 1541557 | 1958470 | 498463 | 1460007 | 2036990 | 498463 | 1538527 | 2993093 | 0 | 2993093 | 2410731 | 0 | 2410731 | 2850400 | 0 | 2850400 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1959750 | 0 | 1959750 | 2807461 | 0 | 2807461 | 495125 | 0 | 495125 | 415595 | 0 | 415595 | 432645 | 0 | 432645 | 1600436 | 0 | 1600436 | 1378854 | 0 | 1378854 | 1477364 | 0 | 1477364 | 7291363 | 0 | 7291363 | 6051885 | 0 | 6051885 | 7060248 | 0 | 7060248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 31080616 | 6667300 | 24413316 | 34776506 | 7193071 | 27583435 | 35980017 | 7196003 | 28784014 | 31080616 | 6667300 | 24413316 | 34776506 | 7193071 | 27583435 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2013 | Q2 | Q2 - 2013 | 12689105 | 1571649 | 11117456 | 11382169 | 1251025 | 10131144 | 12689105 | 1571649 | 11117456 | 2040021 | 498464 | 1541557 | 1958470 | 498463 | 1460007 | 2040021 | 498464 | 1541557 | 2993093 | 0 | 2993093 | 2795413 | 0 | 2795413 | 2993093 | 0 | 2993093 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 2636687 | 0 | 2636687 | 2997474 | 0 | 2997474 | 495125 | 0 | 495125 | 415595 | 0 | 415595 | 495125 | 0 | 495125 | 1600436 | 0 | 1600436 | 1505681 | 0 | 1505681 | 1600436 | 0 | 1600436 | 7291363 | 0 | 7291363 | 6299292 | 0 | 6299292 | 7291363 | 0 | 7291363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 32866707 | 6875378 | 25991329 | 35980017 | 7196003 | 28784014 | 35980017 | 7196003 | 28784014 | 32866707 | 6875378 | 25991329 | 35980017 | 7196003 | 28784014 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570017 | INF | 2013 | Q3 | Q3 - 2013 | 12689105 | 1571649 | 11117456 | 11634984 | 1332516 | 10302468 | 12670285 | 1571649 | 11098636 | 2040021 | 498464 | 1541557 | 2028960 | 498463 | 1530497 | 2028961 | 498464 | 1530497 | 2993093 | 0 | 2993093 | 2795812 | 0 | 2795812 | 2923878 | 0 | 2923878 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 2641330 | 0 | 2641330 | 2986153 | 0 | 2986153 | 495125 | 0 | 495125 | 438695 | 0 | 438695 | 490270 | 0 | 490270 | 1600436 | 0 | 1600436 | 1507056 | 0 | 1507056 | 1606526 | 0 | 1606526 | 7291363 | 0 | 7291363 | 6776989 | 0 | 6776989 | 7400544 | 0 | 7400544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 33697226 | 6956869 | 26740357 | 35980017 | 7196003 | 28784014 | 35980017 | 7196003 | 28784014 | 33697226 | 6956869 | 26740357 | 35980017 | 7196003 | 28784014 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration)
NT10BIX5570018 | INF | 2010 | Q3 | Q3 - 2010 | 2149732 | 760950 | 1388782 | 40837 | 0 | 40837 | 816353 | 657586 | 158767 | 622031 | 0 | 622031 | 65295 | 0 | 65295 | 128915 | 0 | 128915 | 462500 | 0 | 462500 | 62433 | 0 | 62433 | 103185 | 0 | 103185 | 27151000 | 5840000 | 21311000 | 270000 | 270000 | 0 | 25615000 | 4940000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 39482 | 0 | 39482 | 93345 | 0 | 93345 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 3084 | 0 | 3084 | 198918 | 0 | 198918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 2808 | 0 | 2808 | 6372 | 0 | 6372 | 32288795 | 6606425 | 25682370 | 488439 | 270000 | 218439 | 26966588 | 5597586 | 21369002 | 32288795 | 6606425 | 25682370 | 488439 | 270000 | 218439 | 26966588 | 5597586 | 21369002 | 0 | 0 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2010 | Q4 | Q4 - 2010 | 2149732 | 760950 | 1388782 | 115214 | 0 | 115214 | 828565 | 653842 | 174723 | 622031 | 0 | 622031 | 141929 | 0 | 141929 | 205963 | 0 | 205963 | 462500 | 0 | 462500 | 103328 | 0 | 103328 | 138561 | 0 | 138561 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 26515000 | 5840000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 95139 | 0 | 95139 | 155043 | 0 | 155043 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 82208 | 0 | 82208 | 401876 | 0 | 401876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 4653 | 0 | 4653 | 6990 | 0 | 6990 | 32288795 | 6606425 | 25682370 | 27061971 | 5840000 | 21221971 | 28256498 | 6493842 | 21762656 | 32288795 | 6606425 | 25682370 | 27061971 | 5840000 | 21221971 | 28256498 | 6493842 | 21762656 | 0 | 1264 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2011 | Q1 | Q1 - 2011 | 2149732 | 760950 | 1388782 | 874088 | 578380 | 295708 | 953857 | 578380 | 375477 | 622031 | 0 | 622031 | 208793 | 0 | 208793 | 298235 | 0 | 298235 | 462500 | 0 | 462500 | 134295 | 0 | 134295 | 204422 | 0 | 204422 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 26515000 | 5840000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 139154 | 0 | 139154 | 214199 | 0 | 214199 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 331717 | 0 | 331717 | 453050 | 0 | 453050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 4915 | 0 | 4915 | 7339 | 0 | 7339 | 32288795 | 6606425 | 25682370 | 28212462 | 6418380 | 21794082 | 28650602 | 6418380 | 22232222 | 32288795 | 6606425 | 25682370 | 28212462 | 6418380 | 21794082 | 28650602 | 6418380 | 22232222 | 0 | 7000 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2011 | Q2 | Q2 - 2011 | 2149732 | 760950 | 1388782 | 927995 | 578380 | 349615 | 1006214 | 578380 | 427834 | 622031 | 0 | 622031 | 300171 | 0 | 300171 | 387222 | 0 | 387222 | 462500 | 0 | 462500 | 169258 | 0 | 169258 | 236123 | 0 | 236123 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 27105000 | 5840000 | 21265000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 212095 | 0 | 212095 | 304670 | 0 | 304670 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 368828 | 0 | 368828 | 446459 | 0 | 446459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 6073 | 0 | 6073 | 7186 | 0 | 7339 | 32288795 | 6606425 | 25682370 | 28503920 | 6418380 | 22085540 | 29497374 | 6418380 | 23079147 | 32288795 | 6606425 | 25682370 | 28503920 | 6418380 | 22085540 | 29497374 | 6418380 | 23079147 | 0 | 20800 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2011 | Q3 | Q3 - 2011 | 2149732 | 760950 | 1388782 | 1155265 | 578380 | 576885 | 2313238 | 978380 | 1334858 | 622031 | 0 | 622031 | 384466 | 0 | 384466 | 465469 | 0 | 465469 | 462500 | 0 | 462500 | 224823 | 0 | 224823 | 267961 | 0 | 267961 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 27151000 | 5840000 | 21311000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 312934 | 0 | 312934 | 386640 | 0 | 386640 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 481388 | 0 | 481388 | 505212 | 0 | 505212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 8477 | 0 | 8477 | 36157 | 0 | 36157 | 32288795 | 6606425 | 25682370 | 29086853 | 6418380 | 22668473 | 31130177 | 6818380 | 24311797 | 32288795 | 6606425 | 25682370 | 29086853 | 6418380 | 22668473 | 31130177 | 6818380 | 24311797 | 0 | 48193 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2011 | Q4 | Q4 - 2011 | 2149732 | 760950 | 1388782 | 1165387 | 578380 | 587007 | 2291410 | 978380 | 1313030 | 622031 | 0 | 622031 | 479948 | 0 | 479948 | 622031 | 0 | 622031 | 462500 | 0 | 462500 | 257731 | 0 | 257731 | 285793 | 0 | 285793 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 383009 | 0 | 383009 | 505971 | 0 | 505971 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483496 | 0 | 483496 | 538370 | 0 | 538370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 37959 | 0 | 37959 | 41825 | 0 | 41825 | 32288795 | 6606425 | 25682370 | 30058030 | 6418380 | 23639650 | 31535900 | 6818380 | 24717520 | 32288795 | 6606425 | 25682370 | 30058030 | 6418380 | 23639650 | 31535900 | 6818380 | 24717520 | 0 | 65685 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2012 | Q1 | Q1 - 2012 | 2149732 | 760950 | 1388782 | 1308855 | 578380 | 730475 | 2421984 | 978380 | 1443604 | 622031 | 0 | 622031 | 562986 | 0 | 562986 | 646552 | 0 | 646552 | 462500 | 0 | 462500 | 305784 | 0 | 305784 | 344109 | 0 | 344109 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 482671 | 0 | 482671 | 610517 | 0 | 610517 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483007 | 0 | 483007 | 483007 | 0 | 483007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 38606 | 0 | 38606 | 40661 | 0 | 40661 | 32288795 | 6606425 | 25682370 | 30432409 | 6418380 | 24014029 | 31797330 | 6818380 | 24978950 | 32288795 | 6606425 | 25682370 | 30432409 | 6418380 | 24014029 | 31797330 | 6818380 | 24978950 | 0 | 192251 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2012 | Q2 | Q2 - 2012 | 2149732 | 760950 | 1388782 | 1781377 | 760935 | 1020442 | 2027019 | 760935 | 1266084 | 622031 | 0 | 622031 | 647771 | 0 | 647771 | 720706 | 0 | 720706 | 462500 | 0 | 462500 | 330845 | 0 | 330845 | 347801 | 0 | 347801 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 605024 | 0 | 605024 | 701758 | 0 | 701758 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483116 | 0 | 483116 | 484116 | 0 | 484116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 43280 | 0 | 43280 | 47719 | 0 | 47719 | 32288795 | 6606425 | 25682370 | 31141913 | 6600935 | 24540978 | 31579619 | 6600935 | 24978684 | 32288795 | 6606425 | 25682370 | 31141913 | 6600935 | 24540978 | 31579619 | 6600935 | 24978684 | 0 | 276709 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2012 | Q3 | Q3 - 2012 | 2149732 | 760950 | 1388782 | 2013475 | 764504 | 1248971 | 2163475 | 764504 | 1398971 | 622031 | 0 | 622031 | 710882 | 0 | 710882 | 774690 | 0 | 774690 | 462500 | 0 | 462500 | 351429 | 0 | 351429 | 378044 | 0 | 378044 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 692153 | 0 | 692153 | 787130 | 0 | 787130 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 486515 | 0 | 486515 | 486515 | 0 | 486515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 43788 | 0 | 43788 | 45438 | 0 | 45438 | 32288795 | 6606425 | 25682370 | 31548742 | 6604504 | 24944238 | 31885792 | 6604504 | 25281288 | 32288795 | 6606425 | 25682370 | 31548742 | 6604504 | 24944238 | 31885792 | 6604504 | 25281288 | 0 | 378736 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2012 | Q4 | Q4 - 2012 | 2149732 | 760950 | 1388782 | 2132591 | 764504 | 1368087 | 2221120 | 764504 | 1456616 | 622031 | 0 | 622031 | 785128 | 0 | 785128 | 907685 | 0 | 907685 | 462500 | 0 | 462500 | 386045 | 0 | 386045 | 405160 | 0 | 405160 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 761132 | 0 | 761132 | 860808 | 0 | 860808 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 492547 | 0 | 492547 | 503327 | 0 | 503327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 52085 | 0 | 52085 | 61381 | 1921 | 59460 | 32288795 | 6606425 | 25682370 | 31860028 | 6604504 | 25255524 | 32209981 | 6606425 | 25603556 | 32288795 | 6606425 | 25682370 | 31860028 | 6604504 | 25255524 | 32209981 | 6606425 | 25603556 | 0 | 480516 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2013 | Q1 | Q1 - 2013 | 2149732 | 760950 | 1388782 | 2157430 | 764504 | 1392926 | 2184706 | 764504 | 1420202 | 622031 | 0 | 622031 | 835102 | 0 | 835102 | 884108 | 0 | 884108 | 462500 | 0 | 462500 | 406159 | 0 | 406159 | 427274 | 0 | 427274 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 837879 | 0 | 837879 | 899548 | 0 | 899548 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 505327 | 0 | 505327 | 508327 | 0 | 508327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 56371 | 0 | 56371 | 58721 | 1921 | 56800 | 32288795 | 6606425 | 25682370 | 32048768 | 6604504 | 25444264 | 32213184 | 6606425 | 25606759 | 32288795 | 6606425 | 25682370 | 32048768 | 6604504 | 25444264 | 32213184 | 6606425 | 25606759 | 0 | 600258 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2013 | Q2 | Q2 - 2013 | 2149732 | 760950 | 1388782 | 2151559 | 766425 | 1385134 | 2151559 | 766425 | 1385134 | 622031 | 0 | 622031 | 884108 | 0 | 884108 | 912112 | 0 | 912112 | 462500 | 0 | 462500 | 416157 | 0 | 416157 | 449313 | 0 | 449313 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 899369 | 0 | 899369 | 931434 | 0 | 931434 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 511340 | 0 | 511340 | 511340 | 0 | 511340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 32288795 | 6606425 | 25682370 | 32170091 | 6606425 | 25563666 | 32263316 | 6606425 | 25656891 | 32288795 | 6606425 | 25682370 | 32170091 | 6606425 | 25563666 | 32263316 | 6606425 | 25656891 | 0 | 707551 | Critical Hub Networks, Inc
NT10BIX5570018 | INF | 2013 | Q3 | Q3 - 2013 | 2351537 | 966403 | 1385134 | 2351537 | 966403 | 1385134 | 2351537 | 966403 | 1385134 | 1361914 | 449802 | 912112 | 1361914 | 449802 | 912112 | 1361914 | 449802 | 912112 | 479639 | 6027 | 473612 | 479639 | 6027 | 473612 | 479639 | 6027 | 473612 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013295 | 80681 | 932614 | 1013295 | 80681 | 932614 | 1013295 | 80681 | 932614 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611466 | 100126 | 511340 | 611466 | 100126 | 511340 | 611466 | 100126 | 511340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 0 | 836614 | Critical Hub Networks, Inc
NT10BIX5570019 | INF | 2010 | Q3 | Q3 - 2010 | 67500 | 13500 | 54000 | 40178 | 0 | 40178 | 80000 | 80000 | 0 | 14728655 | 2945731 | 11782924 | 0 | 0 | 0 | 2365387 | 394231 | 1971156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 2250 | 0 | 2250 | 110000 | 80000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191208 | 638242 | 2552966 | 295702 | 0 | 295702 | 1449242 | 241540 | 1207702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568000 | 313600 | 1254400 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 338130 | 0 | 338130 | 4004629 | 795771 | 3208858 | 20055363 | 4011073 | 16044290 | 338130 | 0 | 338130 | 4004629 | 795771 | 3208858 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2010 | Q4 | Q4 - 2010 | 67500 | 13500 | 54000 | 144863 | 82879 | 61984 | 444863 | 382879 | 61984 | 14728655 | 2945731 | 11782924 | 0 | 0 | 0 | 1641000 | 341000 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 25495 | 0 | 25495 | 125495 | 0 | 125495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191208 | 638242 | 2552966 | 939640 | 186361 | 753279 | 1409640 | 186361 | 1223279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568000 | 313600 | 1254400 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 1109998 | 269240 | 840758 | 3665998 | 910240 | 2755758 | 20055363 | 4011073 | 16044290 | 1109998 | 269240 | 840758 | 3665998 | 910240 | 2755758 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2011 | Q1 | Q1 - 2011 | 1840754 | 457635 | 1383119 | 86565 | 82878 | 3687 | 511352 | 482176 | 29176 | 14728655 | 2945731 | 11782924 | 1759939 | 0 | 1759939 | 3259939 | 0 | 3259939 | 447423 | 0 | 447423 | 236159 | 0 | 236159 | 286000 | 0 | 286000 | 400000 | 80000 | 320000 | 224242 | 221492 | 2750 | 254242 | 251472 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1380857 | 186361 | 1194496 | 1480857 | 186361 | 1294496 | 305298 | 61060 | 244238 | 147853 | 0 | 147853 | 187853 | 0 | 187853 | 178947 | 35789 | 143158 | 1426 | 0 | 1426 | 1191 | 0 | 1191 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 25490 | 0 | 25490 | 503 | 503 | 0 | 20055363 | 4011073 | 16044290 | 3862531 | 490731 | 3371800 | 6041937 | 980512 | 5061405 | 20055363 | 4011073 | 16044290 | 3862531 | 490731 | 3371800 | 6041937 | 980512 | 5061405 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2011 | Q2 | Q2 - 2011 | 1840754 | 457635 | 1383119 | 125236 | 125236 | 0 | 1675851 | 1675851 | 0 | 14728655 | 2945731 | 11782924 | 2674897 | 0 | 2674897 | 6733896 | 0 | 6733896 | 447423 | 0 | 447423 | 252925 | 0 | 252925 | 312295 | 0 | 312295 | 400000 | 80000 | 320000 | 306638 | 303888 | 2750 | 346638 | 343888 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1384128 | 186361 | 1197767 | 1464128 | 186361 | 1277767 | 305298 | 61060 | 244238 | 201615 | 0 | 201615 | 251615 | 0 | 251615 | 178947 | 35789 | 143158 | 70343 | 0 | 70343 | 95343 | 0 | 95343 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 85000 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 59683 | 0 | 59683 | 65683 | 0 | 65683 | 20055363 | 4011073 | 16044290 | 5075465 | 615485 | 4459980 | 11030449 | 2206100 | 8824349 | 20055363 | 4011073 | 16044290 | 5075465 | 615485 | 4459980 | 11030449 | 2206100 | 8824349 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2011 | Q3 | Q3 - 2011 | 1840754 | 457635 | 1383119 | 836093 | 776228 | 59864 | 1076228 | 776228 | 300000 | 14728655 | 2945731 | 11782924 | 4734783 | 0 | 4734783 | 7234783 | 0 | 7234783 | 447423 | 0 | 447423 | 295058 | 0 | 295058 | 335058 | 0 | 335058 | 400000 | 80000 | 320000 | 224408 | 221492 | 2916 | 243711 | 221492 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1510851 | 186361 | 1324490 | 1686361 | 186361 | 1500000 | 305298 | 61060 | 244238 | 223022 | 0 | 223022 | 272022 | 0 | 272022 | 178947 | 35789 | 143158 | 89317 | 0 | 89317 | 102317 | 0 | 102317 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 170000 | 30000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 7913532 | 1184081 | 6729450 | 11120480 | 1214081 | 9906399 | 20055363 | 4011073 | 16044290 | 7913532 | 1184081 | 6729450 | 11120480 | 1214081 | 9906399 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2011 | Q4 | Q4 - 2011 | 1840754 | 457635 | 1383119 | 890434 | 827937 | 62497 | 1090434 | 1027937 | 62497 | 14728655 | 2945731 | 11782924 | 7268571 | 885528 | 6383043 | 11496536 | 3015145 | 8481391 | 447423 | 0 | 447423 | 334944 | 0 | 334944 | 374944 | 0 | 374944 | 400000 | 80000 | 320000 | 298510 | 221492 | 77018 | 428510 | 351492 | 77018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1511837 | 186361 | 1325476 | 1536837 | 211361 | 1325476 | 305298 | 61060 | 244238 | 222022 | 0 | 222022 | 272022 | 0 | 272022 | 178947 | 35789 | 143158 | 105800 | 0 | 105800 | 136002 | 0 | 136002 | 222038 | 44408 | 177630 | 4142 | 0 | 4142 | 164142 | 0 | 164142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 10636260 | 2121318 | 8514942 | 15499427 | 4605935 | 10893492 | 20055363 | 4011073 | 16044290 | 10636260 | 2121318 | 8514942 | 15499427 | 4605935 | 10893492 | 0 | 66078 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2012 | Q1 | Q1 - 2012 | 1840754 | 457635 | 1383119 | 1065726 | 999602 | 66124 | 1542839 | 1182537 | 360302 | 14728655 | 2945731 | 11782924 | 8589833 | 1225985 | 7363848 | 9689833 | 1298034 | 8391799 | 447423 | 0 | 447423 | 383346 | 0 | 383346 | 413346 | 3617 | 409729 | 400000 | 80000 | 320000 | 230912 | 223862 | 7050 | 360912 | 288862 | 72050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1649658 | 20720 | 1628938 | 1719658 | 90720 | 1628938 | 305298 | 61060 | 244238 | 239676 | 0 | 239676 | 299676 | 0 | 299676 | 178947 | 35789 | 143158 | 111655 | 0 | 111655 | 141655 | 0 | 141655 | 222038 | 44408 | 177630 | 108933 | 0 | 108933 | 150933 | 0 | 150933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 12379739 | 2470169 | 9909570 | 14318852 | 2863770 | 11455082 | 20055363 | 4011073 | 16044290 | 12379739 | 2470169 | 9909570 | 14318852 | 2863770 | 11455082 | 0 | 112094 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2012 | Q2 | Q2 - 2012 | 2437851 | 2000000 | 437851 | 1114453 | 1008070 | 106383 | 1917086 | 1808070 | 109016 | 13927318 | 1267903 | 12659415 | 10300668 | 1449553 | 8851115 | 11521517 | 1267903 | 10253614 | 447423 | 3617 | 443806 | 406481 | 0 | 406481 | 431481 | 3607 | 427874 | 400000 | 322000 | 78000 | 235273 | 226040 | 9233 | 393273 | 316040 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061771 | 373000 | 1688771 | 1951860 | 225729 | 1726131 | 2008378 | 319607 | 1688771 | 315000 | 153 | 314847 | 245991 | 0 | 245991 | 285991 | 153 | 285838 | 176000 | 0 | 176000 | 130608 | 0 | 130608 | 142608 | 0 | 142608 | 290000 | 44400 | 245600 | 158304 | 0 | 158304 | 278304 | 40000 | 238304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 14543638 | 2909392 | 11634246 | 16978638 | 3755380 | 13223258 | 20055363 | 4011073 | 16044290 | 14543638 | 2909392 | 11634246 | 16978638 | 3755380 | 13223258 | 0 | 151750 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2012 | Q3 | Q3 - 2012 | 2699851 | 1900409 | 799442 | 2554828 | 1900409 | 654419 | 2699851 | 1900409 | 799442 | 13315318 | 1697624 | 11617694 | 11268477 | 1655069 | 9613408 | 13298476 | 1685068 | 11613408 | 547423 | 0 | 547423 | 418322 | 0 | 418322 | 478322 | 0 | 478322 | 470000 | 323040 | 146960 | 235273 | 226040 | 9233 | 460273 | 321040 | 139233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1800210 | 39369 | 1760841 | 1890210 | 39369 | 1850841 | 375000 | 0 | 375000 | 245991 | 0 | 245991 | 335991 | 0 | 335991 | 226000 | 0 | 226000 | 150127 | 0 | 150127 | 163127 | 0 | 163127 | 310000 | 50000 | 260000 | 158304 | 0 | 158304 | 258304 | 0 | 258304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 16831532 | 3820887 | 13010645 | 19584554 | 3945886 | 15638668 | 20055363 | 4011073 | 16044290 | 16831532 | 3820887 | 13010645 | 19584554 | 3945886 | 15638668 | 0 | 210626 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2012 | Q4 | Q4 - 2012 | 2699851 | 1900409 | 799442 | 2561453 | 1900409 | 661044 | 2681452 | 1900409 | 781043 | 13315318 | 1697624 | 11617694 | 11905130 | 1655069 | 10250061 | 12518895 | 1655069 | 10863826 | 547423 | 0 | 547423 | 442965 | 0 | 442965 | 491700 | 0 | 491700 | 470000 | 323040 | 146960 | 345388 | 226040 | 119348 | 433639 | 286679 | 146960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1824145 | 39369 | 1784776 | 1884146 | 39369 | 1844777 | 375000 | 0 | 375000 | 278844 | 0 | 278844 | 308844 | 0 | 308844 | 226000 | 0 | 226000 | 162127 | 0 | 162127 | 175127 | 0 | 175127 | 310000 | 50000 | 260000 | 158304 | 0 | 158304 | 250304 | 0 | 250304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 17678356 | 3820887 | 13857469 | 18744107 | 3881526 | 14862581 | 20055363 | 4011073 | 16044290 | 17678356 | 3820887 | 13857469 | 18744107 | 3881526 | 14862581 | 0 | 433759 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2013 | Q1 | Q1 - 2013 | 2699851 | 1900409 | 799442 | 2595351 | 1908592 | 686760 | 2695351 | 1908592 | 786760 | 13315318 | 1697624 | 11617694 | 12454868 | 1746375 | 10708493 | 13076868 | 1796375 | 11280493 | 547423 | 0 | 547423 | 462920 | 0 | 462920 | 482920 | 0 | 482920 | 470000 | 323040 | 146960 | 346067 | 226040 | 120027 | 346067 | 226040 | 120027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1874091 | 39369 | 1834722 | 1884091 | 39369 | 1844722 | 375000 | 0 | 375000 | 278844 | 0 | 278844 | 303844 | 0 | 303844 | 226000 | 0 | 226000 | 170127 | 0 | 170127 | 178127 | 0 | 178127 | 310000 | 50000 | 260000 | 238256 | 38574 | 199682 | 238256 | 38574 | 199682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 18420524 | 3958950 | 14461575 | 19205524 | 4008950 | 15196575 | 20055363 | 4011073 | 16044290 | 18420524 | 3958950 | 14461575 | 19205524 | 4008950 | 15196575 | 0 | 605449 | Mid-Atlantic Broadband Cooperative
NT10BIX5570019 | INF | 2013 | Q2 | Q2 - 2013 | 2699851 | 1900409 | 799442 | 2644236 | 1935121 | 709115 | 2644236 | 1935121 | 709115 | 13315318 | 1697624 | 11617694 | 12933400 | 1761839 | 11171561 | 12933400 | 1761839 | 11171561 | 547423 | 0 | 547423 | 519651 | 0 | 519651 | 519651 | 0 | 519651 | 470000 | 323040 | 146960 | 346067 | 226040 | 120027 | 346067 | 226040 | 120027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1902880 | 39369 | 1863511 | 1902880 | 39369 | 1863511 | 375000 | 0 | 375000 | 297491 | 0 | 297491 | 297491 | 0 | 297491 | 226000 | 0 | 226000 | 171296 | 0 | 171296 | 171296 | 0 | 171296 | 310000 | 50000 | 260000 | 238256 | 38574 | 199682 | 238256 | 38574 | 199682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 19053277 | 4000943 | 15052334 | 19053277 | 4000943 | 15052334 | 20055363 | 4011073 | 16044290 | 19053277 | 4000943 | 15052334 | 19053277 | 4000943 | 15052334 | 0 | 719790 | Mid-Atlantic Broadband Cooperative
NT10BIX5570023 | INF | 2010 | Q3 | Q3 - 2010 | 15667576 | 0 | 15667576 | 0 | 0 | 0 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 405215 | 0 | 405215 | 732505 | 0 | 732505 | 20247000 | 9220000 | 11020000 | 1432000 | 0 | 1432000 | 10587262 | 0 | 10587262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1402605 | 0 | 1402605 | 2420251 | 0 | 2420251 | 384000 | 0 | 384000 | 53193 | 0 | 53193 | 200982 | 0 | 200982 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 1042790 | 0 | 104279 | 104279 | 0 | 104279 | 39369676 | 9220000 | 30142676 | 4335803 | 0 | 3397292 | 15295279 | 0 | 15295279 | 39369676 | 9220000 | 30142676 | 4335803 | 0 | 3397292 | 15295279 | 0 | 15295279 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2010 | Q4 | Q4 - 2010 | 15667576 | 0 | 15667576 | 0 | 0 | 0 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 571334 | 0 | 571334 | 936416 | 0 | 936416 | 20247000 | 9227000 | 11020000 | 1432000 | 0 | 1432000 | 7261262 | 0 | 7261262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 2138215 | 0 | 2138215 | 2976427 | 0 | 2976427 | 384000 | 0 | 384000 | 53193 | 0 | 53193 | 103193 | 0 | 103193 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 104279 | 0 | 104279 | 104279 | 0 | 104279 | 39369676 | 9227000 | 30142676 | 4299021 | 0 | 4299021 | 12631577 | 0 | 12631577 | 39369676 | 9227000 | 30142676 | 4299021 | 0 | 4299021 | 12631577 | 0 | 12631577 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2011 | Q1 | Q1 - 2011 | 15667576 | 0 | 15667576 | 671884 | 0 | 671884 | 5222625 | 0 | 5222625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 802279 | 0 | 802279 | 860779 | 0 | 860779 | 20247000 | 9227000 | 11020000 | 1432000 | 0 | 1432000 | 10150462 | 0 | 10150462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1532681 | 0 | 1532681 | 2073312 | 0 | 2073312 | 384000 | 0 | 384000 | 1243121 | 0 | 1243121 | 1503486 | 0 | 1503486 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 140924 | 65030 | 75894 | 167924 | 65030 | 102894 | 39369676 | 9227000 | 30142676 | 5822889 | 65030 | 5757859 | 19978588 | 65030 | 19913558 | 39369676 | 9227000 | 30142676 | 5822889 | 65030 | 5757859 | 19978588 | 65030 | 19913558 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2011 | Q2 | Q2 - 2011 | 15667576 | 0 | 15667576 | 1008879 | 0 | 1008879 | 5736879 | 0 | 5736879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 863729 | 0 | 863729 | 963549 | 0 | 963549 | 20247000 | 9227000 | 11020000 | 1543258 | 0 | 1543258 | 9662520 | 0 | 9662520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1945931 | 0 | 1945931 | 2314948 | 0 | 2314948 | 384000 | 0 | 384000 | 1433666 | 0 | 1433666 | 1690347 | 0 | 1690347 | 753432 | 0 | 753432 | 0 | 0 | 0 | 375000 | 0 | 375000 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 253438 | 150545 | 102893 | 280438 | 150545 | 129893 | 39369676 | 9227000 | 30142676 | 7048901 | 150545 | 6898356 | 21023681 | 150545 | 20873136 | 39369676 | 9227000 | 30142676 | 7048901 | 150545 | 6898356 | 21023681 | 150545 | 20873136 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2011 | Q3 | Q3 - 2011 | 15667576 | 0 | 15667576 | 4598907 | 0 | 4598907 | 4627157 | 0 | 4627157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 1288773 | 0 | 1288773 | 1426273 | 0 | 1426273 | 20247000 | 9227000 | 11020000 | 6708802 | 0 | 6708802 | 16135752 | 9075854 | 7059898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1945931 | 0 | 1945931 | 2430345 | 0 | 2430345 | 384000 | 0 | 384000 | 1433666 | 0 | 1433666 | 1814396 | 0 | 1814396 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 289640 | 0 | 289640 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 281039 | 151146 | 129893 | 308039 | 151146 | 156893 | 39369676 | 9227000 | 30142676 | 16526918 | 151146 | 16375772 | 27161102 | 9227000 | 17934102 | 39369676 | 9227000 | 30142676 | 16526918 | 151146 | 16375772 | 27161102 | 9227000 | 17934102 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2011 | Q4 | Q4 - 2011 | 15667576 | 0 | 15667576 | 4762623 | 0 | 4762623 | 5877565 | 0 | 5877565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 1884685 | 0 | 1884685 | 2419685 | 0 | 2419685 | 20247000 | 9227000 | 11020000 | 12276612 | 5132101 | 7144511 | 13559368 | 6339857 | 7219511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 2543771 | 0 | 2543771 | 3293771 | 0 | 3293771 | 384000 | 0 | 384000 | 1734137 | 0 | 1734137 | 1769137 | 0 | 1769137 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 365300 | 0 | 365300 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 334387 | 151146 | 183241 | 423592 | 185351 | 238241 | 39369676 | 9227000 | 30142676 | 23806015 | 5283247 | 18522768 | 27837918 | 6525208 | 21312710 | 39369676 | 9227000 | 30142676 | 23806015 | 5283247 | 18522768 | 27837918 | 6525208 | 21312710 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2012 | Q1 | Q1 - 2012 | 15667576 | 0 | 15667576 | 5174159 | 0 | 5174159 | 5652021 | 0 | 5652021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 2054383 | 0 | 2054383 | 2246383 | 0 | 2246383 | 20247000 | 9227000 | 11020000 | 14397917 | 7136406 | 7261511 | 17000460 | 8118949 | 8881511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 3316898 | 0 | 3316898 | 4091898 | 0 | 4091898 | 384000 | 0 | 384000 | 2187183 | 0 | 2187183 | 2222183 | 0 | 2222183 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 365300 | 0 | 365300 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 646638 | 0 | 646638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 413622 | 151146 | 262476 | 527827 | 185351 | 342476 | 39369676 | 9227000 | 30142676 | 27813962 | 7287552 | 20526410 | 32752710 | 8304300 | 24448410 | 39369676 | 9227000 | 30142676 | 27813962 | 7287552 | 20526410 | 32752710 | 8304300 | 24448410 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2012 | Q2 | Q2 - 2012 | 5652021 | 0 | 5652021 | 4722315 | 0 | 4722315 | 5369315 | 0 | 5369315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 2562339 | 0 | 2562339 | 3070339 | 0 | 3070339 | 18425747 | 9041649 | 9384098 | 15172319 | 7856322 | 7315997 | 15914584 | 8533587 | 7380997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 3953751 | 0 | 3953751 | 4703751 | 0 | 4703751 | 2328080 | 0 | 2328080 | 2296948 | 0 | 2296948 | 2299448 | 0 | 2299448 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 755756 | 0 | 755756 | 2530396 | 0 | 2530396 | 1092208 | 0 | 1092208 | 2067208 | 0 | 2067208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 562568 | 232063 | 330505 | 592568 | 232063 | 360505 | 39369676 | 9227000 | 30142676 | 30979204 | 8088385 | 22890819 | 34772969 | 8765650 | 26007319 | 39369676 | 9227000 | 30142676 | 30979204 | 8088385 | 22890819 | 34772969 | 8765650 | 26007319 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2012 | Q3 | Q3 - 2012 | 5652021 | 0 | 5652021 | 5120441 | 0 | 5120441 | 5545441 | 0 | 5545441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3138769 | 0 | 3138769 | 3713769 | 0 | 3713769 | 18425747 | 9041649 | 9384098 | 16007510 | 8653447 | 7354063 | 16675295 | 8821232 | 7854063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 4397284 | 0 | 4397284 | 5186284 | 0 | 5186284 | 2328080 | 0 | 2328080 | 2304539 | 0 | 2304539 | 2325539 | 0 | 2325539 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 776756 | 0 | 776756 | 2530396 | 0 | 2530396 | 1633909 | 0 | 1633909 | 2463909 | 0 | 2463909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 606251 | 232063 | 374188 | 616251 | 232063 | 384188 | 39369676 | 9227000 | 30142676 | 33825459 | 8885510 | 24939949 | 37303244 | 9053295 | 28249949 | 39369676 | 9227000 | 30142676 | 33825459 | 8885510 | 24939949 | 37303244 | 9053295 | 28249949 | 0 | 2078 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2012 | Q4 | Q4 - 2012 | 5652021 | 0 | 5652021 | 5377892 | 0 | 5377892 | 5652021 | 0 | 5652021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3440126 | 0 | 3440126 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18525156 | 9464563 | 9060593 | 18848661 | 9464563 | 9384098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 4988566 | 0 | 4988566 | 5234808 | 0 | 5234808 | 2328080 | 0 | 2328080 | 2362925 | 0 | 2362925 | 2362925 | 0 | 2362925 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 795230 | 0 | 795230 | 2530396 | 0 | 2530396 | 2053110 | 0 | 2053110 | 2530396 | 0 | 2530396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 665102 | 232063 | 433039 | 668004 | 232063 | 435941 | 39369676 | 9227000 | 30142676 | 38029633 | 9696626 | 28333007 | 39839302 | 9696626 | 30142676 | 39369676 | 9227000 | 30142676 | 38029633 | 9696626 | 28333007 | 39839302 | 9696626 | 30142676 | 0 | 2078 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2013 | Q1 | Q1 - 2013 | 5652021 | 0 | 5652021 | 5545206 | 0 | 5545206 | 5635206 | 0 | 5635206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3717582 | 0 | 3717582 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18378236 | 8994937 | 9383299 | 18378236 | 8994937 | 9383299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 697130 | 0 | 697130 | 2530396 | 0 | 2530396 | 2133395 | 0 | 2133395 | 2260524 | 0 | 2260524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 38836067 | 9227000 | 29609067 | 39102871 | 9227000 | 29875871 | 39369676 | 9227000 | 30142676 | 38836067 | 9227000 | 29609067 | 39102871 | 9227000 | 29875871 | 0 | 26878 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2013 | Q2 | Q2 - 2013 | 5652021 | 0 | 5652021 | 5662676 | 0 | 5662676 | 5662676 | 0 | 5662676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18637469 | 8994937 | 9642532 | 18675545 | 8994937 | 9680608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 677130 | 0 | 677130 | 2530396 | 0 | 2530396 | 2222550 | 0 | 2222550 | 2222550 | 0 | 2222550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 39331600 | 9227000 | 30104600 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39331600 | 9227000 | 30104600 | 39369676 | 9227000 | 30142676 | 0 | 35478 | North Florida Broadband Authority
NT10BIX5570023 | INF | 2013 | Q3 | Q3 - 2013 | 5652021 | 0 | 5652021 | 5662676 | 0 | 5662676 | 5662676 | 0 | 5662676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18675545 | 8994937 | 9680608 | 18675545 | 8994937 | 9680608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 677130 | 0 | 677130 | 2530396 | 0 | 2530396 | 2222550 | 0 | 2222550 | 2222550 | 0 | 2222550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 0 | 0 | North Florida Broadband Authority
NT10BIX5570024 | INF | 2010 | Q3 | Q3 - 2010 | 3708900 | 741780 | 2967120 | 0 | 0 | 0 | 0 | 0 | 0 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 2362 | 473 | 1890 | 2363 | 473 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 65166 | 13033 | 52133 | 65166 | 13033 | 52133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 50607 | 10092 | 40515 | 118136 | 23598 | 94538 | 17495691 | 4094595 | 13401096 | 118135 | 23598 | 94538 | 185665 | 37104 | 148561 | 17495691 | 4094595 | 13401096 | 118135 | 23598 | 94538 | 185665 | 37104 | 148561 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2010 | Q4 | Q4 - 2010 | 3708900 | 741780 | 2967120 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 2363 | 472 | 1890 | 2363 | 472 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 76697 | 15339 | 61357 | 76697 | 15339 | 61357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 57335 | 11438 | 45898 | 183526 | 36705 | 146821 | 17495691 | 4094595 | 13401096 | 136395 | 27249 | 109145 | 412586 | 82516 | 330068 | 17495691 | 4094595 | 13401096 | 136395 | 27249 | 109145 | 412586 | 82516 | 330068 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2011 | Q1 | Q1 - 2011 | 3708900 | 741780 | 2967120 | 111549 | 22310 | 89240 | 242073 | 48415 | 193658 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 1458172 | 359335 | 1098837 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 51931 | 24171 | 27760 | 302847 | 14375 | 288472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 79896 | 18139 | 61757 | 80648 | 18890 | 61757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 68590 | 13688 | 54901 | 528742 | 468796 | 59945 | 17495691 | 4094595 | 13401096 | 314329 | 80671 | 233658 | 2614845 | 912174 | 1702669 | 17495691 | 4094595 | 13401096 | 314329 | 80671 | 233658 | 2614845 | 912174 | 1702669 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2011 | Q2 | Q2 - 2011 | 3708900 | 741780 | 2967120 | 244912 | 48982 | 195930 | 374808 | 74962 | 299846 | 7742930 | 1908078 | 5834852 | 156813 | 39203 | 117610 | 2252995 | 495406 | 1757589 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 273475 | 14375 | 259100 | 456476 | 14375 | 442101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 89590 | 22833 | 66757 | 157679 | 37442 | 120237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 585918 | 516429 | 69489 | 585918 | 516429 | 69489 | 17495691 | 4094595 | 13401096 | 1353071 | 644185 | 708886 | 3830239 | 1140977 | 2689262 | 17495691 | 4094595 | 13401096 | 1353071 | 644185 | 708886 | 3830239 | 1140977 | 2689262 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2011 | Q3 | Q3 - 2011 | 3708900 | 741780 | 2967120 | 364199 | 72840 | 291360 | 476096 | 95219 | 380877 | 7742930 | 1908078 | 5834852 | 855835 | 213959 | 641876 | 2487027 | 621757 | 1865270 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 461820 | 14375 | 447445 | 688587 | 14375 | 674212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 151929 | 37120 | 114808 | 211180 | 49486 | 161694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 589034 | 516429 | 72605 | 594312 | 516429 | 77883 | 17495691 | 4094595 | 13401096 | 2425180 | 857086 | 1568094 | 4459565 | 1299629 | 3159936 | 17495691 | 4094595 | 13401096 | 2425180 | 857086 | 1568094 | 4459565 | 1299629 | 3159936 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2011 | Q4 | Q4 - 2011 | 3708900 | 741780 | 2967120 | 365096 | 73019 | 292077 | 1686107 | 337221 | 1348886 | 7742930 | 1908078 | 5834852 | 3101345 | 775336 | 2326009 | 5417301 | 1354325 | 4062976 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 655592 | 14375 | 641217 | 872015 | 14375 | 857640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 207849 | 51654 | 156195 | 228682 | 52988 | 175694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 594604 | 516429 | 78175 | 594604 | 516429 | 78175 | 17495691 | 4094595 | 13401096 | 4926849 | 1433176 | 3493673 | 8801072 | 2277701 | 6523371 | 17495691 | 4094595 | 13401096 | 4926849 | 1433176 | 3493673 | 8801072 | 2277701 | 6523371 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2012 | Q1 | Q1 - 2012 | 3702446 | 740489 | 2961957 | 1701646 | 339946 | 1361700 | 1762714 | 352160 | 1410554 | 7742930 | 1908078 | 5834852 | 3888748 | 972187 | 2916561 | 4260681 | 1065170 | 3195511 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 728213 | 14375 | 713838 | 850527 | 14375 | 836152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 283432 | 68322 | 215110 | 339032 | 79442 | 259590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579770 | 496851 | 82919 | 594604 | 516429 | 78175 | 594604 | 516429 | 78175 | 17495691 | 4094595 | 13401096 | 7200133 | 1914749 | 5285384 | 7811048 | 2031066 | 5779982 | 17495691 | 4094595 | 13401096 | 7200133 | 1914749 | 5285384 | 7811048 | 2031066 | 5779982 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2012 | Q2 | Q2 - 2012 | 3708900 | 741780 | 2967120 | 1857613 | 371522 | 1486091 | 2451512 | 490302 | 1961210 | 7742930 | 1908078 | 5834852 | 4785785 | 1196442 | 3589343 | 5514424 | 1378602 | 4135822 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 834280 | 14375 | 819905 | 867816 | 14375 | 853441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 368015 | 91344 | 276671 | 444267 | 106594 | 337673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 603503 | 518209 | 85294 | 603503 | 518209 | 85294 | 17495691 | 4094595 | 13401096 | 8452686 | 2195382 | 6257304 | 9885012 | 2511572 | 7373440 | 17495691 | 4094595 | 13401096 | 8452686 | 2195382 | 6257304 | 9885012 | 2511572 | 7373440 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2012 | Q3 | Q3 - 2012 | 3708900 | 741780 | 2967120 | 2298283 | 459656 | 1838627 | 3928455 | 785691 | 3142764 | 7742930 | 1908078 | 5834852 | 5556922 | 1388969 | 4167953 | 5700546 | 1424875 | 4275671 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 891999 | 14375 | 877624 | 951999 | 14375 | 937624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 443702 | 106957 | 336745 | 445934 | 107403 | 338531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 603503 | 518209 | 85294 | 603503 | 518209 | 85294 | 17495691 | 4094595 | 13401096 | 9797899 | 2491656 | 7306243 | 11633927 | 2854043 | 8779884 | 17495691 | 4094595 | 13401096 | 9797899 | 2491656 | 7306243 | 11633927 | 2854043 | 8779884 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2012 | Q4 | Q4 - 2012 | 7150931 | 1430186 | 5720745 | 2347805 | 469561 | 1878244 | 4059816 | 811963 | 3247853 | 7742930 | 1908078 | 5834852 | 5700546 | 1424875 | 4275671 | 5737262 | 1434054 | 4303208 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 977306 | 14375 | 962931 | 1009306 | 14375 | 994931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 446673 | 107551 | 339122 | 447784 | 107773 | 340011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 603503 | 518209 | 85294 | 630172 | 523543 | 106629 | 17495691 | 4094595 | 13401096 | 10079323 | 2538061 | 7541262 | 11887830 | 2895198 | 8992632 | 17495691 | 4094595 | 13401096 | 10079323 | 2538061 | 7541262 | 11887830 | 2895198 | 8992632 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2013 | Q1 | Q1 - 2013 | 7150931 | 1430186 | 5720745 | 3668965 | 733790 | 2935175 | 7177255 | 1435451 | 5741804 | 7742930 | 1908078 | 5834852 | 5738097 | 1434263 | 4303834 | 6938980 | 1734484 | 5204496 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 1069626 | 14375 | 1055251 | 1084626 | 14375 | 1070251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 447923 | 107801 | 340122 | 449923 | 109801 | 340122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 611374 | 519783 | 91591 | 659024 | 529313 | 129711 | 17495691 | 4094595 | 13401096 | 11539475 | 2813502 | 8725973 | 16313298 | 3826914 | 12486384 | 17495691 | 4094595 | 13401096 | 11539475 | 2813502 | 8725973 | 16313298 | 3826914 | 12486384 | 0 | 0 | University of Utah, The
NT10BIX5570024 | INF | 2013 | Q2 | Q2 - 2013 | 7150931 | 1430186 | 5720745 | 6809912 | 1361982 | 5447930 | 6809912 | 1361982 | 5447930 | 7742930 | 1908078 | 5834852 | 7273567 | 1818130 | 5455437 | 7273567 | 1818130 | 5455437 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 1152588 | 14375 | 1138213 | 1152588 | 14375 | 1138213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 448332 | 108210 | 340122 | 448332 | 108210 | 340122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 657385 | 528985 | 128400 | 657385 | 528985 | 128400 | 17495691 | 4094595 | 13401096 | 16345274 | 3835172 | 12510102 | 16345274 | 3835172 | 12510102 | 17495691 | 4094595 | 13401096 | 16345274 | 3835172 | 12510102 | 16345274 | 3835172 | 12510102 | 0 | 0 | University of Utah, The
NT10BIX5570025 | INF | 2010 | Q3 | Q3 - 2010 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 0 | 0 | 0 | 32260736 | 5572147 | 22288589 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991980 | 198396 | 793584 | 398621 | 79724 | 318897 | 174596 | 34819 | 139677 | 939678 | 187936 | 751742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 6285079 | 24852315 | 518621 | 103724 | 414897 | 294596 | 58819 | 235677 | 35825394 | 6285079 | 24852315 | 518621 | 103724 | 414897 | 294596 | 58819 | 235677 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570025 | INF | 2010 | Q4 | Q4 - 2010 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 556500 | 111300 | 445200 | 30336358 | 9587272 | 20749086 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 56733 | 11347 | 45386 | 113466 | 22693 | 90773 | 2114434 | 422887 | 1691547 | 0 | 0 | 0 | 951495 | 190299 | 761196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 176733 | 35347 | 141386 | 1941461 | 388292 | 1553169 | 35825394 | 10685079 | 25140315 | 176733 | 35347 | 141386 | 1941461 | 388292 | 1553169 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570025 | INF | 2011 | Q1 | Q1 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 0 | 0 | 0 | 30336358 | 9587272 | 20749086 | 36067 | 7213 | 28854 | 1800000 | 360000 | 1440000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 765142 | 153029 | 612113 | 1315143 | 263029 | 1052114 | 2114434 | 422887 | 1691547 | 721868 | 144374 | 577495 | 956383 | 191277 | 756106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 1643077 | 328616 | 1314462 | 4391526 | 878306 | 3504220 | 35825394 | 10685079 | 25140315 | 1643077 | 328616 | 1314462 | 4391526 | 878306 | 3504220 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570025 | INF | 2011 | Q2 | Q2 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 222600 | 44520 | 178080 | 30336358 | 9587272 | 20749086 | 3223987 | 644797 | 2579190 | 10906018 | 2181204 | 8724814 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 1212451 | 242490 | 969961 | 1508984 | 301797 | 1207187 | 2114434 | 422887 | 1691547 | 997485 | 199497 | 797988 | 1336584 | 267317 | 1069267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 14626 | 2925 | 11701 | 98444 | 19689 | 78755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 5568549 | 1113709 | 4454840 | 14192630 | 2838527 | 11354103 | 35825394 | 10685079 | 25140315 | 5568549 | 1113709 | 4454840 | 14192630 | 2838527 | 11354103 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570025 | INF | 2011 | Q3 | Q3 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 1113000 | 222600 | 890400 | 30336358 | 9587272 | 20749086 | 6468227 | 1293645 | 5174582 | 10168227 | 2033645 | 8134582 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 1450329 | 290066 | 1160263 | 1632507 | 326502 | 1306005 | 2114434 | 422887 | 1691547 | 1290281 | 258056 | 1032225 | 1646281 | 329256 | 1317025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 106372 | 21154 | 84618 | 218015 | 43603 | 174412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 9435209 | 1886921 | 7547688 | 14898030 | 2979606 | 11918424 | 35825394 | 10685079 | 25140315 | 9435209 | 1886921 | 7547688 | 14898030 | 2979606 | 11918424 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570025 | INF | 2011 | Q4 | Q4 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 0 | 0 | 0 | 30336358 | 9587272 | 20749086 | 6468227 | 1293645 | 5174582 | 6468227 | 1293645 | 5174582 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 1450329 | 290066 | 1160263 | 1450329 | 290066 | 1160263 | 2114434 | 422887 | 1691547 | 1290281 | 258056 | 1032224 | 1290311 | 258056 | 1032224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 105772 | 21154 | 84618 | 105772 | 21154 | 84618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 9434609 | 1886921 | 7547687 | 9434639 | 1886921 | 7547687 | 35825394 | 10685079 | 25140315 | 9434609 | 1886921 | 7547687 | 9434639 | 1886921 | 7547687 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570026 | INF | 2010 | Q3 | Q3 - 2010 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 119429848 | 24229170 | 95200678 | 0 | 0 | 0 | 20000 | 0 | 20000 | 1153183 | 1153183 | 0 | 252226 | 252226 | 0 | 362726 | 362726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 155000 | 220000 | 24974 | 10489 | 14485 | 54974 | 23089 | 31885 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 277200 | 262715 | 14485 | 437700 | 385815 | 51885 | 128958031 | 29297353 | 99660678 | 277200 | 262715 | 14485 | 437700 | 385815 | 51885 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2010 | Q4 | Q4 - 2010 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 0 | 0 | 0 | 20000 | 0 | 20000 | 3513083 | 3513083 | 0 | 334210 | 334210 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 51390 | 36905 | 14485 | 72860 | 50000 | 22860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 385600 | 371115 | 14485 | 592860 | 550000 | 42860 | 128958031 | 29297353 | 99660678 | 385600 | 371115 | 14485 | 592860 | 550000 | 42860 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2011 | Q1 | Q1 - 2011 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 19250 | 0 | 19250 | 34417863 | 6879722 | 27538141 | 3513083 | 3513083 | 0 | 418853 | 418853 | 0 | 579091 | 579091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 125137 | 51443 | 73694 | 149377 | 51443 | 97934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 563240 | 470296 | 92944 | 35146331 | 7510256 | 27636075 | 128958031 | 29297353 | 99660678 | 563240 | 470296 | 92944 | 35146331 | 7510256 | 27636075 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2011 | Q2 | Q2 - 2011 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 27455436 | 5487237 | 21968199 | 37093597 | 7093597 | 30000000 | 3513083 | 3513083 | 0 | 645159 | 645159 | 0 | 895159 | 895159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 339059 | 202254 | 136805 | 425994 | 259254 | 166740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 28439654 | 6334650 | 22105004 | 38414750 | 8248010 | 30166740 | 128958031 | 29297353 | 99660678 | 28439654 | 6334650 | 22105004 | 38414750 | 8248010 | 30166740 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2011 | Q3 | Q3 - 2011 | 5850000 | 1610000 | 4240000 | 715196 | 0 | 715196 | 3258235 | 543039 | 2715196 | 118892448 | 23691770 | 95200678 | 32785119 | 6553174 | 26231945 | 69385119 | 13153174 | 56231945 | 3513083 | 3513083 | 0 | 777186 | 777186 | 0 | 927186 | 927186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 444497 | 292500 | 151997 | 469497 | 292500 | 176997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 34721998 | 7622860 | 27099138 | 74040037 | 14915899 | 59124138 | 128958031 | 29297353 | 99660678 | 34721998 | 7622860 | 27099138 | 74040037 | 14915899 | 59124138 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2011 | Q4 | Q4 - 2011 | 5850000 | 1610000 | 4240000 | 4596314 | 1981118 | 2615196 | 6300000 | 2300000 | 4000000 | 118892448 | 23691770 | 95200678 | 61997789 | 12395708 | 49602081 | 80053989 | 16006948 | 64047041 | 3513083 | 3513083 | 0 | 1023552 | 1023552 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 459913 | 292500 | 167413 | 506163 | 292500 | 213663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 68077568 | 15692878 | 52384690 | 88360152 | 20099448 | 68260704 | 128958031 | 29297353 | 99660678 | 68077568 | 15692878 | 52384690 | 88360152 | 20099448 | 68260704 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2012 | Q1 | Q1 - 2012 | 5850000 | 1610000 | 4240000 | 5260592 | 1610000 | 3650592 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 83930814 | 16782313 | 67148501 | 99500000 | 19500000 | 80000000 | 3513083 | 3513083 | 0 | 3041347 | 3041347 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 483038 | 292500 | 190538 | 507500 | 292500 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 92905791 | 21916160 | 70989631 | 109560583 | 25105583 | 84455000 | 128958031 | 29297353 | 99660678 | 92905791 | 21916160 | 70989631 | 109560583 | 25105583 | 84455000 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2012 | Q2 | Q2 - 2012 | 5850000 | 1610000 | 4240000 | 5460837 | 1610000 | 3850837 | 5610000 | 1610000 | 4000000 | 118892448 | 23691770 | 95200678 | 84149308 | 16782313 | 67366995 | 99500000 | 19500000 | 80000000 | 3513083 | 3513083 | 0 | 3122670 | 3122670 | 0 | 3250000 | 3250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 93435315 | 21997483 | 71437832 | 109062500 | 24842500 | 84220000 | 128958031 | 29297353 | 99660678 | 93435315 | 21997483 | 71437832 | 109062500 | 24842500 | 84220000 | 0 | 0 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2012 | Q3 | Q3 - 2012 | 5850000 | 1610000 | 4240000 | 5473356 | 1610000 | 3863356 | 5557240 | 1610000 | 3947240 | 118892448 | 23691770 | 95200678 | 96582465 | 19268944 | 77313521 | 103785294 | 20709510 | 83075784 | 3513083 | 3513083 | 0 | 3217400 | 3217400 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 105975721 | 24578844 | 81396877 | 113558117 | 26315093 | 87243024 | 128958031 | 29297353 | 99660678 | 105975721 | 24578844 | 81396877 | 113558117 | 26315093 | 87243024 | 0 | 500000 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2012 | Q4 | Q4 - 2012 | 5850000 | 1610000 | 4240000 | 5473356 | 1610000 | 3863356 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 108971911 | 21833553 | 87138358 | 113000000 | 23000000 | 90000000 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 118660850 | 27439136 | 91221714 | 123065583 | 28605583 | 94460000 | 128958031 | 29297353 | 99660678 | 118660850 | 27439136 | 91221714 | 123065583 | 28605583 | 94460000 | 0 | 543526 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2013 | Q1 | Q1 - 2013 | 5850000 | 1610000 | 4240000 | 5739994 | 1610000 | 4129994 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 112882085 | 22615588 | 90266497 | 118892448 | 23691770 | 95200678 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 122837662 | 28221171 | 94616491 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660678 | 122837662 | 28221171 | 94616491 | 128958031 | 29297353 | 99660678 | 0 | 578562 | Keystone Initiative For Network Based Education and Research
NT10BIX5570026 | INF | 2013 | Q2 | Q2 - 2013 | 5850000 | 1610000 | 4240000 | 5850000 | 1610000 | 4240000 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 118892448 | 23691770 | 95200578 | 118892448 | 23691770 | 95200678 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660578 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660578 | 128958031 | 29297353 | 99660678 | 0 | 578562 | Keystone Initiative For Network Based Education and Research
NT10BIX5570027 | INF | 2010 | Q3 | Q3 - 2010 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 0 | 0 | 0 | 10076115 | 3392658 | 6683458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252067 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 16602699 | 5350633 | 11252067 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2010 | Q4 | Q4 - 2010 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 0 | 0 | 0 | 10076115 | 3392658 | 6683457 | 0 | 0 | 0 | 510000 | 153000 | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 399225 | 119768 | 279457 | 576036 | 172811 | 403225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 399225 | 119768 | 279457 | 1086036 | 325811 | 760225 | 16602699 | 5350633 | 11252066 | 399225 | 119768 | 279457 | 1086036 | 325811 | 760225 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2011 | Q1 | Q1 - 2011 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 1182930 | 354879 | 828051 | 10076115 | 3392658 | 6683457 | 563915 | 169174 | 394740 | 3526640 | 1057992 | 2468648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 604090 | 181227 | 422863 | 821987 | 246596 | 575391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 1168005 | 350401 | 817603 | 5531557 | 1659467 | 3872090 | 16602699 | 5350633 | 11252066 | 1168005 | 350401 | 817603 | 5531557 | 1659467 | 3872090 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2011 | Q2 | Q2 - 2011 | 5360084 | 1608025 | 3752059 | 1024773 | 307432 | 717341 | 3367294 | 1010188 | 2357106 | 10076115 | 3392658 | 6683457 | 3300576 | 990173 | 2310403 | 5138644 | 1541593 | 3597051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 105147 | 31544 | 73603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 907802 | 272341 | 635461 | 1041516 | 312455 | 729061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 5233151 | 1569946 | 3663205 | 9652601 | 2895780 | 6756821 | 16602699 | 5350633 | 11252066 | 5233151 | 1569946 | 3663205 | 9652601 | 2895780 | 6756821 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2011 | Q3 | Q3 - 2011 | 5360084 | 1608025 | 3752059 | 2543066 | 762920 | 1780146 | 2793066 | 837920 | 1955146 | 10076115 | 3392658 | 6683457 | 5442284 | 1892379 | 3549905 | 6983487 | 2354740 | 4628747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 157502 | 47251 | 110251 | 307502 | 92250 | 215251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 1308816 | 392645 | 916171 | 1772863 | 531859 | 1241004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 9451668 | 3095195 | 6356473 | 11856918 | 3816769 | 8040148 | 16602699 | 5350633 | 11252066 | 9451668 | 3095195 | 6356473 | 11856918 | 3816769 | 8040148 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2011 | Q4 | Q4 - 2011 | 4858938 | 1457797 | 3401141 | 4069330 | 1220799 | 2848531 | 4615991 | 1384797 | 3231194 | 9416893 | 3194720 | 6222173 | 7055746 | 2376418 | 4679328 | 8375350 | 2772299 | 5603051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572995 | 171912 | 401083 | 281907 | 84572 | 197335 | 515696 | 154709 | 360987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753873 | 526204 | 1227669 | 1657055 | 497117 | 1159938 | 1753873 | 526204 | 1227669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 13064038 | 4178906 | 8885132 | 15260910 | 4838009 | 10422901 | 16602699 | 5350633 | 11252066 | 13064038 | 4178906 | 8885132 | 15260910 | 4838009 | 10422901 | 0 | 95961 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2012 | Q1 | Q1 - 2012 | 5040447 | 1546333 | 3494114 | 4554946 | 1389976 | 3164970 | 5040447 | 1546333 | 3494114 | 8998342 | 3017732 | 5980610 | 8083897 | 2723558 | 5360339 | 8998342 | 3017732 | 5980610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666018 | 204324 | 461694 | 666018 | 204324 | 461694 | 666018 | 204324 | 461694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897892 | 582244 | 1315648 | 1754719 | 535466 | 1219253 | 1897892 | 582244 | 1315648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15059580 | 4853324 | 10206256 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15059580 | 4853324 | 10206256 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2012 | Q2 | Q2 - 2012 | 4969701 | 1601610 | 3368091 | 4568987 | 1395671 | 3173316 | 4969701 | 1601610 | 3368091 | 8998342 | 2899939 | 6098403 | 8570792 | 2875754 | 5695039 | 8998342 | 2899939 | 6098403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 237441 | 499323 | 736764 | 237441 | 499323 | 736764 | 237441 | 499323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897892 | 611643 | 1286249 | 1800797 | 550083 | 1250714 | 1897892 | 611643 | 1286249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15677340 | 5058949 | 10618392 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15677340 | 5058949 | 10618392 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2012 | Q3 | Q3 - 2012 | 4969701 | 1524629 | 3445072 | 4709129 | 1440993 | 3268136 | 4969701 | 1524629 | 3445072 | 8953674 | 3004028 | 5949646 | 8575884 | 2881687 | 5694197 | 8953674 | 3004028 | 5949646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1942560 | 595948 | 1346612 | 1942560 | 595948 | 1346612 | 1942560 | 595948 | 1346612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2012 | Q4 | Q4 - 2012 | 4831569 | 1482252 | 3349317 | 4709129 | 1440993 | 3268136 | 4831569 | 1482252 | 3349317 | 9085464 | 3044459 | 6041005 | 8575884 | 2881687 | 5694197 | 9085464 | 3044459 | 6041005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948902 | 597894 | 1351008 | 1942560 | 595948 | 1346612 | 1948902 | 597894 | 1351008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570027 | INF | 2013 | Q1 | Q1 - 2013 | 4764147 | 1461396 | 3302751 | 4764147 | 1461396 | 3302751 | 4764147 | 1461396 | 3302751 | 9085464 | 3044144 | 6041320 | 9085464 | 3044144 | 6041320 | 9085464 | 3044144 | 6041320 | 29630 | 9089 | 20541 | 29630 | 9089 | 20541 | 29630 | 9089 | 20541 | 736764 | 226001 | 510763 | 736764 | 226001 | 510763 | 736764 | 226001 | 510763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948902 | 597823 | 1351079 | 1948902 | 597823 | 1351079 | 1948902 | 597823 | 1351079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570028 | INF | 2010 | Q3 | Q3 - 2010 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 0 | 0 | 0 | 28722959 | 5744592 | 22978368 | 0 | 0 | 0 | 0 | 0 | 0 | 28722959 | 5744592 | 22978368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Administration, Wisconsin Department of
NT10BIX5570028 | INF | 2010 | Q4 | Q4 - 2010 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 106300 | 85040 | 21260 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 74000 | 14800 | 59200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 30100 | 6020 | 24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 481100 | 96220 | 384880 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 691500 | 202080 | 489420 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 691500 | 202080 | 489420 | 0 | 0 | Administration, Wisconsin Department of
NT10BIX5570028 | INF | 2011 | Q1 | Q1 - 2011 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 0 | 0 | Administration, Wisconsin Department of
NT10BIX5570028 | INF | 2011 | Q2 | Q2 - 2011 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 0 | 0 | Administration, Wisconsin Department of
NT10BIX5570029 | INF | 2010 | Q3 | Q3 - 2010 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc.
NT10BIX5570029 | INF | 2010 | Q4 | Q4 - 2010 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc.
NT10BIX5570029 | INF | 2011 | Q1 | Q1 - 2011 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc.
NT10BIX5570030 | INF | 2010 | Q3 | Q3 - 2010 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 225600 | 65600 | 160000 | 10969239 | 766223 | 10203016 | 0 | 0 | 0 | 855882 | 55882 | 800000 | 39000 | 7800 | 31200 | 15015 | 3003 | 12012 | 21000 | 4200 | 16800 | 1435485 | 996922 | 438563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 89500 | 17900 | 71600 | 114500 | 22900 | 91600 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 104515 | 20903 | 83612 | 1241982 | 153582 | 1088400 | 14830204 | 2966040 | 11864164 | 104515 | 20903 | 83612 | 1241982 | 153582 | 1088400 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2010 | Q4 | Q4 - 2010 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 300000 | 60000 | 240000 | 10969239 | 766223 | 10203016 | 0 | 0 | 0 | 1040866 | 208173 | 832693 | 39000 | 7800 | 31200 | 20967 | 4194 | 16773 | 30000 | 6000 | 24000 | 1435485 | 996922 | 438563 | 0 | 0 | 0 | 251000 | 50200 | 200800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 92500 | 18500 | 74000 | 195000 | 39000 | 156000 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 5000 | 10001 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 113467 | 22694 | 90773 | 1821866 | 373374 | 1457493 | 14830204 | 2966040 | 11864164 | 113467 | 22694 | 90773 | 1821866 | 373374 | 1457493 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2011 | Q1 | Q1 - 2011 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 40000 | 16400 | 23600 | 10969239 | 766223 | 10203016 | 595022 | 110871 | 484151 | 2840015 | 268021 | 2571994 | 39000 | 7800 | 31200 | 29001 | 5801 | 22786 | 35000 | 7000 | 28000 | 1435485 | 996922 | 438563 | 142808 | 10151 | 132656 | 688143 | 459806 | 228336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 151022 | 56254 | 94768 | 272422 | 141971 | 130451 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 22500 | 4500 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 917853 | 183077 | 734361 | 3898080 | 897698 | 3000381 | 14830204 | 2966040 | 11864164 | 917853 | 183077 | 734361 | 3898080 | 897698 | 3000381 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2011 | Q2 | Q2 - 2011 | 1695000 | 694950 | 1000050 | 260167 | 106668 | 153499 | 340167 | 139468 | 200698 | 10969239 | 766223 | 10203016 | 2977699 | 189185 | 2788514 | 6040239 | 403563 | 5636676 | 39000 | 7800 | 31200 | 32907 | 6582 | 26325 | 39917 | 7984 | 31933 | 1435485 | 996922 | 438563 | 830119 | 523504 | 306615 | 1158544 | 802778 | 355766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 178470 | 73830 | 104640 | 293470 | 179390 | 114080 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 4279362 | 899769 | 3379593 | 7872337 | 1533183 | 6339153 | 14830204 | 2966040 | 11864164 | 4279362 | 899769 | 3379593 | 7872337 | 1533183 | 6339153 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2011 | Q3 | Q3 - 2011 | 1695000 | 694950 | 1000050 | 280698 | 115086 | 165612 | 1040718 | 426706 | 614012 | 10969239 | 766223 | 10203016 | 5406021 | 359168 | 5046854 | 7373161 | 496868 | 6876293 | 39000 | 7800 | 31200 | 39761 | 7953 | 31808 | 47440 | 9497 | 37943 | 1435485 | 996922 | 438563 | 951299 | 533198 | 418101 | 1572877 | 953296 | 619581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 310928 | 206288 | 104640 | 377832 | 273192 | 104640 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 6988707 | 1221693 | 5767015 | 10412028 | 2159559 | 8252469 | 14830204 | 2966040 | 11864164 | 6988707 | 1221693 | 5767015 | 10412028 | 2159559 | 8252469 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2011 | Q4 | Q4 - 2011 | 1695000 | 694950 | 1000050 | 351306 | 144035 | 207271 | 1186306 | 486385 | 699921 | 10969239 | 766223 | 10203016 | 6731633 | 451961 | 6279672 | 8908306 | 604328 | 8303978 | 39000 | 7800 | 31200 | 47485 | 9498 | 37987 | 53905 | 10782 | 43123 | 1435485 | 996922 | 438563 | 1565294 | 980364 | 584930 | 1785294 | 1181964 | 603330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 435556 | 276429 | 159127 | 532460 | 345013 | 187447 | 45000 | 9000 | 36000 | 244 | 49 | 195 | 10619 | 2124 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 9131518 | 1862336 | 7269182 | 12476890 | 2630596 | 9846295 | 14830204 | 2966040 | 11864164 | 9131518 | 1862336 | 7269182 | 12476890 | 2630596 | 9846295 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2012 | Q1 | Q1 - 2012 | 1695000 | 694950 | 1000050 | 407655 | 167138 | 240517 | 813655 | 333598 | 480057 | 10969239 | 766223 | 10203016 | 7836571 | 629307 | 7207264 | 9284921 | 730691 | 8554230 | 39000 | 7800 | 31200 | 53881 | 10777 | 43104 | 60321 | 12065 | 48256 | 1435485 | 996922 | 438563 | 1565294 | 980364 | 584930 | 1585294 | 981964 | 603330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 502463 | 343336 | 159127 | 569367 | 410240 | 159127 | 45000 | 9000 | 36000 | 11219 | 2244 | 8975 | 11594 | 2319 | 9275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 10377083 | 2133166 | 8243917 | 12325152 | 2470877 | 9854275 | 14830204 | 2966040 | 11864164 | 10377083 | 2133166 | 8243917 | 12325152 | 2470877 | 9854275 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2012 | Q2 | Q2 - 2012 | 1695000 | 694950 | 1000050 | 453748 | 186036 | 267712 | 1185952 | 486240 | 699712 | 10969239 | 766223 | 10203016 | 8520629 | 677191 | 7843438 | 9847307 | 770058 | 9077249 | 39000 | 7800 | 31200 | 61929 | 12387 | 49542 | 69369 | 13875 | 55494 | 1435485 | 996922 | 438563 | 1565915 | 980413 | 585502 | 1585915 | 982013 | 603902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 584881 | 403530 | 181351 | 614881 | 405210 | 209671 | 45000 | 9000 | 36000 | 11219 | 2244 | 8975 | 31769 | 6354 | 25415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 11198321 | 2261801 | 8936520 | 13335193 | 2663750 | 10671443 | 14830204 | 2966040 | 11864164 | 11198321 | 2261801 | 8936520 | 13335193 | 2663750 | 10671443 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2012 | Q3 | Q3 - 2012 | 1695000 | 694950 | 1000050 | 1091827 | 447277 | 644550 | 1194327 | 489302 | 705025 | 10969239 | 766223 | 10203016 | 9158352 | 818449 | 8339903 | 10475352 | 818449 | 9656903 | 39000 | 7800 | 31200 | 69675 | 13868 | 55807 | 78097 | 15212 | 62885 | 1435485 | 996922 | 438563 | 1648699 | 1063197 | 585502 | 1849170 | 1228984 | 620186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 339102 | 129874 | 209228 | 490102 | 237450 | 252652 | 45000 | 9000 | 36000 | 32839 | 6568 | 26271 | 53839 | 10768 | 43071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 12340494 | 2479233 | 9861261 | 14140887 | 2800165 | 11340722 | 14830204 | 2966040 | 11864164 | 12340494 | 2479233 | 9861261 | 14140887 | 2800165 | 11340722 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2012 | Q4 | Q4 - 2012 | 1695000 | 694950 | 1000050 | 1098480 | 447277 | 651203 | 1192049 | 447277 | 744772 | 10969239 | 766223 | 10203016 | 10253648 | 951231 | 9302417 | 10253648 | 951231 | 9302417 | 39000 | 7800 | 31200 | 77739 | 13868 | 63871 | 90571 | 13868 | 76703 | 1435485 | 996922 | 438563 | 1755857 | 1150355 | 605502 | 1796875 | 1189373 | 607502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 378205 | 168977 | 209228 | 428095 | 218867 | 209228 | 45000 | 9000 | 36000 | 41139 | 7168 | 33971 | 54484 | 15713 | 38771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13605068 | 2738876 | 10866192 | 13815722 | 2836329 | 10979393 | 14830204 | 2966040 | 11864164 | 13605068 | 2738876 | 10866192 | 13815722 | 2836329 | 10979393 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2013 | Q1 | Q1 - 2013 | 1361740 | 460277 | 901463 | 1187992 | 447277 | 740715 | 1187992 | 447277 | 740715 | 10573648 | 961231 | 9612417 | 10156133 | 951231 | 9204902 | 10156133 | 951231 | 9204902 | 215713 | 38019 | 177694 | 91844 | 13868 | 77976 | 109844 | 13868 | 95976 | 1894495 | 1184904 | 709591 | 1740542 | 1134381 | 606161 | 1740542 | 1134381 | 606161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595124 | 285896 | 309228 | 447323 | 209071 | 238252 | 502323 | 254071 | 248252 | 189484 | 35713 | 153771 | 56614 | 17843 | 38771 | 56614 | 17843 | 38771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13680448 | 2773671 | 10906777 | 13753448 | 2818671 | 10934777 | 14830204 | 2966040 | 11864164 | 13680448 | 2773671 | 10906777 | 13753448 | 2818671 | 10934777 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2013 | Q2 | Q2 - 2013 | 1361740 | 460277 | 901463 | 1187992 | 447277 | 740715 | 1360816 | 459353 | 901463 | 10573648 | 961231 | 9612417 | 10186598 | 951231 | 9235367 | 10573648 | 961231 | 9612417 | 215713 | 38019 | 177694 | 119848 | 13868 | 105980 | 215713 | 38019 | 177694 | 1894495 | 1184904 | 709591 | 1791989 | 1185828 | 606161 | 1895419 | 1185828 | 709591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595124 | 285896 | 309228 | 479733 | 241481 | 238252 | 595124 | 285896 | 309228 | 189484 | 35713 | 153771 | 57074 | 17843 | 39231 | 189484 | 35713 | 153771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13823234 | 2857528 | 10965706 | 14830204 | 2966040 | 11864164 | 14830204 | 2966040 | 11864164 | 13823234 | 2857528 | 10965706 | 14830204 | 2966040 | 11864164 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570030 | INF | 2013 | Q3 | Q3 - 2013 | 1865962 | 505789 | 1360173 | 1645554 | 447277 | 1198277 | 1645554 | 447277 | 1198277 | 10386598 | 951231 | 9435367 | 10265436 | 951231 | 9314205 | 10265436 | 951231 | 9314205 | 155848 | 13868 | 141980 | 158742 | 13868 | 144874 | 158742 | 13868 | 144874 | 1791989 | 1185828 | 606161 | 1791989 | 1185828 | 606161 | 1791989 | 1185828 | 606161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567733 | 291481 | 276252 | 515504 | 289080 | 226424 | 515504 | 289080 | 226424 | 62074 | 17843 | 44231 | 57074 | 17843 | 39231 | 57074 | 17843 | 39231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 14434299 | 2905127 | 11529172 | 14434299 | 2905127 | 11529172 | 14830204 | 2966040 | 11864164 | 14434299 | 2905127 | 11529172 | 14434299 | 2905127 | 11529172 | 0 | 0 | De Kalb, County of (Inc.)
NT10BIX5570031 | INF | 2010 | Q3 | Q3 - 2010 | 56278640 | 2690000 | 53588640 | 0 | 0 | 0 | 27500000 | 2690000 | 24810000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 12500000 | 5000000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 51500 | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 99058 | 0 | 99058 | 4710240 | 2610240 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159823296 | 33500000 | 126323296 | 99058 | 0 | 99058 | 44761740 | 10300240 | 34461500 | 159823296 | 33500000 | 126323296 | 99058 | 0 | 99058 | 44761740 | 10300240 | 34461500 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2010 | Q4 | Q4 - 2010 | 56278640 | 2690000 | 53588640 | 27421187 | 3371582 | 24049605 | 36190000 | 2690000 | 33500000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 16200000 | 5000000 | 11200000 | 0 | 0 | 0 | 21047 | 0 | 21047 | 75500 | 0 | 75500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 1331778 | 420489 | 911289 | 5110240 | 2610240 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159823296 | 33500000 | 126323296 | 28774012 | 3792071 | 24981941 | 57575740 | 10300240 | 47275500 | 159823296 | 33500000 | 126323296 | 28774012 | 3792071 | 24981941 | 57575740 | 10300240 | 47275500 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2011 | Q1 | Q1 - 2011 | 56278640 | 2690000 | 53588640 | 28087957 | 3371583 | 24716375 | 27832457 | 2432457 | 25400000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 33386055 | 27386055 | 6000000 | 0 | 0 | 0 | 46138 | 0 | 46138 | 200000 | 105000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 1745444 | 0 | 1745444 | 2600000 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 420488 | 420488 | 0 | 495488 | 420488 | 75000 | 159823296 | 33500000 | 126323296 | 30300027 | 3792071 | 26507957 | 65514000 | 30344000 | 35170000 | 159823296 | 33500000 | 126323296 | 30300027 | 3792071 | 26507957 | 65514000 | 30344000 | 35170000 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2011 | Q2 | Q2 - 2011 | 53236719 | 2432457 | 50804262 | 29400388 | 2432457 | 26967931 | 51682457 | 2432457 | 49250000 | 82322630 | 30542055 | 51780575 | 26712640 | 25886055 | 826585 | 36242055 | 30542055 | 5700000 | 3980000 | 105000 | 3875000 | 81776 | 0 | 81776 | 775000 | 25000 | 750000 | 463200 | 0 | 463200 | 260280 | 0 | 260280 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 1557660 | 0 | 1557660 | 3950000 | 0 | 3950000 | 7407800 | 0 | 7407800 | 555725 | 0 | 555725 | 2200000 | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 412367 | 0 | 412367 | 525000 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 429470 | 420488 | 8982 | 455488 | 420488 | 35000 | 159823296 | 33500000 | 126323296 | 59410306 | 28739000 | 30671306 | 96130000 | 33420000 | 62710000 | 159823296 | 33500000 | 126323296 | 59410306 | 28739000 | 30671306 | 96130000 | 33420000 | 62710000 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2011 | Q3 | Q3 - 2011 | 53236719 | 2432457 | 50804262 | 29006260 | 1624457 | 27381803 | 40056260 | 1624457 | 38431803 | 82322630 | 30542055 | 51780575 | 28769673 | 25886055 | 2883618 | 32812492 | 25886055 | 6926437 | 3980000 | 105000 | 3875000 | 102008 | 0 | 102008 | 374550 | 25000 | 349550 | 463200 | 0 | 463200 | 327300 | 0 | 327300 | 463200 | 0 | 463200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 2325416 | 0 | 2325416 | 4632000 | 0 | 4632000 | 7407800 | 0 | 7407800 | 910961 | 0 | 910961 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 452812 | 420488 | 32324 | 453952 | 420488 | 33464 | 159823296 | 33500000 | 126323296 | 61894430 | 27931000 | 33963430 | 80042454 | 27956000 | 52086454 | 159823296 | 33500000 | 126323296 | 61894430 | 27931000 | 33963430 | 80042454 | 27956000 | 52086454 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2011 | Q4 | Q4 - 2011 | 53236719 | 2432457 | 50804262 | 34050562 | 2432457 | 31618105 | 44154657 | 2432457 | 41722200 | 82322630 | 30542055 | 51780575 | 33807730 | 29788191 | 4019539 | 39207730 | 29788191 | 9419539 | 3980000 | 105000 | 3875000 | 224031 | 77951 | 146080 | 294031 | 77951 | 216080 | 463200 | 0 | 463200 | 327300 | 0 | 327300 | 377300 | 0 | 377300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 5327590 | 0 | 5327590 | 6327590 | 0 | 6327590 | 7407800 | 0 | 7407800 | 1246748 | 0 | 1246748 | 2096740 | 0 | 2096740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 24573 | 0 | 24573 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 477303 | 420488 | 56815 | 482988 | 420488 | 62500 | 159823296 | 33500000 | 126323296 | 75485837 | 32719087 | 42766750 | 92971036 | 32719087 | 60251949 | 159823296 | 33500000 | 126323296 | 75485837 | 32719087 | 42766750 | 92971036 | 32719087 | 60251949 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2012 | Q1 | Q1 - 2012 | 56736719 | 2432457 | 54304262 | 41770133 | 2432457 | 39337676 | 54707457 | 2432457 | 52275000 | 78722630 | 30542055 | 48180575 | 34484641 | 29788191 | 4696450 | 42013191 | 29788191 | 12225000 | 3980000 | 105000 | 3875000 | 281125 | 77951 | 203174 | 398176 | 77951 | 320225 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 385763 | 0 | 385763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 8023334 | 0 | 8023334 | 9110000 | 0 | 9110000 | 7407800 | 0 | 7407800 | 1636920 | 0 | 1636920 | 2733000 | 0 | 2733000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 30853 | 0 | 30853 | 225300 | 0 | 225300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 487632 | 420488 | 67144 | 687632 | 420488 | 267144 | 159823296 | 33500000 | 126323296 | 87050401 | 32719087 | 54331314 | 110260519 | 32719087 | 77541432 | 159823296 | 33500000 | 126323296 | 87050401 | 32719087 | 54331314 | 110260519 | 32719087 | 77541432 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2012 | Q2 | Q2 - 2012 | 56736719 | 2432457 | 54304262 | 42109385 | 2432457 | 39676928 | 49337676 | 2432457 | 46905219 | 78722630 | 30542055 | 48180575 | 35420578 | 29788191 | 5632387 | 51113560 | 29788191 | 21325369 | 3980000 | 105000 | 3875000 | 605717 | 77951 | 527766 | 867585 | 77951 | 789634 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 429763 | 0 | 429763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 9215170 | 0 | 9215170 | 9560170 | 0 | 9560170 | 7407800 | 0 | 7407800 | 1843602 | 0 | 1843602 | 1843602 | 0 | 1843602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 325272 | 0 | 325272 | 325272 | 0 | 325272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 494364 | 420488 | 73876 | 496362 | 420488 | 75874 | 159823296 | 33500000 | 126323296 | 90349851 | 32719087 | 57630764 | 113973990 | 32719087 | 81254903 | 159823296 | 33500000 | 126323296 | 90349851 | 32719087 | 57630764 | 113973990 | 32719087 | 81254903 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2012 | Q3 | Q3 - 2012 | 56736719 | 2432457 | 54304262 | 47585623 | 2432457 | 45153166 | 51557457 | 2432457 | 49125000 | 78722630 | 30542055 | 48180575 | 41209142 | 29788191 | 11420951 | 53203000 | 30703000 | 22500000 | 3980000 | 105000 | 3875000 | 733097 | 77951 | 655146 | 1030000 | 105000 | 925000 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 375000 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 10192877 | 0 | 10192877 | 10500000 | 0 | 10500000 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 2525000 | 0 | 2525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 475000 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 495924 | 420488 | 75436 | 348043 | 259543 | 88500 | 159823296 | 33500000 | 126323296 | 103130089 | 32719087 | 70411002 | 120013500 | 33500000 | 86513500 | 159823296 | 33500000 | 126323296 | 103130089 | 32719087 | 70411002 | 120013500 | 33500000 | 86513500 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2012 | Q4 | Q4 - 2012 | 56736719 | 6203000 | 50533719 | 55783639 | 6203000 | 49580639 | 56169176 | 6203000 | 49966176 | 78722630 | 27192000 | 51530630 | 42608993 | 27192000 | 15416993 | 52692355 | 27192000 | 25500355 | 3980000 | 105000 | 3875000 | 987810 | 105000 | 882810 | 1455000 | 105000 | 1350000 | 463200 | 0 | 463200 | 409965 | 0 | 409965 | 463200 | 0 | 463200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 10896509 | 0 | 10896509 | 12500000 | 0 | 12500000 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 3130000 | 0 | 3130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 525000 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 90726 | 0 | 90726 | 575000 | 0 | 575000 | 159823296 | 33500000 | 126323296 | 113355305 | 33500000 | 79855305 | 127509731 | 33500000 | 94009731 | 159823296 | 33500000 | 126323296 | 113355305 | 33500000 | 79855305 | 127509731 | 33500000 | 94009731 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2013 | Q1 | Q1 - 2013 | 56736719 | 6203000 | 50533719 | 55796705 | 6203000 | 49593705 | 56296705 | 6203000 | 50093705 | 78722630 | 27192000 | 51530630 | 43413472 | 27192000 | 16221472 | 56163472 | 27192000 | 28971472 | 3980000 | 105000 | 3875000 | 1506569 | 105000 | 1401569 | 2030000 | 105000 | 1925000 | 463200 | 0 | 463200 | 409965 | 0 | 409965 | 434500 | 0 | 434500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 12112739 | 0 | 12112739 | 12225800 | 0 | 12225800 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 4150000 | 0 | 4150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 625000 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 121319 | 0 | 121319 | 225000 | 0 | 225000 | 159823296 | 33500000 | 126323296 | 115938432 | 33500000 | 82438432 | 132150477 | 33500000 | 98650477 | 159823296 | 33500000 | 126323296 | 115938432 | 33500000 | 82438432 | 132150477 | 33500000 | 98650477 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2013 | Q2 | Q2 - 2013 | 56736719 | 6203000 | 50533719 | 55796705 | 6203000 | 49593705 | 56736719 | 6203000 | 50533719 | 78722630 | 27192000 | 51530630 | 47640821 | 27192000 | 20448821 | 69640821 | 27192000 | 42448821 | 3830000 | 105000 | 3725000 | 2064630 | 105000 | 1959630 | 3364630 | 105000 | 3259630 | 538200 | 0 | 538200 | 409965 | 0 | 409965 | 538200 | 0 | 538200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13270236 | 0 | 13270236 | 12112739 | 0 | 12112739 | 13270236 | 0 | 13270236 | 5407800 | 0 | 5407800 | 2130001 | 0 | 2130001 | 3405000 | 0 | 3405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 700000 | 677237 | 0 | 677237 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 130000 | 0 | 130000 | 205000 | 0 | 205000 | 159823296 | 33500000 | 126323296 | 120962098 | 33500000 | 87462098 | 147860606 | 33500000 | 114360606 | 159823296 | 33500000 | 126323296 | 120962098 | 33500000 | 87462098 | 147860606 | 33500000 | 114360606 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2013 | Q3 | Q3 - 2013 | 56736719 | 6203000 | 50533719 | 55796822 | 6203000 | 49593705 | 56736719 | 6203000 | 50533719 | 78722630 | 27192000 | 51530630 | 49811115 | 27192000 | 22619115 | 67392800 | 27192000 | 40200800 | 3830000 | 105000 | 3725000 | 2687046 | 105000 | 2536056 | 3100000 | 105000 | 2995000 | 538200 | 0 | 538200 | 409965 | 0 | 409965 | 425000 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13270236 | 0 | 13270236 | 12404958 | 0 | 12404958 | 13150100 | 0 | 13150100 | 5407800 | 0 | 5407800 | 2130001 | 0 | 2130001 | 5125000 | 0 | 5125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 700000 | 677237 | 0 | 677237 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 146416 | 0 | 144426 | 200000 | 0 | 200000 | 159823296 | 33500000 | 126323296 | 124063560 | 33500000 | 90515463 | 146829619 | 33500000 | 113329619 | 159823296 | 33500000 | 126323296 | 124063560 | 33500000 | 90515463 | 146829619 | 33500000 | 113329619 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570031 | INF | 2013 | Q4 | Q4 - 2013 | 55572909 | 2646342 | 52926567 | 55572909 | 2646342 | 52926567 | 55572909 | 2646342 | 52926567 | 84320609 | 30748658 | 53571951 | 82372311 | 30748658 | 51623653 | 82372311 | 30748658 | 51623653 | 3160851 | 105000 | 3055851 | 3160851 | 105000 | 3055851 | 3160851 | 105000 | 3055851 | 554403 | 0 | 554403 | 554403 | 0 | 554403 | 554403 | 0 | 554403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13530373 | 0 | 13530373 | 13530373 | 0 | 13530373 | 13530373 | 0 | 13530373 | 489954 | 0 | 489954 | 489954 | 0 | 489954 | 489954 | 0 | 489954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103280 | 0 | 2103280 | 2103280 | 0 | 2103280 | 2103280 | 0 | 2103280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90917 | 0 | 90917 | 90917 | 0 | 90917 | 90917 | 0 | 90917 | 159823296 | 33500000 | 126323296 | 157874998 | 33500000 | 124374998 | 157874998 | 33500000 | 124374998 | 159823296 | 33500000 | 126323296 | 157874998 | 33500000 | 124374998 | 157874998 | 33500000 | 124374998 | 0 | 0 | Executive Office State of West Virginia
NT10BIX5570032 | INF | 2010 | Q3 | Q3 - 2010 | 1538655 | 0 | 1538675 | 0 | 0 | 0 | 0 | 0 | 0 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 50000 | 0 | 50000 | 39000 | 39000 | 0 | 37469 | 37469 | 0 | 38270 | 38270 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 184480 | 0 | 184480 | 300000 | 10000 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 5400 | 884 | 4500 | 10439035 | 2113505 | 8325550 | 226576 | 38353 | 188223 | 413670 | 49154 | 364500 | 10439035 | 2113505 | 8325550 | 226576 | 38353 | 188223 | 413670 | 49154 | 364500 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2010 | Q4 | Q4 - 2010 | 1538655 | 0 | 1538678 | 0 | 0 | 0 | 100000 | 0 | 100000 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 50000 | 0 | 50000 | 39000 | 39000 | 0 | 38467 | 41115 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 289722 | 0 | 289005 | 320000 | 20000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40070 | 4627 | 884 | 3743 | 5400 | 884 | 4516 | 10439035 | 2113505 | 8325153 | 332816 | 41999 | 292748 | 531867 | 77351 | 454516 | 10439035 | 2113505 | 8325153 | 332816 | 41999 | 292748 | 531867 | 77351 | 454516 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2011 | Q1 | Q1 - 2011 | 1538655 | 0 | 1538678 | 0 | 0 | 0 | 0 | 0 | 0 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 100000 | 0 | 100000 | 39000 | 39000 | 0 | 38467 | 38467 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 398170 | 14000 | 384170 | 469170 | 67000 | 402170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 4627 | 884 | 3743 | 10439035 | 2113505 | 8325553 | 441264 | 53351 | 387913 | 630264 | 124351 | 505913 | 10439035 | 2113505 | 8325553 | 441264 | 53351 | 387913 | 630264 | 124351 | 505913 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2011 | Q2 | Q2 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 250000 | 0 | 250000 | 8390480 | 2030505 | 6359975 | 1763664 | 1644581 | 0 | 2313664 | 1763664 | 550000 | 39000 | 39000 | 0 | 38467 | 38467 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 522533 | 79732 | 439058 | 522533 | 79732 | 442801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 6650 | 0 | 6650 | 10439035 | 2113505 | 8325530 | 2329291 | 1763664 | 442801 | 3149314 | 1899863 | 1249451 | 10439035 | 2113505 | 8325530 | 2329291 | 1763664 | 442801 | 3149314 | 1899863 | 1249451 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2011 | Q3 | Q3 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 250000 | 0 | 250000 | 8390480 | 2030505 | 6359975 | 2033502 | 1675661 | 357841 | 2488139 | 1876502 | 611637 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 402533 | 48475 | 354058 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 6650 | 0 | 6650 | 10439035 | 2113505 | 8325530 | 2479973 | 1764331 | 715642 | 3225005 | 1982288 | 1242717 | 10439035 | 2113505 | 8325530 | 2479973 | 1764331 | 715642 | 3225005 | 1982288 | 1242717 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2011 | Q4 | Q4 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 1072044 | 0 | 1072044 | 8390480 | 2030505 | 6359975 | 3195525 | 1885310 | 1221545 | 4067310 | 1867310 | 2200000 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18500 | 18000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 471380 | 48475 | 422905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 5461 | 884 | 4577 | 5780 | 884 | 4897 | 10439035 | 2113505 | 8325530 | 3663202 | 1973980 | 1600552 | 5674325 | 1973980 | 3700346 | 10439035 | 2113505 | 8325530 | 3663202 | 1973980 | 1600552 | 5674325 | 1973980 | 3700346 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2012 | Q1 | Q1 - 2012 | 1538655 | 0 | 1538655 | 943642 | 0 | 943642 | 950000 | 0 | 950000 | 8390480 | 2030505 | 6359975 | 4693139 | 1890734 | 2802405 | 5878760 | 1890734 | 3988026 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 5461 | 884 | 4577 | 10268 | 884 | 9384 | 10439035 | 2113505 | 8325530 | 6104458 | 1979404 | 4125054 | 7319244 | 1997404 | 5321840 | 10439035 | 2113505 | 8325530 | 6104458 | 1979404 | 4125054 | 7319244 | 1997404 | 5321840 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2012 | Q2 | Q2 - 2012 | 1538655 | 0 | 1538655 | 943642 | 0 | 943642 | 960000 | 0 | 960000 | 8390480 | 2030505 | 6359975 | 5625426 | 1894731 | 3730695 | 6200000 | 1930000 | 4270000 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 18000 | 18000 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7538 | 884 | 6654 | 10439035 | 2113505 | 8325530 | 7056392 | 2001401 | 5054991 | 7647754 | 2036670 | 5611084 | 10439035 | 2113505 | 8325530 | 7056392 | 2001401 | 5054991 | 7647754 | 2036670 | 5611084 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2012 | Q3 | Q3 - 2012 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 5799941 | 1894731 | 3905210 | 6940000 | 2030505 | 4909495 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7538 | 884 | 6654 | 10439035 | 2113505 | 8325530 | 7445266 | 2001401 | 5443865 | 8978409 | 2137175 | 6841234 | 10439035 | 2113505 | 8325530 | 7445266 | 2001401 | 5443865 | 8978409 | 2137175 | 6841234 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2012 | Q4 | Q4 - 2012 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1396500 | 0 | 1396500 | 8390480 | 2030505 | 6359975 | 6775416 | 1957412 | 4849435 | 7525416 | 2030505 | 5494911 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7500 | 884 | 6616 | 10439035 | 2113505 | 8325530 | 8420741 | 2064082 | 6388090 | 9421632 | 2137175 | 7284457 | 10439035 | 2113505 | 8325530 | 8420741 | 2064082 | 6388090 | 9421632 | 2137175 | 7284457 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2013 | Q1 | Q1 - 2013 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 7375037 | 2030505 | 5463056 | 8196480 | 2036505 | 6159975 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 36000 | 24000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7500 | 884 | 6616 | 10439035 | 2113505 | 8325530 | 9020362 | 2137175 | 7001711 | 10240851 | 2149175 | 8091676 | 10439035 | 2113505 | 8325530 | 9020362 | 2137175 | 7001711 | 10240851 | 2149175 | 8091676 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2013 | Q2 | Q2 - 2013 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 8092165 | 1962935 | 6129230 | 8347056 | 2006835 | 6340221 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 93311 | 39311 | 54000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7108 | 884 | 6224 | 10439035 | 2113505 | 8325530 | 9737490 | 2069605 | 7667885 | 10439035 | 2113505 | 8325530 | 10439035 | 2113505 | 8325530 | 9737490 | 2069605 | 7667885 | 10439035 | 2113505 | 8325530 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2013 | Q3 | Q3 - 2013 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 8390475 | 2030505 | 6359970 | 8326079 | 2006835 | 6319244 | 8326079 | 2006835 | 6319244 | 39000 | 39000 | 0 | 110000 | 39311 | 70689 | 110000 | 39311 | 70689 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 8438 | 884 | 7554 | 8438 | 884 | 7554 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 0 | 0 | Lane Council of Government
NT10BIX5570032 | INF | 2013 | Q4 | Q4 - 2013 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 8390475 | 2030505 | 6359970 | 8326079 | 2006835 | 6319244 | 8326079 | 2006835 | 6319244 | 39000 | 39000 | 0 | 110000 | 39311 | 70689 | 110000 | 39311 | 70689 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 8438 | 884 | 7554 | 8438 | 884 | 7554 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 0 | 0 | Lane Council of Government
NT10BIX5570033 | INF | 2010 | Q3 | Q3 - 2010 | 7489453 | 0 | 7489453 | 0 | 0 | 0 | 0 | 0 | 0 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 0 | 0 | 0 | 1202000 | 0 | 1202000 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 4805650 | 3412500 | 1393150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 16343674 | 3412500 | 12931174 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2010 | Q4 | Q4 - 2010 | 7489453 | 0 | 7489453 | 44000 | 0 | 44000 | 64000 | 0 | 64000 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 0 | 0 | 0 | 1202000 | 0 | 1202000 | 490455 | 0 | 490455 | 560285 | 0 | 560285 | 4805650 | 3412500 | 1393150 | 4000 | 4000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 0 | 0 | 0 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 538455 | 4000 | 534455 | 689285 | 30000 | 659285 | 16343674 | 3412500 | 12931174 | 538455 | 4000 | 534455 | 689285 | 30000 | 659285 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2011 | Q1 | Q1 - 2011 | 7489453 | 0 | 7489453 | 44000 | 0 | 44000 | 156000 | 0 | 156000 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 6300 | 0 | 6300 | 1202000 | 0 | 1202000 | 574744 | 0 | 574744 | 668574 | 0 | 668574 | 4805650 | 3412500 | 1393150 | 8750 | 6250 | 2500 | 280750 | 156250 | 124500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 65125 | 0 | 65125 | 97125 | 0 | 97125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 692619 | 6250 | 686369 | 1208749 | 156250 | 1052499 | 16343674 | 3412500 | 12931174 | 692619 | 6250 | 686369 | 1208749 | 156250 | 1052499 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2011 | Q2 | Q2 - 2011 | 7489453 | 0 | 7489453 | 178804 | 0 | 178804 | 1569454 | 0 | 1569454 | 2038396 | 0 | 2038396 | 13665 | 0 | 13665 | 68665 | 0 | 68665 | 1202000 | 0 | 1202000 | 702630 | 0 | 702630 | 848630 | 0 | 848630 | 4805650 | 3412500 | 1393150 | 208044 | 158750 | 49294 | 1113048 | 858750 | 254294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 107250 | 0 | 107250 | 147250 | 0 | 147250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 90000 | 0 | 90000 | 16343674 | 3412500 | 12931174 | 1210393 | 158750 | 1051643 | 3837047 | 858750 | 2978293 | 16343674 | 3412500 | 12931174 | 1210393 | 158750 | 1051643 | 3837047 | 858750 | 2978293 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2011 | Q3 | Q3 - 2011 | 7429453 | 0 | 7429453 | 355076 | 0 | 355076 | 3551076 | 0 | 3551076 | 2038396 | 0 | 2038396 | 16534 | 0 | 16534 | 289534 | 0 | 289534 | 1662000 | 400000 | 1262000 | 882616 | 46562 | 836054 | 1065616 | 109562 | 956054 | 4405650 | 3012500 | 1393150 | 785294 | 687600 | 97694 | 1266293 | 1028599 | 237694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 137150 | 0 | 137150 | 167150 | 0 | 167150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 7527 | 0 | 7527 | 343526 | 0 | 343526 | 16343674 | 3412500 | 12931174 | 2184197 | 734162 | 1450035 | 6683195 | 1138161 | 5545034 | 16343674 | 3412500 | 12931174 | 2184197 | 734162 | 1450035 | 6683195 | 1138161 | 5545034 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2011 | Q4 | Q4 - 2011 | 7429453 | 0 | 7429453 | 3077422 | 0 | 3077422 | 6611422 | 0 | 6611422 | 2038396 | 0 | 2038396 | 185566 | 0 | 185566 | 869566 | 0 | 869566 | 1662000 | 400000 | 1262000 | 1066991 | 92062 | 974929 | 1236991 | 132062 | 1104929 | 4405650 | 3012500 | 1393150 | 1036567 | 887443 | 149124 | 2161568 | 1927443 | 234124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 151875 | 0 | 151875 | 172875 | 0 | 172875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 187438 | 0 | 187438 | 453438 | 0 | 453438 | 16343674 | 3412500 | 12931174 | 5705859 | 979505 | 4726354 | 11505860 | 2059505 | 9446354 | 16343674 | 3412500 | 12931174 | 5705859 | 979505 | 4726354 | 11505860 | 2059505 | 9446354 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2012 | Q1 | Q1 - 2012 | 7429453 | 0 | 7429453 | 7127939 | 0 | 7127939 | 7427939 | 0 | 7427939 | 2038396 | 0 | 2038396 | 338054 | 0 | 338054 | 1178054 | 0 | 1178054 | 1662000 | 400000 | 1262000 | 1252761 | 130006 | 1122755 | 1438761 | 177006 | 1261755 | 4405650 | 3012500 | 1393150 | 2523235 | 2045749 | 477486 | 2830235 | 2189749 | 640486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 157000 | 0 | 157000 | 162000 | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 416651 | 0 | 416651 | 437651 | 0 | 437651 | 16343674 | 3412500 | 12931174 | 11815640 | 2175755 | 9639885 | 13474640 | 2366755 | 11107885 | 16343674 | 3412500 | 12931174 | 11815640 | 2175755 | 9639885 | 13474640 | 2366755 | 11107885 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2012 | Q2 | Q2 - 2012 | 7704173 | 0 | 7704173 | 7300949 | 0 | 7300949 | 7409949 | 0 | 7409949 | 1754595 | 0 | 1754595 | 615302 | 0 | 615302 | 1124302 | 0 | 1124302 | 1904782 | 645219 | 1259563 | 1495395 | 238270 | 1257125 | 1697833 | 438270 | 1259563 | 4374703 | 2767281 | 1607422 | 3301722 | 2135649 | 1166073 | 3954722 | 2375649 | 1579073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448421 | 0 | 448421 | 425257 | 0 | 425257 | 432887 | 0 | 432887 | 16343674 | 3412500 | 12931174 | 13295625 | 2373919 | 10921706 | 14776693 | 2813919 | 11962774 | 16343674 | 3412500 | 12931174 | 13295625 | 2373919 | 10921706 | 14776693 | 2813919 | 11962774 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2012 | Q3 | Q3 - 2012 | 7704173 | 0 | 7704173 | 7386339 | 0 | 7386339 | 7704173 | 0 | 7704173 | 1754595 | 0 | 1754595 | 724779 | 0 | 724779 | 1683780 | 0 | 1683780 | 1904782 | 645219 | 1259563 | 1695070 | 437132 | 1257938 | 1885070 | 625507 | 1259563 | 4374703 | 2767281 | 1607422 | 3642747 | 2161022 | 1481725 | 3937443 | 2330022 | 1607421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448421 | 0 | 448421 | 429768 | 0 | 429768 | 448421 | 0 | 448421 | 16343674 | 3412500 | 12931174 | 14035703 | 2598154 | 11437549 | 15815887 | 2955529 | 12860358 | 16343674 | 3412500 | 12931174 | 14035703 | 2598154 | 11437549 | 15815887 | 2955529 | 12860358 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2012 | Q4 | Q4 - 2012 | 7902256 | 119659 | 7782597 | 7782598 | 0 | 7782598 | 7896274 | 113676 | 7782598 | 1902043 | 190119 | 1711924 | 1483722 | 0 | 1483722 | 1881127 | 169203 | 1711924 | 2006759 | 747150 | 1259609 | 1885717 | 626108 | 1259609 | 2004919 | 745310 | 1259609 | 3936561 | 2355572 | 1580989 | 3864561 | 2283572 | 1580989 | 3936561 | 2355572 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439055 | 0 | 439055 | 439054 | 0 | 439054 | 439055 | 0 | 439055 | 16343674 | 3412500 | 12931174 | 15612652 | 2909680 | 12702972 | 16314936 | 3383761 | 12931175 | 16343674 | 3412500 | 12931174 | 15612652 | 2909680 | 12702972 | 16314936 | 3383761 | 12931175 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2013 | Q1 | Q1 - 2013 | 7902256 | 119659 | 7782597 | 7809803 | 27205 | 7782598 | 7902256 | 119659 | 7782597 | 1902043 | 190119 | 1711924 | 1593513 | 24000 | 1569513 | 1902043 | 190119 | 1711924 | 2006759 | 747150 | 1259609 | 1994750 | 735141 | 1259609 | 2006759 | 747150 | 1259609 | 3936561 | 2355572 | 1580989 | 3869661 | 2288672 | 1580989 | 3936561 | 2355572 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439055 | 0 | 439055 | 439055 | 0 | 439054 | 439055 | 0 | 439055 | 16343674 | 3412500 | 12931174 | 15863782 | 3075018 | 12788763 | 16343674 | 3412500 | 12931174 | 16343674 | 3412500 | 12931174 | 15863782 | 3075018 | 12788763 | 16343674 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2013 | Q2 | Q2 - 2013 | 7742060 | 90946 | 7651114 | 7692675 | 41561 | 7651114 | 7742060 | 90946 | 7651114 | 1875258 | 24000 | 1851258 | 1839004 | 24000 | 1815004 | 1875258 | 24000 | 1851258 | 2230041 | 970432 | 1259609 | 2230041 | 970432 | 1259609 | 2230041 | 970432 | 1259609 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 16343674 | 3412500 | 12931174 | 16258035 | 3363115 | 12894920 | 16343674 | 3412500 | 12931174 | 16343674 | 3412500 | 12931174 | 16258035 | 3363115 | 12894920 | 16343674 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570033 | INF | 2013 | Q3 | Q3 - 2013 | 7712648 | 61534 | 7651114 | 7712648 | 61534 | 7651114 | 7712648 | 61534 | 7651114 | 1876517 | 25258 | 1851258 | 1876517 | 25258 | 1851258 | 1876517 | 25258 | 1851258 | 2258195 | 998586 | 1259609 | 2258195 | 998586 | 1259609 | 2258195 | 998586 | 1259609 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO)
NT10BIX5570034 | INF | 2010 | Q3 | Q3 - 2010 | 5462091 | 535825 | 4926266 | 0 | 0 | 0 | 2680965 | 131548 | 2549417 | 3000000 | 294296 | 2705704 | 81289 | 16258 | 65031 | 466000 | 23300 | 442700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743207 | 171007 | 1572200 | 3480 | 696 | 2784 | 1186350 | 59317 | 1127033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 8829 | 81171 | 9435 | 1887 | 7548 | 90000 | 4500 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | 10889 | 100111 | 0 | 0 | 0 | 111000 | 5550 | 105450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325517 | 1325517 | 0 | 0 | 0 | 0 | 938815 | 938815 | 0 | 11731815 | 2346363 | 9385452 | 94204 | 18841 | 75363 | 5473130 | 1163030 | 4310100 | 11731815 | 2346363 | 9385452 | 94204 | 18841 | 75363 | 5473130 | 1163030 | 4310100 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2010 | Q4 | Q4 - 2010 | 5462091 | 535825 | 4926266 | 2919671 | 487062 | 2432609 | 4613671 | 666020 | 3947651 | 2660000 | 260943 | 2399057 | 501861 | 96086 | 405775 | 1197861 | 235286 | 962575 | 15000 | 1472 | 13528 | 0 | 0 | 0 | 14500 | 2900 | 11600 | 1993207 | 195531 | 1797676 | 593302 | 42789 | 550513 | 962558 | 116640 | 845918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 8829 | 81171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 18246 | 167754 | 146574 | 0 | 146574 | 146574 | 0 | 146574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325517 | 1325517 | 0 | 0 | 0 | 0 | 937608 | 937608 | 0 | 11731815 | 2346363 | 9385452 | 4161408 | 625937 | 3535471 | 7872772 | 1958454 | 5914318 | 11731815 | 2346363 | 9385452 | 4161408 | 625937 | 3535471 | 7872772 | 1958454 | 5914318 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2011 | Q1 | Q1 - 2011 | 5462091 | 562086 | 4900005 | 4435531 | 562086 | 3873445 | 4647530 | 562086 | 4085444 | 2446157 | 99675 | 2346482 | 1083592 | 99675 | 983917 | 1451592 | 99675 | 1351917 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1106550 | 96134 | 1010416 | 1334550 | 96133 | 1238417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 899774 | 899774 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 7714846 | 1670743 | 6044103 | 9252431 | 2400328 | 6852103 | 11731815 | 2400329 | 9331486 | 7714846 | 1670743 | 6044103 | 9252431 | 2400328 | 6852103 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2011 | Q2 | Q2 - 2011 | 5462091 | 562086 | 4900005 | 4552353 | 562086 | 3990267 | 4742003 | 562086 | 4179917 | 2446157 | 99675 | 2346482 | 1327063 | 99675 | 1227388 | 1590562 | 99675 | 1490887 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1220185 | 96134 | 1124051 | 1463185 | 96134 | 1367051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 8918360 | 2400329 | 6518031 | 9614509 | 2400329 | 7214180 | 11731815 | 2400329 | 9331486 | 8918360 | 2400329 | 6518031 | 9614509 | 2400329 | 7214180 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2011 | Q3 | Q3 - 2011 | 5462091 | 562086 | 4900005 | 5037138 | 562086 | 4475052 | 5088138 | 562086 | 4526052 | 2446157 | 99675 | 2346482 | 1560576 | 99675 | 1460901 | 1728408 | 99675 | 1628733 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1247604 | 96134 | 1151470 | 1273925 | 96134 | 1177791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 9664077 | 2400329 | 7263748 | 9909230 | 2400329 | 7508901 | 11731815 | 2400329 | 9331486 | 9664077 | 2400329 | 7263748 | 9909230 | 2400329 | 7508901 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2011 | Q4 | Q4 - 2011 | 5462091 | 562086 | 4900005 | 5065183 | 562086 | 4503097 | 5290183 | 562086 | 4728097 | 2446157 | 99675 | 2346482 | 2013792 | 99675 | 1914117 | 2114309 | 99675 | 2014634 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1429827 | 96134 | 1333693 | 1494827 | 96134 | 1398693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10327561 | 2400329 | 7927232 | 10718078 | 2400329 | 8317749 | 11731815 | 2400329 | 9331486 | 10327561 | 2400329 | 7927232 | 10718078 | 2400329 | 8317749 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2012 | Q1 | Q1 - 2012 | 5462091 | 562086 | 4900005 | 5112409 | 562086 | 4550323 | 5368409 | 562086 | 4806323 | 2446157 | 99675 | 2346482 | 2063558 | 99675 | 1963883 | 2164075 | 99675 | 2064400 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1444017 | 96134 | 1347883 | 1509017 | 96134 | 1412883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10438743 | 2400329 | 8038414 | 10860260 | 2400329 | 8459931 | 11731815 | 2400329 | 9331486 | 10438743 | 2400329 | 8038414 | 10860260 | 2400329 | 8459931 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2012 | Q2 | Q2 - 2012 | 5462091 | 562086 | 4900005 | 5124433 | 562086 | 4562347 | 5380433 | 562086 | 4818347 | 2446157 | 99675 | 2346482 | 2101420 | 99675 | 2001745 | 2117920 | 99675 | 2018245 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1508183 | 96134 | 1412049 | 1536183 | 96134 | 1440049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10552795 | 2400329 | 8152466 | 10853295 | 2400329 | 8452966 | 11731815 | 2400329 | 9331486 | 10552795 | 2400329 | 8152466 | 10853295 | 2400329 | 8452966 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2012 | Q3 | Q3 - 2012 | 5462091 | 562086 | 4900005 | 5123383 | 562086 | 4561297 | 5655288 | 562086 | 5093202 | 2446157 | 99675 | 2346482 | 2113140 | 99675 | 2013465 | 2113890 | 99675 | 2014215 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1530086 | 96134 | 1433952 | 1639667 | 96134 | 1543533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10585368 | 2400329 | 8185039 | 11227604 | 2400329 | 8827275 | 11731815 | 2400329 | 9331486 | 10585368 | 2400329 | 8185039 | 11227604 | 2400329 | 8827275 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2012 | Q4 | Q4 - 2012 | 5462091 | 562086 | 4900005 | 5400288 | 562086 | 4838202 | 5400288 | 562086 | 4838202 | 2446157 | 99675 | 2346482 | 2109366 | 99675 | 2009691 | 2109366 | 99675 | 2009691 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1530086 | 96134 | 1433952 | 1530086 | 96134 | 1433952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10858499 | 2400329 | 8458170 | 10858499 | 2400329 | 8458170 | 11731815 | 2400329 | 9331486 | 10858499 | 2400329 | 8458170 | 10858499 | 2400329 | 8458170 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570034 | INF | 2013 | Q1 | Q1 - 2013 | 5462091 | 562086 | 4900005 | 5400288 | 562086 | 4838202 | 5400288 | 562086 | 4838202 | 2446157 | 99675 | 2346482 | 1916228 | 99675 | 1816553 | 1916228 | 99675 | 1816553 | 15000 | 0 | 15000 | 75192 | 0 | 75192 | 75192 | 0 | 75192 | 1993207 | 96134 | 1897073 | 1526291 | 96134 | 1430157 | 1526291 | 96134 | 1430157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10723197 | 2400329 | 8322868 | 10723197 | 2400329 | 8322868 | 11731815 | 2400329 | 9331486 | 10723197 | 2400329 | 8322868 | 10723197 | 2400329 | 8322868 | 0 | 0 | DeltaCom, Inc.
NT10BIX5570035 | INF | 2010 | Q3 | Q3 - 2010 | 947990 | 381962 | 566028 | 75481 | 75481 | 0 | 75481 | 75481 | 0 | 2186252 | 432142 | 1754110 | 355284 | 355284 | 0 | 355284 | 355284 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 205133 | 4983 | 200150 | 4983 | 4983 | 0 | 46116 | 4983 | 41133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 0 | 0 | 0 | 241136 | 0 | 241136 | 0 | 0 | 0 | 0 | 0 | 0 | 41152 | 41152 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 60357 | 58362 | 1995 | 69453 | 69453 | 0 | 97019 | 95024 | 1995 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 71404 | 66422 | 4983 | 71404 | 66421 | 0 | 71404 | 66421 | 4983 | 4145630 | 943871 | 3201760 | 576605 | 571622 | 0 | 935092 | 638345 | 296747 | 4145630 | 943871 | 3201760 | 576605 | 571622 | 0 | 935092 | 638345 | 296747 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2010 | Q4 | Q4 - 2010 | 947990 | 381962 | 566028 | 75481 | 75481 | 0 | 150962 | 75481 | 75481 | 2186252 | 432142 | 1754110 | 355284 | 355284 | 0 | 355284 | 355284 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 205133 | 4983 | 200150 | 4983 | 4983 | 0 | 28383 | 4983 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 324102 | 324102 | 0 | 454901 | 0 | 454901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 60357 | 58362 | 1995 | 69453 | 69453 | 0 | 69453 | 69453 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 71404 | 66421 | 4983 | 25082 | 25082 | 0 | 71404 | 66421 | 4983 | 4145630 | 943870 | 3201760 | 854385 | 854385 | 0 | 1137887 | 571622 | 566265 | 4145630 | 943870 | 3201760 | 854385 | 854385 | 0 | 1137887 | 571622 | 566265 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2011 | Q1 | Q1 - 2011 | 947990 | 381962 | 566028 | 0 | 0 | 0 | 404353 | 381962 | 22391 | 2186252 | 432142 | 1754110 | 505201 | 432142 | 73059 | 925201 | 432142 | 493059 | 7500 | 0 | 7500 | 25082 | 17582 | 7500 | 25082 | 17582 | 7500 | 205133 | 0 | 205133 | 0 | 0 | 0 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 490398 | 0 | 490398 | 713695 | 223297 | 490398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1020681 | 449724 | 570957 | 2128331 | 1054983 | 1073348 | 4015864 | 814104 | 3201760 | 1020681 | 449724 | 570957 | 2128331 | 1054983 | 1073348 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2011 | Q2 | Q2 - 2011 | 947990 | 381962 | 566028 | 45355 | 43863 | 1492 | 45355 | 43863 | 1492 | 2186252 | 432142 | 1754110 | 398026 | 398026 | 0 | 1061120 | 398026 | 663094 | 7500 | 0 | 7500 | 24232 | 16732 | 7500 | 24232 | 16732 | 7500 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 415168 | 0 | 415168 | 576323 | 0 | 576323 | 0 | 0 | 0 | 277009 | 277009 | 0 | 392292 | 392292 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1184990 | 735630 | 449360 | 2124522 | 850913 | 1273609 | 4015864 | 814104 | 3201760 | 1184990 | 735630 | 449360 | 2124522 | 850913 | 1273609 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2011 | Q3 | Q3 - 2011 | 947990 | 381962 | 566028 | 43863 | 43863 | 0 | 267452 | 43863 | 223589 | 2186252 | 432142 | 1754110 | 422536 | 422536 | 0 | 2326300 | 770241 | 1556059 | 7500 | 0 | 7500 | 24232 | 16732 | 7500 | 24232 | 16732 | 7500 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 89354 | 0 | 89354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 569010 | 0 | 569010 | 578636 | 0 | 578636 | 0 | 0 | 0 | 288020 | 288020 | 0 | 392049 | 392049 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 83980 | 0 | 83980 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1372861 | 771151 | 601710 | 3762003 | 1222885 | 2539118 | 4015864 | 814104 | 3201760 | 1372861 | 771151 | 601710 | 3762003 | 1222885 | 2539118 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2011 | Q4 | Q4 - 2011 | 947990 | 381962 | 566028 | 226005 | 159867 | 66138 | 249555 | 159867 | 89688 | 2186252 | 432142 | 1754110 | 1293553 | 644695 | 648857 | 1537982 | 644695 | 893286 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1118532 | 9542 | 1108990 | 1126934 | 9542 | 1117392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 43884 | 0 | 43884 | 139720 | 0 | 139720 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716 | 0 | 2716 | 4015864 | 814104 | 3201760 | 2731406 | 814104 | 1917301 | 3106339 | 814104 | 2292234 | 4015864 | 814104 | 3201760 | 2731406 | 814104 | 1917301 | 3106339 | 814104 | 2292234 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2012 | Q1 | Q1 - 2012 | 947990 | 381962 | 566028 | 259097 | 169409 | 89688 | 398675 | 169409 | 229266 | 2186252 | 432142 | 1754110 | 2013146 | 644695 | 1368451 | 2067599 | 644695 | 1422903 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1155787 | 0 | 1155787 | 1296034 | 0 | 1296034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 157497 | 0 | 157497 | 204124 | 0 | 204125 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5416 | 0 | 5416 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 3640375 | 814104 | 2826271 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 3640375 | 814104 | 2826271 | 4015864 | 814104 | 3201760 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2012 | Q2 | Q2 - 2012 | 947990 | 381962 | 566028 | 323042 | 169409 | 153633 | 323042 | 169409 | 153633 | 2186252 | 432142 | 1754110 | 2152614 | 644695 | 1507919 | 2152614 | 644695 | 1507919 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1207712 | 0 | 1207712 | 1202333 | 0 | 1202333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 184089 | 0 | 184089 | 278687 | 0 | 278687 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9756 | 0 | 9756 | 9756 | 0 | 9756 | 4015864 | 814104 | 3201760 | 3926645 | 814104 | 3112541 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 3926645 | 814104 | 3112541 | 4015864 | 814104 | 3201760 | 0 | 0 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2012 | Q3 | Q3 - 2012 | 947990 | 381962 | 566028 | 311798 | 153262 | 158536 | 311798 | 153262 | 158536 | 2186252 | 432142 | 1754110 | 2219065 | 660842 | 1558223 | 2227465 | 660842 | 1566623 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1148482 | 0 | 1148482 | 1148482 | 0 | 1148482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 278687 | 0 | 278687 | 278687 | 0 | 278687 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 4007464 | 814104 | 3193360 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 4007464 | 814104 | 3193360 | 4015864 | 814104 | 3201760 | 0 | 377 | Hardy Telecommunications, Inc.
NT10BIX5570035 | INF | 2012 | Q4 | Q4 - 2012 | 418898 | 230934 | 187964 | 418898 | 230934 | 187964 | 418898 | 230934 | 187964 | 2501256 | 969062 | 1532194 | 2501256 | 969062 | 1532194 | 2501256 | 969062 | 1532194 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393482 | 292741 | 1100741 | 1393482 | 292741 | 1100741 | 1393482 | 292741 | 1100741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326429 | 0 | 326429 | 326429 | 0 | 326429 | 326429 | 0 | 326429 | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 0 | 319 | Hardy Telecommunications, Inc.
NT10BIX5570036 | INF | 2010 | Q3 | Q3 - 2010 | 1419750 | 354937 | 1064813 | 0 | 0 | 0 | 675000 | 168750 | 506250 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2500 | 675 | 1875 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431912 | 1295738 | 2500 | 675 | 1875 | 817000 | 204250 | 612750 | 1727650 | 431912 | 1295738 | 2500 | 675 | 1875 | 817000 | 204250 | 612750 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2010 | Q4 | Q4 - 2010 | 1419750 | 354937 | 1064813 | 0 | 0 | 0 | 0 | 0 | 0 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431912 | 1295738 | 10000 | 2500 | 7500 | 122000 | 30500 | 91500 | 1727650 | 431912 | 1295738 | 10000 | 2500 | 7500 | 122000 | 30500 | 91500 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2011 | Q1 | Q1 - 2011 | 1419750 | 354938 | 1064812 | 479032 | 119758 | 359274 | 520000 | 130000 | 390000 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 75000 | 18750 | 56250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 489032 | 122258 | 366774 | 609000 | 152250 | 456750 | 1727650 | 431913 | 1295737 | 489032 | 122258 | 366774 | 609000 | 152250 | 456750 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2011 | Q2 | Q2 - 2011 | 1419750 | 354938 | 1064812 | 517075 | 129269 | 387806 | 520000 | 130000 | 390000 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 75000 | 18750 | 56250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 527160 | 131790 | 395370 | 609500 | 152375 | 457125 | 1727650 | 431913 | 1295737 | 527160 | 131790 | 395370 | 609500 | 152375 | 457125 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2011 | Q3 | Q3 - 2011 | 1419750 | 354938 | 1064812 | 591654 | 147913 | 443741 | 605000 | 151250 | 453750 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 623166 | 155791 | 467375 | 720350 | 180088 | 540262 | 1727650 | 431913 | 1295737 | 623166 | 155791 | 467375 | 720350 | 180088 | 540262 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2011 | Q4 | Q4 - 2011 | 1419750 | 354938 | 1064812 | 591654 | 147913 | 443741 | 596654 | 149163 | 447491 | 169600 | 42400 | 127200 | 112125 | 28031 | 84094 | 117000 | 29250 | 87750 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 735811 | 183952 | 551859 | 749109 | 187277 | 561832 | 1727650 | 431913 | 1295737 | 735811 | 183952 | 551859 | 749109 | 187277 | 561832 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2012 | Q1 | Q1 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2012 | Q2 | Q2 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2012 | Q3 | Q3 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 745886 | 186471 | 559415 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 745886 | 186471 | 559415 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2012 | Q4 | Q4 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 771886 | 192971 | 578915 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 771886 | 192971 | 578915 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570036 | INF | 2013 | Q1 | Q1 - 2013 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 55859 | 13965 | 41894 | 55859 | 13965 | 41894 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 780168 | 195042 | 585126 | 780168 | 195042 | 585126 | 1727650 | 431913 | 1295737 | 780168 | 195042 | 585126 | 780168 | 195042 | 585126 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570037 | INF | 2010 | Q3 | Q3 - 2010 | 3023304 | 1634147 | 1389157 | 1434624 | 1434624 | 0 | 1434624 | 1434624 | 0 | 10424137 | 2340987 | 8083150 | 0 | 0 | 0 | 408500 | 0 | 408500 | 664602 | 328902 | 335700 | 176092 | 97320 | 78772 | 436092 | 107092 | 329000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 81988 | 81988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706186 | 0 | 706186 | 300963 | 0 | 300963 | 500963 | 0 | 500963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238739 | 0 | 1238739 | 0 | 0 | 0 | 40000 | 0 | 40000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 1993667 | 1613932 | 379735 | 2902167 | 1623704 | 1278463 | 18002131 | 4519127 | 13483004 | 1993667 | 1613932 | 379735 | 2902167 | 1623704 | 1278463 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2010 | Q4 | Q4 - 2010 | 3023304 | 1634147 | 1389157 | 1464567 | 1463787 | 780 | 1500000 | 1470000 | 30000 | 10424137 | 2340987 | 8083150 | 8050 | 0 | 8050 | 2500000 | 0 | 2500000 | 664602 | 328902 | 335700 | 289705 | 106738 | 182967 | 430000 | 118000 | 312000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 81988 | 81988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706186 | 0 | 706186 | 539504 | 0 | 539504 | 650000 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238739 | 0 | 1238739 | 0 | 0 | 0 | 250000 | 0 | 250000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 2383814 | 1652513 | 731301 | 5411988 | 1669988 | 3742000 | 18002131 | 4519127 | 13483004 | 2383814 | 1652513 | 731301 | 5411988 | 1669988 | 3742000 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2011 | Q1 | Q1 - 2011 | 2923304 | 1634147 | 1289157 | 1463787 | 1463787 | 0 | 1543787 | 1478787 | 65000 | 10424137 | 2340987 | 8083150 | 614835 | 0 | 614835 | 3000000 | 300000 | 2700000 | 732102 | 328902 | 403200 | 417434 | 137049 | 280385 | 450000 | 150000 | 300000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 881988 | 81988 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 740049 | 0 | 740049 | 900000 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 92884 | 0 | 92884 | 300000 | 0 | 300000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 3410977 | 1682824 | 1728153 | 7075775 | 2010775 | 5065000 | 18002131 | 4519127 | 13483004 | 3410977 | 1682824 | 1728153 | 7075775 | 2010775 | 5065000 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2011 | Q2 | Q2 - 2011 | 2923304 | 1634147 | 1289157 | 1555868 | 1463787 | 92081 | 1555868 | 1463787 | 92081 | 10424137 | 2340987 | 8083150 | 3136704 | 0 | 3136704 | 7000000 | 700000 | 6300000 | 732102 | 328902 | 403200 | 417434 | 137049 | 280385 | 500000 | 150000 | 350000 | 1314425 | 72500 | 1241925 | 100777 | 81988 | 18789 | 1200000 | 81988 | 1281988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 855281 | 0 | 855281 | 950000 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 211028 | 0 | 211028 | 350000 | 0 | 350000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 6277092 | 1682824 | 4594268 | 11755868 | 2395775 | 9524069 | 18002131 | 4519127 | 13483004 | 6277092 | 1682824 | 4594268 | 11755868 | 2395775 | 9524069 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2011 | Q3 | Q3 - 2011 | 2923304 | 1634147 | 1289157 | 1643361 | 1463787 | 179574 | 1643361 | 1463787 | 179574 | 10424137 | 2340987 | 8083150 | 5933987 | 0 | 5933987 | 7500000 | 1400000 | 6000000 | 732102 | 328902 | 403200 | 449704 | 195026 | 254678 | 600000 | 200000 | 400000 | 1314425 | 72500 | 1241925 | 100777 | 81988 | 18789 | 836988 | 81988 | 755000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 855281 | 0 | 855281 | 950000 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 348427 | 0 | 348427 | 500000 | 0 | 500000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 392000 | 0 | 392000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 9331537 | 1740801 | 7590736 | 12422349 | 3145775 | 9176574 | 18002131 | 4519127 | 13483004 | 9331537 | 1740801 | 7590736 | 12422349 | 3145775 | 9176574 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2011 | Q4 | Q4 - 2011 | 2632427 | 1418817 | 1213610 | 1531506 | 1389627 | 141879 | 1531506 | 1389627 | 141879 | 10424137 | 2304000 | 8120137 | 6925323 | 0 | 6925323 | 9500000 | 1800000 | 7700000 | 1033890 | 619958 | 413932 | 841113 | 554055 | 287058 | 950000 | 575000 | 375000 | 1403277 | 176352 | 1226925 | 931352 | 176352 | 755000 | 1376352 | 176352 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1021590 | 0 | 1021590 | 1100000 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 514864 | 0 | 514864 | 675000 | 0 | 675000 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 12246723 | 2120034 | 10126689 | 15613833 | 3940979 | 11672854 | 18002131 | 4519127 | 13483004 | 12246723 | 2120034 | 10126689 | 15613833 | 3940979 | 11672854 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2012 | Q1 | Q1 - 2012 | 2632427 | 1418817 | 1213610 | 1531506 | 1389627 | 141879 | 1531506 | 1389627 | 141879 | 10424137 | 2304000 | 8120137 | 8415068 | 1410320 | 7004748 | 10000000 | 2000000 | 8000000 | 1033890 | 619958 | 413932 | 980954 | 585047 | 395907 | 1000000 | 600000 | 400000 | 1403277 | 176352 | 1226925 | 931352 | 176352 | 755000 | 1376352 | 176352 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1275000 | 0 | 1275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 611594 | 0 | 611594 | 700000 | 0 | 700000 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 14212262 | 3561346 | 10650916 | 16363833 | 4165979 | 12197854 | 18002131 | 4519127 | 13483004 | 14212262 | 3561346 | 10650916 | 16363833 | 4165979 | 12197854 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2012 | Q2 | Q2 - 2012 | 2632427 | 1418817 | 1213610 | 1559366 | 1389627 | 169739 | 2350000 | 1389627 | 960373 | 10424137 | 2304000 | 8120137 | 8935027 | 1858767 | 7076260 | 10126480 | 2126480 | 8000000 | 1033890 | 619958 | 413932 | 1015865 | 619958 | 395907 | 1015865 | 619958 | 395907 | 1403277 | 176352 | 1226925 | 1333272 | 176352 | 1156920 | 1403277 | 176352 | 1226925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1260813 | 0 | 1260813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 15324057 | 4044704 | 11279353 | 17376149 | 4312417 | 13063732 | 18002131 | 4519127 | 13483004 | 15324057 | 4044704 | 11279353 | 17376149 | 4312417 | 13063732 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2012 | Q3 | Q3 - 2012 | 2632427 | 1418817 | 1213610 | 1730196 | 1389627 | 340569 | 2632427 | 1418817 | 1213610 | 10424137 | 2304000 | 8120137 | 9587583 | 2191833 | 7395750 | 10424137 | 2304000 | 8120137 | 1033890 | 619958 | 413932 | 1018476 | 619958 | 398518 | 1033890 | 619958 | 413932 | 1403277 | 176352 | 1226925 | 1333272 | 176352 | 1156920 | 1403277 | 176352 | 1226925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1288686 | 0 | 1288686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 16150054 | 4377770 | 11772284 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 16150054 | 4377770 | 11772284 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2012 | Q4 | Q4 - 2012 | 2632427 | 1418817 | 1213610 | 2684195 | 1408638 | 1275557 | 2725081 | 1408638 | 1316443 | 10424137 | 2304000 | 8120137 | 10126625 | 2314179 | 7812446 | 10273829 | 2314179 | 7959650 | 1033890 | 619958 | 413932 | 980539 | 619958 | 360581 | 980539 | 619958 | 360581 | 1403277 | 176352 | 1226925 | 1351312 | 176352 | 1174960 | 1412113 | 176352 | 1235761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1191262 | 0 | 1191262 | 1191262 | 0 | 1191262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 743765 | 0 | 743765 | 743765 | 0 | 743765 | 480975 | 0 | 480975 | 675542 | 0 | 675542 | 675542 | 0 | 675542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 17753240 | 4519127 | 13234113 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 17753240 | 4519127 | 13234113 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of
NT10BIX5570037 | INF | 2013 | Q1 | Q1 - 2013 | 2632427 | 1418817 | 1213610 | 2725081 | 1408638 | 1316210 | 2725081 | 1408638 | 1316210 | 10424137 | 2304000 | 8120137 | 10273829 | 2314179 | 7959883 | 10273829 | 2314179 | 7959883 | 1033890 | 619958 | 413932 | 980539 | 619958 | 360581 | 980539 | 619958 | 360581 | 1403277 | 176352 | 1226925 | 1412113 | 176352 | 1235761 | 1412113 | 176352 | 1235761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1191262 | 0 | 1191262 | 1191262 | 0 | 1191262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 743765 | 0 | 743765 | 743765 | 0 | 743765 | 480975 | 0 | 480975 | 675542 | 0 | 675542 | 675542 | 0 | 675542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of
NT10BIX5570038 | INF | 2010 | Q3 | Q3 - 2010 | 2246125 | 561531 | 1684594 | 0 | 0 | 0 | 850000 | 212500 | 637500 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 6000 | 2000 | 19950 | 4988 | 14963 | 0 | 0 | 0 | 8500 | 2125 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 100000 | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066251 | 14700 | 3675 | 11025 | 1116500 | 283125 | 833375 | 2755000 | 688750 | 2066251 | 14700 | 3675 | 11025 | 1116500 | 283125 | 833375 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2010 | Q4 | Q4 - 2010 | 2246125 | 561531 | 1684594 | 24030 | 6008 | 18022 | 850000 | 212500 | 637500 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 8500 | 2125 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 100000 | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 38730 | 9683 | 29047 | 1116500 | 279125 | 837375 | 2755000 | 688750 | 2066250 | 38730 | 9683 | 29047 | 1116500 | 279125 | 837375 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2011 | Q1 | Q1 - 2011 | 2246125 | 561531 | 1684594 | 561902 | 140476 | 421426 | 580000 | 145000 | 435000 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 576602 | 144151 | 432451 | 752700 | 188175 | 564525 | 2755000 | 688750 | 2066250 | 576602 | 144151 | 432451 | 752700 | 188175 | 564525 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2011 | Q2 | Q2 - 2011 | 2246125 | 561531 | 1684594 | 684321 | 171081 | 513240 | 710000 | 177500 | 532500 | 288300 | 72075 | 216225 | 16865 | 4216 | 12649 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 149 | 37 | 112 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 716035 | 179009 | 537026 | 773200 | 193300 | 579900 | 2755000 | 688750 | 2066250 | 716035 | 179009 | 537026 | 773200 | 193300 | 579900 | 0 | 17651 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2011 | Q3 | Q3 - 2011 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 838000 | 209500 | 628500 | 288300 | 72075 | 216225 | 129095 | 32274 | 96821 | 135000 | 33750 | 101250 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 149 | 37 | 112 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 997988 | 249497 | 748491 | 1013200 | 253300 | 759900 | 2755000 | 688750 | 2066250 | 997988 | 249497 | 748491 | 1013200 | 253300 | 759900 | 0 | 639576 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2011 | Q4 | Q4 - 2011 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 837467 | 209367 | 628100 | 288300 | 72075 | 216225 | 198096 | 49524 | 148572 | 203096 | 50774 | 152322 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1070169 | 267542 | 802627 | 1083592 | 270898 | 812694 | 2755000 | 688750 | 2066250 | 1070169 | 267542 | 802627 | 1083592 | 270898 | 812694 | 0 | 900740 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2012 | Q1 | Q1 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 0 | 900740 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2012 | Q2 | Q2 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 0 | 900740 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2012 | Q3 | Q3 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1073688 | 268422 | 805266 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1073688 | 268422 | 805266 | 0 | 781682 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2012 | Q4 | Q4 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1099688 | 274922 | 824766 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1099688 | 274922 | 824766 | 0 | 1137204 | Level 3 EON, LLC
NT10BIX5570038 | INF | 2013 | Q1 | Q1 - 2013 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 61696 | 15424 | 46272 | 61696 | 15424 | 46272 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1113807 | 278452 | 835355 | 1113807 | 278452 | 835355 | 2755000 | 688750 | 2066250 | 1113807 | 278452 | 835355 | 1113807 | 278452 | 835355 | 0 | 1268539 | Level 3 EON, LLC
NT10BIX5570039 | INF | 2010 | Q3 | Q3 - 2010 | 6725161 | 0 | 6725161 | 4554 | 0 | 4554 | 4554 | 0 | 4554 | 30625132 | 6920000 | 23705132 | 282477 | 0 | 282477 | 494077 | 27600 | 466477 | 919300 | 419300 | 500000 | 649881 | 386185 | 263696 | 813756 | 407560 | 406196 | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286600 | 0 | 286600 | 0 | 0 | 0 | 0 | 0 | 0 | 755200 | 0 | 755200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 936912 | 386185 | 550727 | 2062387 | 1185160 | 877227 | 40161393 | 8089300 | 32072093 | 936912 | 386185 | 550727 | 2062387 | 1185160 | 877227 | 0 | 0 | OpenCape Corporation
NT10BIX5570039 | INF | 2010 | Q4 | Q4 - 2010 | 6725161 | 0 | 6725161 | 4555 | 0 | 4555 | 0 | 0 | 0 | 30625132 | 6920000 | 23705132 | 228797 | 0 | 148547 | 1300000 | 150000 | 1150000 | 919300 | 419300 | 500000 | 829065 | 339300 | 442880 | 919300 | 419300 | 500000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286600 | 0 | 286600 | 215640 | 0 | 215640 | 286600 | 0 | 286600 | 755200 | 0 | 755200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 1278057 | 339300 | 811622 | 3255900 | 1319300 | 1936600 | 40161393 | 8089300 | 32072093 | 1278057 | 339300 | 811622 | 3255900 | 1319300 | 1936600 | 127133 | 127133 | OpenCape Corporation
NT10BIX5570039 | INF | 2011 | Q1 | Q1 - 2011 | 11336564 | 0 | 11336564 | 135196 | 0 | 135196 | 250000 | 0 | 250000 | 24364298 | 6920000 | 17444298 | 1639150 | 25882 | 1613268 | 4600000 | 467000 | 4133000 | 1280532 | 419300 | 861232 | 873585 | 339300 | 534285 | 1110000 | 416184 | 694000 | 750000 | 750000 | 0 | 4200 | 4200 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 0 | 1515885 | 315696 | 0 | 315696 | 700000 | 0 | 700000 | 814114 | 0 | 814114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 2967827 | 369382 | 2598445 | 7410000 | 1633184 | 5777000 | 40161393 | 8089300 | 32072093 | 2967827 | 369382 | 2598445 | 7410000 | 1633184 | 5777000 | 5000000 | 218748 | OpenCape Corporation
NT10BIX5570039 | INF | 2011 | Q2 | Q2 - 2011 | 11336564 | 0 | 11336564 | 352931 | 43547 | 309384 | 1000000 | 43457 | 956543 | 24364298 | 6920000 | 17444298 | 3038204 | 648259 | 2389945 | 6000000 | 1000000 | 5000000 | 1280532 | 419300 | 861232 | 1057284 | 416184 | 641100 | 1131676 | 416184 | 715492 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 0 | 1515885 | 881077 | 264633 | 616444 | 1181077 | 264633 | 916444 | 814114 | 0 | 814114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 6079496 | 2122623 | 3956873 | 10112753 | 2474274 | 7638479 | 40161393 | 8089300 | 32072093 | 6079496 | 2122623 | 3956873 | 10112753 | 2474274 | 7638479 | 5000000 | 555413 | OpenCape Corporation
NT10BIX5570039 | INF | 2011 | Q3 | Q3 - 2011 | 11336564 | 2300000 | 9036564 | 680187 | 43547 | 636640 | 4000000 | 750000 | 3250000 | 24364298 | 4110000 | 20254298 | 3633645 | 869070 | 2764575 | 5000000 | 1000000 | 4000000 | 1280532 | 419300 | 861232 | 1146158 | 416191 | 729967 | 1216000 | 416191 | 799809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1165838 | 374135 | 791703 | 1300000 | 395046 | 904954 | 814114 | 165000 | 649114 | 9000 | 0 | 9000 | 50000 | 9000 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 360 | 360 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 7385188 | 2453303 | 4931885 | 12416000 | 3340237 | 9075763 | 40161393 | 8089300 | 32072093 | 7385188 | 2453303 | 4931885 | 12416000 | 3340237 | 9075763 | 5000000 | 649913 | OpenCape Corporation
NT10BIX5570039 | INF | 2011 | Q4 | Q4 - 2011 | 11336564 | 2300000 | 9036564 | 2026835 | 63547 | 1963288 | 6500000 | 500000 | 6000000 | 24364298 | 4110000 | 20254298 | 4591699 | 1209659 | 3382040 | 8500000 | 2000000 | 6500000 | 1280532 | 419300 | 861232 | 1238555 | 416191 | 822364 | 1325000 | 416191 | 908809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1404408 | 467692 | 936716 | 1450000 | 395046 | 1054954 | 814114 | 165000 | 649114 | 35000 | 0 | 35000 | 70000 | 9000 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 48360 | 48360 | 0 | 70000 | 48360 | 21640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 10094857 | 2955449 | 7139408 | 18665000 | 4118597 | 14546403 | 40161393 | 8089300 | 32072093 | 10094857 | 2955449 | 7139408 | 18665000 | 4118597 | 14546403 | 5000000 | 1069774 | OpenCape Corporation
NT10BIX5570039 | INF | 2012 | Q1 | Q1 - 2012 | 11336564 | 2300000 | 9036564 | 6465505 | 347207 | 6118298 | 8000000 | 800000 | 7200000 | 24364298 | 4110000 | 20254298 | 8526788 | 2106217 | 6420571 | 13000000 | 2500000 | 10500000 | 1280532 | 419300 | 861232 | 1360062 | 416184 | 943878 | 1530000 | 416191 | 1113809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1472158 | 520925 | 951233 | 1572000 | 495000 | 1077000 | 814114 | 165000 | 649114 | 72000 | 9000 | 63000 | 125000 | 40000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88484 | 85654 | 2830 | 98000 | 85654 | 12346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 18734997 | 4235187 | 14499810 | 25075000 | 5086845 | 19988155 | 40161393 | 8089300 | 32072093 | 18734997 | 4235187 | 14499810 | 25075000 | 5086845 | 19988155 | 5000000 | 1827337 | OpenCape Corporation
NT10BIX5570039 | INF | 2012 | Q2 | Q2 - 2012 | 11336564 | 2300000 | 9036564 | 7909996 | 347207 | 7562789 | 10000000 | 1250000 | 8750000 | 24364298 | 4110000 | 20254298 | 11805115 | 2782290 | 9022825 | 16500000 | 3150000 | 13350000 | 1280532 | 419300 | 861232 | 1418622 | 416184 | 1002438 | 1530000 | 416191 | 1113809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1604743 | 565662 | 1039081 | 1700000 | 495000 | 1205000 | 814114 | 165000 | 649114 | 146500 | 9000 | 137500 | 200000 | 9000 | 191000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88483 | 85653 | 2830 | 88485 | 85653 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 23723459 | 4955996 | 18767463 | 30768485 | 6155844 | 24612641 | 40161393 | 8089300 | 32072093 | 23723459 | 4955996 | 18767463 | 30768485 | 6155844 | 24612641 | 5000000 | 2646218 | OpenCape Corporation
NT10BIX5570039 | INF | 2012 | Q3 | Q3 - 2012 | 11336564 | 2300000 | 9036564 | 8355565 | 716057 | 7639508 | 10500000 | 1500000 | 9000000 | 24364298 | 4110000 | 20254298 | 13776050 | 2870065 | 10872382 | 18000000 | 3150000 | 14850000 | 1280532 | 419300 | 861232 | 1728532 | 633144 | 1095389 | 1850000 | 633144 | 1216856 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1619950 | 580869 | 1039082 | 1887000 | 580869 | 1306131 | 814114 | 165000 | 649114 | 182000 | 9000 | 173000 | 600000 | 165000 | 435000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88483 | 85653 | 2830 | 88485 | 85653 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 26500580 | 5644788 | 20822191 | 33675485 | 6864666 | 26810819 | 40161393 | 8089300 | 32072093 | 26500580 | 5644788 | 20822191 | 33675485 | 6864666 | 26810819 | 5000000 | 3064950 | OpenCape Corporation
NT10BIX5570039 | INF | 2012 | Q4 | Q4 - 2012 | 11336564 | 2300000 | 9036564 | 9448179 | 1177397 | 8270782 | 10994012 | 1499649 | 9494363 | 24364298 | 4110000 | 20254298 | 16955664 | 2962569 | 13993096 | 20036545 | 3562569 | 16473976 | 1280532 | 419300 | 861232 | 1790311 | 637274 | 1153037 | 1955311 | 637274 | 1318037 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1686950 | 580869 | 1106082 | 1941760 | 610869 | 1330891 | 814114 | 165000 | 649114 | 250704 | 9954 | 240750 | 250704 | 9954 | 240750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 30970643 | 6204068 | 24766577 | 36017167 | 7156320 | 28860847 | 40161393 | 8089300 | 32072093 | 30970643 | 6204068 | 24766577 | 36017167 | 7156320 | 28860847 | 5000000 | 3574636 | OpenCape Corporation
NT10BIX5570039 | INF | 2013 | Q1 | Q1 - 2013 | 11200689 | 2000000 | 9200689 | 10052640 | 1627093 | 8425547 | 11114288 | 1912999 | 9201289 | 22939955 | 3906449 | 19033506 | 18646565 | 3129040 | 15517525 | 22682955 | 3906449 | 18776506 | 2228962 | 616188 | 1612773 | 1912709 | 616189 | 1296520 | 2070334 | 616189 | 1454145 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1719103 | 580870 | 1138233 | 1917618 | 596077 | 1321541 | 1066100 | 165000 | 901100 | 342954 | 9954 | 333000 | 911054 | 59954 | 851100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089299 | 32072093 | 33512806 | 6799151 | 26713655 | 39535084 | 7927673 | 31607411 | 40161393 | 8089299 | 32072093 | 33512806 | 6799151 | 26713655 | 39535084 | 7927673 | 31607411 | 5000000 | 3877897 | OpenCape Corporation
NT10BIX5570039 | INF | 2013 | Q2 | Q2 - 2013 | 11200689 | 2000000 | 9200689 | 10570968 | 1720692 | 8850276 | 11200689 | 2000000 | 9200689 | 22939955 | 3906449 | 19033506 | 20367755 | 3226478 | 17141277 | 22467158 | 3684004 | 18783154 | 2228962 | 616188 | 1612773 | 2007994 | 616583 | 1391411 | 2078966 | 616583 | 1462383 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1766628 | 587707 | 1178921 | 1909249 | 587707 | 1321542 | 1066100 | 165000 | 901100 | 692319 | 80149 | 612170 | 1066100 | 165000 | 901100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089299 | 32072093 | 36244499 | 7067614 | 29176885 | 39560997 | 7889299 | 31671698 | 40161393 | 8089299 | 32072093 | 36244499 | 7067614 | 29176885 | 39560997 | 7889299 | 31671698 | 5000000 | 4219398 | OpenCape Corporation
NT10BIX5570039 | INF | 2013 | Q3 | Q3 - 2013 | 11200689 | 2000000 | 9200689 | 11012081 | 1786449 | 9225632 | 11225632 | 2000000 | 9225632 | 22939955 | 3906449 | 19033506 | 21540211 | 3296903 | 18243308 | 22915012 | 3906449 | 19008563 | 2228962 | 616189 | 1612773 | 2083393 | 616583 | 1466810 | 2229356 | 616583 | 1612773 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1807053 | 597086 | 1209967 | 1918628 | 597086 | 1321542 | 1066100 | 165000 | 901100 | 800002 | 107346 | 692656 | 1033930 | 133177 | 900753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 38081575 | 7240372 | 30841203 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 38081575 | 7240372 | 30841203 | 40161393 | 8089300 | 32072093 | 0 | 0 | OpenCape Corporation
NT10BIX5570039 | INF | 2013 | Q4 | Q4 - 2013 | 11200689 | 2000000 | 9200689 | 11192814 | 1786930 | 9405884 | 11192814 | 1786930 | 9405884 | 22939955 | 3906449 | 19033506 | 22998163 | 3955570 | 19042594 | 22998163 | 3955570 | 19042594 | 2228962 | 616189 | 1612773 | 2262644 | 673910 | 1588734 | 2262644 | 673910 | 1588734 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1881516 | 597974 | 1283541 | 1881516 | 597974 | 1283541 | 1066100 | 165000 | 901100 | 987421 | 238911 | 748510 | 987421 | 238911 | 748510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 0 | 0 | OpenCape Corporation
NT10BIX5570039 | INF | 2014 | Q1 | Q1 - 2014 | 11200689 | 2000000 | 9200689 | 11192814 | 1786930 | 9405884 | 11192814 | 1786930 | 9405884 | 22939955 | 3906449 | 19033506 | 22998163 | 3955570 | 19042594 | 22998163 | 3955570 | 19042594 | 2228962 | 616189 | 1612773 | 2262644 | 673910 | 1588734 | 2262644 | 673910 | 1588734 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1881516 | 597974 | 1283541 | 1881516 | 597974 | 1283541 | 1066100 | 165000 | 901100 | 987421 | 238911 | 748510 | 987421 | 238911 | 748510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 0 | 0 | OpenCape Corporation
NT10BIX5570040 | INF | 2010 | Q3 | Q3 - 2010 | 1903080 | 475770 | 1427310 | 0 | 0 | 0 | 800000 | 600000 | 200000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 95000 | 23750 | 71250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 6500 | 1625 | 4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2000 | 500 | 1500 | 28000 | 7000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2221160 | 555290 | 1665870 | 2000 | 500 | 1500 | 933500 | 633375 | 300125 | 2221160 | 555290 | 1665870 | 2000 | 500 | 1500 | 933500 | 633375 | 300125 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2010 | Q4 | Q4 - 2010 | 1903080 | 475770 | 1427310 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 6500 | 1625 | 4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 28000 | 7000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2221160 | 555290 | 1665870 | 8000 | 2000 | 6000 | 198500 | 49625 | 148875 | 2221160 | 555290 | 1665870 | 8000 | 2000 | 6000 | 198500 | 49625 | 148875 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2011 | Q1 | Q1 - 2011 | 1585000 | 396250 | 1188750 | 393835 | 98459 | 295376 | 400000 | 100000 | 300000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 401835 | 100459 | 301376 | 452000 | 113000 | 339000 | 1903080 | 475770 | 1427310 | 401835 | 100459 | 301376 | 452000 | 113000 | 339000 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2011 | Q2 | Q2 - 2011 | 1585000 | 396250 | 1188750 | 559471 | 139868 | 419603 | 650000 | 162500 | 487500 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 50000 | 12500 | 37500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 20000 | 5000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 567556 | 141889 | 425667 | 724500 | 181125 | 543375 | 1903080 | 475770 | 1427310 | 567556 | 141889 | 425667 | 724500 | 181125 | 543375 | 0 | 13368 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2011 | Q3 | Q3 - 2011 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 600000 | 150000 | 450000 | 178100 | 44525 | 133575 | 8264 | 2066 | 6197 | 70000 | 17500 | 52500 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 18750 | 6250 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 633299 | 158324 | 474974 | 703380 | 188345 | 515035 | 1903080 | 475770 | 1427310 | 633299 | 158324 | 474974 | 703380 | 188345 | 515035 | 0 | 10331 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2011 | Q4 | Q4 - 2011 | 1585000 | 396250 | 1188750 | 595494 | 148874 | 446620 | 600494 | 150124 | 450370 | 178100 | 44525 | 133575 | 72457 | 18115 | 54343 | 77457 | 19364 | 58093 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 698013 | 174504 | 523510 | 711436 | 177859 | 533577 | 1903080 | 475770 | 1427310 | 698013 | 174504 | 523510 | 711436 | 177859 | 533577 | 0 | 17949 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2012 | Q1 | Q1 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 0 | 26803 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2012 | Q2 | Q2 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 0 | 35672 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2012 | Q3 | Q3 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 703650 | 175912 | 527738 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 703650 | 175912 | 527738 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2012 | Q4 | Q4 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 729650 | 182412 | 547238 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 729650 | 182412 | 547238 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570040 | INF | 2013 | Q1 | Q1 - 2013 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 55859 | 13965 | 41894 | 55859 | 13965 | 41894 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 737932 | 184483 | 553449 | 737932 | 184483 | 553449 | 1903080 | 475770 | 1427310 | 737932 | 184483 | 553449 | 737932 | 184483 | 553449 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2010 | Q3 | Q3 - 2010 | 5256000 | 1314000 | 3942000 | 0 | 0 | 0 | 750000 | 187500 | 562500 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 400000 | 100000 | 300000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 12000 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47813 | 143438 | 32500 | 8125 | 24375 | 120000 | 30000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559263 | 4677789 | 32500 | 8125 | 24375 | 1290000 | 322500 | 967500 | 6237051 | 1559263 | 4677789 | 32500 | 8125 | 24375 | 1290000 | 322500 | 967500 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2010 | Q4 | Q4 - 2010 | 5256000 | 1314000 | 3942000 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 12000 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 34000 | 8500 | 25500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 34000 | 8500 | 25500 | 300000 | 75000 | 225000 | 6237051 | 1559262 | 4677789 | 34000 | 8500 | 25500 | 300000 | 75000 | 225000 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2011 | Q1 | Q1 - 2011 | 5256000 | 1314000 | 3942000 | 655403 | 170226 | 485177 | 700000 | 175000 | 525000 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 235000 | 58750 | 176250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47813 | 143437 | 34000 | 8500 | 25500 | 34000 | 8500 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559263 | 4677788 | 689403 | 178726 | 510677 | 973000 | 243250 | 729750 | 6237051 | 1559263 | 4677788 | 689403 | 178726 | 510677 | 973000 | 243250 | 729750 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2011 | Q2 | Q2 - 2011 | 5256000 | 1314000 | 3942000 | 2074314 | 518578 | 1555735 | 2200000 | 550000 | 1650000 | 662200 | 165550 | 496650 | 15243 | 3811 | 11432 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 362 | 91 | 271 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 34000 | 8500 | 25500 | 70000 | 17500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2123919 | 530980 | 1592938 | 2424500 | 606125 | 1818375 | 6237051 | 1559262 | 4677789 | 2123919 | 530980 | 1592938 | 2424500 | 606125 | 1818375 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2011 | Q3 | Q3 - 2011 | 5256000 | 1314000 | 3942000 | 2151173 | 537793 | 1613380 | 2155000 | 538750 | 1616250 | 662200 | 165550 | 496650 | 86394 | 21598 | 64796 | 550000 | 137500 | 412500 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 362 | 91 | 271 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2293476 | 573368 | 1720108 | 2764370 | 691092 | 2073278 | 6237051 | 1559262 | 4677789 | 2293476 | 573368 | 1720108 | 2764370 | 691092 | 2073278 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2011 | Q4 | Q4 - 2011 | 5256000 | 1314000 | 3942000 | 2320392 | 580098 | 1740294 | 2325992 | 581498 | 1744494 | 662200 | 165550 | 496650 | 516699 | 129175 | 387524 | 531699 | 132925 | 398774 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2895210 | 723802 | 2171408 | 2919233 | 729808 | 2189425 | 6237051 | 1559262 | 4677789 | 2895210 | 723802 | 2171408 | 2919233 | 729808 | 2189425 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2012 | Q1 | Q1 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2012 | Q2 | Q2 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2012 | Q3 | Q3 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2954569 | 738641 | 2215928 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2954569 | 738641 | 2215928 | 0 | 16137 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2012 | Q4 | Q4 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2980569 | 745141 | 2235428 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2980569 | 745141 | 2235428 | 0 | 25936 | Level 3 EON, LLC
NT10BIX5570041 | INF | 2013 | Q1 | Q1 - 2013 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 81153 | 20288 | 60865 | 81153 | 20288 | 60865 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 3014145 | 753535 | 2260610 | 3014145 | 753535 | 2260610 | 6237051 | 1559262 | 4677789 | 3014145 | 753535 | 2260610 | 3014145 | 753535 | 2260610 | 0 | 14309 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2010 | Q3 | Q3 - 2010 | 3671875 | 917969 | 2753906 | 0 | 0 | 0 | 800000 | 200000 | 600000 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 240000 | 60000 | 180000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30938 | 92813 | 5500 | 1375 | 4125 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097332 | 3291994 | 5500 | 1375 | 4125 | 1134000 | 283500 | 850500 | 4389325 | 1097332 | 3291994 | 5500 | 1375 | 4125 | 1134000 | 283500 | 850500 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2010 | Q4 | Q4 - 2010 | 3671875 | 917969 | 2753906 | 0 | 0 | 0 | 0 | 0 | 0 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30938 | 92812 | 22000 | 5500 | 16500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097332 | 3291993 | 22000 | 5500 | 16500 | 174000 | 43500 | 130500 | 4389325 | 1097332 | 3291993 | 22000 | 5500 | 16500 | 174000 | 43500 | 130500 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2011 | Q1 | Q1 - 2011 | 3671875 | 917969 | 2753906 | 549441 | 137360 | 412081 | 650000 | 162500 | 487500 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 22000 | 5500 | 16500 | 22000 | 5500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 571441 | 142860 | 428581 | 756000 | 189000 | 567000 | 4389325 | 1097331 | 3291994 | 571441 | 142860 | 428581 | 756000 | 189000 | 567000 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2011 | Q2 | Q2 - 2011 | 3671875 | 917969 | 2753906 | 734388 | 183597 | 550791 | 820000 | 205000 | 615000 | 474900 | 118725 | 356175 | 66730 | 16683 | 50047 | 125000 | 31250 | 93750 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 234 | 59 | 175 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 22000 | 5500 | 16500 | 22000 | 5500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 823352 | 205839 | 617513 | 971500 | 242875 | 728625 | 4389325 | 1097331 | 3291994 | 823352 | 205839 | 617513 | 971500 | 242875 | 728625 | 0 | 82327 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2011 | Q3 | Q3 - 2011 | 3671875 | 917969 | 2753906 | 1022329 | 255582 | 766747 | 1050000 | 262500 | 787500 | 474900 | 118725 | 356175 | 192969 | 48242 | 144727 | 200000 | 50000 | 150000 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 234 | 59 | 175 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1261979 | 315495 | 946484 | 1300270 | 325068 | 975202 | 4389325 | 1097331 | 3291994 | 1261979 | 315495 | 946484 | 1300270 | 325068 | 975202 | 0 | 65498 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2011 | Q4 | Q4 - 2011 | 3671875 | 917969 | 2753906 | 1031711 | 257928 | 773783 | 1036711 | 259178 | 777533 | 474900 | 118725 | 356175 | 312750 | 78188 | 234562 | 317750 | 79438 | 238312 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1394092 | 348524 | 1045568 | 1407515 | 351880 | 1055635 | 4389325 | 1097331 | 3291994 | 1394092 | 348524 | 1045568 | 1407515 | 351880 | 1055635 | 0 | 105166 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2012 | Q1 | Q1 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 0 | 157976 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2012 | Q2 | Q2 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 0 | 201061 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2012 | Q3 | Q3 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1414247 | 353562 | 1060685 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1414247 | 353562 | 1060685 | 0 | 30028 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2012 | Q4 | Q4 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1440247 | 360062 | 1080185 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1440247 | 360062 | 1080185 | 0 | 69695 | Level 3 EON, LLC
NT10BIX5570042 | INF | 2013 | Q1 | Q1 - 2013 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 69478 | 17370 | 52109 | 69478 | 17370 | 52109 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1462148 | 365538 | 1096611 | 1462148 | 365538 | 1096611 | 4389325 | 1097331 | 3291994 | 1462148 | 365538 | 1096611 | 1462148 | 365538 | 1096611 | 0 | 73119 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2010 | Q3 | Q3 - 2010 | 1047125 | 261781 | 785343 | 0 | 0 | 0 | 480000 | 120000 | 360000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 120000 | 30000 | 90000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2000 | 500 | 1500 | 32000 | 8000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998418 | 2000 | 500 | 1500 | 639200 | 159800 | 479400 | 1331225 | 332806 | 998418 | 2000 | 500 | 1500 | 639200 | 159800 | 479400 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2010 | Q4 | Q4 - 2010 | 1047125 | 261781 | 785343 | 25973 | 6493 | 19480 | 120000 | 30000 | 90000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 32000 | 8000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998418 | 33973 | 8493 | 25480 | 239200 | 59800 | 179400 | 1331225 | 332806 | 998418 | 33973 | 8493 | 25480 | 239200 | 59800 | 179400 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2011 | Q1 | Q1 - 2011 | 1047125 | 261781 | 785344 | 247391 | 61848 | 185543 | 275000 | 69000 | 206000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 255391 | 63848 | 191543 | 330200 | 82800 | 247400 | 1331225 | 332806 | 998419 | 255391 | 63848 | 191543 | 330200 | 82800 | 247400 | 0 | 0 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2011 | Q2 | Q2 - 2011 | 1047125 | 261781 | 785344 | 359376 | 89844 | 269532 | 390000 | 97500 | 292500 | 145800 | 36450 | 109350 | 32207 | 8052 | 24155 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 1000 | 250 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 399668 | 99917 | 299751 | 508200 | 127050 | 381150 | 1331225 | 332806 | 998419 | 399668 | 99917 | 299751 | 508200 | 127050 | 381150 | 0 | 55301 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2011 | Q3 | Q3 - 2011 | 1047125 | 261781 | 785344 | 424688 | 106172 | 318516 | 424688 | 106172 | 318516 | 145800 | 36450 | 109350 | 79089 | 19772 | 59317 | 85000 | 21250 | 63750 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 533319 | 133329 | 399990 | 542968 | 135742 | 407226 | 1331225 | 332806 | 998419 | 533319 | 133329 | 399990 | 542968 | 135742 | 407226 | 0 | 38376 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2011 | Q4 | Q4 - 2011 | 1047125 | 261781 | 785344 | 434689 | 108672 | 326017 | 439689 | 109922 | 329767 | 145800 | 36450 | 109350 | 118848 | 29712 | 89136 | 123848 | 30962 | 92886 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 583599 | 145899 | 437700 | 597022 | 149255 | 447767 | 1331225 | 332806 | 998419 | 583599 | 145899 | 437700 | 597022 | 149255 | 447767 | 0 | 54511 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2012 | Q1 | Q1 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 0 | 70646 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2012 | Q2 | Q2 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 0 | 86806 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2012 | Q3 | Q3 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 585649 | 146412 | 439237 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 585649 | 146412 | 439237 | 0 | 20414 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2012 | Q4 | Q4 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 611649 | 152912 | 458737 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 611649 | 152912 | 458737 | 0 | 36587 | Level 3 EON, LLC
NT10BIX5570043 | INF | 2013 | Q1 | Q1 - 2013 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 55859 | 13965 | 41859 | 55859 | 13965 | 41894 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 619931 | 154983 | 464913 | 619931 | 154983 | 464948 | 1331225 | 332806 | 998419 | 619931 | 154983 | 464913 | 619931 | 154983 | 464948 | 0 | 33407 | Level 3 EON, LLC
NT10BIX5570044 | INF | 2010 | Q3 | Q3 - 2010 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 0 | 0 | 0 | 23499307 | 6852149 | 16647158 | 0 | 0 | 0 | 640000 | 225000 | 415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 0 | 0 | 0 | 9000 | 0 | 9000 | 29386925 | 6852149 | 22534776 | 0 | 0 | 0 | 903990 | 225000 | 678990 | 29386925 | 6852149 | 22534776 | 0 | 0 | 0 | 903990 | 225000 | 678990 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2010 | Q4 | Q4 - 2010 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 0 | 0 | 0 | 23499307 | 6852149 | 16647158 | 144944 | 52678 | 92266 | 2144944 | 825000 | 1319944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 8993 | 0 | 8993 | 8993 | 0 | 8993 | 29386925 | 6852149 | 22534776 | 153937 | 52678 | 101259 | 2408927 | 825000 | 1583927 | 29386925 | 6852149 | 22534776 | 153937 | 52678 | 101259 | 2408927 | 825000 | 1583927 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2011 | Q1 | Q1 - 2011 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 2400000 | 0 | 2400000 | 23499307 | 6852149 | 16647158 | 287221 | 152548 | 134672 | 500000 | 300000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 430772 | 0 | 430772 | 1800000 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 10735 | 0 | 10735 | 12000 | 0 | 12000 | 29386925 | 6852149 | 22534776 | 728728 | 152548 | 576179 | 4712000 | 1200000 | 3512000 | 29386925 | 6852149 | 22534776 | 728728 | 152548 | 576179 | 4712000 | 1200000 | 3512000 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2011 | Q2 | Q2 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 22232196 | 4852149 | 17380047 | 329236 | 245402 | 83834 | 2729872 | 300000 | 2429872 | 23200 | 0 | 23200 | 0 | 0 | 0 | 11600 | 0 | 11600 | 23200 | 0 | 23200 | 0 | 0 | 0 | 11600 | 0 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1200000 | 1200000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 600000 | 500000 | 100000 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 8000 | 0 | 8000 | 74880 | 0 | 74880 | 0 | 0 | 0 | 25000 | 0 | 25000 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 78115 | 0 | 78115 | 29386925 | 6852149 | 22534776 | 1809216 | 1648383 | 160833 | 5664187 | 2000000 | 3664187 | 29386925 | 6852149 | 22534776 | 1809216 | 1648383 | 160833 | 5664187 | 2000000 | 3664187 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2011 | Q3 | Q3 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 22232196 | 4852149 | 17380047 | 630775 | 318979 | 311796 | 3000000 | 375000 | 2625000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 15000 | 0 | 15000 | 33500 | 0 | 33500 | 0 | 0 | 0 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 0 | 0 | 0 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 76999 | 0 | 76999 | 29386925 | 6852149 | 22534776 | 2110755 | 1721960 | 388795 | 6520379 | 2175000 | 4345379 | 29386925 | 6852149 | 22534776 | 2110755 | 1721960 | 388795 | 6520379 | 2175000 | 4345379 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2011 | Q4 | Q4 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | 22232196 | 4852149 | 17380047 | 2755514 | 488334 | 2267180 | 8100000 | 1100000 | 7000000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 100000 | 0 | 100000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 76999 | 0 | 76999 | 29386925 | 6852149 | 22534776 | 4343874 | 1891315 | 2452559 | 11605379 | 2900000 | 8705379 | 29386925 | 6852149 | 22534776 | 4343874 | 1891315 | 2452559 | 11605379 | 2900000 | 8705379 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2012 | Q1 | Q1 - 2012 | 3592892 | 0 | 3592892 | 100000 | 0 | 100000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 5367851 | 939657 | 4428194 | 15000000 | 2500000 | 12500000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 468890 | 468890 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 300000 | 300000 | 0 | 600000 | 500000 | 100000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 35000 | 0 | 35000 | 40000 | 0 | 40000 | 29386925 | 6852149 | 22534776 | 7380121 | 2708547 | 4671574 | 20073380 | 4800000 | 15273380 | 29386925 | 6852149 | 22534776 | 7380121 | 2708547 | 4671574 | 20073380 | 4800000 | 15273380 | 0 | 0 | University of Illinois
NT10BIX5570044 | INF | 2012 | Q2 | Q2 - 2012 | 3592892 | 0 | 3592892 | 900000 | 0 | 900000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 10188453 | 2497341 | 7691111 | 16000000 | 3500000 | 12500000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1468890 | 1468890 | 0 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 50000 | 0 | 50000 | 200000 | 0 | 200000 | 783992 | 0 | 783992 | 500000 | 0 | 500000 | 700000 | 0 | 700000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 40000 | 0 | 40000 | 45000 | 0 | 45000 | 29386925 | 6852149 | 22534776 | 13255723 | 3966231 | 9289491 | 21278380 | 5000000 | 16278380 | 29386925 | 6852149 | 22534776 | 13255723 | 3966231 | 9289491 | 21278380 | 5000000 | 16278380 | 0 | 60000 | University of Illinois
NT10BIX5570044 | INF | 2012 | Q3 | Q3 - 2012 | 3592892 | 0 | 3592892 | 2120761 | 0 | 2120761 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 11029156 | 3021019 | 8008137 | 16000000 | 4800000 | 11200000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 20000 | 0 | 20000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1468890 | 1468890 | 0 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 200000 | 0 | 200000 | 400000 | 0 | 400000 | 783992 | 0 | 783992 | 500000 | 0 | 500000 | 600000 | 0 | 600000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 48886 | 0 | 48886 | 51500 | 0 | 51500 | 29386925 | 6852149 | 22534776 | 15476073 | 4489909 | 10986164 | 21394880 | 6300000 | 15094880 | 29386925 | 6852149 | 22534776 | 15476073 | 4489909 | 10986164 | 21394880 | 6300000 | 15094880 | 0 | 60000 | University of Illinois
NT10BIX5570044 | INF | 2012 | Q4 | Q4 - 2012 | 3592892 | 0 | 3592892 | 2500000 | 0 | 2500000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 13489164 | 3186065 | 10303099 | 15000000 | 3200000 | 11800000 | 23200 | 0 | 23200 | 20000 | 0 | 20000 | 53000 | 0 | 53000 | 23200 | 0 | 23200 | 20000 | 0 | 20000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1668890 | 1500000 | 168890 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 300000 | 57529 | 242471 | 400000 | 157529 | 242471 | 783992 | 0 | 783992 | 550000 | 0 | 550000 | 600000 | 0 | 600000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 60000 | 0 | 60000 | 70000 | 0 | 70000 | 29386925 | 6852149 | 22534776 | 18716434 | 4743594 | 13972840 | 20454580 | 4857529 | 15597051 | 29386925 | 6852149 | 22534776 | 18716434 | 4743594 | 13972840 | 20454580 | 4857529 | 15597051 | 0 | 717187 | University of Illinois
NT10BIX5570044 | INF | 2013 | Q1 | Q1 - 2013 | 3592892 | 2391345 | 1201547 | 3166295 | 1692993 | 1473302 | 3250000 | 2048453 | 1201547 | 22126108 | 2854716 | 19271392 | 13555046 | 2000000 | 11555046 | 17000000 | 2000000 | 15000000 | 23200 | 0 | 23200 | 53000 | 0 | 53000 | 70000 | 0 | 70000 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1700000 | 1500000 | 200000 | 1802479 | 1500000 | 302479 | 742471 | 0 | 742471 | 400000 | 157529 | 242471 | 500000 | 257529 | 242471 | 783992 | 0 | 783992 | 600000 | 0 | 600000 | 650000 | 0 | 650000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 60000 | 0 | 60000 | 65000 | 0 | 65000 | 29280837 | 6746061 | 22534776 | 19665921 | 5350522 | 14315399 | 23469059 | 5805982 | 17663077 | 29280837 | 6746061 | 22534776 | 19665921 | 5350522 | 14315399 | 23469059 | 5805982 | 17663077 | 0 | 945673 | University of Illinois
NT10BIX5570044 | INF | 2013 | Q2 | Q2 - 2013 | 3592892 | 2391345 | 1201547 | 3200000 | 2093056 | 450000 | 3592892 | 2391345 | 1201547 | 22126108 | 2854716 | 19271392 | 17441046 | 2200000 | 15897990 | 22079308 | 2654716 | 19224592 | 23200 | 0 | 23200 | 70000 | 0 | 70000 | 70000 | 0 | 70000 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1750000 | 1500000 | 250000 | 1802479 | 1500000 | 302479 | 742471 | 0 | 742471 | 500000 | 200000 | 300000 | 742471 | 200000 | 542471 | 783992 | 0 | 783992 | 650000 | 0 | 650000 | 783992 | 0 | 783992 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 65000 | 0 | 65000 | 78115 | 0 | 78115 | 29280837 | 6746061 | 22534776 | 23807626 | 5993056 | 17814570 | 29280837 | 6746061 | 22334776 | 29280837 | 6746061 | 22534776 | 23807626 | 5993056 | 17814570 | 29280837 | 6746061 | 22334776 | 0 | 78765 | University of Illinois
NT10BIX5570044 | INF | 2013 | Q3 | Q3 - 2013 | 3592892 | 2391345 | 1201547 | 2844388 | 2352142 | 492246 | 2844388 | 2352142 | 492246 | 22126108 | 2854716 | 19271392 | 22838991 | 2906013 | 19932978 | 22838991 | 2906013 | 19932978 | 23200 | 0 | 23200 | 111605 | 0 | 111605 | 111605 | 0 | 111605 | 23200 | 0 | 23200 | 46750 | 0 | 46750 | 46750 | 0 | 46750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1851949 | 1487965 | 363984 | 1851949 | 1487965 | 363984 | 742471 | 0 | 742471 | 836299 | 0 | 836299 | 836299 | 0 | 836299 | 783992 | 0 | 783992 | 619447 | 0 | 619447 | 619447 | 0 | 619447 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 23087 | 0 | 23087 | 23087 | 0 | 23087 | 29280837 | 6746061 | 22534776 | 29280896 | 6746120 | 22534776 | 29280896 | 6746120 | 22534776 | 29280837 | 6746061 | 22534776 | 29280896 | 6746120 | 22534776 | 29280896 | 6746120 | 22534776 | 0 | 0 | University of Illinois
NT10BIX5570045 | INF | 2010 | Q3 | Q3 - 2010 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 3673242 | 3223242 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 0 | 0 | 0 | 3728242 | 3223242 | 505000 | 8859615 | 3753242 | 5106373 | 0 | 0 | 0 | 3728242 | 3223242 | 505000 | 0 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2010 | Q4 | Q4 - 2010 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 3673242 | 3223242 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 29880 | 1455 | 28425 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 29880 | 1455 | 28425 | 3728242 | 3223242 | 505000 | 8859615 | 3753242 | 5106373 | 29880 | 1455 | 28425 | 3728242 | 3223242 | 505000 | 0 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2011 | Q1 | Q1 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 465200 | 206000 | 259200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 36464 | 2035 | 34429 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 36464 | 2035 | 34429 | 520200 | 206000 | 314200 | 8859615 | 3753242 | 5106373 | 36464 | 2035 | 34429 | 520200 | 206000 | 314200 | 0 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2011 | Q2 | Q2 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 400710 | 183022 | 217688 | 4297163 | 3754841 | 542322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 44405 | 0 | 44405 | 58160 | 0 | 58160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 445115 | 183022 | 262093 | 4365323 | 3754841 | 610482 | 8859615 | 3753242 | 5106373 | 445115 | 183022 | 262093 | 4365323 | 3754841 | 610482 | 0 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2011 | Q3 | Q3 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 3910418 | 3436185 | 474233 | 4686185 | 3436185 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 76101 | 0 | 76101 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 3986519 | 3436185 | 550334 | 4796185 | 3436185 | 1360000 | 8859615 | 3753242 | 5106373 | 3986519 | 3436185 | 550334 | 4796185 | 3436185 | 1360000 | 0 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2011 | Q4 | Q4 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 4762194 | 3460027 | 1211043 | 5560027 | 3460027 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 91124 | 0 | 91124 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 4853318 | 3460027 | 1302167 | 5710027 | 3460027 | 2250000 | 8859615 | 3753242 | 5106373 | 4853318 | 3460027 | 1302167 | 5710027 | 3460027 | 2250000 | 298800 | 5400 | University of Wisconsin System
NT10BIX5570045 | INF | 2012 | Q1 | Q1 - 2012 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 5421441 | 3493857 | 1927584 | 5651441 | 3523857 | 2127584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 123293 | 0 | 123293 | 160000 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 5544734 | 3493857 | 2050877 | 5811441 | 3523857 | 2287584 | 8859615 | 3753242 | 5106373 | 5544734 | 3493857 | 2050877 | 5811441 | 3523857 | 2287584 | 298800 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2012 | Q2 | Q2 - 2012 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 5530584 | 3522261 | 2008323 | 5990584 | 3572261 | 2418323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 156534 | 0 | 156534 | 181534 | 0 | 181534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 5687118 | 3522261 | 2164857 | 6182118 | 3572261 | 2609857 | 8859615 | 3753242 | 5106373 | 5687118 | 3522261 | 2164857 | 6182118 | 3572261 | 2609857 | 298800 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2012 | Q3 | Q3 - 2012 | 1625712 | 0 | 1625712 | 0 | 0 | 0 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 5760535 | 3548833 | 2211702 | 6834082 | 3753242 | 3080840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 169488 | 0 | 169488 | 260000 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 5930023 | 3548833 | 2381190 | 8779794 | 3753242 | 5026552 | 8859615 | 3753242 | 5106373 | 5930023 | 3548833 | 2381190 | 8779794 | 3753242 | 5026552 | 298000 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2012 | Q4 | Q4 - 2012 | 1625712 | 0 | 1625712 | 0 | 0 | 0 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 6355835 | 3574330 | 2781505 | 6920353 | 3753242 | 3167111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 179549 | 0 | 179549 | 253550 | 0 | 253550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 6535384 | 3574330 | 2961054 | 8859615 | 3753242 | 5106373 | 8859615 | 3753242 | 5106373 | 6535384 | 3574330 | 2961054 | 8859615 | 3753242 | 5106373 | 298000 | 0 | University of Wisconsin System
NT10BIX5570045 | INF | 2013 | Q1 | Q1 - 2013 | 1625712 | 0 | 1625712 | 1625712 | 0 | 1625712 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 6473070 | 3461360 | 3011710 | 6834082 | 3753242 | 3080840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 295671 | 0 | 295671 | 339821 | 0 | 339821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 8394453 | 3461360 | 4933093 | 8859615 | 3753242 | 5106373 | 8859615 | 3753242 | 5106373 | 8394453 | 3461360 | 4933093 | 8859615 | 3753242 | 5106373 | 298000 | 71200 | University of Wisconsin System
NT10BIX5570045 | INF | 2013 | Q2 | Q2 - 2013 | 1625712 | 0 | 1625712 | 1523464 | 0 | 1523464 | 1523464 | 0 | 1523464 | 6834082 | 3753242 | 3080840 | 7121335 | 3869042 | 3252293 | 7121335 | 3869042 | 3252293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 298304 | 0 | 298304 | 298304 | 0 | 298304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 9735 | 0 | 9735 | 9735 | 0 | 9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 22577 | 0 | 22577 | 22577 | 0 | 22577 | 8859615 | 3753242 | 5106373 | 8975415 | 3869042 | 5106373 | 8975415 | 3869042 | 5106373 | 8859615 | 3753242 | 5106373 | 8975415 | 3869042 | 5106373 | 8975415 | 3869042 | 5106373 | 298000 | 115800 | University of Wisconsin System
NT10BIX5570046 | INF | 2010 | Q3 | Q3 - 2010 | 21118145 | 7343730 | 13774415 | 0 | 219140 | 219140 | 219140 | 219140 | 0 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 5075490 | 5075490 | 0 | 5075490 | 5075490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 0 | 0 | 0 | 493301 | 0 | 493301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5075490 | 5294630 | 219140 | 5787931 | 5294630 | 493301 | 95016532 | 14420117 | 80596415 | 5075490 | 5294630 | 219140 | 5787931 | 5294630 | 493301 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570046 | INF | 2010 | Q4 | Q4 - 2010 | 21118145 | 7343730 | 13774415 | 218476 | 218476 | 0 | 3534532 | 3484532 | 50000 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 5075490 | 5075490 | 0 | 5075490 | 5075490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 735 | 0 | 735 | 900735 | 0 | 900735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5294701 | 5293966 | 735 | 9510757 | 8560022 | 950735 | 95016532 | 14420117 | 80596415 | 5294701 | 5293966 | 735 | 9510757 | 8560022 | 950735 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570046 | INF | 2011 | Q1 | Q1 - 2011 | 21118145 | 7343730 | 13774415 | 3486840 | 3486840 | 0 | 3547204 | 3486840 | 60364 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 5266289 | 5266289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 366359 | 0 | 366359 | 1746359 | 0 | 1746359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5663297 | 5296938 | 366359 | 12369950 | 10563227 | 1806723 | 95016532 | 14420117 | 80596415 | 5663297 | 5296938 | 366359 | 12369950 | 10563227 | 1806723 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570046 | INF | 2011 | Q2 | Q2 - 2011 | 21118145 | 7343730 | 13774415 | 3552228 | 3486840 | 65388 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 366359 | 0 | 366359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5728685 | 5296938 | 431747 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5728685 | 5296938 | 431747 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570046 | INF | 2011 | Q3 | Q3 - 2011 | 21118145 | 7343730 | 13774415 | 286837 | 221448 | 65389 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 528858 | 0 | 528858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 815695 | 221448 | 594247 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 815695 | 221448 | 594247 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570046 | INF | 2011 | Q4 | Q4 - 2011 | 21118145 | 7343730 | 13774415 | 3539156 | 3486840 | 52316 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 551 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 684295 | 0 | 684295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 6034100 | 5297489 | 736611 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 6034100 | 5297489 | 736611 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents
NT10BIX5570047 | INF | 2010 | Q3 | Q3 - 2010 | 15517288 | 7414371 | 8102917 | 0 | 0 | 0 | 2500000 | 0 | 2500000 | 70065546 | 11209538 | 58856008 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 598165 | 0 | 598165 | 1000000 | 0 | 1000000 | 2136368 | 0 | 2136368 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8194858 | 0 | 8194858 | 377622 | 0 | 377622 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84347997 | 975787 | 0 | 975787 | 4350000 | 20000 | 4330000 | 106546591 | 22198594 | 84347997 | 975787 | 0 | 975787 | 4350000 | 20000 | 4330000 | 2022249 | 0 | Northwest Open Access Network
NT10BIX5570047 | INF | 2010 | Q4 | Q4 - 2010 | 15517288 | 7414371 | 8102917 | 1993702 | 0 | 1993702 | 3000000 | 0 | 3000000 | 70065546 | 11209538 | 58856008 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 1164824 | 0 | 1164824 | 2250000 | 0 | 2250000 | 2136368 | 0 | 2136368 | 344948 | 0 | 344948 | 1000000 | 0 | 1000000 | 8194858 | 0 | 8194858 | 961349 | 0 | 961349 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207687 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84348006 | 4464823 | 0 | 4464823 | 9250000 | 0 | 9250000 | 106546591 | 22198594 | 84348006 | 4464823 | 0 | 4464823 | 9250000 | 0 | 9250000 | 2022249 | 0 | Northwest Open Access Network
NT10BIX5570047 | INF | 2011 | Q1 | Q1 - 2011 | 15517288 | 7414371 | 8102917 | 2651274 | 0 | 2651274 | 4000000 | 0 | 4000000 | 70065546 | 11209538 | 58856008 | 66205 | 57635 | 62078 | 2000000 | 100000 | 1900000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 1379394 | 246 | 1379148 | 2000000 | 500 | 1999500 | 2136368 | 0 | 2136368 | 837886 | 0 | 837886 | 1300000 | 0 | 1300000 | 8194858 | 0 | 8194858 | 1532447 | 2949 | 1529498 | 2200000 | 5000 | 2195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84347997 | 6467206 | 60830 | 6459884 | 11500000 | 105500 | 11394500 | 106546591 | 22198594 | 84347997 | 6467206 | 60830 | 6459884 | 11500000 | 105500 | 11394500 | 2022249 | 0 | Northwest Open Access Network
NT10BIX5570047 | INF | 2011 | Q2 | Q2 - 2011 | 15517288 | 7414371 | 8102917 | 2742881 | 0 | 2742881 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 411548 | 255608 | 155940 | 7500000 | 5000000 | 2500000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 4000 | 0 | 4000 | 3500000 | 3455000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 2784033 | 246 | 2783787 | 4200000 | 0 | 4200000 | 2136368 | 0 | 2136368 | 1662144 | 0 | 1662144 | 2500000 | 0 | 2500000 | 8194858 | 0 | 8194858 | 2286890 | 2949 | 2283941 | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 137433 | 0 | 137433 | 170000 | 0 | 170000 | 106546591 | 22198594 | 84347997 | 10028929 | 258803 | 9770126 | 34870000 | 17455000 | 17375000 | 106546591 | 22198594 | 84347997 | 10028929 | 258803 | 9770126 | 34870000 | 17455000 | 17375000 | 2022249 | 0 | Northwest Open Access Network
NT10BIX5570047 | INF | 2011 | Q3 | Q3 - 2011 | 15517288 | 7414371 | 8102917 | 13270584 | 8925408 | 4345176 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 6870011 | 5280454 | 1589557 | 21000000 | 6000000 | 15000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 3446687 | 3438187 | 8500 | 3600000 | 3500000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 3509870 | 0 | 3509870 | 4000000 | 0 | 4000000 | 2136368 | 0 | 2136368 | 2962656 | 0 | 2962656 | 3500000 | 0 | 3500000 | 8194858 | 0 | 8194858 | 2831443 | 0 | 2831443 | 4000000 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 148871 | 0 | 148871 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 33040122 | 17644049 | 15396073 | 50260000 | 18500000 | 31760000 | 106546591 | 22198594 | 84347997 | 33040122 | 17644049 | 15396073 | 50260000 | 18500000 | 31760000 | 0 | 0 | Northwest Open Access Network
NT10BIX5570047 | INF | 2011 | Q4 | Q4 - 2011 | 15517288 | 7414371 | 8102917 | 13822766 | 8925408 | 4897358 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 21274518 | 6056020 | 15218499 | 35000000 | 7000000 | 28000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 3450473 | 3438187 | 12286 | 3600000 | 3580000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 3961296 | 0 | 3961296 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 3632456 | 0 | 3632456 | 4100000 | 0 | 4100000 | 8194858 | 0 | 8194858 | 5016575 | 0 | 5016575 | 6500000 | 0 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158181 | 0 | 158181 | 175000 | 0 | 175000 | 106546591 | 22198594 | 84347997 | 51316265 | 18419615 | 32896651 | 67875000 | 19580000 | 48295000 | 106546591 | 22198594 | 84347997 | 51316265 | 18419615 | 32896651 | 67875000 | 19580000 | 48295000 | 0 | 7686 | Northwest Open Access Network
NT10BIX5570047 | INF | 2012 | Q1 | Q1 - 2012 | 15517288 | 7414371 | 8102917 | 14807631 | 8925408 | 5882223 | 15500000 | 8926000 | 6574000 | 70065546 | 11209538 | 58856008 | 26447066 | 6329759 | 20117307 | 34000000 | 7000000 | 27000000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 500 | 0 | 500 | 3845935 | 3574685 | 271250 | 3456204 | 3438187 | 18017 | 3550000 | 3500000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4278912 | 0 | 4278912 | 5266912 | 0 | 5266912 | 2136368 | 0 | 2136368 | 4440091 | 0 | 4440091 | 4440091 | 0 | 4440091 | 8194858 | 0 | 8194858 | 6089689 | 0 | 6089689 | 6800000 | 0 | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158181 | 0 | 158181 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 59678244 | 18693354 | 40984890 | 69717503 | 19426000 | 50291503 | 106546591 | 22198594 | 84347997 | 59678244 | 18693354 | 40984890 | 69717503 | 19426000 | 50291503 | 0 | 16302 | Northwest Open Access Network
NT10BIX5570047 | INF | 2012 | Q2 | Q2 - 2012 | 15517288 | 7414371 | 8102917 | 15243998 | 8925408 | 6318590 | 15800000 | 8926000 | 6874000 | 70065546 | 11209538 | 58856008 | 34869041 | 7189045 | 27679996 | 41516621 | 8000000 | 33516621 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3465736 | 3438187 | 27549 | 3473187 | 3438187 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4510065 | 0 | 4510065 | 5321215 | 0 | 5321215 | 2136368 | 0 | 2136368 | 4908610 | 0 | 4908610 | 5400000 | 0 | 5400000 | 8194858 | 0 | 8194858 | 7154273 | 0 | 7154273 | 7600000 | 0 | 7600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158182 | 0 | 158182 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 70310375 | 19552640 | 50757735 | 79271493 | 20364187 | 58907306 | 106546591 | 22198594 | 84347997 | 70310375 | 19552640 | 50757735 | 79271493 | 20364187 | 58907306 | 0 | 25863 | Northwest Open Access Network
NT10BIX5570047 | INF | 2012 | Q3 | Q3 - 2012 | 15517288 | 7414371 | 8102917 | 16248688 | 8925408 | 7323280 | 17548688 | 8925408 | 8623280 | 70065546 | 11209538 | 58856008 | 44637624 | 7490737 | 37146887 | 48000000 | 8000000 | 40000000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4231198 | 0 | 4231198 | 4750000 | 0 | 4750000 | 2136368 | 0 | 2136368 | 5269490 | 0 | 5269490 | 5300000 | 0 | 5300000 | 8194858 | 0 | 8194858 | 9240771 | 0 | 9240771 | 10000000 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 146743 | 0 | 146743 | 165000 | 0 | 165000 | 106546591 | 22198594 | 84347997 | 83238840 | 19854332 | 63384508 | 89228014 | 20363595 | 68864419 | 106546591 | 22198594 | 84347997 | 83238840 | 19854332 | 63384508 | 89228014 | 20363595 | 68864419 | 0 | 47174 | Northwest Open Access Network
NT10BIX5570047 | INF | 2012 | Q4 | Q4 - 2012 | 15517288 | 7414371 | 8102917 | 16793949 | 8925408 | 7868541 | 17548688 | 8925408 | 8623280 | 70065546 | 11209538 | 58856008 | 51627191 | 7522142 | 44105049 | 55100000 | 8020000 | 47080000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4329645 | 0 | 4329645 | 4750000 | 0 | 4750000 | 2136368 | 0 | 2136368 | 5492079 | 0 | 5492079 | 5800000 | 0 | 5800000 | 8194858 | 0 | 8194858 | 10392561 | 0 | 10392561 | 11000000 | 0 | 11000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 146743 | 0 | 146743 | 146743 | 0 | 146743 | 106546591 | 22198594 | 84347997 | 92246494 | 19885737 | 72360757 | 97809757 | 20383595 | 77426162 | 106546591 | 22198594 | 84347997 | 92246494 | 19885737 | 72360757 | 97809757 | 20383595 | 77426162 | 0 | 120873 | Northwest Open Access Network
NT10BIX5570047 | INF | 2013 | Q1 | Q1 - 2013 | 15517288 | 7414371 | 8102917 | 19535101 | 8925408 | 10609693 | 20000000 | 8925408 | 11074592 | 70065546 | 11209538 | 58856008 | 56349041 | 7722078 | 48626963 | 60000000 | 8669270 | 51330730 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4411019 | 0 | 4411019 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 5684827 | 101 | 5684726 | 5800000 | 101 | 5799899 | 8194858 | 0 | 8194858 | 10920527 | 0 | 10920527 | 11200000 | 0 | 11200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 196441 | 0 | 196441 | 200000 | 0 | 200000 | 106546591 | 22198594 | 84347997 | 100561282 | 20085774 | 80475508 | 105164326 | 21032966 | 84131360 | 106546591 | 22198594 | 84347997 | 100561282 | 20085774 | 80475508 | 105164326 | 21032966 | 84131360 | 0 | 194626 | Northwest Open Access Network
NT10BIX5570047 | INF | 2013 | Q2 | Q2 - 2013 | 15517288 | 7414371 | 8102917 | 19457262 | 8925408 | 10531854 | 19457262 | 8925408 | 10531854 | 70065546 | 11209538 | 58856008 | 56962020 | 7821703 | 49140317 | 57381304 | 7900000 | 49481304 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4463881 | 0 | 4463881 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 5784368 | 0 | 5784368 | 6000000 | 0 | 6000000 | 8194858 | 0 | 8194858 | 11139390 | 0 | 11139390 | 11500000 | 0 | 11500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 198241 | 0 | 198241 | 200000 | 0 | 200000 | 106546591 | 22198594 | 84347997 | 101469488 | 20185298 | 81284190 | 102502892 | 20263595 | 82239297 | 106546591 | 22198594 | 84347997 | 101469488 | 20185298 | 81284190 | 102502892 | 20263595 | 82239297 | 0 | 177752 | Northwest Open Access Network
NT10BIX5570047 | INF | 2013 | Q3 | Q3 - 2013 | 17028234 | 8925407 | 8102827 | 20113221 | 8925407 | 11187814 | 20113221 | 8925407 | 11187814 | 68691098 | 9835000 | 58856098 | 60718783 | 9835000 | 50883783 | 60718783 | 9835000 | 50883783 | 1385673 | 0 | 1385673 | 4217 | 0 | 4217 | 4217 | 0 | 4217 | 3709437 | 3438187 | 271250 | 3510414 | 3438187 | 72227 | 3510414 | 3438187 | 72227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4585264 | 0 | 4585264 | 4585264 | 0 | 4585264 | 2136368 | 0 | 2136368 | 5993575 | 0 | 5993575 | 5993575 | 0 | 5993575 | 8194858 | 0 | 8194858 | 11417716 | 0 | 11417716 | 11417716 | 0 | 11417716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 203401 | 0 | 203401 | 203401 | 0 | 203401 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 0 | 0 | Northwest Open Access Network
NT10BIX5570049 | INF | 2010 | Q3 | Q3 - 2010 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 0 | 0 | 0 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 0 | 0 | 0 | 197666 | 39533 | 158133 | 22402 | 4480 | 17922 | 74304 | 14861 | 59443 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 12213 | 2443 | 9770 | 81133 | 16227 | 64906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 34615 | 6923 | 27692 | 155437 | 31088 | 124349 | 2283308 | 456662 | 1826646 | 34615 | 6923 | 27692 | 155437 | 31088 | 124349 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2010 | Q4 | Q4 - 2010 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 0 | 0 | 0 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 0 | 0 | 0 | 197666 | 39533 | 158133 | 80784 | 16157 | 64627 | 143250 | 28650 | 114600 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 68742 | 13748 | 54994 | 149674 | 29935 | 119739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 149526 | 29905 | 119621 | 292924 | 58585 | 234339 | 2283308 | 456662 | 1826646 | 149526 | 29905 | 119621 | 292924 | 58585 | 234339 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2011 | Q1 | Q1 - 2011 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 197666 | 39533 | 158133 | 130454 | 26091 | 104363 | 160453 | 32090 | 128363 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 120567 | 24113 | 96454 | 170568 | 34114 | 136454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 251021 | 50204 | 200817 | 646021 | 129204 | 516817 | 2283308 | 456662 | 1826646 | 251021 | 50204 | 200817 | 646021 | 129204 | 516817 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2011 | Q2 | Q2 - 2011 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 415039 | 83008 | 332031 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 187721 | 37544 | 150177 | 197666 | 39533 | 158133 | 169921 | 31146 | 138775 | 182921 | 36584 | 146337 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 2500 | 500 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 204468 | 36660 | 167808 | 258000 | 51600 | 206400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 4200 | 840 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 374389 | 67806 | 306583 | 1050381 | 210076 | 840305 | 2283308 | 456662 | 1826646 | 374389 | 67806 | 306583 | 1050381 | 210076 | 840305 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2011 | Q3 | Q3 - 2011 | 618991 | 123799 | 495193 | 0 | 0 | 0 | 271632 | 54326 | 217306 | 830297 | 166060 | 664237 | 0 | 0 | 0 | 30000 | 6000 | 24000 | 229666 | 45933 | 183733 | 201609 | 40322 | 161287 | 220600 | 44120 | 176480 | 234020 | 46804 | 187215 | 4850 | 970 | 3880 | 14850 | 2970 | 11880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282692 | 56538 | 226154 | 282337 | 56467 | 225870 | 324868 | 64974 | 259894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87642 | 17528 | 70114 | 0 | 0 | 0 | 10000 | 2000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 488796 | 97759 | 391037 | 871950 | 174390 | 697560 | 2283308 | 456662 | 1826646 | 488796 | 97759 | 391037 | 871950 | 174390 | 697560 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2011 | Q4 | Q4 - 2011 | 618991 | 123799 | 495193 | 275719 | 55144 | 220575 | 482250 | 96450 | 385800 | 830297 | 166060 | 664237 | 0 | 0 | 0 | 664238 | 132848 | 531390 | 229666 | 45933 | 183733 | 224768 | 44954 | 179814 | 229666 | 45933 | 183733 | 234020 | 46804 | 187215 | 4850 | 970 | 3880 | 20850 | 4170 | 16680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282692 | 56538 | 226154 | 315869 | 63174 | 252695 | 322692 | 64538 | 258154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87642 | 17528 | 70114 | 7750 | 1550 | 6200 | 20350 | 4070 | 16280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 828956 | 165792 | 663164 | 1740046 | 348009 | 1392037 | 2283308 | 456662 | 1826646 | 828956 | 165792 | 663164 | 1740046 | 348009 | 1392037 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2012 | Q1 | Q1 - 2012 | 618984 | 123797 | 495187 | 375044 | 75009 | 300035 | 402340 | 80468 | 321872 | 830304 | 166061 | 664243 | 153428 | 30686 | 122742 | 498182 | 99636 | 398546 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 4850 | 970 | 3880 | 24850 | 4970 | 19880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63174 | 252695 | 315869 | 63174 | 252695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 26437 | 5287 | 21150 | 27463 | 3493 | 23970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1117014 | 223403 | 893611 | 1510090 | 300018 | 1210072 | 2283308 | 456662 | 1826646 | 1117014 | 223403 | 893611 | 1510090 | 300018 | 1210072 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2012 | Q2 | Q2 - 2012 | 618984 | 123797 | 495187 | 439230 | 87846 | 351384 | 464238 | 92848 | 371390 | 830304 | 166061 | 664243 | 549194 | 109839 | 439355 | 736700 | 147340 | 589360 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 4850 | 970 | 3880 | 140412 | 28082 | 112330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1592780 | 318556 | 1274224 | 1940856 | 388171 | 1552685 | 2283308 | 456662 | 1826646 | 1592780 | 318556 | 1274224 | 1940856 | 388171 | 1552685 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2012 | Q3 | Q3 - 2012 | 618984 | 123797 | 495187 | 562625 | 112525 | 450100 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 806065 | 161213 | 644852 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 12950 | 2590 | 10360 | 152000 | 30400 | 121600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1981146 | 396229 | 1584917 | 2200794 | 440159 | 1760635 | 2283308 | 456662 | 1826646 | 1981146 | 396229 | 1584917 | 2200794 | 440159 | 1760635 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2012 | Q4 | Q4 - 2012 | 618984 | 123797 | 495187 | 581417 | 116283 | 465134 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 120094 | 24965 | 95129 | 234515 | 46903 | 187612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63174 | 252695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2131320 | 427209 | 1704111 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2131320 | 427209 | 1704111 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2013 | Q1 | Q1 - 2013 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 224899 | 45926 | 178973 | 234515 | 46904 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63173 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2273692 | 455684 | 1818008 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2273692 | 455684 | 1818008 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of
NT10BIX5570049 | INF | 2013 | Q2 | Q2 - 2013 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 234515 | 46904 | 187611 | 234515 | 46904 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63173 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of
NT10BIX5570050 | INF | 2010 | Q3 | Q3 - 2010 | 1913804 | 382761 | 1531043 | 0 | 0 | 0 | 113911 | 22782 | 91129 | 1663723 | 332745 | 1330978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 21450 | 4290 | 17160 | 688716 | 137743 | 550973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 106709 | 21342 | 84366 | 223149 | 44630 | 178519 | 102600 | 20520 | 82080 | 41486 | 8297 | 33189 | 66821 | 13364 | 53457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 169645 | 33929 | 134715 | 1092597 | 218519 | 874078 | 7671130 | 1534227 | 6136903 | 169645 | 33929 | 134715 | 1092597 | 218519 | 874078 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2010 | Q4 | Q4 - 2010 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 554146 | 110829 | 443317 | 1663723 | 332745 | 1330978 | 2575 | 515 | 2060 | 486535 | 97307 | 389228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1093212 | 218643 | 874570 | 1688400 | 337680 | 1350720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 225814 | 45162 | 180652 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 68446 | 13689 | 54756 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 1480670 | 296134 | 1184536 | 3060684 | 612137 | 2448547 | 7671130 | 1534227 | 6136903 | 1480670 | 296134 | 1184536 | 3060684 | 612137 | 2448547 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2011 | Q1 | Q1 - 2011 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 554146 | 110829 | 443317 | 1663723 | 332745 | 1330978 | 49783 | 9957 | 39827 | 486535 | 97307 | 389228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1333526 | 266705 | 1066821 | 1880735 | 376147 | 1504588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 226266 | 45253 | 181013 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 95059 | 19012 | 76047 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 1795257 | 359052 | 1436206 | 3253019 | 650604 | 2602415 | 7671130 | 1534227 | 6136903 | 1795257 | 359052 | 1436206 | 3253019 | 650604 | 2602415 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2011 | Q2 | Q2 - 2011 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 238543 | 47709 | 190834 | 1663723 | 332745 | 1330978 | 49784 | 9957 | 39827 | 245566 | 49113 | 196453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1803428 | 361954 | 1441474 | 2385842 | 477168 | 1908674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 226866 | 45373 | 181493 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 2273301 | 455929 | 1817372 | 3201554 | 640311 | 2561243 | 7671130 | 1534227 | 6136903 | 2273301 | 455929 | 1817372 | 3201554 | 640311 | 2561243 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2011 | Q3 | Q3 - 2011 | 1913804 | 382761 | 1531043 | 529067 | 105814 | 423253 | 1159067 | 231814 | 927253 | 1663723 | 332745 | 1330978 | 49784 | 9957 | 39827 | 881645 | 176329 | 705316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 2907038 | 581407 | 2325631 | 3288181 | 657636 | 2630545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 3817563 | 763513 | 3054050 | 5660567 | 1132114 | 4528453 | 7671130 | 1534227 | 6136903 | 3817563 | 763513 | 3054050 | 5660567 | 1132114 | 4528453 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2011 | Q4 | Q4 - 2011 | 1913804 | 382761 | 1531043 | 1009723 | 201945 | 807778 | 1375000 | 275000 | 1100000 | 1663723 | 332745 | 1330978 | 231602 | 46320 | 185282 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 3480056 | 696011 | 2784045 | 3650000 | 730000 | 2920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 5053055 | 1010611 | 4042444 | 6806674 | 1361335 | 5445339 | 7671130 | 1534227 | 6136903 | 5053055 | 1010611 | 4042444 | 6806674 | 1361335 | 5445339 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2012 | Q1 | Q1 - 2012 | 1913804 | 382761 | 1531043 | 1273302 | 254661 | 1018641 | 1600000 | 320000 | 1280000 | 1663723 | 332745 | 1330978 | 453136 | 90627 | 362509 | 950000 | 190000 | 760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 3798592 | 759718 | 3038874 | 3798592 | 759718 | 3038874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 5856704 | 1171341 | 4685363 | 6680266 | 1336053 | 5344213 | 7671130 | 1534227 | 6136903 | 5856704 | 1171341 | 4685363 | 6680266 | 1336053 | 5344213 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2012 | Q2 | Q2 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 986105 | 197221 | 788884 | 1780798 | 356160 | 1424638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4178614 | 835722 | 3342892 | 4210356 | 842071 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 6769695 | 1353939 | 5415756 | 7596130 | 1519227 | 6076903 | 7671130 | 1534226 | 6136904 | 6769695 | 1353939 | 5415756 | 7596130 | 1519227 | 6076903 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2012 | Q3 | Q3 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1307862 | 261572 | 1046290 | 1830798 | 366160 | 1464638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4180484 | 836096 | 3344388 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7093322 | 1418664 | 5674658 | 7646130 | 1529226 | 6116903 | 7671130 | 1534226 | 6136904 | 7093322 | 1418664 | 5674658 | 7646130 | 1529226 | 6116903 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2012 | Q4 | Q4 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1806799 | 361359 | 1445440 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4192063 | 838412 | 3353651 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7603838 | 1520767 | 6083071 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7603838 | 1520767 | 6083071 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2013 | Q1 | Q1 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2013 | Q2 | Q2 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570050 | INF | 2013 | Q3 | Q3 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC
NT10BIX5570051 | INF | 2010 | Q3 | Q3 - 2010 | 1251330 | 173866 | 1077464 | 389 | 389 | 0 | 350000 | 70000 | 280000 | 1021226 | 222890 | 798336 | 58465 | 58465 | 0 | 85000 | 67000 | 18000 | 149950 | 149950 | 0 | 6369 | 6369 | 0 | 30043 | 0 | 30043 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 350000 | 15000 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 15000 | 3000 | 12000 | 2992029 | 598406 | 2393923 | 86923 | 86923 | 0 | 861743 | 176700 | 685043 | 2992029 | 598406 | 2393923 | 86923 | 86923 | 0 | 861743 | 176700 | 685043 | 440000 | 0 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2010 | Q4 | Q4 - 2010 | 1251330 | 173866 | 1077464 | 389 | 389 | 0 | 350000 | 70000 | 280000 | 1021226 | 222890 | 798336 | 66852 | 66852 | 0 | 85000 | 67000 | 18000 | 149950 | 149950 | 0 | 11987 | 11987 | 0 | 30043 | 30043 | 0 | 430230 | 22000 | 408230 | 150 | 150 | 0 | 350000 | 15000 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 15000 | 3000 | 12000 | 2992029 | 598406 | 2393923 | 101078 | 101078 | 0 | 861743 | 206743 | 655000 | 2992029 | 598406 | 2393923 | 101078 | 101078 | 0 | 861743 | 206743 | 655000 | 440000 | 0 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2011 | Q1 | Q1 - 2011 | 1251330 | 173866 | 1077464 | 1576 | 1576 | 0 | 200000 | 6576 | 193424 | 1021226 | 222890 | 798336 | 75866 | 75866 | 0 | 83866 | 83866 | 0 | 149950 | 149950 | 0 | 25579 | 25579 | 0 | 37579 | 37579 | 0 | 430230 | 22000 | 408230 | 99916 | 700 | 99916 | 224916 | 700 | 224216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 0 | 0 | 0 | 2992029 | 598406 | 2393923 | 224637 | 125421 | 99916 | 578061 | 150421 | 427640 | 2992029 | 598406 | 2393923 | 224637 | 125421 | 99916 | 578061 | 150421 | 427640 | 440000 | 0 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2011 | Q2 | Q2 - 2011 | 1251330 | 173866 | 1077464 | 225285 | 14045 | 211240 | 565285 | 29045 | 536240 | 1021226 | 222890 | 798336 | 99278 | 99278 | 0 | 304278 | 154278 | 150000 | 149950 | 149950 | 0 | 45995 | 45995 | 0 | 60000 | 60000 | 0 | 430230 | 22000 | 408230 | 328270 | 700 | 327570 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 18127 | 0 | 18127 | 37627 | 0 | 37627 | 2992029 | 598406 | 2393623 | 738655 | 181718 | 556937 | 1439120 | 287023 | 1152097 | 2992029 | 598406 | 2393623 | 738655 | 181718 | 556937 | 1439120 | 287023 | 1152097 | 440000 | 0 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2011 | Q3 | Q3 - 2011 | 1251330 | 173866 | 1077464 | 526671 | 20898 | 505773 | 691671 | 40898 | 650773 | 1021226 | 222890 | 798336 | 133670 | 130424 | 3246 | 275670 | 195424 | 80246 | 149950 | 149950 | 0 | 47839 | 47839 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 407644 | 5813 | 401831 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 38641 | 0 | 38641 | 45641 | 0 | 45641 | 2992029 | 598406 | 2393623 | 1196165 | 226674 | 969491 | 1564912 | 360022 | 1204890 | 2992029 | 598406 | 2393623 | 1196165 | 226674 | 969491 | 1564912 | 360022 | 1204890 | 440000 | 0 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2011 | Q4 | Q4 - 2011 | 1251330 | 173866 | 1077464 | 612327 | 37937 | 574390 | 912327 | 80000 | 832327 | 1021226 | 222890 | 798336 | 202937 | 182471 | 20466 | 275000 | 204534 | 70466 | 149950 | 149950 | 0 | 51073 | 51073 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 42605 | 0 | 42605 | 54740 | 2000 | 52740 | 2992029 | 598406 | 2393623 | 1385873 | 300503 | 1085370 | 1798998 | 395556 | 1403442 | 2992029 | 598406 | 2393623 | 1385873 | 300503 | 1085370 | 1798998 | 395556 | 1403442 | 440000 | 4541 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2012 | Q1 | Q1 - 2012 | 1251330 | 173866 | 1077464 | 771785 | 46764 | 725021 | 921785 | 96764 | 825021 | 1021226 | 222890 | 798336 | 229260 | 206110 | 23150 | 247000 | 222000 | 25000 | 149950 | 149950 | 0 | 52875 | 52875 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 51215 | 0 | 51215 | 55307 | 0 | 55307 | 2992029 | 598406 | 2393623 | 1582066 | 334771 | 1247295 | 1781023 | 427786 | 1353237 | 2992029 | 598406 | 2393623 | 1582066 | 334771 | 1247295 | 1781023 | 427786 | 1353237 | 440000 | 10249 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2012 | Q2 | Q2 - 2012 | 1251330 | 173866 | 1077464 | 867116 | 51762 | 815354 | 1100000 | 70000 | 1030000 | 1021226 | 222890 | 798336 | 247276 | 203061 | 44215 | 290000 | 230000 | 60000 | 149950 | 149950 | 0 | 55076 | 55076 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 56310 | 1621 | 54689 | 74000 | 2000 | 72000 | 2992029 | 598406 | 2393623 | 1702709 | 340542 | 1362167 | 2020931 | 411022 | 1609909 | 2992029 | 598406 | 2393623 | 1702709 | 340542 | 1362167 | 2020931 | 411022 | 1609909 | 440000 | 16316 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2012 | Q3 | Q3 - 2012 | 1251330 | 173866 | 1077464 | 902527 | 52894 | 849633 | 1100000 | 65000 | 1035000 | 931456 | 222890 | 798336 | 275312 | 221785 | 53527 | 350000 | 265785 | 84215 | 149950 | 149950 | 0 | 55162 | 55162 | 0 | 60000 | 60000 | 0 | 520000 | 22000 | 408230 | 476071 | 20294 | 455777 | 520000 | 25000 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 57303 | 2614 | 54689 | 75000 | 8000 | 67000 | 2992029 | 598406 | 2393623 | 1808075 | 374449 | 1433626 | 2146700 | 445485 | 1701215 | 2992029 | 598406 | 2393623 | 1808075 | 374449 | 1433626 | 2146700 | 445485 | 1701215 | 440000 | 22559 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2012 | Q4 | Q4 - 2012 | 1251330 | 173866 | 1077464 | 1069577 | 59200 | 1010377 | 1136664 | 59200 | 1077464 | 931456 | 222890 | 708566 | 327388 | 243803 | 83585 | 377388 | 263803 | 113585 | 149950 | 149950 | 0 | 57693 | 57693 | 0 | 70000 | 70000 | 0 | 520000 | 22000 | 498000 | 510316 | 20294 | 490022 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 69917 | 8629 | 61288 | 83629 | 8629 | 75000 | 2992029 | 598406 | 2393623 | 2076591 | 411319 | 1665272 | 2229381 | 443626 | 1785755 | 2992029 | 598406 | 2393623 | 2076591 | 411319 | 1665272 | 2229381 | 443626 | 1785755 | 440000 | 29614 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2013 | Q1 | Q1 - 2013 | 1251330 | 173866 | 1077464 | 1145424 | 70848 | 1074576 | 1245424 | 90848 | 1154576 | 931456 | 222890 | 708566 | 383316 | 272426 | 110890 | 483316 | 292426 | 190890 | 149950 | 149950 | 0 | 58458 | 58458 | 0 | 78458 | 78458 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 70745 | 2749 | 67996 | 74725 | 3500 | 71225 | 2992029 | 598406 | 2393623 | 2219643 | 446475 | 1773168 | 2443623 | 507226 | 1936397 | 2992029 | 598406 | 2393623 | 2219643 | 446475 | 1773168 | 2443623 | 507226 | 1936397 | 440000 | 36408 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2013 | Q2 | Q2 - 2013 | 1351330 | 173866 | 1177464 | 1213610 | 74017 | 1139593 | 1251330 | 80000 | 1171330 | 831456 | 222890 | 608566 | 428843 | 288134 | 140709 | 485000 | 320000 | 165000 | 149950 | 149950 | 0 | 59150 | 59150 | 0 | 80000 | 80000 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 73386 | 2942 | 70444 | 97593 | 4000 | 93593 | 2992029 | 598406 | 2393623 | 2336689 | 466237 | 1870452 | 2475623 | 525994 | 1949629 | 2992029 | 598406 | 2393623 | 2336689 | 466237 | 1870452 | 2475623 | 525994 | 1949629 | 440000 | 7374 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2013 | Q3 | Q3 - 2013 | 1351330 | 173866 | 1177464 | 1235850 | 76390 | 1159460 | 1435850 | 81779 | 1354071 | 831456 | 222890 | 608566 | 485816 | 329040 | 156776 | 500816 | 332040 | 168776 | 149950 | 149950 | 0 | 59454 | 59454 | 0 | 84454 | 84454 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 75176 | 4732 | 70444 | 89176 | 6032 | 83144 | 2992029 | 598406 | 2393623 | 2417996 | 511610 | 1906386 | 2671996 | 546299 | 2125697 | 2992029 | 598406 | 2393623 | 2417996 | 511610 | 1906386 | 2671996 | 546299 | 2125697 | 440000 | 50367 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2013 | Q4 | Q4 - 2013 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1289850 | 86469 | 1203381 | 831456 | 222890 | 608566 | 502853 | 346077 | 156776 | 525000 | 346077 | 178923 | 149950 | 149950 | 0 | 69486 | 61341 | 8145 | 100000 | 65000 | 35000 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 76429 | 5985 | 70444 | 76429 | 5985 | 70444 | 2992029 | 598406 | 2393623 | 2500318 | 541866 | 1958452 | 2552979 | 545525 | 2007454 | 2992029 | 598406 | 2393623 | 2500318 | 541866 | 1958452 | 2552979 | 545525 | 2007454 | 440000 | 62157 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2014 | Q1 | Q1 - 2014 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1289850 | 86469 | 1203381 | 831456 | 222890 | 608566 | 506897 | 350121 | 156776 | 521897 | 355121 | 166776 | 149950 | 149950 | 0 | 90467 | 61529 | 28938 | 103938 | 65000 | 38938 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20194 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 78942 | 5985 | 72957 | 2992029 | 598406 | 2393623 | 2527856 | 546098 | 1981758 | 2556327 | 554469 | 2001758 | 2992029 | 598406 | 2393623 | 2527856 | 546098 | 1981758 | 2556327 | 554469 | 2001758 | 440000 | 75051 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2014 | Q2 | Q2 - 2014 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1336469 | 86469 | 1250000 | 831456 | 222890 | 608566 | 506897 | 350121 | 156776 | 535121 | 355121 | 180000 | 149950 | 149950 | 0 | 93860 | 64922 | 28938 | 105000 | 65000 | 40000 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 80985 | 5985 | 75000 | 2992029 | 598406 | 2393623 | 2531249 | 549491 | 1981758 | 2619275 | 554569 | 2064706 | 2992029 | 598406 | 2393623 | 2531249 | 549491 | 1981758 | 2619275 | 554569 | 2064706 | 440000 | 84286 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2014 | Q3 | Q3 - 2014 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1336469 | 86469 | 1250000 | 831456 | 222890 | 608566 | 506897 | 350121 | 156776 | 535121 | 355121 | 180000 | 149950 | 149950 | 0 | 103504 | 69766 | 33738 | 123504 | 79766 | 43738 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 80985 | 5985 | 75000 | 2992029 | 598406 | 2393623 | 2540893 | 554335 | 1986558 | 2637779 | 569335 | 2068444 | 2992029 | 598406 | 2393623 | 2540893 | 554335 | 1986558 | 2637779 | 569335 | 2068444 | 440000 | 96801 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2014 | Q4 | Q4 - 2014 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1351330 | 86469 | 1264861 | 831456 | 222890 | 608566 | 506897 | 350121 | 156776 | 531297 | 350121 | 181176 | 149950 | 149950 | 0 | 122460 | 75922 | 46538 | 122460 | 75922 | 46538 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 97593 | 5985 | 91608 | 2992029 | 598406 | 2393623 | 2559849 | 560491 | 1999358 | 2664380 | 560491 | 2103889 | 2992029 | 598406 | 2393623 | 2559849 | 560491 | 1999358 | 2664380 | 560491 | 2103889 | 440000 | 109311 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2015 | Q1 | Q1 - 2015 | 1651330 | 112369 | 1538961 | 1449422 | 86469 | 1362953 | 1651330 | 112369 | 1538961 | 531456 | 350121 | 181335 | 506897 | 350121 | 156776 | 531456 | 350121 | 181335 | 149950 | 85922 | 64028 | 124975 | 78437 | 46538 | 127975 | 81437 | 46538 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 97593 | 8000 | 89593 | 2992029 | 598406 | 2393623 | 2721936 | 563006 | 2158930 | 2970054 | 593921 | 2376133 | 2992029 | 598406 | 2393623 | 2721936 | 563006 | 2158930 | 2970054 | 593921 | 2376133 | 440000 | 123870 | First Step Internet, L.L.C.
NT10BIX5570051 | INF | 2015 | Q2 | Q2 - 2015 | 1651330 | 112369 | 1538961 | 1593865 | 88569 | 1505296 | 1651330 | 112369 | 1538961 | 531456 | 350121 | 181335 | 522267 | 355999 | 166268 | 531456 | 355999 | 175457 | 149950 | 85922 | 64028 | 124975 | 78437 | 46538 | 149950 | 80044 | 69906 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 78942 | 5985 | 72957 | 97593 | 8000 | 89593 | 2992029 | 598406 | 2393623 | 2881749 | 570984 | 2310765 | 2992029 | 598406 | 2393623 | 2992029 | 598406 | 2393623 | 2881749 | 570984 | 2310765 | 2992029 | 598406 | 2393623 | 440000 | 135916 | First Step Internet, L.L.C.
NT10BIX5570053 | INF | 2010 | Q3 | Q3 - 2010 | 5225979 | 0 | 5225979 | 671 | 0 | 671 | 1974675 | 0 | 1974675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 4063 | 0 | 4063 | 148777 | 0 | 148777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 100596 | 100596 | 0 | 504672 | 176635 | 328037 | 2553604 | 1328400 | 1225204 | 18060 | 13560 | 4500 | 1696917 | 882397 | 814520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 0 | 0 | 0 | 199821 | 0 | 199821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 33333 | 2968 | 30365 | 32383 | 12629 | 19753 | 10062992 | 2023200 | 8039792 | 156723 | 117124 | 39599 | 4557245 | 1071661 | 3485583 | 10062992 | 2023200 | 8039792 | 156723 | 117124 | 39599 | 4557245 | 1071661 | 3485583 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2010 | Q4 | Q4 - 2010 | 5225979 | 0 | 5225979 | 1115625 | 0 | 1115625 | 2350223 | 0 | 2350223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 20725 | 0 | 20725 | 189696 | 0 | 189696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 293476 | 264000 | 29476 | 658388 | 264000 | 394388 | 2553604 | 1328400 | 1225204 | 25192 | 25192 | 0 | 2213975 | 1151267 | 1062708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 7620 | 0 | 7620 | 140330 | 0 | 140330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 58158 | 15688 | 42470 | 146624 | 93839 | 52785 | 10062992 | 2023200 | 8039792 | 1520796 | 304880 | 1215916 | 5699236 | 1509106 | 4190130 | 10062992 | 2023200 | 8039792 | 1520796 | 304880 | 1215916 | 5699236 | 1509106 | 4190130 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2011 | Q1 | Q1 - 2011 | 5225979 | 0 | 5225979 | 2152922 | 6868 | 2146053 | 5159914 | 0 | 5159914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 36648 | 0 | 36648 | 298147 | 0 | 298147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 459811 | 421759 | 38052 | 685639 | 239974 | 445665 | 2553604 | 1328400 | 1225204 | 0 | 0 | 0 | 2305905 | 1199071 | 1106834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 14418 | 153 | 14265 | 204478 | 0 | 204478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 75297 | 30442 | 44855 | 219093 | 140220 | 78873 | 10062992 | 2023200 | 8039792 | 2739096 | 459222 | 2279873 | 8873176 | 1579265 | 7293911 | 10062992 | 2023200 | 8039792 | 2739096 | 459222 | 2279873 | 8873176 | 1579265 | 7293911 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2011 | Q2 | Q2 - 2011 | 5225979 | 0 | 5225979 | 4365807 | 217758 | 4148050 | 5215109 | 0 | 5215109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 71162 | 0 | 71162 | 361248 | 0 | 361248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 473971 | 264000 | 209971 | 678102 | 237336 | 440766 | 2553604 | 1328400 | 1225204 | 358321 | 358321 | 0 | 2298368 | 1195152 | 1103217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 64103 | 9609 | 54494 | 212519 | 0 | 212519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 150593 | 77947 | 72646 | 391887 | 250808 | 141079 | 10062992 | 2023200 | 8039792 | 5483957 | 927635 | 4556323 | 9157233 | 1683296 | 7473938 | 10062992 | 2023200 | 8039792 | 5483957 | 927635 | 4556323 | 9157233 | 1683296 | 7473938 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2011 | Q3 | Q3 - 2011 | 5225979 | 0 | 5225979 | 5431528 | 325293 | 5106235 | 5536035 | 310056 | 5225979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 85945 | 0 | 85945 | 464256 | 0 | 464256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 473971 | 264000 | 209971 | 691105 | 264000 | 427105 | 2553604 | 1328400 | 1225204 | 557053 | 541372 | 15681 | 2374852 | 1234923 | 1139929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 67588 | 13094 | 54494 | 329232 | 13094 | 316138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 205515 | 130089 | 75426 | 596959 | 382054 | 214905 | 10062992 | 2023200 | 8039792 | 6821600 | 1273848 | 5547752 | 9992439 | 2204127 | 7788312 | 10062992 | 2023200 | 8039792 | 6821600 | 1273848 | 5547752 | 9992439 | 2204127 | 7788312 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2011 | Q4 | Q4 - 2011 | 5225979 | 0 | 5225979 | 5334299 | 429473 | 4904826 | 6535044 | 745278 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 221455 | 114908 | 106547 | 245745 | 127408 | 118337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 1033135 | 337030 | 696105 | 1043135 | 347030 | 696105 | 2553604 | 1328400 | 1225204 | 713045 | 353977 | 359068 | 1399150 | 618176 | 780974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 128904 | 59439 | 69465 | 138904 | 69439 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 233414 | 153531 | 79883 | 251852 | 161969 | 89883 | 10062992 | 2023200 | 8039792 | 7664252 | 1448358 | 6215894 | 9613830 | 2069300 | 7544530 | 10062992 | 2023200 | 8039792 | 7664252 | 1448358 | 6215894 | 9613830 | 2069300 | 7544530 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2012 | Q1 | Q1 - 2012 | 5789766 | 0 | 5789766 | 5578366 | 447508 | 5130858 | 5987536 | 491951 | 5495585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 260003 | 136487 | 123516 | 315902 | 146229 | 169673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1090418 | 394313 | 696105 | 2349110 | 1262684 | 1086426 | 1229876 | 634524 | 595352 | 1819685 | 851564 | 968121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 235544 | 154986 | 80558 | 261761 | 160872 | 100889 | 10062992 | 2023200 | 8039792 | 8490851 | 1794997 | 6695854 | 9604691 | 2104853 | 7499838 | 10062992 | 2023200 | 8039792 | 8490851 | 1794997 | 6695854 | 9604691 | 2104853 | 7499838 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2012 | Q2 | Q2 - 2012 | 5789766 | 0 | 5789766 | 6162001 | 510602 | 5651399 | 6286349 | 588827 | 5697521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 271658 | 143476 | 128182 | 328973 | 154136 | 174837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1101332 | 405227 | 696105 | 2349110 | 1262684 | 1086426 | 1415656 | 789402 | 626254 | 1726807 | 947163 | 779645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 246378 | 157872 | 88506 | 273723 | 171425 | 102298 | 10062992 | 2023200 | 8039792 | 9282755 | 2022844 | 7259911 | 9846573 | 2326702 | 7519871 | 10062992 | 2023200 | 8039792 | 9282755 | 2022844 | 7259911 | 9846573 | 2326702 | 7519871 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2012 | Q3 | Q3 - 2012 | 5789766 | 0 | 5789766 | 6168864 | 517465 | 5651399 | 5789766 | 0 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 289568 | 143476 | 146092 | 329568 | 143476 | 186092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1188651 | 492546 | 696105 | 2349110 | 1262684 | 1086426 | 1877048 | 975298 | 901750 | 2170958 | 1119208 | 1051750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 138904 | 69439 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 260333 | 171827 | 88506 | 299414 | 198531 | 100883 | 10062992 | 2023200 | 8039792 | 9782875 | 2229558 | 7553317 | 9917261 | 2023200 | 7894061 | 10062992 | 2023200 | 8039792 | 9782875 | 2229558 | 7553317 | 9917261 | 2023200 | 7894061 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2012 | Q4 | Q4 - 2012 | 5789766 | 0 | 5789766 | 5775626 | 95751 | 5679875 | 5885517 | 95751 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 330798 | 163225 | 167573 | 431372 | 163225 | 268147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1057673 | 361568 | 696105 | 2349110 | 1262684 | 1086426 | 2071725 | 1160911 | 910814 | 2247337 | 1160911 | 1086426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 284204 | 181821 | 102383 | 311704 | 181821 | 129883 | 10062992 | 2023200 | 8039792 | 9649415 | 2023200 | 7626215 | 10062992 | 2023200 | 8039792 | 10062992 | 2023200 | 8039792 | 9649415 | 2023200 | 7626215 | 10062992 | 2023200 | 8039792 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570053 | INF | 2013 | Q1 | Q1 - 2013 | 5789766 | 0 | 5789766 | 6484248 | 662937 | 5821311 | 6484248 | 662937 | 5821311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 378338 | 138686 | 239652 | 378338 | 138686 | 239652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1322880 | 580036 | 742844 | 1322880 | 580036 | 742844 | 2349110 | 1262684 | 1086426 | 2386782 | 1354356 | 1032426 | 2386782 | 1354356 | 1032426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 133086 | 60171 | 72915 | 133086 | 60171 | 72915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 311220 | 180576 | 130644 | 311220 | 180576 | 130644 | 10062992 | 2023200 | 8039792 | 11016554 | 2976762 | 8039792 | 11016554 | 2976762 | 8039792 | 10062992 | 2023200 | 8039792 | 11016554 | 2976762 | 8039792 | 11016554 | 2976762 | 8039792 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E
NT10BIX5570054 | INF | 2010 | Q3 | Q3 - 2010 | 705331 | 141066 | 564265 | 0 | 0 | 0 | 0 | 0 | 0 | 1018203 | 203641 | 814562 | 0 | 0 | 0 | 0 | 0 | 0 | 82756 | 16553 | 66212 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 25567 | 5113 | 20454 | 0 | 0 | 0 | 3000 | 600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171560 | 34312 | 137248 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57750 | 11550 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061167 | 412235 | 1648941 | 0 | 0 | 0 | 78000 | 15600 | 62400 | 2061167 | 412235 | 1648941 | 0 | 0 | 0 | 78000 | 15600 | 62400 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2010 | Q4 | Q4 - 2010 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 67494 | 13499 | 53995 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 6125 | 1225 | 4900 | 320362 | 64073 | 256289 | 58815 | 11763 | 47052 | 77544 | 15509 | 62035 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 31250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 126763 | 25353 | 101410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 58815 | 11763 | 47052 | 309176 | 55586 | 222340 | 2061176 | 412235 | 1648941 | 58815 | 11763 | 47052 | 309176 | 55586 | 222340 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2011 | Q1 | Q1 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 74524 | 14905 | 59619 | 102110 | 20422 | 81688 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 15761 | 3152 | 12609 | 118761 | 23752 | 95009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 1200 | 240 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 90285 | 18057 | 72228 | 222071 | 44414 | 177657 | 2061176 | 412235 | 1648941 | 90285 | 18057 | 72228 | 222071 | 44414 | 177657 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2011 | Q2 | Q2 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 103364 | 20673 | 82691 | 118935 | 23787 | 95148 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 62500 | 12500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 28010 | 5602 | 22408 | 121354 | 24271 | 97083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 436 | 87 | 349 | 436 | 87 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 131810 | 26362 | 105448 | 303225 | 60645 | 242580 | 2061176 | 412235 | 1648941 | 131810 | 26362 | 105448 | 303225 | 60645 | 242580 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2011 | Q3 | Q3 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 151104 | 30221 | 120883 | 162000 | 32400 | 129600 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 32595 | 6526 | 26069 | 38500 | 7700 | 30800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 436 | 87 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 183699 | 36747 | 146952 | 200936 | 40187 | 160749 | 2061176 | 412235 | 1648941 | 183699 | 36747 | 146952 | 200936 | 40187 | 160749 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2011 | Q4 | Q4 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 320619 | 64124 | 256495 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 126342 | 25109 | 101233 | 142000 | 28400 | 113600 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 37117 | 7423 | 29694 | 44500 | 8900 | 35600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 163459 | 32532 | 130927 | 589619 | 117924 | 471695 | 2061176 | 412235 | 1648941 | 163459 | 32532 | 130927 | 589619 | 117924 | 471695 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2012 | Q1 | Q1 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 641237 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 35000 | 7000 | 28000 | 320362 | 64073 | 256289 | 149442 | 29730 | 119712 | 150000 | 30000 | 120000 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 187618 | 37523 | 150095 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13679 | 2736 | 10943 | 22000 | 4000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 381485 | 76138 | 305347 | 1037062 | 207012 | 830050 | 2061176 | 412235 | 1648941 | 381485 | 76138 | 305347 | 1037062 | 207012 | 830050 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2012 | Q2 | Q2 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 600000 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 300000 | 60000 | 240000 | 320362 | 64073 | 256289 | 150309 | 29902 | 120407 | 200000 | 40000 | 160000 | 374522 | 74904 | 299618 | 53834 | 10767 | 43067 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 139886 | 27977 | 111909 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13805 | 2761 | 11044 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 388580 | 77556 | 311024 | 1745847 | 357416 | 1429668 | 2061176 | 412235 | 1648941 | 388580 | 77556 | 311024 | 1745847 | 357416 | 1429668 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2012 | Q3 | Q3 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 641237 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 453730 | 90746 | 362984 | 320362 | 64073 | 256289 | 156249 | 31090 | 125160 | 160000 | 32000 | 128000 | 374522 | 74904 | 299618 | 59681 | 11936 | 47745 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 139886 | 27977 | 111909 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13805 | 2761 | 11044 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 400367 | 79913 | 320455 | 1826292 | 365258 | 1461034 | 2061176 | 412235 | 1648941 | 400367 | 79913 | 320455 | 1826292 | 365258 | 1461034 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2012 | Q4 | Q4 - 2012 | 620746 | 124149 | 496597 | 292465 | 58493 | 233972 | 641237 | 128247 | 512990 | 543551 | 108710 | 434841 | 254279 | 50856 | 203423 | 453730 | 90746 | 362984 | 330363 | 66073 | 264290 | 172247 | 34289 | 137958 | 300000 | 60000 | 240000 | 55000 | 11000 | 44000 | 288 | 58 | 230 | 55000 | 11000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451516 | 90303 | 361213 | 200109 | 40022 | 160087 | 451516 | 90303 | 361213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 12000 | 48000 | 13805 | 2761 | 11044 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 933193 | 186479 | 746714 | 1961483 | 392296 | 1569187 | 2061176 | 412235 | 1648941 | 933193 | 186479 | 746714 | 1961483 | 392296 | 1569187 | 0 | 0 | Page County Broadband Authority
NT10BIX5570054 | INF | 2013 | Q1 | Q1 - 2013 | 620746 | 124149 | 496597 | 292466 | 58493 | 233973 | 292466 | 58493 | 233973 | 543551 | 108710 | 434841 | 1003867 | 200773 | 803094 | 1003867 | 200773 | 803094 | 330363 | 66073 | 264290 | 201976 | 40236 | 161740 | 201976 | 40236 | 161740 | 55000 | 11000 | 44000 | 288 | 58 | 230 | 288 | 58 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451516 | 90303 | 361213 | 203787 | 40757 | 163030 | 203787 | 40757 | 163030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 12000 | 48000 | 13805 | 2761 | 11044 | 13805 | 2761 | 11044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 1716189 | 343078 | 1373111 | 1716189 | 343078 | 1373111 | 2061176 | 412235 | 1648941 | 1716189 | 343078 | 1373111 | 1716189 | 343078 | 1373111 | 0 | 0 | Page County Broadband Authority
NT10BIX5570055 | INF | 2010 | Q3 | Q3 - 2010 | 2253000 | 574166 | 1678833 | 80030 | 79590 | 440 | 114328 | 89879 | 24449 | 36819229 | 12171576 | 24647652 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 85849 | 0 | 85849 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 148088 | 67760 | 80328 | 211554 | 86799 | 124754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996657 | 800000 | 1196657 | 36961 | 34422 | 2539 | 102801 | 54174 | 48627 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 385958 | 113456 | 272502 | 551368 | 163079 | 388289 | 45985809 | 13795742 | 32190065 | 736886 | 295228 | 441658 | 1184551 | 393931 | 790619 | 45985809 | 13795742 | 32190065 | 736886 | 295228 | 441658 | 1184551 | 393931 | 790619 | 0 | 0 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2010 | Q4 | Q4 - 2010 | 2253000 | 490958 | 1762042 | 695226 | 208568 | 486658 | 150000 | 45000 | 105000 | 36736021 | 12171577 | 24564444 | 484822 | 145447 | 339375 | 1065000 | 319500 | 745500 | 100000 | 0 | 100000 | 99145 | 0 | 99145 | 855 | 0 | 855 | 890000 | 250000 | 640000 | 820315 | 246094 | 574220 | 69685 | 3906 | 65780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 544432 | 163330 | 381102 | 250000 | 75000 | 175000 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 100132 | 0 | 10132 | 199089 | 0 | 199089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 7500 | 0 | 7500 | 45902602 | 13712535 | 32190067 | 2749499 | 763439 | 1896059 | 1746629 | 443406 | 1303224 | 45902602 | 13712535 | 32190067 | 2749499 | 763439 | 1896059 | 1746629 | 443406 | 1303224 | 0 | 0 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2011 | Q1 | Q1 - 2011 | 2253000 | 490958 | 1762042 | 461458 | 138437 | 323021 | 611458 | 183437 | 428021 | 36736021 | 12171577 | 24564444 | 1202437 | 362360 | 840077 | 2267437 | 681860 | 1585577 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 948448 | 284534 | 663914 | 1018133 | 288440 | 729694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 642010 | 192603 | 449407 | 892010 | 267603 | 624407 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 155764 | 46729 | 109035 | 354853 | 46729 | 308124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 12927 | 0 | 12927 | 45902602 | 13712535 | 32190067 | 3515544 | 1024663 | 2490881 | 5261318 | 1468069 | 3793250 | 45902602 | 13712535 | 32190067 | 3515544 | 1024663 | 2490881 | 5261318 | 1468069 | 3793250 | 0 | 0 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2011 | Q2 | Q2 - 2011 | 2253000 | 490958 | 1762042 | 650533 | 195160 | 455374 | 1261991 | 378597 | 883395 | 36736021 | 12171577 | 24564444 | 3177490 | 954876 | 2222614 | 5444926 | 1635107 | 3809819 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 1374752 | 412425 | 962326 | 2392886 | 700865 | 1692020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 1003139 | 300951 | 702188 | 1895149 | 568554 | 1326595 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 168853 | 50646 | 118207 | 523706 | 97375 | 426331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 18354 | 0 | 18354 | 45902602 | 13712535 | 32190067 | 6480194 | 1914058 | 4566136 | 11641512 | 3380498 | 8261014 | 45902602 | 13712535 | 32190067 | 6480194 | 1914058 | 4566136 | 11641512 | 3380498 | 8261014 | 0 | 0 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2011 | Q3 | Q3 - 2011 | 2253000 | 490958 | 1762042 | 1090650 | 327196 | 763454 | 1814880 | 427607 | 1387273 | 36736021 | 12171577 | 24564444 | 8331618 | 2501113 | 5830505 | 13776544 | 4136220 | 9640324 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 750000 | 225000 | 525000 | 890000 | 250000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 1245939 | 373791 | 872148 | 1996658 | 800000 | 1196658 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 1081356 | 324397 | 756959 | 2055235 | 556814 | 1498421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 18354 | 0 | 18354 | 45902602 | 13712535 | 32190067 | 12604990 | 3751497 | 8853493 | 20656171 | 6170641 | 14485530 | 45902602 | 13712535 | 32190067 | 12604990 | 3751497 | 8853493 | 20656171 | 6170641 | 14485530 | 56160 | 56160 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2011 | Q4 | Q4 - 2011 | 2253000 | 673041 | 1579959 | 1090650 | 327197 | 763453 | 1555590 | 466678 | 1088912 | 36736021 | 10974192 | 25761829 | 12597411 | 3809939 | 8787472 | 22252855 | 6706572 | 15546282 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 750000 | 225000 | 525000 | 850000 | 255000 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1245939 | 373791 | 872148 | 1496179 | 448863 | 1047316 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 1094389 | 427624 | 666765 | 1906200 | 671168 | 1235033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 5427 | 1628 | 3799 | 5427 | 1628 | 3799 | 45902602 | 13712535 | 32190067 | 16883816 | 5195052 | 11688764 | 28175851 | 8582650 | 19593201 | 45902602 | 13712535 | 32190067 | 16883816 | 5195052 | 11688764 | 28175851 | 8582650 | 19593201 | 56160 | 56160 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2012 | Q1 | Q1 - 2012 | 2253000 | 673041 | 1579959 | 1136675 | 339560 | 797115 | 1364010 | 407472 | 956538 | 36736021 | 10974193 | 25761829 | 22881640 | 6856529 | 16025111 | 27457964 | 8227832 | 19230132 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 344661 | 102961 | 241700 | 413593 | 123553 | 290040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1065378 | 318261 | 747117 | 1278454 | 381914 | 896540 | 9600 | 2868 | 6732 | 2100 | 627 | 1473 | 2519 | 752 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 2978117 | 889656 | 2088461 | 3275927 | 978621 | 2297306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327616 | 97869 | 229747 | 360377 | 107656 | 252721 | 45902602 | 13712536 | 32190067 | 28836187 | 8635336 | 20200851 | 34252844 | 10257673 | 23995171 | 45902602 | 13712536 | 32190067 | 28836187 | 8635336 | 20200851 | 34252844 | 10257673 | 23995171 | 20983 | 77173 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2012 | Q2 | Q2 - 2012 | 2253000 | 673041 | 1579959 | 1221645 | 364943 | 856702 | 1608339 | 480461 | 1127878 | 36736021 | 10974193 | 25761829 | 28253261 | 8440128 | 19813133 | 33108617 | 9890574 | 23218043 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1701092 | 508169 | 1192923 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 9302 | 2779 | 6523 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3150575 | 941175 | 2209400 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327616 | 97869 | 229747 | 387500 | 115758 | 271742 | 45902602 | 13712536 | 32190067 | 35653491 | 10650807 | 25002684 | 41630537 | 12436337 | 29194200 | 45902602 | 13712536 | 32190067 | 35653491 | 10650807 | 25002684 | 41630537 | 12436337 | 29194200 | 0 | 148070 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2012 | Q3 | Q3 - 2012 | 2253000 | 673041 | 1579959 | 1292068 | 385981 | 906087 | 1737006 | 518898 | 1218108 | 36736021 | 10974193 | 25761828 | 31108412 | 9293050 | 21815362 | 35757306 | 10681820 | 25075486 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265870 | 624129 | 831014 | 248250 | 582764 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1597349 | 477178 | 1120171 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 1500 | 448 | 1052 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3203550 | 957000 | 2246550 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 302671 | 90417 | 212254 | 387500 | 115758 | 271742 | 45902602 | 13712535 | 32190066 | 38436564 | 11482197 | 26954367 | 44407893 | 13266020 | 31141873 | 45902602 | 13712535 | 32190066 | 38436564 | 11482197 | 26954367 | 44407893 | 13266020 | 31141873 | 0 | 197444 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2012 | Q4 | Q4 - 2012 | 2253000 | 673041 | 1579959 | 1747233 | 521953 | 1225280 | 1747407 | 522005 | 1225402 | 36736021 | 10974192 | 25761829 | 32781201 | 9792764 | 22988437 | 33941555 | 10178374 | 23763181 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1856538 | 554606 | 1301932 | 1895650 | 554661 | 1340989 | 9600 | 2868 | 6732 | 9302 | 2779 | 6523 | 9302 | 2779 | 6523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3296172 | 984669 | 2311503 | 3296501 | 984767 | 2311734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 303467 | 90655 | 212812 | 303497 | 90664 | 212833 | 45902602 | 13712535 | 32190067 | 40983913 | 12243170 | 28740743 | 42183912 | 12628994 | 29554918 | 45902602 | 13712535 | 32190067 | 40983913 | 12243170 | 28740743 | 42183912 | 12628994 | 29554918 | 0 | 265596 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2013 | Q1 | Q1 - 2013 | 2253000 | 673041 | 1579959 | 1842764 | 550491 | 1292273 | 1887011 | 563709 | 1323302 | 36736021 | 10974193 | 25761829 | 36064314 | 11035997 | 25028317 | 36496119 | 11146356 | 25349763 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1996658 | 596464 | 1400196 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529824 | 1054468 | 2475356 | 3529824 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327485 | 97830 | 229655 | 327956 | 97970 | 229985 | 45902602 | 13712536 | 32190067 | 44760645 | 13633862 | 31126785 | 45237168 | 13757579 | 31479587 | 45902602 | 13712536 | 32190067 | 44760645 | 13633862 | 31126785 | 45237168 | 13757579 | 31479587 | 0 | 304098 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2013 | Q2 | Q2 - 2013 | 2253000 | 673041 | 1579959 | 1965316 | 673041 | 1292275 | 2253000 | 673041 | 1579959 | 36736021 | 10974193 | 25761829 | 39746810 | 14116247 | 25630563 | 39948657 | 14186828 | 25761829 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 345413 | 115758 | 229655 | 387500 | 115758 | 271742 | 45902602 | 13712536 | 32190067 | 48583621 | 16854591 | 31729030 | 49115239 | 16925172 | 32190067 | 45902602 | 13712536 | 32190067 | 48583621 | 16854591 | 31729030 | 49115239 | 16925172 | 32190067 | 0 | 442827 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2013 | Q3 | Q3 - 2013 | 1842763 | 550490 | 1292273 | 1997314 | 705041 | 1292273 | 1997314 | 705041 | 1292273 | 37146257 | 11096743 | 26049515 | 40876810 | 15246247 | 25630563 | 41545762 | 15496247 | 26049515 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 345416 | 115759 | 229657 | 387501 | 115759 | 271742 | 45902602 | 13712536 | 32190067 | 49745622 | 18016592 | 31729030 | 50456659 | 18266592 | 32190067 | 45902602 | 13712536 | 32190067 | 49745622 | 18016592 | 31729030 | 50456659 | 18266592 | 32190067 | 0 | 567230 | Navajo Tribal Utility Authority Company
NT10BIX5570055 | INF | 2013 | Q4 | Q4 - 2013 | 1842764 | 550491 | 1292273 | 2058006 | 765733 | 1292273 | 2058006 | 765733 | 1292273 | 37014569 | 11057402 | 25957167 | 53386326 | 27429159 | 25957167 | 53386326 | 27429159 | 25957167 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996657 | 596464 | 1400193 | 1996654 | 596461 | 1400193 | 1996654 | 596461 | 1400193 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661512 | 1093808 | 2567704 | 16358199 | 13790495 | 2567704 | 16358199 | 13790495 | 2567704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 387500 | 115758 | 271742 | 387500 | 115758 | 271742 | 45902602 | 13712535 | 32190067 | 75186285 | 42996218 | 32190067 | 75186285 | 42996218 | 32190067 | 45902602 | 13712535 | 32190067 | 75186285 | 42996218 | 32190067 | 75186285 | 42996218 | 32190067 | 0 | 1335979 | Navajo Tribal Utility Authority Company
NT10BIX5570056 | INF | 2010 | Q3 | Q3 - 2010 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 64398 | 12880 | 51518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 0 | 0 | 0 | 11025 | 2205 | 8820 | 6591 | 1318 | 5273 | 0 | 0 | 0 | 1978 | 396 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 0 | 0 | 0 | 0 | 0 | 0 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 77401 | 15481 | 61920 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 77401 | 15481 | 61920 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2010 | Q4 | Q4 - 2010 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 481921 | 96384 | 385537 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 0 | 0 | 0 | 11025 | 2205 | 8820 | 6591 | 1318 | 5273 | 0 | 0 | 0 | 1978 | 396 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 0 | 0 | 0 | 0 | 0 | 0 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 709583 | 141917 | 567666 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 709583 | 141917 | 567666 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2011 | Q1 | Q1 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2011 | Q2 | Q2 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2011 | Q3 | Q3 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2011 | Q4 | Q4 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570056 | INF | 2012 | Q1 | Q1 - 2012 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2010 | Q3 | Q3 - 2010 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 198483 | 39697 | 158786 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 114485 | 22897 | 91588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 0 | 0 | 0 | 21280 | 4256 | 17024 | 7375 | 1475 | 5900 | 0 | 0 | 0 | 1475 | 295 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 0 | 0 | 0 | 4440 | 888 | 3552 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2010 | Q4 | Q4 - 2010 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 198483 | 39697 | 158786 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 114485 | 22897 | 91588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 0 | 0 | 0 | 21280 | 4256 | 17024 | 7375 | 1475 | 5900 | 0 | 0 | 0 | 1475 | 295 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 0 | 0 | 0 | 4440 | 888 | 3552 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2011 | Q1 | Q1 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2011 | Q2 | Q2 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2011 | Q3 | Q3 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22220 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700836 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700836 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2011 | Q4 | Q4 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22220 | 4460 | 17760 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700836 | 340183 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700836 | 340183 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570057 | INF | 2012 | Q1 | Q1 - 2012 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570058 | INF | 2010 | Q3 | Q3 - 2010 | 468660 | 93732 | 374928 | 0 | 0 | 0 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 45744 | 9149 | 36595 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 1000 | 200 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 0 | 0 | 0 | 527904 | 105581 | 422323 | 669135 | 133827 | 535308 | 0 | 0 | 0 | 527904 | 105581 | 422323 | 0 | 0 | City of Williamstown
NT10BIX5570058 | INF | 2010 | Q4 | Q4 - 2010 | 468660 | 93732 | 374928 | 61385 | 16734 | 44651 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 90000 | 18000 | 72000 | 5000 | 1000 | 4000 | 11708 | 7708 | 4000 | 11708 | 7708 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 5925 | 0 | 5925 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 79018 | 24442 | 54576 | 582868 | 121940 | 460928 | 669135 | 133827 | 535308 | 79018 | 24442 | 54576 | 582868 | 121940 | 460928 | 0 | 0 | City of Williamstown
NT10BIX5570058 | INF | 2011 | Q1 | Q1 - 2011 | 468660 | 93732 | 374928 | 330804 | 120720 | 210085 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 11425 | 1145 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 347229 | 122865 | 224085 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 347229 | 122865 | 224085 | 669135 | 133827 | 535308 | 0 | 0 | City of Williamstown
NT10BIX5570058 | INF | 2011 | Q2 | Q2 - 2011 | 468660 | 93732 | 374928 | 353650 | 70730 | 282920 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 138647 | 27729 | 110918 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 509797 | 101959 | 407838 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 509797 | 101959 | 407838 | 669135 | 133827 | 535308 | 0 | 0 | City of Williamstown
NT10BIX5570058 | INF | 2011 | Q3 | Q3 - 2011 | 468660 | 93732 | 374928 | 355280 | 71056 | 284224 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 138647 | 27729 | 110919 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 511427 | 102285 | 409143 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 511427 | 102285 | 409143 | 669135 | 133827 | 535308 | 0 | 7666 | City of Williamstown
NT10BIX5570058 | INF | 2011 | Q4 | Q4 - 2011 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 24960 | City of Williamstown
NT10BIX5570058 | INF | 2012 | Q1 | Q1 - 2012 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 24576 | City of Williamstown
NT10BIX5570058 | INF | 2012 | Q2 | Q2 - 2012 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 33175 | City of Williamstown
NT10BIX5570058 | INF | 2012 | Q3 | Q3 - 2012 | 384844 | 76969 | 307875 | 385446 | 77570 | 307875 | 0 | 0 | 0 | 210652 | 42130 | 168522 | 210652 | 42130 | 168521 | 0 | 0 | 0 | 10500 | 2100 | 8400 | 18174 | 9774 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18237 | 3647 | 14590 | 18437 | 3848 | 14590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624233 | 124846 | 499387 | 632709 | 133322 | 499386 | 0 | 0 | 0 | 624233 | 124846 | 499387 | 632709 | 133322 | 499386 | 0 | 0 | 0 | 0 | 37609 | City of Williamstown
NT10BIX5570059 | INF | 2010 | Q3 | Q3 - 2010 | 1183317 | 236663 | 946654 | 0 | 0 | 0 | 0 | 0 | 0 | 25505940 | 5101188 | 20404752 | 0 | 0 | 0 | 0 | 0 | 0 | 258100 | 51620 | 206480 | 2809 | 562 | 2248 | 5000 | 1000 | 4000 | 1073800 | 214760 | 859040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 126469 | 25294 | 101175 | 400000 | 80000 | 320000 | 666811 | 133362 | 533449 | 15775 | 3155 | 12620 | 30000 | 6000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 145053 | 29011 | 116043 | 435000 | 87000 | 348000 | 34072297 | 6814459 | 27257838 | 145053 | 29011 | 116043 | 435000 | 87000 | 348000 | 2316050 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2010 | Q4 | Q4 - 2010 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 500000 | 100000 | 400000 | 25505940 | 5101188 | 20404752 | 1713370 | 1710462 | 2908 | 1713370 | 1710462 | 2908 | 258100 | 51620 | 206480 | 8124 | 1625 | 6499 | 10000 | 2000 | 8000 | 1073800 | 214760 | 859040 | 184279 | 184279 | 0 | 184279 | 184279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 542521 | 108504 | 434017 | 1000000 | 200000 | 800000 | 666811 | 133362 | 533449 | 42127 | 8425 | 33702 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 2568074 | 2090948 | 477126 | 3482649 | 2211741 | 1270908 | 34072297 | 6814459 | 27257838 | 2568074 | 2090948 | 477126 | 3482649 | 2211741 | 1270908 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2011 | Q1 | Q1 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 500000 | 100000 | 400000 | 25505940 | 5101188 | 20404752 | 1739662 | 1715721 | 23941 | 2250000 | 1750000 | 500000 | 258100 | 51620 | 206480 | 15597 | 3119 | 12477 | 25000 | 5000 | 20000 | 1073800 | 214760 | 859040 | 184279 | 184279 | 0 | 184279 | 184279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 883020 | 176604 | 706416 | 1300000 | 260000 | 1040000 | 666811 | 133362 | 533449 | 91195 | 18239 | 72956 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 2991406 | 2175615 | 815790 | 4409279 | 2329279 | 2080000 | 34072297 | 6814459 | 27257838 | 2991406 | 2175615 | 815790 | 4409279 | 2329279 | 2080000 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2011 | Q2 | Q2 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 100000 | 75000 | 25000 | 25505940 | 5101188 | 20404752 | 2199321 | 1807652 | 391669 | 3200000 | 2000000 | 1200000 | 258100 | 51620 | 206480 | 22816 | 4563 | 18253 | 25000 | 5000 | 20000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 185000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 1503780 | 300756 | 1203024 | 2100000 | 420000 | 1680000 | 666811 | 133362 | 533449 | 147892 | 29578 | 118314 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 4137993 | 2404931 | 1733062 | 5815000 | 2725000 | 3090000 | 34072297 | 6814459 | 27257838 | 4137993 | 2404931 | 1733062 | 5815000 | 2725000 | 3090000 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2011 | Q3 | Q3 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 100000 | 75000 | 25000 | 25505940 | 5101188 | 20404752 | 4189958 | 2035847 | 2154111 | 7000000 | 2000000 | 5000000 | 258100 | 51620 | 206480 | 21462 | 4292 | 17170 | 30000 | 6000 | 24000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 250000 | 200000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 2094852 | 418970 | 1675882 | 2400000 | 480000 | 1920000 | 666811 | 133362 | 533449 | 190273 | 38055 | 152218 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 6760729 | 2759546 | 4001183 | 10030000 | 2811000 | 7219000 | 34072297 | 6814459 | 27257838 | 6760729 | 2759546 | 4001183 | 10030000 | 2811000 | 7219000 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2011 | Q4 | Q4 - 2011 | 1183317 | 236663 | 946654 | 78610 | 77781 | 829 | 100000 | 99000 | 1000 | 25505940 | 5101188 | 20404752 | 6380558 | 2323878 | 4056680 | 8500000 | 2700000 | 5800000 | 258100 | 51620 | 206480 | 52569 | 10514 | 42055 | 80000 | 16000 | 64000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 2838694 | 567739 | 2270955 | 3100000 | 620000 | 2480000 | 666811 | 133362 | 533449 | 256166 | 51233 | 204933 | 325000 | 55000 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15323 | 3064 | 12259 | 25000 | 5000 | 20000 | 34072297 | 6814459 | 27257838 | 9808451 | 3218938 | 6589513 | 12320000 | 3683000 | 8637000 | 34072297 | 6814459 | 27257838 | 9808451 | 3218938 | 6589513 | 12320000 | 3683000 | 8637000 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2012 | Q1 | Q1 - 2012 | 3200000 | 640000 | 2560000 | 78889 | 77817 | 1072 | 80100 | 79000 | 1100 | 21737630 | 4347526 | 17390104 | 7772820 | 2506940 | 5265880 | 11000000 | 3000000 | 8000000 | 258100 | 51620 | 206480 | 101141 | 20228 | 80913 | 150000 | 30000 | 120000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 1040000 | 4160000 | 3280052 | 656010 | 2624042 | 3600000 | 720000 | 2880000 | 666811 | 133362 | 533449 | 333414 | 66683 | 266731 | 420000 | 84000 | 336000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15323 | 3064 | 12259 | 20000 | 4000 | 16000 | 34072297 | 6814459 | 27257838 | 11768170 | 3515471 | 8252699 | 15460100 | 4105000 | 11355100 | 34072297 | 6814459 | 27257838 | 11768170 | 3515471 | 8252699 | 15460100 | 4105000 | 11355100 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2012 | Q2 | Q2 - 2012 | 3200000 | 640000 | 2560000 | 142179 | 86221 | 55958 | 2900000 | 580000 | 2320000 | 21737630 | 4347526 | 17390104 | 12263437 | 3097389 | 9166048 | 16800000 | 3600000 | 13200000 | 258100 | 51620 | 206480 | 187601 | 37520 | 150081 | 230000 | 46000 | 184000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 1040000 | 4160000 | 3540321 | 708064 | 2832257 | 3900000 | 780000 | 3120000 | 666811 | 133362 | 533449 | 393016 | 78603 | 314413 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 16728409 | 4195591 | 12532818 | 24485324 | 5287065 | 19198259 | 34072297 | 6814459 | 27257838 | 16728409 | 4195591 | 12532818 | 24485324 | 5287065 | 19198259 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2012 | Q3 | Q3 - 2012 | 3200000 | 640000 | 2560000 | 1221132 | 229478 | 991654 | 2600000 | 520000 | 2080000 | 21737630 | 4347526 | 17390104 | 14749607 | 3424283 | 11325324 | 17500000 | 3500000 | 14000000 | 258100 | 51620 | 206480 | 231901 | 46380 | 185521 | 250000 | 50000 | 200000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 5319522 | 1063904 | 4255618 | 6000000 | 1200000 | 4800000 | 666811 | 133362 | 533449 | 468734 | 93747 | 374987 | 575000 | 115000 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 22192751 | 5045586 | 17147165 | 27130324 | 5576065 | 21554259 | 34072297 | 6814459 | 27257838 | 22192751 | 5045586 | 17147165 | 27130324 | 5576065 | 21554259 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2012 | Q4 | Q4 - 2012 | 3200000 | 640000 | 2560000 | 3483948 | 529921 | 2954027 | 3500000 | 530000 | 2970000 | 21737630 | 4347526 | 17390104 | 18904020 | 3970526 | 14933494 | 20000000 | 4020000 | 15080000 | 258100 | 51620 | 206480 | 267511 | 53502 | 214009 | 270000 | 54000 | 216000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 7200978 | 1440196 | 5760782 | 7500000 | 1500000 | 6000000 | 666811 | 133362 | 533449 | 524850 | 104970 | 419880 | 620000 | 124000 | 496000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15323 | 3064 | 12259 | 34072297 | 6814459 | 27257838 | 30583162 | 6286909 | 24296253 | 32095323 | 6419064 | 24776259 | 34072297 | 6814459 | 27257838 | 30583162 | 6286909 | 24296253 | 32095323 | 6419064 | 24776259 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2013 | Q1 | Q1 - 2013 | 3200000 | 640000 | 2560000 | 3791871 | 570806 | 3221065 | 3800000 | 575000 | 3225000 | 21737630 | 4347526 | 17390104 | 19869895 | 4097524 | 15772371 | 20500000 | 4137577 | 16362423 | 258100 | 51620 | 206480 | 272840 | 54568 | 218272 | 275000 | 55000 | 220000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 7487646 | 1497529 | 5990117 | 8000000 | 1600000 | 6400000 | 666811 | 133362 | 533449 | 583512 | 116702 | 466810 | 600000 | 120000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 32207619 | 6524923 | 25682696 | 33376855 | 6675371 | 26701484 | 34072297 | 6814459 | 27257838 | 32207619 | 6524923 | 25682696 | 33376855 | 6675371 | 26701484 | 0 | 0 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2013 | Q2 | Q2 - 2013 | 3588747 | 717749 | 2870998 | 3588747 | 532461 | 3056286 | 3588747 | 532461 | 3056286 | 21153596 | 4230718 | 16922878 | 21429121 | 4323689 | 17105432 | 21429121 | 4323689 | 17105432 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 292921 | 58584 | 234337 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 666811 | 133363 | 533448 | 625941 | 125188 | 500753 | 625941 | 125188 | 500753 | 2000000 | 400000 | 1600000 | 1871735 | 374347 | 1497388 | 1871735 | 374347 | 1497388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 0 | 278 | Public Utility District of Pend Oreille County
NT10BIX5570059 | INF | 2013 | Q3 | Q3 - 2013 | 3204993 | 682669 | 2522324 | 3588747 | 532461 | 3056286 | 3588747 | 532461 | 3056286 | 21153596 | 3824940 | 17328656 | 21429121 | 4323689 | 17105432 | 21429121 | 4323689 | 17105432 | 258100 | 51620 | 206480 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 921395 | 184279 | 737116 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5867402 | 1537588 | 4329814 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 666811 | 133363 | 533448 | 625941 | 125188 | 500753 | 625941 | 125188 | 500753 | 2000000 | 400000 | 1600000 | 1871735 | 374347 | 1497388 | 1871735 | 374347 | 1497388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 0 | 19119 | Public Utility District of Pend Oreille County
NT10BIX5570060 | INF | 2010 | Q3 | Q3 - 2010 | 6040947 | 1208190 | 4832757 | 0 | 0 | 0 | 3382930 | 676586 | 2706344 | 2495000 | 499000 | 1966000 | 0 | 0 | 0 | 311875 | 62375 | 249500 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 62632 | 12526 | 50106 | 1508445 | 301689 | 1206756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 286000 | 0 | 0 | 0 | 179200 | 35840 | 143360 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 48720 | 9744 | 38976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 5438 | 1088 | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 222632 | 44526 | 178106 | 5596608 | 1119322 | 4477286 | 11840098 | 2368020 | 9472078 | 222632 | 44526 | 178106 | 5596608 | 1119322 | 4477286 | 400000 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2010 | Q4 | Q4 - 2010 | 6040947 | 1208190 | 4832757 | 0 | 0 | 0 | 3382930 | 676586 | 2706344 | 2495000 | 499000 | 1996000 | 0 | 0 | 0 | 324350 | 64870 | 259480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 181248 | 36250 | 144998 | 538730 | 107746 | 430984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 8700 | 1740 | 6960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 341248 | 68250 | 272998 | 4414710 | 882942 | 3531768 | 11840098 | 2368020 | 9472078 | 341248 | 68250 | 272998 | 4414710 | 882942 | 3531768 | 400000 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2011 | Q1 | Q1 - 2011 | 6040947 | 1208190 | 4832757 | 781819 | 156364 | 625455 | 1812284 | 362457 | 1449827 | 2495000 | 499000 | 1996000 | 88423 | 17685 | 70738 | 374250 | 74850 | 299400 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 422293 | 84459 | 337834 | 808095 | 161619 | 646476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 13050 | 2610 | 10440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 1452535 | 290508 | 1162027 | 3167679 | 633536 | 2534143 | 11840098 | 2368020 | 9472078 | 1452535 | 290508 | 1162027 | 3167679 | 633536 | 2534143 | 700000 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2011 | Q2 | Q2 - 2011 | 6040947 | 1208190 | 4832757 | 838078 | 167616 | 670462 | 1812284 | 362457 | 1449827 | 2495000 | 499000 | 1996000 | 657217 | 131443 | 525774 | 1497000 | 299400 | 1197600 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 543166 | 108633 | 434533 | 1616191 | 323238 | 1292953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 26100 | 5220 | 20880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 2198461 | 439692 | 1758769 | 5111575 | 1022315 | 4089260 | 11840098 | 2368020 | 9472078 | 2198461 | 439692 | 1758769 | 5111575 | 1022315 | 4089260 | 970000 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2011 | Q3 | Q3 - 2011 | 6040947 | 1208190 | 4832757 | 876852 | 175370 | 701482 | 2718426 | 543685 | 2174741 | 2495000 | 499000 | 1996000 | 1243149 | 248630 | 994519 | 1871250 | 374250 | 1497000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 565332 | 113067 | 452265 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 12692 | 2538 | 10154 | 96000 | 19200 | 76800 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 2858025 | 571605 | 2286420 | 6898539 | 1379708 | 5518831 | 11840098 | 2368020 | 9472078 | 2858025 | 571605 | 2286420 | 6898539 | 1379708 | 5518831 | 1200000 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2011 | Q4 | Q4 - 2011 | 6040947 | 1208190 | 4832757 | 1187791 | 237558 | 950233 | 4530710 | 906142 | 3624568 | 2495000 | 499000 | 1996000 | 1689452 | 337890 | 1351562 | 1871250 | 374250 | 1497000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1009794 | 201959 | 807835 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 96000 | 19200 | 76800 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 4077439 | 815488 | 3261951 | 8710823 | 1742165 | 6968658 | 11840098 | 2368020 | 9472078 | 4077439 | 815488 | 3261951 | 8710823 | 1742165 | 6968658 | 1516090 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2012 | Q1 | Q1 - 2012 | 6040947 | 1208190 | 4832757 | 4398879 | 879775 | 3519104 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2191640 | 438328 | 1753312 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1505748 | 301150 | 1204598 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8286669 | 1657334 | 6629335 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8286669 | 1657334 | 6629335 | 9425652 | 1885131 | 7540521 | 0 | 0 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2012 | Q2 | Q2 - 2012 | 6040947 | 1208190 | 4832757 | 4399118 | 879824 | 3519294 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2037834 | 407566 | 1630268 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1875916 | 375183 | 1500733 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8503270 | 1700654 | 6802616 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8503270 | 1700654 | 6802616 | 9425652 | 1885131 | 7540521 | 0 | 5899 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2012 | Q3 | Q3 - 2012 | 6040947 | 1208190 | 4832757 | 4402878 | 880576 | 3522302 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2048761 | 409752 | 1639009 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1972449 | 394490 | 1577959 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8614490 | 1722899 | 6891591 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8614490 | 1722899 | 6891591 | 9425652 | 1885131 | 7540521 | 0 | 25807 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2012 | Q4 | Q4 - 2012 | 6040947 | 1208190 | 4832757 | 4464272 | 892854 | 3571418 | 4832758 | 966552 | 3866206 | 2495000 | 499000 | 1996000 | 2071384 | 414277 | 1657107 | 2370250 | 474050 | 1896200 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2089183 | 417837 | 1671346 | 2558968 | 511794 | 2047174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 48689 | 9738 | 38951 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8833528 | 1766706 | 7066822 | 10259851 | 2051971 | 8207880 | 11840098 | 2368020 | 9472078 | 8833528 | 1766706 | 7066822 | 10259851 | 2051971 | 8207880 | 0 | 54490 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2013 | Q1 | Q1 - 2013 | 6040947 | 1208190 | 4832757 | 5050441 | 1010088 | 4040353 | 6040947 | 1208189 | 4832758 | 2495000 | 499000 | 1996000 | 2430703 | 486141 | 1944562 | 2495000 | 499000 | 1996000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2476450 | 495290 | 1981160 | 2693651 | 538730 | 2154921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 50099 | 10020 | 40079 | 320000 | 64000 | 256000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 10167693 | 2033539 | 8134154 | 11840098 | 2368019 | 9472079 | 11840098 | 2368020 | 9472078 | 10167693 | 2033539 | 8134154 | 11840098 | 2368019 | 9472079 | 0 | 98133 | Pine Telephone Company, Inc.
NT10BIX5570060 | INF | 2013 | Q2 | Q2 - 2013 | 6040947 | 1208190 | 4832757 | 6483335 | 1299686 | 5183649 | 6483335 | 1299686 | 5183649 | 2495000 | 499000 | 1996000 | 2691879 | 538376 | 2153503 | 2691879 | 538376 | 2153503 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2442767 | 488553 | 1954214 | 2442767 | 488553 | 1954214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 65890 | 13178 | 52712 | 65890 | 13178 | 52712 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 11843871 | 2371793 | 9472078 | 11843871 | 2371793 | 9472078 | 11840098 | 2368020 | 9472078 | 11843871 | 2371793 | 9472078 | 11843871 | 2371793 | 9472078 | 0 | 146591 | Pine Telephone Company, Inc.
NT10BIX5570062 | INF | 2010 | Q3 | Q3 - 2010 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 374300 | 74860 | 299440 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 71553 | 14311 | 57242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 0 | 0 | 0 | 15610 | 3122 | 12488 | 6556 | 1311 | 5245 | 0 | 0 | 0 | 1331 | 267 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 11100 | 2775 | 0 | 0 | 0 | 11100 | 2220 | 8880 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2010 | Q4 | Q4 - 2010 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 374300 | 74860 | 299440 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 71553 | 14311 | 57242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 0 | 0 | 0 | 15610 | 3122 | 12488 | 6556 | 1311 | 5245 | 0 | 0 | 0 | 1331 | 267 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 11100 | 2775 | 0 | 0 | 0 | 11100 | 2220 | 8880 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2011 | Q1 | Q1 - 2011 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2011 | Q2 | Q2 - 2011 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2011 | Q3 | Q3 - 2011 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2011 | Q4 | Q4 - 2011 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570062 | INF | 2012 | Q1 | Q1 - 2012 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp.
NT10BIX5570065 | INF | 2010 | Q3 | Q3 - 2010 | 17041210 | 3252984 | 13788226 | 0 | 0 | 0 | 0 | 0 | 0 | 1321850 | 214017 | 1107833 | 0 | 0 | 0 | 0 | 0 | 0 | 277131 | 62428 | 214703 | 0 | 0 | 0 | 15000 | 0 | 15000 | 1256150 | 203380 | 1052770 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 9714 | 50286 | 0 | 0 | 0 | 0 | 146581 | 146581 | 1807524 | 292651 | 1514873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577150 | 93445 | 483705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617682 | 846430 | 771252 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 65000 | 156581 | 201581 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 65000 | 156581 | 201581 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2010 | Q4 | Q4 - 2010 | 17041210 | 3252984 | 13788226 | 0 | 0 | 0 | 0 | 0 | 0 | 1321850 | 214017 | 1107833 | 0 | 0 | 0 | 0 | 0 | 0 | 277131 | 62428 | 214703 | 0 | 0 | 0 | 20000 | 16000 | 4000 | 1256150 | 203380 | 1052770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 9714 | 50286 | 0 | 0 | 0 | 60000 | 48000 | 12000 | 1807524 | 292651 | 1514873 | 0 | 0 | 0 | 390000 | 312000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577150 | 93445 | 483705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617682 | 846430 | 771252 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 470000 | 376000 | 94000 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 470000 | 376000 | 94000 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2011 | Q1 | Q1 - 2011 | 22003511 | 3864959 | 18138552 | 0 | 0 | 0 | 8483849 | 1562079 | 6921770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 0 | 0 | 0 | 168318 | 0 | 168318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 0 | 0 | 0 | 368292 | 21875 | 346417 | 361435 | 361435 | 0 | 0 | 0 | 0 | 361435 | 361435 | 0 | 142800 | 0 | 142800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 9381894 | 1945389 | 7436505 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 9381894 | 1945389 | 7436505 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2011 | Q2 | Q2 - 2011 | 22003511 | 4143394 | 17860117 | 396270 | 396270 | 0 | 2513176 | 703247 | 1809929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 38385 | 16813 | 21572 | 38760 | 16813 | 21947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 203254 | 3196 | 200058 | 235479 | 3196 | 232283 | 361435 | 61324 | 300111 | 145946 | 118251 | 27695 | 145946 | 27695 | 118251 | 142800 | 24229 | 118571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 528688 | 528688 | 0 | 528688 | 528688 | 0 | 23958697 | 4975049 | 18983648 | 1312543 | 1063218 | 249325 | 3462049 | 1279639 | 2182410 | 23958697 | 4975049 | 18983648 | 1312543 | 1063218 | 249325 | 3462049 | 1279639 | 2182410 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2011 | Q3 | Q3 - 2011 | 22003511 | 4143394 | 17860117 | 5604462 | 1232834 | 4371629 | 9121153 | 1812131 | 7309022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 38385 | 16813 | 21572 | 47006 | 16813 | 30193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 258101 | 3196 | 254904 | 280234 | 25330 | 254904 | 361435 | 61324 | 300111 | 145946 | 118251 | 27695 | 145946 | 27695 | 118251 | 142800 | 24229 | 118571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 542188 | 528688 | 13500 | 546688 | 529876 | 16812 | 23958697 | 4975049 | 18983648 | 6589082 | 1899782 | 4689300 | 10141027 | 2411845 | 7729182 | 23958697 | 4975049 | 18983648 | 6589082 | 1899782 | 4689300 | 10141027 | 2411845 | 7729182 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2011 | Q4 | Q4 - 2011 | 22003511 | 4143394 | 17860117 | 11649266 | 2267615 | 9381651 | 14828809 | 2928506 | 11900303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 56175 | 16814 | 39361 | 56175 | 16814 | 39361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 340208 | 21704 | 318504 | 383917 | 21705 | 362212 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 16830 | 0 | 16830 | 27625 | 0 | 27625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 631836 | 529876 | 101960 | 635934 | 529876 | 106058 | 23958697 | 4975049 | 18983648 | 12845046 | 2957885 | 9887161 | 16083191 | 3618777 | 12464414 | 23958697 | 4975049 | 18983648 | 12845046 | 2957885 | 9887161 | 16083191 | 3618777 | 12464414 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2012 | Q1 | Q1 - 2012 | 22003511 | 4143394 | 17860117 | 16174664 | 2988724 | 13185940 | 17239334 | 3193728 | 14045606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 63608 | 16814 | 46794 | 213608 | 16814 | 196794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 436776 | 82909 | 353867 | 496695 | 82909 | 413786 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 43095 | 17085 | 26010 | 63495 | 37485 | 26010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 687707 | 529876 | 157831 | 721213 | 529876 | 191337 | 23958697 | 4975049 | 18983648 | 17556581 | 3757284 | 13799297 | 18885076 | 3982688 | 14902388 | 23958697 | 4975049 | 18983648 | 17556581 | 3757284 | 13799297 | 18885076 | 3982688 | 14902388 | 0 | 0 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2012 | Q2 | Q2 - 2012 | 22003511 | 4143394 | 17860117 | 17239334 | 3193728 | 14045606 | 17339334 | 3218728 | 14120606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 223908 | 16814 | 207094 | 238908 | 31814 | 207094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 502761 | 82909 | 419852 | 577761 | 97909 | 479852 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 67665 | 37485 | 30180 | 67665 | 37485 | 30180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 755294 | 529876 | 225418 | 830294 | 529876 | 300418 | 23958697 | 4975049 | 18983648 | 18939693 | 3982688 | 14957005 | 19204693 | 4037688 | 15167005 | 23958697 | 4975049 | 18983648 | 18939693 | 3982688 | 14957005 | 19204693 | 4037688 | 15167005 | 0 | 2337 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2012 | Q3 | Q3 - 2012 | 22003511 | 4143394 | 17860117 | 17265321 | 3217963 | 14047358 | 17265321 | 3217963 | 14047358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 223908 | 16814 | 207094 | 223908 | 16814 | 207094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 575116 | 94070 | 481046 | 660116 | 111070 | 549046 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 79807 | 37485 | 42322 | 79807 | 37485 | 42322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 798809 | 529876 | 268933 | 848809 | 539876 | 308933 | 23958697 | 4975049 | 18983648 | 19093692 | 4018084 | 15075608 | 19228692 | 4045084 | 15183608 | 23958697 | 4975049 | 18983648 | 19093692 | 4018084 | 15075608 | 19228692 | 4045084 | 15183608 | 0 | 5804 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2012 | Q4 | Q4 - 2012 | 22003511 | 4143394 | 17860117 | 17305121 | 3217963 | 14087158 | 17305121 | 3217963 | 14087158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 232830 | 16814 | 216016 | 232830 | 16814 | 216016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 608569 | 94070 | 514499 | 608569 | 94070 | 608569 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 79807 | 37485 | 42322 | 79807 | 37485 | 42322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 801959 | 529876 | 272083 | 801959 | 529876 | 272083 | 23958697 | 4975049 | 18983648 | 19179017 | 4018084 | 15160933 | 19179017 | 4018084 | 15255003 | 23958697 | 4975049 | 18983648 | 19179017 | 4018084 | 15160933 | 19179017 | 4018084 | 15255003 | 0 | 5804 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2013 | Q1 | Q1 - 2013 | 21482710 | 4607804 | 16874906 | 17810410 | 3761129 | 14049281 | 17810410 | 3761129 | 14049281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286813 | 16813 | 270000 | 232829 | 16813 | 216016 | 253452 | 16813 | 236639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108868 | 177082 | 931786 | 611283 | 92657 | 518626 | 691748 | 173122 | 518626 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 48873 | 93927 | 75680 | 37485 | 38195 | 75680 | 37485 | 38195 | 383825 | 1188 | 382637 | 296670 | 1188 | 295483 | 383825 | 1188 | 382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401537 | 0 | 401537 | 0 | 0 | 0 | 198217 | 0 | 198217 | 23958697 | 4975049 | 18983648 | 19179016 | 4032561 | 15146456 | 19565476 | 4113026 | 15452450 | 23958697 | 4975049 | 18983648 | 19179016 | 4032561 | 15146456 | 19565476 | 4113026 | 15452450 | 0 | 5804 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2013 | Q2 | Q2 - 2013 | 21482710 | 4607804 | 16874906 | 17810410 | 3761128 | 14049282 | 17810410 | 3761128 | 14049282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286813 | 16813 | 270000 | 280901 | 16813 | 264088 | 293812 | 16813 | 276999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108868 | 177082 | 931786 | 825385 | 225997 | 599388 | 864218 | 246110 | 618108 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 48873 | 93927 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 383825 | 1188 | 382637 | 383825 | 1188 | 382637 | 383825 | 1188 | 382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401537 | 0 | 401537 | 267387 | 0 | 267387 | 343632 | 0 | 343632 | 23958697 | 4975049 | 18983648 | 19796747 | 4166915 | 15629832 | 19924736 | 4187028 | 15737708 | 23958697 | 4975049 | 18983648 | 19796747 | 4166915 | 15629832 | 19924736 | 4187028 | 15737708 | 0 | 5804 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2013 | Q3 | Q3 - 2013 | 22003511 | 3864959 | 18138552 | 18194234 | 3762316 | 14431918 | 18534235 | 3832316 | 14701919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 417590 | 32220 | 385370 | 427590 | 16813 | 410777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 881846 | 261360 | 620486 | 890836 | 270350 | 620486 | 361435 | 361435 | 0 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 0 | 142800 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 340181 | 0 | 340181 | 421181 | 0 | 421181 | 23958697 | 4975049 | 18983648 | 20062690 | 4217685 | 15845005 | 20502681 | 4281268 | 16221413 | 23958697 | 4975049 | 18983648 | 20062690 | 4217685 | 15845005 | 20502681 | 4281268 | 16221413 | 0 | 5804 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2013 | Q4 | Q4 - 2013 | 22003511 | 3864959 | 18138552 | 18365548 | 3762566 | 14602982 | 18632106 | 3845919 | 14786187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 380796 | 16813 | 363983 | 412796 | 16813 | 395983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 917338 | 281617 | 635721 | 939337 | 281181 | 658156 | 361435 | 361435 | 0 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 0 | 142800 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 445095 | 11575 | 433520 | 514214 | 31446 | 482768 | 23958697 | 4975049 | 18983648 | 20337616 | 4234360 | 16103256 | 20727292 | 4337148 | 16390144 | 23958697 | 4975049 | 18983648 | 20337616 | 4234360 | 16103256 | 20727292 | 4337148 | 16390144 | 0 | 28277 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2014 | Q1 | Q1 - 2014 | 19824590 | 3737155 | 16087435 | 18182269 | 3346364 | 14835905 | 18262269 | 3386364 | 14875905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 419939 | 22914 | 397025 | 422940 | 22915 | 400025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 956957 | 304566 | 652391 | 966957 | 304566 | 662391 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 106695 | 43810 | 62885 | 83295 | 40500 | 42795 | 83295 | 40500 | 42795 | 393825 | 2958 | 390867 | 387320 | 4683 | 382637 | 387320 | 4683 | 382637 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1374092 | 581859 | 792233 | 1397776 | 581859 | 815917 | 23958697 | 4975049 | 18983648 | 21623887 | 4433778 | 17190109 | 21740572 | 4473779 | 17266793 | 23958697 | 4975049 | 18983648 | 21623887 | 4433778 | 17190109 | 21740572 | 4473779 | 17266793 | 0 | 28277 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2014 | Q2 | Q2 - 2014 | 19824590 | 3737155 | 16087435 | 18483487 | 3428063 | 15055424 | 19710489 | 3623054 | 16087435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 449145 | 25241 | 423904 | 577694 | 49418 | 528276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 965094 | 306903 | 658191 | 1088131 | 315187 | 772944 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 106695 | 43810 | 62885 | 89295 | 42000 | 47295 | 106695 | 43810 | 62885 | 393825 | 2958 | 390867 | 387320 | 4683 | 382637 | 394080 | 4683 | 389397 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1418081 | 588109 | 829972 | 1707402 | 651814 | 1055588 | 23958697 | 4975049 | 18983648 | 22012437 | 4527891 | 17484546 | 23804506 | 4820858 | 18983648 | 23958697 | 4975049 | 18983648 | 22012437 | 4527891 | 17484546 | 23804506 | 4820858 | 18983648 | 0 | 42815 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2014 | Q3 | Q3 - 2014 | 19824590 | 3737155 | 16087435 | 19300670 | 3599304 | 15701366 | 19348939 | 3624476 | 15724463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 449257 | 24191 | 425066 | 449257 | 24191 | 425066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 989500 | 311358 | 678142 | 989500 | 311358 | 678142 | 152144 | 123289 | 28855 | 172226 | 126768 | 45458 | 172226 | 126769 | 45457 | 106695 | 43810 | 62885 | 89295 | 40500 | 48795 | 89295 | 40500 | 48795 | 393825 | 2958 | 390867 | 387819 | 4683 | 383136 | 387819 | 4683 | 383136 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1542947 | 615388 | 927559 | 1611559 | 615388 | 996171 | 23958697 | 4975049 | 18983648 | 22999585 | 4731795 | 18267790 | 23116466 | 4756968 | 18359498 | 23958697 | 4975049 | 18983648 | 22999585 | 4731795 | 18267790 | 23116466 | 4756968 | 18359498 | 0 | 49189 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2014 | Q4 | Q4 - 2014 | 19824590 | 3737155 | 16087435 | 19357885 | 3590698 | 15767187 | 19382019 | 3600698 | 15781321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 461103 | 24191 | 436912 | 461103 | 24191 | 436912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 994850 | 314025 | 680825 | 994850 | 314025 | 680825 | 152144 | 123289 | 28855 | 172226 | 126769 | 45457 | 172226 | 126769 | 45457 | 106695 | 43810 | 62885 | 92545 | 41250 | 51295 | 92545 | 41250 | 51295 | 393825 | 2958 | 390867 | 387819 | 4683 | 383136 | 387819 | 4683 | 383136 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1628256 | 635357 | 992899 | 1655563 | 635357 | 1020206 | 23958697 | 4975049 | 18983648 | 23162555 | 4746576 | 18415979 | 23213996 | 4756576 | 18457420 | 23958697 | 4975049 | 18983648 | 23162555 | 4746576 | 18415979 | 23213996 | 4756576 | 18457420 | 0 | 91410 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2015 | Q1 | Q1 - 2015 | 19824590 | 3737155 | 16087435 | 19537435 | 3612479 | 15924956 | 19741794 | 3625642 | 16116152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 468546 | 24191 | 444355 | 494946 | 24191 | 470755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 994850 | 314025 | 680825 | 996916 | 316091 | 680825 | 152144 | 123289 | 28855 | 172226 | 126769 | 45457 | 172226 | 126769 | 45457 | 106695 | 43810 | 62885 | 95745 | 41250 | 54495 | 95745 | 41250 | 54495 | 393825 | 2958 | 390867 | 387820 | 4683 | 383137 | 387820 | 4683 | 383137 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1695079 | 651371 | 1043708 | 1826258 | 663636 | 1162622 | 23958697 | 4975049 | 18983648 | 23419572 | 4784371 | 18635201 | 23783576 | 4811865 | 18971711 | 23958697 | 4975049 | 18983648 | 23419572 | 4784371 | 18635201 | 23783576 | 4811865 | 18971711 | 0 | 139031 | Buggs Island Telephone Cooperative
NT10BIX5570065 | INF | 2015 | Q2 | Q2 - 2015 | 19824590 | 3737155 | 16087435 | 19711638 | 3634564 | 16077074 | 19745377 | 3637203 | 16108174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577693 | 49417 | 528276 | 471858 | 24191 | 447666 | 494857 | 24191 | 470666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088131 | 315040 | 773091 | 997499 | 316675 | 680825 | 997499 | 316675 | 680824 | 152144 | 123289 | 28855 | 172226 | 126769 | 45457 | 172226 | 126769 | 45457 | 106695 | 43810 | 62885 | 95745 | 41250 | 54495 | 96495 | 42000 | 54495 | 393825 | 2958 | 390867 | 387820 | 4683 | 383137 | 387820 | 4683 | 383137 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 67871 | 9603 | 58268 | 1747748 | 693777 | 1053971 | 1764571 | 657433 | 1107138 | 1768697 | 657433 | 1111264 | 23958697 | 4975049 | 18983648 | 23669228 | 4815168 | 18854060 | 23730842 | 4818557 | 18912285 | 23958697 | 4975049 | 18983648 | 23669228 | 4815168 | 18854060 | 23730842 | 4818557 | 18912285 | 0 | 258178 | Buggs Island Telephone Cooperative
NT10BIX5570066 | INF | 2010 | Q4 | Q4 - 2010 | 1688279 | 850452 | 837827 | 0 | 0 | 0 | 253242 | 127568 | 125674 | 31203526 | 11304543 | 19898983 | 94211 | 20020 | 75369 | 1248141 | 452182 | 795959 | 60000 | 0 | 60000 | 55454 | 0 | 55454 | 60000 | 0 | 60000 | 1242231 | 962231 | 280000 | 0 | 0 | 0 | 186335 | 144335 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 39333 | 8358 | 31467 | 319274 | 63855 | 255419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 6383 | 1276 | 5107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522526 | 22698010 | 188998 | 28378 | 162290 | 2073375 | 789216 | 1284159 | 36220536 | 13522526 | 22698010 | 188998 | 28378 | 162290 | 2073375 | 789216 | 1284159 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2011 | Q1 | Q1 - 2011 | 1942231 | 1102231 | 840000 | 892231 | 892231 | 0 | 932271 | 900239 | 32032 | 31203526 | 11306715 | 19896810 | 6592361 | 6384483 | 207801 | 9985128 | 7063036 | 2922092 | 60000 | 0 | 60000 | 59009 | 0 | 59009 | 60000 | 0 | 60000 | 988279 | 708279 | 280000 | 638279 | 638279 | 0 | 638279 | 638279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 210462 | 42092 | 168370 | 416444 | 83289 | 333156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 12767 | 10214 | 2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698010 | 8392342 | 7957085 | 435180 | 12044889 | 8695057 | 3349833 | 36220536 | 13522525 | 22698010 | 8392342 | 7957085 | 435180 | 12044889 | 8695057 | 3349833 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2011 | Q2 | Q2 - 2011 | 1942231 | 1102231 | 840000 | 892231 | 892231 | 0 | 918595 | 897504 | 21091 | 31203526 | 11306715 | 19896810 | 10311226 | 7128271 | 3182955 | 14030091 | 7872029 | 6158062 | 60000 | 0 | 0 | 59209 | 0 | 59209 | 60906 | 339 | 60567 | 988279 | 708279 | 280000 | 638279 | 638279 | 0 | 638279 | 638279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 434824 | 86965 | 347859 | 659184 | 131837 | 527347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 12767 | 2553 | 10214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22638010 | 12335769 | 8745746 | 3590023 | 16319822 | 9542541 | 6777281 | 36220536 | 13522525 | 22638010 | 12335769 | 8745746 | 3590023 | 16319822 | 9542541 | 6777281 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2011 | Q3 | Q3 - 2011 | 2278724 | 1538724 | 740000 | 1353724 | 1353724 | 0 | 1367261 | 1356431 | 10830 | 39731915 | 19704727 | 20027188 | 22292746 | 16216893 | 6075853 | 25908851 | 16940114 | 8968737 | 65000 | 1000 | 64000 | 59217 | 0 | 59217 | 65000 | 1000 | 64000 | 991431 | 751431 | 240000 | 691431 | 691431 | 0 | 698345 | 692814 | 5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 624066 | 124813 | 499253 | 813309 | 162662 | 650647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45100598 | 22402587 | 22698011 | 25021184 | 18386861 | 6634323 | 28852766 | 19153021 | 9699745 | 45100598 | 22402587 | 22698011 | 25021184 | 18386861 | 6634323 | 28852766 | 19153021 | 9699745 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2011 | Q4 | Q4 - 2011 | 1817231 | 1077231 | 740000 | 275948 | 275948 | 0 | 532828 | 409495 | 123333 | 31366498 | 11339310 | 20027188 | 13520898 | 4270987 | 9249911 | 16495165 | 5449041 | 11046124 | 65000 | 1000 | 64000 | 61834 | 951 | 60883 | 62362 | 959 | 61403 | 938279 | 698279 | 240000 | 324222 | 222769 | 101453 | 426565 | 302021 | 124544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 884472 | 176894 | 707578 | 969589 | 193917 | 775672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 15067374 | 4947549 | 10119825 | 18486509 | 6355433 | 12131076 | 36220536 | 13522525 | 22698011 | 15067374 | 4947549 | 10119825 | 18486509 | 6355433 | 12131076 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2012 | Q1 | Q1 - 2012 | 1817231 | 1077231 | 740000 | 922807 | 615720 | 307086 | 1101692 | 708022 | 393669 | 31366498 | 11339310 | 20027188 | 17283111 | 6516727 | 10766384 | 20099789 | 7481244 | 12618545 | 65000 | 1000 | 64000 | 65303 | 1005 | 64299 | 65303 | 1005 | 64299 | 938279 | 698279 | 240000 | 514751 | 411390 | 103361 | 599457 | 468768 | 130689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1060530 | 212106 | 848424 | 1127459 | 225492 | 901967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 17416 | 3483 | 13933 | 141603 | 28321 | 113283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 19863918 | 7760431 | 12103487 | 23135303 | 8912852 | 14222452 | 36220536 | 13522525 | 22698011 | 19863918 | 7760431 | 12103487 | 23135303 | 8912852 | 14222452 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2012 | Q2 | Q2 - 2012 | 1817231 | 1077231 | 740000 | 1049163 | 742077 | 307086 | 1241181 | 825866 | 415315 | 31366498 | 11339310 | 20027188 | 22165403 | 8210948 | 13954455 | 24465677 | 8993039 | 15472638 | 65000 | 1000 | 64000 | 73685 | 1134 | 72551 | 76755 | 1181 | 75574 | 938279 | 698279 | 240000 | 710313 | 522816 | 187497 | 767305 | 566682 | 200623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1387105 | 277421 | 1109684 | 1389123 | 277825 | 1111298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 76771 | 15354 | 61417 | 217166 | 43433 | 173733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 25462440 | 9769750 | 15692690 | 28157207 | 10708026 | 17449181 | 36220536 | 13522525 | 22698011 | 25462440 | 9769750 | 15692690 | 28157207 | 10708026 | 17449181 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2012 | Q3 | Q3 - 2012 | 1817231 | 1077231 | 740000 | 1116210 | 809123 | 307087 | 1349883 | 898492 | 451391 | 31366498 | 11339310 | 20027188 | 24394899 | 9037208 | 15357691 | 26718764 | 9804575 | 16914189 | 65000 | 1000 | 64000 | 78589 | 3718 | 74871 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 778493 | 574823 | 203670 | 831755 | 615975 | 215780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1847788 | 369558 | 1478230 | 1916224 | 383245 | 1532979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 133627 | 26725 | 106902 | 301868 | 60373 | 241495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 28349606 | 10821155 | 17528451 | 31199994 | 11766516 | 19433478 | 36220536 | 13522525 | 22698011 | 28349606 | 10821155 | 17528451 | 31199994 | 11766516 | 19433478 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2012 | Q4 | Q4 - 2012 | 1817231 | 1077231 | 740000 | 1116209 | 809123 | 307086 | 1466720 | 943177 | 523543 | 31366498 | 11339310 | 20027188 | 25819151 | 9322058 | 16497093 | 28592825 | 10330684 | 18262141 | 65000 | 1000 | 64000 | 78589 | 3718 | 74871 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 1112691 | 641662 | 471029 | 1156701 | 669971 | 486730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2113066 | 422614 | 1690452 | 2183501 | 436701 | 1746800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 198140 | 39628 | 158512 | 418246 | 83649 | 334597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 30437846 | 11238803 | 19199043 | 33899493 | 12468038 | 21431455 | 36220536 | 13522525 | 22698011 | 30437846 | 11238803 | 19199043 | 33899493 | 12468038 | 21431455 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2013 | Q1 | Q1 - 2013 | 1817231 | 1077231 | 740000 | 1182525 | 875439 | 307086 | 1420659 | 1077231 | 343428 | 31366498 | 11339310 | 20027188 | 27109951 | 9969906 | 17140045 | 30509668 | 11339310 | 19170358 | 65000 | 1000 | 64000 | 79211 | 3718 | 75493 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 1476980 | 752473 | 724507 | 1501782 | 775275 | 726507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2255803 | 451161 | 1804642 | 2274475 | 464833 | 1809642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 256574 | 51315 | 205259 | 357220 | 127670 | 229550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 32361044 | 12104012 | 20257032 | 36145304 | 13788175 | 22357129 | 36220536 | 13522525 | 22698011 | 32361044 | 12104012 | 20257032 | 36145304 | 13788175 | 22357129 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2013 | Q2 | Q2 - 2013 | 1817231 | 1077231 | 740000 | 1276089 | 969003 | 307086 | 1355528 | 999135 | 356393 | 31366498 | 11339310 | 20027188 | 28649198 | 10795850 | 17853348 | 30300805 | 11113031 | 19187774 | 65000 | 1000 | 64000 | 79211 | 3718 | 75493 | 83503 | 3746 | 79757 | 938279 | 698279 | 240000 | 1578334 | 826290 | 752044 | 1613857 | 845822 | 768035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2328519 | 465704 | 1862815 | 2410693 | 473509 | 1937184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 318550 | 63710 | 254840 | 356148 | 67281 | 288867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 34229901 | 13124275 | 21105626 | 36120534 | 13502524 | 22618010 | 36220536 | 13522525 | 22698011 | 34229901 | 13124275 | 21105626 | 36120534 | 13502524 | 22618010 | 0 | 0 | BVU Authority
NT10BIX5570066 | INF | 2013 | Q3 | Q3 - 2013 | 1817231 | 1077231 | 740000 | 1276089 | 969003 | 307086 | 1276089 | 969003 | 307086 | 31366498 | 11339310 | 20027188 | 30057793 | 11077568 | 18980225 | 30057793 | 11077568 | 18980225 | 65000 | 1000 | 64000 | 80833 | 4167 | 76666 | 80833 | 4167 | 76666 | 938279 | 698279 | 240000 | 2055998 | 921823 | 1134175 | 2055998 | 921823 | 1134175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2365092 | 473019 | 1892073 | 2365092 | 473019 | 1892073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 384731 | 76946 | 307785 | 384731 | 76946 | 307785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 36220536 | 13522526 | 22698010 | 36220536 | 13522526 | 22698010 | 36220536 | 13522525 | 22698011 | 36220536 | 13522526 | 22698010 | 36220536 | 13522526 | 22698010 | 0 | 0 | BVU Authority
NT10BIX5570067 | INF | 2010 | Q4 | Q4 - 2010 | 28631231 | 8404716 | 20226515 | 5513168 | 3867462 | 1645706 | 9069213 | 3867462 | 5201751 | 35225331 | 15494088 | 19731243 | 0 | 0 | 0 | 501437 | 357282 | 144155 | 268147 | 24379 | 243768 | 72391 | 12088 | 60303 | 87867 | 12088 | 75779 | 4261800 | 0 | 4261800 | 5000 | 0 | 5000 | 2717180 | 0 | 2717180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1222148 | 65824 | 1156324 | 1330420 | 96032 | 1234388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 0 | 0 | 0 | 144156 | 0 | 144156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 525 | 0 | 525 | 525 | 0 | 525 | 69982479 | 25188433 | 44794046 | 6813232 | 3945374 | 2867858 | 13850798 | 4332864 | 9517934 | 69982479 | 25188433 | 44794046 | 6813232 | 3945374 | 2867858 | 13850798 | 4332864 | 9517934 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2011 | Q1 | Q1 - 2011 | 28631231 | 8404716 | 20226515 | 8459386 | 3268414 | 5190972 | 19560982 | 3616862 | 15944120 | 35225331 | 15494088 | 19731243 | 18911 | 0 | 18913 | 3947957 | 394917 | 3553040 | 268147 | 24379 | 243768 | 175848 | 12088 | 163760 | 181488 | 12088 | 169400 | 4261800 | 0 | 4261800 | 164760 | 0 | 164760 | 5593582 | 0 | 5593582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1245402 | 65824 | 1179578 | 1295058 | 65824 | 1229235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39189 | 0 | 39189 | 39189 | 0 | 39189 | 69982479 | 25188433 | 44794046 | 10123496 | 3366326 | 6757172 | 30638256 | 4109691 | 26528566 | 69982479 | 25188433 | 44794046 | 10123496 | 3366326 | 6757172 | 30638256 | 4109691 | 26528566 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2011 | Q2 | Q2 - 2011 | 28631231 | 8404716 | 20226515 | 14630545 | 3262348 | 11368197 | 19356109 | 3420796 | 15935313 | 35225331 | 15494088 | 19731243 | 690944 | 291174 | 399770 | 9939070 | 1085345 | 8853725 | 268147 | 24379 | 243768 | 188160 | 12088 | 176072 | 192160 | 1208 | 180072 | 4261800 | 0 | 4261800 | 644877 | 0 | 644877 | 8188523 | 0 | 8188523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1314350 | 77913 | 1236437 | 1420088 | 77913 | 1342175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39189 | 0 | 39189 | 66708 | 0 | 66708 | 69982479 | 25188433 | 44794046 | 17528065 | 3663523 | 13864542 | 39182658 | 4605262 | 34566516 | 69982479 | 25188433 | 44794046 | 17528065 | 3663523 | 13864542 | 39182658 | 4605262 | 34566516 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2011 | Q3 | Q3 - 2011 | 28631231 | 8404716 | 20226515 | 19110085 | 3232968 | 15877117 | 23622231 | 3391416 | 20230815 | 35225331 | 15494088 | 19731243 | 1543025 | 289409 | 1253616 | 4572838 | 1236356 | 3336482 | 268147 | 24379 | 243768 | 73026 | 12089 | 60937 | 127026 | 12089 | 114937 | 4261800 | 0 | 4261800 | 2008381 | 0 | 2008381 | 10354219 | 0 | 10354219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1685896 | 65824 | 1620072 | 2000810 | 255824 | 1744986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 10079 | 0 | 10079 | 122579 | 100000 | 22579 | 69982479 | 25188433 | 44794046 | 24450492 | 3620290 | 20830202 | 40819703 | 5015685 | 35804018 | 69982479 | 25188433 | 44794046 | 24450492 | 3620290 | 20830202 | 40819703 | 5015685 | 35804018 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2011 | Q4 | Q4 - 2011 | 28631231 | 8404716 | 20226515 | 22432494 | 3196850 | 19235644 | 24888873 | 3683792 | 21205081 | 35225331 | 15494088 | 19731243 | 2944523 | 721530 | 2222993 | 5234752 | 1528489 | 3706263 | 268147 | 24379 | 243768 | 83962 | 12088 | 71874 | 97299 | 12088 | 85211 | 4261800 | 0 | 4261800 | 2509819 | 24419 | 2485400 | 5904699 | 24419 | 5880280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1773114 | 82516 | 1690598 | 1805088 | 82516 | 1722572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 23955 | 23955 | 0 | 23955 | 23955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 17464 | 2974 | 14490 | 21964 | 2974 | 18990 | 69982479 | 25188433 | 44794046 | 29785331 | 4064332 | 25720999 | 37976630 | 5358233 | 32618397 | 69982479 | 25188433 | 44794046 | 29785331 | 4064332 | 25720999 | 37976630 | 5358233 | 32618397 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2012 | Q1 | Q1 - 2012 | 28631231 | 8404716 | 20226515 | 22607986 | 3196850 | 19411136 | 24531172 | 4214158 | 20317014 | 35225331 | 15494088 | 19731243 | 4932410 | 760931 | 4171479 | 8896161 | 1447476 | 7448685 | 268147 | 24379 | 243768 | 84081 | 12088 | 71993 | 84081 | 12088 | 71993 | 4261800 | 0 | 4261800 | 3775913 | 24419 | 3751494 | 5485263 | 24419 | 5460844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1536709 | 82516 | 1454192 | 1611874 | 82516 | 1529358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 23955 | 23955 | 0 | 123955 | 123955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 37697 | 2974 | 34723 | 40697 | 2974 | 37723 | 69982479 | 25188433 | 44794046 | 32998751 | 4103733 | 28895017 | 40773203 | 5907586 | 34865617 | 69982479 | 25188433 | 44794046 | 32998751 | 4103733 | 28895017 | 40773203 | 5907586 | 34865617 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2012 | Q2 | Q2 - 2012 | 28631231 | 8404716 | 20226515 | 22688469 | 3198364 | 19490105 | 23974261 | 3784754 | 20189508 | 35225331 | 15494088 | 19731243 | 7657728 | 852805 | 6804922 | 9547443 | 1318850 | 8228593 | 268147 | 24379 | 243768 | 91998 | 12088 | 79910 | 91998 | 12088 | 79910 | 4261800 | 0 | 4261800 | 4906403 | 24776 | 4881626 | 5974984 | 24776 | 5950207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1627287 | 107513 | 1519774 | 1638599 | 107513 | 1531085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 43475 | 43475 | 0 | 143475 | 143475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39130 | 1155 | 37976 | 40631 | 1155 | 39476 | 69982479 | 25188433 | 44794046 | 37054490 | 4240176 | 32814313 | 41411391 | 5392611 | 36018779 | 69982479 | 25188433 | 44794046 | 37054490 | 4240176 | 32814313 | 41411391 | 5392611 | 36018779 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2012 | Q3 | Q3 - 2012 | 28631231 | 8404716 | 20226515 | 24550001 | 4173998 | 20376003 | 25947771 | 5305632 | 20642139 | 35225331 | 15494088 | 19731243 | 10172578 | 961860 | 9210718 | 13300202 | 3039127 | 10261075 | 268147 | 24379 | 243768 | 92320 | 12088 | 80232 | 92320 | 12088 | 80232 | 4261800 | 0 | 4261800 | 5652548 | 24776 | 5627772 | 6095646 | 24776 | 6070870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1652767 | 121068 | 1531699 | 1668162 | 121068 | 1547094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 43475 | 43475 | 0 | 143475 | 143475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 43859 | 2781 | 41078 | 48359 | 2781 | 45578 | 69982479 | 25188433 | 44794046 | 42207548 | 5340046 | 36867502 | 47295935 | 8648947 | 38646988 | 69982479 | 25188433 | 44794046 | 42207548 | 5340046 | 36867502 | 47295935 | 8648947 | 38646988 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2012 | Q4 | Q4 - 2012 | 26433236 | 5385499 | 21047737 | 25042536 | 4288603 | 20538174 | 25429063 | 4491996 | 20937067 | 21437183 | 5594707 | 15842476 | 11437954 | 608207 | 10541448 | 15157173 | 3608001 | 11549172 | 255856 | 12088 | 243768 | 98823 | 12088 | 86735 | 108823 | 22088 | 86735 | 10510119 | 4452625 | 6057494 | 5878035 | 57594 | 5818812 | 8097197 | 2276756 | 5820440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1624024 | 93505 | 1527774 | 1649024 | 93505 | 1555519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 34750 | 34750 | 0 | 34750 | 34750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 45813 | 2980 | 42832 | 50313 | 7480 | 42832 | 60532495 | 15738449 | 44794046 | 44161935 | 5097727 | 38555775 | 50526343 | 10534576 | 39991765 | 60532495 | 15738449 | 44794046 | 44161935 | 5097727 | 38555775 | 50526343 | 10534576 | 39991765 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2013 | Q1 | Q1 - 2013 | 26433236 | 5385499 | 21047737 | 25986170 | 5272534 | 20713637 | 26881758 | 6044122 | 20837637 | 21437183 | 5594707 | 15842476 | 12424611 | 1518742 | 10905870 | 16272119 | 3455306 | 12816812 | 255856 | 12088 | 243768 | 99767 | 13671 | 86096 | 99767 | 13671 | 86096 | 10510119 | 4452624 | 6057494 | 7732389 | 1736925 | 5995464 | 8760768 | 2705860 | 6054908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1668464 | 119331 | 1549133 | 1682464 | 119331 | 1563133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 37545 | 37545 | 0 | 47545 | 47545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 72945 | 30434 | 42511 | 147945 | 45434 | 102511 | 60532495 | 15738448 | 44794046 | 48021891 | 8729182 | 39292711 | 53892366 | 12431269 | 41461097 | 60532495 | 15738448 | 44794046 | 48021891 | 8729182 | 39292711 | 53892366 | 12431269 | 41461097 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2013 | Q2 | Q2 - 2013 | 26433236 | 5385499 | 21047737 | 26533136 | 5496546 | 21036590 | 27281492 | 5936345 | 21345147 | 21437183 | 5594707 | 15842476 | 14410619 | 2991481 | 11419137 | 18925929 | 4205679 | 14720250 | 255856 | 12088 | 243768 | 99511 | 13671 | 85840 | 99511 | 13671 | 85840 | 10510119 | 4452624 | 6057494 | 8083477 | 2073222 | 6010256 | 11576555 | 5354711 | 6221844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1719160 | 145508 | 1573652 | 1734160 | 145508 | 1588652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 37545 | 37545 | 0 | 47545 | 47545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 74956 | 32148 | 42807 | 89956 | 32148 | 57807 | 60532495 | 15738448 | 44794046 | 50958404 | 10790121 | 40168282 | 59755148 | 15735607 | 44019540 | 60532495 | 15738448 | 44794046 | 50958404 | 10790121 | 40168282 | 59755148 | 15735607 | 44019540 | 0 | 0 | ONECOMMUNITY
NT10BIX5570067 | INF | 2013 | Q3 | Q3 - 2013 | 26433236 | 5385499 | 21047737 | 25858489 | 5022290 | 20836199 | 0 | 0 | 0 | 21437183 | 5594707 | 15842476 | 22224163 | 7074459 | 15149704 | 0 | 0 | 0 | 255856 | 12088 | 243768 | 234418 | 19228 | 215190 | 0 | 0 | 0 | 10510119 | 4452624 | 6057494 | 10197457 | 3770347 | 6427110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1669032 | 59644 | 1609388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 43545 | 43545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 108733 | 61388 | 47345 | 0 | 0 | 0 | 60532495 | 15738448 | 44794046 | 60335837 | 16050901 | 44284936 | 0 | 0 | 0 | 60532495 | 15738448 | 44794046 | 60335837 | 16050901 | 44284936 | 0 | 0 | 0 | 0 | 0 | ONECOMMUNITY
NT10BIX5570068 | INF | 2010 | Q3 | Q3 - 2010 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754390 | 826317 | 1928073 | 76025 | 22808 | 53217 | 265000 | 79500 | 185500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425508 | 6727653 | 15697855 | 76025 | 22808 | 53217 | 465000 | 139500 | 325500 | 22425508 | 6727653 | 15697855 | 76025 | 22808 | 53217 | 465000 | 139500 | 325500 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2010 | Q4 | Q4 - 2010 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 354900 | 106470 | 248430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 293438 | 88031 | 205407 | 849928 | 254978 | 594950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205407 | 1255828 | 376748 | 879080 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205407 | 1255828 | 376748 | 879080 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2011 | Q1 | Q1 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 742966 | 222890 | 520076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 293438 | 88031 | 205406 | 760568 | 228170 | 532398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 25500 | 7650 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205406 | 1529034 | 458710 | 1070324 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205406 | 1529034 | 458710 | 1070324 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2011 | Q2 | Q2 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 959969 | 287991 | 671978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 440491 | 132147 | 308344 | 1064000 | 319200 | 744800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 294363 | 88309 | 206054 | 326363 | 97909 | 228454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 734854 | 220456 | 514398 | 2401332 | 720400 | 1680932 | 22425509 | 6727653 | 15697856 | 734854 | 220456 | 514398 | 2401332 | 720400 | 1680932 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2011 | Q3 | Q3 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 2000000 | 600000 | 1400000 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 959968 | 287990 | 671978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 445491 | 133647 | 311844 | 495491 | 148647 | 346844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 378618 | 113585 | 265033 | 461118 | 138335 | 322783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 824109 | 247232 | 576877 | 3946577 | 1183972 | 2762605 | 22425509 | 6727653 | 15697856 | 824109 | 247232 | 576877 | 3946577 | 1183972 | 2762605 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2011 | Q4 | Q4 - 2011 | 2195529 | 658659 | 1536870 | 2012658 | 603797 | 1408860 | 2012658 | 603797 | 1408860 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 4895826 | 3686484 | 1209343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 466691 | 140007 | 326684 | 1287439 | 386232 | 901207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1429916 | 428975 | 1000941 | 1456416 | 436925 | 1019491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 6299 | 1890 | 4409 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 3915564 | 1174669 | 2740894 | 9703339 | 5128738 | 4574601 | 22425509 | 6727653 | 15697856 | 3915564 | 1174669 | 2740894 | 9703339 | 5128738 | 4574601 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2012 | Q1 | Q1 - 2012 | 2195529 | 658659 | 1536870 | 1986436 | 595931 | 1390505 | 2195529 | 658689 | 1536840 | 15745589 | 4723677 | 11021912 | 7824661 | 2350303 | 5474358 | 12818901 | 3845670 | 8973231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 771545 | 231464 | 540082 | 1236439 | 370932 | 865507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1357670 | 407301 | 950369 | 2190776 | 657233 | 1533543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 11991312 | 3600299 | 8391014 | 18492645 | 5547824 | 12944821 | 22425509 | 6727653 | 15697856 | 11991312 | 3600299 | 8391014 | 18492645 | 5547824 | 12944821 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2012 | Q2 | Q2 - 2012 | 2195529 | 658659 | 1536870 | 2043252 | 612976 | 1430276 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 12452569 | 3735771 | 8716798 | 13917591 | 4175277 | 9742314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1430001 | 429000 | 1001001 | 1430001 | 429000 | 1001001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1835297 | 550589 | 1284708 | 2383501 | 715053 | 1668448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 17812119 | 5343636 | 12468483 | 19977622 | 5993289 | 13984333 | 22425509 | 6727653 | 15697856 | 17812119 | 5343636 | 12468483 | 19977622 | 5993289 | 13984333 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2012 | Q3 | Q3 - 2012 | 2195529 | 658659 | 1536870 | 2063356 | 619007 | 1444349 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 12948128 | 3884438 | 9063690 | 13917591 | 4175277 | 9742314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1539452 | 461836 | 1077616 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1994423 | 598327 | 1396096 | 2383501 | 715050 | 1668451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 18596359 | 5578908 | 13017451 | 20226621 | 6067986 | 14158635 | 22425509 | 6727653 | 15697856 | 18596359 | 5578908 | 13017451 | 20226621 | 6067986 | 14158635 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2012 | Q4 | Q4 - 2012 | 2195529 | 658659 | 1536870 | 2098127 | 629438 | 1468689 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 13008887 | 3902666 | 9106221 | 14263663 | 4279099 | 9984564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 2190607 | 657182 | 1533425 | 2458903 | 737671 | 1721232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 18898703 | 5669611 | 13229092 | 20519177 | 6155754 | 14363423 | 22425509 | 6727653 | 15697856 | 18898703 | 5669611 | 13229092 | 20519177 | 6155754 | 14363423 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2013 | Q1 | Q1 - 2013 | 2195529 | 658659 | 1536870 | 2098127 | 629438 | 1468689 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 14639163 | 4391749 | 10247414 | 15874507 | 4762352 | 11112155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 2334843 | 700453 | 1634390 | 2754391 | 826317 | 1928074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 20673215 | 6201965 | 14471250 | 22425509 | 6727653 | 15697856 | 22425509 | 6727653 | 15697856 | 20673215 | 6201965 | 14471250 | 22425509 | 6727653 | 15697856 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570068 | INF | 2013 | Q2 | Q2 - 2013 | 1931148 | 579344 | 1351804 | 1931148 | 579344 | 1351804 | 1931148 | 579344 | 1351804 | 16063135 | 4818941 | 11244195 | 16063135 | 4818941 | 11244195 | 16063135 | 4818941 | 11244195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2830144 | 849043 | 1981101 | 2830144 | 849043 | 1981101 | 2830144 | 849043 | 1981101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 0 | 0 | Valley Telephone Cooperative, Inc.
NT10BIX5570069 | INF | 2010 | Q4 | Q4 - 2010 | 8240330 | 2068846 | 6171484 | 0 | 0 | 0 | 649205 | 0 | 649205 | 13533583 | 3474949 | 10058634 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068631 | 2068631 | 0 | 246400 | 246400 | 0 | 503600 | 503600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 271400 | 271400 | 0 | 1177805 | 528600 | 649205 | 23867544 | 7637426 | 16230118 | 271400 | 271400 | 0 | 1177805 | 528600 | 649205 | 0 | 0 | Iowa Communications Network
NT10BIX5570069 | INF | 2011 | Q1 | Q1 - 2011 | 19452467 | 6086722 | 13365745 | 0 | 0 | 0 | 2983783 | 933983 | 2049800 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 249001 | 249001 | 0 | 332671 | 275775 | 56896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 274001 | 274001 | 0 | 3341454 | 1234758 | 2106696 | 23867544 | 7637426 | 16230118 | 274001 | 274001 | 0 | 3341454 | 1234758 | 2106696 | 0 | 0 | Iowa Communications Network
NT10BIX5570069 | INF | 2011 | Q2 | Q2 - 2011 | 19452467 | 6086722 | 13365745 | 162121 | 162121 | 0 | 1498638 | 469103 | 1029535 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 249001 | 249001 | 0 | 323401 | 274780 | 48621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 436122 | 436122 | 0 | 1847039 | 768883 | 1078156 | 23867544 | 7637426 | 16230118 | 436122 | 436122 | 0 | 1847039 | 768883 | 1078156 | 0 | 0 | Iowa Communications Network
NT10BIX5570069 | INF | 2011 | Q3 | Q3 - 2011 | 19452467 | 6086722 | 13365745 | 1483328 | 464311 | 1019017 | 6097923 | 1908770 | 4189153 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 329335 | 274147 | 55188 | 559989 | 346346 | 213643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 1837663 | 763458 | 1074205 | 6682912 | 2280116 | 4402796 | 23867544 | 7637426 | 16230118 | 1837663 | 763458 | 1074205 | 6682912 | 2280116 | 4402796 | 0 | 5370 | Iowa Communications Network
NT10BIX5570069 | INF | 2011 | Q4 | Q4 - 2011 | 19452467 | 6086722 | 13365745 | 7937745 | 2808714 | 5129031 | 13031433 | 4079095 | 8952338 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 482586 | 322117 | 160469 | 729969 | 399553 | 330416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 8445331 | 3155831 | 5289500 | 13786402 | 4503648 | 9282754 | 23867544 | 7637426 | 16230118 | 8445331 | 3155831 | 5289500 | 13786402 | 4503648 | 9282754 | 0 | 8151 | Iowa Communications Network
NT10BIX5570069 | INF | 2012 | Q1 | Q1 - 2012 | 19452467 | 6086722 | 13365745 | 9958987 | 3117046 | 6841941 | 12870625 | 4024217 | 8846408 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 550367 | 165110 | 385257 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 899995 | 453775 | 446220 | 1466671 | 630156 | 836515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 10883982 | 3595821 | 7288161 | 14912663 | 4844483 | 10068180 | 23867544 | 7637426 | 16230118 | 10883982 | 3595821 | 7288161 | 14912663 | 4844483 | 10068180 | 0 | 26898 | Iowa Communications Network
NT10BIX5570069 | INF | 2012 | Q2 | Q2 - 2012 | 19452467 | 6086722 | 13365745 | 13251576 | 4145396 | 9106180 | 13755028 | 4303545 | 9451483 | 1831073 | 553626 | 1277447 | 285783 | 85735 | 200048 | 926420 | 277926 | 648494 | 25000 | 25000 | 0 | 27064 | 25619 | 1445 | 176639 | 70492 | 106147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1377382 | 585032 | 792350 | 2024151 | 804658 | 1219493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 14941805 | 4841782 | 10100023 | 16882238 | 5456621 | 11425617 | 23867544 | 7637426 | 16230118 | 14941805 | 4841782 | 10100023 | 16882238 | 5456621 | 11425617 | 0 | 525205 | Iowa Communications Network
NT10BIX5570069 | INF | 2012 | Q3 | Q3 - 2012 | 19452467 | 6086722 | 13365745 | 13802302 | 4315839 | 9486463 | 15052302 | 4711667 | 10340635 | 1831073 | 553626 | 1277447 | 529302 | 158791 | 370511 | 1535925 | 462877 | 1073048 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 200000 | 77500 | 122500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1645629 | 686173 | 959456 | 1927635 | 774447 | 1153188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 16005280 | 5186717 | 10818563 | 18715862 | 6026491 | 12689371 | 23867544 | 7637426 | 16230118 | 16005280 | 5186717 | 10818563 | 18715862 | 6026491 | 12689371 | 0 | 1241444 | Iowa Communications Network
NT10BIX5570069 | INF | 2012 | Q4 | Q4 - 2012 | 19452467 | 6086722 | 13365745 | 14696488 | 4595737 | 10100751 | 17120416 | 5355721 | 11764695 | 1831073 | 553626 | 1277447 | 518354 | 155506 | 362848 | 1432846 | 429854 | 1002992 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 28047 | 25914 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113097 | 33929 | 79168 | 243033 | 72910 | 170123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1825692 | 742537 | 1083155 | 2179097 | 853159 | 1325938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 17181678 | 5553623 | 11628055 | 21003439 | 6737558 | 14265881 | 23867544 | 7637426 | 16230118 | 17181678 | 5553623 | 11628055 | 21003439 | 6737558 | 14265881 | 0 | 1833565 | Iowa Communications Network
NT10BIX5570069 | INF | 2013 | Q1 | Q1 - 2013 | 19452467 | 6086722 | 13365745 | 16718919 | 5219787 | 11499132 | 19686612 | 6163555 | 13523057 | 1831073 | 553626 | 1277447 | 572322 | 171697 | 400625 | 1526324 | 457897 | 1068427 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 28047 | 25914 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113097 | 33929 | 79168 | 243033 | 72910 | 170123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1979272 | 790610 | 1188662 | 2383528 | 917150 | 1466378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 19411657 | 6241937 | 13169720 | 23867544 | 7637426 | 16230118 | 23867544 | 7637426 | 16230118 | 19411657 | 6241937 | 13169720 | 23867544 | 7637426 | 16230118 | 0 | 2628105 | Iowa Communications Network
NT10BIX5570069 | INF | 2013 | Q2 | Q2 - 2013 | 18781048 | 5874182 | 12906866 | 17791911 | 5686097 | 12105814 | 17791911 | 5686097 | 12105814 | 1451448 | 438119 | 1013329 | 1409381 | 422814 | 986567 | 1409381 | 422814 | 986567 | 29000 | 26200 | 2800 | 30054 | 26516 | 3538 | 30054 | 26516 | 3538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193033 | 57910 | 135123 | 192063 | 57619 | 134444 | 192063 | 57619 | 134444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3413015 | 1241015 | 2172000 | 3315876 | 1083525 | 2232351 | 3315876 | 1083525 | 2232351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 22739285 | 7276571 | 15462714 | 22739285 | 7276571 | 15462714 | 23867544 | 7637426 | 16230118 | 22739285 | 7276571 | 15462714 | 22739285 | 7276571 | 15462714 | 0 | 3659603 | Iowa Communications Network
NT10BIX5570070 | INF | 2010 | Q4 | Q4 - 2010 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 0 | 0 | 0 | 51193858 | 19660308 | 31533549 | 197470 | 63151 | 134319 | 5493536 | 5046990 | 446546 | 1871196 | 598342 | 1272854 | 846407 | 270681 | 575726 | 942032 | 301262 | 640770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 969844 | 310156 | 659688 | 1735263 | 554937 | 1180326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 221856 | 70950 | 150906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 2013721 | 643988 | 1369733 | 8392687 | 5974139 | 2418548 | 71645444 | 26200000 | 45445444 | 2013721 | 643988 | 1369733 | 8392687 | 5974139 | 2418548 | 0 | 0 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2011 | Q1 | Q1 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 0 | 0 | 0 | 51193858 | 19660308 | 31533549 | 4952317 | 4782129 | 170188 | 6707920 | 5435350 | 1272569 | 1871196 | 598342 | 1272854 | 1331941 | 425955 | 905986 | 1499793 | 479634 | 1020159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 1576918 | 504298 | 1072620 | 2671461 | 854333 | 1817128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 7861176 | 5712382 | 2148794 | 10879174 | 6769317 | 4109856 | 71645444 | 26200000 | 45445444 | 7861176 | 5712382 | 2148794 | 10879174 | 6769317 | 4109856 | 0 | 15111 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2011 | Q2 | Q2 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 46755 | 14952 | 31803 | 51193858 | 19660308 | 31533549 | 5642994 | 5018484 | 624510 | 12259053 | 7134300 | 5124753 | 1871196 | 598342 | 1272854 | 1497887 | 479024 | 1018863 | 1579815 | 505225 | 1074590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 2846470 | 910301 | 1936169 | 3384774 | 1082451 | 2302323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 9987351 | 6407809 | 3579542 | 17270397 | 8736928 | 8533469 | 71645444 | 26200000 | 45445444 | 9987351 | 6407809 | 3579542 | 17270397 | 8736928 | 8533469 | 0 | 55111 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2011 | Q3 | Q3 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 890098 | 284653 | 605445 | 51193858 | 19660308 | 31533549 | 9908471 | 6428779 | 3479692 | 18635507 | 9219685 | 9415822 | 1871196 | 598342 | 1272854 | 1718696 | 549639 | 1169057 | 1800624 | 575840 | 1224784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 4114915 | 1315950 | 2798965 | 4814312 | 1539617 | 3274695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 221856 | 70950 | 150906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 15742082 | 8294368 | 7447714 | 26362397 | 11690745 | 14671652 | 71645444 | 26200000 | 45445444 | 15742082 | 8294368 | 7447714 | 26362397 | 11690745 | 14671652 | 0 | 95111 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2011 | Q4 | Q4 - 2011 | 7044808 | 2252680 | 4792129 | 1699347 | 543451 | 1155896 | 3316645 | 1060663 | 2255982 | 51193858 | 19660308 | 31533549 | 15381787 | 8139996 | 7241791 | 25544436 | 11390011 | 14154425 | 1871196 | 598342 | 1272854 | 1815016 | 580442 | 1234574 | 1933655 | 618383 | 1315272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 6110610 | 1954173 | 4156437 | 8201510 | 2622843 | 5578667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 75000 | 23985 | 51015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 25006760 | 11218062 | 13788698 | 39071246 | 15715885 | 23355361 | 71645444 | 26200000 | 45445444 | 25006760 | 11218062 | 13788698 | 39071246 | 15715885 | 23355361 | 0 | 135111 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2012 | Q1 | Q1 - 2012 | 7044808 | 2252680 | 4792129 | 2874533 | 984809 | 1889724 | 7051038 | 2613646 | 4437392 | 51193858 | 19660308 | 31533549 | 20859979 | 10172730 | 10687249 | 31166673 | 14192341 | 16974332 | 1871196 | 598342 | 1272854 | 1931425 | 621752 | 1309673 | 2021674 | 656949 | 1364725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 9073047 | 3042602 | 6030445 | 11229743 | 3883713 | 7346030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 75000 | 29250 | 45750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 34738984 | 14821893 | 19917091 | 51544128 | 21375899 | 30168229 | 71645444 | 26200000 | 45445444 | 34738984 | 14821893 | 19917091 | 51544128 | 21375899 | 30168229 | 0 | 186444 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2012 | Q2 | Q2 - 2012 | 7044808 | 2252680 | 4792129 | 5418177 | 1998521 | 3419656 | 8934594 | 3371293 | 5563301 | 51193858 | 19660308 | 31533549 | 30123324 | 13872606 | 16250718 | 37608277 | 16797240 | 20811037 | 1871196 | 598342 | 1272854 | 2033736 | 663459 | 1370277 | 2211693 | 732954 | 1478739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 10811236 | 3748386 | 7062850 | 12445750 | 4387598 | 8058152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 106233 | 41431 | 64802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 48386473 | 20282972 | 28103501 | 61306547 | 25330516 | 35976031 | 71645444 | 26200000 | 45445444 | 48386473 | 20282972 | 28103501 | 61306547 | 25330516 | 35976031 | 0 | 256444 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2012 | Q3 | Q3 - 2012 | 7044808 | 2252680 | 4792129 | 7639986 | 3064989 | 4574997 | 9304801 | 3864101 | 5440700 | 51193858 | 19660308 | 31533549 | 35402062 | 16406634 | 18995428 | 40794872 | 18995154 | 21799718 | 1871196 | 598342 | 1272854 | 2198879 | 742738 | 1456141 | 2383885 | 831540 | 1552345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 11297966 | 3980055 | 7317911 | 13137090 | 4862834 | 8274256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 145000 | 69600 | 75400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 56538893 | 24194416 | 32344477 | 65765648 | 28623229 | 37142419 | 71645444 | 26200000 | 45445444 | 56538893 | 24194416 | 32344477 | 65765648 | 28623229 | 37142419 | 0 | 326444 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2012 | Q4 | Q4 - 2012 | 7044808 | 2252680 | 4792129 | 8311382 | 3377799 | 4933583 | 9173116 | 3791431 | 5381685 | 51193858 | 19660308 | 31533549 | 40146090 | 18495369 | 21650721 | 46775127 | 21677278 | 25097849 | 1871196 | 598342 | 1272854 | 2318187 | 793108 | 1525079 | 2520055 | 890005 | 1630050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 12225955 | 4350107 | 7875848 | 13234137 | 4834034 | 8400103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 343264 | 164767 | 178497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 63001614 | 27016383 | 35985231 | 72045699 | 31357515 | 40688184 | 71645444 | 26200000 | 45445444 | 63001614 | 27016383 | 35985231 | 72045699 | 31357515 | 40688184 | 0 | 396444 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2013 | Q1 | Q1 - 2013 | 7044808 | 2252680 | 4792129 | 9323284 | 3819265 | 5504019 | 10193254 | 4236850 | 5956403 | 51193858 | 19660308 | 31533549 | 47998725 | 21871344 | 26127381 | 53313234 | 24422309 | 28890925 | 1871196 | 598342 | 1272854 | 2380725 | 818977 | 1561748 | 2510774 | 881400 | 1629374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 13001906 | 4669276 | 8332630 | 15496891 | 5866869 | 9630022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 258854 | 105492 | 153362 | 489841 | 216365 | 273476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 72963494 | 31284354 | 41679140 | 82003994 | 35623793 | 46380200 | 71645444 | 26200000 | 45445444 | 72963494 | 31284354 | 41679140 | 82003994 | 35623793 | 46380200 | 0 | 469677 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2013 | Q2 | Q2 - 2013 | 7044808 | 2252680 | 4792129 | 10140947 | 4293076 | 5847871 | 10247217 | 4399346 | 5847871 | 51193858 | 19660308 | 31533549 | 53255744 | 24917630 | 28338114 | 55869406 | 27531292 | 28338114 | 1871196 | 598342 | 1272854 | 2520701 | 900089 | 1620612 | 2731931 | 1111319 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 15431289 | 6077031 | 9354258 | 16746847 | 7392589 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 570904 | 286315 | 284589 | 934717 | 650128 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 81919585 | 36474141 | 45445444 | 86530118 | 41084674 | 45445444 | 71645444 | 26200000 | 45445444 | 81919585 | 36474141 | 45445444 | 86530118 | 41084674 | 45445444 | 0 | 551301 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2013 | Q3 | Q3 - 2013 | 7044808 | 2252680 | 4792129 | 10460006 | 4612135 | 5847871 | 11159892 | 5312021 | 5847871 | 51193858 | 19660308 | 31533549 | 55084769 | 26746655 | 28338114 | 56085466 | 27747352 | 28338114 | 1871196 | 598342 | 1272854 | 2603564 | 982952 | 1620612 | 2775505 | 1154893 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 16161593 | 6807335 | 9354258 | 17227926 | 7873668 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 898570 | 613981 | 284589 | 1241906 | 957317 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 85208502 | 39763058 | 45445444 | 88490695 | 43045251 | 45445444 | 71645444 | 26200000 | 45445444 | 85208502 | 39763058 | 45445444 | 88490695 | 43045251 | 45445444 | 0 | 603479 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2013 | Q4 | Q4 - 2013 | 7044808 | 2252680 | 4792129 | 10720121 | 4872250 | 5847871 | 11161203 | 5313332 | 5847871 | 51193858 | 19660308 | 31533549 | 55501812 | 27163698 | 28338114 | 56445180 | 28107066 | 28338114 | 1871196 | 598342 | 1272854 | 2742104 | 1121492 | 1620612 | 2917042 | 1296430 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 17283720 | 7929462 | 9354258 | 17685291 | 8331033 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 1175221 | 890632 | 284589 | 1476469 | 1191880 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 87422978 | 41977534 | 45445444 | 89685185 | 44239741 | 45445444 | 71645444 | 26200000 | 45445444 | 87422978 | 41977534 | 45445444 | 89685185 | 44239741 | 45445444 | 0 | 612896 | Massachusetts Technology Park
NT10BIX5570070 | INF | 2014 | Q1 | Q1 - 2014 | 7044808 | 2252680 | 4792129 | 8573614 | 3196573 | 5377041 | 8573614 | 3196573 | 5377041 | 51193858 | 19660308 | 31533549 | 52351935 | 23158430 | 29193505 | 52351935 | 23158430 | 29193505 | 2009190 | 642468 | 1366722 | 2816146 | 1234590 | 1581556 | 2816146 | 1234590 | 1581556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9179028 | 2935127 | 6243901 | 16055629 | 7016739 | 9038890 | 16055629 | 7016739 | 9038890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 1205212 | 950760 | 254452 | 1205212 | 950760 | 254452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 81002536 | 35557092 | 45445444 | 81002536 | 35557092 | 45445444 | 71645444 | 26200000 | 45445444 | 81002536 | 35557092 | 45445444 | 81002536 | 35557092 | 45445444 | 0 | 637363 | Massachusetts Technology Park
NT10BIX5570071 | INF | 2010 | Q4 | Q4 - 2010 | 2647380 | 794214 | 1853166 | 0 | 0 | 0 | 800000 | 240000 | 560000 | 15271893 | 4581568 | 10690325 | 0 | 0 | 0 | 1313255 | 393976 | 919279 | 172263 | 51679 | 120884 | 0 | 0 | 0 | 172263 | 51679 | 120884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 422675 | 126803 | 295872 | 0 | 0 | 0 | 120000 | 36000 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735398 | 13382892 | 0 | 0 | 0 | 2655518 | 796655 | 1859163 | 19117990 | 5735398 | 13382892 | 0 | 0 | 0 | 2655518 | 796655 | 1859163 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570071 | INF | 2011 | Q1 | Q1 - 2011 | 2647380 | 794214 | 1853166 | 0 | 0 | 0 | 400000 | 120000 | 280000 | 15271893 | 4581567 | 10690326 | 1610 | 483 | 1127 | 451610 | 135483 | 316127 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 260881 | 78264 | 182617 | 327491 | 98247 | 229244 | 422675 | 126803 | 295872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735397 | 13382593 | 434754 | 130426 | 304328 | 1351364 | 405409 | 945955 | 19117990 | 5735397 | 13382593 | 434754 | 130426 | 304328 | 1351364 | 405409 | 945955 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570071 | INF | 2011 | Q2 | Q2 - 2011 | 2647380 | 794214 | 1853166 | 7231 | 2169 | 5062 | 1607231 | 482169 | 1125062 | 15271893 | 4581568 | 10690325 | 74517 | 22355 | 52162 | 1069517 | 320855 | 748662 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 357772 | 107332 | 250440 | 421127 | 126338 | 294789 | 422675 | 126802 | 295873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735397 | 13382593 | 611783 | 183535 | 428248 | 3270138 | 981041 | 2289097 | 19117990 | 5735397 | 13382593 | 611783 | 183535 | 428248 | 3270138 | 981041 | 2289097 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570071 | INF | 2011 | Q3 | Q3 - 2011 | 2647380 | 794214 | 1853166 | 1897727 | 569318 | 1328409 | 2157727 | 647318 | 1510409 | 15271893 | 4581568 | 10690325 | 826081 | 247824 | 578257 | 2360081 | 708024 | 1652057 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 0 | 0 | 0 | 110000 | 33000 | 77000 | 422675 | 126803 | 295872 | 425931 | 127779 | 298152 | 425931 | 127779 | 298152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 5226002 | 1567800 | 3658202 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 5226002 | 1567800 | 3658202 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570071 | INF | 2011 | Q4 | Q4 - 2011 | 2647380 | 794214 | 1853166 | 1897727 | 569318 | 1328409 | 1897727 | 569318 | 1328409 | 15271893 | 4581568 | 10690325 | 826081 | 247824 | 578257 | 826081 | 247824 | 578257 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 0 | 0 | 0 | 0 | 0 | 0 | 422675 | 126803 | 295872 | 425931 | 127779 | 298152 | 425931 | 127779 | 298152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 3322002 | 996600 | 2325402 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 3322002 | 996600 | 2325402 | 0 | 0 | Zayo Bandwidth, LLC
NT10BIX5570072 | INF | 2010 | Q4 | Q4 - 2010 | 8758868 | 3877761 | 4881107 | 189385 | 189385 | 0 | 2135250 | 1727623 | 407627 | 30306281 | 7831123 | 22475158 | 31409 | 7538 | 23871 | 323966 | 125581 | 198385 | 186863 | 75013 | 111850 | 110983 | 26636 | 84347 | 176969 | 67303 | 109666 | 1497801 | 542165 | 955636 | 8600 | 2064 | 6536 | 117899 | 53083 | 64816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 143984 | 34556 | 109428 | 266890 | 64054 | 202836 | 282530 | 84759 | 197771 | 184852 | 51127 | 133725 | 208852 | 58327 | 150525 | 130000 | 31200 | 98800 | 0 | 0 | 0 | 2600 | 624 | 1976 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 20700 | 6210 | 14490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 669213 | 311306 | 357907 | 3253126 | 2102805 | 1150321 | 42904268 | 12872419 | 30031849 | 669213 | 311306 | 357907 | 3253126 | 2102805 | 1150321 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2011 | Q1 | Q1 - 2011 | 8758868 | 3877761 | 4881107 | 206831 | 193572 | 13259 | 2219070 | 1751678 | 467392 | 30306281 | 7831123 | 22475158 | 48117 | 11548 | 36569 | 1439859 | 359966 | 1079893 | 186863 | 75013 | 111850 | 148967 | 35752 | 113215 | 179484 | 44591 | 134893 | 1497801 | 542165 | 955636 | 21350 | 5124 | 16226 | 65100 | 16824 | 48276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 197529 | 47407 | 150122 | 430698 | 103368 | 327330 | 282530 | 84759 | 197771 | 210099 | 57186 | 152913 | 210099 | 57186 | 152913 | 130000 | 31200 | 98800 | 0 | 0 | 0 | 19607 | 4706 | 14901 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 832893 | 350589 | 482304 | 4563917 | 2338319 | 2225598 | 42904268 | 12872419 | 30031849 | 832893 | 350589 | 482304 | 4563917 | 2338319 | 2225598 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2011 | Q2 | Q2 - 2011 | 8758868 | 3877761 | 4881107 | 1880202 | 1648647 | 231555 | 2692997 | 2361339 | 331658 | 30306281 | 7831123 | 22475158 | 614972 | 320655 | 294317 | 2939687 | 1532794 | 1406893 | 186863 | 75013 | 111850 | 198772 | 60095 | 138677 | 224490 | 85913 | 138577 | 1497801 | 542165 | 955636 | 45300 | 10872 | 34428 | 113566 | 27256 | 86310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 393995 | 94559 | 299436 | 541891 | 130054 | 411837 | 282530 | 84759 | 197771 | 215002 | 58363 | 156639 | 215002 | 58363 | 156639 | 130000 | 31200 | 98800 | 9677 | 2322 | 7355 | 12764 | 3829 | 8935 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 20000 | 6000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 3357920 | 2195513 | 1162407 | 6760397 | 4205548 | 2554849 | 42904268 | 12872419 | 30031849 | 3357920 | 2195513 | 1162407 | 6760397 | 4205548 | 2554849 | 0 | 1190 | COM Net, Inc.
NT10BIX5570072 | INF | 2011 | Q3 | Q3 - 2011 | 8758868 | 3877761 | 4881107 | 2475470 | 1827227 | 648243 | 3158300 | 2331247 | 827053 | 30306281 | 7831123 | 22475158 | 2230100 | 769165 | 1460935 | 3589093 | 1237884 | 2351209 | 186863 | 75013 | 111850 | 259995 | 74788 | 185207 | 344965 | 99230 | 245735 | 1497801 | 542165 | 955636 | 121376 | 30663 | 90713 | 176940 | 44700 | 132240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 535919 | 128621 | 407298 | 587202 | 140929 | 446273 | 282530 | 84759 | 197771 | 215002 | 58363 | 156639 | 215001 | 58363 | 156638 | 130000 | 31200 | 98800 | 48118 | 11549 | 36569 | 76028 | 18247 | 57781 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 5885980 | 2900376 | 2985604 | 8147529 | 3930600 | 4216929 | 42904268 | 12872419 | 30031849 | 5885980 | 2900376 | 2985604 | 8147529 | 3930600 | 4216929 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2011 | Q4 | Q4 - 2011 | 8758868 | 3877761 | 4881107 | 2960289 | 1972673 | 987616 | 3408761 | 2080308 | 1328453 | 30306281 | 7831123 | 22475158 | 3651645 | 1110336 | 2541309 | 7072918 | 1931441 | 5141477 | 186863 | 75013 | 111850 | 331771 | 92835 | 238936 | 441374 | 125716 | 315658 | 1497801 | 542165 | 955636 | 195454 | 49162 | 146292 | 253405 | 66547 | 186858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 694040 | 166570 | 527470 | 988133 | 254797 | 733336 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 241136 | 66204 | 174932 | 130000 | 31200 | 98800 | 93185 | 22364 | 70821 | 131455 | 33846 | 97609 | 205600 | 61680 | 143920 | 4040 | 1212 | 2828 | 25272 | 7582 | 17690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 8145425 | 3473515 | 4671910 | 12562454 | 4566441 | 7996013 | 42904268 | 12872419 | 30031849 | 8145425 | 3473515 | 4671910 | 12562454 | 4566441 | 7996013 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2012 | Q1 | Q1 - 2012 | 8758868 | 3877761 | 4881107 | 3690023 | 2236403 | 1453620 | 5595449 | 3391220 | 2204229 | 30306281 | 7831123 | 22475158 | 6200772 | 1722127 | 4478646 | 9030631 | 2508057 | 6522574 | 186863 | 75013 | 111850 | 433892 | 117344 | 316548 | 489000 | 132248 | 356752 | 1497801 | 542165 | 955636 | 267984 | 66569 | 201415 | 301687 | 74941 | 226746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 877450 | 210588 | 666862 | 1165410 | 279698 | 885712 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 278757 | 75670 | 203087 | 130000 | 31200 | 98800 | 123828 | 29718 | 94109 | 166589 | 39981 | 126608 | 205600 | 61680 | 143920 | 4040 | 1212 | 2828 | 31272 | 9382 | 21890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 11812990 | 4442324 | 7370666 | 17058795 | 6511197 | 10547598 | 42904268 | 12872419 | 30031849 | 11812990 | 4442324 | 7370666 | 17058795 | 6511197 | 10547598 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2012 | Q2 | Q2 - 2012 | 8758868 | 3877761 | 4881107 | 5135871 | 2880399 | 2255472 | 5728191 | 3471670 | 2256521 | 30306281 | 7831123 | 22475158 | 8627650 | 2316407 | 6311243 | 11138633 | 3093508 | 8045125 | 186863 | 75013 | 111850 | 485532 | 129738 | 355794 | 492992 | 133327 | 359665 | 1497801 | 542165 | 955636 | 398808 | 97962 | 300846 | 366897 | 91140 | 275757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 959536 | 230289 | 729247 | 983987 | 236157 | 747830 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 300976 | 81701 | 219275 | 130000 | 31200 | 98800 | 174079 | 41779 | 132300 | 213734 | 51296 | 162438 | 205600 | 61680 | 143920 | 4486 | 1319 | 3167 | 63200 | 18960 | 44240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 16000963 | 5756256 | 10244707 | 19288610 | 7177759 | 12110851 | 42904268 | 12872419 | 30031849 | 16000963 | 5756256 | 10244707 | 19288610 | 7177759 | 12110851 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2012 | Q3 | Q3 - 2012 | 8758868 | 3877761 | 4881107 | 5587352 | 3042442 | 2544910 | 6463092 | 3519304 | 2943788 | 30306281 | 7831123 | 22475158 | 11587812 | 3036779 | 8551033 | 16657215 | 4365302 | 12291913 | 186863 | 75013 | 111850 | 522939 | 138716 | 384223 | 576201 | 152844 | 423357 | 1497801 | 542165 | 955636 | 528660 | 135929 | 392731 | 607772 | 156270 | 451502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1140111 | 273627 | 866484 | 1298558 | 311654 | 986904 | 282530 | 84759 | 197771 | 229476 | 61837 | 167639 | 241685 | 65127 | 176558 | 130000 | 31200 | 98800 | 209449 | 50267 | 159182 | 274349 | 65844 | 208505 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 118475 | 35410 | 83065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 19880508 | 6761926 | 13118582 | 26237347 | 8671755 | 17565592 | 42904268 | 12872419 | 30031849 | 19880508 | 6761926 | 13118582 | 26237347 | 8671755 | 17565592 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2012 | Q4 | Q4 - 2012 | 8758868 | 3877761 | 4881107 | 6239273 | 3211420 | 3027853 | 6658258 | 3337116 | 3321142 | 30306281 | 7831123 | 22475158 | 15367047 | 3962741 | 11404306 | 20205928 | 5412615 | 14793313 | 186863 | 75013 | 111850 | 574245 | 151029 | 423216 | 607310 | 165798 | 441512 | 1497801 | 542165 | 955636 | 659388 | 172551 | 486837 | 757993 | 205934 | 552059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1289194 | 309407 | 979787 | 2018933 | 504734 | 1514199 | 282530 | 84759 | 197771 | 242814 | 65038 | 177776 | 242814 | 65038 | 177776 | 130000 | 31200 | 98800 | 253027 | 60726 | 192301 | 259921 | 64980 | 194941 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 91871 | 28377 | 63494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 24699697 | 7955241 | 16744456 | 30843028 | 9784592 | 21058436 | 42904268 | 12872419 | 30031849 | 24699697 | 7955241 | 16744456 | 30843028 | 9784592 | 21058436 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2013 | Q1 | Q1 - 2013 | 8758868 | 3877761 | 4881107 | 6757333 | 3366838 | 3390495 | 8752578 | 4376289 | 4376289 | 30306281 | 7831123 | 22475158 | 18447936 | 4729767 | 13718169 | 23834356 | 5958589 | 17875767 | 186863 | 75013 | 111850 | 648616 | 177552 | 471064 | 687453 | 192487 | 494966 | 1497801 | 542165 | 955636 | 728763 | 193323 | 535440 | 764763 | 198838 | 565925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1316702 | 316008 | 1000694 | 1366072 | 327857 | 1038215 | 282530 | 84759 | 197771 | 255180 | 68006 | 187174 | 269180 | 69987 | 199193 | 130000 | 31200 | 98800 | 294971 | 70793 | 224178 | 344593 | 79256 | 265337 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 196262 | 56916 | 139346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 28524210 | 8944616 | 19579594 | 36215257 | 11260219 | 24955038 | 42904268 | 12872419 | 30031849 | 28524210 | 8944616 | 19579594 | 36215257 | 11260219 | 24955038 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2013 | Q2 | Q2 - 2013 | 8758868 | 3877761 | 4881107 | 6924905 | 3503460 | 3421445 | 9493779 | 4649627 | 4844152 | 30306281 | 7831123 | 22475158 | 22341769 | 5636674 | 16705095 | 28235192 | 6776446 | 21458746 | 186863 | 75013 | 111850 | 683260 | 185867 | 497393 | 802594 | 240778 | 561816 | 1497801 | 542165 | 955636 | 804726 | 213256 | 591470 | 921313 | 276394 | 644919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1368724 | 328494 | 1040230 | 1455526 | 349326 | 1106200 | 282530 | 84759 | 197771 | 271166 | 71842 | 199324 | 300694 | 90208 | 210486 | 130000 | 31200 | 98800 | 334097 | 80183 | 253914 | 359448 | 87788 | 271660 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 148971 | 44691 | 104280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 32803356 | 10042105 | 22761251 | 41717517 | 12515258 | 29202259 | 42904268 | 12872419 | 30031849 | 32803356 | 10042105 | 22761251 | 41717517 | 12515258 | 29202259 | 0 | 0 | COM Net, Inc.
NT10BIX5570072 | INF | 2013 | Q3 | Q3 - 2013 | 8758868 | 3877761 | 4881107 | 9356354 | 4158259 | 5198095 | 9356354 | 4158259 | 5198095 | 30306281 | 7831123 | 22475158 | 26940177 | 6898563 | 20041614 | 26940177 | 6898563 | 20041614 | 186863 | 75013 | 111850 | 781208 | 212516 | 568692 | 781208 | 212516 | 568692 | 1497801 | 542165 | 955636 | 961835 | 258390 | 703445 | 961835 | 258390 | 703445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1388419 | 333606 | 1054813 | 1388419 | 333606 | 1054813 | 282530 | 84759 | 197771 | 280507 | 74089 | 206418 | 280507 | 74089 | 206418 | 130000 | 31200 | 98800 | 379809 | 91154 | 288655 | 379809 | 91154 | 288655 | 205600 | 61680 | 143920 | 112532 | 33675 | 78857 | 112532 | 33675 | 78857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 40200841 | 12060252 | 28140589 | 40200841 | 12060252 | 28140589 | 42904268 | 12872419 | 30031849 | 40200841 | 12060252 | 28140589 | 40200841 | 12060252 | 28140589 | 0 | 0 | COM Net, Inc.
NT10BIX5570073 | INF | 2010 | Q4 | Q4 - 2010 | 1047656 | 314297 | 733359 | 0 | 0 | 0 | 0 | 0 | 0 | 4788511 | 1436553 | 3351958 | 0 | 0 | 0 | 0 | 0 | 0 | 329125 | 98738 | 230387 | 33199 | 9960 | 23239 | 77949 | 23385 | 54564 | 121855 | 36557 | 85298 | 7500 | 2250 | 5250 | 37500 | 11250 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25375 | 7612 | 17763 | 16915 | 5075 | 11840 | 25375 | 7612 | 17763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 140824 | 42247 | 98577 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 140824 | 42247 | 98577 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2011 | Q1 | Q1 - 2011 | 1047656 | 314297 | 733359 | 0 | 0 | 0 | 314998 | 220499 | 94499 | 4788511 | 1436553 | 3351958 | 0 | 0 | 0 | 169577 | 118704 | 50873 | 329125 | 98738 | 230387 | 33199 | 9960 | 23239 | 86688 | 47402 | 39286 | 121855 | 36557 | 85298 | 7500 | 2250 | 5250 | 53370 | 34359 | 19011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25375 | 7612 | 17763 | 16915 | 5075 | 11840 | 35375 | 17997 | 17378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 660008 | 438961 | 221047 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 660008 | 438961 | 221047 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2011 | Q2 | Q2 - 2011 | 1856242 | 556873 | 1299369 | 7898 | 2369 | 5529 | 1409682 | 422905 | 986777 | 3914725 | 1174417 | 2740308 | 0 | 0 | 0 | 26833 | 8050 | 18783 | 349700 | 104910 | 244790 | 81753 | 24526 | 57226 | 144936 | 43480 | 101456 | 121855 | 36557 | 85298 | 47955 | 14387 | 33569 | 57955 | 17387 | 40568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 28210 | 8464 | 19747 | 48210 | 14463 | 33747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 165816 | 49746 | 116071 | 1687616 | 506285 | 1181331 | 6312522 | 1893757 | 4418765 | 165816 | 49746 | 116071 | 1687616 | 506285 | 1181331 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2011 | Q3 | Q3 - 2011 | 1856242 | 556873 | 1299369 | 1417685 | 425306 | 992379 | 1842991 | 425306 | 1417685 | 3914725 | 1174417 | 2740308 | 0 | 0 | 0 | 735015 | 220505 | 514510 | 349700 | 104910 | 244790 | 141842 | 42553 | 99289 | 214422 | 64327 | 150095 | 121855 | 36557 | 85298 | 71155 | 21347 | 49809 | 100740 | 30222 | 70518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 49473 | 14842 | 34631 | 62308 | 18692 | 43616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 1680155 | 504048 | 1176108 | 2955476 | 759052 | 2196424 | 6312522 | 1893757 | 4418765 | 1680155 | 504048 | 1176108 | 2955476 | 759052 | 2196424 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2011 | Q4 | Q4 - 2011 | 1856242 | 556873 | 1299369 | 1417685 | 425306 | 992379 | 1417685 | 425306 | 992379 | 3914725 | 1174417 | 2740308 | 61271 | 18381 | 42890 | 2999482 | 899845 | 2099637 | 349700 | 104910 | 244790 | 175573 | 52668 | 122905 | 220578 | 66173 | 154405 | 121855 | 36557 | 85298 | 107788 | 32337 | 75451 | 117795 | 35339 | 82456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 91354 | 27407 | 63948 | 91354 | 27407 | 63948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 1853671 | 556099 | 1297573 | 4846894 | 1454070 | 3392825 | 6312522 | 1893757 | 4418765 | 1853671 | 556099 | 1297573 | 4846894 | 1454070 | 3392825 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2012 | Q1 | Q1 - 2012 | 1856242 | 556873 | 1299369 | 1469933 | 440980 | 1028953 | 1559933 | 467980 | 1091953 | 3914725 | 1174417 | 2740308 | 157014 | 47104 | 109910 | 2357014 | 707104 | 1649910 | 349700 | 104910 | 244790 | 218919 | 65672 | 153247 | 235947 | 70784 | 165163 | 121855 | 36557 | 85298 | 112038 | 33612 | 78426 | 117038 | 35111 | 81927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 102518 | 30756 | 71762 | 127518 | 38255 | 89263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 2060422 | 618124 | 1442298 | 4397450 | 1319234 | 3078216 | 6312522 | 1893757 | 4418765 | 2060422 | 618124 | 1442298 | 4397450 | 1319234 | 3078216 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2012 | Q2 | Q2 - 2012 | 1856242 | 556873 | 1299369 | 1552525 | 465757 | 1086768 | 1817243 | 545173 | 1272070 | 3914725 | 1174417 | 2740308 | 1076385 | 322917 | 753467 | 3269279 | 980784 | 2288495 | 349700 | 104910 | 244790 | 235640 | 70692 | 164948 | 251074 | 75322 | 175752 | 121855 | 36557 | 85298 | 114038 | 34211 | 79827 | 119038 | 35711 | 83327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 120764 | 36229 | 84535 | 195762 | 58729 | 137033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 3099352 | 929806 | 2169545 | 5652396 | 1695719 | 3956677 | 6312522 | 1893757 | 4418765 | 3099352 | 929806 | 2169545 | 5652396 | 1695719 | 3956677 | 0 | 0 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2012 | Q3 | Q3 - 2012 | 1856242 | 556873 | 1299369 | 1729224 | 518768 | 1210456 | 1900000 | 570000 | 1330000 | 3914725 | 1174417 | 2740308 | 2620205 | 786061 | 1834144 | 3650000 | 1095000 | 2555000 | 349700 | 104910 | 244790 | 268030 | 80409 | 187621 | 293030 | 87909 | 205121 | 121855 | 36557 | 85298 | 114038 | 34211 | 79827 | 114038 | 34211 | 79827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 153426 | 46028 | 107398 | 153426 | 46028 | 107398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 4884923 | 1465477 | 3419446 | 6110494 | 1833148 | 4277346 | 6312522 | 1893757 | 4418765 | 4884923 | 1465477 | 3419446 | 6110494 | 1833148 | 4277346 | 0 | 4400 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2012 | Q4 | Q4 - 2012 | 1856242 | 556873 | 1299369 | 1891150 | 567346 | 1323804 | 1891150 | 567346 | 1323804 | 3914725 | 1174417 | 2740308 | 3242446 | 972734 | 2269712 | 3650000 | 1095000 | 2555000 | 349700 | 104910 | 244790 | 281664 | 84499 | 197165 | 300000 | 90000 | 210000 | 121855 | 36557 | 85298 | 115118 | 34535 | 80583 | 115118 | 34535 | 80583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 5685651 | 1705696 | 3979955 | 6111541 | 1833463 | 4278078 | 6312522 | 1893757 | 4418765 | 5685651 | 1705696 | 3979955 | 6111541 | 1833463 | 4278078 | 0 | 34052 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2013 | Q1 | Q1 - 2013 | 1856242 | 556873 | 1299369 | 2053076 | 615923 | 1437153 | 2223181 | 666912 | 1556269 | 3914725 | 1174417 | 2740308 | 3528370 | 1058554 | 2469816 | 3528370 | 1058554 | 2469816 | 349700 | 104910 | 244790 | 290440 | 87132 | 203308 | 290440 | 87132 | 203308 | 121855 | 36557 | 85298 | 115258 | 34577 | 80681 | 115258 | 34577 | 80681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 6142417 | 1842768 | 4299649 | 6312522 | 1893757 | 4418765 | 6312522 | 1893757 | 4418765 | 6142417 | 1842768 | 4299649 | 6312522 | 1893757 | 4418765 | 0 | 15000 | Bend Cable Communications, LLC
NT10BIX5570073 | INF | 2013 | Q2 | Q2 - 2013 | 1856242 | 556873 | 1299369 | 2266652 | 723464 | 1543188 | 2266652 | 723464 | 1543188 | 3914725 | 1174417 | 2740308 | 3535315 | 1060595 | 2474720 | 3535315 | 1060595 | 2474720 | 349700 | 104910 | 244790 | 295177 | 88553 | 206624 | 295177 | 88553 | 206624 | 121855 | 36557 | 85298 | 122203 | 36661 | 85542 | 122203 | 36661 | 85542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 6374620 | 1955855 | 4418765 | 6374620 | 1955855 | 4418765 | 6312522 | 1893757 | 4418765 | 6374620 | 1955855 | 4418765 | 6374620 | 1955855 | 4418765 | 0 | 56144 | Bend Cable Communications, LLC
NT10BIX5570074 | INF | 2010 | Q4 | Q4 - 2010 | 2865257 | 573051 | 2292206 | 137052 | 27410 | 109642 | 329652 | 65930 | 263722 | 21603817 | 4320764 | 17283053 | 90645 | 18130 | 72515 | 277610 | 55522 | 222088 | 93905 | 18781 | 75124 | 21700 | 4340 | 17360 | 73948 | 14789 | 59159 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 31062 | 6212 | 24850 | 56062 | 11213 | 44849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 22550 | 4510 | 18040 | 37550 | 7510 | 30040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 303009 | 60602 | 242407 | 774822 | 154964 | 619858 | 25906278 | 5181256 | 20725022 | 303009 | 60602 | 242407 | 774822 | 154964 | 619858 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2011 | Q1 | Q1 - 2011 | 2865257 | 573051 | 2292206 | 143591 | 28718 | 114873 | 315791 | 63158 | 252633 | 21603817 | 4320764 | 17283053 | 185895 | 37179 | 148715 | 967724 | 193545 | 774179 | 93905 | 18781 | 75124 | 75884 | 15177 | 60707 | 85884 | 17177 | 68707 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 119023 | 23805 | 95218 | 119163 | 23833 | 95330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 60411 | 12082 | 48329 | 66411 | 13282 | 53129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 584804 | 116961 | 467842 | 1637473 | 327495 | 1309978 | 25906278 | 5181256 | 20725022 | 584804 | 116961 | 467842 | 1637473 | 327495 | 1309978 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2011 | Q2 | Q2 - 2011 | 2865257 | 573051 | 2292206 | 409288 | 81858 | 327430 | 915791 | 183158 | 732633 | 21603817 | 4320764 | 17283053 | 856044 | 171208 | 684836 | 3356045 | 671209 | 2684836 | 93905 | 18781 | 75124 | 77654 | 15531 | 62123 | 78654 | 15731 | 62923 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 119740 | 23948 | 95792 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 81299 | 16260 | 65039 | 99299 | 19860 | 79439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 1616169 | 323234 | 1292935 | 4663553 | 932711 | 3730842 | 25906278 | 5181256 | 20725022 | 1616169 | 323234 | 1292935 | 4663553 | 932711 | 3730842 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2011 | Q3 | Q3 - 2011 | 2865258 | 573052 | 2292206 | 435893 | 87179 | 348714 | 538834 | 107767 | 431067 | 21603816 | 4320763 | 17283053 | 1906208 | 381242 | 1524966 | 6297797 | 1259559 | 5038238 | 93905 | 18781 | 75124 | 78866 | 15773 | 63093 | 80866 | 16173 | 64693 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 120835 | 24167 | 96668 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 91944 | 18389 | 73555 | 112944 | 22589 | 90355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 2705890 | 541179 | 2164711 | 7244205 | 1448841 | 5795364 | 25906278 | 5181256 | 20725022 | 2705890 | 541179 | 2164711 | 7244205 | 1448841 | 5795364 | 444621 | 390000 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2011 | Q4 | Q4 - 2011 | 2865258 | 573052 | 2292206 | 663399 | 132680 | 530719 | 718620 | 143724 | 574896 | 21603816 | 4320763 | 17283053 | 5220523 | 1044105 | 4176418 | 8363374 | 1672675 | 6690699 | 93905 | 18781 | 75124 | 80144 | 16029 | 64115 | 81000 | 16200 | 64800 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 154180 | 30836 | 123344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 110500 | 22100 | 88400 | 140500 | 28100 | 112400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 6268104 | 1253622 | 5014482 | 9583414 | 1916683 | 7666731 | 25906278 | 5181256 | 20725022 | 6268104 | 1253622 | 5014482 | 9583414 | 1916683 | 7666731 | 889241 | 166340 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2012 | Q1 | Q1 - 2012 | 2865258 | 573052 | 2292206 | 784361 | 156872 | 627489 | 1985661 | 397132 | 1588529 | 21603816 | 4320763 | 17283053 | 7682542 | 1536509 | 6146033 | 14741794 | 2948213 | 11792581 | 93905 | 18781 | 75124 | 83257 | 16651 | 66606 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 87701 | 17540 | 70161 | 200401 | 40080 | 160321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 129975 | 25995 | 103980 | 186175 | 37235 | 148940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 8889230 | 1777846 | 7111384 | 17357936 | 3471441 | 13885495 | 25906278 | 5181256 | 20725022 | 8889230 | 1777846 | 7111384 | 17357936 | 3471441 | 13885495 | 1443041 | 276831 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2012 | Q2 | Q2 - 2012 | 2865258 | 573052 | 2292206 | 879408 | 175882 | 703526 | 1985661 | 397132 | 1588529 | 21603816 | 4320763 | 17283053 | 13899806 | 2779960 | 11119846 | 16993440 | 3398688 | 13594752 | 93905 | 18781 | 75124 | 83926 | 16785 | 67141 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 498413 | 99683 | 398730 | 565840 | 113168 | 452672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 167588 | 33518 | 134070 | 227175 | 45435 | 181740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 15650535 | 3130107 | 12520428 | 20016021 | 4003204 | 16012817 | 25906278 | 5181256 | 20725022 | 15650535 | 3130107 | 12520428 | 20016021 | 4003204 | 16012817 | 1107600 | 502907 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2012 | Q3 | Q3 - 2012 | 2865258 | 573052 | 2292206 | 1478737 | 295747 | 1182990 | 1985000 | 397000 | 1588000 | 21603816 | 4320763 | 17283053 | 18275321 | 3655065 | 14620256 | 21713973 | 4342795 | 17371178 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 637299 | 127460 | 509839 | 675000 | 135000 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 199252 | 39850 | 159402 | 228000 | 45600 | 182400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 20805908 | 4161182 | 16644726 | 24845878 | 4969176 | 19876702 | 25906278 | 5181256 | 20725022 | 20805908 | 4161182 | 16644726 | 24845878 | 4969176 | 19876702 | 2550642 | 650694 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2012 | Q4 | Q4 - 2012 | 2865258 | 573052 | 2292206 | 1609309 | 321862 | 1287447 | 1700000 | 340000 | 1360000 | 21603816 | 4320763 | 17283053 | 21078909 | 4215781 | 16863128 | 21778909 | 4355782 | 17423127 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 239753 | 47951 | 191802 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 23911270 | 4782254 | 19129016 | 24740814 | 4948163 | 19792651 | 25906278 | 5181256 | 20725022 | 23911270 | 4782254 | 19129016 | 24740814 | 4948163 | 19792651 | 3104443 | 1665250 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2013 | Q1 | Q1 - 2013 | 2865258 | 573052 | 2292206 | 1609309 | 321862 | 1287447 | 2865258 | 573052 | 2292206 | 21603816 | 4320763 | 17283053 | 21203825 | 4240764 | 16963061 | 21603816 | 4320763 | 17283053 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 216000 | 43200 | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 295151 | 59031 | 236120 | 359299 | 71860 | 287439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 24091584 | 4818317 | 19273267 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 24091584 | 4818317 | 19273267 | 25906278 | 5181256 | 20725022 | 3866020 | 2121913 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2013 | Q2 | Q2 - 2013 | 2865258 | 573052 | 2292206 | 1890007 | 378001 | 1512006 | 1890832 | 378826 | 1512006 | 21603816 | 4320763 | 17283053 | 22771786 | 4554357 | 18217429 | 23000000 | 4805553 | 18194447 | 93905 | 18781 | 75124 | 110544 | 22109 | 88435 | 110544 | 22109 | 88435 | 768000 | 153600 | 614400 | 706274 | 141255 | 565019 | 710595 | 145576 | 565019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 121394 | 24279 | 97115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 306273 | 61255 | 245018 | 335000 | 67000 | 268000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 26168365 | 5443343 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 26168365 | 5443343 | 20725022 | 4627598 | 2654843 | Contact Network Inc. d/b/a InLine
NT10BIX5570074 | INF | 2013 | Q3 | Q3 - 2013 | 2865258 | 573052 | 2292206 | 1894665 | 378933 | 1515732 | 1894665 | 378933 | 1515732 | 21603816 | 4320763 | 17283053 | 22718616 | 4543723 | 18174893 | 22718616 | 4543723 | 18174893 | 93905 | 18781 | 75124 | 110544 | 22109 | 88435 | 110544 | 22109 | 88435 | 768000 | 153600 | 614400 | 743485 | 148697 | 594788 | 743485 | 148697 | 594788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 121394 | 24279 | 97115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 317574 | 63515 | 254059 | 317574 | 63515 | 254059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 5334176 | 3270148 | Contact Network Inc. d/b/a InLine
NT10BIX5570075 | INF | 2010 | Q4 | Q4 - 2010 | 86655145 | 28058852 | 58596293 | 8861813 | 2443684 | 6418129 | 29205000 | 6800000 | 22405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 432566 | 448031 | 0 | 3215000 | 800000 | 2415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 9993807 | 3591143 | 6418129 | 33119428 | 8299428 | 24820000 | 96793607 | 34253445 | 62540162 | 9993807 | 3591143 | 6418129 | 33119428 | 8299428 | 24820000 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2011 | Q1 | Q1 - 2011 | 86655145 | 28058852 | 58596293 | 20822547 | 3199906 | 17622641 | 40440235 | 7124239 | 33315996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 846154 | 846154 | 0 | 1246154 | 1246154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 22368129 | 4745488 | 17622641 | 42385817 | 9069821 | 33315996 | 96793607 | 34253445 | 62540162 | 22368129 | 4745488 | 17622641 | 42385817 | 9069821 | 33315996 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2011 | Q2 | Q2 - 2011 | 86655145 | 28058852 | 58596293 | 27562567 | 4789149 | 22773418 | 38862567 | 6989149 | 31873418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 1286652 | 1286652 | 0 | 1686652 | 1686652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 29548647 | 6775229 | 22773418 | 41248647 | 9375229 | 31873418 | 96793607 | 34253445 | 62540162 | 29548647 | 6775229 | 22773418 | 41248647 | 9375229 | 31873418 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2011 | Q3 | Q3 - 2011 | 86655145 | 28058852 | 58596293 | 39956741 | 6355610 | 33601131 | 47956741 | 9155610 | 38801131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2455882 | 2455882 | 0 | 3555882 | 3555882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 43112051 | 9510920 | 33601131 | 52212051 | 13410920 | 38801131 | 96793607 | 34253445 | 62540162 | 43112051 | 9510920 | 33601131 | 52212051 | 13410920 | 38801131 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2011 | Q4 | Q4 - 2011 | 86655145 | 28058852 | 58596293 | 49837859 | 10397350 | 39440509 | 58840000 | 15740000 | 43100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2900209 | 2900209 | 0 | 3380000 | 3380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 53437496 | 13996987 | 39440509 | 62919428 | 19819428 | 43100000 | 96793607 | 34253445 | 62540162 | 53437496 | 13996987 | 39440509 | 62919428 | 19819428 | 43100000 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2012 | Q1 | Q1 - 2012 | 86655145 | 28058852 | 58596293 | 61212579 | 13668116 | 47544463 | 73760572 | 19800000 | 53960572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3264186 | 3264186 | 0 | 3740000 | 3740000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 65176193 | 17631730 | 47544463 | 78200000 | 24239428 | 53960572 | 96793607 | 34253445 | 62540162 | 65176193 | 17631730 | 47544463 | 78200000 | 24239428 | 53960572 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2012 | Q2 | Q2 - 2012 | 86655145 | 28058852 | 58596293 | 69305524 | 18566707 | 50738818 | 83305525 | 23566707 | 59738818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2815320 | 2815320 | 0 | 3165320 | 3165320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 72820272 | 22081455 | 50738818 | 87170273 | 27431455 | 59738818 | 96793607 | 34253445 | 62540162 | 72820272 | 22081455 | 50738818 | 87170273 | 27431455 | 59738818 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2012 | Q3 | Q3 - 2012 | 86655145 | 28058852 | 58596293 | 83877012 | 23989349 | 59887663 | 86400000 | 24500000 | 61900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3170031 | 3170031 | 0 | 3520000 | 3520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 87746471 | 27858808 | 59887663 | 90619428 | 28719428 | 61900000 | 96793607 | 34253445 | 62540162 | 87746471 | 27858808 | 59887663 | 90619428 | 28719428 | 61900000 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2012 | Q4 | Q4 - 2012 | 86655145 | 28058852 | 58596293 | 85027327 | 25139664 | 59887664 | 89040000 | 26500000 | 62540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3170031 | 3170031 | 0 | 3170031 | 3170031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 88896786 | 29009123 | 59887664 | 92909459 | 30369459 | 62540000 | 96793607 | 34253445 | 62540162 | 88896786 | 29009123 | 59887664 | 92909459 | 30369459 | 62540000 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2013 | Q1 | Q1 - 2013 | 89392955 | 31791803 | 57601152 | 84513328 | 23140804 | 61372524 | 89354322 | 27339305 | 62015017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6895819 | 1956809 | 4939010 | 6934452 | 6409307 | 525145 | 6934452 | 6409307 | 525145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 91952613 | 30054944 | 61897669 | 96793607 | 34253445 | 62540162 | 96793607 | 34253445 | 62540162 | 91952613 | 30054944 | 61897669 | 96793607 | 34253445 | 62540162 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570075 | INF | 2013 | Q2 | Q2 - 2013 | 89392955 | 31791803 | 57601152 | 89452174 | 27437157 | 62015017 | 89452174 | 27437157 | 62015017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6895819 | 1956809 | 4939010 | 7006202 | 6481057 | 525145 | 7006202 | 6481057 | 525145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 0 | 0 | University Corporation For Advanced Internet Development
NT10BIX5570076 | INF | 2010 | Q4 | Q4 - 2010 | 7054996 | 2116499 | 4938497 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 30720083 | 9216025 | 21504058 | 0 | 0 | 0 | 0 | 0 | 0 | 1951241 | 585372 | 1365869 | 292306 | 87692 | 204614 | 375871 | 112761 | 263110 | 1151500 | 345450 | 806050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 0 | 0 | 0 | 480000 | 144000 | 336000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 8757 | 2627 | 6130 | 308757 | 92627 | 216130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 47704860 | 14311458 | 33393402 | 301063 | 90319 | 210744 | 1444628 | 433388 | 1011240 | 47704860 | 14311458 | 33393402 | 301063 | 90319 | 210744 | 1444628 | 433388 | 1011240 | 4900 | 4900 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2011 | Q1 | Q1 - 2011 | 7522996 | 2584499 | 4938497 | 0 | 0 | 0 | 0 | 0 | 0 | 30720083 | 9216025 | 21504058 | 100000 | 100000 | 0 | 1990735 | 667220 | 1323515 | 1956141 | 590272 | 1365869 | 430547 | 134064 | 301383 | 647137 | 194141 | 452996 | 1151500 | 345450 | 806050 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 87081 | 26124 | 60957 | 641527 | 192458 | 449069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 35000 | 10500 | 24500 | 48177760 | 14784358 | 33393402 | 617628 | 260188 | 362340 | 3364399 | 1079319 | 2285080 | 48177760 | 14784358 | 33393402 | 617628 | 260188 | 362340 | 3364399 | 1079319 | 2285080 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2011 | Q2 | Q2 - 2011 | 7522996 | 2584499 | 4938497 | 0 | 0 | 0 | 70550 | 21165 | 49385 | 30720083 | 9216025 | 21504058 | 681166 | 274350 | 406816 | 2088220 | 858932 | 1229287 | 1956141 | 590272 | 1365869 | 574538 | 176702 | 397836 | 643190 | 363662 | 279528 | 1151500 | 345450 | 806050 | 22301 | 6690 | 15611 | 213831 | 73070 | 140761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 27083 | 8125 | 18958 | 62082 | 29458 | 32625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 249389 | 74817 | 174572 | 850000 | 354756 | 495244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 0 | 0 | 0 | 48177760 | 14784358 | 33393402 | 1554477 | 540684 | 1013793 | 3927873 | 1701043 | 2226830 | 48177760 | 14784358 | 33393402 | 1554477 | 540684 | 1013793 | 3927873 | 1701043 | 2226830 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2011 | Q3 | Q3 - 2011 | 7522996 | 2584499 | 4938497 | 63714 | 19114 | 44600 | 113714 | 34114 | 79600 | 30720083 | 9216025 | 21504058 | 1303311 | 460993 | 842318 | 3856711 | 1227013 | 2629698 | 1956141 | 590272 | 1365869 | 704768 | 216591 | 488177 | 821537 | 251621 | 569916 | 1151500 | 345450 | 806050 | 45530 | 13659 | 31871 | 190276 | 57083 | 133193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 100451 | 30135 | 70316 | 361730 | 108519 | 253211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 642140 | 192642 | 449498 | 1033740 | 310122 | 723618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 190000 | 57000 | 133000 | 48177760 | 14784358 | 33393402 | 2859914 | 933134 | 1926780 | 6567708 | 2045472 | 4522236 | 48177760 | 14784358 | 33393402 | 2859914 | 933134 | 1926780 | 6567708 | 2045472 | 4522236 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2011 | Q4 | Q4 - 2011 | 7522996 | 2584499 | 4938497 | 122723 | 36817 | 85906 | 1122723 | 336817 | 785906 | 30720083 | 9216025 | 21504058 | 4025559 | 1277668 | 2747891 | 7116309 | 2204893 | 4911416 | 1956141 | 590272 | 1365869 | 846722 | 257177 | 589545 | 1024941 | 310642 | 714299 | 1151500 | 345450 | 806050 | 65425 | 19627 | 45797 | 91924 | 27577 | 64347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 189887 | 56966 | 132921 | 389887 | 116966 | 272921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 1160954 | 348286 | 812668 | 1658254 | 497476 | 1160778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 173775 | 52133 | 121643 | 189776 | 56933 | 132843 | 48177760 | 14784358 | 33393402 | 6585045 | 2048674 | 4536371 | 11593814 | 3551304 | 8042510 | 48177760 | 14784358 | 33393402 | 6585045 | 2048674 | 4536371 | 11593814 | 3551304 | 8042510 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2012 | Q1 | Q1 - 2012 | 7522996 | 2584499 | 4938497 | 125961 | 37788 | 88173 | 1949993 | 584998 | 1364995 | 30720083 | 9216025 | 21504058 | 6242527 | 1942758 | 4299769 | 12133859 | 3850158 | 8283701 | 1956141 | 590272 | 1365869 | 983419 | 301632 | 681787 | 1125387 | 344222 | 781165 | 1151500 | 345450 | 806050 | 84914 | 25474 | 59440 | 491311 | 147393 | 343918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 368693 | 110608 | 258085 | 747893 | 224368 | 523525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 1668283 | 500485 | 1167798 | 2043283 | 612985 | 1430298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 175531 | 52659 | 122872 | 350531 | 105159 | 245372 | 48177760 | 14784358 | 33393402 | 9649328 | 2971404 | 6677924 | 18842257 | 5869283 | 12972974 | 48177760 | 14784358 | 33393402 | 9649328 | 2971404 | 6677924 | 18842257 | 5869283 | 12972974 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2012 | Q2 | Q2 - 2012 | 7522996 | 2584499 | 4938497 | 125961 | 37788 | 88173 | 2525960 | 757788 | 1768172 | 30720083 | 9216025 | 21504058 | 9026026 | 2777808 | 6248218 | 13016027 | 4114808 | 8901219 | 1956141 | 590272 | 1365869 | 1162212 | 349607 | 812605 | 1291711 | 388457 | 903254 | 1151500 | 345450 | 806050 | 174380 | 52314 | 122066 | 476380 | 142914 | 333466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 519542 | 155863 | 363679 | 933542 | 280063 | 653479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 2224380 | 667314 | 1557066 | 2649380 | 794814 | 1854566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 540069 | 162021 | 378048 | 48177760 | 14784358 | 33393402 | 13597570 | 4150215 | 9447355 | 21433069 | 6640865 | 14792204 | 48177760 | 14784358 | 33393402 | 13597570 | 4150215 | 9447355 | 21433069 | 6640865 | 14792204 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2012 | Q3 | Q3 - 2012 | 7522996 | 2584499 | 4938497 | 2269023 | 680707 | 1588316 | 4669023 | 1400707 | 3268316 | 30720083 | 9216025 | 21504058 | 11467994 | 3540398 | 8027596 | 16365194 | 5119558 | 11245636 | 1956141 | 590272 | 1365869 | 1098322 | 398137 | 914466 | 1455103 | 440887 | 1014216 | 1151500 | 345450 | 806050 | 542010 | 162603 | 379407 | 642010 | 192603 | 449407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 725801 | 217740 | 508061 | 725801 | 217740 | 508061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 2717854 | 815356 | 1902498 | 3142854 | 942856 | 2199998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 485069 | 145521 | 339548 | 48177760 | 14784358 | 33393402 | 19186073 | 5924462 | 13575892 | 27485054 | 8459872 | 19025182 | 48177760 | 14784358 | 33393402 | 19186073 | 5924462 | 13575892 | 27485054 | 8459872 | 19025182 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2012 | Q4 | Q4 - 2012 | 7522996 | 2584499 | 4938497 | 5227803 | 1568341 | 3659462 | 10073580 | 3022074 | 7051506 | 30720083 | 9216025 | 21504058 | 14849542 | 4524862 | 10324680 | 20052542 | 6225763 | 13826779 | 1956141 | 590272 | 1365869 | 1487929 | 450734 | 1037195 | 1594677 | 482758 | 1111919 | 1151500 | 345450 | 806050 | 539336 | 161801 | 377535 | 808116 | 242435 | 565681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 803199 | 240960 | 562239 | 1304698 | 391409 | 913289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3100827 | 930248 | 2170579 | 3310828 | 993248 | 2317580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 827569 | 248271 | 579298 | 48177760 | 14784358 | 33393402 | 26373705 | 7986467 | 18387238 | 37972010 | 11605958 | 26366052 | 48177760 | 14784358 | 33393402 | 26373705 | 7986467 | 18387238 | 37972010 | 11605958 | 26366052 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2013 | Q1 | Q1 - 2013 | 7522996 | 2584499 | 4938497 | 6571719 | 1971516 | 4600203 | 8748669 | 2624601 | 6124068 | 30720083 | 9216025 | 21504058 | 17093844 | 5128153 | 11965691 | 22768450 | 6830535 | 15937915 | 1956141 | 590272 | 1365869 | 1582684 | 479161 | 1103523 | 1685563 | 510109 | 1175454 | 1151500 | 345450 | 806050 | 708816 | 212645 | 496171 | 999826 | 299948 | 699878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 1407588 | 422276 | 985312 | 2012615 | 603785 | 1408830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3311201 | 993360 | 2317841 | 3471927 | 1041578 | 2430349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 489889 | 146967 | 342922 | 747569 | 224271 | 523298 | 48177760 | 14784358 | 33393402 | 31165741 | 9354078 | 21811663 | 40434619 | 12134827 | 28299792 | 48177760 | 14784358 | 33393402 | 31165741 | 9354078 | 21811663 | 40434619 | 12134827 | 28299792 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2013 | Q2 | Q2 - 2013 | 7522996 | 2584499 | 4938497 | 6989879 | 2096964 | 4892915 | 10616168 | 3184850 | 7431318 | 30720083 | 9216025 | 21504058 | 19475300 | 5842590 | 13632710 | 25765759 | 7729728 | 18036031 | 1956141 | 590272 | 1365869 | 1685484 | 510002 | 1175482 | 1813432 | 548386 | 1265046 | 1151500 | 345450 | 806050 | 747394 | 224218 | 523176 | 957394 | 287218 | 670176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 1768478 | 530543 | 1237935 | 2644487 | 793346 | 1851141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3343026 | 1002908 | 2340118 | 3531926 | 1059578 | 2472348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 500160 | 150048 | 350112 | 780269 | 234081 | 546188 | 48177760 | 14784358 | 33393402 | 34509721 | 10357273 | 24152448 | 46109435 | 13837187 | 32272248 | 48177760 | 14784358 | 33393402 | 34509721 | 10357273 | 24152448 | 46109435 | 13837187 | 32272248 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2013 | Q3 | Q3 - 2013 | 7522996 | 2584499 | 4938497 | 8864995 | 2659499 | 6205496 | 10633021 | 3189906 | 7443115 | 30720083 | 9216025 | 21504058 | 22393531 | 6718060 | 15675471 | 26892602 | 8207711 | 18684891 | 1956141 | 590272 | 1365869 | 1817373 | 549568 | 1267805 | 1935706 | 584142 | 1351564 | 1151500 | 345450 | 806050 | 800533 | 240160 | 560373 | 983337 | 295001 | 688336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2152945 | 645883 | 1507062 | 2870796 | 861238 | 2009558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3455526 | 1036658 | 2418868 | 3671926 | 1101578 | 2570348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 532603 | 159781 | 372822 | 880269 | 264081 | 616188 | 48177760 | 14784358 | 33393402 | 40017506 | 12009609 | 28007897 | 47867657 | 14503657 | 33364000 | 48177760 | 14784358 | 33393402 | 40017506 | 12009609 | 28007897 | 47867657 | 14503657 | 33364000 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2013 | Q4 | Q4 - 2013 | 7522996 | 2584499 | 4938497 | 9945910 | 2983773 | 6962137 | 10935911 | 3280773 | 7655138 | 30720083 | 9216025 | 21504058 | 24844805 | 7453442 | 17391363 | 25219705 | 7635842 | 17583863 | 1956141 | 590272 | 1365869 | 2182453 | 659156 | 1523297 | 2224852 | 671690 | 1553162 | 1151500 | 345450 | 806050 | 802917 | 240875 | 562042 | 877917 | 263375 | 614542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2437946 | 731383 | 1706563 | 2692946 | 807883 | 1885063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3496026 | 1048808 | 2447218 | 3521026 | 1056308 | 2464718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 1023509 | 307053 | 716456 | 1053509 | 316053 | 737456 | 48177760 | 14784358 | 33393402 | 44733566 | 13424490 | 31309076 | 46525866 | 14031924 | 32493942 | 48177760 | 14784358 | 33393402 | 44733566 | 13424490 | 31309076 | 46525866 | 14031924 | 32493942 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2014 | Q1 | Q1 - 2014 | 7522996 | 2584499 | 4938497 | 9864077 | 2959223 | 6904854 | 9964079 | 2989224 | 6974855 | 30720083 | 9216025 | 21504058 | 25546341 | 7663903 | 17882438 | 26179904 | 7853971 | 18325933 | 1956141 | 590272 | 1365869 | 2225322 | 672016 | 1553306 | 2255270 | 680815 | 1574455 | 1151500 | 345450 | 806050 | 808436 | 242531 | 565905 | 859436 | 257831 | 601605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2495715 | 748714 | 1747001 | 2974335 | 892300 | 2082035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3496652 | 1048996 | 2447656 | 3496652 | 1048996 | 2447656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 1028143 | 308443 | 719700 | 1028143 | 308443 | 719700 | 48177760 | 14784358 | 33393402 | 45464686 | 13643826 | 31820860 | 46757819 | 14031580 | 32726239 | 48177760 | 14784358 | 33393402 | 45464686 | 13643826 | 31820860 | 46757819 | 14031580 | 32726239 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2014 | Q2 | Q2 - 2014 | 7522996 | 2584499 | 4938497 | 9902809 | 2970843 | 6931966 | 11031957 | 3637186 | 7394771 | 30720083 | 9216025 | 21504058 | 25915242 | 7774573 | 18140669 | 26707339 | 8015702 | 18691637 | 1956141 | 590272 | 1365869 | 2275066 | 686939 | 1588127 | 2431733 | 733939 | 1697794 | 1151500 | 345450 | 806050 | 814359 | 244308 | 570051 | 906715 | 272015 | 634700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2639452 | 791835 | 1847617 | 3060619 | 918185 | 2142434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3496652 | 1048996 | 2447656 | 3496652 | 1048996 | 2447656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 1047060 | 314118 | 732942 | 1078709 | 323613 | 755096 | 48177760 | 14784358 | 33393402 | 46090640 | 13831612 | 32259028 | 48713724 | 14949636 | 33764088 | 48177760 | 14784358 | 33393402 | 46090640 | 13831612 | 32259028 | 48713724 | 14949636 | 33764088 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570076 | INF | 2014 | Q3 | Q3 - 2014 | 7522996 | 2584499 | 4938497 | 10608665 | 3708465 | 6900200 | 10608665 | 3708465 | 6900200 | 30720083 | 9216025 | 21504058 | 26634533 | 8011363 | 18623170 | 26634533 | 8011363 | 18623170 | 1956141 | 590272 | 1365869 | 2520617 | 872074 | 1648543 | 2520617 | 872074 | 1648543 | 1151500 | 345450 | 806050 | 842711 | 252813 | 589898 | 842711 | 252813 | 589898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 3447078 | 1036943 | 2410135 | 3447078 | 1036943 | 2410135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3496652 | 1048996 | 2447656 | 3496652 | 1048996 | 2447656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 1105429 | 331629 | 773800 | 1105429 | 331629 | 773800 | 48177760 | 14784358 | 33393402 | 48655685 | 15262283 | 33393402 | 48655685 | 15262283 | 33393402 | 48177760 | 14784358 | 33393402 | 48655685 | 15262283 | 33393402 | 48655685 | 15262283 | 33393402 | 0 | 0 | Vermont Telecommunications Authority
NT10BIX5570077 | INF | 2010 | Q4 | Q4 - 2010 | 562825 | 267495 | 295330 | 0 | 0 | 0 | 0 | 0 | 0 | 5043298 | 275005 | 4768293 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 3039 | 3039 | 0 | 5039 | 5039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 216835 | 216835 | 0 | 266459 | 266459 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 219874 | 219874 | 0 | 271498 | 271498 | 0 | 6346571 | 1282948 | 5063623 | 219874 | 219874 | 0 | 271498 | 271498 | 0 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2011 | Q1 | Q1 - 2011 | 562825 | 267494 | 295330 | 0 | 0 | 0 | 56282 | 31282 | 25000 | 5043298 | 275006 | 4768293 | 0 | 0 | 0 | 1008660 | 0 | 1008660 | 20000 | 20000 | 0 | 5685 | 5685 | 0 | 8700 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 316686 | 316686 | 0 | 341486 | 341486 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 3638 | 3638 | 0 | 54902 | 54902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 326009 | 326009 | 0 | 1470030 | 436370 | 1033660 | 6346571 | 1282948 | 5063623 | 326009 | 326009 | 0 | 1470030 | 436370 | 1033660 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2011 | Q2 | Q2 - 2011 | 562825 | 267494 | 295330 | 0 | 0 | 0 | 56282 | 56282 | 0 | 5043298 | 275006 | 4768293 | 239993 | 0 | 239993 | 3782473 | 0 | 3782473 | 20000 | 20000 | 0 | 7916 | 7916 | 0 | 10016 | 10016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 373997 | 373997 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 33561 | 33561 | 0 | 93561 | 93561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 655467 | 415474 | 239993 | 4348280 | 565807 | 3782473 | 6346571 | 1282948 | 5063623 | 655467 | 415474 | 239993 | 4348280 | 565807 | 3782473 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2011 | Q3 | Q3 - 2011 | 562825 | 267494 | 295330 | 47383 | 47383 | 0 | 112565 | 47383 | 65182 | 5043298 | 275006 | 4768293 | 3441477 | 68000 | 3373477 | 4538832 | 136000 | 4402832 | 20000 | 20000 | 0 | 5262 | 5262 | 0 | 7762 | 7762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 426693 | 426693 | 0 | 432693 | 432693 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 181480 | 181480 | 0 | 201480 | 201480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 4102295 | 728818 | 3373477 | 5293332 | 825318 | 4468014 | 6346571 | 1282948 | 5063623 | 4102295 | 728818 | 3373477 | 5293332 | 825318 | 4468014 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2011 | Q4 | Q4 - 2011 | 562825 | 267494 | 295330 | 374561 | 288905 | 85656 | 474561 | 94912 | 379649 | 5043298 | 275006 | 4768293 | 3920792 | 162680 | 3758112 | 4237000 | 200000 | 4037000 | 20000 | 20000 | 0 | 6375 | 6375 | 0 | 10375 | 10375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 446747 | 446747 | 0 | 479948 | 479948 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 259898 | 259898 | 0 | 269898 | 269898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5008373 | 1164605 | 3843768 | 5471782 | 1055133 | 4416649 | 6346571 | 1282948 | 5063623 | 5008373 | 1164605 | 3843768 | 5471782 | 1055133 | 4416649 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2012 | Q1 | Q1 - 2012 | 562825 | 267494 | 295330 | 363792 | 288950 | 85655 | 682742 | 308950 | 373792 | 5043298 | 275006 | 4768293 | 3939078 | 170152 | 3758113 | 4769078 | 240000 | 4529078 | 20000 | 20000 | 0 | 6753 | 6753 | 0 | 14253 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 444875 | 444874 | 0 | 474874 | 474874 | 0 | 9700 | 9700 | 0 | 356 | 356 | 0 | 3356 | 3356 | 0 | 304800 | 304800 | 0 | 290089 | 290089 | 0 | 300089 | 300089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5044943 | 1201174 | 3843768 | 6244392 | 1341522 | 4902870 | 6346571 | 1282948 | 5063623 | 5044943 | 1201174 | 3843768 | 6244392 | 1341522 | 4902870 | 0 | 750 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2012 | Q2 | Q2 - 2012 | 562825 | 267494 | 295330 | 383803 | 287333 | 96470 | 582664 | 267494 | 295330 | 5043298 | 275006 | 4768293 | 4029673 | 185152 | 3844521 | 5043298 | 275006 | 4768293 | 20000 | 20000 | 0 | 13267 | 13267 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 486072 | 486072 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 4979 | 4979 | 0 | 9700 | 9700 | 0 | 304800 | 304800 | 0 | 324778 | 324778 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5242572 | 1301581 | 3940991 | 6366410 | 1282948 | 5063623 | 6346571 | 1282948 | 5063623 | 5242572 | 1301581 | 3940991 | 6366410 | 1282948 | 5063623 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2012 | Q3 | Q3 - 2012 | 562825 | 267494 | 295330 | 551965 | 267494 | 259548 | 562825 | 267494 | 295330 | 5043298 | 275006 | 4768293 | 4417065 | 185152 | 4231913 | 5043298 | 275006 | 4768293 | 20000 | 20000 | 0 | 17945 | 17945 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 40594 | 405948 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 6656 | 6656 | 0 | 9700 | 9700 | 0 | 304800 | 304800 | 0 | 304800 | 304800 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5339025 | 1187995 | 4491461 | 6346571 | 1282948 | 5063623 | 6346571 | 1282948 | 5063623 | 5339025 | 1187995 | 4491461 | 6346571 | 1282948 | 5063623 | 0 | 3248 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2012 | Q4 | Q4 - 2012 | 578901 | 267494 | 311407 | 603823 | 292417 | 311407 | 603823 | 292417 | 311407 | 5027222 | 275006 | 4752216 | 5046244 | 294028 | 4752216 | 5046244 | 294028 | 4752216 | 20000 | 20000 | 0 | 20274 | 20274 | 0 | 20274 | 20274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 500456 | 500456 | 0 | 500456 | 500456 | 0 | 9700 | 9700 | 0 | 9953 | 9953 | 0 | 9953 | 9953 | 0 | 304800 | 304800 | 0 | 372443 | 372443 | 0 | 372443 | 372443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 0 | 22039 | Silver Star Telephone Company, INC.
NT10BIX5570077 | INF | 2013 | Q1 | Q1 - 2013 | 578901 | 267494 | 311407 | 603823 | 292417 | 311407 | 603823 | 292417 | 311407 | 5027222 | 275006 | 4752216 | 5046244 | 294028 | 4752216 | 5046244 | 294028 | 4752216 | 20000 | 20000 | 0 | 20274 | 20274 | 0 | 20274 | 20274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 500456 | 500456 | 0 | 500456 | 500456 | 0 | 9700 | 9700 | 0 | 9953 | 9953 | 0 | 9953 | 9953 | 0 | 304800 | 304800 | 0 | 372443 | 372443 | 0 | 372443 | 372443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 0 | 22039 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2010 | Q4 | Q4 - 2010 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 2789 | 2789 | 0 | 4800 | 4800 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 243058 | 243058 | 0 | 385797 | 385797 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289400 | 289400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 245847 | 245847 | 0 | 390597 | 390597 | 0 | 7234820 | 1626641 | 5608179 | 245847 | 245847 | 0 | 390597 | 390597 | 0 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2011 | Q1 | Q1 - 2011 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 0 | 0 | 0 | 1026754 | 0 | 1026754 | 20000 | 20000 | 0 | 5101 | 5101 | 0 | 7101 | 7101 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 355928 | 355928 | 0 | 410628 | 410628 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289400 | 289400 | 0 | 787 | 787 | 0 | 49819 | 49819 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626441 | 5608179 | 361816 | 361816 | 0 | 1494302 | 467548 | 1026754 | 7234820 | 1626441 | 5608179 | 361816 | 361816 | 0 | 1494302 | 467548 | 1026754 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2011 | Q2 | Q2 - 2011 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 1176376 | 0 | 1176376 | 3080262 | 0 | 3080262 | 20000 | 20000 | 0 | 7343 | 7343 | 0 | 14443 | 14443 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 406699 | 406699 | 0 | 766882 | 766882 | 0 | 60000 | 60000 | 0 | 12015 | 12015 | 0 | 45000 | 45000 | 0 | 289400 | 289400 | 0 | 40124 | 40124 | 0 | 80248 | 80248 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 1642557 | 466181 | 1176376 | 3986835 | 906573 | 3080262 | 7234820 | 1626641 | 5608179 | 1642557 | 466181 | 1176376 | 3986835 | 906573 | 3080262 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2011 | Q3 | Q3 - 2011 | 881968 | 787068 | 94900 | 2431 | 2431 | 0 | 86000 | 86000 | 0 | 5133770 | 40491 | 5093279 | 2033944 | 0 | 2033944 | 2973944 | 0 | 2973944 | 20000 | 20000 | 0 | 4462 | 4462 | 0 | 6662 | 6662 | 0 | 393000 | 0 | 393000 | 155126 | 0 | 155126 | 185126 | 0 | 185126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 438009 | 438009 | 0 | 438009 | 438009 | 0 | 60000 | 60000 | 0 | 12015 | 12015 | 0 | 30000 | 30000 | 0 | 289400 | 289400 | 0 | 94621 | 94621 | 0 | 124621 | 124621 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 2740608 | 551538 | 2189070 | 3871362 | 685292 | 3186070 | 7234820 | 1626641 | 5608179 | 2740608 | 551538 | 2189070 | 3871362 | 685292 | 3186070 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2011 | Q4 | Q4 - 2011 | 881968 | 787068 | 94900 | 107803 | 56455 | 51346 | 207803 | 100000 | 0 | 5133770 | 40491 | 5093279 | 2820527 | 0 | 2820527 | 2964527 | 0 | 144000 | 20000 | 20000 | 0 | 5436 | 5436 | 0 | 7500 | 7500 | 0 | 393000 | 0 | 393000 | 208791 | 0 | 208791 | 258791 | 0 | 258791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 438565 | 438565 | 0 | 448115 | 448115 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 30000 | 30000 | 0 | 289400 | 289400 | 0 | 172802 | 172802 | 0 | 180802 | 180802 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 3796274 | 688608 | 3107664 | 4136738 | 778617 | 429791 | 7234820 | 1626641 | 5608179 | 3796274 | 688608 | 3107664 | 4136738 | 778617 | 429791 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2012 | Q1 | Q1 - 2012 | 881968 | 787068 | 94900 | 62066 | 62066 | 0 | 262066 | 262066 | 0 | 5133770 | 40491 | 5093279 | 2820527 | 0 | 2820527 | 3120527 | 0 | 3120527 | 20000 | 20000 | 0 | 6616 | 6616 | 0 | 8616 | 8616 | 0 | 393000 | 0 | 393000 | 260138 | 0 | 260138 | 300138 | 0 | 300138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 461702 | 461702 | 0 | 471702 | 471702 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 30350 | 30350 | 0 | 289400 | 289400 | 0 | 189498 | 189498 | 0 | 209498 | 209498 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 661 | 661 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 3843558 | 735893 | 3107665 | 4442097 | 994432 | 3447665 | 7234820 | 1626641 | 5608179 | 3843558 | 735893 | 3107665 | 4442097 | 994432 | 3447665 | 0 | 750 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2012 | Q2 | Q2 - 2012 | 881968 | 787068 | 94900 | 230483 | 183241 | 47243 | 497241 | 404798 | 45200 | 5133770 | 40491 | 5093279 | 3057994 | 0 | 3057994 | 4857994 | 0 | 4857994 | 20000 | 20000 | 0 | 12693 | 12694 | 0 | 18793 | 18793 | 0 | 393000 | 0 | 393000 | 208156 | 0 | 208156 | 308156 | 0 | 308156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 528657 | 528658 | 0 | 536157 | 536157 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 48350 | 48350 | 0 | 289400 | 289400 | 0 | 228090 | 228090 | 0 | 274089 | 274089 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 1292 | 1292 | 0 | 6000 | 6000 | 0 | 7234820 | 1626641 | 5608179 | 4309715 | 969325 | 3340393 | 6573780 | 1288187 | 5238350 | 7234820 | 1626641 | 5608179 | 4309715 | 969325 | 3340393 | 6573780 | 1288187 | 5238350 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2012 | Q3 | Q3 - 2012 | 881968 | 787068 | 94900 | 280159 | 230004 | 50155 | 881968 | 787068 | 94900 | 5133770 | 40491 | 5093279 | 3664914 | 0 | 3664914 | 5133770 | 40491 | 5093279 | 20000 | 20000 | 0 | 16357 | 16357 | 0 | 20000 | 20000 | 0 | 393000 | 0 | 393000 | 241981 | 0 | 241981 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 538128 | 538128 | 0 | 417482 | 417482 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 60000 | 60000 | 0 | 289400 | 289400 | 0 | 271525 | 271525 | 0 | 289400 | 289400 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 10521 | 10522 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 5065935 | 1081886 | 3984050 | 7234820 | 1626641 | 5608179 | 7234820 | 1626641 | 5608179 | 5065935 | 1081886 | 3984050 | 7234820 | 1626641 | 5608179 | 0 | 0 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2012 | Q4 | Q4 - 2012 | 881968 | 787068 | 94900 | 777609 | 727454 | 50155 | 882908 | 788008 | 94900 | 5133770 | 40491 | 5093279 | 4931044 | 40454 | 4890589 | 5133770 | 40491 | 5093279 | 20000 | 20000 | 0 | 20179 | 20179 | 0 | 20179 | 20179 | 0 | 393000 | 0 | 393000 | 241981 | 0 | 241981 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 572634 | 572634 | 0 | 572634 | 572634 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 60000 | 60000 | 0 | 289400 | 289400 | 0 | 342583 | 342583 | 0 | 342583 | 342583 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 19879 | 19879 | 0 | 19879 | 19879 | 0 | 7234820 | 1626641 | 5608179 | 6948259 | 1738533 | 5209725 | 7451953 | 1843774 | 5608179 | 7234820 | 1626641 | 5608179 | 6948259 | 1738533 | 5209725 | 7451953 | 1843774 | 5608179 | 0 | 263 | Silver Star Telephone Company, INC.
NT10BIX5570078 | INF | 2013 | Q1 | Q1 - 2013 | 905679 | 787068 | 118611 | 845901 | 727290 | 118611 | 845901 | 727290 | 118611 | 5145213 | 40491 | 5104722 | 5142252 | 37530 | 5104722 | 5142252 | 37530 | 5104722 | 20000 | 20000 | 0 | 20294 | 20294 | 0 | 20294 | 20294 | 0 | 357846 | 0 | 357846 | 357846 | 0 | 357846 | 357846 | 0 | 357846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 566792 | 566792 | 0 | 566792 | 566792 | 0 | 60000 | 60000 | 0 | 15649 | 15649 | 0 | 15649 | 15649 | 0 | 289400 | 289400 | 0 | 329104 | 329104 | 0 | 329104 | 329104 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 18633 | 18633 | 0 | 18633 | 18633 | 0 | 7234820 | 1626641 | 5608179 | 7323471 | 1715292 | 5608179 | 7323471 | 1715292 | 5608179 | 7234820 | 1626641 | 5608179 | 7323471 | 1715292 | 5608179 | 7323471 | 1715292 | 5608179 | 0 | 66678 | Silver Star Telephone Company, INC.
NT10BIX5570079 | INF | 2010 | Q4 | Q4 - 2010 | 2320000 | 2320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6827555 | 0 | 6827555 | 0 | 0 | 0 | 624867 | 0 | 624867 | 612580 | 612580 | 0 | 91000 | 91000 | 0 | 160000 | 160000 | 0 | 205611 | 100000 | 105611 | 0 | 0 | 0 | 82242 | 82242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 312069 | 871015 | 78420 | 23526 | 54894 | 181741 | 72413 | 109328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 169420 | 114526 | 54894 | 1048850 | 314655 | 734195 | 11148830 | 3344649 | 7804181 | 169420 | 114526 | 54894 | 1048850 | 314655 | 734195 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2011 | Q1 | Q1 - 2011 | 2320000 | 2320000 | 0 | 4490 | 4490 | 0 | 184490 | 184490 | 0 | 6827555 | 0 | 6827555 | 0 | 0 | 0 | 530000 | 0 | 530000 | 612580 | 612580 | 0 | 61546 | 61546 | 0 | 94546 | 94546 | 0 | 205611 | 100000 | 105611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 312069 | 871015 | 314801 | 48215 | 266586 | 465647 | 103369 | 362278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 380837 | 114251 | 266586 | 1274683 | 382405 | 892278 | 11148830 | 3344649 | 7804181 | 380837 | 114251 | 266586 | 1274683 | 382405 | 892278 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 790499 | 0 | 790499 | 1947642 | 0 | 1947642 | 416498 | 309498 | 107000 | 90834 | 90834 | 0 | 120834 | 120834 | 0 | 2516082 | 2516082 | 0 | 444554 | 444554 | 0 | 993200 | 993200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 458540 | 0 | 458540 | 651397 | 0 | 651397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 1784427 | 535388 | 1249039 | 3713073 | 1114034 | 2599039 | 11148830 | 3344649 | 7804181 | 1784427 | 535388 | 1249039 | 3713073 | 1114034 | 2599039 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 1920575 | 0 | 1920575 | 3220575 | 0 | 3220575 | 416498 | 309498 | 107000 | 119139 | 119139 | 0 | 148139 | 148138 | 0 | 2516082 | 2516082 | 0 | 694424 | 694424 | 0 | 894424 | 894424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 696848 | 0 | 696848 | 896848 | 0 | 896848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 3430986 | 813563 | 2617423 | 5159986 | 1042562 | 4117423 | 11148830 | 3344649 | 7804181 | 3430986 | 813563 | 2617423 | 5159986 | 1042562 | 4117423 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 2902949 | 0 | 2902949 | 4251109 | 0 | 4251109 | 416498 | 309498 | 107000 | 155244 | 155244 | 0 | 191350 | 191350 | 0 | 2516082 | 2516082 | 0 | 817299 | 817299 | 0 | 2043000 | 2043000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 778220 | 0 | 778220 | 962060 | 0 | 962060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 4653712 | 972543 | 3681169 | 7447519 | 2234350 | 5213169 | 11148830 | 3344649 | 7804181 | 4653712 | 972543 | 3681169 | 7447519 | 2234350 | 5213169 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 4163243 | 0 | 4163243 | 5263243 | 0 | 5263243 | 416498 | 309498 | 107000 | 202937 | 202937 | 0 | 238937 | 238937 | 0 | 2516082 | 2516082 | 0 | 2410835 | 2410835 | 0 | 2410835 | 2410835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 829223 | 0 | 829223 | 894223 | 0 | 894223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 7606238 | 2613772 | 4992466 | 8807238 | 2649772 | 6157466 | 11148830 | 3344649 | 7804181 | 7606238 | 2613772 | 4992466 | 8807238 | 2649772 | 6157466 | 0 | 0 | Clackamas, County of
NT10BIX5570079 | INF | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 5097328 | 0 | 5097328 | 6463243 | 0 | 6463243 | 416498 | 309498 | 107000 | 298412 | 250989 | 47423 | 328412 | 265989 | 62423 | 2516082 | 2516082 | 0 | 2568309 | 2568309 | 0 | 2568309 | 2568309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 884137 | 0 | 884137 | 964223 | 0 | 964223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 8848186 | 2819298 | 6028888 | 10324187 | 2834298 | 7489889 | 11148830 | 3344649 | 7804181 | 8848186 | 2819298 | 6028888 | 10324187 | 2834298 | 7489889 | 0 | 3750 | Clackamas, County of
NT10BIX5570079 | INF | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 5889849 | 80911 | 5808938 | 6739849 | 114411 | 6625438 | 416498 | 309498 | 107000 | 347309 | 286486 | 60823 | 399309 | 338486 | 60823 | 2516082 | 2516082 | 0 | 2568309 | 2568309 | 0 | 2568309 | 2568309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 898658 | 0 | 898658 | 918674 | 0 | 918674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 9704125 | 2935706 | 6768419 | 10626141 | 3021206 | 7604935 | 11148830 | 3344649 | 7804181 | 9704125 | 2935706 | 6768419 | 10626141 | 3021206 | 7604935 | 0 | 3750 | Clackamas, County of
NT10BIX5570079 | INF | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 6497985 | 150000 | 6347985 | 6847985 | 262000 | 6585985 | 416498 | 309498 | 107000 | 347309 | 286486 | 60823 | 361461 | 300638 | 60823 | 2516082 | 2516082 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 914909 | 0 | 914909 | 926974 | 0 | 926974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 10419841 | 3096124 | 7323717 | 10796058 | 3222276 | 7573782 | 11148830 | 3344649 | 7804181 | 10419841 | 3096124 | 7323717 | 10796058 | 3222276 | 7573782 | 0 | 30000 | Clackamas, County of
NT10BIX5570079 | INF | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 6703231 | 189134 | 6514097 | 7033166 | 519069 | 6514097 | 416498 | 309498 | 107000 | 366091 | 305267 | 60823 | 416498 | 309498 | 107000 | 2516082 | 2516082 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 925409 | 0 | 925409 | 1183084 | 0 | 1183084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 10654369 | 3154039 | 7500329 | 11292386 | 3488205 | 7804181 | 11148830 | 3344649 | 7804181 | 10654369 | 3154039 | 7500329 | 11292386 | 3488205 | 7804181 | 0 | 82250 | Clackamas, County of
NT10BIX5570079 | INF | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238804 | 519069 | 6719735 | 6870000 | 355903 | 6514097 | 7238804 | 519069 | 6719735 | 439093 | 309498 | 129595 | 370321 | 309498 | 60823 | 439093 | 309498 | 129595 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954851 | 0 | 954851 | 952085 | 0 | 952085 | 954851 | 0 | 954851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11292386 | 3488205 | 7804181 | 10852044 | 3325039 | 7527005 | 11292386 | 3488205 | 7804181 | 11292386 | 3488205 | 7804181 | 10852044 | 3325039 | 7527005 | 11292386 | 3488205 | 7804181 | 96750 | 123750 | Clackamas, County of
NT10BIX5570079 | INF | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238804 | 519069 | 6719735 | 7244288 | 521787 | 6722501 | 7244288 | 521787 | 6722501 | 439093 | 309498 | 129595 | 636295 | 506700 | 129595 | 636295 | 506700 | 129595 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954851 | 0 | 954851 | 952085 | 0 | 952085 | 952085 | 0 | 952085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11292386 | 3488205 | 7804181 | 11492306 | 3688125 | 7804181 | 11492306 | 3688125 | 7804181 | 11292386 | 3488205 | 7804181 | 11492306 | 3688125 | 7804181 | 11492306 | 3688125 | 7804181 | 0 | 199920 | Clackamas, County of
NT10BIX5570080 | INF | 2010 | Q4 | Q4 - 2010 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 0 | 0 | 0 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 405000 | 0 | 0 | 0 | 0 | 122000 | 122000 | 0 | 2303662 | 88600 | 2215062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 0 | 0 | 0 | 94000 | 94000 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 0 | 0 | 0 | 6501995 | 1317548 | 5184447 | 0 | 0 | 0 | 216000 | 216000 | 0 | 6501995 | 1317548 | 5184447 | 0 | 0 | 0 | 216000 | 216000 | 0 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2011 | Q1 | Q1 - 2011 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 50000 | 0 | 50000 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 405000 | 0 | 218014 | 218014 | 0 | 327031 | 327031 | 0 | 2303662 | 88600 | 2215062 | 0 | 0 | 0 | 157600 | 0 | 157600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 10645 | 0 | 10645 | 74237 | 0 | 74237 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 70250 | 0 | 70250 | 6501995 | 1317548 | 5184447 | 228659 | 218014 | 10645 | 717035 | 334531 | 382504 | 6501995 | 1317548 | 5184447 | 228659 | 218014 | 10645 | 717035 | 334531 | 382504 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2011 | Q2 | Q2 - 2011 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 0 | 0 | 0 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 37500 | 37500 | 0 | 405000 | 405000 | 0 | 308967 | 308967 | 0 | 496830 | 496830 | 0 | 2303662 | 88600 | 2215062 | 2500 | 0 | 2500 | 94786 | 0 | 94786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 82496 | 0 | 82496 | 30417 | 0 | 30417 | 0 | 0 | 0 | 24334 | 0 | 24334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 63112 | 0 | 63112 | 6501995 | 1317548 | 5184447 | 329042 | 308967 | 20075 | 806558 | 541830 | 264728 | 6501995 | 1317548 | 5184447 | 329042 | 308967 | 20075 | 806558 | 541830 | 264728 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2011 | Q3 | Q3 - 2011 | 3406069 | 1317548 | 2088521 | 0 | 0 | 0 | 2352018 | 1419203 | 932815 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1145000 | 0 | 1145000 | 340570 | 0 | 340570 | 468070 | 0 | 468070 | 1054911 | 0 | 1054911 | 2500 | 0 | 2500 | 487500 | 0 | 487500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 36838 | 0 | 36838 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 82112 | 0 | 82112 | 6501995 | 1317548 | 5184447 | 360645 | 0 | 360645 | 3456955 | 1419203 | 2037752 | 6501995 | 1317548 | 5184447 | 360645 | 0 | 360645 | 3456955 | 1419203 | 2037752 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2011 | Q4 | Q4 - 2011 | 3406069 | 1317548 | 2088521 | 2079605 | 1317548 | 762057 | 2194972 | 1317548 | 877424 | 150000 | 0 | 150000 | 0 | 0 | 0 | 37500 | 0 | 37500 | 1145000 | 0 | 1145000 | 435796 | 0 | 435796 | 563296 | 0 | 563296 | 1054911 | 0 | 1054911 | 103751 | 0 | 103751 | 567411 | 0 | 567411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 36838 | 0 | 36838 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 86522 | 0 | 86522 | 6501995 | 1317548 | 5184447 | 2636727 | 1317548 | 1319179 | 3524456 | 1317548 | 2206908 | 6501995 | 1317548 | 5184447 | 2636727 | 1317548 | 1319179 | 3524456 | 1317548 | 2206908 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2012 | Q1 | Q1 - 2012 | 3406069 | 1317548 | 2088521 | 2104746 | 1317548 | 787198 | 2671476 | 1317548 | 1353928 | 150000 | 0 | 150000 | 0 | 0 | 0 | 12500 | 0 | 12500 | 1145000 | 0 | 1145000 | 460796 | 0 | 460796 | 525796 | 0 | 525796 | 1054911 | 0 | 1054911 | 103751 | 0 | 103751 | 411920 | 0 | 411920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 18558 | 0 | 18558 | 89150 | 0 | 89150 | 30417 | 0 | 30417 | 17575 | 0 | 17575 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 256026 | 0 | 256026 | 6501995 | 1317548 | 5184447 | 2705426 | 1317548 | 1387878 | 4004785 | 1317548 | 2687237 | 6501995 | 1317548 | 5184447 | 2705426 | 1317548 | 1387878 | 4004785 | 1317548 | 2687237 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2012 | Q2 | Q2 - 2012 | 3406069 | 1317548 | 2088521 | 2567029 | 1317548 | 1249481 | 3129769 | 1317548 | 1812221 | 150000 | 0 | 150000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 1145000 | 0 | 1145000 | 576496 | 0 | 576496 | 635896 | 0 | 635896 | 1054911 | 0 | 1054911 | 382169 | 0 | 382169 | 941559 | 0 | 941559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 52979 | 0 | 52979 | 81890 | 0 | 81890 | 30417 | 0 | 30417 | 18375 | 0 | 18375 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 12269 | 0 | 12269 | 204538 | 0 | 204538 | 6501995 | 1317548 | 5184447 | 3609317 | 1317548 | 2291769 | 5068647 | 1317548 | 3751099 | 6501995 | 1317548 | 5184447 | 3609317 | 1317548 | 2291769 | 5068647 | 1317548 | 3751099 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2012 | Q3 | Q3 - 2012 | 3406069 | 1317548 | 2088521 | 3021292 | 1317548 | 1703744 | 3379696 | 1317548 | 2062148 | 150000 | 0 | 150000 | 19162 | 0 | 19162 | 49662 | 0 | 49662 | 1145000 | 0 | 1145000 | 623496 | 0 | 623496 | 678496 | 0 | 678496 | 1054911 | 0 | 1054911 | 382169 | 0 | 382169 | 980299 | 0 | 980299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 97066 | 0 | 97066 | 109566 | 0 | 109566 | 30417 | 0 | 30417 | 18375 | 0 | 18375 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 62805 | 0 | 62805 | 165383 | 0 | 165383 | 6501995 | 1317548 | 5184447 | 4224365 | 1317548 | 2906817 | 5395597 | 1317548 | 4078049 | 6501995 | 1317548 | 5184447 | 4224365 | 1317548 | 2906817 | 5395597 | 1317548 | 4078049 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2012 | Q4 | Q4 - 2012 | 3406069 | 1317548 | 2088521 | 3032142 | 1317548 | 1714594 | 3531355 | 1317548 | 2213807 | 150000 | 0 | 150000 | 56435 | 0 | 56435 | 56435 | 0 | 56435 | 1145000 | 0 | 1145000 | 683496 | 0 | 683496 | 713496 | 0 | 713496 | 1054911 | 0 | 1054911 | 400639 | 0 | 400639 | 960604 | 0 | 960604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 114269 | 0 | 114269 | 160534 | 0 | 160534 | 30417 | 0 | 30417 | 23495 | 0 | 23495 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 74002 | 0 | 74002 | 227696 | 0 | 227696 | 6501995 | 1317548 | 5184447 | 4384478 | 1317548 | 3066930 | 5675115 | 1317548 | 4357567 | 6501995 | 1317548 | 5184447 | 4384478 | 1317548 | 3066930 | 5675115 | 1317548 | 4357567 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2013 | Q1 | Q1 - 2013 | 3406069 | 1317548 | 2088521 | 3151629 | 1317548 | 1834081 | 3666784 | 1317548 | 2349236 | 150000 | 0 | 150000 | 56435 | 0 | 56435 | 56435 | 0 | 56435 | 1145000 | 0 | 1145000 | 714296 | 0 | 714296 | 760376 | 0 | 760376 | 1054911 | 0 | 1054911 | 405766 | 0 | 405766 | 1147483 | 0 | 1147483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 128160 | 0 | 128160 | 158160 | 0 | 158160 | 30417 | 0 | 30417 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 111375 | 0 | 111375 | 241169 | 0 | 241169 | 6501995 | 1317548 | 5184447 | 4592356 | 1317548 | 3274808 | 6055102 | 1317548 | 4737554 | 6501995 | 1317548 | 5184447 | 4592356 | 1317548 | 3274808 | 6055102 | 1317548 | 4737554 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2013 | Q2 | Q2 - 2013 | 3790131 | 1317548 | 2472583 | 3272085 | 1317548 | 1954537 | 3489270 | 1317548 | 2171722 | 56436 | 0 | 56436 | 56435 | 0 | 56435 | 59920 | 0 | 59920 | 912140 | 0 | 912140 | 759296 | 0 | 759296 | 801796 | 0 | 801796 | 1176793 | 0 | 1176793 | 1132051 | 0 | 1132051 | 1293838 | 0 | 1293838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191500 | 0 | 191500 | 150073 | 0 | 150073 | 170073 | 0 | 170073 | 24995 | 0 | 24995 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 154465 | 0 | 154465 | 237373 | 0 | 237373 | 6501995 | 1317548 | 5184447 | 5549100 | 1317548 | 4231552 | 6076965 | 1317548 | 4759417 | 6501995 | 1317548 | 5184447 | 5549100 | 1317548 | 4231552 | 6076965 | 1317548 | 4759417 | 0 | 0 | ONWAV INC.
NT10BIX5570080 | INF | 2013 | Q3 | Q3 - 2013 | 3790131 | 1317548 | 2472583 | 3814450 | 2496902 | 1957347 | 3814450 | 1317548 | 2496902 | 56436 | 0 | 56436 | 60477 | 0 | 60477 | 60477 | 0 | 60477 | 912140 | 0 | 912140 | 877305 | 0 | 877305 | 877305 | 0 | 877305 | 1176793 | 0 | 1176793 | 1257390 | 0 | 1257390 | 1257390 | 0 | 1257390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191500 | 0 | 191500 | 191709 | 0 | 191709 | 191709 | 0 | 191709 | 24995 | 0 | 24995 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 275969 | 0 | 275969 | 275969 | 0 | 275969 | 6501995 | 1317548 | 5184447 | 6501995 | 2496902 | 4644892 | 6501995 | 1317548 | 5184447 | 6501995 | 1317548 | 5184447 | 6501995 | 2496902 | 4644892 | 6501995 | 1317548 | 5184447 | 0 | 0 | ONWAV INC.
NT10BIX5570081 | INF | 2010 | Q4 | Q4 - 2010 | 13369978 | 7498090 | 5871888 | 0 | 0 | 0 | 1060342 | 486360 | 573982 | 8139804 | 0 | 8139804 | 8716 | 0 | 8716 | 340802 | 0 | 340802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 36031 | 0 | 36031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77146 | 2 | 62148 | 62148 | 0 | 77148 | 77148 | 0 | 25033000 | 7575236 | 17457764 | 70864 | 62148 | 8716 | 1514323 | 563508 | 950815 | 25033000 | 7575236 | 17457764 | 70864 | 62148 | 8716 | 1514323 | 563508 | 950815 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2011 | Q1 | Q1 - 2011 | 13369978 | 7498090 | 5871888 | 0 | 0 | 0 | 5770644 | 3465910 | 2304734 | 8139804 | 0 | 8139804 | 3291 | 0 | 3291 | 1190793 | 15000 | 1175793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 52500 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77146 | 2 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 117939 | 62148 | 55791 | 7023585 | 3543058 | 3480527 | 25033000 | 7575236 | 17457764 | 117939 | 62148 | 55791 | 7023585 | 3543058 | 3480527 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2011 | Q2 | Q2 - 2011 | 13369978 | 7498088 | 5871890 | 907304 | 317971 | 589333 | 5448463 | 3480910 | 1967553 | 8139804 | 0 | 8139804 | 199511 | 0 | 199511 | 3407469 | 0 | 3407469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 48143 | 0 | 48143 | 80000 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 343181 | 0 | 343181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 1217106 | 380119 | 836987 | 9341261 | 3543058 | 5798203 | 25033000 | 7575236 | 17457764 | 1217106 | 380119 | 836987 | 9341261 | 3543058 | 5798203 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2011 | Q3 | Q3 - 2011 | 13369978 | 7498088 | 5871890 | 1976881 | 317971 | 1658910 | 7942067 | 5468830 | 2473237 | 8139804 | 0 | 8139804 | 366835 | 0 | 366835 | 2315543 | 0 | 2315543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 85398 | 0 | 85398 | 215000 | 0 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 2491262 | 380119 | 2111143 | 10534758 | 5530978 | 5003780 | 25033000 | 7575236 | 17457764 | 2491262 | 380119 | 2111143 | 10534758 | 5530978 | 5003780 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2011 | Q4 | Q4 - 2011 | 13369978 | 7498088 | 5871890 | 5906013 | 4160950 | 1745063 | 8200000 | 4300000 | 3900000 | 8139804 | 0 | 8139804 | 1045071 | 0 | 1045071 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 919789 | 0 | 919789 | 1115000 | 0 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 7933021 | 4223098 | 3709923 | 10877148 | 4362148 | 6515000 | 25033000 | 7575236 | 17457764 | 7933021 | 4223098 | 3709923 | 10877148 | 4362148 | 6515000 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2012 | Q1 | Q1 - 2012 | 13369978 | 7498088 | 5871890 | 7150443 | 4160951 | 2989492 | 9550000 | 5150000 | 4400000 | 8139804 | 0 | 8139804 | 2008486 | 0 | 2008486 | 3450000 | 0 | 3450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 959318 | 0 | 959318 | 1150000 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 10180395 | 4223099 | 5957296 | 14212148 | 5212148 | 9000000 | 25033000 | 7575236 | 17457764 | 10180395 | 4223099 | 5957296 | 14212148 | 5212148 | 9000000 | 0 | 0 | District of Columbia Government
NT10BIX5570081 | INF | 2012 | Q2 | Q2 - 2012 | 13369978 | 7498088 | 5871890 | 8572864 | 4161304 | 4411560 | 10485000 | 5010000 | 5475000 | 8139804 | 0 | 8139804 | 4158058 | 0 | 4158058 | 5000000 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 995425 | 0 | 995425 | 1200000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 13788495 | 4223452 | 9565043 | 16747148 | 5072148 | 11675000 | 25033000 | 7575236 | 17457764 | 13788495 | 4223452 | 9565043 | 16747148 | 5072148 | 11675000 | 0 | 128118 | District of Columbia Government
NT10BIX5570081 | INF | 2012 | Q3 | Q3 - 2012 | 13369978 | 7498088 | 5871890 | 9160711 | 4161304 | 4999407 | 11262852 | 5637852 | 5625000 | 8139804 | 0 | 8139804 | 5136804 | 0 | 5136804 | 5700000 | 0 | 5700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1024213 | 0 | 1024213 | 1175000 | 0 | 1175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 15383876 | 4223452 | 11160424 | 18200000 | 5700000 | 12500000 | 25033000 | 7575236 | 17457764 | 15383876 | 4223452 | 11160424 | 18200000 | 5700000 | 12500000 | 0 | 277264 | District of Columbia Government
NT10BIX5570081 | INF | 2012 | Q4 | Q4 - 2012 | 13369978 | 7498088 | 5871890 | 11586642 | 5180064 | 6406578 | 13247852 | 6447852 | 6800000 | 8139804 | 0 | 8139804 | 6092310 | 0 | 6092310 | 6600000 | 0 | 6600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1045518 | 0 | 1045518 | 1450000 | 0 | 1450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 18786618 | 5242212 | 13544406 | 21510000 | 6510000 | 15000000 | 25033000 | 7575236 | 17457764 | 18786618 | 5242212 | 13544406 | 21510000 | 6510000 | 15000000 | 0 | 360608 | District of Columbia Government
NT10BIX5570081 | INF | 2013 | Q1 | Q1 - 2013 | 13369978 | 7498088 | 5871890 | 12313172 | 5827245 | 6485927 | 13369978 | 6498088 | 6871890 | 8139804 | 0 | 8139804 | 6683912 | 0 | 6683912 | 7185874 | 0 | 7185874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1072633 | 0 | 1072633 | 1200000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 77148 | 77148 | 0 | 25033000 | 7575236 | 17457764 | 20131865 | 5889393 | 14242472 | 21833000 | 6575236 | 15257764 | 25033000 | 7575236 | 17457764 | 20131865 | 5889393 | 14242472 | 21833000 | 6575236 | 15257764 | 0 | 371938 | District of Columbia Government
NT10BIX5570081 | INF | 2013 | Q2 | Q2 - 2013 | 13369978 | 7498088 | 5871890 | 13107863 | 6618855 | 6489008 | 15180020 | 7513088 | 7666932 | 8139804 | 0 | 8139804 | 7384980 | 0 | 7384980 | 8366822 | 0 | 8366822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1094813 | 0 | 1094813 | 1424010 | 0 | 1424010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 21649804 | 6681003 | 14968801 | 25033000 | 7575236 | 17457764 | 25033000 | 7575236 | 17457764 | 21649804 | 6681003 | 14968801 | 25033000 | 7575236 | 17457764 | 0 | 408484 | District of Columbia Government
NT10BIX5570081 | INF | 2013 | Q3 | Q3 - 2013 | 13628980 | 6815232 | 6813748 | 14269362 | 6322015 | 7947347 | 14269362 | 6322015 | 7947347 | 9710851 | 697856 | 9012995 | 9137462 | 1191072 | 7946390 | 9137462 | 1191072 | 7946390 | 133678 | 0 | 133678 | 66684 | 0 | 66684 | 66684 | 0 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497343 | 0 | 1497343 | 1497343 | 0 | 1497343 | 1497343 | 0 | 1497343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 25032999 | 7575235 | 17457764 | 25032999 | 7575235 | 17457764 | 25033000 | 7575236 | 17457764 | 25032999 | 7575235 | 17457764 | 25032999 | 7575235 | 17457764 | 449197 | 449197 | District of Columbia Government
NT10BIX5570082 | INF | 2010 | Q3 | Q3 - 2010 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 28927 | 0 | 28927 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 0 | 0 | 0 | 4855407 | 15000 | 4840407 | 84350 | 0 | 84350 | 414474 | 16153 | 398321 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 0 | 0 | 0 | 34020 | 10151 | 23868 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 175296 | 0 | 175296 | 273296 | 29400 | 243896 | 65847892 | 21366900 | 44480992 | 259646 | 0 | 259646 | 750717 | 55704 | 695012 | 65847892 | 21366900 | 44480992 | 259646 | 0 | 259646 | 750717 | 55704 | 695012 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2010 | Q4 | Q4 - 2010 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 1681670 | 680000 | 1001670 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 1202175 | 70000 | 1132175 | 4855407 | 15000 | 4840407 | 720432 | 0 | 720432 | 1033710 | 29400 | 1004310 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 1097 | 0 | 1097 | 148963 | 48676 | 100288 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 0 | 0 | 0 | 0 | 0 | 0 | 65847892 | 21366900 | 44480992 | 721529 | 0 | 721529 | 4066518 | 828076 | 3238443 | 65847892 | 21366900 | 44480992 | 721529 | 0 | 721529 | 4066518 | 828076 | 3238443 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2011 | Q1 | Q1 - 2011 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 449772 | 256889 | 192883 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 0 | 0 | 0 | 4855407 | 15000 | 4840407 | 1042581 | 0 | 1042581 | 1487059 | 4476 | 1482583 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 118999 | 46566 | 72433 | 436109 | 144823 | 291286 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 1691494 | 521416 | 1170078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 0 | 0 | 0 | 0 | 0 | 0 | 65847892 | 21366900 | 44480992 | 1161580 | 46566 | 1115014 | 4064434 | 927604 | 3136830 | 65847892 | 21366900 | 44480992 | 1161580 | 46566 | 1115014 | 4064434 | 927604 | 3136830 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2011 | Q2 | Q2 - 2011 | 18481355 | 2321328 | 16160027 | 0 | 0 | 0 | 449772 | 252360 | 197412 | 30815467 | 18555862 | 12259605 | 0 | 0 | 0 | 27900 | 8370 | 19530 | 5386259 | 87018 | 5299241 | 1644827 | 20000 | 1624827 | 1785347 | 33403 | 1751944 | 72000 | 21485 | 50515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 282874 | 4509735 | 698824 | 467493 | 231331 | 2057577 | 1341176 | 716401 | 176530 | 0 | 176530 | 110118 | 11956 | 98162 | 143430 | 16360 | 127070 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 5298403 | 0 | 5298403 | 2396829 | 596829 | 1800000 | 4022546 | 596829 | 3425717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671330 | 52151 | 619179 | 29400 | 29400 | 0 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 4879998 | 1125678 | 3754320 | 8584572 | 2277898 | 6306674 | 65847892 | 21366900 | 44480992 | 4879998 | 1125678 | 3754320 | 8584572 | 2277898 | 6306674 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2011 | Q3 | Q3 - 2011 | 23073047 | 15918722 | 7154325 | 2204406 | 1808956 | 395450 | 5768974 | 3822021 | 1946953 | 23982324 | 2555718 | 21426606 | 232255 | 0 | 232255 | 297700 | 65445 | 232255 | 5210962 | 87543 | 5123419 | 1910696 | 40000 | 1870696 | 2229874 | 50054 | 2179820 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 2332251 | 265942 | 2066309 | 3281906 | 1050821 | 2231085 | 176530 | 18860 | 157670 | 128910 | 13960 | 114950 | 163290 | 17860 | 145430 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 1970100 | 0 | 1970100 | 6763964 | 0 | 6763964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 98000 | 29400 | 68600 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 8876618 | 2158258 | 6718360 | 18603708 | 5035601 | 13568107 | 65847892 | 21366900 | 44480992 | 8876618 | 2158258 | 6718360 | 18603708 | 5035601 | 13568107 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2011 | Q4 | Q4 - 2011 | 23073047 | 15918722 | 7154325 | 5540093 | 4628460 | 911634 | 13206914 | 11085175 | 2121739 | 23982324 | 2555718 | 21426606 | 1857894 | 0 | 1857894 | 3321893 | 56385 | 3265508 | 5210962 | 87543 | 5123419 | 2247877 | 50058 | 2197819 | 2580385 | 60356 | 2520029 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 72000 | 21600 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 4280659 | 274478 | 4006180 | 4666590 | 375682 | 4290907 | 176530 | 18860 | 157670 | 136110 | 21160 | 114950 | 161470 | 21160 | 140310 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15394 | 35919 | 7359864 | 2061461 | 5298403 | 3049593 | 0 | 3049593 | 5581505 | 0 | 5581505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 98000 | 29400 | 68600 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 17210226 | 5003556 | 12206670 | 29740070 | 11665152 | 18074917 | 65847892 | 21366900 | 44480992 | 17210226 | 5003556 | 12206670 | 29740070 | 11665152 | 18074917 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2012 | Q1 | Q1 - 2012 | 23073047 | 15918722 | 7154325 | 13269067 | 11290281 | 1978785 | 17796160 | 14690739 | 3105420 | 23982324 | 2555718 | 21426606 | 4557801 | 167403 | 4390398 | 9693402 | 1103120 | 8590282 | 5210962 | 87543 | 5123419 | 2608775 | 75130 | 2533645 | 2978328 | 81525 | 2896803 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5042169 | 376807 | 4665362 | 5375125 | 431068 | 4944058 | 176530 | 18860 | 157670 | 150630 | 23560 | 127070 | 163870 | 24560 | 139310 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 5870250 | 0 | 5870250 | 9463623 | 2061461 | 7402162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 116454 | 29400 | 87054 | 254966 | 68600 | 186366 | 65847892 | 21366900 | 44480992 | 31619965 | 11963881 | 19656083 | 45797474 | 18482555 | 27314919 | 65847892 | 21366900 | 44480992 | 31619965 | 11963881 | 19656083 | 45797474 | 18482555 | 27314919 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2012 | Q2 | Q2 - 2012 | 23073047 | 15918723 | 7154324 | 15923486 | 13175137 | 2748349 | 17095177 | 13555274 | 3539904 | 23982324 | 2555718 | 21426606 | 7301695 | 458804 | 6842891 | 12530658 | 1393954 | 11136704 | 5210963 | 87543 | 5123420 | 2942507 | 79695 | 2862812 | 3357628 | 101716 | 3255912 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5121067 | 394864 | 4726203 | 5684118 | 483518 | 5200600 | 176530 | 18860 | 157670 | 143430 | 16360 | 127070 | 154463 | 17193 | 137270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 9087915 | 2061461 | 7026454 | 9403967 | 2061461 | 7342506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 124054 | 29400 | 94654 | 480126 | 106007 | 374119 | 65847893 | 21366901 | 44480992 | 40648973 | 16217021 | 24431952 | 48778137 | 17740605 | 31037533 | 65847893 | 21366901 | 44480992 | 40648973 | 16217021 | 24431952 | 48778137 | 17740605 | 31037533 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2012 | Q3 | Q3 - 2012 | 23073047 | 15918723 | 7154324 | 17148024 | 13508453 | 3639572 | 18088071 | 13839705 | 4248367 | 23982324 | 2555718 | 21426606 | 10143763 | 883833 | 9259930 | 13708129 | 1373196 | 12334933 | 5210962 | 87542 | 5123420 | 3309472 | 104587 | 3204885 | 3682223 | 115579 | 3566644 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21485 | 50515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5439490 | 466617 | 4972872 | 5660570 | 519219 | 5141350 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 177730 | 16360 | 161370 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15310 | 36003 | 7359864 | 2061461 | 5298403 | 10570197 | 2061461 | 8508736 | 10570197 | 2061461 | 8508736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 348137 | 29400 | 318737 | 447449 | 29400 | 418049 | 65847892 | 21366900 | 44480992 | 47108532 | 17072011 | 30036521 | 52457682 | 17991715 | 34465967 | 65847892 | 21366900 | 44480992 | 47108532 | 17072011 | 30036521 | 52457682 | 17991715 | 34465967 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2012 | Q4 | Q4 - 2012 | 23073046 | 15918722 | 7154324 | 17631494 | 13687857 | 3943637 | 19064908 | 14326764 | 4738144 | 23982324 | 2555718 | 21426606 | 12772279 | 1273163 | 11499116 | 14991576 | 1621354 | 13370222 | 5210963 | 87543 | 5123420 | 3614318 | 114079 | 3500239 | 4567733 | 139410 | 4428323 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 6061830 | 503917 | 5557913 | 6145220 | 533199 | 5612021 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 144630 | 16360 | 128270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15310 | 36003 | 7359864 | 2061461 | 5298403 | 11570433 | 2061461 | 9508972 | 11570433 | 2061461 | 9508972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 624097 | 29400 | 594697 | 723409 | 29400 | 694009 | 65847892 | 21366900 | 44480992 | 52423900 | 17687537 | 34736363 | 57264041 | 18744558 | 38519483 | 65847892 | 21366900 | 44480992 | 52423900 | 17687537 | 34736363 | 57264041 | 18744558 | 38519483 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2013 | Q1 | Q1 - 2013 | 23073046 | 15918722 | 7154324 | 18155232 | 13896388 | 4258844 | 20222746 | 14398004 | 5824742 | 23982324 | 2555718 | 21426606 | 13957788 | 1523602 | 12434186 | 19084291 | 2326339 | 16757952 | 5210963 | 87543 | 5123420 | 3940125 | 116410 | 3823715 | 4257153 | 123763 | 4133390 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 6157188 | 532533 | 5624655 | 6317545 | 568765 | 5748780 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 144630 | 16360 | 128270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 62500 | 18650 | 43850 | 7359864 | 2061461 | 5298403 | 11570433 | 2061461 | 9508972 | 11570433 | 2061461 | 9508972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 65847892 | 21366900 | 44480992 | 54554312 | 18177454 | 36376858 | 62288214 | 19544042 | 42744172 | 65847892 | 21366900 | 44480992 | 54554312 | 18177454 | 36376858 | 62288214 | 19544042 | 42744172 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2013 | Q2 | Q2 - 2013 | 16989927 | 10903618 | 6086309 | 17270483 | 12599706 | 4670777 | 16571750 | 10776531 | 5795219 | 20337047 | 2572036 | 17765011 | 16366740 | 2009150 | 14357590 | 19481902 | 2521478 | 16960424 | 4933387 | 341553 | 4591834 | 4247511 | 119227 | 4128284 | 4691752 | 337016 | 4354736 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6396494 | 531521 | 5864973 | 6546007 | 550979 | 5995028 | 176530 | 17140 | 159390 | 145470 | 16360 | 129110 | 176530 | 16360 | 160170 | 125000 | 37300 | 87700 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 13319536 | 3810564 | 9508972 | 13565341 | 3805564 | 9759777 | 13565341 | 3805564 | 9759777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 62750571 | 18269579 | 44480992 | 58620955 | 19112228 | 39508727 | 61692198 | 18047628 | 43644570 | 62750571 | 18269579 | 44480992 | 58620955 | 19112228 | 39508727 | 61692198 | 18047628 | 43644570 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2013 | Q3 | Q3 - 2013 | 16989927 | 10903618 | 6086309 | 15824489 | 10695776 | 5128713 | 16975012 | 10943612 | 6031400 | 20337047 | 2572036 | 17765011 | 18658381 | 2362501 | 16295880 | 19689831 | 2534745 | 17155086 | 4933387 | 341553 | 4591834 | 4513194 | 119227 | 4393967 | 4917800 | 351119 | 4566681 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6427161 | 540722 | 5886439 | 6579790 | 557604 | 6022186 | 176530 | 17140 | 159390 | 145470 | 16360 | 129110 | 179234 | 16049 | 163185 | 125000 | 37300 | 87700 | 13633 | 4090 | 9543 | 124343 | 30185 | 94158 | 13319536 | 3810564 | 9508972 | 13565341 | 3805564 | 9759777 | 13565341 | 3805564 | 9759777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 62750571 | 18269579 | 44480992 | 59776585 | 17574940 | 42201645 | 62660267 | 18269578 | 44390689 | 62750571 | 18269579 | 44480992 | 59776585 | 17574940 | 42201645 | 62660267 | 18269578 | 44390689 | 0 | 0 | University System of New Hampshire
NT10BIX5570082 | INF | 2013 | Q4 | Q4 - 2013 | 16989927 | 10903618 | 6086309 | 17141439 | 11028845 | 6112594 | 17141439 | 11028845 | 6112594 | 20337047 | 2572036 | 17765011 | 19143714 | 2435596 | 16708118 | 19143714 | 2435596 | 16708118 | 4933387 | 341553 | 4591834 | 5237362 | 370929 | 4866433 | 5237362 | 370929 | 4866433 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6420020 | 561069 | 5858951 | 6420020 | 561069 | 5858951 | 176530 | 17140 | 159390 | 176520 | 17393 | 159127 | 176520 | 17393 | 159127 | 125000 | 37300 | 87700 | 45436 | 13542 | 31894 | 45436 | 13542 | 31894 | 13319536 | 3810564 | 9508972 | 14001659 | 3805564 | 10196095 | 14001659 | 3805564 | 10196095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 543778 | 29400 | 514378 | 543778 | 29400 | 514378 | 62750571 | 18269579 | 44480992 | 62714747 | 18263638 | 44451109 | 62714747 | 18263638 | 44451109 | 62750571 | 18269579 | 44480992 | 62714747 | 18263638 | 44451109 | 62714747 | 18263638 | 44451109 | 0 | 0 | University System of New Hampshire
NT10BIX5570084 | INF | 2010 | Q4 | Q4 - 2010 | 18648743 | 9853848 | 8794895 | 0 | 0 | 0 | 1320000 | 0 | 1320000 | 1153002 | 0 | 1153002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4597038 | 0 | 4597038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309100 | 0 | 2309100 | 123776 | 0 | 123776 | 685000 | 0 | 685000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789800 | 0 | 789800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71084 | 0 | 71084 | 2704 | 0 | 2704 | 0 | 0 | 0 | 27568767 | 9853848 | 17714919 | 126480 | 0 | 126480 | 2005000 | 0 | 2005000 | 27568767 | 9853848 | 17714919 | 126480 | 0 | 126480 | 2005000 | 0 | 2005000 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2011 | Q1 | Q1 - 2011 | 18648743 | 9853848 | 8794895 | 0 | 0 | 0 | 0 | 0 | 0 | 1153002 | 0 | 1153002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4597038 | 0 | 4597038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309100 | 0 | 2309100 | 289549 | 0 | 289549 | 741719 | 0 | 741719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789800 | 0 | 789800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71084 | 0 | 71084 | 2704 | 0 | 2704 | 2704 | 0 | 2704 | 27568767 | 9853848 | 17714919 | 292253 | 0 | 292253 | 744423 | 0 | 744423 | 27568767 | 9853848 | 17714919 | 292253 | 0 | 292253 | 744423 | 0 | 744423 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2011 | Q2 | Q2 - 2011 | 17079303 | 9355655 | 7723648 | 0 | 0 | 0 | 0 | 0 | 0 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146600 | 0 | 1146600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 512527 | 0 | 512527 | 991069 | 0 | 991069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 2835 | 0 | 2835 | 10782 | 0 | 10782 | 24102285 | 9355655 | 14746630 | 515362 | 0 | 515362 | 1001851 | 0 | 1001851 | 24102285 | 9355655 | 14746630 | 515362 | 0 | 515362 | 1001851 | 0 | 1001851 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2011 | Q3 | Q3 - 2011 | 17079303 | 9355655 | 7723648 | 0 | 0 | 0 | 13091137 | 6871848 | 6219289 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146600 | 0 | 1146600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 954886 | 0 | 954886 | 1368407 | 0 | 1368407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 2835 | 0 | 2835 | 14085 | 0 | 14084 | 24102285 | 9355655 | 14746630 | 957721 | 0 | 957721 | 14473629 | 6871848 | 7601780 | 24102285 | 9355655 | 14746630 | 957721 | 0 | 957721 | 14473629 | 6871848 | 7601780 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2011 | Q4 | Q4 - 2011 | 17079303 | 9355655 | 7723648 | 11695425 | 6871848 | 4823577 | 14255655 | 9355655 | 4900000 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 46025 | 0 | 46025 | 46025 | 0 | 46025 | 1146600 | 0 | 1146600 | 251451 | 0 | 251451 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 1552074 | 0 | 1552074 | 1750000 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 50260 | 0 | 50260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 9071 | 0 | 9071 | 15000 | 0 | 15000 | 24102285 | 9355655 | 14746630 | 13554046 | 6871848 | 6682198 | 16516940 | 9355655 | 7161285 | 24102285 | 9355655 | 14746630 | 13554046 | 6871848 | 6682198 | 16516940 | 9355655 | 7161285 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2012 | Q1 | Q1 - 2012 | 16226313 | 9355655 | 6870658 | 12977831 | 8154254 | 4823577 | 14255655 | 9355655 | 4900000 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 100000 | 0 | 100000 | 85800 | 0 | 85800 | 46025 | 0 | 46025 | 65000 | 0 | 65000 | 1146600 | 0 | 1146600 | 251451 | 0 | 251451 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1552074 | 0 | 1552074 | 1950000 | 0 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 9071 | 0 | 9071 | 25000 | 0 | 25000 | 24102285 | 9355655 | 14746630 | 14836452 | 8154254 | 6682198 | 17095655 | 9355655 | 7740000 | 24102285 | 9355655 | 14746630 | 14836452 | 8154254 | 6682198 | 17095655 | 9355655 | 7740000 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2012 | Q2 | Q2 - 2012 | 16226313 | 9355655 | 6870658 | 14096789 | 8154254 | 5942535 | 14754254 | 8154254 | 6600000 | 3071873 | 0 | 3071873 | 145322 | 0 | 145322 | 745322 | 0 | 745322 | 85800 | 0 | 85800 | 60612 | 0 | 60612 | 70000 | 0 | 70000 | 1146600 | 0 | 1146600 | 531525 | 0 | 531525 | 800000 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1846345 | 0 | 1846345 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 20185 | 0 | 20185 | 45000 | 0 | 45000 | 24102285 | 9355655 | 14746630 | 16700778 | 8154254 | 8546524 | 18514576 | 8154254 | 10360322 | 24102285 | 9355655 | 14746630 | 16700778 | 8154254 | 8546524 | 18514576 | 8154254 | 10360322 | 0 | 0 | Iowa Health System
NT10BIX5570084 | INF | 2012 | Q3 | Q3 - 2012 | 16226313 | 9355655 | 6870658 | 14203968 | 8154254 | 6049714 | 14903968 | 8154254 | 6749714 | 3071873 | 0 | 3071873 | 491929 | 0 | 491929 | 1000000 | 0 | 1000000 | 85800 | 0 | 85800 | 60612 | 0 | 60612 | 80000 | 0 | 80000 | 1146600 | 0 | 1146600 | 539448 | 0 | 539448 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1899817 | 0 | 1899817 | 1980000 | 0 | 1980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 300400 | 0 | 300400 | 380400 | 0 | 380400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 56185 | 0 | 56185 | 75000 | 0 | 75000 | 24102285 | 9355655 | 14746630 | 17552359 | 8154254 | 9398105 | 19419368 | 8154254 | 11265114 | 24102285 | 9355655 | 14746630 | 17552359 | 8154254 | 9398105 | 19419368 | 8154254 | 11265114 | 0 | 25000 | Iowa Health System
NT10BIX5570084 | INF | 2012 | Q4 | Q4 - 2012 | 16226313 | 9355655 | 6870658 | 14785274 | 8154254 | 6631020 | 15870658 | 9000000 | 6870658 | 3071873 | 0 | 3071873 | 1786000 | 0 | 1786000 | 2500000 | 0 | 2500000 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 85800 | 0 | 85800 | 1146600 | 0 | 1146600 | 925000 | 0 | 925000 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2361127 | 0 | 2361127 | 2500000 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 475000 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 101235 | 0 | 101235 | 125000 | 0 | 125000 | 24102285 | 9355655 | 14746630 | 20457281 | 8154254 | 12303027 | 22556458 | 9000000 | 13556458 | 24102285 | 9355655 | 14746630 | 20457281 | 8154254 | 12303027 | 22556458 | 9000000 | 13556458 | 0 | 48000 | Iowa Health System
NT10BIX5570084 | INF | 2013 | Q1 | Q1 - 2013 | 16226313 | 9355655 | 6870658 | 15127610 | 8154254 | 6973356 | 16329011 | 9355655 | 6973356 | 3071873 | 0 | 3071873 | 1854398 | 0 | 1854398 | 2500000 | 0 | 2500000 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 75645 | 0 | 75645 | 1146600 | 0 | 1146600 | 952303 | 0 | 952303 | 972303 | 0 | 972303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2888194 | 0 | 2888194 | 2908015 | 0 | 2908015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 423000 | 0 | 423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 131235 | 0 | 131235 | 131235 | 0 | 131235 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 23339209 | 9355655 | 13983554 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 23339209 | 9355655 | 13983554 | 0 | 93033 | Iowa Health System
NT10BIX5570084 | INF | 2013 | Q2 | Q2 - 2013 | 16226313 | 9355655 | 6870658 | 15127610 | 8154254 | 6973356 | 16329011 | 9355655 | 6973356 | 3071873 | 0 | 3071873 | 1854398 | 0 | 1854398 | 3071873 | 0 | 3071873 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 85800 | 0 | 85800 | 1146600 | 0 | 1146600 | 952303 | 0 | 952303 | 1123502 | 0 | 1123502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2888194 | 0 | 2888194 | 2908015 | 0 | 2908015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 423000 | 0 | 423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 131235 | 0 | 131235 | 161084 | 0 | 161084 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 24102285 | 9355655 | 14746630 | 0 | 93033 | Iowa Health System
NT10BIX5570084 | INF | 2013 | Q3 | Q3 - 2013 | 16224699 | 8558654 | 7666045 | 16224699 | 8558654 | 7666045 | 16224699 | 8558654 | 7666045 | 3065856 | 574701 | 2491155 | 3065856 | 574701 | 2491155 | 3065856 | 574701 | 2491155 | 57259 | 0 | 57259 | 57259 | 0 | 57259 | 57259 | 0 | 57259 | 1123506 | 0 | 1123506 | 1123506 | 0 | 1123506 | 1123506 | 0 | 1123506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2958658 | 222300 | 2736358 | 2958658 | 222300 | 2736358 | 2958658 | 222300 | 2736358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541071 | 0 | 541071 | 541071 | 0 | 541071 | 541071 | 0 | 541071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131236 | 0 | 131236 | 131236 | 0 | 131236 | 131236 | 0 | 131236 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 93033 | 93033 | Iowa Health System
NT10BIX5570085 | INF | 2010 | Q4 | Q4 - 2010 | 3763176 | 1088627 | 2674549 | 79990 | 23140 | 56850 | 79990 | 23140 | 56850 | 7824210 | 2451048 | 5373162 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 28928 | 71072 | 35522 | 10276 | 25246 | 49522 | 14476 | 35046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 30482 | 74888 | 76198 | 22043 | 54155 | 104198 | 30443 | 73755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 23143 | 56857 | 0 | 0 | 0 | 0 | 0 | 0 | 5544518 | 1603940 | 3940578 | 4206 | 1217 | 2989 | 75799 | 22694 | 53105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 26614 | 65386 | 46433 | 13432 | 33001 | 34000 | 10200 | 23800 | 17509274 | 5252782 | 12256492 | 242349 | 70108 | 172241 | 343509 | 100953 | 242556 | 17509274 | 5252782 | 12256492 | 242349 | 70108 | 172241 | 343509 | 100953 | 242556 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2011 | Q1 | Q1 - 2011 | 3763176 | 1088627 | 2674549 | 79990 | 23140 | 56850 | 79990 | 23140 | 56850 | 7824210 | 2451048 | 5373162 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 28928 | 71072 | 35522 | 10276 | 25246 | 35522 | 10276 | 25246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 30482 | 74888 | 121752 | 35221 | 86531 | 298366 | 89510 | 208856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 23143 | 56857 | 0 | 0 | 0 | 0 | 0 | 0 | 5544518 | 1603940 | 3940578 | 4206 | 1217 | 2989 | 4206 | 1217 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 26614 | 65386 | 46433 | 13432 | 33001 | 46433 | 13432 | 33001 | 17509274 | 5252782 | 12256492 | 287903 | 83286 | 204617 | 464517 | 137575 | 326942 | 17509274 | 5252782 | 12256492 | 287903 | 83286 | 204617 | 464517 | 137575 | 326942 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2011 | Q2 | Q2 - 2011 | 6400083 | 1920025 | 4480058 | 79990 | 23997 | 55993 | 79990 | 23997 | 55993 | 3650203 | 1095061 | 2555142 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 35522 | 10657 | 24865 | 45522 | 13657 | 31865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 118232 | 35469 | 82762 | 448366 | 134510 | 313856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 2433470 | 730041 | 1703429 | 59529 | 17859 | 41671 | 196010 | 58803 | 137207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 46433 | 13930 | 32503 | 46433 | 27600 | 64400 | 12861126 | 3858338 | 9002788 | 339706 | 101912 | 237794 | 816321 | 258567 | 603321 | 12861126 | 3858338 | 9002788 | 339706 | 101912 | 237794 | 816321 | 258567 | 603321 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2011 | Q3 | Q3 - 2011 | 6400083 | 1920025 | 4480058 | 79990 | 23997 | 55993 | 5389990 | 1616997 | 3772993 | 3650203 | 1095061 | 2555142 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 39186 | 11756 | 27430 | 47862 | 14359 | 33503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 326280 | 97884 | 228395 | 747276 | 224183 | 523093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 2433470 | 730041 | 1703429 | 59528 | 17858 | 41670 | 462359 | 138708 | 323651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 0 | 0 | 0 | 0 | 0 | 0 | 12861126 | 3858338 | 9002788 | 504984 | 151495 | 353488 | 6647487 | 1994247 | 4653240 | 12861126 | 3858338 | 9002788 | 504984 | 151495 | 353488 | 6647487 | 1994247 | 4653240 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2011 | Q4 | Q4 - 2011 | 6400083 | 1920025 | 4480058 | 3185836 | 955750 | 2230086 | 4579990 | 1373997 | 3205993 | 3650203 | 1095061 | 2555142 | 560292 | 168087 | 392204 | 340462 | 102139 | 238323 | 100000 | 30000 | 70000 | 41346 | 12404 | 28943 | 73523 | 22057 | 51466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 99255 | 29777 | 69478 | 848366 | 254510 | 593856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 9091 | 2727 | 6364 | 2433470 | 730041 | 1703429 | 582603 | 174781 | 407822 | 582085 | 174625 | 407460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 32837 | 9852 | 22985 | 43838 | 13151 | 30687 | 12861126 | 3858338 | 9002788 | 4502169 | 1350651 | 3151518 | 6477355 | 1943206 | 4534149 | 12861126 | 3858338 | 9002788 | 4502169 | 1350651 | 3151518 | 6477355 | 1943206 | 4534149 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2012 | Q1 | Q1 - 2012 | 6400083 | 1920025 | 4480058 | 3523924 | 1057176 | 2466748 | 5023924 | 1507177 | 3516747 | 3650203 | 1095061 | 2555142 | 723678 | 217103 | 506574 | 1223678 | 367103 | 856575 | 100000 | 30000 | 70000 | 41346 | 12404 | 28943 | 49615 | 14885 | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 151449 | 45435 | 106014 | 181739 | 54522 | 127217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 25000 | 7500 | 17500 | 2433470 | 730041 | 1703429 | 975286 | 292586 | 682700 | 1170343 | 351103 | 819240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 72639 | 21793 | 50847 | 82639 | 24792 | 57847 | 12861126 | 3858338 | 9002788 | 5488322 | 1646497 | 3841826 | 7756938 | 2327082 | 5429856 | 12861126 | 3858338 | 9002788 | 5488322 | 1646497 | 3841826 | 7756938 | 2327082 | 5429856 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2012 | Q2 | Q2 - 2012 | 6400083 | 1920025 | 4480058 | 4156922 | 1247076 | 2909846 | 4500000 | 1350000 | 3150000 | 3650203 | 1095061 | 2555142 | 922034 | 276610 | 645424 | 1250000 | 375000 | 875000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 49615 | 14885 | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 169277 | 50784 | 118493 | 186205 | 55862 | 130343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 25000 | 7500 | 17500 | 2433470 | 730041 | 1703429 | 1423986 | 427196 | 996790 | 1725000 | 517500 | 1207500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52792 | 15838 | 36954 | 60000 | 18000 | 42000 | 12861126 | 3858338 | 9002788 | 6766357 | 2029908 | 4736449 | 7795820 | 2338747 | 5457073 | 12861126 | 3858338 | 9002788 | 6766357 | 2029908 | 4736449 | 7795820 | 2338747 | 5457073 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2012 | Q3 | Q3 - 2012 | 6400083 | 1920025 | 4480058 | 4135909 | 1240772 | 2895137 | 4963091 | 1488927 | 3474163 | 3650203 | 1095061 | 2555142 | 1171734 | 351520 | 820214 | 1406082 | 421825 | 984257 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 197005 | 59102 | 137903 | 200000 | 60000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 30000 | 9000 | 21000 | 60000 | 18000 | 42000 | 2433470 | 730041 | 1703429 | 1580057 | 474017 | 1106040 | 1896068 | 568820 | 1327248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52791 | 15837 | 36954 | 52791 | 15839 | 36954 | 12861126 | 3858338 | 9002788 | 7208842 | 2162652 | 5046190 | 8628032 | 2588411 | 6039622 | 12861126 | 3858338 | 9002788 | 7208842 | 2162652 | 5046190 | 8628032 | 2588411 | 6039622 | 0 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2012 | Q4 | Q4 - 2012 | 6400083 | 1920025 | 4480058 | 4182113 | 1254633 | 2927480 | 4500000 | 1350000 | 3150000 | 3650203 | 1095061 | 2555142 | 1242882 | 372864 | 870018 | 1600000 | 480000 | 1120000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 210972 | 63292 | 147680 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 85000 | 25500 | 59500 | 2433470 | 730041 | 1703429 | 1802013 | 540604 | 1261409 | 1900000 | 570000 | 1330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52792 | 15838 | 36954 | 53000 | 15900 | 37100 | 12861126 | 3858338 | 9002788 | 7607791 | 2282337 | 5325454 | 8413000 | 2523900 | 5889100 | 12861126 | 3858338 | 9002788 | 7607791 | 2282337 | 5325454 | 8413000 | 2523900 | 5889100 | 938470 | 13934 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2013 | Q1 | Q1 - 2013 | 6400083 | 1920025 | 4480058 | 4309252 | 1292775 | 3016477 | 4800000 | 1440000 | 3360000 | 3650203 | 1095061 | 2555142 | 1433266 | 429980 | 1003287 | 1800000 | 540000 | 1260000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 51346 | 15404 | 35942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 539443 | 161834 | 377610 | 839443 | 251834 | 587609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 75673 | 22702 | 52971 | 2433470 | 730041 | 1703429 | 1959310 | 587793 | 1371517 | 2000000 | 600000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 70000 | 21000 | 59000 | 12861126 | 3858338 | 9002788 | 8411083 | 2523326 | 5887758 | 9636462 | 2890940 | 6755522 | 12861126 | 3858338 | 9002788 | 8411083 | 2523326 | 5887758 | 9636462 | 2890940 | 6755522 | 938470 | 31868 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2013 | Q2 | Q2 - 2013 | 6400083 | 1920025 | 4480058 | 4334428 | 1300328 | 3034101 | 4990000 | 1497000 | 3493000 | 3650203 | 1095061 | 2555142 | 1577878 | 473363 | 1104514 | 2100000 | 632100 | 1467900 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 654388 | 196317 | 458071 | 700000 | 210700 | 489300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2035014 | 610504 | 1424510 | 2200000 | 662200 | 1537800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 52793 | 15838 | 36954 | 12861126 | 3858338 | 9002788 | 8771520 | 2631456 | 6140063 | 10170293 | 3056215 | 7114077 | 12861126 | 3858338 | 9002788 | 8771520 | 2631456 | 6140063 | 10170293 | 3056215 | 7114077 | 938470 | 78893 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2013 | Q3 | Q3 - 2013 | 6400083 | 1920025 | 4480058 | 4424238 | 1327271 | 3096967 | 5421000 | 1626300 | 3794700 | 3650203 | 1095061 | 2555142 | 1912551 | 573765 | 1338786 | 2100000 | 630000 | 1470000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 876900 | 263070 | 613830 | 950000 | 285000 | 665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2151330 | 645399 | 1505931 | 2300000 | 690000 | 1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 52793 | 15838 | 36954 | 12861126 | 3858338 | 9002788 | 9534831 | 2860449 | 6674381 | 10951293 | 3285515 | 7665777 | 12861126 | 3858338 | 9002788 | 9534831 | 2860449 | 6674381 | 10951293 | 3285515 | 7665777 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2013 | Q4 | Q4 - 2013 | 6400083 | 1920025 | 4480058 | 4424989 | 1327496 | 3097493 | 4893612 | 1468084 | 3425528 | 3650203 | 1095061 | 2555142 | 2080021 | 624006 | 1456015 | 2400000 | 720000 | 1680000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 958230 | 287469 | 670761 | 1000000 | 300000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2315869 | 694761 | 1621108 | 2400000 | 720000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 77500 | 23327 | 54173 | 12861126 | 3858338 | 9002788 | 9948921 | 2984676 | 6964244 | 10898612 | 3269788 | 7628824 | 12861126 | 3858338 | 9002788 | 9948921 | 2984676 | 6964244 | 10898612 | 3269788 | 7628824 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2014 | Q1 | Q1 - 2014 | 6400083 | 1920025 | 4480058 | 4438990 | 1331697 | 3107293 | 4893612 | 1468084 | 3425528 | 3650203 | 1095061 | 2555142 | 2322825 | 696847 | 1625978 | 3000000 | 900000 | 2100000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 1053041 | 315912 | 737129 | 1200000 | 360000 | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2416966 | 725090 | 1691876 | 2433470 | 730041 | 1703429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15839 | 36954 | 77500 | 23327 | 54173 | 12861126 | 3858338 | 9002788 | 10401634 | 3120491 | 7281143 | 11732082 | 3519829 | 8212253 | 12861126 | 3858338 | 9002788 | 10401634 | 3120491 | 7281143 | 11732082 | 3519829 | 8212253 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2014 | Q2 | Q2 - 2014 | 6400083 | 1920025 | 4480058 | 4442645 | 1332794 | 3109852 | 4536213 | 1360864 | 3175349 | 3650203 | 1095061 | 2555142 | 2792041 | 837611 | 1954429 | 3399030 | 1019709 | 2379321 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 43030 | 12909 | 30121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 1075399 | 322619 | 752779 | 1236801 | 371040 | 865761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 75673 | 22702 | 52971 | 2433470 | 730041 | 1703429 | 2616530 | 784959 | 1831571 | 2829750 | 848925 | 1980825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15839 | 36955 | 52793 | 15838 | 36955 | 12861126 | 3858338 | 9002788 | 11096427 | 3328928 | 7767499 | 12173290 | 3651987 | 8521303 | 12861126 | 3858338 | 9002788 | 11096427 | 3328928 | 7767499 | 12173290 | 3651987 | 8521303 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2014 | Q3 | Q3 - 2014 | 6400083 | 1920025 | 4480058 | 4858331 | 1457499 | 3400832 | 4858000 | 1457400 | 3400600 | 3650203 | 1095061 | 2555142 | 3882797 | 1164839 | 2717958 | 3890126 | 1167038 | 2723088 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 41346 | 12404 | 28942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 1085617 | 325685 | 759932 | 1220000 | 366000 | 854000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 70000 | 21000 | 49000 | 2433470 | 730041 | 1703429 | 2695335 | 808600 | 1886735 | 2720000 | 816000 | 1904000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15839 | 36954 | 53000 | 15900 | 37100 | 12861126 | 3858338 | 9002788 | 12691892 | 3807568 | 8884324 | 12852472 | 3855742 | 8996730 | 12861126 | 3858338 | 9002788 | 12691892 | 3807568 | 8884324 | 12852472 | 3855742 | 8996730 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570085 | INF | 2014 | Q4 | Q4 - 2014 | 4858000 | 1457400 | 3400600 | 4847418 | 1454226 | 3393192 | 4847418 | 1454226 | 3393192 | 3860779 | 1099982 | 2702545 | 4308748 | 1601985 | 2706763 | 4308748 | 1601985 | 2706763 | 50000 | 15000 | 35000 | 41346 | 12404 | 28942 | 41346 | 12404 | 28942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220000 | 366000 | 854000 | 1257729 | 377319 | 880410 | 1257729 | 377319 | 880410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 75673 | 22702 | 52971 | 75673 | 22702 | 52971 | 2749347 | 824804 | 1924543 | 2719156 | 815747 | 1903409 | 2719156 | 815747 | 1903409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53000 | 15900 | 37100 | 302792 | 212900 | 37100 | 302792 | 212900 | 37100 | 12861126 | 3800086 | 9002788 | 13552862 | 4497283 | 9002787 | 13552862 | 4497283 | 9002787 | 12861126 | 3800086 | 9002788 | 13552862 | 4497283 | 9002787 | 13552862 | 4497283 | 9002787 | 938470 | 0 | Vermont Telephone Company, Inc.
NT10BIX5570086 | INF | 2010 | Q4 | Q4 - 2010 | 2751000 | 825300 | 1925700 | 0 | 0 | 0 | 0 | 0 | 0 | 13382331 | 4014699 | 9367632 | 0 | 0 | 0 | 0 | 0 | 0 | 652966 | 195890 | 457076 | 29445 | 29445 | 0 | 59445 | 59445 | 0 | 551505 | 165452 | 386053 | 114813 | 114813 | 0 | 264813 | 264813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 35527 | 35527 | 0 | 75527 | 75527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 0 | 0 | 0 | 0 | 0 | 0 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 57250 | 57250 | 0 | 57250 | 57250 | 0 | 24032051 | 7209616 | 16822435 | 237035 | 237035 | 0 | 457035 | 457035 | 0 | 24032051 | 7209616 | 16822435 | 237035 | 237035 | 0 | 457035 | 457035 | 0 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2011 | Q1 | Q1 - 2011 | 2751000 | 825300 | 1925700 | 0 | 0 | 0 | 300000 | 120000 | 180000 | 13382331 | 4014699 | 9367632 | 0 | 0 | 0 | 140000 | 56000 | 84000 | 652966 | 195890 | 457076 | 77414 | 30966 | 46448 | 125000 | 50000 | 75000 | 551505 | 165452 | 386053 | 189257 | 75703 | 113554 | 324000 | 129600 | 194400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 153512 | 61405 | 92107 | 275000 | 110000 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 228 | 91 | 137 | 228 | 91 | 137 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 57250 | 22900 | 34350 | 57250 | 22900 | 34350 | 24032051 | 7209616 | 16822435 | 477661 | 191065 | 286596 | 1221478 | 488591 | 732887 | 24032051 | 7209616 | 16822435 | 477661 | 191065 | 286596 | 1221478 | 488591 | 732887 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2011 | Q2 | Q2 - 2011 | 2751000 | 825300 | 1925700 | 5545 | 1930 | 3615 | 5545 | 1774 | 3771 | 13382331 | 4014699 | 9367632 | 37282 | 12978 | 24304 | 3546607 | 1134914 | 2411693 | 652967 | 195890 | 457077 | 118085 | 41105 | 76980 | 142856 | 45714 | 97142 | 551506 | 165452 | 386054 | 272864 | 94984 | 177880 | 302864 | 96916 | 205948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 336764 | 117228 | 219536 | 521764 | 166964 | 354800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 11415 | 3974 | 7441 | 459368 | 146998 | 312370 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 45000 | 14400 | 30600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 61719 | 21475 | 40244 | 66719 | 21350 | 45369 | 24032053 | 7209616 | 16822437 | 843674 | 293674 | 550000 | 5090723 | 1629030 | 3461693 | 24032053 | 7209616 | 16822437 | 843674 | 293674 | 550000 | 5090723 | 1629030 | 3461693 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2011 | Q3 | Q3 - 2011 | 2751000 | 825300 | 1925700 | 19950 | 5985 | 13965 | 471000 | 141300 | 329700 | 13382331 | 4014699 | 9367632 | 4593994 | 1378198 | 3215796 | 5246380 | 1573914 | 3672466 | 652967 | 195890 | 457077 | 145377 | 43613 | 101764 | 200000 | 60000 | 140000 | 551506 | 165452 | 386054 | 451238 | 135371 | 315867 | 550000 | 165000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 485585 | 145676 | 339909 | 961023 | 288307 | 672716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 51719 | 15516 | 36203 | 111719 | 33516 | 78203 | 1018443 | 305533 | 712910 | 41491 | 12447 | 29044 | 51053 | 15316 | 35737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 82347 | 24704 | 57643 | 82347 | 24704 | 57643 | 24032053 | 7209616 | 16822437 | 5871701 | 1761510 | 4110191 | 7673522 | 2302057 | 5371465 | 24032053 | 7209616 | 16822437 | 5871701 | 1761510 | 4110191 | 7673522 | 2302057 | 5371465 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2011 | Q4 | Q4 - 2011 | 2751000 | 825300 | 1925700 | 471331 | 141399 | 329932 | 501331 | 150400 | 350931 | 13382331 | 4014699 | 9367632 | 10502690 | 3150807 | 7351883 | 10602693 | 3180808 | 7421885 | 652967 | 195890 | 457077 | 179583 | 53875 | 125708 | 200000 | 60000 | 140000 | 551506 | 165452 | 386054 | 666530 | 199959 | 466571 | 676530 | 202959 | 473571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 574845 | 172454 | 402392 | 624845 | 187454 | 437391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 90850 | 27255 | 63595 | 90850 | 27255 | 63595 | 1018443 | 305533 | 712910 | 205070 | 61521 | 143549 | 225070 | 67521 | 157549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 99614 | 29884 | 69730 | 120000 | 36000 | 84000 | 24032053 | 7209616 | 16822437 | 12790513 | 3837154 | 8953360 | 13041319 | 3912397 | 9128922 | 24032053 | 7209616 | 16822437 | 12790513 | 3837154 | 8953360 | 13041319 | 3912397 | 9128922 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2012 | Q1 | Q1 - 2012 | 2751000 | 825300 | 1925700 | 480347 | 144104 | 336243 | 915350 | 274605 | 640745 | 13382331 | 4014699 | 9367632 | 10669475 | 3200842 | 7468633 | 12663557 | 3799067 | 8864490 | 652967 | 195890 | 457077 | 196002 | 58801 | 137201 | 220000 | 66000 | 154000 | 551506 | 165452 | 386054 | 691947 | 207584 | 484363 | 778639 | 233592 | 545047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 698463 | 209539 | 488924 | 865556 | 259667 | 605889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 108604 | 32581 | 76023 | 141903 | 42571 | 99332 | 1018443 | 305533 | 712910 | 114692 | 34408 | 80284 | 155692 | 46708 | 108984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 227896 | 68369 | 159527 | 250000 | 75000 | 175000 | 24032053 | 7209616 | 16822437 | 13187426 | 3956228 | 9231198 | 15990697 | 4797210 | 11193487 | 24032053 | 7209616 | 16822437 | 13187426 | 3956228 | 9231198 | 15990697 | 4797210 | 11193487 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2012 | Q2 | Q2 - 2012 | 2751000 | 825300 | 1925700 | 486484 | 145945 | 340539 | 926314 | 277894 | 648420 | 13382331 | 4014699 | 9367632 | 11664422 | 3499327 | 8165095 | 14840894 | 4452268 | 10388626 | 652967 | 195890 | 457077 | 280035 | 84011 | 196024 | 310035 | 93011 | 217024 | 551506 | 165452 | 386054 | 737938 | 221381 | 516557 | 742938 | 222881 | 520057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 809358 | 242807 | 566551 | 1029358 | 308807 | 720551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 162955 | 48886 | 114069 | 207331 | 62199 | 145132 | 1018443 | 305533 | 712910 | 135829 | 40749 | 95080 | 185829 | 55749 | 130080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 166415 | 49925 | 116490 | 166415 | 49925 | 116490 | 24032053 | 7209616 | 16822437 | 14443436 | 4333031 | 10110405 | 18409114 | 5522734 | 12886380 | 24032053 | 7209616 | 16822437 | 14443436 | 4333031 | 10110405 | 18409114 | 5522734 | 12886380 | 0 | 0 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2012 | Q3 | Q3 - 2012 | 1905514 | 571654 | 1333860 | 923588 | 277076 | 646512 | 963588 | 289076 | 674512 | 17963245 | 5388973 | 12574272 | 14921116 | 4476335 | 10444781 | 16484656 | 4945397 | 11539259 | 652967 | 195890 | 457077 | 317421 | 95226 | 222195 | 367421 | 110226 | 257195 | 808259 | 242478 | 565781 | 763611 | 229083 | 534528 | 763611 | 229083 | 534528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 915242 | 274573 | 640669 | 1011142 | 303343 | 707799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 221493 | 66448 | 155045 | 244698 | 73409 | 171289 | 767106 | 230132 | 536974 | 153834 | 46150 | 107684 | 193834 | 58150 | 135684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 18379607 | 5513881 | 12865726 | 20192252 | 6057674 | 14134578 | 24032053 | 7209616 | 16822437 | 18379607 | 5513881 | 12865726 | 20192252 | 6057674 | 14134578 | 0 | 690 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2012 | Q4 | Q4 - 2012 | 1905514 | 571654 | 1333860 | 950636 | 285191 | 665445 | 1142636 | 342791 | 799845 | 17963245 | 5388973 | 12574272 | 16270681 | 4881204 | 11389477 | 16275681 | 4882704 | 11392977 | 652967 | 195890 | 457077 | 349851 | 104955 | 244896 | 399851 | 119955 | 279896 | 808259 | 242478 | 565781 | 758595 | 227579 | 531016 | 758595 | 227579 | 531016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 977508 | 293252 | 684256 | 1035508 | 310652 | 724856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 261467 | 78440 | 183027 | 267967 | 80390 | 187577 | 767106 | 230132 | 536974 | 236867 | 71060 | 165807 | 256867 | 77060 | 179807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 19968907 | 5990671 | 13978236 | 20300407 | 6090121 | 14210286 | 24032053 | 7209616 | 16822437 | 19968907 | 5990671 | 13978236 | 20300407 | 6090121 | 14210286 | 0 | 69457 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2013 | Q1 | Q1 - 2013 | 1905514 | 571654 | 1333860 | 1026017 | 307805 | 718212 | 1264016 | 379205 | 884811 | 17963245 | 5388973 | 12574272 | 16243330 | 4872999 | 11370331 | 17131164 | 5139349 | 11991815 | 652967 | 195890 | 457077 | 373430 | 112030 | 261400 | 413430 | 124029 | 289401 | 808259 | 242478 | 565781 | 806511 | 241953 | 564558 | 814101 | 244230 | 569871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1049381 | 314814 | 734567 | 1156813 | 347044 | 809769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 263319 | 78996 | 184323 | 268231 | 80469 | 187762 | 767106 | 230132 | 536974 | 294542 | 88363 | 206179 | 333542 | 100063 | 233479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 20219832 | 6065950 | 14153882 | 21544599 | 6463379 | 15081220 | 24032053 | 7209616 | 16822437 | 20219832 | 6065950 | 14153882 | 21544599 | 6463379 | 15081220 | 0 | 221296 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2013 | Q2 | Q2 - 2013 | 1905514 | 571654 | 1333860 | 1348246 | 404474 | 943772 | 1350999 | 405300 | 945699 | 17963245 | 5388973 | 12574272 | 16218556 | 4865567 | 11352989 | 16770000 | 5031000 | 11739000 | 652967 | 195890 | 457077 | 399658 | 119897 | 279761 | 480000 | 144000 | 336000 | 808259 | 242478 | 565781 | 811415 | 243424 | 567991 | 814000 | 244200 | 569800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1101935 | 330580 | 771355 | 1163000 | 348900 | 814100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 277375 | 83212 | 194163 | 281000 | 84300 | 196700 | 767106 | 230132 | 536974 | 312482 | 93745 | 218737 | 325489 | 97647 | 227842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 20632969 | 6189889 | 14443080 | 21347790 | 6404337 | 14943453 | 24032053 | 7209616 | 16822437 | 20632969 | 6189889 | 14443080 | 21347790 | 6404337 | 14943453 | 0 | 496466 | Enventis Telecom, Inc.
NT10BIX5570086 | INF | 2013 | Q3 | Q3 - 2013 | 1905514 | 571654 | 1333860 | 1305748 | 391724 | 914024 | 1305748 | 391724 | 914024 | 17963245 | 5388973 | 12574272 | 16146089 | 4843827 | 11302262 | 16146089 | 4843827 | 11302262 | 652967 | 195890 | 457077 | 432046 | 129614 | 302432 | 432046 | 129614 | 302432 | 808259 | 242478 | 565781 | 829339 | 248802 | 580537 | 829339 | 248802 | 580537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1148548 | 344564 | 803984 | 1148548 | 344564 | 803984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 295420 | 88626 | 206794 | 295420 | 88626 | 206794 | 767106 | 230132 | 536974 | 775038 | 232511 | 542527 | 775038 | 232511 | 542527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163407 | 49022 | 114385 | 163407 | 49022 | 114385 | 24032053 | 7209616 | 16822437 | 21095635 | 6328690 | 14766945 | 21095635 | 6328690 | 14766945 | 24032053 | 7209616 | 16822437 | 21095635 | 6328690 | 14766945 | 21095635 | 6328690 | 14766945 | 0 | 562802 | Enventis Telecom, Inc.
NT10BIX5570087 | INF | 2010 | Q4 | Q4 - 2010 | 2937139 | 587428 | 2349711 | 307 | 0 | 0 | 160000 | 160000 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 14686 | 0 | 15815 | 200465 | 0 | 200465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 14993 | 0 | 15815 | 360465 | 160000 | 200465 | 12529059 | 2505812 | 10023247 | 14993 | 0 | 15815 | 360465 | 160000 | 200465 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2011 | Q1 | Q1 - 2011 | 2937139 | 587428 | 2349711 | 307 | 0 | 307 | 85000 | 85000 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 48646 | 0 | 48646 | 380646 | 0 | 380646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 48953 | 0 | 48953 | 465646 | 85000 | 380646 | 12529059 | 2505812 | 10023247 | 48953 | 0 | 48953 | 465646 | 85000 | 380646 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2011 | Q2 | Q2 - 2011 | 2937139 | 587428 | 2349711 | 175386 | 175386 | 0 | 275386 | 275386 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 240000 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 24000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 432745 | 258580 | 174165 | 567050 | 406046 | 161004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 608131 | 433966 | 174165 | 1166436 | 921432 | 461004 | 12529059 | 2505812 | 10023247 | 608131 | 433966 | 174165 | 1166436 | 921432 | 461004 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2011 | Q3 | Q3 - 2011 | 2937139 | 587428 | 2349711 | 436807 | 105047 | 331760 | 2900000 | 600000 | 2300000 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 557000 | 112000 | 445000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 240000 | 48000 | 192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 501642 | 329223 | 172419 | 582487 | 329223 | 253264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 40000 | 8000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 938449 | 434270 | 504179 | 4319487 | 1097223 | 3222264 | 12529059 | 2505812 | 10023247 | 938449 | 434270 | 504179 | 4319487 | 1097223 | 3222264 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2011 | Q4 | Q4 - 2011 | 2937139 | 587428 | 2349711 | 2926669 | 620528 | 2306141 | 2941669 | 635528 | 2306141 | 8260120 | 1652024 | 6608096 | 1528971 | 62111 | 1466860 | 2178971 | 312111 | 1866860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 238638 | 47728 | 190910 | 248138 | 47228 | 200910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 592124 | 339104 | 253020 | 717124 | 364105 | 353020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 125000 | 25000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 5286402 | 1069471 | 4216931 | 6210902 | 1383972 | 4826931 | 12529059 | 2505812 | 10023247 | 5286402 | 1069471 | 4216931 | 6210902 | 1383972 | 4826931 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2012 | Q1 | Q1 - 2012 | 3760076 | 630000 | 3130076 | 2945075 | 622782 | 2322293 | 3022782 | 622782 | 2400000 | 5862934 | 1393441 | 4469493 | 1770954 | 115775 | 1655179 | 2850954 | 358998 | 2491956 | 630000 | 1971 | 628029 | 91470 | 1972 | 89498 | 173988 | 1972 | 172016 | 603637 | 66400 | 537237 | 355873 | 50474 | 305399 | 361384 | 50474 | 310910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 448557 | 342332 | 106225 | 530321 | 342332 | 187989 | 298012 | 22000 | 276012 | 178012 | 21764 | 156248 | 208012 | 21764 | 186248 | 154000 | 0 | 154000 | 24991 | 0 | 24991 | 32991 | 0 | 32991 | 420000 | 40000 | 380000 | 0 | 0 | 0 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10022647 | 5814932 | 1155099 | 4659833 | 7300432 | 1438322 | 5862110 | 12528459 | 2505812 | 10022647 | 5814932 | 1155099 | 4659833 | 7300432 | 1438322 | 5862110 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2012 | Q2 | Q2 - 2012 | 3760076 | 630000 | 3130076 | 2945132 | 622782 | 2322350 | 3352350 | 630000 | 2722350 | 5862934 | 1393441 | 4469493 | 2733661 | 475170 | 2258491 | 3693544 | 875170 | 2818374 | 630000 | 1971 | 628029 | 106557 | 1971 | 104586 | 136557 | 1971 | 134586 | 603637 | 66400 | 537237 | 241337 | 48502 | 192835 | 381336 | 58501 | 322835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 449883 | 343022 | 106861 | 489883 | 343022 | 146861 | 298012 | 22000 | 276012 | 180101 | 21764 | 158337 | 210101 | 21764 | 188337 | 154000 | 0 | 154000 | 40695 | 0 | 40695 | 52695 | 0 | 52695 | 420000 | 40000 | 380000 | 0 | 0 | 0 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10022647 | 6697366 | 1513211 | 5184155 | 8436466 | 1970428 | 6466038 | 12528459 | 2505812 | 10022647 | 6697366 | 1513211 | 5184155 | 8436466 | 1970428 | 6466038 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2012 | Q3 | Q3 - 2012 | 3760076 | 630000 | 3130076 | 3011465 | 622782 | 2388683 | 3111465 | 622782 | 2488683 | 5862934 | 1393441 | 4470093 | 3853815 | 523955 | 3329860 | 5053815 | 723955 | 4329860 | 630000 | 1971 | 628029 | 118271 | 1971 | 116300 | 198271 | 1971 | 196300 | 603637 | 66400 | 537237 | 246278 | 48502 | 197776 | 446278 | 48502 | 397776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 493966 | 349793 | 144173 | 553966 | 349793 | 204173 | 298012 | 22000 | 276012 | 180101 | 21764 | 158337 | 205101 | 21764 | 183337 | 154000 | 0 | 154000 | 58044 | 0 | 58044 | 70044 | 0 | 70044 | 420000 | 40000 | 380000 | 48789 | 0 | 48789 | 198789 | 150000 | 48789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10023247 | 8010729 | 1568767 | 6441962 | 9837729 | 1918767 | 7918962 | 12528459 | 2505812 | 10023247 | 8010729 | 1568767 | 6441962 | 9837729 | 1918767 | 7918962 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2012 | Q4 | Q4 - 2012 | 3760076 | 630000 | 3130076 | 2932392 | 606819 | 2325573 | 3232392 | 606819 | 2625573 | 5862934 | 1393441 | 4470093 | 4273160 | 614124 | 3659036 | 4473159 | 814124 | 3659035 | 630000 | 1971 | 628029 | 125972 | 1971 | 124001 | 191972 | 1971 | 190001 | 603637 | 66400 | 537237 | 333704 | 64466 | 269238 | 343704 | 64466 | 279238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 520207 | 349793 | 170414 | 570207 | 349793 | 220414 | 298012 | 22000 | 276012 | 196178 | 21764 | 174414 | 226178 | 21764 | 204414 | 154000 | 0 | 154000 | 76876 | 0 | 76876 | 88876 | 0 | 88876 | 420000 | 40000 | 380000 | 97575 | 48786 | 48789 | 207575 | 20000 | 187575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10023247 | 8556064 | 1707723 | 6848341 | 9334063 | 1878937 | 7455126 | 12528459 | 2505812 | 10023247 | 8556064 | 1707723 | 6848341 | 9334063 | 1878937 | 7455126 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2013 | Q1 | Q1 - 2013 | 3760076 | 630000 | 3130076 | 2949996 | 620950 | 2329046 | 3559046 | 630000 | 2929046 | 5863534 | 1393441 | 4470093 | 4571186 | 685994 | 3885192 | 5770935 | 1344373 | 4426562 | 630000 | 1971 | 628029 | 144632 | 1971 | 142661 | 174883 | 1971 | 172912 | 603637 | 66400 | 537237 | 340074 | 65486 | 274588 | 347074 | 65486 | 281588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 553553 | 350489 | 203064 | 603553 | 350489 | 253064 | 298012 | 22000 | 276012 | 196178 | 21764 | 174414 | 226178 | 21764 | 204414 | 154000 | 0 | 154000 | 88876 | 0 | 88876 | 100876 | 0 | 100876 | 420000 | 40000 | 380000 | 167870 | 48786 | 119084 | 256656 | 48786 | 207870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 9012365 | 1795440 | 7216925 | 11039201 | 2462869 | 8576332 | 12529059 | 2505812 | 10023247 | 9012365 | 1795440 | 7216925 | 11039201 | 2462869 | 8576332 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2013 | Q2 | Q2 - 2013 | 3760076 | 630000 | 3130076 | 2987320 | 624020 | 2363300 | 3184024 | 624020 | 2560004 | 5863534 | 1393441 | 4470093 | 5002388 | 985910 | 4016478 | 5786659 | 1060910 | 4725749 | 630000 | 1971 | 628029 | 168992 | 1971 | 167021 | 259127 | 1971 | 257156 | 603637 | 66400 | 537237 | 343888 | 66341 | 277547 | 343888 | 66340 | 277548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 566964 | 350489 | 216475 | 597904 | 350489 | 247415 | 298012 | 22000 | 276012 | 204471 | 21764 | 182707 | 204471 | 21764 | 182707 | 154000 | 0 | 154000 | 90701 | 0 | 90701 | 96871 | 0 | 96871 | 420000 | 40000 | 380000 | 167870 | 0 | 167870 | 267870 | 0 | 267870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 9532594 | 2050495 | 7482099 | 10740814 | 2125494 | 8615320 | 12529059 | 2505812 | 10023247 | 9532594 | 2050495 | 7482099 | 10740814 | 2125494 | 8615320 | 0 | 0 | Mid-Atlantic Broadband Cooperative
NT10BIX5570087 | INF | 2013 | Q3 | Q3 - 2013 | 3760076 | 630000 | 3130076 | 3355545 | 655442 | 2700103 | 3355545 | 655442 | 2700103 | 5863534 | 1393441 | 4470093 | 5833983 | 1090234 | 4743749 | 5833983 | 1090234 | 4743749 | 630000 | 1971 | 628029 | 243478 | 4387 | 239092 | 243478 | 4387 | 239092 | 603637 | 66400 | 537237 | 340988 | 66341 | 274647 | 340988 | 66341 | 274647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 608161 | 350489 | 257672 | 608161 | 350489 | 257672 | 298012 | 22000 | 276012 | 204471 | 21764 | 182707 | 204471 | 21764 | 182707 | 154000 | 0 | 154000 | 93000 | 0 | 93000 | 93000 | 0 | 93000 | 420000 | 40000 | 380000 | 168076 | 0 | 168076 | 168076 | 0 | 168076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 10847702 | 2188657 | 8659046 | 10847702 | 2188657 | 8659046 | 12529059 | 2505812 | 10023247 | 10847702 | 2188657 | 8659046 | 10847702 | 2188657 | 8659046 | 0 | 6616 | Mid-Atlantic Broadband Cooperative
NT10BIX5570088 | INF | 2010 | Q4 | Q4 - 2010 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 17900 | 17900 | 0 | 32000 | 32000 | 0 | 4077000 | 4077000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 44399 | 44399 | 0 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 62299 | 62299 | 0 | 112000 | 112000 | 0 | 21092443 | 4389953 | 16702490 | 62299 | 62299 | 0 | 112000 | 112000 | 0 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2011 | Q1 | Q1 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 26240 | 26240 | 0 | 32240 | 32240 | 0 | 4077000 | 4077000 | 0 | 14523 | 14523 | 0 | 84523 | 84523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 82037 | 82037 | 0 | 117037 | 117037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 122800 | 122800 | 0 | 233800 | 233800 | 0 | 21092443 | 4389953 | 16702490 | 122800 | 122800 | 0 | 233800 | 233800 | 0 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2011 | Q2 | Q2 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 60772 | 60772 | 0 | 98738 | 98738 | 0 | 4077000 | 4077000 | 0 | 27111 | 27111 | 0 | 94229 | 94229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 117796 | 117796 | 0 | 167796 | 167796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 205679 | 205679 | 0 | 360763 | 360763 | 0 | 21092443 | 4389953 | 16702490 | 205679 | 205679 | 0 | 360763 | 360763 | 0 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2011 | Q3 | Q3 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 1906642 | 0 | 1906642 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 100754 | 100754 | 0 | 171633 | 171633 | 0 | 4077000 | 4077000 | 0 | 44774 | 44774 | 0 | 119227 | 119227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 162343 | 162343 | 0 | 192343 | 192343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 307871 | 307871 | 0 | 2389845 | 483203 | 1906642 | 21092443 | 4389953 | 16702490 | 307871 | 307871 | 0 | 2389845 | 483203 | 1906642 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2011 | Q4 | Q4 - 2011 | 9576630 | 3400195 | 6176435 | 0 | 0 | 0 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 380005 | 289193 | 90812 | 622016 | 334343 | 287673 | 2123797 | 520159 | 1603638 | 318953 | 318953 | 0 | 697590 | 318953 | 378637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 41312 | 0 | 41312 | 482648 | 0 | 482648 | 920857 | 0 | 920857 | 0 | 0 | 0 | 828113 | 0 | 828113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 0 | 0 | 0 | 354370 | 0 | 354370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 740270 | 608146 | 132124 | 4255832 | 653296 | 3602536 | 21092443 | 4389954 | 16702489 | 740270 | 608146 | 132124 | 4255832 | 653296 | 3602536 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2012 | Q1 | Q1 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1382495 | 0 | 1382495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 643476 | 367801 | 275674 | 834688 | 429801 | 404887 | 2123797 | 520159 | 1603638 | 697590 | 318953 | 378637 | 806090 | 318953 | 487137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 417603 | 0 | 417603 | 417603 | 0 | 417603 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 874485 | 0 | 874485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 236638 | 0 | 236638 | 1561638 | 0 | 1561638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 122582 | 0 | 122582 | 21092443 | 4389954 | 16702489 | 4094516 | 686754 | 3407761 | 5999581 | 748754 | 5250827 | 21092443 | 4389954 | 16702489 | 4094516 | 686754 | 3407761 | 5999581 | 748754 | 5250827 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2012 | Q2 | Q2 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 772607 | 433489 | 339118 | 841000 | 471000 | 370000 | 2123797 | 520159 | 1603638 | 781743 | 318953 | 462790 | 812101 | 318953 | 492257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4495200 | 752442 | 3742758 | 4593951 | 789953 | 3803107 | 21092443 | 4389954 | 16702489 | 4495200 | 752442 | 3742758 | 4593951 | 789953 | 3803107 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2012 | Q3 | Q3 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 846300 | 468931 | 377369 | 912000 | 497000 | 415000 | 2123797 | 520159 | 1603638 | 843172 | 318953 | 524219 | 904601 | 318953 | 585648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4630322 | 787884 | 3842438 | 4757451 | 815953 | 3941498 | 21092443 | 4389954 | 16702489 | 4630322 | 787884 | 3842438 | 4757451 | 815953 | 3941498 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2012 | Q4 | Q4 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 909312 | 501480 | 407832 | 979000 | 536000 | 443000 | 2123797 | 520159 | 1603638 | 921527 | 318953 | 602574 | 1020953 | 318953 | 702000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4771689 | 820433 | 3951256 | 4940803 | 854953 | 4085850 | 21092443 | 4389954 | 16702489 | 4771689 | 820433 | 3951256 | 4940803 | 854953 | 4085850 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2013 | Q1 | Q1 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 984109 | 533019 | 451090 | 1064109 | 568019 | 496090 | 2123797 | 520159 | 1603638 | 1201580 | 529062 | 672517 | 1301579 | 529062 | 772517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5126539 | 1062081 | 4064457 | 5306538 | 1097081 | 4209457 | 21092443 | 4389954 | 16702489 | 5126539 | 1062081 | 4064457 | 5306538 | 1097081 | 4209457 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2013 | Q2 | Q2 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1093191 | 581435 | 511756 | 1205979 | 602223 | 603756 | 2123797 | 520159 | 1603638 | 1252877 | 529062 | 723815 | 1304175 | 529062 | 775113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5286918 | 1110497 | 4176421 | 5451004 | 1131285 | 4319719 | 21092443 | 4389954 | 16702489 | 5286918 | 1110497 | 4176421 | 5451004 | 1131285 | 4319719 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2013 | Q3 | Q3 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1182144 | 603254 | 578889 | 1253890 | 625000 | 628890 | 2123797 | 520159 | 1603638 | 1377729 | 583690 | 794039 | 1383690 | 583690 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5500723 | 1186944 | 4313778 | 5578430 | 1208690 | 4369740 | 21092443 | 4389954 | 16702489 | 5500723 | 1186944 | 4313778 | 5578430 | 1208690 | 4369740 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2013 | Q4 | Q4 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 2388937 | 769751 | 1619186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1266065 | 623294 | 642771 | 1645822 | 633000 | 1012822 | 2123797 | 520159 | 1603638 | 1048759 | 583690 | 465069 | 1380142 | 583690 | 796452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 495775 | 0 | 495775 | 524836 | 0 | 524836 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 920857 | 0 | 920857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380695 | 0 | 380695 | 2826170 | 0 | 2826170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 170607 | 0 | 170607 | 21092443 | 4389954 | 16702489 | 5290503 | 1206984 | 4083519 | 9857371 | 1986441 | 7870930 | 21092443 | 4389954 | 16702489 | 5290503 | 1206984 | 4083519 | 9857371 | 1986441 | 7870930 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2014 | Q1 | Q1 - 2014 | 9576630 | 3400195 | 6176435 | 1756020 | 0 | 1756020 | 3000000 | 1000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1708122 | 685760 | 1022362 | 1762000 | 706000 | 1056000 | 2123797 | 520159 | 1603638 | 1048759 | 583690 | 465069 | 1048759 | 583690 | 465069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 1375107 | 0 | 1375107 | 1400107 | 0 | 1400107 | 920857 | 0 | 920857 | 858114 | 0 | 858114 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 1977023 | 0 | 1977023 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 285011 | 0 | 285011 | 310000 | 0 | 310000 | 21092443 | 4389954 | 16702489 | 9008156 | 1269450 | 7738706 | 10520866 | 2289690 | 8231176 | 21092443 | 4389954 | 16702489 | 9008156 | 1269450 | 7738706 | 10520866 | 2289690 | 8231176 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2014 | Q2 | Q2 - 2014 | 11188208 | 2924730 | 8263478 | 2525771 | 769751 | 1756020 | 4025771 | 1769751 | 2256020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190225 | 881533 | 1308692 | 1756039 | 733677 | 1022362 | 1840039 | 783677 | 1056362 | 1048760 | 583690 | 465070 | 1048759 | 583690 | 465069 | 1048759 | 583690 | 465069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400107 | 0 | 1400107 | 1401107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 2048113 | 0 | 2048113 | 896869 | 0 | 896869 | 1000000 | 783 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797023 | 0 | 2797023 | 1991122 | 0 | 1991122 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420007 | 0 | 420007 | 318455 | 0 | 318455 | 415000 | 0 | 415000 | 21092443 | 4389953 | 16702490 | 9938122 | 2087118 | 7851004 | 11730676 | 3137901 | 8593558 | 21092443 | 4389953 | 16702490 | 9938122 | 2087118 | 7851004 | 11730676 | 3137901 | 8593558 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2014 | Q3 | Q3 - 2014 | 11188208 | 2924730 | 8263478 | 3479354 | 1711879 | 1767475 | 4700000 | 2200000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190225 | 881533 | 1308692 | 1818879 | 796282 | 1022597 | 1875000 | 850000 | 1025000 | 1048760 | 583690 | 465070 | 1048759 | 583690 | 465069 | 1048759 | 583690 | 465069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 2048113 | 0 | 2048113 | 968932 | 0 | 968932 | 1100000 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797023 | 0 | 2797023 | 1991122 | 0 | 1991122 | 2100000 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420007 | 0 | 420007 | 326816 | 0 | 326816 | 412000 | 0 | 412000 | 21092443 | 4389953 | 16703490 | 11034969 | 3091851 | 7943118 | 12636866 | 3633690 | 9003176 | 21092443 | 4389953 | 16703490 | 11034969 | 3091851 | 7943118 | 12636866 | 3633690 | 9003176 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2014 | Q4 | Q4 - 2014 | 11188208 | 2924730 | 8263478 | 6580831 | 2133726 | 4447105 | 8540000 | 2390000 | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190225 | 881533 | 1308692 | 1953304 | 910401 | 1042903 | 2018000 | 950000 | 1068000 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400107 | 0 | 1400107 | 1401107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 2048113 | 0 | 2048113 | 1289918 | 0 | 1289918 | 1610000 | 0 | 1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797023 | 0 | 2797023 | 2127915 | 0 | 2127915 | 2300000 | 0 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420007 | 0 | 420007 | 326816 | 0 | 326816 | 420000 | 0 | 420000 | 21092443 | 4389953 | 16702490 | 14728651 | 3627817 | 11100834 | 17337867 | 3923690 | 13414177 | 21092443 | 4389953 | 16702490 | 14728651 | 3627817 | 11100834 | 17337867 | 3923690 | 13414177 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2015 | Q1 | Q1 - 2015 | 11188208 | 2924730 | 8263478 | 9968887 | 2409983 | 7558904 | 10110000 | 2410000 | 7700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190225 | 881533 | 1308692 | 2058579 | 954836 | 1103743 | 2100000 | 990000 | 1110000 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400107 | 0 | 1400107 | 1401107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 2048113 | 0 | 2048113 | 1484611 | 0 | 1484611 | 1610000 | 0 | 1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797023 | 0 | 2797023 | 2306858 | 0 | 2306858 | 2310000 | 0 | 2310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420007 | 0 | 420007 | 406287 | 0 | 406287 | 406287 | 0 | 406287 | 21092443 | 4389953 | 16702490 | 18675089 | 3948509 | 14726580 | 18986154 | 3983690 | 15002464 | 21092443 | 4389953 | 16702490 | 18675089 | 3948509 | 14726580 | 18986154 | 3983690 | 15002464 | 0 | 0 | Charlotte, City of
NT10BIX5570088 | INF | 2015 | Q2 | Q2 - 2015 | 11188208 | 2924730 | 8263478 | 10021509 | 2462606 | 7558904 | 10021509 | 2462606 | 7558904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190225 | 881533 | 1308692 | 2173846 | 984076 | 1189769 | 2190000 | 990000 | 1200000 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 1048760 | 583690 | 465070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400107 | 0 | 1400107 | 1401107 | 0 | 1401107 | 1401107 | 0 | 1401107 | 2048113 | 0 | 2048113 | 1608559 | 0 | 1608559 | 1626000 | 0 | 1626000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2797023 | 0 | 2797023 | 2428223 | 0 | 2428223 | 2428223 | 0 | 2428223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420007 | 0 | 420007 | 406287 | 0 | 406287 | 406287 | 0 | 406287 | 21092443 | 4389953 | 16702490 | 19088291 | 4030372 | 15057919 | 19121886 | 4036296 | 15085591 | 21092443 | 4389953 | 16702490 | 19088291 | 4030372 | 15057919 | 19121886 | 4036296 | 15085591 | 0 | 0 | Charlotte, City of
NT10BIX5570089 | INF | 2010 | Q4 | Q4 - 2010 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 342000 | 103000 | 239000 | 642000 | 194000 | 448000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 0 | 0 | 0 | 265000 | 80000 | 185000 | 3362099 | 1319009 | 2043090 | 139000 | 42000 | 97000 | 353000 | 107000 | 246000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 5000 | 11000 | 73000 | 22000 | 51000 | 72483637 | 21890086 | 50593551 | 497000 | 150000 | 347000 | 1333000 | 403000 | 930000 | 72483637 | 21890086 | 50593551 | 497000 | 150000 | 347000 | 1333000 | 403000 | 930000 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2011 | Q1 | Q1 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 574000 | 173000 | 401000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 157000 | 47000 | 110000 | 537000 | 162000 | 375000 | 3362099 | 1319009 | 2043090 | 263000 | 79000 | 184000 | 531000 | 161000 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 16000 | 35000 | 127000 | 38000 | 89000 | 72483637 | 21890086 | 50593551 | 1020000 | 308000 | 712000 | 1769000 | 534000 | 1235000 | 72483637 | 21890086 | 50593551 | 1020000 | 308000 | 712000 | 1769000 | 534000 | 1235000 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2011 | Q2 | Q2 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 574000 | 173000 | 401000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 187000 | 57000 | 130000 | 1247000 | 377000 | 870000 | 3362099 | 1319009 | 2043090 | 494000 | 149000 | 345000 | 725000 | 219000 | 506000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103000 | 31000 | 72000 | 180000 | 54000 | 126000 | 72483637 | 21890086 | 50593551 | 1333000 | 403000 | 930000 | 2726000 | 823000 | 1903000 | 72483637 | 21890086 | 50593551 | 1333000 | 403000 | 930000 | 2726000 | 823000 | 1903000 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2011 | Q3 | Q3 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 694000 | 210000 | 484000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 483000 | 146000 | 337000 | 1228000 | 371000 | 857000 | 3362099 | 1319009 | 2043090 | 431000 | 130000 | 301000 | 579000 | 175000 | 404000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 51000 | 119000 | 266000 | 80000 | 186000 | 72483637 | 21890086 | 50593551 | 1633000 | 493000 | 1140000 | 2767000 | 836000 | 1931000 | 72483637 | 21890086 | 50593551 | 1633000 | 493000 | 1140000 | 2767000 | 836000 | 1931000 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2011 | Q4 | Q4 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 708276 | 213899 | 494377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 868864 | 262397 | 606467 | 2090435 | 631311 | 1459124 | 3362099 | 1319009 | 2043090 | 574802 | 173590 | 401212 | 749602 | 226380 | 523222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251881 | 76068 | 175813 | 364514 | 110083 | 254431 | 72483637 | 21890086 | 50593551 | 2378823 | 718404 | 1660419 | 3912827 | 1181673 | 2731154 | 72483637 | 21890086 | 50593551 | 2378823 | 718404 | 1660419 | 3912827 | 1181673 | 2731154 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2012 | Q1 | Q1 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 708276 | 213899 | 494377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 1260422 | 380647 | 879775 | 2237282 | 675659 | 1561623 | 3362099 | 1319009 | 2043090 | 773370 | 233559 | 539811 | 948170 | 286347 | 661823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322607 | 97427 | 225180 | 401457 | 121240 | 280217 | 72483637 | 21890086 | 50593551 | 3039675 | 917982 | 2121693 | 4295185 | 1297145 | 2998040 | 72483637 | 21890086 | 50593551 | 3039675 | 917982 | 2121693 | 4295185 | 1297145 | 2998040 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2012 | Q2 | Q2 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683279 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 2119863 | 640199 | 1479664 | 2733090 | 825393 | 1907697 | 3362099 | 1319009 | 2043090 | 1014178 | 306282 | 707896 | 1314178 | 396882 | 917296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392200 | 118444 | 273756 | 460919 | 139198 | 321721 | 72483637 | 21890086 | 50593551 | 4209517 | 1271274 | 2938243 | 5191466 | 1567822 | 3623641 | 72483637 | 21890086 | 50593551 | 4209517 | 1271274 | 2938243 | 5191466 | 1567822 | 3623641 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2012 | Q3 | Q3 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 693276 | 209369 | 483907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 2778334 | 839057 | 1939277 | 3340800 | 1008922 | 2331878 | 3362099 | 1319009 | 2043090 | 1223655 | 369544 | 854111 | 1420002 | 428841 | 991161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521856 | 157601 | 364255 | 577256 | 174331 | 402925 | 72483637 | 21890086 | 50593551 | 5207121 | 1572551 | 3634570 | 6031334 | 1821463 | 4209871 | 72483637 | 21890086 | 50593551 | 5207121 | 1572551 | 3634570 | 6031334 | 1821463 | 4209871 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2012 | Q4 | Q4 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683276 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3711826 | 1120971 | 2590855 | 3869026 | 1168446 | 2700580 | 3362099 | 1319009 | 2043090 | 1405085 | 424336 | 980749 | 1606898 | 485283 | 1121615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 569142 | 171881 | 397261 | 591490 | 178630 | 412860 | 72483637 | 21890086 | 50593551 | 6369329 | 1923537 | 4445792 | 6750690 | 2038708 | 4711982 | 72483637 | 21890086 | 50593551 | 6369329 | 1923537 | 4445792 | 6750690 | 2038708 | 4711982 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2013 | Q1 | Q1 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683276 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3817045 | 1152747 | 2664298 | 3974245 | 1200222 | 2774023 | 3362099 | 1319009 | 2043090 | 1598031 | 482606 | 1115425 | 1799844 | 543553 | 1256291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580875 | 175425 | 405451 | 589142 | 177921 | 411221 | 72483637 | 21890086 | 50593551 | 6679227 | 2017127 | 4662101 | 7046507 | 2128045 | 4918462 | 72483637 | 21890086 | 50593551 | 6679227 | 2017127 | 4662101 | 7046507 | 2128045 | 4918462 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2013 | Q2 | Q2 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 703276 | 212389 | 490887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3979169 | 1201709 | 2777460 | 4298769 | 1298228 | 3000541 | 3362099 | 1319009 | 2043090 | 1750555 | 528668 | 1221887 | 1938105 | 585308 | 1352797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578419 | 174683 | 403736 | 602349 | 181909 | 420440 | 72483637 | 21890086 | 50593551 | 6991419 | 2111409 | 4880010 | 7542499 | 2277834 | 5264665 | 72483637 | 21890086 | 50593551 | 6991419 | 2111409 | 4880010 | 7542499 | 2277834 | 5264665 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2013 | Q3 | Q3 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 794901 | 240060 | 554841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 4174577 | 1260722 | 2913855 | 4758577 | 1437090 | 3321487 | 3362099 | 1319009 | 2043090 | 2009317 | 606814 | 1402503 | 2199317 | 664194 | 1535123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486598 | 146953 | 339645 | 510501 | 154171 | 356330 | 72483637 | 21890086 | 50593551 | 7353768 | 2220838 | 5132930 | 8263296 | 2495515 | 5767781 | 72483637 | 21890086 | 50593551 | 7353768 | 2220838 | 5132930 | 8263296 | 2495515 | 5767781 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570089 | INF | 2013 | Q4 | Q4 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 808101 | 244046 | 564055 | 808101 | 244046 | 564055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 5003818 | 1511154 | 3492664 | 5003818 | 1511154 | 3492664 | 3362099 | 1319009 | 2043090 | 2247933 | 678876 | 1569057 | 2247933 | 678876 | 1569057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455286 | 137496 | 317790 | 455286 | 137496 | 317790 | 72483637 | 21890086 | 50593551 | 8515138 | 2571572 | 5943566 | 8515138 | 2571572 | 5943566 | 72483637 | 21890086 | 50593551 | 8515138 | 2571572 | 5943566 | 8515138 | 2571572 | 5943566 | 0 | 0 | Motorola Solutions, Inc.
NT10BIX5570090 | INF | 2010 | Q4 | Q4 - 2010 | 3448757 | 1034627 | 2414130 | 0 | 0 | 0 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 106706 | 32012 | 74694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 12023 | 3607 | 8416 | 313841 | 94152 | 219689 | 167377 | 50213 | 117164 | 1365 | 409 | 956 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13388 | 4016 | 9372 | 3346929 | 1004078 | 2342851 | 15401653 | 4620496 | 10781157 | 13388 | 4016 | 9372 | 3346929 | 1004078 | 2342851 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2011 | Q1 | Q1 - 2011 | 3448757 | 1034627 | 2414130 | 212563 | 63769 | 148794 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 106706 | 32012 | 74694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 65339 | 19602 | 45737 | 376609 | 112983 | 263626 | 167377 | 50213 | 117164 | 56421 | 16926 | 39495 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 334323 | 100297 | 234026 | 3409697 | 1022909 | 2386788 | 15401653 | 4620496 | 10781157 | 334323 | 100297 | 234026 | 3409697 | 1022909 | 2386788 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2011 | Q2 | Q2 - 2011 | 3448757 | 1034627 | 2414130 | 212563 | 63769 | 148794 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 213412 | 64023 | 149389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 102658 | 30797 | 71861 | 406609 | 121982 | 284627 | 167377 | 50213 | 117164 | 77470 | 23241 | 54229 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 94150 | 28245 | 65905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 392691 | 117807 | 274884 | 3640553 | 1092164 | 2548389 | 15401653 | 4620496 | 10781157 | 392691 | 117807 | 274884 | 3640553 | 1092164 | 2548389 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2011 | Q3 | Q3 - 2011 | 3448757 | 1034627 | 2414130 | 391309 | 117393 | 273916 | 800000 | 240000 | 560000 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 165172 | 49552 | 115620 | 230000 | 69000 | 161000 | 167377 | 50213 | 117164 | 82470 | 24741 | 57729 | 110000 | 33000 | 77000 | 941506 | 282452 | 659054 | 777 | 233 | 544 | 70000 | 21000 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 639728 | 191919 | 447809 | 3010000 | 903000 | 2107000 | 15401653 | 4620496 | 10781157 | 639728 | 191919 | 447809 | 3010000 | 903000 | 2107000 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2011 | Q4 | Q4 - 2011 | 3448757 | 1034627 | 2414130 | 1402907 | 420872 | 982035 | 2500000 | 750000 | 1750000 | 9860644 | 2958193 | 6902451 | 1274665 | 382399 | 892266 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 271140 | 81342 | 189798 | 350000 | 105000 | 245000 | 167377 | 50213 | 117164 | 94225 | 28268 | 65957 | 120000 | 36000 | 84000 | 941506 | 282452 | 659054 | 119438 | 35832 | 83606 | 140000 | 42000 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 3162375 | 948713 | 2213662 | 4910000 | 1473000 | 3437000 | 15401653 | 4620496 | 10781157 | 3162375 | 948713 | 2213662 | 4910000 | 1473000 | 3437000 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2012 | Q1 | Q1 - 2012 | 3448757 | 1034627 | 2414130 | 2397623 | 719287 | 1678336 | 3448757 | 1034627 | 2414130 | 9860644 | 2958193 | 6902451 | 2206575 | 661973 | 1544602 | 5097000 | 1529100 | 3567900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 28165 | 8449 | 19716 | 35000 | 10500 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 344626 | 103388 | 241238 | 546140 | 163842 | 382298 | 167377 | 50213 | 117164 | 109188 | 32756 | 76432 | 140000 | 42000 | 98000 | 941506 | 282452 | 659054 | 194797 | 58439 | 136358 | 419438 | 125831 | 293607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 5280974 | 1584292 | 3696682 | 9686335 | 2905900 | 6780435 | 15401653 | 4620496 | 10781157 | 5280974 | 1584292 | 3696682 | 9686335 | 2905900 | 6780435 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2012 | Q2 | Q2 - 2012 | 3448757 | 1034627 | 2414130 | 4535927 | 1360777 | 3175150 | 4535927 | 1360778 | 3175149 | 9860644 | 2958193 | 6902451 | 3136115 | 940835 | 2195280 | 6743064 | 2022919 | 4720145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 76765 | 23029 | 53736 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 478469 | 143541 | 334928 | 576140 | 172842 | 403298 | 167377 | 50213 | 117164 | 135130 | 40539 | 94591 | 150000 | 45000 | 105000 | 941506 | 282452 | 659054 | 235626 | 70688 | 164938 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 8598032 | 2579409 | 6018623 | 12585131 | 3775539 | 8809592 | 15401653 | 4620496 | 10781157 | 8598032 | 2579409 | 6018623 | 12585131 | 3775539 | 8809592 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2012 | Q3 | Q3 - 2012 | 3448757 | 1034627 | 2414130 | 4339105 | 1301731 | 3037374 | 4339105 | 1301731 | 3037374 | 9860644 | 2958193 | 6902451 | 5662808 | 1698842 | 3963966 | 7533000 | 2259900 | 5273100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 86605 | 25982 | 60623 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 494074 | 148222 | 345852 | 596140 | 178842 | 417298 | 167377 | 50213 | 117164 | 151409 | 45423 | 105986 | 160000 | 48000 | 112000 | 941506 | 282452 | 659054 | 514737 | 154421 | 360316 | 650000 | 195000 | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 11248738 | 3374621 | 7874117 | 13368245 | 4010473 | 9357772 | 15401653 | 4620496 | 10781157 | 11248738 | 3374621 | 7874117 | 13368245 | 4010473 | 9357772 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2012 | Q4 | Q4 - 2012 | 3448757 | 1034627 | 2414130 | 4351385 | 1305415 | 3045970 | 4351385 | 1305415 | 3045970 | 9860644 | 2958193 | 6902451 | 7189227 | 2156768 | 5032459 | 7983000 | 2394900 | 5588100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 86605 | 25982 | 60623 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 516520 | 154956 | 361564 | 616140 | 184842 | 431298 | 167377 | 50213 | 117164 | 166874 | 50061 | 116813 | 175000 | 52500 | 122500 | 941506 | 282452 | 659054 | 629425 | 188827 | 440598 | 734438 | 220331 | 514107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 12940036 | 3882009 | 9058027 | 13949963 | 4184988 | 9764975 | 15401653 | 4620496 | 10781157 | 12940036 | 3882009 | 9058027 | 13949963 | 4184988 | 9764975 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2013 | Q1 | Q1 - 2013 | 3448757 | 1034627 | 2414130 | 4570876 | 1371263 | 3199613 | 4570876 | 1371263 | 3199613 | 9860644 | 2958193 | 6902451 | 7391164 | 2217349 | 5173815 | 8500000 | 2550000 | 5950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 87155 | 26146 | 61009 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 638973 | 191692 | 447281 | 650000 | 195000 | 455000 | 167377 | 50213 | 117164 | 173860 | 52158 | 121702 | 180000 | 54000 | 126000 | 941506 | 282452 | 659054 | 697642 | 209293 | 488349 | 850000 | 255000 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13559670 | 4067901 | 9491769 | 14840876 | 4452263 | 10388613 | 15401653 | 4620496 | 10781157 | 13559670 | 4067901 | 9491769 | 14840876 | 4452263 | 10388613 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2013 | Q2 | Q2 - 2013 | 3448757 | 1034627 | 2414130 | 4570876 | 1371263 | 3199613 | 4598580 | 1379575 | 3219005 | 9860644 | 2958193 | 6902451 | 7429399 | 2228820 | 5200579 | 8983608 | 2695082 | 6288526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 87155 | 26146 | 61009 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 641554 | 192466 | 449088 | 665000 | 199500 | 465500 | 167377 | 50213 | 117164 | 179702 | 53911 | 125791 | 200000 | 60000 | 140000 | 941506 | 282452 | 659054 | 699970 | 209991 | 489979 | 864465 | 259339 | 605126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13608656 | 4082597 | 9526059 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 13608656 | 4082597 | 9526059 | 15401653 | 4620496 | 10781157 | 0 | 0 | DCN, LLC
NT10BIX5570090 | INF | 2013 | Q3 | Q3 - 2013 | 3448757 | 1034627 | 2414130 | 4487315 | 1346194 | 3141121 | 4487315 | 1346194 | 3141121 | 9860644 | 2958193 | 6902451 | 8841647 | 2652494 | 6189153 | 8841647 | 2652494 | 6189153 | 0 | 0 | 0 | 149373 | 44812 | 104561 | 149373 | 44812 | 104561 | 355687 | 106706 | 248981 | 88105 | 26432 | 61673 | 88105 | 26432 | 61673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 705278 | 211583 | 493695 | 705278 | 211583 | 493695 | 167377 | 50213 | 117164 | 203290 | 60987 | 142303 | 203290 | 60987 | 142303 | 941506 | 282452 | 659054 | 926645 | 277994 | 648651 | 926645 | 277994 | 648651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 0 | 0 | DCN, LLC
NT10BIX5570091 | INF | 2010 | Q4 | Q4 - 2010 | 17879350 | 3036520 | 14842830 | 0 | 0 | 0 | 0 | 0 | 0 | 29509500 | 4932099 | 24577401 | 0 | 0 | 0 | 0 | 0 | 0 | 1818980 | 303120 | 1515860 | 289742 | 49256 | 240486 | 379894 | 64582 | 315312 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 492650 | 2457350 | 278678 | 47375 | 231302 | 1970000 | 334900 | 1635100 | 1250000 | 208750 | 1041250 | 0 | 0 | 0 | 0 | 0 | 0 | 704720 | 129629 | 575091 | 0 | 0 | 0 | 0 | 0 | 0 | 190800 | 55332 | 135468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 568420 | 96631 | 471788 | 2349894 | 399482 | 1950412 | 64803350 | 19658100 | 45145250 | 568420 | 96631 | 471788 | 2349894 | 399482 | 1950412 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2011 | Q1 | Q1 - 2011 | 17879350 | 3036520 | 14842830 | 0 | 0 | 0 | 3575870 | 607898 | 2967972 | 29509500 | 4932099 | 24577401 | 0 | 0 | 0 | 1250000 | 212500 | 1037500 | 1818980 | 303120 | 1515860 | 401582 | 68269 | 333313 | 657894 | 111842 | 546052 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 492650 | 2457350 | 1468487 | 249643 | 1218844 | 2950000 | 501500 | 2448500 | 1250000 | 208750 | 1041250 | 0 | 0 | 0 | 0 | 0 | 0 | 704720 | 129629 | 575091 | 0 | 0 | 0 | 117000 | 19890 | 97110 | 190800 | 55332 | 135468 | 0 | 0 | 0 | 48000 | 8160 | 39840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 1870069 | 317912 | 1552157 | 8598764 | 1461790 | 7136974 | 64803350 | 19658100 | 45145250 | 1870069 | 317912 | 1552157 | 8598764 | 1461790 | 7136974 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2011 | Q2 | Q2 - 2011 | 15886941 | 2678732 | 13208209 | 1065288 | 181099 | 884189 | 2000000 | 340000 | 1660000 | 33319581 | 5620036 | 27699545 | 7042 | 1197 | 5845 | 415000 | 70550 | 344450 | 1611500 | 271699 | 1339801 | 885288 | 150499 | 734789 | 1005000 | 170850 | 834150 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2463781 | 418843 | 2044938 | 2900000 | 493000 | 2407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 20438 | 3474 | 16964 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 30738 | 5225 | 25513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 4421399 | 751638 | 3669761 | 11371176 | 6083099 | 5288077 | 64803350 | 19658100 | 45145250 | 4421399 | 751638 | 3669761 | 11371176 | 6083099 | 5288077 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2011 | Q3 | Q3 - 2011 | 15886941 | 2678732 | 13208209 | 2309191 | 392563 | 1916629 | 4500000 | 765000 | 3735000 | 33319581 | 5620036 | 27699545 | 802796 | 136475 | 666321 | 4250000 | 722500 | 3527500 | 1611500 | 271699 | 1339801 | 1154871 | 196328 | 958543 | 1355000 | 230350 | 1124650 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2689957 | 457293 | 2232664 | 2900000 | 493000 | 2407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 12000 | 2040 | 9960 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 6956815 | 1182659 | 5774157 | 13017000 | 2212890 | 10804110 | 64803350 | 19658100 | 45145250 | 6956815 | 1182659 | 5774157 | 13017000 | 2212890 | 10804110 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2011 | Q4 | Q4 - 2011 | 15886941 | 2678732 | 13208209 | 6517837 | 1108032 | 5409805 | 10000000 | 1700000 | 8300000 | 33319581 | 5620036 | 27699545 | 5000105 | 850018 | 4150087 | 9000000 | 1530000 | 7470000 | 1611500 | 271699 | 1339801 | 1349482 | 229412 | 1120070 | 1500000 | 255000 | 1245000 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2943443 | 500385 | 2443058 | 3200000 | 544000 | 2656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 50000 | 8500 | 41500 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 29297 | 4980 | 24317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 15810867 | 2687847 | 13123020 | 23779297 | 4042480 | 19736817 | 64803350 | 19658100 | 45145250 | 15810867 | 2687847 | 13123020 | 23779297 | 4042480 | 19736817 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2012 | Q1 | Q1 - 2012 | 15886941 | 2678732 | 13208209 | 8148479 | 1385242 | 6763238 | 14298247 | 2430702 | 11867545 | 33319581 | 5620036 | 27699545 | 11744101 | 1996497 | 9747604 | 19500000 | 3315000 | 16185000 | 1611500 | 271699 | 1339801 | 1506226 | 256058 | 1250168 | 1750000 | 297500 | 1452500 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3161047 | 537378 | 2623669 | 3240000 | 550800 | 2689200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 24559853 | 4175175 | 20384679 | 49728247 | 17168802 | 32559445 | 64803350 | 19658100 | 45145250 | 24559853 | 4175175 | 20384679 | 49728247 | 17168802 | 32559445 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2012 | Q2 | Q2 - 2012 | 15886941 | 2678732 | 13208209 | 11797174 | 2005520 | 9791654 | 14298247 | 2430702 | 11867545 | 33319581 | 5620036 | 27699545 | 20131727 | 3422394 | 16709333 | 26750000 | 4547500 | 22202500 | 1611500 | 271699 | 1339801 | 1507189 | 256222 | 1250967 | 1610000 | 273700 | 1336300 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3489155 | 593156 | 2895999 | 3600000 | 612000 | 2988000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44037 | 7486 | 36551 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 36969282 | 6284778 | 30684504 | 57198247 | 18438702 | 38759545 | 64803350 | 19658100 | 45145250 | 36969282 | 6284778 | 30684504 | 57198247 | 18438702 | 38759545 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2012 | Q3 | Q3 - 2012 | 15886941 | 2678732 | 13208209 | 12799209 | 2175866 | 10623343 | 15500000 | 2635000 | 12865000 | 33319581 | 5620036 | 27699545 | 27734367 | 4714842 | 23019525 | 30000000 | 5100000 | 24900000 | 1611500 | 271699 | 1339801 | 1640623 | 278906 | 1361717 | 1675000 | 284750 | 1390250 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3550877 | 603649 | 2947228 | 3600000 | 612000 | 2988000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 56269502 | 18280815 | 37988687 | 61715000 | 19206550 | 42508450 | 64803350 | 19658100 | 45145250 | 56269502 | 18280815 | 37988687 | 61715000 | 19206550 | 42508450 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2012 | Q4 | Q4 - 2012 | 15886941 | 2678732 | 13208209 | 13098954 | 2226822 | 10872132 | 13500000 | 2295000 | 11205000 | 33319581 | 5620036 | 27699545 | 31362792 | 5331674 | 26031118 | 33500000 | 5695000 | 27805000 | 1611500 | 271699 | 1339801 | 1652003 | 280841 | 1371162 | 1667003 | 283391 | 1383612 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3612940 | 614200 | 2998740 | 3624940 | 616240 | 3008700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 60271115 | 18961089 | 41310026 | 63231943 | 19464431 | 43767512 | 64803350 | 19658100 | 45145250 | 60271115 | 18961089 | 41310026 | 63231943 | 19464431 | 43767512 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2013 | Q1 | Q1 - 2013 | 15886941 | 2678732 | 13208209 | 13517732 | 2298014 | 11219717 | 13667732 | 2323514 | 11344217 | 33319581 | 5620036 | 27699545 | 33828896 | 5750912 | 28077984 | 35328896 | 6384729 | 28944167 | 1611500 | 271699 | 1339801 | 1764705 | 300000 | 1464706 | 1774705 | 301700 | 1473006 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3632940 | 617600 | 3015340 | 3636940 | 618280 | 3018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 63288699 | 19474078 | 43814621 | 65348273 | 20203023 | 45145250 | 64803350 | 19658100 | 45145250 | 63288699 | 19474078 | 43814621 | 65348273 | 20203023 | 45145250 | 0 | 0 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2013 | Q2 | Q2 - 2013 | 15886941 | 2678732 | 13208209 | 13618005 | 2315061 | 11302944 | 13722603 | 2419659 | 11302944 | 33319581 | 5620036 | 27699545 | 36211132 | 6894224 | 29316908 | 41001548 | 11647290 | 29354258 | 1611500 | 271699 | 1339801 | 1770920 | 301056 | 1469864 | 1780146 | 347632 | 1432514 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3636940 | 618280 | 3018660 | 3650940 | 632280 | 3018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 0 | 0 | 0 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 44426 | 7552 | 36874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 65781423 | 20636173 | 45145250 | 70699663 | 25554413 | 45145250 | 64803350 | 19658100 | 45145250 | 65781423 | 20636173 | 45145250 | 70699663 | 25554413 | 45145250 | 0 | 234647 | Bluebird Media, L.L.C.
NT10BIX5570091 | INF | 2013 | Q3 | Q3 - 2013 | 15886941 | 2678732 | 13208209 | 13707690 | 2405007 | 11302683 | 13707690 | 2405007 | 11302683 | 33319581 | 5620036 | 27699545 | 39834289 | 10494741 | 29339548 | 39834289 | 10494741 | 29339548 | 1611500 | 271699 | 1339801 | 1756390 | 321079 | 1435311 | 1756390 | 321079 | 1435311 | 10500000 | 10500000 | 0 | 12675000 | 12675000 | 0 | 12675000 | 12675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3651607 | 620773 | 3030834 | 3651607 | 620773 | 3030834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 0 | 0 | 0 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 44426 | 7552 | 36874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 71669402 | 26524152 | 45145250 | 71669402 | 26524152 | 45145250 | 64803350 | 19658100 | 45145250 | 71669402 | 26524152 | 45145250 | 71669402 | 26524152 | 45145250 | 0 | 326923 | Bluebird Media, L.L.C.
NT10BIX5570093 | INF | 2010 | Q4 | Q4 - 2010 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 545000 | 109000 | 436000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 80000 | 16000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 0 | 0 | 0 | 625000 | 125000 | 500000 | 11560803 | 2323043 | 9237760 | 0 | 0 | 0 | 625000 | 125000 | 500000 | 2583000 | 0 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2011 | Q1 | Q1 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 545000 | 109000 | 436000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 403000 | 80600 | 322400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 140000 | 28000 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 49654 | 49654 | 0 | 77404 | 77404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 49654 | 49654 | 0 | 1165404 | 295004 | 870400 | 11560803 | 2323043 | 9237760 | 49654 | 49654 | 0 | 1165404 | 295004 | 870400 | 2583000 | 0 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2011 | Q2 | Q2 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 900000 | 180000 | 720000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 635984 | 127197 | 508787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 223130 | 44626 | 178504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 74767 | 74767 | 0 | 101880 | 101880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 74767 | 74767 | 0 | 1860994 | 453703 | 1407291 | 11560803 | 2323043 | 9237760 | 74767 | 74767 | 0 | 1860994 | 453703 | 1407291 | 2583000 | 0 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2011 | Q3 | Q3 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 872000 | 174400 | 697600 | 9819064 | 1581304 | 8237760 | 586069 | 117214 | 468855 | 962736 | 192547 | 770189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 143365 | 28673 | 114692 | 227928 | 45586 | 182342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 95943 | 95943 | 0 | 122807 | 122807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 825377 | 241830 | 583547 | 2185471 | 535340 | 1650131 | 11560803 | 2323043 | 9237760 | 825377 | 241830 | 583547 | 2185471 | 535340 | 1650131 | 2583000 | 0 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2011 | Q4 | Q4 - 2011 | 1090000 | 218000 | 872000 | 452153 | 90431 | 361722 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 660657 | 132131 | 528526 | 1774255 | 354851 | 1419404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 230131 | 46026 | 184105 | 234513 | 46902 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 120693 | 120693 | 0 | 148352 | 148352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 1463634 | 389281 | 1074353 | 3028668 | 724415 | 2304253 | 11560803 | 2323043 | 9237760 | 1463634 | 389281 | 1074353 | 3028668 | 724415 | 2304253 | 2583000 | 1000 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2012 | Q1 | Q1 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 916841 | 183368 | 733473 | 9819064 | 1581304 | 8237760 | 1389717 | 277943 | 1111774 | 3030809 | 606162 | 2424647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 235499 | 47100 | 188399 | 274353 | 54871 | 219482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 144594 | 144594 | 0 | 171102 | 171102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 2641358 | 643947 | 1997411 | 4393105 | 1015503 | 3377602 | 11560803 | 2323043 | 9237760 | 2641358 | 643947 | 1997411 | 4393105 | 1015503 | 3377602 | 2583000 | 2500 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2012 | Q2 | Q2 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 1952808 | 390561 | 1562247 | 5200000 | 1040000 | 4160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 314829 | 62966 | 251863 | 314829 | 62966 | 251863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 177556 | 177556 | 0 | 216639 | 216639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 3316741 | 805393 | 2511348 | 6603016 | 1493915 | 5109101 | 11560803 | 2323043 | 9237760 | 3316741 | 805393 | 2511348 | 6603016 | 1493915 | 5109101 | 2583000 | 4000 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2012 | Q3 | Q3 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 3511854 | 702371 | 2809483 | 8293263 | 1658653 | 6634610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 321566 | 64313 | 257253 | 321566 | 64313 | 257253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 209094 | 209094 | 0 | 241344 | 241344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 4914062 | 1150088 | 3763974 | 9727721 | 2138620 | 7589101 | 11560803 | 2323043 | 9237760 | 4914062 | 1150088 | 3763974 | 9727721 | 2138620 | 7589101 | 2583000 | 6500 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2012 | Q4 | Q4 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 6021949 | 1204390 | 4817559 | 8360081 | 1672016 | 6688065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 322566 | 64513 | 258053 | 322566 | 64513 | 258053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 247441 | 247441 | 0 | 282384 | 282384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 7463504 | 1690654 | 5772850 | 9836579 | 2193223 | 7643356 | 11560803 | 2323043 | 9237760 | 7463504 | 1690654 | 5772850 | 9836579 | 2193223 | 7643356 | 2583000 | 12500 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2013 | Q1 | Q1 - 2013 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 7970099 | 1594020 | 6376079 | 9404966 | 1811280 | 7593686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 323896 | 64779 | 259117 | 323896 | 64779 | 259117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 258077 | 258077 | 0 | 272674 | 272674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 9423620 | 2091186 | 7332434 | 10873084 | 2323043 | 8550041 | 11560803 | 2323043 | 9237760 | 9423620 | 2091186 | 7332434 | 10873084 | 2323043 | 8550041 | 2583000 | 20000 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2013 | Q2 | Q2 - 2013 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 1172934 | 174310 | 998624 | 9819064 | 1581304 | 8237760 | 8415015 | 1683003 | 6732012 | 9285795 | 1699659 | 7586136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 323896 | 64779 | 259117 | 323896 | 64779 | 259117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 268685 | 268685 | 0 | 272221 | 272221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 9879144 | 2190777 | 7688367 | 11054846 | 2210969 | 8843877 | 11560803 | 2323043 | 9237760 | 9879144 | 2190777 | 7688367 | 11054846 | 2210969 | 8843877 | 2583000 | 27500 | Citizens' Telephone Co-operative
NT10BIX5570093 | INF | 2013 | Q3 | Q3 - 2013 | 1090000 | 218000 | 872000 | 1197782 | 174310 | 1023472 | 1197782 | 174310 | 1023472 | 9819064 | 1581304 | 8237760 | 9283920 | 1705777 | 7578143 | 9283920 | 1705777 | 7578143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 337946 | 64779 | 273167 | 337946 | 64779 | 273167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 273829 | 273829 | 0 | 273829 | 273829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 11093477 | 2218695 | 8874782 | 11093477 | 2218695 | 8874782 | 11560803 | 2323043 | 9237760 | 11093477 | 2218695 | 8874782 | 11093477 | 2218695 | 8874782 | 2583000 | 68371 | Citizens' Telephone Co-operative
NT10BIX5570094 | INF | 2010 | Q4 | Q4 - 2010 | 51441480 | 1133078 | 50308402 | 0 | 0 | 0 | 9125937 | 1133079 | 7586338 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12799710 | 12799710 | 0 | 0 | 0 | 0 | 7319873 | 7319873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17985220 | 0 | 17985220 | 0 | 0 | 0 | 1791995 | 0 | 1791995 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 406520 | 0 | 406520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 0 | 0 | 0 | 18719325 | 8452952 | 9859853 | 83987788 | 13932788 | 70055000 | 0 | 0 | 0 | 18719325 | 8452952 | 9859853 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2011 | Q1 | Q1 - 2011 | 51441480 | 1133078 | 50308402 | 1184979 | 1184979 | 0 | 6301861 | 2083193 | 4218668 | 75000 | 0 | 75000 | 0 | 0 | 0 | 867917 | 0 | 867917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12799710 | 12799710 | 0 | 3677823 | 3677823 | 0 | 5440866 | 5440866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17985220 | 0 | 17985220 | 106165 | 106165 | 0 | 700104 | 107700 | 592403 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 938983 | 0 | 938983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 4968967 | 4968967 | 0 | 14249731 | 7631759 | 6617971 | 83987788 | 13932788 | 70055000 | 4968967 | 4968967 | 0 | 14249731 | 7631759 | 6617971 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2011 | Q2 | Q2 - 2011 | 51233355 | 2083193 | 49150162 | 2015789 | 2015789 | 0 | 12090698 | 1252383 | 10838315 | 11813924 | 0 | 11813924 | 0 | 0 | 0 | 3212091 | 0 | 3212091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 5109503 | 5109503 | 0 | 7821900 | 7821900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 106165 | 106165 | 0 | 2308660 | 107700 | 2200960 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 1301740 | 0 | 1301740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84092847 | 14037847 | 70055000 | 7231457 | 7231457 | 0 | 26735089 | 9181983 | 17553106 | 84092847 | 14037847 | 70055000 | 7231457 | 7231457 | 0 | 26735089 | 9181983 | 17553106 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2011 | Q3 | Q3 - 2011 | 51233355 | 2083193 | 49150162 | 4816028 | 2015789 | 2800239 | 15834302 | 1252383 | 14581919 | 11813924 | 0 | 11813924 | 385634 | 0 | 385634 | 3182546 | 0 | 3182546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 5886703 | 5886703 | 0 | 7138159 | 7138159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 256082 | 106165 | 149917 | 1801604 | 107700 | 1693904 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 4851 | 0 | 4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84092847 | 14037847 | 70055000 | 11344447 | 8008657 | 3335790 | 27961462 | 8498242 | 19463220 | 84092847 | 14037847 | 70055000 | 11344447 | 8008657 | 3335790 | 27961462 | 8498242 | 19463220 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2011 | Q4 | Q4 - 2011 | 51128296 | 1978134 | 49150162 | 12356624 | 2015789 | 10340835 | 16633513 | 2015789 | 14617724 | 11813924 | 0 | 11813924 | 1041210 | 0 | 1041210 | 5622511 | 0 | 5622511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 6518553 | 6518553 | 0 | 6518553 | 6518553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 510940 | 106165 | 404775 | 1914914 | 106165 | 1808749 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 20427327 | 8640507 | 11786820 | 30689491 | 8640507 | 22048984 | 83987788 | 13932788 | 70055000 | 20427327 | 8640507 | 11786820 | 30689491 | 8640507 | 22048984 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2012 | Q1 | Q1 - 2012 | 51128296 | 1978134 | 49150162 | 18568009 | 1903814 | 16664195 | 24394867 | 1903814 | 22491053 | 11813924 | 0 | 11813924 | 2547265 | 0 | 2547265 | 4064832 | 0 | 4064832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 7832817 | 7832817 | 0 | 8939585 | 8939585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1219345 | 106165 | 1113180 | 1581564 | 106165 | 1475399 | 1686378 | 0 | 1686378 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 30172623 | 9842796 | 20329827 | 38986035 | 10949564 | 28036471 | 83987788 | 13932788 | 70055000 | 30172623 | 9842796 | 20329827 | 38986035 | 10949564 | 28036471 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2012 | Q2 | Q2 - 2012 | 51128296 | 1978134 | 49150162 | 21468249 | 1903814 | 19564435 | 26635770 | 1903814 | 24731956 | 11813924 | 0 | 11813924 | 3336542 | 0 | 3336542 | 4374689 | 0 | 4374689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 9315783 | 9315783 | 0 | 9871800 | 9871800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1252326 | 106165 | 1146161 | 2022746 | 106165 | 1916581 | 1686378 | 0 | 1686378 | 5188 | 0 | 5188 | 5188 | 0 | 5188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 35378088 | 11325762 | 24052326 | 42910193 | 11881779 | 31028414 | 83987788 | 13932788 | 70055000 | 35378088 | 11325762 | 24052326 | 42910193 | 11881779 | 31028414 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2012 | Q3 | Q3 - 2012 | 51128296 | 1978134 | 49150162 | 22616408 | 1903814 | 20712594 | 27077788 | 1903814 | 25173974 | 11813924 | 0 | 11813924 | 3598391 | 0 | 3598391 | 5269340 | 0 | 5269340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 9808085 | 9808085 | 0 | 10358870 | 10358870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1449637 | 106165 | 1343472 | 2424132 | 106165 | 2317967 | 1686378 | 0 | 1686378 | 5188 | 0 | 5188 | 5188 | 0 | 5188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 37477709 | 11818064 | 25659645 | 45135318 | 12368849 | 32766469 | 83987788 | 13932788 | 70055000 | 37477709 | 11818064 | 25659645 | 45135318 | 12368849 | 32766469 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2012 | Q4 | Q4 - 2012 | 59196021 | 2074111 | 57121910 | 22680140 | 1903814 | 20776326 | 24615512 | 1903814 | 22711698 | 6626607 | 0 | 626607 | 3598616 | 0 | 3598616 | 4547184 | 0 | 4547184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 10341186 | 10341186 | 0 | 10810536 | 10810536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 1449638 | 106165 | 1343473 | 2024467 | 106165 | 1918302 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 64055000 | 38074767 | 12351165 | 25723602 | 42002886 | 12820515 | 29182371 | 83987788 | 13932788 | 64055000 | 38074767 | 12351165 | 25723602 | 42002886 | 12820515 | 29182371 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2013 | Q1 | Q1 - 2013 | 59196021 | 2074111 | 57121910 | 22680140 | 1903814 | 20776326 | 25023761 | 1903814 | 23119947 | 6626607 | 0 | 6626607 | 3598616 | 0 | 3598616 | 4552326 | 0 | 4552326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 10810536 | 10810536 | 0 | 11279886 | 11279886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 1449638 | 106165 | 1343473 | 2026466 | 106165 | 1920301 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 38544117 | 12820515 | 25723602 | 42887626 | 13289865 | 29597761 | 83987788 | 13932788 | 70055000 | 38544117 | 12820515 | 25723602 | 42887626 | 13289865 | 29597761 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2013 | Q2 | Q2 - 2013 | 59196021 | 2074111 | 57121910 | 24006409 | 1903814 | 22102595 | 26437594 | 1903814 | 24533780 | 6626607 | 0 | 6626607 | 4549490 | 0 | 4549490 | 5365841 | 0 | 5365841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11319853 | 11319853 | 0 | 11331276 | 11331276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2026465 | 106165 | 1920300 | 2343317 | 106165 | 2237152 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 41907404 | 13329832 | 28577572 | 45483215 | 13341255 | 32141960 | 83987788 | 13932788 | 70055000 | 41907404 | 13329832 | 28577572 | 45483215 | 13341255 | 32141960 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2013 | Q3 | Q3 - 2013 | 59196021 | 2074111 | 57121910 | 26399978 | 1903814 | 24496164 | 27281704 | 1903814 | 25377890 | 6626607 | 0 | 6626607 | 5361116 | 0 | 5361116 | 5365226 | 0 | 5365226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11331275 | 11331275 | 0 | 11331275 | 11331275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2341957 | 106165 | 2235792 | 2341958 | 106165 | 2235793 | 3027406 | 0 | 3027406 | 5186 | 0 | 5186 | 5186 | 0 | 5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 45439512 | 13341254 | 32098258 | 46325349 | 13341254 | 32984095 | 83987788 | 13932788 | 70055000 | 45439512 | 13341254 | 32098258 | 46325349 | 13341254 | 32984095 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570094 | INF | 2013 | Q4 | Q4 - 2013 | 59196021 | 2074111 | 57121910 | 26412928 | 1903814 | 24509114 | 26453242 | 1903814 | 24549428 | 6626607 | 0 | 6626607 | 5362391 | 0 | 5362391 | 5361117 | 0 | 5361117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11331275 | 11331275 | 0 | 11331275 | 11331275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2341957 | 106165 | 2235792 | 2341957 | 106165 | 2235792 | 3027406 | 0 | 3027406 | 5186 | 0 | 5186 | 5186 | 0 | 5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 45453737 | 13341254 | 32112483 | 45492777 | 13341254 | 32151523 | 83987788 | 13932788 | 70055000 | 45453737 | 13341254 | 32112483 | 45492777 | 13341254 | 32151523 | 0 | 0 | Executive Office of the State of Mississippi
NT10BIX5570095 | INF | 2010 | Q4 | Q4 - 2010 | 2078817 | 162000 | 1916817 | 0 | 0 | 0 | 3000 | 0 | 3000 | 4470516 | 1312540 | 3157976 | 0 | 0 | 0 | 410000 | 400000 | 10000 | 510200 | 0 | 510200 | 55180 | 0 | 55180 | 157000 | 0 | 157000 | 486000 | 441000 | 45000 | 0 | 0 | 0 | 14500 | 13250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 34092 | 0 | 34092 | 142000 | 0 | 142000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 39787 | 28739 | 11048 | 45787 | 28739 | 17048 | 8199737 | 1930540 | 6269197 | 129059 | 28739 | 100320 | 797287 | 441989 | 355298 | 8199737 | 1930540 | 6269197 | 129059 | 28739 | 100320 | 797287 | 441989 | 355298 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2011 | Q1 | Q1 - 2011 | 2078817 | 162000 | 1916817 | 2797 | 0 | 2797 | 7787 | 0 | 7787 | 4470516 | 1312540 | 3157976 | 35507 | 0 | 35507 | 85000 | 0 | 85000 | 510200 | 0 | 510200 | 131599 | 0 | 131599 | 192000 | 0 | 192000 | 486000 | 441000 | 45000 | 0 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 146111 | 0 | 146111 | 180000 | 0 | 180000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 46262 | 28739 | 17523 | 51262 | 28739 | 22523 | 8199737 | 1930540 | 6269197 | 362276 | 28739 | 333537 | 621049 | 118739 | 502310 | 8199737 | 1930540 | 6269197 | 362276 | 28739 | 333537 | 621049 | 118739 | 502310 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2011 | Q2 | Q2 - 2011 | 2078817 | 162000 | 1916817 | 2797 | 0 | 2797 | 5500 | 0 | 5500 | 4470516 | 1312540 | 3157976 | 44248 | 0 | 44248 | 1420529 | 1312540 | 107989 | 510200 | 0 | 510200 | 197524 | 0 | 197524 | 263449 | 0 | 263449 | 486000 | 441000 | 45000 | 110250 | 110250 | 0 | 112500 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 178562 | 0 | 178562 | 221013 | 0 | 221013 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 51185 | 28739 | 22446 | 56108 | 28739 | 27369 | 8199737 | 1930540 | 6269197 | 584566 | 138989 | 445577 | 2079099 | 1453779 | 625320 | 8199737 | 1930540 | 6269197 | 584566 | 138989 | 445577 | 2079099 | 1453779 | 625320 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2011 | Q3 | Q3 - 2011 | 2078817 | 162000 | 1916817 | 5618 | 0 | 5618 | 10000 | 0 | 10000 | 4470516 | 1312540 | 3157976 | 73974 | 0 | 73974 | 1500000 | 1000000 | 500000 | 510200 | 0 | 510200 | 247253 | 0 | 247253 | 328000 | 0 | 328000 | 486000 | 441000 | 45000 | 148500 | 148500 | 0 | 181500 | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 204116 | 0 | 204116 | 305000 | 0 | 305000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 53544 | 28739 | 24805 | 56108 | 28739 | 27369 | 8199737 | 1930540 | 6269197 | 733935 | 177239 | 556696 | 2405608 | 1210239 | 1195369 | 8199737 | 1930540 | 6269197 | 733935 | 177239 | 556696 | 2405608 | 1210239 | 1195369 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2011 | Q4 | Q4 - 2011 | 2078817 | 162000 | 1916817 | 5618 | 0 | 5618 | 250000 | 0 | 250000 | 4470516 | 1312540 | 3157976 | 859963 | 0 | 859963 | 1365000 | 200000 | 1165000 | 510200 | 0 | 510200 | 314573 | 0 | 314573 | 365000 | 0 | 365000 | 486000 | 441000 | 45000 | 488890 | 475500 | 13390 | 493390 | 480000 | 13390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 231947 | 0 | 231947 | 275000 | 0 | 275000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 65000 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 61577 | 28739 | 32838 | 64739 | 28739 | 36000 | 8199737 | 1930540 | 6269197 | 1963498 | 504239 | 1459259 | 2878129 | 708739 | 2169390 | 8199737 | 1930540 | 6269197 | 1963498 | 504239 | 1459259 | 2878129 | 708739 | 2169390 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2012 | Q1 | Q1 - 2012 | 2078817 | 112000 | 1916817 | 147403 | 0 | 147403 | 950000 | 0 | 950000 | 4470516 | 1312540 | 3157976 | 1416438 | 0 | 1416438 | 4071000 | 1571000 | 2500000 | 510200 | 0 | 510200 | 357798 | 0 | 357798 | 397798 | 0 | 397798 | 536000 | 491000 | 45000 | 502117 | 477759 | 24358 | 505759 | 477759 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 254542 | 0 | 254542 | 314542 | 0 | 314542 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 66082 | 28739 | 37343 | 69082 | 28739 | 40343 | 8249737 | 1930540 | 6269197 | 2745310 | 506498 | 2238812 | 6309111 | 2077498 | 4206413 | 8249737 | 1930540 | 6269197 | 2745310 | 506498 | 2238812 | 6309111 | 2077498 | 4206413 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2012 | Q2 | Q2 - 2012 | 2078817 | 0 | 2078817 | 606150 | 0 | 606150 | 1200000 | 0 | 1200000 | 4587316 | 1591340 | 2995976 | 3505259 | 1571340 | 1933919 | 4151340 | 1571340 | 2580000 | 510200 | 0 | 510200 | 421875 | 0 | 421875 | 470000 | 0 | 470000 | 355461 | 310461 | 45000 | 331995 | 285320 | 46675 | 346675 | 300000 | 46675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 341276 | 0 | 341276 | 400000 | 0 | 400000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78739 | 28739 | 50000 | 71509 | 28739 | 42770 | 78739 | 28739 | 50000 | 8199737 | 1930540 | 6269197 | 5278994 | 1885399 | 3393595 | 6681754 | 1900079 | 4781675 | 8199737 | 1930540 | 6269197 | 5278994 | 1885399 | 3393595 | 6681754 | 1900079 | 4781675 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2012 | Q3 | Q3 - 2012 | 1838817 | 0 | 1838817 | 957314 | 0 | 957314 | 1250000 | 0 | 1250000 | 4687316 | 1591340 | 3095976 | 4307940 | 1571340 | 2736600 | 4491340 | 1591340 | 2900000 | 610200 | 0 | 610200 | 477581 | 0 | 477581 | 525000 | 0 | 525000 | 385461 | 310461 | 75000 | 347450 | 285320 | 62130 | 360320 | 285320 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 461371 | 0 | 461371 | 480000 | 0 | 480000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 80199 | 28739 | 51460 | 90199 | 28739 | 61460 | 8199737 | 1930540 | 6269197 | 6632785 | 1885399 | 4747386 | 7216859 | 1905399 | 5311460 | 8199737 | 1930540 | 6269197 | 6632785 | 1885399 | 4747386 | 7216859 | 1905399 | 5311460 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2012 | Q4 | Q4 - 2012 | 1838817 | 0 | 1838817 | 1098548 | 0 | 1098548 | 1198548 | 0 | 1198548 | 4687316 | 1591340 | 3095976 | 4857158 | 1571340 | 3285818 | 5057158 | 1571340 | 3485818 | 610200 | 0 | 610200 | 547872 | 0 | 547872 | 647872 | 0 | 647872 | 385461 | 310461 | 75000 | 372938 | 285320 | 87618 | 2955818 | 2853200 | 102618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 595025 | 0 | 595025 | 625025 | 0 | 625025 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 92441 | 28739 | 63702 | 94441 | 28739 | 65702 | 8199737 | 1930540 | 6269197 | 7564912 | 1885399 | 5679513 | 10579792 | 4453279 | 6126513 | 8199737 | 1930540 | 6269197 | 7564912 | 1885399 | 5679513 | 10579792 | 4453279 | 6126513 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2013 | Q1 | Q1 - 2013 | 1838817 | 0 | 1838817 | 1196794 | 0 | 1196794 | 1196794 | 0 | 1196794 | 4687316 | 1591340 | 3095976 | 4984803 | 1571340 | 3413463 | 5184803 | 1571340 | 3613463 | 610200 | 0 | 610200 | 616825 | 24467 | 592358 | 626825 | 34467 | 592358 | 385461 | 310461 | 75000 | 385749 | 285320 | 100429 | 385749 | 285330 | 100429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 641761 | 0 | 641761 | 641761 | 0 | 641761 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 95211 | 28739 | 66472 | 95211 | 28739 | 66472 | 8199737 | 1930540 | 6269197 | 7922073 | 1909866 | 6012207 | 8132073 | 1919876 | 6212207 | 8199737 | 1930540 | 6269197 | 7922073 | 1909866 | 6012207 | 8132073 | 1919876 | 6212207 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2013 | Q2 | Q2 - 2013 | 1838817 | 0 | 1838817 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 4687316 | 1591340 | 3095976 | 5100450 | 1581340 | 3519110 | 5150387 | 1581340 | 3569047 | 610200 | 0 | 610200 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 385461 | 310461 | 75000 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 643878 | 0 | 643878 | 643878 | 0 | 643878 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 8199737 | 1930540 | 6269197 | 8149800 | 1930540 | 6219260 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 8149800 | 1930540 | 6219260 | 8199737 | 1930540 | 6269197 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2013 | Q3 | Q3 - 2013 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643878 | 0 | 646878 | 643878 | 0 | 643878 | 643878 | 0 | 643878 | 930 | 0 | 930 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570095 | INF | 2013 | Q4 | Q4 - 2013 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643878 | 0 | 646878 | 643878 | 0 | 643878 | 643878 | 0 | 643878 | 930 | 0 | 930 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 0 | 0 | JKM Consulting, Inc.
NT10BIX5570096 | INF | 2010 | Q4 | Q4 - 2010 | 66838777 | 28886379 | 37952398 | 0 | 0 | 0 | 600000 | 300000 | 300000 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 1500108 | 0 | 1500108 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 0 | 0 | 0 | 700000 | 200000 | 500000 | 280320 | 0 | 280320 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 0 | 0 | 0 | 0 | 0 | 0 | 88274848 | 29386379 | 58888469 | 0 | 0 | 0 | 2000000 | 700000 | 1300000 | 88274848 | 29386379 | 58888469 | 0 | 0 | 0 | 2000000 | 700000 | 1300000 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2011 | Q1 | Q1 - 2011 | 66838777 | 28886379 | 37952398 | 1165696 | 1165696 | 0 | 16890019 | 13750000 | 3140019 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 300000 | 0 | 300000 | 1500108 | 0 | 1500108 | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 378378 | 193629 | 184749 | 700000 | 150000 | 550000 | 280320 | 0 | 280320 | 235071 | 235071 | 0 | 280320 | 0 | 280320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 300000 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 88274848 | 29386379 | 58888469 | 1779145 | 1594396 | 184749 | 31000000 | 14000000 | 17000000 | 88274848 | 29386379 | 58888469 | 1779145 | 1594396 | 184749 | 31000000 | 14000000 | 17000000 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2011 | Q2 | Q2 - 2011 | 66838777 | 28886379 | 37952398 | 1204724 | 1204724 | 0 | 20500000 | 15500000 | 5000000 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 2880000 | 0 | 2880000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 185339 | 0 | 185339 | 1500108 | 0 | 1500108 | 13755 | 13755 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 773519 | 773519 | 0 | 2500000 | 500000 | 2000000 | 280320 | 0 | 280320 | 235393 | 50644 | 184749 | 280000 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 400000 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 45934 | 45934 | 0 | 6000000 | 0 | 6000000 | 88274848 | 29386379 | 58888469 | 2273325 | 2088576 | 184749 | 32820339 | 16000000 | 16820339 | 88274848 | 29386379 | 58888469 | 2273325 | 2088576 | 184749 | 32820339 | 16000000 | 16820339 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2011 | Q3 | Q3 - 2011 | 66838777 | 28886379 | 37952398 | 1596909 | 690152 | 906757 | 7797956 | 3370120 | 4427836 | 2880000 | 0 | 2880000 | 33796 | 0 | 33796 | 41956 | 0 | 41956 | 450000 | 0 | 450000 | 0 | 0 | 0 | 133477 | 0 | 133477 | 1500108 | 0 | 1500108 | 13775 | 0 | 13775 | 13775 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 1383430 | 166521 | 1216910 | 1978342 | 238129 | 1740213 | 280320 | 0 | 280320 | 235071 | 0 | 235071 | 286278 | 0 | 286278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 70283 | 0 | 70283 | 100733 | 0 | 100733 | 88274848 | 29386379 | 58888469 | 3333264 | 856673 | 2476592 | 10352517 | 3608249 | 6744268 | 88274848 | 29386379 | 58888469 | 3333264 | 856673 | 2476592 | 10352517 | 3608249 | 6744268 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2011 | Q4 | Q4 - 2011 | 66838777 | 28886379 | 37952398 | 23996264 | 15247966 | 8748298 | 24599114 | 15247966 | 9351148 | 2880000 | 0 | 2880000 | 41956 | 0 | 41956 | 186956 | 0 | 186956 | 450000 | 0 | 450000 | 22859 | 0 | 22859 | 332607 | 0 | 332607 | 1500108 | 0 | 1500108 | 13775 | 0 | 13775 | 13775 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 1939953 | 233508 | 1706445 | 2080453 | 250420 | 1830033 | 280320 | 0 | 280320 | 268989 | 0 | 268989 | 268989 | 0 | 268989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 121399 | 0 | 121399 | 121399 | 0 | 121399 | 88274848 | 29386379 | 58888469 | 26405195 | 15481474 | 10923721 | 27603293 | 15498386 | 12104907 | 88274848 | 29386379 | 58888469 | 26405195 | 15481474 | 10923721 | 27603293 | 15498386 | 12104907 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2012 | Q1 | Q1 - 2012 | 66838777 | 28886379 | 37952398 | 24399654 | 15330277 | 9069376 | 24554014 | 15361774 | 9192239 | 2880000 | 0 | 2880000 | 149648 | 0 | 149648 | 240409 | 0 | 240409 | 450000 | 0 | 450000 | 316656 | 0 | 316656 | 316656 | 0 | 316656 | 1500108 | 0 | 1500108 | 24950 | 0 | 24950 | 29897 | 0 | 29897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2084060 | 250854 | 1833206 | 2084060 | 250854 | 1833206 | 280320 | 0 | 280320 | 269029 | 0 | 269029 | 271042 | 0 | 271042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 18900 | 0 | 18900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 265277 | 0 | 265277 | 268266 | 0 | 268266 | 88274848 | 29386379 | 58888469 | 27509274 | 15581131 | 11928142 | 27783244 | 15612628 | 12170615 | 88274848 | 29386379 | 58888469 | 27509274 | 15581131 | 11928142 | 27783244 | 15612628 | 12170615 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2012 | Q2 | Q2 - 2012 | 66838777 | 28886379 | 37952398 | 24039141 | 15232764 | 8806377 | 26039141 | 15232764 | 10806377 | 2880000 | 0 | 2880000 | 269362 | 0 | 269362 | 519362 | 0 | 519362 | 450000 | 0 | 450000 | 493621 | 0 | 493621 | 493621 | 0 | 493621 | 1500108 | 0 | 1500108 | 50231 | 0 | 50231 | 50231 | 0 | 50231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2226370 | 340317 | 1886053 | 2426370 | 340317 | 2086053 | 280320 | 0 | 280320 | 269351 | 0 | 269351 | 299351 | 0 | 299351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 18900 | 0 | 18900 | 21600 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 291087 | 0 | 291087 | 679816 | 0 | 679816 | 88274848 | 29386379 | 58888469 | 27658063 | 15573081 | 12084982 | 30529492 | 15573081 | 14956411 | 88274848 | 29386379 | 58888469 | 27658063 | 15573081 | 12084982 | 30529492 | 15573081 | 14956411 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2012 | Q3 | Q3 - 2012 | 66838777 | 28886379 | 37952398 | 24741799 | 15232764 | 9509035 | 25714499 | 15232764 | 10481735 | 2880000 | 0 | 2880000 | 983050 | 0 | 983050 | 1508400 | 0 | 1508400 | 450000 | 0 | 450000 | 507474 | 0 | 507474 | 507474 | 0 | 507474 | 1500108 | 0 | 1500108 | 45626 | 0 | 45626 | 70626 | 0 | 70626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2556055 | 340317 | 2215738 | 2626370 | 340317 | 2286053 | 280320 | 0 | 280320 | 271364 | 0 | 271364 | 314351 | 0 | 314351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 25100 | 0 | 25100 | 84100 | 0 | 84100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 608486 | 0 | 608486 | 701346 | 0 | 701346 | 88274848 | 29386379 | 58888469 | 29738954 | 15573081 | 14165873 | 31527166 | 15573081 | 15954085 | 88274848 | 29386379 | 58888469 | 29738954 | 15573081 | 14165873 | 31527166 | 15573081 | 15954085 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2012 | Q4 | Q4 - 2012 | 66838777 | 28886379 | 37952398 | 25119267 | 15232764 | 9886503 | 27585529 | 15232764 | 12352765 | 2880000 | 0 | 2880000 | 1687845 | 0 | 1687845 | 2880000 | 0 | 2880000 | 450000 | 0 | 450000 | 507829 | 0 | 507829 | 507829 | 0 | 507829 | 1500108 | 0 | 1500108 | 68726 | 0 | 68726 | 101226 | 0 | 101226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2820454 | 340317 | 2480137 | 3291114 | 340317 | 2950797 | 280320 | 0 | 280320 | 271364 | 0 | 271364 | 314351 | 0 | 314351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 25100 | 0 | 25100 | 84100 | 0 | 84100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 755414 | 0 | 755414 | 855500 | 0 | 855500 | 88274848 | 29386379 | 58888469 | 31255999 | 15573081 | 15682918 | 35619649 | 15573081 | 20046568 | 88274848 | 29386379 | 58888469 | 31255999 | 15573081 | 15682918 | 35619649 | 15573081 | 20046568 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2013 | Q1 | Q1 - 2013 | 38700857 | 15247966 | 23452891 | 26546919 | 15192227 | 11354692 | 30139677 | 15192227 | 14947450 | 40591368 | 14138413 | 26452955 | 5060043 | 324543 | 4735500 | 15059845 | 324543 | 14735303 | 1550790 | 0 | 1550790 | 739404 | 0 | 739404 | 943999 | 0 | 943999 | 100000 | 0 | 100000 | 85200 | 0 | 85200 | 85200 | 0 | 85200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250000 | 0 | 6250000 | 2959275 | 0 | 2959275 | 3773524 | 0 | 3773524 | 425000 | 0 | 425000 | 348410 | 0 | 348410 | 367410 | 0 | 367410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646833 | 0 | 646833 | 536900 | 0 | 536900 | 612874 | 0 | 612874 | 88274848 | 29386379 | 58888469 | 36276151 | 15516770 | 20759381 | 50992529 | 15516770 | 35475760 | 88274848 | 29386379 | 58888469 | 36276151 | 15516770 | 20759381 | 50992529 | 15516770 | 35475760 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2013 | Q2 | Q2 - 2013 | 38700857 | 15247966 | 23452891 | 27796334 | 15192227 | 12604107 | 30139677 | 15192227 | 14947450 | 40591368 | 14138413 | 26452955 | 10166767 | 324543 | 9842224 | 15166767 | 324543 | 14842224 | 1550790 | 0 | 1550790 | 755929 | 0 | 755929 | 943999 | 0 | 943999 | 100000 | 0 | 100000 | 85200 | 0 | 85200 | 90200 | 0 | 90200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250000 | 0 | 6250000 | 3620656 | 0 | 3620656 | 4470656 | 0 | 4470656 | 425000 | 0 | 425000 | 379243 | 0 | 379243 | 405243 | 0 | 405243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646833 | 0 | 646833 | 605843 | 0 | 605843 | 646833 | 0 | 646833 | 88274848 | 29386379 | 58888469 | 43409972 | 15516770 | 27893202 | 51873375 | 15516770 | 36356605 | 88274848 | 29386379 | 58888469 | 43409972 | 15516770 | 27893202 | 51873375 | 15516770 | 36356605 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2013 | Q3 | Q3 - 2013 | 35646004 | 10474987 | 25171017 | 26162397 | 10474987 | 15687410 | 33033707 | 10474987 | 22558720 | 29598639 | 4247130 | 25351509 | 15246956 | 324543 | 14922413 | 24075646 | 324543 | 23751103 | 2194110 | 0 | 2194110 | 1128864 | 0 | 1128864 | 1760800 | 0 | 1760800 | 125000 | 0 | 125000 | 85200 | 0 | 85200 | 90200 | 0 | 90200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4109066 | 0 | 4109066 | 4602182 | 0 | 4602182 | 425000 | 0 | 425000 | 396995 | 0 | 396995 | 405243 | 0 | 405243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 660921 | 0 | 660921 | 661833 | 0 | 661833 | 73610586 | 14722117 | 58888469 | 47790399 | 10799530 | 36990869 | 64639611 | 10799530 | 53840081 | 73610586 | 14722117 | 58888469 | 47790399 | 10799530 | 36990869 | 64639611 | 10799530 | 53840081 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2013 | Q4 | Q4 - 2013 | 35646004 | 10474987 | 25171017 | 28195238 | 10474987 | 17720251 | 30224987 | 10474987 | 19750000 | 29598639 | 4247130 | 25351509 | 18160441 | 324543 | 17835898 | 21160441 | 324543 | 20835898 | 2194110 | 0 | 2194110 | 1472688 | 0 | 1472688 | 1532688 | 0 | 1532688 | 125000 | 0 | 125000 | 88700 | 0 | 88700 | 93200 | 0 | 93200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4561607 | 0 | 4561607 | 4696607 | 0 | 4696607 | 425000 | 0 | 425000 | 276697 | 0 | 276697 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 666882 | 0 | 666882 | 666882 | 0 | 666882 | 73610586 | 14722117 | 58888469 | 53422253 | 10799530 | 42622723 | 58679805 | 10799530 | 47880275 | 73610586 | 14722117 | 58888469 | 53422253 | 10799530 | 42622723 | 58679805 | 10799530 | 47880275 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2014 | Q1 | Q1 - 2014 | 35646004 | 10474987 | 25171017 | 30438244 | 10474987 | 19963257 | 32424987 | 10474987 | 21950000 | 29598639 | 4247130 | 25351509 | 19767836 | 324543 | 19443293 | 21824543 | 324543 | 21500000 | 2194110 | 0 | 2194110 | 1628523 | 0 | 1628523 | 1730000 | 0 | 1730000 | 125000 | 0 | 125000 | 88700 | 0 | 88700 | 93200 | 0 | 93200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4737441 | 0 | 4737441 | 4950000 | 0 | 4950000 | 425000 | 0 | 425000 | 276697 | 0 | 276697 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 661227 | 0 | 661227 | 661833 | 0 | 661833 | 73610586 | 14722117 | 58888469 | 57598668 | 10799530 | 46799138 | 61989563 | 10799530 | 51190033 | 73610586 | 14722117 | 58888469 | 57598668 | 10799530 | 46799138 | 61989563 | 10799530 | 51190033 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570096 | INF | 2014 | Q2 | Q2 - 2014 | 35646004 | 10474987 | 25171016 | 35855308 | 10474987 | 25380321 | 35855308 | 10474987 | 25380321 | 29598639 | 4247130 | 25351509 | 29173602 | 4247130 | 24926471 | 29173602 | 4247130 | 24926471 | 2194110 | 0 | 2194110 | 2694376 | 0 | 2694376 | 2694376 | 0 | 2694376 | 125000 | 0 | 125000 | 114570 | 0 | 114570 | 114570 | 0 | 114570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4701499 | 0 | 4701499 | 4701499 | 0 | 4701499 | 425000 | 0 | 425000 | 409398 | 0 | 409398 | 409398 | 0 | 409398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 661833 | 0 | 661833 | 661833 | 0 | 661833 | 73610586 | 14722117 | 58888468 | 73610586 | 14722117 | 58888468 | 73610586 | 14722117 | 58888468 | 73610586 | 14722117 | 58888468 | 73610586 | 14722117 | 58888468 | 73610586 | 14722117 | 58888468 | 0 | 0 | Virgin Islands Public Finance Authority
NT10BIX5570097 | INF | 2010 | Q4 | Q4 - 2010 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 17181 | 0 | 17181 | 111984 | 0 | 111984 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 0 | 0 | 0 | 322500 | 0 | 322500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 55700000 | 17000003 | 38699997 | 17181 | 0 | 17181 | 434484 | 0 | 434484 | 55700000 | 17000003 | 38699997 | 17181 | 0 | 17181 | 434484 | 0 | 434484 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2011 | Q1 | Q1 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 106476 | 0 | 106476 | 338766 | 0 | 338766 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 612682 | 0 | 612682 | 793884 | 0 | 793884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 55700000 | 17000003 | 38699997 | 719158 | 0 | 719158 | 1132650 | 0 | 1132650 | 55700000 | 17000003 | 38699997 | 719158 | 0 | 719158 | 1132650 | 0 | 1132650 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2011 | Q2 | Q2 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 200375 | 0 | 200375 | 338766 | 0 | 338766 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 346235 | 0 | 346235 | 793884 | 0 | 793884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 136652 | 136652 | 0 | 11601004 | 11600004 | 1000 | 55700000 | 17000003 | 38699997 | 683262 | 136652 | 546610 | 12733654 | 11600004 | 1133650 | 55700000 | 17000003 | 38699997 | 683262 | 136652 | 546610 | 12733654 | 11600004 | 1133650 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2011 | Q3 | Q3 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 315346 | 0 | 315346 | 578815 | 0 | 578815 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 630034 | 0 | 630034 | 1309151 | 0 | 1309151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 12545384 | 11600004 | 945380 | 13487970 | 11600004 | 1887966 | 55700000 | 17000003 | 38699997 | 12545384 | 11600004 | 945380 | 13487970 | 11600004 | 1887966 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2011 | Q4 | Q4 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 3615000 | 0 | 3615000 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 1030000 | 0 | 1030000 | 2708999 | 0 | 2708999 | 439427 | 0 | 439427 | 624795 | 0 | 624795 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 1040000 | 0 | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 763336 | 0 | 763336 | 1733536 | 0 | 1733536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 12802767 | 11600004 | 1202763 | 19643335 | 11600004 | 8043331 | 55700000 | 17000003 | 38699997 | 12802767 | 11600004 | 1202763 | 19643335 | 11600004 | 8043331 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2012 | Q1 | Q1 - 2012 | 23203458 | 0 | 23203458 | 4583020 | 0 | 4583020 | 12387586 | 2752260 | 9635326 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 850000 | 0 | 850000 | 2708999 | 0 | 2708999 | 611703 | 0 | 611703 | 770000 | 0 | 770000 | 3390037 | 0 | 3390037 | 92709 | 0 | 92709 | 2359690 | 2245188 | 114502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 931257 | 0 | 931257 | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 102000 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 17818693 | 11600004 | 6218689 | 29869280 | 16597452 | 13271828 | 55700000 | 17000003 | 38699997 | 17818693 | 11600004 | 6218689 | 29869280 | 16597452 | 13271828 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2012 | Q2 | Q2 - 2012 | 23203458 | 0 | 23203458 | 12633420 | 3089119 | 9544301 | 13268420 | 3089118 | 10179301 | 5563136 | 4049216 | 1513920 | 522421 | 0 | 522421 | 4437421 | 0 | 4437421 | 2708999 | 0 | 2708999 | 942061 | 0 | 942062 | 1076691 | 0 | 1076691 | 3390037 | 0 | 3390037 | 2337897 | 2245188 | 92709 | 2337897 | 2245188 | 92710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 1781567 | 0 | 1781567 | 1935567 | 0 | 1935567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 363000 | 0 | 363000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 29817370 | 16934311 | 12883060 | 35019000 | 16934310 | 18084690 | 55700000 | 17000003 | 38699997 | 29817370 | 16934311 | 12883060 | 35019000 | 16934310 | 18084690 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2012 | Q3 | Q3 - 2012 | 19736716 | 3089118 | 16647597 | 13147458 | 3089119 | 10058339 | 14628608 | 3089118 | 11539490 | 6501107 | 0 | 6501107 | 1373527 | 0 | 1373527 | 6230762 | 0 | 6230762 | 2708999 | 0 | 2708999 | 1091723 | 0 | 1091723 | 1166723 | 0 | 1166723 | 2384958 | 2245188 | 139770 | 2359690 | 2245188 | 114502 | 2359690 | 2245188 | 114502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 2249023 | 0 | 2249023 | 2249023 | 0 | 2249023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 553385 | 0 | 553385 | 1442288 | 0 | 1442288 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 32374810 | 16934311 | 15440499 | 39677098 | 16934310 | 22742788 | 55700000 | 17000003 | 38699997 | 32374810 | 16934311 | 15440499 | 39677098 | 16934310 | 22742788 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2012 | Q4 | Q4 - 2012 | 19736716 | 3089118 | 16647597 | 14908008 | 3089119 | 11818890 | 15722164 | 3089118 | 12633046 | 6501107 | 0 | 6501107 | 4094121 | 0 | 4094121 | 4775972 | 0 | 4775972 | 2708999 | 0 | 2708999 | 1244330 | 0 | 1244330 | 1374734 | 0 | 1374734 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 2820220 | 0 | 2820220 | 3654079 | 0 | 3654079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 840542 | 0 | 840542 | 852857 | 0 | 852857 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 37883470 | 16934311 | 20949160 | 40356055 | 16934310 | 23421745 | 55700000 | 17000003 | 38699997 | 37883470 | 16934311 | 20949160 | 40356055 | 16934310 | 23421745 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2013 | Q1 | Q1 - 2013 | 19736716 | 3089118 | 16647597 | 15183545 | 3089118 | 12094426 | 16983544 | 3089118 | 13894426 | 6501107 | 0 | 6501107 | 5065559 | 0 | 5065559 | 5267269 | 0 | 5267269 | 2708999 | 0 | 2708999 | 1341636 | 0 | 1341636 | 1423436 | 0 | 1423436 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 3399393 | 0 | 3399393 | 3741393 | 0 | 3741393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1065045 | 0 | 1065045 | 1325098 | 0 | 1325098 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 40031427 | 16934310 | 23097116 | 42716989 | 16934310 | 25782679 | 55700000 | 17000003 | 38699997 | 40031427 | 16934310 | 23097116 | 42716989 | 16934310 | 25782679 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2013 | Q2 | Q2 - 2013 | 19736716 | 3089118 | 16647597 | 17166021 | 3089118 | 14076903 | 17527021 | 3089118 | 14437903 | 6501107 | 0 | 6501107 | 5408302 | 0 | 5408302 | 5661302 | 0 | 5661302 | 2708999 | 0 | 2708999 | 1464819 | 0 | 1464819 | 1502819 | 0 | 1502819 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 4019255 | 0 | 4019255 | 4785255 | 0 | 4785255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1451503 | 0 | 1451503 | 1501503 | 0 | 1501503 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 43486149 | 16934310 | 26551839 | 44954149 | 16934310 | 28019839 | 55700000 | 17000003 | 38699997 | 43486149 | 16934310 | 26551839 | 44954149 | 16934310 | 28019839 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2013 | Q3 | Q3 - 2013 | 19736716 | 3089118 | 16647597 | 17583018 | 3089118 | 14493900 | 17596518 | 3089118 | 14507400 | 6501107 | 0 | 6501107 | 5556919 | 0 | 5556919 | 5556919 | 0 | 5556919 | 2708999 | 0 | 2708999 | 1591060 | 0 | 1591060 | 1695760 | 0 | 1695760 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 4404785 | 1605 | 4403180 | 5263685 | 1605 | 5262080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1536416 | 0 | 1536416 | 1580016 | 0 | 1580016 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 44648447 | 16935915 | 27712532 | 45669147 | 16935915 | 28733232 | 55700000 | 17000003 | 38699997 | 44648447 | 16935915 | 27712532 | 45669147 | 16935915 | 28733232 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2013 | Q4 | Q4 - 2013 | 19736715 | 3089118 | 16647597 | 16687691 | 3089118 | 13598573 | 16790659 | 3089118 | 13701541 | 6501107 | 0 | 6501107 | 5662000 | 0 | 5662000 | 5675466 | 0 | 5675466 | 2708999 | 0 | 2708999 | 2358455 | 0 | 2358455 | 2423389 | 0 | 2423389 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 5948349 | 1605 | 5946744 | 6109349 | 1605 | 6107744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1421698 | 0 | 1421698 | 1421698 | 0 | 1421698 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 46054442 | 16935915 | 29118527 | 46396810 | 16935915 | 29460895 | 55700000 | 17000003 | 38699997 | 46054442 | 16935915 | 29118527 | 46396810 | 16935915 | 29460895 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2014 | Q1 | Q1 - 2014 | 19736715 | 3089118 | 16647597 | 17345580 | 3089118 | 14256462 | 17401548 | 3089118 | 14312430 | 6501107 | 0 | 6501107 | 5661383 | 0 | 5661383 | 5674849 | 0 | 5674849 | 2708999 | 0 | 2708999 | 1868005 | 0 | 1868005 | 1953091 | 0 | 1953091 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 6049584 | 1605 | 6047979 | 6149583 | 1605 | 6147978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1465870 | 0 | 1465870 | 1465870 | 0 | 1465870 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 46366671 | 16935915 | 29430756 | 46681190 | 16935915 | 29745275 | 55700000 | 17000003 | 38699997 | 46366671 | 16935915 | 29430756 | 46681190 | 16935915 | 29745275 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2014 | Q2 | Q2 - 2014 | 19736715 | 3089118 | 16647597 | 17397072 | 3089118 | 14307954 | 17547223 | 3089118 | 14458105 | 6501107 | 0 | 6501107 | 5650983 | 0 | 5650983 | 5850983 | 0 | 5850983 | 2708999 | 0 | 2708999 | 2406854 | 0 | 2406854 | 2503104 | 0 | 2503104 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 6046158 | 1605 | 6044553 | 6291158 | 1605 | 6289553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1489736 | 0 | 1489736 | 1544736 | 0 | 1544736 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 200000 | 0 | 200000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 47027052 | 16935915 | 30091137 | 47973453 | 16935915 | 31037538 | 55700000 | 17000003 | 38699997 | 47027052 | 16935915 | 30091137 | 47973453 | 16935915 | 31037538 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2014 | Q3 | Q3 - 2014 | 19736715 | 3089118 | 16647597 | 17419088 | 3089118 | 14329970 | 17427088 | 3089118 | 14337970 | 6501107 | 0 | 6501107 | 6216628 | 0 | 6216628 | 6286628 | 0 | 6286628 | 2708999 | 0 | 2708999 | 1999162 | 0 | 1999162 | 2145662 | 0 | 2145662 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 6485179 | 1605 | 6483574 | 6613679 | 1605 | 6612074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1579844 | 0 | 1579844 | 1819844 | 0 | 1819844 | 1500000 | 0 | 1500000 | 198000 | 0 | 198000 | 342000 | 0 | 342000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 47934150 | 16935915 | 30998235 | 48671150 | 16935915 | 31735235 | 55700000 | 17000003 | 38699997 | 47934150 | 16935915 | 30998235 | 48671150 | 16935915 | 31735235 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2014 | Q4 | Q4 - 2014 | 19736715 | 3089118 | 16647597 | 17593039 | 3089118 | 14503921 | 17717539 | 3089118 | 14628421 | 6501107 | 0 | 6501107 | 6329656 | 0 | 6329656 | 6329656 | 0 | 6329656 | 2708999 | 0 | 2708999 | 2165852 | 0 | 2165852 | 2289952 | 0 | 2289952 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 6756775 | 1605 | 6755170 | 6926775 | 1605 | 6925170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1703891 | 0 | 1703891 | 1703891 | 0 | 1703891 | 1500000 | 0 | 1500000 | 198000 | 0 | 198000 | 560000 | 0 | 560000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 48783462 | 16935915 | 31847547 | 49564062 | 16935915 | 32628147 | 55700000 | 17000003 | 38699997 | 48783462 | 16935915 | 31847547 | 49564062 | 16935915 | 32628147 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2015 | Q1 | Q1 - 2015 | 19736715 | 3089118 | 16647597 | 17723337 | 3089118 | 14634219 | 18263737 | 3089118 | 15174619 | 6501107 | 0 | 6501107 | 6329656 | 0 | 6329656 | 6329656 | 0 | 6329656 | 2708999 | 0 | 2708999 | 2387812 | 0 | 2387812 | 2534112 | 0 | 2534112 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 6805315 | 1605 | 6803710 | 7730315 | 1605 | 7728710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1703891 | 0 | 1703891 | 1703891 | 0 | 1703891 | 1500000 | 0 | 1500000 | 258000 | 0 | 258000 | 1258000 | 0 | 1258000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 49244260 | 16935915 | 32308345 | 51855960 | 16935915 | 34920045 | 55700000 | 17000003 | 38699997 | 49244260 | 16935915 | 32308345 | 51855960 | 16935915 | 34920045 | 0 | 0 | Department of Information Technology
NT10BIX5570097 | INF | 2015 | Q2 | Q2 - 2015 | 19736715 | 3089118 | 16647597 | 17732031 | 3089118 | 14642913 | 20356222 | 3089118 | 17267104 | 6501107 | 0 | 6501107 | 6347195 | 0 | 6347195 | 6347195 | 0 | 6347195 | 2708999 | 0 | 2708999 | 2589360 | 0 | 2589360 | 2771987 | 0 | 2771987 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 7659945 | 65693 | 7594252 | 9072398 | 65693 | 9006705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1732190 | 0 | 1732190 | 1733758 | 0 | 1733758 | 1500000 | 0 | 1500000 | 920000 | 0 | 920000 | 1382191 | 0 | 1382191 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 11660004 | 11600004 | 60000 | 55700000 | 17000003 | 38699997 | 51016970 | 17000003 | 34016967 | 55700000 | 17000003 | 38699997 | 55700000 | 17000003 | 38699997 | 51016970 | 17000003 | 34016967 | 55700000 | 17000003 | 38699997 | 0 | 0 | Department of Information Technology
NT10BIX5570098 | INF | 2010 | Q4 | Q4 - 2010 | 8573312 | 1714663 | 6858649 | 0 | 0 | 0 | 275255 | 0 | 275255 | 69013409 | 13802688 | 55210721 | 0 | 0 | 0 | 118230 | 0 | 118230 | 15109345 | 3021870 | 12087475 | 670517 | 0 | 670517 | 2069215 | 0 | 2069215 | 2285826 | 457166 | 1828660 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 201040 | 0 | 201040 | 706383 | 0 | 706383 | 2906663 | 581333 | 2325330 | 689972 | 0 | 689972 | 1586856 | 0 | 1586856 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 1561529 | 0 | 1561529 | 4805939 | 0 | 4805939 | 101435997 | 20287209 | 81148788 | 1561529 | 0 | 1561529 | 4805939 | 0 | 4805939 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2011 | Q1 | Q1 - 2011 | 8573312 | 1714663 | 6858649 | 83572 | 0 | 83572 | 512924 | 0 | 512924 | 69013409 | 13802688 | 55210721 | 10905 | 0 | 10905 | 20905 | 0 | 20905 | 15109345 | 3021870 | 12087475 | 1322396 | 0 | 1322396 | 2178121 | 0 | 2178121 | 2285826 | 457166 | 1828660 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 475069 | 0 | 475069 | 855069 | 0 | 855069 | 2906663 | 581333 | 2325330 | 1294849 | 0 | 1294849 | 1968849 | 0 | 1968849 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 3186791 | 0 | 3186791 | 5537868 | 0 | 5537868 | 101435997 | 20287209 | 81148788 | 3186791 | 0 | 3186791 | 5537868 | 0 | 5537868 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2011 | Q2 | Q2 - 2011 | 8573312 | 1714663 | 6858649 | 547342 | 0 | 547342 | 565542 | 0 | 595542 | 69013409 | 13802688 | 55210721 | 25621 | 0 | 25621 | 25621 | 0 | 25621 | 15109345 | 3021870 | 12087475 | 1795952 | 0 | 1795952 | 2664952 | 0 | 2664952 | 2285826 | 457166 | 1828660 | 18655 | 0 | 18655 | 599927 | 0 | 599927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 751122 | 0 | 751122 | 854571 | 0 | 854571 | 2906663 | 581333 | 2325330 | 1750866 | 0 | 1750866 | 2315866 | 0 | 2315866 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 4889558 | 0 | 4889558 | 7026479 | 0 | 7056479 | 101435997 | 20287209 | 81148788 | 4889558 | 0 | 4889558 | 7026479 | 0 | 7056479 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2011 | Q3 | Q3 - 2011 | 8573312 | 1714663 | 6858649 | 633739 | 0 | 633739 | 1251654 | 161594 | 1090060 | 69013409 | 13802688 | 55210721 | 35669 | 0 | 35669 | 4674258 | 603473 | 4070786 | 15109345 | 3021870 | 12087475 | 2504630 | 0 | 2504630 | 4260484 | 550051 | 3710432 | 2285826 | 457166 | 1828660 | 17237 | 0 | 17237 | 67237 | 8681 | 58556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 1034923 | 0 | 1034923 | 2330923 | 300935 | 2029988 | 2906663 | 571333 | 2325330 | 2374478 | 0 | 2374478 | 2906663 | 375266 | 2531397 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20277209 | 81148788 | 6600676 | 0 | 6600676 | 15491219 | 2000000 | 13491219 | 101435997 | 20277209 | 81148788 | 6600676 | 0 | 6600676 | 15491219 | 2000000 | 13491219 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2011 | Q4 | Q4 - 2011 | 8573312 | 1714663 | 6858649 | 787561 | 0 | 787561 | 5486319 | 405607 | 5080712 | 69013409 | 13802688 | 55210721 | 4975289 | 0 | 4975289 | 8238333 | 609065 | 7629268 | 15109345 | 3021870 | 12087475 | 3483698 | 0 | 3483698 | 6556933 | 484758 | 6072175 | 2285826 | 457166 | 1828660 | 37323 | 0 | 37323 | 697583 | 51573 | 646010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 1576914 | 0 | 1576914 | 2200220 | 162664 | 2037556 | 2906663 | 581333 | 2325330 | 2681887 | 0 | 2681887 | 3873003 | 286333 | 3586670 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 13542672 | 0 | 13542672 | 27052391 | 2000000 | 25052391 | 101435997 | 20287209 | 81148788 | 13542672 | 0 | 13542672 | 27052391 | 2000000 | 25052391 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2012 | Q1 | Q1 - 2012 | 8573312 | 1714663 | 6858649 | 1008050 | 0 | 1008050 | 6612476 | 961341 | 5651135 | 69013409 | 13802688 | 55210721 | 7373202 | 0 | 7373202 | 24675637 | 3587415 | 21088222 | 15109345 | 3021870 | 12087475 | 4822682 | 0 | 4822682 | 8295003 | 1206432 | 7088571 | 2285826 | 457166 | 1828660 | 56598 | 0 | 56598 | 2087728 | 303520 | 1784208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 2147561 | 0 | 2147561 | 2664740 | 387408 | 2277332 | 2906663 | 581333 | 2325330 | 3981764 | 0 | 3981764 | 5185503 | 753884 | 4431619 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 3300 | 0 | 3300 | 3300 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 19393157 | 0 | 19393157 | 49524387 | 7200000 | 42324387 | 101435997 | 20287209 | 81148788 | 19393157 | 0 | 19393157 | 49524387 | 7200000 | 42324387 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2012 | Q2 | Q2 - 2012 | 8573312 | 1714663 | 6858649 | 4645336 | 0 | 4645336 | 5670794 | 242055 | 5428739 | 69013409 | 13802688 | 55210721 | 12896961 | 0 | 12896961 | 24952423 | 2845641 | 22106782 | 15109345 | 3021870 | 12087475 | 6104533 | 0 | 6104533 | 7789858 | 397814 | 7392044 | 2285826 | 457166 | 1828660 | 555290 | 0 | 555290 | 1057562 | 118559 | 939003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 2875069 | 0 | 2875069 | 3393159 | 122293 | 3270866 | 2906663 | 581333 | 2325330 | 3857870 | 0 | 3857870 | 5739638 | 444183 | 5295455 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 125667 | 29663 | 96004 | 314813 | 62963 | 251850 | 23800 | 0 | 23800 | 342000 | 75110 | 266890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 2169 | 0 | 2169 | 2169 | 0 | 2169 | 101435997 | 20287209 | 81148788 | 30961028 | 0 | 30961028 | 49073270 | 4275318 | 44797952 | 101435997 | 20287209 | 81148788 | 30961028 | 0 | 30961028 | 49073270 | 4275318 | 44797952 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2012 | Q3 | Q3 - 2012 | 8573312 | 1714663 | 6858649 | 3182393 | 32196 | 3150197 | 6371092 | 654944 | 5716148 | 69013409 | 13802688 | 55210721 | 17539985 | 100241 | 17439744 | 34228438 | 3518660 | 30709778 | 15109345 | 3021870 | 12087475 | 7364717 | 352204 | 7012513 | 10174341 | 1045914 | 9128427 | 2285826 | 457166 | 1828660 | 1101620 | 508809 | 592811 | 1970597 | 600000 | 1370597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3344057 | 33358 | 3310699 | 3578718 | 268019 | 3310699 | 2906663 | 581333 | 2325330 | 4419970 | 377282 | 4042688 | 5557749 | 671204 | 4886545 | 164635 | 32927 | 131708 | 65130 | 65130 | 0 | 348481 | 66000 | 282481 | 314813 | 62963 | 251850 | 28850 | 0 | 28850 | 734540 | 75510 | 659030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 95953 | 9864 | 86089 | 101435997 | 20287209 | 81148788 | 37050475 | 1469220 | 35581255 | 63059909 | 6910115 | 56149794 | 101435997 | 20287209 | 81148788 | 37050475 | 1469220 | 35581255 | 63059909 | 6910115 | 56149794 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2012 | Q4 | Q4 - 2012 | 8573312 | 1714663 | 6858649 | 3521288 | 306094 | 3215194 | 4729325 | 691260 | 4038065 | 69013409 | 13802688 | 55210721 | 22683418 | 2257744 | 20425674 | 43614731 | 5639548 | 37975183 | 15109345 | 3021870 | 12087475 | 8621554 | 1049511 | 7572043 | 9778030 | 1429202 | 8348828 | 2285826 | 457166 | 1828660 | 1780676 | 558509 | 1222167 | 1781245 | 558509 | 1222736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3664860 | 173337 | 3491523 | 3954949 | 400000 | 3554949 | 2906663 | 581333 | 2325330 | 5491185 | 1292902 | 4198283 | 7282089 | 1450000 | 5832089 | 164635 | 32927 | 131708 | 288790 | 173375 | 115415 | 581347 | 175000 | 406347 | 314813 | 62963 | 251850 | 537173 | 222312 | 314861 | 754927 | 250000 | 504927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 100477 | 14686 | 85791 | 101435997 | 20287209 | 81148788 | 46592697 | 6033784 | 40558913 | 72577120 | 10608205 | 61968915 | 101435997 | 20287209 | 81148788 | 46592697 | 6033784 | 40558913 | 72577120 | 10608205 | 61968915 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2013 | Q1 | Q1 - 2013 | 8573312 | 1714663 | 6858649 | 5726883 | 306094 | 5420789 | 6934920 | 1073785 | 5861135 | 69013409 | 13802688 | 55210721 | 29454768 | 2700805 | 26753963 | 50386081 | 7801652 | 42584429 | 15109345 | 3021870 | 12087475 | 9796055 | 1068443 | 8727612 | 10952531 | 1401390 | 9551141 | 2285826 | 457166 | 1828660 | 1991953 | 558509 | 1433444 | 1992522 | 558509 | 1434013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3949901 | 173337 | 3776564 | 4239990 | 400000 | 3839990 | 2906663 | 581333 | 2325330 | 6292675 | 1292902 | 4999773 | 8083579 | 1400000 | 6683579 | 164635 | 32927 | 131708 | 500107 | 173375 | 326732 | 792664 | 180000 | 612664 | 314813 | 62963 | 251850 | 619485 | 222312 | 397173 | 837239 | 225000 | 612239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 100478 | 15558 | 84920 | 101435997 | 20287209 | 81148788 | 58335580 | 6495777 | 51839803 | 84320004 | 13055894 | 71264110 | 101435997 | 20287209 | 81148788 | 58335580 | 6495777 | 51839803 | 84320004 | 13055894 | 71264110 | 0 | 82500 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2013 | Q2 | Q2 - 2013 | 8573312 | 1714663 | 6858649 | 6147574 | 306094 | 5841480 | 6245351 | 306094 | 5939257 | 69013409 | 13802688 | 55210721 | 50673329 | 4983701 | 45689628 | 62691124 | 12379864 | 50311260 | 15109345 | 3021870 | 12087475 | 10887560 | 1082193 | 9805367 | 11690383 | 1782193 | 9908190 | 2285826 | 457166 | 1828660 | 2114768 | 558509 | 1556259 | 2114769 | 558509 | 1556260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4231418 | 173337 | 4058081 | 4421618 | 200000 | 4221618 | 2906663 | 581333 | 2325330 | 8248413 | 1292902 | 6955511 | 8420960 | 1400000 | 7020960 | 164635 | 32927 | 131708 | 812721 | 173375 | 639346 | 961121 | 180000 | 781121 | 314813 | 62963 | 251850 | 628118 | 222312 | 405806 | 630619 | 224250 | 406369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 3753 | 0 | 3753 | 101435997 | 20287209 | 81148788 | 83747654 | 8792423 | 74955231 | 97179698 | 17030910 | 80148788 | 101435997 | 20287209 | 81148788 | 83747654 | 8792423 | 74955231 | 97179698 | 17030910 | 80148788 | 0 | 96250 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2013 | Q3 | Q3 - 2013 | 8573312 | 1714663 | 6858649 | 6561964 | 519829 | 6042135 | 6700000 | 657865 | 6042135 | 69013409 | 13802688 | 55210721 | 59642229 | 9712630 | 49929599 | 62940353 | 13010754 | 49929599 | 15109345 | 3021870 | 12087475 | 11990484 | 1695591 | 10294893 | 13500000 | 3205107 | 10294893 | 2285826 | 457166 | 1828660 | 2123968 | 559709 | 1564259 | 2132905 | 568646 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4404517 | 267644 | 4136873 | 4601618 | 464745 | 4136873 | 2906663 | 581333 | 2325330 | 8704103 | 1384116 | 7319987 | 9000000 | 1680013 | 7319987 | 164635 | 32927 | 131708 | 933070 | 233449 | 699621 | 961121 | 261500 | 699621 | 314813 | 62963 | 251850 | 1369407 | 229903 | 1139504 | 1500000 | 360496 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 45276 | 23359 | 21917 | 100000 | 78083 | 21917 | 101435997 | 20287209 | 81148788 | 95775018 | 14626230 | 81148788 | 101435997 | 20287209 | 81148788 | 101435997 | 20287209 | 81148788 | 95775018 | 14626230 | 81148788 | 101435997 | 20287209 | 81148788 | 0 | 110000 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2013 | Q4 | Q4 - 2013 | 8573312 | 1714663 | 6858649 | 7034196 | 992061 | 6042135 | 7442135 | 1400000 | 6042135 | 69013409 | 13802688 | 55210721 | 64822747 | 14893148 | 49929599 | 68866898 | 18937299 | 49929599 | 15109345 | 3021870 | 12087475 | 12200574 | 1905681 | 10294893 | 13694893 | 3400000 | 10294893 | 2285826 | 457166 | 1828660 | 2141817 | 577558 | 1564259 | 2164259 | 600000 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4455295 | 318422 | 4136873 | 4536873 | 400000 | 4136873 | 2906663 | 581333 | 2325330 | 8827755 | 1507768 | 7319987 | 9119987 | 1800000 | 7319987 | 164635 | 32927 | 131708 | 971655 | 272034 | 699621 | 1049621 | 350000 | 699621 | 314813 | 62963 | 251850 | 1414822 | 275318 | 1139504 | 1489504 | 350000 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 133059 | 111142 | 21917 | 221917 | 200000 | 21917 | 101435997 | 20287209 | 81148788 | 102001920 | 20853132 | 81148788 | 108586087 | 27437299 | 81148788 | 101435997 | 20287209 | 81148788 | 102001920 | 20853132 | 81148788 | 108586087 | 27437299 | 81148788 | 0 | 199525 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2014 | Q1 | Q1 - 2014 | 8573312 | 1714663 | 6858649 | 7983442 | 1941307 | 6042135 | 8000063 | 1957928 | 6042135 | 69013409 | 13802688 | 55210721 | 68005145 | 18075546 | 49929599 | 68106849 | 18177250 | 49929599 | 15109345 | 3021870 | 12087475 | 13144588 | 2849695 | 10294893 | 13268790 | 2973897 | 10294893 | 2285826 | 457166 | 1828660 | 2161496 | 597237 | 1564259 | 2161496 | 597237 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4595886 | 459013 | 4136873 | 4609386 | 472513 | 4136873 | 2906663 | 581333 | 2325330 | 9144240 | 1824253 | 7319987 | 9240518 | 1920531 | 7319987 | 164635 | 32927 | 131708 | 1051677 | 352056 | 699621 | 1051677 | 352056 | 699621 | 314813 | 62963 | 251850 | 1414822 | 275318 | 1139504 | 1414822 | 275318 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 111112 | 89195 | 21917 | 111112 | 89195 | 21917 | 101435997 | 20287209 | 81148788 | 107612408 | 26463620 | 81148788 | 107964713 | 26815925 | 81148788 | 101435997 | 20287209 | 81148788 | 107612408 | 26463620 | 81148788 | 107964713 | 26815925 | 81148788 | 0 | 382532 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2014 | Q2 | Q2 - 2014 | 8573312 | 1714663 | 6858649 | 8069155 | 2027020 | 6042135 | 8079780 | 2037645 | 6042135 | 69013409 | 13802688 | 55210721 | 68077018 | 18147419 | 49929599 | 68168276 | 18238677 | 49929599 | 15109345 | 3021870 | 12087475 | 13157029 | 2862136 | 10294893 | 14199275 | 3904382 | 10294893 | 2285826 | 457166 | 1828660 | 2161496 | 597237 | 1564259 | 2161496 | 597237 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4595886 | 459013 | 4136873 | 4600133 | 463260 | 4136873 | 2906663 | 581333 | 2325330 | 9144240 | 1824253 | 7319987 | 9219688 | 1899701 | 7319987 | 164635 | 32927 | 131708 | 1051677 | 352056 | 699621 | 1051677 | 352056 | 699621 | 314813 | 62963 | 251850 | 1414822 | 275318 | 1139504 | 1414822 | 275318 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 111112 | 89195 | 21917 | 111112 | 89195 | 21917 | 101435997 | 20287209 | 81148788 | 107782435 | 26633647 | 81148788 | 109006259 | 27857471 | 81148788 | 101435997 | 20287209 | 81148788 | 107782435 | 26633647 | 81148788 | 109006259 | 27857471 | 81148788 | 0 | 1045527 | California Broadband Cooperative, Inc.
NT10BIX5570098 | INF | 2014 | Q3 | Q3 - 2014 | 8573312 | 1714663 | 6858649 | 7917372 | 1875237 | 6042135 | 7917372 | 1875237 | 6042135 | 69013409 | 13802688 | 55210721 | 68089866 | 18160267 | 49929599 | 68089866 | 18160267 | 49929599 | 15109345 | 3021870 | 12087475 | 14956660 | 4661767 | 10294893 | 14956660 | 4661767 | 10294893 | 2285826 | 457166 | 1828660 | 2161497 | 597238 | 1564259 | 2161497 | 597238 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4632493 | 495620 | 4136873 | 4632493 | 495620 | 4136873 | 2906663 | 581333 | 2325330 | 9288338 | 1968351 | 7319987 | 9288338 | 1968351 | 7319987 | 164635 | 32927 | 131708 | 1051677 | 352056 | 699621 | 1051677 | 352056 | 699621 | 314813 | 62963 | 251850 | 1419922 | 280418 | 1139504 | 1419922 | 280418 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 111112 | 89195 | 21917 | 111112 | 89195 | 21917 | 101435997 | 20287209 | 81148788 | 109628937 | 28480149 | 81148788 | 109628937 | 28480149 | 81148788 | 101435997 | 20287209 | 81148788 | 109628937 | 28480149 | 81148788 | 109628937 | 28480149 | 81148788 | 0 | 0 | California Broadband Cooperative, Inc.
NT10BIX5570099 | INF | 2010 | Q4 | Q4 - 2010 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 7058092 | 1411619 | 5646473 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2011 | Q1 | Q1 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 7058092 | 1411619 | 5646473 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2011 | Q2 | Q2 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 207221 | 41444 | 165777 | 282000 | 56400 | 225600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 207221 | 41444 | 165777 | 387000 | 77400 | 309600 | 7058092 | 1411619 | 5646473 | 207221 | 41444 | 165777 | 387000 | 77400 | 309600 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2011 | Q3 | Q3 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 262350 | 52470 | 209880 | 302000 | 60400 | 241600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 440 | 88 | 352 | 2000 | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 262790 | 52558 | 210232 | 359000 | 71800 | 287200 | 7058092 | 1411619 | 5646473 | 262790 | 52558 | 210232 | 359000 | 71800 | 287200 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2011 | Q4 | Q4 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 4535892 | 907179 | 3628713 | 319023 | 63805 | 255218 | 500000 | 100000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 4000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 288954 | 57791 | 231163 | 310000 | 62000 | 248000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 1095 | 219 | 876 | 6000 | 1200 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 609072 | 121815 | 487257 | 921000 | 187200 | 733800 | 7058092 | 1411619 | 5646473 | 609072 | 121815 | 487257 | 921000 | 187200 | 733800 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2012 | Q1 | Q1 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 580377 | 116075 | 464302 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 1600 | 320 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 291183 | 58257 | 232926 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 1095 | 219 | 876 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 872655 | 174551 | 698104 | 2491600 | 498320 | 1993280 | 7058092 | 1411619 | 5646473 | 872655 | 174551 | 698104 | 2491600 | 498320 | 1993280 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2012 | Q2 | Q2 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 1200000 | 240000 | 960000 | 4535892 | 907179 | 3628713 | 1545596 | 309119 | 1236476 | 3000000 | 600000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 1600 | 320 | 1280 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 368470 | 73694 | 294776 | 395000 | 79000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 36721 | 7344 | 29377 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 1952387 | 390477 | 1561909 | 4900000 | 980000 | 3920000 | 7058092 | 1411619 | 5646473 | 1952387 | 390477 | 1561909 | 4900000 | 980000 | 3920000 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2012 | Q3 | Q3 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 1200000 | 240000 | 960000 | 4535892 | 907179 | 3628713 | 3009082 | 601816 | 2407266 | 4300000 | 860000 | 3440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 140101 | 28020 | 112081 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 377688 | 75538 | 302150 | 395000 | 79000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 91925 | 18385 | 73540 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 3618796 | 723759 | 2895037 | 6215000 | 1243000 | 4972000 | 7058092 | 1411619 | 5646473 | 3618796 | 723759 | 2895037 | 6215000 | 1243000 | 4972000 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2012 | Q4 | Q4 - 2012 | 1150000 | 230000 | 920000 | 60885 | 12177 | 48708 | 1092500 | 218500 | 874000 | 4535892 | 907179 | 3628713 | 3698305 | 739661 | 2958644 | 4309097 | 861819 | 3447278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 90000 | 360000 | 250398 | 50080 | 200318 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 404065 | 80813 | 323252 | 542430 | 108486 | 433944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368700 | 73740 | 294960 | 180033 | 36007 | 144026 | 361326 | 72265 | 289061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 4593686 | 918738 | 3674948 | 6755353 | 1351070 | 5404283 | 7058092 | 1411619 | 5646473 | 4593686 | 918738 | 3674948 | 6755353 | 1351070 | 5404283 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2013 | Q1 | Q1 - 2013 | 1150000 | 230000 | 920000 | 830933 | 166187 | 664746 | 1115500 | 223100 | 892400 | 4535892 | 907179 | 3628713 | 4014644 | 802929 | 3211715 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 90000 | 360000 | 266087 | 53217 | 212870 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 436120 | 87224 | 348896 | 530145 | 106029 | 424116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368700 | 73740 | 294960 | 207194 | 41439 | 165755 | 365013 | 73003 | 292010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 5754978 | 1150996 | 4603982 | 6996550 | 1399311 | 5597239 | 7058092 | 1411619 | 5646473 | 5754978 | 1150996 | 4603982 | 6996550 | 1399311 | 5597239 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2013 | Q2 | Q2 - 2013 | 1370000 | 274000 | 1096000 | 979308 | 195862 | 783446 | 1370000 | 274000 | 1096000 | 4535892 | 907179 | 3628713 | 4363838 | 872768 | 3491070 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 62000 | 248000 | 271861 | 54372 | 217489 | 310000 | 62000 | 248000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 458909 | 91782 | 367127 | 553500 | 110700 | 442800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288700 | 57740 | 230960 | 212285 | 42457 | 169828 | 288700 | 57740 | 230960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 6286201 | 1257241 | 5028960 | 7058092 | 1411619 | 5646473 | 7058092 | 1411619 | 5646473 | 6286201 | 1257241 | 5028960 | 7058092 | 1411619 | 5646473 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570099 | INF | 2013 | Q3 | Q3 - 2013 | 1370000 | 274000 | 1096000 | 1350638 | 270128 | 1080510 | 1350638 | 270128 | 1080510 | 4535892 | 907179 | 3628713 | 4363838 | 872767 | 3491071 | 4363838 | 872767 | 3491071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 62000 | 248000 | 280193 | 56039 | 224154 | 280193 | 56039 | 224154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 480779 | 96156 | 384623 | 480779 | 96156 | 384623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288700 | 57740 | 230960 | 214366 | 42873 | 171493 | 214366 | 42873 | 171493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 6689814 | 1337963 | 5351851 | 6689814 | 1337963 | 5351851 | 7058092 | 1411619 | 5646473 | 6689814 | 1337963 | 5351851 | 6689814 | 1337963 | 5351851 | 0 | 0 | Bloomingdale Communications Inc
NT10BIX5570100 | INF | 2010 | Q4 | Q4 - 2010 | 15318520 | 4683718 | 10634802 | 119630 | 46347 | 73283 | 7659260 | 2341859 | 5317401 | 27051500 | 8271139 | 18780361 | 1075000 | 416475 | 658525 | 1182500 | 361556 | 820944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436390 | 169066 | 267324 | 436390 | 133429 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 1759574 | 681692 | 1077882 | 1935531 | 591799 | 1343732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 3390594 | 1313580 | 2077014 | 11213681 | 3428643 | 7785038 | 45395020 | 13879767 | 31515253 | 3390594 | 1313580 | 2077014 | 11213681 | 3428643 | 7785038 | 0 | 4 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2011 | Q1 | Q1 - 2011 | 15318520 | 4683718 | 10634802 | 8672215 | 1581217 | 7090998 | 8672215 | 2651576 | 6020639 | 27051500 | 8271139 | 18780361 | 5244651 | 956264 | 4288386 | 9178139 | 2806265 | 6371875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436390 | 79567 | 356822 | 436390 | 133429 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 2826014 | 515271 | 2310743 | 2826014 | 864069 | 1961945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 17179270 | 3132319 | 14046949 | 21112758 | 6455339 | 14657420 | 45395020 | 13879767 | 31515253 | 17179270 | 3132319 | 14046949 | 21112758 | 6455339 | 14657420 | 0 | 196 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2011 | Q2 | Q2 - 2011 | 15318520 | 4683718 | 10634802 | 10049486 | 2599297 | 7450189 | 12254816 | 3746975 | 8507841 | 27051500 | 8271139 | 18780361 | 8721362 | 2255778 | 6465583 | 11721362 | 3583868 | 8137493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436389 | 112872 | 323517 | 436390 | 133428 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 2784049 | 720094 | 2063956 | 2784049 | 851238 | 1932811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 21991286 | 5688041 | 16303245 | 27196617 | 8315509 | 18881106 | 45395020 | 13879767 | 31515253 | 21991286 | 5688041 | 16303245 | 27196617 | 8315509 | 18881106 | 0 | 910 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2011 | Q3 | Q3 - 2011 | 15318520 | 4683718 | 10634802 | 10408677 | 3215397 | 7193280 | 11408677 | 3488263 | 7920414 | 27051500 | 8271139 | 18780361 | 12247296 | 3783375 | 8463922 | 16247296 | 4967697 | 11279600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 442265 | 136622 | 305642 | 442265 | 135225 | 307040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 4510849 | 1393469 | 3117380 | 5510849 | 1684971 | 3825878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 27609087 | 8528863 | 19080224 | 33609087 | 10276156 | 23332932 | 45395020 | 13879767 | 31515253 | 27609087 | 8528863 | 19080224 | 33609087 | 10276156 | 23332932 | 0 | 981 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2011 | Q4 | Q4 - 2011 | 15318520 | 4683718 | 10634802 | 11154503 | 3315717 | 7838786 | 11654503 | 3563426 | 8091077 | 27051500 | 8271139 | 18780361 | 17258492 | 5130151 | 12128341 | 19258492 | 5888386 | 13370106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 132535 | 313330 | 445865 | 136326 | 309539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 5598653 | 1664220 | 3934433 | 6098653 | 1864695 | 4233958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 34457513 | 10242623 | 24214890 | 37457513 | 11452833 | 26004680 | 45395020 | 13879767 | 31515253 | 34457513 | 10242623 | 24214890 | 37457513 | 11452833 | 26004680 | 992 | 992 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2012 | Q1 | Q1 - 2012 | 15318520 | 4683718 | 10634802 | 12147204 | 3671839 | 8475365 | 12647204 | 3866949 | 8780255 | 27051500 | 8271139 | 18780361 | 22323722 | 6747983 | 15575740 | 24323722 | 7437106 | 16886616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134775 | 311089 | 445865 | 136326 | 309539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 5952317 | 1799258 | 4153059 | 6452317 | 1972830 | 4479487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 40869108 | 12353855 | 28515253 | 43869108 | 13413211 | 30455897 | 45395020 | 13879767 | 31515253 | 40869108 | 12353855 | 28515253 | 43869108 | 13413211 | 30455897 | 0 | 0 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2012 | Q2 | Q2 - 2012 | 15318520 | 4683718 | 10634802 | 12837591 | 3883439 | 8954152 | 13337591 | 4283439 | 9054152 | 27051500 | 8271139 | 18780361 | 25655370 | 7760886 | 17894484 | 27655370 | 9760886 | 17894484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6029621 | 1823992 | 4205629 | 6529621 | 2323992 | 4205629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 44968447 | 13603194 | 31365253 | 47968447 | 16503194 | 31465253 | 45395020 | 13879767 | 31515253 | 44968447 | 13603194 | 31365253 | 47968447 | 16503194 | 31465253 | 0 | 0 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2012 | Q3 | Q3 - 2012 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937782 | 17990424 | 25928207 | 7937782 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920014 | 4257706 | 6177720 | 1920014 | 4257706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 0 | 0 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2012 | Q4 | Q4 - 2012 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937782 | 17990424 | 25928207 | 7937782 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920014 | 4257706 | 6177720 | 1920014 | 4257706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 0 | 936567 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2013 | Q1 | Q1 - 2013 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937783 | 17990424 | 25928207 | 7937783 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920013 | 4257707 | 6177720 | 1920013 | 4257707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 0 | 1551711 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2013 | Q2 | Q2 - 2013 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937783 | 17990424 | 25928207 | 7937783 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920013 | 4257707 | 6177720 | 1920013 | 4257707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 0 | 2297358 | Delta Communications, L.L.C.
NT10BIX5570100 | INF | 2013 | Q3 | Q3 - 2013 | 15318520 | 4683718 | 10634802 | 13121595 | 5603198 | 7518397 | 13121595 | 5603198 | 7518397 | 27051500 | 8271139 | 18780361 | 34387889 | 14684354 | 19703535 | 34387889 | 14684354 | 19703535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 1315263 | 561645 | 753618 | 1315263 | 561645 | 753618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 2638017 | 3539703 | 6177720 | 2638017 | 3539703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 55002467 | 23487214 | 31515253 | 55002467 | 23487214 | 31515253 | 45395020 | 13879767 | 31515253 | 55002467 | 23487214 | 31515253 | 55002467 | 23487214 | 31515253 | 0 | 2556898 | Delta Communications, L.L.C.
NT10BIX5570101 | INF | 2010 | Q4 | Q4 - 2010 | 4116961 | 3844461 | 272500 | 0 | 0 | 0 | 3631426 | 3622926 | 8500 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 0 | 0 | 0 | 2885803 | 152882 | 2732921 | 539935 | 22882 | 459866 | 247600 | 0 | 247600 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 482978 | 0 | 482978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 120963 | 0 | 120963 | 175500 | 0 | 175500 | 586469 | 0 | 586469 | 24000 | 0 | 24000 | 97000 | 0 | 97000 | 279877 | 0 | 279877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 563 | 0 | 563 | 63315 | 0 | 63315 | 26730257 | 5443343 | 21286914 | 1420461 | 22882 | 1340392 | 4697819 | 3622926 | 1074893 | 26730257 | 5443343 | 21286914 | 1420461 | 22882 | 1340392 | 4697819 | 3622926 | 1074893 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2011 | Q1 | Q1 - 2011 | 4116961 | 3844461 | 272500 | 4003 | 0 | 4003 | 321692 | 287895 | 33797 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 0 | 0 | 0 | 2885803 | 152882 | 2732921 | 657323 | 22882 | 634441 | 926351 | 22882 | 903469 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 3260000 | 1166000 | 2070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 304820 | 0 | 304820 | 480320 | 0 | 480320 | 586469 | 0 | 586469 | 24000 | 0 | 24000 | 32011 | 0 | 32011 | 279877 | 0 | 279877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 10811 | 0 | 10811 | 23163 | 0 | 23163 | 26730257 | 5443343 | 21286914 | 1735957 | 22882 | 1713075 | 5043537 | 1476777 | 3542760 | 26730257 | 5443343 | 21286914 | 1735957 | 22882 | 1713075 | 5043537 | 1476777 | 3542760 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2011 | Q2 | Q2 - 2011 | 4116961 | 3844461 | 272500 | 105337 | 0 | 105337 | 3916819 | 3794461 | 122358 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 1062856 | 0 | 1062856 | 2885803 | 152882 | 2732921 | 837778 | 22882 | 814896 | 1062405 | 22882 | 1039523 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 3303000 | 1166000 | 2137000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 673026 | 0 | 673026 | 800939 | 0 | 813026 | 586469 | 0 | 586469 | 93000 | 0 | 93000 | 204087 | 0 | 192000 | 279877 | 0 | 279877 | 20000 | 0 | 20000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 31460 | 0 | 31460 | 38460 | 0 | 38460 | 26730257 | 5443343 | 21286914 | 2495601 | 22882 | 2472719 | 10438566 | 4983343 | 5455223 | 26730257 | 5443343 | 21286914 | 2495601 | 22882 | 2472719 | 10438566 | 4983343 | 5455223 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2011 | Q3 | Q3 - 2011 | 560395 | 287895 | 272500 | 419476 | 287895 | 131581 | 482538 | 287895 | 194643 | 18279455 | 5002566 | 13276889 | 5958913 | 5002566 | 956347 | 7603738 | 5002566 | 2601172 | 2885804 | 152882 | 2732922 | 1126493 | 22882 | 1103611 | 1418804 | 22882 | 1395922 | 3167019 | 0 | 3167019 | 2085000 | 0 | 2085000 | 2349556 | 0 | 2349556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 790026 | 0 | 790026 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 116351 | 0 | 116351 | 165910 | 0 | 165910 | 279877 | 0 | 279877 | 24750 | 0 | 24750 | 150695 | 0 | 150695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 32160 | 0 | 32160 | 36676 | 0 | 36676 | 26730258 | 5443343 | 21286915 | 10553169 | 5313343 | 5239826 | 13008856 | 5313343 | 7695513 | 26730258 | 5443343 | 21286915 | 10553169 | 5313343 | 5239826 | 13008856 | 5313343 | 7695513 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2011 | Q4 | Q4 - 2011 | 560395 | 287895 | 272500 | 499013 | 287895 | 211118 | 524905 | 287895 | 237010 | 18279455 | 5002566 | 13276889 | 6548598 | 5002566 | 1546032 | 9808490 | 5002566 | 4805924 | 2885804 | 152882 | 2732922 | 1300152 | 22882 | 1277270 | 1690682 | 152882 | 1537800 | 3167019 | 0 | 3167019 | 2085389 | 0 | 2085389 | 2095000 | 0 | 2095000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 791076 | 0 | 791076 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 116393 | 0 | 116393 | 171393 | 0 | 171393 | 279877 | 0 | 279877 | 23764 | 0 | 23764 | 70418 | 0 | 70418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 33372 | 0 | 33372 | 57368 | 0 | 57368 | 26730258 | 5443343 | 21286915 | 11397757 | 5313343 | 6084414 | 15219195 | 5443343 | 9775852 | 26730258 | 5443343 | 21286915 | 11397757 | 5313343 | 6084414 | 15219195 | 5443343 | 9775852 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2012 | Q1 | Q1 - 2012 | 1496395 | 287895 | 1208500 | 509993 | 287895 | 222098 | 1477985 | 287895 | 1190090 | 17874455 | 5002566 | 12871889 | 9620189 | 5002566 | 4617623 | 11933645 | 5002566 | 6931079 | 2885804 | 152882 | 2732922 | 1431605 | 22882 | 1408723 | 1768102 | 152882 | 1615220 | 2636019 | 0 | 2636019 | 2085989 | 0 | 2085989 | 2110601 | 0 | 2110601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 791076 | 0 | 791076 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 124266 | 0 | 124266 | 183266 | 0 | 183266 | 279877 | 0 | 279877 | 70188 | 0 | 70188 | 80188 | 0 | 80188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 34290 | 0 | 34290 | 89807 | 0 | 89807 | 26730258 | 5443343 | 21286915 | 14667596 | 5313343 | 9354253 | 18444533 | 5443343 | 13001190 | 26730258 | 5443343 | 21286915 | 14667596 | 5313343 | 9354253 | 18444533 | 5443343 | 13001190 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2012 | Q2 | Q2 - 2012 | 1496395 | 287895 | 1208500 | 518110 | 287895 | 230215 | 1486792 | 287895 | 1198897 | 17874455 | 5002566 | 12871889 | 12758529 | 5002566 | 7755963 | 14758529 | 5002566 | 9755963 | 2885804 | 152882 | 2732922 | 1691596 | 22882 | 1668714 | 1882074 | 152882 | 1729192 | 2636019 | 0 | 2636019 | 2122424 | 0 | 2122424 | 2122424 | 0 | 2122424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 795580 | 0 | 795580 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 244638 | 0 | 244638 | 346318 | 0 | 346318 | 279877 | 0 | 279877 | 75043 | 0 | 75043 | 90043 | 0 | 90043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 84659 | 0 | 84659 | 89175 | 0 | 89175 | 26730258 | 5443343 | 21286915 | 18290579 | 5313343 | 12977236 | 21576294 | 5443343 | 16132951 | 26730258 | 5443343 | 21286915 | 18290579 | 5313343 | 12977236 | 21576294 | 5443343 | 16132951 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2012 | Q3 | Q3 - 2012 | 1596395 | 287895 | 1308500 | 1495151 | 287895 | 1207256 | 1562590 | 287895 | 1274695 | 17874455 | 5002566 | 12871889 | 14106600 | 5002566 | 9104034 | 15672801 | 5002566 | 10670235 | 2885804 | 152882 | 2732922 | 1858087 | 22882 | 1835205 | 2191997 | 152882 | 2039115 | 2636019 | 0 | 2636019 | 2151807 | 0 | 2151807 | 2152196 | 0 | 2152196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797552 | 0 | 797552 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 358949 | 0 | 358949 | 407429 | 0 | 407429 | 179877 | 0 | 179877 | 95337 | 0 | 95337 | 100337 | 0 | 100337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 76682 | 0 | 76682 | 82685 | 0 | 82685 | 26730258 | 5443343 | 21286915 | 20940165 | 5313343 | 15626822 | 22970974 | 5443343 | 17527631 | 26730258 | 5443343 | 21286915 | 20940165 | 5313343 | 15626822 | 22970974 | 5443343 | 17527631 | 0 | 0 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2012 | Q4 | Q4 - 2012 | 1596395 | 287895 | 1308500 | 1553165 | 287895 | 1265269 | 1595165 | 287895 | 1307270 | 17874455 | 5002566 | 12871889 | 15145383 | 5002566 | 10142817 | 16356715 | 5002566 | 11354149 | 2885804 | 152882 | 2732922 | 2046194 | 22882 | 2023312 | 2368787 | 152882 | 2215905 | 2636019 | 0 | 2636019 | 2164902 | 0 | 2164902 | 2169902 | 0 | 2169902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797552 | 0 | 797553 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 439888 | 0 | 439888 | 463233 | 0 | 463233 | 179877 | 0 | 179877 | 97406 | 0 | 97406 | 122406 | 0 | 122406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 77247 | 0 | 77247 | 77997 | 0 | 77997 | 26730258 | 5443343 | 21286915 | 22321737 | 5313343 | 17008394 | 23955144 | 5443343 | 18511801 | 26730258 | 5443343 | 21286915 | 22321737 | 5313343 | 17008394 | 23955144 | 5443343 | 18511801 | 0 | 64837 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2013 | Q1 | Q1 - 2013 | 1596395 | 287895 | 1308500 | 1555489 | 287895 | 1267594 | 1595781 | 287895 | 1307886 | 17874455 | 5002566 | 12871889 | 15793108 | 5002566 | 10790542 | 17433108 | 5002566 | 12430542 | 2885804 | 152882 | 2732922 | 2237888 | 22882 | 2215006 | 2562577 | 152882 | 2409695 | 2636019 | 0 | 2636019 | 2178410 | 0 | 2178410 | 2191920 | 0 | 2191920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797553 | 0 | 797553 | 800342 | 0 | 800342 | 586469 | 0 | 586469 | 439888 | 0 | 439888 | 481888 | 0 | 481888 | 179877 | 0 | 179877 | 120093 | 0 | 120093 | 125093 | 0 | 125093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 78550 | 0 | 78550 | 90100 | 0 | 90100 | 26730258 | 5443343 | 21286915 | 23200979 | 5313343 | 17887636 | 25280809 | 5443343 | 19837466 | 26730258 | 5443343 | 21286915 | 23200979 | 5313343 | 17887636 | 25280809 | 5443343 | 19837466 | 0 | 116613 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2013 | Q2 | Q2 - 2013 | 1635018 | 287895 | 1347123 | 1633233 | 287895 | 1345338 | 1635018 | 287895 | 1347122 | 18325058 | 5002566 | 13322492 | 16976134 | 5002566 | 11973568 | 18325058 | 5002566 | 13322492 | 2885803 | 152882 | 2732921 | 2438741 | 22882 | 2415859 | 2716095 | 152882 | 2563213 | 2185416 | 0 | 2185416 | 2180592 | 0 | 2180592 | 2185416 | 0 | 2185416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 800342 | 0 | 800342 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 462106 | 0 | 462106 | 586469 | 0 | 586469 | 141254 | 0 | 141254 | 123419 | 0 | 123419 | 141254 | 0 | 141254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 91085 | 0 | 91085 | 170300 | 0 | 170300 | 26730257 | 5443343 | 21286914 | 24705652 | 5313343 | 19392309 | 26560549 | 5443343 | 21117205 | 26730257 | 5443343 | 21286914 | 24705652 | 5313343 | 19392309 | 26560549 | 5443343 | 21117205 | 0 | 181617 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2013 | Q3 | Q3 - 2013 | 1716750 | 287895 | 1428855 | 1636203 | 287895 | 1348308 | 1716750 | 287895 | 1428855 | 18226586 | 5002566 | 13224020 | 18151900 | 5002566 | 13149334 | 18226586 | 5002566 | 13224020 | 3025178 | 152882 | 2872296 | 2696102 | 152882 | 2543220 | 3025178 | 152882 | 2872296 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 800342 | 0 | 800342 | 800939 | 0 | 800939 | 570858 | 0 | 570858 | 570642 | 0 | 570642 | 570858 | 0 | 570858 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89786 | 0 | 89786 | 91285 | 0 | 91285 | 89786 | 0 | 89786 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 0 | 231272 | Appalachian Valley Fiber Network
NT10BIX5570101 | INF | 2013 | Q4 | Q4 - 2013 | 1716750 | 287895 | 1428855 | 1636203 | 287895 | 1348308 | 1716750 | 287895 | 1428855 | 18226586 | 5002566 | 13224020 | 18151900 | 5002566 | 13149334 | 18226586 | 5002566 | 13224020 | 3025178 | 152882 | 2872296 | 2696102 | 152882 | 2543220 | 3025178 | 152882 | 2872296 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 800342 | 0 | 800342 | 800939 | 0 | 800939 | 570858 | 0 | 570858 | 570642 | 0 | 570642 | 570858 | 0 | 570858 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89786 | 0 | 89786 | 91285 | 0 | 91285 | 89786 | 0 | 89786 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 0 | 231272 | Appalachian Valley Fiber Network
NT10BIX5570102 | INF | 2010 | Q4 | Q4 - 2010 | 43605098 | 15998347 | 27606751 | 18163 | 18163 | 0 | 3243231 | 1724106 | 1519126 | 28195212 | 0 | 28195212 | 0 | 0 | 0 | 0 | 0 | 0 | 10709094 | 88400 | 10620694 | 70132 | 0 | 70132 | 583157 | 0 | 583157 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 40474 | 0 | 40474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 0 | 0 | 0 | 406737 | 0 | 406737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 0 | 0 | 0 | 4107688 | 0 | 4107688 | 128581820 | 26450427 | 102131393 | 88295 | 18163 | 70132 | 8381287 | 1724106 | 6657182 | 128581820 | 26450427 | 102131393 | 88295 | 18163 | 70132 | 8381287 | 1724106 | 6657182 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2011 | Q1 | Q1 - 2011 | 43605098 | 15998347 | 27606751 | 153397 | 153397 | 0 | 1389853 | 1389853 | 0 | 28195212 | 0 | 28195212 | 266351 | 0 | 266351 | 4548485 | 0 | 4548485 | 10709094 | 88400 | 10620694 | 325950 | 0 | 325950 | 420950 | 0 | 420950 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 0 | 0 | 0 | 271985 | 0 | 271985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 0 | 0 | 0 | 125133 | 0 | 125133 | 128581820 | 26450427 | 102131393 | 745698 | 153397 | 592301 | 6756406 | 1389853 | 5366553 | 128581820 | 26450427 | 102131393 | 745698 | 153397 | 592301 | 6756406 | 1389853 | 5366553 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2011 | Q2 | Q2 - 2011 | 43605098 | 15998347 | 27606751 | 476323 | 476323 | 0 | 12139702 | 5246969 | 6892733 | 28195212 | 0 | 28195212 | 849269 | 0 | 849269 | 6478830 | 0 | 6478830 | 10709094 | 88400 | 10620694 | 717597 | 0 | 717597 | 1112210 | 0 | 1112210 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 501855 | 0 | 501855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 9062 | 0 | 9062 | 1072923 | 0 | 1072923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 263268 | 0 | 263268 | 4201244 | 0 | 4201244 | 128581820 | 26450427 | 102131393 | 2315519 | 476323 | 1839196 | 25506764 | 5246969 | 20259795 | 128581820 | 26450427 | 102131393 | 2315519 | 476323 | 1839196 | 25506764 | 5246969 | 20259795 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2011 | Q3 | Q3 - 2011 | 43605098 | 15998347 | 27606751 | 1830425 | 1562285 | 268140 | 17820121 | 7770683 | 10049438 | 28195212 | 0 | 28195212 | 4337618 | 0 | 4337618 | 13323856 | 0 | 13323856 | 10709094 | 88400 | 10620694 | 1111100 | 0 | 1111100 | 1383670 | 0 | 1383670 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 1048733 | 0 | 1048733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 9062 | 0 | 9062 | 905247 | 0 | 905247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 306434 | 0 | 306434 | 3293513 | 0 | 3293513 | 128581820 | 26450427 | 102131393 | 7594639 | 1562285 | 6032354 | 37775140 | 7770683 | 30004457 | 128581820 | 26450427 | 102131393 | 7594639 | 1562285 | 6032354 | 37775140 | 7770683 | 30004457 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2011 | Q4 | Q4 - 2011 | 43605098 | 15998347 | 27606751 | 13652238 | 5375145 | 8277093 | 28049199 | 12769706 | 15279493 | 28195212 | 0 | 28195212 | 8791538 | 0 | 8791538 | 22254747 | 0 | 22254747 | 10709094 | 88400 | 10620694 | 1600119 | 0 | 1600119 | 1966587 | 0 | 1966587 | 10711692 | 9851632 | 860060 | 820355 | 0 | 820355 | 2401179 | 0 | 2401179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 349591 | 0 | 349591 | 1727606 | 0 | 1727606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 916021 | 0 | 916020 | 5677263 | 0 | 5677263 | 128581820 | 26450427 | 102131393 | 26129862 | 5375145 | 20754716 | 62076581 | 12769706 | 49306875 | 128581820 | 26450427 | 102131393 | 26129862 | 5375145 | 20754716 | 62076581 | 12769706 | 49306875 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2012 | Q1 | Q1 - 2012 | 43605098 | 15998347 | 27606751 | 30295266 | 11269510 | 19025756 | 42514142 | 16862432 | 25651710 | 28195212 | 0 | 28195212 | 15124668 | 0 | 15124668 | 30159180 | 0 | 30159181 | 10709094 | 88400 | 10620694 | 2653828 | 0 | 2653828 | 3385052 | 431840 | 2953212 | 10711692 | 9851632 | 860060 | 2202902 | 0 | 2202902 | 4699099 | 1295520 | 3403579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 1949839 | 0 | 1949839 | 3492963 | 0 | 3492963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 2557266 | 0 | 2557266 | 8608151 | 512048 | 8096103 | 128581820 | 26450427 | 102131393 | 54783769 | 11269510 | 43514259 | 92858587 | 19101840 | 73756748 | 128581820 | 26450427 | 102131393 | 54783769 | 11269510 | 43514259 | 92858587 | 19101840 | 73756748 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2012 | Q2 | Q2 - 2012 | 43605098 | 15998347 | 27606751 | 39255851 | 16826106 | 22429745 | 43502827 | 16826106 | 26676721 | 28195212 | 0 | 28195212 | 20043544 | 0 | 20043544 | 27300579 | 0 | 27300579 | 10709094 | 88400 | 10620694 | 7114310 | 0 | 7114310 | 7748859 | 0 | 7748859 | 10711692 | 9851632 | 860060 | 4790229 | 1389108 | 3401121 | 9979639 | 5778836 | 4200803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2360448 | 0 | 2360448 | 3105327 | 0 | 3105327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17473295 | 512048 | 16961247 | 20739957 | 512048 | 20227909 | 128581820 | 26450427 | 102131393 | 91037677 | 18727262 | 72310415 | 112377188 | 23116990 | 89260198 | 128581820 | 26450427 | 102131393 | 91037677 | 18727262 | 72310415 | 112377188 | 23116990 | 89260198 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2012 | Q3 | Q3 - 2012 | 43605098 | 15998347 | 27606751 | 41655641 | 16844269 | 24811372 | 44068320 | 18325883 | 25742437 | 28195212 | 0 | 28195212 | 21893236 | 0 | 21893236 | 23003135 | 0 | 23003135 | 10709094 | 88400 | 10620694 | 7491920 | 0 | 7491920 | 8396699 | 528771 | 7867928 | 10711692 | 9851632 | 860060 | 5935408 | 2655255 | 3280153 | 8872980 | 4006388 | 4866592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2383964 | 0 | 2383964 | 3121384 | 0 | 3121384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17920845 | 512048 | 17408797 | 20388754 | 484694 | 19904060 | 128581820 | 26450427 | 102131393 | 97281014 | 20011572 | 77269442 | 107851272 | 23345736 | 84505536 | 128581820 | 26450427 | 102131393 | 97281014 | 20011572 | 77269442 | 107851272 | 23345736 | 84505536 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2012 | Q4 | Q4 - 2012 | 43605098 | 15998347 | 27606751 | 42729502 | 16844269 | 25885233 | 42729502 | 16862432 | 25867070 | 28195212 | 0 | 28195212 | 24014690 | 0 | 24014690 | 30571902 | 0 | 30571902 | 10709094 | 88400 | 10620694 | 7755741 | 0 | 7755741 | 9096236 | 920147 | 8176089 | 10711692 | 9851632 | 860060 | 7382533 | 3707269 | 3675264 | 13085407 | 6467712 | 6617695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2576165 | 0 | 2576165 | 3028386 | 0 | 3028386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17936474 | 512048 | 17424426 | 22679695 | 512048 | 22167647 | 128581820 | 26450427 | 102131393 | 102395105 | 21063586 | 81331519 | 121191128 | 24762339 | 96428789 | 128581820 | 26450427 | 102131393 | 102395105 | 21063586 | 81331519 | 121191128 | 24762339 | 96428789 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2013 | Q1 | Q1 - 2013 | 43605098 | 15998347 | 27606751 | 43221753 | 16844269 | 26377484 | 43960192 | 16844269 | 27115923 | 28195212 | 0 | 28195212 | 24312270 | 0 | 24312270 | 24678023 | 0 | 24678023 | 10709094 | 88400 | 10620694 | 8079684 | 0 | 8079684 | 9069925 | 35360 | 9034565 | 10711692 | 9851632 | 860060 | 8279485 | 4184936 | 4094549 | 10542482 | 6105980 | 4436502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2785399 | 0 | 2785399 | 3130439 | 0 | 3130439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 18038566 | 512048 | 17526518 | 29262305 | 512048 | 28750256 | 128581820 | 26450427 | 102131393 | 104717157 | 21541253 | 83175904 | 120643366 | 23497657 | 97145708 | 128581820 | 26450427 | 102131393 | 104717157 | 21541253 | 83175904 | 120643366 | 23497657 | 97145708 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2013 | Q2 | Q2 - 2013 | 43605098 | 15998347 | 27606751 | 42375446 | 15697330 | 26678115 | 43791782 | 15697331 | 28094451 | 28195212 | 0 | 28195212 | 24549072 | 0 | 24549073 | 25225336 | 0 | 25225336 | 10709094 | 88400 | 10620694 | 8423884 | 0 | 8423884 | 10625418 | 88400 | 10537018 | 10711692 | 9851632 | 860060 | 11039861 | 5961348 | 5078513 | 15274159 | 10195596 | 5078563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 3130545 | 0 | 3130545 | 3647999 | 0 | 3647999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 18049588 | 469100 | 17580488 | 30017126 | 469100 | 29548026 | 128581820 | 26450427 | 102131393 | 107568396 | 22127778 | 85440618 | 128581820 | 26450427 | 102131393 | 128581820 | 26450427 | 102131393 | 107568396 | 22127778 | 85440618 | 128581820 | 26450427 | 102131393 | 0 | 0 | University of Arkansas System
NT10BIX5570102 | INF | 2013 | Q3 | Q3 - 2013 | 43605098 | 15998347 | 27606751 | 45326575 | 17481259 | 27845316 | 45326575 | 17481259 | 27845316 | 28195212 | 0 | 28195212 | 25134127 | 0 | 25134127 | 25134127 | 0 | 25134127 | 10709094 | 88400 | 10620694 | 10742058 | 88400 | 10653658 | 10742617 | 88400 | 10654217 | 10711692 | 9851632 | 860060 | 13784726 | 8368720 | 5416006 | 13784726 | 8368720 | 5416006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 3266467 | 0 | 3266467 | 3266467 | 0 | 3266467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 30327308 | 512048 | 29815260 | 30327308 | 512048 | 29815260 | 128581820 | 26450427 | 102131393 | 128581261 | 26450427 | 102130834 | 128581820 | 26450427 | 102131393 | 128581820 | 26450427 | 102131393 | 128581261 | 26450427 | 102130834 | 128581820 | 26450427 | 102131393 | 0 | 0 | University of Arkansas System
NT10BIX5570103 | INF | 2010 | Q4 | Q4 - 2010 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 0 | 0 | 0 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 0 | 0 | 0 | 258125 | 55070 | 203055 | 77718 | 17471 | 60248 | 138540 | 29557 | 108983 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 36125 | 9101 | 27024 | 820728 | 175100 | 645628 | 1712850 | 365432 | 1347418 | 521971 | 100598 | 421373 | 1541017 | 328772 | 1212245 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 0 | 0 | 0 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 635814 | 127170 | 508645 | 2500285 | 533429 | 1966856 | 24971267 | 5327550 | 19643717 | 635814 | 127170 | 508645 | 2500285 | 533429 | 1966856 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2011 | Q1 | Q1 - 2011 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 0 | 0 | 0 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 0 | 0 | 0 | 258125 | 55070 | 203055 | 114693 | 25114 | 89579 | 138540 | 29557 | 108983 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 350247 | 76118 | 274128 | 1520728 | 324443 | 1196285 | 1712850 | 365432 | 1347418 | 661005 | 129501 | 531503 | 841017 | 179429 | 661588 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 0 | 0 | 0 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 1125945 | 230733 | 895210 | 2500285 | 533429 | 1966856 | 24971267 | 5327550 | 19643717 | 1125945 | 230733 | 895210 | 2500285 | 533429 | 1966856 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2011 | Q2 | Q2 - 2011 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 175532 | 37449 | 138083 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 4000 | 853 | 3147 | 258125 | 55070 | 203055 | 128236 | 28826 | 99410 | 149236 | 31839 | 117397 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 3750 | 800 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 765840 | 164784 | 601056 | 1520728 | 324443 | 1196285 | 1712850 | 365432 | 1347418 | 802236 | 166270 | 635966 | 841017 | 179429 | 661588 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 8180 | 1745 | 6434 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 1696312 | 359880 | 1336432 | 2702443 | 576558 | 2125884 | 24971267 | 5327550 | 19643717 | 1696312 | 359880 | 1336432 | 2702443 | 576558 | 2125884 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2011 | Q3 | Q3 - 2011 | 4225003 | 1259161 | 2965843 | 0 | 0 | 0 | 2112502 | 450696 | 1661805 | 10548955 | 3143862 | 7405093 | 0 | 0 | 0 | 0 | 0 | 0 | 1452700 | 432942 | 1019757 | 227003 | 177105 | 49898 | 251003 | 53551 | 197452 | 5186778 | 1545794 | 3640984 | 0 | 0 | 0 | 518678 | 110658 | 408019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 695560 | 1638330 | 1401590 | 1101170 | 300420 | 1916032 | 408780 | 1507252 | 1740318 | 518660 | 1221658 | 1001729 | 792898 | 208831 | 1171792 | 249998 | 921793 | 1832629 | 546171 | 1286458 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 197670 | 465594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983536 | 8339820 | 19643717 | 2630322 | 2071173 | 559149 | 5970007 | 1273683 | 4696321 | 27983536 | 8339820 | 19643717 | 2630322 | 2071173 | 559149 | 5970007 | 1273683 | 4696321 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2011 | Q4 | Q4 - 2011 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 0 | 0 | 0 | 0 | 0 | 0 | 1452699 | 309929 | 1142770 | 429031 | 93000 | 336031 | 453031 | 96653 | 356378 | 5186778 | 1170020 | 4016758 | 0 | 0 | 0 | 1556033 | 331975 | 1224058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2064442 | 441837 | 1622605 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1161327 | 242881 | 918446 | 1331391 | 284049 | 1047342 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 3654800 | 777718 | 2877082 | 9899347 | 2111999 | 7787348 | 27983535 | 8339818 | 19643717 | 3654800 | 777718 | 2877082 | 9899347 | 2111999 | 7787348 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2012 | Q1 | Q1 - 2012 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 0 | 0 | 0 | 0 | 0 | 0 | 1452699 | 309929 | 1142770 | 516281 | 111472 | 404809 | 540281 | 115267 | 425014 | 5186778 | 1170020 | 4016758 | 511930 | 109219 | 402712 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332025 | 497531 | 1833100 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1293042 | 272519 | 1021917 | 1463106 | 312150 | 1150956 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 364795 | 77828 | 286967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 4653278 | 990741 | 3662538 | 12039141 | 2568518 | 9470623 | 27983535 | 8339818 | 19643717 | 4653278 | 990741 | 3662538 | 12039141 | 2568518 | 9470623 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2012 | Q2 | Q2 - 2012 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 3409 | 727 | 2682 | 105490 | 22506 | 82984 | 1452699 | 309929 | 1142770 | 630314 | 134476 | 495838 | 720314 | 153677 | 566637 | 5186778 | 1170020 | 4016758 | 944138 | 201429 | 742709 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2283652 | 487211 | 1796441 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1426164 | 304268 | 1121896 | 1516164 | 323469 | 1192695 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 364795 | 77828 | 286967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 5287677 | 1128111 | 4159566 | 12377722 | 2640753 | 9736969 | 27983535 | 8339818 | 19643717 | 5287677 | 1128111 | 4159566 | 12377722 | 2640753 | 9736969 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2012 | Q3 | Q3 - 2012 | 4225003 | 1520599 | 2704404 | 2599462 | 586930 | 2012532 | 3802502 | 811253 | 2991249 | 10548955 | 3763638 | 6785317 | 75021 | 16004 | 59017 | 1054896 | 225059 | 829837 | 1452699 | 309929 | 1142770 | 770245 | 164330 | 605915 | 860245 | 183531 | 676714 | 5186778 | 1170020 | 4016758 | 1993495 | 425307 | 1568188 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299148 | 490517 | 1808631 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1516570 | 323556 | 1193014 | 1606570 | 342757 | 1263813 | 1832629 | 390986 | 1441643 | 167149 | 35661 | 131488 | 632649 | 134974 | 497675 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 132653 | 28301 | 104352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 9421090 | 2042305 | 7378785 | 13535471 | 2887755 | 10647716 | 27983535 | 8339818 | 19643717 | 9421090 | 2042305 | 7378785 | 13535471 | 2887755 | 10647716 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2012 | Q4 | Q4 - 2012 | 4225003 | 1520599 | 2704404 | 3362102 | 749637 | 2612465 | 3802502 | 811253 | 2991249 | 10548955 | 3763638 | 6785317 | 404721 | 92869 | 311852 | 4219582 | 900236 | 3319346 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 5186778 | 1170020 | 4016758 | 1477900 | 315305 | 1162595 | 3890083 | 829938 | 3060145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 725658 | 154817 | 570841 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 198980 | 42452 | 156528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 10204063 | 2215873 | 7988190 | 17657692 | 3767219 | 13890473 | 27983535 | 8339818 | 19643717 | 10204063 | 2215873 | 7988190 | 17657692 | 3767219 | 13890473 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2013 | Q1 | Q1 - 2013 | 5365839 | 1520599 | 3845240 | 3362102 | 749637 | 2612465 | 4959255 | 1058043 | 3901212 | 11246049 | 3763638 | 7482411 | 404721 | 92869 | 311852 | 2049210 | 437193 | 1612017 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 3422544 | 1170020 | 2252524 | 1477901 | 315306 | 1162595 | 1507901 | 321706 | 1186195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740317 | 371292 | 1369025 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 1368808 | 292031 | 1076777 | 589568 | 315425 | 274143 | 0 | 0 | 0 | 176871 | 37735 | 139136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2013 | Q2 | Q2 - 2013 | 5365839 | 1520599 | 3845240 | 3362102 | 749637 | 2612465 | 4959255 | 1058043 | 3901212 | 11246049 | 3763638 | 7482411 | 404721 | 92869 | 311852 | 2049210 | 437193 | 1612017 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 3422544 | 1170020 | 2252524 | 1477901 | 315306 | 1162595 | 1507901 | 321706 | 1186195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740317 | 371292 | 1369025 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 1368808 | 292031 | 1076777 | 589568 | 315425 | 274143 | 0 | 0 | 0 | 176871 | 37735 | 139136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2013 | Q3 | Q3 - 2013 | 5365839 | 1520599 | 3845240 | 4102677 | 749637 | 3353040 | 4104150 | 749952 | 3354199 | 11246049 | 3763638 | 7482411 | 1350201 | 92869 | 1257332 | 2251376 | 681533 | 1569842 | 1452699 | 309929 | 1142770 | 934283 | 172449 | 761835 | 1008915 | 188371 | 820544 | 3422544 | 1170020 | 2252524 | 1531661 | 315306 | 1216355 | 1556661 | 320640 | 1236022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1740317 | 371292 | 1369025 | 1532002 | 326848 | 1205154 | 1569002 | 334742 | 1234260 | 1832629 | 390986 | 1441643 | 533938 | 75367 | 458572 | 533938 | 75367 | 458572 | 589568 | 315425 | 274143 | 147400 | 0 | 147400 | 147400 | 0 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2013 | Q4 | Q4 - 2013 | 5365839 | 1520599 | 3845240 | 4102677 | 749637 | 3353040 | 4104150 | 749952 | 3354199 | 11246049 | 3763638 | 7482411 | 1350201 | 92869 | 1257332 | 2251376 | 681533 | 1569842 | 1452699 | 309929 | 1142770 | 934283 | 172449 | 761835 | 1008915 | 188371 | 820544 | 3422544 | 1170020 | 2252524 | 1531661 | 315306 | 1216355 | 1556661 | 320640 | 1236022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1740317 | 371292 | 1369025 | 1532002 | 326848 | 1205154 | 1569002 | 334742 | 1234260 | 1832629 | 390986 | 1441643 | 533938 | 75367 | 458572 | 533938 | 75367 | 458572 | 589568 | 315425 | 274143 | 147400 | 0 | 147400 | 147400 | 0 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2014 | Q1 | Q1 - 2014 | 5585357 | 1191621 | 4393736 | 4339232 | 986192 | 3353040 | 5233116 | 986192 | 4246924 | 8678553 | 1851545 | 6827008 | 1420483 | 163151 | 1257332 | 1729424 | 368955 | 1360469 | 2263278 | 482864 | 1780414 | 1212670 | 450835 | 761835 | 1682002 | 460835 | 1221167 | 2006522 | 428086 | 1578436 | 1531661 | 315306 | 1216355 | 1531661 | 315306 | 1216355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1532801 | 327019 | 1205782 | 1532002 | 326848 | 1205154 | 1532002 | 326848 | 1205154 | 946753 | 201987 | 744766 | 537697 | 79125 | 458572 | 678616 | 123442 | 555174 | 818506 | 174626 | 643880 | 247442 | 100042 | 147400 | 519813 | 136042 | 383771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 13154137 | 2912002 | 10242135 | 15239584 | 3208123 | 12031461 | 24971267 | 5327550 | 19643717 | 13154137 | 2912002 | 10242135 | 15239584 | 3208123 | 12031461 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2014 | Q2 | Q2 - 2014 | 5585357 | 1191621 | 4393736 | 5142189 | 1016753 | 4125436 | 5237301 | 1111865 | 4125436 | 8678553 | 1851545 | 6827008 | 1708476 | 182979 | 1525497 | 2216079 | 291271 | 1924808 | 2263278 | 482864 | 1780414 | 1573155 | 482913 | 1090242 | 1720540 | 514991 | 1205549 | 2006522 | 428086 | 1578436 | 1531661 | 315306 | 1216355 | 1531661 | 315306 | 1216355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1532801 | 327019 | 1205782 | 1532002 | 326848 | 1205154 | 1532002 | 326848 | 1205154 | 946753 | 201987 | 744766 | 553030 | 80715 | 472315 | 560486 | 82306 | 478180 | 818506 | 174626 | 643880 | 681895 | 200084 | 481811 | 681895 | 200084 | 481811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 15055358 | 3096101 | 11959257 | 15812914 | 3333174 | 12479740 | 24971267 | 5327550 | 19643717 | 15055358 | 3096101 | 11959257 | 15812914 | 3333174 | 12479740 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2014 | Q3 | Q3 - 2014 | 5585357 | 1191621 | 4393736 | 5223534 | 1016753 | 4206781 | 5266388 | 1016753 | 4249635 | 8678553 | 1851545 | 6827008 | 2674842 | 205696 | 2469146 | 3834613 | 205696 | 3628917 | 2263278 | 482864 | 1780414 | 1812665 | 503792 | 1308873 | 1960547 | 521792 | 1438755 | 2006522 | 428086 | 1578436 | 1856776 | 527282 | 1329494 | 1856776 | 527282 | 1329494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 2787480 | 702478 | 2085002 | 3483871 | 1033690 | 2450181 | 1532801 | 327019 | 1205782 | 1532801 | 326849 | 1205952 | 1532801 | 326849 | 1205952 | 946753 | 201987 | 744766 | 910300 | 292691 | 617609 | 1333802 | 607448 | 726354 | 818506 | 174626 | 643880 | 730645 | 244974 | 485671 | 833329 | 347198 | 486131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 17529043 | 3820515 | 13708528 | 20102127 | 4586708 | 15515419 | 24971267 | 5327550 | 19643717 | 17529043 | 3820515 | 13708528 | 20102127 | 4586708 | 15515419 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2014 | Q4 | Q4 - 2014 | 5585357 | 1191621 | 4393736 | 5336154 | 1016753 | 4319401 | 5380907 | 1036753 | 4344154 | 8678553 | 1851545 | 6827008 | 4079311 | 252843 | 3826468 | 5517961 | 576085 | 4941876 | 2263278 | 482864 | 1780414 | 1982595 | 527488 | 1455107 | 2137133 | 588613 | 1548520 | 2006522 | 428086 | 1578436 | 1856776 | 527282 | 1329494 | 1910566 | 527282 | 1383284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 4059447 | 951609 | 3107838 | 4334954 | 971609 | 3363345 | 1532801 | 327019 | 1205782 | 1532801 | 326849 | 1205952 | 1532801 | 326849 | 1205952 | 946753 | 201987 | 744766 | 1290230 | 515410 | 774820 | 1583348 | 515410 | 1067938 | 818506 | 174626 | 643880 | 830020 | 344349 | 485671 | 918200 | 432529 | 485671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 20967334 | 4462583 | 16504751 | 23315870 | 4975130 | 18340740 | 24971267 | 5327550 | 19643717 | 20967334 | 4462583 | 16504751 | 23315870 | 4975130 | 18340740 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2015 | Q1 | Q1 - 2015 | 5585357 | 1191621 | 4393736 | 5360933 | 1016753 | 4344180 | 5387879 | 1016753 | 4371126 | 8678553 | 1851545 | 6827008 | 4955428 | 306343 | 4649085 | 6045054 | 628872 | 5416182 | 2263278 | 482864 | 1780414 | 2169801 | 582557 | 1587244 | 2232464 | 630557 | 1601907 | 2006522 | 428086 | 1578436 | 1910567 | 529154 | 1381413 | 1945105 | 544392 | 1400713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 4395630 | 1103648 | 3291982 | 4459482 | 1105610 | 3353872 | 1532801 | 327019 | 1205782 | 1532801 | 326849 | 1205952 | 1532801 | 326849 | 1205952 | 946753 | 201987 | 744766 | 1702017 | 648470 | 1053547 | 1862322 | 746561 | 1115761 | 818506 | 174626 | 643880 | 942045 | 389826 | 552219 | 1080858 | 464653 | 616205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 22969222 | 4903600 | 18065622 | 24545965 | 5464247 | 19081718 | 24971267 | 5327550 | 19643717 | 22969222 | 4903600 | 18065622 | 24545965 | 5464247 | 19081718 | 0 | 0 | Nevada Hospital Association
NT10BIX5570103 | INF | 2015 | Q2 | Q2 - 2015 | 5585357 | 1191621 | 4393736 | 5364080 | 1016843 | 4347237 | 5629328 | 1142488 | 4486840 | 8678553 | 1851545 | 6827008 | 6383796 | 732026 | 5651770 | 9524774 | 3855787 | 5668987 | 2263278 | 482864 | 1780414 | 2238860 | 627816 | 1611044 | 2458255 | 839349 | 1618906 | 2006522 | 428086 | 1578436 | 1929867 | 529154 | 1400713 | 1983805 | 544392 | 1439413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139497 | 669802 | 2469695 | 4610558 | 1228840 | 3381718 | 4724841 | 1235234 | 3489607 | 1532801 | 327019 | 1205782 | 1532801 | 326849 | 1205952 | 1532801 | 326849 | 1205952 | 946753 | 201987 | 744766 | 1808378 | 749585 | 1058793 | 1896418 | 778264 | 1118154 | 818506 | 174626 | 643880 | 1050466 | 434609 | 615857 | 1282038 | 666181 | 615857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 24918806 | 5645722 | 19273084 | 29032260 | 9388544 | 19643716 | 24971267 | 5327550 | 19643717 | 24918806 | 5645722 | 19273084 | 29032260 | 9388544 | 19643716 | 0 | 0 | Nevada Hospital Association
NT10BIX5570104 | INF | 2010 | Q4 | Q4 - 2010 | 2117516 | 423503 | 1694013 | 8016 | 1603 | 6413 | 136416 | 27283 | 109133 | 11339864 | 2267973 | 9071891 | 22487 | 449 | 17989 | 166318 | 33264 | 133054 | 93905 | 18781 | 75124 | 21000 | 4200 | 16800 | 75396 | 15079 | 60317 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 5007 | 1001 | 4006 | 42907 | 8582 | 34325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 3058 | 612 | 2446 | 18058 | 3612 | 14446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 59568 | 7865 | 47654 | 439095 | 87820 | 351275 | 14480584 | 2896117 | 11584467 | 59568 | 7865 | 47654 | 439095 | 87820 | 351275 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2011 | Q1 | Q1 - 2011 | 2117516 | 423503 | 1694013 | 9762 | 1952 | 7810 | 420762 | 84152 | 336610 | 11339864 | 2267973 | 9071891 | 115615 | 23123 | 92492 | 1655296 | 331059 | 1324237 | 93905 | 18781 | 75124 | 80025 | 16005 | 64020 | 89863 | 17973 | 71890 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 29939 | 5988 | 23951 | 42323 | 8465 | 33858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 5970 | 1194 | 4776 | 35970 | 7194 | 28776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 241311 | 48262 | 193049 | 2326714 | 465343 | 1861371 | 14480584 | 2896117 | 11584467 | 241311 | 48262 | 193049 | 2326714 | 465343 | 1861371 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2011 | Q2 | Q2 - 2011 | 2117516 | 423503 | 1694013 | 247210 | 49442 | 197768 | 425210 | 85042 | 340168 | 11339864 | 2267973 | 9071891 | 1578316 | 315633 | 1262653 | 3178166 | 635633 | 2542533 | 93905 | 18781 | 75124 | 80025 | 16005 | 64020 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 26866 | 5373 | 21493 | 56866 | 11373 | 45493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 2047441 | 409458 | 1637953 | 3877271 | 775454 | 3101817 | 14480584 | 2896117 | 11584467 | 2047441 | 409458 | 1637953 | 3877271 | 775454 | 3101817 | 0 | 0 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2011 | Q3 | Q3 - 2011 | 2117516 | 423503 | 1694013 | 254796 | 50959 | 203837 | 414112 | 82822 | 331290 | 11339864 | 2267973 | 9071891 | 3128457 | 625665 | 2502792 | 3551983 | 710397 | 2841586 | 93905 | 1878 | 75124 | 80363 | 16073 | 64290 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 61306 | 12261 | 49045 | 71447 | 14289 | 57158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2879214 | 11584467 | 3639946 | 727963 | 2911983 | 4254571 | 850914 | 3403657 | 14480584 | 2879214 | 11584467 | 3639946 | 727963 | 2911983 | 4254571 | 850914 | 3403657 | 185043 | 182883 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2011 | Q4 | Q4 - 2011 | 2117516 | 423503 | 1694013 | 504597 | 100919 | 403678 | 529494 | 105899 | 423595 | 11339864 | 2267973 | 9071891 | 4062838 | 812563 | 3250271 | 4422196 | 884439 | 3537757 | 93905 | 18781 | 75124 | 81430 | 16286 | 65144 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 154180 | 30836 | 123344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 74018 | 14804 | 59214 | 84029 | 16806 | 67223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 4837907 | 967577 | 3870326 | 5318904 | 1063781 | 4255123 | 14480584 | 2896117 | 11584467 | 4837907 | 967577 | 3870326 | 5318904 | 1063781 | 4255123 | 370085 | 323190 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2012 | Q1 | Q1 - 2012 | 2117516 | 423503 | 1694013 | 568352 | 113670 | 454681 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 4275854 | 855158 | 3420696 | 7755710 | 1551142 | 6204568 | 93905 | 18781 | 75124 | 81431 | 16286 | 65145 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 94995 | 18999 | 75996 | 175500 | 35100 | 140400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 100240 | 20048 | 80192 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 5163752 | 1032737 | 4131014 | 9701991 | 1940398 | 7761593 | 14480584 | 2896117 | 11584467 | 5163752 | 1032737 | 4131014 | 9701991 | 1940398 | 7761593 | 675463 | 510471 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2012 | Q2 | Q2 - 2012 | 2117516 | 423503 | 1694013 | 781033 | 156207 | 624826 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 5476746 | 1095349 | 4381397 | 8662990 | 1732598 | 6930392 | 93905 | 18781 | 75124 | 81641 | 16328 | 65313 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 239577 | 47915 | 191662 | 256500 | 51300 | 205200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 148960 | 29792 | 119168 | 167950 | 33590 | 134360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 6770837 | 1354167 | 5416670 | 10708221 | 2141644 | 8566577 | 14480584 | 2896117 | 11584467 | 6770837 | 1354167 | 5416670 | 10708221 | 2141644 | 8566577 | 610756 | 473186 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2012 | Q3 | Q3 - 2012 | 2117516 | 423503 | 1694013 | 999550 | 199910 | 799640 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 7215381 | 1443077 | 5772304 | 8990600 | 1798120 | 7192480 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 285821 | 57164 | 228657 | 290000 | 58000 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 189278 | 37856 | 151422 | 215000 | 43000 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 8826815 | 1765364 | 7061451 | 11116381 | 2223276 | 8893105 | 14480584 | 2896117 | 11584467 | 8826815 | 1765364 | 7061451 | 11116381 | 2223276 | 8893105 | 1286219 | 868632 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2012 | Q4 | Q4 - 2012 | 2117516 | 423503 | 1694013 | 1026671 | 205334 | 821337 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 8710405 | 1742044 | 6968361 | 10210405 | 2042081 | 8168324 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 315628 | 63126 | 252502 | 340000 | 68000 | 272000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 224102 | 44820 | 179282 | 260102 | 52020 | 208082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 10413591 | 2082681 | 8330910 | 12431288 | 2486257 | 9945031 | 14480584 | 2896117 | 11584467 | 10413591 | 2082681 | 8330910 | 12431288 | 2486257 | 9945031 | 1591597 | 1097880 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2013 | Q1 | Q1 - 2013 | 2117516 | 423503 | 1694013 | 1045967 | 209193 | 836774 | 2117516 | 423503 | 1694013 | 11339864 | 2267973 | 9071891 | 8946774 | 1789319 | 7157455 | 10500000 | 2100000 | 8400000 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 315665 | 63133 | 252532 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 231087 | 46217 | 184870 | 280000 | 56000 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 10676278 | 2135219 | 8541059 | 13435421 | 2687084 | 10748337 | 14480584 | 2896117 | 11584467 | 10676278 | 2135219 | 8541059 | 13435421 | 2687084 | 10748337 | 2038689 | 1398904 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2013 | Q2 | Q2 - 2013 | 2117516 | 423503 | 1694013 | 1650718 | 330144 | 1320574 | 2650000 | 530000 | 2120000 | 11339864 | 2267973 | 9071891 | 10444363 | 2088872 | 8355491 | 10949923 | 2189984 | 8759939 | 93905 | 18781 | 75124 | 108148 | 21630 | 86518 | 108148 | 21630 | 86518 | 384000 | 76800 | 307200 | 352072 | 70414 | 281658 | 370334 | 74067 | 296267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 303680 | 60736 | 242944 | 359299 | 71860 | 287439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 12901861 | 2580372 | 10321489 | 14480584 | 2896117 | 11584467 | 14480584 | 2896117 | 11584467 | 12901861 | 2580372 | 10321489 | 14480584 | 2896117 | 11584467 | 2485782 | 1650651 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2013 | Q3 | Q3 - 2013 | 2117516 | 423503 | 1694013 | 2182735 | 436548 | 1746187 | 2214763 | 442952 | 1771811 | 11339864 | 2267973 | 9071891 | 10802955 | 2160590 | 8642365 | 11339864 | 2267973 | 9071891 | 93905 | 18781 | 75124 | 109143 | 21829 | 87314 | 109143 | 21829 | 87314 | 384000 | 76800 | 307200 | 370741 | 74148 | 296593 | 370741 | 74148 | 296593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 368193 | 73639 | 294554 | 403193 | 80639 | 322554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 13876647 | 2775330 | 11101317 | 14480584 | 2896117 | 11584467 | 14480584 | 2896117 | 11584467 | 13876647 | 2775330 | 11101317 | 14480584 | 2896117 | 11584467 | 0 | 1994382 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2013 | Q4 | Q4 - 2013 | 2117516 | 423503 | 1694013 | 2348287 | 469657 | 1878630 | 2348287 | 469657 | 1878630 | 11339864 | 2267973 | 9071891 | 11270331 | 2331860 | 8938797 | 11310331 | 2371534 | 8938797 | 93905 | 18781 | 75124 | 109175 | 21835 | 87340 | 109175 | 21835 | 87340 | 384000 | 76800 | 307200 | 390933 | 78187 | 312746 | 390933 | 78187 | 312746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 415812 | 83162 | 332650 | 415812 | 83162 | 332650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 14577418 | 2993277 | 11584467 | 14617418 | 3032951 | 11584467 | 14480584 | 2896117 | 11584467 | 14577418 | 2993277 | 11584467 | 14617418 | 3032951 | 11584467 | 0 | 2354253 | Contact Network Inc. d/b/a InLine
NT10BIX5570104 | INF | 2014 | Q1 | Q1 - 2014 | 2117516 | 423503 | 1694013 | 2351801 | 473171 | 1878630 | 2351801 | 473171 | 1878630 | 11339864 | 2267973 | 9071891 | 11299940 | 2361143 | 8938797 | 11299940 | 2361143 | 8938797 | 93905 | 18781 | 75124 | 109175 | 21835 | 87340 | 109175 | 21834 | 87340 | 384000 | 76800 | 307200 | 390933 | 78187 | 312746 | 390933 | 78187 | 312746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 415812 | 83162 | 332650 | 415812 | 83162 | 332650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 14610541 | 3026074 | 11584467 | 14610541 | 3026073 | 11584467 | 14480584 | 2896117 | 11584467 | 14610541 | 3026074 | 11584467 | 14610541 | 3026073 | 11584467 | 0 | 2768372 | Contact Network Inc. d/b/a InLine
NT10BIX5570105 | INF | 2010 | Q4 | Q4 - 2010 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 0 | 0 | 0 | 30000 | 0 | 30000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 2287497 | 2287497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 0 | 0 | 0 | 94000 | 0 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 0 | 0 | 0 | 2661497 | 2287497 | 374000 | 51188152 | 11550000 | 39638152 | 0 | 0 | 0 | 2661497 | 2287497 | 374000 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2011 | Q1 | Q1 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 0 | 0 | 0 | 30000 | 0 | 30000 | 14390880 | 11550000 | 2840880 | 589682 | 589682 | 0 | 689682 | 689682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 14477 | 0 | 14477 | 134000 | 0 | 134000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 604159 | 589682 | 14477 | 1103682 | 689682 | 414000 | 51188152 | 11550000 | 39638152 | 604159 | 589682 | 14477 | 1103682 | 689682 | 414000 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2011 | Q2 | Q2 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 63458 | 0 | 63458 | 126801 | 0 | 126801 | 14390880 | 11550000 | 2840880 | 689682 | 689682 | 0 | 1086682 | 1086682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 90673 | 0 | 90673 | 115673 | 0 | 115673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 843813 | 689682 | 154131 | 1579156 | 1086682 | 492474 | 51188152 | 11550000 | 39638152 | 843813 | 689682 | 154131 | 1579156 | 1086682 | 492474 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2011 | Q3 | Q3 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 78458 | 15000 | 63458 | 180000 | 30000 | 150000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 133747 | 0 | 133747 | 133747 | 0 | 133747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 212205 | 15000 | 197205 | 663747 | 130000 | 533747 | 51188152 | 11550000 | 39638152 | 212205 | 15000 | 197205 | 663747 | 130000 | 533747 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2011 | Q4 | Q4 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 150852 | 30000 | 120852 | 280000 | 30000 | 250000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 133747 | 0 | 133747 | 133747 | 0 | 133747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 284599 | 30000 | 254599 | 763747 | 130000 | 633747 | 51188152 | 11550000 | 39638152 | 284599 | 30000 | 254599 | 763747 | 130000 | 633747 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2012 | Q1 | Q1 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 148852 | 28000 | 120852 | 178000 | 28000 | 150000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 150000 | 0 | 150000 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134604 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 2000 | 0 | 2000 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 464604 | 28000 | 436604 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 464604 | 28000 | 436604 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2012 | Q2 | Q2 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 148852 | 28000 | 120852 | 295591 | 28000 | 267591 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 100024 | 0 | 100024 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134504 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 1800 | 0 | 1800 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 531919 | 28000 | 504019 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 531919 | 28000 | 504019 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2012 | Q3 | Q3 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 323671 | 53975 | 269696 | 434344 | 0 | 434344 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 100024 | 0 | 100024 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134604 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 595 | 0 | 595 | 51188152 | 11550000 | 39638152 | 530788 | 81975 | 448813 | 697567 | 28000 | 669567 | 51188152 | 11550000 | 39638152 | 530788 | 81975 | 448813 | 697567 | 28000 | 669567 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2012 | Q4 | Q4 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 457189 | 0 | 457189 | 789516 | 0 | 789516 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 86638 | 0 | 86638 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 321804 | 0 | 321804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 822 | 0 | 822 | 822 | 0 | 822 | 51188152 | 11550000 | 39638152 | 664533 | 28000 | 636533 | 1226780 | 28000 | 1198780 | 51188152 | 11550000 | 39638152 | 664533 | 28000 | 636533 | 1226780 | 28000 | 1198780 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2013 | Q1 | Q1 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 628852 | 0 | 628852 | 853935 | 0 | 853935 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 107985 | 0 | 107985 | 108057 | 0 | 108057 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 238460 | 0 | 238460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1755 | 0 | 1755 | 1755 | 0 | 1755 | 51188152 | 11550000 | 39638152 | 901196 | 28000 | 873196 | 1230207 | 28000 | 1202207 | 51188152 | 11550000 | 39638152 | 901196 | 28000 | 873196 | 1230207 | 28000 | 1202207 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2013 | Q2 | Q2 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 882871 | 52960 | 829911 | 1294704 | 464792 | 829911 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 110309 | 0 | 110309 | 160611 | 50302 | 110309 | 1618825 | 0 | 1618825 | 162604 | 28000 | 134604 | 255124 | 120520 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1755 | 0 | 1755 | 1755 | 0 | 1755 | 51188152 | 11550000 | 39638152 | 1157539 | 80960 | 1076579 | 1712194 | 635614 | 1076579 | 51188152 | 11550000 | 39638152 | 1157539 | 80960 | 1076579 | 1712194 | 635614 | 1076579 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2013 | Q3 | Q3 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1098598 | 256003 | 842595 | 1467182 | 348683 | 1118499 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 130611 | 20302 | 110309 | 157999 | 20302 | 137697 | 1618825 | 0 | 1618825 | 242735 | 108131 | 134604 | 270805 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1756 | 0 | 1756 | 1756 | 0 | 1756 | 51188152 | 11550000 | 39638152 | 1473700 | 384436 | 1089264 | 1897742 | 505187 | 1392556 | 51188152 | 11550000 | 39638152 | 1473700 | 384436 | 1089264 | 1897742 | 505187 | 1392556 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2013 | Q4 | Q4 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1387503 | 531005 | 856498 | 1608180 | 728455 | 879726 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 139923 | 20302 | 119621 | 182549 | 20302 | 162247 | 1618825 | 0 | 1618825 | 270805 | 136202 | 134604 | 270805 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1756 | 0 | 1756 | 1756 | 0 | 1756 | 51188152 | 11550000 | 39638152 | 1799987 | 687509 | 1112479 | 2063290 | 884959 | 1178333 | 51188152 | 11550000 | 39638152 | 1799987 | 687509 | 1112479 | 2063290 | 884959 | 1178333 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2014 | Q1 | Q1 - 2014 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1650084 | 625938 | 1024146 | 1958045 | 748899 | 1209146 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 190870 | 20302 | 170568 | 240870 | 50302 | 190568 | 1618825 | 0 | 1618825 | 270806 | 136202 | 134604 | 270806 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1756 | 0 | 1756 | 1756 | 0 | 1756 | 51188152 | 11550000 | 39638152 | 2113516 | 782442 | 1331074 | 2471477 | 935403 | 1536074 | 51188152 | 11550000 | 39638152 | 2113516 | 782442 | 1331074 | 2471477 | 935403 | 1536074 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2014 | Q2 | Q2 - 2014 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1953734 | 741071 | 1212663 | 2162734 | 800071 | 1362663 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 236777 | 20302 | 216475 | 266777 | 20302 | 246475 | 1618825 | 0 | 1618825 | 270806 | 136202 | 134604 | 270806 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 3783 | 498 | 3285 | 5783 | 898 | 4885 | 51188152 | 11550000 | 39638152 | 2465100 | 898073 | 1567027 | 2706100 | 957473 | 1748627 | 51188152 | 11550000 | 39638152 | 2465100 | 898073 | 1567027 | 2706100 | 957473 | 1748627 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2014 | Q3 | Q3 - 2014 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 2212426 | 839206 | 1373220 | 2274886 | 902206 | 1372680 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 284452 | 26359 | 258094 | 326453 | 28359 | 298094 | 1618825 | 0 | 1618825 | 270806 | 136202 | 134604 | 270806 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 3968 | 498 | 3470 | 3968 | 498 | 3470 | 51188152 | 11550000 | 39638152 | 2771652 | 1002265 | 1769388 | 2876113 | 1067265 | 1808848 | 51188152 | 11550000 | 39638152 | 2771652 | 1002265 | 1769388 | 2876113 | 1067265 | 1808848 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2014 | Q4 | Q4 - 2014 | 13544926 | 0 | 13544926 | 3491524 | 785593 | 2705931 | 31363873 | 6785593 | 24578280 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 2735267 | 1309132 | 1426135 | 2944267 | 1368132 | 1576135 | 12750418 | 9909538 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 302040 | 31292 | 270748 | 332040 | 31292 | 300748 | 1618825 | 0 | 1618825 | 270805 | 136201 | 134604 | 270805 | 136201 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 3968 | 498 | 3470 | 3968 | 498 | 3470 | 49547690 | 9909538 | 39638152 | 6803604 | 2262716 | 4540888 | 34914953 | 8321716 | 26593237 | 49547690 | 9909538 | 39638152 | 6803604 | 2262716 | 4540888 | 34914953 | 8321716 | 26593237 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2015 | Q1 | Q1 - 2015 | 13544926 | 0 | 13544926 | 9042498 | 2021010 | 7021488 | 33219765 | 6446952 | 26772813 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 3142374 | 1331862 | 1810512 | 4133490 | 1968500 | 2164990 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 372035 | 45291 | 326744 | 634266 | 97737 | 536529 | 1618825 | 0 | 1618825 | 270805 | 136201 | 134604 | 270805 | 136201 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 5233 | 758 | 4475 | 478741 | 95459 | 383282 | 51188152 | 11550000 | 39638152 | 12832945 | 3535122 | 9297823 | 38737067 | 8744849 | 29992218 | 51188152 | 11550000 | 39638152 | 12832945 | 3535122 | 9297823 | 38737067 | 8744849 | 29992218 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570105 | INF | 2015 | Q2 | Q2 - 2015 | 44293019 | 8595936 | 35697083 | 20465989 | 4126649 | 16339340 | 44393019 | 8595936 | 35697083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3898859 | 1012205 | 2886654 | 2784813 | 782243 | 2002750 | 3898859 | 1012205 | 2886654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634266 | 97737 | 536529 | 439221 | 58728 | 380493 | 634266 | 97737 | 536529 | 242805 | 108201 | 134604 | 242805 | 108201 | 134604 | 242805 | 108201 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478741 | 95459 | 383282 | 9663 | 1235 | 8428 | 478741 | 95459 | 383282 | 49547690 | 9909538 | 39638152 | 23942491 | 5077056 | 18865615 | 49647690 | 9909538 | 39638152 | 49547690 | 9909538 | 39638152 | 23942491 | 5077056 | 18865615 | 49647690 | 9909538 | 39638152 | 0 | 0 | Treasury, New Jersey Department of
NT10BIX5570106 | INF | 2010 | Q4 | Q4 - 2010 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 0 | 0 | 0 | 895066 | 6000 | 889066 | 0 | 0 | 0 | 24000 | 2000 | 22000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 0 | 0 | 0 | 266356 | 36000 | 230356 | 0 | 0 | 0 | 61000 | 36000 | 25000 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 0 | 0 | 0 | 100000 | 43000 | 57000 | 9502006 | 2432000 | 7070006 | 0 | 0 | 0 | 100000 | 43000 | 57000 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2011 | Q1 | Q1 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 230000 | 0 | 230000 | 895066 | 6000 | 889066 | 0 | 0 | 0 | 30000 | 0 | 30000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 15000 | 0 | 15000 | 266356 | 36000 | 230356 | 15784 | 0 | 15784 | 75000 | 36000 | 39000 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 15784 | 0 | 15784 | 372500 | 58500 | 314000 | 9502006 | 2432000 | 7070006 | 15784 | 0 | 15784 | 372500 | 58500 | 314000 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2011 | Q2 | Q2 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 3000 | 0 | 3000 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2300000 | 100000 | 895066 | 6000 | 889066 | 7629 | 0 | 7629 | 20000 | 0 | 20000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 110000 | 100000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 150000 | 0 | 150000 | 266356 | 36000 | 230356 | 15784 | 0 | 15784 | 55784 | 0 | 55784 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 23413 | 0 | 23413 | 2738784 | 2400000 | 338784 | 9502006 | 2432000 | 7070006 | 23413 | 0 | 23413 | 2738784 | 2400000 | 338784 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2011 | Q3 | Q3 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 895066 | 6000 | 889066 | 38788 | 0 | 38788 | 62788 | 2000 | 60788 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 101002 | 36000 | 65002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 92390 | 0 | 92390 | 2592390 | 2443000 | 149390 | 9502006 | 2432000 | 7070006 | 92390 | 0 | 92390 | 2592390 | 2443000 | 149390 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2011 | Q4 | Q4 - 2011 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 4363 | 0 | 4363 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 895066 | 6000 | 889066 | 63592 | 0 | 63592 | 122844 | 0 | 122844 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 40002 | 0 | 40002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 121557 | 0 | 121557 | 2595809 | 2405000 | 190809 | 9502006 | 2432000 | 7070006 | 121557 | 0 | 121557 | 2595809 | 2405000 | 190809 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2012 | Q1 | Q1 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 4363 | 0 | 4363 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 1886591 | 60000 | 1826591 | 895066 | 6000 | 889066 | 124963 | 0 | 124963 | 118759 | 0 | 118759 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 75079 | 35077 | 40002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 182928 | 0 | 182928 | 2156167 | 130077 | 2026090 | 9502006 | 2432000 | 7070006 | 182928 | 0 | 182928 | 2156167 | 130077 | 2026090 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2012 | Q2 | Q2 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 13000 | 8637 | 4363 | 7612371 | 2300000 | 5312371 | 150048 | 0 | 150048 | 4570808 | 2300000 | 2270808 | 895066 | 6000 | 889066 | 161486 | 0 | 161486 | 192506 | 6000 | 186506 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 70000 | 60000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 65705 | 0 | 65705 | 65705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 395202 | 0 | 395202 | 4968394 | 2440637 | 2563757 | 9502006 | 2432000 | 7070006 | 395202 | 0 | 395202 | 4968394 | 2440637 | 2563757 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2012 | Q3 | Q3 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 18000 | 0 | 18000 | 7612371 | 2300000 | 5312371 | 2450048 | 2300000 | 874834 | 6870808 | 2300000 | 4570808 | 895066 | 6000 | 889066 | 130111 | 6000 | 124111 | 259126 | 6000 | 253126 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 2927653 | 2432000 | 1220439 | 7491065 | 2432000 | 5059065 | 9502006 | 2432000 | 7070006 | 2927653 | 2432000 | 1220439 | 7491065 | 2432000 | 5059065 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2012 | Q4 | Q4 - 2012 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 4303394 | 2300000 | 2003394 | 5100000 | 2300000 | 2800000 | 895066 | 6000 | 889066 | 260439 | 6000 | 254439 | 483004 | 6000 | 477004 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 88456 | 0 | 88456 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 15069 | 0 | 15069 | 15069 | 0 | 15069 | 9502006 | 2432000 | 7070006 | 4857439 | 2432000 | 2425439 | 6214997 | 2432000 | 3782997 | 9502006 | 2432000 | 7070006 | 4857439 | 2432000 | 2425439 | 6214997 | 2432000 | 3782997 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2013 | Q1 | Q1 - 2013 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 4623812 | 2300000 | 2323812 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 488799 | 6000 | 482799 | 732799 | 6000 | 726799 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 88456 | 0 | 88456 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 15069 | 0 | 15069 | 15069 | 0 | 15069 | 9502006 | 2432000 | 7070006 | 5406217 | 2432000 | 2974217 | 8977163 | 2432000 | 6545163 | 9502006 | 2432000 | 7070006 | 5406217 | 2432000 | 2974217 | 8977163 | 2432000 | 6545163 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2013 | Q2 | Q2 - 2013 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 5145801 | 2300000 | 2845801 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 510039 | 6000 | 504039 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 22939 | 0 | 22939 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 5957316 | 2432000 | 3525316 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 5957316 | 2432000 | 3525316 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2013 | Q3 | Q3 - 2013 | 198937 | 0 | 198937 | 189900 | 0 | 189900 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 6137831 | 2300000 | 3837831 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 668528 | 6000 | 662528 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 7746291 | 2432000 | 5314291 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 7746291 | 2432000 | 5314291 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2013 | Q4 | Q4 - 2013 | 198937 | 0 | 198937 | 198937 | 0 | 198937 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 6362280 | 2300000 | 4062280 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 773581 | 6000 | 767581 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 8084830 | 2432000 | 5652830 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 8084830 | 2432000 | 5652830 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570106 | INF | 2014 | Q1 | Q1 - 2014 | 283594 | 0 | 283594 | 276054 | 0 | 276054 | 276054 | 0 | 276054 | 7631252 | 2336000 | 5295252 | 7615798 | 2336000 | 5279798 | 7615798 | 2336000 | 5279798 | 844749 | 0 | 844749 | 804912 | 0 | 804912 | 804912 | 0 | 804912 | 192551 | 66000 | 126551 | 192551 | 66000 | 126551 | 192551 | 66000 | 126551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204600 | 0 | 204600 | 204600 | 0 | 204600 | 204600 | 0 | 204600 | 217347 | 0 | 217347 | 217347 | 0 | 217347 | 217347 | 0 | 217347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61663 | 30000 | 31663 | 61663 | 30000 | 31663 | 61663 | 30000 | 31663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 9439175 | 2432000 | 7007175 | 9439175 | 2432000 | 7007175 | 9502006 | 2432000 | 7070006 | 9439175 | 2432000 | 7007175 | 9439175 | 2432000 | 7007175 | 0 | 0 | Pyramid Lake Paiute Tribe
NT10BIX5570107 | INF | 2010 | Q4 | Q4 - 2010 | 1867707 | 911907 | 956700 | 0 | 0 | 0 | 342281 | 198790 | 143491 | 6819905 | 1923210 | 4895795 | 0 | 0 | 0 | 440978 | 123474 | 317504 | 113322 | 0 | 113322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687127 | 157169 | 529958 | 0 | 0 | 0 | 547458 | 157169 | 390289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 0 | 0 | 0 | 1330717 | 479433 | 851284 | 9543061 | 2992286 | 6550775 | 0 | 0 | 0 | 1330717 | 479433 | 851284 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2011 | Q1 | Q1 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 0 | 0 | 0 | 1651633 | 581295 | 1070338 | 71820 | 0 | 71820 | 4624 | 0 | 4624 | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 8540 | 0 | 8540 | 567651 | 177213 | 390438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 13164 | 0 | 13164 | 2228284 | 758508 | 1469776 | 9543061 | 2992286 | 6550775 | 13164 | 0 | 13164 | 2228284 | 758508 | 1469776 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2011 | Q2 | Q2 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 90 | 25 | 65 | 1328530 | 853499 | 475031 | 71820 | 0 | 71820 | 15959 | 0 | 15959 | 17959 | 0 | 17959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 23497 | 0 | 23497 | 549391 | 141922 | 407469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 39546 | 25 | 39521 | 1895880 | 995421 | 900459 | 9543061 | 2992286 | 6550775 | 39546 | 25 | 39521 | 1895880 | 995421 | 900459 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2011 | Q3 | Q3 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 46561 | 0 | 46561 | 1075096 | 371157 | 703939 | 71820 | 0 | 71820 | 26286 | 0 | 26286 | 28286 | 0 | 28286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 33991 | 0 | 33991 | 525894 | 157169 | 368725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 106838 | 0 | 106838 | 1629276 | 528326 | 1100950 | 9543061 | 2992286 | 6550775 | 106838 | 0 | 106838 | 1629276 | 528326 | 1100950 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2011 | Q4 | Q4 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 898815 | 374271 | 524544 | 2805993 | 915296 | 1890697 | 71820 | 0 | 71820 | 27295 | 0 | 27295 | 56442 | 0 | 56442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 33045 | 0 | 33045 | 34635 | 0 | 34635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 959155 | 374271 | 584884 | 2897070 | 915296 | 1981774 | 9543061 | 2992286 | 6550775 | 959155 | 374271 | 584884 | 2897070 | 915296 | 1981774 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2012 | Q1 | Q1 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 2651322 | 1080103 | 1571219 | 3858545 | 1466414 | 2392131 | 71820 | 0 | 71820 | 29011 | 0 | 29011 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 419685 | 0 | 419685 | 439685 | 6400 | 433285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 3100018 | 1080103 | 2019915 | 4386230 | 1472814 | 2913416 | 9543061 | 2992286 | 6550775 | 3100018 | 1080103 | 2019915 | 4386230 | 1472814 | 2913416 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2012 | Q2 | Q2 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 3505607 | 1585644 | 1919962 | 5958470 | 2200000 | 3758470 | 71820 | 0 | 71820 | 29444 | 0 | 29444 | 37000 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 439644 | 0 | 439644 | 459644 | 6000 | 453644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 3974695 | 1585644 | 2389050 | 6510114 | 2206000 | 4304114 | 9543061 | 2992286 | 6550775 | 3974695 | 1585644 | 2389050 | 6510114 | 2206000 | 4304114 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2012 | Q3 | Q3 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 5247703 | 1899121 | 3348582 | 7247703 | 2499121 | 4748582 | 71820 | 0 | 71820 | 31190 | 0 | 31190 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 451156 | 0 | 451156 | 471156 | 6000 | 465156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 5730049 | 1899121 | 3830928 | 7808859 | 2505121 | 5303738 | 9543061 | 2992286 | 6550775 | 5730049 | 1899121 | 3830928 | 7808859 | 2505121 | 5303738 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2012 | Q4 | Q4 - 2012 | 55000 | 0 | 55000 | 23292 | 0 | 23292 | 34730 | 0 | 34730 | 8687612 | 2835117 | 5852495 | 5532658 | 2044235 | 3488423 | 6486155 | 2330284 | 4155871 | 71820 | 0 | 71820 | 35233 | 0 | 35233 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 470431 | 2319 | 468112 | 488431 | 5400 | 483031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 6061614 | 2046554 | 4015060 | 7048316 | 2335684 | 4712632 | 9543061 | 2992286 | 6550775 | 6061614 | 2046554 | 4015060 | 7048316 | 2335684 | 4712632 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2013 | Q1 | Q1 - 2013 | 55000 | 0 | 55000 | 23292 | 0 | 23292 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 6917401 | 2085053 | 4832348 | 8562642 | 2740045 | 5822597 | 71820 | 0 | 71820 | 35957 | 0 | 35957 | 40957 | 0 | 40957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 490530 | 2319 | 488211 | 714056 | 149951 | 564105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 7467180 | 2087372 | 5379808 | 9372655 | 2889996 | 6482659 | 9543061 | 2992286 | 6550775 | 7467180 | 2087372 | 5379808 | 9372655 | 2889996 | 6482659 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2013 | Q2 | Q2 - 2013 | 26333 | 0 | 26333 | 23292 | 0 | 23292 | 26364 | 0 | 26364 | 8716279 | 2835117 | 5881162 | 7808776 | 2405845 | 5402931 | 8952683 | 2988359 | 5964324 | 71820 | 0 | 71820 | 39522 | 1608 | 37914 | 52198 | 1608 | 50590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 502259 | 2319 | 499940 | 511814 | 2319 | 509495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 8373849 | 2409772 | 5964077 | 9543059 | 2992286 | 6550773 | 9543061 | 2992286 | 6550775 | 8373849 | 2409772 | 5964077 | 9543059 | 2992286 | 6550773 | 0 | 0 | Texas A&M University
NT10BIX5570107 | INF | 2013 | Q3 | Q3 - 2013 | 26364 | 0 | 26364 | 26364 | 0 | 26364 | 26364 | 0 | 26364 | 8949402 | 2988359 | 5961043 | 8949402 | 2988359 | 5961043 | 8949402 | 2988359 | 5961043 | 55481 | 1608 | 53873 | 55481 | 1608 | 53873 | 55481 | 1608 | 53873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511814 | 2319 | 509495 | 511814 | 2319 | 509495 | 511814 | 2319 | 509495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 0 | 0 | Texas A&M University
NT10BIX5570108 | INF | 2010 | Q4 | Q4 - 2010 | 11275418 | 538950 | 10736468 | 0 | 0 | 0 | 905197 | 0 | 905197 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 6359 | 6359 | 0 | 132151 | 24912 | 107239 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 0 | 0 | 0 | 1540211 | 0 | 1540211 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 11232 | 0 | 11232 | 1050000 | 0 | 1050000 | 0 | 0 | 0 | 34570 | 0 | 34570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 0 | 0 | 0 | 49000 | 0 | 49000 | 96382028 | 34486746 | 61895282 | 6359 | 6359 | 0 | 2672361 | 24912 | 2647449 | 96382028 | 34486746 | 61895282 | 6359 | 6359 | 0 | 2672361 | 24912 | 2647449 | 0 | 0 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2011 | Q1 | Q1 - 2011 | 11275418 | 538950 | 10736468 | 696413 | 0 | 696413 | 2797247 | 0 | 2797247 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 187615 | 46199 | 141416 | 370993 | 0 | 370993 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 1133512 | 0 | 1133512 | 2240678 | 0 | 2240678 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 29952 | 0 | 29952 | 1050000 | 0 | 1050000 | 41160 | 0 | 41160 | 391160 | 0 | 391160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2145272 | 2113326 | 31946 | 2250512 | 2218566 | 31946 | 96382028 | 34486746 | 61895282 | 4203972 | 2159525 | 2044447 | 8080542 | 2218566 | 5861976 | 96382028 | 34486746 | 61895282 | 4203972 | 2159525 | 2044447 | 8080542 | 2218566 | 5861976 | 0 | 0 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2011 | Q2 | Q2 - 2011 | 11275418 | 538950 | 10736468 | 714172 | 0 | 714172 | 3691381 | 0 | 3691381 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 379533 | 92189 | 287344 | 634894 | 110967 | 523927 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 1603702 | 0 | 1603702 | 2551578 | 0 | 2551578 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 62400 | 0 | 62400 | 1050000 | 0 | 1050000 | 41160 | 0 | 41160 | 217516 | 0 | 217516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2250512 | 2218566 | 31946 | 2250512 | 2218566 | 31946 | 96382028 | 34486746 | 61895282 | 4989079 | 2310755 | 2678324 | 9408281 | 2329533 | 7078748 | 96382028 | 34486746 | 61895282 | 4989079 | 2310755 | 2678324 | 9408281 | 2329533 | 7078748 | 0 | 0 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2011 | Q3 | Q3 - 2011 | 11275418 | 538950 | 10736468 | 3363817 | 0 | 3363817 | 5391115 | 0 | 5391115 | 63338112 | 30000000 | 33338112 | 22655 | 0 | 22655 | 432071 | 53674 | 378397 | 2309142 | 222637 | 2086505 | 544305 | 131652 | 412653 | 763183 | 176659 | 586524 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5524880 | 0 | 5524880 | 2327211 | 0 | 2327211 | 3365211 | 0 | 3365211 | 600000 | 0 | 600000 | 0 | 0 | 0 | 51869 | 0 | 51869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 144381 | 0 | 144381 | 256173 | 0 | 256173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10422476 | 2213159 | 8209317 | 2286663 | 2227638 | 59025 | 2321113 | 2227638 | 93475 | 96382028 | 34486746 | 61895282 | 8689032 | 2359290 | 6329742 | 12580735 | 2457971 | 10122764 | 96382028 | 34486746 | 61895282 | 8689032 | 2359290 | 6329742 | 12580735 | 2457971 | 10122764 | 0 | 0 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2011 | Q4 | Q4 - 2011 | 11911943 | 538950 | 11372993 | 5267616 | 0 | 5267616 | 8098096 | 7535 | 8090561 | 64182920 | 30249603 | 33933317 | 22655 | 0 | 22655 | 2250899 | 2250899 | 0 | 2451362 | 222637 | 2228725 | 692477 | 179372 | 513105 | 902890 | 189872 | 713018 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5173002 | 0 | 5173002 | 2894189 | 0 | 2894189 | 4041636 | 0 | 4041636 | 600000 | 0 | 600000 | 0 | 0 | 0 | 51864 | 0 | 51864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 276588 | 0 | 276588 | 308725 | 0 | 308725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9150801 | 1963556 | 7187245 | 2287906 | 2227638 | 60268 | 2289964 | 2227638 | 62326 | 96382028 | 34486746 | 61895282 | 11441431 | 2407010 | 9034421 | 17944074 | 4675944 | 13268130 | 96382028 | 34486746 | 61895282 | 11441431 | 2407010 | 9034421 | 17944074 | 4675944 | 13268130 | 538950 | 207510 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2012 | Q1 | Q1 - 2012 | 11275418 | 538950 | 10736468 | 6936014 | 0 | 6936014 | 8041408 | 0 | 8041408 | 63338112 | 30000000 | 33338112 | 3793811 | 3739320 | 54491 | 14018447 | 12463956 | 1554491 | 2428175 | 222637 | 2205538 | 1144170 | 216428 | 927742 | 1230761 | 222637 | 1008124 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 4599436 | 0 | 4599436 | 4962251 | 0 | 4962251 | 600000 | 0 | 600000 | 31527 | 0 | 31527 | 51864 | 0 | 51864 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 308362 | 0 | 308362 | 308362 | 0 | 308362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2289964 | 2227638 | 62326 | 2389964 | 2227638 | 162326 | 96382028 | 34486746 | 61895282 | 19103284 | 6183386 | 12919898 | 31003057 | 14914231 | 16088826 | 96382028 | 34486746 | 61895282 | 19103284 | 6183386 | 12919898 | 31003057 | 14914231 | 16088826 | 538950 | 237368 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2012 | Q2 | Q2 - 2012 | 11275418 | 538950 | 10736468 | 8119998 | 0 | 8119998 | 8480718 | 0 | 8480718 | 63338112 | 30000000 | 33338112 | 13450046 | 11130510 | 2319536 | 25438137 | 20955630 | 4482507 | 2428175 | 222637 | 2205538 | 1258150 | 222637 | 1035513 | 1618880 | 222637 | 1396243 | 1862000 | 1512000 | 350000 | 269400 | 269400 | 0 | 404400 | 404400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 4942378 | 0 | 4942378 | 5467378 | 0 | 5467378 | 600000 | 0 | 600000 | 31527 | 0 | 31527 | 31527 | 0 | 31527 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 310717 | 0 | 310717 | 350459 | 0 | 350459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2289964 | 2227638 | 62326 | 3149687 | 2231238 | 918449 | 96382028 | 34486746 | 61895282 | 30672180 | 13850185 | 16821995 | 44941186 | 23813905 | 21127281 | 96382028 | 34486746 | 61895282 | 30672180 | 13850185 | 16821995 | 44941186 | 23813905 | 21127281 | 538950 | 459943 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2012 | Q3 | Q3 - 2012 | 11275418 | 538950 | 10736468 | 8216162 | 0 | 8216162 | 8572068 | 0 | 8572068 | 63338112 | 30000000 | 33338112 | 20627208 | 16493516 | 4133692 | 40599844 | 25874737 | 14725107 | 2428175 | 222637 | 2205538 | 1708398 | 378296 | 1330102 | 2321945 | 423296 | 1898649 | 1862000 | 1512000 | 350000 | 423500 | 423500 | 0 | 555650 | 555650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5327409 | 0 | 5327409 | 5840232 | 0 | 5840232 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 343795 | 0 | 343795 | 480760 | 0 | 480760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3051229 | 2227638 | 823591 | 3299156 | 2227638 | 1071518 | 96382028 | 34486746 | 61895282 | 39739397 | 19522950 | 20216447 | 61711351 | 29081321 | 32630030 | 96382028 | 34486746 | 61895282 | 39739397 | 19522950 | 20216447 | 61711351 | 29081321 | 32630030 | 538950 | 499674 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2012 | Q4 | Q4 - 2012 | 11275418 | 538950 | 10736468 | 9135057 | 69044 | 9066013 | 9567863 | 180294 | 9387569 | 63338112 | 30000000 | 33338112 | 35762277 | 28434417 | 7327860 | 46572661 | 29032369 | 17540293 | 2428175 | 222637 | 2205538 | 2123685 | 434607 | 1689078 | 2220670 | 474607 | 1746063 | 1862000 | 1512000 | 350000 | 555650 | 555650 | 0 | 672850 | 672850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5685717 | 0 | 5685717 | 5954315 | 0 | 5954315 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 458098 | 0 | 458098 | 489807 | 0 | 489807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3245539 | 2227638 | 1017901 | 4186414 | 2227638 | 1958776 | 96382028 | 34486746 | 61895282 | 57007719 | 31721356 | 25286363 | 69706276 | 32587758 | 37118519 | 96382028 | 34486746 | 61895282 | 57007719 | 31721356 | 25286363 | 69706276 | 32587758 | 37118519 | 538950 | 615807 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2013 | Q1 | Q1 - 2013 | 11275418 | 538950 | 10736468 | 9451186 | 179372 | 9271814 | 10991410 | 522150 | 10469260 | 63338112 | 30000000 | 33338112 | 44115588 | 29032368 | 15083220 | 52449030 | 29032369 | 23416661 | 2428175 | 222637 | 2205538 | 2261752 | 498915 | 1762837 | 2391273 | 561507 | 1829766 | 1862000 | 1512000 | 350000 | 642650 | 642650 | 0 | 642650 | 642650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5833613 | 0 | 5833613 | 6018481 | 0 | 6018481 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 531803 | 0 | 531803 | 571988 | 0 | 571988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3245539 | 2227638 | 1017901 | 4334164 | 2227638 | 2106526 | 96382028 | 34486746 | 61895282 | 66123827 | 32580943 | 33542884 | 77440692 | 32986314 | 44454378 | 96382028 | 34486746 | 61895282 | 66123827 | 32580943 | 33542884 | 77440692 | 32986314 | 44454378 | 538950 | 630807 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2013 | Q2 | Q2 - 2013 | 11275418 | 538950 | 10736468 | 10778330 | 528950 | 10249380 | 11245402 | 550739 | 10694663 | 63338112 | 30000000 | 33338112 | 51311009 | 29032368 | 22278641 | 65224955 | 29032369 | 36192586 | 2428175 | 222637 | 2205538 | 2928141 | 931048 | 1997093 | 3156067 | 1094048 | 2062019 | 1862000 | 1512000 | 350000 | 628800 | 628800 | 0 | 628800 | 628800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 6759786 | 0 | 6759786 | 7035734 | 0 | 7035734 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 667465 | 0 | 667465 | 667465 | 0 | 667465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 4184487 | 2227638 | 1956849 | 4226724 | 2227638 | 1999086 | 96382028 | 34486746 | 61895282 | 77299714 | 33348804 | 43950910 | 92226843 | 33533594 | 58693249 | 96382028 | 34486746 | 61895282 | 77299714 | 33348804 | 43950910 | 92226843 | 33533594 | 58693249 | 538950 | 630807 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2013 | Q3 | Q3 - 2013 | 11275418 | 538950 | 10736468 | 11675040 | 528950 | 11146090 | 15527526 | 541209 | 14986317 | 63338112 | 30000000 | 33338112 | 56200931 | 29032369 | 27168562 | 63965629 | 30018120 | 33947509 | 2428175 | 222637 | 2205538 | 3201402 | 1055896 | 2145506 | 3458138 | 1269085 | 2189053 | 1862000 | 1512000 | 350000 | 245912 | 245912 | 0 | 371463 | 371463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 6932879 | 0 | 6932879 | 6980358 | 0 | 6980358 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 684626 | 0 | 684626 | 686692 | 0 | 686692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 4227564 | 2227638 | 1999926 | 5297529 | 2258870 | 3038659 | 96382028 | 34486746 | 61895282 | 83210050 | 33090765 | 50119285 | 96329031 | 34458747 | 61870284 | 96382028 | 34486746 | 61895282 | 83210050 | 33090765 | 50119285 | 96329031 | 34458747 | 61870284 | 538950 | 632292 | Central Management Services, Illinois Department of
NT10BIX5570108 | INF | 2013 | Q4 | Q4 - 2013 | 15514534 | 541209 | 14973325 | 15515296 | 541289 | 14974007 | 15515296 | 541289 | 14974007 | 63968722 | 30018120 | 33950602 | 62754769 | 29580054 | 33174715 | 62754769 | 29580054 | 33174715 | 3467696 | 1269084 | 2198612 | 3512189 | 1278979 | 2233210 | 3512189 | 1278979 | 2233210 | 399463 | 399463 | 0 | 399463 | 399463 | 0 | 399463 | 399463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005603 | 0 | 7005603 | 6976457 | 0 | 6976457 | 6976457 | 0 | 6976457 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686691 | 0 | 686691 | 686691 | 0 | 686691 | 686691 | 0 | 686691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5297623 | 2258870 | 3038753 | 5287961 | 2249798 | 3038163 | 5287961 | 2249798 | 3038163 | 96382028 | 34486746 | 61895282 | 95174522 | 34049583 | 61124939 | 95174522 | 34049583 | 61124939 | 96382028 | 34486746 | 61895282 | 95174522 | 34049583 | 61124939 | 95174522 | 34049583 | 61124939 | 0 | 0 | Central Management Services, Illinois Department of
NT10BIX5570109 | INF | 2010 | Q4 | Q4 - 2010 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 7494500 | 1498900 | 5995600 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2011 | Q1 | Q1 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494498 | 1498900 | 5995600 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 7494498 | 1498900 | 5995600 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2011 | Q2 | Q2 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 2262002 | 452400 | 1809602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 64061 | 12812 | 51249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 13320 | 2664 | 10656 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 19305 | 3861 | 15444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494498 | 1498900 | 5995600 | 13320 | 2664 | 10656 | 2795368 | 559073 | 2236295 | 7494498 | 1498900 | 5995600 | 13320 | 2664 | 10656 | 2795368 | 559073 | 2236295 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2011 | Q3 | Q3 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 1184393 | 236879 | 947514 | 4496700 | 3597360 | 899340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 237936 | 47587 | 190349 | 300000 | 240000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 1422329 | 284466 | 1137863 | 4796700 | 3837360 | 959340 | 7494500 | 1498900 | 5995600 | 1422329 | 284466 | 1137863 | 4796700 | 3837360 | 959340 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2011 | Q4 | Q4 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 2659872 | 531974 | 2127898 | 4126000 | 825200 | 3300800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 269975 | 53995 | 215980 | 370000 | 74000 | 296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 2929847 | 585969 | 2343878 | 4496000 | 899200 | 3596800 | 7494500 | 1498900 | 5995600 | 2929847 | 585969 | 2343878 | 4496000 | 899200 | 3596800 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2012 | Q1 | Q1 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 4109181 | 821837 | 3287344 | 5020930 | 1004186 | 4016744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 424009 | 84801 | 339208 | 525000 | 105000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 4533190 | 906638 | 3626552 | 5545930 | 1109186 | 4436744 | 7494500 | 1498900 | 5995600 | 4533190 | 906638 | 3626552 | 5545930 | 1109186 | 4436744 | 0 | 0 | Carver, County of
NT10BIX5570109 | INF | 2012 | Q2 | Q2 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 5474045 | 1094809 | 4379236 | 4875647 | 975129 | 3900518 | 5300000 | 1060000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 454039 | 90808 | 363231 | 550000 | 110000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 5329686 | 1065937 | 4263749 | 6500097 | 1300019 | 5200078 | 7494500 | 1498900 | 5995600 | 5329686 | 1065937 | 4263749 | 6500097 | 1300019 | 5200078 | 0 | 75000 | Carver, County of
NT10BIX5570109 | INF | 2012 | Q3 | Q3 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 300000 | 60000 | 240000 | 5474045 | 1094809 | 4379236 | 5647615 | 1129523 | 4518092 | 5647615 | 1129523 | 4518092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 488539 | 97708 | 390831 | 600000 | 120000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6136154 | 1227231 | 4908923 | 6797712 | 1359542 | 5438170 | 7494500 | 1498900 | 5995600 | 6136154 | 1227231 | 4908923 | 6797712 | 1359542 | 5438170 | 0 | 75000 | Carver, County of
NT10BIX5570109 | INF | 2012 | Q4 | Q4 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 5474045 | 1094809 | 4379236 | 5733798 | 1146760 | 4587038 | 6080000 | 1216000 | 4864000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 522097 | 104419 | 417678 | 625000 | 125000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6255895 | 1251179 | 5004716 | 7204722 | 1440944 | 5763778 | 7494500 | 1498900 | 5995600 | 6255895 | 1251179 | 5004716 | 7204722 | 1440944 | 5763778 | 0 | 75000 | Carver, County of
NT10BIX5570109 | INF | 2013 | Q1 | Q1 - 2013 | 803598 | 160720 | 642878 | 51368 | 10274 | 41094 | 803598 | 160720 | 642878 | 5474045 | 1094809 | 4379236 | 5733798 | 1146760 | 4587038 | 5869483 | 1173896 | 4695586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 827321 | 165464 | 661857 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6707736 | 1341548 | 5366188 | 7889938 | 1577987 | 6311950 | 7494500 | 1498900 | 5995600 | 6707736 | 1341548 | 5366188 | 7889938 | 1577987 | 6311950 | 0 | 395438 | Carver, County of
NT10BIX5570109 | INF | 2013 | Q2 | Q2 - 2013 | 803598 | 160720 | 642878 | 191394 | 38279 | 153115 | 803598 | 160720 | 642878 | 5474045 | 1094809 | 4379236 | 5770109 | 1154022 | 4616087 | 5770109 | 1154022 | 4616087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 835360 | 167072 | 668288 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6892112 | 1378423 | 5513689 | 7790564 | 1558113 | 6232451 | 7494500 | 1498900 | 5995600 | 6892112 | 1378423 | 5513689 | 7790564 | 1558113 | 6232451 | 0 | 395438 | Carver, County of
NT10BIX5570109 | INF | 2013 | Q3 | Q3 - 2013 | 803598 | 160720 | 642878 | 653085 | 130617 | 522468 | 653085 | 130617 | 522468 | 5474045 | 1094809 | 4379236 | 6147198 | 1524670 | 4622528 | 6147198 | 1524670 | 4622528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 95249 | 19050 | 76199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 994406 | 220001 | 774405 | 994406 | 220001 | 774405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 7889938 | 1894338 | 5995600 | 7889938 | 1894338 | 5995600 | 7494500 | 1498900 | 5995600 | 7889938 | 1894338 | 5995600 | 7889938 | 1894338 | 5995600 | 0 | 395438 | Carver, County of
NT10BIX5570111 | INF | 2010 | Q4 | Q4 - 2010 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 500000 | 0 | 500000 | 52877030 | 16403258 | 36473772 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 74820 | 7431420 | 0 | 0 | 0 | 400000 | 0 | 400000 | 21573 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23444746 | 54554155 | 0 | 0 | 0 | 900000 | 0 | 900000 | 77998901 | 23444746 | 54554155 | 0 | 0 | 0 | 900000 | 0 | 900000 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2011 | Q1 | Q1 - 2011 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 0 | 0 | 0 | 52877030 | 16526459 | 36350571 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 77998901 | 23546554 | 54452347 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2011 | Q2 | Q2 - 2011 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 11500000 | 11500000 | 0 | 52877030 | 16526459 | 36350571 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 699993 | 153979 | 546014 | 1000000 | 200000 | 800000 | 21573 | 0 | 21573 | 25225 | 0 | 25225 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 725218 | 153979 | 571239 | 15575000 | 14700000 | 875000 | 77998901 | 23546554 | 54452347 | 725218 | 153979 | 571239 | 15575000 | 14700000 | 875000 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2011 | Q3 | Q3 - 2011 | 15239344 | 4672381 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 52877030 | 16526459 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 983851 | 153979 | 829873 | 1500000 | 154000 | 1346000 | 21573 | 0 | 21573 | 102329 | 0 | 102329 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 15465537 | 14533336 | 932202 | 16079357 | 14533357 | 1546000 | 77998901 | 23546554 | 54452347 | 15465537 | 14533336 | 932202 | 16079357 | 14533357 | 1546000 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2011 | Q4 | Q4 - 2011 | 15239344 | 4672381 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 52877030 | 16526459 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 1434030 | 153979 | 1280051 | 2750000 | 153979 | 2596021 | 21573 | 0 | 21573 | 357447 | 0 | 357447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 16170834 | 14533336 | 1637498 | 17129357 | 14533336 | 2596021 | 77998901 | 23546554 | 54452347 | 16170834 | 14533336 | 1637498 | 17129357 | 14533336 | 2596021 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2012 | Q1 | Q1 - 2012 | 15689615 | 5122652 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 48655161 | 12304590 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 2385083 | 153979 | 2231104 | 3100000 | 153979 | 2946021 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75307089 | 20854742 | 54452347 | 16764440 | 14533336 | 2231104 | 17479357 | 14533336 | 2946021 | 75307089 | 20854742 | 54452347 | 16764440 | 14533336 | 2231104 | 17479357 | 14533336 | 2946021 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2012 | Q2 | Q2 - 2012 | 15689615 | 5122652 | 10566963 | 4664490 | 3968916 | 695574 | 5000000 | 3968916 | 1031084 | 48655161 | 12304590 | 36350571 | 8193530 | 7506448 | 687082 | 11993530 | 7900000 | 4093530 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 3115021 | 153979 | 2961042 | 4156171 | 153979 | 4002192 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75307089 | 20854742 | 54452347 | 19026409 | 14682711 | 4343698 | 24203069 | 15076263 | 9126806 | 75307089 | 20854742 | 54452347 | 19026409 | 14682711 | 4343698 | 24203069 | 15076263 | 9126806 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2012 | Q3 | Q3 - 2012 | 15689615 | 5122652 | 10566963 | 5596246 | 3968916 | 1627330 | 6596246 | 3968916 | 2627330 | 48655161 | 12304590 | 36350571 | 13604772 | 7728726 | 5876046 | 23364772 | 9000000 | 14364772 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 3988487 | 0 | 3988487 | 5000000 | 0 | 5000000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 536 | 0 | 536 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 26243409 | 14751010 | 11492399 | 38015386 | 16022284 | 21993102 | 75307089 | 20854742 | 54452347 | 26243409 | 14751010 | 11492399 | 38015386 | 16022284 | 21993102 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2012 | Q4 | Q4 - 2012 | 15689615 | 5122652 | 10566963 | 6186044 | 3968916 | 2217128 | 10000000 | 4000000 | 6000000 | 48655161 | 12304590 | 36350571 | 26648395 | 8012214 | 18636181 | 34000000 | 9500000 | 24500000 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3056139 | 3053368 | 2771 | 3056139 | 3053368 | 2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 5042327 | 0 | 5042327 | 6000000 | 0 | 6000000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 536 | 0 | 536 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 40933441 | 15034498 | 25898943 | 53057139 | 16553368 | 36503771 | 75307089 | 20854742 | 54452347 | 40933441 | 15034498 | 25898943 | 53057139 | 16553368 | 36503771 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2013 | Q1 | Q1 - 2013 | 15689615 | 5122652 | 10566963 | 6927305 | 3968916 | 2958389 | 8050000 | 3968916 | 4081084 | 48655161 | 12304590 | 36350571 | 27930683 | 8066313 | 19864370 | 34000000 | 9000000 | 25000000 | 199992 | 199992 | 0 | 740 | 0 | 740 | 1000 | 0 | 1000 | 3180508 | 3098508 | 82000 | 3056139 | 3053368 | 2771 | 3056139 | 3053368 | 2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 6444908 | 0 | 6444908 | 7250000 | 0 | 7250000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 835 | 0 | 835 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 44360610 | 15088597 | 29272013 | 52358139 | 16022284 | 36335855 | 75307089 | 20854742 | 54452347 | 44360610 | 15088597 | 29272013 | 52358139 | 16022284 | 36335855 | 0 | 0 | Northwest Open Access Network
NT10BIX5570111 | INF | 2013 | Q2 | Q2 - 2013 | 15689615 | 5122652 | 10566963 | 7487030 | 3968916 | 3518114 | 8050000 | 3968916 | 4081084 | 48655161 | 12304590 | 36350571 | 29298798 | 8179513 | 21119285 | 34000000 | 9000000 | 25000000 | 199992 | 199992 | 0 | 740 | 0 | 740 | 740 | 0 | 740 | 3180508 | 3098508 | 82000 | 3360873 | 3053368 | 307505 | 3360873 | 3053368 | 307505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 7267741 | 0 | 7267741 | 7900000 | 0 | 7900000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 32074 | 0 | 32074 | 32074 | 0 | 32074 | 75307089 | 20854742 | 54452347 | 47447256 | 15201797 | 32245459 | 53343687 | 16022284 | 37321403 | 75307089 | 20854742 | 54452347 | 47447256 | 15201797 | 32245459 | 53343687 | 16022284 | 37321403 | 0 | 4343 | Northwest Open Access Network
NT10BIX5570111 | INF | 2013 | Q3 | Q3 - 2013 | 15689615 | 5122652 | 10566963 | 10042810 | 3968916 | 6073894 | 10042810 | 3968916 | 6073894 | 48655161 | 12304590 | 36350571 | 39336582 | 10431181 | 28905401 | 39336582 | 10431181 | 28905401 | 199992 | 199992 | 0 | 740 | 0 | 740 | 740 | 0 | 740 | 3180508 | 3098508 | 82000 | 3366523 | 3053368 | 313155 | 3366523 | 3053368 | 313155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 6496891 | 0 | 6496891 | 6496891 | 0 | 6496891 | 21573 | 0 | 21573 | 3396309 | 0 | 3396309 | 3396309 | 0 | 3396309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 163405 | 0 | 163405 | 163405 | 0 | 163405 | 75307089 | 20854742 | 54452347 | 62803260 | 17453465 | 45349795 | 62803260 | 17453465 | 45349795 | 75307089 | 20854742 | 54452347 | 62803260 | 17453465 | 45349795 | 62803260 | 17453465 | 45349795 | 0 | 0 | Northwest Open Access Network
NT10BIX5570112 | INF | 2010 | Q4 | Q4 - 2010 | 3588505 | 1076552 | 2511953 | 1121773 | 1121773 | 0 | 1121773 | 1121773 | 0 | 9349257 | 2804777 | 6544480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 0 | 0 | 0 | 15000 | 4500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753523 | 526057 | 1227466 | 199413 | 184745 | 14668 | 509182 | 277676 | 231506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 59737 | 17921 | 41816 | 139866 | 41960 | 97906 | 16496952 | 4949086 | 11547866 | 1380923 | 1324439 | 56484 | 1785821 | 1445909 | 339912 | 16496952 | 4949086 | 11547866 | 1380923 | 1324439 | 56484 | 1785821 | 1445909 | 339912 | 0 | 0 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2011 | Q1 | Q1 - 2011 | 3588505 | 1076552 | 2511953 | 1121773 | 1121773 | 0 | 2321773 | 1121773 | 1200000 | 9349257 | 2804777 | 6544480 | 0 | 0 | 0 | 1150000 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753523 | 526057 | 1227466 | 379433 | 184835 | 194598 | 554433 | 184835 | 369598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 154732 | 17921 | 136811 | 254732 | 17921 | 236811 | 16496952 | 4949086 | 11547866 | 1655938 | 1324529 | 331409 | 4295938 | 1324529 | 2971409 | 16496952 | 4949086 | 11547866 | 1655938 | 1324529 | 331409 | 4295938 | 1324529 | 2971409 | 0 | 0 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2011 | Q2 | Q2 - 2011 | 3588505 | 1076552 | 2511953 | 2051720 | 1121773 | 929947 | 2151720 | 1121773 | 1029947 | 9349257 | 2804777 | 6544480 | 4587 | 0 | 4587 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 8031 | 0 | 8031 | 23000 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753253 | 526057 | 1227466 | 517635 | 184745 | 332890 | 657635 | 184745 | 472890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 270910 | 17921 | 252989 | 385910 | 17921 | 367989 | 16496682 | 4949086 | 11547866 | 2852883 | 1324439 | 1528444 | 5268265 | 1324439 | 3943826 | 16496682 | 4949086 | 11547866 | 2852883 | 1324439 | 1528444 | 5268265 | 1324439 | 3943826 | 0 | 35239 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2011 | Q3 | Q3 - 2011 | 3706362 | 1111909 | 2594453 | 2353241 | 1136423 | 1216818 | 2753231 | 1316423 | 1436808 | 9349257 | 2804777 | 6544480 | 1734997 | 71004 | 1663993 | 4284997 | 871004 | 3413993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 8031 | 0 | 8031 | 32031 | 7200 | 24831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 603645 | 188110 | 415535 | 848645 | 296610 | 552035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 585537 | 19966 | 565571 | 770537 | 110466 | 660071 | 16496952 | 4949086 | 11547866 | 5285451 | 1415503 | 3869948 | 8739441 | 2616703 | 6122738 | 16496952 | 4949086 | 11547866 | 5285451 | 1415503 | 3869948 | 8739441 | 2616703 | 6122738 | 0 | 195771 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2011 | Q4 | Q4 - 2011 | 3706362 | 1111909 | 2594453 | 2578721 | 1211484 | 1367237 | 2828721 | 1286484 | 1542237 | 9349257 | 2804777 | 6544480 | 2587316 | 407151 | 2180165 | 3837316 | 782151 | 3055165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 26623 | 5578 | 21045 | 51623 | 13078 | 38545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 732125 | 242340 | 489785 | 907125 | 294840 | 612285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 10000 | 3000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 720912 | 91746 | 629166 | 870912 | 136746 | 734166 | 16496952 | 4949086 | 11547866 | 6645697 | 1958299 | 4687398 | 8505697 | 2516299 | 5989398 | 16496952 | 4949086 | 11547866 | 6645697 | 1958299 | 4687398 | 8505697 | 2516299 | 5989398 | 0 | 0 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2012 | Q1 | Q1 - 2012 | 3706362 | 1111909 | 2594453 | 2750048 | 1266578 | 1483470 | 2900047 | 1311578 | 1588469 | 9349257 | 2804777 | 6544480 | 3421283 | 689818 | 2731465 | 4421283 | 989818 | 3431465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 46722 | 12010 | 34712 | 86722 | 24010 | 62712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1052333 | 338945 | 713388 | 1227333 | 391445 | 835888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 3027 | 908 | 2119 | 18027 | 5408 | 12619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 914906 | 152652 | 762254 | 1094906 | 206652 | 888254 | 16496952 | 4949086 | 11547866 | 8188319 | 2460911 | 5727408 | 9748318 | 2928911 | 6819407 | 16496952 | 4949086 | 11547866 | 8188319 | 2460911 | 5727408 | 9748318 | 2928911 | 6819407 | 0 | 0 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2012 | Q2 | Q2 - 2012 | 3706362 | 1111909 | 2594453 | 2859307 | 1299356 | 1559951 | 3154307 | 1387856 | 1766451 | 9349257 | 2804777 | 6544480 | 5609699 | 1346343 | 4263356 | 8062670 | 2082234 | 5980436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 77383 | 21208 | 56175 | 169092 | 48717 | 120375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1179046 | 376959 | 802087 | 1278046 | 406659 | 871387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 3027 | 908 | 2119 | 45027 | 13508 | 31519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1149909 | 223153 | 926756 | 1352833 | 284030 | 1068803 | 16496952 | 4949086 | 11547866 | 10878371 | 3267927 | 7610444 | 14061975 | 4223004 | 9838971 | 16496952 | 4949086 | 11547866 | 10878371 | 3267927 | 7610444 | 14061975 | 4223004 | 9838971 | 0 | 0 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2012 | Q3 | Q3 - 2012 | 3706362 | 1111909 | 2594453 | 3135065 | 1382083 | 1752982 | 3185065 | 1397083 | 1787982 | 9349257 | 2804777 | 6544480 | 7654781 | 1959868 | 5694913 | 8154781 | 2109868 | 6044913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 119079 | 33717 | 85362 | 129079 | 36717 | 92362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1220155 | 389291 | 830864 | 1330155 | 422291 | 907864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 55969 | 16791 | 39178 | 120969 | 36291 | 84678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1372904 | 290051 | 1082853 | 1552903 | 344051 | 1208852 | 16496952 | 4949086 | 11547866 | 13557953 | 4071801 | 9486152 | 14472952 | 4346301 | 10126651 | 16496952 | 4949086 | 11547866 | 13557953 | 4071801 | 9486152 | 14472952 | 4346301 | 10126651 | 0 | 626464 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2012 | Q4 | Q4 - 2012 | 3706362 | 1111909 | 2594453 | 3169637 | 1392455 | 1777182 | 3269637 | 1422455 | 1847182 | 9349257 | 2804777 | 6544480 | 7835871 | 2014194 | 5821676 | 8635871 | 2254195 | 6381676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 122216 | 34658 | 87558 | 132216 | 37658 | 94558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1282062 | 407863 | 874199 | 1292062 | 410863 | 881199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 115722 | 34717 | 81005 | 125722 | 37717 | 88005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1644933 | 371660 | 1273273 | 1804933 | 419660 | 1385273 | 16496952 | 4949086 | 11547866 | 14170441 | 4255547 | 9914893 | 15260441 | 4582548 | 10677893 | 16496952 | 4949086 | 11547866 | 14170441 | 4255547 | 9914893 | 15260441 | 4582548 | 10677893 | 0 | 900475 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2013 | Q1 | Q1 - 2013 | 3706362 | 1111909 | 2594453 | 3219440 | 1407396 | 1812044 | 3247658 | 1415862 | 1831796 | 9349257 | 2804777 | 6544480 | 8893387 | 2331449 | 6561938 | 9283182 | 2443972 | 6839210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1327104 | 421376 | 905727 | 1428503 | 451796 | 976707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 129641 | 38892 | 90749 | 200641 | 60192 | 140449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1884812 | 443624 | 1441188 | 1884812 | 443624 | 1441188 | 16496952 | 4949086 | 11547866 | 15576600 | 4677395 | 10899204 | 16167012 | 4850104 | 11316908 | 16496952 | 4949086 | 11547866 | 15576600 | 4677395 | 10899204 | 16167012 | 4850104 | 11316908 | 0 | 1069632 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2013 | Q2 | Q2 - 2013 | 3247659 | 974298 | 2273361 | 3229553 | 1410430 | 1819123 | 3229553 | 1410430 | 1819123 | 9613119 | 2883936 | 6729183 | 9216523 | 2428390 | 6788133 | 9631235 | 2552804 | 7078431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122215 | 36664 | 85551 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428504 | 428551 | 999953 | 1377339 | 436446 | 940893 | 1428503 | 449603 | 978900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200642 | 60193 | 140449 | 133581 | 40074 | 93507 | 200633 | 57967 | 142666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884813 | 565444 | 1319369 | 1884812 | 443624 | 1441188 | 1884812 | 443624 | 1441188 | 16496952 | 4949086 | 11547866 | 15964024 | 4793622 | 11170402 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 15964024 | 4793622 | 11170402 | 16496952 | 4949086 | 11547866 | 0 | 999532 | Nebraskalink, LLC
NT10BIX5570112 | INF | 2013 | Q3 | Q3 - 2013 | 3247659 | 974298 | 2273361 | 3229553 | 1410430 | 1819123 | 3229553 | 1410430 | 1819123 | 9613119 | 2883936 | 6729183 | 9639161 | 2560730 | 7078431 | 9639161 | 2560730 | 7078431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122215 | 36664 | 85551 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428504 | 428551 | 999953 | 1413684 | 439991 | 973693 | 1413684 | 439991 | 973693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200642 | 60193 | 140449 | 207525 | 59653 | 147872 | 207525 | 59653 | 147872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884813 | 565444 | 1319369 | 1884813 | 443624 | 1441189 | 1884813 | 443624 | 1441189 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 0 | 908224 | Nebraskalink, LLC
NT10BIX5570113 | INF | 2010 | Q4 | Q4 - 2010 | 27996536 | 8850000 | 19146536 | 0 | 0 | 0 | 0 | 0 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 526000 | 0 | 526000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 147131 | 147131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 0 | 0 | 0 | 29869 | 29869 | 0 | 600000 | 0 | 600000 | 0 | 0 | 0 | 324000 | 0 | 324000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 0 | 0 | 0 | 58000 | 40000 | 18000 | 92907816 | 18909548 | 73998268 | 0 | 0 | 0 | 1085000 | 217000 | 868000 | 92907816 | 18909548 | 73998268 | 0 | 0 | 0 | 1085000 | 217000 | 868000 | 22877800 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2011 | Q1 | Q1 - 2011 | 27996536 | 8850000 | 19146536 | 0 | 0 | 0 | 0 | 0 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 108053 | 108053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 29869 | 29869 | 0 | 382069 | 382069 | 8512 | 600000 | 0 | 600000 | 0 | 0 | 0 | 324000 | 0 | 324000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 251343 | 251343 | 0 | 352021 | 352021 | 0 | 92907816 | 18909548 | 73998268 | 281212 | 281212 | 0 | 1166143 | 842143 | 332512 | 92907816 | 18909548 | 73998268 | 281212 | 281212 | 0 | 1166143 | 842143 | 332512 | 22877800 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2011 | Q2 | Q2 - 2011 | 27996536 | 8850000 | 19146536 | 5003792 | 5003792 | 0 | 5003792 | 5003792 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 1052000 | 0 | 1052000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 117450 | 90450 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 501545 | 501545 | 0 | 881545 | 881545 | 0 | 600000 | 0 | 600000 | 0 | 0 | 0 | 486000 | 0 | 486000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 311198 | 311198 | 0 | 347000 | 347000 | 0 | 92907816 | 18909548 | 73998268 | 5816535 | 5816535 | 0 | 7887787 | 6322787 | 1565000 | 92907816 | 18909548 | 73998268 | 5816535 | 5816535 | 0 | 7887787 | 6322787 | 1565000 | 22877800 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2011 | Q3 | Q3 - 2011 | 27996536 | 8850000 | 19146536 | 8850000 | 8850000 | 0 | 13850000 | 8850000 | 5000000 | 50109380 | 0 | 50109380 | 0 | 0 | 0 | 6630000 | 0 | 6630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8363120 | 4522500 | 3840620 | 4522500 | 4522500 | 0 | 5482655 | 4522500 | 960155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 929468 | 929468 | 0 | 1493438 | 1493438 | 0 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 100000 | 0 | 100000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 343054 | 343054 | 0 | 375000 | 375000 | 0 | 92907816 | 18909548 | 73998268 | 14672657 | 14645022 | 27635 | 27931093 | 15240938 | 12690155 | 92907816 | 18909548 | 73998268 | 14672657 | 14645022 | 27635 | 27931093 | 15240938 | 12690155 | 22877800 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2011 | Q4 | Q4 - 2011 | 27996536 | 8850000 | 19146536 | 8850000 | 8850000 | 0 | 13850000 | 8850000 | 5000000 | 50109380 | 0 | 50109380 | 0 | 0 | 0 | 7111500 | 0 | 7111500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8363120 | 4522500 | 3840620 | 4522500 | 4522500 | 0 | 6442810 | 4522500 | 1920310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 2004858 | 2004858 | 0 | 2291438 | 2007706 | 283732 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 55000 | 0 | 55000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 384579 | 384579 | 0 | 426000 | 426000 | 0 | 92907816 | 18909548 | 73998268 | 15789572 | 15761937 | 27635 | 30176748 | 15806206 | 14370542 | 92907816 | 18909548 | 73998268 | 15789572 | 15761937 | 27635 | 30176748 | 15806206 | 14370542 | 22877800 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2012 | Q1 | Q1 - 2012 | 28860022 | 8850000 | 20010022 | 11280161 | 8850000 | 2430161 | 18448554 | 8850000 | 9598554 | 48945894 | 0 | 48945894 | 0 | 0 | 0 | 24279993 | 0 | 24279993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 5527295 | 4522500 | 1004795 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4817836 | 4817836 | 0 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 62270 | 0 | 62270 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 1917404 | 1917404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 423653 | 423653 | 0 | 480727 | 462727 | 18000 | 92907816 | 18909548 | 73998268 | 22076580 | 18613989 | 3462591 | 58953636 | 20570467 | 38383169 | 92907816 | 18909548 | 73998268 | 22076580 | 18613989 | 3462591 | 58953636 | 20570467 | 38383169 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2012 | Q2 | Q2 - 2012 | 28860022 | 8850000 | 20010022 | 13840540 | 8850000 | 4990540 | 24627734 | 8850000 | 15777734 | 48945894 | 0 | 48945894 | 18974225 | 0 | 18974225 | 44407233 | 0 | 44407233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8131479 | 4522500 | 3608979 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4817836 | 4817836 | 0 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 47435 | 0 | 47435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 1159171 | 1159171 | 0 | 3067845 | 3067845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 460548 | 460548 | 0 | 515351 | 497351 | 18000 | 92907816 | 18909548 | 73998268 | 47431234 | 19810055 | 27621179 | 86432286 | 21755532 | 64676754 | 92907816 | 18909548 | 73998268 | 47431234 | 19810055 | 27621179 | 86432286 | 21755532 | 64676754 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2012 | Q3 | Q3 - 2012 | 28860022 | 8850000 | 20010022 | 23887755 | 8850000 | 15037755 | 26789340 | 8850000 | 17939340 | 48945894 | 0 | 48945894 | 35344776 | 0 | 35344776 | 45459304 | 0 | 45459304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8218666 | 4522500 | 3696166 | 8322603 | 4522500 | 3800103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 5101568 | 4817836 | 283732 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2092090 | 2092090 | 0 | 3758111 | 3758111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 544732 | 528547 | 16185 | 625020 | 607829 | 17191 | 92907816 | 18909548 | 73998268 | 75239022 | 20810973 | 54428049 | 90105381 | 22556276 | 67549105 | 92907816 | 18909548 | 73998268 | 75239022 | 20810973 | 54428049 | 90105381 | 22556276 | 67549105 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2012 | Q4 | Q4 - 2012 | 28860022 | 8850000 | 20010022 | 23914705 | 8850000 | 15064705 | 27360022 | 8850000 | 18510022 | 48945894 | 0 | 48945894 | 40477220 | 0 | 40477220 | 45459304 | 0 | 45459304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8222873 | 4522500 | 3700373 | 8322603 | 4522500 | 3800103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 5101568 | 4817836 | 283732 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 3356541 | 3356541 | 0 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 741653 | 724462 | 17191 | 850322 | 833131 | 17191 | 92907816 | 18909548 | 73998268 | 81863995 | 22271339 | 59592656 | 90978061 | 22858274 | 68119787 | 92907816 | 18909548 | 73998268 | 81863995 | 22271339 | 59592656 | 90978061 | 22858274 | 68119787 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2013 | Q1 | Q1 - 2013 | 28860022 | 8850000 | 20010022 | 24843181 | 8850000 | 15993181 | 28860022 | 8850000 | 20010022 | 48945894 | 0 | 48945894 | 40885120 | 0 | 40885120 | 48945894 | 0 | 48945894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8256228 | 4522500 | 3733728 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4052075 | 3768343 | 283732 | 4052075 | 3216969 | 835106 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2833455 | 2833455 | 0 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 828816 | 811625 | 17191 | 950560 | 933369 | 17191 | 92907816 | 18909548 | 73998268 | 81748310 | 20785923 | 60962387 | 95355913 | 21357645 | 73998268 | 92907816 | 18909548 | 73998268 | 81748310 | 20785923 | 60962387 | 95355913 | 21357645 | 73998268 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2013 | Q2 | Q2 - 2013 | 28860022 | 8850000 | 20010022 | 24843181 | 8850000 | 15993181 | 29819683 | 8850000 | 20969683 | 48945894 | 0 | 48945894 | 41758670 | 0 | 41758670 | 46598524 | 0 | 46598524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8262553 | 4522500 | 3740053 | 8566508 | 4522500 | 4044008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4140895 | 3857163 | 283732 | 4346956 | 2328245 | 2018711 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2942750 | 2942750 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 871799 | 854608 | 17191 | 899493 | 581586 | 317907 | 92907816 | 18909548 | 73998268 | 82869283 | 21027021 | 61842262 | 93280599 | 19282331 | 73998268 | 92907816 | 18909548 | 73998268 | 82869283 | 21027021 | 61842262 | 93280599 | 19282331 | 73998268 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570113 | INF | 2013 | Q3 | Q3 - 2013 | 28860022 | 8850000 | 20010022 | 29798898 | 8850000 | 20948898 | 29798898 | 8850000 | 20948898 | 48945894 | 0 | 48945894 | 44845316 | 0 | 44845316 | 44845316 | 0 | 44845316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8603750 | 4522500 | 4081250 | 8603750 | 4522500 | 4081250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 3857163 | 2349855 | 1507308 | 3857163 | 2349855 | 1507308 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2978390 | 2978390 | 0 | 2978390 | 2978390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 1338840 | 564566 | 774274 | 1338840 | 564566 | 774274 | 92907816 | 18909548 | 73998268 | 91471792 | 19265311 | 72206481 | 91471792 | 19265311 | 72206481 | 92907816 | 18909548 | 73998268 | 91471792 | 19265311 | 72206481 | 91471792 | 19265311 | 72206481 | 0 | 0 | Finance, Oklahoma Office of State
NT10BIX5570114 | INF | 2010 | Q4 | Q4 - 2010 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 0 | 0 | 0 | 51151342 | 10230268 | 40921074 | 1400 | 280 | 1120 | 511913 | 409531 | 102383 | 621845 | 124369 | 497476 | 33415 | 6683 | 26732 | 64835 | 51868 | 12967 | 1116000 | 223200 | 892800 | 0 | 0 | 0 | 12000 | 9600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 62550 | 12510 | 50040 | 1066871 | 853497 | 213374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 87691 | 17538 | 70152 | 112691 | 90153 | 22538 | 87049114 | 17409823 | 69639291 | 185056 | 37011 | 148044 | 1768310 | 1414649 | 353662 | 87049114 | 17409823 | 69639291 | 185056 | 37011 | 148044 | 1768310 | 1414649 | 353662 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2011 | Q1 | Q1 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 0 | 0 | 0 | 51151342 | 10230268 | 40921074 | 529 | 106 | 423 | 1784704 | 356941 | 1427764 | 621845 | 124369 | 497476 | 68140 | 13628 | 54512 | 102211 | 20442 | 81768 | 1116000 | 223200 | 892800 | 12501 | 2500 | 10000 | 21690 | 4338 | 17352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 202896 | 40579 | 162317 | 693731 | 138746 | 554985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31679 | 126717 | 246879 | 49376 | 197504 | 341833 | 68367 | 273466 | 86890718 | 17409823 | 69639291 | 530945 | 106189 | 424756 | 2944169 | 588834 | 2355335 | 86890718 | 17409823 | 69639291 | 530945 | 106189 | 424756 | 2944169 | 588834 | 2355335 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2011 | Q2 | Q2 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 1412230 | 282446 | 1129784 | 51151342 | 10230268 | 40921074 | 62303 | 12461 | 49843 | 2619870 | 523974 | 2095896 | 621845 | 124369 | 497476 | 109009 | 21802 | 87207 | 173113 | 34623 | 138791 | 1116000 | 223200 | 892800 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 581611 | 116322 | 465289 | 1122880 | 224576 | 898304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 289836 | 57967 | 231868 | 242225 | 48445 | 193780 | 87049114 | 17409823 | 69639291 | 1051759 | 210352 | 841407 | 5579318 | 1115864 | 4463755 | 87049114 | 17409823 | 69639291 | 1051759 | 210352 | 841407 | 5579318 | 1115864 | 4463755 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2011 | Q3 | Q3 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 1605711 | 321142 | 1284569 | 51151342 | 10230268 | 40921074 | 219126 | 43825 | 175301 | 17203373 | 3440675 | 13762698 | 621845 | 124369 | 497476 | 150325 | 30065 | 120260 | 241846 | 48369 | 193477 | 1116000 | 223200 | 892800 | 9000 | 1800 | 7200 | 25133 | 5027 | 20106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 1278093 | 255619 | 1022474 | 1628698 | 325740 | 1302958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 5601 | 1120 | 4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 374546 | 74909 | 299637 | 354340 | 70868 | 283472 | 87049114 | 17409823 | 69639291 | 2031090 | 406218 | 1624872 | 21064702 | 4212941 | 16851761 | 87049114 | 17409823 | 69639291 | 2031090 | 406218 | 1624872 | 21064702 | 4212941 | 16851761 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2011 | Q4 | Q4 - 2011 | 28244599 | 5648920 | 22595679 | 768041 | 153608 | 614433 | 6285648 | 1257130 | 5028518 | 51151342 | 10230268 | 40921074 | 4227478 | 845496 | 3381982 | 13951704 | 2790341 | 11161363 | 621845 | 124369 | 497476 | 153607 | 30721 | 122886 | 261063 | 52213 | 208850 | 1116000 | 223200 | 892800 | 30272 | 6054 | 24218 | 30272 | 6054 | 24218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 1861558 | 372312 | 1489246 | 1949940 | 389988 | 1559952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 4567 | 913 | 3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 394949 | 78990 | 315959 | 522737 | 104547 | 418189 | 87049114 | 17409823 | 69639291 | 7435905 | 1487181 | 5948724 | 23005931 | 4601186 | 18404744 | 87049114 | 17409823 | 69639291 | 7435905 | 1487181 | 5948724 | 23005931 | 4601186 | 18404744 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2012 | Q1 | Q1 - 2012 | 28244599 | 5648920 | 22595679 | 826001 | 165200 | 660801 | 6333412 | 1266682 | 5066729 | 51151342 | 10230268 | 40921074 | 9624082 | 1924817 | 7699265 | 18303829 | 3660766 | 14643063 | 621845 | 124369 | 497476 | 170389 | 34078 | 136311 | 455756 | 91151 | 364605 | 1116000 | 223200 | 892800 | 31410 | 6282 | 25128 | 174191 | 34838 | 139353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 2238211 | 447642 | 1790569 | 2240912 | 448182 | 1792729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 407177 | 81435 | 325742 | 1292882 | 258576 | 1034306 | 87049114 | 17409823 | 69639291 | 13297270 | 2659454 | 10637816 | 28800982 | 5760195 | 23040785 | 87049114 | 17409823 | 69639291 | 13297270 | 2659454 | 10637816 | 28800982 | 5760195 | 23040785 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2012 | Q2 | Q2 - 2012 | 28244599 | 5648920 | 22595679 | 1362844 | 272569 | 1090275 | 8117094 | 1623419 | 6493675 | 51151342 | 10230268 | 40921074 | 16086586 | 3217317 | 12869269 | 24939975 | 4987995 | 19951980 | 621845 | 124369 | 497476 | 173948 | 34790 | 139158 | 335745 | 67149 | 268596 | 1116000 | 223200 | 892800 | 82111 | 16422 | 65689 | 636140 | 127228 | 508912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 2757138 | 551428 | 2205710 | 2966921 | 593384 | 2373537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 5682 | 1136 | 4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 498977 | 99795 | 399182 | 559574 | 111915 | 447659 | 87049114 | 17409823 | 69639291 | 20961604 | 4192321 | 16769283 | 37561131 | 7512226 | 30048905 | 87049114 | 17409823 | 69639291 | 20961604 | 4192321 | 16769283 | 37561131 | 7512226 | 30048905 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2012 | Q3 | Q3 - 2012 | 28244599 | 5648920 | 22595679 | 2197701 | 439540 | 1758161 | 10919411 | 2183882 | 8735528 | 51151342 | 10230268 | 40921074 | 24928290 | 4985658 | 19942632 | 33571501 | 6714300 | 26857201 | 621845 | 124369 | 497476 | 173948 | 34790 | 139158 | 399626 | 79925 | 319701 | 1116000 | 223200 | 892800 | 82111 | 16422 | 65689 | 718959 | 143792 | 575167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 3449620 | 689924 | 2759696 | 3692021 | 738404 | 2953617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 7540 | 1508 | 6032 | 723009 | 144602 | 578407 | 11226 | 2245 | 8981 | 319824 | 63965 | 255859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 599523 | 119905 | 479618 | 666043 | 133209 | 532835 | 87049114 | 17409823 | 69639291 | 31442419 | 6288484 | 25153935 | 50294925 | 10058985 | 40235940 | 87049114 | 17409823 | 69639291 | 31442419 | 6288484 | 25153935 | 50294925 | 10058985 | 40235940 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2012 | Q4 | Q4 - 2012 | 28244599 | 5648920 | 22595679 | 5003147 | 1000629 | 4002518 | 16674482 | 3334896 | 13339585 | 51151342 | 10230268 | 40921074 | 33302710 | 6660542 | 26642168 | 42381304 | 8476261 | 33905043 | 621845 | 124369 | 497476 | 221643 | 44329 | 177315 | 492520 | 98504 | 394016 | 1116000 | 223200 | 892800 | 276614 | 55323 | 221291 | 890181 | 178036 | 712145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 4221816 | 844363 | 3377452 | 4853427 | 970685 | 3882742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 11257 | 2251 | 9005 | 723009 | 144602 | 578407 | 11226 | 2245 | 8981 | 420620 | 84124 | 336496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 621003 | 124201 | 496802 | 820865 | 164174 | 656691 | 87049114 | 17409823 | 69639291 | 43658159 | 8731632 | 34926527 | 66544656 | 13308931 | 53235723 | 87049114 | 17409823 | 69639291 | 43658159 | 8731632 | 34926527 | 66544656 | 13308931 | 53235723 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2013 | Q1 | Q1 - 2013 | 28244599 | 5648920 | 22595679 | 5753967 | 1150793 | 4603174 | 17049892 | 3409978 | 13639913 | 51151342 | 10230268 | 40921074 | 38764957 | 7752991 | 31011966 | 45107670 | 9021534 | 36086136 | 621845 | 124369 | 497476 | 219432 | 43886 | 175546 | 494425 | 98885 | 395540 | 1116000 | 223200 | 892800 | 276794 | 55359 | 221435 | 903219 | 180644 | 722575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 4719351 | 943870 | 3775481 | 5385788 | 1077158 | 4308631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 11257 | 2251 | 9005 | 723009 | 144602 | 578407 | 38578 | 7716 | 30863 | 434297 | 86859 | 347437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 635915 | 127184 | 508730 | 824043 | 164809 | 659234 | 87049114 | 17409823 | 69639291 | 50408994 | 10081799 | 40327195 | 70210591 | 14042118 | 56168471 | 87049114 | 17409823 | 69639291 | 50408994 | 10081799 | 40327195 | 70210591 | 14042118 | 56168471 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2013 | Q2 | Q2 - 2013 | 28244599 | 5648920 | 22595679 | 6764508 | 1352902 | 5411606 | 11090978 | 2218196 | 8872782 | 51151342 | 10230268 | 40921074 | 48747244 | 9749449 | 38997795 | 55229862 | 11045972 | 44183890 | 621845 | 124369 | 497476 | 224795 | 44959 | 179836 | 243464 | 48693 | 194771 | 1116000 | 223200 | 892800 | 300780 | 60156 | 240624 | 1018818 | 203764 | 815055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 5289847 | 1057969 | 4231878 | 5913777 | 1182755 | 4731021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 1780 | 356 | 1424 | 4567 | 913 | 3654 | 723009 | 144602 | 578407 | 46761 | 9352 | 37409 | 267615 | 53523 | 214092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 680276 | 136055 | 544221 | 730393 | 146079 | 584314 | 87049114 | 17409823 | 69639291 | 62055991 | 12411198 | 49644793 | 74499474 | 14899895 | 59599579 | 87049114 | 17409823 | 69639291 | 62055991 | 12411198 | 49644793 | 74499474 | 14899895 | 59599579 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2013 | Q3 | Q3 - 2013 | 28244599 | 5648920 | 22595679 | 10928246 | 2185649 | 8742597 | 10945260 | 2189052 | 8756208 | 51151342 | 10230268 | 40921074 | 58455899 | 11691180 | 46764719 | 66985690 | 13397138 | 53588552 | 621845 | 124369 | 497476 | 228844 | 45769 | 183075 | 289971 | 57994 | 231977 | 1116000 | 223200 | 892800 | 403689 | 80738 | 322951 | 1314318 | 262864 | 1051454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 5726327 | 1145265 | 4581062 | 6423027 | 1284605 | 5138422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 12227 | 2445 | 9782 | 13721 | 2744 | 10977 | 723009 | 144602 | 578407 | 52390 | 10478 | 41912 | 207215 | 41443 | 165772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 844380 | 168877 | 675503 | 869912 | 173982 | 695930 | 87049114 | 17409823 | 69639291 | 76652002 | 15330401 | 61321601 | 87049114 | 17409822 | 69639292 | 87049114 | 17409823 | 69639291 | 76652002 | 15330401 | 61321601 | 87049114 | 17409822 | 69639292 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2013 | Q4 | Q4 - 2013 | 28244599 | 5648920 | 22595679 | 11089300 | 2217860 | 8871440 | 11106830 | 2221366 | 8885464 | 51151342 | 10230268 | 40921074 | 64147491 | 12829498 | 51317993 | 66313852 | 13262770 | 53051082 | 621845 | 124369 | 497476 | 232724 | 46545 | 186179 | 259741 | 51948 | 207793 | 1116000 | 223200 | 892800 | 408928 | 81786 | 327142 | 900504 | 180101 | 720403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6268229 | 1253646 | 5014583 | 7173292 | 1434658 | 5738634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29159 | 5832 | 23327 | 104808 | 20962 | 83846 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 210864 | 42173 | 168691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 941498 | 188299 | 753199 | 979223 | 195845 | 783378 | 87049114 | 17409823 | 69639291 | 83183043 | 16636609 | 66546434 | 87049114 | 17409823 | 69639291 | 87049114 | 17409823 | 69639291 | 83183043 | 16636609 | 66546434 | 87049114 | 17409823 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2014 | Q1 | Q1 - 2014 | 28244599 | 5648920 | 22595679 | 13278900 | 2655780 | 10623120 | 13296430 | 2673310 | 10623120 | 51151342 | 10230268 | 40921074 | 65815698 | 13244159 | 52571539 | 67710736 | 15139197 | 52571539 | 621845 | 124369 | 497476 | 323572 | 111152 | 212420 | 476838 | 264418 | 212420 | 1116000 | 223200 | 892800 | 355983 | 72924 | 283059 | 658904 | 375845 | 283059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6594487 | 1477732 | 5116755 | 7045855 | 1929100 | 5116755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29158 | 5831 | 23327 | 29486 | 6159 | 23327 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 172203 | 119632 | 52571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 949586 | 193085 | 756501 | 1030514 | 274013 | 756501 | 87049114 | 17409823 | 69639291 | 87413098 | 17773806 | 69639292 | 90420966 | 20781674 | 69639292 | 87049114 | 17409823 | 69639291 | 87413098 | 17773806 | 69639292 | 90420966 | 20781674 | 69639292 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2014 | Q2 | Q2 - 2014 | 28244599 | 5648920 | 22595679 | 13304179 | 2681059 | 10623120 | 13321709 | 2698589 | 10623120 | 51151342 | 10230268 | 40921074 | 66277036 | 13705497 | 52571539 | 66402224 | 13830685 | 52571539 | 621845 | 124369 | 497476 | 406188 | 193768 | 212420 | 489926 | 277506 | 212420 | 1116000 | 223200 | 892800 | 362405 | 79346 | 283059 | 362405 | 79346 | 283059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6736348 | 1619593 | 5116755 | 6834726 | 1717971 | 5116755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29158 | 5832 | 23326 | 29486 | 6160 | 23326 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 65714 | 13143 | 52571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 954939 | 198438 | 756501 | 1039777 | 283276 | 756501 | 87049114 | 17409823 | 69639291 | 88135967 | 18496676 | 69639291 | 88545967 | 18906676 | 69639291 | 87049114 | 17409823 | 69639291 | 88135967 | 18496676 | 69639291 | 88545967 | 18906676 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2014 | Q3 | Q3 - 2014 | 28244599 | 5648920 | 22595679 | 13304179 | 2681059 | 10623120 | 13304179 | 2681059 | 10623120 | 51151342 | 10230268 | 40921074 | 66939276 | 14367737 | 52571539 | 67009743 | 14438204 | 52571539 | 621845 | 124369 | 497476 | 441875 | 229455 | 212420 | 449010 | 236590 | 212420 | 1116000 | 223200 | 892800 | 396304 | 113245 | 283059 | 396304 | 113245 | 283059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6835808 | 1719053 | 5116755 | 6881831 | 1765076 | 5116755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29158 | 5832 | 23326 | 29158 | 5832 | 23326 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 65714 | 13143 | 52571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 1009675 | 253174 | 756501 | 1061050 | 304549 | 756501 | 87049114 | 17409823 | 69639291 | 89021989 | 19382698 | 69639291 | 89196989 | 19557698 | 69639291 | 87049114 | 17409823 | 69639291 | 89021989 | 19382698 | 69639291 | 89196989 | 19557698 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2014 | Q4 | Q4 - 2014 | 28244599 | 5648920 | 22595679 | 13329917 | 2706797 | 10623120 | 13329917 | 2706797 | 10623120 | 51151342 | 10230268 | 40921074 | 67618492 | 15046954 | 52571539 | 67972709 | 15401170 | 52571539 | 621845 | 124369 | 497476 | 469811 | 257391 | 212420 | 497746 | 285326 | 212420 | 1116000 | 223200 | 892800 | 397130 | 114071 | 283059 | 397130 | 114071 | 283059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6935654 | 1818898 | 5116755 | 7026499 | 1909744 | 5116755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29158 | 5832 | 23326 | 29158 | 5832 | 23326 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 65714 | 13143 | 52571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 1026448 | 269947 | 756501 | 1038450 | 281949 | 756501 | 87049114 | 17409823 | 69639291 | 89872324 | 20233033 | 69639291 | 90357323 | 20718032 | 69639291 | 87049114 | 17409823 | 69639291 | 89872324 | 20233033 | 69639291 | 90357323 | 20718032 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2015 | Q1 | Q1 - 2015 | 28244599 | 5648920 | 22595679 | 13329917 | 2706797 | 10623120 | 13329917 | 2706797 | 10623120 | 51151342 | 10230268 | 40921074 | 67773714 | 15202175 | 52571539 | 67827464 | 15255925 | 52571539 | 621845 | 124369 | 497476 | 492165 | 279745 | 212420 | 514519 | 302099 | 212420 | 1116000 | 223200 | 892800 | 397130 | 114071 | 283059 | 397130 | 114071 | 283059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 7090873 | 1974118 | 5116755 | 7144623 | 2027868 | 5116755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29158 | 5832 | 23326 | 29158 | 5832 | 23326 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 65714 | 13143 | 52571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 1048802 | 292301 | 756501 | 1071156 | 314655 | 756501 | 87049114 | 17409823 | 69639291 | 90227473 | 20588182 | 69639291 | 90379681 | 20740390 | 69639291 | 87049114 | 17409823 | 69639291 | 90227473 | 20588182 | 69639291 | 90379681 | 20740390 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570114 | INF | 2015 | Q2 | Q2 - 2015 | 14120263 | 2824053 | 11296210 | 14120263 | 2824053 | 11296210 | 14120263 | 2824053 | 11296210 | 62784060 | 12556812 | 50227248 | 65198867 | 14971619 | 50227248 | 65198867 | 14971619 | 50227248 | 584016 | 116803 | 467213 | 812942 | 345729 | 467213 | 812942 | 345729 | 467213 | 2572015 | 514403 | 2057612 | 2673793 | 616181 | 2057612 | 2673793 | 616181 | 2057612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6607678 | 1321536 | 5286142 | 7106683 | 1820541 | 5286142 | 7106683 | 1820541 | 5286142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381082 | 76216 | 304866 | 467133 | 162267 | 304866 | 467133 | 162267 | 304866 | 87049114 | 17409823 | 69639291 | 90379681 | 20740390 | 69639291 | 90379681 | 20740390 | 69639291 | 87049114 | 17409823 | 69639291 | 90379681 | 20740390 | 69639291 | 90379681 | 20740390 | 69639291 | 0 | 0 | Merit Network Inc.
NT10BIX5570115 | INF | 2010 | Q4 | Q4 - 2010 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 454350 | 107394 | 346956 | 28819806 | 8669749 | 20150057 | 0 | 0 | 0 | 36391 | 8602 | 27789 | 1660444 | 498133 | 1162311 | 0 | 0 | 0 | 322293 | 109613 | 212680 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 247444 | 58488 | 188956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 0 | 0 | 0 | 362389 | 97453 | 264936 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 0 | 0 | 0 | 27339 | 27339 | 0 | 42726744 | 12841830 | 29884914 | 0 | 0 | 0 | 1457706 | 416389 | 1041317 | 42726744 | 12841830 | 29884914 | 0 | 0 | 0 | 1457706 | 416389 | 1041317 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2011 | Q1 | Q1 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 536416 | 126792 | 409624 | 28819806 | 8669749 | 20150057 | 0 | 0 | 0 | 5570206 | 1495209 | 4074997 | 1660444 | 498133 | 1162311 | 112065 | 0 | 77837 | 477710 | 146349 | 331361 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 472328 | 138372 | 333956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 122526 | 0 | 122526 | 543096 | 140166 | 402930 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 0 | 34228 | 0 | 41589 | 30707 | 10882 | 42726744 | 12841830 | 29884914 | 234591 | 34228 | 200363 | 7648845 | 2085095 | 5563750 | 42726744 | 12841830 | 29884914 | 234591 | 34228 | 200363 | 7648845 | 2085095 | 5563750 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2011 | Q2 | Q2 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 300000 | 0 | 300000 | 28819806 | 8669749 | 20150057 | 1027237 | 333288 | 693949 | 10458838 | 2301718 | 8157120 | 1660444 | 498133 | 1162311 | 203772 | 74367 | 129405 | 389607 | 74367 | 315240 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 1651469 | 1509000 | 142469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 233670 | 45424 | 188246 | 397498 | 45424 | 352074 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 1498337 | 486737 | 1011600 | 13231070 | 3964167 | 9266903 | 42726744 | 12841830 | 29884914 | 1498337 | 486737 | 1011600 | 13231070 | 3964167 | 9266903 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2011 | Q3 | Q3 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 28819806 | 8669749 | 20150057 | 5216483 | 825500 | 4390983 | 14252769 | 4332568 | 9920201 | 1660444 | 498133 | 1162311 | 394740 | 74367 | 320373 | 472440 | 74367 | 398073 | 3805578 | 1141673 | 2663905 | 1639772 | 1509000 | 130772 | 1639772 | 1509000 | 130772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 481542 | 60871 | 420671 | 1638524 | 60871 | 1577653 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 7773695 | 2510896 | 5262799 | 20044663 | 6017964 | 14026699 | 42726744 | 12841830 | 29884914 | 7773695 | 2510896 | 5262799 | 20044663 | 6017964 | 14026699 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2011 | Q4 | Q4 - 2011 | 6553615 | 1966084 | 4587531 | 2828637 | 250000 | 2578637 | 3016219 | 250000 | 2766219 | 28819806 | 8669749 | 20150057 | 12198281 | 3293037 | 8905244 | 13165220 | 3815911 | 9349309 | 1660444 | 498133 | 1162311 | 508024 | 74368 | 433656 | 568438 | 74367 | 494071 | 3805578 | 1141673 | 2663905 | 1724379 | 1509000 | 215379 | 1748172 | 1509000 | 239172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 537394 | 60871 | 476523 | 560592 | 60871 | 499721 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 17837873 | 5228434 | 12609439 | 19099799 | 5751307 | 13348492 | 42726744 | 12841830 | 29884914 | 17837873 | 5228434 | 12609439 | 19099799 | 5751307 | 13348492 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2012 | Q1 | Q1 - 2012 | 6553615 | 1966084 | 4587531 | 3021876 | 250000 | 2771876 | 4472408 | 700000 | 3772408 | 28819806 | 8669749 | 20150057 | 14415670 | 4185998 | 10229672 | 15898076 | 4674265 | 11223811 | 1660444 | 498133 | 1162311 | 632675 | 74367 | 558308 | 699212 | 74367 | 624845 | 3805578 | 1141673 | 2663905 | 1751919 | 1509000 | 242919 | 1751919 | 1509000 | 242919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 559084 | 60871 | 498213 | 591249 | 60871 | 530378 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 20422382 | 6121394 | 14300988 | 23454022 | 7059661 | 16394361 | 42726744 | 12841830 | 29884914 | 20422382 | 6121394 | 14300988 | 23454022 | 7059661 | 16394361 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2012 | Q2 | Q2 - 2012 | 6553615 | 1966084 | 4587531 | 4316766 | 500000 | 3816766 | 4320078 | 500000 | 3820078 | 28819806 | 8669749 | 20150057 | 16027039 | 4930271 | 11096768 | 17627112 | 5505484 | 12121628 | 1660444 | 498133 | 1162311 | 764921 | 74367 | 690554 | 1006813 | 74367 | 932446 | 3805578 | 1141673 | 2663905 | 1771829 | 1509000 | 262829 | 1793446 | 1509000 | 284446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 727637 | 60871 | 666766 | 769875 | 60871 | 709004 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 23649350 | 7115667 | 16533683 | 25558482 | 7690880 | 17867602 | 42726744 | 12841830 | 29884914 | 23649350 | 7115667 | 16533683 | 25558482 | 7690880 | 17867602 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2012 | Q3 | Q3 - 2012 | 6553615 | 1966084 | 4587531 | 4480278 | 550000 | 3930278 | 4480278 | 550000 | 3930278 | 28819806 | 8669749 | 20150057 | 17965563 | 5630643 | 12334920 | 22777465 | 7093193 | 15684272 | 1660444 | 498133 | 1162311 | 1054891 | 74367 | 980524 | 1140318 | 74367 | 1065951 | 3805578 | 1141673 | 2663905 | 1796795 | 1509000 | 287795 | 1801195 | 1509000 | 292195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 759604 | 60871 | 698733 | 797153 | 60871 | 736282 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 26098289 | 7866039 | 18232250 | 31037567 | 9328589 | 21708978 | 42726744 | 12841830 | 29884914 | 26098289 | 7866039 | 18232250 | 31037567 | 9328589 | 21708978 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2012 | Q4 | Q4 - 2012 | 6553615 | 1966084 | 4587531 | 4480278 | 550000 | 3930278 | 4742484 | 550000 | 4192484 | 28819806 | 8669749 | 20150057 | 24572272 | 7787880 | 16784392 | 25872809 | 8241159 | 17631650 | 1660444 | 498133 | 1162311 | 1262279 | 74367 | 1187912 | 1429304 | 74367 | 1354937 | 3805578 | 1141673 | 2663905 | 2185005 | 1509000 | 676005 | 2428995 | 1661000 | 767995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 797272 | 60871 | 736401 | 842705 | 60871 | 781834 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 33338612 | 10023276 | 23315336 | 35357803 | 10628555 | 24729248 | 42726744 | 12841830 | 29884914 | 33338612 | 10023276 | 23315336 | 35357803 | 10628555 | 24729248 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2013 | Q1 | Q1 - 2013 | 6553615 | 1966084 | 4587531 | 5094935 | 550000 | 4544935 | 5594935 | 550000 | 5044935 | 28819806 | 8669749 | 20150057 | 25584290 | 8299263 | 17285027 | 27794405 | 9059263 | 18735142 | 1660444 | 498133 | 1162311 | 1479067 | 74368 | 1404699 | 1581567 | 74368 | 1507199 | 3805578 | 1141673 | 2663905 | 3015448 | 1814000 | 1201448 | 3515448 | 2064000 | 1451448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 841657 | 60871 | 780786 | 886657 | 60871 | 825786 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 36056903 | 10839660 | 25217243 | 39414518 | 11849660 | 27564858 | 42726744 | 12841830 | 29884914 | 36056903 | 10839660 | 25217243 | 39414518 | 11849660 | 27564858 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2013 | Q2 | Q2 - 2013 | 6553615 | 1966084 | 4587531 | 5817896 | 550000 | 5267896 | 6258680 | 550000 | 5708680 | 28819806 | 8669749 | 20150057 | 27572145 | 9145622 | 18426523 | 30473165 | 10181433 | 20291732 | 1660444 | 498133 | 1162311 | 1643549 | 74368 | 1569181 | 1728291 | 74368 | 1653923 | 3805578 | 1141673 | 2663905 | 3315817 | 1934000 | 1381817 | 3317567 | 1934000 | 1383567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 881535 | 60871 | 820664 | 907535 | 60871 | 846664 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 39272448 | 11806019 | 27466429 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 39272448 | 11806019 | 27466429 | 42726744 | 12841830 | 29884914 | 0 | 0 | University of Wisconsin System
NT10BIX5570115 | INF | 2013 | Q3 | Q3 - 2013 | 6553615 | 1966084 | 4587531 | 6584360 | 655000 | 5929360 | 6584360 | 655000 | 5929360 | 28819806 | 8669749 | 20150057 | 29875825 | 10076433 | 19799392 | 29875825 | 10076433 | 19799392 | 1660444 | 498133 | 1162311 | 1901432 | 74368 | 1827064 | 1901432 | 74368 | 1827064 | 3805578 | 1141673 | 2663905 | 3412400 | 1934000 | 1478400 | 3412400 | 1934000 | 1478400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 911221 | 60871 | 850350 | 911221 | 60871 | 850350 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 0 | 0 | University of Wisconsin System
NT10BIX5570116 | INF | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 0 | 0 | 0 | 500000 | 0 | 394500 | 150000 | 31664 | 118336 | 14763 | 3115 | 11648 | 34763 | 7335 | 27428 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 96940 | 20454 | 76485 | 694889 | 104854 | 548267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 111703 | 23569 | 88133 | 1229652 | 112189 | 970195 | 13391443 | 2825651 | 10565792 | 111703 | 23569 | 88133 | 1229652 | 112189 | 970195 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 0 | 0 | 0 | 373500 | 0 | 373500 | 150000 | 31664 | 118336 | 30567 | 6450 | 24117 | 45852 | 9675 | 36177 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 417633 | 88122 | 329511 | 824360 | 173943 | 650417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 448200 | 94572 | 353628 | 1243712 | 183618 | 1060094 | 13391443 | 2825651 | 10565792 | 448200 | 94572 | 353628 | 1243712 | 183618 | 1060094 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 111000 | 23421 | 87579 | 3886194 | 819987 | 3066207 | 150000 | 31664 | 118336 | 49036 | 10347 | 38689 | 59809 | 12620 | 47189 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 400000 | 84000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 716073 | 151094 | 564979 | 826073 | 174194 | 651879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 876109 | 184862 | 691247 | 5172076 | 1090801 | 4081275 | 13391443 | 2825651 | 10565792 | 876109 | 184862 | 691247 | 5172076 | 1090801 | 4081275 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 2994721 | 628891 | 2365830 | 6132221 | 1287766 | 4844455 | 150000 | 31664 | 118336 | 81012 | 17094 | 63918 | 112012 | 23094 | 88918 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 819323 | 172882 | 646441 | 922320 | 193687 | 728633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 4718956 | 1642767 | 3076189 | 8033953 | 2371947 | 5662006 | 13391443 | 2825651 | 10565792 | 4718956 | 1642767 | 3076189 | 8033953 | 2371947 | 5662006 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 5461525 | 1149397 | 4312128 | 7046844 | 1095593 | 5951251 | 150000 | 31664 | 118336 | 102445 | 21616 | 80828 | 122785 | 25367 | 97418 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 944112 | 199213 | 744899 | 1042320 | 219008 | 823312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 7331982 | 2194126 | 5137855 | 9035849 | 2163868 | 6871981 | 13391443 | 2825651 | 10565792 | 7331982 | 2194126 | 5137855 | 9035849 | 2163868 | 6871981 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 5873856 | 1233510 | 4640346 | 6640856 | 1365510 | 5275346 | 150000 | 31664 | 118336 | 125144 | 26280 | 98864 | 133144 | 28280 | 104864 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1148128 | 241107 | 907021 | 1188128 | 250107 | 938021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 7971028 | 2324797 | 5646231 | 8786028 | 2467797 | 6318231 | 13391443 | 2825651 | 10565792 | 7971028 | 2324797 | 5646231 | 8786028 | 2467797 | 6318231 | 0 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 8257719 | 1233510 | 7024209 | 9517769 | 1404868 | 8112901 | 150000 | 31664 | 118336 | 158407 | 33439 | 124968 | 162611 | 34326 | 128285 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1275356 | 269112 | 1006244 | 1427208 | 301154 | 1126054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 10515382 | 2359961 | 8155421 | 11931488 | 2564248 | 9367240 | 13391443 | 2825651 | 10565792 | 10515382 | 2359961 | 8155421 | 11931488 | 2564248 | 9367240 | 169480 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 8986712 | 1270717 | 7715995 | 9845740 | 1453278 | 8392462 | 150000 | 31664 | 118336 | 180290 | 35198 | 145092 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1327062 | 269112 | 1057950 | 1490754 | 314563 | 1176191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 11317964 | 2398927 | 8919037 | 12350392 | 2628988 | 9721404 | 13391443 | 2825651 | 10565792 | 11317964 | 2398927 | 8919037 | 12350392 | 2628988 | 9721404 | 169480 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 9924088 | 1453278 | 8470810 | 10495122 | 1549130 | 8945992 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 244398 | 77247 | 167151 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1490754 | 314563 | 1176191 | 1535197 | 323941 | 1211257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 12428740 | 2628988 | 9799752 | 13142117 | 2817718 | 10324400 | 13391443 | 2825651 | 10565792 | 12428740 | 2628988 | 9799752 | 13142117 | 2817718 | 10324400 | 169480 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10110456 | 1518929 | 8591527 | 10529252 | 1593391 | 8935861 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1534387 | 333196 | 1201191 | 1599060 | 333196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 12658741 | 2713272 | 9945469 | 13185710 | 2831234 | 10354476 | 13391443 | 2825651 | 10565792 | 12658741 | 2713272 | 9945469 | 13185710 | 2831234 | 10354476 | 169480 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10542535 | 1532818 | 9009717 | 10734985 | 1587808 | 9147177 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 843900 | 843900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1599060 | 333196 | 1265864 | 1599060 | 333196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 13175493 | 2747161 | 10428332 | 13391443 | 2825651 | 10565792 | 13391443 | 2825651 | 10565792 | 13175493 | 2747161 | 10428332 | 13391443 | 2825651 | 10565792 | 169480 | 0 | North Central New Mexico Economic Development District
NT10BIX5570116 | INF | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10840875 | 1693698 | 9147177 | 10840875 | 1693698 | 9147177 | 150000 | 31664 | 118336 | 258641 | 105890 | 152751 | 258641 | 105890 | 152751 | 867400 | 867400 | 0 | 867400 | 867400 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1634060 | 368196 | 1265864 | 1634060 | 368196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 13600976 | 3035184 | 10565792 | 13600976 | 3035184 | 10565792 | 13391443 | 2825651 | 10565792 | 13600976 | 3035184 | 10565792 | 13600976 | 3035184 | 10565792 | 169480 | 92853 | North Central New Mexico Economic Development District
NT10BIX5570117 | INF | 2010 | Q4 | Q4 - 2010 | 12818604 | 4101953 | 8716651 | 4886 | 1564 | 3322 | 2708617 | 866757 | 1841860 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 556903 | 291769 | 265134 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 5742 | 1895 | 3847 | 34500 | 11040 | 23460 | 14306764 | 4701924 | 9604840 | 367531 | 231228 | 136303 | 3477520 | 1226366 | 2251154 | 14306764 | 4701924 | 9604840 | 367531 | 231228 | 136303 | 3477520 | 1226366 | 2251154 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2011 | Q1 | Q1 - 2011 | 12818604 | 4101953 | 8716651 | 34037 | 11331 | 22706 | 4888827 | 1564425 | 3324402 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 528760 | 282763 | 245997 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 11339 | 3628 | 7711 | 50000 | 16000 | 34000 | 14306764 | 4701924 | 9619840 | 402279 | 242728 | 159551 | 5645087 | 1919988 | 3725099 | 14306764 | 4701924 | 9619840 | 402279 | 242728 | 159551 | 5645087 | 1919988 | 3725099 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2011 | Q2 | Q2 - 2011 | 12818604 | 4101953 | 8716651 | 34037 | 11331 | 22706 | 4888827 | 1564425 | 3324402 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 528760 | 282763 | 245997 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 14410 | 4611 | 9799 | 53701 | 16983 | 36088 | 14306764 | 4701924 | 9619840 | 405350 | 243711 | 161639 | 5648788 | 1920971 | 3727187 | 14306764 | 4701924 | 9619840 | 405350 | 243711 | 161639 | 5648788 | 1920971 | 3727187 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2011 | Q3 | Q3 - 2011 | 12818604 | 4101953 | 8716651 | 534808 | 171577 | 363228 | 4534808 | 1451577 | 3083231 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 371928 | 232577 | 139351 | 571928 | 296577 | 275351 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 100000 | 32000 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 29790 | 9475 | 20135 | 129610 | 41475 | 88135 | 14306764 | 4701924 | 9604840 | 936526 | 413629 | 522714 | 5336346 | 1821629 | 3514717 | 14306764 | 4701924 | 9604840 | 936526 | 413629 | 522714 | 5336346 | 1821629 | 3514717 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2011 | Q4 | Q4 - 2011 | 12818604 | 4101953 | 8716651 | 2493270 | 798285 | 1694985 | 5493271 | 1757847 | 3735424 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 431090 | 251509 | 179581 | 531090 | 283509 | 247581 | 483500 | 154720 | 328780 | 100238 | 32076 | 68162 | 300238 | 96076 | 204162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 33128 | 10601 | 22527 | 113128 | 36201 | 76927 | 14306764 | 4701924 | 9604840 | 3057726 | 1092471 | 1965255 | 6437727 | 2173633 | 4264094 | 14306764 | 4701924 | 9604840 | 3057726 | 1092471 | 1965255 | 6437727 | 2173633 | 4264094 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2012 | Q1 | Q1 - 2012 | 12280364 | 3929716 | 8350648 | 5127970 | 1641389 | 3486581 | 7921199 | 2534784 | 5386415 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 668229 | 327393 | 340836 | 793229 | 367393 | 425836 | 844740 | 270317 | 574423 | 154239 | 49356 | 104883 | 454239 | 145356 | 308883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 33128 | 10601 | 22527 | 100000 | 32000 | 68000 | 14306764 | 4701924 | 9604840 | 5983566 | 2028739 | 3954827 | 9268667 | 3079533 | 6189134 | 14306764 | 4701924 | 9604840 | 5983566 | 2028739 | 3954827 | 9268667 | 3079533 | 6189134 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2012 | Q2 | Q2 - 2012 | 12280364 | 3929716 | 8350648 | 8181776 | 2618607 | 5563169 | 11340341 | 3628909 | 7711432 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 767102 | 359033 | 408069 | 805760 | 371404 | 434356 | 844740 | 270317 | 574423 | 212189 | 67900 | 144289 | 512189 | 163900 | 348289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 241710 | 77347 | 164363 | 14306764 | 4701924 | 9604840 | 9202777 | 3058887 | 6143890 | 12900000 | 4241560 | 8658440 | 14306764 | 4701924 | 9604840 | 9202777 | 3058887 | 6143890 | 12900000 | 4241560 | 8658440 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2012 | Q3 | Q3 - 2012 | 12280364 | 3929716 | 8350648 | 9096723 | 2911390 | 6185333 | 11700000 | 3744000 | 7956000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 782462 | 363948 | 418514 | 805760 | 371403 | 434357 | 844740 | 270317 | 574423 | 378220 | 121030 | 257190 | 844740 | 270317 | 574423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 300000 | 96000 | 204000 | 14306764 | 4701924 | 9604840 | 10299115 | 3409715 | 6889400 | 13650500 | 4481720 | 9168780 | 14306764 | 4701924 | 9604840 | 10299115 | 3409715 | 6889400 | 13650500 | 4481720 | 9168780 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2012 | Q4 | Q4 - 2012 | 12280364 | 3929716 | 8350648 | 11224120 | 3592157 | 7631963 | 12280364 | 3929716 | 8350648 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 815792 | 374613 | 441179 | 1016060 | 438699 | 577361 | 634440 | 203021 | 431419 | 504990 | 161597 | 343393 | 634440 | 203021 | 431419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 360900 | 115488 | 245412 | 14306764 | 4701924 | 9604840 | 12586612 | 4141714 | 8444898 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 12586612 | 4141714 | 8444898 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2013 | Q1 | Q1 - 2013 | 12502265 | 4000725 | 8501540 | 11993313 | 3838299 | 8155014 | 12377242 | 3960718 | 8416525 | 15000 | 15000 | 0 | 2893 | 2893 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 925314 | 409660 | 515654 | 1016060 | 438699 | 577361 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 41710 | 13347 | 28363 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 13676257 | 4492368 | 9183889 | 14181741 | 4661917 | 9519825 | 14306764 | 4701924 | 9604840 | 13676257 | 4492368 | 9183889 | 14181741 | 4661917 | 9519825 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2013 | Q2 | Q2 - 2013 | 12502265 | 4000725 | 8501540 | 12332135 | 3946722 | 8385413 | 12502265 | 4000725 | 8501540 | 15000 | 15000 | 0 | 5670 | 5670 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 948354 | 417033 | 531321 | 1016060 | 438699 | 577361 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 14059598 | 4616925 | 9442673 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14059598 | 4616925 | 9442673 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County
NT10BIX5570117 | INF | 2013 | Q3 | Q3 - 2013 | 12433575 | 3979183 | 8454392 | 12433575 | 3979183 | 8454392 | 12433575 | 3979183 | 8454392 | 15000 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084750 | 460241 | 624509 | 1084750 | 460241 | 624509 | 1084750 | 460241 | 624509 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County
NT10BIX5570118 | INF | 2010 | Q4 | Q4 - 2010 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 100000 | 0 | 100000 | 8329504 | 1035600 | 7293904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 0 | 0 | 0 | 108000 | 0 | 108000 | 570000 | 570000 | 0 | 0 | 0 | 0 | 123750 | 123750 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 0 | 0 | 0 | 406750 | 123750 | 283000 | 12343984 | 3180600 | 9163384 | 0 | 0 | 0 | 406750 | 123750 | 283000 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2011 | Q1 | Q1 - 2011 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 0 | 0 | 0 | 8329504 | 1035600 | 7293904 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 1205000 | 1005000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 238234 | 0 | 238234 | 600000 | 0 | 600000 | 570000 | 570000 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 238234 | 0 | 238234 | 3005000 | 1105000 | 1900000 | 12343984 | 3180600 | 9163384 | 238234 | 0 | 238234 | 3005000 | 1105000 | 1900000 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2011 | Q2 | Q2 - 2011 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 750000 | 500000 | 250000 | 8329504 | 1035600 | 7293904 | 765000 | 0 | 0 | 3000000 | 50000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 765227 | 765227 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 530196 | 0 | 530196 | 530196 | 0 | 530196 | 570000 | 570000 | 0 | 125000 | 125000 | 0 | 190000 | 190000 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 2185423 | 890227 | 530196 | 6212696 | 1745000 | 4017696 | 12343984 | 3180600 | 9163384 | 2185423 | 890227 | 530196 | 6212696 | 1745000 | 4017696 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2011 | Q3 | Q3 - 2011 | 1435980 | 570000 | 865980 | 702716 | 136290 | 566426 | 1000000 | 400000 | 600000 | 8329504 | 1035600 | 7293904 | 1262560 | 325567 | 936993 | 5600000 | 1000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 382333 | 330733 | 51600 | 1080733 | 830733 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 707520 | 65379 | 642141 | 800000 | 65379 | 734621 | 570000 | 570000 | 0 | 72588 | 32258 | 40330 | 272588 | 232258 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 0 | 1685 | 1685 | 0 | 1685 | 12343984 | 3180600 | 9163384 | 3129402 | 890227 | 2239175 | 8855006 | 2528370 | 5726636 | 12343984 | 3180600 | 9163384 | 3129402 | 890227 | 2239175 | 8855006 | 2528370 | 5726636 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2011 | Q4 | Q4 - 2011 | 1435980 | 570000 | 865980 | 973942 | 403047 | 570895 | 1415000 | 550000 | 865000 | 8329504 | 1035600 | 7293904 | 4028642 | 776090 | 3252552 | 6500000 | 1000000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1145863 | 1094263 | 51600 | 1145863 | 1094263 | 51600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 901802 | 114083 | 787719 | 1000000 | 164083 | 835917 | 570000 | 570000 | 0 | 257976 | 217646 | 40330 | 307976 | 267646 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1686 | 0 | 1686 | 1686 | 0 | 1686 | 12343984 | 3180600 | 9163384 | 7309911 | 2605129 | 4704782 | 10370525 | 3075992 | 7294533 | 12343984 | 3180600 | 9163384 | 7309911 | 2605129 | 4704782 | 10370525 | 3075992 | 7294533 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2012 | Q1 | Q1 - 2012 | 1435980 | 570000 | 865980 | 977395 | 403047 | 574348 | 1250000 | 403047 | 846953 | 8329504 | 1035600 | 7293904 | 4621518 | 776090 | 3845428 | 5000000 | 776090 | 4223910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1226421 | 1094263 | 132158 | 1226421 | 1094263 | 132158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 1111748 | 144293 | 967455 | 1111748 | 144293 | 967455 | 570000 | 570000 | 0 | 299218 | 258888 | 40330 | 340330 | 300000 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1686 | 0 | 1686 | 1686 | 0 | 1686 | 12343984 | 3180600 | 9163384 | 8237986 | 2676581 | 5561405 | 8930185 | 2717693 | 6212492 | 12343984 | 3180600 | 9163384 | 8237986 | 2676581 | 5561405 | 8930185 | 2717693 | 6212492 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2012 | Q2 | Q2 - 2012 | 1810980 | 570000 | 1240980 | 1162206 | 403047 | 759159 | 1403047 | 403047 | 1000000 | 7004505 | 1035600 | 5968905 | 5133870 | 776090 | 4357780 | 6000000 | 1035600 | 4964400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1443830 | 1094263 | 349567 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1234018 | 144293 | 1089725 | 1244293 | 144293 | 1100000 | 570000 | 570000 | 0 | 258888 | 258888 | 0 | 340000 | 340000 | 0 | 150000 | 0 | 150000 | 127714 | 0 | 127714 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 9360526 | 2676581 | 6683945 | 10637340 | 3017203 | 7620137 | 12343984 | 3180600 | 9163384 | 9360526 | 2676581 | 6683945 | 10637340 | 3017203 | 7620137 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2012 | Q3 | Q3 - 2012 | 1810980 | 570000 | 1240980 | 1669893 | 403047 | 1266846 | 1800000 | 500000 | 1300000 | 7004505 | 1035600 | 5968905 | 5522492 | 776090 | 4746402 | 6000000 | 1000000 | 5000000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1594263 | 1094263 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1213558 | 144293 | 1069265 | 1350000 | 150000 | 1200000 | 570000 | 570000 | 0 | 342188 | 342188 | 0 | 400000 | 400000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 10370868 | 2759881 | 7610987 | 11347230 | 3144263 | 8202967 | 12343984 | 3180600 | 9163384 | 10370868 | 2759881 | 7610987 | 11347230 | 3144263 | 8202967 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2012 | Q4 | Q4 - 2012 | 1810980 | 570000 | 1240980 | 1674807 | 403047 | 1271760 | 1900000 | 403047 | 1496953 | 7004505 | 1035600 | 5968905 | 5569126 | 776090 | 4793036 | 6500000 | 850000 | 5650000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1350491 | 232257 | 1118234 | 1400000 | 250000 | 1150000 | 570000 | 570000 | 0 | 390499 | 390499 | 0 | 450000 | 450000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 175000 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 2200 | 0 | 2200 | 12343984 | 3180600 | 9163384 | 10609860 | 2896156 | 7713704 | 11930167 | 3047310 | 8882857 | 12343984 | 3180600 | 9163384 | 10609860 | 2896156 | 7713704 | 11930167 | 3047310 | 8882857 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2013 | Q1 | Q1 - 2013 | 1810980 | 570000 | 1240980 | 1674807 | 403047 | 1271760 | 1900000 | 403047 | 1496953 | 7004505 | 1035600 | 5968905 | 5569126 | 776090 | 4793036 | 6500000 | 850000 | 5650000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1359988 | 241754 | 1118234 | 1400000 | 250000 | 1150000 | 570000 | 570000 | 0 | 427044 | 427044 | 0 | 450000 | 450000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 175000 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 2200 | 0 | 2200 | 12343984 | 3180600 | 9163384 | 10655902 | 2942198 | 7713704 | 11930167 | 3047310 | 8882857 | 12343984 | 3180600 | 9163384 | 10655902 | 2942198 | 7713704 | 11930167 | 3047310 | 8882857 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2013 | Q2 | Q2 - 2013 | 1810980 | 570000 | 1240980 | 1739898 | 403047 | 1336851 | 1975431 | 403047 | 1572384 | 7004505 | 1035600 | 5968905 | 6280554 | 776090 | 5504464 | 6350000 | 776090 | 5573910 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1453606 | 1094263 | 359343 | 1642500 | 1094263 | 548237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1459636 | 293746 | 1165890 | 1584142 | 377888 | 1206254 | 570000 | 570000 | 0 | 427044 | 427044 | 0 | 570000 | 570000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 168044 | 0 | 168044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50900 | 48575 | 2325 | 50900 | 48575 | 2325 | 12343984 | 3180600 | 9163384 | 11582649 | 3042765 | 8539884 | 12343984 | 3269863 | 9074121 | 12343984 | 3180600 | 9163384 | 11582649 | 3042765 | 8539884 | 12343984 | 3269863 | 9074121 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570118 | INF | 2013 | Q3 | Q3 - 2013 | 1810980 | 570000 | 1240980 | 2340806 | 655259 | 1685547 | 2340806 | 655259 | 1685547 | 7004505 | 1035600 | 5968905 | 6569761 | 798164 | 5771597 | 6569761 | 798164 | 5771597 | 0 | 0 | 0 | 7266 | 4299 | 2967 | 7266 | 4299 | 2967 | 1642500 | 1005000 | 637500 | 1466014 | 1101216 | 364798 | 1466014 | 1101216 | 364798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1505983 | 335877 | 1170106 | 1505983 | 335877 | 1170106 | 570000 | 570000 | 0 | 436482 | 436482 | 0 | 436482 | 436482 | 0 | 150000 | 0 | 150000 | 213523 | 45479 | 168044 | 213523 | 45479 | 168044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66059 | 65734 | 325 | 66059 | 65734 | 325 | 12343984 | 3180600 | 9163384 | 12605894 | 3442510 | 9163384 | 12605894 | 3442510 | 9163384 | 12343984 | 3180600 | 9163384 | 12605894 | 3442510 | 9163384 | 12605894 | 3442510 | 9163384 | 0 | 0 | Nexus Systems, Inc.
NT10BIX5570119 | INF | 2010 | Q4 | Q4 - 2010 | 14259128 | 4277738 | 9981390 | 0 | 0 | 0 | 12237736 | 3671321 | 8566415 | 66228948 | 19868684 | 46360264 | 0 | 0 | 0 | 4850000 | 1455000 | 3395000 | 1485174 | 445552 | 1039622 | 433932 | 130180 | 303752 | 125000 | 37500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 94174 | 28252 | 65922 | 1021647 | 306494 | 715153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 528106 | 158432 | 369674 | 18234383 | 5470315 | 12764068 | 94963210 | 28488963 | 66474247 | 528106 | 158432 | 369674 | 18234383 | 5470315 | 12764068 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2011 | Q1 | Q1 - 2011 | 14259128 | 4277738 | 9981390 | 843221 | 252966 | 590255 | 1843221 | 552966 | 1290254 | 66228948 | 19868684 | 46360264 | 0 | 0 | 0 | 1144482 | 343345 | 801137 | 1485174 | 445552 | 1039622 | 694620 | 208386 | 486234 | 1101877 | 330563 | 771314 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 331429 | 99429 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 472496 | 141749 | 330747 | 1141230 | 342369 | 798861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 2111637 | 633491 | 1478146 | 5562239 | 1668672 | 3893566 | 94963210 | 28488963 | 66474247 | 2111637 | 633491 | 1478146 | 5562239 | 1668672 | 3893566 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2011 | Q2 | Q2 - 2011 | 14259128 | 4277738 | 9981390 | 843221 | 252966 | 590254 | 6225223 | 1867567 | 4357656 | 66228948 | 19868684 | 46360264 | 265635 | 79690 | 185945 | 5694346 | 1708304 | 3986042 | 1485174 | 445552 | 1039622 | 1019324 | 305797 | 713527 | 1167842 | 350353 | 817489 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 1398213 | 419464 | 978749 | 4512224 | 1353667 | 3158557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 3627693 | 1088307 | 2539385 | 17700935 | 5310281 | 12390654 | 94963210 | 28488963 | 66474247 | 3627693 | 1088307 | 2539385 | 17700935 | 5310281 | 12390654 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2011 | Q3 | Q3 - 2011 | 14259128 | 4277738 | 9981390 | 882486 | 264746 | 617740 | 11587719 | 3476316 | 8111403 | 66228948 | 19868684 | 46360264 | 5368691 | 1610607 | 3758084 | 16627612 | 4988283 | 11639329 | 1485174 | 445552 | 1039622 | 1217025 | 365108 | 851917 | 1365542 | 409663 | 955879 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 3281594 | 984478 | 2297116 | 5617102 | 1685130 | 3931972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 10851096 | 3255329 | 7595767 | 35299275 | 10589782 | 24709493 | 94963210 | 28488963 | 66474247 | 10851096 | 3255329 | 7595767 | 35299275 | 10589782 | 24709493 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2011 | Q4 | Q4 - 2011 | 14259128 | 4277738 | 9981390 | 10228544 | 3068563 | 7159981 | 13148153 | 3944446 | 9203707 | 66228948 | 19868684 | 46360264 | 13279164 | 3983749 | 9295415 | 33147849 | 9944355 | 23203494 | 1485174 | 445552 | 1039622 | 1374407 | 412322 | 962085 | 1493221 | 447966 | 1045255 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 4939721 | 1481916 | 3457805 | 6107475 | 1832242 | 4275233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 29923136 | 8976940 | 20946196 | 53997998 | 16199399 | 37798599 | 94963210 | 28488963 | 66474247 | 29923136 | 8976940 | 20946196 | 53997998 | 16199399 | 37798599 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2012 | Q1 | Q1 - 2012 | 14259128 | 4277738 | 9981390 | 10375930 | 3112779 | 7263150 | 12895929 | 3868779 | 9027150 | 66228948 | 19868684 | 46360264 | 27413608 | 8224082 | 19189526 | 40064491 | 12019347 | 28045144 | 1485174 | 445552 | 1039622 | 1559248 | 467774 | 1091474 | 1679248 | 503774 | 1175474 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 6741131 | 2022339 | 4718792 | 7629327 | 2288798 | 5340529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 1197134 | 359140 | 837994 | 94963210 | 28488963 | 66474247 | 46191217 | 13857364 | 32333852 | 63567429 | 19070228 | 44497201 | 94963210 | 28488963 | 66474247 | 46191217 | 13857364 | 32333852 | 63567429 | 19070228 | 44497201 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2012 | Q2 | Q2 - 2012 | 14259128 | 4277738 | 9981390 | 12367552 | 3710266 | 8657286 | 14867552 | 4460266 | 10407286 | 66228948 | 19868684 | 46360264 | 34395988 | 10318796 | 24077192 | 44395988 | 13318796 | 31077192 | 1485174 | 445552 | 1039622 | 2086676 | 626003 | 1460673 | 2236676 | 671003 | 1565673 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8141090 | 2442327 | 5698763 | 8641090 | 2592327 | 6048763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 1608995 | 482698 | 1126297 | 94963210 | 28488963 | 66474247 | 57092606 | 17127782 | 39964824 | 71851601 | 21555480 | 50296121 | 94963210 | 28488963 | 66474247 | 57092606 | 17127782 | 39964824 | 71851601 | 21555480 | 50296121 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2012 | Q3 | Q3 - 2012 | 14259128 | 4277738 | 9981390 | 14242099 | 4272630 | 9969469 | 15242099 | 4572630 | 10669468 | 66228948 | 19868684 | 46360264 | 45980808 | 13794242 | 32186566 | 54980808 | 16494242 | 38486566 | 1485174 | 445552 | 1039622 | 1861428 | 558428 | 1303000 | 1891428 | 567428 | 1324000 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8741121 | 2622336 | 6118785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428540 | 999923 | 1608995 | 482699 | 1126297 | 94963210 | 28488963 | 66474247 | 72305219 | 21691566 | 50613653 | 82565751 | 24769725 | 57796026 | 94963210 | 28488963 | 66474247 | 72305219 | 21691566 | 50613653 | 82565751 | 24769725 | 57796026 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2012 | Q4 | Q4 - 2012 | 14259128 | 4277738 | 9981390 | 14706494 | 4411948 | 10294546 | 15476494 | 4642948 | 10833545 | 66228948 | 19868684 | 46360264 | 56017094 | 16805128 | 39211966 | 60517094 | 18155128 | 42361966 | 1485174 | 445552 | 1039622 | 2030191 | 609057 | 1421134 | 2130191 | 639057 | 1491134 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8741121 | 2622336 | 6118785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428539 | 999924 | 1608995 | 482699 | 1126297 | 94963210 | 28488963 | 66474247 | 82974663 | 24892398 | 58082265 | 88575195 | 26572558 | 62002637 | 94963210 | 28488963 | 66474247 | 82974663 | 24892398 | 58082265 | 88575195 | 26572558 | 62002637 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2013 | Q1 | Q1 - 2013 | 14259128 | 4277738 | 9981390 | 15062742 | 4518823 | 10543919 | 15762742 | 4728823 | 11033919 | 66228948 | 19868684 | 46360264 | 62204332 | 18661300 | 43543032 | 63704332 | 19111300 | 44593032 | 1485174 | 445552 | 1039622 | 2095643 | 628693 | 1466950 | 2145643 | 643693 | 1501950 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8691121 | 2607336 | 6083785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428539 | 999924 | 1608995 | 482698 | 1126297 | 94963210 | 28488963 | 66474247 | 89583601 | 26875081 | 62708520 | 92014133 | 27604240 | 64409893 | 94963210 | 28488963 | 66474247 | 89583601 | 26875081 | 62708520 | 92014133 | 27604240 | 64409893 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2013 | Q2 | Q2 - 2013 | 14259128 | 4277738 | 9981390 | 15133437 | 4589518 | 10543919 | 15938437 | 5394518 | 10543919 | 66228948 | 19868684 | 46360264 | 64410453 | 19363482 | 45046971 | 65610453 | 20563482 | 45046971 | 1485174 | 445552 | 1039622 | 2326769 | 698031 | 1628738 | 2376769 | 748031 | 1628738 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8691121 | 2607336 | 6083785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 95091543 | 28617296 | 66474247 | 97146543 | 30672296 | 66474247 | 94963210 | 28488963 | 66474247 | 95091543 | 28617296 | 66474247 | 97146543 | 30672296 | 66474247 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2013 | Q3 | Q3 - 2013 | 14259128 | 4277738 | 9981390 | 15227797 | 4683878 | 10543919 | 16811672 | 6267753 | 10543919 | 66228948 | 19868684 | 46360264 | 68801320 | 23754349 | 45046971 | 69337048 | 24290077 | 45046971 | 1485174 | 445552 | 1039622 | 2385094 | 756356 | 1628738 | 2650000 | 1021262 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8792421 | 2637726 | 6154695 | 8792421 | 2637726 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 99635095 | 33160848 | 66474247 | 102019604 | 35545357 | 66474247 | 94963210 | 28488963 | 66474247 | 99635095 | 33160848 | 66474247 | 102019604 | 35545357 | 66474247 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2013 | Q4 | Q4 - 2013 | 14259128 | 4277738 | 9981390 | 16059090 | 5515171 | 10543919 | 16859090 | 6315171 | 10543919 | 66228948 | 19868684 | 46360264 | 70032061 | 24985090 | 45046971 | 70282061 | 25235090 | 45046971 | 1485174 | 445552 | 1039622 | 2430662 | 801924 | 1628738 | 2480663 | 851925 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8792421 | 2637726 | 6154695 | 8792421 | 2637726 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428493 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 101742697 | 35268450 | 66474247 | 102842728 | 36368451 | 66474247 | 94963210 | 28488963 | 66474247 | 101742697 | 35268450 | 66474247 | 102842728 | 36368451 | 66474247 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2014 | Q1 | Q1 - 2014 | 14259128 | 4277738 | 9981390 | 16492941 | 5949022 | 10543919 | 16492941 | 5949022 | 10543919 | 66228948 | 19868684 | 46360264 | 71351161 | 26304190 | 45046971 | 71601161 | 26554190 | 45046971 | 1485174 | 445552 | 1039622 | 2473445 | 844707 | 1628738 | 2523446 | 894708 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8792421 | 2637726 | 6154695 | 8792421 | 2637726 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 103538431 | 37064184 | 66474247 | 103838432 | 37364185 | 66474247 | 94963210 | 28488963 | 66474247 | 103538431 | 37064184 | 66474247 | 103838432 | 37364185 | 66474247 | 0 | 0 | Horizon Telecom, Inc.
NT10BIX5570119 | INF | 2014 | Q2 | Q2 - 2014 | 14259128 | 4277738 | 9981390 | 19032118 | 8488199 | 10543919 | 19032118 | 8488199 | 10543919 | 66228948 | 19868684 | 46360264 | 65092036 | 20045065 | 45046971 | 65092036 | 20045065 | 45046971 | 1485174 | 445552 | 1039622 | 2765550 | 1136812 | 1628738 | 2765550 | 1136812 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 9697872 | 3543177 | 6154695 | 9697872 | 3543177 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 101016039 | 34541792 | 66474247 | 101016039 | 34541792 | 66474247 | 94963210 | 28488963 | 66474247 | 101016039 | 34541792 | 66474247 | 101016039 | 34541792 | 66474247 | 0 | 1257786 | Horizon Telecom, Inc.
NT10BIX5570120 | INF | 2010 | Q4 | Q4 - 2010 | 6971935 | 1693210 | 5278725 | 4585 | 1114 | 3471 | 4585 | 1114 | 3471 | 87329001 | 25240320 | 62088681 | 12160 | 2953 | 9207 | 12160 | 2953 | 9207 | 757080 | 183865 | 573215 | 572625 | 139068 | 433557 | 640080 | 155450 | 484630 | 3401000 | 1363539 | 2037461 | 0 | 0 | 0 | 470000 | 114145 | 355855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 187280 | 45483 | 141797 | 3300663 | 801602 | 2499061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 100000 | 24286 | 75714 | 106091969 | 30334680 | 75757289 | 776650 | 188618 | 588032 | 4527488 | 1099550 | 3427938 | 106091969 | 30334680 | 75757289 | 776650 | 188618 | 588032 | 4527488 | 1099550 | 3427938 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2011 | Q1 | Q1 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 47006 | 11416 | 35590 | 85037468 | 24683797 | 60353671 | 34025 | 8263 | 25762 | 4394274 | 1067197 | 3327077 | 757080 | 183865 | 573215 | 595054 | 144516 | 450538 | 670054 | 162730 | 507324 | 5692533 | 1920062 | 3772471 | 46978 | 11409 | 35569 | 441978 | 107339 | 334639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 1887752 | 458461 | 1429291 | 4255352 | 1033459 | 3221893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 100000 | 24286 | 75714 | 106091969 | 30334680 | 75757289 | 2610815 | 634065 | 1976750 | 9908664 | 2406427 | 7502237 | 106091969 | 30334680 | 75757289 | 2610815 | 634065 | 1976750 | 9908664 | 2406427 | 7502237 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2011 | Q2 | Q2 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 297006 | 72131 | 224875 | 85037468 | 24683797 | 60353671 | 4849166 | 3661089 | 1188077 | 8598716 | 4571708 | 4027008 | 757080 | 183865 | 573215 | 696990 | 191986 | 505004 | 800000 | 194289 | 605711 | 5692533 | 1920062 | 3772471 | 127796 | 31037 | 96759 | 427796 | 103895 | 323901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 3045045 | 739522 | 2305523 | 4545000 | 1103803 | 3441197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 8766003 | 4635050 | 4130953 | 14868518 | 6094398 | 8774120 | 106091969 | 30334680 | 75757289 | 8766003 | 4635050 | 4130953 | 14868518 | 6094398 | 8774120 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2011 | Q3 | Q3 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 47006 | 11416 | 35590 | 85037468 | 24683797 | 60353671 | 6738932 | 3889849 | 2849083 | 15000000 | 6126329 | 8873671 | 757080 | 183865 | 573215 | 742946 | 180432 | 562514 | 792946 | 192576 | 600370 | 5692533 | 1920062 | 3772471 | 261155 | 63424 | 197731 | 522310 | 126849 | 395461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 3713805 | 901938 | 2811867 | 4500000 | 1092874 | 3407126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 129975 | 31566 | 98409 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 11633819 | 5078625 | 6555194 | 21062262 | 7598616 | 13463646 | 106091969 | 30334680 | 75757289 | 11633819 | 5078625 | 6555194 | 21062262 | 7598616 | 13463646 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2011 | Q4 | Q4 - 2011 | 6971935 | 1693210 | 5278725 | 68019 | 16519 | 51500 | 100000 | 24286 | 75714 | 85037468 | 24683797 | 60353671 | 17531320 | 6741088 | 10790232 | 28400000 | 9380665 | 19019335 | 757080 | 183865 | 573215 | 823518 | 200000 | 623518 | 845000 | 205217 | 639783 | 5692533 | 1920062 | 3772471 | 405324 | 166649 | 238675 | 1250000 | 371788 | 878212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 4745461 | 1152487 | 3592974 | 5393000 | 1309749 | 4083251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 158214 | 38424 | 119790 | 185000 | 44929 | 140071 | 106091969 | 30334680 | 75757289 | 23731856 | 8315167 | 15416689 | 36173000 | 11336634 | 24836366 | 106091969 | 30334680 | 75757289 | 23731856 | 8315167 | 15416689 | 36173000 | 11336634 | 24836366 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2012 | Q1 | Q1 - 2012 | 6971935 | 1693210 | 5278725 | 73552 | 17863 | 55689 | 4500000 | 1092874 | 3407126 | 85037468 | 24683797 | 60353671 | 32909457 | 12451600 | 20457857 | 47909457 | 16094514 | 31814943 | 757080 | 183865 | 573215 | 884166 | 214729 | 669437 | 925000 | 224646 | 700354 | 5692533 | 1920062 | 3772471 | 1157311 | 354347 | 802964 | 5000000 | 1287586 | 3712414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5454850 | 1324770 | 4130080 | 6500000 | 1578596 | 4921404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 186365 | 45261 | 141104 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 40665701 | 14408570 | 26257131 | 65034457 | 20326788 | 44707669 | 106091969 | 30334680 | 75757289 | 40665701 | 14408570 | 26257131 | 65034457 | 20326788 | 44707669 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2012 | Q2 | Q2 - 2012 | 6971935 | 1693210 | 5278725 | 4321486 | 1049520 | 3271966 | 6000000 | 1457165 | 4542835 | 85037468 | 24683797 | 60353671 | 50698471 | 17214320 | 33484151 | 65698471 | 20857233 | 44841238 | 757080 | 183865 | 573215 | 941811 | 228729 | 713082 | 996811 | 242086 | 754725 | 5692533 | 1920062 | 3772471 | 2911273 | 808252 | 2103021 | 5692533 | 1483712 | 4208821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5278479 | 1281936 | 3996543 | 6000000 | 1457165 | 4542835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 303845 | 73792 | 230053 | 350000 | 85001 | 264999 | 106091969 | 30334680 | 75757289 | 64455365 | 20656549 | 43798816 | 84737815 | 25582362 | 59155453 | 106091969 | 30334680 | 75757289 | 64455365 | 20656549 | 43798816 | 84737815 | 25582362 | 59155453 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2012 | Q3 | Q3 - 2012 | 6971935 | 1693210 | 5278725 | 5224988 | 1268945 | 3956043 | 6000000 | 1457165 | 4542835 | 85037468 | 24683797 | 60353671 | 63261929 | 20265492 | 42996437 | 74000000 | 22873349 | 51126651 | 757080 | 183865 | 573215 | 962773 | 233820 | 728953 | 975000 | 236789 | 738211 | 5692533 | 1920062 | 3772471 | 3335470 | 911273 | 2424197 | 5000000 | 1315522 | 3684478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5380422 | 1306694 | 4073728 | 5600000 | 1360021 | 4239979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 288107 | 69970 | 218137 | 308000 | 74801 | 233199 | 106091969 | 30334680 | 75757289 | 78453689 | 24056194 | 54397495 | 91883000 | 27317647 | 64565353 | 106091969 | 30334680 | 75757289 | 78453689 | 24056194 | 54397495 | 91883000 | 27317647 | 64565353 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2012 | Q4 | Q4 - 2012 | 6971935 | 1693210 | 5278725 | 5729521 | 1391476 | 4338045 | 6250000 | 1517881 | 4732119 | 85037468 | 24683797 | 60353671 | 74049369 | 22885339 | 51164030 | 81851354 | 24289020 | 57562334 | 757080 | 183865 | 573215 | 994371 | 241494 | 752877 | 1000000 | 242861 | 757139 | 5692533 | 1920062 | 3772471 | 3966714 | 1121923 | 2844791 | 5000000 | 1372867 | 3627133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5540730 | 1345626 | 4195104 | 6000000 | 1457165 | 4542835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 300242 | 72917 | 227325 | 350000 | 85001 | 264999 | 106091969 | 30334680 | 75757289 | 90580947 | 27058775 | 63522172 | 100451354 | 28964795 | 71486559 | 106091969 | 30334680 | 75757289 | 90580947 | 27058775 | 63522172 | 100451354 | 28964795 | 71486559 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2013 | Q1 | Q1 - 2013 | 6971935 | 1693210 | 5278725 | 6184646 | 1502008 | 4682638 | 6971935 | 1693210 | 5278725 | 85037468 | 24683797 | 60353671 | 79721744 | 23312532 | 56409212 | 86500000 | 24958705 | 61541295 | 757080 | 183865 | 573215 | 998780 | 242565 | 756215 | 1000000 | 242861 | 757139 | 5692533 | 1920062 | 3772471 | 4931473 | 1815514 | 3115959 | 5000000 | 1832157 | 3167843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5590114 | 1357620 | 4232494 | 5700000 | 1384307 | 4315693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 302736 | 73523 | 229213 | 370000 | 89859 | 280141 | 106091969 | 30334680 | 75757289 | 97729493 | 28303762 | 69425731 | 105549140 | 30202849 | 75346291 | 106091969 | 30334680 | 75757289 | 97729493 | 28303762 | 69425731 | 105549140 | 30202849 | 75346291 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2013 | Q2 | Q2 - 2013 | 6971935 | 1693210 | 5278725 | 7682670 | 1865820 | 5816850 | 7682670 | 1865820 | 5816850 | 85037468 | 24683797 | 60353671 | 83296661 | 24180739 | 59115922 | 86533094 | 24966742 | 61566352 | 757080 | 183865 | 573215 | 1015775 | 246692 | 769083 | 1022000 | 248204 | 773796 | 5692533 | 1920062 | 3772471 | 4945821 | 1818999 | 3126822 | 4946000 | 1819042 | 3126958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5544068 | 1346437 | 4197631 | 5575000 | 1353949 | 4221051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 305882 | 74287 | 231595 | 326000 | 79173 | 246827 | 106091969 | 30334680 | 75757289 | 102798082 | 29534724 | 73263358 | 106091969 | 30334680 | 75757289 | 106091969 | 30334680 | 75757289 | 102798082 | 29534724 | 73263358 | 106091969 | 30334680 | 75757289 | 0 | 0 | MCNC
NT10BIX5570120 | INF | 2013 | Q3 | Q3 - 2013 | 6971935 | 1693210 | 5278725 | 7820412 | 1899272 | 5921140 | 7820412 | 1899272 | 5921140 | 87329001 | 25240320 | 62088681 | 84959325 | 24584535 | 60374790 | 84959325 | 24584535 | 60374790 | 757080 | 183865 | 573215 | 1064529 | 258532 | 805997 | 1064529 | 258532 | 805997 | 3401000 | 1363539 | 2037461 | 4944441 | 1818664 | 3125777 | 4944441 | 1818664 | 3125777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5722349 | 1389735 | 4332614 | 5722349 | 1389735 | 4332614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 336402 | 81699 | 254703 | 336402 | 81699 | 254703 | 106091969 | 30334680 | 75757289 | 104854663 | 30034187 | 74820476 | 104854663 | 30034187 | 74820476 | 106091969 | 30334680 | 75757289 | 104854663 | 30034187 | 74820476 | 104854663 | 30034187 | 74820476 | 0 | 0 | MCNC
NT10BIX5570122 | INF | 2010 | Q4 | Q4 - 2010 | 21503295 | 6000000 | 15503295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 1020215 | 0 | 1020215 | 1433138 | 0 | 1433138 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 0 | 0 | 0 | 212000 | 0 | 212000 | 1539000 | 0 | 1539000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 1020215 | 0 | 1020215 | 1645138 | 0 | 1645138 | 34149665 | 10456000 | 23693665 | 1020215 | 0 | 1020215 | 1645138 | 0 | 1645138 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2011 | Q1 | Q1 - 2011 | 21503295 | 6000000 | 15503295 | 0 | 0 | 0 | 3040000 | 0 | 3040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 638576 | 0 | 638576 | 712808 | 0 | 712808 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 779883 | 0 | 779883 | 1603338 | 0 | 1603338 | 1539000 | 0 | 1539000 | 115318 | 0 | 115318 | 191318 | 0 | 191318 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 60438 | 60438 | 0 | 60438 | 60438 | 0 | 34149665 | 10456000 | 23693665 | 1594215 | 60438 | 1533777 | 5607902 | 60438 | 5547464 | 34149665 | 10456000 | 23693665 | 1594215 | 60438 | 1533777 | 5607902 | 60438 | 5547464 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2011 | Q2 | Q2 - 2011 | 21503295 | 6000000 | 15503295 | 2045000 | 1445000 | 600000 | 4950400 | 2150400 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 678064 | 0 | 678064 | 1074279 | 0 | 1074279 | 816370 | 456000 | 360370 | 425000 | 425000 | 0 | 481000 | 425000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1249638 | 0 | 1249638 | 1823362 | 0 | 1823362 | 1539000 | 0 | 1539000 | 163002 | 0 | 163002 | 189179 | 0 | 189179 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 1959000 | 1959000 | 0 | 2818438 | 2818438 | 0 | 34149665 | 10456000 | 23693665 | 6519704 | 3829000 | 2690704 | 11336658 | 5393838 | 5942820 | 34149665 | 10456000 | 23693665 | 6519704 | 3829000 | 2690704 | 11336658 | 5393838 | 5942820 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2011 | Q3 | Q3 - 2011 | 21503295 | 6000000 | 15503295 | 6198353 | 3993353 | 2205000 | 13823209 | 4105343 | 9717866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 858329 | 0 | 858329 | 1069018 | 0 | 1069018 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 456000 | 456000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1524529 | 0 | 1524529 | 2579362 | 0 | 2579362 | 1539000 | 0 | 1539000 | 191627 | 0 | 191627 | 544229 | 0 | 544229 | 450000 | 0 | 450000 | 0 | 0 | 0 | 190085 | 0 | 190085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 1541057 | 1541057 | 0 | 2913423 | 2913423 | 0 | 34149665 | 10456000 | 23693665 | 10769895 | 5990410 | 4779485 | 21575326 | 7474766 | 14100560 | 34149665 | 10456000 | 23693665 | 10769895 | 5990410 | 4779485 | 21575326 | 7474766 | 14100560 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2011 | Q4 | Q4 - 2011 | 21503295 | 6000000 | 15503295 | 10292030 | 4063354 | 6228676 | 15425037 | 4105343 | 11319694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 1050738 | 0 | 1050738 | 1168833 | 0 | 1168833 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1758948 | 0 | 1758948 | 2804361 | 0 | 2804361 | 1539000 | 0 | 1539000 | 278277 | 0 | 278277 | 899279 | 0 | 899279 | 450000 | 0 | 450000 | 0 | 0 | 0 | 315810 | 0 | 315810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 2913423 | 2913423 | 0 | 4000000 | 4000000 | 0 | 34149665 | 10456000 | 23693665 | 16749416 | 7432777 | 9316639 | 25429690 | 8561343 | 16868347 | 34149665 | 10456000 | 23693665 | 16749416 | 7432777 | 9316639 | 25429690 | 8561343 | 16868347 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2012 | Q1 | Q1 - 2012 | 18632393 | 5662097 | 12970296 | 11638300 | 3337165 | 8301135 | 14070359 | 3379154 | 10691205 | 3259189 | 726190 | 2532999 | 1040285 | 726189 | 314096 | 1988845 | 726189 | 1262656 | 1750000 | 0 | 1750000 | 1163268 | 0 | 1163268 | 1333068 | 0 | 1333068 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 456000 | 456000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2257743 | 0 | 2257743 | 2789794 | 0 | 2789794 | 1539000 | 0 | 1539000 | 431515 | 0 | 431515 | 902623 | 0 | 902623 | 450000 | 0 | 450000 | 0 | 0 | 0 | 276870 | 0 | 276870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611713 | 3611713 | 0 | 2913423 | 2913423 | 0 | 3266765 | 3266765 | 0 | 34149665 | 10456000 | 23693665 | 19900534 | 7432777 | 12467757 | 25084324 | 7828108 | 17256216 | 34149665 | 10456000 | 23693665 | 19900534 | 7432777 | 12467757 | 25084324 | 7828108 | 17256216 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2012 | Q2 | Q2 - 2012 | 18632393 | 5662097 | 12970296 | 11089046 | 1720000 | 9369046 | 11089046 | 1720000 | 9369046 | 3259189 | 726190 | 2532999 | 726189 | 726189 | 0 | 1373980 | 1373980 | 0 | 1750000 | 0 | 1750000 | 1256804 | 0 | 1256804 | 1389833 | 0 | 1389833 | 816370 | 456000 | 360370 | 4307637 | 4307637 | 0 | 5495637 | 5495637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2547034 | 0 | 2547034 | 3011421 | 0 | 3011421 | 1539000 | 0 | 1539000 | 589981 | 0 | 589981 | 906040 | 0 | 906040 | 450000 | 0 | 450000 | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611713 | 3611713 | 0 | 421782 | 421782 | 0 | 421782 | 421782 | 0 | 34149665 | 10456000 | 23693665 | 20938473 | 7175608 | 13762865 | 23726739 | 9011399 | 14715340 | 34149665 | 10456000 | 23693665 | 20938473 | 7175608 | 13762865 | 23726739 | 9011399 | 14715340 | 0 | 9998 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2012 | Q3 | Q3 - 2012 | 17127343 | 4157048 | 12970295 | 9450660 | 0 | 9450660 | 9840799 | 337415 | 9503384 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 752530 | 752530 | 0 | 1750000 | 0 | 1750000 | 1344387 | 0 | 1344387 | 1607672 | 0 | 1607672 | 816370 | 456000 | 360370 | 4307637 | 3586800 | 0 | 6497315 | 6497315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2814206 | 0 | 2814206 | 3325105 | 0 | 3325105 | 1539000 | 0 | 1539000 | 638345 | 0 | 638345 | 1022784 | 0 | 1022784 | 450000 | 0 | 450000 | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 421782 | 0 | 0 | 594707 | 594707 | 0 | 34149665 | 10456000 | 23693665 | 18977017 | 3586800 | 14247598 | 23679912 | 8181967 | 15497945 | 34149665 | 10456000 | 23693665 | 18977017 | 3586800 | 14247598 | 23679912 | 8181967 | 15497945 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2012 | Q4 | Q4 - 2012 | 17127343 | 4157048 | 12970295 | 10250482 | 0 | 10250482 | 10818568 | 0 | 10818568 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 1834586 | 0 | 1834586 | 1750000 | 0 | 1750000 | 1612448 | 0 | 1612448 | 1826950 | 0 | 1826950 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 4900000 | 4900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3487187 | 0 | 3487187 | 1539000 | 0 | 1539000 | 1068267 | 0 | 1068267 | 1687716 | 0 | 1687716 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3589608 | 3589608 | 0 | 3589608 | 3589608 | 0 | 34149665 | 10456000 | 23693665 | 22990979 | 7176408 | 15814571 | 28144615 | 8489608 | 19655007 | 34149665 | 10456000 | 23693665 | 22990979 | 7176408 | 15814571 | 28144615 | 8489608 | 19655007 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2013 | Q1 | Q1 - 2013 | 17127343 | 4157048 | 12970295 | 10275510 | 0 | 10275510 | 10693063 | 0 | 10693063 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 1622639 | 0 | 1622639 | 1750000 | 0 | 1750000 | 1726371 | 0 | 1726371 | 2221949 | 0 | 2221948 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 3586800 | 3586800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3068074 | 0 | 3068074 | 1539000 | 0 | 1539000 | 1726546 | 0 | 1726546 | 2550000 | 0 | 2550000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 83997 | 0 | 83997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3588808 | 3588808 | 0 | 3791036 | 3588808 | 202228 | 34149665 | 10456000 | 23693665 | 23787409 | 7175608 | 16611801 | 27617558 | 7175608 | 20441949 | 34149665 | 10456000 | 23693665 | 23787409 | 7175608 | 16611801 | 27617558 | 7175608 | 20441949 | 0 | 9998 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2013 | Q2 | Q2 - 2013 | 17127343 | 4157048 | 12970295 | 10631598 | 0 | 10631598 | 10693063 | 0 | 10693063 | 4375952 | 1842952 | 2533000 | 56160 | 0 | 56160 | 1622639 | 0 | 1622639 | 1750000 | 0 | 1750000 | 2133085 | 0 | 2133085 | 2221948 | 0 | 2221948 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 3586800 | 3586800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3068074 | 0 | 3068074 | 1539000 | 0 | 1539000 | 2560667 | 0 | 2560667 | 2550667 | 0 | 2550667 | 450000 | 0 | 450000 | 0 | 0 | 0 | 83997 | 0 | 83997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3588808 | 3588808 | 0 | 5636036 | 5433808 | 202228 | 34149665 | 10456000 | 23693665 | 25440492 | 7175608 | 18264884 | 29463224 | 9020608 | 20442616 | 34149665 | 10456000 | 23693665 | 25440492 | 7175608 | 18264884 | 29463224 | 9020608 | 20442616 | 0 | 9998 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2013 | Q3 | Q3 - 2013 | 20145569 | 8960000 | 11185569 | 18032569 | 7175608 | 10856961 | 20145569 | 8960000 | 11185569 | 4762182 | 1221000 | 3541182 | 401698 | 0 | 401698 | 4762182 | 1221000 | 3541182 | 3853561 | 275000 | 3578561 | 2505967 | 0 | 2505967 | 3853561 | 275000 | 3578561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 2916958 | 0 | 2916958 | 3058759 | 0 | 3058759 | 2224594 | 0 | 2224594 | 2996931 | 0 | 2996931 | 2224594 | 0 | 2224594 | 105000 | 0 | 105000 | 11400 | 0 | 11400 | 105000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 26865523 | 7175608 | 19689915 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 26865523 | 7175608 | 19689915 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2013 | Q4 | Q4 - 2013 | 20145569 | 8960000 | 11185569 | 18221364 | 7175608 | 11045756 | 20145569 | 8960000 | 11185569 | 4762182 | 1221000 | 3541182 | 1797652 | 0 | 1797652 | 4424593 | 1221000 | 3203593 | 3853561 | 275000 | 3578561 | 2708697 | 0 | 2708697 | 3183697 | 275000 | 2908697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 3224598 | 0 | 3224598 | 3224598 | 0 | 3224598 | 2224594 | 0 | 2224594 | 3066208 | 0 | 3066208 | 3066208 | 0 | 3066208 | 105000 | 0 | 105000 | 47923 | 0 | 47923 | 105000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 29066442 | 7175608 | 21890834 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 29066442 | 7175608 | 21890834 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2014 | Q1 | Q1 - 2014 | 20145569 | 8960000 | 11185569 | 21100564 | 9887882 | 11212682 | 21393682 | 10181000 | 11212682 | 4762182 | 1221000 | 3541182 | 2042416 | 0 | 2042416 | 2428174 | 0 | 2428174 | 3853561 | 275000 | 3578561 | 3196541 | 275000 | 2921541 | 3275000 | 275000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 3720048 | 0 | 3720048 | 3920048 | 0 | 3920048 | 2224594 | 0 | 2224594 | 3084838 | 0 | 3084838 | 3084838 | 0 | 3084838 | 105000 | 0 | 105000 | 47923 | 0 | 47923 | 47923 | 0 | 47923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 33192330 | 10162882 | 23029448 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 33192330 | 10162882 | 23029448 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570122 | INF | 2014 | Q2 | Q2 - 2014 | 20145569 | 8960000 | 11185569 | 21674260 | 10181000 | 11493260 | 21674260 | 10181000 | 11493260 | 4762182 | 1221000 | 3541182 | 2278874 | 0 | 2278874 | 2278874 | 0 | 2278874 | 3853561 | 275000 | 3578561 | 3340461 | 275000 | 3065461 | 3340461 | 275000 | 3065461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 3722548 | 0 | 3722548 | 3722548 | 0 | 3722548 | 2224594 | 0 | 2224594 | 3085599 | 0 | 3085599 | 3085599 | 0 | 3085599 | 105000 | 0 | 105000 | 47923 | 0 | 47923 | 47923 | 0 | 47923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC
NT10BIX5570123 | INF | 2010 | Q4 | Q4 - 2010 | 680684 | 28300 | 652384 | 0 | 0 | 0 | 60000 | 0 | 60000 | 453000 | 0 | 453000 | 0 | 0 | 0 | 0 | 0 | 0 | 440022 | 257377 | 182645 | 8184 | 4733 | 3451 | 22259 | 9433 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 229750 | 0 | 229750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 51143 | 51143 | 0 | 51000 | 51000 | 0 | 2282589 | 713480 | 1569109 | 59327 | 55876 | 3451 | 136769 | 60433 | 76336 | 2282589 | 713480 | 1569109 | 59327 | 55876 | 3451 | 136769 | 60433 | 76336 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2011 | Q1 | Q1 - 2011 | 680684 | 28300 | 652384 | 58962 | 0 | 58962 | 58548 | 0 | 58548 | 453000 | 0 | 453000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 440022 | 257377 | 182645 | 22203 | 7533 | 14670 | 31575 | 12033 | 43608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 229750 | 0 | 229750 | 0 | 0 | 0 | 212950 | 0 | 212950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 106690 | 106690 | 0 | 50815 | 50815 | 0 | 2282589 | 713480 | 1569109 | 187855 | 114223 | 73632 | 417398 | 62848 | 378616 | 2282589 | 713480 | 1569109 | 187855 | 114223 | 73632 | 417398 | 62848 | 378616 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2011 | Q2 | Q2 - 2011 | 680688 | 28300 | 652388 | 58962 | 0 | 58962 | 242487 | 0 | 242487 | 731555 | 85953 | 645602 | 25139 | 15116 | 10023 | 177483 | 19365 | 158118 | 238263 | 171424 | 66839 | 18099 | 5689 | 12410 | 26853 | 8797 | 18056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3612 | 0 | 3612 | 152950 | 0 | 152950 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 93418 | 93418 | 0 | 153418 | 129678 | 23740 | 2282589 | 713480 | 1569109 | 195618 | 114223 | 81395 | 703853 | 157840 | 546013 | 2282589 | 713480 | 1569109 | 195618 | 114223 | 81395 | 703853 | 157840 | 546013 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2011 | Q3 | Q3 - 2011 | 680688 | 28300 | 652388 | 293905 | 0 | 293905 | 420536 | 70536 | 321700 | 731555 | 85953 | 645602 | 58129 | 25449 | 32680 | 615499 | 35799 | 579700 | 238263 | 171424 | 66839 | 60227 | 9961 | 50266 | 78500 | 11661 | 66839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 152950 | 0 | 152950 | 65596 | 0 | 65596 | 152950 | 0 | 152950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 150897 | 150897 | 0 | 185639 | 163900 | 21739 | 2282589 | 713480 | 1569109 | 628754 | 186307 | 442447 | 1456634 | 281896 | 1146438 | 2282589 | 713480 | 1569109 | 628754 | 186307 | 442447 | 1456634 | 281896 | 1146438 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2011 | Q4 | Q4 - 2011 | 680688 | 28300 | 652388 | 356788 | 24635 | 332153 | 442843 | 53189 | 389634 | 731555 | 85953 | 645602 | 572147 | 34646 | 537501 | 686147 | 43646 | 642501 | 238263 | 171424 | 66839 | 95117 | 24606 | 70511 | 117317 | 34806 | 82511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 3612 | 0 | 3612 | 8650 | 0 | 8650 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 113414 | 0 | 113414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 222017 | 188429 | 33588 | 267017 | 223429 | 43588 | 2282589 | 713480 | 1569109 | 1329429 | 272316 | 1057113 | 1635388 | 355070 | 1280298 | 2282589 | 713480 | 1569109 | 1329429 | 272316 | 1057113 | 1635388 | 355070 | 1280298 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2012 | Q1 | Q1 - 2012 | 680688 | 28300 | 652388 | 468544 | 47189 | 421355 | 478544 | 47189 | 431355 | 731555 | 85953 | 645602 | 753919 | 35625 | 718294 | 833803 | 55625 | 778178 | 238263 | 171424 | 66839 | 117249 | 37229 | 80020 | 152368 | 61948 | 90420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 144748 | 0 | 144748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 281369 | 238282 | 43087 | 331369 | 278282 | 53087 | 2282589 | 713480 | 1569109 | 1705866 | 358325 | 1347541 | 1945869 | 443044 | 1502825 | 2282589 | 713480 | 1569109 | 1705866 | 358325 | 1347541 | 1945869 | 443044 | 1502825 | 0 | 544 | Nez Perce Tribe
NT10BIX5570123 | INF | 2012 | Q2 | Q2 - 2012 | 680688 | 28300 | 652388 | 488567 | 47189 | 441377 | 500283 | 47189 | 453094 | 731555 | 85953 | 645602 | 811610 | 39601 | 772009 | 948707 | 59575 | 889132 | 238263 | 171424 | 66839 | 120819 | 37229 | 83590 | 152369 | 61949 | 90420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 79748 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 334643 | 292733 | 41910 | 374642 | 332732 | 41910 | 2282589 | 713480 | 1569109 | 1840424 | 416752 | 1423671 | 2060786 | 501445 | 1559341 | 2282589 | 713480 | 1569109 | 1840424 | 416752 | 1423671 | 2060786 | 501445 | 1559341 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2012 | Q3 | Q3 - 2012 | 680688 | 28300 | 652388 | 540770 | 89896 | 450874 | 540770 | 89896 | 450874 | 731555 | 85953 | 645602 | 947568 | 55102 | 892466 | 947568 | 55102 | 892466 | 238263 | 171424 | 66839 | 143364 | 53641 | 89723 | 165641 | 68641 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 378460 | 336550 | 41910 | 478460 | 436550 | 41910 | 2282589 | 713480 | 1569109 | 2095887 | 536129 | 1559758 | 2218164 | 651129 | 1567035 | 2282589 | 713480 | 1569109 | 2095887 | 536129 | 1559758 | 2218164 | 651129 | 1567035 | 0 | 0 | Nez Perce Tribe
NT10BIX5570123 | INF | 2012 | Q4 | Q4 - 2012 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453292 | 731555 | 85953 | 645602 | 936724 | 75917 | 860807 | 953371 | 95917 | 857551 | 238263 | 171424 | 66839 | 145627 | 54144 | 91483 | 186714 | 55143 | 131571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 480496 | 438586 | 41910 | 513494 | 471584 | 41910 | 2282589 | 713480 | 1569109 | 2191857 | 659483 | 1532374 | 2282589 | 713480 | 1569109 | 2282589 | 713480 | 1569109 | 2191857 | 659483 | 1532374 | 2282589 | 713480 | 1569109 | 0 | 28730 | Nez Perce Tribe
NT10BIX5570123 | INF | 2013 | Q1 | Q1 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 150869 | 54144 | 96725 | 155369 | 54144 | 101225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523179 | 481269 | 41910 | 523179 | 481269 | 41910 | 2282589 | 713480 | 1569109 | 2255073 | 713480 | 1541593 | 2259573 | 713480 | 1546093 | 2282589 | 713480 | 1569109 | 2255073 | 713480 | 1541593 | 2259573 | 713480 | 1546093 | 0 | 46193 | Nez Perce Tribe
NT10BIX5570123 | INF | 2013 | Q2 | Q2 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 158178 | 54144 | 104033 | 158178 | 54144 | 104033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523991 | 481269 | 42722 | 523991 | 481269 | 42722 | 2282589 | 713480 | 1569109 | 2263194 | 713480 | 1549713 | 2263194 | 713480 | 1549713 | 2282589 | 713480 | 1569109 | 2263194 | 713480 | 1549713 | 2263194 | 713480 | 1549713 | 0 | 58884 | Nez Perce Tribe
NT10BIX5570123 | INF | 2013 | Q3 | Q3 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 160581 | 54144 | 106437 | 160581 | 54144 | 106437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523991 | 481269 | 42722 | 523991 | 481269 | 42722 | 2282589 | 713480 | 1569109 | 2265597 | 713480 | 1552117 | 2265597 | 713480 | 1552117 | 2282589 | 713480 | 1569109 | 2265597 | 713480 | 1552117 | 2265597 | 713480 | 1552117 | 0 | 58884 | Nez Perce Tribe
NT10BIX5570125 | INF | 2010 | Q4 | Q4 - 2010 | 639339 | 127868 | 511471 | 0 | 0 | 0 | 62431 | 0 | 62431 | 14337357 | 2867471 | 11469886 | 192933 | 0 | 192933 | 810116 | 0 | 810116 | 434100 | 86820 | 347280 | 140359 | 0 | 140359 | 214500 | 0 | 214500 | 298083 | 58617 | 234466 | 0 | 0 | 0 | 96400 | 0 | 96400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 53939 | 0 | 53939 | 279000 | 0 | 279000 | 714775 | 142955 | 571820 | 216701 | 0 | 216701 | 446750 | 0 | 446750 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 0 | 0 | 0 | 17217800 | 3442560 | 13770240 | 603932 | 0 | 603932 | 1909197 | 0 | 1909197 | 17217800 | 3442560 | 13770240 | 603932 | 0 | 603932 | 1909197 | 0 | 1909197 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2011 | Q1 | Q1 - 2011 | 639339 | 127868 | 511471 | 470 | 0 | 470 | 83212 | 0 | 83212 | 14337357 | 2867471 | 11469886 | 366794 | 0 | 366794 | 1022288 | 50000 | 972288 | 434100 | 86820 | 347280 | 172903 | 0 | 172903 | 242600 | 0 | 242600 | 293083 | 58617 | 234466 | 0 | 0 | 0 | 137800 | 0 | 137800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 213908 | 0 | 213908 | 430000 | 0 | 430000 | 714775 | 142955 | 571820 | 419706 | 0 | 419706 | 480250 | 0 | 480250 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 0 | 0 | 0 | 17212800 | 3442560 | 13770240 | 1173781 | 0 | 1173781 | 2396150 | 50000 | 2346150 | 17212800 | 3442560 | 13770240 | 1173781 | 0 | 1173781 | 2396150 | 50000 | 2346150 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2011 | Q2 | Q2 - 2011 | 639339 | 127868 | 511471 | 917 | 0 | 917 | 87312 | 0 | 87312 | 14337357 | 2867471 | 11469886 | 575623 | 0 | 575623 | 4474920 | 420000 | 4054920 | 434100 | 86820 | 347280 | 192378 | 0 | 192378 | 309200 | 0 | 309200 | 293083 | 58617 | 234466 | 0 | 0 | 0 | 267283 | 80000 | 187283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 381692 | 0 | 381692 | 489400 | 100000 | 389400 | 714775 | 142955 | 571820 | 549995 | 0 | 549995 | 563250 | 0 | 563250 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 9120 | 0 | 9120 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 45475 | 0 | 45475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 28924 | 0 | 28924 | 17212800 | 3442560 | 13770240 | 1700605 | 0 | 1700605 | 6274884 | 600000 | 5674884 | 17212800 | 3442560 | 13770240 | 1700605 | 0 | 1700605 | 6274884 | 600000 | 5674884 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2011 | Q3 | Q3 - 2011 | 639339 | 127868 | 511471 | 917 | 0 | 917 | 16917 | 0 | 16917 | 14337357 | 2867471 | 11469886 | 1054861 | 34453 | 1020408 | 2558704 | 385000 | 2173704 | 434100 | 86820 | 347280 | 231043 | 11592 | 219450 | 283290 | 0 | 283290 | 293083 | 58617 | 234466 | 18271 | 0 | 18271 | 18271 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 487893 | 2097 | 485795 | 513893 | 250000 | 263893 | 714775 | 142955 | 571820 | 555063 | 0 | 555063 | 575063 | 0 | 575063 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 8801 | 0 | 8801 | 8801 | 0 | 8801 | 17212800 | 3442560 | 13770240 | 2356849 | 48142 | 2308705 | 3974939 | 635000 | 3339939 | 17212800 | 3442560 | 13770240 | 2356849 | 48142 | 2308705 | 3974939 | 635000 | 3339939 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2011 | Q4 | Q4 - 2011 | 639339 | 127868 | 511471 | 17518 | 0 | 17518 | 17667 | 0 | 17667 | 14337357 | 2867471 | 11469886 | 2385235 | 150654 | 2234581 | 3550656 | 249087 | 3301569 | 434100 | 86820 | 347280 | 299660 | 70381 | 229279 | 449705 | 90654 | 359051 | 293083 | 58617 | 234466 | 22019 | 0 | 22019 | 22550 | 0 | 22550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552369 | 568874 | 16504 | 552369 | 714775 | 142955 | 571820 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 3857546 | 237539 | 3620006 | 5173692 | 356245 | 4817446 | 17212800 | 3442560 | 13770240 | 3857546 | 237539 | 3620006 | 5173692 | 356245 | 4817446 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2012 | Q1 | Q1 - 2012 | 639339 | 127868 | 511471 | 18300 | 0 | 18300 | 19300 | 0 | 19300 | 14337357 | 2867471 | 11469886 | 4083046 | 329737 | 3753309 | 7924874 | 753937 | 7170937 | 434100 | 86820 | 347280 | 448672 | 92362 | 356310 | 531972 | 167662 | 364310 | 293083 | 58617 | 234466 | 22196 | 0 | 22196 | 22727 | 0 | 22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 591868 | 0 | 591868 | 618868 | 0 | 618868 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 45475 | 32500 | 12975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 5742133 | 438603 | 5303530 | 9741267 | 970603 | 8770664 | 17212800 | 3442560 | 13770240 | 5742133 | 438603 | 5303530 | 9741267 | 970603 | 8770664 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2012 | Q2 | Q2 - 2012 | 639339 | 127868 | 511471 | 18449 | 0 | 18449 | 431223 | 412774 | 18449 | 14337357 | 2867471 | 11469886 | 8555034 | 1254551 | 7300483 | 11595492 | 1781777 | 9813715 | 434100 | 86820 | 347280 | 560653 | 191298 | 369355 | 671652 | 302297 | 369355 | 293083 | 58617 | 234466 | 22373 | 0 | 22373 | 22904 | 0 | 22904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552369 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 40033 | 1787 | 38246 | 48433 | 1787 | 46646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 10376568 | 1464140 | 8912428 | 13949730 | 2515139 | 11434590 | 17212800 | 3442560 | 13770240 | 10376568 | 1464140 | 8912428 | 13949730 | 2515139 | 11434590 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2012 | Q3 | Q3 - 2012 | 639339 | 127868 | 511471 | 19415 | 0 | 19415 | 2169415 | 900000 | 1269415 | 14337357 | 2867471 | 11469886 | 9318965 | 1371234 | 7947731 | 10159870 | 1371234 | 8788636 | 434100 | 86820 | 347280 | 695984 | 242721 | 453263 | 833484 | 331235 | 502249 | 293083 | 58617 | 234466 | 22373 | 0 | 22373 | 22904 | 0 | 22904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 637975 | 0 | 637975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 127380 | 1787 | 125593 | 127380 | 1787 | 125593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 11364143 | 1632246 | 9731897 | 14529079 | 2620760 | 11908319 | 17212800 | 3442560 | 13770240 | 11364143 | 1632246 | 9731897 | 14529079 | 2620760 | 11908319 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2012 | Q4 | Q4 - 2012 | 639339 | 127868 | 511471 | 1707499 | 1261368 | 446131 | 1917499 | 1261368 | 656131 | 14337357 | 2867471 | 11469886 | 9369907 | 1386234 | 7983673 | 10434007 | 1386234 | 9047773 | 434100 | 86820 | 347280 | 841084 | 242721 | 598363 | 976084 | 242721 | 733363 | 293083 | 58617 | 234466 | 530699 | 0 | 530699 | 531230 | 0 | 531230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 127380 | 1787 | 125593 | 127380 | 1787 | 125593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 119676 | 0 | 119676 | 125676 | 0 | 125676 | 17212800 | 3442560 | 13770240 | 13867094 | 2908614 | 10958480 | 15282725 | 2908614 | 12374111 | 17212800 | 3442560 | 13770240 | 13867094 | 2908614 | 10958480 | 15282725 | 2908614 | 12374111 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2013 | Q1 | Q1 - 2013 | 639339 | 127868 | 511471 | 1926004 | 976633 | 949371 | 2276004 | 1316633 | 959371 | 14337357 | 2867471 | 11469886 | 9832926 | 1390622 | 8442304 | 11129526 | 1426749 | 9702777 | 434100 | 86820 | 347280 | 938707 | 242721 | 695986 | 1083707 | 277721 | 805986 | 293083 | 58617 | 234466 | 533698 | 0 | 533698 | 534229 | 0 | 534229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 129536 | 1787 | 127749 | 129536 | 1787 | 127749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 155837 | 0 | 155837 | 161837 | 0 | 161837 | 17212800 | 3442560 | 13770240 | 14687557 | 2628267 | 12059290 | 16485688 | 3039394 | 13446294 | 17212800 | 3442560 | 13770240 | 14687557 | 2628267 | 12059290 | 16485688 | 3039394 | 13446294 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2013 | Q2 | Q2 - 2013 | 639339 | 127868 | 511471 | 2359863 | 1530515 | 829348 | 2429863 | 1580515 | 849348 | 14337357 | 2867471 | 11469886 | 10966618 | 1417773 | 9548845 | 11664315 | 1553605 | 10110710 | 434100 | 86820 | 347280 | 1085857 | 290149 | 795708 | 1093357 | 290149 | 803208 | 293083 | 58617 | 234466 | 534054 | 0 | 534054 | 534410 | 0 | 534410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 129536 | 1787 | 127749 | 129536 | 1787 | 127749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 190470 | 0 | 190470 | 190470 | 0 | 190470 | 17212800 | 3442560 | 13770240 | 16437247 | 3256728 | 13180519 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 16437247 | 3256728 | 13180519 | 17212800 | 3442560 | 13770240 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570125 | INF | 2013 | Q3 | Q3 - 2013 | 2771330 | 1730041 | 1041289 | 2485683 | 1600051 | 885632 | 2485683 | 1600051 | 885632 | 11217409 | 1319262 | 9898147 | 11785927 | 1525493 | 10260434 | 11785927 | 1525493 | 10260434 | 1278591 | 345692 | 932899 | 1087807 | 269028 | 818779 | 1087807 | 269028 | 818779 | 530214 | 0 | 530214 | 534144 | 0 | 534144 | 534144 | 0 | 534144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568874 | 1891 | 566983 | 568874 | 0 | 568874 | 568874 | 0 | 568874 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291319 | 45674 | 245645 | 195302 | 47988 | 147314 | 195302 | 47988 | 147314 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 0 | 0 | Plumas Sierra Rural Electric Cooperative
NT10BIX5570126 | INF | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 0 | 0 | 0 | 0 | 0 | 0 | 227000 | 68100 | 158900 | 187557 | 56267 | 131290 | 211432 | 63430 | 148002 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 51754 | 15526 | 36228 | 582504 | 174752 | 407752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 239311 | 71793 | 167518 | 793936 | 238182 | 555754 | 66599667 | 19979910 | 46619757 | 239311 | 71793 | 167518 | 793936 | 238182 | 555754 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 11126 | 3338 | 7788 | 4556720 | 1367017 | 3189703 | 227000 | 68100 | 158900 | 196557 | 58967 | 137590 | 227000 | 68100 | 158900 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 246317 | 73895 | 172422 | 1950000 | 585000 | 1365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 454000 | 136200 | 317800 | 6949683 | 2084906 | 4864777 | 66599667 | 19979910 | 46619757 | 454000 | 136200 | 317800 | 6949683 | 2084906 | 4864777 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 45655 | 17401 | 28254 | 6556000 | 1966801 | 4589199 | 227000 | 68100 | 158900 | 231610 | 69484 | 162126 | 271610 | 81483 | 190127 | 215963 | 64789 | 151174 | 7348 | 2205 | 5143 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 1239311 | 371794 | 867517 | 1950000 | 585000 | 1365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 1523924 | 460884 | 1063040 | 8993573 | 2698073 | 6295500 | 66599667 | 19979910 | 46619757 | 1523924 | 460884 | 1063040 | 8993573 | 2698073 | 6295500 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 147475 | 87655 | 59820 | 6556000 | 1966801 | 4589199 | 227000 | 68100 | 158900 | 294890 | 96008 | 198882 | 334890 | 100467 | 234423 | 215963 | 64789 | 151174 | 329160 | 124012 | 205148 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2537350 | 847277 | 1690073 | 3000000 | 900000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 3308875 | 1154952 | 2153923 | 10465890 | 3139768 | 7326122 | 66599667 | 19979910 | 46619757 | 3308875 | 1154952 | 2153923 | 10465890 | 3139768 | 7326122 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 4098623 | 1229588 | 2869035 | 15000000 | 4500000 | 10500000 | 227000 | 68100 | 158900 | 348453 | 104536 | 243917 | 450000 | 135000 | 315000 | 215963 | 64789 | 151174 | 524717 | 157415 | 367302 | 800000 | 240000 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2759232 | 827770 | 1931462 | 3000000 | 900000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 16884 | 5065 | 11819 | 150000 | 45000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 7747909 | 2324374 | 5423535 | 19400000 | 5820000 | 13580000 | 66599667 | 19979910 | 46619757 | 7747909 | 2324374 | 5423535 | 19400000 | 5820000 | 13580000 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 14506475 | 4351945 | 10154530 | 35000000 | 10500000 | 24500000 | 227000 | 68100 | 158900 | 460135 | 138041 | 322094 | 560000 | 168000 | 392000 | 215963 | 64789 | 151174 | 937313 | 281194 | 656119 | 1100000 | 330000 | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2983682 | 895105 | 2088577 | 3200000 | 960000 | 2240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 277061 | 83118 | 193943 | 600000 | 180000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 19164666 | 5749403 | 13415263 | 40460000 | 12138000 | 28322000 | 66599667 | 19979910 | 46619757 | 19164666 | 5749403 | 13415263 | 40460000 | 12138000 | 28322000 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 21876436 | 6562934 | 15313502 | 40000000 | 12000006 | 27999994 | 227000 | 68100 | 158900 | 546729 | 164019 | 382710 | 650000 | 195000 | 455000 | 215963 | 64789 | 151174 | 1576452 | 472936 | 1103516 | 1600000 | 480000 | 1120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 3655258 | 1096578 | 2558680 | 3800000 | 1140001 | 2659999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 818187 | 245456 | 572731 | 900000 | 270000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 28473062 | 8541923 | 19931139 | 46950000 | 14085007 | 32864993 | 66599667 | 19979910 | 46619757 | 28473062 | 8541923 | 19931139 | 46950000 | 14085007 | 32864993 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 35283757 | 10585133 | 24698624 | 49000000 | 14700007 | 34299993 | 227000 | 68100 | 158900 | 669441 | 200832 | 468609 | 750000 | 225000 | 525000 | 215963 | 64789 | 151174 | 1660760 | 498228 | 1162532 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4032865 | 1209860 | 2823005 | 4100000 | 1230001 | 2869999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 1360902 | 408271 | 952631 | 1500000 | 450000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 43007725 | 12902324 | 30105401 | 57050000 | 17115008 | 39934992 | 66599667 | 19979910 | 46619757 | 43007725 | 12902324 | 30105401 | 57050000 | 17115008 | 39934992 | 0 | 0 | CVIN, LLC
NT10BIX5570126 | INF | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 40946710 | 12284019 | 28662691 | 55000000 | 16500009 | 38499991 | 227000 | 68100 | 158900 | 705723 | 211717 | 494006 | 750000 | 225000 | 525000 | 215963 | 64789 | 151174 | 1711516 | 513455 | 1198061 | 1740000 | 522000 | 1218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4223939 | 1267183 | 2956756 | 4300000 | 1290001 | 3009999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 1867257 | 560177 | 1307080 | 2000000 | 600000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 49455145 | 14836551 | 34618594 | 63790000 | 19137010 | 44652990 | 66599667 | 19979910 | 46619757 | 49455145 | 14836551 | 34618594 | 63790000 | 19137010 | 44652990 | 0 | 832484 | CVIN, LLC
NT10BIX5570126 | INF | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 44255537 | 13276668 | 30978869 | 57000000 | 17100009 | 39899991 | 227000 | 68100 | 158900 | 795133 | 238540 | 556593 | 850000 | 255000 | 595000 | 215963 | 64789 | 151174 | 1757311 | 527194 | 1230117 | 1760000 | 528000 | 1232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4490411 | 1347124 | 3143287 | 4500000 | 1350001 | 3149999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 2339626 | 701888 | 1637738 | 2400000 | 720000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 53638018 | 16091414 | 37546604 | 66510000 | 19953010 | 46556990 | 66599667 | 19979910 | 46619757 | 53638018 | 16091414 | 37546604 | 66510000 | 19953010 | 46556990 | 0 | 216158 | CVIN, LLC
NT10BIX5570126 | INF | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 49895793 | 14968745 | 34927048 | 62605667 | 23001536 | 39604131 | 227000 | 68100 | 158900 | 830138 | 249042 | 581096 | 870000 | 288904 | 581096 | 215963 | 64789 | 151174 | 1868522 | 560557 | 1307965 | 1900000 | 592035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4598448 | 1379535 | 3218913 | 4600000 | 1381087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 2725218 | 817566 | 1907652 | 3000000 | 1092348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 59918119 | 17975445 | 41942674 | 72975667 | 26355910 | 46619757 | 66599667 | 19979910 | 46619757 | 59918119 | 17975445 | 41942674 | 72975667 | 26355910 | 46619757 | 0 | 216158 | CVIN, LLC
NT10BIX5570126 | INF | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 59642245 | 20038114 | 39604131 | 63038836 | 23434705 | 39604131 | 227000 | 68100 | 158900 | 935669 | 354573 | 581096 | 950000 | 368904 | 581096 | 215963 | 64789 | 151174 | 1971085 | 663120 | 1307965 | 2000000 | 692035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4662950 | 1444037 | 3218913 | 4700000 | 1481087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 3162778 | 1255126 | 1907652 | 3300000 | 1392348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 70374727 | 23754970 | 46619757 | 73988836 | 27369079 | 46619757 | 66599667 | 19979910 | 46619757 | 70374727 | 23754970 | 46619757 | 73988836 | 27369079 | 46619757 | 0 | 266389 | CVIN, LLC
NT10BIX5570126 | INF | 2013 | Q4 | Q4 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 64763443 | 25159312 | 39604131 | 66000000 | 26395869 | 39604131 | 227000 | 68100 | 158900 | 983738 | 402642 | 581096 | 1000000 | 418904 | 581096 | 215963 | 64789 | 151174 | 1996377 | 688412 | 1307965 | 2000000 | 692035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4906466 | 1687553 | 3218913 | 4910000 | 1691087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 3657275 | 1749623 | 1907652 | 3700000 | 1792348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 76307299 | 29687542 | 46619757 | 77610000 | 30990243 | 46619757 | 66599667 | 19979910 | 46619757 | 76307299 | 29687542 | 46619757 | 77610000 | 30990243 | 46619757 | 0 | 391524 | CVIN, LLC
NT10BIX5570126 | INF | 2014 | Q1 | Q1 - 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 66750177 | 27146046 | 39604131 | 66800000 | 27195869 | 39604131 | 227000 | 68100 | 158900 | 983738 | 402642 | 581096 | 1000000 | 418904 | 581096 | 215963 | 64789 | 151174 | 1996377 | 688412 | 1307965 | 2000000 | 692035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4906466 | 1687553 | 3218913 | 4910000 | 1691087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 3854907 | 1947255 | 1907652 | 3900000 | 1992348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 78491665 | 31871908 | 46619757 | 78610000 | 31990243 | 46619757 | 66599667 | 19979910 | 46619757 | 78491665 | 31871908 | 46619757 | 78610000 | 31990243 | 46619757 | 0 | 391524 | CVIN, LLC
NT10BIX5570126 | INF | 2014 | Q2 | Q2 - 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 67582302 | 27978171 | 39604131 | 67582302 | 27978171 | 39604131 | 227000 | 68100 | 158900 | 996179 | 415083 | 581096 | 996179 | 415083 | 581096 | 215963 | 64789 | 151174 | 1669998 | 362033 | 1307965 | 1669998 | 362033 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4956741 | 1737828 | 3218913 | 4956741 | 1737828 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 4168414 | 2260762 | 1907652 | 4168414 | 2260762 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 79373634 | 32753877 | 46619757 | 79373634 | 32753877 | 46619757 | 66599667 | 19979910 | 46619757 | 79373634 | 32753877 | 46619757 | 79373634 | 32753877 | 46619757 | 0 | 391524 | CVIN, LLC
NT10BIX5570127 | INF | 2010 | Q4 | Q4 - 2010 | 2171421 | 722124 | 1449297 | 0 | 0 | 0 | 0 | 0 | 0 | 16130066 | 5010193 | 11119873 | 0 | 0 | 0 | 0 | 0 | 0 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45000 | 45000 | 0 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 9811 | 3047 | 6764 | 317274 | 3047 | 314227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 42001 | 20285 | 21716 | 73501 | 20285 | 53216 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 96812 | 68332 | 28480 | 435775 | 68332 | 367443 | 24071690 | 7842369 | 16229321 | 96812 | 68332 | 28480 | 435775 | 68332 | 367443 | 953688 | 0 | Utopia
NT10BIX5570127 | INF | 2011 | Q1 | Q1 - 2011 | 2171421 | 722124 | 1449297 | 0 | 0 | 0 | 590711 | 187946 | 402765 | 16130066 | 5010193 | 11119873 | 0 | 0 | 0 | 1275109 | 396064 | 879045 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45555 | 45172 | 383 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 140994 | 43794 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 139809 | 3047 | 136762 | 379809 | 117973 | 261836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 83172 | 29956 | 53216 | 162172 | 75999 | 86173 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 117000 | 36342 | 80658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 267981 | 78003 | 189978 | 2711350 | 903290 | 1808060 | 24071690 | 7842369 | 16229321 | 267981 | 78003 | 189978 | 2711350 | 903290 | 1808060 | 953688 | 0 | Utopia
NT10BIX5570127 | INF | 2011 | Q2 | Q2 - 2011 | 2171421 | 722124 | 1449297 | 2814 | 0 | 2814 | 608956 | 199495 | 409461 | 16130066 | 5010193 | 11119873 | 515009 | 191826 | 323183 | 2492600 | 806090 | 1686510 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 46365 | 45424 | 941 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 140994 | 43794 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 229350 | 27374 | 201976 | 429349 | 133361 | 295988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 151393 | 87677 | 63716 | 245513 | 142006 | 103507 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 117000 | 36342 | 80658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 943566 | 351877 | 591689 | 4080777 | 1406512 | 2674265 | 24071690 | 7842369 | 16229321 | 943566 | 351877 | 591689 | 4080777 | 1406512 | 2674265 | 953688 | 0 | Utopia
NT10BIX5570127 | INF | 2011 | Q3 | Q3 - 2011 | 2171421 | 722124 | 1449297 | 9595 | 0 | 9595 | 651427 | 216638 | 434789 | 16130066 | 5010193 | 11119873 | 1218372 | 325773 | 892599 | 4032517 | 1252549 | 2779968 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 46500 | 45466 | 1034 | 1879920 | 583926 | 1295994 | 81808 | 0 | 81808 | 187992 | 58393 | 129599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 348177 | 39124 | 309053 | 910019 | 282663 | 627356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 232473 | 168757 | 63716 | 337920 | 193204 | 144716 | 1560000 | 484555 | 1075445 | 31251 | 31251 | 0 | 312000 | 96911 | 215089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 1966676 | 609905 | 1356771 | 6478375 | 2145824 | 4332551 | 24071690 | 7842369 | 16229321 | 1966676 | 609905 | 1356771 | 6478375 | 2145824 | 4332551 | 953688 | 4310 | Utopia
NT10BIX5570127 | INF | 2011 | Q4 | Q4 - 2011 | 2171421 | 722124 | 1449297 | 352689 | 22879 | 329810 | 1194281 | 397168 | 797113 | 16130066 | 5010193 | 11119873 | 1947127 | 592394 | 1354733 | 6290725 | 1953975 | 4336750 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 225910 | 38923 | 186987 | 520593 | 161703 | 358890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 482684 | 83396 | 399288 | 970686 | 301507 | 669179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 289048 | 225333 | 63715 | 528000 | 301881 | 226119 | 1560000 | 484555 | 1075445 | 129608 | 114367 | 15241 | 624000 | 193822 | 430178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 3472066 | 1122292 | 2349774 | 10175535 | 3357306 | 6818229 | 24071690 | 7842369 | 16229321 | 3472066 | 1122292 | 2349774 | 10175535 | 3357306 | 6818229 | 953688 | 4840 | Utopia
NT10BIX5570127 | INF | 2012 | Q1 | Q1 - 2012 | 2171421 | 722124 | 1449297 | 441388 | 111578 | 329810 | 767101 | 219897 | 547204 | 16130066 | 5010193 | 11119873 | 4270415 | 1465912 | 2804503 | 8302931 | 2268460 | 6034471 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 445082 | 102770 | 342312 | 968708 | 223676 | 745032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 758864 | 195557 | 563307 | 1037937 | 282240 | 755697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 419464 | 349388 | 70076 | 525064 | 409764 | 115300 | 1560000 | 484555 | 1075445 | 269778 | 227421 | 42357 | 790066 | 666020 | 124046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 6649991 | 2497626 | 4152365 | 12439057 | 4117307 | 8321750 | 24071690 | 7842369 | 16229321 | 6649991 | 2497626 | 4152365 | 12439057 | 4117307 | 8321750 | 953688 | 9070 | Utopia
NT10BIX5570127 | INF | 2012 | Q2 | Q2 - 2012 | 2171421 | 722124 | 1449297 | 592986 | 242188 | 350798 | 1135842 | 422719 | 713123 | 16130066 | 5010193 | 11119873 | 7044078 | 2421190 | 4622888 | 11076594 | 3223738 | 7852856 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 728958 | 102770 | 626188 | 1231687 | 173645 | 1058042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 968569 | 261698 | 706871 | 1211240 | 337075 | 874165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 546458 | 441302 | 105155 | 652058 | 501678 | 150380 | 1560000 | 484555 | 1075445 | 270988 | 227421 | 43567 | 794900 | 667102 | 127798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 10197037 | 3741569 | 6455467 | 16149571 | 5373207 | 10776364 | 24071690 | 7842369 | 16229321 | 10197037 | 3741569 | 6455467 | 16149571 | 5373207 | 10776364 | 953688 | 10616 | Utopia
NT10BIX5570127 | INF | 2012 | Q3 | Q3 - 2012 | 2171421 | 722124 | 1449297 | 834387 | 483588 | 350799 | 1122456 | 505105 | 617351 | 16130066 | 5010193 | 11119873 | 8279660 | 2508882 | 5770778 | 11160598 | 3571391 | 7589207 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 728958 | 102770 | 626188 | 887042 | 177409 | 709633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1060795 | 264678 | 796117 | 1177346 | 329657 | 847689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 668930 | 306292 | 362638 | 791402 | 316561 | 474841 | 1560000 | 484555 | 1075445 | 371177 | 227421 | 143756 | 967682 | 483841 | 483841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 11988907 | 3938631 | 8050276 | 16153776 | 5431214 | 10722562 | 24071690 | 7842369 | 16229321 | 11988907 | 3938631 | 8050276 | 16153776 | 5431214 | 10722562 | 953688 | 15374 | Utopia
NT10BIX5570127 | INF | 2012 | Q4 | Q4 - 2012 | 2171421 | 722124 | 1449297 | 993708 | 572485 | 421223 | 1168708 | 525920 | 642789 | 16130066 | 5010193 | 11119873 | 10556262 | 3131486 | 7424776 | 12832864 | 4106516 | 8726348 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 55000 | 55000 | 0 | 1879920 | 583926 | 1295994 | 1026887 | 254612 | 772275 | 1196887 | 239377 | 957509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1157045 | 307836 | 849209 | 1207045 | 337973 | 869072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 774929 | 389411 | 385518 | 880928 | 449273 | 431655 | 1560000 | 484555 | 1075445 | 487436 | 293350 | 194086 | 967682 | 464487 | 503195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 15041267 | 4994180 | 10047087 | 18309114 | 6178546 | 12130568 | 24071690 | 7842369 | 16229321 | 15041267 | 4994180 | 10047087 | 18309114 | 6178546 | 12130568 | 953688 | 28896 | Utopia
NT10BIX5570127 | INF | 2013 | Q1 | Q1 - 2013 | 2171421 | 722124 | 1449297 | 1005685 | 572484 | 433201 | 1155685 | 520058 | 635627 | 16130066 | 5010193 | 11119873 | 12658029 | 3630936 | 9027093 | 14759796 | 4575537 | 10184259 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 55000 | 55000 | 0 | 1879920 | 583926 | 1295994 | 1112103 | 338917 | 773186 | 1503936 | 451181 | 1052755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1261560 | 359012 | 902548 | 1321560 | 370037 | 951523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 827251 | 426223 | 401028 | 879572 | 448582 | 430990 | 1560000 | 484555 | 1075445 | 607847 | 312219 | 295628 | 967682 | 464487 | 503195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 17517475 | 5684791 | 11832684 | 20643231 | 6884882 | 13758349 | 24071690 | 7842369 | 16229321 | 17517475 | 5684791 | 11832684 | 20643231 | 6884882 | 13758349 | 953688 | 44902 | Utopia
NT10BIX5570127 | INF | 2013 | Q2 | Q2 - 2013 | 2171421 | 722124 | 1449297 | 1317925 | 572484 | 745441 | 2000000 | 760000 | 1240000 | 16130066 | 5010193 | 11119873 | 14649501 | 4372355 | 10277146 | 15800000 | 4740000 | 11060000 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 60925 | 60925 | 0 | 1879920 | 583926 | 1295994 | 1514048 | 480586 | 1033462 | 1800000 | 522000 | 1278000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1351819 | 385950 | 965869 | 1380000 | 386400 | 993600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 977725 | 543217 | 434508 | 1050000 | 588000 | 462000 | 1560000 | 484555 | 1075445 | 712268 | 333902 | 378366 | 1000000 | 480000 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 20568286 | 6733494 | 13834792 | 23090925 | 7537325 | 15553600 | 24071690 | 7842369 | 16229321 | 20568286 | 6733494 | 13834792 | 23090925 | 7537325 | 15553600 | 953688 | 62050 | Utopia
NT10BIX5570127 | INF | 2013 | Q3 | Q3 - 2013 | 2171421 | 722124 | 1449297 | 1448238 | 593965 | 854273 | 1448238 | 593965 | 854273 | 16130066 | 5010193 | 11119873 | 16707719 | 4839201 | 11868518 | 16707719 | 4839201 | 11868518 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45000 | 45000 | 0 | 1879920 | 583926 | 1295994 | 1711450 | 580274 | 1131176 | 1711450 | 580274 | 1131176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1440762 | 399656 | 1041106 | 1440762 | 399656 | 1041106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 1070465 | 597993 | 472472 | 1070465 | 597993 | 472472 | 1560000 | 484555 | 1075445 | 956387 | 476504 | 479883 | 956387 | 476504 | 479883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 23380021 | 7532593 | 15847428 | 23380021 | 7532593 | 15847428 | 24071690 | 7842369 | 16229321 | 23380021 | 7532593 | 15847428 | 23380021 | 7532593 | 15847428 | 953688 | 82218 | Utopia
NT10BIX5570128 | INF | 2010 | Q4 | Q4 - 2010 | 1137016 | 228158 | 908858 | 0 | 0 | 0 | 481041 | 96528 | 384513 | 16923915 | 3396017 | 13527898 | 0 | 0 | 0 | 3033645 | 608743 | 2424902 | 1770811 | 355337 | 1415474 | 389869 | 78233 | 311636 | 467950 | 93901 | 374049 | 1394639 | 279853 | 1114786 | 1700 | 341 | 1359 | 693713 | 139204 | 554509 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 7200 | 1440 | 5760 | 847460 | 170055 | 677405 | 41680 | 8364 | 33316 | 629103 | 126239 | 502864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 19250 | 3863 | 15387 | 10411565 | 2089224 | 8322341 | 0 | 0 | 0 | 1993520 | 400028 | 1593492 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 13700 | 2750 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 433249 | 86938 | 346311 | 7339122 | 1472696 | 5866426 | 32612412 | 6544128 | 26068284 | 433249 | 86938 | 346311 | 7339122 | 1472696 | 5866426 | 0 | 0 | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2011 | Q1 | Q1 - 2011 | 1137016 | 228158 | 908858 | 14333 | 2875 | 11457 | 220175 | 44181 | 175994 | 16923915 | 3396017 | 13527898 | 0 | 0 | 0 | 1100000 | 220730 | 879270 | 1770811 | 355337 | 1415474 | 505179 | 103514 | 401665 | 589624 | 118318 | 471308 | 1394639 | 279853 | 1114786 | 1700 | 342 | 1359 | 157400 | 31584 | 125816 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 10000 | 2007 | 7993 | 847460 | 170055 | 677405 | 60292 | 12099 | 48193 | 314276 | 63064 | 251212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 9751 | 1957 | 7794 | 10411565 | 2089224 | 8322341 | 701 | 141 | 560 | 1000000 | 200664 | 799336 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 5000 | 1003 | 3997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 582205 | 118971 | 463234 | 3406226 | 683508 | 2722720 | 32612412 | 6544128 | 26068284 | 582205 | 118971 | 463234 | 3406226 | 683508 | 2722720 | 0 | 0 | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2011 | Q2 | Q2 - 2011 | 1137016 | 228158 | 908858 | 84344 | 16925 | 67419 | 284254 | 57040 | 227214 | 16923915 | 3396017 | 13527898 | 1108103 | 224693 | 883410 | 4230979 | 849004 | 3381975 | 1770811 | 355337 | 1415474 | 664715 | 133384 | 531331 | 815700 | 163681 | 652019 | 1394639 | 279853 | 1114786 | 6721 | 1349 | 5372 | 348660 | 69963 | 278697 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 5400 | 1084 | 4316 | 847460 | 170055 | 677405 | 344523 | 69133 | 275390 | 404523 | 81173 | 323350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 7800 | 1565 | 6235 | 10411565 | 2089224 | 8322341 | 741613 | 148815 | 592798 | 2602891 | 522306 | 2080585 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 2950019 | 594299 | 2355720 | 8700207 | 1745816 | 6954391 | 32612412 | 6544128 | 26068284 | 2950019 | 594299 | 2355720 | 8700207 | 1745816 | 6954391 | 0 | 0 | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2011 | Q3 | Q3 - 2011 | 1137016 | 228158 | 908858 | 424654 | 85213 | 339441 | 764964 | 153501 | 611463 | 16923915 | 3396017 | 13527898 | 2334063 | 468362 | 1865701 | 3545439 | 711441 | 2833998 | 1770811 | 355337 | 1415474 | 799758 | 160482 | 639276 | 934801 | 187581 | 747220 | 1394639 | 279853 | 1114786 | 258162 | 51804 | 206358 | 509603 | 102259 | 407344 | 21600 | 4333 | 17267 | 5102 | 1024 | 4078 | 10204 | 2048 | 8156 | 847460 | 170055 | 677405 | 388172 | 77892 | 310280 | 431821 | 86651 | 345170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 14831 | 2976 | 11855 | 29662 | 5952 | 23710 | 10411565 | 2089224 | 8322341 | 1642246 | 329539 | 1312707 | 2542879 | 510264 | 2032615 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 5866988 | 1177292 | 4689696 | 8769373 | 1759697 | 7009676 | 32612412 | 6544128 | 26068284 | 5866988 | 1177292 | 4689696 | 8769373 | 1759697 | 7009676 | 0 | 44805 | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2011 | Q4 | Q4 - 2011 | 1137016 | 228158 | 908858 | 564541 | 113283 | 451258 | 833903 | 167334 | 666569 | 16923915 | 3396017 | 13527898 | 4455242 | 894006 | 3561236 | 6593758 | 1323129 | 5270629 | 1770811 | 355337 | 1415474 | 913040 | 183214 | 729826 | 1026257 | 205933 | 820324 | 1394639 | 279853 | 1114786 | 276606 | 55505 | 221101 | 301456 | 60491 | 240965 | 21600 | 4333 | 17267 | 5176 | 1039 | 4137 | 5280 | 1060 | 4220 | 847460 | 170055 | 677405 | 501506 | 100634 | 400872 | 614846 | 123377 | 491469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 31359 | 6293 | 25066 | 47040 | 9439 | 37601 | 10411565 | 2089224 | 8322341 | 3956580 | 793942 | 3162638 | 6330528 | 1270308 | 5060220 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 10704050 | 2147916 | 8556134 | 15753068 | 3161071 | 12591997 | 32612412 | 6544128 | 26068284 | 10704050 | 2147916 | 8556134 | 15753068 | 3161071 | 12591997 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2012 | Q1 | Q1 - 2012 | 1137016 | 228158 | 908858 | 866000 | 173775 | 692225 | 1046055 | 209906 | 836149 | 16923915 | 3396017 | 13527898 | 6129040 | 1229988 | 4899052 | 7802838 | 1565747 | 6237091 | 1770811 | 355337 | 1415474 | 946569 | 189942 | 756627 | 984432 | 197540 | 786892 | 1394639 | 279853 | 1114786 | 531686 | 106690 | 424996 | 786766 | 157875 | 628891 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 12616 | 2532 | 10084 | 847460 | 170055 | 677405 | 596126 | 119621 | 476505 | 690747 | 138608 | 552139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 35285 | 7080 | 28205 | 39211 | 7868 | 31343 | 10411565 | 2089224 | 8322341 | 5999836 | 1203950 | 4795886 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 1300 | 261 | 1039 | 1300 | 261 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 15114738 | 3033092 | 12081646 | 20257058 | 4064859 | 16192199 | 32612412 | 6544128 | 26068284 | 15114738 | 3033092 | 12081646 | 20257058 | 4064859 | 16192199 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2012 | Q2 | Q2 - 2012 | 1137016 | 228158 | 908858 | 1024534 | 205587 | 818947 | 1046055 | 209905 | 836149 | 16923915 | 3396017 | 13527898 | 7542650 | 1513537 | 6029112 | 8962660 | 1798481 | 7164179 | 1770811 | 355337 | 1415474 | 1044302 | 209553 | 834749 | 1086074 | 217936 | 868139 | 1394639 | 279853 | 1114786 | 776016 | 155718 | 620298 | 1020347 | 204747 | 815600 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 8896 | 1785 | 7111 | 847460 | 170055 | 677405 | 640609 | 128547 | 512062 | 685091 | 137473 | 547618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 72304 | 14509 | 57795 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 7558472 | 1516712 | 6041760 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 1300 | 261 | 1039 | 1300 | 261 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 18669083 | 3746209 | 14922873 | 21781522 | 4370763 | 17410759 | 32612412 | 6544128 | 26068284 | 18669083 | 3746209 | 14922873 | 21781522 | 4370763 | 17410759 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2012 | Q3 | Q3 - 2012 | 1137016 | 228158 | 908858 | 1032377 | 207161 | 825216 | 1046055 | 209905 | 836150 | 16923915 | 3396017 | 13527898 | 9105123 | 1826841 | 7278282 | 12021375 | 2412255 | 9609120 | 1770811 | 355337 | 1415474 | 1115429 | 223826 | 891603 | 1416649 | 284270 | 1132379 | 1394639 | 279853 | 1114786 | 894521 | 179498 | 715023 | 1227282 | 246271 | 981011 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 17792 | 3570 | 14222 | 847460 | 170055 | 677405 | 678241 | 136098 | 542143 | 745765 | 149648 | 596117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 8619412 | 1729604 | 6889808 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 9480 | 1902 | 7578 | 9480 | 1902 | 7578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 21541485 | 4322368 | 17219117 | 25455497 | 5107996 | 20347501 | 32612412 | 6544128 | 26068284 | 21541485 | 4322368 | 17219117 | 25455497 | 5107996 | 20347501 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2012 | Q4 | Q4 - 2012 | 1137016 | 228158 | 908858 | 1049083 | 210513 | 838570 | 1129981 | 226746 | 903235 | 16923915 | 3396017 | 13527898 | 10483590 | 2103765 | 8379825 | 13059720 | 2620613 | 10439107 | 1770811 | 355337 | 1415474 | 1200320 | 240861 | 959459 | 1656713 | 332442 | 1324271 | 1394639 | 279853 | 1114786 | 908081 | 182219 | 725862 | 1297327 | 260327 | 1037001 | 21600 | 4333 | 17267 | 9721 | 1951 | 7770 | 21600 | 4334 | 17266 | 847460 | 170055 | 677405 | 719030 | 144283 | 574747 | 834617 | 167477 | 667140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9063825 | 1818782 | 7245044 | 10303746 | 2067589 | 8236157 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 23532486 | 4722207 | 18810280 | 28409110 | 5700679 | 22708432 | 32612412 | 6544128 | 26068284 | 23532486 | 4722207 | 18810280 | 28409110 | 5700679 | 22708432 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2013 | Q1 | Q1 - 2013 | 1137016 | 228158 | 908858 | 1078138 | 216343 | 861795 | 1137016 | 228158 | 908857 | 16923915 | 3396017 | 13527898 | 11252104 | 2258147 | 8993957 | 13259720 | 2660746 | 10598974 | 1770811 | 355337 | 1415474 | 1261502 | 253138 | 1008364 | 1770811 | 355338 | 1415473 | 1394639 | 279853 | 1114786 | 926490 | 185913 | 740577 | 1297327 | 260327 | 1037001 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 21600 | 4334 | 17266 | 847460 | 170055 | 677405 | 758284 | 152160 | 606124 | 847460 | 170055 | 677405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9450628 | 1896399 | 7554229 | 10303746 | 2067589 | 8236157 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 24835811 | 4983905 | 19851906 | 28743086 | 5767698 | 22975388 | 32612412 | 6544128 | 26068284 | 24835811 | 4983905 | 19851906 | 28743086 | 5767698 | 22975388 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2013 | Q2 | Q2 - 2013 | 1137016 | 228158 | 908858 | 1079997 | 218202 | 861795 | 1137016 | 228158 | 908858 | 16923915 | 3396017 | 13527898 | 12838222 | 2574935 | 10263287 | 15902492 | 3191056 | 12711437 | 1770811 | 355337 | 1415474 | 1332587 | 267402 | 1065185 | 1529788 | 306973 | 1222815 | 1394639 | 279853 | 1114786 | 934711 | 187563 | 747148 | 1394639 | 279854 | 1114785 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 18069 | 3626 | 14443 | 847460 | 170055 | 677405 | 798541 | 160238 | 638303 | 798542 | 160238 | 638303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9899917 | 1986555 | 7913362 | 10293886 | 2065610 | 8228276 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 25758 | 5169 | 20589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 26992640 | 5416700 | 21575940 | 31178196 | 6256337 | 24921859 | 32612412 | 6544128 | 26068284 | 26992640 | 5416700 | 21575940 | 31178196 | 6256337 | 24921859 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2013 | Q3 | Q3 - 2013 | 1137016 | 228158 | 908858 | 1080096 | 216736 | 863360 | 1137016 | 228158 | 908858 | 16923915 | 3396017 | 13527898 | 14091808 | 2827970 | 11263838 | 16923915 | 3396017 | 13527898 | 1770811 | 355337 | 1415474 | 1409928 | 282922 | 1127006 | 1770811 | 355337 | 1415474 | 1394639 | 279853 | 1114786 | 934711 | 187563 | 747148 | 1394639 | 279853 | 1114786 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 21600 | 4333 | 17267 | 847460 | 170055 | 677405 | 812383 | 163016 | 649367 | 847460 | 170055 | 677405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 10194585 | 2045684 | 8148901 | 10411565 | 2089224 | 8322341 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 28632176 | 5745696 | 22886480 | 32612412 | 6544128 | 26068284 | 32612412 | 6544128 | 26068284 | 28632176 | 5745696 | 22886480 | 32612412 | 6544128 | 26068284 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570128 | INF | 2013 | Q4 | Q4 - 2013 | 1122630 | 225271 | 897359 | 1122630 | 225271 | 897359 | 1122630 | 225271 | 897359 | 15389489 | 3088369 | 12301120 | 15389489 | 3088369 | 12301120 | 15389489 | 3088369 | 12301120 | 1611677 | 323405 | 1288272 | 1611677 | 323405 | 1288272 | 1611677 | 323405 | 1288272 | 1042711 | 209234 | 833477 | 1042711 | 209234 | 833477 | 1042711 | 209234 | 833477 | 9281 | 1862 | 7419 | 9281 | 1862 | 7419 | 9281 | 1862 | 7419 | 845276 | 169616 | 675660 | 845276 | 169616 | 675660 | 845276 | 169616 | 675660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10563288 | 2119670 | 8443618 | 10563288 | 2119670 | 8443618 | 10563288 | 2119670 | 8443618 | 26463 | 5310 | 21153 | 26463 | 5310 | 21153 | 26463 | 5310 | 21153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc.
NT10BIX5570129 | INF | 2010 | Q4 | Q4 - 2010 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 208700 | 62610 | 146090 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 0 | 0 | 0 | 35150 | 0 | 35150 | 0 | 0 | 0 | 5000 | 1500 | 3500 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 0 | 0 | 0 | 97000 | 29100 | 67900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 0 | 0 | 0 | 15000 | 4500 | 10500 | 9990570 | 2997171 | 6993399 | 0 | 0 | 0 | 325700 | 97710 | 227990 | 9990570 | 2997171 | 6993399 | 0 | 0 | 0 | 325700 | 97710 | 227990 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2011 | Q1 | Q1 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 60000 | 18000 | 42000 | 35150 | 0 | 35150 | 1291 | 387 | 904 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 52008 | 15602 | 36406 | 252173 | 75652 | 176521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 13889 | 4167 | 9721 | 16574 | 4973 | 11601 | 9990570 | 2997171 | 6993399 | 67188 | 20156 | 47031 | 433747 | 130125 | 303622 | 9990570 | 2997171 | 6993399 | 67188 | 20156 | 47031 | 433747 | 130125 | 303622 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2011 | Q2 | Q2 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 35150 | 0 | 35150 | 5679 | 1704 | 3975 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 395679 | 118704 | 276975 | 550000 | 165000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 17822 | 5346 | 12476 | 24820 | 7446 | 17374 | 9990570 | 2997171 | 6993399 | 419180 | 125754 | 293426 | 929820 | 278946 | 650874 | 9990570 | 2997171 | 6993399 | 419180 | 125754 | 293426 | 929820 | 278946 | 650874 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2011 | Q3 | Q3 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 500000 | 150000 | 350000 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 60000 | 18000 | 42000 | 35150 | 0 | 35150 | 5679 | 1704 | 3975 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 220224 | 66067 | 154157 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 500522 | 150157 | 350365 | 700000 | 210000 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 17822 | 5346 | 12476 | 24820 | 7446 | 17374 | 9990570 | 2997171 | 6993399 | 744247 | 223274 | 520973 | 1814820 | 544446 | 1270374 | 9990570 | 2997171 | 6993399 | 744247 | 223274 | 520973 | 1814820 | 544446 | 1270374 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2011 | Q4 | Q4 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 641816 | 0 | 641816 | 2973056 | 497171 | 2475885 | 37925 | 31378 | 6547 | 712925 | 213877 | 499048 | 35150 | 0 | 35150 | 13935 | 0 | 13935 | 30000 | 0 | 30000 | 3219000 | 2500000 | 719000 | 307928 | 298654 | 9274 | 1344000 | 843741 | 500259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 721831 | 0 | 721831 | 771831 | 0 | 771831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 18487 | 0 | 18487 | 24820 | 0 | 24820 | 9990570 | 2997171 | 6993399 | 1100106 | 330032 | 770074 | 3525392 | 1057618 | 2467774 | 9990570 | 2997171 | 6993399 | 1100106 | 330032 | 770074 | 3525392 | 1057618 | 2467774 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2012 | Q1 | Q1 - 2012 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 641816 | 0 | 641816 | 2973056 | 497171 | 2475885 | 38515 | 6440 | 32075 | 712925 | 213877 | 499048 | 35150 | 0 | 35150 | 14728 | 0 | 14728 | 20000 | 0 | 20000 | 3219000 | 2500000 | 719000 | 643535 | 438689 | 204846 | 2949750 | 2290776 | 658974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 763111 | 0 | 763111 | 837149 | 0 | 837149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 23872 | 0 | 23872 | 28872 | 0 | 28872 | 9990570 | 2997171 | 6993399 | 1483761 | 445129 | 1038632 | 5195512 | 2504653 | 2690859 | 9990570 | 2997171 | 6993399 | 1483761 | 445129 | 1038632 | 5195512 | 2504653 | 2690859 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2012 | Q2 | Q2 - 2012 | 2239010 | 0 | 2239010 | 368464 | 0 | 368464 | 1300000 | 0 | 1300000 | 2973056 | 497171 | 2475885 | 45747 | 7648 | 38099 | 700000 | 117040 | 582960 | 35150 | 0 | 35150 | 15777 | 0 | 15777 | 17000 | 0 | 17000 | 3219000 | 2500000 | 719000 | 1448825 | 796105 | 652720 | 3020000 | 2345332 | 674668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 776494 | 0 | 776494 | 850000 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 23872 | 0 | 23872 | 45000 | 0 | 45000 | 9990570 | 2997171 | 6993399 | 2679179 | 803753 | 1875426 | 5957000 | 2462372 | 3494628 | 9990570 | 2997171 | 6993399 | 2679179 | 803753 | 1875426 | 5957000 | 2462372 | 3494628 | 0 | 0 | Rockbridge, County of
NT10BIX5570129 | INF | 2012 | Q3 | Q3 - 2012 | 2239010 | 0 | 2239010 | 1089044 | 326713 | 762331 | 1500000 | 450000 | 1050000 | 2973056 | 497171 | 2475885 | 615487 | 184646 | 430841 | 1200000 | 360000 | 840000 | 35150 | 0 | 35150 | 19051 | 5715 | 13336 | 21000 | 6300 | 14700 | 3219000 | 2500000 | 719000 | 2964857 | 889457 | 2075400 | 3100000 | 930000 | 2170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 847133 | 254140 | 592993 | 900000 | 270000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 4872 | 1462 | 3410 | 23000 | 6900 | 16100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 100802 | 30241 | 70561 | 210000 | 63000 | 147000 | 9990570 | 2997171 | 6993399 | 5641246 | 1692374 | 3948872 | 6954000 | 2086200 | 4867800 | 9990570 | 2997171 | 6993399 | 5641246 | 1692374 | 3948872 | 6954000 | 2086200 | 4867800 | 0 | 286 | Rockbridge, County of
NT10BIX5570129 | INF | 2012 | Q4 | Q4 - 2012 | 2239010 | 0 | 2239010 | 1202977 | 360893 | 842084 | 1600000 | 480000 | 1120000 | 2973056 | 497171 | 2475885 | 1372711 | 411813 | 960898 | 2000000 | 600000 | 1400000 | 35150 | 0 | 35150 | 20517 | 6155 | 14362 | 21500 | 6450 | 15050 | 3219000 | 2500000 | 719000 | 3092734 | 927821 | 2164913 | 3142734 | 942820 | 2199914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 877235 | 263171 | 614064 | 927000 | 278100 | 648900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 14616 | 4385 | 10231 | 34000 | 10200 | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 138761 | 41628 | 97133 | 210000 | 63000 | 147000 | 9990570 | 2997171 | 6993399 | 6719551 | 2015866 | 4703685 | 7935234 | 2380570 | 5554664 | 9990570 | 2997171 | 6993399 | 6719551 | 2015866 | 4703685 | 7935234 | 2380570 | 5554664 | 0 | 744 | Rockbridge, County of
NT10BIX5570129 | INF | 2013 | Q1 | Q1 - 2013 | 2239010 | 0 | 2239010 | 1474050 | 442215 | 1031835 | 2000000 | 600000 | 1400000 | 2973056 | 497171 | 2475885 | 2096442 | 628933 | 1467509 | 2970000 | 891000 | 2079000 | 35150 | 0 | 35150 | 20806 | 6242 | 14564 | 25000 | 7500 | 17500 | 3219000 | 2500000 | 719000 | 3095820 | 928746 | 2167074 | 3146000 | 943800 | 2202200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 929386 | 278816 | 650570 | 1050000 | 315000 | 735000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 24360 | 7308 | 17052 | 60000 | 18000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 210779 | 63234 | 147545 | 270000 | 81000 | 189000 | 9990570 | 2997171 | 6993399 | 7851643 | 2355494 | 5496149 | 9521000 | 2856300 | 6664700 | 9990570 | 2997171 | 6993399 | 7851643 | 2355494 | 5496149 | 9521000 | 2856300 | 6664700 | 0 | 1382 | Rockbridge, County of
NT10BIX5570129 | INF | 2013 | Q2 | Q2 - 2013 | 2239010 | 0 | 2239010 | 1525054 | 457516 | 1067538 | 1569042 | 470713 | 1098329 | 2973056 | 497171 | 2475885 | 3061709 | 918513 | 2143196 | 3643024 | 1092907 | 2550117 | 35150 | 0 | 35150 | 21679 | 6504 | 15175 | 35150 | 10545 | 24605 | 3219000 | 2500000 | 719000 | 3117589 | 935277 | 2182312 | 3219000 | 965700 | 2253300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 996862 | 299059 | 697803 | 1089718 | 326915 | 762803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 48720 | 14616 | 34104 | 73316 | 21995 | 51321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 213215 | 63963 | 149252 | 361320 | 108396 | 252924 | 9990570 | 2997171 | 6993399 | 8984828 | 2695448 | 6289380 | 9990570 | 2997171 | 6993399 | 9990570 | 2997171 | 6993399 | 8984828 | 2695448 | 6289380 | 9990570 | 2997171 | 6993399 | 0 | 2019 | Rockbridge, County of
NT10BIX5570129 | INF | 2013 | Q3 | Q3 - 2013 | 1569042 | 470713 | 1098329 | 1569042 | 470713 | 1098329 | 1569042 | 470713 | 1098329 | 3731516 | 1119455 | 2612061 | 3731516 | 1119454 | 2612062 | 3731516 | 1119454 | 2612062 | 35292 | 11730 | 23562 | 24923 | 6622 | 17446 | 24923 | 6622 | 17446 | 3217789 | 965337 | 2252452 | 3217789 | 965337 | 2252452 | 3217789 | 965337 | 2252452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088379 | 326514 | 761865 | 1086854 | 326056 | 760797 | 1086854 | 326056 | 760797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 22411 | 52293 | 74704 | 22411 | 52293 | 74704 | 22411 | 52293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279030 | 86193 | 192837 | 287251 | 89803 | 197448 | 287251 | 89803 | 197448 | 9995752 | 3002353 | 6993399 | 9992079 | 3000396 | 6990827 | 9992079 | 3000396 | 6990827 | 9995752 | 3002353 | 6993399 | 9992079 | 3000396 | 6990827 | 9992079 | 3000396 | 6990827 | 0 | 5182 | Rockbridge, County of
NT10BIX5570130 | INF | 2010 | Q4 | Q4 - 2010 | 21306005 | 6668780 | 14637225 | 291170 | 164263 | 126907 | 1542349 | 497702 | 1044647 | 1371989 | 429433 | 942557 | 0 | 0 | 0 | 301837 | 94475 | 207362 | 1234225 | 386312 | 847913 | 193751 | 0 | 193751 | 302687 | 0 | 302687 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 354200 | 110865 | 243335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 0 | 0 | 0 | 60000 | 0 | 60000 | 10399126 | 3254926 | 7144199 | 886296 | 566960 | 319336 | 2069982 | 729706 | 1340276 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 22217 | 6954 | 15263 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 128367 | 0 | 128367 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 10162 | 0 | 10162 | 1575896 | 488207 | 1087689 | 86256980 | 26998436 | 59258544 | 1381379 | 731223 | 650156 | 6357535 | 1927909 | 4429626 | 86256980 | 26998436 | 59258544 | 1381379 | 731223 | 650156 | 6357535 | 1927909 | 4429626 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2011 | Q1 | Q1 - 2011 | 21306005 | 6668780 | 14637225 | 329613 | 194263 | 299613 | 4030000 | 1261390 | 2768610 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 301837 | 94475 | 207362 | 1234225 | 386312 | 847913 | 359194 | 6000 | 359194 | 502687 | 157341 | 345346 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 0 | 0 | 0 | 0 | 0 | 0 | 10399125 | 3254926 | 7144199 | 1823533 | 566960 | 1256573 | 2769033 | 866707 | 1902326 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 22217 | 6954 | 15263 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2140000 | 669820 | 1470180 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 10737 | 0 | 10737 | 0 | 986511 | 2165281 | 86256980 | 26998436 | 59258544 | 2523077 | 767223 | 1926117 | 10029774 | 4125830 | 9055736 | 86256980 | 26998436 | 59258544 | 2523077 | 767223 | 1926117 | 10029774 | 4125830 | 9055736 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2011 | Q2 | Q2 - 2011 | 21306005 | 6668780 | 14637225 | 544646 | 205738 | 338908 | 4150900 | 1299232 | 2851668 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 322965 | 101088 | 221877 | 1234225 | 386312 | 847913 | 520764 | 7000 | 513764 | 544578 | 170453 | 374125 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 60000 | 0 | 60000 | 0 | 0 | 60000 | 10399125 | 3254926 | 7144199 | 2404797 | 566960 | 1837837 | 3156697 | 988046 | 2168651 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 23994 | 7510 | 16484 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2204200 | 689915 | 1514285 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 15364 | 0 | 15364 | 3309381 | 1035836 | 2273545 | 86256980 | 26998436 | 59258544 | 3545571 | 779698 | 2765873 | 13976715 | 4374712 | 9662003 | 86256980 | 26998436 | 59258544 | 3545571 | 779698 | 2765873 | 13976715 | 4374712 | 9662003 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2011 | Q3 | Q3 - 2011 | 21306005 | 6668780 | 14637225 | 4994155 | 2306786 | 2687369 | 9472217 | 2936387 | 6535830 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 322965 | 101088 | 221877 | 1234225 | 386312 | 847913 | 622389 | 7000 | 615389 | 1039151 | 322137 | 717014 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 79835 | 0 | 79835 | 79835 | 18780 | 60755 | 10399125 | 3254926 | 7144199 | 3488353 | 566960 | 2921393 | 5804273 | 1799325 | 4004948 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 23994 | 7510 | 16484 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2204200 | 689915 | 1514285 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 15932 | 0 | 15932 | 3309949 | 1035836 | 2274113 | 86256980 | 26998436 | 59258544 | 9200664 | 2880746 | 6319918 | 22520584 | 6993610 | 15526674 | 86256980 | 26998436 | 59258544 | 9200664 | 2880746 | 6319918 | 22520584 | 6993610 | 15526674 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2011 | Q4 | Q4 - 2011 | 22470612 | 6668780 | 15801832 | 2979111 | 365524 | 2613587 | 17642460 | 2690300 | 14952160 | 1371989 | 429433 | 942556 | 0 | 0 | 0 | 439364 | 66999 | 372365 | 1761710 | 386312 | 1375398 | 872079 | 0 | 872079 | 1597687 | 243631 | 1354056 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 106000 | 16164 | 89836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 35948 | 5482 | 30466 | 10379021 | 3254926 | 7124095 | 4757362 | 567019 | 4190343 | 7285453 | 1110959 | 6174494 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 87873 | 13400 | 74473 | 19589925 | 6006703 | 13583222 | 846714 | 7000 | 839714 | 7589014 | 1157249 | 6431764 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 945040 | 15278 | 929762 | 5158378 | 786601 | 4371778 | 86256980 | 26998436 | 59258544 | 10400306 | 954821 | 9445485 | 39942177 | 6090785 | 33851392 | 86256980 | 26998436 | 59258544 | 10400306 | 954821 | 9445485 | 39942177 | 6090785 | 33851392 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2012 | Q1 | Q1 - 2012 | 22470612 | 6668780 | 15801832 | 2988430 | 365524 | 2622906 | 7060188 | 1590458 | 5469730 | 1371989 | 429433 | 942556 | 0 | 0 | 0 | 460547 | 27893 | 432654 | 1761710 | 386312 | 1375398 | 1038207 | 0 | 1038207 | 1097721 | 59514 | 1038207 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 35333 | 29945 | 5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 11982 | 1827 | 10155 | 10379021 | 3254926 | 7124095 | 5362620 | 567019 | 4795601 | 5760749 | 965148 | 4795601 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 31087 | 6263 | 24824 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 2086908 | 655255 | 1431653 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 3674151 | 439477 | 3234674 | 86256980 | 26998436 | 59258544 | 12013446 | 954821 | 11058625 | 20218666 | 3775780 | 16442886 | 86256980 | 26998436 | 59258544 | 12013446 | 954821 | 11058625 | 20218666 | 3775780 | 16442886 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2012 | Q2 | Q2 - 2012 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 7122130 | 1590458 | 5531672 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 660547 | 27893 | 632654 | 1761710 | 386312 | 1375398 | 1375232 | 0 | 1375232 | 1434485 | 59253 | 1375232 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 35333 | 29945 | 5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 11982 | 1827 | 10155 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5831217 | 965148 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 31087 | 6263 | 24824 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 2086908 | 655255 | 1431653 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 3674151 | 439477 | 3234674 | 86256980 | 26998436 | 59258544 | 12682881 | 954821 | 11728060 | 20887840 | 3775519 | 17112321 | 86256980 | 26998436 | 59258544 | 12682881 | 954821 | 11728060 | 20887840 | 3775519 | 17112321 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2012 | Q3 | Q3 - 2012 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 3050372 | 365524 | 2684848 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 200000 | 0 | 200000 | 1761710 | 386312 | 1375398 | 1509876 | 0 | 1509876 | 1614443 | 0 | 1614443 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 0 | 0 | 0 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5433088 | 567019 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 0 | 0 | 0 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 1262765 | 7000 | 1255765 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 1361424 | 15278 | 1346146 | 86256980 | 26998436 | 59258544 | 12817525 | 954821 | 11862704 | 12922092 | 954821 | 11967271 | 86256980 | 26998436 | 59258544 | 12817525 | 954821 | 11862704 | 12922092 | 954821 | 11967271 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2012 | Q4 | Q4 - 2012 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 3050372 | 365524 | 2684848 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 200000 | 0 | 200000 | 1761710 | 386312 | 1375398 | 1579717 | 0 | 1579717 | 1684284 | 0 | 1684284 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 0 | 0 | 0 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5433088 | 567019 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 0 | 0 | 0 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 1262765 | 7000 | 1255765 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 1361424 | 15278 | 1346146 | 86256980 | 26998436 | 59258544 | 12887366 | 954821 | 11932545 | 12991933 | 954821 | 12037112 | 86256980 | 26998436 | 59258544 | 12887366 | 954821 | 11932545 | 12991933 | 954821 | 12037112 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2013 | Q1 | Q1 - 2013 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 3050372 | 365524 | 2684848 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 200000 | 0 | 200000 | 1761710 | 386312 | 1375398 | 1678455 | 0 | 1678455 | 1783022 | 0 | 1783022 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 0 | 0 | 0 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5433088 | 567019 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 0 | 0 | 0 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 1262765 | 7000 | 1255765 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 1361424 | 15278 | 1346146 | 86256980 | 26998436 | 59258544 | 12986104 | 954821 | 12031283 | 13090671 | 954821 | 12135850 | 86256980 | 26998436 | 59258544 | 12986104 | 954821 | 12031283 | 13090671 | 954821 | 12135850 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570130 | INF | 2013 | Q2 | Q2 - 2013 | 22470612 | 6668780 | 15801832 | 2341248 | 365524 | 1975724 | 2341248 | 365524 | 1975724 | 1371989 | 429433 | 942556 | 200882 | 0 | 200882 | 200882 | 0 | 200882 | 1761710 | 386312 | 1375398 | 1953160 | 0 | 1953160 | 1953160 | 0 | 1953160 | 349577 | 316756 | 32821 | 573157 | 573157 | 0 | 573157 | 573157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 0 | 0 | 0 | 10379021 | 3254926 | 7124095 | 4673036 | 567019 | 4106017 | 4673036 | 567019 | 4106017 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 0 | 0 | 0 | 19589925 | 6006703 | 13583222 | 1319624 | 7000 | 1312624 | 1319624 | 7000 | 1312624 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1039438 | 15278 | 1024160 | 1039438 | 15278 | 1024160 | 86256980 | 26998436 | 59258544 | 12100545 | 1527978 | 10572567 | 12100545 | 1527978 | 10572567 | 86256980 | 26998436 | 59258544 | 12100545 | 1527978 | 10572567 | 12100545 | 1527978 | 10572567 | 0 | 0 | Trillion Communications Corp.
NT10BIX5570131 | INF | 2010 | Q4 | Q4 - 2010 | 3709590 | 741918 | 2967672 | 0 | 0 | 0 | 2448 | 490 | 1958 | 25805608 | 5161122 | 20644486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 0 | 0 | 0 | 727283 | 145456 | 581827 | 1290280 | 258056 | 1032224 | 0 | 0 | 0 | 107560 | 21512 | 86048 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 0 | 0 | 0 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 0 | 0 | 0 | 837291 | 167458 | 669833 | 36031695 | 7206339 | 28825356 | 0 | 0 | 0 | 837291 | 167458 | 669833 | 0 | 0 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2011 | Q1 | Q1 - 2011 | 3709590 | 741918 | 2967672 | 2448 | 490 | 1958 | 2448 | 490 | 1958 | 25805608 | 5161122 | 20644486 | 0 | 0 | 0 | 1599032 | 319806 | 1279226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 0 | 0 | 0 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 603420 | 120684 | 482736 | 1041331 | 208266 | 833065 | 1290280 | 258056 | 1032224 | 188119 | 37624 | 150495 | 753349 | 150670 | 602679 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 796438 | 159288 | 637150 | 3571801 | 714360 | 2857441 | 36031695 | 7206339 | 28825356 | 796438 | 159288 | 637150 | 3571801 | 714360 | 2857441 | 0 | 0 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2011 | Q2 | Q2 - 2011 | 3709590 | 741918 | 2967672 | 3811 | 762 | 3049 | 3811 | 762 | 3049 | 25805608 | 5161122 | 20644486 | 792397 | 158480 | 633917 | 1599032 | 319806 | 1279226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 15725 | 3145 | 12580 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 882836 | 176567 | 706269 | 1041331 | 208266 | 833065 | 1290280 | 258056 | 1032224 | 70881 | 14176 | 56705 | 753349 | 150670 | 602679 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 1768101 | 353620 | 1414481 | 3573164 | 714632 | 2858532 | 36031695 | 7206339 | 28825356 | 1768101 | 353620 | 1414481 | 3573164 | 714632 | 2858532 | 0 | 0 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2011 | Q3 | Q3 - 2011 | 3709590 | 741918 | 2967672 | 974670 | 194934 | 779736 | 1124670 | 224934 | 899736 | 25805608 | 5161122 | 20644486 | 1948066 | 389613 | 1558453 | 3698066 | 739613 | 2958453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 16225 | 3245 | 12980 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1215205 | 243041 | 972164 | 1590205 | 318041 | 1272164 | 1290280 | 258056 | 1032224 | 83381 | 16676 | 66705 | 83381 | 16676 | 66705 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 9357 | 1872 | 7485 | 9357 | 1871 | 7485 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 4249355 | 849871 | 3399484 | 6681320 | 1336263 | 5345056 | 36031695 | 7206339 | 28825356 | 4249355 | 849871 | 3399484 | 6681320 | 1336263 | 5345056 | 0 | 0 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2011 | Q4 | Q4 - 2011 | 3709590 | 741918 | 2967672 | 1007147 | 201429 | 805718 | 1261261 | 252252 | 1009009 | 25805608 | 5161122 | 20644486 | 4329112 | 865822 | 3463290 | 6451402 | 1290280 | 5161122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 21050 | 4210 | 16840 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1374108 | 274823 | 1099285 | 1459948 | 291989 | 1167959 | 1290280 | 258056 | 1032224 | 83381 | 16676 | 66705 | 221764 | 44353 | 177411 | 950297 | 190059 | 760238 | 152678 | 30536 | 122142 | 166323 | 33265 | 133058 | 192000 | 38400 | 153600 | 15763 | 3152 | 12611 | 19200 | 3840 | 15360 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841 | 568 | 2273 | 2841 | 568 | 2273 | 36031695 | 7206339 | 28825356 | 6986080 | 1397216 | 5588864 | 9625124 | 1925024 | 7700100 | 36031695 | 7206339 | 28825356 | 6986080 | 1397216 | 5588864 | 9625124 | 1925024 | 7700100 | 0 | 0 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2012 | Q1 | Q1 - 2012 | 3709590 | 741918 | 2967672 | 1012050 | 202410 | 809640 | 1261000 | 252200 | 1008800 | 25805608 | 5161122 | 20644486 | 6478956 | 1295792 | 5183164 | 8250500 | 1650100 | 6600400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 25950 | 5190 | 20760 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1623834 | 324766 | 1299068 | 1772100 | 354420 | 1417680 | 1290280 | 258056 | 1032224 | 132875 | 26575 | 106300 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 159259 | 31852 | 127407 | 187150 | 37430 | 149720 | 192000 | 38400 | 153600 | 26053 | 5211 | 20842 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841 | 568 | 2273 | 2841 | 568 | 2273 | 36031695 | 7206339 | 28825356 | 9461818 | 1892364 | 7569454 | 11760663 | 2352132 | 9408531 | 36031695 | 7206339 | 28825356 | 9461818 | 1892364 | 7569454 | 11760663 | 2352132 | 9408531 | 0 | 5845 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2012 | Q2 | Q2 - 2012 | 3709590 | 741918 | 2967672 | 1215672 | 243134 | 972538 | 1602561 | 320512 | 1282049 | 25805608 | 5161122 | 20644486 | 8648849 | 1729770 | 6919079 | 10952640 | 2190527 | 8762113 | 0 | 0 | 0 | 8430 | 1686 | 6744 | 8430 | 1686 | 6744 | 1012000 | 202400 | 809600 | 35300 | 7060 | 28240 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 2054410 | 410882 | 1643528 | 2443306 | 488662 | 1954644 | 1290280 | 258056 | 1032224 | 132875 | 26575 | 106300 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 159259 | 31852 | 127407 | 218720 | 43744 | 174976 | 192000 | 38400 | 153600 | 26053 | 5211 | 20842 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 12280848 | 2456170 | 9824678 | 15512729 | 3102545 | 12410184 | 36031695 | 7206339 | 28825356 | 12280848 | 2456170 | 9824678 | 15512729 | 3102545 | 12410184 | 0 | 32730 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2012 | Q3 | Q3 - 2012 | 3709590 | 741918 | 2967672 | 1421087 | 284217 | 1136870 | 1668300 | 333650 | 1334650 | 25805608 | 5161122 | 20644486 | 12320187 | 2464037 | 9856150 | 15780508 | 3156112 | 12624396 | 0 | 0 | 0 | 8430 | 1686 | 6744 | 8430 | 1686 | 6744 | 1012000 | 202400 | 809600 | 35300 | 7060 | 28240 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 2497678 | 499536 | 1998142 | 3203000 | 640600 | 2562400 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 277519 | 55504 | 222015 | 311390 | 62278 | 249112 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 16749478 | 3349896 | 13399582 | 21258700 | 4251740 | 17006960 | 36031695 | 7206339 | 28825356 | 16749478 | 3349896 | 13399582 | 21258700 | 4251740 | 17006960 | 0 | 155652 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2012 | Q4 | Q4 - 2012 | 3709590 | 741918 | 2967672 | 1629668 | 325933 | 1303735 | 1904668 | 380935 | 1523733 | 25805608 | 5161122 | 20644486 | 15173419 | 3034684 | 12138735 | 18923420 | 3784684 | 15138736 | 0 | 0 | 0 | 9119 | 1824 | 7295 | 19119 | 3823 | 15296 | 1012000 | 202400 | 809600 | 37300 | 7460 | 29840 | 46800 | 9360 | 37440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 3042997 | 608599 | 2434398 | 3676752 | 735350 | 2941402 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 163043 | 32609 | 130434 | 950297 | 190059 | 760238 | 338110 | 67622 | 270488 | 379356 | 75871 | 303485 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 33633 | 6726 | 26907 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 20419890 | 4083978 | 16335912 | 25146791 | 5029358 | 20117433 | 36031695 | 7206339 | 28825356 | 20419890 | 4083978 | 16335912 | 25146791 | 5029358 | 20117433 | 0 | 373013 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2013 | Q1 | Q1 - 2013 | 3709590 | 741918 | 2967672 | 1839204 | 367841 | 1471363 | 2575000 | 515000 | 2060000 | 25805608 | 5161122 | 20644486 | 18480957 | 3696190 | 14784767 | 23730000 | 4746000 | 18984000 | 0 | 0 | 0 | 9119 | 1824 | 7295 | 19119 | 3823 | 15296 | 1012000 | 202400 | 809600 | 58002 | 11600 | 46402 | 75300 | 15060 | 60240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 3505465 | 701093 | 2804372 | 4005000 | 801000 | 3204000 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 163044 | 32609 | 130435 | 950297 | 190059 | 760238 | 378013 | 75603 | 302410 | 485300 | 97060 | 388240 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 24460037 | 4892007 | 19568030 | 31090263 | 6218052 | 24872211 | 36031695 | 7206339 | 28825356 | 24460037 | 4892007 | 19568030 | 31090263 | 6218052 | 24872211 | 0 | 645222 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2013 | Q2 | Q2 - 2013 | 2869590 | 573918 | 2295672 | 2838488 | 567697 | 2270791 | 2869590 | 573918 | 2295672 | 27237608 | 5447522 | 21790086 | 24172400 | 4834479 | 19337921 | 27237608 | 5447522 | 21790086 | 10000 | 2000 | 8000 | 9164 | 1834 | 7330 | 10000 | 2000 | 8000 | 77000 | 15400 | 61600 | 75455 | 15091 | 60364 | 77000 | 15400 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171920 | 834384 | 3337536 | 3726193 | 745239 | 2980954 | 4171920 | 834384 | 3337536 | 840280 | 168056 | 672224 | 408608 | 81722 | 326886 | 840280 | 168056 | 672224 | 750297 | 150059 | 600238 | 456343 | 91268 | 365075 | 750297 | 150059 | 600238 | 75000 | 15000 | 60000 | 73233 | 14647 | 58586 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 31759884 | 6351977 | 25407907 | 36031695 | 7206339 | 28825356 | 36031695 | 7206339 | 28825356 | 31759884 | 6351977 | 25407907 | 36031695 | 7206339 | 28825356 | 0 | 1070533 | Peoples Telephone Cooperative Inc.
NT10BIX5570131 | INF | 2013 | Q3 | Q3 - 2013 | 2900636 | 580128 | 2320508 | 2906600 | 586091 | 2320508 | 2906600 | 586091 | 2320508 | 28069887 | 5613978 | 22455909 | 28072209 | 5616300 | 22455909 | 28072209 | 5616300 | 22455909 | 9164 | 1834 | 7330 | 9164 | 1834 | 7330 | 9164 | 1834 | 7330 | 84875 | 16975 | 67900 | 84875 | 16975 | 67900 | 84875 | 16975 | 67900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3687828 | 737564 | 2950264 | 3967124 | 1016861 | 2950264 | 3967124 | 1016861 | 2950264 | 618406 | 123681 | 494725 | 618406 | 123681 | 494725 | 618406 | 123681 | 494725 | 583142 | 116628 | 466514 | 583142 | 116628 | 466514 | 583142 | 116628 | 466514 | 77757 | 15551 | 62206 | 77757 | 15551 | 62206 | 77757 | 15551 | 62206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 36319277 | 7493921 | 28825356 | 36319277 | 7493921 | 28825356 | 36031695 | 7206339 | 28825356 | 36319277 | 7493921 | 28825356 | 36319277 | 7493921 | 28825356 | 0 | 1564739 | Peoples Telephone Cooperative Inc.
NT10BIX5570132 | INF | 2010 | Q4 | Q4 - 2010 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 0 | 0 | 0 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 23515451 | 7054635 | 16460815 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2011 | Q1 | Q1 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 0 | 0 | 0 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 23515451 | 7054635 | 16460815 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2011 | Q2 | Q2 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 478839 | 143652 | 335187 | 762368 | 228711 | 533657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 478839 | 143652 | 335187 | 962368 | 288711 | 673657 | 23515451 | 7054635 | 16460815 | 478839 | 143652 | 335187 | 962368 | 288711 | 673657 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2011 | Q3 | Q3 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 643745 | 193123 | 450622 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 2459130 | 737739 | 1721391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 581570 | 174471 | 407099 | 940352 | 282106 | 658246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 581570 | 174471 | 407099 | 4043227 | 1212968 | 2830259 | 23515451 | 7054635 | 16460815 | 581570 | 174471 | 407099 | 4043227 | 1212968 | 2830259 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2011 | Q4 | Q4 - 2011 | 4519951 | 1355985 | 3163965 | 479073 | 143722 | 335351 | 1659934 | 497980 | 1161954 | 15690500 | 4707150 | 10983350 | 263102 | 78931 | 184171 | 4247732 | 1274320 | 2973412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 744136 | 223241 | 520895 | 1694000 | 508200 | 1185800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 1486311 | 445894 | 1040417 | 7601666 | 2280500 | 5321166 | 23515451 | 7054635 | 16460815 | 1486311 | 445894 | 1040417 | 7601666 | 2280500 | 5321166 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2012 | Q1 | Q1 - 2012 | 4519951 | 1355985 | 3163965 | 1997859 | 599358 | 1398501 | 3750000 | 1125000 | 2625000 | 15690500 | 4707150 | 10983350 | 2098223 | 629467 | 1468756 | 7500000 | 2250000 | 5250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 46867 | 14060 | 32807 | 195000 | 58500 | 136500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 1069013 | 320704 | 748309 | 1750000 | 525000 | 1225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 5211962 | 1563589 | 3648373 | 13195000 | 3958500 | 9236500 | 23515451 | 7054635 | 16460815 | 5211962 | 1563589 | 3648373 | 13195000 | 3958500 | 9236500 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2012 | Q2 | Q2 - 2012 | 4304863 | 1291459 | 3013404 | 2352600 | 705780 | 1646820 | 3442270 | 1032681 | 2409589 | 15424113 | 4627234 | 10796879 | 5309813 | 1592944 | 3716869 | 10723753 | 3217126 | 7506627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 807064 | 242119 | 564945 | 295618 | 88685 | 206933 | 807064 | 242119 | 564945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 1494236 | 448271 | 1045965 | 2459572 | 737872 | 1721700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 9452267 | 2835680 | 6616587 | 17432659 | 5229798 | 12202861 | 23515451 | 7054635 | 16460816 | 9452267 | 2835680 | 6616587 | 17432659 | 5229798 | 12202861 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2012 | Q3 | Q3 - 2012 | 4304863 | 1291459 | 3013404 | 3092270 | 927681 | 2164589 | 3817270 | 1145181 | 2672089 | 15424113 | 4627234 | 10796879 | 8896390 | 2668917 | 6227473 | 12146390 | 3643917 | 8502473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 807064 | 242119 | 564945 | 792675 | 237803 | 554873 | 807064 | 242119 | 564945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 2139588 | 641876 | 1497712 | 2589588 | 776876 | 1812712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 14920923 | 4476277 | 10444647 | 19360312 | 5808093 | 13552219 | 23515451 | 7054635 | 16460816 | 14920923 | 4476277 | 10444647 | 19360312 | 5808093 | 13552219 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2012 | Q4 | Q4 - 2012 | 4273040 | 1281912 | 2991128 | 3142319 | 942696 | 2199623 | 4059388 | 1217816 | 2841572 | 15424113 | 4627234 | 10796879 | 9906507 | 2971952 | 6934555 | 13418978 | 4025693 | 9393285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 2490617 | 747185 | 1743432 | 2830440 | 849132 | 1981308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 16378330 | 4913499 | 11464831 | 21147693 | 6344307 | 14803386 | 23515451 | 7054635 | 16460816 | 16378330 | 4913499 | 11464831 | 21147693 | 6344307 | 14803386 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2013 | Q1 | Q1 - 2013 | 4518939 | 1355682 | 3163257 | 3319560 | 995868 | 2323692 | 4518939 | 1355682 | 3163257 | 14485517 | 4345655 | 10139862 | 11549419 | 3464826 | 8084593 | 13761241 | 4128372 | 9632869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 2768727 | 830618 | 1938109 | 3304897 | 991469 | 2313428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 18476593 | 5542978 | 12933615 | 22423964 | 6727189 | 15696775 | 23515451 | 7054635 | 16460816 | 18476593 | 5542978 | 12933615 | 22423964 | 6727189 | 15696775 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2013 | Q2 | Q2 - 2013 | 4518939 | 1355682 | 3163257 | 3991493 | 1197448 | 2794045 | 4518939 | 1355682 | 3163257 | 14485517 | 4345655 | 10139862 | 13775994 | 4132798 | 9643196 | 14485517 | 4345655 | 10139862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 3562670 | 1068801 | 2493869 | 3672108 | 1101632 | 2570476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 22169044 | 6650713 | 15518331 | 23515451 | 7054635 | 16460816 | 23515451 | 7054635 | 16460816 | 22169044 | 6650713 | 15518331 | 23515451 | 7054635 | 16460816 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570132 | INF | 2013 | Q3 | Q3 - 2013 | 4518939 | 1355682 | 3163257 | 4326826 | 1163569 | 3163257 | 4326826 | 1163569 | 3163257 | 14485517 | 4345656 | 10139861 | 14686116 | 4546255 | 10139861 | 14686116 | 4546255 | 10139861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 3727743 | 1157267 | 2570476 | 3727743 | 1157267 | 2570476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054636 | 16460815 | 23579572 | 7118757 | 16460815 | 23579572 | 7118757 | 16460815 | 23515451 | 7054636 | 16460815 | 23579572 | 7118757 | 16460815 | 23579572 | 7118757 | 16460815 | 0 | 0 | E.N.M.R. Telephone Cooperative
NT10BIX5570133 | INF | 2010 | Q3 | Q3 - 2010 | 5598140 | 1119628 | 4478512 | 0 | 0 | 0 | 558700 | 111740 | 446960 | 37772032 | 7554407 | 30217626 | 215145 | 43029 | 172116 | 491448 | 98291 | 393158 | 1030440 | 206088 | 824352 | 31813 | 6363 | 25450 | 115032 | 23006 | 92026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 64216 | 12843 | 51373 | 294167 | 58833 | 235333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 0 | 0 | 0 | 4907 | 981 | 3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 311174 | 62235 | 248939 | 1464254 | 292851 | 1171403 | 48673735 | 9734747 | 38938988 | 311174 | 62235 | 248939 | 1464254 | 292851 | 1171403 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2010 | Q4 | Q4 - 2010 | 5598140 | 1119628 | 4478512 | 558700 | 111740 | 446960 | 558700 | 111740 | 446960 | 37772032 | 7554407 | 30217626 | 491448 | 98290 | 393158 | 2493611 | 498722 | 1994889 | 1030440 | 206088 | 824352 | 115032 | 23007 | 92026 | 198251 | 39650 | 158601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 294167 | 58833 | 235333 | 753481 | 150696 | 602785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 4907 | 981 | 3926 | 4907 | 981 | 3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 1464254 | 292851 | 1171403 | 4008950 | 801789 | 3207161 | 48673735 | 9734747 | 38938988 | 1464254 | 292851 | 1171403 | 4008950 | 801789 | 3207161 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2011 | Q1 | Q1 - 2011 | 5598140 | 1119628 | 4478512 | 251784 | 50357 | 201427 | 1187300 | 237460 | 949840 | 37772032 | 7554407 | 30217626 | 1492401 | 298480 | 1193921 | 4833642 | 966728 | 3866913 | 1030440 | 206088 | 824352 | 177581 | 35516 | 142065 | 281470 | 56294 | 225176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 585004 | 117001 | 468003 | 909675 | 181935 | 727740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 86554 | 17311 | 69244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 2507018 | 501404 | 2005614 | 7298641 | 1459728 | 5838913 | 48673735 | 9734747 | 38938988 | 2507018 | 501404 | 2005614 | 7298641 | 1459728 | 5838913 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2011 | Q2 | Q2 - 2011 | 5598140 | 1119628 | 4478512 | 258621 | 51724 | 206897 | 1315100 | 263020 | 1052080 | 37772032 | 7554407 | 30217626 | 3116387 | 623278 | 2493110 | 7756073 | 1551215 | 6204858 | 1030440 | 206088 | 824352 | 258137 | 51627 | 206509 | 364689 | 72938 | 291751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 878355 | 175671 | 702684 | 1077210 | 215442 | 861768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 166900 | 33380 | 133520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 4511748 | 902350 | 3609398 | 10679972 | 2135995 | 8543977 | 48673735 | 9734747 | 38938988 | 4511748 | 902350 | 3609398 | 10679972 | 2135995 | 8543977 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2011 | Q3 | Q3 - 2011 | 5598140 | 1119628 | 4478512 | 381335 | 76267 | 305068 | 1454960 | 290992 | 1163968 | 37772032 | 7554407 | 30217626 | 6115183 | 1223036 | 4892147 | 11319659 | 2263932 | 9055727 | 1030440 | 206088 | 824352 | 329516 | 65903 | 263613 | 447908 | 89582 | 358326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1330560 | 266112 | 1064448 | 1500000 | 300000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 285729 | 57146 | 228583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 8156842 | 1631368 | 6525474 | 15008256 | 3001652 | 12006604 | 48673735 | 9734747 | 38938988 | 8156842 | 1631368 | 6525474 | 15008256 | 3001652 | 12006604 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2011 | Q4 | Q4 - 2011 | 5598140 | 1119628 | 4478512 | 1977085 | 395417 | 1581668 | 2500000 | 500000 | 2000000 | 37772032 | 7554407 | 30217626 | 9334208 | 1866841 | 7467366 | 13757134 | 2751427 | 11005707 | 1030440 | 206088 | 824352 | 431028 | 86205 | 344822 | 531126 | 106225 | 424901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1568728 | 313746 | 1254983 | 1700000 | 340000 | 1360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 366348 | 73270 | 293079 | 411225 | 82245 | 328980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 13677397 | 2735479 | 10941918 | 18899485 | 3779897 | 15119588 | 48673735 | 9734747 | 38938988 | 13677397 | 2735479 | 10941918 | 18899485 | 3779897 | 15119588 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2012 | Q1 | Q1 - 2012 | 5598140 | 1119628 | 4478512 | 2819230 | 563846 | 2255384 | 4620620 | 924124 | 3696496 | 37772032 | 7554407 | 30217626 | 13140533 | 2628107 | 10512426 | 18573659 | 3714732 | 14858927 | 1030440 | 206088 | 824352 | 484377 | 96875 | 387502 | 614345 | 122869 | 491476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1915710 | 383142 | 1532568 | 2147342 | 429468 | 1717874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 456386 | 91277 | 365109 | 530425 | 106085 | 424340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 18816236 | 3763247 | 15052989 | 26486391 | 5297278 | 21189113 | 48673735 | 9734747 | 38938988 | 18816236 | 3763247 | 15052989 | 26486391 | 5297278 | 21189113 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2012 | Q2 | Q2 - 2012 | 5598140 | 1119628 | 4478512 | 4152719 | 830544 | 3322175 | 4251620 | 850324 | 3401296 | 37772032 | 7554407 | 30217626 | 16252550 | 3250510 | 13002040 | 22923701 | 4584740 | 18338961 | 1030440 | 206088 | 824352 | 548749 | 109750 | 438999 | 697565 | 139513 | 558052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 2216072 | 443214 | 1772858 | 2651934 | 530387 | 2121547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 932686 | 186537 | 746149 | 946626 | 189325 | 757301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 24102776 | 4820555 | 19282221 | 31471446 | 6294289 | 25177157 | 48673735 | 9734747 | 38938988 | 24102776 | 4820555 | 19282221 | 31471446 | 6294289 | 25177157 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2012 | Q3 | Q3 - 2012 | 5598140 | 1119628 | 4478512 | 7120560 | 1424112 | 5696448 | 7494680 | 1498936 | 5995744 | 37772032 | 7554407 | 30217626 | 20082680 | 4016536 | 16066144 | 23247659 | 4649532 | 18598127 | 1030440 | 206088 | 824352 | 659870 | 131974 | 527896 | 780784 | 156157 | 624627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 2532516 | 506503 | 2026013 | 2859730 | 571946 | 2287784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 1745565 | 349113 | 1396452 | 1830626 | 366125 | 1464501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 32141191 | 6428238 | 25712953 | 36213479 | 7242696 | 28970783 | 48673735 | 9734747 | 38938988 | 32141191 | 6428238 | 25712953 | 36213479 | 7242696 | 28970783 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2012 | Q4 | Q4 - 2012 | 8746002 | 1749200 | 6996801 | 8093945 | 1618789 | 6475156 | 8353302 | 1670661 | 6682641 | 32512638 | 6502528 | 26010111 | 21252249 | 4250449 | 17001800 | 24612850 | 4922570 | 19690280 | 1023794 | 204759 | 819035 | 778074 | 155615 | 622459 | 870469 | 174094 | 696375 | 24093 | 4819 | 19274 | 28654 | 5731 | 22923 | 28654 | 5731 | 22923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 2853908 | 570782 | 2283126 | 3074017 | 614803 | 2459214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2584734 | 516947 | 2067787 | 2888979 | 577796 | 2311183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 35591564 | 7118313 | 28473251 | 39828271 | 7965655 | 31862616 | 48673735 | 9734747 | 38938988 | 35591564 | 7118313 | 28473251 | 39828271 | 7965655 | 31862616 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2013 | Q1 | Q1 - 2013 | 8746002 | 1749200 | 6996801 | 8464485 | 1692897 | 6771588 | 8633395 | 1726679 | 6906716 | 32512638 | 6502528 | 26010111 | 26163620 | 5232724 | 20930896 | 29973031 | 5994606 | 23978425 | 1023794 | 204759 | 819035 | 910736 | 182147 | 728589 | 978571 | 195714 | 782857 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 3072536 | 614507 | 2458029 | 3251474 | 650294 | 2601180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2758475 | 551695 | 2206780 | 2901255 | 580251 | 2321004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 41393945 | 8278789 | 33115156 | 45761819 | 9152363 | 36609456 | 48673735 | 9734747 | 38938988 | 41393945 | 8278789 | 33115156 | 45761819 | 9152363 | 36609456 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2013 | Q2 | Q2 - 2013 | 8746002 | 1749200 | 6996801 | 8561001 | 1712200 | 6848801 | 8746002 | 1749200 | 6996801 | 32512638 | 6502528 | 26010111 | 29588668 | 5917734 | 23670934 | 32512638 | 6502528 | 26010111 | 1023794 | 204759 | 819035 | 728794 | 145759 | 583035 | 908794 | 181759 | 727035 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 3196541 | 639308 | 2557233 | 3370766 | 674153 | 2696613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2286269 | 457254 | 1829015 | 2996442 | 599288 | 2397154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 44385366 | 8877074 | 35508292 | 48558735 | 9711747 | 38846988 | 48673735 | 9734747 | 38938988 | 44385366 | 8877074 | 35508292 | 48558735 | 9711747 | 38846988 | 0 | 0 | ION Newco Corp
NT10BIX5570133 | INF | 2013 | Q3 | Q3 - 2013 | 8432785 | 1686557 | 6746228 | 9581179 | 2834951 | 6746228 | 9581179 | 2834951 | 6746228 | 32512638 | 6502527 | 26010111 | 31885720 | 5875609 | 26010111 | 31885719 | 5875608 | 26010111 | 1023794 | 204759 | 819035 | 1290178 | 471143 | 819035 | 1290178 | 471143 | 819035 | 24093 | 4819 | 19274 | 31154 | 11880 | 19274 | 31154 | 11880 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 4129468 | 1432855 | 2696613 | 4129468 | 1432855 | 2696613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309659 | 661932 | 2647727 | 5027840 | 2380113 | 2647727 | 5027840 | 2380113 | 2647727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 51945539 | 13006551 | 38938988 | 51945538 | 13006550 | 38938988 | 48673735 | 9734747 | 38938988 | 51945539 | 13006551 | 38938988 | 51945538 | 13006550 | 38938988 | 0 | 0 | ION Newco Corp
NT10BIX5570135 | INF | 2010 | Q4 | Q4 - 2010 | 29211582 | 8888681 | 20322901 | 0 | 0 | 0 | 3505390 | 955384 | 2550006 | 93402141 | 18671661 | 74730480 | 0 | 0 | 0 | 2802064 | 763694 | 2038370 | 12479100 | 7394000 | 5085100 | 468534 | 229900 | 238634 | 2373155 | 646796 | 1726359 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 92793 | 0 | 92793 | 2239049 | 610246 | 1628803 | 6109850 | 2869099 | 3240751 | 25277 | 0 | 25277 | 582635 | 158795 | 423840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 586604 | 229900 | 356704 | 11727293 | 3196238 | 8531055 | 158416521 | 43175940 | 115240581 | 586604 | 229900 | 356704 | 11727293 | 3196238 | 8531055 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2011 | Q1 | Q1 - 2011 | 29211582 | 8888681 | 20322901 | 0 | 0 | 0 | 3505390 | 955384 | 2550006 | 93402141 | 18671661 | 74730480 | 0 | 0 | 0 | 2802064 | 763694 | 2038370 | 12479100 | 7394000 | 5085100 | 778136 | 320980 | 457156 | 2373155 | 646796 | 1726359 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 157905 | 0 | 157905 | 2239049 | 610246 | 1628803 | 6109850 | 2869099 | 3240751 | 169531 | 0 | 169531 | 582635 | 158795 | 423840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 1105572 | 320980 | 784592 | 11727293 | 3196238 | 8531055 | 158416521 | 43175940 | 115240581 | 1105572 | 320980 | 784592 | 11727293 | 3196238 | 8531055 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2011 | Q2 | Q2 - 2011 | 29211582 | 8888681 | 20322901 | 1812078 | 1812078 | 0 | 6124156 | 4124156 | 2000000 | 93402141 | 18671661 | 74730480 | 1032787 | 1032787 | 0 | 4665575 | 2065574 | 2600000 | 12479100 | 7394000 | 5085100 | 1553924 | 561960 | 991964 | 4617848 | 1633920 | 2983928 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 298202 | 0 | 298202 | 1699404 | 480000 | 1219404 | 6109850 | 2869099 | 3240751 | 169531 | 0 | 169531 | 489062 | 0 | 489062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 4866522 | 3406825 | 1459697 | 17821045 | 8364973 | 9456071 | 158416521 | 43175940 | 115240581 | 4866522 | 3406825 | 1459697 | 17821045 | 8364973 | 9456071 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2011 | Q3 | Q3 - 2011 | 29211582 | 8888681 | 20322901 | 5763723 | 2279112 | 3484611 | 6758413 | 2566882 | 4191531 | 93402141 | 18671661 | 74730480 | 5510629 | 2627451 | 2883178 | 14885973 | 4089036 | 10796937 | 12479100 | 7394000 | 5085100 | 2920378 | 1201944 | 1718434 | 4241750 | 1814232 | 2427517 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 337500 | 0 | 337500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 1431855 | 0 | 1431855 | 2640552 | 0 | 2640552 | 6109850 | 2869099 | 3240751 | 812329 | 38225 | 774104 | 2983202 | 835297 | 2147905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 16438914 | 6146732 | 10292182 | 31847390 | 9305447 | 22541942 | 158416521 | 43175940 | 115240581 | 16438914 | 6146732 | 10292182 | 31847390 | 9305447 | 22541942 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2011 | Q4 | Q4 - 2011 | 29211582 | 8888681 | 20322901 | 5794572 | 2278318 | 3516254 | 6337552 | 2635209 | 3702343 | 93402141 | 18671661 | 74730480 | 11579661 | 3118029 | 8461632 | 22436345 | 6638089 | 15798256 | 12479100 | 7394000 | 5085100 | 4740495 | 1506773 | 3233722 | 4953956 | 1676904 | 3277052 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 880589 | 0 | 880589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 2728922 | 0 | 2728922 | 4597697 | 285061 | 4312636 | 6109850 | 2869099 | 3240751 | 2097414 | 38225 | 2059189 | 2437602 | 133478 | 2304124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 27352153 | 6941345 | 20410808 | 41643741 | 11368741 | 30275000 | 158416521 | 43175940 | 115240581 | 27352153 | 6941345 | 20410808 | 41643741 | 11368741 | 30275000 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2012 | Q1 | Q1 - 2012 | 29211582 | 8888681 | 20322901 | 4206430 | 1953252 | 2253178 | 11638946 | 4276135 | 7362811 | 93402141 | 18671661 | 74730480 | 25038578 | 6254951 | 18783627 | 48053404 | 11844779 | 36208625 | 12479100 | 7394000 | 5085100 | 4795487 | 2279328 | 2516159 | 5299273 | 2328029 | 2971244 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 411089 | 0 | 411089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 3129924 | 0 | 3129924 | 4717629 | 0 | 4717629 | 6109850 | 2869099 | 3240751 | 4276775 | 602662 | 3674113 | 5622500 | 1574300 | 4048200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 41858283 | 11090193 | 30768090 | 75742841 | 20023243 | 55719598 | 158416521 | 43175940 | 115240581 | 41858283 | 11090193 | 30768090 | 75742841 | 20023243 | 55719598 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2012 | Q2 | Q2 - 2012 | 29211582 | 8888681 | 20322901 | 4678794 | 2347814 | 2330980 | 14815235 | 5543353 | 9271882 | 93402141 | 18671661 | 74730480 | 50545456 | 11092420 | 39453035 | 73018602 | 16272508 | 56746093 | 12479100 | 7394000 | 5085100 | 5288361 | 2583471 | 2704891 | 5911160 | 2770713 | 3140447 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 874939 | 0 | 874939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 4562776 | 0 | 4562776 | 5577995 | 0 | 5577995 | 6109850 | 2869099 | 3240751 | 5373416 | 1126154 | 4247262 | 8350778 | 2092599 | 6258179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 70859892 | 17149859 | 53710033 | 108548709 | 26679173 | 81869535 | 158416521 | 43175940 | 115240581 | 70859892 | 17149859 | 53710033 | 108548709 | 26679173 | 81869535 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2012 | Q3 | Q3 - 2012 | 29211582 | 8888681 | 20322901 | 8136854 | 2157470 | 5979383 | 10695380 | 4262087 | 6433292 | 93402141 | 18671661 | 74730480 | 68603324 | 18064883 | 50538441 | 90052997 | 22471838 | 67581159 | 12479100 | 7394000 | 5085100 | 5891365 | 2788417 | 3102948 | 6255225 | 2937330 | 3317894 | 1350000 | 0 | 1350000 | 874939 | 0 | 874939 | 874939 | 0 | 874939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 5493694 | 0 | 5493694 | 6384968 | 0 | 6384968 | 6109850 | 2869099 | 3240751 | 6968391 | 1861537 | 5106854 | 7645188 | 2064683 | 5580505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 95968567 | 24872307 | 71096259 | 121908697 | 31735938 | 90172757 | 158416521 | 43175940 | 115240581 | 95968567 | 24872307 | 71096259 | 121908697 | 31735938 | 90172757 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2012 | Q4 | Q4 - 2012 | 29211582 | 8888681 | 20322901 | 9968741 | 3457705 | 6511036 | 15206802 | 4136249 | 11070553 | 93402141 | 18671661 | 74730480 | 83965737 | 22141818 | 61823919 | 93964986 | 27120905 | 66844081 | 12479100 | 7394000 | 5085100 | 6465196 | 3213737 | 3251459 | 6868273 | 3416727 | 3451546 | 1350000 | 0 | 1350000 | 935972 | 0 | 935972 | 1053965 | 0 | 1053965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 6290079 | 0 | 6290079 | 7372122 | 0 | 7372122 | 6109850 | 2869099 | 3240751 | 7685095 | 2086681 | 5598414 | 7814195 | 2142763 | 5671432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 115310820 | 30899941 | 84410879 | 132280343 | 36816644 | 95463699 | 158416521 | 43175940 | 115240581 | 115310820 | 30899941 | 84410879 | 132280343 | 36816644 | 95463699 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2013 | Q1 | Q1 - 2013 | 29211582 | 8888681 | 20322901 | 14099689 | 4569826 | 9529863 | 16434107 | 5721602 | 10712505 | 93402141 | 18671661 | 74730480 | 94550651 | 27604657 | 66945994 | 107477715 | 30043469 | 77434246 | 12479100 | 7394000 | 5085100 | 6754623 | 3407199 | 3347424 | 7156015 | 3642882 | 3513133 | 1350000 | 0 | 1350000 | 1257956 | 0 | 1257956 | 1257956 | 0 | 1257956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 7297717 | 0 | 7297717 | 8126040 | 0 | 8126040 | 6109850 | 2869099 | 3240751 | 8261896 | 2412935 | 5848960 | 8336476 | 2457147 | 5879329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 132222532 | 37994617 | 94227914 | 148788309 | 41865100 | 106923209 | 158416521 | 43175940 | 115240581 | 132222532 | 37994617 | 94227914 | 148788309 | 41865100 | 106923209 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2013 | Q2 | Q2 - 2013 | 18619128 | 5862684 | 12756444 | 15208206 | 4950874 | 10257332 | 18619128 | 5862684 | 12756444 | 113689497 | 30971125 | 82718372 | 104922047 | 29026841 | 75895206 | 113689497 | 30971125 | 82718372 | 7479147 | 3811988 | 3667160 | 7015499 | 3578250 | 3437249 | 7429147 | 3798338 | 3630810 | 1350000 | 0 | 1350000 | 1257956 | 0 | 1257956 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749198 | 157764 | 8591434 | 8114213 | 0 | 8114213 | 8749198 | 157764 | 8591434 | 8529550 | 2372379 | 6157170 | 8529550 | 2523068 | 6006482 | 8529550 | 2372379 | 6157170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416520 | 43175940 | 115240580 | 145047471 | 40079033 | 104968438 | 158366520 | 43162290 | 115204230 | 158416520 | 43175940 | 115240580 | 145047471 | 40079033 | 104968438 | 158366520 | 43162290 | 115204230 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570135 | INF | 2013 | Q3 | Q3 - 2013 | 18291208 | 6020448 | 12270761 | 18291208 | 6020448 | 12270761 | 18291208 | 6020448 | 12270761 | 114175181 | 30971125 | 83204056 | 114175181 | 30971125 | 83204056 | 114175181 | 30971125 | 83204056 | 7479147 | 3811987 | 3667160 | 7479147 | 3811987 | 3667160 | 7479147 | 3811987 | 3667160 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8591434 | 0 | 8591434 | 8591434 | 0 | 8591434 | 8591434 | 0 | 8591434 | 8529550 | 2372380 | 6157170 | 8529550 | 2372380 | 6157170 | 8529550 | 2372380 | 6157170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 0 | 0 | Information Technology, Maryland Department of
NT10BIX5570136 | INF | 2010 | Q4 | Q4 - 2010 | 19870336 | 500000 | 19370336 | 0 | 0 | 0 | 203000 | 0 | 203000 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22800563 | 11301200 | 11499363 | 0 | 0 | 0 | 592800 | 442800 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 863058 | 863058 | 0 | 903058 | 863058 | 40000 | 251066 | 0 | 251066 | 0 | 0 | 0 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 863058 | 863058 | 0 | 1878858 | 1305858 | 573000 | 51939135 | 12664258 | 39274877 | 863058 | 863058 | 0 | 1878858 | 1305858 | 573000 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2011 | Q1 | Q1 - 2011 | 19825624 | 500000 | 19325624 | 97851 | 0 | 97851 | 1305149 | 0 | 1305149 | 6561810 | 0 | 6561810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21552560 | 11301200 | 10251360 | 0 | 0 | 0 | 5012800 | 1162800 | 3850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972059 | 863058 | 1109002 | 653996 | 653996 | 0 | 733996 | 653996 | 80000 | 251066 | 0 | 251065 | 184111 | 0 | 184111 | 270000 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776017 | 0 | 1776017 | 0 | 0 | 0 | 0 | 0 | 0 | 51939136 | 12664258 | 39274878 | 935958 | 653996 | 281962 | 7321945 | 1816796 | 5505149 | 51939136 | 12664258 | 39274878 | 935958 | 653996 | 281962 | 7321945 | 1816796 | 5505149 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2011 | Q2 | Q2 - 2011 | 21655252 | 500000 | 21155252 | 172851 | 75000 | 97851 | 200000 | 75000 | 125000 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 0 | 0 | 0 | 1125000 | 0 | 1125000 | 0 | 0 | 0 | 375000 | 0 | 375000 | 19870647 | 11301200 | 8569447 | 4413898 | 799200 | 3614698 | 6122200 | 2122200 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 547452 | 547452 | 0 | 890202 | 590202 | 300000 | 271066 | 0 | 271066 | 217314 | 0 | 217314 | 290000 | 0 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 5351515 | 1421652 | 3929863 | 7877402 | 2787402 | 5090000 | 51939135 | 12664258 | 39274877 | 5351515 | 1421652 | 3929863 | 7877402 | 2787402 | 5090000 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2011 | Q3 | Q3 - 2011 | 21655252 | 500000 | 21155252 | 1335035 | 33180 | 1301855 | 2115035 | 33180 | 2081855 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 100000 | 0 | 100000 | 1125000 | 0 | 1125000 | 440179 | 35000 | 405179 | 740179 | 35000 | 705179 | 19870647 | 11301200 | 8569447 | 12154506 | 8458450 | 3696056 | 14806456 | 10410400 | 4396056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 717120 | 411509 | 305611 | 862120 | 456509 | 405611 | 271066 | 0 | 271066 | 287626 | 0 | 287626 | 296626 | 0 | 296626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 11000 | 0 | 11000 | 51939135 | 12664258 | 39274877 | 14934466 | 8938139 | 5996327 | 18931416 | 10935089 | 7996327 | 51939135 | 12664258 | 39274877 | 14934466 | 8938139 | 5996327 | 18931416 | 10935089 | 7996327 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2011 | Q4 | Q4 - 2011 | 20007697 | 33180 | 19974517 | 2627667 | 33180 | 2594487 | 6877667 | 33180 | 6844487 | 6570942 | 3262000 | 3308942 | 0 | 0 | 0 | 350000 | 0 | 350000 | 2197000 | 35000 | 2162000 | 804434 | 35000 | 769435 | 1054435 | 35000 | 1019435 | 20023726 | 8562569 | 11461157 | 12565388 | 8562569 | 4002819 | 13365388 | 8562569 | 4802819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 896979 | 455759 | 441219 | 1241978 | 500759 | 741219 | 401341 | 0 | 401341 | 297682 | 0 | 297682 | 347682 | 0 | 347682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 17192150 | 9086508 | 8105642 | 23237150 | 9131508 | 14105642 | 51939135 | 12664258 | 39274877 | 17192150 | 9086508 | 8105642 | 23237150 | 9131508 | 14105642 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2012 | Q1 | Q1 - 2012 | 20007698 | 33180 | 19974518 | 4558739 | 33180 | 4525559 | 7758739 | 33180 | 7725559 | 6570942 | 3262000 | 3308942 | 271312 | 0 | 271312 | 1109102 | 17790 | 1091312 | 2197000 | 35000 | 2162000 | 1052671 | 35000 | 1017671 | 1412671 | 35000 | 1377671 | 20023726 | 8562569 | 11461157 | 9210778 | 3436116 | 5774662 | 12407316 | 5382654 | 7024662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1252275 | 503571 | 748704 | 1447275 | 548571 | 898704 | 401340 | 0 | 401340 | 343380 | 0 | 343380 | 363380 | 0 | 363380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 52382 | 0 | 52382 | 252382 | 0 | 252382 | 51939135 | 12664258 | 39274877 | 16741537 | 4007867 | 12733670 | 24750865 | 6017195 | 18733670 | 51939135 | 12664258 | 39274877 | 16741537 | 4007867 | 12733670 | 24750865 | 6017195 | 18733670 | 2762000 | 0 | GOVNET, INC.
NT10BIX5570136 | INF | 2012 | Q2 | Q2 - 2012 | 20007698 | 33180 | 19974518 | 5046848 | 33180 | 5013668 | 6606848 | 33180 | 6573668 | 6570942 | 3262000 | 3308942 | 512122 | 4250 | 507872 | 788402 | 30530 | 757872 | 2197000 | 35000 | 2162000 | 1192942 | 35000 | 1157942 | 1549127 | 35000 | 1514127 | 20023726 | 8562569 | 11461157 | 9096091 | 3554886 | 5541204 | 11736227 | 5495022 | 6241205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1346879 | 532446 | 814433 | 1391879 | 547446 | 844432 | 401340 | 0 | 401340 | 349045 | 0 | 349045 | 403416 | 0 | 403416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 111424 | 0 | 111424 | 261424 | 0 | 261424 | 51939135 | 12664258 | 39274877 | 17655351 | 4159762 | 13495588 | 22737323 | 6141178 | 16596144 | 51939135 | 12664258 | 39274877 | 17655351 | 4159762 | 13495588 | 22737323 | 6141178 | 16596144 | 2762000 | 4250 | GOVNET, INC.
NT10BIX5570136 | INF | 2012 | Q3 | Q3 - 2012 | 20007698 | 33180 | 19974518 | 5052711 | 33180 | 5019531 | 7927924 | 33180 | 7894744 | 6570942 | 3262000 | 3308942 | 640600 | 4250 | 636350 | 1034901 | 44420 | 990481 | 2197000 | 35000 | 2162000 | 1333089 | 35000 | 1298089 | 1495397 | 35000 | 1460397 | 20023726 | 8562569 | 11461157 | 11133095 | 5451006 | 5682089 | 11823922 | 5522106 | 6301816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1413513 | 580446 | 833067 | 1516501 | 631634 | 884867 | 401340 | 0 | 401340 | 353507 | 0 | 353507 | 403507 | 0 | 403507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 131562 | 0 | 131562 | 151969 | 0 | 151969 | 51939135 | 12664258 | 39274877 | 20058077 | 6103882 | 13954195 | 24354121 | 6266340 | 18087781 | 51939135 | 12664258 | 39274877 | 20058077 | 6103882 | 13954195 | 24354121 | 6266340 | 18087781 | 2762000 | 4250 | GOVNET, INC.
NT10BIX5570136 | INF | 2012 | Q4 | Q4 - 2012 | 20007698 | 33180 | 19974518 | 6427924 | 33180 | 6394744 | 7076408 | 33180 | 7043228 | 6570942 | 3262000 | 3308942 | 786157 | 4250 | 781907 | 1788921 | 85810 | 1703111 | 2197000 | 35000 | 2162000 | 1501045 | 35000 | 1466045 | 1601832 | 35000 | 1566832 | 20023726 | 8562569 | 11461157 | 11606816 | 5451006 | 6155810 | 12562383 | 5506306 | 7056077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1512114 | 626571 | 885543 | 1593302 | 677759 | 915543 | 401340 | 0 | 401340 | 353167 | 0 | 353167 | 403167 | 0 | 403167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 156912 | 0 | 156912 | 230584 | 0 | 230584 | 51939135 | 12664258 | 39274877 | 22344135 | 6150007 | 16194128 | 25256597 | 6338055 | 18918542 | 51939135 | 12664258 | 39274877 | 22344135 | 6150007 | 16194128 | 25256597 | 6338055 | 18918542 | 2762000 | 44420 | GOVNET, INC.
NT10BIX5570136 | INF | 2013 | Q1 | Q1 - 2013 | 20007698 | 33180 | 19974518 | 6331440 | 33180 | 6298260 | 7331440 | 33180 | 7298260 | 6570942 | 3262000 | 3308942 | 774400 | 4250 | 770150 | 1062350 | 72200 | 990150 | 2197000 | 35000 | 2162000 | 1590351 | 0 | 1590351 | 2000351 | 0 | 2000351 | 20023726 | 8562569 | 11461157 | 11946630 | 5433840 | 6512790 | 12812770 | 5599980 | 7212790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1451271 | 518696 | 932575 | 1522459 | 569884 | 952575 | 401340 | 0 | 401340 | 353507 | 0 | 353507 | 403507 | 0 | 403507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 165132 | 0 | 165132 | 265132 | 0 | 265132 | 51939135 | 12664258 | 39274877 | 22612731 | 5989966 | 16622765 | 25398009 | 6275244 | 19122765 | 51939135 | 12664258 | 39274877 | 22612731 | 5989966 | 16622765 | 25398009 | 6275244 | 19122765 | 2762000 | 58310 | GOVNET, INC.
NT10BIX5570136 | INF | 2013 | Q2 | Q2 - 2013 | 20007698 | 33180 | 19974518 | 6767135 | 33180 | 6733955 | 7711135 | 33180 | 7677955 | 6570942 | 3262000 | 3308942 | 831595 | 23930 | 807665 | 1040348 | 132683 | 907665 | 2197000 | 35000 | 2162000 | 2067276 | 0 | 2067276 | 2267276 | 0 | 2267276 | 20023726 | 8562569 | 11461157 | 12489270 | 5447175 | 7042095 | 13227570 | 5485475 | 7742095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1508125 | 570259 | 937866 | 1553563 | 605697 | 947866 | 401340 | 0 | 401340 | 364703 | 0 | 364703 | 404703 | 0 | 404703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 191474 | 0 | 191474 | 197474 | 0 | 197474 | 51939135 | 12664258 | 39274877 | 24219578 | 6074544 | 18145034 | 26402069 | 6257035 | 20145034 | 51939135 | 12664258 | 39274877 | 24219578 | 6074544 | 18145034 | 26402069 | 6257035 | 20145034 | 2762000 | 23930 | GOVNET, INC.
NT10BIX5570136 | INF | 2013 | Q3 | Q3 - 2013 | 17059271 | 33180 | 17026091 | 6770680 | 33180 | 6737500 | 7070680 | 33180 | 7037500 | 4479813 | 821793 | 3658020 | 927577 | 4250 | 923327 | 1371616 | 148289 | 1223327 | 4854785 | 0 | 4854785 | 2625620 | 0 | 2625620 | 2925620 | 0 | 2925620 | 22287483 | 11076276 | 11211207 | 15303596 | 8075370 | 7228226 | 16576771 | 8348545 | 8228226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1477485 | 539509 | 937976 | 1712860 | 674884 | 1037976 | 604613 | 0 | 604613 | 403694 | 0 | 403694 | 453694 | 0 | 453694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 197638 | 0 | 197638 | 200638 | 0 | 200638 | 51561929 | 12664258 | 38897671 | 27706290 | 8652309 | 19053981 | 30311879 | 9204898 | 21106981 | 51561929 | 12664258 | 38897671 | 27706290 | 8652309 | 19053981 | 30311879 | 9204898 | 21106981 | 821793 | 4250 | GOVNET, INC.
NT10BIX5570136 | INF | 2013 | Q4 | Q4 - 2013 | 17059271 | 33180 | 17026091 | 6775491 | 33180 | 6742311 | 7479912 | 37601 | 7442311 | 4479813 | 821793 | 3658020 | 1000083 | 59050 | 941033 | 1476452 | 155419 | 1321033 | 4854785 | 0 | 4854785 | 2964655 | 0 | 2964655 | 3318655 | 0 | 3318655 | 22287483 | 11076276 | 11211207 | 16036447 | 8552745 | 7483702 | 17766822 | 8783120 | 8983702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1569628 | 589947 | 979682 | 1755003 | 725321 | 1029682 | 604613 | 0 | 604613 | 409714 | 0 | 409714 | 419714 | 0 | 419714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 205826 | 0 | 205826 | 211826 | 0 | 211826 | 51561929 | 12664258 | 38897671 | 28961844 | 9234922 | 19726923 | 32428384 | 9701461 | 22726923 | 51561929 | 12664258 | 38897671 | 28961844 | 9234922 | 19726923 | 32428384 | 9701461 | 22726923 | 821793 | 59050 | GOVNET, INC.
NT10BIX5570136 | INF | 2014 | Q1 | Q1 - 2014 | 17059271 | 33180 | 17026091 | 6876653 | 33180 | 6843473 | 10881074 | 37601 | 10843473 | 4479813 | 821793 | 3658020 | 1080319 | 106027 | 974292 | 2135908 | 161616 | 1974292 | 4854785 | 0 | 4854785 | 3292722 | 0 | 3292722 | 3692722 | 0 | 3692722 | 22287483 | 11076276 | 11211207 | 16924973 | 8955296 | 7969677 | 19086673 | 9116996 | 9969677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1659720 | 639259 | 1020462 | 1995096 | 774634 | 1220462 | 604613 | 0 | 604613 | 433979 | 0 | 433979 | 498979 | 0 | 498979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 211967 | 0 | 211967 | 217967 | 0 | 217967 | 51561929 | 12664258 | 38897671 | 30480333 | 9733762 | 20746572 | 38508419 | 10090847 | 28417572 | 51561929 | 12664258 | 38897671 | 30480333 | 9733762 | 20746572 | 38508419 | 10090847 | 28417572 | 821793 | 106027 | GOVNET, INC.
NT10BIX5570136 | INF | 2014 | Q2 | Q2 - 2014 | 17059271 | 33180 | 17026091 | 6961058 | 37601 | 6923457 | 10161058 | 37601 | 10123457 | 4479813 | 821793 | 3658020 | 1163089 | 132530 | 1030559 | 2301692 | 217133 | 2084559 | 4854785 | 0 | 4854785 | 3633804 | 0 | 3633804 | 4133804 | 0 | 4133804 | 22287483 | 11076276 | 11211207 | 17107801 | 8973386 | 8134415 | 19252481 | 9218066 | 10034415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1870941 | 785696 | 1085245 | 2131879 | 846634 | 1285245 | 604613 | 0 | 604613 | 465848 | 0 | 465848 | 605848 | 0 | 605848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 218108 | 0 | 218108 | 224108 | 0 | 224108 | 51561929 | 12664258 | 38897671 | 31420649 | 9929213 | 21491436 | 38810870 | 10319434 | 28491436 | 51561929 | 12664258 | 38897671 | 31420649 | 9929213 | 21491436 | 38810870 | 10319434 | 28491436 | 821793 | 132530 | GOVNET, INC.
NT10BIX5570136 | INF | 2014 | Q3 | Q3 - 2014 | 15971093 | 37696 | 15933397 | 9302348 | 37601 | 9264747 | 13929439 | 37601 | 13891838 | 4410965 | 370044 | 4040921 | 1484337 | 163397 | 1320940 | 2705673 | 226000 | 2479673 | 4243622 | 0 | 4243622 | 4019914 | 0 | 4019914 | 4206919 | 0 | 4206919 | 23300140 | 11413633 | 11886507 | 18297095 | 9976937 | 8320158 | 19642635 | 10113812 | 9528823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806265 | 842885 | 1963380 | 2088971 | 902509 | 1186462 | 2292473 | 963446 | 1329027 | 605000 | 0 | 605000 | 487114 | 0 | 487114 | 500000 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224844 | 0 | 224844 | 224096 | 0 | 224096 | 230777 | 0 | 230777 | 51561929 | 12664258 | 38897671 | 35903875 | 11080444 | 24823431 | 43507916 | 11340859 | 32167057 | 51561929 | 12664258 | 38897671 | 35903875 | 11080444 | 24823431 | 43507916 | 11340859 | 32167057 | 370044 | 149031 | GOVNET, INC.
NT10BIX5570136 | INF | 2014 | Q4 | Q4 - 2014 | 15971093 | 37696 | 15933397 | 13384863 | 37601 | 13347262 | 14384863 | 37601 | 14347262 | 4410965 | 370044 | 4040921 | 1745831 | 195382 | 1550449 | 3623407 | 272958 | 3350449 | 4243622 | 0 | 4243622 | 4234071 | 0 | 4234071 | 4534071 | 0 | 4534071 | 23300140 | 11413633 | 11886507 | 20480146 | 10768067 | 9712079 | 21528271 | 10916192 | 10612079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806265 | 842885 | 1963380 | 2345764 | 1027571 | 1318193 | 2571702 | 1088509 | 1483193 | 605000 | 0 | 605000 | 500370 | 0 | 500370 | 515370 | 0 | 515370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224844 | 0 | 224844 | 228721 | 0 | 228721 | 228721 | 0 | 228721 | 51561929 | 12664258 | 38897671 | 42919766 | 12028621 | 30891145 | 47386405 | 12315260 | 35071145 | 51561929 | 12664258 | 38897671 | 42919766 | 12028621 | 30891145 | 47386405 | 12315260 | 35071145 | 370044 | 189748 | GOVNET, INC.
NT10BIX5570136 | INF | 2015 | Q1 | Q1 - 2015 | 15971093 | 37696 | 15933397 | 13642979 | 37696 | 13605283 | 15242979 | 37696 | 15205283 | 4410965 | 370044 | 4040921 | 2125436 | 285614 | 1839822 | 4041566 | 370044 | 3671522 | 4243622 | 0 | 4243622 | 4526031 | 0 | 4526031 | 4836631 | 0 | 4836631 | 23300140 | 11413633 | 11886507 | 21359125 | 11413633 | 9945492 | 23106192 | 11413633 | 11692559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806265 | 842885 | 1963380 | 2596192 | 1166696 | 1429496 | 2871792 | 1166696 | 1705096 | 605000 | 0 | 605000 | 514209 | 0 | 514209 | 529209 | 0 | 529209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224844 | 0 | 224844 | 228565 | 0 | 228565 | 228565 | 0 | 228565 | 51561929 | 12664258 | 38897671 | 44992537 | 12903639 | 32088898 | 50856934 | 12988069 | 37868865 | 51561929 | 12664258 | 38897671 | 44992537 | 12903639 | 32088898 | 50856934 | 12988069 | 37868865 | 370044 | 285614 | GOVNET, INC.
NT10BIX5570136 | INF | 2015 | Q2 | Q2 - 2015 | 15971093 | 37696 | 15933397 | 14008505 | 37696 | 13970809 | 16296652 | 37696 | 16258956 | 4410965 | 370044 | 4040921 | 2491321 | 355274 | 2136047 | 4084508 | 451613 | 3632895 | 4243622 | 0 | 4243622 | 4736809 | 0 | 4736809 | 5100058 | 0 | 5100058 | 23300140 | 11413633 | 11886507 | 22423063 | 11965561 | 10457502 | 22840519 | 11965561 | 11522708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806265 | 842885 | 1963380 | 2862084 | 1302634 | 1559450 | 2942801 | 1363571 | 1579230 | 605000 | 0 | 605000 | 525259 | 0 | 525259 | 575259 | 0 | 575259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224844 | 0 | 224844 | 228565 | 0 | 228565 | 228565 | 0 | 228565 | 51561929 | 12664258 | 38897671 | 47275606 | 13661165 | 33614441 | 52068362 | 13818441 | 38897671 | 51561929 | 12664258 | 38897671 | 47275606 | 13661165 | 33614441 | 52068362 | 13818441 | 38897671 | 370044 | 355274 | GOVNET, INC.
NT10BIX5570138 | INF | 2010 | Q4 | Q4 - 2010 | 1464565 | 451993 | 1012572 | 0 | 0 | 0 | 410078 | 126558 | 283520 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 3449040 | 1064440 | 2384600 | 1574266 | 485849 | 1088417 | 327608 | 101106 | 226502 | 362989 | 112025 | 250964 | 80000 | 24690 | 53310 | 0 | 0 | 0 | 22400 | 6913 | 15487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 0 | 0 | 0 | 494405 | 152583 | 341822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 3623 | 1118 | 2505 | 21549 | 6650 | 14899 | 17279523 | 5332795 | 11944728 | 331231 | 102224 | 229007 | 4760461 | 1469169 | 3291292 | 17279523 | 5332795 | 11944728 | 331231 | 102224 | 229007 | 4760461 | 1469169 | 3291292 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2011 | Q1 | Q1 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 94843 | 115752 | 322304 | 98948 | 223356 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 2709960 | 826538 | 1883422 | 1574266 | 485859 | 1088417 | 381850 | 36994 | 344856 | 418843 | 48092 | 370751 | 80000 | 24690 | 53310 | 0 | 0 | 0 | 2350 | 725 | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 365075 | 163001 | 202074 | 463457 | 142281 | 321176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 10699 | 3274 | 7425 | 17279523 | 5332805 | 11944728 | 957520 | 294838 | 662682 | 3927613 | 1119858 | 2807755 | 17279523 | 5332805 | 11944728 | 957520 | 294838 | 662682 | 3927613 | 1119858 | 2807755 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2011 | Q2 | Q2 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 94843 | 115752 | 1200000 | 360000 | 840000 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 1574266 | 485849 | 1088417 | 630593 | 214644 | 415949 | 645782 | 193735 | 452047 | 80000 | 24690 | 55310 | 2775 | 805 | 1970 | 15000 | 4500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1636124 | 458920 | 1177204 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 2480087 | 769212 | 1710875 | 3810782 | 1143235 | 2667547 | 17279523 | 5332795 | 11946728 | 2480087 | 769212 | 1710875 | 3810782 | 1143235 | 2667547 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2011 | Q3 | Q3 - 2011 | 1464565 | 451993 | 1012572 | 211417 | 95665 | 115752 | 992847 | 307783 | 685064 | 12318000 | 3801573 | 8516427 | 331698 | 102181 | 229517 | 1503992 | 466238 | 1037754 | 1574266 | 485849 | 1088417 | 675722 | 233036 | 442686 | 720722 | 223424 | 497298 | 80000 | 24690 | 55310 | 2775 | 805 | 1970 | 40000 | 12400 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1848207 | 522545 | 1325662 | 1848207 | 522545 | 1325662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 3069819 | 954232 | 2115587 | 5105768 | 1532390 | 3573378 | 17279523 | 5332795 | 11946728 | 3069819 | 954232 | 2115587 | 5105768 | 1532390 | 3573378 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2011 | Q4 | Q4 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 64934 | 145661 | 597819 | 184327 | 413492 | 12318000 | 3801573 | 8516427 | 1482127 | 456988 | 1025139 | 4967143 | 1531532 | 3435611 | 1574266 | 485849 | 1088417 | 710674 | 219124 | 491550 | 750626 | 231442 | 519184 | 80000 | 24690 | 55310 | 13493 | 4160 | 9333 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1834935 | 565770 | 1269165 | 1834935 | 565770 | 1269165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 4251824 | 1310976 | 2940848 | 8190523 | 2525404 | 5665119 | 17279523 | 5332795 | 11946728 | 4251824 | 1310976 | 2940848 | 8190523 | 2525404 | 5665119 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2012 | Q1 | Q1 - 2012 | 1464565 | 451993 | 1012572 | 470595 | 172843 | 297752 | 1318109 | 395433 | 922676 | 12318000 | 3801573 | 8516427 | 4384398 | 1317978 | 3066420 | 8253060 | 2475918 | 5777142 | 1574266 | 485849 | 1088417 | 770297 | 252734 | 517563 | 830300 | 272338 | 557962 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 4182 | 0 | 4182 | 4182 | 0 | 4182 | 17279523 | 5309044 | 11970479 | 7507099 | 2291115 | 5215984 | 12297972 | 3695953 | 8602019 | 17279523 | 5309044 | 11970479 | 7507099 | 2291115 | 5215984 | 12297972 | 3695953 | 8602019 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2012 | Q2 | Q2 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 525000 | 189000 | 336000 | 12318000 | 3801573 | 8516427 | 9079025 | 2726366 | 6352659 | 11979025 | 3597215 | 8381810 | 1574266 | 485849 | 1088417 | 827735 | 281424 | 546311 | 1177439 | 365006 | 812433 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 4182 | 0 | 4182 | 4182 | 0 | 4182 | 17279523 | 5332795 | 11946728 | 12266358 | 3730351 | 8536007 | 15577967 | 4703485 | 10874482 | 17279523 | 5332795 | 11946728 | 12266358 | 3730351 | 8536007 | 15577967 | 4703485 | 10874482 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2012 | Q3 | Q3 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175002 | 302787 | 600000 | 185160 | 414840 | 12317820 | 3801573 | 8516247 | 11425612 | 3430342 | 7995270 | 11648111 | 3594607 | 8053504 | 1574266 | 485849 | 1088417 | 989413 | 333217 | 656196 | 1125000 | 347175 | 777825 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 14781453 | 4486121 | 10295332 | 15316444 | 4691563 | 10624881 | 17279343 | 5309044 | 11970299 | 14781453 | 4486121 | 10295332 | 15316444 | 4691563 | 10624881 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2012 | Q4 | Q4 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 925000 | 285473 | 639527 | 12317820 | 3801573 | 8516247 | 11425612 | 3430342 | 7995270 | 11925000 | 3680339 | 8244661 | 1574266 | 485849 | 1088417 | 1017198 | 333217 | 683981 | 1275000 | 393490 | 881510 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 14809238 | 4486120 | 10323118 | 16068333 | 4923923 | 11144410 | 17279343 | 5309044 | 11970299 | 14809238 | 4486120 | 10323118 | 16068333 | 4923923 | 11144410 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2013 | Q1 | Q1 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 1000000 | 308600 | 691400 | 12317820 | 3801573 | 8516247 | 11725612 | 3730342 | 7995270 | 12000000 | 3816000 | 8184000 | 1574266 | 485849 | 1088417 | 1445569 | 467732 | 977837 | 1525000 | 470615 | 1054385 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 15537609 | 4920635 | 10616974 | 16468333 | 5159836 | 11308497 | 17279343 | 5309044 | 11970299 | 15537609 | 4920635 | 10616974 | 16468333 | 5159836 | 11308497 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2013 | Q2 | Q2 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 11725612 | 3730342 | 7995270 | 13122705 | 4002425 | 9120280 | 1574266 | 485849 | 1088417 | 1484290 | 484835 | 999455 | 1783222 | 584058 | 1199164 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 18000 | 0 | 18000 | 17279343 | 5309044 | 11970299 | 15576330 | 4937738 | 10638592 | 17279343 | 5309044 | 11970299 | 17279343 | 5309044 | 11970299 | 15576330 | 4937738 | 10638592 | 17279343 | 5309044 | 11970299 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2013 | Q3 | Q3 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 12352277 | 3692203 | 8660074 | 12834856 | 3806977 | 9027879 | 1574266 | 485849 | 1088417 | 1590630 | 519934 | 1070696 | 1590630 | 519934 | 1070696 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 13426 | 0 | 13426 | 41674 | 0 | 41674 | 17279343 | 5309044 | 11970299 | 16311749 | 4934698 | 11377051 | 16822576 | 5049472 | 11773104 | 17279343 | 5309044 | 11970299 | 16311749 | 4934698 | 11377051 | 16822576 | 5049472 | 11773104 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570138 | INF | 2013 | Q4 | Q4 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 12834856 | 3968952 | 8865904 | 12834856 | 3968952 | 8865904 | 1574266 | 485849 | 1088417 | 1590630 | 519934 | 1070696 | 1590630 | 519934 | 1070696 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 13426 | 0 | 13426 | 13426 | 0 | 13426 | 17279343 | 5309044 | 11970299 | 16794328 | 5211447 | 11582881 | 16794328 | 5211447 | 11582881 | 17279343 | 5309044 | 11970299 | 16794328 | 5211447 | 11582881 | 16794328 | 5211447 | 11582881 | 0 | 0 | Region 18 Education Svc Ctr.
NT10BIX5570139 | INF | 2010 | Q4 | Q4 - 2010 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 234766 | 46953 | 187813 | 617350 | 123470 | 493880 | 640161 | 128032 | 512129 | 153633 | 30727 | 122906 | 249663 | 49933 | 199730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 1534014 | 306803 | 1227211 | 2205260 | 441052 | 1764208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 3600 | 720 | 2880 | 3600 | 720 | 2880 | 30758722 | 6151744 | 24606978 | 1926013 | 385203 | 1540810 | 3075873 | 615175 | 2460698 | 30758722 | 6151744 | 24606978 | 1926013 | 385203 | 1540810 | 3075873 | 615175 | 2460698 | 0 | 0 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2011 | Q1 | Q1 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 454703 | 90941 | 363762 | 1113817 | 222763 | 891054 | 640161 | 128032 | 512129 | 291550 | 58310 | 233240 | 461550 | 92310 | 369240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 3374666 | 674933 | 2699733 | 4574666 | 914933 | 3659733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 5800 | 1160 | 4640 | 7900 | 1580 | 6320 | 30758722 | 6151744 | 24606978 | 4126719 | 825344 | 3301375 | 6157933 | 1231586 | 4926347 | 30758722 | 6151744 | 24606978 | 4126719 | 825344 | 3301375 | 6157933 | 1231586 | 4926347 | 0 | 1716 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2011 | Q2 | Q2 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 2269992 | 453998 | 1815994 | 5269992 | 1053998 | 4215993 | 640161 | 128032 | 512129 | 405820 | 81164 | 324656 | 555820 | 111164 | 444656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 5730837 | 1146169 | 4584668 | 7580837 | 1516167 | 6064670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 7600 | 1520 | 6080 | 10400 | 2080 | 8320 | 30758722 | 6151744 | 24606978 | 8414249 | 1682851 | 6731398 | 13417049 | 2683409 | 10733639 | 30758722 | 6151744 | 24606978 | 8414249 | 1682851 | 6731398 | 13417049 | 2683409 | 10733639 | 0 | 3432 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2011 | Q3 | Q3 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 5361601 | 1072320 | 4289281 | 7361601 | 1472320 | 5889281 | 640161 | 128032 | 512129 | 553534 | 110707 | 442827 | 765534 | 153107 | 612427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 6526199 | 1305240 | 5220959 | 7276199 | 1455240 | 5820959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 9400 | 1880 | 7520 | 10400 | 2080 | 8320 | 30758722 | 6151744 | 24606978 | 12450734 | 2490147 | 9960587 | 15413734 | 3082747 | 12330987 | 30758722 | 6151744 | 24606978 | 12450734 | 2490147 | 9960587 | 15413734 | 3082747 | 12330987 | 0 | 0 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2011 | Q4 | Q4 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 800000 | 160000 | 640000 | 20427522 | 4085504 | 16342018 | 9222293 | 1844459 | 7377834 | 12222293 | 2444459 | 9777834 | 640161 | 128032 | 512129 | 893245 | 178649 | 714596 | 1168245 | 233649 | 934596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 6972344 | 1394469 | 5577875 | 7472344 | 1494469 | 5977875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 8800 | 1760 | 7040 | 9800 | 1960 | 7840 | 30758722 | 6151744 | 24606978 | 17096682 | 3419337 | 13677345 | 21672682 | 4334537 | 17338145 | 30758722 | 6151744 | 24606978 | 17096682 | 3419337 | 13677345 | 21672682 | 4334537 | 17338145 | 0 | 0 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2012 | Q1 | Q1 - 2012 | 799970 | 159994 | 639976 | 0 | 0 | 0 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 10811734 | 2162347 | 8649387 | 13011734 | 2602347 | 10409387 | 1923334 | 384667 | 1538667 | 1102181 | 220436 | 881745 | 1352181 | 270436 | 1081745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 7802210 | 1560442 | 6241768 | 8302210 | 1660442 | 6641768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 8800 | 1760 | 7040 | 30758722 | 6151745 | 24606977 | 19724925 | 3944985 | 15779940 | 23474895 | 4694979 | 18779916 | 30758722 | 6151745 | 24606977 | 19724925 | 3944985 | 15779940 | 23474895 | 4694979 | 18779916 | 0 | 0 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2012 | Q2 | Q2 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 14057427 | 2811485 | 11245941 | 15257427 | 3051485 | 12205942 | 1923334 | 384667 | 1538667 | 1375527 | 275106 | 1100422 | 1625528 | 325106 | 1300422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8224576 | 1644915 | 6579661 | 8424576 | 1684915 | 6739661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 30758722 | 6151745 | 24606977 | 24466300 | 4893260 | 19573040 | 26116301 | 5223260 | 20893041 | 30758722 | 6151745 | 24606977 | 24466300 | 4893260 | 19573040 | 26116301 | 5223260 | 20893041 | 0 | 0 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2012 | Q3 | Q3 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 15073977 | 3014795 | 12059181 | 15573638 | 3114728 | 12458910 | 1923334 | 384667 | 1538667 | 1526409 | 305282 | 1221127 | 1676409 | 335282 | 1341127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8334310 | 1666862 | 6667448 | 8409310 | 1681862 | 6727448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 10000 | 2000 | 8000 | 30758722 | 6151745 | 24606977 | 25743466 | 5148693 | 20594772 | 26469127 | 5293826 | 21175301 | 30758722 | 6151745 | 24606977 | 25743466 | 5148693 | 20594772 | 26469127 | 5293826 | 21175301 | 240000 | 303384 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2012 | Q4 | Q4 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 15293389 | 3058678 | 12234711 | 15643389 | 3128678 | 12514711 | 1923334 | 384667 | 1538667 | 1621053 | 324211 | 1296842 | 1696053 | 339211 | 1356842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8428581 | 1685716 | 6742865 | 8453581 | 1690716 | 6762865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 30758722 | 6151745 | 24606977 | 26151793 | 5230359 | 20921434 | 26601793 | 5320359 | 21281434 | 30758722 | 6151745 | 24606977 | 26151793 | 5230359 | 20921434 | 26601793 | 5320359 | 21281434 | 590000 | 653421 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2013 | Q1 | Q1 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 16218767 | 3243753 | 12975014 | 18713767 | 3742753 | 14971014 | 1923334 | 384667 | 1538667 | 1695002 | 339000 | 1356002 | 1745002 | 349000 | 1396002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8434622 | 1686924 | 6747698 | 8444622 | 1688924 | 6755698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 9800 | 1960 | 7840 | 30758722 | 6151745 | 24606977 | 27157161 | 5431431 | 21725730 | 29713161 | 5942631 | 23770530 | 30758722 | 6151745 | 24606977 | 27157161 | 5431431 | 21725730 | 29713161 | 5942631 | 23770530 | 949500 | 1120205 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2013 | Q2 | Q2 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 19108344 | 3821669 | 15286675 | 19341835 | 3868367 | 15473468 | 1923334 | 384667 | 1538667 | 1734446 | 346889 | 1387557 | 1923334 | 384667 | 1538667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8446349 | 1689270 | 6757079 | 8673583 | 1734717 | 6938866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 20000 | 4000 | 16000 | 30758722 | 6151745 | 24606977 | 30097909 | 6019582 | 24078327 | 30758722 | 6151745 | 24606977 | 30758722 | 6151745 | 24606977 | 30097909 | 6019582 | 24078327 | 30758722 | 6151745 | 24606977 | 1309000 | 1502669 | Maine Fiber Company, Inc.
NT10BIX5570139 | INF | 2013 | Q3 | Q3 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19714604 | 3942921 | 15771683 | 19645904 | 3929181 | 15716723 | 19645904 | 3929181 | 15716723 | 1806438 | 361288 | 1445150 | 1845689 | 369138 | 1476551 | 1845689 | 369138 | 1476551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8426910 | 1685382 | 6741528 | 8446349 | 1689270 | 6757079 | 8446349 | 1689270 | 6757079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 2160 | 8640 | 10417 | 2083 | 8334 | 10417 | 2083 | 8334 | 30758722 | 6151745 | 24606977 | 30748329 | 6149666 | 24598663 | 30748329 | 6149666 | 24598663 | 30758722 | 6151745 | 24606977 | 30748329 | 6149666 | 24598663 | 30748329 | 6149666 | 24598663 | 1548667 | 1779040 | Maine Fiber Company, Inc.
NT10BIX5570140 | INF | 2010 | Q4 | Q4 - 2010 | 14663000 | 823200 | 13839800 | 0 | 0 | 0 | 4996204 | 0 | 4996204 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 0 | 0 | 0 | 7271204 | 608554 | 6662650 | 42466000 | 8493200 | 33972800 | 0 | 0 | 0 | 7271204 | 608554 | 6662650 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2011 | Q1 | Q1 - 2011 | 14663000 | 823200 | 13839800 | 2192010 | 0 | 2192010 | 14663000 | 823200 | 13839800 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 10028000 | 1308946 | 8719054 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 2192010 | 0 | 2192010 | 26966000 | 2740700 | 24225300 | 42466000 | 8493200 | 33972800 | 2192010 | 0 | 2192010 | 26966000 | 2740700 | 24225300 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2011 | Q2 | Q2 - 2011 | 14663000 | 823200 | 13839800 | 3881221 | 13853 | 3867368 | 6598350 | 1319670 | 5278680 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 5105600 | 1021120 | 4084480 | 75000 | 0 | 75000 | 0 | 0 | 0 | 110948 | 0 | 110948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2000000 | 550554 | 1449446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 3881221 | 13853 | 3867368 | 13814898 | 2891344 | 10923554 | 42466000 | 8493200 | 33972800 | 3881221 | 13853 | 3867368 | 13814898 | 2891344 | 10923554 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2011 | Q3 | Q3 - 2011 | 14663000 | 823200 | 13839800 | 4537453 | 229767 | 4307686 | 13808000 | 660000 | 13148000 | 25528000 | 7061446 | 18466554 | 2600000 | 754000 | 1846000 | 5717000 | 1285000 | 4432000 | 75000 | 0 | 75000 | 110948 | 0 | 110948 | 110948 | 0 | 110948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 200000 | 58000 | 142000 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 7448401 | 1041767 | 6406634 | 21835948 | 2553554 | 19282394 | 42466000 | 8493200 | 33972800 | 7448401 | 1041767 | 6406634 | 21835948 | 2553554 | 19282394 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2011 | Q4 | Q4 - 2011 | 14663000 | 823200 | 13839800 | 6807032 | 549455 | 6257577 | 9925455 | 659455 | 9266000 | 25528000 | 7061446 | 18466554 | 2600000 | 754000 | 1846000 | 3726600 | 1080600 | 2646000 | 75000 | 0 | 75000 | 110978 | 0 | 110978 | 110978 | 0 | 110978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 602566 | 117107 | 485459 | 1204000 | 233000 | 971000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 10120576 | 1420562 | 8700014 | 14967033 | 1973055 | 12993978 | 42466000 | 8493200 | 33972800 | 10120576 | 1420562 | 8700014 | 14967033 | 1973055 | 12993978 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2012 | Q1 | Q1 - 2012 | 14663000 | 823200 | 13839800 | 10354813 | 671917 | 9682896 | 10531813 | 703917 | 9827896 | 25528000 | 7061446 | 18466554 | 3374715 | 919397 | 2455318 | 4610715 | 1337397 | 3273318 | 75000 | 0 | 75000 | 110978 | 0 | 110978 | 110978 | 0 | 110978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 758769 | 214516 | 544253 | 877769 | 254516 | 623253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 14599275 | 1805830 | 12793445 | 16131275 | 2295830 | 13835445 | 42466000 | 8493200 | 33972800 | 14599275 | 1805830 | 12793445 | 16131275 | 2295830 | 13835445 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2012 | Q2 | Q2 - 2012 | 14663000 | 823200 | 13839800 | 10388926 | 676432 | 9712494 | 10530500 | 686000 | 9844500 | 25528000 | 7061446 | 18466554 | 4674926 | 1350235 | 3324691 | 6492588 | 1758857 | 4733731 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 862600 | 256089 | 606511 | 1037988 | 295517 | 742471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 16037460 | 2282756 | 13754704 | 18172084 | 2740374 | 15431710 | 42466000 | 8493200 | 33972800 | 16037460 | 2282756 | 13754704 | 18172084 | 2740374 | 15431710 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2012 | Q3 | Q3 - 2012 | 14663000 | 823200 | 13839800 | 10403428 | 676432 | 9726996 | 11749316 | 691400 | 11057916 | 25528000 | 7061446 | 18466554 | 4716263 | 1362223 | 3354040 | 8883868 | 2452328 | 6431540 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 866587 | 257244 | 609343 | 1268726 | 362431 | 906295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 16097286 | 2295899 | 13801387 | 22012918 | 3506159 | 18506759 | 42466000 | 8493200 | 33972800 | 16097286 | 2295899 | 13801387 | 22012918 | 3506159 | 18506759 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2012 | Q4 | Q4 - 2012 | 14663000 | 823200 | 13839800 | 11515148 | 676432 | 10838716 | 12496148 | 681432 | 11814716 | 25528000 | 7061446 | 18466554 | 5151451 | 1474098 | 3677353 | 9097007 | 2618309 | 6478698 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 908578 | 268038 | 640540 | 1289289 | 378444 | 910845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 17686185 | 2418568 | 15267617 | 22993452 | 3678185 | 19315267 | 42466000 | 8493200 | 33972800 | 17686185 | 2418568 | 15267617 | 22993452 | 3678185 | 19315267 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2013 | Q1 | Q1 - 2013 | 14663000 | 823200 | 13839800 | 11630050 | 775608 | 10854442 | 13170496 | 823200 | 12347296 | 25528000 | 7061446 | 18466554 | 8734403 | 2540520 | 6193883 | 13844235 | 4022371 | 9821864 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 22675461 | 3924682 | 18750779 | 29325739 | 5454125 | 23871614 | 42466000 | 8493200 | 33972800 | 22675461 | 3924682 | 18750779 | 29325739 | 5454125 | 23871614 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2013 | Q2 | Q2 - 2013 | 14663000 | 823200 | 13839800 | 12538248 | 844281 | 11693967 | 14553000 | 854000 | 13699000 | 25528000 | 7061446 | 18466554 | 15226385 | 4389235 | 10837150 | 24267992 | 6763846 | 17504146 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 30075641 | 5842070 | 24233571 | 41132000 | 8226400 | 32905600 | 42466000 | 8493200 | 33972800 | 30075641 | 5842070 | 24233571 | 41132000 | 8226400 | 32905600 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2013 | Q3 | Q3 - 2013 | 14663000 | 823200 | 13839800 | 13804444 | 849776 | 12954668 | 13967050 | 849776 | 13117274 | 25528000 | 7061446 | 18466554 | 24154901 | 6604559 | 17550342 | 24891388 | 6829559 | 18061829 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 40270353 | 8062889 | 32207464 | 41169446 | 8287889 | 32881557 | 42466000 | 8493200 | 33972800 | 40270353 | 8062889 | 32207464 | 41169446 | 8287889 | 32881557 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2013 | Q4 | Q4 - 2013 | 14663000 | 823200 | 13839800 | 13891711 | 858221 | 13033490 | 14497800 | 864000 | 13633800 | 25528000 | 7061446 | 18466554 | 24866202 | 6753859 | 18112343 | 25095000 | 6908208 | 18186792 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 41068921 | 8220634 | 32848287 | 41903808 | 8380762 | 33523046 | 42466000 | 8493200 | 33972800 | 41068921 | 8220634 | 32848287 | 41903808 | 8380762 | 33523046 | 0 | 0 | University of Hawaii Systems
NT10BIX5570140 | INF | 2014 | Q1 | Q1 - 2014 | 14663000 | 823200 | 13839800 | 14459001 | 860255 | 13598746 | 0 | 0 | 0 | 25528000 | 7061446 | 18466554 | 25287997 | 6942843 | 18345154 | 0 | 0 | 0 | 75000 | 0 | 75000 | 111258 | 0 | 111258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 42058256 | 8411652 | 33646604 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 42058256 | 8411652 | 33646604 | 0 | 0 | 0 | 0 | 0 | University of Hawaii Systems
NT10BIX5570144 | INF | 2010 | Q4 | Q4 - 2010 | 11386911 | 0 | 11386911 | 0 | 0 | 0 | 910953 | 0 | 910953 | 50277258 | 22461586 | 27815672 | 0 | 0 | 0 | 2011090 | 750208 | 1112626 | 3486487 | 0 | 3486487 | 151065 | 0 | 151065 | 324735 | 0 | 324735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303920 | 0 | 1303920 | 0 | 0 | 0 | 0 | 0 | 0 | 1488758 | 0 | 1488758 | 0 | 0 | 0 | 1488758 | 0 | 1488758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67943334 | 22461586 | 45481748 | 151065 | 0 | 151065 | 4735536 | 750208 | 3837072 | 68530276 | 22461586 | 46068690 | 151065 | 0 | 151065 | 4735536 | 750208 | 3837072 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2011 | Q1 | Q1 - 2011 | 9778411 | 0 | 9778411 | 0 | 0 | 0 | 0 | 0 | 0 | 25911490 | 22416250 | 48327740 | 0 | 0 | 0 | 1054140 | 315000 | 1369140 | 3711487 | 0 | 3711487 | 480396 | 0 | 480396 | 803376 | 0 | 803376 | 4647688 | 0 | 4647688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 0 | 1223700 | 0 | 0 | 0 | 236293 | 0 | 236293 | 841250 | 0 | 841250 | 0 | 0 | 0 | 56249 | 0 | 56249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46114026 | 22416250 | 68530276 | 480396 | 0 | 480396 | 2150058 | 315000 | 2465058 | 46114026 | 22416250 | 68530276 | 480396 | 0 | 480396 | 2150058 | 315000 | 2465058 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2011 | Q2 | Q2 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 1548533 | 309707 | 1238826 | 48327740 | 15810021 | 32517719 | 3204584 | 0 | 3204584 | 14945666 | 2989132 | 11956534 | 3711487 | 1213656 | 2497831 | 738242 | 30000 | 708242 | 1138243 | 227649 | 910594 | 4647688 | 1519794 | 3127894 | 0 | 0 | 0 | 41575 | 8315 | 33260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 286519 | 51556 | 234963 | 553823 | 110765 | 443058 | 841250 | 275089 | 566161 | 25000 | 0 | 25000 | 81249 | 16250 | 64999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 4254345 | 81556 | 4172789 | 18309089 | 3661818 | 14647271 | 68530276 | 22416250 | 46114026 | 4254345 | 81556 | 4172789 | 18309089 | 3661818 | 14647271 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2011 | Q3 | Q3 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 265000 | 53000 | 212000 | 48327740 | 15810021 | 32517719 | 5747937 | 1293364 | 4454572 | 11875000 | 3801100 | 8073900 | 3711487 | 1213656 | 2497831 | 919568 | 183914 | 735655 | 1650000 | 330000 | 1320000 | 4647688 | 1519794 | 3127894 | 391095 | 78219 | 312876 | 1265000 | 253000 | 1012000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 311519 | 62304 | 249215 | 865000 | 173000 | 692000 | 841250 | 275089 | 566161 | 122200 | 24440 | 97760 | 343000 | 68600 | 274400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 7492319 | 1642241 | 5850078 | 16263000 | 4678700 | 11584300 | 68530276 | 22416250 | 46114026 | 7492319 | 1642241 | 5850078 | 16263000 | 4678700 | 11584300 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2011 | Q4 | Q4 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 960000 | 0 | 960000 | 48327740 | 15810021 | 32517719 | 11641109 | 2607378 | 9033732 | 21171684 | 8341260 | 12830424 | 3711487 | 1213656 | 2497831 | 1100349 | 214297 | 886052 | 1454577 | 214297 | 1240279 | 4647688 | 1519794 | 3127894 | 603649 | 120730 | 482919 | 1132730 | 120730 | 1012000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 402371 | 80474 | 321897 | 502371 | 80474 | 421897 | 841250 | 275089 | 566161 | 134721 | 26944 | 107776 | 194721 | 26944 | 167776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 13882199 | 3049823 | 10832376 | 25416083 | 8783705 | 16632376 | 68530276 | 22416250 | 46114026 | 13882199 | 3049823 | 10832376 | 25416083 | 8783705 | 16632376 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2012 | Q1 | Q1 - 2012 | 9778411 | 3197540 | 6580871 | 883934 | 0 | 883934 | 2383934 | 0 | 883934 | 48327740 | 15810021 | 32517719 | 23318136 | 13186111 | 10132026 | 32038137 | 14706111 | 18832026 | 3711487 | 1213656 | 2497831 | 1576688 | 145496 | 1431192 | 2168188 | 145496 | 2022692 | 4647688 | 1519794 | 3127894 | 798816 | 30000 | 768816 | 978816 | 30000 | 948816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 411748 | 86367 | 325381 | 456748 | 86367 | 370381 | 841250 | 275089 | 566161 | 146721 | 0 | 146721 | 176721 | 0 | 176721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 27136043 | 13447974 | 13688070 | 38202544 | 14967974 | 23234570 | 68530276 | 22416250 | 46114026 | 27136043 | 13447974 | 13688070 | 38202544 | 14967974 | 23234570 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2012 | Q2 | Q2 - 2012 | 9778411 | 3197540 | 6580871 | 883934 | 0 | 883934 | 3383934 | 0 | 3383934 | 48327740 | 15810021 | 32517719 | 23941674 | 8549696 | 15391978 | 35113494 | 12593030 | 22520464 | 3711487 | 1213656 | 2497831 | 1924557 | 106138 | 1818419 | 2496557 | 106138 | 2390419 | 4647688 | 1519794 | 3127894 | 6483780 | 5743589 | 740191 | 6483780 | 5743589 | 740191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 417148 | 114950 | 302198 | 542148 | 114950 | 427198 | 841250 | 275089 | 566161 | 146721 | 0 | 146721 | 556235 | 0 | 556235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 33797814 | 14514373 | 19283441 | 48576148 | 18557707 | 30018441 | 68530276 | 22416250 | 46114026 | 33797814 | 14514373 | 19283441 | 48576148 | 18557707 | 30018441 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2012 | Q3 | Q3 - 2012 | 9778411 | 3197540 | 6580871 | 2951708 | 0 | 2951708 | 5250000 | 0 | 5250000 | 48327740 | 15810021 | 32517719 | 29026675 | 10538992 | 18487683 | 33500000 | 13182059 | 20317941 | 3711487 | 1213656 | 2497831 | 2359878 | 106138 | 2253740 | 2802877 | 106138 | 2696739 | 4647688 | 1519794 | 3127894 | 6972595 | 5743589 | 1229006 | 7100000 | 5743589 | 1356411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 908934 | 114950 | 793984 | 1100000 | 114950 | 985050 | 841250 | 275089 | 566161 | 473735 | 0 | 473735 | 565000 | 0 | 565000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 42693525 | 16503669 | 26189856 | 50317877 | 19146736 | 31171141 | 68530276 | 22416250 | 46114026 | 42693525 | 16503669 | 26189856 | 50317877 | 19146736 | 31171141 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2012 | Q4 | Q4 - 2012 | 8811229 | 0 | 8811229 | 3605078 | 0 | 3605078 | 6005078 | 0 | 6005078 | 47274517 | 14887053 | 32387464 | 35814786 | 14104331 | 21710455 | 40316255 | 14210354 | 26105901 | 1977277 | 0 | 1977277 | 1076649 | 0 | 1076649 | 1414385 | 0 | 1414385 | 7533200 | 7308110 | 225090 | 5229597 | 5004507 | 225090 | 6579415 | 6354325 | 225090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 1614974 | 221087 | 1393887 | 2022974 | 221087 | 1801887 | 775000 | 0 | 775000 | 507275 | 0 | 507275 | 607503 | 0 | 607503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 47848359 | 19329925 | 28518434 | 56945610 | 20785766 | 36159844 | 68530276 | 22416250 | 46114026 | 47848359 | 19329925 | 28518434 | 56945610 | 20785766 | 36159844 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2013 | Q1 | Q1 - 2013 | 8811229 | 0 | 8811229 | 4023078 | 0 | 4023078 | 6345000 | 0 | 6345000 | 47274517 | 14887053 | 32387464 | 38874694 | 14104331 | 24768893 | 44326470 | 14478490 | 29847980 | 1977277 | 0 | 1977277 | 1193746 | 0 | 1193746 | 1636746 | 0 | 1636746 | 7533200 | 7308110 | 225090 | 5560195 | 5004507 | 555688 | 6710000 | 6107485 | 602515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 1790618 | 221087 | 1569531 | 2075000 | 221087 | 1853913 | 775000 | 0 | 775000 | 583865 | 0 | 583865 | 689000 | 0 | 689000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 52026196 | 19329925 | 32694801 | 61782216 | 20807062 | 40975154 | 68530276 | 22416250 | 46114026 | 52026196 | 19329925 | 32694801 | 61782216 | 20807062 | 40975154 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2013 | Q2 | Q2 - 2013 | 8811229 | 0 | 8811229 | 4786346 | 0 | 4786346 | 7645000 | 0 | 7645000 | 47274517 | 14887053 | 32387464 | 40458454 | 14104331 | 26354123 | 41253543 | 14140998 | 27112545 | 1977277 | 0 | 1977277 | 1307434 | 0 | 1307434 | 1583958 | 0 | 1583958 | 7533200 | 7308110 | 225090 | 6025618 | 5004507 | 1021111 | 7533200 | 5004507 | 2528693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 2089751 | 221087 | 1868664 | 2159053 | 221087 | 1937966 | 775000 | 0 | 775000 | 659865 | 0 | 659865 | 775000 | 0 | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 55327468 | 19329925 | 35997543 | 60949754 | 19366592 | 41583162 | 68530276 | 22416250 | 46114026 | 55327468 | 19329925 | 35997543 | 60949754 | 19366592 | 41583162 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2013 | Q3 | Q3 - 2013 | 8811229 | 0 | 8811229 | 6181083 | 0 | 6181083 | 8811229 | 0 | 8811229 | 47274517 | 14887053 | 32387464 | 45842775 | 14104331 | 31738444 | 47274517 | 17190656 | 30083861 | 1977277 | 0 | 1977277 | 1436773 | 0 | 1436773 | 1977277 | 0 | 1977277 | 7533200 | 7308110 | 225090 | 6210353 | 5004507 | 1205846 | 7533200 | 5004507 | 2528693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 2155160 | 221087 | 1934073 | 2159053 | 221087 | 1937966 | 775000 | 0 | 775000 | 769065 | 0 | 769065 | 775000 | 0 | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 62595209 | 19329925 | 43265284 | 68530276 | 22416250 | 46114026 | 68530276 | 22416250 | 46114026 | 62595209 | 19329925 | 43265284 | 68530276 | 22416250 | 46114026 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570144 | INF | 2013 | Q4 | Q4 - 2013 | 7697472 | 0 | 7697472 | 6820463 | 0 | 6820463 | 6820463 | 0 | 6820463 | 47585477 | 14514681 | 33070796 | 50485173 | 15500593 | 34984580 | 50485173 | 15500593 | 34984580 | 1485523 | 48750 | 1436773 | 1407350 | 0 | 1407350 | 1407350 | 0 | 1407350 | 6210353 | 5004507 | 1205846 | 5560353 | 5004507 | 555846 | 5560353 | 5004507 | 555846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2425411 | 491337 | 1934074 | 2111025 | 534303 | 1576722 | 2111025 | 534303 | 1576722 | 769065 | 0 | 769065 | 769065 | 0 | 769065 | 769065 | 0 | 769065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66173301 | 20059275 | 46114026 | 67153429 | 21039403 | 46114026 | 67153429 | 21039403 | 46114026 | 66173301 | 20059275 | 46114026 | 67153429 | 21039403 | 46114026 | 67153429 | 21039403 | 46114026 | 0 | 0 | Northern Illinois University, Inc.
NT10BIX5570145 | INF | 2010 | Q4 | Q4 - 2010 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 51605 | 15921 | 35685 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 101391 | 31280 | 70111 | 740184 | 228352 | 511832 | 0 | 0 | 0 | 228414 | 70467 | 157947 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 11782 | 3635 | 8147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 0 | 0 | 0 | 10800 | 3332 | 7469 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 9103 | 2808 | 6295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 186827 | 57637 | 129189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 0 | 0 | 0 | 33004 | 10182 | 22822 | 2051021 | 632755 | 1418266 | 0 | 0 | 0 | 632926 | 195262 | 437665 | 2051021 | 632755 | 1418266 | 0 | 0 | 0 | 632926 | 195262 | 437665 | 0 | 0 | Ute Indian Tribe
NT10BIX5570145 | INF | 2011 | Q1 | Q1 - 2011 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 86328 | 21582 | 64746 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 169611 | 42403 | 127208 | 740184 | 228352 | 511832 | 29060 | 7265 | 21795 | 382101 | 95525 | 286574 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 19709 | 4927 | 14782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 19294 | 4824 | 14470 | 18068 | 4517 | 13551 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 15229 | 3807 | 11421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 312531 | 78133 | 234398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 45000 | 11250 | 33750 | 55210 | 13803 | 41408 | 2051021 | 632755 | 1418266 | 93354 | 23339 | 70015 | 1058787 | 264697 | 794088 | 2051021 | 632755 | 1418266 | 93354 | 23339 | 70015 | 1058787 | 264697 | 794088 | 0 | 0 | Ute Indian Tribe
NT10BIX5570145 | INF | 2011 | Q2 | Q2 - 2011 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 111167 | 27792 | 83376 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 218414 | 54603 | 163810 | 740184 | 228352 | 511832 | 95720 | 23930 | 71790 | 492046 | 123011 | 369034 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 25381 | 6345 | 19035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 6049 | 18146 | 24202 | 6049 | 18146 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 19610 | 4903 | 14708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 80288 | 20072 | 60216 | 402458 | 100615 | 301844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 49300 | 12325 | 36975 | 71096 | 17774 | 53322 | 2051021 | 632755 | 1418266 | 249502 | 62376 | 187127 | 1364374 | 341092 | 1023275 | 2051021 | 632755 | 1418266 | 249502 | 62376 | 187127 | 1364374 | 341092 | 1023275 | 0 | 0 | Ute Indian Tribe
NT10BIX5570145 | INF | 2011 | Q3 | Q3 - 2011 | 167229 | 51591 | 115638 | 105744 | 32622 | 73120 | 152974 | 47194 | 105780 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 134727 | 41564 | 93163 | 740184 | 228352 | 511832 | 226912 | 70004 | 156908 | 303515 | 93637 | 209879 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 19709 | 6080 | 13629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 26817 | 8273 | 18544 | 29500 | 9101 | 20399 | 12452 | 3842 | 8610 | 15228 | 4698 | 10530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 137153 | 42313 | 94841 | 146866 | 45309 | 101557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 606755 | 187188 | 419566 | 900136 | 277698 | 622439 | 2051021 | 632755 | 1418266 | 606755 | 187188 | 419566 | 900136 | 277698 | 622439 | 0 | 0 | Ute Indian Tribe
NT10BIX5570145 | INF | 2011 | Q4 | Q4 - 2011 | 167229 | 51591 | 115638 | 105744 | 32623 | 73121 | 153000 | 47202 | 105798 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 0 | 0 | 0 | 740184 | 228352 | 511832 | 373901 | 123831 | 250070 | 451640 | 139334 | 312306 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 12720 | 3924 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 34194 | 10549 | 23645 | 29500 | 9101 | 20399 | 12453 | 3842 | 8611 | 22453 | 6927 | 15526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 335650 | 103551 | 232099 | 335650 | 103549 | 232099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 952242 | 302254 | 649988 | 1109957 | 342428 | 767527 | 2051021 | 632755 | 1418266 | 952242 | 302254 | 649988 | 1109957 | 342428 | 767527 | 0 | 0 | Ute Indian Tribe
NT10BIX5570145 | INF | 2012 | Q1 | Q1 - 2012 | 167229 | 51591 | 115638 | 150563 | 46449 | 104113 | 162069 | 49999 | 112070 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 251750 | 77667 | 174083 | 740184 | 228352 | 511832 | 471165 | 168305 | 302861 | 576146 | 177745 | 398401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 29254 | 9025 | 20229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 26817 | 8273 | 18544 | 29500 | 9101 | 20399 | 12453 | 3842 | 8611 | 22603 | 6973 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 335650 | 103551 | 232099 | 463885 | 143112 | 320773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 1094325 | 360554 | 733771 | 1632824 | 503737 | 1129087 | 2051021 | 632755 | 1418266 | 1094325 | 360554 | 733771 | 1632824 | 503737 | 1129087 | 10800 | 10800 | Ute Indian Tribe
NT10BIX5570145 | INF | 2012 | Q2 | Q2 - 2012 | 167229 | 51591 | 115638 | 161904 | 49949 | 111955 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 205683 | 63455 | 142228 | 251750 | 77667 | 174083 | 740184 | 228352 | 511832 | 575308 | 177487 | 397821 | 677092 | 208887 | 468204 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 29254 | 9025 | 20229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 16852 | 5198 | 11654 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 346071 | 106765 | 239306 | 402458 | 124161 | 278297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 1436774 | 443254 | 993520 | 1699233 | 524225 | 1175007 | 2051021 | 632755 | 1418266 | 1436774 | 443254 | 993520 | 1699233 | 524225 | 1175007 | 21600 | 21600 | Ute Indian Tribe
NT10BIX5570145 | INF | 2012 | Q3 | Q3 - 2012 | 167229 | 51591 | 115638 | 161904 | 49949 | 111955 | 164404 | 50720 | 113684 | 328560 | 101363 | 227197 | 328415 | 99017 | 229398 | 328415 | 99017 | 229398 | 740184 | 228352 | 511832 | 669815 | 201949 | 467866 | 704815 | 212502 | 492313 | 38180 | 11779 | 26401 | 36173 | 10907 | 25266 | 37173 | 11208 | 25965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 34156 | 10299 | 23857 | 29500 | 9101 | 20399 | 16852 | 5198 | 11654 | 22852 | 6889 | 15963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 554012 | 167035 | 386977 | 599012 | 180603 | 418409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 105300 | 31747 | 73553 | 106300 | 32049 | 74251 | 2051021 | 632755 | 1418266 | 1903127 | 575259 | 1327868 | 1997127 | 603287 | 1393840 | 2051021 | 632755 | 1418266 | 1903127 | 575259 | 1327868 | 1997127 | 603287 | 1393840 | 0 | 32400 | Ute Indian Tribe
NT10BIX5570145 | INF | 2012 | Q4 | Q4 - 2012 | 167229 | 51591 | 115638 | 164444 | 50732 | 113712 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328415 | 101318 | 227097 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 731237 | 225592 | 505644 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 37922 | 11699 | 26223 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 21480 | 6627 | 14854 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 598877 | 184758 | 414119 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106841 | 32961 | 73879 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2019872 | 623144 | 1396727 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2019872 | 623144 | 1396727 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe
NT10BIX5570145 | INF | 2013 | Q1 | Q1 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe
NT10BIX5570145 | INF | 2013 | Q2 | Q2 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe
NT10BIX5570145 | INF | 2013 | Q3 | Q3 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe
NT10BIX5570146 | INF | 2010 | Q4 | Q4 - 2010 | 11245000 | 2450000 | 8795000 | 0 | 0 | 0 | 3953014 | 1185904 | 2767110 | 24114319 | 8800000 | 15314319 | 0 | 0 | 0 | 0 | 0 | 0 | 583281 | 0 | 583281 | 89049 | 26715 | 62334 | 157282 | 47185 | 110097 | 572400 | 0 | 572400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 155063 | 46519 | 108544 | 342992 | 102898 | 240094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 244112 | 73234 | 170878 | 4453288 | 1335987 | 3117301 | 38000000 | 11400000 | 26600000 | 244112 | 73234 | 170878 | 4453288 | 1335987 | 3117301 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2011 | Q1 | Q1 - 2011 | 11245000 | 2450000 | 8795000 | 0 | 0 | 0 | 4086014 | 1225804 | 2860210 | 24114319 | 8800000 | 15314319 | 35731 | 10719 | 25012 | 1562796 | 468839 | 1093957 | 583281 | 0 | 583281 | 88476 | 26543 | 61933 | 217032 | 65109 | 151922 | 572400 | 0 | 572400 | 8000 | 2400 | 5600 | 236850 | 71055 | 165795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 310499 | 93150 | 217349 | 451493 | 135448 | 316045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 442706 | 132812 | 309894 | 6773185 | 2031955 | 4741229 | 38000000 | 11400000 | 26600000 | 442706 | 132812 | 309894 | 6773185 | 2031955 | 4741229 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2011 | Q2 | Q2 - 2011 | 11245000 | 2450000 | 8795000 | 2788252 | 836476 | 1951776 | 7825313 | 2347594 | 5477719 | 24114319 | 8800000 | 15314319 | 128386 | 38516 | 89870 | 2814107 | 844232 | 1969875 | 583281 | 0 | 583281 | 166028 | 49808 | 116220 | 265157 | 79547 | 185610 | 572400 | 0 | 572400 | 132636 | 39791 | 92845 | 330600 | 99180 | 231420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 447483 | 134245 | 313238 | 559994 | 167998 | 391996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 57521 | 17256 | 40265 | 269250 | 80775 | 188475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 3720306 | 1116092 | 2604214 | 12064421 | 3619326 | 8445095 | 38000000 | 11400000 | 26600000 | 3720306 | 1116092 | 2604214 | 12064421 | 3619326 | 8445095 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2011 | Q3 | Q3 - 2011 | 11245000 | 2450000 | 8795000 | 3296650 | 988995 | 2307655 | 8229182 | 988995 | 7240187 | 24114319 | 8800000 | 15314319 | 3076419 | 922926 | 2153493 | 10689972 | 5422926 | 5267046 | 583281 | 0 | 583281 | 210338 | 63101 | 147237 | 310156 | 63101 | 247055 | 572400 | 0 | 572400 | 180012 | 54004 | 126009 | 330600 | 54004 | 276596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 603678 | 181104 | 422575 | 764996 | 181104 | 583892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 380254 | 114076 | 266178 | 403125 | 114076 | 289049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 7747351 | 2324206 | 5423147 | 20728031 | 6824206 | 13903825 | 38000000 | 11400000 | 26600000 | 7747351 | 2324206 | 5423147 | 20728031 | 6824206 | 13903825 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2011 | Q4 | Q4 - 2011 | 11245000 | 2450000 | 8795000 | 5842101 | 1018480 | 4823621 | 8619703 | 1018480 | 7601223 | 24114319 | 8800000 | 15314319 | 10517455 | 5520441 | 4997013 | 14751543 | 6710441 | 8041102 | 583281 | 0 | 583281 | 266279 | 64982 | 201296 | 303069 | 64982 | 238087 | 572400 | 0 | 572400 | 200092 | 55614 | 144477 | 220092 | 55614 | 164478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 766339 | 186503 | 579836 | 849870 | 186503 | 663367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 617798 | 117477 | 500321 | 636448 | 117477 | 518971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 18210064 | 6963497 | 11246564 | 25380725 | 8153497 | 17227228 | 38000000 | 11400000 | 26600000 | 18210064 | 6963497 | 11246564 | 25380725 | 8153497 | 17227228 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2012 | Q1 | Q1 - 2012 | 11245000 | 2450000 | 8795000 | 6717363 | 1018480 | 5698883 | 6717363 | 1018480 | 5698883 | 24114319 | 8800000 | 15314319 | 12476815 | 6491242 | 5985573 | 16982842 | 7044773 | 9938069 | 583281 | 0 | 583281 | 303584 | 64982 | 238602 | 400157 | 64982 | 335175 | 572400 | 0 | 572400 | 217152 | 55614 | 161538 | 429300 | 55614 | 373686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 901148 | 186503 | 714645 | 966998 | 186503 | 780495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 663746 | 117477 | 546269 | 663746 | 117477 | 546269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 21279808 | 7934298 | 13345510 | 26160406 | 8487829 | 17672577 | 38000000 | 11400000 | 26600000 | 21279808 | 7934298 | 13345510 | 26160406 | 8487829 | 17672577 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2012 | Q2 | Q2 - 2012 | 11245000 | 2450000 | 8795000 | 6778932 | 1018480 | 5760452 | 9191595 | 1018480 | 8173115 | 24114319 | 8800000 | 15314319 | 14007190 | 6491242 | 7515948 | 17501099 | 7330442 | 10170657 | 583281 | 0 | 583281 | 353606 | 64982 | 288624 | 388606 | 64982 | 323624 | 572400 | 0 | 572400 | 218038 | 55614 | 162424 | 218038 | 55614 | 162424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 955980 | 186503 | 769477 | 1076481 | 186503 | 889978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 796575 | 117477 | 679098 | 810415 | 117477 | 692938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 23110321 | 7934298 | 15176023 | 29186234 | 8773498 | 20412736 | 38000000 | 11400000 | 26600000 | 23110321 | 7934298 | 15176023 | 29186234 | 8773498 | 20412736 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2012 | Q3 | Q3 - 2012 | 11245000 | 2450000 | 8795000 | 9828734 | 1129226 | 8699508 | 9859200 | 1167804 | 8700197 | 24114319 | 8800000 | 15314319 | 17231761 | 7311989 | 9919772 | 20759085 | 8363596 | 12385689 | 583281 | 0 | 583281 | 395628 | 66508 | 329120 | 425628 | 68173 | 357454 | 572400 | 0 | 572400 | 218138 | 55618 | 162520 | 218138 | 56471 | 162666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1010292 | 188475 | 821817 | 1040292 | 192546 | 847746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 810536 | 117984 | 692552 | 824376 | 121210 | 703167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 29495089 | 8869800 | 20625289 | 33126719 | 9969800 | 23156919 | 38000000 | 11400000 | 26600000 | 29495089 | 8869800 | 20625289 | 33126719 | 9969800 | 23156919 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2012 | Q4 | Q4 - 2012 | 11245000 | 2450000 | 8795000 | 9909266 | 1159111 | 8750155 | 10422493 | 1159111 | 9263382 | 24114319 | 8800000 | 15314319 | 20744955 | 8434752 | 12310203 | 23995998 | 9499752 | 14496246 | 583281 | 0 | 583281 | 440153 | 67835 | 372318 | 470153 | 67835 | 402318 | 572400 | 0 | 572400 | 218026 | 56276 | 161750 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1058478 | 191667 | 866811 | 1088478 | 191667 | 896811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 787578 | 120359 | 667219 | 787578 | 120359 | 667219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 33158456 | 10030000 | 23128456 | 36982726 | 11095000 | 25887726 | 38000000 | 11400000 | 26600000 | 33158456 | 10030000 | 23128456 | 36982726 | 11095000 | 25887726 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2013 | Q1 | Q1 - 2013 | 11245000 | 2450000 | 8795000 | 10035848 | 1159111 | 8876737 | 10704714 | 1159111 | 9545603 | 24114319 | 8800000 | 15314319 | 22414740 | 8924752 | 13489988 | 24696051 | 9804752 | 14891299 | 583281 | 0 | 583281 | 440153 | 67835 | 372318 | 454976 | 67835 | 387141 | 572400 | 0 | 572400 | 218026 | 56276 | 161750 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1084857 | 191667 | 893190 | 1114857 | 191667 | 923190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 811376 | 120359 | 691017 | 811376 | 120359 | 691017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 35005000 | 10520000 | 24485000 | 38000000 | 11400000 | 26600000 | 38000000 | 11400000 | 26600000 | 35005000 | 10520000 | 24485000 | 38000000 | 11400000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2013 | Q2 | Q2 - 2013 | 11245000 | 2450000 | 8795000 | 10009050 | 1159111 | 8849939 | 10682716 | 1159111 | 9523605 | 24114319 | 8800000 | 15314319 | 24046659 | 9704752 | 14341907 | 24669210 | 9804752 | 14864458 | 583281 | 0 | 583281 | 488810 | 67835 | 420975 | 508810 | 67835 | 440975 | 572400 | 0 | 572400 | 218025 | 56276 | 161749 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1100007 | 191667 | 908340 | 1110007 | 191667 | 918340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 811231 | 120359 | 690872 | 811231 | 120359 | 690872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 36673782 | 11300000 | 25373782 | 38000000 | 11400000 | 26600000 | 38000000 | 11400000 | 26600000 | 36673782 | 11300000 | 25373782 | 38000000 | 11400000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570146 | INF | 2013 | Q3 | Q3 - 2013 | 11245000 | 2450000 | 8795000 | 10455290 | 1177668 | 9277623 | 10455290 | 1177668 | 9277623 | 24114319 | 8800000 | 15314319 | 25605952 | 10570956 | 15034996 | 25605952 | 10570956 | 15034996 | 583281 | 0 | 583281 | 546275 | 104956 | 441319 | 546275 | 104956 | 441319 | 572400 | 0 | 572400 | 218026 | 48459 | 169566 | 218026 | 48459 | 169566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1119757 | 167520 | 952237 | 1119757 | 167520 | 952237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 810700 | 86441 | 724259 | 810700 | 86441 | 724259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 38756000 | 12156000 | 26600000 | 38756000 | 12156000 | 26600000 | 38000000 | 11400000 | 26600000 | 38756000 | 12156000 | 26600000 | 38756000 | 12156000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C.
NT10BIX5570148 | INF | 2010 | Q4 | Q4 - 2010 | 4316305 | 1299398 | 3016907 | 0 | 0 | 0 | 0 | 0 | 0 | 8189627 | 2465437 | 5724190 | 0 | 0 | 0 | 149976 | 45149 | 104827 | 6354845 | 1913088 | 4441757 | 0 | 0 | 0 | 68760 | 20700 | 48060 | 129600 | 39015 | 90585 | 0 | 0 | 0 | 48000 | 14450 | 33550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 15173 | 35227 | 0 | 0 | 0 | 5040 | 1517 | 3523 | 35200 | 10597 | 24603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 199577 | 463371 | 0 | 0 | 0 | 0 | 0 | 0 | 19738925 | 5942285 | 13796640 | 0 | 0 | 0 | 271776 | 81816 | 189960 | 19738925 | 5942285 | 13796640 | 0 | 0 | 0 | 271776 | 81816 | 189960 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2011 | Q1 | Q1 - 2011 | 4316305 | 1299398 | 3016907 | 150159 | 0 | 150159 | 500000 | 151235 | 348765 | 8189627 | 2465437 | 5724190 | 1080416 | 1080416 | 0 | 218800 | 65859 | 152941 | 6354845 | 1913088 | 4441757 | 39185 | 0 | 39185 | 1791872 | 1620624 | 171248 | 129600 | 39015 | 90585 | 0 | 0 | 0 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19469 | 0 | 19469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 15173 | 35227 | 0 | 0 | 0 | 12600 | 3793 | 8807 | 35200 | 10597 | 24603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 199577 | 463371 | 0 | 0 | 0 | 0 | 0 | 0 | 19738925 | 5942285 | 13796640 | 1289229 | 1080416 | 208813 | 2573272 | 1856561 | 716711 | 19738925 | 5942285 | 13796640 | 1289229 | 1080416 | 208813 | 2573272 | 1856561 | 716711 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2011 | Q2 | Q2 - 2011 | 4316305 | 0 | 4316305 | 1546888 | 0 | 1546888 | 2315500 | 0 | 2315500 | 8189627 | 0 | 8189627 | 88524 | 0 | 88524 | 2802814 | 0 | 2802814 | 6354845 | 5942285 | 412560 | 1261138 | 1080416 | 180722 | 4835523 | 4454801 | 380722 | 129600 | 0 | 129600 | 46317 | 0 | 46317 | 77760 | 0 | 77760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 1225 | 0 | 1225 | 16128 | 0 | 16128 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 2944092 | 1080416 | 1863676 | 10710673 | 4454801 | 6255872 | 19738925 | 5942285 | 13796640 | 2944092 | 1080416 | 1863676 | 10710673 | 4454801 | 6255872 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2011 | Q3 | Q3 - 2011 | 4316305 | 0 | 4316305 | 2324177 | 0 | 2324177 | 2325000 | 0 | 2325000 | 8189627 | 0 | 8189627 | 935600 | 0 | 935600 | 2802814 | 0 | 2802814 | 6354845 | 5942285 | 412560 | 4751379 | 4454801 | 296578 | 4951379 | 4454801 | 496578 | 129600 | 0 | 129600 | 172352 | 0 | 172352 | 260602 | 0 | 260602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 1225 | 0 | 1225 | 16128 | 0 | 16128 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 8184733 | 4454801 | 3729932 | 11018871 | 4454801 | 6564070 | 19738925 | 5942285 | 13796640 | 8184733 | 4454801 | 3729932 | 11018871 | 4454801 | 6564070 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2011 | Q4 | Q4 - 2011 | 3316305 | 0 | 3316305 | 2324177 | 0 | 2324177 | 2324177 | 0 | 2324177 | 14245272 | 5285285 | 8959987 | 6671267 | 4466701 | 2204566 | 8344973 | 4466701 | 3878272 | 928800 | 542000 | 386800 | 403387 | 100614 | 302773 | 539700 | 164927 | 374773 | 500000 | 115000 | 385000 | 197243 | 23648 | 173595 | 220243 | 38648 | 181595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 9647802 | 4590963 | 5056839 | 12143769 | 4670276 | 7473493 | 19738925 | 5942285 | 13796640 | 9647802 | 4590963 | 5056839 | 12143769 | 4670276 | 7473493 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2012 | Q1 | Q1 - 2012 | 3031253 | 0 | 3031253 | 2327822 | 0 | 2327822 | 2331722 | 0 | 2331722 | 14245272 | 5285285 | 8959987 | 8295747 | 4466701 | 3829046 | 10205696 | 4466701 | 5738995 | 928800 | 542000 | 386800 | 462945 | 158351 | 304594 | 574563 | 222664 | 351899 | 500000 | 115000 | 385000 | 221631 | 41178 | 180453 | 290000 | 53178 | 236822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 0 | 0 | 0 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 11359873 | 4666230 | 6693643 | 14401709 | 4742543 | 9659166 | 19738925 | 5942285 | 13796640 | 11359873 | 4666230 | 6693643 | 14401709 | 4742543 | 9659166 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2012 | Q2 | Q2 - 2012 | 3031253 | 0 | 3031253 | 2363077 | 0 | 2363077 | 2455500 | 0 | 2455500 | 14245272 | 5285285 | 8959987 | 9635749 | 4466701 | 5169048 | 11105500 | 4466701 | 6638799 | 928800 | 542000 | 386800 | 531446 | 217665 | 313781 | 633877 | 281978 | 351899 | 500000 | 115000 | 385000 | 330340 | 51758 | 278582 | 400655 | 66758 | 333897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 13860340 | 4736124 | 9124216 | 15595260 | 4815437 | 10779823 | 19738925 | 5942285 | 13796640 | 13860340 | 4736124 | 9124216 | 15595260 | 4815437 | 10779823 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2012 | Q3 | Q3 - 2012 | 3031253 | 0 | 3031253 | 2534594 | 0 | 2534594 | 2608094 | 0 | 2608094 | 14245272 | 5285285 | 8959987 | 11192663 | 4511201 | 6681462 | 11884500 | 4661201 | 7223299 | 928800 | 542000 | 386800 | 604457 | 272771 | 331686 | 689772 | 337086 | 352686 | 500000 | 115000 | 385000 | 405616 | 65239 | 340377 | 445616 | 80239 | 365377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 15737058 | 4849211 | 10887847 | 16627710 | 5078526 | 11549184 | 19738925 | 5942285 | 13796640 | 15737058 | 4849211 | 10887847 | 16627710 | 5078526 | 11549184 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2012 | Q4 | Q4 - 2012 | 3031253 | 0 | 3031253 | 2607867 | 0 | 2607867 | 2637867 | 0 | 2637867 | 14245272 | 5285285 | 8959987 | 11846982 | 4692871 | 7154111 | 12281265 | 4692871 | 7588394 | 928800 | 542000 | 386800 | 693809 | 329641 | 364168 | 738809 | 374641 | 364168 | 500000 | 115000 | 385000 | 441941 | 75192 | 366749 | 461941 | 90192 | 371749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 17100 | 0 | 17100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 16590327 | 5097704 | 11492623 | 17136710 | 5157704 | 11979006 | 19738925 | 5942285 | 13796640 | 16590327 | 5097704 | 11492623 | 17136710 | 5157704 | 11979006 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2013 | Q1 | Q1 - 2013 | 2781253 | 0 | 2781253 | 2643458 | 0 | 2643458 | 2768458 | 0 | 2768458 | 14443944 | 5285285 | 9158659 | 12416761 | 4850005 | 7566756 | 12721765 | 5155006 | 7566759 | 978800 | 542000 | 436800 | 787884 | 368199 | 419685 | 804999 | 368199 | 436800 | 500000 | 115000 | 385000 | 455615 | 79207 | 376408 | 464207 | 79207 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17303446 | 5297411 | 12006035 | 17794357 | 5602412 | 12191945 | 19738925 | 5942285 | 13796640 | 17303446 | 5297411 | 12006035 | 17794357 | 5602412 | 12191945 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2013 | Q2 | Q2 - 2013 | 2613062 | 0 | 2613062 | 2613062 | 0 | 2613062 | 2613062 | 0 | 2613062 | 14612135 | 5285285 | 9326850 | 12652358 | 4905023 | 7747335 | 12952358 | 5155024 | 7797334 | 978800 | 542000 | 436800 | 810540 | 368199 | 442341 | 845540 | 368199 | 477341 | 500000 | 115000 | 385000 | 476760 | 79207 | 397553 | 478760 | 79207 | 399553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 4723 | 0 | 4723 | 4723 | 0 | 4723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17557171 | 5352429 | 12204742 | 17894171 | 5602430 | 12291741 | 19738925 | 5942285 | 13796640 | 17557171 | 5352429 | 12204742 | 17894171 | 5602430 | 12291741 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2013 | Q3 | Q3 - 2013 | 2613062 | 0 | 2613062 | 2613599 | 0 | 2613599 | 2613599 | 0 | 2613599 | 14612135 | 5285285 | 9326850 | 13014033 | 5215892 | 7798141 | 13105000 | 5215892 | 7889108 | 978800 | 542000 | 436800 | 845552 | 403211 | 442341 | 902577 | 460236 | 442341 | 500000 | 115000 | 385000 | 479995 | 82442 | 397553 | 500000 | 102447 | 397553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 1278 | 0 | 1278 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17954185 | 5701545 | 12252640 | 18156104 | 5778575 | 12377529 | 19738925 | 5942285 | 13796640 | 17954185 | 5701545 | 12252640 | 18156104 | 5778575 | 12377529 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2013 | Q4 | Q4 - 2013 | 2613062 | 0 | 2613062 | 2613599 | 0 | 2613599 | 2613599 | 0 | 2613599 | 14612135 | 5285285 | 9326850 | 13135256 | 5227225 | 7908031 | 13664316 | 5285285 | 8379031 | 978800 | 542000 | 436800 | 857123 | 414782 | 442341 | 917123 | 474782 | 442341 | 500000 | 115000 | 385000 | 492017 | 94464 | 397553 | 500000 | 102447 | 397553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 3750 | 0 | 3750 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 18101473 | 5736471 | 12365002 | 18729966 | 5862514 | 12867452 | 19738925 | 5942285 | 13796640 | 18101473 | 5736471 | 12365002 | 18729966 | 5862514 | 12867452 | 0 | 0 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2014 | Q1 | Q1 - 2014 | 2613062 | 0 | 2613062 | 2615945 | 2346 | 2613599 | 2615945 | 2346 | 2613599 | 14612135 | 5285285 | 9326850 | 15334347 | 7061270 | 8273077 | 15900939 | 7061270 | 8839669 | 978800 | 542000 | 436800 | 858783 | 416442 | 442341 | 878800 | 416442 | 462358 | 500000 | 115000 | 385000 | 495617 | 98064 | 397553 | 500000 | 98064 | 401936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 3750 | 0 | 3750 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 20308170 | 7578122 | 12730048 | 20930612 | 7578122 | 13352490 | 19738925 | 5942285 | 13796640 | 20308170 | 7578122 | 12730048 | 20930612 | 7578122 | 13352490 | 0 | 2675916 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2014 | Q2 | Q2 - 2014 | 2613062 | 0 | 2613062 | 2615945 | 2346 | 2613599 | 2615945 | 2346 | 2613599 | 14612135 | 5285285 | 9326850 | 15465574 | 7092520 | 8373054 | 16325739 | 7092520 | 9233219 | 978800 | 542000 | 436800 | 858783 | 416442 | 442341 | 903800 | 461459 | 442341 | 500000 | 115000 | 385000 | 497693 | 100140 | 397553 | 500000 | 102447 | 397553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 3750 | 0 | 3750 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 20441473 | 7611448 | 12830025 | 21380412 | 7658772 | 13721640 | 19738925 | 5942285 | 13796640 | 20441473 | 7611448 | 12830025 | 21380412 | 7658772 | 13721640 | 0 | 2709242 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2014 | Q3 | Q3 - 2014 | 2613062 | 0 | 2613062 | 2617945 | 2346 | 2615599 | 2617945 | 2346 | 2615599 | 14612135 | 5285285 | 9326850 | 16023652 | 7092520 | 8931132 | 16278415 | 7092520 | 9185895 | 978800 | 542000 | 436800 | 925780 | 416442 | 509338 | 978800 | 416442 | 562358 | 500000 | 115000 | 385000 | 500000 | 100140 | 399860 | 500000 | 100140 | 399860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 21983 | 0 | 21983 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 21089088 | 7611448 | 13477640 | 21410088 | 7611448 | 13798640 | 19738925 | 5942285 | 13796640 | 21089088 | 7611448 | 13477640 | 21410088 | 7611448 | 13798640 | 0 | 2709242 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2014 | Q4 | Q4 - 2014 | 2613062 | 0 | 2613062 | 2617945 | 2346 | 2615599 | 2617945 | 2346 | 2615599 | 14612135 | 5285285 | 9326850 | 16193474 | 7104686 | 9088788 | 16303800 | 7104686 | 9199114 | 978800 | 542000 | 436800 | 957388 | 448050 | 509338 | 963800 | 448050 | 515750 | 500000 | 115000 | 385000 | 500000 | 100140 | 399860 | 500000 | 100140 | 399860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35000 | 0 | 35000 | 25394 | 3411 | 21983 | 35000 | 3411 | 31589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738725 | 5942285 | 13796440 | 21293929 | 7658633 | 13635296 | 21420273 | 7658633 | 13761640 | 19738725 | 5942285 | 13796440 | 21293929 | 7658633 | 13635296 | 21420273 | 7658633 | 13761640 | 0 | 2756427 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2015 | Q1 | Q1 - 2015 | 2613062 | 0 | 2613062 | 2617945 | 2346 | 2615599 | 2617945 | 2346 | 2615599 | 14612135 | 5285285 | 9326850 | 16254255 | 7165467 | 9088788 | 16364581 | 7165467 | 9199114 | 978800 | 542000 | 436800 | 957978 | 448640 | 509338 | 964390 | 448640 | 515750 | 500000 | 115000 | 385000 | 500000 | 100140 | 399860 | 500000 | 100140 | 399860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 25394 | 3411 | 21983 | 35000 | 3411 | 31589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 21355300 | 7720004 | 13635296 | 21481644 | 7720004 | 13761640 | 19738925 | 5942285 | 13796640 | 21355300 | 7720004 | 13635296 | 21481644 | 7720004 | 13761640 | 0 | 2817798 | Ronan Telephone Co.
NT10BIX5570148 | INF | 2015 | Q2 | Q2 - 2015 | 2613062 | 0 | 2613062 | 2617945 | 2346 | 2615599 | 2617945 | 2346 | 2615599 | 14612135 | 5285285 | 9326850 | 16345352 | 7195365 | 9149987 | 16435691 | 7195365 | 9240326 | 978800 | 542000 | 436800 | 958235 | 448897 | 509338 | 958235 | 448897 | 509338 | 500000 | 115000 | 385000 | 500300 | 100440 | 399860 | 500300 | 100440 | 399860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 25394 | 3411 | 21983 | 35200 | 3411 | 31789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 21446954 | 7750459 | 13696495 | 21547099 | 7750459 | 13796640 | 19738925 | 5942285 | 13796640 | 21446954 | 7750459 | 13696495 | 21547099 | 7750459 | 13796640 | 0 | 2848252 | Ronan Telephone Co.
NT10BIX5570150 | INF | 2010 | Q4 | Q4 - 2010 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 0 | 0 | 0 | 70971874 | 13914779 | 57057095 | 0 | 0 | 0 | 4200000 | 840000 | 3360000 | 650000 | 190803 | 459197 | 4118 | 0 | 4118 | 21500 | 4300 | 17200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 25872 | 25872 | 0 | 1195000 | 239000 | 956000 | 117318786 | 23463757 | 93855029 | 29990 | 25872 | 4118 | 5416500 | 1083300 | 4333200 | 117318786 | 23463757 | 93855029 | 29990 | 25872 | 4118 | 5416500 | 1083300 | 4333200 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2011 | Q1 | Q1 - 2011 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 12190000 | 2450000 | 9740000 | 70971874 | 13914779 | 57057095 | 5224750 | 3774750 | 1450000 | 14750000 | 3774750 | 10975250 | 650000 | 190803 | 459197 | 39753 | 0 | 39753 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 67711 | 25872 | 41839 | 2250000 | 450000 | 1800000 | 117318786 | 23463757 | 93855029 | 5332214 | 3800622 | 1531592 | 29250000 | 6686750 | 22563250 | 117318786 | 23463757 | 93855029 | 5332214 | 3800622 | 1531592 | 29250000 | 6686750 | 22563250 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2011 | Q2 | Q2 - 2011 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 14550000 | 2900000 | 11650000 | 70971874 | 13914779 | 57057095 | 12877410 | 4599750 | 8277660 | 21125000 | 5500000 | 15625000 | 650000 | 190803 | 459197 | 47118 | 0 | 47118 | 67000 | 12000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 146343 | 36468 | 109875 | 1988750 | 423750 | 1565000 | 117318786 | 23463757 | 93855029 | 13070871 | 4636218 | 8434653 | 37730750 | 8835750 | 28895000 | 117318786 | 23463757 | 93855029 | 13070871 | 4636218 | 8434653 | 37730750 | 8835750 | 28895000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2011 | Q3 | Q3 - 2011 | 38619962 | 7441061 | 31178901 | 5794718 | 0 | 5794718 | 16750000 | 4187500 | 12562500 | 70971874 | 13914779 | 57057095 | 21851754 | 7030713 | 14821041 | 30500000 | 9150000 | 21350000 | 650000 | 190803 | 459197 | 47118 | 0 | 47118 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 296274 | 75732 | 220542 | 850000 | 170000 | 680000 | 117318786 | 23463757 | 93855029 | 27989864 | 7106445 | 20883419 | 48160000 | 13519500 | 34640500 | 117318786 | 23463757 | 93855029 | 27989864 | 7106445 | 20883419 | 48160000 | 13519500 | 34640500 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2011 | Q4 | Q4 - 2011 | 38619962 | 7441061 | 31178901 | 19742681 | 3065267 | 16677414 | 26000000 | 6350000 | 19650000 | 70971874 | 13914779 | 57057095 | 24714136 | 7426095 | 17288041 | 38000000 | 9250000 | 28750000 | 650000 | 190803 | 459197 | 49709 | 0 | 49709 | 62500 | 12500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 414820 | 104838 | 309982 | 1500000 | 387500 | 1112500 | 117318786 | 23463757 | 93855029 | 44921346 | 10596200 | 34325146 | 65562500 | 16000000 | 49562500 | 117318786 | 23463757 | 93855029 | 44921346 | 10596200 | 34325146 | 65562500 | 16000000 | 49562500 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2012 | Q1 | Q1 - 2012 | 38619962 | 7441061 | 31178901 | 27024480 | 3066222 | 23958258 | 31200000 | 5600000 | 25600000 | 70971874 | 13914779 | 57057095 | 29907549 | 9597628 | 20309921 | 45800000 | 9960000 | 35840000 | 650000 | 190803 | 459197 | 50627 | 0 | 50627 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 846019 | 230000 | 616019 | 2000000 | 400000 | 1600000 | 117318786 | 23463757 | 93855029 | 57828675 | 12893850 | 44934825 | 79200000 | 16000000 | 63200000 | 117318786 | 23463757 | 93855029 | 57828675 | 12893850 | 44934825 | 79200000 | 16000000 | 63200000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2012 | Q2 | Q2 - 2012 | 38619962 | 7441061 | 31178901 | 27580205 | 3085374 | 24494831 | 32850000 | 6570000 | 26280000 | 70971874 | 13914779 | 57057095 | 46166804 | 9597628 | 36569176 | 54250000 | 10850000 | 43400000 | 650000 | 190803 | 459197 | 56076 | 4544 | 51532 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 1653137 | 349248 | 1303889 | 3250000 | 650000 | 2600000 | 117318786 | 23463757 | 93855029 | 75456222 | 13036794 | 62419428 | 90550000 | 18110000 | 72440000 | 117318786 | 23463757 | 93855029 | 75456222 | 13036794 | 62419428 | 90550000 | 18110000 | 72440000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2012 | Q3 | Q3 - 2012 | 38619962 | 7441061 | 31178901 | 29136068 | 3469406 | 25666662 | 32250000 | 6450000 | 25800000 | 70971874 | 13914779 | 57057095 | 54766451 | 9597628 | 45168823 | 62750000 | 12550000 | 50200000 | 650000 | 190803 | 459197 | 59211 | 6191 | 53020 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 2328106 | 412976 | 1915130 | 4500000 | 900000 | 3600000 | 117318786 | 23463757 | 93855029 | 86289836 | 13486201 | 72803635 | 99575000 | 19915000 | 79660000 | 117318786 | 23463757 | 93855029 | 86289836 | 13486201 | 72803635 | 99575000 | 19915000 | 79660000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2012 | Q4 | Q4 - 2012 | 38619962 | 7441061 | 31178901 | 35085673 | 6477287 | 28608386 | 37500000 | 7000000 | 30500000 | 70971874 | 13914779 | 57057095 | 64113748 | 13810830 | 50302918 | 67500000 | 13900000 | 53600000 | 650000 | 190803 | 459197 | 62703 | 9684 | 53020 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 2946550 | 451067 | 2495483 | 4500000 | 900000 | 3600000 | 117318786 | 23463757 | 93855029 | 102208674 | 20748868 | 81459807 | 109575000 | 21815000 | 87760000 | 117318786 | 23463757 | 93855029 | 102208674 | 20748868 | 81459807 | 109575000 | 21815000 | 87760000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2013 | Q1 | Q1 - 2013 | 38619962 | 7441061 | 31178901 | 35549742 | 6554788 | 28994953 | 38619962 | 7441061 | 31178900 | 70971874 | 13914779 | 57057095 | 66911063 | 13914779 | 52996284 | 70971850 | 13914779 | 57057071 | 650000 | 190803 | 459197 | 62703 | 9684 | 53020 | 62703 | 9684 | 53020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 3075915 | 472160 | 2603755 | 6580425 | 1908295 | 4672130 | 117318786 | 23463757 | 93855029 | 105599423 | 20951411 | 84648012 | 116234940 | 23273819 | 92961121 | 117318786 | 23463757 | 93855029 | 105599423 | 20951411 | 84648012 | 116234940 | 23273819 | 92961121 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2013 | Q2 | Q2 - 2013 | 39575806 | 7645380 | 31930426 | 38002667 | 7407719 | 30594948 | 39575806 | 7645380 | 31930426 | 71771874 | 14146779 | 57625095 | 70971850 | 13914779 | 57057071 | 71771874 | 14146779 | 57625095 | 65000 | 9684 | 55316 | 62703 | 9683 | 53020 | 65000 | 9684 | 55316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906106 | 1661914 | 4244192 | 4148357 | 951762 | 3196595 | 5906106 | 1661914 | 4244192 | 117318786 | 23463757 | 93855029 | 113185577 | 22283943 | 90901634 | 117318786 | 23463757 | 93855029 | 117318786 | 23463757 | 93855029 | 113185577 | 22283943 | 90901634 | 117318786 | 23463757 | 93855029 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570150 | INF | 2013 | Q3 | Q3 - 2013 | 39697535 | 7756764 | 31940771 | 39650921 | 7754517 | 31896404 | 39650921 | 7754517 | 31896404 | 71771874 | 14146779 | 57625095 | 71771752 | 14146779 | 57624973 | 71771752 | 14146779 | 57624973 | 65000 | 9684 | 55316 | 62704 | 9684 | 53020 | 62704 | 9684 | 53020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5784377 | 1550530 | 4233847 | 5684672 | 1531088 | 4153584 | 5684672 | 1531088 | 4153584 | 117318786 | 23463757 | 93855029 | 117170049 | 23442068 | 93727981 | 117170049 | 23442068 | 93727981 | 117318786 | 23463757 | 93855029 | 117170049 | 23442068 | 93727981 | 117170049 | 23442068 | 93727981 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology
NT10BIX5570153 | INF | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2011 | Q1 | Q1 - 2011 | 4484034 | 1834958 | 2649076 | 267500 | 86310 | 181190 | 297549 | 59510 | 238039 | 27531256 | 8441149 | 19090107 | 7027505 | 1394147 | 5633358 | 7721930 | 1544386 | 6177544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 7295005 | 1480457 | 5814548 | 8019479 | 1603896 | 6415583 | 32476991 | 10737808 | 21739183 | 7295005 | 1480457 | 5814548 | 8019479 | 1603896 | 6415583 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2011 | Q2 | Q2 - 2011 | 4484034 | 1834958 | 2649076 | 290442 | 86310 | 204132 | 2005163 | 501290 | 1503873 | 27531256 | 8441149 | 19090107 | 7644601 | 1523321 | 6121280 | 8222038 | 2055510 | 6166528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 7935043 | 1609631 | 6325412 | 10227201 | 2556800 | 7670401 | 32476991 | 10737808 | 21739183 | 7935043 | 1609631 | 6325412 | 10227201 | 2556800 | 7670401 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2011 | Q3 | Q3 - 2011 | 4484034 | 1834958 | 2649076 | 3015884 | 1278564 | 1737320 | 4249373 | 1578564 | 2670809 | 27531256 | 8441149 | 19090107 | 7784100 | 1727781 | 6056319 | 12347562 | 2227781 | 10119781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 10799984 | 3006345 | 7793639 | 16596935 | 3806345 | 12790590 | 32476991 | 10737808 | 21739183 | 10799984 | 3006345 | 7793639 | 16596935 | 3806345 | 12790590 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2011 | Q4 | Q4 - 2011 | 4484034 | 1834958 | 2649076 | 4427596 | 1771039 | 2656557 | 4484034 | 1793614 | 2690420 | 27531256 | 8441149 | 19090107 | 12251700 | 2964338 | 9287362 | 15095457 | 3764338 | 11331119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 16679296 | 4735377 | 11943919 | 19579491 | 5557952 | 14021539 | 32476991 | 10737808 | 21739183 | 16679296 | 4735377 | 11943919 | 19579491 | 5557952 | 14021539 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2012 | Q1 | Q1 - 2012 | 4484034 | 1834958 | 2649076 | 5496885 | 2213902 | 3282983 | 6248380 | 2482007 | 3766373 | 27531256 | 8441149 | 19090107 | 14023524 | 3205456 | 10818068 | 15380039 | 3845010 | 11535029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 19520409 | 5419358 | 14101051 | 21628419 | 6327017 | 15301402 | 32476991 | 10737808 | 21739183 | 19520409 | 5419358 | 14101051 | 21628419 | 6327017 | 15301402 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2012 | Q2 | Q2 - 2012 | 4484034 | 1834958 | 2649076 | 6385505 | 2479757 | 3905748 | 7018065 | 2807226 | 4210839 | 27531256 | 8441149 | 19090107 | 14460705 | 3424806 | 11035899 | 16527535 | 4131884 | 12395651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 20846210 | 5904563 | 14941647 | 23545600 | 6939110 | 16606490 | 32476991 | 10737808 | 21739183 | 20846210 | 5904563 | 14941647 | 23545600 | 6939110 | 16606490 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2012 | Q3 | Q3 - 2012 | 4484034 | 1834958 | 2649076 | 6438186 | 2508520 | 3929666 | 6624891 | 2508520 | 4116371 | 27531256 | 8441149 | 19090107 | 19828407 | 4696882 | 15131525 | 21374984 | 5343746 | 16031238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 26266593 | 7205402 | 19061191 | 27999875 | 7852266 | 20147609 | 32476991 | 10737808 | 21739183 | 26266593 | 7205402 | 19061191 | 27999875 | 7852266 | 20147609 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2012 | Q4 | Q4 - 2012 | 4484034 | 1834958 | 2649076 | 6615274 | 2559772 | 4055502 | 6746553 | 2697516 | 4049037 | 27531256 | 8441149 | 19090107 | 21024308 | 5431277 | 15593031 | 23245548 | 6643933 | 16601615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 27639582 | 7991049 | 19648533 | 29992101 | 9341449 | 20650652 | 32476991 | 10737808 | 21739183 | 27639582 | 7991049 | 19648533 | 29992101 | 9341449 | 20650652 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2013 | Q1 | Q1 - 2013 | 7102776 | 2484533 | 4618243 | 6658650 | 2648803 | 4009847 | 6672200 | 2655474 | 4016726 | 24046719 | 8072258 | 15974461 | 20362892 | 4971237 | 15391655 | 23669347 | 6455975 | 17213372 | 629796 | 78349 | 551447 | 512773 | 344818 | 167955 | 541773 | 373818 | 167955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583182 | 102669 | 480513 | 518072 | 313929 | 204143 | 560572 | 356429 | 204143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114518 | 0 | 114518 | 107250 | 18645 | 88605 | 107250 | 18645 | 88605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737809 | 21739182 | 28159637 | 8297432 | 19862205 | 31551142 | 9860341 | 21690801 | 32476991 | 10737809 | 21739182 | 28159637 | 8297432 | 19862205 | 31551142 | 9860341 | 21690801 | 0 | 604782 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2013 | Q2 | Q2 - 2013 | 7102776 | 2781489 | 4321287 | 6706546 | 2689820 | 4016726 | 7363860 | 3314150 | 4049710 | 24046719 | 7775301 | 16271418 | 21947577 | 5541546 | 16406031 | 23799961 | 6578615 | 17221346 | 629796 | 78349 | 551447 | 543334 | 375379 | 167955 | 586601 | 411222 | 175379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583182 | 102669 | 480513 | 556893 | 352750 | 204143 | 619319 | 415176 | 204143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114518 | 0 | 114518 | 107250 | 18645 | 88605 | 107250 | 18645 | 88605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 29861600 | 8978140 | 20883460 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 29861600 | 8978140 | 20883460 | 32476991 | 10737808 | 21739183 | 0 | 151639 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570153 | INF | 2013 | Q3 | Q3 - 2013 | 7364740 | 3348014 | 4016726 | 7340847 | 3324121 | 4016726 | 7340847 | 3324121 | 4016726 | 23807396 | 6555996 | 17251400 | 23796004 | 6538845 | 17257159 | 23796004 | 6538845 | 17257159 | 583286 | 404977 | 178309 | 635417 | 472753 | 162664 | 635417 | 472753 | 162664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614319 | 410176 | 204143 | 598798 | 383244 | 215554 | 598798 | 383244 | 215554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107250 | 18645 | 88605 | 105925 | 18845 | 87080 | 105925 | 18845 | 87080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 0 | 1640788 | Ocean State Higher Education Economic Development Administrative Network
NT10BIX5570156 | INF | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Centennial Board of Cooperative Educational Services
NT10BIX5570156 | INF | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Centennial Board of Cooperative Educational Services
NT10BIX5570157 | INF | 2010 | Q4 | Q4 - 2010 | 9572649 | 800000 | 8772649 | 0 | 0 | 0 | 500000 | 0 | 500000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 0 | 0 | 0 | 333000 | 120000 | 213000 | 50018 | 2200 | 47818 | 76200 | 6200 | 70000 | 1582200 | 1537200 | 45000 | 128100 | 128100 | 0 | 256200 | 256200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 63000 | 12000 | 2063882 | 253750 | 1810132 | 9485 | 9485 | 0 | 75000 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 187603 | 139785 | 47818 | 982400 | 350400 | 632000 | 18029069 | 5891647 | 12137422 | 187603 | 139785 | 47818 | 982400 | 350400 | 632000 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2011 | Q1 | Q1 - 2011 | 9572649 | 800000 | 8772649 | 488759 | 0 | 488759 | 3000000 | 500000 | 2500000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 150000 | 150000 | 0 | 333000 | 120000 | 213000 | 70349 | 7405 | 62944 | 120000 | 17000 | 103000 | 1582200 | 1537200 | 45000 | 256200 | 256200 | 0 | 384300 | 384300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 16937 | 0 | 16937 | 75000 | 0 | 75000 | 2063882 | 253750 | 1810132 | 56614 | 20614 | 36000 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 888859 | 284219 | 604640 | 3899300 | 1091300 | 2808000 | 18029069 | 5891647 | 12137422 | 888859 | 284219 | 604640 | 3899300 | 1091300 | 2808000 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2011 | Q2 | Q2 - 2011 | 9572649 | 800000 | 8772649 | 685077 | 0 | 685077 | 3000000 | 600000 | 2400000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 200000 | 0 | 200000 | 333000 | 120000 | 213000 | 95108 | 17205 | 77903 | 130000 | 30000 | 100000 | 1582200 | 1537200 | 45000 | 275415 | 275415 | 0 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 2063882 | 253750 | 1810132 | 98451 | 30739 | 67712 | 130000 | 45000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 1154051 | 323359 | 830692 | 4050000 | 1050000 | 3000000 | 18029069 | 5891647 | 12137422 | 1154051 | 323359 | 830692 | 4050000 | 1050000 | 3000000 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2011 | Q3 | Q3 - 2011 | 9572649 | 800000 | 8772649 | 1810524 | 298244 | 1512280 | 2775000 | 675000 | 2100000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 0 | 0 | 0 | 333000 | 120000 | 213000 | 145502 | 28474 | 117028 | 210000 | 50000 | 160000 | 1582200 | 1537200 | 45000 | 435540 | 435540 | 0 | 525210 | 525210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 2063882 | 253750 | 1810132 | 2293322 | 589689 | 1703633 | 3400000 | 1000000 | 2400000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 608869 | 0 | 608869 | 682 | 0 | 682 | 275000 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 0 | 334 | 334 | 0 | 334 | 18029069 | 5891647 | 12137422 | 4686004 | 1351947 | 3334057 | 7260644 | 2250210 | 5010434 | 18029069 | 5891647 | 12137422 | 4686004 | 1351947 | 3334057 | 7260644 | 2250210 | 5010434 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2011 | Q4 | Q4 - 2011 | 6345080 | 960000 | 5385080 | 2415588 | 636227 | 1779361 | 3400000 | 830000 | 2570000 | 2451391 | 1101550 | 1349841 | 0 | 0 | 0 | 250000 | 250000 | 0 | 303000 | 150000 | 153000 | 231889 | 39460 | 192429 | 260000 | 60000 | 200000 | 1121040 | 1076040 | 45000 | 673585 | 646905 | 26680 | 750000 | 720000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 3471927 | 867645 | 2604282 | 5100000 | 1100000 | 4000000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 96002 | 0 | 96002 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 0 | 334 | 334 | 0 | 334 | 16678762 | 4541340 | 12137422 | 6899125 | 2190237 | 4708888 | 9970134 | 2960000 | 7010134 | 16678762 | 4541340 | 12137422 | 6899125 | 2190237 | 4708888 | 9970134 | 2960000 | 7010134 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2012 | Q1 | Q1 - 2012 | 6345080 | 960000 | 5385080 | 4216949 | 886277 | 3330672 | 4800000 | 986277 | 3813723 | 2451391 | 1101550 | 1349841 | 1206 | 0 | 1206 | 1200000 | 300000 | 900000 | 303000 | 150000 | 153000 | 375410 | 51864 | 323546 | 405000 | 75000 | 330000 | 1121040 | 1076040 | 45000 | 629003 | 602070 | 26933 | 750000 | 710000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 3953391 | 881744 | 3071647 | 5053391 | 981744 | 4071647 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 135657 | 0 | 135657 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239 | 0 | 1239 | 1239 | 0 | 1239 | 16678762 | 4541340 | 12137422 | 9322655 | 2421955 | 6900700 | 12419430 | 3053021 | 9366409 | 16678762 | 4541340 | 12137422 | 9322655 | 2421955 | 6900700 | 12419430 | 3053021 | 9366409 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2012 | Q2 | Q2 - 2012 | 6345080 | 960000 | 5385080 | 3388792 | 570801 | 2817991 | 3440000 | 590000 | 2850000 | 2451391 | 1101550 | 1349841 | 1206 | 0 | 1206 | 150000 | 0 | 150000 | 303000 | 150000 | 153000 | 210396 | 61986 | 148410 | 230000 | 70000 | 160000 | 1121040 | 1076040 | 45000 | 647351 | 608475 | 38876 | 766740 | 691740 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5389948 | 1255127 | 4134821 | 5605000 | 1270000 | 4335000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 189549 | 38037 | 151512 | 238037 | 38037 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516 | 0 | 2516 | 3500 | 0 | 3500 | 16678762 | 4541340 | 12137422 | 9839558 | 2534426 | 7305132 | 10443077 | 2659777 | 7783300 | 16678762 | 4541340 | 12137422 | 9839558 | 2534426 | 7305132 | 10443077 | 2659777 | 7783300 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2012 | Q3 | Q3 - 2012 | 6345080 | 960000 | 5385080 | 3438596 | 570801 | 2867795 | 3471000 | 571000 | 2900000 | 2451391 | 1101550 | 1349841 | 126934 | 113273 | 13661 | 180000 | 150000 | 30000 | 303000 | 150000 | 153000 | 215535 | 67336 | 148199 | 230000 | 70000 | 160000 | 1121040 | 1076040 | 45000 | 730616 | 691740 | 38876 | 805005 | 775005 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5605058 | 1257821 | 4347237 | 5640237 | 1270000 | 4370237 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 179906 | 38037 | 141869 | 208037 | 38037 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3320 | 0 | 3320 | 4125 | 0 | 4125 | 16678762 | 4541340 | 12137422 | 10309765 | 2739008 | 7570757 | 10548204 | 2874042 | 7674162 | 16678762 | 4541340 | 12137422 | 10309765 | 2739008 | 7570757 | 10548204 | 2874042 | 7674162 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2012 | Q4 | Q4 - 2012 | 6345080 | 960000 | 5385080 | 3442645 | 570801 | 2871844 | 3447645 | 570801 | 2876844 | 2451391 | 1101550 | 1349841 | 148774 | 113273 | 35501 | 180000 | 125000 | 55000 | 303000 | 150000 | 153000 | 224101 | 69202 | 154899 | 232000 | 73000 | 159000 | 1121040 | 1076040 | 45000 | 813881 | 775005 | 38876 | 898270 | 858270 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5630946 | 1262687 | 4368259 | 5657000 | 1267000 | 4390000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 182912 | 38037 | 144875 | 187037 | 38037 | 149000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4382 | 0 | 4382 | 5395 | 0 | 5395 | 16678762 | 4541340 | 12137422 | 10457441 | 2829005 | 7628436 | 10617147 | 2932108 | 7685039 | 16678762 | 4541340 | 12137422 | 10457441 | 2829005 | 7628436 | 10617147 | 2932108 | 7685039 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2013 | Q1 | Q1 - 2013 | 6345080 | 960000 | 5385080 | 3448357 | 570801 | 2877556 | 3463357 | 570801 | 2892556 | 2451391 | 1101550 | 1349841 | 158403 | 113273 | 45130 | 858403 | 233273 | 625130 | 303000 | 150000 | 153000 | 242130 | 75099 | 167031 | 268000 | 95000 | 173000 | 1121040 | 1076040 | 45000 | 919611 | 858270 | 61341 | 1002876 | 941535 | 61341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5660851 | 1270458 | 4390393 | 5692985 | 1280458 | 4412527 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 195116 | 38037 | 157079 | 215116 | 38037 | 177079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5372 | 0 | 5372 | 5372 | 0 | 5372 | 16678762 | 4541340 | 12137422 | 10639640 | 2925938 | 7713702 | 11515909 | 3159104 | 8356805 | 16678762 | 4541340 | 12137422 | 10639640 | 2925938 | 7713702 | 11515909 | 3159104 | 8356805 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2013 | Q2 | Q2 - 2013 | 6345080 | 960000 | 5385080 | 3449397 | 570801 | 2878596 | 3519397 | 570801 | 2948596 | 2451391 | 1101550 | 1349841 | 158429 | 113273 | 45156 | 858403 | 233273 | 625130 | 303000 | 150000 | 153000 | 252308 | 79240 | 173068 | 267000 | 89000 | 178000 | 1121040 | 1076040 | 45000 | 1002876 | 941535 | 61341 | 1086800 | 1024800 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5685128 | 1272436 | 4412692 | 5712234 | 1277000 | 4435234 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 196646 | 38037 | 158609 | 248037 | 38037 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | 6425 | 7478 | 0 | 7478 | 16678762 | 4541340 | 12137422 | 10761009 | 3015322 | 7745687 | 11709149 | 3232911 | 8476238 | 16678762 | 4541340 | 12137422 | 10761009 | 3015322 | 7745687 | 11709149 | 3232911 | 8476238 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2013 | Q3 | Q3 - 2013 | 6345080 | 960000 | 5385080 | 3452645 | 570801 | 2881844 | 3552645 | 570801 | 2981844 | 2451391 | 1101550 | 1349841 | 890859 | 333002 | 557857 | 890859 | 333002 | 557857 | 303000 | 150000 | 153000 | 272626 | 84717 | 187909 | 309000 | 89000 | 220000 | 1121040 | 1076040 | 45000 | 1058386 | 997045 | 61341 | 1059045 | 997045 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5709072 | 1273838 | 4435234 | 5735000 | 1275000 | 4460000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 196646 | 38037 | 158609 | 247037 | 38037 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488 | 0 | 7488 | 8572 | 0 | 8572 | 16678762 | 4541340 | 12137422 | 11597522 | 3297440 | 8300082 | 11811958 | 3302885 | 8509073 | 16678762 | 4541340 | 12137422 | 11597522 | 3297440 | 8300082 | 11811958 | 3302885 | 8509073 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2013 | Q4 | Q4 - 2013 | 6345080 | 960000 | 5385080 | 3454638 | 570801 | 2883837 | 3504638 | 570801 | 2933837 | 2451391 | 1101550 | 1349841 | 890859 | 333002 | 557857 | 990859 | 393002 | 597857 | 303000 | 150000 | 153000 | 301600 | 87383 | 214217 | 321600 | 90383 | 231217 | 1121040 | 1076040 | 45000 | 1169406 | 1108065 | 61341 | 1252671 | 1191330 | 61341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944521 | 1253750 | 4690501 | 5735489 | 1273838 | 4461651 | 5780708 | 1275838 | 4504870 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 223865 | 38037 | 185828 | 278865 | 38037 | 240828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8572 | 0 | 8572 | 8572 | 0 | 8572 | 16679032 | 4541340 | 12137422 | 11794229 | 3411126 | 8383103 | 12147713 | 3559391 | 8588322 | 16679032 | 4541340 | 12137422 | 11794229 | 3411126 | 8383103 | 12147713 | 3559391 | 8588322 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2014 | Q1 | Q1 - 2014 | 4769371 | 676501 | 4092870 | 3560338 | 676501 | 2883837 | 3834218 | 676501 | 3157717 | 1505943 | 746992 | 758951 | 890859 | 333002 | 557857 | 1354849 | 746992 | 607857 | 583584 | 114686 | 468898 | 346485 | 88626 | 257859 | 381485 | 90626 | 290859 | 1543553 | 1441125 | 102428 | 1252671 | 1191330 | 61341 | 1336671 | 1275330 | 61341 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7424536 | 1363804 | 6060732 | 5760595 | 1274807 | 4485788 | 6142893 | 1277807 | 4865086 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 663878 | 38037 | 625841 | 241780 | 38037 | 203743 | 291780 | 38037 | 253743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900 | 0 | 12900 | 9697 | 0 | 9697 | 10841 | 0 | 10841 | 16518565 | 4381145 | 12137420 | 12072225 | 3602303 | 8469922 | 13362537 | 4105293 | 9257244 | 16518565 | 4381145 | 12137420 | 12072225 | 3602303 | 8469922 | 13362537 | 4105293 | 9257244 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2014 | Q2 | Q2 - 2014 | 4769371 | 676501 | 4092870 | 3836749 | 676501 | 3160248 | 4061749 | 676501 | 3385248 | 1505943 | 746992 | 758951 | 1160549 | 602692 | 557857 | 1369849 | 746992 | 622857 | 583584 | 114686 | 468898 | 381635 | 92411 | 289224 | 427635 | 98411 | 329224 | 1543553 | 1441125 | 102428 | 1335936 | 1274595 | 61341 | 1419201 | 1357860 | 61341 | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0 | 5000 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7424536 | 1363804 | 6060732 | 6183319 | 1287561 | 4895758 | 7206722 | 1307561 | 5899161 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 663878 | 38037 | 625841 | 254063 | 38037 | 216026 | 304063 | 38037 | 266026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900 | 0 | 12900 | 10841 | 0 | 10841 | 11985 | 0 | 11985 | 16518565 | 4381145 | 12137420 | 13172892 | 3971797 | 9201095 | 14816004 | 4225362 | 10590642 | 16518565 | 4381145 | 12137420 | 13172892 | 3971797 | 9201095 | 14816004 | 4225362 | 10590642 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2014 | Q3 | Q3 - 2014 | 4769371 | 676501 | 4092870 | 3884889 | 676501 | 3208388 | 4064889 | 676501 | 3388388 | 1505943 | 746992 | 758951 | 1327414 | 746992 | 580422 | 1357414 | 746992 | 610422 | 583584 | 114686 | 468898 | 413919 | 95080 | 318839 | 448919 | 100080 | 348839 | 1543553 | 1441125 | 102428 | 1419201 | 1357860 | 61341 | 1502466 | 1441125 | 61341 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7424536 | 1363804 | 6060732 | 6233731 | 1301136 | 4932595 | 7323079 | 1324773 | 5998306 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 663878 | 38037 | 625841 | 257085 | 38037 | 219048 | 282085 | 38037 | 244048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900 | 0 | 12900 | 12018 | 0 | 12018 | 12900 | 0 | 12900 | 16518565 | 4381145 | 12137420 | 13558057 | 4215606 | 9342451 | 15001552 | 4327508 | 10674044 | 16518565 | 4381145 | 12137420 | 13558057 | 4215606 | 9342451 | 15001552 | 4327508 | 10674044 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2014 | Q4 | Q4 - 2014 | 4769371 | 676501 | 4092870 | 3904412 | 676501 | 3227911 | 4204412 | 676501 | 3527911 | 1505943 | 746992 | 758951 | 1368165 | 746992 | 621173 | 1418165 | 746992 | 671173 | 583584 | 114686 | 468898 | 442039 | 95080 | 346959 | 457039 | 95080 | 361959 | 1543553 | 1441125 | 102428 | 1502466 | 1441125 | 61341 | 1595731 | 1524390 | 71341 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7424536 | 1363804 | 6060732 | 6753468 | 1306553 | 5446916 | 6853469 | 1306553 | 5546916 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 663878 | 38037 | 625841 | 275730 | 38037 | 237694 | 275730 | 38037 | 237694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12900 | 0 | 12900 | 12611 | 0 | 12611 | 13282 | 0 | 13282 | 16518565 | 4381145 | 12137420 | 14268691 | 4304288 | 9964405 | 14827628 | 4387553 | 10440076 | 16518565 | 4381145 | 12137420 | 14268691 | 4304288 | 9964405 | 14827628 | 4387553 | 10440076 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2015 | Q1 | Q1 - 2015 | 4957871 | 676501 | 4281370 | 4129520 | 676501 | 3453019 | 4957871 | 676501 | 4281370 | 1505943 | 746992 | 758951 | 1385936 | 746992 | 638944 | 1505943 | 746992 | 758951 | 583584 | 114686 | 468898 | 449127 | 95080 | 354047 | 583584 | 114686 | 468898 | 1710083 | 1607655 | 102428 | 1585731 | 1524390 | 61340 | 1710083 | 1607655 | 102428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7418201 | 1357469 | 6060732 | 7179470 | 1309330 | 5870141 | 7418201 | 1357469 | 6060732 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 478878 | 38037 | 440841 | 287307 | 38037 | 249270 | 478878 | 38037 | 440841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 14400 | 13349 | 0 | 13349 | 14400 | 0 | 14400 | 16678760 | 4541340 | 12137420 | 15040240 | 4390330 | 10649910 | 16678760 | 4541340 | 12137420 | 16678760 | 4541340 | 12137420 | 15040240 | 4390330 | 10649910 | 16678760 | 4541340 | 12137420 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570157 | INF | 2015 | Q2 | Q2 - 2015 | 4957871 | 676501 | 4281370 | 4201933 | 676501 | 3525432 | 4476933 | 676501 | 3800432 | 1505943 | 746992 | 758951 | 1385936 | 746992 | 638944 | 1385936 | 746992 | 638944 | 583584 | 114686 | 468898 | 449127 | 95080 | 354047 | 454127 | 95080 | 359047 | 1710083 | 1607655 | 102428 | 1668996 | 1607655 | 61341 | 1752261 | 1690920 | 61341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 7418201 | 1357469 | 6060732 | 7207739 | 1313798 | 5893941 | 7212739 | 1318798 | 5893941 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 478878 | 38037 | 440841 | 287307 | 38037 | 249270 | 320516 | 38037 | 282479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 14400 | 14019 | 0 | 14019 | 14400 | 0 | 14400 | 16678760 | 4541340 | 12137420 | 15224857 | 4478063 | 10746794 | 15626712 | 4566328 | 11060384 | 16678760 | 4541340 | 12137420 | 15224857 | 4478063 | 10746794 | 15626712 | 4566328 | 11060384 | 0 | 0 | Adams County Communications Center, Inc.
NT10BIX5570158 | INF | 2010 | Q4 | Q4 - 2010 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 62968 | 62968 | 0 | 200000 | 200000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 0 | 0 | 0 | 560000 | 60000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 62968 | 62968 | 0 | 760000 | 260000 | 500000 | 217894365 | 63254365 | 154640000 | 62968 | 62968 | 0 | 760000 | 260000 | 500000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2011 | Q1 | Q1 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 80029 | 80029 | 0 | 359555 | 359555 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 515778 | 0 | 515778 | 1499998 | 0 | 1499998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 595807 | 80029 | 515778 | 1859553 | 359555 | 1499998 | 217894365 | 63254365 | 154640000 | 595807 | 80029 | 515778 | 1859553 | 359555 | 1499998 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2011 | Q2 | Q2 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 535480 | 535480 | 0 | 800000 | 800000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1095026 | 0 | 1095026 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 1630506 | 535480 | 1095026 | 2800000 | 800000 | 2000000 | 217894365 | 63254365 | 154640000 | 1630506 | 535480 | 1095026 | 2800000 | 800000 | 2000000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2011 | Q3 | Q3 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 796390 | 796390 | 0 | 1000000 | 1000000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2194522 | 796390 | 1398132 | 3000000 | 1000000 | 2000000 | 217894365 | 63254365 | 154640000 | 2194522 | 796390 | 1398132 | 3000000 | 1000000 | 2000000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2011 | Q4 | Q4 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 999240 | 999240 | 0 | 1200000 | 1200000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2100000 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2397372 | 999240 | 1398132 | 3300000 | 1200000 | 2100000 | 217894365 | 63254365 | 154640000 | 2397372 | 999240 | 1398132 | 3300000 | 1200000 | 2100000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2012 | Q1 | Q1 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 1289713 | 1289713 | 0 | 1400000 | 1400000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2607410 | 0 | 2607410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2687845 | 1289713 | 1398132 | 4007410 | 1400000 | 2607410 | 217894365 | 63254365 | 154640000 | 2687845 | 1289713 | 1398132 | 4007410 | 1400000 | 2607410 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2012 | Q2 | Q2 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 1448699 | 1448699 | 0 | 1600000 | 1600000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2362853 | 0 | 2362853 | 2600000 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 3811552 | 1448699 | 2362853 | 4200000 | 1600000 | 2600000 | 217894365 | 63254365 | 154640000 | 3811552 | 1448699 | 2362853 | 4200000 | 1600000 | 2600000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2012 | Q3 | Q3 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2139282 | 1823166 | 316116 | 2318524 | 1972408 | 346116 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2873560 | 0 | 2873560 | 3286120 | 0 | 3286120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5012842 | 1823166 | 3189676 | 5604644 | 1972408 | 3632236 | 217894365 | 63254365 | 154640000 | 5012842 | 1823166 | 3189676 | 5604644 | 1972408 | 3632236 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2012 | Q4 | Q4 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2309308 | 1993192 | 316116 | 2500000 | 2100000 | 400000 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2873560 | 0 | 2873560 | 2957353 | 0 | 2957353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5182868 | 1993192 | 3189676 | 5457353 | 2100000 | 3357353 | 217894365 | 63254365 | 154640000 | 5182868 | 1993192 | 3189676 | 5457353 | 2100000 | 3357353 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2013 | Q1 | Q1 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2422126 | 2067680 | 354446 | 2728000 | 2147000 | 581000 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2965717 | 0 | 2965717 | 3070000 | 0 | 3070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5387843 | 2067680 | 3320163 | 5798000 | 2147000 | 3651000 | 217894365 | 63254365 | 154640000 | 5387843 | 2067680 | 3320163 | 5798000 | 2147000 | 3651000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2013 | Q2 | Q2 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2427323 | 1973913 | 453410 | 2724911 | 2122337 | 602574 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 3367072 | 349226 | 3017846 | 3849407 | 517226 | 3332181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5794395 | 2323139 | 3471256 | 6574318 | 2639563 | 3934755 | 217894365 | 63254365 | 154640000 | 5794395 | 2323139 | 3471256 | 6574318 | 2639563 | 3934755 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2013 | Q3 | Q3 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 3007264 | 2218273 | 788991 | 3238642 | 2350228 | 888414 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 4279573 | 538792 | 3740781 | 4598090 | 639894 | 3958196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 7286837 | 2757065 | 4529772 | 7836732 | 2990122 | 4846610 | 217894365 | 63254365 | 154640000 | 7286837 | 2757065 | 4529772 | 7836732 | 2990122 | 4846610 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2013 | Q4 | Q4 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 3230200 | 2415661 | 814539 | 3637821 | 2613049 | 1024772 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 4516486 | 641413 | 3875073 | 6504968 | 744034 | 5760934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 7746686 | 3057074 | 4689612 | 10142789 | 3357083 | 6785706 | 217894365 | 63254365 | 154640000 | 7746686 | 3057074 | 4689612 | 10142789 | 3357083 | 6785706 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2014 | Q1 | Q1 - 2014 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 6576075 | 5335184 | 1240892 | 7321267 | 5585839 | 1735428 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 5541755 | 759804 | 4781951 | 6944414 | 878196 | 6066219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 12117830 | 6094988 | 6022843 | 14265681 | 6464035 | 7801647 | 217894365 | 63254365 | 154640000 | 12117830 | 6094988 | 6022843 | 14265681 | 6464035 | 7801647 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2014 | Q2 | Q2 - 2014 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 5814676 | 0 | 5814676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 7181812 | 5872483 | 1309329 | 8199238 | 6481624 | 1717614 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 6060533 | 860181 | 5200353 | 6889232 | 991218 | 5898015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 13242345 | 6732664 | 6509682 | 20903146 | 7472842 | 13430305 | 217894365 | 63254365 | 154640000 | 13242345 | 6732664 | 6509682 | 20903146 | 7472842 | 13430305 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2014 | Q3 | Q3 - 2014 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 7974995 | 0 | 7974995 | 0 | 0 | 0 | 0 | 0 | 0 | 9176004 | 0 | 9176004 | 13297104 | 2685484 | 10611620 | 8896955 | 6898550 | 1998405 | 10433516 | 7474903 | 2958613 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 7130643 | 1065839 | 6064804 | 8629524 | 1189215 | 7440309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 2420314 | 0 | 2420314 | 217894365 | 63254365 | 154640000 | 16027598 | 7964389 | 8063209 | 38634353 | 8664118 | 29970235 | 217894365 | 63254365 | 154640000 | 16027598 | 7964389 | 8063209 | 38634353 | 8664118 | 29970235 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2014 | Q4 | Q4 - 2014 | 113368574 | 20394864 | 92973710 | 4584514 | 0 | 4584514 | 16045799 | 0 | 16045799 | 0 | 0 | 0 | 0 | 0 | 0 | 5084560 | 0 | 5084560 | 13297104 | 2685484 | 10611620 | 10113670 | 6870422 | 3243248 | 13527021 | 7310466 | 6216555 | 73597901 | 37780781 | 35817120 | 4007005 | 4007005 | 0 | 14751370 | 10091803 | 4659567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 8299309 | 1044677 | 7254632 | 12459187 | 1167632 | 11291555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337769 | 0 | 1337769 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 2466789 | 0 | 2466789 | 217894365 | 63254365 | 154640000 | 27004498 | 11922104 | 15082394 | 65672495 | 18569901 | 47102594 | 217894365 | 63254365 | 154640000 | 27004498 | 11922104 | 15082394 | 65672495 | 18569901 | 47102594 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2015 | Q1 | Q1 - 2015 | 113368574 | 20394864 | 92973710 | 13108157 | 0 | 13108157 | 23933810 | 330480 | 23603330 | 0 | 0 | 0 | 0 | 0 | 0 | 8154007 | 0 | 8154007 | 13297104 | 2685484 | 10611620 | 12572795 | 7740982 | 4831813 | 18215893 | 8619687 | 9596206 | 73597901 | 37780781 | 35817120 | 4007005 | 4007005 | 0 | 4007005 | 4007005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 10638315 | 1125046 | 9513269 | 12285112 | 1205414 | 11079698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 3135738 | 0 | 3135738 | 217894365 | 63254365 | 154640000 | 40326272 | 12873033 | 27453239 | 69731565 | 14162586 | 55568979 | 217894365 | 63254365 | 154640000 | 40326272 | 12873033 | 27453239 | 69731565 | 14162586 | 55568979 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT10BIX5570158 | INF | 2015 | Q2 | Q2 - 2015 | 113368574 | 20394864 | 92973710 | 13108157 | 0 | 13108157 | 41703189 | 1917968 | 39785221 | 0 | 0 | 0 | 0 | 0 | 0 | 22375599 | 0 | 22375599 | 13297104 | 2685484 | 10611620 | 16481151 | 8311106 | 8170045 | 21638208 | 9051435 | 12586773 | 73597901 | 37780781 | 35817120 | 4007005 | 4007005 | 0 | 13924063 | 6503266 | 7420797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 11000358 | 1233965 | 9766393 | 31932812 | 1405994 | 30526818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 6318019 | 1870500 | 4447519 | 217894365 | 63254365 | 154640000 | 44596671 | 13552076 | 31044595 | 137891890 | 20749163 | 117142727 | 217894365 | 63254365 | 154640000 | 44596671 | 13552076 | 31044595 | 137891890 | 20749163 | 117142727 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority
NT11BIX5570001 | INF | 2010 | Q3 | Q3 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 0 | 0 | 0 | 252000 | 0 | 252000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 9452958 | 8918958 | 534000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 1396723 | 0 | 1396723 | 3808862 | 0 | 3808862 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 10315681 | 8918958 | 1396723 | 13421820 | 8918958 | 4502862 | 135300777 | 34665587 | 100635190 | 10315681 | 8918958 | 1396723 | 13421820 | 8918958 | 4502862 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 252000 | 0 | 252000 | 74598 | 0 | 74598 | 104598 | 0 | 104598 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 8918958 | 8918958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 5001281 | 0 | 5001281 | 11029010 | 0 | 11029010 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 13994837 | 8918958 | 5075879 | 21052566 | 8918958 | 12133608 | 135300777 | 34665587 | 100635190 | 13994837 | 8918958 | 5075879 | 21052566 | 8918958 | 12133608 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 108159 | 25000 | 83159 | 6036096 | 1025000 | 5011096 | 252000 | 0 | 252000 | 103572 | 0 | 103572 | 128572 | 0 | 128572 | 24832866 | 11912238 | 12920628 | 14814619 | 8918958 | 5895661 | 18314619 | 8918958 | 9395661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 8057626 | 0 | 8057626 | 10104689 | 0 | 10104689 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 23083976 | 8943958 | 14140018 | 34583976 | 9943958 | 24640018 | 135300777 | 34665587 | 100635190 | 23083976 | 8943958 | 14140018 | 34583976 | 9943958 | 24640018 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 20325643 | 1025000 | 19300643 | 26961543 | 1025000 | 25936543 | 252000 | 0 | 252000 | 116302 | 0 | 116302 | 141302 | 0 | 141302 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 8918958 | 8918958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 6788073 | 0 | 6788073 | 8062073 | 0 | 8062073 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 36148976 | 9943958 | 26205018 | 44083876 | 9943958 | 34139918 | 135300777 | 34665587 | 100635190 | 36148976 | 9943958 | 26205018 | 44083876 | 9943958 | 34139918 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 26481103 | 1025000 | 25456103 | 40983011 | 3025000 | 37958011 | 252000 | 0 | 252000 | 201970 | 0 | 201970 | 226970 | 0 | 226970 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 11912238 | 11912238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 7920452 | 0 | 7920452 | 9301521 | 0 | 9301521 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 43522483 | 9943958 | 33578525 | 62423740 | 14937238 | 47486502 | 135300777 | 34665587 | 100635190 | 43522483 | 9943958 | 33578525 | 62423740 | 14937238 | 47486502 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 43431785 | 1025000 | 42406785 | 65188073 | 1025000 | 64163073 | 252000 | 0 | 252000 | 304119 | 0 | 304119 | 431042 | 0 | 431042 | 24832866 | 11912238 | 12920628 | 9780342 | 8918958 | 861384 | 9980342 | 8918958 | 1061384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 8689218 | 0 | 8689218 | 10332810 | 0 | 10332810 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 62205464 | 9943958 | 52261506 | 85932267 | 9943958 | 75988309 | 135300777 | 34665587 | 100635190 | 62205464 | 9943958 | 52261506 | 85932267 | 9943958 | 75988309 | 0 | 2657 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 54294716 | 1025000 | 53269716 | 69933492 | 1025000 | 68908492 | 252000 | 0 | 252000 | 434193 | 0 | 434193 | 535100 | 0 | 535100 | 24832866 | 11912238 | 12920628 | 9965308 | 8918958 | 1046350 | 10298170 | 8918958 | 1379212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 10421167 | 0 | 10421167 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 74348921 | 9943958 | 64404963 | 91187929 | 9943958 | 81243971 | 135300777 | 34665587 | 100635190 | 74348921 | 9943958 | 64404963 | 91187929 | 9943958 | 81243971 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 56912354 | 1025000 | 55887354 | 58212354 | 1025000 | 57187354 | 252000 | 0 | 252000 | 644980 | 0 | 644980 | 844980 | 0 | 844980 | 24832866 | 11912238 | 12920628 | 9965308 | 8918958 | 1046350 | 9965308 | 8918958 | 1046350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 9654704 | 0 | 9654704 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 77177346 | 9943958 | 67233388 | 78677346 | 9943958 | 68733388 | 135300777 | 34665587 | 100635190 | 77177346 | 9943958 | 67233388 | 78677346 | 9943958 | 68733388 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 12858509 | 0 | 12858509 | 93228004 | 18066349 | 75161655 | 57282940 | 1025000 | 56257940 | 55793021 | 0 | 55793021 | 252000 | 0 | 252000 | 886335 | 0 | 886335 | 8370304 | 0 | 8370304 | 24832866 | 11912238 | 12920628 | 9365308 | 8318958 | 1046350 | 34326473 | 31937974 | 2388499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 14949507 | 600000 | 14349507 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 77189287 | 9343958 | 67845329 | 126297814 | 32537974 | 93759840 | 135300777 | 34665587 | 100635190 | 77189287 | 9343958 | 67845329 | 126297814 | 32537974 | 93759840 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2013 | Q2 | Q2 - 2013 | 18646122 | 0 | 18646122 | 14451717 | 0 | 14451717 | 14453232 | 0 | 14453232 | 53279568 | 0 | 53279568 | 50624658 | 0 | 50624658 | 53484389 | 0 | 53484389 | 9230560 | 0 | 9230560 | 7987805 | 0 | 7987805 | 8365172 | 0 | 8365172 | 36811327 | 33615587 | 3195740 | 34123919 | 31596583 | 2527336 | 36143333 | 33615587 | 2527746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 14652436 | 1050000 | 13602436 | 15157842 | 1050000 | 14107842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 121840535 | 32646583 | 89193952 | 127603968 | 34665587 | 92938381 | 135300777 | 34665587 | 100635190 | 121840535 | 32646583 | 89193952 | 127603968 | 34665587 | 92938381 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2013 | Q3 | Q3 - 2013 | 18646122 | 0 | 18646122 | 14453232 | 0 | 14453232 | 14895320 | 0 | 14895320 | 53279568 | 0 | 53279568 | 53481489 | 0 | 53481489 | 54715142 | 0 | 54715142 | 9230560 | 0 | 9230560 | 8382290 | 0 | 8382290 | 8606368 | 0 | 8606368 | 36811327 | 33615587 | 3195740 | 36143333 | 33615587 | 2527746 | 36143333 | 33615587 | 2527746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 15138417 | 1050000 | 14088417 | 16173559 | 1050000 | 15123559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 127598761 | 34665587 | 92933174 | 130533722 | 34665587 | 95868135 | 135300777 | 34665587 | 100635190 | 127598761 | 34665587 | 92933174 | 130533722 | 34665587 | 95868135 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2013 | Q4 | Q4 - 2013 | 18646122 | 0 | 18646122 | 14771083 | 0 | 14771083 | 14929635 | 0 | 14929635 | 53279568 | 0 | 53279568 | 54189469 | 0 | 54189469 | 54668941 | 0 | 54668941 | 9230560 | 0 | 9230560 | 8601886 | 0 | 8601886 | 8751886 | 0 | 8751886 | 36811327 | 33615587 | 3195740 | 36150255 | 33615587 | 2534668 | 36160255 | 33615587 | 2544668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 16051430 | 1050000 | 15001430 | 16358582 | 1050000 | 15308582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 129764123 | 34665587 | 95098536 | 130869299 | 34665587 | 96203712 | 135300777 | 34665587 | 100635190 | 129764123 | 34665587 | 95098536 | 130869299 | 34665587 | 96203712 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2014 | Q1 | Q1 - 2014 | 18646122 | 0 | 18646122 | 14929648 | 0 | 14929648 | 14929648 | 0 | 14929648 | 53279568 | 0 | 53279568 | 54300096 | 0 | 54300096 | 55608220 | 0 | 55608220 | 9230560 | 0 | 9230560 | 8706273 | 0 | 8706273 | 8886147 | 0 | 8886147 | 36811327 | 33615587 | 3195740 | 36150255 | 33615587 | 2534668 | 36195255 | 33615587 | 2579668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 16265963 | 1050000 | 15215963 | 16322212 | 1050000 | 15272212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 130352235 | 34665587 | 95686648 | 131941482 | 34665587 | 97275895 | 135300777 | 34665587 | 100635190 | 130352235 | 34665587 | 95686648 | 131941482 | 34665587 | 97275895 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2014 | Q2 | Q2 - 2014 | 18646122 | 0 | 18646122 | 14956994 | 0 | 14956994 | 15034603 | 0 | 15034603 | 53279568 | 0 | 53279568 | 54731517 | 0 | 54731517 | 56519615 | 0 | 56519615 | 9230560 | 0 | 9230560 | 8925576 | 0 | 8925576 | 9064458 | 0 | 9064458 | 36811327 | 33615587 | 3195740 | 36150255 | 33615587 | 2534668 | 36217755 | 33615587 | 2602168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 16277212 | 1050000 | 15227212 | 16302165 | 1050000 | 15252165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 131041554 | 34665587 | 96375967 | 133138596 | 34665587 | 98473009 | 135300777 | 34665587 | 100635190 | 131041554 | 34665587 | 96375967 | 133138596 | 34665587 | 98473009 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2014 | Q3 | Q3 - 2014 | 15105755 | 0 | 15105755 | 14956994 | 0 | 14956994 | 15049924 | 0 | 15049924 | 58448208 | 0 | 58448208 | 55690732 | 0 | 55690732 | 58420501 | 0 | 58420501 | 9111443 | 0 | 9111443 | 9071933 | 0 | 9071933 | 9093369 | 0 | 9093369 | 36255255 | 33615587 | 2639668 | 36203879 | 33615587 | 2588292 | 36239250 | 33615587 | 2623663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16380116 | 1050000 | 15330116 | 16311682 | 1050000 | 15261682 | 16350176 | 1050000 | 15300176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 132235220 | 34665587 | 97569633 | 135153220 | 34665587 | 100487633 | 135300777 | 34665587 | 100635190 | 132235220 | 34665587 | 97569633 | 135153220 | 34665587 | 100487633 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2014 | Q4 | Q4 - 2014 | 15051064 | 0 | 15051064 | 15046114 | 0 | 15046114 | 15046114 | 0 | 15046114 | 58530139 | 0 | 58530139 | 57575109 | 0 | 57575109 | 58108089 | 0 | 58108089 | 9117129 | 0 | 9117129 | 9087906 | 0 | 9087906 | 9114718 | 0 | 9114718 | 36250069 | 33615587 | 2634482 | 36212463 | 33615587 | 2596876 | 36232463 | 33615587 | 2616876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16352376 | 1050000 | 15302376 | 16339126 | 1050000 | 15289126 | 16359126 | 1050000 | 15309126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 134260718 | 34665587 | 99595131 | 134860510 | 34665587 | 100194923 | 135300777 | 34665587 | 100635190 | 134260718 | 34665587 | 99595131 | 134860510 | 34665587 | 100194923 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2015 | Q1 | Q1 - 2015 | 15105755 | 0 | 15105755 | 15046114 | 0 | 15046114 | 15046114 | 0 | 15046114 | 58448208 | 0 | 58448208 | 57688795 | 0 | 57688795 | 58114315 | 0 | 58114315 | 9111443 | 0 | 9111443 | 9103310 | 0 | 9103310 | 9117366 | 0 | 9117366 | 36255255 | 33615587 | 2639668 | 36212463 | 33615587 | 2596876 | 36250069 | 33615587 | 2634482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16380116 | 1050000 | 15330116 | 16339126 | 1050000 | 15289126 | 16352376 | 1050000 | 15302376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 134389808 | 34665587 | 99724221 | 134880240 | 34665587 | 100214653 | 135300777 | 34665587 | 100635190 | 134389808 | 34665587 | 99724221 | 134880240 | 34665587 | 100214653 | 0 | 0 | Eagle-Net Alliance
NT11BIX5570001 | INF | 2015 | Q2 | Q2 - 2015 | 15105755 | 0 | 15105755 | 15046114 | 0 | 15046114 | 15066114 | 0 | 15066114 | 58448208 | 0 | 58448208 | 57688796 | 0 | 57688796 | 58460568 | 0 | 58460568 | 9111443 | 0 | 9111443 | 9138724 | 0 | 9138724 | 9138724 | 0 | 9138724 | 36255255 | 33615587 | 2639668 | 36248497 | 33615587 | 2632910 | 36255255 | 33615587 | 2639668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16380116 | 1050000 | 15330116 | 16352376 | 1050000 | 15302376 | 16380116 | 1050000 | 15330116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 134474507 | 34665587 | 99808920 | 135300777 | 34665587 | 100635190 | 135300777 | 34665587 | 100635190 | 134474507 | 34665587 | 99808920 | 135300777 | 34665587 | 100635190 | 0 | 0 | Eagle-Net Alliance
NT12BIX5570001 | INF | 2012 | Q1 | Q1 - 2012 | 1113000 | 222600 | 890400 | 1042468 | 208494 | 833974 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 8285937 | 1657187 | 6628751 | 17391410 | 6998282 | 10393127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 10080 | 2016 | 8064 | 281193 | 56239 | 224954 | 898478 | 179696 | 718782 | 790226 | 158045 | 632181 | 108252 | 21651 | 86601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 48232 | 9646 | 38586 | 245996 | 49200 | 196796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 10176943 | 2035388 | 8141556 | 19139851 | 7347972 | 11791878 | 28274326 | 9174866 | 19099460 | 10176943 | 2035388 | 8141556 | 19139851 | 7347972 | 11791878 | 0 | 0 | Zayo Group, LLC
NT12BIX5570001 | INF | 2012 | Q2 | Q2 - 2012 | 1113000 | 222600 | 890400 | 1065027 | 213005 | 852022 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 12664058 | 2532812 | 10131246 | 17391410 | 6998282 | 10393127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 210288 | 42057 | 168231 | 281193 | 56239 | 224954 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 85843 | 17169 | 68674 | 245996 | 49200 | 196796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 14923694 | 2984739 | 11938955 | 19930077 | 7506017 | 12424059 | 28274326 | 9174866 | 19099460 | 14923694 | 2984739 | 11938955 | 19930077 | 7506017 | 12424059 | 0 | 0 | Zayo Group, LLC
NT12BIX5570001 | INF | 2012 | Q3 | Q3 - 2012 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 25667347 | 8655469 | 17021878 | 15085438 | 3017088 | 12068350 | 25667347 | 8655469 | 17021878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 641684 | 128336 | 513348 | 641684 | 128336 | 513348 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 158535 | 31707 | 126828 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28264326 | 9174866 | 19099460 | 17852562 | 3570512 | 14282050 | 28614737 | 9244947 | 19379790 | 28264326 | 9174866 | 19099460 | 17852562 | 3570512 | 14282050 | 28614737 | 9244947 | 19379790 | 0 | 0 | Zayo Group, LLC
NT12BIX5570001 | INF | 2012 | Q4 | Q4 - 2012 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 16449918 | 3289984 | 13159934 | 25123093 | 8544618 | 16578475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 845527 | 169106 | 676422 | 845527 | 169106 | 676421 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 201975 | 40395 | 161580 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 19464325 | 3892866 | 15571460 | 28274326 | 9174866 | 19099460 | 28274326 | 9174866 | 19099460 | 19464325 | 3892866 | 15571460 | 28274326 | 9174866 | 19099460 | 0 | 0 | Zayo Group, LLC
NT12BIX5570001 | INF | 2013 | Q1 | Q1 - 2013 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 24677347 | 8455469 | 16221878 | 17375089 | 3475018 | 13900071 | 21191793 | 7758359 | 13433434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291273 | 258255 | 1033018 | 1116859 | 223372 | 893487 | 1291273 | 258255 | 1033018 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 216625 | 43325 | 173300 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 20675478 | 4135096 | 16540382 | 24788772 | 8477756 | 16311016 | 28274326 | 9174866 | 19099460 | 20675478 | 4135096 | 16540382 | 24788772 | 8477756 | 16311016 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2012 | Q1 | Q1 - 2012 | 2647380 | 794214 | 1853166 | 179991 | 53997 | 125994 | 2467389 | 740217 | 1727172 | 15004615 | 4501385 | 10503230 | 4652353 | 1395706 | 3256647 | 10352262 | 3105679 | 7246583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 350669 | 105201 | 245468 | 253110 | 75933 | 177177 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 5205614 | 1561684 | 3643930 | 13072761 | 3921829 | 9150932 | 18278375 | 5483513 | 12794862 | 5205614 | 1561684 | 3643930 | 13072761 | 3921829 | 9150932 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2012 | Q2 | Q2 - 2012 | 2647380 | 794214 | 1853166 | 179991 | 53997 | 125994 | 2467389 | 740217 | 1727172 | 15004615 | 4501385 | 10503230 | 7009336 | 2102801 | 4906535 | 10352262 | 3105679 | 7246583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 474040 | 142212 | 331828 | 474040 | 142212 | 331828 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 7685968 | 2305790 | 5380178 | 13316292 | 3994888 | 9321404 | 18278375 | 5483513 | 12794862 | 7685968 | 2305790 | 5380178 | 13316292 | 3994888 | 9321404 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2012 | Q3 | Q3 - 2012 | 2647380 | 794214 | 1853166 | 185353 | 55606 | 129747 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 8753680 | 2626104 | 6127576 | 15004615 | 4501385 | 10503230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 568527 | 170558 | 397969 | 603779 | 181134 | 422645 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 9530161 | 2859048 | 6671113 | 18278375 | 5483513 | 12794862 | 18278375 | 5483513 | 12794862 | 9530161 | 2859048 | 6671113 | 18278375 | 5483513 | 12794862 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2012 | Q4 | Q4 - 2012 | 2647380 | 794214 | 1853166 | 192284 | 57685 | 134599 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 10609055 | 3182717 | 7426338 | 14954989 | 4486498 | 10468491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 653405 | 196021 | 457384 | 653405 | 196021 | 457384 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 11477345 | 3443203 | 8034142 | 18278375 | 5483513 | 12794862 | 18278375 | 5483513 | 12794862 | 11477345 | 3443203 | 8034142 | 18278375 | 5483513 | 12794862 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2013 | Q1 | Q1 - 2013 | 2647380 | 794214 | 1853166 | 233685 | 70105 | 163579 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 10798742 | 3239622 | 7559119 | 13851615 | 4155484 | 9696131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 755956 | 226787 | 529169 | 755956 | 226787 | 529169 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 11810984 | 3543294 | 8267688 | 17277552 | 5183265 | 12094287 | 18278375 | 5483513 | 12794862 | 11810984 | 3543294 | 8267688 | 17277552 | 5183265 | 12094287 | 0 | 0 | Zayo Group, LLC
NT12BIX5570002 | INF | 2013 | Q2 | Q2 - 2013 | 2647380 | 794214 | 1853166 | 354562 | 106369 | 248193 | 354562 | 106369 | 248193 | 15004615 | 4501385 | 10503230 | 14750659 | 4425198 | 10325461 | 14750659 | 4425198 | 10325461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626380 | 187914 | 438466 | 977778 | 293333 | 684445 | 977778 | 293333 | 684445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 16082999 | 4824900 | 11258099 | 16082999 | 4824900 | 11258099 | 18278375 | 5483513 | 12794862 | 16082999 | 4824900 | 11258099 | 16082999 | 4824900 | 11258099 | 0 | 0 | Zayo Group, LLC

## CCI_Annual_KeyIndicators_Actual
Award_Num | Year | MMile_AvgCost | MMile_AvgCost_Desc | LMileHous_AvgCost | LMileHous_AvgCost_Desc | LMileSubsc_AvgCost | LMileSubsc_AvgCost_Desc | MMile_MaxSpeed | MMile_MaxSpeed_Desc | LMile_MaxSpeed | LMile_MaxSpeed_Desc | MMile_AvgSpeed | MMile_AvgSpeed_Desc | LMile_AvgSpeed | LMile_AvgSpeed_Desc | SpeedIncrease_Desc | RetService_Desc | NetManagemnt_Desc | DiscontReason_Desc | TotalStrand_Num | AvgActStrand_Num | AvgLeaseStrand_Num | AvgDarkStrand_Num | BuildActStrand_Num | BuildLeaseStrand_Num | BuildDarkStrand_Num | WSaleCustList_Desc | SqFeet_Total_Num | SqFeet_Use_Num | SqFeet_Lease_Num | SqFeet_Availbl_Num | NetConnect_Desc | SubcontrConcern_Desc | BestPractice_Desc | Recipient | School_Total_Num | Library_Total_Num | CCollege_Total_Num | Universt_Total_Num | Healthcr_Total_Num | PublSafety_Total_Num | OtherGov_Total_Num | OtherGov_Improv_Num | OtherNonGov_Total_Num | PublHousng_Total_Num | TotalComInst_Num | InterAgreement_Name | PeerAgreemnt_Name
NT10BIX5570003 | 2010 | 28,285 | This number is slightly higher than our Baseline projection based on the limited construction completed for the project. As miles are added we anticipate this number to fall in line with our projections. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 47.5 Meg | With only two Anchor Institutions connected at this time, this number is skewed higher than normal due to one subscriber requesting an atypical speed. | N/A | N/A | Since SDN was not the provider of service to these institutions prior to this award, we are not able to provide the data requested. | N/A | (a.) Network management policies are currently being developed as part of the overall project design and implementation as we roll out the enhanced broadband infrastructure to our customers. (b.) No, we have not blocked or limited consumers to our network. | N/A | 12576 | 432 | 0 | 3024 | 1140 | 0 | 7980 | N/A | 0 | 0 | 0 | 0 | Interconnection can be accomplished at any meetpoint where SDN connects to other carriers throughout the network. Interconnection can be requested by contacting our sales staff at SDN Communications, 2910 West 10th Street, Sioux Falls, South Dakota 57104 or by visiting our website at: www.sdncommunications.com. | N/A | Maintain regularly scheduled contact with the Federal Program Officer and make sure they are aware of everything you are doing. | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | N/A None No | N/A
NT10BIX5570003 | 2011 | 23,644 | Original Baseline projections were projected to be at $22,000 for the project. The average cost per mile using the Middle Cost to Build divided by the miles. This calculation is consistent with Baseline calculations. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 28 Mbps | This metric was calculated using the new facilities added during the 2011 year. | N/A | N/A | 44 Mbps increase as it was calculated using total bandwidth ordered minus previous, divided by total site count. | N/A | a.) Network Management Policies are in place and posted on the SDN Website, sdncommunications.com. b.) No | N/A | 16992 | 4410 | 0 | 11658 | 308 | 0 | 616 | N/A | 0 | 0 | 0 | 0 | Points of Presence (PoP's) are available and identified on the attached addendum. | N/A | N/A | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | 1). None 2). None 3). No | N/A
NT10BIX5570003 | 2012 | $23,644 | Original Baseline projections were projected to be at $22,000 for the project. The average cost per mile using the Middle Cost to Build divided by the miles. This calculation is consistent with Baseline calculations. This metric was consistent with 2011 as the Middle Mile component was completed during that year. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 44Mbps. | This metric was calculated using the new facilities added during the 2012 year. | N/A | N/A | 44 Mbps increase as it was calculated using total bandwidth ordered minus previous, divided by total site count. | N/A | a.) Network Management Policies are in place and posted on the SDN Website, sdncommunications.com. b.) No | N/A | 17440 | 5096 | 0 | 12344 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Points of Presence (PoP's) are available and identified on the attached addendum. | N/A | N/A | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | 1.) None 2.) None 3.) No | N/A
NT10BIX5570004 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Physical locations for collocation points have been determined, however the collocation facilities and specifications have not been finalized due to waiting on Environmental Assessment approval. | N/A | Environmental Assessments regulations and requirements vary with different agencies. We recommend that other BTOP projects fully research what is required prior to contracting with an Environmental firm. | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A
NT10BIX5570004 | 2011 | 13,690.00 | Southern Route construction is not yet complete. This cost for this build will be higher than the average cost shown. | N/A | As of 12/31/2011, no last mile connections have been made. | N/A | As of 12/31/2011, no last mile connections have been made. | 10 Gb | Meets Baseline | 100 Mb | Meets Baseline | 10 Gb | Meets Baseline | 15 Mb | Based on pre-market take rates the average speed will be 15Mb | N/A | N/A | N/A | N/A | 28190 | 0 | 0 | 24313 | 758 | 0 | 3119 | N/A | 0 | 0 | 0 | 0 | CPOP and SPOP construction will be completed in January of 2012 at that point collocation facilities will be offered. | N/A | N/A | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A
NT10BIX5570004 | 2012 | 16,856 | Meets Baseline | 662 | Meets Baseline | 7,918 | Meets Baseline | 10 Gb | Meets Baseline | 100 Mb | Meets Baseline | 10 Gb | Meets Baseline | 15 Mb | Based on market take rates the average speed will be 15-20Mb | NGN has compared information from CAIs. The average before the BTOP project was 3 Mb with no ability for expansion. Currently, our average current CAIs package is around 15 Mb. The BTOP program has given the CAIs the ability to increase this bandwidth to 1000Mb (1Gb) if interested. | Broadband Services. We deliver internet bits to premises. | Currently all of our data traffic is internet bits that do not require quality of service. We do not filter internet content or services. We currently sell internet packages. These packages define bandwidth rates controlled at the endpoint. | N/A | 54584 | 23499 | 896 | 30189 | 0 | 0 | 0 | N/A | 864 | 576 | 0 | 288 | CPOP and SPOP facilities can be offered as collocation facilities. | N/A | N/A | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A
NT10BIX5570009 | 2010 | 0 | None Noted | 0 | N/A | 0 | N/A | 10 Gbps | None Noted | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | a) CAI's can request their bandwidth limited but by default Merit does not limit the users access. b) Merit has not block access to any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 73630 | 0 | 0 | 1080 | 17897 | 5221 | 49432 | N/A | 0 | 0 | 0 | 0 | Merit does not own collocation space for this build. Other network providers and CAI's can interconnect to Merit at splice points along the route. | N/A | Merit encourages all BTOP recipients to reach out to communities at all levels and get them involved in the process. Build relationships with all the permitting agencies; we would suggest informal meetings with them on a regular basis. Merit would encourage that inquiries with communities on existing infrastructure as well as talking with others in your industry about existing infrastructure given that the cost is about the same or less and the time savings will get you ahead of your project. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | N/A | N/A
NT10BIX5570009 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 0 | N/A | 0 | N/A | Broadband speeds have not increased since construction and deployment have not been completed. | Pricing plans have not been provided, since construction and deployment have not been completed. | Our project is not yet providing service. | N/A | 72821 | 0 | 0 | 6552 | 17715 | 5221 | 43333 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers will have opportunities to connect to the recipient and subrecipient networks at leased facilities along the route, including, but not limited to: telecommunication huts; Central Offices; Community Anchor Institutions; and other leased facilities. No part of the project network was lit and operational during the reporting period; the locations, owners, and interconnection method data will be available in the 2012 reporting year. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | 1. N/A 2. N/A 3. N/A (No requests for interconnection were made.) | 1. N/A 2. N/A 3. N/A (No requests for peering or transit were made.)
NT10BIX5570009 | 2012 | 33461 | No significant variance. | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 10 Mbps | No variance. | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 81789 | 3863 | 74686 | 0 | 180 | 0 | 3060 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | N/A | N/A
NT10BIX5570009 | 2013 | 34734 | The variance, 2%, is not significant, but could be attributed to unanticipated expenses associated with the Environmental Assessment and higher than expected permitting costs. | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 10 Mbps | No variance. | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 81789 | 4043 | 74686 | 3060 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | There were no interconnection agreements entered into during the annual reporting period, however one agreement was under negotiation. No requests were denied. | N/A
NT10BIX5570011 | 2010 | $0 | No fiber yet deployed, although at end of quarter conduit placement had occurred. | N/A | N/A to our project. | N/A | N/A to our project. | N/A | No fiber yet deployed. | N/A | N/A to our project. | N/A | No fiber yet deployed | N/A | N/A to our project. | No CAI's were explicitly called out for direct service as a part of this project. As of 12/31/2010, no network components had been deployed as part of this project. | N/A | MCNC has Internet/Data Acceptable Use, Nondiscrimination, Interconnection, and Network Management Policies (see https://www.mcnc.org/about/policies.html for further details). MCNC does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to it's existing infrastructure or on proposed BTOP infrastructure. | N/A | 46274 | 0 | 0 | 2642 | 0 | 0 | 43632 | N/A | 0 | 0 | 0 | 0 | Although we have not yet deployed, access to other network providers will be allowed at all hand holds deployed within the network and all carrier neutral facilities we end up colocating in. . | While our next tier contractors are not SDB, each are including a SDB component via their subcontractors. | Get your RFP's out as quickly as you can. With folks desperate for work and orders, you might end up with more favorable pricing. Continue to work with incumbents in your area as new opportunities for partnerships arise. Realize that every day will present a new challenge and opportunity, but to keep the big picture in focus. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | MCNC has a Definitive Agreement with FRC which provides for IRUs (exclusive, unrestricted and indefeasible right to use the fibers associated with the IRUs) - such IRU grant does not convey any legal title to any real or personal property, including the fibers, the cable or the network; however, the Grantee shall have the exclusive, unrestricted and indefeasible right to use the fibers associated with the IRU for any lawful purpose during the term applicable to such IRU. -FRC will be getting IRUs in New MCNC Fiber Segments -MCNC will be getting IRUs in Existing FRC Fiber Segments For ERC we have a Fiber Optics Exchange Agreement The agreement defines IRU as an indefeasible right to use a designated number of fiber strands within the other party's cable -ERC will be getting an exclusive and unrestricted IRU from MCNC -MCNC will be getting an exclusive and unrestricted IRU from ERC | N/A
NT10BIX5570011 | 2011 | 61,704.50 | New miles built and fully deployed stand at 105. Total cost of engineering, construction, and relevant permits to light those segments that are in service is $6,478,973. We are less than what was forecasted in our baseline due to lower than expected construction costs. As we deploy more miles in the areas that were cheaper, this number will continue to drop. While we had forecasted more miles to be completed at this point, they are not yet operated (i.e. equipment deployed). Even were they deployed, the cost per mile would be lower as our expenses have turned out to be lower on those segments as well. | 0 | N/A to our project | 0 | N/A to our project | 10Gbps | 10Gbps is the maximum current speed realized on our network, however the equipment deployed has the ability to scale to 100G as user needs would dictate. | 0 | N/A to our project | 1.9Gbps | Four 10Gbps services have been provisioned on the MCNC portions of the network, and 17 50Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | All of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at a minimum of 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. | FRC has used 2 fiber pairs (4 fiber strands) in Asheville, NC to provide ethernet based services to Verizon Wireless at approximately 17 cell tower locations. FRC charges Verizon Wireless approximately $1,400 per month at each tower location. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A as no subscribers have dropped the service. | 46562 | 998 | 246 | 39942 | 616 | 0 | 4760 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure and with Haywood County Government for use of 6 fibers over 1 mile of the infrastructure yielding the 246 miles referenced above. | 0 | 0 | 0 | 0 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, we also had the route designed and built to allow for interconnection at all hand holes that exist along the route and have the ability to have fiber splicing occur. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with seven SDB concerns: Indepth Utility Resources, LLC - WBE applied for T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE applied for Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy stuff, let the remainder, and our prime contractor has had difficulty finding someone to complete the segment they were awarded. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | We have finalized two agreements with FRC and ERC related to fibers built with BTOP awards. These were agreements that were outlined in our project application and represent new access for both in these regions. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure.
NT10BIX5570011 | 2012 | 64,615.28 | New miles built and deployed is 444. Total cost of engineering, construction, and relevant permits for this fiber is $28,689,184. We are less than what was forecasted in our baseline due to lower than expected construction costs. | 0 | N/A to our project | 0 | N/A to our project | 10Gbps | 10Gbps is the maximum current speed realized on our network for CAI connections, however the equipment deployed has the ability to scale to 100G as user needs would dictate. In addition we have deployed 100G core upgrades for the North Carolina Research and Education (NCREN) backbone as approved by NTIA this past year. | 0 | N/A to our project | 4.2Gbps | 12 10Gbps services have been provisioned on the MCNC portions of the network, and 17 50Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | 1847 of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. 19 CAI's have now had direct fiber built to them as a result of the project with minimum connectivity of 1Gbps scalable to 100Gbps in the future now that fiber as been deployed. | FRC is providing point to point services for cell towers in the western portion of the network for Verizon wireless. They have not yet had demand for other wholesale lit services related to these areas. Their marketing strategy enables them to provide services from 50M-10Gbps as required by customers. Each opportunity has to be priced on a case by case basis to offset additional capital costs (additional lateral builds and equipment) that were not funded by the BTOP program specifically. For the existing services they're providing to Verizon wireless, they are charging $1400/mo for 50M backhaul services from their towers to other locations off the BTOP route. MCNC is not providing wholesale services to carriers per our mission. We are providing transport, lambda, and internet services on the network for CAI's in these regions. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a content based filtering service that our K-12 community can subscribe to to meet CIPA (Children's Internet Protection Act) requirements that the districts may have, as well as firewall based service. MCNC does not limit access to any lawful content. | N/A - as no subscribers have dropped the service. | 49676 | 2564 | 366 | 46746 | 0 | 0 | 0 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure, Haywood County Government for use of 6 fibers over 1 mile of the infrastructure, Pangea for 6 fibers over 7.6 miles of the infrastructure, and Morris Broadband for 2 fibers over 37.2 miles of the infrastructure yielding the 366 miles referenced above. | 0 | 0 | 0 | 0 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, hand holds along the route, placed at a minimum of 1 mile apart, allow for interconnect to other carriers or CAI's that would build fiber to those meet points. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with nine SDB concerns: Indepth Utility Resources, LLC - WBE T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE Edwards Telecommunication, Inc VBE HK&L, LLC WBE applied for | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. 1) Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy construction, left the remainder and our prime contractor had difficulty finding someone to complete the segment they were awarded. 2) Award RFP's early. 3) Implement stringent contracts for material delivery and construction delivery. 4) Expect your legal bills to be more than you anticipated. 5) Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | FRC finalized two agreements with Pangea and Morris Broadband related to fibers built with BTOP awards. MCNC executed agreements with FRC and ERC related to fibers in the project. There are an additional five agreements being considered and discussed that are various stages of completeness as of writing of this report. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure.
NT10BIX5570011 | 2013 | 65,440.23 | New miles built and deployed is 444. Total cost of engineering, construction, and relevant permits for this fiber is $29,055,463. We are less than what was forecasted in our baseline due to lower than expected construction costs. | 0 | N/A to our project | 0 | N/A to our project | 100Gbps | 10Gbps is the maximum current speed realized on our network for CAI connections, however the equipment deployed has the ability to scale to 100G as user needs would dictate. In addition we have deployed 100G core upgrades for the North Carolina Research and Education (NCREN) backbone as approved by NTIA this past year. | 0 | N/A to our project | 5Gbps | This project focused on middle mile access and backbone services were the focus until directly connected CAI's were funded through savings. As a result of all work, thirty-six 10Gbps backbone services and 19 100M customer connections have been provisioned on the MCNC portions of the network and 17 100Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | 1847 of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. 19 CAI's have now had direct fiber built to them as a result of the project with minimum connectivity of 100Mbps scalable to 100Gbps in the future now that fiber as been deployed. | FRC is providing point to point services for cell towers along the footprint of the network for Verizon wireless. They have not yet had demand for other wholesale lit services related to these areas. Their marketing strategy enables them to provide services from 50M-10Gbps as required by customers. Each opportunity has to be priced on a case by case basis to offset additional capital costs (additional lateral builds and equipment) that were not funded by the BTOP program specifically. For the existing services they're providing to Verizon wireless, they are charging $1400/mo for 50M backhaul services from their towers to other locations off the BTOP route. Earthlink has bought fibers along the footprint from MCNC and is providing lit services up to 100G to customers they serve. MCNC is not providing wholesale services to carriers per our mission. We are providing transport, lambda, and internet services on the network for CAI's in these regions. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a content based filtering service that our K-12 community can subscribe to to meet CIPA (Children's Internet Protection Act) requirements that the districts may have, as well as firewall based service. MCNC does not limit access to any lawful content. | N/A - as no subscribers have dropped the service. | 49676 | 2610 | 5258 | 41808 | 0 | 0 | 0 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure, a separate agreement with ERC for the lease of 4 fibers over 31 miles of the infrastructure, Pangea for 6 fibers over 7.6 miles of the infrastructure, Morris Broadband for 2 fibers over 37.2 miles of the infrastructure, Earthlink for 2 fibers over 186 miles of the infrastructure, Broadplex for 1 fiber over 502 miles of the infrastructure, RST for 6 fibers over 472 miles of the infrastructure, and MOX networks for 12 fibers over 89 miles of the infrastructure yielding the 5258 miles referenced above. | 600 | 96 | 0 | 504 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, hand holds along the route, placed at a minimum of 1 mile apart, allow for interconnect to other carriers or CAI's that would build fiber to those meet points. In addition we built three colocation facilities in this reporting period that were included as part of the project at the end of 2012 with a portion of the original project savings that yields the figures in the tables above. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with nine SDB concerns: Indepth Utility Resources, LLC - WBE T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE Edwards Telecommunication, Inc VBE HK&L, LLC WBE applied for | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. 1) Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy construction, left the remainder and our prime contractor had difficulty finding someone to complete the segment they were awarded. 2) Award RFP's early. 3) Implement stringent contracts for material delivery and construction delivery. 4) Expect your legal bills to be more than you anticipated. 5) Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | FRC has executed agreements with Pangea and Morris Broadband related to fibers built with BTOP awards. MCNC has executed agreements with FRC, Broadplex, RST Communications, Earthlink, MOX networks and ERC related to fibers in the project. There are an additional four agreements being considered and discussed that are at various stages of completeness as of writing of this report. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure.
NT10BIX5570016 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide 3 interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1- Start the Environmental Assessment process as early as possible for long, linear projects. 2- Perform design work in advance to aid in preparation of EA and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | N/A | N/A
NT10BIX5570016 | 2011 | 17,778.74 | Average cost is less than Baseline due to both 1) lower-than-anticipated bid prices, and 2) being based on 82% complete (86 miles) | 0 | N/A | 0 | N/A | 10 Gbps | N/A | 0 | N/A | 100 mbps | N/A | 0 | N/A | 0 | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in Â¼ rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. . Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 14894 | 26 | 0 | 1846 | 436 | 0 | 12586 | N/A | 0 | 0 | 0 | 0 | Co-location point is with PemTel, located in Newport, VA. Two new interconnection points are built in New Castle, VA, and Bonsack, VA (Eastpark Business Park) | N/A | 1. Start the Environmental Assessment process as early as possible for long, linear projects 2. Perform design work in advance to aid in preparation of EA and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1. Entered into 1 agreement (PemTel) 2. Negotiating 1 interconnection agreement (TDS) 3. Have not denied any requests for interconnection. | N/A
NT10BIX5570016 | 2012 | 46115 | Average cost less than baseline due to lower than expected bid prices, and baseline estimate included all grant costs | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 105 mbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | Broadband speed has not increased. | [REDACTED] | We provide an open-access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 15004 | 585 | 29 | 14146 | 3 | 0 | 241 | N/A | 480 | 240 | 15 | 225 | One (1) co-location point is with Pemtel, located in Newport, VA. Our lease space is 36 square feet. | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1) Entered into four (4) agreements: Pemtel (1), Lumos (3) 2) Negotiating two (2) interconnection agreements (TDS, Citizens Telephone) 3) Have not denied any requests for interconnection | N/A
NT10BIX5570016 | 2013 | 33695 | Average cost is less than baseline because of lower than expected bid prices and baseline estimate included in all grant costs. | 0 | N/A | 0 | N/A | 10Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 105 mbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | Broadband speed was not increased. | MBC provides optical transport services, using SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STS's for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments are 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case by case bysis. See attachment for pricing sheet. | We provide an open-access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 15004 | 585 | 29 | 14390 | 0 | 0 | 0 | Carilion - 28 Bonsack - 464 | 720 | 360 | 30 | 330 | One (1) co-location point is with Pemtel, located in Newport, VA. Our lease space is 36 square feet. | N/A | 1. Start the environment assessment process as early as possible for long, linear projects. 2. Do the SHPO assess for both aerial and buried construction methods. 3. Perform design work in advance to aid in preparation of Environment Assessment and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1) Entered int five (5) agreements: Pemtel (1); Lumos (3); Citizens (1) 2) Negotiating two (2) interconnection agreements (TDS, Comcast) 3) Have note denied any requests for interconnection | N/A
NT10BIX5570017 | 2010 | 0 | N/A at this point in the project | 0 | N/A | 0 | N/A | 0 | N/A at this point in the project | 0 | N/A | 0 | N/A at this point in the project | 0 | N/A | N/A | N/A, no services have been provided at this point in the project | N/A, no services have been provided at this point in the project | N/A, no services have been provided at this point in the project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A, there is no plan to lease dark fiber. | 0 | 0 | 0 | 0 | The Commonwealth of PA will provide a telecommunications pad and cabinet within the tower compound for both last mile providers and long distance carriers to interconnect with the middle mile broadband network at the 68 backbone locations. In most cases, the switching equipment will be located within our shelter, and we will run a fiber jumper between the shelter and the interconnect cabinet. We will not allow collocation within our shelters for security reasons. | N/A. No subcontracts or sub grants have been made. | With any construction project, there is the inherent risk of delays due to weather. It is prudent to plan for them ahead of time so that you can minimize the impact upon the project should the worst case happen, because chances are good that it will. Also, know that your Federal Program Officer (FPO) is there to ensure that your project is completed successfully and on time. Make sure you communicate with him or her along the way and document everything. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A | N/A
NT10BIX5570017 | 2011 | n/a | The miles that have been upgraded as part of this project are not considered to be "new" miles. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 0 | No speeds have been advertised to date, due to ongoing construction of the network; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. | n/a | This is a middle mile project. | 0 | No services have been provided to date; however, our baseline estimates that the average broadband speed will be 20 Mbps. | n/a | This is a middle mile project. | N/A. No services have been provided to Community Anchor Institutions at this point. | N/A. No services have been provided at this point. | N/A. No services have been provided at this point due to the ongoing construction of the network; however, the network management policies that we plan to implement are as follows. Our standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. We anticipate that the agreement will include access to the tower site compound but not tower space or access to the Commonwealth's shelter. | N/A. No services have been provided at this point. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. There is no plan to lease dark fiber as part of this project. | 2700 | 2700 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment will be located within our shelters; however, we will run a fiber jumper between the shelter and an interconnect cabinet within the compound. We will not allow collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practice/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we bring our vendors and staff together for a group discussion. During these face to face meetings, we dissect each area of the project and discuss any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. Additionally, we have found that having both GIS software as well as professionals trained to use it has proven to be invaluable for many aspects of the project. Our GIS folks have assisted with route change research as well as providing information necessary for the completion of our performance reports. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A. No interconnection agreements have been signed to date; however, we are currently in negotiations with a last mile service provider as well as a community anchor institution with multiple locations in our project footprint. We have not denied any requests for service in 2011. | N/A. No peering or transit agreements have been signed to date. Additionally, we have not denied any requests for service in 2011.
NT10BIX5570017 | 2012 | n/a | The miles that have been upgraded as part of this project are not considered to be "new" miles. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 0 | No speeds have been advertised to date; however, we have connected to two last mile service providers in order to test the network. The maximum speed that these customers are receiving as part of the test, is 10 Mbps. The "Maximum broadband speed advertised metric" noted in our baseline report was 50Mbps; however, as our project reached the stage of connecting customers to the network, we found that most of the project footprint was not necessarily in need of faster broadband, they instead were in need of reliable service at reasonable pricing. With that in mind, advertising faster speeds is not necessarily a driving force in generating demand. | n/a | This is a middle mile project. | 10 | While we are still negotiating an agreement with three last mile service providers, we have actually connected to two of them in order to test the network. The maximum speed that these customers are currently receiving is 10 Mbps. This "average speed provided" metric differs from our baseline report which noted that we would provide an average of 20 Mbps. This variance can be explained in that the customers we are in the process of negotiating contracts with to date, have requested less bandwidth than we had predicted when the baseline report was created. As additional customers are added to the network, the "average speed provided" is expected to change and more closely align with our baseline. | n/a | This is a middle mile project. | N/A. No services have been provided to Community Anchor Institutions at this point; however, we are in negotiations with multiple government facilities (state and local) as well as multiple public safety entities that we intend to connect in the 2013 calendar year. | N/A. No services have been provided at this point. | No services have been provided at this point due to the completion of switching equipment upgrades occurring in mid December of 2012; however, the network management policies that we plan to implement are as follows. Our standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. We anticipate that the agreements will also include access to the tower site compound but not tower space or access to the Commonwealth's shelter. We intend to have customers connect to the network through an elevated platform structure where their own secure cabinet can be placed and cabling be routed through existing conduit into our equipment shelter. | N/A. Only the testing of services has occurred to date as we continue to finalize agreements with our first two last mile service providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. There is no plan to lease dark fiber as part of this project. | 2700 | 2700 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment will be located within our shelters; however, we will run a fiber jumper between the shelter and an interconnect cabinet within the compound. This interconnect cabinet will be mounted to an elevated platform where our last mile providers may add their own secure cabinet and connect to our network. The construction of the platforms is nearing completion as of the writing of this report; however, since they are not complete, they have not been included in the collocation information above. We will not allow collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practice/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we bring our vendors and staff together for a group discussion. During these face to face meetings, we dissect each area of the project and discuss any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A. No interconnection agreements have been signed to date; however, we are currently in negotiations with three last mile service providers as well as a few community anchor institutions each with multiple locations in our project footprint. We have not denied any requests for service in 2012. | N/A. No peering or transit agreements have been signed to date. Additionally, we have not denied any requests for service in 2012.
NT10BIX5570017 | 2013 | N/A | The miles of network that have been upgraded as part of this project are not considered to be "new" miles. | N/A | This is a middle mile project. | N/A | This is a middle mile project. | 0 | No broadband speeds were advertised; however, the baseline report that was submitted at the start of this project noted that we would advertise speeds of 50 Mbps. As the project began the process of connecting customers to the network, it was realized that most customers in the northern tier were not interested in speeds over 10 Mbps. Reliable service at reasonable pricing was the driving factor in making connections for our project. | N/A | This is a middle mile project. | 10 | Most of the customers that have connected to the network are receiving speeds of 10 Mbps; however, we do have four Community Anchor Institutions receiving speeds of 40 Mbps. Our baseline report noted that we would provide an average of 20 Mbps; however, most of the customers that actually connected to the network were more interested in reliable service than they were in speeds over 10 Mbps. | N/A | This is a middle mile project. | The lowest speed increase is zero (same speed, just a more reliable connection) and the highest increase is 567% where a T1 line was replaced by a 10MB wireless connection. The CAI-wide average increase in broadband speed is 242%. This figure wad derived by subtracting new speed from old speed for each CAI yielding a delta percent; averaging all of these, then, provides the overall average of 242%. | N/A. No retail services have been provided as part of this project. Only wholesale services were sold in order to remain in compliance with the Pennsylvania Utility Commission's requirements. | Our standard features include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price includes burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. The agreements include access to the tower site compound but not tower space or access to the Commonwealth's shelter. Our customers connect to the network through an elevated platform structure where their own secure cabinet can be placed and cabling be routed through existing conduit into our equipment shelter. | N/A. No subscribers have dropped the services provided through this project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. No dark fiber was leased as part of this project. | 5436 | 2830 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment has been located within our shelters with a fiber jumper between the shelter and an interconnect cabinet within the compound. This interconnect cabinet has been mounted to an elevated platform where our last mile providers have added their own secure cabinet and connected to our network. We have not allowed collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practices/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we brought our vendors and staff together for a group discussion. During these face to face meetings, we dissected each area of the project and discussed any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | We have signed agreements with two last mile service providers within the northern tier of Pennsylvania. Through these providers, we were able to provide service to 47 Community Anchor Institutions (CAIs) requiring reliable, low cost high speed internet. Of these CAIs, two are receiving new service while the others are receiving improved services. The last mile service providers that we have connected to are KCNet of Lock Haven, Pennsylvania and North Central Pennsylvania Regional Planning and Development Commission of Ridgway, Pennsylvania. No requests for interconnection were denied. | N/A. No peering or transit agreements have been signed. Additionally, no requests for service were denied.
NT10BIX5570018 | 2010 | 0 | We have yet to deploy services. However, total project expenditures to date were $27,061,970 for 3901 miles, for an average cost per new mile of $6,937.19 | 0 | N/A | 0 | N/A | 0 | We have yet to activate services. However, we plan to offer transit speeds up to 1Gbps to last mile providers. | 0 | N/A | 0 | Currently there are no interconnected networks utilizing the services. | 0 | N/A | As of 12/31/2010, we are still testing the PR-FL facilities and have not officially activated services. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Network management policies regarding the new transit & peering services for service providers are still in development as we are still in testing and are finalizing the network architecture & design, which must be completed first. 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 0 | 15604 | 0 | 0 | 0 | 0 | N/A | 8000 | 150 | 4602 | 1117 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, Fire Control Corporation, JAS Corporation, International Hardware Inc. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. And, if you have any doubts, always ask. - Ensure all SAC requirements, including BAA, Davis Bacon, are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start all required reporting early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Hire early. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | As of 12/31/2010, PRBI has not activated services. Five contracts have been signed with last mile providers. We anticipate activating services for some of these signed contracts in the next quarter. Some of the providers are in the process of constructing the middle mile to the PRBI interconnection point, which will delay the activation of services until that is completed. We are working with 12 potential interconnection clients. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. We have not denied any request for interconnection. | N/A
NT10BIX5570018 | 2011 | 7705.21 | Total project expenditures as of 12/31/2011 were $30,058,030. Total miles completed as of 12/31/2011: 3901. Expenditures include costs for future mile deployment. | 0 | N/A | 0 | N/A | 1Gbps | We offer transit speed up to 1Gbps for last mile providres. | 0 | N/A | 258Mbps | As of 12/31/2011, there are 8 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for laterals or last mile connectivity to CAI's. In Q1 2012, interconnected providers will report on how many CAIs each of their networks serve and we will provide this data to the NTIA in our next quarterly reporting. Additionally, Critical Hub is working directly with the Dept of Education to provide local peering with 1,473 schools at their main facilities. Peering interconnection will be via a 1Gbps port. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 0 | 15604 | 0 | 0 | 0 | 0 | N/A | 8000 | 150 | 4602 | 2131 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, Fire Control Corporation, JAS Corporation, International Hardware, Than Inc. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. And, if you have any doubts, always ask. - Ensure all SAC requirements, including BAA, Davis Bacon, are properly included in procurement documents such as PO's, RFP/ RFQ, and any contractor agreements. - Start all required reporting early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Hire early. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | As of 12/31/2011, PRBI has signed interconnection agreements with twelve (12) last mile service providers. Eight (8) of those agreements have already established interconnection. The other four (4) pending networks are in the process of constructing/preparing their last mile to the PRBI interconnection site or are pending the completion of the terrestrial middle-mile network spans to their desired interconnection point. We are continuing to negotiate with eight (8) last mile providers. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. We have not denied any request for interconnection. | N/A
NT10BIX5570018 | 2012 | 6948.40 | Calculation based on costs associated with middle miles completed as of 12/31/2012: 4,096. | 0 | N/A | 0 | N/A | 10 Gbps | We offer middle mile transit and peering at up to 10Gbps for last mile providers | 0 | N/A | 836.78 Mbps | As of 12/31/2012, there were 14 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for laterals or last mile connectivity to CAI's. Critical Hub is working directly with the Dept of Education to provide local peering with 1,473 schools at their main facilities. Peering interconnection will be via a 1Gbps port. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 15604 | 0 | 0 | 0 | 0 | 0 | N/A | 8000 | 1267 | 4620 | 2113 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, EOA Telecom, Fire Control Corporation, JAS Corporation, International Hardware, JD Interiors, Sanchez Technical, TecnolAir, Teknical Telekom, VersaTech. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. We prepare a memo for each call to summarize project status, ongoing challenges, other pending issues. - Ensure all SAC requirements, including BAA, Davis Bacon, Disbarment, etc are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start reporting preparations early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | In 2012, PRBI has signed interconnection agreements with five (5) last mile service providers. We are continuing to negotiate interconnection agreements with seven (7) last mile providers. We have not denied any requests for interconnectivity. | N/A
NT10BIX5570018 | 2013 | 7014.10 | Calculation based on costs associated with middle miles completed as of 9/30/2013: 4,119 | 0 | N/A | 0 | N/A | 10 Gbps | We offer middle mile transit and peering at up to 10Gbps for last mile providers | 0 | N/A | 1122.5 Mbps | As of 9/30/2013, there were 14 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data which we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for last mile connectivity to CAI's. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15692 | 15626 | 0 | 0 | 0 | 0 | 0 | N/A | 8000 | 1267 | 4620 | 2113 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, EOA Telecom, Fire Control Corporation, JAS Corporation, International Hardware, JD Interiors, Sanchez Technical, TecnolAir, Teknical Telekom, VersaTech. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. We prepare a memo for each call to summarize project status, ongoing challenges, other pending issues. - Ensure all SAC requirements, including BAA, Davis Bacon, Disbarment, etc are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start reporting preparations early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | No new interconnection agreements were entered into for the period January 1, 2013 to September 30, 2013. In total, PRBI has entered into 17 interconnection agreements. We are currently negotiating interconnection with seven (7) last mile providers. We have not denied any requests for interconnectivity. | N/A
NT10BIX5570019 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS-100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1- Start the Environmental Assessment (EA) process as early as possible for long, linear projects. 2- Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | N/A | N/A
NT10BIX5570019 | 2011 | 21505 | Complete 338 miles or 80% of total miles | 0 | N/A | 0 | N/A | 0 | 10mbps - 100mbps - Open Access | 0 | N/A | 82 mpbs | 10mbps - 100mbps - Open Access | 0 | N/A | Most schools (CAIs) requested 100 mbps services | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | None | 29413 | 200 | 0 | 2200 | 160 | 0 | 26853 | N/A | 0 | 0 | 0 | 0 | We provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1. Start the Environmental Assessment (EA) process as early as possible for long, linear projects. 2. Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1. Entered into 18 interconnection agreements 2. Currently negotiating 2 interconnection agreements. 3. Have not denied any request for interconnection, peering or transit agreements. | N/A
NT10BIX5570019 | 2012 | $31,374 | Average cost less than Baseline due to lower than expected bid prices and only 88% of construction is complete | 0 | N/A | 0 | N/A | 10 Gbps | 10 mpbs - 100 mbps - Open Access | 0 | N/A | 59 | 10 mpbs - 100 mbps - Open Access | 0 | N/A | Most schools (CAI's) request either 50 mbps or 100 mbps services. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 28969 | 278 | 0 | 28111 | 137 | 0 | 443 | N/A | 1440 | 720 | 0 | 720 | N/A | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1) Entered into 49 agreements 2) Negotiating 1 agreement (Virginia State University) 3) Have not denied any requests for interconnection. | N/A
NT10BIX5570019 | 2013 | 29430 | Average cost less than Baseline due to lower than expected bid prices and only 95% of construction budget was actually spent. | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 64 | 10 mbps - 100 mbps - Open Access | 0 | N/A | Most schools (CAIs) request either 50 mbps or 100 mbps services | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | Buggs Island Telephone(BIT) contracted with MBC to backhaul four (4) cell sites being developed under their BTOP grant. Due to equipment issues, they decreased their footprint and discontinued service to four (4) sites in our footfprint. The percentage of subscribers who have dropped off is 6.7%. The "churn rate" is 6.7%. | 28206 | 396 | 0 | 27810 | 0 | 0 | 0 | N/A | 1440 | 720 | 45 | 675 | N/A | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1) Entered into sixty (60) agreements; Shentel (4), Kinex (7), Lumos (11), GCR (31), BIT (4), Telpage (2), Gamewood (1) 2) Negotiating eight (8) agreements 3) Have not denied any requests for interconnection | N/A
NT10BIX5570023 | 2010 | 0 | Equipment procurement is underway; however, actual deployment has not started, and no portion of the network is available for service yet. Therefore, there is no cost per mile indicated for this report. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 1 Gbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 100 Mbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps, and we anticipate that most of our customers will fall into that level of service. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that we anticipate will be offered to most community anchor institutions. | Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the NFBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern Florida. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The NFBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network that has not yet been deployed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will not be providing access to dark fiber, as we do not have that access. | 292 | 292 | 292 | 292 | The availability of any additional co-location space is yet to be determined, as is its necessity. Upstream IRU design configuration is complete, IRU with Level 3 is in place to connect the core middle mile network to the first mile Internet backbone, and circuit delivery is on schedule. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network link. | We have not issued any subcontracts or subgrants. | We improved our approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability, greater capacity, and greater competition from more available manufacturersâ€”all within the original overall project budget. This approach requires more time for site assessments (for existing commercial towers and in-kind vertical assets) and follow-up engineering and network design, but it yields improved efficiency and shortens the overall deployment schedule. We are asking the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office (for our NFBA project) that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles. We are also conducting our own research on this matter in order to move forward with the development of the Equipment Installation and Pathing RFP in an effort to avoid any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Discovery of previous or duplicate federal funding for in-kind assets may or may not impact planned project progress, depending on the interpretation of this particular requirement. We are seeking to utilize only a limited amount of space on any given in-kind asset to mount microwave antennas and equipment; we are not seeking to utilize any in-kind asset in its entirety. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | N/A. We are continuing to finalize products and pricing with pre-deployment service level agreements. We have continuing dialogue with carriers, resellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements this quarter and next. We have not denied any request for interconnection. | N/A. As noted above, we are developing products and pricing with pre-deployment service level agreements, and developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. Also, the network design is committed to meeting the stringent quality of service and reliability standards set by the State of Florida for providing transport and direct internet access (as a last mile provider of last resort) to State agencies. Once deployed, the NFBA network will be qualified to serve State offices, community colleges, and their last mile network partners.
NT10BIX5570023 | 2011 | 0 | Deployment is still underway due to the grant suspension and transfer to new General Contractors; therefore, no portion of the network is available for service yet, hence, there is no cost per mile indicated for this report. | 0 | n/a | 0 | n/a | 1 Gbps | Currently engaging a vendor to conduct a market analysis to analyze services and pricing in rural Florida to validate baseline service offerings. However, the Maximum of 1 Gbps will continue to be available as described in the baseline for those last mile providers connecting at point of presence locations. | 0 | This is a middle mile network. The connection to last mile customers will be made by last mile providers. | 100 Mbps | Currently engaging a vendor to conduct a market analysis to analyze services and pricing in rural Florida to validate baseline service offerings. Services of up to 1 Gbps service will be available for those last mile providers connecting at point of presence locations. | 0 | This is a middle mile network. The connection to last mile customers will be made by last mile providers. | N/A | N/A | N/A - policies under development | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 292 | 146 | 0 | 146 | The NFBA does have collocation space available for interconnection with our network. In addition, as a wireless network, we have 92 interconnection points with ground lease space available at each site for collocating within the NFBA footprint. | None at this time. | n/a | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | The NFBA has been working on implementing a Corrective Action Plan and Transition Plan approved by the Grants Office following suspension of the Grant Award. NFBA is now completing a network evaluation and revised Project Plan to reflect its path forward following the completion of the transition to its new operating structure. In 1st quarter 2012, the NFBA will be conducting one or more community outreach events to inform key stakeholders regarding NFBA's activities, and is working to provide updated information regarding network routes and interconnection points. No request for interconnection has been denied. In addition, the NFBA has begun negotiation of two interconnection agreements with last mile providers. The NFBA, however, is currently in the process of updating its analysis of service offerings, pricing, and needs. These negotiations will proceed more rapidly following the completion of that analysis. | The NFBA has been working on implementing a Corrective Action Plan and Transition Plan approved by the Grants Office following suspension of the Grant Award. NFBA is now completing a network evaluation and revised Project Plan to reflect its path forward following the completion of the transition to its new operating structure. In 1st quarter 2012, NFBA will be conducting one or more community outreach events to inform key stakeholders regarding NFBA's activities and will provide updated information regarding network routes and interconnection points. Currently, the NFBA board has approved the Acceptable Use Policy, the Privacy Policy, and the main Service Level Agreement. Exhibits to articulate specifics to the providers to acquire space for peering and transit which will be negotiated on an as needed basis. service and costs would be negotiated at future time. Colocation space is available at the Level 3 facility to allow for anchor institutions and last mile
NT10BIX5570023 | 2012 | $28,537 | Average cost per new mile is calculated as follows: Cumulative direct capital costs associated with the installation of middle mile transmission infrastructure (through the end of calendar year 2012), divided by the route miles that the middle mile transmission infrastructure traverses. Capital costs are derived from equipment, material, and associated labor costs for the deployment of middle mile transmission infrastructure, such as tower cabling, field-installed equipment cabinets and access platforms (switches), licensed wireless radios and antennas, leased vertical tower space, and donated in kind vertical tower space. Capital costs do not include network access (e.g., core routers, upstream / first mile circuit provisioning, and associated leased co-location space for upstream circuits), customer premise equipment, testing equipment, billing and operational support systems, and professional services. Average cost per new mile, through the end of calendar year 2012: $20,546,768 / 720 miles = $28,537 / mile Route miles are determined as total new miles, which for this project corresponds to total new wireless core network miles. Our baseline plan was based on our original network design. The total new middle mile network miles and average cost per mile indicated in this report reflect our updated network design, which was approved through an Award Action Request. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 1 Gbps | At out Point of Presence we will deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions. Available speed tiers are customizable, generally increasing in increments of 10 Mbps. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 100 Mbps | The NFBA will deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions at our Point of Presence. Available speed tiers will begin at 10 Mbps, increasing in increments of 10 Mbps and 100 Mbps. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | Our partners at the Florida State University Information Institute conducted needs assessment, benchmarking, and onsite diagnostics at participating community anchor institutions in our network service area. Their research indicates that the current broadband speed available for the majority of community anchor institutions in our service area is 5 Mbps or less, according to survey respondents that were asked to identify their Internet Service Provider's advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we estimate the average increase in broadband speed provided through our project to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that is typically offered to most community anchor institutions. | Planned services include wholesale, enterprise, and e-Rate / discounted government Internet access. Private households and businesses are served through our last mile provider partners. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the Notice of Funds Availability. This project provides open, ubiquitous, Middle Mile access to broadband Internet services for both private entities (last mile service providers) and community anchor institutions in the underserved areas of northern Florida. Our non-discrimination policies are available to the public, and we will provide notice to our customers of any changes to these policies. We are fully committed to offering wholesale access at reasonable rates and terms. Our network management practices and policies adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and do not show favoritism to any lawful Internet applications and content over others. The North Florida Broadband Authority network is not a private, closed network, but instead is connected to the public Internet directly and provides open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network. Private households and businesses are served through our Last Mile provider partners. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. We will not be providing access to dark fiber, as we do not have that access. In reference to Question 9 above, this project is not constructing any fiber miles, so therefore all 7 fields in Question 9 are N/A, or not applicable. The formatting of this report does not permit us to enter letters (such as "N/A") in these fields, so we entered "0" instead. | 292 | 146 | 0 | 146 | The North Florida Broadband Authority has co-location space available for interconnection with our network. In addition, as a wireless network, we have 92 interconnection points with ground lease space available at each site for co-location within our core network footprint. Interconnection for customers (last mile providers) is available through switched multi-service access platforms located at each core network tower/wireless link. | N/A. We have not issued any subcontracts or subgrants. | Our in-house general management staff hosted a series of stakeholder workshops during this past calendar year to build relationships with the local broadband service providers in our service area. These events proved to be effective as we were able to present these local providers with the latest information regarding the status and direction of our network development. We also invited them to discuss their expectations for bandwidth and services in an open forum where they provided us with important feedback. We are continuing to plan workshops and seek other opportunities to build and leverage our relationships with the local broadband service providers in our service area. We also completed a comprehensive market and rate study to develop customer growth forecasts for our network services portfolio. This analysis supported our internal management strategies for product and service pricing, demand forecasting, capacity planning, network enhancements, capital and operational budgeting, long-term financial planning, and providing value-added services. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | We completed a market and rate study to develop customer growth forecasts for our network services portfolio and to provide current-state assessments and future-state recommendations for business planning and organizational activities. Through this analysis, we developed effective management strategies to plan, deliver, and manage our broadband services. In addition, following a transition period that resulted in significant improvements to our network engineering and deployment processes, our core middle mile network is now complete, fully operational, and available for customer access. We also successfully executed our network enhancement plan to ensure that network performance and capacity requirements are aligned with actual market conditions and forecasted customer demand. We have entered into 3 interconnection agreements for our organization to sell our wholesale services to last mile providers in our network service region. We are in negotiations for 1 interconnection agreement at this time to sell our wholesale services to another last mile provider. We have not denied any request for interconnection, as it is our policy to remain actively engaged in open customer acquisition. | Co-location space is available at our upstream (first mile) providers' facilities to allow for last mile Internet service providers and community anchor institutions to acquire space for peering and transit services, which will be negotiated on an as-needed basis. We currently have signed agreements in place for our organization to sell our wholesale services to 3 last mile providers in our network service region. We are in negotiations for 1 agreement at this time to sell our wholesale services to another last mile provider. We have not denied any request for peering and transit services, as it is our policy to remain actively engaged in open customer acquisition.
NT10BIX5570023 | 2013 | $22,144.89 | Average cost per new mile is calculated as follows: Cumulative direct capital costs associated with the installation of middle mile transmission infrastructure (from project inception through the end of the 3rd quarter of calendar year 2013), divided by the route miles that the middle mile transmission infrastructure traverses. Average cost per new mile, through the end of 3rd Quarter 2013: $18,291,678.96 / 826 new miles = $22,144.89 / new mile New miles are represented by new wireless network miles determined by equipment installed at towers within a direct line of sight. Fiber leased from our upstream providers is not included in this calculation. Our baseline plan was based on our original network design. The total new middle mile network miles and average cost per mile indicated in this report reflect our updated network design, which was approved through an Award Action Request. | 0 | This project is a Middle Mile Network. As such, Last Mile customer provisioning costs are incurred by our Last Mile provider partner. | 0 | This project is a Middle Mile Network. As such, Last Mile customer provisioning costs are incurred by our Last Mile provider partner. | 1 Gbps | Our Points of Presence are designed to deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions. Available speed tiers are customizable and generally increase in increments of 10 Mbps. | 0 | This project is a Middle Mile Network, and our network is capable of delivering maximum broadband speeds of up to 1 Gbps to Community Anchor Institutions from our Points of Presence. Our Last Mile provider partner publishes their maximum advertised broadband speeds at their discretion. Please see the attached Excel spreadsheet â€œAnnual PPR CCI Addendumâ€ for more details regarding broadband speeds provided to Community Anchor Institutions. | 100 Mbps | Our network is designed to deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions at our Points of Presence. Available speed tiers begin at 10 Mbps and increase in increments of 10 Mbps and 100 Mbps. | 8 Mbps | This project is a Middle Mile Network. The average broadband speed listed here is based on information provided by our Last Mile provider partner and represents the average speed provided to residential, business, and Community Anchor Institution last mile customers that receive broadband service through our network. We will continue to work with our Last Mile partner to provide this information as it is made available to us. Please see the attached Excel spreadsheet â€œAnnual PPR CCI Addendumâ€ for more details regarding broadband speeds provided to Community Anchor Institutions. | According to research from our partners at the Florida State University Information Institute, broadband speeds previously available for the majority of community anchor institutions in our service area were 5 Mbps or less, according to survey respondents that were asked to identify their Internet Service Provider's advertised speed. Actual speeds measured at end-user client workstations can be substantially less than advertised speeds due to high demand for broadband capacity within the facility. We therefore estimate the average increase in broadband speed provided through the North Florida Broadband Authority network to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that is typically offered to most community anchor institutions. | This project is a Middle Mile network that provides wholesale high speed Internet access to Last Mile providers and Community Anchor Institutions (as a provider of last resort, in the event Last Mile provider services are not available to the Community Anchor Institution). Our services include wholesale, enterprise, and e-Rate / discounted government Internet access. Private households and businesses are served through our last mile provider partner. | Our network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the Notice of Funds Availability. Our network provides open, ubiquitous, Middle Mile access to broadband Internet services for both private entities (last mile service providers) and community anchor institutions in the underserved areas of northern Florida. Our non-discrimination policies are available to the public, and we will provide notice to our customers of any changes to these policies. We are fully committed to offering wholesale access at reasonable rates and terms. Our network management practices and policies adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and do not show favoritism to any lawful Internet applications and content over others. The North Florida Broadband Authority network is not a private, closed network, but instead is connected to the public Internet directly and provides open access to all Internet resources. We offer interconnection opportunities where technically feasible without exceeding current or reasonably anticipated capacity limitations, with reasonable rates and terms negotiated with requesting parties. | N/A. This project is a Middle Mile network. Private households and businesses are served through our Last Mile provider partner. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. We do not provide access to dark fiber, as we do not have that access. In reference to Question 9 above, this project has not constructed any fiber miles, so therefore all 7 fields in Question 9 are N/A, or not applicable. The formatting of this report does not permit us to enter letters (such as "N/A") in these fields, so we entered "0" instead. | 438 | 438 | 0 | 438 | The North Florida Broadband Authority has co-location space available for interconnection with our network. In addition, as a wireless network, we have 95 interconnection points with ground lease space available at each site for co-location within our core network footprint. Interconnection for customers (Last Mile providers) is available through switched multi-service access platforms located at each core network tower site. | N/A. We have not issued any subcontracts or sub-grants to any socially and/or economically disadvantaged small businesses. | â€¢ We continued to organize workshops and outreach events for project stakeholders, community leaders, and Last Mile service providers. Our goals with these workshops are to provide stakeholders with current information regarding the status of our network development plans and to provide them with an open forum to discuss their expectations and concerns for bandwidth and services. This interaction gives us important feedback to include as an input for our market-based engineering processes. We expect that utilizing these types of outreach events and workshops would produce similar benefits for other BTOP projects. â€¢ During this past calendar year, we developed and launched of series of informational videos to create awareness for our network services. These videos include testimonials from some of our early adopter customers who describe how they are using high-speed broadband Internet service provided through our network to create their own success stories, which include building a profitable startup business (ahead of schedule) and improving the quality of online educational resources for the children who attend our rural community schools. Other similar BTOP projects might benefit from these types of informational or promotional videos by using them as supplemental media on their public-facing websites and social media pages. North Florida Broadband Authority informational videos can be viewed online at: www.youtube.com/user/NFBA1 â€¢ We continued to plan and coordinate in-kind site development with our Last Mile provider partner in a collaborative effort to provide broadband service to Community Anchor Institutions. We leveraged this Middle Mile / Last Mile partnership to reduce implementation time, cost, and risk, which helped to ensure faster "time to benefit" for everyone involved. â€¢ We continued to implement our network design enhancement plan this past calendar year, which included comprehensive independent reviews and assessments of our network's (then) current-state capabilities and future-state requirements to ensure that our network is able to meet current and anticipated customer demand for our high-speed Internet services and solutions. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | We entered into one interconnection agreement to sell our wholesale broadband services to a last mile provider in our network service region. We have not denied any request for interconnection, as it is our policy to remain actively engaged in open customer acquisition. | Co-location space is available at our upstream (First Mile) providers' facilities to allow Last Mile Internet service providers and Community Anchor Institutions to acquire space for peering and transit services, which is negotiated on an as-needed basis. We have not denied any request for peering and transit services, as it is our policy to remain actively engaged in open customer acquisition.
NT10BIX5570024 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No network build out has been completed at this time. | The U of U /UEN will not be offering any retail services. | UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | The U of U/UEN BTOP project has not completed connectivity to any subscribers at this point in time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | The U of U/UEN network Points of Presence (PoP) are located in all institutions of higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | No network build out has been completed at this time. | No network build out has been completed at this time.
NT10BIX5570024 | 2011 | 58,224 | There is a significant increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. Additionally, the U of U/UEN has not been invoiced for thirty (30) of the ninety five (95) completed builds, so the budgeted amount was used for these sites when calculating this average. | 0 | N/A | 0 | N/A | 1000Mbps | This is the maximum circuit connection speed that is being offered by sub recipients. | 0 | N/A | 712Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs, connecting at 100Mbps and 1000Mbps. These circuits speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average increase in broadband speed for CAI customers as a result of the BTOP Utah Anchors project is seven hundred ten (710) Mbps or an average of four hundred sixty (460) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were previously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the ninety five (95) CAIs that are now completed as a part of this project, is seven hundred twelve (712) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous average broadband speed (A) from the BTOP project average broadband speed (B) to arrive at the average increase in speed (C) and divided this by the previous average broadband speed to arrive at a percentage of increase. See the following: 712 -1.544 = 710.456 / 1.544 = 460%. | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2175 | 734 | 0 | 0 | 1441 | 0 | 0 | N/A | 600 | 50 | 0 | 550 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone, drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has entered into four (4) interconnection agreements during this annual reporting period. The U of U/UEN in not currently negotiating any additional agreements nor have we denied any requests for interconnection. | N/A
NT10BIX5570024 | 2012 | 95,765 | There is a significant increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. | 0 | N/A | 0 | N/A | 1000Mbps | This is maximum circuit connection speed that is being offered by the sub-recipients. | 0 | N/A | 660Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs connecting at 1000Mbps. These circuit speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average broadband speed for CAI customers as a result of the BTOP Utah Anchors project is six hundred sixty (660) Mbps or an average increase of four hundred twenty six (426) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were previously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the one hundred thirty five (135) CAIs that are now completed as a part of this project, is six hundred sixty six (660) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous average broadband speed for CAIs (B) from the BTOP project average broadband speed for CAIs (A) to arrive at the average increase in speed (I) and divided this by the previous average broadband speed (B) to arrive at a percentage of increase (P) . See the following: A - B = I/B = P (660 -1.544 = 658.456 / 1.544 = 426%). | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | The U of U/UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. The U of U/UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2339 | 998 | 0 | 0 | 1441 | 0 | 0 | N/A | 853 | 71 | 0 | 782 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone, drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has not entered into any interconnection agreements during the annual reporting period. The U of U/UEN is not currently negotiating and additional agreements nor have we denied any requests for interconnection. | N/A
NT10BIX5570024 | 2013 | 92,991 | There is an increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. | 0 | N/A | 0 | N/A | 100000Mbps | This is the maximum circuit connection speed that is being offered by the sub-recipients. | 0 | N/A | 675Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs connecting at 1000Mbps. These circuit speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average broadband speed for CAI customers as a result of the BTOP Utah Anchors project is six hundred seventy-five (675) Mbps or an average increase of four hundred thirty six (436) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were prevously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the one hundred forty-two (142) CAIs that are now completed as a part of this project, is six hundred seventy five (675) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous broadband speed for CAIs (B) from the BTOP project average broadband speed for CAIs (A) to arrive at the average increase in speed (I) and divided this by the previous average broadband speed (B) to arrive at a percentage of increase (P). See the following: A - B = I / B = P or (675 - 1.544 = 673.456 / 1.544 = 436%). | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunications services to residential and business customers on a retail or commercial basis in these service areas. | The U of U/UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. The U of U/UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception of sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2589 | 1073 | 0 | 0 | 0 | 0 | 0 | N/A | 963 | 855 | 27 | 108 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has not entered into any interconnection agreements during the annual reporting period. The U of U/UEN is not currently negotiating any additional agreements nor have we denied any requests for interconnection. | N/A
NT10BIX5570025 | 2010 | $54,263.56 | N/A | N/A | N/A | N/A | N/A | 10Gbps | N/A | N/A | N/A | 1Gbps | N/A | N/A | N/A | Seventeen of the sites are connected via NxT1, or DS3, and four sites are connected via Gigabit ethernet connections. The average increase is approximately 2.5gigabits. This is based on the gig locations moving to 10gig connections, and all other sites moving to 1 gig connections. Specifically, 4 sites increase by 9 gig, seven sites increase from 45 meg to 1000 meg, and nine sites increase from 9 meg to 1000 meg. The average is 2.5 gigabit increase. | The Zayo Bandwidth Middle Mile Proposal leverages dark fiber, DWDM (Dense Wave Division Multiplexing), and SONET (Synchronous Optical Network) technologies to provide Point to Point Private Line, Ethernet, Wavelength, Dark Fiber and Dedicated Internet services to last mile providers and end users. High count single mode fiber is being deployed in rings and linear spurs off of Zayo Bandwidthâ€™s existing network infrastructure to maximize the reach of the proposal. DWDM and SONET technologies are being deployed over the fiber to enable 1.5M to 10G services from the newly reached communities to the Zayo network infrastructure and the internet. The proposal provides interconnect points for connectivity to last mile providers or end users in the various markets via strategically placed points along the fiber path. From each interconnection point, Zayo will be capable of delivering Ethernet, Private Line, Wavelength, Dark Fiber and Dedicated Internet Access services from 1.5Mbps to 10Gbps via industry standard interfaces. A last mile provider or end user can connect to Zayo Bandwidth at any interconnection point via 2 fiber or 4 fiber optical interfaces. A 2 fiber interface is provided for Ethernet, Wavelength, and Unprotected SONET services while a 4 Fiber interface is used to provide Protected SONET services. The interconnection will leverage industry standard SONET interfaces at OC3, OC12, OC48, or OC192 SONET rates for the various service types, or can leverage standard Gigabit or 10Gigabit Ethernet interfaces for Ethernet private line, Wavelength, and Dedicated Internet Access services. A last mile provider or end user can also request that Zayo Bandwidth extend from a standard interconnection point to their facility. In this case Zayo Bandwidth would construct new fiber from an interconnection point to the customers designated premise and deploy equipment at the premise as appropriate for the requested service type. This extension is provided on an Individual Case Basis (ICB) and is dependent on the distance and complexity of the build. | Zayo will provide a customer with the bandwidth subscribed to, e.g. DS3 (45meg), Fast Ethernet (100meg or fractions thereof), etc. Zayo does not limit a customerâ€™s bandwidth up to the subscribed level, but will â€œchokeâ€ the bandwidth once the level is met. Traffic prioritization is not needed, since Zayo is not providing an â€œMPLSâ€ type service. Customers may, at their discretion, elect to run VLANs, traffic shaping or prioritization within the confines of their subscribed to bandwidth. Zayoâ€™s standard Master Service Agreement carries language forbidding customers from using the service for any unlawful act. We do not block customer traffic from any site deemed legal and lawful, but clearly will comply with government sanctions against sites found to be harmful or illegal. Customer may attach any legal device to our service, and we have not prevented customers from doing this at any time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is in talks with Verizon Wireless and FiberTower for dark fiber in Southwestern Indiana. The number of miles are unknown. | 0 | 0 | 0 | 0 | Pending locations for COâ€™s and New Huts Frontier CO, 711 Popular, Terra Haute, Indiana AT&T CO, 61 North Jefferson, Bloomfield, Indiana Smithville CO, 302 North Walnut, Bloomington, Indiana or AT&T CO 301 Washington, Bloomington, Indiana New Hut 1204 East 6th street, Huntingburg, New Hut between Rockport and Reo AT&T CO, 134 N.W. 6th Street, Evansville, Indiana Frontier CO, 315 North Hart Street, Princeton, Indiana New hut between English and Milltown Level 3 CO, 848 south 8th Street, Louisville, Kentucky Frontier CO in Connersville, Indiana New Hut between Chester and Webster New Hut between North Manchester and Warsaw New Hut in Marriam, Indiana Level3 Hut, 911 Adams, Gary Indiana Us Signal Hut, 3904 Massachusetts Street, Gary, Indiana | 3. Zayo has issued 4 subcontracts under this work. 1 Went to TurnKey for our Environmental Assessment. Zayo then divided the Engineering into 3 sections in order to meet our time line and ensure that we had backup in case one firm began to fall behind. Two of these sections went to small businesses. 1 was another subcontract to TurnKey for Engineering. 1 went to RCG for Engineering. | N/A | Zayo Bandwidth, LLC | 1070 | 0 | 21 | 0 | 3271 | 423 |  | 2388 | 0 | 0 | 7173 | 0. Per our baseline, this will not happen until Q2 of this year. | N/A
NT10BIX5570025 | 2011 | 67394 | This is slightly higher than our baseline, based on route changes and additional EA and Engineering work. | 0 | N/A | 0 | N/A | 10Gbps | This matches our baseline. | 0 | N/A | 1Gbps | This matches our baseline. | 0 | N/A | 1 Gbps based on customers that are currently unserved. | N/A This is a middle mile project. | Zayo's standard policies. Zayo has never blocked customers from accessing any lawful content, service, service provider or application. Zayo has never prevented any consumers from attaching any legal device to our network. | N/A This is a middle mile project. | 818 | 355 | 55 | 408 | 355 | 55 | 408 | 0 | 0 | 0 | 0 | 0 | Zayo will have collocation space, but we have not provided it yet. We are currently purchasing huts and ISP equipment. | Turnkey Network Solutions is a small business and did our EA work and some of our engineering. Gray and Pape is a small woman owned business and doing our Archeological work. JDH is a small business doing some of our engineering. (Engineering was divided up and bid out in segments because of the size of the project). Mitchell is a small business providing strand. Eustis Cable is a small woman owned business doing some construction for us. Baseline NXC is a small business doing some construction for us. White Mountain is a small veteran owned business doing splicing for us. | Zayo's biggest challenge has been dealing with pole providers and permitting agencies. We have had to tell them that we are willing to bypass them and go underground if we cannot reach agreement and agree to pricing. When we explain our deadline and our willingness to seek other solutions, we have found the pole providers and permitting agencies much easier to work with. | Zayo Bandwidth, LLC | 1070 | 0 | 21 | 0 | 3271 | 423 |  | 2388 | 0 | 0 | 7173 | 0 Currently entered into. Zayo is currently negotiating 30 agreements. Zayo has not denied any request. | 0 Currently entered into. Zayo is not currently negotiating any and Zayo has not denied any request.
NT10BIX5570026 | 2010 | Unknown | Construction is just beginning, therefore the cost is unknown at this time. | n/a | Middle mile project | n/a | Middle mile project | Unknown | Service is not yet available | n/a | Middle mile project | Unknown | No service is available yet | n/a | Middle mile project | No service has been provided. | No service has been provided. | A. Policies are currently under development. B. No. | No service has been provided. | 81600 | 0 | 0 | 0 | 6800 | 0 | 74800 | KINBER is not currently providing dark fiber services. | 0 | 0 | 0 | 0 | KINBER plans to enter into member agreements to provide collocation space at service and access nodes along the network. Other network providers and/or customers will interconnect with KINBER's network by working with KINBER engineers who will, in turn, work with the member hosting the site. | None. | None at this time. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | n/a | n/a
NT10BIX5570026 | 2011 | Unknown | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | n/a | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | Unkknown | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | Construction is underway. No services are being provided at this time. | Construction is underway. No services are being provided at this time. | A. Policies are currently under development. B. No. | n/a | 77520 | 0 | 0 | 0 | 0 | 0 | 77520 | None at this time. | 0 | 0 | 0 | 0 | KINBER plans to enter into member agreements to provide collocation space at service and access nodes along the network. Other network providers and/or customers will interconnect to the network by working with KINBER engineers. No space has been contracted at this time. KINBER also plans to connect to other network providers at Alleghany Center Mall in Pittsburgh and 401 N. Broad Street in Philadelphia. | n/a | Communication and transparency are very important to get broad public buy-in. KINBER is planning a Network member day event that is being very well received by the community. Since many people have question about the project and its eventual impact in Pennsylvania; we have also launched a website with weekly updates on the progress of the network construction, maps and other data that is of interest to the public. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | n/a | n/a
NT10BIX5570026 | 2012 | $75,833 | Construction is still underway on the network, so this figure represents the total construction cost to date (approx. $109M) divided by miles to date of 1437. This figure is slightly higher than expected due the construction not being complete. | n/a | This is a middle mile project, not last mile. | n/a | This is a middle mile project, not last mile. | 10G | Speed is as described in baseline. | n/a | This is a middle mile project, not last mile. | 1G | Speed is as described in baseline. | n/a | This is a middle mile project, not last mile. | To date, four CAIs have received improved broadband access. Their speed increases vary from 10X (100Mbps to 1,000Mbps to 200X (50Mbps to 10,000Mbps). With an average increase of 60X. | Proposed FY2013 prices for on-net services to members : Dark Fiber $700 per strand mile 1G Ethernet Port $1650 10G Ethernet Port $5,000 100M Ethernet Port $2,000 1G Ethernet Point-to-point $5,000 10G Ethernet Point -to-point $15,000 10G Lambda point-to-point $15,000 Commodity Internet $3 per Mbps | No policies are in place at this time other than acceptable use policies. KINBER has never blocked or limited a consumer from accessing content or service. | 0 | 77424 | 2874 | 34488 | 31614 | 352 | 4224 | 3872 | KINBER is not a provider of wholesale fiber. KINBER has made 24 strands available to IRU. | 0 | 0 | 0 | 0 | KINBER does not own any facilities or co-location space. Instead, it has entered into agreements with the CAIs connected to the network. | n/a | We have found that strong partnerships and good communication have been the best tools to make this project a success. Keeping our program officer, local government, and the public updated on our project has been very helpful in dealing with any questions that have come up about what we are doing and how it can benefit the Commonwealth. Engaging the appropriate professionals (staff, legal counsel, auditors) and ensuring detailed documentation have also allowed us to be successful. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | KINBER has entered into an interconnection agreement with Cogent, a commercial internet provider. We have not been approached by any other providers. | n/a
NT10BIX5570026 | 2013 | $65,083 | This figure represents 1612 miles of 48 strands of fiber (77,376 strand miles) which is a decrease from the originally proposed 1696 miles. This decrease was a result of changing construction contractors, an expedited construction schedule and a route change due to potential overlap with another BTOP funded project, Zito Media in the Northwestern corner of Pennsylvania. Although the route changed, we did not lose any CAIs. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 10G | As described in the baseline. | n/a | This is a middle mile project. | 1G | As described in the baseline. | n/a | This is a middle mile project. | To date, 7 CAIS have received improved broadband access. Their speed increases vary from 10X (from 100Mbps to 1,000MBps) to 200X (50Mbps to 10,000MBps). | Current pricing to on-net members is below. Non-members pay an additional 10%. 1G Ethernet Port Connection $1,650 10G Ethernet Port Connection $5,000 Point to Point Services 100M Ethernet $2,000 1G Ethernet $5,000 10 Ethernet $15,000 10G Lambda $5,000 Commodity Internet $3.00 per Mbps Dark Fiber $700 per strand mile | No policies are in place at this time other than an acceptable use policy. KINBER is working on developing and adopting model policies for network management. KINBER has never blocked or limited a consumer from accessing content or service. | 0. We haven't experienced anyone dropping service. | 77376 | 3224 | 38688 | 35464 | 0 | 0 | 0 | KINBER is not a wholesale provider of fiber. KINBER has made 24 strands available through an IRU. | 0 | 0 | 0 | 0 | KINBER does not own any facilities or collocation space. Instead, we have entered into agreements for space with CAIs connected to the network. | n/a | Communication with all stakeholders has been the most important lesson learned. KINBER continues to work to build its brand awareness within Pennsylvania through marketing efforts, gatherings and outreach activities. We are learning not to concentrate on the technology but on the outcomes it can facilitate. Of course, excellent record keeping and transparency help to answer any questions raised and facilitate a positive audit experience. The importance of sustainability planning, especially for new organizations, cannot be overstated. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | KINBER has entered into an interconnection agreement with Cogent, a commercial Internet provider. | KINBER has not entered into any peering or transit agreements.
NT10BIX5570027 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, however due to the increased demand for bandwidth; the DPI system will be brought back online in 2011 with the intention of prioritizing certain applications over others on our wireless access networks only. In managing our network through traffic prioritization, we intend to give a lower priority to peer to peer file sharing traffic and other traffic that does not noticeably impair our customer experience. Though a lower priority will be given to certain applicati | N/A | 8250 | 0 | 0 | 0 | 0 | 0 | 8250 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | ENMR-Plateau has 3 interconnection agreements in place prior to this reporting period. No new interconnection agreements have been entered into in this reporting period and no agreements are being negotiated at this time. ENMR-Plateau has not denied any requests for interconnection during this reporting period. | ENMR-Plateau is currently providing peering services to the University of New Mexico and in negotiations with New Mexico State University. ENMR-Plateau has not denied any requests for peering or transit during this reporting period.