NT10BIX5570027 | 2011 | $82,773.87 | Positive variance. Total cost of construction divided by the number of fiber miles constructed as of 12/31/11. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 1Gb | As of the end of the reporting period the average broadband speed provided by ENMR-Plateau is 1Gb to the 23 Roswell Independent School District CAI locations. | 0 | N/A | As of 12/29/2011 ENMR-Plateau activated 23 CAI (schools k-12) locations providing 1Gb broadband service to each. 19 of the CAI locations were previously utilizing dual T-1 services comprising of broadband speeds of 3Mb to each location, four of the CAI locations were previously utilizing 1Gb broadband service from ENMR-Plateau. Therefore the average increase in broadband speed provided to the 23 CAI locations as a result of the project is 824Mb per location. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. At this time ENMR-Plateau does not prioritize any network traffic and at no time will we block access to any lawful content, service, service provider, or application. | N/A | 8271 | 43 | 0 | 0 | 8228 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of Plateauâ€™s Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to Plateauâ€™s POI building. This fiber splice would connect the network providerâ€™s fiber to Plateauâ€™s single-mode fiber entering the building and terminating on Plateauâ€™s optical equipment. This enables optical level interconnection between the other network providerâ€™s optical equipment and Plateauâ€™s. Interconnections with customers of Plateauâ€™s services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR-Plateau has entered into 3 new interconnection agreements this annual reporting period, (2) ENMR-Plateau is currently negotiating 1 new agreement, (3) ENMR-Plateau has not denied any requests for interconnection during this reporting period. | N/A
NT10BIX5570027 | 2012 | $90,163.66 | Total cost of construction divided by the number of fiber miles constructed as of 12/31/12. Includes fiber cable, vaults, etc. and labor of outside plant construction contractor. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR Telephone Cooperative is 1Gb. | 0 | N/A | 557Mb | As of the end of the reporting period the average broadband speed provided by ENMR-Plateau and subrecipients is 557Mb to CAI locations. This average includes a 10Gb connection to UNM. | 0 | N/A | As of 12/31/12 ENMR-Plateau and Baca Valley Telephone have activated 60 CAI locations. The following is a breakdown of the number of anchor instutions for each speed tier: 1.5Mb (1), 3Mb (4), 5Mb (11), 8Mb (7), 10Mb (4), 20Mb (7), 40Mb (1), 100Mb (1), 1Gb (23), 10Gb (1). Out of the 60 CAI locations that ENMR and Baca Valley are providing services to, as of 12/31/12, we were able to determine the previous broadband speeds of 48 of those locations. We calculated an average current broadband speed of 486Mb and an average previous broadband speed of 67Mb, which results in an average increase in broadband speed of 419 per CAI location as a result of the BTOP award. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 8271 | 8271 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR Telephone Cooperative has entered into 1 new interconnection agreements this annual reporting period with Conterra Ultra Broadband, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A
NT10BIX5570027 | 2013 | $94,363.99 | Total cost of construction divided by the number of fiber miles constructed as of 1/31/13. Includes fiber cable, vaults, etc. and labor of outside plant construction contractor. Slightly higher than last reporting period due to final invoicing being paid in the interim. | 0 | N/A | 0 | N/A | 1Gb | The maximum speed advertised by ENMR Telephone Cooperative is 1Gb. | 0 | N/A | 557Mb | As of the end of the reporting period the average broadband speed provided by ENMR Telephone Cooperative and subrecipients is 557Mb to CAI locations. This average includes a 10Gb connection to UNM. | 0 | N/A | As of 1/31/13 ENMR Telephone Cooperative and Baca Valley Telephone Company have activated 60 CAI locations. The following is a breakdown of the number of anchor institutions for each speed tier: 1.5Mb (1), 3Mb (4), 5Mb (11), 8Mb (7), 10Mb (4), 20Mb (7), 40Mb (1), 100Mb (1), 1Gb (23), 10Gb (1). Out of the 60 CAI locations that ENMR and Baca Valley are providing service to, as of 1/31/13, we were able to determine the previous broadband speeds of 48 of those locations. We calculated an average current broadband speed of 486Mb and an average previous broadband speed of 67Mb, which results in an average increase in broadband speed of 419Mb per CAI location as a result of the BTOP award. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access services which are typically Ethernet services from the local interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 8271 | 8271 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR Telephone Cooperative has entered into 3 new interconnection agreements this annual reporting period with Verizon Wireless, North Central NM Economic Development and Northern New Mexico Telecom, (2) ENMR Telephone Cooperative is currently negotiating no new agreements, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period | N/A
NT10BIX5570028 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 406 | 0 | 3506 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Administration, Wisconsin Department of | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570029 | 2010 | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | 0 | N/A, Middle Mile Project | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | N/A | N/A, Middle Mile Project | N/A | N/A | 1120 | 0 | 0 | 0 | 1120 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | All points of interconnection between the proposed Middle Mile network are either at the indicated Community Anchor Institutions of by direct negotiation with interested Last Mile providers. | N/A | None at this time. | Education Networks of America, Inc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570029 | 2011 | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | 0 | N/A, Middle Mile Project | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | N/A | N/A. Middle Mile Project | N/A. Grant terminated. | N/A. Grant terminated. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. Grant terminated. | N/A. Grant terminated. | N/A Grant terminated. | Education Networks of America, Inc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570030 | 2010 | 0 | Deployment is not complete for any parts of the network. | 0 | N/A | 0 | N/A | 1Gb | This is the maximum speed to be offered by the one last mile provider with which we have an agreement. (TBCNet) | 0 | N/A | 0 | Deployment is not complete for any parts of the network. | 0 | N/A | N/A Deployment is not complete for any parts of the network. | N/A Deployment is not complete for any parts of the network. | N/A Our project is middle mile. | N/A Deployment is not complete for any parts of the network. | 6240 | 0 | 0 | 0 | 520 | 0 | 5720 | N/A Deployment is not complete for any parts of the network. | 0 | 0 | 0 | 0 | Customers and/or network providers connect either at Community Anchor Institutions or hand hole locations along the route. | DeKalb Fiber Optic, LLC has awarded two supplier contracts to Women's Business Enterprises. Those are B and C Distribution dba R-BOC Representatives and KGP Telecommunications, Inc. | DeKalb County has been working collaboratively together with the Northern Illinois University (NIU) BTOP finding project by collaborating weekly on strategic interconnections between the networks and their methodology. NIU has regular correspondence with the IBOP-EC project to assure that the Illinois Century Network interconnection points as successfully executed for delivery of content to ICN constituents. The synergies between DeKalb County and the IBOP-EC are in process by regular e-mails, phone or in person meetings. DeKalb County has been working with the Partnership for Connected Illinois (PCI) on developing the necessary information and processes to meet their goals. DeKalb County plans to attend the seminars presented by PCI for the State of Illinois BTOP grantees to understand further the requirements of PCI. For future BTOP project applicants, we recommend keeping in regular communication with proposed Community Anchor Institutions during the application, due diligence, award, and environmental assessment periods. We are finding that entities previously interested in being a community anchor in our project have accessed other providers of high speed internet or constructed their own high speed infrastructure in the lag time between initial contact and actual build of the system. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1) None entered into. 2 )None are currently being negotiated. However, we expect to have interconnection agreements with Northern Illinois University and several school districts that have multiple schools on the system. 3) None denied. | 1) None entered into 2) None currently being negotiated. However, we may have peering agreements eventually with other BTOP projects and non-BTOP-funded projects in the northern Illinois area. 3) None denied.
NT10BIX5570030 | 2011 | $90,077 | 4.09 miles in service @ total cost of $368,414. This is the same cost as we provided in our application and upon which the construction budget is based. | 0 | N/A | 0 | N/A | 10Gb | Available within networks, rings and dark fiber. | 0 | N/A | 683Mb | Two customers (three locations) active for which our project is not the ISP for eany. Project is providing transport only at 50Mb for one and other has two locations running at 1 Gb. 50+1000+1000= 2050/3= .683 Gb | 0 | N/A | For the three connections mentioned in Q1, two were using a wireless connection @ 20Mb and was increased to 1 Gb (increase of 980 Mb). The third connection was using a wireless connection @ 768 Kb and was increased to 50Mb (increase of 49.232Mb). 2 x 980Mb + 49.232Mb= 2,009.232 / 3 = average increase in speed of 669.744 Mb. | None | Network policies based on port speed system will use protocols PPB-TE and IEEE 802.1Q with IP for prioritizing network traffic. | None | 19034 | 8 | 5717 | 6525 | 1790 | 3203 | 1791 | DeKalb Fiber Optics. LLC is being provided, via IRU, 68 strands of fiber throughout the system for economic development purposes. Dekalb Fiber Optics has, in turn, has to-date subleased more than 45 strand miles for economic development including providing service to an underserved community wireless network previously providing service to approximately 35 residents via a 3Mbps connection. The new connection is running at 50 Mbps, more than a 16 fold increase in speed. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in the Northern Illinois University Network Operations Center and indirectly in the Northern Illinois University Central Office. In addition, interconnection also can be provided at any of more than 300 hand holes provided as a part of the project. | None by the recipient. Sub-Awards have been made by the contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1) B and C Distribution dba R-BOC Representatives and KGP Telecommunications, Inc. | All duct used in the project contains multiple sub-ducts that allow additional cable to be installed in the future of needs dictate with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. None entered into. 2. We are in discussions with four ISP's to provide service over the BTOP funded network 3. We have not denied any requests for interconnection. | 1. Entered into peering agreement with DNA Communications for collocation space in four telephone central offices. 2. Currently negotiating agreement with Northern Illinois University for peering location at Network Operation Center. Draft agreement is currently in University administrative review process. 3. We have not denied any requests for interconnection.
NT10BIX5570030 | 2012 | $90,077 | 596,672 feet of new construction completed as of December 31, 2012 at cost of $10,179,247. This is the same cost provided in our application and upon which the construction was based. | 0 | N/A | 0 | N/A | 10Gb | Available within networks, rings and dark fiber. | 0 | N/A | 943Mb | Of 61 connections, 52 are lit. 47 are at 1 Gbps, 3 are at 50 Mbps and two are dark fiber. ([47*1000] + [3*50]) = 47,150/ 50 = 947 Mbps | 0 | N/A | The average speed increase for the lit connections is 916 Mbps. This was calculated by obtaining the pre-project broadband speeds for each Community Anchor Institution and subtracting that speed from the new connection speed. The results were totalled and averaged. New connections and dark fiber connections were omitted from the calculations. | None | Network policies based on port speed system will use protocols PPB-TE and IEEE 802.1Q with IP for prioritizing network traffic. | None | 18661 | 553 | 8592 | 9194 | 72 | 322 | 146 | DeKalb Fiber Optics, LLC is being provided, via IRU, 68 strands of fiber throughout the system for economic development purposes. This amounts to 8,624 of the strand miles built to-date. DFO has subleased 2 strands across the majority of the network to a carrier providing LTE upgrades in fiber-to-the-cell, resulting in expanded mobile broadband access. DFO has contracted with a number of financial institutions to utilize the leased fiber to provide upgraded connectivity. DFO and their providers are rolling out broadband service to agricultural businesses throughout the region at speeds in excess of 300 Mbps. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in Northern Illinois University Network Operations Center and indirectly at Northern Illinois University Central Telephone Office. In addition, interconnection can be provided at any of the 291 hand holes currently deployed. The project also has interconnection agreements with the Northwest Illinois BTOP project (iFiber) for two additional interconnection points, extending interconnection potential for the DATA project to network providers and/or customers at locations throughout the six northwest Illinois counties as well as the DeKalb County area. | None by the recipient. Sub-awards have been made by the Contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1)B and C Distribution dba R-BOC Representatives and 2) KGP Communications, Inc. | The County engaged an independent engineer to verify all footages billed by the contractor for the project and to confirm the placement of all hand holes. The project used duct containing multiple sub-ducts, allowing for additional cable to be installed in the future if needed with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. Five entered into during this reporting period, 2. Three are in current negotiations, 3. We have not denied any interconnection requests. | No peering agreements entered into during reporting period. Transit agreements: 1. Three entered into during this reporting period. 2. One in current negotiations 3. We have not denied any interconnection requests.
NT10BIX5570030 | 2013 | $90,077 | 597,196 feet of new construction completed as of end of 2013 at a cost of $10,201,061. This is the same cost provided in our application and baseline report. | 0 | N/A | 0 | N/A | 10Gbps | Available within networks, rings and dark fiber. | 0 | N/A | 897Mbps | Of 78 total connections, 64 are lit, 3 are connected via dark fiber and 11 did not elect service as of this time. Of the 64 lit connections, 57 are at 1Gb, 1 is at 100 Mbps and 6 are at 50 Mbps. ([57*1000] + [6*50] + [1*100]/64=897Mbps. | 0 | N/A | The average speed increase for the lit connections is 843Mbps. This was calculated by obtaining the pre-project broadband speeds for each Community Anchor Institution and subtracting that speed from the new, post-project connection speed. The result was totaled and averaged. New connections and dark fiber connections were omitted from the calculations. | None | a)Network policies are based on port speed system with use protocols PPB-TE and IEEE 802 1Q with IP for prioritizing network traffic. The DeKalb County Network is a layer 2 designed network providing for Metro Ethernet connectivity. Three classes of priorities have been defined in the network based on off ELAN classes of traffic. The three levels of traffic are 1) E-911 Services, 2) ISP Services and 3) Cloud (intranet) Traffic. The highest level of priority is given to the E-911 services with the next level to ISP services and the lowest to the intranet cloud traffic. The system is open to all lawful content and types of traffic. b) We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | None | 18132 | 1574 | 8354 | 8204 | 0 | 0 | 0 | DeKalb Fiber Optics, LLC is being provided, via IRU, with 68 strands of fiber throughout the newly constructed network for economic development purposes. This amounts to 8,354 of the strand miles built by the project. This number is less than we reported last year. When we audited the entire build in preparing the 2013 annual report we discovered we erroneously counted fiber in pin point duct for service lateral as 144 fibers when, in fact, only 12 fibers were installed in pin point for the most part and none of the fibers in the pin point has been allocated to DeKalb Fiber Optic, LLC for economic development. This adjustment also lowered the Total Strand-mile metric as compared to last year. Of the 68 fibers allocated to DFO: - 2 strands has been subleased across the majority of the network to a carrier providing LTE upgrades in fiber-to-the-cell resulting in expanded mobile broadband access. - a number of financial institutions, especially in rural areas of the county, have leased fiber to provide increased connectivity to existing and new facilities. - broadband services to agricultural businesses throughout the region is being rolled out by DFO and its providers. Speeds are in excess of 300 Mbps. - broadband services to residential areas, especially in rural areas of the county, is being improved as DFO has provided increased connectivity to cable tv providers. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in Northern Illinois University Network Operations Center and at Northern Illinois University Central Telephone Office. In addition, interconnection can be provided at any of the 291 hand holes through which owed and leased fiber passes. The project also has interconnection agreements with the Northwest Illinois BTOP project (iFiber) for two additional interconnection points, extending interconnection potential for the DATA project to network providers and/or customers at locations throughout the six northwest Illinois counties as well as the DeKalb County area. | None by the recipient. Sub-awards have been made by the Contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1)B and C Distribution dba R-BOC Representatives and 2) KGP Communications, Inc. | The County engaged an independent engineer to verify all footages billed by the contractor for the project and to confirm the placement of all hand holes. The project used duct containing multiple sub-ducts, allowing for additional cable to be installed in the future if needed with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. Three entered into during 2013. 2. None are currently being negotiated 3. We have not denied any interconnection requests. | No peering agreements entered into during 2013. Transit Agreements: 1. One entered into during 2013. 2. None in current negotiations. 3. We have not denied any interconnection agreements.
NT10BIX5570031 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 47088 | 0 | 37632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The most monumental lesson learned related to the WV BTOP grant is that of the Environmental Assessment process. Because of the scope, complexity, and geography of our project, this was a monumental task. Recommendation: Start this process early and have a â€œteamâ€ dedicated solely to this aspect of the overall environmental effort. Another lesson learned is that of planning teams. Shortly into the planning and engineering the magnitude of the effort surfaced. We were a bit slow to induce planning and engineer teams into the process. After we originated these teams and implemented their operation, the entire process gained momentum. Recommendation: Begin with all engineers, planners, and stakeholders involved. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | (1) N/A (2) Interconnect -2 Peering - 0 Transit - 1 (3) N/A | N/A
NT10BIX5570031 | 2011 | 50,000 | Baseline shows 17,000. This price has been on the rise since the Hurricane in Japan. The lack of sources to buy Fiber has driven the cost up as well. | N/A | N/A | N/A | N/A | 50 MEG | As noted in baseline | N/A | N/A | 10 MEG | As noted in baseline | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtrue bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a rock-steady 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, OC3 (155 Mbps), OC12 (622 Mbps), and OC48 (2.5 Gbps) if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. | 7a. N/A 7b. N/A | The Project is under the initial activation phase customers are currently just beginning to sign up with carrier for enhanced Broadband service to date there has been no one removed from the new served areas. This in time may change but as of 12-31-11 this metric in not applicable. | 99585 | 0 | 0 | 20962 | 849603144 | 7862 | 39312 | We are currently negotiating one interconnect agreement with CityNet West Virginia LLC. Frontier is still awaiting the amount of fiber strands that CityNet wishes to utilize, but the total mileage of that agreement will 0.19 miles. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two subcontracts. One is with Frontier Communications, the other is with Lewis County Commission. | Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier Communications is currently finalizing an interconnect agreement with CityNet West Virginia LLC for the Bridgeport Library location. The details of said "in progress" agreement are below. 2.0 BTOP Fiber Meet Point 2.1 All Charges are based on the following in accordance with the Technical Specifications Form: GPS COORDINATES A Location GPS Stop 39.2996 -80.2752 Z Location GPS Start 39.2989 -80.2731 PHYSICAL LOCATION Access to Fiber serving the Bridgeport Public Library 1200 Johnson Avenue, Bridgeport, WV in Harrison County ACCESS The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses.The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses. | N/A
NT10BIX5570031 | 2012 | 47,500 | Although the baseline indicates a cost of $17,000 per mile, the actual cost is at $47,500 per mile. This is a decrease from $50,000 as noted on the 2011 Annual Report. We expect the cost to continue to decrease. However, the storms late in 2012, the environmental considerations, delay on fiber receipts, and other factors continue to cause the per mile cost to be above baseline. | N/A | N/A | N/A | N/A | 50 MEG | The 50 MEG maximum is in keeping with the baseline for the EOWV BTOP grant. | N/A | N/A | 10 MEG | The average speed at 10MEG is in keeping with the baseline for the EOWV BTOP grant. | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtruer bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a reliable approximate 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, OC3 (155 Mbps), OC12 (622 Mbps), and OC48 (2.5 Gbps) if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. | 7a. N/A 7b. N/A | This project does not offer broadband services. | 91296 | 27388 | 0 | 63908 | 29160 | 0 | 68040 | We are currently negotiating one interconnect agreement with CityNet West Virginia LLC. Frontier is still awaiting the amount of fiber strands that CityNet wishes to utilize, but the total mileage of that agreement will 0.19 miles. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two subcontracts. One is with Frontier Communications, the other is with Lewis County Commission. | Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. In retrospect, it would be a positive for all similar grants to begin "outreach" programs at receipt of grant funding. After grant award, the "outreach" should be on-going. A proactive program would serve to minimize many misunderstandings associated with grant actions. We utilized a Point of Contact (POC) approach to disseminate information to the end user. It would have been better had we had more direct approach at the user level at intervals, but maintaining the overall POC approach. The magnitude of the grant, including total funding, differences of major efforts contained within the grant, and varying entities associated would have been better served had we utilized at all levels a single data-base. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier Communications is currently finalizing an interconnect agreement with CityNet West Virginia LLC for the Bridgeport Library location. The details of said "in progress" agreement are below. 2.0 BTOP Fiber Meet Point 2.1 All Charges are based on the following in accordance with the Technical Specifications Form: GPS COORDINATES A Location GPS Stop 39.2996 -80.2752 Z Location GPS Start 39.2989 -80.2731 PHYSICAL LOCATION Access to Fiber serving the Bridgeport Public Library 1200 Johnson Avenue, Bridgeport, WV in Harrison County ACCESS The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses. | N/A
NT10BIX5570031 | 2013 | $57,881/$62,338 | There are 2 calculations for cost per mile. If we remove all FBO and Legal/Audit fees, the cost for building 675 miles of fiber equated to $57,881 per mile. If we include those "non construction" components that include customer premise FBO work, along with Legal and Audit fees, the cost per mile equated to $62,338. Federal regulations dictating Davis-Bacon wages added $7.5 million to the overall cost. Below is a breakdown of our analysis. Restated Totals 1. Remove FBO, Audit & Legal BTOP Invoiced Cost $42,078,450 FBO $2,435,316 Audit & Legal $573,371 X - FBO & Audit $39,069,763 Miles 675 $/Mile $57,881.13 | N/A | N/A | N/A | N/A | 10Gig | The link connecting NRAO/WVU will be provisioned and capable of providing speeds up to 10 Gigabits per second to meet the demands of data transfer between those 2 facilities. | N/A | N/A | 100Meg | Frontier has provisioned and installed over 300 Metro-E circuits for BTOP CAIs since the inception of the BTOP program. The average rate of those circuits is approximately 100 Megabits per second. | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtruer bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a reliable approximate 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, and even 10 Gigabit Ethernet if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. As stated above, over 300 CAIs have upgraded to MetroE services since the inception of this project. | 7A. There are no bandwidth limitations with this project. As for traffic priority, standard Class of Service (CoS) and Quality of Service (QoS) policies are applied. 7b. N/A | This project does not provide broadband services. However, as stated above, over 300 CAIs have upgraded to MetroE services since the inception of this project. | 95225 | 38090 | 0 | 57135 | 38090 | 0 | 57135 | Dark fiber is available to other carriers at wholesale rates. However, as stated above, there are currently no finalized, signed interconnection agreements. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two sub grants. One is with Frontier Communications, the other is with Lewis County Commission. | Best practices for this grant remain as stated last year, which is noted below. Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. In retrospect, it would be a positive for all similar grants to begin "outreach" programs at receipt of grant funding. After grant award, the "outreach" should be on-going. A proactive program would serve to minimize many misunderstandings associated with grant actions. We utilized a Point of Contact (POC) approach to disseminate information to the end user. It would have been better had we had more direct approach at the user level at intervals, but maintaining the overall POC approach. The magnitude of the grant, including total funding, differences of major efforts contained within the grant, and varying entities associated would have been better served had we utilized at all levels a single data-base. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier has been contacted by seven carriers seeking information on BTOP facilities, and has entered into detailed negotiations with one carrier. However, there are currently no finalized, signed interconnection agreements. | N/A
NT10BIX5570032 | 2010 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | No services are being provided yet, so it is not possible to calculate an average increase in speed. | No retail services are being provided at this time. LCOG will contract with retail service providers who will then offer services to the anchor institutions. When those arrangements are made, LCOG will report them. | 7a. No policies are yet in place. The plan is to not have any limitations except as they relate to increased price for greater service. these price structures will be evenly applied. 7b. The contracts that we will negotiate with service providers will have an express prohibition on limiting access. | Not Applicable | 398 | 185 | 295 | 295 | 0 | 3 | 110 | No leases have been made | 1040 | 100 | 0 | 940 | LCOG will be providing collocatoin space. | No subcontracts with socially or economically disadvantaged small businesses have been made thus far. | None at this time. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | N/A | N/A
NT10BIX5570032 | 2011 | $159,597 | This number was reached by dividing the federal funds spent on engineering and construction by the number of customers connected as of December 31. It is misleading because a great deal has been spent to connect other customers, but these customers have not yet been brought on line. | NA | NA | NA | NA | 55Mbs | This is the speed offered in the promotional advertising for commercial operations by the provider who is currently connected to the most customers. There is no advertising for connections to anchor institutions, because individual arrangements are made. As additional segments become available, speeds will increase. The planned gigabit ethernet segment is not on line yet, so no advertising has been done for this segment. | NA | NA | 10Mbs | It is difficult to discuss an average speed with so few customers currently connected. Initial demand is always lower than what it grows to be within a short time. | NA | NA | Only a few sites have been connected so far. The average increase is approximately 10 Megabits per second, because prior to connection, the sites had no broadband connectivity, and the service provider is providing services at that level. | We are contracting with service providers to provide retail services. The one provider that we have contracted with that is offering services over the fiber constructed by the project thus far is Douglas Fast Net. Douglas Fast Net offers a range of services. The attached service plan describes and provides the prices for these services. The relevant prices for this project are attached. The fiber based services range from 1 to 100 plus megabits. | No services are provided yet, except through contracts with other service providers. By contract the service providers are required to offer services to all on a non-discriminatory open platform. 7b. The service providers are contractually required to provide non-discriminatory services. | No subscribers have dropped service. | 4114 | 0 | 1310 | 1762 | 0 | 521 | 521 | This question is confusing (as is question 9) It presents misleading figures. A number of the fibers that are currently dark will be used by the recipient, but this does not allow that to be reported. | 0 | 0 | 0 | 0 | No collocation space has yet been finished. When completed there will be approximately 200 square feet of collocation space available. Approximately 10 square feet of recipient's owned space will be used by the recipient, and an additional 4 square feet will be leased by recipient. The remaining approximately 190 square feet will be available for other users. | No contracts have been made to socially and economically disadvantaged small businesses. | None. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | We have not entered into any interconnection, peering or transit agreements yet. We are negotiating or will soon negotiate six (6) interconnection agreements and five (5) transit agreements. We do not expect to negotiate any peering agreements. We have not denied any requests and will not deny any requests. | We have not entered into any interconnection, peering or transit agreements yet. We are negotiating or will soon negotiate six (6) interconnection agreements and five (5) transit agreements. We do not expect to negotiate any peering agreements. We have not denied any requests and will not deny any requests.
NT10BIX5570032 | 2012 | 16785 | This has increased slightly because the number of miles for the project has decreased slightly as we get better estimates of actual distance., | NA | NA | NA | NA | Gigabit | No change from baseline. | NA | NA | 10Meg | I believe that this is the same. This is a average using the projected mode. | NA | NA | The average increase is perhaps 70 Megabits/ second. This is calculated by considering the previous average speed, which was either zero (for most users) or poor DSL, and considering the speed most commonly purchased. | We are not providing retail services. We contract with several retail providers across a three county area. They have varying prices that they offer. | We have no network management policies in place. We have been able to provide more bandwidth than needed by the customers. No customers have been blocked from accessing any content. | NA | 500 | 107 | 393 | 0 | 107 | 0 | 0 | We are leasing as dark fiber all of the constructed strand miles, an estimated 107 miles. | 300 | 6 | 6 | 288 | NA | No sub grants have been made. No subcontracts have been made to SBD concerns. | A successful outreach program will overwhelm you with demand for services from potential customers who may not qualify for service but would still like to get service. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | One Agreement has been signed. We are negotiating four additional interconnection agreements. We expect to negotiate an additional five agreements in the next year or so. We have not denied any request for interconnection. | We have not negotiated any peering agreements yet. We hope to do so in the next year.
NT10BIX5570032 | 2013 | $16,785 | This has increased slightly as the number of miles has become more accurately measured. | NA | NA | NA | NA | Gigabit | No change from baseline | NA | NA | 10 Meg | Same | NA | NA | The average increase is perhaps 70 Megabits/ second. This is calculated by considering the previous average speed, which was either zero (for most users) or poor DSL, and considering the speed most commonly purchased. | We are not providing retail services. We contract with several retail providers across a three county area. They have varying prices that they offer. | There are no network management policies allowed. Each provider signs an agreement that they will provide an open network, with equal service to all customers. Bandwidth uses are all tiered, and all users pay the same prices for use. | NA | 499 | 104 | 395 | 0 | 104 | 104 | 0 | Coast Com, 8 miles; Douglas Fast Net, 120 miles; Hunter Communications, 31 miles; City of Cottage Grove, 4 miles. Note this adds up to more than the active strand miles because some of the leased fibers are sub-leased. | 300 | 6 | 24 | 270 | NA | NA | None | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | Five have been signed. | Two agreements have been signed. This was not projected in the baseline report.
NT10BIX5570033 | 2010 | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Applicable. Project is in Pre-Construction Stage. | 0 | 0 | 0 | 0 | Not Applicable. Project is in Pre-Construction Stage. | We have not made any subcontracts with entities with section 8a definition. Project is in pre-construction stage. | a) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; 1) create a baseline for comparison when the project is implemented, 2) Pinpoint resources in the school system to foment the use of broadband resources, 3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, 4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, 5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form b) The baseline report which we initially submitted was not prepared utilizing cash spent versus project total cash, as the project progress measurement method. The original baseline prepared was based on the planning of activities. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time in addition to the time it takes to deliver, install and test the equipment. This effort does not require a big amount of cash disbursement, therefore t he progress made, measured with the cash disbursement method is not recognized. However we have recognized that our project plan needs to reflect the cash disbursement methodology and we will comply with the SAC goal of more than 70% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and 100% completion in the three years of the project. The lesson learned here is to avoid assuming a methodology and to insure that you understand the requirement. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | N/A. Project in Pre construction stage. | N/A. Project in Pre construction stage.
NT10BIX5570033 | 2011 | 0 | N/A. Project in construction stage | 0 | N/A. Project in construction stage | 0 | N/A. Project in construction stage | 9 mbps | Project in construction stage | N/A | N/A. Middle mile project in construction stage | 5.6 mbps | Project in construction stage | N/A | N/A. Middle mile project in construction stage | Project network is in construction stage. | Not applicable. Project network is in construction stage. | Project network is in construction stage. | Not applicable. Project in construction stage. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 0 | 0 | 0 | 0 | Project is in construction stage | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB - Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we meet the 67% objective in the first two years, we have developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already exist (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will install equipment in these towers and complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center will be completed or ordered in 2011 which will assure substantial completion of expenditures for the project within the two year requirement. We will also be constructing in these two initial quadrants, three of the eight new towers in the network. We have construction permits for these three towers and completed the RFP process to award construction. By developing this quadrant strategy and prioritizing the site preparation and tower construction, INTECO has established the objective to activate the network and the operations in the these two areas in summer of 2012, ahead of the Grant schedule. We will initiate connection for CAIâ€™s in the third quarter of 2012 in the quadrants which are activated. We have completed interconnection agreements and a wholesale agreement with two providers in the 4th quarter of 2011, as we anticipate the network start-up. b) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form c) This type of project in Broadband infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method used for the original baseline analysis does not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. We will comply with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and 100% completion in the three years of the project. d) Major activities and tasks of INTECO project completed by December 2011; 1) Sites Surveys and Network Design verification and confirmation, the sites in the network were submitted to the EA process Did a RFP (request for proposal) to select entity to do Environmental Assessment (EA). Completed EA, submitted and (FONSI) received from NTIA. 2) In first two years INTECO has prepared five additional Requests for Proposal (RFP) processes, four RFPâ€™s were completed in 2011 (proposals received, evaluated and awarded, contracts established). RFP for construction of three towers will be completed in first quarter 2012. [a] RFP 1 - Construction Permits contract, submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of eight new telecommunications towers to be used by the network in underserved areas. Approval received for four sites in 2011. Work continues on three additional sites which we expect to receive in 2012. [b] RFP 2 - Site prep and construction on exiting tower Sites, For preparation of existing tower sites, construction of pads, ice bridge, electrical connection. 10 of 16 sites were completed by December 2011. Structural analysis has been requested from all existing sites to latest code requirement; negotiation of improvements to existing towers has been completed and is in process. Example, one of our key vendors is Crown Castle which has 9 of the existing towers in the network and they have completed all structural analysis and we have negotiated updated terms. [c] RFP 3 - Telecommunications Equipment, For all telecommunication equipment, microwave backbone- point to point radios, Wi Max - point to multipoint radios, switches, cables, antennas, spares, installation and commissioning. RFP was evaluated, vendor selected and equipment was ordered. All equipment for this RFP to be received and installed in 15 sites by March 2012 with three more sites installed by June 2012. [d] RFP 4 - Central Office Equipment for Network, All central office gear, servers, routers, switches, firewall, security, network operations management, HVAC, UPS, ect. Proposals were evaluated and vendor selected, contract negotiations completed in 2011. All equipment to be installed in the first quarter of 2012. [e] RFP 5 â€“ Tower Construction for three new locations, Site preparation, construction and installation of foundation in three telecommunication towers in first two years. Published and meetings held in 2011, evaluation and vendor to selected in Jan 2012. The three towers are one 200 ft. self-sustaining tower, and two 150 ft. mono pods The three towers will be installed in the first two quarters of 2012. 3) The FCC frequencies for the projectâ€™s backbone have been secured. All the frequencies for the point to point microwave backbone, are reserved by the FCC in INTECOâ€™s name. All frequencies required in the Backbone in 6 and 11GHz and have completed the Client Approval Notification (CAN). 4) The 2.5 spectrum for Wi Max transmission is reserved by contract agreement 5) The lease agreements for sixteen existing towers will be completed by 1st quarter 2012; we have 13 signed, three in process. 6) The land- lease agreements for eight new tower sites will be completed by 1st quarter of 2012, we have 6 signed, two in process. 7) The Command Center (NOC) of the network and its data center will be completed by 1st quarter 2012. 8) Evaluation of personnel needed to adequately manage the project was completed and Engineering resources were added to the project. In 2011, we added, an engineer to do tower site construction inspections and a Network Engineering Manager. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have completed an interconnection agreement with a key ISP supplier on the island and have a wholesale agreement completed with another supplier in order to provide Broadband Service connection. Although the network is in construction, we have a target of activating two major quadrants by late summer 2012, ahead of the grant schedule. We are establishing agreements beforehand in order to be able to provide service to key municipalities and CAI's once we active the BTOP network. | We agreed to acquire transit agreements in order to provide Broadband service which may include interconnection service. Although the network is in construction, we have a target of activating two major quadrants by late summer 2012, ahead of the grant schedule. We are establishing transit agreements beforehand in order to be able to provide service to key municipalities and CAI's once we active the BTOP network. We also want to have local peering on the island through an agreement with the other BTOP project on the island. We will have the benefits of local peering to all key CAI's from the begging of the project.
NT10BIX5570033 | 2012 | 84,843 | This considers linear miles of a microwave network. | N/A | Same as baseline. | N/A | Same as baseline | 200 mbps | N/A | 9 mbps | N/A | 7.6 mbps | N/A | 5.6 mbps | N/A | 4 MBPS . Most institutions had a DLS Service and now will be provided by Broadband Service | Retail services to be provided is Internet connectivity, (DIA, Direct Internet Access). Point to Point and Point to Multipoint Mesh services will be provided. | Network Management Policies are being structured to comply with SLA (Service Level Agreement) standard to the Puerto Rico Market. Will be implemented at the end of Q1, 2013. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 2400 | 480 | 0 | 1920 | N/A | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB-Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we met the 67% objective in the first two years, we developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already existed (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will installed equipment in these towers and had complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center has been completed. This assured substantial completion of expenditures for the project within the two year requirement. We also constructed in these two initial quadrants, three of the eight new towers in the network. By developing the quadrant strategy and prioritizing the site preparation and tower construction, INTECO was able to achieve the objective of activating the network and the operations in the these two areas in August/September of 2012, ahead of the Grant schedule. We initiated connection for CAIâ€™s in the third quarter of 2012 in the quadrant which was activated. All at the NOC (Network Operation Center) equipment was installed and testing initiated in 2012. The network start-up was done in August/September of 2012. b) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form. As part of this survey we discovered the State Government Educational System has a procurement policy on a State-Wide basis, which eliminates regional possibility of participation. c) This type of project in Broadband Microwave infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method for the original baseline analysis did not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. We have complied with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and will achieve 100% completion of the project in three years. d) Major activities and tasks of INTECO project completed by December 2012; 1) Did sites surveys and network design verification, the sites in the network were submitted to the Environmental Assessment (EA) process . Completed EA, submitted and (FONSI) Finding of No Significant Impact received from NTIA. 2) INTECO managed six Requests for Proposal (RFP) processes. [a] RFP 1 - Construction Permits contract, submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of eight new telecommunications towers or roof-tops to be used by the network in underserved areas. All permit approvals for the sites were received by the end of 2012. [b] RFP 2 - Site preparation and equipment installation on sixteen existing tower Sites were completed by December 2012. [c] RFP 3 - Telecommunications Equipment, For all telecommunication equipment, microwave backbone- point to point radios, Wi Max - point to multipoint radios, switches, cables, antennas, spares, installation and commissioning. All equipment received and installed in 22 sites by December 2012. [d] RFP 4 - Central Office Equipment for Network, All central office gear, servers, routers, switches, firewall, security, network operations management, HVAC, UPS, etc. All equipment in central office were installed in 2012. [e] RFP 5/6 â€“ Tower Construction for four new locations, Site preparation, construction and installation of foundation of four telecommunication towers. 3) The FCC frequencies for the projectâ€™s backbone have been secured. All the frequencies for the point to point microwave backbone, are reserved by the FCC in INTECOâ€™s name. All frequencies required in the Backbone in 6 and 11GHz and have completed the Client Approval Notification (CAN). 4) The 2.5 frequencies for WiMax transmission is reserved by contract agreement 5) The lease agreements for sixteen existing tower sites and land-lease agreements for eight new tower/roof-top sites were completed in 2012. 6) The Command Center (NOC) of the network and its data center was completed in 2012. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have two interconnection / transit agreements. Inteco has entered into an interconnection agreement with Critical Hub Networks and Ednet. We have not denied any request for interconnection. | Under the interconnection agreement with Critical Hub Networks, Inteco’s network is also peered with the Puerto Rico Bridge Initiative’s Internet Exchange Point (IXP) for local IP traffic exchange.
NT10BIX5570033 | 2013 | 84,843 | This considers linear miles of a microwave network. | N/A | N/A. Project is classified as middle mile. | N/A | N/A. Project is classified as middle mile. | 300 mbps | N/A. | 9 mbps | N/A. | 7.6 mbps | N/A. | 5.6 mbps | N/A. | 4 mbps. Most institutions had a DLS Service ad now will provided by Broadband Service. | Retail services to be provided is internet connectivity. (DIA, Direct Internet Access). Point to Point and Point to Multipoint Mesh services will be provided. | Network Management Policies are being structured to comply with SLA (Service Level Agreement) standard to the Puerto Rico Market. They were implemented as of the end of the award date 07/31/2013. | 1 subscriber - 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 5800 | 1600 | 0 | 4200 | N/A. | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB-Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we met the 67% objective in the first two years, we developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already existed (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will installed equipment in these towers and had complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center has been completed. This assured substantial completion of expenditures for the project within the two year requirement. We also constructed in these two initial quadrants, three of the eight new towers in the network. By developing the quadrant strategy and prioritizing the site preparation and tower construction, INTECO was able to complete the project within time frame required. b) Lessons learned. Collection of information on regional public school broadband use There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form. As part of this survey we discovered the State Government Educational System has a procurement policy on a State-Wide basis, which eliminates regional possibility of participation. c) This type of project in Broadband Microwave infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method for the original baseline analysis did not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. Adjustents were made to complete the project on time. We have complied with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and achieved 100% completion of the project on time. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have two (2) interconnection/transit agreements. INTECO has entered into an interconnection agreement with Critical Hub Networks and Ednet. We have not denied any request for interconnection. | Under the interconnection agreement with Critical Hub Networks, INTECO's network is also peered with the Puerto Rico Bridge Initiative's Internet Exchange Point (IXP) for local IP traffic exchange.
NT10BIX5570034 | 2010 | N/A | The network is not deployed at this time. | N/A | N/A | N/A | N/A | N/A | The network is not deployed at this time. | N/A | N/A | N/A | The network is not deployed at this time. | N/A | N/A | N/A | The network is still being deployed so services utilizing this network are not being provided at this time. DeltaCom is creating competitive middle mile pricing that enables connectivity for last mile provider networks. Additionally, DeltaCom will utilize last mile providers to enable direct DeltaCom services to public anchor institutions in select markets at a 20% discount below our list pricing for qualifying broadband services. | The network management policies for this specific project are being reviewed and will be ready prior to the launch of the network.DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to evaluate | N/A | 5668 | 0 | 0 | 3570 | 175 | 0 | 1923 | N/A | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices defined as interconnection points in DeltaCom's award application. | No subcontracts or sub grants have been made. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | N/A | N/A
NT10BIX5570034 | 2011 | $3,911 | This number was calculated based on Construction funds expended and the number of miles deployed as of December 31, 2011. This number is different from the Baseline because it does not include the total funds required to complete the project. | N/A | N/A | N/A | N/A | 0 | Not applicable at this time. | N/A | N/A | 0 | Not applicable at this time. | N/A | N/A | Community anchor institutions are not connected to the network at this time. | Community anchor institutions are not connected to the network and services are not being provided at this time. DeltaCom will lease facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | Not applicable at this time. | 5668 | 3731 | 0 | 1773 | 14 | 0 | 150 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | [REDACTED] | [REDACTED]
NT10BIX5570034 | 2012 | $4029 | This number was calculated based on Construction funds expended and the number of miles deployed as of December 31, 2012. This number is different from the Baseline because it does not include the total funds required to complete the project. | N/A | N/A | N/A | N/A | OC-12, 100 Gig, 225 Mile | Service Offering: OC- 12 Distance Band or Point to Point: 225 Mile Distance Band Minimum Peak Load Network Bandwidth Capacity: 100 Gig | N/A | N/A | 8 Gig | This number is slightly higher than the baseline plan. | N/A | N/A | In order to respond to this question, DeltaCom surveyed the community anchor institution customers that connect to the BTOP funded network. One community anchor institution added a 50Mbps Ethernet connection for internet connectivity to their existing facilities. The other community anchor institution customer upgraded from a 4.5Mbps bonded circuit to a 10Mbps Ethernet connection. | DeltaCom leases facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. Currently one customer is utilizing a 50Mbps Ethernet connection and another community anchor institution customer is utilizing a 10Mbps Ethernet connection. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | No customers have dropped the broadband service provided through this project. | 5668 | 3745 | 0 | 1923 | 0 | 0 | 0 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | [REDACTED] | [REDACTED]
NT10BIX5570034 | 2013 | 3,659.83 | This number was calculated based on Construction funds expended and the number of miles deployed as of May 1, 2013. This number is different from the Baseline because it does not include the total funds required to complete the project. Additional decrease from the 2012 APPR is the result of a return of funs to ASAP for expenditures not covered by the grant. | N/A | N/A | N/A | N/A | OC-12, 100 Gig, 225 Mile | Service Offering: OC- 12 Distance Band or Point to Point: 225 Mile Distance Band Minimum Peak Load Network Bandwidth Capacity: 100 Gig | N/A | N/A | 8 Gig | This number is slightly higher than the baseline plan. | N/A | N/A | In order to respond to this question, DeltaCom surveyed the community anchor institution customers that connect to the BTOP funded network. One community anchor institution added a 50Mbps Ethernet connection for internet connectivity to their existing facilities. The other community anchor institution customer upgraded from a 4.5Mbps bonded circuit to a 10Mbps Ethernet connection. | DeltaCom leases facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. Currently one customer is utilizing a 50Mbps Ethernet connection and another community anchor institution customer is utilizing a 10Mbps Ethernet connection. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | No customers have dropped the broadband service provided through this project. | 5668 | 3745 | 0 | 1923 | 0 | 0 | 0 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | DeltaCom has not entered into any interconnection agreements at this time. DeltaCom is not currently negotiation any interconnection agreements at this time and DeltaCom has not denied any requests for interconnection on the BTOP funded network. | DeltaCom has entered into eight transit/transport interconnection agreement utilizing the BTOP funded network. These agreements include one agreement with Sunset Digital Communications, and one agreement with Morristown Utilities Commission, five agreements with Dukenet Communications, and one agreement with Twin Lakes Telephone Cooperative. DeltaCom has not denied any requests for peering or transit agreements.
NT10BIX5570035 | 2010 | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | 0 | Middle Mile only | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | Middle Mile network only. | Hardy Telecommunications does not limit bandwidth or prioritize traffic. Hardy has never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | 13667 | 13113 | 0 | 554 | 12144 | 0 | 554 | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | 180 | 160 | 0 | 20 | Collocation space will be provided. Facilities deployment not yet started. | No subcontracts or sub grants to SDBs to date. | Communicate well and often with NTIA staff and project team. Keep detailed, contemporaneous project records. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | No interconnection agreements. Network deployment not yet completed. | No peering and transit agreements.
NT10BIX5570035 | 2011 | $19,217.18 | (44.8%) Variance is due to difference in basis of calculation of Baseline Plan indicator compared to APR-2011 guidance. Baseline indicator was calculated based on total project costs, including equipment, professional services, and operational support systems. APR-2011 indicator guidance is to base calculation on labor and materials costs only of new middle mile network deployed. | 0 | NA | 0 | NA | 0 | Basline Plan Indicator is 1-Gbps. Speed tiers associated with service plans for purchase have not yet been advertised -- deployment of backbone ring still in process. New construction of CAI laterals and drops not yet started. Delays due to section 106 review process requiring Phase 1 survey and archaeological shovel testing. Hardy has conducted marketing and outreach in newspaper stories, company website and company newsletter. The following is a link to Hardy's newsletter on the web with an article that can be downloaded. The newletter was published in November, 2011: http://hardynet.net/images/stories/PDfs/Hardy_November_2011_newsletter_WEB.pdf | 0 | Baseline Indicator "N/A" | 10 | Backbone ring partially complete at 12-31-2011. Spans between 8 nodes constructed as of 12-31-2011, with 10-Gbps capacity turned up between nodes. At this time dedicated ethernet transport can be offered between nodes at 10, 50 and 100 Mbps up to 1 Gbps. New construction of laterals and drops to CAIs not yet started. Network upgraded to local schools, school administration office, and three cellular towers. Seven schools sites each receiving 10-Mbps dedicated ethernet transport service. Cellular carriers considering replacement or system upgrades for upstream TDM equipment to take advantage of low-cost high capacity ethernet service. Deployment delays are due to section 106 review process requiring Phase 1 survey and archaeological shovel testing. | 0 | Baseline Indicator "N/A" | Pending backbone network completion, laterals and drops to anchor institutions, Hardy AnchorRing service is available for six schools, the school administration office, and three cellular towers. Prior to deployment, each school site received T1 transmission service at 1.544 Mbps second. Currently school sites are each receiving 10 Mbps transport service, for a capacity increase of approximately 548% over T1 service. Service is available to the schools up to 1 Gbps per site, an increase of approximately 66,221% over T1 service. Cellular carriers could obtain only T1 service to three tower sites. Two towers are served with two T1 lines each, or 3.088 Mbps per tower, and one tower is served one T1 line at 1.544 Mbps. Service up to 1 Gbps is now available to the towers, representing a capacity increase of approximately 33,061% or 66,221% depending upon number of T1 lines connected. | Hardy AnchorRing offers from 10 Mbps to 1 Gbps service to connected community anchor institutions. Six local schools and the school administration office currently purchase 10 Mbps service per site for a total of 70 Mbps, a capacity increase of approximately 548% over T1 service at an increase in cost of only 63.1%. On March 30, 2012 a price decrease will go into effect for the schools, which will lower the schools' total cost of service by an additional 22.8%. At that time, the schools will be receiving 548% more capacity at only a 26.3% increase in cost over T1 service. | Hardy Telecommunications does not limit or block consumers from accessing any lawful content, service, service provider or application, or prevent any consumers from attaching any legal devices to the network. Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.com/images/stories/PDfs/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | No broadband services provided through this project have been dropped or discontinued. | 15383 | 122 | 0 | 1826 | 12997 | 0 | 438 | Hardy Telecommunications has not received requests for wholesale dark fiber during the performance period. | 0 | 0 | 0 | 0 | Not yet constructed. | No contracts have been awarded to socially and economically disadvantaged small business concerns within the performance period. Hardy Telecommunications encourages qualified local small businesses of all types, including small disadvantaged, women-owned, veteran-owned, and service disabled veteran-owned small businesses, to respond to requests for proposals for construction and installation services in order to create more jobs within the local area. Hardy instructs contractors to be proactive in subcontracting to such small businesses. | NTIA's web-based guidance sessions and drop-in calls have been very helpful to Hardy's project team members; Hardy encourages other BTOP recipients to take advantage of these sessions whenever possible. Networking with other BTOP recipients has been valuable to Hardy and its project team as a way to learn about progress of other projects, delays and suggestions for avoidance or mitigation, news of emerging risks, and suggestions to speed deployment, save time, and control costs. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | Hardy Telecommunications did not receive requests for interconnection during the annual reporting period. | Hardy telecommunications did not receive requests for peering and transit agreements during the annual reporting period.
NT10BIX5570035 | 2012 | 19734.95 | (43.3%) Variance is due to basis in calculation of Basedline Indicator compared to APR-2012. Baseline indicator calculated based on total project costs including equipment, professional services, and operational support systems. APR-2012 indicator based on labor and materials costs of new middle mile network deployed. | 0 | Middle Mile | 0 | Middle Mile | 10 Gbps | Baseline Plan Indicator = 1 Gbps. Speed Tiers offered to CAIs range include 5Mbps/2Mbps, 15Mbps/7Mbps, 25Mbps/10Mbps, and other increments up to 1 Gbps bidrectional service. Wholesale service is offered from 1Gbps to 10Gbps. | 0 | Middle Mile | 18 Mbps / 8 Mbps | Average broadband speed provided to CAIs 18 Mbps upstream /8 Mbps downstream | 0 | Middle Mile | Prior to BTOP deployment of broadband infrastructure many CAIs in Hardy County could not obtain affordable or reliable broadband service. The available connection speed for many CAIs was 1.544 Mbps upstream and downstream, or T1 transmission service. In addition the existing upstream network was not diverse or redundant, and frequent outages were experienced. Hardy AnchorRing service is now available at speeds up to 1 Gbps, and the network is diverse and redundant. 18 Mbps is the average downstream service speed now being provided, with 8 Mbps upstream. This represents an average increase in bandwidth of 16.5 Mbps downstream and 6.5 Mbps upstream, or an average increase of 1066% and 418% respectfully. Hardy began serving Hardy County Scho2ols and three cellular towers prior to award of BTOP funding, but was unable to provide for diversity and redundancy. These sites have now been connected to Hardy AnchorRing and can now obtain up to 1 Gbps of affordable and reliable service. | Hardy AnchorRing is a Middle Mile network. Hardy Telecommunications was also awarded a Broadband Initiatives Program loan/grant award from the Rural Utilities Service of the U.S. Department of Agriculture to deploy Hardy OneNet. Hardy OneNet. which began construction in 2011, is a Fiber-to-the-Premise Last Mile network serving underserved areas of Hardy County. Hardy OneNet leverages the BTOP Middle Mile Backbone Ring and upstream connection to the Global Internet to lower costs and speed deployment to homes and businesses, especially small businesses. | Hardy Telecommunications does not limit or block consumers from accessing any lawful content, service, service provider or application, or prevent any consumers from attaching any legal devices to the network. Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.net/wp-content/uploads/2012/09/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | No subscribers have dropped Hardy AnchorRing service. | 14701 | 2821 | 0 | 11880 | 0 | 0 | 0 | No wholesale fiber leases at this time. | 0 | 0 | 0 | 0 | Customers may connect with Hardy AnchorRing at Hardy Telecommunications' central offices. | No contracts have been awarded to socially and economically disadvantaged small business concerns within the performance period. Hardy Telecommunications encourages qualified local small businesses of all types, including small disadvantaged, women-owned, veteran-owned, and service disabled veteran-owned small businesses to respond to requests for proposals for construction and installation services in order to create more jobs within the local area. Hardy instructs contractors to be proactive in subcontracting to small local businesses and hiring qualified local employees. | Early communication of issues or questions to the Federal Program Officer and Grants Management Officer is key. Hardy's Program and Grants Management Officers have been proactive and responsive in tracking down information and following up. NTIA's web-based guidance sessions and drop-in calls have been very helpful to Hardy's project team. Networking with other BTOP recipients at events hosted by NTIA and other public and nonprofit institutions has been valuable to Hardy and its project team as a way to learn about progress of other projects, delays and suggestions for avoidance or mitigation, news of emerging opportunities or risks, and potential opportunities for interconnection and collaboration. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | No Interconnection requests received or denied. | No peering agreements requested to date. 155-Mbps wholesale transport service was requested and is being provided to a wholesale interexchange carrier for connection to the carrier's cellular customer site. Higher capacity can improved cellular coverage in the area. No additional transport agreements have been requested to date.
NT10BIX5570035 | 2013 | 19734.95 | (43.3%) Variance is due to basis in calculation of Basedline Indicator compared to APR-2012. Baseline indicator calculated based on total project costs including equipment, professional services, and operational support systems. APR-2012 indicator based on labor and materials costs of new middle mile network deployed. | 0 | Middle Mile | 0 | Middle Mile | 0 | Baseline Plan Indicator = 1Gbps. Speed tiers offered from 10Mbps to 1Gbps. | 0 | Middle Mile | 0 | 18 Mbps upstream, 8 Mbps downstream | 0 | Middle Mile | Prior to BTOP deployment of broadband infrastructure many CAIs in Hardy County could not obtain affordable or reliable broadband service. The available connection speed for many CAIs was 1.544 Mbps upstream and downstream, or T1 transmission service. In addition the existing upstream network was not diverse or redundant, and frequent outages were experienced. Hardy AnchorRing service is now available at speeds up to 1 Gbps, and the network is diverse and redundant. 18 Mbps is the average downstream service speed now being provided, with 8 Mbps upstream. This represents an average increase in bandwidth of 16.5 Mbps downstream and 6.5 Mbps upstream, or an average increase of 1066% and 418% respectfully. Hardy began serving Hardy County Scho2ols and three cellular towers prior to award of BTOP funding, but was unable to provide for diversity and redundancy. These sites have now been connected to Hardy AnchorRing and can now obtain up to 1 Gbps of affordable and reliable service. | Hardy AnchorRing is a Middle Mile network. Hardy Telecommunications was also awarded a Broadband Initiatives Program loan/grant award from the Rural Utilities Service of the U.S. Department of Agriculture to deploy Hardy OneNet. Hardy OneNet. which began construction in 2011, is a Fiber-to-the-Premise Last Mile network serving underserved areas of Hardy County. Hardy OneNet leverages the BTOP Middle Mile Backbone Ring and upstream connection to the Global Internet to lower costs and speed deployment to homes and businesses, especially small businesses. | Hardy Telecommunications does not limit or block consumers from accessing any lawful content, service, service provider or application, or prevent any consumers from attaching any legal devices to the network. Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.net/wp-content/uploads/2012/09/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | No subscribers have dropped HardyAnchorRing service. | 14701 | 2821 | 0 | 11880 | 0 | 0 | 0 | No wholesale fiber leases at this time | 0 | 0 | 0 | 0 | Customers may interconnect with the HardyAnchorRing at Hardy central office facilities. | No contracts have been awarded to socially and economically disadvantaged small business concerns within the performance period. Hardy Telecommunications encourages qualified local small businesses of all types, including small disadvantaged, women-owned, veteran-owned, and service disabled veteran-owned small businesses to respond to requests for proposals for construction and installation services in order to create more jobs within the local area. Hardy instructs contractors to be proactive in subcontracting to small local businesses and hiring qualified local employees. | Early communication of issues or questions to the Federal Program Officer and Grants Management Officer is key. Hardy's Program and Grants Management Officers have been proactive and responsive in tracking down information and following up. NTIA's web-based guidance sessions and drop-in calls have been very helpful to Hardy's project team. Networking with other BTOP recipients at events hosted by NTIA and other public and nonprofit institutions has been valuable to Hardy and its project team as a way to learn about progress of other projects, delays and suggestions for avoidance or mitigation, news of emerging opportunities or risks, and potential opportunities for interconnection and collaboration.. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | No Interconnection requests received or denied. | No peering agreements requested to date. 155-Mbps wholesale transport service was requested and is being provided to a wholesale interexchange carrier for connection to the carrier's cellular customer site. Higher capacity can improved cellular coverage in the area. No additional transport agreements have been requested to date.
NT10BIX5570036 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3) N/A | N/A
NT10BIX5570036 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A
NT10BIX5570036 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570036 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50Mb - 10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570037 | 2010 | $53132.00 | Phase I Fiber Bid $1,275,169.44 - 23.72 Conduit miles, 26.10 cable miles | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | Construction Started December 13, 2010 | Construction Started December 13, 2010 | Construction Started December 13, 2010 | Construction Started December 13, 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction Started December 13, 2010 | 0 | 0 | 0 | 0 | Construction Started December 13, 2010 | None at this time | During the Environmental Assessment, pre-qualify contractors and stake the routes. This process will speed the construction process. Created Twitter account @cccbu and as of December 2010 have 500+ users following the progress of our stimulus project. Created Facebook page Columbia County Community Broadband Utility to communicate project milestones and present pictures and videos pertaining to project. Utilizing RSS feeds and text updates to inform citizens about the status of our project. Created an article introducing our project and included it in our local Water Utility direct mail insert, which on average, reaches 44,000 households. Setup Website to communicate project milestones and vendors to register to receive project updates. Evaluate outside and inside plant materials (quality, cost, etc.) before issuing construction bids. Standardize and Include materials evaluated including the cost received from suppliers in the construction bids. This will lower your overall material cost including material management cost. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A
NT10BIX5570037 | 2011 | 55,193 | Cost based on fiver awarded construction contracts. | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | 42836 | 0 | 0 | 0 | 0 | 0 | 42836 | Fiber plant under construction. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A
NT10BIX5570037 | 2012 | 55,193 | Cost based on five awarded construction contracts. | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | CAI's Speeds ~ Upgraded Avg Old Avg New Avg Increase Speed Service Speed Speed <10Mb >=10Mb and <50Mb 12 .5Mb 10Mb 20 times 240 >=50Mb and <100Mb 6 1.5Mb 50Mb 33.33 times 200 >=100Mb and < 1Gb 7 5Mb ~ 100Mb 20 times 140 >=1Gb 41 10Mb ~ 1000Mb 100 times 4100 Total upgraded connections 66 70.909 4680/66 upgraded service Upgraded 66 CAI's with and an average increase of 71 times faster service | Price structure waiting approval of Board of Commissioners. | Columbia County will manage the network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently Columbia County does not discriminate or favor any lawful Internet applications, content, or services where lawfully used. Columbia County will promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. Columbia County follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. Columbia county uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None at this time | 42294 | 4838 | 0 | 37456 | 0 | 0 | 0 | Once Board of Commissioners approve rate structure, Columbia County will be actively marketing the lease of fiber. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A
NT10BIX5570037 | 2013 | 55,193 | Cost based on five awarded construction contracts. | 0 | N/A | 0 | N/A | 1Gig | No Change | 0 | N/A | 500Mb | No change | 0 | N/A | CAI's Speeds ~ Upgraded Avg Old Avg New Avg Increase Speed Service Speed Speed <10Mb >=10Mb and <50Mb 12 .5Mb 10Mb 20 times 240 >=50Mb and <100Mb 6 1.5Mb 50Mb 33.33 times 200 >=100Mb and < 1Gb 7 5Mb ~ 100Mb 20 times 140 >=1Gb 41 10Mb ~ 1000Mb 100 times 4100 Total upgraded connections 66 70.909 4680/66 upgraded service Upgraded 66 CAI's with and an average increase of 71 times faster service | Our plan is to connect CAIs and provide wholesale services. Rate plan attached. | Columbia County will manage the network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently Columbia County does not discriminate or favor any lawful Internet applications, content, or services where lawfully used. Columbia County will promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. Columbia County follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. Columbia county uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None at this time | 42294 | 4838 | 0 | 37456 | 0 | 0 | 0 | Columbia County Board of Commissioners approved a rate plan on January 15,2013. Columbia County is actively marketing the lease of fiber. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A
NT10BIX5570038 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) 2 interconnection agreements (3) N/A | N/A
NT10BIX5570038 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A
NT10BIX5570038 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570038 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50Mb-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570039 | 2010 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The negotiation of all contracts associated with your project will take longer and cost more than you anticipate. Use a very competent law firm with multiple in house disciplines to provide aid in this regard. Where possible, include drafts of your anticipated contracts in RFPs for respondents to mark up with concerns and issues that can then be discussed in interviews. Meet with pole and conduit owners early and often and aggressively pursue all master agreements and organize with them to ensure the fastest possible response to license applications for pole attachments and conduit access, and the performance of make ready. Request that they look at your project outside the box of normal procedure so that innovative methods can be used to expedite the project. They will not alter long established procedures or ignore collective bargaining agreements, but will work with you to devise methods to move things more quickly. An example would be the use of a single detailed field survey acceptable to all parties for assessment of make ready needs. Contract for field survey, licensing and permitting, and engineering services early. Chose a competent company with experience within your region and a good reputation with utility companies. Start this activity as soon as possible as it can aid in all other contract development and decision-making about path. Select a very capable engineering company to prepare your Environmental Assessment as early as possible. Ensure they have in-house capability or a partnership relationship with a cultural and historical survey firm. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | N/A
NT10BIX5570039 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The negotiation of all contracts associated with your project will take longer and cost more than you anticipate. Use a very competent law firm with multiple in house disciplines to provide aid in this regard. Where possible, include drafts of your anticipated contracts in RFPs for respondents to mark up with concerns and issues that can then be discussed in interviews. Meet with pole and conduit owners early and often and aggressively pursue all master agreements and organize with them to ensure the fastest possible response to license applications for pole attachments and conduit access, and the performance of make ready. Request that they look at your project outside the box of normal procedure so that innovative methods can be used to expedite the project. They will not alter long established procedures or ignore collective bargaining agreements, but will work with you to devise methods to move things more quickly. An example would be the use of a single detailed field survey acceptable to all parties for assessment of make ready needs. Contract for field survey, licensing and permitting, and engineering services early. Chose a competent company with experience within your region and a good reputation with utility companies. Start this activity as soon as possible as it can aid in all other contract development and decision-making about path. Select a very capable engineering company to prepare your Environmental Assessment as early as possible. Ensure they have in-house capability or a partnership relationship with a cultural and historical survey firm. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | N/A
NT10BIX5570039 | 2012 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A. Though CAIs are connected, services is not yet offered on the network. | N/A | N/A. Network management policies are under development. | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | Owned colocation space is still under construction. Other providers/customers may interconnect with the network at 10 leased colocation or central office facilities, and one microwave location. Customers may also connect into the network with new fiber laterals at multiple points around the fiber network where splice points and slack loops are located. | N/A | Specificity in contracts is always desirable, but as time passes since initial contacts were signed projects mature and evolve. This is especially true when key personnel change from time to time. Conducting an annual review of all major contracts is important to refresh what the contracts actually say versus what day to day practice may be. Such a review must be done with the perspective of as if one is reading them for the first time. In conjunction with such a contract review, also note all of the future obligations of the company for such things as equipment list updates to tower owners or permitting jurisdictions, lease renewals, etc. Creating the ongoing operational action list is critical in a new company especially. With no history to follow, items in underlying rights that need to be updated on regular intervals won't be lost, especially in situations where key people with institutional memory are lost over time. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | OpenCape effectively entered into one transit agreement during this reporting period by virtue of an IRU with OSHEAN, Inc. No other peering and transit agreements are being negotiated.
NT10BIX5570039 | 2013 | $54,739 | Costs per mile are as expected in the baseline plan, and consistent with other BTOP projects in the state. | 0 | N/A, middle mile project | 0 | N/A, middle mile project | 1000 | Speeds up to 1 Gbps are available on the network | 0 | N/A, middle mile project | 200 | Average speed of network customers today is approximately 100 Mbps. Speeds of customers range from 10 Mbps to 2.5 Gbps. Average speeds depend on what customers need for their application and are not limited by the network. Once the Barnstable County RFP evaluation is completed, average speeds should increase considerably. | 0 | N/A | Average broadband speed increases at CAIs has been moderate to date. Most CAIs acquiring service on the network are replacing existing connectivity and making only moderate increases of around 20% in speed. The Barnstable County RFP process has delayed connecting more CAIs at the higher speeds of shared 1 Gbps service rings (a total of 14 Gbps on net capacity that will be reserved for 63 of the Cape CAIs) with 1 Gbps connectivity to the Internet. The connections will be shared across 14 service rings operating at 1 Gbps, shared 1 Gbps Internet, and shared 1 Gbps Internet2 connections. When service is provided through the proposal, all 63 CAIs will have a 1 Gbps connection to the network. | OpenCape only offers retail services in the collocation data center. Retail pricing is currently set at $750/rack/month, or $50/RU/month. Connectivity to the Internet is offered at $10/mbps/month. Power is charged at the rated power supply of the equipment installed. Pricing is under review based on a recent reconfiguration of the data center cooling system. | Network management practices consistent with FCC 10-201A1. As a general network practice, no bandwidth limitations are imposed on network users other than limiting traffic at the level contracted for by the end user. No traffic prioritization methods are in place. No lawful content is blocked on the network, nor access to any service, service provider, or application. Firewall services have been requested in the Barnstable County RFP and will be applied, including any content blocking, as desired by the end network user (for example, educational institutions). | No users have dropped service provided through this project. | 44000 | 9000 | 0 | 35000 | 9000 | 0 | 35000 | N/A. OpenCape does not wholesale dark fiber. | 2500 | 100 | 0 | 2400 | Network provider can interconnect with the network at any of the 12 points of presence maintained by OpenCape. Eight of these location are ILEC central office locations. One is a CLEC collocation facility. One is a private facility with limited interconnection facilities, but one carrier plans on interconnecting with the network at that point. The remaining facility is the OpenCape collocation center. Network providers or customers may also connect at any of the 11 microwave sites that are active in the network, provided they can obtain physical access rights from the facility owners. All sites are connected to the fiber optic network. Customers can connect at any convenient point in the network where splice points exist. Laterals would be run from these splice points to the customer location. There are slack loops and existing splice locations throughout the network to facilitate customer connections. | N/A | Local permitting cannot be started too early. An understanding of the local permitting processes is critical, but always takes longer than one expects. For ongoing operations, it is also important to maintain an updated financial model. As real costs are determined as compared to what was modeled years ago, the operational plan should continue to be updated to understand the financial aspects of the business post-grant. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | No interconnection agreements were entered into by OpenCape during the period. CapeNet, the OpenCape network operator, has entered into one interconnection agreement during this period. On additional interconnection agreements are planned at this time. | OpenCape has not entered into any additional transit agreements during this annual reporting period, and maintains a single interconnection agreement. No other peering and transit agreements are being negotiated by OpenCape. Transit agreements may be negotiated and added by the OpenCape network operator, CapeNet. No interconnection requests have been denied to either CapeNet or OpenCape.
NT10BIX5570040 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3) N/A | N/A
NT10BIX5570040 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570040 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570040 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570041 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) N/A (3) N/A | N/A
NT10BIX5570041 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 2 interconnection agreement (3)N/A | N/A
NT10BIX5570041 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570041 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570042 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) N/A (3) N/A | N/A
NT10BIX5570042 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A
NT10BIX5570042 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570042 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570043 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually <1 mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) N/A (3) N/A | N/A
NT10BIX5570043 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570043 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570043 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A
NT10BIX5570044 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | While we have not started delivering services yet, in our proposal and in all of our discussions with NTIA and the public we have said that we would have 10 Gbps Middle Mile connections available. | 0 | While we have not started delivering services yet, in our proposal and in all of our discussions with NTIA and the public we have said that we would have 1 Gbps Last Mile connections available. | 0 | N/A - While we have no data yet, we expect the vast majority of our Middle Mile customers to have 1 Gbps connections so this numbers should be slightly more than 1 Gbps. | 0 | N/A - While we have no data yet, we expect the vast majority of our Last Mile customers to have 100 Mbps connections, so this number should be slightly more than 100 Mbps. | N/A - We have not delivered any services yet. When we do, we believe it will be a substantial increase for each Anchor Institution. We will track before and after bandwidths for each Anchor Institution, and can report the average percentages of those increases. | UC2B has not provided any retail services yet. The proposed retail services are detailed on the attached PDF file. In short, we will offer a base local symmetric Intranet connection that is as fast as the equipment will go - either 100 Mbps or 1 Gbps. In addition to that there are 5 tiers of symmetric Internet connectivity that start at $19.99 a month for a 5 Mbps Internet connection with a 100 Mbps Intranet connection and range up to $85.99 a month for a 40 Mbps Internet Connection with a 1 Gbps Intranet connection. Depending on the competitive landscape, those Internet bandwidth tiers may be adjusted upwards at the same price levels before we actually roll out services to our first service areas in the fall of 2011. Our issues with securing rights-of-way will not impact our ability to deliver services to some areas in the fall of 2011. Retail services across all eleven Census Block Groups will not be available until 2012. | We plan to provide QOS for all services that need it - such as VoIP and IPTV, but beyond that, no other prioritization of any traffic based on content, source or destination. The only bandwidth limitations will be through the tiers of Internet bandwidth that a customer subscribes to. We have not delivered any traffic yet, and therefore could not have blocked any, but we have pledged to never block any lawful content. Our management policies are on-line at: www.uc2b.net. | N/A - No customers to churn yet. | 36259 | 0 | 0 | 0 | 8379 | 5464 | 22416 | We agreed to provide dark fiber IRU's to the organizations that provided our local matching funds. The value of those IRU's determined each organization's "contribution". No lease or IRU agreements have been signed yet, but the number of proposed strand miles for each organization is in the attached PDF file. | 0 | 0 | 0 | 0 | UC2B will make 1/4th of a standard 7-foot telco rack available to each IRU holder for co-location in each of our two core nodes, so that they can co-locate equipment that connects to their fiber strands on our seven rings. We will have in excess of 350 splice points on our rings throughout the community, and any provider/customer will be able to diversely connect to our core network architecture from any of those ring spice points. The rings eliminate the need for any large central co-location facility. | We have made no sub-awards at this time. We plan to make two sub awards - one to the City of Urbana and one to the City of Champaign that will cover the costs of the backbone rings and fiber-to-the-curb construction in their respective communities. Each city will hire the contractors that will be working in that city on the UC2B project. No direct subcontracts or grants to SDB's are anticipated, but we fully expect SDB's to participate as primary or sub contractors on our fiber construction. The two cities have agreed to adopt the University's goal of 15% Minority and Female Business Enterprise (MAFBE) participation on this construction. | Lesson # 1: It is never too early to understand all of your easement challenges. While more than 90% of our project is within the city boundaries of Urbana and Champaign, some of our proposed backbone fiber routes extend beyond those cities' limits. In those unincorporated areas, it is not uncommon for a property owner to own the right-of-way all the way to the center of the road. Often the same applies to the other side of the road. To legally install underground fiber in the right-of-way along that road requires an easement from one or the other property owners. Each of our participating cities has its own easement negotiation process and the Federal government has a required process that must be followed as well for federally funded projects. None of those processes are are designed to be completed within the short time periods that are required by the BTOP grants. Our engineering firm will be creating construction bid documents based on a contracted, "easement-free" design, that only builds on city-owned right-of-way. Then we will have several alternates in those bid documents that can be activated if we are able to negotiate the private easements. From the perspective of public safety and economic development, the full design that requires the private easements is a preferable design, but if the acquisition of easements can not be completed in the time available, we will be forced to build the less desirable design. Lesson # 2: Communicate early and often and then again. We have a diverse group of people working toward the same goals on this project. Given the differing backgrounds, levels of understanding, experience, time, etc, it's a challenge to maintain an open, relevant dialog. UC2B is comprised of a major research University, and two cities that formed the Urbana-Champaign Big Broadband (UC2B) intergovernmental consortium. The University and the cities appointed the members of the UC2B Policy Board to represent their interests on the project. The Policy Board members appointed the members of the UC2B Technical Committee to advise them on technical issues. At any one time it is fair to say that not every Policy Board member nor every Technical Committee member fully understands every detail of the project. These are volunteer positions and often the people appointed to fill them already had over-subscribed professional and personal lives before they became involved with UC2B. There need to be recurring regular communications with these committee members to keep them on the same page. This is further complicated by the fact that there are elected and appointed officials in both cities as well as University administrators who also want to be in the loop. This project would benefit from someone working full-time just to keep all of these stakeholders informed, because out of necessity this project is moving at the speed of light (no pun intended), while cities and universities are more accustomed to and more comfortable with a more considered pace. Keeping stakeholders informed is made more complicated by by the Illinois Open Meetings Act, which pretty much outlaws discussions between UC2B committee members outside of pubic meetings. If there is a silver bullet for communications, we have not found it yet. The staff managing the grant is typically so busy with the day-to-day activities and planning that must be done to remain on schedule that there is little time or energy left over to tell people what they are doing. We did not budget for a "communications officer", but if there ever is a BTOP2 opportunity, that would be money well spent for any project. We do have a marketing and outreach subcommittee and they are doing a good job of planning for communications with the community about the value of Big Broadband and why families and business should subscribe, but probably nothing short of hiring someone whose primary responsibility is to communicate to our administrative stakeholders for the next two years will provide the level of information within the time frames that are desired. In the meanwhile those of us managing the grant must tell our story early and often and not worry about repeating ourselves. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | N/A | N/A
NT10BIX5570044 | 2011 | 0 | We have not yet completed any of our middle mile fiber rings or laterals. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. | 0 | We have not yet passed any of our FTTP households with fiber. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. While this is not a metric that NTIA tracks, we have passed 1,613 households with conduit, which is roughly one third of the total in our Fiber-to-the-Premise (FTTP) service areas. | 0 | We have not yet completed any of our FTTP installations. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. | 10 Gbps | We will be able to deliver 10 Gbps (or partial 10 Gbps on a 10 Gbps link) ringed connections to major Anchor Institutions or businesses if they so desire. | 1 Gbps | All of our last mile FTTP customers will have a 1 Gbps connection to our local UC2B Intranet. Their Internet connectivity will be sold in tiers, starting with a 20 Mbps symmetric Internet connection and going up from there. | 20 Mbps | We expect almost all of our middle mile Anchor Institution customers to have a 20 Mbps Internet connection. (1 Gbps to the local Intranet.) A few will have larger Internet connections, but not enough to impact the average. | 20 Mbps | We expect almost all of our last-mile FTTP customers to have 20 Mbps Internet connections. (1 Gbps to the local Intranet.) A few will have larger connections, but not enough to raise the average. | We have not begun services to Anchor Institutions yet, but when we do, the minimum Internet speed available from UC2B will be a 20 Mbps symmetric service. That will be typically 2-10 times faster than what they receive today via DSL or cable modem. | UC2B does not provide any retail services yet. They will start in the 2nd quarter of 2012. We have attached our planned suite of retail services, but please also know that we are in the midst of a review of our pricing models and there is a good chance that we may make some adjustments in the weeks to come. We do know for sure that we will offer the 20 Mbps symmetric service to FTTP residential customers for $19.99 a month. We are looking at perhaps breaking out non-profits and government entities as well as for profit businesses and having different rate scales for each. We are also seeking to monetize a ringed, high-availability service that our equipment will allow us to provide. The UC2B Policy Board has hired a municipal broadband consultant (with non-grant funds) for this final business plan and service offering review. The consultant's report is due on February 15th. We expect the Board to act quickly on the recommendations, and finalize the remaining service offerings. | We have yet to offer any service and therefore have not been in a position to block anything. However, we have no plans to limit bandwidth utilization beyond the Internet rate limiting that is built into the tiers of service. We may implement Quality of Service (QOS)on some or all VLANS, but that by itself will not discriminate against any single user or class of users. | N/A | 24963 | 0 | 0 | 0 | 6256 | 5706 | 13001 | UC2B has not executed any IRU agreements yet, but we have letters of intent for IRU's from the following: City of Champaign - 637 strand miles, City of Urbana - 496 strand miles, University of Illinois - 900 strand miles, Unit 4 Schools - 290 strand miles, District 116 Schools - 164 strand miles, Champaign County - 252 strand miles, C-U Mass Transit District - 453 strand miles, Champaign Telephone Company - 453 strand miles, State of Illinois/ICN - 764 strand miles, State of Illinois/IDOT - 453 strand miles. Recently we entered into discussions with the Illinois Rural Health Network for 584 strand miles. | 850 | 754 | 0 | 96 | UC2B will be leasing space from the University in two UIUC Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our Dark Fiber customers. In order to have as redundant a system as possible, our Dark Fiber customers will need to locate a small router that can terminate the fiber coming from the 7 rings in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer. Beyond that, UC2B is not offering any collocation space. Instead, we are including diverse fiber transport on any of our seven rings as part of our service provider packages. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that will contain splice cases, they can connect redundantly to the UC2B network core and distribute their services. Additionally, service providers will be able to connect to UC2B in three University telecommunications nodes, where many of them already have facilities today. AT&T has a presence in all three nodes. Windstream and Champaign Telephone have presences in two of the nodes. ICN, Comcast, Pavlov Media and Volo Broadband have a presence in one of the nodes. There is also a group of private firms that is looking at constructing a data center / carrier hotel that will have dual connections to several of the UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our seven ring design reduces the need for co-location and decentralizes service provider hardware. | UC2B has only made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. The City of Urbana hired a prime contractor for the fiber construction in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They are: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). The City of Champaign's prime contractor for the fiber construction in Champaign hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. | This will not apply to all projects, but sub-awarding the construction with will happen in Champaign to the City of Champaign and sub-awarding the construction that will happen in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors report directly to the Public Works departments of each city, there is great communication between each contractor and its employing city, and issues are resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | N/A We have no completed interconnection agreements at this time. UC2B has always intended to interconnect with local providers and has published rates for doing so in our BTOP application. We are currently reviewing those rates one last time before we seek interconnection agreements. | N/A We have no completed peering or transit agreements at this time. We have started discussions with the University of Illinois about peering with the University and their local caching services such as Akamai. We have started discussions about peering with the Illinois Century Network. We are strong proponents of local peering, and certainly have not denied any request to peer, nor do we anticipate ever denying a request to peer. Our core network design has always included local peering connections. UC2B will be purchasing Internet transit in Chicago.
NT10BIX5570044 | 2012 | $59,690 | This is substantially less than the $135,808 in our baseline plan, but there are several months of contractors' invoices that have not hit NTIA's books yet. This average will go up as those are processed. | $1,744 | This is slightly less than the $1,750 in our baseline plan. When the outstanding invoices are processed, this too will rise. | $11,008 | This is substantially more than the $4,062 in our baseline plan. As we connect more customers n the Fiber-to-the-Premise areas, this average will decrease. This reflects the high cost of getting the infrastructure up and down every street. At this point we are at less than one third of our customer projections, so this number will be high. | 10 Gbps | We offer up to 10 Gbps ports on layer-two services. | 200 Mbps | Our fastest retail service is 200 Mbps. | N/A | We have no existing Middle-Mile customers. Even though we are connecting some Anchor Institutions to our Middle-Mile fiber, we are treating them like Last-Mile customers. | 22.5 Mbps | This is the weighted average of the bandwidths subscribed to by all of our Last-Mile customers. Our network delivers its advertised speeds. | While we do not have exact data, we know that most of our CAIs have converted to UC2B from either a T-1, DSL or cable-modem connection. The fastest of those can offer speeds as fast as the slowest UC2B fiber tier on downloads, but those technologies are far slower on uploads. UC2B's download speeds at our slowest bandwidth could range from "equivalent" to 13 times faster. UC2B's upload speeds at our slowest bandwidth would be 20-40 times faster than either T-1, DSL or cable modems. | UC2B customers can self-self to subscribe to Consumer or Commercial tiers of services. The Commercial tiers provide more IPv4 public IP addresses and have greater bandwidth tiers. All UC2B customers have unlimited bandwidth to the UC2B Intranet, but have tiers of connectivity to the Internet. The customer CPE can deliver close to 900 Mbps to the Intranet. Consumer Internet connectivity is sold in 20, 30 and 40 Mbps tiers. 82.5% of our Consumer customers have elected a 20 Mbps symmetric connection. 10.3% have elected a 30 Mbps symmetric connection. 7.2% have elected a 40 Mbps symmetric connection. We have three subscribers who have chosen our Commercial services, two have 20 Mbps and one has 100 Mbps. UC2B's retail pricing plans are attached. | The only rate limiting done by UC2B is to enforce the tiers of Internet connectivity that a customer has subscribed to. We have never blocked any customer's access to any content or service, not do we ever intend to. We have had to remove customers from the network for failing to comply in a timely fashion with lawful requests to remove copyrighted content from their computers and cease sharing it. | We have lost 24 installed retail customers thus far out of a total customer base of 811 . That would give us a churn rate thus far of just less than 3%. Typically they have either been unsatisfied with their installation experience or the limited technical support UC2B has been able to provide them for customer owned equipment. We will be rebidding our Fiber-to-the-Premise (FTTP) construction to address the unacceptable installation experiences. Our monthly service rates are quite low, and allow us to be able to make sure the network is working, but do not allow us to be able to make sure that every device owned by a customer will always work on a UC2B connection. We understand that is a need, but it is not one that we can currently fill. | 24963 | 8611 | 897 | 15455 | 0 | 0 | 0 | We have two IRU agreements with Big Broadband Services. They total 897 strand miles. We are in negotiations for more IRUs, but those IRUs were not complete at the end of 2012. | 850 | 754 | 48 | 48 | UC2B is leasing space from the University in two of its Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our Dark Fiber customers. In order to have as redundant a system as possible, our Dark Fiber customers will need to locate a small router that can terminate the fiber coming from the 7 rings in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer's router. Beyond that, UC2B is not offering any collocation space. Service providers will be able to connect to UC2B in three of the University's telecommunications nodes, where many of them already have facilities today. AT&T and Champaign Telephone Company have presences in all three nodes. Windstream, US Signal and Metro Communications have presences in two of the nodes. The Illinois Century Network, Comcast, Pavlov Media and Volo Broadband have a presence in one of the nodes. We are also providing diverse fiber transport on any of our seven rings for service providers without facilities in the UIUC Nodes. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that contain splice cases, they can connect redundantly to the UC2B network core and distribute their services. A local provider is planning to build a data center / carrier hotel in the spring that will have dual connections to four of the seven main UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our cotangent seven ring design reduces the need for co-location in our facilities and decentralizes service provider hardware. | UC2B has made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. Urbana hired a prime contractor for the phase one fiber construction (all fiber in rights-of-way) in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They are: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). Champaign's prime contractor for the phase one fiber construction hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. Through their sub-award, City of Champaign handled the contracting for all the phase two construction (fiber from the curbs to the buildings) and hired PowerUp an MBE firm as the prime contractor. PowerUp also engaged Southern Belle Electric and HVAC (MBE) as a sub-contractor. | This will not apply to all projects, but sub-awarding the right-of-way construction with will happen in Champaign to the City of Champaign and sub-awarding the construction that will happen in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors report directly to the Public Works departments of each city, there is great communication between each contractor and its employing city, and issues are resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | We have not yet entered into any interconnection agreements, because we have not yet officially accepted our ring fiber from our contractors. We have not denied any requests, but we have not acted on any either. Once the fiber has been fully tested and accepted, we will move forward with the two informal interconnection requests that we have received. | UC2B has one peering arrangement - with the University of Illinois, but it is not a formal agreement. As the University is one of the three members of the UC2B Intergovernmental Consortium, we have not gone through the process of creating a formal agreement. Our legal team's time is scarce and there have been more pressing contractual things for them to work on. We have no other peering arrangements pending.
NT10BIX5570044 | 2013 | $107,253.84 | This is substantially less than the $135,808 in our baseline plan. We had originally specified larger fiber cables and a spare conduit on the rings. Those elements were changed to reduce costs. | $1,616.44 | This is slightly less than the $1,750 in our baseline plan. | $10,220.57 | This is substantially more than the $4,062 in our baseline plan. Due to issues with landlords and UC2B's lack of a TV service, our take rate was substantially less than our projections. The base cost of building the infrastructure in the FTTP areas was divided by less than half of our projected number of subscribers, which more than doubled the cost per subscriber. | 10 Gbps | We offer up to 10 Gbps ports on layer-two services. | 200 Mbps | Our fastest retail service is 200 Mbps. | N/A | We have no existing Middle-Mile customers. Even though we are connecting many Anchor Institutions to our Middle-Mile fiber, we are provisioning them with electronics and are providing services to them just them like our Last-Mile FTTP customers. | 22.45 Mbps | This is the weighted average of the bandwidths subscribed to by all of our Last-Mile customers. Our network delivers its advertised speeds, and all service levels provide symmetrical bandwidth. | While we do not have exact data, we know that most of our CAI's have converted to UC2B fiber from either a T-1, DSL or cable-modem connections. The fastest of those technologies can offer speeds as fast as the slowest UC2B fiber tier on downloads, but those technologies are far slower on uploads. UC2B's download speeds at our slowest bandwidth could range from "equivalent" to 13 times faster. UC2B's upload speeds at our slowest bandwidth would be 20-40 times faster than either T-1, DSL or cable modems. | UC2B customers can self-determine to subscribe to Consumer or Commercial tiers of services. The Commercial tiers provide access to more IPv4 public IP addresses, have greater bandwidth tiers and offer reverse DNS. All UC2B customers have unlimited bandwidth to the UC2B Intranet, but have tiers of connectivity to the Internet. The customer CPE can deliver close to 900 Mbps to the Intranet. Consumer Internet connectivity is sold in 20, 30 and 40 Mbps tiers. 87.2% of all customers have elected a 20 Mbps symmetric connection. 9.7% of all customers have elected a 30 Mbps symmetric connection. 1.5% of all customers have elected a 40 Mbps symmetric connection. Additionally we have 17 commercial customers that have subscribed to faster tiers. There are 12 at 60 Mbps symmetrical, 4 customers at 100 Mbps symmetrical and 1 customer at 200 Mbps symmetrical. UC2B's retail pricing plans are attached. | The only bandwidth limiting done by UC2B is to enforce the tier of Internet connectivity that a customer has subscribed to. We have never blocked any customer's access to any content or service, not do we ever intend to. We also do no traffic prioritization, be it based on source, content or recipient. We have not prevented any customer from attaching any legal device to the network. We have had to remove some customers from the network for failing to comply in a timely fashion with lawful requests to remove copyrighted content from their computers and cease sharing it | We have lost 64 installed retail customers thus far out of a total customer base of 1,389 . That would give us a churn rate thus far of 4.61%. The most common reason for dropping UC2B service has been when customers move. However in some instances we have been able to sell UC2B service to the new occupants of rental units that are connected to UC2B fiber. Other customers cancelling service have either been unsatisfied with their installation experience or with the limited technical support UC2B has been able to provide them for customer-owned equipment. Our monthly service rates are quite low, and allow us to be able to make sure the network is working, but they do not allow us to be able to make sure that every device owned by a customer will always work on a UC2B connection. We understand that is a need, but it is not one that we can currently fill. | 31005 | 5297 | 5277 | 20431 | 0 | 0 | 0 | UC2B wholesales dark fiber to six service providers and to five public entities. We have two IRU agreements with Big Broadband Services and recently amended one of those agreements adding strand miles. Their combined agreements now total 1,075.89 miles. We have an IRU agreement with the Central Illinois Regional Broadband Network for 69.93 strand miles. We have an IRU agreement with the State of Illinois Department of Central Management Services - Illinois Century Network (CMS/ICN) for 343.65 strand miles. We have an IRU agreement with PEG Bandwidth for 201.58 strand miles. We lease 19.39 strand miles of dark fiber on a short-term lease to Volo Broadband. We also lease 22.96 strand-miles of dark fiber on a short-term lease to Metro Communications. We also have or will soon have IRU agreements with the University of Illinois, the City of Champaign, the City of Urbana, the Champaign-Urbana Mass Transit District (MTD), and Champaign County totalling 3,293.53 strand miles. Those five public entities are not Internet Service Providers, but rather use the fiber for internal communications and distributing Internet among their various locations in our community. | 850 | 754 | 40 | 8 | UC2B is leasing space from the University in two of its Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our dark fiber customers. In order to have as redundant a system as possible, our dark fiber customers need to locate a small router that can terminate the fiber coming from the 7 rings (and their subrings) in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer's router. Beyond that, UC2B is not offering any collocation space. UC2B does also have fiber cross-connect panels in a third University node on two inter-nodal fiber cables to facilitate connections to the Illinois Century Network, the University itself, AT&T, Comcast, Windstream, Champaign Telephone Company, Metro Communications and Pavlov Media, who all have facilities in that node. Service providers will be able to connect to UC2B in those three University's telecommunications nodes, where many of them already have facilities today. The Illinois Century Network, AT&T and Champaign Telephone Company have presences in all three nodes. Windstream, US Signal, Peg Bandwidth and Metro Communications have (or will have) presences in two of the nodes. Comcast, and Volo Broadband have presences in one of the nodes. We are also providing diverse fiber transport on any of our seven rings for service providers without facilities in the UIUC Nodes. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that contain splice cases, they can lease dark UC2B fiber strands to connect redundantly to the UC2B network core and distribute their services. A local provider is planning to build a data center / carrier hotel in 2014 that will have diverse connections to four of the seven main UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our cotangent seven ring design reduces the need for co-location in our facilities and decentralizes service provider hardware. A simplified diagram of the ring design, the inter-nodal cables and the three nodes is attached. | UC2B has made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. Urbana hired a prime contractor for the phase one fiber construction (all fiber in rights-of-way) in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They were: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). Champaign's prime contractor for the phase one fiber construction hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. Through their sub-award, City of Champaign handled the contracting for all the phase two construction (fiber from the curbs to the buildings) and hired PowerUp an MBE firm as the prime contractor. PowerUp also engaged Southern Belle Electric and HVAC (MBE) as a sub-contractor. | This will not apply to all projects, but sub-awarding the right-of-way construction that happened in Champaign to the City of Champaign and sub-awarding the construction that happened in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors reported directly to the Public Works departments of each city, there was great communication between each contractor and its employing city, and issues were resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | In 2013, we signed agreements with and interconnected with four service providers - Champaign Telephone Company, Metro Communications, the Illinois Century Network (ICN)and the Central Illinois Regional Broadband Network (CIRBN). In early 2014, we also signed agreements with and interconnected with PEG Bandwidth and Volo Broadband, for a total of six interconnections with service providers as of this reporting. There are no other interconnection agreements currently being negotiated. UC2B has not denied any requests for interconnection. | UC2B has three peering arrangements, although they are not formal agreements. UC2B peers with the University of Illinois, the Illinois Century Network and Champaign Telephone Company. All three organizations lease dark fiber from UC2B and peer with UC2B's network core. UC2B supports local peering and encourages all local providers to peer with UC2B and its peering partners. UC2B is not providing transit for any other service providers, but UC2B purchases transit from Cogent in Chicago and from US Signal in Champaign.
NT10BIX5570045 | 2010 | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010 | 0 | N/A | 0 | N/A | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010. We are offering dark fiber such that speed can be anything from 10Mb to 100Gbps. | 0 | N/A | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010 and our 1 wholesale contract has not begun using MUFN (BTOP-funded) facilities yet. | 0 | N/A | N/A - we received a FONSI on 12/23/10 such that we did not perform any construction in 2010 with BTOP funds. | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN offers wireline services via fiber optic strands consistent w/ the NTIA BTOP NOFA non-discrimination & network interconnection obligations. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). System users, at their full expense, will be permitted to connect their choice of hardware to dark fiber strands, provided such hardware does not adversely affect the use by and/or electronic or optronic equipment of other system users. General network management policies include: users must pay all initial and ongoing costs to connect to MUFN facilities; system users can request interconnect at MUFN system manholes, handholes, identified interconnection â€œwire serving or terminationâ€ locations and other splice points as determined by MUFN and designated in the course of negotiation; MUFN may route system user fiber through its facilities at MUFNâ€™s sole discretion, provided such routing does not materially impact system userâ€™s use of facilities; system users shall execute a separate agreement with reasonable terms and conditions for interconnection of MUFN facilities with a 3rd party facilities; MUFN, with 120 day notice and minimized disruption to system user, may at its sole option and full expense, substitute fiber on any fiber segment(s) or portions thereof wi | N/A | 6057 | 161 | 0 | 1578 | 240 | 1845 | 2473 | Mad City Broadband is currently our only wholesale customer. We have not leased any fiber strand-miles to them yet as we did not receive a FONSI until 12/23/10 and therefore did not build any fiber plant yet (and they have not looked to use our existing in-kind plant yet either). | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 1 interconnection agreement during the reporting period. We are currently and actively negotiating 2 additional interconnection agreements. We have not denied any request for interconnection. | MUFN has entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period.
NT10BIX5570045 | 2011 | 150185 | MUFN new mileage construction is behind schedule due to delays in obtaining an EA FONSI. The result is completion of several miles of fiber installs JUST after the end of 4Q2011 (lower denominator) though many expenses (numerator) are reflected in our costs at end of 4Q2011. Also, we removed 12.6% of our full in-kind match in the numerator (3.25mi/25.75 miles of conduit match * $3,223,242) so we exclude from the numerator the portion of MUFN (phase 3) that has not been started yet. We are also excluding $91,124 in the numerator for admin/engineering expenses. ($4355377 / 29 miles) | 0 | N/A | 0 | N/A | 10Gbps | We are offering dark fiber. | 0 | N/A | 1Gbps | Currently, all subscribers are lit at 1Gbps. | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 10 times (100Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 6057 | 161 | 50 | 4228 | 93 | 450 | 1075 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as our fiber builds were completed late in 3Q2011 and predominantly in 4Q2011 due to delays in obtaining an EA FONSI. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 1 new interconnection agreement during the reporting period. We are currently negotiating 7 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period.
NT10BIX5570045 | 2012 | 115884 | We note our original baseline of $62,245 is not calculated correctly and includes (31.25) leased miles in denominator and excludes our in-kind contribution match. Recalculating this correctly, our original baseline should have been $152,811. Also, we received approval in Dec 2012 for a route change that adds 18.25 miles. This will bring down our average cost/mile in the next Annual PPR report. | 0 | N/A | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 100 times (10Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 10829 | 674 | 0 | 6952 | 256 | 173 | 2774 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as they are currently building laterals and other connections into the MUFN middle-mile infrastructure. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 2 new interconnection agreement during the reporting period. We are currently negotiating 6 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period.
NT10BIX5570045 | 2013 | 98302 | We note our original baseline of $62,245 is not calculated correctly and includes (31.25) leased miles in denominator and excludes our in-kind contribution match. Recalculating this correctly, our original baseline should have been $152,811. Also, we received approval in Dec 2012 for a route change that adds 18.25 miles of fiber installed in existing conduit. | 0 | N/A | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps or multiple wavelengths via dense wave division multiplexing (DWDM) | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 100 times (10Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 10829 | 124 | 1006 | 9699 | 0 | 0 | 0 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as they are currently building laterals and other connections into the MUFN middle-mile infrastructure. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at 100 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. 8. Advertise permit meetings in the newspaper to increase awareness of project and reduce surprises to neighborhoods. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 2 new interconnection agreement during the reporting period. We are currently negotiating 7 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period.
NT10BIX5570046 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | $40 per Mbps for 1000Mbps | 0 variance | 0 | N/A | $40 per Mbps for 100Mbps | 0 variance | 0 | N/A | N/A | N/A | N/A | N/A | 131040 | 0 | 0 | 0 | 0 | 0 | 131040 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | We've learned it has worked well selecting a firm that can perform both the environmental assessment as well as the construction design. There have been several case that having access to the immediate internal collaboration within the same firm has avoided environmental concerns that could be mitigated by construction techniques. | Louisiana Board of Regents | 253 | 49 | 15 | 0 | 273 | 237 |  | 37 | 385 | 0 | 1249 | N/A | N/A
NT10BIX5570046 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | $40 /1000Mbps | 0 variance | 0 | N/A | $40 /100Mbps | 0 variance | 0 | N/A | N/A | N/A | N/A | N/A | 131040 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Louisiana Board of Regents | 253 | 49 | 15 | 0 | 273 | 237 |  | 37 | 385 | 0 | 1249 | N/A | N/A
NT10BIX5570047 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (a.)-N/A (b.)-No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | None at this point in the project. | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | (1)-3 (2)-1 Interconnection agreement currently being negotiated. (3)- No, we have not denied requests for interconnection. | N/A
NT10BIX5570047 | 2011 | $30,892 | Baseline-$78,747 - Completion of a Sub Participant Route in Northwest Washington is complete and In Service for calculation purposes but is not a good indicator for the true cost per mile calculation for the complete project. | N/A | N/A | N/A | N/A | 1 Gig | Meeting Baseline projections. | N/A | N/A | 100 Mbps | Meeting Baseline projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most AI's were utilizing traditional copper T1 services and are upgrading to ethernet services from NoaNet and it's participants with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 88416 | 720 | 0 | 0 | 87696 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A Northwest Open Access Network will be installing POP and BTOP funded Interconnection equipment in quarters 1 and 2 of 2012. This metric will appear in future reports based upon feedback received from NTIA. | N/A | None at this time in the project. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1. 6 Interconnection Agreements as Wholesale Providers with Capacity Provisioning Inc., Columbia County, Olmpus Net, Spectrum, Touchet Valley TV, and WCI. 2. 1 3. No, we have not denied requests for interconnection. | 4 Transit Agreements-NoaNet currently has transit agreements with four companies: NTT, Ti Net, Cogent, and Spectrum. 3 Peering Agreements with Google, Microsoft, and SIX.
NT10BIX5570047 | 2012 | $68,836 | This is under the projected cost per mile estimate of $78,747. | N/A | N/A | N/A | N/A | 100 Gig | Exceeding Baseline projections. | N/A | N/A | 100 Mbps | Meeting Baseline projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most AI's were utilizing traditional copper T1 services and are upgrading to ethernet services from NoaNet and it's participants with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 75744 | 4500 | 0 | 67500 | 3744 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | POP and Interconnection locations via BTOP funded equipment are identified on the attached addendum to this report in various strategic areas as outlined and noted as City Pairs. Anyone wishing to inquire further may contact Northwest Open Access Network by visiting our website at noanet.net. | N/A | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) Netflix CDN 2.) N/A 3.) N/A
NT10BIX5570047 | 2013 | $73,719 | This is under the projected cost per mile estimate of $78,747. | N/A | N/A | N/A | N/A | 100 Gig | Exceeding Baseline Projections. | N/A | N/A | 100 Mbps | Meeting Baseline Projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most CAI's were utilizing traditional copper T1 Services and are being upgraded to ethernet services from NoaNet and it's sub-recipients with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 74880 | 74880 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | POP and Interconnection locations via BTOP funded equipment are identified on the attached addendum to this report in various strategic areas as outlined and noted as City Pairs. Anyone wishing to inquire may contact Northwest Open Access Network by visiting our website at noanet.net. | N/A | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) - Fatbeam 2.) N/A 3.) N/A
NT10BIX5570049 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A network not yet constructed | N/A network not yet constructed | N/A network not yet constructed | N/A network not yet constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A network not yet constructed | 0 | 0 | 0 | 0 | N/A network not yet constructed | N/A - no subgrants provided | Lessons learned include planning for environmental compliance early in the project as this task may take much longer than anticipated. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | N/A no agreements entered into | N/A no agreements entered into
NT10BIX5570049 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | N/A, network not yet constructed | 0 | 0 | 0 | 0 | N/A, network not yet constructed | N/A, no sub grants provided in this project | Lessons learned include planning for environmental compliance early in the project. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | N/A, no agreements entered into | N/A, no agreements entered into
NT10BIX5570049 | 2012 | 57,442 | Variance due to increase in construction costs to deploy all fiber underground in conduit rather than primarily aerial as initially proposed. | 0 | N/A | 0 | N/A: The county is not providing services on the network. | 1 Gbps | No variance | 0 | N/A: The county is not providing services on the network. | 0 | N/A: The county is not providing services on the network and no private providers have begun offering services. Network testing confirms 1 Gbps capability. | 0 | N/A: The county is not offering services on the network. | Currently Nelson County is providing 10 Mbps Internet service to their facilities across the middle mile network. Previously each of those county facilities was capable of receiving only 1.5 Mbps T1 service. The remaining community anchor institutions are to be served by private providers at speeds desired up to 1 Gbps. | No retail services are provided. | The County has contracted with Blue Ridge InterNetworks for third party network operation services. Rates for transport have been established by the County and agreements used to govern contractual relationships and network use policies. Bandwidth is limited only by the capability of the electronics (currently 1 Gbps). No private providers are serving customers from the middle mile network currently. No limiting or blocking has occurred. | Not applicable. The County is not a service provider on this network. | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | No dark fiber has been leased although capacity is available if desired. | 392 | 84 | 36 | 272 | The County does provide collocation space for interconnection at the Lovingston network operating center. Additional interconnection points are at the Colleen, Afton, Avon, and Lovingston equipment shelters and network cabinets. Two providers are currently collocated in the Lovingston network operating center only. | No subgrants or subcontracts have been made by the recipient to SDB concerns. | All aspects of implementing the broadband network were new for Nelson County personnel. The most important lesson learned is that it is crucial for elected officials to be engaged in the project early and to be aware of all aspects of ongoing implementation for effective communication with constituents and timely approval of any resolutions or decisions to keep the project on schedule. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | The County has entered into interconnection agreements with two providers to date, Lumos Networks and Blue Ridge InterNetworks. One additional interconnection agreement is currently being negotiated. No requests for interconnection have been denied. | No peering or transit agreements were proposed or completed. Interconnection agreements have been completed with Lumos Networks and Blue Ridge InterNetworks, and Lumos has completed interconnection of their facilities in the Lovingston network operating center. An initial 25 Mbps Internet circuit is available from Lumos for wholesale services to private providers who wish to use the middle mile network.
NT10BIX5570049 | 2013 | 57,442 | Variance due to increase in construction costs to deploy all fiber underground in conduit rather than primarily aerial as initially proposed. | 0 | N/A | 0 | N/A: The County does not provide services on the network | 1 Gbps | No Variance | 0 | N/A: The County does not provide services on the network | 0 | N/A: The county is not providing services on the network and no private providers have begun offering services. Network testing confirms 1 Gbps capability. | 0 | N/A: The County does not provide services on the network | Currently Nelson County is providing 15 Mbps Internet service to their facilities across the middle mile network. Previously each of those county facilities was capable of receiving only 1.5 Mbps T1 service. The remaining community anchor institutions are to be served by private providers at speeds desired up to 1 Gbps. | No retail services are provided. | The County has contracted with Blue Ridge InterNetworks for third party network operation services. Rates for transport have been established by the County and agreements used to govern contractual relationships and network use policies. Bandwidth is limited only by the capability of the electronics (currently 1 Gbps). No private providers are serving customers from the middle mile network currently but last mile services planning by Blue Ridge InterNetworks is in progress. No limiting or blocking has occurred. | Not applicable. The County is not a service provider on this network. | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | No dark fiber has been leased although capacity is available if desired. | 392 | 84 | 36 | 272 | The County does provide collocation space for interconnection at the Lovingston network operating center. Additional interconnection points are at the Colleen, Afton, Avon, and Lovingston equipment shelters and network cabinets. Two providers are currently collocated in the Lovingston network operating center. | No subgrants or subcontracts have been made by the recipient to SDB concerns. | All aspects of implementing the broadband network were new for Nelson County personnel. The most important lesson learned is that it is crucial for elected officials to be engaged in the project early and to be aware of all aspects of ongoing implementation for effective communication with constituents and timely approval of any resolutions or decisions to keep the project on schedule. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | At the end of the grant period, the County had completed interconnection with Blue Ridge InterNetworks. An initial agreement with provider Lumos had been negotiated and the connection completed, but the final agreement has not been executed. One additional interconnection agreement is currently being negotiated with Mid Atlantic Broadband. No requests for interconnection have been denied. | No peering or transit agreements were proposed or completed. Interconnection has been completed with Blue Ridge InterNetworks, and negotiations continue with Lumos. Lumos has completed interconnection of their facilities in the Lovingston network operating center and an initial 25 Mbps Internet circuit is available from Lumos for wholesale services to private providers who wish to use the middle mile network.
NT10BIX5570050 | 2010 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No construction has occurred yet. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.No construction has occurred yet. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No construction has occurred yet. | 10Gbps | No variance from baseline. | 8Mbps | No variance from baseline. | 10Mbps | No variance from baseline. | 8Mbps | No variance from baseline. | A majority of the project area currently receives internet services with a maximum speed of .5-1Mbps. Zito's network will offer speeds from 6Mbps to 10,000Mbps depending on the service. The average increase based off a survey of service offerings in the project area would be 10Mbps to 1,000Mbps. | Zito's project is unique in that it offers both middle and last mile service offerings. Last mile service offerings include internet and voice services with internet speeds 6-8Mbps. Commercial service offerings include local point to point ethernet circuits with speeds between 1,000Mbps-10,000Mbps, internet service ad SIP trunks. The full list of services and pricing is attached to the report. | 7a) Zito will not apply restrictions to residential or commercial internet traffic. Zito will employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic will be restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito will offer managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics will be used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito shall not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from at | None. | 12300 | 0 | 0 | 0 | 0 | 0 | 0 | None. | 0 | 0 | 0 | 0 | Network construction has not started yet. Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; Edgewood, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Saegertown, PA; Meadville, PA. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | N/A | N/A
NT10BIX5570050 | 2011 | $9,268 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction started at the beginning of quarter 4 2011, but network is not currently active. | 0 | N/A | 0 | N/A | 1 Gbps | No variance from baseline. | 0 | No speeds are being advertised currently as construction has not commenced in last mile areas. | 0 | Average broadband speed is currently zero as network is not active. | 0 | Average broadband speed is currently zero as network is not active. | Broadband speeds have not increased as not CAIs are connected and the network is not currently lit for services. | Retail services are not currently be provided as network build during the reporting period is not lit for services. | 7a) Zito does not apply restrictions to residential or commercial internet traffic. Zito does employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic is restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito offers managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics is used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito does not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any le | None | 16066 | 0 | 160 | 2616 | 13290 | 0 | 0 | None | 0 | 0 | 0 | 0 | Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Greenville, PA; Meadville, PA; Mercer, PA; Hermitage PA; Edinboro, PA. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. Weekly quality control checks by project manager ensure that project is progressing and work completed is accurate. Interface often with utilties to ensure make ready work progresses in a timely manner. We engaged with outside consultants to improve our accounting management and internal controls. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | No agreements were entered into or denied in 2011. | No agreements were entered into or denied in 2011.
NT10BIX5570050 | 2012 | $20,550 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Based off of miles constructed divided by amount of funds expended. | $17 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Based off of the cost of overlashing fiber in the last mile areas divided by the number of households passed. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The portion of the network in last mile areas is not yet active. For that reason there is no average cost per subscriber. | 1 Gbps | No variance from baseline. | 10 Mbps | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. 10 Mbps are currently being advertised in the Last Mile areas. | 10-100 Mbps | Average broadband speed in the areas that the network is active is 10-100 Mbps. The speed depends on the services used by the location. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No speeds are being advertised currently as construction and connectivity is not finished in last mile areas. | The average increase varies on the services provided to the anchor institutions. The average speed previous to our services varied from 1.5Mbps to 3Mbps with the Zito services these anchor institutions now receive at a minimum 10Mbps with a few receiving 100Mbps. The increase then is between 7Mbps to 97Mbps for the anchor institutions. | The retail services Zito Media Communications II, LLC offers are attached as an attachment. The majority of Zito's network is not currently active as construction and splicing are still being completed. The general services Zito offers include the following: local point to point ethernet circuits, internet service, SIP trunks (inbound/outbound), voice services, and dark fiber leases. | 7a) Zito does not apply restrictions to residential or commercial internet traffic. Zito does employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic is restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito offers managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics is used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito does not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any le | None | 16066 | 7850 | 168 | 7668 | 380 | 0 | 0 | None | 1080 | 36 | 36 | 1008 | Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Greenville, PA; Meadville, PA; Mercer, PA; Hermitage PA; Edinboro, PA. Under the lease agreements with facilities other network providers and/or customers interconnect with our network at these locations not owned by us. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. Weekly quality control checks by project manager ensure that project is progressing and work completed is accurate. Interface often with utility companies to ensure make ready work progresses in a timely manner. We engaged with outside consultants to improve our accounting management and internal controls. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | No agreements were entered into or denied in 2012. | No agreements were entered into or denied in 2012.
NT10BIX5570050 | 2013 | $19,852 | Based off of miles constructed divided by amount of funds expended pertaining to middle mile construction. | $17 | Based off of the cost of overlashing fiber in the last mile areas divided by the number of households passed. | $240 | Based off of the cost of constructing the network in last mile areas divided by the number of subscribers. | 1 Gbps | No variance from baseline. | 20 Mbps | 20 Mbps are currently being advertised in the Last Mile areas. Due to upgraded electronics Zito is able to provide faster speeds to last mile areas. | 10-100 Mbps | Average broadband speed depends on the services used by the location. Middle Mile customers receive a range of services from internet to point to point circuits. | 10-20 | Average broadband speed in our last mile varies between 10Mbps to 20 Mbps. | The average increase varies on the services provided to the anchor institutions. The average speed previous to our services varied from 1.5Mbps to 3Mbps with the Zito services these anchor institutions now receive at a minimum 10Mbps with a few receiving 100Mbps. The increase then is between 7Mbps to 97Mbps for the anchor institutions. | The retail services Zito Media Communications II, LLC offers are attached as an attachment. The general services Zito offers include the following: local point to point ethernet circuits, internet service, SIP trunks (inbound/outbound), voice services, and dark fiber leases. | 7a) Zito does not apply restrictions to residential or commercial internet traffic. Zito does employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic is restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito offers managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics is used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito does not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any le | One subscriber was lost in our last mile area the reasoning was the customer was moving from the area. | 16066 | 15898 | 168 | 0 | 386 | 0 | 0 | None | 1080 | 684 | 648 | 396 | Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Greenville, PA; Meadville, PA; Mercer, PA; Hermitage PA; Edinboro, PA. Under the lease agreements with facilities other network providers and/or customers interconnect with our network at these locations not owned by us. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. Weekly quality control checks by project manager ensure that project is progressing and work completed is accurate. Interface often with utility companies to ensure make ready work progresses in a timely manner. We engaged with outside consultants to improve our accounting management and internal controls. Lastly, for critical anchor institutions, interfacing with local development groups or a chamber of commerce help facilitate discussions with local institutions. Utilizing these groups allows conversations to begin and bring positive advertising for your project as you can gain the community's support for the project. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | No agreements were entered into or denied in 2013. | No agreements were entered into or denied in 2013.
NT10BIX5570051 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | 0 | Keep good notes and document. It is very important to read the CFR's and ask questions in advance. Get written clarification on all aspects of projects before moving forward. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | n/a | n/a
NT10BIX5570051 | 2011 | $3,748 | actual cost/mile is up $391/mile. cost/mile will fluctuate with the distances covered. We anticipate additional longer shots coming up which will lower the overall cost/mile. | $0 | n/a | $0 | n/a | 45megs | 45megs will be advertised, however actual available could be as high as 200megs depending on location and distance. | 0 | n/a | 150 | all paths are currently licensed between 100/megs and 400megs | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts or or sub grants. | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. n/a 2. 3 3. none denied | n/a - not defined in application
NT10BIX5570051 | 2012 | $2,978.49 | cost/mile is down ~$378/mile. This is most due to cost savings in the construction of the network. First Step was able to build the network with fewer man hours than originally estimated. | 0 | n/a | 0 | n/a | 100megs | All CAI connections are built with 100meg minimum capacity. All middle mile paths are constructed with a minimum 200megs capacity and are software upgradable as necessary | 0 | n/a | 150 | all paths are currently licensed between 100/megs and 400 megs | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts or or sub grants. | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. As the project has continued and progressed it has become increasingly apparent and important to communicate directly and clearly with any other potential entities or project partners. This is especially true when dealing with other Federal agencies. The timelines for decisions are often very long and much different than one would expect when dealing with private enterprise. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. 0 2. 3 3. no requests have been denied. | n/a - not defined in application
NT10BIX5570051 | 2013 | $3,596.79 | Cost/mile is up $618/mile from last year. This is due to the increased administrative costs associated with this years work being completed with few miles being constructed this season. | 0 | n/a | 0 | n/a | 100 | All CAI connections are built with 100meg minimum capacity. All middle mile paths are constructed with a minimum 200megs capacity and are software upgradable as necessary | 0 | n/a | 150 | All middle mile paths are currently licensed between 100 megs and 400 megs. | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. The current average speed increase for the CAI clients is 4.75 megs. This represents the average increase in the amount of purchased bandwidth. Each CAI has a 100meg connection to the Internet. This number represents a ~98meg average increase in possible connection speeds. Please see the attachment (CAI Speed Comparison V2) for details. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows: Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts and/or sub grants | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. As the project has continued and progressed it has become increasingly apparent and important to communicate directly and clearly with any other potential entities or project partners. This is especially true when dealing with other Federal agencies. The timelines for decisions are often very long and much different than one would expect when dealing with private enterprise. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. 0 2. 3 3. no requests have been denied. | n/a - not defined in application
NT10BIX5570051 | 2014 | $3596.79 | no change in the cost per mile from last year's report as no construction was completed and associated construction costs were incurred. | 0 | n/a | 0 | n/a | 100 | All CAI connections are built with 100meg minimum capacity. All middle mile paths are constructed with a minimum 200megs capacity and are software upgradable as necessary | 0 | n/a | 150 | All middle mile paths are currently licensed between 100 megs and 400 megs. | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. The current average speed increase for the CAI clients is 4.75 megs. This represents the average increase in the amount of purchased bandwidth. Each CAI has a 100meg connection to the Internet. This number represents a ~98meg average increase in possible connection speeds. Please see the attachment (CAI Speed Comparison V2) for details. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows: Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts and/or sub grants | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. As the project has continued and progressed it has become increasingly apparent and important to communicate directly and clearly with any other potential entities or project partners. This is especially true when dealing with other Federal agencies. The timelines for decisions are often very long and much different than one would expect when dealing with private enterprise. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. 0 2. 3 3. no requests have been denied. | n/a - not defined in application
NT10BIX5570053 | 2010 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. | 448 | 200 | 4 | 244 | Please see answer to 11. | N/A | A. Management Practices 1. Modification of normal procurement practices to match Federal Regulations (FAR) for all ARRA-related procurements. 2. Strict accounting of time by cost centers using bi-weekly time sheets. 3. All documentation relating to grant activities stored in soft copy on server to insure audit trails are completely visible. 4. Competitive procurement vehicles (IFB, RFP) contain explicit statements of work, contract deliverable requirements lists (CDRLs), explicit statements of conditions under which procurement actions can be cancelled in best interest of IT&E and U.S. Government, and clear, understandable evaluation criteria to guide vendors in developing proposals. 5. Oversight of individual projects and project managers by management team experienced in Federal procurement practices and Federal grants management. 6. Separate accounting for ARRA funds; no mixing of ARRA funds with other company accounts to insure clear audit trails. 7. RFPs evaluated separately on technical and cost factors by teams; evaluators assign raw scores without knowledge of weighting factors; weighted scores computed by procurements administrator and grants management team to select short list of vendors in each step; selection of final contract awardees based on best value to IT&E and U.S. Government in accordance with FAR. 8. Procurement actions reviewed by in house General Counsel experienced in Federal Acquisition Regulations and Federal procurement practices. B. Adherence to Federal Rules and Regulations 1. Strict Adherence to Special Award Conditions and FAR. 2. Inclusion of appropriate FAR Clauses in all ARRA-funded procurements 3. All sole-source procurements backed by NTIA/DOC approved J&A (Justification and Authorization) per FAR 6.302.1 4. Level Playing Field for all vendors according to intent of Congress as directed in ARRA and implemented in FAR. 5. Pre-evaluation/pre-award vetting of all vendors per Federal suspension and debarment lookup on www.epls.gov. C. Community Outreach 1. Large signs following criteria spelled out in Special Award Conditions posted at major company locations. 2. Periodic press releases issued at major milestones in project completion. 3. Meetings with Government officials and community organizations with direct interest in the various projects. 4. Pictures of project-related activities collected and saved on server for use in community outreach activities. 5. Establishment of public web site to publicize ARRA-related activities and to advertise ARRA-related procurements. Established links to and from local Government ARRA web sites to insure wider public awareness. D. Examples 1. On our NOC project, we received a only single quote to a widely advertised and subscribed IFB that was three times the engineerâ€™s estimate. It was obvious from the prices listed that the quote was heavily padded with unjustifiable costs. We cancelled the procurement using â€œoutside the competitive rangeâ€ as the reason. We then devised a different, far more cost-effective strategy to complete the procurement action by breaking the activity into smaller, separately advertised procurements and substituting our own in-house labor force for some of the labor originally intended to be contracted out. 2. On our Prepaid Charging Platform Billing System project, our original RFP produced responses that were all above the engineerâ€™s estimate and the available budget by factors ranging from 3 to 10. Again we cancelled the procurement as being outside the competitive range, revised the RFP to make many of the original fixed requirements separately priced options, and re-advertised. Mostly the same vendors responded and even with the options included, all of the proposals were significantly lower in total cost, proving our suspicions that the original cost proposals were heavily padded with unjustifiable costs. We are in the final process of selecting the winning vendor and hope to make an award early in January after we visit existing customers of the short-listed vendors to gain insight on their experience. The purpose of these visits is to insure we select the vendor who will deliver the best total value to IT&E and the Government even if it is not the vendor with the lowest cost. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | N/A. | N/A.
NT10BIX5570053 | 2011 | 16500.72 | Total project cost to date divided by the completed miles = $7,664,252/464.48=$16,500.72. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for Middle Mile. | n/a | n/a | 3.0 Mbps | This is for Middle Mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.035 Mbps. | None. | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | None. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a | Community Outreach: 1. Invite all Community Anchor Institutions to an initial (introductory) meeting to provide information on the Grant Award. Discuss how it would benefit the Community Anchor Institutions. IT&E did this on Guam in October 2011 and had 14 CAIs (IT Managers) that attended the meeting. After that initial meeting, a relationship had been established and IT&E continues to work with these anchors to see how we can support their broadband requirements. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | none | none
NT10BIX5570053 | 2012 | 20149.75 | Total project cost to date divided by the completed miles = $10,165,145/504.48=$20,149.75. In 2011, Total project cost to date divided by the completed miles = $7,664,252/464.48=$16,500.72. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for middle mile. | n/a | n/a | 3.0 Mbps | This is for middle mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.035 Mbps. | none | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a | NONE. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | none | none
NT10BIX5570053 | 2013 | $9,588.79 | $4,837,351/504.48=$9,588.79. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for Middle Mile | n/a | n/a | 3.0 Mbps | This is for middle mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.619 Mbps. | none. | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | none. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a. | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a. | none. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | None. | none.
NT10BIX5570054 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | N/A | N/A
NT10BIX5570054 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | 4464 | 0 | 0 | 0 | 3168 | 1296 | 0 | N/A, network not yet constructed | 0 | 0 | 0 | 0 | N/A, network not yet constructed | N/A, no sub grants provided in this project | It is important for BTOP recipients to begin work on the make-ready connections early in the design profits. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | N/A, no agreements at this time | N/A
NT10BIX5570054 | 2012 | 36035 | Variance due to change in costs as a result of a project modification in early 2012. The inter-community fiber was replaced with microwave transport between towers in each of the proposed funded service areas. | 0 | N/A | 0 | N/A | 1Gbps | At completion, the fiber middle mile network will provide 1 Gbps transport services to private providers. At completion, the microwave network will provide 1 Gbps transport between towers for interconnection to the fiber. | 0 | N/A | 0 | N/A: The PCBA will not provide retail services on the network. The network is nearing completion but no private providers are offering services at this time. | 0 | N/A | The network is currently under construction and no community anchor institutions are being served at this time. | No retail services will be provided by the PCBA. | The PCBA has contracted with Shentel for third party network operation services. Rates for transport have been established by the PCBA and agreements are currently under development to govern contractual relationships for network transport and network use policies. The network is still under construction at this time, and no private providers are serving customers from the middle mile network currently. | N/A | 972 | 486 | 486 | 0 | 0 | 0 | 0 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel) for dark fiber. No additional agreements for dark fiber will be signed. | 1494 | 747 | 0 | 747 | The PCBA does provide collocation space for interconnection at the Luray POP. Additional interconnection points are at the Rileyville Tower, Stanley Water Tank, Cub Run Tower, and Shenandoah Water Tank network cabinets. | No sub grants or subcontracts have been made by the recipient to SDB concerns. | It is important for BTOP recipients to begin work on the make-ready connections early in the design process. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel). The PCBA is not negotiating any interconnection, peering or transit agreements at this time. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. No requests for interconnection have been denied by the PCBA at this time. | N/A
NT10BIX5570054 | 2013 | 36035 | No Variance. Project is complete. | 0 | N/A | 0 | N/A | 500mbs | No Variance. Project is complete. | 0 | N/A | 0 | N/A: The PCBA will not provide retail services on the network. The project is complete. | 0 | N/A | Improved broadband access for all community anchor institutions connected. Not customers have signed on to the network as of grant end date, February 28, 2013. | No retail services will be provided by the PCBA. | The PCBA has contracted with Shentel for third party network operation services. Rates for transport have been established by the PCBA and agreements are currently developed to govern contractual relationships for network transport and network use policies. | N/A | 972 | 486 | 486 | 0 | 0 | 0 | 0 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel) for dark fiber. No additional agreements for dark fiber will be signed. | 1494 | 747 | 0 | 747 | The PCBA does provide collocation space for interconnection at the Luray POP. Additional interconnection points are at the Rileyville Tower, Stanley Water Tank, Cub Run Tower, and Shenandoah Water Tank network cabinets. | No sub grants or subcontracts have been made by the recipient to SDB concerns. | It is important for BTOP recipients to begin work on the make-ready connections early in the design process. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel). The PCBA is not negotiating any interconnection, peering or transit agreements at this time. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. No requests for interconnection have been denied by the PCBA at this time. | N/A
NT10BIX5570055 | 2010 | $25,963.00 | No Variance | $1,053.62 | No Variance | $327.39 | No Variance | 100 Mbps | NTUA can provide tiered service. Please refer to attachment A for details | 1.0 Mbps up to 3.0 Mpbs | NTUA can provide tiered service. Please refer to attachment A for details | N/A | NTUA can provide tiered service. Please refer to attachment A for details | .512 to 1.128 Mpbs | NTUA can provide tiered service. Please refer to attachment A for details | Given the absence of broadband capacity in and around the Navajo Nation, the average increase in broadband speed will be enormous. Most community anchor institutions only have access to T-1 lines which equates to 1.5 Mbps. The NTUA can offer up to 100Mbps or dark fibers capable of up to 10 Gbps. | Retail Services shall be provided by NTUA's sub-recipient Commnet Wireless LLC. For pricing plans, please refer to Attachment A. | Not Applicable | Not Applicable | 550 | 0 | 0 | 0 | 0 | 0 | 550 | N/A | 0 | 0 | 0 | 0 | The NTUA will provide collocation space at their proposed Data Center as well as collocation space at their telecommunications shelters throughout the Navajo Navajo. | Not Applicable | The most important practices/lessons learned are to adhere to the rules and procedures stipulated in the Grant. Following the rules and training our staff on grant procedures helped immensely in eliminating problems that might arise in the reporting process. Equally important is developing clear lines of communications between various departments. For example, the ROW department needs to communicate with the Engineering department, which needs to communicate with the IT department to obtain the information they require. Another lesson to keep in mind is to develop contingencies for all aspects of the job; always have a backup plan and plan everything ahead of time. In particular, allowing enough time for ordering equipment is imperative. Also, creating a detailed project plan is crucial to a successful project. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | The NTUA is currently in negotiations for interconnection agreements. | The NTUA is currently in negotiations for Peering and Transit Agreements.
NT10BIX5570055 | 2011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA anticipates completion of the Broadband Rate study by the first month of the following quarter at which time NTUA will provide pricing plans for all services provided. | In regards to network management policies, NTUA has committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of this proposal. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are developed. NTUA anticipates completion of network management policies and procedures during the following quarter. | N/A | 55372 | 0 | 652 | 17568 | 0 | 0 | 37152 | Although NTUA is currently not leasing any dark fibers, NTUA has agreements in place to provide dark fibers to the following entities: 1. Navajo Nation - NTUA has committed to offer up to 12 dark fibers to the Navajo Nation for a total of 6840 fiber strand miles. 2. Bureau of Reclamations (BoR) - NTUA has committed to provide 4 dark fibers to the BoR for a total of 2280 fiber strand miles. | 15000 | 0 | 0 | 15000 | N/A | N/A | Listed below are the best practices/lessons learned: 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | 1. NTUA has finalized the Tri-State indefeasible right of use (IRU) agreement to obtain dark fibers to a point of presence (POP) in Albuquerque, NM. 2. The total number of agreements NTUA is currently negotiating is one. NTUA is currently negotiating an interconnection agreement with CenturyLink to provide a back up route to Albuquerque, NM via Gallup, NM. 3. NTUA has not denied any request for interconnection. | N/A
NT10BIX5570055 | 2012 | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The maximum broadband speed will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The maximum broadband speed advertised will be determined once the Last Mile infrastructure has undergone the acceptance test procedures (ATP). | N/A | The average broadband speed will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The average broadband speed advertised will be determined once the Last Mile infrastructure has undergone the acceptance test procedures (ATP). | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA Wireless is in the process of completing their retail plan and shall publish the various pricing plans prior to the retail launch. | In regards to network management policies, NTUA has committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of this proposal. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are developed. NTUA has not prevented any consumers from attaching any legal device to the network. | N/A | 54220 | 0 | 652 | 50844 | 0 | 0 | 2724 | Although NTUA is currently not leasing any dark fibers, NTUA has agreements in place to provide dark fibers to the following entities: 1. Navajo Nation - NTUA has committed to offer up to 12 dark fibers to the Navajo Nation for a total of 6840 fiber strand miles. 2. Bureau of Reclamations (BoR) - NTUA has committed to provide 4 dark fibers to the BoR for a total of 2280 fiber strand miles. | 15000 | 3750 | 0 | 11250 | N/A | N/A | 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | 1. NTUA has finalized the Tri-State indefeasible right of use (IRU) agreement to obtain dark fibers to a point of presence (POP) in Albuquerque, NM. 2. The total number of agreements NTUA is currently negotiating is one. NTUA is currently negotiating an interconnection agreement with CenturyLink to provide a back up route to Albuquerque, NM via Gallup, NM. 3. NTUA has not denied any request for interconnection. | N/A
NT10BIX5570055 | 2013 | $19,226 | There is a variance from the baseline plan. In the baseline, NTUA anticipated the average cost per new mile to be $25,963. The methodology to calculate the average cost per new mile is as follows: Average Cost per new mile = (total costs for (conduit, cables, towers, antennas/wireless transceivers, and the labor used to install this transmission infrastructure)) / (number of fiber miles + number of microwave miles) The calculation includes the original budget and overages. The calculation does not include the following: network access (e.g., core network routers), customer premise equipment (CPE), building/facility construction, make ready, test equipment, billing and operational support systems, and/or any additional professional services. | $494.69 | Variance is due to the methodology utilized to calculate costs. The current formula used includes costs for the following: distribution and remote terminals (e.g., DSLAM, B/GPON), conduit, cables, wireless transceivers, antennas and the labor used to install the transmission infrastructure. The formula excludes the following: any costs associated with CPE, CPE installation services, building/facility/tower construction, test equipment, billing and operational support systems and/or any additional professional services. Average cost per household = cumulative direct last mile capital costs / total entities passed. | $162.39 | Variance is due to the methodology utilized to calculate costs. The current formula used includes costs for the following: distribution and remote terminals (e.g., DSLAM, B/GPON), conduit, cables, wireless transceivers, antennas and the labor used to install the transmission infrastructure. The formula excludes the following: any costs associated with CPE, CPE installation services, building/facility/tower construction, test equipment, billing and operational support systems and/or any additional professional services. Average cost per household = cumulative direct last mile capital costs / total households available for subscription. | 10 Gb | No Variance | 3 Mb | Variance is due to NTUA Wireless (NTUAW) adding two additional pricing tiers. In the baseline, NTUAW offered two options: â€¢ $27.95: 765 Kb Download / 200 Kb Upload â€¢ $49.95: 2 Mb Download / 2 Mb Upload In addition to the plans offered above, NTUAW offers two additional plans: â€¢ $39.95: 1.5Mb Download / 765Kb Upload â€¢ $79.95: 3 Mb Download / 2 Mb Upload | 50 Mb | The average speed or rather average capacity provided by this network is in 50 Mbps Circuits. Wireless carriers, among others, have requested 50 Mb circuits for wireless and LTE backhaul. NTUA has the ability to offer circuits up to 10 Gbps in size. | 1.8 Mb | Variance is due to the additional plans offered. As of December 31, 2013, NTUAW has the following subscribers: Rate Plan $27.95 - (765 Kbps) 81 Subscribers $39.95 - (1.5 Mbps)140 Subscribers $49.95 - (2.0 Mbps)184 Subscribers $79.95 - (3.0 Mbps) 74 Subscribers Formula: The sum of the total number of subscribers multiplied by their respective speed divided by the total number of subscribers. | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA Wireless has completed their retail plan and shall publish the various pricing plans prior to the retail launch. Refer to Attachment A & B for details | In regards to network management policies, NTUA and NTUA Wireless have committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of the project. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are updated and/or developed. Neither NTUA nor NTUA Wireless have prevented any consumers from attaching any legal device to the network. | N/A | 55372 | 2280 | 652 | 52440 | 0 | 0 | 0 | NTUA is a wholesale dark fiber provider and is currently in negotiations with the following entities to provide them dark fiber or Lambdas: 1. Tri-State Generation & Transmission 2. CenturyLink 3. Navajo Nation 4. Tuba City Hospital, Tuba City, AZ 5. Western Area Power Administration (WAPA) | 15000 | 3750 | 0 | 11250 | N/A | N/A | 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | N/A | N/A
NT10BIX5570056 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. When constructed DBC's network will offer wholesale option to any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570056 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570056 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A
NT10BIX5570057 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale option to any provider. | N/A | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570057 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | n/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | o | 0 | 0 | 0 | 0 | N/A.When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A. | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570057 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570058 | 2010 | 0 | N/A | 0 | The homes passed at this time are with inactive plant and are in the construction phase. | 0 | Subscribers passed at this time are with inactive plant and are in the construction phase. | 0 | N/A | 10Mbps | No Variance from Baseline | 0 | N/A | 6Mbps | No Variance from Baseline | N/A, Project does not yet offer broadband, therefore no increase can be determined. | Retail Services will not be determined until network is completed, tested, and running. | Grant Recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant Recipient has never blocked consumers from accessing any lawful content, service, service provider, application, and has not prevented any consumers from attaching any legal devices to its network. | N/A, Project has not yet been completed. | 942 | 0 | 0 | 0 | 156 | 0 | 786 | N/A Grant Recipient is not currently wholesaling any fiber in the project area. System is under construction. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers will interconnect with network at network nodes located throughout system. | N/A, there are no subcontract or sub grants under this grant. | Best practice to provide as much dark fiber as financially feasible. It is also best practice to provide adequate start-up and initial grant administration time in the baseline performance perimeters to permit delays in initial engineering, design and permit acquisition. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant Recipient has not entered into or is currently negotiating any interconnection agreements. Grant Recipient has not had any and has not denied any request for interconnection agreements. | Grant Recipient has not entered into or is currently negotiating an peering or transit agreements. Grant Recipient has not had any and has not denieid any request for peering or transit agreements.
NT10BIX5570058 | 2011 | N/A | N/A | $495.33 | We have not made all draw downs on the project, The distribution construction and equipment cost totals $337814.32 divided by 682 homes passed making the average cost per homes passed $495.33 | $5118.40 | We have not made all draw downs on the project. The distribution construction and equipment cost totals $337814.32 divided by 66 subscribers making the average cost per subscriber $5118.40 | N/A | N/A | 50 Mbps | We have increased both the basic and maximum speed offerings since project was started. | N/A | N/A | 11Mbps | Increase from baseline due to our increased in speed offerings. | 9 Mbps, All three had 1 Mbps and now are at 10 Mbps. | We offer 10, 15 and 50 Mbps broadband and a full video lineup. Refer to attachment entitled Rate Card. | Grant recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant recipient has never blocked consumers from accessing any lawful content, service, service provider, application and has not prevented any consumers from attaching any legal devices to its network. | At present time we have not had any subscribers drop the service. | 942 | 156 | 0 | 786 | 0 | 0 | 0 | N/A Grant recipient is not currently wholesaling any fiber in the project area. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers interconnect with network at network nodes located throughout system. | N/A There are no subcontract or sub grants under this grant. | Best practice is to build as much dark fiber as financially feasible, this would allow for future expansion into other under or undeveloped areas. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant recipient has not entered into or is currently negotiating any interconnection agreements. Grant recipient has not had any and has not denied any request for interconnection agreements | Grant recipient has not entered into or is currently negotiating any peering or transit agreements. Grant recipient has not had any and has not denied any request for peering or transit agreements
NT10BIX5570058 | 2012 | N/A | N/A | $ 874.04 | Total of construction and equipment cost $ 596,098.00 divided by 682 homes passed making the average cost per homes passed $ 874.04 | $ 6550.53 | Total of construction and equipment cost $ 596,098.00 divided by 91 subscribers making the average cost per subscriber $6550.53 | N/A | N/A | 50 Mbps | We have increased both the basic and maximum speed offerings since project was started. | N/A | N/A | 11 Mbps | Increase from baseline due to our increased in speed offerings. | 9 Mbps, all 5 had 1 Mbps and now are at 10 Mbps. | We offer 10, 15 and 50 Mbps broadband and a full video lineup. Refer to attachment entitled Rate Card. | Grant recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant recipient has never blocked consumers from accessing any lawful content, service, service provider, application and has not prevented any consumers from attaching any legal devices to its network. | At present time we have not had any subscribers drop the service. | 942 | 156 | 0 | 786 | 0 | 0 | 0 | N/A Grant recipient is not currently wholesaling any fiber in the project area. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers interconnect with network at network nodes located throughout system. | N/A There are no subcontract or sub grants under this grant. | Best practice is to build as much dark fiber as financially feasible, this would allow for future expansion into other under or undeveloped areas. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant recipient has not entered into or is currently negotiating any interconnection agreements. Grant recipient has not had any and has not denied any request for interconnection agreements. | Grant recipient has not entered into or is currently negotiating any peering or transit agreements. Grant recipient has not had any and has not denied any request for peering or transit agreements.
NT10BIX5570059 | 2010 | N/A | N/A | 0 | Nothing to report. | 0 | Nothing to report. | N/A | N/A | 0 | Nothing to report. | N/A | N/A | 0 | Nothing to report. | Nothing to report at this time in the project. | N/A | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 16309 | 0 | 0 | 0 | 2120 | 0 | 14189 | Nothing to report. | 0 | 0 | 0 | 0 | Providers can interconnect with our network at our single interconnection point at the US Bank building in Spokane. Interested parties may contact Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.com. | None at this time in the project. | None at this time. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | Nothing to report. | N/A
NT10BIX5570059 | 2011 | N/A | N/A | 4,239 | $9,902.26 was the Year 2 Baseline. This number is significantly below the Baseline projection primarily caused by aerial plant being the only thing constructed in 2011. With addition of buried construction in 2012, this number will rise significantly by end of year three of the project. | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nothing to report as services have not been turned up as of 12-31-11. | Pend Oreille PUD dba Community Network Systems will be entertaining agreements with Local Service Providers for a variety of retail services all of which will be finalized in 2012. To date, no agreements have been signed and pricing is still being reviewed. | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 16309 | 0 | 0 | 0 | 0 | 0 | 16309 | Nothing to Report. | 0 | 0 | 0 | 0 | Providers can interconnect with our network at our single interconnection point in the US Bank building in Spokane, WA. Interested parties may contact Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at this time in the project. | Clear and open communications with your Federal Program Officer allows for a smooth and cooperative relationship during the process. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | N/A | N/A
NT10BIX5570059 | 2012 | $37,139.79 | 460 miles of Backbone or Middle Mile construction at a cost of 17,084,303. | $3726.43 | Baseline projection was $5061.81, with the anticipation that this number will more than likely rise as the project nears completion. | 0 | N/A There are no subscribers for service as of 12-31-12. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable as services have not been turned up as of 12-31-2012. | Pend Oreille PUD dba Community Network Systems has entered into agreements with Local Service Providers for a variety of retail services all of which will be finalized in 2013. To date, pricing is still being determined by each of the Service Providers and will be available once finalized. | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 31000 | 0 | 0 | 25368 | 5632 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Providers can interconnect with our network at several interconnection points or at the network hub in the US Bank building in Spokane, WA. Interested parties may contact the Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at this time in the project. | Clear and open communication with your Federal Program Officer allows for a smooth and cooperative relationship during the award process. Commitment to share lessons learned with all unserved and underserved community leaders. Building the project with openness to all interested parties seeking to expand broadband services in rural environments. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | N/A | N/A
NT10BIX5570059 | 2013 | 36,566 | Baseline estimates were $51,821 per mile. The final metric shows significant decrease in cost per new mile. This was calculated by taking total construction cost ($21,429,121) and multiplying by the middle mile percentage of 86 % (504 Middle miles/585 total miles) equals $18,429,044 then dividing middle mile $ by the number of middle miles (504), $36,566. | 4,286 | Baseline was $5,061, again, this cost per household metric out-performed projections and original forecasts. This was calculated by taking total construction cost ($21,429,121) divided by households (5,000). | 22,846 | Baseline projections were $17,450. This metric was short or exceeding costs based on the project lagging progress as early as originally planned. Subscribers were only recently signed up and did not reach baseline projections. This was calculated by taking total construction cost ($21,429,121) dividing by 938 original application predicted subscriber connections. | 10 Gig | Exceeding Baseline projections. | 1 Gig | Exceeding Baseline projections. | 10 Gig | Exceeding Baseline projections. | 100 Meg | Meeting Baseline Projections. | We can now offer speeds up to 1 Gig and provide redundancy across the network. Calculations were made using the current speeds provided. | Pend Oreille PUD dba Community Network Systems has entered into agreements with Local Service Providers for a variety of retail services all of which were finalized in 2013. Pricing is attached as is currently determined. | Policies addressing network management have been developed for the expanded network. These policies have been implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | Customers in our area are ecstatic to have High Speed Fiber Optic Broadband services in the area. Those leaving or discontinuing service are doing so only for reason of relocating to a different area or out of our service area. | 30112 | 30112 | 0 | 0 | 0 | 0 | 0 | Pend Oreille County PUD in it's core mission of providing open access network will typically not offer to it's wholesale customers dark fiber leases. | 0 | 0 | 0 | 0 | Providers can, and have interconnected with our network at interconnection points in Pend Oreille County. Interested parties may contact the Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at the the conclusion of the project. | Accurate Cost Accounting methods and close supervision of Sub-Contractors are two things that come to mind as we complete the project. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | 1.) N/A 2.) N/A 3.) N/A | 1.) One-NoaNet to Douglas County. 2.) N/A 3.) N/A
NT10BIX5570060 | 2010 | N/A | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 3Mbps | N/A | N/A | N/A | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | The rates are provided below in lieu of an attachment. Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25.00/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) NONE 7b) NO | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in Pine Telephone Companyâ€™s offices will be available. Pine Telephone Company may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | Due to the length of time and the work involved in getting the Environmental Assessment completed and approved, it is recommended that this portion of the BTOP project be given top priority as soon as an application has been approved. | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570060 | 2011 | $191,176.50 / mile | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 3Mbps | N/A | N/A | N/A | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25.00/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) NO | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570060 | 2012 | $191,176.50 / mile | N/A | $1,414.50 / household | N/A | $3,382.87 / subscriber | N/A | N/A | Pine Telephone Company is not currently advertising a middle mile component. | 3Mbps | N/A | 219Mbps | Pine Telephone Company is the only entity utilizing the middle mile segment and the speed is 219Mbps. | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570060 | 2013 | $14,460.54 / mile | N/A | $1,099.99 / household | N/A | $11,722.60 / subscriber | As customers subscribe to the service the cost per subscriber will drop. The application proposed an incremental turn-up of sites as they became available, but some of the approval processes required the majority of the sites to be turned up at one time closer to the end of the project. | N/A | Pine Telephone Company is not currently advertising a middle mile component. | 3 Mbps | N/A | 219 Mbps | Pine Telephone Company is the only entity utilizing the middle mile segment and the speed is 219 Mbps. | 1.17 Mbps | Currently the range of speeds is from 1 Mbps to 3 Mbps. | The areas addressed in the project are predominantly unserved. Pine provides Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and an upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services are available: 1. 1Mbps / 256Kbps - $25/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services are offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570062 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570062 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570062 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
NT10BIX5570065 | 2010 | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | The average community anchor institution in a currently unserved or underserved rural area will see an increase of a minimum of 1.5 Mbps. In areas that have one or more providers, critical anchor institutions will see their average available service offering increase to a maximum of 10 Mbps in areas where the minimum achievable speed currently is currently only 5 Mbps. The increase was calculated based on competitive analysis of areas where broadband services are offered and not offered. All broadband speeds are based on availability of services offered by this project compared to services currently available or not available to each community anchor institution. | See Word document attached titled '03) Q-19. Attachment A - Last Mile Offerings'. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their service profile allows. Buggs Island Telephone Cooperative does not restrict any lawful device from attaching to the network, nor does it block consumers from accessing any content. | N/A | 0 | 0 | 928 | 0 | 0 | 0 | 0 | N/A | 1000 | 800 | 0 | 200 | Buggs Island Telephone Cooperative does own collocation space. | N/A | It is important to procure all equipment, engineering and project management services as early in the process as possible. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | Buggs Island Telephone has not entered into any interconnection agreements. | Buggs Island Telephone has not entered into any peering and transit agreements.
NT10BIX5570065 | 2011 | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | Broadband speeds have not increased since construction has not been completed and service is not yet live. | Pricing plans have not been provided, since construction has not been completed and service is not yet live. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their service profile allows. Buggs Island Telephone Cooperative does not restrict any lawful device from attaching to the network, nor does it block consumers from accessing any content. BIT has not yet begun providing service. | Not applicable. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative's project is a wireless broadband project and no fiber cable is being constructed for this project. | Not applicable. | It is important to procure all equipment, engineering and project management services as early in the process as possible. Additionally, if applicable, submit your Department Of Labor Davis Bacon Wage Conformance Request as early as possible. Begin working on the Environmental Assessment immediately upon acceptance of the grant in order to avoid project delays. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | Buggs Island Telephone Cooperative (BIT) has not entered into any agreements during this annual period. BIT is negotiating with two (2) wholesale providers, and has not denied any request for interconnection. | N/A
NT10BIX5570065 | 2012 | 0 | BIT is a last mile provider. | 311.04 | From the current funds spent at the end of 2012, that figure was divided by the number of households passed, i.e. 19,333,697 / 62,159 = 311.04. | 0 | BIT currently has not commercially deployed the service. | 0 | n/a | 0 | BIT has not begun to commercially deploy the service so no advertising has been done. | 0 | n/a | 1.5 | This is the average speed received by the beta testers. No commercial subscribers at the end of 2012. | Broadband speeds have not increased since the service has not been commercially ready. | BIT has not yet begun offering broadband services commercially as of now. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their selected service package. VOIP services will have prioritization over all other traffic types. BIT has not yet begun offering commercially deployed services. | Of BIT's beta testers, 20 out of 100 have dropped the service even though the beta testers were not paying for the service due to the broadband service's inconsistencies and lack of reliability and quality, i.e. firmware problems causing CPE to constantly factory default. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Applicable | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is a wireless broadband project and no fiber cable is being constructed for this project. | Not Applicable | It is important to procure all equipment, engineering and project management services as early in the process as possible. Additionally, if applicable, submit your Department of Labor Davis Bacon Wage Conformance Request as early as possible. Most importantly, make sure your leadership is committed and dedicated to the project's success. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | N/A | N/A
NT10BIX5570065 | 2013 | 0 | BIT is a last mile provider. | $106.08 | BIT has projected to begin the LTE construction in Q2 of 2014 so currently there is no commercially deployed service, however, BIT has estimated that the average cost per household passed will be based on the remaining funding divided by the number of households passed. BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area but can only pass 34,322. | $2,261.34 | BIT has projected to begin the LTE construction in Q2 of 2014 so currently there is no commercially deployed service, however, BIT has estimated that the average cost per subscriber will be based on the remaining funding divided by the number of subscribers predicted to be serviced by end of the project period. BIT has projected to have the potential to serve 35,345 households included in the 5 county serving. | 0 | N/A | 4 Mbps | As explained above, BIT has not begun to commercially deploy the service so no advertising has been done, however, BIT has anticipated the maximum speeds to be delivered to the end user to be 4 Mbps. | 0 | N/A | 1.5 Mbps | No commercial subscribers at the end of 2013, however, BIT has anticipated the average broadband speeds to be delivered to the end user to be 1.5 Mbps. | Broadband speeds have not increased since the service has not been commercially ready. Construction for the retrofit to LTE is projected to begin in Q2 of 2014. | BIT has not yet begun offering broadband services commercially as of now, however, BIT has developed a comprehensive offering of products and services at competitive prices. Included in the service offerings will be wireless high-speed broadband, voice, unlimited long distance, up to 10 calling features. The minimum broadband high-speed internet that will be available to the residents and businesses in the 5 county service area will be 1.5 Mbps of service. Generally, residential and business subscribers will have the option to upgrade to 3.0 or 4.0 Mbps of service for an additional monthly fee. BIT estimates that the monthly access rates to residential subscribers will be between $30 and $60 per month for internet service based on the selected package. Business rates will be between $40 and $90 per month based on the selected package. All subscribers will be charged a monthly $3.00 lease fee for the Customer Premise Equipment (CPE). See attachment that provides the specific pricing plans. | BIT will utilize a Policy Server that will restrict users from receiving more bandwidth than their selected service package. VOIP services will have prioritization over all other traffic types. BIT has not yet begun offering commercially deployed services. Construction for the retrofit to LTE is projected to begin in Q2 of 2014. | Of BIT's remaining WiMAX customers, 50 out of 100 have dropped the service, even though they are not paying for the service, due to the WiMAX broadband service's inconsistencies, lack of reliability and quality, i.e.. interference issues. BIT plans to retrofit the remaining customers with LTE, once the network has been deployed, as beta testers for the new service. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Other network providers can connect to BIT's network via a Virtual Private Network (VPN) using their current Internet Service Provider (ISP) for provisioning of subscriber services. Customers would connect to BIT's network using either a Customer Premise Equipment (CPE) or a User Equipment (UE) device that contains a SIM card. | N/A | It is important to thoroughly review all contracts and if possible, have amendments to the contracts that allow a means of termination if the products are not delivered as stated in the contract. Contract negotiations can lead to a tedious and lengthy process which can potentially delay your project milestones, so start the process as early as possible. Work closely with your vendors in order to have project milestones and the time line as precise as possible in order to meet the requirements you set forth in your BTOP application. Always make sure your quarterly and annual reports are filed on time. Delinquent reports affect your good standing and are unacceptable with the rules and regulations of your grant. Most importantly, make sure your leadership and staff is committed and dedicated to the project's success. An extreme amount of man hours go in to the successful implementation of your project, so be prepared. Have the essential staff dedicated for this purpose. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | N/A | BIT's equipment vendor ordered circuits in 12/2013 through Level 3 and Mid-Atlantic Broadband in order to connect BIT to the hosted core (SuperCenter) in Texas.
NT10BIX5570065 | 2014 | 0 | BIT is a last mile provider. | $71.38 | Although BITâ€™s entire BTOP grant budget was $23,958,697, BITâ€™s budget for the revised LTE deployment was $3,895,577.85, of which capital costs include $2,192,754.12. BIT has estimated that the average cost per household passed is based on capital funding spent as of 12/31/14 divided by the number of households passed. BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area but can only pass 30,720. | $5,335.17 | Although BITâ€™s entire BTOP grant budget was $23,958,697, BITâ€™s budget for the revised LTE deployment was $3,895,577.85, of which capital costs include $2,192,754.12. BIT has estimated that the average cost per subscriber is based on capital funding spent as of 12/31/14 divided by the total number of actual subscribers serviced of 411 by end of 2014. | 0 | N/A | 10 Mbps | BIT has advertised the maximum speeds to be delivered to residents to be 4 Mbps, 6 Mbps for CAIs and 10 Mbps for businesses with higher speed packages such as 12 Mbps available only if requested by the customer. This is not an advertised speed package. | 0 | N/A | 3 Mbps | BIT has estimated the average broadband speeds to be delivered to the end user to be 3 Mbps. | BIT has connected one CAI, and for that CAI, broadband speeds went from 3 Mbps to 6 Mbps resulting in a 100% increase in speed at a lower cost. BIT anticipates an increase in speeds for the other 9 CAIs to be connected before the project end date because of better prices. | BIT has a comprehensive offering of products and services at competitive prices. Included in the service offerings are wireless high-speed broadband, with voice, unlimited long distance, up to 10 calling features available in mid-2015. The minimum broadband high-speed internet available to the residents and businesses in the 5 county service area is 1.5 Mbps of service. Generally, residential and business subscribers have the option to upgrade to higher speed tiers for an additional monthly fee. BIT's monthly access rates to residential subscribers are between $35 and $60 per month for internet service based on the selected package. Business rates are between $45 and $200 per month based on the selected package. All subscribers are charged a monthly $3.00 lease fee for the Customer Premise Equipment (CPE). See attachment that provides the specific pricing plans. | BIT utilizes a Policy Server that restricts users from receiving more bandwidth than their selected service package. VOIP services will have prioritization over all other traffic types once available in 2015. | Deployment of service to subscribers began in Q3 2014 and as of the end of 2014, none of BIT's subscribers have dropped the broadband service provided through this project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | BIT does not have any wholesalers at this time. If BIT does resell services to other network providers, BIT would provide access to a customer provisioning database which would connect to BIT's network via a Virtual Private Network (VPN). Customers connect to BIT's network using either a Customer Premise Equipment (CPE) or a User Equipment (UE) device that contains a SIM card. | N/A | It is important to thoroughly review all contracts and if possible, have amendments to the contracts that allow a means of termination if the products are not delivered as stated in the contract. Contract negotiations can lead to a tedious and lengthy process which can potentially delay your project milestones, so start the process as early as possible. Work closely with your vendors in order to have project milestones and the time line as precise as possible in order to meet the requirements you set forth in your BTOP application. Always make sure your quarterly and annual reports are filed on time. Delinquent reports affect your good standing and are unacceptable with the rules and regulations of your grant. Most importantly, make sure your leadership and staff is committed and dedicated to the project's success. An extreme amount of man hours go in to the successful implementation of your project, so be prepared. Have the essential staff dedicated for this purpose. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | N/A | BIT has transit agreements with Level 3 and Mid-Atlantic Broadband to use their circuits to reach NetAmerica' hosted core (SuperCenter) in Texas which connects the customer to the internet.
NT10BIX5570066 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No formal policy since this a middle-mile project and we structure based on leases needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | We will add 7 PoPs (connection points) as part of the middle-mile build out of the routes and customers will connect through these facilities. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | N/A | N/A
NT10BIX5570066 | 2011 | 70,034 | Cost a factor of higher than expected hard rock found during underground burial. To mitigate, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on VDOT rights-of-way. | 0 | N/A | 0 | N/A | 10Gb | Consistent with plan. | 0 | N/A | 2Gb | N/A | 0 | N/A | N/A. Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any CAI's as part of the project. | N/A. Only providing dark fiber services as part of middle mile project. | No services have yet begun over the constructed routes. We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 72051 | 0 | 0 | 34552 | 0 | 0 | 37499 | N/A. No customers as of end of reporting period. | 0 | 0 | 0 | 0 | We will add 5 PoPs (connection points) as part of the middle-mile build out of the routes and customers will connect through these facilities. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | We do not have any interconnection agreements at this time. No last mile providers have contacted BVU requesting interconnection to-date. However, BVU has provided last mile interconnection to the first completed route for Hiltons, VA, themselves. | N/A
NT10BIX5570066 | 2012 | 74,024 | Cost a factor of higher than expected hard rock found during underground burial. To mitigate, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on VDOT rights-of-way. | 0 | N/A | 0 | N/A | 10 Gb | Consistent with plan. | 0 | N/A | 2 Gb | Consistent with plan. | 0 | N/A | N/A. Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any CAI's as part of the project, unless approved by NTIA with any surplus funds. | N/A. Only providing dark fiber services as part of middle mile project. | We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 68332 | 1842 | 0 | 0 | 66302 | 0 | 188 | Virginia Department of Transportation (VDOT): 188 miles | 972 | 972 | 0 | 0 | It was expected that colocation space would be available. However, actual PoP structures purchased, due to cost, are compact and will not allow BVU to support full colocation, except for perhaps, some rack space. Other network providers would connect by running their fiber from their PoP into the BVU PoP for connection to our fiber panel/equipment. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. Lastly, spend time researching how to correctly fill out the necessary reports. The instructions are somewhat vague. Attend webinars on how to interpret the instructions. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | We do not have any interconnection agreements at this time. No last mile providers have contacted BVU requesting interconnection to-date. However, BVU has provided last mile interconnection to Hiltons, VA, themselves. BVU plans to connect some other cities on the completed routes through other funding sources. | N/A
NT10BIX5570066 | 2013 | 63,108 | Cost calculation only considers costs associated with new miles (not leased or upgraded miles) and include ONLY costs associated with conduit, cables, towers, antennas/wireless transceivers, and the labor used to install transmission infrastructure. Cost per mile higher than expected due to hard rock found during underground burial. To mitigate hard rock costs, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on Virginia Department of Transportation's rights-of-way. | 0 | NA. Middle mile project. | 0 | NA. Middle mile project. | 10 Gbps | Consistent with plan. | 0 | NA. Middle mile project does not include providing last mile | 2 Gbps | Consistent with plan. | 0 | NA. Middle mile project does not include providing last mile | Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any Community Anchor Institutions's as part of the project, however, increased speeds will be achieved when last mile provided. Many Community Anchor Institutions along routes are accessing network through Digital Subscriber Line (1.5 Megabits per second) and the new fiber network could offer, on average, 2 Gigabits per second, or an increase of over 1300%. | NA | We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (Voice Over Internet Protocol) over other types. | NA | 67653 | 1842 | 188 | 65623 | 0 | 0 | 0 | Virginia Department of Transportation (VDOT): 188 strand-miles. | 1141 | 1057 | 0 | 84 | There is space for one rack, which consist of 44 vertical rack units, in each National Telecommunications and Information Administration / Broadband Technologies Opportunity Program funded PoP (Point-of-Presence) site. The floor space would equate to 14 square feet of area for the rack and access room around it. Facility Identifer/Name County Total Sq Ft Colocation Space Sq Ft Bland PoP Bland, VA 162.4 14.0 Broadford PoP Smyth, VA 162.4 14.0 Damascus PoP Washington, VA 162.4 14.0 Rosedale PoP Russell, VA 185.6 14.0 Valley PoP Washington, VA 162.4 14.0 Wytheville PoP Wythe, VA 306.0 14.0 Optionally, any provider could interconnect at BVU Authority's primary data center and utilize in place transport equipment to the PoP (Point-of-Presence) sites. The data center has a dedicated colocation center. | NA | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by Broadband Technology Opportunities Program as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the Environmental Assessment we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified Environmental Assessment consultant would recognize missing areas even though not specifically listed in examples. Also, spend time researching how to correctly fill out the necessary reports. The instructions are somewhat vague. Attend webinars on how to interpret the instructions. Lastly, be flexible as the instructions for filling out reports changed quite often and different Broadband Technology Opportunities Program administrative departments did not always agree on what report is needed or what information is needed in report. We consistantly had to go back and amend report information. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | NA | NA
NT10BIX5570067 | 2010 | $0.00 | Construction has not started, awaiting FONSI | n/a | Per our program application & baseline, we are targeting community anchor institutions. This is a middle mile project | n/a | Per our program application & baseline, we are targeting community anchor institutions. This is a middle mile project | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | N/A. Construction has not begun on our middle mile project, as we are awaiting receipt of our "FONSI". | N/A. Construction has not begun on our middle mile project, as we are awaiting receipt of our "FONSI". | 7a. OneCommunity rates limit customer traffic per their contracted committed information rate. On top of the CIR the customer has the ability to burst at 50% above their ordered bandwidth. An example of this is a customer contract has a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the Committed information rate. OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest priority and is meant fo | N/A. This is a middle mile project, and construction has not yet started. | 160608 | 0 | 0 | 0 | 36518 | 3384 | 120706 | N/A - we do not currently wholesale and dark fiber. | 0 | 0 | 0 | 0 | OneCommunity will be upgrading five (5) existing core network locations and building out thirteen (13) new core locations in primarily commercially available collocation space, such as that offered by ATT, Verizon, First Energy, Conneaut Telephone, Horizon Telecom, and ComNet. Two of the new locations will be collocation/leased space from OARnet, our sub-recipient / partner in the project. All space is leased, with capacity available in the commercially available collocation spaces. | None at this time | We are just preparing for construction ramp up. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | (1) none were entered into / signed during the period or since project inception (2) as of 12/31/2010, none were under negotiation (3) as of 12/31/2010, OneCommunity has never denied an request for interconnection | (1) none were entered into / signed during the period or since project inception (2) as of 12/31/2010, none were under negotiation (3) as of 12/31/2010, OneCommunity has never denied an request for interconnection or peering
NT10BIX5570067 | 2011 | 17,481 | based on ring segments that were completed and "lit" during the period (costs include direct and allocated costs for construction materials, labor). In my baseline, I estimated higher costs for initial miles, leveling off to our historic average as we got more miles completed and spread out the non-variable costs. The costs on which the 2011 Annual PR average is based is direct costs for completed miles only. The miles completed were the miles that could be easily â€œclearedâ€ â€“ e.g., they did not require much if any â€œmake readyâ€, and therefore experienced a below average cost. When these miles are combined with miles which will be built in 2012, we will see the overall average climb closer to our historic levels of $25k per mile. | 0 | Not Applicable | 0 | not applicable | 10 gigabits | per baseline | 0 | not applicable | 364 mbps | calculated as the weighted average of all new or improved CAI connections made during 2011. EX: 28 CAI's at 10 mbps each = 280 total mbps in equation. Sum of all mbps/total CAI's = avg bandwidth | 0 | not applicable | The average speed for all current CAI connections is 364 mbps, as calculated by the sum of all mbps available to all locations, divided by the number of locations. For example, 28 locations have a 10 mbps service, that would be 280 mpbs available and added into the numerator. At the other end of the spectrum we have 30 locations with 1 gigabit of service, or 1,000 mbps each, for a total of 30,000 mbps added into the numerator. Sum of all mbps available divided by number of locations resulted in the average of 364 mbps. | not applicable. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted committed information rate. On top of the CIR the customer has the ability to burst at 50% above their ordered bandwidth. An example of this is a customer contract has a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the Committed information rate. OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest priority and is | Not applicable. | 150917 | 1249 | 484 | 3748 | 26532 | 4080 | 114824 | Windstream LLC - 2 IRU agreements (1 @ 50 miles, 4 fibers, 20 years; 1 @ 41 miles, 4 fibers, 20 years) ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2 for a list of current and planned "hub sites". All sites are POPs with Internet gateways. | None at this time. | None at this time. FOR Question 15 - we are using census blocks from the 2000 census, in order to stay consistent with our application. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | A total of seventy one (71) interconnection, peering and/or transit agreements were either entered into or enhanced during the period as a result of establishing a new presence or upgrading existing hub sites. Six new hub site locations (see Excel addendum for Question #2) were established, seven existing hub site locations were upgraded. As of the end of the reporting period, no other interconnection, peering or transit agreements were under active negotiations. OneCommunity operates a completely open network and has never denied any request for interconnection. | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions.
NT10BIX5570067 | 2012 | 27471 | Based on the total costs per ring segment, divided by total fiber miles deployed. Total costs include: engineering/"EA" costs, pole owner engineering and make ready costs, construction labor, and materials. | 0 | not applicable | 0 | not applicable | 10 gigabits/sec | per baseline | 0 | not applicable | 343 | Calculated as the average of the speeds of all CAI's from inception to-date as of 12-31-2012 | 0 | not applicable | The average speed for all currently connected CAI's is 343 mbps (calculated as the average speed of circuits provided to CAI's where fiber was built into the building). The average speed is estimated to be 2 to 4 times greater, on average, across all locations with new or improved service. | Please see additional attachment for current MSA pricing on file with the State of Ohio. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted "committed information rate". On top of the CIR the customer has the ability to burst at 50% above their committed rate. An example of this is, a customer who has a contract at a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the "committed information rate". OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest pri | Not Applicable. | 151827 | 26005 | 243 | 121710 | 1872 | 124 | 1872 | NEW: SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription (note this is a subscription) - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU, 2 strands, 6 miles PENDING - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2 for a list of current and planned "hub sites". All sites are POPs with Internet gateways. | None at this time. | FOR Question 15 - we are using census blocks from the 2000 census, in order to stay consistent with our application. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | We had or now have relationships with the following wholesale/last mile providers: Global Crossing, North Coast Wireless, Net X Internet, Mango Bay Internet, ACC, Time Warner Cable, Agile Networks, and Continental Broadband (formerly Expedient), and Time Warner Telecomm of Ohio. We have sold to all of these entities (and have purchased from some). NEW: SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription. - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU. - ALLTEL - signed services agreement with last mile provider PENDING - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions.
NT10BIX5570067 | 2013 | 27604.75 | Based on the total costs per ring segment, divided by total fiber miles deployed. Total costs include: engineering/"EA" costs, pole owner engineering and make ready costs, construction labor, and materials. | 0 | n/a | 0 | n/a | 10 Gbps | per baseline | 0 | n/a | 313 | calculated as the average of the speeds of all CAI's where new service was provided | 0 | not applicable | The average speed for all currently connected CAI's is 313 mbps (calculated as the average speed of circuits provided to CAI's where fiber was built into the building). The average speed is estimated to be 2 to 4 times greater, on average, across all locations with new or improved service. | Please see additional attachment for current MSA pricing on file with the State of Ohio. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted "committed information rate". On top of the CIR the customer has the ability to burst at 50% above their committed rate. An example of this is, a customer who has a contract at a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the "committed information rate". OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest pri | Not applicable. | 160994 | 31118 | 1902 | 127974 | 0 | 0 | 0 | - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription (note this is a subscription) - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU, 2 strands, 6 miles - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2's Addendum for a list of "hub sites". All sites are POPs with Internet gateways. | None. | None at this time. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | Global Crossing/Level 3 (existing/improved) North Coast Wireless (existing/improved) NetX Internet (new) Windstream KDL (existing/improved) Mango Bay Internet (new) Zito Media (existing/improved) ACC (new) Time Warner Cable (existing/improved) Agile Networks (new) Continental Broadband (existing/improved) Time Warner Telecom of Ohio (existing/improved) United Private Networks (new) Alltel Wireless (new) Cox Communications (new) Fidelity Access Networks (new) | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions.
NT10BIX5570068 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. Existing network management policies will be used 7b. No | N/A | 58296 | 0 | 0 | 58296 | 0 | 0 | 0 | N/A | 3700 | 0 | 0 | 3700 | We own co location space | N/A | N/A | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | N/A | N/A
NT10BIX5570068 | 2011 | 0 | Construction underway, but no cost information yet | 0 | Does not apply | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | [REDACTED] | [REDACTED] | N/A | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | 3700 | 0 | 0 | 3700 | We own the collocation space. | N/A | Obtain approval from NEPA to do engineering at the same time the Phase 1 Environmental Assessment is being performed. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | N/A
NT10BIX5570068 | 2012 | $39,970 | Rio Grande City, Harlingen - Brownsville, Brownsville - Weslaco, Weslaco - Hidalgo, Brownsville - Hidalgo (express route) and six in-kind contribution routes (total of 370 miles) | 0 | N/A | 0 | N/A | 2.5 Gbps | Initial maximum wholesale offering will be equivalent to an OC48 (2.5 Gbps) with a future offering of an OC192 equivalent (10 Gbps) available in the future. | 0 | N/A | 622 Mbps | Out of the seven inital speed tiers offered, the OC12 (622 Mbps) is the average. | 0 | N/A | The dark fiber being provided to CAIs is not replacing an existing connection, so no increase calculation is possible. Also, since we are delivering dark fiber, actual bandwidth for the connection will be determined by each CAIs choice of network electronics. | We will be offering transport, Internet access, and/or collocation services. The transport service includes point-to-point (a.k.a.; A-to-Z) connectivity with a selection of bandwidth options. Internet access adds connectivity through our Internet gateway; and is also available in a selection of bandwidth options. (Speed and price tiers attached) | 7a) We will utilize our current management policies across this network. Bandwidth limitations are determined by contracted servce tiers and traffic prioritization is only done for quality of service (QoS) purposes. 7b) We do not block or censor our connections. | N/A | 50318 | 93 | 0 | 38952 | 5219 | 6054 | 0 | N/A | 4800 | 840 | 0 | 3960 | N/A (We own the collocation space.) | N/A | Obtain approval from NEPA to do engineering at the same time the Phase 1 Environmental Assessment is being performed. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | 1) Did not enter into any agreements during this reporting period. 2) We are currently negotiating two (2) interconnection agreements. 3) We have not denied any requests for interconnection. | 1) Did not enter into any agreements during this reporting period. 2) Negotiating dark fiber IRU participation agreements with five (5) entities.
NT10BIX5570068 | 2013 | 64475 | Construction costs of $12,894,941 / 200 new miles constructed = $64,475 per mile. Baseline projections were for approximately $94,853 per mile. | 0 | N/A | 0 | N/A | 10 Gbps | As per baseline plan. | 0 | N/A | 0 | All participant CAIs have been connected. However, they have been provided with dark fiber drops, as per the baseline plan. As none of the participant CAIs have currently installed equipment to utilize the dark fiber at this time, we cannot calculate an average speed. | 0 | N/A | All of the current CAIs are dark fiber recipients that have not yet connected equipment to their fibers. It is, therefore, not possible to calculate a figure for increased bandwidth speed at this time. | We will be offering transport, Internet access, and/or collocation services. The transport service includes point-to-point (a.k.a.; A-to-Z) connectivity with a selection of bandwidth options. Internet access adds connectivity through our Internet gateway; and is also available in a selection of bandwidth options. (Speed and price tiers attached) | 7a) We will utilize our current management policies across this network. Bandwidth limitations are determined by contracted servce tiers and traffic prioritization is only done for quality of service (QoS) purposes. 7b) We do not block or censor our connections. | N/A | 50318 | 93 | 0 | 50225 | 0 | 0 | 0 | We do offer dark fiber access as a service, but currently do not have any commercial subscribers leasing this option. We have provided dark fiber to participant CAIs without a lease fee as a condition of the grant award. (So, technically, they are not being leased.) Those institutions are: South Texas College (20 fibers), University of Texas Pan American (20 fibers), Texas State Technical College (20 fibers), Texas Southmost College (10 fibers), University of Texas Brownsville (10 fibers), and University of Texas Health Science Center (20 fibers). All together, these entities account for 100 fiber strands throughout this network; or approximately 50% of all strand-miles deployed. | 4800 | 840 | 0 | 3960 | N/A (We own the collocation space.) | N/A | 1) Obtain approval from NEPA to perform engineering at the same time as the Phase 1 Environmental Assessment. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. 2) The Federal Program Officers are an invaluable resource when trying to learn the, sometimes confusing, reporting requirements of federal grants. Engaging them early on when difficulties arise can same a lot of time. 3) Do not pass up the opportunity to attend the many webinars that are offered. Many times, the topic discussed presents solutions to problems that several recipients are experiencing. | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | 1) One (1) interconnection agreement was established during this reporting period. 2) We are currently negotiating one (1) interconnection agreement. 3) We have not declined any requests for interconnection. | 1) Five (5) transit agreements were established during this reporting period encompassing seven (7) entities. 2) We are in the process of hiring staff to market and negotiate new transit agreements on this network.
NT10BIX5570069 | 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 18928 | 9212 | 0 | 0 | 6846 | 0 | 2870 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | The key to successfully moving forward the BTOP project was solid out front planning and initial focus on driving through all issues related to the Environmental Assessment process. The entire ICN plan was committed very early on to the Microsoft Project Planning format so all details large and small would receive adequate visibility with the entire project team. Without this type of format critical task and time line linkages would be difficult to identify and manage. The Environmental Assessment process required a great deal of communication and follow up with a myriad of entities. It is suggested that this communication occur early and project teams remain highly focused and subsequently follow up regarding any refinements or adjustments that may be needed to clear each particular agency. Don't hesitate to contact BTOP support staff for clarification and guidance throughout the process. This will help with formulating the required components of the EA draft. Meet regularly with a specific agenda not only with your BTOP team but with the Federal Program Management team as well. Clear communication combined with clear goals and time lines for detail management will keep a complex process steadily moving forward. There are not any "short cuts". Steady organized effort will deliver results. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010
NT10BIX5570069 | 2011 | 0 | No new miles have yet been constructed. Baseline shows total for end of project. | 0 | Baseline indicates N/A. | 0 | Baseline indicates N/A. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 34Mbps | No variation from baseline. | 34Mbps | No variation from baseline. | Broadband speeds are increased at the request of customers. For example, Community School District in Williamsburg, Iowa ordered an increase from 25Mb to 100Mb of Ethernet services in December 2011. Previous to the BTOP switch and DWDM deployment, the maximum capacity at the location was 45Mb of which 25Mb was the maximum Ethernet service they could get. Current maximum capacity now is 1Gbs which allowed them to order the additional 75Mb. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | N/A | 19009 | 6000 | 0 | 0 | 0 | 0 | 13009 | N/A ICN wholesales no dark fiber. | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | Engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | In order to facilitate the management of the many sites that require installs and then followed by migration of traffic to the new circuits for the BTOP project, the team decided to develop an application to plan and monitor the progress. This required extracting information from the ICNâ€™s Order Entry system, the Work Order system, Circuit Provisioning system, and Billing system. Currently, Engineering is using spreadsheets to assign and track work. This type of short-term solution is duplicating much of the information within existing systems while taking valuable time from the engineers, thus reducing productivity. The BTOP Information System will provide a universal view into the BTOP project as well as provide the opportunity for the ICN to easily develop dashboard views and specific reports/charts, once those needs are determined. There are several benefits for this new system. It will reduce and in most cases eliminate double entry of pertinent data while reducing the number of errors and the need for synching/normalizing the information. It will also permit ICN to pinpoint issues in the process either with individuals, segments within the process, or equipment so that they can be addressed immediately rather than waiting for the issue to become apparent through missed implementation steps and disparate data flows. Another plus with the system is simplifying the information gathering for the Federal reporting. The dashboard items developed, as well as the global view of projects, can be translated to any or all project(s) the ICN currently has or will have in the future. The primary cost savings will be in employee time saved and the ramifications in not completing the project on time, within the budget. Double entry, compiling data, and the validation of multiple spreadsheets can be eliminated. This will speed determination of status and thus resolution. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to.
NT10BIX5570069 | 2012 | 73,243 | Baseline says 89,358. Variance due to overestimation in baseline. | 4,737 | Baseline says NA. Includes 197 households passed. Variance due to overestimation error in baseline. | 4,737 | Baseline says 7,717. Includes 197 subscribers served. Variance due to overestimation in baseline. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 34Mbps | No variation from baseline. | 34Mbps | No variation from baseline. | Customers turned up as part of the BTOP program now have a minimum of 10 Mb each. This represents an average increase of 8.95 Mb per customer added. Based on total CAIs added, that represents an increase of 2.1 Gb of network to the community overall. Sites receiving new connectivity previously had in the 1.5 Mb-3Mb range prior to the BTOP program, now they can get up to 980 Mb per location. Sites receiving new edge routers were previously limited to 45 Mb, with an available segment for broadband of up to 25 Mb. Now, those sites can get slightly more than 980 Mb. Users at aggregation sites were previously limited to 25 Mb or 980 Mb connections and now have the capability of nearly 10 Gb of usable bandwidth. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | A total of 31 CAIs expected to receive service improvements or new service have been dropped from the project. This represents 9 percent of customers who have so far received new or improved service and 1.2 percent of those capable of receiving new service. Of the 31 who have have churned out, 16 were customer disconnections. Disconnects were based on budgeting issues. There were 12 sites in which the CAI closed or moved out of the service area. Three sites canceled service before it was installed, again, due to budgeting reasons. | 19009 | 17209 | 0 | 0 | 0 | 0 | 1800 | N/A ICN wholesales no dark fiber | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | During 2011 and 2012, engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | Recipients should make clear the scope and intent of all equipment changes and ensure they are allowable under the scope of the project and budget. When making changes that include 1) the purchase of 'bigger', more costly version of the equipment originally intended such as a higher capacity router or switch and 2) the purchase of additional equipment to handle the higher broadband demands of customers, be sure to submit AAR an obtain a clear response before proceeding. Even changes that are within budget and scope should be approved before project changes are made. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to.
NT10BIX5570069 | 2013 | 69,538 | Baseline says 89,358. Variance due to over-estimation in baseline. Costs calculated include only the fiber build from the ICN backbone to the Sac & Fox backbone and the fiber build costs from Decorah divided by the mileage from those builds. | 4,564 | Baseline says N/A. Includes 197 households passed. Variance due to over-estimation in the baseline. | 4,564 | Baseline says 7,717. Includes 197 subscribers served. Variance due to over-estimation in the baseline. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 78Mbps | Baseline was calculated using only the new IRU customers and did not factor in the increases from existing customers. This figures represents the average speed of all middle mile circuits being provided. | 44Mbps | Baseline was calculated using only the new IRU customers and did not factor in the increases from existing customers. This figures represents the average speed of all last mile circuits being provided. | Customers turn up as part of the BTOP program now now have a minimum of 10 Mb each. This represents an average increase of 8.95 Mb per customer added. Based on total CAIs added, that represents an increase of 2.1 Gb of network to the community overall. Sites receiving new connectivity previously had in the 1.5 Mb-3Mb range prior to the BTOP program, now they can get up to 980 Mb per location. Sites receiving new edge routers were previously limited to 45 Mb, with an available segment for broadband of up to 25 Mb. Now, those sites can get slightly more than 980 Mb. Users at aggregation sites were previously limited to 25 Mb or 980 Mb connections and now have the capability of nearly 10 Gb of usable bandwidth. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | The original grant included 3,080 CAIs expected to receive new or improved service. The final count was 2,818 CAIs receiving new or improved service. This represents a total change of 262 fewer CAIs or a 8.5% decrease. A total of 103 CAIs dropped service because it was no longer needed. A total of 32 CAIs were dropped because the customer location was closed. A total of 74 CAIs were dropped from the list because they did not meet the definition of CAI. A total of 49 CAI were dropped from the project due to overlap with another BTOP recipient. A total of 10 CAIs were removed due to an inability of the carrier to deliver network connectivity. A total of 3 CAIs were removed because they were duplicative. This represents 262 CAIs removed from the project for various reasons. A total of 9 CAIs were added via approved AARs bringing the grand total to 2,818. | 19009 | 17497 | 0 | 1512 | 0 | 0 | 0 | N/A ICN does not wholesale dark fiber. | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | During 2011 and 2012, engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | CAI lists should be carefully managed and trued up with NTIA on a quarterly basis to avoid process complications. AARs for CAI changes should be submitted at least quarterly. Recipients should closely monitor sub-recipients and ensure funds are not released until sub-recipient reporting and other obligations are met. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to.
NT10BIX5570070 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 157662 | 0 | 0 | 0 | 7852 | 615 | 149195 | N/A | 0 | 0 | 0 | 0 | MassBroadband 123 is currently negotiating to lease collocation space in the carrier-neutral hotel and Internet PoP at One Federal Street in Springfield, MA. In the Baseline Plan we projected that by Year 2, Quarter 1 MassBroadband 123 will complete fit out of our space at One Federal Street and will also have completed agreements for siting 22 Point of Interconnection nodes that will house interconnection equipment for third parties and last-mile providers. | N/A | POLE ATTACHMENT LICENSE APPLICATION PROCESSES The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) have worked collaboratively with Verizon, Western Massachusetts Electric (â€œWMECOâ€), and National Grid (â€œGridâ€) to develop new processes for submitting pole attachment license applications that we believe will help speed up the initial phase of pole attachment licensing and greatly help the MassBroadband 123 fiber build. In Massachusetts, as in most states, an entity wishing to gain access to attach to an existing utility pole must first submit an application to the pole owners along with payment for pre-construction surveys to determine adequacy of the poles to handle the applicantâ€™s proposed attachment. In Massachusetts as most poles are owned jointly by the incumbent telephone and electric companies this requires submitting an application to two pole owners for most applications. In order to prepare the application, the applicant typically conducts a field survey to collect appropriate information on each pole that it wants to license. Upon receiving the application each pole owner also conducts a field survey of the poles included in the application so each owner can assess what make-ready work they believe is required to accommodate a new attachment and who they believe should be responsible for paying for that make-ready work. Sometimes the applicant will attend the pole owner field surveys to represent their own interests. The scheduling of so many field surveys is cumbersome, time consuming, and costly to all parties. The applicant receives a make-ready estimate from each owner only after all the surveys have been conducted and the parties have reconciled their results. Faced with the prospect of licensing 35,000 pole attachments MTC and MBI worked collaboratively with Verizon, WMECO, and Grid to execute Memorandums of Understanding that allow MTC to hire a single third party to collect the detailed data on each pole that all parties will rely upon as the basis of the application phase for determining pole adequacy and developing make-ready work estimates. The data being collected includes GPS locations of each pole, the height and type of all existing attachments measured utilizing photogrammetry, digital photographs and, if required, load screening and analysis. All parties will work off the same data set to discuss and reconcile make-ready requirements so the estimates can be prepared. MAKE-READY WORK In addition, to speed up make-ready work, MTC is currently negotiating with Grid to be able to hire and oversee a make-ready contractor to do all of their make-ready work. Where third party attachers will give MTC permission to do any of their transfers and moves we will attempt to obtain agreements that allow our Design-Builder to do the work just in advance of installing the cable to save time and achieve an economy of scale. | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | N/A | N/A
NT10BIX5570070 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. We will offer tiered bandwidth service options for our transit agreements; the only bandwidth limitations are the 10 gigabyte hardware. Traffic prioritization is not applicable at this time. 7b. No | N/A | 143095 | 0 | 0 | 15840 | 23500 | 0 | 103755 | N/A | 0 | 0 | 0 | 0 | MassBroadband 123 has executed a lease for a co-location space in the carrier-neutral hotel and Internet Point of Presence at One Federal Street in Springfield, MA. We are currently negotiating agreements for 22 Points of Interconnection nodes that will house interconnection equipment for third parties and last-mile providers | N/A | N/A | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. N/A 2. MTC's Network Operator have four interconnection agreements being negotiated at this time: Crocker Communication, Cornerstone Telephone, CenturyLink, and Windstream 3. No requests for interconnection have been denied | 1. N/A 2. We have two transit agreements being negotiated at this time: Crocker Communication and CenturyLink 3. No requests for peering or transit have been denied
NT10BIX5570070 | 2012 | 0 | We have 3 "lit" miles on the network, but it was for I91, which was an in-kind contribution to the network and is categorized as "existing upgraded" infrastructure, so it is not to be included as a "new mile" cost | 0 | N/A | 0 | N/A | $2500/month/1 Gbps | For Ethernet services, we offer up to 1 Gigabit Ethernet. For wavelength services, we offer 10 Gigabit wavelength | 0 | N/A | 100 Mbps | N/A | 0 | N/A | N/A | N/A | 7a. None at this time 7b. No | N/A | 83203 | 3 | 0 | 42500 | 17500 | 0 | 23200 | None at this time | 544 | 408 | 408 | 136 | MassBroadband 123 has has leased a co-location space in the Internet Point of Presence at One Federal Street in Springfield, MA and One Summer Street in Boston, MA. We are currently working on installing equipment and connecting 22 Points of Interconnection nodes that will house interconnection equipment in our racks for third parties and last-mile providers | N/A | Make-Ready The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) work collaboratively, proactively, and aggressively with all utility pole owners and all third parties on the poles including cable providers, municipalities and private entities. Operations staffs from all companies are in regular communication on a weekly and often daily basis. Senior staffs from all companies meet bi-weekly. Company executives meet on an as-needed basis. MBI is also in regular communication with Government Relations staffs of the utility and cable companies. This strategy has built strong support for MassBroadband 123 at all levels of the companies involved in the successful outcome of the project. MBI holds a variety of weekly project management meetings to oversee the make-ready process including weekly meetings that bring together joint pole owners. Typically each owner or third party prefers to manage their own make-ready work and they are uncomfortable meeting with joint owners and licensees. MBI understood from the start that collaborative project management would be required to stay on top of make-ready work on over 30,000 utility poles. MBI collects work progress trackers from each company and loads them into one database so all parties involved in the make-ready work for a single pole can work together to clear roadblocks and can work together on the same MBI identified priorities. MBI will liaise among the various parties to mitigate problems, particularly in a situation where one company is road blocked by another. Whenever possible, MTC has executed agreements with municipalities, cable providers and other third parties to enable our builder to perform make-ready construction. If the pole owner knows that MTCâ€™s contractor is going to perform third party make-ready, they will release licenses before all the work is complete and allow MTC to perform the third party make-ready work in conjunction with installation of our cable. This requires very close communication among all parties, but saves time and also gives the contractor more flexibility in prioritizing where they work. Construction Regardless of how quickly licenses are issued, on a project of this size there are many issues that arise that can cause delays. MTC has worked closely with our builder to find ways to mitigate delays and compress the schedule where possible. Some of the practices that have helped MassBroadband 123 to make up time in the schedule include: â€¢ Beginning negotiations with utilities and railroads prior to final design completion â€¢ Installing messenger strand ahead of fiber when there are not enough contiguous miles of licenses to install fiber. MTC fiber is typically stored on 20,000 foot reels and can not be cut arbitrarily. Strand is stored on smaller reels and can be cut as needed. This helped keeps crews working during lulls in licensing so they could stay on the project and not have to demobilize and then remobilize again at a later time. â€¢ Partnering with a prime contractor with relationships and access to multiple vendors to assist with crew allocation â€¢ Whenever possible, rodding and roping underground segments early in the project to avoid "work-arounds" required late in the project â€¢ Utilizing directional boring instead of grass trenching can speed up environmental permitting and reduce restoration work â€¢ Starting community anchor institution (â€œCAIâ€) and point of interconnection (â€œPOIâ€) installation work prior to backbone fiber installation, so POIs and CAIs are ready to be connected by the time the fiber reaches them | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. 8. Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies, Center for Education Leadership (CELT), Access Plus, Community WISP, Inc., Streamline Networks 2. 20 3. No requests for Interconnection have been denied | 1. None at this time 2. None at this time 3. No requests for Interconnection have been denied
NT10BIX5570070 | 2013 | $50,186.52 / mile | Based on the 950 route miles (of 954 expected final miles) completed as of Dec 31, 2013 and currently forecasted total cost of $47,677,193.78 | 0 | N/A | 0 | N/A | 1 Gbps | For Ethernet services, we offer up to 1 Gigabit Ethernet. For wavelength services, we offer 10 Gigabit wavelength | 0 | N/A | 125 Mbps | Provisioned speeds (excluding wavelength services) range from 5 Mbps to 1Gbps. The average speed is based on 31 active Ethernet and Broadband services. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions (CAIs) is approximately 73 Mbps. This figure is based upon each CAI using the lowest value from the Planned Speed Tier range and assumes that CAIs classified as "New" are considered to have a broadband speed of 0 Mbps and CAIs classified as "Improved" are considered to currently have broadband service at one speed tier one lower than their Planned Speed Tier. Speed Tiers for this purpose are 1-19 Mbps, 20-49 Mbps, 50-99 Mbps, 100 - 999 Mbps, and 1Gbps+. | MassTech only provides wholesale service via the MassBroadband123 network and therefore has no retail service descriptions or pricing plans. | 7a. None at this time 7b. No | N/A | 143095 | 17422 | 8 | 125641 | 4 | 0 | 20 | None at this time | 5784 | 5784 | 0 | 0 | MassBroadband 123 has leased co-location space in 23 locations as noted in the Colocation Capacity Addendum. We have finalized the installation of equipment and connections to all Points of Interconnection nodes that will house interconnection equipment in our racks for third parties and last-mile providers. While MBI does make space available within our racks for qualified service providers to install equipment for interconnection purposes, the number of rack units available for colocation varies by site. The square footage listed above is the amount of space occupied by MassBroadband 123 and no floor space is available at any site for 3rd party use. | N/A | Make-Ready The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) worked collaboratively, proactively, and aggressively with all utility pole owners and all third parties on the poles including cable providers, municipalities and private entities. Operations staffs from all companies were in regular communication on a weekly and often daily basis. Senior staffs from all companies met bi-weekly and company executives met on an as-needed basis. MBI was in regular communication with Government Relations staffs of the utility and cable companies. This strategy built strong support for MassBroadband 123 at all levels of the companies involved in the successful outcome of the project. MBI held a variety of weekly project management meetings to oversee the make-ready process including weekly meetings that brought together joint pole owners. Typically each owner or third party preferred to manage their own make-ready work and they were uncomfortable meeting with joint owners and licensees. MBI understood from the start that collaborative project management would be required to stay on top of make-ready work on over 30,000 utility poles. MBI collected work progress trackers from each company and loaded them into one database so all parties involved in the make-ready work for a single pole could work together to clear roadblocks and work together on the same MBI identified priorities. MBI liaised among the various parties to mitigate problems, particularly in a situation where one company was road blocked by another. Whenever possible, MTC executed agreements with municipalities, cable providers and other third parties to enable our builder to perform make-ready construction. If the pole owner knew that MTCâ€™s contractor was going to perform third party make-ready, they would release licenses before all the work was complete and allow MTC to perform the third party make-ready work in conjunction with installation of our cable. This required very close communication among all parties, but saved time and gave the contractor more flexibility in prioritizing where they work. Construction Regardless of how quickly licenses are issued, on a project of this size there are many issues that arise that can cause delays. MTC worked closely with our builder to find ways to mitigate delays and compress the schedule where possible. Some of the practices that have helped MassBroadband 123 to make up time in the schedule include: â€¢ Beginning negotiations with utilities and railroads prior to final design completion â€¢ Installing messenger strand ahead of fiber when there are not enough contiguous miles of licenses to install fiber. MTC fiber is typically stored on 20,000 foot reels and can not be cut arbitrarily. Strand is stored on smaller reels and can be cut as needed. This helped keeps crews working during lulls in licensing so they could stay on the project and not have to demobilize and then remobilize again at a later time. â€¢ Partnering with a prime contractor with relationships and access to multiple vendors to assist with crew allocation â€¢ Whenever possible, rodding and roping underground segments early in the project to avoid "work-arounds" required late in the project â€¢ Utilizing directional boring instead of grass trenching can speed up environmental permitting and reduce restoration work â€¢ Starting community anchor institution (â€œCAIâ€) and point of interconnection (â€œPOIâ€) installation work prior to backbone fiber installation, so POIs and CAIs are ready to be connected by the time the fiber reaches them | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. 7 2. 1 3. No requests for Interconnection have been denied | 1. None at this time 2. None at this time 3. No requests for Interconnection have been denied
NT10BIX5570070 | 2014 | $50,270.61 / mile | Based on the 949 new route miles against a total cost of $ 47,706,807 | 0 | N/A | 0 | N/A | 1 Gbps | For Ethernet services, we offer up to 1 Gigabit Ethernet. For wavelength services, we offer 10 Gigabit wavelength | 0 | N/A | 52 Mbps | Provisioned speeds (excluding wavelength services) range from 5 Mbps to 1Gbps. The average speed is based on 228 active Ethernet and Broadband services. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions (CAIs) is approximately 67 Mbps. This figure is based upon each CAI using the lowest value from the Planned Speed Tier range and assumes that CAIs classified as "New" are considered to have a broadband speed of 0 Mbps and CAIs classified as "Improved" are considered to currently have broadband service at one speed tier lower than their Planned Speed Tier. Speed Tiers for this purpose are 1-19 Mbps, 20-49 Mbps, 50-99 Mbps, 100 - 999 Mbps, and 1Gbps+. | MassTech does not provide any retail services directly to CAI. It provides wholesale services to Retail Services Providers via the MassBroadband123 network who in turn provide retail services to connect CAIs. The Wholesale Pricing Plan for Retail Services Providers is attached the final PPR. | 7a. None at this time 7b. No | N/A | 143095 | 17426 | 8 | 125661 | 0 | 0 | 0 | Currently leasing a 4 fiber-mile route to the Massachusetts Executive Office of Public Safety and Security. This 4 fiber-mile route has 2 strands for a total of 8 strand-miles (listed in the table above). | 5784 | 5784 | 0 | 0 | MassBroadband 123 has leased co-location space in 23 locations as noted in the Colocation Capacity Addendum. We have finalized the installation of equipment and connections to all Points of Interconnection nodes that will house interconnection equipment in our racks for third parties and last-mile providers. While MBI does make space available within our racks for qualified service providers to install equipment for interconnection purposes, the number of rack units available for colocation varies by site. The square footage listed above is the amount of space occupied by MassBroadband 123 and no floor space is available at any site for 3rd party use. | N/A | Make-Ready The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) worked collaboratively, proactively, and aggressively with all utility pole owners and all third parties on the poles including cable providers, municipalities and private entities. Operations staffs from all companies were in regular communication on a weekly and often daily basis. Senior staffs from all companies met bi-weekly and company executives met on an as-needed basis. MBI was in regular communication with Government Relations staffs of the utility and cable companies. This strategy built strong support for MassBroadband 123 at all levels of the companies involved in the successful outcome of the project. MBI held a variety of weekly project management meetings to oversee the make-ready process including weekly meetings that brought together joint pole owners. Typically each owner or third party preferred to manage their own make-ready work and they were uncomfortable meeting with joint owners and licensees. MBI understood from the start that collaborative project management would be required to stay on top of make-ready work on over 30,000 utility poles. MBI collected work progress trackers from each company and loaded them into one database so all parties involved in the make-ready work for a single pole could work together to clear roadblocks and work together on the same MBI identified priorities. MBI liaised among the various parties to mitigate problems, particularly in a situation where one company was road blocked by another. Whenever possible, MTC executed agreements with municipalities, cable providers and other third parties to enable our builder to perform make-ready construction. If the pole owner knew that MTCâ€™s contractor was going to perform third party make-ready, they would release licenses before all the work was complete and allow MTC to perform the third party make-ready work in conjunction with installation of our cable. This required very close communication among all parties, but saved time and gave the contractor more flexibility in prioritizing where they work. Construction Regardless of how quickly licenses are issued, on a project of this size there are many issues that arise that can cause delays. MTC worked closely with our builder to find ways to mitigate delays and compress the schedule where possible. Some of the practices that have helped MassBroadband 123 to make up time in the schedule include: â€¢ Beginning negotiations with utilities and railroads prior to final design completion â€¢ Installing messenger strand ahead of fiber when there are not enough contiguous miles of licenses to install fiber. MTC fiber is typically stored on 20,000 foot reels and can not be cut arbitrarily. Strand is stored on smaller reels and can be cut as needed. This helped keeps crews working during lulls in licensing so they could stay on the project and not have to demobilize and then remobilize again at a later time. â€¢ Partnering with a prime contractor with relationships and access to multiple vendors to assist with crew allocation â€¢ Whenever possible, rodding and roping underground segments early in the project to avoid "work-arounds" required late in the project â€¢ Utilizing directional boring instead of grass trenching can speed up environmental permitting and reduce restoration work â€¢ Starting community anchor institution (â€œCAIâ€) and point of interconnection (â€œPOIâ€) installation work prior to backbone fiber installation, so POIs and CAIs are ready to be connected by the time the fiber reaches them | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | Total number of interconnection agreements: 19 Total number of interconnection agreements currently being negotiating: 0 No requests for interconnection have been denied Listing of parties with executed interconnection agreements: 186 Communications Access Plus Ayacht Technology Solutions Berkshire Unified Phone CELT Community WISP Cornerstone Telephone Crocker Communications DSCI FTG HG&E Lightower MECNet (Addition Networks) PEG Bandwidth Streamline Networks TOWARDWX Warwick Broadband Service Windstream Wired West | Total number of peering agreements: 0 Total number of peering agreements currently being negotiating: 0 No requests for peering have been denied Total number of transit agreements: 1 Total number of transit agreements currently being negotiating: 0 No requests for transit have been denied Listing of parties with executed transit agreements: Crocker Communications Inc.
NT10BIX5570071 | 2010 | 67,055.90 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 1Gbps | N/A | 0 | N/A | On average institution customers will see at least a 20x increase in available bandwidth. In a small sample of institutions visited, the current common broadband speeds ranged from T1 (1.544Mbps) to 10Mbps Cable Modem. The majority of institutions will have an access port with at least 100Mbps rate, most Academic Type locations will have a 1Gbps available bandwidth. Given our sample data's average bandwidth of about 5Mbps, we can expect on average a 20x increase to the 100Mbps service. | The Zayo Bandwidth Middle Mile Proposal leverages dark fiber, DWDM (Dense Wave Division Multiplexing), and SONET (Synchronous Optical Network) technologies to provide Point to Point Private Line, Ethernet, Wavelength, Dark Fiber and Dedicated Internet services to last mile providers and end users. High count single mode fiber is being deployed in rings and linear spurs off of Zayo Bandwidthâ€™s existing network infrastructure to maximize the reach of the proposal. DWDM and SONET technologies are being deployed over the fiber to enable 1.5M to 10G services from the newly reached communities to the Zayo network infrastructure and the internet. The proposal provides interconnect points for connectivity to last mile providers or end users in the various markets via strategically placed points along the fiber path. From each interconnection point, Zayo will be capable of delivering Ethernet, Private Line, Wavelength, Dark Fiber and Dedicated Internet Access services from 1.5Mbps to 10Gbps via industry standard interfaces. A last mile provider or end user can connect to Zayo Bandwidth at any interconnection point via 2 fiber or 4 fiber optical interfaces. A 2 fiber interface is provided for Ethernet, Wavelength, and Unprotected SONET services while a 4 Fiber interface is used to provide Protected SONET services. The interconnection will leverage industry standard SONET interfaces at OC3, OC12, OC48, or OC192 SONET rates for the various service types, or can leverage standard Gigabit or 10Gigabit Ethernet interfaces for Ethernet private line, Wavelength, and Dedicated Internet Access services. A last mile provider or end user can also request that Zayo Bandwidth extend from a standard interconnection point to their facility. In this case Zayo Bandwidth would construct new fiber from an interconnection point to the customers designated premise and deploy equipment at the premise as appropriate for the requested service type. This extension is provided on an Individual Case Basis (ICB) and is dependent on the distance and complexity of the build. | Zayo will provide a customer with the bandwidth subscribed to, e.g. DS3 (45meg), Fast Ethernet (100meg or fractions thereof), etc. Zayo does not limit a customerâ€™s bandwidth up to the subscribed level, but will â€œchokeâ€ the bandwidth once the level is met. Traffic prioritization is not needed, since Zayo is not providing an â€œMPLSâ€ type service. Customers may, at their discretion, elect to run VLANs, traffic shaping or prioritization within the confines of their subscribed to bandwidth. Zayoâ€™s standard Master Service Agreement carries language forbidding customers from using the service for any unlawful act. We do not block customer traffic from any site deemed legal and lawful, but clearly will comply with government sanctions against sites found to be harmful or illegal. Customer may attach any legal device to our service, and we have not prevented customers from doing this at any time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Currently have IRU Agreement in place with Anoka County to provide 8 Dark Fibers upon completion of Fiber Construction @ a Rate $ $1.00 per month for 30 years. | 0 | 0 | 0 | 0 | All 145 Anchor Institutions are providing Zayo with Rack Space or Location for Zayo to place necessary Racks. Any new customers in the future it would be necessary to do the same. | 0. Zayo has only awarded one subcontract so far on this grant. That subcontract is for Environmental Assessment and Route Development. Zayo has an internal target of 12% to 15% SBD for this project and is working hard to meet this target. | N/A | Zayo Bandwidth, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 67 | 0 | 145 | N/A, Per our baseline, this will not take place until Q2 of year 2. | N/A
NT10BIX5570071 | 2011 | 0 | Zayo has not started building yet, because we are still doing engineering and permitting. | 0 | N/A | 0 | N/A | 10Gbps | This is in line with our baseline. | 0 | N/A | 1Gbps | This is in line with our baseline. | 0 | N/A | 10Gbps based on unserved areas. | N/A | Zayo's standard. Zayo had never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to our network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is in the process of identifying our spaces and hut requirements. | Fiber Engineering and Design is a Small woman owned business doing the engineering work for this project. Mitchell Industries is a Small business providing us strand for this project. | Zayo's biggest challenge has been dealing with pole providers and permitting agencies. We have had to tell them that we are willing to bypass them and go underground if we cannot reach agreement and agree to pricing. When we explain our deadline and our willingness to seek other solutions, we have found the pole providers and permitting agencies much easier to work with. | Zayo Bandwidth, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 67 | 0 | 145 | 0 Currently. 0 Negotiating. Zayo has not denied any request. We have not started building yet. | 0 Currently. 0 Negotiating. Zayo has not denied any request. We have not started building yet.
NT10BIX5570072 | 2010 | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 7a.. Com Net has network management polices in place for our project to address rate limiting, traffic prioritization and other policies related to the openess of our network. Com Net's network openess policy is available to the general public at www.gigepac.com. 7b. To our knowledge, Com Net has never intentionally blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumer from attaching any legal device to the network. | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 0 | 0 | 0 | 0 | 11798 | 13012 | 39467 | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 0 | 0 | 0 | 0 | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | To date Com Net has not made any subcontracts or sub grants to socially and economically disadvantaged small business (SDB) concerns. | Com Net has noted the following best practices and lessons learned: 1) Upon notification of receipt of award, although you have thirty-days (30) to accept, Com Net strongly recommends making your preliminary decision within ten (10) days or less. If your preliminary decision is to proceed but you are waiting on clarification of requirements, Com Net would recommend that you conduct a compliance review of your procurement policy(s) and that you initiate your request for proposal for Environmental Assessment Consultant services unless you do not have such resources available in-house. Com Net still recommends that you wait until you receive clarification on key award requirements prior to final acceptance, it is just important to start your Environmental Assessment work as soon as possible if it is highly probable you will accept the award. 2) In conducting your Environmental Assessments, Com Net recommends you break your overall route into multiple segments for release of work. As work is completed on each segment, it should be reviewed with your Federal Program Officer for route modifications of significance from your application. This approach allows you to prioritize your build-out by segment based on interest and timing requirements for Environmental Assessment, permitting, special construction considerations and of interested Community Anchor Institutions when it comes time to implementation. 3) Do not under estimate the time and expense required for project administration during the six month Special Award Condition especially if you are a first-time grant recipient who may be relying on outside consultants as subject matter experts. There are multiple items that will need to be addressed in parallel following award acceptance, therefore, ensuring training and involvement by qualified individuals is critical to success. Com Net learned that the following items had to be addressed in parallel: Award Requirements Review for Acceptance, establishment of a compliance management program, review of procurement-employment and other policies for compliance, Environmental Assessment for qualified consultant services, establishment of sub-recipient management program, action items for satisfaction of special award conditions, accounting database-system set-up, financing, corporate governance resolutions-directives, reporting administration, community out-reach meetings, route reviews, agency consultations, environmental assessment field work, on-going communications with contacts from community out-reach efforts, attending BTOP orientation meeting and webinars, sub-recipient contract negotiations, other project partner contract negotiations, sub-recipient communications, partner communications, site acquisition efforts, Environmental Assessment draft report review for submission and other project management activities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | (1) N/A (2) Com Net is working to finalize four (4) agreement for Points-of-Interconnect; two (2) with sub-recipients ZAYO and OARnet, and two (2) with One Community and Horizon Technologies as Ohio Middle Mile Consortium partners. Com Net is working on a total of ten (10) unique agreements for mid-span meet points of interconnect for meet point billed services with its Broadband Service Provider Partners. (3) Com Net has not denied any request for interconnect. | (1) NA (2) Com Net is not aware of any conditions in any agreements at this time that differentiate them as peering and transit agreements rather than as Points of Interconnect Agreements. (3) Com Net has not denied any request for interconnection
NT10BIX5570072 | 2011 | $25,534.41 | A favorable variance versus budget of just under $7000 per mile due to the total miles completed being fewer than originally projected with a favorable mix of miles constructed using the direct plow versus boring method of construction. The new fiber route segments that were accepted as fully complete as of the end of 2011 involved highly rural portions of the build-out with minimal obstructions. The routes build therefore did not require the use of the more costly boring operation. | N/A | N/A | N/A | N/A | 10 Gbps | Baseline indicated 10 Gbps in Year 2 of the project. No Variance. | N/A | N/A | 249 Mbps | Com Net's baseline included a projection of 100 Mbps. Com Net's average is driven above the 100 Mbps average based on high bandwidth users by a few hospitals in the healthcare industry, OARnet's lit service usage and the diverse connectivity to Com Net Points-of-Presence through diverse backhaul routes to the Northwest Ohio Area Computer Service Cooperatives data center. | N/A | N/A | The average increase in broadband speed was by a factor of ~5.5. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All service provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | Com Net is offering three basic types of service at the present time. Ethernet Linear (ELINE) transport service for point-to-point connection, Ethernet Local Area Network (ELAN) transport service for point-to-multipoint through port connection to a customer private virtual Local (Metro) Area Network and a dual homed satellite facility to two hub locations (Primary and Disaster Recovery Site) as Ethernet Virtual Private Line (EVPL) circuits through multiservice user network interface ports. | At the present time Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | Com Net has not experienced any dropped subscriber for the GigEPAC to date. Com Net has lost prospective community anchor institutions to competitive broadband providers that were included in its initial projections. | 64277 | 28 | 14 | 4931 | 11770 | 13004 | 34530 | Ottoville Mutual Telephone Company, 8.5 route miles, 1 Fiber or 8.5 Fiber Miles for the purpose of providing service to Grover Hill Elementary as a K-12 Community Anchor Institution Benton Ridge Telephone Company, 5.85 Route Miles, 1 Fiber, 5.85 Fiber Miles for the purpose of serving Findlay High School as a K-12 Community Anchor Institution | 692 | 527 | 36 | 129 | None of the facilities specified above are owned. The square footage reported is based on (i) two sites where in-kind equipment along with DWDM network upgraded equipment is collocated in network centers/transmission sites of an interexchange carrier; (ii) in one site where in-kind equipment is located in carrier neutral space of the data center operator; (iii) in one site where in-kind equipment, along with DWDM network upgrade equipment, is located in carrier neutral space of the data center operator; (iv) in one site where in-kind equipment located in a legacy leased suite of Com Net; (v) in one site where in-kind equipment is located in rack space inside of Com Net's wholly owned subsidiary Independents Fiber Network; and (vi) in one site where upgraded DWDM equipment of Com Net occupies space at an incumbent Local Exchange Carrier Central Office. Other network providers can also connect to Com Net's federally funded backhaul network through mid span point-of-meet arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned | Com Net recommends involving the County Engineer's office early on in your Community Outreach efforts with County Commissioners and economic development agencies. It is important that the County Engineer's office understands that the BTOP award is a fixed budget award and that forced changes in the method of construction by the authority having jurisdiction can limit the fiber optic system's reach in that county as well as downstream counties in the system. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | Com Net has entered into eleven (11) agreements that it classifies as an interconnection, peering and/or transit arrangement. As of year-end 2011, Com Net had established mid-span point-of-meet, meet-point billed points of interconnection with Middle Point Home Telephone Company, Arthur Mutual Telephone Company, Northwest Net and its wholly owned subsidiary Independents Fiber Network. Com Net is currently in the process of negotiating 21 similar such agreements. Com Net had established mid-span point-of-meet interconnections with the Ottoville Mutual Telephone Company and Benton Ridge Telephone Company allowing them to secure an Indefeasible Right to Use (IRU) Dark Fiber (DF) for serving community anchor institutions through their local service point-of-presence. Com Net is currently in the process of negotiating agreements with 5 additional such agreements. The five entities are not unique from the 21 mentioned above. Com Net had established intrabuilding mid-span point-of-meet interconnections with Community Internet Service Provider (CISP) in its data center located at 3035 Moffat Street; Toledo, OH; and with OneCommunity and OARnet at DatacenterBZ located at 535 Scherers Court; Columbus, OH. Com Net is currently in the process of negotiating 2 additional such agreements that are unique from the 21 mentioned above. Com Net had established interbuilding mid span point-of-meet interconnections with Northwest Ohio Area Computer Services Cooperative (NOACSC) and Ohio Academic Resources Network (OARnet) through a splice case located outside of 1680 North Sugar Street; Lima, OH. Com Net has not started negotiations with another party on a similar agreement at the present time. Com Net had established an agreement with T2 Communications, a wholly owned subsidiary of Com Net, allowing each party to purchase facilities and services from the other. The original basis of the agreement was for T2 Communications, as a sub-recipient to sub-lease conduit space it could secure through a legacy Interconnect Agreement to Com Net. Com Net had established an agreement with Sycamore Telephone Company to Interconnect for the sale of transport service for connectivity to Com Net IP data and IP video services. This agreement was contingent on the completion of a joint build by Sycamore as the construction management company, the completion of certain route segments by Com Net between Lima, Ohio and a planned point-of-meet with the Sycamore Telephone Company north of Upper Sandusky, Ohio. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver an Indefeasible Right to Use (IRU) dark fiber based on plans to serve Community Anchor Institutions (CAIs) in certain areas of the network. | None based on Com Net's interpetation. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as inkind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services.
NT10BIX5570072 | 2012 | 28,525 | This price includes all outside plant construction firm charges, fiber-optic plant materials, private easement costs, authority having jurisdiction (AHJ) permit application costs, conduit costs, pole attachment application costs, pole make ready costs, Railroad (RR) crossing occupancy costs, RR liability insurance cost and RR flagman costs. | NA | NA | NA | NA | 10 Gbps | Baseline indicated 10 Gbps in Year 2 of the project. No Variance | NA | NA | 139 | CNI's most common service being sold is point-to-point Ethernet service, so this number is based on the average committed data rate being ordered. In 2011 CNI saw limited customer's subscribing for service but with several requesting connection speeds in excess of 100 Mbps. In 2012 CNI has seen more moderate capacity requirements from Community Anchor Institutions and wholesale customers. | NA | NA | The average increase in broadband speed was by a factor of ~4.0. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All service provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE; ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | At the present time Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | CNI has not experienced any dropped subscriber to date for the GigE Plus project. CNI is not tracking and reporting on dropped subscibers of its Broadband Service Partners. CNI has lost the opportunity to serve prospective community anchor institutions that were included in its initial projections to competitive broadband providers on price and service availability at the time of customer commitment. | 64396 | 761 | 287 | 29732 | 9026 | 3406 | 21184 | Ottoville Mutual Telephone Company, 8.5 route miles, 1 Fiber or 8.5 Fiber Miles for the purpose of providing service to a K-12 educational institution Benton Ridge Telephone Company, 5.85 Route Miles, 1 Fiber, 5.85 Fiber Miles for the purpose of serving a K-12 Community Anchor Institution, 1 Fiber for serving the a K-12 school district, 1 Fiber for serving a K-12 school district, 1 Fiber for serving a K-12 school district Wabash Mutual Telephone Company 2 Fiber for Serving a K-12 school district SAA bright.net 2 fiber for serving a K-12 school district Telephone Service Company 1 Fiber for serving the a K-12 school district and one fiber for delivering IP service to a K-12 school district. McClure Telephone Company 2 Fiber for customer access to Com Net Findlay Point-of-Presence for protected network connectivity as part of Network Interface connection Bascom Mutual Telephone Company 2 Fiber for establishing mid-span meet-point interconnect with the Sycamore Telephone Company. Sycamore Telephone Company 2 Fiber for establishing mid-span meet-point interconnect with the Bascom Mutual Telephone Company Northwest Net 2 Fiber for providing service to a K-12 school district. Northwest Net 1 Fiber for providing service to a commercial entity 2 fiber Toledo to Dayton route to be used by ZAYO for leasing to an undisclosed customer | 708 | 420 | 36 | 252 | The square footage reported is comprised of (i) one sites where in-kind equipment along with DWDM network upgraded equipment is placed in leased collocation space of an ISP; (ii) addition of a rack in 2012 at one site to house the Cyan chassis where in-kind equipment is located in carrier neutral space of the data center operator as reported in 2011; (iii) addition of a rack in 2012 at one site where in-kind MPLS Network equipment had to be separated from DWDM network upgrade equipment for cooling purpose, which is located in carrier neutral space of the data center operator as reported in 2011; (iv) three newly constructed 12x10 concrete hut enclosures in 2012; (v) in one site where upgraded DWDM equipment of CNI was installed in occupied space at an ISP's Point-of-Presence as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as service are sold; (vi) in one site where upgraded DWDM equipment of CNI was installed in occupied space at an Cable TV provider's central network distribution office as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as service are sold; and (vi)i in 24 sites where upgraded DWDM equipment of CNI was installed in occupied space at an incumbent Local Exchange Carrier Central Office as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as services are sold. Other network providers can also connect to Com Net's federally funded backhaul network through mid span meet-point interconnect arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned | Although aerial plant may be lucrative from a construction cost standpoint, do not underestimate the application fees and make ready costs in aerial construction as well as time line impacts and on-going repair costs. A thorough inspection of pole facilities should be completed prior to making a final determination to go aerial versus underground from a cost and timing perspective. At the same time, when making the decision to go underground, one should pursue all resource information available on subsurface soil and rock conditions. The presence of quarries in or around the planned route is a good indication you may encounter obstructions during construction. It is also important to engage with the authorities having jurisdiction to establish a working relationship, especially if the authorities have encountered problems with workmanship associated with the placement of communication facilities in the past. You may encounter resistance to certain methods of construction that can only be overcome through relationship building and/or negotiation of special agreements to repair any disturbed underground facilities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | In Com Net Incorporated's (CNI's) 2011 annual performance progress report it was noted that eleven (11) agreements classified as an interconnection, peering and/or transit arrangement were established. It was later determined that four (4) of these should not have been reported in OARnet and OneCommunity as sub-recipients, as well as Tier 2 Communications and Independents Fiber Network as wholly owned subsidiaries of CNI making the adjusted total agreements seven (7) for 2011. As of year-end 2012 CNI had established 34 agreements classified as interconnection, peering and/or transit arrangements. CNI had established mid-span meet-point (MSMP), meet-point billed points of interconnection as services are sold with Telephone Service Company; Bascom Mutual Telephone Company; Wabash Mutual Telephone Company; Sherwood Mutual Telephone Association; Vaughnsville Telephone Company; Farmers Mutual Telephone Company; Kalida Telephone Company; Glandorf Telephone Company; Defiance Holdings property Qualstar; SAA bright.net; New Knoxville Telephone Company; Buckland Telephone Company; Waldron Telephone Company; Ayersville Telephone Company; Fort Jennings Telephone Company; Ridgeville Telephone Company; Ogden Telephone Company; Sand Creek Telephone Company; McClure Telephone Company and Champaign Telephone Company. Com Net was in the process of negotiating one such additional agreement. CNI had established or upgraded Mid-Span Meet Point Network-to-Network Interconnection (NNI) agreement with carriers with the purchase and/or sale of transport services with Columbus Grove, a Fairpoint Communications property; AVETEC; Buckeye Telesystem and MediaCom as well as Bowling Green Municipal Utilities. Com Net was in the process of negotiating one such additional agreement. CNI had established intrabuilding mid-span point-of-meet interconnections with Level3 at its network center located at 1946 N. 13th Street, Toledo, OH; US Signal at 121 N. Erie Street through an intrabuilding cross connect at 1946 N. 13th Street, Toledo, OH to US Signal fiber facilities; XO Communications at 535/545 Scherers Court, Columbus, OH; and INDATEL Service at 305 E. Cermak Street, Chicago, IL through leased DWDM service from 535 Scherers Court to the INDATEL Services collocation cage. CNI had entered into agreement to provide new or improved transient transport for connectivity to CNI's regional transient IP network to WATCH Communications; Bascom Communications; Wabash Communications; and Securus Technologies. CNI sub-recipient ZAYO had reported it had entered into an agreement with one undisclosed customer to provide two dark fiber under an IRU. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver an Indefeasible Right to Use (IRU) dark fiber as a fiber tail service under a managed service agreement based on jointly provided service plans to a Community Anchor Institutions (CAIs) in certain areas of the network. | CNI did not enter into any peering or transit agreement as part of the federally funded project. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, Content Delivery Networks, IP Exchanges, Ethernet Exchanges, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as in-kind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services.
NT10BIX5570072 | 2013 | $43,416 | This price includes all outside plant construction firm charges, fiber-optic plant materials, private easement costs, authority having jurisdiction (AHJ) permit application costs, route surveying, conduit costs, pole attachment application costs, pole make ready costs, Railroad (RR) crossing occupancy costs, RR liability insurance cost and RR flagman costs, EA consultant fees for route changes and route inspection, as well as, allocation of for right-of-way, permits, construction progress reporting and construction contract management support. The original baseline new route mile construction cost was developed on a non-cumulative project year basis with 10% construction completed project year 1, 45% project year 2 and 45% project year 3 which works out to $43,467 composite. CNI firmly believes its composite cost would have been on or over the cumulative average cost per mile per new mile if construction to downtown Dayton would have been completed prior to the end of the project award. | NA | NA | NA | NA | 100Gbps | Baseline indicated 40Gbps in Year 3 of the project. CNI is promoting concatenated 10Gbps ports until such time it is economical to upgrade to a 100 Gbps port. CNI successfully completed a 100Gbps field test on its network with Cyan and JDSU to demonstrate the capability. | NA | NA | 298 Mbps | CNI's most common service being sold is point-to-point Ethernet service on a wholesale basis. This number is based on the average committed data rate being ordered. In 2011, CNI saw limited customer's subscribing for service but with several requesting connection speeds in excess of 100Mbps. In 2012, CNI saw more moderate capacity requirements from Community Anchor Institutions and wholesale customers. In 2013, CNI deployed CISCO 9K MPLS network equipment across its core network, running Sylvania-Lima-Worthington-Sylvania operating at 10Gbps for wholesaling Dedicated Internet Access to its Broadband Service Providers serving residential and business end users throughout west-central Ohio. At the end of 2013, CNI's network planning team was finalizing implementation documentation to upgrade this core to 2x10Gbps for an aggregate capacity of 20Gbps In 2013, CNI extended its 10Gbps service to Chicago via Lima and Worthington, which has led to several sales of 1Gbps point-to-point circuits. | NA | NA | The average increase in broadband speed was by a factor of ~4.0. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All services provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE; ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer-provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserving additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | At the present time, Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | CNI has not experienced any dropped subscribers to date for the GigE Plus project. CNI is not tracking and reporting on dropped subscribers of its Broadband Service Partners. CNI has lost the opportunity to serve prospective community anchor institutions that were included in its initial projections to competitive broadband providers on price and service availability at the time of customer commitment. | 64339 | 3970 | 2858 | 56224 | 36 | 57 | 1194 | Ottoville Mutual Telephone Company, Benton Ridge Telephone Company, Qualstar, Wabash Mutual Telephone Company, New Knoxville Telephone Company, SAA bright.net, Telephone Service Company, McClure Telephone Company, Bascom Mutual Telephone Company, Sycamore Telephone Company, NorthwestNet, Champaign Telephone Company, NetGain, Ohio K-12 Information Technology Center(s) and undisclosed customer of ZAYO. The total number of fiber miles to be delivered on completion of the post award build totals 2,915 fiber strand miles with the majority delivered to the undisclosed customer of ZAYO. With the exception of the undisclosed customers of ZAYO, all recipients of dark fiber are also using the facilities as a dark fiber tail to deliver broadband services to subscribers which drives its demand for Com Net wholesale bandwidth service; to jointly deliver with Com Net lit services to a commercial or public organization; or to establish a mid-span meet point route for connecting the company's office to another broadband service provider or to a Com Net Point-of-Presence (PoP) for a City Pair on Com Net's GigE PLUS network. | 923 | 179 | 108 | 636 | ,,,The square footage reported for 2013 is comprised of (i) one site housing Cyan equipment in leased rack space from a local service provider; (ii) leased rack space of three 19" racks in a city municipality facility with two racks for housing CNI equipment and one rack for sub-recipient equipment; (iii) rack space occupancy in a city administration building for the placement of a Cyan Chassis and auxiliary equipment; (iv) rack space occupancy in a sub-station of an electrical cooperative for the placement of Cyan equipment and auxiliary equipment; (v) one newly constructed 12x26 concrete hut enclosure placed in 2013; (vi) occupancy of rack space for the placement of Cyan equipment at one independent exchange carriers office; (vii) occupancy of rack space for the placement of Cyan equipment in a leased suite of a wireless Internet Service Provider (WISP); (viii) occupancy of rack space for the placement of Cyan equipment at a K-12 Information Technology Center's office; (ix) lease of rack space in a suite at a non-profit organization's facility for the placement of Com Net and sub-recipient equipment with the ability to sub-lease rack space as room permits; (x) adjustment of previously reported 3 huts from 12x10 to 12x20 along with the placement of 1 rack at one site and 2 racks at 2 sites by sub-recipient ZAYO with only the incremental 120 square feet and new ZAYO leased space reported; and (xi) single rack collocation space at the Equinix datacenter at 350 E. Cermak Street in Chicago, IL where customers wishing to interconnect can make their own arrangements for space and cross connect facilities to a meet-me room or Com Net's rack space demarcation point as permitted by the landlord. Fiber facilities were, also, placed to non-federally funded existing facilities of ZAYO in Toledo, Ohio and Lima, Ohio. Installation of fiber entrance facilities to ZAYO collocation space at a Dayton datacenter and to a ZAYO network center in Columbus, Ohio were still outstanding at the end of the project award. Prior to the end of the project award, Com Net had, also, entered into agreement with NetGain and Disaster Recovery Services, along with their jointly held entity Mercury Networks, to interconnect through protected-diverse path facilities that will extend the reach of the GigE network with access equipment occupying space in landlord buildings in Bellefontaine, Marysville, Delaware and Westerville Ohio. Customer will be able to interconnect to the GigE PLUS network through these sites. Non-federally funded fiber facilities were extended and lit with 10Gbps capabilities to a datacenter operator at 1 Limestone St; Springfield, Ohio, as well as, in the process of being extended to the datacenter at Wright State University with an expected completion date of January 31, 2014. Other network providers can, also, connect to Com Net's federally funded backhaul network through mid span meet-point interconnect arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned Team Fishel - Women Business Enterprise | Although aerial plant may be lucrative from a construction cost standpoint, do not underestimate the application fees and make ready costs in aerial construction, as well as, time line impacts and on-going repair costs. A thorough inspection of pole facilities should be completed prior to making a final determination to go aerial versus underground from a cost and timing perspective. At the same time, when making the decision to go underground, one should pursue all resource information available on subsurface soil and rock conditions. The presence of quarries in or around the planned route is a good indication you may encounter obstructions during construction. It is, also, important to engage with the authorities having jurisdiction to establish a working relationship, especially if the authorities have encountered problems with workmanship associated with the placement of communication facilities in the past. You may encounter resistance to certain methods of construction that can only be overcome through relationship building and/or negotiation of special agreements to repair any disturbed underground facilities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | In Com Net Incorporated's (CNI's) 2011 annual performance progress report, it was noted that eleven (11) agreements classified as interconnection, peering and/or transit arrangements were established. It was later determined that four (4) of these should not have been reported in OARnet and OneCommunity as sub-recipients, as well as, Tier 2 Communications and Independents Fiber Network as wholly owned subsidiaries of CNI making the adjusted total agreements seven (7) for 2011. As of year-end 2012, CNI had established 34 agreements classified as interconnection, peering and/or transit arrangements with sub-recipient ZAYO reporting it had entered into an agreement for dark fiber with one wholesale customer. In 2013, CNI entered into a agreement to interconnect with dark fiber facilities of AVETEC in order to light them and deliver services, with TDS to move and upgrade legacy lit service provided by Com Net's wholly owned subsidiary to the federally funded network, with a national 4G wireless provider to move and upgrade legacy lit service provided by Independents Fiber Network to the federally funded network, two other national 4G wireless providers to deliver lit cell site backhaul services, with Consolidated Electric Company to establish a network-to-network interface to provide wholesale transport services and with Piqua Municipal Electric Utility Service to provide bandwidth services and to manage excess fibers deployed for the utilities SCADA system in an open network environment for the benefit of the community. In addition, Com Net entered into an agreement with NetGain and Disaster Recovery Services, along with their jointly owned entity Mercury Networks, to deliver a 10Gbps wavelength service and backhaul network management service to establish protected, diverse-path network-to-network connectivity in a mutually beneficial manner. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver Indefeasible Right to Use (IRU) dark fiber as a fiber tail service under a managed service agreement based on jointly provided service plans to Community Anchor Institutions (CAIs) in certain areas of the network. | CNI did not enter into any peering or transit agreement as part of the federally funded project. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, Content Delivery Networks, IP Exchanges, Ethernet Exchanges, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as in-kind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services for delivering IP Bandwidth CNI purchases on wholesale and resells with its transport to Broadband Service Providers for their resale. CNI, also, procured a Cyan chassis and deployed it at 350 East Cermak Street, Chicago, IL for the purpose of protected transport over leased 10Gbps wavelength service for connecting to and peering with the INDATEL Services Content Delivery Network (CDN).
NT10BIX5570073 | 2010 | $0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | Not available at this time. | Not available at this time. | N/A - the network has not been implemented as of yet. However, we will adhere to the network management policies provided by BTOP. | N/A | 9576 | 0 | 0 | 0 | 1064 | 0 | 8512 | N/A - we will not be wholesaling dark fiber. | 0 | 0 | 0 | 0 | We will have five new interconnection points and four existing that out network providers may interconnect to our network. | 0 | We are using our normal project management processes to run this project. However, very soon after award, we placed RFPs for legal and EA consulting. We also worked on our RFPs for construction, materials and technology in parallel to EA process. Once we have final FONSI, we'll be ready to roll. | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | N/A | N/A
NT10BIX5570073 | 2011 | $35,303 | Total project cost divided by total miles. Cost decreased as total miles increased as we didn't account for the GePON miles in the baseline. | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline plan | NA | Middle and last mile business project | 100Mbs | No variance from baseline plan | NA | Middle and last mile business project | Most of the CAIs have 1.5 Mpbs with DS-3 service or didn't exist at all as it is a brand new building. The hospitals have an existing dedicated 1Gbs route. With this project, these entities will be able to select from symmetrical 10 Mbps to 1Gbs. | NA | Will upload once we have customers online. | NA | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | NA - We will not wholesale dark fiber | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA
NT10BIX5570073 | 2012 | 35,303 | Total project cost divided by total miles. Cost decreased as total miles increased as we didn't account for the Passive Optical Network (PON) | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline | 100 MB | Last mile business | 100MB | Middle mile | 25 | Last mile business | NA | MetroEthernet Direct Internet Access - 10MB - $414; 50 MB - $1,615; 100MB - $2,612 Metro Ethernet Point to Point - 50 MB - $675; 100 MB - $825; 1GB - $1,900 Community Anchor Institutions receive 25% discount if sign a five year contract PON - 4/1.5 - $54.95; 12/1.5 - $71.95; 25/25 - $91.00; 50/50 - $150; 100/100 - $249.00 | Network Management For Internet customers, BendBroadband has not deployed congestion or network management principles. There is no mechanism in place today to adjust a customerâ€™s experience based on the type of activities they are performing on the Internet. Shared bandwidth allocated to streaming video, flash video and peer to peer file sharing applications is managed to reduce network congestion during peak traffic times. BendBroadband does not block any lawful content, applications or services and does not discriminate in transmitting lawful network traffic. BendBroadband does not block or manage any specific protocols or protocol ports, except in cases of malware, spam and viruses to protect customers. Port blocks or preventive action may be used temporarily following notice to a customer who has violated the terms of service. Voice traffic may be prioritized to improve quality. BendBroadband does not otherwise target specific types of traffic based on technology, application or provider, modify protocol fields in ways not prescribed by the protocol standard, or otherwise inhibit or favor certain applications or classes of applications. BendBroadband does not engage in any â€œdeep packet inspectionâ€ or other inspection of content for non-diagnostic purposes, such as providing customers with specific advertising or recommendations based on use of the Internet. | Zero. | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | NA - We will not wholesale dark fiber | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA
NT10BIX5570073 | 2013 | 35,812 | Total project cost divided by total miles. | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline | 100MB | Last mile business | 100MB | Middle Mile | 25MB | Last mile | The Community Anchor Institutions seem to be mostly in two buckets: ones that received new service - average 20MB; ones that increased their bandwidth - average 100MB. We also have one who increased to 1GB. | MetroEthernet Direct Internet Access - 10MB - $414; 50 MB - $1,615; 100MB - $2,612 Metro Ethernet Point to Point - 50 MB - $675; 100 MB - $825; 1GB - $1,900 Community Anchor Institutions receive 25% discount if sign a five year contract within the grant period PON - 4/1.5 - $54.95; 12/1.5 - $71.95; 25/25 - $91.00; 50/50 - $150; 100/100 - $249.00 | Network Management For Fiber Internet customers, BendBroadband has not deployed congestion or network management principles. There is no mechanism in place today to adjust a customerâ€™s experience based on the type of activities they are performing on the Internet. Shared bandwidth allocated to streaming video, flash video and peer to peer file sharing applications is managed to reduce network congestion during peak traffic times. BendBroadband does not block any lawful content, applications or services and does not discriminate in transmitting lawful network traffic. BendBroadband does not block or manage any specific protocols or protocol ports, except in cases of malware, spam and viruses to protect customers. Port blocks or preventive action may be used temporarily following notice to a customer who has violated the terms of service. Voice traffic may be prioritized to improve quality. BendBroadband does not otherwise target specific types of traffic based on technology, application or provider, modify protocol fields in ways not prescribed by the protocol standard, or otherwise inhibit or favor certain applications or classes of applications. BendBroadband does not engage in any â€œdeep packet inspectionâ€ or other inspection of content for non-diagnostic purposes, such as providing customers with specific advertising or recommendations based on the use of the Internet. | Zero | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | One - due to confidentiality provisions can not provide the name and number of miles | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA
NT10BIX5570074 | 2010 | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 66680 | 56 | 0 | 280 | 12433 | 932 | 52979 | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | 0 | 0 | 0 | Contact Network Inc. is in process of negotiating collocation space in Jackson, MS and negotiations will be finalized in January 2011. In addition to this collocation space, we will have communication huts in each county. Service providers or customers that wish to make their own last mile connection into the network will be able to interconnect with us at the hut. We will also assist providers and customers with their last mile connection. | N/A | No comment | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities
NT10BIX5570074 | 2011 | 46,612 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 970Mbps | Currently we have 32 subscribers receiving 1000Mbps and 1 subscriber receiving 10Mbps. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 968Mbps. This number was calculated based on the fact that all 33 of our current customers were receiving 1.5Mpbs before upgrading to our service. Thirty two of our current customers are receiving 1000Mbps and one is receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 66680 | 120 | 3877 | 6552 | 12313 | 22994 | 20824 | Currently we have one wholesale customer purchasing dark fiber, PEG Bandwidth. We are leasing 76.26 fiber miles or 3877 strand miles to PEG Bandwidth. | 1035 | 260 | 0 | 775 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | No comment. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570074 | 2012 | 37308 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 948Mbps | Currently we have two subscribers receiving 100Mbps, one receiving 10Mbps , the rest are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 824Mbps. This number was calculated based on the fact that all 90 percent of our current customers were receiving 1.5Mpbs before upgrading to our service. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 64697 | 1137 | 26345 | 34651 | 69 | 101 | 2394 | Currently we have two wholesale customers purchasing dark fiber, PEG Bandwidth and Windstream. We are leasing 372 fiber miles or 25,830 strand miles to PEG Bandwidth and 50 fiber miles or 515 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on permits for railroads, department of transportation and pole attachments. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570074 | 2013 | 37709 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 755Mbps | Currently we have four subscribers receiving 500Mbps; twenty six receiving 100Mbps, thirteen receiving 50Mbps; three receiving 20Mbps, seven receiving 10Mbps , the rest are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 378Mbps. This number was calculated based on the fact that all 95 percent of our current customers were receiving 1.5Mpbs before upgrading to our service. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 20Mpbs, 50Mbps 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps, 20Mbps, 50Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 74062 | 4021 | 26446 | 43595 | 0 | 0 | 0 | Currently we have two wholesale customers purchasing dark fiber, PEG Bandwidth and Windstream. We are leasing 372 fiber miles or 25,931 strand miles to PEG Bandwidth and 50 fiber miles or 515 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on franchise agreements and permits for railroads, department of transportation and pole attachments. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570075 | 2010 | 0 | The first fiber miles will be put in service during the forth quarter of the project; this annual report only includes the first two quarters of the project | 0 | NA | 0 | NA | 1000000000 | 10Gb/s sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | N/A | N/A | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | N/A | 32624 | 0 | 0 | 0 | 32624 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as Level 3's. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | N/A | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). | For clarification, this project includes the improvement of access for 20 pre-existing transit customers.
NT10BIX5570075 | 2011 | 7105 | This number was calculated by using the Actual Total Cost from Project Inception through the End of the Current Reporting Period ($53,437,496) divided by the Number of Network Miles Leased (7,521). ($53,437,496 Ã· 7,521 = $7,105) | 0 | NA | 0 | NA | 1000000000 | 10Gb/sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 32624 | 7521 | 0 | 0 | 25103 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). Internet2 maintains a number of informal settlement-free-interconnect agreements with content providers and small internet service providers. There are no formal agreements that have been arranged in the last annual reporting period, nor are there any agreements currently in negotiation. | For clarification, this project includes the improvement of access for 20 pre-existing transit customers. We have 2 Letters of Intent that may result in 2 additional connections by Year 3, Quarter 1.
NT10BIX5570075 | 2012 | 0 | Internet2 leased all miles for this project. | 0 | NA | 0 | NA | 10000000000 | 100Gb/sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 36360 | 31434 | 0 | 0 | 31434 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). Internet2 maintains a number of informal settlement-free-interconnect agreements with content providers and small internet service providers. There are no formal agreements that have been arranged in the last annual reporting period, nor are there any agreements currently in negotiation. | For clarification, this project includes the improvement of access for 20 pre-existing transit customers and new access for 2 new customers.
NT10BIX5570075 | 2013 | 0 | Internet2 leased all miles for this project. | 0 | NA | 0 | NA | 100000000000 | 100GB/sec | 0 | NA | 8000000000 | NA | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 36360 | 36360 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). | For clarification, this project includes the improvement of access for 21 pre-existing transit customers and new access for 3 new customers.
NT10BIX5570076 | 2010 | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | 0 | Not Last Mile provider. | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | N/A - No facilities constructed to date | N/A - No facilities constructed to date; all services planned are described in the Application Service Deck. | N/A - No facilities constructed to date | N/A - Not there yet | 111312 | 0 | 0 | 0 | 111312 | 0 | 0 | NA - No facilities constructed to date | 0 | 0 | 0 | 0 | Sovernet Fiber Corp is not constructing any collocation facilities. Providers and/or customers will interconnect at Fairpoint collocation facilities. | None | Our project is just getting started. At this time we do not have any best practices/lessons learned to share. As our project progresses, we will include. | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | N/A | N/A
NT10BIX5570076 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | for data transport service | 0 | N/A | 0 | N/A | 0 | N/A | Network construction has not been completed; no CAI's have yet been connected or experienced an increase in broadband speed. | Retail services are not yet being provided since the network is still under construction. | Subrecipient has not begun to provide service. | Not applicable, as network is only middle mile. | 111312 | 0 | 0 | 0 | 111312 | 0 | 0 | N/A. | 0 | 0 | 0 | 0 | N/A. No collocation space is presently in service. | To our knowledge, no SDB has been subcontracted or received a subgrant under this award. | Entering contracts with multiple fiber vendors has alleviated concerns regarding ability to timely procure fiber. | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | N/A | N/A
NT10BIX5570076 | 2012 | $33,200 | Figure is preliminary, as OSP construction contractors have not yet rendered final invoices for any of the primary bid packages. Includes make-ready charges. | 0 | N/A | 0 | N/A | 10 Gbps | for data transport service | 0 | N/A | GigE,100 Mbps CIR | N/A | 0 | N/A | 79 Mbps. Average increase in broadband speed is calculated as difference between contracted-for broadband connection speeds before and after connection to BTOP network. | Only Direct Internet Access service as of end of reporting period. | 7a.: SFC will not manage or limit the content of communications traffic transiting SFC's network, except to the extent necessary to maintain reliable service. SFCâ€™s network management practices does not involve preferential routing of traffic on the basis of content or provider. SFC utilizes neutral traffic routing, and will enable connections to other carriers and to the public Internet. 7b.: No. | Not applicable, as network is only middle mile. | 111312 | 53 | 0 | 54288 | 56971 | 0 | 0 | N/A. | 0 | 0 | 0 | 0 | In the attached addendum, SFC has identified the Points of Presence where any carrier collocated in that facility would have the ability interconnect with SFC. A typical carrier-to-carrier network interconnection would use a fiber cross-connect to create an NNI. | To our knowledge, no SDB has been subcontracted or received a subgrant under this award. | N/A | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | Duncan Cable Television Southern Vermont Broadband Cooperative Educational Networks of America | N/A
NT10BIX5570076 | 2013 | $31,200 | Figure is preliminary, as OSP construction contractors have not yet invoiced SFC for all work that has been completed. The average cost for the Essex County build is $23,000 per mile | 0 | N/A | 0 | N/A | 10 Gbps | for transport service | 0 | N/A | 88 Mbps | N/A | 0 | N/A | 81 Mbps. We have incomplete data on the broadband speeds that were being purchased by CAI's prior to this project, but estimate the average was 7.5 Mbps. The average speed of service provided to CAI customers using the new network is 88 Mbps (symmetrical, and committed rate). Burst rates provided as WAN transport services can be substantially higher. This average is computed using the committed information rate of WAN transport services provided to each customer, or, for Internet-access-only services, the committed Internet bandwidth provided. | Retail services provided include: symmetrical Internet access starting at 10 Mbps, GigE WAN point-to-point or point-to-multipoint transport services with committed information rates starting at 100 Mbps and burstable rates up to 10 Gbps, combined transport and Internet delivered over the same connection. Prices vary on a case-by-case basis, as market and competitive conditions warrant. Attachment name: "VTA FiberConnect Rate Sheet.pdf" | 7a/b for the Essex dark fiber segment: VTA does not have any restrictive policies for dark fiber (it is open access) 7a.: SFC will not manage or limit the content of communications traffic transiting SFC's network, except to the extent necessary to maintain reliable service. SFC's network management practices do not involve preferential routing of traffic on the basis of content or provider. SFC utilizes neutral traffic routing, and will enable connections to other carriers and to the public Internet. 7b.: No. | No subscribers of broadband service provided through this project have dropped the service. | 117560 | 58780 | 2936 | 55556 | 288 | 0 | 0 | The VTA built 13 miles of fiber in Essex county. This segment is available to lease which connects to other dark fiber routes in the Northeast region of Vermont. The VTA expects this route to be utilized in a planned fiber route from Boston to Montreal by a service provider once the adjoining fiber routes are finished. | 852 | 828 | 4 | 20 | Sovernet is collocated in the incumbent central offices or PoPâ€™s listed in the APR addendum as â€œFacilitiesâ€. Other service providers can interconnect with Sovernetâ€™s network by collocating in those facilities as well and requesting permission from the owner of the facility for indirect cross-connects or direct cable connections between collocation bays. Interconnection points can be reached at the following locations: Brattleboro CO Brattleboro, Main St Wilmington CO Williamstown CO St. Johnsbury CO Hardwick CO Lebanon CO Stratton CO Manchester CO Rutland CO Middlebury CO Burlington CO Burlington POP Essex Junction CO Keene CO Manchester, Sundial Manchester CO Boston, 1 Summer For the Essex county dark fiber segment, access to use the fiber will be accommodated at any splice point along the route by contacting the VTA and entering into an IRU. | No SDB has been subcontracted or received a subgrant under this award. | N/A | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | Interconnect: 1) Three wholesale service agreements have been entered with broadband and communications service providers. Cloud Alliance Vanu Coverage Co. WaveComm 2) None. 3) No | Peering / Transit: 1) Peering or transit agreements have been entered with three service providers. Fairpoint Verizon Sidera 2) None. 3) No.
NT10BIX5570076 | 2014 | $34,000 | The baseline estimate for average cost was $36,290. In general, make-ready costs were less than estimated, but were offset by high average costs for construction. [Sovernet's cost per mile for 828 miles averaged $34,800. VTA's cost per mile averaged $23,000 for 13 miles.] | 0 | N/A | 0 | N/A | 10 Gbps | 10 Gbps for transport service as indicated in the baseline plan. | 0 | N/A | 92 Mbps | Average is calculated using the committed information rates for dedicated Internet access service and Ethernet transport. All DIA services offered are symmetrical. All Ethernet WAN products currently provided allow burstable (i.e., non-committed) transmission up to 1,000 Mbps, which matches the baseline plan. | 0 | N/A | 85 Mbps. We have incomplete data on the broadband speeds that were being purchased by CAI's prior to this project, but estimate the average was 7.5 Mbps. The average speed of service provided to CAI customers at the end of the award period was 92 Mbps (symmetrical, and committed rate). Burst rates provided with WAN transport services can be substantially higher. This average is computed using the committed rate of WAN transport service provided to each customer, or, for customers purchasing only Internet access service, the committed Internet connectivity bandwidth provided. | Retail services provided by subrecipient Sovernet Fiber Corp. include: symmetrical Internet access starting at 10 Mbps; point-to-point Ethernet transport and point-to-multipoint WAN services with committed information rates starting at 100 Mbps and burstable rates up to 10 Gbps; and combined transport and Internet packages. Prices vary on a case-by-case basis, as market conditions warrant. Price descriptions are included in the file attached to this report called "VTA FiberConnect Rate Sheet.pdf." | 7a: SFC has a policy of not managing or limiting the content of communications traffic transiting the SFC's network, except to the extent necessary to maintain reliable service. SFC's network management practices do not involve preferential routing of traffic on the basis of content or provider. SFC utilizes neutral traffic routing, and will enable connections to other carriers and to the public Internet. Access to the Essex County segment of the project is on a dark fiber basis, and therefore licensees are not subject network management policies. | No subscribers of broadband service provided through this project have dropped the service. | 119723 | 59081 | 0 | 60642 | 0 | 0 | 0 | Recipient VTA built 13 miles of fiber in Essex County. This segment, which connects to other dark fiber routes in the Northeast regionl of Vermont, is available to lease. The VTA expects this route be utilized in a planned fiber route between Boston and Montreal by a service provider, once the adjoining fiber routes are finished. Sub recipient Sovernet Fiber Corp. does not offer dark fiber. | 852 | 828 | 4 | 20 | Sovernet is collocated in the incumbent telco central offices or POP's listed in the APR Addendum as "Facilities". Other service providers can interconnect with Sovernet's network by collocating in those facilities and interconnect with Sovernet's network by requesting permission from the owner of the facility for indirect cross-connects or direct cable connections between collocation bays. In addition, subject to availability, approximately 20 sq feet of collocation space at the Sovernet Burlington facility is available for carrier interconnection. | No SDB was subcontracted or received a subgrant under the Award. | Create opportunities for last-mile providers to interconnect with your network at multiple locations along a route if possible, not just a limited number of interconnection points. Fiber access points (FAPs) can be a useful tool for facilitating this access. Serving cellular towers can be an important opportunities, but donâ€™t neglect emerging opportunities to serve small cells. This may require planning for serving many more locations along a route at a lower price point. For Community Anchor Institutions, the focus should not be just on providing internet access to individual locations. There are important efficiencies to be gained by linking CAIs together in Wide Area Networks. Create a simple database to track the status of Community Anchor Institutions and Points of Interconnection over a project. It will be useful, especially if there changes to the project. Focus early on obtaining necessary easements and rights-of-way; they may be the long pole in the tent of a project. | Vermont Telecommunications Authority | 105 | 44 | 7 | 22 | 31 | 29 |  | 73 | 5 | 0 | 316 | [REDACTED] | [REDACTED]
NT10BIX5570077 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 10213 | 0 | 0 | 0 | 4428 | 0 | 5785 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A
NT10BIX5570077 | 2011 | $106,656 | Variance is due to actual construction bid cost lower than original estimate | N/A | N/A | N/A | N/A | 1 Gbps | No variance | N/A | N/A | Mbps | N/A | N/A | N/A | N/A | N/A | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10213 | 336 | 0 | 2100 | 4428 | 0 | 5785 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A
NT10BIX5570077 | 2012 | 120,149 | Variance due to actual construction bid cost lower than original estimate; cost increased from prior year due to "in-town" higher costs of construction. | N/A | N/A | N/A | N/A | 10 Gbps | No variance | N/A | N/A | 10 Gbps | N/A | 100 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Recipient's broadband offerings are varied and pricing depends on the type(s) of service(s) and location. Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10535 | 3069 | 0 | 7466 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any are patched through project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A
NT10BIX5570078 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 10537 | 0 | 0 | 0 | 6480 | 0 | 4057 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A
NT10BIX5570078 | 2011 | $96,258 | No Variance | N/A | N/A | N/A | N/A | 1 Gbps | N/A | N/A | N/A | Mbps | N/A | N/A | N/A | Testing to occur and services anticipated to be available 1q012 | N/A | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10537 | 0 | 0 | 0 | 6480 | 0 | 4057 | N/A | 528 | 384 | 0 | 144 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A
NT10BIX5570078 | 2012 | 74,950 | Variance due to lower than estimated construction contractor bid | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 10 Gpbs | N/A | 10 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 11584 | 6780 | 172 | 4632 | 0 | 0 | 0 | N/A | 528 | 384 | 0 | 144 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any are patched through project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A
NT10BIX5570078 | 2013 | 62710 | Variance due to lower than estimated construction contractor bid | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 10 Gbps | N/A | 10 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 11584 | 6780 | 172 | 4632 | 0 | 0 | 0 | N/A | 528 | 384 | 0 | 144 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any, are patched through at project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining positive external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A
NT10BIX5570079 | 2010 | 0 | Consistent with Baseline - No Construction Activity until FONSI received | 0 | N/A - no households or businesses served | 0 | Consistent with Baseline - No Construction Activity until FONSI received | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | N/A. The project has not broken ground to begin construction yet. We anticipate benefits to both broadband speeds as well as reduced costs for those speed tiers. | The project is not providing any retail services. The project is only providing dark fiber only. Pricing for one pair of fibers will be about $250 per month for government and non profit anchor sites, and about $1,000 per month for commercial entities and enterprises. | A) - Network Management policies are still under development B) - No limiting or blocking of service | As the project is providing only dark fiber, not lit services, its typical network stakeholders will be CAIs and local communications companies, not "subscribers." Since the project has yet to start construction and has not yet connected any CAIs or interconnected with any communications companies, there have been no fiber connections to drop. | 0 | 0 | 0 | 0 | 23055 | 0 | 23055 | As the network has not yet been constructed, there are no current customers. | 750 | 6 | 0 | 18 | In addition to County collocation space, the network is being designed for future likely interconnection points with providers. There are over 20 facilities-based providers in the county. We are trying to meet and plan interconnection with them where feasible and where they desire it. Two definite collocation spaces will be in the data centers at the Clackamas Education Service District (approx. 4,000 sq/ft facility), and SandyNet (approx. 160 sq/ft facility), a retail service provider in the City of Sandy. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | (1) - No Agreement completed (2) - 7 Agreements currently in various levels of negotiation (3) - No requests have been denied | 1) No agreements have been completed. 2) 7 agreements are in various levels of negotiation; whether they include peering arrangements or not has yet to be determined. 3) No requests have been denied.
NT10BIX5570079 | 2011 | 0 | N/A. There were no Middle Miles in service as of 12/31/2011, as described in the January 2012 APR Reporting Guidance document. | 0 | N/A. The project will not directly serve any households or businesses. | 0 | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | N/A - The project construction has concentrated on Middle Mile Backbone and pole make ready. Lateral connections will begin in Q1 of 2012. We anticipate benefits to both broadband speeds as well as reduced costs for those speed tiers. The project will track the historic connection speeds and costs to CAI sites for reporting purposes as they are connected to our project. Current pre-project options range from no connectivity, T1, DSL and some fiber connections, though speed is questionable because the fiber connections are typically shared among multiple CAI sites. | This project is not providing any retail services - dark fiber only. Pricing for one pair of fibers is $250 per month for governmental and Non-Profit anchor sites. Commercial rates are $1,000 per month per pair of ring fiber. | A) - Network Management policies are on the project web site. However, the project has no services so there are policies related to services or network traffic. B) - No, we have never blocked or limited users. The project only provides dark fiber so there are no services to block or limit. | N/A. This project does not have subscribers. | 33834 | 0 | 0 | 17428 | 1970 | 7382 | 7054 | None. Wholesale customers are awaiting the rings to be finished before leasing. | 350 | 50 | 0 | 300 | Clackamas County owns 2 interconnect facility locations (hubs). One is the Development Services Building (200 sq/ft) and the other is North Station (150 sq/ft). Both are now operational and available. There are two other primary facilities currently under development with providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with providers. We are currently in negotiations with several local and regional providers which include collocation facilities, and the middle mile path was planned to be within one block of most central offices of local telecom providers. | None at this time | Not at this Time | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | (1) - No Agreement Completed (2) - 9 Agreements with providers currently in negotiation under Non-Disclosure Agreements. 20+ Service Level Agreements under review with CAI sites for connection. (3) - No requests have been denied. | (1) - No agreements have been completed. (2) - 9 Agreements are in various levels of negotiation; whether they include peering arrangements or not has yet to be determined. (3) - No requests have been denied.
NT10BIX5570079 | 2012 | $47,168 | Consistent with Baseline (it is 0.005% greater, or $269/route mile more, than baseline of $46,899). | N/A | N/A. The project will not directly serve any households or businesses. | N/A | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | The estimated average increase to CAIs is between 900mb-1Gig. Generally, schools and institutions of higher education were getting 100mb shared connections which were less than 100mb each. Generally, fire stations and county sites had T1s, which was 1.5mb, so the fiber resulted in almost full 1Gig increases. Typical basic off-the-shelf electronics provide a minimum of 1Gig service; some school districts are using 10Gig equipment. | N/A. This is a dark fiber project. No services are provided. | 7a. This is a dark fiber project and we will not be providing any services. We do not have any policies that limit bandwidth or traffic prioritization. 7b. No, and we have no way to limit or block customers. This is an open access, dark fiber project. The network is open to any service provider that wishes to connect. Once connected, the service provider can utilize the dark fiber network as needed to meet its needs. | N/A. This is a dark fiber project and we do not provide any lit services to the general public. Therefore, we have not had any subscribers drop our services. | 34088 | 223 | 133 | 33060 | 0 | 0 | 672 | No wholesaler signed on as of Dec 31, 2012 because the Middle Mile network has not been completed yet. | 350 | 50 | 0 | 300 | Clackamas County owns 2 interconnect facility locations (hubs) at the Development Services Building (DSB) (200 sq/ft), and North Station (150 sq/ft). Both are now operational and available. There are two other primary facilities with local providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with local providers. We are currently in negotiations with several local and regional providers which include collocation facilities, and the middle mile path was planned to be within one block of most central offices of local telecom providers. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | 1) No agreements completed. 2) One public last mile provider is using the fiber (City of Sandy’s broadband utility (SandyNet), which is a partner in our grant). No Service Agreements yet with a private provider, but there are about 10 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. Based on those conversations, we do not expect the first signed agreement with a private provider until construction of both fiber rings are completed, which is projected to be in Q1 2013. 3) No requests have been denied. | N/A as we only offer dark fiber and not any lit service.
NT10BIX5570079 | 2013 | $45,773 | Consistent with baseline ( it is a decrease of 2.4% from the baseline of $46,899) | N/A | N/A. The project will not directly serve any households or businesses. | N/A | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | The estimated average increase to CAIs is between 900mb-1Gig. Generally, schools and institutions of higher education were getting 100mb shared connections which were less than 100mb each. Generally, fire stations and county sites had T1s, which was 1.5mb, so the fiber resulted in almost full 1Gig increases. Typical basic off-the-shelf electronics provide a minimum of 1Gig service; some school districts are using 10Gig equipment. | N/A. This is a dark fiber project. No services are provided. | 7a. This is a dark fiber project and we will not be providing any services. We do not have any policies that limit bandwidth or traffic prioritization. 7b. No, and we have no way to limit or block customers. This is an open access, dark fiber project. The network is open to any service provider that wishes to connect. Once connected, the service provider can utilize the dark fiber network as needed to meet its needs. | N/A. This is a dark fiber project and we do not provide any lit services to the general public. Therefore, we have not had any subscribers drop our services. | 34205 | 273 | 2649 | 31283 | 0 | 0 | 0 | 1) Edge IT. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. 2) Silver Star. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. 3) Wave Broadband; 151.6 fiber miles leased. 4) Integra Telecom. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. | 450 | 100 | 0 | 350 | Clackamas County owns 3 interconnect facility locations (hubs) at the Development Services Building (DSB) (200 sq/ft), North Station (150 sq/ft) and at Water Environmental Services (WES) (100sq/ft). All hubs are now operational and available. There are two other primary facilities with local providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with local providers. We are currently in negotiations with several local and regional providers which include collocation facilities and the middle mile path is planned to be within one block of most central offices of local telecom providers. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | 1) One public last mile provider is using the fiber (City of Sandy’s broadband utility (SandyNet), which is a partner in our grant). We have 3 Service Level Agreements with Telecoms (Edge IT, Integra and Silver Star Telecom) but they are not utilizing any dark fiber before the end of the grant. Wave Broadband is a private last mile provider that is leasing fiber on the dark fiber network. 2) Clackamas County is currently in active negotiations with 5 other telecoms, all looking to connect and provide telecom services. 3) No requests have been denied. | N/A as we only offer dark fiber and not offer any lit service.
NT10BIX5570080 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no service has yet been made available to community anchor institutions. | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no retail services have yet been made available. | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - OnWav does not have any fiber components in its network. | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Delve into the details. Onwav's original deployment schedule needs to be amended as a result of the difficulties in solving an overlap issue with a BIP winner. OnWav approached the problem by initially mapping out the affected census blocks. This showed that descoping those blocks from OnWav's project would not have a meaningful impact, Final resolution is expected to be complete the first week of January. Resolving issues like these is best solved by examining the details. - Bring in experienced help. OnWav brought in outside help through an outside consulting firm to assist in project management, procurement and reporting for this project. That decision has allowed OnWav to continue maintaining its existing business while accelerating the deployment process. By taking advantage of the consultant's prior experience with BTOP requirements and network deployment, OnWav was able to augment its capabilities without increasing costs. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | - OnWav has spoken and is in negotiations with Celina Cable Company to provide them with backhaul, Internet, and Voice over Internet Protocol for their current customer base. - OnWav contacted Info-Ed regarding Onwav's ability to provide them with broadband access, backhaul, and Voice over Internet Protocol. | - OnWav is currently negotiating to replace its existing internet backhaul agreement. Currently there are two potential candidates: Deltacom and IRIS Networks. The new connection will provide more capacity and redundancy options.
NT10BIX5570080 | 2011 | 0 | OnWav signed an IRU to acquire 190.44 miles of dark Middle Mile fiber for a total cost of $2,079,604.80. However, as this is all existing fiber so far, This section does not apply. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, no homes are passed at this time. The initial households passed are expected to be turned up Q2 or Q3 2012 | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, there are no subscribers currently on the grant network. The initial households passed are expected to be turned up Q2 or Q3 2012. | 1 Gbps | OnWav anticipates being able to provide at least 1 Gbps. Once the network is closer to completion, OnWav expects to adjust this number upwards. | 10 Mbps / 2Mbps | OnWav has not yet finished deployment of it's Last Mile wireless network. OnWav anticipates being able to provide 10 Mbps / 2 Mbps. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, OnWav does not yet have any customers on the Middle Mile Network. OnWav anticipates being able to provide at least 130 Mbps. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, OnWav does not yet have any customers on the Last Mile Network. OnWav anticipates providing an average of 8 Mbps / 1.5 Mbps. | N/A. OnWav's network is still under construction and no sites have yet been turned up. As a result, no service has yet been made available to community anchor institutions. | N/A. OnWav's network is still under construction and no sites have yet been turned up. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. | N/A. Policies under development. OnWav's network is still under construction and no sites have yet been turned up. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. OnWav has an Acceptable Use Policy which is posted on its website. | N/A | 418 | 0 | 0 | 381 | 37 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Plan plenty of time for your RFP processes. Invariably, you will find that there are additional technical questions which need to be answered based on the RFP responses received, and you want to ensure you are not short-changing yourself by providing yourself insufficient time to review the responses and ask for clarifications from bidders. - Partner with local organizations. OnWav's new relationship with the local telephone cooperative has allowed it access to acquire dark fiber for the backhaul between it's tower locations. This backhaul will provide higher capacity and reliability than the microwave backhaul solution OnWav would need to deploy without the cooperation of the telephone cooperative. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection, but has not yet completed any agreements. OnWav has not denied any requests for interconnection. | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection, but has not yet completed any agreements. OnWav has not denied any requests for interconnection.
NT10BIX5570080 | 2012 | N/A | OnWav signed an IRU to acquire 190.44 miles of dark Middle Mile fiber for a total cost of $2,079,604.80. However, as this is all existing fiber so far, This section does not apply. | $188.04 | OnWav has not yet finished deployment of it's Last Mile wireless network. So far two markets have been deployed. The direct cost of deployment at these sites is $243,705. There are 1296 households in Jamestown and Allardt, for an average cost of $188.04 per household passed | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. So far two markets have been deployed. The direct cost of deployment at these sites is $243,705. OnWav does not yet have any households subscribers. As a result, this section does not apply. | 1 Gbps | OnWav is capable of offering service as high as 1Gbps. OnWav has not actively marketed this speed tier, but is available if approached. | 12 Mbps / 2Mbps | OnWav highest offered service tier is currently 12 Mbps download with 2 Mbps upload. | 460Mbps | OnWav currently measures approximately 460Mbps Down and 230 Mbps Up as an average speed on the middle mile portion of the network. However, there is not currently sufficient traffic on the network to guage this value with complete confidence. | 8 Mbps / 1 Mbps | Based on a combination of the average speed tier selected by customers and an average of the performance supplied by the network. | OnWav is currently offering CAIs free service as a backup to their existing service. As a result, while there has been no increase in broadband speed for these providers, the reliability and redudency of their service has significantly improved as they now have two sources of Internet access In the event of a failure of service to their primary access, | OnWav is currently only offering Internet services to CAI customers. In the future OnWav plans to offer backup VoIP lines to all customers as well. | Currently OnWav is only offering last mile customers speed tiers as backup service to their primary Internet service. As a result, OnWav is throttling customers to provide service within their relevant speed tier. Other than the aforementioned speed tier limitations, OnWav is not limiting or blocking customer from accessing any Lawful content, service, service provider or applications. Nor has OnWav prevented any consumers from attaching any legal device to the network. | No OnWav grant customers have dropped the broadband service provided through this project (0% churn). | 418 | 381 | 0 | 0 | 37 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Construction projects can take a long time to pass various governmental regulatory requirements (FAA, FCC, etc.). But once construction starts it can move extremely quickly Towers can take 6 months of regulatory filings, and then be built in the matter of weeks. - Repeat and Reiterate your Environmental Special Award conditions to your internal teams, vendors and subcontractors on a regular basis, both verbally as well as in writing Individuals and teams who are not dealing with them on a regular basis can easily forget, or mis-remember details. Repetition helps ensure memory and compliance in the field. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection.
NT10BIX5570080 | 2013 | $10920 | OnWav signed an IRU for 215.955 miles of Middle Mile fiber (2 strands) including both existing dark fiber and newly constructed fiber, for a total cost of $2,358,228.60. OnWav's cost per mile of fiber was $10,920 | $182.51 | The direct cost of deployment at all six last mile sites is $833,722. There are 4567 households in OnWav's Service Area, for an average cost of $182.51 per household passed | N/A | The direct cost of deployment at all six last mile sites is $833,722. OnWav does not have any households subscribers. As a result, this section does not apply. | 1 Gbps | OnWav is capable of offering service as high as 1Gbps. OnWav has not actively marketed this speed tier, but is available if approached. | 16 Mbps / 2 Mbps | OnWav highest offered service tier is currently 16 Mbps download with 2 Mbps upload. | 460 Mbps | OnWav currently measures approximately 460Mbps Down and 230 Mbps Up as an average speed on the middle mile portion of the network. However, because the CAIs current use the service primarily as backup, there is not currently sufficient traffic on the network to gauge this value with complete confidence. | 8 Mbps / 1 Mbps | Based on a combination of the average speed tier selected by customers and an average of the performance supplied by the network. | OnWav is currently offering CAIs free service as a backup to their existing service. As a result, while there has been no increase in broadband speed for these providers, the reliability and redudency of their service has significantly improved as they now have two sources of Internet access In the event of a failure of service to their primary access, | OnWav is currently only offering Internet services to CAI customers. In the future OnWav plans to offer backup VoIP lines to all customers as well. | Currently OnWav is only offering last mile customers speed tiers as backup service to their primary Internet service. As a result, OnWav is throttling customers to provide service within their relevant speed tier. Other than the aforementioned speed tier limitations, OnWav is not limiting or blocking customer from accessing any Lawful content, service, service provider or applications. Nor has OnWav prevented any consumers from attaching any legal device to the network. | Two of the locations OnWav had previously listed as served CAIs are no longer being listed as served CAIs by OnWav: One has since closed and was removed from our CAI list in a September 2013 CAI Change AAR. The other had some uncertainty of its current operational status as a valid CAI and in order to remain conservative it was also removed in the September 2013 AAR. As a result, we are not reporting them as subscribers. OnWavâ€™s final total subscribers are 154 CAIs (126 from Q2 2013, minus 2 dropped, plus 30 added Q3 2013) | 432 | 432 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. OnWav also leases rackspace in Gainesboro from Twin Lakes Telephone Cooperative for its Core Network Equipment and Internet Access. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Make sure to schedule a meeting between your Operations teams and Accounting Department to ensure that expenses and invoices are being booked to the correct accounts. Many vendor invoices are not explicit on what they are for and it's important to ensure that equipment is being booked to the correct account so it can be depreciated at the correct rate. - Document everything as soon as possible after work is complete. The longer you wait the harder it is for those involved to remember the details of the project as it happened. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection.
NT10BIX5570081 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Community Anchors have been installed or upgraded during this reporting period, consistent with the Baseline Plan. | No retail services have been offered as of the end of this reporting period, consistent with the Baseline Plan. | DC-CAN will provide quality-of-service capabilities. As part of District of Columbia Government, neither OCTO nor DC-NET have ever blocked lawful content to any subscriber. For DC-CAN, OCTO and DC-Net have no intention of blocking lawful content for any reason, except as required by law. | No subscribers have dropped broadband service. | 33120 | 0 | 0 | 0 | 33120 | 0 | 0 | Not applicable, as no dark fiber has been, or will be, offered to wholesale subscribers. | 4000 | 4000 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans ten (10) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these ten (10) sites, DC-Net currently operates and supports electronics at eight (8) of these sites; the other two sites are either under construction or are under lease negotiation currently. Once fully operational, seven (7) of the ten (10) DC-CAN sites will be owned by DC Government; the remaining three (3) will be leased. | No sub-contracts or sub-grants have been made as of the end of this reporting period. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at mega-POP sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | N/A. No Inter-connection Agreements executed this period, consistent with accepted Baseline Plan. None are currently being negotiated, and no requests have been denied. | N/A. No Peering and Transit Agreements executed this period, consistent with accepted Baseline Plan. None are currently being negotiated, and no requests have been denied.
NT10BIX5570081 | 2011 | 51166 | Through Dec 31, 2011, DC-CAN experience suggests a cost per fiber mile of approximately $51,166. Total costs for 45 miles of fiber are $2.3 million, with a resulting cost per fiber mile = $51,166. OCTO DC-Net has been able to procure equipment, materials and services at favorable rates when compared to the original budget. | 0 | DC-CAN is only a middle-mile project. | 0 | DC-CAN is only a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is only a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is only a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, or 1.54 Mbps. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of December 31, 2011, no retail services have been offered. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net (or DC-CAN have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped broadband service. | 33206 | 7614 | 0 | 0 | 25592 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 1200 | 1200 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans fourteen (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, DC-Net currently operates and supports electronics at eight (8) of these sites; the other sites are either under construction or are under lease negotiation currently. Once fully operational, ten (10) of the fourteen (14) DC-CAN sites will be owned by DC Government; the remaining four (4) will be leased. | DC-CAN has made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at mega-POP sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | N/A | N/A
NT10BIX5570081 | 2012 | 53000 | Through Dec 31, 2012, DC-CAN has spent $6.88 million in outside plant costs. With one hundred thirty (130) miles fiber installed, that results in a cost per mile of just under $53,000 per installed fiber mile. OCTO DC-Net has been able to procure equipment, materials and services at favorable rates when compared to the original budget. | 0 | DC-CAN is solely a middle-mile project. | 0 | DC-CAN is solely a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is solely a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is solely a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps or 50 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, 1.54 Mbps service, or digital subscriber line (DSL) service. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of December 31, 2012, no retail services have been offered. None are planned. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net (or DC-CAN have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped DC-CAN broadband services. | 33206 | 16412 | 0 | 0 | 16794 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 3600 | 3600 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans fourteen approved (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, DC-Net currently operates and supports electronics at nine (9) of these sites; the other sites are either under construction or are under lease negotiation currently. Once fully operational, ten (10) of the fourteen (14) DC-CAN sites will be owned by DC Government; the remaining four (4) will be leased. | DC-CAN has made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at inter-connection sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | DC-CAN has executed one (1) inter-connection agreement with a local high-speed internet service provider. The partner entity, DC Access, is a notfor- profit organization based in the District of Columbia; the intent of the agreement is for DC Access to provide last mile services to individuals and corporations. DC-CAN is currently in negotiations with two high-speed internet providers to offer last-mile services directly to households and businesses. DC-CAN has denied no requests for inter-connection. | N/A
NT10BIX5570081 | 2013 | 38,719.10 | Through Dec 31, 2013, the end of the grant closeout period, DC-CAN has spent $8,154,241.88 in outside plant costs. With approximately two hundred eleven (211) linear miles of fiber installed, that results in a cost per mile of $38,719 per installed fiber mile. | 0 | DC-CAN is solely a middle-mile project. | 0 | DC-CAN is solely a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is solely a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is solely a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps or 50 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, 1.54 Mbps service, or digital subscriber line (DSL) service. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of the end of the grant closeout period, December 31, 2013, no retail services have been offered. None are planned. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped DC-CAN broadband services. | 26459 | 26459 | 0 | 0 | 0 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 5400 | 5400 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net has installed fourteen approved (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, seven (7) are owned by DC Government, and the final seven (7) are leased. | Throughout the grant period, DC-CAN made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at inter-connection sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | DC-CAN has executed four (4) inter-connection agreement with local high-speed internet service providers. All four entities have presence within the District of Columbia; the intent is for all four to provide last-mile services to individuals and corporations. Through the entire grant period, DC-CAN has denied no requests for inter-connection. | N/A
NT10BIX5570082 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | None this period | None this period | None this period | None this period | 0 | 0 | 0 | 0 | 0 | 74304 | 107616 | None this period | 0 | 0 | 0 | 0 | None this period | None this period | Open, clear, timely and consistent communication with NTIA FPO and other Federal contacts has led to streamlined addressing of issues that have surfaced during the first year of this project. Following clear PMBOK practices and regular (weekly and monthly) project management meetings with both prime recipients and sub-recipients allows for the entire project team to remain current with project activities and challenges as they surface. Recommend early public relations on BTOP projects. Would like to leverage other communications plans from other BTOP projects in the future. We have been meeting with other local projects to review challenges and leverage expertise. With the project having been awarded in July of this first year, there are a number of practices that are beginning to emerge as best and will likely appear in this area in subsequent Annual Reports. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | None this period | None this period
NT10BIX5570082 | 2011 | 0 | 0 at this time due to current construction phase. | 0 | 0 at this time due to current construction phase. | 0 | 0 at this time due to current construction phase. | 10GB | No variance from plan. | 0 | 0 at this time due to current construction phase. | 1.3GB | No variance from plan. | 0 | 0 at this time due to current construction phase. | Average broadband speed is estimated to increase to 1.3 GB which is based on averaging their current speed factored with an estimated 20x increase in speed. | No retail services were provided in 2011. | 7a. We are utilizing BTOP optical network equipment to light fiber between the University of New Hampshire and Keene State College. The equipment is dividing a 10 GB wave into 1 GB VLANS. Bandwidth is being allocated for internet services, video conferencing, and disaster recovery. We use Quality of Service (QOS) for voice and video services. 7b. No consumers have been limited or blocked from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 135936 | 0 | 0 | 17280 | 0 | 0 | 118656 | No leasing in 2011. | 0 | 0 | 0 | 0 | Colocation space is owned. | None | a. Communicate frequently with state and local officials frequently on the project status and benefits it can bring to the region. Focus on whatâ€™s important, economic, educational, and medical seem to be the hot buttons for our project. b. Work closely with the state regulatory groups. We meet quarterly to provide updates both positive and negative. In challenging situations we make every effort to work through the problems independently first before reaching out to the regulating authorities. They appreciate the efforts and if it does come time to actually meet over an issue we find them to be more receptive to our project. c. Weâ€™ve worked very hard on our relationships with the local utility companies. Making adjustments when necessary to accommodate their processes and communicating regularly helps to keep things moving and provides a level of visibility necessary for such a big project. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | 1. Interconnection agreements are in place with Keene State College and DSCI corporation. 2. We are currently working on interconnection agreements with Plymouth State College, Dartmouth College, NH Community College System, Granite State College, UNH Law in Concord, and Northern Community Investment Organization. 3. We have not denied requests for interconnection. | N/A
NT10BIX5570082 | 2012 | 40,000 | Estimated at 40K due to fixed price contract with New Hampshire Optical Systems. Actual average is trending toward 53K per mile. Some sections of make-ready have cost over 250K per mile. | 0 | No households available for subscription in 2012 as network is under construction. Construction occurred later than baseline estimates due to delays in match funding and longer than expected make ready time frames. | 0 | No subscribers in 2012 as network is under construction. Construction occurred later than baseline estimates due to delays in match funding and longer than expected make ready time frames. | 10GB | No variance from plan. | 1GB | No variance from plan. | 1.3GB | No variance from plan. | 0 | 0 at this time due to current construction | Average broadband speed is estimated to increase by 9.5Gbps, approximately a 20x increase. Keene State College aggregate 400Mbps to 10Gbps, delta = 9.6 Gbps UNH aggregate 600Mbps to 10Gbps, delta = 9.4 Gbps | New Hampshire Optical Systems provides wholesale dark fiber for lease on a fiber mile basis. Pricing plan is attached. NH FastRoads will provide retail last mile services but is still under construction and pricing plans have not yet been established. | 7a. USNH is using BTOP Optical network equipment to light fiber between the University of New Hampshire and Keene State College. The equipment is dividing a 10GB wave into 1GB VLANs. Bandwidth is being allocated for Internet services, video conferencing, and disaster recovery. We use Quality of Service (QOS) for voice and video services. 7b. No consumers have been limited or blocked from accessing lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | 0 | 185276 | 2659 | 19152 | 74503 | 7260 | 3456 | 78246 | USNH 9108 fiber miles Company A 1050 fiber miles Company B 1000 fiber miles Company C 50 fiber miles | 8 | 8 | 0 | 0 | These locations are collocation facilities for the USNH fiber leased from NHOS. There will be additional interconnect points as NHOS fiber is completed and becomes available for lease but this was not the case as of December 31, 2012. DSCI Corp (commercial co-lo facility), 1 Sundial (ISP/carrier hotel), Manchester, NH - UMAINE is leasing a rack at DSCI and UNH has an agreement with UMAINE to share use of that rack and has installed BTOP DWDM equipment in that rack. This site is currently utilized to provide the USNH interconnection between the University of New Hampshire data center and the Keene State College data center. ADDITIONAL RESPONSE TO Q11 - The remaining two sites below are owned by the University System of New Hampshire and are not available for commercial co-location use. BTOP DWDM equipment is installed in one rack (4 sq ft) at each facility: Keene State College Data Center, 229 Main St, Keene, NH University of New Hampshire Data Center, 1 Leavitt Lane, Durham, NH | None | Project recommends utilizing current and very conservative make-ready costs estimates and timelines because: Make-ready time frames have exceeded estimates. This is due to a combination of factors including some areas having more make-ready needed than originally expected (especially in urban areas, highway crossings and major route intersections). Other factors include the number of third party make-ready moves that need to occur and higher than expected costs to complete make-ready. The process to coordinate third party moves was more complex than expected and we have worked closely with the New Hampshire Public Utilities Commission and state and federal officials to work around obstacles that have arisen during construction. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | 1. NHOS has dark fiber IRU agreements with 4 entities. Three of the entities have requested confidentiality agreements. The fourth entity is the University of New Hampshire. 2. NH FastRoads has been in negotiations with three Internet service providers and is finalizing an agreement with a network service provider, but no agreements were signed in 2012. New Hampshire Optical Systems is currently negotiating agreements for use of dark fiber and is working to connect the NH BTOP Network with BTOP assets in Maine, Massachusetts, and Vermont. 3. No one has been denied requests for interconnection. | None
NT10BIX5570082 | 2013 | $49,639 | Baseline was $33,663 The make-ready costs for aerial construction were much higher than anticipated. The Department of Transportation (DOT) portion of the project constructed 20 miles of fiber in conduit along Interstate 93 at a significantly higher cost than the aerial construction. Cost/MILE: NHOS $41,176 (592 miles: Route mileage was derived from GIS middle mile and lateral segment â€œas builtsâ€. Some overlap of middle mile and lateral miles exists due to the tracking mechanism within the GIS system. ) DOT averaged $299,968 per mile (20 miles). | $3,433 | Baseline was $1,770. The original baseline projection was calculated using only the two Last Mile communities, Enfield and Rindge. In reality, the entire NH FastRoads portion of this project is Last Mile. There are 1,266 households passed, 363 CAIs passed, and 254 businesses passed totalling 1,883 "households" passed. Cost for labor ($2,066,734), equipment ($2,150,902) and site preparation expenses ($2,247,067) total $6,464,703. This total cost of $6,464,703 divided by 1,883 last mile connections equals $3,433 per connection. Throughout this project we experienced Make Ready costs that exceeded the original budgeted amounts. These extra costs explain the difference between baseline and actual. Note - If you include the prorated average cost for 48 strands of the middle mile fiber utilized by NH FastRoads, the average cost per household passed jumps to $4,610. Theses costs are already included in the Average cost per new mile (Middle Mile) question. | $29,655 | Baseline was $8,681. At the end of 2013, 162 residents, 47 CAIs, and 9 businesses (218 total) subscribed to the NH FastRoads Last Mile network. Total cost ($6,464,703)/218=$29,655). Baseline estimates assumed subscribers would start taking service in January 2013. Due to construction delays, the network was not available to subscribers until the end of September 2013. Had the network been ready in January 2013 and, assuming the same subscription rate as Q4 2013, the average cost per subscriber could have been been much lower ($6,464,703/720 = $8,979). | 10Gbps | Baseline 10Gbps. No variance. | 1Gbps | Baseline was 100 Mbps. At the time the baseline was calculated, NH FastRoads assumed the maximum speeds would be 100 Mbps. The capabilities of the equipment ultimately purchased under the grant now allow an improved maximum of 1 Gbps. | 1.9Gbps | Baseline was 10Gbps The network has the capability of multiple 10Gbps connections, but is currently provisioned for an average of 1.9Gbps. | 20Mbps | Baseline was 100Mbps. The last mile calculations are based on NH FastRoads only. Current customers taking service have opted for an average of 20Mbps. Network construction delays reduced the number of subscribers that were able to be connected before grant closure. Since the contracts for the higher speeds typically taken by CAIs and businesses take longer to complete than requests for residential service, the higher speed connections were not realized in time for this calculation. | The CAI broadband speeds increased from a pre-grant average of 16 Mbps to the grant completion average of 104 Mbps resulting in an overall average increase of 88 Mbps. Dartmouth College, Keene State College, Plymouth State University, and the University of NH already had high bandwidth connections prior to the grant (400Mbps to 1.5 Gbps). These would have significantly skewed the data so they were not included in the above computed averages. These four institutions went from an average of 813 Mbps to an average of 8.625 Gbps. If included in the overall averages, the result would be a pre-grant average of 61 Mbps to the grant completion average of 584 Mbps resulting in an average increase of 523 Mbps. Many of the pre-grant speeds are estimates based on the best information we have available. It should also be noted that many of the pre-grant connections were asymmetrical and have been replaced with symmetrical connections. | NH FastRoads, the last-mile component, provides last mile retail services via resellers. The wholesale base prices per subscriber for these resellers noted in the FastRoads section of attached price list. USNH is leasing 12 strands of fiber from NHOS and is providing lit service to education CAIs at between 50Mbps and 10Gbps. The pricing is noted in the University System of New Hampshire section of the attached price list. | 7a. Each of the components of the project provide some type of bandwidth limitations and traffic prioritization corresponding to the client being served: USNH has provisioned its network into multiple 10 Gbps waves and multiple 1 Gbps VLANs. Bandwidth is being allocated for Internet services, video conferencing, and disaster recovery. USNH uses Quality of Service (QoS) for voice and video services. The NHSafeNet closed public safety microwave network prioritizes traffic with highest priority QoS for the NH Department of Safety and NH Public Television. Each of the stakeholders have defined peak information rates to ensure that there is no chance of oversubscribing. NH FastRoads prioritizes its traffic using priority bits on the network. VoIP and Point-to-Point or Point-to-Network Traffic have the highest priority, followed by business class traffic, leaving residential traffic as best effort. 7b. No entities have been limited or blocked from accessing lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. NH FastRoads Acceptable Use policies indicate use must be lawful. | No dropped subscribers or turnover. | 142664 | 15700 | 19713 | 107251 | 0 | 0 | 0 | [REDACTED] | 152 | 152 | 0 | 0 | The 750 miles of middle-mile fiber infrastructure is owned and operated by sub-awardee, New Hampshire Optical Systems, LLC (NHOS). Access to fiber strands in the NHOS cable infrastructure is available virtually anywhere along the middle-mile route via aerial or manhole splicing. The NHOS cable infrastructure has splice cases at a maximum of every 20,000 feet or closer. Service Providers can access this network at DSCI in Manchester, NH, and BayRing Communications in Portsmouth. The last mile component, NH FastRoads, is located in the Keene Technology Center collocation facility and NH FastRoads provides rack space to their own Service Providers at this location. NH FastRoads is also located in the Hanover, NH Community and Senior Center building. The agreement with the Town of Hanover is not exclusive, and on request, the Town would consider allowing other service providers access to the collocation space. NH FastRoads utilized BTOP funds to provide leasehold improvements to the Keene technology Center noted above. NH FastRoads also utilized BTOP funds to provide leasehold improvements at a HUB location in the ATA Construction, LLC building in Rindge, New Hampshire. (Note - this site is not an interconnection facility) | N/A | 1) Make-ready in New Hampshire is significantly more expensive and takes much longer than expected. We learned through this project that the pole attachment processes and regulations are not clearly defined which led to both delays and cost overruns. This process will discourage build out for economic development purposes. Recruiting a business to your region requires a nimbleness that the current process does not support. 2) Work closely with the state regulatory groups and provide updates, both positive and negative. In challenging situations, we made every effort to work through the problems independently first before reaching out to the regulating authorities. They appreciate the efforts and if it does come time to actually meet over an issue, we find them to be more receptive to our project. 3) Communicate frequently with state and local officials frequently on the project status and benefits that it can bring to the region. Focus on whatâ€™s important--economic, educational, and medical seem to be the hot buttons for our project. 4) Weâ€™ve worked very hard on our relationships with the local utility companies. Making adjustments, when necessary, to accommodate their processes and communicating regularly helps to keep things moving and provides a level of visibility necessary for such a big project. 5) Open access networks are a new concept. Attracting service providers into this environment has been a challenge. However, it is with open access that the region finally has real competition. This competitive environment is bringing down pricing and making big broadband affordable and plentiful. 6) Although welcome on the open access network, incumbent carriers have chosen to overbuild this network with DSL instead of delivering services over the open access network. 7) To support the smaller networks, companies providing network operations, outside plant construction, and provisioning services would be helpful to save costs with economies of scale. 8) From a grant management perspective, we discovered that baselines would have been more accurate if they had been set after engineering was completed. 9) Some of the data requested during closeout would have been more easily delivered if we had known up front what was going to be required. It would have been easier to extract some of the data if tracking systems were put in place at the beginning of the project to categorize some of the items. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | [REDACTED] | [REDACTED]
NT10BIX5570084 | 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010. The only contract in 2010 that was issued was for the Environmental Assessment. The recipient was not a SDB entity. | Ensure that you have the correct and most recently updated forms for reporting and submission. Be open about all the issues you are experiencing, especially regarding the EA as it was an intensive process. You will face many obstacles that seem insurmountable but seek BTOP counsel in an effort to obtain clarity and direction. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010
NT10BIX5570084 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Iowa Health System (IHS)/Broadband, Inc. (BBI) have not provided pricing plans since construction and deployment have not begun. | Broadband, Inc. has not begun providing service, however, the network management policy does not limit or prioritize traffic up to the agreed purchased service level. No limits are imposed for lawful access or use of the network. | N/A | 6522 | 6100 | 0 | 0 | 224 | 198 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered any interconnection agreements, BBI is in negotiations for a middle mile transit agreement with one customer, and BBI has not denied any request for interconnection. Broadband, Inc. is currently in discussions with 14 potential customers to start working towards negotiations for agreements with customers. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered any peering and/or transit agreements, BBI is in negotiations for a middle mile transit agreement with one customer, and BBI has not denied any request for peering and/or transit agreements. Broadband, Inc. is currently in discussions with 14 potential customers to start working towards negotiations for agreements with customers.N/A
NT10BIX5570084 | 2012 | $10,000 | Deep urban construction and limited amounts of construction builds have increased the cost to obtain construction vendors in Iowa. Cost was also driven up due to the waiting time to obtain an EA and vendors waiting upon approval to start the small construction activities in rural Iowa as well. | N/A | N/A | N/A | N/A | 10G | No variance from baseline plan | N/A | N//A | 100M | No variance from Baseline Plan | N/A | N/A | N/A | Iowa Health System (IHS)/Broadband, Inc. (BBI) is working through pricing plans for retail services but currently has not started offering. | Broadband, Inc. network management policy does not limit or prioritize traffic up to the agreed purchased service level. No limits are imposed for lawful access or use of the network. | N/A | 6522 | 6100 | 198 | 0 | 224 | 0 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. Two years into the BTOP project, construction costs have increased as a result of limited construction activities to build in different locations throughout Iowa and the waiting time for EA approvals have been a challenge as a result of the project modification to eliminate wireless towers and construct broadband fiber. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has entered into 7 interconnection agreements with last mile provider customers and BBI has not denied any request for peering and/or transit agreements. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered into any peering agreements. BBI currently has 9 middle mile transit agreements with customers.
NT10BIX5570084 | 2013 | $10,000 | Deep urban and longer rural fiber construction builds boring through rock were a direct result of increased construction costs. Cost was also driven due to longer than expected winter season that condensed the construction schedule. | N/A | N/A | N/A | N/A | 10G | No Variance from Baseline Plan | N/A | N/A | 100M | No Variance from Baseline Plan | N/A | N/A | N/A | Wholesale Internet Access Service provides managed access to Internet via Broadband Inc. facilities designed for small to mid sized internet service providers. Pricing attached. | N/A | N/A | 6522 | 6522 | 198 | 0 | 224 | 0 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. Construction costs have increased as a result of limited construction activities to build in different locations throughout Iowa and the waiting time for EA approvals have been a challenge as a result of the project modification to eliminate wireless towers and construct broadband fiber. Construction costs continue to be limiting in how much fiber can be built to customers to continue these connections. This continues to be the difficulty when signing rural customers. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Enseva Data Center Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer City of Maquoketa City of Charles City BBI has not denied any request for peering or transit agreements. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered into any peering agreements. BBI currently has 14 middle mile transit agreements with customers.
NT10BIX5570085 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in broadband speed provided to community anchor institutions has been achieved. We are still completing the Environmental Assessment and negotiating a resolution of the overlap with NTIA. | N/A | VTel posts our terms of service and network managment policies on our website where customers can access them. We do not prevent consumers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 0 | 0 | 0 | 18504 | 0 | 0 | N/A | 544 | 9 | 9 | 526 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. | One of the lessons learned is that it is a critical first step to quickly start on the environmental assessment portion of the project. It is also important that the process be handled by someone or an organization that has had experience with similar environmental issue and has the ability to properly coordinate with local, state and federal governmental organizations. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered into. 0 Interconnection agreements being negotiated 0 Interconnection agreements denied | 1 Peering Relationship entered into. VTel entered into a peering relationship with Telx Peering exchange at 60 Hudson Street, New York, NY 0 Peering or Transit Agreements being negotiated. 0 Peering or Tranist Agreements denied.
NT10BIX5570085 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in broadband speed provided to community anchor institutions has been achieved. Construction will begin in the 1st quarter of 2012. | N/A | VTel posts our terms of service and network management policies on our website where customers can access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 0 | 0 | 0 | 18504 | 0 | 0 | N/A | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. We are entering into a construction contract with a socially and economically disadvantaged small business. | As a result of our BTOP site visit in October, we have learned that in order to remain compliant with the final award agreement, it was necessary to make a few changes. Although construction is not scheduled to begin until the first quarter of 2012, it was necessary to increase the rate in which we were reaching out to community anchors. By doing that, we quickly became aware that there might be changes to the list proposed originally, and determined through the overlap process, based on many different factors including economic conditions, market competition from other providers, changes in location due to tropical storm Irene, etc. VTel also needed to adopt and document procedures to adequately comply with the financial management guidelines for the BTOP project. Processes are in place to identify allowable costs, however the policies needed to be clearly outlined, to ensure that BTOP guidelines are being followed. The last performance improvement plan that was identified concerned identifying that all BTOP terms and conditions be included in any contracts entered into during the NTIA grant period. We have made corrections to all existing contracts, and any new contracts are being reviewed by VTel's attorneys to make sure that they include all the necessary terms and conditions required. Several CAI's listed on the attached "Annual PPR CCI Addendum" have been stricken at the request of NTIA. Our understanding is that another BTOP funded project has included these and despite Vtel having built fiber prior to BTOP, these CAI's remain in the other BTOP project's scope. While VTel will not expend any grant funds to overbuild the fiber we've already placed, VTel's grant is also upgrading our network's overall speed and capacity. These pre-existing customers will receive improved service from VTel if they choose to remain our customers. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this | 7 Peering Relationship entered into. 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied.
NT10BIX5570085 | 2012 | EST $35,000 | This is an estimate based on engineering, make ready, and construction costs. | 0 | N/A | 0 | N/A | 100 gb | No variance from base line. | 0 | N/A | 75mg | No variance from base line. | 0 | N/A | Although there may be increases in broadband speed, the final increase will not be measurable until the full network has been upgraded. | N/A | VTel posts our terms of service and network management policies on our website where customers can access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 5965 | 0 | 0 | 12539 | 0 | 0 | N/A | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. We are entering into a construction contract with a socially and economically disadvantaged small business. | Management of the make ready process has proven to be the most difficult part of this project. Although the utility pole owners have guidelines for time frames in getting the work done, it is necessary to actively manage and track the process, in order for the construction deadlines to be met. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. | 7 Peering Relationship entered into. 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied.
NT10BIX5570085 | 2013 | 88044 | Our baseline target of $82,975 per mile. We fully expect that we will be on or under our baseline target as our miles increase during the last construction phase. | 0 | n/a | 0 | n/a | 100Gb/s | We are happy to report that we have started offering speeds up to 100Gb/s, which is improved and faster access than in our baseline. | 0 | n/a | 72Mb/s | No variance from base line | 0 | n/a | We have reviewed the speeds that our CAI's contracted for before the BTOP project as well as the speeds contracted for now that the grant is underway. We took the average total speed prior and the average total speed subsequent and calculated the delta between the two to come up with a speed increase to be 420 Mbps. | Community Anchor institutions can avail themselves with one of our seven pricing options outlined on the attached CAI pricing sheet. We offer the following: #1 10Mbps of internet access bursting up to 25Mbps #2 25Mbps of internet access with bursting up to 50Mbps #3 50Mbps of internet access with bursting to 100Mbps. #4 100Mbps with bursting to GigE. #5 200Mbps with bursting up to GigE h #6 Dedicated GigE "spoke" back to any of the above #7 100Mbps of dedicated access with bursting to GigE to any of the above | VTel posts our terms of service and network management policies on our web site therefore any and all customers have access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | n/a | 18504 | 5965 | 0 | 0 | 12539 | 0 | 0 | n/a | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at primarily third party collocation facilities/Central Offices. The Central Offices are: White River Junction CO, Chelsea Hut, Montpelier CO, Waterbury CO, Essex CO, Burlington CO, Burlington Telecom CO, New Haven Cabinet, Brandon Hut, Rutland CO, Waterbury CO, Stowe CO, Morrisville CO, Milton CO | Our Prime Construction Contractor is a SDB (Eustis Cable Enterprises) and we have contracted with them to build the entire network. | Management of the make ready process continues to be the most difficult part of this project. Although the utility pole owners have guidelines for time frames in getting the work done, it is necessary to actively manage and track the process in order for the construction deadlines to be met. Consistent scheduled meetings where all parties can see the work work that is being completed, and the work not yet done are key. These status meetings can be used to raised issues, and work through roadblocks to resolution to keep progress on track. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | We have 6 pre-existing agreements with broadband wholesale and last mile providers whose connection will be upgraded (all were existing customers prior to our BTOP project) as a result of this project once the core optical network is installed. These customers are: Earthlink, Topsham Telephone, Burlington Telecom, Wavecomm, Great Awk (formerly Finowen and Light Tower (formerly Sidera). 6 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. | 1. Netflix 2. Google 3. Apple 4. ISPrime.com 5. FPL FiberNET LLC 6. BroadbandONE 7. Webair 8. Amazon 9. TelX 10. Free Software Foundation (GNU) 11. TowardEX 12. Studsvik Scandpower 13. OCCAID 14. RCN Cable 15. Akamai 15 New Peering Relationship entered into (all entered into subsequent to the project starting) 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied.
NT10BIX5570085 | 2014 | 82,029 | Baseline was $82,975 and we were able to come in under that target. | 0 | N/A | 0 | N/A | 100Gb/s | We are happy to report that we have started offering speeds up to 100Gb/s which is improved and faster than our baseline | 0 | N/A | 72Mb/s | No variance from baseline. | 0 | N/A | We have reviewed the speeds that our CAI's contracted for before the BTOP project as well as the speeds contracted for now that the grant is complete. We took the average total speed prior and the average total speed subsequent and calculated the delta between the two to come up with a speed increase to be 420 Mbps. | Community Anchor institutions can avail themselves with one of our seven pricing options outlined on the attached CAI pricing sheet. We offer the following: #1 10Mbps of internet access bursting up to 25Mbps #2 25Mbps of internet access with bursting up to 50Mbps #3 50Mbps of internet access with bursting to 100Mbps. #4 100Mbps with bursting to GigE. #5 200Mbps with bursting up to GigE h #6 Dedicated GigE "spoke" back to any of the above #7 100Mbps of dedicated access with bursting to GigE to any of the above | VTel posts our terms of service and network management policies on our web site therefore any and all customers have access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | 1 business has dropped service and that was solely due to non-payment | 21507 | 21507 | 0 | 0 | 0 | 0 | 0 | N/A | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at primarily third party collocation facilities/Central Offices. The Central Offices are: White River Junction CO, Chelsea Hut, Montpelier CO, Waterbury CO, Essex CO, Burlington CO, Burlington Telecom CO, New Haven Cabinet, Brandon Hut, Rutland CO, Waterbury CO, Stowe CO, Morrisville CO, Milton CO | Our Prime Construction Contractor is a SDB (Eustis Cable Enterprises) and we have contracted with them to build the entire network. | Management of the make ready process was the most difficult part of this project. Although the utility pole owners have guidelines for time frames in getting the work done, it is necessary to actively manage and track the process in order for the construction deadlines to be met. Consistent scheduled meetings where all parties can see the work work that is being completed, and the work not yet done are key. These status meetings can be used to raise issues, and work through roadblocks to resolution to keep progress on track. NOTE: AS WE ARE IN THE PROCESS OF FINAL CLOSEOUT AND MAPPING WE HAVE ESTIMATED THE STRAND MILES IN QUESTION 11 AND AS OUR MAPPING PROJECT IS FINALIZED WE WILL UPDATE INFORMATION AS NECESSARY. THE COST PER MILE IN QUESTION 1 MAY ALSO CHANGE AS WE FINALIZE MAPPING AND COSTS. | Vermont Telephone Company, Inc. | 56 | 9 | 3 | 11 | 22 | 2 |  | 6 | 15 | 1 | 125 | We have 5 pre-existing agreements with broadband wholesale and last mile providers whose connection will be upgraded (all were existing customers prior to our BTOP project) as a result of this project once the core optical network is installed. These customers are: Earthlink, Topsham Telephone, Burlington Telecom, Wavecomm, and Light Tower (formerly Sidera). Great Awk (formerly Finowen) was disconnected for non-payment. 5 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. | We are peered with: 1. Netflix 2. Google 3. Apple 4. ISPrime.com 5. FPL FiberNET LLC 6. BroadbandONE 7. Webair 8. Amazon 9. TelX 10. Free Software Foundation (GNU) 11. TowardEX 12. Studsvik Scandpower 13. OCCAID 14. RCN Cable 15. Akamai 15 New Peering Relationship entered into (all entered into subsequent to the project starting) 0 Peering or Transit Agreements being ne
NT10BIX5570086 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include â€œcarrier hotelsâ€ such as the 511 building and TriTech buildings in Minneapolis as well as Qwest central office co-locations throughout the state. | N/A | Enventis has learned that it is very important to document everything and keep a central repository. We have started a Grants File to track all required documents and reporting along with anything that is project related. We continually update and organize that folder to make it easy to find required information. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | N/A | Enventis is currently negotiating transit agreements with three separate wholesale customers.
NT10BIX5570086 | 2011 | 53,972.95 | Due to location and conditions this was the most expensive part of the project. Remaining miles will be less bringing the overall average down. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 50mbps | We are providing 50mbps service to one CAI site at this time. | 0 | N/A | We are currently serving one community anchor institution. They were upgraded from a point to point T1 to 50Mbps Ethernet service. | Enventis has completed a build to a Mayo Clinic site and now provide improved access at this location. The site previously had a T1 of service and now enjoys 50Mbps. This project seeks to provide 100Mg to 10G lit capacity as well as leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that are based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 41721 | 0 | 0 | 15072 | 0 | 0 | 26649 | Enventis intends to wholesale dark fiber as part of this project and we are actively negotiating four Agreements with three customers. We have not yet signed these documents and as such are not currently leasing any dark fiber to customers. | 300 | 200 | 0 | 100 | In addition to the collocation space available at the two new Point of Presence sites, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state. | N/A | Through the implementation of this federal project, Enventis has learned some valuable lessons that may benefit other federal recipients. These include: Federal projects require consistent and thorough documentation; it is easier to track progress and document open issues as they unfold versus revisiting the matter afterward and trying to recall important facts, decisions or dates. Census tracts and census blocks can vary significantly in geographic size; it may benefit a recipient to carefully review each before requesting one versus the other as it may unexpectedly narrow the proposed funded service area. Use the guidance and information that is available on the BTOP websites. Take advantage of conferences, drop in calls and webinars that are offered to stay up to date on processes. Make every effort to ensure that all employees who are part of the project are aware of requirements to stay in compliance. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | Enventis has completed three interconnection agreements during the reporting period. Completion of one agreement provided Enventis access to a major carrier hotel in Minneapolis which is the preferred endpoint for three customers; the associated dark fiber agreements are currently in negotiation. Enventis also entered into two joint construction agreements with other BTOP recipients to collaborate on de minimus shared segments along the long haul route. Enventis adheres to a defined policy on Network Openness and Non-Discrimination and fully explores each interconnection request received. | Enventis is in active negotiations with three customers on four dark fiber agreements. Enventis adheres to a defined policy on Network Openness and Non-Discrimination and fully explores each request for new or improved service that is received.
NT10BIX5570086 | 2012 | 39494.00 | This amount is currently below our estimated cost. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 92Mbps | We are providing 100Mbps service to 5 of the 6 CAI's that are receiving service. The other one is getting 50Mbps. | 0 | N/A | The average increase in broadband speed provided is 92Mbps. We have 6 customers currently receiving service, with one getting 50Mbps and 5 getting 100Mbps. | Enventis is now providing new or improved access to nine Community Anchor Institutions. This project seeks to provide 100Mg to 10G lit capacity as well as leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that is based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 41721 | 1554 | 652 | 35619 | 162 | 0 | 3734 | [REDACTED] | 240 | 170 | 35 | 35 | In addition to collocation space available at two Point of Presence sites along the BTOP-funded middles mile routes, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state of Minnesota. | N/A | Through the implementation of this federal project, Enventis has learned valuable lessons that may benefit other federal recipients. These include: It is important to provide project updates and reminders on program requirements to all employees working on the project on a regular basis. Some employees are participating in a small part of the project but still must be familiar with all federal guidelines. Enventis has updated internal and contractor fact sheets on a quarterly basis to refresh project information and we continually remind the project team and participating employees on key directives including the need to verify Federal status in EPLS or SAM before engaging a new contractor or vendor. Take advantage of BTOP-sponsored conferences, drop in calls and webinars that are offered to stay up to date on program requirements. Continually review project policies for accuracy. Enventis developed a Program Income policy at the start of the project but it required an update once we had obtained Program Income and verified how it was tracked through our internal accounting process and systems. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | [REDACTED] | [REDACTED]
NT10BIX5570086 | 2013 | 51309 | This is above our initial baseline due to decreased number of route miles. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 166Mbps | The average increase in broadband speed provided is 166Mbps. We have 20 CAI customers currently receiving service, with 2 customers receiving 1Gb service, 11 customers receiving 100Mbps, 2 customers receiving 50Mbps service, 1 customer receiving 45Mbps service, 1 customer receiving 40Mbps service, 1 customer receiving 20Mbps service, 1 customer receiving 10Mbps service and 1 customer receiving 5Mbps service. | 0 | N/A | The average increase in broadband speed provided is 166Mbps. We have 20 CAI customers currently receiving service, with 2 customers receiving 1Gb service, 11 customers receiving 100Mbps, 2 customers receiving 50Mbps service, 1 customer receiving 45Mbps service, 1 customer receiving 40Mbps service, 1 customer receiving 20Mbps service, 1 customer receiving 10Mbps service and 1 customer receiving 5Mbps service. | Enventis is now providing new or improved access to 34 Community Anchor Institutions. This project seeks to provide 100Mg to 10G lit capacity and leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that is based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 39267 | 3238 | 2112 | 33917 | 0 | 0 | 0 | Enventis is leasing 191 route miles of dark fiber to MND, 163 route miles to Zayo, and 157 route miles to the State of MN OET. | 240 | 170 | 70 | 0 | In addition to collocation space available at two Point of Presence sites along the BTOP-funded middles mile routes, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state of Minnesota. | N/A | Through the implementation of this federal project, Enventis has learned valuable lessons that may benefit other federal recipients. These include: It is important to provide project updates and reminders on program requirements to all employees working on the project on a regular basis. Some employees are participating in a small part of the project but still must be familiar with all federal guidelines. Enventis has updated internal and contractor fact sheets on a quarterly basis to refresh project information and we continually remind the project team and participating employees on key directives including the need to verify Federal status in EPLS or SAM before engaging a new contractor or vendor. Take advantage of BTOP-sponsored conferences, drop in calls and webinars that are offered to stay up to date on program requirements. Utilize the wiki for references and resources. Continually review project policies for accuracy. Enventis developed a number of policies at the start of the project but some required updates as we moved through the project period. Keep internal records updated to ensure accurate reporting. Begin preparing reports and verifying internal information as soon as possible - do not wait to begin just before a deadline. If there are questions or you run into an issue, it is better to have more time to straighten it out. If you have a question for an NTIA or BAH representative, ask it right away. The unanticipated federal government shutdown prevented access to key resources at all federal agencies and BAH during the close out reporting period. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | Enventis has secured multiple agreements with some providers and also secured agreements that document multiple services (services may be New or Improved Access) on one agreement. During the reporting period, Enventis completed 25 agreements with 11 providers including Verizon Wireless (4), WIN (1), MND (1), SDN (1), Qwest QCC (3), Verizon Business (2), State of MN OET (9), Cooperative Network Services (1), Cooperative Light & Power (1), XO (1), Compudyne (1). Enventis adheres to a Network Openness policy and fully explores each interconnection request received. | Enventis has secured dark fiber agreements with MND and the State of MN OET. Enventis adheres to a Network Openness and Non-Discrimination policy and fully explores each request for new or improved service that is received.
NT10BIX5570087 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection & access points and co-location points. | N/A | N/A | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | N/A | N/A
NT10BIX5570087 | 2011 | 0 | Not yet started construction | 0 | N/A | 0 | N/A | 0 | 10mbps-100mbps- Open Access | 0 | N/A | 0 | Not yet started construction | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 25024 | 0 | 0 | 0 | 340 | 0 | 24684 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection & access points and co-location points. | N/A | N/A | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1. None 2. None 3. We have not denied any requests. | N/A
NT10BIX5570087 | 2012 | $33,861 | Average cost less than baseline due to lower than expected bid prices and only 84% of construction is complete. | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps- 100 mbps - Open Access | 0 | N/A | 57 mbps | 10 mbps- 100 mbps - Open Access | 0 | N/A | Broadband speed has not increased. Most CAI's request 50 mbps or 100 mbps. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 24057 | 0 | 0 | 19348 | 192 | 0 | 4517 | N/A | 960 | 480 | 15 | 465 | N/A | N/A | 1) Start the Environmental Assessment process as early as possible for long, linear projects 2) Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1) Entered into one (1) agreement (County of Surry) 2) Negotiating seven (7) agreements with Cox, VDOT, Comcast, Town of Suffolk, BIT(2), Surry County Schools 3) Have not denied any requests for interconnection | N/A
NT10BIX5570087 | 2013 | 24697 | Average cost less than baseline due to lower than expected bid prices and 87% of budgeted funds were actually spent. | 0 | N/A | 0 | N/A | 10 Gbps | 10mbps- 100mbps- Open Access | 0 | N/A | 40 mbps | 10mbps- 100mbps- Open Access | 0 | N/A | Broadband speed has not increased. Most CAIs request 10mbps, 50mbps or 100mbps. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 23923 | 605 | 0 | 23318 | 0 | 0 | 0 | N/A | 960 | 480 | 15 | 465 | N/A | N/A | 1) Start the Environmental Assessment process as early as possible for long, linear projects. 2) Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1) Entered into five (5) agreements: (3)GCR, (2) Kinex 2) Negotiating four (4) agreements with Cox, VDOT, Comcast, Town of Suffolk 3) Have not denied any requests for interconnection | N/A
NT10BIX5570088 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | LTE devices will be very expensive. Consider a transition or refresh plan to minimize costs. | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A
NT10BIX5570088 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | None | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A
NT10BIX5570088 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | None | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A
NT10BIX5570088 | 2013 | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. This project is specific to public safety entities only. | 0 | N/A. Due to suspension last mile has not been deployed. | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. Due to suspension last mile has not been deployed. | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. Due to suspension last mile has not been deployed. | N/A | None | N/A. 7a. Due to suspension network has not been deployed. 7b. This project is specific to public safety only and is not providing commercial services. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | 1. Plan on Significant cost increase for Band 14 devices and maintenance. 2. Commercial costs structure for LTE 4G service have become very competitive. 3. Preserving network design in such a fluid tower space market. 4. Local zoning conditions can have a significant impact on schedule and site costs. 5. Balancing commitment to a design with tower modification expense. | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A
NT10BIX5570088 | 2014 | 0 | N/A. Due to Project Restructure middle mile is not being deployed. | 0 | N/A. This project is specific to public safety entities only. | 0 | N/A. Due to Project Restructure. | 0 | N/A. Due to Project Restructure middle mile is not being deployed. | 0 | N/A. Due to Project Restructure. | 0 | N/A. Due to Project Restructure middle mile is not being deployed. | 0 | N/A. Due to Project Restructure. | Charlotte Mecklenburg Police Department (CMPD) stations were 100Mbs, new station switches made it possible for us to upgrade to 1Gps circuits = 900Mbs increase. Old Charlotte Fire Department (CFD) switches were 10Mbs, new switches made it possible for us to upgrade to 100Mbs = 90Mbs increase. | This project is specific to public safety and is not providing commercial services. | A. The restructured project does not include network management. B. This project is specific to public safety and is not providing commercial services. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. Private public safety network. | N/A | 1. Plan on equipment ordering-to-delivery lead-times. 2. Plan on significant cost increase for band 14 devices and maintenance. 3. Local zoning conditions can have a significant impact on schedule. 4. Preserving network design in a fluid tower space market. 5. Balancing design changes with tower modifications required. | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 60 |  | 0 | 0 | 0 | 60 | N/A | N/A
NT10BIX5570089 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in speed at this time. | No retail services are being provided by this project. | No network management policies have been developed at this time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | No interconnection points have been finalized at this time. | No subcontracts have been awarded to SDB businesses at this time. | N/A | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A
NT10BIX5570089 | 2011 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | Since no infrastructure has been deployed to date, no network policies have been developed to date. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure has been deployed to date, no collocation space can be reported. | No SDB subcontracts have been awarded. | Since deployment has not yet begun Motorola is not yet in a position to share best practices/lessons learned. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A
NT10BIX5570089 | 2012 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure has been deployed to date, no collocation space can be reported. | No SDB subcontracts have been awarded. | Motorola Solutions participated in a site visit with members of the First Responder Network Authority (First Net) board, JPA executives, NTIA, Sate of California representative, representative from the Mayor of San Francisco office, the Police Chief of City of San Francisco, director of EMA, and Motorola Solutions executives. During that meeting Motorola and the BAYRICS authority shared many lessons learned concerning contracting, BOOM agreements, SAU agreements, and vendors. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A
NT10BIX5570089 | 2013 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and ultimate expiration of the BTOP grant. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Since no infrastructure was deployed due to the expiration of the BTOP grant, no increase in broadband speed can be reported. | N/A | Since no infrastructure was deployed due to the expiration of the BTOP grant, no network policies can be reported. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure was deployed due to the expiration of the BOP grant, no collocation space can be reported. | No SDB subcontracts were awarded. | Motorola Solutions continued to participate in meetings with members of the First Responder Network Authority (First Net) board, Joint Powers Authority (JPA executives, NTIA, State of California representatives, and Motorola Solutions executives. During those meetings, Motorola and the BAYRICS authority shared many lessons learned concerning contracting, Build Own Operate Maintain(BOOM) agreements, Site Access and Use (SAU) agreements, and vendors. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A
NT10BIX5570090 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. Only limitations are the service level the customer is contracted to pay for the service (SLA). 7b. No. | N/A | 408 | 0 | 0 | 0 | 408 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Network providers and customers are either connected in their space or they are connected to DCN's equipment in DCN's space within our facility. | None. | N/A | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | 1. 17 2. 0 3. N/A | N/A
NT10BIX5570090 | 2011 | 44869 | So far we have been below our estimate by $14,000/mile. But not all of our costs from sub recipients have been incurred yet. This is a good indication that our budgets should not be exceeded. | 0 | N/A | 0 | N/A | 100 | Mbps | 0 | N/A | 5 | Mbps | 0 | N/A | 0 Mbps; no increase at this time since only one has been connected with no change to their purchased speed at this time. Service quality and consistency are greatly increased due to the change from copper to fiber and dedicated service. | N/A | 7a. Only limitations are the service levels the customer is contracted to pay for (SLA). 7b. No | N/A | 5632 | 3184 | 0 | 0 | 408 | 0 | 2040 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the serve providers location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | 1. 17 2. 0 3. N/A | N/A
NT10BIX5570090 | 2012 | 43,049 | So far we have been below our estimate by $5,000 per mile. But not all of our costs have been incurred yet. | 0 | N/A | 0 | N/A | 100 Mbps | N/A | 0 | N/A | 7 Mbps | N/A | 0 | N/A | 4 Mbps on average. Subscribers were being by TI's and now have 5 mpbs service or higher. | No retail service provided. | 7a. Only limitations are the service levels the customer is contracted to pay for (SLA). 7b. No | N/A | 5725 | 3193 | 0 | 0 | 422 | 0 | 2110 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the serve providers location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | Number of signed agreements: 17 Number being negotiated: 0 Average term of the signed agreements: 7 | N/A
NT10BIX5570090 | 2013 | 42064 | We are below our estimate by $6,000 per mile. Costs were lower than estimated. | 0 | N/A | 0 | N/A | 1000 Mbps | N/A | 0 | N/A | 13.6 | N/A | 0 | N/A | 10 Mbps on average. Subscribers were being served by TI's and now have 5 mbps service or higher. | no retail service provided. | 7a. Only limitations are the service levels the customer is contract to pay for (SLA) 7b. No | N/A | 5725 | 5725 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the service provider's location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate quarterly reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | Number of signed agreements: 17 Number being negotiated: 0 Average term of the signed agreements: 7 Denied requests: 0 | N/A
NT10BIX5570091 | 2010 | 0 | Deployment is not complete | 0 | NA | 0 | NA | 10GB | Planned maximum speed in line with baseline | 0 | NA | 1GB | Planned average speed in line with baseline | 0 | NA | NA | NA | NA, no network in place to date | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA, no network to date | NA | Bluebird decided to split the mapping/staking engineering between three engineering firms. This allows the firms to work on a smaller portion of the project decreasing the return time on the work requested. This also mitigates the risk of a single firm delaying the project. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | NA | NA
NT10BIX5570091 | 2011 | 0 | N/A-no fiber in service to date. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 0 | No subscribers to date, therefore no average speed. | N/A | N/A | NA | NA | NA, no network in place to date. | NA | 107212 | 0 | 0 | 21197 | 2920 | 0 | 83095 | NA | 0 | 0 | 0 | 0 | NA, no collocation space built to date. | NA | Bluebird decided to split the outside plant construction into 7 segments. This allowed Bluebird to contract with four different construction companies to build the fiber routes mitigating the risk of a single company faltering. Bluebird also went directly to several equipment manufactures to request a bid on the equipment used for this BTOP project. This strategic decision has allowed Bluebird to obtain the lowest price for manufactured goods without paying a premium to a re-seller. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | N/A | N/A
NT10BIX5570091 | 2012 | 0 | N/A-no portion of the network was fully deployed, complete, and in service. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 0 | No subscribers to date, therefore no average speed. | N/A | N/A | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | 105464 | 1174 | 0 | 91851 | 346 | 0 | 12093 | N/A | 4110 | 2055 | 0 | 2055 | N/A-own collocation space | N/A | Bluebird decided to split the outside plant construction into 7 segments. This allowed Bluebird to contract with four different construction companies to build the fiber routes mitigating the risk of a single company faltering. Bluebird also went directly to several equipment manufactures to request a bid on the equipment used for this BTOP project. This strategic decision has allowed Bluebird to obtain the lowest price for manufactured goods without paying a premium to a re-seller. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | Total number of interconnections entered into during this annual reporting period was 22; currently negotiating 5 interconnection agreements; no requests for interconnection has been denied. | N/A
NT10BIX5570091 | 2013 | $55,170 | The average variance increase of $12,083 per mile was caused from engineering and construction costs being under estimated. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 140 Mb | The average variance decrease of 50 Mb was caused by less than estimated CAIs subscribing for 1GB of service. This decrease caused the average to fall below estimated. | N/A | N/A | The average increase in broadband speed provided to the CAI customers was 20 Mb. Bluebird calculated this increase by comparing the CAIs service speed prior to connecting to the grant network against the current speed while connected to the grant network. These figures were than averaged. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are unique to each individual customer since Bluebird is a middle mile network and the majority of retail customers need outside plant to directly connect for services. | Bluebird's management policies consist of no traffic prioritization and the bandwidth limitations are capped at the bandwidth the customer subscribed. Bluebird has never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A- zero subscribers have dropped during this project once connect to the grant network. | 98097 | 2602 | 110 | 95385 | 0 | 0 | 0 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | 4470 | 2235 | 0 | 2235 | N/A-own collocation space | N/A | Bluebird learned that it is better to start sooner rather than later when filing federal liens with all the appropriate counties as each county has different formats, costs, and requirements. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | Total number of interconnections entered into during this annual reporting period was 2; currently negotiating 5 interconnection agreements; no requests for interconnection has been denied. | N/A
NT10BIX5570093 | 2010 | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project
NT10BIX5570093 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | The one CAI that has been connected using BTOP funding had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed (increase = (new amount - original amount)/original amount. In both cases this is a transport circuit only between the school and the central technology center for the school system. The internet connectivity is centralized and shared with all schools in the school system from the technology center. | No retail services have been provided by this project at this time. Delays with EA approval and in acquiring fiber have limited progress until January 2012. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy, Acceptable Use Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms & Conditions. http://citizens.coop/terms/ b) No | N/A | 38419 | 38419 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A | N/A
NT10BIX5570093 | 2012 | 33,455 | Average cost per new mile is less than the baseline amount of $52,791 due to the fact that construction is 96% complete, but we have only received and paid invoices for 65% of the project. This amount will come in line with the baseline once we start receiving and paying invoices for completed construction. | 0 | N/A | 0 | N/A | 1G | No Variance | 0 | N/A | 1G | The 5 Subscribers we are currently serving over BTOP-funded facilities are all using a 1G circuit. | 0 | N/A | The five CAI's that have been connected using BTOP funding had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed (increase = (new amount - original amount)/original amount. In these cases this is a transport circuit only between the school and the central technology center for the school system. The internet connectivity is centralized and shared with all schools in the school system from the technology center. | See Attachment for services offered and pricing plan. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy, Acceptable Use Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms & Conditions. http://citizens.coop/terms/ b) No | N/A | 43039 | 43039 | 0 | 0 | 0 | 0 | 0 | N/A | 480 | 240 | 0 | 240 | N/A | N/A | N/A | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A | N/A
NT10BIX5570093 | 2013 | 49,914 | Average cost per new mile is less than the baseline amount of $52,791 due to the fact that Citizens was able to complete the project and come in under budget. Construction was originally budgeted for $9,819,064 and the actual construction expense was $9,283,920. | 0 | N/A | 0 | N/A | 10G | No Variance | 0 | N/A | 1G | No Variance | 0 | No Variance | There are 17 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed. There are 4 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 10.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 9900.00% increase in broadband speed. There are 2 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 45.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 2122.22% increase in broadband speed. There are 5 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 100.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 900.00% increase in broadband speed. There is 1 CAI that has been connected using BTOP funding that had a symmetrical broadband connection of 768.0Kbps (0.768Mbps) replaced by a symmetrical 3.0Mbps broadband connection. This resulted in a 290.63% increase in broadband speed. The increases in speeds above were calculated using the following formula: (increase = (new amount - original amount)/original amount. | See Attachment for services offered and pricing plan. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms and Conditions. http://citizens.coop/terms/ b) No | N/A | 41997 | 40743 | 0 | 1254 | 0 | 0 | 0 | Radford University - 93.40 Miles Virginia Department of Transportation - 200 | 480 | 240 | 0 | 240 | N/A | N/A | None at this time. | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | No new Interconnection Agreements were entered into during this annual reporting period. We are continuing and extending the eight existing agreements we have with Bristol Virginia Utility (BVU), Mid Atlantic Broadband (MBC), Shentel, Cox Communications, Windstream, Lumos, Surry Telephone Membership Corporation, and Skyline Telephone Membership Corporation, that were in place before the NTIA Grant was awarded. No Interconnection Agreements are currently being negotiated. No Interconnection requests have been denied. | No new Peering and/or Transit Agreements were entered into during this annual reporting period, but we are continuing and extending the three existing agreements we have with Virginia Tech, Radford University, and New River Community College. No Peering and/or Transit Agreements are currently being negotiated.
NT10BIX5570094 | 2010 | $0 | No new miles were constructed during 2010. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 Mbps | N/A | 1 Mbps | N/A | N/A | N/A | 7a. Network Management is within the scope of RFP 3639, which has been released. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | Once the addition of LTE equipment on the towers begins, we will be able to offer best practices to other BTOP recipients. | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A
NT10BIX5570094 | 2011 | $3559.40 | 428 new miles completed in 2011 which included the installation of microwave backhaul equipment for 24 new network links in Phase 2C & 2D. Each set of microwave dishes costs $63,476 which equates to $3559.40 per mile. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | The upgraded microwave backhaul was in the initial stages of deployment and therefore was not utilized in 2011. | 0 | The upgraded microwave backhaul was in the initial stages of deployment and therefore was not utilized in 2011. | In 2011, we were in the initial stages of designing and deploying the components of the LTE network. We had not begun offering broadband services to community anchor institutions during 2011. | N/A | 7a. Network Management is within the scope of RFP 3639 which has been awarded to Motorola Solutions. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | N/A | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A
NT10BIX5570094 | 2012 | $3559.40 | 428 new miles completed in 2011 which included the installation of microwave backhaul equipment for 24 new network links in Phase 2C & 2D. Each set of microwave dishes costs $63,476 which equates to $3559.40 per mile. Payment milestones related to microwave installation in Phase 3 have been achieved during 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. We continued to deploy the upgraded microwave backhaul, however it was not utilized in 2012. | 0 | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. We continued to deploy the upgraded microwave backhaul however it was not utilized in 2012. | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Therefore, we have not begun offering broadband services to community anchor institutions during 2012. | N/A | 7a. Network Management is within the scope of RFP 3639 which has been awarded to Motorola Solutions. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | N/A | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A.
NT10BIX5570094 | 2013 | $16,604.33 | 1,051 new miles completed through the end of 2013 which included the installation of equipment for 70 new network links in Phase 2C , 2D and 3. The cost associated with the installation of the microwave equipment is $17,451,155 which equates to $16,604.33 average cost per new mile. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | over 10 mb | On May 11, 2012, NTIA determined it was necessary to partially suspend, the LTE-related components of Mississippi's BTOP grant until Mississippi was able to secure long term access to the spectrum from FirstNet. Mississippi was unable to reach an agreement which would allow for a sustainable statewide public safety broadband network. Mississippi's BTOP grant ended on December 31, 2013. At the time of the grant suspension, the majority of the LTE network had been deployed to 135 MSWIN tower sites across the state. Mississippi also used a portion of BTOP grant funds to upgrade its existing MSWIN microwave backbone network to a greater bandwidth to accommodate the broadband network. The MSWIN microwave network is complete and currently in use by 20,000 first responders statewide for emergency communication needs including dispatch services, global positioning services and automatic vehicle location. | 0 | On May 11, 2012, NTIA determined it was necessary to partially suspend, the LTE-related components of Mississippi's BTOP grant until Mississippi was able to secure long term access to the spectrum from FirstNet. Mississippi was unable to reach an agreement which would allow for a sustainable statewide public safety broadband network. Mississippi's BTOP grant ended on December 31, 2013. | On May 11, 2012, NTIA determined it was necessary to partially suspend, the LTE-related components of Mississippi's BTOP grant until Mississippi was able to secure long term access to the spectrum from FirstNet. Mississippi was unable to reach an agreement which would allow for a sustainable statewide public safety broadband network. Mississippi's BTOP grant ended on December 31, 2013. Mississippi also used a portion of BTOP grant funds to upgrade its existing MSWIN microwave backbone network to a greater bandwidth to accommodate the broadband network. The MSWIN microwave backbone network is complete and currently in use by public safety entities across Mississippi. | N/A | 7a. Traffic prioritization is in accordance with the State's license for use of the 700 MHz spectrum. 7b. No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A
NT10BIX5570095 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | Network Management will utilize 'best practices' for protection of the network. The six steps were outlined in our initial BTOP application and exceed the word limitation for this section. However, all of these capabilities are available from the appliances provided by all major providers of content filtering devices. Additionally, these capabilities are fully configured to ensure that the filtering and protection taking place is fully in compliance with the NOFA without compromising the ability of the network to provide the required services to its users. | N/A | 9800 | 0 | 0 | 0 | 1000 | 1200 | 7600 | N/A | 0 | 0 | 0 | 0 | Network providers and/or customers requesting interconnection have 3 options: 1)Secure collocation at one of our current collocation facilities or point of presence. 2)Meet at a splice point for mid-span meet. 3)Instruct/Request that we build to their premise. | N/A | One of our best practices has been the selection of East Alabama Regional Planning Commission for the development of our Environmental Assessment. We had several concerns expressed from other government agencies due to this selection, however having a local representative that is very familiar with the processes and, most importantly, the personnel responsible for services throughout our state has been a large benefit to reaching our goals for the EA. | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | N/A | N/A
NT10BIX5570095 | 2011 | 0 | Final invoices, including splicing, for the currently completed segments have not been received as of 12/31/2011. Insufficient data to calculate average cost per mile as of yet. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Not provided because deployment has not yet begun. | Services are not yet being provided. | N/A | 9800 | 0 | 0 | 0 | 1000 | 1800 | 7600 | N/A | 0 | 0 | 0 | 0 | Interconnect to the network can occur at negotiated splice points, or with POP locations. All POP locations reside within data centers that are open to collocation or at carrier hotel type facilities. | Willie T. Gooden d/b/a Gooden Construction P.O. Box 3250 Anniston, Alabama 36202 | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | N/A | N/A
NT10BIX5570095 | 2012 | $29,266 | Changing standards/requirements from AL DOT (Department of Transportation) and the NESC (National Electric Safety Code) increased construction cost. | 0 | N/A | 0 | N/A | 1 Gbps | No variance from baseline | 50 Mbps | Changes in technology allowed an increase in offered speeds on wireless system | 100 Mbps | No variance from baseline | 0 | N/A | Average increase is 80 Mbps. Prior services ranged from 0 to 50 Mbps. CAI's subscribing to our receiving 100 Mbps service. | As of December, we were not serving retail customers that were not on the CAI (Community Anchor Institution) list. | Network Management Policies: Traffic for services with a purchased CIR (Committed Information Rate)feature are given higher priority to services that are sold at best effort, otherwise prioritization policies exist. Service providers are limited to oversubscription ratio of 4 to 1. No traffic has been blocked or limited to date. | We have not experienced any number of subscribers dropping services provided through this project. | 12500 | 1500 | 0 | 11000 | 0 | 0 | 0 | At this time, we do not have wholesale customers for dark fiber services. | 0 | 0 | 0 | 0 | We have established interconnection points at the equivalent of carrier hotels owned by third parties where multiple service providers collocate. Additional interconnection is made available at fiber splice points. | N/A | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 Roanoke Telephone interconnection agreement under negotiations. SynchGlobal interconnection agreement under negotiations. | Transit agreements with both Cogent Communications and EarthLink completed,
NT10BIX5570095 | 2013 | 39,187.79 | n/a | 0 | n/a | 0 | n/a | 1 gigabyte | n/a | 0 | n/a | 100 megabyte | n/s | 0 | n/a | Average increase is 80 Mbps. Prior services ranged from 0 to 50 Mbps. CAI's subscribing to our receiving 100 Mbps service. | At the retail level fiber services are; 100 mps Ethernet transport, virtual private lines, internet access and dark fiber. Wireless internet access is available in select locations. | Network Management Policies: Traffic for services with a purchased CIR (Committed Information Rate)feature are given higher priority to services that are sold at best effort, otherwise prioritization policies exist. Service providers are limited to oversubscription ratio of 4 to 1. No traffic has been blocked or limited to date. | We have not experienced any number of subscribers dropping services provided through this project. | 12500 | 320 | 52 | 12128 | 160 | 38 | 11218 | Jacksonville State University: 24 fiber miles: Calhoun County Administration: 14 fiber miles Slappey Telephone: 6 fiber miles SyncGlobal Telecom: 8 fiber miles | 0 | 0 | 0 | 0 | Other network providers and/or may interconnect at any of our 7 collocated POP's or at a mutually agreeable splice point on the network. We have established interconnection points at the equivalent of carrier hotels owned by third parties where multiple service providers collocate. | N/A | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 SynchGlobal Telecommunications agreement completed March 1, 2013 Roanoke Telephone Company/TEC June 2013 | Internet Transit Traffic peering agreements with Cogent Communication and Hurricane Electric
NT10BIX5570096 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | NONE | N/A | N/A | 1438323 | 0 | 0 | 0 | 1434723 | 1200 | 2400 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | N/A
NT10BIX5570096 | 2011 | 0 | N/A: Until the network build is completed and tested, the U.S. Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation (viNGN) team is unable to accurately calculate the average cost per new mile. The team has executed an Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3; has purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network and has purchased Carrier Ethernet equipment; however, the network build and equipment deployment have been delayed due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The team plans to address these challenges by compressing construction schedules, implementing parallel construction activities; maintaining aggressive work schedules; and, hiring additional staff. | 0 | N/A | 0 | N/A | 10Gbps | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. | 0 | N/A | 0 | N/A; Until the network build is completed and tested, viNGN will not be able to accurately determine the speeds that will be available. | 0 | N/A | N/A | N/A | N/A | N/A | 31489 | 0 | 0 | 0 | 31489 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the â€œmeet meâ€ rooms; the interconnection to other carriers is via â€œmid-spanâ€ fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN will lease 6 sq ft. The NY NAP has 15,000 sq ft.; viNGN will lease 6 sq ft in this facility, as well. | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | 1) viNGN has executed one Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, providing a strong network with a diverse route and the ability to purchase bandwidth at prices that are significantly less than what is offered in the local market today. The IRU with Global Crossing / Level 3 is expected to offer 1) a 10Gb Clear Ethernet WAV, 2) a “one hop” to the core of the NAP of the Americas, 3) better connectivity than the city of Miami, 4) an internet peering point, and 5) a Carrier Ethernet network. 2) The team is still in negotiations with a second wholesale service provider, AT&T. 3) The team has not denied any request for interconnection, as its network is being built and tested. The project team is not able to finalize negotiations with last mile providers before finalizing an IRU agreement with AT&T, as the terms of the IRU agreements are key to the development of viNGN's schedule of products and pricing. As a result, viNGN has not signed any agreements with retail services providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Two additional Broadband Coalition meetings were held during October 2011, one on St. Thomas and the other on St. Croix. These meetings and conversations have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The formulation of the Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered.
NT10BIX5570096 | 2012 | 0 | N/A: Until the network build is completed and tested, the U.S. Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation (viNGN) team is unable to accurately calculate the average cost per new mile. The team has executed an Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 and a lease agreement with AT&T; has purchased all of the fiber required for its network; and, has purchased all of the required Carrier Ethernet equipment. | 0 | N/A | 0 | N/A | 10Gbps | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. The Broadband speeds that are expected to be available are from 1 Gbps to 10 Gbps. | 0 | N/A | 0 | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. | 0 | N/A | N/A; CAI connections are expected to begin during Quarter 2, CY 2013. | N/A; The VIPFA/viNGN team is building out a middle mile network; thus, retail services will not be provided. | N/A; 7a. Network management policies are being developed for viNGN's middle mile services 7b. The VIPFA/viNGN team is building out a middle mile network; thus, retail services will not be provided directly to retail consumers. | N/A; The VIPFA/viNGN team is building out a middle mile network; thus, retail subscriber services will not be provided. | 31489 | 0 | 0 | 0 | 31489 | 0 | 0 | N/A | 12 | 12 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the "meet me" rooms; the interconnection to other carriers is via "mid-span" fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN leased 6 sq. ft. The New York NAP has 15,000 sq. ft.; viNGN leased 6 sq. ft. in this facility, as well. These areas that are leased are not collocation spaces. However, as the FAPs are completed, the square footage within them will be collocation spaces between viNGN and the ISPs (Internet Service Providers) and other service providers. viNGN may also lease additional space on St. Croix from Global Crossing/Level 3, in an effort to provide customers with an earlier service date, i.e. prior to the completion of its entire network build. | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | 1) viNGN has executed one Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, providing a strong network with a diverse route and the ability to purchase bandwidth at prices that are significantly less than what is offered in the local market today. The IRU with Global Crossing/Level 3 is providing 1) two 10Gb Clear Ethernet WAVE, 2) a "one hop" to the core of the NAP (Network Access Point) of the Americas and to New York City, 3) an internet peering point, and 4) a Carrier Ethernet Network. 2) The team has a lease agreement with AT&T for the SONET OC-48 to temporarily connect St. Thomas and St. Croix. 3) The team has not denied any request for interconnection, as its network is being built and tested. viNGN has not signed any agreements with retail services providers; however, the team continues to engage the local community of anchor tenants/ Community Anchor Institutions (CAIs) and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Three Broadband Coalition meetings were held during CY 2012, two of which were simulcast through video conference on St. Thomas and on St. Croix. One of the simulcasts was held at the University of the Virgin Islands (UVI), and the second simulcast was held at the U.S. Virgin Islands Emergency Management Agency (VITEMA), both of which are CAIs on VIPFA/viNGN's network. The Broadband Coalition meeting discussions included the following: -VIPFA/viNGN's Organization, Key Contacts and Working Relationship with Service Providers, ISPs, the local government and the Federal government; -CCI Build-out Plans and Schedule; -Equipment to be deployed at each CAI, the technical specifications and the schematics; -FAP Details (Locations and Layout); -Community Anchor Institutions (Connecting to the Network); and -viNGN's Future Business Plans. These meetings and conversations have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as viNGN refines its range of products, prices, terms and conditions for the services and products to be offered.
NT10BIX5570096 | 2013 | $116,156 | The actual "Average cost per mile (Middle Mile)", per NTIA's definition, is below the Baseline estimate of $157,294. | 0 | N/A | 0 | N/A | 10Gbps | The network is designed to offer broadband speeds that are up to 10 Gbps. | 0 | N/A | 0 | N/A: Until the network build is completed and tested and service is provided to a larger customer base, the VIPFA/viNGN team will not be able to accurately provide an average broadband speed provided. | 0 | N/A | Prior to the VIPFA/viNGN team's installation of its fiber optic network at the Althalie McFarlane Peterson Library, the library's network was operating at 2 Mbps to 5 Mbps. After VIPFA/viNGN installed its equipment and fiber and the library was connected to VIPFA/viNGN's 100% fiber optic, wholesale/middle mile network, the library's speed was recorded at between 20 Mbps to 50 Mbps, i.e. ten times (10X) the speeds previously experienced at the library. | N/A; The VIPFA/viNGN team is building out a 100% fiber optic, wholesale/middle mile network; thus, retail services are not being provided. | 7a. Network management policies are being developed. 7b. No | N/A; The VIPFA/viNGN team is building out a 100% fiber optic, wholesale/middle mile network. | 29602 | 21 | 6494 | 22515 | 572 | 0 | 0 | N/A | 2128 | 2128 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the "meet me" rooms; the interconnection to other carriers is via "mid-span" fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN leased 6 sq. ft. The New York NAP has 15,000 sq. ft.; viNGN leased 6 sq. ft. in this facility, as well. These areas that are leased are not collocation spaces. However, as the FAPs are completed, the square footage within them will be collocation spaces between viNGN and the ISPs (Internet Service Providers) and other broadband service providers. | The entire U.S. Virgin Islands has been classified as a Historically Under-utilized Business Zone (HUBZone), as it is a 100% underserved or un-served, rural, insular territory, consisting of four inhabited islands with less than 110,000 residents in total, low per capita income levels and a higher than the national average unemployment rate. Thus, it is believed that most of the project's local vendors can be classified as SDBs; however, the information to verify the relevant data is not available at the time of the publication of this report. Further, it is believed that some of the project's non-local vendors can be classified as SDBs; however, additional resources would have to be identified and allocated for the data to be collected and verified. Additional funding is not currently available through VIPFA, viNGN or the Government of the U.S. Virgin Islands. In addition, the VIPFA/viNGN's procurement process allows for open and, at a minimum, limited competition, the latter in those cases when the purchases are defined as "Small Purchases" or in cases of emergency under Federal and local law, for which there have been none to date. Full and open competition solicitations are posted on www.vingn.com, the VIPFA's Office of Economic Opportunity (OEO) website, local newspapers, and local online media, with sufficient time for respondents to provide quotes, bids or proposals, in order to ensure that all potential vendors, including SDBs, are aware of all opportunities. | The key best practices and lessons learned by the VIPFA/viNGN team are the following: â€¢ Recipients must identify additional financial and human resources needed to meet the extensive reporting requirements under the BTOP projects and to most effectively and efficiently implement a major construction project, especially in environments with relatively low broadband speeds and reliability and very high prices and limited local government financial resources, like the U.S. Virgin Islands; and, â€¢ In order to have significant penetration in broadband adoption levels in communities which are significantly underserved and unserved, like the U.S. Virgin Islands, significant financial resources, well in excess of what is currently available under the VIPFA/viNGN's team's BTOP programs, must be allocated to marketing, public relations, promotions, community outreach, and awareness activities; Internet-based research support; training and other educational courses; and, other services to encourage broadband use and adoption and to have impact in an insular broadband market within the short term of the program. | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | Under its Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3, which was executed during CY 2011, the VIPFA/viNGN team activated connections through Level 3 in New York, Level 3 in Miami, FAP STX-02 (Frederiksted)/Lagoon and the U.S. Virgin Islands Department of Planning and Natural Resources' Althalie McFarlane Petersen Library in Frederiksted, St. Croix, the latter of which is a CAI and a Public Computer Center (PCC). The team has not denied any request for interconnection. | N/A
NT10BIX5570096 | 2014 | $119,279.15 | The actual "Average cost per mile (Middle Mile)", per NTIA's definition, is below the Baseline estimate of $157,294. | 0 | N/A | 0 | N/A | 10Gbps | N/A; The network is designed to offer broadband speeds that are up to 10Gbps. | 0 | N/A | 0 | VIPFA/viNGN team created and provided open access fiber optic service from our fiber optic points to the Community Anchor Institutions (CAIs) being serviced. As a result, the average broadband speed requested by the CAIs was a direct output from viNGN to the CAIs. VIPFA/viNGN has not yet provided any direct middle mile access. | 0 | N/A; VIFPA/viNGN is a middle mile provider and resells to last mile providers or ISPs. The current subscriber on viNGN network requests speed in a range from 25 Mbps to 1 Gbps. | The average speed provided by VIPFA/viNGN team thus far is 122 Mbps. For example, prior to the VIPFA/viNGN team's installation of its fiber optic network at the Althalie McFarlane Peterson Library, the library's network was operating at 2 Mbps to 5 Mbps. After VIPFA/viNGN installed its equipment and fiber and the library was connected to VIPFA/viNGN's 100% fiber optic, wholesale/middle mile network, the library's speed was recorded at between 20 Mbps to 50 Mbps, i.e. ten times (10X) the speeds previously experienced at the library. Another example, at the Department of Education Headquarters located at Kongens Gade, St. Thomas, the department was operating at a maximum of 300 Mbps. Now with viNGN network upgrade, the Department of Education Headquarters is now operating at 1 Gbps, i.e. three times (3X) the speeds previously experienced at the Department of Education Headquarters. Finally the Virgin Islands Governments Bureau of Information Technology increased their Internet capacity from 300 Mbps to 3 Gbps connections while staying in their existing budget. | N/A; The VIPFA/viNGN team is building out a 100% fiber optic, wholesale/middle mile network; thus, retail services are not being provided. | 7a. Yes. For example, the bandwidth is based on the service requested by the customer. In some cases, the internet traffic is prioritize based on the data/service requested by the customer on their dedicated Wide Area Network (WAN) for Class of Service (CoS) management only. 7b. No. VIPFA/viNGN has not and does not plan to limit or block consumers from accessing any lawful content, service, service provider or application. | N/A; The VIPFA/viNGN team built a 100% fiber optic, wholesale/middle mile network. No subscribers have dropped their broadband service provided through VIFPA/viNGN and the ISP through the date of this document. | 23087 | 21 | 6494 | 22515 | 0 | 0 | 0 | N/A | 2128 | 2128 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the "meet me" rooms; the interconnection to other carriers is via "mid-span" fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN leased 6 sq. ft. The New York NAP has 15,000 sq. ft.; viNGN leased 6 sq. ft. in this facility, as well. These areas that are leased are not collocation spaces. However, as the FAPs are completed, the square footage within them will be collocation spaces between viNGN and the ISPs (Internet Service Providers) and other broadband service providers. | The entire U.S. Virgin Islands has been classified as a Historically Under-utilized Business Zone (HUBZone), as it is a 100% underserved or un-served, rural, insular territory, consisting of four inhabited islands with less than 110,000 residents in total, low per capita income levels and a higher than the national average unemployment rate. Thus, it is believed that most of the project's local vendors can be classified as SDBs; however, the information to verify the relevant data is not available at the time of the publication of this report. Further, it is believed that some of the project's non-local vendors can be classified as SDBs; however, additional resources would have to be identified and allocated for the data to be collected and verified. Additional funding is not currently available through VIPFA, viNGN or the Government of the U.S. Virgin Islands. In addition, the VIPFA/viNGN's procurement process allows for open and, at a minimum, limited competition, the latter in those cases when the purchases are defined as "Small Purchases" or in cases of emergency under Federal and local law, for which there have been none to date. Full and open competition solicitations are posted on www.vingn.com, the VIPFA's Office of Economic Opportunity (OEO) website, local newspapers, and local online media, with sufficient time for respondents to provide quotes, bids or proposals, in order to ensure that all potential vendors, including SDBs, are aware of all opportunities. | The key best practices and lessons learned by the VIPFA/viNGN team are the following: â€¢ To continue communication of fiber maintenance activities with the general public. Throughout the project VIPFA/viNGN issued public notices to the general public on road activities throughout the island. In some instances, the work activities took place along major arteries of the island road network. As work occurred along these major roadways, there were instances where traffic flow was greatly reduced because of VIPFA/viNGN work activities. VIPFA/viNGN can only assume the impact of not making a public notice. As a result, VIPFA/viNGN learned and planned to continuously make public notices when the company is performing work along the roadways. â€¢ Recipients must be mindful that fiber optic that have been successful installed in the early stages of the project may not remain continuous due to damages incur from vehicular accidents involving utility poles, petty thieves in search of copper, or buried underground fiber optic damaged by "rodding equipment". As a result, such actions require a second check to verify fiber connectivity which can be critical in a time restricted project. â€¢ Recipients must identify additional financial and human resources needed to meet the extensive reporting requirements under the BTOP projects and to most effectively and efficiently implement a major construction project, especially in environments with relatively low broadband speeds and reliability and very high prices and limited local government financial resources, like the U.S. Virgin Islands. | Virgin Islands Public Finance Authority | 69 | 6 | 2 | 6 | 15 | 47 |  | 137 | 14 | 20 | 316 | Under its Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3, which was executed during CY 2011, the VIPFA/viNGN team activated connections through Level 3 in New York and Level 3 in Miami. In a capacity purchase agreement with AT&T, VIFPA/viNGN purchased an OC48 or 2.5 Gbps of interisland capacity between the STT-01 and STX-02. In addition, three hundred sixteen (316) of the CAIs have been successfully tested end-to-end to the Internet; one hundred ninety four (194) of these CAIs have signed contracts with their selected ISPs/retail/last mile service providers and are receiving service on viNGN's network as of March 31, 2015. The team has not denied any request for interconnection. | N/A
NT10BIX5570097 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A
NT10BIX5570097 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | Service to Community Anchor Institutions's (CAI) not yet offered. | N/A | N/A | Broadband speeds have not increased since construction/deployment has not begun | N/A | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT plans to implement a Network Operation Center capability as part of our Middle Mile Broadband system, but this capability is still in the planning stages and will be implemented as portions of the network are substantially completed. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A
NT10BIX5570097 | 2012 | 0 | NA | NA | NA | NA | NA | 0 | NA | NA | NA | NA | Service to Community Anchor Institutions's (CAI) not yet offered. | NA | NA | Broadband speeds have not increased since construction/deployment has not begun | NA | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT plans to implement a Network Operation Center capability as part of our Middle Mile Broadband system as part of the system implementation in early CY13. | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | NA | NA | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | NA | NA
NT10BIX5570097 | 2013 | 0 | Cost analysis in process and has not yet been completed. | N/A | N/A | N/A | N/A | 0 | Until the system is up and operational, advertisement of broadband speed has not been established. | N/A | N/A | N/A | Service to Community Anchor Institutions (CAI) not yet offered. | N/A | N/A | Until the system is up and operational, broadband speed has not been established or advertised. | N/A | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT has implemented a Network Operation Center capability as part of our Middle Mile Broadband system as part of the system implementation. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A
NT10BIX5570097 | 2014 | $10,080.81 | This is the first year that the calculation was made. | N/A | N/A | N/A | N/A | 286 Mb/s | Maximum broadband speed has been established at 286 Mb/s. | N/A | N/A | N/A | Service to Community Anchor Institutions (CAI) not yet offered. | N/A | N/A | Until the system is up and operational, broadband speed has not been established or advertised. However, the new network is capable of 286 Mb/s. | This project is not designed for retail services. | 7a. The State of New Mexico has implemented holistic network protocols to include: Multi Protocol Label Switching (MPLS), Open Shortest Path First (OSPF) and Border Gateway Protocol (BGP) for a complete self healing public safety network. 7b. No. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A
NT10BIX5570098 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 245364 | 0 | 0 | 0 | 2120 | 2544 | 240700 | N/A | 0 | 0 | 0 | 0 | N/A | 1) Chambers Group - Subcontract (Vendor) 2) Praxis Associates, Inc. - Sub-grant (Subrecipient) | (1) Obtain detailed engineering measurements and construction methods early in the process as a basis for budgeting and environmental studies. (2) Develop strong GIS mapping capabilities early on as a basis for Environmental Assessment and project documentation, (3) Build budget and plan as detailed as possible so that the various information is consistently developed and used. It is also a key basis for accurate modifications as plans or budget changes occur. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | N/A | N/A
NT10BIX5570098 | 2011 | 0 | Construction not started | 0 | NA | 0 | NA | 0 | We have not begun advertising as construction not started | 0 | NA | 0 | Construction not started | 0 | NA | None, Construction not started | NA | 7a. None, Construction not started 7b. No, Construction not started | None, Construction not started | 245364 | 0 | 0 | 0 | 2120 | 2544 | 240700 | ZAYO Group, LLC. ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber from us between Carson and Barstow. | 0 | 0 | 0 | 0 | We do not own collocation space but other network providers will be able to interconnect with our network at node sites, splice points, terminals and carrier central offices. | 1. Chambers Group - Subcontractor (Vendor) 2. Praxis Associates, Inc. - Sub-grant (Subrecipient) | Aggressively and continuously monitor primary environmental consultant using project staff or secondary consultant to ensure accurate and timely deliverable. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | None | None
NT10BIX5570098 | 2012 | 470,633.30 | The forecast of $229,097.78 was predicated on a higher completion of conduit and fiber placement by this time. These costs are based upon total dollars spent against the total miles of fiber placed. The dollars spent are heavily burdened with front end engineering, permitting, environmental, and materials acquisition costs. As the denominator increases with miles placed, these fixed costs will proportionately go down. | 0 | NA | 0 | NA | 10Gbps | Increase to 10Gbps from 2.5Gbps, due to unexpected demand and the fact that equipment hardware is cheaper to provision this level than to break services down to the 2.5Gbps. | 0 | NA | 0 | 10Mbps Variance - No anchors have yet to be connected. | 0 | NA | None - Construction started but no community anchor institutions connected | NA - This is a wholesale network | California Broadband Cooperative, Inc. (CBC) will solely manage the proposed funded network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently CBC does not discriminate or favor any lawful Internet applications, content, or services where lawfully used, and these same practices will be continued for the proposed funded network. We promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. While CBC does not engage in blocking customer access to illegal or legal Internet content, CBC supports industry practices for safeguarding children, intellectual property rights and our customers' privacy and security. CBC follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. CBC uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None - Network presently under construction but no community anchor institutions connected. | 245364 | 0 | 0 | 47088 | 2120 | 2544 | 193612 | ZAYO Group, LLC ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber between Carson and Barstow. | 1664 | 712 | 0 | 952 | NA - We own collocation space | N/A | 1) External stakeholder management and on-going interactions with Agencies is important factor. Local agencies, and elected officials expect a high degree of information. We were able to achieve this with a dynamic web site that kept the public informed of our progress. 2) Timeframes and complexity of environmental permits and approvals are exponentially related to the number of agencies involved. In many instances, at project start, many agencies are unfamiliar with longitudinal projects, especially fiber. Many of the paradigms they use in their work do not apply. 3) Flexible start dates should be included in construction contracts, as seasonality can have a great impact of future cost changes. 4) Strength in contract administration is a Key Success Factor. This includes a high level of field inspections, regulatory compliance, and thorough documentation. The use of databases and cloud computing is especially effective. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | 1) Agreements Entered Into ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. AT&T Nevada – Signed interconnection agreement for NV. Verizon California – Signed interconnection agreement for CA. Suddenlink - Signed agreement for dark fiber 2) Agreements Being Negotiated - 11 3) NA | 1) Agreements Entered Into ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Level 3 - Signed interconnection agreement for collocation and peering for Barstow and Reno. 2) Agreements Being Negotiated - 0 3) NA
NT10BIX5570098 | 2013 | 181,498.07 | The forecast of $139,191.74 was predicated on a an overrun in budget due to higher environmental permitting costs and method of construction (i.e, change in CPUC Pole calculation formulas) There was approximately $25M in environmental costs. | 0 | NA | 0 | NA | 10Gbps | Increase to 10Gbps from 2.5Gbps, due to unexpected demand and the fact that equipment hardware is cheaper to provision this level than to break services down to the 2.5Gbps. | 0 | NA | 500Mbps | Increase from 10Mbps, due to the connection of only 6 customers through the end of 2013. These initial customers are significantly heavier users of bandwidth. As the remaining customers are hooked up we expect the average bandwidth speed to decrease toward the average bandwidth projected | 0 | NA | 48.5 MB increase. This is calculated based on the majority of customers were receiving T1 service and will now have 50MB delivered via a gigabit ethernet circuit allowing growth of up to 1000MB. | NA - This is a wholesale network | California Broadband Cooperative, Inc. (CBC) will solely manage the proposed funded network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently CBC does not discriminate or favor any lawful Internet applications, content, or services where lawfully used, and these same practices will be continued for the proposed funded network. We promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. While CBC does not engage in blocking customer access to illegal or legal Internet content, CBC supports industry practices for safeguarding children, intellectual property rights and our customers' privacy and security. CBC follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. CBC uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None - Network presently under construction and only few community anchor institutions were connected in December | 245364 | 2248 | 0 | 243116 | 0 | 0 | 0 | ZAYO Group, LLC ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber between Carson and Barstow. | 1664 | 712 | 0 | 952 | NA - We own collocation space | NA | 1) External stakeholder management and on-going interactions with Agencies is important factor. Local agencies, and elected officials expect a high degree of information. Use web sites and any available media opportunities. 2) Time frames and complexity of environmental permits and approvals are exponentially related to the number of agencies involved. In many instances, at project start, many agencies are unfamiliar with longitudinal projects, especially fiber. Many of the paradigms they use in their work do not apply. 3) Flexible start dates should be included in construction contracts, as seasonality can have a great impact of future cost changes. 4) Strength in contract administration is a Key Success Factor. This includes a high level of field inspections, regulatory compliance, and thorough documentation. The use of databases and cloud computing is especially effective. 5) Strong focus on agile budget management and cost control. 6) In additional to fundamental network construction capability, fiber optic projects have complex data communication elements that must be properly designed, implemented and managed. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | 1) Agreements Entered Into Plumas Sierra - Signed internet and collocation agreement Lone Pine TV - Internet Access SchatNet - Internet Access and Transport 2) Agreements Being Negotiated - 3 3) Have we denied a request for interconnection and if so, why? No | 1) Agreements Entered Into - 0 2) Agreements Being Negotiated - 0 3) Have we denied a request for interconnection and if so, why? No
NT10BIX5570098 | 2014 | 179,132.25 | The forecast of $139,191.74 was predicated on a an overrun in budget due to higher environmental permitting costs and method of construction (i.e, change in CPUC Pole calculation formulas) There was approximately $25M in environmental costs. | 0 | NA | 0 | NA | 10Gbps | Increase to 10Gbps from 2.5Gbps, due to unexpected demand and our new pricing is more affordable and cost effective allowing customers to purchase higher plans. We advertise 10Gbps but can go as high as 100Gbps | 0 | NA | 60Mbps | Increase from 10Mbps, our new pricing is more affordable and cost effective allowing customers to purchase higher plan and therefore increasing the average speed. | 0 | NA | 50MB increase. This is calculated based on the majority of customers were receiving T1, DSL and Cable service and will now have 50MB delivered via a gigabit ethernet circuit allowing growth of up to 1000MB. | NA - This is a wholesale network | California Broadband Cooperative, Inc. (CBC) will solely manage the proposed funded network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently CBC does not discriminate or favor any lawful Internet applications, content, or services where lawfully used, and these same practices will be continued for the proposed funded network. We promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. While CBC does not engage in blocking customer access to illegal or legal Internet content, CBC supports industry practices for safeguarding children, intellectual property rights and our customers' privacy and security. CBC follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. CBC uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | NA - There have not been any subscribers who have dropped the broadband service | 245044 | 2340 | 0 | 242704 | 0 | 0 | 0 | ZAYO Group, LLC ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber between Carson and Barstow. | 1664 | 712 | 15 | 937 | NA - We own collocation space | NA | GENERAL â€¢ Allow sufficient time for projects to be successfully executed. Projects are bound by three factors: Scope, Resources and Time. The inability to vary all of these components makes project success extremely difficult. While aggressive time frames are important, unrealistically short time frames lead to parallel processes, greater risk, and rework. â€¢ Know all the administrative requirements from funding and oversight agencies so that the correct processes, data collection and designs are in place to meet reporting and compliance needs. â€¢ Establish a â€œhigherâ€ mission and goal for the project beyond the work. Team and stakeholders must see the greater (perhaps historical) significance to what they do. This is a source of energy during trying times. STAKEHOLDER MANAGEMENT â€¢ Develop strong project branding that the local community can identify with: â€œDigital 395â€ (named after the highway prominently running through the region) was easy to engage and recognize. â€¢ Develop a comprehensive communications plan, including stakeholder analysis, core/consistent messaging, and channel strategy. â€¢ Extensively use multimedia and digital communications: web site, social networking (Twitter, Face Book, etc), public meetings, and local media. â€¢ Extensively use web site as clearinghouse for official communications, job, bid notices, bid awards, and project progress. â€¢ Thoroughly set community expectations of project execution, impacts, and â€œwhatâ€™s in it for them.â€ PROJECT MANAGEMENT â€¢ Extensively use Contingency Planning methodologies in the Project Planning process. An adequate execution strategy must be in place at the outset, but it must be flexibly employed as the project unfolds detailed steps. â€¢ Utilize Cloud technology (Drop Box, Evernote) for storing and sharing data. â€¢ Develop, define and train all personnel on the Project Management processes and tools that will be used in the project. â€¢ Structure information in accessible, well-organized databases and make them widely accessible â€¢ Establish formal project scheduling, meetings, and regular progress status reports. Rigidly hold to these to establish project structure. â€¢ Establish an incident reporting hierarchy for involvement by leadership, create an escalation process to remove agency bureaucratic road blocks â€¢ Constant/persistence pressure on State and Federal permitting agencies to meet project targets â€¢ Develop a highly effective contract administration process ï‚§ Find proven, effective model contracts for boilerplate solicitations aimed at minimizing change requests and unexpected extra costs ï‚§ Use well-documented and consistent processes for bid solicitation, evaluation and on-going contract administration. ï‚§ Develop an effective program to monitor construction processes, perform inspections and documentation performance. Provide compliance training on safety, permits, and construction standards. ENVIRONMENT AND PERMITS â€¢ Recognize that Environmental Permits will have a profound impact on the scope, cost, and timeframes of the project. Carefully develop a comprehensive environmental plan in the earliest stages of the project. ï‚§ Create and staff a position on the project team regarding Biological and AHPA environmental requirements, processes and mitigation ï‚§ Clear and thorough understanding of the route, scope and construction processes of the project and their corresponding environmental requirements. Document this thoroughly with a walk-through by environmental team ï‚§ Work with local and regional environmental stakeholders early in the project design to determine contentious or sensitive areas / issues. ï‚§ Work with the permitting agencies to define a clear Scope of Work for and deliverables for the Environmental Process. ï‚§ Clearly establish and document environmental monitoring coordination process and communicate effectively throughout the organization. ï‚§ Engage tribal stakeholders early in the process and obtain written agreements on cultural considerations, Rights-of-Way, and project impacts. ï‚§ Recognize that environmental requirements will be a considerable factor in project constraints and engineering design. Educate engineering on the environmental rules early in the process. â€¢ Thoroughly investigate the selection of environmental firms to ensure that their project team has the experience corresponding to the project, especially with regard to the area for planned development. â€¢ Wherever possible avoid Programmatic Agreement. â€¢ Include permit stipulations in permit negotiations â€¢ Clearly define implications and level of accuracy for APE, establish early on in the design process and the ramifications for changes, violations and costs. In doing this, work design scenarios with key agencies prior to engineering designs. â€¢ Survey both sides when following roads to enable route flexibility â€¢ Shift environmental effort from studies to mitigation to save time â€¢ Be sure to understand that the project is not the â€œmain projectâ€: Understand ALL components with respect to environmental and permit requirements. ENGINEERING AND DESIGN â€¢ Adequately staff engineering early in the project to complete route requirements and create construction drawings for bidding. â€¢ Obtain engineering base maps at the outset of the project so that all documentation can be captured in GIS â€¢ Obtain shapefiles on all environmentally sensitive areas for route development â€¢ Extensive use of ortho imagery and GIS Surveying Tools reduces field time and facilitates agency communication. â€¢ Closely integrate construction, permitting, and rights-of-way skills into initial route selection to avoid rework high costs. â€¢ Pre-Construction staking of route using GIS to within one-foot accuracy. â€¢ Use accurate CAD measurements as basis of all materials and contracts. CONSTRUCTION MANAGEMENT â€¢ Integrate construction expertise in route selection and requirements definition â€¢ Clarify work operations to identify staging and lay down area requirements. â€¢ Project Documentation ï‚§ Establish real-time documentation and inspections ï‚§ Consolidate documentation forms and go paperless, leveraging database ï‚§ Integrate documentation and photos with data capture â€¢ Extensively train personnel on compliance, mitigation, safety, permit requirements, and documentation â€¢ Utilize electronic signature technology to facilitate field operations, approvals, documentation â€¢ Establish materials depots and assign contractors and materials handlers accordingly. Use floaters to address load imbalances. â€¢ Ensure have flexibility to add depot locations for material dispersals RIGHTS-OF-WAY AND ENCROACHMENT PERMITS â€¢ Establish ROW boundaries and land use early on â€¢ Work with Federal and State land agencies to assess documentation requirements, along with terms and conditions required during construction. â€¢ Focus on Public ROWs; avoid private ROWs â€¢ Clarify Public Works plans to take advantage of related projects and avoid conflicts or future re-routes â€¢ Avoid bridge-crossings and controlled access highways â€¢ Set agency requirements for permits, agree on process and get buy in (to overcome agency resistance to issuing the work). â€¢ Obtain local leadership to engage commitment from local federal and state agencies. â€¢ Develop personal relationships with agency contacts for coordinating required work. FINANCIAL AND BUDGET MANAGEMENT â€¢ Comprehensively develop financial tools at the outset of the project. ï‚§ Understand Agency requirements and develop Chart of Accounts accordingly. ï‚§ Use Chart of Accounts in forecasting, budgeting and reporting ï‚§ Train staff on Agency requirements, account definitions and closely monitor for consistency â€¢ Establish detailed budget categories, tracking and training early â€¢ Utilize digital signature and other emerging applications to facilitate information exchanges and approvals. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | 1) Agreements Entered Into Plumas Sierra - Signed internet and collocation agreement Lone Pine TV - Internet Access SchatNet - Internet Access and Transport Escape Broadband - Internet Service Northern Nevada High Speed - Internet Service East Sierra.net - Internet Service 2) Agreements Being Negotiated - 3 3) Have we denied a request for interconnection and if so, why? No | 1) Agreements Entered Into - 0 2) Agreements Being Negotiated - 0 3) Have we denied a request for interconnection and if so, why? No
NT10BIX5570099 | 2010 | $0 | N/A | $0 | N/A | $0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7a. N/A 7b. No | N/A | 12961 | 0 | 0 | 0 | 1548 | 0 | 11413 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A
NT10BIX5570099 | 2011 | $0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated average cost per new mile for Middle Mile is expected to be around $40,511. | N/A | N/A | N/A | N/A | 0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated maximum broadband speed advertised for Middle Mile is expected to be 20 Mbps. | 0 | N/A | 0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated average broadband speed provided for Middle Mile is expected to be 10 Mbps. | 0 | N/A | N/A | N/A | 7a. N/A 7b. No | N/A | 12961 | 0 | 0 | 0 | 1548 | 0 | 11413 | NA | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A
NT10BIX5570099 | 2012 | $33,500 | Due to construction re-bid, Bloomingdale Communications, Inc. has not completed construction by the end of December 2012. The construction is close to completion and will be fully complete within the 3 year project window. However, through December 31, 2012, Bloomingdale Communications has spent around $33,500 per new mile based on total budget. | N/A | N/A | N/A | N/A | N/A | Bloomingdale Communications, Inc. has not completed construction by the end of December 2012, therefore speeds have not been advertised at this point in the project. However by the end of the project the estimated maximum broadband speed advertised for Middle Mile is expected to be 100 Mbps. | N/A | N/A | N/A | Bloomingdale Communications, Inc. has not completed construction by the end of December 2012, therefore is not providing average broadband speeds yet. However, by the end of the project the estimated average broadband speed provided for Middle Mile is expected to be 20 Mbps. | N/A | N/A | N/A, Bloomingdale Communications, Inc. has not completed construction of the project yet, therefore the average increase in broadband speed provided to the community anchor institution customers is not applicable at this time. | N/A, Bloomingdale Communications, Inc. is not providing retail services by this project. | 7a. Bloomingdale has an Acceptable Use Policy (AUP) on its website (http://www.bloomingdalecom.net/forms.php) regarding network management practices, performance and commercial terms of service sufficient for consumers to make an informed choice regarding their use of such services. Bloomingdale will not unjustly or unreasonably prevent or interfere with competition among content, applications, service, or device providers. Following is a non-exclusive list of policies included within Bloomingdaleâ€™s AUP: Bloomingdale uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. Bloomingdale reserves the right to 1) immediately disconnect or modify Service if determined that use of Service is inconsistent with normal residential or business usage patterns or is in violation of the AUP; 2) protect its network from harm, which may impact legitimate data flows; 3) limit throughput or amount of data transferred, and to deny or discontinue service, without notice, to anyone it believes is using an unlimited data plan or feature in any manner prohibited by the AUP or whose usage adversely impacts network or service levels. Bloomingdale is under no obligation to monitor customer's usage, bandwidth, transmissions and/or content of Service however may do | N/A | 16043 | 0 | 0 | 0 | 1548 | 0 | 14495 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A
NT10BIX5570099 | 2013 | $48,900 | Bloomingdale Communications, Inc (BCI) has completed the project and average cost per mile based on the total budget is around $48,900 per new mile. | N/A | N/A | N/A | N/A | 100 Mbps | BCI currently advertises up to 100 Mbps. | N/A | N/A | 40 Mbps | Based on the 32 Community Anchor Institutions (CAIs) BCI currently provides service to utilizing the new network, the average speed subscribed to is 40 Mbps. | N/A | N/A | Using straight average calculation, the average increase in broadband speed provided to the 32 CAIs that are taking the new service from BCI is about 30 Mbps. The average of the 32 CAIs previous speed was around 10 Mbps, however the new average speed since connected to the new network and subscribing to BCI service the average speed is now around 40 Mbps. | N/A, BCI is not providing retail services by this project. | 7a. Bloomingdale has an Acceptable Use Policy (AUP) on its website (http://www.bloomingdalecom.net/forms.php) regarding network management practices, performance and commercial terms of service sufficient for consumers to make an informed choice regarding their use of such services. Bloomingdale will not unjustly or unreasonably prevent or interfere with competition among content, applications, service, or device providers. Following is a non-exclusive list of policies included within Bloomingdaleâ€™s AUP: Bloomingdale uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. Bloomingdale reserves the right to 1) immediately disconnect or modify Service if determined that use of Service is inconsistent with normal residential or business usage patterns or is in violation of the AUP; 2) protect its network from harm, which may impact legitimate data flows; 3) limit throughput or amount of data transferred, and to deny or discontinue service, without notice, to anyone it believes is using an unlimited data plan or feature in any manner prohibited by the AUP or whose usage adversely impacts network or service levels. Bloomingdale is under no obligation to monitor customer's usage, bandwidth, transmissions and/or content of Service however may do | N/A, no BCI subscribers have dropped the new broadband service. | 14172 | 974 | 0 | 13198 | 0 | 0 | 0 | N/A | 480 | 392 | 0 | 88 | BCI connects to their customers network with an Overture Network Interface Device (NID) that resides at the customers location. This NID has the ability to connect either with a fiber or copper connector. The Overture NID connects back to the Cyan transport network via fiber. They Cyan transport then carries the customer traffic to whatever end point is required by the customer. If the customer is needing internet connectivity BCI has two ISPâ€™s that they connect with to provide that service. The interconnection to the ISPâ€™s is located in the Bloomingdale central office. | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A
NT10BIX5570100 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 106560 | 0 | 0 | 0 | 17760 | 5920 | 82880 | N/A | 6 | 6 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | N/A | Working through the Environmental Assessment (EA) can be time consuming process. Because of this we have been working concurrently on other tasks that will allow us to be ready to start construction once we have received our Finding of No Significant Impact (FONSI). This has included working on obtaining Rights of Way from local municipalities, railroads, and the Illinois Department of Transportation. These all take time, so doing this at the same time as the EA is being done has been a good use of our time. We have also been going through the selection process of equipment vendors as well as going through the RFP process for selecting our General Contractor. All of these processes take time, so doing these at the same time as the EA is being done has been a good use of our time. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | N/A | N/A
NT10BIX5570100 | 2011 | $44,975.92 | End of Year 2011 is the end of our Q2 Year 2. Our baseline estimated cost per mile for Year 1 to be $56,657 and Year 2 to be $36,972. Our cost of $44,975.92 is in line with our baseline projections. | 0 | N/A | 0 | N/A | I Gig. | In line with baseline | 0 | N/A | 0 | N/A | 0 | N/A | As of the end of 2011 we have not begun to provide broadband service. | As of the end of 2011 we have not begun to provide broadband service. | As of the end of 2011 we have not begun to provide broadband service. | We have not begun providing service, so we have not had any subscribers drop the service. | 106560 | 328 | 0 | 0 | 17432 | 5920 | 82880 | N/A | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | N/A | Rights of Way and Permitting â€“ This will take longer than expected. To be able to make significant construction progress you must stay ahead of the permitting process. Allow for ample time for Railroad permits as well as certain highway and local permitting. We have been helped by using people that are experienced in dealing with these entities, but the process is still time consuming. You must plan for the time it will take and match that to your desired construction time lines. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | N/A. We are in negotiations with 6 third party service providers. This process is going slower than expected. Most carriers want at least part of the network to be lit before they sign an agreement. | N/A
NT10BIX5570100 | 2012 | 43,127 | Higher than baseline of 36,972 due to higher construction and permitting costs than anticipated. | NA | NA | NA | NA | 1 Gig | In line with baseline plan | NA | NA | 50 Mbps | Slightly lower than baseline of 76.76 for year two, but in line with baseline of 50.95 by the end of year 3. | NA | NA | The average increase in broadband speed has been approximately 38 Mbps. Most of the CAIs we serve had single or multiple T1's before the project. We estimate their prior broadband speeds to be 12 Mbps. Their average speed today is a little over 50Mbps. This gives an average increase of broadband speed of 38 Mbps or 216%. | Ethernet Services ranging in speeds of 10 Mbps to 1 Gbps and Internet Services. | 7a. We have no network management policies to limit bandwidth or prioritize traffic. 7b. We have not limited nor blocked consumers from accessing any legal content, service, service provider, nor application, nor prevented any consumers from attaching any legal device to the network. | No subscribers have dropped the broadband service provided through this project | 106560 | 5699 | 0 | 91069 | 0 | 0 | 9792 | NA | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | NA | Creating and marketing your brand can be a key factor in making your project sustainable. Clearwave utilizes our own sales and marketing team including business to business account executives. Company team members are avid in attending events of other businesses in the communities. Members have attended: Open houses, grand openings, ribbon cuttings, chamber luncheons and dinners, technology showcases, summits, seminars, and job fairs. Members also present at town hall meetings and other organizational meetings. These events are attended by decision makers and civic leaders. Attendees are given take-home packets full of informational materials including key facts, slideshow handouts, and contact information. Clearwave produces an informative newsletter every quarter, and has made a media presence with news releases, and paid advertising through radio, newspaper, and events. Clearwave also has a social media presence with Facebook, Twitter, and YouTube. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | [REDACTED] | [REDACTED]
NT10BIX5570100 | 2013 | $45,903 | Higher than baseline of 36,972 due to higher construction costs than anticipated. | NA | NA | NA | NA | 1000 Mbps | In line with Baseline | NA | NA | 50.59 Mbps | Within 99% of baseline estimate of 50.95 Mbps. Subscribed speeds range between 10Mbps and 1000 Mbps. 57% of subscribers are getting less than 50 Mbps and 43% are getting 50 Mbps and higher. | NA | NA | The average increase in broadband speed has been approximately 38 Mbps. Most of the CAIs we serve had single or multiple T1's before the project. We estimate their prior broadband speeds to be 12 Mbps. Their average speed today is a little over 50Mbps. This gives an average increase of broadband speed of 38 Mbps or 216%. | Ethernet Services ranging in speeds of 10 Mbps to 1 Gbps and Internet Services. | 7a. We have no network management policies to limit bandwidth or prioritize traffic. 7b. We have not limited nor blocked consumers from accessing any legal content, service, service provider, nor application, nor prevented any consumers from attaching any legal device to the network. | None have dropped service. | 107318 | 9860 | 0 | 97458 | 0 | 0 | 0 | NA | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's network. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | NA | Clearwave Communications has successfully completed the construction of 749 miles of fiber and has signed up 230 Community Anchor Institutions for service by the scheduled end date of our project. Lessons learned include a greater appreciation that in a project of this magnitude obstacles and challenges occur almost every week. Being a small company we were able to meet these challenges and make adjustments quickly. In order to react and adjust to these challenges in a timely manner your management structure needs to be lean and efficient. Another lesson learned is that costs of engineering and permitting are significant and can be much higher than expected. The amount of time and expense involved in completing the Environmental Analysis as well as the network design were higher than anticipated. Permitting costs are also a significant expense in being able to complete a project of this size. As an example we had over 80 different railroad permits in our project area. These can be time consuming and expensive and need to be considered when making budgets and time lines. Clearwave was fortunate to have an existing sales team that had a strong presence in most of our proposed service area. Because of this we were able to contract and provide service to 200 of the original 232 CAIs that we listed in our original application and serve 230 CAIs by the end of our project. Highlighted among these 230 CAIs, we were able to greatly improve the bandwidth connectivity at 105 K-12 Schools and 62 Medical facilities. These institutions will be able to benefit from the BTOP initiative for years to come, and our company is proud to have been a part of that initiative. To accomplish a project of this size in this short a period of time you need a management team that is committed to the goals you have. They must be willing to handle setbacks and challenges in a proactive way. You also need to have the ability to communicate and make decisions in an efficient manner. We were fortunate to already have that type of management team and structure in place before the project began. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | [REDACTED] | [REDACTED]
NT10BIX5570101 | 2010 | 0 | No variance | NA | No variance | NA | No variance | 0 | No variance | NA | No variance | 0 | No variance | NA | No variance | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | 11832 | 0 | 0 | 0 | 1092 | 120 | 10620 | NA | 0 | 0 | 0 | 0 | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | - AVFN has learned that finalization of fiber routes, both primary and alternate routes, is a critical path item for commencement and completion of the environmental assessment process. EA consultants must have clear and documented fiber route maps in order to perform the necessary surveys. AVFN advises other applicants to begin the process of route finalization as early as possible. - AVFN has learned that resolving potential duplication of funding issues (AKA overlaps) is a time-consuming process. Other applicants often do not share the same urgency to resolve these issues, and are often unwilling or unable to share detailed street-level maps. AVFN advises other applicants to begin the process to resolve such overlaps as early as possible. - AVFN has learned that securing the eventual commitment of community anchor institutions is an ongoing, time-consuming process. While project planning and construction is underway, applicants must also be communicating consistently with potential CAIs to educate them on the services the network will offer, stay up to date on deadlines (e.g. eRate) faced by those CAIs, set the CAIs expectations on when service will be available, and educate CAIs on the importance of CAI commitment to the network. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI.
NT10BIX5570101 | 2011 | 0 | N/A. Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. Therefore, no broadband speeds are currently being advertised. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. Therefore, no broadband speeds are currently being provided. | 0 | N/A. AVFN is a purely middle-mile project. | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over its network yet. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | None are in place at this time, since fiber availability has prevented AVFN from being able to offer services over the network. AVFN does have a non discrimination and interconnect policy in place and it adheres strictly to the requirements and intent of the BTOP program. | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over the network yet. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over the network yet. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | Due to lack of fiber availability, AVFN has not begun to interconnect with other service providers yet. | Due to lack of fiber availability, AVFN has not begun to peer with other service providers yet.
NT10BIX5570101 | 2012 | 48000 | Cumulative direct middle mile capital costs divided by total new miles. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 10Gbps | Maximum speed offered. | 0 | N/A. AVFN is a purely middle-mile project. | 20Mbps | Average speed of subscribers. | 0 | N/A. AVFN is a purely middle-mile project. | Since AVFN is a wholesale-only, middle mile provider, it does not have visibility into the speeds provisioned by retail customers before and after the AVFN network is introduced. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | AVFN has no bandwidth caps, throttling, blocking of lawful content or other traffic prioritization schemes in place. AVFN supports the free and open nature of the Internet and embraces the FCC's policy on the "Four Freedoms." | None. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | Parker FiberNet is AVFN's only wholesale customer at this point. AVFN does not have a measurement of the number of strand miles at this time. AVFN leases dark fiber to service providers, including Parker FiberNet, on a customer-connection basis, and these connections can vary in length. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Permitting processes can vary greatly from state to state. Do not assume timing is the same or even similar. Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | In 2012, AVFN signed an interconnection agreement with Parker FiberNet. AVFN is currently negotiating three additional interconnect agreements. AVFN has not denied any request to interconnect. | AVNF has signed an agreement for colocation space at the 56 Marietta Telx facility in Atlanta. AVFN is currently coordinating with North Georgia Network (NGN) and Troy Cablevision to peer at the Telx facility.
NT10BIX5570101 | 2013 | 52072 | Cumulative direct middle mile capital costs divided by total new miles | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 10Gbps | Maximum speed offered | 0 | N/A. AVFN is a purely middle-mile project. | 20Mbps | Average speed of subscribers | 0 | N/A. AVFN is a purely middle-mile project. | Since AVFN is a wholesale-only, middle mile provider, it does not have visibility into the speeds provisioned by retail customers before and after the AVFN network is introduced. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | AVFN has no bandwidth caps, throttling, blocking of lawful content or other traffic prioritization schemes in place. AVFN supports the free and open nature of the Internet and embraces the FCC's policy on the "Four Freedoms." | None. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | Parker FiberNet is AVFN's only wholesale customer at this point. AVFN does not have a measurement of the number of strand miles at this time. AVFN leases dark fiber to service providers, including Parker FiberNet, on a customer-connection basis, and these connections can vary in length. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Permitting processes can vary greatly from state to state. Do not assume timing tis the same or even similar. Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, and proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. Overestimate the amount of time it takes to closeout on construction activities with subcontractors. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | In 2013, AVFN signed an interconnection agreement with Cartersville FiberCom and Calhoun Telecommunications (Calnet) of Calhoun. AVFN is not currently negotiating any additional interconnect agreements. AVFN has not denied any request to interconnect. | None for 2013
NT10BIX5570102 | 2010 | 0 | In this and all upcoming narratives, the following remains true: The Baseline Report collected a Year 1 figure, which UAMS understood to include the first 12 months of the project period. However, the 2010 Annual Report appears to collect information on progress on a calendar year basis (January 1 - December 31), rather than a 12-month basis (First month of Project Period to 12th month of Project Period). Since the UAMS BTOP grant was awarded in August 2010, the outcomes reported on this 2010 Annual Report only embody the first five months of the grant period, which was dedicated to Environmental Assessment development and planning activities. As such, the figures provided in the Baseline Report differ from those reported in this 2010 Annual Report for the reasons described. As verification, the reported figures in this report are on target with the progress UAMS expected by Month Five of the first year of the project period. | 0 | N/A | 0 | N/A | 0 | See explanation above. The Baseline Report figure and the figure reported here differ in terms of timing: Baseline reflects first 12 months of the project period; whereas the Annual Report reflects the first 5 months of the project. The reported outcome is accurate to anticipated progress by Month 5 of the project period. | 0 | N/A | 0 | See explanation above. The Baseline Report figure and the figure reported here differ in terms of timing: Baseline reflects first 12 months of the project period; whereas the Annual Report reflects the first 5 months of the project. The reported outcome is accurate to anticipated progress by Month 5 of the project period. | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | In this, the first five months of the Arkansas Healthcare, Higher Education, Public Safety, & Research Integrated Broadband Initiative, the University of Arkansas System has noted several best practices and lessons learned that may be helpful in other BTOP projects, Some of these comments may only be helpful for projects in the planning phases of their BTOP projects. At such a time when these comments are circulated, most BTOP projects will have progressed beyond such a stage. * Meet weekly with your Federal Program Officer (FPO) and collect non-pressing questions for your time with him or her. Contact your FPO directly for pressing questions. * For in-kind match items, begin filing Uniform Commercial Codes (UCCs) for the contributed items as soon as possible. Many items may be included on a single form. * Create a BTOP project website and launch promptly to route requests and news updates for your partners and visitors. * To organize numerous vendor contacts, create a distribution list for vendors to notify them when Request for Proposals and related requests are released in respect to your BTOP-funded project. * Designate a single person to act as primary contact to the FPO and other Federal officials to help streamline communication. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A
NT10BIX5570102 | 2011 | 0 | The network is still being built-out. Per instructions, the information is N/A until deployment for the network is complete and in service. | 0 | N/A | 0 | N/A | 10Gpbs | The ARE-ON backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connections to all ARE-ONâ€™s CAIs. | 0 | N/A | 1Gbps | The ARE-ON backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connection to all ARE-ONâ€™s CAIs. | 0 | N/A | The project's healthcare CAI were provided with new broadband, therefore their increase would be 100%. This consists of 307 sites with <10Mbps; 82 sites with >/= 10Mbps and <50Mbps; seven sites with >/= 100Mbps and <1000Mbps. The average broadband speed for the two-year colleges (12 of 22 respondents) is 21.4Mbps (minimum is 6Mbps, maximum is 56Mbps). The project is providing 1000Mbps (1Gbps) connections to each of the schools, for an average increase of 978.6Mbps. The individual schools can opt for any commodity Internet bandwidth up to the full 1000Mbps per their campus needs and budget. The increase was calculated as the current average broadband speed subtracted from the new connection speed of 1000Mbps. | N/A | The project currently does not have any portion of the expanded network completed or in service. However, the projectâ€™s network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 10240 | 0 | 0 | 0 | 0 | 4141 | 6099 | N/A | 200 | 196 | 0 | 4 | Network providers will interconnect with our network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. Network providers can also interconnect at one of our member institutions where we maintain a presence. | N/A | Items to consider should include standardization of data, data management and face-to-face contact in the field with CAI. Structure a strong plan for inventory management and support. Block time for adequate reporting preparation and submission for both federal and internal needs. For fiber construction, use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. Be as specific as possible about every aspect of the construction, including setting minimum standards for testing and acceptance. In selecting the contractors, consider an interview or selection process that identifies specific skill levels needed for the type of fiber and writing specifications for such in the contract. Pay for and perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. For hut construction, be as detailed as possible on every aspect of their construction. Consider having your hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A
NT10BIX5570102 | 2012 | 0 | The network is still being built-out. Per instructions, the information is N/A until deployment for the network is complete and in service. | 0 | N/A | 0 | N/A | 10Gbps | The Arkansas e-Link backbone can support connection speeds up to 10 Gbps. | 0 | N/A | 1Gbps | The Arkansas e-Link backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connection to all Higher Ed CAIs. | 0 | N/A | The project's healthcare CAIs were provided with new broadband, therefore their increase would be 100%. This consists of 291 sites with <10Mbps; 77 sites with >/= 10 Mbps and <50 Mbps; five (5) sites with >/= 50 Mbps and <100 Mbps; and, 1 site with <1000 Mbps. At the end of the project, the average broadband speed for the two-year colleges (12 of 22 respondents) is 21.4Mbps (minimum is 6Mbps, maximum is 56Mbps). The project is providing 1000Mbps (1Gbps) connections to each of the schools receiving fiber connectivity, for an average increase of 978.6Mbps, and 100Mbps connections to each of the schools receiving broadband circuit connectivity, for an average increase of 78.6Mbps. The individual schools can opt for any commodity Internet bandwidth up to the full capacity of the connection per their campus needs and budget. The increase was calculated as the current average broadband speed subtracted from the new connection speed of 1000Mbps or 100Mbps. | N/A | Arkansas e-Link currently does not have any portion of the expanded network completed with the exception of Southern Arkansas University, Magnolia. The projectâ€™s network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video-conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 11687 | 1574 | 0 | 9848 | 9 | 0 | 256 | N/A | 200 | 196 | 0 | 4 | Network providers will interconnect with the network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. ARE-ON can provide a limited amount of space for collocation within the facilities. ARE-ON typically connects to its members (colleges and universities) via direct fiber into the customer's campus. Members can also interconnect at a member institutions where we maintain a presence. | N/A | UAS suggests these best practices/lessons learned: â€¢ Start the Environmental Assessment (EA) process as early as possible and monitor consultant for timely completion. â€¢ Develop and implement operational procedures. â€¢ To help stay focused, review project goals often with your team. â€¢ Identify and study institutional and regulatory requirements. â€¢ Develop a checks and balances system to ensure that sub-recipient is compliant with regulatory requirements. â€¢ Maintain effective communication with partners and vendors by keeping them informed and updated. â€¢ Develop strategy for inventory management. â€¢ Maintain schedule of compliance deadlines. â€¢ Define data that is needed from CAIs and develop comprehensive plan for acquiring and managing the data. â€¢ Keep a reference log of decisions made between recipient and NTIA program officer and/or other representatives of NTIA. â€¢ Allow sufficient time in the process to develop, release, evaluate, and award bids for RFPs, including order lead time to avoid delays during deployment. â€¢ When selecting contractors for fiber construction, consider an interview or selection process that identifies specific skill levels needed and include these written specifications in the contract. â€¢ Use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. â€¢ Contracts should include specifics about every aspect of the construction, including setting minimum standards for testing and acceptance. â€¢ Perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. â€¢ Be as detailed as possible on every aspect of hut construction. â€¢ Consider having the hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A
NT10BIX5570102 | 2013 | $146,498 | This is calculated as the total allocated cost of construction of fiber and conduit, engineering, and splicing of all fiber laterals constructed in the project. | 0 | N/A | 0 | N/A | 10 Gb | The Arkansas e-Link backbone can support connection speeds up to 10 Gb. | 0 | N/A | 1 Gb | All ARE-ON fiber-connected CAIs have 1 Gb connections, and all ARE-ON circuit-connected CAIs have 100 Mb. | 0 | N/A | The project's healthcare CAIs were provided with improved broadband, therefore their increase would be 100%. This consists of: 296 sites with <10 Mb 80 sites with >/= 10 Mb and <50 Mb 8 sites with >/= 50 Mb and <100 Mb 21sites with >/=100 Mb and <1 Gb 9 sites with >/= 1 Gb The remaining 44 sites received BTOP-funded equipment but are using their own connectivity bringing our total to 458. The average broadband speed is 980 Mb. Typical broadband speeds for the community colleges was previously 6-20 Mb. All college CAIs received 1 Gb connections. The average was calculated by subtracting the high end of the two numbers. | N/A | 7a. The Arkansas e-Link portion of the network is a membership-only network, open only to defined and HIPAA compliant medical purposes. This is not a public, consumer-oriented network. The fiber projectâ€™s (ARE-ON) network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video-conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. 7b. Only standards-compliant devices will function on the e-Link network. The e-Link network is not a public, consumer-oriented network. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 11820 | 1583 | 0 | 10237 | 0 | 0 | 0 | N/A | 8738 | 8310 | 114 | 314 | Network providers will interconnect with the network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. Network providers can also interconnect at one of our member institutions where we maintain a presence. | N/A | UAS suggests these best practices/lessons learned: â€¢ Start the Environmental Assessment (EA) process as early as possible and monitor consultant for timely completion. â€¢ Develop and implement operational procedures. â€¢ To help stay focused, review project goals often with your team. â€¢ Identify and understand institutional and regulatory requirements. â€¢ Develop a checks and balances system to ensure that sub-recipient is compliant with regulatory requirements. â€¢ Maintain effective communication with partners and vendors. â€¢ Develop strategy for inventory management. â€¢ Maintain schedule of compliance deadlines. â€¢ Define data that is needed from CAIs and develop comprehensive plan for acquiring and managing the data. â€¢ Keep a reference log of decisions made between recipient and NTIA program officer and/or other representatives of NTIA. â€¢ Allow sufficient time in the process to develop, release, evaluate, and award bids for RFPs, including order lead time to avoid delays during deployment. â€¢ When selecting contractors for fiber construction, consider an interview or selection process that identifies specific skill levels needed and include these written specifications in the contract. â€¢ Use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. â€¢ Contracts should include specifics about every aspect of the construction, including setting minimum standards for testing and acceptance. â€¢ Perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. â€¢ Be as detailed as possible on every aspect of hut construction. â€¢ Consider having the hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. â€¢ Ensure there are comprehensive contracts with all vendors that assure grant requirements are met and flexibility is included. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A
NT10BIX5570103 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | 11658 | 0 | 0 | 0 | 896 | 906 | 9856 | No activity for year ending December 31, 2010. | 0 | 0 | 0 | 0 | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | Moving from proposal to actual award and implementation has caused the management team to review, refine and often modify preliminary program planning elements, desktop engineering assumptions, initial line item allocations and management practices. Estimates of those participating in the network, thus affecting the overall sustainability model, has been significantly enhanced now that the project is funded; requiring us to re-budget the capital resources needed to meet expected demand. The real lesson learned here is that once programs have a firm foundation, the leadership team must be flexible enough to meet new obligations and opportunities; all while ensuring compliance with BTOP policies. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | N/A | N/A
NT10BIX5570103 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | 63040 | 0 | 0 | 0 | 1219 | 4515 | 57306 | No Activity for year ending December 31, 2011. | 0 | 0 | 0 | 0 | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | Throughout the Environmental Assessment process, the management team has had to review, refine and modify aspects of the preliminary program planning elements; specifically addressing Tribal relation concerns and their impact upon network design. By including alternative routes within the EA as possible contingency plans, the network design was able to adapt as necessary. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | 1) 0 2) 2 3) 0 | N/A
NT10BIX5570103 | 2012 | $37,897.83 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 0 | N/A | 0 | N/A | 1G | Increased from 100 Mbps to 1G to meet market demand. | 1G | Increased from 100 Mbps to 1G to meet market demand. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | We are not yet providing services to CAIs. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | No activity for year ending December 31, 2012 | 7a. The Nondiscrimination and Network Management Policy and Interconnection Policy information are in place, available and published on the Subrecipient's Web site, the network operators of the project. A link to the policies are posted on the NHA Web site. 7b. We are not yet providing services to consumers therefore we have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | No activity for year ending December 31, 2012. | 47756 | 0 | 0 | 13858 | 1088 | 0 | 32810 | No activity for year ending December 31, 2012. | 0 | 0 | 0 | 0 | No activity for year ending December 31, 2012. | No activity for year ending December 31, 2012. | NHA has encountered challenges during year two of the project construction and environmental assessment process. Continuous evaluation, pre-planning tasks and modification in the project planning elements; specifically in acquiring local permitting; agreements for rights-of-way and other land easements; utility pole agreements and make-ready work; and other deployment activities helps identify and address barriers quickly to ensure timely project progress. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | 1) 2 (SwitchNAP - Las Vegas - 200M IP and Zayo - Reno - 200M IP) 2) 0 3) 0 (We have not denied interconnection to anyone.) | 1) 2 (SwitchNAP - Las Vegas - BGP Peering and Zayo - Reno - BGP Peering) 2) 0 3) 0 (We have not denied interconnection to anyone.)
NT10BIX5570103 | 2013 | 37897.83 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 0 | N/A | 0 | N/a | 1G | Increased from 100 Mbps 1G to meet market demand. | 1G | Increased from 100 Mbps 1G to meet market demand. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | We are not yet providing services to CAIs. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | No activity for year ending December 31, 2013. | 7a. The Nondiscrimination and Network Management Policy and Interconnection Policy information are in place, available and published on the Subrecipient's Web site, the network operators of the project. A link to the policies is posted on the NHA Web site. 7b. We are not yet providing services to consumers therefore we have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | No activity for year ending December 31, 2013. | 47756 | 0 | 0 | 13858 | 1088 | 0 | 32810 | No activity for the year ending December 31, 2013. | 0 | 0 | 0 | 0 | No activity for the year ending December 31, 2013. | No activity for the year ending December 31, 2013. | N/A | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | N/A | N/A
NT10BIX5570103 | 2014 | 40669.81 | Project construction restarted after completing corrective action plan process. | 0 | N/A | 0 | N/A | 1G | Maximum project speed did not change last year. | 1G | Maximum project speed did not change last year. | N/A | Service commencement is scheduled for 2015. Completion of the corrective action plan delayed 2014 commencement. | N/A | Service commencement is scheduled for 2015. Completion of the corrective action plan delayed 2014 commencement. | Improved service has yet to be delivered due to project delays encountered in 2014. | No activity for year ending December 31, 2014. | 7a. The Nondiscrimination and Network Management Policy and Interconnection Policy information are in place, available and published on the Subrecipient's Web site, the network operators of the project. A link to the policies is posted on the NHA Web site. 7b. We are not yet providing services to consumers therefore we have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | No activity for year ending December 31, 2014. | 46330 | 146 | 0 | 29734 | 877 | 0 | 15573 | No activity for year ending December 31, 2014. | 0 | 0 | 0 | 0 | No activity for year ending December 31, 2014. | N/A | N/A | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | Total number of new agreements: 1 A new interconnection agreement was completed with Nevada State Higher Education during 2014. | N/A
NT10BIX5570104 | 2010 | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | N/A;Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | 38394 | 0 | 0 | 0 | 7082 | 704 | 30608 | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | 0 | 0 | 0 | 0 | Contact Network Inc. is in process of negotiating collocation space in Jackson, MS and negotiations will be finalized in January 2011. In addition to this collocation space, we will have communication huts in each county. Service providers or customers that wish to make their own last mile connection into the network will be able to interconnect with us at the hut. We will also assist providers and customers with their last mile connection. | N/A | No comment | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities
NT10BIX5570104 | 2011 | 38,521 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out (ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 980Mbps | Currently we have 46 subscribers receiving 1000Mpbs and one receiving 10Mbps | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 968Mbps. This number was calculated based on the fact that all 47 of our current customers were receiving 1.5Mpbs before upgrading to our service. Forty six of our current customers are receiving 1000Mbps and one is receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 38602 | 286 | 0 | 9318 | 7082 | 704 | 30816 | As of December 31, 2011, Contact Network Inc. does not have any wholesale customers leasing dark fiber. | 1035 | 260 | 0 | 775 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | No comment | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570104 | 2012 | 44669 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out (ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 838Mbps | Currently we have nine subscribers receiving 10Mpbs and the remainder are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 836Mbps. This number was calculated based on the fact that all 55 of our current customers were receiving 1.5Mpbs before upgrading to our service. Forty Six of our current customers are receiving 1000Mbps and the rest are receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 31495 | 390 | 100 | 17672 | 746 | 0 | 12587 | We are leasing 25 miles of dark fiber or 100 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on permits for railroads, DOT and pole attachment. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570104 | 2013 | 47477 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 909Mbps | Currently we have 5 subscribers receiving 10Mbps; 4 receiving 100Mbps and 85 receiving 1000Mbps | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 836Mbps. This number was calculated based on the fact that 84 of our current customers were receiving 10Mpbs, the remainder had 1.5Mbps before upgrading to our service. Eight five of our current customers are receiving 1000Mbps, four are receiving 100Mbps and the rest are receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 31696 | 617 | 100 | 30223 | 0 | 0 | 756 | We are leasing 25 miles of dark fiber or 100 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on franchise agreements and permits for railroads, DOT and pole attachment. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570104 | 2014 | 45234 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 867Mbps | Currently we have 5 subscribers receiving 10Mbps; 14 receiving 100Mbps and 113 receiving 1000Mbps | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 803Mbps. This number was calculated based on the fact that 84 of our current customers were receiving 10Mpbs, the remainder had 1.5Mbps before upgrading to our service. One hundred and thirteen of our current customers are receiving 1000Mbps, fourteen are receiving 100Mbps and the rest are receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 31696 | 617 | 100 | 30979 | 0 | 0 | 0 | We are leasing 25 miles of dark fiber or 100 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on franchise agreements and permits for railroads, DOT and pole attachment. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection.
NT10BIX5570105 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A
NT10BIX5570105 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A
NT10BIX5570105 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | PLEASE NOTE: The data provided in response to questions 15 and 16 below are simply re-produced from the State's most recent Annual PPR, because they reflect the currently approved project, though that original project direction has been overtaken by events. Due to regulatory and budgetary issues stemming from the passage in February 2012 of the Middle Class Tax Relief and Job Creation Act (for example, NTIA's partial suspension of grant funds, the FCC's termination of the State's conditional permission to use the 700 MHz public safety broadband spectrum, and FirstNet's uncertainty whether it will permit the State to use such spectrum), the direction and budget of the State's project is in flux. The State has proposed a revised project to FirstNet; FirstNet has stated that it will respond to the State's proposal in February 2013. The State intends that, with FirstNet's guidance, it will then submit to NTIA a revised project budget, including revised data in response to questions 15 and 16 below. | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A
NT10BIX5570105 | 2013 | 0 | Based on the newly approved project scope, network miles will not apply to New Jersey moving forward. Because of the project focus on deployables , middle-mile calculations were removed from the project | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | The New Jersey BTOP team will purchase 37 deployable assets equipped with microwave and satellite backhaul, and end-user devices. The project calls for allocating 27 deployable assets (COWs and SOWs) for the three proof-of-concept networks, and 10 assets in ready standby which will be deployed as necessary throughout the State and Region. The deployables based networks will include LTE equipment, microwave, satellite, and appropriate Band Class 14 devices (Band Class 14 is the portion of radio spectrum that is licensed to FirstNet and designated for broadband services for the public safety community). The New Jersey BTOP team will procure User Equipment (UEs) â€“ specifically vehicular modems, dongles (USB wireless antenna devices), tablets and air cards â€“ that can be used with the LTE Band Class 14 services. Users of the deployable-based network will include State law enforcement, fire service, EMS and NJ Transit personnel. | N/A | We currently don't have any best practices/lessons learned to share with other BTOP projects. | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A
NT10BIX5570105 | 2014 | 0 | Based on the newly approved project scope, network miles will not apply to New Jersey moving forward. Because of the project focus on deployables , middle-mile calculations were removed from the project | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | CAIs have not been connected yet. | This is a public safety project and that retail services do not apply | The network will be managed using existing New Jersey Office of Information Technology policies on use and security of networks within the State. A regional Network Operations Center (NOC) will be integrated into the topology architecture to monitor against network outage issues and general overall health of the system. User access will be granted through a provisioning and security approval feature driven by the Office of Homeland Security and New Jersey State Police. To date no users access the network as the construction of the network in is process. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | NONE | Treasury, New Jersey Department of | 0 | 0 | 0 | 3 | 0 | 53 |  | 4 | 0 | 0 | 60 | N/A | N/A
NT10BIX5570106 | 2010 | 0 | NA | 0 | NA | 0 | NA | 100 mbps | Same as baseline | 0 | NA | 60 | NA | 0 | NA | NA | NA | 7a. NA 7b NA | NA | 80 | 0 | 80 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | NA | Multitasking for the project is essential in order to get a headstart on as many issues as possible. There are always delays caused by the schedules of various parties, weather, and unanticipated circumstances. Proactive and persistent contact with government agencies is essential in keeping tasks moving forward. Having one individual to oversee and understanding all aspects of the project is beneficial for keeping the tasks on schedule. Integration of the tasks by team meetings helps the coordinator have a firm grasp of the tracking and understanding of the reporting requirements. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA
NT10BIX5570106 | 2011 | 0 | NA | 0 | NA | 0 | NA | 100 | Same as Baseline | 0 | NA | 0 | NA | 0 | NA | NA | NA | 7a. NA 7b. NA | NA | 6336 | 0 | 0 | 0 | 32 | 0 | 6304 | NA | 0 | 0 | 0 | 0 | Presently we do not own collocation space. The dark fiber (IRU) with Level-3 allows us to chose between providers in Reno, NV. We have the option of buying bandwidth from Charter Communications, Level-3, At&t and the California Broadband Coalition. The California Broadband Coalition is building a Network Operations Center next to Level-3s' building which will increase the number of providers available to us. | NA | NA | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA
NT10BIX5570106 | 2012 | 93412 | The electronics have not been purchased yet and will increase this amount to get us back on track with the baseline data. | 0 | NA | 0 | NA | 100 Mbps | Same as Baseline | 0 | NA | 0 Mbps | This is the average speed we expect our customers to use. | 0 | NA | NA | NA | 7a. The service level agreements will dictate the the limitations on the bandwidth offered. 7b We will not block or limit any consumer from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | NA | 6336 | 0 | 0 | 3024 | 3312 | 0 | 0 | NA | 0 | 0 | 0 | 0 | Presently we do not own collocation space. The dark fiber (IRU) with Level-3 allows us to chose between providers in Reno, NV. We have the option of buying bandwidth from Charter Communications, Level-3, At&t and the California Broadband Coalition. The California Broadband Coalition is building a Network Operations Center next to Level-3s' building which will increase the number of providers available to us. | NA | Multitasking for the project is essential in order to get a headstart on as many issues as possible. There are always delays caused by the schedules of various parties, weather, and unanticipated circumstances. Proactive and persistent contact with government agencies is essential in keeping tasks moving forward. Having one individual to oversee and understanding all aspects of the project is beneficial for keeping the tasks on schedule. Integration of the tasks by team meetings helps the coordinator have a firm grasp of the tracking and understanding of the reporting requirements. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA
NT10BIX5570106 | 2013 | $99,941 | Baseline was 99,094. There was a slight increase due to site prep construction costs. | 0 | NA | 0 | NA | 100 MBPS | No variance | 100 MBPS | No Variance | 60 MBPS | No Variance | 0 | NA | Average increase is 58.5 mbps. Average speed (using bandwidth testing) is 60 mbps. The maximum current service capability of 100 mbps is shared among 25 CAIs A prior maximum of 1.5 mbps was shared among 21 CAIs. Therefore the average increase is 60 mbps - 1.5 mbps = 58.5 mbps. | Retail services will be 5 - 10 mbps shared service, >= 10 mbps dedicated service and 100 mbps shared service. Attachment has full description and pricing for proposed services. | Bandwidth limitations will be based upon level of service. We will not block retail or commercial customers from accessing any lawful content, service service provider, or application. We will not prevent consumers from attaching any legal device to the network | Two have decline service prior to being activated. The grade school was connected to another provider's fiber under a county wide E Rate program with which we were unable to bid for service. A juvenile treatment facility has declined service at this time, however they indicated that they may be interested in the near future. | 6336 | 3312 | 0 | 3024 | 0 | 0 | 0 | NA | 425 | 225 | 0 | 200 | NA | NA | Interaction with state and federal agencies with similar projects provides potential opportunities for interconnection. In addition, contact with state agencies involved with economic development provides information and contacts with potential business customers. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA
NT10BIX5570106 | 2014 | 99941 | Baseline was 99,094. There was a slight increase due to site prep construction consts. | 0 | NA | 0 | NA | 100 MBPS | No Variance | 100 MBPS | No Variance | 60 MBPS | No Variance | 0 | NA | Average increase is 58.5 mbps. Average speed (using bandwidth testing) is 60 mbps. The maximum current service capability of 100 mbps is shared among 25 CAIs. A prior maximum of 1.5 mbps was shared among 21 CAIs. Therefore the average increase is 60 mbps - 1.5 mbps = 58.5 mbps. | Retail services will be 1) 5-10 mbps shared service, 2) >= 10mbps dedicated service and 3) 100 mbps shared service. Attachment has full description and pricing for proposed services. | Bandwidth limitations will be based upon level of service. We will not block retail or commercial customers from accessing any lawful content, service provider, or application. We will not prevent customers from attaching any legal device to the network. | No one has dropped service during this reporting period. | 6336 | 3312 | 0 | 3024 | 0 | 0 | 0 | NA | 425 | 225 | 0 | 200 | NA | NA | Because of the short reporting period, there hasn't been much time for experiences to provide much insight. However there is one area that we are learning needs to be carefully thought out for sustainability. If the organization operating the network needs to rely on outside vendors for facility and equipment support, it is good to have more than one vendor knowledgeable on each area of the system. Good designs and individuals that understand the operations at even a high level, can be instrumental in assisting vendors with understanding the system for solving problems and extending capabilities. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA
NT10BIX5570107 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Our connections are all anticipated to be at the gigabit or greater data rate. | No network is built at this time so these figures are not yet available. | We have not yet had to incorporate any network policy changes to date but we anticipate that our System Policy will need to change to reflect the non-discrimination provisions of the NTIA grant. We do not block or limit any bandwidth within our customers committed data rates. | None. | 4422 | 264 | 592 | 3566 | 4422 | 592 | 3566 | N/A | 0 | 0 | 0 | 0 | All of our collocation space is either in the carrier facilities of our network partners or in carrier hotel facilities where we rent space by the rack. | None have been made yet. We anticipate at least 5 subcontracts within the next quarter. | Never underestimate the complexity of an environmental assessment. | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | 0 | 0
NT10BIX5570107 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Our connections are all anticipated to be at the gigabit or greater data rate. | None, this is a middle mile project. | 7a No policy changes at this time. 7b No for TAMU | N/A | 4847 | 17 | 16 | 392 | 265 | 772 | 3385 | N/A | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. | We have identified 5 subcontract opportunities at this time. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Provide them with a high level Project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | N/A | N/A
NT10BIX5570107 | 2012 | $48,267.00 | N/A | 0 | N/A | 0 | N/A | 10 Gigabit | N/A | 0 | N/A | 1 Gigabit | N/A | 0 | N/A | All connections anticipated to be at gigabit or greater data rate. | None. This is a middle mile project. | 7a. No policy changes at this time. 7b. No for TAMU | N/A | 4847 | 178 | 16 | 4605 | 4 | 0 | 44 | N/A | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. We are currently in colocation sites in Goldthwaite, Stephenville, Temple, Commerce, Corpus Christi, San Antonio, Cleta, Tulia, Campbell, and Tyler, TX. | We have identified 5 subcontract opportunities at this time.None are SDB. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Early in the process, provide them with a high level Project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | None at this time | None at this time
NT10BIX5570107 | 2013 | $59,267 | Includes: conduit, cables, towers, antennas/wireless transceivers, and the labor used to install this transmission infrastructure Does not include: network access (e.g., core network routers), customer premise equipment (CPE), building/facility construction, test equipment, billing and operational support systems, and/or any additional professional services | 0 | n/a | 0 | n/a | 10 Gigabit | n/a | 0 | n/a | 1 Gigabit | n/a | 0 | n/a | CAIâ€™s identified on this project are receiving new access rather than improved access . In that regard the least connection is anticipated to be a minimum data rate of 1 gigabit therefore there is no sound method for calculating an increase to their broadband speed. 1 gigabit is the minimum anticipated data rate that would be available for the CAIs | None. This is a middle mile project. | 7a. The Trans Texas Video Network manages the network. Bandwidth is determined on a customer by customer basis depending on their needs and the physical limitation of the data network equipment. 7b. No for TAMU | n/a | 4847 | 108 | 0 | 4739 | 0 | 0 | 0 | none at this time | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. We are currently in collocation sites in Goldthwaite, Stephenville, Temple, Commerce, Corpus Christi, San Antonio, Cleta, Tulia, Campbell, Waller, Waco, Atlanta, Dallas, and Tyler, TX. | We have identified two subcontract opportunities at this time. None are SBD. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Early in the process, provide them with a high level project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | none at this time | none at this time
NT10BIX5570108 | 2010 | 0 | No fiber deployment to date. | 0 | NA - Last Mile services are not included within the project. | 0 | NA - Last Mile services are not included within the project. | 0 | No fiber deployment to date. When complete the maximum speed will be 10 Gbps. | 0 | NA - Last Mile services are not included within the project. | 0 | No fiber deployment to date. When complete the speed tiers advertised will be the same as the actual speed provided. | 0 | NA - Last Mile services are not included within the project. | Since construction has yet to begin, there is no increase in broadband speeds to report at this time. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. Customers are required to sign a participation agreement, which is posted on the ICN website at http://www.illinois.net/connect/default.htm. The agreement outlines responsibilities of the ICN and the customer and includes ICN's policies for acceptable use. The participation agreement will be modified to reflect the new service offerings resulting from the IBOP EC project. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None to date. | 168517 | 0 | 0 | 0 | 8519 | 3539 | 156460 | Since construction has yet to begin, there are no services currently being offered. | 0 | 0 | 0 | 0 | Collocation space is not yet established as construction activities have not started. | None to date. | The IBOP EC project is receiving strong support from all parties within the service area. As a current service provider, Central Management Services currently supports a number of customers in the area but is seeing a lot of interest and enthusiasm from potential new customers and stakeholders. We believe this positive response is a result of outreach efforts to share project information and engage the local communities in planning discussions. The project team is reaching out to the community on a local, regional and state level. At the local level, Field Staff are meeting with community anchors and stakeholders within individual towns and counties. At the regional level, Field Staff are working with local Economic Development Councils and University Cooperative Extension resources. At the state level, the project team is working with the state coordinating boards/agencies for education, libraries, museums, health care, emergency management, and public safety. As a result, consistent information regarding the benefits of the project is flowing to communities and stakeholders. The project team also sends a monthly update to all schools, libraries and universities as well as hundreds of other anchor institutions. The updates are posted on the project web site at www.illinois.net/IBOP.htm. The web site includes a link for interested parties to subscribe to future updates. The project team is also working closely with an advisory panel comprised of technical managers from various community anchor institutions throughout the state. This advisory panel is providing direct input into the development of network policies and service offerings. Members of the advisory panel are based on nominations collected annually from the general public and customers of Central Management Services' current broadband services. Nominations are reviewed and approved by a statutorily created policy committee (20 ILCS 3921) which guides Central Management Services on the operations of its broadband network. More information regarding the advisory committee and the policy committee are available at www.illinois.net. At the state level, the Illinois BTOP and BIP projects gathered to share information on their various projects and establish lines of communications. The level of cooperation among the BTOP Infrastructure projects is phenomenal and will result in all projects interconnected. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | Since construction has yet to begin, there are no interconnection, peering and/or transit agreements in place. However, we are in the discovery phase with several potential wholesale customers. | Since construction has yet to begin, there are no interconnection, peering and/or transit agreements in place. However, we are in the discovery phase with several potential wholesale customers.
NT10BIX5570108 | 2011 | 0 | Construction activities started in November. No invoices were paid during this reporting period. | 0 | NA - Last mile services are not included in the project. | 0 | NA - Last mile services are not included in the project. | 0 | Since only a small portion of the network is operational, CMS is not offering services at this time. When complete the maximum speed will be 10 Gbps. | 0 | NA - Last mile services are not included in the project. | 0 | Since only a small portion of the network is operational, CMS is not offering services at this time. When complete the speed tiers advertised will be the same as the actual speed provided. | 0 | NA - Last mile services are not included in the project. | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 1 gigabit. Since only a small portion of the network (80 of 2,000 miles is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 megabits to 50-100 megabits. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. Customers are required to sign a participation agreement, which is posted on the ICN website at http://www.illinois.net/connect/default.htm. The agreement outlines responsibilities of the ICN and the customer and includes ICN's policies for acceptable use. The participation agreement will be modified to reflect the new service offerings resulting from the IBOP EC project. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 168518 | 320 | 0 | 0 | 8199 | 3539 | 156460 | Since only a small portion of the network is operational, no dark fiber has been leased. | 0 | 0 | 0 | 0 | CMS is not using grant funds to purchase or lease collocation capacity. Customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. | None | Our sub recipient, Illinois State University (ISU), has learned that it is imperative to appoint a single point of contact to work with CAIs. In the beginning, ISU had several staff members working with the same CAIs sometimes created confusion. The CAIs prefer working with one person even if it takes longer to respond to inquiries. CMS is using Share Point as the central repository for program and project management. The capabilities inherent to Share Point enhance the collaboration among the team members and streamline record keeping through automation. For example, CMS stores permit documents in Share Point and uses "view capabilities" to sort and analyze the data by construction package, status, and permitting authority. This feature allows team members to quickly sort and access the information in a view that meets their specific need. Another example of how CMS is using Share Point is managing vendor weekly certified payroll. Vendors send their weekly certified payroll documents to a specific email address that automatically files the email and its attachments in the appropriate Share Point folder. These easy to use features in Share Point are saving staff time generating and filing reports. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) No interconnection agreements have been executed. 2) CMS is negotiating three interconnection agreements with other providers. 3) CMS has not denied any requests for interconnection. | 1) One transit agreement has been executed with the Illinois Rural HealthNet. 2) CMS and the sub recipient are in discussions with 11 entities regarding transit services. 3) CMS has not denied any requests for peering or transit services.
NT10BIX5570108 | 2012 | $50,000 | The baseline forecasted costs at $61,674. Through competitive bidding, costs are running lower than anticipated. The average cost per new mile may increase as construction proceeds into more difficult areas (rock, utility congested areas, etc.). | 0 | NA - no last mile component. | 0 | NA - no last mile component. | 10 Gbps | Standard service offerings are 10 Mbps to 10 Gbps. The network can support faster speeds if required. | 0 | NA - no last mile component. | 10 Gbps | CMS provides symmetrical, dedicated broadband services. Customers are guaranteed to receive the subscribed speeds. | 0 | NA - no last mile component. | The leased fiber lit in 2011 positions these CAIs to connect at speeds up to 10 Gbps. The average increase in broadband speeds is 32 Mbps which is a 5- 7 times increase in previous speeds. | Since construction is ongoing, the availability of services is limited. Once fully operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. The acceptable use policy is posted on the website at www.illinois.net. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 167792 | 507 | 0 | 72785 | 3626 | 0 | 90874 | Since the network is under construction, no dark fiber has been leased. | 0 | 0 | 0 | 0 | CMS is not using grant funds to purchase or lease collocation capacity; however, ISU, the sub recipient will. CMS customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. ISU customers can lease collocation space at the BTOP funded facilities. The ISU collocation space is not operational at this point in the project. | Integrated Technology Providers Inc. | Having a single point of contact for potential customers is very helpful for continuity and customer confidence in the organization and process. Start working with railroads immediately in order to obtain permits. The process with the railroads can be lengthy and frustrating. Collect and validate the final as built diagrams for the new fiber and utilize a fiber management system. The fiber management system can assist in tracking fiber assignments for internal use and customer leases as well as generate accurate and detailed mapping information to be used for fiber locates and maintenance. Through the course of construction our vendors have discovered or hit unmarked utilities. We believe the problem is a result of poor network maps for the older infrastructure. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) No new interconnection agreements were executed during this reporting. 2) CMS is not negotiating any new agreements. 3) CMS has not denied any requests for interconnection. CMS currently interconnects with more than a dozen service providers. These service providers are providing last mile connections for CAIs connected to the State's educational network. | 1) One transit agreement has been executed with the Illinois Rural HealthNet. 2) CMS is in contract negotiations with a wholesale provider and in discussions with an additional 9 providers. 3) CMS has not denied any requests for peering or transit services.
NT10BIX5570108 | 2013 | $53,345 | The baseline forecasted costs at $61,674. Through competitive bidding, costs were lower than anticipated. | 0 | NA - no last mile component. | 0 | NA - no last mile component. | 10 Gbps | Standard service offerings are 10 Mbps to 10 Gbps. The network can support faster speeds if required. | 0 | NA - no last mile component. | 10 Gbps | CMS provides symmetrical, dedicated broadband services. Customers are guaranteed to receive the subscribed speeds. | 0 | NA - no last mile component. | The new fiber infrastructure positions these CAIs to connect at speeds up to 10 Gbps. Prior to completion of this project, most K-12 schools were connected at speeds of 1.5 to 20 Mbps and higher education sites were connected at speeds of 10 to 50 Mbps. As a result of this project, K-12 schools are now connected at speeds of 10 Mbps to 1 Gbps with more than half connected at speeds at 100+ Mbps which is an increase of more than 80 Mbps. The majority of higher education sites are now connected at speeds of 100+ Mbps which is an increase of more than 50 Mbps. | CMS provides wholesale services only. The sub recipient, Illinois State University, does provide the following retail services: 1) ISP Internet Services, 2) Subscriber Internet Services, 3) Intranet Services, and 4) Dark Fiber Leases. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. The acceptable use policy is posted on the website at www.illinois.net. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 149722 | 6141 | 2862 | 140719 | 0 | 0 | 0 | [REDACTED] | 1520 | 1166 | 0 | 354 | CMS is not using grant funds to purchase or lease collocation capacity; however, the sub recipient, Illinois State University, has used grant funds to lease collocation space. CMS customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. ISU customers can lease collocation space at the BTOP funded facilities. | Integrated Technology Providers Inc. | Having a single point of contact for potential customers is very helpful for continuity and customer confidence in the organization and process. Start working with railroads immediately in order to obtain permits. The process with the railroads can be lengthy and frustrating. Collect and validate the final as built diagrams for the new fiber and utilize a fiber management system. The fiber management system can assist in tracking fiber assignments for internal use and customer leases as well as generate accurate and detailed mapping information to be used for fiber locates and maintenance. Through the course of construction our vendors have discovered or hit unmarked utilities. We believe the problem is a result of poor network maps for the older infrastructure. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) CMS currently interconnects with 20 service providers of which 3 were added in 2013. These service providers are providing last mile connections for CAIs connected to the State's educational network. 2) CMS is not negotiating any new agreements. 3) CMS | 1) CMS has 17 peering agreements of which 5 were added in 2013. CMS did not complete any new transit agreements in 2013. 2) CMS is negotiating 1 transit agreement. 3) CMS has not denied any requests for peering or transit services.
NT10BIX5570109 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A
NT10BIX5570109 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | We have not yet begun to provide service. | N/A | N/A | 17880 | 0 | 0 | 0 | 0 | 8940 | 8940 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A
NT10BIX5570109 | 2012 | 45386 | N/A | 0 | N/A | 0 | N/A | 1GB | N/A | 0 | N/A | 10MB | N/A | 0 | N/A | N/A | We have not yet begun to provide service. | N/A | N/A | 17880 | 0 | 0 | 0 | 0 | 8940 | 8940 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A
NT10BIX5570109 | 2013 | 45386 | N/A | 0 | N/A | 0 | N/A | 1 GB | N/A | 0 | N/A | 10 MB | N/A | 0 | N/A | N/A | We are not providing retail service | N/A | N/A | 17880 | 8940 | 8940 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A
NT10BIX5570111 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | One (1) interconnection agreement entered into during the annual reporting period. Currently negotiating one interconnection agreement. We have not denied any requests for interconnection during the annual reporting period. | N/A
NT10BIX5570111 | 2011 | 0 | Since construction has not yet started on this project, calculations are not applicable. | 0 | Construction has not yet started. | 0 | Construction has not yet started. | 0 | Broadband speeds have not been advertised and will be available once construction has commenced and services turned up. | 0 | Broadband speeds have not been advertised and will be available once construction has commenced and services turned up. | 0 | Construction has not yet started so speeds are not available. | 0 | Construction has not yet started so speeds are not available. | There has not been any increase in Broadband speed since construction of the Network has not yet begun. | None at this time of the project life cycle. | N/A No | N/A | 47705 | 0 | 0 | 0 | 47705 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1). 7 agreements entered into in 2011. Capacity Provisioning, Columbia County, Olympus Net, Spectrum, and Touchet Valley, and WCI all were signed with Wholesale Agreements this past year. 2). 1 Interconnection agreement being negotiated 3). No, none denied. | N/A
NT10BIX5570111 | 2012 | $134,506.89 | This cost was calculated using the Outside Plant expenditures and dividing by the actual miles built as of the end of 2012. With the most expensive portion of the Network Build being done in 2012, this number is not representative of the overall project when the project has been completed. | N/A | N/A | N/A | N/A | 100 Gig | With the improvement in technology since the application was submitted, Northwest Open Access Network has been able to advertise and provide 100 Gig service for those that are interested in securing. | N/A | N/A | 100 Meg | No Variance. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past annual reporting period. | NoaNet is a wholesale provider and not authorized to provide retail services. The services provided are to Retail Service Providers with array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | N/A No | N/A | 51648 | 5 | 0 | 14683 | 36960 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) Netflix CDN 2.) N/A 3.)N/A
NT10BIX5570111 | 2013 | 79,600 | This cost was calculated using the Outside Plant expenditures and dividing by the actual miles built as of the end of 2013. This number is down considerably from the 2012 report as the less expensive portion of the build was done in 2013. Baseline was $74,299, we found additional rock in areas making the build slightly more expensive. | N/A | N/A | N/A | N/A | 100 Gig | With the improvement in technology since the application was submitted, Northwest Open Access Network has been able to advertise and provide 100 Gig service for those that are interested in securing. | N/A | N/A | 100 Meg | No Variance. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past annual reporting period. | NoaNet is a wholesale provider and not authorized to provide retail services. The services provided are to Retail Service Providers with an array of services including Broadband Internet, Wave/Lamda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | N/A No | N/A | 45216 | 45216 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me points. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1.) None 2.) N/A 3.) N/A | 1.) One- Fatbeam 2.) N/A 3.) N/A
NT10BIX5570112 | 2010 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 7a: All NebraskaLink customers have full access/ bandwidth to their purchased bandwidth / no traffic prioritization. 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any legal device to the network. | N/A | 50976 | 809 | 0 | 0 | 5000 | 2500 | 42667 | N/A | 0 | 0 | 0 | 0 | Currently we are leasing collocation space from the following: Nebraska Central Telephone Company - 887 H St, Burwell, NE Four-U-Technology - 104 W Centre St, Hartington, NE Consolidated Long Distance - 234 S. Price St, Merna, NE 68856 | N/A | Communication is the best practice we can share thus far in our project - communication with your Grants Officer, Environmental Officers,etc. Don't be afraid to ask questions of your team - they are there to assist you and to work with you on all aspects of your award. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 3 interconnection agreements have been signed 2) Currently working on 7 interconnection agreements 3) No requests for interconnection have been denied. | N/A
NT10BIX5570112 | 2011 | 13485.60 | NebraskaLink is on target for the average cost per mile as compared to our baseline plan. | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 115 mbps | NebraskaLink is on target with our baseline plan. | N/A | N/A | N/A | N/A | 7a: All NebraskaLink customers have full access/bandwidth to their purchased bandwidth / no traffic prioritization. 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any legal device to the network. | N/A | 35086 | 15865 | 1415 | 0 | 17695 | 111 | 0 | N/A | 0 | 0 | 0 | 0 | Currently NebraskaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone: Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial Northeast Nebraska Telephone Company: Clearwater, Bartlett | N/A | Communications with our Federal Program Officer and team is the best practice we can share. Secondly would be to take advantage of any and all advice and communications - via email, webinar training, drop in calls, etc - many times others have the same questions we have and it is truly advantageous to attend this meetings to increase knowledge of expectations and to see how others are meeting their objectives and any obstacles they may be encountering. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 33 interconnection agreements have been signed 2) NebraskaLink is currently working on 4 new interconnection agreements 3) No requests for interconnection have been denied. | N/A
NT10BIX5570112 | 2012 | 13449.50 | NebraskaLink is on target for this milestone | N/A | N/A | N/A | N/A | 10 Gbps | NebraskaLink is on target for this milestone | N/A | N/A | 150 Mbps | NebraskaLink is on track with this milestone | N/A | N/A | Prior to services offered to the CAI's by NebraskaLink, the CAI's were utilizing asymetrical DSL services provided by their carriers. NebraskaLink is now offering Ethernet services to the CAI's which gives them the ability for increased bandwidth to each CAI. The average speed provided is 89 Mbps. The average was arrived by taking the speed of each CAI taking our services and dividing by number of CAI's taking our service. We currently offer to our CAI's services ranging from 5 Mbps to 1 Gig of service. | Currently NebraskaLink offers full symmetrical Direct Internet Access and Layer 2 Ethernet Service to our retail customers. Pricing attached. | 7a: All NebraskaLink customers have full access to their purchased bandwidth / no traffic prioritization 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | N/A | 35086 | 31320 | 1415 | 0 | 2240 | 111 | 0 | N/A | 0 | 0 | 0 | 0 | Currently NebrakaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone : Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna, Paxton Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial, Crookston, Chadron, Trenton, Wood Lake Northeast Nebraska Telephone Company: Clearwater, Bartlett, Stuart Eastern Nebraska Telephone Company: Osmond Hartelco: Hartington | N/A | Communications with our Grants team is the best practice/ lesson that we can share. Take advantage of any and all training, webinars, calls with other recipients. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 52 interconnection agreements have been signed 2) NebraskaLink is currently working on 3 new interconnection agreements 30 No requests have been denied. | N/A
NT10BIX5570112 | 2013 | 24429 | NebraskaLink was over target on this milestone. Cost includes construction, materials, engineering and inspections costs. | N/A | N/A | N/A | N/A | 10 Gbps | NebraskaLink is on target for this milestone | N/A | N/A | 150 Mbps | NebraskaLink is on target with this milestone | N/A | N/A | Prior to services offered to the CAI's by NebraskaLink, the CAI's were utilizing asymetrical DSL services provided by their carriers. NebraskaLink is now offering Ethernet services to the CAI's which gives them the ability for increased bandwidth to each CAI. The average speed provided is 89 Mbps. The average was arrived by taking the speed of each CAI taking our services and dividing by number of CAI's taking our service. We currently offer to our CAI's services ranging from 5 Mbps to 1 Gig of service. | Currently NebraskaLink offers full symmetrical Direct Internet Access and Layer 2 Ethernet Service to our retail customers. Pricing attached. | 7a: All NebraskaLink customers have full access to their purchaesed bandwidth/ no traffic prioritization 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or applicaton or prevented any consumers from attaching any legal device to the network. | N/A | 48266 | 43050 | 1415 | 0 | 0 | 0 | 0 | No dark fiber | 0 | 0 | 0 | 0 | Currently NebrakaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone : Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna, Paxton Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial, Crookston, Chadron, Trenton, Wood Lake Northeast Nebraska Telephone Company: Clearwater, Bartlett, Stuart Eastern Nebraska Telephone Company: Osmond Hartelco: Hartington | N/A | Communications with our Grants team is the best practice we can share. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 24 interconnection agreements have been signed 2) NebraskaLink is not currently working on any new interconnection agreements 3) No requests have been denied | N/A
NT10BIX5570113 | 2010 | $62,277 | No Variance. | 0 | N/A | 0 | N/A | 1000 Meg | No variance. | 0 | N/A | 100 Meg | No variance. | 0 | N/A | No Community Anchor Institutions have yet been connected. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 64824 | 0 | 0 | 0 | 12060 | 28764 | 24000 | N/A | 0 | 0 | 0 | 0 | The Oklahoma Community Anchor Network (OCAN) project will build 15 Communication/Collocation facilities along the OCAN route. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A
NT10BIX5570113 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Community Anchor Institutions (CAI) have yet been connected. The numbers listed above in number 4 include the 32 CAI's that will be directly connected to the Oklahoma Community Anchor Network (OCAN) plus 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. Each of the 32 directly connected CAI's will have a 1 Gig connection, when connected. The current average broadband speed at the CAI's is 44 Meg, thus the increase in broadband speed available will be 956 Meg. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 105864 | 0 | 0 | 0 | 19696 | 46974 | 39194 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project is constructing sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility will have 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A
NT10BIX5570113 | 2012 | $60,713 | Variance from Baseline Plan of $62,277. Actual average cost per mile on project has come in $2,064 lower than the Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | The average increase in broadband speed at the Community Anchor Institutions (CAI's) is 956 Meg. The current average speed is 44 Meg and the CAI's are being provided with 1000 Meg connections. The numbers listed in question 4 include the 32 CAI's directly connected by the OCAN fiber. There are 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 91382 | 2324 | 0 | 76002 | 0 | 0 | 13056 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project has constructed sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility has 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A
NT10BIX5570113 | 2013 | $50,187.09 | Variance from Baseline of $62,277. Average cost per new middle mile calculation: 44,845,316.28 (New Construction & IRU's) + 5,019,339.73 (Fiber Cost) + 4,081,250.51 (Communication Huts) + 49,435 (Permits Cost) + 2,264,390.65 (Engineering Cost) = $56,259,732.17; 827mi New Built + 294mi IRU's = 1,121 new middle miles; $56,259,732.17 / 1,121 = $50,187.09. | 0 | N/A | 0 | N/A | 1Gb | No variance from baseline. | 0 | N/A | 100 Mb | No variance from baseline. Other than the 31 CAI's directly connected to OCAN which are provided 1Gb connections, all other CAI's receive 100Mb connections. | 0 | N/A | The average increase in broadband speed at the Community Anchor Institutions (CAI's) is 956 Meg. The current average speed is 44 Meg and the CAI's are being provided with 1000 Meg connections. The numbers listed in question 4 include the 31 CAI's directly connected by the OCAN fiber. Connection with the remaining CAI's, Choctaw Hospital and Southeastern OSU, is pending IRU negotiation. There are 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. | Point to Point and Multi-point Ethernet Services Lit Services Dark Fiber IRU Services (Please see attachment "2014_APR_ITEM 6 - OCAN Services") | 7a. Per NTIA regulations of the BTOP grant, all inquiries/offers by providers for services must be entertained but not to the extent that any other provider invests in a controlling percentage of the OCAN route. 7b. There are no plans to limit access to the network. | N/A | 93706 | 17870 | 23620 | 52216 | 0 | 0 | 0 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project has constructed sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility has 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A
NT10BIX5570113 | 2014 | $50,187.09 | Variance from Baseline of $62,277. Average cost per new middle mile calculation: 44,845,316.28 (New Construction & IRU's) + 5,019,339.73 (Fiber Cost) + 4,081,250.51 (Communication Huts) + 49,435 (Permits Cost) + 2,264,390.65 (Engineering Cost) = $56,259,732.17; 827mi New Built + 294mi IRU's = 1,121 new middle miles; $56,259,732.17 / 1,121 = $50,187.09. | 0 | N/A | 0 | N/A | 1Gb | No variance from baseline. | 0 | N/A | 0 | N/A | 0 | N/A | The average increase in broadband speed at the Community Anchor Institutions (CAI's) is 956 Meg. The current average speed is 44 Meg and the CAI's are being provided with 1000 Meg connections. The numbers listed in question 4 include the 31 CAI's directly connected by the OCAN fiber. Connection with the remaining CAI's, Choctaw Hospital and Southeastern OSU, is pending IRU negotiation. There are 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. | Point to Point and Multi-point Ethernet Services Lit Services Dark Fiber IRU Services (Please see attachment "2014_APR_ITEM 6 - OCAN Services") | 7a. Per NTIA regulations of the BTOP grant, all inquiries/offers by providers for services must be entertained but not to the extent that any other provider invests in a controlling percentage of the OCAN route. 7b. There are no plans to limit access to the network. | N/A | 91382 | 2324 | 642 | 76002 | 0 | 0 | 0 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project has constructed sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility has 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A
NT10BIX5570114 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | None Noted | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | a) CAI's can request their bandwidth limited but by default Merit does not limit the users access. b) Merit has not block access to any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 147730 | 0 | 0 | 0 | 39279 | 12177 | 96274 | N/A | 0 | 0 | 0 | 0 | Although collocation space will be built in the future for this project, Merit does not currently own collocation space for this build. Other network providers and CAI's can interconnect to Merit at splice points along the route. | N/A | Merit encourages all BTOP recipients to reach out to communities at all levels and get them involved in the process. Build relationships with all the permitting agencies; we would suggest informal meetings with them on a regular basis. Merit would encourage that inquiries with communities on existing infrastructure as well as talking with others in your industry about existing infrastructure given that the cost is about the same or less and the time savings will get you ahead of your project. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | N/A | N/A
NT10BIX5570114 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 0 | N/A | 0 | N/A | Broadband speeds have not increased since construction and deployment have not been completed. | Pricing plans have not been provided, since construction and deployment have not been completed. | Our project is not yet providing service. | N/A | 153737 | 0 | 0 | 0 | 35713 | 10762 | 107262 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers will have opportunities to connect to the recipient and subrecipient networks at leased facilities along the route, including, but not limited to: telecommunication huts; Central Offices; Community Anchor Institutions; and other leased facilities. No part of the project network was lit and operational during the reporting period; the locations, owners, and interconnection method data will be available in the 2012 reporting year. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | 1. N/A 2. N/A 3. N/A (No requests for interconnection were made.) | 1. N/A 2. N/A 3. N/A (No requests for peering or transit were made.)
NT10BIX5570114 | 2012 | 90988 | This number is higher than the baseline plan primarily because Merit Network, Inc. focused on installing the most difficult and labor-intensive sections of the network before the winter season. The cost per new mile should gradually align with the baseline cost as additional miles are completed, and Merit anticipates no variance at the project culmination. | 0 | N/A | 0 | N/A | 10 Gbps | No variance | 0 | N/A | 10 Mbps | No variance | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 153616 | 108 | 0 | 2844 | 4774 | 0 | 145890 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | N/A | N/A
NT10BIX5570114 | 2013 | 57331 | The cost per mile was significantly above the estimate in the baseline plan, primarily due to unanticipated costs associated with underground construction. Merit's construction crews encountered unforeseen stretches of solid rock in the Upper Peninsula; boring through rock is the mostly costly construction method, and the overall cost per mile increased as a result. | 0 | N/A | 0 | N/A | 10 Mbps | No variance | 0 | N/A | 10 Mbps | No variance | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 153741 | 38390 | 0 | 115170 | 45 | 0 | 135 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | There were no interconnection agreements entered into during the annual reporting period, however, four agreements were under negotiation. No requests were denied. | There were no peering or transit agreements entered into during the annual reporting period, however one agreement was under negotiation. No requests were denied.
NT10BIX5570114 | 2014 | $42,722 | The cost per mile was significantly above the estimate in the baseline plan, primarily due to unanticipated costs associated with underground construction. Merit's construction crews encountered unforeseen stretches of solid rock in the Upper Peninsula; boring through rock is the most costly construction method, and, as a result, the overall cost per mile increased. | 0 | N/A | 0 | N/A | 10 Mbps | No variance | 0 | N/A | 10 Mbps | No variance | 0 | N/A | The averaged increase in 10 Gbps. This was calculated by taking the average of the average speed connections to the community anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 155731 | 39234 | 0 | 116497 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and sub-recipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office vis the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and condition, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, having agreements in place with sub-recipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for sub-recipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring sub-recipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organization see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 90 | 29 | 6 | 17 | 26 | 5 |  | 22 | 11 | 0 | 206 | There were 5 interconnection agreements entered into during the annual reporting period and 2 agreements under negotiation. No requests were denied. | There was 1 peering and no transit agreements entered into during the annual reporting period and 1 agreement under negotiation. No requests were denied.
NT10BIX5570115 | 2010 | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | na | na | There are no services being provided at this time. Network management policies are currently being developed with partners. | na | 0 | 0 | 0 | 0 | 0 | 0 | 0 | na | 0 | 0 | 0 | 0 | na | na | na | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | na | na
NT10BIX5570115 | 2011 | $65,488 | Network build has just started with initial fiber being installed in late December. Current cost is for very small portion of overall network only (a higher portion of urban and rocky conditions were experienced) and should normalize as more installation takes place in the next year. | 0 | No last mile service areas yet installed. | 0 | No last mile service areas yet installed. | 40 Mb | Only WiMAX connections are available to date and are limited to Community Anchor Institutions. Maximum speed is 40 Mb and typical speed for WiMAX expected to be around 10 Mb. | 0 | No last mile service areas yet installed. | 10 Mb | Only WiMAX connections are available to date and are limited to Community Anchor Institutions. Typical speed for WiMAX is expected to be around 10 Mb. | 0 | No last mile service areas yet installed. | 10 Mb average improvement: The institutions connected to date are all considered "new" with a previous speed of zero. In all cases, the new broadband connections are accomplished via WiMAX with a typically expected speed of 10Mb. With no previous service, this represents an increase of 10Mb for each institution. | No retail services will be provided until network is available in last mile service areas. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by the hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. Network management policies in each community are under development. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | N/A | 67995 | 0 | 0 | 2499 | 11100 | 3400 | 50996 | N/A | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | Order fiber optic cable immediately; lead times run from 2 months to 12 months. If installation is intended to be direct-bury method, consider installing conduit first, then returning later to install the fiber when the order arrives. Document all assumptions, calculation methods, and explanations for any reportable information - as much for your own future reference as to satisfy audit requirements. Consider hiring outside project management help. Where some community partners were having a hard time making progress, bringing in a dedicated person to focus on the project immediately resulted in forward progress. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. Negotiations are currently underway with two providers. 3. No interconnection agreements have been denied. | No activity has occurred regarding peering and transit agreements this year.
NT10BIX5570115 | 2012 | 58,711 | Average cost per new mile is slightly higher than $56,331 / mile Year 2 milestone target cost due to higher portion of rocky conditions than originally planned. | 0 | No last mile service areas yet installed. | 0 | No last mile service areas yet installed. | 40Gb | Hospitals are making use of 40Gb link on newly installed BCCB network. | 0 | No last mile service areas yet installed. | 2.65Gb | Most new connections are 1Gb. There are three connections running at 10Gb and one at 40Gb. Simple average calculated across all Community Anchor Institutions currently receiving service. | 0 | No last mile service areas yet installed. | Average increase in broadband speed for three upgraded connections is 953Mb - institutions previously had 20-100Mb connections, increased to 1Gb each. The net increase was calculated for each site and averaged together. Average increase in broadband speed for 37 new connections is 2.78Gb - institutions considered "new" (institutions never before served by sub recipient) are treated as having a previous speed of zero. The new connections are typically 1Gb, with three at 10Gb and one at 40Gb. The speed for each connection was averaged together. Overall average increase in broadband speed is 2.64Gb when net increase from all sites above is averaged together. | No retail services will be provided until network is available in last mile service areas. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by the hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. Network management policies in each community are under development. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | NA | 67995 | 571 | 0 | 36170 | 0 | 0 | 31254 | NA | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | It is advisable to include environmental experts early and throughout all phases of project construction. If these experts are not available in-house, find qualified consultants to ensure compliance with all requirements. There are more agencies involved than might initially seem likely and the requirements are often more stringent for federally-funded projects than might otherwise be the case in privately-funded projects. It may take multiple experts to cover all requirements, such as those experienced in archeological, historical, wetlands and waterways, and threatened and endangered species. Another best practice and lesson learned is the value of our key partnerships. Our project was created through collaboration with many entities that had similar missions and clearly shared the goals of the endeavor. The partnership built off the strengths of each individual organization, bringing together the technical, construction experience and community engagement skill sets needed for completion. Given the scope and complexities inherent in this project, the partnership has proven to be invaluable. Our partners have been engaged, informed and remained steadfast in making the numerous adjustments required to complete the project successfully. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. Negotiations are currently underway with two providers. 3. No interconnection agreements were denied this year. | No activity has occurred regarding peering and transit agreements this year.
NT10BIX5570115 | 2013 | 50,220 | Average cost in Baseline Plan was 52,916. | 142 | Average cost in Baseline Plan was 167. | 31,232 | Average cost in Baseline Plan was 941. The Baseline Plan assumed 331 residential and 220 business subscribers over a two year growth period. However, actual services were limited to 14 residential subscribers since services did not become available until the last quarter of the project. | 40Gb | Baseline Plan was 10Gb. Actual connections for Community Anchor Institutions included one subscriber at 40Gb, 2 subscribers at 20Gb and 12 subscribers at 10Gb. New technology and demands exceeded expectations set three years prior. | 20Mb | Baseline Plan was 10,000 Mb. Of the 14 actual subscribers connected, eight of them are at 20 Mb. The variance is due to a new understanding of this category since initial application: the baseline value falsely included wholesale backbone circuit sizes. Those wholesale links are excluded in this calculation, leaving just business and residences in last mile service areas. | 1874Mb | The baseline plan was 513 Mb. Most new connections are 1Gb. The speeds range from 10 Mb to 40Gb. We calculated the average of all 172 Community Anchor Institutions currently receiving services. The variance is due to more users with high speed connections (10Gb, 20Gb and 40Gb) than initially anticipated. | 17Mb | Of the 14 actual subscribers connected, eight of them are at 20 Mb, three are at 15Mb and three are at 10Mb.The variance from baseline is due to a new understanding of this category since initial application: the baseline value incorrectly included wholesale backbone circuit sizes. Those wholesale links are excluded here, leaving just business and residences in last mile service areas. | The average broadband speed for 20 UPGRADED connections increased from 734Mb to 4,300 Mb - institutions previously had 20-2,000Mb connections that increased to 1,000 - 20,000Mb. The increase was calculated for each individual site and then averaged together. The average broadband speed for 152 NEW connections increased from 0 speed to 1.17Gb - institutions considered "new" are institutions never before served by sub recipient. The new connections are typically 1 or 2Gb, with five at 10Gb and one at 40Gb. The increase was calculated for each site and averaged together. | Our last mile service provider is offering High-Speed Internet access delivered via cable modem and fiber architecture to residential customers with speed range from 10-20Mb and price range of $36.95 - $56.95 per month. Business customers offerings include high -Speed Cable Modems with a low speed of 10Mb at $89.95 per month to highest Point-to-Point speed of 1,000 Mb for $2,450 per month. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | NA | 54792 | 11002 | 0 | 43790 | 0 | 0 | 0 | As sub recipient, Packerland Broadband has access to dark fiber and will provide wholesale services to third party providers. Currently they are leasing 409 miles of fiber to one provider and 331 miles to another provider. | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | It is advisable to include environmental experts early and throughout all phases of project construction. If these experts are not available in-house, find qualified consultants to ensure compliance with all requirements. There are more agencies involved than might initially seem likely and the requirements are often more stringent for federally-funded projects than might otherwise be the case in privately-funded projects. It may take multiple experts to cover all requirements, such as those experienced in archeological, historical, wetlands and waterways, and threatened and endangered species. Another best practice and lesson learned is the value of our key partnerships. Our project was created through collaboration with many entities that had similar missions and clearly shared the goals of the endeavor. The partnership built off the strengths of each individual organization, bringing together the technical, construction experience and community engagement skill sets needed for completion. Given the scope and complexities inherent in this project, the partnership has proven to be invaluable. Our partners have been engaged, informed and remained steadfast in making the numerous adjustments required to complete the project successfully. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. No negotiations are currently underway. 3. No interconnection agreements were denied this year. | No activity has occurred regarding peering and transit agreements this year.
NT10BIX5570116 | 2010 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | 0 | N/A | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | During the reporting period, no community anchor institutions were connected or passed by this project. The project is still completing its Environmental Assessment. | During the reporting period, no retail services were provided. The project is still completing its Environmental Assessment. | During the reporting period, no network management policies were in place, as the Environmental Assessment is still in progress. No consumers were limited or blocked access to any lawful content, service, service provider or application, or prevented from attaching any legal devise to the network. This publicly owned network will be governed by a board composed of official representatives of five Pueblos, three Counties, one City and one inter-governmental organization, to whom the grant was awarded. This board is in formation. No services are being provided because the project is still completing its Environmental Assessment. These issues will be addressed upon formation of the board and in accordance with federal regulations. | N/A. No services have been provided to date. The project is still completing its Environmental Assessment. | 16217 | 0 | 0 | 0 | 16217 | 0 | 0 | No dark fiber services are yet being provided. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | Once the Environmental Assessment is complete and network implementation begins, the project will own its collocation space and offer interconnect points with other network providers and customers. The project can also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at a splice point within a manhole location, or by building REDI Net owned infrastructure into the interconnect providers' facilities and collocating REDI Net equipment there. | No subcontracts have yet been awarded to such entities. The project has two contracts in place, one for the Environmental Assessment and one for Engineering and Project Management. | This project includes five federal or state permitting agencies and five Indian tribes, in addition to the three counties and one city that make up the rest of the consortium. NTIA BTOP staff provided valuable assistance in working with the other federal partners, but it would have been a great advantage to have had a programmatic agreement at the federal level to insure all local and regional staff had the authority to accept the NTIA Environmental Assessment format and the direction to do so, with the understanding that all individual agency concerns would be addressed in the EA. That said, the selection of a highly qualified EA firm with strong local working relationships with these other federal partners helped to expedite the EA process. In addition, the selection of an engineering and management team with local knowledge was essential. Getting things done fast requires trust among disparate partners, especially in such an unusual partnership.. It also means there is a practical limitation on how much time one can spend building relationships and educating team members about the specific and often unique needs of some of the parties involved. Finally, when dealing with so many jurisdictions, it is essential to investigate fully the status of all easement agreements between the infrastructure owners and land owners. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | There were no interconnection agreements entered into during this reporting period, no agreements are under negotiation and no denials have been made for interconnection. The project is still completing its Environmental Assessment. | There were no peering and/or transit agreements entered into during this reporting period, no agreements are under negotiation and no denials have been made. The project is still completing its Environmental Assessment.
NT10BIX5570116 | 2011 | $89964.88 | Cost per mile is higher than baseline because the majority of construction completed to date is underground construction, which has a higher per mile cost. As more aerial segments are built out, the cost per mile will decrease. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 16217 | 0 | 0 | 0 | 16217 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Once the construction is complete and network implementation begins, the project will own its collocation space and offer interconnect points with other network providers and customers. The project can also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at a splice point within a manhole location, or by building REDI Net owned infrastructure into the interconnect providers' facilities and collocating REDI Net equipment there. | N/A | Verify all the route easements well in advance along with early coordination with the easement owners. Also ensure that all desired network and community anchor locations are identified and included in the Environmental Assessment. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | N/A | N/A
NT10BIX5570116 | 2012 | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | 0 | N/A. | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | On average, we find that CAIs that are currently utilizing a DSL or cable modem style service are moving to a fiber service on REDI Net below 10 Mbps. However, the performance of REDI Net fiber-based services is typically far superior to that of older DSL/cable modem services, even though the "advertised" speeds might be similar numbers. So, there may not be an increase when comparing the numbers of the advertised speeds, but there are significant performance improvements on REDI Net. CAI's that are on private line T-1 type services from the incumbent telephone companies are typically moving to 10 Mbps and 20 Mbps services from REDI Net. We also find that CAIs on higher tiers of service, such as 50 Mbps and 100 Mbps, are doubling their capacity over the current incumbent services, indicating a market gap that REDI Net has been able to address. | REDI Net provides wholesale services to last-mile providers and to qualifying CAIs. REDI Net does not provide retail consumer services. | REDI Net's Board of Directors has enacted a comprehensive Network Policy manual, addressing both CAI network services and wholesale services to last-mile providers. The service policies contain provisions for establishing the bandwidth rate pursuant to the tier of service being subscribed to. REDI Net does not prioritize traffic based on source/destination addressing nor application type. REDI Net forwards data packets at the speed provisioned under the service tier. REDI Net has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. REDI Net's network management policies have also adopted Open Access, Nondiscrimination and Interconnection provisions, consistent the the terms provided NTIA BTOP. | N/A. REDI Net has not experienced any churn. | 13858 | 13858 | 0 | 0 | 16401 | 0 | 0 | N/A. REDI Net does not currently offer wholesale access to dark fiber. | 484 | 436 | 0 | 48 | REDI Net Point-of-Presence (POP) facilities contain collocation space and offers interconnect points with other network providers and customers. REDI Net also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at splice point within a manhole location, or by building our own infrastructure into the interconnect providers facilities and collocating our equipment there. REDI Net also considers establishing "meet-me-points" with last-mile providers at outside plant locations, such as vaults, cabinets, and splice cases. | n/a | Establish best practices for asset management early on to ensure development of operational and financial infrastructure is addressed adequately. In turn, a practical business model can be created and sustained. Given the complexity and multi-layered partnerships REDI Net has, critical attention is necessary towards provision and update of information to all stakeholders on regular basis. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | REDI Net signed one interconnect agreement, for providing REDI Net with upstream Internet bandwidth. REDI Net was under negotiation with 5 downstream last-mile providers, for providing them with wholesale Internet and point-to-point Ethernet transport. No requests were denied for interconnection. | There were no peering and/or transit agreements entered into during this reporting period, no agreements were under negotiation, and no denials were made.
NT10BIX5570116 | 2013 | $56,393.67 | 136 new route miles built at a direct capital cost of $7,669,539.66, for the installation of the passive elements of the middle-mile transmission infrastructure. The 136 new route miles are comprised of 108 new linear fiber route miles (not actual fiber miles) and 28 new route miles of microwave transmission. | 0 | N/A | 0 | N/A | 100Mbps | 100Mbps is the maximum advertised speed pursuant to a standardized rate schedule. However, speeds up to 10Gbps are quoted on a case-by-case basis, depending on available infrastructure resources. | 0 | N/A | 37Mbps | 37Mbps is the average speed provided, based on actual service subscriptions. | 0 | N/A | On average, we find that CAIs that are currently utilizing a DSL or cable modem style service are moving to a fiber service on REDI Net below 10 Mbps. However, the performance of REDI Net fiber-based services is typically far superior to that of older DSL/cable modem services, even though the "advertised" speeds might be similar numbers. So, there may not be an increase when comparing the numbers of the advertised speeds, but there are significant performance improvements on REDI Net. CAI's that are on private line T-1 type services from the incumbent telephone companies are typically moving to 10 Mbps and 20 Mbps services from REDI Net. We also find that CAIs on higher tiers of service, such as 50 Mbps and 100 Mbps, are doubling to quadrupling their capacity over the current incumbent services, indicating a market gap that REDI Net has been able to address. Based on the before/after speeds for the CAIs connected under the trial/provisional service, the average increase was ~25 Mbps. | REDI Net provides wholesale services to Last-Mile Providers and to qualifying CAIs. REDI Net does not provide retail consumer services. REDI Net's CAI and Last-Mile Provider pricing plan is as follows: 1 Mbps, Ethernet & Internet Bundle, $80.00 MRC; 1 Mbps, Ethernet Only, $60.00 MRC 3 Mbps, Ethernet & Internet Bundle, $210.00 MRC; 3 Mbps, Ethernet Only, $157.50 MRC 5 Mbps, Ethernet & Internet Bundle, $300.00 MRC; 5 Mbps, Ethernet Only, $225.00 MRC 10 Mbps, Ethernet & Internet Bundle, $500.00 MRC; 5 Mbps, Ethernet Only, $375.00 MRC 15 Mbps, Ethernet & Internet Bundle, $675.00 MRC; 15 Mbps, Ethernet Only, $506.25 MRC 20 Mbps, Ethernet & Internet Bundle, $800.00 MRC; 20 Mbps, Ethernet Only, $600.00 MRC 35 Mbps, Ethernet & Internet Bundle, $1,050.00 MRC; 35 Mbps, Ethernet Only, $787.50 MRC 50 Mbps, Ethernet & Internet Bundle, $1,200.00 MRC; 50 Mbps, Ethernet Only, $900.00 MRC 75 Mbps, Ethernet & Internet Bundle, $1,575.00 MRC; 75 Mbps, Ethernet Only, $1,181.25 MRC 100 Mbps, Ethernet & Internet Bundle, $1,800.00 MRC; 100 Mbps, Ethernet Only, $1,350.00 MRC 1 Gbps, Ethernet & Internet Bundle, custom quote; 1 Gbps, Ethernet Only, custom quote Services above 100 Mbps are quoted on a case-by-case basis, pending engineering analysis, network resource availability, and subcommittee review. For last-mile service providers, REDI Net also offers co-location services, on a similar custom quote process. | REDI Net's Board of Directors has enacted a comprehensive Network Policy manual, addressing both CAI network services and wholesale services to last-mile providers. The service policies contain provisions for establishing the bandwidth rate pursuant to the tier of service being subscribed to. REDI Net does not prioritize traffic based on source/destination addressing nor application type. REDI Net forwards data packets at the speed provisioned under the service tier. REDI Net has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. REDI Net's network management policies have also adopted Open Access, Nondiscrimination and Interconnection provisions, consistent the the terms provided NTIA BTOP. | N/A. REDI Net has not experienced any churn. | 16620 | 16620 | 0 | 0 | 0 | 0 | 0 | N/A. REDI Net does not currently offer wholesale access to dark fiber. | 242 | 224 | 0 | 18 | REDI Net installed two new Point-of-Presence (POP) facilities that contain collocation space. The Espanola POP is a 242 sq. ft. facility, with 224 sq. ft. being used by REDI Net and 18 sq. ft. of collocation space available (qty. 3 2'x3' cabinets). The Espanola POP serves as a POI, by establishing physical connection through either colocation at the POP, or at a midspan meet point, depending on service provider preferences. While the Santa Fe POP facility construction is complete, it is not currently capable of establishing interconnects with REDI Net until a 3rd party fiber build is finished to the POP, post-BTOP. Therefore, the square footage of the SF POP and available colocation space is not reported above in question 11. However, once the 3rd party fiber build is completed post-BTOP, the 242 sq. ft. facility will have 230 sq. ft. used by REDI Net and 12 sq. ft. of collocation space available (qty. 2 2'x3' cabinets).The third REDI Net POP is in Los Alamos, NM. This is a shared facility which is not REDI Net property, nor was it funded through the REDI Net grant. The facility is owned by Los Alamos County government. REDI Net's space in the shared communications room is limited and does not enable colocation. However, interconnections could be established with REDI Net if the 3rd party were able to create their own presence in the shared communications room, by gaining approval from the facility owner. Midspan meet points would be another interconnect option for the Los Alamos POP. The Espanola POP and Los Alamos POP are a completed REDI Net community pair, as reported in the final APR Addendum (spreadsheet). | not applicable | REDI Net as a joint public network requires continuing collaboration amongst the local and tribal governments. Towards this end, much of the design, build and development of the infrastructure require consensus on achieving mutual and common benefits and impact for a large geographic region with diverse cultural and environmental fabric. Active and ongoing engagement with public and private stakeholders were critical and key to completing the middle mile open access network to the extend that it functions and operates in a robust high performance manner. This parallels the innovations for better asset management practices that attempts to align with the changing needs of the respective communities in Northern New Mexico. As a result, opportunities to expand beyond the built coverage area in collaboration with other public and private entities have actualized. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | REDI Net signed SLAs with 3 downstream last-mile providers, Plateau Telecommunications, Los Alamos Network, and Cyber Mesa, for providing them with wholesale Internet and point-to-point Ethernet transport. No interconnection requests were denied for interconnection. | REDI Net has signed one IP transit agreement, with Plateau Telecommunications, for providing REDI Net with upstream Internet bandwidth. There were no peering and/or transit agreements entered into during this reporting period, no agreements were under negotiation, and no denials were made.
NT10BIX5570117 | 2010 | 0 | na | na | na | na | na | na | na | na | na | na | na | na | na | NA Deployment has not yet started. | NA Retail services are not provided in this project. | Not completed during this reporting period. | NA Deployment has not yet started. | 69288 | 0 | 0 | 0 | 26500 | 28930 | 13858 | NA | 0 | 0 | 0 | 0 | No co-location space is currently active in this project. | NA | NA | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | na | na
NT10BIX5570117 | 2011 | 36,237 | N/A | 0 | N/A | 0 | N/A | 10 GB | N/A | 1GB | N/A | 10mb | N/A | 0 | N/A | Most anchors will receive 1 GB connection. Currently most do not have a connection. | N/A | N/A | N/A | 2304 | 0 | 0 | 2304 | 0 | 0 | 0 | N/A | 1350 | 0 | 0 | 1350 | Oconee FOCUS will have collocation space available in future. At this moment, the team is in process of setting up the NOCs. | GeoVision, Technology Solutions, JET, and Network Controls | - Crossing rail roads at public or SC DOT right of way areas. Private crossings are expensive. - Constant communication between engineering, construction, blowing, and splicing crews is critical. - Continue to work with fiber manufacture on lead times. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | N/A | N/A
NT10BIX5570117 | 2012 | 36237 | na | 0 | na | 0 | na | 10GB | na | 1GB | na | 10mb | na | 0 | na | Most anchors will receive 1GB connection. Currently most do not have a connection. | na | na | na | 2304 | 0 | 0 | 2304 | 0 | 0 | 0 | County has entered into a dark fiber agreement with DukeNet for 143 fiber miles. | 1350 | 0 | 0 | 1350 | Project FOCUS will allow collocation at Seneca NOC. Future collocation sites at fire stations and other NOCs. | GeoVision, Technology Solutions, JET, and Network Controls | Quality verification, identification, and inspection of hand hole, depth, and anchor egress. GPS of fiber, hand hole, markers, and splice points. Results entered into fiber management software. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | NA | NA
NT10BIX5570117 | 2013 | 36237 | na | 0 | na | 0 | na | 10 GB | na | 1GB | na | 10mb | na | 0 | na | Most anchors will receive 1GB connection. Currently most do not have GB connection. | na | na | na | 36288 | 3629 | 0 | 32659 | 0 | 0 | 0 | County has entered into a dark fiber agreement with Dukenet for 143 fiber miles | 1350 | 400 | 0 | 950 | Project FOCUS will allow collocation at Seneca NOC. Future collocation sites at fire stations and other NOCs. | Geovision, JET, Network Controls, and Technology Solutions | 17 aggregation sites built to reduce costs of build out for last mile connections for ISPs. ISPs take advantage GPON connections closer to the businesses and residential areas which provides sustainability for the project and cost savings for customer. Utilizing Telvent software to manage and map both inside and outside fiber infrastructure. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | na | na
NT10BIX5570118 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - No customer churn at this point. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - There is no wholesale dark fiber at this time. | 0 | 0 | 0 | 0 | Co-location planning is underway as part of the design and construction process. Co-location is projected to be available at the Huey P Long Hospital (Pineville - not a Nexus owned facility), and Nexus facilities in Dry Prong, Winnfield, Jonesboro, Ruston, and Vienna. Although construction design has not been finalized at this time, the co-location facilities are projected to be 288 to 384 square feet with approximately half the space available for co-location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | At this point in the project, we are engaged in engineering design and environmental assessment services. For best practices, we learned the most impressive engineering firms may not be the best contractors for this type of project. In our case, we selected an excellent firm with impressive credentials which appeared to exceed our expectations. We were disappointed, however, when the firm withdrew as it was not willing to commit the resources to meet timelines and other commitments for the project. We also learned many professional engineers appear to not read an RFP, but instead reply with a standardized, vague, response and do not wish to commit to project fee caps or timelines as noted above. We learned our best engineer might be the smaller firm with a good organizational effort. The best practice therefore is to carefully prepare specifications in the engineering RFP and even more carefully evaluate proposals received. Environmental assessment response appear to be the item which will cause the greatest delays in any of the BTOP or BIP projects. In another project, we have already experienced six to eight month delays for environmental clearances which would normally be routine. the problem appears to be the environmental officers at all levels (local, State, Federal) are overwhelmed with project requests. The lesson learned is environmental clearance processing cannot be a passive request process, but must be pursued on a daily basis. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time. | N/A - Peering and Transit Agreements for this project have not been completed at this time.
NT10BIX5570118 | 2011 | 56000 | Cost based on budgeted cost of construction of 125 miles including all facilities and equipment. | 0 | N/A - Middle mile project | 0 | N/A - Middle mile project | 10G | Standard speeds will be from 10M to 10G | 0 | N/A - Middle mile project | 0 | Network not yet available due to construction in progress | 0 | N/A - Middle mile project | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - There has been no customer churn at this point. | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - There is no wholesale dark fiber at this point. | 1680 | 840 | 0 | 840 | Co-location planning is underway as part of the design and construction process. Co-location is projected to be available at the Huey P Long Hospital (Pineville - Nexus owned facility on grounds of the hospital), and Nexus facilities in Dry Prong, Winnfield, Jonesboro, Ruston, and Vienna. Co-location facilities are 120 square feet except for Vienna which is 1200 square feet. Approximately half the space available for co-location in each location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | We followed the established USDA RUS format for engineering and contracting and found these contracts and standards protected all parties fairly. Early securing of fiber was essential to success in the project . We were very disappointed to discover the absolute power railroads have and how they can hold a project hostage for any amount of budget dollars the railroad deems appropriate. We learned to value and advantage of hiring an expert environmental engineer to keep the project on track with the complex requirements of the environmental review. Through our project engineer, we found the value of contracting with an experienced installation company as opposed to the first or lowest bidder. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time due to construction in progress. | N/A Peering and transit agreements for this project have not been completed at this time due to construction in progress.
NT10BIX5570118 | 2012 | 38035 | Cost based on actual cost of construction to date of 125 miles. | 0 | N/A - Middle mile project | 0 | N/A - Middle mile project | 10G | Standard speeds will be from 10M to 10G | 0 | N/A - Middle mile project | 500 | CAI sites connected at speeds from 100M to 1G. | 0 | N/A - Middle mile project | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - There has been no customer churn at this point. | 18000 | 3000 | 0 | 15000 | 20228 | 0 | 17228 | N/A - There is no wholesale dark fiber at this point. | 2480 | 1240 | 0 | 1240 | Co-location planning is underway as part of the design and construction process. Co-location is available available at Nexus facilities in Dry Prong, Winnfield, Jonesboro, and Vienna as well as the Nexus Venable POP. Co-location facilities are 120 square feet except for Vienna which is 1400 square feet and Venable at 360 square feet. Approximately half the space available for co-location in each location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | We followed the established USDA RUS format for engineering and contracting and found these contracts and standards protected all parties fairly. Early securing of fiber was essential to success in the project . We learned to value and advantage of hiring an expert environmental engineer to keep the project on track with the complex requirements of the environmental review. Through our project engineer, we found the value of contracting with an experienced installation company as opposed to the first or lowest bidder. As we continue with the project through a project modification, we have learned the essential nature of tracking environmental and related regulatory concerns carefully. We have also found partners willing to enhance the project through cooperative endeavors. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time due to construction in progress. | N/A Peering and transit agreements for this project have not been completed at this time due to construction in progress.
NT10BIX5570118 | 2013 | $42,587 | Cost based on budgeted cost of new construction of 120 miles including all facilities and equipment plus upgrades of 176 miles including 56 miles of microwave upgrade and 120 miles of fiber upgrades. The average cost per mile is based on the total of $12,605,894 expended (Including match) for 296 total miles or $42,587/mile. | 0 | N/A - Middle mile project | 0 | N/A - Middle mile project | 10G | Standard speeds will be from 10M to 10G | 0 | N/A - Middle mile project | 500 | CAI sites connected at speeds from 100M to 1G | 0 | N/A - Middle mile project | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. Public safety and transportation sites in Ouachita, Lincoln, Bienville, Claiborne, Webster, and Caddo parishes were upgraded with improvements to their existing services. In those sites, existing, but unlit fiber was upgraded to raise service levels from 1.5 Mbit ("T1") service to a minimum of 20 Mbits with backbone sites receiving up to 1 Gbps service. | N/A Retail services are not being provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - There has been no customer churn at this point. | 18000 | 9000 | 0 | 9000 | 3000 | 0 | 15000 | N/A - There is no wholesale dark fiber at this point. | 2480 | 1240 | 0 | 1240 | Co-location is available as part of the design of the net. Co-location is available at Nexus facilities in Dry Prong, Winnfield, Jonesboro, and Vienna as well as the Nexus Venable POP. Co-location facilities are 120 square feet except for Vienna which is 1400 square feet and Venable at 360 square feet. Approximately half the space available for co-location in each location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | We followed the established USDA RUS format for engineering and contracting and found these contracts and standards protected all parties fairly. Early securing of fiber was essential to success in the project . We learned to value and advantage of hiring an expert environmental engineer to keep the project on track with the complex requirements of the environmental review. Through our project engineer, we found the value of contracting with an experienced installation company as opposed to the first or lowest bidder. We have also found partners willing to enhance the project through cooperative endeavors. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | Interconnection or master agreements have been completed with two (2) providers at this time with negotiations underway with three (3) other providers. There have been no requests for agreements denied. | There has been one peering agreement initiated at this time. There are no specific transit agreements in place at this time.
NT10BIX5570119 | 2010 | n/a | No construction yet | n/a | Middle-mile project | n/a | Middle-mile project | n/a | No speeds advertised yet | n/a | Middle-mile project | n/a | No service provided yet | n/a | Middle-mile project | n/a; no connections yet | n/a; no services provided yet | n/a | n/a | 0 | 0 | 0 | 0 | 1960 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a; no construction yet | We made no subcontracts or subgrants in the reporting period | n/a | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | n/a | n/a
NT10BIX5570119 | 2011 | 0 | Not yet available. The first work-orders have only just begun to close. There is not enough information to provide decisive data. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 16 Mbps | n/a | 0 | n/a | Average increase in speed was 8.5 Megabytes per second (Mbps). Most above had a T1 which is 1.5 Mbps and have chosen 10 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are only a starting point for negotiations and are not written in stone. | None. We are not limiting or blocking access to our network. | none | 257600 | 100 | 0 | 57500 | 60000 | 120000 | 20000 | none | 0 | 0 | 0 | 0 | When we complete our builds to Columbus and Cincinnati we will be in the same proximity as other major carriers. This will be an optical hand-off. | KGP Logistics - 1 sub-contract | n/a | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Six (6) 2. One (1) 3. Zero (0) | n/a
NT10BIX5570119 | 2012 | $46,876 | Initial statistics appear to be running slightly below the projected cost in our baseline (96.75% of $48,450). However we are seeing signs that the costs will come in much higher due to higher than average costly make-ready charges. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 16 Mbps | This is a direct result of slower build rate than expected. The environmental assessment requirements, make-ready and permitting delays put us behind our baseline of 20 Mbps in year 1 and 150 Mbps in year 2. These rates will increase as the build is finished and more customers are added. This rate is the result of thirty-two connections ranging from 5 Mbps to 1 Gbps, averaging 16 Mbps. | 0 | n/a | Average increase in broadband speed provided is 60 Mbps. Calculated by averaging speed prior to connection with Horizon (in most cases a T-1 or 1.5 Mbps, but ranging from 0 to 100 Mbps) which was 9 Mbps subtracted from average of current connection with Horizon (ranging from 5 Mbps to 1 Gbps) which was 69 Mbps, for a total of 60 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are only a starting point for negotiations and are not written in stone. | none | none | 257500 | 101355 | 0 | 520 | 155129 | 0 | 496 | Windstream - 250 miles | 0 | 0 | 0 | 0 | Connectlink, Inc - we connect at their physical location Country Connection (2) - we connect at their physical location JB-Nets, LLC - we connect at their physical location New ERA Broadband - we connect at their physical location Smart Networks - we connect at their physical location Southern Ohio Communication Services (SOCS) - we connect at their physical location | KGP Logistics - 1 sub-contract | none | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Windstream. 2. Zero (0) 3. Zero (0) | n/a
NT10BIX5570119 | 2013 | $64,516 | 133.2% of $48,450. This per mile rate does includes estimates for post construction make ready not yet invoiced. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 108 Mbps | Based on direct connections; subscribers have speeds ranging from 5 Mbps to 1 Gbps. | 0 | n/a | Average increase in broadband speed provided is 191 Mbps. Calculated by averaging speed prior to connection with Horizon (in most cases a T-1 or 1.5 Mbps, but ranging from 0 to 100 Mbps) which was 9 Mbps subtracted from average of current connection with Horizon (ranging from 5 Mbps to 1 Gbps) which was 200 Mbps for a total of 191 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are on a starting point for negotiations and are not written in stone. | 7a. None 7b. No | none | 256293 | 255273 | 0 | 1020 | 0 | 0 | 0 | Windstream - 250 miles Washington County Board of Commissioners - 2 miles | 4882 | 4882 | 0 | 0 | To date we have built to each provider's meet point. Connectlink, Inc - we connect at their physical location Country Connection (2) - we connect at their physical location Intelliwave - we connect at their physical location JB-Nets, LLC - we connect at their physical location New ERA Broadband (2) - we connect at their physical location Rowe Wireless Networks - we connect at their physical location Smart Networks - we connect at their physical location Southern Ohio Communication Services (SOCS) - we connect at their physical location | KGP Logistics - 1 sub-contract | none | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Windstream. 2. Zero (0) 3. Zero (0) | n/a
NT10BIX5570119 | 2014 | $49,387 | 102% of baseline. This per mile rate does not include all make ready as some has not yet been performed. Horizon expects this expense to take approximately three additional years to complete. This amount will raise the average cost per mile by approximately $5k to over $54,000 per mile or 112% of budget. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 100 Mbps | Based on direct connections; subscribers have speeds ranging from 5 Mbps to 1 Gbps. | 0 | n/a | Average Increase in broadband speed provided is 191 Mbps. Calculated by averaging speed prior to connection with Horizon (in most cases a T-1 or 1.5 Mbps, but ranging from 0 to 100 Mbps) which was 9 Mbps subtracted from average of current connection with Horizon (ranging from 5 Mbps to 1 Gbps) which was 200 Mbps for a total of 191 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 40 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are a starting point for negotiations and are not written in stone. | 7a. None 7b. No | none | 237711 | 18787 | 4430 | 214494 | 0 | 0 | 0 | Windstream - 250 miles; Washington County Board of Commissioners - 2 miles; OARnet - 875 miles; Southern Ohio Medical Center - 36 miles; Shawnee State University - 0.63 miles | 5040 | 5040 | 0 | 0 | We have built to each provider's meet point, connecting at their physical location. Going forward we have meet points at Columbus Scherer's Ct (40.11554, -83.00267), Horizon's Chillicothe POP (39.333201, -82.979905), Horizon's Portsmouth POP (38.733983, -82.996002) and Columbus Blue Mile (39.967655, -82.995404). | KGP Logistics - 1 sub-contract | Two major issues we struggled with both related to tracking information on spreadsheets. In one case there were multiple overlapping pieces of information being tracked on spreadsheets by multiple people and departments. In some cases there was only one or two differences in what was being tracked. This duplication of effort was not an efficient use of our time. We found a solution in Google Docs (for our purposes). This allowed multiple people to update the same document, but only if they were one of a select few. Then an even greater number of people could have access to view the data, but not make any changes in advertantly which protected the integrity. If someone needed to work with the data, they were able to download the information into excel to manipulate. The second case dealt with tracking the Community Anchor Institutions (CAIs). They were also being tracked in spreadsheet form. Problem here was getting consistent counts of each type of CAI. Also they changed names and moved locations. Occassionally the spreadsheet file would become corrupt or the wrong version would be used for reporting. We finally put them in an access database which has live counts. From that point forward our counts were very consistent and gave us greater confidence in our reporting. | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Avolve; Country Connection; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communications Services (SOCS); Sprint; Verizon (4); Windstream. Horizon has five dark fiber agreements with the following: Windstream; Washington County Board of Commissioners; The Ohio Academic Resources Network (OARnet); Southern Ohio Medical Center; and Shawnee State University. Shawnee State University was signed in 2014. The rest were signed in prior years. There was one other WISP online who has since been disconnected for non-pay. 2. Horizon is not currently negotiating any interconnection agreements. 3. Horizon has not denied any requests for interconnection. | n/a
NT10BIX5570120 | 2010 | $0 | N/A | N/A | N/A | N/A | N/A | $0 | N/A | N/A | N/A | $0 | N/A | N/A | N/A | N/A | N/A | MCNC has Internet/Data Acceptable Use, Nondiscrimination, Interconnection, and Network Management Policies (see https://www.mcnc.org/about/policies.html for further details). MCNC does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to it's existing infrastructure or on proposed BTOP infrastructure. | N/A | 192922 | 0 | 0 | 112 | 0 | 0 | 192810 | N/A | 0 | 0 | 0 | 0 | We will be deploying network huts as we get in to construction after the FONSI has been received and interconnect can happen at that time in those locations, as well as all handholds with splice locations along the route. | N/A | N/A | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | N/A | N/A
NT10BIX5570120 | 2011 | 0 | While newly constructed miles have been installed in the ground, they are not in service at this point, and per guidance are not included in this report. | 0 | N/A to our project | 0 | N/A to our project | 0 | At this point we have not placed any segments in to service. Ultimately the initial offering will be 10Gpbs with capabilities up to 100Gbps. | 0 | N/A to our project | 0 | At this point we have not placed any segments in to service. Ultimately the initial offering will allow for 10Gbps average connectivity. | 0 | N/A to our project | While we have not yet completed any of the infrastructure, plans call for all CAI's to receive service at a minimum of 1Gpbs over the fiber enabled infrastructure. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 189725 | 0 | 0 | 0 | 6372 | 0 | 183353 | No customers have been signed on as of this report. | 0 | 0 | 0 | 0 | MCNC will be deploying telecommunication huts as part of the project as we enter the next 6 months of the project. As of this report, several had been started from a site work perspective, but none had been finished. Where suitable existing space exists, MCNC will use a few select CAI's along the route to house the equipment that will operate the network. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. Do not allow your contracts that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy stuff, let the remainder, and our prime contractor has had difficulty finding someone to complete the segment they were awarded. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | No agreements have been signed to date. Our marketing partner is discussing opportunities with potential carriers and users of the network, but none have been signed to date. We are learning that carriers want to see the final product before making any commitments. No requests for discussion about potential agreements have been denied. | As the construction of the network is ongoing, with no full segments ready for operation, there are no peering and transit agreements yet in place.
NT10BIX5570120 | 2012 | 54,349 | While newly constructed miles have been installed in the ground, they are not in service at this point, and per guidance are not included in this report. We are lower to baseline than forecasted because the miles counted toward this calculation are those miles that were cheaper to construct and operate at this point. More challenging and thus costly miles are built, but not yet considered completed and in service. | N/A | N/A to our project | N/A | N/A to our project | 10Gbps | We anticipate initially that most expected service offerings requested from our user base will be 1Gbps through 10Gbps. The system being deployed, however, has capability to scale to 100Gbps as required. | N/A | N/A to our project | 1Gbps | As it relates to services to the CAI's served, all are provisioned with 1Gbps capacity. Along the backbone routes of the network, which at this point we've deployed three such services, the average capacity for those is 10Gbps. | N/A | N/A to our project | The CAI's that we currently serve operate on limited capacity 100M interfaces at most. As we deployed, we are putting them on to burstable 1Gbps links that interface directly with a 10Gbps path. Therefore based on what we know, their immediate increase with the equipment deployed gives them 900Mbps more in capability day one. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. The two carriers that have signed on for dark fiber access will provide this service, but to date we do not have visibility in to how they will price their offerings, although we do know that it will be scalable service as required from 10Mbps up to 10Gbps as users warrant. Both carriers are wholesale carriers. Discussions with 1-2 residential providers are ongoing. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 197412 | 2092 | 1481 | 65287 | 43632 | 0 | 84920 | MCNC has sold dark fibers to two wholesale carriers, Broadplex and Dukenet Communications. The Broadplex agreement is for 1279 strand miles and the Dukenet Communications agreement is for 202 strand miles. | 3600 | 224 | 0 | 3376 | MCNC has deployed telecommunication huts as part of the project as outlined above. MCNC will additionally use a few select CAI's along the route to house the equipment that will operate the network. In these particular facilities MCNC does not control the ability to allow other carriers or entities to colocate. Above and beyond that, hand hands that are placed no farther apart than a mile act as interconnect points for splicing capability to the backbone to fibers another provider or user would build to those locations. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE Vertech International MBE MSM, Inc. MBE Dig-It MBE Coastline Cable Construction WBE HK&L, LLC WBE applied for Peachtree Telecommunications, Inc. WBE | Work through your permitting process as quickly as possible, especially those involving railroads. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to to only focus on the easy elements of construction first without also addressing some of the difficult elements. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | To date we have entered in to two IRU agreements for dark fiber with wholesale and last mile carriers. The agreements were for one fiber across portions of the footprint totaling 1279 miles, and a second agreement for two fibers across 101 miles. We have not executed any other transit, peering, or interconnection agreements to date. Negotiations continue with eight additional providers for fibers in various portions of the constructed route. We have not denied any request for interconnection to the fiber routes. | N/A
NT10BIX5570120 | 2013 | $63,759.66 | Total capital construction costs not including IRUs, equipment and software total $82,951,324 for 1,301 miles. We are slightly above baseline of $59,657.62 per mile due to costs of construction in the western portion of the network being higher than expected than in the budget. | NA | N/A to our project | NA | N/A to our project | 100Gbps | We anticipate initially that most expected service offerings requested from our user base will be 1Gbps through 10Gbps. The system being deployed, however, has capability to scale to 100Gbps as required. | NA | N/A to our project | 3.2Gbps | As it relates to services to the CAI's served, all are provisioned with 1Gbps capacity. Along the backbone routes of the network we provisioned thirty-eight 10Gbps backbone services. Additionally we have turned up MPLS based last mile services to the following speeds and tiers of services: 10M:6 20M:4 30M:1 50M:6 100M:52 150M:1 250M:30 275M:2 475M:1 500M:13 1G:11 2G:2 3G:1 | NA | N/A to our project | The CAI's that we currently serve operate on limited capacity 100M interfaces at most. As we deployed, we put them on to burstable 1Gbps links that interface directly with a 10Gbps path. Therefore based on what we know, their immediate increase with the equipment deployed gives them 900Mbps more in capability day one. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. Several of the carriers that have signed on for dark fiber access will provide this service, but to date we do not have visibility in to how they will price their offerings. We do know that it will be scalable service as required from 10Mbps up to 100Gbps as users warrant. Additionally one of the carriers that has bought fiber on the whole footprint is a residential provider that in it's current operations provides 50x50M service for $59.95/month. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 197921 | 6256 | 11865 | 179800 | 0 | 0 | 0 | MCNC has sold dark fibers to MOX Networks (12 strands over 70 miles), RST Communications (6 strands over 1345 miles), Broadplex Communications (2 strands over 1349 miles), Dukenet Communications (2 strands over 101 miles), Conterra (2 strands over 15.5 miles), and Earthlink (2 strands over 12 miles) to account for the 11,865 strand miles noted above. | 3600 | 592 | 16 | 2992 | MCNC has deployed telecommunication huts as part of the project as outlined above. MCNC will additionally use a few select CAI's along the route to house the equipment that will operate the network. In these particular facilities MCNC does not control the ability to allow other carriers or entities to colocate. Above and beyond that, hand holes that are placed no farther apart than a mile act as interconnect points for splicing capability to the backbone to fibers another provider or user would build to those locations. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE Vertech International MBE MSM, Inc. MBE Dig-It MBE Coastline Cable Construction WBE HK&L, LLC WBE applied for Peachtree Telecommunications, Inc. WBE | Work through your permitting process as quickly as possible, especially those involving railroads. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to to only focus on the easy elements of construction first without also addressing some of the difficult elements. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | To date we have entered in to 6 IRU agreements for dark fiber with wholesale and last mile carriers. The agreements are with Broadplex, Dukenet Communications, RST Communications, Conterra, Earthlink, and MOX networks. We have not executed any other transit, peering, or interconnection agreements to date. Negotiations continue with 6 additional providers for fibers in various portions of the constructed route. We have not denied any request for interconnection to the fiber routes. | N/A
NT10BIX5570122 | 2010 | 0 | Deployment has not started, and no portion of the network is available for service yet. Therefore, there is no cost per mile indicated for this report. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 1 Gbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 100 Mbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps, and we anticipate that most of our customers will fall into that level of service. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that we anticipate will be offered to most community anchor institutions. | Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the FRBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern Florida. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network that has not yet been deployed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will not be providing access to dark fiber, as we do not have that access. | 0 | 0 | 0 | 0 | Co-location facility square footage information is yet to be determined. Contract negotiations with Level 3 have commenced, and upstream engineering and provisioning are currently still in development. Interconnection for customers (last mile providers) will be accessed through switched Internet Protocol/Ethernet multi-service access platforms (MSAPs)located at each tower/wireless network link. | We have not issued any subcontracts or subgrants. | We improved our approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability, greater capacity, and greater competition from more available manufacturersâ€”all within the original overall project budget. This approach requires more time for site assessments (for existing commercial towers and in-kind vertical assets) and follow-up engineering and network design, but it yields improved efficiency and shortens the overall deployment schedule. We have asked the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office (for our NFBA project) that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles. We are also conducting our own research on this matter in order to move forward with the development of the Equipment Installation and Pathing Request for Proposals (RFP) in an effort to avoid any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Discovery of previous or duplicate federal funding for in-kind assets may or may not impact planned project progress, depending on the interpretation of this particular requirement. We are seeking to utilize only a limited amount of space on any given in-kind asset to mount microwave antennas and equipment; we are not seeking to utilize any in-kind asset in its entirety. | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | N/A. We are developing products and pricing with pre-deployment service level agreements. We are also developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements over the next subsequent quarters. | N/A. As noted above, we are developing products and pricing with pre-deployment service level agreements, and developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. Also, the network design is committed to meeting the stringent quality of service and reliability standards set by the State of Florida for providing transport and direct internet access (as a last mile provider of last resort) to State agencies. Once deployed, the FRBA network will be qualified to serve State offices, community colleges, and their last mile network partners.
NT10BIX5570122 | 2011 | $19,042 | Average cost per mile based on initial 230 mile build of Hardee County. | $3771.76 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | $3771.76 | This project is a Middle Mile network. The cost per subscriber are based on anchor tenant connections. | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 10 Mbps | This project is a Middle Mile network. Last mile services are being provided to selective anchors. The current average speed for anchor tenants is 10 Mbps. | The FRBA network is increasing broadband speeds by a multiple of 4 to 20 times previously available services throughout the region. CAIs are moving from DSL speeds of 1 Mbps to FRBA wireless speeds of 5 to 20 Mbps. Other CAIs are upgrading to 200 Mbps which is 20 times the available capacity they were able to receive prior to FRBA providing broadband in their serving area. Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual average anchor tenant speeds have been less than 1.5 Mbps based on T1 or DSL connectivity. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Current anchor connection speeds being provided by FRBA in Hardee county average 10 Mbps or better. Top speeds currently being provided peak at 20 Mbps. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 10 Mbps with the capability of reaching 100 Mbps on average for high speed connections. | FRBA is a middle provider and as such will not be offering a broad based retail service except to anchor institutions and as carrier of last resort. However, in these scenarios, FRBA plans to offer wireless Ethernet and Internet based services. These services will be offered in bandwidth pricing tiers to accommodate the needs of the region. These services will be offered in multiples of 2, 5, 10, 15, 20, and up Mbps. Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the FRBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern and central Florida. FRBAs network management policies are in effect and active with the initial deployment of Hardee County. These policies will continue to be developed and scaled to meet the needs of the region as the FRBA network continuous to be deployed in other counties. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limi | No subscriber has dropped service during the early testing and pilot phase of the deployment in Hardee County. Based on the small sample size of 26 subscribers the churn rate is 0%. The FRBA network is still relatively new and an effective churn rate cannot be calculated at this time. | 1216 | 1216 | 0 | 0 | 0 | 0 | 0 | N/A | 144 | 144 | 0 | 0 | FRBA has negotiated space with Level 3 and Rapid Systems and has a collocated cabinet at each of the tower location sites. FRBA provides wireless network access so subscriber and wholesale service connections can be made at any one of the 4 fiber collocation data centers or at the tower sites through either wireless or physical Ethernet service connections to the cabinet. This enables FRBA to provide wholesale providers and anchor tenants a number of geographic options. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. | FRBA has not issued any subcontracts or subgrant SDB firms. | FRBA has improved its approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability and greater â€” all within the original project budget. This approach enabled FRBA to redesign its network to meet commercial carrier class service objectives and create more cost effective opportunities for wholesale services providers. FRBA in collaboration with its partners and vendors has developed and tested the next generation high capacity wireless backbone designs capable of multi-gigabit speeds and network access options from 10 Mbps to 1 Gbps. In addition FRBA has created and leveraged Level 3s BTOP grant investment that was essential to providing fiber access through the ILAs in rural central and northern Florida. This has proved to be essential to managing high capacity links and services to FRBAs wireless core. With the help of Rapid Systems, FRBA has developed an ISO standardized documentation framework for the project and plans to continue to develop ISO best practices as part of its operational deployment. These standards are being incorporated into FRBAs Operational Support and Back Office Systems to streamline operational and customer service management processes. This high degree of automation will help reduce the operational burden and cost that FRBA will incur as anchor tenants and wholesale partners begin to fully utilize the network. Some of FRBAs ISO documents include; â€¢ Quality Policy Manual â€¢ Document Control Manual/Record Retention Policy â€¢ Warehouse Policy/Procedures â€¢ Finance Policy/Procedures â€¢ Inventory Control/Asset Tagging â€¢ Dispatch/RMA Policies/Procedures â€¢ Interoperability and Benchmark Testing â€¢ Security and Disaster Plan/Hurrican/Fire â€¢ Fabrication and Work Practices FRBA also attended the BTOP Best Practices workshop and identified a number of awardees that have already developed best practices. Some of these best practices have contributed to the redesign and development of internal processes related to procurement, fraud prevention, and the development of RFPs for construction. In addition FRBA has been evaluating how other programs are managing compliance.. | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has interconnection agreements with four wholesale providers. • Rapid Systems has agreement with the Hardee County Broadband Project. • Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project • Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol • Rapid Systems has a wholesale/Last Mile agreements with TampaBayDSL No requests were denied in 2011. | FRBA has established a IRU and IP transit agreement with Level 3 for fiber and internet services. These services are being provided to FRBA anchor tenants and wholesale service providers using FRBAs network services.
NT10BIX5570122 | 2012 | $11,776 | FRBA's average cost per new mile is calculated by dividing total capital costs for network construction (less certain equipment categories) by 1,201 total route miles in the project to arrive at an average cost per mile of $11,776. | 0 | FRBA is a middle-mile network only and does not provide any direct last-mile residential access. Last-mile providers will provide such services utilizing FRBAâ€™s middle-mile capacity for backhaul to reach markets within the service area. | 0 | FRBA is a middle-mile network only and subscriber connections will only be made to community anchors throughout the region (as well as last-mile providers). Costs associated with such infrastructure are not included in this section. | 200Mbps | FRBA is a middle-mile network capable of providing wholesale capacity in increments of 200Mbps. Gigabit speeds are available on the FRBA network on an individual case basis. | 200Mbps | FRBA is a middle-mile network but will provide last-mile services to community anchors. Anchors will be able to receive a maximum of 200Mbps, but additional capacity may be provisioned to increase that capacity to higher rates. | 200Mbps | FRBAâ€™s middle-mile wholesale access will provide transport and commodity Internet services between speeds of 5Mbps and 200Mbps. We anticipate the average middle-mile transport circuit at 20Mbps, based on the requirements of CAIs in the region and last-mile providers. Last-mile providers will require larger transport circuits for backhaul into local service areas. In addition, last-mile providers will require direct type 2 services to reach customers in these areas. | 10Mbps | Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport services in FRBAâ€™s service area. Currently, many anchors utilize DSL, T1 or T1xN services and FRBAâ€™s services will provide a significant increase in capacity over legacy copper infrastructure. | The FRBA network will provide significant increases in broadband speeds to community anchors throughout the region. Through our market research, we have found that many CAIs in the service area receive DSL, Cable and NxT1 local access services, in most cases limited to 6Mbps or less. FRBAâ€™s network will provide bandwidth from 5Mbps to 200Mbps to CAIs, utilizing both shared and dedicated products. On average, and through our outreach programs, we have recognized that many CAIs will upgrade existing services by 3-5 times the amount of bandwidth they currently receive. On average, a 6Mbp customer will double or triple their bandwidth on the FRBA network, for competitive rates using FRBAâ€™s redundant middle-mile infrastructure. In addition, CAIs will be able to interconnect their facilities utilizing FRBAâ€™s transport services, allowing them to provision site-to-site connectivity, previously only possible through high-cost, legacy private line circuits and unreliable Internet-based VPNs. | FRBA will offer retail services to CAIs throughout the region. These services include point-to-point/multi-point transport and Internet services to community anchors as identified in this APR and its attachments. FRBA has identified many CAIs in its region that require a combination of transport and Internet services. Transport services will provide site-to-site connectivity for many of the local government, public safety and healthcare customers in the region, enabling them to upgrade or replace their costly copper-based WAN services with higher speed wireless WAN services. FRBA will also participate in the E-Rate program for Schools and Libraries as administered by USAC and will be an eligible E-Rate provider for these organizations. For these critical education-based CAIs, FRBAâ€™s network will provide high-performance Internet and site-to-site transport interconnections between schools, libraries and related facilities, helping ensure students have access to critical online resources. Pricing for services is also included in the attached rate sheet for dedicated transport and Internet capacity (Please see FRBA Rate Sheet 1.0.pdf) | FRBAâ€™s network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. FRBA will offer at least two classes of services to its customers depending on their particular needs and budgetary constraints. FRBA will offer both dedicated and shared access to customers. Dedicated access will provide committed rate services for CAIs and last-mile providers that require guaranteed bandwidth. Shared services will provide best-effort services to customers that donâ€™t require stringent performance requirements, geared primarily for smaller CAIs, branch offices and small businesses. Pricing for shared services will be significantly lower than dedicated services as a result. | The FRBA network is currently under construction and does not have any subscribers | 1216 | 1216 | 1216 | 0 | 0 | 0 | 0 | FRBA does not wholesale dark fiber. | 300 | 300 | 0 | 0 | FRBA has negotiated and purchased colocation space in two Level3 data centers in Orlando, FL and Tallahassee, FL. Both data centers have neutral access to significant regional and national carriers, through which FRBA will develop interconnection agreements and NNIs. Data centers have available cage and cabinet space to provide colocation services to potential subtenants who require local presence for peering and interconnection. FRBA will maintain direct cross-connects to other carriers in these facilities. Additionally, each of FRBAâ€™s tower sites is equipped with colocation facilities for last-mile providers, local exchange carriers and other entities. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. These sites will enable local last-mile networks interconnect with FRBA's middle-mile backhaul to deliver new bandwidth to local service areas. In doing so, FRBA's network will offer a significant amount of points of interconnection into underserved service areas that lack adequate backhaul. Many regions maintain legacy T1 and DS3 backhaul and few offer bandwidth beyond those transport technologies. FRBA will deliver new wireless backhaul to these service areas as an upgrade to existing legacy copper backhaul networks. | FRBA has not issued any subcontracts or subgrants to SDB firms. | No Comments at this time | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has not signed any interconnection agreements during the period in question. FRBA is actively identifying interconnection partners and will be establishing NNIs for wholesale and type 2 services in the region. These activities will coincide with completion and activation of the network to ensure that NNIs and interconnections can be made immediately, allowing the network to begin providing services as soon as it is commissioned. FRBA has begun this process early to ensure that we budget a 6-month window for negotiation of interconnection agreements, required network testing and certification and regulatory filings that may be required. | FRBA currently maintains IRU capacity with Level3 for backhaul connectivity between the wireless middle-mile core network and its two data centers in Tallahassee, FL and Orlando, FL. As the network nears completion, FRBA will identify commodity Internet, peering and interconnection partners to be integrated into the network. FRBA seeks tier 1 IP providers to ensure the highest quality Internet services available to its network. FRBA will also identify value-based Internet providers that can provide diversity to FRBA's network, blended IP transit and maintain competitive overall costs for FRBA's IP transit.
NT10BIX5570122 | 2013 | $17,530.00 | FRBA's average cost per new mile is calculated by dividing total capital costs for network construction (less certain equipment categories) by 1,948 total route miles in the project to arrive at an average cost per mile of $17,530.00 | 0 | FRBA is a middle-mile network only and does not provide any direct last-mile residential access. Last-mile providers will provide such services utilizing FRBAâ€™s middle-mile capacity for backhaul to reach markets within the service area. | 0 | FRBA is a middle-mile network only and subscriber connections will only be made to community anchors throughout the region (as well as last-mile providers). Costs associated with such infrastructure are not included in this section. | 200Mbps | FRBA is a middle-mile network capable of providing wholesale capacity in increments of 200Mbps. | 200Mbps | FRBA is a middle-mile network but will provide last-mile services to community anchors. Anchors will be able to receive a maximum of 200Mbps, but additional capacity may be provisioned to increase that capacity to higher rates. | 200Mbps | FRBAâ€™s middle-mile wholesale access will provide transport and commodity Internet services between speeds of 5Mbps and 200Mbps. We anticipate the average middle-mile transport circuit at 200Mbps, based on the requirements of CAIs in the region and last-mile providers. Last-mile providers will require larger transport circuits for backhaul into local service areas. In addition, last-mile providers will require direct type 2 services to reach customers in these areas. | 10Mbps | Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport services in FRBAâ€™s service area. Currently, many anchors utilize DSL, T1 or T1xN services and FRBAâ€™s services will provide a significant increase in capacity over legacy copper infrastructure. | The FRBA network will provide significant increases in broadband speeds to community anchors throughout the region. Through our market research, we have found that many CAIs in the service area receive DSL, Cable and NxT1 local access services, in most cases limited to 6Mbps or less. FRBAâ€™s network will provide bandwidth from 5Mbps to 200Mbps to CAIs, utilizing both shared and dedicated products. On average, and through our outreach programs, we have recognized that many CAIs will upgrade existing services by 3-5 times the amount of bandwidth they currently receive. On average, a 6Mbp customer will double or triple their bandwidth on the FRBA network, for competitive rates using FRBAâ€™s redundant middle-mile infrastructure. In addition, CAIs will be able to interconnect their facilities utilizing FRBAâ€™s transport services, allowing them to provision site-to-site connectivity, previously only possible through high-cost, legacy private line circuits and unreliable Internet-based VPNs. | FRBA will offer retail services to CAIs throughout the region. These services include point-to-point/multi-point transport and Internet services to community anchors as identified in this APR and its attachments. FRBA has identified many CAIs in its region that require a combination of transport and Internet services. Transport services will provide site-to-site connectivity for many of the local government, public safety and healthcare customers in the region, enabling them to upgrade or replace their costly copper-based WAN services with higher speed wireless WAN services. FRBA will also participate in the E-Rate program for Schools and Libraries as administered by USAC and will be an eligible E-Rate provider for these organizations. For these critical education-based CAIs, FRBAâ€™s network will provide high-performance Internet and site-to-site transport interconnections between schools, libraries and related facilities, helping ensure students have access to critical online resources. Pricing for services is also included in the attached rate sheet for dedicated transport and Internet capacity (Please see FRBA Rate Sheet 1.0.pdf) | FRBAâ€™s network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. FRBA will offer at least two classes of services to its customers depending on their particular needs and budgetary constraints. FRBA will offer both dedicated and shared access to customers. Dedicated access will provide committed rate services for CAIs and last-mile providers that require guaranteed bandwidth. Shared services will provide best-effort services to customers that donâ€™t require stringent performance requirements, geared primarily for smaller CAIs, branch offices and small businesses. Pricing for shared services will be significantly lower than dedicated services as a result. | The FRBA network is currently in the final phases of construction and does not have an aging customer base in which to gauge or forecast a churn rate. FRBA currently has 3 serviceable CAI's with the ability to connect to the network. A single test connection has been provided at a shared facility to beta test the connectivity. It is the intent that each of the 3 customers will ultimately contract directly with FRBA for primary Internet connectivity. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FRBA does not wholesale dark fiber. | 300 | 300 | 0 | 0 | FRBA has negotiated and purchased colocation space in two Level3 data centers in Orlando, FL and Tallahassee, FL. Both data centers have neutral access to significant regional and national carriers, through which FRBA will develop interconnection agreements and NNIs. Data centers have available cage and cabinet space to provide colocation services to potential subtenants who require local presence for peering and interconnection. FRBA will maintain direct cross-connects to other carriers in these facilities. Additionally, each of FRBAâ€™s tower sites is equipped with colocation facilities for last-mile providers, local exchange carriers and other entities. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. These sites will enable local last-mile networks interconnect with FRBA's middle-mile backhaul to deliver new bandwidth to local service areas. In doing so, FRBA's network will offer a significant amount of points of interconnection into underserved service areas that lack adequate backhaul. Many regions maintain legacy T1 and DS3 backhaul and few offer bandwidth beyond those transport technologies. FRBA will deliver new wireless backhaul to these service areas as an upgrade to existing legacy copper backhaul networks | FRBA has not issued any subcontracts or subgrants to SDB firms. | N/A | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has not signed any interconnection agreements during the period in question. FRBA is actively identifying interconnection partners and will be establishing NNIs ("Network to network interconnections") for wholesale and type 2 services in the region. These activities will coincide with completion and activation of the network to ensure that NNIs and interconnections can be made immediately, allowing the network to begin providing services as soon as it is commissioned. FRBA is in the final stages of completing a definitive agreement with competitively chosen network operator. The network operator is a seasoned telecom provider with the potential to perform a more thorough outreach to a much wider audience of interconnection partners. | FRBA currently maintains IRU capacity with Level3 for back-haul connectivity between the wireless middle-mile core network and its two data centers in Tallahassee, FL and Orlando, FL. As the network nears completion, FRBA has identified commodity Internet, peering and interconnection partners to be integrated into the network. Initially FRBA has partnered with a "sister" project in NFBA to arrange an initial 500Mb of HSIP. Not only does this solution provide a service arrangement with a partner in the same data-center as FRBA, but is ultimately a Tier 1 wholesale connection provided directly from Level 3.
NT10BIX5570123 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 Mbps/ $ | N/A | 0 | N/A | 3 Mbps /$ 20 | N/A | N/A; Service is contained to the existing network capacity. The project work has been in environmental planning for the BTOP funded expansion. Community Anchor Institutions will be connected as soon as possible following the construction of the expanded network. | The Nez Perce Tribe Information Systems broadband network currently serves the immediate Lapwai, Idaho area; the service includes internet subscriber accounts of up to 3 Mbps for a flat rate $20/month. | Bandwidth limitations based on service level subscribed to. Content has not been limited. | The Nez Perce Tribe Information Systems network service has152 residential subscribers; 11 dropped service, the reasons are not currently tracked; and, 99 new subscribers were connected in 2010. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No fiber in the Nez Perce Tribe project | 0 | 0 | 0 | 0 | N/A; no construction has taken place | N/A the Nez Perce Tribe is the primary and sole project recipient. | N/A | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | N/A | N/A
NT10BIX5570123 | 2011 | 3621/32.5 Mbps | To date the Nez Perce Tribe network has connected two CAI's: Lapwai Library at 20 Mbps and Clearwater County at 45 Mbps; these connection were made due to a BTOP upgrade to middle mile. Overall project build out has been delayed by weather conditions; one middle mile link is up and on line utilizing two existing towers (Bio-Control - Stoney Point). Across the entire BTOP network, the tower construction is complete; and an wireless equipment installation contract has been awarded and will be underway early 2012. With exception of the proposed route modification, the middle mile is expected to be complete and tested by Q2 2012. | 49.67 | The network has one last mile site active: Stoney Point. The project is considerable behind the projected baseline regarding last mile service delivery. Contracts have been awarded, equipment procured and the last mile access points installation will be project staff priority during Q1 - Q2 2012. | 1490.08 / 3Mbps | The technology for wireless last mile access is limited to line of sight signal transmission. The topography in the Stoney Point tower vicinity has limited the area of coverage. Network staff are busy doing site surveys; and the IT support staff are considering adding last mile equipment that might get the transmission rate up. In addition, project development staff are working to expand existing tower collocation agreements to include a tower above Spaulding, which would complement the service area of Stoney Pt. | 10+ | Rates are $ 100.Mb up to 10; above 10 Mb demand will be negotiated | 20 | Speed tiers offered include 3 Mbps, 10 Mbps and 20+ Mbps | 3621/32.5 Mbps | To date the Nez Perce Tribe network has connected two CAI's: Lapwai Library at 20 Mbps and Clearwater County at 45 Mbps; these connection were made due to a BTOP upgrade to middle mile. | 3 | To date residential subscribers are all at 3 Mbps connection; Lapwai library is connected with 20 Mbps | Last mile service is not built out across the entire network yet. Connections have been made to: Lapwai library where their previous connection rate/costs was 7 Mbps for $ 81/month; and now on the Nez Perce Tribe network is 20 Mbps for $ 50/month Clearwater County government office: where 45 Mbps provided at a cost savings advantage | Wireless high speed internet service is what we offer as a service. Three tiers are available: 3/1.5 Mbps $ 20/month; 10/10 Mbps $ 300/month; 20+ Mbps cost negotiated per month | Subscribers are provided the bandwidth capacity with no limitations of access based on the service tier they select. There are no limits or blocks on subscribers accessing lawful content, service or application; or that would prevent them from attaching any legal device to the network. | No (0%) dropped subscribers from the BTOP funded network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 384 | 120 | 0 | 264 | NA The Nez Perce tribe does own, each tower site has a 8 x 12 communications building with space available for collocation equipment. The project focus has been on construction of towers. Towers range from 100' to 250' tall and there is ample room on most towers for collocation. Collocation requests will be considered first come first serve and be based on tower loading capacity limitations. | NA, no subcontracts with 8(a) businesses. However, there has been a subcontract awarded to Certified Indian owned businesses in accordance with the Nez Perce Tribal Employment Rights Ordinance: GEM Electric and B & C Development Inc | The Nez Perce Tribe entered into mutually beneficial collocation lease rates with its project partners for space on towers for wireless equipment. Staffing for network technician positions: Information Systems program partnership with Tribal workforce development program and interns were trained and able to compete for openings when jobs were advertised; resulting in two technicians hired in full time jobs with benefits. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | Two interconnection agreements have been established between the Nez Perce Tribe and XO Communications for access to ; and between the Nez Perce tribe and Idaho Regional Optic Network. There are no other agreements at this time; and, there have been no agreements denied. | NA; there are no peering or transit agreements
NT10BIX5570123 | 2012 | 10090/200 Mbps | The middle mile network construction was completed Q2 2012 with 152 miles of wireless links installed and functional at speeds of 200 Mbps. Total middle mile project costs $ 1834657 for an average costs of $ 12070 | 115/3,6,9 Mbps | The project last mile delivery has reached 99% completion; testing and working to resolve non line of sight connection in several targeted community areas is underway. To resolve the lack of line of sight connectivity the project staff are placing neighborhood solutions (nanobridge connections to rooftops and distributing signal via sector or omni antenna). Residential subscribers have a choice of 3, 6 or 9 Mbps plans. To date last mile project costs are $ 416,711 and the project has passed 3610 residences for an average cost of $ 115 | 1096/3, 6, 9 Mbps | To date, the project has 380 subscribers; the average last mile cost is $ 1096 | 10+ Mbps | Up to 10 Mb connection is available at established rates; above 10 Mbps rates are negotiable. | 9 Mbps | There are three service levels advertised for last mile: 3, 6, 9 Mbps | 8.25 Mbps | The Nez Perce Network System has three libraries (20, 6,6 Mbps), two city governments (3 Mbps), one county government (15 Mbps), one rural fire district (3 Mbps) and one commercial provider (10 Mb) receiving middle mile connectivity. | 3 Mbps | The Nez Perce Network System has 288 subscribers at 3 Mbps, 75 at 6 Mbps, 16 at 9 Mbps, 1 at 10 Mbps and 1 at 20 Mbps. | As a result of Nez Perce Network Systems BTOP expansion the Connected CAI's include: Lapwai (library receives more affordable service - previous connection rate/costs was 7 Mbps for $ 81/month; and on the Nez Perce Tribe (NPT) network is 20 Mbps for $ 50/month); Culdesac City and Library (more affordable service - the City connection is part of an agreement (land use for tower location in exchange for free 3 Mbps connectivity; previous connection at the Library was $ 45 for 2 Mbps; and on the NPT network $ 40/mo for 6 Mbps) and Public safety entities receive first mobile access; Peck (library previous connection was $ 79 for satellite and Rural Fire District received its first broadband service available); Clearwater County(county received more affordable service previously $ 830/mo, on NPT network $ 700 for 20 Mbps and in addition the benefits of centralized management, WAN deployment and improved system support in remote locations); and Kamiah (senior center received a new broadband connection). In addition to fixed service the project expanded mobile broadband access in partnership with Inland Cellular; the mobile access was deployed in an area of the Reservation previously unserved and provided access to ID State Police, Lewis and Nez Perce County Sheriff Dept's, Tribal police and Emergency Mgmt entities greatly improving public safety along a dangerous section of State Hwy 95. | Residential and Business last mile services offered include three plan tiers: 3 Mbps ( $ 20/month); 6 Mbps ($ 40/month); and, 9 Mbps ($ 60/month). | Subscribers are provided with the bandwidth capacity with no limitations of access based on the service tier they select. There are no limitations or blocks on subscribers accessing lawful content, service or application. There are no blocks that would prevent subscribers from attaching any legal device to the network. | Over the past year two (2) subscribers dropped service (< 0.1%), the reason for discontinuing the service was at the base plan (3 Mbps) they experienced lag while streaming and this dissatisfied them. No, our technicians let perspective subscribers know if they plan to do a fair amount of streaming the higher bandwidth plans may be better suited for such use. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 864 | 288 | 100 | 476 | NA; the Nez Perce Tribe owns nine of the facility sites and space. Collocation on towers at each site will be considered on a first come first serve basis and be based on tower loading capacity/limitations. Currently, tower space and communication building space has been leased to one provider at one site. | There have been no 8A subcontracts let. Three Certified Indian owned businesses under the Nez Perce Tribal Employment Rights Ordinance have received subcontract opportunities (BOSS Heating & Air, B&C Development Inc, and GEM Electric). | The Nez Perce Tribe developed proactive partnerships with a regional mobile provider for tower space utilization and mutually agreeable collocation rates; this partnership enabled both entities to expand coverage affordably and efficiently. In addition, the Tribe pursued site use partnerships where possible in exchange for service delivery to implement its neighborhood solution equipment to reach customers outside of the main network line of sight coverage areas. The marketing effort is targeted to neighborhoods and the project staff found a tool offered by the US Postal Service - Direct Mail, enabling low cost bulk direct mailings delivery to targeted areas. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | The Nez Perce Tribe has two sources for interconnection: XO Communications; and the Idaho Regional Optic Network. There are no additional source for interconnection available. | The Nez Perce Tribe currently has two transit agreements: Washington RSA #8 Limited Partnership, dba Inland Cellular has contracted 10 Mbps of network middle mile to facilitate their expansion of mobile access; and the Education Network of America, Inc. to provide a dedicated 3 Mbps between Peck Elementary and Orofino High School, which is expected to be live early in Q1 2013.
NT10BIX5570123 | 2013 | 10856 | 175 Miles of middle mile network was deployed across the Tribes wireless network with functional speed of 200 Mbps. Total cost to deploy middle mile $ 1,899,847. | 115 | Residential subscribers have the choice of three tiers: 3, 6 or 9 Mbps connectivity. Project costs to deploy last mile are $ 416,711 and the network has passed 3,601 households for an average cost of $ 115. | 590 | The network has 706 active subscribers; the average cost per subscriber is $ 590 | 10 + Mbps | Connections up to 10 Mbps are available at a set rate of $ 100/Mb; above 10 Mbps connections are possible and rates negotiated. | 9 Mbps | There are three tier levels available: 3, 6 and 9 Mbps | 10.44 Mbps | There are 18 CAI's connected at rates ranging from 3 - 20 Mbps; and one wholesale agreement at 3 Mbps established on the Tribes network. The average connection is 10.44 Mbps | 3 Mbps | There are 480 (68%) subscribers at 3 Mbps; 189 (26%)at 6 Mbps; and 33 (4%)at 9 Mbps | As a result of Nez Perce Network Systems BTOP expansion the Connected CAI's include: Lapwai (library receives more affordable service - previous connection rate/costs was 7 Mbps for $ 81/month; and on the Nez Perce Tribe (NPT) network is 20 Mbps for $ 50/month); Culdesac City and Library (more affordable service - the City connection is part of an agreement (land use for tower location in exchange for free 3 Mbps connectivity; previous connection at the Library was $ 45 for 2 Mbps; and on the NPT network $ 40/mo for 6 Mbps) and Public safety entities receive first mobile access; Peck (library previous connection was $ 79 for satellite and Rural Fire District received its first broadband service available); Clearwater County(county received more affordable service previously $ 830/mo, on NPT network $ 700 for 20 Mbps and in addition the benefits of centralized management, WAN deployment and improved system support in remote locations); the ID Fish-Game Clearwater Hatchery had only access to satellite or dial up connection and now has a wireless 6 Mbps connection; and the Dworshak National Fish Hatchery which also was limited by a copper line connection with slow speeds, now has a 6 Mbps connection via the TrIbes wireless network. In addition to fixed service the project expanded mobile broadband access in partnership with Inland Cellular; the mobile access was deployed in an area of the Reservation previously unserved and provided access to ID State Police, Lewis and Nez Perce County Sheriff Dept's, Tribal police and Emergency Mgmt entities greatly improving public safety along a dangerous section of State Hwy 95. | Residential and Business last mile services offered include three plan tiers: 3 Mbps ( $ 20/month); 6 Mbps ($ 40/month); and, 9 Mbps ($ 60/month). | Subscribers are provided with the bandwidth capacity with no limitations of access based on the service tier they select. There are no limitations or blocks on subscribers accessing lawful content, service or application. There are no blocks that would prevent subscribers from attaching any legal device to the network. | Since service delivery began less than1 percent, of the subscribers have discontinued service. The reason for discontinuing the service was at the base plan (3 Mbps) they experienced lag while streaming and this dissatisfied them. No, our technicians let perspective subscribers know if they plan to do a fair amount of streaming the higher bandwidth plans may be better suited for such use. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1600 | 672 | 210 | 718 | NA; the Tribe owns nine of the facility sites used in the network. Collocation is being considered on a first come first serve basis. Currently, the Tribe has lees with Inland Cellular at two sites (Beard, Culdesac). | There have been no 8A subcontracts let. Three Certified Indian owned businesses under the Nez Perce Tribal Employment Rights Ordinance have received subcontract opportunities (BOSS Heating & Air, B&C Development Inc, and GEM Electric). | The Nez Perce Tribe developed proactive partnerships with a regional mobile provider for tower space utilization and mutually agreeable collocation rates; this partnership enabled both entities to expand coverage affordably and efficiently. In addition, the Tribe pursued site use partnerships where possible in exchange for service delivery to implement its neighborhood solution equipment to reach customers outside of the main network line of sight coverage areas. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | There are two sources for interconnection: XO Communications; and the Idaho Regional Optic Network for the Nez Perce Tribe's network. There are no other sources of interconnection available. | There are two transit agreements currently on the Nez Perce Tribe's network: Inland Cellular has contracted a dedicated 10 Mb path; and Education Networks of America has contracted a dedicated 3 Mbps path. QRO of Idaho had inquired about accessing bandwidth but no follow up occurred. The Nez Perce Tribe has not denied interconnection to any entitiy.
NT10BIX5570125 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 48240 | 0 | 0 | 0 | 756 | 378 | 47106 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | n/a | n/a
NT10BIX5570125 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | Broadband speeds have not increased since construction/deployment has not begun. | Price plans have not been provided since construction/deployment has not begun. | We have not begun providing service as construction/deployment has not begun. | N/A | 48240 | 0 | 0 | 0 | 756 | 378 | 47106 | N/A at this time as construction/deployment has not begun. | 0 | 0 | 0 | 0 | N/A as construction deployment has not yet begun. | N/A | An unforeseen obstacle with increased vendor demand as a result of these grant funded projects occurred which has an impact on the construction time line for the project. With all of these grant funded projects having similar time lines, acquiring the materials needed has been a challenge to the project. Many fiber vendors have stopped taking orders as the demand has exceeded their plants production ability. In many cases delivery forecast have gone out farther than anticipated by anyone, during the grant writing process. As a result, having your material orders in to the vendors as quickly as possible is about all you can do with the hope that the materials will come timely enough to allow the project to stay within the tight construction time frames outlined by the grant requirements. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | N/A | N/A
NT10BIX5570125 | 2012 | 37,695 | This is $38,090 under the Baseline Key Project Indicator of $75,785. Route improvements accounted for $17,347 of this difference. The remaining difference of $20,743 is because there were indirect costs included in the Baseline Key Project Indicator. | n/a | n/a | n/a | n/a | 0 | Still to be determined. Baseline was OC-12 Service offering. | n/a | n/a | 0 | Service has not been provided. Baseline was 45 Mbp/s. | n/a | n/a | n/a | Retail service is not currently being provided. | 7a. - Network management policies are currently displayed on our web page (Attachment - Acceptable Use Policy). 7b. - No. Our network is not operational as of 12/31/12. | n/a | 43304 | 1396 | 0 | 40642 | 75 | 0 | 1191 | n/a. We are not currently providing services. | 600 | 450 | 0 | 150 | We will have two collocation spaces that we will not own. The details are as follows: 1.) Location: 200 S. Virginia St, Reno, NV 89501 Owner: Basin Street Properties Interconnecting With: Zayo Enterprises Method fo Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to Zayo Fiber Optic Cables. 2.) Location: 210 Gardner St, Reno, NV 89501 Owner: California Broadband Cooperative (CBC) Interconnecting With: California Broadband Cooperative (CBC) Method fo Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to California Broadband Cooperative (CBC) Fiber Optic Cables. | n/a | None this year of that were out of the normal scopes of construction. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | 1.) Entered into: 0 2.) Negotiating: 2 3.) Denied: 0 | 1.) Entered into: 0 2.) Negotiating: 0 3.) Denied: 0
NT10BIX5570125 | 2013 | $47,164 | This is $28,621 under the Baseline Key Project Indicator of $75,785. Route improvements accounted for $17,347 of this difference. The remaining difference of $11,274 is because there were indirect costs included in the Baseline Key Project Indicator. | N/A | N/A | N/A | N/A | 1 GB | Baseline was OC-12 Service Offering. | N/A | N/A | 210 MB | 12 circuits. 7 Customers as of 12/31/213. | N/A | N/A | The average increase in broadband speed will be 294 Mb per CAI. Methodology used was (sum of new speeds (5,375 Mb) - sum of previous speeds (382.15)) / Total CAI's (17) | Retail services provided in 2013: 25 Mb Internet Access 40 Mb Internet Access 100 Mb Internet Access 100 Mb Internet Access Pricing plan info included in attachment. | 7a. - Network management policies are currently displayed on our web page (Attachment - Acceptable Use Policy) 7b. - No. | There have been no subscribers who have dropped our service. | 41953 | 2409 | 32 | 39512 | 0 | 0 | 0 | Zayo Group - 34 Miles. | 600 | 450 | 0 | 150 | We have two collocation spaces that we do not own. The details are as follows: 1.) Location: 200 S. Virginia St, Reno, NV 89501 Owner: Basin Street Properties Interconnecting With: Zayo Enterprises Method of Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to Zayo Fiber Optic Cables. 2.) Location: 210 Gardner St, Reno, NV 89501 Owner: California Broadband Cooperative (CBC) Interconnecting With: California Broadband Cooperative (CBC) Method of Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to California Broadband Cooperative (CBC) Fiber Optic Cables. | N/A | None this year that were out of the normal scopes of construction and Network Management. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | 1.) Entered into in 2013: 0 2.) Negotiating in 2013: 0 3.) Denied in 2013: 0 | 1.) Entered into in 2013: 0 2.) Negotiating in 2013: 0 3.) Denied in 2013: 0
NT10BIX5570126 | 2010 | $0.00 | N/A | $0.00 | N/A | $0.00 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A construction has not yet begun | N/A construction has not yet begun | N/A construction has not yet begun | N/A construction has not yet begun | 62174 | 0 | 0 | 0 | 4510 | 600 | 57064 | N/A construction has not yet begun | 0 | 0 | 0 | 0 | N/A construction has not yet begun | N/A construction has not yet begun | We cannot stress enough how important and valuable community outreach efforts have been. Our project is quite large encompassing fiber construction in 18 counties in California. We have conducted site visits and follow-up meetings at each of our 63 anchor institutions to determine cabinet locations, building entry points, and plans for route diversity where appropriate. We met with road authorities in each county and each city our project construction effects to identify the best route through each community to minimize disruption of roadways. Each authority has expressed a willingness to work together to simplify the right-of-way process. We also met with government leadership in all 18 counties and the individual communities to determine how our project could best meet their economic development needs. We have been met with great enthusiasm by each county and community because they realize the enormous value our project brings to their area. These meetings have allowed us to create a good working relationship with each anchor institution, county and community. The information gathered will aid in the detailed engineering process, minimize route changes that could effect environmental assessment, streamline right-of-way procurement processes and simplify eventual turn-up of services. | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | N/A | N/A
NT10BIX5570126 | 2011 | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 62174 | 0 | 0 | 0 | 4510 | 600 | 57064 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | 0 | 0 | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | We have entered into two wholesale service agreements with last mile ISP's, Sebastian Corp (DBA: Audeamus) and Sierra Tel Internet. We are negotiating 34 others. We have not received nor denied any other request for interconnection but since we are early in the construction phase, connection points are very limited at this time. | N/A
NT10BIX5570126 | 2012 | $53,025.81 | Slightly below the projected cost in the baseline. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 10Gbps | No change from baseline plan. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 1Gbps | Wholesale last mile provider bandwidth ranges from 100Mbps to 2.5Gbps. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. No CAI's have been turned-up. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | We have not implemented any policies that limit bandwidth beyond the service provided nor applied any traffic prioritization. We also will not filter, limit nor block consumers from accessing any lawful content, service, service provider, or application, or prevent any consumer from attaching any legal device to the network. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 62174 | 470 | 0 | 14400 | 4040 | 600 | 42664 | We have no wholesale dark fiber customers at this time. | 0 | 0 | 0 | 0 | Collocation space and fiber interconnection will be available for other providers at several "hub" locations across the project but these locations have not been established yet. Fiber interconnection will also be available at all of the proposed equipment cabinet locations. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | N/A | N/A
NT10BIX5570126 | 2013 | $74,668 | Higher than baseline plan due to construction challenges associated with rocky terrain in northern mountainous segments. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 10Gbps | No change from baseline plan. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 1Gbps | Wholesale last mile provider bandwidth ranges from 100Mbps to 10Gbps. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Public Safety Entities generally increase from current 100Mbps speeds to 1Gbps speeds. Libraries generally increase from current 10Mbps speeds to 1Gbps speeds. Community Colleges generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. County Offices of Education generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. California State Universities generally increase from current 1Gbps speeds to 10Gbps speeds with diverse routing. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | We have not implemented any policies that limit bandwidth beyond the service provided nor applied any traffic prioritization. We also will not filter, limit nor block consumers from accessing any lawful content, service, service provider, or application, or prevent any consumer from attaching any legal device to the network. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | 62174 | 2782 | 46 | 33760 | 1728 | 554 | 23304 | We have one wholesale dark fiber customer, Kings County Office of Education, who is leasing 46 miles. | 1080 | 278 | 34 | 768 | Collocation space and fiber interconnection is available for other providers at several "hub" locations across the project. Fiber interconnection is also available at all of the equipment cabinet locations. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | We entered into nine interconnection agreements and did not deny any request for interconnection. | We have one peering and transit agreement with the Corporation for Educational Network Initiatives in California (CENIC).
NT10BIX5570126 | 2014 | $83,635 | Higher than baseline plan due to construction challenges associated with rocky terrain in northern mountainous segments. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 10Gbps | No change from baseline plan. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 1Gbps | Wholesale last mile provider bandwidth ranges from 100Mbps to 10Gbps. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Public Safety Entities generally increase from current 100Mbps speeds to 1Gbps speeds. Libraries generally increase from current 10Mbps speeds to 1Gbps speeds. Community Colleges generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. County Offices of Education generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. California State Universities generally increase from current 1Gbps speeds to 10Gbps speeds with diverse routing. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | We have not implemented any policies that limit bandwidth beyond the service provided nor applied any traffic prioritization. We also will not filter, limit nor block consumers from accessing any lawful content, service, service provider, or application, or prevent any consumer from attaching any legal device to the network. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | 52644 | 3818 | 46 | 48780 | 0 | 0 | 0 | We have one wholesale dark fiber customer, Kings County Office of Education, who is leasing 46 miles. | 1080 | 278 | 34 | 768 | Collocation space and fiber interconnection is available for other providers at several "hub" locations across the project. Fiber interconnection is also available at all of the equipment cabinet locations. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | We entered into ten interconnection agreements and did not deny any request for interconnection. | We have one peering and transit agreement with the Corporation for Educational Network Initiatives in California (CENIC).
NT10BIX5570127 | 2010 | 0 | N/At | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | Not providing any services at this time. | Not providing any services at this time. | Not providing services at this time. | 14000 | 0 | 0 | 0 | 4000 | 0 | 10000 | Zero at this time. | 0 | 0 | 0 | 0 | N/A | N/A | None at this time | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | N/A | N/A
NT10BIX5570127 | 2011 | 147368 | This is consistent with the baseline plan. | 0 | N/A | 0 | N/A | 10 Gbps | This is consistent with the baseline plan. | 0 | N/A | 10 Mbps | This is lower than anticipated in the baseline plan. Cost is the most prohibiting factor for most CAI's. | 0 | N/A | Average increase in broadband speed estimated from existing T1 services (1.544Mbps) to an average connection speed of symmetrical 10 Mbps provided with fiber. This is 6.5 times faster. This was calculated by dividing 10 by 1.544. | UTOPIA does not provide retail services. UTOPIA is a government agency and operates an open access network wholesaling end to end transport services to various retail service providers. As a government agency, UTOPIA can also provide wholesale services directly to other government entities. Please see service offering attachment for details. | All network devices are managed by UTOPIA on a separate VLAN that is not customer or edge accessible. UTOPIA uses 802.1p prioritization tagging at customer sites to identify the priority of customer traffic based on the type of circuit that is ordered, giving priority to traffic in the following order from highest to lowest: Management, Public Safety/Security, Business Gold/TLS, Voip, IPTV, Business Data, Residential Data. Traffic queues are implemented on aggregation and core devices to enforce traffic priorities. All aggregation links and devices are actively monitored and upgraded when link capacity reaches 60% utilization at 95% percentile statistical useage. We have cooperated with FBI lawful interception requests. We also notify customers of copyright infringement complaints but do not actively block or disconnect customers from accessing unlawful content. | No subscribers have dropped the broadband service provided through this project. | 28212 | 1028 | 0 | 343 | 20131 | 0 | 6710 | None | 720 | 720 | 0 | 0 | We are extending our existing network using BTOP funds and do not have collocation space allocated in our BTOP project. However, our existing network does contain collocation space where we interconnect with providers and customers and in some cases we interconnect with the providers in their collocation facilities. | None have been made. | In UTOPIA's case, we are focused on providing network connectivity to many different public safety agencies. We have benefited by working closely with local government entities to form public safety partnerships. These partnerships have begun to increase collaborative use and help in the development of various uses of the network. | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | Zero new agreements, 3 agreements in negotiation, No requests have been denied. | N/A
NT10BIX5570127 | 2012 | 109142 | This is consistent with the baseline plan. | 0 | N/A | 0 | N/A | 10 Gbps | This is consistent with baseline plan. | 0 | N/A | 10 Mbps | This is lower than anticipated in the baseline plan. Cost is the most prohibiting factor for most CAI's. | 0 | N/A | Average increase in broadband speed estimated from existing T1 services (1.544Mbps) to an average connection speed of symmetrical 10 Mbps provided with fiber. This is 6.5 times faster. This was calculated by dividing 10 by 1.544. | UTOPIA does not provide retail services. UTOPIA is a government agency and operates an open access network wholesaling end to end transport services to various retail service providers. As a government agency, UTOPIA can also provide wholesale services directly to other government entities. Please see service offering attachment for details. | All network devices are managed by UTOPIA on a separate VLAN that is not customer or edge accessible. UTOPIA uses 802.1p prioritization tagging at customer sites to identify the priority of customer traffic based on the type of circuit that is ordered, giving priority to traffic in the following order from highest to lowest: Management, Public Safety/Security, Business Gold/TLS, Voip, IPTV, Business Data, Residential Data. Traffic queues are implemented on aggregation and core devices to enforce traffic priorities. All aggregation links and devices are actively monitored and upgraded when link capacity reaches 60% utilization at 95% percentile statistical useage. We have cooperated with FBI lawful interception requests. We also notify customers of copyright infringement complaints but do not actively block or disconnect customers from accessing unlawful content. | No subscribers have dropped the broadband service provided through this project. | 28212 | 11009 | 0 | 3670 | 10150 | 0 | 3383 | N/A | 3840 | 3840 | 0 | 0 | We are extending our existing network using BTOP funds and do not have collocation space allocated in our BTOP project. However, our existing network does contain collocation space where we interconnect with providers and customers and in some cases we interconnect with the providers in their collocation facilities. | None have been made. | In UTOPIA's case, we are focused on providing network connectivity to many different public safety agencies. We have benefited by working closely with local government entities to form public safety partnerships. These partnerships have begun to increase collaborative use and help in the development of various uses of the network. | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | Two new agreements, One in negotiation, Zero denied | N/A
NT10BIX5570127 | 2013 | $61,851 | This is consistent with the baseline plan | 0 | N/A | 0 | N/A | 10 Gbps | This is consistent with the baseline plan | 0 | N/A | 10 Mbps | This is lower than anticipated in the baseline plan. Cost is the most prohibiting factor for most CAI's | 0 | N/A | Average increase in broadband speed estimated from existing T1 services (1.544Mbps) to an average connection speed of symmetrical 10 Mbps provided with fiber. This is 6.5 times faster. This was calculated by dividing 10 by 1.544. | UTOPIA does not provide retail services. UTOPIA is a government agency and operates an open access network wholesaling end to end transport services to various retail service providers. As a government agency, UTOPIA can also provide wholesale services directly to other government entities. Please see service offering attachment for details. | All network devices are managed by UTOPIA on a separate VLAN that is not customer or edge accessible. UTOPIA uses 802.1p prioritization tagging at customer sites to identify the priority of customer traffic based on the type of circuit that is ordered, giving priority to traffic in the following order from highest to lowest: Management, Public Safety/Security, Business Gold/TLS, Voip, IPTV, Business Data, Residential Data. Traffic queues are implemented on aggregation and core devices to enforce traffic priorities. All aggregation links and devices are actively monitored and upgraded when link capacity reaches 60% utilization at 95% percentile statistical useage. We have cooperated with FBI lawful interception requests. We also notify customers of copyright infringement complaints but do not actively block or disconnect customers from accessing unlawful content. | No subscribers have dropped the broadband service provided through this project. | 26265 | 26265 | 0 | 0 | 0 | 0 | 0 | N/A | 7320 | 7320 | 0 | 0 | We are extending our existing network using BTOP funds and do not have collocation space allocated in our BTOP project. However, our existing network does contain collocation space where we interconnect with providers and customers and in some cases we interconnect with the providers in their collocation facilities. | None have been made. | In UTOPIA's case, we are focused on providing network connectivity to many different public safety agencies. We have benefited by working closely with local government entities to form public safety partnerships. These partnerships have begun to increase collaborative use and help in the development of various uses of the network. | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | N/A | N/A
NT10BIX5570128 | 2010 | 0 | Not yet deployed | 0 | N/A | 0 | N/A | 0 | Not yet deployed | 0 | N/A | 0 | Not yet deployed | 0 | N/A | N/A | N/A | N/A | N/A | 72793 | 0 | 0 | 0 | 34940 | 0 | 37853 | N/A | 0 | 0 | 0 | 0 | N/A not yet deployed | N/A | N/A | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | N/A | N/A
NT10BIX5570128 | 2011 | [REDACTED] | Based on miles deployed (273) divided by budget cost classification number nine (9) - Construction. Average cost per mile is below the Baseline Projections. Although 273 miles have been constructed only 34.7% or approximately 95 miles have been activated. Additional construction cost will be incurred once the remaining miles are activated. | 0 | Not applicable. | 0 | Not applicable. | 1 Gbps | [REDACTED] | 0 | Not applicable. | 10.82 Mbps | 1 Mbps â€“ 1 Gbps are available. | 0 | Not applicable. | The actual increase per customer would be difficult to calculate because SmartBand would only increase speed based on customer request. Additionally, previous bandwidth speeds are not always known. The biggest improvement is the physical connection itself. Previously most of the physical connections in our service area were limited to 100 Mbps per second. Today all new connections and any upgraded connections will have capacity to receive 1 Gbps or 10 times most previous connections. Listed below are the known broadband speed increases since the CAIâ€™s direct connection to the network: Original SB Connection Upgraded -Local School System 10 Mbps 20 Mbps -Local School System 50 Mbps 100 Mbps | Service offerings include: -Switched Ethernet 10 Mbps to 1000 Mbps -Internet Access 1 Mbps to 1000 Mbps | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream internet service providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other middle mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where are available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | Not applicable. | 74830 | 782 | 2037 | 33421 | 34158 | 0 | 4432 | Not applicable. | 3340 | 2348 | 18 | 974 | Not applicable. | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED]
NT10BIX5570128 | 2012 | [REDACTED] | Based on route miles deployed 424.38 divided by budget cost classification number nine (9) - Construction. Average cost per mile is below the Baseline Projections. Although 424.38 route miles have been constructed, only 90% or approximately 382.08 miles have been activated. Additional construction cost will be incurred once the remaining miles are activated. | 0 | Not Applicable | 0 | Not Applicable | 1 Gbps | [REDACTED] | 0 | Not Applicable | [REDACTED] | [REDACTED] | 0 | Not Applicable | [REDACTED] | Service offerings include: -Switched Ethernet 10 Mbps to 1000 Mbps -Internet Access 1 Mbps to 1000 Mbps See attached pricing schedule. | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream Internet Service Providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other Middle Mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | Not Applicable | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | Not Applicable | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | Not Applicable | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED]
NT10BIX5570128 | 2013 | [REDACTED] | [REDACTED] | 0 | Not Applicable. | 0 | Not Applicable. | 100Gbps | [REDACTED] | 0 | Not Applicable. | 58.43Mbps | [REDACTED] | 0 | Not Applicable. | [REDACTED] | Service offerings include: -Switched Ethernet 10 Mbps to 10,000 Mbps -Internet Access 1 Mbps to 10,000 Mbps See attached pricing schedule. | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream Internet Service Providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other Middle Mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | [REDACTED] | 74830 | 19712 | 2037 | 53081 | 0 | 0 | 0 | Not Applicable. | 3340 | 2348 | 18 | 974 | Not Applicable. | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED]
NT10BIX5570129 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A
NT10BIX5570129 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A
NT10BIX5570129 | 2012 | $29,000 | No variance | 0 | N/A | 0 | N/A | 1 Gbps | No variance | 0 | N/A | 100 Mbps | No variance | 0 | N/A | N/A | N/A | N/A | N/A | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 4500 | 2250 | 0 | 2250 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A
NT10BIX5570129 | 2013 | $43,577 | Variance from baseline from reduced original network mileage and increased cost from rock encountered during underground construction. | 0 | N/A | 0 | N/A | 1 Gbps | No variance | 0 | N/A | 100 Mbps | No variance | 0 | N/A | N/A - Rockbridge Area Network Authority (RANA) will not be providing any services to the end-users. RANA will sell wholesale services to service providers that will then offer services to the end-users. | N/A - Rockbridge Area Network Authority (RANA) will not be providing any services to the end-users. RANA will sell wholesale services to service providers that will offer services to the end-users. | Rockbridge Area Network Authority (RANA) limits the total bandwidth that the service provider can transport over the network for a certain monthly cost. If the service provider needs more bandwidth then they can upgrade their transport bandwidth. RANA has not limited or blocked end-users or service providers from accessing any lawful content. | 0 | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 4500 | 2250 | 0 | 2250 | N/A | N/A | Please start early on community support and planning for marketing the new network. Our operating expenses were higher than anticipated in early project planning, but with the steady increase in network users, they are predicted to level out after the first year of operation. | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A
NT10BIX5570130 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | 7a. Network Management policies are being developed and will be completed in April, 2011. 7b. N/A | N/A. Awaiting approval of Environmental Assessment | 140474 | 0 | 0 | 0 | 107210 | 16632 | 16632 | N/A | 0 | 0 | 0 | 0 | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | N/A | N/A
NT10BIX5570130 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | No variance | 1Gbps | No variance | 0 | N/A | 0 | N/A | The broadband speeds have not increased since construction/deployment has not begun | Pricing plans have not been provided, since construction/deployment have not begun | Network Management policies have not been provided, since the network has not begun providing services. | N/A | 140474 | 0 | 336 | 2016 | 107210 | 16632 | 16632 | We are currently proposing to lease dark fiber to the Alabama Department of Homeland Security and Emergency Management. | 0 | 0 | 0 | 0 | The network will collocate equipment within the following service provider interconnect locations: (1) Level 3 Communication's Marion Junction, AL Regeneration Facility , (2) Earthlink/Deltacom's Carrier Hotel in Montgomery, AL, (3) Atlanta's 55 Marietta Street Carrier Hotel, and (4) Level 3 Communication's Mobile, AL Carrier Hotel. The network has 31 terminals located throughout the footprint; any terminal can be used for incumbent service providers to interconnect to the network. This includes but not limited to Pinebelt Telephone, Hayneville Telephone, Frontier Com,, Magnolia Bell, etc. | A2D, Inc. is a small business that meets the requirements of SDB. A2D, Inc is the sub-recipient. Other SDB contractors include Concise and GlobaServe | 1) For an underground burial network, a significant amount of extra effort and resource allocation needs to go into utility data collection in rural demographics. We found that between severe lack of utility data by local municipalities and lack of utility locating services a significant amount of additional time, effort and resources went toward our GPS locate/permitting tasks. 2) The awareness of Broadband as a utility model versus and Service Provider model is much needed in the municipal sector so as to educate them on the legislative differences, as it relates to franchise fees, right of ways and etc. Trillion does not underestimate the amount of up front municipal understanding and support required to successfully advance this project. | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | Five (5) Interconnection Agreements are currently under negotiation. We have not denied any requests for interconnection. | One (1) Peering and Transit Agreement is currently negotiation. We have not denied any requests for Peering or Transit Interconnection
NT10BIX5570130 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No Variance | 1Gbps | No Variance | 1Gbps | No Variance | 5Mbps | No Variance | The broadband speeds have not increased since the network construction and deployment effort have just began. | Pricing Plans were submitted to NTIA and NOAA during the July 2012 CAP Responses. The Plans covered potential revenue streams from Community Anchor Institutes and Businesses that were to be served in the project area. | 7a. No Network Management Policies are in place at this time. 7b. Construction of the network has terminated. Therefore, no services are provided. | N/A | 140474 | 0 | 0 | 0 | 107210 | 16632 | 16632 | N/A | 0 | 0 | 0 | 0 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No co-location sites in place. | Since the projectâ€™s inception, A2D served as a Sub-Recipient and was also a small business that met the requirements of SDB. Other disadvantaged Small Businesses involved in the project as contractors included Concise Communications and GlobalServe. | N/A | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned. | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned.
NT10BIX5570130 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | Project was terminated | 1Gbps | Project was terminated | 1Gbps | Project was terminated | 5Mbps | Project was terminated | The broadband speeds have not increased since the network construction and deployment effort have just began. | Project was terminated | Project was terminated | N/A | 140474 | 0 | 0 | 0 | 107210 | 16632 | 16632 | N/A | 0 | 0 | 0 | 0 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No co-location sites in place. | Since the projectâ€™s inception, A2D served as a Sub-Recipient and was also a small business that met the requirements of SDB. Other disadvantaged Small Businesses involved in the project as contractors included Concise Communications and GlobalServe. | N/A | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned. | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned.
NT10BIX5570131 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | 1 GIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No Anchor Institutions have been connected to our network yet. There is no increase in broadband speed to report at this time. | No retail services are being provided at this time. | No network management policies are in place at this time. Pricing and policy development are on hold pending federal approval of our environmental assessment. | No subscribers are connected to our network yet, as construction is on hold pending federal approval of our environmental assessment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We currently have no wholesale dark fiber customers and are not anticipating any with this project. | 0 | 0 | 0 | 0 | We have not yet constructed any facilities pending federal approval of our environmental assessment. | We have not issued any subcontracts or subgrants. | Start the environmental assessment process as early as possible. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | N/A | N/A
NT10BIX5570131 | 2011 | 32036.40 | N/A | N/A | N/A | N/A | N/A | 10 Gig | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | We plan to provide ethernet services at speeds from 10 Meg to 10 Gig. | We have a network management policy posted on our website at www.peoplescom.net. We have never, nor do we ever intend to, block consumers from accessing anything noted above nor will we prevent them from attaching any legal device to the network. | N/A | 73095 | 5956 | 0 | 0 | 67139 | 0 | 0 | We do not intend to wholesale dark fiber. | 0 | 0 | 0 | 0 | We have provided hand-holes approximately every mile for Last Mile provider interconnection to our network and to their customers. We do not contemplate leasing floor space in any of our cabinets or offices. We have terminal space in a carrier hotel in Dallas and access to one in Longview. Each of these places has extensive interconnection capabilities in various meet points. | N/A | Order fiber optic cable ahead of schedule. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | One interconnection agreement was procured during 2011. We are currently negotiating 5 additional agreements. We have not denied any requests for interconnection and am, in fact, actively seeking interconnection with last mile providers. | None.
NT10BIX5570131 | 2012 | 47,269.22 | Average cost per mile includes fiber and construction costs, but engineering fees were not included when calculating this figure. | N/A | N/A | N/A | N/A | 10 Gig | N/A | N/A | N/A | 252 Meg | N/A | N/A | N/A | The average increase in broadband speed is not available at this time. | Peoples offers ethernet services at speeds from 10 Meg to 10 Gig. | Currently, voice is prioritized throughout our network. We are presently developing a bandwidth prioritization schedule for medical and healthcare providers' traffic as well. We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal devices to the network. | We have had no subscribers drop the bandwidth service provided through this project. | 44822 | 44822 | 0 | 0 | 40608 | 0 | 0 | We do not intend to wholesale dark fiber. | 0 | 0 | 0 | 0 | We have provided hand-holes approximately every mile to connect to ISPs, Last Mile Providers and end users to the fiber. We do not contemplate leasing floor space or space in any of our cabinets or offices. We have terminal space in a "carrier hotel" in Dallas and access to one in Longview. Each of these places has extensive interconnection capabilities for many carriers. | N/A | It is always prudent to order fiber optic cable ahead of schedule. In addition, do detailed engineering on routes early in the project so route changes have time to get through extremely long approval cycles. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | We are providing data interconnection with one wireless private network provider interfacing to over 50 schools in Region 8. We are also providing fiber interconnection for seven small regional ISPs. We have twelve points of interconnection with Verizon through a SuddenLink cable TV subsidiary and several points of interconnection to a WISP known as Peoples Wireless. We have not denied any requests for interconnection. | We are providing internet to two ILECs in the area as network peers. We have not denied any requests for peering or transit agreements.
NT10BIX5570131 | 2013 | 55,309 | Average cost per mile includes fiber and construction costs, but engineering fees were not included when calculating this figure. | N/A | N/A | N/A | N/A | 10 Gig | N/A | N/A | N/A | 187 | N/A | N/A | N/A | N/A | Peoples offers ethernet services at speeds from 10 Meg to 10 Gig. | Currently, voice is prioritized throughout our network. We are presently developing a bandwidth prioritization schedule for medical and healthcare providers' traffic as well. We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal devices to the network. | One last mile provider dropped their service due to financial difficulties. No other subscribers have dropped their broadband service. | 82721 | 82541 | 180 | 0 | 0 | 0 | 0 | We do not have any dark fiber customers, nor do we intend to wholesale dark fiber. | 0 | 0 | 0 | 0 | We have provided hand-holes approximately every mile to connect to ISPs, Last Mile Providers and end users to the fiber. We do not contemplate leasing floor space or space in any of our cabinets or offices. We have terminal space in a "carrier hotel" in Dallas and access to one in Longview. Each of these places has extensive interconnection capabilities for many carriers. | N/A | It is always prudent to order fiber optic cable ahead of schedule. In addition, do detailed engineering on routes early in the project so route changes have time to get through extremely long approval cycles. Contact municipalities early in the project. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | We are providing data interconnection with one wireless private network provider interfacing to over 50 schools in Region 8. We are also providing fiber interconnection for seven small regional ISPs and four wireless operators. We have twelve points of interconnection with Verizon through a SuddenLink cable TV subsidiary and several points of interconnection to a WISP known as Peoples Wireless. We have not denied any requests for interconnection. Overall, we have added broadband to or increased the broadband speeds of 51 communities and increased the number of broadband providers in our area to encourage competition. Building to last mile providers also increased access to and current speeds of countless other communities as we also provide access to lower cost bandwidth for these carriers. Our future plans include developing the area's medical network to allow telemedicine in rural areas that desperately need it. | We are providing internet to two ILECs in the area as network peers. We have not denied any requests for peering or transit agreements.
NT10BIX5570132 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, however due to the increased demand for bandwidth; the DPI system will be brought back online in 2011 with the intention of prioritizing certain applications over others on our wireless access networks only. In managing our network through traffic prioritization, we intend to give a lower priority to peer to peer file sharing traffic and other traffic that does not noticeably impair our customer experience. Though a lower priority will be given to certain applicati | N/A | 18161 | 0 | 0 | 0 | 0 | 0 | 18161 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | N/A | N/A
NT10BIX5570132 | 2011 | 0 | Minimal construction was completed as of 12/31/11. Only 15.5 miles of duct (with only 5 miles of fiber cabling) was placed as of the end of the year therefore an accurate average cost per mile could not be calculated. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. At this time ENMR-Plateau does not prioritize any network traffic and at no time will we block access to any lawful content, service, service provider, or application. | N/A | 15615 | 0 | 0 | 0 | 15615 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of Plateauâ€™s Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to Plateauâ€™s POI building. This fiber splice would connect the network providerâ€™s fiber to Plateauâ€™s single-mode fiber entering the building and terminating on Plateauâ€™s optical equipment. This enables optical level interconnection between the other network providerâ€™s optical equipment and Plateauâ€™s. Interconnections with customers of Plateauâ€™s services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) 0, (2) 0, (3) ENMR-Plateau has not denied any requests for interconnection during this reporting period. | N/A
NT10BIX5570132 | 2012 | $75,921.99 | Total cost of construction divided by the number of fiber miles constructed as of 12/31/12. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 0 | No CAIs have been connected as of 12/31/12. | 0 | N/A | N/A | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 15615 | 12997 | 0 | 0 | 2618 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) ENMR Telephone Cooperative has entered into 1 new interconnection agreement this annual reporting period with Conterra Ultra Broadband, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A
NT10BIX5570132 | 2013 | $78,300.09 | Total cost of construction divided by the number of fiber miles constructed as of 7/31/13, the project's end date. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 0 | Even though all 369 CAI's had been connected as of 7/31/13, none were being provided with service by ENMR Telephone Cooperative at that time. | 0 | N/A | N/A | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | No CAI subscribers were activated for service by the end date of 7/31/13. | 15615 | 15615 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) ENMR Telephone Cooperative has entered into 3 new interconnection agreements this annual reporting period with Verizon Wireless, North Central Economic Development and Northern New Mexico Telecom, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A
NT10BIX5570133 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 92128 | 0 | 0 | 0 | 76989 | 15139 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | N/A | N/A
NT10BIX5570133 | 2011 | 37759 | Baseline=$35,168. As of December 31 we have a relatively small amount of new miles completed upon which to compute an average cost. A disproportionately high amount of buried construction in the sample compared to the overall new build to be completed tends to increase the average cost compared to the baseline plan. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 2.5 times their current capacity. Calculated as follows - one CAI went from 45 Mbit/s to 150 Mbit/s, the other doubled their capacity by adding a second link. Two customers have been connected but are not yet receiving service. | N/A | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)ION has not limited or blocked consumers from accessing the network. | N/A | 96885 | 18192 | 0 | 0 | 63554 | 15139 | 0 | N/A | 0 | 0 | 0 | 0 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | N/A | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1)Four agreements entered. (2)Thirteen agreements being negotiated. (3) No request for interconnection has been denied. | N/A
NT10BIX5570133 | 2012 | 38817 | Baseline=35,168. For various reasons there have been more buried fiber miles than originally planned. Also, make ready costs have been greater per mile than anticipated. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 4 times their current capacity. Calculated based on sampling of connected CAI's where we are aware of the speed of their prior broadband service. | ION provides only wholesale services. The Development Authority of the North Country primarily sells wholesale services, however, we do have two retail Healthcare networks to which we are providing retail services. Service is Ethernet transport between healthcare sites with a shared internet component. Prices are $600 for 10 Mbps, $2,268 for 100 Mbps, and $3,218 for 1 Gbps circuits. | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)As a wholesale service provider we do not rate limit or block any lawful content or service provider on the network. We do have several methods for prioritization of traffic, however, we have not had any customer requests to do that at this time. | N/A | 96939 | 54214 | 0 | 0 | 25009 | 17716 | 0 | N/A | 0 | 0 | 0 | 0 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | 1. Engage pole owners early in process and frequently to avoid delays in make ready work. 2. Use the same architectural and engineering firm(s) throughout the project to build a high level of knowledge of the project and to minimize re-work. 3. Proactively engage local government, economic development agencies, chambers of commerce and industrial development agencies before project implementation to gain feedback on local needs. 4. Publish a newsletter to inform the communities of all aspects of the project. 5. Communicate with state broadband and technology office proactively providing them maps and updates of project progress and availability. 6. Continue to engage the Environmental Agencies as necessary throughout the project, paying close attention to any Special Award Conditions that were identified during the award phase. | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1) 10 agreements entered. (2) 8 agreements being negotiated. (3) No request for interconnection has been denied. | N/A
NT10BIX5570133 | 2013 | 39,455 | Baseline=35,168. For various reasons there have been more buried fiber miles than originally planned. Also, make ready costs have been greater per mile than anticipated. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 4 times their current capacity. Calculated based on sampling of connected CAI's where we are aware of the speed of their prior broadband service. | ION provides only wholesale services. The Development Authority of the North Country primarily sells wholesale services, however, we do have two retail Healthcare networks to which we are providing retail services. Service is Ethernet transport between healthcare sites with a shared internet component. Prices are $600 for 10 Mbps, $2,268 for 100 Mbps, and $3,218 for 1 Gbps circuits. | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)As a wholesale service provider we do not rate limit or block any lawful content or service provider on the network. We do have several methods for prioritization of traffic, however, we have not had any customer requests to do that at this time. | N/A | 91795 | 91795 | 0 | 0 | 0 | 0 | 0 | N/A | 2950 | 2950 | 0 | 2950 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | 1. Engage pole owners early in process and frequently to avoid delays in make ready work. 2. Use the same architectural and engineering firm(s) throughout the project to build a high level of knowledge of the project and to minimize re-work. 3. Proactively engage local government, economic development agencies, chambers of commerce and industrial development agencies before project implementation to gain feedback on local needs. 4. Publish a newsletter to inform the communities of all aspects of the project. 5. Communicate with state broadband and technology office proactively providing them maps and updates of project progress and availability. 6. Continue to engage the Environmental Agencies as necessary throughout the project, paying close attention to any Special Award Conditions that were identified during the award phase. | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1) 29 agreements entered. (2) 0 agreements being negotiated. (3) No request for interconnection has been denied. | N/A
NT10BIX5570135 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No community anchor were connected during this reporting period | N/A | 7a.No network management policies exist that impact consumer access. Commercial access to the One Maryland Broadband Network infrastructure is limited to wholesale, dark fiber lease, over which each access seeker will be able to implement network management policies according to their own requirements. 7b. N/A | 0-percent | 153201 | 0 | 0 | 0 | 97383 | 3000 | 52818 | None this reporting period | 0 | 0 | 0 | 0 | Network providers and/or customers can access One Maryland Broadband Network dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | - The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 2) Closely coordinate with your Federal Program Officer on all challenges. 3) Reach out to the vendor community via a vendor fair to ensure open and competitive procurement, as well as to efficiently disseminate relevant information regarding Program requirements, limitations, and opportunities 4) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. 5) Centralize accounting and reporting functions among multiple sub recipients to the greatest degree possible, thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 0 2) We are currently finalizing an interconnection agreement with the Maryland Broadband Cooperative, who will become a sub-recepient of the grant and will leverage fiber infrastructure constructed by the Project to provide a range of middle mile commercial services. 3) No request for interconnection have been denied. | N/A
NT10BIX5570135 | 2011 | $79,277 | Our baseline is $72,181. We are confident that our trend will keep us well within budget. The ICBN sub recipient has averaged $61,815 per mile. This average was brought up by the DOIT portion of the project, which averaged $98,510. This latter number is not indicative of a trend as it represents all underground construction and was awarded on the previous Stateâ€™s Cable & Wire contract, which had a limited number of vendors cable of work on this scale. The Cable & Wire contract has since been re-competed and re-issued. New awards are coming in under our baseline. | 0 | N/A | 0 | N/A | 10Gbps | This the planned back haul speed. | 0 | N/A | 1Gbps | This is the average broadband speed for middle mile. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. The other 9 CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 908Mbps. | N/A | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 234796 | 1638 | 1684 | 0 | 97597 | 53662 | 80215 | 0 | 5860 | 3400 | 330 | 2130 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Closely coordinate with your Federal Program Officer on all challenges. 2) Take advantage and attend all BTOP/NTIA drop-in calls and conferences, ensure that BTOP updates are shared with the compliance team ensuring compliance cohesiveness. 3) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 4) Mitigate some of the risk by the centralizing accounting and reporting functions thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. 5) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 8 2) We currently are negotiating 12 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A
NT10BIX5570135 | 2012 | $76,629 | Our baseline is $72,181. The ICBN sub recipient has averaged $79,372 per mile. The DOIT portion of the project, which averaged $72,559. We are confident that our trend will keep us well within budget, since most of the remaining work is aerial construction, which is less costly than our underground construction cost. | 0 | N/A | 0 | N/A | 40Gbps | 40Gbps is the maximum advertised broadband speed. | 0 | N/A | 1Gbps | 1Gbps is the average broadband speed for middle mile. We offer the following speed tiers 10Mgps, 100Mgps, 1Gbps, 10Gbps and 40Gbps. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. All the other CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 996.9Mbps. | Not providing retail services. | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 244024 | 3828 | 1466 | 0 | 100596 | 55413 | 82721 | 0 | 5860 | 3400 | 330 | 2130 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. Baytek is an engineering subcontractor for DoIT Mack Communication is an engineering subcontractor for both ICBN & DoIT CTC is an engineering subcontractor for ICBN | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Closely coordinate with your Federal Program Officer on all challenges. 2) Take advantage and attend all BTOP/NTIA drop-in calls and conferences, ensure that BTOP updates are shared with the compliance team ensuring compliance cohesiveness. 3) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 4) Mitigate some of the risk by the centralizing accounting and reporting functions thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. 5) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 8 2) We currently are negotiating 42 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A
NT10BIX5570135 | 2013 | $86,235 | Final average cost per new mile | 0 | N/A | 0 | N/A | 40Gbps | 40Gbps is the maximum advertised broadband speed. | 0 | N/A | 1Gbps | 1Gbps is the average broadband speed for middle mile. We offer the following speed tiers 10Mgps, 100Mgps, 1Gbps, 10Gbps and 40Gbps. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. All the other CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 996.9Mbps. | Not providing retail services. | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 203650 | 88696 | 53824 | 61130 | 0 | 0 | 0 | 0 | 6760 | 3900 | 330 | 2530 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. Baytek is an engineering subcontractor for DoIT Mack Communication is an engineering subcontractor for both ICBN & DoIT CTC is an engineering subcontractor for ICBN | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: As a state government agency with sub recipients of different types, there were a number of lessons that we learned along the way. The first lesson and most important is that we cannot do this project alone. We needed the help and collaboration of many of the state and local government agencies to get this done. Some of the relationships were not developed ahead of time so we had to create them as needed. The second, is that things will take longer to get done, than the forms or guidance says it will. Time must always be allotted for people and agencies to do their work and then get it back to you. The third, make sure to pay attention to and attend the webinars and circulars that are put out by the respective agencies for your project. The information can be invaluable in helping get through the project. Lastly, make sure to build a strong relationship with your federal officers on the project. As we faced challenges and successes on this project, the relationship with our team helped us to navigate the changes and move forward. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 12 2) We currently are negotiating 56 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A
NT10BIX5570136 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | As construction has not started, an average increase estimated would be from a T1 (1.5 Mbps), which most community anchor institutions currently utilize, to having access to a 100 Mbps drop as a result of this project. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET will have customer interconnection available on every tower, monopole and roof mount installed. Collocation space varies per Backbone or Node location, and the actual amount will be calculated when construction begins. Other network providers will be able to connect with this network at any of the equipment shelters or cabinet area drop points in the rural communities. GovNET operates as a 'carrier's carrier' and welcomes any interest in interconnection. | GovNET has issued one vendor project contract to date - the Environmental Assessment - and it was to a Woman-owned business named "Tierra Right of Way" from Tucson Arizona. | Be lucky enough to be assigned to a Federal Program Officer like Mary Rudokas (and the assistance of Norman Davis, BAH)! Her knowledge and suggestions have been instrumental for a first-time federal grantee. The BTOP Handbook is very well put together and an excellent reference utilized often. The Compliance Conference in November 2010 was very valuable to meet other recipients and network together. | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | Currently negotiating with two (2) last mile providers for interconnection. | Currently negotiating a Peering Agreement with Level 3.
NT10BIX5570136 | 2011 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 0 | n/a | 0 | n/a | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. | 0 | n/a | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. | 0 | n/a | Construction has not begun. However, we expect the average increase in broadband speed will increase from a T1 (1.5 Mbps) to a 100 Mbps drop as a result of this project. Most Community Anchor Institutions currently utilize 1.5 Mbps broadband speed. | n/a | We have not begun providing service due to the delay in EA approval. GovNET received its FONSI in November 2011 and construction activities are now underway. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - We do not have a fiber project. | 0 | 0 | 0 | 0 | Collocation space varies per backbone or node location. GovNET has conducted a significant amount of public outreach to develop partnerships for interconnection. Customers will be able to interconnect through almost every tower, monopole and roof mount installed through this project. Other network providers will be able to connect to the network at a majority of the equipment shelters or cabinet area drop points in the rural communities included in the network. | GovNET has issued two vendor contracts to women-owned businesses: 1. A contract with Kestrel Consulting Inc. of Hood River, Oregon, was signed in January 2011 for grant management services. 2. A contract with Tierra Right of Way Services of Tucson, Arizona, was signed in November 2010 for preparation of the Environmental Assessment. | The learning curve that went into completing the Environmental Assessment was significant and in retrospect, having a team who is aggressive on working through the detailed items to achieve FONSI is critical. It may be helpful to be directly connected with other projects that the FPO's may see similar issues so as to have someone to bounce ideas off that could benefit both projects, as often each project is an island in their own state. | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | We signed zero agreements last mile providers for interconnection. We have not denied any request for interconnection. | We signed two peering agreements for 2 Gigabytes of Tier One Internet access with a provider.
NT10BIX5570136 | 2012 | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | 0 | n/a | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | Connection to Community Anchor Institutions had not yet occurred in 2012. However, we expect the average increase in broadband speed will increase from a T1 (1.5 Mbps) to access to 100 Mbps capability as a result of this project. | n/a | Network is not yet active. | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET currently has towers available for collocation space, but no equipment shelters yet installed on the sites prior to suspension. The amount of available space varies per backbone or node location. GovNET has conducted a significant amount of public outreach to develop partnerships for interconnection. Other network providers will be able to interconnect through almost every tower, monopole and roof mount installed as Community Interconnect Points in the rural communities included in the network. | No subcontracts were made in 2012 to SDBs. | n/a | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | There were no interconnection agreements signed in 2012, although three (3) agreements were being negotiated. GovNET has not denied any requests for interconnection. | GovNET entered into two (2) peering agreements with a provider for 2 Gbps for Tier One internet.
NT10BIX5570136 | 2013 | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | 0 | n/a | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | We expect the average increase in broadband speed will increase from 1.5 - 10 Mbps to access to over 100Mbps - 1Gbps capability as a result of this project. | n/a | Network is not fully active yet. | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET owns collocation space, and will have towers and cabinet space available for collocation. | No subcontracts were made in 2013 to SDBs. | n/a | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | Due to project suspension and lift occurring in September 2013, here were no interconnection agreements signed in 2013, although two (2) agreements were being revived and negotiated. GovNET has not denied any requests for interconnection. | GovNET had entered into two (2) peering agreements with a provider for 2 Gbps for Tier One internet, which were terminated due to suspension. One agreement was reinstated at the end of 2013.
NT10BIX5570136 | 2014 | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Network construction is still underway. | 0 | N/A | 0 | N/A | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Network construction is still underway. | 0 | N/A | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Network construction is still underway. | 0 | N/A | GovNET has been able to increase broadband speed provided to community anchor institution customers at least 5x-10x. One CAI customer previously had maxed out local capacity with 7 bonded T1s (or 1.5 Mbps x 7 = 10 Mbps of speed). GovNET was able to provide 100 Mbps of full-duplex broadband service (same upload speed as download speed) to a very excited rural district school office and campus. GovNET expects the average increase in broadband speed will increase from 1.5 - 10 Mbps current average access to over 100Mbps - 1Gbps capability as a result of this project. | N.A | 7a. Network is operating in parts of the State of Arizona. Bandwidth limitations are in effect only in terms of provisioning requested bandwidth to specific customers. 7b. No - we have never limited access to any entity requesting service. | No community anchor institutions have dropped GovNET services in 2014. There are no households or business that take services. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 600 | 450 | 0 | 150 | GovNET owns collocation space, and will have towers and space for cabinets available for collocation. | No subcontracts or sub grants were made in 2014 to SDBs. | N/A | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | No interconnection agreements signed in 2014, although two (2) agreements were being revived and negotiated. GovNET has not denied any requests for interconnection. | GovNET has entered into a second peering agreement in 2014 with a separate provider for 10 Gbps of Tier One Internet. No further agreements are anticipated.
NT10BIX5570138 | 2010 | 0 | NA at this time as construction has not begun | 0 | NA | 0 | NA | 0 | NA at this time as construction has not begun | 0 | NA | 0 | NA at this time as construction has not begun | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | NA | NA | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | NA
NT10BIX5570138 | 2011 | 57881 | This amount represents a 28% reduction in cost per mile. This is due to the inclusion of 48.05 air miles in the calculation. The air miles were not included in our original mile count. | NA | NA | NA | NA | 1GBS | No variance to baseline | NA | NA | 100mg | No variance to baseline | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have a cost per meg of $106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per meg will range from $4.75 per meg to $31.47 per meg and will represent a 70% - 90% cost reduction while providing in most cases an over 90% increase in speed. | NA | NA | NA | 5080 | 8 | 0 | 1282 | 300 | 0 | 3490 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2010. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. Wes-Tex Midland where Wes-Tex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend and Wes-Tex connect. 4. TLSN McCamey HUB where Big Bend and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned that working together with local companies that are experts in their field and also have a vested and long term investment in the community has helped the success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2010. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. WesTex Midland where WesTex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend and WesTex connect. 4. TLSN McCamey HUB where Big Bend and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed.
NT10BIX5570138 | 2012 | 57881 | This amount represents a 28% reduction in cost per mile. This is due to the inclusion of 48.05 air miles in the calculation. The air miles were not included in our original mile count. This is the same amount and information provided in the 2011 annual report. | NA | NA | NA | NA | 1GBS | No variance to baseline | NA | NA | 100 MG | No variance to baseline | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have a cost per Mbps of$106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per Mbps from $4.75 per Mbps to $31.47 per Mbps and will represent a 70% - 90% cost reduction while providing in most cases an over 90% increase in speed. | NA | NA | NA | 5080 | 8 | 0 | 1282 | 300 | 0 | 3490 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. WesTex Midland where WesTex Telephone Coopand Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex Telephonecoop connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned the benefits of working with local telephone companies on this project. Their industry knowledge and expertise in the area of fiber and wireless installation has contributed to our ability to stay on and ahead of our construction schedule. Also working with local companies helps the local communities and has helped in the community support of our project as we look to expand our reach beyond our ISD (Independent School Districts) to the surrounding community anchor institutions. By forming long term agreements with long standing local companies we can feel confident in the long term success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. 1. Dell City/Pecos, where Delcom and Hill Country Telephone connect. 2. WestTex Midland where WesTex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex Connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed.
NT10BIX5570138 | 2013 | $54,560 | Final project miles are 244. Final construction and equipment cost for the project are$13,312,645. Equipment costs are favorable to baseline. Miles greater than baseline due to the inclusion of wireless miles as requested during site visit. | NA | NA | NA | NA | 1 GBS | No variance | NA | NA | 100 MG | No variance | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have an average cost per M.G. of $106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per MG will range from $4.75 to $31.47 and will represent approximately 70% to 90% cost reduction while providing in most cases a 90% increase in speed. | NA | NA | NA | 5530 | 781 | 0 | 4749 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. They were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. Dell City/Pecos, where Delcom and Hill Country Telephone interconnect. 2. WesTex Midland where WesTex Telephone Co-op and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned the benefits of working with local telephone companies on this project. Their industry knowledge and expertise in the area of fiber and wireless installation has contributed to our ability to successfully complete all forecast project routes and to connect all primary CAI locations as well as many secondary locations. With fixed price contracts we were able to stay on track with our budget. Working with local companies has been beneficial to the local economies and has helped the community support of our project. By forming long term agreements with long standing local companies we can feel confident in the long term success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. They were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. Dell City/Pecos, where Delcom and Hill Country Telephone interconnect. 2. WesTex Midland where WesTex Telephone Co-op and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed.
NT10BIX5570139 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A (Dark fiber only) | 0 | N/A | 0 | N/A (Dark fiber only) | 0 | N/A | Dark fiber only, service providers do not disclose | None, dark fiber on a wholesale basis | Dark fiber only, open access/non-discrimination policy posted on MFC website | N/A | 159319 | 0 | 55 | 1728 | 0 | 0 | 157536 | 55 strand miles are currently in use, amongst the customers outlined earlier in this report. | 0 | 0 | 0 | 0 | Network providers may interconnect anywhere on the Three-Ring Binder that is technically feasible, and MFC is providing splice cases every 15,000 feet, and slack loops every 1,500 to 2,400 feet to facilitate interconnection wherever possible. | None at this time. | - Convene stakeholder advisory board to assist with CAI connection issues. - Meeting with pole owners biweekly to prioritize make-ready and resolve issues. - Post google route map publicly to encourage uptake. - Provide periodic construction schedule updates to interested service providers to assist them with broadband adoption efforts. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | None (Dark fiber only) | None (Dark fiber only)
NT10BIX5570139 | 2011 | $18,893 | At the moment, this cost per new mile is less than the projected baseline cost. However, the current cost is based on make-ready and construction costs on segments with lower cost make-ready which allowed them to complete first. In addition, these segments also have lower-count fiber which is less expensive. We anticipate this cost per new mile to increase to the projected baseline number as we complete segments with heavier, more expensive make-ready and with higher-count, more expensive fiber. | N/A | N/A | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | Dark fiber only, service providers do not disclose | None, dark fiber on a wholesale basis | Dark fiber only, open access/non-discrimination policy posted on MFC website | N/A | 171028 | 0 | 353 | 83267 | 0 | 18000 | 69408 | We are leasing 353 miles to six customers with whom we have signed dark fiber leases. | 0 | 0 | 0 | 0 | Network providers may interconnect anywhere on the Three Ring Binder that is technically feasible. MFC is providing splice cases every 15, 000 feet and slack loops every 1, 500 to 2,500 feet to facilitate interconnection wherever possible. | None at this time. | - Meeting with pole owners biweekly to prioritize make-ready and resolve issues. Provided make-ready prioritization and requested completion dates to the pole owners to coordinate the make-ready process. - Post route map publicly to encourage service provider uptake. - Weekly meetings with contractors and vendors to review the project's status and coordinated items. - Worked closely with the fiber vendor to coordinate fiber production and delivery times with the project's schedule to limit the impact of fiber rationing imposed upon the project due to global fiber shortage. - Utilized Google Earth KMZ maps to coordinate fine engineering among the subcontractors. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | -We have six dark fiber lease agreements with various service providers to date. Each lease agreement varies in terms of overall mileage leased and number of interconnection points depending on service provider need. - We have not denied service to any provider. - We continue to negotiate additional dark fiber lease agreements. | - None (Dark fiber only)
NT10BIX5570139 | 2012 | $23,414 | Ability to release major RFPs early in the project resulted in better than anticipated pricing for labor and materials. Tight management and good working relationships with pole owners helped to keep Make Ready costs in line. These along with other less material factors have resulted in better than projected cost per new mile, when compared to the baseline. | N/A | N/A | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | We only provide the dark fiber, service providers do not provide this information to us. | None, we offer dark fiber on a wholesale basis. | We do not offer any lit service so there are no restrictions on content, applications, etc. The dark fiber strands are offered on an open access/non-discriminatory basis, as advertised on the MFC website. | N/A | 187467 | 0 | 7026 | 180429 | 0 | 4 | 8 | Our 16 customers are currently utilizing 7,026 strand miles on our network. Our current customers are GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, TDS Telecom, Unity Telephone and two unnamed parties (under NDA). | 240 | 0 | 40 | 200 | The primary way customers of MFC interconnect with the network is aerially along the route using splice cans at existing butt splice or ring cut locations, or by utilizing a slackloop by turning it into a ring cut. Slackloops and/or splice locations exist around the network about every 2,500' or less. This aerial model represents most of the 225 interconnection points being used on the network. | N/A | - We utilized Google Earth KMZ maps to coordinate fine engineering among the subcontractors. Limited the number of trips into the field and provided high level of detail. - Sales cycles for leasing dark fiber are long and often require educating potential customers on use and benefit. Plan on both of these to ensure sales/sustainability goals are reasonable and can be achieved within set time lines. - Have a plan to document and track 'asbuilt' network data. Ability to track each strand of fiber for each customer in addition to knowing what is available for lease where is a critical path item. - Meet with pole owners biweekly to prioritize make-ready and resolve issues. Provide make-ready prioritization and request completion dates to the pole owners to coordinate the make-ready process. - Hold weekly, in person, meetings with contractors and vendors to review the project's status and work through any 'problem' items. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | 1) We have executed 10 new dark fiber lease agreements in calendar year 2012, bringing our total to date to 16. All agreements are for the leasing of dark fiber, we do not offer any other service. Each lease agreement varies in terms of overall mileage leased and number of interconnection points being utilized depending on service provider need. 2) We are currently in various stages of negotiations with 8 additional entities. All agreements are for the leasing of dark fiber. 3) We have not denied service to any provider | None - we only offer dark fiber.
NT10BIX5570139 | 2013 | $23,048 | MFC achieved favorable results in releasing major RFPs early in the project, which resulted in better than anticipated pricing for sub-contract labor and materials. Rigorous oversight and good working relationships with pole owners helped to keep Make Ready costs reasonable. These along with other less material factors have resulted in better than anticipated â€˜cost per new mileâ€™, when compared to the baseline. | N/A | N/A | N/A | N/A | 0 | N/A (Dark Fiber Only) | N/A | N/A | N/A | N/A (Dark Fiber Only) | N/A | N/A | We only provide the dark fiber, service providers do not provide this information to us. | None, we offer dark fiber on a wholesale basis. | We do not offer any lit service so there are no restrictions on content, applications, etc. The dark fiber strands are offered on an open access/non-discriminatory basis, as advertised on the MFC website. | N/A | 189910 | 0 | 8586 | 181324 | 0 | 0 | 0 | Our 19 customers are currently utilizing 8,586 strand miles on our network. Our current customers are GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, TDS Telecom, Unity Telephone, Northeast Wireless, Bowdoin College and three unnamed parties (NAMES REDACTED DUE TO NDA). | 1610 | 0 | 268 | 1342 | Although MFC has collocation space available,the primary way customers of MFC interconnect with the network is aerially along the route using splice cans at existing butt splice or ring cut locations, or by utilizing a slack loop by turning it into a ring cut. Slack loops and/or splice locations exist around the network about every 2,500' or less. This aerial model represents most of the 225 interconnection points being used on the network. These points are made available on the MFC website in a Google Earth layer. | N/A | - Google Earth is a highly effective, free, software package that allows detailed information, such as KMZ maps to incorporating fine engineering, to be conveyed in an effective way to subcontractors, as well as to distribute 'as built' information to customers. - Plan to incorporate software to document and track 'asbuilt' network data. The ability to track each strand of fiber for each customer in addition to knowing what is available for lease where is a critical path item for operating success. - Meet with pole owners biweekly to prioritize make-ready and resolve issues. Provide make-ready prioritization lists and request completion dates to the pole owners to help coordinate the make-ready process. - Hold weekly, in person, meetings with contractors and vendors to review the project's status and work through any 'problem' items. - Be detail oriented and set realistic, tangible, goals and hold team members, suppliers and contracts accountable for meeting the goals. Review goals and expectations often during regular and established get-togethers. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | 1) We have executed 3 new dark fiber lease agreements in calendar year 2013 (YTD), bringing our total to date to 19. All agreements are for the leasing of dark fiber, we do not offer any other service. Each lease agreement varies in terms of overall mileage leased and number of interconnection points being utilized depending on service provider need. 2) We are currently in various stages of negotiations with 5 additional entities. All agreements are for the leasing of dark fiber. 3) We have not denied service to any provider. | None - we only offer dark fiber.
NT10BIX5570140 | 2010 | 0 | Since this project started 9/1/10, our first annual report contains only 4 months and there have been no costs during this time. It is expected that the actual costs will match the Baseline after a full year has passed. | 0 | N/A | 0 | N/A | 0 | Baseline listed 10Gbps projected speed, based on Year 1 of 4 quarters. Since this project started 9/1/10, our first annual report contains only 4 months and there has been no actual construction yet. It is expected that the actual speed will match the Baseline after a full year has passed. | 0 | N/A | 0 | Baseline listed 1Gbps projected speed, based on Year 1 of 4 quarters. Since this project started 9/1/10, our first annual report contains only 4 months and there has been no actual construction yet. It is expected that the actual speed will match the Baseline after a full year has passed. | 0 | N/A | N/A | N/A | N/A | N/A | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None at this time. | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | N/A | N/A
NT10BIX5570140 | 2011 | $40,000 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education institutions is 10Gbps. | 0 | n/a | 2Gbps | Roughly 340 sites (K12, Libraries, some Higher Ed sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps. | 0 | n/a | The average site had its bandwidth increased by over 75 times. Almost all community colleges and higher educational institutions went from 1 Gbps to 10Gbps. Almost all K-12 sites went for 6 Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to reach the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the network. Each network (K-12, Library, Community College/Higher Ed) is fully independent of each other and is solely managed by the respective entity. | n/a | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a
NT10BIX5570140 | 2012 | $41,211 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education institutions is 10Gbps. | 0 | n/a | 2Gbps | Roughly 340 sites (K12, Libraries, some Higher Ed sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps. | 0 | n/a | The average site had its bandwidth increased by over 75 times. Almost all community colleges and higher educational institutions went from 1 Gbps to 10Gbps. Almost all K-12 sites went for 6 Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to reach the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the network. Each network (K-12, Library, Community College/Higher Ed) is fully independent of each other and is solely managed by the respective entity. | n/a | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a
NT10BIX5570140 | 2013 | 48,046 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education Institutions is 10Gbps | 0 | n/a | 2Gbps | Roughly 339 sites (K12, Libraries, some Higher Ed Sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps | 0 | n/a | The average site had its bandwidth increased by over 75 times Almost all community colleges and higher educational institutions went from 1Gbps to 10Gbps. Almost all K-12 sites went from 6Mbps to 1Gbps. All Libraries went from 1Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to obtain the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the optical network. Each network (K-12, Library, Community College/Higher Education) is fully independent of each other and is solely managed by their respective entity. | n/a | 3186 | 3178 | 0 | 0 | 8 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a
NT10BIX5570140 | 2014 | $48,759 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education Institutions is 10Gbps | 0 | n/a | 2Gbps | Roughly 344 sites (K12, Libraries, some Higher Ed Sites) receive 1Gpbs, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps. | 0 | n/a | The average site had its bandwidth increased by over 75 times Almost all community colleges and higher educational institutions went from 1Gbps to 10Gbps. Almost all K-12 sites went from 6Mbps to 1Gbps. All Libraries went from 1Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to obtain the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the optical network. Each network (K-12, Library, Community College/Higher Education) is fully independent of each other and is solely managed by their respective entity. | n/a | 3186 | 3186 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a
NT10BIX5570144 | 2010 | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | N/A | N/A | N/A | N/A | 100800 | 0 | 0 | 0 | 2800 | 13368 | 84632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Northern Illinois University (NIU) has been working collaboratively together with the DeKalb County BTOP finding project by collaborating weekly on strategic interconnections between the networks and their methodology. NIU has regular correspondence with the IBOP-EC project to assure that the Illinois Century Network interconnection points as successfully executed for delivery of content to ICN constituents. In addition, the IBOP-NW has needs for fiber routes that will be provided by NIU that avoids any overlay in the projects. The synergies between NIU and IBOP-EC are in process by regular e-mails, phone or in person meetings. NIU has been working with the Partnership for Connected Illinois (PCI) on developing the necessary information and processes to meet their goals. Currently NIU is working with PCI to assist in providing seminars for the State of Illinois BTOP projects to help PCI deliver their goals and requirements of Illinois BTOP projects. | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A
NT10BIX5570144 | 2011 | 68,682 | N/A | 0 | N/A | 0 | N/A | 10 gig | N/A | 0 | N/A | 100 mb | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 100800 | 0 | 0 | 4176 | 2800 | 13368 | 84632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A
NT10BIX5570144 | 2012 | 64,662 | This cost is lower than baseline primarily due to the fact that completed mileage to date is more heavily weighted toward plow miles. The remaining miles to be built are mainly bore which will shift the average up as we near completion. | 0 | n/a | 0 | n/a | 10 gig | n/a | 0 | n/a | 100 mb | n/a | 0 | n/a | In general, our CAIs will transition from around 1.54 to 4.5 mb on T-1 lines with a small percent on connections with speeds that can go up to 20 mb. The new installation for CAIs will be 1 gig increasing speeds on average of 995 mb. | N/A | Network policies based on port speed will use protocol PBB-TE and IEEE 802.1Q with IP prioritizing network traffic. | N/A | 89678 | 0 | 571 | 60084 | 16226 | 13368 | 60084 | N/A | 0 | 0 | 0 | 0 | The project has access to co-location rack space in 36 CAI locations where space was available. Some facilities are willing to lease space where available to other entities. For access to the iFiber equipment, interconnections also can be provided through hand hole locations that are within 1500' of any facilities along an intra-municipal route or 4000' along a rural route. | N/A | All duct in the project contains multiple sub-ducts that allow additional cable to be installed during the project and the future. This reduced the costs overall to the project in helping to centralize splice locations and reducing the overall splicing. The duct reserves future capabilities without ground disturbance when adding fiber to the system. This will reduce future costs to the project as we move past the grant period. | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A
NT10BIX5570144 | 2013 | 72,524 | This cost is higher than baseline due to changes in expected versus actual rock terrain and delays in approval of route modifications. The original proposal estimated the amount of rock versus soil construction. The actual amount of rock terrain was higher than projected and therefore, increased construction costs. The route modification process halted complete construction in municipalities where permitting authorities required changes to the original routes. This caused loss of economies-of-scale as contractors were required to redeploy crews and equipment once NTIA approvals were received. In addition, the delay required the project to extend beyond the original end date which contributed to increased costs as contractors held resources to complete segments upon NTIA approval. | 0 | N/A | 0 | N/A | 10 gig | N/A | 0 | N/A | 100 mb | N/A | 0 | N/A | In general, our CAIs will transition from around 1.54 to 4.5 mb on T-1 lines with a small percent on connections with speeds that can go up to 20 mb. The new installation for CAIs will be 1 gig increasing speeds on average of 995 mb. | We are providing transport services to ISPs and other content providers at a cost of $500 per month per/port, plus 15% of monthly gross revenues earned providing network access and services to Community Anchor Institutions. We are providing transport services to Community Anchor Institutions. See attached pricing schedule. | 7a) Network policies are based on port speed system with use protocol IEEE 802 1Q with IP for prioritizing network traffic. The iFiber is a layer 2 designed network providing for Metro Ethernet connectivity. Three classes of priorities have been defined in the network based on off ELAN classes of traffic. The three levels of traffic are 1) E-911 Services, 2) ISP Services and 3) Cloud (intranet) Traffic. The highest level of priority is given to the E-911 services with the next level to ISP services and the lowest to the intranet cloud traffic. The system is open to all lawful content and types of traffic. 7b) We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | We have had 4 requests or >1% who have dropped or will be dropping broadband service at this time. All of these locations have closed facilities or will be closing facilities. | 89678 | 7694 | 571 | 81413 | 7694 | 571 | 81413 | OSF Healthcare - 118.9 miles | 0 | 0 | 0 | 0 | The project has access to co-location rack space in 33 CAI locations where space was available. Some facilities are willing to lease space where available to other entities. For access to the iFiber equipment, interconnections also can be provided through hand hole locations that are within 1500' of any facilities along an intra-municipal route or 4000' along a rural route. | N/A | All duct in the project contains multiple sub-ducts that allow additional cable to be installed during the project and the future. This reduced the costs overall to the project in helping to centralize splice locations and reducing the overall splicing. The duct reserves future capabilities without ground disturbance when adding fiber to the system. This will reduce future costs to the project as we move past the grant period. | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | (1) twelve agreements (2) none at this time (3) none have been denied | (1) one agreement (2) none at this time (3) none have been denied
NT10BIX5570145 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 100 Mbs | 100 MB Fiber connection | 10Mbs | 802.11 Wireless. | N/A | At this time not connections are active so we can not get an average reading. | N/A | At this time not connections are active so we can not get an average reading. | N/A - Averages are not available for this project at this time. | 100 MB Fiber data/Voice over IP connection per anchor institution, charge of $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent ruling or statement, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and not content will be favored. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place, however, the Tribe as a contingency plan in place should opportunity present it self. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A
NT10BIX5570145 | 2011 | $433,261 | This number does not reflect a true average. We have purchased much of the equipment and supplies, but have just started to lay the fiber. Thus the numbers show the expenses, roughly 44 % of money spent (outside plant), but only represents 1 mile of new middle mile fiber. This will come back into line as more middle mile fiber is installed. | N/A | We have most of the network installed and are in the testing phase, but have not yet connected any last mile subscribers. | N/A | We have not currently connected any LM Subscribers. | 100 Mbs | 100 Mbs Fiber Connection | 10Mbs | 802.11 Wireless Connection | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless Connection, With 10 Mbs feed | Some of the locations that we have connected had no previous connectivity, others had connections via dedicated lattice circuits with an aggregate speed of 1028K, all new connections are 100MB Fiber. | 100 MB Fiber data/Voice over IP connection per anchor institution, charge of $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent rulings or statements, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and no content will be favored. | N/A | 912 | 18 | 0 | 6 | 780 | 0 | 108 | N/A | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place and there has been now demand for such. However the Tribe does have a contingency plan in place if such a demand should present itself. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A
NT10BIX5570145 | 2012 | $197,274.13 | We currently have 9 miles of fiber completed and have spent 2,019,871.66 87.90% of which is costed to MM which gives us a total spent for middle mile of 1,775.467.19. Divide this by miles completed 9 to get 197,274.13 | $1358 | We have currently spent 2,019,871.66 dollars of which 12.10 % or $244,404.47 is allocated to the Last Mile portion of this project. We have passed180 total households leaving us with a current cost per household passed of $1,358.00 | $1629 | We have currently spent 2,019,871.66 dollars of which 12.10 % or 244,404.47 of is allocated to Last Mile portion of this project. We have connected a total of 150 households, which leaves us with a current cost per household connected at roughly $1,629.00 | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless Connection | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless connection, with 10 Mbs feed | Some of the locations that we have connected had no previous connectivity, others had connections via dedicated lattice circuits with an aggregate speed of 1028K, all new connections are 100MB Fiber. | 100 MB Fiber data/Voice over IP connection per anchor institution, we plan to charge $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent rulings or statements, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and no content will be favored. | N/A | 912 | 798 | 0 | 114 | 0 | 0 | 0 | We currently do not have any wholesale customers, but we have set aside 12 strands of fiber for future the possibility of leasing fiber to a third-party. | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place and there has been now demand for such. However the Tribe does have a contingency plan in place if such a demand should present itself. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A
NT10BIX5570145 | 2013 | $197,274.13 | We currently have 9 miles of fiber completed and have spent 2,019,871.66 87.90% of which is costed to MM which gives us a total spent for middle mile of 1,775.467.19. Divide this by miles completed 9 to get 197,274.13 | $1358 | We have currently spent 2,019,871.66 dollars of which 12.10 % or $244,404.47 is allocated to the Last Mile portion of this project. We have passed180 total households leaving us with a current cost per household passed of $1,358.00 | $1629 | We have currently spent 2,019,871.66 dollars of which 12.10 % or 244,404.47 of is allocated to Last Mile portion of this project. We have connected a total of 150 households, which leaves us with a current cost per household connected at roughly $1,629.00 | 100 Mbs | 100 Mbs Fiber Connection | 10 MBs | 802.11 Wireless Connection | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless connection, with 10 Mbs feed | Some of the locations that we have connected had no previous connectivity, others had connections via dedicated lattice circuits with an aggregate speed of 1028K, all new connections are 100MB Fiber. | 100 MB Fiber data/Voice over IP connection per anchor institution, we plan to charge $400 per month per connection. | Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and no content will be favored. | N/A | 912 | 798 | 0 | 114 | 0 | 0 | 0 | We currently do not have any wholesale customers, but we have set aside 12 strands of fiber for future the possibility of leasing fiber to a third-party. | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place and there has been now demand for such. However the Tribe does have a contingency plan in place if such a demand should present itself. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A
NT10BIX5570146 | 2010 | 0 | Construction has not yet begun. | N/A | N/A | N/A | N/A | 0 | Construction has not yet begun. | N/A | N/A | 0 | Construction has not yet begun. | N/A | N/A | We have not yet begun connecting community anchor institutions since construction has not yet begun. We anticipate several CAIs will be upgrading from copper based T1 services to fiber speeds ranging from 10Mb/s up to GigE service. | Pricing has not yet been finalized for this project. DS-1, DS-3, OC-3, OC-12, OC-48, 2.5G Lambda, 10G Lambda, 10Mb/s, 20Mb/s, 50Mb/s, 100Mb/s, 200Mb/s, 500Mb/s and GigE. | Have not yet completed our network management policies for the stimulus funded network. We will abide by all interconnection and open access requirements of the program. | Have not yet begun construction. | 36520 | 0 | 0 | 3520 | 16500 | 8250 | 8250 | N/A | 0 | 0 | 0 | 0 | We will own collocation space but construction has not yet begun therefore no facility collocation capacity to report at this time. | N/A | Attending the BTOP Recipient Workshop was very helpful. We took away a lot of good information that has allowed us to stay on top of reporting requirements as well as overall project requirements. Meeting the grant officers and other Federal project staff provided useful tips for managing the project. We also believe that weekly update meetings with engineering, finance, purchasing, environmental and right of way staff help to minimize any project surprises. These weekly meetings coincide nicely with our weekly Federal Project Officer meetings allowing us to seek answers to questions quickly and share that information with the entire project staff. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | Interconnection agreements are currently in progress. | Peering and Transit Agreements are currently in progress.
NT10BIX5570146 | 2011 | $40,520 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed and was based on overall costs rather than simply capital costs. The first segments built were comprised primarily of underground fiber and were the most expensive routes. The cost per mile, $40,520, falls within Sho-Me's overall estimates for per mile costs for underground fiber. At the end of 2011, Sho-Me calculates overall per mile costs for the entire project to be $30,677 which includes approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V.D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1.pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limitat | None. 0% | 32488 | 1840 | 0 | 5184 | 3552 | 0 | 21912 | N/A | 3246 | 1388 | 0 | 1858 | N/A | N/A | Sho-Me Technologies, LLC often uses checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Pre-Construction meetings are held with each contractor prior to construction beginning. This has helped to ensure contractors know what is expected of them regarding prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of Sho-Me's project. Biweekly meetings are held between the project's key personnel where issues and concerns are raised, progress is acknowledged, and upcoming events are discussed. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 4 2) Total number of interconnection agreements currently negotiating = 8 3) No requests for interconnection have been denied. | N/A
NT10BIX5570146 | 2012 | $31,340 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed. The first segments built were comprised primarily of underground fiber and were the most expensive routes. The cost per mile, $31,340, falls within Sho-Me's overall estimates for per mile costs for underground fiber. At the end of 2012, Sho-Me calculates overall per mile costs for the entire project to be $32,045 which includes approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V.D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1.pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limitat | None. 0% | 35961 | 1612 | 0 | 25346 | 4021 | 0 | 4982 | N/A | 3104 | 1334 | 0 | 1770 | N/A | N/A | Sho-Me Technologies, LLC often uses checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Pre-Construction meetings are held with each contractor prior to construction beginning. This has helped to ensure contractors know what is expected of them regarding prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of Sho-Me's project. Biweekly meetings are held between the project's key personnel where issues and concerns are raised, progress is acknowledged, and upcoming events are discussed. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 22 2) Total number of interconnection agreements currently negotiating = 3 3) No requests for interconnection have been denied. | N/A
NT10BIX5570146 | 2013 | $31,026.23 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed. The first segments built were comprised primarily of underground fiber and were the most expensive routes. Sho-Me calculates average cost per mile to be $31,026.23 for the entire middle-mile project which estimated approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V. D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1. pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limi | None. 0% | 36442 | 5959 | 0 | 30483 | 0 | 0 | 0 | N/A | 3104 | 1334 | 0 | 1770 | N/A | N/A | Sho-Me Technologies, LLC implemented use of checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Also, pre-construction meetings are necessary with each contractor prior to construction start to reinforce what is expected of them regarding time lines, safety, prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of the "Sho-Me MO" middle mile project. Biweekly update meetings are held with the project's key personnel from engineering, accounting, purchasing, human resources, IT, environmental and right of way staff. Project milestones are reviewed, construction progress is acknowledged, budget issues and concerns are discussed, and upcoming community outreach events are announced. These meetings coincide with our biweekly status calls with our Federal Project Officer allowing us to seek answers to questions quickly and share that information with the BTOP team. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 13 2) Total number of interconnection agreements currently negotiating = 6 3) No requests for interconnection have been denied. | N/A
NT10BIX5570148 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Construction has not started yet. | Construction has not started yet. | Construction has not started yet. | Construction has not started yet. | 29760 | 0 | 0 | 0 | 17856 | 5952 | 5952 | We are negotiating with another provider for their lease of dark fiber along part of the planned route once completed. Construction has not started yet. | 400 | 50 | 50 | 350 | We will connect with other network providers at the Fiber Hotel in Missoula, the Flathead Electric Coop in Kalispell, the Northern Telephone Exchange to 360networks in Santa Rita, and at the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made. | Most important....get started on the EA early, and stay tuned in to what your consultant is doing. Finding a good EA consultant is extremely important. If dealing with Tribes, determine early on what the Tribal Employment Rights Ordinance says and what it means to your budget. It may be possible to negotiate the TERO fees and maybe these fees and right of way fees can be paid for with some form of partial ownership of infrastructure across Tribal lands. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | N/A | N/A
NT10BIX5570148 | 2011 | $0 | 55.7 miles of fiber/conduit installed at a cost of $1,795,661 for labor and materials, however not ready for deployment as these segments are only those that permits were available for. Deployment is dependent on splicing, fiber availablity, additional segment build, and interconnection to the Internet in Missoula and Seattle. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | No CAI's yet, still under construction. | No CAI's yet, passed some but still under construction. See attached CAI projections spreadsheet. | Ronan Telephone Company already has non-descrimination and network managment policies in place and Montana West will be modifying these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies will be in place before the network is finished and service is offered. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to the network and do not intend to do so when the network is turned up. | N/A We have not lost any subscribers yet as we are still under construction. | 29760 | 0 | 0 | 0 | 27648 | 1780 | 332 | We have a contract to provide 165.9 miles of 2 dark fibers to another provider on a 20 year IRU, between Kalispell and Missoula, with a delivery date of August 1, 2012, at a rate of $1750 per fiber mile, prepaid upon delivery. | 544 | 50 | 50 | 444 | We will connect with other network providers at the Fiber Hotel in Missoula, the Flathead Electric Coop in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts of sub grants have been made to socially and economically disadvantaged small business concerns. | In the event of fiber shortage, and the resulting increase in fiber pricing, it may be advantageous to place conduit and pull in fiber when it becomes available. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | 1. (0) We have not entered into any interconnection, peering, and/or transit agreements during this annual reporting period. 2. Currently negotiating (0) interconnection agreements. 3. We have not denied any requests for interconnection. | A. Currently negotiating (0) peering agreements B. Currently negotiating (2) transit agreements for upstream transport
NT10BIX5570148 | 2012 | $48,901 | $8.9Million to date, divided by 182 miles completed (includes conduit ready for fiber) | $14,590 | $8.9 Million, divided by 610 households passed. Evaro 70, Arlee 105, St., Ravalli 35, Ignatius 140, Ronan 170, Pablo 90 | $787/3Mb | 70 last mile wireless subscribers in Arlee..base station $36,173 plus 70 CPE's at $270, total $55,073 for 70 subscribers...average cost per sub $787.00 | 1Gb | No variance | 4Mb | No Variance | 1.1Gb | (1) customer at 200Mb, (1) customer at 2Gb...average broadband speed provided is 2.2Gb divided by 2. | 2.0Mb | 55 customers at 1.5Mb and 15 at 4.0Mb | No CAI's yet, still under construction. | No CAI's yet, construction to CAI's is scheduled for Q2 and Q3 2013. See attached CAI projections spreadsheet. We are providing retail wireless services to the community of Arlee...upgraded 60 customers and added 10 new ones. Retail charges are $29.95 for 1.5mb, and $49.95 for 4.0Mb | Ronan Telephone Company already has non-discrimination and network management policies in place and Montana West has modified these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies are in place and are stated in the Montana West Master Services Agreement. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to the network. | N/A..we have not lost any subscribers to the network. | 29760 | 11616 | 0 | 0 | 17812 | 0 | 332 | We have a contract to provide 166 miles of 2 dark fibers to Bresnan on a 20 year IRU, between Kalispell and Missoula, with a delivery date of August 1, 2012, at a rate of $1750 per fiber mile, prepaid upon delivery. Presently this is re-scheduled for delivery April 15, 2013. | 544 | 50 | 50 | 444 | We connect with other network providers at the fiber hotel in Missoula, the Kalispell Regional Medical Center in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business concerns. | When depending on work from a contractor for a significant part of your build, be sure to put in enough late delivery penalty to motivate the contractor to finish on time, no matter how large the company is. You can't start early enough on the permitting part of the project. Have a backup plan or a "plan B" for everything that you intend to do. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | 1. (0) We have not entered into any interconnection, peering, during this annual reporting period. We have entered into one transit agreement, with Cutthroat Communications. (CCI) Montana West is providing 2Gb transport to CCI between Missoula and Seattle. 2. Currently negotiating (0) interconnection, peering and/or transit agreements 3. We have not denied any requests for interconnection. | Two transit agreements with Cutthroat Communications (CCI). CCI is providing 1Gb transport to Montana West between Missoula and Santa Rita, and Montana West is providing 2Gb transport to CCI between Missoula and Seattle.
NT10BIX5570148 | 2013 | $51,574 | $13.1M to date, divided by 254 miles completed. | $30.16 | Households in Arlee 235 Households in Elmo/Big Arm 124 Wireless costs $102,586 divided by 359 = $30.16 | $915.95 | 107 last mile subscribers in Arlee, 5 last mile subscribers in Elmo/Big Arm, (2) base stations at $36,173 plus 112 CPE's at $270, total $102,586 for 112 subscribers...average cost per sub $915.95 | 1Gb | No Variance | 4Mb | No Variance | 233Mb | 100Mb (13), 200Mb (1), 2Gb (1) 3500Mb/15=233.33Mb | 10.68Mb | Residences: 1.5Mb* (28)=42, 2.5Mb* (5)=12.5, 4Mb* (74)=296, 100Mb* (5)=500 Businesses: 100Mb*(3)=300 50Mb*(2)=100 100+300+500+296+12.5+42=1250.5/117=10.68Mb | Broadband speed has been increased to 100Mb as this is the lowest offering we have for CAI's Original New % CAI Bandwidth (Mb) Bandwidth (Mb) Increase (Mb) Increase Salish Kootenai College 10 100 90 900 St. Luke Medical Center 10 100 90 900 Ronan City Library 4 100 96 2400 Polson School District 10 100 90 900 Ronan School District 10 100 90 900 Ronan Fire Department 4 100 96 2400 Lake County Housing 4 100 96 2400 Kalispell Regional Med Ctr. 10 100 90 900 Flathead Comm. College 10 100 90 900 Salish Kootenai Headquarters 10 100 90 900 Ronan City Hall 4 100 96 2400 Mission Valley Power 10 100 90 900 Valley View School 4 100 96 2400 | Retail services are being offered in both wireless and fiber broadband from 1.0Mb to 100Mb Wireless Internet 1Mb...$24.95 2Mb...$34.95 4Mb...$44.95 Residential Internet via fiber 100Mb...$100 Business Internet via fiber ranging from $11 to $18 per Mb Port connections for WAN 1Gb Dedicated...$1400 1Gb Best Effort...$750 100Mb Dedicated...$750 100Mb Best Effort...$250 | Ronan Telephone Company already has a non-descrimination and network management policies in place and Montana West has modified these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies are in place and are stated in the Montana West Master Services Agreement. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to our network. | N/A..we have not lost any subscirbers to the network. | 26784 | 22944 | 332 | 0 | 3508 | 0 | 0 | We have provided 166 miles of 2 dark fibers to Bresnan on a 20 year IRU. | 544 | 50 | 50 | 444 | We connect with other network providers at the fiber hotel in Missoula, the Kalispell Regional Medical Center in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business concerns. | Even though you have a grant, never take anything for granted. Always have a backup plan. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | Interconnection agreement with Cogent Communications at the Westin Fiber Hotel in Seattle | 1. (0) We have not entered into any interconnection, transit or peering agreements during this annual reporting period. 2. Currently negotiating (1) Interconnection agreement, (0) peering and (0) transit agreements. (Qwest) 3. We have not denied any requests for interconnection
NT10BIX5570148 | 2014 | $48,227 | 282 Mi. divided into $13.6M | $267 | Arlee 235 Elmo/Big Arm 108 Evaro 34 Heart Butte 164 $144,692 /541 households = $267 | $1,528 | Arlee 107 Elmo/Big Arm 7 Evaro 1 Heart Butte 0 $175,742/115 subs = $1,528 | 1Gb | No Variance | 4Mb | No Variance | 128Mb | 50Mb (4) 100Mb (20) 1Gb(1) 3200Mb/25 = 128Mb | 6.27Mb | 3123Mb/498 customers = 6.27Mb | Broadband speed has been increased for all of our CAI's that accepted our service. Original New % CAI Bandwidth (Mb) Bandwidth (Mb) Increase (Mb) Increase Salish Kootenai College 10 100 90 900 St. Luke Medical Center 10 100 90 900 Ronan City Library 4 100 96 2400 Polson School District 10 100 90 900 Ronan School District 10 100 90 900 Ronan Fire Department 4 100 96 2400 Lake County Housing 4 100 96 2400 Kalispell Regional Med Ctr. 10 100 90 900 Flathead Comm. College 10 100 90 900 Salish Kootenai Headquarters 10 100 90 900 Ronan City Hall 4 100 96 2400 Mission Valley Power 10 100 90 900 Valley View School 4 100 96 2400 Browning Middle School 10 50 40 400 Elmo-Tribal Headquarters 10 100 90 900 Salish-Kootenai Housing 10 100 90 900 Arlee Fire Department 4 10 6 150 | Retail services are being offered in both wireless and fiber broadband from 1.0Mb to 100Mb Wireless Internet 1Mb...$24.95 2Mb...$34.95 4Mb...$44.95 Residential Internet via fiber 100Mb...$100 Business Internet via fiber $10 per Mb Port connections for WAN 1Gb Dedicated...$1400 1Gb Best Effort...$750 100Mb Dedicated...$750 100Mb Best Effort...$250 | Ronan Telephone Company already has non-descrimination and network management policies in place and Montana West has modified these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies are in place and are stated in the Montana West Master Services Agreement. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to our network. | We have not lost any last mile subscribers to the network We have lost a provider who had contracted for 2Mb between Missoula and Seattle. | 26784 | 22944 | 332 | 0 | 3508 | 0 | 0 | We have provided 166 miles of 2 dark fibers to Bresnan on a 20 year IRU | 544 | 50 | 50 | 444 | We connect with other network providers at the fiber hotel in Missoula, the Kalispell Regional Medical Center in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business concerns. | Research the cost and time required for obtaining rights of way carefully when writing the grant. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | There were no new Interconnection agreements this period | There were no new peering and transit agreements this period We have not denied any requests for interconnection.
NT10BIX5570150 | 2010 | 0 | Deployment not yet started | 0 | N/A | 0 | N/A | 0 | Deployment not yet started | 0 | N/A | 0 | Deployment not yet started | 0 | N/A | Deployment not yet started, not applicable for this reporting period | N/A | Deployment not yet started, not applicable for this reporting period | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5336 | 2668 | 0 | 2668 | N/A | None at this time | Start discussions early with any Environmental Assessment related entities/agencies. This often takes longer than anticipated and seems to involve additional entities/agencies that were previously unknown. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | N/A | N/A
NT10BIX5570150 | 2011 | 50,000 | Original baseline utilized total project miles for this calculation because all miles were considered to be new (as they have never been in service or utilized by the State). Because of the projects use of fiber IRU, later guidance has directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 880 new miles and 4664 miles are upgraded. | 0 | N/A | 0 | N/A | 1000 Mbps | No Variance | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | Average speed at the connected entities has gone from no connectivity in most CAI to 1000Mbps availability. For CAI that had prior service, it has increased from 8 Mbps to 1000 Mbps. | None at this time. | The network has the capacity to perform traffic prioritization and bandwidth shaping policies. However, these polices have not been implemented or required because most CPE devices are interfacing into the network at 10 or 100 Mbps. Additionally, we have not limited or blocked any subscribers access. | N/A | 15224 | 4164 | 0 | 2870 | 2260 | 0 | 5930 | N/A | 5336 | 2668 | 0 | 2668 | N/A | None at this time | Continual contact with FPO is extremely beneficial. Many guidance changes have been implemented during the program period. Be meticulous in the record keeping, showing all notes and explanations pertaining to a particular item. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time. | None at this time.
NT10BIX5570150 | 2012 | 50,000 | As this project utilizes 100% IRU facilities, all new mile costs are fixed at $50,000 per new mile. Original baseline utilized total project miles for this calculation because all miles were considered new (as they have never been in service or utilized by the State). Because of the projects use of Fiber IRU, later guidance had directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 1053 new miles and 7827 miles are upgraded. Additionally, PPR reporting guidance was changed to now reflect route miles. Under this new guidance, there are 1053 route miles of new fiber and 2293 route miles are upgraded. If all route miles are taken into consideration for this calculation, the current cost per route mile would be $21,035. | 0 | N/A | 0 | N/A | 1000 Mbps | No Variance | 0 | N/A | 533 Mbps | The network offers 3 speed tiers - 10 Mbps - 306 subscribers currently connected 100 Mbps - 111 subscribers currently connected 1000 Mbps - 425 subscribers currently connected | 0 | N/A | Average speed at the connected entities has increased approximately 1087%, increasing from an average of 4.9 Mbps (as measured across the 840 connected entities) to an average of 533 Mbps. This was calculated based on 321 CAI's having 10 Mbps service and 408 CAI's having no connectivity at all. Once BTOP funded facilities were in place, 111 CAI's increased from 10 Mbps to 1000 Mbps and 408 increased from zero connectivity to 1000 Mbps. Additionally, the improved 321 CAI's while technically not receiving additional bandwidth, benefit dramatically from vastly increased backbone link connectivity that has had a 100% increase in capacity (from single 10Gbps link to two 10Gbps links) as a result of BTOP funds. | None at this time | The project is fully committed to providing access to any entity requesting connection to the network as outlined in the NOFA under Section D.3.b (Nondiscrimination and Interconnection obligations for CCI projects). As of the filing of this report, we have not blocked or limited any subscribers access to service or lawful content at the connected locations. From a network management standpoint, the network has the inherent capability to perform application separation, traffic prioritization and bandwidth shaping should these requirements be necessary. Applicable policies and determination guidelines are currently being revised and/or developed and will be posted as required as soon as they are complete. | N/A | 20463 | 9528 | 0 | 9600 | 405 | 0 | 930 | N/A | 5088 | 3816 | 0 | 1272 | N/A | None at this time and none planned in this project. | Continual contact with FPO and Grants office is extremely beneficial. As the project has progressed, many guidance changes have been implemented. Make sure that all information is kept updated in the grants files along with all notes and explanations. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time | None at this time
NT10BIX5570150 | 2013 | 50,000 | As this project utilizes 100% IRU facilities, all new mile costs are fixed at $50,000 per new mile. The original baseline utilized total project miles for this calculation because all miles were considered new (as they had never been in service or utilized by the State). Because of the projects use of Fiber IRU only, later guidance had directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 1053 new miles and 7827 upgraded miles. Additionally, PPR reporting guidance was changed to now reflect route miles. Under this guidance, there are 1053 route miles of new fiber and 2293 route miles are upgraded. If all route miles are taken into consideration, the cost per route mile would be $21,450 based on final expenditures. | 0 | N/A | 0 | N/A | 1000 Mbps | No variance | 0 | N/A | 533 Mbps | The network offers 3 speed tiers - 10 Mbps - 306 subscribers connected 100 Mbps - 111 subscribers connected 1000 Mbps - 525 subscribers connected | 0 | N/A | Average speed at the connected entities has increased approximately 1087%, increasing from an average of 4.9 Mbps (as measured across the 940 connected entities) to an average of 533 Mbps. This was calculated based on 321 CAI's having 10 Mbps service and 508 CAI's having no connectivity at all. Once BTOP funded facilities were in place, 111 CAI's increased from 10 Mbps to 1000 Mbps and 508 increased from zero connectivity to 1000 Mbps. Additionally, the improved 321 CAI's while technically not receiving additional bandwidth, benefit dramatically from vastly increased backbone link connectivity that has had a 100% increase in capacity (from single 10Gbps link to two 10Gbps links) as a result of BTOP funds. | None at this time | The project is fully committed to providing access to any entity requesting connection to the network as outlined in the NOFA under Section D.3.b (Nondiscrimination and Interconnection obligations for CCI projects). As of the filing of this report, we have not blocked or limited any subscribers access to service or lawful content at the connected locations. From a network management standpoint, while the network has the inherent capability to perform application separation, traffic prioritization and bandwidth shaping should these requirements be necessary, no limiting or blocking has been implemented. Should the need arise, applicable policies and determination guidelines would be developed and/or revised. As required, these policy changes would be posted as soon as they were completed and ready to implement. | N/A | 22427 | 17760 | 0 | 4712 | 0 | 0 | 0 | N/A | 5088 | 3816 | 0 | 1272 | N/A | N/A | Continual contact with FPO and Grants office has been extremely beneficial and should be emphasized to any current or future grantee as a critical success factor. As the project progressed, many guidance changes occurred and had to be implemented and followed. Without the support of the FPO and Grants office, compliance with these changes would have been difficult if not impossible to achieve. Additionally, be sure that all information, correspondence and documentation that is related to the grant is retained and kept up to date in the grant files. Supporting documentation for everything will smooth the compliance process. Finally, if issues occur, be sure to inform your FPO and Grants officer for their awareness to the situation as soon as possible and seek their assistance as necessary. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time | None at this time
NT10BIX5570153 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1.) N/A 2.) N/A 3.) N/A | 1.) N/A 2.) N/A 3.) N/A Transit Agreements: 1.) N/A 2.) In 2010, OSHEAN provided tentative award to one fiber vendor in Rhode Island and one fiber vendor in Massachusetts. OSHEAN is currently negotiating the terms and conditions of the IRU with both vendors. 3.) N/A
NT10BIX5570153 | 2011 | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | The backbone fiber was not lit as of 2011 Q4. Therefore, no CAIs were provided with service. When connected, broadband service speeds from 1Gbps to 10Gbps will be provided. | Pricing plans have not been provided because fiber deployment is not complete. | Provision of services had not begun as on 2011 Q4. However, an Acceptable Use Policy, Interconnection Policy, Network Management Policy, and Nondiscrimination Policy have been established for the project. | N/A | 15288 | 0 | 0 | 0 | 0 | 0 | 15228 | N/A | 0 | 0 | 0 | 0 | The network was not complete as of 2011 Q4, so interconnections were not yet available. | N/A | None. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1. 0 2. 0 3. No request was denied | 1. 0 2. 0 3. No request was denied
NT10BIX5570153 | 2012 | 52,958 | Average cost is lower than that projected in the baseline. Through competitive bid, OSHEAN was able to secure lower IRU pricing. | 0 | N/A - No last mile provided | 0 | N/A - No last mile provided | 10G | No change | 0 | N/A - No last mile provided | 3G | Per the baseline, OSHEAN is offering a 1G and 10G handoff. 3G is the average handoff speed of CAIs connected as of 12/31/12. | 0 | N/A - No last mile provided | The average increase in broadband speed is 2.5G. This is calculated as the average of the average of broadband speed increases for CAIs receiving new or improved access. | No retail services are being provided by this project. | OSHEAN's network management policy includes provisions stating that bandwidth will not be preferentially allocated or limited to any specific class of users, applications, providers or sources. Except for enforcing contracted bandwidth limits, OSHEAN does not limit bandwidth usage by its users, peers, or providers via mechanisms such as rate limiting or policing. OSHEAN does not restrict a user's access to specific content, block the use of specific applications, or limit the type of devices that can be used to access to network. | No subscribers have dropped bandwidth service. | 18081 | 17337 | 0 | 48 | 0 | 0 | 696 | N/A | 0 | 0 | 0 | 0 | Network providers and/or customers may interconnect with the OSHEAN network at any of the points of interconnection. OSHEAN has also installed slack loops along the backbone routes so that laterals can easily be installed to directly connect to new facilities to the network. | N/A | OSHEAN has utilized IRUs for the procurement of fiber, and found this to be a cost and time savings vehicle. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1. 0 2. 0 3. No request was denied | 1. 0 2. 0 3. No request was denied
NT10BIX5570153 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10G | No change | 0 | N/A | 1.4G | Per the baseline, OSHEAN is offering a 1G and 10G handoff. 1.4G is the average speed of all CAIs included in the final project total. | 0 | N/A | The average increase in broadband speed is 1.0G. This is calculated as the average of the broadband speed increases for all CAIs included in the project. For CAIs where the previous service was being provided by another provider or otherwise unknown, estimates were used. | OSHEAN provides our member organizations with the following retail services under this project (see attachment for current price lists): 1) IP transport services - connectivity of up to 10Gbps per individual site via the BTOP network for IP transport between member locations, to other OSHEAN, regional, and national on-net services, and to OSHEAN POPs for delivery of commodity Internet service. 2) Commodity Internet service which includes multiple upstream ISPs, redundant POP locations, 1.5x burst capability, and unmetered access to Internet2. 3) OSHEAN Safe Harbor service: On-net colocation rack, power, and pipe service for backup and disaster recovery. | OSHEAN's network management policy includes provisions stating that bandwidth will not be preferentially allocated or limited to any specific class of users, applications, providers or sources. Except for enforcing contracted bandwidth limits, OSHEAN does not limit bandwidth usage by its users, peers, or providers via mechanisms such as rate limiting or policing. OSHEAN does not restrict a user's access to specific content, block the use of specific applications, or limit the type of devices that can be used to access to network. | No subscribers have dropped bandwidth service to date. | 20397 | 2399 | 0 | 17998 | 0 | 0 | 0 | OSHEAN makes available wholesale dark fiber, but currently have no wholesale customers and no fiber miles being leased. | 0 | 0 | 0 | 0 | Network providers and/or customers may interconnect with the OSHEAN network at any of the points of interconnection. OSHEAN has also installed slack loops along the backbone routes so that laterals can easily be installed to directly connect to new facilities to the network. | N/A | OSHEAN has utilized IRUs for the procurement of fiber, and found this to be a cost and time savings vehicle. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | N/A - no formal requests have been made to date | As part of the IRU maintenance agreement with Cox Communications, a peering relationship was established providing for settlement free peering between the Cox (RI) network and OSHEAN, allowing traffic destined for each other's network to pass directly without going out to the Internet. This provides better performance for both OSHEAN and Cox customers' local traffic that traverses our networks. This peering connection is being made physically at OSHEAN's AP1 facility at 235 Promenade Street in Providence. In addition, as part of our IRU agreement with the BTOP recipient OpenCape, we have a peering arrangement where they connect to our network at OSHEAN's AP1 facility at 235 Promenade Street in Providence.
NT10BIX5570156 | 2010 | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | n/a The network has not yet been deployed as we are waiting for a Grantee Substitution finalization. Once this is complete, we can begin the Environmental Assessment and Network Design. | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a The network has not yet been deployed so we are not yet at this step. | 0 | 0 | 0 | 0 | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | Due to the pending Grantee Substitution request, we have not spent any grant funds through the fourth quarter. The request should be finalized in January 2011. Because we were the first grant recipient to request this, the process was unclear and there were many starts and stops. The lessons learned were to work closely with the Federal Program Officer and to be extremely flexible with time frame targets whenever engaged in a process that is not part of the normal program processes. | Centennial Board of Cooperative Educational Services | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | n/a | n/a
NT10BIX5570157 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | As the project is still completing the Environmental Assessment, we have not implemented any new fiber. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | As we did not accept the grant until mid-October our experience has been limited. Our primary activities have been centered around establishing all necessary policies, procedures and other foundational aspects in order to properly administer the grant and begin the development of our project. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570157 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | For one CAI, the speed shifted from a standard T1 line to a 10GB/sec connection. For the remaining connections they shifted from 1GB/sec to 10GB/sec. | N/A | The network in question is a closed public safety network. | N/A | 2072 | 40 | 0 | 160 | 1872 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570157 | 2012 | 45,239 | This number varies from the previous APR and Baseline Plan because it was previously believed our project did not count as a Middle Mile provider. Our fiber project connects directly between Community Anchor Institutions, but does not interconnect to fiber provided by 3rd party re-sellers. Therefore, we considered the fiber as "home run" and was unreported. Upon further clarification from the Grants Office, we are now counting this as middle mile connectivity. This number is calculated based on true costs incurred from the installation of the fiber. This is higher than the baseline estimate, because that was an estimate only - it was generated using the install cost of one run of fiber through one specific area. We had no empirical data to use for the various terrains, terrain etc. that would be required when formulating the original project plan. We also had to revise our originally planned route to accommodate changes to the project, and the distance of the new routes did not match original estimates. | 0 | N/A | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | For one CAI, this was the first connectivity they had to the network - 100% increase. Several CAIs were upgraded from a T1 line (1.5 Mbps) to the fiber network (100 Mbps) - 66.6% increase. Another CAI was upgraded from a Microwave connection (50 Mbps) to the fiber network (100 Mpbs) - 50% increase. One additional CAI was added to our list - Southwest Adams County Fire. This was not in our original project plan because it was originally intended as an LTE site alone. We have since formed an agreement with the agency to provide network access through the installed backhaul to our facility and other CAI locations. This CAI will be added to the project plan when the project plan revision is submitted. | N/A | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. This limitation is imposed at the network device connecting to the CAI. Each CAI uses the connection to access servers and data hosted at the ADCOM911 facility, or share data directly between each other. Since this is a closed network that does not link to the internet or other 3rd party network, no other blocking mechanism has been established. | N/A | 871 | 57 | 0 | 646 | 56 | 0 | 112 | N/A | 1570 | 1364 | 0 | 206 | The majority of interconnection and peering points are facilities owned and maintained by Community Anchor Institutions. Those entities allow us to use collocation space in return for us providing them service on the network. We typically connect to each CAI inside their existing data center. Therefore they own their own space, and we do not pay any lease for use of that space. Our project does not include connection to other 3rd party or internet based networks. | N/A | Accurate documentation of each segment of fiber that exists between two interconnection points is critical. Most network diagrams simply list the connectivity between Point A and Point B, without listing any patch panels or interconnections between them. To help facilitate more accurate reporting, and for internal tracking purposes, projects should list the number of strands and distance of those strands between each interconnection point, whether equipment terminates at that location or not. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570157 | 2013 | 40,495 | This number varies from the Baseline Plan because it was previously believed our project did not count as a Middle Mile provider. Our fiber project connects directly between Community Anchor Institutions, but does not interconnect to fiber provided by 3rd party re-sellers. Therefore, we considered the fiber as "home run" and was unreported. Upon further clarification from the Grants Office, we are now counting this as middle mile connectivity. This number is calculated based on true costs incurred from the installation of the fiber. This is higher than the baseline estimate, because that was an estimate only - it was generated using the install cost of one run of fiber through one specific area. We had no empirical data to use for the various terrains, terrain etc. that would be required when formulating the original project plan. We also had to revise our originally planned route to accommodate changes to the project, and the distance of the new routes did not match original estimates. | 0 | N/A | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | The only new connection to a CAI's for 2013 was connected via new fiber optic installed to those locations, which represents a 100% increase. One of the CAI's listed in the 2013 addendum (Adams County Sheriffs Office) had not been reported in previous PPR or APR's. The link had been established in 2011. I am unsure as to why the discrepancy exists, but that CAI was also not listed in the 2012 APR addendum. I have corrected that mistake and it will be accounted for in future reports. The total number of CAI's increased from the 2012 report because of the addition of 5 CAI's which are represented in our route modification. | N/A | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. This limitation is imposed at the network device connecting to the CAI. Each CAI uses the connection to access servers and data hosted at the ADCOM911 facility, or share data directly between each other. Since this is a closed network that does not link to the internet or other 3rd party network, no other blocking mechanism has been established. | N/A | 1290 | 104 | 0 | 1186 | 0 | 0 | 0 | N/A | 1570 | 1364 | 0 | 206 | The majority of interconnection and peering points are facilities owned and maintained by Community Anchor Institutions. Those entities allow us to use collocation space in return for us providing them service on the network. We typically connect to each CAI inside their existing data center. Therefore they own their own space, and we do not pay any lease for use of that space. Our project does not include connection to other 3rd party or internet based networks. | N/A | Accurate documentation of each segment of fiber that exists between two interconnection points is critical. Most network diagrams simply list the connectivity between Point A and Point B, without listing any patch panels or interconnections between them. To help facilitate more accurate reporting, and for internal tracking purposes, projects should list the number of strands and distance of those strands between each interconnection point, whether equipment terminates at that location or not. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570157 | 2014 | 46899 | This number is derived from the fiber that installed during 2014. Essentially the number of miles that was constructed divided by the contract amount. We were able to utilize existing conduit for approximately 40% of the distance so the construction costs were lower than if we had to install conduit for the entire route. | 0 | N/A | 0 | N/A | 100Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | 100Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | Prior to BTOP funds being available to Adams County the majority of our CAI's either had no connect to Adcom or a T1 line. The increase in broadband speed to those institutions would be either 0mbps to 100 mbps or 1.4mbps to 100mbps. Some CAI's have a full GB connection available but for the sake of simplicity a reasonable average of connection speeds would be 100 mbps. | N/A | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. This limitation is imposed at the network device connecting to the CAI. Each CAI uses the connection to access servers and data hosted at the ADCOM911 facility, or share data directly between each other. Since this is a closed network that does not link to the internet or other 3rd party network, no other blocking mechanism has been established. | N/A | 1908 | 130 | 0 | 1778 | 0 | 0 | 0 | N/A | 1570 | 1364 | 0 | 206 | The majority of interconnection and peering points are facilities owned and maintained by Community Anchor Institutions. Those entities allow us to use collocation space in return for us providing them service on the network. We typically connect to each CAI inside their existing data center. Therefore they own their own space, and we do not pay any lease for use of that space. Our project does not include connection to other 3rd party or internet based networks. | N/A | Accurate documentation of each segment of fiber that exists between two interconnection points is critical. Most network diagrams simply list the connectivity between Point A and Point B, without listing any patch panels or interconnections between them. To help facilitate more accurate reporting, and for internal tracking purposes, projects should list the number of strands and distance of those strands between each interconnection point, whether equipment terminates at that location or not. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A
NT10BIX5570158 | 2010 | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Not at this time. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A
NT10BIX5570158 | 2011 | 0 | On July 28, 2011, the LA-RICS Authority Board of Directors passed a motion to cancel the existing procurement. Per Counselâ€™s review, the original procurement for a turn-key system was not in compliance with California Public Contracts Code. The Authority released a new Request for Proposal (RFP) for the Telecommunications System on November 8, 2011. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A
NT10BIX5570158 | 2012 | 0 | While the proposals for the second procurement were being evaluated, HR 3630 was signed into law by President Obama. It mandates public agencies to vacate the T-Band spectrum which had been the cornerstone of the LA-RICS system design. After evaluating different options and deciding on a hybrid system to comply with the new law, the LA-RICS Authority Board decided to cancel the second procurement. A decision was also made to conduct separate procurements for telecom contractors for the Long Term Evolution (LTE) and the Land Mobile Radio (LMR) systems. On October 25, 2012, the RFP for the LMR system was released. Proposals are being evaluated and a contract is expected to be executed by June, 2013. By mid February, 2013, the RFP for the LTE system should be substantially complete pending decision by FirstNet and instructions from NITA. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A
NT10BIX5570158 | 2013 | 0 | In April, 2010, LA-RICS began its first procurement of an LTE contract. During its course, concerns were raised about the request for proposal's compliance with the State of California Public Contracts Code, leading to its cancellation in July, 2011. In November, 2011, the second procurement started and was deep in the evaluation of proposals when Public Law 112-96 was signed by President Obama in February, 2012. The new law mandated public agencies to vacate the T-Band, which is the heart of the LA-RICS system design. The impact on the system design caused the second procurement to be cancelled in August, 2012. Also on May 11, 2012, the NTIA suspended all LTE-related activities and would not lift it until Aug 9, 2013. These events continue to hurt the project's ability to move forward: planned progress in network design, rights of way, construction permits and other approvals have been delayed. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Contracting Lessons regarding Site Selection to facilitate environmental clearances: Specifying a list of sites known to have least environmental issues and mandating vendors to use all sites enabled evaluators to analyze system capabilities, site lists, and costs on an equal platform. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A
NT10BIX5570158 | 2014 | 0 | LA-RICS executed a contract with Motorola Solutions, Inc. on March 6, 2014 for the design and build out of the Public Safety Broadband Network. The State Historic Preservation Officer issued a Finding of No Significant Impact for the project on October 15, 2014, paving the way for construction to start in December, 2014. At this early point, no cost figures will be reported for this period. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | The public safety broadband network is currently under construction and no community anchor institution has been added. | This project will not be providing retail services. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Community Outreach. When planning outreach activities, a wider net should be cast to include stakeholder unions in long-range outreach programs. This was validated when construction start was delayed after labor unions expressed concerns over the installation of PSBN cell towers at fire stations and how the prolonged exposure to radio frequency emissions could affect the health and safety of firefighters. It is highly probable that if the labor unions are included in the long rang plan, the project will likely receive their support with site design and preserve implementation as scheduled. The lesson also makes a case for having an effective outreach process in place addressing RF exposure as it pertains to health and safety concerns. Thus, when an organization envisions that a project has the potential for encountering health and safety challenges from local stakeholders, it is imperative of the organization to include such issues as part of the long-range outreach strategic plan. | Los Angeles Regional Interoperable Communications System Authority | 0 | 0 | 0 | 0 | 0 | 454 |  | 0 | 0 | 0 | 454 | N/A | N/A
NT11BIX5570001 | 2011 | 0 | n/a. No construction in 2011. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | Will offer 1G as norm; some future subscribers may request up to 10 G. | 0 | n/a. Middle mile network only. | 93 | Current subscribers averaging 93.29 mbps. | 0 | n/a. Middle mile network only. | n/a. | n/a. EAGLE-Net is a middle-mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/Support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing infrastructure or on proposed BTOP infrastructure. | n/a. | 6776 | 392 | 0 | 3300 | 3084 | 0 | 0 | n/a. | 0 | 0 | 0 | 0 | Currently lease rack space in 8 locations plus a room in our own leased building space. Square footage of facilities, total leased and available space is unknown. Locations are: Comfluent: 3 racks. Point of Interconnection Type: POP. Longmont-CBOCES: 2 racks. Point of Interconnection Type: Internet Exchange Point. Longmont-Kimbark: 1 rack. Point of Interconnection Type: POP. Tri-State: 4 racks. Point of Interconnection Type: Internet Exchange Point. FRGP: 1 rack. Point of Interconnection Type: POP Zayo: 5 racks. Point of Interconnection Type: Internet Exchange Point. Level 3: 1 rack. Point of Interconnection Type: POP. tw telecom: 2 racks. Point of Interconnection Type: POP. EAGLE-Net Alliance: 4 racks and 153 sq feet in server room of our office. Point of Interconnection Type: Internet Exchange Point. | n/a. | Two main things come to mine: 1. Hire a good, experienced contractor. The knowledge provided by our design/build contractor, G4S Technologies has been invaluable in this process. 2. The procurement process can often take longer than anticipated, so make sure that you plan on sufficient lead time to meet your deadlines. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | n/a. | n/a.
NT11BIX5570001 | 2012 | 49036 | This calculation is based on 660 miles of completed new fiber construction in several areas of the state. Variance to baseline is mostly based on change from microwave to fiber build in most areas of the state. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | We offer 1G as the norm; some future subscribers may request up to 10G. | 0 | n/a. Middle mile network only. | 76.2 | For current subscribers, the highest speed currently requested is 500mbps and the lowest is 10mbps. | 0 | n/a. Middle mile network only. | The average increase in broadband speed to CAI's has varied from entities that have received 20 Mbps increases to CAI's that have received 300 Mbps increases in broadband speed. | n/a. EAGLE-Net is a middle-mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing intrastructure or on proposed BTOP infrastructure. | 1 CAI. School district now purchases service from the local provider, although EAGLE-Net now supplies service to the local provider for this customer. | 38944 | 3712 | 0 | 23584 | 1165 | 0 | 10483 | n/a. No dark fiber leased out at this time. | 0 | 0 | 0 | 0 | Currently lease rack space in several locations throughout the state. Locations are: Colorado Springs POI: 1 rack, 4 sq feet 910 15th St Denver POI: 1 rack, 4 sq feet Akron POI: 1 rack, 4 sq feet Aurora POP: 2 racks, 8 sq feet Byers POI: 1 rack, 4 sq feet Cheyenne Wells POI: 1 rack, 4 sq feet Flagler POI: 1 rack, 4 sq feet Fort Morgan POI: 1 rack, 4 sq feet Limon POI: 1 rack, 4 sq feet Prospect Valley POI: 1 rack, 4 sq feet Pueblo Peer: 1 rack, 4 sq feet Rifle POI: 1 rack, 4 sq feet Sterling POI: 1 rack, 4 sq feet Wray POI: 1 rack, 4 sq feet Cahone POI: 1 rack, 4 sq feet Durango POP: 1 rack, 4 sq feet Empire POI: 1 rack, 4 sq feet Montrose POI: 1 rack, 4 sq feet Nucla POI: 1 rack, 4 sq feet Haystack Butte POI: 1 rack, 4 sq feet Lynn POI: 1 rack, 4 sq feet Pueblo DC POI: 4 racks, 16 sq feet, 200 sq feet available Pueblo Peer: 1 rack, 4 sq feet Grand Junction Peer: 1 rack, 4 sq feet Durango Peer: 1 rack, 4 sq feet Denver Peer: 4 racks, 16 sq feet Colorado Springs Peer: 3 racks, 12 sq feet, 400 sq feet available | n/a | The building of a large network such as our statewide project will result in many changes from the original plan and design for many reasons. Our primary lesson learned is to ensure that all changes are discussed in detail and approved. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | EAGLE-Net currently has 8 interconnection agreements and is in negotiations for 5 more. No requested agreements have been denied. | EAGLE-Net currently has 1 Peering agreement and is in negotiations for 6 more. No requested agreements have been denied.
NT11BIX5570001 | 2013 | 44,212 | This calculation is based on 809 miles of completed new fiber construction in several areas of the state. Variance to baseline is mostly based on change from microwave to fiber build in most areas of the state. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | We offer 1G as the norm; some future subscribers may request up to 10G. | 0 | n/a. Middle mile network only. | 107.7 | For current subscribers, the highest speed currently requested is 800mbps and the lowest is 10mbps. | 0 | n/a. Middle mile network only. | The average increase in broadband speed to CAI's has varied from entities that have received 20 Mbps increases to CAI's that have received 300 Mbps increases in broadband speed. | n/a. EAGLE-Net is a middle mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing intrastructure or on proposed BTOP infrastructure. | No subscribers dropped EAGLE-Net service during this year. | 37656 | 3860 | 0 | 27790 | 104 | 3456 | 2446 | n/a. No dark fiber leased at this time. | 0 | 0 | 0 | 0 | Currently lease rack space in several locations throughout the state. Locations are: Colorado Springs POI: 1 rack, 4 sq feet 910 15th St Denver POI: 1 rack, 4 sq feet Akron POI: 1 rack, 4 sq feet Aurora POP: 2 racks, 8 sq feet Byers POI: 1 rack, 4 sq feet Cheyenne Wells POI: 1 rack, 4 sq feet Flagler POI: 1 rack, 4 sq feet Fort Morgan POI: 1 rack, 4 sq feet Limon POI: 1 rack, 4 sq feet Prospect Valley POI: 1 rack, 4 sq feet Pueblo Peer: 1 rack, 4 sq feet Rifle POI: 1 rack, 4 sq feet Sterling POI: 1 rack, 4 sq feet Wray POI: 1 rack, 4 sq feet Cahone POI: 1 rack, 4 sq feet Durango POP: 1 rack, 4 sq feet Empire POI: 1 rack, 4 sq feet Montrose POI: 1 rack, 4 sq feet Nucla POI: 1 rack, 4 sq feet Haystack Butte POI: 1 rack, 4 sq feet Lynn POI: 1 rack, 4 sq feet Pueblo DC POI: 4 racks, 16 sq feet, 200 sq feet available Pueblo Peer: 1 rack, 4 sq feet Grand Junction Peer: 1 rack, 4 sq feet Durango Peer: 1 rack, 4 sq feet Denver Peer: 4 racks, 16 sq feet Colorado Springs Peer: 3 racks, 12 sq feet, 400 sq feet available Craig POI: 1 rack, 4 sq feet | n/a. | One of our key decisions was to sign an agreement with a network operator. This process started with an Invitation to Negotiate for interested parties to become involved. The end result was definitely what we wanted and it is working out very well for both parties. However, if a grantee intends to follow a similar process, please be sure to anticipate the amount of time and resources that the process may take, as it can become very time consuming. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | EAGLE-Net currently has eight service agreements with wholesale and last mile providers to whom it is providing service. In addition, it has 26 signed Master Service Agreements that provide the framework for future service agreements, and it is in negotiations with another 33 providers for future agreements. No requests for interconnection have been denied. | EAGLE-Net currently has service agreements with seven providers from whom it is purchasing peering and transit services. No other agreements are currently being negotiated to obtain additional transit services.
NT11BIX5570001 | 2014 | 50973 | This calculation is based on 795 miles of completed new construction in several areas of the state. Variance to baseline is mostly based on change from microwave to fiber build in most areas of the state. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | We offer 1G as the norm; some future subscribers may request up to 10G. | 0 | n/a. Middle mile network only. | 131.0 | For current subscribers, the highest speed currently requested is 1000mbps and the lowest is 10mbps. | 0 | n/a. Middle mile network only. | The average increase in broadband speed to CAIs has varied from entities that have received 20 Mbps increases to CAIs that have received 500 Mbps in broadband speed. | n/a. EAGLE-Net is a middle mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing intrastructure or on proposed BTOP infrastructure. | Three subscribers dropped EAGLE-Net service in 2014. Two of these were both school districts that received lower bids for services based on their e-Rate 470 requisitions. In one instance, EAGLE-Net was using a third-party circuit to provide service and we could not provide a lower bid to compete. In the other instance, we were simply underbid by a larger provider. The third was a school district using EAGLE-Net as a secondary provider for a special project. The project ended, so they stopped purchasing the service. These three CAIs represented a 4.3% loss of our total customers. | 49986 | 8536 | 21849 | 17469 | 482 | 384 | 1266 | [REDACTED] | 0 | 0 | 0 | 0 | Currently lease rack space in several locations throughout the state. Locations are: Colorado Springs POI: 1 rack, 4 sq feet 910 15th St Denver POI: 1 rack, 4 sq feet Akron POI: 1 rack, 4 sq feet Aurora POP: 2 racks, 8 sq feet Byers POI: 1 rack, 4 sq feet Cheyenne Wells POI: 1 rack, 4 sq feet Flagler POI: 1 rack, 4 sq feet Fort Morgan POI: 1 rack, 4 sq feet Limon POI: 1 rack, 4 sq feet Prospect Valley POI: 1 rack, 4 sq feet Pueblo Peer: 1 rack, 4 sq feet Rifle POI: 1 rack, 4 sq feet Sterling POI: 1 rack, 4 sq feet Wray POI: 1 rack, 4 sq feet Cahone POI: 1 rack, 4 sq feet Durango POP: 1 rack, 4 sq feet Empire POI: 1 rack, 4 sq feet Montrose POI: 1 rack, 4 sq feet Nucla POI: 1 rack, 4 sq feet Haystack Butte POI: 1 rack, 4 sq feet Lynn POI: 1 rack, 4 sq feet Pueblo DC POI: 4 racks, 16 sq feet, 200 sq feet available Pueblo Peer: 1 rack, 4 sq feet Grand Junction Peer: 1 rack, 4 sq feet Durango Peer: 1 rack, 4 sq feet Denver Peer: 4 racks, 16 sq feet Colorado Springs Peer: 3 racks, 12 sq feet, 400 sq feet available Craig POI: 1 rack, 4 sq feet Kersey Peer: 1 rack, 4 sq feet Kimbark POI: 1 rack, 4 sq feet Rockport POI: 1 rack, 4 sq feet Steamboat Springs POI: 1 rack, 4 sq feet | n/a. | Budget carefully, and with a large contingency built in to the projections. Surprises are always bound to happen, and can affect the budget in a significant way. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | EAGLE-Net currently has eighteen service agreements with wholesale and last mile providers to whom it is providing service. We have 29 signed Master Service Agreements that provide the framework for future service agreements, and we are in current negotiations with another 17 providers for future agreements. No requests for interconnection have been denied. Now that we have a network operator actively marketing for wholesale agreements, and as the network has grown and is being completed, there is an increased awareness by other providers of the opportunities available with the EAGLE-Net network throughout Colorado. | EAGLE-Net currently has service agreements with eight providers from whom it is purchasing peering and transit services. No other agreements are currently being negotiated to obtain additional transit services.
NT12BIX5570001 | 2012 | $54,263.56 | Based on the miles constructed versus estimated funds to Zayo is tracking on budget. | 0 | N/A | 0 | N/A | 10G | This matches our baseline. | 0 | N/A | 1G | This matches our baseline. | 0 | N/A | 10 GBPS based on the unserved areas | This is a middle mile project. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application and we have never prevented any customer from attaching any legal devise to our network.. | 0 | 64128 | 1334 | 298 | 62399 | 1 | 2 | 94 | Comcast Cable - 17, Extenet Systems - 12, I-Light - 692, Windstream - 210, Lightbound - 45, Smithville Digital - 146, ETC/Sunman - 16, Trelleborg - 14.5, | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build. | 4 - Gray and Pape, Eustis Cable, Baseline NXC, ECOP Cable | From the sales perspective, it's important to engage with any prospects, whether CAIs or wholesale companies, early on. We found that the wholesale customer understand the challenges faced with any build, and will therefore order early and wait on delivery. CAIs, however, need to understand that the project is done before committing to using service. | Zayo Group, LLC | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 9 | 38 agreement, combination of both lit and dark services. Currently negotiating 57 agreements. We have denied no request for interconnection. | Zayo does not enter into Peering and Transit Agreements, except at the national level, which is not impacted by Indiana's assets.
NT12BIX5570002 | 2012 | $65,077/10G | Based on the miles constructed versus estimated funds to Zayo is tracking on budget. | 0 | N/A | 0 | N/A | 10G | This matches our baseline. | 0 | N/A | 1G | This matches our baseline. | 0 | N/A | 10 GBPS based on the unserved areas | Current retail services are 0. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application and we have never prevented any customer from attaching any legal devise to our network.. | 0 | 35532 | 1952 | 3112 | 12702 | 0 | 0 | 17766 | Anoka County for 12 Dark Fibers in the core ring as well as 4 dark fibers throughout the distribution network. | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build, or the Zayo existing POP site located at 511 11th Ave South Suite 110 Minneapolis, MN | 4 - Fiber Engineering and Design, Entagon, Power and Telephone, ECOP Cable | N/A | Zayo Group, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 53 | 0 | 131 | Zayo current agreements - Anoka County IRU Agreement also Master Services Agreement. 0 Negotiating - Zayo has not denied any request for services. | 0 - Currently, 0 - Negotiating, Zayo has not denied any request for services.
NT12BIX5570002 | 2013 | $ 68,148.00 | Based on the miles constructed versus estimated, projected funds. Baseline was $ 67,065.00, variation there from is generally due to geotech matters, i.e., having to bore around a previously unidentified underground obstacles. | 0 | N/A | 0 | N/A | 0 | Zayo provides dark fiber only, which supports speeds up to 100G as determined by the optronix the last mile provider chooses to install. Anoka County provides 10G to its CAI customers. | 0 | N/A | 0 | Zayo provides dark fiber only, which supports speeds up to 100G as determined by the optronix the last mile provider chooses to install. Anoka County provides 10G to its CAI customers. | 0 | N/A | Zayo is only providing dark fiber facilities, it is not providing lit services. Dark fiber installed is capable of supporting up to 100G depending upon the optronix Anoka, or any other dark fiber customer choses to install. Anoka has installed its own optronix and is currently providing 10G service over the dark fiber they lit to the CAIs. Average increase in speed in entirely dependent what service they previously had and same was not provided by Zayo, thus Zayo has no way of calculating an average increase in speed. | Zayo does not provide retail services and thus does not maintain any pricing plans. CAIs are billed by Anoka County, not by Zayo, as Anoka County provides the lit services, Zayo only provides dark fiber facilities. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application, and we have never prevented any customer from attaching any legal devices to our network. | 0 | 35532 | 1952 | 3112 | 30468 | 0 | 0 | 0 | Anoka County, MN. 3,112 strand miles, 215 route miles. | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build. | 4 - Fiber Engineering and Design, Entagon, Power and Telephone, and ECOP Cable. | The BTOP reporting requirements and their deadlines are uniform regardless of the size of the project whether it is a 1 mile project or a 500 mile project. It is not reasonable to require such large projects to be reported within the same time frame as smaller projects and it places a significant paperwork and labor burden on the recipient. It particularly places socially and economically disadvantaged business concerns in jeopardy as they do not always have the resources available to compile the required data and prepare the required reports within such short time frames while struggling to support all customers. We encountered significant permitting delays from local permitting agencies. | Zayo Group, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 53 | 0 | 131 | (1) As of the project end, 6/30/2013, Zayo had a dark fiber, and master service agreement for technical, field, and engineering services, with Anoka County only. (2) None. (3) Zayo has not denied any requests for services. | 0 - Currently, 0 - Negotiating, Zayo has not denied any request for services.
NT12BIX5570002 | 2014 | $ 68,148.00 | Based on the miles constructed versus estimated, projected funds. Baseline was $ 67,065.00, variation there form is generally due to geotech matters, i.e., having to bore around a previously unidentified underground obstacles. | 0 | N/A | 0 | N/A | 0G | Zayo is only providing dark fiber that supports any speed Anoka, or any customer desires up to 100G by their own optronix the chose to install. Anoka is providing 10G to its customers, the CAIs, which is what our baseline meant. | 0 | N/A | 0G | Zayo is providing only dark fiber. Average broadband speed is contingent on the optronix the customer installed to light the fiber. | 0 | N/A | Zayo is only providing dark fiber facilities, it is not providing lit services. Dark fiber installed is capable of supporting up to 100G depending upon the optronix Anoka, or any other dark fiber customer choses to install. Anoka has installed its own optronix and is currently providing 10G service over the dark fiber they lit to the CAIs. Average increase in speed in entirely dependent what service they previously had and same was not provided by Zayo, thus Zayo has no way of calculating an average increase in speed. | Zayo does not provide retail services and thus does not maintain any pricing plans. CAIs are billed by Anoka County, not by Zayo, as Anoka County provides the lit services, Zayo only provides dark fiber facilities. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application, and we have never prevented any customer from attaching any legal devices to our network. | 0 | 35532 | 1952 | 3112 | 30468 | 0 | 0 | 0 | Anoka County, MN. 3,112. | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build. | 4 - Fiber Engineering and Design, Entagon, Power and Telephone, and ECOP Cable. | The BTOP reporting requirements and their deadlines are uniform regardless of the size of the project whether it is a 1 mile project or a 500 mile project. It is not reasonable to require such large projects to be reported within the same time frame as smaller projects and it places a significant paperwork and labor burden on the recipient. It particularly places socially and economically disadvantaged business concerns in jeopardy as they do not always have the resources available to compile the required data and prepare the required reports within such short time frames while struggling to support all customers. We encountered significant permitting delays from local permitting agencies. | Zayo Group, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 53 | 0 | 131 | Zayo current agreements Anoka County IRU Agreement for the dark fiber facilities, also Master Services Agreement for technical field services, engineering services. 0 Negotiating - Zayo has not denied any request for services. | 0 - Currently, 0 - Negotiating, Zayo has not denied any request for services.