## CCI Data Dictionary
CCI Performance Progress Report Data
CCI Quarterly Key Indicators
CCI Quarterly Milestones (Actual (This Quarter) and Projected (Next Quarter))
CCI Quarterly Budget Information
CCI Annual Performance Progress Report Data
CCI Annual Report Data
CCI Quarterly Key Indicators (see Tab CCI_KeyIndicators_Actuals)
| Database Field | Report Heading | Description
| Award_Num | Award Number | The 10 digit grant award number listed on the CD-450 form
| Year | Year | Year of the reporting period
| Quarter | Quarter | Quarter of the reporting period
| YearQuarter | Reporting Period | Combination of the year and quarter of the reporting period
| Project_Indicator_Desc | Project Indicators (Project Accomplishments) | Narrative to describe significant project accomplishments completed during the quarter, which can be described quantitatively or qualitatively
| NetMileDeploy_Num | New Network Miles Deployed | Cumulative number of new network miles deployed
| NetMileLease_Num | New Network Miles Leased | Cumulative number of new network miles leased
| ExistMileUpgrade_Num | Existing Network Miles Upgraded | Cumulative number of existing network miles upgraded
| ExistMileLease_Num | Existing Network Miles Leased | Cumulative number of existing network miles leased
| FiberMile_Num | New Fiber Miles | Cumulative number for new fiber miles
| WirelessLinks_Num | New Wireless Links | Cumulative number for new wireless links
| Towers_Num | New Towers | Cumulative number of new towers
| InterconnectPoints_Num | New and Upgraded Interconnection Points | Cumulative number of new and upgraded interconnection points
| NetMileDeploy_Desc | New Network Miles Deployed Description | Describes any delays in deploying new miles, reasons for variance, and plan for catching up to baseline
| NetMileLease_Desc | New Network Miles Leased Description | Describes any delays in leasing new miles, reasons for variance, and plan for catching up to baseline
| ExistMileUpgrade_Desc | Existing Network Miles Upgraded Description | Describes any delays in upgrading existing miles, reasons for variance, and plan for catching up to baseline
| ExistMileLease_Desc | Existing Network Miles Leased Description | Describes any delays in leasing existing miles, reasons for variance, and plan for catching up to baseline
| FiberMile_Desc | New Fiber Miles Description | Describes any delays in deploying new miles of fiber, reasons for variance, and plan for catching up to baseline
| WirelessLinks_Desc | New Wireless Links Description | Describes any delays in deploying new wireless links, reasons for variance, and plan for catching up to baseline
| Towers_Desc | New Towers Description | Describes any delays in deploying new towers, reasons for variance, and plan for catching up to baseline
| InterconnectPoints_Desc | New and Upgraded Interconnection Points Description | Describes any delays in deploying new or upgraded interconnection points, reasons for variance, and plan for catching up to baseline
| SignAgreemnt_Num | Number of Signed Agreements | Total number of signed agreements with broadband wholesalers and/or last mile providers since the inception of the project
| PotentAgreemnt_Num | Number of Potential Agreements | Total number of agreements currently in negotiation (not cumulative) with broadband wholesalers and/or last mile providers
| AvgTermAgreemnt_Num | Average Term Agreement | Average term of the signed agreements with broadband wholesalers and/or last mile providers, in quarters
| Providers_List_Desc | Providers Description | Names of the wholesale and last mile providers with signed agreements
| WholeService_Desc | Wholesale Services Description | Describes any wholesale services that are being provided by the project
| ThirdParty_Info_Desc | Third Party Information Description | Includes information about any third party designated to operate all or a portion of the network, including name and contact info, portion operated, and relationship
| Providrs_NewAccess_Num | Providers with New Access | Cumulative number of signed agreements with providers receiving new access
| Providrs_ImprAccess_Num | Providers with Improved Access | Cumulative number of signed agreements with providers receiving improved access
| Providrs_FiberAccess_Num | Providers with Access to Dark Fiber | Cumulative number of signed agreements with providers receiving access to dark fiber
| Providrs_SpeedTier_Num | Provider Speed Tiers | Number of speed tiers that are available to providers
| Providrs_NewAccess_Desc | Providers with New Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding providers with new access
| Providrs_ImprAccess_Desc | Providers with Improved Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding providers with improved access
| Providrs_FiberAccess_Desc | Providers with Access to Dark Fiber Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding providers with access to dark fiber
| Providrs_SpeedTier_Desc | Provider Speed Tiers Description | Describes the speed tiers that are available to providers
| ComInst_Total_Num | Total Subscribers Served | Total number of subscribers (CAIs) served
| ComInst_NewAccess_Num | Subscribers with New Access | Cumulative number of subscribers (CAIs) receiving new access
| ComInst_ImprAccess_Num | Subscribers with Improved Access | Cumulative number of subscribers (CAIs) receiving improved access
| ComInst_SpeedTier_Num | Subscriber Speed Tiers | Number of speed tiers that are available to subscribers (CAIs)
| ComInst_Total_Desc | Total Subscribers Served Description | Describes any variance between the actual figure and baseline target regarding total subscribers (CAIs) served
| ComInst_NewAccess_Desc | Subscribers with New Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding subscribers (CAIs) with new access
| ComInst_ImprAccess_Desc | Subscribers with Improved Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding subscribers (CAIs) with improved access
| ComInst_SpeedTier_Desc | Subscriber Speed Tiers Description | Describes the speed tiers that are available to subscribers (CAIs)
| Househld_Entity_Num | Household Entities Passed | Total number of households passed (not connected)
| Househld_Total_Num | Household Total Subscribers | Cumulative number of household subscribers
| Househld_NewAccess_Num | Household Subscribers with New Access | Cumulative number of household subscribers receiving new access
| Househld_ImprAccess_Num | Household Subscribers with Improved Access | Cumulative number of household subscribers receiving improved access
| Househld_SpeedTier_Num | Household Subscribers Speed Tiers | Number of speed tiers that are available to household subscribers
| HouseHld_Entity_Desc | Household Entities Passed Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding households passed
| Househld_Total_Desc | Household Total Subscribers Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding household subscribers (total)
| HouseHld_NewAccess_Desc | Household Subscribers with New Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding household subscribers with new access
| Househld_ImprAccess_Desc | Household Subscribers with Improved Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding household subscribers with improved access
| Househld_SpeedTier_Desc | Household Subscribers Speed Tiers Description | Describes the speed tiers that are available to household subscribers
| Business_Entity_Num | Business Entities Passed | Total number of businesses passed (not connected)
| Business_Total_Num | Business Total Subscribers | Cumulative number of business subscribers
| Business_NewAccess_Num | Business Subscribers with New Access | Cumulative number of business subscribers receiving new access
| Business_ImprAccess_Num | Business Subscribers with Improved Access | Cumulative number of business subscribers receiving improved access
| Business_SpeedTier_Num | Business Subscribers Speed Tiers | Number of speed tiers that are available to business subscribers
| Business_Entity_Desc | Business Entities Passed Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding businesses passed
| Business_Total_Desc | Business Total Subscribers Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding businesses subscribers (total)
| Business_NewAccess_Desc | Business Subscribers with New Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding business subscribers with new access
| Business_ImprAccess_Desc | Business Subscribers with Improved Access Description | Describes any variance between the actual figure and baseline target and any other relevant information regarding business subscribers with improved access
| Business_SpeedTier_Desc | Business Subscribers Speed Tiers Description | Describes the speed tiers that are available to business subscribers
| SpecialOffer_Desc | Special Offerings Description | Description of any special offerings that the recipient may provide
| PracticeChange_Ind | Management Practice Changes | Indicates any changes in network management practices
| PracticeChange_Desc | Management Practice Changes Description | Description of any change in network management practices during the reporting period
| ProjectPlanned_Accomplish_Desc | Project Planned Accomplishments | Narrative to describe significant project activities or accomplishments planned for completion during the next quarter
| Recipient | Recipient | The name of the recipient organization
| Current_Milestone_Challenges | Current Challenges | Narrative to describe any challenges or issues faced during the past quarter that impacted planned progress against the project milestones
| Next_Milestone_Challenges | Next Quarter Challenges | Narrative to describe any challenges or issues anticipated during the next quarter that may impact planned progress against the project milestones
CCI Quarterly Milestones (Actual (This Quarter) and Projected (Next Quarter)) (See Tabs CCI_MileStones_Actuals and CCI_MileStones_Projected)
| Database Field | Heading | Description
| award_num | Award Number | The 10 digit grant award number listed on the CD-450 form
| Year_Desc | Year | Year of the reporting period
| Quarter_Cd | Quarter | Quarter of the reporting period
| YearQuarter | Reporting Period | Combination of the year and quarter of the reporting period
| Milestone_Id | Milestone ID | Milestone Identifier
| PPRMain_Id | PPR ID | PPR Identifier
| ProjOverall_Prcnt_Amt | Overall Project Percent Complete | Percentage complete for the overall project (based on budget expenditure)
| ProjOverall_Narrtv_Desc | Overall Project Narrative | Narrative to describe any variance between actual percent competed and target provided in the baseline plan for the overall project
| OtherMilstone_Prcnt_Amt | Other Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| OtherMilstone_Specify_Desc | Other Description | Specification of the Other milestone
| OtherMilstone_Narrtv_Desc | Other Narrative | A brief description of the primary activities involved in meeting the Other milestone
| EnvmntAssessmnt_Prcnt_Amt | Environmental Assessment Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| EnvmntAssessmnt_Narrtv_Desc | Environmental Assessment Narrative | A brief description of the primary activities involved in meeting the Environmental Assessment milestone
| NetworkDesign_Prcnt_Amt | Network Design Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| NetworkDesign_Narrtv_Desc | Network Design Narrative | A brief description of the primary activities involved in meeting the Network Design milestone
| RightsofWay_Prcnt_Amt | Rights of Way Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| RightsofWay_Narrtv_Desc | Rights of Way Narrative | A brief description of the primary activities involved in meeting the Rights of Way milestone
| ConstructPermit_Prcnt_Amt | Construction Permits and Other Approvals Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| ConstructPermit_Narrtv_Desc | Construction Permits and Other Approvals Narrative | A brief description of the primary activities involved in meeting the Construction Permits and Other Approvals milestone
| SitePreprtn_Prcnt_Amt | Sire Preparation Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| SitePreprtn_Narrtv_Desc | Site Preparation Narrative | A brief description of the primary activities involved in meeting the Site Preparation milestone
| EquipProcurmnt_Prcnt_Amt | Equipment Procurement Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| EquipProcurmnt_Narrtv_Desc | Equipment Procurement Narrative | A brief description of the primary activities involved in meeting the Equipment Procurement milestone
| NetworkBuild_Prcnt_Amt | Network Build Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| NetworkBuild_Narrtv_Desc | Network Build Narrative | A brief description of the primary activities involved in meeting the Network Build milestone
| EquipDeploy_Prcnt_Amt | Equipment Deployment Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| EquipDeploy_Narrtv_Desc | Equipment Deployment Narrative | A brief description of the primary activities involved in meeting the Equipment Deployment milestone
| NetworkTest_Prcnt_Amt | Network Testing Percent Complete | Percentage of completion, based primarily on the expenditure of the project budget and reported cumulatively from award inception through the end of the reporting quarter
| NetworkTest_Narrtv_Desc | Network Testing Narrative | A brief description of the primary activities involved in meeting the Network Testing milestone
| Created_Date | Created Date | Date the PPR was created
| Modified_Date | Modified Date | Date the PPR was last modified
| Created_Person_Id | Created Person ID | Identifier (Number) of person that created the PPR
| Modified_Person_Id | Modified Person ID | Identifier (Number) of person that last modified the PPR
| Recipient | Recipient | Name of the recipient organization
CCI Quarterly Budget Information (see Tab CCI_Expenditures)
| Database Field | Heading | Description
| Award_Num | Award Number | The 10 digit grant award number listed on the CD-450 form
| ProjectType_Cd | Project Type Code | Identifier for CCI, PCC, or SBA awards
| Year_Desc | Year | Year of the reporting period
| Quarter_Cd | Quarter | Quarter of the reporting period
| YearQuarter | Reporting Year and Quarter | Combination of the year and quarter of the reporting period
| TotCostPlan_Equipmnt_Amt | Equipment - Total Costs Budgeted | Total amount budgeted for equipment expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_Equipmnt_Amt | Equipment - Matching Funds Budgeted | Total amount of matching funds budgeted for equipment expenditures
| FedFundPlan_Equipmnt_Amt | Equipment - Federal Funds Budgeted | Total amount of federal funds budgeted for equipment expenditures
Created_Dat+A122:A123e | TotCostActl_Equipmnt_Amt | Equipment - Total Costs Actual | Total amount of funds used for equipment expenses from the project's inception through the end of the current reporting period
| MatchFundActl_Equipmnt_Amt | Equipment - Matching Funds Actual | Amount of matching funds used for equipment expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_Equipmnt_Amt | Equipment - Federal Funds Actual | Amount of federal funds used for equipment expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_Equipmnt_Amt | Equipment - Total Costs Anticipated | Total amount of funds anticipated for equipment expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_Equipmnt_Amt | Equipment - Matching Funds Anticipated | Amount of matching funds anticipated for equipment expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_Equipmnt_Amt | Equipment - Federal Funds Anticipated | Amount of federal funds anticipated for equipment expenses from the projects inception through the end of the next reporting period
| TotCostPlan_Constructn_Amt | Construction - Total Costs Budgeted | Total amount budgeted for construction expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_Constructn_Amt | Construction - Matching Funds Budgeted | Total amount of matching funds budgeted for construction expenditures
| FedFundPlan_Constructn_Amt | Construction - Federal Funds Budgeted | Total amount of federal funds budgeted for construction expenditures
| TotCostActl_Constructn_Amt | Construction - Total Costs Actual | Total amount of funds used for construction expenses from the project's inception through the end of the current reporting period
| MatchFundActl_Constructn_Amt | Construction - Matching Funds Actual | Amount of matching funds used for construction expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_Constructn_Amt | Construction - Federal Funds Actual | Amount of federal funds used for construction expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_Constructn_Amt | Construction - Total Costs Anticipated | Total amount of funds anticipated for construction expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_Constructn_Amt | Construction - Matching Funds Anticipated | Amount of matching funds anticipated for construction expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_Constructn_Amt | Construction - Federal Funds Anticipated | Amount of federal funds anticipated for construction expenses from the projects inception through the end of the next reporting period
| TotCostPlan_LegalExp_Amt | Administrative and Legal - Total Costs Budgeted | Amount budgeted for administrative and legal expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_LegalExp_Amt | Administrative and Legal - Matching Funds Budgeted | Total amount of matching funds budgeted for administrative and legal expenditures
| FedFundPlan_LegalExp_Amt | Administrative and Legal - Federal Funds Budgeted | Total amount of federal funds budgeted for administrative and legal expenditures
| TotCostActl_LegalExp_Amt | Administrative and Legal - Total Costs Actual | Total amount of funds used for administrative and legal expenses from the project's inception through the end of the current reporting period
| MatchFundActl_LegalExp_Amt | Administrative and Legal - Matching Funds Actual | Amount of matching funds used for administrative and legal expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_LegalExp_Amt | Administrative and Legal - Federal Funds Actual | Amount of federal funds used for administrative and legal expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_LegalExp_Amt | Administrative and Legal - Total Costs Anticipated | Total amount of funds anticipated for administrative and legal expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_LegalExp_Amt | Administrative and Legal - Matching Funds Anticipated | Amount of matching funds anticipated for administrative and legal expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_LegalExp_Amt | Administrative and Legal - Federal Funds Anticipated | Amount of federal funds anticipated for administrative and legal expenses from the projects inception through the end of the next reporting period
| TotCostPlan_LandApprsl_Amt | Land Structures Right of Ways - Total Costs Budgeted | Total amount budgeted for land structures right of ways expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_LandApprsl_Amt | Land Structures Right of Ways - Matching Funds Budgeted | Total amount of matching funds budgeted for land structures right of ways expenditures
| FedFundPlan_LandApprsl_Amt | Land Structures Right of Ways - Federal Funds Budgeted | Total amount of federal funds budgeted for land structures right of ways expenditures
| TotCostActl_LandApprsl_Amt | Land Structures Right of Ways - Total Costs Actual | Total amount of funds used for land structures right of ways expenses from the project's inception through the end of the current reporting period
| MatchFundActl_LandApprsl_Amt | Land Structures Right of Ways - Matching Funds Actual | Amount of matching funds used for land structures right of ways expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_LandApprsl_Amt | Land Structures Right of Ways - Federal Funds Actual | Amount of federal funds used for land structures right of ways expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_LandApprsl_Amt | Land Structures Right of Ways - Total Costs Anticipated | Amount of funds anticipated for land structures right of ways expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_LandApprsl_Amt | Land Structures Right of Ways - Matching Funds Anticipated | Amount of matching funds anticipated for land structures right of ways expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_LandApprsl_Amt | Land Structures Right of Ways - Federal Funds Anticipated | Amount of federal funds anticipated for land structures right of ways expenses from the projects inception through the end of the next reporting period
| TotCostPlan_RelocExp_Amt | Relocation - Total Costs Budgeted | Total amount budgeted for relocation expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_RelocExp_Amt | Relocation - Matching Funds Budgeted | Total amount of matching funds budgeted for relocation expenditures
| FedFundPlan_RelocExp_Amt | Relocation - Federal Funds Budgeted | Total amount of federal funds budgeted for relocation expenditures
| TotCostActl_RelocExp_Amt | Relocation - Total Costs Actual | Total amount of funds used for relocation expenses from the project's inception through the end of the current reporting period
| MatchFundActl_RelocExp_Amt | Relocation - Matching Funds Actual | Amount of matching funds used for relocation expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_RelocExp_Amt | Relocation - Federal Funds Actual | Amount of federal funds used for relocation expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_RelocExp_Amt | Relocation - Total Costs Anticipated | Total amount of funds anticipated for relocation expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_RelocExp_Amt | Relocation - Matching Funds Anticipated | Amount of matching funds anticipated for relocation expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_RelocExp_Amt | Relocation - Federal Funds Anticipated | Amount of federal funds anticipated for relocation expenses from the projects inception through the end of the next reporting period
| TotCostPlan_ArchFee_Amt | Architectural and Engineering - Total Costs Budgeted | Total amount budgeted for architectural and engineering expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_ArchFee_Amt | Architectural and Engineering - Matching Funds Budgeted | Total amount of matching funds budgeted for architectural and engineering expenditures
| FedFundPlan_ArchFee_Amt | Architectural and Engineering - Federal Funds Budgeted | Total amount of federal funds budgeted for architectural and engineering expenditures
| TotCostActl_ArchFee_Amt | Architectural and Engineering - Total Costs Actual | Total amount of funds used for architectural and engineering expenses from the project's inception through the end of the current reporting period
| MatchFundActl_ArchFee_Amt | Architectural and Engineering - Matching Funds Actual | Amount of matching funds used for architectural and engineering expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_ArchFee_Amt | Architectural and Engineering - Federal Funds Actual | Amount of federal funds used for architectural and engineering expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_ArchFee_Amt | Architectural and Engineering - Total Costs Anticipated | Total amount of funds anticipated for architectural and engineering expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_ArchFee_Amt | Architectural and Engineering - Matching Funds Anticipated | Amount of matching funds anticipated for architectural and engineering expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_ArchFee_Amt | Architectural and Engineering - Federal Funds Anticipated | Amount of federal funds anticipated for architectural and engineering expenses from the projects inception through the end of the next reporting period
| TotCostPlan_OtherArchFee_Amt | Other Architectural - Total Costs Budgeted | Total amount budgeted for other architectural expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_OtherArchFee_Amt | Other Architectural - Matching Funds Budgeted | Total amount of matching funds budgeted for other architectural expenditures
| FedFundPlan_OtherArchFee_Amt | Other Architectural - Federal Funds Budgeted | Total amount of federal funds budgeted for other architectural expenditures
| TotCostActl_OtherArchFee_Amt | Other Architectural - Total Costs Actual | Total amount of funds used for other architectural expenses from the project's inception through the end of the current reporting period
| MatchFundActl_OtherArchFee_Amt | Other Architectural - Matching Funds Actual | Amount of matching funds used for other architectural expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_OtherArchFee_Amt | Other Architectural - Federal Funds Actual | Amount of federal funds used for other architectural expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_OtherArchFee_Amt | Other Architectural - Total Costs Anticipated | Total amount of funds anticipated for other architectural expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_OtherArchFee_Amt | Other Architectural - Matching Funds Anticipated | Amount of matching funds anticipated for other architectural expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_OtherArchFee_Amt | Other Architectural - Federal Funds Anticipated | Amount of federal funds anticipated for other architectural expenses from the projects inception through the end of the next reporting period
| TotCostPlan_ProjInspFee_Amt | Project Inspection - Total Costs Budgeted | Total amount budgeted for project inspection expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_ProjInspFee_Amt | Project Inspection - Matching Funds Budgeted | Total amount of matching funds budgeted for project inspection expenditures
| FedFundPlan_ProjInspFee_Amt | Project Inspection - Federal Funds Budgeted | Total amount of federal funds budgeted for project inspection expenditures
| TotCostActl_ProjInspFee_Amt | Project Inspection - Total Costs Actual | Total amount of funds used for project inspection expenses from the project's inception through the end of the current reporting period
| MatchFundActl_ProjInspFee_Amt | Project Inspection - Matching Funds Actual | Amount of matching funds used for project inspection expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_ProjInspFee_Amt | Project Inspection - Federal Funds Actual | Amount of federal funds used for project inspection expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_ProjInspFee_Amt | Project Inspection - Total Costs Anticipated | Total amount of funds anticipated for project inspection expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_ProjInspFee_Amt | Project Inspection - Matching Funds Anticipated | Amount of matching funds anticipated for project inspection expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_ProjInspFee_Amt | Project Inspection - Federal Funds Anticipated | Amount of federal funds anticipated for project inspection expenses from the projects inception through the end of the next reporting period
| TotCostPlan_SiteWork_Amt | Site Work - Total Costs Budgeted | Total amount budgeted for site work expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_SiteWork_Amt | Site Work - Matching Funds Budgeted | Total amount of matching funds budgeted for site work expenditures
| FedFundPlan_SiteWork_Amt | Site Work - Federal Funds Budgeted | Total amount of federal funds budgeted for site work expenditures
| TotCostActl_SiteWork_Amt | Site Work - Total Costs Actual | Total amount of funds used for site work expenses from the project's inception through the end of the current reporting period
| MatchFundActl_SiteWork_Amt | Site Work - Matching Funds Actual | Amount of matching funds used for site work expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_SiteWork_Amt | Site Work - Federal Funds Actual | Amount of federal funds used for site work expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_SiteWork_Amt | Site Work - Total Costs Anticipated | Total amount of funds anticipated for site work expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_SiteWork_Amt | Site Work - Matching Funds Anticipated | Amount of matching funds anticipated for site work expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_SiteWork_Amt | Site Work - Federal Funds Anticipated | Amount of federal funds anticipated for site work expenses from the projects inception through the end of the next reporting period
| TotCostPlan_Demolitn_Amt | Demolition and Removal - Total Costs Budgeted | Total amount budgeted for demolition and removal expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_Demolitn_Amt | Demolition and Removal - Matching Funds Budgeted | Total amount of matching funds budgeted for demolition and removal expenditures
| FedFundPlan_Demolitn_Amt | Demolition and Removal - Federal Funds Budgeted | Total amount of federal funds budgeted for demolition and removal expenditures
| TotCostActl_Demolitn_Amt | Demolition and Removal - Total Costs Actual | Amount of funds used for demolition and removal expenses from the project's inception through the end of the current reporting period
| MatchFundActl_Demolitn_Amt | Demolition and Removal - Matching Funds Actual | Amount of matching funds used for demolition and removal expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_Demolitn_Amt | Demolition and Removal - Federal Funds Actual | Amount of federal funds used for demolition and removal expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_Demolitn_Amt | Demolition and Removal - Total Costs Anticipated | Total amount of funds anticipated for demolition and removal expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_Demolitn_Amt | Demolition and Removal - Matching Funds Anticipated | Amount of matching funds anticipated for demolition and removal expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_Demolitn_Amt | Demolition and Removal - Federal Funds Anticipated | Amount of federal funds anticipated for demolition and removal expenses from the projects inception through the end of the next reporting period
| TotCostPlan_OtherMisc_Amt | Miscellaneous - Total Costs Budgeted | Total amount budgeted for miscellaneous expenditures; this figure includes federal funds and matching funds
| MatchFundPlan_OtherMisc_Amt | Miscellaneous - Matching Funds Budgeted | Total amount of matching funds budgeted for miscellaneous expenditures
| FedFundPlan_OtherMisc_Amt | Miscellaneous - Federal Funds Budgeted | Total amount of federal funds budgeted for miscellaneous expenditures
| TotCostActl_OtherMisc_Amt | Miscellaneous - Total Costs Actual | Total amount of funds used for miscellaneous expenses from the project's inception through the end of the current reporting period
| MatchFundActl_OtherMisc_Amt | Miscellaneous - Matching Funds Actual | Amount of matching funds used for miscellaneous expenses from the project's inception through the end of the current reporting quarter
| FedFundActl_OtherMisc_Amt | Miscellaneous - Federal Funds Actual | Amount of federal funds used for miscellaneous expenses from the projects inception through the end of the current reporting quarter
| TotCostAntcp_OtherMisc_Amt | Miscellaneous - Total Costs Anticipated | Total amount of funds anticipated for miscellaneous expenses from the project's inception through the end of the next reporting period
| MatchFundAntcp_OtherMisc_Amt | Miscellaneous - Matching Funds Anticipated | Amount of matching funds anticipated for miscellaneous expenses from the project's inception through the end of the next reporting period
| FedFundAntcp_OtherMisc_Amt | Miscellaneous - Federal Funds Anticipated | Amount of federal funds anticipated for miscellaneous expenses from the projects inception through the end of the next reporting period
| TotCostPlan_DirCh_SubTot_Amt | Subtotal - Total Costs Budgeted | Subtotal of the total costs budgeted
| MatchFundPlan_DirCh_SubTot_Amt | Subtotal - Matching Funds Budgeted | Subtotal of matching funds budgeted
| FedFundPlan_DirCh_SubTot_Amt | Subtotal - Federal Funds Budgeted | Subtotal of federal funds budgeted
| TotCostActl_DirCh_SubTot_Amt | Subtotal - Total Costs Actual | Subtotal of total costs actual
| MatchFundActl_DirCh_SubTot_Amt | Subtotal - Matching Funds Actual | Subtotal of matching funds actual
| FedFundActl_DirCh_SubTot_Amt | Subtotal - Federal Funds Actual | Subtotal of federal funds actual
| TotCostAntcp_DirCh_SubTot_Amt | Subtotal - Total Costs Anticipated | Subtotal of total costs anticipated
| MatchFundAntcp_DirCh_SubTot_Amt | Subtotal - Matching Funds Anticipated | Subtotal of matching funds anticipated
| FedFundAntcp_DirCh_SubTot_Amt | Subtotal - Federal Funds Anticipated | Subtotal of federal funds anticipated
| TotCostPlan_Total_Amt | Totals - Total Costs Budgeted | Total amount of all budgeted expenses; this figure includes federal funds and matching funds
| MatchFundPlan_Total_Amt | Totals - Matching Funds Budgeted | Total amount of all budgeted matching funds
| FedFundPlan_Total_Amt | Totals - Federal Funds Budgeted | Total amount of all budgeted federal funds
| TotCostActl_Total_Amt | Totals - Total Costs Actual | Total amount of all expenditures from the project's inception through the end of the current reporting period
| MatchFundActl_Total_Amt | Totals - Matching Funds Actual | Total amount of all matching funds expended from the project's inception through the end of the current reporting period
| FedFundActl_Total_Amt | Totals - Federal Funds Actual | Total amount of all federal funds expended from the project's inception through the end of the current reporting period
| TotCostAntcp_Total_Amt | Totals - Total Costs Anticipated | Total amount of all expenditures anticipated from the project's inception through the end of the next reporting period
| MatchFundAntcp_Total_Amt | Totals - Matching Funds Anticipated | Total amount of all matching funds expenditures anticipated from the project's inception through the end of the next reporting period
| FedFundAntcp_Total_Amt | Totals - Federal Funds Anticipated | Total amount of all federal funds expenditures anticipated from the project's inception through the end of the next reporting period
| BudgetIncome_Amt | Budget Program Income | Program income listed in the application budget
| ToDateIncome_Amt | Program Income to Date | Actual program income received to date through the end of the current reporting period
| Recipient | Recipient | Name of the recipient organization
CCI Annual Report Data (see Tab CCI_Annual_KeyIndicators_Actual)
| Database Field | Heading | Description
| Award_Num | Award Number | The 10 digit grant award number listed on the CD-450 form
| Year | Reporting Year | Year of the reporting period
| MMile_AvgCost | Middle Mile - Average Cost Per New Mile | Cumulative direct capital costs associated with the installation of middle mile transmission infrastructure, divided by the route miles the transmission infrastructure traverses
| MMile_AvgCost_Desc | Middle Mile - Average Cost Per New Mile Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| LMileHous_AvgCost | Last Mile - Average Cost Per Household | Cumulative direct capital costs associated with the installation of the last mile transmission infrastructure to the households in the area, divided by the number of households to which that infrastructure makes service available
| LMileHous_AvgCost_Desc | Last Mile - Average Cost Per Household Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| LMileSubsc_AvgCost | Last Mile - Average Cost Per Subscriber | Cumulative direct capital costs associated with the last mile transmission infrastructure to the households in the service area, divided by the number of households subscribing to broadband service delivered over the last mile transmission infrastructure
| LMileSubsc_AvgCost_Desc | Last Mile - Average Cost Per Subscriber Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| MMile_MaxSpeed | Middle Mile - Maximum Broadband Speed | Maximum speed advertised of BTOP-funded middle mile services
| MMile_MaxSpeed_Desc | Middle Mile - Maximum Broadband Speed Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| LMile_MaxSpeed | Last Mile - Maximum Broadband Speed | Maximum speed advertised of BTOP-funded last mile services
| LMile_MaxSpeed_Desc | Last Mile - Maximum Broadband Speed Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| MMile_AvgSpeed | Middle Mile - Average Broadband Speed | Average broadband speed provided by BTOP-funded middle mile services
| MMile_AvgSpeed_Desc | Middle Mile - Average Broadband Speed Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| LMile_AvgSpeed | Last Mile - Average Broadband Speed | Average broadband speed provided by BTOP-funded last mile services
| LMile_AvgSpeed_Desc | Last Mile - Average Broadband Speed Narrative | Narrative to explain if actual costs are higher or lower than the figures projected in the baseline plan
| SpeedIncrease_Desc | Average Increase in Broadband Speed Narrative | Average increase in broadband speed associated with the community anchor institution customers as a result of the BTOP-funded project
| RetService_Desc | Retail Services Narrative | Information for all retail services offered by the reporting organization
| NetManagemnt_Desc | Network Management Policies Narrative | Information on network management policies for all services offered (e.g. bandwidth limitations and traffic prioritizations)
| DiscontReason_Desc | Dropped Service | Total number and the percentage of subscribers who have dropped the broadband service provided through the project (total number of households and/or businesses and the "churn rate") and the subscribers' reasons for discontinuing their service
| TotalStrand_Num | Total Number of Strand Miles | Total number of strand-miles used, leased, or dark. This is the total capacity of the network (including miles provided by the recipient and the subrecipient) when it is complete (actual deployment plus any expected construction)
| AvgActStrand_Num | Active Strand Miles - Average | Number represents how many miles are currently in use as of the period of this annual report
| AvgLeaseStrand_Num | Leased Strand Miles - Average | Number represents how many miles the recipient leases to third parties (customers, other service providers, etc.).
| AvgDarkStrand_Num | Dark Strand Miles - Average | Number represents how many dark or unlit miles the recipient currently has deployed
| BuildActStrand_Num | Active Strand Miles - Actual | Includes the active strand miles that the recipient expects or plans to build
| BuildLeaseStrand_Num | Leased Strand Miles - Actual | Includes the leased strand miles that the recipient expects or plans to build
| BuildDarkStrand_Num | Dark Strand Miles - Actual | Includes the dark strand miles that the recipient expects or plans to build
| WSaleCustList_Desc | Dark Fiber Wholesale Description | The names of wholesale customers and the number of fiber miles the recipient currently leases
| SqFeet_Total_Num | Total Facility Square Feet | Total capacity of facility in square feet (used, leased or available)
| SqFeet_Use_Num | Facility Square Footage Used | Total facility square footage used
| SqFeet_Lease_Num | Facility Square Footage Leased | Total facility square footage leased
| SqFeet_Availbl_Num | Facility Square Footage Available | Total facility square footage available
| NetConnect_Desc | Network Interconnection Description | If the recipient does not own collocation space, this includes: actual location of the equipment; location and/or point of interconnection; owner of the alternate location (e.g. Internet Exchange Point, POP); and a description of how the interconnection occurs
| SubcontrConcern_Desc | Subcontractor Agreements Description | Identifies any subcontracts or subgrants that have been made to socially and economically disadvantaged small business concerns
| BestPractice_Desc | Best Practices Narrative | Best practices or lessons learned that can be shared with other similar BTOP projects
| Recipient | Recipient | Name of the recipient organization
| School_Total_Num | Schools - Total CAI | Total schools within service area capable of receiving service as a result of BTOP funds
| Library_Total_Num | Libraries - Total CAI | Total libraries within service area capable of receiving service as a result of BTOP funds
| CCollege_Total_Num | Community College - Total CAI | Total community colleges within service area capable of receiving service as a result of BTOP funds
| Universt_Total_Num | Other Higher Education - Total CAI | Total other higher education entities within service area capable of receiving service as a result of BTOP funds
| Healthcr_Total_Num | Healthcare - Total CAI | Total healthcare facilities within service area capable of receiving service as a result of BTOP funds
| PublSafety_Total_Num | Public Safety - Total CAI | Total public safety entities within service area capable of receiving service as a result of BTOP funds
| OtherGov_Total_Num/OtherGov_Improv_Num | Other Government - Total CAI | Total other government institutions within service area capable of receiving service as a result of BTOP funds
| OtherNonGov_Total_Num | Other Community - Total CAI | Total other community institutions within service area capable of receiving service as a result of BTOP funds
| PublHousng_Total_Num | Public Housing - Total CAI | Total public housing entities within service area capable of receiving service as a result of BTOP funds
| TotalComInst_Num | Total CAI | Total CAIs within service area capable of receiving service as a result of BTOP funds
| InterAgreement_Name | Interconnection Agreements | Includes the names of providers that the recipient has entered into interconnection agreements during the annual reporting period
| PeerAgreemnt_Name | Peering and Transit Agreements | Includes the names of providers the recipient has entered into peering/transit agreements during this annual reporting period

## CCI_KeyIndicators_Actual
Award_Num | Year | Quarter | YearQuarter | Project_Indicator_Desc | NetMileDeploy_Num | NetMileLease_Num | ExistMileUpgrade_Num | ExistMileLease_Num | FiberMile_Num | WirelessLinks_Num | Towers_Num | InterconnectPoints_Num | NetMileDeploy_Desc | NetMileLease_Desc | ExistMileUpgrade_Desc | ExistMileLease_Desc | FiberMile_Desc | WirelessLinks_Desc | Towers_Desc | InterconnectPoints_Desc | SignAgreemnt_Num | PotentAgreemnt_Num | AvgTermAgreemnt_Num | Providers_List_Desc | WholeService_Desc | ThirdParty_Info_Desc | Providrs_NewAccess_Num | Providrs_ImprAccess_Num | Providrs_FiberAccess_Num | Providrs_SpeedTier_Num | Providrs_NewAccess_Desc | Providrs_ImprAccess_Desc | Providrs_FiberAccess_Desc | Providrs_SpeedTier_Desc | ComInst_Total_Num | ComInst_NewAccess_Num | ComInst_ImprAccess_Num | ComInst_SpeedTier_Num | ComInst_Total_Desc | ComInst_NewAccess_Desc | ComInst_ImprAccess_Desc | ComInst_SpeedTier_Desc | Househld_Entity_Num | Househld_Total_Num | Househld_NewAccess_Num | Househld_ImprAccess_Num | Househld_SpeedTier_Num | HouseHld_Entity_Desc | Househld_Total_Desc | HouseHld_NewAccess_Desc | Househld_ImprAccess_Desc | Househld_SpeedTier_Desc | Business_Entity_Num | Business_Total_Num | Business_NewAccess_Num | Business_ImprAccess_Num | Business_SpeedTier_Num | Business_Entity_Desc | Business_Total_Desc | Business_NewAccess_Desc | Business_ImprAccess_Desc | Business_SpeedTier_Desc | SpecialOffer_Desc | PracticeChange_Ind | PracticeChange_Desc | ProjectPlanned_Accomplish_Desc | Recipient | Current_Milestone_Challenges | Next_Milestone_Challenges
NT10BIX5570003 | 2010 | Q3 | Q3 - 2010 | This quarter was earmarked with the start of Construction at various sites throughout the State. Ground Breaking events were held at several locations celebrating the commencement of South Dakota Network's Broadband Technology Opportunities Program grant to bring high speed internet service to rural and underserved areas of the state. Equipment purchases were made for planned deployment bringing speeds of up to 10 Meg to current and future customers. In addition, site work and permitting continued to enable ongoing progress and completion of the project within the timelines allowed. | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | The duration of the Environmental Assessment submittal and approval has pushed construction back by approximately one quarter. | N/A | N/A | N/A | The duration of the Environmental Assessment submittal and approval has pushed construction back by approximately one quarter. | N/A | N/A | N/A | 0 | 0 | 0 | None at this time in the project as construction was started this quarter. | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Special offerings are not provided at this point in the project as construction is underway and sites have not been turned up. | FALSE | N/A | Construction will continue at several sites as we continue to make progress towards our baseline projections initiated early on in the project. Equipment is projected to be deployed to bring existing customers improved services through increased broadband speeds as a result of Project Connect South Dakota. | South Dakota Network, LLC | Construction has lagged the original projections and milestones from the Baseline Report. South Dakota Network plans to accelerate the construction as weather allows to meet the Broadband Technology Opportunities Program guidelines. | Progress will continue, particularly in the area of construction, as long as we are not affected by extreme early weather conditions that will cause impedance or stoppage beyond projections. Any setback in construction of the Network Build will also affect Testing and potentially site preparation.
NT10BIX5570003 | 2010 | Q4 | Q4 - 2010 | Construction continued this quarter with work in the Vermillion, Yankton Watertown, and Rapid City areas across the state. Network Build was a primary focus while continuing staking of routes, right of way acquisition and permitting. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | Construction has been lagging this milestone category with additional fiber ready to be deployed in early 2011. An aggressive construction schedule originally was planned to begin one quarter earlier than actual. | N/A | N/A | N/A | See narrative above. | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Based on several of our sub recipients being awarded BIP awards during 2010, SDN is currently finalizing the contracts with those involved with our BTOP award. | See narrative above. | N/A | Although signed agreements are in place, these Last Mile Providers have not initiated service. | 2 | 2 | 0 | 2 | SDN was not able to connect as many Community Anchor Institutions as projected in the baseline due to both the timing of initial construction start date and the inclement weather arriving early. | See Narrative above. | See Narrative above. | 5,10,15,20,75,100Meg. 1-75 Meg, 1-20 Meg | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Limited increase in baseline projections are anticipated for next quarter by schedule design. It is anticipated that some additional site preparation, network testing and construction will be completed during the next quarter. Sub-recipient participation will become more prevalent in the overall project with limited construction activities, site preparation, and planning the primary focus. Marketing of SDN's BTOP project to the Communities throughout the State continues to be a focus of attracting customers to SDN's improved Network. | South Dakota Network, LLC | The weather came into play towards the end of the quarter, as cold and snow hampered progress on construction. Although somewhat anticipated and projected, we were hoping that some ground could be made up in the overall progress of the network build. Technical assistance is appreciated and will be asked for when it is needed for the project acceleration. | SDN anticipates weather to be the only item to effect the project at this time.
NT10BIX5570003 | 2011 | Q1 | Q1 - 2011 | Progress was made in implementing and planning towards additional construction crews and resources necessary to advance and tighten the gap between our milestone and actual completion of the project. Marketing and Community Outreach activities were planned for peak periods over the next several months. Work on a new website to be rolled out in the future that enhances the project and utilizes Social Media as a form of stakeholder feedback and input. | 72 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | An aggressive schedule the first year along with a longer than anticipated Environmental process has found the milestone lagging. Additional crews will be deployed to shorten this gap and we are committed to reaching our mile projection by end of Year 2 of the project. | N/A | N/A | N/A | See narrative under 'New Network miles deployed' above. | N/A | N/A | A clerical error is in process of being revised with the program office with this milestone. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | This milestone originally utilized our Sub Recipient count to come up with the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. | See narrative under above Access Type. | N/A | N/A | 40 | 35 | 5 | 12 | South Dakota Network was not able to connect to the number of Community Anchor Institutions as due to the initial delays in the Environmental process. | See narrative above. | See narrative above for this milestone as well. | 5,10,15,20,75,100 Meg. 10-10 Meg. 1-75 Meg, 1-100 Meg. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Construction will be a major focus this next quarter with additional resources being deployed to expedite the process. Events are being planned to 'kick off' construction in markets where construction has not yet started. Job creation is anticipated to peak as we start the network build phase again at an increased rate. | South Dakota Network, LLC | Minimal activity was expected as was shown on the Baseline Project Plan during this quarter. Inclimate seasonal weather was anticipated that would not be conducive to build during January through March. | Weather may continue to be an issue this Spring as we have had a significant amount of flooding and rainfall hindering to some degree the amount of construction activities we were planning. Any additional challenges or issues are not currently anticipated.
NT10BIX5570003 | 2011 | Q2 | Q2 - 2011 | South Dakota Network focused on construction activities this quarter, in anticipation of achieving Baseline projections for network build and overall project milestones. Additionally, two Sub Recipients were added this quarter for equipment purchases to supplement the project. Planning for additional resources as needed to insure the project is completed on time was another major component of this quarters' activity. Community Outreach efforts continue as the project extends out to additional towns and areas throughout the State. | 94 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | Based upon the environmental process taking longer than anticipated and therefore a later than planned construction start date, the number of network miles of fiber has not met our Baseline projections. The Baseline originally called out for minimal construction during the final year of the project. We anticipate meeting the Baseline projections in Q3 of 2012. | N/A | N/A | N/A | See narrative under 'New network miles deployed' above. | N/A | N/A | A clerical error is in the process of being revised with the Program Office with this milestone. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering, or other related verbiage. | See narrative above under Access Type. | N/A | N/A | 124 | 102 | 22 | 34 | South Dakota Network had originally based their projections on an earlier Environmental Assessment, as a result have not been able to connect to the number forecasted. | See narrative above. | See narrative above for this milestone as well. | 5, 10, 15,20, 75, 100 Meg. 31-10 Meg, 1-20Meg, 1-75Meg., 1-100 Meg. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | South Dakota Network (SDN) intends to continue an aggressive schedule for construction in the following quarter. Equipment for Sub Recipients recently added will be ordered and deployed. Planning for additional resources as required to shorten the gap between the Baseline projections and actual build will be implemented. Community Outreach efforts continue as the project is kept updated via the SDN website and other media outlets. | South Dakota Network, LLC | An unusually wet spring altered original plans, but revisions to the construction schedule were made to continue the build and keep the project moving. Weather issues continue to be a challenge, but adjustments will be made and no technical assistance is currently needed. | Although nothing is anticipated, weather can always be a factor and slow progress against milestone projections. We are confident our aggressive build schedule and ability to add construction crews in the event of a delay caused by weather, will keep us on track with our projections.
NT10BIX5570003 | 2011 | Q3 | Q3 - 2011 | South Dakota Network continued a strong build of it's network in all parts of the state. Ribbon cutting events were held to kick off construction in select cities. Equipment for additional Sub Recipients was ordered and awaiting installation in future quarters. | 235 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | An additional one hundred forty miles of fiber were added to the network in this quarter closing some of the gap in actual verses Baseline projections. Favorable weather outlook, additional crews planned, and only a five mile increase over the next quarter will bring this metric closer to our goal. | N/A | N/A | N/A | Same as 'new network miles deployed' metric above. | N/A | N/A | A clerical error in in the process of being revised with the Program Office with this milestone. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. | See narrative above under Access Type. | N/A | N/A | 302 | 178 | 124 | 162 | Exceeding Baseline. | Nearly exceeding Baseline. | Exceeding Baseline. | 0-5Meg 115-10Meg 2-20Meg 1-25Meg 1-40Meg 1-75Meg 38-100Meg 4-1Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Continued construction, as long as weather will allow, is the primary focus for the project. Additional equipment will be deployed as recently added Sub Recipients place equipment upon receipt. An additional 65 CAI's and 50 Miles of Fiber will be deployed this quarter. | South Dakota Network, LLC | None at this time. | Weather may be a factor as this quarter is typically very uncertain when it comes to weather patterns. A favorable quarter with minimal moisture will allow for continued construction and additional miles deployed.
NT10BIX5570003 | 2011 | Q4 | Q4 - 2011 | Substantial completion of the project highlighted the last quarter of 2011. Two thirds of the project has been completed as measured by Grant Dollars received and Miles of Fiber deployed. This milestone was met by November 30th as we completed our second project year. Community Outreach efforts included a visit by South Dakota Senator Tim Johnson with a public media announcement of our progress thus far with the Broadband Technology Opportunities Program grant. Construction activity, although slowed, continued as the Midwest has experienced unseasonable warm weather this winter allowing for progress in fiber deployment. | 282 | 0 | 0 | 0 | 282 | 0 | 0 | 0 | An additional forty seven miles of fiber were placed this quarter bringing the total to 282. Our Baseline had only projected five miles for the quarter. Due to unseasonably mild weather, additional miles beyond projections were able to be built. This metric will be able to meet Baseline Projections early in 2012. | N/A | N/A | N/A | Same as "New Network miles deployed" above. | N/A | N/A |  | 0 | 0 | 0 | N/A | N/A | Sub Recipients identified below will own and operate the portion of the Network they build for expansion to their footprint. City of Faith-Telephone Department, 204 N Main Street, Faith, South Dakota 57626 Interstate Telecommunications Cooperative, Inc., 312 4th Street, West, Clear Lake, South Dakota 57226 Northern Valley Communications, LLC, 235 East First Ave., Groton, South Dakota 57445 Northern Hills Transport, LLC, 2900 West 10th Street, Sioux Falls, South Dakota 57104 TrioTel Communications, Inc., 330 S Nebraska St., Salem, South Dakota 57058 Venture Communications, Inc., 218 Commercial Ave. SE, Highmore, South Dakota 57345 | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. | See narrative above under "Providers with signed agreements receiving new access" | N/A | N/A | 436 | 219 | 217 | 10 | Exceeding Baseline. | Exceeding Baseline. | Meeting Baseline projections. | 5-5 Mb/s 132 -10 Mb/s 4-15 Mb/s 5-20 Mb/s 1-25 Mb/s 2-40 Mb/s 2-45 Mb/s 1-80 Mb/s 38-100 Mb/s 4-1000 Mb/s Not all of the CAI's being served are subscribing to service at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | With winter weather at it's peak in South Dakota during this time frame, minimal construction activity will be taking place. Some work in the western part of the State will occur, but only minimally. Planning for upcoming quarters and requirements for closing out the award are being undertaken in the next quarter. Quarterly Projections: Network Miles Deployed- 10 Projected CAI's- 19 Wholesale Providers-N/A | South Dakota Network, LLC | None at this time. | None at this time.
NT10BIX5570003 | 2012 | Q1 | Q1 - 2012 | SDN continued to work on construction during the quarter adding an additional 15 miles of fiber. Planning for the final months of the project continues as some program changes are anticipated and being coordinated with the help of our Federal Program Officer. Additional Community Anchor Institutions are being connected to the network with additional subscribers adding service. | 297 | 0 | 0 | 0 | 297 | 0 | 0 | 0 | Although slightly behind Baseline projections, we will meet the goal of completing the project in the allotted timeframe. | N/A | N/A | N/A | See 'new network miles deployed' narrative above. | N/A | N/A | This continues to be a point of discussion and needs to be clarified. | 0 | 0 | 0 | N/A | N/A | Sub Recipients identified below will own and operate the portion of the Network they build for expansion to their footprint. City of Faith-Telephone Department, 204 N. Main Street, Faith, South Dakota 57626 Interstate Telecommunications Cooperative, Inc., 312 4th Street West, Clear Lake, South Dakota 57226 Northern Valley Communications, LLC, 235 East First Ave., Groton, South Dakota 57445 Northern Hills Transport, LLC, 2900 West 10th Street, Sioux Falls, South Dakota 57104 TrioTel Communications, Inc., 330 S. Nebraska St., Salem, South Dakota 57058 Venture Communications, Inc., 218 Commercial Ave. SE, Highmore, South Dakota 57345 | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. It is not anticipated that we will have any agreements with Wholesalers or Last Mile Providers over the remainder of the project. | See narrative above under "Providers with signed agreements receiving new access." | N/A | N/A | 451 | 234 | 217 | 11 | Exceeding Baseline | Exceeding Baseline | Exceeding Baseline | 7-5Mb/s, 158-10Mb/s, 4-15Mb/s, 4-20Mb/s, 1-25Mb/s, 2-40Mb/s, 3-45Mb/s, 1-80Mb/s, 38-100Mb/s, 1-175Mb/s, 4-1000Mb/s Not all of the CAI's being served are subscribing to service at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | SDN plans to complete an additional 32 fiber miles of installation in the upcoming quarter. Additionally, forty four (44) Community Anchor Institutions will be added with some subscriptions for new service as well. Media releases are planned for segments of the BTOP project recently completed and those coming on line in additional quarters. We do not anticipate any Wholesale or Last Mile Provider agreements being negotiated in this or upcoming quarters. | South Dakota Network, LLC | None at this time in the project. | None at this time.
NT10BIX5570003 | 2012 | Q2 | Q2 - 2012 | SDN focused on construction activities this quarter with the project nearing completion. Additional Community Anchor Institutions were connected to the network as we now approach nearly 500 subscribers receiving new or improved service as a result of BTOP funds. Sub Recipient projects are also completed or nearing completion as we enter the final phase of the project. Planning for closeout of the award is taking place to insure a smooth and seamless process. | 341 | 0 | 0 | 0 | 341 | 0 | 0 | 0 | With minimal miles remaining to build, completion of construction is planned for next quarter and meeting Baseline projection. | N/A | N/A | N/A | See "New network miles deployed' narrative above. | N/A | N/A | No interconnection points have been identified at this point in the project. This will be clarified during the final phase of the project. | 0 | 0 | 0 | N/A | N/A | Sub Recipients identified below will own and operate their portion of the Network they build for expansion to their footprint. City of Faith-Telephone Department, 204 N. Main Street, Faith, South Dakota 57626 Interstate Telecommunications Cooperative, Inc., 312 4th Street West, Clear Lake, South Dakota 57226 Northern Valley Communications, LLC, 235 East First Ave., Groton, South Dakota 57445 Northern Hills Transport, LLC, 2900 West 10th Street, Sioux Falls, South Dakota 57104 TrioTel Communications, Inc., 330 S. Nebraska St., Salem, South Dakota 57058 Venture Communications, Inc., 218 Commercial Ave. SE, Highmore, South Dakota 57345 | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. It is not anticipated that we will have any agreements with Wholesalers or Last Mile Providers | See narrative above under "Providers with signed agreements receiving new access." | N/A | N/A | 493 | 276 | 217 | 12 | Exceeding Baseline. | Exceeding Baseline. | Exceeding Baseline. | 8-5Mb/s, 163-10Mb/s, 4-15Mb/s, 4-20Mb/s, 1-25Mb/s, 2-30Mb/s, 2-40Mb/s, 3-45Mb/s, 1-80Mb/s, 39-100Mb/s, 1-175Mb/s, 4-1000Mb/s Not all of the CAI's being served are subscribing to service at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | Next quarter will find this project near completion with minimal 'tidying' up to be done. Community Anchor Institutions yet to be connected will be completed during the final quarter of planned construction activity. Closeout activities will be reviewed and planning done for quarter four of this year as we finalize all necessary requirements of the grant. Public and Community Outreach events will be held signifying and celebrating the completion of the project. An additional 31 miles of fiber are scheduled to be deployed, with 29 Community Anchor Institutions being connected in the third quarter of 2012. As stated in past reports, no wholesale or last mile provider agreements are anticipated. | South Dakota Network, LLC | None at this time in the project cycle. | None at this time.
NT10BIX5570003 | 2012 | Q3 | Q3 - 2012 | Construction activities along with splicing and testing continued as we approach the final phase of the project. One additional route was approved for the project in the northern part of the state accounting for an additional twenty seven (27) miles of fiber deployment. Closeout activities also continued as the final months of the project are nearing. Additional Community Anchor Institutions are being connected to bring us closer to completion of this metric as well. | 360 | 0 | 1804 | 0 | 360 | 0 | 0 | 9 | With the additional approved route, new network miles deployed will reach 398 total miles for the project. | N/A | Although not originally identified in our Baseline projections, existing network miles have been upgraded with the addition of BTOP funded equipment. | N/A | See 'New Network miles deployed' narrative above. | N/A | N/A | This metric has been revised from our original Baseline at the request of NTIA. Interconnection points as clarified have been made. | 0 | 0 | 0 | N/A | N/A | Sub Recipients identified below will own and operate their portion of the Network they build for expansion to their footprint. City of Faith-Telephone Department, 204 N. Main Street, Faith, South Dakota 57626 Interstate Telecommunications Cooperative, Inc., 312 4th Street West, Clear Lake, South Dakota 57226 Northern Valley Communications, LLC, 235 East First Ave., Groton, South Dakota 57445 Northern Hills Transport, LLC, 2900 West 10th Street, Sioux Falls, South Dakota 57104 TrioTel Communications, Inc., 330 S. Nebraska St., Salem, South Dakota 57058 Venture Communications, Inc., 218 Commercial Ave. SE, Highmore, South Dakota 57345 | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. It is not anticipated that we will have any agreements with Wholesalers or Last Mile Providers | See narrative above under "Providers with signed agreements receiving new access." | N/A | N/A | 501 | 284 | 217 | 12 | This metric will meet Baseline projections at the end of the award period. | This metric will meet Baseline projections at the end of the award period. | Meeting Baseline. | 1-1Mb/s, 10-5Mb/s, 170-10Mb/s, 4-15Mb/s, 4-20Mb/s, 1-25Mb/s, 7-30Mb/s, 2-40Mb/s, 3-45Mb/s, 1-80Mb/s, 39-100Mb/s, 1-175Mb/s, 1-450Mb/s, 4-1000Mb/s. Not all of the CAI's being served are subscribing to service at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | Remaining construction activities will be completed with final testing being done as well. Project closeout activities will play a major part of this quarter's activities. As built drawings and federal interest documentation will also be included in the quarter's scheduled activities. | South Dakota Network, LLC | None anticipated at this time. | None, as the project will be completed.
NT10BIX5570003 | 2012 | Q4 | Q4 - 2012 | The project construction was completed in this quarter as well as all testing, route closeouts, and all Federal Interest Documents filed for project assets. The final ASAP draw against the Federal Grant Funds was made in December for the project and all accounting records finalized by quarter end. | 397 | 0 | 1804 | 0 | 397 | 0 | 0 | 9 | Exceeding Baseline Projections. | N/A | Although not originally identified in our Baseline projections, existing network miles have been upgraded with the addition of BTOP funded equipment. | N/A | Exceeding Baseline Projections. | N/A | N/A | This metric has been revised from our original Baseline at the request of NTIA. Interconnection points as clarified have been made. | 0 | 0 | 0 | N/A | N/A | Sub Recipients identified below will own and operate their portion of the Network they build for expansion to their footprint. City of Faith-Telephone Department, 204 N. Main Street, Faith, South Dakota 57626 Interstate Telecommunications Cooperative, Inc., 312 4th Street West, Clear Lake, South Dakota 57226 Northern Valley Communications, LLC, 235 East First Ave., Groton, South Dakota 57445 Northern Hills Transport, LLC, 2900 West 10th Street, Sioux Falls, South Dakota 57104 TrioTel Communications, Inc., 330 S. Nebraska St., Salem, South Dakota 57058 Venture Communications, Inc., 218 Commercial Ave. SE, Highmore, South Dakota 57345 | 0 | 0 | 0 | 0 | This milestone originally included the Sub Recipients to calculate the Baseline projection. Based upon feedback from NTIA, we will not be counting Sub Recipients as Last Mile Providers. Agreements with Sub Recipients do not involve interconnection, peering or other related verbiage. It is not anticipated that we will have any agreements with Wholesalers or Last Mile Providers. | See narrative above under "Providers with signed agreements receiving new access." | N/A | N/A | 512 | 308 | 204 | 14 | Exceeds Baseline. | Exceeds Baseline. | Meets Baseline. | 1-1Mb/s, 10-5Mb/s, 170-10Mb/s, 4-15Mb/s, 4-20Mb/s, 1-25Mb/s, 12-30Mb/s, 2-40Mb/s, 2-45Mb/s, 1-80Mb/s, 39-100Mb/s, 1-175Mb/s, 1-450Mb/s, 4-1000Mb/s. Not all of the CAI's being served are subscribing to service at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project was completed last quarter with minimal closeout activities taking place in the next quarter. The final ASAP withdrawal was made in December and the entire budget has been expended for the project. Final reports and audit requirements will be completed and submitted to NTIA for review and approval to close out the project. | South Dakota Network, LLC | N/A | None
NT10BIX5570004 | 2010 | Q3 | Q3 - 2010 | Significant progress on substantial EA revisions toward receiving FONSI. Secured C-POP site leases. Planning and logistics in preparation for construction. Issued RFQs and/or RFPs for auditor and marketing consultant and for equipment, materials and labor in preparation for construction phase. All allowable activities to be prepared for construction phase with receipt of FONSI. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Complete final EA revisions and receive FONSI. Complete network design for middle mile, logical network design for middle mile. Obtain ROWs and secure permits in selected zones. Begin construction phase to include awarding vendor and equipment contracts; site preparation and staging of construction equipment. Complete IRU agreements; begin developing testing plans and procedures. | North Georgia Network Cooperative, Inc. | NGN had challenges with revising our EA to include the Last Mile portion of our project, which caused considerable delays. NTIA's environmental team has been providing technical assistance and we feel the issues have been resolved and we are very close now to receiving a FONSI. | N/A
NT10BIX5570004 | 2010 | Q4 | Q4 - 2010 | Significant progress on Environmental Assessment with final approval being received January 3, 2011. Issued RFPs for DWDM Equipment and Optical Test Equipment. Contracts on some of the equipment were prepared but could not be executed until final Environmental Assessment was received. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | N/A | N/A | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | N/A | N/A | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | N/A | Project delayed due to pending Environmental Assessment approval. Final approval received January 3, 2011. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | With the completed Environmental Assessment being received we will begin the construction phase. This includes awarding vendors, equipment contracts, and actual fiber construction. Continue to develop testing plans and procedures. | North Georgia Network Cooperative, Inc. | Final Environmental Assessment approval was received January 3, 2011. We will be working toward meeting the original baseline projections within the first half of 2011. | N/A
NT10BIX5570004 | 2011 | Q1 | Q1 - 2011 | During the first quarter of 2011 Fiber construction began, multiple equipment contracts were executed and some equipment received. Evaluation of last mile customers began and negotiations with business and anchor institutions. | 8 | 154 | 0 | 0 | 8 | 0 | 0 | 0 | Over eight miles of fiber construction completed in first quarter 2011. One hundred forty three miles of fiber projected to be completed in second quarter 2011. | Twenty four miles of leased fiber from HEMC and one hundred thirty miles from Fiber Lite have been finalized during the first quarter. In second quarter of 2011 additional IRU's with Blue Ridge Mountain EMC and ETC are expected to be completed. | N/A NGN had no existing network. | N/A NGN had no existing network. | Over eight miles of fiber construction completed in first quarter 2011. One hundred forty three miles of fiber projected to be completed in second quarter 2011. | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Interconnections points appealability projected as portion of network is complete in third quarter, 2011. | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | N/A | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | 0 | 0 | 0 | 0 | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | 0 | 0 | 0 | 0 | 0 | N/A | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue in the second quarter with implementation to begin in the third quarter. | 0 | 0 | 0 | 0 | 0 | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Planning will continue in the second quarter with implementation to begin in the third quarter. | N/A | FALSE | N/A | Fiber construction will continue during the second quarter. Procurement of equipment expected to continue and implementation of equipment should begin during the second quarter. We will continue to develop and implement testing plans and procedures. Planning for last mile customers and community anchors will continue during second quarter. | North Georgia Network Cooperative, Inc. | Construction of fiber plant began at the end of first quarter and multiple equipment contracts were awarded and equipment ordered during this quarter. We will be working toward meeting the original baseline projections during the second and third quarters of 2011. | N/A
NT10BIX5570004 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011 over 105 miles of Fiber construction was completed in Habersham, Rabun, Towns, Union and White counties. Multiple equipment contracts were executed and a portion of the equipment was received. Evaluation of last mile customer connections continued and will continue into the next two quarters. We have continued negotiations with business and anchor institutions during this quarter but negotiations will continue into the next two quarters. Over twenty-one full time jobs we utilized during the second quarter of 2011. | 113 | 154 | 0 | 0 | 113 | 0 | 0 | 0 | One hundred five miles of fiber construction completed in second quarter 2011. | Remaining 34 miles of leased fiber should be completed in third quarter 2011. | N/A NGN had no existing network. | N/A NGN had no existing network. | One hundred five miles of fiber construction completed in second quarter 2011. | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Interconnections points appealability projected as portion of network is complete in third quarter, 2011. | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | N/A | Construction of fiber plant began last week of March, 2011. Plan for all core and middle mile fiber construction to be completed by third quarter 2011. Meetings have began with potential wholesales or last mile providers. | 0 | 0 | 0 | 0 | Last mile construction is projected to begin in third quarter 2011. Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the third quarter. | Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the third quarter. | Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the third quarter. | Marketing executives have been meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the third quarter. | 0 | 0 | 0 | 0 | 0 | N/A | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the third quarter. | Last mile construction is projected to begin in third quarter 2011. Letters have been mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the third quarter. | 0 | 0 | 0 | 0 | 0 | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the third quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the third quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the third quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the third quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the third quarter. | N/A | FALSE | N/A | Fiber construction will continue during the third quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should begin during the third quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will begin during third quarter. | North Georgia Network Cooperative, Inc. | Construction of core and middle mile fiber continued and multiple equipment contracts were awarded and equipment ordered during this quarter. We will be working toward meeting the original baseline projections for the third quarters of 2011. | We do not anticipate any challenges or issues with meeting our projections for the third quarter. Fiber construction will continue during the third quarter. Procurement of equipment is expected to continue and implementation of major equipment, CPOP and SPOP will begin during the third quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will begin during third quarter.
NT10BIX5570004 | 2011 | Q3 | Q3 - 2011 | During the third quarter of 2011 Fiber construction continued, multiple equipment contracts were executed and some equipment received. Evaluation of last mile customers continued, as well as, negotiations with business and anchor institutions. | 277 | 154 | 0 | 0 | 277 | 0 | 0 | 0 | Two hundred seventy-seven miles of fiber construction completed in third quarter 2011. | Remaining 34 miles of leased fiber should be completed in fourth quarter 2011. | N/A NGN had no existing network. | N/A NGN had no existing network. | Two Hundred seventy-seven miles of fiber construction completed in third quarter 2011. | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Interconnections points appealability projected as portion of network is complete in fourth quarter, 2011. | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant continued during the third quarter of 2011. Plan for all core and middle mile fiber construction to be completed by fourth quarter 2011. Meetings have continued with potential wholesales or last mile providers. | Construction of fiber plant continued during the third quarter of 2011. Plan for all core and middle mile fiber construction to be completed by fourth quarter 2011. Meetings have continued with potential wholesales or last mile providers. | N/A | Construction of fiber plant continued during the third quarter of 2011. Plan for all core and middle mile fiber construction to be completed by fourth quarter 2011. Meetings have continued with potential wholesales or last mile providers. | 0 | 0 | 0 | 0 | Last mile construction began last week of September 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the fourth quarter. | Last mile construction began last week of September 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the fourth quarter. | Last mile construction began last week of September 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the fourth quarter. | Last mile construction began last week of September 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has began to lay out the network with the most impact in the shortest time. Implementation to begin in the fourth quarter. | 0 | 0 | 0 | 0 | 0 | N/A | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the fourth quarter. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the fourth quarter. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the fourth quarter. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the fourth quarter. | 0 | 0 | 0 | 0 | 0 | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the fourth quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the fourth quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the fourth quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the fourth quarter. | Marketing executives have been meeting with the business that are going to be passed as part of this network. Planning will continue and implementation will begin in the fourth quarter. | N/A | FALSE | N/A | Fiber construction will continue during the fourth quarter. Procurement of equipment expected to continue and implementation of major equipment, CPOP and SPOP locations should continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will begin during fourth quarter. New network miles deployed will increase to 494 miles during the fourth quarter. We will have a minimum of one signed wholesale provider agreements during the fourth quarter. We expect to have 22 Community Anchor Institutions receiving improved access during the fourth quarter. . | North Georgia Network Cooperative, Inc. | Construction of core and middle mile fiber continued last mile construction began the last week of September 2011. We will be working toward meeting the original baseline projections for the fourth quarter of 2011. | We do not anticipate any challenges or issues with meeting our projections for the fourth quarter. Fiber construction will continue during the fourth quarter. Procurement of equipment is expected to continue and implementation of major equipment, CPOP and SPOP will continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors began in the last week of September 2011.
NT10BIX5570004 | 2011 | Q4 | Q4 - 2011 | During the fourth quarter of 2011 Fiber construction continued for both core, middle and last mile. Four CPOP's completed in the fourth quarter in White, Lumpkin, Dawson, and Union and equipment installed and tested. Eight SPOP locations were set and equipment installed and tested during fourth quarter 2011. Evaluation of last mile customer continued, as well as, negotiations with business and anchor institutions. | 450 | 188 | 0 | 0 | 450 | 0 | 0 | 225 | Meets baseline | Meets baseline | N/A NGN had no existing network. | N/A NGN had no existing network. | Meets baseline | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Meets baseline | 0 | 2 | 0 | [REDACTED] | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant continued during the fourth quarter of 2011. Meetings have continued with potential wholesale or last mile providers. | Construction of fiber plant continued during the fourth quarter of 2011. Meetings have continued with potential wholesale or last mile providers. | N/A | Construction of fiber plant continued during the fourth quarter of 2011. Meetings have continued with potential wholesale or last mile providers. | 0 | 0 | 0 | 0 | Last mile construction began the last week of September, 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012. | Last mile construction began the last week of September, 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012. | Last mile construction began the last week of September, 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012. | Last mile construction began the last week of September, 2011. Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012. | 9800 | 0 | 0 | 0 | 0 | Meets Baseline | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | 425 | 0 | 0 | 0 | 0 | Meets Baseline | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | Last mile construction began last week of September 2011. Letters continue to be mailed and replies received to determine customers interest and location. Planning has began to lay out the network with the most impact in the shorted time. Planning will continue and implementation will begin in the first quarter or 2012 when the connection to our main bandwidth provider is completed. | N/A | FALSE | N/A | CPOP and SPOP construction will continue in first quarter of 2012. Our network connections on both our Eastern and Western side to our main Colo location will be complete. Turn up of customers will begin in the first quarter of 2012. | North Georgia Network Cooperative, Inc. | First quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be seventy-five percent complete which will meet our baseline milestones. | We do not anticipate any challenges or issues with meeting our projections for the first quarter. Fiber construction will continue during the first quarter. Implementation of major equipment, one additional CPOP and ten additional SPOP will continue during the first quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will began in the first quarter when our connection to our main bandwidth provider is complete.
NT10BIX5570004 | 2012 | Q1 | Q1 - 2012 | During the first quarter of 2012 Fiber construction continued for both core, middle and last mile. One CPOP's completed in the first quarter in Forsyth and equipment installed and tested. Eight SPOP locations were set and equipment installed and tested during first quarter 2012. Evaluation of last mile customer continued, as well as, negotiations with business and anchor institutions. | 475 | 188 | 0 | 0 | 475 | 0 | 0 | 238 | Meets baseline report | Meets baseline report | N/A NGN had no existing network. | N/A NGN had no existing network. | Meets baseline report | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Meets baseline report | 0 | 2 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant continued during the first quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | Construction of fiber plant continued during the first quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | N/A | Construction of fiber plant continued during the first quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | 0 | 0 | 0 | 0 | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012 most community anchor will be completed in second or third quarter of 2012. Customers with erate services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012 most community anchor will be completed in second or third quarter of 2012. Customers with erate services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012 most community anchor will be completed in second or third quarter of 2012. Customers with erate services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Implementation to begin in the first quarter when the connection to our main bandwidth provider is completed the end of January, 2012 most community anchor will be completed in second or third quarter of 2012. Customers with erate services are scheduled to change effective July 2012. | 7872 | 2832 | 134 | 2698 | 0 | Meets baseline report | Meets baseline report | Last mile marketing efforts will continue until the end of the project which will add additional subscribers receiving new access. | Meets baseline report | 10 Customers 30x30 124 Customers 15x15 | 886 | 240 | 11 | 229 | 0 | Meets baseline report | Meets baseline report | Last mile marketing efforts will continue until the end of the project which will add additional subscribers receiving new access. | Meets baseline report | 11 Customers 20x20 0 Customers 50x50 | N/A | FALSE | N/A | SPOP construction will continue in second quarter of 2012. Our network connections on both our Eastern and Western side to our main Colo location will be complete. Turn up of customers will continue in the second quarter of 2012. Last mile fiber construction will continue during the second quarter. CPOP grand openings are planned in Dahlonega and Forsyth. Implementation of major equipment located in the CPOP's in Dawson and Union will continue. Installation of ten additional SPOP locations will continue during the second quarter. We will continue to develop and implement testing plans and procedures. | North Georgia Network Cooperative, Inc. | Second quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be eighty-six percent complete which will meet our baseline milestones. | We do not anticipate any challenges or issues with meeting our projections for the second quarter. Last mile fiber construction will continue during the second quarter. CPOP grand openings are planned in Dahlonega and Forsyth. Implementation of major equipment located in the CPOP's in Dawson and Union will continue. Installation of ten additional SPOP location will continue during the second quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will continue in the second quarter when our connection to our main bandwidth provider is complete.
NT10BIX5570004 | 2012 | Q2 | Q2 - 2012 | During the second quarter of 2012 Fiber construction continued for core, middle and last mile. CPOP Grand Opening was held for our Dahlonega location. Twenty-one new SPOP's were deployed during the second quarter. Our fiber optic ring was deemed fully operational on both sides of our network as of June 29, 2012. Evaluation of last mile customers continued, as well as, negotiations with business and anchor institutions. | 490 | 188 | 0 | 0 | 490 | 0 | 0 | 245 | Meets baseline report | Meets baseline report | N/A NGN had no existing network. | N/A NGN had no existing network. | Meets baseline report | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Meets baseline report | 0 | 5 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant continued during the second quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | Construction of fiber plant continued during the second quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | N/A | Construction of fiber plant continued during the second quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | 0 | 0 | 0 | 0 | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Most community anchors will be completed in third quarter of 2012. Customers with erate or USAC services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Most community anchors will be completed in third quarter of 2012. Customers with erate or USAC services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Most community anchors will be completed in third quarter of 2012. Customers with erate or USAC services are scheduled to change effective July 2012. | Marketing executives have continued meeting with the community anchors that are going to be passed as part of this network. Planning has continued to lay out the network with the most impact in the shortest time. Most community anchors will be completed in third quarter of 2012. Customers with erate or USAC services are scheduled to change effective July 2012. | 17107 | 6313 | 410 | 5903 | 0 | Meets baseline report | Meets baseline report | Last mile marketing efforts will continue until the end of the project which will add additional subscribers receiving new access. | Meets baseline report | 45 Customers 30x30 325 Customers 15x15 3 Customers 6x6 37 Customers 12x12 | 909 | 599 | 24 | 575 | 0 | Meets baseline report | Meets baseline report | Last mile marketing efforts will continue until the end of the project which will add additional subscribers receiving new access. | Meets baseline report | 20 Customers 20x20 4 Customers 50x50 | N/A | FALSE | N/A | SPOP construction will continue in third quarter of 2012. Turn up of customers will continue in the third quarter of 2012. Last mile fiber construction will continue during the third quarter. CPOP grand openings are planned in Dawson, Forsyth and Union during August 2012. Implementation of major equipment located in the CPOP in Union will continue. Installation of additional SPOP locations will continue during the third quarter. We will continue to develop and implement testing plans and procedures. Twenty-seven CAI's with new or improved service completed during third quarter of 2012. One wholesale provider contract will be executed during the third quarter of 2012. A minimum of five additional miles of fiber deployment is planned during third quarter of 2012. | North Georgia Network Cooperative, Inc. | Third quarter 2012 will reflect additional funds expended for core, middle and last mile deployment. We do expect to be ninety-two percent complete which will meet our baseline milestones. | We do not anticipate any challenges or issues with meeting our projections for the third quarter. Last mile fiber construction will continue during the third quarter. CPOP grand openings are planned in Dawson, Forsyth and Union. Implementation of major equipment located in the CPOP's in Union will continue. Installation of additional SPOP locations will continue during the third quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will continue in the third quarter.
NT10BIX5570004 | 2012 | Q3 | Q3 - 2012 | During the third quarter of 2012 Fiber construction continued for core, middle and last mile. Six new SPOP's were deployed during the third quarter of 2012. Evaluation on last mile customers continued, as well as, negotiations with business and anchor institutions. Twenty-two CAI's were connected during third quarter of 2012. | 500 | 188 | 0 | 0 | 500 | 0 | 0 | 250 | Two miles of middle mile fiber was not completed until the second week of October | Meets baseline report | N/A NGN had no existing network. | N/A NGN had no existing network. | Two miles of middle mile fiber was not completed until the second week of October | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Meets baseline report | 0 | 5 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction of fiber plant continued during the third quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | Construction of fiber plant continued during the third quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | N/A | Construction of fiber plant continued during the third quarter of 2012. Meetings have continued with potential wholesale or last mile providers. | 22 | 0 | 22 | 0 | An additional sixty eight customers will be completed during fourth quarter 2012 | More customer are receiving improved access instead of new | An additional sixty eight customers will be completed during fourth quarter 2012 | 14 - 1000 x 1000 1 - 500 x 500 1 - 10 x 100 2 - 25 x 25 3 - 20 x 20 1 - 10 x 10 | 18268 | 6849 | 907 | 5942 | 0 | Last mile marketing efforts will continue until the end of the project which will add additional SPOP's to have more entities passed | Meets baseline report | More customer are receiving improved access instead of new | Meets baseline report | 14 - 3 x 3 23 - 6 x 6 218 - 12 x 12 567 - 15 x 15 85 - 30 x 30 | 1111 | 639 | 64 | 575 | 0 | Meets baseline report | Meets baseline report | Meets baseline report | Meets baseline report | 4 - 12 x 12 10 - 15 x 15 41 - 20 x 20 3 - 30 x 30 6 - 50 x 50 | N/A | FALSE | N/A | SPOP construction will continue in fourth quarter of 2012. Turn up of customers will continue in the fourth quarter of 2012. Last mile construction will continue during the fourth quarter. CPOP grand opening are planned in Dawson, Forsyth and Union during November 2012. Installation of 5 SPOP locations will continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Sixty-eight CAI's will new or improved service will be completed during the fourth quarter of 2012. Two wholesale provider contracts will be executed during the fourth quarter of 2012. Two additional miles of middle mile construction will be completed during the fourth quarter of 2012. | North Georgia Network Cooperative, Inc. | Our project is scheduled for completion on November 30, 2012. We should be one hundred percent complete with construction. The final close out invoices being paid prior to February 28, 2012. | We do not anticipate any challenges or issues with meeting our projections for the fourth quarter. Last mile fiber construction will continue during the fourth quarter. CPOP grand openings are planned in Dawson, Forsyth and Union. Installation of additional SPOP locations will continue during the fourth quarter. We will continue to develop and implement testing plans and procedures. Planning and installation of last mile customers and community anchors will continue in the fourth quarter.
NT10BIX5570004 | 2012 | Q4 | Q4 - 2012 | Our project was completed on time on November 30, 2012. During the fourth quarter of 2012 fiber construction continued for middle and last mile. The final SPOPs were deployed during the fourth quarter of 2012 (for a total of 50 SPOPs). Evaluation on last mile customers continued, as well as, negotiations with business and anchor institutions. 72 new CAI's were connected during fourth quarter of 2012 bringing the total number connected to 94. NGN has hooked up a variety of CAIs including but not limited to hospitals, medical facilities, school systems, colleges, technical colleges, public safety, libraries and government facilities in our footprint. | 500 | 184 | 0 | 0 | 500 | 0 | 0 | 285 | Meets baseline report | Revised from 224 miles which included slack in fiber; baseline report had 188 estimated miles. | Meets baseline report | Meets baseline report | Meets baseline report | N/A Not applicable over entire life of project. | N/A Not applicable over entire life of project. | Meets baseline report | 0 | 9 | 0 | In NGN's baseline report, we identified that we would have 3 Broadband Wholesalers or Last Mile Provider by the end of our project (11/30/2012). NGN has wholesale contracts with its 3 members who were considered subrecipients under the grant (Habersham EMC, Blue Ridge Mountain EMC and Connect North Georgia) and therefore do not count as signed agreements. NGN members have been successful in marketing and signing up customers as last mile providers. | As noted under 5b, NGN has signed agreements with its members in which NGN provides wholesale services to the members. | N/A | 0 | 0 | 0 | 0 | Meetings have continued with potential wholesale or last mile providers. | Meetings have continued with potential wholesale or last mile providers. | Negotiations have taken place with potential dark fiber customers. | N/A | 94 | 73 | 21 | 0 | Exceeds baseline report. | N/A | N/A | 14-1000 x 1000 1 - 500 x 500 1 - 100 x 100 1 - 85 x 85 6 - 50 x 50 4 - 25 x 25 41 - 20 x 20 8 - 15 x 15 3 - 12 x 12 4 - 10 x 10 3 - 5 x 5 | 21559 | 7741 | 1850 | 5891 | 0 | Baseline report of 24,000 is slightly higher. Last mile routes were constructed to maximize committed subscribers thus changing the number slightly | Exceeds baseline report of 6,414 | More customers are receiving improved access instead of new | Meets baseline report | 97 - 3 x 3 86 - 6 x 6 323 - 12 x 12 1,148 - 15 x 15 9 - 30 x 30 187 - 50 x 50 | 1364 | 706 | 131 | 575 | 0 | Exceeds baseline report of 621 | Excceds baseline report of 252 | Exceeds baseline report of 61 | Exceeds baseline report of 191 | 9 - 5 x 5 18 - 12 x 12 27 - 15 x 15 153 - 20 x 20 10 - 25 x 25 1 - 30 x 30 19 - 50 x 50 | N/A | FALSE | N/A | Since construction has been completed for the grant, NGN will continue to negotiate with wholesale and last mile providers to bring additional customers to the network along with adding additional services/customers with our own funding. NGN and its members continue to provide last mile drops to customers in our region along with plans to expand our network into other areas as funding permits. | North Georgia Network Cooperative, Inc. | Our project was completed as scheduled on November 30, 2012. Approximately $375,000 (Federal drawn down = $303,795.35) remains to be paid for work finished before November 30, 2012. The remaining invoices will be paid before February 28, 2013. | Our project is complete. NGN will continue to negotiate with wholesale and last mile providers to bring additional customers to the network along with adding additional services/customers with our own funding. NGN and its members continue to provide last mile drops to customers in our region along with plans to expand our network into other areas as funding permits. NGN is already working with local schools and universities along with other entities to bring broadband awareness to & educate the community on the benefits of fiber and broadband. NGN appreciates the opportunities that this grant project has given North Georgia Network, but more importantly to the citizens of the North Georgia region who will be the beneficiaries of this project for many years to come.
NT10BIX5570009 | 2010 | Q3 | Q3 - 2010 | Merit has satisfied the Environmental Assessment Special Award Condition by receiving a "Finding of No Significant Impact" (FONSI) before the deadline. We have also hired an engineering firm and have started engineering on the project. Merit has started the permitting process to lead us to the construction phase of the project. Merit is also reviewing RFP's for Hardware, Materials, Cable, and Construction. It is anticipated that all decisions will be final early next quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | None Noted | N/A | N/A | None Noted | 0 | 0 | 0 | N/A | N/A | It is anticipated that 3 sub-recipients will be participating in this "condo" build. Each sub-recipient will own strands in the build depending on the segment/location of the build. The 3 sub-recipients anticipated to participate are as follows: LYNX Network Group, LLC: This sub-recipient will own fiber on all segments of the build. Their contact information is as follows: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. (D.B.A. - ACD.net): This sub-recipient will own fiber on all segments of the build. Their contact information is as follows: Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. (D.B.A. - TC3Net): This sub-recipient will own fiber from Monroe, MI to Benton Harbor, MI. Their contact information is as follows: Joe Mattaucsh, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | 43 | 0 | 0 | 43 | None Noted | None Noted | None Noted | All 43 at 1 Gbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Some construction will be able to start during this quarter. We will be making the decision on all RFP's that have been posted and all of the contracts with the vendors and partners will be in place. Merit intends to make decisions on are the Cable, Materials and Construction RFP's in this quarter. A majority of the engineering will be completed and we will have all of the information necessary to initiate route changes throughout. | Merit Network Inc. | The major challenge that Merit has ran into is the permits with local governments. Many local governments have proposed route changes for various reasons and/or are proposing changes to the rights-of-way agreements. To get through these issues we are reaching out to these municipalities and meeting with them one-on-one to work out the details of the agreements. We are also in the process of developing contracts with our partners on the build. The negotiation of the contracts have been slower than originally anticipated due to the complexities of the project as a whole. To help speed the process we have proposed a fixed cost pricing to alleviate sub-recipients risk of overages on the build. This strategy appears to be appealing to them considering it limits their exposure. | Merit anticipates that the route changes resulting from engineering, permit applications, and municipality input will take time to develop and coordinate internally. Approval from the NTIA, considering the Environmental Assessment, will take time to go through review. This may hinder the permitting as well as construction in some areas. As more organizations are getting funding for there Round 2 applications Merit has discovered that we are overlapping with Bloomingdale in the Southwestern region of Michigan. We are currently working with Bloomingdale to propose how we will handle the build route and cost allocation to the NTIA for approval.
NT10BIX5570009 | 2010 | Q4 | Q4 - 2010 | Merit was able to construction 15 miles of underground fiber infrastructure placed in existing conduit in Manistee, MI. Merit has announced the selection a construction firm to be one of the several contractors that will be assisting Merit on this build. Merit has announced it's selection of the Cable, Materials and Fiber vendors on the build. Merits Requests for Proposals (RFP's) was posted on our web site and available to the public. Merit also sent out e-mail notifications to known vendors and organizations. Merit reviewed all RFP's and interviewed several candidates before make its selection. 85% of engineering of the route is complete and permitting had started in all corridors of the network. Permitting has been initiated with over half the proper agencies and the process is underway. Merit has also coordinated with Bloomingdale Communications to work out the details of overlap in the Southwest of Michigan. Merit has also applied for a route change to purchase existing fiber in Monroe County. Merit expects cost savings from purchasing existing fiber, as opposed to constructing new fiber, would be allocated to cost overruns in make-ready fees and construction. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | 0 | 0 | 0 | N/A | N/A | It is anticipated that 3 sub-recipients will be participating in this "condo" build. Each sub-recipient will own strands in the build depending on the segment/location of the build. The 3 sub-recipients anticipated to participate are as follows: LYNX Network Group, LLC: This sub-recipient will own fiber on all segments of the build. Their contact information is as follows: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. (D.B.A. - ACD.net): This sub-recipient will own fiber on all segments of the build. Their contact information is as follows: Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. (D.B.A. - TC3Net): This sub-recipient will own fiber from Monroe, MI to Benton Harbor, MI. Their contact information is as follows: Joe Mattaucsh, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | All at 1 Gdps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit plans to have more construction completed as well as deployment of equipment in the the build areas and potentially other CAI's. Permitting should be coming back with approvals or changes that may be needed. We will also be developing internal procedures to monitor and track the project moving forward with our sub-recipients and vendors. Our main focus for this quarter will be the completion of the permitting process considering this is a critical path to construction. | Merit Network Inc. | Merit anticipates that the route changes resulting from engineering, permit applications, and municipality input will take time to develop and coordinate internally. Approval from the NTIA, considering the Environmental Assessment, will take an unknown amount of time to go through review. This may hinder the permitting as well as construction in some areas. The volume of permitting we are presenting to some agencies is beyond their capacity and subsequently we have been getting a bit of push back from the agencies. We are working through these issues with the agencies by meeting with them on a regular basis. | Permitting will continue to be our biggest struggle given the quantity and the capacity of the permitting agencies. We are mitigating this by working with the various agencies to develop a process that is streamlined. Merit has weekly meetings with several permitting agencies to work through these issues. Other struggles will include route changes to be complete given that Merit has not gone through the process at this point and need an extenuating amount of information to complete the request.
NT10BIX5570009 | 2011 | Q1 | Q1 - 2011 | Merit has submitted Davis Bacon Act wage determinations for approval. 90% of the route engineered has been engineered. All known permitting has been submitted and we are starting to receive approved permits. Merit has meet with multiple pole owners to expedite pole permit approvals and make-ready construction. The Monroe route change was approved. Route changes necessitated by Special Awards Conditions and engineering requirements have been submitted to the Federal Program Officer. | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | To ensure compliance with all award requirements, Merit is waiting to receive the applicable Davis Bacon Act wage determinations before working with additional construction crews to install infrastructure. | No variance | No variance | No variance | To ensure compliance with all award requirements, Merit is waiting to receive the applicable Davis Bacon Act wage determinations before working with additional construction crews to install infrastructure. | N/A | N/A | No variance | 0 | 0 | 0 | None at this time. | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | We have not lit any fiber at this time. | We have not lit any fiber at this time. | We have not lit any fiber at this time. | We have not lit any fiber at this time. | 0 | 0 | 0 | 0 | We have not lit any fiber at this time. | We have not lit any fiber at this time. | We have not lit any fiber at this time. | We have not lit any fiber at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Construction will be underway for the Benton Harbor to Mackinaw and Mt. Pleasant to Hillman areas of our infrastructure project. Merit will begin to engineer lateral fiber builds to community anchor institutions. | Merit Network Inc. | Obtaining pole permits and right of way agreements continues to be our biggest challenge. To overcome this challenge, we have been meeting in person with municipalities, pole owners, and our engineering firm to find ways to expedite the application process. For third party make-ready, Merit will pay any fees necessary for construction to start and seek reimbursement from the pole owners when the third parties make payment. Wage determinations are vital to signing contracts with our construction contractors; Merit has submitted the necessary wage determination paperwork and is awaiting a response from the Department of Labor. | Coordinating several construction companies to keep the work flowing progressing may be challenging. In anticipation, Merit has hired an individual to assist with coordinating construction crews. Based on the route changes Merit has submitted, we believe it will be very difficult to build in areas that deviate from the approved route. If there are unforeseen engineering or construction problems with the approved route, Merit may have to choose between spending additional time to obtain approval for a route change, or spend additional time and money completing the originally proposed route.
NT10BIX5570009 | 2011 | Q2 | Q2 - 2011 | Bulk fiber and materials orders have been placed to prepare for increasing amounts of construction. A storage facility for warehousing fiber and materials was located and the process of contract negotiation is currently underway, and security measures are being analyzed. We have implemented multiple tools to track and monitor construction. Currently have agreements with 40 community anchor institutions and also we have collocation contracts in place with a majority of the sites necessary to make the network operationally viable. Make-ready for pole attachments have been moving along and many make-ready estimates have been paid and an in the construction process. Merit has hired a temporary position to work solely on follow up of these permits. Only 9 right-of-way permits were not returned and we have the Michigan Public Service Commission contacting the municipalities for clarification. If no response is received the commission will approve the permits. Merit has submitted route changes and is currently awaiting guidance on the process of the environmental completion. Construction contractors now have signed contracts due to the wage determinations approved by the Department of Labor. Posted a position for Project Manager and Environmental Assessor. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | To ensure compliance with all award requirements, Merit is waited to receive the applicable Davis Bacon Act wage determinations before working with additional construction crews to install infrastructure. | No variance | No variance | No variance | To ensure compliance with all award requirements, Merit is waited to receive the applicable Davis Bacon Act wage determinations before working with additional construction crews to install infrastructure. | N/A | N/A | To ensure compliance with all award requirements, Merit is waited to receive the applicable Davis Bacon Act wage determinations before working with additional construction crews to install infrastructure. | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Route changes will be completed or direction will be made to approve at least 50% of these changes. Continue to work with pole owners to complete make-ready on poles across the state. About 18 Community Anchor Institutions will be connected and multiple Collocation sites will be engineered. Merit will build in areas where the Environmental Assessment is consistent with engineering. We project that we will have a total of 69 miles new underground completed. | Merit Network Inc. | Merit is working on many route changes, and we are continuing to correspond with our Federal Program Officer and creating supporting documentation on the matter. Changes have been made to the route due to engineering issues. To get these approvals, Merit has created multiple documents and spreadsheets to explain the changes in great detail. Certain materials have been in short supply and long lead times are anticipated. Merit needs approval to purchase from countries not list on the Buy American Act list. As of June 30, we were currently awaiting approval. | We anticipate delays due to length of time it has taken so far to have route changes approved. We are continuing to correspond with our Federal Program Officer and creating supporting documentation on the matter. Certain materials have been in short supply and long lead times are anticipated; however, we have placed orders for fiber and materials for the entire network build and set up a facility for storage to ensure all necessary supplies are on hand.
NT10BIX5570009 | 2011 | Q3 | Q3 - 2011 | All known Round 1 permits have been submitted, and 56% of permits for Round 1 have been approved. We just released a southern segment for construction, which is located from Monroe to Adrian, Michigan. Released our last known RFP for the entire project one month ago. Several overlap agreements were put in place with other ARRA fund recipients. Merit had our A-133 Audit and we also had an NTIA audit/site visit. Merit also secured a warehouse facility for improved logistics, hired a Project Manager and an Environmental Compliance Manager. | 57 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | With various delays in both construction and environmental permitting with multiple entities and to ensure compliance with all award requirements, Merit is waiting until appropriate clearance has been given before working with multiple construction crews to install infrastructure. | No variance | No variance | No variance | With various delays in both construction and environmental permitting with multiple entities and to ensure compliance with all award requirements, Merit is waiting until appropriate clearance has been given before working with multiple construction crews to install infrastructure. | N/A | N/A | With various delays in both construction and environmental permitting with multiple entities and to ensure compliance with all award requirements, Merit is waiting until appropriate clearance has been given before working with multiple construction crews to install infrastructure. | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Route changes will be completed or direction will be made to approve at least 50% of these changes. Continue to work with pole owners to complete make-ready on poles across the state. About 18 Community Anchor Institutions will be connected and multiple Collocation sites will be engineered. Merit will build in areas where the Environmental Assessment is consistent with engineering. We project that we will have a total of 69 miles new underground completed. | Merit Network Inc. | Merit was required to re-engineer portions of our route, and we are continuing to correspond with our Federal Program Officer and creating supporting documentation on the matter. To get these approvals, Merit has created multiple documents and spreadsheets to explain the changes in great detail. All other challenges and issues are referenced in the above variance narrative. The re-engineering sometimes requires re-submission of permits or delays in permit issuance. | We anticipate delays due to the length of time it has taken so far to acquire the necessary construction and environmental permits as well as approval of route changes. We are continuing to correspond with our Federal Program Officer and creating supporting documentation on the matter. Certain materials have been in short supply however we have placed all orders for fiber and materials for the entire network build along with securing a 50,000 square foot warehouse to ensure all materials are on hand.
NT10BIX5570009 | 2011 | Q4 | Q4 - 2011 | Merit worked closely with the NTIA to prepare an addendum to Meritâ€™s Environmental Assessment (EA), classifying route changes by potential impact in terms of geography and the nature of the changes. This included work with the State Historic Preservation Office (SHPO) and United States Fish and Wildlife Service (USFWS) to obtain departmental approval of proposed route changes, and correspondence with tribes who had inquiries after the Tower Construction Notification System (TCNS) broadcast went out. The EA amendment and required Award Action Request (AAR) was approved by the Grants Office. Merit continued to work with BTOP recipient Bloomingdale Communications on overlapping route segments, and began to lay conduit. Merit continues to work with Allband, a BIP recipient with overlapping segments in Northeast Michigan; an agreement was signed. Merit submitted an AAR request for our new Network Operations Director to replace our former Network Operations Director, who was listed as a key person on Meritâ€™s grant application. Merit completed our A-133 audit, which revealed no instances of noncompliance and no Federal Program findings. Meritâ€™s Engineering and Compliance teams reviewed the Route/Switch RFP responses. Our project manager met with a large utility that was non-responsive to permit applications, and was able to obtain approvals for outstanding permit requests. Merit completed the Key Project Indicator (KPI) report requested by the NTIA. | 85 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | Merit anticipates completing most of the fiber construction during the next two quarters. We currently have 15 crews in the field. | No variance | No variance | No variance | Merit anticipates completing most of the fiber construction during the next two quarters. We currently have 15 crews in the field. | N/A | N/A | While some infrastructure has been installed, there are not enough contiguous segments constructed to bring in testing and splicing crews. We anticipate interconnection points will be added and/or upgraded next quarter. | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | We anticipate construction and environmental permitting will be complete for the approved route. Merit plans to complete additional middle mile fiber installation, and start testing and lighting fiber. Merit will deploy optical equipment and purchase route/switch equipment. Our engineers will be working all over Michigan to complete a significant number of inside plant work and connect anchor institutions to the outside plant fiber as it is constructed. Merit will be working with our subrecipients to connect to central office facilities, including general installation, wiring, and connecting project-funded central office equipment. Merit projects that next quarter there will be: - 125 new network miles deployed; - 25 new network miles leased; - 2 community anchor institution subscribers served; and - 3 signed agreements with wholesalers and/or last mile providers. | Merit Network Inc. | Merit was required to re-engineer portions of our route due to excessive permitting costs, uncooperative municipalities and pole owners, and physical impediments. Merit worked extensively with our Federal Program Officer and creating supporting documentation and obtaining formal approval. Re-engineering sometimes requires re-submission of permits or results in delays in permit issuance; in addition, obtaining the required environmental permits from state agencies has required several full-time staff members and multiple re-submissions. All other challenges and issues are referenced in the above variance narrative. | We believe we will have overcome most of the major challenges and issues that could impact progress against our project milestones with the exception of weather. Although this winter has been mild, it is still possible that conditions may delay some installation in some areas of the state.
NT10BIX5570009 | 2012 | Q1 | Q1 - 2012 | Construction in the Bloomingdale Joint Build area has begun with both underground and aerial construction. Crews are also working in the Southern, Eastern, Western, and Central Corridors. All permit requests have been submitted to the appropriate parties. Merit has all necessary poles for project completion in Make Ready or Final Review. All Fiber for the Round 1 project has been ordered. Merit has received permits from the Michigan Department of Environmental Quality (MDEQ) for Allegan, Berrien, Branch, Cass, St. Joesph, Van Buren, Isabella, Clare, and Gladwin counties. | 123 | 0 | 50 | 0 | 173 | 0 | 0 | 0 | Delays in some of the milestone categories has resulted in a delay in fiber installation; however, once construction is fully underway Merit anticipates closing the gap between our Baseline Report and the reported totals. | No variance. | No variance. | No variance. | Delays in some of the milestone categories has resulted in a delay in fiber installation; however, once construction is fully underway Merit anticipates closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | We have not lit fiber at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit plans to complete additional middle mile fiber installation, and start testing and lighting fiber. Merit will deploy optical equipment and purchase route/switch equipment. Merit's engineers and contractors will be working throughout Michigan to complete the bulk of the inside plant work and connect anchor institutions to the outside plant fiber as it is constructed. Merit will be working with the project's subrecipients to connect to central office facilities, including general installation, wiring, and connecting project-funded central office equipment. - Estimate of the number of miles you plan to deploy next quarter: 35 - Estimate of the number of CAIs you plan to connect by the end of the next quarter: 3 - Estimate of the number of broadband wholesaler/last mile provider agreements you plan to sign by the end of the next quarter: 3 | Merit Network Inc. | The length of time it has taken to get our Finding of No Significant Impact and get permits continues to impact the project, but we do anticipate gaining ground during the second and third quarters in 2012. Merit is still working to obtain the few remaining pole permits and complete make ready prior to construction. Construction was slowed January-March due to weather in northern Michigan, however Merit anticipates completing most of the remaining construction during the spring and summer months. | Merit does not project encountering any challenges or issues leading to delays unique to this quarter, with the exception of possible weather delays. The length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues to impact the project, but we do anticipate completing most of the remaining construction during the second and third quarters in 2012 and beyond.
NT10BIX5570009 | 2012 | Q2 | Q2 - 2012 | By May 2012, Merit had released all segments for construction, and work in these segments began. Merit has finalized remaining easements needed for construction. Merit put together a final materials order that will provide any remaining materials for the rest of the project. Merit has formed an environmental inspection team to finalize documentation and perform pre- and post-construction inspection to ensure environmental compliance. Merit worked with pole owners and municipalities to expedite remaining make ready work and permit issuance. As of June 30, 2012, Merit had been issued 97% of known needed permits. Consumers energy has provided permits at an accelerated rate and given Merit specific dates in next quarter when to expect outstanding permits. Merit interconnected the REACH DWDM (10GB) network to existing Merit infrastructure at the Monroe ISD and Monroe Community College in Monroe, MI. Merit connected Reach I fiber to the BTOP-funded Reach II fiber at the Mackinaw Bridge. Merit completed fiber work to Mackinaw Public Schools with lighting expected in the following quarter. Merit submitted all CAI addition and removal requests and documentation to the NTIA for review. Merit completed fiber to the University of Michigan Biological Station in Pellston, Michigan, which will be lit in the next quarter. Approximately 50% of CAI sites are in the construction phase of the project. | 182 | 0 | 85 | 0 | 182 | 0 | 0 | 0 | Delays in some of the milestone categories has resulted in a delay in fiber installation; however, once construction is fully underway Merit anticipates closing the gap between our Baseline Report and the reported totals. In addition to the mileage listed, conduit and strand has already been installed along much of the route, ready for fiber to be pulled or hung as soon as contiguous stretches are available. | No variance. | No variance. | No variance. | Delays in some of the milestone categories has resulted in a delay in fiber installation; however, once construction is fully underway Merit anticipates closing the gap between our Baseline Report and the reported totals. In addition to the mileage listed, conduit and strand has already been installed along much of the route, ready for fiber to be pulled or hung as soon as contiguous stretches are available. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 subrecipients will participate in this infrastructure project. Each subrecipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | No variance. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed, which Merit anticipates occurring in the third quarter. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed, which Merit anticipates occurring in the third quarter. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed, which Merit anticipates occurring in the third quarter. | 2 | 0 | 2 | 1 | Although there were two Community Anchor Institutions connected to the BTOP funded network in Q2 2012, broadband service was only being provided to one by the end of the quarter. Additional Community Anchor Institutions will be connected as the middle mile is completed during the third and fourth quarter of 2012. | Both Community Anchor Institutions connected in the reporting quarter had access to broadband previously. | Additional Community Anchor Institutions will be connected as the middle mile is completed during the third and fourth quarter of 2012. | Both Community Anchor Institutions are connected at 1GB; one is currently receiving service at 1 GB; the other will begin to receive service in the following quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No additional special service offerings are planned, at this time, to deviate from the original application Attachment B -- Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit anticipates the completion of infrastructure installation and lighting of fiber in the Bloomingdale joint build, a collaborative project between Merit and Bloomingdale Communications, a BTOP recipient, in Southwest Michigan. Merit also plans to have interconnection with the Comnet project, another BTOP-funded project, in Hillsdale, Michigan complete. Merit plans to have segments from Monroe, MI to Hillsdale, MI and Kalkaska, MI to Grayling, MI complete and lit. Merit will continue to work on additional middle mile fiber installation, and start testing and lighting fiber. Merit anticipates having 95% of all strand and conduit in place by the end of the quarter. Merit anticipates increased deployment of optical equipment in the second half of the third quarter, and Merit's engineers and contractors will be working throughout Michigan to complete the bulk of the inside plant work and connect anchor institutions to the outside plant fiber as it is constructed. Merit will be working with the project's subrecipients to connect to central office facilities, including general installation, wiring, and connecting project-funded central office equipment. Projected number of miles deployed next quarter (not cumulative): 450 Projected number of CAIs connected next quarter (not cumulative): 15 Projected number of broadband wholesaler/last mile provider contracts expected to be signed next quarter: Merit has all three of the projected contracts in place. | Merit Network Inc. | The length of time it has taken to get our Finding of No Significant Impact and get permits continues to impact the project, but we do anticipate significant progress during the third quarter and completing by the end of the fourth quarter of 2012. Merit is still working to obtain the few remaining pole permits and complete make ready prior to construction. Merit has been active during the spring and summer months anticipates completing most of the remaining construction over the remaining months in the third and fourth quarter. Permitting for CAI lateral builds may be a challenge, but Merit is prepared to work with agencies to expedite issuance of permits or alter the construction method or route within the confines of the approved Environmental Assessment to facilitate the remaining builds. | Merit does not project encountering any challenges or issues leading to delays unique to this quarter. The length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues toimpact the project, but we do anticipate completing most of the remaining construction during the third quarter in 2012 with completion during the fourth quarter of 2012.
NT10BIX5570009 | 2012 | Q3 | Q3 - 2012 | Merit has received all outstanding forestry and Michigan Department of Environmental Quality permits for this project. Merit is making continued progress with construction, averaging 35-40 miles of completed infrastructure construction per week. Fiber will be blown through once the infrastructure is completed. Merit submitted an Award Action Request to remove some Community Anchor Institutions and replace with more committed Community Anchor Institution sites. The request was approved. Merit has all easements approved for the project. Merit has begun splicing fiber in the southeast and eastern segments of the Round 1 project. Merit obtained 97% of all permits needed for the Round 1 project. Merit held a press event in Monroe, Michigan in July of 2012 celebrating the first lit segment of the project. The event took place at Monroe Community College. Also of significance, Merit has worked with Bloomingdale to complete an overlap area of the project. The overlap area has been mostly completed except for an area affected by a pole permit issue in September 2012. | 441 | 0 | 85 | 0 | 441 | 0 | 0 | 0 | Delays in some of the milestone categories have resulted in a delay in fiber installation. However, construction is fully underway and Merit anticipates closing the gap between our Baseline Report and the reported totals. In addition to mileage listed, conduit and strand has already been installed along much of the route, and is ready for fiber to be pulled or hung as soon as contiguous stretches are available. Conduit Miles Installed as of Q3 2012: 277 Miles (includes purchased infrastructure) Strand Miles Installed as of Q3 2012: 608 Miles (includes purchased infrastructure) | No variance. | No variance. | No variance. | Delays in some of the milestone categories have resulted in a delay in fiber installation. However, construction is fully underway and Merit anticipates closing the gap between our Baseline Report and the reported totals. In addition to mileage listed, conduit and strand has already been installed along much of the route, and is ready for fiber to be pulled or hung as soon as contiguous stretches are available. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 sub recipients will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 0 | 0 | No variance. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed which Merit anticipates completing in the fourth quarter. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed which Merit anticipates completing in the fourth quarter. | Broadband wholesalers and last mile providers are waiting for contiguous segment of fiber to be installed which Merit anticipates completing in the fourth quarter. | 4 | 0 | 4 | 1 | Merit plans to connect and serve all approved CAIs by the project end date, which is at the end of the quarter ending 12/31/12. | N/A | Merit plans to connect and serve all approved CAIs by the project end date, which is at the end of the quarter ending 12/31/12. | Merit is serving the connected CAI with a 1Gbps connection; the other 3 CAIs did not subscribe to service in the reporting quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit anticipates the completion of infrastructure installation and lighting of fiber in the Bloomingdale joint build, a collaborative project between Merit Network and Bloomingdale Communications, a BTOP recipient, in Southwest Michigan. Merit is working towards completing backbone construction of the fiber network and blowing fiber through aerial and underground conduit. Once construction and fiber placement are completed Merit will begin testing and lighting fiber in preparation for service. Merit anticipates deployment of optical equipment in the fourth quarter. Meritâ€™s engineers and contractors will be working throughout Michigan to complete the inside plant work and connect Community Anchor Institutions to the outside plant fiber as it is constructed. Merit will be working with the projectâ€™s sub recipients to connect to central office facilities, including general installation, wiring, and connecting project-funded central office equipment. Community Anchor sites that received permits by October 1, 2012 are anticipated to be completed by November 1, 2012. Merit anticipates completing Community Anchor Institution sites that are waiting for permits by the end of the quarter. Merit also anticipates connecting the remaining fifty (50) Community Anchor Institution sites during the fourth quarter of 2012, with at least half of those receiving service during the fourth quarter of 2012. Many Community Anchor Institution sites have been completed, but we are waiting for backbone fiber to pass through so they can be connected. Estimated Miles to Deploy during Q4 2012: Strand - 44 Miles Conduit - 51 Total Completed Miles with Fiber - 526 Miles Estimated CAI sites to be connected during the Q4 2012: Connected - 50 Receiving Service-at least 25 will receive service during the quarter, the remaining will begin receiving service after the quarter | Merit Network Inc. | The length of time it has taken to get our Finding of No Significant Impact and to get permits continues to impact the project, but we do anticipate completing by the end of the fourth quarter of 2012. Merit is still working to obtain the few remaining pole permits and complete make ready prior to construction. Permitting for Community Anchor Institutions lateral builds may be a challenge, but merit is prepared to work with agencies to expedite issuance of permits or alter the construction method or route within the confines of the approved EA to facilitate the remaining builds. Managing large number of construction crews out in the field performing the build has been challenging. Merit conducts weekly status calls to gather updates regarding the progress to plan ahead for the coming weeks and to identify and resolve any issues that could obstruct the build. | The length of time it has taken to get our Finding of No Significant Impact and to get permits continues to impact the project, but we do anticipate completing by the end of the fourth quarter of 2012. Time has become a factor with only three (3) months remaining to complete the build, but Merits is working closely with its contractors to make sure that all construction stays on pace and is completed on time. Any last minute permitting that is needed to accommodate Job Change Orders or Field Change Orders could create a timing issue but Merit will work with the appropriate parties to expedite any challenges to reduce impact. Weather could become a factor as construction approaches the winter season, but Merit anticipates the construction being completed prior to winter weather conditions setting in.
NT10BIX5570009 | 2012 | Q4 | Q4 - 2012 | As of the end of the quarter, 98% of infrastructure is in place relating to the project. Final construction will be wrapping up which includes final fiber placement and splicing. Merit conducted daily calls with contractors to monitor the remaining work to ensure completion. The Bloomingdale project was completed with Merit and Bloomingdale signing off on completed construction for their joint build. Merit was granted a no cost extension to complete the remaining portion of the project in the subsequent quarter(s). | 966 | 0 | 34 | 0 | 966 | 0 | 0 | 0 | Delays in some of the milestone categories have resulted in a delay in fiber installation. However, construction increased at a rapid pace during Q3 and Q4 of 2012 and is near complete. Merit anticipates completing the remaining construction work in early 2013. | No variance | This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2012. | No variance | Delays in some of the milestone categories have resulted in a delay in fiber installation. However, construction increased at a rapid pace during Q3 and Q4 of 2012 and is near complete. Merit anticipates completing the remaining construction work in early 2013. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | We anticipate 3 sub recipients will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 3 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | Speed tiers that are available will be dependant on what the equipment of the wholesale providers are using. | 119 | 28 | 91 | 1 | Many CAI sites have been completed and connected, but are not receiving service until Q1 of 2013. | Will be receiving new access due to the REACH-3MC project. | Many CAI sites have been completed and connected, but are not receiving service until Q1 of 2013. All are receiving improved access over what they had before the REACH-3MC project. | All 119 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit anticipates completing the remaining construction during Q1 of 2013. Once construction and fiber placement are completed Merit will begin testing and lighting fiber in preparation for service. Merit anticipates deployment of remaining optical equipment in Q1 2013. Meritâ€™s engineers and contractors will be working throughout Michigan to complete the inside plant work and connect Community Anchor Institutions to the outside plant fiber as it is constructed. Merit will be working with the projectâ€™s sub recipients to connect to central office facilities, including general installation, wiring, and connecting project-funded central office equipment. Merit anticipates connecting the remaining Community Anchor sites. Miles Planned to Deploy in Following Quarter - 100% (1,010miles) of all fiber will be deployed Number of CAI's connected in Following Quarter - 100% (57 sites) will be connected | Merit Network Inc. | The length of time it has taken to get our Finding of No Significant Impact and to get permits continues to impact the project, but we do anticipate completing by early 2013. Merit received a no cost extension which will allow us to complete the project and deliver the services we promised to the state of Michigan. Managing large number of construction crews out in the field performing the build has been challenging. Merit conducts weekly status calls to gather updates regarding the progress to plan ahead for the coming weeks and to identify and resolve any issues that could obstruct the build. | Weather could impact the project during Q1 of 2013 but it is not expected to provide any notable delays.
NT10BIX5570009 | 2013 | Q1 | Q1 - 2013 | As of the end of the quarter, almost all of the construction has been completed, but Merit continues to test the network and make the necessary repairs to light the fiber. Merit has completed the build of all CAI sites and they are all connected, with the exception of two that elected not to participate and will be formally removed via Award Action Request. | 980 | 0 | 34 | 0 | 980 | 0 | 0 | 0 | Delays in some of the milestone categories have resulted in a delay in fiber installation. Construction was completed in quarter 1 in 2013. | No Variance | This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2012. | No Variance | Delays in some of the milestone categories have resulted in a delay in fiber installation. Construction was completed in quarter 1 in 2013. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | Merit has 3 sub recipients that will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 3 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 146 | 55 | 91 | 1 | Merit CAI sites that have been connected to the BTOP funded network. | Will be receiving new access due to the REACH-3MC project. | Merit CAI sites that have been connected to the network. All are receiving improved access over what they had before the REACH-3MC project. | All 146 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | During the next quarter, Merit anticipates completing testing on network infrastructure. Merit will be working with our contractors to complete any warranty repair work on network infrastructure before final acceptance. Merit is expecting to connect Round 1 infrastructure to Round 2 infrastructure. Merit will begin working on project closeout, if ready, during the next quarter. | Merit Network Inc. | Merit will no longer be connecting two community anchors to our project via BTOP-funded laterals. | Merit anticipates the following challenges in the next quarter: Completing testing of sub recipient fibers, connecting the Round 1 and Round 2 project together in the lower peninsula, completing warranty work on network infrastructure while not impacting service, and beginning to close out the project. Merit is working with our sub-recipients on fiber testing to ensure the fibers are acceptable. Merit is also working closely with our contractors on any warranty work to minimize impact on the rest of the network. Merit does not expect any of these tasks to delay project completion.
NT10BIX5570009 | 2013 | Q2 | Q2 - 2013 | Merit completed construction on network infrastructure and moved into the testing phase of the project. Warranty work is being worked on to repair any areas of the network infrastructure that are not functioning correctly. As-Built drawings are being finalized for the new network infrastructure. Final acceptance was completed with Bloomingdale communications on the co-build that they participated in with Merit. | 1010 | 0 | 34 | 0 | 1010 | 0 | 0 | 0 | Delays in some of the milestone categories have resulted in a delay in fiber installation. Construction was completed in quarter 1 in 2013 with testing now taking place. | No Variance | This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2012. | No Variance | Delays in some of the milestone categories have resulted in a delay in fiber installation. Construction was completed in quarter 1 in 2013 with testing now taking place. | N/A | N/A | N/A | 3 | 0 | 80 | We originally projected having 4 agreements, but only 3 parties chose to sign the agreement. LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | Merit has 3 sub recipients that will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, 4798 Campus Drive, Suite 111 Kalamazoo, MI 49008, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 3 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 146 | 55 | 91 | 1 | Merit CAI sites that have been connected to the BTOP funded network. | Will be receiving new access due to the REACH-3MC project. | Merit CAI sites that have been connected to the network. All are receiving improved access over what they had before the REACH-3MC project. | All 146 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | During the next quarter, Merit anticipates completing and receiving all As-Built drawings for the new network infrastructure. Merit will also be looking to complete testing and request all warranty work to be completed to resolve any outstanding issues. Merit will work with contractors to complete restoration work in construction areas. Merit will be working with municipalities to close out permits and to complete any outstanding tasks. Merit will be preparing to begin the closeout process. | Merit Network Inc. | Merit has been faced with challenges in getting As-Built drawings completed but is working closely with contractors and engineering firms to get the drawings completed. Merit has experienced issues coordinating warranty work to take place but is communicating with our Sub-Recipients and with the contractors to have necessary work completed. Testing has shown occasional issues with the fiber where warranty work and repair needs to be made, but that is being coordinated to contractors. | Merit could face difficulties during the coming quarter while working with different municipalities along the route to close out permits. Scheduling remaining testing and warranty work with the contractors and sub recipients could be a challenge but Merit will work with all parties involved to complete in a timely fashion. Preparing for grant closeout may generate issues but Merit will work with our Grant Administrator if any needs/issues come up.
NT10BIX5570009 | 2013 | Q3 | Q3 - 2013 | Merit has completed the REACH-3MC project and has closed out the project. | 1044 | 0 | 34 | 0 | 1044 | 0 | 0 | 66 | Merit has completed all REACH-3MC infrastructure construction, which was completed in Q1 in 2013. This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2014. | No Variance | This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2012. | No Variance | Merit has completed all REACH-3MC infrastructure construction, which was completed in Q1 in 2013. This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2014. | N/A | N/A | The project has been completed and Merit has reached the baseline projections. | 3 | 0 | 80 | LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | Merit has 3 sub recipients that will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, 4798 Campus Drive, Suite 111 Kalamazoo, MI 49008, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 3 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 146 | 55 | 91 | 1 | Merit CAI sites that have been connected to the BTOP funded network. | Will be receiving new access due to the REACH-3MC project. | Merit CAI sites that have been connected to the network. All are receiving improved access over what they had before the REACH-3MC project. | All 146 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit Network has completed the REACH-3MC project across the lower peninsula of the State of Michigan. As a result, the state and the communities and organizations within can begin utilizing the benefits of this project. Merit has built or upgraded over 1000 miles broadband infrastructure that will provide broadband connectivity throughout the state. This new infrastructure will provide upgraded service to areas that previously experienced poor connectivity, including areas that may not have even had broadband access. Community Anchor Institutions (CAI) will be connected to the network with a 1 GB connection while universities will be able to receive up to a 10GB connection. This will allow these anchors to collaborate and share data, and perform research in ways they could not do prior to the REACH-3MC project. Universities will now be able to connect to their satellite and remote facilities using the new network to conduct business and research in a more efficient and useful way. K-12 schools will now have more capacity to share resources and class work. Hospitals, libraries, public safety services, among others, will benefit from the new capacity and connectivity to perform their services to their respective communities. The REACH-3MC project has created the possibility for our Sub Recipient partners to offer last mile service to communities and business throughout Michigan that otherwise may not have been able to experience upgraded broadband. In addition to broadband benefits of the REACH-3MC project, new jobs have been added and communities across the state have received positive economic benefits. Merit has hired additional, full time staff, to oversee the implementation and management of the project from inception to completion. Merit also has added member relationship managers in areas around the state to work with new and existing members on how to best utilize the new network. Throughout the project, Merit staff and contractors visiting communities along the route to oversee the implementation of the project and putting money into small business within those communities. Merit partnered with 7 contractors who each brought on additional staff in order to meet the expectations and timelines necessary to ensure the project would be completed on schedule. Our Sub Recipient partners have hired upward of 20 new staff members as a result of the REACH-3MC project. Power companies in Michigan brought on additional resources to perform make ready in order for Merit to make attachments to poles. The project has given these power companies an opportunity to upgrade their old infrastructure in order to support the new REACH-3MC infrastructure. Lastly, Merit and its Sub Recipient partners have gained immense knowledge in operating and supporting an advanced optical network and technologies. | Merit Network Inc. | Merit has completed the REACH-3MC project and has closed out the project. | Merit has completed the REACH 3MC project and has closed out the project.
NT10BIX5570009 | 2013 | Q4 | Q4 - 2013 | Merit has completed the REACH-3MC project and has closed out the project. | 1044 | 0 | 34 | 0 | 1044 | 0 | 0 | 66 | Merit has completed all REACH-3MC infrastructure construction, which was completed in Q1 in 2013. This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2014. | No Variance | This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2012. | No Variance | Merit has completed all REACH-3MC infrastructure construction, which was completed in Q1 in 2013. This field had been tabulated incorrectly previously, and was corrected after an email exchange between Merit Network and the Federal Program Officer in December 2014. | N/A | N/A | The project has been completed and Merit has reached the baseline projections. | 3 | 0 | 80 | LYNX Network Group, LLC (fiber strands on all segments) KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) | None at this time. | Merit has 3 sub recipients that will participate in this infrastructure project. Each sub recipient will own strands in the network depending on the segment and location of the build. LYNX Network Group, LLC (fiber strands on all segments) Chris Barber, 4798 Campus Drive, Suite 111 Kalamazoo, MI 49008, Phone: 877.585.5969 KEPS Technologies, Inc. d.b.a. ACD.net (fiber strands on all segments) Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 The Computer Care Company, Inc. d.b.a. TC3Net (fiber strands from Monroe, MI to Benton Harbor, MI) Joe Mattausch, President, 247 S. Main St. Adrian, MI 49221, Phone: 517-266-0402 | 0 | 0 | 3 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 146 | 55 | 91 | 1 | Merit CAI sites that have been connected to the BTOP funded network. | Will be receiving new access due to the REACH-3MC project. | Merit CAI sites that have been connected to the network. All are receiving improved access over what they had before the REACH-3MC project. | All 146 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no additional special service offerings are planned that would deviate from the original application Attachment B-Proposed Middle Mile Service Offerings. | FALSE | N/A | Merit Network has completed the REACH-3MC project across the lower peninsula of the State of Michigan. As a result, the state and the communities and organizations within can begin utilizing the benefits of this project. Merit has built or upgraded over 1000 miles broadband infrastructure that will provide broadband connectivity throughout the state. This new infrastructure will provide upgraded service to areas that previously experienced poor connectivity, including areas that may not have even had broadband access. Community Anchor Institutions (CAI) will be connected to the network with a 1 GB connection while universities will be able to receive up to a 10GB connection. This will allow these anchors to collaborate and share data, and perform research in ways they could not do prior to the REACH-3MC project. Universities will now be able to connect to their satellite and remote facilities using the new network to conduct business and research in a more efficient and useful way. K-12 schools will now have more capacity to share resources and class work. Hospitals, libraries, public safety services, among others, will benefit from the new capacity and connectivity to perform their services to their respective communities. The REACH-3MC project has created the possibility for our Sub Recipient partners to offer last mile service to communities and business throughout Michigan that otherwise may not have been able to experience upgraded broadband. In addition to broadband benefits of the REACH-3MC project, new jobs have been added and communities across the state have received positive economic benefits. Merit has hired additional, full time staff, to oversee the implementation and management of the project from inception to completion. Merit also has added member relationship managers in areas around the state to work with new and existing members on how to best utilize the new network. Throughout the project, Merit staff and contractors visiting communities along the route to oversee the implementation of the project and putting money into small business within those communities. Merit partnered with 7 contractors who each brought on additional staff in order to meet the expectations and timelines necessary to ensure the project would be completed on schedule. Our Sub Recipient partners have hired upward of 20 new staff members as a result of the REACH-3MC project. Power companies in Michigan brought on additional resources to perform make ready in order for Merit to make attachments to poles. The project has given these power companies an opportunity to upgrade their old infrastructure in order to support the new REACH-3MC infrastructure. Lastly, Merit and its Sub Recipient partners have gained immense knowledge in operating and supporting an advanced optical network and technologies. | Merit Network Inc. | Merit has completed the REACH-3MC project and has closed out the project. | Merit has completed the REACH 3MC project and has closed out the project.
NT10BIX5570011 | 2010 | Q3 | Q3 - 2010 | MCNC received it's FONSI on 8/26/10. We closed out an RFP for materials in July/August and awarded a contract to NC based Commscope to provide construction materials. An RFP was issued and closed for identifying construction firms to perform the physical build in August/September, with Globe Communications selected to perform the work in the southeast and Fiber Tech selected to perform the work in the west. An optical RFP was issued and closed for identifying an equipment manufacturer to light the fiber, with Cisco Systems selected for that work. Formal IRU/swap agreements were finalized with two of our primary partners identified in the application, FRC and ERC. All engineering work is on schedule and relevant permits for priority construction activities have been applied for and many have started to be approved and received. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | While we did complete formal agreement with two providers for 197 miles of IRU fiber as noted above in the design, it will be some time before these miles are actually placed in to service. While 0% shown complete here is not a variance, we did want to explain why no miles are noted new here. | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 1 | 20 | FRC The Education and Research Consortium | MCNC is not providing wholesale service. The agreements spoken to above are part of IRU swaps that were negotiated and submitted to NTIA for approval. | FRC/Palmettonet, 1500 Hampton St. Suite 101 Columbia, SC 29201 has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once constructed. They will be providing route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise, while MCNC would be focused on the education, government and public health sectors. | 2 | 0 | 0 | 0 | Agreements have been signed, but service will not become active until network is constructed. We had forecast 3 at this point. We are still discussing with Balsamwest specific pieces of our work with them and have exchanged contracts for review, but they are not signed yet. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We expect to order equipment for lighting the Raleigh/Wilmington segment and begin that process. While our hope would be that it's complete, lead times on equipment may mean that it takes one more quarter for that. We expect to begin construction on five priority routes that represent approximately 200 miles of the infrastructure and perhaps have about 10-15% of those sections complete. We will also hold a ground breaking to promote the project. | MCNC | We have some concerns about turn around time requests related to items not specifically addressed under current NTIA rules. Specifically anything that requires a legal opinion seem to slow down. We have two pending requests of NTIA related to acquisition of an IRU from Morris Broadband versus a build as well as formalization of an agreement defined in our application with FRC that have been pending for months. Issuance of the FONSI took longer than expected, although as of now it has not materially delayed us to where we can't recover the lost time. | Successful receipt of ROW's from DOT will slow down some construction activities. As we approach winter, weather is always a concern. Beyond that, all our contractors for engineering, construction, and materials are lined up, so we hope to begin making more visible tangible success.
NT10BIX5570011 | 2010 | Q4 | Q4 - 2010 | During the quarter, we completed construction on approximately 7 miles. With the exception of a required reroute by the NC DOT on a 25 mile segment, all fiber has been engineered. The first significant equipment order was placed for lighting a 199 mile segment from Raleigh to Wilmington as approved by the NTIA. We received approval from the NTIA on the purchase of fiber via IRU from an existing carrier from Hendersonville to Cashiers that will replace 50 miles of previously planned build. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | Not applicable at this time. | We had forecasted 197 miles of fiber to be lit and operated from a previously owned IRU that NTIA funds paid for the equipment to operate. Efforts toward that completion had started but were not finished at the end of the quarter and as such amounts to this 197 mile variance. | Not Applicable | Not Applicable | We started construction later than anticipated due to permit and encroachment delay. However we are catching up in first part of 2011 and have no concerns. At end of quarter we'd place 7 miles of conduit but had not placed fiber yet. | Not applicable to our project | Not applicable to our project | We had forecasted placement of 58 handholds by this date. We were delayed getting to construction due to finalization of EA FONSI, permits, and engineering, but expect to normalize within Y2Q1 and Y2Q2. The 11 noted here are where he handholds have been placed, but fiber didn't get deployed by quarter end. | 2 | 0 | 80 | The Education and Research Consortium (ERC) FRC, LLC, a subsidiary of PalmettoNet | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and submitted to NTIA for approval and those sites are expected to supply those services | FRC/Palmettonet, 1500 Hampton Street, Suite 101, Columbia, SC 29201 - has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once constructed. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers and private enterprise. MCNC would be focused on the education, government and public health sectors. | 0 | 0 | 2 | 0 | Not Applicable | Not Applicable | No other arrangements beyond those previously noted with FRC and ERC have been completed. General talks with interested parties (Zayo and Dukenet Communications most notably) continue. Agreements are signed, but service not yet delivered. Previously these arrangements were noted in access rather fiber in error. | Not Applicable | 0 | 0 | 0 | 0 | Not applicable at this time | Not Applicable at this time | Not Applicable at this time | Not Applicable at this time | 0 | 0 | 0 | 0 | 0 | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | 0 | 0 | 0 | 0 | 0 | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | Not applicable to our project. | Not Applicable | FALSE | Not Applicable | We expect to have successfully deployed the first hardware as part of the project between Raleigh and Wilmington. We expect to have received a significant number of all permits/encroachments required on the project in the next quarter and have a minimum of 5 segments either completed or under construction totaling 150 of the planned miles in the project. We expect to placed more equipment orders related to the project as some of the 5 segments referenced are put in to service. | MCNC | We received a slight setback from the NC DOT with the denial of a permit on a piece of controlled access highway previously planned to traverse. While this will require a reroute and an addendum to the EA, it is not expected to impact the overall schedule of the project. We are also tracking a concern from our partner FRC with them having to move to sub-recipient status that at the end of the quarter had not been resolved. | With all permits for priority segments in hand at this point, the only major challenge we expect to potentially pose problems with our schedule will be adverse weather.
NT10BIX5570011 | 2011 | Q1 | Q1 - 2011 | MCNC used award funds to place in to service 197 miles of fiber previously owned between Raleigh and Wilmington using dense wave division multiplexing equipment. The first service enabled on this path is a 10Gbps IP network improving service to 490 community anchor institutes who are provided service through the Fayetteville and Wilmington NCREN points of presence and who were previously on a limited capacity lease of a 1Gbps backbone. Construction efforts ramped up significantly with approximately 120 miles of conduit placed by the end of the quarter through work on five defined spans of the project totaling approximately 150 miles of the overall build. While none of the conduit had yet had fiber deployed through it, construction of the conduit is the most significant part of the task in locating the fiber. The reason the fiber had not yet been placed was to allow for completion of the entire spans within a region before deploying any of the fiber for safety reasons of the fiber and balance of the project. An indefeasible right to use (IRU) was closed with an incumbent provider on 61 miles of fiber that were previously planned for construction between Hendersonville and Cashiers, but approved for acquisition by NTIA during 4th quarter of 2010. 95% of all required permits on all segments have been obtained by the end of the quarter for the entire project. In addition, equipment purchases and commits for $1.6M of the project have been made. | 7 | 258 | 197 | 0 | 462 | 0 | 0 | 133 | While we have officially only deployed 7 miles, we have constructed by end of quarter approximately 127 miles of fiber and conduit. Placement of fiber is the last work step and not the hard part of the construction process. While we are behind relative to the number reported in the baseline, we anticipate being fully caught up by no later than the end of Y2Q3. | 197 from ERC and FRC. 61 from Morris Broadband acquisition. | Put in to operation 197 miles from Raleigh to Wilmington that MCNC already had rights to the fiber. The BTOP project funded the equipment. | na | Total number of miles enabled by the project includes the existing miles upgraded MCNC previously owned (197), newly acquired miles this quarter from Morris (61), and all the miles acquired through agreements as part of the application (197) and fully constructed miles (7). | Not applicable | Not applicable | 76 are from fibers in the FRC acquisition. 16 from from fibers in the ERC acquisition. 23 from the Morris Broadband fiber acquisition. 18 from MCNC new builds. | 3 | 1 | 80 | The Education and Research Consortium (ERC) FRC, LLC, a subsidiary of PalmettoNet Morris Broadband (an IRU from them) | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and submitted to NTIA for approval and those sites are expected to supply those services. FRC is currently negotiating for a long term IRU sale of Dark Fiber assets along specific portions of the planned ring build. The potential customer is a company known as Zayo LLC, a Colorado company. Pricing for the fiber has been offered at a one time IRU fee of $1.8M, and annual maintenance fees of $70.19K, or $5848.00 per month. The deal has not yet closed. | FRC/Palmettonet has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once constructed. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers and private enterprise. MCNC would be focused on the education, government and public health sectors. | 2 | 0 | 2 | 0 | The baseline was incorrect due to interpretation of what was asked. We have two agreements where providers will receive fibers in BTOP funded routes. One is with the newly designated sub-recipient. The second agreement is with a different company (pending approval by NTIA of a sale/lease waiver) as part of a planned swap of fiber identified in the initial MCNC application. We have a signed agreement for the swap between the two organizations on fibers exchanged and maintenance components associated with it, and will be submitting the request for sale/lease waiver soon. Our baseline had forecasted swaps with another company that did not play out due to the arrangement shifting to straight IRU agreements. Weâ€™ve executed from them and anticipate at some point they will execute on BTOP fibers. The cumulative total to date is 2. | The baseline was incorrect due to interpretation of what was asked. We have two agreements where providers will receive fibers in BTOP funded routes. One is with the newly designated sub-recipient. The second agreement is with a different company (pending approval by NTIA of a sale/lease waiver) as part of a planned swap of fiber identified in the initial MCNC application. We have a signed agreement for the swap between the two organizations on fibers exchanged and maintenance components associated with it, and will be submitting the request for sale/lease waiver soon. Our baseline had forecasted swaps with another company that did not play out due to the arrangement shifting to straight IRU agreements. Weâ€™ve executed from them and anticipate at some point they will execute on BTOP fibers. | Similarly to the above two responses, our baseline turns out to be wrong based on interpretation at the time of completing it. To date, only two agreements for access to new fibers have occurred. | Not Applicable | 497 | 0 | 497 | 497 | This number represents the number of CAI's on MCNC's network that receive service through the NCREN points of presence in Fayetteville and Wilmington. With the deployment of the new fibers and equipment to these areas, these users went from a limited 1Gbps shared arrangement to a 10Gbps IP backbone. The reason the number missed what was reported in the baseline is due to a slower than expected deployment on the fibers that were to be constructed by the end of this quarter. As we begin deployment of the constructed fibers in Y2Q2 and Y2Q3 we anticipate recovering. | na | This number represents the number of CAI's on MCNC's network that receive service through the NCREN points of presence in Fayetteville and Wilmington. With the deployment of the new fibers and equipment to these areas, these users went from a limited 1Gbps shared arrangement to a 10Gbps IP backbone. The reason the number missed what was reported in the baseline is due to a slower than expected deployment on the fibers that were to be constructed by the end of this quarter. As we begin deployment of the constructed fibers in Y2Q2 and Y2Q3 we anticipate recovering. | 10Gbps shared backbone is available to all of these subscribers with more bandwidth available to be provisioned as required. | 0 | 0 | 0 | 0 | 0 | N/A to our project | N/A to our project | N/A to our project | N/A to our project | N/A to our project | 0 | 0 | 0 | 0 | 0 | N/A to our project | N/A to our project | N/A to our project | N/A to our project | N/A to our project | We are able to provide lambda based point to point based circuits between the NCREN POP's enabled by the new infrastructure. | FALSE | na | We anticipate placement of at least 100 miles of fiber in the sections of conduit that have been completed thus far. Additionally we believe we will deploy another 120-150 miles of conduit in the quarter ending in June. Our hope will be to deploy equipment on the fibers enabled to Asheville and Greenville, but this activity may slip until later in the summer. All permits should be received by the end of this quarter and we would anticipate having all 11 segments of the network under active construction or complete. We lastly expect to close on both the Plateau and Balsamwest IRU's to enable approximately 38 miles in the far western part of the network. | MCNC | It was a good quarter. The biggest challenges have continued to be final acquisition for all relevant encroachment agreements from NC DOT, as well as a few sticking ones with various railroad operators. They've certainly taken longer than we forecasted, but we feel good with where we're at at this point. Communication and feedback from NTIA has improved dramatically over the last quarter. Input and feedback is timely. As we have shifted to construction the challenges are now different and relate more to local issues in the field with dealing with cuts of utilities, working with contractors to make sure they are not impacting homeowners and businesses on the route, etc. At this point we feel confident about our ability to finish the project ahead of schedule. Biggest area we need to solve soon will be guidance on how to sale and lease fiber if new guidance is forthcoming. | At this point we don't anticipate any challenges beyond potentially adverse weather. All contractors are performing well and are under contract for completion of the project. All segments in our project plan will be released for construction by end of the quarter and in doing so, the crew will ramp up at a quicker pace.
NT10BIX5570011 | 2011 | Q2 | Q2 - 2011 | Construction efforts continued to proceed briskly. With all activities related to engineering/permitting nearly complete, most activities in the quarter related to project oversight of construction and planning efforts around deployment of equipment. At the end of the quarter construction of approximately 310 miles of the 413 engineered conduit miles had been completed, with placement of approximately 105 miles of fiber within that conduit. All remaining planned Indefeasible Rights to Use for fibers were closed with incumbent providers on approximately 33 miles during the quarter. All required permitting for the remainder of the project is nearly complete, with a few railroad permits the outliers. For the July-September quarter we anticipate completing all construction activities and placing in to production service several spans of the recently completed construction. The project is currently about one year ahead of schedule. | 107 | 291 | 197 | 0 | 595 | 0 | 0 | 865 | In total we have deployed 107 miles of fiber and 310 miles of conduit. While we are behind the number reported in the baseline due to the delay in the start of construction, we anticipate being fully caught up by end of Y2Q3. The construction of the conduit is what takes 90-95% of the time per segment to complete. When the fiber crews get started as the conduit is complete, they are able to complete 2-3 miles a day across the footprint. Both crews are on pace to complete all construction activities by end of September based on forecasts they are currently giving. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our reporting efforts. As it relates to leasing (or in our case acquisition under IRU), we have now fully executed all that were planned. The total of 291 is from 197 from ERC and FRC routes communicated in application, 61 from Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP funded the equipment. | NA | We had forecasted 546.5 in our baseline and at this point are ahead of our baseline. | NA | NA | We had projected 160 in our baseline and are well above that. This number is representative of all splice enclosures and hand holds on our new builds as well as acquired fibers that have agreements allowing for interconnect at existing access points like hand holds and splice points. | 2 | 4 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. FRC, our subrecipient, has agreed in principle to agreements with Zayo Bandwidth and Dukenet Communications for fibers in the route. The negotiated agreements are with ERC for more fibers along the route than originally planned in a different location and with Haywood County Government. | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and sumitted to the NTIA for approval and those sites are expected to supply those services. FRC is currently negotiating for a long term IRU sale of Dark Fiber assets along specific portions of the planned ring build. The potential customer is a company known as Zayo, LLC, a Colorado company. Pricing for the fiber has been offered at a one time IRU fee of $1.8M, and annual maintenance fees of $70.19K, or $5,848 per month. The deal has not yet closed. | FRC (Primary Business Contact Mike Baldwin, 1500 Hampton St., Columbia SC., 803-771-7476) has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once construction is complete. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC would be focused on the education, government, and public health sectors. | 2 | 0 | 2 | 0 | N/A | Initial projection in baseline was wrong due to planned swaps being removed from project. | 0 | N/A | 497 | 0 | 497 | 0 | We are below projections due to a delay in starting construction. We forecast lighting two priority spans to Asheville, NC and Greenville, NC in the third quarter as construction efforts to those areas are completed and that activity will enable greatly improved access to a large number of CAI's. Numbers presented here were reported in our last quarterly report. There was no new activity this quarter. | N/A | We are below projections due to a delay in starting construction. We forecast lighting two priority spans to Asheville, NC and Greenville, NC in the third quarter as construction efforts to those areas are completed and that activity will enable greatly improved access to a large number of CAI's. Numbers presented here were reported in our last quarterly report. There was no new activity this quarter. | 10Gbps shared backbone is available to all of these subscribers with more bandwidth available to be provisioned as required. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure. | FALSE | N/A | We anticipate being very close to having all construction completed or close to complete by the end of the September reporting quarter. We additionally expect to begin operating newly constructed fiber paths to Asheville and Greenville and upgrading service to those regions of North Carolina with 10G of IP internet service, as well as the capability to have lambda based connectivity out of those regions. | MCNC | Issues related to execution of the project itself are now limited to construction activities themselves. Needs from NTIA are starting to lessen as we get more closure around how to handle sell and swap of fibers within the project. During the next quarter we expect to bring opportunities to the NTIA on how to leverage our savings we have realized within the project to deploy more miles related to the award. | Adverse weather could continue to be something beyond our control that could impact us. We still need to start and complete a 2400 foot river bore in eastern NC that could be challenging. However, we remain confident the crew that will do this work will be successful given they completed one much more difficult in the western portion of our state.
NT10BIX5570011 | 2011 | Q3 | Q3 - 2011 | While we had forecasted on the last quarterly report completion of all construction activities of the 413 engineered conduit miles during this quarter, we encountered difficulty in doing so due to hitting the toughest terrain in the project in the mountains. By the end of the quarter 395 miles (95.7%) of conduit construction were complete, with placement of 205 miles of fiber within those 395 miles of conduit completed. The single most significant milestone for the quarter was the successful deployment of equipment on a 52 mile segment between Rocky Mount and Greenville that provided an upgraded 10Gbps IP path for a portion of the eastern part of North Carolina. The bulk of activity within the project now centers around project oversight and preparing for equipment deployment. For the October -December quarter we anticipate completing all construction activities and placing several more spans of the recently completed construction in to service. Our goal is to complete all portions of the project as awarded by December, but in reality it may slip to January 2012. The total project is currently about one year ahead of schedule and projected to be favorable to budget by 12.5% based on delivery of project as awarded. | 205 | 291 | 197 | 0 | 205 | 0 | 0 | 1048 | In total, we have placed 205 miles of fiber and 395 miles of conduit. While we are slightly behind the number forecasted in the baseline (215.5 miles) due to the delay in the start of construction, we will no doubt be caught up by end of the Y2Q4 reporting period. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. As it relates to leasing (or in our case acquisition under IRU), we have now fully executed all that were planned or approved by NTIA once our project started. The total of 291 is from 197 from ERC and FRC routes communicated in application, 61 from Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. This number will always be less than the final projection of 420. The higher number reported in baseline are miles that now reside in the upgraded section below. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in quarterly reporting. | NA | In total, we have placed 205 miles of fiber and 395 miles of conduit. While we are slightly behind the number forecasted in the baseline (215.5 miles) due to the delay in the start of construction, we will no doubt be caught up by end of the Y2Q4 reporting period. We are pushing contractors for completion by end of calendar 2011, and certainly no later than Y3Q1. | NA | NA | We had projected 160 in our baseline and are well above that. This number is representative of all splice enclosures and hand holds on our new builds as well as acquired fibers that have agreements allowing for interconnect at existing access points like hand holds and splice points. | 2 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. FRC, our subrecipient, has been discussing agreements with Zayo Bandwidth and Dukenet Communications for fibers in the route but contracts are not signed. They are now also talking to Pangea Internet about a possible IRU acquisition. MCNC is exploring additional agreements with ERC for more fibers they would IRU along the BTOP route than originally planned and with Haywood County Government for a dark fiber lease respectively. | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and sumitted to the NTIA for approval and those sites are expected to supply those services. FRC is currently negotiating for a long term IRU sale of Dark Fiber assets along specific portions of the planned ring build. The potential customer is a company known as Zayo, LLC, a Colorado company. Pricing for the fiber has been offered at a one time IRU fee of $1.8M, and annual maintenance fees of $70.19K, or $5,848 per month. The deal has not yet closed. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once construction is complete. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC would be focused on the education, government, and public health sectors. | 2 | 0 | 2 | 0 | We inadvertently reported 4 in the last quarter. While agreements between FRC and Dukenet, and FRC and Zayo are being negotiated, they are not formally signed as we discovered in retrieving data this quarter. | We have found that most providers we've talked to are interested in dark services and not lit wholesale capacity, therefore our projection here was wrong. We currently do not forecast any providers receiving improved access beyond ourselves and FRC. | We inadvertently reported 4 in the last quarter. While agreements between FRC and Dukenet, and FRC and Zayo are being negotiated, they are not formally signed as we discovered in preparing data this quarter. | NA | 1136 | 0 | 1136 | 1136 | We believe our projections in our application may be wrong due to misinterpretation of the guidance. What we report here are CAI's that were already directly connected to the North Carolina Research and Education Network (NCREN) backbone that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. Our projections were based on those types of institutions located in those counties our fiber route passes through, but may not actually be a part of NCREN today. | NA | We believe our projections in our application may be wrong due to misinterpretation of the guidance. What we report here are CAI's that were already directly connected to the NCREN backbone that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. Our projections were based on those types of institutions located in those counties our fiber route passes through, but may not actually be a part of NCREN today. | 10Gbps shared backbone is available to all of these subscribers with more bandwidth available to be provisioned as required. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure, and to portions of the central core (defined as Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | FALSE | NA | We believe all conduit construction will be complete and our goal is for the remaining fiber to be complete as well. We anticipate having placed in to service all fiber in the eastern portion of the network, as well as much of the fiber on the western portion. By the end of the quarter we project cumulative totals of 413 new network miles deployed, 291 miles leased, 1136 total CAI's receiving improved access (zero directly connected as the original project didn't forecast this), and two providers with signed agreements. | MCNC | Challenging terrain is the primary concern of the past quarter and what remains to be built. Our contractor in the west has encountered extremely rocky terrain and is having to bring in special directional boring equipment (rock hammers) to get through it. It slows the construction down relative to the pace we were achieving. | The remaining areas of construction are the most difficult in the entire project. Adverse weather could continue to be something beyond our control that could impact us.
NT10BIX5570011 | 2011 | Q4 | Q4 - 2011 | We closed in on completion of construction related to the project during the quarter. The remaining portions of the build continue to be challenging, but there were milestones. We placed in to operation segments built between Mocksville and Asheville, representing nearly 60 miles of new builds to complement fibers over nearly 100 miles that MCNC had IRU rights to operate on. This enabled the North Carolina Research and Education Network operated by MCNC to upgrade connectivity in to the Hickory and Asheville points of presence to 10G. Construction efforts continued and at the end of the quarter we had an aggregate of about 2 miles of conduit left to place to finish all of those efforts. Construction during the quarter did finalize the bore of the Trent River in New Bern which was one of the last major hurdles in eastern North Carolina. In total nearly 410 miles of conduit have been placed, with 357 miles of fiber placed within that conduit. Anticipating more fiber completion along other defined segments, we have now started the deployments of the remaining equipment so that it is in place when the fiber is completed and spliced. The project remains ahead of schedule and we project that all components of the project (fiber and equipment deployment) will complete by the end of the March reporting quarter. | 357 | 291 | 197 | 0 | 357 | 0 | 0 | 1062 | By the end of this reporting cycle we had begun to catch up with fiber placement relative to conduit placement as had been forecasted in previous quarters and are now ahead of baseline. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. As it relates to leasing (or in our case acquisition under IRU), we have now fully executed all that were planned or approved by NTIA once our project started. The total of 291 is from 197 from ERC and FRC routes communicated in application, 61 from Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. This number will always be less than the final projection of 420, but is now complete at 291. The higher number reported in baseline are miles that now reside in the upgraded section below. The 197 miles referenced in this paragraph that are attributable to FRC and ERC acquisitions are different from the 197 referenced in the existing network miles upgraded section below. | These miles represent fiber that MCNC already had the rights to via IRU from a BTI Telecom acquisition in 2007 and MCNC put in to the project as in-kind match. BTOP funded the equipment used to light this fiber. Baseline always showed 0 throughout the project due to misunderstanding of guidance and were moved from the "network miles leased" area here in quarterly reporting. | NA | In total we have placed 357 miles of fiber and 410 miles of conduit, and so now are ahead of our baseline of 295 miles for this quarter. | NA | NA | We are ahead of baseline as this number is representative of all splice enclosures and hand holds on the route, which enable interconnect points. | 2 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. We also signed an agreement with Haywood County Government on a 5 year lease of fibers in the western portion of the project over a short 2 mile segment of the route. Because this is not a wholesaler we do not include it in the numbers above. FRC, our subrecipient, has been discussing agreements with Zayo Bandwidth and Dukenet Communications for fibers in the route but contracts are not signed. They are now also talking to Pangea Internet about a possible IRU acquisition. Of these three possible agreements, the Dukenet Communications agreement is forecasted for no later than June of 2012 by FRC. The Zayo discussions have stalled on the Zayo side and may not materialize. The Pangea efforts will likely not come to fruition before end of calendar 2012 if they occur. MCNC is exploring additional agreements with ERC for more fibers they would IRU along the BTOP route than originally planned that may officially close by June of 2012. | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and submitted to the NTIA for approval and those sites are expected to supply those services. FRC is planning response to a number of RFP's related to wireless service but pricing plans are not yet available as the overall proposal contains BTOP and non-BTOP related fibers. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber once construction is complete. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC would be focused on the education, government, and public health sectors. | 2 | 0 | 2 | 0 | Baseline is 1, so no variance. Discussions continue between FRC, Zayo, and Dukenet, but nothing formally signed. | We have found that most providers we've talked to are interested in dark services and not lit wholesale, so our projections here have been wrong. | Interest from existing providers has been tepid, and interest from new providers is not yet there. Our marketing partner in the round 2 project is starting to gain some traction related to that project, which is extending further interest in to the round 1 footprint, so we hope to see more activity in this arena over the next year. | NA | 1279 | 0 | 1279 | 1279 | We believe our projections in our application may be wrong due to misinterpretation of the guidance. What we report here are CAI's that were already directly connected to the North Carolina Research and Education Network (NCREN) backbone that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. Our projections were based on those types of institutions located in those counties our fiber route passes through, but some of which may not actually be a part of NCREN today. The final number we anticipate receiving improved access are 1890. | NA | We believe our projections in our application may be wrong due to misinterpretation of the guidance. What we report here are CAI's that were already directly connected to the North Carolina Research and Education Network (NCREN) backbone that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. Our projections were based on those types of institutions located in those counties our fiber route passes through, but may not actually be a part of NCREN today. | None of the improved access is due to directly connected CAI's, but rather an improved middle mile infrastructure. That infrastructure has capability for 100G connectivity. We anticipate the final number of subscribers benefitting and served from the new infrastructure to be 1890. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | FALSE | NA | We expect to complete the project as awarded with all fiber placed and equipment deployed. | MCNC | Similar to what was reported in the last quarter, the major challenge remains getting through rocky terrain encountered in western North Carolina. While less than 2 miles remains to be built, it is under challenging creek crossings in granite formations that simply take time to complete. We only have about 10 of these locations remaining and expect all fiber to be complete and placed by February. | The only challenge that could potentially keep us from completing as described would be a delay in these final few placements of conduit not occurring. Weather and geography could factor in to that. While the risk for this occurring over a three month period is low, it is a risk nonetheless. Additionally if for whatever reason our fiber that has been ordered was to be damaged during placement by the contractors, replacement reels could be delayed in being received due to a backlog of fiber by our contractor. We can mitigate that if needed, though, by having them manufacture from our allocated allotment of glass for the round 2 project if that were to occur.
NT10BIX5570011 | 2012 | Q1 | Q1 - 2012 | Construction efforts for BTOP Round 1 as originally funded are complete and all equipment related to the project has been deployed and placed in to operation. There is now a DWDM core infrastructure serving the North Carolina Research and Education Network in the southeastern part of North Carolina along the Rocky Mount/Morehead City/Wilmington corridor, and in the western part of North Carolina between Mocksville/Asheville/Cullowhee/Charlotte corridor. The first service deployed on the system is a 10Gbps ring interconnecting all points of presence in those regions to the NCREN IP backbone. | 414 | 291 | 197 | 0 | 414 | 0 | 0 | 1062 | The final mileage represents the final constructed miles in the project after final engineering was complete and construction performed. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. As it relates to leasing (or in our case acquisition under Indefeasible Right to Use-IRU), we have now fully executed all that were planned or approved by NTIA once our project started. The total of 291 miles is made up of 197 from ERC and FRC routes communicated in application, 61 from Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. This number will always be less than the final projection of 420. The higher number reported in baseline are miles that now reside in the upgraded section below. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter | N/A | The final mileage represents the final constructed miles in the project after final engineering was complete and construction performed. | N/A | N/A | We are ahead of baseline as this number is representative of all splice enclosures and hand holds on the route, which enable interconnect points. | 2 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. We also signed an agreement with Haywood County Government on a 5 year lease of fibers in the western portion of the project over a short 2 mile segment of the route. Because this is not a wholesaler we do not include in the numbers above. FRC, our subrecipient, has been discussing agreements with Zayo Bandwidth and Dukenet Communications for fibers in the route but contracts are not signed. They are now also talking to Pangea Internet about a possible IRU acquisition. Of these three possible agreements, the Dukenet agreement is forecasted for close in the June 2012 quarter. The Zayo efforts did not materialize. The Pangea opportunity may close the last half of 2012. MCNC is exploring additional agreements with ERC for more fibers they would IRU along the BTOP route than originally planned that may officially close in June of 2012. | MCNC is not providing wholesale services. The Agreements noted above are part of the IRU swaps that were negotiated and submitted to the NTIA for approval and those sites are expected to supply those services. FRC is planning response to a number of RFP's related to wireless service but pricing plans are not yet available as the overall proposal contains BTOP and non-BTOP related fibers. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. | 2 | 0 | 2 | 0 | Discussions continue between FRC, Dukenet, and Pangea, but nothing formally signed between these. We are lower to baseline by one but expect when one of these signs later this year we will recover. | We have discovered that most providers we've talked to are interested in dark services and not lit wholesale services so our projection here has been inaccurate. | Discussions continue between FRC, Dukenet, and Pangea, but nothing formally signed between these. We are lower to baseline by one but expect when one of these signs later this year we will recover. We have discovered that some interest is there, but didn't start becoming more apparent until route was close to completion. Some interest has also been tied to the round 2 footprint as a complimentary route to help entice to the round 1 routes. | Speeds and tiers available are anywhere from 100Mbps to 10Gbps. To date, no wholesalers have signed on for lit services. | 1870 | 0 | 1870 | 0 | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with NCREN today. Based on the clarifications from last quarter, what we report here are CAI's that were already connected to the North Carolina Research and Education Network (NCREN) backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. This clarification means that some site names in lists previously uploaded on prior quarterly reports may need to be removed and replaced to correlate with the final 1870 site names reported here and within the annual report which is accurate. The total number of CAI's reported of 1870 matches the final count of on-net CAI's directly benefitting from the new infrastructure. | N/A | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with NCREN today. Based on the clarifications from last quarter, what we report here are CAI's that were already connected to the North Carolina Research and Education Network (NCREN) backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. This clarification means that some site names in lists previously uploaded on prior quarterly reports may need to be removed and replaced to correlate with the final 1870 site names reported here and within the annual report which is accurate. The total number of CAI's reported of 1870 matches the final count of on-net CAI's directly benefitting from the new infrastructure. | None of the improved access is due to directly connected CAI's but rather an improved middle mile infrastructure. That infrastructure has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | FALSE | N/A | The project as funded is complete. During this quarter, Q12012, we have submitted to the NTIA opportunities on how to leverage savings that have been realized during execution of the project. If approved, an additional 20 CAI's will be added to the project along with 23 new leased miles and 31 newly constructed miles. If approved during Q22012 we would anticipate starting the engineering and contract negotiations of these miles, but would not anticipate deployment during the quarter of any of the miles or CAI's. | MCNC | The final 1000's of feet of the project proved to be challenging due to the terrain of the areas they were in. These challenges spanned many quarters and were focused specifically on difficult creek and river crossings in the western footprint of the route due to rock, in many cases blue granite. At this point in the project, all issues rested squarely with us in implementation because we were well beyond permitting, contracting, and other issues. It was just a matter of executing which we have now done. | We will need quick turnaround from our engineering firm on the design of the new routes if NTIA gives clearance to proceed with the additional builds related to the project.
NT10BIX5570011 | 2012 | Q2 | Q2 - 2012 | MCNC had previously reported completion of the originally approved project in the March reporting quarter. During the first half of this quarter MCNC worked with the NTIA on developing a plan to utilize savings realized during execution of the project for deploying 54 more additional miles of fiber to serve additional CAI's in the previously approved proposed service funding area, as well as an upgrade to the North Carolina Research and Education core backbone to 100Gbps (gigabits per second). Formal approval of these requests was provided on May 22nd, and work began on all required engineering efforts shortly thereafter. For the balance of the quarter, all activities on the project related to network design, permitting, and the start of equipment ordering toward completion of this effort. No actual construction or execution of the indefeasible rights to use (IRU's) on the new 54 miles has commenced yet, but it is expected that those efforts will start in August. | 414 | 291 | 197 | 0 | 414 | 0 | 0 | 1062 | The 414 miles represented here matches the amount of mileage reported last quarter. Baseline would have projected 467.1 miles for this quarter, but included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began. The 414 miles represented here are the final constructed miles in the project after final engineering and builds were complete, and do not represent any of the additional miles approved by the NTIA as they are not yet under construction per the savings request that was submitted and approved. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. As it relates to leasing (or in our case acquisition under Indefeasible Right to Use-IRU), we have now fully executed all that were planned or approved by NTIA for the original project. The total of 291 miles is made up of 197 from ERC and FRC routes communicated in application, 61 from Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. This number will always be less than the final projection of 420. The higher number reported in baseline are miles that now reside in the upgraded section below. None of the additional miles approved during this quarter are shown in the 291 miles as those efforts were not fully complete at the end of the quarter. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter. | N/A | This mileage represents the final constructed miles of the project as initially funded. Over the next two quarters the amount will increase due to the newly approved CAI connections. | N/A | N/A | We are ahead of baseline as this number is representative of all splice enclosures and hand holds on the route, which enable interconnect points. This number will further increase over the next two reporting quarters as we finalize the builds associated with the newly approved miles to the project. | 2 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. We also signed an agreement with Haywood County Government on a 5 year lease of fibers in the western portion of the project over a short 2 mile segment of the route. Because this is not a wholesaler we do not include in the numbers above. FRC, our subrecipient, has now signed an agreement with Pangea for access to fibers as of 6-5-2012. They have also been discussing agreements with Dukenet Communications for fibers in the route but final contracts are not signed. Terms are agreed to but the delay at this point is now related to colocation availability on the route by FRC to Dukenet. It is anticipated these issues will be worked through. MCNC is exploring additional agreements with ERC for more fibers they would IRU along the BTOP route than originally planned. Contract was near signing at the end of the June quarter. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | Both MCNC, as the prime recipient, and FRC, as a sub-recipient, will operate their respective fibers (48 each) in the sheath. MCNC has the ultimate responsibility for maintenance of the sheath as the cable owner, but has contracted with FRC to provide this maintenance (locate services, break/fix, etc.) on an annual basis under an operational contract. MCNC will operate their strands in the sheath to provide service to the public sector, while FRC will operate their strands for commercial based opportunities (service to wholesalers, private sector enterprise, etc.) | 2 | 0 | 2 | 0 | Discussions continue between FRC and Dukenet, but nothing is formally signed between these as of yet. While lower to baseline, we do expect further agreements to materialize now that the route is completed and discussions to leverage portions of both project footprints make some areas more viable. | We have discovered that most providers we've talked to are interested in dark services and not lit wholesale services so our projection here has been inaccurate to date. | Discussions continue between FRC, Dukenet, and Pangea, but nothing formally signed between these. We are lower to baseline by one but expect when one of these signs later this year we will recover. We have discovered that some interest is there, but didn't start becoming more apparent until route was close to completion. Some interest has also been tied to the round 2 footprint as a complimentary route to help entice to the round 1 routes. | To date, no wholesalers have signed on to provide wholesale lit services. Once this occurs, we would anticipate a provider that can provide services from 10M to 100G as required. | 1870 | 0 | 1870 | 0 | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. The newly funded direct fiber connections to the 20 additional CAI's are not yet included in this count as the construction has not yet commenced. | Now that the NTIA has approved 54 miles of additional builds or acquisition there will be 20 more CAI's receiving direct fiber access. These efforts will commence over the next quarter. | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | None of the improved access is due to directly connected CAI's but rather an improved middle mile infrastructure. That infrastructure has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | FALSE | N/A | We will be full force in our efforts to complete the newly funded 54 miles of fiber and connections to the 20 CAI's. We would anticipate closing on all the IRU's related to the 23 leased miles to be acquired, and potentially 1/2 of the 31 miles to be constructed. Additionally final engineering with Cisco will occur during this quarter on the 100Gbps backbone upgrade such that it will be in place by December of this year. We do not project any further additional signed agreements for the next quarter although a few negotiations are ongoing. | MCNC | Related to this project, there were no major challenges or obstacles. The initial funded work was largely completed except for close out activities with the contractors on minor ground restorations and corrections. Most efforts in the first half of the quarter centered around discussions with NTIA on how to leverage those savings found within the project to which there were no major challenges other than identifying and working through the process to get those approved. Once the approval was received, it did set in motion, on a smaller scale, implementing variables in the project that are now under tight time lines. At this point there is no reason for concern in being able to complete the additional funded builds. | Obstacles remaining for completion at this point would be timely delivery of materials and equipment associated with those things that we bought late in this quarter to facilitate the builds and deployment of equipment. We're confident in our ability to work with our providers such that this doesn't happen.
NT10BIX5570011 | 2012 | Q3 | Q3 - 2012 | MCNC continued working toward completion of the additional project elements approved by NTIA during the prior quarter. We executed on IRU agreements with providers for 23 miles that will serve 9 CAI's. Construction on the remaining 30 miles as part of the savings request with nearly 1/2 complete from a conduit perspective during the quarter, but no fiber was placed. Ordering of equipment related to the 100G core upgrade request commenced with much of the equipment starting to arrive by quarter end for deployment during the rest of the calendar 2012 year. | 414 | 314 | 197 | 0 | 414 | 0 | 0 | 1100 | The 414 miles represented here matches the amount of mileage reported last quarter. Baseline would have projected 467.1 miles for this quarter, but included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began. The 414 miles represented here are the final constructed miles in the originally approved project after final engineering and builds were complete. The additional routes approved by the NTIA last quarter represent 30 additional miles, but none of that fiber has yet been completed and thus is not shown yet. 13.5 miles of the conduit has been completed. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. The total of 314 miles is made up of 197 from ERC and FRC routes communicated in the original application, 61 from the Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. The additional 23 miles as approved in the savings request have now been added for a total of 314 miles. This number will always be less than the final projection of 420 due to misunderstanding of accounting of these miles at baseline completion. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter. | N/A | This mileage represents the final constructed miles of the project as initially funded. Over the next two quarters the amount will increase due to the newly approved CAI connections. | N/A | N/A | We are ahead of baseline as this number is representative of all splice enclosures and hand holds on the route, which enable interconnect points. This number will settle in around 1125 when all builds are fully complete. | 2 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. We also signed an agreement with Haywood County Government on a 5 year lease of fibers in the western portion of the project over a short 2 mile segment of the route. Because this is not a wholesaler we do not include in the numbers above. FRC, our subrecipient, has now signed an agreement with Pangea for access to fibers as reported in the last quarter. They have also been discussing agreements with Dukenet Communications for fibers in the route but final contracts are not signed. Terms are agreed to but the delay at this point is now related to collocation availability on the route by FRC to Dukenet. It is anticipated these issues will be worked through. MCNC is exploring additional agreements with ERC for more fibers they would IRU along the BTOP route than originally planned. Contract is expected to sign in October. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. | 2 | 1 | 2 | 0 | Discussions continue between FRC and Dukenet, but nothing is formally signed between these as of yet. While lower to baseline, we do expect further agreements to materialize now that the route is completed and discussions to leverage portions of both project footprints make some areas more viable. | In advance of FRC lighting portions of the route on their own for the fibers they acquired in the route, they have contracted with MCNC for the next year to provide a 10Gbps lambda between New Bern and Wilmington on the MCNC network. | Discussions continue between FRC and Dukenet but nothing formally signed between these entities. We are lower to baseline but have seen more interest due to the round 2 network being marketed with the round 1 network now. We have discovered that some interest is there, but didn't start becoming more apparent until route was close to completion. | To date, no wholesalers have signed on to provide wholesale lit services. Once this occurs, we would anticipate a provider that can provide services from 10M to 100G as required. | 1870 | 0 | 1870 | 0 | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. The newly funded direct fiber connections to the 20 additional CAI's are not yet included in this count as the construction has not yet commenced or IRU's fully accepted.. | Now that the NTIA has approved 54 miles of additional builds or acquisition there will be 20 more CAI's receiving direct fiber access. These efforts started this past quarter. | As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | None of the improved access is due to directly connected CAI's but rather an improved middle mile infrastructure. That infrastructure has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | TRUE | We have now implemented our mapping software that allows us to have a better ability to track where our fiber assets are in the field. As it relates to providing access or specific services on the network, that has not changed. | We anticipate completing the balance of the round 1 project additional requests that were approved by the NTIA in the June reporting quarter. This includes the addition of 54 miles and full equipment deployment associated with those 20 CAI's. | MCNC | No significant challenges in continuing on the execution of the project were experienced. | We do not anticipate any challenges in completing the project as approved.
NT10BIX5570011 | 2012 | Q4 | Q4 - 2012 | By the end of the quarter, MCNC had finished the project as originally funded as well as the approved project modifications from March 2012. The remaining 30 miles of build for the project were completed and fiber to 13 CAI's completed bringing the cumulative totals to date are 444 miles of new fiber and 1883 CAI's with improved or new connectivity. The equipment associated with the 100G core upgrade of the North Carolina Research and Education Network backbone was in place and ready to have traffic migrated to it in over the course of the next several months as network maintenance availability allowed. | 444 | 314 | 197 | 0 | 444 | 0 | 0 | 1125 | The 444 miles represented here matches the original approved build and additional miles added during the project. Initial baseline established would have projected 467.1 miles for this quarter, but the forecasted amount included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began and means this number will always track below baseline. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. The total of 314 miles reported here is made up of 197 from ERC and FRC routes communicated in the original application, 61 from the Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. The additional 23 miles as approved in the savings request have now been added for a total of 314 miles. This number will always be less than the final projection of 420 due to misunderstanding of accounting of these miles at baseline completion. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP then funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter which is creating the variance to baseline. | N/A | The 444 miles represented here matches the original approved build and additional miles approved during the project. | N/A | N/A | This final number is higher to baseline due to the additional approved builds during the project and our estimate for number of required handholds designed during engineering being low initially. | 4 | 5 | 80 | MCNC has signed agreements for an approved swap with ERC and FRC as part of the project that was defined at application. We also signed an agreement with Haywood County Government on a 5 year lease of fibers in the western portion of the project over a short 2 mile segment of the route. Because this is not a wholesaler we do not include in the numbers above. FRC, our subrecipient, has now signed an agreement with Morris Broadband in Western North Carolina for 37 miles on a 20 year IRU. A previous agreement with Pangea was closed and executed. They have also been discussing agreements with Dukenet Communications for fibers in the route but final contracts are not signed. Terms are agreed to but the delay at this point is now related to collocation availability on the route by FRC to Dukenet. When proposed colocation facilities coming online that MCNC has worked with NTIA for approval on, we're confident this agreement would execute in the next 6-9 months. In addition there are several other agreements being negotiated with wholesale and residential carriers interested in expanding in to these markets. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. FRC Contact Info: Mike Baldwin Senior Counsel, Business and Legal Affairs 1500 Hampton Street, Columbia SC 29201 (803)-726-4053 MCNC Contact Info: Tommy Jacobson COO 3021 E. Cornwallis Road Research Triangle Park, NC 27709 | 4 | 1 | 4 | 0 | New agreement with Morris Broadband signed with FRC. Discussions continue between FRC and Dukenet, but nothing is formally signed between these as of yet. We do expect further agreements to materialize as the round 1 and round 2 footprints are being marketed together. There are two such agreements for access to both routes being contemplated. | In advance of FRC lighting portions of the route on their own for the fibers they acquired in the route, they have contracted with MCNC for the next year to provide a 10Gbps lambda between New Bern and Wilmington on the MCNC network. | Discussions continue between FRC and Dukenet but nothing formally signed between these entities. We have seen more interest due to the round 2 network being marketed with the round 1 network now. We have discovered that some interest is there, but didn't start becoming more apparent until route was close to completion. There are two such agreements being contemplated. | To date, no wholesalers have begun operating fibers that they have acquired. Once this occurs, we would anticipate a range of services from 10M to 10G as required. | 1866 | 19 | 1847 | 0 | We are now reporting 1866 CAI's. This is 4 less than was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | These 19 sites reported represent locations approved for new builds during the project that have now been completed as of this reporting quarter. | We are now reporting 1847 CAI's. This is less than what was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities | Most of our CAI's have improved access due to being on the improved middle mile infrastructure. That infrastructure now has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. For CAI's that have had new fiber constructed to their locations they have capability with the equipment deployed for services up to 10Gbps depending on what service level they choose. As their capabilities grow beyond the equipment deployed, we could upgrade that equipment through operational funds and improve their connectivity up to 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. | FALSE | N/A | We will work with NTIA to finalize those elements of additional builds and equipment deployments related to the approved huts and 100G Research1 locations. We anticipate by the end of the next quarter to have 6 signed agreements for new access. | MCNC | No significant challenges in continuing on the execution of the project were experienced. | We do not anticipate any challenges based on the remaining work left to perform. Quick review and consideration of the environmental package related to the hut facilities being proposed is the only element requiring assistance and guidance by BTOP.
NT10BIX5570011 | 2013 | Q1 | Q1 - 2013 | MCNC has previously reported that the original project, as well as the project modifications approved in spring of 2012, are complete. The associated miles in the project are 444 miles of new fiber and 1866 CAI's with improved or new connectivity. During the quarter MCNC finalized additional equipment engineering associated with the 100G upgrades for R1 universities in the state that was approved in late December, as well as preliminary work with NTIA on the approval of three additional telecommunication hut sites along the fiber network. Efforts of both were nearing completion by the end of the quarter. | 444 | 314 | 197 | 0 | 444 | 0 | 0 | 1125 | The 444 miles represented here matches the original approved build and additional miles added during the project. Initial baseline established would have projected 467.1 miles for this quarter, but the forecasted amount included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began and means this number will always track below baseline. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. The total of 314 miles reported here is made up of 197 from ERC and FRC routes communicated in the original application, 61 from the Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. The additional 23 miles as approved in the savings request have now been added for a total of 314 miles. This number will always be less than the final projection of 420 due to misunderstanding of accounting of these miles at baseline completion. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP then funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter which is creating the variance to baseline. | N/A | The 444 miles represented here matches the original approved build and additional miles approved during the project. | N/A | N/A | This final number is higher to baseline due to the additional approved builds during the project and our estimate for number of required handholds designed during engineering being low initially. | 7 | 4 | 70 | Signed agreements completed to date are as follows: 1. ERC (dark fiber) through MCNC 2. FRC (dark fiber) through MCNC 3. FRC (lit service) through MCNC 4. Earthlink (dark fiber) through MCNC 5. Verizon Wireless (lit service) through FRC (subrecipient) 6. Morris Broadband (dark fiber) through FRC (subrecipient) 7. Pangea Internet (dark fiber) through FRC (subrecipient) Conversations with Dukenet continue for round 1 routes, but have now expanded to include more of the footprint involved with the round 2 project. While nothing has formally closed, we remain optimistic that an agreement will come to fruition. We have been involved with discussions with RST Communications out of Shelby, NC as well about fibers along the round 1 footprint. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. FRC Contact Info: Mike Baldwin Senior Counsel, Business and Legal Affairs 1500 Hampton Street, Columbia SC 29201 (803)-726-4053 MCNC Contact Info: Tommy Jacobson COO 3021 E. Cornwallis Road Research Triangle Park, NC 27709 | 1 | 1 | 5 | 2 | FRC is providing lit service under a master contract with Verizon Wireless to about 10 wireless towers in the western portion of the network. | In advance of FRC lighting portions of the route on their own for the fibers they acquired in the route, they have contracted with MCNC for the next year to provide a 10Gbps lambda between New Bern and Wilmington on the MCNC network. Agreements for service have been limited due to most interest being in dark fiber. | Dark fiber agreements communicated in previous reports for the arrangements with FRC (as part of the subrecipient agreement), ERC, and Pangea Internet. As noted above additional agreements with Earthlink and Morris Broadband completed during this quarter on portions of the new construction. Discussions continue between FRC and Dukenet but nothing formally signed between these entities. We have seen more interest due to the round 2 network being marketed with the round 1 network now. We have discovered that some interest is there, but didn't start becoming more apparent until route was close to completion. There are two such agreements being contemplated. | We do believe that Earthlink when they bought their fiber immediately placed it in to service, however we have no idea what speeds they are operating at. We would anticipate it has a range of up to 100G. Other wholesalers that have purchased we believe have not yet deployed but are offering speeds in the range of 10M to 100G. The Verizon Wireless lit services identified above operate at 100M and the service MCNC is providing to FRC operates at 10G. 100M: 10 subscribers 10G: 1 subscriber | 1866 | 19 | 1847 | 0 | We are now reporting 1866 CAI's. This is 4 less than was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | These 19 sites reported represent locations approved for new builds during the project that have now been completed as of this reporting quarter. | We are now reporting 1847 CAI's. This is less than what was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | Most of our CAI's have improved access due to being on the improved middle mile infrastructure. That infrastructure now has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. For CAI's that have had new fiber constructed to their locations they have capability with the equipment deployed for services up to 10Gbps depending on what service level they choose. As their capabilities grow beyond the equipment deployed, we could upgrade that equipment through operational funds and improve their connectivity up to 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. In addition, due to funding from the NTIA, the entire NCREN core operates at 100Gbps. | FALSE | N/A | 100G equipment approved by the NTIA for the R1 CAI's in our network will be ordered and deployed. We additionally expect to finalize environmental and engineering requirements of the three additional telecommunication huts approved by NTIA. Continued negotiations are ongoing with four additional providers regarding access to dark fiber. At this point we are unable to place specific confidence on any of them, but we anticipate potentially closing one additional agreement bringing our total agreements to 8 with 6 dark fiber agreements. | MCNC | No significant challenges in continuing on the execution of the project were experienced. | We do not anticipate any challenges based on the remaining work to be performed.
NT10BIX5570011 | 2013 | Q2 | Q2 - 2013 | MCNC has previously reported that the original project, as well as the project modifications approved in spring of 2012, are complete. The associated miles in the project are 444 miles of newly constructed fiber, 314 miles of new network miles leased, 197 miles of upgraded fiber, and 1866 CAI's with improved or new connectivity. During the quarter MCNC finalized the purchase of the 100G upgrades for the R1 universities that was approved in December of 2012, and all of this equipment was received during the quarter but not yet deployed. Final engineering efforts were completed for the three additional hut sites that were approved as additions to the project in December of 2012. At the end of the quarter these facilities had been ordered, engineering completed, but project work at the site had not yet commenced. All other aspects of the project as originally approved were complete. | 444 | 314 | 197 | 0 | 444 | 0 | 0 | 1125 | The 444 miles represented here matches the original approved build and additional miles added during the project. Initial baseline established would have projected 467.1 miles for this quarter, but the forecasted amount included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began and means this number will always track below baseline. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. The total of 314 miles reported here is made up of 197 from ERC and FRC routes communicated in the original application, 61 from the Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. The additional 23 miles as approved in the savings request have now been added for a total of 314 miles. This number will always be less than the final projection of 420 due to misunderstanding of accounting of these miles at baseline completion. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP then funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter which is creating the variance to baseline. | N/A | The 444 miles represented here matches the original approved build and additional miles approved during the project. | N/A | N/A | This final number is higher to baseline due to the additional approved builds during the project and our estimate for number of required handholds designed during engineering being low initially. | 8 | 4 | 70 | Signed agreements completed to date are as follows: 1. ERC (dark fiber) through MCNC 2. FRC (dark fiber) through MCNC 3. FRC (lit service) through MCNC 4. Earthlink (dark fiber) through MCNC 5. RST Communications (dark fiber) through MCNC 6. Verizon Wireless (lit service) through FRC (subrecipient) 7. Morris Broadband (dark fiber) through FRC (subrecipient) 8. Pangea Internet (dark fiber) through FRC (subrecipient) Conversations with Dukenet continue for round 1 routes but have had to go to their board of directors for approval. Conversations with Balsamwest regarding fibers along a portion of the route are ongoing, as well as additional purchases from RST and Earthlink. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. FRC Contact Info: Mike Baldwin Senior Counsel, Business and Legal Affairs 1500 Hampton Street, Columbia SC 29201 (803)-726-4053 MCNC Contact Info: Tommy Jacobson COO 3021 E. Cornwallis Road Research Triangle Park, NC 27709 | 1 | 1 | 6 | 2 | FRC is providing lit service under a master contract with Verizon Wireless to 10 wireless towers in the western portion of the network. | In advance of FRC lighting portions of the route on their own for the fibers they acquired in the route, they have contracted with MCNC for the next year to provide a 10Gbps lambda between New Bern and Wilmington on the MCNC network. | Dark fiber agreements communicated in previous reports for the arrangements with FRC (as part of the subrecipient agreement), ERC, Pangea Internet, Morris Broadband, and Earthlink. As noted above, an additional agreement was completed with RST Communications was completed during the quarter. Discussions continue with Dukenet, Balsamwest, and Earthlink (additional purchase) for portions of the constructed network. | Earthlink and RST are the first two providers that we believe will be providing wholesale and residential services in the areas of their purchases. However, we do not have direct visibility to what those offerings are or how they have provisioned the dark fibers they have received. Within the MCNC/FRC fibers, the service MCNC is providing is operating at 10G and the services that FRC is providing is operating at 100M. 100M: 10 subscribers 10G: 1 subscriber | 1866 | 19 | 1847 | 0 | We are serving 1866 CAI's. This is 4 less than was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | These 19 sites reported represent locations approved for new builds during the project. | We are now reporting 1847 CAI's. This is less than what was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | Most of our CAI's have improved access due to being on the improved middle mile infrastructure. That infrastructure now has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. For CAI's that have had new fiber constructed to their locations they have capability with the equipment deployed for services up to 10Gbps depending on what service level they choose. As their capabilities grow beyond the equipment deployed, we could upgrade that equipment through operational funds and improve their connectivity up to 100G. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. In addition, due to funding from the NTIA, the entire NCREN core operates at 100Gbps. | FALSE | N/A | We anticipate completing all activities associated with the extension request of December 2012. This includes the deployment of the three colocation facilities and the deployment of all 100G equipment to the R1's. | MCNC | No significant challenges in continuing on the execution of the project were experienced. | We do not anticipate any challenges based on the remaining work to be performed.
NT10BIX5570011 | 2013 | Q3 | Q3 - 2013 | MCNC previously reported that the original project, as well as the project modifications approved in spring of 2012, are complete. The associated miles in the project are 444 miles of new fiber; 314 miles of leased fibers and197 miles of existing network miles upgraded; and 1866 CAI's with improved or new connectivity. During this quarter all remaining 100G upgrade equipment for the Research universities was deployed as were the three huts that were approved in December of 2012. All aspects of the project have been completed. | 444 | 314 | 197 | 0 | 444 | 0 | 0 | 1125 | The 444 miles represented here matches the original approved build and additional miles added during the project. Initial baseline established would have projected 467.1 miles for this quarter, but the forecasted amount included miles that NTIA allowed to be acquired under IRU (indefeasible right to use) once the project began and means this number will always track below baseline. | Our projections on network miles leased have been inaccurate due to misinterpretation of network miles leased versus network miles upgraded in our baseline projections. The total of 314 miles reported here is made up of 197 from ERC and FRC routes communicated in the original application, 61 from the Morris Broadband acquisition, and 33 from the Balsam and Plateau IRU's approved during the project. The additional 23 miles as approved in the savings request have now been added for a total of 314 miles. This number will always be less than the final projection of 420 due to misunderstanding of accounting of these miles at baseline completion. | These miles represent fiber that MCNC already had the rights to via IRU and presented in the project and BTOP then funded the equipment. Baseline always showed 0 throughout the project and were moved from the "network miles leased" area here in a previous quarter which is creating the variance to baseline. | N/A | The 444 miles represented here matches the original approved build and additional miles approved during the project. | N/A | N/A | This final number is higher to baseline due to the additional approved builds during the project and our estimate for number of required handholds designed during engineering being low initially. | 10 | 3 | 70 | Signed agreements completed to date are as follows: 1. ERC (dark fiber) through MCNC 2. FRC (dark fiber) through MCNC 3. FRC (lit service) through MCNC 4. Earthlink (dark fiber) through MCNC 5. RST Communications (dark fiber) through MCNC 6. Verizon Wireless (lit service) through FRC (subrecipient) 7. Morris Broadband (dark fiber) through FRC (subrecipient) 8. Pangea Internet (dark fiber) through FRC (subrecipient) 9. Broadplex (dark fiber) through MCNC 10. MOX Networks (dark fiber) through MCNC Conversations with Dukenet have stalled. We contribute this primarily due to their recent announcement about being acquired by Time Warner Cable. Conversations with Balsamwest and TW Cable regarding fibers along a portion of the route are ongoing, as well as additional purchases from RST and Earthlink. | MCNC is not providing wholesale services. The Agreements and providers noted above will be providing wholesales services as these agreements are formalized and these providers begin deploying equipment and services in those regions. | FRC has been contracted to provide fiber maintenance (locates and break/fix) on the fiber. Now that construction is complete, they have assumed this responsibility. They will provide route maintenance on 100% of the newly constructed fiber. On fiber assets that they retain in the new fiber footprint, they will be in a position to provide wholesale services to other wholesale carriers, last mile carriers, and private enterprise. MCNC will be focused on the education, government, and public health sectors. FRC Contact Info: Mike Baldwin Senior Counsel, Business and Legal Affairs 1500 Hampton Street, Columbia SC 29201 (803)-726-4053 MCNC Contact Info: Tommy Jacobson COO 3021 E. Cornwallis Road Research Triangle Park, NC 27709 | 1 | 1 | 8 | 2 | FRC is providing lit service under a master contract with Verizon Wireless to 17 wireless towers over portions of the network. | In advance of FRC lighting portions of the route on their own for the fibers they acquired in the route, they have contracted with MCNC for the next year to provide a 10Gbps lambda between New Bern and Wilmington on the MCNC network. | Dark fiber agreements communicated in previous reports for the arrangements with FRC (as part of the subrecipient agreement), ERC, Pangea Internet, Morris Broadband, RST and Earthlink. During the quarter agreements with Broadplex and MOX Networks materialized. Discussions continue with Dukenet, Balsamwest, Time Warner Cable and Earthlink (additional purchase) for portions of the constructed network. | Earthlink and RST are the first two providers that we believe will be providing wholesale and residential services in the areas of their purchases. However, we do not have direct visibility to what those offerings are or how they have provisioned the dark fibers they have received. Within the MCNC/FRC fibers, the service MCNC is providing is operating at 10G and the services that FRC is providing is operating at 100M. 100M: 17 subscribers 10G: 1 subscriber | 1866 | 19 | 1847 | 1 | We are serving 1866 CAI's. This is 4 less than was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities | These 19 sites reported represent locations approved for new builds during the project. | We are now reporting 1847 CAI's. This is less than what was communicated in prior quarters. MCNC was advised by NTIA to remove 17 CAIs that were previously reported as improved because now they are counted on the MCNC Round 2 project as receiving new fiber builds. Additionally, we added 13 sites that were approved during this past year during project reroutes. 19 sites were approved as part of that process, but 6 were already included in the report as receiving improved access due to the initial project as funded. We do not include them again now to keep from double counting. Therefore, 1847 will be listed as receiving improved access and 19 will be listed as receiving new access, for a total of 1866. As our understanding of the reporting requirements refined during the project, we now know that projections in our initial application and baseline are inaccurate due to misinterpretation of the guidance. Initial projections were based on community anchor institutions located in the counties in which our fiber route passes through, but not necessarily on-net with the North Carolina Research and Education Network (NCREN) today. Based on the clarifications from a previous quarter, what we report here are CAI's that were already connected to the NCREN backbone in some capacity that have received improved access due to the deployment of fiber and higher grades of service (i.e. 10Gbps internet service) out of NCREN maintained facilities. | Most of our CAI's that are noted have improved access due to being on the improved middle mile infrastructure. That infrastructure now has capability for 100G. On the system deployed, direct point to point services as shown below are possible: 100M, 250M, 500M, increments of 1G, 10G, 100G. For CAI's that have had new fiber constructed to their locations they have capability with the equipment deployed for services up to 10Gbps depending on what service level they choose. As their capabilities grow beyond the equipment deployed, we could upgrade that equipment through operational funds and improve their connectivity up to 100G. Currently these locations that had direct fiber built have had 100M services provisioned over 1G interfaces. 100M: 19 subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are able to provide lambda based point to point based circuits between all NCREN POP's enabled by the new infrastructure and to portions of the central core (defined as the Charlotte to Raleigh corridor) of the NCREN network that existed prior to application. In addition, due to funding from the NTIA, the entire NCREN central core operates at 100Gbps. | FALSE | N/A | N/A as project is complete. | MCNC | No significant challenges in continuing on the execution of the project were experienced. | N/A as project is complete.
NT10BIX5570016 | 2010 | Q3 | Q3 - 2010 | EA draft completed and submitted to NTIA. Awaiting response from USFWS for approval of EA and SHPO for completion of PA. Preliminary bidder interviews held. Bid assessments completed. Successful bidder selected and notified of award. Pre-construction meeting with successful bidder held at MBC headquarters that included representatives from landbase provider and DOL. Started railroad permitting process. National Forest Service application sent - awaiting approval of EA and Biological Evaluation for issuance of permit. NPS determined project would have no impact on Blue Ridge Parkway. Corps of Engineers project manager assigned. New landbase uploaded to our mapping system to record OSP property routes and records. Dates established for mapping system training. Ordered generators for hut sites. Completed site surveys for one of the two interconnection points. Negotiating joint use pole agreements with three utility companies. Performed first drawdown of funds on this project. Ordered generators for interconnection sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No information to add | N/A | N/A | N/A | No information to add | No information to add | No information to add | No information to add | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No information to add | No information to add | No information to add | No information to add | 0 | 0 | 0 | 0 | No information to add | No information to add | No information to add | General offering of 10-100 mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Approval of EA â€¢ Satisfaction of PA â€“ site visits of architectural and historical sites in accordance with PA â€¢ Approval of PA â€¢ Final execution and distribution of EF&I contract â€¢ Obtain VDOT, railroad, NFS, USACE, USFWS permits â€¢ Complete detailed design and engineering activities â€¢ Complete joint use pole agreements â€¢ Obtain easements and complete interconnection point design â€¢ Begin reviewing and issuing construction prints â€¢ Hire field inspector â€¢ Start construction activities of project, including ordering materials â€¢ Provide M-4(CAD) training to engineering vendors â€¢ Order pre-fabricated huts | Virginia Tech Foundation, Inc. | Major challenge has been getting response from USFWS for EA & obtaining PA approval. | Obtaining approval of the EA and PA. Weather conditions will be of a concern for construction activities.
NT10BIX5570016 | 2010 | Q4 | Q4 - 2010 | The Programmatic Agreement (PA) was drafted and submitted to the NTIA. The State Historic Preservation Office (SHPO) and other agencies had some questions about content/form. MBC, in consultation with our consultant and the NTIA, decided to forego future work on the PA and move forward with the preparation of a conventional Environmental Assessment (EA). That work is in progress. It was felt that the detailed engineering was now far enough along that it could be accomplished faster than completing the PA. Consultations continue with the National Forest Service (NFS), and they are in the process of doing a biological and archeological assessment. A joint permit was submitted to the US Army Corps of Engineers (USACE) and the Virginia Marine Resources Commission (VMRC). MBC had a meeting with the VMRC during December to discuss the scope of the project and any permitting issues. Our EA consultant is addressing a few issues that the USACE and the VMRC wanted clarified. A field inspector was hired for this project. A vehicle was purchased for use by the inspector. Outside Plant Engineering has been completed on the project. Seventy-five percent of the work orders have been field checked. Approximately 20% of the material has been ordered and received. The interconnection sites have been obtained and approvals acquired. The huts for the interconnection sites have been ordered. The VDOT permits have been obtained by the contractor. Utility pole agreements have been ex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No additional information to add. | N/A | N/A | N/A | No additional information to add. | N/A | N/A | No additional information to add. | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | No additional information to add. | N/A | No additional information to add. | No additional information to add. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | General Offering of 10-100 MBPS | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ APPROVAL OF THE EA â€¢ APPROVAL OF ALL OTHER PERMITS â€¢ COMPLETION OF THE ENGINEERING PRINTS â€¢ COMPLETION OF FIELD VERIFICATION OF THE PRINTS â€¢ START CONSTRUCTION ACTIVITIES | Virginia Tech Foundation, Inc. | We have the EA prepared, awaiting response from National Forest Service. This has been a rather drawn-out consultation process. It, along with the submittal of the VARMC permit and SHPO consultations/surveys have held up the construction of this project to the point of very little will be done during the remainder of the winter months. | Winter weather will severely limit the amount of construction activity that will get accomplished.
NT10BIX5570016 | 2011 | Q1 | Q1 - 2011 | The SHPO consultation and evaluation was submitted to SHPO for concurrence and we await their approval before submitting the final draft of the environmental assessment. The permit fees were paid for the US Forest Service permit, but we have not received the approved copy. The Virginia Marine Resources and US Army Corp of Engineers permits were approved. The VDOT Land Use permits were approved. The pre-fabricated huts ordered and received. The network equipment was ordered for the three (3) interconnection sites. The on-site generators have been ordered for the hut sites. The Project Engineering has been completed and all prints have been field verified. All pole permits and pole make ready requests have been submitted and approved. Approximately 70% of the fiber cable and associated material has been ordered. Montgomery County had the most project activity this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will Offer 10 mbps - 100 mbps; open access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will Offer 10 mbps - 100 mbps; open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Gain approval of the EA and obtain the FONSI statement â€¢ Order additional OSP material â€¢ Receive the approved NFS permit â€¢ Begin site preparation and placement of the huts â€¢ Begin Outside plant construction activities We plan to increase the number of construction crews working on this project, once we receive the FONSI. We have had discussions with the contractor regarding this plan. Rainy weather this Spring, though beyond our control, will hamper construction efforts if it continues. If we cannot catch up with the baseline estimates, we will move the completion date of the project. It should still be completed within the time frame allowed by the grant. | Virginia Tech Foundation, Inc. | Obtaining approval of the EA and the FONSI statement and the NFS permit. | Obtaining approval of the EA and the FONSI statement.
NT10BIX5570016 | 2011 | Q2 | Q2 - 2011 | The State Historic Preservation Officer (SHPO) consultation report was approved on 4-8-11 and the Environment Assessment (EA) was approved and the Finding of No Significant Impact (FONSI) was issued on 5-17-11. THE National Forest Service (NFS) permit has not been received, but we were assured it is being prepared. We received a partial shipment of the network transport equipment. All pole permits have been applied for, and responses received, however the make-ready work continues to be done by various utilities. The contracts for the site work and placement of the interconnection huts (2) was completed, the Request for Proposal (RFP) issued, and the successful bidder selected and awarded the contract. A pre-construction meeting was held for huts construction. Outside Plant construction activities started on 5-23-11. Approximately 15 miles or 16% had been placed by the end of the quarter. | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Outside Plant Construction (OSP) started on 5-23-2011. The baseline in Q2 was not met because of delay in construction. Construction was delayed because the approval of the Environmental Assessment was delayed. However, MBC is deploying additional crews to attempt to "catch up" on the schedule. | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will offer 10mbps/100mbps open access. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will offer 10mbps/100mbps open access. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Obtain National Forest Service permit. Complete the site work and the completion of the huts (2). Receive the remaining transport equipment. Begin installation of the transport equipment. Complete make-ready work. Continue progress in construction to "catch up" on the construction schedule. | Virginia Tech Foundation, Inc. | The lack of approval of the National Forest Service permit had potential to delay certain sections of construction. (Permit was received in Y2Q3.) Rock was encountered in numerous locations. | 1. Receiving the remainder of the required cable in a timely manner. 2. Gaining completion of the make-ready work by other utilities in a timely manner. 3. Encountering rock in locations.
NT10BIX5570016 | 2011 | Q3 | Q3 - 2011 | The National Park Service Permit was approved on 9-1-11. We have received the majority of the network transport equipment. We have received the cable from the alternate supplier we had been waiting for. The two huts have been received, paid for, and are ready for installation. Make-ready work continues to be done by various utilities. Construction has been completed from Virginia Tech to Pemtelâ€™s co-location site in Newport, VA (12 miles). We will be providing a circuit for Pemtel thru this fiber. Site work is continuing on the two interconnection hut sites. Approximately 45 miles or 43% of the cable had been placed by the end of the quarter. Giles County had the most project activity this quarter. | 45 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | Due to late start, progress has been slower than anticipated. | N/A | N/A | N/A | Due to late start, progress has been slower than anticipated. | N/A | N/A | N/A | 0 | 1 | 12 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will offer 10 mbps-100mbps; open access. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Will off 10 mbps-100 mbps; open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Complete the site work and placement of the Huts â€¢ Receive the remaining transport equipment * Begin installation of the transport equipment â€¢ Complete make-ready work â€¢ Deploy 31 new network miles â€¢ Sign an agreement with Pemtel (1st agreement) â€¢ In order to catchup on the milestones, the contractor will add 3 additional crews in November, for a total of 7 crews working on the project. See "Next Quarter Challenges" for additional mitigation efforts. | Virginia Tech Foundation, Inc. | â€¢ Gaining completion of the make-ready work by other utilities in a timely manner â€¢ Continue to encounter numerous locations with rock * Encountered construction problems (water seepage) on the hut sites. â€¢ Heavy rains have slowed construction progress in some areas | â€¢ Gaining completion of the make-ready work by other utilities in a timely manner â€¢ Continue to encountered numerous locations with rock â€¢ Weather may slow construction progress in all areas â€¢ Work in the National Park area will present unique challenges; permit requirements. â€¢ In order to ensure that 67% of the project is completed by the end of year 2, the contractor will add 3 additional crews, and will provide weekly progress reports to project management and VT inspector. Potential problems/roadblocks will be identified and promptly addressed. Focus on finishing buried construction prior to winter weather. Complete the site work on the 3rd interconnection site and place the node building by the end of Nov. Accept contractor billing twice per month instead of once per month to decrease lag time in the billing and construction ratio.
NT10BIX5570016 | 2011 | Q4 | Q4 - 2011 | A site visit was conducted by the NTIA program officer on November 9-10, 2011. An OMB-A133 audit of the Virginia Tech Foundation (to include this grant) was conducted in this quarter; the final report has not been issued. All of the network transport equipment has been received. All make-ready work has been completed by the various utilities. Site work is completed on one of the two interconnection hut sites: East Park Hut. Wet weather hampered completion of the second site at New Castle. Placement of the fiber cable in the National Forest area has been completed with no problems/issues. Approximately 41 miles of fiber cable was placed during the quarter, bringing the total cable placed, to date, to 86 miles or 82%. The first circuit was placed in service to Pemtel on November 1, 2011. There are no CAIâ€™s to be served on this project. Botetourt County had the most project activity this month. | 86 | 0 | 0 | 0 | 86 | 0 | 0 | 1 | Due to late start, progress has been slower than anticipated | N/A | N/A | N/A | Completed 41 miles in Y2Q4 for a total of 86 miles | N/A | N/A | Pem Tel co-location completed in October 2011 | 1 | 1 | 12 | Pembroke Telephone Company | [REDACTED] | N/A | 1 | 0 | 0 | 1 | PemTel-Signed November 2011 | N/A | N/A | 10 mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Complete the site work an placement of the remaining hut â€¢ Begin installation of the transport equipment â€¢ Complete 100% of fiber construction, including all the aerial construction â€¢ Obtain electrical service to both hut sites * The contract with the Pembroke Telephone Company is for 200 Mbps transport to Ashburn, VA, for IP traffic for their DSL customers. * A 10 Gbps TDS circuit, to be used for DSL expansion in the New Castle area, is also being discussed. | Virginia Tech Foundation, Inc. | â€¢ Gaining completion of the aerial make-ready work by the other utilities in a timely manner â€¢ Wet weather causing delays in placing buried fiber cable and site work for huts â€¢ Placing fiber cable over mountainous terrain with numerous rock locations â€¢ Completing installation and splicing of fiber to make service date for Pemtel circuit | â€¢ Heavy rains have slowed construction progress in some areas â€¢ Obtaining electrical service to the hut locations â€¢ Completing the construction activities by the end of the quarter since winter weather has begun
NT10BIX5570016 | 2012 | Q1 | Q1 - 2012 | Virginia Tech (VT) and Mid-Atlantic Broadband Cooperative (MBC) prepared a route modification request to add one interconnection point (Prices Fork hut) and a proposed IRU from the Eastpark Node to the Cox POP in Roanoke, VA and to Virginia Techâ€™s Carilion School of Medicine at a cost of approximately $1,400,000. VT and MBC prepared a budget modification to request that the original budget be modified to redistribute existing budgeted funds to cover the additional expenditures. These requests will be sent to the NTIA for approval in the 2nd quarter 2012. The two huts (interconnection points) on the project have been placed on site and power connected to all of them. This completes the construction of the two nodes (huts) and the co-location site at Pemtel. The installation of transport equipment continued in the 1st quarter 2012 and should be complete by the end of the 2nd quarter 2012. Virginia Tech continued regular field inspections of the project, along with MBCâ€™s inspector, during the quarter. We spent $1,293,804 on the project this quarter, bringing the total spent to $4,661,726 (67.3%). Approximately 10 miles of fiber cable was placed this quarter. This brings the total cable placed to date to 96 miles or 91%. All that remains to be constructed is the aerial cable (strand has been placed). There are no CAIâ€™s to be served on this project. We had one new contract for a 50 mbps circuit to a cell site signed this quarter by a last mile provider. Craig County had the most project activity this month. | 96 | 0 | 0 | 0 | 96 | 0 | 0 | 3 | Aerial cable remains to be placed in Y3Q2 | N/A | N/A | N/A | Completed 10 miles in Y3Q1 | N/A | N/A | All interconnection points (huts) complete | 2 | 3 | 12 | Pembroke Telephone Company Lumos | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no long offered. Fiber lease arrangements are considered on case by case basis. (Member pay annual fee for use of dark fiber strands.) Five year minimum lease term. | N/A | 2 | 2 | 0 | 2 | Pemtel-signed in November 2011; Lumos - signed in March 2012 | Pemtel; Lumos | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Complete installation of the transport equipment at the three interconnection points (huts) â€¢ Complete 100% of fiber construction, including all the aerial construction â€¢ Complete contracts with Verizon (cell site) and TDS (transport) in Y3Q2 | Virginia Tech Foundation, Inc. | â€¢ Completion of the aerial construction across mountainous terrain. â€¢ Preparing route modification and budget modification requests | â€¢ Progress on completion of Equipment installation is dependent upon manpower resources â€¢ Obtain NTIA approval of the new route modification and budget modification requests. â€¢ Obtain quick EA addendum approval of route modification request
NT10BIX5570016 | 2012 | Q2 | Q2 - 2012 | The route modification request to add one interconnection point (Prices Fork hut) and a proposed IRU from the Eastpark Node to the Cox POP in Roanoke, VA and to Virginia Techâ€™s Carillion School of Medicine at a cost of approximately $1,400,000 has been approved and activities are underway to complete the modifications before the December 31, 2012 deadline. The budget modification to reallocate the federal and matching funds was also approved. Approval was obtained to use program income to offset the matching funds share. The installation of transport equipment was completed during the 2nd quarter 2012. Installation of the remaining aerial cable was also completed during the 2nd quarter 2012. Fiber testing was completed between all sections. Virginia Tech continued regular field inspections of the project, along with MBCâ€™s inspector, during the quarter. The annual audit of the Virginia Tech Foundation began during the quarter. We spent $419,475 on the project during the quarter, bringing the total spent to $5,081,201 (73.37%). Approximately 9 miles of fiber cable was placed this quarter. This brings the total cable placed to date to 105 miles or 100%. There are no CAIâ€™s to be served on this project. No new contracts have been signed this quarter. MBC is holding meetings with Citizens Telephone, the Virginia Department of Transportation and The County of Botetourt concerning possible agreements. Botetourt County had the most project activity this quarter. | 105 | 0 | 0 | 0 | 105 | 0 | 0 | 4 | 100% - 9 miles placed in Y3Q2 | N/A | N/A | N/A | 9 miles placed in Y3Q2 | N/A | N/A | 3 new interconnection points built; 1 new co-location with Pemtel buil; 1 new co-location with Pemtel built | 2 | 3 | 12 | Pemtel (Pembroke Telephone Company) Lumos | MBC provides optical transport services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case-by-case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease termt services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case-by-case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 2 | 2 | 0 | 2 | Pemtel, Lumos | Pemtel, Lumos | N/A | 10 mbps-100 mbps- Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ To complete the approved reroute modification work before the December 31, 2012 deadline. â€¢ To complete all invoicing and refund retainage for all work except the route modification. â€¢ To prepare engineering drawings and start construction on Prices Fork node. â€¢ To complete and have Cox-MBC IRU signed by the end of August, 2012. | Virginia Tech Foundation, Inc. | * Completion of the aerial construction across mountainous terrain * Preparing route modification and budget modification requests and their approval * Completion of equipment installation | â€¢ To commence construction work on route modification so as to be finished by the December 31, 2012 deadline. â€¢ To obtain building permit from the Town of Blacksburg for placing the Prices Fork Node.
NT10BIX5570016 | 2012 | Q3 | Q3 - 2012 | All of the construction work has been completed on the original proposed route. Preliminary work is progressing on the proposed additions approved under the route modification (Prices Fork hut and a proposed IRU from the Eastpark Node to the Cox POP in Roanoke, VA and to Virginia Techâ€™s Carilion School of Medicine). The Mid-Atlantic Broadband Cooperative (MBC) inspector and the inspector from Virginia Tech have completed a final ride-out and quality control audit of the original construction. The easement and approved site plan have been submitted to the Town of Blacksburg for a building permit for the Prices Fork hut site. The power company has placed underground power service to the site. The construction prints have been prepared and approved. The materials have been ordered for the hut and cable construction. We conducted a meeting and field visit with Citizens Telephone to co-ordinate their co-location work. The IRUs have been signed by MBC and Cox Cable and a â€œmeet pointâ€ established near the node at Eastpark. We spent $894,373 on the project during the quarter, bringing the total spent to $5,975,574 (86.29%). No additional fiber cable was placed this quarter. The total cable placed to date remains at 105 miles or 100%. There are no CAIâ€™s to be served on this project. No new contracts have been signed this quarter. We have pending contacts for three (3) circuits-2 cell tower sites and a doctorâ€™s office. MBC has conducted meetings with the Virginia Department of Transportation and The County of Botetourt concerning possible agreements. Montgomery County had the most project activity this month. | 105 | 0 | 0 | 0 | 105 | 0 | 0 | 4 | Complete | N/A | N/A | N/A | Complete | N/A | N/A | Three (3) new interconnection points built. One (1) new colocation with Pemtel built. | 2 | 3 | 12 | Pemtel (Pembroke Telephone Company) Lumos | MBC provides optical transport services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Because grant funds are being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case-by-case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 2 | 2 | 0 | 2 | Pemtel; Lumos | Pemtel; Lumos | N/A | 100mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10mpbs-100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10mpbs-100mbps - Open Access | N/A | FALSE | N/A | â€¢ To complete the approved reroute modification work before the December 31, 2012 deadline. â€¢ To complete all invoicing and refund retainage for all performed work before the December 31, 2012 deadline. | Virginia Tech Foundation, Inc. | â€¢ Obtaining the easement for Prices Fork Node â€¢ Obtaining agreement and approval of the two IRUs with Cox â€¢ Completion of Prices Fork site plan and its approval | â€¢ To commence construction work on route modification so as to be finished by the December 31, 2012 deadline. â€¢ To successfully complete the entire grant project on time and within the budget.
NT10BIX5570016 | 2012 | Q4 | Q4 - 2012 | All of the construction work has been completed on the original proposed route. Construction work began this quarter on the Prices Fork hut and the proposed IRUs from the Eastpark Node to the Cox POP in Roanoke, VA and to Virginia Techâ€™s Carilion School of Medicine authorized under the route modification plan. The engineering was completed for the Prices Fork hut and the permits from the Town of Blacksburg and VDOT were submitted and approved during the quarter. Installation continues on the Infinera ring equipment, but canâ€™t be completed until the last node is in place. An Extension Request for this grant was submitted on December 21, 2012 to request extension of the construction complete date from February 1, 2013 to June 30, 2013. This extension will compensate in part for the time lost due to bad weather and delays in getting approval of the Environmental Assessment and a permit from the National Park Service. We spent $519,313.69 on the project during the quarter, bringing the total spent to $6,494,887.39 (93.79%). No additional fiber cable was placed this quarter. The total cable placed to date remains at 105 miles or 100% of the original route. There were no CAIâ€™s on the original project, but the route extension will add one CAI to be served on this project. Two new contracts for circuits have been signed this quarter, bringing the total to four for the project YTD. Montgomery County had the most project activity this month. | 105 | 15 | 0 | 0 | 105 | 0 | 0 | 4 | Original design complete. Route modification will add 0.8% of the original number of miles | IRU completed from Cox Communications | N/A | N/A | Complete | N/A | N/A | Three (3) new interconnection points built. One (1) new colocation with Pemtel built. | 4 | 2 | 12 | Pemtel (1) Lumos (3) | MBC provides optical transport services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Because grant funds are being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case-by-case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 4 | 0 | 0 | 4 | Pemtel, Lumos | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | N/A | FALSE | N/A | * To receive approval of the project extension request in January, 2013 * Complete construction of the approved route modification work before March 30, 2013 * Complete the equipment installation in the nodes | Virginia Tech Foundation, Inc. | * Commence construction (site work and fiber construction) work on route modification to be finished by grant extension deadline * Finalization of the two IRUs with Cox * Completion of Prices Fork site plan and its approval | * To complete all construction and cutover work on the route modification to be finished before March 30, 2013 * Be in a position to complete the Infinera ring installation so grant can be closed by June 30, 2013.
NT10BIX5570016 | 2013 | Q1 | Q1 - 2013 | All of the construction work has been completed on the original proposed route. Construction work continued on the Prices Fork node site, consisting mostly of directional boring, but has been hampered by winter weather. The proposed IRUs from the Eastpark Node to the Cox POP in Roanoke, VA and to Virginia Techâ€™s Carilion School of Medicine authorized under the route modification plan have been completed. The franchise agreement with the Town of Blacksburg was approved at the City Council meeting on March 12, 2013. Installation continues on the Infinera ring equipment, but canâ€™t be completed until the last node is in place. An Extension Request for this grant was submitted on December 21, 2012 to request extension of the construction complete date to June 30, 2013. This extension will compensate in part for the time lost due to bad weather and delays in getting approval of the Environmental Assessment and a permit from the National Park Service. The extension was approved on January 28, 2013. We spent $49,137.97 on the project during the quarter, bringing the total spent to $6,544,025.36 (94.50%). No additional fiber cable was placed this quarter. The total cable placed to date remains at 105 miles or 100% of the original route. There were no CAIâ€™s on the original project, but the route extension added one CAI. No contracts were added this quarter, so they remain at four (4) for the project YTD. Montgomery County had the most project activity this month. | 105 | 15 | 0 | 0 | 105 | 0 | 0 | 4 | Original design complete. Route modification will add 0.8 miles of new cable. | IRU from Cox complete | N/A | N/A | Route modification will add 0.8 miles of new cable | N/A | N/A | 3 new interconnection points built. One (1) new co-location built. One (1) new location in progress. | 4 | 2 | 12 | Pemtel (1); Lumos(3) | MBC provides optical transport services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Because grant funds are being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case-by-case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 4 | 0 | 0 | 4 | Pemtel, Lumos | N/A | N/A | 10 mbps-100 mbps; Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-100 mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps; Open Access | N/A | FALSE | N/A | â€¢ Complete construction of the approved route modification work and close out the project construction by June 30, 2013. â€¢ Complete the equipment installation in the nodes by June 30, 2013 | Virginia Tech Foundation, Inc. | â€¢ Construction (site work and fiber construction) work on the route modification has been slowed by winter weather conditions | â€¢ To complete all construction and cutover work on the route modification so as to be finished by June 30, 2013. â€¢ To complete the Infinera ring installation in the nodes by June 30, 2013.
NT10BIX5570016 | 2013 | Q2 | Q2 - 2013 | The Virginia Tech Foundation (VTF) BTOP Project NT10BIX5570016 (248) provides for constructing a 106-mile open access fiber-optic network from the Town of Blacksburg in Montgomery County to the City of Bedford in Bedford County. VTF partnered with Mid-Atlantic Broadband Communities Corporation (MBC) to extend their existing fiber-optic footprint to unserved and underserved communities in the Appalachian region reaching the Virginia Tech main campus in Blacksburg, Virginia. The resulting network crosses six counties (Montgomery, Craig, Giles, Bedford, Botetourt, Roanoke) in Virginiaâ€™s Appalachian region. Virginia Tech is leveraging the fiber to dramatically improve access for the university to national and international research networks, increasing the competitiveness of VT science and engineering research and enhancing technology-enabled learning. Using the BTOP fiber path to reach MBCâ€™s extensive network, Virginia Tech implemented a new, diverse 10Gbps link to the Mid-Atlantic Research and Education Exchange in Ashburn, Virginia for direct access to Internet2, federal research networks, content providers, and tier one internet gateways. On behalf of the VT Carilion Research Institute (CRI) located in Roanoke, Virginia Tech is lighting a new private optical network over the BTOP fiber linking the Institute to the university main campus to support biomedical research and education. This network will also support location of a disaster recovery site for Virginia Techâ€™s Information Technology infrastructure on at the CRI campus location. Virginia Tech is using the BTOP fiber path to connect the remote University of Virginia Mountain Lake Biological Monitoring Station and VTâ€™s Kimballton Deep Underground Research Facility both located in the mountainous region of Giles County, Virginia. The BTOP fiber dramatically increases the capacity available to these facilities enabling new forms of physics and biology research at both locations. MBC is working with retail and public service providers along the fiber path to increase availability for all modes of broadband access and to increase competition. Even before the fiber was completed, MBC provided a gigabit link to the Pembroke Telephone Cooperative which provides service to rural communities in Giles County, Craig County, and the surrounding area effectively boosting the total access capacity available to that entire community. Similarly, MBC increased the capacity and diversity for TDS Telecom serving the residents of the New Castle, Virginia community which previously advertised no available broadband services in that region. LUMOS has leveraged the unique fiber path as a middle mile resource to gain diversity and to increase capacity for customers throughout the region. Citizens Telephone Cooperative has partnered with MBC to leverage the BTOP fiber in concert with other BTOP funded projects to expand broadband access through Floyd, Montgomery, Giles, Wythe, and Bland counties and all the surrounding communities they serve. The fiber is being used to support backhaul for cellular network providers, significantly increasing the availability of mobile coverage and capacity along the fiber path including communities where cell service was poor or unavailable previously. | 106 | 15 | 0 | 0 | 106 | 0 | 0 | 5 | Complete | IRU from Cox | N/A | N/A | Complete | N/A | N/A | Complete | 5 | 2 | 12 | Pemtel (1); Lumos (3); Citizens (1) | MBC provides optical transport services, using both SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 5 | 0 | 0 | 5 | Pemtel (1); Lumos (3); Citizens (1) | N/A | N/A | 10 mbps-100mbps - Open Access | 2 | 1 | 1 | 0 | N/A | Virginia Tech | Carilion | 10 mbps-100 mbps - Open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps - Open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps - Open access | N/A | FALSE | N/A | Complete all close-out activities and reports. | Virginia Tech Foundation, Inc. | Ensuring that all charges were submitted for reimbursement and all close-out activities were begun. | Complete all close-out activities and reports.
NT10BIX5570017 | 2010 | Q3 | Q3 - 2010 | During the 3rd quarter of 2010, the Commonwealth of Pennsylvania focused on issuing purchase orders of equipment and services to support the launch of our project. In the process, the commonwealth issued purchase orders to Alcatel-Lucent Corporation for a portal based product to provide asset management as well as to assist in business management of the high-speed internet sales. We have also issued purchase orders for the engineering, project management and installation services in support of the various upgrades to the microwave network. The Commonwealth held a "Broadband Summit" in September bringing equipment vendors together with internet service providers and the public to educate and discuss the issues at hand concerning broadband and the lack of broadband in underserved and unserved areas of Pennsylvania. The Commonwealth added two new employees to dedicate to grant compliance and project management. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No construction or implementation started at this point. | Our project does not include leased network. | No construction or implementation started at this point. | Our project does not include leased network. | No construction or implementation started at this point. | No construction or implementation started at this point. | No construction or implementation started at this point. | No construction or implementation started at this point. | 0 | 0 | 0 | n/a at this point in the project | Current plan is to offer Ethernet virtual circuits at 3, 6,10, 20 and 50 Mbps. Price will be based on Network Interface Access and number of microwave hops between ports. Standard features to include Layer 2 MPLS Ethernet ports, best effort routing with route protection in backbone hops, and base price includes basic burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Includes tower site compound access, but not tower space. | n/a | 0 | 0 | 0 | 0 | No providers have signed agreements at this point. | No providers have signed agreements at this point. | Not included in this project. | No providers have signed agreements at this point. | 0 | 0 | 0 | 0 | No subscribers served at this point | No subscribers served at this point | No subscribers served at this point | No subscribers served at this point | 0 | 0 | 0 | 0 | 0 | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | 0 | 0 | 0 | 0 | 0 | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | Not addressed in this project. | Because the BTOP grant is being implemented by a Public Safety communications agency, we will be considering discounting services to local public safety entities by approximately 30%, such as local fire, police and emergency response. | FALSE | n/a | By the end of the 4th quarter of 2010, the Commonwealth of Pennsylvania hopes to begin site preparation and construction of the first link between two sites of our project, weather permitting. We also expect the centralized operating software, customer support and billing components of the software that we procured during the 3rd quarter be installed onto hardware. Purchase orders for shelter, tower and compound work will be issued. A procurement for a quality assurance vendor will be completed. By the close of the 4th quarter, we also hope to have received the remaining site agreement amendments fully executed as well as any site permits we might need for the following quarter. Additionally, we plan to begin equipment installation at three of our sites to enable speeds up to 150 Mbps. This progress will position the project to remain on schedule with the focus on major infrastructure improvements to be rolled out in the 2nd Quarter of 2011. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | Significant effort was expended to move from detailed vendor quotations to issuance of Commonwealth purchase orders within the structure of the grant program. Accomplishing this administrative task is enabling equipment and service delivery to begin. | The challenge in Q4 that we anticipate might delay our progress, would be a colder or wetter than normal winter. Significant rain or snowfalls accumulations during these months would make tower work perilous and progress on site work and tower/shelter construction difficult.
NT10BIX5570017 | 2010 | Q4 | Q4 - 2010 | During the fourth quarter of 2010, the commonwealth of Pennsylvania focused on issuing any remaining purchase orders for equipment and services to allow the first pieces of equipment to be installed by the close of the year. We were able to initiate equipment installation by the end of December and saw three microwave connections become capable of passing broadband traffic. We have issued purchase orders for wireless equipment and installation as well as purchase orders for five self-supporting towers and eleven shelters on and in which the equipment will be mounted. The commonwealth also held an asset management workshop with our vendor to finalize details on an asset management system to track and manage the equipment purchased with the broadband project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | At this point in the project, we have not deployed any new network miles. | n/a, our project does not include leased network | While we have installed and tested equipment at three sites in the network, until the MPLS is installed at those sites, we will not consider them to be fully upgraded | n/a, our project does not include leased network | n/a, our project does not include fiber | At this point we have not created any new wireless links but plan to during the third quarter of 2011. | We will be building five new towers as part of our project. Those towers are expected to reach completion in the second and third quarters of 2011. | We have not added any interconnection points into the backbone at this point in the project. | 0 | 0 | 0 | At this point we do not have any agreements currently being negotiated with wholesale/last-mile providers. While our baseline indicated that we would potentially have five, we have not begun negotiations at this point. We do expect; however, to open our doors to sell broadband services as of Q3, 2011. As we get closer to that time, we would anticipate negotiations to begin. | Our current plan continues to be to offer Ethernet virtual circuits at 3, 6, 10, 20, and 50 Mb/s. Our pricing will be based upon Network Interface Access and number of microwave hops between ports. Standard features will include Layer 2 MPLS Ethernet ports, best effort routing with route protection in backbone hops, and base price includes basic capability of up to 25% of contracted bandwidth at no cost if access capacity is available. Agreement includes tower site compound access but not tower space. | n/a | 0 | 0 | 0 | 0 | n/a at this point in the project | n/a at this point in the project | n/a, not a part of this project | No providers have signed agreements at this point | 0 | 0 | 0 | 0 | No subscribers served at this point in the project | No subscribers served at this point in the project | No subscribers served at this point in the project | No subscribers served at this point in the project | 0 | 0 | 0 | 0 | 0 | Not addressed in this project | Not addressed in this project | Not addressed in this project | Not addressed in this project | Not addressed in this project | 0 | 0 | 0 | 0 | 0 | Not addressed in this project | Not addressed in this project | Not addressed in this project | Not addressed in this project | Not addressed in this project | Because the BTOP grant is being implemented by a Public Safety communications agency, we will be considering discounting services to local public safety entities by approximately 30% such as local fire, police and emergency response. | FALSE | n/a | Looking forward to Q1 of 2011, the Commonwealth of Pennsylvania, hopes to see significant progress on our project such as increased equipment deployment and the beginning stages of tower construction. By the close of Q1, 2011 we hope to be closer to the goal of 100% of our permissions documents in place. We also hope to begin receiving invoices for equipment that was installed the previous quarter. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | During Q4 of 2010 the Commonwealth of Pennsylvania was able to issue the remaining purchase orders for equipment and services deemed critical to our ability to complete the project on time. With that accomplishment, we were able to have all of the equipment, towers and shelters ordered and also were able to install the first pieces of equipment prior to the close of the quarter. We feel confident that our progress during the 4th quarter has put us into an excellent position to catapult into continued progress in 2011. | The greatest challenge with equipment installation during the late winter months is rain and snow along with the slippery conditions they create for any tower climbs. Additionally there is the potential for softened ground should there be any thawing which would create an increased risk of trucks getting stuck, causing damage to the compounds and roadways.
NT10BIX5570017 | 2011 | Q1 | Q1 - 2011 | By the close of the first quarter of 2011, the Commonwealth of Pennsylvania was able to continue installation of microwave equipment, begin shelter construction and work on the initial design of our billing and provisioning system for the sale of broadband to last mile providers and community anchor institutions. As of the end of March 2011, we have installed fifteen of the seventy-one microwave connections included within the project scope as well as poured three of the shelter foundations. We have also actively inspected the completed and planned work with a quality assurance vendor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no new network miles have been deployed | n/a, our project does not include leased network | While we have installed upgraded microwave equipment at fifteen sites in the network, until the switching upgrades have been installed at those sites as well, we are not considering them to be fully upgraded | n/a, our project does not include leased network | n/a, our project does not include fiber | Much of the wireless portion of our network will be determined by the first customers to connect to our project. Our plan is to begin the sale of services within the third quarter of 2011. | Our project includes the construction of five new self-supporting radio towers. The construction of those towers will begin in the second quarter of 2011. We expect to complete construction of two of those new towers within the second quarter of 2011. | Interconnection points will be added to the network as the new customers and their needs are determined. We expect to begin offering broadband services as the initial segments of switching enabled bandwidth are completed to interested last mile providers or anchor institutions. | 0 | 0 | 0 | While we have not signed any agreements to date with wholesale or last mile providers, we have had discussions with various middle mile and last mile providers and are working toward determining exactly how the relationship will be structured between the Commonwealth of Pennsylvania and the last mile provider as well as logical points of interconnection between networks. We anticipate signing the first contracts within Q2 of 2011 for service that would start the quarter following. | Our current plan continues to be to offer Ethernet virtual circuits at 3,6,10, 20, and 50 Mb/s. Our pricing will be based upon Network Interface Access and number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports, best effort routing with route protection in backbone connections, and base price includes basic capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement includes tower site compound access but not tower space. | The Commonwealth of Pennsylvania has not designated a third party to manage the available broadband services offered by our network. | 0 | 0 | 0 | 0 | n/a at this point in the project | n/a at this point in the project | n/a at this point in the project | n/a at this point in the project | 0 | 0 | 0 | 0 | n/a No subscribers served at this point in the project | n/a No subscribers served at this point in the project | n/a No subscribers served at this point in the project | n/a No subscribers served at this point in the project | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | Not addressed in this middle mile project | Because our project is implemented by a Public Safety communications agency, we are considering offering discounted services to local public safety entities such as local fire, police and emergency response. | FALSE | n/a Our network management practices have not changed. | By the close of the second quarter of 2011, our project expects to have completed construction of five new shelters as well as two new self supporting radio towers. We believe that we will have begun installation of switching equipment on the network and continued the upgrade of microwave radio connections as well. We also anticipate being on the verge of having worked out a relationship with last mile service provider(s) or interested community anchor institution(s) allowing us to open our doors for business in the areas of the network that have been completely upgraded. We will be able to show a significant increase in actual expenditures during this quarter as items are completed. The commonwealth requires that items procured through purchase order be received, installed, and tested prior to invoicing. With that said, we will have reached this point for many of our shelters, two of our towers and up to a dozen of our microwave radio connections allowing for invoicing of each. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | During the first quarter of 2011, the Commonwealth of Pennsylvania was able to continue to make progress. While we had a winter that brought significant snowfalls to many areas of Pennsylvania and a rainy start to spring, our crews have been able to continue to get into the sites and complete installations and upgrades. The only delay we experienced was the need to alter switching equipment chosen for the project due to a network card becoming discontinued. We have adjusted our purchase order accordingly and the first batch of new equipment has arrived at our vendor's warehouse. We expect that this equipment should begin to be installed within the second quarter of 2011. No significant delays were experienced. | One challenge anticipated within the second quarter of 2011 revolves around the weather and the effects that it has upon the ground surrounding our sites. Within the quarter we have planned multiple installations of towers and shelters which require large vehicles to deliver the equipment pieces to the site. With the melting snow and increased rain of spring, the ground is rather soft which makes movement of the trucks difficult as well as increasing the likelihood of causing damage to the dirt and stone covered roadways leading to each site. To mitigate any damage that our trucks may cause to the roadways, we have included line items in our purchase orders to repair any and all damage and return the roads to a condition that is as least as good as when we started the project, should any damage occur. This is customary for any roadways to sites that are either dirt or stone covered. These lines will only be use where necessary. Worth noting, the commonwealth has a strict policy of obtaining all goods and or services related to a specific line item of any of our procurements prior to payment of any invoice for such items. With that in mind, we must receive the good or service, have it tested for quality assurance purposes and sign off on a customer acceptance document in order for our vendor to invoice for the goods/services rendered. Once an invoice is received, it is paid within a thirty day period of time. The current direction from our Federal Program Officer is
NT10BIX5570017 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011, we completed the construction of the first of five new self supporting radio towers as well as the first five of a total ten shelters. We have completed additional microwave radio connection upgrades as well giving us a total of 21 completed by the close of the second quarter. Additionally, during the second quarter of 2011 we received the final Federal Aviation Administration approval allowing us to move forward with construction at one of our Lycoming County sites. We have adjusted our schedule to move this tower forward in the schedule due to its location in the network and the need to install both a shelter and a tower at this location and anticipate its construction to be completed within the third quarter. | 0 | 0 | 311 | 0 | 0 | 21 | 1 | 0 | No new network miles have been deployed | Our project does not include the leasing of network miles. | Our project has upgraded the microwave radios on a portion of the project network providing an additional 150 Mbps but have not upgraded the switching equipment on these miles to date. We will continue to progress on the roll out of microwave radio upgrades and expect to begin installation of the switching equipment by the close of the fourth quarter of 2011. While we trail the number of upgraded miles reported on our baseline report, we expect to begin closing that gap within the next quarter. | Our project does not include leased network. | Our project does not include fiber. | At this point in our project we have added 21 new microwave links capable of handling an additional 150 Mbps of traffic. | Our project includes five new self supporting towers. The construction of one new tower was completed within the second quarter of 2011. Construction of the second of these towers is currently in progress and expected to be completed within the third quarter. Construction on the remaining three towers is scheduled to take place within the third quarter of 2011 as well. | Interconnection points will be added to the network as the new customers and their needs are determined. We expect to begin offering broadband services as the initial segments of switching enabled bandwidth are completed to interested last mile providers or anchor institutions. | 0 | 0 | 0 | While we have not signed any agreements to date with wholesale or last mile providers, we have had discussions with various middle mile and last mile providers and are working toward determining exactly how the relationship will be structured between the Commonwealth of Pennsylvania and the last mile provider as well as logical points of interconnection between networks. We anticipate signing the first contract(s) within the third quarter of 2011. | Our current plan continues to be to offer Ethernet virtual circuits at 3, 6, 10, 20, and 50 Mb/s. Our pricing will be based upon Network Interface Access and number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports, best effort routing with route protection in backbone connections, and base price includes basic capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement includes tower site compound access but not tower space. | At this point in the project, the Commonwealth has not designated a third party to manage the available broadband services offered by our network. | 0 | 0 | 0 | 0 | We are still negotiating with our first wholesale/last mile provider and hope to have a signed agreement by the close of the third quarter. | No subscribers served with improved access at this point in the project. | Dark fiber is not included in this project. | At this point we are not serving subscribers but expect to begin doing so in the third quarter of 2011. | 0 | 0 | 0 | 0 | No subscribers served at this point in the project although we expect to sign our first subscribers onto the network by the end of the calendar year. | No subscribers served at this point in the project although we expect to sign our first subscribers onto the network by the end of the calendar year. | No subscribers served with improved access at this point in the project. | The actual speed tiers available and the number of subscribers for each will be determined at the time of our first subscriber's connection to the network. | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Due to the fact that our project is implemented by a Public Safety communications agency, we are considering offering discounted services to local public safety entities such as local fire, police and emergency response. | FALSE | Our network management practices have not changed. | During the third quarter of 2011, we will finish construction on the second of five new self supporting radio towers included within this project as well as initializing construction of the remaining three towers. Our project crew will continue to install microwave radio upgrades to the existing microwave connections and plan to begin the installation of the switching equipment as well. Additionally, during the third quarter, our project plans to bring on two additional people to manage the project. One will be an expert on the switching portion of the network while the other will be responsible for selling the bandwidth capacity created by our project to last mile providers and community anchor institutions. With these additional personnel, we hope to expand our work reaching out to the Community Anchor Institutions as well as last mile providers. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | One challenge that we have faced is in regard to the motors that run the generators that are contained within our new shelters. There are a limited number of manufacturers for these motors and many of them are located in Japan where they were affected by the earthquake and tsunami that occurred in March of 2011. We do not expect this to delay the project and are working through the issues by adjusting our installation schedule where necessary. | The only challenge we anticipated is in regard to acquiring customers for the network. Being a middle mile network, we are working to find the right partners to bring services to Pennsylvania's northern tier communities as well as community anchor institutions. This is a new business model for us and are working to find the right connections.
NT10BIX5570017 | 2011 | Q3 | Q3 - 2011 | Our project continues to progress on schedule with the completion of the construction of nine shelters and four of five new self supporting towers by the close of the quarter. The remaining tower's construction was slowed due to substantial rains that drenched the area in the month of September. Progress is expected to continue as soon as the resulting collection of water dissipates. We have continued to progress on our installation of upgraded microwave radio equipment and have completed a total of 32 of the total 71 microwave radio connections by the close of the quarter. We consider ourselves on schedule. | 0 | 0 | 473 | 0 | 0 | 32 | 4 | 0 | No new network miles have been deployed. | Our project does not include leased network. | Our project has upgraded the microwave radios on a significant portion of the network providing an additional 150 Mbps but have not upgraded the switching equipment on these miles to date. We will continue to progress on the roll out of microwave upgrades and expect to begin the installation of switching equipment by the close of the fourth quarter of 2011. While we trail the number of upgraded miles reported on our baseline report, we expect to begin closing that gap over the next two quarters. | Our project does not include leased network. | Our project does not include fiber. | As of the close of the third quarter, our project has installed a total of 32 new microwave links capable of handling an additional 150 Mbps of traffic. | Our project includes the construction of a total of five new self supporting radio towers. As of the close of the third quarter of 2011, we had finished the construction of four of those towers and completed a substantial amount of progress on the remaining tower which we expect to finish early in the fourth quarter. The remaining tower was scheduled to have been completed by the close of the third quarter; however, the substantial rains that hit Pennsylvania in September required us to delay completion of the final tower until the grounds surrounding the tower have a chance to dry a bit. We expect the last tower to be completed in early October. | Interconnection points will be added to the network as the new customers and their needs are determined. We expect to begin offering broadband services as the initial segments of switching enabled bandwidth are completed to interested last mile providers and/or anchor institutions. | 0 | 1 | 0 | While we have not signed any agreements to date with wholesale or last mile providers, we have had discussions with various middle mile and last mile providers and are working toward determining exactly how the relationship will be structured between the Commonwealth of Pennsylvania and the last mile provider as well as logical points of interconnection between networks. We anticipate signing the first contract(s) within the first quarter of 2012 but will be commencing a "pilot" project during the fourth quarter of 2011 which will give us a great deal of experience in building the connections and in our opinion, assist us in entering into agreements intelligently. | Our plan continues to be to offer Ethernet virtual circuits at 3,6,10,20, and 50 Mbps. Our pricing will be based upon Network Interface Access and number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports, best effort routing with route protection in backbone connections, and base price includes basic capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement includes tower site compound access but not tower space. As a result of the pilot project that we will be undertaking during the fourth quarter of 2011, we may alter the current plan. | At this point in the project, the Commonwealth has not designated a third party to manage the available broadband services offered by our network. | 0 | 0 | 0 | 0 | We are still negotiating with our first wholesale/last mile provider and hope to have a signed agreement by the close of the first quarter, 2012 as we will be embarking on a pilot project with that entity during the fourth quarter of 2011 and beyond. While our baseline report predicted that we would have a total of seven providers receiving new access by this point in the project, we remain at zero. | No subscribers served with improved access at this point in the project. While our baseline report predicted that we would have one wholesaler or last mile provider receiving improved access at this point in the project, we remain at zero. We anticipate making our first connection to a last mile service provider during the fourth quarter of 2011. | Dark fiber is not included in this project. | The actual speed tiers available and the number of subscribers for each will be determined at the time of our first subscriber's connection to the network. | 0 | 0 | 0 | 0 | No subscribers served at this point in the project although we anticipate the opportunity to sign our first subscribers onto the network by the end of the calendar year. Our baseline report predicted that we would have a total of eleven community anchor institutions connected to the network by this point in the project. We anticipate catching up to the baseline's predictions by finalizing an agreement involving multiple CAI's that we are pursuing at this time. | No subscribers served at this point in the project although we anticipate the opportunity to sign our first subscribers onto the network by the end of the calendar year. Our baseline report predicted that we would have eight subscribers receiving new access at this point in the project. We anticipate closing the current gap with the baseline report within the fourth quarter. | No subscribers served with improved access at this point in the project. Our baseline report predicted that we would have three subscribers receiving improved access at this point in the project. We anticipate closing the current gap with the baseline report within the fourth quarter. | The actual speed tiers available and the number of subscribers for each will be determined at the time of our first subscriber's connection to the network. | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | 0 | 0 | 0 | 0 | 0 | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Not addressed in this middle mile project. | Due to the fact that our project is implemented by a public safety communications agency, we are considering offering discounted services to local public safety entities such as local fire, police and emergency response. | FALSE | Our network management practices have not changed. | We anticipate the start of a WiMAX pilot project with a last mile provider to commence during the fourth quarter. This pilot project will enable our office the experience necessary to further our business with future customers as well as provide a "proof of concept" to potential subscribers. We anticipate that this project will allow us to sign the first last mile provider onto our network. We are also finalizing negotiations to bring multiple community anchor institutions onto the network as well. Until the negotiations are complete, we will not know how exactly many CAI's will be connected within the fourth quarter. Additionally we expect to complete construction on the last of five towers in the early part of the quarter allowing us to QC inspect the structures, approve and receive invoices for these items. This will close out one significant portion of our project that other portions were contingent upon. Our microwave installation will continue through the Thanksgiving holiday allowing us to complete an estimated total of 41 of the 71 microwave connections included in this project as well as closing a few rings in the design of the network. The closure of those upgraded rings allows us a re-rerouting capability within the network as well as an additional level of redundancy. We anticipate that the total number of miles completed as of the end of the fourth quarter will be 661.5 miles. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | During the third quarter of 2011, we discovered that we had some potential weaknesses in the network and worked to determine ways to reinforce the components of the network that would be susceptible to failure. We accomplished our goal but were forced to put the deployment of our switching equipment and service portal on hold until we were able to finalize the plans. The end result will be a stronger network. Additionally, we have been challenged with finding the right business partners for the capacity that our network will produce especially since this is a new business for our office to operate. In order to gain the experience that we are currently lacking, we have moved forward with the planning of a pilot project that will enable us to test the system as well as prove the ability of the network to deliver bandwidth to an end user. | We will be forced to halt microwave radio installations at our tower sites in the project after the Thanksgiving Day holiday due to the start of hunting season. This break in activity is built into the schedule so it shouldn't effect the progress of our project in a significant manner.
NT10BIX5570017 | 2011 | Q4 | Q4 - 2011 | As of Q4, 2011, the Commonwealth of Pennsylvania has completed 42 of the 71 microwave radio connections resulting in 656 miles of upgraded network. 100% of the new tower and shelter structures have been constructed on their respective sites. 100% of the compound expansions have been completed. Final engineering on the switching equipment was made within Q4 allowing for configuration and implementation to commence within Q1 and Q2. The Commonwealth of Pennsylvania began the selection process to hire an additional resource with technical networking knowledge in working with MPLS networks. We expect that the selected person will begin working on the project in Q1, 2012. The Commonwealth of Pennsylvania began development of an RFI (Request for Information) during Q4 to be implemented as a procurement tool to aid in connecting to last mile service providers in 2012 and beyond. The RFI will not only raise commercial awareness of the project but also encourage appropriate businesses to share information with the Commonwealth promoting potential business relationships. Final details were determined for a WiMax pilot project with a last mile service provider which will commence in Q1 2012. This WiMax pilot will provide significant understanding of the middle mile/last mile connectivity challenge facing us, and all BTOP middle mile infrastructure recipients. | 0 | 0 | 656 | 0 | 0 | 42 | 5 | 0 | No new network miles have been deployed. | n/a for this project | 42 of 71 microwave radio connections have been upgraded by the close of Q4. The project is on schedule. | n/a for this project | n/a for this project | Project is ahead of schedule with deployment of new microwave radio connections. | This indicator is complete. | Interconnection points will be added to the network as new customers and their requirements are determined. It is expected that the project will begin offering broadband services as the initial segments of switching enabled bandwidth are completed. | 0 | 1 | 0 | None at this time. Once the infrastructure build out and switching equipment installations are complete, the network will be available for sales of services. In the meantime, a Request for Information is being prepared for broadcast through the Commonwealth's procurement channels in order to raise awareness and foster communications with potential last mile service providers in Pennsylvania's un-served and under-served regions. We will commence a "pilot" project with a last mile service provider during Q1 of 2012 which is expected to assist in providing valuable experience in building the connections necessary to bring our middle mile capacity to the northern tier communities of Pennsylvania. | While services and pricing models are still in development, the plan continues to be to offer Ethernet virtual circuits at 3, 6,10, 20, and 50 Mbps. Pricing is expected to be based upon Network Interface Access and possibly the number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. Base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement is expected to include tower site compound access but not tower space. | At this time, the Commonwealth does not intend to utilize a third party to manage broadband middle mile services. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. No services have been offered to providers to date; however, a pilot project is planned within Q1 of 2012 with a last mile service provider. This pilot is expected to produce one of the first signed agreements. | Network infrastructure continues to be built. No services have been offered to providers to date; however, a pilot project is planned within Q1 of 2012 with a last mile service provider. This pilot is expected to produce one of the first signed agreements. | n/a dark fiber is not a part of the Commonwealth of Pennsylvania project | The actual speed tiers available as well as the number of subscribers will be determined at the time of the first connections to the network; however our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. We anticipate the first connections to be made within Q2, 2012. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within Q2, 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within Q2, 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within Q2, 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date; however our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. We anticipate the first connections to be made within Q2, 2012. | 0 | 0 | 0 | 0 | 0 | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | We noted on our application that we plan to offer discounts to Government and Public Safety organizations. | FALSE | Our network management practices have not changed. More information is publicly available on our website. | In Q1, 2012, we are on-schedule to complete an additional six microwave radio connections, taking the number of completed links to 48, or 67% of the total (71). This percentage completion far exceeds the expenditure metric at the same time and completes a total of 742 miles of microwave upgrades. Significant engineering on the MPLS switching portion of the project will also occur, enabling switching equipment installations in Q2, 2012. Also in Q1, 2012, we anticipate completion of the WiMax pilot project with a last mile service provider. This pilot will yield valuable experience with middle mile backhaul and will give this potential customer a first-hand and detailed understanding of our network's capabilities. We also expect to commence an additional pilot project with a government entity to provide middle mile capacity into some of the more remote regions of the state. These pilot projects are expected to yield the first signed agreements and bring the first one or two Community Anchor Institutions onto the network. Since we anticipate that our CAIs will be connected through a last mile provider, we believe that we will also have at least one agreement signed with a last mile provider by the end of the second quarter as well. Lastly, we will issue a Request for Information (RFI) in the first quarter, which will provide significant exposure to last mile providers (a large portion of our customer base) and begin a broad, non-discriminatory, sales process. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | Installation of the switching equipment was delayed due to engineering necessary to incorporate box redundancy at key locations in the network. While this slight change in equipment has delayed the roll out of MPLS on the network, it will allow for a significantly more robust and resilient infrastructure. The Commonwealth of Pennsylvania and its vendors have built cushions into the schedule for situations such as this. As a result, crews will be continuing to work during mild weather spells in Q1 where there was originally no work scheduled. We are currently in discussions with the Pennsylvania Utility Commission (PUC) to determine if our middle mile project connections can be made without becoming a certified telecommunications provider. | The weather will be key to progress attained during Q1, 2012 on the project due to the location in Northern Pennsylvania. While much of the work intended to be completed during the first quarter is engineering in nature, any opportunity to take advantage of mild weather will be used to advance the microwave radio installations.
NT10BIX5570017 | 2012 | Q1 | Q1 - 2012 | As of the close of Q1 2012, the Commonwealth of Pennsylvania has completed 51 of 71 microwave radio connections resulting in 800 miles of upgraded network. This is approximately 72% of the microwave equipment upgrades scheduled for the project. We have completed Quality of Service testing for the provisioning of the circuits within a test bed environment and created an implementation plan for the roll out of upgrades to our switching hubs. The implementation plan allows for the installation of switching equipment at all sites to follow within the second and third quarters of 2012. The Commonwealth of Pennsylvania added an additional resource to the project with a network technician skilled in MPLS technology during Q1. We continued work on our Request for Information and participated in multiple meetings with potential community anchor institutions as well as last mile service providers. We worked through line-of-sight technical difficulties for the WiMax leg of the project and neared the final configuration for this equipment. | 0 | 0 | 800 | 0 | 0 | 51 | 5 | 0 | No new network miles have been deployed. | N/A for this project. | 51 of 71 microwave radio connections have been upgraded as of the close of Q1, 2012. The project remains on schedule. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of new microwave radio connections. | This indicator is complete. | Interconnection points will be added to the network as new customers and their requirements are determined. Negotiations are ongoing with community anchor institutions and last mile service providers. We anticipate the first connections could take place within the second quarter. | 0 | 3 | 0 | At this date, we have not signed any agreements with wholesale or last mile providers; however, we are working with multiple entities and anticipate the confirmation of our first agreement within the second quarter. | While services and pricing models are still in development, the plan continues to be to offer Ethernet virtual circuits at 3, 6, 10, 20, and 50 Mbps. Pricing is expected to be based upon Network Interface Access and possibly the number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. Base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement is expected to include tower site compound access but not tower space. | At this point, the Commonwealth has not designated a third party to manage all or a portion of our network. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. The pilot has taken longer than expected due to line of sight challenges at the originally selected locations. | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. The pilot has taken longer than expected due to line of sight challenges at the originally selected locations. | N/A dark fiber is not a part of the Commonwealth of Pennsylvania project. | The actual speed tiers available as well as the number of subscribers will be determined at the time of the first connections to the network; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20, and 50 Mbps. We anticipate the first connections to be made within the second quarters of 2012. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the second or early third quarters of 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the second or early third quarters of 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the second or early third quarters of 2012 as a result of our pilot projects. | Network infrastructure continues to be built, and no services have been offered to providers to date; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. We anticipate the first connections to be made within the second or early third quarters of 2012. | 0 | 0 | 0 | 0 | 0 | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle-mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle-mile infrastructure project does not and will not connect to any businesses directly. | We noted on our application that we plan to offer discounts to Government and Public Safety organizations. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | During the second quarter of 2012, our team will complete an additional 5 microwave radio connections giving us a total of 857 miles of existing network miles upgraded. We anticipate completion of a significant portion of the switching equipment installation and configurations and that our switching hubs will be upgraded as well. Also scheduled for the second quarter is completion of the billing support system allowing us to generate invoices and adjust the criteria upon which the invoice is determined. During the second quarter we will be completing the assessments, tower analyses and path surveys to finalize multiple minor route changes that allow us to reach interested community anchor institutions. Due to challenges experienced with the vendor chosen for assistance with our business model, we expect to complete our Request for Information early in the second quarter which will assist us in getting information into the hands of last mile service providers. These last mile service providers, are expected to be the link between our project and Community Anchor Institutions connecting to the network. We anticipate connecting to two or more community anchor institutions near the end of the second quarter. We also anticipate signing our first agreement with a broadband wholesaler or last mile provider near the end of the second quarter. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | The business development portion of the project has been our most challenging. To help us, we hired a firm to research the business potential in our project area as well as to put together an information packet or "Request for Information" that we could send out to all appropriate entities. While working with this firm to develop the business and pricing structure, the consultant assigned to us fell seriously ill and ceased work on the project. The firm's other members stepped in to work towards completion of the project, but unfortunately did not possess the appropriate skill set forcing us to end the engagement. On the positive side, over the past several months, our team has gained enough experience to complete the work ourselves. | Much of the progress that our project plans to attain during the second quarter lies with switching equipment upgrades and configuration of that equipment. Project stakeholders and the schedule are very much on-schedule; therefore, we expect to not have any problem in exceeding our construction goals for the quarter. The Commonwealth continues to focus on securing end users/customers of the rural network, Community Anchor Institutions (CAI) in particular. We continue to focus on last mile providers, since they are the key to deploying broadband Internet in the project area. We have two agreeable LM providers working with us at this time.
NT10BIX5570017 | 2012 | Q2 | Q2 - 2012 | During the second quarter of 2012 our team completed an additional six microwave radio links for a total of 57 of 71 complete, resulting in 866 miles upgraded to date. We have six microwave radio links currently in progress accounting for an additional 98 miles soon to be completed. We have started the planning and testing phase prior to the deployment of our switching equipment and switching hub upgrades in anticipation of the roll out of this equipment to commence in the third quarter. We completed environmental assessments and submitted an award action request to program leadership requesting an adjustment to multiple sites within the broadband network. The proposed changes will make the network more sustainable and assist in reaching interested community anchor institutions and customers through a last mile provider. We have continued discussions with three last mile service providers and are working to resolve line of sight issues with one of them to kick off a pilot project proving the value of the network. | 0 | 0 | 866 | 0 | 0 | 57 | 5 | 0 | N/A for this project. No NEW network miles have been deployed. | N/A for this project. | 57 of 71 microwave radio connections have been upgraded as of the close of Q2, 2012. An additional 6 links are currently in progress. The project remains on schedule. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of upgraded microwave radio links. While we have completed 57 of the 71 links, an additional 6 are in progress as of the close of the second quarter and anticipated to be completed early in the third quarter. | This indicator is complete. | Interconnection points will be added to the network as new customers and last mile connection locations are determined. Negotiations are ongoing with community anchor institutions and last mile service providers. We anticipate the first connections to take place in the third quarter once the switching equipment is upgraded and last mile interconnection locations are finalized. | 0 | 3 | 0 | At this date, we have not signed any agreements with wholesale or last mile providers; however, we are working with multiple entities and anticipate the confirmation of our first agreements to coincide with the upgrade of our switching equipment which will occur largely in the third quarter. | While services and pricing models are still in development, the plan continues to be to offer Ethernet virtual circuits at 3, 6, 10, 20, and 50 Mbps. Pricing is expected to be based upon Network Interface Access and possibly the number of microwave connections between ports. Standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. Base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. Agreement is expected to include tower site compound access but not tower space. | At this point, the Commonwealth has not designated a third party to manage all or a portion of our network. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. The pilot has taken longer than expected due to line of sight challenges at the originally selected locations. | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. The pilot has taken longer than expected due to line of sight challenges at the originally selected locations. | N/A dark fiber is not a part of the Commonwealth of Pennsylvania project. | The actual speed tiers available as well as the number of subscribers will be determined at the time of the first connections to the network; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20, and 50 Mbps. We anticipate the first connections to be made once the MPLS switching upgrades have been completed within the third quarter. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built, and no services have been provided to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the third quarter of 2012 as a result of our pilot project as well as the upgrade of the switching equipment. | Network infrastructure continues to be built, and no services have been provided to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the third quarter of 2012 as a result of our pilot project as well as the upgrade of the switching equipment. | Network infrastructure continues to be built, and no services have been provided to date. It is anticipated that most, if not all community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected within the third quarter of 2012 as a result of our pilot project as well as the upgrade of the switching equipment. | Network infrastructure continues to be built, and no services have been offered to providers to date; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20, and 50 Mbps. We anticipate the first connections to coincide with the switching equipment upgrades in Q3. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | We noted on our application that we plan to offer discounts to Government and Public Safety organizations. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | During the third quarter of 2012, our project team intends to finalize testing and begin implementation of the switching equipment upgrades allowing for invoicing of not only switching equipment but also the services to install microwave radio equipment on a site by site basis. We anticipate receiving word that our requested route changes, submitted as an Award Action Request in June, are approved by project leadership, allowing us to move forward in upgrading multiple sites with broadband equipment. This adjustment to the project will allow us to reach interested community anchor institutions through multiple wholesale or last mile providers as well as become more sustainable by eliminating sites where there was little to no possibility of serving customers. We believe that we will have completed 65 of the original 71 links as the remaining six connections are expected to be changed as part of the requested route change. This progress will provide us with 984 miles of microwave network upgraded. We anticipate that we will have completed negotiations with two wholesale/last mile service providers and will be working toward providing service to them by the close of the quarter. Our first direct connections to Community Anchor Institutions are currently scheduled to occur just beyond the close of the third quarter with 10 to 14 connections anticipated. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | Due to the mountainous terrain of the northern tier of Pennsylvania, we have encountered various line of sight challenges that have prevented quick connections to a last mile provider. Through various engineering attempts, we believe that we have found a solution to the problem with our Pilot Project partner and at the current time, this last mile provider is working out the details to connect to our network. | Provided that the switching equipment installations and configurations along with the switching hub upgrades are completed without issue, we will have a successful quarter. Should issues arrive in the testing and /or implementation of these upgrades, our expenditures for many of the milestones will fall short of what has been predicted.
NT10BIX5570017 | 2012 | Q3 | Q3 - 2012 | During the third quarter of 2012 our team completed upgrades to an additional eight microwave radio links for a total of 65 of 71 complete, resulting in 984 miles upgraded to date. Of the remaining six connections, four of the links recently received approval through the NTIA's Award Action Request review process to change the original paths to more effectively reach potential customers and community anchor institutions. Due to the timing in receiving the approval, the completion of these links will occur early within the fourth quarter. The final two links, are also affected by a requested route change; however, they are still undergoing their environmental and historic preservation assessments. We anticipate receiving the results of the reviews within the fourth quarter for these final links and finishing the microwave upgrades in January of 2013, provided the NTIA approves these changes as well. These final two links will allow us to connect portions of Sullivan County into the network. During the third quarter, we proceeded with our switching equipment upgrades as scheduled. As of the end of the quarter, we continued to work through acceptance testing on the upgrades and anticipate completion of this task within the fourth quarter. With the completion of this portion of the project, we will be able to receive and make payment on multiple invoices for the installation of equipment allowing our project to show significant progress. We continue to work with three last mile service providers and anticipate finalizing agreements with them upon completion of the switching equipment upgrades. | 0 | 0 | 984 | 0 | 0 | 65 | 5 | 0 | N/A for this project. There are no NEW network miles included in this project. | N/A for this project. | We have completed 65 of 71 microwave radio connection upgrades on the network by the close of the third quarter. The project remains on schedule. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of upgraded microwave radio links. We have completed 65 of the 71 links and have started to work on the links recently approved through the award action request. | This key program indicator is complete. | Interconnection points will be added to the network as new customers and last mile connection locations are determined. Negotiations are ongoing with community anchor institutions and last mile service providers. We anticipate the first connections will take place shortly after the switching equipment is upgraded and last mile interconnection locations are finalized. Due to a longer than expected time to deploy the switching equipment, we believe that our interconnection points will be added to the network during the fourth quarter. | 0 | 3 | 0 | As of the close of the third quarter, we have not signed any agreements with wholesale or last mile service providers; however, we are working with multiple entities and anticipate that as soon as we are able to complete our switching equipment upgrades, those providers will finalize the agreements and connect to our network. Due to the longer than anticipated switching equipment deployment, we now believe that these agreements will be finalized in the fourth quarter. | While services and pricing models are still being developed, we intend to offer Layer 2 MPLS Ethernet back haul that is not distance dependent. We intend to charge $45 per month for each physical port or router connection plus additional fees as noted below. The MPLS Ethernet back haul will be offered in many different data rate increments (0.25Mbps, 0.5Mbps, 1.5Mbps, etc.) but all of them average approximately $50/Mbps. A burstable data rate is available for circuits greater than 2Mbps. The monthly charges for these circuits would adjust as follows. A 5Mbps service at $250/month without burst, would increase to $350/month for 10% burst, and $450/month for 20% burst, and so on. We intend to charge the following non-recurring charges: administrative setup fee of $100; network setup fee of $200; and physical setup fee at the remote site of $450. Customers will be allowed to adjust data rates within the term of the contract provided that there is a minimum of 1 month between changes. Each change requires a 2-week advance notice. We will offer our customers access to the compound and space on an elevated, external platform for the placement of their own weather-proof equipment cabinet. We will offer customers a 10% discount off of the total price when committing to a 2-year term, or 25% off of the total price for a 3-year term. | At this point, the Commonwealth has not designated a third party to manage all or a portion of the network. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. We anticipate agreements to be signed upon completion of the switching equipment deployment. | Network infrastructure continues to be built. No services have been offered to providers to date; however, we have been finalizing plans on a pilot project. We anticipate agreements to be signed upon completion of the switching equipment deployment. | N/A. Dark fiber is not a part of the Commonwealth of Pennsylvania project. | The actual speed tiers available as well as the number of subscribers will be determined at the time of the first connections to the network; however, our baseline indentified that we would offer our customers Ethernet virtual circuits at 10, 20, and 50 Mbps. We anticipate the first connections to be made once the MPLS switching upgrades have been completed. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. No services have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed. | Network infrastructure continues to be built. No services have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed. | Network infrastructure continues to be built. No services have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed. | Network infrastructure continues to be built. No services have been offered to providers to date; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. We anticipate the first connections to coincide with the completion of our switching equipment upgrades. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | We noted on our application that we may offer discounts to Government and Public Safety organizations. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | During the fourth quarter of 2012, our team intends to complete the switching equipment upgrades. With the completion of this portion of our project, we will then be able to finalize the agreements we have been negotiating with last mile providers and begin to provide service to Community Anchor Institutions within the northern tier of Pennsylvania. We anticipate connection to as many as seven Community Anchor Institutions within the fourth quarter and additional connections to follow in January. With the NTIA's approval of our recent route change, we plan to complete these four links of microwave radio upgrades giving us a total of 69 of the 71 connections complete and a total of 1035 miles of upgraded network. The remaining two links are affected by an additional route change which will allow us to reach Sullivan County. This route change will be submitted within the fourth quarter, upon completion of the environmental and historic preservation assessment for the sites involved in the change. Installation of the equipment would be planned for January of 2013. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | The acceptance testing for the switching equipment has taken longer than originally anticipated; however, we still believe that the work will be completed prior to the close of the fourth quarter. Additionally, the time involved in acquiring approval for our route changes took significantly longer than we had anticipated creating a multiple month period of time where our crews were unable to work on microwave equipment installations. | Our successful completion of this project currently relies upon a few more months of cooperative weather as well as a quick turn around on the final award action request for a route modification. The northern tier of Pennsylvania typically begins to experience snowy conditions as early as November which may hamper our efforts to complete the final installations of equipment at the last remaining tower sites. We will also need the BTOP management to move through the review of our route modification request as quickly as possible so that we will still have enough time to reach the intended community anchor institutions within Sullivan County.
NT10BIX5570017 | 2012 | Q4 | Q4 - 2012 | During the fourth quarter of 2012, we were able to complete the upgrades to four additional microwave radio links for a total of 69 of 71 complete and 1,035 miles of upgraded network. The final two links are affected by a route change that we intend to submit to the NTIA upon completion of the environmental and historic preservation assessments. We anticipate receiving the results of the reviews within the first week of the first quarter of 2013. These last two links will allow us to connect to portions of Sullivan County. During the quarter, we were able to complete the acceptance testing on the switching equipment portion of the network. This accomplishment will allow for a substantial increase in our progress upon receipt and payment of the associated invoices, likely within the first quarter of 2013. We continue to work with three last mile service providers and anticipate finalizing agreements with them now that the switching equipment upgrades are complete. During the quarter, we began a pilot project to test TV White Space equipment and its ability to navigate the terrain in Northern Pennsylvania. We continue to reach out to interested community anchor institutions and are working toward connection with at least six of these institutions currently. | 0 | 0 | 1035 | 0 | 0 | 69 | 5 | 2 | N/A for this project. There are no NEW network miles included in this project. | N/A for this project. | We have completed 69 of the 71 microwave radio connection upgrades on the network by the close of the fourth quarter. The project remains on schedule. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of upgraded microwave radio links. We have completed 69 of the 71 links and will be submitting an award action request for the final two early in the first quarter of 2013. | This key program indicator is complete. | We have added two interconnection points to the network during the fourth quarter of 2012 through two different last mile service providers. The agreements with these providers are nearing completion and are expected to be completed within the first quarter of 2013. Our baseline stated that we would have significantly more connections at this point in the project; however, there are only 17 fixed wireless last mile providers in the state and only a portion of these fall within project's footprint. | 0 | 3 | 0 | While we have not finalized agreements with the last mile providers that we have been in negotiations with, we have physically connected to two providers and eagerly await the signed agreements that will allow traffic to begin flowing through the links. We continue to negotiate with an additional provider and hope to finalize an agreement with this provider within the first quarter of 2013 as well. | While services and pricing models are still being developed, we intend to offer Layer 2 MPLS Ethernet back haul that is not distance dependent. We intend to charge $45 per month for each physical port or router connection plus additional fees as noted below. The MPLS Ethernet back haul will be offered in different data rate increments with all of them averaging $50/Mbps. A burstable data rate is available for all circuits with monthly charges that would adjust as follows. A 5Mbps service at $250/month without burst, would increase to $350/month for 10% burst, and $450/month for 20% burst, and so on. We intend to charge the following non-recurring charges: administrative setup fee of $100; network setup fee of $200; and physical setup fee at the remote site of $450. Customers will be allowed to adjust data rates within the term of the contract provided that there is a minimum of 1 month between changes. Each change requires a 2-week advance notice. We will offer our customers access to the compound and space on an elevated, external platform for the placement of their own weather-proof equipment cabinet. We will offer customers a 10% discount off of the total price when committing to a 2-year term, or 25% off of the total price for a 3-year term. | At this point, the Commonwealth has not designated a third party to manage all or a portion of the network. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. Only services to test the connections to last mile service providers have been provided to date. We anticipate agreements to be signed upon completion of the switching equipment deployment. | Network infrastructure continues to be built. Only services to test the connections to last mile service providers have been provided to date. We anticipate agreements to be signed upon completion of the switching equipment deployment. | N/A. Dark fiber is not a part of the Commonwealth of Pennsylvania project. | The actual speed tiers available as well as the number of subscribers will be determined at the time of the first connections to the network; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20, and 50 Mbps. We anticipate the first connections to be made once the MPLS switching upgrades have been completed and agreements are finalized. | 0 | 0 | 0 | 0 | Network infrastructure continues to be built. Only services to test the connections to last mile service providers have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed and agreements are finalized. | Network infrastructure continues to be built. Only services to test the connections to last mile service providers have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed and agreements are finalized. | Network infrastructure continues to be built. Only services to test the connections to last mile service providers have been provided to date. It is anticipated that most, if not all, community anchor institutions that connect will be reached through a last mile service provider. We anticipate that the first community anchor institutions will be connected as soon as our switching equipment upgrades are completed and agreements are finalized. | Network infrastructure continues to be built. No services have been offered to providers to date; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. We anticipate the first connections to coincide with the completion of our switching equipment upgrades. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | We intend to offer customers a 10% discount off of the total price when committing to a 2-year term and 25% off of the total price for a 3-year term. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | During the first quarter of 2013, we anticipate the completion of our last two links of microwave giving us a total of 71 of 71 complete and 1,064 miles of upgraded network. The completion of the last two links is dependent upon approval of the route change submitted to the NTIA in early January and will allow us to reach multiple Community Anchor Institutions in need of affordable service in Sullivan County. Additionally, we intend to complete the connections to six state police stations giving us our first Community Anchor Institutions on the network. We anticipate finalizing agreements with three last mile service providers and physically connecting with all three by the quarter's end. Significant outreach will occur within the first quarter to facilitate negotiations with interested Community Anchors and determine where our next connections will happen. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | The acceptance testing of our switching equipment upgrades took longer than anticipated; however, we were able to wrap it up by the middle of December. During this testing we found instances were the network did not behave as originally expected and as a result have determined that a lab must be built to test any software upgrade prior to installation on the live network. | The Commonwealth of Pennsylvania, as stated in previous reports, requires vendors to provide goods and/or services prior to the payment of invoices. With the percent of progress complete being based upon expenditures alone, our payment process causes our percent of progress to trail the actual physical completion of work. As a result, much of the work completed by the close of January, may not be invoiced and paid until March or April of 2013.
NT10BIX5570017 | 2013 | Q1 | Q1 - 2013 | During the first quarter of 2013, we completed the environmental assessment and historic preservation review for the sites that will take our network into Sullivan County. Our project remains at 69 of 71 microwave radio connections completed to date. The remaining two links are located in Lycoming and Sullivan counties which received significant snowfall during the first quarter preventing tower crews from accessing the sites. These two remaining links are now scheduled to be completed in May of 2013 once the snow has melted and the winds have calmed. With the completion of the switching equipment acceptance testing late in the fourth quarter, we received and paid over $9M in invoices for equipment and services within the first quarter. We continue to work with two last mile providers to connect community anchor institutions to our network and have finalized an agreement for our working relationship. Formal contracts remain to be signed with these entities that define the term and pricing of services provided. The pilot project to test TV White Space equipment in the northern tier of Pennsylvania has ended without the success that we had hoped for. The vendor that we were working with was not able to resolve software issues leaving us unable to move forward. We successfully connected directly to 4 community anchor institutions during the first quarter and aggressively surveyed, planned and designed the remaining last-mile solutions. | 0 | 0 | 1035 | 0 | 0 | 69 | 5 | 69 | N/A for this project. There are no NEW network miles included in the project. | N/A for this project. | We have completed 69 of the 71 microwave radio connection upgrades on the network by the close of the first quarter. This is no change from the previous quarter. The remaining two links will be completed during the spring season, once the snow and ice melt and the winds die down. The project remains on schedule. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of upgraded microwave radio links. We have completed 69 of the 71 links to date with the final two scheduled for early in the second quarter of 2013. | This key program indicator is complete. | We have added two internet gateways to the network through two different last mile service providersâ€“ one in the middle of the networkâ€™s footprint (KCnet), and the other at the western end (North Central). The actual nodes of the network are, literally, points of interconnection and this quarter the 69th node became operational. | 2 | 0 | 0 | Currently we have signed agreements with two last mile providers within the norther tier of Pennsylvania: KCNet of Lockhaven, Pennsylvania and North Central Regional Planning and Development Commission of Ridgway, Pennsylvania. | We are offering Layer 2 MPLS Ethernet back haul that is not distance dependent, does not incur a per-hop charge, and is straightforward in price and application. The pricing plan contractually agreed-to with our two last mile providers is a revenue share, with the larger proportion of the share going to the last mile provider. Our two last mile providers will be allocated whatever bandwidth they require. Todayâ€™s optimistic estimates are <50Mbps for each. Should a retail customer need only data backhaul (no Internet), we will sell to them directly and anticipate $45 per month per physical port plus backhaul averaging $50/Mbps. This generic MPLS Ethernet back haul will be offered in data rate increments; 1.5/3/10/20Mbps. These speed tiers are burstable with monthly charges adjusting based upon the percentage burst. For example, a 5Mbps service at $250/month wanting a 50% burst (to 7.5Mbps) would incur a 10% fee increase; a 100% burst increase (to 10Mbps) would incur a 25% fee increase. We will enact non-recurring charges such as administrative setup fee of $100; network setup fee of $200; and physical setup fee at the remote site of $450. Customers will be allowed to adjust data rates within the term of the contract provided that there is a minimum of 1 month between changes. Each change requires a 2-week advance notice. We will offer customers a 10% discount off of the total price when committing to a 2-year term, or 25% off of the total price for a 3-year term. | At this point, the Commonwealth has not designated a third party to manage all or a portion of the network. | 0 | 2 | 0 | 2 | We have not signed agreements with wholesalers or last mile providers who are receiving new access. | We have connected to two last mile service providers. Each provider will be expanding their area of service through the use of our network. | N/A. Dark fiber is not a part of the Commonwealth of Pennsylvania project. | We have connected to two last mile internet service providers. We have allowed them to tell us what speeds they need instead of making them choose from what we chose to make available. At this point, we have provisioned 2 Mbps and 5 Mbps services. | 4 | 0 | 4 | 4 | We have connected four Pennsylvania State Police (PSP) stations to our broadband network within the first quarter of 2013. | The CAIs that we connected to the network are not receiving new access. | The CAIs that we have connected directly to the network are receiving improved access through our project that also serves as a redundant path to the connection that was in place. | The four PSP stations that we connected to our network within the first quarter are each capable of receiving 40 Mbps. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | We intended to offer customers a 10% discount off of the total price when committing to a 2-year term and 25% off of the total price for a 3-year term. As we connected last mile service providers to the network, the actual agreements to date have turned out to be for significantly longer periods of time. The contracts, currently in the signature process with our two last mile providers, are actually for twenty years with an ten year renewal option. We will offer our customers access to the compound and space on an elevated, external platform for the placement of their own weather-proof equipment cabinet. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | During the second quarter of 2013, we are scheduled to complete the last two microwave radio connections which will take our services into Sullivan County. This accomplishment will also take our number of upgraded miles to 1,064 and the number of links complete at 71 of 71. Our outreach into the northern tier will continue to investigate and facilitate connections to community anchor institutions and un-served/under-served residential areas. Specifically for CAIs, we project the following new connections: +3 Sullivan County government; +2 Cameron County government; +1 state park in Potter County; +1 public television station in Clearfield County; +1 critical care facility in McKean County. These projected 8 new CAI connections raise the total projected Q2 cumulative CAI total to 12. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | Due to the significant snowfall in the northern tier of Pennsylvania during the winter months, our crews were unable to get into many of our remote tower sites including the sites in Lycoming and Sullivan counties to complete the last two microwave radio connections. As the warmer temperatures of Spring move into Pennsylvania, we anticipate the snow will melt quickly and access will be restored. Our crews will complete these installations as quickly as the site and wind conditions allow for a tower climber to safely scale the structures. The steep and tree-covered terrain of rural Pennsylvania continues to prove difficult for clear line-of-sight last-mile wireless solutions. GIS analysis might predict â€œcloseâ€ line of sight, but only through manual investigation can actual radio frequency propagation be determined. In several instances, we will utilize 900MHz for fixed wireless last mile because it can penetrate up to Â¼-mile of foliage obstruction. However, more potential CAIs have not materialized due to impenetrable foliage or actual ground obstruction.â€ | During the second quarter of 2013, we will be evaluating the upgraded broadband network with an "end to end" test. This testing is designed to ensure that the network and its components operate reliably and in a manner that is to be expected. Should any components of this test not produce the results that are expected, it will delay final payment.
NT10BIX5570017 | 2013 | Q2 | Q2 - 2013 | During the second quarter, work began on the final two microwave backbone upgrades which will allow the project to reach into Sullivan County. Currently at 69 of 71 links complete, these final two connections will complete the network back bone and allow for connection to an additional 15 CAIs within Sullivan County. Our broadband services manager continued to work with the connected last mile internet service providers to determine any and all connections capable of being completed within the remaining award period. During the quarter, our broadband services manager met with Sullivan County executives to discuss specific technology initiatives. He also met with Cook State Forest park personnel and local businesses to discussing the broadband offering. In June, he met with staff from the Abraxas School and treatment facility to discuss what we could do to resolve their high speed internet challenges. He also met with the Wayne County Commissioners and their staff to discuss the development of broadband in their county. During the quarter, an additional 23 CAIs were added to the network. Area Transportation Authority, a community support organization in Bradford, McKean County, connected to the network during the second quarter. The Cameron County Courthouse building in Emporium was also connected to the network. Within the courthouse, a total of 22 government and public safety agencies reside. Network clean-up and planning for a final "end to end" test of the system continued through the quarter with the final test currently scheduled for July. During the quarter, no additional requests were received for interconnection from Internet Service Providers in the northern tier. | 0 | 0 | 1035 | 0 | 0 | 69 | 5 | 69 | N/A for this project. There are no NEW network miles included in the project. | N/A for this project. | We have completed 69 of the 71 microwave radio connection upgrades on the network. Work is underway for the final two connections. Work on the final two links is expected to be completed within the month of July. | N/A for this project. | N/A for this project. | The project is on schedule with the deployment of upgraded microwave radio links. We have completed 69 of the 71 links to date with the final two currently in progress and scheduled for completion in July. | This key program indicator is complete. | The project currently contains 69 upgraded nodes, each of which can be used as a point of interconnection. There are internet gateways to the network through two last mile service providers located at the western and middle portions of the network. | 2 | 0 | 80 | We have signed agreements with two last mile service providers within the northern tier of Pennsylvania: KCNet of Lock Haven, Pennsylvania and North Central Regional Planning and Development Commission of Ridgway, Pennsylvania | We are offering Layer 2 MPLS Ethernet back haul that is not distance dependent, does not incur a per-hop charge, and is straightforward in price and application. The pricing plan contractually agreed-to with our two last mile providers is a revenue share, with the larger proportion of the share going to the last mile provider. Our two last mile providers will be allocated whatever bandwidth they require. Todayâ€™s optimistic estimates are <50Mbps for each. Should a retail customer need only data backhaul (no Internet), we will sell to them directly and anticipate $45 per month per physical port plus backhaul averaging $50/Mbps. This generic MPLS Ethernet back haul will be offered in data rate increments; 1.5/3/10/20Mbps. These speed tiers are burstable with monthly charges adjusting based upon the percentage burst. For example, a 5Mbps service at $250/month wanting a 50% burst (to 7.5Mbps) would incur a 10% fee increase; a 100% burst increase (to 10Mbps) would incur a 25% fee increase. We will enact non-recurring charges such as administrative setup fee of $100; network setup fee of $200; and physical setup fee at the remote site of $450. Customers will be allowed to adjust data rates within the term of the contract provided that there is a minimum of 1 month between changes. Each change requires a 2-week advance notice. We will offer customers a 10% discount off of the total price when committing to a 2-year term, or 25% off of the total price for a 3-year term. | At this point, the Commonwealth has not designated a third party to manage all or a portion of the network. | 0 | 2 | 0 | 2 | We have not signed agreements with wholesalers or last mile providers who are receiving new access. | We have connected to two last mile service providers. Each provider will be expanding their area of service through the use of our network. | N/A. Dark fiber is not a part of the Commonwealth of Pennsylvania project. | We have connected to two last mile internet service providers. We have allowed them to tell us what speeds they need instead of making them choose from what we chose to make available. At this point, we have provisioned 2 Mbps and 5 Mbps services. | 27 | 0 | 27 | 3 | We have connected four Pennsylvania State Police (PSP) stations, 22 offices within Cameron County Courthouse and the Area Transit Authority in Bradford, McKean County. | The CAIs that we connected to the network are not receiving new access. | All of the CAIs that we have connected to the network are receiving improved access. | Four of the community anchor institutions that have connected to the network are each capable of receiving 40 Mbps. The remaining 23 CAIs are each capable of receiving 2 - 5 Mbps services. The actual service will be determined upon subscription. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | We intended to offer customers a 10% discount off of the total price when committing to a 2-year term and 25% off of the total price for a 3-year term. As we connected last mile service providers to the network, the actual agreements to date have turned out to be for significantly longer periods of time. The contracts are actually for twenty years with a ten year renewal option. We will offer our customers access to the compound and space on an elevated, external platform for the placement of their own weather-proof equipment cabinet. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | Next quarter, we plan to finish up the links to all remaining community anchor institutions to be connected to our project during the award period. Currently we plan to connect 14 Community Anchor Institutions within the Sullivan County Courthouse as well as the Sullivan County Emergency Resource Communication Center (ERCC) during the third quarter. We plan to also connect a critical care facility in Clinton County as well as a public safety facility in McKean County. We are also working to connect state parks within Potter and Clarion counties, a community support organization in Elk County and a public TV station in Clearfield County. Should all of the work to connect these listed CAIs be completed within the award period, it will total an additional 21 CAIs for the project bringing our total to 48. We also plan to fully test the network with an end to end test intended to put the network through multiple scenarios to ensure it operates as expected. Upon successful completion of the final testing of the system, we will be able to close out multiple purchasing documents on the project. During the next quarter we will also complete the final two links of the microwave backbone taking the project to 71 of 71 complete and 1,064 miles of network upgraded. We have presentations planned at the North-Central Regional Planning and Development Commission's semi-annual members meeting as well as the Area Transportation Authority's annual meeting. No additional last mile providers are expected to connect to the network within the remainder of the award period; however, any requests that are received will be considered. We anticipate receipt of the first program income for the network within the third quarter of 2013. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | The steep and tree-covered terrain of rural Pennsylvania continues to prove difficult for clear line-of-sight last-mile wireless solutions. GIS analysis might predict â€œcloseâ€ line of sight, but only through manual investigation can actual radio frequency propagation be determined. In several instances, we will utilize 900MHz for fixed wireless last mile because it can penetrate up to Â¼-mile of foliage obstruction. However, more potential CAIs have not materialized due to impenetrable foliage or actual ground obstruction. | During the month of July, we will be evaluating the upgraded broadband network with an "end to end" test. This testing is designed to ensure that the network and its components operate reliably and in a manner that is to be expected. This testing will prove that the network works as it was engineered.
NT10BIX5570017 | 2013 | Q3 | Q3 - 2013 | During the third quarter, work was completed on the final two microwave backbone sites reaching into Sullivan County. Upon completion of these links, we were able to connect the Sullivan County Courthouse building in Laporte and Emergency Resource Communication Center (ERCC) two miles outside of town. Within the courthouse, a total of 14 government and public safety agencies reside. Area Transportation Authority, a community support organization in Johnsonburg, Elk County, connected to the network during the third quarter as well as the primary transmitter site of Penn State Public Broadcasting (WPSU) in Clearfield. Penn State Public Broadcasting is a PBS station providing educational and instructional programming to central Pennsylvania. We also connected a Pennsylvania Game Commission Office in Lycoming County and two State Park Offices (Cook Forest State Park and Cherry Springs State Park) in Cooksburg and Galeton respectively. Network clean-up and a final "end to end" test of the system were successfully performed within the quarter. The completion of these tasks signify the network reaching operational status. Our broadband services manager continued to work with the connected last mile service providers to determine and connect interested institutions within the project footprint and will continue to do so into the foreseeable future. During the quarter, a total of 20 CAIs were added to the network. No additional requests were received for interconnection from Internet Service providers in the northern tier. Through the BTOP grant, Pennsylvania's project was able to provide broadband services to state and local government agencies in remote locations enabling their employees to achieve increased productivity and improved reliability while the agencies realized significant cost savings. Various utilities and business as well as residents will also benefit through the local internet service providers that we connected to the network. Due to Public Utility Commission (PUC) regulations our project was prevented from connecting directly to residents or businesses. As a result, the relationships built with two Internet Service Providers (ISPs) proved to be invaluable. Through these ISPs, we reached four remote Marcellus Shale gas producing facilities allowing them to increase productivity and lower costs. We were able to provide services to a regional bus facility, public television station and a lodge/conference center that previously could only obtain broadband through a satellite connection. These facilities are all receiving improved reliability, increased capacity and lower cost for their broadband connection. The ISPs that connected to our network also are now capable of serving residential customers in seventeen communities within the northern tier as a result of our project. Multiple public safety agencies in Pennsylvania are also reaping the benefits of the increased availability of broadband in the northern tier of Pennsylvania. Four Pennsylvania State Police locations have been connected to the network as well as a public safety answering point within Sullivan County providing for increased reliability and capacity. Pennsylvania's state and local officials have taken an interest in rural broadband and understand its importance as well as the relevance of the network that has been improved as part of the BTOP project. | 0 | 0 | 1064 | 0 | 0 | 71 | 5 | 71 | N/A for this project. There are no NEW network miles included in the project. | N/A for this project. | This key program indicator is complete. | N/A for this project. | N/A for this project. | This key program indicator is complete. | This key program indicator is complete. | The project currently contains 69 upgraded nodes, each of which can be used as a point of interconnection. There are internet gateways to the network through two last mile service providers located at the western and middle portions of the network. | 2 | 0 | 60 | We have signed agreements with two last mile service providers within the northern tier of Pennsylvania: KCNet of Lock Haven, Pennsylvania and North Central Regional Planning and Development Commission of Ridgway, Pennsylvania. One of the providers has signed a 10 year agreement while the other has signed a 20 year agreement. | Our network offers Layer 2 MPLS Ethernet backhaul that is not distance dependent and does not incur a per-hop charge. Our two wholesale last mile providers (ISPs) will be allocated bandwidth as needed (best effort). If a retail customer requests data backhaul (no internet), we will sell to them directly at an average of $50/Mbps. This generic MPLS Ethernet backhaul will be offered in different rate increments, and many different combinations of committed and best-effort Quality of Service. A pricing plan is attached. | At this point, the Commonwealth has not designated a third party to manage all or a portion of the network. | 0 | 2 | 0 | 2 | We have not signed agreements with wholesalers or last mile providers who are receiving new access. | We have connected to two last mile service providers. Each provider will be expanding their area of service through the use of our network. | N/A. Dark fiber is not a part of the Commonwealth of Pennsylvania project. | We have connected to two last mile internet service providers. We have allowed them to tell us what speeds they need instead of making them choose from what we chose to make available. At this point, we have provisioned 2 Mbps and 5 Mbps services. | 47 | 0 | 47 | 3 | We have connected four Pennsylvania State Police (PSP) stations, 22 offices within Cameron County Courthouse, 14 offices within Sullivan County Courthouse, the Emergency Resource Communication Center (ERCC), the Area Transit Authority in McKean County as well as Elk County, a public TV station in Clearfield County, a Game Commission site in Lycoming County and two State Park Offices in Forest County and Potter County. | The CAIs that we connected to the network are not receiving new access. | All of the CAIs that we have connected to the network are receiving improved access. | Four of the community anchor institutions that have connected to the network are each capable of receiving 40 Mbps. Three of the CAIs are capable of receiving 10 Mbps services. The remaining CAIs are each capable of receiving 5 Mbps services. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | N/A. This middle mile infrastructure project does not and will not connect to any residence or households directly. | 0 | 0 | 0 | 0 | 0 | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | N/A. This middle mile infrastructure project does not and will not connect to any businesses directly. | Two agreements have been executed with each ISP because our actual relationship involves broadband service and physical access to a tower site. Each ISP has a Wireless Broadband Service Level Agreement and a Site License Agreement. Broadband Service specifies the revenue share, best-effort bandwidth, or 25% off of the total price for a 3-year term. The Site License specifies such items as compound access, snow removal and maintenance, equipment maintenance, space on the elevated platform for their equipment cabinet, etc. | FALSE | Our network management practices have not changed. Additional information is publicly available on our website. | Our project will have entered the closeout period. Nonetheless, our broadband services manager will continue to connect customers to the network in an effort to close the digital divide in northern Pennsylvania. The significant project accomplishments occurring within the period will be the receipt and payment of all remaining invoices. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | During the quarter our vendors encountered various delays in acquiring equipment, specifically access points, allowing for connection to rural Internet Service Providers (ISP's). Additionally the late summer time frame found the tower construction industry and their climbers in the busiest time of the year making the scheduling of work to install antennas difficult. | No issues identified.
NT10BIX5570018 | 2010 | Q3 | Q3 - 2010 | Completion of contract negotiations for acquisition of submarine cable capacity (FAC) for Puerto Rico-Florida span. Design of copper and optical infrastructure, emergency power & fire suppression systems for PRBI facilities. Engineering planning for FAC acceptance, network activation, provisioning, operations & management of Layer 2 & 3 services. Completed the procurement selection process for core routing/bridging equipment for PR-Florida span, as well as for emergency power, fire suppression, data center facility infrastructure, data management and storage systems. Purchase orders have been issued. Ongoing negotiations with broadband providers and community anchor institutions on interconnection agreements. Identification of Steering Committee candidates. Project Foreman, Project Coordinator, and Network Technician recruitment completed. Meetings with strategic contacts at Community Anchor Institutions for project presentation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 13 | 0 | Final agreements are currently being negotiated. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 0 | 0 | 0 | no variance from baseline | no variance from baseline | no variance from baseline | Services will be available from 100Mbps-1Gbps. | 0 | 0 | 0 | 0 | no variance from baseline | no variance from baseline | no variance from baseline | Services will be available from 100Mbps-1Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government agencies; and broadband providers. | FALSE | N/A | We anticipate the completion of acquisition, acceptance and expenditure of funds associated with the submarine cable capacity (FAC) for the Puerto Rico-Florida span next quarter. This expenditure is significant, and explains why we have projected 99% completion of the Network Build milestone. We also anticipate the execution of various interconnection agreements with broadband providers and community anchor institutions. PR-Florida span equipment will be received & deployed. PR-Florida span will begin testing phase. | Critical Hub Networks, Inc | Delays in recruitment/employee start date caused some delays in network design and site preparation tasks. The recruitment delays were a result of challenges encountered in finding qualified candidates and coordinating the selected employees commencement dates. We do not foresee any significant delays which would impede ongoing network design and site preparation, and we anticipate the commencement of additional staff in Q4 to accelerate Network Design, Site Preparation and Equipment Deployment going into Phase II of the wireless buildout of the project. We are awaiting the receipt of core network equipment, which was originally schedule for delivery this quarter but has been delayed to next quarter. While this represents a significant variance from the baseline, we had not planned any procurement for the next quarter, which will allow for us to receive the equipment and get back on schedule without affecting the scheduled completion date. | Weather: In the event that any adverse weather conditions impact either Puerto Rico or Miami, the project progress may be delayed and/or otherwise affected. Supplier/Vendor Deliverables: If any external supplier/vendor incurs delays in fulfilling their obligations, such as equipment delivery or service activation, the project schedule may be delayed. Contingency plans are in place to ensure overall project completion within the project timeframe.
NT10BIX5570018 | 2010 | Q4 | Q4 - 2010 | During the previous quarter, the PRBI project activities included: (a) Backbone Activation: Activation of submarine cable capacity (FAC) for the Puerto Rico-Florida span. Network testing currently underway. (b) Engineering Design Implementation: Commencement of implementation of copper and optical infrastructure at PR-NAP and MIA-NAP, PRBI facility preparations including emergency power and fire suppression systems, network activation, provisioning, operations & management of Layer 2 & 3 services. (c) Interconnection Agreements: Execution of interconnection agreements with broadband providers. Ongoing negotiations with other broadband providers, government agencies and community anchor institutions on interconnection agreement for peering and transit. Ongoing negotiations of peering agreements with network & content providers in MIA-NAP. (d) Steering Committee: Invitation of candidates to PRBI Steering Committee. Awaiting response from government representatives. Seeking nonprofit candidate. (e) Employee Recruiting: Project System Administrator was recruited. Employee recruiting is ongoing. (f) Provisioning: Commencement of provisioning of interconnections with broadband provider networks. All broadband providers invited to assist with network testing. Official service launch and activation anticipated for next quarter. (g) Collaboration with ARRA projects and Community Anchor Institutions: Ongoing talks with other ARRA recipients regarding project synergies, interconnectivi | 0 | 3901 | 0 | 0 | 3901 | 0 | 0 | 2 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant informationl Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) | 5 | 12 | 9 | As of 12/31/2010, PRBI has not activated services. Five contracts have been signed with last mile providers. We anticipate activating services for some of these signed contracts in the next quarter. Some of the providers are in the process of constructing the middle mile to the PRBI interconnection point, which will delay the activation of services until that is completed. We are working with 12 potential interconnection clients. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agenciest and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline. | No variance from baseline. | Services will be available from 100Mbps-1Gbps. | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government agencies; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Backbone Activation: Completion of network testing of Puerto Rico-Florida span. Official launch and activation of interconnection and peering services. (b) Engineering Design Implementation: Continuance of PRBI facility preparations including emergency power, network activation, provisioning, operations & management of Layer 2 & 3 services.(c) Interconnection Agreements: We anticipate the execution of several interconnection agreements with broadband providers. We anticipate also executing peering agreements with network & content providers in MIA-NAP. (d) Steering Committee: Finalization of Steering Committee and scheduling of first meeting. (e) Employee Recruiting: Employee recruitment is ongoing. Specialized training in development. (f) Provisioning: Fine-tuning of provisioning processes. (g) Rights of Way: Contract negotiation for wireless tower sites for terrestrial network phase. | Critical Hub Networks, Inc | Equipment procurement of core network equipment is currently on schedule. However, baseline projections are tied to expenditures and payment for this equipment will be completed in the first quarter of 2011. We are continuing to encounter delays in recruiting of knowledgeable Network Engineer, RF Engineer and Analyst candidates, but this has not yet impeded actual progression of project. We are evaluating training alternatives for future recruitments. Last-mile costs are posing some challenges for executing interconnection contracts with some Community Anchors. While we anticipating addressing this with laterals funding through program income, this may be delayed due to new Environmental Assessment work which may need to be completed. | Weather: Hurricane season has ended. However, in the event that any adverse weather conditions impact either Puerto Rico or Miami, the project progress may be delayed and/or otherwise affected. Supplier/Vendor Deliverable: If any external supplier/vendor incurs delays in fulfilling their obligations, such as equipment delivery or service activation, the project schedule may be delayed. Contingency plans are in place to ensure overall project completion within the project timeframe.
NT10BIX5570018 | 2011 | Q1 | Q1 - 2011 | During the previous quarter, the PRBI project activities included: (a) Activation of PR-FL Services: The submarine cable capacity (FAC) for the Puerto Rico-Florida span was officially activated.(b) Inauguration Activity: On February 22, the PRBI held its inauguration event in San Juan. Congressman Pierluisi, AMPATH and INTECO participated in the event. In attendance were Puerto Rico government officials, broadband providers, Community Anchor Institutions and representatives of the press. (c) Engineering Design Implementation: Completion of copper and optical infrastructure at in PR-NAP and MIA-NAP. Ongoing PRBI facility preparations including security, emergency power, monitoring and management. (d) Terrestrial Network Deployment: Negotiations for tower sites in progress. Site inspections and review of availability of licensed frequencies initiated. Development of RFP/RFQ for wireless network equipment in progress. (e) Interconnection Agreements: Execution of interconnection agreement with broadband provider. Ongoing negotiations with broadband providers, government agencies and community anchor institutions on interconnection agreements. Continued negotiations of peering agreements with network & content providers in MIA-NAP. (f) Steering Committee: Three industry leaders have agreed to join the steering committee. Continue awaiting response from invited government representatives. (g) Employee Recruiting: Three positions were recruited. Employee recruiting is ongoing. (h) | 0 | 3901 | 0 | 0 | 3901 | 0 | 0 | 2 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione your reasons for any variance from the baseline plan or any other relevant information) | 6 | 11 | 9 | PRBI activated network services in late February 2011. Since activation, OSNet has completed its last mile connectivity and its interconnection was activated. The other five (5) pending networks are still in the process of constructing their last mile to the PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. Agreements continue to be in legal negotiations with many providers, resulting in a variance of 2 contracts off our original baseline projections. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agenciest and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | NA | 0 | 1 | 0 | 1 | No variance from baseline | Delays in last-mile fiber construction/wireless activation by the Broadband Providers to the PRBI interconnection point have delayed network activation for five (5) pending customers. Two of the broadband providers are hopeful to complete their last mile in the following quarter. | No variance from baseline. | Services are available from 100Mbps to 1Gbps. | 0 | 0 | 0 | 0 | Calculations for Community Anchor Institutions served included connectivity via last mile interconnected providers. Delays in last-mile construction by providers to the PRBI interconnection point, and high last-mile costs for direct PRBI connections also contribute to variance. | No variance | Calculations for Community Anchor Institutions served included connectivity via last mile interconnected providers. Delays in last-mile construction by providers to the PRBI interconnection point, and high last-mile costs for direct connections contribute to variance. | No variance | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Finalization of tower site leasing agreement(s). Completion of site visits and site assessment needs. (b) Engineering Design Implementation: Completion of rooftop antenna mounting structure for wireless interconnection initiations; (c) Interconnection Agreements: execution of additional interconnection agreements; (d) Employee Recruitment: hiring of RF Engineer & Network Engineer; (e) Network Interconnectivity: Activation of peering and interconnection with content and network providers at MIA-NAP.(f) Steering Committee finalization: We are working towards finalizing the members on the Steering Committee, and scheduling our first meeting, with a target of June for the first meeting. | Critical Hub Networks, Inc | FCC licensing and equipment procurement for RF equipment is delayed due to ongoing negotiations for tower sites and delays in recruiting of RF Engineer and Network Engineering staff. We are continuing to evaluate training alternatives for future recruitments. Expensive recurring last mile costs from last mile providers has resulted in a challenge in executing interconnection agreements with community anchor institutions. We are seeking alternatives for laterals to reduce this cost. | (a) Weather: Due to the nature of many facility accommodations activities, such as construction, in the case that any adverse weather conditions impact the Island, the project progress might be affected. (b) External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract our and supervising work on a regular basis. Variances in Architectural and Engineering Fees disbursements versus projected are a direct result of recruitment delays. Variances in site work versus projections was due to delays in disbursement of costs associated with cage and rooftop preparation work, where invoices were received past our draw down cutoff. In our previous PPR, we reported a projection of 828,565 in equipment expenses, which was a typographical error - it should have been 858,565. The variance between this amount and the actual expenditures was due to additional routing equipment which was delivered within the quarter.
NT10BIX5570018 | 2011 | Q2 | Q2 - 2011 | During the previous quarter, the PRBI project accomplishments included: (a) Terrestrial Network Deployment: Negotiations for tower sites in progress. Site inspections and review of availability of licensed frequencies, pathloss and endpoint bandwidth/capacity planning in progress. Development of RFP for wireless network equipment in progress. (b) Interconnection Agreements: Execution of interconnection agreement with broadband providers. Ongoing negotiations with broadband providers, government agencies and community anchor institutions on interconnection agreements. (c) Peering: Continued negotiations of peering agreements with network & content providers in MIA-NAP. Connections with Facebook, Google and Amazon were completed, among others. (d) Steering Committee: Two government representative accepted our invitation to the Steering Committee. The first Steering Committee meeting was held June 28. (e) Employee recruiting: 4 new recruitment took place -RF Engineer, Field Specialist, Grant Finance/Reporting Accountant and Network Engineer. Employee recruiting is ongoing. (f) Provisioning: Continuity of provisioning of interconnections with broadband provider networks -1 new provider was activated (g) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, government representatives, government agencies and educational institutions seeking collaboration to support the expansion of broadband usage. Participation of activ | 0 | 3901 | 0 | 0 | 3901 | 0 | 0 | 2 | Variance of 14 miles due to finalization of contracts for tower sites. | No variance | No variance | No variance | No variance | Variance of 3 due to finalization of contracts for tower sites. | Variance of 1 due to finalization of contracts for tower sites. | Variance of 2 due to finalization of contracts for tower siten of contracts for tower sites | 9 | 13 | 12 | OSNet, Worldnet, and Liberty Cablevision have completed its last mile connectivity and its interconnection was activated. The other six (6) pending networks are in the process of constructing their last mile to the PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering/IXP services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agenciest and peering/IXP services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 3 | 0 | 3 | No variance from baseline | Delays in last-mile construction have delayed network activation for pending customers. However, we are ahead of baseline projections for signed interconnection agreements. | No variance from baseline. | Services are available from 100Mbps to 1Gbps. | 0 | 0 | 0 | 0 | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAI's in 2012. | No variance | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAI's in 2012. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Finalization of tower site agreement(s). (b) Completion of RFP process for Microwave Equipment and issuance of purchase order for equipment acquisition. (c) Engineering Design Implementation: Completion of rooftop facilities; (d) Interconnection Agreements: execution of additional interconnection agreements; (e) Network Interconnectivity: Continuity of activation of peering and interconnection with content and network providers at MIA-NAP and PR-NAP.(f) Steering Committee: Scheduling next meeting and seeking candidates to fill final two (2) seats on committee. (g) Ongoing community outreach and work with key agencies including Department of Education and Office of the CIO. | Critical Hub Networks, Inc | We are currently finalizing the capital lease agreements for the network tower sites, which was delayed in part due to some of the sites identified were not able to enter into a capital lease and alternative sites needed to be located which could be substituted. FCC licensing and equipment procurement for RF equipment is delayed due to finalization of contracts for tower sites. Various interconnections which are being constructed by broadband providers, as well as tower site analysis work was delayed due to poor weather conditions in Puerto Rico. There was significant rain during the quarter. | (a) Weather: Much of the work remaining to be completed will be in the mounting of antennas on existing towers or rooftop. Due to the nature of many facility activation activities, any adverse weather conditions which impact the Island may affect the progress of the project. (b) External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier in compliance, we are limiting what we contract our and supervising work on a regular basis. (c) Capital Lease - if we are unable to finalize the capital leases for the tower sites, we will need to seek alternative sites which may require approval for route changes and other approvals.
NT10BIX5570018 | 2011 | Q3 | Q3 - 2011 | (a) Terrestrial Network Deployment: Negotiations and execution of agreements for tower sites in progress. RFP/RFQ for wireless network equipment was issued. We received responses from over 10 vendors, and are completing our formal review. (b) Interconnection Agreements: Execution of interconnection agreement with Community Anchor Institutions and 1 new Broadband Provider. Ongoing negotiations with broadband providers, government agencies and other community anchor institutions. (c) Peering & Provisions: Continued negotiations and activation of peering agreements with network & content providers in MIA-NAP. Over 40 organizations now peered. Two new provisions for broadband providers were completed. (d) Steering Committee: First meeting held at the end of 2nd quarter reporting period. (e) Employee recruiting is ongoing. (f) Provisioning: Continuity of provisioning of interconnections with broadband provider networks. 1 new network activated (g) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, government representatives and agencies, and educational institutions seeking collaboration to support the expansion of broadband usage. In process of finalizing interconnection agreements with Department of Education and the Puerto Rico Health Information Network (PRHIN). (h) Facilities: Facility readiness for rooftop access is in process. The electrical and fiber connectivity was completed. (i) Wireless Network: Preparatio | 0 | 3901 | 0 | 0 | 0 | 0 | 0 | 2 | Variance of 43 miles due to finalization of contracts for tower sites and pending route change submission. | no variance | no variance | no variance | no variance | Variance of 6 due to finalization of contracts for tower sites and pending route change submission. | Variance of 4 due to finalization of contracts for tower sites and pending route change submission. | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Variance of 43 miles due to finalization of contracts for tower sites and pending route change submission. Variance of 6 due to finalization of contracts for tower sites and pending route change submission. Variance of 4 due to finalization of contracts for tower sites and pending route change submission. Variance of 5 due to finalization of contracts for tower sites and ending route change submissions for any variance from the baseline plan or any other relevant information) Variance of 43 miles due to finalization of contracts for tower sites and pending route change submission. Variance of 6 due to finalization of contracts for tower sites and pending route change submission. Variance of 4 due to finalization of contracts for tower sites and pending route change submission. Variance of 5 due to finalization of contracts for tower sites and ending route change submission. | 11 | 14 | 12 | OSNet, Worldnet, Liberty Cablevision, AWV, Red Dog, and Columbus Networks have already established interconnectivity. The other five (5) pending networks are in the process of constructing their last mile to the PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering/IXP services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agenciest and peering/IXP services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 6 | 0 | 6 | No variance from baseline | On-going last mile construction by broadband providers with signed interconnection agreements. | No variance from baseline | Services are available from 100Mbps to 1Gbps+ | 0 | 0 | 0 | 0 | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAIs in 2012. | No variance | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAIs in 2012. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Submission of the Route Change. (b) Subject to route change approval, finalization of tower site capital lease agreement(s). (c) Engineering Design Implementation: Subject to route change approval, completion of rooftop facilities and initiation of wireless site deployment allocations. Final selection of vendor(s) for the wireless network equipment; (d) Interconnection Agreements: ongoing negotiations with Providers, government & CAI. Execution of additional interconnection agreements. We project 2 new interconnections agreements with broadband providers. (e) CAI's served will be reported by interconnected networks to PRBI in Q1 2012, for reporting to NTIA in Q2 2012. (f) Network Interconnectivity: Continuity of activation of network interconnection in PR, and activation of peering and interconnection with content and network providers at MIA-NAP. (g) Network Deployment. Subject to route change, we anticipate deployment of wireless network initiating in Q1 2012. | Critical Hub Networks, Inc | We are in the process of preparing a request for route change, due to the loss of several sites and a new obstruction. Redesign of the network and identification of alternative sites took longer than expected. SHPO's response also took longer than expected. The route change will be submitted early next quarter. Until the route change is approved, we cannot finalize all the rights of way, FCC licensing or equipment procurement. Our projected milestone achievements for the coming quarter are based on the assumption that NTIA will approve the route change promptly. | (a) Route Change. Any delay in our ability to submit the route change for NTIA review, or in NTIAâ€™s response to our request, will impact the planned progress of the project. (b) Weather: Due to the nature of many facility accommodations activities, such as construction, in the case that any adverse weather conditions impact the Island, the project progress might be affected. (c) External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract our and supervising work on a regular basis.
NT10BIX5570018 | 2011 | Q4 | Q4 - 2011 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Network Deployment: A route change was submitted to the NTIA Grants Office in October, and was approved in November. Negotiations for tower sites ongoing. Two additional tower agreements were executed. Completion of procurement process for licensed wireless network equipment. Purchase Order was issued in December following route change approval. (b) Interconnection Agreements: Execution of one new interconnection agreement with a Broadband Provider. Execution of interconnection agreement with the Puerto Rico Department of Education for peering for approximately 1475 schools. Ongoing negotiations with broadband providers,government agencies and other community anchor institutions.(c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. 49 organizations peered in total. (d) Employee recruiting: 1 new recruitment took place - Jr. Network Engineer. Employee recruiting is ongoing. (e Provisioning: Continuity of provisioning of interconnections with broadband provider networks and change orders. 2 new providers were activated (f) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, educational institutions, government representatives and agencies seeking collaboration to support the expansion of broadband usage. | 0 | 3901 | 0 | 0 | 0 | 0 | 0 | 2 | Variance due to pending route change request. | No variance | No variance | No variance | No variance | Variance due to pending route change request. | Variance due to pending route change request. | Variance due to pending route change request. | 12 | 8 | 12 | OSNet, Worldnet, Liberty Cablevision, AWV, Xecure, Aeronet, Big Dog and Columbus Networks have already established interconnectivity. The other four (4) pending networks are in the process of constructing/preparing their last mile to the PRBI interconnection site or are pending the completion of the terrestrial middle-mile network spans to their desired interconnection point. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 8 | 0 | 8 | No variance | Variance due to on-going last mile construction and preparations by broadband providers with signed interconnection agreements. | No variance | Services are available from 100Mbps to 1Gbps+ | 0 | 0 | 0 | 0 | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAI's in Q1 2012. | No variance | Calculations for Community Anchor Institutions served included connectivity to be provided via interconnected last mile providers. Providers will report their interconnected CAI's in Q1 2012. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Terrestrial Network Deployment: Receipt & acceptance of RF Network Equipment. Initiation of deployment of terrestrial wireless network infrastructure. Assuming the approval of licensed frequencies early in quarter and receipt of equipment, we will complete 3 links, equal to 24 miles. (b) Interconnection Agreements: Execution of one (1) new interconnection agreement with a Broadband Provider. Execution of interconnection agreement with the Puerto Rico Department of Health for peering with the Puerto Rico Health Information Network (PRHIN). Continued negotiations with broadband providers,government agencies and other community anchor institutions.(c) Employee recruiting: recruitment of 2-3 new positions related to the deployment of the terrestrial network. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers. Planning & coordination for the activation of PRHIN and Department of Educationâ€™s network interconnectivity. We plan to activate interconnection with one (1) CAI (PRHIN). In addition, we anticipate receiving the reports from interconnected broadband providers on the number of CAIs which their last-mile broadband network serves. The PRBI project is not directly interconnecting most CAIs, rather we are working with broadband providers who will deploy the last mile network services to CAIs. | Critical Hub Networks, Inc | All Equipment Procurement related to the RF Network was put on hold pending the route change approval. In December, a purchase order was issued and we anticipate delivery in Q1 2012. If payment for the equipment is issued in Q1 2012, we will catch up to our original projected Equipment Procurement milestone in the next quarterly PPR. | (a) Weather: Due to the nature of many facility accommodations activities, such as construction, in the case that any adverse weather conditions impact the Island, the project progress might be affected. (b) External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract our and supervising work on a regular basis.(c) Approval of Licensed Frequencies - in the event that any of our licensed frequencies are not approved this quarter, it will affect the anticipated deployment of the network.
NT10BIX5570018 | 2012 | Q1 | Q1 - 2012 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Network Deployment: Negotiated additional tower sites as per approved route change. FCC licenses submitted & pending.(b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. (c) Peering & Provisioning: Continued negotiations of peering agreements with network & content providers in MIA-NAP. Connections with OCCAID, Mojohost and Hostdime - 52 organizations peered in total. Continuity of provisioning of interconnections with broadband provider networks and change orders- 1 new service upgrade was activated. The Puerto Rico Health Internet Network was activated through the bridge. (d) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, government representatives, government agencies and educational institutions seeking collaboration to support the expansion of broadband usage. Coordination of educational activities for broadband provider community, including IPv6 Workshop and promotion of IPv6 peering via PRBI.(e) Facilities: Facility readiness for rooftop access was completed. The electrical and fiber connectivity was completed. Terrestrial Network Deployment preparations are in progress. | 0 | 3901 | 0 | 0 | 0 | 0 | 0 | 2 | Variance due to pending FCC license issuance. | No variance | No variance | No variance | No variance | Pending FCC licenses | Pending FCC licenses | Pending FCC licenses | 13 | 8 | 12 | OSNet, Worldnet, Liberty Cablevision, AWV, Xecure, Aeronet, Big Dog, Tropical Networks and Columbus Networks have established interconnectivity. The other three (3) pending networks are still constructing/provisioning connectivity with PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 9 | 0 | 9 | No variance | Agreements signed with 13 providers - no variance from baseline. 9 network interconnections are currently active. Pending ongoing last mile and port preparation by broadband providers in order to activate 4 remaining signed interconnection agreements. | No variance | Services are available from 100Mbps to 1Gbps+ | 1 | 0 | 1 | 0 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, one direct CAI connection to Puerto Rico Dept. of Health -PRHIN | No variance | Baseline calculations for CAI served included connectivity via interconnected last mile providers. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI will be offering peering services, both in Puerto Rico and in Florida. These services will allow for the local exchange of traffic between networks. Peering will be available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) FCC License Issuance. (b) Finalization of tower site leasing agreement(s) â€“Pending 1 to complete the new sites included at the route change. (c) Procurement â€“ Receipt of wireless antenna equipment for fixed wireless terrestrial network. (d) Interconnection Agreements: continued negotiations with last mile providers. We anticipate the execution of one (1) new interconnection agreement in the quarter with a broadband provider; (e) Network Interconnectivity: Continuity of activation of peering and interconnection with content and network providers at MIA-NAP. (f) Network Build: Anticipated deployment of 3 fixed wireless links, estimated 23 miles deployed and in testing state. (g) Community Outreach: Continued IPv6 outreach activities with broadband providers, promoting peering and broadband expansion. (h) Provisioning: Anticipate the activation of two (2) interconnections with broadband providers which have signed interconnection agreements. The PRBI is not directly interconnecting most CAIs, rather we are working with broadband providers who deploy the last mile services to CAIs. We are continuing work on provisioning the direct interconnection with the Department of Education. | Critical Hub Networks, Inc | FCC license application submission was delayed, as we were requested to extend the standard Prior Coordination Notification (PCN) period due to the quiet zones in Puerto Rico due to the Arecibo Observatory. PCNs have been cleared, and licenses applications were submitted to FCC. FCC is taking approximately 60 days to process applications, which is longer than anticipated. | Weather: Due to the nature of many facility accommodations activities, such as construction, in the case that any adverse weather conditions impact the Island, the project progress might be affected. External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we subcontract and supervising work on a regular basis. FCC Licenses: We are anticipating the issuance of our FCC licenses in the next quarter. Any delays or denials by the FCC will cause significant delays in miles activated. Equipment Delivery: Any delays in the receipt of our wireless network equipment for the will cause delays in network build and miles activated.
NT10BIX5570018 | 2012 | Q2 | Q2 - 2012 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Network Deployment: Continuity of the facilities preparation were managed this quarter and we anticipate having them completed by the end of Q3. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. 3 new interconnection agreements signed in reporting period. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. Connections with Nordunet -53 organizations peered in total. (d) Employee recruiting: Employee recruiting is ongoing. (e) Provisioning: Continuity of provisioning of interconnections with broadband provider networks and change orders -3 new interconnections were activated. (f) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, government representatives, government agencies and educational institutions seeking collaboration to support the expansion of broadband usage. Attendance at NTIA-SHLB 2012 Conference in Arlington, VA. (g) Wireless Network: Activities related to the allocation of facilities for the Terrestrial Network are in progress. The engineering design implementation for the Wireless Towers allocations was initiated. (h) FCC Licensing: As of May 31, pending issuance of FCC licenses. | 0 | 3901 | 0 | 0 | 0 | 0 | 0 | 2 | Delays in issuance of FCC licenses. Deployed wireless infrastructure pending link activation, testing & acceptance. | No variance | No variance | No variance | No variance | Delays in issuance of FCC licenses. | Delays in issuance of FCC licenses. | Delays in issuance of FCC licenses. | 16 | 8 | 12 | OSNet, Worldnet, Liberty Cablevision, AWV, Xecure, Aeronet, Big Dog, Tropical Networks, Columbus Networks, Puerto Rico Webmasters (PRW), and AT&T have established interconnectivity. The other five (5) pending networks are constructing/provisioning last mile connectivity to PRBI interconnection site, or are awaiting for activation of a terrestrial POP nearest to their facilities. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 11 | 0 | 11 | No variance | Agreements signed with 16 providers - +2 over original baseline projection. 11 network interconnections are currently active. Pending ongoing last mile and port preparation by broadband providers in order to activate remaining 5 signed interconnection agreements. | No variance | Services are available from 100Mbps to 1Gbps+ | 1 | 0 | 1 | 0 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, one direct CAI connection to Puerto Rico Dept. of Health - PRHIN. | No variance | Baseline calculations for CAI served included connectivity via interconnected last mile providers. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | (a) Receipt of FCC licenses, and initiation of activation of microwave network. We estimate deployment of 136 Miles in the licensed microwave network by the end of the next quarter. (b) Finalization of tower site leasing agreement(s). (c) Engineering Design Implementation: Continuity of Wireless Towers allocations. (d) Interconnection Agreements: continuity of the execution of additional interconnection agreements; Anticipate the execution of one new interconnection agreement for broadband wholesaler/last mile provider during the quarter. (e) Network Interconnectivity: Continuity of activation of peering and interconnection with content and network providers at MIA-NAP. Working to establish physical presence at PRBI facilities in Puerto Rico for key content providers. We anticipate the activation of interconnections with two broadband wholesaler/last mile networks during the quarter. We do not anticipate activation of any CAIs during the quarter. | Critical Hub Networks, Inc | Due to delays in the receipt of FCC licenses, we were unable to commence the installation and activation of our terrestrial microwave network in Q2-2012. | (a) Weather: Due to the nature of many facility accommodations activities, such as construction, in the case that any adverse weather conditions impact the Island, the project progress might be affected. Hurricane season officially started in June, and peak season is during the months of August & September. (b) External Contractors Deliverable: If any external contractor/supplier/vendor incur in delays or does not fulfill the established plan - deliverable - it also affects the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract our and supervising work on a regular basis. (c) Tower Sites. In the event that a tower/rooftop site becomes unavailable, we will face delays in deployment of the terrestrial network and will be forced to seek an alternative site and submit for a new route change and new FCC licenses. Some sites will have more impact than others in the overall network build-out.
NT10BIX5570018 | 2012 | Q3 | Q3 - 2012 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Network Deployment: Continuity of the facilities preparation was managed this quarter and we anticipate having them completed by the end of 3rd quarter of 2012. By the closing of this quarter we had deployed 72 Miles in our fixed wireless terrestrial network over 7 links. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. 1 new interconnection agreement in this reporting period with a CAI/University System. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. New peering established with 365Wireless.net -54 organizations peered in total. (d) Provisioning: Continuity of provisioning interconnections with broadband providers -3 new service ports were activated (Nustream, CoquiTel & Inteco) & 3 port upgrades. As result of port activations, PR.GOV government portal is now peered. (e) Community Outreach: Implementation of Community Outreach plan. Meetings held with other ARRA and BTOP recipients, government representatives, government agencies and educational institutions seeking collaboration to support the expansion of broadband usage. (f) Wireless Network: Activities related to the allocation of facilities for the Terrestrial Network are in progress. By the closing of this quarter we had deployed 71 Miles a total of 7 links. (g) Route Change: Preparation of a route change to address challenges identified with two POIs. Alternatives were found to resolve the site location needs. Route change will be submitted in October 2012. | 72 | 3901 | 0 | 0 | 0 | 7 | 9 | 11 | Variance of 79 miles due to delays in FCC licensing, which have since been resolved. | No variance | No variance | No variance | No variance | Variance of 6 due to delays in FCC licensing, which have since been resolved | Variance of 1 due to delays in FCC licensing and legal challenges with some site owners. | Variance of 3 due to delays in FCC licensing and legal challenges with some site owners. | 16 | 8 | 12 | Liberty Cablevision, Worldnet, Xecure, Aeronet, AWV, Big Dog, OSNet, AT&T, Puerto Rico Webmasters (PRW), Tropical Networks, Columbus Networks, CoquiTel, Nustream and Inteco have established interconnectivity. The other two (2) pending networks are still in the process of constructing their last mile to the PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 14 | 0 | 14 | No variance | Agreements signed with 16 providers - no variance from baseline. 14 network interconnections are currently active. Pending ongoing last mile and port preparation by broadband providers in order to activate remaining 2 signed interconnection agreements. | No variance | Service are available from 100Mbps to 10Gbps | 1 | 0 | 1 | 0 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, one direct CAI connection to Puerto Rico Dept. of Health - PRHIN. | No variance | Baseline calculations for CAI served included CAIs served by interconnected last mile providers. Due to NTIA revised guidance, only direct-connect CAIs are now reported. We request to revise the baseline to reflect this guidance. | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Route Change: Submission of route change to address challenges with 2 interconnection sites. Anticipate route change approval during the quarter. (b) Wireless Network Deployment: Activation of 11 POIs and associated links. (c) Interconnection Agreements: Continuity of execution of interconnection agreements with broadband providers. Anticipate one (1) new agreement during the quarter. (d) Network Interconnectivity: Continuity of activation of peering and interconnection with content and network providers at MIA-NAP. Anticipate ten (10) new peering interconnections at MIA-NAP. (e) Community Outreach: Meeting with government agencies, broadband providers and other community leaders to implement plans to promote the adoption of broadband in the island. (f) Close Out Preparations: Preparations for project close-out initiated. | Critical Hub Networks, Inc | Legal challenges with two sites will require us to submit a route change in October, and caused some delay as time was invested in identifying alternatives to address the challenges. FCC licensing has been completed for all unaffected sites. A new FCC license will need to be submitted in November, subject to successful route change approval. | (a) Route Change. We will be submitting a route change in October 2012 in order to address the challenges encountered with two points of interconnection. Subject to route change approval, we will submit for new associated FCC licenses. If route change approval is delayed or denied, it may impact our ability to complete this link within the funded period. (b) Weather: Due to the nature of many facility accommodation activities, in the case that any adverse weather conditions impact Puerto Rico the project's progress may be affected. (c) External Contractor Deliverables: If any external contractor/supplier/vendor incurs delays or does not fulfill their duties/materials, it may impact the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract out. (d) Tower/Antenna Sites. In the event that a tower/rooftop becomes unavailable, we will face delays in deployment of the terrestrial network and will be forced to seek an alternative site and submit for a new route change and new FCC licenses. Some sites will have more impact than others in the overall network build out.
NT10BIX5570018 | 2012 | Q4 | Q4 - 2012 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Wireless Network Deployment: Route Change was submitted & approved in October 2012. Implementation of new route in progress. By the closing of this quarter we had deployed 195 Miles in our fixed wireless terrestrial network. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. 1 new interconnection agreement in this reporting period with a broadband provider, for a total of 17 interconnection agreements. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers. (e) Community Outreach: Meetings held with other ARRA and BTOP recipients, government representatives, government agencies and educational institutions seeking collaboration to support broadband adoption. (f) Project Modification: In December 2012, submitted a request for project modification to expand project to include fiber in an existing rail system (PRBI-TU segment). | 195 | 3901 | 0 | 0 | 0 | 17 | 17 | 19 | No significant variance. 12 miles pending for deployment. | No variance | No variance | No variance | No variance | Additional links due to route change approvals. | Additional towers due to route change approvals. | Additional interconnection points due to route change approvals. | 17 | 7 | 12 | Liberty Cablevision, Worldnet, Xecure, Aeronet, AWV, Big Dog, OSNet, AT&T, Puerto Rico Webmasters (PRW), Tropical Networks, Columbus Networks, CoquiTel, Nustream and Inteco have established interconnectivity. The other three (3) pending networks are still in the process of constructing their last mile to the PRBI interconnection site. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. All interconnection agreements are with last mile service providers which are obtaining PRBI interconnectivity for use in offering their own broadband Internet services. | PRBI will provide middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | N/A | 0 | 17 | 0 | 17 | No variance | Agreements signed with 17 providers - no variance from baseline. 14 network interconnections are currently active. Pending ongoing last mile and port preparation by broadband providers in order to activate remaining 3 signed interconnection agreements. | No variance | Services are available from 100Mbps to 10Gbps | 1 | 0 | 1 | 0 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, one direct CAI connection to Puerto Rico Dept. of Health - PRHIN. | No variance | Baseline calculations for CAI served included CAIs served by interconnected last mile providers. Due to NTIA revised guidance, only direct-connect CAIs are now reported. We request to revise the baseline to reflect this guidance. | No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations; government organizations; and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Project Modification: Anticipate the project modification submitted in December 2012 will be approved during the quarter. (b) Wireless Network Deployment: Receipt of final pending FCC licenses and activation of the final 12miles. (c) Interconnection Agreements: Continuity of execution of interconnection agreements with broadband providers. Anticipate one (1) new agreement during the quarter. (d) Network Interconnectivity: Continuity of activation of peering and interconnection with content and network providers at MIA-NAP. (e) Community Outreach: Meeting with government agencies, broadband providers and other community leaders to implement plans to promote the adoption of broadband in the island and promote local peering. (f) Close Out Preparations: Preparations for project close-out initiated. | Critical Hub Networks, Inc | Critical Hub's route change request was approved in November, and required us to request a new FCC license for a new site. As of the end of the quarter, the license has yet to be approved. Delays in its issuance will impact our ability to activate this final wireless link within the funded period. Critical Hub submitted in Q4-2012 a Project Modification for the PRBI-TU Segment, which has yet to be approved. | (a) Weather: Due to the nature of many facility accommodation activities, in the case that any adverse weather conditions impact Puerto Rico the project's progress may be affected. (b) External Contractor Deliverables: If any external contractor/supplier/vendor incurs delays or does not fulfill their duties/ materials, it may impact the project outcome. In order to reduce risk of contractor/supplier incompliance, we are limiting what we contract out. (c) FCC Licenses: Critical Hub is pending 2 FCC licenses in order to finish the terrestrial wireless network. Delay in the issuance of the licenses will impact our ability to complete the link activation within the funded period.
NT10BIX5570018 | 2013 | Q1 | Q1 - 2013 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Wireless Network Deployment: By the closing of this quarter we had deployed 207 Miles in our fixed wireless terrestrial network. Final testing underway. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers. (e) Project Modification: Received approval for PRBI-TU segment. (f) PRBI-TU: Testing of existing fiber completed. Engineering design for interconnection points and fiber activation underway. | 207 | 3901 | 0 | 0 | 0 | 22 | 21 | 23 | No variance | No variance | No variance | No variance | No variance | Additional links due to route change approvals | Additional towers due to route change approvals | Additional interconnection points due to route change approvals | 17 | 8 | 12 | Liberty Cablevision, Worldnet, Xecure, Aeronet, AWV, Big Dog, OSNet, AT&T, Puerto Rico Webmasters (PRW), Tropical Networks, Columbus Networks, CoquiTel, Nustream and Inteco have established interconnectivity. We have signed interconnection and are pending the last mile construction for Orizon Wireless, VPNet, and Yiga Corp. All interconnection agreements are with last mile service providers which are obtaining PRBI interconnectivity for use in offering their own broadband Internet services. | PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI also provides peering services to Critical Community Anchor Institutions and Government Agencies. See attachment for confidential wholesale pricing. | N/A | 0 | 17 | 0 | 17 | No variance | Agreements signed with 17 providers - no variance from baseline. 14 network interconnections are currently active. Pending last mile and port activation by three remaining broadband providers which have signed interconnection agreements | No variance | Services are available from 100Mbps to 10Gbps | 1 | 0 | 1 | 1 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, there is one direct CAI connection to the Puerto Rico Department of Health - PRHIN. | No variance | Baseline calculations for CAI served included CAIs served by interconnected last mile providers. Due to NTIA revised guidance, only direct-connect CAIs are now being reported. We request to revise the baseline to reflect this guidance. | Services are available from 10Mbps to 1Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations, government organizations and broadband providers. | FALSE | N/A | During the next quarter, we anticipate the following accomplishments: (a) Terrestrial Wireless Network Deployment: Completion of testing of fixed wireless terrestrial network. (b) Interconnection Agreements: Continuity of execution of interconnection agreements with broadband providers. Anticipate the execution of one (1) Interconnection Agreement with a broadband wholesaler/last mile provider during the quarter. (c) Network Interconnectivity: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers, and with peered network & content providers at MIA-NAP. (e) CAI's and Community Outreach: Meeting with government agencies, broadband providers and other community leaders to implement plans to promote the expansion & adoption of broadband in the island, and to promote local peering. We do not anticipate activating any new CAIs during this quarter. (f) PRBI-TU: Completion of engineering design for interconnection points. Procurement of equipment for optical network activation. We do not anticipate the activation or completion of deployment of any miles on the PRBI-TU segment during this quarter, as we will be pending installation of optical network equipment. | Critical Hub Networks, Inc | In Q1-2013, Critical Hub received approval for a project modification for the PRBI-TU Segment. In order to facilitate our completion of this new segment, Critical Hub was also granted a project extension in Q1-2013. We anticipate project completion by September 2013. | (a) Weather. In the event that any adverse weather conditions impact Puerto Rico, the project's progress may be affected. (b) External Deliverables. If any external contrator/supplier incurs delays, impedes access, or does not fulfill their duties, it will impact our ability to complete the project on time. The new PRBI-TU segment depends on the operator of the Tren Urbano system providing us with access to TU's ROW. (c) Procurement Delays. Weather may impact the shipment of equipment to Puerto Rico. In the event that a vendor experiences delays or backorders on materials or equipment necessary for activation of the PRBI-TU segment, it will impact our ability to complete the project on time.
NT10BIX5570018 | 2013 | Q2 | Q2 - 2013 | During the previous quarter, the PRBI project activities included: (a) Terrestrial Wireless Network Testing: All links deployed. Testing and optimization of terrestrial wireless network. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers. (e) PRBI-TU: Engineering design of interconnection points completed. Procurement of equipment as per approved design for fiber optic network activation. Installation of equipment and fiber splicing at interconnection points along TU route in progress. | 207 | 3901 | 0 | 0 | 0 | 22 | 21 | 23 | No variance | No variance | No variance | No variance | No variance | Additional links | Additional towers due to route change approvals | Additional interconnection points due to route change approvals | 17 | 8 | 12 | Liberty Cablevision, Worldnet, Xecure, Aeronet, AWV, Big Dog, OSNet, AT&T, Puerto Rico Webmasters (PRW), Tropical Networks, Columbus Networks, CoquiTel, Nustream and Inteco have established interconnectivity. We have signed interconnection and are pending the last mile construction for Orizon Wireless, VPNet, and Yiga Corp. All interconnection agreements are with last mile service providers which are obtaining PRBI interconnectivity for use in offering their own broadband Internet services. | PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI also provides peering services to Critical Community Anchor Institutions and Government Agencies. See attachment for confidential wholesale pricing. | N/A | 0 | 17 | 0 | 3 | No variance | Agreements signed with 17 providers - no variance from baseline. 14 network interconnections are currently active. Pending last mile and port activation by three remaining broadband providers which have signed interconnection agreements | No variance | Three (3) port sizes are offered for wholesale interconnections - 100M, 1G and 10G. PRBI has agreements for three 10G interconnections, four 1G interconnections, and ten 100M interconnections. | 1 | 0 | 1 | 1 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently, there is one direct CAI connection to the Puerto Rico Department of Health - PRHIN. | No variance | Baseline calculations for CAI served included CAIs served by interconnected last mile providers. Due to NTIA revised guidance, only direct-connect CAIs are now being reported. We request to revise the baseline to reflect this guidance. | Services are available from 10Mbps to 1Gbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations, government organizations and broadband providers. | FALSE | N/A | During the next and final quarter, Critical Hub will successfully complete the PRBI project. In particular, we anticipate the following accomplishments: (a) Terrestrial Wireless Network Deployment: Completion of fixed wireless terrestrial network. (b) PRBI-TU Network Expansion: Activation of the PRBI-TU fiber optic network span extending through the Tren Urbano railway system. (c) Interconnection Agreements: Continuity of execution of interconnection agreements with broadband providers. (d) Network Interconnectivity: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (e) Provisioning: Continuity of provisioning of interconnections with broadband providers, and with peered network & content providers at MIA-NAP. (f) Community Outreach: Continued work with other ARRA recipients, government agencies, broadband providers and other community leaders to promote the expansion & adoption of broadband in the island, and to promote local peering. (g) Closeout: Completion of necessary documentation prior to end of award period. Preparations for final audit. | Critical Hub Networks, Inc | In Q1-2013, Critical Hub received approval for a project modification for the PRBI-TU Segment. In order to facilitate our completion of this new segment, Critical Hub was also granted a project extension in Q1-2013 until September 31, 2013. Any delays are due to our ongoing activities related to the project modification. NOTE: In our Q1-2013 PPR, we reported a total federal fund expenditure of $25,444,264. The correct expenditure in Q1-2013 was $25,439,916. This error was revised in the SF425 for Q1-2013, but we were unable to revise the Q1 2013 PPR. Rather, we were advised to note this error in our Q2-2013 PPR. For that reason, the federal funds reported to be expended in Q2-2013 appears less than was was expended in Q1-2013. The correct federal fund expenditure for equipment in Q1-2013 was 1,384,965. The correct federal fund expenditure for site work in Q1-2013 was 505,327 | (a) Weather. In the event that any adverse weather conditions impact Puerto Rico, the project's progress may be affected. (b) External Deliverables. If any external contrator/supplier incurs delays, impedes access, or does not fulfill their duties, it will impact our ability to complete the project on time. The new PRBI-TU segment depends on the operator of the Tren Urbano system providing us with access to TU's ROW. (c) Procurement Delays. Weather may impact the shipment of equipment to Puerto Rico. In the event that a vendor experiences delays or backorders on materials or equipment necessary for activation of the PRBI-TU segment, it will impact our ability to complete the project on time.
NT10BIX5570018 | 2013 | Q3 | Q3 - 2013 | The PRBI project successfully completed the deployment & activation of its Puerto Rico network, comprised of fiberoptic subsea connectivity between PR and Florida, fixed wireless terrestrial network, the establishment of an Internet Exchange Point (IXP) in San Juan, and the expanded PRBI-TU network segment through the San Juan Metropolitan area in via the Tren Urbano transit rail ROW. PRBI's successful completion has resulted in significant increase in broadband speeds available in Puerto Rico since 2010, as well as significant reduction in the cost per megabit. Some of PRBI's interconnected providers are now offering speeds up to 60Mbps. Since 2009, residential broadband rates has fallen from over $50/Mbps to less than $5/Mbps. The Puerto Rico Bridge Initiativeâ€™s infrastructure has facilitated these improvements in speed and price, as well as in the quality of service and latency for interconnected network operators. PRBI's IXP has also attracted the hosting of significant bandwidth-heavy content to the island, thus reducing that load on the submarine cable network and providing a superior QoS for consumers. In particular, our final quarterly work activities included: (a) Terrestrial Wireless Network Optimization: Optimization of terrestrial wireless network. (b) Interconnection Agreements: Ongoing negotiations are in place with broadband providers, government agencies and other community anchor institutions on interconnection agreements. (c) Peering & Provisions: Continued negotiations of peering agreements with network & content providers in MIA-NAP. (d) Provisioning: Continuity of provisioning of interconnections with broadband providers. (e) PRBI-TU: Completion of access point equipment installation, splicing and testing of fiber along TU route. Total activated fiber miles on PRBI-TU Segment: 11 miles. Total PRBI miles: 4,119 miles. | 207 | 3901 | 11 | 0 | 0 | 22 | 21 | 23 | 207 Miles of wireless links, 11 miles fiber via PRBI-TU Segment | No variance | PRBI-TU Segment completed | No variance | No variance | Additional links due to approved route change | Additional towers due to approved route change | Additional interconnection points due to approved route change | 17 | 8 | 12 | Liberty Cablevision, Worldnet, Xecure, Aeronet, AWV, Big Dog, OSNet, AT&T, Puerto Rico Webmasters (PRW), Tropical Networks, Columbus Networks, CoquiTel, Nustream and Inteco have established interconnectivity. We have signed interconnection agreements with Orizon Wireless, VPNet and YigaCorp, and are pending their last mile construction to a PRBI interconnection point. All interconnection agreements are with last mile service providers which obtain PRBI interconnectivity for use in their own broadband Internet services. | PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI also provides peering services to Critical Community Anchor Institutions and Government Agencies. See attachment for confidential wholesale pricing. | N/A | 0 | 17 | 0 | 3 | No variance | Agreements signed with 17 providers, no variance from baseline. 14 network interconnections are currently active. Pending last mile and port activation by three remaining broadband providers which have signed interconnection agreements. | No variance | Three (3) port sizes are offered for wholesale interconnections - 100M, 1G and 10G. PRBI has agreements for three 10G interconnections, four 1G interconnection and ten 100M interconnections. | 1 | 0 | 1 | 1 | Baseline calculations for CAI served included connectivity via interconnected last mile providers. Currently there is one direct CAI - Puerto Rico Department of Health (PRHIN) | No variance | Baseline calculations for CAI served included CAIs served through interconnected last mile providers. Due to NTIA revised guidance, only direct-connect CAIs are now being reported. | Services are available for 10Mbps to 1Gbps | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | PRBI offers peering services in Puerto Rico and Florida. These services allow for the local exchange of IP traffic between networks. Peering is available for community anchor institutions such as schools, libraries, health care providers and non-profit organizations, government organizations and broadband providers. | FALSE | NA | N/A | Critical Hub Networks, Inc | None to report. | N/A
NT10BIX5570019 | 2010 | Q3 | Q3 - 2010 | Draft Environmental Assessment completed and submitted to NTIA. Awaiting response from USFWS for approval of EA. Preliminary bidder interviews held. Bid assessments completed. Five successful contractors selected and notified of award. Pre-construction meeting held with successful bidder at MBC headquarters that included representatives from landbase provider and DOL. Started railroad permitting process. Corps of Engineers project manager assigned. New landbase uploaded to our mapping system to record OSP property routes and records. Dates established for mapping system training. Ordered generators for hut sites. Completed site surveys for all four interconnection points. Environmental firm hired on consulting basis to provide architectural historian and approved archaeologist to review design plans for possible impacts under PA. Negotiating joint use pole agreements with utility companies. Performed first drawdown of funds on this project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | General Offering of 10-100 mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Final approval of EA â€¢ Satisfaction of PA â€“ site visits of architectural and historical sites in accordance with PA â€¢ Distribution and final execution of EF&I contracts â€¢ Obtain VDOT, railroad, USACE, USFWS permits â€¢ Complete design and engineering field work â€¢ Complete joint use pole agreements â€¢ Obtain easements and complete interconnection point design â€¢ Begin reviewing and issuing construction prints â€¢ Hire two field inspectors â€¢ Start construction activities of project â€¢ Order pre-fab huts â€¢ Provide Cad Training to Engineering Vendors | Mid-Atlantic Broadband Cooperative | Major challenge has been getting response from USFWS and responding to VA Marine Resources commission requirements. | Gaining approval of the final EA and USCOE and VA Marine Resources permits.
NT10BIX5570019 | 2010 | Q4 | Q4 - 2010 | The final Environmental Assessment was approved and the National Telecommunications and Information Administration issued the FONSI on 12-7-10. Work on the Programmatic Agreement continued during the quarter with cemetery and archeological field visits being completed and the proposed avoidance strategy and construction methods being incorporated into the design prints. A joint permit is being prepared to submit to the Corps of Engineers and the Virginia Marine Resources Commission. MBC had a meeting with the VMRC during December to discuss the scope of the project and any permitting issues. They wanted to divide the project into 6 permits, which complicates the Corps permit since they wanted the project on one permit. Our EA consultant continued to obtain data required for the permit concerning stream statistics, methods of crossing, and drainage area to determine how many streams will be under VMRC jurisdiction. It appears there will be 103. Outside Plant Engineering and field verification has been completed on approximately 70% of the total project. Approximately 20% of the material has been ordered and received. The interconnection sites have been finalized and the huts have been ordered. The VDOT permits have been obtained by the contractor for 85% of the project. Utility pole agreements have been executed and pole permits sent for approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | General Offering of 10-100 MBPS | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ SUBMISSION AND APPROVAL OF THE JOINT PERMITS WITH CORPS OF ENGINEERS AND VIRGINIA MARINE RESOURCES COMMISSSION â€¢ COMPLETION OF THE ENGINEERING FIELD WORK AND WORK PRINTS â€¢ COMPLETION OF FIELD VERIFICATION OF THE PRINTS â€¢ START CONSTRUCTION ACTIVITIES IN ALL SEGMENTS â€¢ COMPLETION AND APPROVAL OF THE CERTIFICATIONS/CONSULTATIONS UNDER THE PA | Mid-Atlantic Broadband Cooperative | Due to scope of project, the data collection requirements of the VA Marine Resources Commission for the joint application was very stringent and voluminous. We had a meeting with the Commission in December 2010, and resolved specific requirements that were needed. MBC will submit joint permit in January 2011. | We are having to re-design/re-route a portion of segment 5 in Petersburg, VA due to Battlefield Park restrictions. NTIA assistance in expediting the EA & SHPO addendum would be of great assistance.
NT10BIX5570019 | 2011 | Q1 | Q1 - 2011 | The joint permit applications (6) to Virginia Marine Resources and the US Army Corps of Engineers were completed and submitted to the agencies. The SHPO consultations and review under the Programmatic Agreement was completed and reviewed and approved by SHPO and the NTIA. There were no negative comments from the consulting parties. Construction activities were started on Grant 972 on March 7, 2011. Four pre-fabricated huts for the interconnection locations (matching funds) were purchased. The network equipment for the four interconnection points (huts) was ordered. We received bids for the site work for the four interconnection points (huts). A request by MBC to re- route a portion of Segment 6 around Halifax, VA due to a proposed modernization project in the Town was submitted to the NTIA. MBC performed site visits to two contractorsâ€™ work center operations to verify security of materials and review availability of equipment. We purchased Cable Locating Equipment for field inspectors. We processed various pole permits, railroad permits, and pole make-ready requests with various utilities and railroads. MBC met with a representative from our fiber cable supplier and provided updated fiber cable requirements. Ninety percent (90%) of the Outside Plant Engineering has been completed. Ten (10%) of the construction has been completed. Most of the project activity has been in Campbell County this quarter. | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | The general understanding from our discussion on this matter was that "new network miles of fiber" was interpreted as miles constructed and "new network miles deployed" were miles placed in service. Therefore, we are stating that at that point, we had constructed 42 miles of cable, but placed none of it in service (for use). | N/A | N/A | N/A | Started construction in March 2011 due to delay in PA.The general understanding from our discussion on this matter was that "new network miles of fiber" was interpreted as miles constructed and "new network miles deployed" were miles placed in service. Therefore, we are stating that at that point, we had constructed 42 miles of cable, but placed none of it in service (for use). | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | General offering will be 10-100mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Approval of the VMRC and USCOE permits â€¢ Complete all field engineering â€¢ Complete field review of all work orders â€¢ Complete the RFP for site work for the interconnection site locations â€¢ Complete the submission of all permitting and make-ready requests â€¢ Complete 30% of the construction of the project | Mid-Atlantic Broadband Cooperative | Virginia Marine Resource Commission VMRC requires public notice and fifteen (15) day comment period after submission of permits. Awaiting end of comment period and issue of permits. Due to unforeseen issues, two partial routes in Segments 5 & 6 will have to be re-designed. Segment 5 (Petersburg, VA) is due to permit issues with National Parks Services (NPS). Segment 6 (Halifax, VA) portion is due to a re-development project in downtown Halifax. Re-route request was sent to the NTIA in March. Re-route request for Petersburg to be sent to NTIA in Y2Q2. | â€¢ Delay in the approval of the VMRC and USCOE permits will delay construction activities in 5 segments of the project â€¢ The proposed re-routes in segment 5 and segment 6 will require an addendum to the EA and to permitting agencies â€¢ MBC plans to add more construction crews when and if needed to mitigate project schedule risks.
NT10BIX5570019 | 2011 | Q2 | Q2 - 2011 | The permits from VMRC were approved during this quarter. A portion of the transport equipment was ordered and received. The remaining fiber optic cable was ordered from an alternate supplier after our current supplier increased shipping intervals by five to six months. The design engineering for the Petersburg re-route is 50% complete and, for the Halifax re-route, it is 100% complete. All other design work and permitting has been completed. Co-coordinating meetings were held with the VDOT, our construction vendor, and MBC on the portion of the reroute that is on I85, I95, and I295. The SHPO review for the reroutes has been completed. The RFP for the site work and placement of the huts was issued, the bids reviewed, and a vendor selected for the work. A pre-construction meeting was held for hut construction. A milestone was celebrated this quarter with the first school, Cumberland High School (Cumberland County), receiving service. Service was also established to 3 schools in Franklin County and 3 in Lunenburg County as a result of this project. 38% or 158 miles of construction has been completed. Most of the activity this quarter has been in Franklin County, Virginia. | 158 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | Miles constructed | N/A | N/A | N/A | 38% completed 116 miles this quarter. | N/A | N/A | N/A | 6 | 6 | 15 | Shentel; Kinex ; NTelos | 10 to 100 mbps circuits- Schools use these circuits for interconnecting their schools together and for internet services (LAN & WAN). DSI's used for cellular tower trunks. | N/A | 3 | 0 | 0 | 0 | Did not identify any on baseline. | N/A | N/A | General Offering will be 10-100 mbps | 7 | 7 | 0 | 0 | Seven schools with actual service. Will count other schools as served when splicing is completed. | Seven schools with actual service. | N/A | General offering will be 10-100 mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Provided 4 DSI's to NTelos for cell tower trunking. | FALSE |  | â€¢ Start placement and site work on the 4 interconnection sites â€¢ Complete at least 2 sites â€¢ Achieve approval of EA addendum for re-route â€¢ Gain VMRC approval of reroutes â€¢ Complete engineering design of re-route â€¢ Begin construction on re-routes in segments 5 and 6 â€¢ Continue construction and splicing activities in other segments to accomplish 55% completion | Mid-Atlantic Broadband Cooperative | Preparing the SHPO report, finalizing the EA addendum and preparing VMRC and USACOE permits for the two reroutes has been challenging to our schedule for segment 5. | Delivery dates for fiber optic cable and hand holes have been pushed back by vendors. We have changed vendors to improve delivery dates; however, the actual delivery dates may impede our planned progress. Make ready requests to other utilities may delay some planned aerial construction. We are following-up on all such requests.
NT10BIX5570019 | 2011 | Q3 | Q3 - 2011 | The majority of the transport equipment was ordered and received. The remainder of the fiber optic cable that was ordered from an alternate supplier has arrived. The design engineering for the Petersburg re-route has been completed. The Virginia Marine Resources Commission (VMRC) permits for the re-routes have been received. The addendum to the Environmental Assessment (EA)has been submitted for the reroutes. The contract for the site work for the hut placement was signed, a pre-construction meeting conducted with the contractor, and two of the four huts (interconnection points) have been placed on their respective sites. The majority of the work activity this quarter was in Sussex County. Fifty-nine schools have been passed in total. 61% or 254 miles of construction has been completed on this project. | 257 | 0 | 0 | 0 | 257 | 0 | 0 | 2 | Miles constructed/deployed; 61% of total. | N/A | N/A | N/A | 96 miles completed this quarter. | N/A | N/A | Remaining 2 to be complete by 12-31-11 | 10 | 3 | 15 | Multiple agreements with providers. Number of circuits (13) by wholesale provider: Shentel (4), Kinex(3), Lumos(4), GCR(2) Number of agreements (10) by wholesale provider: Shentel (4), Kinex(3), Lumos(1), GCR(2) | 10mbps-100mbps- Schools use these services for interconnecting schools together and for internet (LAN & WAN), DS1'a used for cell tower trunks. | N/A | 9 | 0 | 0 | 0 | Did not identify any on baseline. | N/A | N/A | General Offering will be 10mbps-100mbps. | 62 | 62 | 0 | 0 | Schools that have facilities available | Schools served | N/A | General Offering will be 10mbps-100mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering will be 10mbps-100mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering will be 10mbps-100mbps. | Provided DSI's for cell tower trunking. | FALSE | N/A | â€¢ Complete the site work and placement of the remaining 2 interconnection sites. â€¢ Achieve approval of Environmental Assessment (EA) addendum for re-route. â€¢ Begin construction on re-routes in segments 5 and 6. â€¢ Begin equipment installation at the four interconnection points. â€¢ Continue construction and splicing activities in all segments to accomplish 84% completion. â€¢ Increase CAIs served to 85; adding 23 in Y2Q4 â€¢ Increase signed agreements to 11 â€¢ Place 95 miles of fiber cable | Mid-Atlantic Broadband Cooperative | â€¢ Due to heavy rains and wet conditions, construction activities have been slowed in all segments â€¢ Make ready activities by other utilities have been slowed by storm damages to their own facilities | Make ready requests to other utilities may delay some planned aerial construction. We are following up on all requests. Wet weather has also impeded our buried plowing progress. This is likely to continue in Y2Q4.
NT10BIX5570019 | 2011 | Q4 | Q4 - 2011 | The NTIA program officer conducted a site visit of this grant on October 24-26, 2011. The addendum to the Environmental Assessment (EA) for the reroutes has been revised to add additional requested information and was re-submitted to the NTIA on December 20, 2011. We anticipate their review and approval within a few weeks. Three of the four huts (interconnection points) have been placed on site and power connected. We now have three of the four sites completed. Wet weather has hampered efforts to complete the fourth unit. It is anticipated it will be completed in January, 2012. The installation of transport equipment began in the fourth quarter, with installation in one interconnection point being completed. The installations will continue next quarter in the newly constructed sites. Ninety-four schools (CAIâ€™s) have been passed in total, with 33 added this quarter. There has been 8 contract with last mile provider executed this quarter, bringing the total to 18. Construction continues in 4 of the 6 segments (2 segments are awaiting approval of the EA supplement) with 81 miles of fiber being placed this quarter. This brings the total placement to 338 miles or 80% of this project. During the fourth quarter we spent $2,716,166.73, bringing the total amount spent YTD (Federal and Matching) to $10,596,259.82 (52.8%).The majority of the work activity this quarter was in Bedford County. | 338 | 0 | 0 | 0 | 338 | 0 | 0 | 4 | 81 miles deployed this quarter- 80% of the project | N/A | N/A | N/A | 81 miles deployed this quarter- 80% of the project | N/A | N/A | 3 of 4 completed this quarter | 18 | 2 | 12 | Shentel (4); Kinex (4); Lumos (2); GCR (8) Note: The number of contracts are listing in the parentheses. | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in Â¼ rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. . Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term See attachment for Member Pricing sheet | N/A | 18 | 0 | 0 | 18 | Did not identify any on baseline | N/A | N/A | General offering of 10 mbps to 100 mbps; Shentel (4) - 100mbps; Kinex (4)-10mbps; Lumos (2) -155mbps; GCR (8) - 100mbps | 94 | 94 | 0 | 94 | Schools and other government facilities | Schools and other government facilities | N/A | General Offering is 10mbps - 100mbps. Open Access Most schools order 50mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10mbps - 100mbps. Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10mbps - 100mbps. Open Access | Provide DSI's for cell tower trunking | FALSE | N/A | â€¢ Complete the site work and placement of the remaining one (1) interconnection site â€¢ Achieve approval of Environmental Assessment (EA) addendum for the re-routes â€¢ Complete construction of the re-routes in Segment 5 and 6 â€¢ Complete equipment installation in at least three of the four interconnection points â€¢ Continue construction and splicing activities in all segments to accomplish 97% completion â€¢ Increase CAIs served to 117; adding 23 in Y3Q1 â€¢ Increase total signed agreements to 20 â€¢ Place 63 miles of fiber cable for a total of 401 miles (97 %) | Mid-Atlantic Broadband Cooperative | â€¢ Submission of revised EA supplement delaying the approval and construction of the two (2) reroutes to next quarter â€¢ Wet weather conditions hamper fiber and hut site construction efforts â€¢ Some make ready work has been delayed by Dominion Power in Waverly, VA (Segment 1) | â€¢ Due to heavy rains and wet conditions, construction activities will be slowed in all segments â€¢ Work will be slowed by VDOT on the Segment 5 reroute due to VDOT work restrictions, weather conditions, and traffic/signage requirements â€¢ Dominion Power has been slow to complete make-ready so we can complete the remainder of the fiber placement on Segment 1 â€¢ Progress on completion of Equipment installation is dependent upon placement of final hut, power provisioning, and manpower resources
NT10BIX5570019 | 2012 | Q1 | Q1 - 2012 | MBC has prepared a route modification request to add three schools, one university, and two interconnection points (huts) to the original route at a cost of approximately $2,174,689. MBC has also prepared a budget modification to request that the original budget be modified to redistribute existing budgeted funds to cover the additional expenditures. These requests will be sent to the NTIA for approval in the 2nd quarter. The four huts (interconnection points) on the project have been placed on site and power connected to all of them. The installation of transport equipment continued in the 1st quarter and should be complete by the end of the 2nd quarter. One Hundred and Nine (109) CAIâ€™s have been passed in total, with 15 added this quarter. There have been new contracts with a last mile provider executed this quarter for eighteen (18) new circuits to Henry County Schools. Along with seven (7) other circuits added this quarter, this brings the total number of circuits added under this grant to forty-three (43). Construction has been completed in 2 of the 6 segments, is close to completion in 3 other segments, and is awaiting VDOT permit approval to restart construction in segment 5 (Petersburg reroute). Sixty-one (61) miles were placed this quarter, bringing the total miles placed YTD to 399 miles or 94% of this project. During the fourth quarter we spent $ 1,743,481, bringing the total amount spent YTD (Federal and Matching) to $12,379,739 (61.7%). The majority of the work activity this quarter was in Halifax County. | 399 | 0 | 0 | 0 | 399 | 0 | 0 | 4 | 61 miles deployed this quarter. 94% of the project | N/A | N/A | N/A | 61 miles deployed this quarter. 94% of the project | N/A | N/A | Final interconnection site completed in March 2012. Delayed due to wet weather conditions. | 43 | 2 | 12 | Shentel (4), Kinex (4) Lumos (5), GCR (29), BIT (1) Note: The number of contracts is listed in parentheses. | MBC provides secured, carrier-class collocation space (in Â¼ rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. . Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term | N/A | 43 | 0 | 0 | 43 | Did not identify any on Baseline | N/A | N/A | GCR(2) 100 mbps; GCR (4) 200 mbps; BIT(1) 50 mbps; GCR(3) 10 mbps; GCR(5) 20 mbps; GCR (15) 50 mbps; Shentel (4) 100 mbps; Kinex (4) 10 mbps; Lumos (5) 155 mbps; General offering of 10 mbps to 100 mbps; Open Access | 109 | 109 | 0 | 109 | Schools and other government institutions | Schools and other government institutions | N/A | General offering is 10 mbps to 100 mbp; Open Access Most schools order 50 mbps service | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10 mbps to 100 mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10 mbps to 100 mbps; Open Access | Provide DS1's for wireless service back haul from towers. | FALSE | N/A | â€¢ Complete construction of the re-route on Segment 6 â€¢ Complete equipment installation in the four interconnection points â€¢ Continue construction and splicing activities in remaining segments to accomplish 100% construction completion â€¢ Start construction on the route modification work, when approved â€¢ Increase CAIs served to 112 â€¢ Increase total signed agreements/circuits to 46. â€¢ Place 21 miles of fiber cable for a total of 420 miles (100%) | Mid-Atlantic Broadband Cooperative | â€¢ Some make ready work has been delayed by Dominion Power in Waverly, VA (Segment 1) â€¢ VDOT issued new permitting requirements for the Segment 5 Petersburg reroute, thus requiring resubmittal of permits and delaying start of work. â€¢ Have encountered rock on Segment 5 construction â€¢ Preparation of route modification and budget modification for submittal | â€¢ Work will be slowed by VDOT on the Segment 5 reroute due to VDOT work restrictions, weather conditions, and traffic/signage requirements â€¢ Obtain NTIA approval of the new route modification and budget modification requests. â€¢ Obtain quick EA addendum approval of route modification request. â€¢ Progress on completion of Equipment installation is dependent upon manpower resources
NT10BIX5570019 | 2012 | Q2 | Q2 - 2012 | MBC prepared a route modification request to add three schools, one university, and two interconnection points (huts) to the original route at a cost of approximately $2,174,689. MBC has also prepared a budget modification to request that the original budget be modified to redistribute existing budgeted funds to cover the additional expenditures. The budget modification was approved in the 2nd quarter. The route modification request is under consideration by the NTIA and is expected to be approved in the 3rd quarter. The installation of transport equipment continued in the 2nd quarter. We have finished three of the four nodes and 50% of the ring equipment. This should be completed by the end of the 3rd quarter. One Hundred and Fourteen (114) CAIâ€™s have been passed in total, with 5 added this quarter. There has been one (1) new contract with a last mile provider executed this quarter for a new circuit to Buckingham County Career and Technology Center. This brings the total number of circuits added under this grant to forty-four (44). Construction has been completed in 3 of the 6 segments, is close to completion in 2 other segments (waiting on make ready work), and is underway in the 6th segment (waiting for VDOT permit approval to restart construction on the Petersburg reroute). Fourteen (14) miles were placed this quarter, bringing the total miles placed YTD to 413 miles or 96% of this project. During the fourth quarter we spent $2,163,891, bringing the total amount spent YTD (Federal and Matching) to $14,543,638 (72.52%). The majority of the expenditures were for construction and materials. The majority of the work activity this quarter was in Buckingham County (Dillwyn). | 412 | 0 | 0 | 0 | 412 | 0 | 0 | 4 | 13 miles deployed this quarter. 96% of project | N/A | N/A | N/A | 13 miles deployed this quarter. 96% of project | N/A | N/A | Completed | 44 | 2 | 12 | Shentel (4); Kinex (5); Lumos(5); GCR (29); BIT(1) Note: The number of contracts is listed in parenthesis. | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 44 | 0 | 0 | 44 | Did not identify any on Baseline | N/A | N/A | Same as Y3Q1 PPR except Kinex (4) 10 mbps changes to (5) 10 mbps | 114 | 114 | 0 | 114 | Schools and other government institutions | Schools and other government institutions | N/A | General offering is 10 mbps to 100 mbps - Open access Most schools have 50 mbps service | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10 mbps to 100 mbps; Open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10 mbps to 100 mbps; Open access | Provide DS1's for wireless backhaul from towers | FALSE | N/A | â€¢ Continue fiber construction in the remaining 3 segments â€¢ Complete equipment installation in the fourth interconnection point â€¢ Complete construction and splicing activities in remaining segments to accomplish 100% construction completion on original project route â€¢ Start construction on the route modification work, when approved â€¢ Increase CAIs served to 117 â€¢ Increase total signed agreements/circuits to 46. â€¢ Complete 13 additional miles | Mid-Atlantic Broadband Cooperative | â€¢ Some make ready work has been delayed by Dominion Power due to recent storms. â€¢ VDOT approved one of three permits on the Petersburg reroute. We are awaiting approval of the remaining two permits. This is delaying completion of this segment â€¢ Manpower for equipment installations â€¢ Gaining approval of the proposed route modification since part of it is outside the PFSA. | â€¢ Work will be slowed by VDOT permitting on the Segment 5 reroute and by lack of make-ready completion on Segments 1 and 4. â€¢ Obtaining quick NTIA approval of the new route modification â€¢ Obtaining quick EA addendum and revised PA approval of route modification request. â€¢ Equipment installation progress will be dependent upon manpower resources â€¢ Completion of the proposed reroute work before the December 31, 2012 deadline
NT10BIX5570019 | 2012 | Q3 | Q3 - 2012 | MBC prepared a route modification request to add three schools, one university, and two interconnection points (huts) to the original route at a cost of approximately $2,174,689. The route modification request was approved on August 8, 2012. During this quarter, we have completed engineering and design work and permitting for the new route additions. We have also ordered materials, equipment, and the concrete shelters (huts). The installation of transport equipment continued in the 3rd quarter. We have completed 85% of the installations. One hundred and seventeen (117) CAIâ€™s have been passed in total. There have been three (3) new contracts with last mile providers executed this quarter. This brings the total number of circuits added under this grant to forty-seven (47.). Fiber cable construction has been completed in 3 of the 6 segments, is nearing completion in 2 other segments (waiting on make ready work), and is underway in the last segment. Total miles placed YTD is 413 miles or 96% of this project. During the third quarter we spent $2,287,894, bringing the total amount spent YTD (Federal and Matching) to $16,831,532 (83.93%). The majority of the expenditures were for equipment and materials. The majority of the work activity this quarter was in Buckingham County (Dillwyn). | 413 | 0 | 0 | 0 | 413 | 0 | 0 | 4 | One(1) mile deployed this quarter; 96% of project complete | N/A | N/A | N/A | One(1) mile deployed this quarter; 96% of project complete | N/A | N/A | Two (2) additional sites under construction | 47 | 2 | 12 | Shentel (4); Kinex (6); Lumos (5); GCR(31); BIT(1) Note: The number of contracts is listed in parenthesis. | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 47 | 0 | 0 | 47 | Did not identify any on Baseline | N/A | N/A | Shentel (4) 100 mbps; Kinex (4)10 mbps,(1)50 mbps, (1)100 mbps; GCR (3)10 mbps, (4)20 mbps, (16)50 mbps, (4)100 mbps, (4)200 mbps; BIT (1)50 mbps; Lumos (4)DS-1, (1)OC-3 | 117 | 117 | 0 | 117 | Schools & other government institutions | Schools & other government institutions | N/A | General Offering is 10 mbps to 100 mbps. Open Access: Most schools have 50 mbps service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10 mbps to 100 mbps. Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10 mbps to 100 mbps. Open Access | N/A | FALSE | N/A | â€¢ Continue fiber construction in the remaining 3 segments to completion. â€¢ Complete equipment installation in the two new interconnection points and the remainder of the nodes by 11-30-12. â€¢ Complete all construction and splicing activities to accomplish 100% completion of entire project. â€¢ Increase CAI's served to 118. â€¢ Increase total signed agreements/circuits to 54. | Mid-Atlantic Broadband Cooperative | â€¢ Some make ready work has been delayed by Dominion Power thus delaying our completion of segment 1. â€¢ VDOT approved one of three permits on the Petersburg reroute during Y3Q4. The remaining two permits were approved 9-20-12. This has delayed the completion of segment 5. â€¢ Obtaining private right of way for some portions of the VSU aerial route | â€¢ Obtain completion of make-ready activities along the proposed pole line to VSU. â€¢ Complete the placement of the two huts and fiber cable under the route modification plan â€¢ Complete all of the grant work activities before the December 31, 2012 deadline
NT10BIX5570019 | 2012 | Q4 | Q4 - 2012 | MBC completed all of the construction work on the original project during the 4th quarter, except for approximately 4,000 feet (Segment 1) in Waverly, VA. This work was delayed due to ready-ready issues along the pole line route. We have completed the â€œPetersburg rerouteâ€ along I-85, I-95, and I-295 that was necessary due to conflicts with the original routing in the Petersburg Battlefield Park. A route modification request was approved on August 8, 2012 for this project and construction has been completed on the two proposed new Nodes (huts) and the fiber to Lunenburg County schools. The only construction work remaining to do under the modification is providing fiber facilities to Virginia State University. This part of the project may require another route modification due to aerial and buried right-of-way issues. MBC has applied for a construction extension on this grant from 2-1-13 to 6-30-13, mainly due to delays in obtaining approval of the initial Environmental Assessment, delays with permitting, and three route modifications. The installation of transport equipment continued in the 4rd quarter, however it cannot be completed until the remaining node equipment is installed in the new huts. We have completed 90% of the installations. One hundred and seventeen (117) CAI's have been connected in total. There has been two (2) new contract with last mile providers executed this quarter. This brings the total number of circuits added under this grant to forty-nine (49.) Fiber cable construction has been completed in 4 of the 6 segments, is nearing completion in 1 other segment (waiting on make ready work), and is underway in the 6th segment. Total miles placed YTD is 421 miles or 97% of this project. During the fourth quarter we spent $846,823.62, bringing the total amount spent YTD (Federal and Matching) to $17,678,355.93 (88.15%). The majority of the expenditures were for equipment and materials. The majority of the work activity this quarter was in Prince George County and Petersburg. | 421 | 0 | 0 | 0 | 421 | 0 | 0 | 6 | Eight (8) miles deployed this quarter. 97% of project build complete | N/A | N/A | N/A | Eight (8) miles deployed this quarter. 97% of project build complete | N/A | N/A | All complete | 49 | 2 | 12 | Shentel (4), Kinex (6), Lumos (6), GCR (31), BIT (1), Telpage (1) | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 49 | 0 | 0 | 49 | Did not identify any on Baseline | N/A | N/A | Shentel(4) 100 mbps; Kinex (4) 10 mbps, (1) 50 mbps, (1) 100 mbps; GCR (3) 10 mbps, (4) 20 mbps, (16) 50 mbps, (4) 100 mbps, (4) 200 mbps; BIT(1) 50 mbps; Lumos (4) DS-1, (1) 100 mbps, (1) OC-3; Telpage (1) 50 mbps | 117 | 117 | 0 | 117 | Schools and other government institutions | Schools and other government institutions | N/A | General offering is 10 mbps - 100 mbps - Open Access. Most schools have 50 mbps service | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10 mpbs - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10 mpbs - 100 mbps - Open Access | N/A | FALSE | N/A | â€¢ Complete equipment installation in the two new interconnection points and the remainder of the ring equipment by 6-30-13. â€¢ Complete all construction and splicing activities to accomplish 100% completion of entire project by the end of the second quarter, 2013. â€¢ Increase CAIs served to 118. â€¢ Increase total signed agreements/circuits to 54. | Mid-Atlantic Broadband Cooperative | â€¢ Some make ready work has been delayed by Dominion Power and Verizon, thus delaying our completion of segment 1. â€¢ Constructing the â€œPetersburg rerouteâ€ in a timely manner after delays with VDOT permitting. â€¢ Obtaining private right of way for some portions of the VSU aerial and buried route. | â€¢ Obtain final right of way commitments for construction of the proposed cable to VSU. â€¢ Submit and gain approval of a route change, including EA modification, for a portion of the route to VSU. â€¢ Complete all of the grant work activities before the anticipated June 30, 2013 deadline
NT10BIX5570019 | 2013 | Q1 | Q1 - 2013 | MBC completed the remaining 4,000 feet of aerial cable in Waverly. VA., which was held up by make-ready issues along the pole line route. MBC also completed the â€œPetersburg rerouteâ€ work and approximately 9,000 feet of the Virginia State University route modification work. The remaining 7,000 feet of cable required another route modification due to pole line and buried right of way issues. This was submitted on January 30, 2013. MBC applied for a construction extension on this grant until 6-30-13, mainly due to delays in obtaining approval of the initial Environmental Assessment, delays with permitting, and three route modifications. The extension was approved on January 31, 2013. The installation of transport equipment continued in the 1st quarter, however it couldnâ€™t be completed until the nodes and Waverly-Petersburg fiber were completed. We have completed 95% of the installations. One hundred and seventeen (117) CAIs have been served in total. There have been three (3) new contracts with last mile providers executed this quarter. This brings the total number of circuits added under this grant to fifty-two (52). Fiber cable construction has been completed in 5 of the 6 segments and is nearing completion in the last segment. Total miles placed YTD is 423 miles or 98% of this project. During the fourth quarter we spent $742,168.46, bringing the total amount spent YTD (Federal and Matching) to $18,420,524.39 (91.85%). The majority of the expenditures were for equipment, construction, and retainage. The majority of the work activity this quarter was in Chesterfield County. | 423 | 0 | 0 | 0 | 423 | 0 | 0 | 6 | Two miles deployed this quarter. To be complete by 6-30-13 | N/A | N/A | N/A | Two miles deployed this quarter. To be complete by 6-30-13 | N/A | N/A | All complete | 52 | 10 | 12 | Shentel (4); Kinex (6); Lumos (8); GCR (31); BIT (1); Telpage (2) | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 52 | 0 | 0 | 52 | Did not identify any on Baseline | N/A | N/A | Shentel (4); Kinex (6); Lumos(8); GCR(31); BIT(1); Telpage(2) | 117 | 117 | 0 | 117 | Schools and other government institutions | Schools and other government institutions | N/A | General offering is 10mbps-100mbps; Open Access. Most schools have 50mbps service | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10mbps-100mbps; Open access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General Offering is 10mbps-100mbps; Open access | N/A | FALSE | N/A | â€¢ Complete equipment installation of the Infinera ring by 6-30-13. â€¢ Complete all construction and splicing activities to accomplish 100% completion of entire project by June 30, 2013. â€¢ Increase CAIs served to 118. â€¢ Increase total signed agreements/circuits to 54. â€¢ Gain approval of the VSU reroute request so we can complete construction of segment 1. â€¢ Total miles built by the end of the project is 428. | Mid-Atlantic Broadband Cooperative | â€¢ Obtaining the approval of the VSU reroute request in a timely manner â€¢ Constructing the â€œPetersburg rerouteâ€ in a timely manner after delays with VDOT permitting. â€¢ Failure to obtain private right of way for some portions of the VSU aerial and buried route, thereby requiring preparation of a reroute request. | â€¢ Complete all of the grant work activities before the anticipated June 30, 2013 deadline
NT10BIX5570019 | 2013 | Q2 | Q2 - 2013 | MBC has completed all the fiber construction on this project as there has been no construction activity this quarter. All nodes were completed last quarter, along with equipment installation and splicing. Acceptance testing was completed on all network elements and the UCC-1 filing information was sent to the attorneys to file on the state level last quarter. An audit was conducted this quarter. Only close-out activities have been on-going in this quarter. One hundred and eighteen (118) CAIs have been served in total on this project. The total number of circuits added under this grant was sixty (60). No new contracts were added this quarter. The project total remains at 56 (four (4) disconnected circuits due to BIT). Total miles placed on this project were 428 miles (100%). During the quarter we spent $345,116.18, bringing the total amount spent (Federal and Matching) to $19,053,277 (95%). The majority of the expenditures were for construction, equipment installation, and retainage. | 428 | 0 | 0 | 0 | 428 | 0 | 0 | 6 | Complete | N/A | N/A | N/A | Complete | N/A | N/A | Complete | 60 | 8 | 12 | Shentel(4), Kinex (7), Lumos(11), GCR(31), Telpage (2), Gamewood (1)**BIT (4) **Disconnected four (4) BIT circuits on 5/30/13 which were included in program income. | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 60 | 0 | 0 | 60 | Did not identify any on Baseline | N/A | N/A | Shentel(4), Kinex (7), Lumos (11), GCR (31), BIT (4). Telpage(2),Gamewood (1). General offering is 10mbps - 100mbps - Open Access | 118 | 118 | 0 | 118 | Complete | Complete | N/A | General offering is 10mbps - 100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10mbps - 100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | General offering is 10mbps - 100mbps - Open Access | N/A | FALSE | N/A | â€¢ Completed | Mid-Atlantic Broadband Cooperative | â€¢ Assuring all charges were submitted and all close-out activities were begun as instructed | â€¢ Completed
NT10BIX5570023 | 2010 | Q3 | Q3 - 2010 | 1. Final network design: 80% complete. 2. Compliance review for equipment RFPs complete. 3. Final drafts for Equipment RFPs written and ready for distribution (October 1). 4. Deployment/Installation RFPs development in progress: 50% complete. 5. Civil work bid packages (less than $100,000) being prepared to encourage local bidding. 50% complete. 6. Bulk of commercial tower leases (American Tower/Crown Castle) negotiation of terms completed. 7. Community Outreach plan/Public Relations strategy: 50% complete. 8. Procurement of third party auditing firm complete. 9. Offered services and rate analysis: 70% complete. 10. E-rate registration SPIN number obtained. 11. In Kind assets lease agreement template complete. | 0 | 1240 | 0 | 1240 | 0 | 0 | 0 | 0 | Deployment of wireless network underway in Q1, 2011 | Leased IRU capacity provisioning in progress - first circuits available in Q1, 2011 | Upgrading of netork facilities performed by upstream partner | Leased IRU capacity doesn't differentiate between new or existing network facilities. We assume most/all of the fiber is existing and the equipment is new | Fiber plant owned by Level 3 is existing | Future core network will have 102 links | We are not building any towers. | There will be 102 interconnection points on the core network | 0 | 0 | 0 | None yet. Finalizing products and pricing now with pre-deployment service level agreements. Continuing dialogue with carriers, re- sellers and anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several this quarter and next. | Internet and Transport Services. Services are being offered in standard, premium (protected), and enterprise packages. Will offer term and volume discounts as well. Final list of services matrix is being developed under a rate/services study as part of the update to our initial pricing and services model. | As deployment of the project nears completion, the Authority will advertise in an open and competitive procurement for contract operations services. These services will be performed under the management of Government Services Group, the General Manager of the Authority. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market we will assume that all providers are receiving improved access. | we are in discussion with several providers, agreements pending finalization of product and service plans - which is imminent. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 510 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | 0 | 0 | 0 | 0 | Our plan outlines service to nearly 200 anchor institutions by project closeout. | We will work with our Local Access providers to provide us with this information. | We will assume that if service is provided through our network, that all subscribers that have some kind of service will be receiving improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | No special offerings at this time. Rate and services study to evaluate future additional services/needs/offerings complete. Internal analysis underway. We have secured very substantial capacity to allow third party providers to provide a wide array of services across our network.. The full range of offerings will be determined by the marketplace - but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | 1. Final network design. 2. Equipment RFPs distributed to solicit vendor proposals. 3. Equipment vendor proposals evaluated. 4. Equipment vendors selected to initiate contracting process. 5. Deployment/Installation RFP draft complete. 6. Compliance review for Deployment/Installation RFP complete. 7. Completion of civil work bid packages. 8. Civil work contractors selected; contracting process initiated. 9. Remaining commercial tower leases negotiated and completed. 10. In Kind assets lease agreement drafts completed. | North Florida Broadband Authority | In the previous quarter, the interim network design was re-evaluated, yielding increased reliability, greater capacity, and lower cost. The re-design added time in collecting field data and modifying design parameters pushing procurement and deployment activities back by 30-60 days. Engineering tasks will now be performed simultaneously, regaining the original schedule within the next 60-120 days. Expenditure or funds has been commensurately delayed, moving several of the larger expenses (IRU payment, capital leases) into the next quarter. The recipient in-kind contribution is disproportionate due to the nature of the in-kind contributions. Our city and county membership donated space on municipally-owned towers, buildings, and land. The capital leases are near completion (with the required security interest language), but the site plans, are still being finalized. The prerequisites for site plans include vendor/equipment selection and final network engineering. The final network design should be complete by next quarter, and our equipment procurement period will begin this quarter, with leases ready for submittal to the appropriate local government owner over the following 2-3 quarters. Once the lease is submitted, approved, and recorded, we can begin booking the assets and reporting recipient disbursement on our quarterly SF-425. We anticipate this disproportionate disbursement will continue for the next 2-3 quarters. | The engineer is currently evaluating a number of indeterminate commercial tower sites that need to be vetted for structural and cost concerns. This is due in part to the engineering re-evaluation undertaken in the previous quarter in order to design greater reliability and capacity into the network while still remaining within the original budget. The extra field work and engineering redesign caused a delay in progress against the baseline, but will be made up in subsequent quarters due to working tasks in parallel and providing greater efficiency in the new design and deployment plan. An updated engineering design / route change request will be submitted for approval once the associated route change design parameters are finalized. As a result of the re-evaluation of the design approach, the complexity of the specifications for procurement and the modified requirements for the capacity delivery under the IRU are responsible for the resultant delay in the purchase of equipment, progress payments to Level 3, and the execution of commercial tower leases. As you will notice in the following Infrastructure Budget Execution Details section, that our projected costs for Administrative and Legal expenses and for Architectural and Engineering fees exceed our current allocated budget amount. We plan to submit a budget re-allocation request to the Project Office for these categories in the next quarter.
NT10BIX5570023 | 2010 | Q4 | Q4 - 2010 | 1. Final engineering design is 95% complete, pending final structural assessments. 2. Equipment Request for Proposals (RFPs) were approved and distributed. RFP responses were evaluated and ranked for selection. 3. Equipment RFP vendor rankings and selections were approved by the NFBA Board of Directors. 4. Initial equipment purchase orders were issued for data center equipment and multi-service access platforms. The remainder of data center equipment items and Mulit-Service Access Platforms will be purchased in subsequent quarters. 5. A block of IPv4 numbers were secured upon verification of initial executed equipment purchase orders. 6. Deployment/Installation RFPs development is near completion, pending Davis-Bacon wage decision information. 7. Commercial tower leases negotiation of business terms settled. A generic tower lease agreement contract template draft will be submitted to the Grants Office for their review and authorization of tower lease language. 8. In Kind assets lease agreement template draft completed. 9. Community Outreach Plan/Public Relations strategy is 90% complete. Initial community outreach meetings were a success. 10. Offered services and rate analysis is complete. Initiated development of preliminary draft pricing and service schedule, along with preliminary network and service rate sheets for pre-deployment discount pricing. 11. Upstream Indefeasible Right of Use (IRU) design configuration complete. Circuit delivery is on schedule. Tampa ga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Deployment of the wireless network is expected to be underway in Q1, 2011. As mentioned above, the re-evaluation of the network design approach that began in previous quarters and continued through this reporting quarter has impacted the overall network build progress as anticipated per the baseline plan. Per the baseline plan, we originally planned to have approximately 48 miles of new network miles deployed by the end of this current reporting quarter. However, with equipment procurement currently underway and the expectation that our commercial tower license language will be approved, we anticipate that this indicator will be on track with the baseline plan as network deployment moves forward in subsequent quarters. | In reference to leased upstream fiber, the agreement with Level 3 is in place, the upstream design configuration is complete, and circuit delivery is on schedule, corresponding to approximately 1,240 miles of leased fiber for upstream connection to the Internet backbone. In reference to the core wireless network, all network miles will be considered new. As mentioned above, per the baseline plan, we originally planned to have approximately 48 miles of new network miles deployed by the end of this current reporting quarter. However, with equipment procurement currently underway and the expectation that our commercial tower lease language will be approved, we anticipate that this indicator will be on track with the baseline plan as network deployment moves forward in subsequent quarters. | N/A. Upgrading of network facilities performed by the upstream partner. | N/A. Leased capacity does not differentiate between new or existing network facilities. We assume most/all of the fiber is existing and the equipment is new. | The fiber plant owned by Level 3 is existing. The description for this indicator on the baseline report for this project reads as â€œNumber of miles of fiber (aerial or underground)â€ and does not make the distinction between new or leased miles. Therefore, when drafting the baseline report, in an effort to avoid ambiguity we used the same quarterly numbers from the â€œNew network miles leasedâ€ indicator for the quarterly numbers in this indicator, since these numbers seemed to coincide with each other according the original baseline report indicator descriptions. However, as these indicator descriptions have been altered or clarified in subsequent report forms, it is apparent that we should have placed â€œ0â€ or â€œN/Aâ€ in every quarter for this indicator in the baseline report since we are leasing upstream fiber capacity and have no plans to install new fiber for this project. | The future core network will have 102 wireless links. Per the baseline plan, we originally anticipated that we would have equipment in place at a minimal number (3) of wireless links by the end of this current reporting quarter. With equipment procurement currently underway and the expectation that our commercial tower lease language will be approved, we anticipate that this indicator will be on track with the baseline plan as network deployment moves forward in subsequent quarters. | We are not building any new towers for this project. | We originally anticipated that we would have equipment in place at a minimal number of tower sites by the end of this current reporting quarter. With equipment procurement currently underway and the expectation that our commercial tower lease language will be approved, we anticipate that the number of new interconnection points (for future last mile providers) will be on track with the baseline plan as network deployment moves forward in subsequent quarterst we would have equipment in place at a minimal number of tower sites by the end of this current reporting quarter. With equipment procurement currently underway and the expectation that our commercial tower lease language will be approved, we anticipate that the number of new interconnection points (for future last mile providers) will be on track with the baseline plan as network deployment moves forward in subsequent quarters. | 0 | 0 | 0 | None yet. We are continuing to finalize products and pricing with pre-deployment service level agreements. We have continuing dialogue with carriers, re-sellers, and anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements this quarter and next. | Internet and Transport Services. Services are being offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. A final list of services matrix is being developed under a rate/services study as part of the update to our initial pricing and services model. A preliminary draft copy of our Wholesale - Standard Ethernet Access Pricing matrix is attached. Services are being offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. A final list of services matrix is being developed under a rate/services study as part of the update to our initial pricing and services model. A preliminary draft copy of our Wholesale - Standard Ethernet Access Pricing matrix is attached. | As deployment of the project nears completion, the Authority will advertise in an open and competitive procurement for contract operations services. These services will be performed under the management of Government Services Group, the General Manager of the Authority. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans, which is imminent. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | 0 | 0 | 0 | 0 | Our plan outlines service to 308 anchor institutions by project closeout. | We will work with our Local Access providers to provide us with this information. | We will assume that if service is provided through our network, that all subscribers that have some kind of service will be receiving improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | No special offerings at this time. Rate and services study to evaluate future additional services/needs/offerings is complete. Internal analysis is underway. We have secured very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | 1. Final network design 100% complete, with remaining structural assessments completed. 2. Execute purchase orders to approved vendors to keep equipment procurement ahead of anticipated installation activities. 3. Delivery of initial purchased equipment to staging warehouse. 4. Benchmark testing and asset tagging and management of initial purchased equipment. 5. Installation RFP draft completed to include current Davis-Bacon wage decision information. 6. Installation RFP approved and released. Selection process initiated and completed for Installation contractors. 7. Installation of data center equipment at Level 3â€™s Tampa and Orlando co-location facilities. 8. Commercial tower lease draft template language approved. Commercial tower leases negotiated and executed. 9. Civil work and site preparation to proceed upon execution of commercial tower leases. 10. In Kind asset lease agreement draft language approved. In-kind asset leases negotiated and executed as necessary. 11. Installation of microwave radios and antennas at initial tower sites. 12. Additional community outreach meetings are planned for next quarter. | North Florida Broadband Authority | In previous quarters, the interim network design was re-evaluated and additional engineering resources were added to our project. Although this yielded increased reliability, greater capacity, and lower cost, it has affected the pace at which we planned to expend projected funds, moving several of the larger planned expenses (such as Indefeasible Right of Use payment and tower leases) into subsequent quarters. We will ask the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the lease agreement is in compliance with grant requirements. Our goal is to get this milestone component and the overall project back on schedule over the next few subsequent quarters; therefore, it is imperative that we move forward with the execution of tower license agreements in order to clear the way for site preparation and equipment installation and to avoid impacts to the remainder of the project milestone categories on the scheduleâ€™s critical path. | As mentioned above, we are asking the Grants Office to review a draft template of our master tower lease agreement in order to obtain verification from the Grants Office that the contract language in the license agreement is in compliance with grant requirements. Our goal is to get this milestone component and the overall project back on schedule over the next few subsequent quarters; therefore, it is imperative that we move forward with the execution of tower license agreements in order to clear the way for site preparation and equipment installation and to avoid impacts to the remainder of the project milestone categories on the scheduleâ€™s critical path. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles, specific to the Florida counties in the NFBA network region. With the Award Action Request still pending, we are conducting our own research on this matter and have continued to move forward in the development of the Equipment Installation and Pathing RFP in an effort to minimize any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are also checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Disco
NT10BIX5570023 | 2011 | Q1 | Q1 - 2011 | 1. Commercial tower master site license agreements and individual site license agreement templates were approved by the North Florida Broadband Authority Board of Directors for Crown Castle International and American Tower Company. 2. The master license agreement for in-kind vertical assets was approved by the North Florida Broadband Authority Board of Directors. 3. Final structural assessments have passed for 47 (out of 93) commercial towers in the core network. Site licenses were approved and executed for 38 tower sites in the core network. 4. Equipment purchase orders were issued for routers, multi-service access platforms, and equipment cabinets. Asset tagging and inventory management procedures have been implemented as equipment is received, inventoried, bench tested, palletized, and staged for deployment. 5. Federal Communications Commission license applications have started for microwave radio frequencies, which follow approved structural assessments and the subsequent execution of individual site license agreements for the towers in each corresponding network link. 6. Davis Bacon wage decision determinations were obtained for Tower Technician and Radio Frequency technician job classifications in all core network counties. Technical assistance from the Program Office was instrumental in this process, and with the wage decisions in hand, we were able to go forward this past quarter with the release of the Request for Bids for Equipment Installation and Pathing | 0 | 1620 | 0 | 0 | 1620 | 0 | 0 | 0 | The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | The mileage indicated here represents fiber leased from our upstream provider. | N/A. Upgrade of network facilities is being performed by our upstream provider. | N/A | The mileage indicated here represents fiber leased from our upstream partner. | The future core network will have 102 wireless links. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | N/A | The mileage indicated here represents fiber leased from our upstream partner. The future core network will have 102 wireless links. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. There are 93 primary interconnection points planned for the core network. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plans fiber leased from our upstream partner. The future core network will have 102 wireless links. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. There are 93 primary interconnection points planned for the core network. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | 0 | 0 | 0 | None yet. We are developing our initial service catalog as products, pricing, and pre-deployment service level agreements continue to be finalized and business support system requirements continue to be defined. We have ongoing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. | Internet and transport services. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. We are also reaching out to community anchor institutions in the network region to gage their level of interest as potential beta customers with simplified, straightforward service plans that may be provided on a best-effort basis before the network rings are complete and more formal service level agreement pricing strata are implemented. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. We are also reaching out to community anchor institutions in the network region to gage their level of interest as potential beta customers with simplified, straightforward service plans that may be provided on a best-effort basis before the network rings are complete and more formal service level agreement pricing strata are implemented. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. | As project deployment nears completion, the North Florida Broadband Authority will advertise in an open and competitive procurement for contract operations services. These services will be performed under the management of Government Services Group, the General Manager for the NFBA. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | 0 | 0 | 0 | 0 | Our plan outlines service to 308 anchor institutions by project closeout. | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. The variance from the Baseline Plan is a result of the network design re-evaluation that began in previous quarters. Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available. | No special offerings at this time. Service catalog products and pricing are being developed along with business support system requirements. We have secured very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | 1. Civil and site electrical contractors selected, approved, and under contract. 2. Equipment installation and pathing contractors selected, approved, and under contract. 3. Site license agreements executed for all commercial towers in the core network. 4. Site-specific drawing packages, bill of material lists, and scopes of work complete for all sites in the core network. 5. Pre-deployment site visits and scope reviews complete for civil contractors and equipment installation & pathing contractors. 6. Electrical utility accounts established for all commercial tower sites in the core network. 7. Federal Communications Commission license applications submitted for all core network links, and approved Federal Communications Commission license applications for core network links in the initial phases of deployment. 8. Building and electrical permit applications submitted for all tower sites in the core network, and approved for tower sites in the initial phases of deployment. 9. Purchase orders issued for remaining equipment cabinets, multi-service access platforms, and tower attachment cable and hardware. Purchase orders issued for licensed microwave radios and antennas following approved radio license applications. 10. Routers installed and upstream vertical connectivity complete at all Point-of-Presence and Gateway datacenter locations. 11. Start of civil and site electrical work at tower sites in the initial phases of deployment. 12. Start of installation and pathing work | North Florida Broadband Authority | The following is a summary explanation of the reasons for the variance between Baseline Plan projections and milestone completion percentages experienced this past quarter and in previous quarters: In previous Performance Progress Reports, we reported against Baseline Plan projections and cost classification budget categories that were based on the original turnkey link/spur network design topology and project plan. After a period of re-evaluation, it became evident that the original network design would not meet the carrier-class network performance requirements of our anticipated wholesale customer base. We therefore had to pursue a more robust network design, and that process led to the development of our current interconnected-ring network design topology. To accomplish this transition, engineering consultants were removed and replaced under strict procurement guidelines. This entire process (design re-evaluation, engineering services procurement, and network redesign) was stretched out over a period of two to three quarters, which was the period of time originally designated in the Baseline Plan for the turnkey link design phase as well as subsequent equipment procurement, site acquisition, and pre-deployment activities. In an effort to re-establish accurate baseline and budget progress indicators, we are currently preparing an Award Action Request for the network design changes discussed above. We are also in the process of preparing a budget reallocation Aw | Please see Section 1, Item #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan, as we anticipate these issues to carry forward into the next quarter. In an effort to re-establish accurate baseline and budget progress indicators, we are in the process of preparing Award Action Requests for the following items: - Award Action Request for Network Design Change: We are preparing an Award Action Request to establish that network design has changed from the original Turnkey Link Spur Network design as originally submitted in the grant application to our current network design that utilizes an interconnected, dual counter-rotating resilient packet ring topology in order to meet the carrier-class performance and service level agreement requirements of our anticipated wholesale customer base. - Award Action Request for Budget Reallocation: We are preparing an Award Action Request that reapportions funds to project budget categories according to anticipated and actual expenditures as established by both the network design change and the Program Office's determination of grant-eligible expenses in regard to capital leases. We also submitted an Award Action Request for Davis Bacon wage decisions for Tower Technician and Radio Frequency Technician job classifications in four peripheral counties in which transit towers are located (transit towers are necessary to close network rings in the core service
NT10BIX5570023 | 2011 | Q2 | Q2 - 2011 | BUSINESS DEVELOPMENT ACTIVITIES â€¢ A Work Authorization was issued to the Network Engineer for Early Adopter Assistance and Subscriber Evaluation Services, which includes Customer Relations Management software installation and training. â€¢ Beta Customer Acquisition procedures have been drafted for implementing a structured methodology for obtaining customer feedback and validation for the network design and its associated operations and business support systems. â€¢ A Work Authorization was issued to the Quality Assurance Engineer for review and recommendations for the network's Operations Support System and Business Support System implementation process. PROCUREMENT ACTIVITIES â€¢ Civil Installation Services Request for Bids #2011-08 was released on 6/15/2011 for the procurement of additional subcontractors for civil and site electrical work. The due date for these bids is 07/05/2011, which falls into the next reporting period. SITE ACQUISITION ACTIVITIES â€¢ Site license agreements have been executed for 79 tower sites out of 94 sites total. Site license agreements are pending with the tower companies listed below for the remaining 15 tower sites as follows: - 3 Sites: 52Eighty, LLC (Point of Presence sites): Agreements pending confirmation of site licenses as capital expenses. - 1 Site: American Tower Corporation: Execution of site license agreement is pending (awaiting landlordâ€™s consent). - 3 Sites: Crown Castle International: Structura | 0 | 1620 | 0 | 0 | 1620 | 0 | 0 | 0 | The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | The mileage indicated here represents fiber leased from our upstream provider. | N/A. Upgrade of network facilities is being performed by our upstream provider. | N/A | The mileage indicated here represents fiber leased from our upstream provider. | The core network will have 102 wireless links. The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | N/A | There are 93 primary interconnection points planned for the core network. The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | 0 | 2 | 0 | None yet. We have received a Commitment Letter for a substantial monthly service commitment from one of our last mile partners, and we expect to receive additional Commitment Letters over the next quarter as we continue to actively engage last mile providers in the network region. | Internet and transport services. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. We are also reaching out to community anchor institutions in the network region to gage their level of interest as potential beta customers with simplified, straightforward service plans that may be provided on a best-effort basis before the network rings are complete and more formal service level agreement pricing strata are implemented. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. We are also reaching out to community anchor institutions in the network region to gage their level of interest as potential beta customers with simplified, straightforward service plans that may be provided on a best-effort basis before the network rings are complete and more formal service level agreement pricing strata are implemented. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. | As project deployment nears completion, the North Florida Broadband Authority will advertise in an open and competitive procurement for contract network operations services. These services will be performed under the management of Government Services Group, Inc., the General Manager for the NFBA. Over the next reporting period, we expect to complete the determination of procurement requirements for contract network operations services. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 6, 12, 25, 60, 150Mbps, and can be customized to 1 Gbps. | 0 | 0 | 0 | 0 | Our plan outlines service to 308 anchor institutions by project closeout. | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. The variance from the Baseline Plan is a result of the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (2 months). Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. | Available speed tiers will begin at 6, 12, 25, 60, 150Mbps, and can be customized to 1 Gbps. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | This will depend completely on the retail Last Mile providers | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | This will depend completely on the retail Last Mile providers | No special offerings at this time. Service catalog products and pricing are being developed along with business support system requirements. We have secured very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | BUSINESS DEVELOPMENT ACTIVITIES â€¢ We have received a Commitment Letter for a substantial monthly service commitment from one of our last mile partners, and we expect to receive additional Commitment Letters over the next quarter as we continue to actively engage last mile providers in the network region. â€¢ We expect to engage our initial group of Beta and Early Adopter Customers as network sites are activated, network rings are completed, paths to Point of Presence demarcation sites are established, and last mile access equipment is procured. â€¢ We expect to issue a supplementary Work Authorization to the Quality Assurance Engineer to provide Quality Assurance services for the development, integration, and implementation of the network's Operations Support System, Business Support System, and Customer Relations Management system. â€¢ We also expect to issue a Work Authorization to the Quality Assurance Engineer to provide Quality Assurance services for the integration, implementation, and operation of network elements and devices according to the Open Systems Interconnection model. PROCUREMENT ACTIVITIES We expect to complete the determination of procurement requirements for the following critical network operations components: â€¢ Long-Term Network Operator to manage the network's Operations Support System and Business Support System. â€¢ Network access equipment for last mile providers. Although Multi-Service Access Platforms are currently designated for each tow | North Florida Broadband Authority | The following is an explanation of the reasons for the variance between Baseline Plan projections and milestone completion percentages experienced this past quarter and in previous quarters. This explanation was provided in the previous Performance Progress Report submitted for the first quarter of 2011, but it is summarized again here for continuity and clarity. In previous Performance Progress Reports, we reported against Baseline Plan projections and cost classification budget categories that were based on the original turnkey link/spur network design topology and project plan. As it became evident that the original network design would not meet the carrier-class network performance requirements of our anticipated wholesale customer base, we pursued a more robust network design, which led to the development of our current interconnected-ring network design topology. This entire process (which included design re-evaluation, engineering services procurement, and network redesign) was carried out over a period of two to three quarters, which was the period of time designated in the original Baseline Plan for the turnkey link design phase as well as for subsequent equipment procurement, site acquisition, and pre-deployment activities. Additional variance from the Baseline Plan resulted substantial delays that were incurred awaiting wage-rate determinations (more than 3 months), awaiting a response to a waiver request to allow eligibility of Long term Operational leases ( | Please see Section 1, Item #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. Although we anticipate that these issues will continue into the next few quarters, we expect to achieve resolution toward these matters as the Award Action Requests discussed below are submitted and approved and as the deployment of the network continues to move forward and make progress. In an effort to re-establish accurate baseline and budget progress indicators, we have prepared draft Award Action Requests for review and approval by the Program Office prior to submittal of the following items: - Network Design Change: We drafted and forwarded our Network Design Change Documentation for review and approval (prior to submission of an Award Action Request) to establish that the network design has changed from the original Turnkey Link Spur Network design as originally submitted in the grant application to our current network design, which utilizes an interconnected, dual counter-rotating resilient packet ring topology in order to meet the carrier-class performance and service level agreement requirements of our anticipated wholesale customer base. - Budget Reallocation: We drafted a budget re-allocation for the Program Office for the purposes of re-aligning the budget following the microwave re-design and route change. Greater expenditures are required for engineering and program management services, and the r
NT10BIX5570023 | 2011 | Q3 | Q3 - 2011 | (Please note: The Certifying Officialâ€™s name and contact information needs to be updated on this form. This information is automatically generated in the Program Officeâ€™s Adobe form for the Performance Progress Report. It is our understanding that these fields cannot be edited or changed without an Administratorâ€™s permission.) We confirmed our inventory of in-kind assets committed to the project by our local member governments. We streamlined our site acquisition process for in-kind assets, and we have compiled legal descriptions, parcel identification numbers, and other legal data necessary to formally execute site lease agreements with in-kind asset owners. We received a written commitment from Main Street Broadband (CityNet, LLC) to purchase 15 Gb of bandwidth for $240,000 per month in increments starting when our first network ring and path to Point of Presence are available, properly tested, operational, and customers are ready to be brought on the network. This commitment represents over $2.8 million of potential revenue per year for the next five years. We made significant progress with the deployment of our core network during the 3rd Quarter of 2011. During this reporting period, workers and supervisors were in the field performing the following network deployment tasks: â€¢ Site preparation, trenching, and installation of conduit and wire for underground electrical work. â€¢ Coordination with local electrical utility companies to make final sit | 0 | 1620 | 0 | 0 | 1620 | 0 | 0 | 0 | Significant progress was made in the field due to the efforts of our deployment contractors this past quarter. Variance from Baseline is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. According to our projections, we would have made substantial progress toward our Baseline goal if deployment had not been interrupted by this suspension. Substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on | The mileage indicated here represents fiber leased from our upstream provider. | N/A. Upgrade of network facilities is being performed by our upstream provider. | N/A | The mileage indicated here represents fiber leased from our upstream provider. | The core network will have 102 wireless links. Variance from Baseline is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. According to our projections, we would have made substantial progress toward our Baseline goal if deployment had not been interrupted by this suspension. Substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (submitted for comment in March 2011, AAR | N/A | Substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (submitted for comment in March 2011, AAR submitted in July 2011, still awaiting response). Upon reinstatement of Federal funding (expected to occur in late October 2011), we expect to make significant progress toward reaching our Baseline projection for this categoryt were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (submitted for comment in March 2011, AAR submitted in July 2011, still awaiting response). Upon reinstatement of Federal funding (expected to occur in late October 2011), we expect to make significant progress toward reaching our Baseline projection for this category. | 0 | 2 | 0 | None yet. We have received a Commitment Letter for a substantial monthly service commitment from one of our last mile partners. Following reinstatement of Federal funding and upon resumption of network deployment activities, we expect to receive additional commitment letters and execute signed agreements over the next quarter as we continue to actively engage last mile providers in the network region. | Internet and transport services. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. We continued to reach out to community anchor institutions in the network region to gage their level of interest as potential early adopter customers with simplified, straightforward service plans that may be provided on a best-effort basis before the network rings are complete and more formal service level agreement pricing strata are implemented. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached.3 | As project deployment nears completion, the North Florida Broadband Authority will advertise in an open and competitive procurement for contract network operations services. These services will be performed under the oversight of the North Florida Broadband Authority Board of Directors. We expected to complete the determination of procurement requirements for contract network operations services during this current reporting period. However, the suspension of Federal grant funding has pushed this activity into the next reporting period. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans and the reinstatement of Federal funding. The variance from the Baseline Plan is primarily the result of (1) the use of resources to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011, as well as the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Prog | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 6, 12, 25, 60, 150Mbps, and can be customized to 1 Gbps. | 0 | 0 | 0 | 0 | Our plan outlines service to 308 anchor institutions by project closeout. | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. The variance from the Baseline Plan is primarily the result of suspension of Federal grant funding this past quarter as well as the network design re-evaluation and re-engineering process that began in previous quarters. In addition, substantial delays in deployment were also incurred awaiting Davis Bacon wage-rate determinations (more than 3 months), which delayed the procurement of our equipment installation contractors; awaiting a response to a waiver request to allow eligibility of Long term Operational leases (requested process in December, 2010, AAR submitted in April 2011, received in June, 2011); and comments from the Program Office on a Route Change Request (submitted for comment in March 2011, AAR submitted in July 2011, still awaiting response). Upon reinstatement of Federal funding (expected to occur in late October 2011), we | Available speed tiers will begin at 6, 12, 25, 60, 150Mbps, and can be customized to 1 Gbps. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | This will depend completely on the retail Last Mile providers. | 0 | 0 | 0 | 0 | 0 | When completed, the NFBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | This will depend completely on the retail Last Mile providers. | No special offerings at this time. Service catalog products and pricing are being developed along with business support system requirements. We have secured very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | The overall project will be Substantially Complete before the end of next quarter based on expenditures to date (as defined per SF-270), projected expenditures, and in-kind contributions for our recipient match. We will implement a Transition Plan that will allow the project to move forward into its next phase of operations. In accordance with the recommendations and guidance from the Program Office, our Transition Plan sets forth the steps necessary to augment the North Florida Broadband Authority's organizational capabilities in order to assume "in-house" control of many functions formerly provided through contracted general management services. The North Florida Broadband Authority (NFBA) is hiring an Interim General Manager as a direct employee to execute this transition process. The Interim General Manager reports directly to the NFBA Board of Directors and will be the NFBA executive with overall responsibility for project management, operations, vendor and contractor management, human resources, and all other NFBA executive functions. The Interim General Manager will be supported in her role by key "in-house" direct employees as well as by the services of Jacobs Telecommunications, Inc., which has been engaged to provide comprehensive project management services that were formally provided by valued vendor resources that voluntarily stepped aside during this transition period. In addition, Jacobs will provide general contracting and deployment oversight servic | North Florida Broadband Authority | Planned project progress was significantly impacted by (1) compliance with the directive to prepare a Corrective Action Plan, as directed by the Program and Grants Offices; (2) the suspension of payments under the Grant Award, effective August 18, 2011; and (3) the suspension of the Grant Award effective September 21, 2011. We are pleased to report that our Corrective Action Plan was accepted and Federal funding is expected to be reinstated (in some capacity) by late October 2011. As Federal funding is reinstated, assistance from the BTOP program would be useful in helping us to identify ways to be proactive in our compliance with Federal program guidelines to ensure that grant funding remains available for the North Florida Broadband Authority to re-establish and maintain momentum as we continue to work with the Program Office toward our mutual goals of creating jobs and stimulating economic development for our citizens and communities. | The most significant challenge awaiting us next quarter (next reporting period) stems from the transition process (described above) that must be undertaken due to the events of this recent reporting period. As Federal funding is reinstated (anticipated October 2011), it is critical that grant funding remains available and accessible per the original draw schedule as necessary to allow us to acquire and employ the resources necessary to accelerate the project schedule and to re-establish the momentum that we had achieved previously in the deployment of our core network. As we move forward, we have identified the following area where assistance from the BTOP program would be useful and sincerely appreciated: According to Section 2.3 of the BTOP / NTIA "FY11 BTOP Monitoring and Assessment Plan, "At the conclusion of the site visit, the program office staff will develop a draft Site Visit Report that documents the findings and conclusions from the visit. A copy of the final Site Visit Report will be sent to the recipient indicating the results of the visit." Program Office staff visited our project in March 2011 and reviewed our organizational structure, vendor oversight, financial controls, and overall project progress. However, we still have not received our Site Visit Report from that meeting. As this might be an internal technical matter, assistance from the BTOP program would be useful in providing us with a copy of our March 2011 Site Visit Report and with copies o
NT10BIX5570023 | 2011 | Q4 | Q4 - 2011 | The 4th Quarter was a very productive quarter with a lot of activity. The suspension of the award was lifted, and the NFBA successfully developed and executed a Corrective Action Plan (CAP) approved by the Grants Office. In doing so, the NFBA hired employee staff for vendor oversight and monitoring progress going forward. The NFBA Board elected a new Chairman and, in the course of executing the CAP, procured new engineering, project management, financial accounting, general counsel, and compliance services. With the suspension lifted, the NFBA was also again able to issue payment for services and equipment related to the deployment of the NFBA system. Additional resources were procured to assume responsibility for the continued design and construction of the NFBA network and successfully obtained NFBA assets from the previous Engineer, which are now stored in an NFBA-owned warehouse. The network design is still under review and the NFBA started to obtain permits for construction of towers and has tower construction firms under contract to construct the system. Work will continue into next quarter in regards to verifying asset inventories, design details and network performance characteristics necessary for successful marketing of the system. NFBA was also able to book substantial in-kind matching contributions to the project, chiefly tower sites contributed by NFBA member governments and identified in Memoranda of Understanding and resolutions adopted by the member governments. This process will continue in 1Q2012. In addition, the Outreach program has been re-established in full form and additional Marketing approaches have been discussed. We continue to reach out to CAIs to keep them informed of the target deployment dates. During this quarter, the NFBA laid the groundwork for a stakeholder outreach event to be held in February 2012, as well as the solicitation of a network operator to operate and maintain the network. | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | Progress was delayed while transition plan was being executed and transfer of equipment took place. | Fiber leased from our upstream provider | n/a | n/a | n/a | Progress was delayed while transition plan was being executed and transfer of equipment took place. | n/a | Progress was delayed while transition plan was being executed and transfer of equipment took place. | 0 | 2 | 0 | None. We are planning a stakeholder outreach event for February 2012 to provide information on NFBA's plans and network capabilities. We are working diligently to be able to provide updated information on specific routes and points of interconnection. | We are engaging in a marketing analysis to determine current pricing structures in the rural areas. The current pricing structure is outdated. Once the rate analysis study is completed, we will present it to the NTIA. | An RFI for Network Operator services will be issued in February 2012. An RFP is currently under development to obtain vendors who could provide network operational services to the NFBA. This RFP will be distributed 2nd quarter 2012. | 0 | 0 | 0 | 0 | Progress was delayed while transition plan was being executed and transfer of equipment took place. | Progress was delayed while transition plan was being executed and transfer of equipment took place. | N/A | We are engaging in a marketing analysis to validate previous delineated service offerings. Once complete we will outline service offerings and pricing. | 0 | 0 | 0 | 0 | Progress was delayed while transition plan was being executed and transfer of equipment took place. | Progress was delayed while transition plan was being executed and transfer of equipment took place. | Progress was delayed while transition plan was being executed and transfer of equipment took place. | We are engaging in a marketing analysis to validate previous delineated service offerings. Once complete we will outline service offerings and pricing. | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | n/a | n/a | n/a | n/a | We are engaging in a marketing analysis to outline potential service offerings. This will be underway 1st quarter 2012. | TRUE | The Network management policies are available to the public for review at anytime. Just request a copy from the website via e-mail and they will be provided. | Next Quarter will show significant movement with the project as described in the CAP and Transition Plan, with equipment moved and inventoried, and vendors re-engaged. Some of these milestones are as follows: - Budget Reallocation completed. - Deployment continues. - Network commissioning to begin. - RFP for Operator Network Monitor under development. - Last Mile Providers identified and negotiations to begin. - New network miles will begin to increase significantly as POP sites are built with equipment. Goal is to reach 300 additional miles - Commence execution of site leases with county governments for additional in-kind contributions of tower sites, and to memorialize the terms of those previously contributed. | North Florida Broadband Authority | NFBA overcame several obstacles during this reporting period, and is poised to make rapid and efficient progress during the upcoming quarter and throughout 2012. With valuable assistance from federal Program and Grants Office representatives, NFBA addressed performance concerns that led to the suspension of its award, developed and implemented a CAP and associated Transition Plan, and terminated or substantially restructured its relationship with several key vendors. NFBA employees assumed significant operational responsibilities formerly discharged by contractor staff. Teams are now assembled and the Transition Plan has been executed, with the final parts of the transition (to new accounting and IT service vendors) scheduled to be completed in 1st quarter 2012. | Timely approval of the budget reallocation is pertinent in moving the project forward so the NFBA can adjust budget numbers and time frames that represent reality and can report appropriately going forward.
NT10BIX5570023 | 2012 | Q1 | Q1 - 2012 | The project experienced another productive quarter as we successfully navigated through remaining transition activities while making considerable progress with network deployment and customer acquisition. As a result, the project reached its Substantial Completion milestone during this quarter. We finalized and submitted our Budget Reallocation Award Action Request; approval is still pending as of the closing date of this reporting period. Our project management team developed and released a Request for Proposal procurement document for the acquisition of Network Operator services. We completed a market and rate study to develop customer growth forecasts for our network services portfolio and to provide current-state assessments and future-state recommendations for business planning and organizational activities. Our general management staff hosted a Stakeholder Workshop this quarter to build relationships with the local broadband service providers in our service area. This event proved to be effective as we were able to provide these local service providers with the latest information regarding the status and direction of our network deployment. We also invited them to discuss their expectations for bandwidth and services in an open forum where they provided us with important feedback. As part of our ongoing proactive effort to ensure that our network capabilities are aligned with actual market conditions and anticipated customer demand, we brought all of our vendors together to assess the current network design. Following this assessment, and in accordance with industry best practices, we developed a strategy for near-term and long-term network performance upgrades, which include increasing network capacity at key wireless links for greater backhaul bandwidth and identifying additional fiber access points. We completed our physical inventory assessment of previously-purchased network equipment. Equipment assembly, configuration, testing, and staging activities resumed this past reporting period, and there were noticeable improvements in process efficiency and transparency that were gained by having the performance of these key functions (and the oversight of same) centralized at our Lake City warehouse. Network deployment progress was re-established this past quarter as follows: â€¢ The process of transferring site permits to our new General Contractor was completed. â€¢ Vendor contracts for civil work and tower equipment installation were renegotiated and re-executed. â€¢ With the redeployment of these contractors, civil and site electrical work is now complete at 74 core network tower sites. â€¢ Installation of licensed microwave radios and antennas, multi-service access platforms, and tower cabling is now complete at 42 core network tower sites. Equipment in place at towers within a direct line of site account for 37 network links and 262 new network miles deployed this quarter. â€¢ Path alignment and end-to-end testing between core network tower sites started this past quarter and was completed for network sites adjacent to our first operational fiber access point in Branford, Florida. These sites were then placed on air for transmitting high-speed broadband traffic and were made available for customer access. Our first fiber access point in Branford was brought online and connected with redundant fiber links to our Tampa and Orlando datacenters, which became operational this past quarter. Deployment activities resumed at our other Fiber Access Point sites. Network management system servers and software were installed and configured, and we are now monitoring live network traffic as the network is being built out. We continued to book substantial in-kind matching contributions to the project, where our booked match will result in meeting our obligations for match by grant close. These contributions are identified in Memoranda of Understanding and resolutions adopted by our member governments. This process will continue through the end of the project. We are pleased to report that we connected our first customer, a local broadband service provider. Connectivity was also established for a medical facility in our service area, which is the first community anchor institution to be served by the North Florida Broadband Authority network. | 262 | 1620 | 0 | 0 | 0 | 37 | 0 | 42 | This amount represents new network miles deployed as determined by equipment installed at towers within a direct line of sight. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. All new core wireless network miles are scheduled to be deployed by the end of next quarter (720 miles total). | This amount represents fiber leased from our upstream provider. | N/A | N/A | N/A | Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. All new core network wireless links planned for deployment are expected to be completed by the end of next quarter (99 new core network wireless links total). | N/A | Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. All planned core network interconnection points are expected to be completed by the end of next quarter (92 new core network interconnection points total). | 0 | 2 | 0 | Although we were in active negotiations with last mile providers in our service area, there are no signed agreements as of the closing date if this past reporting quarter. We connected one of our last mile partners to our core network for testing purposes during this past quarter, and this connection will be translated into a signed agreement with an expected term of 36 months (12 quarters). | We completed a marketing and rate analysis to determine current pricing structures in the rural areas because the previously submitted pricing structure raised questions. We are currently in the process of updating and finalizing our service offerings and pricing. | We developed and released a Request for Proposal procurement document for the acquisition of Network Operator services. Responses to this Request for Proposal are due next quarter, and we expect to execute a master service agreement with a selected and approved respondent shortly thereafter. | 0 | 0 | 0 | 0 | We are in active negotiations with last mile providers in our service area. We connected one of our last mile partners to our core network this past quarter, and this connection will be translated into a signed agreement. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. We are in position to complete core network deployment by the end of next quarter, and we expect to sign agreements with last mile providers as network sites are activated, tested, and made available for last mile providers to receive new access. | We are in active negotiations with last mile providers in our service area. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. We are in position to complete the core network by the end of next quarter, and we expect to sign agreements with last mile providers as network sites are activated, tested, and made available for last mile providers to receive improved access. | N/A | We completed a marketing and rate analysis to validate previous delineated service offerings, and we are currently in the process of updating and finalizing our service offerings and pricing. | 1 | 0 | 1 | 0 | Connectivity was established this quarter for a not-for-profit medical facility that is now being served by the North Florida Broadband Authority network. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. We are in position to complete the core network by the end of next quarter, and we anticipate more community anchor institutions will be served as our network sites are tested, activated, and made available for customer access. | N/A | We assume that all subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Connectivity was established this quarter for a not-for-profit medical facility that is now receiving improved access from being served by the North Florida Broadband Authority network. Variance from the baseline plan is largely the result of issues that began in previous quarters and carried over into this reporting period. Please see Section 3 above for more details. We are in position to complete the core network by the end of next quarter, and we anticipate more community anchor institutions will be served as our network sites are tested, activated, and made available for customer access. | We completed a marketing and rate analysis to validate previous delineated service offerings, and we are currently in the process of updating and finalizing our service offerings and pricing. | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We completed a market and rate analysis to develop customer growth forecasts for our network services portfolio and to provide current-state assessments and future-state recommendations for business planning and organizational activities. We are currently in the process of updating and finalizing our service offerings and pricing. | FALSE | N/A | The following accomplishments are planned for next quarter: â€¢ Receipt and evaluation of Request for Proposal responses for Network Operator services, followed by the execution of a master contract with the selected and approved respondent. â€¢ Installation of remaining operational support software at our network datacenters. â€¢ We expect to complete the deployment of our core network by the end of next quarter as follows: - Fiber Access Points (Points of Presence) completed and connected to our datacenters with redundant fiber links. - Continuation and completion of equipment assembly, configuration, and testing at our Lake City warehouse and staging facility. - Completion of civil work and equipment installation at remaining core network tower sites. - Completion of link pathing and alignment at core network tower sites, moving outward from our Fiber Access Point sites. - Completion of end-to-end site testing. This activity will closely follow link pathing and alignment at core network tower sites. - As core network sites are brought onto the network, they will be monitored with our network and element management platform. Based on these projections for deployment progress next quarter, we expect to have 92 interconnection points completed and available for customer access, with 99 wireless links and 720 total new network miles deployed. We anticipate the approval of our Budget Reallocation Award Action Request by early next quarter. Although the aggregate budget will not change, the reallocation of funds among the projectâ€™s individual cost classification categories will accurately reflect our current post-transition state and provide an appropriate framework for monitoring, controlling, and reporting cost and schedule performance from this point forward (2nd Quarter 2012) through the remainder of the grant period. We will continue to plan workshops and seek other opportunities to build and leverage our relationships with the local broadband service providers in our service area. With this continued focus on customer outreach and contract negotiations, we expect to have agreements signed with 2 last mile providers by the end of next quarter. Also, according to our projections, connectivity will be provided for 4 Community Anchor Institutions (medical facilities) that will be served by the North Florida Broadband Authority network. As a footnote, quarterly Performance Progress Reports from this point forward (including this report) reflect the status of in-kind contributions as defined per the restated financial information established through our third-party auditing firm. Please note that the quarterly Performance Progress Reports that were submitted previously will not be restated to reflect this information (which will be accurately reflected going forward). | North Florida Broadband Authority | We were able to work through substantial challenges experienced this past quarter, including the engagement of a new project accounting firm, the transfer of institutional knowledge to our new project lead accountant, and the subsequent loss of our project lead accountant to a sudden fatal illness. Our general management staff is working closely with our accounting firm to ensure that project accounting services continue to be provided with the same degree of effectiveness demonstrated in previous quarters. Over the course of performing ongoing site quality control and testing activities, our project management team dealt with residual issues that began in previous quarters and carried over into this reporting period. Site-installed network equipment is exceeding manufacturer-recommended operating temperatures inside the field equipment cabinets that were originally specified for this project. The cabinetâ€™s integral fan unit does not circulate and ventilate air sufficiently enough to cool the electronic devices operating inside the cabinet. Our staff took immediate action and we are working closely with our new Engineering and Project Management vendors to address this situation. Our remediation strategy includes retrofitting the cabinets with integral air conditioning units to ensure that site equipment operating temperatures fall within acceptable control limits. We also discovered that the site coordinates originally provided for FCC license applications were inc | We anticipate that some of the challenges and issues faced during this current reporting period will continue into the next quarter. Our new accounting services firm assigned a new lead accountant for the project, and this person will have to be brought up to speed through the transfer of institutional knowledge while adjusting to their increased role and responsibilities. We will also continue to develop, implement, and monitor our remediation plan for retrofitting field equipment cabinets with integral air conditioning units. Ospreys have nested on several of our core network towers. As a result, Crown Castle is slowing down their Notice to Proceed process, which will restrict our access to these tower sites and cause delays. Our staff and project management team are working closely with Crown Castle to minimize the impact to the deployment schedule while ensuring that appropriate guidelines are followed for migratory bird protection.
NT10BIX5570023 | 2012 | Q2 | Q2 - 2012 | Our Budget Reallocation Award Action Request was approved this quarter. From this point forward, beginning with this Performance Progress Report, we will report progress according to the reallocation of funds among the project's individual cost classification categories as set forth below in the Infrastructure Budget Execution Details section of this report. Please note the following: â€¢ Progress reported against our approved revised budget may result in some milestone category completion percentages being decreased in comparison to our previous Performance Progress Report, which is due to the re-allocation of funds among related cost categories. Since progress is measured by expenditures against budget categories, an increase to a budget category amount (per the approved budget reallocation) may translate to an associated decrease in a completion percentage for a related milestone category. Please see Section 2 below for additional details. â€¢ Our aggregate project budget amount has not changed; however, per our approved Award Action Request, budget funds were reallocated among the project's individual cost classification categories in order to reflect our post-transition state and to provide a corresponding framework for monitoring, controlling, and reporting cost and schedule performance. We received responses to our Request for Proposal for Network Operator services. Our Evaluation Committee calculated final scores and rankings based on four scoring areas: (1) technical qualifications, (2) written proposals, (3) oral presentations, and (4) price. Following this process, a respondent was subsequently identified for consideration to enter into contract negotiations. Network deployment progress continued through this past quarter as follows: â€¢ The fiber design was finalized for our Fiber Access Points (Point of Presence sites) located in the cities of Monticello, Chiefland, and Live Oak. Fiber connections are also complete at these sites with the activation of redundant fiber links back to our core data centers in Orlando and Tampa. â€¢ Civil and site electrical work is complete at 89 out of 92 core network tower sites. â€¢ Installation of site network equipment, cabling, and licensed microwave radios and antennas is complete at 87 core network sites, representing 620 new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. â€¢ Path alignment is complete for 63 network links as we continue to deploy network paths outward from our Fiber Access Points. â€¢ End-to-end testing for throughput and link reliability continued through this quarter, and we are continuing to see positive results. â€¢ We are now monitoring traffic at 22 core network sites with our network performance monitoring and management software platform. â€¢ Integral A/C units were ordered for all core network tower sites, and 87 of these units have been installed at sites located along network segments that provide paths back to our Fiber Access Points. As a result of our deployment progress this quarter: â€¢ 620 total new (wireless) core network miles are deployed; â€¢ 88 wireless links are deployed, and; â€¢ 87 interconnection points are complete and being made available for customer access. We continued with our proactive effort to ensure that our network capabilities are aligned with actual market conditions and anticipated customer demand. We implemented our plan for system enhancements, which include increasing network capacity at key wireless links for greater backhaul bandwidth. To support this effort, we developed and released a Request for Bids procurement document for additional Fiber Access Points in strategic areas of our core network. We successfully implemented our remediation plan for retrofitting field equipment cabinets with integral air conditioning units. Our tests confirm that operating temperatures are within acceptable limits for cabinet-mounted site equipment. We continued to book in-kind matching contributions to the project, where our booked match will result in meeting our obligations for match by grant close. These contributions are identified in Memoranda of Understanding, Resolutions of Intent, and Site Lease Agreements adopted and executed by our member governments. This process will continue through the end of the project. We also continued our focus on customer outreach and negotiations with last mile providers. Agreements are executed with 1 last mile provider in our network service region, and connectivity is being provided for a Community Anchor Institution (medical facility) that is being served by the North Florida Broadband Authority network. | 620 | 1620 | 0 | 0 | 0 | 88 | 0 | 87 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. All new core wireless network miles are scheduled to be deployed by the end of next quarter (720 miles total). | This amount represents fiber leased from our upstream provider. | N/A | N/A | N/A | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. All new core network wireless links planned for deployment are expected to be completed by the end of next quarter (99 new core network wireless links total). | N/A | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. All planned core network interconnection points are expected to be completed by the end of next quarter (92 new core network interconnection points total). | 1 | 2 | 12 | â€¢ Main Street Broadband | We are currently in the process of updating and finalizing our service offerings and pricing. | We received responses to our Request for Proposal for Network Operator services this quarter. These responses were evaluated, and a respondent was identified for consideration to enter into contract negotiations. | 0 | 1 | 0 | 0 | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We remain in active negotiations with last mile providers, and we will continue to plan workshops and seek other opportunities to build and leverage these relationships. We are in position to complete core network deployment before the end of next quarter and expect to sign additional agreements as more network sites are activated and made available for last mile providers to receive new access. | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We remain in active negotiations with last mile providers, and we are in position to complete core network deployment before the end of next quarter. We expect to sign additional agreements as more network sites are activated and made available for last mile providers to receive improved access. | N/A | We are currently in the process of updating and finalizing our service offerings and pricing. | 1 | 0 | 1 | 0 | Connectivity is established for a not-for-profit medical facility that is being served by the North Florida Broadband Authority network. Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We are in position to complete core network deployment before the end of next quarter, and we anticipate more Community Anchor Institutions will be served as more network sites are activated and made available for customer access. | N/A | We assume that all subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We are in position to complete core network deployment before the end of next quarter, and we anticipate more Community Anchor Institutions will be served as more network sites are activated and made available for customer access. | We are currently in the process of updating and finalizing our service offerings and pricing. | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are currently in the process of updating and finalizing our service offerings and pricing. | FALSE | N/A | The following accomplishments are planned for next quarter: â€¢ We expect to execute a master services agreement with the selected and approved respondent to our Request for Proposal for Network Operator Services. â€¢ Receipt and evaluation of responses to our Request for Proposal for additional Fiber Access Points, followed by the execution of a master agreement with the selected and approved respondent(s). â€¢ We expect to complete the deployment of our core network by the end of next quarter as follows: - Completion of civil work and equipment installation at our remaining core network tower sites. - Completion of link alignment and end-to-end site testing at our remaining core network tower sites. - We will continue to monitor our core network with our element management platform as more sites are deployed. Based on these projections for deployment progress next quarter, we expect to have 92 interconnection points completed, with 99 wireless links and 720 total new network miles deployed. We will continue to seek opportunities to build and leverage our relationships with the local broadband service providers in our service area. With this continued focus on customer outreach and contract negotiations, we expect to have agreements signed with 2 additional last mile providers by the end of next quarter. We also anticipate that by the end of next quarter, connectivity will be provided for 3 new Community Anchor Institutions that will be served by the North Florida Broadband Authority network. | North Florida Broadband Authority | Severe thunderstorms and flooding from Tropical Storm Debby caused sporadic site power outages throughout our core network region, disrupting remaining link alignment and end-to-end testing activities. We nevertheless remain on target with our original baseline plan, and we are working closely with the local utility companies in our service area to ensure that interruptions to electrical service are immediately addressed. We have Osprey nests on two of our core network towers, which prevents us from installing microwave antennas and tower cables at these locations. Our staff and project management team are working closely with the tower companies to mitigate any further impact to the deployment schedule while ensuring that appropriate guidelines are followed for migratory bird protection. Permit applications needed to be resubmitted for three of our core network tower sites, which delayed deployment activities at these locations. Our General Contractor and project management team are working closely with the local permitting agencies to expedite this process. | We anticipate that some of the challenges faced during this current reporting period will continue into the next quarter. We expect to resolve the issue with Osprey nests at two of our core network towers next quarter, which will allow us to proceed with the installation of antennas and tower cables, link alignment, and end-to-end testing at these locations. We also expect to obtain approval of our resubmitted permit applications for three of our remaining core network towers next quarter, which will allow us to complete civil work, equipment installation, link alignment, and end-to-end testing activities at these locations.
NT10BIX5570023 | 2012 | Q3 | Q3 - 2012 | We evaluated responses to our Request for Proposal for Network Operator services. The Board of Directors formally approved an agreement with the vendor recommended by our Evaluation Committee. Our network engineering and deployment management team subsequently initiated the process of transferring network documentation to the awarded Network Operator in order to facilitate the development of the selected vendor's network management system. We experienced progress with our core network deployment as follows: â€¢ Civil and site electrical work is complete at 91 out of 92 core network tower sites. â€¢ Installation of site network equipment, cabling, and licensed microwave radios and antennas is complete at 91 core network sites, representing 97 new wireless links and 692 new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. â€¢ We received the necessary permissions and releases to work on our core tower sites that had migratory bird nests. Site preparation and equipment installation activities are complete at these sites. â€¢ Path alignment is complete for 95 core network links as we continue to deploy network paths outward from our Fiber Access Points. End-to-end testing for throughput and link reliability continued through this quarter, and we are continuing to see positive results. â€¢ We are monitoring equipment performance at all 92 core network sites with our network element management software platform. â€¢ Air conditioning units were installed at 91 designated core network tower sites, as we successfully executed our plan to retrofit field equipment cabinets. We are continuing to monitor operating temperatures to ensure that they fall within acceptable limits for site-installed network equipment. (An air conditioning unit retrofit was not required at one of our core network sites.) As a result of our deployment progress this quarter: â€¢ 692 total new (wireless) core network miles are deployed; â€¢ 97 wireless links are deployed, and; â€¢ 91 interconnection points are complete and being made available for customer access. We continued to execute our network enhancement strategy to align capacity and performance requirements with anticipated demand. Additional licensed microwave radios and antennas were specified and ordered, and our first round of network enhancement equipment was received. Preparations are being made for testing and staging this equipment at our Lake City warehouse. We also initiated the procurement process for additional fiber access points to increase network capacity at key wireless links for greater backhaul bandwidth. Qualified bids were received and evaluated this quarter, and we are currently in negotiations with the recommended fiber access point provider. We continued to book in-kind matching contributions to the project, where our booked match will result in meeting our obligations for match by grant close. These contributions are identified in Memoranda of Understanding, Resolutions of Intent, and Site Lease Agreements adopted and executed by our member governments. This process will continue through the end of the project. We maintained our efforts toward customer outreach and with building relationships with last mile providers. Agreements are executed with 1 last mile provider in our network service region and we are continuing to connect Community Anchor Institutions to the North Florida Broadband Authority network. | 692 | 1620 | 0 | 0 | 0 | 97 | 0 | 91 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. With the planned completion of our last remaining core tower site, all new core wireless network miles will be deployed by the end of next quarter (720 miles total). | This amount represents fiber leased from our upstream provider. | N/A | N/A | N/A | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. With the planned completion of our last remaining core tower site, all new core network wireless links planned for deployment are expected to be completed by the end of next quarter (99 new core network wireless links total). | N/A | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. With the planned completion of our last remaining core tower site, all planned core network interconnection points are expected to be completed by the end of next quarter (92 new core network interconnection points total). | 1 | 2 | 12 | Suwannee Valley Internet and Computers (SVIC) | We are currently in the process of updating and finalizing our service offerings and pricing, and we have finalized requirements for our Service Level Agreement with Last Mile providers. | The Board of Directors formally approved an agreement with our selected Network Operator contractor: INOC: INOC Madison Office 2810 Crossroads Drive, Suite 2600 Madison, WI 53718, USA (608) 663-4555 phone (608) 663-4558 fax www.inoc.com Our network engineering and deployment management team subsequently initiated the process of transferring network documentation to the awarded Network Operator in order to facilitate the development of the selected vendor's network management system. | 0 | 1 | 0 | 1 | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We remain in active negotiations with last mile providers, and we will continue to plan workshops and seek other opportunities to build and leverage these relationships. | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We remain in active negotiations with last mile providers and expect to sign additional agreements as our core network will be completed by next quarter and all core interconnection points will be made available for last mile providers to receive improved access. | N/A | Internet (Per Mbps) / # Customers 10 20 50 100 200 300 400 500 1000 - 1 Transport (Per Mbps) 10 20 50 100 200 300 400 500 1000 | 10 | 0 | 10 | 0 | Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We anticipate more Community Anchor Institutions will be served as our core network will be completed by next quarter and all core interconnection points will be made available for customer access. | N/A | We assume that all subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to challenges faced this reporting period. Please see Section 3 above for more details. We anticipate more Community Anchor Institutions will be served as our core network will be completed by next quarter and all core interconnection points will be made available for customer access. | Internet (Per Mbps) 10 20 50 100 200 300 400 500 1000 Transport (Per Mbps) 10 20 50 100 200 300 400 500 1000 | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are currently in the process of updating and finalizing our service offerings and pricing, and we have finalized requirements for our Service Level Agreement with Last Mile providers. | FALSE | N/A | The following accomplishments are planned for next quarter: We expect to complete the deployment of our core network by the end of next quarter as follows: â€¢ Completion of civil work and equipment installation at our last remaining core network tower site. â€¢ Completion of link alignment and end-to-end site testing at our last remaining core network tower site. â€¢ We will continue to monitor our core network equipment as we transition this function over to our new Network Operator. Our planned deployment progress for next quarter is expected to produce the following metrics: â€¢ 720 total new (wireless) core network miles deployed; â€¢ 99 wireless links deployed, and; â€¢ 92 interconnection points complete and available for customer access. We will continue to execute our network enhancement strategy by exploring options and conducting cost/benefit analysis for increasing the quantity of fiber access points at strategic areas of our core network. In parallel with this effort, additional licensed microwave radios and antennas (procured for network enhancement purposes) will be tested and deployed at selected core network sites. We will continue to build and leverage our relationships with the local broadband service providers in our service area. We expect to have agreements signed with 1 additional last mile provider by the end of next quarter. We also anticipate that by the end of next quarter, connectivity will be provided for 3 new Community Anchor Institutions (CAI) that will be served Directly by the North Florida Broadband Authority network. The rest of the CAI's will be connected by our Last Mile Providers. | North Florida Broadband Authority | One of Our Last Mile providers and partners closed their doors this past quarter, which has created both challenges and opportunities for us to serve the local communities in our region that relied on them for broadband internet service. We remain in active negotiations with last mile providers in our service area, and we are seeking opportunities to provide direct-connect service to Community Anchor Institutions. Our procurement team developed and issued a Request for Bids for Field Services. However, bid response fell well short of expectations, which compelled us to evaluate the internal and external factors that led to the lack of response. We will reissue this procurement document after we determine and implement the appropriate course of action for generating more interest among potential bidders. Flooding issues delayed site preparation work and equipment installation at our last remaining core network tower site. The original site drawings were not sufficient as the equipment cabinet needed to be installed on a raised platform. New drawings were produced, and we were subsequently able to move forward with site preparation and equipment deployment activities at this tower site. We experienced some issues with power being disconnected at some of core network tower sites, and we discovered that meters were not installed at some of these sites (an oversight by our previous General Contractor). Our staff worked with the current deployment contractor to get all | We anticipate that some of the challenges faced during this current reporting period will continue into the next quarter. A big factor in rolling out service this year has been the weather. Excessive rain has caused several weeks in delay of rolling out services as well as the demise of one of our last mile providers and partners. We expect this weather trend to continue into next quarter, which coincides with the remainder of the Florida hurricane season.
NT10BIX5570023 | 2012 | Q4 | Q4 - 2012 | Core middle mile network deployment was completed during this quarter, and we made significant progress with the implementation and execution of our network enhancement plan as follows: â€¢ Installation of tower cabling, licensed microwave radios and antennas, and multi-service access platforms (switches) is complete on all core network tower sites, representing 99 new core wireless links and 720 new core network miles deployed, as determined by equipment installed at towers within a direct line of sight. â€¢ Equipment installation and circuit provisioning is complete at our 4 original Fiber Access Points. â€¢ System acceptance testing, site commissioning, and characterization of our core network rings continued through this past quarter with positive results. â€¢ We continued to monitor equipment performance at all 92 core network sites with our network and element management platform. â€¢ Additional licensed microwave radios and antennas were ordered, configured, and staged as we continued to execute our Network Enhancement strategy to increase network capacity at key wireless links for greater backhaul bandwidth. â€¢ The final Fiber Access Point in Putnam County is in its final stages of design. Wireless antenna licensing and equipment procurement activities began during this past quarter for this Fiber Access Point. â€¢ We also experienced substantial progress with network deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and broadband adoption opportunities for our target customers. We are synchronizing the development of our in kind tower assets with the build-out of our new Fiber Access Point in order to leverage our resources and to optimize both of these efforts. As a result of our deployment progress this quarter: â€¢ All 720 new (wireless) core network miles are deployed; â€¢ All core wireless links are deployed, and; â€¢ All core network interconnection points are complete and are being made available for customer access. We maintained our efforts toward ongoing customer outreach and building relationships with last mile providers as follows: â€¢ Agreements are executed with 3 last mile providers in our network service region, and; â€¢ 42 Community Anchor Institutions are being served by the North Florida Broadband Authority network. | 720 | 1620 | 0 | 0 | 0 | 99 | 0 | 92 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. | This amount represents fiber leased from our upstream providers. | N/A | N/A | N/A | This amount represents our new core wireless network links. We are continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for our target customers. | N/A | This amount represents our new core wireless network interconnection points. We are continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for our target customers. | 3 | 1 | 24 | We are selling wholesale broadband services to the last mile providers listed below: â€¢ Suwannee Valley Internet and Computers (SVIC) â€¢ Webkraft Wireless â€¢ RocketComm Wifi | This project is providing wholesale high speed internet access that will benefit incumbents and new service providers, while leading to improved access to information, markets, educational opportunities, and critical government services as our wholesale services are made available to our target customers in our rural service area. The nominal link capacity of the fixed-wireless network is 200 Mbps and will deliver up to 1 Gbps to last mile providers and/or community anchor institutions at our interconnection points. The most common connectivity currently available to the community anchor institutions in our region is provided through fractional T-1's (less than 1.5 Mbps), Cable, or DSL. The flexibility of the North Florida Broadband Authority network allows for as little as 1 Mbps to collection sites and continues to go up to meet the demands of the Community Anchor Institutions. A draft of our wholesale pricing plan is attached. | INOC (Contractor) 2810 Crossroads Drive, Suite 2600 Madison, WI 53718, USA (608) 663-4555 phone (608) 663-4558 fax www.inoc.com INOC is under contract with the North Florida Broadband Authority to manage, operate, and monitor our core middle mile network through their network and element management platform. | 1 | 2 | 0 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. Please see Section 3 above for more details. We will continue to plan workshops and seek other opportunities to build and leverage these relationships. | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. Please see Section 3 above for more details. We continue to invite Last Mile Providers to our Outreach events and meetings in hope to sign additional Providers. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for our target customers. | N/A | Internet (in Mbps) / # Customers 10 / 2 20 50 100 200 300 400 500 1000 / 1 Transport (in Mbps) 10 20 50 100 200 300 400 500 1000 | 42 | 2 | 40 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. Please see Section 3 above for more details. We anticipate more Community Anchor Institutions will be served as our core network is now complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for Community Anchor Institutions. | We anticipate more Community Anchor Institutions will be served as our core network is now complete and all core interconnection points are available for new customer access. | We assume that most subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. Please see Section 3 above for more details. We anticipate more Community Anchor Institutions will be served as our core network is now complete and all core interconnection points are available for improved customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for Community Anchor Institutions. | Internet (in Mbps) 10 20 50 100 200 300 400 500 1000 Transport (in Mbps) 10 20 50 100 200 300 400 500 1000 | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are updating and finalizing our service offerings and pricing to reflect anticipated customer demand, and we have finalized requirements for our Service Level Agreement with Last Mile providers. | FALSE | N/A | We will continue with our network enhancement activities while building links out from the core network by using our in kind tower sites to create lateral extensions to reach our target customers and facilitate connectivity to Community Anchor Institutions. As part of this effort, link design, wireless antenna licensing, and equipment procurement activities will continue through next quarter for the Fiber Access Point in Putnam County. We will also continue to explore options and conduct cost/benefit analysis for integrating additional Fiber Access Points at strategic areas of our core network as necessary to ensure that our network capabilities are aligned with customer demand forecasts. We also will finalize the process of compiling closeout documentation for each of our core network tower sites and performing administrative closure for the project as we transition into long-term operations management. As a result of our deployment progress next quarter: â€¢ 720 out of 720 total new (wireless) core network miles will be deployed; â€¢ 50 new wireless network miles will be deployed as lateral extensions of the core network to reach target customers; â€¢ 99 out of 99 core wireless links will be deployed, and; â€¢ 92 out of 92 core network interconnection points will be complete and made available for customer access. Community outreach activities will continue through next quarter. Our community outreach team will speak to community leaders and officials and present them with information on the services and broadband adoption opportunities available through the North Florida Broadband Authority network. Our team is scheduled next quarter to meet with representatives from Madison, Gilchrist, Hamilton, and Wakulla counties and from leaders and citizens from local communities within these counties. We will continue to build and leverage our relationships with the local broadband service providers in our service area and continue to connect Community Anchor Institutions. Our estimates for next quarter are as follows: â€¢ We expect to have agreements signed with 4 last mile provider(s) by the end of next quarter; â€¢ We estimate that 50 Community Anchor Institutions will be served by the North Florida Broadband Authority network. | North Florida Broadband Authority | We dealt with the residual effects of challenges and issues that began in previous quarters and continued into this reporting quarter. The deployment of our core middle mile network is complete; however, excessive rain and inclement weather continued to impact the rollout of network services at our in kind tower sites. We also continued to face challenges in generating responses to our Request for Bids for Field Services, and we are therefore exploring procurement options for securing a Field Services vendor. Our network deployment team is continuing to troubleshoot and address core network site issues as they occur. Community Anchor Institutions (CAIs) continue to be connected, but due to the delays in earlier quarters, we missed the E-rate window for 2012 and will therefore be unable to connect those CAIs until the 2013 E-rate cycle. Other CAIs are under current contracts and will remain until those contracts expire. However, we continue to pick up additional Community Anchor Institutions. | We anticipate that the residual effects of challenges and issues that began in previous reporting periods will continue into the next quarter. Inclement weather and transition-related issues from previous quarters delayed our overall deployment schedule, which in turn impacted customer acquisition activities. We met these challenges by bringing additional personnel on staff to augment our professional in-house project management and business development teams, while also ensuring that we continue to be supported by qualified engineers, contractors, consultants, community leaders, and financial and legal professionals. We are also working through the challenge of integrating a Voice over Internet Protocol offering into our current offerings and addressing the issues of those Community Anchor Institutions that are under long term contracts and might not be willing to break those contracts; we would then have to wait until those contracts expire to connect them to our network.
NT10BIX5570023 | 2013 | Q1 | Q1 - 2013 | As we draw closer to the completion of our core network, we focused our efforts this past quarter on customer outreach and business development activities, pursuing E-Rate opportunities, connecting more Community Anchor Institutions, and continuing the implementation of our network enhancement plan. â€¢ Network Operations & Deployment: â—‹ We filed permits and continued with the build-out of our new Fiber Access Point in Palatka (Putnam County), which includes an associated fiber connection to a communications tower in nearby San Mateo. â—‹ We continued to build-out and incorporate in-kind assets to extend our core network to reach our target customers and connect Community Anchor Institutions. â—‹ We compiled vendor closeout documentation from our engineering and deployment contractors for each of our core network tower sites. â€¢ As a result of our deployment progress: â—‹ 744 new (wireless) core network miles are deployed; â—‹ 50 new wireless network miles are deployed as lateral extensions of the core network; â—‹ 100 wireless links are deployed, and; â—‹ 93 core network interconnection points are complete and are being made available for customer access. â€¢ Business Development: â—‹ Our business development team continued to reach out to local community leaders and anchor institutions in our service region to generate interest and to create new business opportunities. â—‹ We continued to work in partnership with Last Mile providers to seek ways to leverage our Middle Mile network infrastructure so that we can provide more broadband services and solutions to more customers and community anchor institutions. â—‹ We drafted an application for participation in the E-Rate Universal Service Fund Program, which will allow us to connect more community anchor institutions during the 2013 E-Rate funding year cycle (July 1, 2013 through June 30, 2014). â—‹ We are in the process of updating our business model, and we held a special informational workshop in March to meet with representatives from the National Telecommunications and Information Administration so that they could review our current business model and provide feedback and insight to further refine our plans to cut costs and raise revenue. â—‹ We also developed and launched of series of informational videos to create awareness for our network services. These videos include testimonial comments from some of our early adopter customers that describe how they are using high-speed broadband Internet service provided through our network to create their own success stories, which include building a profitable startup business (ahead of schedule) and improving the quality of online educational resources for the children who attend our rural schools. Our informational videos can be viewed online at: www.youtube.com/user/NFBA1 â€¢ As a result of our efforts with ongoing customer outreach and building relationships with last mile providers: â—‹ Agreements are executed with 3 last mile providers in our network service region, and; â—‹ 62 Community Anchor Institutions are being served by the North Florida Broadband Authority network. We received approval this past quarter for an Award Action Request to extend our grant period to September 30, 2013. Milestone percent complete quantities reported for this quarter may therefore vary from our original baseline plan projections, as these were based on percent complete estimates that anticipated the original January 31, 2013 project completion date. | 744 | 1762 | 0 | 0 | 0 | 100 | 0 | 93 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. | This amount represents fiber leased from our upstream providers. | N/A | N/A | N/A | This amount represents our new core wireless network links. We are continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for our target customers. | N/A | This amount represents our new core wireless network interconnection points. We are continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which will function as lateral extensions of our core network to create increased connectivity and adoption opportunities for our target customers. | 3 | 1 | 24 | We are selling wholesale broadband services to 3 last mile providers. Suwanee Valley Internet & Computers Rocketcomm Wifi Webkraft Wireless | This project is providing wholesale high speed internet access that will benefit incumbents and new service providers, while leading to improved access to information, markets, educational opportunities, and critical government services as our wholesale services are made available to our target customers in our rural service area. The nominal link capacity of the fixed-wireless network is 200 Mbps and will deliver up to 1 Gbps to last mile providers and/or community anchor institutions at our interconnection points. The most common connectivity currently available to the community anchor institutions in our region is provided through fractional T-1's (less than 1.5 Mbps), Cable, or DSL. The flexibility of the North Florida Broadband Authority network allows for as little as 1 Mbps to collection sites and continues to go up to meet the demands of the Community Anchor Institutions. A draft of our wholesale pricing plan is attached. | INOC (Contractor) 2810 Crossroads Drive, Suite 2600 Madison, WI 53718, USA (608) 663-4555 phone (608) 663-4558 fax www.inoc.com INOC is under contract with the North Florida Broadband Authority to manage, operate, and monitor our core middle mile network through their network and element management platform. | 1 | 2 | 0 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We will continue to plan workshops and seek other opportunities to build our relationships with last mile providers in our area. | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We will continue to invite Last Mile Providers to our outreach events and meetings and hope to sign additional Providers. We will also maintain our progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for our target customers. | N/A | Internet (in Mbps) / # Customers 10 / 2 20 50 100 200 300 400 500 1000 / 1 Transport (in Mbps) 10 20 50 100 200 300 400 500 1000 | 62 | 2 | 60 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for Community Anchor Institutions. | We anticipate more Community Anchor Institutions will be served as our core network is now complete and all core interconnection points are available for new customer access. | We assume that most subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for Community Anchor Institutions. | Internet (in Mbps) / # Customers 10 / 2 20 50 100 200 300 400 500 1000 / 1 Transport (in Mbps) 10 20 50 100 200 300 400 500 1000 | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are developing plans to integrate Voice over Internet Protocol (VoIP) solutions and services into our current offerings. | FALSE | N/A | We will continue to build out our in kind tower sites to extend our core network and reach our target customers. As part of this effort, site permitting, site preparation, and equipment deployment activities will continue through next quarter for our new Fiber Access Point in Putnam County and its associated communications tower in nearby San Mateo. We will also finalize our plan to grow NFBAâ€™s retail presence and to seek out partnership opportunities with utilities through establishing community development districts. Our business development team will continue to meet with local community leaders, anchor institutions, and last mile providers to create new business opportunities and to cultivate existing relationships. As a result of our deployment progress through next quarter: â€¢ 744 new (wireless) network miles will be deployed; â€¢ 50 new wireless network miles will be deployed as lateral extensions of the core network; â€¢ 100 core wireless links will be deployed, and; â€¢ 93 core network interconnection points will be complete and made available for customer access. We will continue to build and leverage our relationships with the local broadband service providers in our service area and continue to connect Community Anchor Institutions. Our estimates for next quarter are as follows: â€¢ We expect to have agreements signed with 1 last mile provider(s) by the end of next quarter; â€¢ We estimate that 80 Community Anchor Institutions will be served by the North Florida Broadband Authority network. As noted above, our Award Action Request to extend our grant period to September 30, 2013 was approved, and therefore, milestone percent complete quantities projected for next quarter may vary from our original baseline plan projections, as these were based on percent complete estimates corresponding to the original January 31, 2013 project completion date. | North Florida Broadband Authority | The deployment of our core middle mile network is complete; however, as in previous quarters, excessive rain and inclement weather continued to impact the rollout of network services at our in kind tower sites. We submitted a bid to the Bradford County School Board to provide Wide Area Network connectivity, and although we submitted the lowest bid in a definitive, all-inclusive proposal, our bid was nonetheless rejected with no stated reason or justification provided. We are also working to mitigate the actions of a former board member who, working in partnership with our former engineering contractor and with a blogger from Columbia County, has maintained an ongoing misinformation campaign in a deliberate attempt to discourage local support for the project and obstruct customer acquisition and business development efforts. We held an informational workshop in March in an effort to dispel some of this misinformation and to address the concerns expressed by our partners and our member local government entities (both former and current). We will also continue to move this project forward by building upon the success of our experiences and relationships with our early adopter customers in an effort to generate meaningful support for the network and to reinforce our ongoing business development efforts. | We will continue to embrace the challenge of building a sustainable enterprise despite experiencing diminished support from some of the local government entities that had initially helped to create our organization and had resolved to help ensure its success. With our core network effectively deployed, tested, operational, and beginning to generate income, we can bring more resources to bear on processes associated with business development, raising revenue, and reducing costs. We are in a good position to generate new support throughout our network service region, as our customer acquisition and market-based engineering processes have been recognized by program leadership as leading edge and best practices. Our network deployment and enhancement efforts are already creating an impact in our rural communities, where the demand for reliable high-speed broadband service could not be greater, and where we expect that we will continue to see positive results from our new and existing customers.
NT10BIX5570023 | 2013 | Q2 | Q2 - 2013 | â€¢ Network Operations & Deployment: â—‹ We completed the build-out of our Fiber Access Point in Palatka (Putnam County) and its associated fiber connection to a communications tower in nearby San Mateo. â—‹ We deployed network access equipment on our in-kind assets (tower infrastructure) in Hamilton, Putnam, and Levy counties during this past quarter to reach target customers and connect community anchor institutions. This work included the installation of network access equipment on an in-kind water tower in the town of Bronson. â—‹ We continued to support and expand to IN-Kind Assets for Last Mile Providers as they connect CAIs under the E-Rate program. â€¢ As a result of our network deployment progress: â—‹ 744 new (wireless) core network miles are deployed; â—‹ 66 new wireless network miles are deployed as lateral extensions of the core network; â—‹ 100 wireless links are deployed, and; â—‹ 95 core network interconnection points are complete and available for customer access. â€¢ Business Development: â—‹ Our business development team continued to reach out to local community leaders, anchor institutions, and last mile providers in our service region to generate interest and to create new business opportunities. â—‹ Our board leadership and staff members reached out to a local University to discuss opportunities for our organization to provide broadband service for their facilities located throughout the NFBA footprint â—‹ Our project management staff also met with several groups representing areas in rural Alachua County that are interested in the broadband and Internet access services provided through our network via Last mile providers and the NFBA once the grant is closed out. â—‹ We issued an Invitation to Negotiate for a Strategic Partner, evaluated written responses, and conducted interviews with qualified respondents. After fulfilling our initial mission to design and deploy the network and render it operational, the North Florida Broadband Authority is now seeking to align itself with a strategic partner who will join forces with us to help ensure the networkâ€™s long-term sustainability and planned growth by further extending the network and generating additional business opportunities among the unserved and underserved customers in our network service region. â€¢ As a result of our ongoing efforts with customer outreach and building relationships with last mile providers: â—‹ Agreements are executed with 1 last mile provider in our network service region, and; â—‹ 91 Community Anchor Institutions are being served by the North Florida Broadband Authority network. | 810 | 1762 | 0 | 0 | 0 | 100 | 0 | 95 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. | This amount represents fiber leased from our upstream providers. | N/A | N/A | N/A | This amount represents our new core wireless network links. We are also continuing to make progress with equipment deployment and link provisioning at our in-kind tower sites, which function as lateral extensions of our core network and create increased connectivity and adoption opportunities for our target customers. | N/A | This amount represents our new core wireless network interconnection points. We are also continuing to make progress with equipment deployment and link provisioning at our in-kind tower sites, which function as lateral extensions of our core network and create increased connectivity and adoption opportunities for our target customers. | 1 | 1 | 24 | We are selling wholesale broadband services to1 last mile provider: â€¢ Suwanee Valley Internet & Computers | This project is providing wholesale high speed internet access that will benefit incumbents and new service providers, while leading to improved access to information, markets, educational opportunities, and critical government services as our wholesale services are made available to our target customers in our rural service area. The nominal link capacity of the fixed-wireless network is 200 Mbps and will deliver up to 1 Gbps to last mile providers and/or community anchor institutions at our interconnection points. The most common connectivity currently available to the community anchor institutions in our region is provided through fractional T-1's (less than 1.5 Mbps), Cable, or DSL. The flexibility of the North Florida Broadband Authority network allows for as little as 1 Mbps to collection sites and continues to go up to meet the demands of the Community Anchor Institutions. | INOC (Contractor) 2810 Crossroads Drive, Suite 2600 Madison, WI 53718, USA (608) 663-4555 phone (608) 663-4558 fax www.inoc.com INOC is under contract with the North Florida Broadband Authority to manage, operate, and monitor our core middle mile network through their network and element management platform. | 0 | 1 | 0 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We are continuing to plan workshops and seek other opportunities to build relationships with last mile providers in our area. | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We will continue to invite Last Mile Providers to our outreach events and meetings and hope to sign additional Providers. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for our target customers. | N/A | We provide direct-connect service to last mile providers indicated in the speed tiers listed below. Internet (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 1 Transport (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 | 91 | 2 | 89 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for Community Anchor Institutions. | We anticipate more Community Anchor Institutions will be served as our core network is now complete and all core interconnection points are available for new customer access. | We assume that most subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which extend our core network and create increased connectivity and adoption opportunities for Community Anchor Institutions. | We provide direct-connect service to community anchor institutions indicated in the speed tiers listed below. The community anchor institutions that are served by our network are normally connected through our last mile provider customers and partners. Internet (in Mbps) / # Customers 10 / 2 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 Transport (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 | 0 | 0 | 0 | 0 | 0 | Residential households will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses will have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are continuing to develop plans to integrate Unified Communications and Voice over Internet Protocol (VoIP) solutions and services into our current offerings and service catalog. | FALSE | N/A | We will continue to build out our in-kind tower infrastructure sites to extend our network capabilities and provide service to target customers and community anchor institutions. We will finalize the process of selecting and engaging a strategic partner to expand our customer service footprint and ensure the sustainability and growth of our network. Our business development team will continue to meet with local community leaders, anchor institutions, and last mile providers to create new business opportunities and to cultivate existing relationships. We will also continue with our plans to grow NFBAâ€™s retail presence and to seek out partnership opportunities with utilities through the establishment of community development districts. As a result of our deployment progress through next quarter: â€¢ 744 new (wireless) network miles will be deployed; â€¢ 82 new wireless network miles will be deployed as lateral extensions of the core network; â€¢ 100 core wireless links will be deployed, and; â€¢ 95 core network interconnection points will be complete and made available for customer access. We will continue to build and leverage our relationships with the local broadband service providers in our service area and continue to connect community anchor institutions. Our estimates for next quarter are as follows: â€¢ We expect to have agreements signed with 1 last mile provider(s) by the end of next quarter; â€¢ We estimate that 135 Community Anchor Institutions will be served by the North Florida Broadband Authority network. | North Florida Broadband Authority | A wet weather pattern across North Central Florida this quarter has caused a minor delay to the build-out of our in-kind towers, but we continue to push forward. We also experienced brief, intermittent wind and lightning related outages, but our network proved to be resilient and we experienced no significant downtime as a result. We experienced a shortage of qualified network equipment installers during this past quarter due to demand for tower climbers created by cellular telephone companies in our region. Our project management staff remained in contact with several wireless communication companies in an effort to offset this temporary labor shortage and mitigate its effect on the build-out of our in-kind tower infrastructure. Our Test Link for the Bradford County School District confirmed that our 200 megabit/second test link in Bradford County performed flawlessly for the 90 days it was installed as well as officially recognized the expertise and professionalism of our employees. They further stated publicly in their belief that the North Florida Broadband Authority network provides a workable alternative to school districts in north Florida in need of higher bandwidth Internet services. The NFBA hopes to win the bid this E-Rate season and provide service to Brandford County School District. | Next quarter corresponds with the height of the Atlantic hurricane season, and we expect to encounter the effects of an active tropical storm season throughout next quarter in addition to a multitude of unnamed thunderstorms that are common to our region this time of year. Wind, lightning, rain, and flooding conditions have typically translated to weather-related delays over the course of this project. However, we will continue to optimize periods of clear weather, as well as take advantage of opportunities to stress test our disaster recovery capabilities during periods of inclement weather.
NT10BIX5570023 | 2013 | Q3 | Q3 - 2013 | â€¢ Network Operations & Deployment: â—‹ We deployed network access equipment on our in-kind assets (tower infrastructure) in Madison and Hamilton counties during this past quarter to reach target customers and to connect community anchor institutions. This work included the installation of network access equipment on an in-kind water tower located in the town of White Springs. â—‹ We continued to support and expand our in-kind tower infrastructure capacity for our last mile provider partner as they connect community anchor institutions under the E-Rate program. â—‹ We completed system benchmark testing on network access equipment installed on our in-kind tower assets in Putnam County. â€¢ As a result of our network deployment progress: â—‹ 744 new (wireless) core network miles are deployed; â—‹ 82 new wireless network miles are deployed as lateral extensions of the core network; â—‹ 100 wireless links are deployed, and; â—‹ 95 core network interconnection points are complete and available for customer access. â€¢ Business Development: â—‹ Our business development team continued to reach out to local community leaders, anchor institutions, and last mile providers in our service region to generate interest in our services and to create new business opportunities. â—‹ We entered into negotiations and executed a Letter of Intent with our proposed Strategic Partner that we selected to join forces with us to help ensure the networkâ€™s long-term sustainability and planned growth. Our Board of Directors selected a negotiating team (represented by selected members of the Board of Directors, our direct employees, and our legal counsel), and authorized them to negotiate a definitive agreement with the selected respondent. â€¢ As a result of our ongoing efforts with customer outreach and building relationships with last mile providers: â—‹ Agreements are executed with 1 last mile provider in our network service region, and; â—‹ 100 Community Anchor Institutions are being served by the North Florida Broadband Authority network. The success of this project is being demonstrated by the economic benefits and positive impact generated to our stakeholders, business partners, anchor institutions, and the community at large in our service region by completing network deployment. Our accomplishments can be seen in our ability to provide improved reliability and increased bandwidth at lower rates for the 100 Community Anchor Institutions currently being served by our middle mile network infrastructure. For example, at a rural school in Jefferson County, BTOP-funded infrastructure is being used to help advance their goal of providing a high-quality, college preparatory education through the use of online classroom management solutions that have been enhanced and improved by increased broadband capacity provided through the North Florida Broadband Authority network. We are also connecting North Florida businesses to the rest of the world and helping them create their own success stories, as demonstrated by a local landscaping nursery that used high-speed broadband Internet service provided through our network to build their startup business and turn it into a profitable enterprise ahead of schedule. In addition, over the last three years this project has resulted in approximately 260 full-time equivalent jobs created or retained through American Recovery and Reinvestment Act funding. As indicated above, during this past quarter we took steps toward sustaining our success by moving forward with our proposed Strategic Partner, which places the North Florida Broadband Authority network and its business partners in the hands of an experienced and well-financed manager with established organizational capabilities and resources. The goal of this partnership is to ensure the continued success of our network in delivering the benefits of broadband service to the community anchor institutions, businesses, and residents within our service area. Please note that although we reported program income in our previous quarterly Performance Progress Reports, program income is being reported as $0 on this report because it was necessary for the North Florida Broadband Authority to deduct operational costs incidental to the generation of the program income during this reporting period. | 826 | 1762 | 0 | 0 | 0 | 100 | 0 | 95 | This amount represents new wireless network miles deployed as determined by equipment installed at towers within a direct line of sight. | This amount represents fiber leased from our upstream providers. | N/A | N/A | N/A | This amount represents our new core wireless network links. We are also continuing to make progress with equipment deployment and link provisioning at our in-kind tower sites, which function as lateral extensions of our core network and create increased connectivity and adoption opportunities for our target customers. | N/A | This amount represents our new core wireless network interconnection points. We are also continuing to make progress with equipment deployment and link provisioning at our in-kind tower sites, which function as lateral extensions of our core network and create increased connectivity and adoption opportunities for our target customers. | 1 | 1 | 24 | We are selling wholesale broadband services to one last mile provider: â€¢ Suwanee Valley Internet & Computers | This project provides wholesale high speed internet access that will benefit incumbents and new service providers, while leading to improved access to information, markets, educational opportunities, and critical government services as our wholesale services are made available to our target customers in our rural service area. The nominal link capacity of the fixed-wireless network is 200 Mbps and will deliver up to 1 Gbps to last mile providers and/or community anchor institutions at our interconnection points. The most common connectivity currently available to the community anchor institutions in our region is provided through fractional T-1's (less than 1.5 Mbps), Cable, or DSL. The flexibility of the North Florida Broadband Authority network allows for as little as 1 Mbps to collection sites and continues to go up to meet the demands of the Community Anchor Institutions. | INOC (Contractor) 2810 Crossroads Drive, Suite 2600 Madison, WI 53718, USA (608) 663-4555 phone (608) 663-4558 fax www.inoc.com INOC is under contract with the North Florida Broadband Authority to manage, operate, and monitor our core middle mile network through their network and element management platform. | 0 | 1 | 0 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We are continuing to seek opportunities and build relationships with last mile providers in our area. | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We are continuing to invite Last Mile Providers to our outreach events and meetings and hope to sign additional Providers. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which is extending our core network and creating increased connectivity and adoption opportunities for our target customers. | N/A | We provide direct-connect service to last mile providers indicated in the speed tiers listed below. Internet (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 1 Transport (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 | 100 | 2 | 98 | 18 | Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which is extending our core network and creating increased connectivity and adoption opportunities for our target customers. | We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. | We assume that most subscribers have some type of pre-existing service, and these subscribers will receive improved service with the increased bandwidth provided through our network. Variance from the baseline plan is due to the residual effects of challenges and transition-related issues that began in previous quarters. We anticipate more Community Anchor Institutions will be served now that our core network is complete and all core interconnection points are available for customer access. We are also continuing to make progress with equipment deployment and link provisioning at our in kind tower sites, which is extending our core network and creating increased connectivity and adoption opportunities for our target customers. | We provide direct-connect service to community anchor institutions indicated in the speed tiers listed below. The community anchor institutions that are served by our network are normally connected through our last mile provider customers and partners. Internet (in Mbps) / # Customers 10 / 2 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 Transport (in Mbps) / # Customers 10 / 0 20 / 0 50 / 0 100 / 0 200 / 0 300 / 0 400 / 0 500 / 0 1000 / 0 | 0 | 0 | 0 | 0 | 0 | Residential households have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Businesses have service delivered through last mile providers only. | N/A | N/A | N/A | N/A | We are working with our strategic partners to develop plans to integrate Unified Communications and Voice over Internet Protocol (VoIP) solutions and services into our current service catalog and to ensure that any proposed special offerings are aligned with our organizational goals and objectives. | FALSE | N/A | We expect to enter into an agreement with our proposed Strategic Partner and then begin the process of transitioning key business management and administrative functions to the selected respondent. We will continue to build out our in-kind tower infrastructure to extend our network capabilities and our customer service footprint, and to provide service to target customers and community anchor institutions. As a result of our deployment progress through next quarter: â€¢ 744 new (wireless) network miles will be deployed; â€¢ 82 new wireless network miles will be deployed as lateral extensions of the core network; â€¢ 100 core wireless links will be deployed, and; â€¢ 95 core network interconnection points will be complete and made available for customer access. We will continue to build and leverage our relationships with the local broadband service providers in our service area and continue to connect community anchor institutions. Our estimates for next quarter are as follows: â€¢ We expect to have agreements signed with 1 last mile provider(s) by the end of next quarter; â€¢ We estimate that 135 Community Anchor Institutions will be served by the North Florida Broadband Authority network. We will also continue the process of compiling closeout documentation for our network asset and equipment inventory and performing administrative closure for the project as we transition from project management to long-term business operations. Project closeout activities planned for next quarter include BTOP Grant closeout and final reporting, preparation of financial audits for previous fiscal years, and settlement or continuance (as necessary) of current vendor contracts. We will work with our selected Strategic Partner through a defined pre-transition period that will establish roles and responsibilities associated with project close-out activities in addition to ongoing business development, customer acquisition and relations management, day-to-day operations, and the future direction of the North Florida Broadband Authority's business and network. | North Florida Broadband Authority | We continued to experience a summer wet weather pattern this past quarter that caused negligible delays to the build-out of our in-kind tower infrastructure. We anticipated a more active hurricane season and prepared for the corresponding impact to our network operations. However, hurricane activity did not seriously threaten or affect our region during this past quarter. We nevertheless monitored our network performance to assess the current state of our disaster recovery capabilities and to ensure the appropriate levels of high availability, failover, and redundancy are maintained in the event of a major storm. Negotiations with our proposed strategic partner have been protracted as we worked through the process of developing an agreement that will be suitable for all affected stakeholders. This was in part caused by our negotiating team's due diligence efforts as well as the inherent complexities associated with defining and assigning key terms, roles, and responsibilities. | Next quarter corresponds with the end of the Atlantic hurricane season, and although there has been relatively minimal tropical activity this year, we will continue to assess our state of preparedness and network resiliency to ensure appropriate strategies and procedures are place in the event a named storm impacts our service region. We will also continue working toward finalizing our negotiations with our strategic partner, and we expect to approve and execute an agreement before the end of next quarter. We will then address the challenge of transitioning roles and responsibilities within the context of day-to-day business management and administrative requirements, as well as within our broader organizational objectives of growth, sustainability, and the promotion of economic development opportunities in our service region.
NT10BIX5570024 | 2010 | Q3 | Q3 - 2010 | During this past quarter, the University of Utah (U of U)/Utah Education Network (UEN) has placed priority on completion of the Environmental Assessment (EA). This Special Award Condition must be completed before any network build out activities can begin, such as ground excavation and new construction. The first and second draft versions of the EA were submitted in July and September, respectively. NTIA reviews of these draft EA documents found that additional information was needed including further consultation with the State Historic Preservation Office and the Army Corps of Engineers. After working with these two agencies, the U of U/UEN have completed the SHPO consultation and the 3rd draft EA has been submitted for review. Work continues on language contained in the contract agreements with Telecommunications Partners that will meet NTIA requirements. Additionally, the U of U/UEN is concluding meetings with all effected stakeholders and vendors to finalize network designs, implementation plans and sign off on contracts. These activities, when completed, will position the U of U/UEN to launch the implementation phase of the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance to Baseline Report | No variance to Baseline Report | N/A | N/A | No variance to Baseline Report | N/A | N/A | No variance to Baseline Report | 0 | 8 | 60 | None at this time. The U of U/UEN, with the help of NTIA and BTOP representatives, is negotiating final contract details with Telecommunication Partners and expects to have all agreements signed by the end of the fourth quarter. | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific Community Anchor Institutions (CAI) working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end site. These Telecommunication Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | The following Telecommunications Partners will operate a portion of the U of U/UEN network. This includes all physical infrastructure and transport elements and in some instances, they will operate and provide support on layer 2 and 3 equipment. Qwest Communications â€“ Salt Lake City, Utah, (800) 899-7780 Veracity Networks â€“ Lehi, Utah, (801) 407-6000 Emery Telecom â€“ Orangeville, Utah, (435) 748-2223 South Central Communications â€“ Escalante, Utah, (435) 826-4211 Strata Networks â€“ Roosevelt, Utah, (435) 622-5007 Centracom â€“ Fairview, Utah, 800-427-8449 Frontier Communications â€“ Moab, Utah, (435) 259-5157 Utopia â€“ West Valley City, Utah, (801) 613-3800 | 0 | 0 | 0 | 0 | N/A | The U of U/UEN is continuing to work with BTOP Program Officers and Telecommunication Partners to complete contract agreements that outline specific language required to meet NTIA requirements. As such, no contracts have been signed at this time. | N/A | No variance to Baseline Report | 0 | 0 | 0 | 0 | No variance to Baseline Report | No variance to Baseline Report | No variance to Baseline Report | No variance to Baseline Report | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing and special offerings. | FALSE | The U of U/UEN network management practices have not changed over the last quarter. | For the fourth quarter beginning October 1, 2010 and ending December 31, 2010, The U of U/UEN is expecting to have the Environmental Assessment and Telecommunications Partner contracts completed allowing project funding to be released and vendor job initiation to begin. Final stakeholder approval on vendor designs and contracts are expected this quarter as well. Vendors will begin the procurement process, acquiring permits and rights of way, performing site surveys, and site preparations as well as network build out activities. It is expected that locations, which are shovel ready or that, have minimal construction requirements will be positioned to have equipment installations completed and final preparations for network testing and turn up. | University of Utah, The | The U of U/UEN has been working closely with NTIA BTOP program officers and consulting organizations in efforts to complete the Environmental Assessment and the contracts with Telecommunications Partners. The major challenges faced in completing the EA has been the amount of time required to complete surveys and begin consultation on Historic Sites and in getting access to the appropriate representative from the Army Corps of Engineers to begin their consultation. The delay in finalizing Telecommunication Partner contracts is due to an inability to identify an acceptable means of meeting the security interest requirement for the government. | Any obstacle in receiving a Finding of No Significant Impact (FONSI) for the U of U/UEN Environmental Assessment or in finalizing the Telecommunications Partner contracts during this upcoming quarter would have a significant impact on planned project milestones. Release of project funding is pending approval of these two conditions, and this funding is necessary to begin Network Build Out activities. The U of U/UEN is working closely with BTOP Program Officers on completing these two project-funding prerequisites.
NT10BIX5570024 | 2010 | Q4 | Q4 - 2010 | During this past quarter, the University of Utah (U of U) / Utah Education Network (UEN) completed two major milestones that will advance the project into the construction and implementation phase. First, we received approval by the NTIA on our Environmental Assessment and was issued a Finding of No Significant Impact (FONSI) and secondly, we signed an agreement with our primary Telecommunication Partner that meets all of the grant Special Award Conditions. With this completed contract, job initiation can begin and network build out commences. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance to Baseline Report | No variance to Baseline Report | No variance to Baseline Report | N/A | No variance to Baseline Report | N/A | N/A | No variance to Baseline Report | 1 | 7 | 15 | The U of U/UEN has signed a contractual agreement with Qwest Communications Corporation for the BTOP project. | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific Community Anchor Institutions (CAI) working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end site. These Telecommunication Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber and physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. Qwest Communications( Sub Recipient) â€“ Salt Lake City, Utah, (800) 899-7780 Veracity Networks ( Sub Recipient) â€“ Lehi, Utah, (801) 407-6000 Emery Telecom ( Sub Recipient) â€“ Orangeville, Utah, (435) 748-2223 South Central Communications ( Sub Recipient) â€“ Escalante, Utah, (435) 826-4211 Strata Networks ( Sub Recipient) â€“ Roosevelt, Utah, (435) 622-5007 Centracom ( Sub Recipient) â€“ Fairview, Utah, (800) 427-8449 Frontier Communications ( Sub Recipient) â€“ Moab, Utah, (435) 259-5157 Utopia â€“ ( Sub Recipient) West Valley City, Utah, (801) 613-3800 | 0 | 1 | 0 | 0 | N/A | The U of U/UEN Baseline Report projected the completion of all Telecommunication Partner contracts in the fourth quarter of project year one. However, efforts to come to an agreement on security interest requirements required more time than anticipated. It is for these reasons this milestone in not completed at this time. The remaining Telecommunication Partner contracts are pending signatures and are expected to be completed within the first quarter of project year two. | N/A | No variance to Baseline Report | 0 | 0 | 0 | 0 | No variance to Baseline Report | No variance to Baseline Report | No variance to Baseline Report | No variance to Baseline Report | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing and special offerings. | FALSE | The U of U/UEN network management practices have not changed during the past quarter. | With all Telecommunication Partner agreements completed, the U of U/UEN is projecting that significant progress with be made in the construction, network build out and turn up of Community Anchor Institutions. All vendors will begin the procurement process, acquiring permits and rights of way, performing site surveys and site construction. It is expected that locations that have minimal construction requirements will be positioned to have circuit installation completed and turned up during this first quarter of project year two. | University of Utah, The | In order to keep the overall project on schedule, the U of U/UEN faced major challenges in completing the Telecommunication Partner contracts and associated federal security interest requirements. Our ability to consult with our FPO and the guidance we received on these issues proved to be invaluable, and provided the leverage that was needed to advance these issues with our Telecommunication Partners until a resolution was found. Without this support, project schedules were in jeopardy. | The major challenges anticipated by the U of U/UEN for this upcoming quarter involve construction and build out of the network infrastructure. Seasonal moratoriums, permits and rights of way may prevent construction in selected areas affecting the planned implementation schedule. The U of U/UEN is planning to focus construction activities in geographic areas that are not affected by these moratoriums.
NT10BIX5570024 | 2011 | Q1 | Q1 - 2011 | During the first quarter of 2011, the University of Utah / Utah Education Network (U of U/UEN) completed contracts with sub recipient telecommunication partners that meet all NTIA security interest requirements and special award conditions for the grant. This milestone allowed the project to move into the implementation phase. Telecommunication Partners have begun construction activities and network build out and the U of U/UEN started it's procurement process and received shipment for the first phase of Customer Premise Equipment. Installation and turn up of nine (9) Community Anchor Institutions was completed and the U of U/UEN is expecting the rate of installations to increase significantly during this next quarter. In addition, a publicly accessible U of U/UEN BTOP project website has been developed and is now available with site lists and status updates. | 1 | 96 | 0 | 0 | 1 | 0 | 0 | 9 | The U of U/UEN is behind schedule on this milestone primarily due to the delays in site construction and network build out activities encountered while approvals were pending for the Davis Bacon Wage Determination Act job classifications. | The U of U/UEN is behind schedule on this milestone primarily due to the delays in site construction and network build out activities encountered while approvals were pending for the Davis Bacon Wage Determination Act job classifications. | No variance to Baseline Report | No variance to Baseline Report | The U of U/UEN is behind schedule on this milestone primarily due to the delays in site construction and network build out activities encountered while approvals were pending for the Davis Bacon Wage Determination Act job classifications. | No variance to Baseline Report | No variance to Baseline Report | The U of U/UEN is behind schedule on this milestone primarily due to the delays in site construction and network build out activities encountered while approvals were pending for the Davis Bacon Wage Determination Act job classifications. | 0 | 0 | 0 | None at this time. | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end site. These Telecommunication Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunication Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber and physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunication Partners for troubleshooting and or maintenance of this equipment. Qwest Communications Corporation (Sub Recipient) - Salt Lake City, Utah, (800) 899-7780 UTOPIA (Sub Recipient) - West Valley City, Utah, (801) 613-3800 | 0 | 0 | 0 | 0 | Neither of our sub recipients (Qwest, UTOPIA) have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest, UTOPIA) have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest, UTOPIA) have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest, UTOPIA) have entered into wholesale or Last Mile agreements with other providers on our behalf. | 9 | 0 | 9 | 4 | The U of U/UEN projected the turn up of fifteen (15) Community Anchor Institutions in the first quarter of 2011 and was only able to complete nine (9). The U of U/UEN is behind schedule on this milestone primarily due to the delays in site construction and network build out activities encountered while approvals were pending for the Davis Bacon Wage Determination job classifications. | None of the CAI installations completed this quarter is receiving new access, which is consistent with the U of U/UEN Baseline Report. | All of the CAI installations completed this quarter are receiving improved access, which is consistent with the U of U/UEN Baseline Report. | 1000 Mbps = 3, 100 Mbps = 3, 10 Mbps = 2, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN network management practices have not changed during the past quarter. | The U of U/UEN is projecting to meet or exceed the installation and turn up of CAIs during the upcoming quarter. The U of U/UEN is working closely with the project Telecommunication Partners on getting the installation milestones back on schedule. The regional Vice President for Qwest Communications informed the U of U/UEN that the allocation of manpower resources to this project is being increased in support of the quarterly milestones established in the U of U/UEN BTOP project Baseline Report. | University of Utah, The | The U of U/UEN's major challenges during this past quarter were twofold. First, we encountered construction and network build out delays pending approval of the Davis Bacon Wage Determination Act job classifications and secondly, while completing the outstanding telecommunications partner contracts, twenty six (26) of the original one hundred thirty (130) CAIs in our application have closed, relocated or connected to fiber through other project activities. The U of U/UEN has reviewed the Davis Bacon Wage Determination job classifications with each sub recipient and has agreed on a job classification to use for this project. The U of U/UEN will perform a more extensive analysis to ensure compliance and submit a request for evaluation by the Department Of Labor. The U of U/UEN is working with our Federal Program Officer to determine the appropriate course of action in dealing with the changes in project scope and budget. | The major challenges the U of U/UEN is expecting to face during the upcoming quarter revolve around network build out activities and ensuring the Telecommunication Partners address obstacles quickly so as not to impact projected milestones. The U of U/UEN is submitting a post award amendment in order to address the loss of twenty five (25) of the original one hundred thirty (130) CAIs in our application that have closed, relocated or connected to fiber through other project activities. The U of U/UEN will work closely with our Federal Program Officer on this issue.
NT10BIX5570024 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011, the University of Utah / Utah Education Network (U of U/UEN) has been actively working with telecommunication partners on the network build out, installation and turn up of Community Anchor Institutions (CAIs). At this time, the U of U/UEN has successfully completed the turn up of forty four (44) CAI installations. This exceeds the projected milestone of forty (40) CAI installations by the end of the second quarter of 2011. The U of U /UEN is proposing a route change to address the loss of twenty-five (25) of the original one hundred thirty (130) CAIs in our application that have closed, relocated and connected to fiber through other projects. The U of U/UEN is working closely with our Federal Program Officer on submitting an Action Award Modification to address this issue. Other activities during this quarter include additional equipment procurement and continued development of information for community outreach purposes. | 12 | 326 | 0 | 0 | 338 | 0 | 0 | 44 | The U of U/UEN did not meet our projection for this quarter and missed this milestone by three (3) miles. Although the U of U/UEN has completed nearly fifty (50) percent of the CAI installations, the larger construction projects are scheduled to begin during the third quarter of 2011 and we anticipate a significant increase in the miles of new fiber installed during this period. | The U of U/UEN did not meet our projection for this quarter and missed this milestone by forty eight (48) miles. Although the U of U/UEN has completed nearly fifty (50) percent of the CAI installations, the larger construction projects are scheduled to begin during the third quarter of 2011. | No variance to Baseline Report | No variance to Baseline Report | The U of U/UEN did not meet our projection for this quarter and missed this milestone by forty eight (48) miles. Although the U of U/UEN has completed nearly fifty (50) percent of the CAI installations, the larger construction projects are scheduled to begin during the third quarter of 2011 and we anticipate a significant increase in the miles of new fiber installed during this period. | No variance to Baseline Report | No variance to Baseline Report | This milestone is ahead of schedule. The U of U/UEN exceeded our projection of forty (40) CAI installations by the end of the second quarter of 2011. | 2 | 0 | 60 | 1.Qwest Communication Corporation / CenturyLink 2. UTOPIA | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end site. These Telecommunication Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunication Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber and physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunication Partners for troubleshooting and or maintenance of this equipment. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 | 0 | 0 | 0 | 0 | Neither of our sub recipients (Qwest / CenturyLink, UTOPIA), have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest / CenturyLink, UTOPIA), have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest / CenturyLink, UTOPIA), have entered into wholesale or Last Mile agreements with other providers on our behalf. | Neither of our sub recipients (Qwest / CenturyLink, UTOPIA), have entered into wholesale or Last Mile agreements with other providers on our behalf. | 44 | 0 | 44 | 4 | The U of U/UEN exceeded our projection of forty (40) CAI installations by the end of the second quarter of 2011. | None of the CAI installations completed this quarter is receiving new access, which is consistent with the U of U/UEN Baseline Report. | All of the CAI installations completed this quarter are receiving improved access, which is consistent with the U of U/UEN Baseline Report. | 1000 Mbps = 29 100 Mbps = 12, 10 Mbps = 2, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN's network management practices have not changed during the past quarter. | The U of U/UEN expects to continue the rate of CAI installations as projected for the upcoming quarter and should meet or exceed this milestone. The U of U/UEN is working closely with our Federal Program Officer on the submission of a Post Award Modification in order to address the loss of twenty five (25) CAIs from the original one hundred thirty (130) in our application, that have closed, relocated or connected to fiber through other project activities. | University of Utah, The | The U of U/UEN's major challenges during this past quarter involved construction activities and coordination with sub recipients. Access into school locations that were closed during summer months required special arrangements and we also had some challenges ensuring sub contractors followed specific site installation instructions. Despite a very aggressive installation schedule, these issues were handled without too much difficulty. Additionally, the U of U/UEN was able to achieve consensus among the sub recipient contractors on a wage classification and pay scale that is compliant with the Davis Bacon Wage Determination Act. | The major challenges the U of U/UEN is expecting to face during this upcoming quarter revolve around network build out activities and ensuring Telecommunication Partners address obstacles quickly so as not to impact projected milestones. Additionally, the U of U/UEN is working with our FPO on a Post Award Modification to address the loss of twenty five (25) of the original one hundred thirty (130) CAis in our application that have closed, relocated or connected to fiber through other project activities. The U of U/UEN is seeking approval from the State Historical Preservation Office and the United States Fish and Wildife Service on these projects.
NT10BIX5570024 | 2011 | Q3 | Q3 - 2011 | UEN is making excellent progress on the Broadband Technologies Opportunities Program (BTOP) project called Utah Anchors. During the third quarter of 2011, the University of Utah / Utah Education Network (U of U/UEN) has been actively working with telecommunication partners on the network build out, installation and turn up of Community Anchor Institutions (CAIs). By the end of September, the U of U/UEN successfully completed the turn up of 65 CAI installations. In order to meet the substantially complete milestone required by NTIA, UEN will need to complete broadband connections to as many as 95 institutions. The BTOP project is on time, and we believe we will reach this milestone. Construction work continues on the major segments of fiber installation this fall with favorable weather. The U of U/UEN has completed an Action Award Request proposing a Route Change to address the loss of twenty-five (25) of the original one hundred thirty (130) CAIs in our application that have closed, relocated and connected to fiber through other projects. All materials have been compiled and submitted to the National Telecommunications and Information Administration (NTIA) for review. The U of U/UEN has completed equipment procurement of Customer Premise Equipment for all remaining contracted sites. Other activities include the continued development and delivery of information and materials for Community Outreach purposes. | 22 | 438 | 0 | 0 | 22 | 0 | 0 | 65 | The U of U/UEN did not meet our projection for this quarter and missed the milestone by four (4) miles. Although we have completed fifty (50) percent of the CAI installations, we are just under half the total of new fiber mileage for the project. The larger construction builds will continue this quarter and we anticipate this milestone will be met by the next reporting period. | The U of U/UEN did not meet our projection for this quarter. Although we have completed fifty (50) percent of the CAI installations, we are just under half the total of new network miles leased for the project. The larger construction builds will continue this quarter and we anticipate this milestone will be met by the next reporting period. | No variance to Baseline Report | No variance to Baseline Report | The U of U/UEN did not meet our projection for this quarter and missed the milestone by four (4) miles. Although we have completed fifty (50) percent of the CAI installations, we are just under half the total of new fiber mileage for the project. The larger construction builds will continue this quarter and we anticipate this milestone will be met by the next reporting period. | No variance to Baseline Report | No variance to Baseline Report | This milestone is on schedule. | 2 | 0 | 60 | 1. Qwest Communication Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunication Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber and physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunication Partners for troubleshooting and or maintenance of this equipment. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 UTOPIA (sub recipient) - West Valley City, Utah (801) 613-3800 | 0 | 2 | 0 | 0 | The two sub recipients (Qwest / CenturyLink, UTOPIA) we have entered into agreements with have existing services. | Both sub recipients (Qwest / CenturyLink, UTOPIA) we have entered into agreements with, will see improvements to existing services as a result of this project. | There are no dark fiber segments included in this project which is consistent with the U of U/UEN Baseline Report. | 1000 Mbps = 2, 100Mbps = 2, 10 Mbps = 2, 2 Mbps = 2 | 65 | 0 | 65 | 4 | The U of U/UEN has completed the turn up of twenty (20) CAIs during the third quarter of 2011 for a cumulative project total of sixty five (65), meeting the projected milestone for the third quarter 2011. Please note that a reporting error was made in the second quarter report. Although the name table in section nine (9) is correct, the sum total in section six (6) is in error and indicates forty four (44) CAIs completed and should indicate forty five (45). | None of the CAI installations completed this quarter is receiving new access. This is consistent with the U of U/UEN Baseline Report. | All of the CAI installations completed this quarter are receiving improved access. This is consistent with the U of U/UEN Baseline Report. | 1000 Mbps = 49, 100Mbps = 13, 10 Mbps = 2, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed it's Network Management Practices during this past quarter. | The U of U/UEN is working with one of our sub recipients on expediting the process of invoicing for work performed, thereby improving the turnaround time between the work completed and the draw down of federal funds. The U of U/UEN will continue to seek approval for the Action Award Request. NTIA has scheduled a site visit to UEN during the first week of December to review BTOP compliance and conduct field visits with UEN staff. The following are projections (cumulative) for the 4th quarter 2011: a. New network miles deployed = 38 b. New network miles leased = 755 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 94 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this past quarter involved construction activities and coordination with sub recipients. The installation of entrance facilities at Anchor Institutions have required careful attention this past quarter to ensure that approved designs are being followed and problems are quickly addressed so as not to delay turn up schedules. The U of U/UEN continued work on the proposed Route Change and associated documentation. All materials were provided to our FPO for review on September 9th, 2011. | The major challenges the U of U/UEN is anticipating for this upcoming quarter revolve around network build out activities and ensuring Telecommunications Partners address obstacles quickly so as not to impact projected milestones. The U of U/UEN has submitted all materials requesting a Route Change to address the loss of twenty five (25) of the original one hundred thirty(130) CAIs in our application that have closed, relocated or connected to fiber through other projects. The U of U/UEN will continue to work closely with our FPO on this request.
NT10BIX5570024 | 2011 | Q4 | Q4 - 2011 | The University of Utah / UEN (U of U/UEN) continues to make excellent progress on the Broadband Technologies Opportunities Program (BTOP) project called Utah Anchors. During the fourth quarter of 2011, the U of U/UEN has been actively working with telecommunications partners on network build out activities and the connectivity and turn up of Community Anchor Institutions (CAIs). In October, the U of U/UEN received approval from the NTIA on an Action Award Modificiation that included a route change comprising one hundred forty-four (144) additional miles of fiber and an increase in the total number of CAIs for the project to one hundred forty (140). By the end of the fourth quarter of 2011, the U of U/UEN has successfully completed connectivity to ninety-five (95) CAIs, also meeting a BTOP grant requirement to be substantially complete, or sixty seven (67) percent, by the end of the second project year. In early December, the U of U/UEN completed an on-site visit conducted by representatives from the NTIA and Booz Allen. This site visit is a requirement for all Grant Awardees. Other activities during this quarter include additional equipment procurement and continued development and distribution of information for community outreach purposes. | 33 | 778 | 0 | 0 | 33 | 0 | 0 | 95 | The U of U/UEN did not meet our projection for this quarter and missed the milestone by five (5) miles. Although we have completed over sixty seven (67) percent of the CAI installations, we are just over sixty one (61) percent of new fiber miles for the project. We anticipate this milestone will be met by the end of the next quarter as we complete the remaining larger construction builds. | This milestone is on schedule and accounts for seventy six (76) percent of the total network miles leased for the project. | No variance to Baseline Report. | No variance to Baseline Report. | The U of U/UEN did not meet our projection for this quarter and missed the milestone by five (5) miles. Although we have completed over sixty seven (67) percent of the CAI installations, we are just over sixty one (61) percent of new fiber miles for the project. We anticipate this milestone will be met by the end of the next quarter as we complete the remaining larger construction builds. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is on schedule and meets the "substantially complete" percentage grant requirement at the end of the second year of the project. | 4 | 0 | 60 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive | The U of U/UEN is not a wholesale service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 4 | 0 | 4 | All four sub recipients that we have entered into agreements with, have existing service. | All four sub recipients that we have entered into agreements with, will see improvements to existing services as a result of this project. (We anticipate having two new signed agreements for IRU middle mile acquisitions completed by the end of February 2012). | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 1000 Mbps = 4, 100 Mbps = 4, 10 Mbps = 4, 2 Mbps = 4 | 95 | 0 | 95 | 4 | The U of U/UEN has completed the turn up of thirty (30) CAIs during the fourth quarter of 2011 for a cumulative project total of ninety five (95), which meets the quarterly milestone and the "substantially complete" sixty seven (67) percent grant completion requirement for the end of the second year of the project. | None of the CAI installations completed this qurter is receiving new access. This is consistent with the Baseline Report. | All of the CAI installations completed this quarter are receiving improved access. This is consistent with the Baseline Report. | 1000 Mbps = 65, 100 Mpbs = 26, 10 Mbps = 3, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed it's Network Management Practices during this past quarter. | The U of U/UEN is planning on continued installation and turn up of CAIs and to begin the installation of fiber for the Salt Lake Middle Mile segment. The U of U/UEN has also submitted and is seeking approval from the NTIA on an Action Award Request to add an additional three (3) mile fiber IRU to the Salt Lake Middle Mile project. a. New network miles deployed = 45 b. New network miles leased = 847 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 108 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this past quarter involved advancing network build out and construction activities against the projected schedule. The U of U/UEN received approval on an Action Award Request in October 2011 that included a route change involving an additional one hundred forty four (144) miles of fiber and forty (40) additional CAIs. This change significantly increased the amount of work needing to be completed by the end of the year in order to meet the "substantially complete" project milestone of sixty seven (67) percent. Working closely with our project sub-recipients on build out schedules, the U of U/UEN has met this goal. | The major challenges facing the U of U/UEN for this upcoming quarter revolve around network build out activities and ensuring Telecommunications Partners address obstacles quickly so as not to impact projected milestones. The U of U/UEN has submitted an Action Award Request adding an additional fiber IRU to the project. The U of U/UEN will continue to work closely with our FPO on this request.
NT10BIX5570024 | 2012 | Q1 | Q1 - 2012 | The University of Utah / Utah Education Network (U of U/UEN) had another very productive quarter to start 2012 and continues to build out the network and connect Community Anchor Institutions (CAI) on schedule. The U of U/UEN has successfully connected one hundred fifteen (115) of the total one hundred forty (140) CAIs for the project and has installed forty-four (44) miles of new fiber. The completion of the Salt Lake and Logan Middle Mile Optical Network segments of the project, which were included in an Award Action Request approved last fall, are progressing on schedule as well. All associated contracts have been signed including 20 year Indefeasible Rights of Use (IRU) agreements with two providers, Zayo Networks and Syringa Networks. All site surveys have been completed and the site preparations and fiber installation is underway. The installation of equipment and lighting of the fiber for the Salt Lake segment is scheduled for completion during the second quarter. Other activities include equipment procurement and the continued development and distribution of information for community outreach purposes. | 44 | 1015 | 0 | 0 | 44 | 0 | 0 | 115 | This milestone is on schedule and accounts for seventy-six (76) percent of the total number of new fiber miles for the project. | This milestone is on schedule and accounts for seventy-five (75) percent of the total number of leased fiber miles for the project. Two IRUs recently acquired by the U of U/UEN account for one hundred thirty-two (132) miles or approximately ten (10) percent of the total miles of leased fiber for the project. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is on schedule and accounts for seventy-six (76) percent of the total number of new fiber miles for the project. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is on schedule and accounts for eighty-two (82) percent of the total number of CAIs for the project. | 4 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be pproviding the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 4 | 0 | 6 | All four sub-recipients that we have entered into agreements with, have existing service. | Four sub-recipients that we have entered into agreements with, will see improvements to existing services as a result of this project. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 6, 100 Mbps = 6, 10 Mbps = 6, 2 Mbps = 6 | 115 | 0 | 115 | 6 | The U of U/UEN has completed connectivity to twenty (20) CAIs during the first quarter of 2012 for a cumulative project total of one hundred fifteen (115), which meets the quarterly milestone. | None of the CAI installations completed this quarter is receiving new access. This is consistent with the Baseline Report. | All of the CAI installations completed this quarter are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 0, 1000 Mbps = 73, 100 Mbps = 34, 10 Mbps = 7, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is planning on continuing emphasis on the network build out activities and installation and turn up of CAIs. This includes the installation of fiber and Optical Transport nodes for the Salt Lake Middle Mile segment. The U of U/UEN is also working with our sub recipients to ensure timely completion of the security interests they will need to file. a. New network miles deployed = 53 b. New network miles leased = 1,132 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 132 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this past quarter have been related to construction activities such as crushed conduit, blocked inner-duct and getting pole permits for aerial fiber designs. Non of these obstacles could be anticipated nor did they have a negative impact on project milestones for the quarter, but required substantial time and manpower to work through. In all cases solutions were found and the project build out continued on schedule. | The major challenges facing the U of U/UEN for this upcoming quarter involve implementation activities and the network build out against the schedule. The careful monitoring of this work is important and quickly addressing obstacles faced by the Telecommunication Partners so that they do not impact projected milestones.
NT10BIX5570024 | 2012 | Q2 | Q2 - 2012 | For the second quarter of 2012, The University of Utah / Utah Education Network (U of U/UEN) is pleased to report significant progress in the continued build out of the network and connectivity of Community Anchor Institutions (CAIs). The U of U/UEN has completed the installation of fiber for the Salt Lake and Logan Middle Mile Optical segments which completes all but one (1) percent of the total fiber installation for the U of U/UEN BTOP project. This work also included the installation of Optronics equipment for the Salt Lake segment. A Re-budget Request submitted by the U of U/UEN this past April was approved by the NTIA in May and included one additional Optical Amplifier the for Logan Middle Mile segment and one hundred (100) gigabit optics for connecting the Salt Lake Middle Mile segment to the Internet 2 National Backbone. These additional parts have been ordered and delivery is expected during the third (3rd) quarter. The U of U/UEN has successfully completed connectivity to one hundred twenty-six (126) CAIs, which is ten (10) less than projected in our baseline. Obstacles encountered during fiber installations, such as crushed conduit have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone for the 2nd quarter. Other important activities include the continued development and distribution of information for community outreach purposes. | 54 | 1333 | 0 | 0 | 54 | 0 | 0 | 126 | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-three (93) percent of the total number of new fibers miles has been completed. As such, the U of U/UEN will miss this milestone for the quarter. | This milestone is on schedule and accounts for ninety-nine (99) percent of the total number of leased fiber miles for the project. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-three (93) percent of the total number of new fibers miles has been completed. As such, the U of U/UEN will miss this milestone for the quarter. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. The U of U/UEN has successfully completed connectivity to one hundred twenty-six (126) CAIs, which is ten (10) less than projected in our baseline. As such, the U of U/UEN will miss this milestone for the quarter. | 6 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive 5. Syringa Networks 6. Zayo | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Providers intend to make sue of this infrastructure by offering telecommunication services to residential and business customers on a retail basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be pproviding the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 6 | 0 | 6 | All four sub-recipients that we have entered into agreements with, have existing service. | Four sub-recipients that we have entered into agreements with, will see improvements to existing services as a result of this project. The two others are in support of fiber IRUs. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 6, 100 Mbps = 6, 10 Mbps = 6, 2 Mbps = 6 | 126 | 0 | 126 | 6 | The U of U/UEN has successfully completed connectivity to one hundred twenty-six (126) CAIs, which is ten (10) less than projected in our baseline. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone for the quarter. | None if the CAI installations completed is receiving new access This is consistent with the Baseline Report. | All of the CAI installations completed are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 0, 1000 Mbps = 81, 100 Mbps = 36, 10 Mbps = 8, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is planning on continuing emphasis on the network build out activities and installation and turn up of CAIs. The U of U/UEN is projecting that the installation and turn up of all CAIs will be completed during the 3rd quarter. We also expect to receive shipment and install the remaining optical transport hardware for the Logan Middle Mile segment, completing the implementation phase of the U of U/UEN Utah Anchors Community Broadband Project. a. New network miles deployed = 58 b. New network miles leased = 1,344 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 140 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this quarter have been related to construction activities. Specifically, crushed conduit and blocked inner-duct during fiber installations. Non of these obstacles could be anticipated, but required substantial time and manpower to resolve. These delays created enough slippage in the project schedule to cause the U of U/UEN to miss the milestone for CAIs connected for the 2nd quarter. | The major challenges facing the U of U/UEN for this upcoming quarter once again involves implementation activities and the network build out against the schedule. The careful monitoring of this work is important and the ability to quickly address unforeseen obstacles faced by the Telecommunications Providers so that they do not impact the projected milestones.
NT10BIX5570024 | 2012 | Q3 | Q3 - 2012 | For the third quarter of 2012, The University of Utah / Utah Education Network (U of U/UEN) is pleased to report continued progress with the network build out and connectivity of Community Anchor Institutions (CAIs), and a rapid approach to project completion projected for the fourth quarter. The U of U/UEN has completed the installation of fifty-seven (57) new fiber miles (98% of the project total) and thirteen hundred forty-four (1,344) new leased fiber miles (100% of the project total). One hundred thirty-four (134) of a total of one hundred forty (140) CAIs have been successfully connected. This is six (6) less than projected in our baseline for this quarter. Obstacles encountered during fiber installation, such as crushed conduit, have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone for the quarter. The Re-budget Request approved in May included one additional optical amplifier and one hundred (100) gigabit optics for connecting the Salt Lake Optical Middle Mile segment to the Internet 2 National Backbone. The supplier has indicated that these parts wonÂ¹t arrive during the third quarter as originally indicated. We are expecting shipment during the fourth quarter. Other notable activities include the continued development and distribution of information for community outreach purposes. | 57 | 1344 | 0 | 0 | 57 | 0 | 0 | 134 | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-eight (98) percent of the total number of new fibers miles has been completed. As such, the U of U/UEN will miss this milestone for the quarter. | This milestone is on schedule and accounts for one hundred (100) percent of the total number of leased fiber miles for the project. | No variance to Baseline Report | No variance to Baseline Report | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-three (93) percent of the total number of new fibers miles has been completed. As such, the U of U/UEN will miss this milestone for the quarter. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is behind schedule. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. The U of U/UEN has successfully completed connectivity to one hundred thirty-four (134) CAIs, which is six (6) less than projected in our baseline. As such, the U of U/UEN will miss this milestone for the quarter. | 6 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive 5. Syringa Networks 6. Zayo | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Providers intend to make sue of this infrastructure by offering telecommunication services to residential and business customers on a retail basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 6 | 0 | 6 | All four sub-recipients that we have entered into agreements with have existing service. | Four sub-recipients that we have entered into agreements with will see improvements to existing services as a result of this project. The two others are in support of fiber IRUs. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 6, 100 Mbps = 6, 10 Mbps = 6, 2 Mbps = 6 | 134 | 0 | 134 | 6 | The U of U/UEN has successfully completed connectivity to one hundred thirty-four (134) CAIs, which is six (6) less than projected in our baseline. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone for the quarter. | None if the CAI installations completed is receiving new access This is consistent with the Baseline Report. | All of the CAI installations completed are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 0, 1000 Mbps = 84, 100 Mbps = 40, 10 Mbps = 9, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is planning on continuing emphasis on the network build out activities and installation and turn up of the remaining CAIs during the 4th quarter. We also expect to receive shipment and install the remaining optical transport hardware for the Logan Middle Mile segment, completing the implementation phase. Aside from some invoicing and related payments that may carry over into the 1st quarter of 2013, the U of U/UEN is projecting that Utah's Broadband Technologies Opportunities Program project, Utah Anchors: A Community Broadband Project, will be completed in the 4th quarter of 2012. a. New network miles deployed = 58 b. New network miles leased = 1,344 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 140 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this quarter have been related to construction activities. Specifically, crushed conduit and blocked inner-duct during fiber installations. Non of these obstacles could be anticipated, but required substantial time and manpower to resolve. These delays created enough slippage in the project schedule to cause the U of U/UEN to miss the milestone for CAIs connected for the 3rd quarter. | The major challenges facing the U of U/UEN for this upcoming quarter once again involves implementation activities and the network build out against the schedule. The careful monitoring of this work is important and the ability to quickly address unforeseen obstacles faced by the Telecommunications Providers so that they do not impact the projected milestones.
NT10BIX5570024 | 2012 | Q4 | Q4 - 2012 | For the fourth quarter of 2012, The University of Utah / Utah Education Network (U of U/UEN) is pleased to report continued progress with the network build out and connectivity of Community Anchor Institutions (CAIs), and a rapid approach to project completion. The U of U/UEN has completed the turn up one additional CAI, the installation of equipment providing a one hundred (100) gigabit connection to the Internet 2 National Backbone and the installation of optical amplifiers supporting the fiber path to Utah State University. In total, the U of U/UEN has completed the installation of fifty-seven (57) new fiber miles (98% of the project total) and thirteen hundred forty-four (1,344) new leased fiber miles (100% of the project total) and one hundred thirty-five (135) of one hundred-forty (140) CAIs. The CAI count is five (5) less than projected in our baseline for this quarter. Continued obstacles encountered with fiber installation, such as crushed conduit, have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone. The U of U/UEN has submitted a BTOP request to extend the project deadline, which will allow for additional time to complete these outstanding CAI installations. Other notable activities include the continued development and distribution of information for community outreach purposes. | 57 | 1344 | 0 | 0 | 57 | 0 | 0 | 135 | This milestone is behind schedule. Obstacles encountered during installation, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-eight (98) percent of the total number of new fiber miles has been installed. As such, UEN will miss this milestone for the quarter. | This milestone is on schedule and accounts for one hundred (100) percent of the total number of leased fiber miles for the project. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is behind schedule. Obstacles encountered during installation, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-eight (98) percent of the total number of new fiber miles has been installed. As such, UEN will miss this milestone for the quarter. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is behind schedule. Obstacles encountered during installation, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. The U of U/UEN has successfully completed connectivity to one hundred thirty-five (135) CAIs, which is five (5) less than projected in our Baseline. As such, UEN will miss this milestone for the quarter. | 6 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive 5. Syringa Networks 6. Zayo | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Providers intend to make sue of this infrastructure by offering telecommunication services to residential and business customers on a retail basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 6 | 0 | 6 | All four sub-recipients that we have entered into agreements with have existing service. | U of U/UEN has entered into agreements with four (4) providers that will see improvements to existing services Two others are in support of fiber IRUs. Since the original submission of the U of U/UEN grant application and Baseline Report projections, several providers were not able to meet all of the Special Award Conditions and elected to opt out of the project, while other providers have been added for a total of six (6) signed agreements. It is for these reasons there is a discrepancy with the Baseline Report. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 6, 100 Mbps = 6, 10 Mbps = 6, 2 Mbps = 6 | 135 | 0 | 135 | 6 | The U of U/UEN has successfully completed connectivity to one hundred thirty-five (135) CAIs, which is five (5) less than projected in our baseline. Obstacles encountered during fiber installations, such as crushed conduit, have delayed the turn up of several CAIs, slipping our implementation schedule. As such, the U of U/UEN will miss this milestone for the quarter. | None of the CAI installations completed is receiving new access. This is consistent with the Baseline Report. | All of the CAI installations completed are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 0, 1000 Mbps = 85, 100 Mbps = 40, 10 Mbps = 9, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is continuing to focus on completing the network build out and installation and turn up of the remaining CAIs during the first quarter of 2013. The U of U/UEN has submitted a BTOP request to extend the project deadline, which will allow for additional time to complete this work. The U of U/UEN is projecting that Utah's Broadband Opportunities Program project, Utah Anchors: A Community Broadband Project, will be completed in the first quarter of 2013. a. New network miles deployed = 58 b. New network miles leased = 1,344 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 140 f. Number of signed agreements with broadband wholesalers or last mile providers = 4 | University of Utah, The | The U of U/UEN's major challenges during this quarter have been related to construction activities. Specifically, crushed conduit and blocked inner-duct during fiber installations. Non of these obstacles could be anticipated, but required substantial time and manpower to resolve. These delays created enough slippage in the project schedule to cause the U of U/UEN to miss the milestone for CAIs connected for the 4th quarter. The U of U/UEN has submitted a BTOP request to extend the project deadline, which will allow for additional time to complete these outstanding CAI installations. | The major challenges facing the U of U/UEN for this upcoming quarter once again involves implementation activities and the network build-out against the schedule. Approval by the NTIA to extend the project deadline will provide the additional time needed to complete the installation and turn up of the remaining CAIs.
NT10BIX5570024 | 2013 | Q1 | Q1 - 2013 | During the first quarter of 2013, the University of Utah / Utah Education Network (U of U/UEN) received approval for an extension to complete the build out of two Community Anchor Institutions (CAIs) in our project. This approval extends our grant deadline to May 31, 2013. During this period the U of U/UEN has also contracted four (4) additional IRUs to further develop network ring infrastructure that serves community institutions and will include procurement of additional networking equipment needed to support these new paths. A fifth (5) IRU contract is expected to be signed in April. Four (4) new CAIs have been added to the project during the extension period for a project total of one hundred forty-four (144). The U of U/UEN has completed connectivity to seven (7) CAIs during this first quarter of 2013, for a total of one hundred forty-two (142) completed CAIs. The U of U/UEN has completed the installation of over fifty-seven (57) new fiber miles (99% of the project total). An additional Seventy-five (75) new leased fiber miles have been added to the project in the form of IRUs, for a total of fourteen hundred nineteen (1,419) new leased fiber miles. The U of U/ has completed installation of thirteen hundred eighty (1,380) of these new leased fiber miles. The U of U/UEN continues to develop and provide community outreach materials in support of this project. | 57 | 1380 | 0 | 0 | 57 | 0 | 0 | 142 | This milestone is behind schedule. Obstacles encountered during installation, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-nine (99) percent of the total number of new fiber miles has been installed. As such, UEN will miss this milestone for the quarter. | This milestone is on schedule and accounts for 97% of the total number of leased fiber miles for the project. | No variance to Baseline Report | No variance to Baseline Report | This milestone is behind schedule. Obstacles encountered during installation, such as crushed conduit, have delayed the installation at some locations, slipping our implementation schedule. Despite this delay, ninety-nine (99) percent of the total number of new fiber miles has been installed. As such, UEN will miss this milestone for the quarter. | No variance to Baseline Report | No variance to Baseline Report | This milestone is on schedule. Four (4) additional CAIs were added to the project during the extension period, all but two (2) CAIs are connected or ninety-nine (99) percent of the project total. | 7 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive 5. Syringa Networks 6. Zayo 7. Integra | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Providers intend to make sue of this infrastructure by offering telecommunication services to residential and business customers on a retail basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 7 | 0 | 6 | All four sub-recipients that we have entered into agreements with have existing service. | U of U/UEN has entered into agreements with four (4) providers that will see improvements to existing services Three others are in support of fiber IRUs. Since the original submission of the U of U/UEN grant application and Baseline Report projections, several providers were not able to meet all of the Special Award Conditions and elected to opt out of the project, while other providers have been added for a total of seven (7) signed agreements. It is for these reasons there is a discrepancy with the Baseline Report. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 7, 100 Mbps = 7, 10 Mbps = 7, 2 Mbps = 7 | 142 | 0 | 142 | 6 | The U of U/UEN has successfully completed connectivity to one hundred forty-two (142) CAIs. Four (4) additional CAIs were added to the project during the extension period, all but two (2) CAIs are connected or ninety-nine (99) percent of the project total. | None of the CAI installations completed is receiving new access. This is consistent with the Baseline Report. | All of the CAI installations completed are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 4, 1000 Mbps = 85, 100 Mbps = 41, 10 Mbps = 11, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is continuing to focus on completing the network build out, installation and turn up of the remaining CAIs. The U of U/UEN is scheduled to complete the Broadband Opportunities Program Project, Utah Anchors; A Community Broadband Project by the end of the grant period on May 31, 2013. These activities will include signing a contract for one remaining IRU, installation and turn up of two (2) remaining CAIs and the remaining installation of network and optical equipment. a. New network miles deployed = 58 b. New network miles leased = 1,419 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 144 f. Number of signed agreements with broadband wholesalers or last mile providers = 7 | University of Utah, The | The U of U/UEN's major challenges during this quarter have been related to construction activities. Specifically, crushed conduit and blocked inner-duct during fiber installations. None of these obstacles could be anticipated, but required substantial time and manpower to resolve. These delays created enough slippage in the project schedule to cause the U of U/UEN to miss the milestone for CAIs connected for the 4th quarter. The U of U/UEN received approval from the NTIA for an extension to complete installation of these outstanding CAIs. | The U of U/UEN will closeout our BTOP project, Utah Anchors; A Community Broadband Project effective May 31st, 2013.
NT10BIX5570024 | 2013 | Q2 | Q2 - 2013 | As of May 31st, 2013, the University of Utah / Utah Education Network (U of U/UEN) completed build out and implementation of the Broadband Technologies Opportunity Program Project entitled Utah Anchors; A Community Broadband Project. The U of U/UENâ€™s Community Anchorâ€™s infrastructure project has resulted in extending infrastructure to one hundred forty-two (142) community anchor sites including fiber-optic connections to seventy-four (74) Elementary Schools, twenty (20) charter schools and eighteen (18) public libraries, and fast broadband to twenty (20) Pre-K Head Start programs. In addition, UEN developed a research middle mile optical ring network with Utah research universities, including establishing one hundred (100) Gbps core wavelength connections to the Internet2 national backbone and U.S. UCAN network. This project greatly benefited eight (8) higher education campuses and four (4) governmental facilities/agencies by extending middle mile and last mile optical networking research infrastructure and capabilities to these institutions. Over forty-eight (48) local communities statewide benefited from the extension of fiber that businesses, residences, and employers have also been able to utilize with UENâ€™s sub recipients. Project totals include the installation of fifty-eight (58) new fiber miles and fourteen hundred nineteen (1,419) new leased fiber miles The U of U/UEN has been completing the BTOP Project Closeout. The U of U/UEN would like to extend our appreciation and thanks to our NTIA program officers; namely Doug Kinkoph , Janice Wilkins, and Michael Murphy of Booz Allen Hamilton, for all of their support and direction which contributed to the success of this project. | 58 | 1419 | 0 | 0 | 58 | 0 | 0 | 142 | This milestone is on schedule and represents one-hundred (100) percent of the project total. | This milestone is on schedule and represents one-hundred (100) percent of the project total. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is on schedule and represents one-hundred (100) percent of the project total. | No variance to Baseline Report. | No variance to Baseline Report. | This milestone is on schedule and represents one-hundred (100) percent of the project total. | 7 | 0 | 40 | 1. Qwest Communications Corporation / CenturyLink 2. UTOPIA (Utah Telecommunications Open Infrastructure Agency) 3. CentraCom Interactive 4. Wireless Beehive 5. Syringa Networks 6. Zayo 7. Integra | The U of U/UEN is not a wholesale provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Providers who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Providers intend to make sue of this infrastructure by offering telecommunication services to residential and business customers on a retail basis in these service areas. | All of the following Telecommunications Partners are sub recipients and will operate a portion of the U of U/UEN network. They will be providing the U of U/UEN with an end to end service that includes responsibility for monitoring, managing and maintaining the fiber physical infrastructure as well as the optical transport equipment. In all cases this includes Customer Premise Equipment (CPE) that will require on site access by the Telecommunications Partners for troubleshooting and or maintenance of this equipment. 1. Qwest Communications Corporation / CenturyLink (sub recipient) - Salt Lake City, Utah, (800) 899-7780 2. UTOPIA (sub recipient) - West Valley City, Utah, (801) 613-3800 3. CentraCom Interactive (sub recipient) - Fairview, Utah, (800) 427-8449 4. Wireless Beehive (sub recipient) - Lakepoint, Utah, (435) 837-6000 | 0 | 7 | 0 | 6 | All four sub-recipients that we have entered into agreements with have existing service. | The U of U/UEN has entered into agreements with four (4) providers that will see improvements to existing services. Three others are in support of fiber IRUs. Since the original submission of the U of U/UEN grant application and Baseline Report projections, several providers were not able to meet all of the Special Award Conditions and elected to opt out of the project, while other providers have been added for a total of seven (7) signed agreements. It is for these reasons there is a discrepancy with the Baseline Report. | There are no dark fiber segments included in this project which is consistent with the Baseline Report. | 100000 Mbps = 1, 10000 Mbps = 4, 1000 Mbps = 7, 100 Mbps = 7, 10 Mbps = 7, 2 Mbps = 7 | 142 | 0 | 142 | 6 | The U of U/UEN has successfully completed connectivity to one hundred forty-two (142) CAIs. This accounts for one-hundred (100) percent of the project total. | None of the CAI installations completed is receiving new access. This is consistent with the Baseline Report. | All of the CAI installations completed are receiving improved access. This is consistent with the Baseline Report. | 100000 Mbps = 0, 10000 Mbps = 4, 1000 Mbps = 85, 100 Mbps = 41, 10 Mbps = 11, 2 Mbps = 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The U of U/UEN is not providing any special offerings. | FALSE | The U of U/UEN has not changed its Network Management Practices during this past quarter. | The U of U/UEN is now in the project Closeout period. All of our efforts are directed toward the timely completion of these activities. The following are project totals: a. New network miles deployed = 58 b. New network miles leased = 1,419 c. Existing network miles upgraded = 0 d. Existing network miles leased = 0 e. Total CAI subscribers served (CAIs connected) = 142 f. Number of signed agreements with broadband wholesalers or last mile providers = 7 | University of Utah, The | The U of U/UEN completed all Installations by the Award End Date and the closeout documentation is being submitted by the Closeout end date of 8/29/2013. | The U of U/UEN is completing closeout activities for the BTOP project, Utah Anchors; A Community Broadband Project .
NT10BIX5570025 | 2010 | Q3 | Q3 - 2010 | Zayo was notified of three route changes after we submitted our original draft EA. These route changes are being driven by the pole providers along the route as well as an airport expansion project. Zayo had to make changes to our original draft EA submittal. Because of these changes, we have had to issue 2 mods that increased our EA cost and delayed our schedule. Because of the extra EA work and engineering issues, Zayo has had an increase in labor cost. This explains our increase in expenditures. Zayo received permission from the Government to proceed with engineering while waiting on our draft EA submittal and our FONSI. The third draft EA was submitted on September 28, 2010. Our Draft EA is done, but because it was the last day of the quarter, we have not been invoiced for this yet. Zayo issued our Engineering RFP to 10 firms on September 1, 2010. Received Bids back on September 8, 2010. Based on the information we received back, Zayo determined that based on the size of the project and the time limit we had for the engineering phase, we would award the route in three sections to the three lowest bidders. Zayo Awarded the Engineering to RCG, TurnKey and JDH. All three are small businesses and familiar with the pole providers in the area as well as with this type of work and government. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Draft Environmental Assessment is 100% complete. Construction will begin when the EA and Engineering is complete. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | None Currently | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Once Zayo starts building, we will be offering Fiber to the Tower. | FALSE | N/A | Zayo should have our FONSI for our EA by the end of October. Zayo should have our Engineering done by the end of December and have our permit applications submitted to the proper authorities and pending approval. | Zayo Bandwidth, LLC | None this quarter. | None
NT10BIX5570025 | 2010 | Q4 | Q4 - 2010 | 11/23/10 Zayo received our FONSI. Mid November Zayo put together our Engineering Request for Proposal (RFP) and sent it out to 11 subcontractors. Zayo issued the Engineering work to 3 subcontractors based on our competitive bid process. Zayo issued this work to three subcontractors based on the amount of work and in order to insure that we meet our project deadline. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | This project is a middle mile project. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Zayo is a middle mile provider and special offerings will be made by last mile providers. | FALSE | N/A | Next quarter Zayo should start purchasing and deploying equipment we should also start site preparation. | Zayo Bandwidth, LLC | Zayo is currently working on getting route approval for five route changes. Zayo is making these changes to both meet our customers needs in connecting their sites as well as based on our route design and engineering. | Zayo is not anticipating any issues at this time other than the weather issues that we outlined above.
NT10BIX5570025 | 2011 | Q1 | Q1 - 2011 | 3 Engineering firms have completed about 85% of Engineering Computer Aided Drafting work and have submitted about 65% of the required pole attachment permit applications. There is about a 60 day turnaround time for pole permits. Some are just now coming in. In January we sent out the RFP for the Archeological requirements per the PA between Zayo the Indiana SHPO and BTOP. Our Archeological firm is about 70% done with the work required by the Progamatic Agreement. Zayo went through the materials Request For Proposal (RFP) process for materials. Bids are due back in early April. Sent out a RFP for a consultant for one of our pole providers. Zayo needed a consultant to work with one of our pole providers on our pole permit applications. Bids are due in early April. Zayo should have enough permits come in this April so that we can start construction on segments in May. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | This project is a middle mile project. The Wholesale services will be provided by the last mile service providers. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Zayo is a middle mile provider and special offerings will be made by last mile providers. | FALSE | N/A | Next quarter Zayo should award our materials contract, start purchasing and deploying equipment, start site preparation and start construction on some segments. | Zayo Bandwidth, LLC | Zayo's biggest issue has been dealing with some of the smaller utilities we need pole attachment agreements with. Many of these smaller companies are understaffed and were not prepared to process the volume of permits that we need. | Zayo is not anticipating any issues at this time other than the permitting and acquisition issues that we outlined above.
NT10BIX5570025 | 2011 | Q2 | Q2 - 2011 | 3 Engineering firms have completed about 95% of Engineering CAD work and have submitted about 85% of the required pole attachment permit applications. There is about a 60 day turnaround time for pole permits. Some are just now coming in. In January we sent out the RFP for the Archeological requirements per the Programmatic Agreement between Zayo the Indiana SHPO and BTOP. The award went to Gray and Pape, Inc. Gray and Pape are about 95% done with the work required by the PA. Awarded our materials contract. Zayo has been ordering cable and storing it in our warehouse so that it does not slow down construction waiting on materials. Zayo awarded our Warsaw route for construction after going through our competitive bid process. We have also awarded our splicing contract and are awaiting approval from DOL on our rate proposal. Zayo has also awarded construction of our Newburgh to Huntingburg route and have sent out the rest of our core ring for competitive bid. Zayo's sales team is reaching out to our CAI's and last mile providers on a weekly basis. | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | These will be placed along the route as needed. This will happen as we build the network. Zayo should be on target by Q1 2012. | 0 | 0 | 0 | 0 Zayo will develop these as we get more of the network built. Cannot sell what we do not have. We plan to be back on schedule by the end of Q1 2012. | N/A | N/A | 0 | 0 | 0 | 0 | Zayo will be on target by Q1 2012. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Zayo should have the rest of our construction awarded and start making up time on our construction progress. We should also be complete or close to complete with having all of our permits and ROW's. Our consultant should have hut site acquisition close to complete. With our construction moving forward, we should make great progress on materials acquisition and deployment. | Zayo Bandwidth, LLC | Areas where we have had issues is permitting because of staffing at the permitting offices. We have been working with the BTOP office to get approval on reroutes and site changes requested by our customer. Splicing has also been a little delayed because we had to submit a SF 1444 to the DOL because there is not a splicer rate on the current WD as required by the Davis Bacon Act. The BTOP program office has also been very helpful with this process. | At this time we are not anticipating any issues or challenges for next quarter that will need BTOP assistance. As stated above, our goal is to do our best to close the gaps where we are currently behind and stay ahead of our baseline where identified above. Zayo's overall goal is to be 90% complete overall by the end of Q4 2011.
NT10BIX5570025 | 2011 | Q3 | Q3 - 2011 | Zayo awarded the last of our segments for construction. Zayo also had our government site visit this quarter. | 140 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | This is on 311 behind our baseline. This has to do with the issues in 3 above. Zayo should be caught up on 2 quarters. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on 311 behind our baseline. This has to do with the issues in 3 above. Zayo should be caught up on 2 quarters. | This is on target with our baseline. | This is on target with our baseline. | This is 41 behind our baseline. We should be caught up by next quarter. | 0 | 30 | 0 | Zayo is behind on signed agreements because we are behind on our network miles deployed. We plan to be caught up in 2 quarters when we get caught up on our network miles deployed. | None | None | 0 | 0 | 0 | 0 | This is on target with our baseline. | This is two less than identified in our baseline. Zayo is working to secure these agreements. | This is on target with our baseline. | This is on target with our baseline. | 0 | 0 | 0 | 0 | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | 0 | 0 | 0 | 0 | 0 | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | 0 | 0 | 0 | 0 | 0 | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | This is on target with our baseline. | None | FALSE | N/A | Zayo should have another 260 miles of construction completed for a total of 400 Miles. | Zayo Bandwidth, LLC | Zayo's biggest challenge has been in make ready and permitting. Zayo has run into excessive pole change out cost in certain areas. In areas where there is a large number of poles, Zayo has come up with a plan to dip underground and avoid these excessive costs. Zayo is working to submit a plan for this action and is working with our environmental team to take the appropriate action to get our EA amended and plan approved. | Even though we are behind based on the financial numbers presented in our baseline, based on miles completed in our build we should be about 85% completed with the project based on actual work done. Zayo needs to file a Waiver for our match based on our in-kind contribution. 10% of our match is in-kind contribution which cannot be recognized until it is tied into the route and turned over to the government. This should be complete by the end of Q2 of Year 3.
NT10BIX5570025 | 2011 | Q4 | Q4 - 2011 | Zayo requested a Termination for Convenience with an effective date of 9/30/11 for this project. Zayo Bandwidth, LLC was absorbed by its parent Zayo Group, LLC. Zayo has asked for a termination for convenience of the current grant and is asking NTIA and BTOP to reissue the grant under a new grant to Zayo Group, LLC. Zayo is pursuing this course of action under the direction of NTIA and BTOP. Zayo is continuing to build and fully commit to this project because of our commitment to both the project and or faith in the NTIA and BTOP. Zayo has continued to build and is actually at 38% build based on dollars spend and 41% based on actual miles built (264 miles of 645). This information will be on the first quarter report of our new award. Zayo I- Light applied for 480 permits by 9-30 2011 Rail Road -40 INDOT â€“ 214 County â€“ 163 City â€“ 73 As of 9-30-2011 62% of the permits have been approved â€¢ Executed pole attachment agreements with 20 REMCâ€™s, 2 AHJâ€™s and two Cityâ€™s Total Project: 16,205 pole attachments. Wabash County REMC, Kosciusko REMC, Noble REMC, Northeastern REMC, Harrison REMC, Vectren, Utilities District of Western Indiana REMC, Dubois REMC, Win Energy REMC, Southeastern Indiana REMC, Rush Shelby Energy REMC, Richmond Power and Light, Henry County REMC, White Water Valley REMC, Southern Indiana Power, South Central REMC, Bartholomew County REMC, Hendricks Power Cooperative REMC, Kankakee Valley REMC, White Water Valley, Clark County REMC, Daviess Martin County REMC, City of Huntingburg, City of Jasper, City of Linton United REMC, Johnson County REMC Met with all pole owners and went over detailed drawings. As of 9-30 2011 â€¢ 8,120 poles or just over 50% of the make ready has been completed Place Material Orders and secured warehouse in Mitchell Indiana â€¢ Fiber Optic cable 3.7 million feet â€¢ Duct 739,200â€™ 1.25â€ â€¢ Pole line Hardware 650 miles Construction â€¢ Completed: Warsaw south, East, North, totaling 82 miles new build and 78 miles In-kind contribution. â€¢ Completed: Ivy Tech Warsaw lateral â€¢ Started: Ivy Tech Goshen, Evansville, Lafayette, Monticello, Gary, LA Porte. | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | This is behind our baseline. This has to do with the issues in 3 above. | This is on target. | This is on target. | This is on target. | This is behind our baseline. This has to do with the issues in 3 above. | This is on target. | This is on target. | This is 41% behind our baseline. | 0 | 30 | 0 | Zayo is behind on our signed agreements because we are behind on our miles deployed. | None | None | 0 | 0 | 0 | 0 | This is on target. | This is 2 behind our target. | This is on target. | This is on target. | 0 | 0 | 0 | 0 | This is on target. | This is on target. | This is on target. | This is on target. | 0 | 0 | 0 | 0 | 0 | This is on target. | This is on target. | This is on target. | This is on target. | This is on target. | 0 | 0 | 0 | 0 | 0 | This is on target. | This is on target. | This is on target. | This is on target. | This is on target. | None | FALSE | N/A | This agreement should be terminated. | Zayo Bandwidth, LLC | Please see #1 above. | This award should be terminated.
NT10BIX5570026 | 2010 | Q3 | Q3 - 2010 | After completing the environmental assessment, KINBER has received a FONSI and is able to proceed with project construction. KINBER is still in negotiations with its contractor FIBERTECH (FT) related to a 20-year maintenance agreement and finalization of the purchase agreement (construction contract). However FT has requested a waiver of the mandatory performance bond for 100% of the project cost. If FT is not successful in obtaining a waiver, KINBER will need to select another contractor through a competitive RFP process. KINBER has begun developing an RFP as a contingency plan. KINBER has engaged an audit firm to conduct an annual financial review. KINBER staff and board members continue to attend public and professional meetings to promote the project. This included the first statewide Pennsylvania Broadband Summit where KINBER participated as a vendor with an informational booth. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | . . | n/a | n/a | n/a | . | n/a | n/a | . | 0 | 0 | 0 | No agreements signed yet. | KINBER is still developing its preliminary schedule of services and related prices. A draft services document was submitted on our Q2 report and is still under review. | n/a | 0 | 0 | 0 | 0 | . | . | . | 1G to 10G Ethernet | 0 | 0 | 0 | 0 | . | . | . | 100M to 10G Ethernet | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | KINBER has provided a draft services document as an attachment to the Q2 report. This document is till under internal review. | FALSE | n/a | Completion of the RFP process, selection of construction vendor(s) and engagement in both the master maintenance agreement and fiber purchase agreement (construction contract). Initial drawdown of federal grant funds. Completion of annual audit and 990 form. | Keystone Initiative For Network Based Education and Research | KINBER's current vendor, FIBERTECH has requested a waiver of the performance bond requirement. KINBER is currently working with their program officer to determine if this is possible. In the meantime, KINBER has started a RFP process if the waiver request is unsuccessful since KINBER will need to select a new vendor or vendors to build the network. Without the waiver, the construction process will be stalled by at least 3 months due to the RFP process, vendor selection and contract negotiations. If necessary, KINBER anticipates being able to select a new contractor in mid-December 2010 and start pre-construction work (make ready and permitting) in January 2011. | KINBER anticipates entering into purchase and master maintenance agreements with a new vendor or vendors by December 2010. Negotiations related to these agreements may take longer than anticipated.
NT10BIX5570026 | 2010 | Q4 | Q4 - 2010 | KINBER initiated and completed a competitive RFP process to identify and select a new (replacement) construction vendor. This was necessitated in Q4 due to the original vendor (Fibertech) being unable to obtain a performance bond. KINBER was able to select a new vendor (BlairPark/Sunesys) as well as negotiate and execute the following agreements: Fiber Purchase and Master Facilities Agreement, Master Maintenance Agreement, Contribution Agreement, and Cable Overlash and Indefeasible Right to Use Agreement. KINBER engaged an independent Auditing firm to complete the organization's first fiscal review and audit. The audit had no findings. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | . | n/a | . | n/a | 0 | n/a | n/a | 0 | 0 | 0 | 0 | None yet. | The services that KINBER has proposed to offer have not changed since the Services Document was uploaded in a previous report. Pricing is still in development. | n/a KINBER will operate its own network. | 0 | 0 | 0 | 0 | . | . | . | 1G to 100 G Ethernet | 0 | 0 | 0 | 0 | . | . | . | 100M to 10G Ethernet | 0 | 0 | 0 | 0 | 0 | . | . | . | . | . | 0 | 0 | 0 | 0 | 0 | . | . | . | . | . | None | FALSE | n/a | Negotiation of member node agreements. Informational webinars will be provided to community anchor institutions. Press releases related to the award of the construction contracts will increase KINBER project awareness across the Commonwealth. Site surveys will be completed and site preparation will begin. Vendor will begin ordering process for fiber optic materials. | Keystone Initiative For Network Based Education and Research | The RFP process occurred during Q4 and delayed the construction of the project. | Weather in Q1 2011 may contribute to delays in pole attachment and related construction.
NT10BIX5570026 | 2011 | Q1 | Q1 - 2011 | Construction began in this quarter resulting in the first eleven (11) miles of fiber hung in areas outside of Philadelphia and Pittsburgh. 56 of the 62 site surveys have been completed and the engineering process has begun at many of these sites. Approximately 20% of the required pole permits have been submitted for approval. KINBER has applied for and been granted provisional CAP (Competitive Access Provider) status in Pennsylvania. Also in this Quarter, KINBER's Primary Investigator and Point of Contact was changed to reflect the change in personnel from an interim Executive Director to a full-time Executive Director. KINBER received and accepted its final financial audit which contained no findings. | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | Eleven miles of fiber have been overlashed to date, Project is on schedule for 237 network miles to be deployed in Q4 2011. | n/a for this project | n/a for this project | n/a for this project | 11 miles of fiber were overlashed in Q1 | n/a for this project | n/a for this project | none at this time, project is on schedule for interconnection points in Q4 2011. | 0 | 0 | 0 | None yet. | Services and pricing are still under development | n/a KINBER is planning to operate the PennREN network. | 0 | 0 | 0 | 0 | Network not yet built, can not provide services at this time. | Network not yet built, can not provide services at this time. | Network not yet built, can not provide services at this time. | 100M to 10G Ethernet | 0 | 0 | 0 | 0 | Network not yet built, can not provide services at this time. | Network not yet built, can not provide services at this time. | Network not yet built, can not provide services at this time. | Network not yet built, can not provide services at this time. | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None. | FALSE | N/A | RFP process begun to procure equipment and related professional services. Completion of Regional informational awareness session to increase awareness about KINBER across the Commonwealth. Hire a Lead Network Engineer (not using Program funds). All pole permit applications submitted. | Keystone Initiative For Network Based Education and Research | Construction activities have been delayed due to reissuing the construction RFP and changing vendors in Q4 2010. We have accelerated our construction schedule to make up this time loss. Although network design and construction activities have begun, KINBER did not receive any invoices by the end of Q1 2011 and therefore does not yet show expenditures. The only construction related expenses were $19,250 to pay for the Environmental Assessment. | Receiving signed node agreements from CAIs; the length of time it takes to get permitting completed for the 60,000+ poles that we need to attach fiber to, especially with regards to accessing Verizon's conduit.
NT10BIX5570026 | 2011 | Q2 | Q2 - 2011 | During Quarter 2 of 2011; KINBER took receipt of 1,030 miles of fiber. So, far 60 aerial miles of fiber have been strung. All of the approved project engineering has been completed, 58 site surveys and building entrance drawings have been completed of the 62 identified community access institutions on the PennREN network. Construction on these sites is scheduled to begin in late July. Of the anticipated 1,480 pole permit applications that are needed to build the network; 80% of the make ready applications have been submitted. It is anticipated that coordinating the total 43,842 poles into1,480 grouped permits will reduce the processing and approval time. KINBER submitted a minimally revised environmental assessment for review due to minor route changes that occurred during the construction process and expects to receive approval early in Q3, 2011. Construction has been halted on the network until the revised EA can be approved. KINBER also requested Davis Bacon Wage rates from the Department of Labor and is awaiting their approval. The RFP process to procure hardware, equipment and related services was released. Vendor selection will be made in Q3, 2011. KINBER received their Certificate of Public Convenience, certifying KINBER as a Competitive Access Provider in Pennsylvania. The KINBER staff participated in an on-site desk audit program review with Federal program office staff. Candidates for the lead engineer position were interviewed. It is anticipated that this new | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 miles over aerial fiber (via overlash) have been hung | n/a for this project | n/a for this project | n/a for this project | 60 miles over aerial fiber (via overlash) have been hung. | n/a for this project | n/a for this project | None at this time, project is on schedulen schedule. | 0 | 0 | 0 | None at this time. | Services and pricing models are currently under development. KINBER has hired an outside firm to complete a current market analysis of price and service offeringse currently under development. KINBER has hired an outside firm to complete a current market analysis of price and service offerings. | KINBER will operate the PennREN network. | 0 | 0 | 0 | 0 | Network construction in-on-going. There are no services offered or subscribers at this time. | Network construction in-on-going. There are no services offered or subscribers at this time. | Network construction in-on-going. There are no services offered or subscribers at this time. | 100M to 10G | 0 | 0 | 0 | 0 | Network construction in-on-going. There are no services offered or subscribers at this time. | Network construction in-on-going. There are no services offered or subscribers at this time. | Network construction in-on-going. There are no services offered or subscribers at this time. | Network construction in-on-going. There are no services offered or subscribers at this time. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER is not providing last mile or residential services. | n/a. KINBER is not providing last mile or residential services. | n/a. KINBER is not providing last mile or residential services. | n/a. KINBER is not providing last mile or residential services. | n/a. KINBER is not providing last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER is not providing services to businesses. | n/a. KINBER is not providing services to businesses. | n/a. KINBER is not providing services to businesses. | n/a. KINBER is not providing services to businesses. | n/a. KINBER is not providing services to businesses. | None. | FALSE | n/a | Award and negotiate contract with equipment and design services vendor; release NOC services RFP; hire lead network engineer, speak at community outreach events, and engage replacement marketing and communications director. KINBER anticipates the network design to be 100% complete and an additional 200 miles of overlashed fiber to be hung. New aerial fiber construction will begin in 11Q4. All site surveys and building entrance drawings will be completed for the 62 identified community access institutions on the PennREN network. Node site construction will begin and cabinets will be installed in 50% of node sites. | Keystone Initiative For Network Based Education and Research | KINBER has proposed slight route changes due to conditions that presented themselves during final route mapping (bridge crossing permits that were denied, previously existing poles that have been removed, etc.) that require a revised environmental assessment. KINBER is also waiting for the Department of Labor to approve new Davis Bacon Wage rates. KINBER entered into a fixed-price contract with its construction vendor and only makes payments based on completed activities tied to a progress and payment schedule. There has been a lot more progress on the construction of the network than can not yet be reported here because KINBER has not yet been invoiced for the work. | Right of way acquisition and pole make ready work delays are possible due to the response of the local utilities. Ultimate and timley resolution of the possible overlap with the Zito Media project in Northwestern PA. KINBER had anticipated a large invoice form its construction vendor in late September 2011; but funds through ASAP will be unavailable from September 15 - October 1, 2011 and may push those payments into 11Q4.
NT10BIX5570026 | 2011 | Q3 | Q3 - 2011 | As of Q3 2011 KINBER has hung 325 miles of fiber, mostly in the Philadelphia and Pittsburgh regions. 98% of all network backbone engineering is complete and 90% of all make-ready application have been submitted. 60 of the 62 node site building surveys have been completed and of these, construction has been completed on 28. Ten (10) node locations of the 62 have had network equipment cabinets installed. KINBER received approval (FONSI) on their revised environmental assessment. The revision was necessary due to slight route changes. KINBER awarded a contract to a vendor for the procurement of network hardware, software, and related professional services after successfully completing a competitive request for proposal (RFP) process. It is anticipated that the hardware will be ordered and some will be received within Q4, 2011. Currently, KINBER has an open Network Operations Center (NOC) RFP which they expect to award in Q4, 2011. KINBER hired a full-time lead network engineer and expects to start the employment process of recruiting two additional engineers in Q4 2011. KINBER had a face to face meeting with their new federal program officer and reviewed project progress. KINBER expects to complete their annual financial audit in Q4, 2011. KINBER continues to develop its outreach activities and anticipates launching a branding campaign in Q3 2011 while capitalizing on opportunities to promote the PENNREN network publicly. KINBER continues to receive frequent requests fr | 325 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | KINBER has exceeded its milestone in this category | n/a for this project | n/a for this project | n/a for this project | 325 aerial miles have been hung | n/a for this project | n/a for this project | None at this time, project is on scheduln schedule | 0 | 3 | 0 | None at this time. | Services and pricing models are still under development. KINBER has hired an outside firm to complete a current market analysis of price and service offerings to advise the Board and staffe still under development. KINBER has hired an outside firm to complete a current market analysis of price and service offerings to advise the Board and staff. | N/A. KINBER will operate the PennREN network. | 0 | 0 | 0 | 0 | Network construction is on-going. there are no services being offered or subscribers at this time. | Network construction is on-going. there are no services being offered or subscribers at this time. | Network construction is on-going. there are no services being offered or subscribers at this time. | 100M to 1G | 0 | 0 | 0 | 0 | Network construction is on-going. there are no services being offered or subscribers at this time. | Network construction is on-going. there are no services being offered or subscribers at this time. | Network construction is on-going. there are no services being offered or subscribers at this time. | Network construction is on-going. there are no services being offered or subscribers at this time. | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | n/a KINBER is not providing last mile or residential services | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not providing services to businesses | n/a KINBER is not providing services to businesses | n/a KINBER is not providing services to businesses | n/a KINBER is not providing services to businesses | n/a KINBER is not providing services to businesses | None | FALSE | n/a | It is projected that KINBER will have over 600 miles of fiber hung by the end of Q4, 2011. All network equipment will be ordered and some will be delivered for testing. We will award the NOC services contract; advertise to hire two additional network engineers; and resolve the Zito overlap situation. KINBER will begin a marketing/branding campaign, develop a draft services and pricing model for Board review, complete the annual audit, and start planning for network member days in Spring 2012. Additionally, KINBER staff will be making presentations to various heads of PA state Government. We will continue to build relationships, revise our webpage and increase communication throughout out entire service region. Although no CAIs will be connected Q4, 2011 we will be poised to have up to 4 connected in Q1, 2012. We also plan on being in early negotiations with 3-4 last mile providers. | Keystone Initiative For Network Based Education and Research | Overall project construction has been delayed due to a number of events. First, KINBER changed construction vendors approximately 6 months into the project which pushed the entire schedule back. KINBER is currently awaiting a decision to move forward with a solution to potential overlap of fiber routes with the Zito Media project in Northwestern Pennsylvania. Finally,Hurricane Irene not only stopped aerial fiber construction but it slowed the ability of utility companies being able to review rights of way and issue permits since their linemen were fixing storm related damage in Northeastern Pennsylvania. The approval time for rights of way and permits continues to delay the project as well. Fortunately, the project schedule was developed with enough of a time cushion built in that none of these delays should impact an on-time project completion. KINBER is proactively working with its construction partner to ensure the timley completion of the project. | As we enter the winter season, weather may impact the construction schedule. Additionally, time to get permits and right of way approvals may also delay the project.
NT10BIX5570026 | 2011 | Q4 | Q4 - 2011 | At the end of Q4, 2011; KINBER reports 548 miles of fiber completed. Sixty (of 62) building surveys have been completed and the building fiber entrance construction has been completed on 43 sites. Electronics cabinets have been installed in 28 locations. KINBER received approval to proceed with a cooperative overlash agreement with another BTOP awardee, Zito Media LLC. The final environmental assessment is being prepared for submission. The first round of purchased hardware has been received, staged, inventoried and tested. Purchase orders were issued for the second and third round of hardware purchases. KINBER has established a staging facility for receipt of hardware for testing and inventory work Additionally, KINBER has concluded and submitted the annual financial and A-133 audits. No issues were identified by the auditors. The business plan was completed and a 5-year strategic planning process has begun. Services to be delivered and a pricing structure have been developed. KINBER signed a Network Operation Center (NOC) service provider agreement and is negotiating an out-of-band management circuit provider agreement. | 548 | 0 | 0 | 0 | 548 | 0 | 0 | 0 | This exceeds the baseline plan of 237 miles complete. | n/a for this project | n/a for this project | n/a for this project | This exceeds the baseline plan of 237 miles complete. | n/a for this project | n/a for this project | None at this time. | 0 | 3 | 0 | None at this time. | Service and pricing models were drafted and presented to the KINBER Board of Directors in Q4 2011 and are currently under review. | n/a. KINBER will operate the PennREN network. | 0 | 0 | 0 | 0 | Network construction is on-going. No services are being offered at this time. | Network construction is on-going. No services are being offered at this time. | Network construction is on-going. No services are being offered at this time. | 100 M to 10 G | 0 | 0 | 0 | 0 | Network construction is on-going. No services are being offered at this time however 43 sites have been prepped for fiber entrance from outside poles. It is anticipated that 13 sites will be connected to the network in Q1 2012. | Network construction is on-going. No services are being offered at this time. | Network construction is on-going. No services are being offered at this time. | Network construction is on-going. No services are being offered at this time. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be providing last mile or residential services. | n/a. KINBER will not be providing last mile or residential services. | n/a. KINBER will not be providing last mile or residential services. | n/a. KINBER will not be providing last mile or residential services. | n/a. KINBER will not be providing last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | None. | FALSE | n/a | The project will be substantially complete. (Overall project greater than 66% complete). 700 miles of fiber will be strung and six segments (B,C, F, G, L, and M) will be lit. Ten (10) CAIs will be connected. All equipment will be received and tested. At least one last mile provider will be in contract negotiations. KINBER expects to receive its final EA approval for the route change necessitated by the Zito Media project overlap. We will hire an additional network engineer and finalize plans for a two-day "member networking" event to showcase the services and potential of the PennREN network and facilitate conversations about collaboration. | Keystone Initiative For Network Based Education and Research | It was necessary to request a route change due to a potential overlap with another BTOP funded project. (Zito Media). The related environmental assessment (EA) has slowed down construction progress on that section of the network. Once the EA is approved, progress will begin. The project is also trying to catch up from a 2-3 week delay related to weather in Q3 2011. In order to reduce liability and cost, and increase the efficiency of equipment delivery, KINBER elected to receive, inventory, test and configure its optical and network equipment in two staging facilities, strategically located in the state. This slowed the initial deployment of equipment to node sites; but will facilitate a more coordinated and rapid deployment in the next two reporting quarters. | Winter weather is always an unpredictable factor. Conduit approvals on bridge crossings near Pittsburgh are the only potential challenge identified in the upcoming quarter.
NT10BIX5570026 | 2012 | Q1 | Q1 - 2012 | KINBER met the grant special award condition to have the project substantially complete by February 2012. In fact, many of the baseline milestones were exceeded. At the end of Q1, 2012; KINBER reports 787 miles of fiber completed. Thirty-nine (39) Community Anchor Institutions (CAIs) are connected to the network. Sixty (of 62) building surveys have been completed and entrance construction has been completed on 43 sites. KINBER received approval on a final Environmental assessment that allows project coordination in Western Pennsylvania with another BTOP awardee, Zito Media LLC. KINBER has completed the staging and burn-in activities for PennREN network equipment and has completed network equipment installations at six (6) of the twenty-three (23) planned locations to house equipment. KINBER staff have initiated negotiations for external network connectivity providers to deliver services to PennREN including Internet2, Internet, and MPLS based VPN services. We have also engaged and started integration planning and startup activities for network operations center services with outsourced provider (GRNOC - Global Research Network Operations Center). Staff have also initiated network IP and Autonomous System Number requests with ARIN for integration with external networks and providers. KINBER staff submitted a satisfactory response to a request for a Performance Improvement Plan (PIP) by the NTIA. KINBER continues to have discussions with last mile providers to satisfy its open access requirement. | 787 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | This exceeds the baseline plan of 237 miles complete. | n/a for this project. | n/a for this project. | n/a for this project. | This exceeds the baseline plan of 237 miles complete. | n/a for this project. | n/a for this project. | None at this time. | 0 | 3 | 0 | None at this time. | Service offering and pricing models are still under review by the KINBER Board of Directors. | n/a | 0 | 0 | 0 | 0 | Network services are not yet being offered. | Network services are not yet being offered. | Network services are not yet being offered. | 100 M to 10 G | 39 | 3 | 36 | 0 | Although 39 CAIs have been connected to the network, no services are currently being offered. | Although 39 CAIs have been connected to the network, no services are currently being offered. | Although 39 CAIs have been connected to the network, no services are currently being offered. | No services are currently being offered. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | n/a. KINBER will not be providing services to businesses. | None at this time. | FALSE | n/a. No changes. | In 2012 Q2, KINBER will continue equipment installations at designated locations per the project schedule and begin segment testing on select network segments to prepare for segment turnover activities. We will have over 1,000 miles of fiber completed and at least 43 community anchor institutions connected to the network. All equipment will be procured. Equipment will be staged and delivered to ten (10) of the twenty-three (23) sites requiring equipment. At least one segment will be lit and tested. KINBER will finalize its 2013 operating budget and service offering catalog as well as develop pricing models. KINBER will continue the search to hire two additional network engineers and advertise other positions in sales and administration. These job titles and responsibilities are yet to be determined. No federal grant funds will be used for any of these postions. The KINBER staff and board will continue to build the organizationâ€™s visibility through public meetings, a marketing campaign and creating a framework for handling sales and service inquiries. Additionally, KINBER's website will become more robust with content and information. KINBER will be hosting the first annual Member Meeting, which is open to the public, in April. The member meeting is envisioned as an opportunity for public officials, anchor institution representatives, and the public to learn more about KINBER and what the PennREN network will be offering. It will also be a place for people to collaborate on projects and technology solutions for their institutions. The KINBER Board and staff will be holding a "Town Hall" session to share their vision for the future of KINBER and answer questions from attendees. Negotiations with last mile providers will continue as will discussions about an IRU of KINBER fiber to meet the NTIA open access requirements. | Keystone Initiative For Network Based Education and Research | There were some minor delays in getting answers to issues that were raised in the past two quarters such as Davis Bacon wage rates and the necessity of an on-site archeologist for construction work that was being done on ground that had been previously dug or disturbed with no prior discovery. BTOP program staff assisted in the resolution of both issues. | Although we do not anticipate any new challenges in 2012, Q2 we continue to wait for make ready and right of way permits and this could result in delays. We have some segments that can not be completed and tested due to small portions of the network that have not yet received all of the necessary approvals. Specifically, there is an Amtrak crossing in Paradise, Pa. (Segment C) that we have been waiting over a year for approvals on the permits that were filed in 2011. These delays could force much of the segment testing into the last few months of the grant award period.
NT10BIX5570026 | 2012 | Q2 | Q2 - 2012 | At the end of Q2, 2012 KINBER reports 1,001 miles of fiber completed and thirty-nine (39) community anchor institutions (CAIS) connected to the network. Building entrance construction and cabinet delivery at CAIs is complete at 59 sites (95%). â€¢ KINBER has completed the network equipment installations at fourteen (14) of the twenty-three (23) planned locations to house equipment. â€¢ KINBER has completed the installation of commodity Internet connectivity at one of our two major routing nodes and obtained Internet Protocol (IP) and Autonomous System Numbers (ASN) to allow us to exchange BGP information with upstream providers. â€¢ KINBER has also completed the installation of Research & Education ( R&E) connectivity for exchange of Internet2 routes. â€¢ KINBER continues to build out the Multiprotocol Label Switching (MPLS) based Virtual Private Networks (VPN)services to use of out-of-band management and connectivity for remote management. â€¢ KINBER has completed the turn-up of its management database and related systems for monitoring and management of the PennREN network. Segment B nodes are integrated into the systems with alerts, alarms, and SNMP management operating as expected. â€¢ The integration of network performance management tools and servers into the Service nodes on Segment B have been completed. Performance information is being generated and pulled into the various reporting platforms. â€¢ KINBER demonstrated Virtual Private Lan Service (VPLS)-based services and connectivity in support of the KINBER member meeting in April. This was PennREN's first "client" connecting Lehigh University to Montgomery County Community College for demonstration purposes â€¢ Segment B has been lit and tested and will shortly go into a Day 1 production status. â€¢ KINBER continues to work with last mile providers to establish a last mile services strategy that includes the implementation of Network to Network Interfaces (NNI) as a way to connect off-net customers to PennREN. â€¢ KINBER has developed the technology solutions for providing last mile services to PennREN ON-NET customers who wish to be early adopters and get connected as soon as possible. â€¢ KINBER continues to use a milestone based work-breakdown structure to manage field and engineering activities. KINBER's partners are working together collaboratively with online tools and services to manage the work efforts. â€¢ KINBER continues to manage risk by use of disciplined project management, effective communication among team members and other best practices. Site readiness is being managed directly by KINBER Operations team members. No significant personnel or partner turnover has occurred in the last quarter. â€¢ KINBER and its partners continue to manage risk with equipment failures and engineering mistakes by paying close attention to detailed configuration checklists, design documents, and architectural documents. KINBER has included specific unit testing, system testing in its segment turnover activities milestones. Hardware failures have been minimal and well within expected norms. â€¢ No significant problems with fiber construction, splicing, or other outside plant work have occurred to affect the schedule. â€¢ KINBER has developed its service catalog, product data sheets and other materials to use in working with members on the use of PennREN. â€¢ KINBER has added a network engineer to its staff. | 1001 | 0 | 0 | 0 | 1001 | 0 | 0 | 0 | This exceeds the baseline estimate of 813 miles. | n/a for this project | n/a for this project | n/a for this project | This exceeds the baseline estimate of 813 miles. | n/a for this project | n/a for this project | None at this time | 0 | 3 | 0 | None at this time. | PennREN Proposed On-net Network Service Prices for KINBER members, FY2013. â€¢ Dark Fiber â€” $700 per strand mile per year â€¢ 1G Ethernet Port Connection â€” $1,650 â€¢ 10G Ethernet Port Connection â€” $5,000 â€¢ 100M Ethernet Point-to-Point â€” $2,000 â€¢ 1G Ethernet Point-to-Point â€” $5,000 â€¢ 10G Ethernet Point-to-Point â€” $15,000 â€¢ 10G Lambda Point-to-Point â€” $15,000 â€¢ Commodity Internet - $5 per Mbps | n/a | 0 | 0 | 0 | 0 | Network services are not yet being offered. | Network services are not yet being offered. | Network services are not yet being offered. | 100 M to 10 G | 39 | 3 | 36 | 0 | Although 39 CAIs have been connected to the network, no services are currently being offered. | Although 39 CAIs have been connected to the network, no services are currently being offered. | Although 39 CAIs have been connected to the network, no services are currently being offered. | No service is currently being offered. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | n/a. KINBER will not be offering last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER will not be offering last mile or service to businesses. | n/a. KINBER will not be offering last mile or service to businesses. | n/a. KINBER will not be offering last mile or service to businesses. | n/a. KINBER will not be offering last mile or service to businesses. | n/a. KINBER will not be offering last mile or service to businesses. | None at this time. | FALSE | N/a. There have been no changes. | â€¢ KINBER plans to have 1350 fiber miles complete and 57 CAIs connected to the network. KINBER will complete the installation of equipment in all twenty-three (23) nodes by the end of September 2012. Slips to this schedule will not significantly affect the project. â€¢ KINBER plans to complete testing and turn-up of four segments in Q3. Once equipment installations and outside plant construction is completed, resources will be focused on accelerating the turn up of segments into Day 1 production status. â€¢ KINBER expects to complete additional commodity Internet and R&E services out of its second major routing node in during this quarter. â€¢ KINBER expects to complete its forms for network services agreements that include terms, conditions, and other information about services in this quarter. KINBER will begin its annual audit process and also hire additional staff. | Keystone Initiative For Network Based Education and Research | Waiting for rights of way, construction permits and other approvals has slowed the construction progress of the project and impacted the payment and use of federal funds. There are a number of segments on the network that are mostly complete but waiting on a small section (such as a train or bridge crossing) approval to actually complete and fully test the fiber and equipment for that segment. | We continue to work with local utility companies to get approvals and make ready work completed although this has slowed some segments of the project down. We are working diligently to correct any delays this might have on the project completion timeline.
NT10BIX5570026 | 2012 | Q3 | Q3 - 2012 | â— KINBER reports having 1,284 miles of fiber complete and 61 CAIS connected. KINBER has completed the network equipment installations at twenty two (22) of the twenty-three (23) planned locations to house equipment. The final site will be installed on Oct 17, 2012. â— KINBER has promoted Segment B into production status. Four additional Segments (C, F, G and H) are lit, turned up with integration teams working on Day 0 (testing) activities. â— KINBER has completed the installation of commodity Internet and at both of our major routing nodes. â— KINBER has also completed the installation of R&E connectivity for exchange of Internet2 routes and established physical connectivity with in Pittsburgh. â— KINBER continues to build out the MPLS based VPN services from Earthlink to use of out-of-band management and connectivity for remote management. â— KINBER continues to bring online the various systems and web-based tools provided by the GRNOC to manage the operations of PennREN. This includes a portal page from which members can access various information tools such as online calendars, service request and trouble ticketing, performance reports, the real time ATLAS tool and others. â— KINBER is using the Footprints trouble-ticketing system for all problems, change management, and customer provisioning activities. â— GRNOC service desk technicians and 2nd and 3rd tier support teams have been involved in segment turnup and trained on PennREN hardware and systems. â— GRNOC has completed the integration of network performance management tools and servers into the Service nodes on Segment B, C, F, G, H. Performance information is being generated and pulled into the various GRNOC reporting platforms. â— KINBER has delivered new service to one customer and is in the process of completing service provisioning for two others to be completed in October 2012. â— KINBER continues to work with last mile providers to establish a last mile services strategy that includes the implementation of Network to Network Interfaces (NNI) as a way to connect off-net customers to PennREN. â— KINBER has developed the technology solutions for providing last mile services to PennREN ON-NET customers who wish to be early adopters and get connected as soon as possible. â— KINBER continues to use a milestone based work-breakdown structure to manage field and engineering activities. KINBER's partners are working together collaboratively with online tools and services to manage the work efforts. â— KINBER continues to manage risk by use of disciplined project management, effective communication among team members and other best practices. Site readiness is being managed directly by KINBER Operations team members. â— KINBER and its partners continue to manage risk with equipment failures and engineering mistakes by paying close attention to detailed configuration checklists, design documents, and architectural documents. â— KINBER has included specific unit testing, system testing in its segment turnover activities milestones. Hardware failures have been minimal and well within expected norms. â— KINBER has developed its service catalog, product data sheets and other materials to use in working with members on the use of PennREN. â— KINBER has completed its customer forms for master services agreements, PennREN services agreements and service orders to be used for customer wishing to subscribe to services. KINBER held another successful "Community Day" outreach event at Lehigh University in Bethlehem, PA and is planning its second annual members meeting for May 2013, in Pittsburgh. KINBER moved and expanded its corporate offices to State College, PA and hired an additional network engineer . A Member Relations Manager as well as a Director of External Relations have been hired to increase outreach activities, attract customers, and ensure sustainability. | 1284 | 0 | 0 | 0 | 1284 | 0 | 0 | 61 | Project is slightly behind due to delayed permitting but will catch up in Q4. | n/a for this project | n/a for this project | n/a for this project | Project is slightly behind due to delayed permitting but wil catch up in Q4. | n/a for this project | n/a for this project | Project is ahead of schedule. | 2 | 3 | 44 | Sunesys, LLC and One Source Networks (OSN) | Both Sunesys, LLC and OSN will provide last mile capability or access to additional, offnet fiber. These services will be coordinated with KINBER and customized to the individual institution's needs. Proposed FY2013 prices for on-net network services for member: Dark Fiber - $700 per strand mile/year 1G Ethernet Port $1,650 10G Ethernet Port $5,000 100M Ethernet Point-to-Point $2,000 1G ethernet Point-to-Point $5,000 10G Ethernet Point-to-Point $15,000 10G lambda Point-to-Point $15,000 Commodity Internet $3 per Mbps | n/a. KINBER is operating the network. | 1 | 0 | 0 | 0 | Sunesys is a last mile provider who will also be fulfilling KINBER's open access commitment across the network footprint. | Services are not yet being offered. | Services are not yet being offered. | 100M to 10G | 61 | 3 | 58 | 0 | 61 CAIs have been connected to the network, and one is KINBER's first customer. Services are not yet fully available in many parts of the network | Three locations have new access through the PennREN network. | Of the 58 CAIs connected to the network, there is one current subscriber. This is simply the lag in time for the network to be completed and services being offered as of the end of Q3 2012. | 100M to 10G will be offered | 0 | 0 | 0 | 0 | 0 | n/a. KINBER is not offering last mile or residential services. | n/a. KINBER is not offering last mile or residential services. | n/a. KINBER is not offering last mile or residential services. | n/a. KINBER is not offering last mile or residential services. | n/a. KINBER is not offering last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER is not offering last mile or services to businesses. | n/a. KINBER is not offering last mile or services to businesses. | n/a. KINBER is not offering last mile or services to businesses. | n/a. KINBER is not offering last mile or services to businesses. | n/a. KINBER is not offering last mile or services to businesses. | None at this time. | FALSE | n/a | KINBER will have over 1500 miles of fiber complete (93%) and all 63 CAIs connected. All equipment will be deployed and over 50% of the network will be tested and in full production status. KINBER plans to complete the installation of equipment in all twenty-three (23) nodes by the end of September 2012. Slips to this schedule will not significantly affect the project. KINBER plans to complete testing and turn-up of four segments in Q4.. Once equipment installations and outside plant construction is completed, resources will be focused on accelerating the turn up of segments into Day 1 production status. KINBER expects to complete additional commodity Internet and R&E services out of its second major routing node in during this quarter. KINBER expects to complete its forms for network services agreements that include terms, conditions, and other information about services in this quarter. The annual financial audit will be reviewed and accepted by the Board of Directors and filed with the Federal Clearinghouse. KINBER will submit documentation to fulfill the required Federal Government Security Interest in the asset. | Keystone Initiative For Network Based Education and Research | There are still a small number of ROW and permits that have not been approved which delays completing full segments. KINBER also experienced some downed fiber from storms and also a "limb trimming" incident. All of this damage has been corrected. | Weather related challenges are the most obvious and unpredictable obstacles that KINBER will face in Q4 2012.
NT10BIX5570026 | 2012 | Q4 | Q4 - 2012 | As of the end of Q4 2012, KINBER reports 1,437 miles of fiber complete and 62 CAIs connected to the network Additionally, â— KINBER has completed the network equipment installations at all twenty-three (23) of the twenty-three (23) planned locations to house equipment. â— KINBER has promoted ten (10) of the fifteen (15) network segments into production status (Day 1). Segments A, I, J, K, O are currently being worked on by fiber construction teams with various spans and locations on these segments in Day 0 (testing activities) underway. â— KINBER has completed the designs and implementation of the final management network architecture for out-of-band management of all node locations. â— KINBER and its Network Operations Center continues to develop and customize the various reporting and management tools for operations of PennREN. These include a portal pages from which members can access various information tools such as online calendars, service request and trouble ticketing, performance reports, and real-time performance management tools. â— KINBER continues to develop and use the Footprints trouble-ticketing system for all problems, change management, and customer provisioning activities. KINBER has developed and integrated business processes including fiber maintenance, fiber IRU requests, and incident management procedures for interfacing with the field maintenance teams. â— The Network Operation Center has completed the integration of network performance management tools and servers into the Service nodes on all segments in production status. Performance information is being generated and pulled into various reporting platforms. â— KINBER has delivered new service to four customers utilizing the PennREN network. â— KINBER continues to work with last mile providers to establish a last mile services strategy that includes the implementation of Network to Network Interfaces (NNI) as a way to connect off-net customers to PennREN. â— KINBER has developed the technology solutions for providing last mile services to PennREN ON-NET customers who wish to be early adopters and get connected as soon as possible. â— KINBER continues to use a milestone based work-breakdown structure to manage field and engineering activities. KINBER's partners are working together collaboratively with online tools and services to manage the work efforts and ensure the project is completed in a timely manner. â— KINBER continues to manage risk by use of disciplined project management, effective communication among team members and other best practices. Site readiness is being managed directly by KINBER Operations team members. â— KINBER and its partners continue to manage risk with equipment failures and engineering issues. â— KINBER has included specific unit testing, system testing in its segment turnover activities milestones. Hardware failures have been minimal and well within expected norms. â— KINBER continues to develop its service catalog, product data sheets and other materials to use in working with members on the use of PennREN. KINBER continues to interact with the community and politiial leadership across the commonwealth to get the message out about the impact KINBER and PennREN will have. | 1437 | 0 | 0 | 0 | 1437 | 0 | 0 | 62 | Approximately 89% of the fiber was completed by the end of Q4 2012. Project is slightly behind due to weather related delays but all fiber should be completed in Q1 2013. | n/a for this project | n/a for this project | n/a for this project | Approximately 89% of the fiber was completed by the end of Q4 2012. Project is slightly behind due to weather related delays but all fiber should be completed in Q1 2013. | n/a for this project | n/a for this project | Project is on schedule. | 3 | 2 | 44 | Sunesys, LLC, One Source Networks and Windstream | The three signed agreements are in place to provide last mile solutions and access to offnet members. These services will be coordinated with KINBER staff and customized to the individual institution's needs. Proposed FY2013 prices for on-net services to members : Dark Fiber $700 per strand mile 1G Ethernet Port $1650 10G Ethernet Port $5,000 100M Ethernet Port $2,000 1G Ethernet Point-to-point $5,000 10G Ethernet Point -to-point $15,000 10G Lambda point-to-point $15,000 Commodity Internet $3 per Mbps | n/a KINBER is operating the network. | 2 | 0 | 1 | 0 | Three last mile providers have entered into contracts with KINBER. | We are unaware if the providers' service was improved. | One last mile provider has entered into an IRU with KINBER for dark fiber. | 100M to 10G | 62 | 3 | 59 | 0 | 62 CAIs are connected to the network. | To date, three locations have received new access through the PennREN network. | There are 59 CAIs connected to the network who will receive improved access. | 100M to 10G | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | None at this time. | FALSE | n/a | Superstorm Sandy caused delays in the construction of the outside fiber plant have impacted our schedule and not allowed us to complete the segments as originally planned in Q4 2012. KINBER anticipates having all 1613 miles of fiber hung and all 62 CAIs connected. KINBER expects to have 5 Last Mile provider agreements signed. â€¢ A detailed installation plan has been created for promoting these segments into production status (Day 1) in Q1 2013. â€¢ KINBER plans to complete the turn up and promotion to production status of the remaining segments (listed above) by the end of February 2013. â€¢ KINBER will be completing its plans for quality of service features to utilize in the PennREN network. â€¢ All fiber installation will be completed in Q1 2013 and network testing will continue. â€¢ KINBER anticipates signing new customers throughout the quarter. | Keystone Initiative For Network Based Education and Research | KINBER was heavily impacted by Superstorm Sandy in October and November 2012. Not only was part of the network damaged by the storm, but make-ready and splicing crews that were out in the field were re-deployed to other states to assist in the emergency repairs of poles, wires,and fiber due to the storm's impact. KINBER received an official Notice of Schedule Impact of 60 days from its construction vendor but hopes to be able to get all fiber strung on the coming months. There is also one bridge crossing (Segment A to the North of Bethlehem) that has been problematic in getting ROW permitting because it crosses over a railyard. | Weather related delays may be a factor in completing the fiber build in Q1 2013. No other challenges are anticipated.
NT10BIX5570026 | 2013 | Q1 | Q1 - 2013 | Construction of the network was completed. 1,612 mile of fiber we completed with 62 CAIS connected to the network. All 15 segments of the network are lit and passing traffic. | 1612 | 0 | 0 | 0 | 1612 | 0 | 0 | 62 | Construction is complete on the network. | n/a for this project. | n/a for this project. | n/a for this project. | Construction is complete on the network. | n/a for this project. | n/a for this project. | Construction is complete on the network. | 5 | 0 | 20 | Sunesys, Windstream, One Source Networks, Velocity Networks, and PenTeledata | KINBER is not providing wholesale services. Instead, KINBER has entered into agreements with last mile providers to provide solutions and access to offnet members. These services will be coordinated with KINBER staff and customized to each individual need. | n/a KINBER will operate the network. | 5 | 0 | 1 | 0 | Five last mile providers have entered into contracts with KINBER. | We are unaware if any of the partnering providers' service has been improved. | One last mile provider has entered into an IRU for dark fiber. | 100M to 10G | 62 | 4 | 58 | 0 | 62 CAIs are connected to the network | To date, four locations have received new access from KINBER's network. | The remaining 59 CAIS connected to the network will receive improved access. | 100M to 10G | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | n/a KINBER is not offering last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | n/a KINBER is not offering last mile or services to businesses. | None at this time. | FALSE | n/a No changes have occurred. | Completion of final network documentation. We plan on beginning the closeout period in the next quarter and documenting the Federal Government's security interest in the network. we will also be hosting a 2-day Annual Meeting to provide educational and networking opportunities to our members and potential customers in Pittsburgh ( June 26 & 27). NTIA staff and Officials have been invited to attend and speak. In the next quarter, KINBER will continue to market the network and expand service offerings to members and Participants. | Keystone Initiative For Network Based Education and Research | No issues to report. | No challenges are anticipated.
NT10BIX5570026 | 2013 | Q2 | Q2 - 2013 | Construction of the network is complete. 1,612 miles of fiber were completed with 59 CAIs connected to the network. All 15 segments of the network are lit, tested, and passing traffic. There are also three (3) co-location/carrier hotels connected to the network. KINBER held its annual 2-day Member Meeting in Pittsburgh, Pa. and celebrated the completion of the project. There were almost 200 people in attendance who participated in over 30 educational sessions. Tony Wilhelm (NTIA) was a keynote speaker. KINBER received a lot of positive press after the event. KINBER has applied for a SPIN number from the FCC to be able to provide services at discounted rates to schools and libraries. KINBER â€˜s build of the PennREN network has facilitated public-private partnerships, created construction and engineering jobs with new fiber builds and has brought seemingly divergent groups of people together to discuss and work collectively to bring broadband to more locations throughout Pennsylvania. All of this is being accomplished while rates are dropping and broadband access, speed and accessibility are increasing throughout Pennsylvania. KINBER has seen the â€œCommunity Solutionâ€ in effect, where small rural counties band together to collectively work on building last mile connections throughout their community to gain access to PennREN. Usually there is a CAI connected to PennREN that works with KINBER staff to facilitate a partnership between Higher Education, K-12 schools, nonprofit organizations, libraries, charitable foundations, hospitals and local government in the community. These community groups effeclty reduce their costs through economies of scale purchasing power and coordinating a one-build, across the board solution. Rural economic development groups are in negotiations to connect business parks that will recruit, grow and retain businesses in their local economies and we believe that the availability of PennREN will eventually aid in reducing costs to government broadband subscribers and increasing public safety activities throughout the Commonwealth either directly through KINBER facilitated services or in a Public-private partnership. KINBERâ€™s open access requirement has allowed for numerous fiber splice points along the backbone, facilitating many new connections for data transfer, backhaul and commerce. Additionally, the PennREN network has spawned a lot of interest in providers of â€œabove the net servicesâ€ (disaster recovery, co-location, data storage and archiving, and group purchasing) of interest to the CAIs on PennREN. KINBER will enable the connection of Pennsylvaniaâ€™s research community to Internet2, as well as national and international partners. In the future, we envision the PennREN network will only expand its presence and impact on Pennsylvania | 1612 | 0 | 0 | 0 | 1612 | 0 | 0 | 62 | Construction of the network is complete. | n/a for this project. | n/a for this project. | n/a for this project. | Construction of the network is complete. | n/a for this project. | n/a for this project. | Construction of the network is complete. | 5 | 0 | 20 | Sunesys, Windstream, One Source Networks, Velocity Networks, PenTeleData | KINBER is not providing wholesale services. Instead, KINBER has entered into agreements with last mile providers to provide solutions and access to offnet members and users. The provision of these services will be coordinated with KINBER staff. | n/a. KINBER will operate the network. | 4 | 0 | 1 | 0 | Five last mile providers have entered into contracts with KINBER, one for dark fiber. | We are unaware of provider's service improvements. | One last mile provider has entered into an IRU for dark fiber. | 100M to 10G, as of 06/30/2013 there were no services delivered | 59 | 0 | 59 | 7 | 59 CAIs are connected to the network. There are also three (3) co-location/carrier hotels connected to the network. | None of the current subscribers are new. | 59 CAIs are connected to the network and in various negotiations for service delivery. 7 CAIs are currently receiving services. There are also three (3) co-location/carrier hotels connected to the network. | Speed tiers are 100M to 10G. As of 06/30/2013 we had six 1G subscribers and one 10G subscriber. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER does not offer last mile or residential services. | n/a. KINBER does not offer last mile or residential services. | n/a. KINBER does not offer last mile or residential services. | n/a. KINBER does not offer last mile or residential services. | n/a. KINBER does not offer last mile or residential services. | 0 | 0 | 0 | 0 | 0 | n/a. KINBER does not offer last mile or services to businesses. | n/a. KINBER does not offer last mile or services to businesses. | n/a. KINBER does not offer last mile or services to businesses. | n/a. KINBER does not offer last mile or services to businesses. | n/a. KINBER does not offer last mile or services to businesses. | None at this time. | FALSE | No changes. | n/a Project is complete. KINBER has started Closeout procedures. | Keystone Initiative For Network Based Education and Research | No issues to report. | Project is complete. No challenges are anticipated.
NT10BIX5570027 | 2010 | Q3 | Q3 - 2010 | The environmental assessment was completed and the FONSI was issued by NTIA. Construction plans and specifications have been completed along with tabulations and staking sheets. Central office verification was completed in Roswell and Tucumcari. An RFP for outside plant construction was sent to contractors. Finalized the design of the DWDM network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No new progress. | No new progress. | No new progress. | No new progress. | No new progress. | N/A | N/A | No new progress. | 3 | 0 | 3 | SuddenLink, CableOne and US Cable | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnect point to Interconnect point; Local Access Services which are typically Ethernet services from the local Interconnect point to the anchor institution. | N/A | 0 | 0 | 0 | 0 | ENMR-Plateau currently has agreements with several broadband wholesalers on the current network and intend to transfer those services onto the new network once completed. ENMR-Plateau also intends to sell additional services to these current customers as well as other customers who would be considered broadband wholesalers. | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | No new progress. | No new progress. | No new progress. | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The RFP responses for the outside plant construction were received. The construction contract will be awarded this quarter based on the company's procurement policy. The construction permits are expected to be obtained. The RFP's for the DWDM and access equipment are expected to be sent out this quarter. The DWDM vendor selection is expected to be complete. | E.N.M.R. Telephone Cooperative | When the Baseline Report and project schedule were originally created we assumed a total of six months to complete the Environmental Assessment and receive the FONSI. We submitted the draft EA prior to the August 1st deadline, however the FONSI was not issued until September 30th. This has negatively affected our project schedule by approximately two months, due to NTIA's requirements of not being able to expense grant funds or begin construction until the issuance of the FONSI. | Originally the Baseline Report was created on the assumption that Year 1, Quarter 1 began on the project start date, which for ENMR-Plateau is February 1, 2010. Since it has been approved by NTIA we have determined that the Baseline Report should have been created based on calendar quarters, which would have began for ENMR-Plateau on January 1, 2010. Because of the confusion on this issue we are approximately one month behind schedule when compared to the Baseline Report. Additionally when we were creating the Baseline Report we assumed that the environmental assessment would take a total of six months to finalize and approve; the draft environmental assessment was due to NTIA by August 1st which was also taken into account when creating the Baseline Report. In actuality, even though the draft environmental assessment was submitted to NTIA before the August 1st deadline, the entire environmental process took an additional two extra months to complete. The FONSI was signed and issued on September 30th, and due to the fact that grant funds cannot be committed and construction permits cannot be requested prior to the issuance of the FONSI, this has also affected our project schedule by two additional months. Therefore, taking into account these two issues we feel that there is a difference of approximately one quarter, or three months, between the Baseline Report and the actual project schedule.
NT10BIX5570027 | 2010 | Q4 | Q4 - 2010 | The outside plant construction contract was awarded. Construction began January 21st in two of the five markets. Equipment RFP's for the DWDM and Layer 2/3 equipment have been sent out to various vendors. Responses will be received next quarter and vendor selection will be in process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 0 | 12 | SuddenLink, CableOne and US Cable | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Service which are typically Ethernet services from the local Interconnection point to the anchor institution. | N/A | 0 | 0 | 0 | 0 | ENMR-Plateau currently has agreements with several broadband wholesalers on the current network and intend to transfer those services onto the new network once completed. ENMR-Plateau also intends to sell additional services to these current customers as well as other customers who would be considered broadband wholesalers. | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Construction of the outside plant network began on January 21st in two of the five markets. DWDM and Layer 2/3 equipment vendor selection will be complete and procurement will begin by the end of the quarter. | E.N.M.R. Telephone Cooperative | As stated in the prior quarter's reporting documentation the major issue with not meeting the projected milestones for this reporting period is due to the additional time that was taken to complete the Environmental Assessment and receive the FONSI. The draft Environmental Assessment was submitted prior to the deadline given in the special award conditions, however the FONSI wasn't received until approximately 60 days later. This has ultimately created a domino affect that has pushed back our schedule and delayed the completion of the milestones reflected in the Baseline Report. Additionally ENMR-Plateau has been diligently working to remain in compliance with all DOC/NTIA requirements, however our limited experience with Federal procurement causes us to have to seek council from NTIA at times to obtain further guidance. Receiving answers to specific questions takes longer than anticipated causing the project to be delayed. Finally the in depth analysis that is being conducted related to equipment vendor selection has added to the schedule delays. Overall ENMR-Plateau is optimistic that we will be able to catch up to our projected milestone progress reflected in our Baseline Report. | ENMR-Plateau will be working to catch up to projected milestones reflected in the Baseline Report related to equipment procurement and deployment. The DWDM and Layer 2/3 Equipment vendor selection is expected to be complete by the end of the quarter with procurement of the equipment to follow. Construction on the outside plant network began on January 21st and is progressing on schedule at this point.
NT10BIX5570027 | 2011 | Q1 | Q1 - 2011 | Construction is progressing on schedule. Two of the three equipment vendors have been selected and awarded. Anchor institutions are being contacted on an individual basis. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 0 | 12 | SuddenLink, CableOne and US Cable | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution. | N/A | 0 | 0 | 0 | 0 | ENMR-Plateau currently has agreements with several broadband wholesalers on the current network and intend to transfer those services onto the new network once completed. ENMR-Plateau also intends to sell additional services to these current customers as well as other customers who would be considered broadband wholesalers. | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Begin procurement and deployment of DWDM network equipment. Begin construction of CO buildings. Continue progressing with construction and contacting anchor institutions. | E.N.M.R. Telephone Cooperative | ENMR-Plateau has been diligently working to catch up to projected milestones reflected in the Baseline Report related to equipment procurement and deployment and site preparation. We are optimistic that we will be able to catch up to the projected milestones reflected in the Baseline Report. | ENMR-Plateau has been diligently working to catch up to projected milestones reflected in the Baseline Report related to equipment procurement and deployment and site preparation. At this point all equipment vendors have been selected, with one contract being finalized and executed and the other two expected to be completed this quarter. As of now construction is progressing on schedule. We are optimistic that we will be able to catch up to the projected milestones reflected in the Baseline Report. The estimated construction expense for next quarter is based on actual invoices obtained for March, April and estimated amount for May. Since invoices for each month are received and paid in the following month reporting for these expenses will always be one month behind.
NT10BIX5570027 | 2011 | Q2 | Q2 - 2011 | Construction is progressing on schedule. Equipment procurement and deployment is under way and is proceeding very quickly. Anchor institutions are continuing to be contacted. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 0 | 12 | SuddenLink, CableOne, US Cable | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution. | N/A | 0 | 0 | 0 | 0 | ENMR-Plateau currently has agreements with several broadband wholesalers on the current network and intend to transfer those services onto the new network once completed. ENMR-Plateau also intends to sell additional services to these current customers as well as other customers who would be considered broadband wholesalers. | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue procurement and deployment of DWDM, Layer 2/3 and Access network equipment. Begin construction on CO buildings. Continue outside plant construction and contacting anchor institutions. Anticipate having approximately 63 miles of construction completed by 9/30. At this time do not anticipate being able to turn up anchor institutions by 9/30 due to scheduling of access equipment installation; expecting to be able to begin providing service to anchor institutions some time during quarter 4. | E.N.M.R. Telephone Cooperative | ENMR-Plateau has been diligently working to catch up to projected milestones reflected in the Baseline Report related to equipment procurement and deployment and site preparation. At this point all equipment vendors have been selected, and all contracts have been executed. As of now construction is progressing on schedule. We are optimistic that we will be able to catch up to the projected milestones reflected in the Baseline Report. | ENMR-Plateau has been diligently working to catch up to projected milestones reflected in the Baseline Report related to equipment procurement and deployment and site preparation. At this point all equipment vendors have been selected and all contracts have been executed. As of now construction is progressing on schedule and equipment procurement and deployment are proceeding very quickly. We are optimistic that we will be able to catch up to the projected milestones reflected in the Baseline Report.
NT10BIX5570027 | 2011 | Q3 | Q3 - 2011 | Mainline fiber construction has been completed in three of the five funded service areas. Equipment procurement and installation is proceeding quickly. Anchor institutions are continuing to be contacted. Overall at this point the project is on schedule to reach target of at least 66% complete by the end of year 2. | 68 | 528 | 1268 | 0 | 1864 | 0 | 0 | 17 | Ahead of baseline estimates for construction deployment. | No variance. | Not reflected as a separate line item in baseline. No variance. | N/A | No variance. | N/A | N/A | Waiting on buildings at two locations and power equipment upgrades for the other. All interconnection points expected to be completed in Q1 2012. | 3 | 0 | 12 | SuddenLink, CableOne, US Cable | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution. | N/A | 0 | 0 | 0 | 0 | ENMR-Plateau currently has agreements with several broadband wholesalers on the current network and intend to transfer those services onto the new network once completed. ENMR-Plateau also intends to sell additional services to these current customers as well as other customers who would be considered broadband wholesalers. | N/A | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continuing outside plant construction and equipment procurement/deployment. Expected to complete all outside plant construction by the end of Q4 2011; total of 85 miles. Total of 528 network miles have been leased; no additional leased network miles. Expecting to connect approximately 24 CAI locations by the end of Q4 2011. Expecting to sign 1 new agreement with a broadband wholesaler or last mile provider. | E.N.M.R. Telephone Cooperative | Delays at the beginning of the project have affected ENMR's ability to reach milestone objectives. As of 9/30/11 the total project dollars spent equates to 56%, at approximately 55% of the award period, compared to baseline estimates of 58%. Based on recent productivity we are expected to surpass the targeted 66% completion by the end of award year 2. | No potential challenges or issues known. At this point construction and equipment deployment are progressing quickly and we've been able to catch up to the projected planned percentage of project completion. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Reporting Period" below includes $370,991 of ENMR Telephone Cooperative, Inc.'s in-kind matching requirement.
NT10BIX5570027 | 2011 | Q4 | Q4 - 2011 | Outside plant fiber construction is continuing and expected to be fully complete by the end of Q1 2012. Equipment procurement and installation is also proceeding ahead of schedule. Anchor institutions are continuing to be contacted. A total of 23 CAI locations have been connected to the BTOP funded network and are receiving broadband services from ENMR-Plateau as of 12/29. | 79 | 528 | 1268 | 0 | 1875 | 0 | 0 | 17 | Positive variance. | No variance. | Not reflected as a separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | Waiting on the completion of buildings at two locations and power equipment upgrades for the others. All interconnection points expected to be completed in Q1 2012. | 10 | 0 | 12 | Windstream, TLSN, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Delcom, Five Area Systems, Yucca Telecommunications, Penasco Valley Telecom | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 2 | 8 | 0 | 13 | There are 2 providers currently receiving new access to ENMR-Plateau's core middle mile network. | There are 8 providers currently receiving improved access to ENMR-Plateau's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 100Mb - 5, 200Mb - 2, 1Gb - 1, 2.5Gb - 1, 10Gb - 2 | 23 | 19 | 4 | 23 | Activated 23 CAI (Schools K-12) locations on 12/29/11. | 19 of the 23 CAI locations are receiving new access. | 4 of the 23 CAI locations are receiving improved broadband access. | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 23 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of outside plant fiber construction in all markets; approximately 90 total miles. Completion of buildings construction in all locations. Continue procurement and installation of networking equipment. Continue to contact anchor institutions to sign up for service. Total of 528 network miles have been leased; no additional leased network miles. Anticipating to connect 70 total CAI locations by the end of Q1 2012. Anticipating to sign 1 new agreement with a broadband wholesaler or last mile provider. | E.N.M.R. Telephone Cooperative | Delays at the beginning of the project have affected ENMR-Plateau's ability to reach milestone projections. As of 12/31/2011 the total project dollars spent equates to 79%, at approximately 64% of the award period, compared to 67% of baseline estimates. ENMR-Plateau has exceeded the 67% required completion by the end of award year 2. | No potential challenges or issues known at this time. Construction and equipment deployment are progressing quickly and ENMR-Plateau has been able to catch up to projected milestones reflected in the baseline report. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative, Inc.'s in-kind matching requirement.
NT10BIX5570027 | 2012 | Q1 | Q1 - 2012 | Outside fiber construction was nearly complete by the end of Q1 2012, and was completed in April. Equipment procurement and installation is proceeding ahead of schedule and expected to be complete in Q2 2012. Anchor institutions are continuing to be contacted and community outreach is continuing to be conducted. | 89 | 528 | 1268 | 0 | 1885 | 0 | 0 | 17 | Positive variance. | No variance. | Not reflected as a separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | Interconnection points expected to be complete next quarter (Q2 2012). | 11 | 0 | 12 | Windstream, TLSN, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Delcom, Five Area Systems, Yucca Telecommunications, Penasco Valley Telecom | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 2 | 8 | 0 | 13 | There are 2 providers currently receiving new access to ENMR-Plateau's core middle mile network. | There are 8 providers currently receiving improved access to ENMR-Plateau's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 100Mb - 5, 200Mb - 2, 1Gb - 1, 2.5Gb - 1, 10Gb - 2 | 182 | 178 | 4 | 24 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 1, 50Mb - 0, 100Mb - 0, 1Gb - 23 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of fiber optic facilities construction. Completion of network equipment installation. | E.N.M.R. Telephone Cooperative | None, ENMR-Plateau has been able to surpass projected milestones. | No potential challenges or issues at this time. Construction and equipment deployment are expected to be completed ahead of baseline projections. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative's in-kind matching requirement.
NT10BIX5570027 | 2012 | Q2 | Q2 - 2012 | Fiber construction complete. Splicing and acceptance testing being completed. Equipment procurement and installation is proceeding ahead of schedule and only a few items remain for Q3 2012. Anchor institutions are continuing to be contacted and community outreach is being conducted. | 91 | 528 | 1268 | 0 | 1887 | 0 | 0 | 17 | Positive variance. | No variance. | Not reflected as a separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | Interconnection points expected to be complete next quarter. Currently waiting on third party to complete splicing needed for interconnection. All equipment has been installed at this point. | 11 | 0 | 12 | Windstream, TLSN, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Inc., Delcom, Five Area Systems, Yucca Communications, Penasco Valley Telecom, Conterra Ultra Broadband | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 3 | 8 | 0 | 14 | There are 3 providers currently receiving new access to ENMR-Plateau's core middle mile network. | There are 8 providers currently receiving improved access to ENMR-Plateau's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 50Mb - 1, 100Mb - 5, 200Mb - 2, 1Gb - 1, 2.5Gb - 1, 10Gb - 2 | 223 | 219 | 4 | 33 | N/A | N/A | N/A | 1.5Mb - 1, 5Mb - 6, 10Mb - 0, 15Mb - 0, 20Mb - 2, 30Mb - 0, 40Mb - 1, 50Mb - 0, 100Mb - 0, 1Gb - 23 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalize splicing and acceptance testing. Finalize equipment procurement and deployment. | E.N.M.R. Telephone Cooperative | None, ENMR-Plateau has been able to surpass projected milestones. | No potential challenges or issues at this time. Construction and equipment deployment are expected to be completed ahead of baseline projections. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative's in-kind matching requirement.
NT10BIX5570027 | 2012 | Q3 | Q3 - 2012 | Splicing has been completed and equipment procurement and installation is proceeding ahead of schedule and should be complete Q4 2012. Anchor institutions are continuing to be contact and community outreach is being conducted. | 91 | 528 | 1268 | 0 | 1887 | 0 | 0 | 20 | Positive variance. | No variance. | Not reflected as separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | N/A | 11 | 0 | 12 | Windstream, TLSN, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Inc., Delcom, Five Area Systems, Yucca Communications, Penasco Valley Telecom, Conterra Ultra Broadband | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 3 | 8 | 0 | 14 | There are 3 providers currently receiving new access to ENMR-Plateau's core middle mile network. | There are 8 providers currently receiving improved access to ENMR-Plateau's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 50Mb - 1, 100Mb - 5, 200Mb - 2, 1Gb - 1, 2.5Gb - 1, 10Gb - 2 | 223 | 219 | 4 | 33 | N/A | N/A | N/A | 1.5Mb - 1, 5Mb - 6, 10Mb - 0, 15Mb - 0, 20Mb - 2, 30Mb - 0, 40Mb - 1, 50Mb - 0, 100Mb - 0, 1Gb - 23 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalize splicing and acceptance testing. Finalize equipment procurement and deployment. | E.N.M.R. Telephone Cooperative | None, ENMR-Plateau has been able to surpass projected milestones. | No potential challenges or issues known at this time. Construction and equipment deployment are expected to be completed ahead of baseline projections. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative's in-kind matching requirement.
NT10BIX5570027 | 2012 | Q4 | Q4 - 2012 | Construction, splicing, equipment installation and testing has been completed. All PFSA's have been activated and are able to carry traffic. Anchor institutions are being activated daily. | 91 | 528 | 1268 | 0 | 1887 | 0 | 0 | 20 | Positive variance. | No variance. | Not reflected as a separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | No variance. | 11 | 0 | 12 | Windstream, TLSN, US Cable, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Inc., Delcom, Five Area Systems, Yucca Communications, Penasco Valley Telecom, Conterra Ultra Broadband | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 3 | 8 | 0 | 14 | There are 3 providers currently receiving new access to ENMR-Plateau's core middle mile network. | There are 8 providers currently receiving improved access to ENMR-Plateau's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 50Mb - 1, 100Mb - 5, 200Mb - 2, 1Gb - 1, 2.5Gb - 1, 10Gb - 2 | 286 | 282 | 4 | 60 | N/A | N/A | N/A | 1.5Mb - 1, 3Mb - 4, 5Mb - 11, 8Mb - 7, 10Mb - 4, 15Mb - 0, 20Mb - 7, 30Mb - 0, 40Mb - 1, 50Mb - 0, 100Mb - 1, 1Gb - 23, 10Gb - 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Payment of final invoicing, begin project closeout activities. No network miles will be deployed next quarter construction is complete. No additional CAI's will be connected by the end of next quarter, all CAI's have been connected. ENMR is continuing direct communication to the CAI's in order to sign them up for service on the BTOP funded network. ENMR estimates 1 new agreement by the end of next quarter. | E.N.M.R. Telephone Cooperative | None. | No potential challenges or issues known at this time. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative's in-kind matching requirement.
NT10BIX5570027 | 2013 | Q1 | Q1 - 2013 | Construction, equipment installation, and testing has been completed. All PFSA's have been activated and are able to carry traffic. Anchor institutions are being activated daily. | 91 | 528 | 1268 | 0 | 1887 | 0 | 0 | 20 | Positive variance. | No variance. | Not reflected as separate line item in baseline. No variance. | N/A | Positive variance. | N/A | N/A | No variance. | 16 | 0 | 12 | Windstream, TLSN, US Cable, CableOne, Sierra Communications, South Plains Telephone Cooperative, WT Services, Inc., Delcom, Five Area Systems, Yucca Communications, Penasco Valley Telecom, Conterra Ultra Broadband, Verizon Wireless, North Central NM Economic Development, Northern New Mexico Telecom, Inc. | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access Services which are typically Ethernet services from the local Interconnection Point to the anchor institution. | N/A | 8 | 8 | 0 | 17 | There are 8 providers currently receiving new access to ENMR's core middle mile network. | There are 8 providers currently receiving improved access to ENMR's core middle mile network. | N/A | DS1 - 0, DS3 - 0, OC3 - 0, OC12 - 2, 50Mb - 1, 100Mb - 6, 200Mb - 2, 500Mb - 1, 1Gb - 1, 2.5Gb - 1, 10Gb - 3 (one subscriber is receiving services via two separate speed tiers which is why this row totals 17). | 269 | 265 | 4 | 269 | N/A | N/A | N/A | 1.5Mb - 1, 3Mb - 4, 5Mb - 11, 8Mb - 7, 10Mb - 4, 15Mb - 0, 20Mb - 7, 30Mb - 0, 40Mb - 1, 50Mb - 0, 100Mb - 1, 1Gb - 23, 10Gb - 1, 209 - speed tiers not yet determined. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project complete. | E.N.M.R. Telephone Cooperative | None. | Project complete. The total for part i. Construction under Matching Funds for the "Actuals from Project Inception through End of Current Report Period" below includes $370,991 of ENMR Telephone Cooperative's in-kind matching requirement.
NT10BIX5570028 | 2010 | Q3 | Q3 - 2010 | No federal grant funds were expended during the quarter. The major task for the quarter has been to negotiate the extension of the BadgerNet Converged Network (BCN) contract. Implementation of this grant will be through the current managed service BCN contract between the State of Wisconsin and the Wisconsin BadgerNet Access (WBAA), a consortium of the telecommunication carriers in the state. The current contract period runs through November 2011 with a possible contractual extension to November 2016. At the end of the quarter, negotiations were proceeding. In addition, the State of Wisconsin, WBAA and NTIA have had discussion relative to the Special Award conditions, specifically the condition relating to the security interest for assets created by the grant. Significant progress was made during the 3rd quarter on the draft Environmental Assessment for the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Awaiting negotiation of BCN contract extension | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | When implemented, improved access would be at speeds at either 20MB per second or 100MB per second | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Not Applicable | In the next quarter, negotiations will continue on the extension of the overall BCN service contract, complete the work needed for the draft environmental assessment, with NTIA finalizing the EA process with issuance of a FONSI for the project. Once the contract extension is finalized, the project should make some progress on preliminary activities such as network design, right of way and permit activities and placing orders for equipment. | Administration, Wisconsin Department of | N/A | As mentioned in the second quarter report, this grant may face a challenge if we are unable to reach a satisfactory agreement relating to Special Award Condition #5, Security Interest in Real Property.
NT10BIX5570028 | 2010 | Q4 | Q4 - 2010 | No federal grant funds were expended during the quarter. Further progress was made during the 4th quarter on the draft Environmental Assessment for the project. Discussions between the State of Wisconsin Department of Administration, the network provider (the Wisconsin BadgerNet Access (WBAA)), and the NTIA have continued relative to the Special Award conditions, specifically the conditions relating to the security interest for assets created by the grant, non-discrimination and interconnection requirements. Successfully addressing these issues will allow the State of Wisconsin and WBAA to finalize the extension of the BadgerNet Converged Network (BCN) contract. As noted in previous progress reports, implementation of this grant will be through the current managed service BCN contract between the State of Wisconsin and the Wisconsin BadgerNet Access (WBAA), a consortium of the telecommunication carriers in the state. The current contract period runs through November 2011 with a possible contractual extension to November 2016. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Awaiting negotiation of BCN contract extension | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | When implemented, improved access would be at speeds at either 20MB per second or 100MB per second | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Not Applicable | We assume that in the first quarter of 2011, we will be able to finalize the discussion on the Special Award conditions and finish negotiations on the extension of the overall BCN service contract, and complete the work needed for the draft environmental assessment, with NTIA finalizing the EA process with issuance of a FONSI for the project. With those steps taken, the project should make some progress on preliminary activities such as network design, right of way and permit activities and placing orders for equipment. | Administration, Wisconsin Department of | The narratives for the Project Indicators #1 and #2 fully describes the current situation. | As mentioned above, the primary challenges facing the project are the resolution of questions relating to the Special Award conditions and from that point the extension of the managed service contract of the BadgerNet Converged Network.
NT10BIX5570028 | 2011 | Q1 | Q1 - 2011 | No federal grant funds were expended during the quarter. The revised draft of Environmental Assessment for the project was completed. Discussions between the State of Wisconsin Department of Administration, the network provider (the Wisconsin BadgerNet Access (WBAA)), and the NTIA continued in this reporting quarter relative to the Special Award conditions, specifically the conditions relating to the security interest for assets created by the grant, non-discrimination and interconnection requirements. Following extensive examination of complex issues, and review of multiple alternatives, it was determined that the parties had examined and exhausted all practical options. In February 2011, the Department of Administration requested to NTIA that the grant be terminated for convenience. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Delayed awaiting negotiation of BCN contract extension | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | The project was planned when implemented, to improved access at speeds of either 20MB per second or 100MB per second | 0 | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | FALSE | Not Applicable | In the second quarter of 2011, we will finalize the costs of the consultant hired to assist in the Environmental Assessment, seek and receive reimbursement for 80% of those costs and close the project. | Administration, Wisconsin Department of | The narratives for the Project Indicators #1 and #2 fully describes the current situation. | As noted earlier in the report, the project will be terminated for convenience.
NT10BIX5570028 | 2011 | Q2 | Q2 - 2011 | Reimbursement received for environmental assessment & project closed. The grant was terminated for convenience. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Not Applicable | Not Applicable -- grant and project terminated | Administration, Wisconsin Department of | Grant terminated for convenience. | N/A - project terminated
NT10BIX5570029 | 2010 | Q3 | Q3 - 2010 | A. Finalized Wave 1 deployments and confirmed needs of community anchor institutions for the wave. B. Began confirming Wave 2 deployments. C. Verified no over-builds in targeted service areas. D. Made progress towards finalizing primary vendor contract. E. Worked with National Telecommunications and Information Administration and vendor regarding security interest approach. F. Developed plan for customer outreach activities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See item #2a above | N/A | N/A | N/A | See item #2a above | N/A | N/A | See item #2a above | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | See item #2a above | See item #2a above | See item #2a above | See item #2a above | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We do not expect to provide any special offerings. | FALSE | ENA has no network management changes to report over the last quarter. | A. Finalize key vendor contract and National Telecommunications and Information Administration security interest requirements. B. Begin Wave I build-out and implementation. C. Secure signage, order circuits. D. Develop individual site transition plans and timeline. E. Begin customer outreach activities, includes ground-breaking. F. Finalize Wave 2 deployments. | Education Networks of America, Inc. | See response to item #2a above. ENA anticipates continued technical assistance to address security interest requirement concerns already brought to the National Telecommunications and Information Administration's attention. | A. Delayed contract finalization may impact planned progress. B. ENA anticipates continued technical assistance to address security interest requirement concerns already brought to the National Telecommunications and Information Association's attention.
NT10BIX5570029 | 2010 | Q4 | Q4 - 2010 | A. Finalized Wave 1 deployments and confirmed needs of community anchor institutions for the wave. B. Began confirming Wave 2 deployments. C. Verified no over-builds in targeted service areas. D. Continued work on finalizing primary vendor contract. E. Worked with the National Telecommunications and Information Administration and vendor regarding security interest requirements. F. Developed plan for customer outreach activities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See item #2a above. | N/A | N/A | N/A | See item #2a above. | N/A | N/A | See item #2a above. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | See item #2a above. | See item #2a above. | See item #2a above. | See item #2a above. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We do not expect to provide any special offerings. | TRUE | ENA has no network management changes to report over the last quarter. | A. Finalize key vendor contract and National Telecommunications and Information Administration security interest requirements. B. Initiate process to adjust project scope. C. Begin Wave 1 build-out and implementation. D. Secure signage, order circuits. E. Develop individual site transition plans and timeline. F. Begin customer outreach activities, includes ground-breaking. G. Finalize Wave 2 deployments. | Education Networks of America, Inc. | See response to item #2a above. ENA anticipates continued technical assistance to address security interest requirements and program adjustments. | A. Delayed contract finalization may impact planned progress. B. ENA anticipates continued technical assistance to address security interest requirement and program adjustments.
NT10BIX5570029 | 2011 | Q1 | Q1 - 2011 | Began and completed grant termination activities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See item #2a above. | N/A | N/A | N/A | See item #2a above. | N/A | N/A | See item #2a above. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | See item #2a above. | See item #2a above. | See item #2a above. | See item #2a above. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | N/A - Grant terminated. | Education Networks of America, Inc. | See response to item #2a above. | N/A - Grant terminated.
NT10BIX5570030 | 2010 | Q3 | Q3 - 2010 | Satisfied Environmental Assessment Special Award Condition. Prepared materials, made presentations, and obtained DeKalb County Economic Development Committee and Board approval of Ordinance designating DeKalb Fiber Optics, LLC as sole source provider for infrastructure to be constructed under this grant. Negotiated drafts of Indefeasible Right of Use Documents with DeKalb Fiber Optics for completed segments. Drafted agreement to be used with Community Anchor Institutions. Started drafting of scope of work for Northern Illinois University Outreach for Community Anchor Institution consulting. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction not started. Additional installation crew will be provided to assist in catching up with substantial and final completion requirements. | N/A | Construction not started. Reflects new fiber to be installed in contributed duct per Contribution Agreement. Will be completed within available resources in construction sequence. | Reflects those segments o be acquired by IRU from DeKalb Fiber Optics per Contribution Agreement. | Construction not started. Additional installation crew will be provided to assist in catching up with substantial and final completion requirements. | N/A | N/A | Construction not started. Additional installation crew will be provided to assist in catching up with substantial and final completion requirements. | 1 | 2 | 5 | TBC Net, Inc. | 100mb vlan; 1gb vlan; wholesale bandwidth; consumer access. | DeKalb Fiber Optic, nc. (Fiber Physical Layer), Vendor Northern Illinois University (Electronics and CAI) , Vendor/ Sub-recipient status tbd | 0 | 1 | 0 | 0 | Discussions are continuing with prospective providers. | Discussions are continuing with prospective providers. | We have approached one possible dark fiber subscriber. | See response to Q. 5c. | 41 | 0 | 0 | 41 | Current estimate of anchor institutions at end of Q3. | None at this time. | None at this time. | dark fiber | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Work continues on the downtown DeKalb renovation mentioned in the Q2 PPR. Infrastructure to be constructed under this grant will provide connection for the downtown DeKalb project. | FALSE | N/A | Assuming we can get the required agreements in-place, we plan to install as much as 40,000 feet of duct and sufficient fiber to connect the first Community Anchor Institutions by the end of Q4. This would include equipment placement and fiber testing. We expect to sign agreement with Northern Illinois University Outreach early in Q4 for recruitment and needs assessment of community anchors. | De Kalb, County of (Inc.) | With assistance from materials provided by BTOP, DeKalb Fiber Optics determined their status as a vendor. Once this determination was completed, justification and presentation of a sole source ordinance was presented for approval by the DeKalb County Board. This approval was followed by the drafting of the needed documents with DeKalb Fiber Optics, which is where we currently are in the process. There are three agreements between DeKalb County and DeKalb Fiber Optics that are being drafted and negotiated: Those are an Indefeasible Right of Use (IRU), a Contribution Agreement and a Location, Maintenance and Relocation (LMR) Agreement. The IRU is the instrument by which the County will acquire the 48 strands of fiber. The Contribution Agreement outlines the contributions of DFO to the project. We see no reason at this time why the IRU, Contribution and LMR agreements cannot be complete in Q4. The final challenge we are experiencing is receipt of the local cash share being provided by the State of Illinois. We are using all efforts to get the State to provide an written agreement for the funds the State has agreed in writing to provide. We have been promised this agreement will be provided in Q4 and State funds will be released. This entire process has taken longer than we anticipated when we prepared the baseline report. | Good progress has been made toward getting the public/private agreements in-place including approval of a sole source ordinance and the consulting agreement with Northern Illinois University Outreach. We expect agreements with DeKalb Fiber Optics will be completed and construction started in Q4. Construction is contingent on receiving the local cash share being provided by the State of Illinois.
NT10BIX5570030 | 2010 | Q4 | Q4 - 2010 | Completed and executed Indefeasible Right of Use (IRU) with DeKalb Fiber Optic, LLC.. Started infrastructure construction. Completed and executed agreement with Northern Illinois University Outreach Broadband Development Group to help engineer and integrate new DeKalb Advancement of Technology Authority (DATA) members' existing network into new network architecture. Started surveys of new DATA members to determine equipment needs and physical layout. Executed agreement with State of Illinois for grant to provide substantial portion of local cash share. Started procurement process for participant premise equipment. Drafted and received State's Attorney approval of template Participant (Community Anchor) Agreement. Drafted agreement to be used for node equipment facility owners. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Underground duct only, no fiber installed. | N/A | Reflects new fiber to be installed in duct to be contributed by DeKalb Fiber Optic, LLC. | Reflects existing fiber to be acquired from Northern Illinois University | No fiber installed. | N/A | N/A | Only duct installed in Q4. | 1 | 3 | 20 | TBC Net, Inc. | 100mb VLAN; 1gb VLAN; wholesale bandwidth; consumer access. | DeKalb Fiber Optic, LLC (Fiber Physical Layer); Vendor Northern Illinois University (Electronics and CAI); Vendor/ Sub recipient TBD. | 0 | 1 | 0 | 0 | Discussions are continuing with prospective providers. | Discussions are continuing with other prospective providers. | We have been discussing dark fiber with one prospective provider. | Please see response to Q. 5c. | 0 | 0 | 0 | 0 | There is no fiber installed as of the end of Q4. We had estimated in the baseline report there would be 59 serviced by the end of Q4. Start of work was delayed due to additional time needed for negotiation and drafting of documents. | None at this time. | None at this time. | None at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing wifi and video surveillance for City of DeKalb central business district. | FALSE | N/A | Duct installation amounting to approximately 56,000lf. Fiber installation amounting to approximately 60,000lf. Actively working fiber consisting of 11 miles as of end of Q5. Connection of 10-15 anchor institutions including Brooks Elementary School, DeKalb County Highway Department, Downtown DeKalb Ben Gordon DeKalb locations and Genoa-Kingston Schools (local connections). Procurement of participant premise switching equipment for Q5 community anchors. DeKalb County is working closely with Northern Illinois University to assure that both BTOP projects have interconnection points to create a cohesive network. The DeKalb County grant in partnership with the Northern Illinois University grant will benefit in both network architecture and scalability of delivering services to a wider region. DeKalb County is also working with the IBOP-EC project where enhanced services will be delivered for Illinois Century Network constituents from an interconnection point in DeKalb Illinois at Northern Illinois University. As an ongoing effort to maximize the efforts throughout the State of Illinois, DeKalb County is cooperating with the Partnership for Connected Illinois and providing the necessary information required under their charter. | De Kalb, County of (Inc.) | Last quarter we mentioned we did not have an agreement with the State of Illinois yet for a grant to provide a significant share of the local cash match. That issue is resolved: We signed the Grant Agreement with the State of Illinois and received 25% of the State's Grant amount in cash. Resources for Rights-of-Way and permits are in place to acquire rights and permits when they are needed to keep pace with construction. Equipment procurement process is on-track for equipment acquisition when needed to connect anchors. Network Build scheduled and resources in place to be on-schedule by July and accomplish substantial completion as required. Fiber to be received and installation and connection started in Q5. Final agreement reached in early December and start of construction in late December was not the best timing weather-wise but we did manage to install a mile of duct and get fully mobilized. | Weather during the early part of Q5 is always unpredictable and may be a challenge. The contractor has committed to bringing on additional resources in April to get the construction back on target. As we recontact potential Community Anchors, the plans of some have changed and will not now be Anchors. Some additional entities are now interested in becoming Anchors. There will be a need for some route alterations to accommodate these changes. We expect to submit these for review and approval to NTIA in Q5. There is a great concern by the recipient to make sure the vendor/ sub-recipient issues is correctly resolved especially as it relates to post-completion auditing. Finally, our vendor/contractor is committed in terms of resources, procurement and technology to recover the original schedule in order to meet the substantial and final completion deadlines.
NT10BIX5570030 | 2011 | Q1 | Q1 - 2011 | Installed 79,666 feet (15 miles) of duct and 48,198 (9 miles) of fiber in Q5; completed optical path between DeKalb Brooks School and DeKalb High School; exceeded target by one month to move to summer installation rate for duct; completed on-site engineering for 14 Community locations. | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 41 | Baseline predicted the system to be 60% built at this time (78 miles). The project was behind schedule early due to difficulty getting agreements in place. Expected to reach 78 miles in Quarter 7. | N/A | N/A | Reflects existing fiber to be acquired from Northern Illinois University | The project was behind schedule early due to difficulty getting agreements in place. We project we will have 67 miles installed Quarter 7. | N/A | N/A | Project will reach baseline of 228 interconnect points in Quarter 7. | 1 | 3 | 20 | TBC Net, Inc. | o 100MB VLAN- $300/ month o 1GB VLAN- $600/month o Wholesale Bandwidth- $20/MB/month o Consumer access- $90/month o Dark fiber- $750/strand/mile./year | DeKalb Fiber Optics, LLC (Fiber Physical Layer); Vendor Northern Illinois University, (Electronics and CAI); Vendor | 0 | 1 | 0 | 0 | Discussions are continuing with prospective providers. Project will be as baseline (3) in Quarter 8. | Discussions are continuing with other providers. Project will be at baseline (3) in Quarter 8. | We have been discussing dark fiber with one prospective provider. | Please see response to Q. 5c. | 0 | 0 | 0 | 0 | Baseline target of 76 CAI's projected to be reached in Quarter 7. | Baseline target of 35 CAI's projected to be reached in Quarter 7. | Baseline target of 41 CAI's projected to be reached in Quarter 10. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing wifi and video surveillance for City of DeKalb central business district. | FALSE | N/A | We expect the north segments (1-6) to be complete by 6/30/11. We also expect the duct installation to be approximately 36% complete (47 miles) and the fiber to be approximately 30% complete (39 miles) by 6/30/11. Project 50-70 anchor institutions to be connected by the end of Quarter 6. Community Anchor switching equipment will be installed in the facilities of those anchors in the north part of the route in Q6 and many of those anchors are expected to be connected and "lit". Backbone equipment is expected to be competitively bid and installed in the node locations in the north part of the route. Equipment required to connect the emergency radio system towers and repeaters to the system will be bid in Q6. | De Kalb, County of (Inc.) | One week of production was lost due to rescoping of project to change ownership of project assets. A great deal of administrative time is being spent by DeKalb County and DeKalb Fiber Optics regarding in-kind contribution of DeKalb Fiber Optics as a part of grant local share and payment for IRU for strands being granted to DeKalb Fiber Optics for economic development. Projections for Rights of Way, Construction Permits, Network Build and Testing are based on detailed production schedules which have been targeted to required substantial completion deadline. Production has been exceeded targets during each week crew has worked since 2/1/11. For Equipment, projection is based on actual purchase awarded for CAI switches and engineering progress for backbone equipment. Since 1/1/11, contractor has exceeded production goals designed to meet the substantial completion deadline. This has been accomplished through additional work hours and additional equipment.ï‚§ | Despite loosing one week of production due to work being stopped while project was rescoped, duct installation exceeded winter production requirements. We expect these production levels to continue during Q6. Considering the project was essentially at 0% at the end of Q4, 6% at the end of Q5, 10% (actual) at the end of April, 2011, 15% (actual) at the end of May, and projected to be 26% at the end of Q6, we are on schedule to meet the substantial completion deadline.
NT10BIX5570030 | 2011 | Q2 | Q2 - 2011 | Installed 196,733 feet (37.26 miles) of duct and 148,808 feet (28.18 miles) of fiber in Q6. Completed optical path and connected 11 community anchor institutions. Continued on-site engineering for community anchor institutions. Received and inventoried switches to be used by community anchors. Bid, awarded and ordered backbone equipment. Employed 13.91 full time equivalent individuals in construction and administration of project. Project is on schedule to meet substantial completion and final completion deadlines. | 37 | 0 | 0 | 0 | 37 | 0 | 0 | 135 | Baseline predicted 95 miles of duct at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to reach 95 miles in Q8 (4-6 additional months). | N/A | N/A | Reflects existing fiber to be leased from Northern Illinois University. This lease will be part of overall agreement with NIU and is expected in Q8. | Baseline predicted 85 miles of fiber built at this time. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 85 miles of fiber installed by Q8 (4-6 additional months | N/A | N/A | Baseline predicted 285 interconnection points as of now. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 285 interconnection points by Q8 (4-6 additional months). | 1 | 3 | 20 | TBC Net, Inc. | - 100MB VLAN- $300/mo. - 1Gb VLAN- $600/ mo. - Wholesale Bandwidth- $20/Mb/mo. - Consumer Access- $90/ mo. - Dark fiber- $750/strand/mile/year | DeKalb Fiber Optics, LLC, (Fiber Physical Layer); Vendor, Dan Halverson (danh@admin.tbc.net) Northern Illinois University, (Electronics and CAI); Vendor, Herb Kuryliw (hkuryliw@niu.edu) | 0 | 1 | 0 | 0 | Baseline predicted 2 at this point. Project will be at baseline in Q8. | Baseline predicted 2 at this point. Project will be at baseline in Q8. | Discussions continuing with several potential dark fiber customers. | See response to Q 6c. | 11 | 5 | 6 | 11 | Baseline predicted 111 at this point. Project expected to be at baseline in Q9 or Q10. | Baseline predicted 70 at this point. Project expected to be at baseline in Q9 or Q10. | Baseline predicted 41 at this point. Project expected to be at baseline in Q9 or Q10. | 10 @ 1 Gb; 1 @ 50Mb to date. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide wifi and video surveillance for City of DeKalb downtown, fiber back haul system for E-911 emergency radio network and co-location in four telephone company central offices. | FALSE | N/A | We expect to pay for 171,500 feet (32.48 miles) of duct and 219,291 feet (41.5 miles) of fiber (53% completed with construction). We expect to complete fiber path to north part of route and connect those community anchors when backbone equipment is received and installed. We will bid and order equipment needed for E-911 fiber back haul equipment. | De Kalb, County of (Inc.) | The project was behind schedule early due to difficulty getting agreements in place but has been making good progress since then. For example, network build has gone from 1% at end of Q4 to current 27% at the end of Q6. Projections for rights of way, construction permits, network build, and testing are based on detailed construction schedule which have been targeted to required substantial completion deadline. Production has exceeded targets during each week in Q6. Community anchor switches have been received and are ready for deployment; backbone equipment is ordered and expected to be received and paid in Q8. Row acquisition for the south part of the route has been a challenge. Our route south and west of Hinckley involves a laborious process of permitting from each township road commissioner as well as the land owner, many of whom own to the center of the road or, in some cases, the entire road. Contractor has provided additional personnel and legal resources to keep the project on schedule. The contractor has moved crews to areas that have row agreements in place so work can continue on schedule. | Any ROW issues that cannot be resolved with the landowners may require minor route changes. All efforts are being made to maintain the approved route.
NT10BIX5570030 | 2011 | Q3 | Q3 - 2011 | Installed 115,000 feet (21.78 miles) of duct and 120,374 feet (22.8 miles) of fiber in Q7. Bid E-911 fiber back haul equipment. Continued on-site engineering of Community Anchor Institutions including holding meetings with agencies representing 161 possible connections to-date. Community anchor engineering is being conducted with Villages, Libraries and other municipalities at this point. Continued efforts to obtain row agreements with landowners on the south portion of the project. Obtained connection to Northern Illinois Technology Triangle. Contacted all county fire districts about project. Employed 14.95 full time equivalent individuals in construction and administration of the project. Project is on schedule to meet substantial completion and final completion deadlines. | 54 | 0 | 0 | 0 | 54 | 0 | 0 | 160 | Baseline predicted 120 at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to reach 120 miles in Q9 (4-6 additional months). | N/A | N/A | Fiber to be leased from Northern Illinois University. Agreement expected to be approved in Q8 | Baseline predicted 115 miles of fiber at this point. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 115 miles installed in Q9 (4-6 additional months). | N/A | N/A | Baseline predicted 343 interconnection points installed by now. The project was behind schedule early due to difficulty getting agreements in place. Expect to have 343 interconnection points installed by Q10 (7-9 additional months). | 1 | 1 | 20 | TBC Net, Inc. | -100Mb VLAN- $300/mo. - 1Gb VLAN- $600/mo. - Wholesale bandwidth- $20/Mb/Mo. - Consumer Access- $90/Mo - Dark Fiber- $750/strand/mile/year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, Vendor,Dan Halverson, (danh@admin.tbc.net). DeKalb Fiber is operating 68 fibers for economic development and providing locating, maintenance and repair for the DeKalb County's 76 fibers. Electronics, Network Operations and CAI's: Northern Illinois University, Herb Kuryliw, (hkuryliw@niu.edu) | 0 | 1 | 0 | 0 | Baseline Predicted 3 at this point. Project will be at baseline in Q8 | Baseline Predicted 3 at this point. Project will be at baseline in Q8 | There is good interest in dark fiber from the commercial and economic development perspective. | N/A | 11 | 5 | 6 | 11 | Baseline predicted 111 at this point. Project expected to be at baseline in Q10. | Baseline predicted 70 at this point. Project expected to be at baseline in Q10. | Baseline predicted 40 at this point. Project expected to be at baseline in Q10. | 10 @ 1Gb, 1 @50Mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide wifi and video surveillance for City of DeKalb downtown; fiber back haul for County-wide E-911 system; and colocation in four telephone company central offices. | FALSE | N/A | Plan to install 73,500 feet (13.92 miles) of duct making total duct 89.2 miles and 138,336 feet (26.2 miles) of fiber in Q8, making total fiber installed 80.2 miles by the end of Q8; Plan to connect all Anchors on north part of the route (10-15 new connections) resulting in 21-26 total connections by the end of Q8 including anchor switching equipment; Plan to receive all backbone equipment and deploy that needed to light the north part of the route; Plan to award the E-911 fiber back haul equipment purchase; Plan to finalize the agreement with Northern Illinois University providing for lease of 12 strands over 10 miles; plan to receive remainder of in-kind donation of duct from DeKalb Fiber Optics, LLC on Peace Road; plan to finalize one additional last mile provider agreement in Q8 resulting in a total of 4 signed agreements. | De Kalb, County of (Inc.) | The project was behind schedule early due to difficulty getting agreements in place but has been making good progress since then. For example, network build has gone from 1% at end of Q4 to current 50% at the end of Q7. Projections for rights of way, construction permits, network build, and testing are based on detailed construction schedule which have been targeted to required substantial completion deadline. Production has slowed in Q6 due to ROW acquisition issues. Community anchor switches have been received and are ready for deployment; backbone equipment is ordered and expected to be fully received and paid in Q8. Row acquisition for the south part of the route has been a challenge. Our route south and west of Hinckley involves a laborious process of permitting from each township road commissioner as well as the land owner, many of whom own to the center of the road or, in some cases, the entire road. A route change is being requested to allow us to reach the Community Anchors in some areas of the south county. The contractor has moved crews to areas that have row agreements in place so work can continue. | Right of Way acquisition is the biggest challenge to the project at this point. We are working with the program officials to resolve these issues so we can serve the intended Community Anchors.
NT10BIX5570030 | 2011 | Q4 | Q4 - 2011 | Installed 116,936 feet (22.15 miles) of duct and 160,801 feet (30.46 miles) of fiber in Q8, taking the percentage complete for duct to 84% and percentage complete for fiber to 65%. Continued on-site engineering for community anchor institutions. All potential anchors have been contacted (some more than once) and the connection agreement negotiation process continues. Continued the Rights of Way (ROW) acquisition process in southern DeKalb and northern La Salle Counties. Continued the municipal utility agreement negotiation process. Obtained one additional utility agreement (Waterman). Submitted route change request to NTIA in December, 2011. Completed rail and interstate crossing permit process. Completed 13 additional connections (total now 24). Received and started configuration of backbone equipment. Ordered and started deployment of fiber back haul equipment for E-911 system. Completed purchase of fiber strands from Northern Illinois University. Completed acquisition of duct from DeKalb Fiber Optics, LLC (in-kind). Tested installed fiber paths in completed sections totalling 52,000 feet. Employed 14.43 full time equivalent individuals is the construction and administration of the project. Project is on-schedule to meet substantial and final completion deadlines. | 84 | 0 | 0 | 12 | 84 | 0 | 0 | 210 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. The network build has been progressing well since 1/1/11. Expect to reach 130 miles in Q10. (nine additional months). | N/A | N/A | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | Installed as of 12/31/11. Project total is 129.59 miles of new fiber. | N/A | N/A | Baseline predicted 366 interconnection points at the end of Q8. Additional interconnection points are to be added as duct is completed. | 0 | 4 | 0 | One last mile agreement in place between DeKalb Fiber Optics and TBCNet. Recipient is not a party to this agreement so it has not been included in the indicators provided above. | Provided by DeKalb Fiber Optics to Commercial Customers: -100Mb VLAN: $300/month - 1Gb VLAN: $600/month - Wholesale bandwidth: $20/Mb/Month - Consumer Access: $90/month - Dark Fiber: $750/strand/mile/year Provided by DeKalb County to Community Anchors: - Full participant: dark fiber, 1Gb transport to Illinois Century Network- $7,000/location/year - Subscriber Services: Transport and ISP: 100Mb- $2,800/ year; 50Mb- $1,050/year. | Fiber Physical Layer: DeKalb Fiber Optics, LLC., Vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber is operating 68 fibers for economic development and providing locating, maintenance and repair functions for DeKalb County's 76 fibers. Electronics, Network Operations and Community Anchor Engineering: Northern Illinois University, Vendor, Herb Kuryliw, hkuryliw@niu.edu | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 24 | 5 | 19 | 24 | Baseline predicted 111 at this point. Project total is expected to be 105 which will be reached in Q10 | Baseline predicted 70 at this point. Project total is expected to be 30 which will be reached in Q10. | Baseline predicted 41. Project total is expected to be 75 which will be reached in Q10 | 21 @ 1Gb; and 3 @50 Mbps to internet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide wifi and video surveillance for City of DeKalb downtown area, fiber back haul for DeKalb County E-911 system and collocation in four telephone company central offices. | FALSE | N/A | Plan to install 50,000 additional feet (9.5 miles) of duct and 160,000 additional feet (30 miles) of fiber in next quarter making 114 total network miles deployed. Plan to make 45 additional connections next quarter making a total of 69 CAI connections. No additional leased network is anticipated for the project making the expected network miles leased 12 miles at the end of the next quarter. Last mile provider agreements are in discussions with providers but no signed agreements are expected in the next quarter. Plan to deploy backbone equipment in four telephone company collocation sites and into the network operations center at Northern Illinois University. Plan to deploy fiber back haul equipment. Plan to complete design for GPON, wireless access points and downtown wireless and bid and order equipment. We plan to obtain all row next quarter and intend to have 13 of 14 utility agreement in hand by the end of next quarter. We plan to have 25% of the system tested by the end of next quarter. In Q9, we will complete an independent verification of installed duct and fiber footage performed by a registered professional engineer. | De Kalb, County of (Inc.) | The project was behind schedule early due to problems getting the indefeasible right to use and locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Good progress has been made since 12/31/10 with project completion now at 62%. Production slowed from predictions because of row issues detailed above. Progress has been made in spite of row issues by contractor moving crews to areas of approved row access. Project is on schedule to meet the substantial and final completion requirements if row issues can be resolved. | Some of the utility agreements with municipalities have been more difficult to obtain than anticipated. We expect to get some resolved in Q9 but probably not all. We are only able to complete the build in these areas when the agreements are completed.
NT10BIX5570030 | 2012 | Q1 | Q1 - 2012 | Installed 14162 feet (2.68 miles) of duct and 95,298 feet (18.07 miles) of fiber in Q9 of award, taking percentage complete for duct to 86% and percentage complete for fiber to 80%. Continued on-site engineering for community anchor institutions. The process of approval of connection agreements with community anchors continues. Continued the rights-of-way acquisition process in southern DeKalb County and northern LaSalle County. Continued the municipal utility agreement negotiation process. Acquired one additional utility agreement (Shabbona) and installed duct in Shabbona shortly thereafter. Received route change approval from NTIA in early January and installed duct (and some fiber) on approved route in same month. Completed eight additional connections in Q9, making total now 32 of 85 expected. Deployed backbone equipment in four node locations (Genoa Frontier central office, Northern Illinois University Network Operations Center, Northern Illinois University central office and DeKalb Frontier central office). Completed an independent verification of all duct and fiber installed as of 12/31/11. Tested 177,000 additional feet (33.53 miles) of fiber making total tested 229,000 feet (43.37 miles). Continued deployment of E-911 fiber back haul equipment. Met required substantial completion deadline of 67% complete by 24 months after award. Employed 6.91 full time equivalent individuals in the construction and administration of the project in Q9 of award. | 102 | 0 | 0 | 12 | 102 | 0 | 0 | 228 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Expect to reach 130 miles in Q11 of award (nine additional months). | N/A | N/A | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | Installed as of 3/31/12. Project total is 129.59 miles of new fiber. | N/A | N/A | Baseline predicted 366 interconnection at the end of Q9 of award. Expect to reach baseline in Q11 of award. Additional interconnection points are added as duct and fiber is constructed. | 1 | 4 | 12 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. . DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement so it has not been included in the indicators provided above. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport and ISP: 100 Mb (shared): $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 32 | 6 | 26 | 32 | Baseline predicted 111 at this point. 85 are currently projected. The projected CAI count was reduced to eliminate the 911 towers and the agricultural businesses at the direction of NTIA. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. | Baseline predicted 70 at this point. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. | Baseline predicted 41 at this point. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. | 26 1 GB; 3 @ 50 MB to internet; 1 dark fiber only and 2 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide public wifi and video surveillance for City of DeKalb downtown area, fiber back haul for DeKalb County E-911 system and collocation in four telephone central offices. | FALSE | N/A | Plan to install an additional 87,600 feet (16.6 miles) of duct and fiber in Q10 of award assuming additional municipal right of way becomes available by May 1. This would put the project at 120 miles of fiber at the end of June, 2012 or 95% of network build complete. Plan to make 31 additional CAI connections by June 30, making total connections by June 30 at 63 of 85 anticipated or 74% of connections completed for project by June 30. All leased fiber was completed for the project in the previous quarter so no additional leased network is anticipated for Q10 of award. We expect to sign two of the four anticipated last mile provider agreements in Q10 of award. We expect to deploy equipment in one additional collocation site in Q10 of award. We plan to complete the procurement of wireless access points for libraries by ordering, receiving and starting deployment in Q10 of award. Plan to complete analysis of vendor neutral cabinets and start procurement process in Q10 of award. Plan to complete engineering design and competitively bid the downtown DeKalb wifi/ surveillance project in Q10. We plan to either acquire outstanding row in Q10 or submit route change request to reroute around parts of the route that we have been unable to acquire. We plan to have all municipal row agreements in hand by the end of Q10 of award or submit route change requests to reroute around municipalities from which we have not been able to acquire access for the approved route. Testing of installed fiber will continue in Q10. We expect to test and additional 184,000 feet (30 miles) which would make the system 58% tested by the end of Q10. | De Kalb, County of (Inc.) | The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approval of the route change in January, 2012 allowed the project to install substantial amounts of duct in the rural Somonauk, Leland and Earlville areas. Duct installation has stopped until we can acquire the remaining municipal row agreements and private property agreements. All municipality and private row agreements are being actively negotiated. The project has been delayed in accessing telephone company central offices in Genoa, DeKalb and Hinckley due to scheduling and coordination issues with the central office owner. Genoa and DeKalb were competed in Q9 of award, Hinckley is expected to be completed in Q10 of award and the final central office location (Sandwich) schedule depends on approval of utility agreement with Sandwich so network can be expanded into City of Sandwich to reach the telephone central office co location facility. | Municipal row agreements and access to some privately-owned row has proven to be the biggest challenge to the project. In order to complete the project in the areas for which we have not able to acquire access, we may need to request route changes.
NT10BIX5570030 | 2012 | Q2 | Q2 - 2012 | No new duct was installed in Q10. Total duct installed is 99.21 miles and new total for project is 113.51, making the duct 87% complete. 6.9 miles of fiber was installed in Q10 making total fiber installed 110.3 miles. New project total for fiber is 127 miles, making fiber 87% complete. Continued on-site engineering with Community Anchor Institutions. Continued the right-of-way and municipality utility agreement process. Acquired right-of-way access for one parcel; one right-of-way issue remains. Acquired municipality utility agreements for three municipalities; one remains to be completed. Ten new connections were completed in Q10 as the agreement to connect DeKalb School District #428 was completed. No other connections were finalized in this quarter due right-of-way and utility agreement issues. Connections are now at 39 of 84 expected. One DeKalb School District #428 school was sold and are no longer is a potential Community Anchor connection. Lit the backbone equipment at co location sites in Genoa central office, DeKalb central office, Northern Illinois University network operations center and Northern Illinois University central office. Deployed and lit the backbone equipment in Hinckley central office. One backbone equipment site (Sandwich) remains to be deployed and will be completed when fiber installation in the City of Sandwich is completed. Continued deployment of E-911 fiber back haul equipment. Completed analysis of vendor neutral cabinets at several locations throughout the County and decided to not pursue this project. Completed connection to Northern Illinois Technology Triangle (NITT). Worked with DeKalb Fiber Optics, LLC and Northern Illinois University on deployment of network management software. Approved agreement with Northern Illinois University for network operations center services. Updated and revised project web site to include additional information and documents on project status and policies. Worked with representatives of BTOP northwest project (iFiber) on coordinated regional marketing of dark fiber. Submitted City of DeKalb downtown surveillance project to NTIA for funding review and was informed that surveillance equipment is not an allowable program expense. Employed 3.24 full time equivalent individuals in the construction and administration of the project in Quarter 10 of award. | 110 | 0 | 0 | 12 | 110 | 0 | 0 | 234 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. New completed network total is 127 miles which we expect to reach in Q12 of award (twelve additional months). | N/A | N/A | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | Installed as of 6/30/12. Project total if 127 miles of new fiber. | N/A | N/A | Baseline predicted 366 interconnection at the end of Q9 of award. Elimination of Knolls build reduced interconnection points by 8 to 358 (new baseline). Expect to reach baseline in Q11 of award. Additional interconnection points are added as duct and fiber is constructed. | 1 | 4 | 12 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. . DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement so it has not been included in the indicators provided above. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport and ISP: 100 Mb (shared): $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 1 | 1 | 1 | None at this time. We are in discussions with three providers and anticipate agreements in Quarter 11 or award. All are current providers so access is expected to be "improved" for all. | DeKalb Fiber Optics, LLC. We are in discussions with three additional providers and anticipate agreements in Quarter 11 of award. All are current providers so access is expected to be "improved" for all. | DeKalb Fiber Optics, LLC. We are in discussions with three additional providers and anticipate agreements in Quarter 11 of award. None of the providers are expected to received access to dark fiber. | All lit connections provided by DeKalb Fiber Optics are expected to be over a 1Gb interface. | 39 | 6 | 33 | 39 | Baseline predicted 111 at this point. 84 are currently projected. Ten new subscribers served in Q11 of award. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. Total subscriber count reported in Q1 2012 was corrected. The total of 39 reflects 10 additional CAI's listed in Section 9 and the current project total. | Baseline predicted 70 at this point. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. | Baseline predicted 41 at this point. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. | 33 1 GB; 3 @ 50 MB to internet; 1 dark fiber only and 2 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide public wifi for City of DeKalb downtown area, fiber back haul for DeKalb County E-911 system and collocation in four telephone central offices. | FALSE | N/A | All right-of-way and municipal utility agreements are expected to be complete early in Q12 of award. That will allow for significant progress towards completing the network. Plan to install as much as 60,000 feet (11.36 miles) of duct of the 12.31 miles to completed the project in Q11 of award. Expect duct to be 97% complete by the end of Q11 of award. Fiber should be installed in 50% of the new duct (additional 6.7 miles) in Q11 of award making fiber 92% by the end of Q11 of award. The completion of the fiber will allow for 30 additional CAI connections by September 30, making total connections 69 of 84 anticipated or 82% of connections completed for project. All leased fiber was completed for the project in the previous quarter so no additional leased network is anticipated for Q11 of award. We expect to sign two of the four anticipated last mile provider agreements in Q11 of award. We expect to deploy equipment in one additional collocation site in Q11 of award. We plan to complete the procurement of additional 10Gig "ring" modules and start deployment in Q11 of award. Plan to complete engineering design and competitively bid the downtown DeKalb wifi project in Q11. We plan to acquire outstanding row in Q11. We plan to have all municipal row agreements in hand by the end of Q11 of award and to have installed all duct and substantial fiber in these open areas in the system. Testing of installed fiber will continue in Q11. We expect to test and additional 184,000 feet (30 miles) which would make the system 58% tested by the end of Q11. Plan to submit route change requests to modify approved route in order to serve community anchors that were intended to be served by the project but were omitted from the official route map and to serve some additional community anchors that were not originally intended to be served but are now requesting to be included. | De Kalb, County of (Inc.) | The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Duct installation stopped in Q10 until the remaining municipal row agreements and private property agreements can be acquired. Late in the quarter we resolved one right-of-way and three municipal utility agreements which will allow duct installation to continue in July. The final co-location site (Sandwich) cannot be installed until approval of utility agreement by the City of Sandwich. At that point, the network can be expanded into City of Sandwich to reach the telephone central office co location facility. The City gave tentative approval in May of 2012 and final approval will be given when the detailed engineering drawings are submitted and approved. Final approval is expected in July and duct installation should start shortly thereafter. | None anticipated.
NT10BIX5570030 | 2012 | Q3 | Q3 - 2012 | 13.45 additional miles of duct were installed in Q11 of award. Total duct is now 112.66 miles and is 97.26% complete. The remaining duct is in the Sandwich, Somonauk and Malta areas for which we recently received right of way agreements. 10.41 miles of new fiber was installed in Q11. Total new fiber installed is now 120.71 miles and is 94.8% complete. 12.02 miles of fiber was purchased for the project in previous quarters. Total network approved network miles is 139.66 and is 95.00% complete. A route change is pending which, if approved will add approximately 2.5 miles to the total network. Started duct and fiber installation in City of Sandwich which will allow for the connections of the community anchors and final backbone equipment node site at the Sandwich telephone central office. Continued on-site engineering with community anchor institutions. Continued the right of way access and municipality utility agreement approval process. Acquired the one remaining right of way agreement; all right of way has now been acquired for the project. Received the final municipal utility agreement needed for the project. Completed 10 additional connections to the network this quarter. Continued deployment of E-911 fiber back haul equipment; connections have been finalized between Kirkland, Genoa and Sycamore. Completed last mile provider agreement with provider. City of DeKalb decided to not participate in downtown wireless project so that element is not being pursued. Completed participation agreement and contribution agreement with Northern Illinois University. Provided response to Corrective Action Plan. Completed letters of clarification for Indefeasible Right to Use Agreement with DeKalb Fiber Optics that were recommended in the fiber verification audit. Submitted first draft of route change request. Released request for proposals and awarded project for valuation of duct donated to the project by DeKalb Fiber Optics, LLC as an in-kind to the project. As a result of the County's annual audit, an adjustment was made to match expenditures in the "Architectural and Engineering Fees". Auditors opinion was that the documents for in-kind engineering provided by DeKalb Fiber Optics, LLC did not support the entire in-kind that had been taken. Therefor a reduction correction was taken during Q3-12. Employed 9.83 full time equivalent individuals in the construction and administration of the project in quarter 11 of award. | 133 | 12 | 0 | 0 | 121 | 0 | 0 | 269 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approved new completed network total is 136 miles which we expect to reach in Q12 of award (twelve additional months). | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | N/A | Miles reported as "existing" in last report was corrected to be categorized as "New Network Miles leased upon clarification of NTIA's definitions. | Installed as of 9/30/12. Project total of 127.64 miles of new installed fiber. | N/A | N/A | Baseline predicted 366 interconnection at the end of Q9 of award. Elimination of Knolls build reduced interconnection points by 8 to 358 (new baseline). Expect to reach baseline in Q12 of award. Additional interconnection points are added as duct and fiber is constructed. | 2 | 2 | 14 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement so it has not been included in the indicators provided above. In Q3-12, DeKalb County signed an agreement with Syndeo Networks, Inc. to provide last mile services on the network. DeKalb County expects two additional last mile provider agreements by the end of the award period. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport and ISP: 100 Mb (shared): $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 2 | 1 | 2 | None at this time. We are in discussions with two providers and anticipate agreements in Quarter 12 of award. All are current providers so access is expected to be "improved" for all. | DeKalb Fiber Optics, LLC and Syndeo Networks, Inc. We are in discussions with two additional providers and anticipate agreements in Quarter 12 of award. All are current providers so access is expected to be "improved" for all. | DeKalb Fiber Optics, LLC. We are in discussions with two additional providers and anticipate agreements in Quarter 12 of award. None of the providers are expected to receive access to dark fiber. | All lit connections provided by DeKalb Fiber Optics are expected to be over a 1Gb interface. Syndeo Networks, Inc. is offering up to 100Mbps to the internet. | 50 | 6 | 44 | 50 | Baseline predicted 111 at this point. 80 are currently projected. Ten new subscribers served in Q11 of award. Project was behind schedule early due to delay in getting agreements with DeKalb Fiber Optics. Total subscriber count reported in Q2 2012 was reported as 39 and should have been 40. That corrected total plus 10 additional CAI's listed in Section 9 is the current project total. | Baseline predicted 70 at this point. Project total is expected to be substantially fewer than baseline predicted. | Baseline predicted 41 at this point. Project total is expected to be substantially more than baseline predicted. | 42 @ 1 GB; 3 @ 50 MB to internet; 1@ 100Mb to internet; 1 dark fiber only and 3 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project will provide fiber backhaul for DeKalb County E-911 system and co-location in four telephone central offices. | FALSE | N/A | All duct and fiber will be installed and testing completed by the end of Q4-12. As-built documentation will be underway. Fiber back haul project for E-911 system will be complete. Negotiations for remaining last mile providers on the network will continue. Route change approved is expected which will allow for connection of the final community anchors and add 2.5 miles to the network total. Acquire independent appraisal for additional infrastructure being provided to project by DeKalb Fiber Optics, LLC. Phase 2 of independent verification of installed duct and fiber will be complete. Remaining 30 connections are expected to be completed and in service. All Community Anchor engineering will be complete, and all premise equipment will be installed and in operation. Remaining backbone node site in Sandwich telephone office will be in operation, completing backbone sites. 10 Gb ring equipment will be awarded, received, installed and paid by end of quarter. Firewalls for libraries will be received, installed and paid. | De Kalb, County of (Inc.) | The project activity increased in Q3-12 as additional right of way became available. Access to municipal rights-of way were received for Cortland, Sandwich, Somonauk and Malta during the quarter. In addition, the permit for installation on State Route 30 and the final private right of way access issue was resolved. Access to these areas allowed installation of duct and fiber in all the above areas with the exception of Somonauk and Malta, which will be constructed in October and November of 2012. Fiber is expected to reach the Sandwich telephone central office in October, allowing for the connection of the one remaining node sites and for the lighting of the connections in the south part of the project served by the Sandwich co-location site. | We wiil be submitting a substantial number of route changes in Q4-12. Timely processing of these requested changes will be important to assure that the project objective are met.
NT10BIX5570030 | 2012 | Q4 | Q4 - 2012 | All approved duct and fiber for the project was completed in 2012-Q4. Duct installed for the project is 113 miles. Fiber installed in Peace Road duct is an additional 13.53 miles. An additional 12 miles of fiber was purchased from Northern Illinois University making the total installed network as of the end of 2012 138.53 miles. Pending route changes, if approved will add an additional 4.5 miles to the total network. Completed all rights of way and municipal utility agreements needed for the project. Northern Illinois University Broadband Development Group continued engineering for community anchor institutions not yet connected to the network. Completed all railroad crossings needed for the project. Connected the approved community anchors in the Sandwich and Somonauk areas. Completed thirteen additional connections to the network this quarter making 61 total connections. Continued deployment of the E-911 fiber back haul equipment. Completed connection to the Sandwich telephone central office and racked and lit the backbone equipment there. Submitted one list of retroactive and one list of prospective route change requests. Employed 6.54 full time equivalent individuals in the construction and administration of the project in Q12 of award and includes the project contractor and subcontractors. | 126 | 12 | 0 | 0 | 126 | 0 | 0 | 291 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Q3-2012 PPR included "leased" miles in this number. Approved network was completed in December, 2012 (thirteen additional months from baseline). | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | N/A | N/A | Total approved for the project. | N/A | N/A | Baseline predicted 366 interconnection at the end of Q9 of award. Elimination of Knolls build reduced interconnection points by 8 to 358 (new baseline). Total reported here is total approved for the project. Additional interconnection points will be added if route changes are approved. | 2 | 3 | 14 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement. In Q3-12, DeKalb County signed an agreement with Syndeo Networks, Inc. to provide last mile services on the network. DeKalb County expects three additional last mile provider agreements by the end of the award period. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport to ISP: 100 Mb: $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 fibers for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 2 | 1 | 2 | None at this time. No providers with new access are anticipated. | DeKalb Fiber Optics, LLC and Syndeo Networks, Inc. We are in discussions with three additional providers and anticipate signed agreements in 2013-Q1. All would be receiving improved access. | DeKalb Fiber Optics, LLC. None of the providers with which we are negotiating agreements are expected to receive access to dark fiber. | All connections provided by DeKalb Fiber Optics are expected to be over a 1Gb interface. Syndeo Networks is offering speeds of up to 100Gbps to the internet. | 61 | 2 | 59 | 61 | Baseline predicted 111 at this point. 78 are currently projected. Thirteen new subscribers connected in 2012-Q4. Previous quarter connections were reported as 50, but now corrected to 48 to align with approved CAI total of 78, making the total now served 63. | Baseline predicted 70. Corrected from previously reported total of 6. Only 2 new connections are anticipated for project. | Baseline predicted 41. Project total is expected to be 76. | 47 @ 1Gb; 2 @ 50Mbps to the internet; 1 @ 100 Mbps to the internet; 2 dark fiber only, 4 are not lit and 5 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing fiber back haul for DeKalb County E-911 system and co-location in four telephone central offices. | FALSE | N/A | As-built documentation process will continue. Signed agreements with three last mile providers/ wholesalers will be completed. Complete phase 2 of independent verification of duct and fiber installation. Complete final community anchor equipment procurement. If route change approval is received, start work on final network infrastructure, weather permitting. | De Kalb, County of (Inc.) | Submitted one list of retroactive and one list of prospective route changes in December, 2012. Approval is needed in order to complete the project as originally intended. | The project has submitted a list of retroactive and a list of prospective route changes. Approval of these route changes is essential to completion of the project as intended.
NT10BIX5570030 | 2013 | Q1 | Q1 - 2013 | All approved build was complete in previous quarter. No additional build was completed in Q1-13. Credits received from DeKalb Fiber Optics LLC for laterals constructed to unapproved locations resulted in a reduction of 0.46 to total network miles. Approval of retroactive route changes late in this quarter resulted in adding 1.88 miles of duct and fiber contributed from DeKalb Fiber Optics (from Dresser and Wildflower to the DeKalb Frontier Central office) to network miles. Total network as of the end of Q1-13 is 139.95 miles. Pending prospective route changes will add an additional 3.16 miles of contributed and constructed network. Total project network is expected to be 143.11 miles. All required rights of way and municipal utility agreements have been acquired for the project. Northern Illinois University Broadband Development Group continues to provide engineering support for those Community Anchor Institutions not yet connected to the network. Approval of retroactive route changes late in the quarter allowed nine additional Community Anchors to be connected in the quarter. Total Community Anchors connected are 70 of an expected 78 total. All backbone equipment was lit in the previous quarter. Continued deployment of 911 fiber back haul equipment. Submitted to NTIA and received approval of budget modification. Submitted to NTIA and received approval of project completion extension to September 30, 2013. Employed 1.6 full time equivalent individuals, primarily in the administration of the project. | 127 | 12 | 0 | 0 | 130 | 0 | 0 | 300 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approved network was completed in December, 2012 (thirteen additional months from baseline). | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | N/A | N/A | Total approved for the project, including prospective route changes upon EA clearance. | N/A | N/A | Baseline predicted 366 interconnection at the end of Q9 of award. Elimination of Knolls build reduced interconnection points by 8 to 358 (revised target). Includes those added with approval of retroactive route changes. Total reported here is current total approved for the project. Additional interconnection points will be added if prospective route changes are approved | 2 | 3 | 14 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement. DeKalb County has an agreement with Syndeo Networks, Inc. to provide last mile services on the network. DeKalb County expects three additional last mile provider agreements by the end of the award period. Efforts to secure additional signed agreements include providing draft agreements to all three providers, responding to providers' concerns and questions and obtaining reviews of draft agreements from County staff and third party review. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month for best effort up to 1Gbps (averaging 300 Mbps). - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport to ISP: 100 Mb: $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 fibers for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 2 | 1 | 2 | None; No providers receiving new access are anticipated. | DeKalb Fiber Optics and Syndeo Networks, Inc. We are in discussion with three additional providers and anticipate signed agreements in 2013-Q3. All would be receiving improved access. | DeKalb Fiber Optics, Inc. None of the last mile providers with which we are negotiating agreements are expected to receive access to dark fiber. | All connections provide by DeKalb Fiber Optics are expected to be over a 1Gb interface. Syndeo is offering speeds of up to 100Gbps to the internet | 70 | 3 | 67 | 70 | Baseline predicted 111; 78 are currently projected. Nine new subscribers connected in Q1-13. | Russell Woods is receiving new service. No additional new connections are expected for the project. | Baseline predicted 41. Total projected for project is 75. | 49 @ 1Gb, 3@50Mb, 2@100MB, 5 dark fiber and 11 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing fiber backhaul for DeKalb County E-911 system and co-location in four telephone central offices. | FALSE | N/A | The route to one additional community anchor is approved and can be connected. The seven remaining CAI's are dependent on pending prospective route change approval. Build of remainder of network is also dependent on route change approval. If route change approval is received prior to the end of the quarter, some work can proceed in 2013-Q2 to build the additional 1.26 miles remaining and to acquire an additional 1.9 miles of duct and fiber from DeKalb Fiber Optics as an in-kind contribution to the project. However, it is doubtful we would also pay for that construction in Q2-2013 so we did not project those expenses in the financial projection for that quarter. Plan to complete all outstanding last mile agreements in Q2-13. | De Kalb, County of (Inc.) | Received approval of retroactive route changes late in 2013-Q3. Prospective route change request is pending, Approval is needed in order to complete the project as originally intended. | The project has submitted a list of prospective route changes. Approval of these route changes is essential to the completion of the project as intended.
NT10BIX5570030 | 2013 | Q2 | Q2 - 2013 | All approved build was completed in 2012-Q4. No additional build was completed in Q2-13. Environmental clearance of prospective route changes late in this quarter resulted in adding 1.88 miles of duct and fiber contributed from DeKalb Fiber Optics ("Islands" Fiber) to network miles. Total network as of the end of Q2-13 is 141.83 miles. Additional build authorized by prospective route changes will add an additional 1.27 miles of constructed network. Total project network is expected to be 143.11 miles. One prospective route change addition (Shabbona Library) will require a Illinois Department of Transportation permit. That permit was applied for immediately after notification that environmental clearance was received but the permit has not been issued as of the end of the quarter. Otherwise, all required rights of way and municipal utility agreements have been acquired for the project. Northern Illinois University Broadband Development Group continues to provide engineering support for those Community Anchor Institutions not yet connected to the network. Environmental clearance for prospective route changes late in the quarter allowed one additional Community Anchor to be connected in the quarter. Total Community Anchors connected are 71 of an expected 78 total. All backbone equipment was lit previously. Completed deployment of 911 fiber back haul equipment. Employed 1.38 full time equivalent individuals, primarily in the administration of the project. | 129 | 12 | 0 | 0 | 130 | 0 | 0 | 311 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approved network was completed in December, 2012 (thirteen additional months from baseline). | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | N/A | N/A | Total approved for the project, including prospective route changes upon EA clearance. | N/A | N/A | Baseline predicted 366 total interconnection points. Added 11 interconnection points in 2013-Q2 as a result of DeKalb Fiber Optics providing "islands" duct and fiber as an in-kind to the project. Total reported here is current number installed as of end of 2013-Q2 . Additional interconnection points will be added when prospective route changes are constructed. | 2 | 3 | 14 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement. DeKalb County has an agreement with Syndeo Networks, Inc. to provide last mile services on the network. DeKalb County expects three additional last mile provider agreements by the end of the award period. Efforts to secure additional signed agreements include providing draft agreements to all three providers, responding to providers' concerns and questions and obtaining reviews of draft agreements from County staff and third party review. All three expected agreements are in final stages of approval and are expected to be finalized early in 2013-Q3. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month for best effort up to 1Gbps (averaging 300 Mbps). - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport to ISP: 100 Mb: $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 fibers for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 1 | 1 | 2 | None; No providers receiving new access are anticipated. | Syndeo Networks, Inc. We are expecting three additional provider agreements to be completed 2013-Q3. All would be receiving improved access. | DeKalb Fiber Optics, LLC. None of the providers with which we are negotiating agreements are expected to receive access to dark fiber. | All connections provided by DeKalb Fiber Optics, LLC are expected to be over a 1Gb interface. Syndeo Networks, Inc. is offering speeds of up to 100Gbps to the internet. | 71 | 3 | 68 | 71 | Baseline predicted 111; 78 are currently projected. One new connection in 2013-Q2. | No additional new connections are expected for the project. | Baseline predicted 41. Total projected for the project is 75 | 49@ 1Gb; 4@50Mb; 2@100Mb; 5 dark fiber only and 11 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing fiber backhaul for DeKalb County E-911 system and co-location in four telephone central offices. | FALSE | N/A | Complete build of 1.27 network miles to serve seven remaining Community Anchor Institutions, test new fiber, deploy equipment and finalize those connections; finalize three remaining provider agreements. | De Kalb, County of (Inc.) | Received environmental clearance for prospective route changes late in 2013-Q2. This will allow us to complete the network as intended within budget and schedule parameters. | None are anticipated. We expect to complete all work on the network by the end of the next quarter.
NT10BIX5570030 | 2013 | Q3 | Q3 - 2013 | All approved build was completed in 2013-Q3 including prospective and retroactive route changes. Total network as of the end of Q3-13 (and project total) is 143.67 miles. Northern Illinois University Broadband Development Group completed engineering for Community Anchor Institutions that were connected to the network in the last quarter of the project. The seven remaining Community Anchors were connected in 2013-Q3 making 78 total for the project. All school districts in DeKalb County are connected to the network as well as one school district in LaSalle County and one school in Kane County. All backbone equipment was lit previously. The community anchors now have broadband speeds available at up to 1Gbps which, prior to the project, was not available to those community anchors located outside the DeKalb-Sycamore area. In addition, anchors are experiencing lower broadband costs because of increased competition brought about by availability of fiber connections to their individual locations and multiple providers on the DATA network. DeKalb County has contracted with five providers on the network, bringing increased competition and services to all anchors. Three of these last mile provider agreements were finalized in the last quarter of the award. Employed 0.78 full time equivalent individuals in the construction and administration of the project. At peak construction on the project, as many as 30 individuals were employed for construction, engineering, and administrative services. As the system is operated, individuals are employed for locating and maintenance, engineering, network operations, new connections and administration of the network. The project is a significant economic development asset for the county. Already 12 business, 3 cell phone carriers and one cable provider have connected to the system at speeds not formerly available in their locations. The county continues to market the network. The network map is being added to the county's GISWeb application which will make the details of the network available to everyone via the county's website. The DeKalb County Economic Development Corporation (DCEDC) aggressively promotes the county's fiber assets to prospective businesses through its presentations and meetings. With more than 400 potential interconnection points, additional connections are facilitated in all areas of the county. The county has designed the system to be financially self-sustaining with user fees paying for all operational and equipment replacement costs. The reliability of the system is supported by network operations center services provided by Northern Illinois University Network Operations Center that continually monitors the network for proper performance and also provides help desk services to the users. In addition, DeKalb Fiber Optics LLC provides locating, maintenance and relocation services for the network.The project worked closely with the county Emergency Services Telephone Board (E-911) to provide fiber backhaul connections to eleven tower and radio broadcast sites throughout the county, benefitting all emergency service providers. These fiber links provide better reliability at a lower cost compared to the copper backhaul links that were replaced. The project also linked the 911 dispatch centers in DeKalb County with the county public safety building. An interconnection with Lee County will facilitate disaster preparedness and enhanced E-911. The project is co-located at four telephone offices throughout the county, These co-locations provide DATA customers with access to providers on a regional level. These sites are also the locations for much of the backbone operation equipment, providing a high level of security, increased redundancy and motor generator backup. Finally, the project worked closely with the Northern Illinois University BTOP project (iFiber). Some of the benefits of this relationship are marketing of dark fiber routes through both projects and creation of a 10Gb redundant ring circling both projects. | 132 | 12 | 0 | 0 | 132 | 0 | 0 | 428 | Baseline predicted 130. The project was behind schedule early due to problems getting the indefeasible right to use and the locating, maintenance and repair agreements in place with DeKalb Fiber Optics, LLC. Approved network was completed in December, 2012 (thirteen additional months from baseline). | Acquired 12 strands over 12 miles from Northern Illinois University. Completes leased fiber in project. | N/A | N/A | Total for the project. Increase from previous quarter reflects additional build in Q3-13 and adjustment made due to correction to reflect final audited network constructed. | N/A | N/A | Baseline predicted 366 total interconnection points. Total reported here is total for the project. Differences from baseline projection resulted from some network build removed from project (Knolls, agricultural businesses, etc.), which decreased the total and additional interconnection points not anticipated in baseline such as additional contributed duct and fiber by DeKalb Fiber Optics LLC and the interconnection points acquired with the lease of 12 miles of fiber from Northern Illinois University. | 5 | 0 | 17 | DeKalb County has an agreement in place with DeKalb Fiber Optics for the construction, operation and economic expansion of the system. DeKalb Fiber Optics has one signed agreement with TBC Net. Recipient is not a party to this agreement. DeKalb County has agreements with Syndeo Networks, Inc., Illini Cloud, LLC, State of Illinois Department of Central Management Services (ICN) and Northern Illinois University (NIUNet) to provide last mile services on the network. | Provided by DeKalb Fiber Optics to Commercial Customers: - 100 Mb VLAN: $300/ month - 1 Gb VLAN: $600/ month - Wholesale Bandwidth: $20/ Mb/ Month - Consumer Access: $90/ Month for best effort up to 1Gbps (averaging 300 Mbps). - Dark Fiber: $750/ strand/ mile/ year Provided by DeKalb County to Community Anchors: Full participant: Dark Fiber, 1Gb transport to Illinois Century Network: $7,000/ location/ year Subscriber Services: Transport to ISP: 100 Mb: $2,800/ year; 50 Mb (shared): $1,050/ year | Fiber Physical Layer: DeKalb Fiber Optics, LLC, vendor, Dan Halverson, (dan@admin.tbc.net). DeKalb Fiber Optics is operating 68 fibers for economic development as well as providing locating, maintenance and repair functions for all 144 fibers being constructed. Electronics, network operations and community anchor engineering: Northern Illinois University, vendor, Herb Kuryliw, hkuryliw@niu.edu. | 0 | 4 | 1 | 5 | None; No providers receiving new access are anticipated. | Syndeo Networks, Inc., IlliniCloud, NIUNet and Illinois Century Network. | DeKalb Fiber Optics, LLC. | All connections provided by DeKalb Fiber Optics, LLC are expected to be over a 1Gb interface. Syndeo Networks, Inc. is offering speeds of up to 100Gbps to the internet. ICN offers a variety of services including bandwidth up to 1000 Mbs, NIU Net offers bandwidth in tiers as small as 100Mbs pooled to 1 Gbs dedicated. IlliniCloud provides a variety of cloud services primarily to school districts. | 78 | 3 | 75 | 78 | Baseline predicted 111; seven new connections in 2013-Q3. The actual number of community anchor institutions connected is less than the baseline for several reasons: 1) the baseline counted libraries in schools separately from the schools, 2) some facilities closed or relocated in the period from grant application to construction, 3) agricultural business connections were shifted from community anchors to being served by the fibers allocated to DeKalb Fiber Optics for economic development 4) 911 towers were removed from community anchor listing and 5) several locations were removed from the list of community anchors because the manner in which they were connected did not meet the NTIA connection definition. | Baseline predicted 70 with a predicted total of 111 CAI's. The approved number of CAI's was revised to 78. In the interim period after the grant metrics we submitted and the network was constructed, most of the CAI's for which "new" service was originally predicted were able to obtain broadband connections. | Baseline predicted 41. | 51@ 1Gb; 6@50Mb; 2@100Mb; 5 dark fiber only and 14 are not subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project is providing fiber backhaul for DeKalb County E-911 system and co-location in four telephone central offices. | FALSE | N/A | Project is complete. | De Kalb, County of (Inc.) | None | None.
NT10BIX5570031 | 2010 | Q3 | Q3 - 2010 | Expression of Interest (EOI) bid for engineering, technical validation, and overall grant compliance was approved through Purchasing. Design of NRAO/WVU connection is complete. The EA is nearly completed for the 12 Tower sites and is in progress for the MPLS poles and ditches. EA completion is on track for October 31, 2010. With NTIA assistance, we reviewed the Special Award Considerations (SAC) with plans to fully meet overall criteria. Routers have been ordered (>$22M) and shipment/delivery has begun. Approval from NTIA was obtained for pre-FONSI purchase of tower build material to include: tower steel, buildings, and generators. We have hired three employees for the project: 1. Engineering Project Manager - professional project management: responsible for the general engineering, planning, execution, and closing of this grant project; 2. Engineer - Lead Engineer for tower design, development, and installation for the 12 towers, broadband and microwave associated with this grant; 3. Administrative Assistant - Administrative Support (reports, letters, power points, graphs, tracking),coordination, monitoring and accounting for all grant related processes. These positions are essential to completion of the grant project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A | - | - | - | N/A | - | - | 0 | 0 | 0 | Frontier Communications - middle and last mile services (Memorandum of Understanding) | Currently wholesale services will be provided by Frontier Communications. These services are outlined in the attached pricing schedule (MPLS Pricing.pdf). We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) WV Dept. of Health & Human Resources (WVDHHR) / 304-581-2900 (Tower portion w/ WVOT) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Not available until install begins | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Speed will be indicated and calculated as actual installation begins. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Speed will be indicated and calculated as actual installation begins. | Until project fully begins (4th quarter) there will be no special offerings provided. | FALSE | N/A | EA will be completed; tower build can begin; router programming, fiber build and install can begin; full kick off of project. | Executive Office State of West Virginia | The single most problematic area remains that of the completion of the Environmental Assessment. BTOP/NTIA is diligently working with us to correct this deficiency. We expect completion by the end of October 2010. | None seen at this time. Completion of EA will allow project to fully kick off.
NT10BIX5570031 | 2010 | Q4 | Q4 - 2010 | The Environmental Assessment for the Multi-protocol Label Switching (MPLS) poles and ditches, and 12 towers was sent to NTIA on November 1, 2010. Design of National Radio Astronomy Observatory-West Virginia University connection is complete. We await the Findings of No Significance (FONSI). The routers have been shipped and received; tower build materials (tower steel, buildings, and generators) have been ordered. We continue to foster the overall relationship with Frontier Communications as a sub-recipient on the grant, having weekly meetings. Also, network design, especially the tower piece, is rapidly coming to full fruition, having bench marked and tested many of the applications. Sufficient design, engineering and coordination meetings with tower vendors, Frontier, and stakeholders continue. Tower steel, building, and generators are ordered and will be shipped when WV gives the vendors the "go" for delivery. The working teams remain poised and ready to begin construction upon receipt of the FONSI. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting FONSI for project kick-off/construction to begin. | N/A | Awaiting FONSI for project kick-off/construction to begin. | N/A | Awaiting FONSI for project kick-off/construction to begin. | Awaiting FONSI for project kick-off/construction to begin. | Awaiting FONSI for project kick-off/construction to begin. | Awaiting FONSI for project kick-off/construction to begin. | 1 | 6 | 0 | Frontier Communications, Sub-recipient - middle and last mile services (Memorandum of Understanding) | Currently wholesale services will be provided by Frontier Communications, Grant Sub-recipient. These services are outlined in the pricing schedule (MPLS Pricing.pdf attached). We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase. WV Dept. of Health & Human Resources (WVDHHR) / 304-581-2900 (Tower portion w/ WVOT) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct. | 0 | 0 | 0 | 0 | Awaiting FONSI for project kick-off/construction to begin. | Awaiting FONSI for project kick-off/construction to begin. | N/A | Not available until install begins. | 0 | 0 | 0 | 0 | Connection with all Community Anchor Institutions can begin upon receipt of FONSI | Connection with all Community Anchor Institutions can begin upon receipt of FONSI | Connection with all Community Anchor Institutions can begin upon receipt of FONSI | Speed will be indicated and calculated as actual installation begins. Awaiting receipt of FONSI | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Until receipt of the Findings of No Significant Impact, and the project fully begins, there will be no special offerings provided. | FALSE | N/A | Primary accomplishment expected for next quarter is the award of the Finding of No Significant Impact (FONSI). After receipt of the FONSI, we will begin construction of towers, installation of CISCO routers, fiber build out, and associated tasks related to this grant. Full construction kick-off of the project will begin. The WV Dept. of Health and Human Services tower project lead (tower portion) clearly articulates that his team is poised and ready to commence construction immediately upon receipt of FONSI. Further, all critical areas as noted in the Environmental Assessment are resolved, meaning an immediate start up is pending. Equipment and materials (steel, buildings, generators, antennae, etc.) are ordered, some of which are ready for immediate shipment. Concept testing has been completed with full validation proven. Routers are at Community Anchor store houses. | Executive Office State of West Virginia | The single most problematic area remains that of the Environmental Assessment. The Environmental Assessment was submitted to the NTIA on November 1, 2010. We are awaiting the Finding of No Significant Impact (FONSI). The issue with FONSI completion centered on a lack of the grant recipient providing to US Fish & Wildlife sufficient detailed drawings for issue of a general letter to generate the FONSI. The working teams remain poised and ready to begin construction upon receipt of the FONSI. NTIA is working diligently with the West Virginia Grant Implementation Team to correct any deficiencies of the report. | Weather may be a deterrent during the next quarter, however, as winter passes, this threat will diminish. After receipt of FONSI (upcoming quarter), construction will begin. A potential medium-level issue may result from our sub-recipient being overwhelmed by the magnitude of immediate construction. We do not expect to request any "unique" technical assistance from the BTOP program.
NT10BIX5570031 | 2011 | Q1 | Q1 - 2011 | During this reporting period the WV BTOP grant received the Finding of No Significant Impact (FONSI), effectively, within the scope of the environmental programmatic agreement, commencing the construction phase of the grant. Lewis County is now a sub-recipient, providing through an existing, grant compliant contract, services to construct towers and antennae on related towers. National Telecommunications and Information Administration (NTIA) completed an on-site review of the WV Grant processes. Specifications were completed for the routers directly associated with the National Radio Astronomy Observatory (NRAO) and West Virginia University fiber connections. A special meeting with Frontier Communications reviewed the Special Award Conditions (SAC), sub-grant roles and responsibilities, and reporting requirements related to the grant. Inventory and accountability was completed for all routers. The Governorâ€™s Executive appointed a communications, publicity, and outreach coordinator for actions relating to the grant. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule for the upcoming quarter. | N/A | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule for the upcoming quarter. | N/A | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule for the upcoming quarter. | N/A | Tower construction approval forms signed 03/11/2011. Two of 12 towers have site construction ongoing. | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule for the upcoming quarter. | 0 | 6 | 0 | N/A | Frontier Communications, Sub-recipient. No additional service providers at this point. We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase; WV Dept. of Health & Human Resources (WVDHHR-OEMS) / 304-581-2900 (Tower portion) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct; Lewis County Commission,Grant Sub-recipient / 304-269-8200 (Tower construction portion w/ DHHR-OEMS). | 0 | 0 | 0 | 0 | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule within the next two quarters. | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule within the next two quarters. | N/A - Baseline did not indicate this category | FONSI received March 10, 2011 with programmatic agreement issues being worked out. We will be on schedule within the next two quarters. | 0 | 0 | 0 | 0 | Due to lack of approved FONSI and PA until the end of this quarter, construction is just commencing. We will be on schedule within the next two quarters. | Due to lack of approved FONSI and PA until the end of this quarter, construction is just commencing. We will be on schedule within the next two quarters. | Due to lack of approved FONSI and PA until the end of this quarter, construction is just commencing. We will be on schedule within the next two quarters. | <10 meg = 175 10 meg - 50 meg = 475 >50 meg = 414 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | As construction is completed, special offerings will be provided. | FALSE | N/A | The second quarter of 2011 will have significant increases directly related to construction â€“ especially the twelve (12) towers. A minimum of six of the twelve will be in the construction phase by the end of June 2011. Further, using Lewis County as a sub-recipient effectively facilitated a vendor to begin installation of antennae on existing and new towers (as completed). During the 2nd quarter over 60 antennae will be installed. The routers for community anchor institutes will have commenced and most, if not all of the routers, not requiring new fiber will be programmed and installed. Engineering and programmatic agreement requirements will be met for the National Radio Astronomy Observatory (NRAO) to West Virginia University (WVU) link and some construction will have started on that leg of the grant. | Executive Office State of West Virginia | Award of the Finding of No Significant Impact (FONSI) presented some unique problems as we started construction start-up of the project. For instance, the programmatic agreement (PA) specified certain actions necessary for WV to complete to be in compliance with environmental stipulations. It has been difficult to fully ascertain exactly the detail required by the state agencies to work/satisfy the programmatic agreement. The Special Award Conditions (SAC) caused a medium level of challenge, specifically determination if Davis Bacon applied and to what level to sub contractors of grant sub-recipient. Technical advice from BTOP was instrumental in solving this problem; however, we feel as if Technical assistance will continue to be required in the SAC area. Resolution of overlap due to other BTOP or federal grants was difficult to resolve in that full visibility of overlap locations has been difficult. That said, the NTIA program manager and his staff assigned to WV has been especially instrumental in resolution of this challenge. We processed a draw down request in the amount of $13,415.25 which did not show in NTIA system as 1st quarter expenditure. As verified by the Fiscal Officer-Governor's Executive Office, this draw down was completed before close of business 03/31/2011, therefore we included this amount in our Overall Project percentage for this quarter. | The next quarter will be the most productive quarter since inception of the grant award. The overall twelve (12) tower build-out will be in full swing with associated microwave antennae being installed. The most significant challenge directly relating to this portion of the grant centers would be for the spring to continue to be extra rainy. While not directly stopping construction, it could be hampered if this condition were to persist. The Community Anchor Institutes will have received most, if not all, of their routers. A challenge to this portion of the grant would be the magnitude of routers to install. This challenge will be mitigated by programmed/scheduled router deployments and cross efforts of installers. The National Radio Astronomy Observatory (NRAO) to West Virginia University (WVU) link (portion) of the grant will be fully engineered. The greatest challenge to the initiation of construction on this link would be the sub-recipient having the majority of construction assets assigned on different portions. Mitigation is to keep the sub-recipient advised as to construction process. During the next quarter, we will be hiring one (1) accountant to assist with the project. NTIA may be asked to assist in the overall train-up of this individual to meet NTIA requirements. Also, the administrative assistant assigned to this grant is retiring in May 2011. As we chose a replacement, we will likely need NTIA technical assistance to train this individual.
NT10BIX5570031 | 2011 | Q2 | Q2 - 2011 | During this reporting period the WV BTOP grant accomplished the following critical elements: â€¢ Tower construction is fully engaged through a sub-grant with Lewis County. Radios (approximately $19 mil) were ordered. â€¢ Community Anchor Institute (CAI) has 6 miles new fiber in place. â€¢ K1-K12 schools installed approximately 90 new routers. â€¢ Frontier Communications (sub-recipient) established interconnect processes. â€¢ Engineering for the National Radio Astronomy Observatory (NRAO) is in progress with early expectations that the cost estimate will be less than previously expected. â€¢ Completed coordination regarding overlap with Hardy County. â€¢ Engaged Seneca telecommunications to resolve overlap with their BIP grant. | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 20 | After completion and receipt of the Finding of No Significant Impact (FONSI), and subsequent programmatic agreement, Frontier Communications (sub-recipient) immediately began the process of fiber construction. As regions and counties received the go-ahead for construction, Frontier was primed and ready to go. Simultaneously, fiber realized a world-wide shortage. This shortage had a direct and immediate impact on our construction schedules. Although an alternate fiber vendor has been identified and ordered, we remain about seven weeks behind schedule. By calendar year end significant closure on baseline numbers should result. | N/A | N/A | N/A | After completion and receipt of the Finding of No Significant Impact (FONSI), and subsequent programmatic agreement, Frontier Communications (sub-recipient) immediately began the process of fiber construction. As regions and counties received the go-ahead for construction, Frontier was primed and ready to go. Simultaneously, fiber realized a world-wide shortage. This shortage had a direct and immediate impact on our construction schedules. Although an alternate fiber vendor has been identified and ordered, we remain about seven weeks behind schedule. By calendar year end significant closure on baseline numbers should result. (Same as network miles deployed.) | N/A | The baseline indicates that we would have five towers complete, but an abnormally wet spring delayed construction of the towers. However, a dry summer, an aggressive sub-contractor and related vendor, and strong leadership clearly indicate that we should be ahead of schedule by Fiscal Year End. | Proportionally as areas of â€œnew network miles deployedâ€ and â€œnumber of miles new fiberâ€ improve (see information in related areas) this number will increase to meet baseline | 0 | 6 | 0 | N/A | Frontier Communications, Sub-recipient. No additional service providers at this point. We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase; WV Dept. of Health & Human Resources (WVDHHR-OEMS) / 304-581-2900 (Tower portion) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct; Lewis County Commission,Grant Sub-recipient / 304-269-8200 (Tower construction portion w/ DHHR-OEMS). | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 98 | 8 | 90 | 0 | As construction continues and we move to meet schedule, the total new subscribers will increase to baseline. | 167 sites were visited or engineered. 8 sites were completed to the DMARC. 60 sites were red-lined. 15 sites have fiber on the pole awaiting access to building. The rest are either improved or awaiting EA. | This number is mostly resultant from installation of routers for sites having existing fiber. During the upcoming quarter this number will increase. | <10 meg = 175 10 meg - 50 meg = 475 >50 meg = 414 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | As construction is completed, special offerings will be provided. | FALSE | N/A | The third quarter of 2011 will illustrate dynamic and positive adjustments to actual vs. baseline reporting. Due to current extremely good weather, receipt of radios, and strong efforts, the tower portion of the project will move to either on or slightly ahead of schedule. Further, as Frontier Communications receives fiber from the new vendor, miles of fiber constructed will increase. As the National Radio Astronomy Observatory to WVU link is engineered, we will begin fiber build of the separate portions of the various legs of that construct. The routers identified for improved services will be mostly installed and functional. Tower radios will be received, tested, and paid resultant in a one -time invoice of approximately $19 million. | Executive Office State of West Virginia | Although we identified an alternate vendor for fiber (mostly for the community anchor and National Radio Astronomy Observatory to West Virginia University) build outs, the result has not been proven. Should the new vendor fail to meet promised deliveries, overall slowdowns to the project could result. Frontier agreed to hire additional employees and commence over time authorizations as a mechanism to reduce the fiber construction gap. Should this effort fail, it could seriously hamper the overall project. | At this time, the single biggest challenge is to overcome the delays promulgated by the world-wide fiber shortage. The mitigation (alternate vendor) has been executed and we are on mark to fix the issue; however, with the magnitude of community anchors to install, the improvement is slow. Another challenge lies in the area of special construction. Frontier Communications and our community anchor representatives are working methodology to ease the timing of the actual special construction, we must make this a smooth and seamless process. The mitigation is an aggressive approach to both Frontier and community anchor representatives. A wet late summer and/or early fall could delay the installation of the National Radio Astronomy Observatory to West Virginia University connectivity. To ensure compliance with all special award conditions, sub-recipient guidance, and audit requirements, we are placing a contract employee with singular responsibility in these areas.
NT10BIX5570031 | 2011 | Q3 | Q3 - 2011 | During this quarter five (5) towers were fully constructed. The microwave radios completed vendor, field, and engineering testing for compliance and compatibility and the first of four shipments of radios were received in West Virginia. A total of twenty nine (29) miles of new fiber was constructed by our sub-recipient, Frontier Communications. One hundred forty seven routers were installed. Due to delays in construction due to cable shortage and other critical factors, Frontier Communications worked on and submitted a mitigation plan to begin the process of meeting the overall grant criteria. A high level stakeholder summit was held at Stonewall Jackson Resort that presented the overall grant progress, shortfalls, and processes to move ahead into the future. The NTIA Program Officer attended and presented NTIA processes to the overall audience. Four of the WV noted fiber regions have been engineered with three of the four West Virginia University to National Radio Astronomy Observatory engineered. | 29 | 0 | 0 | 0 | 29 | 0 | 5 | 21 | The sub-recipient, Frontier Communications, due to fiber shortages and slowness of startup remain behind on overall miles deployed. As the proposed mitigation plan comes to fruition, this will increase to meet overall guidance. | The project will not lease any fiber. | N/A | N/A | New, pending Frontier mitigation plan should resolve these deficiencies in the upcoming quarter. | The wireless links for the towers should be ready to be installed in the 4th QTR. | Five Forks, Spencer, Cleveland MTN, Greenbrier, Long Ridge. | We have one interconnect point in progress. As this agreement closes, it will serve as the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 0 | 7 | 0 | Frontier Communications remains in negotiation with CityNet regarding an interconnection request for the Bridgeport Public Library. This interconnect agreement will serve as the model for all future WV BTOP interconnect agreements. | Frontier Communications, Sub-recipient. No additional service providers at this point. We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase; WV Dept. of Health & Human Resources (WVDHHR-OEMS) / 304-581-2900 (Tower portion) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct; Lewis County Commission,Grant Sub-recipient / 304-269-8200 (Tower construction portion w/ DHHR-OEMS). | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 241 | 20 | 221 | 0 | As noted within the confines of this report, Frontier Communications remains behind in the fiber portion of the overall project. In concert with the State of West Virginia, Frontier developed a mitigation plan that will serve to achieve overall baseline. We added 143 this quarter. | As noted within the confines of this report, Frontier Communications remains behind in the fiber portion of the overall project. In concert with the State of West Virginia, Frontier developed a mitigation plan that will serve to achieve overall baseline. Further, last week, the State of West Virginia resolved a purchasing and contracting issues that resolves methodology for build out costs which will expedite the overall process. We added 12 this quarter. | This number is indicative of the routers installed to date. During a recent stakeholders meeting, we feel certain as if most of the community anchors receiving improved service by installation of a new router will be complete during the next quarter. We added 131 this quarter. | <10meg =175 10meg-50meg=475 >50meg=414 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | The next quarter will serve to begin and complete several critical aspects of the grant. The West Virginia University to National Radio Astronomy Observatory link construction will begin and the first grouping (about 50) microwave radios will be installed and tested. Further all engineering of fiber connected Community Anchor Institutions (CAIs) will be fully complete and Frontier will begin to meet expectations as noted on the overall mitigation plan. We will begin the process of validation of fiber, radios, and other crucial aspects of the installation. All remaining microwave radios will be delivered and ready for installation and all towers will be fully constructed. Total new miles next quarter should be 103 with a cumulative total of 153 per mitigation plan. Total CAI's served (connected) next quarter should be 123 with a cumulative total of 143 per mitigation plan. We do not expect to have any new signed agreements with wholesalers or last mile providers next quarter. | Executive Office State of West Virginia | The primary concern during this quarter was a slowness of construction on the fiber portion of the overall grant. This was caused by a shortage of fiber and a delay in overall start-up of construction. During the quarter a draft mitigation plan was developed. NTIA and their contractors worked with the State of West Virginia and Frontier communications in development and approval of this plan. A revised plan should be sent to NTIA by 1 Nov ember 2011. The microwave radios proved to be a somewhat problematic as to overall functionality. The WV team met with radio manufactures and engineers to resolve the problem. Although the radio functionality has been satisfactorily resolved, we will need continuing assistance from NTIA to work the mitigation plan for fiber construction. For clarification on page 12 of this report a number was changed due to an internal audit with an house Accountant. In Site Work our number was $412,367, this number was changed to $0. | To date, weather has not been a negative factor with tower, radio, microwave, or antennae installation. Neither has it been detrimental to the overall fiber build out. However, as we move into the more severe winter months, weather could cause delays in the overall project. We believe that West Virginia is poised to minimize any weather impacts. Another challenge is Frontier Communicationâ€™s ability to meet the programmed mitigation plan. Both NTIA and the West Virginia team will, on a daily basis, receive sufficient information to immediately identify and real or perceived shortfall to the construction process. There remains a possibility of some funding remaining after completion of the grant. We started the process and will complete a revised budget to NTIA as revised forecasts and budgets are complete. We will work with NTIA on the revised budget and planning for processes to comply with NTIA guidance, including a revised budget.
NT10BIX5570031 | 2011 | Q4 | Q4 - 2011 | During this quarter we completed installation of five (5) towers for a total of (9) towers complete. Approximately Â½ of the microwave radios completed vendor, field, and engineering testing for compliance and compatibility with two of the four shipments received in West Virginia. The State of West Virginia, specifically Frontier Communications, completed a full mitigation plan that was subsequently approved by NTIA. Frontier was on track to meet mitigation plan stated goals. This improvement was a direct result of improved fiber availability, emphasis by the Grant Implementation Team, and push by Frontier Communications. A total of 327 miles fiber construction has been engineered and approved to build. A total of 127 miles of fiber has been constructed. Ten (10) Community Anchor Institutes had Facilities build out scheduled. Engineering for 606 Community Anchor Institutes has been submitted with engineering approved for 420 of these Anchors. We conducted a Community Anchor Institute stakeholderâ€™s planning meeting in Charleston. | 127 | 0 | 0 | 0 | 127 | 0 | 9 | 21 | The original number of Community Anchor Institute locations and subsequent miles was originally 1,062 locations and 900 miles. These numbers decreased dramatically. The current Community Anchor fiber build out list is at 653 locations with an approximate total mileage for the middle mile portion of 590 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. | N/A | N/A | N/A | The original number of Community Anchor Institute locations and subsequent miles was originally 1,062 locations and 900 miles. These numbers decreased dramatically. For instance, eighty eight (88) Community Anchors were determined to have existing fiber prior to BTOP and have been removed from the list of 1063 leaving 974 Community Anchors for fiber build out. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. The current Community Anchor build list coupled with the National Radio Astronomy Observatory to Greenbank build is at 571 miles. | N/A | We have nine (9) new towers complete. The remaining three towers are very near complete. This number will move to 100%next quarter. | We have one interconnect point in progress. As this agreement closes, it becomes the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 0 | 7 | 0 | Frontier Communications remains in negotiation with CityNet regarding an interconnection request for the Bridgeport Public Library. This interconnect agreement will serve as the model for all future WV BTOP interconnect agreements. | Frontier Communications, Sub-recipient. No additional service providers at this point. We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase; WV Dept. of Health & Human Resources (WVDHHR-OEMS) / 304-581-2900 (Tower portion) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct; Lewis County Commission,Grant Sub-recipient / 304-269-8200 (Tower construction portion w/ DHHR-OEMS). | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 254 | 47 | 207 | 0 | ** CORRECTION previously reported inaccurate data. Please see below for ENTIRE listing of all sites completed. | 4th QTR = 27 sites were completed receiving fiber to the DMARC and router. ** CORRECTION previously reported inaccurate data. Please see below for ENTIRE listing of all sites completed. | 4th QTR = 92 sites received router only. ** CORRECTION previously reported inaccurate data. Please see below for ENTIRE listing of all sites completed. | <10meg =173 10meg-50meg=475 >50meg=414 DARK FIBER | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | The upcoming quarter will serve to provide and complete several critical aspects of the grant. The construction of West Virginia University to National Radio Astronomy Observatory link will continue with further installation of the four defined links. Frontier Communications should continue to meet and possibly exceed expectations as defined on the overall mitigation plan. We identified five existing radio towers that are either at or exceed capacity as we install the BTOP radios and antennae causing a need for replacement towers. After NTIA coordination and approval, we expect to begin the process of removal of old towers and installation of new towers. Validation of fiber, radios, and other crucial aspects of the installation continues. Fiber build out continues throughout the quarter. Total new miles next quarter should be 155 with a cumulative total of 282 per mitigation plan. Total CAIâ€™s served (FIBER CONNECTED TO DMARC) next quarter should be 75 with a cumulative total of 113 per mitigation plan. We do not expect to have any new signed agreements with wholesalers or last mile providers next quarter. | Executive Office State of West Virginia | As with previous quarters, the single primary challenge during the past quarter was a slowness of construction on the fiber portion of the overall grant. The overall State of WV (Frontier focused) mitigation plan will serve to minimize this impact during future quarters. NTIA approved the plan and Frontier Communications is ahead of mitigation plan goals. We lost several individuals directly involved with grant execution such as within the confines of DHHR and Office of Technology. These individuals were essential to the administrative processing of grant related data. At DHHR we approved a contract individual to absorb a portion of these requirements until such time as a full time replacement can be hired. At the Governorâ€™s Office of Technology, a replacement was hired and is being trained. During this quarter, we completed a Fair Market Value (FMV) assessment of the existing 95 towers to be used for wireless broadband. After that FMV, a structural analysis was necessary to ascertain if the towers would support the additional weight associated with microwave antennae and equipment. Five (5) of the related towers failed this test causing a problem. We are working with NTIA to develop methodology to replace these five towers. The environmental assessment has commenced and we are developing the necessary FCC criteria for this effort. Most likely this initiative will reach out to the close of the grant. | As noted in the last report, weather has not been a negative factor with either the tower, the fiber, or antenna installation and it has not been detrimental to the overall fiber build out. However, January, February, and early March are typically the more severe winter months, which could cause delays in the overall fiber build out. To minimize this potential impact, Frontier Communicationâ€™s mitigation plan provides sufficient â€œgap recoveryâ€ time in the last several months of build out. Although Frontier Communications is progressing ahead of mitigation plan projections, there remains a possibility of a â€œshortfallâ€ in this area. By continual weekly and monthly monitoring, WV would recognize possible problems early and through increased vigilance and coordination cause the shortfalls to be minimized. Fiber build out continues to be the biggest threat to advancement of the total Community Anchor Institutes (CAI) installed; however, Frontier Communications and the Governorâ€™s Office of Technology remains poised to bring on additional sub contractors to mitigate this potential shortfall. To mitigate excess funding at the end of the grant, we are developing multiple financial progress charts. We continue to work with NTIA on revising the overall budget and planning for processes to comply with NTIA guidance, including the revised budget.
NT10BIX5570031 | 2012 | Q1 | Q1 - 2012 | Through March 31, 2012 nine (9) of twelve (12) towers are constructed. In the wireless network, 35 radios and 29 antennaeâ€™s were installed. We submitted to NTIA the proposed initiative to replace five (5) towers noted as having structural issues. Approximately 60% of the total radios have been factory tested and delivered to the project. Representatives of the Grant Implementation Team (GIT) continued providing community outreach by attending and presenting BTOP progress and opportunities at bi-monthly K12 Board of Education meetings. Further, members of the GIT met with representatives of the separate major community anchor institutes, briefed Governorâ€™s Executive Office staff and enhanced our web page presentations. A-133 audits for both sub-recipients (Frontier Communications and Lewis County Commission) were completed and under review by the GIT. This team also met with the wireless project team to discuss compliance progress. Frontier Communications energetically is working to ensure that they satisfy terms associated with the NTIA approved mitigation plan. To date, due to Frontier efforts, good weather, and dynamic leadership, they (Frontier) continue to outpace their planning and subsequent mitigation schedule. During this quarter 205 subscribers were completed and a total of 118 miles of fiber was completed for the quarter for a total of 245 miles totally complete. The final factory testing of microwave radios is beginning. After this testing is complete, we will receive the last phased microwave radio shipment. Radios received to date are in the process of being installed and field tested. After factory testing, shipment, inventory, installation, and final testing these radios serve to enable broad band across the entire wireless network. During this quarter 106 jobs were created directly attributable to the BTOP grant. | 245 | 0 | 0 | 0 | 245 | 29 | 9 | 21 | The total of 245 miles of new fiber directly correlates with the Frontier mitigation plan (Frontierâ€™s construction progress exceeds the miles as noted in the approved mitigation plan). Based on construction progress and Frontierâ€™s continued construction progress, we will have be at 100% fiber miles constructed by end of the grant. | N/A | N/A | N/A | The total of 245 miles of new fiber directly correlates with the Frontier mitigation plan (Frontierâ€™s construction progress exceeds the miles as noted in the approved mitigation plan). Based on construction progress and Frontierâ€™s continued construction progress, we will have be at 100% fiber miles constructed by end of the grant. | Twenty nine total towers have radios and antennas installed awaiting final testing. Testing should be completed during Q4 2012. | Nine new towers are completed with erection of steel. The majority are awaiting radio and antenna installs. | We have one interconnect point in progress. As this agreement closes, it becomes the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 0 | 1 | 0 | Frontier Communications remains in negotiation with CityNet regarding an interconnection request for the Bridgeport Public Library. This interconnect agreement will serve as the model for all future WV BTOP interconnect agreements. The last report indicated 7 ongoing negotiations. While there are up to 10 agreements being talked about, none have been reduced to writing. As these talks move to more formal processes, we will change the number of agreements being currently negotiated to reflect. | Frontier Communications, Sub-recipient. No additional service providers at this point. We expect additional wholesale services during the course of the project. | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); WV Office of Technology (WVOT) / 304-558-8145 (Partial of MPLS network, connectivity with towers) - Serves within the confines of a MOU as partner and contractor facilitating grant implementation, especially with design, engineering, and router purchase; WV Dept. of Health & Human Resources (WVDHHR-OEMS) / 304-581-2900 (Tower portion) - Serves within the confines of a MOU as a partner and contractor facilitating grant implementation, especially with the overall tower portion of the construct; Lewis County Commission,Grant Sub-recipient / 304-269-8200 (Tower construction portion w/ DHHR-OEMS). | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 459 | 205 | 254 | 0 | There have been 205 CAI's receiving new and/or improved service. Per Frontier Mitigation plan we will be current with the baseline as of quarter 4 2012. | There have been 158 CAI's receiving fiber to the DMARC. | There have been 47 CAI's receiving router only. | <10meg =173 10meg-50meg=475 >50meg=414 DARK FIBER | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | During 2nd quarter 2012, we should order tower steel and commence construction on the five (5) replacement tower sites (due to capacity issues - Hargreave, Limestone, North Mountain, Montgomery Hill, and Mt. Storm). Further, all tower construction should be nearing completion by the end of the quarter. The last proof of concept for microwave radios and subsequent delivery will also occur during this quarter. All known changes to Community Anchor Institutes should be finalized, mitigation plan adjusted, and submitted to NTIA for final approval. Frontier Communications will continue construction effectively ensuring full compliance with the current approved mitigation schedule/plan. The National Radio Astronomy Observatory to West Virginia University link will begin full construction enabling completion by end of the calendar year. Internal formalized compliance processes will be implemented and full compliance reviews will be ongoing. Specifically, a minimum of 10% of Community Anchors and towers will have environmental compliance reviewed by contract. A performance improvement plan necessitated by A-133 audits will be reviewed by our internal compliance team. Equipment for the WVNet initiative will be ordered and received with actual installation commencing. Total new miles fiber next quarter should be 155 miles with a cumulative total of approximately 400 miles. Total Community Anchors Served (Fiber connected to DMARC) next quarter should be ahead of mitigation plans. We do not expect to have any new signed agreements with wholesalers or last mile providers next quarter. | Executive Office State of West Virginia | We anticipated significant issues with fiber build out at the community anchors. However, the contractors chosen by Frontier for fiber build out performed above expectations, mitigating expected issues within this area. Winter was unusually mild with an early spring enabling progress to continue ahead of schedule. Frontier continues to be behind projections as depicted on the overall project baseline; they (Frontier) astutely continue to progress ahead of schedule as noted on the mitigation plan. | A surfacing challenge this quarter is the fact we are nearing the end of the grant. Commensurate with this fact is an inherent â€œpushâ€ to meet goals and objectives. We will mitigate this challenge by strengthening compliance reviews and audits. Another challenge will be the reconciliation of existing community anchors by adjusted and administrative changes, additions, or deletions to NTIA for final approval. This challenge will be mitigated by a thorough review with the stakeholders, Frontier Communications, and NTIA. As we near the completion of the grant, we need to accurately determine any possible remaining funds available for the project. The mitigation for this challenge: a dynamic review of existing expenditures, projections of costs, and invoices. The five replacement towers could represent a challenge. It remains imperative that we coordinate smoothly and efficiently with NTIA for approval. Steel for these towers has a five to eight week deliverable time lag. Mitigation is in progress with weekly coordination and administrative submissions to NTIA.
NT10BIX5570031 | 2012 | Q2 | Q2 - 2012 | Through June 30, 2012, nine (9) towers are constructed. In the wireless network, 378 radios and 314 antenna were installed. We wait for environmental approval to begin construction on the five (5) replacement towers that were noted as having structural issues. This quarter we received the balance of the microwave radios for the project. We commenced the inventory, installation, and testing of the radios to enable broadband across the entire wireless network. Representatives of the Grant Implementation Team (GIT) continued community outreach by attending and presenting BTOP progress and opportunities at bi-monthly K12 Board of Education meetings, County Commission and Planning Council meetings. We continued to meet with representatives of the separate major community anchor institutes, briefed the Governorâ€™s Executive Office staff, and enhanced our web page presentations. Sub-recipient Frontier Communications continues to pace ahead of their approved mitigation plan. During this quarter, we completed 126 new and 15 improved Community Anchor constructions. Six sites were previously not reported in quarter 1, two of which were new service and 4 were improved service. A total of 154 miles of fiber was completed for the quarter for a total of 399 miles complete. We submitted to NTIA and had approved a project for â€œWVNETâ€. During the quarter we ordered approximately $3.5M of equipment for this project. As reported by Frontier Communications, Premier Construction, WV Military Authority, The Office of Technology, and Department of Health and Human Resources, during this quarter, 131 jobs were created directly attributable to the BTOP grant. | 399 | 0 | 0 | 0 | 399 | 356 | 9 | 21 | The numbers of Community Anchor Institution locations and subsequent miles were originally 1,064 locations and approximately 900 miles. Existing infrastructure, route changes, and other factors caused these numbers to decrease. The current Community Anchor fiber build out list is at 641 locations with an approximate total mileage of 567. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. | N/A | N/A | N/A | The numbers of Community Anchor Institution locations and subsequent miles were originally 1,064 locations and approximately 900 miles. Existing infrastructure, route changes, and other factors caused these numbers to decrease. The current Community Anchor fiber build out list is at 641 locations with an approximate total mileage of 567. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. | Radios Installed: 378 Antennae Installed:314 | Nine new towers are completed with construction of towers. The majority are awaiting radio and antenna installs. The remaining three towers are scheduled to be completed this upcoming quarter. | We have one interconnect point in progress. As this agreement closes, it becomes the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 1 | 0 | 40 | Frontier Communications has entered into a signed final agreement with CityNet regarding an interconnection to the Bridgeport Public Library. All applicable documents have been signed, but CityNet has yet to execute on the financial terms of the agreement. | Although CityNet has yet to execute on the financial terms of the agreement, it is our understanding that the type of Wholesale services they intend to provide are a TLS (transparent LAN service) Ethernet type product. The pricing for this agreement is listed below. Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered To Be Determined TOTAL Charges $0 To Be Determined (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 606 | 333 | 273 | 0 | Frontier Communications mitigation plan will cause WV to meet overall grant requirements by the end of year three. The WV Office of Technology is intensifying delivery of routers during the upcoming quarter. | Frontier Communications mitigation plan will cause WV to meet overall grant requirements by the end of year three. The WV Office of Technology is intensifying delivery of routers during the upcoming quarter. A total of 126 sites received new access this quarter. Two sites were previously not reported in the 1st quarter and are reflected in the list below. | A total of 15 sites receives new access this quarter. Four sites were previously not reported in the 1st quarter and are reflected in the list below. | <10meg =173 10meg-50meg=475 >50meg=414 DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | During the upcoming quarter, the following should be accomplished: The balance of the remaining microwave radios should be delivered with subsequent installation to be in progress. The WVNet equipment should be received with installation 50% accomplished. We will identify any potential residual from the overall grant and prepare a budget estimate and plan for the remaining funding. The money flow for the overall grant will significantly increase, largely due to the influx of Frontier Communications invoices. We should receive approval, order steel, and begin construction for the five (5) replacement towers. We will continue to have progress with the mitigation plan. Ten of the twelve towers should be complete. We expect to have an Office of the Inspector General visit and review of the overall grant. We expect to have an NTIA Program Office visit. Frontier plans to lay approximately 90 miles of new fiber, in the third quarter, for a total of approximately 500 miles. We plan to connect approximately 135 new CAI locations. We anticipate zero (0) new Wholesaler or Provider last mile agreements in the third quarter. | Executive Office State of West Virginia | No major challenges occurred during this quarter until late in June 2012, the entire state of West Virginia suffered from devastating winds that caused major damage and disruption of electricity, communications, and other essential services to our communities and businesses. Frontier lost valuable BTOP construction time due to the monumental efforts required to regain the stateâ€™s infrastructure. This event is not expected to significantly delay the overall fiber project, The BTOP team diligently worked with the WV team during this time to provide input and general guidance. Actual draw down flow has been hampered due to a need to provide sufficient data for State of West Virginia accounting processes. The Office of Technology worked with Frontier Communications to resolve the actual invoice presentation. The invoices now meet the overall necessary criteria with invoices currently processing through the system. | We continue to validate processes utilized for procurement of equipment early in the grant. This causes a challenge directly related to time and effort. As the Office of Inspector General (OIG), the NTIA Program Office and others meet with us and review our efforts, the team will need to redirect time and efforts. NTIA will work with us to minimize any impact to construction and/or reporting associated with such visits. The June 2012 storm directly caused approximately one monthâ€™s delay in their mitigation plan. This delay should not cause the effort to go beyond acceptable limits, but it will be a challenge to ensure compliance with deadlines and grant completion. We requested approval to reconstruct five (5) towers that has structural deficiencies when adding the BTOP antenna. Due largely to the associated environmental efforts, we have not ordered steel or started site preparation. This presents a significant challenge to complete this initiative by grant deadlines. NTIA is working with WV to obtain the necessary approvals. There is a potential for some funding left over after completion of the grant. This presents two challenges. First, we must develop an estimate of any remaining funds and submit our recommendation to the Governorâ€™s Office for the following; grant turn in, additional projects, etc. The second challenge is to present any proposals to NTIA, obtain necessary approval, and commence that effort.
NT10BIX5570031 | 2012 | Q3 | Q3 - 2012 | During the quarter July, August, and September 2012, by grant definition, 107 community anchor institutions have new construction (fiber & router) and 21 have improved service (fiber & router) for a total of 128 community anchors complete during the quarter. Total BTOP Fiber mileage installed during the quarter is 88 miles. In the wireless portion 1 new towers finished construction. WV Net received 90% of the equipment for their portion of the project. During the quarter, we drew down $3,448756.30 for grant execution. | 486 | 0 | 0 | 0 | 486 | 376 | 10 | 21 | The current Community Anchor fiber build out list is at 638 locations with an approximate total mileage for the middle mile portion of 655 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. (Note: This mileage includes NRAO/WVU build) | N/A | N/A | N/A | The current Community Anchor fiber build out list is at 638 locations with an approximate total mileage for the middle mile portion of 655 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. (Note: This mileage includes NRAO/WVU build) | Radios Installed: 419 (62 TDM & 367 BB) | Cleveland MTN, Cottle Knob, Franklin/Long Ridge, Grantsville/Five Forks, Greenbrier, Kenna, Sharps Knob, Spencer, Weirton, Williamson towers are completed to date. | We have one interconnect point in progress. As this agreement closes, it becomes the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 1 | 0 | 40 | Frontier Communications has entered into a signed final agreement with CityNet regarding an interconnection to the Bridgeport Public Library. All applicable documents have been signed, but CityNet has yet to execute on the financial terms of the agreement. | Although CityNet has yet to execute on the financial terms of the agreement, it is our understanding that the type of Wholesale services they intend to provide are a TLS (transparent LAN service) Ethernet type product. The pricing for this agreement is listed below. Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 734 | 440 | 294 | 0 | A total of 734 sites have been completed as of the end of 3rd quarter. | 103 Total new subscribers in Q3. *4 New subscribers not previously recorded on Q2* (107 total new sites accounted for on this report.) | 17 Total improved subscribers in Q3.* 4 Improved subscribers not previously recorded on Q2*(21 total improved sites accounted for on this report.) | <10meg =173 10meg-50meg=475 >50meg=414 DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | During the upcoming quarter, the following should be accomplished: The balance of the original twelve towers should be constructed. Antenna and radios for the original tower design should be installed. The WV Net equipment should be installed and functional. The cash flow for the overall grant will significantly increase, largely due to continuing influx of Frontier Communications invoices. We will complete an on-site NTIA Program Manager visit. NRAO/WVU fiber build will be complete. The grant will be at final stages, less the five (5) replacement towers. Frontier Construction plans to add approximately 90 miles of fiber during the next quarter. Approximately 80 Community Anchor Institutes are planned to be connected during the next quarter. We are working on broadband wholesaler and/or last mile provider agreements and anticipate addition of two signed during the next quarter. | Executive Office State of West Virginia | No major challenges were incurred during last quarter. As we submitted and NTIA approved the 5 replacement towers, NTIA provided support by ensuring sufficient detail and documentation were included in the overall processes to apply and receive approval for the towers. | The single largest challenge is the build-out of the 5 replacement towers. We will be in the middle of winter causing severe weather at the 5 sites. This could delay the overall replacement tower project until such time as weather permits construction. We are working on a plan to use any residual funding associated with the grant. After finalization of the plan, submission to NTIA, and potential approval time will be essential and minimal to complete any project.
NT10BIX5570031 | 2012 | Q4 | Q4 - 2012 | As of December 31, 2012, by grant definition, 578 community anchor institutions have new construction (fiber & router) and 307 have improved service (router) for a total of 885 community anchors considered complete. Of 321 sites requiring facility build out, 263 are complete. Total BTOP Fiber mileage to date is 634 miles. In the wireless portion of the project 11 new towers are constructed. WV Net received 100% of the equipment for their portion of the project. We have drawn down a total of $79,855,305.69 for grant execution. | 634 | 0 | 0 | 0 | 634 | 376 | 11 | 21 | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. Further the NRAO/WVU build will be approximately 85 miles. There are 634 miles complete as of December 31, 2012. | N/A | N/A | N/A | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. Further the NRAO/WVU build will be approximately 85 miles. There are 634 miles complete as of December 31, 2012. | There are no reported changes since last quarter. | Eleven of twelve towers are fully constructed. During the first quarter of 2013, we will complete the twelfth tower and begin construction and completion of the five replacement towers. | We have one interconnect point in progress. As this agreement closes, it becomes the model for additional interconnect sites. Most likely we will not see significant interconnects until actual completion of the project. | 0 | 0 | 40 | Frontier Communications has entered into a signed agreement with CityNet regarding an interconnection to the Bridgeport Public Library. All applicable documents have been signed, but CityNet has yet to execute on the financial terms of the agreement. Therefore, there is one agreement in progress. This will be NEW SERVICE. | Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract); | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 885 | 578 | 307 | 0 | 151 total subscribers served in Q4. | 138 New subscribers served in Q4. | 13 Improved subscribers served in Q4 (10 Router only & 4 Fiber Only) | <10meg =173 10meg-50meg=475 >50meg=414 DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | â€¢ The last of the original 12 towers will be complete. â€¢ Construction begins with two of five replacement towers complete. â€¢ Antenna and radios for the original wireless design should be installed. â€¢ WV Net installation will be complete by the end of February 2013. â€¢ NRAO/WVU equipment will be installed and received. â€¢ We should build 12 miles of fiber next quarter. â€¢ Approximately 95 CAI's should be completed. â€¢ The agreement with Bridgeport Public Library should be completed. â€¢ We will have site visits to every Community Anchor and wireless site to validate inventory, processes, etc. | Executive Office State of West Virginia | *Super Storm Sandy caused damage to some of the NRAO/WVU fiber build as well as some of the middle mile CAI fiber. This delayed overall completion of the project and will have monetary impact to the project. The NTIA team continues to work with WV BTOP to mitigate this situation. *By nature Thanksgiving and Christmas Holidays have some negative impacts to construction. This was held to a minimum by a Frontier aggressive approach to minimize down time. | â€¢ As we begin to conclude the overall initial grant efforts, there remains a potential for some residual funding. The WV Governorâ€™s Office will make a recommendation for NTIA review. â€¢ A further challenge will be the actual process of close out of grant. Although, we do not expect any surprises, often when tying loose ends, some unique situations arise that must be handled. â€¢ A large challenge will be that of full inventory documentation. Our team will work with NTIA to assist in validation of this process.
NT10BIX5570031 | 2013 | Q1 | Q1 - 2013 | As of 31 March 2013 by grant definition, 614 community anchor institutes are complete with new construction (fiber & router) and 380 are complete with improved service for a total of 994 community anchors considered complete. Total BTOP fiber mileage to date is 642 miles. On the wireless portion of the project, 11 new towers are constructed. The current total numbers for Facility Build Outs (FBO) are 324. Of the 324 there are 313 complete with 11 FBO remaining. We have drawn down a total of $82,438,432.65 for the grant execution. | 642 | 0 | 0 | 0 | 642 | 525 | 11 | 623 | As of March 31, 2013 the Community Anchor Fiber build out list is at 640 locations with an approximate total mileage for the middle mile portion at 590 miles, and 85 miles of the NRAO portion. There are 76 NRAO miles complete, and 566 CAI miles complete. This brings the total to 642. Further the NRAO /WVU build will be complete during 2nd quarter 2013. | N/A | N/A | N/A | As of March 31, 2013 the Community Anchor Fiber build out list is at 640 locations with an approximate total mileage for the middle mile portion at 590 miles, and 85 miles of the NRAO portion. There are 76 NRAO miles complete, and 566 CAI miles complete. This brings the total to 642. Further the NRAO /WVU build will be complete during 2nd quarter 2013. | Five hundred twenty five radios are installed with forty one remaining for a total of five hundred sixty six total. We are at 94% complete. | Eleven of the twelve original towers have been completed to date. EA Issues and Tree like tower steel complaints hold up the last new tower. Replacement towers (5) are on track for build out during next quarter. | The fiber connection points directly correlate with the fiber build out and as of this report 623 sites have new fiber. As the project comes to completion, this number will grow accordingly. This number increased from last report because previous reports included only wireless connection points. | 0 | 0 | 40 | Frontier Communications has entered into a signed agreement with CityNet regarding an interconnection to the Bridgeport Public Library. All applicable documents have been signed, but CityNet has yet to execute on the financial terms of the agreement. Therefore, there is one agreement in progress. This will be NEW SERVICE. | Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 994 | 614 | 380 | 0 | 109 Total subscribers served in Q1 of 2013. | 36 subscribers received new access in Q1 2013. There are a total of 630 in this area. | 73 subscribers received improved access in Q1 2013. There are a total of 534 in this area. | <10meg =163 with 85 still planned. 10meg-50meg=417 with 46 still planned. >50meg=414 with 39 still planned. DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | â€¢ Two - three of five replacement towers complete. â€¢ Antenna and radios for the original wireless design should be installed. â€¢ WV Net installation will be complete by the end of 2nd quarter 2013. â€¢ NRAO/WVU equipment should be fully installed. â€¢ We should fully complete fiber build out next quarter. â€¢ Approximately 100% of the planned CAI's should be completed. â€¢ The agreement with Bridgeport Public Library should be completed or discarded. â€¢ We will have site visits to every Community Anchor and wireless site to validate inventory, processes, etc. â€¢ The number of miles FTR plans to deploy next quarter is 13.66 miles (including storm damaged lines). â€¢ FTR plans to connect seven CAI's by the end of the next quarter. â€¢ At this time we do not anticipate any broadband wholesaler/last mile provider agreements with FTR. | Executive Office State of West Virginia | * Because some tower sites are on the highest mountains in West Virginia, substantive snow prohibited engineers, construction, and others from access to these sites. As the snow melted and continues to melt, this will no longer be an inhibitor. * Procurement of equipment ($652,000) has been problematic due to bid processes. The final connectivity of NRAO to WVU hinges on this equipment order, installation, and testing. | * As we begin to conclude the overall initial grant efforts, there remains a potential for some residual funding. The WV Governorâ€™s Office will make a recommendation for NTIA review. * A further challenge will be the actual process of close out of grant. Although, we do not expect any surprises, often when tying loose ends, some unique situations arise that must be handled. * A large challenge will be that of full inventory documentation. Our team will work with NTIA to assist in validation of this process. * The Snow Shoe tower issue (tree type tower or conventional) has not been resolved and, in order to complete the grant, we must make resolution. This effort has proven problematic. * Determination of "last" and/or replacement routers continues to be an ongoing process. To close out the grant, this issue will need to be resolved.
NT10BIX5570031 | 2013 | Q2 | Q2 - 2013 | As of 30 June 2013 by grant definition, 626 community anchor institutes are complete with new construction (fiber & router) and 463 are complete with improved service for a total of 1089 community anchors considered complete. Total BTOP fiber mileage to date is 671 miles. On the wireless portion of the project, 11 new towers are constructed. The current total numbers for Facility Build Outs (FBO) are 324. Of the 324 there are 318 complete with 6 FBO remaining. We have drawn down a total of $87,462,098.42 for the grant execution. Prior to June 1 there was a cash return in the amount of $138,106.57. | 671 | 0 | 0 | 0 | 671 | 494 | 11 | 623 | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. Further the NRAO/WVU build will be approximately 85 miles. There are 671 miles complete as of June 30th, 2013. There are 81 NRAO miles complete, and 590 CAI miles complete. This brings the total to 671. | N/A | N/A | N/A | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Frontierâ€™s mitigation plan will cause the total number of network miles to grow substantially each subsequent month and quarter. Further the NRAO/WVU build will be approximately 85 miles. There are 671 miles complete as of June 30th, 2013. There are 81 NRAO miles complete, and 590 CAI miles complete. This brings the total to 671. | Last report showed 525 radios installed in error. As of this report we actually installed 494. This was an administrative error. We have remaining to install 6 TruePoint and 54 IRU BB radios to complete installation. | Snowshoe Mtn is the only remaining tower of the original twelve. It is in the final stages of completion. The five (5) replacement towers remain under construction (Hargreave, Limestone, Montgomery Hill, Mt. Storm, and North Mountain). | The fiber connection points directly correlate with the fiber build out and as of this report 623 sites have new fiber. As the project comes to completion, this number will grow accordingly. This number increased from last report because previous reports included only wireless connection points. | 0 | 0 | 40 | Frontier Communications has entered into a signed agreement with CityNet regarding an interconnection to the Bridgeport Public Library. All applicable documents have been signed, but CityNet has yet to execute on the financial terms of the agreement. Therefore, there is one agreement in progress. This will be New Service. | Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 1087 | 619 | 468 | 0 | 93 Total subscribers for Q2 2013. Two school were removed due to Hardy County overlap. | 5 subscribers received NEW access in the 2nd QTR. | 88 subscribers received IMPROVED service in the 2nd QTR. Two school were removed due to Hardy County overlap. | <10meg =190 with 57 still planned. 10meg-50meg=463 with 0 still planned. >50meg=436 with 17 still planned. DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | The primary accomplishment for full completion during the next quarter is the completion of the entirety of the Frontier fiber build out, including the Community Anchor Institutions (CAI). We plan to complete the final four miles for the NRAO build-out. The CAI miles are complete at this time. We plan to connect to the final five CAI's in this quarter. We do not anticipate any broadband wholesaler agreements in this quarter. We further anticipate completion of the wireless portion of the build out. The last of the five replacement towers should be completed. After receipt of the end equipment for the WVU / NRAO portion of the build, we should complete this portion of the project. With residual funding, we anticipate NTIA approval and construction of a GigaPOP proposal (currently under review). We anticipate close out of construction of the entire project during the upcoming quarter. WV Net installation will be complete by the end of 3rd quarter 2013. | Executive Office State of West Virginia | An important contract (AUE) expired that was directly associated with the wireless portion of the grant. Inherent with this expiration was an explicit need for such a contract for wireless completion. To facilitate this shortfall, via State of West Virginia purchasing an Expression of Interest (EOI) was developed. This has caused some delays with the finalization of the wireless process. For the West Virginia University (WVU) / National Radio Astronomy Observatory (NRAO) build there has been a purchasing delay with purchase of the end equipment associated with this build out. The association responsible to provide electricity to the Mt. Storm tower site reneged on their commitment to provide electricity. We are seeking a work around for this. | The wireless portion of the project has the following challenges during the next quarter: The road at Workman must be rerouted in order to deliver the antennae to the site. The contractor is waiting on the purchase order to complete this effort. The Grant Implementation Team will continue to monitor this effort. The mechanism and funding has not been identified to enable electricity to the Mt. Storm tower. This has been elevated to a high level, seeking a resolve. The Expression of Interest must be awarded and associated efforts commence to complete close out of the wireless portion. As we receive an inventory WEB based program, we must enter inventory detail onto the system. This will require considerable manpower effort.
NT10BIX5570031 | 2013 | Q3 | Q3 - 2013 | As of 30 September 2013 by grant definition, 632 community anchor institutes are complete with new construction (fiber & router). 21 of the 632 were accounted for in the 3rd quarter. 460 are complete with improved service. 10 of the 460 were accounted for in the 3rd quarter. A total of 1092 community anchors considered complete. 88 routers are left to be distributed. This will bring our total to 1180 sites. The current total numbers for Facility Build Outs (FBO) are 324. Of the 324 there are 324 complete with zero FBO remaining. Total BTOP fiber mileage to date is 675.2 miles which completes BTOP Fiber Miles. On the wireless portion of the project, 12 of the 12 new towers are constructed (one tower needs limbs installed), five of the five rebuild towers are constructed (needs ice bridges and wave guides installed). We have drawn down a total of $90,515,463.56 for the grant execution. We have included 33 total sites to this report that were either newly completed in the 3rd quarter or previously unaccounted for. We removed 12 sites that are from the Hardy County overlap. We removed 9 sites that were deemed to be duplicate entries on past PPR's. | 675 | 0 | 0 | 0 | 675 | 494 | 17 | 623 | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Further, the NRAO/WVU build is approximately 85 miles. There are 675 miles complete as of September 30th, 2013. All Frontier construction is complete. | N/A | N/A | N/A | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Further, the NRAO/WVU build is approximately 85 miles. There are 675 miles complete as of September 30th, 2013. All Frontier construction is complete. | Last report showed 525 radios installed in error. As of this report we actually installed 494. This was an administrative error. We have remaining to install 6 TruePoint and 54 IRU BB radios to complete installation. | Towers are complete. Pending final inspections and Testing. | The fiber connection points directly correlate with the fiber build out and as of this report 623 sites have new fiber. As the project comes to completion, this number will grow accordingly. This number increased from last report because previous reports included only wireless connection points. | 0 | 0 | 40 | NONE | Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 1092 | 632 | 460 | 0 | A total of 1092 community anchors considered complete. 88 routers are left to be distributed. This will bring our total to 1180 sites. We have included 31 total sites to this report that were either newly completed in the 3rd quarter or previously unaccounted for. We removed 12 sites that are from the Hardy County overlap. We removed 16 sites that were deemed to be duplicate entries on past PPR's. | 632 community anchor institutes are complete with new construction (fiber & router). 21 of the 632 were accounted for in the 3rd quarter. | 460 are complete with improved service. 10 of the 460 were accounted for in the 3rd quarter. | <10meg =225 connected 10meg-50meg=440 connected >50meg=427 connected DARK FIBER As this grant comes to fruition, these numbers will adjust from estimated to actual. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | The primary accomplishment for full completion during the next quarter is the completion of the entirety of the Frontier fiber build out, including the Community Anchor Institutions (CAI). The primary accomplishment for full completion during the next quarter is the proposed change out of CISCO 3945 routers, enabling additional routers and funding available for the overall grant completion. We do not anticipate any broadband wholesaler agreements in this quarter. We further anticipate completion of the wireless portion of the build out. The last of the five replacement towers should be completed. After receipt of the end equipment for the WVU / NRAO portion of the build, we should complete this portion of the project. With residual funding, we anticipate NTIA approval and construction of a WV Core initiative (currently under review). We anticipate close out of construction of the entire project during the upcoming quarter. We expect the UCC filing and related covenants to be 95% complete during the quarter. We plan to connect zero miles of fiber. 81 routers are left to be distributed. This will bring our total to 1180 sites. | Executive Office State of West Virginia | â€¢ As the grant comes to closure, some residual funding will be identified that will be used for additional efforts. During this quarter considerable time and effort was utilized to identify and quantify viable projects. The NTIA Program Manager and his team worked diligently with the WV Grant Implementation Team (ongoing into next quarter) in this initiative. â€¢ The U. S. Government Fiscal Year close restricted the use of ASAP for drawdown of funding during the 2nd half of September. Working closely with the NTIA team we provided notification to our sub-recipients and our vendors minimizing the impact of the ASAP hold-up (due to FY end). â€¢ Ernst & Young commenced their annual A-133 WV audit. This effort causes minimal impact, nonetheless, it takes away from grant production. | The wireless portion of the project has the following challenges during the next quarter: â€¢ During late October and early November 2013, the Grant Implementation Team will continue working with NTIA to identify and quantify utilization of residual WV BTOP Funding. NTIA continues to diligently work with our team in this effort. Significant considerations with any identified project will be the time required to complete the project vs the expiration construction time to complete the grant. â€¢ Should the U. S. Government have a shutdown, it remains unclear the impact to the WV BTOP. The NTIA Program Manager continues to work with the GIT to develop plans sufficient to continue grant efforts should such a shut down occur. Should there be a full government shutdown, it could have significant impacts to the WV Grant Construction. â€¢ As normal with any major construction project, the final tweaking and accounting will be a major endeavor. NTIA is committed to work with us during the construction close out planning and the overall grant close out. * The road at Workman must be rerouted in order to deliver the antennae to the site. The contractor is waiting on the purchase order to complete this effort. The Grant Implementation Team will continue to monitor this effort. * As we receive an inventory WEB based program, we must enter inventory detail onto the system. This will require considerable manpower effort.
NT10BIX5570031 | 2013 | Q4 | Q4 - 2013 | The construction associated with the WV BTOP grant is 100% complete. We have drawn down a total of $124,374,998.75 for the grant execution. Including the Match portion this brings our total to $157,874,998.75 We completed 675.2 fiber miles to 644 physical locations of which 85.2 miles were completed in the West Virginia University (WVU) to National Radio Astronomy Observatory (NRAO). Noteworthy is the $1M partnership funds that WVU pledged to this continuing effort. All of the 324 New Facility Build Out (FBO) are complete. All WV K12 schools have fiber available. Some examples of dramatic improvements resultant from this construction include: Southside K-8 (new speed/cost â€“ 100 Mbps@$1505 mo: $15/Mbps); Woodrow Wilson (new speed/cost â€“ 500 Mbps @$2500 mo:$5/Mbps); New River Health 500 Mpbs@$200 mo: $20 Mbps) and NRAO 10 Gbps@ $5000 mo: $0.50 Mbps). Each of these examples plus many more reflect greater service at significant unit reduction in cost. Fiber and or New routers have been provided to 1,127 Community Anchor Institute (CAI) locations including: Schools â€“ 523; Libraries â€“ 174; Telemedicine â€“ 90; Public Safety â€“ 129; Higher Ed â€“ 26; Courthouses â€“ 54; and others (state agencies municipalities, planning & development â€“ 131. The BTOP grant facilitated construction of 12 new towers and 5 replacement towers. Additionally equipment was upgraded on 105 towers and in 13 buildings. This should facilitated a jump start of WVâ€™s implementation of FirstNet. Cost saving efforts enabled the WV BTOP grant to close with an approximate residual of $1,948,297.25 which will be available to the Federal Government for other usage. | 675 | 0 | 0 | 0 | 675 | 554 | 17 | 623 | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Further, the NRAO/WVU build is approximately 85 miles. There are 675 miles complete as of September 30th, 2013. All Frontier construction is complete. | N/A | N/A | N/A | The current Community Anchor Fiber build out list is at 645 locations with an approximate total mileage for the middle mile portion of 590 miles. Further, the NRAO/WVU build is approximately 85 miles. There are 675 miles complete as of September 30th, 2013. All Frontier construction is complete. | All wireless links have been completed. | All 17 towers (12 New and 5 Replacement) are completed. | The fiber connection points directly correlate with the fiber build out and as of this report 623 sites have new fiber. As the project comes to completion, this number will grow accordingly. This number increased from last report because previous reports included only wireless connection points. | 0 | 0 | 40 | NONE | Frontier has had inquires from 7 providers listed below. The nature of the services and inquires varies per provider. The potential pricing is also listed below as only one inquiry (CityNet), progressed to the point of pricing plans. CityNet Wheeling Area Port Authority Mox Networks Lumos Spruce Knob/Seneca Rocks Telephone Stratuswave Windstream Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered TOTAL Charges $ (To Be Determined) (need to add total fibers before final) Non Recurring Costs Service Order Charge per request $162.50 BTOP Fiber Look Up, Engineering Fee $248.75 | Frontier Communications (Sub-recipient) / 304-344-3939 (TELCO portion of MPLS contract) | 0 | 0 | 0 | 0 | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | AS PER BASELINE | 1127 | 639 | 488 | 0 | This is the entire number of routers distributed and total number of CAI's connected. We removed all Hardy County sites. There remains 53 routers not distributed. | COMPLETED. 40 sites chose to only have a router and not fiber. This made those sites become IMPROVED instead of NEW. | 488 COMPLETED 53 routers are still in boxes at West Virginia Office of Technology | <10meg =0 connected 10meg-50meg=1180 connected >50meg=0 connected DARK FIBER | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | There are no new offerings since the last quarterly report. | FALSE | N/A | Note: Effective January 1, 2014 we moved into the administrative close-out portion of the grant. We expect to complete payments of 100% of construction invoices. We expect to complete the Ernst & Young audit. Final functional testing of the wireless portion of the grant will be complete mid February. UCC filings should be complete. Administrative close-out should be complete. | Executive Office State of West Virginia | We continue to work with NTIA for resolve as to methodology for potential utilization of any remaining BTOP funds. The Chief Technology Officer for WV is in direct contact with the Program Management Office to work through this process. The NTIA Program Manager and his team continue to work diligently with the GIT on this initiative. December was a month of holidays which caused minimal delays in grant efforts. We worked around this by planning ahead, which resulted in minimal adverse slow down. Due to a large volume and detail involved processing of Frontier invoices remains slow. Although the invoices for construction were submitted there remains a delay in payment. This should be rectified during the administrative close-out. We continue the Ernst & Young audit, which should be complete first quarter 2014. | COMPLETED All amounts listed in the columns and rows below are the actuals for the entire grant. All the numbers we have used before were our best guesses at the time of submitting the report. Every dollar amount listed below is the 100% reimbursed amount. We are returning $1,948,297.25 from the original $126,323,296 grant award.
NT10BIX5570032 | 2010 | Q3 | Q3 - 2010 | Worked on completion of detailed design of system; responded to comments on environmental assessment; initiated selection process for some construction contractors. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline projection was too optimistic. The resolution of the environmental assessment has delayed the start of construction, and thus dealyed the deploymentof new network miles. As soon as constructin can begin, LCOG should be able to catch up on this aspect of the project. | LCOG has entered into negotiatins to acquire this additional network fiber, but has not resolved matters by the end of the reporting period. LCOG expects to complete the lease in the next quarter and be back on track. | No deviation from expected progress | No deviation from expected progress | Concentration on completion of the environmental assessment has distracted LCOG from completion of this step. The agreements have been negotiated and only need to be signed. This will be accomplished in the next quarter. | NA | NA | No deviation from expected progress | 0 | 0 | 0 | None. LCOG intended to have construction underway before entering into formal agreements with broadband providers. The delay in completion of the Environmental Assessment has delayed this process. In addition the relationship with most wholesale broadband providers will be influenced by the resolution of the security interest questions. When these issues are resolved, LCOG will be able to move forward with securing the agreements with the broadband providers. | Maximum services are planned at the gigabit or the 100 megabit level. It is planned to offer services in 10 mg increments. No pricing decisions have been made at this time. | No designations have been made yet. | 0 | 0 | 0 | 0 | The delay in construction caused by the delay in completion of the environmental assessment has resulted in no signed agreements with new providers. When constructin can begin, LCOG will be able to sign agreements with providers, granting them additional access. | No deviation from expected progress | No deviation from expected progress | NA | 0 | 0 | 0 | 0 | The delay in starting construction because of the delay in completing the environmental assessment has meant that no community anchor institutions have been connected. When construction is underway, the number of institutions served should grow quickly. | The delay in starting construction because of the delay in completing the environmental assessment has meant that no community anchor institutions have been connected. When construction is underway, the number of institutions served should grow quickly. | No deviation from expected progress | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | We plan to provide a variety of speeds, ranging up to one gigabit on the Eugene to Klamath Falls route. | FALSE | No changes have been made. | Complete Environmental Assessment; complete design work; initiate requests for construction permits where necessary; solicit bids for construction work; contract for some construction services. | Lane Council of Government | Resolution of the Section 106 (Natural and Cultural Resource preservation) compliance issues is proving difficult because of the number of parties involved and the variety of expectations. A draft agreement for compliance has been submitted and modified in response to comments. | The Section 106 compliance issues will mean that an archeologist must do some survey work. It will be a challenge to do this work in the winter, but we are hopeful that it can be accomplished in a way that will not impede progress.
NT10BIX5570032 | 2010 | Q4 | Q4 - 2010 | Worked on the environmental assessment, reached agreement among all parties concerning a Programmatic Agreement for archeological work. Submited requests for approval of sole source construction contracts for a portion of total construction. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline projection was too optimistic. The resolution of the environmental assessment delayed the start of construction and thus delayed the deployment of new network miles. Constriction is anticipated to start this quarter and progress rapidly after that start. | A lease for additional miles of network has been negotiated and will be completed in January. | No deviation from expected progress | No deviation from expected progress. The agreements have been negotiated and two will be signed in the next quarter for a lease of more than 350 miles of fiber. | Construction will begin as soon as the environmental assessment is completed. | NA | NA | Progress is continuing on this matter, the architects are nearly completed with the design and it is nearing the bidding phase. | 0 | 2 | 0 | None thus far. We have been delayed until the Environmental Assessment was completed and we were certain of the route. When the assessment is completed we expect to get back on track with this quickly. | Maximum service levels are planned at the gigabit or the 100 megabit level. Services are planned to be offered at all levels. No pricing decisions have been made at this time. | No designations have been made yet. It is planned to designate several third party contractors to operate portions of the network. | 0 | 0 | 0 | 0 | Delays in the environmental assessment approval have delayed this aspect of the project. When the exact character of the network has been determined by approval of the environmental assessment, agreements will be negotiated and signed. | Delays in the environmental assessment approval have delayed this aspect of the project. When the exact character of the network has been determined by approval of the environmental assessment, agreements will be negotiated and signed. | Delays in the environmental assessment approval have delayed this aspect of the project. When the exact character of the network has been determined by approval of the environmental assessment, agreements will be negotiated and signed. | NA | 0 | 0 | 0 | 0 | Delays in the environmental assessment approval have delayed this aspect of the project. When construction can begin after approval of the approval of the environmental assessment, LCOG will select providers, who will then be able to contact subscribers and initiate service agreements. | Delays in the environmental assessment approval have delayed this aspect of the project. When construction can begin after approval of the approval of the environmental assessment, LCOG will select providers, who will then be able to contact subscribers and initiate service agreements | Delays in the environmental assessment approval have delayed this aspect of the project. When construction can begin after approval of the approval of the environmental assessment, LCOG will select providers, who will then be able to contact subscribers and initiate service agreements | Delays in the environmental assessment approval have delayed this aspect of the project. When construction can begin after approval of the approval of the environmental assessment, LCOG will select providers, who will then be able to contact subscribers and initiate service agreements | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None planned. | FALSE | NA | This quarter (January-March 2011) we expect that the environmental assessment will be approved and completed. That will allow LCOG to publish solicitations for construction and initiate construction at several locations. LCOG will also follow through with the Programmatic Agreement reached as a part of the environmental assessment, and retain an archeologist to carry out field surveys and oversee construction at sensitive sites identified in the Programmatic Agreement. | Lane Council of Government | The challenges discussed above reflect the problems faced this quarter. | LCOG has submitted several sole source justifications for construction of portions of the network. If these can be approved quickly, LCOG will be able to start construction as soon as the environmental assessment is approved. The justification for these sole source contracts is that, for the particular location where the process is proposed, there are no other equally qualified construction contractors, that a several of these proposed contracts are with other governmental entities, and that all of them will provide a significant cost savings to the project.
NT10BIX5570032 | 2011 | Q1 | Q1 - 2011 | Completed the Environmental Assessment and received the Finding of No Significant Impact. Received approval for four sole source construction contracts. | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline was too optimistic, especially with regard to the completion of the environmental assessment. It should be possible to quickly catch up for most of the original prediction because much of it involved an IRU which is in the process of completion this quarter. | The terms for all the network leases have been accepted. Completion of all the leases is expected this quarter. | No deviation from expected progress | No deviation from expected progress | Mobilization for construction will begin in Q2 2011, actual construction is expected to begin Q3 2011 | NA | NA | Bids are expected to be distributed in Q2 2011. Construction is expected to start Q3 2011 | 0 | 3 | 0 | None thus far. We are nearing completion of negotiations with three providers, and will solicit proposals from additional providers as the network develops. | Maximum service levels are planned at the gigabit or the 100 megabit level. Services are planned to be offered at all levels. No pricing decisions have been made at this time. | No designations have been made yet. It is planned to designate several third party contractors to operate portions of the network. | 0 | 0 | 0 | 0 | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | NA | 0 | 0 | 0 | 0 | After construction is begun, the project will begin to serve the anchor institutions. | After construction is begun, the project will begin to serve the anchor institutions. | After construction is begun, the project will begin to serve the anchor institutions. | After construction is begun, the project will begin to serve the anchor institutions | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Begin Construction. Solicit construction bids for additional portions of the network. Solicit construction bids for the interconnection site. | Lane Council of Government | The challenges discussed above encompass the challenges faced. The delay in completion of the environmental assessment delayed the start of construction. We were able to work out with the BTOP program a plan to work back to the original schedule. | No special challenges are anticipated. It will take sometime to get construction back on schedule, but by using multiple contractors working on different portions of the network, project completion within the original three year time frame is expected.
NT10BIX5570032 | 2011 | Q2 | Q2 - 2011 | Completed project visit. Initiated construction contracting process. Solicited for construction contractors, signed construction contracts. Finalized in-kind match donation. | 0 | 230 | 0 | 0 | 230 | 0 | 0 | 0 | The baseline was too optimistic, especially with regard to the completion of the environmental assessment. It should be possible to catch up with the original prediction because the IRU for the largest portion of the network is now secure. With construction beginning Q3, we will be able to move forward, top get back in sync with the baseline sometime Q3 2012. | The IRU with the Fiber Consortium has been completed. The only remaining IRU has completed negotiations and should be signed this quarter. This puts us ahead in terms of match, because the largest portion of our match was in one IRU. | No deviation from expected progress | No deviation from expected progress | Construction will begin early Q3. After the completion of the environmental assessment, construction should gradually get back on schedule. | No deviation from expected progress | No deviation from expected progress | The delay in the environmental assessment pushed back the progress on making connections. With construction beginning, we expect tht these interconnection points will be coming on line soon. We should be able to return to the baseline projection sometime in Q3 2012. | 0 | 5 | 0 | None yet. | Maximum service levels are planned at the gigabit or the 100 megabit level. Services are planned to be offered at all levels. No pricing decisions have been made at this time. | No designations have been made yet. It is planned to designate several third party contractors to operate portions of the network. | 0 | 0 | 0 | 0 | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | No agreements were negotiated until the environmental assessment was completed. Discussions have started with some of the providers. | NA | 0 | 0 | 0 | 0 | After construction is begun in Q3 2011, the project will begin to serve the anchor institutions. We should catch up to baseline projections in Q3 2012. | After construction is begun in Q3 2011, the project will begin to serve the anchor institutions. We should catch up to baseline projections in Q3 2012. | After construction is begun in Q3 2011, the project will begin to serve the anchor institutions. We should catch up to baseline projections in Q3 2012. | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Start Construction. Connect the first anchor institutions. Complete the match donations of fiber (IRUs). Complete additional procurements for construction. | Lane Council of Government | The challenges discussed above encompass the challenges faced. The delay in completion of the environmental assessment delayed the start of construction. We were able to work out with the BTOP program a plan to work back to the original schedule. One area where we have been able to keep with the projected schedule is in terms of match. The match expenditures consist of several relatively small contributions, and one IRU which represents perhaps eighty percent of the match. This IRU was finalized, and put the project ahead in terms of the match contribution. This is likely to remain the case for some time. | The continued delay in the delivery of fiber will delay some aspects of the project.
NT10BIX5570032 | 2011 | Q3 | Q3 - 2011 | Design work is progressing. Over sixty percent of the construction contracts (by value) have been signed. Construction has been initiated for several locations. Construction of the interconnection site is approximately fifty percent completed. | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline was too optimistic, especially because it did not take into account the delays caused by an extended environmental review. Construction has begun, so there will be network miles deployed in Q4. | This is approaching the baseline projection. The leases should be completed in Q4. | No deviation from expected progress. | No deviation from expected progress. | In the Q2 report this was read to include network miles leased. If it refers only to constructed fiber, then it should be zero until Q4. | No deviation from expected progress. | No deviation from expected progress. | The delay in the environmental assessment pushed back the progress on making connections. With construction underway, we expect that these interconnection points will be coming on line soon. We expect to return to the baseline projections sometime in Q3 2012. | 0 | 5 | 0 | None yet. | Maximum service levels are planned at the gigabit level, with services offered at all levels, centering around 100 megabit level. No pricing decisions have been made at this time. | One third party contractor has been designated. The University of Oregon's Network for Engineering Research has been selected to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net No other third parties have been designated yet. All of the designations will be for contractors. Negotiations are nearing completion with several contractors for service. | 0 | 1 | 0 | 0 | No agreements were negotiated until the environmental assessment was completed. Several providers have been selected and negotiations are nearing completion. | No agreements were negotiated until the environmental assessment was completed. Several providers have been selected and negotiations are nearing completion | No agreements were negotiated until the environmental assessment was completed. Several providers have been selected and negotiations are nearing completion | NA | 0 | 0 | 0 | 0 | Because construction began in Q3, the project expects to begin to serve anchor institutions in Q4 2011. We should catch up to the baseline projections in Q3 2012. | Because construction began in Q3, the project expects to begin to serve anchor institutions in Q4 2011. We should catch up to the baseline projections in Q3 2012. | Because construction began in Q3, the project expects to begin to serve anchor institutions in Q4 2011. We should catch up to the baseline projections in Q3 2012. | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Connect first anchor institutions. Complete agreements with four broadband service providers. Process and receive approval for route changes adding anchor institutions to the list to be served. Complete additional procurements for construction. Construct additional network miles, (estimated 25). Complete network leases, adding an additional 40 miles of network. Begin connectiong CAIs, with an estimated | Lane Council of Government | The challenge that cause a delay was the environmental review. We are experiencing some delays no because of fiber shortages. We have proceeded with the installation of underground conduit where appropriate and have ordered the fiber to install later when it arrives. We are working to implement the plan developed with NTIA after the loss of schedule because of the delays caused by the environmental review. Much of the preliminary work, design, permitting and so forth takes up much more time than the actual construction takes, especially for the above ground construction. For that reason, although we are not fifty percent spent, we are approaching the fifty percent mark in terms of the time required for completion. Two delays that we experienced that can be seen below in the Budget Execution Details 1b; there was a delay in securing the ground lease for a regeneration site because of unrelated fiscal and electoral difficulties in the city of Oakridge, there also was a delay in the acquisition of some equipment because of a delay in testing the signal loss in a portion of the network. We anticipate completion of these matters in quarter 4, 2011. | The continued delay in the delivery of fiber will cause some disruption. We are solving this problem by contracting with suppliers and builders who have some supplies on hand.
NT10BIX5570032 | 2011 | Q4 | Q4 - 2011 | Additional construction contracts signed. First Critical Anchor Institutions connected. Construction of the interconnection site completed except for fiber connectivity. | 35 | 353 | 0 | 0 | 35 | 0 | 0 | 0 | The baseline was too optimistic, both in terms of time and in the estimate of miles to be constructed. The final engineering has reduced the miles needed for construction. The environmental review also delayed the start of construction. We have identified some additional CAIs, which, if approved, will increase the estimated network miles by an estimated 14 miles. The total estimated miles built by the project will be approximately 86 miles. The additional construction will be completed in the third quarter 2012. | All planned miles have been leased. | No deviation from expected progress. | No deviation from expected progress | Construction is beginning to catch up with the original too optimistic projections. We expect to be back to the baseline projections third quarter 2012. | NA | NA | The baseline was too optimistic. The environmental review also delayed the start of construction. The interconnection point to be constructed is nearly complete, lacking only fiber access to be completed. Completion is anticipated first quarter 2012. | 3 | 2 | 80 | Douglas Fast Net, CoastCom, Inc., Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date the only provider providing services on the wholesale level as a part of this project id Douglas Fast Net. Their pricing is attached. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek and Riddle Oregon. Will use additional routes as construction is completed. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 1 | 2 | 0 | 8 | This is a correction, based on a clearer understandng of what is being asked. Based on current understanding a provider is only receiving new access if an entirely new route is being opened up, not just new access to community anchor institutions. | This report represents a correction based on a clearer understanding of the concept behind the question. The answer to this question (and the others in this section) is that if a provider already has service from City A to City B and the internet and this project gives them, by contract, access to new anchor institutions in City A, that constitutes receiving improved access. This changed understanding reflects a change in understanding from what was reported at the baseline, and therefore a change in the baseline report. | No deviation. This question is now understood to ask for a category that is exclusive of the question above (new access). In earlier answers it may have been answered differently, that is, answered as if a provider could be put into two categories. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (app. 5) select services in the 10 Mgbit range. | 10 | 10 | 0 | 8 | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. | There were no existing subscribers at the time of the application, so no subscribers will receive improved access from this project, although some subscribers who had access to broadband from other providers may choose to change because they will get improved service. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (app. 5) select services in the 10 Mgbit range. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet at speeds up to 1 Gigabit. | FALSE | NA | Continue construction. File amended environmental assessment for route changes, receive approval for route changes. Let all contracts for construction. Connect an additional 40 Community Anchor Institutions for a total of 50 connected. Deploy an additional 25 miles of new network miles. Because all the anticipated miles of leased fiber has been obtained, no additional miles are anticipated to be leased. Sign an additional two provider agreements. | Lane Council of Government | The challenge that cause a delay was the environmental review. We have proceeded with the installation of underground conduit where appropriate and have ordered the fiber to install later when it arrives. We are working to implement the plan developed with NTIA after the loss of schedule because of the delays caused by the environmental review. Much of the preliminary work, design, permitting and so forth takes up much more time than the actual construction takes, especially for the above ground construction. For that reason, although we are not fifty percent spent, we are well past the fifty percent mark in terms of the time required for completion. | We must file a request for route modification and a revised EA. The increased reporting requirements have delayed this already. If review is extended when the request is actually filed, then construction on these elements may be delayed. This will cause some increase in cost because the crews will have to go back to make connections that would have been done as construction passes the site but for the delay.
NT10BIX5570032 | 2012 | Q1 | Q1 - 2012 | Continued construction. achieved fifty percent completion in terms of expenditures. Completed request for route and Anchor Institution change. | 50 | 353 | 0 | 0 | 50 | 0 | 0 | 0 | The baseline was too optimistic, both in terms of time and in the estimate of miles to be constructed. The final engineering has reduced the miles needed for construction. The environmental review also delayed the start of construction. We have identified some additional CAIs, which, if approved, will increase the estimated network miles by an estimated 14 miles. The total estimated miles built by the project will be approximately 86 miles. The additional construction will be completed in the third quarter 2012. | All planned miles have been acquired | No deviation from expected progress. | No deviation from expected progress. | Construction is beginning to catch up with the original too optimistic projections. We expect to be back to the baseline projections third quarter 2012. | NA | NA | The interconnection points are expected to come online beginning second quarter 2012. | 3 | 2 | 80 | Douglas FastNet; CoastCom, Inc.; Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date the only provider providing services on the wholesale level as a part of this project id Douglas Fast Net. Their pricing is attached. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek and Riddle Oregon. Will use additional routes as construction is completed. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 1 | 2 | 0 | 8 | This is a correction, based on a clearer understandng of what is being asked. Based on current understanding a provider is only receiving new access if an entirely new route is being opened up, not just new access to community anchor institutions. | This report represents a correction based on a clearer understanding of the concept behind the question. The answer to this question (and the others in this section) is that if a provider already has service from City A to City B and the internet and this project gives them, by contract, access to new anchor institutions in City A, that constitutes receiving improved access. This changed understanding reflects a change in understanding from what was reported at the baseline, and therefore a change in the baseline report. | No deviation. This question is now understood to ask for a category that is exclusive of the question above (new access). In earlier answers it may have been answered differently, that is, answered as if a provider could be put into two categories. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (app. 5) select services in the 10 Mgbit range. | 40 | 40 | 0 | 8 | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. | There were no existing subscribers at the time of the application served by the networks to be constructed, so no subscribers will receive improved access from this project, although some subscribers who had access to broadband from other providers may choose to change because they will get improved service. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (app. 5) select services in the 10 Mgbit range. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet at speeds up to 1 Gigabit. | FALSE | NA | Let final construction contracts. Complete Douglas County construction. Initiate construction in Klamath County. Connect another 15 Anchor Institutions. Complete an additional 15 miles of fiber construction. Complete an additional two wholesale provider agreements. | Lane Council of Government | The challenge that cause a delay was the environmental review. We have proceeded with the installation of underground conduit where appropriate and have ordered the fiber to install later when it arrives. We are working to implement the plan developed with NTIA after the loss of schedule because of the delays caused by the environmental review. Much of the preliminary work, design, permitting and so forth takes up much more time than the actual construction takes, especially for the above ground construction. For that reason, although we are not quite sixty percent spent, we are well past the two thirds mark in terms of the time required for completion. | Our request for modification of some routes and Community Anchor Institutions is under review by NTIA. Approval is essential to keeping the momentum going to get back in line with projections.
NT10BIX5570032 | 2012 | Q2 | Q2 - 2012 | Continued construction. Executed final construction contract. Passed sixty seven percent substantial completion milestone. Completed RFP process for last service provider, initiated sustainability analysis for selection of provider. Continued outreach including to several Lane County cities and with the Klamath Tribes. | 60 | 353 | 0 | 0 | 60 | 0 | 0 | 1 | The baseline was too optimistic, both in terms of time and in the estimate of miles to be constructed. The final engineering has reduced the miles needed for construction. The environmental review also delayed the start of construction. We have identified some additional CAIs, which, if approved, will increase the estimated network miles by an estimated 14 miles. The total estimated miles built by the project will be approximately 86 miles. The additional construction will be completed in the third quarter 2012, if approved. | All planned network miles have been acquired. | No deviation from expected progress. | No deviation. | Construction is catching up to projections. | NA | NA | The interconnection point is being brought online this quarter. | 3 | 2 | 80 | Douglas Fast Net; CoastCom, Inc.; Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date the only provider providing services on the wholesale level as a part of this project id Douglas Fast Net. This was provided in previous reports. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek and Riddle Oregon. Will use additional routes as construction is completed. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 1 | 2 | 0 | 8 | This is a correction, based on a clearer understanding of what is being asked. Based on current understanding a provider is only receiving new access if an entirely new route is being opened up, not just new access to community anchor institutions. | This report represents a correction based on a clearer understanding of the concept behind the question. The answer to this question (and the others in this section) is that if a provider already has service from City A to City B and the internet and this project gives them, by contract, access to new anchor institutions in City A, that constitutes receiving improved access. This changed understanding reflects a change in understanding from what was reported at the baseline, and therefore a change in the baseline report. | No deviation. This question is now understood to ask for a category that is exclusive of the question above (new access). In earlier answers it may have been answered differently, that is, answered as if a provider could be put into two categories. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (approximately 20) select services in the 10 Mgbit range. | 49 | 49 | 0 | 8 | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. In prior reports, on subscriber was counted in two quarters. The Umpqua Regional Medical Center in Sutherlin was connected in the final quarter of 2011. It was inadvertently reported again in the first quarter of 2012. | Because construction was delayed, connectivity for subscribers was delayed. This is now changing rapidly. We anticipate getting back to the baseline in third quarter 2012. | There were no existing subscribers at the time of the application served by the networks to be constructed, so no subscribers will receive improved access from this project, although some subscribers who had access to broadband from other providers may choose to change because they will get improved service. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers (approximately 20) select services in the 10 Mgbit range. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet. | FALSE | NA | Start construction in Lane County small cities area; start construction in Klamath County; complete construction in Douglas County; complete construction in Springfield. Additional miles planned to be deployed: 10. Additional CAIs to be connected: 17. Additional broadband providers with service agreements: two. | Lane Council of Government | The process of route change approval has been difficult. We spent a great deal of time working out how to request changes, and since that time have spent a great deal of time working through the route change request process. In particular, the additional environmental review has been difficult because the portions of the route change where that is no controversy or possible environmental review have been held up by one segment where legitimate questions are being worked through. We have asked if the non-controversial portions of the route change could be released so that those segments could be completed. | We need final environmental clearance of the environmental review of the route changes.
NT10BIX5570032 | 2012 | Q3 | Q3 - 2012 | Initiated final construction phase. Completed construction in many areas. Obtained final permits required from Forest Service and Bureau of Indian Affairs. The Interconnection Site is operational. | 63 | 353 | 0 | 0 | 63 | 0 | 0 | 1 | The original projections were based on optimistic map based estimates. As construction progressed, the more exact measurements have decreased slightly. | All planned network miles have been acquired. | NA | NA | Construction is catching up with projections, but the final mileage will be less than the original projections. | NA | NA | The site is operational. Leases for occupancy are being negotiated. | 3 | 2 | 80 | Douglas Fast Net; CoastCom, Inc. Hunter Communications. | The wholesale services are all fiber based ethernet services. As of this date, the only provider providing services on the wholesale level as a part of this project is Douglas Fast Net. The pricing plan was provided in previous reports. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek and Riddle Oregon. Will use additional routes as construction is completed. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 1 | 2 | 0 | 8 | Based on the requirement that this measure is a reflection of new service to a community not previously served, the number thus far is two providers. This should increase soon, probably this quarter. | This number should increase this quarter. | Based on the instructions that each of these three categories are exclusive, this number should not increase, because of the structure of our project. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers select services in the 10 Mgbit range. | 71 | 60 | 10 | 8 | We are catching up to the original projections. We expect to be back to the level projected by the end of the fourth quarter. | Most subscribers are gaining new access. A few are receiving improved access. These are the customers most appreciative of the services being offered. | in the time between when we proposed the project and when we actually got to some subscribers, they had purchased some broadband services. They have enthusiastically embrassed our improved services. | There are tiers available from one Megabit to a gigabit. Most clients are choosing services in the 10 Megabit range. In our project the services are provided by third party service providers. We do not have details on each end user. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet | FALSE | NA | Completion of construction in Klamath County. Completion of construction in Douglas County. Total additional miles planned: three. Installation of equipment and to establish service from Klamath County to Eugene Interconnection site. Lighting up first tenant in Interconnection Site. Connecting 30 CAIs. Signing three additional wholesaler/ last mile provider agreements. | Lane Council of Government | We continue the outreach process, which results in more requests for additional service. We are running up against the barrier of the end of the program. There are certain areas that we might be able to add, but we will not be able to complete the work by the end of the project, January 31. | Dealing with the potential of adding additional sites, including dealing with the time limitations that may prevent service to some interested and eligible sites.
NT10BIX5570032 | 2012 | Q4 | Q4 - 2012 | Continued Construction. Reached 81 percent completion level. Outreach enabled us to add additional CAIs. | 75 | 353 | 0 | 0 | 75 | 0 | 0 | 1 | The original projections were based on optimistic map based estimates. As construction progressed, the more exact measurements have decreased slightly. | All network miles originally planned have been acquired. We are in discussions to lease an additional segment of approximately one mile to avoid some building costs. | NA | NA | Construction is catching up with projections. | NA | NA | The site is operational. | 3 | 3 | 80 | Douglas Fast Net, Coast Com, Inc. Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date, the only provider providing services on the wholesale level as a part of this project is Douglas Fast Net. The pricing plan was provided in previous reports. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek and Riddle Oregon. Will use additional routes as construction is completed. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 3 | 0 | 0 | 8 | Negotiating the agreements has taken longer than expected because we have concentrated on construction. | Negotiating the agreements has taken longer than expected because we have concentrated on construction. This should improve this quarter. | Based on the instructions that each of these three categories are exclusive, this number should not increase, because of the structure of our project. | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers select services in the 10 Mgbit range. | 109 | 90 | 19 | 8 | We are catching up to the original projections. We have added some additional sites, but we expect to be completed before the end of the second quarter. | Most subscribers are gaining new access. | These are the customers most appreciative of the services being offered. | There are tiers available from one Megabit to a gigabit. Most clients are choosing services in the 10 Megabit range. In our project the services are provided by third party service providers. We do not have details on each end user. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet | FALSE | NA | Complete 99 percent of all construction. Achieve over 80 percent equipment deployment. Light the Eugene to Klamath Falls backbone. Deploy an additional 8.6 miles of fiber, bringing the cumulative total to 104 miles. Connect an additional 26 CAIs, creating a cumulative total of 135 CAIs. Sign an additional 3 broadband wholesaler / last mile agreements, bringing the total to 6 agreements. | Lane Council of Government | Delays at the start of the project required that we seek an extension. Seeking the extension also delayed some work. Outreach generates demand for additional connections. We have accommodated that in the past, but we are now no longer going to add sites, but instead focus on finishing construction and deploying the equipment to light service to the CAIs. | We need to finish the environmental assessment on the few additonal CAIs added last quarter. If that is delayed, we will not be able to meet these projections.
NT10BIX5570032 | 2013 | Q1 | Q1 - 2013 | Completed construction on all of the remaining anchor institutions from the original application. Received review and approval of additional anchor institutions. | 98 | 353 | 0 | 0 | 98 | 0 | 0 | 1 | This represents a more accurate measure of actual distances built, as opposed to earlier estimates based on map estimates. | All planed network miles have been leased. We are in discussin to lease an additional approximatly one mile of network fiber. | NA | NA | Construction is catching up with projections. | NA | NA | The site is operational. | 3 | 3 | 80 | Douglas Fast Net, CoastCom, Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date, the only provider providing services on the wholesale level as a part of this project is Douglas Fast Net. The pricing plan was provided in previous reports. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek, Canyonville, Winston and Riddle Oregon. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 3 | 0 | 0 | 8 | Negotiating the agreements has taken longer than expected because we have concentrated on construction. | Negotiating the agreements has taken longer than expected because we have concentrated on construction. They have all been negotiated, the only task remaining is collecting signatures. | NA | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers select services in the 10 Mgbit range | 124 | 105 | 19 | 8 | This represents an increase in the baseline, based on subsequent approvals of additional Anchor Insitutions | Most subscribers are gaining new access | These are the customers most appreciative of the services being offered. | There are tiers available from one Megabit to a gigabit. Most clients are choosing services in the 10 Megabit range. In our project the services are provided by third party service providers. We do not have details on each end user. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet | FALSE | NA | Completion of all network builds, Compete equipment purchasing and equipment deployment. By the end of the quarter we expect to have built 102 miles of fiber and connected 138 Community Anchor Institutions. | Lane Council of Government | We had an Award Action Request under review to add a few additional sites. We worked forward with already approved sites. We delayed equipment purchasing and deployment to make certain that there were adequate funds to complete the basic connections. | The only possible delay will be that equipment delivery may be delayed due to unforseen conditions.
NT10BIX5570032 | 2013 | Q2 | Q2 - 2013 | Completed construction on eight additional anchor institutions. Received permitting approval for additional four anchor institutions.. | 102 | 353 | 0 | 0 | 102 | 0 | 0 | 1 | This is a more accurate measure of distances. | All planned network miles have been leased. | NA | NA | Construction is catching up with projections | NA | NA | The site is operational. | 3 | 3 | 80 | Douglas Fast Net, CoastCom, Hunter Communications | The wholesale services are all fiber based ethernet services. As of this date, the only provider providing services on the wholesale level as a part of this project is Douglas Fast Net. The pricing plan was provided in previous reports. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365, 541-574-9999, Contractor using one half of the fibers installed in Florence, Oregon. Douglas Fast Net, 450 NE Oakland Ave. Roseburg, OR 97601, 541-673-4242, Contractor using one half of the constructed fibers in Sutherlin, Myrtle Creek, Canyonville, Winston and Riddle Oregon. Hunter Communication, 541-772-9282, Contractor will provide services in the future over one half the installed fiber in Chemult and Chiloquin, Oregon. The University of Oregon's Network for Engineering Research has been selected as a contractor to operate the network equipment on the route between Eugene and Klamath Falls. Contact information: David Crowe, NERO, crowe@nero.net | 3 | 0 | 0 | 8 | Negotiating the agreements has taken longer than expected because we have concentrated on construction. | Negotiating the agreements has taken longer than expected because we have concentrated on construction. They have all been negotiated, the only task remaining is collecting signatures. | NA | There are tiers available from 1 Megabit to a gigabit. Thus far most subscribers select services in the 10 Mgbit range | 135 | 116 | 19 | 8 | This represents an increase in the baseline, based on subsequent approvals of additional Anchor Insitutions | Most subscribers are gaining new access | These are the customers most appreciative of the services being offered. | There are tiers available from one Megabit to a gigabit. Most clients are choosing services in the 10 Megabit range. In our project the services are provided by third party service providers. We do not have details on each end user. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Gigabit Ethernet | FALSE | NA | Completion of all network builds, Compete equipment purchasing and equipment deployment. Complete an additional three broadband service provider agreements. Complete connection to all Anchor institutions (139 total). Complete fiber construction adding approximately one and one half miles of new fiber, bringing the total miles to 103.7 miles. Close grant. | Lane Council of Government | Delays in equipment delivery affected some of the project completion dates. | The only possible delay will be that equipment delivery may be delayed due to unforseen conditions. In that event we will complete equipment installation in the next month, at no additional cost to the grant.
NT10BIX5570032 | 2013 | Q3 | Q3 - 2013 | Completed project. Provided connection to 139 total anchor institutions; including 32 schools, 23 medical facilities, 22 public safety facilities and eleven libraries. Provided improved service to a number of institutions including schools, offering them a substantial savings, sometimes amounting to a reduction by more than half of some school's operating costs. Brought fiber optic connectivity for the first time to twelve rural communities, which has already resulted in the opening of a call center increasing jobs by over 120 in the community, with a projected total employment of 200 within 18 months. Provided improved services to multiple communities, allowing additional, non-anchor institutions to access improved broadband connectivity, including a large hotel, which is the major employer in a small rural community. Developed a network extending across three counties, in twenty communities, creating over 400 miles of connectivity opportunities. | 104 | 353 | 0 | 0 | 104 | 0 | 0 | 3 | The original baseline was an estimate of the distances involved. Actual construction was less. | This represents the same number of miles in the application. Again a variance with some reports may have occurred based on original estimates which were not, in the end, accurate. | NA | NA | This is not a variance it is a more accurate measurement than the original estimates | NA | NA | This is what the baseline projected | 5 | 0 | 80 | CoastCom, Inc., Douglas Fast Net, EWEB, City of Cottage Grove, Hunter Communications | We are providing 10 gigabit ethernet service along a portion of the route, for sale in 1 gigabit segments. The price for a one gigabit circuit will be $2000 a month. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365; a contractor serving the Florence portion of our build. Douglas FastNet, 480 NE Oakland Ave Roseburg, OR 97470 a contractor serving the Douglas County area. City of Cottage Grove 400 E. Main St. Cottage Grove OR 97424 a contractor providing services to the City of Cottage Grove Eugene Water and Electric Board, 500 E 8th Ave Eugene OR 97401 a contractor serving the city of Eugene Springfield Utility Board 250 A St Springfield OR 97477 a contractor serving the City of Springfield Hunter Communications 801 Enterprise Dr Central Point OR 97502 a contractor serving other portions of Lane County and the entire portion of Klamath County. | 5 | 0 | 0 | 10 | This is an increase over what was projected. | na | na | Since we are using contractors to provide the service, we do not know the tiers and the number of subscribers to each tier. Generally the range of speeds range from 10 M to 100 M, The subscribers may vary their purchase depending on their needs. | 139 | 83 | 56 | 10 | This is an increase in the number projected in the application and baseline. | This represents an increase in the original estimate. | This represents an increase in the original estimate. | Since we are using contractors to provide the service, we do not know the tiers and the number of subscribers to each tier. Generally the range of speeds range from 10 M to 100 M, The subscribers may vary their purchase depending on their needs. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | On a portion of the route; from Eugene to Klamath Falls we are providing up to 10 gigabit ethernet service at the wholesale level. | FALSE | NA | Complete closeout. | Lane Council of Government | Equipment deployment was delayed by late delivery of the equipment. This problem was overcome. | None
NT10BIX5570032 | 2013 | Q4 | Q4 - 2013 | Completed project. Provided connection to 139 total anchor institutions; including 32 schools, 23 medical facilities, 22 public safety facilities and eleven libraries. Provided improved service to a number of institutions including schools, offering them a substantial savings, sometimes amounting to a reduction by more than half of some school's operating costs. Brought fiber optic connectivity for the first time to twelve rural communities, which has already resulted in the opening of a call center increasing jobs by over 120 in the community, with a projected total employment of 200 within 18 months. Provided improved services to multiple communities, allowing additional, non-anchor institutions to access improved broadband connectivity, including a large hotel, which is the major employer in a small rural community. Developed a network extending across three counties, in twenty communities, creating over 400 miles of connectivity opportunities. | 104 | 353 | 0 | 0 | 104 | 0 | 0 | 3 | The original baseline was an estimate of the distances involved. Actual construction was less. | This represents the same number of miles in the application. Again a variance with some reports may have occurred based on original estimates which were not, in the end, accurate. | NA | NA | This is not a variance it is a more accurate measurement than the original estimates | NA | NA | This is what the baseline projected | 5 | 0 | 80 | CoastCom, Inc., Douglas Fast Net, EWEB, City of Cottage Grove, Hunter Communications | We are providing 10 gigabit ethernet service along a portion of the route, for sale in 1 gigabit segments. The price for a one gigabit circuit will be $2000 a month. | CoastCom, Inc. 151 E. Olive St. Newport OR 97365; a contractor serving the Florence portion of our build. Douglas FastNet, 480 NE Oakland Ave Roseburg, OR 97470 a contractor serving the Douglas County area. City of Cottage Grove 400 E. Main St. Cottage Grove OR 97424 a contractor providing services to the City of Cottage Grove Eugene Water and Electric Board, 500 E 8th Ave Eugene OR 97401 a contractor serving the city of Eugene Springfield Utility Board 250 A St Springfield OR 97477 a contractor serving the City of Springfield Hunter Communications 801 Enterprise Dr Central Point OR 97502 a contractor serving other portions of Lane County and the entire portion of Klamath County. | 5 | 0 | 0 | 10 | This is an increase over what was projected. | na | na | Since we are using contractors to provide the service, we do not know the tiers and the number of subscribers to each tier. Generally the range of speeds range from 10 M to 100 M, The subscribers may vary their purchase depending on their needs. | 139 | 83 | 56 | 10 | This is an increase in the number projected in the application and baseline. | This represents an increase in the original estimate. | This represents an increase in the original estimate. | Since we are using contractors to provide the service, we do not know the tiers and the number of subscribers to each tier. Generally the range of speeds range from 10 M to 100 M, The subscribers may vary their purchase depending on their needs. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | On a portion of the route; from Eugene to Klamath Falls we are providing up to 10 gigabit ethernet service at the wholesale level. | FALSE | NA | Complete closeout. | Lane Council of Government | Equipment deployment was delayed by late delivery of the equipment. This problem was overcome. | None
NT10BIX5570033 | 2010 | Q3 | Q3 - 2010 | Issuance and on time submission of ARRA Report for 2nd Quarter 2010 Report was approved. Issuance and on time submission of BTOP Progress Quarterly Report for 2nd Quarter 2010. Report was approved. Issuance and on time submission of Federal Transaction Report (SF-425). Issuance and on time submission of EA Progress Report and also of EA Draft. Start and efficient progress of the updated engineering network design. EA Final Draft as of the end of this quarter was efficiently on progress. Will comply with the due date established for submission of EA 10/7/2010. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | N/A. | No wholesale services are currently being offered at this stage. | No designated third party. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all subscribers, 2/1 mbps, 6/2 mbps dedicated internet access and Metro E. | 0 | 0 | 0 | 0 | 0 | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. for all subscribers 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. | Not applicable at this stage. | FALSE | Not applicable at this stage. | Milestone #2 EA Activities Q4-2010 1. EA Final Draft and Final versions completed and file to NTIA including SHPO clearances (100%). 2. FONSI status completed and properly documented (100%). Milestone #3 Network Design Activities Q4-2010 1. Final updating of complete network (100%). 2. Network design; spectrum agreements, site locations and commercial tower availability up date (100%). 3. GIS up date (100%). 4. PR Engineer Certifications of preliminary drawings (50%). Milestone #4 Rights of Ways Activities Q4-2010 1. Identification, research of right of way requirements and acquisition agreements (75%). Milestone #5 Construction Permits and Other Approvals Activities Q4-2010 1. Applications completion, packaging and submittals and/or data gathering; produce and file additional information requested and/or conduct meetings, coordination and clarifications and obtain permits and/or endorsement approvals (SHPO, PR Permits Administration, PR Planning Board, Electric Energy Authority and PR Telecommunications Regulation Board among others (20%). Milestone #6 Site Preparation Activities Q4-2010 1. Procurement process for contractor(s); detailed scope of work prepared for each site and/or construction permits and endorsements (10%). Milestone #11 Other Activities Q4-2010 1. Administration and Management works (10% completed). 2. Total Federal Expenditures = $903,000 | Iniciativa Tecnologica Centro Oriental (INTECO) | (1) State Historic Preservation Office (SHPO) has not yet issued any comments although request was file more than 4 months ago. (2) Some of the sites locations of the fifteen existing towers to be leased, as well as the eight towers to be built in the design, had to be changed. This occurred if existing towers had their capacity used up and different tower placements sites needed to be considered. The same issue occurred with the expected sites of the tower sites to be leased; we needed to verify that the land owners hadnâ€™t made any commitments in the last year and some had. The change of placement of a few towers in the network didnâ€™t change the scope of the project, but the EA "Environmental Assessment" submission with final site locations was needed to have final design verified and completed as the EA process is completed with updated locations. | 1. Delay in receiving written comments from State Historic Preservation Office (SHPO). Submitted all requested information. 2. Some of the sites locations of the fifteen existing towers to be leased, as well as the eight towers to be built in the design, had to be changed. This occurred if existing towers had their capacity used up and different tower placements sites needed to be considered. The same issue occurred with the expected sites of the tower sites to be leased, we needed to verify that the land owners hadn't made any commitments in the last year and some had. The change of placement of few towers in the network didnâ€™t change the scope of the project but the EA "Environmental Assessment" submission with final site locations was needed to have the design verified and completed as the EA process is completed with updated locations. 3. To assure completion of the project within the three year time frame required, steps will be taken to mitigate the additional time required to complete the EA process. Competitive procurement processes will be moved as a step function instead of sequentially.
NT10BIX5570033 | 2010 | Q4 | Q4 - 2010 | Special Award Conditions (SAC) accomplishments. Issuance and on time submission of ARRA Report for 3rd Quarter 2010. Report was approved. Issuance and on time submission of BTOP Progress Quarterly Report for 3rd Quarter 2010. Report was approved. Issuance and on time submission of Federal Transaction Report (SF-425) for 3rd Quarter 2010. Environmental Assessment (EA) Special Award Condition (SAC) accomplishments. Final revision of Environmental Assessment (EA) was submitted. A Finding of No Significant Impact (FONSI) was obtained from BTOP-NTIA. FONSI was approved and signed on 11/23/2010 by the Director of Compliance and Audit, BTOP. Overall Project accomplishments. Network design and spectrum site locations reviewed, commercial tower availability reviewed and design documents were updated. Commenced development of RFQ / RFP technical documents for the design, permitting and construction of new site builds. Initiated timetable and milestone developments of project planning for procurement requests for next three months. Attended all conference calls, e-mails and/or webinars scheduled by NTIA as well as providing all answers to the Action Requests received from Grants on Line (GOL) and/or Federal Reporting.gov. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | Not Applicable. Pre Construction Stage. | No wholesale services are currently being offered at this stage. | No designated third party. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | N/A. No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all subscribers, 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. | Not applicable at this stage; Pre construction. | TRUE | Not applicable at this stage; Pre construction. | Milestone #1 Overall Project Activities Q1-2011 1. Deployment and service delivery of INTECO's Middle Mile Network as approved by NTIA-BTOP (5% completion) Milestone #4 Rights of Ways Activities Q1-2011 1. Identification, research of right of way requirements and acquisition agreements. Identification of space allocation, Negotiation and contract signing (65% completion). Milestone #5 Construction Permits and Other Approvals Activities Q1-2011 1. Issue Request for proposal for competitive process,Evaluation and selection of entity to complete Puerto Rico permits required. Applications completion, packaging and submittals and/or data gathering; produce and file additional information requested and/or conduct meetings, coordination and clarifications and obtain permits and/or endorsement approvals PR Permits Administration, PR Planning Board, Electric Energy Authority and PR Telecommunications Regulation Board among others (20% completion). Milestone #11 Other Activities Q1-2011 1. Administration and Management works (5% completion). 2. Total Federal Expenditures = $659,285. Will receive funds from Key Stakeholder, the Puerto Rico Government for matching funds for the project, meeting the committed funds needed for this year. Total funds received are $1.2 Million (35%) of matching funds required. the Puerto Rican Government has reiterated their commitment to complete all the matching funds in the next two years. | Iniciativa Tecnologica Centro Oriental (INTECO) | (1) Delay in completing EA (Environmental Assessment) process. We received the different inputs required during this quarter and obtained the EA-(Environmental Assessment) FONSI (Finding of No Significant Impact) approval. (2) Some of the original sites locations of the fifteen existing towers to be leased, as well as some of the eight towers to be built, had to be changed. The change of placement of some towers in the network didnâ€™t change the scope of the project, but the EA "Environmental Assessment" submission with updated site locations was needed. We wanted to have the final design verified and completed and the EA process completed with updated locations which we were able to acheive. (3) The original baseline was prepared based on the planning and execution of of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 70% completion of the project, as measured | 1.In the process of obtaining rights of way we have found three sites of towers to be built that had issues that impeded their use. Three alternate sites have been identified. Contact with Federal agencies on new sites has been initiated , once feedback is received, the Environmental Assessment will be updated. The new sites are in the same municipalities and neighborhoods as the original sites. The environmental site conditions are the same including flora and fauna, soils, hydrology, ect.. The change in coordinates does not impact the planning stage. The permitting process will integrate these changes for evaluation and permit requirements for the site. 2. Strategy to catch up and meet substantial completion on project. a. We have developed a quadrant strategy, dividing out network of 23 towers into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for these 17 sites and all the equipment for all sites will be purchased in 2011 which will assure substantial completion of expenditures for the project within the initial two year requirement. b. We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the ac
NT10BIX5570033 | 2011 | Q1 | Q1 - 2011 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Fourth Quarter 2010 Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Fourth Quarter 2010. [iii] Issuance, submittal and approval of ARRA Progress Report for Fourth Quarter 2010. b) Overall Project Accomplishments. [i] Held open meeting to explain major project milestones with expected dates of RFPâ€™s with all entities interested in INTECO BTOP project. [ii] Published Request for Proposal (RFP) requesting proposals for Permits and Tower Construction Design of 9 New Towers; in state and regional newspapers. Held meeting with over 18 interested entities, received proposals from 10 companies. Evaluated proposals, based on criteria and evaluation report. Selected entity, established contract and initiated work. [iii] Developed promotional project awareness through various news items in regional and Puerto Ricoâ€™s national newspapers. [iv] Obtained leveraged funds for the project, matching share from the Government of Puerto Rico in the amount of $1.2M during this Fiscal Year. [v] Signed contracts for land lease for 6 of new build tower sites. [vi] Received draft leasing contract or letter of intent for all existing tower sites. [vii] Published a Request for Proposal (RFP) requesting proposals for Site Preparation for Existing Tower Sites; in state newspa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | Not applicable. Pre construction stage. | No wholesale services are currently being offered at this stagey being offered at this stage. | No designated third party. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. | Not applicable at this stage; pre construction. | FALSE | Not applicable at this stage; pre construction. | Milestone #1 Overall Project Activities Q2-2011 1. Deployment and service delivery of INTECO's Infrastructure Middle Mile Network as approved by NTIA-BTOP. Milestone #4 Rights of Ways Activities Q2-2011 1. Identification, research of right of way requirements and acquisition agreements. Identification of space allocation, Negotiation leading to letters of intent or contract signing with all tower sites. Milestone #5 Construction Permits and Other Approvals Activities Q2-2011 1. Entity selected for Permits Tower Construction will review new build sites, do terrain study and develop pre design foundation build. Permits applications worked on for high priority sites, packaging and submittals and/or data gathering; produce and file additional information as requested by endorsing agencies and/or conduct meetings, coordination and clarifications and obtain permits and/or endorsements approvals PR Permits Administration; PR Telecommunications Regulation Board; PR Electric Energy Authority; PR Planning Board, among others. Milestone #6 Site Preparation Activities Q2-2011 1. Site Preparation Request for Proposals for existing sites completed, published, coordinating site visits, receive proposals, evaluation of proposals, selection and signature of contracts. Milestone #7 Equipment Procurement Activities Q2-2011 1. Telecom Equipment Request for Proposals, for 23 Sites (all sites), final edition, published, coordinating site visits, receive proposal | Iniciativa Tecnologica Centro Oriental (INTECO) | (a) In the process of obtaining rights of way we have found three sites of towers to be built that had issues that impeded their use. Three alternate sites were identified. Requested and obtained SHPO feedback of no findings, coordination with NTIA's environmental group was made to update the Environmental Assessment. (b) The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. Based upon expenditure we are six months behind our baseline report. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 67% completion of the project in two years, as measured in money drawdownâ€™s and 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 23 towers into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in | 1. In the process of obtaining rights of way we have found three sites of towers to be built that had issues that impeded their use. Three alternate sites have been identified. Requested and received SHPO feedback of no findings, coordination with NTIAS environmental was made to update the Environmental Assessment. The new sites are in the same municipalities and neighborhoods as the original sites. The environmental site conditions are the same including flora and fauna, soils, hydrology, ect.. The change in coordinates does not impact the planning stage. The permitting process will integrate these changes for evaluation and permit requirements for the site. 2. Strategy to catch up and meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 23 towers into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for these 17 sites and all the equipment for all sites will be purchased in 2011 which will assure substantial completion of expenditures for the project within the initial two year requirement. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the complet
NT10BIX5570033 | 2011 | Q2 | Q2 - 2011 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP First Quarter 2011 Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for First Quarter 2011. [iii] Issuance, submittal and approval of ARRA Progress Report for First Quarter 2011. b) Overall Project Accomplishments. Initiated work on permit requirements for new tower construction. Includes soil studies, terrain elevation and foundation design. Infrastructure expenditure purpose and rationale includes the following pre-construction activities: Published 2 RFPâ€™s, Site Preparation & Construction and Telecommunications Equipment in state/regional newspapers. For RFP 2, Site Preparation & Construction, met with over 40 interested entities, coordinated and lead 6 days of visits to existing towers with interested entities and responded to questions. Received and evaluated proposals from 10 companies for RFP 2. Based on the RFP criteria and evaluation report an entity was selected. For RFP 3, Telecommunications Equipment, met with over 20 interested entities. Coordinated and lead 2 days of visits to existing towers and responded to all questions. Received proposals from 6 companies for RFP 3. The proposals were evaluated and based on the RFP criteria and evaluation report an entity was selected. All FCC frequencies for the projectâ€™s backbone | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. NOTE: Baseline Item 5 of Infrastructure Key Indicators Section expressed "5. Number of towers (when erected/leased)" thus we are including the leased towers as of this quarter. | No variance from baseline. | 0 | 0 | 0 | Not applicable. Pre-construction stage. | No wholesale services are currently being offered at this stagey being offered at this stage. | No designated third party. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. | Not applicable at this stage; pre-construction stage. | FALSE | Not applicable at this stage; pre-construction stage. | MILESTONE #1 OVERALL PROJECT Activities Q3-2011 1. Deployment and service delivery of INTECO's Infrastructure Middle Mile Network as approved by NTIA-BTOP. We will not have any CAI's connected during Q3, we anticipate CAI's connections will initiate in the second quarter (Q2) of 2012. MILESTONE #4 RIGHTS OF WAYS Activities Q3-2011 1. Identification, research of right of way requirements and acquisition agreements. Establish negotiation of terms and applicable elements for contracts. Complete contract signing with all existing tower sites. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q3-2011 1. Entity selected for Permits Tower Construction is working on high priority sites per quadrant strategy. Reviewing new build sites, completing terrain studies and developing pre design foundation build for five high priority sites. Developing permits applications and submittals ; producing additional information as requested by endorsing agencies and obtain endorsements from PR Telecommunications Regulation Board; PR Electric Energy Authority; PR Planning Board, among others. MILESTONE #6 SITE PREPARATION Activities Q3-2011 1. RFP was completed and company awarded contract. The company selected for Site Preparation and Construction will complete eight existing sites preparation and construction according to quadrant strategy priorities. MILESTONE #7 EQUIPMENT PROCUREMENT Activitie | Iniciativa Tecnologica Centro Oriental (INTECO) | (a) The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. Based upon expenditure we are six months behind our baseline report. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 67% completion of the project in two years, as measured in money drawdownâ€™s and 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 23 towers into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for these 17 sites and all the equipment for all sites will be purchased in 2011 which will assure substantial completion of expenditures for the project within the initial two year r | 1. Strategy to catch up and meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 23 towers into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for these 17 sites and all the equipment for all sites will be purchased in 2011 which will assure substantial completion of expenditures for the project within the initial two year requirement. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the acquisition and installation of the equipment and the network. 2. The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method
NT10BIX5570033 | 2011 | Q3 | Q3 - 2011 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Second Quarter 2011 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Second Quarter 2011. [iii] Issuance, submittal and approval of ARRA Progress Report for Second Quarter 2011. b) Overall Project Accomplishments. â€¢ Completed existing tower specifications, negotiations and contract signatures for 10 additional existing towers leases. Developed agreement to be able to meet FCC substantial use requirements for the 2.5 MHz licensed frequencies to be used by the network. â€¢ Interviewed and selected Site Engineer for inspections and a Telecommunications Specialist which will be responsible for equipment being requested for Command Center and Network Management. â€¢ Continued Project awareness thru various news items in regional/state newspapers. Presented project scope in diverse symposiums and professional association conferences. â€¢ Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency and authorization granted for the construction of four new telecommunications towers to be used by the network in underserved areas. All tower permit submissions were approved. â€¢ Completed contract negotiation and signature for Request for Pr | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Three additional existing towers lease contracts were completed. | Preliminary agreement made with a major island ISPh a major island ISP. | 0 | 0 | 0 | Not applicable. Construction Stage. | No wholesale services are currently being offered at this stagey being offered at this stage. | No designated third party. | 0 | 0 | 0 | 0 | No variance from baseline. | Variance from baseline; 1. We will sign our first provider agreement in Q4-2011 to catch up with baseline projection. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No anchor institution are connected to network. Network is in Construction Stage. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. Dedicated Internet Access and Metro E will be available to all. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | No entities passed by network. Network is in Construction Stage, we anticipate entities connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No variance from baseline. For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. | Not applicable at this stage; construction stage. | FALSE | Not applicable at this stage; construction stage. | MILESTONE #1 OVERALL PROJECT Activities Q4-2011 1. Major Activity on Network launch to be held with INTECO board, Mayors of Municipalities, University officials, Government officials; in which we are indicating summer 2012 initiation of network in two quadrants. The overall strategy of prioritizing activities in two of the four quadrants (loops) in the network is paying off, we expect to activate two of the four quadrants in summer 2012. These cover the areas where we are leasing principally existing towers. These two quadrants have a high percentage of the population of the region. All mayor RFP ( request for proposals) for equipment will be completed in this quarter. MILESTONE #4 RIGHTS OF WAYS Activities Q4-2011 1. Complete existing tower specifications, negotiations and contract signatures for 3 additional existing towers leases. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q4-2011 1. Submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency and authorization granted for the construction for three new telecommunications towers to be used by the network in underserved areas. MILESTONE #6 SITE PREPARATION Activities Q4-2011 1. The vendor for Request for Proposal #2, â€œSite Preparation & Constructionâ€ continues work on twelve existing sites with ten existing tower sites expected to be completed i | Iniciativa Tecnologica Centro Oriental (INTECO) | (a) The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. Based upon expenditure we are six months behind our baseline report. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 67% completion of the project in two years, as measured in money drawdownâ€™s and 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 24 sites into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 15 existing towers, 3 new towers and the command center. The site preparation and construction for 16 sites and all the equipment for all sites will be completed by March 2012, which will assure substantial completion of expenditures for the project within th | 1. Strategy to catch up and meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 23 towers and the command center into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 15 existing towers, 3 new towers and the command center. The site preparation for 16 of these sites and the equipment for all sites will be completed by March 2012, which will assure substantial completion of expenditures for the project within the initial two year requirement. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the acquisition and installation of the equipment and the network. 2. The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with
NT10BIX5570033 | 2011 | Q4 | Q4 - 2011 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Third Quarter 2011 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Third Quarter 2011. [iii] Issuance, submittal and approval of ARRA Progress Report for Third Quarter 2011. b) Overall Project Accomplishments. â€¢ Presented project launch dates for two initial quadrants in regional meeting with numerous regional and state officials in attendance, the project launch received numerous newspaper and internet news references. By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in two of the largest quadrants in the region by late summer of 2012, ahead of the Grant schedule. We will initiate connection for CAIâ€™s in the third quarter of 2012 in the quadrants which are activated. We have obtained interconnection agreements with a wholesale provider in the 4th quarter of 2011. â€¢ The project has continued full bore with numerous Request for Proposals being executed and site work completed as well as telecommunications equipment starting to be received. â€¢ The site engineer completed on-site inspections for installations on existing towers. Work was completed for site preparation on 10 existing tower sites for Request for Proposal #2. Initiated receiving of equipment of Request for Proposal #3, â€œTelecommunication Equipmentâ€ and completed installation of telecommunication enclosures in 10 existing sites. Implemented system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received staged and installed. â€¢ We reviewed proposals from Request for Proposal 4, in depth, for equipment being proposed for Command Center and Network Management. Completed evaluation, selection and negotiation of contract with selected vendor for Request for Proposal #4; â€œAcquisition and Implementation of the Central Office Equipment for INTECOs Broadband Networkâ€. This Request for Proposal covers all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc â€¢ Continued work on development of permits submission for three additional new tower sites. We have authorized construction permits for four new towers which already approved and are now requesting build proposals through Request for Proposal #5 â€œSite Preparation and Construction of Telecommunication Structuresâ€. This Request for Proposal was published, meetings held, site visits coordinated and questions answered in the quarter. Proposals for this Request for Proposal 5# will be received in the first weeks of next quarter. â€¢ A total of 142.46 Full Time Equivalent (FTE) jobs were created and retained. Description of the FTE jobs includes: Managers and Administrators (5.86); Warehousing-Inventories Specialist (0.27); Construction (15.10); Architectural and Engineering (0.79); Advertisement and Publications Specialist (0.14); Sales of Telecommunication Equipment (119.50); Appraisers (0.01); Insurance Agents (0.61); Travel Agents (0.18). | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in summer of 2012. | Additional existing tower lease contract completed. Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in summer of 2012. | No variance from baseline. | 1 | 1 | 12 | WorldNet | No wholesale services are currently being offered via the BTOP network at this stage. The BTOP Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in summer of 2012. | No designated third party. | 0 | 0 | 0 | 0 | Variance from baseline of 1. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | No anchor institution are connected to network. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No anchor institution are connected to network. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No anchor institution are connected to network. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps symmetrical, 6/2 mbps and 9/3 mbps. Dedicated Internet Access and Metro E will be available to all. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in summer of 2012. We anticipate business connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers receiving new access will initiate in the third quarter (Q3) of 2012. | No subscribers are connected to network. Network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in summer of 2012. We anticipate subscriber connections will initiate in the third quarter (Q3) of 2012. | Not applicable at this stage; construction stage. | FALSE | Not applicable at this stage, construction stage. | MILESTONE #1 OVERALL PROJECT Activities Q1-2012 1. The project is proceeding as expected in major milestones and critical events. All major RFP have been completed and are in process. All major elements of equipment has been contracted and most will be received and installed in this next quarter . All site preparation in existing sites will be completed and initiation of tower construction in three sites will occur. The NOC construction will be completed and most critical equipment will be installed. MILESTONE #4 RIGHTS OF WAYS Activities Q1-2012 1. Lease agreements for 16 existing towers to be completed. 2. Land lease agreements for 7 new towers site to be completed. 3. Command Center (NOC) of the network and its data center will be completed. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q1-2012 1. Three additional sites permits to be approved. MILESTONE #6 SITE PREPARATION Activities Q1-2012 1. Ten sites have been completed, five more sites will be completed in this quarter. The Request for Proposal for three new tower construction will be evaluated, awarded, contract completed and construction of foundation initiated. MILESTONE #7 EQUIPMENT PROCUREMENT Activities Q1-2012 1. Equipment installed in Data Center (NOC). 2. We will receive 90% or more of all equipment for Request for Proposal #3; Telecommunications Equipment. Implemented system to provide inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of being received, staged and implemented. MILESTONE #8 NETWORK BUILD AND EQUIPMENT DEPLOYMENT Activities Q1-2012 1. Generator installation in Command Center. 2. Complete installation of 15 existing towers sites. 3. Three new towers to have foundation constructed in Q1-2012. 4. We will receive 90% or more of all equipment for Request for Proposal #3 (Telecommunications Equipment). 5. NOC equipment will be received and installed in command center. INFRASTRUCTURE KEY INDICATOR #1 - NEW NETWORK MILES DEPLOYED Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles deployed as we are in the construction phase of the project. INFRASTRUCTURE KEY INDICATOR #3 - NUMBER OF MILES OF FIBER (AERIAL OR UNDERGROUND) Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles deployed as we are in the construction phase of the project. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles deployed as we are in the construction phase of the project. INFRASTRUCTURE KEY INDICATOR #5 - NUMBER OF TOWERS (WHEN ERECTED/LEASE) Activities Q1-2012 1. Lease agreements for 16 existing towers to be completed. 2. Three new towers under construction INFRASTRUCTURE KEY INDICATOR #6 - NUMBER OF INTERCONNECTIONS POINTS Activities Q1-2012 1. We have one signed interconnection agreement. INFRASTRUCTURE KEY INDICATOR #7 - NUMBER OF SIGNED AGREEMENTS WITH BROADBAND WHOLESALE PROVIDERS Activities Q1-2012 1. We will add an additional (one) signed agreement with a wholesale provider in Q1-2012. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q1-2012 1. Expected Federal Grant expenditures in the 1st quarter will be $4,420,000.00 INFRASTRUCTURE KEY INDICATOR #10A - TOTAL CAI SUBSCRIBERS SERVED (CAIs CONNECTED) Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants, we are in the construction phase of the project so we have zero (0) CAI's which we will connect in Q1-2012 . We expect CAI subscribers in the Q3-2012 when we start activating the network in the Caguas/Cayey/Gurabo quadrant. INFRASTRUCTURE KEY INDICATOR #11 - EXISTING NETWORK MILES UPGRADED Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have no existing miles upgraded as we are in the construction phase of the project. IINFRASTRUCTURE KEY INDICATOR #12 - EXISTING NETWORK MILES LEASED Activities Q1-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles leased as we are in the construction phase of the project. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in two of the largest quadrants in the region by late summer of 2012, ahead of the Grant schedule. (a) The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 67% completion of the project in two years, as measured in money drawdownâ€™s and 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 24 sites into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center | 1. Strategy to catch up and meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 23 towers and the command center into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for 16 of these sites and the equipment for all sites will be completed by March 2012, which will assure substantial completion of expenditures for the project within the initial two year requirement. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the acquisition and installation of the equipment and the network. 2. The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with
NT10BIX5570033 | 2012 | Q1 | Q1 - 2012 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Fourth Quarter 2011 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Fourth Quarter 2011. [iii] Issuance, submittal and approval of ARRA Progress Report for Fourth Quarter 2011. b) Overall Project Accomplishments. â€¢ All activities of the project continue on track based on the priorities of the quadrant plan strategy. We divided the network into four quadrants and have been prioritizing two quadrants. We completed the awarding of the contract for the Request for Proposal of the construction of three telecommunication towers which are in the priority quadrants. â€¢ By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in two of the largest quadrants in the region by late summer of 2012, ahead of the Grant schedule. We will initiate connection for CAIâ€™s in the third quarter of 2012 in the quadrants which are activated. â€¢ We have met and exceeded the requirement of substantially completing more than 67% of the project funds within the two year mark of the project. The total project funds disbursed by the end of the first quarter 2012 was 72%. â€¢ Completed installation of telecommunication enclosures and telecommunication equipment installation in 12 existing tower sites. We are using a controlled system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of installation. â€¢ Completed preparation of the NOC (network operational center) with all construction activities completed. The equipment required by the contract for Request for Proposal #4; â€œAcquisition and Implementation of the Central Office Equipment for INTECOs Broadband Networkâ€ was received and installation initiated. This Request for Proposal covers all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. â€¢ We completed the awarding of the contract for the Request for Proposal #5, for the construction of telecommunication towers. The construction of the three telecommunications towers was initiated in a fast track mode and significant work was completed on foundation preparation. â€¢ Continued work on permits submission for additional new tower sites. We have authorized construction permits for 4 new towers. We are expecting approval for 3 additional sites in April/May 2012. â€¢ A total of 213.47 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes Managers and Administrators (6.11); Warehousing-Inventories Specialist (0.17); Construction Permits and Design (5.91); Architectural and Engineering (0.22); Telecommunication Equipment (112.83); Appraisers (13.75); Digital Equipment Services (74.16); Insurance Services (0.15); and Travel Services (0.17). | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Variance from baseline of 15. Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in late summer of 2012. | Variance from baseline of 2. Additional existing tower lease contract completed. Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in summer of 2012. | No variance from baseline. | 1 | 2 | 12 | WorldNet | No wholesale services are currently being offered via the BTOP network at this stage. The BTOP Wireless microwave project is in construction stage. We have a target of initiating two major quadrants in summer of 2012. | No designated third party. | 1 | 0 | 0 | 0 | Variance from baseline of 1. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps asymmetric, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | Variance of 122 from baseline. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in late summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | Variance of 30 from baseline. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in late summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | Variance of 91 from baseline. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in late summer of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps asymmetric , 6/2 mbps and 9/3 mbps. Dedicated Internet Access and Metro E will be available to all. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Variance of 303 from baseline. Wireless microwave network is in construction stage. We have a target of initiating two major quadrants in late summer of 2012. We anticipate business connections will initiate in the third quarter (Q3) of 2012. | Variance of 30 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | Variance of 8 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers receiving new access will initiate in the third quarter (Q3) of 2012. | Variance of 22 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. Wireless microwave network is in construction stage. e have a target of initiating two major quadrants in late summer of 2012. We anticipate subscriber connections will initiate in the third quarter (Q3) of 2012. | Not applicable at this stage; construction stage. | FALSE | Not applicable at this stage, construction stage. | MILESTONE #1 OVERALL PROJECT Activities Q2-2012 1. Complete the NOC (network operational center) with all construction completed and equipment installed. The equipment required by the contract for Request for Proposal #4; â€œAcquisition and Implementation of the Central Office Equipment for INTECOs Broadband Networkâ€ will have installation and Network testing completed. This Request for Proposal covers all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. Completed site preparation in fourteen existing tower sites. The construction of telecommunications towers has continued in a fast track mode, we expect to complete three new towers in this quarter and substantially complete a fourth site. MILESTONE #4 RIGHTS OF WAYS Activities Q2-2012 1. Completed existing tower lease contracts for total 16 existing tower sites. Completed land lease contracts for 6 sites. Will complete two additional lease contracts this quarter. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q2-2012 1. Continued work on permits submission for additional new tower sites. We have authorized construction permits for four new towers. We are expecting approval for three additional sites in this quarter. MILESTONE #6 SITE PREPARATION Activities Q2-2012 1. Complete site preparation in fourteen existing tower sites. The construction of telecommunications towers has continued in a fast track mode, we expect to complete three new towers in this quarter and substantially complete a fourth site. MILESTONE #7 EQUIPMENT PROCUREMENT Activities Q2-2012 1. Complete installation of telecommunication enclosures and telecommunication equipment installation in 14 existing tower sites. We are using a controlled system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of installation MILESTONE #8 NETWORK BUILD Activities Q2-2012 1. Complete installation of telecommunication enclosures and telecommunication equipment installation in 14 existing tower sites. Complete equipment installation in two new tower sites. MILESTONE #9 EQUIPMENT DEPLOYMENT Activities Q2-2012 1. Complete installation of telecommunication enclosures and telecommunication equipment installation in 14existing tower sites. Will complete installation of telecommunication enclosures and telecommunication equipment in two new tower sites. NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 will be completed this quarter. MILESTONE #10 NETWORK TESTING Activities Q2-2012 1. Acquisition and installation of the NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 will be completed and this quarter we will be completing quality checks , system integrity and integration testing. MILESTONE #11 OTHER: ADMINISTRATION AND PROJECT MANAGEMENT Activities Q2-2012 1. With our Project planning update and we completed the 72% expenditure target in two years and will meet the 100% in three years. INFRASTRUCTURE KEY INDICATOR #1 - NEW NETWORK MILES DEPLOYED (WHEN IN OPERATION) Activities Q2-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles deployed as we are in the construction phase of the project. IINFRASTRUCTURE KEY INDICATOR #2 - NEW NETWORK MILES LEASED Activities Q2-2012 1. We are a tower based, microwave project we have zero (0) network miles leased. INFRASTRUCTURE KEY INDICATOR #3 - NUMBER OF MILES OF FIBER (AERIAL OR UNDERGROUND) Activities Q2-2012 1. We are a tower based, microwave project which has zero (0) network miles deployed as we are in the construction phase of the project. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q2-2012 1. We are a tower based, microwave project which is in construction phase, we have zero (0) wireless links activated. INFRASTRUCTURE KEY INDICATOR #5 - NUMBER OF TOWERS (WHEN ERECTED/LEASE) Activities Q2-2012 1. Will complete three new tower construction in quadrants one and two and complete two additional lease agreements for sites in quadrants three and four. INFRASTRUCTURE KEY INDICATOR #6 - NUMBER OF INTERCONNECTIONS POINTS Activities Q2-2012 1. We have one signed interconnection agreement. INFRASTRUCTURE KEY INDICATOR #7 - NUMBER OF SIGNED AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q2-2012 1. We have one signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q2-2012 1. We will add one additional signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q2-2012 1. Expected Federal Grant expenditures in the 2nd quarter 2012 will be $1,468,000.00 . INFRASTRUCTURE KEY INDICATOR #10A - TOTAL SUBSCRIBERS SERVED (CAIs CONNECTED) Activities Q2-2012 1. We are a tower based, microwave project which will be activated by quadrants, we are in the construction phase of the project so we have zero (0) CAI's which we will connect in Q2-2012 . We expect CAI subscribers in the Q3-2012 when we start activating the network in the Caguas/Cayey/Gurabo quadrant. INFRASTRUCTURE KEY INDICATOR #10B - BUSINESS ENTITIES PASSED AND TOTAL SUBSCRIBERS SERVED Activities Q2-2012 1. We are a tower based, microwave project we are in the construction phase of the project so we have zero business entities passed and no subscribers served. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in two of the largest quadrants in the region by late summer of 2012, ahead of the Grant schedule. (a) The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Therefore the progress made in the project, measured with the cash disbursement method is not recognized. We are taking steps to meet both planning activities and cash disbursement requirements in order to comply with the SAC goal of more than 67% completion of the project in two years, as measured in money drawdownâ€™s and 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 24 sites into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and t | 1. Strategy to meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 24 towers and the command center into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. The site preparation for 16 of these sites and the equipment for all sites will be completed by June 2012. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the testing of the equipment and completing the network in the remaining two quadrants. (c) The project is now completing contract processes and equipment has been installed and testing initiated. We have met the cash disbursement requirements of the SAC goal of more than 67% completion of the project with a 72% project completion in the first two years of the project and will complete100% in the three years of the project.
NT10BIX5570033 | 2012 | Q2 | Q2 - 2012 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP First Quarter 2012 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for First Quarter 2012. [iii] Issuance, submittal and approval of ARRA Progress Report for First Quarter 2012. b) Overall Project Accomplishments. â€¢ All activities of the project continue on track based on the priorities of the quadrant plan strategy. We divided the network into four quadrants and have been prioritizing two quadrants. During the quarter we completed the construction of three telecommunication towers which are in the priority quadrants. Work was completed on foundation preparation, tower erection and site prep for the three sites. We completed installation of all equipment needed in the NOC (network operational center), commenced integration and qualification testing. â€¢ By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in the largest quadrants in August of 2012, ahead of the Grant schedule. We will initiate connection for CAIâ€™s in the third quarter of 2012 in the quadrants which are activated. â€¢ We met and exceeded the requirement of substantially completing more than 67% of the project funds within the two year mark of the project. The total project funds disbursed within the two year mark was 72%. â€¢ Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter. We are using a controlled system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of installation. â€¢ Completed equipment installation in the NOC (network operational center) with all construction activities completed. Commenced integration and qualification testing that includes all central office gear, servers, routers, switches, fire wall, security, network operations management, HUAC, UPS, etc. â€¢ Completed installation of key egress point. â€¢ We completed the awarding of the contract for the Request for Proposal #6, for a construction of a 150â€ monopod, telecommunication tower. This tower is part of quadrant 3 and 4 which will be on line in Jan 2013. Construction of the tower will commence in July 2012. â€¢ A total of 52.54 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes Managers and Administrators (5.84); Construction, Permits and Design (25.91); Telecommunication and related Equipment (19.08); Warehousing/Inventory (0.17); land Structures and Rights of Ways (1.26); and Insurances (0.28). | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 2 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Variance from baseline of 22. Wireless microwave project is in construction stage. We will initiate service in largest quadrant in August of 2012. | Variance from baseline of 3. Wireless microwave project is in construction stage. We will initiate service in largest quadrant in August of 2012., ahead of grant schedule. | Variance of 1 from baseline. | 2 | 2 | 12 | WorldNet, Critical Hub | No wholesale services are currently being offered via the BTOP network at this stage. The BTOP Wireless microwave project is in construction stage. We have a will initiate service in largest quadrant in August of 2012. | No designated third party. | 2 | 0 | 0 | 0 | Variance from baseline of 1. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps asymmetric, 6/2 mbps and 9/3 mbps. | 0 | 0 | 0 | 0 | Variance of 183 from baseline. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in August of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | Variance of 46 from baseline. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in August of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | Variance of 137 from baseline. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in August of 2012. We anticipate CAI's connections will initiate in the third quarter (Q3) of 2012. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps asymmetric , 6/2 mbps and 9/3 mbps. Dedicated Internet Access and Metro E will be available to all. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Variance of 454 from baseline. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in August of 2012. We anticipate business connections will initiate in the third quarter (Q3) of 2012. | Variance of 45 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | Variance of 11 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers receiving new access will initiate in the third quarter (Q3) of 2012. | Variance of 34 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the third quarter (Q3) of 2012. | For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in August of 2012. We anticipate subscriber connections will initiate in the third quarter (Q3) of 2012. | Not applicable at this stage; construction stage. | FALSE | Not applicable at this stage; construction stage. | MILESTONE #1 OVERALL PROJECT Activities Q3-2012 1. Complete the NOC (network operational center) systems integration and testing . This covers all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. 2. Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter. We expect to have 20 subscribers connected to the network by the end of the third quarter and will have 5 Community Anchor Institutions connected in Q3 2012. MILESTONE #4 RIGHTS OF WAYS Activities Q3-2012 1. Completed existing tower and land lease contracts for total 21 existing tower sites. Will complete three additional lease contracts this quarter. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q3-2012 1. Continue work on permits submission for three additional roof-top sites. MILESTONE #6 SITE PREPARATION Activities Q3-2012 1. Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter 2012. MILESTONE #9 EQUIPMENT DEPLOYMENT Activities Q3-2012 1. Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We have work pending on nine sites, of these contractors are completing construction work on three new towers. We will complete four sites in the third quarter with five sites to be completed in the fourth quarter 2012. MILESTONE #10 NETWORK TESTING Activities Q3-2012 1. The NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 will be complete quality checks , system integrity and integration testing. MILESTONE #11 OTHER: ADMINISTRATION AND PROJECT MANAGEMENT Activities Q3-2012 1. With our Project planning update and quadrant strategy, we exceeded the SAC requirement of expenditures target in two years and will meet the 100% expenditure requirement in three years. INFRASTRUCTURE KEY INDICATOR #1 - NEW NETWORK MILES DEPLOYED (WHEN IN OPERATION) Activities Q3-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have zero (0) network miles deployed as we are in the construction phase of the project. IINFRASTRUCTURE KEY INDICATOR #2 - NEW NETWORK MILES LEASED Activities Q3-2012 1. We are a tower based, microwave project we have zero (0) network miles leased. INFRASTRUCTURE KEY INDICATOR #3 - NUMBER OF MILES OF FIBER (AERIAL OR UNDERGROUND) Activities Q3-2012 1. We are a tower based, microwave project which has zero (0) network miles deployed as we are in the construction phase of the project. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q3-2012 1. We are a tower based, microwave project which is in construction phase, we have zero (0) wireless links activated. These will commence to be activated in the largest quadrant in August. INFRASTRUCTURE KEY INDICATOR #5 - NUMBER OF TOWERS (WHEN ERECTED/LEASE) Activities Q3-2012 1. Will complete three additional lease agreements for sites. INFRASTRUCTURE KEY INDICATOR #6 - NUMBER OF INTERCONNECTIONS POINTS Activities Q3-2012 1. We have two signed interconnection agreements. INFRASTRUCTURE KEY INDICATOR #7 - NUMBER OF SIGNED AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q3-2012 1. We have one signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q3-2012 1. We will add one additional signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q3-2012 1. Expected Federal Grant expenditures in the 2nd quarter 2012 will be $1,041,068.43 INFRASTRUCTURE KEY INDICATOR #10A - TOTAL SUBSCRIBERS SERVED (CAIs CONNECTED) Activities Q3-2012 1. We are a tower based, microwave project which will be activated by quadrants, we are in the construction phase of the project so we have zero (0) CAI's which we will connect in Q2-2012 . We expect five CAI subscribers in the Q3-2012 when we start activating the network in the Caguas/Cayey/Gurabo quadrant. INFRASTRUCTURE KEY INDICATOR #10B - BUSINESS ENTITIES PASSED AND TOTAL SUBSCRIBERS SERVED Activities Q3-2012 1. We are a tower based, microwave project we are in the construction phase of the project so we have zero business entities passed and no subscribers served. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in two of the largest quadrants in the region by late summer of 2012, ahead of the Grant schedule. The original baseline was prepared based on the planning and execution of activities, not based upon measurement of cash disbursement, which uses cash spent versus project total cash as the project progress measurement method. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time and do not require a large amounts of cash disbursement. Nevertheless, the progress made in the project, (measured with the cash disbursement method) met the SAC requirement of 67% with a 72% disbursement completion in the two year time frame. We will comply with 100% completion in the three years of the project. We have developed a quadrant strategy, dividing our network of 24 sites into four quadrants. We are assigning priorities to two quadrants where we have prioritized the installation of equipment, site preparation and construction of new towers so we will initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. Fifteen of these sites have been completed, we con | 1. Strategy to meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 24 towers and the command center into four quadrants. We are assigning priorities to two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in fifteen tower sites. We will be completing four additional sites in the third quarter, which leaves five sites, mostly roof-tops, to be completed in the fourth quarter. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the testing of the equipment and completing the network in the remaining two quadrants. (c) The project is now completing contract processes and equipment has been installed and testing initiated. We have met the cash disbursement requirements of the SAC goal of more than 67% completion of the project with a 72% project completion in the first two years of the project and will complete100% in the three years of the project.
NT10BIX5570033 | 2012 | Q3 | Q3 - 2012 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Second Quarter 2012 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Second Quarter 2012. [iii] Issuance, submittal and approval of ARRA Progress Report for Second Quarter 2012. b) Overall Project Accomplishments. â€¢ By developing a quadrant strategy and prioritizing site preparation and tower construction, INTECO has been capable of activating the largest quadrant with 13 sites and the NOC (network operations center) in August of 2012, ahead of the Grant schedule. We are providing Internet service to various CAIâ€™s in the quadrant. We continue to validate and do quality checks for CPE set-upâ€™s, verification, testing, provisioning for customers, ensuring that the whole system is ready for expansion for future customers. â€¢ All activities of the project continue on track based on the priorities of the quadrant plan strategy. We divided the network into four quadrants and have been prioritizing the project by quadrants. During this quarter we initiated the construction of the last remaining telecommunication tower which is in quadrant three. Work on this tower was completed on foundation preparation, electrical site work and site prep. The 150 foot monopod will be erected on site in October as well as all site preparation. In the NOC (network operational center) we have continued integration & qualification testing, commissioning of systems, security and routing validation as well as monitoring and testing of modules. â€¢ A total of 28.52 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes Managers and Administrators (6.31); Construction (19.17); Telecommunications Equipment (2.8); Insurance Agents (.13); Warehousing (.07); Office Supplies Sales (.04). | 0 | 0 | 0 | 0 | 0 | 17 | 23 | 3 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Variance from baseline of 21. Wireless microwave project is in construction stage. We will initiate service in largest quadrant in October of 2012. This is the number of active links. | Variance from baseline of 1. Wireless microwave project is in construction stage. We will initiate service in largest quadrant in October of 2012, ahead of grant schedule. | Variance of 1 from baseline. | 2 | 2 | 12 | EdNet, Critical Hub. | The INTECO BTOP Wireless microwave project has initiated service for Internet Connection Services in the largest quadrant in August of 2012 (there are four quadrants in total in the network). We are completing construction and activation of the rest of the network in the fourth quarter of 2012. | No designated third party. | 2 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps asymmetric, 6/2 mbps and 9/3 mbps. | 10 | 1 | 9 | 1 | Variance of 219 from baseline. Wireless microwave network is in construction stage. We have initiated service in largest quadrant in Aug/Sept 2012. We anticipate additional CAI's connections in the fourth quarter (Q4) of 2012. | Variance of 55 from baseline. Wireless microwave network is in construction stage. We will initiate service in largest quadrant in October of 2012. We anticipate additional CAI's connections in the fourth quarter (Q4) of 2012. | Variance of 164 from baseline. Wireless microwave network is in construction stage. We have initiated service in largest quadrant in August/September 2012. We anticipate additional CAI's connections in the fourth quarter (Q4) of 2012. | No variance from baseline. For all future subscribers dedicated internet access at 2/1 mbps asymmetric , 5/1 mbps and 9/3 mbps. At this moment we are only using 5/1 mbps for all subscribers. | 0 | 0 | 0 | 0 | 0 | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | 0 | 0 | 0 | 0 | 0 | Variance of 545 from baseline. Wireless microwave network is in construction stage. We have initiated service in largest quadrant in Aug/Sept 2012. We anticipate business connections will initiate in the first quarter (Q1) of 2013. | Variance of 54 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the first quarter (Q1) of 2013. | Variance of 14 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers receiving new access will initiate in the first quarter (Q1) of 2013. | Variance of 40 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the first quarter (Q1) of 2013. | For all future subscribers; 2/1 mbps, 6/2 mbps and 9/3 mbps dedicated internet access and Metro E. Wireless microwave network is in construction stage. We have initiated service in the largest quadrant in August/September 2012. We anticipate subscriber connections will initiate in the first quarter (Q1) of 2013. | No special offerings are available at this moment; construction stage. | FALSE | Not applicable. | MILESTONE #1 OVERALL PROJECT Activities Q4-2012 1. Complete the NOC (network operational center) systems integration and testing . This covers all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. 2. Completed site preparation , construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We will be completing five additional sites, one tower and four rooftops in the fourth quarter. We will connect 42 additional Community Anchor Institutions to the network by the end of the fourth quarter. MILESTONE #4 RIGHTS OF WAYS Activities Q4-2012 1. Completed existing tower and land lease contracts for total 23 existing tower sites. Will complete one additional lease contracts this quarter. MILESTONE #5 CONSTRUCTION PERMITS AND OTHER APPROVALS Activities Q4-2012 1. Continue work on getting local permits approval for three roof-top sites. MILESTONE #6 SITE PREPARATION Activities Q4-2012 1. Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We will be completing five additional sites, one tower and four rooftops in the fourth quarter 2012. MILESTONE #7 EQUIPMENT PROCUREMENT Activities Q4-2012 1. All equipment for sites and NOC has been acquired. MILESTONE #9 EQUIPMENT DEPLOYMENT Activities Q4-2012 1. Completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We have work pending on five sites, which we will complete in the fourth quarter 2012. MILESTONE #10 NETWORK TESTING Activities Q4-2012 1. The NOC Equipment for INTECO's Broadband Network , Request for Proposal #4 will be completed in this quarter; quality checks , system integrity and integration testing. MILESTONE #11 OTHER: ADMINISTRATION AND PROJECT MANAGEMENT Activities Q4-2012 1. With our Project planning update and quadrant strategy, we will meet the 100% expenditure requirement in three years. INFRASTRUCTURE KEY INDICATOR #1 - NEW NETWORK MILES DEPLOYED (WHEN IN OPERATION) Activities Q4-2012 1. We are a tower based, microwave project which needs to be activated by quadrants so we have network miles deployed. INFRASTRUCTURE KEY INDICATOR #2 - NEW NETWORK MILES LEASED Activities Q4-2012 1. We are a tower based, microwave project we have zero (0) network miles leased. INFRASTRUCTURE KEY INDICATOR #3 - NUMBER OF MILES OF FIBER (AERIAL OR UNDERGROUND) Activities Q4-2012 1. We are a tower based, microwave project which has zero (0) network miles deployed of fiber. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q4-2012 1. We are a tower based, microwave project which is still in construction phase in some quadrants, we have 17 wireless links activated. These were activated in the largest quadrant in three municipalities during August / September. INFRASTRUCTURE KEY INDICATOR #5 - NUMBER OF TOWERS (WHEN ERECTED/LEASE) Activities Q4-2012 1. Will complete all lease agreements for sites, one lease agreement remaining. INFRASTRUCTURE KEY INDICATOR #6 - NUMBER OF INTERCONNECTIONS POINTS Activities Q4-2012 1. We have two signed interconnection agreements. INFRASTRUCTURE KEY INDICATOR #7 - NUMBER OF SIGNED AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q4-2012 1. We have one signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q4-2012 1. We will add one additional signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q4-2012 1. Expected Federal Grant expenditures in the 3rd quarter 2012 will be $1,422,809.00. INFRASTRUCTURE KEY INDICATOR #10A - TOTAL SUBSCRIBERS SERVED (CAIs CONNECTED) Activities Q4-2012 1. We are a tower based, microwave project which will be activated by quadrants, we are still in the construction phase of the project in some quadrants, As we continue to complete the quadrants we continue to connect CAI's. We have forty two (42) additional CAI's activated in Q4-2012. INFRASTRUCTURE KEY INDICATOR #10B - BUSINESS ENTITIES PASSED AND TOTAL SUBSCRIBERS SERVED Activities Q4-2012 1. We are a tower based, microwave project still in the construction phase of the project in some quadrants, we have zero business entities passed and no subscribers. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO has established an objective of activating the network and the operations in the largest quadrant in the region by late summer of 2012, ahead of the Grant schedule. We have achieved this goal with service capability in the municipalities of Caguas, Cayey and Gurabo in this quarter. We have completed installation of telecommunication enclosures and telecommunication equipment installation in all pre-existing tower sites. We are using a controlled system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of installation. We have completed equipment installation in the NOC (network operational center) with all construction activities completed. Commenced integration & qualification testing as well as commissioning for all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. Work continues on the last site preparation work, which are four roof-tops, one will be completed in October, two in November and one in December. During this quarter we initiated the construction of the last remaining telecommunication tower which is in quadrant three. Work on this tower was completed on foundation preparation, electrical site work and site prep. The 150 foot monopod will be erected on site in Octobe | 1. Strategy to meet substantial completion on project. (a) We have developed a quadrant strategy, dividing out network of 24 towers and the command center into four quadrants. We have assigned priorities to the two quadrants where we will initialize the installation of equipment and eventually initiate operations in these areas first. The initial two quadrants have 14 existing towers, 3 new towers and the command center. We have completed site preparation, construction, telecommunication enclosures installation and telecommunication equipment installation in nineteen tower sites. We will be completing five additional sites in the fourth quarter, one tower and four roof-tops. (b) We have updated our project management tasks and the activities with latest information and experiences. Activities are being reviewed to integrate steps and assure the completion of the testing of the equipment and completing the network in the remaining two quadrants. (c) The project is now completing contract processes and equipment has been installed and testing initiated. We have met the cash disbursement requirements of the SAC goal and will complete 100% in the three years of the project.
NT10BIX5570033 | 2012 | Q4 | Q4 - 2012 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Third Quarter 2012 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Third Quarter 2012. [iii] Issuance, submittal and approval of ARRA Progress Report for Third Quarter 2012. b) Overall Project Accomplishments. â€¢ By developing a quadrant strategy and prioritizing site preparation and tower construction, INTECO activated the largest quadrant with 13 sites and the NOC (Network Operations Center) in August of 2012, ahead of the Grant schedule. We are providing Internet service to various Community Anchor Institutions (CAIs) in the quadrant. Every major equipment and component for the NOC (Network Operational Center) is already installed, tested and in service. All the applications related with billing, authentication and authorization, adding, eliminating and monitoring customers are commissioned. In the Network Operations Center we have continued integration & qualification testing, commissioning of systems, security and routing validation as well as monitoring and testing of modules. We continue to validate and do quality checks for Wimax set-ups, verification, testing, provisioning for customers, ensuring that the whole system is ready for expansion for future customers. All Data Center equipment and the Systems components are installed, tested and in service. Equipment such as the IBM Blade Servers, Fortinet Firewall and UTM (Unified Telecommunication Management), JUNIPER Routers, APC UPS (Uninterrupted Power System) and air conditioning system are installed and commissioned. The communication links between the NOC and Data Center are completed, tested and in production. The main egress point is installed and in service. The second egress point will be installed on January 15. During this quarter we completed the construction and site prep for three roof-tops and the last remaining telecommunication tower, all of which are in quadrant three. The 150 foot monopod was erected on site per schedule. Work completed on this tower included foundation preparation, electrical site work and site prep. Work continues actively on three of the last four sites with all preparation and construction completed in the last quarter. In the one remaining site, which is leased there was a delay due to inquiries by neighbors concerning the permits, the permit is being worked on by the leasing company and resolution is expected early in the next quarter. In the next quarter we will be installing the telecommunications equipment in two roof-top sites. â€¢ We have completed installation of telecommunication enclosures and telecommunication equipment installation in all preexisting tower sites. During this quarter we completed the construction of the last remaining telecommunication tower which is in quadrant three. The 150 foot monopod was erected on site per schedule. Work completed on this tower included foundation preparation, electrical site work and site prep. Connection to main power grid and installation of telecommunication equipment will occur in the next quarter. â€¢ A total of 52.57 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes Construction (19.66); Equipment/Installation (32.50); and Insurances (0.41). | 80 | 0 | 0 | 0 | 0 | 20 | 24 | 2 | Wireless microwave project is in construction stage. We initiated service in largest quadrant in 2012. This is the number of addition of the individual active links. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Variance from baseline of 7. Wireless microwave project is in construction stage. We initiated service in largest quadrant in 2012. The final number of active links in the network is 27. | No variance from baseline. | Variance of 2 from baseline. We have two interconnection points , we do not need more interconnection points at this time. Third quarter report indicted 3 interconnection points which was incorrect. Development of traffic volume will determine further increment of interconnection points. | 2 | 2 | 6 | EdNet, Critical Hub. | The INTECO BTOP Wireless microwave project has initiated service for Internet Connection Services in the largest quadrant in August of 2012 (there are four quadrants in total in the network). We are completing construction and activation of the rest of the network in the first quarter of 2013. | No designated third party. | 2 | 0 | 0 | 0 | Variance of two from baseline. Network has not been fully deployed. | No variance from baseline. | No variance from baseline. | No variance from baseline. For all future providers dedicated internet access at 2/1 mbps asymmetric, 5/2 mbps and 9/3 mbps. | 15 | 0 | 15 | 1 | Variance of 60 from baseline. Wireless microwave network is in final construction stage. We have initiated service in largest quadrant in August/September 2012. We anticipate additional CAI's connections in the first quarter (Q1) of 2013. | Variance of 17 from baseline. Wireless microwave network is in final construction stage. We have initiated service in largest quadrant in August/September 2012. We anticipate additional CAI's connections in the first quarter (Q1) of 2013. | Variance of 58 from baseline. Wireless microwave network is in construction stage. We have initiated service in largest quadrant in August/September 2012. We anticipate additional CAI's connections in the 1st quarter (Q1) of 2013. | For all future subscribers dedicated internet access at 2/1 mbps asymmetric , 5/2 mbps and 9/3 mbps. At this moment we are only using 5/2 mbps for all subscribers. This is what we are offering our customers , the baseline was developed almost three years ago, indicated 6/2. | 0 | 0 | 0 | 0 | 0 | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | 0 | 0 | 0 | 0 | 1 | Variance of 605 from baseline. Wireless microwave network is in construction stage. We have initiated service in largest quadrant in Aug/Sept 2012. We anticipate business connections will initiate in the first quarter (Q1) of 2013. | Variance of 61 from baseline. Wireless microwave network is in final Construction Stage. We anticipate subscribers connections will initiate in the first quarter (Q1) of 2013. | Variance of 15 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers receiving new access will initiate in the first quarter (Q1) of 2013. | Variance of 46 from baseline. Wireless microwave network is in Construction Stage. We anticipate subscribers connections will initiate in the first quarter (Q1) of 2013. | For all future subscribers; 2/1 mbps, 5/2 mbps and 9/3 mbps dedicated internet access and Metro E. Wireless microwave network is in final construction stage. We have initiated service in the largest quadrant in August/September 2012. We anticipate subscriber connections will initiate in the first quarter (Q1) of 2013. At this moment we are only using 5/2 mbps for all subscribers. This is what we are offering our customers , the baseline was developed almost three years ago, indicated 6/2. | No special offerings are available at this moment; in final construction stage. | FALSE | Not applicable. | MILESTONE #1 OVERALL PROJECT Activities Q1-2013 1. Completion of installation of equipment and connection to power grid by Puerto Rico Power Authority in two roof-tops and last tower constructed, Juncos9 site. MILESTONE #6 SITE PREPARATION Activities Q1-2013 1. We will be completing two sites, in the first quarter 2013. MILESTONE #10 NETWORK TESTING Activities Q1-2013 1. The NOC Equipment for INTECO's Broadband Network will be completed in this quarter; quality checks, system integrity and integration testing. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q1-2013 1. We will activate 7 additional wireless links. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q1-2013 1. We will add one additional signed wholesale agreement. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q1-2013 1. Expected Federal Grant expenditures in the 1st quarter 2013 will be $228,202.00. INFRASTRUCTURE KEY INDICATOR #10A - TOTAL SUBSCRIBERS SERVED (CAIs CONNECTED) Activities Q1-2013 1. We are a tower based, microwave project which will be activated by quadrants, we are still in the construction phase of the project in some quadrants. As we continue to complete the quadrants we continue to connect CAI's. We will add 25 CAI's activated in Q1-2013. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO had established an objective of activating the network and the operations in the largest quadrant in the region by late summer of 2012, ahead of the Grant schedule. We have achieved this goal with service capability in the municipalities of Caguas, Cayey and Gurabo . We have completed installation of telecommunication enclosures and telecommunication equipment installation in all preexisting tower sites. We used a controlled system for inventory asset control and equipment tag identification for proper asset control for all equipment in diverse stages of installation. We have completed equipment installation in the NOC (network operational center) with all construction activities completed. Commenced integration & qualification testing as well as commissioning for all central office gear, servers, routers, switches, firewall, security, network operations management, HUAC, UPS, etc. Work continues on the last sites which will have telecommunications equipment installed, all preparation work has been completed in these sites, the sites will be completed in Q1 2013. | 1. We will be completing two additional sites in the first quarter. One of the sites, which is a leased site is dealing with concerns raised by neighbors. The site has all permits required by Puerto Rican law however we are reviewing site agreement and neighbors concerns.
NT10BIX5570033 | 2013 | Q1 | Q1 - 2013 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP Fourth Quarter 2012 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for Fourth Quarter 2012. [iii] Issuance, submittal and approval of ARRA Progress Report for Fourth Quarter 2012. b) Overall Project Accomplishments. By developing a quadrant strategy and prioritizing site preparation and tower construction, INTECO activated the largest quadrant with 13 sites and the NOC (Network Operations Center) in August of 2012, ahead of the Grant schedule. We are providing Internet service to various Community Anchor Institutions (CAIs) in the quadrant. Every major equipment and component for the NOC (Network Operational Center) is already installed, tested and in service. All the applications related with billing, authentication and authorization, adding, eliminating and monitoring customers are commissioned. In the Network Operations Center we have continued integration & qualification testing, commissioning of systems, security and routing validation as well as monitoring and testing of modules. We have validated and done quality checks for Wimax set-ups, verification, testing, provisioning for customers, ensuring that the whole system is ready for expansion for future customers. All Data Center equipment and the Systems components are installed, tested and in service. Equipment such as the IBM Blade Servers, Fortinet Firewall and UTM (Unified Telecommunication Management), JUNIPER Routers, APC UPS (Uninterrupted Power System) and air conditioning system are installed and commissioned. The communication links between the NOC and Data Center are completed, tested and in service. The main egress point are installed and in service. We completed the telecommunications equipment installation in three roof-tops. The last remaining telecommunication tower, a 150 foot monopod construction was completed per schedule. The only remaining work pending on this tower is connection to power grid by the local power authority. A total of 3.73 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes; Construction (3.73). | 102 | 0 | 0 | 0 | 0 | 25 | 24 | 2 | Wireless microwave project is in its final construction stage. We initiated service in largest quadrant in 2012. We are pending two links of last tower connection. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Variance from baseline of 2. Connection to grid by PR Power Authority to last tower will be completed in May 2013. | No variance from baseline. | Variance of 2 from baseline. We have two interconnection points , we do not need more interconnection points at this time. Third quarter report indicted 3 interconnection points which was incorrect. Development of traffic volume will determine further increment of interconnection points. | 2 | 1 | 8 | EdNet, Critical Hub. | [REDACTED] | No designated third party. | 2 | 0 | 0 | 4 | Variance of two from baseline. | No variance from baseline. | No variance from baseline. | For all future providers internet service at 3/1 mbps asymmetric, 5/1 mbps ,8/1 and 10/1 mbps. | 24 | 0 | 24 | 4 | Variance of 51 from total CAI's.. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate complete CAI's connections by the end of the second quarter (Q2) of 2013. | Variance of 17 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate complete CAI's connections by the end of the second quarter (Q2) of 2013. | Variance of 34 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate complete CAI's connections by the end of the second quarter (Q2) of 2013. | Present CAI's layout : 3/1mbps = 6 5/1Mbps = 12 8/1Mbps =3 10/1mbps= 3 | 0 | 0 | 0 | 0 | 0 | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | 0 | 0 | 0 | 0 | 4 | Variance of 605 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate to start providing service to Business accounts during the second quarter (Q2) of 2013. | Variance of 61 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate to start providing service to Business accounts during the second quarter (Q2) of 2013. | Variance of 15 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate to start providing service to Business accounts during the second quarter (Q2) of 2013. | Variance of 46 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate to start providing service to Business accounts during the second quarter (Q2) of 2013. | For all future subscribers; 3/1 mbps, 5/1 mbps , 8/1 mbps and 10/1 mbps internet access. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate to start providing service to Business accounts during the second quarter (Q2) of 2013. | No special offerings are available at this moment; in final construction stage. | FALSE | Not applicable. | MILESTONE #1 OVERALL PROJECT Activities Q2-2013 1. Completion of installation of equipment and connection to power grid by Puerto Rico Power Authority in last tower constructed, Juncos9 site. Two links to be connected for 7.06 miles deployed in this quarter. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q2-2013 1. We will activate 2 additional wireless links once last tower is connected to grid by PR Power Authority. INFRASTRUCTURE KEY INDICATOR #6 - INTERCONNECTION POINTS Activities Q2-2013 1. We have two interconnection points, we do not need more interconnection points at this time. Third quarter report indicted 3 interconnection points which was incorrect. Development of traffic volume will determine further increment of interconnection points. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q2-2013 1. We are negotiating with additional wholesaler a wholesale agreement. We will continue the negotiations with one additional wholesaler. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q2-2013 1. Expected Federal Grant expenditures in the 2ND quarter 2013 will be $142,410.00 INFRASTRUCTURE KEY INDICATOR #10A - TOTAL SUBSCRIBERS SERVED (CAI's CONNECTED) Activities Q2-2013 1. We are a tower based, microwave project which will be activated by quadrants, we are completing construction phase of the project in last quadrant. As we continue to complete the quadrants we continue to connect CAI's. We added 9 CAI's activated in Q1-2013. We expect to connect an additional 54 CAI's in this quarter. | Iniciativa Tecnologica Centro Oriental (INTECO) | By developing a quadrant strategy and prioritizing the tower preparation and construction, INTECO had established an objective of activating the network and the operations in the largest quadrant in the region by late summer of 2012, ahead of the Grant schedule. We have achieved this goal with service capability in the municipalities of Caguas, Cayey and Gurabo. Completed all construction and equipment installation on the last sites, three roof-tops and a 150 ft. tower. We are pending connection to power grid of the last tower by PR Power Authority due to delay by the Power Authority in completing service to this rural area tower. This connection will be completed in May 2013. | No issues expected for project, INTECO Broadband to be completed by Q2 2013.
NT10BIX5570033 | 2013 | Q2 | Q2 - 2013 | a) Special Award Conditions (SAC) accomplishments. [i] Issuance, submittal, revision and approval of BTOP First Quarter 2013 Performance Progress Report. [ii] Issuance submittal and approval of the Federal Transaction Report (SF 425) for First Quarter 2013. [iii] Issuance, submittal and approval of ARRA Progress Report for First Quarter 2013. b) Overall Project Accomplishments. By developing a quadrant strategy and prioritizing site preparation and tower construction, INTECO activated the largest quadrant with 13 sites and the NOC (Network Operations Center) in 2012, ahead of the Grant schedule. Every major equipment and component for the NOC (Network Operational Center) is in service. All the applications related with billing, authentication and authorization, adding, eliminating and monitoring customers are commissioned. We have completed validated and quality checks for Wimax set-ups, verification, testing, provisioning for customers, ensuring that the whole system is ready for expansion for future customers. All Data Center equipment and the Systems components are installed, tested and in service. Equipment such as the IBM Blade Servers, Fortinet Firewall and UTM (Unified Telecommunication Management), JUNIPER Routers, APC UPS (Uninterrupted Power System) and air conditioning system are commissioned. The communication links between the NOC and Data Center is in service. Two egress points are installed and in service. We completed all telecommunications equipment installation in all sites. The last remaining telecommunication tower, a 150 foot monopod construction was completed per schedule. The only remaining work pending on this tower is connection to power grid by the local power authority which is being coordinated by the Juncos Muicipipality. The equipment and network on this tower was installed, tested and verified with on site back up generator. A total of 4.96 Full Time Equivalent (FTE) jobs were created or retained. Description of the FTE jobs includes; Construction (4.96). | 109 | 0 | 0 | 0 | 0 | 27 | 24 | 2 | Wireless microwave project is in its final construction stage. We initiated service in largest quadrant in 2012. Al links verified and tested, all equipment on all links installed and verified. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Al links verified and tested, all equipment on all links installed and verified. | No variance from baseline. | Variance of 2 from baseline. We have two interconnection points , we do not need more interconnection points at this time. Third quarter report indicted 3 interconnection points which was incorrect. Development of traffic volume will determine further increment of interconnection points. | 2 | 1 | 8 | EdNet, Critical Hub. | The INTECO BTOP Wireless microwave project has initiated service for Internet Connection Services in the largest two quadrants (there are four quadrants in total in the network). We are completing construction and activation of the rest of the network in the second quarter of 2013. Basic products and services are: speed plans offering different speeds at different prices according to the selected speed. These plans are available at: 1 Mbps download/256 kbps upload; at 3 Mbps download/512 Kbps upload; at 5 Mbps/512 Kbps; at 8 Mbps/1 Mbps and at 10 Mbps/1 Mbps. Also, available a Home Router service with WiFi capacity including 4 Ethernet ports. Customized or Personalized case by case price estimates products and services are; Access Point, Switcher, Point to Point; Fiber, Security/Firewall and Content Filtering. | No designated third party. | 2 | 0 | 0 | 4 | Variance of two from baseline. | No variance from baseline. | No variance from baseline. | For all future providers internet service at 3/1 mbps asymmetric, 5/1 mbps, 8/1 and 10/1 mbps. | 68 | 0 | 68 | 4 | For all future providers internet service at 3/1 mbps asymmetric, 5/1 mbps ,8/1 and 10/1 mbps. | Variance of 17 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate complete CAI's connections in July, 2013. | Variance of 34 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. We anticipate complete CAI's connections in July, 2013. | Present CAI's layout : 3/1mbps = 39 5/1Mbps = 27 8/1Mbps = 0 10/1mbps= 2 | 0 | 138 | 0 | 0 | 4 | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | 3Mbps/512Kbps = 119 5Mbps/512Kbps = 17 8/1Mbps =2 10/1Mbps= 0 | 0 | 11 | 0 | 11 | 4 | Variance of 605 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. | Variance of 50 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. | Variance of 15 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. | Variance of 55 from baseline. Wireless microwave network is in final construction stage and ready for optimization. We have initiated service in largest two quadrants. | 3Mbps/512Kbps = 6 5Mbps/512Kbps =4 8/1Mbps =0 10/1Mbps=1 | No special offerings are available at this moment, in final construction stage. | FALSE | Not applicable. | MILESTONE #1 OVERALL PROJECT Activities Q3-2013 1. Completion of installation of equipment and connection to power grid by Puerto Rico Power Authority in last tower constructed, Juncos9 site. Overall project will be 100% completed. Closeout period will be started. MILESTONE #2 ENVIRONMENTAL ASSESSMENT. Activities Q3-2013 1. Already completed at a 100%. Closeout process will be started. MILESTONE #3 NETWORK DESIGN Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #4 RIGHT OF WAY Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #5 CONSTRUCTION PERMITS Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #6 SITE PREPARATION Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #7 EQUIPMENT PROCUREMENT Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #8 NETWORK BUILD Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #9 EQUIPMENT DEPLOYMENT Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #10 NETWORK TESTING Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. MILESTONE #11 OTHER: ADMINISTRATION AND PROJECT MANAGEMENT Activities Q3-2013 1. Already completed at 100%. Closeout process will be started. INFRASTRUCTURE KEY INDICATOR #1 - NEW NETWORK MILES DEPLOYED (WHEN IN OPERATION) Activities Q3-2013 1.Already completed at 100%. Closeout process will be started. INFRASTRUCTURE KEY INDICATOR #2 - NEW NETWORK MILES LEASED Activities Q3-2013 1. None leased INFRASTRUCTURE KEY INDICATOR #3 - NUMBER OR MILES OF FIBER (AERIAL OR UNDERGROUND) Activities Q3-2013 1. No miles of fiber, project is tower based wireless microwave. INFRASTRUCTURE KEY INDICATOR #4 - NUMBER OF WIRELESS LINKS Activities Q3-2013 1. All links verified and connected. INFRASTRUCTURE KEY INDICATOR #5 - NUMBER OF TOWERS (WHEN ERECTED/LEASED) Activities Q3-2013 1. 24 Sites lease completed INFRASTRUCTURE KEY INDICATOR #6 - INTERCONNECTION POINTS Activities Q3-2013 1. We have two interconnection points, we do not need more interconnection points at this time. Third quarter report indicted 3 interconnection points which was incorrect. Development of traffic volume will determine further increment of interconnection points. Already completed at 100%. INFRASTRUCTURE KEY INDICATOR #7 - NUMBER OF SIGNED AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS. Activities Q3-2013 1. No additional agreements to be completed. INFRASTRUCTURE KEY INDICATOR #8 - NUMBER OF POTENTIAL AGREEMENTS WITH BROADBAND WHOLESALERS OR LAST MILE PROVIDERS Activities Q3-2013 1. No additional agreements to be completed. INFRASTRUCTURE KEY INDICATOR #9 - FEDERAL GRANT EXPENDITURES Activities Q3-2013 1. Expected Federal Grant expenditures in the 3RD quarter 2013 will be $49,385.00. INFRASTRUCTURE KEY INDICATOR #10A-1 - TOTAL SUBSCRIBERS SERVED (CAI's CONNECTED) Activities Q3-2013 1. 84 CAI's in total to be connected. INFRASTRUCTURE KEY INDICATOR #10A-2 - TOTAL SUBSCRIBERS RECEIVING NEW ACCESS (CAI's CONNECTED) Activities Q3-2013 1. O CAI's subscribers receiving new access. INFRASTRUCTURE KEY INDICATOR #10A-3 - TOTAL SUBSCRIBERS RECEIVING IMPROVE ACCESS (CAI's CONNECTED) Activities Q3-2013 1. Sixteen CAI's receiving improved access. INFRASTRUCTURE KEY INDICATOR #10A-4 - CAI'S SPEED TIRES THAT WILL BE AVAILABLE AND THE ESTIMATED NUMBER OF SUBSCRIBERS FOR EACH. Activities Q3-2013 3/1mbps = 51 5/1Mbps = 36 8/1Mbps = 0 10/1mbps= 4 INFRASTRUCTURE KEY INDICATOR #10B-1 - BUSINESS ENTITIES PASSED. Activities Q3-2013 1.Focus in July will be on CAI's, no new business entities served. INFRASTRUCTURE KEY INDICATOR #10B-2 - BUSINESS TOTAL SUBSCRIBERS SERVED. Activities Q3-2013 1. Focus in July will be on additional CAI's, no new business entities served. INFRASTRUCTURE KEY INDICATOR #10B-3 - BUSINESS SUBSCRIBERS RECEIVING NEW ACCESS. Activities Q3-2013 1. Focus in July will be on additional CAI's, no new business entities served. INFRASTRUCTURE KEY INDICATOR #10B-4 - BUSINESS SUBSCRIBERS RECEIVING IMPROVED ACCESS. Activities Q3-2013 1. Focus in July will be on additional CAI's, no new business entities served. INFRASTRUCTURE KEY INDICATOR #10B - BUSINESS SPEED TIRES THAT WILL BE AVAILABLE AND THE ESTIMATED NUMBER OF SUBSCRIBERS FOR EACH. Activities Q3-2013 3Mbps/512Kbps = 6 5Mbps/512Kbps =4 8/1Mbps =0 10/1Mbps=1 | Iniciativa Tecnologica Centro Oriental (INTECO) | The last remaining telecommunication tower, a 150 foot monopod construction was completed per schedule. The only remaining work pending on this tower is connection to power grid by the local power authority which is being coordinated by the Juncos Municipality. The equipment and network on this tower was installed, tested and verified with on site back up generator. We expect connection to occur in August. | INTECO Broadband already completed 100% in Q3-2013.
NT10BIX5570033 | 2013 | Q3 | Q3 - 2013 | a) Overall Project Accomplishments. The project accomplished the main goal of providing a Broadband service to eight Municipalities in the Eastern Central region of Puerto Rico. The region has over 440,000 inhabitants in those municipalities, many of which were in underserved areas until the INTECO project was completed. This region is characterized by a mountainous topography with schools and housing areas dispersed throughout the area. The Municipalities have been provided with a network free of charge in each city to provide the citizens with Internet capability in parks, interactive zones or other areas designated by the Municipality. Jobs were created not only in developing and construction the network but also in the implementation, validation, testing and operation of the network equipment. A total of 136.36 Full Time Equivalent (FTE) jobs were created or retained. All the entities awarded contracts for the equipment, construction of sites and NOC implementation were local companies whose participation in the project benefited the region and their employees. INTECO activated all quadrants with 24 sites and the NOC (Network Operations Center). Every major equipment and component for the NOC (Network Operational Center) is in service. All the applications related with billing, authentication and authorization, adding, eliminating and monitoring customers are commissioned. We have completed validated and quality checks for Wimax set-ups, verification, testing, provisioning for customers, ensuring that the whole system is ready for expansion for future customers. All Data Center equipment and the Systems components are installed, tested and in service. Equipment such as the IBM Blade Servers, Fortinet Firewall and UTM (Unified Telecommunication Management), JUNIPER Routers, APC UPS (Uninterrupted Power System) and air conditioning system are commissioned. The communication links between the NOC and Data Center is in service. Two egress points are installed and in service. We completed all telecommunications equipment installation in all sites. All telecommunication towers were completed per schedule and in service. The equipment and network on all towers were installed, tested and verified. Construction was fully completed within the authorized time period. In terms of business development, the network is being used for business development by developing companies in the Business Incubator in Valle Tolima, Caguas. A number of small developing businesses are using the BroadBand capabilities of the network due to the competitive prices offered which help them offer excellent service while keeping their Internet costs low. The Community Anchor Institution goal was met and exceeded, with more CAI's expected to be connected in the following months after the time frame of the award is completed. The number of schools and libraries connected to the network continue to increase. The expected number of CAI's connected to the network is expected to be duplicated over the next nine months after the proyect is closed. A total of 136.36 Full Time Equivalent (FTE) jobs were created or retained. | 109 | 0 | 0 | 0 | 0 | 27 | 24 | 2 | Wireless microwave project construction ended. We initiated service in all quadrants. All links verified and tested, all equipment on all links installed and verified. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | All links verified and tested, all equipment on all links installed and verified. | No variance from baseline. | Variance of 2 from baseline. We have two interconnection points, we do not need more interconnection points at this time. Development of traffic volume will determine further increment of interconnection points. | 2 | 1 | 8 | EdNet, Critical Hub. | The INTECO BTOP Wireless microwave project has initiated service for Internet Connection Services in all quadrants (there are 4 quadrants in total in the network). Construction and activation completed in the network. Basic products and services are: speed plans offering different speeds at different prices according to the selected speed. These plans are available at: 1 Mbps download/256 kbps upload; at 3 Mbps download/512 Kbps upload; at 5 Mbps/512 Kbps; at 8 Mbps/1 Mbps and at 10 Mbps/1 Mbps. Also, available a Home Router service with WiFi capacity including 4 Ethernet ports. Customized or Personalized case by case price estimates products and services are; Access Point, Switcher, Point to Point; Fiber, Security/Firewall and Content Filtering. NOTE: Attached Updated Pricing List for Services. | No designated third party. | 2 | 0 | 0 | 4 | Variance of 2 from baseline. Negociations were not successful with other entities. | No variance from baseline. | No variance from baseline. | For all future providers internet service at 3/1 mbps asymmetric, 5/1 mbps, 8/1 and 10/1 mbps. | 84 | 0 | 84 | 4 | For all future providers internet service at 3/1 mbps asymmetric, 5/1 mbps ,8/1 and 10/1 mbps. | Variance of 17 from baseline. Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Completed CAI's connections. | Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Completed CAI's connections. | 3/1mbps = 50 5/1Mbps =31 8/1Mbps = 0 10/1mbps= 3 | 0 | 141 | 0 | 0 | 4 | N/A in baseline. | N/A in baseline. | N/A in baseline. | N/A in baseline. | 3Mbps/512Kbps = 121 5Mbps/512Kbps = 18 8/1Mbps =2 10/1Mbps= 0 | 0 | 11 | 0 | 11 | 4 | Variance of 605 from baseline. Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Focus of project changed to CAI connections, original projection was incorrect. | Variance of 50 from baseline. Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Focus of project changed to CAI connections, original projection was incorrect. | Variance of 15 from baseline. Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Focus of project changed to CAI connections, original projection was incorrect. | Variance of 55 from baseline. Wireless microwave network construction ends and optimized. We have initiated service in all quadrants. Focus of project changed to CAI connections, original projection was incorrect. | 3Mbps/512Kbps = 6 5Mbps/512Kbps =4 8/1Mbps =0 10/1Mbps=1 | No special offerings are available at this moment. | FALSE | Not applicable. | MILESTONE #1 OVERALL PROJECT Activities This Quarter (Q4-2013) 1. End of Award Period 07/31/2013; Q3-2013. Overall project 100% completed in Q3-2013; Q3 and Q4-2013 Activities will be those related to the closeout. All closeout activities will be performed before due date, 10/29/2013. | Iniciativa Tecnologica Centro Oriental (INTECO) | We have begun close out of project per schedule; as required by NTIA-BTOP. | INTECO Broadband already completed 100% in this Quarter (Q3-2013). All closeout activities will be performed in Q3, Q4-2013. Closeout package will be upload to PAM on or before the due date 10/29/2013.
NT10BIX5570034 | 2010 | Q3 | Q3 - 2010 | Final Network Design Engineering and Outside Plant Engineering was completed. DeltaCom's Environmental Assessment was approved and a Finding of No Significant Issues ("FONSI") was issued. Long lead equipment procurement activities were completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Not applicable at this time. | Not applicable at this time. | Not applicable at this time. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom is creating competitive middle mile pricing that enables the expansion of last mile provider networks. We are also utilizing last mile providers to enable direct DeltaCom services to public anchor institutions in select markets at a 20% discount below our list pricing for qualifying broadband services. | FALSE | N/A | Project activity planned for the Fourth Quarter of 2010, includes the following milestones: 1) Property acquisition in Blountville, Tennessee. 2) Pre-fabricated shelter/building procurement and integration material procurement. 3) Site preparation and pre-fabricated shelter/building installation. 4) Infinera and Lucent optical network equipment procurement and deployment. 5) Outside plant construction from existing backbone fiber to pre-fabricated shelter/building. 6) Deployment of in-kind fiber match from Nashville to Knoxville to Chattanooga. Project is expected to be back on schedule at the conclusion of Fourth Quarter 2010. | DeltaCom, Inc. | Planned progress was delayed due to the Environmental Assessment FONSI being issued on 9/30/2010. However, spending will accelerate in the Fourth Quarter in order to meet the 2010 forecasted budget milestones. | No issues at this time preventing completion of the work as scheduled in the Baseline Plan.
NT10BIX5570034 | 2010 | Q4 | Q4 - 2010 | Primary activities completed in the quarter included: - Procurement activity for the construction of facilities and outside plant fiber installation for the fiber backbone portion of the network from Nashville to Knoxville to Chattanooga, Tennessee. - Procurement of Infinera and Alcatel Lucent fiber optic transport equipment - Procurement of prefabricated concrete shelter buildings - Procurement of integration related material - Procurement of outside plant subcontractor to perform fiber installation from the backbone fiber network splice point to the DeltaCom Point of Presence (POP) - Procurement of installation subcontractors to perform construction and installation of prefabricated shelter buildings, power plant and generator power installation, and fiber optic equipment installation - Installation of fiber optic equipment at all pre-existing DeltaCom locations on the route from Nashville to Knoxville to Chattanooga, Tennessee. - Installation of prefabricated concrete shelters at Oak Ridge, Cleveland, and Philadelphia, Tennessee. The backbone fiber from Nashville to Knoxville to Chattanooga, is projected to be operational in January 2011. | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Not applicable at this time | Not applicable at this time | N/A | 0 | 0 | 0 | 0 | To be served in a subsequent quarters | To be served in a subsequent quarters | To be served in a subsequent quarters | To be served in a subsequent quarters | 0 | 0 | 0 | 0 | To be served in a subsequent quarters | To be served in a subsequent quarters | To be served in a subsequent quarters | To be served in a subsequent quarters | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom is creating competitive middle mile pricing that enables connectivity for last mile provider networks. We are also utilizing last mile providers to enable direct DeltaCom services to public anchor institutions in select markets at a 20% discount below our list pricing for qualifying broadband services. | FALSE | N/A | The backbone fiber from Nashville to Knoxville to Chattanooga, is projected to be operational by the end of January 2011. The scope for completing the backbone fiber network route from Knoxville, Tennessee to Blountville, Tennessee includes the following: - Procurement of Infinera and Alcatel Lucent fiber optic transport equipment - Procurement of prefabricated concrete shelter buildings - Procurement of integration related material - Procurement of outside plant subcontractor to perform fiber installation from the backbone fiber network splice point to the DeltaCom Point of Presence (POP) - Procurement of installation subcontractors to perform construction and installation of prefabricated shelter buildings, power plant and generator power installation, and fiber optic equipment installation. - Commence design and construction of the lateral fiber builds from the Deltacom POP locations to the ILEC Central Offices in Cookeville, Oak Ridge, Cleveland, Sweetwater, and Morristown, Tennessee. | DeltaCom, Inc. | No issues at this time | No issues at this time.
NT10BIX5570034 | 2011 | Q1 | Q1 - 2011 | During this quarter DeltaCom completed Phase I of the project funded by the American Recovery and Reinvestment Act (ARRA) through the Broadband Technology Opportunity Program (BTOP). Phase I of the project included a network expansion of a diverse fiber optic route from Nashville to Knoxville and the lighting of a new diverse fiber optic route from Knoxville to Chattanooga. Fiber Optic transport equipment and prefabricated concrete buildings were installed in Oak Ridge, Tennessee; Cleveland, Tennessee; and Philadelphia, Tennessee. Fiber optic transport equipment was installed at existing facility locations in Nashville, Tennessee; Watertown, Tennessee; Cookeville, Tennessee; Knoxville, Tennessee; and Chattanooga, Tennessee. Work commenced on Phase II of the project in January 2011. Phase II of the project includes lighting a new fiber route from Knoxville, Tennessee to Bristol, Tennessee. During the first quarter of 2011, fiber optic transport equipment and prefabricated concrete shelters were installed in Morristown, Tennessee; Johnson City, Tennessee; and Bristol, Tennessee. Phase II of this project is forecasted to be complete in April 2011. During the quarter, twenty-one external laborers performed tasks associated with Fiber Optic Cable Installation. These tasks consisted of backhoe operation, general operation and common/general labor. Additionally, two laborers performed common/general labor tasks associated with Equipment Installation. This labor equated to | 0 | 8 | 335 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Nothing to report at this time | Nothing to report at this time3 | N/A | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom is creating competitive middle mile pricing that enables connectivity for last mile provider networks. We are also utilizing last mile providers to enable direct DeltaCom services to public anchor institutions in select markets at a 20% discount below our list pricing for qualifying broadband services. | FALSE | N/A | Phase II is scheduled for completion in April 2011. Phase II includes the lighting of a new fiber route from Knoxville, Tennessee to Bristol, Tennessee. Fiber optic transport equipment will be installed in the prefabricated concrete buildings located in Morristown, Tennessee; Johnson City, Tennessee; and Bristol, Tennessee. Detailed planning for Phase III of the project and outside plant make-ready work will commence in the second quarter of 2011. Phase III of the project is projected to be completed in the fourth quarter of 2011. Full Time Equivalent job creation for this quarter is expected to be minimal because DeltaCom did not seek funding for internal labor associated with this project and therefore, DeltaCom resources are not included in the Full Time Equivalent job creation calculations. | DeltaCom, Inc. | No issues at this time. | No additional issues at this time.
NT10BIX5570034 | 2011 | Q2 | Q2 - 2011 | The East Tennessee Middle Mile Fiber Broadband Project is approximately 76% complete as of June 30, 2011, with 68% of the awarded grant funds reimbursed to DeltaCom, Inc. as of June 30, 2011. During the second quarter of 2011, DeltaCom completed the Phase Two network expansion that included deployment of a new 131 mile fiber optic route from Knoxville, Tennessee to Bristol, Tennessee. Point of Presence (POP) sites along the route include: Knoxville, TN; Morristown, TN; Johnson City, TN; and Bristol, TN. As of June 30th, 474 fiber route miles have been deployed. Fiber Optic transport equipment was installed in Morristown, Tennessee; Johnson City, Tennessee; and Bristol, Tennessee. Phase Three of the project includes adding five new incumbent local exchange carrier interconnection points, including Cookeville, Oak Ridge, Cleveland, Sweetwater and Morristown, Tennessee, that are located in areas designated as under served. Work began in the second quarter on utility make-ready work associated with Phase Three and general project planning and procurement activities associated with Phase Three collocation access equipment. Additionally, during the second quarter, the remaining in-kind matching funds and cash matching funds were dedicated to the project. | 0 | 8 | 467 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Nothing to report at this time | Nothing to report at this time | N/A | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom is developing competitive pricing plans for middle mile connectivity and Community Anchor Institutions. Special offers for Community Anchor Institutions will include discounts of at least 20% below list pricing. | FALSE | N/A | DeltaCom will commence the lateral fiber builds from the Point of Presence locations, completed in Phase One and Two of this project, to the Incumbent Local Exchange Carrier interconnection collocation facilities. These facilities are located in five underserved markets in East Tennessee and include Cookeville, Oak Ridge, Cleveland, Sweetwater, and Morristown. The fiber construction portion of Phase Three will be complete by the end of the third quarter 2011. Equipment installation will commence at the interconnection collocation facilities in the third quarter 2011, but is not scheduled to be completed until the fourth quarter 2011. In support of the new markets, DeltaComâ€™s Sales and Marketing departments will continue Community Outreach activities. These activities will support the Sales Launch planned for the fourth quarter of 2011 in these new markets. | DeltaCom, Inc. | No issues at this time. | No issues anticipated at this time.
NT10BIX5570034 | 2011 | Q3 | Q3 - 2011 | As of September 30, 2011, the East Tennessee Middle Mile Fiber Broadband Project (the â€œProjectâ€) is approximately 82.4% complete with 77.4% of the awarded grant funds reimbursed to DeltaCom, Inc. During the third quarter of 2011, DeltaCom commenced Phase Three of the Project. Phase Three includes five construction fiber builds from the DeltaCom Point of Presence (â€œPOPâ€) sites to Incumbent Local Exchange Carrier (â€œILECâ€) collocation sites. During the third quarter, DeltaCom began four of the lateral builds to the ILEC collocation site. The ILEC collocation sites are located in the underserved Tennessee markets of Morristown, Oak Ridge, Cleveland and Sweetwater. At the end of the third quarter, Phase Three construction is 100% complete in Morristown, 95% complete in Oak Ridge, less than 50% complete in Cleveland, and less than 25% complete in Sweetwater. Collocation Access Equipment was procured and installed in four new ILEC sites including: Morristown, Oak Ridge, Cleveland, and Sweetwater, Tennessee. A new Interconnection Agreement was established with Frontier for the Cookeville, Tennessee ILEC interconnection site. | 20 | 8 | 467 | 0 | 20 | 0 | 0 | 0 | During the third quarter of 2011, DeltaCom completed the construction fiber build from DeltaCom's Point of Presence (â€œPOPâ€) site in Morristown, Tennessee, to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. Three additional fiber builds are scheduled to complete in the third quarter of 2011. The final fiber build is scheduled to complete in the first quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | No variance from the baseline | Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | During the third quarter of 2011, DeltaCom completed the construction fiber build from DeltaCom's Point of Presence (â€œPOPâ€) site in Morristown, Tennessee, to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. Three additional fiber builds are scheduled to complete in the third quarter of 2011. The final fiber build is scheduled to complete in the first quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | Due to the delayed start associated with Environmental Assessment approval date and additional make-ready delays, three of the planned interconnection points will be operational in the fourth quarter of 2011 and the remaining two interconnection points will be operational in the first quarter of 2012. DeltaCom's project is currently projected to complete in the first quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 0 | 0 | 0 | Nothing to report at this time | Nothing to report at this time | N/A | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom is developing competitive pricing plans for middle mile connectivity and Community Anchor Institutions. Special offers for Community Anchor Institutions will include discounts of at lease 20% below list pricing. | FALSE | N/A | In fourth quarter of 2011, DeltaCom is scheduled to complete the fiber builds from the DeltaCom Point of Presence (â€œPOPâ€) sites to Incumbent Local Exchange Carrier (â€œILECâ€) collocation sites located in Oak Ridge, Cleveland and Sweetwater, Tennessee. DeltaCom will complete equipment testing and activation of the collocation sites in Oak Ridge and Cleveland, Tennessee. Additionally, DeltaCom will commence fiber construction in Cookeville, Tennessee. By the end of fourth quarter 2011, 467 network miles will be upgraded, 32.3 new network miles will be deployed, 8 new network miles will be leased and 3 new interconnection points will be operational. DeltaCom does not forecast any CAIs connected or any signed agreements with broadband wholesales or last mile providers by the end of the fourth quarter 2011. | DeltaCom, Inc. | No issues at this time. | No issues anticipated at this time.
NT10BIX5570034 | 2011 | Q4 | Q4 - 2011 | As of December 31, 2011, the East Tennessee Middle Mile Fiber Broadband Project is approximately 88% complete with 79.53% of the federal grant funds received / invoiced. During the fourth quarter of 2011, DeltaCom completed four lateral fiber builds. The fiber builds connect the DeltaCom Point of Presence (POP) site to the Incumbent Local Exchange Carriersâ€™ (ILEC) collocation site in each service area. The ILEC collocation sites are located in the East Tennessee markets of Morristown, Oak Ridge, Cleveland and Sweetwater. Collocation site testing and activation is complete in Morristown and Oak Ridge. These areas are operational, and marketing activities are underway. Testing and activation is being finalized in the Cleveland and Sweetwater collocation sites in order to be operational in January 2012. The fifth fiber lateral build, located in Cookeville, Tennessee, has not started due to extended negotiations with make-ready and collocation vendors. This fiber build will begin when make-ready work is complete. Equipment installation will begin when collocation space is available and ready for occupancy in the ILEC collocation site. The estimated completion date for the Cookeville fiber lateral build is second quarter 2012. | 40 | 8 | 467 | 0 | 40 | 0 | 0 | 4 | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to complete in the second quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | No variance from the baseline | Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to complete in the second quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | Due to the delayed start associated with Environmental Assessment approval date and additional make-ready delays, the remaining interconnection point is expected to be operational in the second quarter of 2012. DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 2 | 0 | 12 | [REDACTED] | [REDACTED] | N/A | 2 | 0 | 0 | 5 | Metric is ahead of baseline. | No variance from the baseline. | N/A | Gig E - 1 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 1 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | Planned activities for first quarter 2012 include finalizing make-ready work and procurement. DeltaCom expects to finalize negotiations related to the Joint Use Pole Attachment Agreement (JUPA) with the incumbent local exchange carrier in Cookeville, Tennessee. Once the JUPA is in place, make ready work will begin in Cookeville. DeltaCom will also initiating procurement activity associated with obtaining collocation facility space in Cookeville. Procurement of equipment, required to connect Carrier Customers, Last Mile Providers, and Community Anchor Institutions to the network, will begin in first quarter 2012. DeltaCom will begin marketing and sales activity in the markets that are ready for service. These markets include Oak Ridge, Morristown, Cleveland, and Sweetwater, Tennessee. By the end of first quarter 2012, 467 network miles will be upgraded, 40.3 new network miles will be deployed, eight new network miles will be leased and four new interconnection points will be operational. DeltaComâ€™s baseline plan estimates that initial marketing and sales initiatives should result in five Community Anchor Institutions and three broadband wholesalers or last mile providers will receive service during the first quarter 2012. | DeltaCom, Inc. | Extended negotiations outlined above. | No issues anticipated at this time.
NT10BIX5570034 | 2012 | Q1 | Q1 - 2012 | As of March 31, 2012, the East Tennessee Middle Mile Fiber Broadband Project is approximately 89% complete with 84% of the federal grant funds received / invoiced. During the first quarter of 2012, DeltaCom completed the testing and activation of the Cleveland and Sweetwater collocation sites and both are service ready at this time. In addition, make ready work commenced on the final lateral build in Cookeville, TN. The fifth fiber lateral build, located in Cookeville, Tennessee, has not started due to extended negotiations with make-ready and collocation vendors. This fiber build will begin upon completion of the make-ready work. Equipment installation will begin when collocation space is available and ready for occupancy in the ILEC collocation site. The estimated completion date for the Cookeville fiber lateral build is second quarter 2012. | 40 | 8 | 467 | 0 | 40 | 0 | 0 | 4 | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to complete in the second quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | No variance from the baseline | Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to complete in the second quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | Due to the delayed start associated with Environmental Assessment approval date and additional make-ready delays, the remaining interconnection point is expected to be operational in the second quarter of 2012. DeltaCom's project is currently projected to complete in the third quarter of 2012, well in advance of the BTOP deadline of January 31, 2013. | 4 | 0 | 16 | [REDACTED] | [REDACTED] | N/A | 2 | 2 | 0 | 5 | In sync with baseline plan | In sync with baseline plan | In sync with baseline plan | Gig E - 1 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 3 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 1 | 0 | 1 | 3 | It is too early in the offer period to draw conclusions regarding customer responsiveness to the initial service offerings and pricing. DeltaCom will continue ongoing coordination with sales and marketing departments. Activities include monitoring outreach efforts and accurate sales reporting as well as participation by members of the grant implementation team, sales management team and executive management in the CAI/BTOP Conference on May 21, 22 and 23. We will continue to target CAIâ€™s identified in the Dunn & Bradstreet study that was part of the original grant application while seeking new opportunities and strategies. | It is too early in the offer period to draw conclusions regarding customer responsiveness to the initial service offerings and pricing. DeltaCom will continue ongoing coordination with sales and marketing departments. Activities include monitoring outreach efforts and accurate sales reporting as well as participation by members of the grant implementation team, sales management team and executive management in the CAI/BTOP Conference on May 21, 22 and 23. We will continue to target CAIâ€™s identified in the Dunn & Bradstreet study that was part of the original grant application while seeking new opportunities and strategies. | It is too early in the offer period to draw conclusions regarding customer responsiveness to the initial service offerings and pricing. DeltaCom will continue ongoing coordination with sales and marketing departments. Activities include monitoring outreach efforts and accurate sales reporting as well as participation by members of the grant implementation team, sales management team and executive management in the CAI/BTOP Conference on May 21, 22 and 23. We will continue to target CAIâ€™s identified in the Dunn & Bradstreet study that was part of the original grant application while seeking new opportunities and strategies. | Speed Tiers: 1.5 Mbps - 100Mbps 100 Mbps and up 500Mbps Please see the attached Retail Service Descriptions document for additional information regarding DeltaCom services. Current Subscriber: 1 - Ethernet from 50Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | DeltaCom plans to complete the lateral fiber build from the Cookeville, TN point of presence (POP) site to the Cookeville, TN Incumbent Local Exchange Carrier (ILEC) collocation facility. Make-ready for this ILEC collocation facility will be completed in May. DeltaCom will install the collocation site equipment and complete the testing and activation of the Cookeville, TN collocation site in June. Once this lateral fiber build is complete, this will add the final 3.4 miles to the project. DeltaCom plans to have a total of 12 Community Anchor Institutions connected to the network by the end of the second quarter. This is contingent on overall economic and market conditions in the respective service areas. DeltaCom also expects to have a total of five broadband wholesaler / last mile providers connected to the project. | DeltaCom, Inc. | Extended negotiations outlined above. | No issues anticipated at this time.
NT10BIX5570034 | 2012 | Q2 | Q2 - 2012 | As of June 30, 2012, the East Tennessee Middle Mile Fiber Broadband Project is approximately 92% complete. 90% of the grant funds have been expended with 86% of the federal grant funds received / invoiced. During the second quarter of 2012, DeltaCom completed the make ready work and lateral fiber build for the Cookeville, Tennessee Collocation site. The collocation site equipment build-out in Cookeville, Tennessee, has not started due to the collocation site not being completed and released by the collocation Incumbent Local Exchange Carrier (ILEC). Equipment installation will begin when collocation space is available and ready for occupancy in the ILEC collocation site. The estimated completion date for the Cookeville collocation site equipment build-out is third quarter 2012. DeltaCom has a total of one Community Anchor Institution and four broadband wholesaler / last mile provider agreements connected to the network. The project team has established biweekly calls with sales/marketing to ensure aggressive outreach to community anchor institutions including individually designed/priced service offerings where appropriate. | 40 | 8 | 467 | 0 | 40 | 0 | 0 | 4 | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to be active in the third quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | No variance from the baseline | Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | As of December 31, 2011, DeltaCom had completed four construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The final fiber build is scheduled to be active in the third quarter of 2012. Additional variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | Due to the delayed start associated with Environmental Assessment approval date and additional make-ready delays, the remaining interconnection point is expected to be operational in the third quarter of 2012. DeltaCom's project is currently projected to complete in the third quarter of 2012, with all expenditures being invoiced by the BTOP deadline of January 31, 2013. | 4 | 2 | 16 | [REDACTED] | [REDACTED] | N/A | 2 | 2 | 0 | 5 | In sync with baseline plan | In sync with baseline plan | In sync with baseline plan | Gig E - 1 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 3 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 1 | 0 | 1 | 3 | Variance from projected results is primarily due to the need for better Community Anchor Institution initiative integration with new product rollouts and company merger issues. The project team will continue coordination with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. | Variance from projected results is primarily due to the need for better Community Anchor Institution initiative integration with new product rollouts and company merger issues. The project team will continue coordination with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. | Variance from projected results is primarily due to the need for better Community Anchor Institution initiative integration with new product rollouts and company merger issues. The project team will continue coordination with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. | Speed Tiers: 1.5 Mbps - 100Mbps 100 Mbps and up 500Mbps Please see the attached Retail Service Descriptions document for additional information regarding DeltaCom services. Current Subscriber: 1 - Ethernet from 50Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | DeltaCom will install the collocation site equipment and complete the testing and activation at the Cookeville, Tennesse Incumbent Local Exchange Carrier's collocation facility. Upon completion of these activities, the final lateral fiber build will be in-service adding 3.4 miles to the total new fiber miles deployed. In addition, DeltaCom will begin final payment of invoices and project close out activities. DeltaCom will continue to market our services in the effort to reach the goal of 19 Community Anchor Institutions and seven broadband wholesaler / last mile providers connected to the project by the end of the third quarter contingent on overall economic and market conditions in the respective service areas. | DeltaCom, Inc. | Extended negotiations outlined above. | No issues anticipated at this time.
NT10BIX5570034 | 2012 | Q3 | Q3 - 2012 | As of September 30, 2012, the East Tennessee Middle Mile Fiber Broadband Project network implementation is 100% complete with 86% of the federal grant funds received / invoiced. During the third quarter of 2012, DeltaCom completed the remaining lateral fiber build in Cookeville, Tennessee and completed the installation, testing, and turn up of the collocation site equipment. The completion of the Cookeville, Tennessee lateral fiber build completes the construction for this project. DeltaCom has a total of one Community Anchor Institution and nine broadband wholesaler / last mile provider agreements connected to the network. The project team has established biweekly calls with sales/marketing to ensure aggressive outreach to community anchor institutions including individually designed/priced service offerings where appropriate. | 44 | 10 | 470 | 0 | 44 | 0 | 0 | 5 | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | The 8 mile variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. The remaining 2 miles of additional variance is due to a true-up of the TVA miles leased by DeltaCom. | Original variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. The additional 5.3 miles of variance is due to the need to reach the Electrical Power Board fiber IRU from the Chattanooga Point of Presence. | N/A | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | All interconnection points are operational and all expenditures will be invoiced by the BTOP deadline of January 31, 2013. | 9 | 0 | 10 | [REDACTED] | [REDACTED] | N/A | 2 | 7 | 0 | 9 | Consistent with baseline projection | Consistent with baseline projection | Consistent with baseline projection | Gig E - 2 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 7 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 1 | 0 | 1 | 3 | Variance from projected results has been affected by the need for Community Anchor Institution sales integration with new product rollouts and company merger issues. The project team continues to coordinate with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. Additionally, the sales team has attempted to contact all Community Anchor Institutions listed on the original Dunn and Bradstreet list included in the grant application and will continue to follow up with leads. | Variance from projected results has been affected by the need for Community Anchor Institution sales integration with new product rollouts and company merger issues. The project team continues to coordinate with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. Additionally, the sales team has attempted to contact all Community Anchor Institutions listed on the original Dunn and Bradstreet list included in the grant application and will continue to follow up with leads. | Variance from projected results has been affected by the need for Community Anchor Institution sales integration with new product rollouts and company merger issues. The project team continues to coordinate with sales and marketing departments to insure sales representatives are focused on Community Anchor Institutions in the grant areas. Activities include biweekly calls with sales marketing teams, aggressive Community Anchor Institution offers/acquisition initiatives and frequent progress reporting. Additionally, the sales team has attempted to contact all Community Anchor Institutions listed on the original Dunn and Bradstreet list included in the grant application and will continue to follow up with leads. | Speed Tiers: 1.5 Mbps - 100Mbps 100 Mbps and up 500Mbps Please see the attached Retail Service Descriptions document for additional information regarding DeltaCom services. Current Subscriber: 1 - Ethernet from 50Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | DeltaCom will begin project closeout activities, final invoice payment, reimbursement of allowable project cost, and grant closeout activities in the fourth quarter of 2012. DeltaCom will continue to market our services in the effort to reach Community Anchor Institutions and broadband wholesaler / last mile providers. Based on overall economic and market conditions, DeltaCom expects to connect 5 additional Community Anchor Institutions to the network by January 31, 2012. | DeltaCom, Inc. | No issues or challenges at this time. | No issues anticipated at this time.
NT10BIX5570034 | 2012 | Q4 | Q4 - 2012 | The East Tennessee Middle Mile Fiber Broadband Project network implementation is 100% complete with 90% of the federal grant funds received / invoiced. DeltaCom began final invoice payment, reimbursement of allowable project cost, and grant closeout activities in the fourth quarter of 2012. DeltaCom has continued to offer services to Community Anchor Institutions and broadband wholesaler / last mile providers. DeltaCom has a total of two Community Anchor Institutions and eight broadband wholesaler / last mile provider agreements connected to the network. | 44 | 10 | 475 | 0 | 44 | 0 | 0 | 5 | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | The 8 mile variance from the baseline is detailed in the approved Route Change Request dated 12/103/2010. The remaining 2 miles of additional variance is due to a true-up of the TVA miles leased by DeltaCom. | Original variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. The additional 5.3 miles of variance is due to a true-up of the TVA miles leased by DeltaCom. | N/A | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | All interconnection points are operational. | 8 | 0 | 10 | [REDACTED] | [REDACTED] | N/A | 2 | 6 | 0 | 5 | Consistent with baseline projection | Consistent with baseline projection | Consistent with baseline projection | Gig E - 2 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 6 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 2 | 0 | 2 | 3 | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Speed Tiers: 1.5 Mbps - 100Mbps 100 Mbps and up 500Mbps Please see the attached Retail Service Descriptions document for additional information regarding DeltaCom services. Current Subscribers: 1 - Ethernet from 50Mbps 1 - Ethernet from 10Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | DeltaCom will continue project closeout activities, final invoice payment, reimbursement of allowable project cost, and grant closeout activities in the first quarter of 2013. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. The sales team is currently engaged with several potential CAI customers; however, we are unable to project sales that will close during the first quarter of 2013. | DeltaCom, Inc. | No issues or challenges at this time. | No issues anticipated at this time.
NT10BIX5570034 | 2013 | Q1 | Q1 - 2013 | The East Tennessee Middle Mile Fiber Broadband Project network implementation is 100%. DeltaCom will continue to offer services to Community Anchor Institutions and broadband wholesaler / last mile providers. DeltaCom has a total of two Community Anchor Institutions and eight broadband wholesaler / last mile provider agreements connected to the network. | 44 | 10 | 475 | 0 | 44 | 0 | 0 | 5 | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | The 8 mile variance from the baseline is detailed in the approved Route Change Request dated 12/103/2010. The remaining 2 miles of additional variance is due to a true-up of the TVA miles leased by DeltaCom. | Original variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. The additional 5.3 miles of variance is due to a true-up of the TVA miles leased by DeltaCom. | N/A | DeltaCom has completed all five construction fiber builds from DeltaCom's Point of Presence (â€œPOPâ€) sites to the Incumbent Local Exchange Carrier (â€œILECâ€) collocation site. The total new network miles deployed is 43.7 miles. Variance from the baseline is detailed in the approved Route Change Request dated 12/13/2010. | N/A | N/A | All interconnection points are operational. | 8 | 0 | 10 | [REDACTED] | [REDACTED] | N/A | 2 | 6 | 0 | 5 | Consistent with baseline projection | Consistent with baseline projection | Consistent with baseline projection | Gig E - 2 Subscribers 2.5 Gig - 0 Subscribers 10 Gig - 6 Subscribers OC-3 - 0 Subscribers OC-12 - 0 Subscribers | 2 | 0 | 2 | 3 | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Variance from projected results has been affected by lower retail demand than anticipated at the time of our application and competitive pressure from incumbent carriers in the project area. The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. | Speed Tiers: 1.5 Mbps - 100Mbps 100 Mbps and up 500Mbps Please see the attached Retail Service Descriptions document for additional information regarding DeltaCom services. Current Subscribers: 1 - Ethernet from 50Mbps 1 - Ethernet from 10Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | DeltaCom has launched pricing plans for each market based on providing business class internet, voice and data services to end user businesses in the markets served by the project. DeltaCom will provide a 20% discount for any anchor institutions off the standard product offerings. We may provide custom quotes for non-standard bandwidth offerings or configurations to meet the needs of these institutions. | FALSE | N/A | The DeltaCom sales team continues to target CAIs and expects to meet our original estimates at some point in the future. Economic growth and existing CAI customers exiting contracts with other carriers should provide increased sales opportunities. The sales team is currently engaged with several potential CAI customers; however, we are unable to project sales that will close in 2013. | DeltaCom, Inc. | No issues or challenges at this time. | No issues anticipated at this time.
NT10BIX5570035 | 2010 | Q3 | Q3 - 2010 | Submission of Recovery Act Report. Submission of Financial and Performance Progress Reports. Preparation and Submission of draft Environmental Assessment. Contacts with WV State Historic Preservation Office (â€œSHPOâ€) to conduct Section 106 consultation. Review of WV SHPO archives by qualified archaeologist. Site visits by archaeologist and environmental consultant to view network route. Development of detailed maps of historical and cultural resources sites along network route and archaeologist report of potential impacts of deployment. Contact with US Fish & Wildlife Service Ecological Services Offices to conduct Section 7 consultation, and submission of detailed route maps and project description. Discussions and review of documents by NTIA legal staff and Hardyâ€™s existing lenders to develop mutually agreeable terms and conditions of co-first security interest. Request for reclassification of line item budget items in connection with deployment of aerial fiber on existing poles in previously disturbed Rights of Way to connect education institutions and provide for needed network geo-diversity. Deployment required by education institutions to meet eRate timeline for service initiation, and to prevent communications outages in the area. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting written confirmation of acceptance by NTIA of co-first priority, pari passu security interest by NTIA and Hardy's existing first priority secured lenders. | Same as above | Same as above | Same as above | Same as above | Same as above | Same as above | Same as above | 0 | 0 | 0 | Not applicable. Network not yet deployed. | Not applicable. Network not yet deployed. | No third party operator. | 0 | 0 | 0 | 0 | Network not yet deployed, awaiting confirmation of co-first priority security interest, as detailed above. | Same as above | Same as above | Same as above | 0 | 0 | 0 | 0 | Same as above | Same as above | Same as above | Same as above | 0 | 0 | 0 | 0 | 0 | Award funded deployment not yet started | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | Award funded deployment not yet started | NA | NA | NA | Award funded deployment not yet started | Network deployment not completed. | FALSE | Not applicable. | Completion of Section 106 and Section 7 consultations, final update of environmental assessment, and finding of no significant impact. Completion of outside plant network design. Outside plant staking completed. Permits approved. Preparation of pre-bid contract documents. Requests for Quotations issued to contractors and distributors, and responses received. Equipment and materials purchases to begin when written notification received from NTIA of co-first priority security interest with Hardy existing first priority secured lenders. | Hardy Telecommunications, Inc. | 1) Resolution of co-first priority, pari passu security interest with Hardyâ€™s current first priority secured lenders. 2) Ongoing review by NTIA of request for reclassification of line item budget items for network deployment to meet critical need of education CAIs to comply with eRate deadline for service initiation and to prevent network outages. Deployment was performed from Hardyâ€™s own funds due to delay in resolution of co-first security interest requirement and NTIA requirement for environmental assessment (see #3). 3) NTIA restriction on award-funded aerial deployment on existing poles in previously disturbed Rights of Way as required by education institutions due to NTIA Environmental Assessment requirement and grant of only limited categorical exclusions to NEPA, which are not required by USDA-RUS for the same work. | NTIA confirmation of co-first priority security interest between NTIA and existing lenders, as previously discussed. Reclassification of Line Item Budget items, as previously discussed. Hardy Telecommunications has also received a BIP award from RUS, performance of which is dependent in part upon performance of the BTOP award. RUS has granted categorical exclusions to NEPA and does not require an EA. RUS will allow non-ground disturbing or land clearing activities to begin immediately upon release of BIP funds. BTOP has not granted categorical exclusions to NEPA and does require an EA, preventing construction before obtaining a FONSI. If NTIA and RUS could coordinate on NEPA categorical exclusions, Hardy could begin aerial deployment on existing poles in previously disturbed ROWs.
NT10BIX5570035 | 2010 | Q4 | Q4 - 2010 | Historic Preservation package submitted. Environmental approval. Field engineering 106 miles. Obtained private right of way. In process Highway Dept. permitting. State conservation engineering. Rural Development Assn. permitting. Water permit at Baker WV. Construction safety procedures & review by Highway Dept. Planning for entrances into Hardy remotes. Commercial discussions with inside plant equipment vendor, inside plant installation/cut-over vendor, materials vendors and contractors. Inside plant fiber termination plan. Facility requirements analysis. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Intercreditor Agreement and Historic Preservation Review. | N/A | Pending Intercreditor Agreement and Historic Preservation Review. | N/A | Pending Intercreditor Agreement and Historic Preservation Review. | N/A | N/A | Pending Intercreditor Agreement and Historic Preservation Review. | 0 | 0 | 0 | N/A | N/A | No third party operator planned. | 0 | 0 | 0 | 0 | Pending Intercreditor Agreement and Historic Preservation Review. | Pending Intercreditor Agreement and Historic Preservation Review. | Pending Intercreditor Agreement and Historic Preservation Review. | Pending Intercreditor Agreement and Historic Preservation Review. | 0 | 0 | 0 | 0 | Pending Intercreditor Agreement and Historic Preservation Review. | Same as above | Same as above | Same as above | 0 | 0 | 0 | 0 | 0 | Pending Intercreditor Agreement and Historic Preservation Review. | Middle Mile only | Middle Mile only | Middle Mile only | Middle Mile only | 0 | 0 | 0 | 0 | 0 | Pending Intercreditor Agreement and Historic Preservation Review. | Middle Mile only | Middle Mile only | Middle Mile only | Middle Mile only | N/A | FALSE | N/A | Conclude Historic Preservation Review. Intercreditor Agreement approvals by NTIA and existing lender. Signed permits from Highway Dept. Construction Drawings finalized. Sign private easements needed for construction. Issue construction contracts. Begin issuing equipment contracts. Issue contract for electronics and installation services. Purchase and installation of equipment at one central office. Benchmark cutover and provisioning for replication to twenty other central offices. Port voice traffic to newly installed electronics. | Hardy Telecommunications, Inc. | 1) Timeframe for Historic Preservation review; 2) Timeframe for Intercreditor Agreement approval. 3) Issues with Post-Award Management System log-in during reporting window It would be helpful for BTOP Help Desk staff to remain available by phone during the reporting window. | No challenges anticipated if Intercreditor Agreement and Historic Preservation Review are concluded.
NT10BIX5570035 | 2011 | Q1 | Q1 - 2011 | An Intercreditor Agreement was approved by the National Telecommunications & Information Administration (â€œNTIAâ€) and an existing lender in March 2011. This was a significant project accomplishment, allowing Hardy to seek reimbursement of project expenditures for the first time since award notification in March 2010. Project expenditures funded by Hardy through March 31, 2011 totaled $1,020,681. Prior to approval of the Intercreditor Agreement, a reimbursement to Hardy would constitute a breach of loan covenants with respect to the lenderâ€™s first security interest. In 1st quarter 2011, Hardy completed revisions to its Environmental Assessment of October, 2010 and provided an Archaeological report, as requested by NTIA. Hardy complied with a comprehensive document request relating to environmental compliance, project progress and expenditures required by the Grants Management Office. Upon receipt of the revised Environment Assessment from NTIA, the WV State Office of Historic Preservation (â€œSHPOâ€) completed a Cultural & Historic Resources Review and notified NTIA that no further consultation was required for aerial deployment, although a Phase 1 archaeological survey of 9.3 miles of buried line was required, and adherence to best practice management for connection of broadband equipment to historic structures. Completion of the revised environmental assessment, archaeological report, and Historic & Cultural Resources review by WV SHPO were material undertakings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 miles of the planned 117-mile network were forecasted to be completed by March 31, 2011. Variance is a direct result of delays in obtaining approvals of an Intercreditor Agreement by NTIA and an existing lender, delays in NTIA's review of Hardyâ€™s environmental assessment submitted in October, 2010, completion of revisions and an archaeological report requested by NTIA in January, 2011, and completion of an Historic and Cultural Resources Review by WV State Office of Historic Preservation. As of March 31, 2011 a Finding of No Significant Impact had not been issued by NTIA, precluding materials procurement and deployment commencement. The timeline for deployment is approximately twelve months. Barring any future delays beyond Hardyâ€™s control, the network can be completed within 36 months of award date of February 28, 2010 as required by grant program rules. | NA | Same as above | N/A | Same as above | N/A | N/A | Same as above Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) 78 miles of the planned 117-mile network were forecasted to be completed by March 31, 2011. Variance is a direct result of delays in obtaining approvals of an Intercreditor Agreement by NTIA and an existing lender, delays in NTIA's review of Hardy’s environmental assessment submitted in October, 2010, completion of revisions and an archaeological report requested by NTIA in January, 2011, and completion of an Historic and Cultural Resources Review by WV State Office of Historic Preservation. As of March 31, 2011 a Finding of No Significant Impact had not been issued by NTIA, precluding materials procurement and deployment commencement. The timeline for deployment is approximately twelve months. Barring any future delays beyond Hardy’s control, the network can be completed within 36 months of award date of February 28, 2010 as required by grant program rulese your reasons for any variance from the baseline plan or any other relevant information) 78 miles of the planned 117-mile network were forecasted to be completed by March 31, 2011. Variance is a direct result of delays in obtaining approvals of an Intercreditor Agreement by NTIA and an existing lender, delays in NTIA's review of Hardy’s environmental assessment submitted in October, 2010, completion of revisions and an archaeological report requested by NTIA in January, 2011, and completion of an Historic and Cultural Resources Review by WV State Office of Historic Preservation. As of March 31, 2011 a Finding of No Significant Impact had not been issued by NTIA, precluding materials procurement and deployment commencement. The timeline for deployment is approximately twelve months. Barring any future delays beyond Hardy’s control, the network can be completed within 36 months of award date of February 28, 2010 as required by grant program rules. | 0 | 0 | 0 | N/A | N/A | No Third Party Operator | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Hardy forecasted 29 total subscribers by the end of Q1 2011, but network deployment had not yet begun. This variance is a direct result of delays in obtaining approvals of an Intercreditor Agreement by NTIA and an existing lender, delays in NTIA's review of Hardyâ€™s environmental assessment submitted in October, 2010, completion of revisions and an archaeological report requested by NTIA in January, 2011, and completion of an Historic and Cultural Resources Review by WV State Office of Historic Preservation. As of March 31, 2011 a Finding of No Significant Impact had not yet been issued by NTIA, precluding materials procurement and deployment commencement. The timeline for deployment is approximately twelve months. Barring any future delays beyond Hardyâ€™s control, the network can be completed within 36 months of award date of February 28, 2010 as required by program rules. | N/A | Hardy forecasted 29 subscribers receiving improved access by end of Q1 2011, but network deployment had not yet commenced. This variance is a direct result of delays in obtaining approvals of an Intercreditor Agreement by NTIA and an existing lender, delays in NTIA's review of Hardyâ€™s environmental assessment submitted in October, 2010, completion of revisions and an archaeological report requested by NTIA in January, 2011, and completion of an Historic and Cultural Resources Review by the WV State Office of Historic Preservation. As of March 31, 2011 a Finding of No Significant Impact had not yet been issued by NTIA, precluding materials procurement and deployment commencement. The timeline for deployment is approximately twelve months. Barring any future delays beyond Hardyâ€™s control, the network can be completed within 36 months of award date of February 28, 2010 as required by grant program rules. | Network deployment not yet begun. Same as above. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Approval of Environmental Assessment and release of Finding of No Significant Impact by NTIA. Submission of request for reimbursement of expenditures and draw-down of funds. Completion of Phase 1 archaeological survey and shovel testing as required by NTIA and WV State Historic Preservation Office for a 9.3 mile buried section and building sites. Obtain WV Department of Transportation permitting approvals. WV State Environmental Agency approval for section of line in a flood control area, or an approximate 5-mile reroute to avoid area. Fiber-optic cable order placement for Phases 1 and 2 of construction. Bid documents release to Outside Plant Contractors and award(s). Execution of contract with major electronics vendor. Electronics ordered for nine remote facilities, installation and testing. | Hardy Telecommunications, Inc. | On March 25, 2011, The WV State Historic Preservation Office concluded its review with no further consultation required for aerial deployment; however a Phase 1 archaeological survey and shovel testing to discover artifacts is required for a 9.3-mile buried section of line and building placement sites. Hardy's archaeological services provider has begun a review of rights of way as required for this section, with no artifiacts found to date. If artifacts are discovered, it may delay deployment of buried sections of line; however those sections may be rerouted if necessary. The WV Environmental Agency's approval is required for a section of line to be placed in a flood control area. The Line can be rerouted in a 5-mile section to avoid the flood control area if necessary. Fiber-optic cable order fulfillment time has increased from 12 to 16 weeks due to worldwide demand for fiber and an overall decrease in global manufacturing capacity after earthquake and tsunami damage in Japan. While these issues have impacted deployment timelines, the expected completion date is within the timeframe allowable under program rules. | NTIA and the WV State Historic Preservation Office require a Phase 1 archaeological survey and shovel testing to discover artifacts in a planned 9.3-mile buried section of line and building placement sites. If artifacts are discovered, it may delay deployment of buried sections of line; however those sections may be rerouted if necessary. The WV Environmental Agency's approval is required for a section of line to be placed in a flood control area. The Line can be rerouted in a 5-mile section to avoid the flood control area if necessary. Fiber-optic cable order fulfillment time has increased from 12 to 16 weeks due to worldwide demand for fiber and an overall decrease in global manufacturing capacity after earthquake and tsunami damage in Japan. While these issues may impact deployment timelines, the expected completion date is within the timeframe allowable under program rules.
NT10BIX5570035 | 2011 | Q2 | Q2 - 2011 | Hardy Telecommunications is the recipient of a Broadband Technology Opportunities Program ("BTOP") Middle Mile Network Infrastructure award and a Broadband Initiatives program ("BIP") Last Mile Fiber to the Premise award. In the second quarter of 2011, the designs for BTOP and BIP outside plant and network access were revised to produce technical and cost efficiencies by leveraging the infrastructure of the two awards. Archaeological shovel testing commenced in connection with a phase 1 survey of an approximate 9.3-mile area of buried line. Hardy substantially completed public and private permitting and staking. Construction drawings were prepared, materials units and labor units were identified and quantified, and specifications were prepared, in connection with requests for proposals for construction of all four phases of the BTOP network. Orders for fiber-optic cable and major construction materials were placed. A major equipment contract was renegotiated; pricing, quantities, and shipment dates were finalized. Hardy submitted a Recovery Act Report, a Performance Progress Report and a Financial Report for first quarter, 2011, and reimbursed expenditures through draw downs of award funds. Hardy created 6.7 jobs and made project expenditures of $193,929 during the three-month period ended June 30, 2011. | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 117 miles of the planned Middle Mile network were forecasted to be completed by June 30, 3011. Variance is a result of a number of delays in obtaining approvals, including for an Intercreditor Agreement by NTIA and an existing lender, and approval by NTIA of Hardyâ€™s environmental assessment. Aerial deployment may now commence upon awards of construction contracts, but approximately construction of 9.3 miles of buried line may not commence until completion of a Phase I archaeological survey and approval by the WV State Historic Preservation Office. | NA | 15 miles of connectivity to anchor institutions and a portion of an upstream Internet route were contributed by Hardy to the Project. | NA | Same as above | NA | NA | Same as above | 0 | 0 | 0 | NA | NA | No third party operator | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 9 | 0 | 9 | 5 | Construction delayed pending approvals by NTIA, and WV State Historic Preservation Office requirement for a Phase 1 archaeological survey for area of buried line. | None | Nine subscribers | Speed Tiers are 10 Mbps (8 subscribers), 20 Mbps (1 subscribers), 50 Mbps (0 Subscribers), 100 Mbps (0 Subscribers), and 1 Gbps (0 Subscribers). | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None | FALSE | NA | Request for Proposals conference, negotiations and award of contract(s) for construction of all four phases of Middle Mile network. Aerial Construction will commence September 26, 2011. Make-ready is included in construction activities. Major materials being furnished by Hardy. Fiber-optic cable shipments will be received and tested prior to construction commencement. Contractor and inspector training to begin September 12, 2011. Environmental and historical preservation training will begin September 22, 2011. New CAIs and mileage deployed will be zero in 3Q2011 considering construction commencement date of September 26, 2011. Completion of Phase 1 survey report and submission to NTIA and WV State Historic Preservation Office. Major electronics order placed. Equipment installation begins. If NTIA and WV State Historic Preservation office approve Phase 1 Survey, building will be ordered and site prep will begin. | Hardy Telecommunications, Inc. | The WV State Historic Preservation Office ("WV-SHPO") requires a Phase 1 archaeological survey and shovel testing to discover artifacts in a 9.3-mile area of buried line and building placement sites. Shovel testing every 50 feet along the area of buried line is underway, with no significant artifacts found to date Lab analysis of any artifacts that may be found and preparation of the final report for WV-SHPO will be extensive and will further delay buried deployment. Aerial deployment may commence as soon as contracts are awarded, but deployment may not be completed until WV-SHPO approves buried placement. | WV State Historic Preservation Office approval of Phase 1 archaeological survey and report of archaeologist.
NT10BIX5570035 | 2011 | Q3 | Q3 - 2011 | Hardy Telecommunications achieved the following objectives in Q3 2011: Fiber-optic cable and major construction materials ordered and received. Fiber-optic cable testing performed. Contractors' qualifications evaluated. Request for proposals for outside plant construction prepared and issued. Contractors conference held. Contractor proposals evaluated and negotiated. Contracts prepared and construction contracts awarded. Safety and environmental/archaeological best practices management information provided to contractors by WV Dept. of Highways and consultants. Outside plant construction of aerial fiber optic-cable commenced September 26, 2011. As of September 30, 2011, 106 route miles have been staked. 92 rights of way have been acquired. 189 construction drawings have been produced. 6.2 miles of aerial fiber-optic cable have been placed. A fiber termination plan for each facility and equipment configurations were developed. A final site survey of facilities receiving network access equipment was conducted, and relay rack configurations were identified. Network access equipment was installed at three central office locations and cutover activities commenced. An engineered splice plan was completed for the entire core ring. Archaeological shovel testing of buried fiber-optic cable routes was completed, and a Phase 1 archaeological survey report was submitted to the National Telecommunications & Information Administration ("NTIA") and the West Virginia S | 6 | 0 | 15 | 0 | 21 | 0 | 0 | 0 | 117 miles of the planned Middle Mile network were forecasted to be completed by June 30, 3011. Variance is a result of a number of delays in obtaining approvals, including for an Intercreditor Agreement by NTIA and an existing lender, and approval by NTIA of Hardyâ€™s environmental assessment. Aerial deployment may now commence upon awards of construction contracts, but approximately construction of 9.3 miles of buried line may not commence until completion of a Phase I archaeological survey and approval by the WV State Historic Preservation Office. | NA | 15 miles of connectivity to anchor institutions and a portion of an upstream Internet route were contributed by Hardy to the Project. | NA | Same as above | NA | NA | Same as above | 0 | 0 | 0 | NA | NA | No third party operator | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 9 | 0 | 9 | 5 | Construction delayed pending approvals by NTIA, and WV State Historic Preservation Office requirement for a Phase 1 archaeological survey for area of buried line. | None | Nine subscribers | Speed Tiers are 10 Mbps (8 subscribers), 20 Mbps (1 subscribers), 50 Mbps (0 Subscribers), 100 Mbps (0 Subscribers), and 1 Gbps (0 Subscribers). | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None | FALSE | NA | Review of report of Phase 1 archaeological shovel testing by the National Telecommunications & Information Administration (â€œNTIAâ€) and the West Virginia State Historic Preservation Office (â€œWV-SHPOâ€), and approvals to commence construction of buried fiber, expected to be completed in fourth quarter, 2011. Upon approval, buried construction will commence for approximately 5.4 miles. Barring hazardous snow and ice storms, outside plant construction of approximately 107 miles of the Hardy AnchorRing core ring is expected to be 90% completed by the end of fourth quarter 2011. Fiber termination equipment will be ordered and received. Requests for Proposals for fiber-optic cable splicing will be issued, proposals evaluated, and contracts awarded at which time splicing will commence. Engineering for one anchor institution lateral is expected to be completed. Network access equipment will be installed and tested at five central office locations, at which time service cutover will commence. No new CAIs are expected to be connected in 4th quarter 2011. Hardy expects outside plant construction of the core ring to be completed depending upon weather conditions, but deployment of laterals and customer premises equipment is not expected to begin until first quarter 2012. Hardy is in discussions with one last mile service provider, which may result in a signed agreement by year-end 2011 depending upon continued interest and timing of the service provider. | Hardy Telecommunications, Inc. | No significant challenges | Delays in obtaining approvals from National Telecommunications & Information Administration and West Virginia State Historic Preservation Office for buried deployment of approximately 5.4 miles.
NT10BIX5570035 | 2011 | Q4 | Q4 - 2011 | Project is substantially complete at 70.1%. As of 12-31-2011, 76.6 miles of cable had been placed, with splicing complete for three spans and nodes placed in service at 10 Gigabits/second. Other completion as of 12-31-2011: Backbone staking 100%, Backbone Rights of Way, 97%, approximately 75% of Backbone ring construction completed. 100% of fiber termination equipment installed in central offices by year-end. Rights of way and engineering for laterals to anchor institutions in progress. Some re-engineering of anchor institution laterals required due to closures, relocations, and new requests to be connected. | 76 | 0 | 15 | 0 | 76 | 0 | 0 | 5 | (35)% Variance. Delays in materials procurement and construction commencement due to intercreditor agreement delays and requirement for Phase 1 Archaeological Shovel Testing. | NA | 15 miles of connectivity to anchor institutions and a portion of an upstream Internet route were contributed by Hardy to the Project. | NA | (35)% Variance. Same as New network miles deployed. | NA | NA | (76)% Variance. Delays in materials procurement and construction commencement due to intercreditor agreement delays and requirement for Phase 1 Archaeological Shovel Testing. The Backbone network ring is not complete, but spans between facilities on-net have been constructed and 10-Gigabit service turned up at 5 locations. | 0 | 0 | 0 | No wholesale agreements have been requested. | No wholesale providers have requested agreements. | Hardy Telecommunications does not outsource network operation. | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 10 | 0 | 10 | 5 | (89)% Variance. Delays in construction commencement due to Intercreditor Agreement, archaeological Phase 1 shovel testing. Transport service is available up to 1 Gbps to seven school sites and 3 cellular towers. | NA | (89)% Variance. Same as above. | Transmission speed tiers: 10-Mbps, 5 subscribers. 20-Mbps, 2 subscribers sharing service for a total of 10-Mbps each. 50-Mbps, 0 subscribers. 100-Mbps, 0 subscribers; 1-Gbps, 0 Subscribers. 3 Cellular sites connected at up to 1-Gbps per site, but no carriers have subscribed to date. | 0 | 0 | 0 | 0 | 0 | Middle Mile Only | Middle Mile Only | Middle Mile Only | Middle Mile Only | Middle Mile Only | 0 | 0 | 0 | 0 | 0 | Middle Mile only | Middle Mile only | Middle Mile only | Middle Mile only | Middle Mile only | No special offerings are provided at this time. | FALSE | Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.com/images/stories/PDfs/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | 28 miles of backbone ring construction, splicing and testing will be completed, which will complete the core ring. A modification request for community anchor institutions will be provided to NTIA for approval. Modifications are due to facility closures, relocations, and new requests for connectivity. For all approved modifications and additions, engineering will be completed by 2-20-2012, rights of way acquired, and clearances obtained from West Virginia State Historic Preservation office for ground-disturbing construction. Pending approvals from NTIA and WV-SHPO, construction of community anchor institution laterals will commence. Orders for network access equipment, facilities equipment, and customer premises equipment to be placed in first quarter. Community anchor institutions requesting service will be turned up as laterals and drops are placed. Requests for service by broadband wholesalers or last mile providers are not expected in Q1-2012. | Hardy Telecommunications, Inc. | No challenges encountered in the quarter ended 12/31/2011 during construction of the core backbone ring. | Construction delays in deployment of anchor institution laterals may occur if approval of modifications and route changes are delayed by NTIA, or if extensive environmental studies are required by NTIA or phase 1 archaeological surveying is required by WV State Historic Preservation Office. Anchor institution lateral deployment is primarily aerial.
NT10BIX5570035 | 2012 | Q1 | Q1 - 2012 | Backbone Ring Construction: Phases 1, 4, and 5 complete pending inspection and close-out. Historic preservation roadblock cleared for Phase 2. Rock trenching completed for Phase 3. Aerial construction completed for Phase 6; cable installation in progress. 90.5 miles of backbone ring fiber and 5.5 miles of conduit placed. As-builts in progress. 109 ROWs requested with 99 completed. All remote locations but two spliced. Optical Time Domain Reflectometer (â€œOTDRâ€) testing in progress. Lasers for electronics received and installed except 80 kilometer optics still on order. Final engineering and splicing schematics for Community Anchor Institutions (â€œCAIsâ€) underway. Material orders placed for CAIs. Eight CAI locations shovel tested to determine potential effects of buried construction on historic and cultural resources. | 96 | 0 | 15 | 0 | 96 | 0 | 0 | 20 | (17)% Variance. Delays in construction commencement as previously noted. | N/A | 15 miles of connectivity to community anchor institutions and a portion of an upstream Internet route were contributed by Hardy to the project. | N/A | (17)% Variance. Same as New network miles deployed. | N/A | N/A | (4.8)% Variance. Delays in materials procurement and construction commencement due to Intercreditor Agreement, environmental and historic preservation assessments and shovel testing surveys prevented earlier completion of backbone ring interconnecting facilities. | 1 | 0 | 8 | Lumos Networks | 155 Mbps transport | No third party operator. | 1 | 0 | 0 | 0 | Baseline value was "N/A" | Baseline value was "N/A" | Baseline value was "N/A" | 10 Mbps to 1 Gbps. 1 Subscriber for 155 Mbps service. | 10 | 0 | 10 | 5 | (89)% Variance. Delays in commencement of construction as previously discussed. Transport service is available up to 1-GigE to seven school sites and three cellular towers. Final engineering and materials procurement for remaining CAIs underway. | N/A | (89)% Variance. Same as above. | Transmission speed tiers: 10-Mbps, 5 subscribers; 20-Mbps, 2 subscribers sharing service for a total of 10-Mbps each. 50-Mbps, 0 subscribers. 100-Mbps, 0 subscribers. 1-GigE, 0 subscribers. 3 cellular sites connected at up to 1-GigE per site, but carriers have not subscribed due to requirement to replace legacy equipment upstream. | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | 0 | 0 | 0 | 0 | 0 | Middle MIle | Middle Mile | Middle Mile | Middle Mile | Middle Mile | No special offerings are provided at this time. | FALSE | No changes over the last quarter. | Approximately 22 miles of new construction including laterals to CAIs. Completion of backbone ring construction, inspection, splicing, testing and as-builts. Completion of equipment and electronics installation. Completion of archaeological shovel testing and survey report for community anchor institution ("CAI") laterals. Approval by West Virginia State Historic Preservation Office and the National Telecommunications & Information Administration to commence buried deployment for CAI laterals. Placement of splice cases and splicing along the backbone ring completed for service availability to 91 CAIs. Procurement of CPE and installation for CAIs ordering services. No additional agreements with wholesale/last mile service providers are anticipated next quarter. Hardy anticipates a rebudget request to move all remaining savings obtained in the line item categories equipment, facilities, operating equipment, site work, demolition and removal, and construction to architectural & engineering fees that exceeded the line item budget category total. Archaeological and environmental studies, assessments, testing and reporting charged to architectural & engineering far exceeded the budget for these items due to the high number of prehistoric and historic sites in Hardy County and the requirement to shovel test all ground disturbing construction not in a previously disturbed corridor. Hardy anticipates that the award close-out process will begin in third quarter 2012. | Hardy Telecommunications, Inc. | Environmental and historic preservation roadblocks have been cleared. The presence of underground rock and private easement acquisition issues delayed backbone ring construction, but not materially. | No significant challenges are anticipated.
NT10BIX5570035 | 2012 | Q2 | Q2 - 2012 | In Q2 2012 Hardy Telecommunications ordered and received customer premises equipment and drop cable. Hardy completed construction of 16 Community Anchor Institution ("CAI') laterals out of 92 total CAI connections, with 6 of the 16 CAIs subscribing to broadband service. Documentation describing approximately 0.44 miles of route additions or modifications affecting 24 CAI connections was submitted to NTIA historic preservation staff and the West Virginia State Historic Preservation Office for review and approval. Archaeological shovel testing was performed for buried cable additions or modifications to CAI laterals as required. No significant artifacts were found and no further archaeological review was recommended by Hardy's archaeologists. Private easements were requested for 5 CAIs. Connections to the remaining 47 CAIs were in progress at the end of the quarter. Owner and Engineer inspections of all phases of backbone ring construction were completed, and construction contractors began clean-up for Hardy's final approval and acceptance. All network and access equipment and electronics have been installed and tested. | 98 | 0 | 15 | 0 | 98 | 0 | 0 | 20 | 16)% Variance. Delays in construction commencement as previously noted. Fifteen miles of upgraded fiber network contributed by Hardy in lieu of new construction. | NA | 15 miles of connectivity to community anchor institutions and a portion of an upstream Internet route were contributed by Hardy to the project. | NA | (16)% Variance. Same as New network miles deployed. | NA | NA | (4.8)% Variance. Delays in materials procurement and construction commencement due to Intercreditor Agreement, environmental and historic preservation assessments and shovel testing surveys prevented earlier completion of backbone ring interconnecting facilities. | 1 | 0 | 8 | Lumos Networks | 155 Mbps transport. Pricing Plans previously provided. | No third party operator | 1 | 0 | 0 | 0 | Baseline Value = "N/A" | Baseline Value = "N/A" | Baseline Value = "N/A" | 10 Mbps to 1 Gbps. 1 Subscriber for 155 Mbps service | 16 | 0 | 16 | 5 | (84)% Variance. Delays in commencement of construction as previously discussed. Broadband and Transport service is available up to 1-GigE to seven school sites, three cellular towers, and six other CAIs. Construction underway for remaining CAIs, pending historic preservation review and approval by NTIA and WV-SHPO, and rights of way for 5 sites. | NA | (84)% Variance. Same as above. | Transmission speed tiers: 10-Mbps, 5 subscribers; 20-Mbps, 2 subscribers sharing service for a total of 10-Mbps each. 50-Mbps, 0 subscribers. 100-Mbps, 0 subscribers. 1-GigE, 0 subscribers. | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | No special offerings provided. | FALSE | No change to network management practices over the last quarter. | Approximately 17 miles of new construction including laterals to remaining 72 CAI sites. Contractor completion of backbone ring corrections and final acceptance by Hardy. Hardy will submit a rebudget request to move all remaining savings obtained in the line item categories equipment, facilities, operating equipment, site work, demolition and removal, and construction to architectural & engineering fees that exceeded the line item budget category total. Archaeological and environmental studies, assessments, testing and reporting charged to architectural & engineering far exceeded the budget for these items due to the high number of prehistoric and historic sites in Hardy County and the requirement to shovel test all ground disturbing construction not in a previously disturbed corridor. Hardy will request an early award close-out in third quarter 2012. | Hardy Telecommunications, Inc. | None. | The only challenge remaining is the delay in obtaining NTIA approval of route modifications or additions affecting 24 community anchor institution connections. Archaeological shovel testing has already been performed, if required, and approval from the West Virginia State Historic Preservation office has been obtained for all but two connections. No further review is recommended by Hardy's archaeologists, and no barriers are expected to approval.
NT10BIX5570035 | 2012 | Q3 | Q3 - 2012 | As of the end of third quarter 2012, Hardy Telecommunications had completed construction and splicing of the Hardy AnchorRing backbone ring and upstream connections, upfitting of facilities, installation of electronics and equipment, and construction and splicing of 38 community anchor institution connections. All environmental and historic preservation clearances had been obtained, and construction and splicing of connections for all remaining community anchor institutions was in progress. | 103 | 0 | 16 | 0 | 103 | 0 | 0 | 20 | (12)% Variance. Sixteen miles of upgraded fiber network contributed by Hardy in lieu of new construction. Delays in construction commencement and NTIA approvals of route modifications as previously noted. | NA | 16 miles of connectivity to community anchor institutions and a segment of an upstream Internet route were contributed to the project by Hardy. | NA | (12)% Variance. Sixteen miles of upgraded fiber network contributed by Hardy in lieu of new construction. Delays in construction commencement and NTIA approvals of route modifications as previously noted. | NA | NA | (4.9)% Variance. Delays in construction commencedment as previously noted. | 1 | 0 | 8 | Lumos Networks. | 155 Mpbs Transport. | No third party operation. | 1 | 0 | 0 | 0 | Baseline = "N/A" | Baseline = "N/A" | Baseline = "N/A" | 10 Mbps to 1 Gbps. 1 Subscriber for 155 Mbps Service. | 38 | 3 | 35 | 0 | (62)% Variance. Delays in commencement of construction as previously noted. Fifteen CAIs approved by NTIA for removal due to business closing, relocation, or no longer an eligible CAI. Broadband Internet and Transport services available up to 1-GigE to eight school sites, three cellular towers and twenty-seven other CAIs. | Baseline = 0 | (65)% Variance. Same as Total subscribers served above. | Transport or Internet Service speed tiers available up to 1 Gbps. Internet Service Customers: (1) 25 Mbps upstream / 10 Mbps downstream; (2) 15 Mbps upstream / 7 Mbps downstream; (4) 5 Mbps Upstream / 2 Mbps downstream. Transmission Service Customers: (7) 20 Mbps bidirectional (2 Subscribers sharing 1-20 Mbps circuit). | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | No special offerings requested at this time. | FALSE | No changes to network management practices. | Hardy expects to complete connectivity to twenty-four additional community anchor institutions in fourth quarter 2012 for a total of sixty-two. Hardy will request an early award close-out in fourth quarter. | Hardy Telecommunications, Inc. | Buried construction of laterals to community anchor institutions was delayed awaiting review and approval of route modifications by NTIA. Reroute was required due to right of way issues. | No challenges or issues anticipated in Q4-2012
NT10BIX5570035 | 2012 | Q4 | Q4 - 2012 | Construction of approximately 4 miles of new network, completing network construction. Final completion of Community Anchor Instituition connections, for a total of 63 connected with BTOP funding. All contracts closed out, invoices obtained, unit inventories verified, and payments issued. HardyTel submitted a request for an early award close-out on 12/31/2012 which was approved by the Federal Program Office and Grants Management Office. | 107 | 0 | 16 | 0 | 107 | 0 | 0 | 20 | (8,6)% Variance. Sixteen miles of upgraded fiber network contributed by Hardy in lieu of new construction. | N/A | Baseline = 0%. 16 miles of connectivity to community anchor institutions and a segment of an upstream Internet route were contributed to the project by Hardy. | N /A | (8.6)% Variance. Sixteen miles of upgraded fiber network contributed by Hardy in lieu of new construction. | N/A | N/A | (4.9)% Variance. No change from prior quarter. Savings due to Hardy OneNet USDA-Rural Utilities Service Fiber-to-the-Home loan/grant awrd, which increases the reach of optics and reduces the need for additional equipment. | 1 | 0 | 8 | Lumos Network | 150 Mbps Transport | No third party operator | 1 | 0 | 0 | 0 | Baseline = "N/A" | Baseline = "N/A" | Baseline = "N/A" | 10 Mbps to 1 Gbps. 1 Subscriber for 155 Mbps Transport Service | 63 | 3 | 60 | 0 | Baseline = 98. Variance (35.7%). Continued downturn in economy disproportionately affected rural nonprofit and public institutions. Removals due to office closings and relocations out of rural area, budget cuts, and existing contract terms.. | Baseline = 0. | Baseline = 98. Variance (35.7%). Continued downturn in economy disproportionately affected rural nonprofit and public institutions. Removals due to office closings and relocations out of rural area, budget cuts, and existing contract terms.. | Ttransport and Internet Service speed tiers available from 5 Mbps to 1 Gbps | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | 0 | 0 | 0 | 0 | 0 | Middle Mile | Middle Mile | Middle Mile | Middle Mile | Middle Mile | No special offerings requested. | FALSE | No changes | Final reports submitted. Filing and attorney certification of recording federal security interest in BTOP-funded real and personal property. A-133 audit commences. | Hardy Telecommunications, Inc. | No challenges faced in Q4-2012. | Award completed in 2012.
NT10BIX5570036 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Set up and completed procurement processes for equipment and engineering designs. Completed engineering designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | On track | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570036 | 2010 | Q4 | Q4 - 2010 | Set up the construction procurement process at all the locations. Completed the wavelength system designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | N/A | N/A | Pending the construction procurement process (item 2f above). | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the construction procurement process (item 2f above). | Pending the construction procurement process (item 2f above). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction procurement process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction procurement process is completed. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011.
NT10BIX5570036 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the construction procurement process (item 2f above). | Pending the construction procurement process (item 2f above). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Deploy equipment. | Level 3 EON, LLC | Finished ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction begins. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction activities will commence in Q2 2011.
NT10BIX5570036 | 2011 | Q2 | Q2 - 2011 | Completed all inside plant construction work at each site which included racks to support equipment, power, fuse panels, etc. Purchased equipment to support our Private Line and Ethernet Private Line products. Deployed dense wavelength division multiplexing equipment to support wavelengths services and expect it to be turned up early in 3rd quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). | 0 | 0 | 0 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | In the 3rd quarter we plan to complete all construction, equipment procurement and deployment. | Level 3 EON, LLC | Delay on Network Build and deployment due to longer construction procurement process than expected. We haven't encountered any material challenges in 2nd quarter. The construction process is moving forward with target completion in 3Q. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction and deployment activities will continue in 3Q2011.
NT10BIX5570036 | 2011 | Q3 | Q3 - 2011 | All construction has been completed for this award including all inside and outside plant work. All DWDM and ADM equipment deployments have been completed. Testing is complete for all DWDM equipment and for the ADM equipment 2 of the 4 interconnection points. Purchased equipment test sets. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 of the 4 sites are complete. | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are either complete or near completion, so we expect to see movement in this area soon. | The interconnection points are either complete or near completion, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete our network build and equipment testing in the 4th quarter. | Level 3 EON, LLC | We haven't encountered any material challenges in the 3rd quarter. We have been able to move forward very quickly in the construction and equipment deployments. | No challenges anticipated at this time.
NT10BIX5570036 | 2011 | Q4 | Q4 - 2011 | All construction has been completed for this award including all inside and outside plant work. All equipment deployments have been completed. Testing is complete for all equipment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 0 | 1 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all four of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 4th quarter. We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all interconnection points are available. | No challenges anticipated at this time.
NT10BIX5570036 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 0 | 1 | 0 | We are currently negotiating with one provider and expect this to be completed within the next quarter. The name of the provider is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570036 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to ensure an efficient project close out strategy. Continue to market our services to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 0 | 1 | 0 | We are currently negotiating with one provider and expect this to be completed within the next quarter. The name of the provider is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570036 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine the process required for the project close out. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570036 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570036 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will complete the project closeout, this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570037 | 2010 | Q3 | Q3 - 2010 | Final Draft of Environmental Assessment (EA) has been sent to Department of Commerce. We currently are waiting on the Memorandum of Agreement (MOA) to be executed among FCC, GA SHPO, and Columbia County to resolve the adverse effect associated with couple towers. Once the MOA has been executed, we should be receiving our finding of no significant impact (FONSI) from Department of Commerce to start construction. Board of Commissioners declared 18 firms qualified to perform the services required by the County for the Broadband Fiber Optic Cable Installation project. Board of Commissioners declared 13 firms qualified to perform the services required by the County for the Broadband Tower construction project. Released Bid# 2010-038: Installation of Fiber Optic Cable â€“ Phase I to the 18 qualified vendors approved by the Board of Commissioners. Phase I project is approximately 26.19 miles of cable and 23.25 miles of conduit with no inside plant construction. Sixty-one (61) fiber route miles of staking and engineering has been completed during this quarter and three (3) railroad crossing permits have been submitted to CSX Transportation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | construction not started yet | construction not started yet | construction not started yet | construction not started yet | construction not started yet | construction not started yet | construction not started yet | construction not started yet | 0 | 1 | 1 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | construction not started yet | construction not started yet | construction not started yet | construction not started yet | 0 | 0 | 0 | 0 | construction not started yet | construction not started yet | construction not started yet | construction not started yet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | construction not started yet | construction not started yet | construction not started yet | construction not started yet | construction not started yet | N/A | FALSE | N/A | Receive finding of no significant impact (FONSI) letter from Department of Commerce to start construction. Board of Commissioners approve Phase I fiber construction bid on November 16, 2010. Approved bidder for Phase I fiber construction start construction in December. Receive permits from US Army Corps of Engineers, Georgia DOT, and Georgia EPD for phase I fiber construction in a timely manner. Release Phase II fiber construction bid on November 21, 2010 for approximately 57 miles of fiber construction. Start fiber route engineering for phase III fiber construction project. Complete tower site design and release tower construction bid sometime between November and December. Complete initial network component evaluations and start developing electronic specifications to send out Request For Proposal (RFP) the first quarter in 2011. Building strategic alliances and expanding marketing plan to include branding and expansion of web site. | Columbia, County of | Execution of Memorandum (MOA) among FCC, GA-SHPO and Columbia County to resolve adverse effect with couple of towers. Process was delayed due to determining lead agency for MOA. | Permitting approval US Army Corps of Engineers, MOA signed by FCC and GA-SHPO for tower adverse effect in a timely manner, Railroad Permits from CSX Railroad
NT10BIX5570037 | 2010 | Q4 | Q4 - 2010 | On December 13, 2010, a ground breaking ceremony was held to begin the first of five phases of installation of over 220 miles of fiber optic cable. On Monday December 21, 2010, Columbia County released bid for Intelligent Transportation System (ITS) switches. The system includes adaptive traffic signals, dynamic message signs, emergency priority control, and the ability to monitor real-time traffic via Pan Tilt Zoom cameras. On Monday December 13, 2010, Columbia County released Bid# 2010-053: Installation of Communication Tower Facilities to the 13 qualified vendors approved by the Board of Commissioners. The Bid is to construct five (5) communication tower facilities. These facilities will support public safety equipment as well as additional tenants/broadband service providers. On December 7, 2010, we received our Mitigated Finding of No Significant Impact (FONSI) from National Telecommunications and Information Administration (NTIA). On Monday November 22, 2010, Columbia County released Bid# 2010-046: Installation of Fiber Optic Cable â€“ Phase II to the 25 qualified vendors approved by the Board of Commissioners. Phase II project is approximately 51 miles of cable and 55.5 miles of conduit with no inside plant construction. On November 16, 2010, the first phase of fiber construction was awarded to the ComTran Group, Inc. from Buford, GA for a cost of $1,275,169.44. Columbia County received thirteen bids ranging from $1,275,169.44 to $3,133,469.30. Sixty-seven | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010n on December 13, 2010. | 0 | 1 | 1 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | 0 | 0 | 0 | 0 | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | Started Phase I Fiber construction on December 13, 2010. | N/A | FALSE | N/A | Obtain required permits (US Army Corps of Engineers, Georgia DOT, and Georgia EPD NPDES) for phase two and three fiber construction. Receive, review, and award Phase II and III Fiber Construction bids by March 31, 2011. Start phase II fiber construction approximately 55 miles by February 28, 2011. Receive, review and award Communications Tower Facilities bid by March 31, 2011. Complete eighty-five percent of Phase I Fiber Construction (approx 20 miles) and five percent of Phase II Fiber Construction (approx 5 miles). Start and complete pre-construction project planning including fiber route engineering for phase four and five (approx 100 miles). Survey sites of all anchor tenant s. Release electronics request for proposal (RFP) to network equipment firms. Start refining service offering scope to sustain network. Building strategic alliances and expanding marketing plan to include branding and expansion of web site. | Columbia, County of | N/A | Working with City of Harlem and Grovetown to obtain rights of way easement to install fiber cable in the cities.
NT10BIX5570037 | 2011 | Q1 | Q1 - 2011 | On Monday March 21, 2011, Columbia County released Bid# 2011-025: Installation of Fiber Optic Cable â€“ Phase IV to the 25 qualified vendors approved by the Board of Commissioners. Phase IV is approximately 61 miles of cable and 56 miles of conduit with no inside plant construction. The bidder will supply all materials and labor for bid. On Tuesday March 15, 2011, Columbia County awarded Bid# 2010-008: Installation of Fiber Optic Cable â€“ Phase III to low bidder Utilipath, LLC from Mooresville, NC. The Phase III project is approximately 47 miles of fiber optic cable and 42.5 miles of conduit with no inside plant construction. On Monday March 14, 2011, Columbia County released two bids for Library Computer Lab Equipment. The equipment will include 56 Virtual Desktop Systems including VMware View Manager Software, 35 Laptops and 2 IBM Blade Servers. Bids are due Thursday April 14, 2011. On Thursday March 3, 2011, Columbia County received 7 bids for Bid# 2010-008: Fiber Installation Phase III. The bids ranged from $1,882,034.77 - $3,299,465.82. On Tuesday February 22, 2011, a Pre-Bid Conference was held for Bid# 2010-008: Fiber Installation Phase III. On Tuesday February 15, 2011, Columbia County awarded Bid# 2010-053: Installation of Communication Tower Facilities to low bidder Jacobs Project Management Company from Norcross, GA. The Bid is to construct five (5) communication tower facilities. These facilities will support public safety equipment as well as additional | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Only conduit has been installed | Only conduit has been installed | Only conduit has been installed | Only conduit has been installed | Only conduit has been installed | N/A | Columbia County awarded Bid# 2010-053: Installation of Communication Tower Facilities to low bidder Jacobs Project Management Company from Norcross, GA in February currently waiting on signed contract. | Only conduit has been installed | 0 | 1 | 1 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will deploy equipment to connect Anchor Institutions. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | Only conduit has been installed. Our focus is on network build and once our construction has been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Obtain required permits (US Army Corps of Engineers, Georgia DOT, and Georgia EPD NPDES) for phase four and five fiber construction. Advertise, receive, review, and award Phase IV and V Fiber Construction bids by June 30, 2011. Start phase III fiber construction approximately 47 miles by April 18, 2011. Start phase IV fiber construction approximately 61 miles by June 30, 2011. Start Installation of Communication Tower Facilities by April 30, 2011. Survey anchor tenant sites to determine entry points at each facility. Advertise construction bid for anchor tenant entry point by June 30, 2011. Release electronics request for proposal (RFP) to network equipment firms by June 30, 2011. Start refining service offering scope to sustain network. Building strategic alliances and expanding marketing plan to include branding and expansion of web site. | Columbia, County of | Working with City of Harlem and Grovetown on rights of way issues. Our County attorney is working with their city attorney to resolve the ROW issues. | Working with City of Harlem and Grovetown to obtain rights of way easement to install fiber cable in the cities.
NT10BIX5570037 | 2011 | Q2 | Q2 - 2011 | On Monday April 11, 2011, Jacobs Project Management started construction of the five (5) communication tower facilities. These facilities will support public safety equipment as well as additional tenants/broadband service providers. On Monday April 18, 2011, Utilipath, LLC started Phase III fiber construction. On Thursday April 21, 2011, Columbia County received 9 bids for Bid# 2011-025: Installation of Fiber Optic cable â€“ Phase IV. World Fiber Technologies, Inc. from Alpharetta GA was low bidder. Bids ranged from $1,715,170.94 - $3,475,582.27. Phase IV is approximately 61 miles of cable and 56 miles of conduit with no inside plant construction. On Monday May 2, 2011, Columbia County released Bid# 2011-030: Installation of Fiber Optic Cable â€“ Phase V to the 25 qualified vendors approved by the Board of Commissioners. Phase V is approximately 42 miles of cable and 42 miles of conduit with no inside plant construction. The bidder will supply all materials and labor for bid. On Thursday June 2, 2011, Columbia County Procurement Department received 8 bids for Bid# 2011-030: Installation of Fiber Optic cable â€“ Phase V. Gibson Technical Services, Inc. from Canton GA was low bidder because Utilitpath, LLC didnâ€™t include units added to addendum #2 dated May 23, 2011 Bids ranged from $1,558,052.38 - $2,741,850.87. On Tuesday June 21, 2011, Columbia County awarded Bid# 2011-030: Installation of Fiber Optic cable â€“ Phase V to Gibson Technical Services, Inc. On | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | N/A | N/A | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | Construction started April 11, 2011 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule, ROW issues, and fiber shipment delays have impacted project schedule. | 0 | 1 | 0 | None at this time. | Pricing structure under development3 | Issuing Request for Proposal for Network Operations services next quarter. | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | N/A | FALSE | N/A | Obtain CSX Railroad Permits and resolve ROW issues inside cities by September 30, 2011. Obtain required permits for Phase V and Phase VI fiber optical cable construction by September 30, 2011. Finalized United States Army Corps of Engineering Easement. Start Phase V fiber construction by July 25, 2011. Award Phase VI fiber construction contract by August 16, 2011. Award Network Operation Services and Fiber Restoration and Maintenance contract by September 30, 2011. Release electronics request for proposal by September 1, 2011. | Columbia, County of | Working with City of Harlem and Grovetown on right of way issues inside the cities and should have these issues resolved by end of third quarter. Our County Attorney is work with CSX Transportation on encroachment agreements for the eight rail road crossings. CSX Transportation is requesting a one-time license fee of $12,000 per crossing. This license fees wasn't included in our project budget. | Working with City of Harlem and Grovetown on right of way issues inside the cities and should have these issues resolved by end of third quarter. Our County Attorney is work with CSX Transportation on encroachment agreements for the eight rail road crossings. CSX Transportation is requesting a one-time license fee of $12,000 per crossing. This license fees wasn't included in our project budget. We are hoping for some savings in other areas of the project or may have to adjust project scope to off set the one-time license fees. Delays in fiber shipments may cause a delay in project schedule.
NT10BIX5570037 | 2011 | Q3 | Q3 - 2011 | On Monday June 27, 2011, Columbia County released Bid# 2010-035 Installation of Fiber Optic Cable Phase VI. This bid will consist of connecting anchor tenants from the inner and/or outer fiber rings, node cabinets, electronic racks, DC Power plant and patch panels. The bid was released to the 25 pre qualified vendors approved by the Board of Commissioners. The bidder will supply majority materials and all labor for bid. On Monday July 11, 2011, Columbia County released RFP 2011-052 Fiber Restoration and Maintenance Service seeking proposals from qualified Proposers to provide fiber emergency restoration and maintenance services necessary to maintain approximately 200 miles of fiber optic cable and conduit infrastructure. On Monday July 11, 2011, Columbia County released RFP 2011-053 Managed Network Operations Services seeking proposals from qualified Proposers to manage and monitor the network operations needs of the middle mile network. On Monday August 8, 2011, Columbia County released RFP 2011-060: Carrier Ethernet Infrastructure seeking proposals from qualified Proposers to provide equipment and services necessary to implement a carrier class Ethernet network. On Monday August 8, 2011, Columbia County released RFP 2011-061: Router and Firewall Infrastructure seeking proposals from qualified Proposers to provide equipment and services necessary to implement an edge router and firewall solution to complement our carrier class Ethernet network. On Thursday August 2 | 48 | 0 | 0 | 0 | 48 | 0 | 4 | 0 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | N/A | N/A | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | Construction started April 11, 2011 and the last tower should be completed by December 30, 2011. | Construction started April 11, 2011 and the last tower should be completed by December 30, 2011. Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule, 2011 and the last tower should be completed by December 30, 2011. Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 | 1 | 0 | None at this time | Pricing structure under development | County staff is in the process of evaluating proposals submitted by various firms to provide managed network operations and fiber restoration and maintenance services for the utility. County staff should recommend a firm for approval by December 2011 | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | Our focus is on network build and once completed, we will focus on subscribers. | N/A | FALSE | N/A | Award Phase VI fiber construction bid. Award network operation services contract. Award fiber restoration and maintenance contract. Start evaluating submitted electronics RFP's. Obtaining all easements inside the cities. Construct 100 miles of fiber and 60 miles of conduit. Currently working with several broadband service providers in our area to offer services with an anticipation of one agreement negotiated. Do not anticipate any CAIs connected this quarter. | Columbia, County of | Working with City of Harlem and Grovetown on right of way issues inside the cities and should have these issues resolved by January 31, 2012. | Working with City of Harlem and Grovetown on right of way issues inside the cities and should have these issues resolved by end of quarter.
NT10BIX5570037 | 2011 | Q4 | Q4 - 2011 | County staff is in the process of evaluating RFP 2011-052 Fiber Restoration and Maintenance Service and RFP 2011-053 Managed Network Operations Services proposals submitted by various firms to provide managed network operations and fiber restoration and maintenance services for the utility. County staff should recommend a firm for approval by end of second quarter 2012. County staff is in the process of evaluating RFP 2011-060: Carrier Ethernet Infrastructure and RFP 2011-061: Router and Firewall Infrastructure proposals submitted by various firms to provide various broadband middle mile services. County staff should recommend a firm for approval by April 2012. Jacobs Project Management started the last communication tower facility in November and should be completed by end of February 2012. During this quarter, eighteen and half (18.5) miles of conduit, fifty-one (51) miles of fiber has been placed. â€¢ Advertised in the January 2012 issue of Georgia Trend Magazine, vol.27 No.5 page 101 â€¢ Created a QR code for advertising campaigns which will help measure market penetration. â€¢ Collaborated with local Development Authority regarding creating local chapter of the stateâ€™s new non-profit technology organization, the Technology Association of Georgia (TAG). â€¢ Helped facilitate a roundtable discussion with the local Information Technology workforce and anchor tenants regarding our project and the benefits it will provide to the community. â€¢ Continued to meet periodically with local stakeholders and anchor tenants regarding project status and giving site tours. â€¢ Made a site visit with a BTOP CCI recipient to discuss best practices and gain additional knowledge regarding production networks â€¢ Hosted a fellow BTOP CCI recipient here in Columbia County to exchange best practices. â€¢ Researched and presented information to our advisory board regarding the possibility of creating an infomercial and or purchasing local television advertising. â€¢ Researching regional and national conferences to identify venues to market our project and eventually our network â€¢ Uploaded YouTube videos to our channel cccbroadbandutility to be used in QR advertising campaigns â€¢ 18 lists and 537 people following @cccbu tweets on Twitter â€¢ Facebook Insights data for the last 89 days: User traffic from the United States, Germany, Morocco and the United Kingdom | 124 | 0 | 0 | 0 | 124 | 0 | 4 | 0 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | N/A | N/A | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | Construction started April 11, 2011 and the last tower should be completed by end of February 2012. | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 | 1 | 0 | None at this time. | Pricing structure under development | County staff is in the process of evaluating proposals submitted by various firms to provide managed network services and fiber restoration services. Our goal is to have County staff recommend a firm for approval by June 30, 2012. | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | N/A | FALSE | N/A | Obtain all easements inside the cities to complete Phase II, Phase III and Phase IV construction. Reject all Phase VI construction bids due to cost over budget and look at alternatives to reduce construction cost of building entrance facilities. Evaluate electronic proposals submitted by firms. Working with several broadband service providers in our areas to offer services with an anticipation of one agreement negotiated. We anticipate connecting 12 traffic CAIs this quarter. Construct 25 miles of new conduit and 50 miles of fiber. Bid out and purchase directly from vendor DC Power Plant, fiber patch panels and node cabinets to reduce cost. | Columbia, County of | Working with City of Harlem and Grovetown on right of way issues inside the cities and should have these issues resolved by January 31, 2012. | Working with City of Harlem and Grovetown to resolve right of way issues and should have these issues resolved by end of quarter. If issues are not resolved by end of this quarter, we will look at alternatives to finish project.
NT10BIX5570037 | 2012 | Q1 | Q1 - 2012 | County staff is in the final stages of evaluating RFP 2011-052 Fiber Restoration and Maintenance Service and RFP 2011-053 Managed Network Operations Services proposals submitted by various firms to provide managed network operations and fiber restoration and maintenance services for the utility. County staff should recommend a firm for approval by end of second quarter 2012. County staff is evaluating RFP 2011-060: Carrier Ethernet Infrastructure and RFP 2011-061: Router and Firewall Infrastructure proposals submitted by various firms to provide various broadband middle mile services. County staff should recommend a firm for approval by July 2012. Jacobs Project Management completed the last communication tower facility in March 2012. During this quarter, twenty-three and quarter (23.25) miles of conduit, twenty-six and half (26.5) miles of fiber has been placed. â€¢ 15 QR scans from the January 2012 issue of Georgia Trend Magazine, vol.27 No.5 page 101 â€¢ Attended inaugural Greater Augusta Technology Association of Georgia (TAG) chapter meeting held at Augusta State University. â€¢ Evaluating the possibility of hiring an outside firm to offload certain business development aspects â€¢ Business development meetings with anchor tenants â€¢ Researching regional and national conferences to identify venues to market our project and eventually our network â€¢ Participated in Regional Traffic Engineering presentation discussing our project and its initiatives â€¢ Attended 2012 TAG Georgia Technology Summit in March 2012 to evaluate potential future marketing opportunities. â€¢ Evaluating current land lease contracts to incorporate C3BU marketing strategies â€¢ Facebook Insights data 50 â€œLikesâ€ â€¢ 53 Tweets. 18 lists and 549 people following @cccbu tweets on Twitter | 150 | 0 | 0 | 0 | 150 | 0 | 5 | 0 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | N/A | N/A | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | Completed | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 | 1 | 0 | None at this time. | Pricing structure under development. | County staff is in the process of evaluating proposals submitted by various firms to provide managed network services and fiber restoration services. Our goal is to have County staff recommend a firm for approval by June 30, 2012. | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | Our focus is on cable plant construction and electronics selection. Once these tasks have been completed, we will focus on subscribers. | N/A | FALSE | N/A | Install 40 miles of fiber, 20 miles of conduit and connect 20 CAI's. Complete evaluation of electronic proposals and select a firm. Value engineering building entrances to reduce construction costs. Working with several broadband service providers in our area to offer services with an anticipation of one agreement negotiated. Complete construction and close out contracts for Phases I, II, IV and V by June 30, 2012. Bid out DC Power plant, fiber patch panels and node cabinets to reduce cost. Select and approve fiber restoration and maintenance service firm. | Columbia, County of | N/A | The CAI's building terminations cost coming in over budget may provide a challenge.
NT10BIX5570037 | 2012 | Q2 | Q2 - 2012 | County awarded Fiber Restoration and Maintenance Service contract to Ansco and Associates. County awarded Carrier Ethernet electronics contract to Cyan. County awarded Router and Firewall electronics contract to Torrey Point. During this quarter, 13.25 miles of conduit and 46 miles of fiber have been placed. | 196 | 0 | 0 | 0 | 196 | 0 | 5 | 0 | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | N/A | N/A | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | N/A | Completed | Environmental Assessment, Permits, ROW issues, and fiber shipment delays have impacted project schedule. | 0 | 1 | 0 | None at this time | Pricing structure under development | County has award a fiber restoration and maintenance contract to Ansco and Associates. County staff is in the process of evaluating various firms to provide managed network services. | 0 | 0 | 0 | 0 | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | 0 | 0 | 0 | 0 | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | 0 | 0 | 0 | 0 | 0 | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | Our focus has been on cable plant construction and electronics selection. Once the outside plant construction and electronic equipment have been installed, we will focus on subscribers. | N/A | FALSE | N/A | Install 7 miles of fiber and connect 50 CAI's Install core network equipment and 20 Network Interface Devices (NID). Close out all construction contracts for outside plant construction. Installation of DC power plant, fiber patch panels and node cabinets. | Columbia, County of | N/A | None at this time
NT10BIX5570037 | 2012 | Q3 | Q3 - 2012 | Installed 7.7 miles of conduit and 9 miles of fiber. Connected 106 Community Anchor Institutions (CAIs). Installation Equipment Racks at (7) Tower Nodes (Grounding, Casters, and Cable Management). Installation Equipment Racks at POP (Grounding, Casters, and Cable Management). Carrier Ethernet Electronics (Configure, Burn In, and Installation) at 13 Nodes. Cyan 3-Day Hand-On Fundamentals Training On-site. Installation Fiber Distribution Panels at (5) Outdoor Node Cabinets. Installation DC Power Equipment at (7) Tower Node. Turn up Power Service (5) Outdoor Node Cabinets - Georgia Power and Jefferson EMC Router configuration and burn in. Fire Suppression Commissioned 7 Tower Facilities. Operational Inner/Outer Ring, 13 Nodes and 8 MetroE Sites. | 205 | 0 | 0 | 0 | 205 | 0 | 5 | 20 | Completed | N/A | N/A | N/A | Completed | N/A | Completed | Completed | 0 | 2 | 0 | None at this time | Price structure waiting approval of Board of Comissioners. | County has awarded a fiber restoration and maintenance contract to Ansco and Associates. County has awarded NOC services contract to Cyan Optics to monitor the network. | 0 | 0 | 0 | 0 | Our focus has been on cable plant construction and electronics installation. The Board of Commissioners should approve the rate schedule in November. Once the Board of Commissioners approves the rate schedule, we plan to start focusing on subscribers. | Our focus has been on cable plant construction and electronics installation. The Board of Commissioners should approve the rate schedule in November. Once the Board of Commissioners approves the rate schedule, we plan to start focusing on subscribers. | Our focus has been on cable plant construction and electronics installation. The Board of Commissioners should approve the rate schedule in November. Once the Board of Commissioners approves the rate schedule, we plan to start focusing on subscribers. | Our focus has been on cable plant construction and electronics installation. The Board of Commissioners should approve the rate schedule in November. Once the Board of Commissioners approves the rate schedule, we plan to start focusing on subscribers. | 106 | 27 | 79 | 106 | Connected sites to County Wide Area network with Internet access. Connected 7 Communication tower facilites to provide back haul for new Public Safety 800Mhz Phase 2 radio system. | Back haul for Public Safety Radio System City of Grovetown and Harlem WAN | County Wide Area network with Internet access. | < 10 Mb - None >= 10 Mb and < 50 Mb - 25 >= 50 Mb and < 100 Mb - 27 >= 100 Mb and < 1 Gb - (25 CAIs) >= 1 Gb - (29 CAIs) | 0 | 0 | 0 | 0 | 0 | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | 0 | 0 | 0 | 0 | 0 | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | Not a last mile provider. | N/A | FALSE | N/A | Setup meetings with Columbia County School Board, Fire Departments, Water Utility, City of Harlem and Grovetown to discuss connectivity migration plan. Close out all construction contracts. Purchase and install wireless access points. Connect additional Community Anchor institutions to network. | Columbia, County of | N/A | N/A
NT10BIX5570037 | 2012 | Q4 | Q4 - 2012 | Three construction contracts were closed out. Installed, configured, and tested 25 circuits to connect Community Anchor Institutions (CAIs) to network. ALL GA DOT construction permits were closed out. A notice of construction termination was sent to Georgia Environmental Protection Division to close out all NPDES permits. | 205 | 0 | 0 | 0 | 205 | 0 | 5 | 20 | Completed | N/A | N/A | N/A | Completed | N/A | Completed | Completed | 0 | 2 | 0 | None at this time | Price Structure waiting approval of Board of Commissioners | County has awarded a fiber restoration and maintenance contract to Ansco and Associates. County has awarded NOC services contract to Cyan Optics to monitor the network. | 0 | 0 | 0 | 0 | Our focus has been closing out construction contracts and installing Community Anchor Institutions network interface devices. The Board of Commissioners will approve rate schedule in January 2013. Once rates are approved, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and installing Community Anchor Institutions network interface devices. The Board of Commissioners will approve rate schedule in January 2013. Once rates are approved, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and installing Community Anchor Institutions network interface devices. The Board of Commissioners will approve rate schedule in January 2013. Once rates are approved, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and installing Community Anchor Institutions network interface devices. The Board of Commissioners will approve rate schedule in January 2013. Once rates are approved, we plan to start focusing on network subscribers. | 99 | 33 | 66 | 99 | Connected sites to County Wide Area network with Internet access. Connected 7 Communication tower facilites to provide back haul for new Public Safety 800Mhz Phase 2 radio system. | Back haul for Public Safety Radio System City of Grovetown and Harlem WAN | County Wide Area network with Internet access. | < 10 Mb - None >= 10 Mb and < 50 Mb - 33 >= 50 Mb and < 100 Mb - 14 >= 100 Mb and < 1 Gb - (10 CAIs) >= 1 Gb - (42 CAIs) | 0 | 0 | 0 | 0 | 0 | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | 0 | 0 | 0 | 0 | 0 | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | N/A | FALSE | N/A | Setup meetings with Columbia County School Board, Fire Departments, Water Utility, City of Harlem and Grovetown to discuss connectivity migration plan. Close out remaining construction contracts. Receive and install wireless access points. Community Anchor Institutions connected with fiber will be provided lit service with network interface device (NID). | Columbia, County of | N/A | Don't anticipate any problems with closing out the grant next quarter.
NT10BIX5570037 | 2013 | Q1 | Q1 - 2013 | Board of Commissioners adopted Broadband rates on January 15,2013. Installation of Wireless Access Points in Parks Held meetings with Fire Departments, Water Utility and City of Harlem and Grovetown to discuss connectivity migration plan. | 205 | 0 | 0 | 0 | 205 | 0 | 5 | 20 | Completed | N/A | N/A | N/A | Completed | N/A | Completed | Completed | 0 | 3 | 0 | None at this time. Currently Georgia Business Net, US Army Points West and Professional Disc Golf Association is reviewing a contract to provide last mile connectivity. | Board of Commissioners adopted Broadband rates on January 15,2013. | County has awarded a fiber restoration and maintenance contract to Ansco and Associates. County has awarded NOC services contract to Cyan Optics to monitor the network. | 0 | 0 | 0 | 0 | Our focus has been closing out construction contracts and grant. Next quarter, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and grant. Next quarter, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and grant. Next quarter, we plan to start focusing on network subscribers. | Our focus has been closing out construction contracts and grant. Next quarter, we plan to start focusing on network subscribers. | 99 | 33 | 66 | 9 | Connected sites to County Wide Area network with Internet access. Connected 7 Communication tower facilites to provide back haul for new Public Safety P25 800Mhz Phase 2 radio system. | Back haul for Public Safety Radio System City of Grovetown and Harlem WAN | County Wide Area network with Internet access. | < 10 Mb - None >= 10 Mb and < 50 Mb - 33 >= 50 Mb and < 100 Mb - 14 >= 100 Mb and < 1 Gb - (10 CAIs) >= 1 Gb - (42 CAIs) | 0 | 0 | 0 | 0 | 0 | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | 0 | 0 | 0 | 0 | 0 | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | Not a last mile provider | N/A | FALSE | N/A | We plan to start focusing on network subscribers. | Columbia, County of | N/A | N/A
NT10BIX5570038 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Completed Network Designs. Set up and completed procurement processes for equipment and engineering designs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 1 | 1 | 5 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 0 | Ahead of baseline | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570038 | 2010 | Q4 | Q4 - 2010 | Set up the construction procurement process at all the locations. Completed the wavelength system designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | N/A | N/A | Pending the construction procurement process (item 2f above). | 1 | 0 | 20 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 0 | On track | On track | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction procurement process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction procurement process is completed. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011.
NT10BIX5570038 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | 1 | 1 | 20 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | On track | On track | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Purchase the support and management systems for monitoring. Deploy equipment. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction begins. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction activities will commence in Q2 2011.
NT10BIX5570038 | 2011 | Q2 | Q2 - 2011 | All inside plant and outside plant construction has been completed at all 7 sites, which included trenching and manholes for interconnection points. Most dense wavelength division multiplexing equipment has been deployed. This will provide the support for the ADM systems to be deployed next quarter. Selected the vendors and purchased equipment for the support and management of our MOSS Network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | We will have 7 new interconnection points when we finish. Pending equipment deployment and fiber splicing. | 1 | 1 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete fiber splicing at each of the interconnection points, all equipment deployment and testing. | Level 3 EON, LLC | The construction vendor selection process put our overall project behind, but we have since moved forward very quickly. We didn't experience any material challenges in the 2nd quarter. | We don't anticipate any major challenges at this time. We plan to be very near the projects completion by the end of 3Q2011.
NT10BIX5570038 | 2011 | Q3 | Q3 - 2011 | All deployments for our DWDM, ADM and IP management systems are complete. Testing for each of the systems is also complete. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 2 | 1 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 2 | 0 | 2 | Slightly behind baseline plan. Expect signed agreements to pick up now that our interconnection points are complete. | Slightly behind baseline plan. Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We expect to see an increase in service requests now that all 7 of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 3rd quarter. We have been able to move forward very quickly in the construction and equipment deployments. | We don't anticipate any major challenges at this time.
NT10BIX5570038 | 2011 | Q4 | Q4 - 2011 | All construction has been completed for this award including all inside and outside plant work. All DWDM and ADM equipment deployments have been completed. Testing has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 2 | 1 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all seven of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 4th quarter. We are finalizing invoices with the construction contractor. | No challenges anticipated at this time.
NT10BIX5570038 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 2 | 2 | 20 | We hope to have the contracts currently being negotiated complete within the next quarter. The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570038 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to ensure an efficient project close out strategy. Continue to market our services to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 2 | 2 | 20 | We hope to have the contracts currently being negotiated complete within the next quarter. The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 2nd quarter. | No challenges anticipated at this time.
NT10BIX5570038 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine the process required for the project close out. Marketed services through out sales team to last mile providers. Submitted an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 3 | 0 | 16 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 3 | 0 | 0 | 3 | 1 new agreement signed in Q3. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570038 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 7 interconnection points are complete. | 4 | 0 | 17 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 4 | 0 | 0 | 4 | 1 new agreement was signed in Q4. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570038 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 4 | 0 | 17 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 4 | 0 | 0 | 4 | Completion of the project took longer than originally planned. We expect this to pick up going forward. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide seven new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 | FALSE | N/A | We will complete the project closeout; this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570039 | 2010 | Q3 | Q3 - 2010 | In the 3rd Quarter OpenCape submitted its Final Environmental Assessment, issued an RFP for Auditing Services, issued an RFP for Field Data Survey, Licensing and Permitting, and Engineering, hired its first three full time employees, and completed an MOU with the regional power authority NSTAR to collaborate on the development of both broadband and smart grid. OpenCape conducted meetings and otherwise communicated with regional pole owners to ensure expeditious processing of applications, surveys and make ready. OpenCape submitted a common local exchange carrier (CLEC) application for review to the Massachusetts Department of Telecommunications and Cable. OpenCape continued contract negotiation with the Commonwealth of Massachusetts regarding its $5 million match and anticipates conclusion in October, 2010. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline | N/A | N/A | N/A | Baseline | Baseline | N/A | Baseline | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape will issue an RFP in October, 2010 to identify the operator of its network who will be a contractor. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Special offerings included within RFPs include a requirement of the operating partner to offer a 15% discount to non-profits and a 25% discount to government entities below the commercial rate for services. | FALSE | N/A | OpenCape expects to reach major milestones in the fourth quarter. OpenCape will receive its finding of no significant impact (FONSI) from the NTIA. OpenCape will award an Auditing Services Contract. OpenCape will award a contract for the Field Survey, Licensing and Permitting, and Engineering of the network outside plant (OSP). OpenCape will issue in early October an RFP for the Network Design and Build, and the Network Operation and possibly conclude associated contracts before the end of the quarter. OpenCape will conclude its contract with the Commonwealth of Massachusetts and begin receiving its match component. OpenCape will respond to an RFP by Barnstable County in order to secure a lease for the Countyâ€™s public safety building and prepare to release an RFP for the renovation of that building in Y2Q1 to become the Regional Collocation Center building. | OpenCape Corporation | After consultation with legal experts and the NTIA, OpenCape concluded that it was prudent to pursue a formal request for proposals (RFP) process to seek a company to construct and operate the OpenCape system. This decision was made to ensure that OpenCape is fully compliant with all federal regulations associated with the award of contracts using federal grant funds. An RFP process at this time is not expected to delay the projectâ€™s completion. OpenCape has completed a substantial amount of engineering that will result in a far more refined scope of work to be included in the RFPs. It is anticipated that there will be a greater number of responses that may improve the overall outcome of the project. Negotiation of the $5 million match contract with the Commonwealth of Massachusetts continues and a contract completion is expected in October, 2010. | OpenCape has adjusted to the requirement to issue a new series of RFPs. An aggressive plan and timetable is underway to begin construction immediately after receipt of the FONSI early in the 4th quarter. Coordination with pole owners will work to ensure rapid progress once a contractor is in place to perform Field Survey, Licensing and Permitting, and Engineering early in the 4th Quarter.
NT10BIX5570039 | 2010 | Q4 | Q4 - 2010 | OpenCape reached major milestones in the fourth quarter. OpenCape awarded an Auditing Services Contract to Oâ€™Connor and Drew P.C. and began providing necessary documentation for A133 audit after the end of the fiscal year. OpenCape received a Finding of No Significant Impact (FONSI) on environmental and cultural resources from construction of the OpenCape system from the NTIA under the National Environmental Policy Act (NEPA). The release of a FONSI allows OpenCape to move forward with its project and eliminates the need for a full Environmental Impact Statement. OpenCape became a Common Local Exchange Carrier (CLEC) in order to gain access to Incumbent Local Exchange Carrier (ILEC) Central Offices. This is an essential element of OpenCapeâ€™s strategy to own all underlying rights associated with the OpenCape system. OpenCape awarded a contract for the Field Survey, Licensing and Permitting, and Engineering of the network outside plant (OSP) to UC/Synergetic of Mansfield, MA. UC/Synergetic immediately began surveying the the entire fiber optic route to assess in very fine detail the telephone poles, bridge crossings, and other infrastructure that will receive the OpenCape fiber optics. They began managing the process of preparing Verizon, NSTAR, and National Grid telephone poles and conduit to receive the OpenCape fiber while simultaneously engineering the detailed plans needed by the contractor OpenCape will select to build the network. OpenCape issued in | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | N/A | N/A | N/A | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | Baseline | N/A | Baseline Due to requirement to issue new RFPs and select new contractors this item has been delayed. See Section 3 for detailso issue new RFPs and select new contractors this item has been delayed. See Section 3 for details. | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape issued an RFP for a network operator in October, 2010, and selected a successful respondent in November, 2010. OpenCape is currently negotiating a contract with the successful respondent and expects to conclude a contract in February, 2011. The operator will be a contractor. OpenCape will license the Operator to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCapeâ€™s Field Survey, Licensing and Permitting, and Engineering contractor, UC/Synergetic, will complete all field survey and make significant headway in license applications for pole and conduit access. They will coordinate with OpenCapeâ€™s environmental engineering contractor, Horsley Witten, and the Design, Build, and Operate contractor on the further refinement of the path and begin the engineering of the fiber plant. OpenCape will have completed a contract with its Network Design and Build, and Network Operation contractor. The contractor will finalize all engineering and ramp up for construction to begin in Y1Q2. OpenCape will have received a lease from Barnstable County to the Public Safety Building and will issue an RFP for its renovation. OpenCape will continue its normal outreach to stake holders and community anchor institutions to include the planning of a regional summit on broadband. OpenCape will resolve the overlap with OSHEAN, a round 2 BTOP recipient, along an eight mile overlap of fiber in the New Bedford, MA area. OpenCape will work with the Barnstable County Regional Emergency Preparedness Committee 700Mhz Sub-Committee further progress the issue of organization and strategy to acquire a 700Mhz waiver from the FCC and acquiring a 700Mhz core. Complete first agreements with water district and other tower owners for placement of radio and antenna equipment associated with its public safety microwave overlay. Begin the formal permitting pro | OpenCape Corporation | OpenCape remains behind its Baseline Projection of 16% for this quarter at approximately 10% in Overall Project progress. In addition, OpenCapeâ€™s Federal expenditures are less than 3% of total federal budget at this time; however, the pace of progress increased significantly in the 4th Quarter as anticipated and projected. OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner. After consultation with legal experts and the NTIA, OpenCape concluded that federal procurement regulations would not permit it to conclude a contract with this partner. Rather, OpenCape had to issue new RFPs for all aspects of construction of the network; 2) the process of obtaining a Finding of No Significant Impact was far longer than anticipated; 3) the process of negotiating the many legal contracts associated with the project has been far longer than anticipated; 4) though OpenCape has a partnership with Barnstable County to renovate the regional collocation center, a determination was made that the County must go through a lengthy RFP process under Chapter 30 of the Massachusetts General Laws; and 5) the process of negotiating Master Agreements with utility pole and conduit owners was far longer than anticipated. OpenCape has successfully adjusted to items 1 through 5 in the previous paragraph and transitioned in a manner that will permit it to increase pace. Rather than moving f | Y1Q4 progress has been very good. OpenCape anticipates forward progress to continue at this pace, but is always concerned about obstacles such as the failure to obtain Master Agreements with utilities, lack of capacity within the utilities to process license applications or perform make ready work at a pace that will ensure the on-time completion of the project. Thus far, the utilities are working cooperatively to try and ensure their most rapid response. The permitting of the Cape Cod Canal directional bore with the Army Corps of Engineers is not progressing at a pace acceptable to OpenCape. We have ramped up our efforts in this regard to move this important element forward faster.
NT10BIX5570039 | 2011 | Q1 | Q1 - 2011 | OpenCape reached major milestones in Year 2 Quarter 1. OpenCapeâ€™s contractor, UC/Synergetic of Mansfield, MA is in the field collecting detailed information about the telephone poles, bridge crossings, and other infrastructure that will receive the OpenCape fiber optics. They are also managing the process of applying for licenses from Verizon, NSTAR, and National Grid to place fiber optics on the telephone poles and in conduit to receive the OpenCape fiber. UC Synergetic is simultaneously engineering the detailed plans needed for the installation of the fiber optics. OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network following a competitive request for proposal (RFP) process. CapeNet LLC, a joint venture of Telecom Global Inc. and CapeNet Partners, Inc., will immediately begin preparations to install OpenCapeâ€™s fiber optic and microwave network in the summer of 2011. CapeNet is working closely with UC Synergetic to survey and engineer the fiber optic component of the network. OpenCape Corporation received a lease for the vacant Barnstable County Public Safety Building from Barnstable County as a in-kind match component following a County RFP process. OpenCape will renovate the building and create a regional collocation computing data center as an integral part of the OpenCape system. OpenCape issued an RFP for the general renovation of the former Barnstable County Public Safety Building on March 7, 2011. Responses a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. This category is also delayed by the much slower than anticipated process of obtaining Master Agreements, pole attachment licenses, and make ready from utility pole owners. | N/A | N/A | N/A | Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. This category is also delayed by the much slower than anticipated process of obtaining Master Agreements, pole attachment licenses, and make ready from utility pole owners. | OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCapeâ€™s design build contractor is currently assessing qualifications and issuing bids for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Marthaâ€™s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolution. | N/A | Baseline Due to requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. This category is also delayed by the much slower than anticipated process of obtaining Master Agreements, pole attachment licenses, and make ready from utility pole owners. OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCape’s design build contractor is currently assessing qualifications and issuing bids for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Martha’s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolutiono issue new RFPs and select new contractors this item has been delayed. See section 3 for details. This category is also delayed by the much slower than anticipated process of obtaining Master Agreements, pole attachment licenses, and make ready from utility pole owners. OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCape’s design build contractor is currently assessing qualifications and issuing bids for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Martha’s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolution. | 0 | 0 | 0 | None at this time. | No services are yet being offered.3 | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas and low income areas. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas and low income areas. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape will hold a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff are meeting with town, school, library, and college leaders to discuss the build process, timeline, and implications. These visits are expected to be completed in May, 2011. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape will hold a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff are meeting with town, school, library, and college leaders to discuss the build process, timeline, and implications. These visits are expected to be completed in May, 2011. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape will hold a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff are meeting with town, school, library, and college leaders to discuss the build process, timeline, and implications. These visits are expected to be completed in May, 2011. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCape will secure a Master Agreement with NStar. It will begin receiving pole attachment licenses from all utility pole and conduit owners. OpenCape will award a contract for the general renovation of the former Barnstable County Public Safety building to bring that building up to code and ADA requirements in preparation for the construction of a collocation data center. An RFP will be issued to design, build and operate the collocation data center within the renovated building. OpenCape will refine the Cape Cod Canal directional bore site locations, perform preliminary engineering analysis, and continue the process of application and permitting with the Army Corps of Engineers for the south canal rail road bridge and north canal directional bore crossings of the canal. OpenCape will also request permission from the Army Corps for Verizon to process an application for OpenCape to obtain access to existing conduit on the Sagamore Bridge as an alternate to the directional bore. Verizon license applications for conduit access on the Sagamore and Bourne Bridges requires Army Corps approval prior to processing. OpenCape will perform an assessment of proposed path changes to its planned fiber network and prepare a draft amendment to its original Environmental Assessment (EA). Detailed path analysis and field survey, and utility conduit capacity assessments will reveal issues in the original path proposed in OpenCape's EA. Path changes are inevitable after detailed f | OpenCape Corporation | OpenCape remains behind its Baseline Projection of 27% for this quarter at approximately 8% in Overall Project expenditures. OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner. After consultation with legal experts and the NTIA, OpenCape concluded that federal procurement regulations would not permit it to conclude a contract with this partner. Rather, OpenCape had to issue new RFPs for all aspects of construction of the network; 2) the process of obtaining a Finding of No Significant Impact was far longer than anticipate; 3) the process of negotiating the many legal contracts associated with the project has been far longer than anticipated; 4) though OpenCape has a partnership with Barnstable County to renovate the regional collocation center, a determination was made that the County must go through a lengthy RFP process under Chapter 30 of the Massachusetts General Laws; and 5) the process of negotiating Master Agreements with utility pole and conduit owners was far longer than anticipated. OpenCape has successfully adjusted to items 1 through 5 in the previous paragraph and transitioned in a manner that will permit it to increase pace. OpenCape has made the adjustment and is moving forward at a pace that will ensure on-time completion. A primary challenge faced is the securing of Master Agreements with utility pole and conduit owners. This has proven a | OpenCape continues in its concern that the lack of capacity within the utility companies to process license applications or perform make ready is the greatest risk to on time completion of the project. OpenCape remains concerned with the cost and pace of processing applications for crossings of the Cape Cod Canal through the Army Corps of Engineers. OpenCape has discovered that its planned crossing over an existing bridge at the Taunton River in Fall River, MA is not possible. The existing bridge is being replaced by a new draw bridge without permanent catenaries. OpenCape must seek an alternative route. The most probable of three options is the laying of a cable on the river bed at a designated cable crossing area on the river just south of the bridge. Verizon and ATT currently have riverbed cables in this location. This type of crossing will be more complicated and will require Army Corps permitting on a navigable waterway. OpenCape is currently examining all issues and options related to this crossing.
NT10BIX5570039 | 2011 | Q2 | Q2 - 2011 | UC Synergetic has completed the field survey, license application, and make ready assessment in the NGrid territory where make ready work will begin in the third quarter of 2011. UC Synergetic began the process of field survey within the NSTAR territory during this quarter. OpenCapeâ€™s goal is to complete the make ready assessment in the NSTAR territory by September 1, 2011. Make ready work will be performed in the 3rd and 4th quarters of 2011. All required applications for access to existing Verizon conduit have been submitted and make ready rod and roping has begun on the conduit requested. A small amount of new underground will be required and necessary permit applications associated with that activity are being submitted. CapeNet LLC placed its first order for 35 miles of fiber. CapeNet is executing a detailed competitive process for the selection in August, 2011 of sub-contractors to install the fiber. CapeNet has also been meeting with active equipment (optronics, switching, etc.) providers in preparation for selecting a provider of equipment for the network. OpenCape met with the owners of towers that will host its microwave radios, antennas, and associated equipment. Engineers visited each of the sites on the Cape to assess specific requirements for each location. All of this work is required to develop the contractual basis and engineering specifications needed for accessing each of the towers. OpenCape continues to develop the microwave options t | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. OpenCape is confident that its build will complete on time within the existing timeline. We have adjusted the construction timeline based on the new circumstances. Fiber deliveries will begin in September, 2011. Make Ready will be complete in 20% of the territory in Fall 2011. Sub-contractors will be in place to begin installation in Fall 2011. Fiber deliveries are guaranteed for 35 miles per month from the manufacturer. We expect construction of fiber miles to begin in Fall 2011 with a total construction time of one year, with the ability to compress the timeline even further if necessary and if fiber production and delivery can be increased. | N/A | N/A | N/A | Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. | OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCapeâ€™s design build contractor is currently assessing qualifications and issuing bids requests for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Marthaâ€™s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolution. | N/A | Baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) the timeline even further if necessary and if fiber production and delivery can be increased. Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCape’s design build contractor is currently assessing qualifications and issuing bids requests for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Martha’s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolutionr reasons for any variance from the baseline plan or any other relevant information) the timeline even further if necessary and if fiber production and delivery can be increased. Due primarily to a requirement to issue new RFPs and select new contractors this item has been delayed. See section 3 for details. OpenCape planned in its baseline to build the microwave links in the latter stages of the project. OpenCape’s design build contractor is currently assessing qualifications and issuing bids requests for sub-contractors to build the microwave component. At the same time, OpenCape is negotiating with water district and other tower owners for a license to attach to their towers with a follow-on process for obtaining a long term lease. It is anticipated the licenses will be obtained within six months and the installation of the microwave radios will follow shortly thereafter. OpenCape is evaluating issues with the intended tower on Martha’s Vineyard for the primary link from the mainland. There are capacity issues and OpenCape is working with several state and private entities to determine a resolution. | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas and low income areas. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas and low income areas. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCapeâ€™s contractor, Stateside, will begin the general renovation of the future Regional Collocation Center. OpenCape will select a design, build and operation contractor for the Collocation Data Center that will be constructed in the ground floor level of the Regional Collocation Center. Make ready work will begin in the NationalGrid territory. Make ready assessment within the NSTAR territory will largely be completed. The nearly 50,000 feet of conduit applications with Verizon will have completed rod and roping to determine availability and innerduct placement will begin on those that are clear and available. OpenCapeâ€™s network design, build and operate contractor, CapeNet, will receive shipment of its first order of 35 miles of fiber and select sub-contractors to install fiber. CapeNet will select a vendor for optronic equipment. OpenCape will submit an Environmental Assessment amendment. OpenCape will submit applications and permits to the Army Corps of Engineers for both canal crossings and the Taunton River crossing. OpenCape will also apply to Verizon for conduit access, with Army Corps authorization, on the Sagamore and Bourne Bridges as part of OpenCapeâ€™s crossing alternative development. OpenCapeâ€™s contractor, UC Synergetic will continue to develop and submit all necessary special permits required for network construction. OpenCape will continue to develop the basis of contracts for access to towers that will host OpenCape microwave and | OpenCape Corporation | OpenCape remains behind its Baseline Projection of 40% for this quarter at slightly over 15% in Overall Project expenditures; however, the delta between Baseline Projection and the percentage of Overall Project expenditures is decreasing as projected. OpenCape lags its Baseline Projection and federal expenditure pace for several reasons: 1) OpenCape pursued its grant with a construction contractor as a partner. After consultation with legal experts and the NTIA, OpenCape concluded that federal procurement regulations would not permit it to conclude a contract with this partner. Rather, OpenCape had to issue new RFPs for all aspects of construction of the network; 2) the process of obtaining a Finding of No Significant Impact was far longer than anticipated; 3) the process of negotiating the many legal contracts associated with the project has taken longer than anticipated; 4) though OpenCape has a partnership with Barnstable County to renovate the regional collocation center, a determination was made that the County was required to pursue a lengthy RFP process under Chapter 30 of the Massachusetts General Laws; and 5) the process of negotiating Master Agreements with utility pole and conduit owners was far longer than anticipated. OpenCape has successfully adjusted to items 1 through 5 in the previous paragraph and transitioned in a manner that will permit it to increase pace and ensure on-time completion. OpenCape established a new normal for its baseline following compl | OpenCape continues in its concern that the lack of capacity within NSTAR to process license applications or perform make ready work is the greatest risk to on time completion of the project. OpenCape remains concerned with the cost and pace of processing applications for crossings of the Cape Cod Canal through the Army Corps of Engineers. OpenCape has discovered that its planned crossing over an existing bridge at the Taunton River in Fall River, MA is not possible. The existing bridge is being replaced by a new draw bridge without permanent catenaries. OpenCape must seek an alternative route. OpenCape will seek to lay a cable on the river bed at a designated cable crossing area on the river just south of the new bridge. Verizon and ATT currently have riverbed cables in this location. This type of crossing will be more complicated and will require Army Corps permitting on a navigable waterway. Although fiber manufacture is a major concern among many grant recipients, OpenCape's contractor has secured an eight week delivery commitment for all fiber orders related to our project. This is an acceptable time-line, but OpenCape will continue to monitor actual delivery times to ensure no issues arise.
NT10BIX5570039 | 2011 | Q3 | Q3 - 2011 | OpenCapeâ€™s contractor, CapeNet LLC, received the first delivery of approximately thirty-five miles of fiber in nine reels in September, 2011. The manufacturer, Draka Communications, will make monthly deliveries of approximately thirty-five miles of fiber to meet project needs. Make ready work has begun in the National Grid territory (approximately 20% of the project area). Though this work was negatively effected by the Verizon strike and Hurricane Irene the work will likely be completed in the fourth quarter. ElecComm Corporation and Hawkeye LLC were selected as sub-contractors to CapeNet LLC to build the fiber backbone of the project. Ciena Corporation was selected as the primary vendor for switching and routing equipment. OpenCape initiated the process of crossing the Cape Cod Canal via the Vertical Lift Rail Road Bridge at the south end of the Canal by submitting an application for attachment to the Army Corps of Engineers. The north end Canal crossing has been initiated through an application for attachment to the Sagamore Bridge with Verizon New England. Verizon controls the twelve conduits on the bridge through an easement with the Army Corps. The microwave path was finalized following a process of assessment and engineering to ensure that all links were viable and antenna sizes were kept to a minimum. Engineering will soon be complete to permit the purchase of radios, antennas and power management equipment. OpenCape continues to meet with water c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award. | N/A | N/A | N/A | See Sections 2a and 3 above.OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award. | Baseline | N/A | Baseline See Sections 2a and 3 above.OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award3 above.OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award. | 0 | 0 | 0 | None at this time. | No services are yet being offered3 | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services, particularly in underserved areas. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, timeline, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCapeâ€™s contractor will receive delivery of nearly half of the fiber reels necessary for construction of the OpenCape fiber optic backbone. All switching and routing equipment will be received and DWDM configured. All microwave radio equipment will possibly be delivered in the fourth quarter. Make ready work in the National Grid territory (approximately 20% of the project area) will be completed. Make ready work in the NSTAR territory (approximately 80% of the project area) will begin. It is anticipated that in the NSTAR territory an innovative solution to reduce the amount of make ready, and thus improve the time line for completion and its associated costs will be decided and implemented, but this cannot be assured until an agreement is reached with both NSTAR and Verizon. OpenCape will complete construction of no new network miles in the fourth quarter. The OpenCape project includes no leased network miles. The number of CAI subscribers and broadband wholesalers is at baseline in this quarter. OpenCape will submit an Environmental Assessment (EA) Addendum early in the fourth quarter. If the EA Addendum is approved by the NTIA early in the fourth quarter OpenCapeâ€™s contractor will complete a significant portion of the underground dig and conduit placement required of the project; however, road opening restrictions will be in place in the region by Thanksgiving. ElecComm Corporation and Hawkeye LLC, sub-contractors to CapeNet LLC, will begin mobilization | OpenCape Corporation | Pole survey and make ready work was negatively impacted in this quarter by a strike that was conducted by Verizon employees from August 7-20 and Hurricane Irene from August 25 to September 9,2011. The primary challenge to on-time completion is the pace at which NSTAR, joint pole owner with Verizon in 80% of the OpenCape project territory, can complete make ready assessment and perform the make ready work. NSTAR has completed approximately 60% of the make ready assessment by the end of this quarter. It has ordered mandatory overtime for its employees and is preparing to issue a request for proposals to bring contract work to bear on the issue. At the same time, the make ready assessment that has been performed has revealed more make ready than was anticipated â€“ largely due to a very old pole base in the region. This is concerning with regard to timeline and cost. OpenCape, NSTAR, and Verizon are discussing innovative approaches to fiber placement on the pole that may reduce dramatically the timeline and cost of make ready if successful, but the result of these efforts will not be known until the fourth quarter. Because OpenCape is using All-Dielectric Self Supporting (ADSS) fiber optic cable, and is using energy space qualified sub-contractors it has options that other projects may not. Any solution developed will be in complete compliance with the National Electric Safety Code, but must be agreed by both NSTAR and Verizon as joint pole owners. The crossi | The primary challenges described in Section 3 will remain the primary challenges in the fourth quarter until the resolutions and interventions pursued are concluded. Innovative solutions and aggressive action to address make ready, the Cape Cod Canal crossings, and the Taunton River crossing have been the focus for OpenCape in the third quarter and will remain the focus in the fourth quarter. Resolutions are at hand to these challenges, but cannot be assured until agreements are concluded. Weather will begin to play a role in the progress of the project as the fourth quarter will begin the winter season. The region is often subjected to violent winter storms that can cause power outages and damage to utility infrastructure that demands all of the utilities' attention for extended periods to the total exclusion of work on the OpenCape project. In addition, the Cape Cod Canal is a wind tunnel and work on the bridges is often halted due to high winds. OpenCape has several undergound sections that can be completed in the fourth quarter but work cannot begin until its Environmental Assessment Amendment is approved by the NTIA. Regional authorities do not permit road openings beyond Thanksgiving.
NT10BIX5570039 | 2011 | Q4 | Q4 - 2011 | OpenCapeâ€™s contractor received delivery of nearly half of the fiber reels necessary for construction of the OpenCape fiber optic backbone. All switching and routing equipment was received. DWDM components were received and sent for assembly and configuration. All microwave radio equipment was ordered but delivery delayed until early January, 2012. Make ready work in the National Grid territory was nearly complete by the end of the quarter and is anticipated to be completed in January, 2012. Make ready work in the NSTAR territory is being reassessed based on a new pole placement that will radically reduce the amount of make ready work required, and thus reduce the cost and time-line for completing make ready. It is anticipated the reassessment will be completed in mid-January, 2012. OpenCape received an Environmental Assessment (EA) Addendum approval from the NTIA in the fourth quarter. As a result, underground work was released for construction and approximately 3197 feet of underground conduit work was completed at five sites, nearly one quarter of all planned underground conduit work, prior to the winter hiatus for opening roads. OpenCape has substantially progressed toward an easement from the Army Corps of Engineers to cross the Cape Cod Canal via the Vertical Lift Rail Road Bridge at the south end of the Canal. Applications have been submitted and fees paid to move forward in engineering and appraisals with the Army Corps in the first quarter of 2012. OpenCape has substantially progressed toward obtaining a sub-license placement within conduit on the Sagamore Bridge controlled by Verizon New England under an Army Corps of Engineers issued easement. Verizon completed an assessment of the manhole and access basket infrastructure on the bridge and completed replacement of all access baskets during this quarter, thus enabling safe rod and roping of the conduits upon authorization by the Army Corps to sub-license a portion of one of the twelve conduits to OpenCape. OpenCape has substantially completed business issues related to the crossing of the Taunton River over a privately held riverbed conduit. Contract completion is anticipated in the first quarter of 2012. The microwave engineering is complete and radios and antennas were ordered in the fourth quarter with anticipated delivery in early January, 2012. OpenCape continued to make significant progress in acquiring rights to access towers for placement of microwave equipment and expects to obtain licenses for the towers in the first and second quarters of 2012. OpenCapeâ€™s building renovation contractor, Stateside Construction, completed interior demolition of the former Barnstable County Public Safety Building, completed architectural designs and cost estimates, received a permit from the Old Kings Highway Historical Association, and applied for a building permit that is anticipated to be received in early January, 2012. Stateside has issued bid packages and received responses to most bids for renovation construction to begin in January, 2012. An RFQ was issued for a design consultant for the construction of the collocation data center in the ground level of the Regional Collocation Center. IBM was selected to perform the design work and contract negotiations are underway. OpenCape and the 700MHz Sub-Committee of the Barnstable County Regional Emergency Planning Committee (BCREPC) is in discussion with the state Executive Office of Public Safety and Security regarding a statewide waiver request with regional implementation. A 9-1-1 Regional Dispatch Study funded by the group will be released in early January, 2012. Barnstable County will issue an RFP in January, 2012 to conduct a telecommunications and technology audit of all 15 towns on Cape Cod to support the development of regional application solutions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award. | N/A | N/A | N/A | See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction with the period of the grant award. | Baseline | N/A | Baseline | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May, 2011 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May, 2011to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape held a â€œSmarterCape Summitâ€ in May, 2011to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development. OpenCapeâ€™s engineering contractor is visiting each anchor institution to assess entrance paths, building penetrations, and internal installations. At the same time, OpenCape staff have met with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCape’s contractor will receive an additional 100 miles of fiber during Q1 of 2012. All switching and routing equipment, to include assembled and configured DWDM equipment will be received and invoiced. All microwave radio equipment will be received and invoiced. Make ready work in the National Grid territory for NGRID, Verizon, and 3rd parties will be completed and licenses provided for approximately forty miles of backbone within the NGRID territory. Make ready reassessment for new pole placement will be completed in the NSTAR territory. Make ready work will begin in earnest in the NSTAR territory with completion of adequate amounts of make ready to keep pace with the construction schedule. Verizon conduit rod and roping will be completed for all applications and innerduct placement will be nearly complete in this quarter. At least 40 miles of backbone fiber will be built in Q1 of 2012. Lateral construction will begin in Q1 of 2012. No CAI connections are projected for Q1 of 2012. No Last Mile Provider agreements are anticipated in Q1 of 2012. Splicing and lateral construction sub-contractors will be selected by CapeNet in Q1 of 2012. Most, if not all tower licenses will be obtained in Q1 of 2012 and tower site engineering will begin in anticipation of construction and microwave equipment installation in the second and third quarters. The Regional Collocation Center general renovation will be 50% complete in Q1 of 2012. The Regional Collocation Center Data Center Design will be completed in Q1 of 2012 and an RFP for the Construction of the Data Center will be issued. An easement from the Army Corps of Engineers for the Vertical Lift Rail Road Bridge at the south end of the Cape Cod Canal will be obtained in Q1 of 2012. Verizon will be authorized by the Army Corps of Engineers to sub-license a portion of one of twelve conduits it controls under easement from the Army Corps on the Sagamore Bridge to OpenCape. Verizon will begin rod and roping of conduit on the Sagamore Bridge to identify a path for placement of the OpenCape fiber within an innerduct. An agreement will be concluded for access to an existing riverbed conduit in the Taunton River in Q1 of 2012. Verizon and other collocation agreements will be substantially completed in Q1 of 2012. The Commonwealth of Massachusetts Executive Office of Public Safety and Security will file with the Federal Communications Commission (FCC) for a statewide 700Mhz Waiver. The Barnstable County Regional Emergency Planning Committee (BCREPC) will release a 911 regional dispatch study. The Cape Cod Economic Development Commission will release an RFP to conduct a telecommunications and technology audit of all Cape Cod communities as part of the evaluation and planning of regional municipal applications and public safety umbrella services. | OpenCape Corporation | OpenCape has overcome the make ready challenge to its project through cooperation with NSTAR and Verizon New England for a different placement on the poles. This was the greatest threat to on time and on budget completion of the project. Barring any unforeseen issues, this appears to have been resolved. The unusual October Nor'Easter storm caused significant delay in make ready assessment walkouts and make ready work. The storm stopped pole work on the project for approximately three weeks. The crossing of the Cape Cod Canal in two locations and the crossing of the Taunton River have represented challenges to the project. However, negotiation of agreements to cross in all three locations are underway and appear that they will be concluded in the first quarter. Assuming all agreements can be obtained, the remaining challenge will be the age and condition of conduit on the Sagamore Bridge and the ability of Verizon to find a pathway through what is largely former phone wire filled conduit that has old copper wires that were abandoned in place years ago. Concluding necessary 251/252 forms for collocation within Verizon Central Offices has proved a challenge this quarter and will be a top priority in the first quarter of 2012. Fulfilling the requirements for a lease of tower space on municipal towers is too lengthy a process under Massachusetts procurement laws. OpenCape will make formal request to all tower owners for a less constraining license process to ensure | The primary challenge to on time completion at this time is weather. Uncooperative severe winter weather could stop all make ready and construction work in its tracks. A severe event in our region can stop work for three to four weeks on poles as utilities perform direct repair, perform mutual aid, and provide for post event crew rest. The crossing of the Cape Cod Canal in two locations and the crossing of the Taunton River have represented challenges to the project. However, negotiation of agreements to cross in all three locations are underway and appear that they will be concluded in the first quarter. Assuming all agreements can be obtained, the remaining challenge will be the age and condition of conduit on the Sagamore Bridge and the ability of Verizon to find a pathway through what is largely filled unused conduit that has old copper wires that were abandoned in place years ago.
NT10BIX5570039 | 2012 | Q1 | Q1 - 2012 | OpenCape completed installation of 46 miles of fiber optic cable in Q1 2012, exceeding its projections. OpenCapeâ€™s contractor has received delivery of fiber reels totaling over 265 miles of fiber available for construction of the OpenCape fiber optic backbone. DWDM equipment was sent for assembly and configuration and returned to OpenCape to await installation in regeneration facilities. Make ready work in the National Grid territory was completed in Q1 and nearly 40 miles of fiber installed in the National Grid territory. Make ready work in the NSTAR territory was reassessed to accommodate a new pole placement position to radically reduce the amount of make ready work required, and thus reduce the cost and time-line for completing make ready. OpenCape is engaged in a detailed process with both NSTAR and Verizon to expedite the remaining make ready, and establish a pace of make ready completion consistent with project timelines. OpenCape has substantially progressed toward an easement from the Army Corps of Engineers to cross the Cape Cod Canal via the Vertical Lift Rail Road Bridge at the south end of the Canal. Engineering site visits resulted in necessary drawings and other analysis to support completion of an easement early in Q2 of 2012. OpenCape has substantially progressed toward obtaining a sub-license placement within conduit on the Sagamore Bridge controlled by Verizon New England under an Army Corps of Engineers easement issued to Verizon. Verizon completed basket replacement on the bridge and desktop analysis of available conduit. OpenCape has paid for rod and roping of the conduits to occur early in Q2, 2012. OpenCape is negotiating a contract for access to an existing riverbed conduit under the Taunton River in Fall River, MA following a successful rod and rope of the conduit in Q1 2012. OpenCape continued to make significant progress in acquiring rights to access towers for placement of microwave equipment with five licenses nearly concluded by the end of Q1 2012. OpenCapeâ€™s building renovation contractor, Stateside Construction, continues on schedule to renovate the former Barnstable County Public Safety Building as a regional collocation center. IBM was selected to design the data center in the ground floor of the facility in Q1 of 2012 and immediately began design work. | 46 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | Exceeds projection within PIP. See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction within the period of the grant award. | N/A | N/A | N/A | Exceeds projection within PIP | Baseline | N/A | Baseline | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and will hold the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and will hold the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and will hold the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCape will complete nearly 115 miles of fiber installation in Q2, 2012 for a total of approximately 160 miles complete by the end of the quarter. No CAI connections are projected for Q1 of 2012. No Last Mile Provider agreements are anticipated in Q1 of 2012. A contract for collocation will be completed with Lightower for 235 Promenade Street, Providence, RI, and an agreement will be reached for collocation at 200 Mill Road, Fairhaven, MA. Verizon Central Office rights will be obtained for the Brockton, Plymouth, Cataumet, and Falmouth, MA Central Offices in Q2 of 2012. The Regional Collocation Center general renovation will be 80% complete in Q2 of 2012. The Regional Collocation Center Data Center Design will be completed in Q2 of 2012 and an RFP for the Construction of the Data Center will be issued in Q2. An easement from the Army Corps of Engineers for the Vertical Lift Rail Road Bridge at the south end of the Cape Cod Canal will be obtained in early Q2 of 2012. Verizon will be authorized by the Army Corps of Engineers to sub-license a portion of one of twelve conduits it controls under easement from the Army Corps on the Sagamore Bridge to OpenCape. Verizon will complete rod and roping of conduit on the Sagamore Bridge to identify a path for placement of the OpenCape fiber within an innerduct. An agreement will be concluded for access to an existing riverbed conduit in the Taunton River in Q2 of 2012. Tower rights will be obtained for water towers in Provincetown, Wellfleet, Harwich, Orleans, and Yarmouth, as well as the Barnstable and Truro Communications towers, the Woods Hole Oceanographic Institution Clark Tower, and the American Tower Edgartown facility in Q2 2012. Rights will be obtained for Cotuit and Falmouth Water Towers in Q3. | OpenCape Corporation | OpenCape has overcome the make ready challenge to its project through cooperation with NSTAR and Verizon New England for a different placement on the poles. This was the greatest threat to on time and on budget completion of the project. OpenCape is working with both utilities in a weekly conference call to prioritize all make ready and expedite the make ready process. Both utilities will begin working in earnest on the remaining make ready in early Q2 2012. Approximately 185 poles must be replaced as part of the make ready. NSTAR is seeking a single process from Massachusetts Highway District 5 for all pole replacement permits to accelerate the process. Keeping make ready completion ahead of construction crew availability remains the major challenge for the project. Mass Highway has been a challenge to progress in that the pace of releasing essential permits is inadequate. OpenCape is working with Mass Highway to accelerate this process. The Cape Cod National Seashore requires a permit for work within easements that cross its land. This was a late discovery and we will work this issue aggressively to ensure crews can install fiber in this territory in mid-April, 2012. | The primary challenge to on time completion at this time is the pace of make ready by utilities and the speed with which Massachusetts Highway District 5 releases state highway permits. The crossing of the Cape Cod Canal in two locations and the crossing of the Taunton River have represented challenges to the project. However, negotiation of agreements to cross in all three locations are underway and appear that they will be concluded in the second quarter. Tower licenses have also posed a challenge, but appear set for near term agreements to permit microwave construction to begin in Q2 2012.
NT10BIX5570039 | 2012 | Q2 | Q2 - 2012 | OpenCape has completed installation of nearly 100 miles of fiber optic cable through Q2 2012 with an additional 40 miles released for construction. OpenCapeâ€™s contractor has received delivery of all fiber reels for construction of the OpenCape fiber optic backbone. DWDM equipment was assembled and configured and returned to OpenCape to await installation in regeneration facilities. OpenCape concluded agreements for 9 of 11 regeneration sites. Construction is underway in these sites for the receipt and installation of DWDM and other network equipment in Q3. OpenCape is engaged in a detailed process with both NSTAR and Verizon to expedite the remaining make ready, and establish a pace of make ready completion consistent with project timelines. A commitment was received from NSTAR to apply additional resources to the OpenCape make ready. OpenCape received an easement from the Army Corps of Engineers to cross the Cape Cod Canal via the Vertical Lift Rail Road Bridge at the south end of the Canal and installed the fiber cables over the bridge in Q2. The agreement with the Army Corps also included rights to cross the Sagamore Bridge in Verizon conduit and OpenCape has received necessary conduit licenses from Verizon. Construction on the Sagamore Bridge crossing will occur in late Q3. OpenCape is negotiating a contract for access to an existing riverbed conduit under the Taunton River in Fall River, MA following a successful rod and rope of the conduit in Q1 2012. OpenCape worked with a cooperative Verizon to obtain conduit space to cross Rte 44, a federal limited access highway, which was a major obstacle for permitting and construction. OpenCape successfully negotiated with the Massachusetts Department of Transportation for permits to perform work in rights of way along state highways. OpenCape successfully negotiated a permit with the Cape Cod National Seashore and installed fiber along the utility easement in this national park. OpenCape received several microwave tower licenses and began engineering for submission of permits. Simultaneously, FCC interference studies were begun and submitted to the FCC for licensed spectrum allocation. OpenCape expects to have all necessary tower license agreements and permits in Q3 with construction on a few towers likely to begin in that quarter. OpenCapeâ€™s building renovation contractor, Stateside Construction, substantially completed the general renovation of the OpenCape Regional Collocation Center First and Second Floors in Q2. OpenCape has moved into the new building in this quarter. Stateside has completed approximately 50% of the construction for the Ground Floor Collocation Data Center space. IBM completed the design of the Ground Floor data center and an RFP was issued for the procurement, installation, and configuration of the Collocation Data Center. RFP responses are due on July 20, 2012. | 94 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | Below goals indicated in PIP. See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction within the period of the grant award. | N/A | N/A | N/A | Below goals indicated in PIP. Lack of completion of make ready by NSTAR is the primary cause of this shortcoming. This pushes more fiber construction into Q3 and Q4. | Baseline | N/A | Baseline | 0 | 0 | 0 | None at this time. | No services are yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCape will complete nearly 130 miles of fiber installation in Q3, 2012 for a total of approximately 230 miles complete by the end of the quarter. No CAI connections are projected for Q3 of 2012. However, lateral construction to CAIs will begin in Q3 and internal building work will begin in Q3. No Last Mile Provider agreements are anticipated in Q3 of 2012. A contract for collocation will be completed for collocation at 200 Mill Road, Fairhaven, MA and Granite Block in Fall River, MA. Verizon Central Office rights will be obtained for all Verizon Central Offices in Q3, construction completed, and DWDM equipment deployed. The Regional Collocation Center general renovation will be nearly 100% complete in Q3 of 2012. The Regional Collocation Center Data Center equipment deployment and configuration contract will be completed based on an RFP and installation of the equipment will begin. An agreement will be concluded for access to an existing riverbed conduit in the Taunton River in Q3 of 2012. Tower rights will be obtained for all remaining towers hosting the microwave public safety backup system, permits will be filed, and construction will begin in Q3. | OpenCape Corporation | Make ready pace of completion is the greatest threat to on time project completion. OpenCape is working with both NSTAR and Verizon in a weekly conference call to prioritize all make ready and expedite the make ready process. Verizon is maintaining a pace consistent with construction requirements. NSTAR, despite its stated desire, statements of commitment and intention to apply additional resources, continues to fail to complete make ready at a desirable pace. Rain detracts from make ready. Heat waves detract from make ready. Thunderstorms detract from make ready. Mutual aid obligations to hard hit areas in Maryland and Virginia in June detracts from make ready. Labor agreements prevent the application of contracted labor to the effort. OpenCape will continue to work with the utilities with regard to make ready production. This is an issue of great concern that we believe can be dealt with locally, but without substantial progress in Q3 it will be a growing concern about the construction time line. Massachusetts Department of Transportation does not permit work on state highways on Cape Cod between Memorial Day and Labor Day. OpenCape has submitted two requests for waivers and received two approvals thus far. Additional requests will be made in Q3 for specific segments where reels could be installed or digs performed without major disruption to heavy traffic areas. Massachusetts Department of Transportation inserted into several recent permits a requirement | Make ready pace of completion is the greatest threat to on time project completion. OpenCape is working with both NSTAR and Verizon in a weekly conference call to prioritize all make ready and expedite the make ready process. Verizon is maintaining a pace consistent with construction requirements. NSTAR, despite its stated desire, statements of commitment and intention to apply additional resources, continues to fail to complete make ready at a desirable pace. Rain detracts from make ready. Heat waves detract from make ready. Thunderstorms detract from make ready. Mutual aid obligations detract from make ready. Hurricane season in Q3 represents an additional threat to make ready accomplishment. Labor agreements prevent the application of contracted labor to the effort. OpenCape will continue to work with the utilities with regard to make ready production. This is an issue of great concern that we believe can be dealt with locally, but without substantial progress in Q3 it will be a growing concern about the fiber construction time line.
NT10BIX5570039 | 2012 | Q3 | Q3 - 2012 | OpenCape has completed installation of 180 miles of fiber optic cable through Q3 2012 with an additional 75 miles released for construction for a total of 255 miles constructed or released for construction. OpenCape has successfully stimulated the pole owners to increase production of make ready to the point that a backlog of miles released for construction has resulted. OpenCape's build contractor has contracted with a third sub-contractor and asked the existing two sub-contractors to bring on additional crews to increase fiber construction production. OpenCape concluded agreements for all 11 regeneration sites. Construction is underway in these sites for the receipt and installation of DWDM and other network equipment. OpenCape is negotiating a contract for access to an existing riverbed conduit under the Taunton River in Fall River, MA. An award amendment request has been submitted related to this agreement. OpenCape has received all but two microwave tower licenses, completed nearly all civil engineering, and begun preparing permit applications for installation of equipment on towers. Simultaneously, FCC interference studies were begun and submitted to the FCC for licensed spectrum allocation. OpenCape has received seven FCC licenses thus far. OpenCapeâ€™s building renovation contractor, Stateside Construction, substantially completed the general renovation of the OpenCape Regional Collocation Center. IBM was selected to procure, install, and configure the Collocation Data Center equipment. OpenCape selected a new CEO to lead the company. An award amendment request was submitted for Change of Key Person. OpenCape submitted an award amendment request to change two towers and another to build 34 additional CAI laterals. | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 16 | Below goals indicated in PIP. See Sections 2a and 3 above. OpenCape is confident that its build will be completed on time. The construction time line has been adjusted based on new circumstances. Contractors and sub-contractors are prepared to deploy the necessary crews to accomplish the construction within the period of the grant award. | N/A | N/A | N/A | Below goals indicated in PIP. Lack of completion of make ready by NSTAR is the primary cause of this shortcoming. This pushes more fiber construction into Q4. | Below goals indicated in PIP. Long process of obtaining licenses and daunting permitting process has delayed completion of links. | N/A | Below goals indicated in PIP. Make Ready delays have caused this shortcoming. | 0 | 0 | 0 | None at this time. | No services yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. | 0 | 0 | 0 | 0 | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No CAI subscribers are yet served. OpenCape is addressing anchor institutions in several ways, to include aggressive community outreach. OpenCape founded the SmarterCape Partnership on Cape Cod and held the second SmarterCape Summit on May 14 and 15, 2012 to bring together the community to discuss OpenCape as an underpinning infrastructure of economic development, but more so on how the community can shape its future using broadband. OpenCape staff meet frequently with town, school, library, and college leaders, as well as many other stake holders to discuss the build process, time-line, and implications. | No service is yet available. Anticipate the full breadth of speeds from 10Mbps to 1000Mbps Ethernet, Wavelengths of Light, and Dark Fiber availability to CAIs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Discounts for non-profits and government entities. | FALSE |  | OpenCape will complete 150 miles of fiber installation in Q4, 2012 for a total of approximately 330 miles complete by the end of the quarter. An additional 40 CAI lateral and interior construction will be completed in Q4 of 2012. No Last Mile Provider agreements are anticipated in Q4 of 2012. The Regional Collocation Center Data Center equipment will be installed and configured. An agreement will be concluded for access to an existing riverbed conduit in the Taunton River in Q4 of 2012. Tower rights will be obtained for all remaining towers hosting the microwave public safety backup system, a majority of permits will be received, and installation of microwave equipment will begin. | OpenCape Corporation | Make ready pace of completion is the greatest threat to on time project completion. OpenCape is working with both NSTAR and Verizon in a weekly conference call to prioritize all make ready and expedite the make ready process. Verizon is maintaining a pace consistent with construction requirements. NSTAR has recently picked up the pace of make ready completion. OpenCape made significant inroads in this area in Q3, but must be ever vigilant to ensure adequate production. OpenCape hopes to conclude all remaining make ready before the first snowfalls of the winter season. Microwave links are a difficult task to complete. Obtaining licenses from tower owners under difficult Massachusetts procurement rules and local control within each town took far longer than anticipated. With the licenses in hand, it is now necessary to complete permitting processes in each of 13 different town jurisdictions. Each town has a different process, some with very long timelines that include 30 day public comment periods. Obtaining all of the permits in a timely manner to allow construction to be completed on time is a major challenge. The OpenCape Regional Collocation Center will be largely complete in Q4, 2012. The one concern about full completion is the delivery of adequate power to the facility by the power company, NSTAR. Most testing of equipment can be accomplished using generator capacity, but full testing requires the new additional power to be installed. NSTAR's ability to | Make ready pace of completion is the greatest threat to on time project completion. OpenCape is working with both NSTAR and Verizon in a weekly conference call to prioritize all make ready and expedite the make ready process. Verizon is maintaining a pace consistent with construction requirements. NSTAR has recently picked up the pace of make ready completion. OpenCape made significant inroads in this area in Q3, but must be ever vigilant to ensure adequate production. OpenCape hopes to conclude all remaining make ready before the first snowfalls of the winter season. Microwave links have proven a difficult task to complete. Obtaining licenses from tower owners under difficult Massachusetts procurement rules and local control within each town took far longer than anticipated. With the licenses in hand, it is now necessary to complete permitting processes in each of 13 different town jurisdictions. Each town has a different process, some with very long timelines that include 30 day public comment periods. Obtaining all of the permits in a timely manner to allow construction to be completed on time is a major challenge. The OpenCape Regional Collocation Center will be largely complete in Q4, 2012. The one concern about full completion is the delivery of adequate power to the facility by the power company, NSTAR. Most testing of equipment can be accomplished using generator capacity, but full testing requires the new additional power to be installed. NSTAR's abi
NT10BIX5570039 | 2012 | Q4 | Q4 - 2012 | OpenCape has completed installation of 222 route miles of fiber optic cable through Q4 2012 with an additional 62 route miles under construction or released for construction, for a total of 284 miles constructed or released for construction. A total of 31 route miles has been lit with the production electronics to begin initial calibration and testing. Make-ready work of the utility companies and construction was slowed due to Hurricane Sandy. Though long recovery period was not experienced on the Cape, utility crews and those of the build contractor's subcontractors were redeployed to New Jersey and New York for 3-5 weeks for restoration there. OpenCape concluded agreements for all 10 of 11 regeneration sites. A last minute change delayed landlord execution of the final agreement that had been reported complete in the previous quarterly report. Negotiations with the landlord continued, as well as inital planning of an alternate location should final negotiations be unfruitful. DWDM and carrier Ethernet equipment is complete in 2 sites, and installation is underway in the remaining licensed sites for the receipt and installation of DWDM and other network equipment. Contract for access to an existing riverbed conduit under the Taunton River in Fall River, MA were reported complete by the other party in the agreements, but the agreements have not yet been received by OpenCape. An award amendment request related to this agreement was approved. OpenCape submitted an extension request from January 31, 2013 to September 30, 2013. Largely, continued delays in utility company make ready work continue to cause unexpected, uncontrollable delays in construction of the fiber network. Though completion of the project is expected well before September 2013, the lack of ability to consistently influence utility company make ready and the impact of storms supported the request for the maximum extension time period. OpenCape has received all but three microwave tower licenses. One license previously reported complete was approved by the governing board, but additional lease terms continue to be negotiated. Civil engineering plan preparation continues, and permitting applications submitted for all licensed locations. Simultaneously, FCC interference studies were begun and submitted to the FCC for licensed spectrum allocation. OpenCape has received seven FCC licenses thus far. OpenCape's build contractor brought on a subcontractor as planned to specifically focus on the microwave network construction. OpenCapeâ€™s building renovation contractor, Stateside Construction, substantially completed the general renovation of the OpenCape Regional Collocation Center. Late delivery of electrical switchboard equipment from Siemens and a building power upgrade by NStar (the latter impacted by Hurricane Sandy) will delay completion of the Stateside work. IBM began installation of Collocation Data Center equipment. Equipment racks, UPS, and cooling equipment installation began during this quarter per plan. Final commissioning of equipment will be dependent on the NStar power upgrade for the building. Transition to the new CEO was effected during the quarter. OpenCape submitted an award amendment request to change two towers and another to build 34 additional CAI laterals. These requests are still outstanding. | 222 | 0 | 0 | 0 | 222 | 0 | 0 | 21 | Below goals of PIP. See Sections 2a and 3 above. A date of April 2013 is the estimated date for completion of construction of the fiber network, to be followed by a 5-8 week calibration, tuning, and testing period. | N/A | N/A | N/A | Below goals indicated in PIP. Delays in utility company make ready causing delays in new fiber miles. | Below goal in PIP. Unique process required in each of the 13 jurisdictions remained a challenge to negotiate, though it was well underway. | N/A | 2 backbone and 19 CAI interconnection points established. Make ready delays impacted progress. | 0 | 0 | 0 | None at this time. | No services yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate sixty percent (60%) of the total fiber optic strands (User Fibers) in both dark and lit services to fulfill the obligations of the grant award. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. Network equipmeng is being configured such that a full breadth of speeds from 10 Mbps to 1000 Mbps Ethernet, 2.5 Gbps wavelengths of light, and dark fiber will be available. | 19 | 0 | 19 | 0 | Though physical connections are complete for 19 CAIs, they await completion of the rest of the network before service will begin. | N/A | Though physical connections are complete for 19 CAIs, they await completion of the rest of the network before service will begin. | No service is yet available. All non-state CAIs will initially be connected to the network with a 1 Gbps Ethernet connection with a shared 1 Gbps ethernet service offering. The full range of services defined above will be available if an individual CAI requires such service. State entities will be connected to fibers allocated to the state as part of the agreement for the matching grant. Discussions are underway with the state to facilitate provisioning of that service offering. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The selected network operator is required to offer services in excess of the Municipal Regional Area Network at discounted rates for non-profit and government entities. | FALSE |  | During the next quarter, planned accomplishments include completion of all make ready work for the fiber network, all microwave permitting, and physical connection of 60 CAIs. To complete these efforts, all final regeneration facility and tower licenses will be required to be completed and the final agreements for crossing the Taunton River will be completed. OpenCape will complete 300 route miles of fiber, out of the total of 311 route miles (total of 336 miles of aerial and underground fiber). Four microwave links will have been completed. OpenCape anticipates that our designated network operator will have multiple service offerings for CAIs, businesses, and residential users defined and several under test. Additionally, the operator plans on completing 3 reseller agreeements for services offered on the OpenCape network. | OpenCape Corporation | The completion of utility company make ready continued as the greatest threat to on time project completion. OpenCape worked with both NSTAR and Verizon in weekly conference calls to prioritize all make ready and expedite the make ready process. Verizon maintained a pace consistent with NStar release of licenses, but NStar remained the pacing factor. The impact of Hurricane Sandy was felt significantly as a slow down of make ready work and also reassignment of OpenCape's build contractor subcontractors to storm restoration work due to utility company preemptive contract rights. A significant portion of make ready was completed during the reporting period, but remained less than 100%. After 8 months of NStar engineering work, a plan for delivery of a power upgrade to the regional colocation data center was received during the quarter, with a nebulas 3-6 month completion period from NStar. The work was prioritized behind Hurricane Sandy impacts and other planned electrical upgrade work planned to support the entire Cape Cod area. OpenCape continued to work with NStar to receive a definitive construction schedule for the work, but the NStar schedule remained uncommitted. Permitting for each of the 13 different jurisdictions continued. Those towns deemed to have the longest permitting time frames were prioritized. Permitting is complete on 2 sites with final construction drawings up for review and approval. A prioritized focus continued on the microwave portion of the n | OpenCape has requested an extension to the project to allow completion of the network. If the extension is not granted, the entire network will be in jeopardy as an end to end connection is not yet possible on the network. The challenges during the next quarter will be the continued make ready and slow progress of NStar in completing the power upgrade to the colocation data center. While escalated to top management levels within NStar, lack of progress continues. Weather will be a challenge during the next quarter. Winter weather will impact the ability to complete outside work such as pulling the fiber cable and installing the microwave equipment. Any major winter event could cause asymmetric impacts on the construction completion. Massachusetts Department of Transportation inserted into several recent permits a requirement that OpenCape seek and obtain a lease from Mass DOT for the use of the right of way along its highways prior to lighting services on its network. This is a recent change and one other operators do not appear to be subject to. MassDOT remains intransient on the issue and has not responded to FOIA requests on the matter. OpenCape questions the authority of DOT to impose this requirement and the efficacy of this requirement for economic development throughout the Commonwealth. OpenCape will work with state authorities to eliminate this requirement from its permits. It is a major threat to sustaining the OpenCape network over time if it is not address
NT10BIX5570039 | 2013 | Q1 | Q1 - 2013 | For this reporting period, OpenCape is reporting a decrease in Administrative and Legal Expenses, Matching Funds in the Infrastructure Budget Execution Details when compared to that reported in the previous quarter. The amount reported in the previous quarter was in error due to a spreadsheet error in calculating in-kind match donated hours. The numbers reported in this quarterly report are the corrected amounts. During this quarter, OpenCape completed construction of an additional 78 route miles of fiber, bringing the total to 300 route miles constructed. All utility company make-ready, a significant delaying factor over the entire life of the project, was completed this quarter, about a month earlier than had been expected. An additional 10.4 route miles are under construction. Only 0.6 miles of the entire project has not been released for construction due to a final lease agreement for conduit access. This lease remains under negotiation with the rights owner. A major snow storm occurred throughout the network service area in February 2013. Utility poles were downed in 3 areas of the network, with damage to only one location on the network. That damage was easily and quickly repaired. Had we been operational at the time, the damage would not have caused any service outages due to the design of the network. OpenCape concluded the agreement for the last of the 11 fiber regeneration/DWDM sites. DWDM equipment is installed at all of these sites, is powered up in 6 of the 11 sites to begin testing, tuning, and calibration processes on the electronic equipment. Further coordination is underway for powering equipment in the remaining sites per the Verizon tariffed product process. The plan for crossing the Taunton River was fully completed during the quarter. Fiber connections were 100% completed in the south coast section of the network. The OpenCape extension request through September 30, 2013 was approved by the Program and Grants Offices. AARs for additional laterals and amended microwave sites were both approved. Leases/licenses for 12 of 15 microwave sites are in hand. The remaining leases/licenses are under negotiation. Work continued with each of the local jurisdictions for these 15 sites through planning boards, town meetings, and construction plan reviews. Building permit for 1 site is in hand. FCC license filings continued, with 10 licenses received to date. All major construction and equipment installation was completed for the Collocation Data Center. Electric switchboard equipment from Siemens was received and installed. Equipment racks, UPS, and cooling equipment were all installed. Equipment commissioning was delayed while waiting for a power upgrade to the building from NStar that has been in the works since February 2012. The upgrade plan was delayed due to right of way issues for NStar that required new survey work. Through coordination with Barnstable County, the plan was approved and the NStar upgrade work should begin early second quarter 2013 with a 4-6 week completion time frame. | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 37 | Below goals of PIP. See Sections 2a and 3 above. Progress continued for completion of the fiber component of the network during the second quarter of 2013. Completion of construction will be followed by a 5-8 week calibration, tuning, and acceptance test period. | N/A | N/A | N/A | Below goals in PIP. See Sections 2a and 3 above. | Below goals in PIP. Unique processes in each of the 15 jurisdictions remained a challenge to negotiate, though efforts are well underway with the first building permit in hand. | N/A | 5 backbone and 32 CAI interconnection points established. Make ready delays and Verizon tariffed procedures impacted progress. All remaining backbone interconnection points are awaiting Verizon action to power DWDM equipment. | 0 | 0 | 0 | None at this time. | No services yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Telecom Global Inc. and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate and maintain the entire network including all microwave components, and to sell both lit and dark services on a portion of the fiber exclusive of the OpenCape reserve. The project does not include any sub recipients. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements for dark fiber lease have been signed with wholesale or last mile providers. OpenCape and its design, build and operate contractor are conducting outreach to encourage wholesalers and last mile provider leases. | No speed tiers are as yet available as no wholesale or last mile provider agreements are yet in place. Network equipmeng is being configured such that a full breadth of speeds from 10 Mbps to 1000 Mbps Ethernet, 2.5 Gbps wavelengths of light, and dark fiber will be available. | 31 | 0 | 31 | 0 | No CAI subscribers are yet served. Though physical connections are complete for 31 CAIs, they await completion of the rest of the network before service will begin. | No CAI subscribers are yet served. Though physical connections are complete for 31 CAIs, they await completion of the rest of the network before service will begin. | No CAI subscribers are yet served. Though physical connections are complete for 31 CAIs, they await completion of the rest of the network before service will begin. | No service is yet available. All non-state CAIs will initially be connected to the network with a 1 Gbps Ethernet connection with a shared 1 Gbps ethernet service offering. The full range of services defined above will be available if an individual CAI requires such service. State entities will be connected to fibers allocated to the state as part of the agreement for the matching grant. Discussions are underway with the state to facilitate provisioning of that service offering. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The network operator is required to offer services in excess of the Municipal Regional Area Network at discoutned rates for non-profit and government entities. | FALSE |  | During the next quarter, completion of the fiber construction, testing, and acceptance is anticipated to be completed. Initial customers will be connected to the network. The collocation data center will have been tested and accepted for service. Four microwave links will have been completed. Additional product offerings from the network operator will also have been launched. | OpenCape Corporation | Though now complete, the NStar make ready work was a significant factor in getting network construction completed. NStar continues to be a pacing factor for completion of the Collocation Data Center due to the required power upgrade. Recasting schedules from both Stateside Construction and IBM had cost increase implications to the project that continue to be worked. Even with a projected schedule from NStar, past performance against schedule commitments leads one to be doubtful of their ability to perform on schedule. The snow storm of February 2013 was a significant weather event for the area. Though as noted above, direct impact to the OpenCape network was minimal. However, regional power outages affected virtually the entire Cape area and extended several days after the storm in most areas. The storm was of sufficient significance to trigger activation of the regional sheltering plan by Barnstable County emergency planning officials. The time lost due to the storm, snow removal time, and extended power outages further delayed construction and added to the priority NStar work load. Post construction OTDR results have uncovered fiber that was damaged during construction. The fiber has been spliced or replaced at no additional costs to the program and had minor impacts to the overall schedule. These types of issues may continue to be uncovered as testing progresses. The long standing issue with the Massachusetts Department of Transportation was resolved favorab | The approval of additional laterals added make-ready work for some of these laterals. The schedule will once again be dependent upon utility company work schedules, over which OpenCape has no control and minimal influence. This comes at a time when NStar is conducting major upgrades of the power feed into the entire Cape and Islands area. Prioritization of their work flows will be a major focus and a major challenge.
NT10BIX5570039 | 2013 | Q2 | Q2 - 2013 | During this quarter, OpenCape completed an additional 10 route miles of fiber, bringing the total completed route miles to 310 miles. The remaining miles are all under construction and consist of the final 0.6 miles of backbone fiber and 0.4 miles of lateral connections. Following completion of as-build drawings of the build, a final route mile calculation will be completed to validate the results of the construction effort. All DWDM sites have been completed, with fiber lit for testing across all backbone segments. DWDM and carrier Ethernet equipment was installed at all sites. Testing was completed on 4 of the 10 segments in the network. Initial focus was placed on completing testing and lighting up one bundle of fiber to begin service to a federal customer on Otis Air National Guard Base on Cape Cod. That service began this quarter. Additional cross connects to upstream Internet providers are being pursued to connect the network to the Internet. Testing of the remaining network segments will continue into the next quarter. Leases/licenses for 13 of 15 microwave sites are in hand. The remaining sites are under negotiation. Work continued with each of the local jurisdictions for all sites through planning boards, town meetings, and construction plan reviews. Building permits are in hand for 3 sites and construction work will commence next quarter. Focus on the initial 3 sites will support a planned maintenance schedule of one tank owner that would otherwise interfere with equipment placement. The power upgrade required for the regional collocation data center was completed at the very end of the quarter. The power upgrade allowed commissioning of the new electrical switchboard equipment. Completion of generator, data center UPS and cooling systems is scheduled for early next quarter. Engineering work began on the additional 34 laterals approved as part of the project. One of the connections was completed and make-ready work will be the pacing item for completion of the remaining additional laterals. | 310 | 0 | 0 | 0 | 310 | 0 | 0 | 77 | Below goals of PIP. See Sections 2a and 3 above. Remaining construction is ongoing, with blocked conduit issues scheduled for resolution in one remaining lateral build in the initial 72 programmed laterals. Engineering is underway on the additionally approved laterals so that construction of as many of those as possible will be completed during the grant period. Microwave network continues to be under construction. | Lease negotiations underway. | N/A | N/A | Final mile of new fiber under construction. Route being replotted with as built drawings to validate distances. | 3 building permits in hand. Pushing remaining through local permitting processes. | N/A | 11 backbone and 66 CAI interconnection points established. | 0 | 0 | 0 | None at this time. | No wholesale services yet being offered. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Lightbridge Inc (formerly Telecom Global Inc). and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate and maintain the entire network including all microwave components, and to sell both lit and dark services on a portion of the fiber exclusive of the OpenCape reserve. The project does not include any sub recipients. | 0 | 0 | 0 | 0 | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | No signed agreements in place. OpenCape and its design, build and operate contractor are engaging last mile providers in order to develop potential last mile solutions. Several companies are interested in offering services. | 66 | 0 | 66 | 0 | CAIs are connected to the network fiber, service pending cross connections to upstream providers. | Delay in microwave network. | CAIs are connected to the network fiber, service pending cross connections to upstream providers. | Speed tiers available range up to 1 Gbps, with the increment defined by the needs of the customer. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The network operator is required to offer services in excess of the Municipal Regional Are Network at discounted rates for non-profit and government entities. | FALSE | N/A | The fiber network will be completed during this next quarter. Internet and point to point services will be offered on the network. The data center will be operational. All initial 72 CAIs will be connected. Additional laterals approved by NTIA will also be completed. The number will depend on utility company make ready efforts. All microwave radio sites will be completed. | OpenCape Corporation | Post construction OTDR results continued to uncover fiber that was damaged during construction, bad splicing, and swapped bundles. The testing is progressing, but at a slow rate. As the network segments are tested, three crews are utilized. Two crews are dispatched to the end points of the segment while the third crew moves along the fiber route to rectify any issues discovered during the testing. A 100% test approach is being utilized in that every fiber is being tested. When completed, the network fiber will be working 100% and will exceed contractual performance specifications. | Completion of the microwave radio network will be a challenge. The local permitting processes operate on a timeline that cannot easily be influenced by OpenCape, with some mandatory review and objection periods.
NT10BIX5570039 | 2013 | Q3 | Q3 - 2013 | Durign this quarter, OpenCape completed all backbone fiber construction, testing, and acceptance. All fiber laterals in the initial grant application (68) were also completed, tested, and accepted. The total fiber build at this point is 311 route miles of new fiber. The construction punch list was developed and is being worked by the construction companies. All DWDM and carrier Ethernet equipment has been installed and is fully operational. Construction of the microwave sites continues. The project was granted an additional 60 days for completion primarily due to difficulties in permitting of the microwave network. Licenses/leases for 12 of 15 microwave sites are in hand. One of the license previously held expired and we are working all to complete. Site construction on 5 sites is essentially complete, waiting setting of equipment cabinets that have been pre-populated and pre-tested. Construction is underway on 3 additional sites. A site legal complication is holding up construction of one site. Construction of 3 sites are ready to start once local permits are released. All work has been completed in the Regional Collocation Data Center. The virtual machine/storage area network environment has been installed and configured. Installing an internal network infrastructure was delayed with the additional extension on the project to discuss partnerships to operate the data center or certain data center services. Engineering work and licensing for the additional 34 laterals continues, with one having been completed already. Utility company make ready time frames will preclude finishing all 34 connections, but these will be worked to complete as many as possible during the extended grant period. | 311 | 0 | 0 | 0 | 311 | 0 | 0 | 82 | Fiber network is complete with the exception of additional laterals. Completion of the 21 of 34 additional laterals as currently planned will add approximately 2 fiber miles to the overall network. | N/A | N/A | N/A | Fiber network is complete with the exception of additional laterals. Completion of the 21 of 34 additional laterals as currently planned will add approximately 2 fiber miles to the overall network. | 5 sites are essentially complete, waiting on cabinet placement until sufficient sites are ready to warrant crew mobilization. 4 sites are under construction. 3 sites are pending a single permit. Leases are required on 2 sites, and 1 site became the subject of a legal disagreement between the town and tower owner. | N/A | 13 backbone and 69 CAI interconnection points established | 0 | 0 | 0 | CapeNet LLC has a long term agreement as the operator of the OpenCape network. CapeNet offers retail services to end users on the network, and works with those entities that would like to be connected to the network. | No wholesale services are offered by OpenCape. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network. CapeNet LLC is a joint venture of Lightbridge Inc (formerly Telecom Global Inc). and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis, 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate and maintain the entire network including all microwave components, and to sell both lit and dark services on a portion of the fiber exclusive of the OpenCape reserve. The project does not include any sub recipients. | 0 | 0 | 0 | 0 | OpenCape has no signed agreements in place. OpenCape and its network operator are engaging last mile providers in order to develop potential last mile solutions. | N/A | N/A | N/A | 69 | 0 | 69 | 69 | CAIs are connected to the network and the network is available for service. CAIs are working through their budgeting cycles, contractual requirements, schedules, etc prior to signing up for service. Barnstable County indicated they would be issuing an RFP for services for all towns, schools, and non-profits that may be connected to the network. OpenCape is waiting on that RFP. | Delay in microwave network | Delay in microwave network and additional utility company make ready. | Speed tiers available run continuously the range of 10 Mbps through 1 Gbps, defined by the customer requirements. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | OpenCape intends to offer a Municipal Regional Area Network allowing towns on the Cape to communicate within the network at shared 1 Gbps speeds within the service segments of the network (a total of 7 Gbps aggregated capacity on the Cape) and a shared 1 Gbps connection to the Internet. The on-net connectivity includes connectivity into the regional collocation data center. Offering such service is dependent on the County issuing an RFP to act as the procurement function for the towns and schools that may be connected to the network. | FALSE | N/A | The project will be completed by November 30, 2013, at which time the close out period will begin. The project will include the original project scope plus 20 additional laterals. Total CAIs connected would be 92. The microwave network will be completed and the data center completely operational. The microwave network would account for an additional 94 miles of overall network miles if all links can be built. | OpenCape Corporation | Current challenges in completing the project are ongoing license and permit processed with the local government entities for the microwave network. Deferrals in hearings and required public notification times continue to delay the work, even though an individual site can be completed within only a few days. Some construction progress has been held up based on the extended grant period just to be more efficient in crew scheduling. In completing the additional laterals, make ready work is still pending. That is holding up start of some work associated with those sites, but is rippling into holding up other work as well given the desire for the most efficient crew scheduling. | Completion of the microwave sites will be a challenge. Local permitting processes operate on a timeline that cannot easily be influenced by OpenCape, with some mandatory public review and objection periods.
NT10BIX5570039 | 2013 | Q4 | Q4 - 2013 | Project was completed during the fourth quarter of 2013. All network construction was complete, as modified by a final AAR. Some CAIs added earlier in the year were removed due to excessive utility company make ready time frames. Some microwave sites were removed due to problems in obtaining legal rights. In total, 91 CAIs were connected to the network, and 13 microwave sites were completed. Close out activities are underway. | 382 | 0 | 0 | 0 | 306 | 10 | 0 | 117 | A total of 382 miles of new network were deployed, including new fiber and microwave. | N/A | N/A | N/A | The route of new fiber was replotted with as-built drawings. The total route miles was determined to be 306 miles. This amount less than previous reports due to: 1) pre-engineered route mile estimates, 2) reporting of reel based distances in situations where cable routes overlapped, especially in the case of laterals paralleling the backbone to a splice point. | 76 miles of microwave network was completed | N/A | Above original grant application and exceeds baseline | 0 | 0 | 0 | CapeNet LLC has a long term agreement awarded through a competitive process as the operator of the OpenCape network. As the operator, CapeNet is responsible for all sales on the network. CapeNet offers retail services to end users on the network, and works with those entities that would like to be connected to the network. CapeNet also works through a set of resellers. | No wholesale services are offered by OpenCape. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network through a competitive process. CapeNet LLC is a joint venture of Lightbridge Inc (formerly Telecom Global Inc). and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis, 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate and maintain the entire network including all microwave components, and to sell both lit and dark services on a portion of the fiber exclusive of the OpenCape reserve. The project does not include any sub recipients. | 0 | 0 | 0 | 0 | OpenCape cannot enter into broadband wholesale agreements. The OpenCape network operator provides all sales services for network access. They have multiple resellers (6) who are reselling CapeNet services on the network. | N/A | N/A | N/A | 91 | 1 | 90 | 91 | The initial grant application contained 72 CAIs. OpenCape was able to connect 91 CAIs within the original grant amounts. | N/A | N/A | Speed tiers available run continuously from 10 Mbps through 1 Gbps. One microwave connection is only available at 10 Mbps due to power limitations on the island served (no commercial power). An RFP is currently under evaluation by Barnstable County for connection of all CAIs on the Cape at speeds up to 1 Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The OpenCape network has been designed to provide a Municipal Regional Area Network allowing towns on the Cape to communicate within the network as shared 1 Gbps speeds on individual service rings, providing a total of 14 Gbps of capacity (14 separate service rings). The on-net connectivity includes connection to the regional collocation data center. This offering is currently the subject of a county RFP, which is under evaluation by the County. | FALSE | N/A | Project is complete and in close out. | OpenCape Corporation | During the past quarter, completion of the "additional CAIs" approved earlier in 2013 became challenged by utility company make ready. Of the planned 34 additional CAIs, 20 were completed. The balance of the additional CAIs, as well as one of the original CAIs, were removed from the project by an approved AAR. Additionally, obtaining permits and legal access to several of the microwave sites began to exceed the project timeline. Of the 15 microwave sites planned in the project, 13 were completed. Equipment for the remaining two sites was procured and OpenCape is working to complete the installation of these sites using non-grant funding. 100% of grant funds were obligated through the end of 2013. Close out activities will continue into 2014 without further grant funding. | None.
NT10BIX5570039 | 2014 | Q1 | Q1 - 2014 | Project was completed during the fourth quarter of 2013. All network construction was complete, as modified by a final AAR. Some CAIs added earlier in the year were removed due to excessive utility company make ready time frames. Some microwave sites were removed due to problems in obtaining legal rights. In total, 91 CAIs were connected to the network, and 13 microwave sites were completed. Close out activities are underway. | 382 | 0 | 0 | 0 | 306 | 10 | 0 | 117 | A total of 382 miles of new network were deployed, including new fiber and microwave. | N/A | N/A | N/A | The route of new fiber was replotted with as-built drawings. The total route miles was determined to be 306 miles. This amount less than previous reports due to: 1) pre-engineered route mile estimates, 2) reporting of reel based distances in situations where cable routes overlapped, especially in the case of laterals paralleling the backbone to a splice point. | 76 miles of microwave network was completed | N/A | Above original grant application and exceeds baseline | 0 | 0 | 0 | CapeNet LLC has a long term agreement awarded through a competitive process as the operator of the OpenCape network. As the operator, CapeNet is responsible for all sales on the network. CapeNet offers retail services to end users on the network, and works with those entities that would like to be connected to the network. CapeNet also works through a set of resellers. | No wholesale services are offered by OpenCape. | OpenCape awarded a contract to CapeNet LLC to design, build, and operate the OpenCape network through a competitive process. CapeNet LLC is a joint venture of Lightbridge Inc (formerly Telecom Global Inc). and CapeNet Partners, Inc. CapeNet LLC is a contractor. The primary contact for CapeNet LLC is Alan Davis, 1900 West Park Drive, Suite 280, Westborough, MA 01581, 508-983-1475. OpenCape has licensed CapeNet LLC to operate and maintain the entire network including all microwave components, and to sell both lit and dark services on a portion of the fiber exclusive of the OpenCape reserve. The project does not include any sub recipients. | 0 | 0 | 0 | 0 | OpenCape cannot enter into broadband wholesale agreements. The OpenCape network operator provides all sales services for network access. They have multiple resellers (6) who are reselling CapeNet services on the network. | N/A | N/A | N/A | 91 | 1 | 90 | 91 | The initial grant application contained 72 CAIs. OpenCape was able to connect 91 CAIs within the original grant amounts. | N/A | N/A | Speed tiers available run continuously from 10 Mbps through 1 Gbps. One microwave connection is only available at 10 Mbps due to power limitations on the island served (no commercial power). An RFP is currently under evaluation by Barnstable County for connection of all CAIs on the Cape at speeds up to 1 Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The OpenCape network has been designed to provide a Municipal Regional Area Network allowing towns on the Cape to communicate within the network as shared 1 Gbps speeds on individual service rings, providing a total of 14 Gbps of capacity (14 separate service rings). The on-net connectivity includes connection to the regional collocation data center. This offering is currently the subject of a county RFP, which is under evaluation by the County. | FALSE | N/A | Project is complete and in close out. | OpenCape Corporation | During the past quarter, completion of the "additional CAIs" approved earlier in 2013 became challenged by utility company make ready. Of the planned 34 additional CAIs, 20 were completed. The balance of the additional CAIs, as well as one of the original CAIs, were removed from the project by an approved AAR. Additionally, obtaining permits and legal access to several of the microwave sites began to exceed the project timeline. Of the 15 microwave sites planned in the project, 13 were completed. Equipment for the remaining two sites was procured and OpenCape is working to complete the installation of these sites using non-grant funding. 100% of grant funds were obligated through the end of 2013. Close out activities will continue into 2014 without further grant funding. | None.
NT10BIX5570040 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Set up and completed procurement processes for equipment and engineering designs. Completed engineering designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | On track | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570040 | 2010 | Q4 | Q4 - 2010 | Set up the construction procurement process at all the locations. Completed the wavelength system designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | N/A | N/A | Pending the construction procurement process (item 2f above). | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the construction procurement process (item 2f above). | Pending the construction procurement process (item 2f above). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction procurement process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction procurement process is completed. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011.
NT10BIX5570040 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | On track | On track | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Purchase the support and management systems for monitoring. Deploy equipment. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. One interconnection point is completed. Construction will commence in Q2 2011. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction activities will commence in Q2 2011.
NT10BIX5570040 | 2011 | Q2 | Q2 - 2011 | Outside plant work which includes the manhole construction and trenching is complete in Soperton and is under way in Gordon. All inside plant work is complete at each site. Dense wavelengths division multiplexing equipment has been deployed at Soperton. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Soperton interconnection point is complete. By the end of 3rd quarter we expect all four interconnection points to be completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete all outside plant construction and fiber splicing. The majority of equipment deployments and equipment testing will also be completed in 3Q2011. | Level 3 EON, LLC | The construction vendor selection process put our overall project behind, but we have since moved forward very quickly. We didn't experience any material challenges in the 2nd quarter. | We don't anticipate any major challenges at this time. We plan to be very near the projects completion by the end of next quarter.
NT10BIX5570040 | 2011 | Q3 | Q3 - 2011 | Construction has been completed at all of the interconnection sites. All equipment has been deployed and tested. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We expect to see an increase in service requests now that all 4 of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 3rd quarter. We have been able to move forward very quickly in the construction and equipment deployments. | We don't anticipate any major challenges at this time.
NT10BIX5570040 | 2011 | Q4 | Q4 - 2011 | Construction has been completed at all of the interconnection sites. All equipment has been deployed and tested. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all four of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 4th quarter. We are finalizing invoices with the construction contractor. | No challenges anticipated at this time.
NT10BIX5570040 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570040 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to determine exact process required for the project close out. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 2nd quarter. | No challenges anticipated at this time.
NT10BIX5570040 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine the process required for the project close out. Marketed services through out sales team to last mile providers. Submitted an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570040 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 4 interconnection points are complete. | 2 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Expect signed agreements to pick up now that our interconnection points are complete. | Expect signed agreements to pick up now that our interconnection points are complete. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570040 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 2 | 0 | 12 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Completion of the project took longer than originally planned. We expect this to pick up going forward. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will complete the project closeout; this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570041 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Set up and completed procurement processes for equipment and engineering designs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | On track | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570041 | 2010 | Q4 | Q4 - 2010 | Set up RFP process for construction at all the locations. Completed DWDM designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2f above | N/A | N/A | See 2f above | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending 2f | Pending 2f | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction RFP process than expected. Ready to move forward quickly as soon as construction RFP is completed. | No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction RFP process. We plan to be back on schedule by Q2 2011.
NT10BIX5570041 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the construction procurement process (item 2f above). | Pending the construction procurement process (item 2f above). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable highspeed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Purchase the support and management systems for monitoring. Deploy equipment. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. One interconnection point is completed. Construction will commence in Q2 2011. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction activities will commence in Q2 2011.
NT10BIX5570041 | 2011 | Q2 | Q2 - 2011 | Outside plant construction has been completed at five sites with a sixth under way. Inside plant construction has been completed at six sites. Selected the vendors and purchased equipment for the support and management of our MOSS Network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending completion of construction and splicing. | 0 | 1 | 0 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). | Pending the completion of construction and equipment deployment at each site (items 2f and 2i). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete all outside plant construction, inside plant construction and fiber splicing. The majority of equipment deployments and equipment testing should also be completed. | Level 3 EON, LLC | The construction vendor selection process put our overall project behind, but we have since moved forward very quickly. We didn't encountered any material challenges in the 2nd quarter. | We don't anticipate any major challenges at this time. We plan to be very near the projects completion by the end of 3Q2011.
NT10BIX5570041 | 2011 | Q3 | Q3 - 2011 | All DWDM, ADM and IP management equipment has been deployed. DWDM and IP management equipment has been tested. The ADM testing has been completed at 8 of the 17 sites. All construction has been competed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 of the 17 are complete. | 0 | 2 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Expect signed agreements to pick up as we complete our interconnection points. | Expect signed agreements to pick up as we complete our interconnection points. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to finish the network build and equipment testing. We also expect to see an increase in service requests as the interconnection points are completed. | Level 3 EON, LLC | We haven't encountered any material challenges in the 3rd quarter. We have been able to move forward very quickly in the construction and equipment deployments. | We don't anticipate any major challenges at this time.
NT10BIX5570041 | 2011 | Q4 | Q4 - 2011 | Construction has been completed at all of the interconnection sites. All equipment has been deployed and tested. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 17 interconnection points are complete. | 0 | 2 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | Expect signed agreements to pick up as we complete our interconnection points. | Expect signed agreements to pick up as we complete our interconnection points. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all 17 of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 4th quarter. We are finalizing invoices with the construction contractor. | No challenges anticipated at this time.
NT10BIX5570041 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 17 interconnection points are complete. | 0 | 2 | 0 | We hope to have the contracts currently being negotiated complete within the next quarter. The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all 17 of the interconnection points are available. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570041 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to determine exact process required for the project close out. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 17 interconnection points are complete. | 0 | 2 | 0 | We hope to have the contracts currently being negotiated complete within the next quarter. The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 2nd quarter. | No challenges anticipated at this time.
NT10BIX5570041 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine exact process required for the project close out. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 17 interconnection points are complete. | 1 | 0 | 12 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | 1 new agreement was signed in the 3rd quarter. We expect to see this pick in the coming quarters. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. Plan to submit an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570041 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All 17 interconnection points are complete. | 1 | 0 | 12 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570041 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 1 | 0 | 12 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Completion of the project took longer than originally planned. We expect this to pick up going forward. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 17 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will complete the project closeout; this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570042 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Set up and completed procurement processes for equipment and engineering designs. Completed engineering designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 0 | 0 | 0 | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | On track | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Set up and complete construction RFP process. Begin construction, start network designs, purchase equipment. | Level 3 EON, LLC | Ahead of schedule on engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570042 | 2010 | Q4 | Q4 - 2010 | Set up the construction procurement process at all the locations. Completed the wavelength system designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f). | N/A | N/A | Pending the construction procurement process (item 2f). | 1 | 0 | 12 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 0 | Pending the construction procurement process (item 2f above). | Pending the construction procurement process (item 2f above). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction procurement process is completed. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011.
NT10BIX5570042 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Deployed equipment at one of the sites. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | 1 | 0 | 12 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 0 | On Track | On Track | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Purchase ADM and support and management systems for monitoring. Deploy equipment. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Construction will commence in Q2 2011. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The construction activities will commence in Q2 2011.
NT10BIX5570042 | 2011 | Q2 | Q2 - 2011 | All outside plant construction is complete. The inside plant work for nine of the eleven sites is complete. All equipment has been ordered including dense wavelength division multiplexing and ADM. Selected the vendors and purchased all equipment for the support and management of our MOSS Network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Interconnection point in Palo Cedro is available for customers seeking wavelengths services. By the end of next quarter we expect all interconnection points to be completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete the rest of the inside plant construction and fiber splicing. The majority of equipment deployments and testing should also be completed. | Level 3 EON, LLC | The construction vendor selection process put our overall project behind, but we have since moved forward very quickly. We didn't experience any material challenges. | We don't anticipate any major challenges at this time. We plan to be very near the projects completion by the end of 3Q2011.
NT10BIX5570042 | 2011 | Q3 | Q3 - 2011 | All construction is complete including inside and outside plant work. Equipment has been ordered for each site including DWDM, ADM and IP management equipment. DWDM testing is complete at seven of the eleven sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Wavelength capabilities are available at seven of the eleven sites. The remaining products and sites will be completed in the 4th quarter. | 2 | 1 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 2 | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete equipment deployments and network builds at all of our interconnection sites in the 4th quarter. | Level 3 EON, LLC | Fiber assignments at four of the sites have taken a bit longer than expected, but plan on having it completed early next quarter. | We don't anticipate any major challenges at this time.
NT10BIX5570042 | 2011 | Q4 | Q4 - 2011 | Construction has been completed at all of the interconnection sites. All DWDM equipment has been deployed and tested. ADM equipment has been deployed and tested at 8 of the 11 interconnection sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Wavelength capabilities are available at all of the sites. The remaining products and sites will be completed in the 1st quarter. | 2 | 1 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 2 | 0 | 0 | 0 | Expect signed agreements to pick up when interconnection points are completed. | Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | All equipment deployments and testing will be completed in the 1st quarter. We are finalizing invoices with the construction contractor and expect to see an increase in service requests now that all four of the interconnection points are available. | Level 3 EON, LLC | Fiber assignments at three of the sites have taken a bit longer than expected, but plan on having it completed early next quarter. | No challenges anticipated at this time.
NT10BIX5570042 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 3 | 0 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 3 | 0 | 0 | 3 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570042 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to ensure an efficient project close out strategy. Continue to market our services to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 3 | 0 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 3 | 0 | 0 | 3 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 2nd quarter. | No challenges anticipated at this time.
NT10BIX5570042 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine exact process required for the project close out. Marketed services through out sales team to last mile providers. Submitted an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 3 | 0 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 3 | 0 | 0 | 3 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570042 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | 3 | 0 | 20 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 3 | 0 | 0 | 3 | The interconnection points are complete, so we expect to see movement in this area soon. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. We will submit an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570042 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 4 | 0 | 20 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 4 | 0 | 0 | 4 | Completion of the project took longer than originally planned. We expect this to pick up going forward. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide 11 new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will complete the project closeout; this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570043 | 2010 | Q3 | Q3 - 2010 | Satisfied Section 106 SAC and revised ASV SAC. Set up and completed procurement processes for equipment and engineering designs. Completed engineering designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | See 2g above | N/A | N/A | On track | 1 | 1 | 3 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 0 | 0 | 0 | 0 | On track | On track | N/A | See 5c | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction RFP process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on engineering designs. During 3Q, was in process of fulfilling the Section 106 and the accounting system verification requirements. With these items completed, will get back on schedule in 4Q10 and early 1Q11. Worked closely with BTOP program officer throughout the quarter. | No challenges anticipated at this time. Possibly limited staff support during Thanksgiving and December holidays.
NT10BIX5570043 | 2010 | Q4 | Q4 - 2010 | Set up the construction procurement process at all the locations. Completed the wavelength system designs for all sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Variance due to delay in construction procurement activities (item 2f). | N/A | N/A | Variance due to delay in construction procurement activities (item 2f). | 1 | 0 | 12 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 0 | Pending the construction procurement process (item 2f). | Pending the construction procurement process (item 2f). | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Purchase equipment. Deploy equipment. Set up and complete construction procurement process. Begin construction and begin completing interconnection points. | Level 3 EON, LLC | Ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction procurement process is completed. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Possibly minor setbacks due to the delay in construction procurement process. We plan to be back on schedule by Q2 2011.
NT10BIX5570043 | 2011 | Q1 | Q1 - 2011 | Completed the construction procurement process. Began negotiations with the construction contractor to nail down the scheduling and scope of work (SOW). All DWDM and ADM designs are complete. Purchased DWDM and ADM equipment to support each of the locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pending the construction procurement process (item 2f above). | 1 | 0 | 12 | This is confidential per our contracts | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 0 | On Track | On Track | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | Begin construction at each of the locations and begin completing interconnection points. Deploy equipment. | Level 3 EON, LLC | Finished ahead of schedule on network and engineering designs. Delay on Network Build and deployment due to longer construction procurement process than expected. Ready to move forward quickly as soon as construction begins. | Variances due to delay in construction procurement process. No challenges anticipated at this time. Construction will commence in Q2 2011.
NT10BIX5570043 | 2011 | Q2 | Q2 - 2011 | All inside and outside plant construction is complete. Purchased dense wavelength division equipment and ADMs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Interconnection point in Elmdale is available for customers seeking wavelengths services. By the end of 3rd quarter we expect all interconnection points to be completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 1 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | Slightly behind baseline plan. Expect signed agreements to pick up when interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to complete all fiber splicing and equipment deployments. The majority of network testing should be completed by early 4th quarter. | Level 3 EON, LLC | The construction vendor selection process put our overall project behind, but we have since moved forward quickly and expect this to continue through the 3rd quarter. | Variances due to delay in construction procurement process. No challenges anticipated at this time. The equipment deployment will continue in Q3 2011.
NT10BIX5570043 | 2011 | Q3 | Q3 - 2011 | Completed all construction, equipment deployments and testing at each of the interconnection points. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Slightly behind baseline plan. Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We plan to see an increase in service requests now the interconnection points are near completion. | Level 3 EON, LLC | We haven't encountered any material challenges in the 3rd quarter. | We don't anticipate any major challenges at this time.
NT10BIX5570043 | 2011 | Q4 | Q4 - 2011 | Construction has been completed at all of the interconnection sites. All equipment has been deployed and tested. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We are finalizing invoices with the construction contractor. Expect to see an increase in service requests now that all four of the interconnection points are available. | Level 3 EON, LLC | We haven't encountered any material challenges in the 4th quarter. We are finalizing invoices with the construction contractor. | No challenges anticipated at this time.
NT10BIX5570043 | 2012 | Q1 | Q1 - 2012 | Finalized invoice payments to the construction contractor. Marketed services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time.
NT10BIX5570043 | 2012 | Q2 | Q2 - 2012 | We have been working with the NTIA to ensure an efficient project close out strategy. Continue to market our services to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 2nd quarter. | No challenges anticipated at this time.
NT10BIX5570043 | 2012 | Q3 | Q3 - 2012 | We have been working with the NTIA to determine exact process required for the project close out. Marketed services through out sales team to last mile providers. Submitted an award action request (AAR) to utilized the Cost-Sharing Method for a our matching funds. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin preparations for the project closeout, which will include discussions with the auditors for our final audit. Hope to also have our UCC-1 filings close to complete. | Level 3 EON, LLC | We didn't encounter any material challenges in the 3rd quarter. | No challenges anticipated at this time.
NT10BIX5570043 | 2012 | Q4 | Q4 - 2012 | Working with the NTIA on the project closeout process, which will happen in Q1 2013. Continued to market services through out sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Each of the 4 sites have been completed. | 1 | 0 | 12 | This is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Expect signed agreements to pick up now that interconnection points are completed. | Expect signed agreements to pick up now that interconnection points are completed. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to under served areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will begin project close out, UCC-1 fillings will be complete and begin the final audit process. | Level 3 EON, LLC | We didn't encounter any material challenges in the 4th quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570043 | 2013 | Q1 | Q1 - 2013 | Working with the NTIA on the project closeout process. Finalizing our final audit and reports. Continued to market services throughout sales team to last mile providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All interconnection points are complete. | 1 | 0 | 12 | The name of the providers is confidential per our contracts. | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. Pricing varies based on length of circuit, bandwidth, type of transport, and contract term. | N/A | 1 | 0 | 0 | 1 | Completion of the project took longer than originally planned. We expect this to pick up going forward. | The interconnection points are complete, so we expect to see movement in this area soon. | N/A | Protected and unprotected transport 50Mbps to 10Gbps to last mile providers. Speeds: 50M, 100M, 150M, 200M, 300M, 400M, 500M, 600M, 1G, 2.5G, 10G, OC-3, OC-12, OC-48, OC-192. | 0 | 0 | 0 | 0 | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | N/A - Will serve anchor institutions via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | N/A - Will serve households via last mile providers. | 0 | 0 | 0 | 0 | 0 | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | N/A - Will serve businesses via last mile providers. | We will provide four new access points on Level 3's existing broadband network to enable last mile providers to offer affordable high-speed services to underserved areas. The additional points of interconnection will offer broadband speeds between 50 Mbps and 10 Gbps. | FALSE | N/A | We will complete the project closeout; this will include our final audit, reports and UCC-1 fillings. | Level 3 EON, LLC | We didn't encounter any material challenges in the 1st quarter. | No challenges anticipated at this time. We expect the project closeout, including final audit, to go smoothly.
NT10BIX5570044 | 2010 | Q3 | Q3 - 2010 | Our Environmental Assessment was completed and we received a "Finding of No Significant Impact" (FONSI). We issued a Request for Qualifications for our fiber engineering consultant. We finalized the requirements for our Fiber-to-the-Premise (FTTP) equipment Request for Proposals (RFP). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | None. There have been informal discussions with several providers, but as we are 9 months away from turning up services, we have not formalized any relationships yet. | None yet. We will be providing layer two transport to retail service providers. We will transport their VLANs and IP space to their customers from a connection to our core electronics. See "Middle Mile - Wholesale" attachment for services and rates. | N/A - no third party operator. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | No services available yet. See "Middle Mile -Wholesale" attachment for proposed services and rates. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | No services available yet. See "Last Mile - Retail" attachment for proposed services and rates. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | No services available yet. See "Last Mile - Retail" attachment for proposed services and rates. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | No services available yet. See "Last Mile - Retail" attachment for proposed services and rates. | All of our customers will have at least 100 Mbps symmetric connectivity to each other, and to all local Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT). We will provide that local Intranet connectivity for customers with both 100 Mbps and 1 Gbps ONTs. This is very similar to the model deployed by Lafayette Louisiana in their FTTP system. | FALSE | N/A | We plan to hire our fiber engineering consultants and get them working on the details of our backbone rings and FTTP designs. We will issue and award our FTTP Electronics RFP. We plan to further develop our marketing plan for residential, business and Anchor Institution customers in the next quarter. | University of Illinois | There was also a delay in getting the proper accounts for this grant set up in the University's accounting system and processing grant expenditures. There were no charges processed through 9/30/10. So while officially we are at zero percent for all categories, there has been progress made on several fronts as noted above. The accounts have now all been set up and charges have been processed, so the next quarterly report will more accurately show expenditures and completion percentages. | If we have an early or heavy winter with persistent snow on the ground, that could impact our engineering firm's ability to complete their field surveys on time. Otherwise we expect the next quarter to get us caught up a little on our time line.
NT10BIX5570044 | 2010 | Q4 | Q4 - 2010 | The primary project accomplishment of the 4th quarter was the issuance of the Request for Proposals (RFP) for Engineering Services and the ultimate selection and hiring of Shive-Hattery, a civil engineering firm based in the Chicago area. They in turn have subcontracted with NewCom Technologies from Des Moines, which specializes in fiber construction planning and design. Both firms have been actively engaged in permit submittals, easement acquisition, surveying and design of the backbone rings and fiber-to-the-premise (FTTP) fiber infrastructure since the approval of Shive-Hattery's contract on November 18th by the University of Illinois Board of Trustees. Additionally, we finalized the evaluation criteria and issued an RFP for FTTP Electronics. The responses to that RFP were due in early January. The first two full-time grant-funded employees were also hired in December. The first is a GIS specialist and project manager with a Masters degree in Urban Planning who is working with Shive-Hattery on mapping and coordinating with our Anchor Institutions. The second is a fiber construction specialist with 30+ years of experience who has built fiber infrastructure in this community before and who is also working with Shive-Hattery on the construction planning and the outside plant materials specifications. In November, a local organization called eBlackCU sponsored a day-long symposium that explored how Big Broadband could impact education, religious organizations, community | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No construction was planned as of this quarter. | Discussions are ongoing with several organizations that may have infrastructure available that may be useful for our project and may be priced lower than what it would cost us to build it. Those discussions will be completed in the first quarter of 2011. | No construction was planned as of this quarter. | Both the City of Urbana and the City of Champaign have some existing conduit and fiber in the ground that will be sold to UC2B. While the verbal agreements have been in place for quite some time, the formal paperwork will not be executed until the second or third quarter of 2011. | No construction was planned as of this quarter. | N/A - we will not be deploying wireless links | N/A - we will not be building any towers | No construction was planned as of this quarters of this quarter. | 0 | 0 | 0 | None. We are 6 months away from turning up services, and we have focused our energies on getting the engineering complete and the construction process started. While we have had discussions with several last-mile providers and inquiries from others, those discussions will not get serious until the 2nd quarter of 2011 when the construction has been bid and we can shift our attention to recruiting service providers. We have both Marketing and Open Access subcommittees that are exploring ways to attract last-mile providers and to make the UC2B network a desirable place for them to do business. | We will provide middle-mile and last mile wholesale services on our backbone rings, and in our fiber-to-the-premise (FTTP) service areas. We agreed to provide Indefeasible Rights of Use (IRU) agreements for dark fiber for 8 organizations. We will also make dark fiber available to two state agencies - The Illinois Department of Transportation and to the Illinois Century Network (ICN), which provides Internet connectivity to state agencies, schools and local government. ICN will also have BTOP-funded cross-country fiber built to the edges of our community. We have agreed to provide fiber to connect their fiber to their Point of Presence. (Wholesale pricing plan is attached.d last mile wholesale services on our backbone rings, and in our fiber-to-the-premise (FTTP) service areas. We agreed to provide Indefeasible Rights of Use (IRU) agreements for dark fiber for 8 organizations. We will also make dark fiber available to two state agencies - The Illinois Department of Transportation and to the Illinois Century Network (ICN), which provides Internet connectivity to state agencies, schools and local government. ICN will also have BTOP-funded cross-country fiber built to the edges of our community. We have agreed to provide fiber to connect their fiber to their Point of Presence. (Wholesale pricing plan is attached.) | We have not designated a third party to operate our network. | 0 | 0 | 0 | 0 | We had not planned to provide wholesale services in this quarter. | We had not planned to provide wholesale services in this quarter. | We had not planned to provide wholesale services in this quarter. | While we are not yet providing any wholesale services, the attached "Wholesale Services" document lists the tiers of services we plan to provide. | 0 | 0 | 0 | 0 | We had not planned to provide services to Anchor Institutions in this quarter. | We had not planned to provide services to Anchor Institutions in this quarter. | We had not planned to provide services to Anchor Institutions in this quarter. | While we are not yet providing any services to Anchor Institutions, the attached "Retail Services" document lists the tiers of services we plan to provide. | 0 | 0 | 0 | 0 | 0 | We had not planned to pass any households in this quarter. | We had not planned to provide residential services in this quarter. | We had not planned to provide residential services in this quarter. | We had not planned to provide residential services in this quarter. | While we are not yet providing any residential services, the attached "Retail Services" document lists the tiers of services we plan to provide. | 0 | 0 | 0 | 0 | 0 | We had not planned to pass any businesses in this quarter. | We had not planned to provide any services to businesses in this quarter. | We had not planned to provide any services to businesses in this quarter. | We had not planned to provide any services to businesses in this quarter. | While we are not yet providing any services to businesses, the attached "Retail Services" document lists the tiers of services we plan to provide. | All of our customers will have at least 100 Mbps symmetric Intranet connectivity to each other, and to all local Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT). We plan to provide that local Intranet connectivity for customers with both 100 Mbps and 1 Gbps ONTs. This is very similar to the model deployed by Lafayette, Louisiana in their fiber-to-the-premise system. | FALSE | N/A | In the first quarter of 2011, we will determine the "winner" of our fiber-to-the-premise (FTTP) electronics Request for Proposals (RFP), and the contract resulting from that RFP will go before the University of Illinois Board of Trustees for approval in late March. We will receive the Design Documents from our engineering firm - Shive-Hattery - from which we will get a good indication of whether or not we have enough money in our budget to build the project as proposed within the total time allotted. Thus far, the preliminary indications have been positive on both counts, but should there be budget issues, in consultation with NTIA we will find ways of cutting costs so that we can execute our project but still stay within our approved budget. In terms of time, there is a good chance that late start of our activities necessitated by the Environmental Assessment and the winter weather in Central Illinois may prevent us from reaching the 67% milestone on 1/31/2012 However,we believe we will have no problem making our 100% completion deadline of 1/31/2013. We will continue to make a best effort to meet the 67% milestone. The Design Documents will probably reflect some minor changes from the route that we submitted for our Environmental Assessment (EA). This will require filing an amended EA in the next quarter. The approval process for that amended EA can happen in parallel with other local activities. There are no significant differences between the areas that have already b | University of Illinois | No sooner than our contract with our engineering firm - Shive-Hattery - was approved, Champaign-Urbana had an all-time record snowfall for the month of December - some 28 inches. This early and heavy snow impacted the ability of Shive-Hattery's surveyors to complete their in-field survey work for both the backbone rings and the fiber-to-the-premise (FTTP) areas. The overall physical network design proposed for UC2B is somewhat nontraditional, and the City of Urbana requested that once the engineering firm was hired that their first deliverable be a review of that backbone design with recommendations for possible improvements. Before the engineering firm could deliver that review, they needed to know the technology that would be deployed for the FTTP areas, as that technology choice would directly impact the infrastructure design needed for those areas and potentially the backbone ring design. Getting the FTTP electronics RFP perfected and released took longer than we wanted it to and that delayed the work of our engineers. The Overall Project completion percentage above only reflects the actual payments that have been processed by the University's Grants and Contracts office. Because we are essentially still ramping up this project, the expenses that show on that financial report do not yet accurately reflect the actual level of effort. For instance, at the close of this quarter our engineering firm had not yet billed us. Over the next two quarters our costs should becom | Should the remaining winter months have as much snowfall as December did, that could delay the timely completion of the engineering work, which then would delay the start of construction. In order to collect our local matching funds from the organizations that have agreed to purchase Indefeasible Rights of Use (IRU) agreements for dark fiber, we will need to be able to execute contracts for those IRUs. There are several issues pertaining to the issuance of IRUs on which NTIA has yet to make decisions. If those decisions are not forthcoming in the first quarter of 2011, that will impact our ability to collect matching funds, which impacts our ability to collect Federal funds, which could stall the project. Additionally, the three organizations that make up the UC2B Consortium have to decide on the operational legal structure for UC2B so it can sign those IRUs. While the consortium structure has worked well for seeking grants, as well as shaping policies and practices as we have refined the design of the network, hired an engineering firm and issued our FTTP electronics RFP, an Intergovernmental Consortium is not the ideal legal structure for UC2B as it moves into operations. Attorneys for all three parties are working on this issue and are expected to have their recommendations for better operational structures next quarter. If UC2B cannot sign IRUs, that triggers the same bad consequences detailed above. Our expectations are that we will receive the information we need f
NT10BIX5570044 | 2011 | Q1 | Q1 - 2011 | The were two significant accomplishments on the first quarter of 2011. First, we completed the RFP process for our Fiber-to-the-Premise (FTTP) technology. The recommendation of an Active Ethernet technology resulting from that RFP has been approved by the University of Illinois Board of Trustees, and is pending approval by the State of Illinois Chief Procurement Officer and NTIA. Our grant application had specified a different FTTP technology, but during Due Diligence, NTIA requested that we conduct a technology-neutral RFP, which we did. An Active Ethernet proposal was the winning technology in that RFP. The second accomplishment was the significant progress on the detailed engineering drawings for our seven fiber backbone rings and the FTTP infrastructure. At the end of the quarter, our engineering firm - Shive-Hattery - was prepared to deliver the 50% drawings in early April (which they did.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This is consistent with our baseline plan. | N/A | This is consistent with our baseline plan. | N/A | This is consistent with our baseline plan. | N/A | N/A | This is consistent with our baseline plan. | 0 | 0 | 0 | Until we get signed construction agreements and have established a firm time-line for building our infrastructure, UC2B is not real to wholesale and last mile providers. We know that UC2B will be a retail Internet service provider as well as a Middle-Mile Provider, so on the first day we are in a position to offer services, we know we will have at least one provider â€“ UC2B. Until we have several hundred customers connected, we do not foresee last-mile providers beating a path to our doors to provide their services to a small number of primarily low-income households. | We will provide middle- and last-mile wholesale layer-two transport on our Ethernet electronics, as well as provide dark fiber Indefeasible Rights of Use (IRU) agreements for 8 local organizations and two state agencies. The Illinois Department of Transportation will use our fiber for monitoring and managing an Intelligent Transportation System. The Illinois Century Network (ICN) provides Internet connectivity to state agencies, schools and local governments. ICN will have BTOP-funded cross-country fiber built to the edges of our community. We have agreed to provide UC2B fiber to connect their fiber to their Point of Presence. (UC2B's Wholesale pricing plan is attached.) | We have not designated a third party to operate any of our network. | 0 | 0 | 0 | 0 | Our baseline plan has indicated one signed agreement with a provider with new access in this quarter. We will achieve that in the 3rd quarter of 2011. We have been focused on getting construction started up until now. | Our baseline plan has indicated one signed agreement with a provider getting improved access in this quarter. We will achieve that in the 3rd quarter of 2011. Again, we have been focused on getting construction started up until now. | This is consistent with our baseline plan. | We have not begun to offer services yet, and hence there are no Wholesale or Last Mile subscribers. As our Active Ethernet equipment is automatically 1 Gbps, we no longer have any 100 Mbps-based tiers of retail services. Please see attached lists of UC2B Wholesale and Retail Services. | 0 | 0 | 0 | 0 | This is consistent with our baseline plan. | This is consistent with our baseline plan. | This is consistent with our baseline plan. | We have not begun to offer services yet, and hence there are no Community Anchor Institution subscribers. As our Active Ethernet equipment is automatically 1 Gbps, we no longer have any 100 Mbps-based tiers of retail services. Please see the attached lists of UC2B Wholesale and Retail Services. | 0 | 0 | 0 | 0 | 0 | This is consistent with our baseline plan. | This is consistent with our baseline plan. | This is consistent with our baseline plan. | This is consistent with our baseline plan. | We have not begun to offer services yet, and hence there are no Residential subscribers. As our Active Ethernet equipment is automatically 1 Gbps, we no longer have any 100 Mbps-based tiers of retail services. Please see the attached list of UC2B Retail Services. | 0 | 0 | 0 | 0 | 0 | This is consistent with our baseline plan. | This is consistent with our baseline plan. | This is consistent with our baseline plan. | This is consistent with our baseline plan. | We have not begun to offer services yet, and hence there are no Business subscribers. As our Active Ethernet equipment is automatically 1 Gbps, we no longer have any 100 Mbps-based tiers of retail services. Please see the attached lists of UC2B Retail Services. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. We are also considering layering a community-wide Wi-Fi service on top of the private Wi-Fi SSID that each of our customers will have. "UC2Bnet" Wi-Fi service would be available anywhere that there was UC2B service and would use the existing Wi-Fi equipment. UC2B fiber customers and "Wi-Fi only" UC2B customers could access the UC2Bnet wireless service wherever they can get the signal. As UC2B subscriber locations grow, the UC2Bnet Wi-Fi signal will be available in ever increasing areas throughout the community. UC2B "Wi-Fi only" customers would pay a monthly fee that would be less than the lowest rate that a fiber-connected customer pays, and would have access to less Internet bandwidth. Wi-Fi only customers would still have connectivity to all UC2B-connected Community Anchor Institutions and customers at the full speed of their wireless adapter. | FALSE | No Change. | During the next quarter, we will release our RFP's for fiber backbone and "fiber-to-the-curb" construction and award those contracts. We will also create the RFP for the construction of fiber from the curb into the buildings and release it late in the quarter. We will finalize the design of our core electronics and begin that procurement process. We will also have an RFP for UC2B's upstream Internet access. | University of Illinois | Our best hope for achieving substantial completion by 1/31/2012 lies in getting our contractors hired and into the field and building infrastructure as soon as possible. We have delayed some other planned activities to focus on starting construction. With a little cooperation from the weather, 8 of the remaining 10 months before our substantial completion deadline are months during which we could be installing fiber. Our fiber contractors will be highly motivated to get as much of our project competed in 2011 as they possibly can. They would prefer to compete our project before the next construction season if they possibly can. Their profits are tied to their ability to come in, get it built and move onto the next project. We are counting on their natural motivations to help achieve our completion goals. The weather may not cooperate however. We could have record rain throughout this summer and have an early hard freeze in late October or early November. Both events could delay construction to the point where we will not be able to complete 67% of our project by our substantial completion deadline. We are also starting to hear of fiber shortages. Once we hire our contractors, we will have a better idea of their access to fiber, and how any fiber shortage may impact our schedule. Until we know who has won our fiber construction RFPâ€™s, we will not know how many crews they will be able to bring to bear on our project. State law requires us to accept the lowest bid by a qua | As has been previously discussed the Environmental Assessment slowed us down by some six months as we could not incur non-EA-related expensed until after receiving our Finding of No Significant Impact. Also previously discussed has been the complexity of our project. We grossly underestimated the time it would take to complete some tasks. There has been constant effort, but the targets we established in the Baseline Plan were not realistic. It has also taken our engineering firm far more time than they estimated to compete their detailed fiber construction drawings. It was a challenge to get some of the participants in this project to stop trying to optimize this or that. Even when we established a firm date for no more changes, not everybody honored that request. One of our municipalities requested a review of the fiber backbone design before allowing the engineering firm to seriously start their design efforts. But at the end of the day, the single biggest contributor to the variance between our projected completion percentage and our actual for any of these categories is that we lacked tools to more accurately predict how long individual steps would take to complete. While some activities need to be done serially, some can be done in parallel if you have a lot of equally qualified people to work in parallel. UC2B is a lean and mean operation, which is good for containing expenses, but it is bad in that we sometimes have human choke points. This time crunch will hopefu
NT10BIX5570044 | 2011 | Q2 | Q2 - 2011 | The most significant accomplishment of this quarter was the release of the RFPs for our three construction bid packages. The combined total of the three low bids exceeded our budget, so at the end of the quarter we were in negotiations with the apparent low bidders on changes to the specifications that would allow them to reduce their costs and pass those savings onto the project. We believe we were able to find ways to cut costs that did not negatively impact the overall scope or purposes of our project. We have also filed a request for an amended Environmental Assessment to take into account some small route changes that were made during the fiber engineering process. Approvals were pending with Fish and Wildlife as well as the Illinois Historical Preservation Agency at the end of the quarter. The RFP winner for the UC2B Fiber-to-the-Premise (FTTP) electronics was approved both by the University of Illinois Board of Trustees as well as the State of Illinois procurement office. The vendor has a major hardware/software release scheduled for August 21st, so we will wait until then to purchase this equipment. In the meanwhile we are making arrangements to have demo equipment shipped to us so that our network engineers can become more familiar with it. We are also planning for two community forums at which we will demonstrate this technology. We have also begun work on an RFP to procure a fiber management system. That RFP will most likely be released in the next quarter. We h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline projected 56.45 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | N/A | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We will be purchasing some existing fiber and conduit infrastructure and will either be installing larger fiber cables, or lighting more of the existing strands. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | N/A | Baseline projected 56.45 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | N/A | N/A | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. Baseline projected 198 interconnection points. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012s for any variance from the baseline plan or any other relevant information) starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. Baseline projected 198 interconnection points. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | 0 | 0 | 0 | We have not signed any wholesale or last mile provider agreements yet. We have concentrated all of our efforts thus far in getting construction started. Until we have fiber in the ground we cannot reasonable expect any wholesale or last-mile provider to be serious about negotiating or entering into agreements with us. This activity will pick up speed in the 3rd and 4th quarters of this year. | We will provide layer-two transport services, which are often referred to as Metro Ethernet. We will also offer dark fiber services. We have several commitments for 20-year dark fiber IRUs, but have not completed those contracts yet. We may also offer shorter term dark fiber leases. Attached are our proposed pricing plans for layer-two transport and 20-year dark fiber IRUst services, which are often referred to as Metro Ethernet. We will also offer dark fiber services. We have several commitments for 20-year dark fiber IRUs, but have not completed those contracts yet. We may also offer shorter term dark fiber leases. Attached are our proposed pricing plans for layer-two transport and 20-year dark fiber IRUs. | We have not designated a third party to operate any portion of our network. | 0 | 0 | 0 | 5 | Baseline projected 1 provider with new access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to be caught up with our baseline projection in this area by the end of the 4th quarter of 2011. | Baseline projected 3 providers with improved access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about a full quarter. We expect to be caught up with our baseline projection in this area by the end of the 4th quarter of 2011. | The baseline did not include a projection for dark fiber customers. | There will be two levels of customer connectivity - 100 Mbps and 1 Gbps, and three levels of provider connectivity - dual 1 Gbps connections, dual 2 Gbps connections and dual 10 Gbps connections to our network core. See the attached chart of wholesale services and speed tiers for customer and provider connections. | 0 | 0 | 0 | 5 | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any Anchor Institutions. We will serve our first Anchor Institutions in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any Anchor Institutions. We will serve our first Anchor Institutions in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any Anchor Institutions. We will serve our first Anchor Institutions in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | There are five levels of Anchor Institution connectivity. They are detailed on the attached chart of retail services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | 0 | 0 | 0 | 0 | 5 | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any households. We will pass our first residences in the 3rd quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any households. We will serve our first residences in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any households. We will serve our first residences in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any households. We will serve our first residences in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | There are five levels of residential connectivity. They are detailed on the attached chart of retail services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | 0 | 0 | 0 | 0 | 5 | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any businesses. We will pass our first businesses in the 3rd quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any businesses. We will serve our first businesses in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any businesses. We will serve our first businesses in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction and serving any businesses. We will serve our first businesses in the 4th quarter of 2011. We will get back on our baseline plan in the 3rd quarter of 2012. | There are five levels of business connectivity. They are detailed on the attached chart of retail services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. We are also considering layering a community-wide Wi-FI service on top of the private Wi-Fi SSID that each of our customers will have. UC2Bnet Wi-Fi service would be available anywhere that there was UC2B service and would use the existing Wi-Fi equipment. UC2B fiber customers and "Wi-Fi only" UC2B service could access the UC2Bnet wireless service wherever they can get the signal. As UC2B subscriber locations grow, the UC2Bnet Wi-Fi signal will be available in ever increasing areas throughout the community. UC2B "Wi-Fi only" customers would pay a monthly fee that would be less than the lowest rate that a fiber-connected customer pays, and would have access to less Internet bandwidth. Wi-Fi only customers would still have connectivity to all UC2B-connected Community Anchor Institutions and customers at the full speed of their wireless adapter. | FALSE | N/A | We have our negotiated fiber construction contracts queued up to be approved by the City of Urbana and the City of Champaign city councils the first week in August. That will set the stage for fiber construction to begin later in August or in early September. We will stage construction so that we can get a maximum number of Community Anchor Institutions throughout the community as well as households and businesses in our eleven underserved Census Block Groups connected this calendar year. We will not be able to complete all fiber construction this calendar year, but we will seek to optimize the results we get from what we can accomplish before the ground freezes. | University of Illinois | Our primary challenge in the last quarter was that the low bids for our three construction packages totaled more than we have budgeted or available. As was detailed above, we entered into a "Value Engineering" process with the two apparent low bidders. At the end of the quarter it looked likely that we would be able to drive enough cost from the construction to meet our budget without negatively impacting the scope or goals of our project. | Like many BTOP projects, we are concerned about the availability of fiber-optic cables. Our contractors will be providing their own materials and in the next quarter we will learn of what they have available to them and what we may have to wait on. It is possible that we will be able to complete most of our conduit infrastructure this calendar year, but may need to wait until 2012 to have access to fiber in the lengths and strand-counts we need. If we lack access to the fiber we need, it will negatively impact our equipment deployment as well as our network testing line items, not to mention providing services. We will have two prime fiber installation contractors on this project working in different parts of the community. It is possible that each will have upwards of 20 boring crews here at the same time. Those 30-40 crews could be quite a burden for the local J.U.L.I.E. underground utility locate crews. The Public Works departments of both cities are working on ways to coordinate the locates and keep the locators a step ahead of the contractors.
NT10BIX5570044 | 2011 | Q3 | Q3 - 2011 | The third quarter was mostly devoted to finalizing our first phase construction contracts with two contractors, staging a groundbreaking ceremony and then actually beginning construction. Our first phase of construction involves building the seven fiber backbone rings that span the community, the fiber-to-the-curb infrastructure in the 11 underserved Census Block Groups, and the fiber laterals-to-the-curb for the Community Anchor Institutions that are outside of the fiber-to-the-premise (FTTP) areas. Our construction bids came in above our budget, so much of the third quarter was spent â€œvalue engineeringâ€ the project in an effort to reduce costs without impacting the overall goals and purpose of our project. We were successful doing that, and on September 6th, we had our groundbreaking ceremony, which was attended by more than 150 people and featured short speeches by our local mayors and the Universityâ€™s Chancellor. The next week we held two public open houses at which community residents could see the actual FTTP electronics that we will be deploying in action, and learn about some of the applications we expect to be available over the gigabit network. Each session was attended by more than 75 people. By the end of the quarter, one of our contractors had two directional boring crews up and running, and the second contractor was on the verge of starting their construction in early October. Both contractors will gradually increase the number of crews they have deploye | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline projected 129.5 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are getting conduits, manholes and handholes installed. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we did install our first 3 miles of conduit in September. | N/A | This was not a milestone in the Baseline Plan. | N/A | Baseline projected 129.5 miles. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are getting conduits and manholes installed. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we did install our first 3 miles of conduit in September. | N/A | N/A | Baseline projected 396 interconnection points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are getting conduits, manholes and handholes installed. We expect to get caught up to our baseline projection in the 3rd quarter of 2012n points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are getting conduits, manholes and handholes installed. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | 0 | 0 | 0 | We have not signed any wholesale or last mile provider agreements yet. We have concentrated all of our efforts thus far in getting construction started. Until we have fiber in the ground we cannot reasonable expect any wholesale or last-mile provider to be serious about negotiating or entering into agreements with us. This activity will pick up speed in the next two quarters as we approach a launch of services in late March or early April of 2012. | We will provide layer-two transport services, which are often referred to as Metro Ethernet. We will also offer dark fiber services. We have several commitments for 20-year dark fiber IRUs, but have not completed those contracts yet. We may also offer shorter term dark fiber leases. Attached are our proposed pricing plans for layer-two transport and 20-year dark fiber IRUs.3 | We have not designated a third party to operate any of our network. | 0 | 0 | 0 | 5 | Our baseline projected 1 provider with new access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 1st quarter of 2012. | Our baseline projected 4 providers with improved access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 1st quarter of 2012. | The baseline did not include a projection for dark fiber customers. | There are no active subscribers of our wholesale services yet. There are two planned levels of customer connectivity - 100 Mbps and 1 Gbps, and three planned levels of provider connectivity - dual 1 Gbps connections, dual 2 Gbps connections and dual 10 Gbps connections to our network core. See the attached chart of UC2B Wholesale Services for customer and provider connection details. | 0 | 0 | 0 | 5 | Our baseline was 57 total CAIs served. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first Anchor Institutions in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was zero. | Our baseline was 57 CAIs receiving improved access. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first Anchor Institutions in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are no active CAI subscribers as of yet. There are five planned levels of Anchor Institution connectivity. They are detailed on the attached chart of UC2B Retail Services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | 0 | 0 | 0 | 0 | 5 | Our baseline was 3,712. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customer in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 750 total household subscribers. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential subscriber in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline 113. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customer in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 638. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customers in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are no residential subscribers as of yet. There are five planned levels of residential connectivity. They are detailed on the attached chart of UC2B Retail Services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | 0 | 0 | 0 | 0 | 5 | Our baseline was 160 businesses passed with fiber. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 46 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 7 businesses receiving new access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 39 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are no business subscribers as of yet. There are five planned levels of business connectivity. They are detailed on the attached chart of UC2B Retail Services. All levels have 1 Gbps connections to the UC2B Intranet. The Internet bandwidth is tiered from 5 Mbps to 40 Mbps. All connections are symmetrical. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. We are also considering layering a community-wide Wi-FI service on top of the private Wi-Fi SSID that each of our customers will have. UC2Bnet Wi-Fi service would be available anywhere that there was UC2B service and would use the existing Wi-Fi equipment. UC2B fiber customers and "Wi-Fi only" UC2B service could access the UC2Bnet wireless service wherever they can get the signal. As UC2B subscriber locations grow, the UC2Bnet Wi-Fi signal will be available in ever increasing areas throughout the community. UC2B "Wi-Fi only" customers would pay a monthly fee that would be less than the lowest rate that a fiber-connected customer pays, and would have access to less Internet bandwidth. Wi-Fi only customers would still have connectivity to all UC2B-connected Community Anchor Institutions and customers at the full speed of their wireless adapter. | FALSE | N/A | In the next quarter, we plan to bid our fiber management system and the installation of our fiber from the curb to the buildings. In the next quarter we also plan to purchase our first wave of Fiber-to-the-Premise (FTTP) electronics, and the core network electronics. We will also receive the recommendations from the municipal broadband consultant (hired outside of grant funds) in the coming quarter. Those recommendations will inform the UC2B Policy Board's discussions and decisions on a variety of issues; including our service offerings, business practices and operational issues that impact our outreach and marketing. The first wave of the door-to-door canvass will also be completed in the next quarter. "Project Indicators (Next Reporting Quarter), Question 1: As part of your description of planned project accomplishments for next quarter (Q4 2011), please also provide updated projections for the following key indicators: â€¢ New network miles deployed - Zero. Target was 90%. We will not have fiber until Q1 of 2012. â€¢ New network miles leased - Zero. Target was Zero. We will not be leasing fiber. â€¢ Total CAI subscribers served (CAIs connected) - Zero. Target was 114. We will not have fiber until Q1 of 2012. â€¢ Number of signed agreements with broadband wholesalers or last mile providers - Zero. Target was four. That contract work will be done in Q1 of 2012. | University of Illinois | The primary challenges in the past quarter were getting the construction contracts and sub-award agreements finalized. Most of our construction is being done through sub-awards to the cities of Urbana and Champaign. Once they got their respective construction contracts finalized, we then needed to finalize the sub-award agreements. All of those activities took much longer then we would have liked, but they are now all complete. | Our primary potential challenges for the next quarter will the the weather and fiber availability. The longer the weather remains favorable, the more conduit and manholes our contractors will be able to get into the ground. Neither of our contractors expects to receive backbone fiber much before the end of the year, so in terms of the metrics for this report, we will still show a lot of zeros next quarter, even though we may have a fair amount of conduit installed. We expect the weather to eventually get bad enough that we will need to suspend construction until the Spring. With a little luck, we will get two full months under our belt in this coming quarter.
NT10BIX5570044 | 2011 | Q4 | Q4 - 2011 | The 4th quarter of 2011 was dominated by the start of construction by both of our fiber contractors. Through the end of December they had completed roughly 261,000 feet of conduit installation, which is approximately 30% of our total project. Much of that total was in the Fiber-to-the-Premise (FTTP) areas, where manholes and handholes are frequent and the progress is slower than on the backbone rings. In December both contractors brought plowing rigs to town to install conduit in the more â€œruralâ€ sections of our backbone and lateral routes that lent themselves to plowing instead of directional boring. Plowing typically goes much faster than horizontal/directional boring. At the same time we have been finalizing our procurement process for the installation of fiber from the curb into homes, businesses and Anchor Institutions. After some public meetings in early January to get additional community and contractor input, that RFP will go out for bid in the first quarter of 2012. On December 19th, the five fiber construction crews that were previously working in Champaign all moved to the University campus to install conduits in the high traffic areas while the students were gone on their semester break. The weather cooperated, and they were able to complete all of the campus conduit work by mid-January. In general the weatherman has been our friend through December and January, as there have been no significant accumulations of snow and our contractors have been able to work throughout both months. In November and December our "Community Ambassadors" took to the streets in some of our FTTP areas to reach out to the residents and businesses and determine who was interested in subscribing to UC2B's FTTP service. Through the first 900 households they talked to, 58% have expressed interest in subscribing to UC2B. There are a total of roughly 4850 households and businesses in our FTTP service areas. The follow-up visits by the Ambassadors will begin on March 5th, at which time potential customers will be asked to sign on the dotted line. Even if there is a 10% drop-off when households are asked to formally commit to paying for UC2B services, we will still be in the ballpark of the 54% take rate we projected in our grant application. The next major milestone for our construction efforts will be in February when both of our contractors expect to receive their first shipments of fiber. For now they are only installing conduits, manholes and handholes. Once the fiber arrives, the contractors will bring on additional crews to pull, splice and terminate the fiber in the conduits that have already been installed. We hope to light up our first Anchor Institutions and FTTP customers in April or May. We have now placed our order for the core FTTP equipment. We are waiting for our FTTP vendor to release a combo "Optical Network Terminal - Gateway - Wi-Fi" device in the near future. Once we can order them we will place our first CPE order. We will be ordering the network core electronics in February. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline projected 169 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are installing conduits, manholes and handholes. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 50 miles of conduit through December. | N/A | This was not a milestone in the Baseline Plan. | N/A | Baseline projected 169 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are installing conduits, manholes and handholes. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 50 miles of conduit through December. | N/A | N/A | Baseline projected 396 interconnection points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are installing conduits, manholes and handholes. We expect to get caught up to our baseline projection in the 3rd quarter of 2012n points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors will also not be able to get fiber until the 1st quarter of 2012. In the meanwhile they are installing conduits, manholes and handholes. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | 0 | 0 | 0 | We do not have any signed agreements with wholesale or last mile providers yet. The UC2B Policy Board has engaged the services of a municipal broadband consultant (with non-grant funds) to perform a final review of our business model and services matrix. Their final report is due February 15th, after which we will move forward with wholesale and last mile service provider agreements. | The wholesale services we anticipate providing include private VLAN transport and dark fiber leases. While the proposed wholesale services matrix is being reviewed and may be adjusted in the next quarter, we have attached the plan as it stands today.3 | While we we may do so in the future, at this time we have not designated a third party to operate any of our network. | 0 | 0 | 0 | 5 | Our baseline projected 1 provider with new access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 2nd quarter of 2012. | Our baseline projected 4 providers with improved access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 2nd quarter of 2012. | The baseline did not include a projection for dark fiber customers. | While our suite of services is currently under review, the proposed wholesale services are provided on the attachment titled UC2B Wholesale Services. There are five planned levels of Wholesale and Last Mile Provider connectivity. This will be finalized in the next quarter. | 0 | 0 | 0 | 3 | Our baseline was 114 total CAIs served. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first Anchor Institutions in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was zero. | Our baseline was 114 CAIs receiving improved access. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first Anchor Institutions in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | While this suite of services is currently under review, the proposed services are on the attachment titled UC2B Retail Services. We have simplified our proposed retail services, and combined the former 5 Mbps, and 10 Mbps services into the 20 Mbps service. There are currently three planned levels of Anchor Institution connectivity. We are considering having a separate pricing plan for non-profit and Anchor Institutions. This will be finalized in the next quarter. | 0 | 0 | 0 | 0 | 3 | Our baseline was 4,640. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customer in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 1,250 total household subscribers. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential subscriber in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 188. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customer in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 1,063. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first residential customers in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | While this suite of services is currently under review, the proposed services are on the attachment titled UC2B Retail Services. We have simplified our proposed retail services, and combined the former 5 Mbps, and 10 Mbps services into the 20 Mbps service. It has already been decided by the UC2B Policy Board that the $19.99-a-month 20 Mbps symmetric residential service will be part of the final plan. There are three planned levels of Residential connectivity. This plan will be finalized in the next quarter. | 0 | 0 | 0 | 0 | 3 | Our baseline was 200 businesses passed with fiber. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 57 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 9 businesses receiving new access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 48 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now face a fiber shortage that will further delay our progress. We will serve our first business in the 2nd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | While this suite of services is currently under review, the proposed services are on the attachment titled UC2B Retail Services. We have simplified our proposed retail services, and combined the former 5 Mbps, and 10 Mbps services into the 20 Mbps service.We are considering having a separate pricing plan for for-profit businesses. There are currently three planned levels of Business connectivity. This will be finalized in the next quarter. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. We are in the final stages of planning for a layered community-wide Wi-FI service on top of the private Wi-Fi SSID that each of our customers will have. UC2Bnet Wi-Fi service would be available anywhere that there was UC2B service and would use the existing Wi-Fi equipment. UC2B fiber customers and "Wi-Fi only" UC2Bnet service customers could access the UC2Bnet wireless service wherever they can get the signal. As the number of UC2B subscriber locations grows, the UC2Bnet Wi-Fi signal will be available in ever increasing areas throughout the community. UC2Bnet "Wi-Fi only" customers would pay a daily, weekly, monthly or annual fee that would be less than the lowest rate that a fiber-connected UC2B customer pays, and would have access to less Internet bandwidth. UC2Bnet "Wi-Fi only" customers would still have connectivity to all UC2B-connected Community Anchor Institutions and customers at the full speed of their wireless adapter. We have included proposed pricing for this service on our UC2B Retail Services attachment. | FALSE | N/A | Next quarter will mark the installation of the first fiber cables as well as the installation of all of the core network elements and our Internet connection. While it is not likely that we will turn up the first customer by March 31st, that happy event will not be too long after that. We will make sure it is a public event with media coverage. As noted earlier, January has been very unseasonably warm, and our contractors have been able to make far more progress with installing conduits that they ever anticipated. While we cannot rationally hope for more of the same weather through February and March, the forecast for the first week of February shows no sign of snow or winter. The Community Ambassadors will return to the streets in March, and they will return with our first signed contracts for UC2B services, paving the way for activating those customers in April or May. The UC2B Policy Board has a host of pending decisions to make, all of which will affect our deployment of services. Once they have their consultant's report in hand, they are prepared to act with a sense of urgency and finalize service plans and policies. Also expected are decisions on if and how to outsource day-to-day operations. After the consultantâ€™s report is delivered, we also plan to finalize our pending IRU agreements with our local â€œinvestorsâ€. We anticipate having 10 new network miles completed by the end of the next quarter. The first shipments fiber will be arriving in mid-February, and | University of Illinois | The past quarter had no significant challenges. | Weather is our first concern this time of year. While we have had a mild winter thus far, should we get an accumulation of snow, that would slow down our progress.
NT10BIX5570044 | 2012 | Q1 | Q1 - 2012 | Our fiber construction contractors were able to capitalize on the unusually mild winter we have just come through. While they had hoped to be able to average 5-10 working days each month in the past quarter, they were actually able to work almost every single day. As of the end of March, they had installed 622,558 feet of conduit (117.91 miles), which represents 74.2% of the planned total for our seven fiber rings and the fiber-to-the-curb in our targeted 11 Census Block Groups that will receive Fiber-to-the-Premise (FTTP) services. Further, both contractors received their first shipments of fiber in February and have been able to install 41,890 feet of fiber (18.0 miles) thus far, which represents 7.3% of our planned total for the project. Our Fiber-to-the-Premise electronics vendor has shipped all of our core FTTP equipment, and the node locations are being prepared for that equipment to be installed in the second quarter. The RFP for contractors to install the fiber from the curbs into buildings has taken longer to develop than we would have liked, and it was not released in the first quarter as we had hoped. It was issued on April 20th. We have taken some extra steps to encourage participation from Minority and Female-owned businesses, as well as implementing a scoring scheme that promotes diversity in the workforce. We will know by the end of the next quarter if those efforts have been successful. Our Community Ambassadors have been out knocking on doors in our FTTP areas, and thus far more than 70% of those households they have spoken with have expressed interest in subscribing to UC2B service. Once we have retail service agreements ready for them to sign in May, the Ambassadors will revisit those households who expressed interest and get them signed up for UC2B service. We are converging on early July as the date for the turn up of our first retail fiber customers. The UC2B Policy Board has now approved our complete suite of retail Internet services. They are attached to this report. In general they are very similar to what was proposed in our BTOP grant application. In the interest of sustainability, we did add some differentiation (higher rates) for customers who need more than one public IP address and for customers who require more than 40 Mbps of symmetric Internet bandwidth. All of our customers have access to 1 Gbps of Intranet bandwidth, regardless of how much Internet bandwidth they purchase. Our three core retail tiers remain 20 Mbps, 30 Mbps and 40 Mbps of symmetric Internet bandwidth that is priced at roughly $1.00 per Mbps per month. Those tiers are available to homes and businesses located in the 11 underserved Census Block Groups that are eligible for FTTP services as well as to Community Anchor Institutions located throughout the community. As we have no current funding to expand our network beyond the grant-funded areas, we have not yet developed a retail rate structure for other areas of the community. UC2B was one of the founding communities of the Gig.U initiative and we continue to work with the 36 other University communities to develop strategies for expanding our services through our community in the future. For now we are concentrating on executing and finishing our BTOP grant-funded construction. In some ways UC2B is a prototype for the Gig.U effort. We know that the higher education community is watching us closely. In May, the UC2B Policy Board will be considering the Wholesale pricing that was proposed in our BTOP grant application and throughout the Due Diligence process. | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 111 | Baseline projected 172 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors did receive their fiber in the 1st quarter of 2012. As they get close to finishing their conduit installations, they will increasingly turn more of their attention to installing fiber. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 118 miles of conduit through March. | N/A | This was not a milestone in the Baseline Plan. | N/A | Baseline projected 172 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors did receive their fiber in the 1st quarter of 2012. As they get close to finishing their conduit installations, they will increasingly turn more of their attention to installing fiber. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 118 miles of conduit through March. | N/A | N/A | Baseline projected 495 interconnection points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. As our contractors start installing and splicing fiber in the second quarter, this number will grow significantly. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | 0 | 1 | 0 | We do not have any signed agreements with wholesale or last mile providers yet. The UC2B Policy Board has engaged the services of a municipal broadband consultant (with non-grant funds) to perform a final review of our business model and services matrix. The Policy Board is considering the report from the consultant before taking final action in this area. | The wholesale services we anticipate providing include private VLAN transport and dark fiber leases. While the proposed wholesale services matrix is being reviewed and may be adjusted in the next quarter, we have attached the plan as it stands today. | While we we may do so in the future, at this time we have not designated a third party to operate any of our network. | 0 | 0 | 0 | 5 | Our baseline projected 1 provider with new access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 2nd quarter of 2012. | Our baseline projected 4 providers with improved access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 2nd quarter of 2012. | The baseline did not include a projection for dark fiber customers. | While our suite of services is currently under review, the proposed wholesale services are provided on the attachment titled UC2B Wholesale Services. There are five planned levels of Wholesale and Last Mile Provider connectivity. This will be finalized in the next quarter. | 0 | 0 | 0 | 11 | Our baseline was 143 total CAIs served. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We will serve our first Community Anchor Institutions in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was zero. | Our baseline was 143 CAIs receiving improved access. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We will serve our first Anchor Institutions in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are 3 tiers of symmetric bandwidth that form the core of our retail services for Community Anchor Institutions. We expect most of our CAI customers to subscribe to one of those three tiers. They are detailed on the attached rate sheet. However, we do also have eight additional expanded tiers that allow for additional pubic IP addresses and greater bandwidth than in our core tiers. While we do expect a few customers to want these expanded services, we believe our three core tiers will meet the needs of most of our CAI customers. These 8 additional tiers and the charges for additional public IP addresses are provided on an attached file. None of these tiers have any subscribers at this time. | 1013 | 0 | 0 | 0 | 11 | Our baseline was 4,640. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customer in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Baseline was 1,500. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow ring and fiber-to-the-curb fiber. We will finish hiring our contractor(s) for installing fiber from the curb into the buildings (FTTP) in the second quarter, but they will probably not begin making those installations until the last week of June or the first week of July. We are requiring our bidders on the FTTP RFP to demonstrate that they can accomplish the number of installations per week that we need to achieve in order to complete our project by 1/31/2013. We do not expect to catch up to our baseline numbers until the end of the 4th quarter of 2012. | Our baseline was 225. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customer in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 1,275. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customers in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are 3 tiers of symmetric bandwidth that form the core of our retail residential services. We expect most of our residential customers to subscribe to one of those three tiers. They are detailed on the attached rate sheet. However, we do also have eight additional expanded tiers that allow for additional pubic IP addresses and greater bandwidth than in our core tiers. While we do expect a few residential customers to want these expanded services, we believe our three core tiers will meet the needs of most of our residential customers. These 8 additional tiers and the charges for additional public IP addresses are provided on an attached file. None of these tiers have any subscribers at this time. | 8 | 0 | 0 | 0 | 11 | Our baseline was 200 businesses passed with fiber. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 57 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 9 businesses receiving new access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 48 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are 3 tiers of symmetric bandwidth that form the core of our retail businesses services. We expect most of our business customers to subscribe to one of those three tiers. They are detailed on the attached rate sheet. However, we do also have eight additional expanded tiers that allow for additional pubic IP addresses and greater bandwidth than in our core tiers. While we do expect a few customers to want these expanded services, we believe our three core tiers will meet the needs of most of our business customers. These 8 additional tiers and the charges for additional public IP addresses are provided on an attached file. None of these tiers have any subscribers at this time. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. We are in the final stages of planning for a layered community-wide Wi-FI service on top of the private Wi-Fi SSID that each of our customers will have. UC2Bnet Wi-Fi service would be available anywhere that there was UC2B service and would use the existing Wi-Fi equipment. UC2B fiber customers and "Wi-Fi only" UC2Bnet service customers could access the UC2Bnet wireless service wherever they can get the signal. As the number of UC2B subscriber locations grows, the UC2Bnet Wi-Fi signal will be available in ever increasing areas throughout the community. UC2Bnet "Wi-Fi only" customers would pay a daily, weekly, monthly or annual fee that would be less than the lowest rate that a fiber-connected UC2B customer pays, and would have access to less Internet bandwidth. UC2Bnet "Wi-Fi only" customers would still have connectivity to all UC2B-connected Community Anchor Institutions and customers at the full speed of their wireless adapter. | FALSE | N/A | The next quarter will be all the behind-the-scenes activity leading up to the lighting of our first fiber customers. We expect that to happen in early July. Before we can light up that first customer, we will have decided on the contractor to install fiber from the curb to the residences and businesses, hired a firm to provide call-center customer support, hired a firm to do truck-roll customer support, accepted the first of twelve fiber distribution hub service areas' infrastructure and turned up our upstream Internet connection in Chicago. It will be a very active quarter. We will also finalize our IRU agreements with the organizations that provided our local matching funds, and collect the first installments of those payments. We expect all of our conduit to be completed in the next quarter and a significant portion of our fiber blown into those conduits. Our estimate is that we will have 166 miles of new fiber installed by the end of the next quarter which is 67.7 percent of our estimate for the entire project. We will light up the first couple of fiber distribution hubs for testing purposes and make sure all of our equipment is performing as expected. As part of our testing process, we will also connect 20 Community Anchor Institutions, whose fiber from the curb to the building will be installed by our phase one contractors. We moved those CAI locations to our phase one contractors due to one or more of several reasons which included: the length or the complexity of the construction, the need to coordinate with other phase one construction, and some critical time factors for the CAI. We expect to finalize our terms and conditions for broadband wholesale and last mile providers in the next quarter and sign one agreement prior to June 30th. | University of Illinois | The past quarter had no significant challenges. | We will bid and award our construction from the curb into our customer's buildings in the next quarter. Some of our existing contractors may win this work, but we could end up with an entirely new set of contractors to work with. There will be a short period of time when our existing contractors who are building fiber to the curb overlap with the new contractors. That overlap could be contentious in regards to issues such as landscape restoration, or it could go smoothly. We know that it will tax our resources to be able to oversee all of the crews simultaneously. There is not much that NTIA can do to assist with this period of overlap.
NT10BIX5570044 | 2012 | Q2 | Q2 - 2012 | The second quarter of 2012 was a productive one for UC2B. Our contractor in Urbana has completed just about all of the conduit installation for the fiber rings and the fiber-to-the-curb, and is finishing up with manhole installation and landscape restoration. They have started pulling fiber and splicing as well. The contractor on the University campus has installed all of the ring conduits, manholes and fiber and has started splicing. The contractor in Champaign and Savoy is 88% complete with conduits and has started pulling fiber as well. The work in the nodes for the central core network equipment is just about complete. The DC power systems are installed and operational and our networking staff members have started configuring and testing the core networking equipment in those nodes. The twelve neighborhood equipment cabinets have arrived and will be installed soon. We have placed orders for the remaining core network equipment as well as the customer premise equipment. We have recently completed the RFP process to hire a contractor for building fiber from the curb into the homes, businesses and Community Anchor Institutions and installing customer premise electronics. We have signed a contract with the winning firm. They will start their work in July and continue through the end of our BTOP grant period â€“ January 31, 2013. All of this is leading up to the beginning of UC2B services to customers in select areas in August and expanding those areas throughout the fall. Our Community Ambassadors are going door-to-door securing signatures on service agreements with Anchor Institutions, businesses and households and doing the pre-coordination work for the fiber installation. At the end of June we had 299 signed contracts, representing 277 households and 4 businesses in the Fiber-to-the-Premise (FTTP) service areas and 18 Community Anchor Institutions spread across the entire community. Of those 299 customers, 70.5% (211) subscribed to the 20/1,000 Mbps Consumer service, while 14.4% (43) subscribed to the 30/1,000 Mbps Consumer service while another 14.4% (43) subscribed to the 40/1,000 Mbps Consumer service. There was one business that subscribed to the 20/1,000 Mbps Commercial service and one Anchor Institution that subscribed to the 40/1,000 Commercial service. Those numbers represent a much higher percentage of customers subscribing to the higher bandwidth services than we had projected. If those percentages hold as we sign up additional subscribers that will help our sustainability. While it is too early to make any bold statements, thus far we seem to have crafted services and prices that are being well received by the underserved residents in our grant-funded FTTP service areas. Thus far all budget categories are within our projections, but we have not closed out any of the construction contracts yet, and we know that some of the funds we set aside for contingency will be used. By the end of the next quarter we should have a more detailed understanding of where we are with our budget. | 88 | 0 | 2 | 0 | 88 | 0 | 0 | 226 | Baseline projected 179.78 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors did receive their fiber in the 1st quarter of 2012. As they get close to finishing their conduit installations, they are concentrating on installing fiber. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 146 miles of conduit through June. | N/A | This was not a milestone in the Baseline Plan, but we have some short segments of conduit and fiber that we are taking over from the cities of Urbana and Champaign. These will be complete at the end of the next quarter. | N/A | Baseline projected 179.78 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. Our contractors did receive their fiber in the 1st quarter of 2012. As they get close to finishing their conduit installations, they are concentrating on installing fiber. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. While this is not a metric that NTIA is tracking, we have installed 146 miles of conduit through June. | N/A | N/A | Baseline projected 495 interconnection points. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. As our contractors continue installing and splicing fiber in the third quarter, this number will grow significantly. We expect to get caught up to our baseline projection in the 3rd quarter of 2012. | 0 | 3 | 0 | We do not have any signed agreements with wholesale or last mile providers yet. At the end of the quarter the UC2B Policy Committee had not yet approved the proposed wholesale layer two and layer three service rates. Those discussions have begun and should be finalized in the coming quarter. IRU and dark fiber lease pricing has been approved. | UC2B will offer 20-year dark fiber Indefeasible Rights of Use (IRU) contracts, as well as shorter-term dark fiber leases. Pricing for both are attached to this report. UC2B will also offer layer-two and layer-three wholesale services. The proposed pricing for those services is also attached to this report. | While we we may do so in the future, at this time we have not designated a third party to operate any of our network. | 0 | 0 | 0 | 4 | Our baseline projected 1 provider with new access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. We expect to be caught up with our baseline projection in this area by the end of the 3rd quarter of 2012. | Our baseline projected 4 providers with improved access. Because we have not connected any providers yet we are behind in this category. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We are therefore behind in starting construction by about two quarters. As explained elsewhere in this report, we now expect a total of 3 providers with improved access. We expect to have those providers signed by the end of the 3rd quarter of 2012. | The baseline did not include a projection for dark fiber customers. We are in active negotiations with one provider for dark fiber that should be concluded in the 3rd quarter. | While our suite of wholesale services is currently under review, the proposed wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planned levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. There used to be two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps CPE. Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to accomplish technically, while still providing Gigabit access to our local network resources. This will be finalized in the next quarter. | 0 | 0 | 0 | 11 | Our baseline was 143 total CAIs served. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We will serve our first Community Anchor Institutions in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was zero. | Our baseline was 143 CAIs receiving improved access. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We will serve our first Anchor Institutions in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | There are no active CAI customers at this time. Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. None of these tiers have any subscribers at this time. | 1757 | 0 | 0 | 0 | 11 | Our baseline was 4,640. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customer in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Baseline was 2,000. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow ring and fiber-to-the-curb fiber. We will finish hiring our contractor(s) for installing fiber from the curb into the buildings (FTTP) in the second quarter, but they will probably not begin making those installations until the last week of July. We are requiring our bidders on the FTTP RFP to demonstrate that they can accomplish the number of installations per week that we need to achieve in order to complete our project by 1/31/2013. We do not expect to catch up to our baseline numbers until the end of the 4th quarter of 2012. | Our baseline was 300. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customer in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 1,700. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first residential customers in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. None of these tiers have any subscribers at this time. | 75 | 0 | 0 | 0 | 11 | Our baseline was 200 businesses passed with fiber. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 57 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Our baseline was 9 businesses receiving new access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012 | Our baseline was 48 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We have now begun to blow fiber. We will serve our first business in the 3rd quarter of 2012. We will get back on our baseline plan in the 4th quarter of 2012. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. None of these tiers have any subscribers at this time. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. The community wireless plan we were considering is on hold for now. | FALSE | N/A | The next quarter will be our most rewarding to date, as we will connect the first customers and commence providing services. In order for that to happen, a lot of previously parallel activities will need to converge. The phase one contractors will finish installing and splicing the fiber cables necessary to turn up the first fiber service areas that we are now calling â€œfiberhoodsâ€ â€“ borrowing a phrase from Google. The upstream Internet connection will go live after all of the core network equipment is delivered, configured and brought on-line. The first of the 12 neighborhood cabinets will be powered up in early August, and by the end of that month, all 12 should be live. The phase two contractors will be completing fiber from the curb into homes, businesses and Anchor Institutions and installing the customer premise equipment. We have issued RFPs for call center support and for on-site customer support. Both of those will be awarded in the next quarter and those firms will begin servicing our customers. We will of course continue our outreach and canvassing efforts as we strive to reach our goal of 2,700 Fiber-to-the-Premise (FTTP) customers. We have a fair number of rental properties and Multiple Dwelling Units in our FTTP service areas, and we have just rolled out a plan to engage those landlords. Most of our subscriptions to date have come from owner-occupied dwellings. There are also two mobile home parks that we should be able to market to in the next quarter. Private easement issues have delayed that effort, but the easements are just about in place. In the next quarter we plan to complete conduit deployment of some 160 miles. In the next quarter we plan to complete fiber deployment of some 203 miles. Most of our fiber-to-the-premise fiber from the curbs to the buildings is direct buried and not in conduit, which is why our fiber mileage total will be greater than our conduit mileage total. This number is also greater than our baseline projection for total network miles, for we did not include the fiber drop cables in our baseline projection of network miles. By the end of the next quarter we plan to have 75 Community Anchor Institutions connected to UC2B fiber. Next quarter we will also finalize our layer-two and layer-three wholesale pricing plans and be in a position to sign up additional service providers. Three local firms continue to express interest in providing services over the UC2B fiber infrastructure. A fourth service provider we were talking to has elected to concentrate on its core service area for now and not expand to our community. By the end of the next quarter we plan to have one broadband/wholesaler/last mile provider agreement signed and two very close to being signed. We will also finalize our dark fiber IRU contract forms and get signatures and funds from those organizations seeking IRUs. That will be considered program income that will be used as part of our local match. Next quarter we will also examine our budget and our remaining funds and determine whether or not to request permission from NTIA to connect another 50+ Community Anchor Institutions (CAIs) that were inadvertently left off the CAI list that was submitted with our initial BTOP grant application. We included these sites on our route maps when we submitted our revised Environmental Assessment, which was approved, so if we have funding and permission, we should be good to go. That request would probably advance to NTIA in late August or early September. | University of Illinois | There have been some slight delays of the materials needed to construct fiber from the curb to the homes, businesses and Anchor Institutions. Those delays should be resolved early in the 3rd quarter. | We are not anticipating any challenges or issues in the next quarter.
NT10BIX5570044 | 2012 | Q3 | Q3 - 2012 | This past quarter saw a significant milestone for the Urbana-Champaign Big Broadband (UC2B) project. The first of our Community Anchor Institution (CAI) and Fiber-to-the-Premise (FTTP) customers were connected to the UC2B network via fiber and began receiving UC2B Internet services. In addition to the fiber construction, all of the work behind the scenes had to be completed in order for those first Internet customers' connections to work. That required the acquisition, installation and configuration of all the core network equipment, making the connections to our upstream Internet provider, as well as turning up support systems such as Domain Name Service (DNS), Dynamic Host Configuration Protocol (DHCP) and network monitoring. As of this report, almost all of the middle-mile fiber cables have been installed although some of them still need to be spliced. In the FTTP areas, almost all of the fiber-to-the-curb cables are in the ground, with some still needing to be spliced and tested. All twelve of the neighborhood equipment cabinets have equipment and power and are ready for fiber splicing, but we are rolling out FTTP installations in compact areas to make the most efficient use of our installers. We are one of a dozen charter communities nationwide for the US Ignite initiative, which will develop the next generation of applications that will leverage gigabit networks â€“ like UC2B. The University of Illinois' research community is engaged with the US Ignite effort, and we hope to be able to provide UC2B customers with access to applications developed through US Ignite from across the country. In late September, UC2B was honored by NATOA as their 2012 National Community Broadband Project of the Year. NATOA is a national trade association representing local government jurisdictions and consortiums, including elected and appointed officials and staff, who oversee communications policies and services in local governments throughout the country. Larry Strickling, Assistant Secretary of Commerce and Administrator of NTIA, was honored by NATOA in 2010 as the Broadband Hero of the Year, so UC2B is in good company as a NATOA honoree. We have attached some documentation and photos from US Ignite and NATOA to this report. | 149 | 0 | 9 | 0 | 149 | 0 | 0 | 1071 | Baseline projected 187.06 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We were therefore behind in starting construction by about two quarters. While this is not a metric that NTIA is tracking, we have installed 154 miles of new conduit through September. | N/A | This was not a milestone in the Baseline Plan, but we have some short segments of conduit and fiber that we have taken over from the cities and upgraded with larger fiber cables and additional manholes and splice cases.. | N/A | Baseline projected 187.06 miles. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We were therefore behind in starting construction by about two quarters. While this is not a metric that NTIA is tracking, we have installed 154 miles of new conduit through September. | N/A | N/A | The Baseline Plan projected 495 interconnection points. Our Baseline Plan only included the manholes on our main rings and the three nodes where we terminate fiber. There are hundreds of additional manholes and splice points in our Fiber-to-the-Premise areas, which are now included in this number. Our cotangent ring design allows providers to redundantly connect to our network core and provide services from any location where they can splice into our fiber. | 0 | 6 | 0 | There were no signed agreements with wholesale or last mile providers at the end of last quarter, but since then a service provider has signed two IRU agreements. While we have approved pricing for IRU's, short-term dark fiber leases, layer two and layer three transport services, we only have contract templates for IRU's. Our attorneys are working on the rest. Four additional service providers have expressed interest in dark fiber leases or IRUs and several may be interested in layer two or layer three transport. When contracts are ready to be signed in the next quarter, we will know more. | The UC2B Policy Committee has approved pricing and contract terms for 20-year dark fiber IRU's. The Policy Committee has also approved pricing for short-term dark fiber leases, layer two transport and layer three transport. Contract documents for those last three services are being prepared by our attorneys. The approved pricing plans for these wholesale services are attached. | The City of Champaign has been designated by the members of the UC2B Intergovernmental Consortium to be the lead agency for all of UC2B's operations. The City of Champaign is also an NTIA grant sub-recipient - managing the first phase of construction in the City of Champaign and the second phase of construction throughout the community. The City has named Teri Legner as acting Consortium Coordinator. She can be reached at Teri.Legner@ci.champaign.il.us, or by phone at (217) 403-8705. Her office is at 102 North Neil Street, Champaign, IL 61820. | 1 | 0 | 0 | 4 | Our baseline projected 1 provider with new access. UC2B itself is a new last-mile provider and it is now receiving middle-mile access for the first time. | Our baseline projected 4 providers with improved access, which to our thinking in 2009 included both dark fiber and transport services. There are 3 providers - Volo Broadband, Champaign Telephone and the Illinois Century Network (ICN) - that have expressed interest in using UC2B's lit layer two and layer three services to improve their access. Our attorneys are working on those contract templates, and our construction crews are finishing up the fiber that will make that improved access possible. All of that will come together in the 4th quarter. | The baseline did not include a specific projection for dark fiber customers. We have signed two separate IRU agreements with one provider - Big Broadband Services (BBS) - and four additional providers - Volo Broadband, Pavlov Media, Metro Communications and the Illinois Century Network (ICN) have expressed interest in dark fiber. Our Policy committees has voted to not sell any additional IRU's until February 1, 2013. Until then we will make dark fiber available via short-term lease. The pricing for those short-term leases has been established, but we do not yet have contract templates available, and the fiber has not been completed, tested and accepted yet. That will all happen in the next quarter. The pricing for short-term lease of dark fiber is attached. | Our wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planned levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. There used to be two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps CPE. Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to accomplish technically, while still providing Gigabit access to our local network resources. There are no current customers of these services. | 4 | 2 | 2 | 11 | Our baseline was 143 total CAIs served. Our detailed fiber engineering and our construction bidding have taken longer than we estimated in our baseline plan. We now have fiber at the curb of almost all of these locations and will build the fiber drop cables and install electronics in the 4th quarter. | Our baseline was zero, so this is an improvement from what we projected in 2010. | Our baseline was 143 CAIs receiving improved access. Our detailed fiber engineering and our construction took longer than we estimated in our baseline plan. Our Phase One contractors are currently focusing on getting the FTTP areas turned over the the Phase Two contractors, In the 4th quarter when that is done, they will turn their attention to connecting the Anchor Institutions. Most of the laterals are built to our Anchors, we just need the drop cables for the curb installed and spliced. | Two of the four connected Anchors are Unit 4 school buildings, that at this point are using the UC2B fiber to connect their facilities to each other. One of the schools is a new facility that just opened its doors this fall. The 3rd Anchor is a medical facility that is using dark UC2B fiber for improved access to its service provider. The 4th Anchor is a small African-American church that is in the heart of our FTTP service area that has never had a broadband connection before. The church is the only UC2B Last-Mile Anchor customer thus far, and they chose the 20 Mbps symmetrical Consumer service. Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. | 4604 | 19 | 6 | 13 | 11 | Our baseline was 4,640, which was based on the 2000 census, but in reality is a bit low in 2012. There are some 300 mobile homes that we have yet to pass, so our final number will be closer to 4,900 if we can get the easement from the owner of that mobile home park, 4,604 if we cannot. | Baseline was 2,500. Our detailed fiber engineering and our construction took longer than we estimated in our baseline plan. Our Phase Two contractors were just getting started at the end of the 3rd quarter. They are now connecting 8-10 residential customers a day and we hope that they will be able to greatly increase the average. We currently have just more than 1,100 residential contracts, so it is not likely that we will reach the goal of 2,500 installed residential customers by February 1st. We are striving to get those customers who have signed up for UC2B service installed by then. | Our baseline was 375. Our detailed fiber engineering and our construction took longer than we estimated in our baseline plan. That 375 represented 15% of our entire projected residential customer base. Based on their self reporting, of the households that have signed up for UC2B service, closer to 50% will be receiving new access. That is a positive development, but it has implications for our support systems and the need for training for 1st-time broadband users. We now have fiber in the right-of-way in front of almost all of hour homes in the FTTP service areas and more are connected every week. | Our baseline was 2,125. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in the right-of-way in front of almost all of hour homes in the FTTP service areas and more are connected every week. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. there are 18 subscribers to our 20 Mbps symmetrical service and one subscriber to our 30 Mbps symmetrical service. Across all of our ~1,200 subscribers, almost 25% have elected for a service that include more than 20 Mbps of bandwidth. | 211 | 0 | 0 | 0 | 11 | Our baseline was 200 businesses passed with fiber, which was based on the 2000 census data. There has been some growth since then that is reflected in this higher number. | Our baseline was 57 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in front of all of the businesses in our FTTP service areas. We will begin connecting businesses in the 4th quarter. | Our baseline was 9 businesses receiving new access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in front of all of the businesses in our FTTP service areas. We will begin connecting businesses in the 4th quarter. | Our baseline was 48 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in front of all of the businesses in our FTTP service areas. We will begin connecting businesses in the 4th quarter. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. No businesses are yet connected. | All of our customers will have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity will be sold in tiers of bandwidth, UC2B Intranet connectivity will be limited only by the port speed of the customer's Optical Network Terminal (ONT), which will be 1 Gbps. This is very similar to the service model deployed by Lafayette, Louisiana in their Fiber-to-the-Premise system. | FALSE | N/A | In the next quarter, all of our Phase One fiber construction should be complete, tested and accepted. That combined with the drop cables for the projected 600 installed Fiber-to-the-Premise (FTTP) customers will account for 196 total miles of new fiber. Our Phase One construction consisted of the seven backbone rings, the laterals to the Community Anchor Institutions (CAIs) and the fiber-to-the-curb in our 11 FTTP Census Block Groups that qualified as underserved. All of the Anchor Institutions on our original list that desire UC2B service will be connected to the fiber in the next quarter. Adding in some "additional" CAIs that were located in the FTTP areas but not on the original list of CAIs in our grant application, we project having a total of 182 CAI's connected by January 1st. We project that our Phase Two contractor will also complete 600 Fiber-to-the-Premise (FTTP) installations in the next quarter. Our customer support, billing and fiber maintenance systems will all go operational in the next quarter. In addition to providing wholesale service for UC2B's retail service offering, we expect to sign or be very close to signing four or five additional contracts with broadband wholesale/last mile providers. Those organizations are: Champaign Telephone Company, Volo Broadband, Pavlov Media, Metro Communications and the Illinois Century Network (ICN), which is another BTOP project. The ICN agreement may take longer, as it requires NTIA's approval on top of all the local lawyers for both sides. | University of Illinois | Our primary challenge has been ramping up the Phase-Two contractor that is building the fiber drop from the curbs to homes, businesses and Anchor Institutions. The prime contractor has engaged one sub-contractor to build the drops cables to the Anchor Institutions and a second sub-contractor to build the drop cables to the homes and businesses in the Fiber-to-the-Premise (FTTP)grant-funded areas. The sub-contractor building the fiber cable drops to the Anchor Institutions has made good progress and is well on its way to complete that construction in a timely manner. The sub-contractor that is building the fiber drop cables to the FTTP homes and businesses and installing the customer premise equipment has had a number of issues that have limited their progress. We have asked the prime contractor for an action plan that will result in getting the 1,000 homes and businesses that have already signed service contracts installed before February 1st, but there is not a high degree of confidence that they will be able to achieve that. | We believe that at the end of the 4th quarter that all of our middle-mile fiber will be installed and that all of the Anchor Institutions on our original list will be installed. However, as of the date of filing this report, we have roughly 1,000 primarily low-income households that have signed up for UC2B Internet service that have not been installed yet. UC2B fiber exists in the right-of-way in front of their homes, but the Phase Two contractor needs to extend the fiber into those homes and install the customer-premise electronics. If the Phase Two contractor is able to significantly increase the number of homes that are installed each day, and if the weather cooperates, there is a small chance that all of the households that have already subscribed to UC2B will be installed before February 1st. However, we are continuing to sign up customers, and there is no guarantee that we will have a mild, snow-less winter like we did last year. There is a real possibility that we will run out of time before all the households that have subscribed can be connected. There are a few businesses in the grant-funded service areas as well that are similarly affected. Following a UC2B Policy Committee meeting on November 14th, we plan to file an Award Action Request (AAR) with NTIA that will ask for more time to complete our project, add some Community Anchor Institutions and seek permission to provide UC2B service to the living units of the residents living in senior living centers that
NT10BIX5570044 | 2012 | Q4 | Q4 - 2012 | The 4th quarter of 2012 saw 790 additional UC2B fiber installations. At the end of the quarter, there were a total of 716 residential Fiber-to-the-Premise (FTTP) connections, 19 business FTTP connections and 78 Community Anchor Institutions connected to UC2B. UC2B began functioning as a service provider in the 4th quarter and also signed its first two Indefeasible Rights of Use (IRU) contracts. A third IRU contract is close to being signed as well. The fiber to the curb infrastructure in our 11 grant-eligible Census Block Groups was almost complete by the end of the quarter as were our seven middle-mile backbone rings for serving Community Anchor Institutions. While it was not a grant-funded activity, UC2B also issued a Request for Information (RFI) seeking private providers to expand the UC2B fiber network beyond the grant-funded areas. This RFI was done in conjunction with the Gig.U initiative and we had several interesting responses to the RFI that will be explored in February. We believe that private investment will allow our network to grow, connect additional residences and businesses and be more sustainable. As we reached the end of the quarter, it became apparent that we would not have enough time in the final month of our grant period to connect the remaining households and business that had signed up for UC2B service, but had not yet been installed. We applied to NTIA for a no-cost time extension, which was approved in late January. We now have through 9/30/13 to complete our project. | 179 | 0 | 9 | 0 | 179 | 0 | 0 | 1114 | Baseline projected 187.06 miles. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We were therefore behind in starting construction by about two quarters. Our baseline plan did not adequately take into account the route miles that would be added to our project by the drop cables from the curb into our FTTP sites, so our final number of network miles of fiber will exceed our baseline plan. | N/A | This was not a milestone in the Baseline Plan, but we do have 8.5 miles of conduit and fiber that we have taken over from the cities and upgraded with larger fiber cables and additional manholes and splice cases.. | N/A | Baseline projected 187.06 miles. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We were therefore behind in starting construction by about two quarters. Our baseline plan did not adequately take into account the route miles that would be added to our project by the drop cables from the curb into our FTTP sites, so our final number of network miles will exceed our baseline plan. | N/A | N/A | The Baseline Plan projected 495 interconnection points. Our Baseline Plan only included the manholes on our main rings and the three nodes where we terminate fiber. There are hundreds of additional manholes and splice points in our Fiber-to-the-Premise areas, which are now included in this number. Our cotangent ring design allows providers to redundantly connect to our network core and provide services from any location where they can splice into our fiber, so we have included these additional interconnection points. | 2 | 6 | 80 | We have signed two 20-year IRU agreements with one provider - Big Broadband Services, which is referred to in our application and due diligence documents as Champaign Telephone Company. It is the same principal owner, just a different legal entity. Six additional service providers have expressed interest in dark fiber leases or IRUs and several may be interested in layer two or layer three transport. When contracts are ready to be signed in Q1 of 2013, we will have a better feel for what these providers actually want to do. | The UC2B Policy Committee has approved pricing and contract terms for 20-year dark fiber IRU's. The Policy Committee has also approved pricing for short-term dark fiber leases, layer two transport and layer three transport. Contract documents for those last three services are being prepared by our attorneys. The approved pricing plans for these wholesale services are attached. | The City of Champaign has been designated by the members of the UC2B Intergovernmental Consortium to be the lead agency for all of UC2B's operations. The City of Champaign is also an NTIA grant sub-recipient - managing the first phase of construction in the City of Champaign and the second phase of construction throughout the community. The City has named Teri Legner as acting Consortium Coordinator. She can be reached at Teri.Legner@ci.champaign.il.us, or by phone at (217) 403-8705. Her office is at 102 North Neil Street, Champaign, IL 61820. | 1 | 1 | 1 | 4 | Our baseline projected 1 provider with new access. UC2B itself is a new last-mile provider and it is now receiving middle-mile access for the first time. | Our baseline projected 4 providers with improved access, which to our thinking in 2009 included both dark fiber and transport services. There are 3 providers - Volo Broadband, Champaign Telephone and the Illinois Century Network (ICN) - that have expressed interest in using UC2B's lit layer two and layer three services to improve their access. Our attorneys are working on those contract templates, and our construction crews are finishing up the fiber that will make that improved access possible. All of that will come together in the 1st quarter of 2013. Big Broadband Services (BBS) is the one provider with improved access. | The baseline did not include a specific projection for dark fiber customers. We have signed two separate IRU agreements with one provider - Big Broadband Services (BBS) - and six additional providers - Volo Broadband, Pavlov Media, Metro Communications, the Central Illinois Regional Broadband Network (CIRBN), PEG Bandwidth and the Illinois Century Network (ICN) have expressed interest in dark fiber. Our Policy Committees has voted to not sell any additional IRU's until February 1, 2013 - until then we will make dark fiber available via short-term lease. The pricing for those short-term leases has been established, but we do not yet have contract templates available, and the fiber has not been completed, tested and accepted yet. That will all happen in the 1st quarter of 2013. The pricing for short-term lease of dark fiber is attached with our other wholesale pricing. | Our wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planned levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. UC2B used to have two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps CPE. Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to accomplish technically while still providing Gigabit access to our local Intranet network resources. There are no current customers of these services. | 78 | 12 | 66 | 11 | Our baseline was 143 total CAIs served. Our detailed fiber engineering and our construction bidding took much longer than we estimated in our baseline plan. We now have fiber at the curb of many of these locations and will build the fiber drop cables and install electronics in the next quarter to those that are not yet connected. | Our baseline was zero, so this is an improvement from what we projected in 2010. These numbers are based on the CAI's self reporting of whether they are a new or upgrading broadband subscriber. | Our baseline was 143 CAIs receiving improved access. Our detailed fiber engineering and our construction took much longer than we estimated in our baseline plan. Our Phase One contractors have completed their work in the FTTP areas and are now concentrating on connecting Anchor Institutions. Most of the laterals are built to our Anchors, we just need the drop cables from the curb installed and spliced. | Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans (that allow for additional public IP addresses and greater bandwidth than in our Consumer plans.) The retail tiers are detailed on the attached Schedule of Retail Services. There are 34 CAI customers of our Consumer 20 Mbps symmetrical service, 3 CAI customers of our Consumer 30 Mbps symmetrical service, and 4 CAI customers of our Consumer 40 Mbps symmetrical service. Two CAIs are subscribed to the 20 Mbps Commercial Service and one is subscribed to the 100 Mbps Commercial service. A good number (35)of our Community Anchor Institutions are not getting their internet access from UC2B, but using UC2B fiber to connect to their provider. | 4620 | 716 | 340 | 376 | 11 | Our baseline was 4,640, which was based on the 2000 census, but in reality is a bit low in 2012. There are some 280 mobile homes that we have yet to pass, so our final number will be closer to 4,900 now that we have the easement from the owner of that mobile home park and additional time to pass those residences. | Baseline was 2,500. Our detailed fiber engineering and our construction took longer than we estimated in our baseline plan. Our Phase Two contractors were just getting started at the end of the 3rd quarter. They have now connected 716 residential customers, and will continue through January to connect more. As of this writing, the ground is frozen solid, so we will take a brief pause from construction, but will start up again when the weather makes it possible to continue. | Our baseline was 375. Our detailed fiber engineering and our construction took longer than we estimated in our baseline plan. That 375 represented 15% of our entire projected residential customer base. Based on their self reporting, of the households that have signed up for UC2B service, closer to 45% will be receiving new access. That is a positive development, but it has implications for our support systems and the need for training for first-time broadband users. We now have fiber in the right-of-way in front of almost all of our homes in the FTTP service areas and more are connected every week. | Our baseline was 2,125. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in the right-of-way in front of almost all of our homes in the FTTP service areas and more are connected every week. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. There are 596 residential customers of our Consumer 20 Mbps symmetrical service, 70 residential customers of our Consumer 30 Mbps symmetrical service, and 50 residential customers of our Consumer 40 Mbps symmetrical service. Across all of our subscribers, 17.5% have elected a service that include more than our minimum 20 Mbps of Internet bandwidth. | 211 | 19 | 11 | 8 | 11 | Our baseline was 200 businesses passed with fiber, which was based on the 2000 census data. There has been some growth since then that is reflected in this higher number. | Our baseline was 57 total businesses served. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in front of all of the businesses in our FTTP service areas. We will continue connecting businesses in 2013. | Our baseline was 9 businesses receiving new access, so we have exceeded that projection. | Our baseline was 48 businesses receiving improved access. Our detailed fiber engineering and our construction bidding took longer than we estimated in our baseline plan. We now have fiber in front of all of the businesses in our FTTP service areas. We will continue connecting businesses in 2013. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans )that allow for additional public IP addresses and greater bandwidth than in our Consumer plans.) The retail tiers are detailed on the attached Schedule of Retail Services. There are 8 business customers of our Consumer 20 Mbps symmetrical service, 6 business customers of our Consumer 30 Mbps symmetrical service, and 2 business customers of our Consumer 40 Mbps symmetrical service. As of 12/31/12 we had no commercial customers connected, but there are some that have signed up for that service and will be connected in the next quarter. | All of our customers have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity is sold in tiers of bandwidth, UC2B Intranet connectivity is limited only by the port speed of the customer's Optical Network Terminal (ONT), which is 1 Gbps. This is very similar to the service model deployed by the City of Lafayette, Louisiana in their Fiber-to-the-Premise system. | FALSE | N/A | The next quarter for UC2B represents the worst time of the year in Central Illinois for underground fiber-optic construction due to snow and frozen ground. As it appears that we will have a somewhat â€œnormalâ€ winter this year, we will pause most construction efforts in February and March, and ramp back up fiber construction in the 2nd quarter of 2013 when the weather is typically more cooperative. We will be in our extension period, and we have 61 newly approved by NTIA additional Community Anchor Institutions to design and install fiber into. In addition we also have several hundred "original" subscribers that were not installed before the ground froze in January. As we have had issues with some of our current contractors and sub-contractors, we intend to take advantage of what we have learned thus far and rebid the remaining construction with modified specifications during this down-time. The time needed for the rebidding process will prevent us from restarting construction immediately after the ground thaws, but we will still have plenty of time to complete the remaining work. There have been some installations completed in January, but the 1st quarter of 2013 will be more of a time to get caught up on construction documentation and plan for future construction than to build much fiber. In the coming quarter we plan to deploy an additional 2.3 miles of fiber (primarily in fiber drop cables.) In the coming quarter we plan to connect an additional 61 Community Anchor Institutions. Many of them had fiber in place at the beginning of the quarter and only needed to be spliced and have electronics installed. In the coming quarter we plan to sign 2 broadband wholesaler/last mile provider contracts. We expect Champaign Telephone Company to sign a layer three services agreement and we expect Metro Communications to sign a short term dark fiber lease. There is a time lag of several months between the time that work is completed in the field, and when the request for payment is processed by NTIA. This is explained by the process that a typical payment request must go through. The contractor submits a pay request to the project's engineering firm, which checks for Davis-Bacon compliance and conformity to the contract with UC2B, and then passes the request along to the appropriate the city sub-recipient. The city verifies that all is accurate in the pay request, pays it and submits it to the University for payment. The University verifies the accuracy of the request, pays the City and then requests payment from NTIA. Each of those steps can take upwards of 20-30 days. This planned pause in the construction process will allow our federal expenditures to more closely match the actual work completed in terms of percentage of completion in our reporting for the 1st quarter of 2013. | University of Illinois | Our main issue was the lack of time to complete our project, which NTIA responded to by approving the no-cost time extension. | None
NT10BIX5570044 | 2013 | Q1 | Q1 - 2013 | The first quarter of 2013 was a slow one for UC2B fiber construction due to frozen ground and unfavorable weather. However, we were able to complete some splicing and some electronics installations. By the end of the quarter, 1,001 customers had live UC2B fiber connections. That included 816 residential Fiber-to-the-Premise (FTTP) customers, 19 business FTTP customers and 166 Anchor Institutions. In January, NTIA approved 61 additional Community Anchor Institutions for BTOP grant-funded installations. Then later in that month NTIA granted our request for a no-cost time extension through September 30, 2013. The previous end of our grant period had been January 31st. In addition to the 61 additional Anchors, we have 434 fiber-to-the-Premise (FTTP) subscribers and 24 Anchor Institutions, who had signed up for UC2B service but were not yet connected when we shut down underground fiber FTTP construction in January for the winter. We will restart construction in the next quarter when the ground thaws and dries out and when the weather is more conducive for underground fiber construction. In the meanwhile we are doing the planning and preparatory work for the remaining FTTP sites and the 61 additional Community Anchor Institutions. The financial report for this quarter reflects a slightly reduced level of local match that NTIA approved in January as well. The local match and the project total were both reduced by $106,088. The overall project percentage of the local match was 23.32% prior to this change, which reduced it to 23.04%. The Federal amount remained unchanged. Finally we sought and received approval from NTIA via an Award Action Request in January to use grant funds to implement as many as three different Wi-Fi based initiatives in our service areas if funding is available. Those initiatives will be bid as alternates on our RFP for the 61 additional Anchor Institutions. Once we receive those bids, we will know how many (if any) of three Wi-Fi initiatives we can implement. The UC2B Policy Committee will make those decisions in June. | 185 | 0 | 9 | 0 | 194 | 0 | 0 | 1114 | This is actually 1 mile greater than our Extension projection of 184 for 3/31/13 new network miles deployed. For the length of the extension through 9/30/13, the total projection for the project is 216.3 miles of new fiber deployed. | N/A | This was not a milestone in the Baseline Plan, but we do have slightly more than 8.5 miles of conduit and fiber that we have taken over from the cities and upgraded with larger fiber cables and additional manholes and splice cases. | N/A | This is actually 1 mile greater than our Extension projection of 193 for 3/31/13 total network miles deployed. For the length of the extension through 9/30/13 the Extension projection is 124.8 miles of total fiber deployed or upgraded. | N/A | N/A | This metric was not included in the extension projections, but we are greatly over the 495 that were projected in our original project plan. In addition to our two main service nodes and 12 neighborhood FTTP distribution cabinets, there are hundreds of additional manholes and splice points on our main rings and in our Fiber-to-the-Premise areas, which are included in this larger number. Our cotangent ring design allows providers to redundantly connect to our network core and provide services from any location where they can splice into our fiber, so we have included these additional interconnection points. | 3 | 6 | 80 | We have signed two 20-year IRU agreements with one provider - Big Broadband Services, which is referred to in our application and due diligence documents as Champaign Telephone Company. It has the same principal owner, it is just a different legal entity. UC2B is also providing wholesale transport for its own last mile operations. There was no point in signing a contract with ourselves, but we have certainly agreed to provide our last-mile operations with bandwidth from our middle-mile facilities. Six additional service providers have expressed interest in dark fiber leases or IRUs and several may be interested in layer two or layer three transport. When contracts are ready to be signed in Q2 of 2013, we will have a better feel for what these providers actually want to do. | The UC2B Policy Committee has approved pricing and contract terms for 20-year dark fiber IRU's. The Policy Committee has also approved pricing for short-term dark fiber leases, layer two transport and layer three transport. Contract documents for those last three services are being prepared by our attorneys. The approved pricing plans for these wholesale services are attached. | The City of Champaign has been designated by the members of the UC2B Intergovernmental Consortium to be the lead agency for all of UC2B's operations. The City of Champaign is also an NTIA grant sub-recipient - managing the first phase of construction in the City of Champaign and the second and thirds phases of construction throughout the community. The City has named Teri Legner as acting Consortium Coordinator. She can be reached at Teri.Legner@ci.champaign.il.us, or by phone at (217) 403-8705. Her office is at 102 North Neil Street, Champaign, IL 61820. | 1 | 1 | 1 | 4 | Our baseline projected 1 provider with new access. UC2B itself is a new last-mile provider and it is now receiving middle-mile access for the first time. | Our baseline projected 4 providers with improved access, which to our thinking in 2009 included both dark fiber and transport services. There are 3 providers - Volo Broadband, Champaign Telephone and the Illinois Century Network (ICN) - that have expressed interest in using UC2B's lit layer two and layer three services to improve their access. Our attorneys are working on those contract templates, and our construction crews are finishing up the fiber that will make that improved access possible. All of that will come together in the 2nd quarter of 2013. Big Broadband Services (BBS) is the one provider with improved access. | The baseline did not include a specific projection for dark fiber customers. We have signed two separate IRU agreements with one provider - Big Broadband Services (BBS) - and six additional providers - Volo Broadband, Pavlov Media, Metro Communications, the Central Illinois Regional Broadband Network (CIRBN), PEG Bandwidth and the Illinois Century Network (ICN) have expressed interest in dark fiber. The pricing for those short-term leases has been established, but we do not yet have contract templates available, and the fiber has not been completed, tested and accepted yet. That will all happen in the 2nd quarter of 2013. The pricing for short-term lease of dark fiber is attached with our other wholesale pricing. | Our wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planned levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. UC2B used to have two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps CPE. Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to implement technically while still providing Gigabit access to our local Intranet network resources. Champaign Telephone has recently started testing layer two delivery at two sites. | 166 | 24 | 142 | 11 | Our Extension projection was 141. We were able to get more splicing and electronics installed in the first quarter than we had projected. The adverse weather shifted our efforts from construction to splicing and other non-weather affected activities. | Our Extension projection was 7. We were able to get more splicing and electronics installed in the first quarter than we had projected. The adverse weather shifted our efforts from construction to splicing and other non-weather affected activities. | Our Extension projection was 134. We were able to get more splicing and electronics installed in the first quarter than we had projected. The adverse weather shifted our efforts from construction to splicing and other non-weather affected activities. | Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans (that allow for additional public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans.) The retail tiers are detailed on the attached Schedule of Retail Services. The CAI customer breakout is: 46 are subscribed to our 20 Mbps symmetrical Consumer service 2 are subscribed to our 30 Mbps symmetrical Consumer service 9 are subscribed to our 40 Mbps symmetrical Consumer service 8 are subscribed to our 20 Mbps Commercial service 1 is subscribed to the 40 Mbps Commercial service 1 is subscribed to the 80 Mbps Commercial service, 1 is subscribed to the 100 Mbps Commercial service 2 are subscribed to the 200 Mbps Commercial service A good number - 96 (57.8%) - of our Community Anchor Institutions are not getting their internet access directly from UC2B. They are either using UC2B fiber to connect to a different service provider or they are purchasing UC2B bandwidth in a single main location and then using UC2B fiber to distribute it to their "satellite" locations. | 4620 | 816 | 393 | 423 | 11 | Our Extension projection was 4620. | Our Extension projection was 740. The weather held a little longer than we had anticipated. We had to close down underground fiber construction in mid January due to frozen ground and snow. | Our Extension projection was 370. The weather held a little longer than we had anticipated. We had to close down underground fiber construction in mid January due to frozen ground and snow. | Our Extension projection was 370. The weather held a little longer than we had anticipated. We had to close down underground fiber construction in mid January due to frozen ground and snow. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. The breakout of our residential customer subscriptions is: 676 subscribe to our Consumer 20 Mbps symmetrical service 84 subscribe to our Consumer 30 Mbps symmetrical service 56 subscribe to our Consumer 40 Mbps symmetrical service No residential customers have opted for our Commercial plans. Across all of our residential subscribers, 17.2% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | 211 | 19 | 8 | 11 | 11 | Our Extension projection was 211. | Our Extension projection was 70. The construction shutdown stranded a couple dozen business that had signed up, but were not connected before the ground froze. They will be connected once the weather becomes more consistently suitable for underground construction in the next quarter. This particular projection is probably a little on the high side to begin with. | Our Extension projection was 10.The construction shutdown stranded a couple dozen business that had signed up, but were not connected before the ground froze. They will be connected once the weather becomes more consistently suitable for underground construction in the next quarter. The numbers for business subscribers receiving new access and improved access were accidentally flip-flopped on the last quarter's PPR. These numbers are accurate. | Our Extension projection was 60.The construction shutdown stranded a couple dozen business that had signed up, but were not connected before the ground froze. They will be connected once the weather becomes more consistently suitable for underground construction in the next quarter. This particular projection is probably a little on the high side to begin with. The numbers for business subscribers receiving new access and improved access were accidentally flip-flopped on the last Quarter's PPR. These numbers are accurate. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. The breakout of our business customer subscriptions is: 12 subscribe to our Consumer 20 Mbps symmetrical service 1 subscribes to our Consumer 30 Mbps symmetrical service 3 subscribe to our Consumer 40 Mbps symmetrical service 2 subscribe to our Commercial 20 Mbps service 1 subscribes to our Commercial 40 Mbps service Across all of our business subscribers, 26.2% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | All of our customers have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity is sold in tiers of bandwidth, UC2B Intranet connectivity is limited only by the port speed of the customer's Optical Network Terminal (ONT), which is 1 Gbps. This is very similar to the service model deployed by the City of Lafayette, Louisiana in their Fiber-to-the-Premise system. | FALSE |  | In the second quarter of 2013, UC2B will resume construction to the 458 locations that have signed up for UC2B service, but that have not yet been connected. Of those 458 locations, 209 are single family residential, including 31 mobile homes. (Perhaps we should trademark "FTTT" â€“ Fiber-to-the-Trailer.) Construction will not resume until late in the quarter, and most of that work will be installing drop cables from the curbs to the buildings and installing electronics. We will install 4.6 additional route miles of fiber in those drop cables and will serve an additional 20 Anchor Institutions, 20 FTTP businesses and 100 FTTP residential subscribers. The bulk of the Anchors and FTTP subscribers we have remaining to install will be installed in the 3rd quarter. We are also on track to sign 2 or 3 wholesale service provider agreements in the next quarter. There are 198 units in Multiple Dwelling Unit buildings that are yet to be connected, as well as 14 single location businesses and 13 businesses in Multiple Tenant Unit (MTU) buildings. Finally, there are 24 remaining Community Anchor Institutions that have subscribed but are not yet connected. 6 of those 24 sites do not need construction, but instead need some combination of splicing and electronics configuration. We will continue to work on them regardless of whatever weather challenges we may have. 18 of those Anchor sites still require some underground fiber construction, which will resume as soon as the ground is consistently both warm and dry. All of this construction will be slightly delayed by the time it will take to administratively process a change order with one of our contractors to include this construction during the extension period. That should be complete by mid-May, which will allow that work to begin shortly thereafter in June if the weather cooperates. Thus far it has been a very wet spring. In May will also bid the construction for the additional 61 Anchor Institutions that were approved by NTIA in January. Conceivably that construction could start in late June, but more likely it will commence in early July. Behind the scenes, the as-built information from our three prime contractors is being aggregated into our GIS database, and that documentation work on the initial construction should be complete by the end of the coming quarter. As more fiber locations are built, we will continue to update the GIS database. We have several large pending contractor pay requests that will be processed in the coming quarter, so our percentage of completion from a financial perspective will increase significantly, even though most of that work has been completed for some time. There remains a significant time lag from when the fiber construction work is complete until when NTIA pays for it. That lag is created by the time it takes for the prime contractors to collect the required Davis-Bacon documentation as well as get lien wavers from their sub contractors. Then our sub-awardees have their approval processes to go through, and finally the University has its own internal approval processes. All of these processes are good to have, but they all take time. In this coming quarter our payment percentage should better reflect our actual completion percentage as the first phases of our project are closed out. | University of Illinois | The weather was sub-optimal for underground fiber construction for much of the past quarter, with both snow accumulations which made JULIE locates impossible, and frozen ground, which made some methods of burying fiber cable impossible to deploy as well. Accordingly, we did very little underground construction this past month, but concentrated on pulling fiber in existing conduit, splicing and network testing instead. | The weather could be a significant challenge in the coming quarter that could impact planned progress against the project milestones listed above. Underground fiber construction is easiest to do when the ground is reasonable dry. Thus far we have had a fairly wet spring, and if that continues into the summer it will affect progress. We also have a Request for Proposals (RFP) to issue for construction to the 61 additional Anchor Institutions that NTIA approved earlier this year. We then have to evaluate and award that contract in the next quarter. The City of Champaign will be issuing that RFP through its sub-award, and the procurement process used by UC2B must be approved by the City Council before the RFP is issued. Then the apparent winning vendor has to be approved by the City Council as well. There is always the possibility that those approval processes will take longer than we would like, as the swift approval by elected officials can never be guaranteed. There is also the possibility that we could have no bidders, or that we will have qualified bidders, but their bids could greatly exceed our proposed budget for that work. If faced with any of those scenarios, we will work closely with NTIA to find a solution.
NT10BIX5570044 | 2013 | Q2 | Q2 - 2013 | The second quarter of 2013, was a slow period for the UC2B project. While our fiber backbone construction was basically complete, there remained significant documentation and testing that was done in the second quarter. Some of that testing led to corrective work, which then had to be re-tested. We are on track for final acceptance of the backbone fiber rings in August. Our Fiber-to-the-Premise (FTTP) contractor under-performed in terms of the quality of the work, and did not complete all of the locations that had signed up for UC2B service before the ground froze in January. We then had snow on the ground, which interferes with underground utility locating. We elected to allow that contractorâ€™s contract expire at the end of January. We have since moved the remaining FTTP installations to a different existing UC2B fiber contractor, whose performance had been far better. That process was time consuming and involved prolonged negotiations on several fronts. However, our customers have been rewarded by our efforts, as the new FTTP contractor is doing a much better job and providing far better service to our customers. In early January, we received approval from NTIA to use some unspent funds to add an additional 61 Community Anchor Institutions to our project. Those locations are all outside of our Fiber-to-the-Premise (FTTP) service areas. These extra Anchor sites led to additional engineering and planning efforts, which culminated in a new fiber construction Request for Proposals that was issued in late May. That contract was awarded in June and the work began in early July. In late January, UC2B was granted a no-cost time extension by NTIA, so we extended the Fiber-to-the-Premise (FTTP) subscription period through mid-March for FTTP customers. Those new subscribers and the â€œleft-overâ€ customers that the original FTTP contractor did not complete were combined into one scope of work for the new FTTP contractor. The construction process for those roughly 400 total FTTP sites began in late June and is progressing well as of this writing. | 185 | 0 | 9 | 0 | 194 | 0 | 0 | 1114 | The Revised Project Plan projected 205.5 new network miles deployed by the end of this quarter. We did not add any network miles in the second quarter, due to winter weather and changing our FTTP fiber construction contractors. | N/A | This was not a milestone in the Baseline Plan, but we do have slightly more than 8.5 miles of conduit and fiber that we have taken over from the cities and upgraded with larger fiber cables and additional manholes and splice cases. | N/A | The Revised Project Plan projected 214 total miles of fiber deployed. We did not add any network miles in the second quarter, due to winter weather and changing fiber construction contractors. | N/A | N/A | This metric was not included in the extension projections, but we are greatly over the 495 that were projected in our original project plan. In addition to our two main service nodes and 12 neighborhood FTTP distribution cabinets, there are hundreds of additional manholes and splice points on our main rings and in our Fiber-to-the-Premise areas, which are included in this larger number. Our cotangent ring design allows providers to redundantly connect to our network core and provide services from any location where they can splice into our fiber, so we have included these additional interconnection points. | 3 | 6 | 80 | We have signed two 20-year IRU agreements with one provider - Big Broadband Services, which is referred to in our application and due diligence documents as Champaign Telephone Company. It has the same principal owner, it is just a different legal entity. UC2B is also providing wholesale transport for its own last mile operations. There was no point in signing a contract with ourselves, but we have certainly agreed to provide our last-mile operations with bandwidth from our middle-mile facilities. Six additional service providers have expressed interest in dark fiber leases or IRUs and several may be interested in layer two or layer three transport. When contracts are ready to be signed in Q3 of 2013, we will have a better feel for what these providers actually want to do. | The UC2B Policy Committee has approved pricing and contract terms for 20-year dark fiber IRU's. The Policy Committee has also approved pricing for short-term dark fiber leases, layer two transport and layer three transport. Contract documents for those last three services are being prepared by our attorneys. The approved pricing plans for these wholesale services are attached. | The City of Champaign has been designated by the members of the UC2B Intergovernmental Consortium to be the lead agency for all of UC2B's operations. The City of Champaign is also an NTIA grant sub-recipient - managing the first phase of construction in the City of Champaign and the second and thirds phases of construction throughout the community. The City has named Teri Legner as acting Consortium Coordinator. She can be reached at Teri.Legner@ci.champaign.il.us, or by phone at (217) 403-8705. Her office is at 102 North Neil Street, Champaign, IL 61820. | 1 | 1 | 1 | 4 | Our baseline projected 1 provider with new access. UC2B itself is a new last-mile provider and it is now receiving middle-mile access for the first time. | Our baseline projected 4 providers with improved access, which to our thinking in 2009 included both dark fiber and transport services. There are 3 providers - Volo Broadband, Champaign Telephone and the Illinois Century Network (ICN) - that have expressed interest in using UC2B's lit layer two and layer three services to improve their access. Our attorneys are working on those contract templates, and our construction crews are finishing up the fiber that will make that improved access possible. All of that will come together in the 3rd quarter of 2013. Big Broadband Services (BBS) is the one provider with improved access. | The baseline did not include a specific projection for dark fiber customers. We have signed two separate IRU agreements with one provider - Big Broadband Services (BBS) - and six additional providers - Volo Broadband, Pavlov Media, Metro Communications, the Central Illinois Regional Broadband Network (CIRBN), PEG Bandwidth and the Illinois Century Network (ICN) have expressed interest in dark fiber. The pricing for those short-term leases has been established, but we do not yet have contract templates available, and the fiber has not been accepted yet. That will all happen in the 3rd quarter of 2013. The pricing for IRU's and for short-term lease of dark fiber is attached with our other wholesale pricing. | Our wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planned levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. UC2B formerly had two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps Customer Premise Equipment (CPE). Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to implement technically while still providing Gigabit access to our local Intranet network resources. Champaign Telephone has deployed layer two services at a half-dozen sites as part of UC2B finalizing this service offering. | 177 | 27 | 150 | 11 | Our Extension projection was 204 CAI's connected at the end of this quarter. We were actually able to increase our total number of connected Community Anchor Institutions (CAI's) by 14 this quarter despite the slowdown of construction. Although this number is only 11 greater that the total in our last PPR it is because we accidentally double-counted three sites on our Q1 PPR, so the actual CAI total should have been 163. We have 19 of our original group of anchors currently in progress, and it looks like 54 of the 61 CAI's approved in January will end up getting connected, so our final total should exceed our 9/30/13 Extension projected total of 230 by about 20 CAI's. | Our Extension projection was 10 CAI's with new access. We have already exceeded our end-of-the-project Extension projection for the number of Community Anchor Institutions with new broadband connectivity. | Our Extension projection was 194. We actually have still have19 of our original Community Anchor Institutions in progress and will easily surpass our total number of CAIs with improved access by the end of the project. | Community Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans (that allow for additional public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans.) The retail tiers are detailed on the attached Schedule of Retail Services. The current CAI customer breakout is: 48 are subscribed to our 20 Mbps symmetrical Consumer service 3 are subscribed to our 30 Mbps symmetrical Consumer service 11 are subscribed to our 40 Mbps symmetrical Consumer service 9 are subscribed to our 20 Mbps Commercial service 1 is subscribed to the 40 Mbps Commercial service 1 is subscribed to the 80 Mbps Commercial service, 1 is subscribed to the 100 Mbps Commercial service 2 are subscribed to the 200 Mbps Commercial service A good number - 101 (57.1%) - of our Community Anchor Institutions are not getting their internet access directly from UC2B. They are either using UC2B fiber to connect to a different service provider or they are purchasing UC2B bandwidth at a single main location and then using UC2B fiber to distribute it to their "satellite" locations. | 4620 | 816 | 393 | 423 | 11 | Our Extension projection was 4620. | Our Extension projection was 1,200. Winter weather and replacing our FTTP contractor closed down FTTP construction for this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job in doing so. | Our Extension projection was 600. Winter weather and replacing our FTTP contractor closed down FTTP construction for this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job in doing so. | Our Extension projection was 600. Winter weather and replacing our FTTP contractor closed down FTTP construction for this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job in doing so. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. The breakout of our residential customer subscriptions is: 676 subscribe to our Consumer 20 Mbps symmetrical service 84 subscribe to our Consumer 30 Mbps symmetrical service 56 subscribe to our Consumer 40 Mbps symmetrical service No residential customers have opted for our Commercial plans. Across all of our residential subscribers, 17.2% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | 211 | 20 | 8 | 12 | 11 | Our Extension projection was 211. | Our Extension projection was 70. We connected a single business towards the end of June as construction started up again. Winter weather and replacing our FTTP contractor closed down FTTP construction for almost all of this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job in doing so. The remainder of our business subscribers will be connected in the third quarter. | Our Extension projection was 12. Winter weather and replacing our FTTP contractor closed down FTTP construction for this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job in doing so. The remainder of our business subscribers will be connected in the third quarter. | Our Extension projection was 60. Winter weather and replacing our FTTP contractor closed down FTTP construction for this quarter. Our new FTTP contractor is now actively connecting customers and doing a good job doing so. The remainder of our business subscribers will be connected in the third quarter. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. The breakout of our business customer subscriptions is: 13 subscribe to our Consumer 20 Mbps symmetrical service 1 subscribes to our Consumer 30 Mbps symmetrical service 3 subscribe to our Consumer 40 Mbps symmetrical service 2 subscribe to our Commercial 20 Mbps service 1 subscribes to our Commercial 40 Mbps service Across all of our business subscribers, 25.0% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | All of our customers have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity is sold in tiers of bandwidth, UC2B Intranet connectivity is limited only by the port speed of the customer's Optical Network Terminal (ONT), which is 1 Gbps. This is very similar to the service model deployed by the City of Lafayette, Louisiana in their Fiber-to-the-Premise system. This means that even our customers who subscribe to our least expensive Consumer service plan - $19.99 a month for a symmetric 20 Mbps Internet connection, still have access to local schools, local medical providers, local businesses, local government and to each other at far greater speeds - up to 1 Gbps. | FALSE |  | Next quarter will be extremely busy on several fronts. We will complete our grant-funded residential, business and Community Anchor Institution installations before October 1st. We will finalize agreements with several entities for dark fiber leases and IRUs. We will also sign several agreements for Layer Two and Layer Three wholesale services. In the next quarter we plan to connect a total of 73 additional Community Anchor Institutions, 30 additional FTTP businesses and 260 additional residential FTTP customers. We will install another 20 route miles of fiber in doing connecting these sites. The business and residential customer counts are down from our extension projections. We have seen a high turn-over rate in many of the residential rental units and the person who signed up for service last summer may no longer live there today. There have also been issues with some landlords granting UC2B permission to install infrastructure on their property that have cut into our numbers. It does not appear that there will be sufficient funds remaining to pursue any of the Wi-Fi initiatives that NTIA approved in January that were dependent on having available funds. Organizationally, UC2B the three-member Intergovernmental Consortium will evolve into UC2B, Inc. a non-profit corporation. We will seek NTIAâ€™s permission to transfer the assets of UC2B from the University of Illinois to UC2B Inc. through an Award Action Request. As the grant period winds down, we will resume our efforts to attract a private partner to extend fiber connectivity throughout our entire community, as UC2B fiber currently only passes 10% of our residences. In order for UC2B to be sustainable long-term, it must grow its FTTP service area. The potential partners who we have connected with through the Gig.U initiative may be able to help us do that. | University of Illinois | As was mentioned above, this past quarter we had challenges with our fiber construction contractors. The first challenge was making and following through on the decision to not renew the contract of one fiber construction contractor that was under-performing in two important areas - the quality of the work performed and completing the work within a given deadline. When we came to the conclusion that no amount of coaching or assistance would help this contractor to be successful, we ended the relationship. That was a politically sensitive thing to do and was not universally well received in our local community. We then had to find a way to get the work completed by our new extended deadline. Ultimately we decided to issue a change order to one of our other existing contractors, who had been doing better quality work. That turned out to be a good decision, as we have yet to have a complaint or a service failure at any of the sites they have installed. Both decisions took time to make and then get approved by the Champaign City Council. Champaign has a sub-award that covers this phase of construction, so all UC2B procurements related to that sub-award need to be approved by the Champaign City Council. So some of the quarter we found ourselves waiting for approvals to work their way through the appropriate processes, when we would have rather been building fiber. | There is a lot of work to complete in the short period of remaining time, and a limited number of people to do the work. This will result in many of us burning the candle at both ends for the remainder of the third quarter. Maintaining the health of our staff during this sprint to the finish line could be a challenge.
NT10BIX5570044 | 2013 | Q3 | Q3 - 2013 | September 30th marked the end of UC2Bâ€™s construction performance period. In the "middle-mile" component of our project, we completed 114.12 route miles of backbone and lateral fiber and connected 256 Community Anchor Institutions - 113 more Anchors than we projected in our grant application. UC2B was the only BTOP project that leveraged the language in the ARRA legislation to expand the definition of Community Anchor Institution to include organizations that serve â€œvulnerable populationsâ€. In addition to the standard categories of Community Anchor Institutions (CAIâ€™s): we have brought UC2B fiber connections to agencies that serve low-income families and the homeless; to agencies that serve battered women, their children and people with disabilities; to Head Start centers, a Boys and Girls club and a crisis nursery; and to multiple senior living facilities. In the "last-mile" component of our project we passed 4,838 locations with fiber-to-the-curb, and connected 1,058 residences and 75 businesses with Fiber-to-the-Premise (FTTP.) UC2B is the Internet provider for most of those sites, but four other ISPâ€™s also provide Internet connectivity over UC2Bâ€™s open access network. UC2B had originally projected that it would connect 2,557 residences and businesses. When the residential subscription rate ended up being below projections, we added 113 CAIâ€™s, which will greatly increase the impact of the UC2B project throughout the fabric of our entire community. There were 109.72 route miles of fiber built in the "last-mile" FTTP component of our project. In December, the members of the Urbana-Champaign Big Broadband Intergovernmental Consortium formed the UC2B-NFP not-for-profit corporation to administer the operations of the UC2B network. While there are no direct legal ties between the Consortium members and the new NFP, the Board members of the NFP are appointed by the Consortium members. UC2B has already impacted the local competitive Internet Service Provider landscape. Since the end of the third quarter, UC2B has negotiated IRU dark fiber agreements with two additional providers (ICN and PEG) and is in the final stages of executing short-term dark-fiber leases with two more providers (Volo and Metro.) Working with one of UC2Bâ€™s IRU holders, Champaign Unit 4 Schools is now saving $130,000 (post e-Rate) a year on their connectivity, and has increased their bandwidth from 100 Mbps to 1 Gbps between their facilities. Prior to the UC2B project, the City of Champaign had approved a long-term plan to connect all of its public safety, public works and other facilities together with fiber. The estimated cost of that project was greater than $4 million, and it was estimated to be a 5-7 year capital project. Champaignâ€™s dark-fiber IRU with UC2B has allowed the City to be totally connected in less than two years, and was done at 17% of the original projected cost. Champaign now has Gigabit and 10 Gigabit connections between its facilities, and its annual recurring cost for fiber maintenance is less than the leased T-1 lines that the fiber replaced. Its internal bandwidth between its buildings is now 600 times greater than before. Now that the City has fiber between its buildings, it has further saved money by consolidating backup and disaster recovery services. In February of 2014, the UC2B NFP Board of Directors entered into a contract with a private provider to build out the remaining 90% of our community with Fiber-to-the-Premise. Subject to NTIAâ€™s approval, this provider will leverage the existing UC2B fiber infrastructure and invest $50 million of its own money to build out our entire community with FTTP. By the end of 2016, we could be of the few communities in this country with universal coverage and open access for competing providers. | 215 | 0 | 9 | 0 | 224 | 0 | 0 | 1120 | This is slightly less than the 216.3 miles projected in our extension request, but still significantly greater than our original project plan of 187.1. Due to issues with landlords that we were not able to resolve within our grant period, we ended up serving fewer MDU residents than we projected. That reduction accounts for the variance. | N/A | This was not a milestone in the Baseline Plan, but we do have slightly more than 8.5 miles of conduit and fiber that we have taken over from the cities and upgraded with larger fiber cables and additional manholes and splice cases. | N/A | Extension projection was 224.8, so this is slightly less than that projection. Due to issues with landlords that we were not able to resolve within our grant period, we ended up serving fewer MDU residents than we projected. That reduction accounts for the variance. | N/A | N/A | We now have the early drafts of our as-built files, and we ended up with a net increase of 6 more fiber network splice points that we had originally planned for, so this is a very slight increase. | 3 | 4 | 80 | UC2B has two executed IRU agreements with Big Broadband Services (CTC-BBS), which is referred to in our grant application as Champaign Telephone Company (CTC.) We also now have an executed IRU with the CIRBN BTOP project that allows CIRBN to connect to a secondary CMS/ICN node in our service area. UC2B is also providing wholesale transport for its own last mile operations. Four additional service providers have expressed interest in dark fiber leases or IRU's and several of them may be interested in layer two transport. There are two IRU's and one short-term fiber lease that are in the final stages of being negotiated. | The UC2B Policy Committee has approved pricing and contract terms for 20-year dark fiber IRU's, for short-term dark fiber leases, for layer two transport and for layer three transport. Contract templates exist for IRU's and short-term dark fiber leases. We have not yet developed contract templates for layer two and layer three transport services. The approved pricing plans for these wholesale services are attached. | The City of Champaign has been designated by the members of the UC2B Intergovernmental Consortium to be the lead agency for all of UC2B's operations. The City of Champaign is also an NTIA grant sub-recipient - managing the first phase of construction in the City of Champaign and the second and third phases of construction throughout the community. The City has named Teri Legner as acting Consortium Coordinator. She can be reached at Teri.Legner@ci.champaign.il.us, or by phone at (217) 403-8705. Her office is at 102 North Neil Street, Champaign, IL 61820. After the close of the 3rd quarter, but before this writing, UC2B's operations were transferred to the new Urbana-Champaign Big Broadband not-for-profit corporation, which had it's first Board of Directors meeting on October 29, 2013. Its offices are at 713 Edgebrook Drive, Champaign, IL 61820. The NFP's Operations Manager is Sabrina Gosnell. She may be reached at (217) 239-6683 or by e-mail at sabrina@uc2b.net. | 0 | 0 | 3 | 4 | Our baseline plan projected 1 provider with new access. In 2010 in setting our baseline, we believed that this category included Wholesalers or Last Mile Providers that were leasing UC2B's dark fiber. We have since learned that dark fiber customers are not to be included in this category. | Our baseline plan projected 4 providers with improved access, which to our thinking in 2010 included both dark fiber leases and layer-two transport services. There were 2 providers - Champaign Telephone (CTC-BBS) and the Illinois Century Network (ICN) - that were testing using UC2B's lit layer-two services to improve their customers' access at the end of the quarter, but no layer-two transport contracts had been signed yet. | Our baseline plan did not include a specific projection for dark fiber customers. We have signed two separate IRU agreements with one provider - Big Broadband Services (BBS), and one with the Central Illinois Regional Broadband Network (CIRBN.) This is confusing because there are thee signed fiber access agreements but one provider signed two of them. To make the numbers on this report internally consistent and match the number of contracts shown in section 5A above, this is shown as 3 providers. Four providers - Volo Broadband, Metro Communications, PEG Bandwidth and the Illinois Century Network (ICN) have expressed interest in dark fiber IRU's or short-term leases and are negotiating contracts. Our fiber rings have been accepted from the contractors and we now have contract templates for short-term leases as well as for IRU's. At the end of the 3rd Quarter, ICN and Metro Communications were already using UC2B dark fiber in advance of the finalization of their contract paperwork, while PEG Bandwidth and Volo Broadband were working towards signed agreements. At one time, Pavlov Media had expressed interest in UC2B dark fiber, but now appears to be on a course to build their own fiber infrastructure. Pavlov specializes in providing Internet access to Multiple Dwelling Units's for college students, and the UC2B fiber build did not intensely cover the areas in our community where most of those student MDU's are located. Those areas did not qualify for our FTTP build. The pricing for IRU's and for the short-term lease of dark fiber is attached with our other wholesale pricing. | UC2B's wholesale services are provided on the attachment titled UC2B Wholesale Services. There are four planed levels of Wholesale and Last Mile Provider connectivity. Three of those are core connection options and there is a single customer connection option. UC2B formerly had two customer connection options, but that was an artifact of our our previous plan to use both 100 Mbps and 1 Gbps Customer Premise Equipment (CPE). Now that we are only using 1 Gbps CPE, we opted to drop the 100 Mbps offering, as it would be hard to implement technically while still providing Gigabit access to our local Intranet network resources. There were 2 providers - Champaign Telephone (CTC/BBS )and the Illinois Century Network (ICN) - that were testing using UC2B's lit layer-two services to improve their customers' access at the end of the quarter, but no layer-two transport contracts had been signed yet. Champaign Telephone (CTC) had six layer-two sites operational, while Illinois Century Network (ICN) had two. | 256 | 31 | 225 | 11 | Our Extension projection was 230 CAI's connected at the end of this quarter. We exceeded this projection. | Our Extension projection was 12 CAI's with new access. We exceeded this projection. | Our Extension projection was 218. We exceeded this projection. | Community Anchor Institutions can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, static IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. IRU holders serve roughly one third (89) of all of our CAI sites. Another 31 sites get their Internet indirectly from UC2B as a satellite of another location. The retail tiers are detailed on the attached Schedule of Retail Services. The current CAI customer breakout is: 94 are subscribed to our 20 Mbps symmetrical Consumer service 3 are subscribed to our 30 Mbps symmetrical Consumer service 15 are subscribed to our 40 Mbps symmetrical Consumer service 13 are subscribed to our 20 Mbps Commercial service 3 are subscribed to the 40 Mbps Commercial service 1 is subscribed to the 80 Mbps Commercial service, 3 is subscribed to the 100 Mbps Commercial service 2 are subscribed to the 200 Mbps Commercial service 89 CAI's are being served by IRU holders 31 CAI's are satellites of a main UC2B connection at another CAI 2 CAI's cancelled service after it had been installed. A good number - 120 (47.2%) - of our Community Anchor Institutions are not getting their Internet access directly from UC2B. They are either using UC2B fiber to connect to a different service provider or they are purchasing UC2B bandwidth at a single main location and then using UC2B fiber to distribute that UC2B bandwidth internally to their "satellite" locations. | 4620 | 1058 | 531 | 527 | 11 | Our Extension projection was 4620. | The Extension projection was 1,420. That was later reduced to 1,150. Due to issues with landlords that we were not able to resolve within our grant period, we ended up serving fewer MDU residents than we projected. That reduction accounts for the variance. | The Extension projection was 710, That was later reduced to 575. Due to issues with landlords that we were not able to resolve within our grant period, we ended up serving fewer MDU residents than we projected. That reduction accounts for the variance. | The Extension projection was 710, That was later reduced to 575. Due to issues with landlords that we were not able to resolve within our grant period, we ended up serving fewer MDU residents than we projected. That reduction accounts for the variance. | Households can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, static IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. The retail tiers are detailed on the attached Schedule of Retail Services. The breakout of our residential customer subscriptions is: 821 subscribe to our Consumer 20 Mbps symmetrical service 99 subscribe to our Consumer 30 Mbps symmetrical service 72 subscribe to our Consumer 40 Mbps symmetrical service 1 Subscribes to the Commercial 100 Mbps symmetrical service There are an additional 65 residential locations that were connected with fiber, but then the subscriber cancelled service. In some cases the customer moved. In others there were issues with the UC2B service or the equipment. Yet in others, the customer may have had financial issues or repeated problems with copyright infringement complaints. Only one residential customers has opted for one of our Commercial plans. Across all of our residential subscribers, 17.3% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | 218 | 75 | 30 | 45 | 11 | Our Extension projection was 211. We exceeded this projection. | Our Extension projection was 87. While we missed our Extension projection, we exceeded our application baseline of 57. | Our Extension projection was 14. We exceeded this projection. | Our Extension projection was 73. We did not end up with as many layer two sites as we had expected. One of our providers cut back on the number of sites they said they would serve. | Businesses can self select to subscribe to either our Consumer or Commercial service plans. There are three Consumer plans and eight Commercial plans that allow for additional IPv4 public IP addresses, static IPv4 public IP addresses, reverse DNS and greater bandwidth than in our Consumer plans. Some businesses are served by other providers via layer two services and some are served by dark fiber IRU holders. The UC2B retail speed tiers are detailed on the attached Schedule of Retail Services. We do not track the speed tiers that are provided by other providers via layer two or IRU's. The breakout of our business customer subscriptions is: 33 subscribe to our Consumer 20 Mbps symmetrical service 2 subscribe to our Consumer 30 Mbps symmetrical service 3 subscribe to our Consumer 40 Mbps symmetrical service 2 subscribe to our Commercial 20 Mbps service 1 subscribes to our Commercial 40 Mbps service 24 are served by providers with IRU's for UC2B fiber 10 are served by providers via layer two service Across all of our business subscribers with UC2B Internet, 19.5% have elected a service that provides more than our minimum 20 Mbps of Internet bandwidth. | All of our customers have 1 Gbps symmetric Intranet connectivity to each other, and to all local Community Anchor Institutions. While Internet connectivity is sold in tiers of bandwidth, UC2B Intranet connectivity is limited only by the port speed of the customer's Optical Network Terminal (ONT), which is 1 Gbps. This is very similar to the service model deployed by the City of Lafayette, Louisiana in their Fiber-to-the-Premise system. This means that even our customers who subscribe to our least expensive Consumer service plan - $19.99 a month for a symmetric 20 Mbps Internet connection - still have access to local schools, local medical providers, local businesses, local government and to each other at far greater speeds - up to 1 Gbps. | FALSE | N/A | The next quarter will be devoted to completing project closeout paperwork. | University of Illinois | The construction budget overrun was dealt with by a loan from the University to the UC2B Not-for-Profit Corporation to be paid back over a 10-year period starting in 2017. | We ended up with an extra $59 of local matching funds due to interest paid by the State of Illinois on a delayed grant payment. That $59 was applied to the project.
NT10BIX5570045 | 2010 | Q3 | Q3 - 2010 | Environmental Assessment (EA) consultant, Bonestroo, produced an EA report to identify any NEPA, NHPA and Endangered Species Act compliance issues as well as perform required section 106 and section 7 consultations with the State of WI Historical Society and US Fish and Wildlife Service. During the period, we continued to make substantial progress on network design. We participated on conference calls and performed information gathering to complete a draft EA in collaboration with our consultant for NTIA comment. UW participated in NTIA financial, reporting and environmental assessment calls/webinars. Additionally, UW has begun development of a website (http://www.mufn.org) and other communication media to convey information to stakeholders, participants and vendors. UW expects to launch the MUFN website in Q4-2010. UW completed development of a fiber construction bid, executed a request for bid process and awarded the construction bid to Intercon Construction, Inc. | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 4 | N/A | We were unable to complete a fiber agreement to lease 11 miles of fiber in 2Q2010 and 3Q2010; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement to be executed in 4Q2010 | N/A | N/A | N/A | N/A | N/A | Didn't add 2 points of interconnect (POI) as expected as 11mi fiber lease agreement did not get executed in 3Q2010 | 1 | 2 | 5 | Xiocom d/b/a Mad City Broadband | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Xiocom d/b/a Mad City Broadband will operate the network together. UW and the City are formalizing and finalizing the relationships now as a contractor and the City is finalizing its relationship with Xiocom as a subcontractor. | 0 | 0 | 1 | 0 | N/A | N/A | N/A | N/A - dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A as our project involves dark fiber where users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | TRUE | N/A | UW submitted a 2nd draft MUFN Environmental Assessment (EA) and anticipate a FONSI in 4Q2010. We completed the fiber construction bid that will include construction permitting, material acquisition and placement and post-installation (as-built) documentation activities. Upon receipt of the FONSI, we expect to begin construction on East Washington Ave and Mineral Point Road service areas. Finally, we expect to have our website http://www.mufn.org in operation by the beginning of 4Q2010. | University of Wisconsin System | FONSI delayed due to significant delays at the WI Historical Society (SHPO). SHPO took 90 days to finalize our section 106 consultation due to backlog of stimulus grant projects rather than an estimated 45 days. Could use expedient review if not FONSI determination of our submitted EA documentation by NTIA if at all possible in order to complete some construction activities before WI winter sets in. | Winter construction in WI is difficult and expensive. UW is concerned we will receive FONSI too late to undertake construction in calendar year 2010; delaying us until ~4/15/2011.
NT10BIX5570045 | 2010 | Q4 | Q4 - 2010 | During Q42010, UW-Madison submitted the Environmental Assessment report to identify any NEPA, NHPA and Endangered Species Act compliance issues as well as perform required section 106 and section 7 consultations with the State of WI Historical Society and US Fish and Wildlife Service. UW-Madison received the Finding of No Significant Impact (FONSI) from NTIA effective December 23, 2010. We also participated in recurring reporting conference calls with our program officer and designees and participated in NTIA webinars. UW also placed into production the www.mufn.org website and plan to involve other communication media to convey information to stakeholders, participants, and vendors. | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 4 | N/A | We were unable to complete a fiber agreement to lease 11 miles of fiber in 2Q2010, 3Q2010, and 4Q2010; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement to be executed in 2Q2011. The FONSI was approved on December 23, 2010. FONSI required for new fiber installation activities. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. The FONSI was approved on December 23, 2010. FONSI required for new fiber installation activities. | N/A | N/A | N/A | Didn't add 2 points of interconnect (POI) as expected as 11mi fiber lease agreement did not get executed in 4Q2010 | 1 | 2 | 5 | Xiocom d/b/a Mad City Broadband. | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Xiocom d/b/a Mad City Broadband will operate the network together. UW and the City are formalizing and finalizing the relationships now as a contractor and the City is finalizing its relationship with Xiocom as a subcontractor. | 0 | 0 | 1 | 0 | N/A | N/A | N/A | N/A - dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | The FONSI was approved on December 23, 2010. FONSI required for installation/network connectivity of Community Anchor Institutions (CAIs) | N/A | N/A | N/A as our project involves dark fiber where users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | N/A | University of Wisconsin System | FONSI approved on December 23, 2010. As such, we were unable to begin any construction activities for the 2010 winter season. | Winter construction in WI is difficult and expensive. With the receipt of the FONSI on 12/23/10, UW will undertake construction in ~4/15/2011.
NT10BIX5570045 | 2011 | Q1 | Q1 - 2011 | During the first quarter of 2011, UW requested contact information from the MUFN stakeholders that included primary and secondary contact information for building administrative personnel, technical personnel, on-site access phone numbers, and support hours. Upon receipt of the contact information, UW began scheduling building site surveys for Phase 1 (3 of 6 service areas) building locations, approximately two building surveys per day. Phase 1 locations include backbone and laterals for E. Washington and S. Park St. laterals. Phase 1 site surveys are expected to continue into the second quarter of 2011. In addition, the request for quote construction bid for Phase 2 (service areas 4 and 5) has been released and responses are currently being evaluated with an expectation to award by April 1, 2011. Additionally, construction materials have been ordered and received with InterCon, our construction company for Phase 1 sites, housing the construction materials. InterCon has also initiated the process to obtain permits for Phase 1 construction sites and will work with UW to prioritize installations. UW created a file-share web directory to receive Davis-Bacon payroll accounting reports from InterCon and to share other pertinent project information with InterCon and UW internal purchasing and accounting teams. On March 29, 2011, UW participated in a pre-construction meeting with InterCon, City of Madison Traffic Engineering, and City of Madison Engineering to discuss the areas of c | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 4 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. 20.15 miles will be done in 4Q2011. | We were unable to complete a fiber agreement to lease 11 miles of fiber in 2Q2010, 3Q2010, and 4Q2010; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement to be executed in 2Q2011. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. In addition we have not completed the UW Hospital and Clinics agreement due to UWHC attorney delays. | N/A | N/A | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. 20.15 miles will be done in 4Q2011. We were unable to complete a fiber agreement to lease 11 miles of fiber in 2Q2010, 3Q2010, and 4Q2010; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement to be executed in 2Q2011. 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/ central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. In addition we have not completed the UW Hospital and Clinics agreement due to UWHC attorney delays. Didn't add 2 points of interconnect (POI) as expected as 11mi fiber lease agreement did not get executed in 1Q2011. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011s for any variance from the baseline plan or any other relevant information) FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. 20.15 miles will be done in 4Q2011. We were unable to complete a fiber agreement to lease 11 miles of fiber in 2Q2010, 3Q2010, and 4Q2010; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement to be executed in 2Q2011. 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/ central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. In addition we have not completed the UW Hospital and Clinics agreement due to UWHC attorney delays. Didn't add 2 points of interconnect (POI) as expected as 11mi fiber lease agreement did not get executed in 1Q2011. FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | 1 | 2 | 5 | Citywide d/b/a Mad City Broadband. | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf)3 | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City are formalizing and finalizing the relationships now as a contractor and the City is finalizing its relationship with Citywide as a subcontractor. | 0 | 0 | 1 | 0 | On target with the baseline projections | On target with the baseline projections | On target with the baseline projections | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | N/A as our project involves dark fiber where users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Phase 1 site surveys will be completed. The construction contract for Phase 2 was awarded in Q22011 and Phase 1 construction will begin soon. Phase 2 site surveys will be completed by the end of June 2011. Phase 1 & 2 permits will be pulled. InterCon will order materials for Phase 2 during this quarter. | University of Wisconsin System | There have been challenges scheduling meetings with the City of Madison Traffic Engineering team. Permit office adjusted their application of administrative rules causing a two-week delay. Further challenges include finalizing the sub-award agreement causing delayed booking of the match and the challenges related to coordinating with road construction schedules. Delayed receipt of FONSI has stretched our internal network engineering resources resulting in delays in site preparation at one location. While we did not include network design in our proposal for CAI stakeholders, we are finding we must assist CAIs in developing their new network designs. This has resulted in delays in equipment procurement for an existing fiber ring which we believe will be deployed in 4Q2011. | Fiber shipment delays of 10-12 weeks for delivery due to the earthquake and tsunami in Japan. As a result, foreign-made fiber manufacturer supply chains have been injured and orders to American manufacturers have increased substantially. MUFN may use materials from Phase 1 in Phase 2 in order to compensate for delays.
NT10BIX5570045 | 2011 | Q2 | Q2 - 2011 | During the second quarter of 2011, Phase 1 site surveys have been completed and construction activities for Phase 1 began effective April 4, 2011. The construction bid for Phase 2 was awarded to InterCon, our current construction vendor. Phase 2 site surveys were completed by end of the second quarter. Phase 2 permits have been submitted for approval. While our construction contractor, InterCon, has received all materials including fiber for Phase 1 and received all materials except the fiber for Phase 2, expected target fiber shipment date is now August 2011 for Phase 2 per a different fiber company, CommScope. Our original fiber vendor, Corning, alerted us that due to the overwhelming demand of fiber requests stemming from the tsunami event in Japan earlier this year, earliest estimates of fiber shipment is now December 2011 which is unacceptable for the MUFN project. We are also conducting network planning design meetings with MUFN stakeholders as it was determined that many needed additional assistance with the design of their respective locations. We completed negotiations of a sub-recipient agreement with the City of Madison to codify the Cityâ€™s relationship and rights with UW. | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 4 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. 20.15 miles will be done in 4Q2011 which tracks with our baseline as of 4Q2010. | We were unable to complete a fiber agreement to lease 11 miles of fiber; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. In addition we have not completed the UW Hospital and Clinics agreement due to UWHC attorney delays. 20.15 miles will be done in 4Q2011. | N/A | N/A | Road construction projects we did not anticipate caused delays from our baseline plan. At the end of 4Q2011, we expect to be at our baseline (75) which was our 3Q2011 baseline projection. At the end of 4Q2012, we expect to meet our baseline projection of 104. | 1 | 4 | 20 | Citywide d/b/a Mad City Broadband. | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City are formalizing and finalizing the relationships now as a contractor and the City is finalizing its relationship with Citywide as a subcontractor. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Todd Anderson 608-237-6152; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 1 | 0 | On target with the baseline projections | On target with the baseline projections | In negotiations with several groups though a second agreement hasn't been reached yet as our baseline predicted. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 0 | 0 | 0 | 0 | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | FONSI timing and weather delayed start of MUFN Phase 1 until April 2011. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Phase 1 construction will be completed. Phase 2 permits will be approved and construction will commence upon the arrival of fiber. | University of Wisconsin System | We have experienced ROW issues/delays with the City of Middleton. Proofing of in-kind match conduit has resulted in additional unanticipated work to clear mud. | Fiber shipment delays of 10-12 weeks for delivery due to the earthquake and tsunami in Japan. As a result, foreign-made fiber manufacturer supply chains have been injured and orders to American manufacturers have increased substantially. MUFN may use materials from Phase 1 in Phase 2 in order to compensate for delays. Obtaining right-of-way and excavation permits from the city of Middleton and Shorewood is proving to be challenging.
NT10BIX5570045 | 2011 | Q3 | Q3 - 2011 | In East Washington Ave. service area, directional boring and conduit placement is complete to 21 of 24 locations (1 to be finished Fall 2012 due to road construction), fiber pulled to 19 of 24 locations and 9 of 24 locations have splicing and completed service. In the S. Park St service area, directional boring and conduit placement is complete to 12 of 13 locations while fiber is pulled to 3 of 13 locations. In the Mineral Point Rd service area phase 1, all directional boring, conduit placement and fiber pulling is complete. MUFN Phase 2 (Mineral Point Rd, University Ave, and Northport Dr service areas), all but 5 permits have been obtained. Directional boring and conduit placement is complete to one phase 2 location in the Mineral Point service area. All network planning meetings with consortium community anchor institutions are completed. Additionally, a consulting firm UW hired to value our in-kind contribution completed its work and UW will claim it's entire in-kind contribution match in this quarter. | 9 | 0 | 0 | 20 | 9 | 0 | 0 | 13 | We are behind our baseline 26 miles due to delays with the EA. At the end of 4Q2011, we will be at 2Q2011. MUFN will not fully catch our 4Q2011 baseline until 4Q2012 due to weather issues (starting Monona Dr service area construction 4/15/2012). | We were unable to complete a fiber agreement to lease 11 miles of fiber; we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. The UW Hospital & Clinics written agreement has not been finalized yet. We anticipate having this completed in 2Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path (black fiber path on the Northeast/central side of Madison on the map) leased at the beginning of the project. The UW Hospital & Clinics written agreement has not been finalized yet. We anticipate having this completed in 2Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | We are behind our baseline 57 miles due to delays with the EA. At the end of 4Q2011, we will be at 2Q2011. MUFN will not catch up to our 4Q2011 baseline until 4Q2012 due to weather issues (starting Monona Dr service area construction 4/15/2012). | N/A | N/A | At the end of 4Q2011, we expect to have 65 points which is past our 2Q2011 baseline (50) but shy of our 3Q2011 baseline projection. We are short due to unanticipated road construction and some CAI cancellations of service (5). We will near our 100% completion baseline at the end of 4Q2012. | 1 | 8 | 20 | Citywide d/b/a Mad City Broadband. | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City have formalized and finalized the relationships. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Todd Anderson 608-237-6152; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 1 | 0 | On target with the baseline projections | On target with the baseline projections | In negotiations with several groups though a second agreement hasn't been reached yet as our baseline predicted. There is a negotiation near completion with the WI Independent Network (aka WINs) that is likely to be finished up in 4Q2011 which should catch us up with our baseline. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 9 | 4 | 5 | 0 | Expect to reach our 2Q2011 baseline in 4Q2011 and near (65) our 3Q2011 baseline in 1Q2012. Will not reach 4Q2011 baseline until near end of project and assuming additional locations are approved to make up for the 5 dropped locations by CAI decision. | Expect to reach our 2Q2011 baseline in 4Q2011 and near (65) our 3Q2011 baseline in 1Q2012. Will not reach 4Q2011 baseline until near end of project and assuming additional locations are approved to make up for the 5 dropped locations by CAI decision. | Expect to reach our 2Q2011 baseline in 4Q2011 and near (65) our 3Q2011 baseline in 1Q2012. Will not reach 4Q2011 baseline until near end of project and assuming additional locations are approved to make up for the 5 dropped locations by CAI decision. | MUFN is a dark fiber project - most groups lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Expect (phase 1) East Washington Ave, S. Park St backbone and laterals to be completed (w/ 1 CAI exception (delay for road construction until 4Q2012). Anticipate MUFN Phase 2 (Mineral Point Rd, University Ave, Northport Dr service areas) to have substantial completion. Mineral Point Rd backbone will be complete (except route change at Junction Rd between Watts and Valley View Rd) along with all Mineral Point laterals (excluding 2 cancelled by UW-Medical Foundation due to clinic consolidations announced in July 2012). University Ave laterals will be completed (except 2 due to 2012 road construction), all laterals and backbone in Northport Dr service area will be completed. We expect to have 65 CAI locations (67%) completed at the end of 4Q2011 . We also anticipate having a 2nd signed agreement in place for commercial use of the infrastructure. Our expenditures are tracking below requested/budgeted amounts such that we do not anticipate hitting the 67% expenditure level until end of 2Q2012. We expect to complete 29 miles of fiber in 4Q11 in addition to the 9 miles reporting in 3Q2011. | University of Wisconsin System | The Madison Metro Planning Organization (a federally designated Metro Planning Org or MPO for the Madison urban area), has pushed up a project to resurface and widen County M from Watts Rd to Valley View Rd and along County S (aka Minera Point Rd). This impacts permitting for directional boring excavation of the backbone and 2 laterals in the the Mineral Point Rd backbone. We are finalizing an alternative and will propose to NTIA soon (must wait for City of Madison 35% plans for this road work). | Should winter weather (deep freeze without snow cover) hit WI earlier than 12/1/2011 our plans may be delayed until Spring 2012. Also, we have a forthcoming route change in the Mineral Point Rd service area due to planned road construction in 2013 that will require an EA review. This will delay us from our original baseline plan to complete the Mineral Point Rd service area in 4Q2011.
NT10BIX5570045 | 2011 | Q4 | Q4 - 2011 | In 4Q2011, MUFN completed 43 Community Anchor Institution connections (CAIs) and 29.1 total miles of network. In the East Washington Service Area, 20 of 23 CAIs are completed, 2 are partially completed. In the S. Park St Service Area, 5 of 15 CAI connections are completed with the remaining 10 only awaiting fiber splicing before final acceptance. In the Mineral Point Rd Service Area, 14 of 23 CAIs are completed with another 6 awaiting fiber splicing before final acceptance. In the University Ave Service Area, 2 of 14 CAIs are completed with 7 near completion only awaiting fiber splicing before final acceptance. In the Northport Drive Service Area, 2 of 7 CAIs are complete with 4 locations awaiting fiber splicing before final acceptance. In addition to construction activities, we completed a draft version of the consortium agreement and are circulating to legal counsel now for review. MUFN also submitted a route change in the Mineral Point Rd Service Area due to significant road construction plans in the far southwest portion of the service area. | 29 | 0 | 0 | 20 | 29 | 0 | 0 | 43 | We are behind our baseline due to delays with the EA and road construction which delayed our access in the Northport Drive service area and Monona Drive Service ARea. MUFN will not fully catch our 4Q2011 baseline until 4Q2012 due to weather issues (starting Monona Dr service area construction 4/15/2012). | We were unable to complete a fiber agreement to lease 11 miles of fiber though we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. We anticipate having this completed in 2Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path leased at the beginning of the project. | We are behind our baseline 57 miles due to delays with the EA. We are at 2Q2011. MUFN will not catch up to our 4Q2011 baseline until 4Q2012 due to weather issues (starting Monona Dr service area construction 4/15/2012). | N/A | N/A | We are just short of our 2Q2011 projection of 50 interconnect points and will match our 3Q2011 projection of 75 interconnect points by the end of 1Q2012. We are short due to delays obtaining an EA FONSI, unanticipated road construction and some CAI cancellations of service (5). We will near our 100% completion baseline at the end of 4Q2012. | 2 | 7 | 20 | Citywide d/b/a Mad City Broadband; WI Independent Network (WINs) | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City have formalized and finalized the relationships. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Todd Anderson 608-237-6152; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 2 | 0 | Below baseline projection of 2 due to delays in fiber installation which was delayed by delay in obtaining an EA FONSI | On target with the baseline projections | On target with the baseline projections | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 43 | 7 | 36 | 0 | Surpassed our 1Q2011 baseline in 4Q2011. We will approach our 3Q2011 # of subscribers in 1Q2012 as we expect to complete a significant number of CAIs in Jan 2012. We will not reach 4Q2011 baseline until near end of project (4Q2012) due to Monona Drive PFSA delays and assuming additional locations are approved to make up for the 5 dropped locations by CAI decision. | We are near our 3Q2011 baseline (2 short) at the end of 4Q2011 and expect be at 11 by the end of 1Q2012. We will not meet our initial baseline of 14 new access subscribers until 4Q2012 due to road construction in the Monona Drive Service Area. | We are just short of our 2Q2011 baseline number and will surpass our 3Q2011 baseline number of 64 in 1Q2012. We will not approach our 4Q2011 (84) baseline of improved access subscribers until 4Q2012 due to road construction delays. In addition, due to 5 CAIs asking MUFN to drop laterals to their facilities, we will not reach 4Q2011 baseline of 84 unless additional CAI locations are approved to make up for the 5 dropped locations. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN expects to have 74 CAIs completed and 40 miles of fiber installed - including all Northport Drive Service Area backbone fiber as well as 2 CAIs in the East Washington Service Area, 10 CAIs in the S. Park St Service Area, 6 more CAIs in the Mineral Point Rd Service Area, 5 more CAIs in the Northport Drive Service Area, and 8 more CAIs on University Ave Service Area. We also expect to develop, finalize, issue and award a request for bid (RFB) on MUFN Phase 3 which encompasses the Monona Drive Service Area. MUFN also anticipates finalizing an optical design and procuring hardware for installation. Finally, MUFN expects to be substantially complete with a legal review of the MUFN consortium agreement. | University of Wisconsin System | The Madison Metro Planning Organization (a federally designated Metro Planning Org or MPO for the Madison urban area), has pushed up a project to resurface and widen County M from Watts Rd to Valley View Rd and along County S (aka Minera Point Rd). This impacts permitting for directional boring excavation of the backbone and 2 laterals in the the Mineral Point Rd backbone. We submitted a route change to NTIA and per NTIA's request, have initiated EA and archeological consultant services to review and amend the original EA. | MUFN may encounter problems acquiring final right-of-way in the City of Monona which may impact 2 CAIs. Also, we are proceeding with an amendment to our EA FONSI for our proposed route change and request NTIA to expediently review the submission as soon as resources are available. The EA soil testing may be delayed if WI winter weather turns colder.
NT10BIX5570045 | 2012 | Q1 | Q1 - 2012 | During the first quarter of 2012, UW completed conduit and fiber installations and splicing for 72 community anchor institutions (CAI) in Phase 1 (E. Washington Ave, S. Park St proposed funded service areas) and for Phase 2 (Mineral Point Rd, University Ave and Northport Drive proposed funded service areas) resulting in 44 miles of fiber being completed and ready for production service. UW submitted a route change request to NTIA and is working with Stantec, an environmental consulting organization, to complete a route change environmental assessment (EA) checklist within the Mineral Point Rd service area due to road construction starting in 2013. As part of this effort, UW has contracted an archeologist to review the route change area and complete a report to be included in the final EA route change report for submission to NTIA. UW completed a bid package and solicited bids for Phase 3 (Monona Drive service area). Vendor responses were received on 3/28/12. The Phase 3 bid is expected to be awarded at the beginning of the second quarter 2012. | 44 | 0 | 0 | 20 | 44 | 0 | 0 | 74 | We are behind our baseline due to delays with the EA and road construction which has delayed our FULL completion of Phase 1 (E. Washington Ave) and Phase 2 (Mineral Point Rd) until 4Q2012. In addition, road construction changes in the Monona Drive (phase 3) service area also delayed our ability to finish this area until 4Q2012 when we catch up to our 4Q2011 baseline. | We were unable to complete a fiber agreement to lease 11 miles of fiber though we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. We anticipate having this completed in 3Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path leased at the beginning of the project. | We are behind our baseline 57 miles due to delays with the EA. We are at 2Q2011. MUFN will not catch up to our 4Q2011 baseline until 4Q2012 due to weather issues (starting Monona Dr service area construction 4/15/2012). | N/A | N/A | We are just short of our 3Q2011 projection of 75 interconnect points. We are short due to delays obtaining an EA FONSI, unanticipated road construction and some CAI cancellations of service (5). We will near our 100% completion baseline by the end of 4Q2012. | 1 | 7 | 20 | Citywide d/b/a Mad City Broadband | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City have formalized and finalized the relationships. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Andy Hoyos 608-320-2000; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 1 | 0 | Below baseline projection of 2 due to delays in fiber installation which was delayed by delay in obtaining an EA FONSI | On target with the baseline projections | Behind baseline production due to ruling from NTIA requiring UW or City of Madison agreements to be counted here. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 72 | 10 | 62 | 0 | Surpassed our 1Q2011 baseline in 4Q2011. We will approach our 3Q2011 # of subscribers in 1Q2012 as we expect to complete a significant number of CAIs in Jan 2012. We will not reach 4Q2011 baseline until near end of project (4Q2012) due to Monona Drive PFSA delays and assuming additional locations are approved to make up for the 5 dropped locations by CAI decision. | We just surpassed our 3Q2011 baseline (1 over) at the end of 1Q2011. We will not meet our initial baseline of 14 new access subscribers until 4Q2012 due to road construction in the Monona Drive Service Area. | We are just short of our 3Q2011 baseline number and will surpass our 3Q2011 baseline number of 64 in 3Q2012. We will not approach our 4Q2011 (84) baseline of improved access subscribers until 4Q2012 due to road construction delays. In addition, due to 5 CAIs asking MUFN to drop laterals to their facilities, we will not reach 4Q2011 baseline of 84 unless additional CAI locations are approved to make up for the 5 dropped locations. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN expects to complete an optical network design and begin procurement activities. We expect to begin the Monona Drive service area (phase 3) and have ordered all materials, obtained permits and most if not all rights-of-way. We do not expect to connect any additional CAIs or sign up any additional wholesaler/last mile agreements in 2Q2012 though we expect to complete .7 miles of backbone fiber during the period. | University of Wisconsin System | The City of Monona has changed their construction schedule and plans for Monona Drive (substantial portion of MUFN Phase 3) between Nichols Rd and Winnequah. Rather than reconstructing the entire path in 2014 as originally planned, the City has decided to reconstruct the road in small sections such that we are unable to obtain pole right-of-way on this path and must move 2 blocks to the west as well as redesign 1 lateral. | MUFN may have issues with delivery of fiber optic cable due to seasonal demand from American-made manufacturers. NTIA delays evaluating and approving 2 route change submissions may cause schedule to slide to 3Q2012.
NT10BIX5570045 | 2012 | Q2 | Q2 - 2012 | In 2Q2012, UW completed a bid for phase 3 (Monona Drive service area) and awarded it to Intercon Construction. Intercon and UW completed site surveys of all phase 3 CAIs and also obtained excavation permits from the City of Madison for work in two areas. Intercon directionally bored and installed conduit along Broadway and Nichols Rd. Finally, 1 new CAI, Madison Badger School, was completed in the quarter. | 44 | 0 | 0 | 20 | 44 | 0 | 0 | 89 | We are behind our baseline due to delays with the EA and road construction which has delayed our FULL completion of Phase 1 (E. Washington Ave) and Phase 2 (Mineral Point Rd) until 4Q2012. In addition, road construction changes in the Monona Drive (phase 3) service area also delayed our ability to finish this area until 4Q2012 when we catch up to our 4Q2011 baseline. | We were unable to complete a fiber agreement to lease 11 miles of fiber though we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. We anticipate having this completed in 4Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path leased at the beginning of the project. | We are behind our baseline 57 miles due to delays with the EA. We are at 2Q2011. MUFN will not catch up to our 4Q2011 baseline until 4Q2012 due to weather issues (we began Monona Dr service area construction 4/25/2012). | N/A | N/A | We are under our planned 104 in 2Q2012 due to a delay in obtaining our EA FONSI which pushed the project back 1 yr. Also, we have 5 CAIs (also interconnect points) that were requested be dropped from the project due to budget cuts. We expected to complete Monona Drive in 4Q2012 and hit 99 interconnection points in early Dec 2012. | 1 | 7 | 20 | Citywide d/b/a Mad City Broadband | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City have formalized and finalized the relationships. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Andy Hoyos 608-320-2000; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 1 | 0 | Below baseline projection of 2 due to delays in fiber installation which was delayed by delay in obtaining an EA FONSI | On target with the baseline projections | Behind baseline production due to ruling from NTIA requiring UW or City of Madison agreements to be counted here. Expect a 2nd agreement to be executed in 3Q2012 | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 73 | 11 | 62 | 0 | We will not reach 4Q2011 baseline until near end of project (4Q2012) due to Monona Drive PFSA delays (connecting laterals in 3Q2012 and 4Q2012). | We will not meet our initial baseline of 14 new access subscribers until 4Q2012 due to road construction in the Monona Drive Service Area. | We are just short of our 3Q2011 baseline number and will surpass our 3Q2011 baseline number of 64 in 3Q2012. We will not approach our 4Q2011 (84) baseline of improved access subscribers until 4Q2012 due to road construction delays. In addition, due to 5 CAIs asking MUFN to drop laterals to their facilities, we will not reach 4Q2011 baseline of 84 unless additional CAI locations are approved to make up for the 5 dropped locations. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN anticipates completing 10 CAI laterals and an additional 5.5 miles of fiber in 3Q2011. We also expect to begin work on remaining laterals and backbone sections delayed by road construction. MUFN expects to complete an optical equipment procurement. We expect to sign an additional wholesale provider in 3Q2012 for a total of 2. | University of Wisconsin System | The City of Monona has changed their construction schedule and plans for Monona Drive (substantial portion of MUFN Phase 3) between Nichols Rd and Winnequah. Rather than reconstructing the entire path in 2014 as originally planned, the City has decided to reconstruct the road in small sections such that we are unable to obtain pole right-of-way on this path and must move 2 blocks to the west as well as redesign 1 lateral. We will need NTIA's help to approve a route change in this PFSA. In addition, we redesigned our optical network and request NTIA approval of a budget change AAR in order to proceed with purchase. | MUFN is discussing 3 route changes (phase 2 (Watts Rd), phase 3 (Monona Dr), phase 4) as well as a rebudget request to accommodate an optical transmission system and a fiber database product. We anticipate challenges depending on NTIA's timing of making a decision. Also, MUFN is losing its project manager in early July 2012. We have selected a new person and have commenced cross-training activities.
NT10BIX5570045 | 2012 | Q3 | Q3 - 2012 | In 3Q2012, UW completed 7 Community Anchor Institution (CAI) connections in the Monona Drive Service Area (phase 3) and a total of 5.3 miles (48 miles completed for project). We also submitted a rebudget request (approval received on 8/30/12), environmental assessment and programmatic documents for route changes in the Mineral Point Rd (Watts Rd), Monona Drive, S. Park St, E. Washington Ave and Northport Drive service areas. Finally, during the quarter we also let out an RFB for purchasing direct current (DC) power systems and an RFP for purchasing optical hardware. | 48 | 0 | 0 | 20 | 48 | 0 | 0 | 96 | We are behind our baseline due to delays with the EA and road construction which has delayed our FULL completion of Phase 1 (E. Washington Ave) and Phase 2 (Mineral Point Rd) until 4Q2012. In addition, road construction changes in the Monona Drive (phase 3) service area also delayed our ability to finish this area until 4Q2012 when we catch up to our 4Q2011 baseline. | We were unable to complete a fiber agreement to lease 11 miles of fiber though we have a verbal agreement with UW Hospital & Clinics and are developing a written agreement. We anticipate having this completed in 4Q2012 after we complete the MUFN consortium agreement. The UWHC agreement will be between the MUFN consortium and UWHC rather than UW-Madison and UWHC which is the delay. | N/A | 20 miles is the total of the Wisconsin Department Of Transportation fiber path leased at the beginning of the project. | We are behind our baseline 57 miles due to delays with the EA. We are at 2Q2011. MUFN will not catch up to our 4Q2011 baseline until 4Q2012 due to weather issues (we began Monona Dr service area construction 4/25/2012). | N/A | N/A | We are under our planned 104 in 2Q2012 due to a delay in obtaining our EA FONSI which pushed the project back 1 yr. Also, we have 5 CAIs (also interconnect points) that were requested be dropped from the project due to budget cuts. We expected to complete Monona Drive in 4Q2012 and hit 99 interconnection points in early Dec 2012. | 2 | 6 | 50 | Citywide d/b/a Mad City Broadband, Wisconsin Independent Network (aka WINs) | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and Citywide d/b/a Mad City Broadband will operate the network together. UW and the City have formalized and finalized the relationships. Mad City Broadband's contact information: 301 N. Broom St., Madison, WI 53703, Andy Hoyos 608-320-2000; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 2 | 0 | Below baseline projection of 2 due to delays in fiber installation which was delayed by delay in obtaining an EA FONSI | On target with the baseline projections | City of Madison signed agreement with WINs in early 3Q2012 | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 80 | 11 | 69 | 0 | We will not reach 4Q2011 baseline until near end of project (4Q2012) due to Monona Drive PFSA delays (connecting laterals in 3Q2012 and 4Q2012). Also finishing phase 1 (1 location) and phase 2 (2 locations) work in mid-4Q2012 as road construction is completed in these areas. | We will not meet our initial baseline of 14 new access subscribers until 4Q2012 due to road construction in the Monona Drive Service Area. | Met 3Q2011 baseline metric but will not meet 4Q2011 metric until 4Q2012. We will not meet our 4Q2011 (84) baseline of improved access subscribers due to 5 CAIs asking MUFN to drop laterals to their facilities. Will meet 79 improved access subscribers in 4Q2012. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN expects to complete procurement, ordering and installation of DC power and optical network hardware based on the 8/25/12 approved rebudget request. We also expect to finish all remaining fiber construction including Monona Dr, E. Washington Ave & University Ave service areas. This includes connecting the remaining 9 community anchor institutions for a total of 91 and 8.3 miles for a project total of 56.3 miles. Finally, we expect to complete the MUFN consortium agreement. | University of Wisconsin System | Need final approval of Monona Drive and Mineral Point Rd route change requests in order to complete construction in 4Q2012 before winter hits in WI. Also, we continue working with MG&E on a license agreement to use poles for the planned route change in the Monona Drive service area. This process has been slowed due to personnel changes at MG&E and we are expediting so we are ready once the anticipated route change approval is received. In addition, we ran into some delays gaining final internal approvals to issue an RFP for optical hardware. This delayed us approximately 2.5 weeks from issuing the bid by Labor Day. Finally, after several iterations and delays with certain THPOs and the SHPO, we submitted a phase 4 route change request to NTIA. | MUFN continues to work with MG&E on a license agreement to use poles for the planned route change in the Monona Drive service area. This process has been slowed due to personnel changes at MG&E and we are expediting so we are ready once the anticipated route change approval is received. Also, MUFN requests expedient approval of a submitted phase 4 route change request in order to ensure installation can occur in 4Q2012.
NT10BIX5570045 | 2012 | Q4 | Q4 - 2012 | During the fourth quarter of 2012, UW completed conduit and fiber installations and splicing for 8 community anchor institution (CAI) in Phase 3 (Monona Drive service area) and 1 CAI in Phase 1 (East Washington Ave service area) resulting in a total of 89 CAI connections and 56 miles of fiber being completed and ready for production service. We received approval on 10/22/12 and have completed 2 route changes; Watts Rd change in the Mineral Point Rd service area (phase 2) and Monona Drive (Phase 3) route change. In addition, we received approval to begin a phase 4 route change comprised of an additional 18.25 miles of fiber approved on 12/6/12 and have issued PO to Intercon Construction to furnish and install the fiber. With the above work, MUFN has completed 5 of 6 service areas (East Washington Ave, Mineral Point Rd, Northport, Monona Drive and S. Park St) with a small amount of work remaining in the University Ave service area. MUFN has also awarded a DC power system RFP agreement to Tabur Systems to provide Alpha Technologies, Inc power equipment for an optical system. We ordered, received and installed the equipment during the quarter. We also awarded an optical network RFP to TorreyPoint Group to provide ADVA optical hardware. We ordered, received and began hardware installation during period. | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 99 | We are near our baseline but weather caused us to miss completing our planned activities. Due to dropping 5 sites and even adding in additional route change miles, we can not hit our baseline of 57.05 miles. Also, we received approval for MUFN Phase 4 in 4Q2012 and have a late start to completing this by 1/31/13. | NTIA has determined that the segment associated with the UW Hospitals and Clinics lease will be counted as Existing Network Miles Upgraded once the agreement is signed and the grant-funded equipment is used to light the miles. No new miles will be leased. | MUFN plans to light via grant-funded optical equipment in-kind fiber (5.75 miles) and leased fiber from WisDOT (20.25 miles) and UW Hospitals and Clinics (11 miles) in 1Q2013. | NTIA has determined that the segment associated with the existing WisDOT lease will be counted as Existing Network Miles Upgraded once the grant-funded equipment is used to light the miles. | MUFN will finish original plan in January 2013, completing MUFN phases 1-3 by 1/11/13. We will likely struggle to complete phase 4 by 1/31/13 due to a late start and delays obtaining fiber materials. | N/A | N/A | We are under our planned 104 in 2Q2012 due to a delay in obtaining our EA FONSI which pushed the project back 1 yr. Also, we have 5 CAIs (also interconnect points) that were requested be dropped from the project due to budget cuts (dropping our interconnection points to 99. | 2 | 6 | 50 | SupraNet (formerly Citywide d/b/a Mad City Broadband), Wisconsin Independent Network (aka WINs) | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The City of Madison in collaboration with UW and SupraNet (formerly Citywide d/b/a Mad City Broadband) will operate the network together. UW and the City have formalized and finalized the relationships. SupraNet's contact information: 8000 Excelsior Drive, Madison, WI 53717, Bryan Chang 608-836-0282; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699. | 0 | 0 | 0 | 0 | Optical network not completed yet but will be available for use by 1/16/13. | Optical network not completed yet but will be available for use by 1/16/13. | Two (2) commercial providers have not started using fiber (yet) but will in near future. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 89 | 12 | 77 | 0 | Below 98 CAIs due to 5 dropped locations (at institution request due to facility closures); also not counting 2 CAIs per NTIA request; snowstorm and road construction issues delayed completion of 2 CAIs in 4Q2012 as expected. Will meet baseline in January 2013 | Below 14 CAIs per NTIA request to not count 2 locations as CAIs | Below 84 CAIs due to 5 dropped locations (at institution request due to facility closures); snowstorm and road construction issues in University Ave PFSA delayed completion of 2 CAIs in 4Q2012 as expected. Will meet baseline in January 2013 | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN expects to: complete DC power and optical network installation; complete fiber construction to 3 remaining CAIs (including one added in "Phase 4" route change request); complete Phase 4 route change of 18.25 miles; execute and "stand up" the MUFN Consortium, Unincorporated Association; execute subrecipient amendment between UW and City of Madison, (with NTIA approval) allocate conduit, fiber and optical network to MUFN Consortium. We anticipate having 3 broadband wholesaler provider agreements by the end of 1Q2013. | University of Wisconsin System | A significant snowstorm hit Wisconsin the week before Xmas resulting in 1 week delays in fiber construction (e.g. clearing snow, inactivity). MUFN received approval to proceed with phase 4 on 12/6/13. We submitted a phase 4 grant extension request on 12/20/13 and hope to receive approval in January to ensure we meet phase 4 plans. Fiber for phase 4 will be received approximately 1/14/13. Finally, we submitted a request to add a subrecipient (MUFN Consortium, Unincorporated Association). We hope this will be approved before the end of January so UW can allocate conduit, fiber and the optical network to the consortium before the end of the grant period. | MUFN anticipates potential struggles with weather in 1Q2013. As a result, we hope NTIA will approve our extension request to ensure if we hit any bad weather we can finish Phase 4 route changes. We also seek approval of adding MUFN Consortium, Unincorporated Association as a grant subrecipient in order to alleviate issues created by the State of Wisconsin legislature in 2011 (Act 32).
NT10BIX5570045 | 2013 | Q1 | Q1 - 2013 | During the first quarter of 2013, UW completed conduit and fiber installations for the University Avenue service area and added an additional 2 community anchor institutions (CAIs) for a total of 91 CAIs and a total of 56.03 miles of new fiber. We also completed 90% of MUFN Phase 4 (16.4 miles of an 18.25 mile route change) though construction was halted as of 1/30/13 until approximately mid-April due to ice/snow in the conduits. UW received a grant extension until 6/30/13 in order to complete phase 4 work. UW completed entry of fiber as-built information into a GIS-based conduit and fiber database system for phases 1-3 of the project and for the completed portions of phase 4. We also completed a 12-node optical network installation of ADVA hardware during the period. In addition, UW created the Metropolitan Unified Fiber Network - Consortium, Unincorporated Association (MUFN-C, U.A.) under Wisconsin Statute 184. The consortium has begun the process of acquiring an IRS 501(c)(4) designation and is bootstrapping operations into long-term production. Finally, UW executed several agreements including a subrecipient agreement with the newly formed MUFN-C, U.A. and an amendment to the City of Madison subrecipient agreement clarifying agreement terms. | 72 | 0 | 56 | 0 | 72 | 0 | 0 | 99 | Adverse winter weather conditions slowed and then halted construction (ice in conduits). | No new network miles are being leased. | NTIA determined that the segment associated with the UW Hospitals and Clinics lease will be counted as Existing Network Miles Upgraded once the the grant-funded equipment is used to light the miles. | NTIA has determined that the segment associated with the existing WisDOT lease will be counted as Existing Network Miles Upgraded once the grant-funded equipment is used to light the miles. | MUFN will finish with 74.3 miles of fiber completed by 6/7/13 | N/A | N/A | We have 1 more upgraded interconnection point to finish as part of MUFN Phase 4 which will be completed by 6/7/13. | 2 | 7 | 50 | SupraNet (formerly Citywide d/b/a Mad City Broadband), Wisconsin Independent Network (aka WINs) | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf) | The MUFN Consortium (subrecipient to UW) in collaboration with the City of Madison (subrecipient to UW), UW, WINs (subcontractor to MUFN-C) and SupraNet (subcontractor to MUFN-C) (formerly Citywide d/b/a Mad City Broadband) will operate the network together. SupraNet's contact information: 8000 Excelsior Drive, Madison, WI 53717, Bryan Chang 608-836-0282; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699, WINMetro, LLC contact information: 800 Wisconsin Street, Building DO2, Suite 219, Eau Claire, WI 54703, Scott Hoffmann (715) 832-3722. The City of Madison is responsible for maintaining conduit and fiber within the City of Madison jurisdiction. MUFN-C is responsible for maintaining fiber outside the City of Madison jurisdiction and managing the optical infrastructure. WINMetro, LLC and SupraNet will provide NOC services and inforation technology services respectively for all conduit and fiber infrastructure while UW-Madison will perform engineering services for conduit, fiber and the optical infrastructure. | 0 | 2 | 0 | 0 | MUFN is not in negotiations with providers receiving new access. | SupraNet and WINs received improved access. | Two (2) commercial providers have not started using fiber (yet) but will in near future. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 91 | 12 | 79 | 0 | Below 98 CAIs due to 5 dropped locations (at institution request due to facility closures); also not counting 2 CAIs per NTIA request. Will complete last CAI as part of phase 4 (Bedford St) by 6/7/13. | Below 14 CAIs per NTIA request to not count 2 locations as CAIs | Below 84 CAIs due to 5 dropped locations (at institution request due to facility closures); snowstorm and ice in conduits delayed completion of 1 CAI in 1Q2013 as anticipated. Will meet baseline by 6/7/13. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | MUFN will complete phase 4 which includes upgrading connectivity to 1 CAI, installation of 1.8 miles of fiber and entry of phase 4 into our fiber database. We anticipate having 3 broadband wholesaler provider agreements by the end of 2Q2013. | University of Wisconsin System | Wisconsin suffered a normal to severe winter season followed by significant rain in March. We have been unable to work in the conduit system since 1/30/13 due to ice in the system. | It is possible for a wet spring to hamper our installation activities though we do not anticipate any insurmountable issues and will complete the project in 2Q2013.
NT10BIX5570045 | 2013 | Q2 | Q2 - 2013 | UW received and paid all outstanding invoices as well as performed a final draw-down of federal funds. We submitted 3 UCC-1 statements (1 for the City of Madison, 1 for the Metropolitan Unified Fiber Network Consortium, Unincorporated Association and 1 for UW-Madison), received approval of form/content of the 3 UCC-1 statements and submitted to appropriate State of WI or local register of deeds. We also submitted final SF425 and other required closeout documentation. | 74 | 0 | 56 | 0 | 74 | 0 | 0 | 100 | All new network miles are deployed | No new network miles are being leased | All network mile upgrades are complete | No existing network miles are being leased | MUFN finished the grant with 74.3 miles of new fiber | N/A | N/A | MUFN has completed all interconnection points | 2 | 7 | 50 | SupraNet (formerly Citywide d/b/a Mad City Broadband), Wisconsin Independent Network (aka WIN) | MUFN wholesale services offered by the project include point-to-point dark fiber and point-to-point wavelength services (where fiber IRUs permit). See attached document (BTOP-MUFN-PricingPlan.pdf). | The MUFN Consortium (subrecipient to UW) in collaboration with the City of Madison (subrecipient to UW), UW, WINs (subcontractor to MUFN-C) and SupraNet (subcontractor to MUFN-C) (formerly Citywide d/b/a Mad City Broadband) will operate the network together. SupraNet's contact information: 8000 Excelsior Drive, Madison, WI 53717, Bryan Chang 608-836-0282; UW-Madison's contact information: Pat Christian, 1210 W. Dayton St., Madison, WI 53706, 608-265-9699, WINMetro, LLC contact information: 800 Wisconsin Street, Building DO2, Suite 219, Eau Claire, WI 54703, Scott Hoffmann (715) 832-3722. The City of Madison is responsible for maintaining conduit and fiber within the City of Madison jurisdiction. MUFN-C is responsible for maintaining fiber outside the City of Madison jurisdiction and managing the optical infrastructure. WINMetro, LLC and SupraNet will provide NOC services and inforation technology services respectively for all conduit and fiber infrastructure while UW-Madison will perform engineering services for conduit, fiber and the optical infrastructure. | 0 | 0 | 2 | 0 | MUFN is not in negotiations with providers receiving new access. | Commercial groups not using optical network yet - focusing efforts on dark fiber first. | Both commercial entities began using MUFN fiber infrastructure at the end of 2Q2013. | Dark fiber; users can pick their own baseband speed/signaling type (i.e. ethernet) or light fiber via wave-division multiplexing | 92 | 12 | 80 | 0 | Below 99 CAIs due to 5 dropped locations (at institution request due to facility closures); also not counting 2 locations MUFN initially considered CAIs per NTIA request. | Below 14 CAIs per NTIA request to not count 2 locations as CAIs | Below 84 CAIs due to 5 dropped locations (at institution request due to facility closures) and addition of 1 CAI as part of MUFN phase 4. | MUFN is a dark fiber project - most subscribers lighting dark fiber at minimum 1Gbps if not 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of grant closeout activities including recording of NTIA security interest. | University of Wisconsin System | None - grant term ended and finalizing grant closeout paperwork. | None - grant term and 90 day closeout period ended 9/28/13.
NT10BIX5570046 | 2010 | Q3 | Q3 - 2010 | This quarter the Joint Legislative Committee of Budget approved our spending authority for our construction, engineering design and environmental budget. The State Facility Planning and Control has selected an engineering firm to conduct both the engineering design and environmental assessment. We have an acceptable set of principles between a certain number of private service providers in how to most effectively utilize the fiber assets resulting from the grant. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 5 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The next quarter we will be spending federal funds on engineering design and environmental assessment. The selected firm will submit the draft environment assessment as well as complete the program completion and schematic design including some amount of survey work by 1/31/10. | Louisiana Board of Regents | As the grant administering agency, the Louisiana Board of Regents/LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary state requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with the Board of Regents suffering an approximate 50% reduction in general state fund support. LONI operations, although largely protected, did suffer a funding reduction of a manageable magnitude. In recent news this quarter the State's end-of-year accounting from last year resulting in a deficit requiring the Board of Regents to accept a $2.4M budget cut in this year budget as all of state government is cut by more than $150M. | One major challenge will be to finish the EA as quickly as possible based upon our approved extension.
NT10BIX5570046 | 2010 | Q4 | Q4 - 2010 | In this quarter we finalized our contract with Gulf Engineers and Consultants (GEC) the firm selected to provide our Engineering Design and Environmental Assessment (EA) services. GEC is still on schedule to submit our draft EA by January 31, 2011. GEC has started the research and data collection for the existing environment section of the EA. Several sub-sections, including, geology and soils, air quality, water quality, biological resources, land use, and aesthetics were completed substantially (95%). Work on the subsections for cultural resources and infrastructure commenced (50%). Office coordination with the Louisiana State Historical Presevation Office (SHPO) is ongoing. Coordination letters to the U.S. Fish and Wildlife and the U.S. Army Corps of Engineers (New Orleans and Vicksburg Districts) were delivered. Environmental field crews inspected over 800 miles of the route to determine potential environmental issues and data was delivered to environmental personnel for processing. Fiber field crews surveyed all project segments (both rural and urban areas) to determine which side of the existing roadway is the optimal route. This information was forwarded to the environmental field crews and design personnel for processing. Required permits are being identified as part of the EA document preparation as well as field inspections. Right-of-way (ROW) issues, if any, are and will continue to be discovered during the preliminary and final inspections of the outside plant (O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | N/A | 0 variance Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione your reasons for any variance from the baseline plan or any other relevant information) | 0 | 5 | 0 | 0 variance | 0 variance | N/A | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter GEC will be submitting the Environmental Assessment, Program Completion and Schematic Design. In addition, we intent to purchase some of the hardware and software needed to facilitate the network testing phase. | Louisiana Board of Regents | The time taken to execute the contract between the State Facility Planning and Control (FP&C) and GEC took 30 days more than anticipated. We were delayed by the Executive Branch from being authorized to spend the awarded federal funding until August 18, 2010. GEC reports the compressed schedule for all efforts is atypical for a project of this size, however efforts are tracking week and currently there are no delays. As the grant administering agency, the Louisiana Board of Regents/LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary state requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with a $1.6B deficit predict next fiscal year starting July 1, 2011. | GEC reports the compressed schedule for all efforts is atypical for a project of this size, however efforts are tracking week and currently there are no delays. The BTOP program might have to engage on our behalf the U.S. Arm Corps of Engineers to obtain a final response to GEC's coordination letter and resulting permit. As the grant administering agency, the Louisiana Board of Regents/LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary state requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with a $1.6B deficit predict next fiscal year starting July 1, 2011. Recent communications with the Executive Branch highlight this upcoming cliff.
NT10BIX5570046 | 2011 | Q1 | Q1 - 2011 | In this quarter Gulf Engineers and Consultants (GEC) the firm contracted to provide our Engineering Design and Environmental Assessment (EA) services submitted our draft EA by January 31, 2011. GEC has completed the research and data collection for the existing environment, environmental consequences, and other sections of the EA. GECâ€™s environmental field crews completed inspection of the route for the purpose of determining potential environmental issues. GECâ€™s environmental field crews completed inspection of the route for the purpose of determining potential environmental issues. Final draft EA is substantially complete, will be submitted once agency coordination is complete, and will include the information necessary to allow the preparation of a Finding Of No Significant Impact (FONSI). Remaining items to be included are (1) SOV response letter from the USACE â€“ Vicksburg District, (2) responses from solicited Native American tribes (or sufficient elapse of time), (3) final determination of a course of action for undefined cultural sites, and (4) response from USFS. GECâ€™s communications field crews began surveying each project segment (both rural and urban areas) for the purpose of finalizing the fiber route and identifying the placement of conduit, structures, construction techniques, handholes, and interconnect points and for identifying required permits for construction. GEC has begun coordination for placement of interconnect points (new standalone building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | N/A | 0 variance | 0 | 5 | 0 | 0 variance | 0 variance | N/A | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | FALSE | N/A | Next quarter GEC will be submitting the final Environmental Assessment, Schematic Design, Design Development and Construction Documents submittals. We intent to purchase additional hardware to conduct the network testing to qualify the performance characteristics of the fiber and service. | Louisiana Board of Regents | GEC reports a challenge taken to complete the coordination with and the receipt of timely responses from coordinating agencies (USACE and USFS). GEC reports good communications with the LA SHPO but archaeological aspects of the project are still in review. GEC reports the compressed schedule for all efforts is atypical for a project of this size, however efforts are tracking weekly and currently there are no significant delays. We initiated the procurement of some hardware and software to assist with the network design, network build, equipment deployment and network testing. As the grant administering agency, the Louisiana Board of Regents/LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with a $1.6B deficit next fiscal year starting July 1, 2011. | GEC reports the compressed schedule for all efforts is atypical for a project of this size, however efforts are tracking week and currently there are no delays. As the grant administering agency, the Louisiana Board of Regents/ LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary state requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with a $1.6B deficit next fiscal year starting July 1, 2011.
NT10BIX5570046 | 2011 | Q2 | Q2 - 2011 | In this quarter Gulf Engineers and Consultants (GEC) the firm contracted to provide our Engineering Design and Environmental Assessment (EA) services submitted our final EA on May 11, 2011. NTIA issue a Finding of No Significant Impact (FONSI) against the final EA on June 3, 2011. GEC completed coordination efforts with respect to the EA with the U.S. Fish and Wildlife Service (USFS), the U.S. Army Corps of Engineers â€“ New Orleans and Vicksburg Districts, the U.S. Forest Services (USFS) the Louisiana State Historic Preservation Office (LASHPO) and the Louisiana Department of Natural Resources (LDNR). GEC continues to coordinate with these agencies for construction and permitting purposes. GECâ€™s communications field crews completed the survey of each rural project segment but the survey of urban project segments continues for the purpose of finalizing the fiber route and identifying the placement of conduit, structures, construction techniques, handholes, and interconnect points. GEC continues to identify required permits for construction. GECâ€™s field inspection and survey data was delivered to the design team for review and incorporation into the fiber route maps for construction. Consequently, draft fiber route maps were delivered to the design team and field crews for review and verification. GEC has started the work to incorporate the fiber route maps into the construction documents. GEC was directed to develop and organize the construction documents into twelv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | N/A | 0 variance | 0 | 5 | 0 | 0 variance | 0 variance3 | N/A | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | FALSE | N/A | STATEMENTS PROVIDED BY THE STATE: As discussed in our July 6th meeting with NITA, we have documented the steps required in an alternative approach include a project work plan. We will now initiate the initial phases of that plan, including scheduling meetings with the vendor community to identify the facilities available and required to provide the identified services. We will provide NTIA with written results of these meetings. Based on the results, we will then seek formal NTIA approval for any changes in approach by September 7, 2011. | Louisiana Board of Regents | STATEMENTS PROVIDED BY GEC: Compressed schedule for all efforts is atypical for a project of this size. Changes introduced during 2Q have impacted the schedule and deliverables. Coordination with and the receipt of timely responses from agencies / entities where existing conduit will be utilized for the benefit of the fiber route. Perceived competition by private interests delayed the finalization of several interconnect points and the fiber routes thereto. Coordination with and the timely responses from coordinating agencies (USACE, USFS). STATEMENTS PROVIDED BY THE STATE: There is a growing concern with GEC who has not met their deliverables for this quarter per the terms of their contract. | STATEMENTS PROVIDED BY THE STATE: On July 20, 2011, GEC has been placed suspension for failure to meet the original and recovery milestones, so the State is investigating the validity of an IRU approach to construction. The state plans to represent any changes to the project scope by September 7, 2011. As the grant administering agency, the Louisiana Board of Regents/ LONI, is a state governmental unit subject to all state laws, policies and procedures, and certain necessary state requirements must be met (i.e., approval of appropriation/funding authority, procurement procedures for services, etc.) by state agency grant recipients. Additionally, Louisiana continues to face significant state budget problems with a $1.6B deficit next fiscal year starting July 1, 2011.
NT10BIX5570046 | 2011 | Q3 | Q3 - 2011 | Because of GECâ€™s inability to meet its contracted deliverables, the State is in the process of submitting a design alternative which would use the federal funds to procure 20-year dark fiber IRU solution to deliver the programmatic goals and application intentions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | N/A | 0 variance | 0 | 5 | 0 | 0 variance | 0 variance | N/A | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | FALSE | N/A | The State received a grant termination notice on 10/26/11. | Louisiana Board of Regents | The Louisiana Board of Regents, along with the Division of Administration and Louisiana State University, has worked with the NTIA staff since July to submit an acceptable alternative design which would satisfy their programmatic goals and application intentions. Unfortunately, the State has not been successful in proving the solution based procurement model for the 20-year dark fiber IRU solution within the remaining time of the grant award period. | N/A
NT10BIX5570046 | 2011 | Q4 | Q4 - 2011 | The State of Louisiana proposed an alternative approach on October 14, 2011 but was rejected by NTIA on October 26, 2011 resulting in the termination of the award. The award is being de-obligated this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | N/A | 0 variance | 0 | 5 | 0 | 0 variance | 0 variance | N/A | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | 0 | 0 | 0 | 0 | 0 | 0 variance | 0 variance | 0 variance | 0 variance | 0 variance | N/A | FALSE | N/A | N/A | Louisiana Board of Regents | N/A | N/A
NT10BIX5570047 | 2010 | Q3 | Q3 - 2010 | A major accomplishment this quarter was receiving the Finding of No Significant Impact (FONSI) for this project at the end of the quarter, September 30th. Network and Outside Plant Design continued this quarter in addition to preparing permitting and construction bid documents allowing for initial construction to begin in the next quarter. Detailed staking of the project routes was initiated along with development of material specifications for the construction bid packages. Procurement processes for network equipment began this quarter. Contract evaluations and awarding of the bids are in process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The initial baseline projections indicated construction starting in Q3. Based on the delay of completion of the Environmental Assessment and subsequently the Finding of No Significant Impact (FONSI) being received, the project timeline is delayed by approximately one quarter. | N/A | See new network miles deployed narrative. | 0 | 0 | 0 | 0 | See new network miles deployed narrative. | 37 | 1 | 5 | The 37 signed agreements referred to above are comprised of 36 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and one (1) new agreement in this quarter. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales-marketing information. | There are currently no wholesale services provided as this project has only recently received its Finding of No Significant Impact (FONSI). Construction is scheduled to begin in Q4 of 2010, with some potential that a small number of customers will receive new service. As the network is built, turned up and tested, this list will be updated and data will be provided. | The following entities are sub participants of the project: Sawtooth Technologies, LLC Brian Adams 50 S.E. Cascade Ave., P.O. Box 857 Stevenson, WA 98648 503-807-3048 phone adams@saw.net Black Rock Cable Bob Warshawer 1512 Fairview St. Bellingham, WA 98229 360-738-3116 phone bobw@blackrockcable.com Clallam County Public Utility District Doug Nass 2431 East Highway 101 P.O. Box 1090 Port Angeles, WA 98362 360-452-9771 Phone Pacific County PUD#2 405 Duryea Street P.O. Box 472 Raymond, WA 98577 360-942-2411 Phone webmaster@pacificpud.org Port of Whitman PUD 302 N. Mill Street Colfax, WA 99111 509-397-3791 portwhit@stjohncable.com Franklin PUD Ed Brost 1411 West Clark Street P.O. Box 2407 Pasco, WA 99302 509-547-5591 Phone franklin@franklinpud.com Yakima County 128 North 2nd Street Yakima, WA 98901 509-574-1000 Phone See attached network drawings for the portion of the network they operate. | 0 | 0 | 0 | 0 | The initial baseline projections indicated construction starting in Q3. Due to the delay of a completed Environmental Assessment and subsequently the Finding of No Significant Impact (FONSI) being received, the project timeline is delayed by approximately one quarter. | See narrative above. | N/A | N/A | 0 | 0 | 0 | 0 | See narrative above. | See narrative above. | See narrative above. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Special offerings are not provided at this point in the project as construction is just beginning. | FALSE | N/A | Construction bid packages will be released and construction is planned to begin on a selected route within the project. Equipment contracts will be awarded and deployment will proceed. Site preparation will continue as well as permitting and acquisition of Rights of Way. | Northwest Open Access Network | The baseline projection originally forecasted construction to begin this quarter. Due to delays in completing the Environmental Assessment and receipt of Finding of No Significant Impact (FONSI), the projected milestones have not been met. However, NoaNet continues to modify the project plan with the anticipation of the overall project being completed within the Broadband Technology Opportunities Program guidelines. | Based on the Environmental Assessment and Finding of No Significant Impact (FONSI) being delayed by one quarter, construction is planned to begin in the 4th quarter and baseline projections will be short of goal for Q4. NoaNet has revised the project plan to include an accelerated project construction during Year 2 of the project in order to complete the overall project within the Broadband Technology Opportunities Program guidelines.
NT10BIX5570047 | 2010 | Q4 | Q4 - 2010 | Northwest Open Access Network (NoaNet) continued to progress on route preparation, right of way acquisition, and permitting. NoaNet provided notice of the Statewide State Environmental Protection Act (SEPA) determination and fulfilled associated process that are expected to conclude mid January. No comments of any substance were received in response to this SEPA determination which clears the way for construction permitting with local and governmental jurisdictions. Optical Network equipment was purchased for placement once construction has proceeded. Final staking has been completed on all NoaNet routes as well as sub participant routes for Pacific PUD and Black Rock Cable. Construction bids were released to the street and responses were received within the quarter. In addition, route modifications are being finalized on select routes with final approval pending with NTIA. Finally, we completed our first reimbursement for sub participants as well as additional training for sub participant reporting. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline projections had indicated construction starting in the 3rd quarter of 2010. Due to the duration of the permitting process taking longer than originally projected, the project timeline is delayed. It is anticipated Northwest Open Access Network will be on target with this milestone by the end of Year 2 of the project. | N/A | See narrative above. | See narrative above. | See narrative above. | N/A | N/A | See narrative above. | 38 | 1 | 20 | The 38 signed agreements referred to above are comprised of 36 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and (2) new agreements in the past two quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales-marketing information. | There are currently no wholesale services being provided as a result of this funding since limited construction started this quarter. As the network is built, turned up, and tested, this list will be updated and data will be provided. | Subrecipients: SawNet, c/o Sawtooth Technologies, 50 SE Cascade Ave, Stevenson, WA 98648 509-427-4865 Black Rock Cable,Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Network drawings have been previously provided. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Additional construction contracts will be advertised for bidding and awards made for additional NoaNet and most sub participant segments of the network. Rights of way and permitting continue within the project, with anticipated completion by end of Year 2 of the project timeline. Construction will start to advance at a rapid pace as weather and permitting allows. Some sub participants are anticipated to begin construction on their phases of the project as we near the end of the quarter. We will begin processing reimbursements for a majority of our sub participants, which will include more comprehensive reporting for the quarter. | Northwest Open Access Network | Based on the original baseline projections, construction was scheduled to begin prior to this quarter. With the permitting taking on some unanticipated delays, this will delay construction until the next quarter. | Once again, weather could play a role in progression of construction during the next quarter. It is anticipated that in Year 2 of the project that some, if not all of the lag in the milestones will be on target. Northwest Open Access Network has intentions of completing the project within the Broadband Technology Opportunities Program guidelines.
NT10BIX5570047 | 2011 | Q1 | Q1 - 2011 | The quarter was primarily focused on preparation and finalization of construction related activities on initial routes. Construction contracts were awarded for segments of the project, with some construction starting this period. Staking, network design, right of way acquisition, permitting, and equipment procurement activities all continued to advance during this quarter resulting in awards to Outside Plant contractors for six different routes and included over three hundred fifty (350) miles of the project. Permits for these projects are expected within weeks which will enable construction to start in multiple areas around the state. Sub recipient involvement increased activity as they near finalization of agreements, contracts and vendor selection. One sub recipient in the northeast corner of the state started construction on March 25, 2011. | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | Initial projections had construction starting earlier in the three year timeline of the project. Resources and planning for completion on time have been implemented to meet the Broadband Technology Opportunities Program guidelines. | N/A | N/A | N/A | See Narrative above. | Wireless links, as part of this project, were originally scheduled to be in operation. Due to delay in the initial start of construction, this phase has not yet been initiated. | See narrative under "new wireless links' above. | Interconnection points have not been made available yet as indicated by the delay in start of construction of the network. As the project progresses and 'points' are brought on line in the network, this number will be provided at the rate of progression. | 39 | 1 | 20 | The 39 signed agreements referred to above are comprised of 36 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and (3) new agreements in the past three quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales-marketing information. | There are currently no wholesale services being provided as a result of this funding since construction started this quarter. As the network is built, tested and put into service this list will be updated and data will be provided. | Subrecipients: SawNet, c/o Sawtooth Technologies, 50 SE Cascade Ave, Stevenson, WA 98648 509-427-4865 Black Rock Cable,Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Network drawings have been previously provided. | 0 | 0 | 0 | 0 | As indicated earlier in this report, construction was started very late in this quarter. As a result, initial projections of having service up and operational as a result of this funding will occur later than originally forecasted. Progress is anticipated on this milestone as the project proceeds throughout the year. | See narrative above concerning new access, this will hold true for those with improved access as well. | N/A | N/A | 0 | 0 | 0 | 0 | With the Network Build starting this quarter, and service not yet initiated, no subscribers have received service. Progress is anticipated on this milestone as the project proceeds throughout the year. | See narrative above. | See narrative above. | None at this time in the construction phase. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this stage of the project. | FALSE | N/A | Activities will gain momentum as construction on several segments that comprise over four hundred (400) route miles throughout the state begins. An additional 140 miles will be awarded and construction started prior to quarter end. Sub Recipient projects are anticipated to be awarded in May account for 267 miles of the overall project, or 27%. A combined total of approximately seven hundred (700) miles or 72% of the project will be under construction or awarded by end of 2nd Quarter 2011. Work in all areas of the project will continue and its anticipated the project will begin to align with the milestones. Job creation with additional construction activities will add to the Full Time Equivalent hours already created by this funding opportunity. | Northwest Open Access Network | Based on initial projections, it has been challenging reaching Milestones, as the project originally intended the construction phase of the project to commence much earlier. The extended timeline for staking and permitting has protracted construction start dates. | Construction is anticipated to accelerate through this quarter as long as the necessary permits and approvals to proceed are received from agencies and tribes. Additionally, finalization and approval of the In Kind assets attributed toward the project would help in attaining the project milestones as originally implemented during the Baseline planning process. Any assistance from BTOP program to expedite the process is greatly appreciated.
NT10BIX5570047 | 2011 | Q2 | Q2 - 2011 | Increased construction activities highlighted the quarter, with numerous areas around the State starting to see the benefits of the past year of planning, permitting and preparation. Some Sub Recipient construction activity began in select parts of the state with other sub recipients in process of finalizing contracts. Finalization of permitting, easement acquisition, and Rights of Way for projects scheduled for completion during 2011 is taking place. | 27 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | Initial Baseline projections had construction and Network Build taking place in quarter three of the project life cycle and as previously stated those items are behind schedule due to the length of time it took to receive approval on the Environmental Assessment. | N/A | N/A | N/A | See narrative under 'New Network miles deployed' above. | Wireless links, as part of this project, were originally scheduled to be in operation. Due to delay in the initial start of construction, this phase has not yet started. | See narrative under "new wireless links" above. | Interconnection points have not been made available yet as indicated by the delay in start of construction of the network. As the project progresses and 'points' are added to the network, this number will be updated and provided. | 42 | 1 | 20 | The 42 signed agreements referred to above are comprised of 36 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and six (6) new agreements in the past four quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales-marketing information. | There are currently no wholesale services being provided as a result of this funding since construction has just recently started within this quarter. As the network is built and put into service this list will be updated and data will be provided. | Subrecipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave, Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Network drawings have been previously provided. | 0 | 0 | 0 | 0 | As was indicated earlier, construction was started this quarter. As a result, Baseline projections of having service up and operational as a result of this funding will occur later than originally forecasted. Progress is anticipated on this milestone as the project proceeds throughout the year. | The narrative above is the same for those with improved access as well. | N/A | N/A | 0 | 0 | 0 | 0 | With the Network Build in it's infancy with regards to construction, and service not yet initiated, no subscribers have received service. Progress is anticipated on this milestone as the project proceeds throughout the year. | This milestone narrative would be the same as above. | This milestone narrative would mirror what was stated in 'Total subscribers served' above. | None at this stage in the construction phase. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this stage in the project timeline. | FALSE | N/A | A significant amount of construction activities will be taking place throughout the State with projects underway in the east side and southwest portions of Washington. Job growth through these activities will continue to build as we award additional construction contracts and add segments of the project slated for construction this quarter. | Northwest Open Access Network | An overly aggressive Baseline projection coupled with unanticipated challenges with cultural clearance and easement acquisition created an on going challenge as it relates to measuring performance to the metrics originally forecasted. | Approval of the In Kind asset valuation is anticipated to occur in this quarter. Any assistance with expediting the process would be greatly appreciated.
NT10BIX5570047 | 2011 | Q3 | Q3 - 2011 | Construction was a primary focus and accomplishment over the third quarter time-frame. During the quarter, 175 miles of conduit and aerial miles were constructed, with accelerated production from multiple aerial, plow, and bore crews working statewide. Continuous permitting, Tribal approval, rights-of-way acquisition and bidding of the remaining segments were another focus for NoaNet and their Sub Recipients as we wind down this activity of the project. In Kind assets were attributed to the project to bring the percentage of Match Funds to Grant Funds in line with projections. | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 3 | Noanet, due to delayed delivery of fiber, is aggressively building conduit miles for fiber delivery in February of 2012. At the end of this reporting period NoaNet has successfully constructed 125 conduit miles. Combined, over 175 miles of aerial fiber, buried fiber, and conduit have been placed. Initial Baseline Projections had construction and Network Build components of the project starting in the third quarter of the project life cycle. All available resources within the time frame allowed will be utilized to insure completion and attainment of Baseline metric by quarter four of year two in the project. | N/A | N/A | N/A | See narrative under 'New network miles deployed' above. | Original projections indicated that the "build" would have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. The wireless links will be incorporated into the project during quarter three 2012. | Original projections indicated that the "build" would have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. The one new tower slated for the project will have a completion date in 2012. The additional six towers referred to in the Baseline are collocations and will be brought online with completion of the project. | Original projections indicated that the "build" would have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. | 43 | 1 | 20 | The 43 signed agreements referred to above are comprised of 36 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and seven (7) new agreements in the past five quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no wholesale services being provided as part of the construction of the project. Once service is turned up and able to allow for wholesale service, this metric will be reported. | Sub Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave, Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Network drawings have been previously submitted. | 3 | 1 | 0 | 4 | As was indicated in previous metrics, construction of the network build will allow for wholesalers to connect and offer service as was planned. This metric will progress and exceed projections in the following quarter. | As was indicated in previous metrics, construction of the network build will allow for wholesalers to connect and offer service as was planned. This metric will progress and exceed projections in the following quarter. | N/A | 10Mbps, 30Mbps, 50Mbps, 100Mbps, 1Gig, 10 Gig 2-10Mbps, 1-30Mbps, and 1-100Mbps | 4 | 3 | 1 | 4 | Initial connections to Community Anchor Institutions began to take place this quarter. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed timeframe. | See narrative above. | See narrative above. | 2-10Mbps, 1-30Mbps, and 1-100Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Continued construction activities will be the focus for the next quarter along with completion of the Network Design and substantial completion of Rights of Way and permitting. Additional sites will be reached and services turned up as we progress on construction of routes throughout the state. Sub Recipient projects will continue to progress as we approach completion of the second year of the three year time frame. Key indicator projections for the end of this quarter are provided below (cumulative): New Network Miles Deployed- Buried-314 Aerial-219 Total-533 New Network Miles Leased-N/A Total CAI Subscribers Served (CAI's Connected)- 10 Number of Signed agreements with broadband wholesale or last mile providers- 44 | Northwest Open Access Network | An aggressive Baseline projection coupled with unanticipated challenges with cultural clearance and easement acquisition have created an on going challenge as it relates to measuring performance to the metrics originally forecasted. With delays in fiber shipments until February of 2012, Northwest Open Access has pursued an aggressive approach to putting in conduit and accomplished over 175 miles of conduit and fiber installation. With this reporting period we are seeing much higher weekly production with over a dozen crews working statewide. We understand the issues surrounding this is beyond NTIA's control, but any assistance that can be provided would be greatly appreciated. | Unfavorable weather may hamper construction progress and will be considered as we plan into future quarters. With delays in fiber shipments until February of 2012, Northwest Open Access has pursued an aggressive approach to putting in conduit. We understand the issues surrounding this is beyond NTIA's control, but any assistance that can be provided would be greatly appreciated.
NT10BIX5570047 | 2011 | Q4 | Q4 - 2011 | The fourth quarter of 2011 continued to focus on construction activities. Fiber deployment continues to be a major initiative as we strive to overcome some of the lag in original baseline forecasting. Additional permitting and Right of Way acquisition continues as we finalize remaining routes and prepare for remaining construction contracts to be awarded. Sub Recipient participation and activity continues to ramp up as we approach the final project year. | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 5 | NoaNet, due to delayed delivery of fiber, is aggressively building conduit miles for fiber delivery scheduled for February of 2012. At the end of this reporting quarter 120 miles of fiber and 300 conduit miles have been placed for a total of 420. | N/A | N/A | N/A | See narrative under 'New Network Miles Deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Due to unanticipated delays associated with environmental, permitting, and easement processes, wireless links are projected to be incorporated during Q3 of 2012. | Original projections indicated that the "build" of new towers would have been higher than current actuals and is delayed due to unanticipated timing of environmental approval, permitting, and easement processes. Tower placement in NW-1 is currently in jeopardy with permitting dependant upon approval from Federal Agencies. The one additional new tower slated for the SW-1 is being replaced with wet cable placement as outlined in EA Addendum 2. Additional tower sites are projected for completion in quarter three of 2012. | Original projections indicated that this "build" metric would have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. Current projections indicate this metric will meet Baseline projections in quarter three of year three. | 43 | 1 | 20 | The 43 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start date pre-dating the Broadband Technology Opportunities Program award and seven (7) new agreements in the past seven quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously Provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Network drawings have been previously submitted. | 3 | 1 | 0 | 4 | One existing service provider is predominantly the Broadband Wholesale provider for the recent additions to new service locations in the network. Current projections indicate this metric to meet Baseline projections in quarter three of year three of the project. | See Narrative above. | N/A | 2-10 Meg, 1-30 Meg, and 1-100 Meg | 8 | 7 | 1 | 8 | Initial connections to Community Anchor Institutions began to take place last quarter. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections indicate this metric to be attained in quarter three of year three of the project. | See narrative above under 'Total Subscribers Served'. | See narrative above under 'Total Subscribers Served'. | 6-10Mbps. 1-30Mbps, and 1-100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Construction and additional miles of deployed Fiber will be the emphasis again this next quarter as we complete the second year of the project life cycle. These numbers are cumulative project to date. New Network Miles Deployed (Fiber Only)- Total 420 New Network Miles Leased N/A Total CAI Subscribers Served (CAI's Connected)- 21 Number of Signed Agreements with Wholesale or Last Mile Providers- 46 | Northwest Open Access Network | An aggressive Baseline projection coupled with unanticipated challenges with cultural clearance and easement acquisition, has created an ongoing challenge as it relates to measuring performance to the metrics originally forecasted. With delays in fiber shipments until February 2012, Northwest Open Access Network has pursued an aggressive approach to putting in conduit and accomplished over 300 miles of conduit and 120 miles of fiber. Although some slowdown with the weather has occurred in the fourth quarter, construction continues at a rapid pace. | Unfavorable weather may hamper construction progress yet during this quarter, but will be considered when planning for 2012. With delays in fiber shipment until the middle of this quarter, Northwest Open Access Network is pursuing an aggressive approach to installing conduit. We understand the issues surrounding this is beyond NTIA's control, but any assistance would be greatly appreciated.
NT10BIX5570047 | 2012 | Q1 | Q1 - 2012 | The first quarter of 2012 saw continued progress in route construction and moving toward completion with fiber pulls and splicing being a new construction activity on NoaNetâ€™s projects. NoaNetâ€™s team is collaborating with the NTIA-BTOP program on any additional modifications required to complete the remaining, unfinished routes. Sub Recipient projects continued to move ahead with construction related activities and progress towards completing routes. Sub-recipient routes were substantially completed in Clallam and Franklin Counties with Anchor Institution implementations to follow. Final permitting and easement acquisition is being completed for routes scheduled for construction during the remainder of the year. Project Team meetings and sub-recipient meetings continue to take place to assure compliance, monitor project budget and scope. NoaNet has had much success working with the BTOP Program Team on reporting, cultural coordination and route modification processes. The team continues to progress towards connecting Community Anchor Institutions as routes are completed and equipment is installed. | 472 | 0 | 0 | 0 | 472 | 0 | 0 | 17 | NoaNet has been aggressively blowing in fiber with recent shipments arriving as scheduled. An aggressive project schedule for the remainder of the time frame will allow for completion according to the BTOP guidelines. Projections are to meet this metric in Q4 2012 of the project timeline. | N/A | N/A | N/A | See narrative under 'new network miles deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Due to unanticipated delays associated with environmental, permitting, and easement processes, wireless links are projected to be incorporated during Q3 of 2012. | Original projections indicated that the "build" of new towers would have been higher than current actuals and is delayed due to unanticipated timing of environmental approval, permitting, and easement processes. Tower placement in NW-1 is currently in jeopardy with permitting dependant upon approval from Federal Agencies. The one additional new tower slated for the SW-1 is being replaced with wet cable placement as outlined in EA Addendum 2. Additional tower sites are projected for completion in quarter three of 2012 and work has begun on SC3 tower at Diamond Lake. | Original projections indicated that this "build" metric would have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. Current projections indicate this metric will meet Baseline projections in quarter three of 2012. | 45 | 1 | 20 | The 45 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technology Opportunities Program award and eleven (11) new agreements in the past eight quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names with out prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 4 | 1 | 0 | 5 | One existing service provider is predominantly the Broadband Wholesale provider for the recent additions to new service locations in the network. Current projections indicate this metric to meet Baseline projections in quarter three of 2012. | See narrative above. | N/A | 3-10 Meg, 1-30 Meg, and 1-100 Meg | 15 | 12 | 3 | 15 | Initial connections to Community Anchor Institutions began to take place over the last two quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections indicate this metric to be attained in quarter three of 2012. It should be noted that per instructions received from the Program Office after submission of the last PPR and APR, there was an error in reporting of CAI's. A Round 2 Community Anchor Institution was inadvertently listed as a Round 1 CAI in the last quarterly report. Steps to eliminate this type of error going forward have been implemented to include furnishing an updated list by award to each member of the reporting team. In addition, the listed CAI's are cross checked by both NoaNet and the consultant team to verify correct placement on the respective report. | See narrative above under 'total subscribers served' above. | See narrative above under 'total subscribers served' above. | 7-10 Meg, 1-30 Meg, 7-100 Meg, 0-1 Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project life cycle. | FALSE | None | Next quarter plans are focused on continued construction of routes scheduled for completion, connecting to additional Community Anchor Institutions and completion of all necessary permits and Right of Ways to complete the project. The metric below are forecasts through quarter two and cumulative project to date: New Network Miles Deployed-632 New Network Miles Leased- N/A Total CAI Subscribers Served (CAI's Connected)-29 Number of Signed Agreements with Wholesale or Last Mile Providers-46 | Northwest Open Access Network | The continued lag in Baseline projection to actual along with unanticipated cultural and easement issues, has created some challenges as it relates to measuring performance. With fiber shipments arriving in this quarter, Northwest Open Access Network is aggressively blowing in fiber and will continue to build at a rapid pace in order to make up this shortfall. | None are anticipated at this time.
NT10BIX5570047 | 2012 | Q2 | Q2 - 2012 | The second quarter of 2012 saw continued progress in route construction and moving toward completion with fiber pulls and splicing being a new construction activity on NoaNet's projects. NoaNet's engineering team is in the process of implementing the optical equipment on portions of Route SW-2, and all of EC routes. NoaNet's team is working collaboratively with the NTIA-BTOP program on any additional modifications required to complete the remaining, unfinished routes. NoaNet is also working with the Program Office on an Anchor Institution adjustment to recognize those that have been re-scoped due to office move or agency office no longer existing, or rescoping of route SW-4. Sub-recipient routes are substantially completed in Blackrock's NC-1, Clallam and Franklin Counties with Anchor Institution implementations to follow. Final permitting and easement acquisition is being completed for routes scheduled for construction during the remainder of the year. Project Team meetings and subrecipient meetings continue to take place to assure compliance, and monitor project budget and scope. NoaNet has had much success working with the BTOP Program Team on reporting, cultural coordination and route modification processes. The team continues to progress towards connecting Community Anchor Institutions as routes are completed and equipment is installed. The A-133 audits for Public Entities are in process and single audits for "For Profit" sub recipients. Lastly, NoaNet is working closely with one sub-recipient to complete the covenant filings, then we will revise already developed guidance to reflect lessons learned in the first covenant submittal to assure that all sub-recipients file covenants efficiently and appropriately. | 588 | 0 | 0 | 0 | 588 | 3 | 1 | 31 | NoaNet has been aggressively blowing in fiber with recent shipments arriving as scheduled. An aggressive project schedule for the remainder of the time frame will allow for completion according to the BTOP guidelines. Projections are to meet this metric in Q4 2012 of the project timeline. | N/A | N/A | N/A | See narrative under 'new network miles deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Due to unanticipated delays associated with environmental, permitting, and easement processes, wireless links are projected to be incorporated during Q3 of 2012. | Original projections indicated that the "build" of new towers would have been higher than current actuals and is delayed due to unanticipated timing of environmental approval, permitting, and easement processes. Tower placement in NW-1 is currently in jeopardy with permitting dependant upon approval from Federal Agencies. The one additional new tower slated for the SW-1 is being replaced with wet cable placement as outlined in EA Addendum 2. Additional tower sites are projected for completion in quarter three of 2012 and work has begun on SC3 tower at Diamond Lake. | Original projections indicated that this "build" metric could have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. Current projections indicate this metric will meet Baseline projections in quarter three of 2012. | 48 | 1 | 20 | The 48 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 14 (fourteen) new agreements in the past nine quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names with out prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 5 | 1 | 0 | 6 | One existing service provider is predominantly the Broadband Wholesale provider for the recent additions to new service locations in the network. Current projections indicate this metric to meet Baseline projections in quarter four of 2012. | See narrative above. | N/A | 4-10 Meg, 1-30 Meg, and 1-100 Meg | 17 | 14 | 3 | 17 | Initial connections to Community Anchor Institutions began to take place over the last two quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections indicate this metric to be attained in quarter three of 2012. | See narrative above under 'total subscribers served' above. | See narrative above under 'total subscribers served' above. | 9-10Meg, 1-30Meg, 7-100Meg, 0-1Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Next quarter continues to focus on route construction that remains for NoaNet as well as Sub Recipients, Community Anchor Institution connections, and testing of the network. The metrics below are forecasting progress through the third quarter of 2012: New Network Miles Deployed- 750 New Network Miles Leased-N/A Total CAI Subscribers Served- 53 Number of Signed Agreements with Wholesale Providers or Last Mile Providers-49 | Northwest Open Access Network | The continued lag in Baseline projection to actual along with unanticipated cultural and easement issues, has created some challenges as it relates to measuring performance. With fiber shipments arriving in the first and second quarter, Northwest Open Access Network is aggressively blowing in fiber and will continue to build at a rapid pace in order to make up this shortfall. | None at this time in the project lifecycle.
NT10BIX5570047 | 2012 | Q3 | Q3 - 2012 | The third quarter of 2012 continues to see completion of construction on routes and connections to Community Anchor Institutions being made. Progress is being made on closeout activities associated with completed routes and NTIA required procedures. Weekly project meetings are being held in a collaborative environment in which all team members involved in the planning, project management and oversight keep abreast of the project status. Sub recipient monitoring continues for those projects or portions of routes left to build or still in process. Sub-recipient routes fully closed include SE-1, SC-2, NW-1 Sequim to Blyn, NC-1 and EC-6. NoaNet routes SE-3 and SW-4 also closed out in this period. In addition, NoaNet routes SW-2, EC-2,3,4 and 5 are also closed out. Routes EC-1, SE-2, SW-1 and SC-3 are in final clean up with less than 10-miles in aggregate to complete. Collocation facilities are being prepped for lighting of remaining routes in the last quarter of 2012. | 704 | 0 | 0 | 0 | 704 | 3 | 1 | 31 | NoaNet has been aggressively working on completion of remaining routes. An aggressive project schedule for the remainder of the time frame will allow for completion according to the BTOP guidelines. Projections are to meet this metric in Q4 2012 of the project timeline. | N/A | N/A | N/A | See narrative under 'new network miles deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Due to unanticipated delays associated with environmental, permitting, and easement processes, wireless links were completed during Q3 of 2012. | Original projections indicated a higher quantity than current actuals. Completion has been delayed due to unanticipated timing of environmental approval, permitting, and easement processes. Tower placement in NW-1 will not be completed as previously planned due to permitting issues. The one additional new tower slated for the SW-1 is being replaced with an undersea cable as outlined in EA Addendum 2. The tower on route (SC3) at Diamond Lake has been completed. | Original projections indicated that this "build" metric could have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. Current projections indicate this metric will meet Baseline projections in quarter three of 2012. | 49 | 1 | 20 | The 49 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 15 (fifteen) new agreements in the past ten quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names with out prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 5 | 1 | 0 | 6 | One existing service provider is predominantly the Broadband Wholesale provider for the recent additions to new service locations in the network. Current projections indicate this metric to meet Baseline projections in quarter four of 2012. | See narrative above. | N/A | 4-10 Meg, 1-30 Meg, and 1-100 Meg | 29 | 26 | 3 | 29 | Initial connections to Community Anchor Institutions began to take place over the last two quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections indicate this metric to be attained in quarter three of 2012. | 14 Last time BL 46--See narrative above under 'total subscribers served' above. | 3 Last time BL 70--See narrative above under 'total subscribers served' above. | 21-10 Meg, 1-30 Meg, and 7-100 Meg, 0-1Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | This quarter, Q4 2012, is the final remaining full quarter for the project timeline. Final construction of routes will be taking place with fiber splicing, testing and closeout activities being the significant tasks being performed. Remaining Community Anchor Institutions where we were able to achieve a Right of Entry or Service Order will be connected, additional equipment turned up, and as built drawings completed. New Network Miles Deployed- 790 New Network Miles Leased-N/A Total CAI Subscribers Served- 57 Number of Signed Agreements with Wholesale Providers or Last Mile Providers-50 | Northwest Open Access Network | None at this time. | None at this time.
NT10BIX5570047 | 2012 | Q4 | Q4 - 2012 | The fourth quarter of 2012 saw additional segments of the network completed from the construction standpoint. Closeout activities associated with routes, Federal Interest filings, and other documentation took place as we approach the final phase of the project. Approvals for CAI In-Fill Requests #1 and #2 were received allowing for expansion of the number of Community Anchor Institutions that are reached with this project. The Closeout Team is working diligently to insure all necessary routes are closed out according to the BTOP guidelines and all necessary support material is in place. Virtually all backbone and ground disturbing activity has been completed with additional optical equipment being connected and tested. | 750 | 0 | 0 | 0 | 750 | 3 | 1 | 60 | Final network build will be completed in January of 2013. Around 40 miles remained to complete as of the end of December 2012. | N/A | N/A | N/A | See narrative under 'New network miles deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Due to unanticipated delays associated with environmental, permitting, and easement processes, wireless links were completed during Q3 of 2012. | Original projections indicated a higher quantity than current actuals. Completion has been delayed due to unanticipated timing of environmental approval, permitting, and easement processes. Tower placement in NW-1 will not be completed as previously planned due to permitting issues. The one additional new tower slated for the SW-1 is being replaced with an undersea cable as outlined in EA Addendum 2. The tower on route (SC3) at Diamond Lake has been completed. | Original projections indicated that this "build" metric could have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be available as fiber routes are placed and services are turned up throughout the life of the project. | 49 | 1 | 20 | The 49 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 15 (fifteen) new agreements in the past eleven quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names with out prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 15 | 34 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 8-10 Meg, 25-100 Meg, 9-1 Gig and 7-10 Gig | 62 | 58 | 4 | 62 | Initial connections to Community Anchor Institutions began to take place over the last three quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections and intent is this metric will be attained at the end of the Grant Period. | See narrative above under 'Total Subscribers Served'. | See narrative above under 'Total Subscribers Served'. | 51-10 Meg, 1-30 Meg, 10-100 Meg, and 0-1Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | The project is slated to end in this quarter with all final closeout activities taking place in the second quarter of 2013. All closeout activities will be taking place during this phase of the project. Additionally, NoaNet will be working on the approved In-Fill request #1 and #2 which consists of of connecting to Community Anchor Institutions where a right of entry or service order has not been acquired. Projected Metrics for end of quarter are noted below: New Network Miles to be Deployed- 789 New Network Miles Leased-N/A Total CAI Subscribers Served-123 Number of Signed Agreements with Wholesalers or Last Mile Providers-50 | Northwest Open Access Network | None as the project is nearing completion. | None anticipated at this time.
NT10BIX5570047 | 2013 | Q1 | Q1 - 2013 | The first quarter of 2013 activity continued to be centered on construction of fiber laterals, equipment installation of CPEâ€™s and UPS and turn up of circuits to approved Community Anchor Institutions (CAIâ€™s) and closeout activity associated with the project. The close out activities included but not limited to final billing from vendors, reconciling of construction contracts, Federal Interest Filings and all required paperwork. The Closeout Team is working diligently to insure all necessary routes are closed out according to the BTOP guidelines and all necessary support material is in place. All documentation and closeout forms will be completed and furnished to NTIA during the closeout period. Metrics Achieved this past Quarter: Miles Deployed-30 New Network Miles Leased-N/A CAI's Connected-35 Broadband Wholesale or Last Mile Providers-0 | 780 | 0 | 0 | 0 | 780 | 3 | 1 | 113 | Final network build was completed in January of 2013. | N/A | N/A | N/A | See narrative under 'New network miles deployed' above. | Original projections indicated that the project would have been further along than currently reporting. Wireless links were completed during Q3 of 2012. | Original projections indicated a higher quantity than current actuals. The tower on route (SC3) at Diamond Gap has been completed. The additional towers originally planned were not part of the final design. | Original projections indicated that this "build" metric could have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, and easement processes. Interconnection points will be finalized as remaining Community Anchor Institutions are connected. | 49 | 1 | 20 | The 49 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 15 (fifteen) new agreements in the past twelve quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names with out prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the state of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub-Recipients: Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 15 | 34 | 0 | 4 | Exceeding Baseline | Exceeding Baseline | N/A | 8-10 Meg, 25-100 Meg, 9-1 Gig and 7-10 Gig | 97 | 92 | 5 | 97 | Initial connections to Community Anchor Institutions began to take place over the last three quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections and intent is this metric will be attained at the end of the Grant Period. | See narrative above under 'Total Subscribers Served'. | See narrative above under 'Total Subscribers Served'. | 86-10 Meg, 1-30 Meg, 10-100 Meg, and 0-1Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | As the project nears final completion, remaining activities are limited to closeout activities, final reporting and reconciliation of accounts for final payments. All necessary reporting and documents required as part of the project closeout are in process of being completed and submitted when required. Community Anchor Institution connections will continue as previously indicated in the No Cost Extension Request. Projected Metrics this Quarter: New Network Miles to be Deployed- 3 New Network Miles Leased-N/A Total CAI Subscribers Served-52 Number of Signed Agreements with Wholesalers or Last Mile Providers-1 | Northwest Open Access Network | The challenges that NoaNet faced during Q1 2013 was completing construction due to weather conditions and restrictions. Q1 is a winter quarter and it is extremely difficult to construct fiber due to hazard conditions. Construction of fiber backbone and laterals require heavy road travel by large equipment on unsafe road conditions. Most permits restrict travel by large equipment on roads due to the potential road damage. This created delay in fiber construction. In addition to weather conditions NoaNet has faced many challenges in providing service to CAIâ€™s. NoaNet is a Wholesale entity and cannot enter into telecommunications agreements with end users and we must sell to authorized Service Providers. This requires NoaNet to rely on the Service Provider to acquire Service Orders which provides NoaNet the authorization to enter the building. If this cannot be acquired then NoaNet must receive a legal Right of Entry from the building owner. This process has been challenging and delayed progress on CAI interconnection. | NoaNet continues to face challenges in acquiring Service Orders from Service Providers and/or legal Rights of Entry to install fiber to targeted CAIâ€™s. NoaNet is hyper focused on this effort and will continue to extend fiber connections to committed CAIâ€™s as agreements are received.
NT10BIX5570047 | 2013 | Q2 | Q2 - 2013 | The second quarter of 2013 activity continued to center on closeout and turn up of circuits to approved Community Anchor Institutions (CAI's). The close out activities included but not limited to final billing from vendors, reconciling of construction contracts, Federal Interest Filings and all required paperwork. The Closeout Team is working diligently to insure all necessary routes are closed out according to the BTOP guidelines and all necessary support material is in place. All documentation and closeout forms will be completed and furnished to NTIA during the closeout period. Metrics Achieved this past Quarter: Miles Deployed-0 New Network Miles Leased-N/A CAI's Connected-23 Broadband Wholesale or Last Mile Providers-1 | 780 | 0 | 0 | 0 | 780 | 3 | 1 | 136 | Exceeding Baseline. | N/A | N/A | N/A | Exceeding Baseline. | Original projections indicated that the project would have been further along than currently reporting. Wireless links were completed during Q3 of 2012. | Original projections indicated a higher quantity than current actuals. The tower on route (SC3) at Diamond Gap has been completed. The additional towers originally planned were not part of the final design. | Original projections indicated that this "build" metric could have been higher than current actuals and is due to unanticipated delays associated with environmental, permitting, ad easements processes. Interconnection points will be finalized as remaining Community Anchor Institutions are connected. | 50 | 0 | 20 | The 50 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 16 (sixteen) new agreements in the past thirteen quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Priveleged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application servic providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o of Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 16 | 34 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 9-10 Meg, 25-100 Meg, 9-1 Gig and 7-10 Gig | 120 | 112 | 8 | 4 | Initial connections to Community Anchor Institutions began to take place over the last three quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Current projections and intent is this metric will be attained at the end of the Grant Period. | See narrative above under 'Total Subscribers Served'. | See narrative above under ' Total Subscribers Served'. | 109-10 Meg, 1-30 Meg, 10-100 Meg and 0-1 Gig. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Remaining invoices and approval/payment of the same will take place as well as any remaining Community Anchor Institution connections. Closeout activities will continue as we enter the final quarter of the No Cost Extension previously granted. Projected Metrics this Quarter: Miles Deployed-0 Negligible New Network Miles Leased-N/A CAI's Connected-76 Broadband Wholesale or Last Mile Providers-1 | Northwest Open Access Network | A challenge is working with the CAI's to achieve right of entry or a signed service order to insure those are completed in the final quarter of the extended project timeframe. | Connection to as many as possible remaining Community Anchor Institutions may be a challenge as we move in to the final quarter of the project. Coordination and administration of sub recipient final invoicing and closeout documentation will be challenging due to the volume of Sub Recipient projects requiring compliant closeout. NoaNet may reach out to the Program for assistance during this process.
NT10BIX5570047 | 2013 | Q3 | Q3 - 2013 | Northwest Open Access Network continued it's aggressive focus on connecting Community Anchor Institutions this past quarter. Metrics Achieved This Past Quarter: Miles Deployed-0 (Negligible) New Network Miles Leased-N/A CAI's Connected-42 Broadband Wholesale or Last Mile Providers-0 See attachment regarding project narrative. | 780 | 0 | 0 | 0 | 780 | 3 | 1 | 136 | This is the final metric for this category. The initial plan indicated routes and projects with cumulative miles of 830 as indicated in our application. As engineering and other planning and revisions were done over the early stages of development, phases or segments were eliminated or re-routed to avoid overbuild of other carrier fiber networks or due to unforeseen circumstances. As a result, the mileage metric for this project did not meet early projections, but additional CAI's were connected with the miles built. This shortfall was in part due to NoaNet and Sub Recipient projects combined, particularly in the NW-1 and SW-4 routes. | N/A | N/A | N/A | This is the final mileage metric for this project. See Above. | All wireless links have previously been completed for the project. | Initial projections had indicated more towers, but the final design included only the tower at Diamond Gap and that was completed in a previous quarter. | This is the final for this metric. | 50 | 0 | 20 | The 50 signed agreements referred to above are comprised of 34 pre-existing wholesale customers of NoaNet with Agreement start dates pre-dating the Broadband Technologies Opportunity Program award and 16 (sixteen) new agreements in the past fourteen quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Priveleged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub- Recipients: Sawnet, c/o of Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Network drawings have been previously submitted. | 16 | 34 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 9-10 Meg, 25-100 Meg, 9-1 Gig and 7-10 Gig | 152 | 144 | 8 | 4 | Initial connections to Community Anchor Institutions began to take place over the last five quarters. Initial projections had construction and subscribers starting in quarter three of year one. With the delay in construction, permitting and the environmental process, this metric will lag into the final year of the project. The compressed construction schedule will require an accelerated rate of build to meet the allowed time frame. Due to issues with previous quarters in CAI reporting, this metric reflects the actual number connected per the listing previously provided to NTIA. This metric exceeded the original target of connecting 123 CAI's. | See narrative above under ' Total Subscribers Served'. | See narrative above under ' Total Subscribers Served'. | 141-10 Meg, 1-30 Meg, 10-100 Meg and 0-1 Gig. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Closeout activities are the focus and the only remaining item for this quarter. | Northwest Open Access Network | The primary challenge faced last quarter was completion of the Community Anchor Institution connections to remaining sites. This was compounded by the difficulty in receiving rights of entry or service orders for those CAI's as well. | A delay in closeout may be the only possible challenge as we complete the final phase of this project.
NT10BIX5570049 | 2010 | Q3 | Q3 - 2010 | Finalized contract with engineering, design and project management firm; finalized route base mapping, began make ready surveying onsite, coordination with utility for aerial placement. Completed initial environmental consultations, developed EA document; submitted EA document end of August, received NTIA comments late September and began adjustments to document gathering new information to conform to EA document guidelines revised in August; initiated consultation with Corps of Engineers. Continued signal analysis for tower placement, meetings with private property owners for tower placement. Onsite meetings with project team, developed wiki for project task coordination, meetings with local service providers to incorporate needs into design. Began development of RFP for network operator. Met with VDOT and utility to coordinate fiber placement in right of ways, develop an agreed upon make ready work process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No change | N/A | N/A | N/A | No change | No change | No change | No change | 0 | 0 | 0 | No agreements yet | Wholesale services description: No services being provided at this point in the project. | There are no subrecipients in this project. The procurement process to select a network operator began at the end of this quarter with the start to developing the RFP for services. The third party to be selected is expected to serve as a contractor to the County. | 0 | 0 | 0 | 0 | No change | No change | No change | No change | 0 | 0 | 0 | 0 | No Change | No change | No change | No change | 0 | 0 | 0 | 0 | 0 | No change | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | No change | N/A | N/A | N/A | N/A | Project intends to provide high speed middle mile access to providers at speeds up to 1Gbps, and access to community anchor institutions at broadband speeds desired. | FALSE | No changes to plan. | Outside plant make ready assessment should be complete with work to be coordinated with the utility for making changes; minimal make ready work is estimated at this time, and needed changes will be provided to utility as phases of surveying are complete. The RFP process to select a network operator will be finalized and agreement negotiations in process. Right of way access with private property owners will be underway with significant progress expected; route design will be finalized and permitting underway. Anticipate completion of EA. Tower sites will be finalized and agreements with private property owners should be complete. As tower sites are finalized, the public notice process will begin & registration with FCC initiated. The equipment specifications will be in process as will development of required procurement proceedings to negotiate access agreements with private providers. | Nelson, County of | Procurement delays in quarters 1 and 2 have only slightly affected the baseline timeline at this point and we anticipate being back on schedule by end of Qtr 4. The EA guidelines that were followed beginning July 1st to develop the EA were revised in August without notice. The EA comments received in September requests changes to the EA to conform to the August version of guidelines, requiring significant additional work and another consultation. In addition we are still waiting for USFWS to respond to our consultation request. We have met all deadlines imposed for submitting the EA and response to comments, but cannot submit the final EA document until all consultations are complete, estimated currently to occur late October. The prolonged EA process is not impeding progress on other project elements and design is underway and on schedule to catch up with Qtr 4 projections. No BTOP technical assistance is needed at this time. | There are no challenges anticipated at this time. Due to the SHPO electing to utilize a programmatic agreement for Section 106 compliance, all four towers will require submittal to the FCC and a resubmission of EA information. While this has created additional work, this work will be completed concurrent with ongoing network design and engineering tasks and will not affect the overall project progress. No technical assistance from BTOP is anticipated at this time.
NT10BIX5570049 | 2010 | Q4 | Q4 - 2010 | The bulk of easement agreements from property owners were secured. Field make ready assessment is complete and make ready work requirements documented; meetings with pole owners to coordinate make ready work. Network operator and service provider RFPs issued and subcommittee established to review. Continue to work on securing tower sites, meetings with property owners to negotiate access. Meetings with wholesale provider as potential Internet transport agent. Construction RFP development started. Continued to develop network design and equipment specifications. Investigation of potential tower tenants. Network governance documents under development, continued education of and communication with project stakeholders. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No change | N/A | N/A | N/A | No change | No change | No change | No change | 0 | 2 | 0 | Responses to RFP received, negotiations not started. Received responses from Nelson Cable, Stewart Computer Services, Nations Line, Blue Ridge InterNetworks as potential service providers on the middle mile network. | No services being provided at this point. | Response to RFP received, interview scheduled for 1st quarter 2011. Network not constructed. | 0 | 0 | 0 | 0 | No change | No change | No change | No change | 0 | 0 | 0 | 0 | No change | No change | No change | No change | 0 | 0 | 0 | 0 | 0 | No change | No change | No change | No change | No change | 0 | 0 | 0 | 0 | 0 | No change | No change | No change | No change | No change | Project intends to provide high speed middle mile access to providers at speeds of up to 1 Gbps, and access to community anchor institutions at broadband speeds desire. | FALSE | No changes to plan. | Complete ROW easement process, adjust design based on access and finalize make ready requirements for coordination with pole owner. Finalize negotiations with property owners for tower placement and submit applications to FCC. Implement programmatic agreement with NTIA for Section 106 review on towers, finalize EA document for FONSI from NTIA. Negotiate access agreements with service providers. Conduct interview with potential network operator, potentially seek additional candidates. Continue to refine governance documents and review options for interconnection with wholesale bandwidth providers. | Nelson, County of | Finalization of tower sites slowed due to holidays and absent property owners. Final design and make ready engineering dependent upon securing easement access, continue to meet with property owners to explain the process and community benefit. Some owners do not reside in the county and have proven difficult to contact. Nearing completion or cut off of easement process to move design forward. | No challenges anticipated at this time other than what is provided in the narrative for construction permits and approvals. No technical assistance from the BTOP program is anticipated at this time.
NT10BIX5570049 | 2011 | Q1 | Q1 - 2011 | Work on final design for construction RFP continued and meetings held with the electric cooperative regarding make ready work and department of transportation to incorporate changes required. The RFP to select a network operator was reissued to seek a greater number of competitive proposals. The RFP for construction was developed. The final EA document was submitted to NTIA environmental team for FONSI determination. Drawings delivered to VDOT for approval and start of permitting. VMRC contacted for permitting requirements, no water permits necessary. Avon and Afton tower sites solidified, initial agreements with property owners acquired, Sec 106 site analysis completed for FCC application. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance to plan | No variance to plan | No variance to plan | No variance to plan | No variance to plan | No variance to plan | No variance to plan | No variance to plan | 0 | 0 | 0 | No agreements to date. Nelson County anticipated a network operator to have been selected in the first quarter, prior to negotiating and entering into agreements with wholesalers. After receiving only one proposal in response to the RFP, the County elected to modify and re-release the RFP to solicit additional competitive proposals from a wider audience. The second RFP received several proposals with interviews scheduled this month. The County anticipates the selected operator to move forward immediately to assist with negotiations for wholesale providers. The County is accepting quotes for wholesale services currently and continues to seek additional interested firms. | No services being provided at this time; construction has not started. | No network operator selected yet, the RFP for services was rebid in this quarter due to only one viable proposal received from first issue. Six proposals were received in response to the rebid at the end of this quarter; proposal review, interviews and selection is anticipated during the second quarter of this year. | 0 | 0 | 0 | 0 | No variance - construction not started. | No variance - construction not started. | No variance - construction not started. | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Project intends to provide high speed middle mile access to providers at speeds of up to 1 Gbps, and access to community anchor institutions at broadband speeds desired. | FALSE | No changes to plan. | Selection of a network operator is expected which will be incorporated into the final design and equipment specifications. The department of transportation is expected to issue final permitting, and the electric utility expects to be underway with make ready work. A construction contractor is expected to have been selected | Nelson, County of | Completion of the final design, permitting and rights of way have been delayed as a result of working with the department of transportation on permitting in a limited access area. Additionally, the make ready requirements are in review between engineering and the electric utility to further determine the necessity of pole replacements to reduce the initial estimate to more closely align to budget. Progress is being made and construction is still slated to occur during optimum weather conditions. | The materials will have been ordered but there is the potential for longer than normal delivery times for fiber due to several BTOP projects starting at the same time. Make ready work will have been started by the electric utility, but delayed start versus planned. Protracted period of permitting with FCC and state historic resources for two tower sites, local permitting will begin after FCC approval. The third tower site selection has not been finalized but site review continues.
NT10BIX5570049 | 2011 | Q2 | Q2 - 2011 | FONSI received for EA. Afton and Avon tower applications submitted through FCC e106 process and approved. Review of Massies Mill tower site, costs for electric too expensive from utility, looking for additional sites. Completed agreement with VDOT for limited access ROW approval. Design complete pending VDOT approval and agreement with utility for make ready. Performed pole loading calculations using utility methodology for continued make ready discussions. Completed RFP and proposal review for construction contractor and began negotiations with top two respondents. Ordered fiber for project. Finalizing agreements with property owners for tower site lease in advance of local permitting. Entered into discussions with wholesale carrier to lease fiber or conduit access. Continued discussions with candidates for network operation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | No signed agreements at this time, pending selection of network operator prior to developing agreements. | Network not constructed, no services provided at this time | Network operator not yet selected | 0 | 0 | 0 | 0 | Network not constructed | Network not constructed | Network not constructed | Network not constructed | 0 | 0 | 0 | 0 | Network not constructed | Network not constructed | Network not constructed | Network not constructed | 0 | 0 | 0 | 0 | 0 | Network not constructed | Network not constructed | Network not constructed | Network not constructed | Network not constructed | 0 | 0 | 0 | 0 | 0 | Network not constructed | Network not constructed | Network not constructed | Network not constructed | Network not constructed | Project intends to provide high speed middle mile access to providers at speeds of up to 1 Gbps, and access to community anchor institutions at broadband speeds desired | FALSE | N/A | Final design deployment method will be selected, final permit applications submitted for approval, make ready work completed by the utility if necessary and a construction firm under contract and beginning construction. Afton and Avon towers going through local permit process, soil testing to develop bid for turnkey tower construction. Network operator selection to be finalized and contracts in negotiation. | Nelson, County of | High make ready costs precipitated evaluation of design changes from aerial to underground and the impact on project budget and timing. The evaluation includes meeting with VDOT for preliminary feedback and approval for underground construction in ROW to be concluded in July and a design made by the County on deployment method. The process to select a construction contractor continued during the design evaluation but a firm will not be under contract until the design is finalized and all costs confirmed. Fiber was ordered but due to inventory shortages will take longer than normal for delivery. The remaining construction materials will be ordered in Qtr 3 as soon as the deployment method is confirmed. No technical assistance from BTOP is required at this time. Changing deployment technique from aerial to underground requires reinitiating consultation with environmental agencies and amendment to EA. Anticipate receiving approvals and completing EA work in 3rd Qtr. Once construction starts, progress indicators will align more closely with baseline. Challenge continues to be availability of fiber and some materials, all ordered but not yet received. Construction scheduled to start in 3rd Qtr. | The start of construction is dependent upon timely response from VDOT and VMRC for permitting, and additionally from environmental agencies that may need to be reconsulted for deployment changes. Materials have been ordered but not received, and the fiber vendor has missed the expected delivery date with no hard date yet for delivery. We are not expecting delays in VDOT permitting due to working closely with their personnel for preliminary design approvals in areas that may prove problematic. Expecting to start construction in areas cleared by permitting agencies that will not require make ready work. Should areas of the deployment remain aerial, there may be work required by the electric utility that must be completed prior to construction; the utility has indicated they will expedite work but should an unforeseen event occur that requires attention to electric infrastructure, make ready could experience delay.
NT10BIX5570049 | 2011 | Q3 | Q3 - 2011 | Nelson County submitted a project modification request to change fiber construction from primarily aerial to all underground due to high make ready estimate for attaching to utility poles. Working with the Virginia Department of Transportation (VDOT), a redesign was completed and applications for VDOT permitting submitted. Reconsultation with environmental agencies commenced at the end of August for the change to all underground construction. A construction contractor was selected and contracts completed. Fiber, conduit and one-half of vaults were received and staged in the contractor materials storage area. Applications for water crossing permitting were submitted to the Virginia Marine Resources Commission, the Virginia Department of Environmental Quality and the US Corps of Engineers; the required public notice was advertised in September and all affected property owners notified. The Federal Communication Commission environmental review process for two tower sites were completed and findings of No Adverse Affects received for both towers. Tower site leases with two property owners were completed and development of applications for local permitting was initiated. An additional potential tower site in the Massie's Mill area was initially reviewed for line of sight requirements, and further review is warranted. Discussions continued with wholesale providers regarding access to the proposed new middle mile fiber and for parties submitting proposals for network operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance due to delayed construction start. Approximately 2 quarters behind originally planned progress. | N/A | N/A | N/A | Variance due to delayed construction start. Construction will begin in Qtr 4 of 2011, currently only pending EA amendment approval. Approximately 2 quarters behind originally planned progress. | Variance due to delay in finalizing the Massie's Mill tower site. The Colleen tower that will receive equipment is in place, but will not deploy any equipment until both are ready. This item is approximately 3 quarters behind planned progress. | Variance due to delay in receiving tower site environmental clearance, negotiating agreements with property owners and local permitting. Two towers are in the process of local permitting, and soil testing will shortly commence as the precursor to bids for turn key tower construction. Those two towers are approximately 2 quarters behind planned progress. The third tower was not originally planned for completion until Qtr 4 but is approximately 3 quarters behind planned progress. | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Variance due to delayed construction start. Approximately 2 quarters behind originally planned progress. Variance due to delayed construction start. Construction will begin in Qtr 4 of 2011, currently only pending EA amendment approval. Approximately 2 quarters behind originally planned progress. Variance due to delay in finalizing the Massie's Mill tower site. The Colleen tower that will receive equipment is in place, but will not deploy any equipment until both are ready. This item is approximately 3 quarters behind planned progress. Variance due to delay in receiving tower site environmental clearance, negotiating agreements with property owners and local permitting. Two towers are in the process of local permitting, and soil testing will shortly commence as the precursor to bids for turn key tower construction. Those two towers are approximately 2 quarters behind planned progress. The third tower was not originally planned for completion until Qtr 4 but is approximately 3 quarters behind planned progress. Variance due to delayed construction start. Interconnection with providers is not possible until network deployed, approximately 2 quarters behind planned progresss for any variance from the baseline plan or any other relevant information) Variance due to delayed construction start. Approximately 2 quarters behind originally planned progress. Variance due to delayed construction start. Construction will begin in Qtr 4 of 2011, currently only pending EA amendment approval. Approximately 2 quarters behind originally planned progress. Variance due to delay in finalizing the Massie's Mill tower site. The Colleen tower that will receive equipment is in place, but will not deploy any equipment until both are ready. This item is approximately 3 quarters behind planned progress. Variance due to delay in receiving tower site environmental clearance, negotiating agreements with property owners and local permitting. Two towers are in the process of local permitting, and soil testing will shortly commence as the precursor to bids for turn key tower construction. Those two towers are approximately 2 quarters behind planned progress. The third tower was not originally planned for completion until Qtr 4 but is approximately 3 quarters behind planned progress. Variance due to delayed construction start. Interconnection with providers is not possible until network deployed, approximately 2 quarters behind planned progress. | 0 | 1 | 0 | No signed agreements at this time, pending selection of network operator prior to developing agreements. Discussions are continuing with one last mile provider for interconnection and potentially network operation. | Network not yet constructed, no services being provided at this timeo services being provided at this time. | Network operator not yet selected, discussions ensuing with qualified candidates. | 0 | 0 | 0 | 0 | Variance due to delayed construction start and delay in selecting network operator due to necessity to reissue RFP seeking additional candidates. | No variance to baseline estimate | No variance, not proposed on baseline. The County is interested in leasing dark fiber but no solid candidates at this time. | Network not constructed, no services provided at this time. | 0 | 0 | 0 | 0 | Variance due to delayed construction start. Network not constructed, no services provided at this time. | Variance due to delayed construction start. Network not constructed, no services provided at this time. | Variance due to delayed construction start. Network not constructed, no services provided at this time. | Network not constructed, no services provided at this time. | 0 | 0 | 0 | 0 | 0 | Variance due to delayed construction start. Network not constructed, no services provided at this time. | N/A | N/A | N/A | Network not constructed, no services provided at this time. | 0 | 0 | 0 | 0 | 0 | Variance due to delayed construction start. Network not constructed, no services provided at this time. | N/A | N/A | N/A | Network not constructed, no services provided at this time. | Project intends to provide high speed middle mile access to providers at speeds of up to 1 Gbps and access to community anchor institutions at broadband speeds desired. | FALSE | No change to plan | The County expects to have all construction permits in hand, as well as approval of the environmental project modification that has been submitted to NTIA for final review. The construction of the all underground network will be in progress. Local tower permitting will have been completed for two towers, and final selection of the third tower is expected to have been made and negotiations in process with the property owner. The majority of outside plant construction materials will have been ordered and received. Soil testing for two towers will have been completed and preparation of turn key tower bids will commence during this quarter. Additionally, an update on the progress of project key indicators is as follows: a. New network miles deployed: 4 miles projected to be completed by end of December 2011, variance due to delayed start of fiber construction and Department of Transportation limits on construction around holiday periods. b. New network miles leased: 0, No Variance to baseline c. Total CAI subscribers served (CAIs connected): 0, Variance due to delayed start of fiber construction. No CAIs can be served until the network is complete. Completion of network includes fiber construction and equipment deployment and testing expected to be concluded by Qtr2 of 2012. d. Number of signed agreements with broadband wholesalers or last mile providers: 1, Variance due to delay in selecting a third party Network Operator and delay in start of fiber construction. | Nelson, County of | High make ready cost estimates for aerial construction necessitated a complete network redesign to all underground and varying VDOT requirements prolonged that process significantly. There was additional work involved in consultation with environmental agencies for project modification approval not required during the original assessment, and Virginia Department of Historic Resources further requested third party archaeological review that resulted in additional unplanned expenditures and time. Water permitting with Virginia regulatory authorities was delayed due to agency staffing shortages. | Nelson County has finally moved past the significant impediments to starting construction. With the redesign complete, VDOT permitting complete, contractor negotiation and contract complete, fiber received and materials staged and a FONSI expected for the EA amendment, construction is ready to begin in the 4th quarter. At this time the County does not anticipate delays that would prevent it from achieving the progress projected going forward.
NT10BIX5570049 | 2011 | Q4 | Q4 - 2011 | The County continued to review tower sites in the Massies Mill area. Tower sites in Afton and Avon cleared environmental review and began local permitting. The Avon site was approved but an alternate site for Afton was requested. The environmental review was completed for a tower at the fire department about 2500 feet south. Local permitting was completed for the alternate tower and awaits Board of Supervisors approval. Work continued to finalize the construction design. A project modification for the all underground construction was approved by the grants office and re-consultation with environmental agencies was conducted and concluded with findings of no adverse effect. All permitting was concluded. A materials order was placed, fiber order received, and a contract executed for construction. Construction began in December. 2,364 feet of conduit was installed by the end of the year. Inspection protocols were developed and a full time inspector assigned to the project. A website was developed for communication between construction and project management personnel. Planning meetings were held to review operations, business planning and development of policies and procedures. Meetings were held with providers to explore interest in offering services over the network, interconnection of facilities, and delivery of wholesale Internet. Economic development officials kicked off a public relations effort to notify businesses of the start of construction and to increase awareness of the broadband project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The start of construction was delayed approximately 6 months due to a redesign and protracted permitting process with the Virginia Department of Transportation. Installation of less than 1 mile (.45 of a mile) of conduit was completed by the end of the year. Work restrictions around the December holidays and significant rain slowed the construction process considerably. | N/A | N/A | N/A | The start of construction was delayed approximately 6 months due to a redesign and protracted permitting process with the Virginia Department of Transportation. Less than 1 mile (.45 of a mile) of construction was completed by the end of the year. Work restrictions around the December holidays and significant rain slowed the construction process considerably. | Variance due to delay in finalizing the Massies Mill tower site. The Colleen tower that will receive equipment is in place, but no equipment can be deployed until both towers are ready. This item is approximately 3 quarters behind planned progress. | Variance due to delay in receiving tower site environmental clearance and completing the local permitting process. One of three towers received local permit approval, approval on a second site is anticipated in the next quarter, and a third site is still under review. Follow on pre construction tasks will be performed when review and permitting is complete for all towers to limit additional expenses for multiple site visits to perform like tasks. | Construction just beginning, no circuits completed between interconnection points. | 0 | 1 | 0 | No signed agreements at this time. Previous discussions with a wholesale internet provider stalled due to a corporate shifting of attention following an acquisition made by the provider but resumed again at the end of December. New quotes for service are expected in Qtr 1 2012 that are expected to result in an agreement for wholesale service delivery to the network operating center. | The network is under construction and no services are being provided at this time. | A network operator has not been selected at this time, though discussions are ensuing with qualified candidates. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Access not possible until significant network segments are completed and connected to the network operating center. | Variance due to network construction lagging projections by approximately 6 months. Access not possible until significant network segments are completed and connected to the network operating center. | No variance, not included in baseline projections. The County is interested in leasing dark fiber but no solid candidates at this time. | Variance due to network construction lagging projections by approximately 6 months. Network not constructed, no services available at this time. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until the fiber segments and network testing is complete. Anticipate last mile service equipment to be deployed in Qtr 2 2012. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until the fiber segments and network testing is complete. Anticipate last mile service equipment to be deployed in Qtr 2 2012. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until the fiber segments and network testing is complete. Anticipate last mile service equipment to be deployed in Qtr 2 2012. | Variance due to network construction lagging projections by approximately 6 months. Less than 1 mile of construction completed in this quarter, no services available at this time. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Less than 1 mile of construction completed in this quarter. | N/A | N/A | N/A | N/A: services will be offered by last mile providers after construction is complete. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Less than 1 mile of construction completed in this quarter. | N/A | N/A | N/A | N/A: services will be offered by last mile providers after construction is complete. | The project intends to provide high speed middle mile access to private providers at speeds of up to 1 Gbps and access to community anchor institutions at broadband speeds desired. | FALSE | No change to management plan at this time. | Construction is expected to continue on schedule with approximately 80 percent of the fiber network construction completed by the end of the next quarter. A request for proposals for network equipment will be released and vendor proposals under review. Formal surveying and soil testing at the Afton and Avon tower sites will occur to develop specifications for tower construction. A third tower site in the Massies Mill area will be selected and under review. A decision to select a network operator will have been made, an agreement for wholesale internet reached and agreements with last mile service providers will be in development. Additionally, accomplishments towards key project indicators are projected as follows: A. New Network Miles Deployed: 16 miles projected to be completed at the end of the next quarter. Variance to baseline due to delayed construction start of approximately 6 months. B. New Network Miles Leased: 0 miles, no variance, N/A. C. Total CAI Subscribers Served (CAIs connected): 0, Variance due to delayed construction start of approximately 6 months. No CAIs can be served until the network is complete. Completion of the network includes fiber construction and equipment deployment and testing expected to be concluded by the end of Qtr 2 of 2012. D. Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 1, variance due to delay in construction start and restarting of negotiations for wholesale internet due to a provider acquisition and name change. Expect to finalize agreement with a wholesale internet provider and agreements will be in development with two last mile providers. | Nelson, County of | Construction was delayed approximately 6 months due to a redesign of the network to avoid high make ready costs. Approval of two of the three tower sites did not proceed according to schedule due to citizen requests to find one alternative site and to adjust the placement of the tower and access road on the other site, resulting in additional environmental and permitting work. Construction of the fiber network did begin with locates in November and ground breaking in December, but the Virginia Department of Transportation restriction on work during holiday periods and significant rain slowed the progress of construction. Delays due to availability resulted in slowed delivery and expenditures for materials though it did not affect construction as enough materials were on hand to begin construction. The contractor is closely monitoring the project schedule and will utilize additional crews as necessary to maintain planned progress. | Weather is expected to be the most critical variable in the construction schedule. To date it has been unseasonably warm and rainy which slowed the start of construction at the end of the year. The contractor is utilizing additional crews as necessary to maintain projected progress. This project's expenditures will continue to lag reporting and most specifically in the area of construction labor due to the project inspection and invoicing review procedures as agreed to between the County and the contractor.
NT10BIX5570049 | 2012 | Q1 | Q1 - 2012 | The county continued to review potential tower sites in Massie's Mill but concentrated on moving forward with pre-construction planning at the Avon and Afton tower sites. Leases and permitting were completed on those towers, geotechnical engineering completed and an RFP developed for tower construction that will be released in the following quarter as will an RFP for construction of one access road. Construction of the fiber network continued with installation of approximately 13 miles of conduit primarily along Rt. 29 from Colleen to Lovingston. A RFP for electronics was issued and eight proposals received and reviewed; product demonstrations were scheduled in the following quarter to aid the county in selecting the electronics vendor. Discussions with providers continued this quarter to determine optimum network interconnection points, last mile options to connect additional end users, and network operation alternatives. All of the remaining outside plant materials were ordered. Davis Bacon Act review activities were conducted to confirm compliance. The Nelson County Broadband Authority and the working subcommittee continued to meet regularly to oversee the project implementation and make business development decisions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction start delayed by approximately 6 months. Approximately 13 miles of conduit was installed in this quarter, but fiber will not be pulled until the following quarter. | N/A | N/A | N/A | Construction start delayed by approximately 6 months. Approximately 13 miles of conduit was installed in this quarter, but fiber will not be pulled until the following quarter. | Variance due to delay in finalizing a Massie's Mill tower site. The Colleen tower is in place but no equipment will be deployed until both towers are ready. | Variance due to delays in environmental assessment clearance followed by local permitting. Two of the towers to be constructed have all approvals in place. Requests for proposals for road grading and tower construction to be released in Quarter 2. | Construction start delayed by approximately 6 months, now in progress but conduit only at this time. No fiber circuits completed between interconnection points. | 0 | 1 | 0 | No agreements signed as of this time, but quotes received this quarter. Negotiations and discussions ongoing with one wholesale provider who will also provide services to end users. | The network is under construction and no services are being provided at this time. | A network operator has not been selected at this time, though discussions are ensuing with qualified candidates. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | No variance, not included in baseline projections. | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in quarter 2. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in quarter 2. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in quarter 2. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in quarter 2. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Approximately 13 miles of conduit has been deployed but fiber not yet pulled. | N/A | N/A | N/A | Network not completed, services to be offered by last mile providers not the county. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Approximately 13 miles of conduit has been deployed but fiber not yet pulled. | N/A | N/A | N/A | Network not completed, services to be offered by last mile providers not the county. | The project intends to provide high speed middle mile access to private providers at speeds of up to 1 Gbps and access to community anchor institutions at broadband speeds desired. | FALSE | No change. | Construction of the network is expected to be 85% complete and testing in progress. Deployment of network equipment will be in progress and testing with service providers commenced. An additional 13 miles of network construction is anticipated to have been completed for a total of 26 miles, including last mile drop fiber connections. At least 9 community anchor institutions will be ready to receive services but installation of electronics in the network operating center and testing will be in progress with service to start in the 3rd quarter. A construction firm will have been selected for the Avon and Afton towers and pre- construction work in progress. A tower site in Massie's Mill will have been selected and negotiations in progress with the property owner to be followed by the Section 106 review through FCC application. A signed agreement with one wholesale Internet provider and one service provider will have been completed and collocation in progress to coincide with testing. | Nelson, County of | Construction of the fiber network has been slowed due to significant periods of rain in the first quarter. The Virginia Department of Transportation initially imposed numerous restrictions on working hours, but has since agreed to longer work times that will enable the contractor to be more efficient. The contractor is working several crews to make up delays due to weather. The County has continued to experience frustration in locating a suitable tower site in the Massie's Mill area; sites offered by citizens have not met the line of sight service requirements. Instead, the County has identified suitable properties and is now initiating discussions with property owners to find a willing lessee. The project continues to move forward in deployment at a steady pace. | Construction is well along and although not on the originally envisioned schedule due to weather and department of transportation delays is still expected to be completed during the optimum construction period and completed well before summer's end. Impediments to construction of the towers at Avon and Afton are not anticipated but at this time tower material availability is unknown and could be impacted by the tower construction across the nation. There are no anticipated delays in the receipt of electronics equipment but will not be known for sure until procurement has been completed. There are no known issues where BTOP technical assistance is needed at this time.
NT10BIX5570049 | 2012 | Q2 | Q2 - 2012 | Construction of the middle mile fiber continued with a total of 23 miles of conduit and 11 miles of fiber installed as of the quarter end. Work is concentrated on rock removal in portions of all segments and in particular on River Road where most of the route must be bored. Additional purchases of miscellaneous construction materials such as gravel were made as needed. The Afton and Avon tower construction bid was released and the erosion and sediment control plan completed for the Avon access road. A network electronics vendor was selected, contract negotiations completed, and the order for equipment placed. Contract negotiations began with both a wholesale Internet provider and a service provider to interconnect with the Nelson County network to provide services, and planning began to make the fiber connections and collocate in the network operating center. An anchor institution conduit installation contractor was selected through competitive procurement and work completed in preparation for pulling fiber into the buildings. Additional suitable tower sites in the Massies Mill area were identified and forwarded for zoning review prior to contacting property owners in the following quarter. A request for proposals soliciting network operation services was re-released. County staff continued to conduct Davis Bacon Act compliance review with field interviews of new crew members and payroll record inspection. The Nelson County Broadband Authority and the working subcommittee continued to meet regularly to oversee the project implementation and make business development decisions. | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | Construction start delayed by approximately 6 months. Approximately 23 miles of conduit and 11 miles of fiber were installed by the end of this quarter. | N/A | N/A | N/A | Construction start delayed by approximately 6 months. Approximately 23 miles of conduit and 11 miles of fiber was installed by the end of this quarter. | Variance due to delay in finalizing a Massies Mill tower site. The Colleen tower is in place but no equipment will be deployed until both towers are ready. | Variance due to delays in environmental assessment clearance followed by local permitting for the Avon and Afton towers, and site selection impediments for Massies Mill. Bids for construction of the Avon and Afton towers have been let and construction will begin in the following quarter. Additionally, access road construction at the Avon tower will occur in the following quarter. | Construction start delayed by approximately 6 months, now in progress but slowed because of rock removal. No fiber circuits have been completed between interconnection points. | 0 | 2 | 0 | Agreements in principal have been reached with a wholesale Internet provider and a service provider; contract negotiations are in progress. Planning is progressing to interconnect the fiber networks of these two providers with the County network and collocation planning in the network operations center is in progress as well. Contracts expected to be completed in the following quarter. | The network is under construction and no services are being provided at this time. | A request for proposals to select a network operator was re-released this quarter with proposals due in the following quarter. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | No variance. | Variance due to network construction lagging projections by approximately 6 months. Access not possible until network segments are completed and connected to the network operating center where providers will collocate equipment. | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in the following quarter. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in the following quarter. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in the following quarter. | Variance due to network construction lagging projections by approximately 6 months. No subscribers will be served until all fiber segments and testing is complete. Anticipate last mile service equipment to begin deployment in the following quarter. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. In total, approximately 23 miles of conduit and 11 miles of fiber have been deployed but no segments are complete at this time. | N/A | N/A | N/A | Network not completed, services to be offered by last mile service providers not the County. | 0 | 0 | 0 | 0 | 0 | Variance due to network construction lagging projections by approximately 6 months. In total, approximately 23 miles of conduit and 11 miles of fiber have been deployed but no segments are complete at this time. | N/A | N/A | N/A | Network not completed, services to be offered by last mile service providers not the County. | The project intends to provide high speed middle mile access to private providers at speeds of up to 1 Gbps and access to community anchor institutions at broadband speeds desired. | FALSE | No change. | Approximately 20 miles of fiber is expected to be installed in the next quarter. Construction of the fiber network is expected to be complete and testing in progress. Fiber connections to thirteen community anchor institutions will have been completed, customer premise equipment installed and testing in progress. Deployment of network equipment to be in process and collocation with two providers to be nearing completion. Two towers will be under construction and permitting in progress for the third site. The access road at the Avon tower will be under construction. The County will finalize network operations planning and agreements will be signed with two broadband wholesalers/last mile providers. | Nelson, County of | By this quarter's end, construction on the fiber network was focused on rock removal in all segments. Fiber was pulled through segments containing reel lengths of completed conduit. The rock removal is done through the slower construction method of boring and the segment along River Road is difficult to construct. Additionally, Department of Transportation oversight during this segment's construction includes an approval process that has slowed progress. Locating a suitable tower site in the Massies Mill area is a continued area of frustration due to the mountains impeding line of sight capabilities, but an additional pool of potential sites has been selected and vetting by planning and zoning is underway prior to contacting property owners which is expected to occur in the following quarter. | The removal of rock and installation of fiber by boring along River Road continues to be an area of concern, but construction will still be completed within the grant time frame. Impediments to construction at the Avon and Afton tower sites are not foreseen. The network equipment has been ordered and installation is expected to occur with no delays. There are no known issues where BTOP technical assistance is needed at this time.
NT10BIX5570049 | 2012 | Q3 | Q3 - 2012 | Construction of the middle mile fiber network continued with approximately 29 miles of fiber installed by the end of this quarter. Fiber connections into community anchor institutions, customer premise equipment installation and testing is in progress and on schedule for completion in the following quarter. Small purchases of miscellaneous outside plant materials were ordered to complete the conduit tie ins for the final fiber pulls. The Afton and Avon tower procurement process was completed, towers ordered and foundation designs approved. The access road for the Avon tower was fully under construction and conduit installed to the tower compound. Network electronics were received and installation and testing by the vendor began in the network operating center. One wholesale Internet provider completed collocation in the network operating center. Negotiations began with a third party for network operation services that will be completed in the following quarter. Agreements are in negotiation with two last mile providers. A tentative site was selected for a Massies Mill tower and due diligence negotiations with the property owner commenced, though the County continued to research alternative sites. Work began on the development of marketing materials to advertise the middle mile network to private providers outside of the County. The Nelson County Broadband Authority and the working subcommittee continued to meet regularly to oversee the project implementation and make business development decisions. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 3 | Construction start was delayed by approximately six months. All of the conduit and vaults have been installed, the majority of fiber pulled and the final connections of fiber into the community anchor institutions are in progress. The remaining network fiber will be installed in the following quarter. The microwave backhaul will not be completed until the first quarter of 2013. | N/A | N/A | N/A | Variance due to a delayed construction start of approximately six months. The final fiber tie ins and installation into community anchor institutions is in progress and will be complete in the following quarter. | Variance due to a delay in locating a suitable tower site in the Massies Mill area. The Colleen tower is in place but no equipment will be deployed until the Massies Mill tower is constructed. | Variance due to a delay in locating a suitable tower site in the Massies Mill area. The Afton and Avon towers have been ordered, foundation designs completed, and construction will occur in the following quarter. A third site has been tentatively selected and is in negotiation with the property owner. The County continues to search for alternative sites during this time. | Variance due to a delayed construction start of approximately six months. Collocation space in the network operating center is complete and a wholesale Internet provider has completed connectivity in the center. The public safety tower interconnection point is ready for private provider collocation with backhaul into the network operating center, as is the tower at Colleen. The additional interconnection points are in the process of installation as cabinets are being set at the Afton and Avon tower sites. The Massies Mill tower interconnection point will not be completed until the first quarter of 2013. | 1 | 2 | 20 | The County has a signed agreement with Lumos Networks. | The network is nearing completion with the final fiber tie ins and equipment installation in progress. No services are being offered by private providers at this time. The County will not be a service provider on this network but will provide transport for private provider services to the businesses and residents within reach of the middle mile fiber. | The County is in contract negotiations with a third party to operate the middle mile fiber network. Negotiations are expected to be completed in the following quarter. | 0 | 0 | 0 | 0 | Variance due to network construction delayed by approximately six months. Two new providers are currently negotiating last mile agreements for new access but services not available as equipment installation and testing is in progress. | Variance due to network construction delayed by approximately six months. One agreement is currently in negotiation with a provider that would receive improved access to their current customers but services are not available as equipment installation and testing is in progress. | No variance to plan, but dark fiber is available if desired and is advertised on the network service rate schedule. | Variance due to network construction delayed by approximately six months. Access is not possible until equipment and testing is completed. The County will not be a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | 0 | 0 | 0 | 0 | Variance due to network construction delayed by approximately six months. 13 community anchor institutions are in the process of network equipment and fiber installation and testing to confirm connectivity. New services over the fiber to all of the community anchor institutions will be possible in the following quarter. | Variance due to network construction delayed by approximately six months. 13 community anchor institutions are in the process of network equipment and fiber installation and testing to confirm connectivity. New services over the fiber to all of the community anchor institutions will be possible in the following quarter. | Variance due to network construction delayed by approximately six months. 13 community anchor institutions are in the process of network equipment and fiber installation and testing to confirm connectivity. New services over the fiber to all of the community anchor institutions will be possible in the following quarter. | Variance due to network construction delayed by approximately six months. Access is not possible until equipment and testing is completed. The County will not be a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | 299 | 0 | 0 | 0 | 0 | Variance due to network construction delayed by approximately six months. The fiber network is nearly complete with work in progress to complete tie ins and fiber pulls into the community anchor institutions. Approximately 299 homes are located within 500 feet of the fiber and could be served by private provider connections to the middle mile network. | N/A | N/A | N/A | Variance due to network construction delayed by approximately six months. Access not possible until equipment and testing is completed. The County will not be a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | 30 | 0 | 0 | 0 | 0 | Variance due to network construction delayed by approximately six months. The fiber network is nearly complete with work in progress to complete tie ins and fiber pulls into the community anchor institutions. Approximately 30 businesses are located within 500 feet of the fiber and could be served by private provider connections to the middle mile network. | N/A | N/A | N/A | Variance due to network construction delayed by approximately six months. Access is not possible until equipment and testing is completed. The County will not be a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | The project intends to provide high speed middle mile access to private providers at speeds of up to 1 Gbps and access to community anchor institutions at broadband speeds desired. | FALSE | No change. | The final fiber tie ins and installation of the remaining fiber will be complete in the next quarter. A third party network operator will be under contract. Two last mile service provider agreements will be completed and an additional wholesale provider will be in the process of collocating in the County network operating center. A third tower site in the Massies Mill area will have been selected and planning underway for local approval and tower construction procurement activities will have begun. All community anchor institutions will be capable of receiving new or improved services over the fiber network. The tower installation at Avon and Afton will be complete. | Nelson, County of | Construction on the fiber network in the third quarter was slow due to a large amount of rock removal primarily along River Road. Selection of a suitable tower site in the Massies Mill area continued to be problematic in achieving clear line of sight to the Colleen tower. A site that was selected last quarter was subsequently eliminated when the County and property owner failed to reach an agreement for a ground lease. An additional site has been located with an interested property owner and is currently in due diligence negotiations; the County continues to research alternative locations in the meantime. | No known issues at this time. The Massies Mill tower site will need FCC environmental approval but there are no known impediments to receiving clearance.
NT10BIX5570049 | 2012 | Q4 | Q4 - 2012 | Construction of the fiber backbone network and customer fiber interconnections was completed this quarter and final splicing and testing commenced. Final inspection activities began and a punch list of activities for clean up or correction was developed following site inspection with the Virginia Department of Transportation. Very small fill in orders for miscellaneous outside plant materials were ordered and received. Construction of two monopole towers was completed at the Avon and Afton sites. Selection of a final tower site in Massieâ€™s Mill and local permitting was completed, as was the required environmental and historic resource review through the FCC. The optimum site selected required a project modification to reroute the microwave backhaul path, adding 10 new miles of microwave network to the project with the microwave to fiber interconnection occurring at the Avon tower instead of the Colleen tower as originally proposed. The request was fully vetted, a determination of no environmental impact was made and the modification approved. A request for proposals was issued for the tower and microwave equipment, vendors selected and contracts initiated to start procurement. All of the network electronics were installed in the network operating center, at the customer facilities and in cabinets at the tower sites. Testing and turn up of county anchor facilities was completed. A wholesale Internet provider, Lumos Networks, completed interconnection in the network operating center and an initial turn up of a 25 Mbps Internet circuit. The County completed all contractual activities with the chosen network operator, Blue Ridge InterNetworks. All grant management activities including quarterly reports and twice monthly progress calls with the federal project officer were completed timely. | 31 | 0 | 0 | 0 | 31 | 4 | 3 | 5 | Variance due to a delayed construction start, delay in securing an optimum tower site in the Massie's Mill area, and significant weather events that impacted project resources. The backbone and interconnection drop fiber construction is complete though clean up and splicing will continue into the next quarter. The microwave backhaul mileage remains to be installed and will be deployed in the first quarter of 2013 with the Massie's Mill tower construction. | N/A | N/A | N/A | No variance | Variance due a delayed construction start, delay in securing an optimum tower site in the Massie's Mill area, and significant weather events that impacted project resources. Interconnection points have been completed between the Avon, Afton, Colleen and Lovingston towers and the backbone fiber network. Following construction of the Massie's Mill tower in the first quarter of 2013, a link will be established between that tower and the backbone fiber network at the Avon tower. | Variance due a delayed construction start, delay in securing an optimum tower site in the Massie's Mill area, and significant weather events that impacted project resources. The Avon, and Afton towers in this project have been constructed. The Colleen tower was an existing tower erected before the grant award. The Massie's Mill tower site has been secured, a vendor selected, and construction scheduled to commence in the first quarter of 2013. | Variance due a delayed construction start, delay in securing an optimum tower site in the Massie's Mill area, and significant weather events that impacted project resources. Interconnection points have been established at the Avon, Afton, Colleen, and Lovingston towers and at the network operating center at the county administration building. The Massie's Mill tower site has been secured, a vendor selected, and construction scheduled to commence in the first quarter of 2013 that will complete the project's interconnection points. | 2 | 1 | 12 | Lumos Networks and Blue Ridge InterNetworks | Currently the County is receiving Internet service from Lumos Networks at the network operating center and redistributing to county anchor facilities over the new fiber network. The County does not provide wholesale Internet services but Lumos has brought a circuit into the network operating center for wholesale services to other providers. The County provides transport for private provider services on the middle network only. | Blue Ridge InterNetworks is a contractor providing network operation services for the Nelson County middle mile fiber network. The contact is Baylor Fooks, (434) 531-4002 or baylor@briworks.com. The entire Nelson County fiber network is operated by this firm; management of the towers constructed in this project is not included in the network operation service. The County IInformation Systems Department will manage the towers and microwave connectivity. The Nelson County Information Systems Director is Susan Rorrer, 434-263-7122 or SRorrer@nelsoncounty.org. | 1 | 1 | 0 | 0 | Variance to due to delayed construction start and private provider scheduling issues. One provider agreement is complete but the provider is engaged in business planning and has not begun the collocation process. Anticipate new service delivery by that private provider to occur in the second or third quarter of 2013 at the earliest. One additional new provider continues to negotiate a contract for collocation, expected to be executed in the first quarter of 2013. | Variance due to delayed construction start. One provider completed collocation and testing and has begun Internet service delivery to the County as a first anchor customer. Marketing of fiber services to the provider's new and current customers is expected to begin in the first quarter of 2013. | No variance to plan, but dark fiber is available if desired and is advertised on the network services rate schedule. | The end user equipment has been installed at the community anchor institutions and the County facilities began receiving 10 Mbps Internet services at the end of the year. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | 12 | 5 | 7 | 0 | Network connectivity to 12 of the network's community anchor institutions has been completed and are capable of receiving services. The County has begun providing service to 5 county facilities. 7 institutions are ready to be served by private providers. 1 additional institution will be connected in first quarter of 2013. | Network connectivity to 12 of the network's community anchor institutions has been completed and are capable of receiving services. The County has begun providing service to 5 county facilities. 7 institutions are ready to be served by private providers. 1 additional institution will be connected in first quarter of 2013. | Network connectivity to 12 of the network's community anchor institutions has been completed and are capable of receiving services. The County has begun providing service to 5 county facilities. 7 remaining institutions are ready to be served by private providers. 1 additional institution will be connected in first quarter of 2013. | The end user equipment has been installed at the community anchor institutions and the County facilities began receiving 10 Mbps Internet services at the end of the year. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. | 299 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 299 homes located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. | 30 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 30 businesses located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. | The Nelson County middle mile fiber network is complete and available for private provider use to provide high speed services. Transport service is available at broadband speeds desired up to 1 Gbps. | FALSE | No change | Over the next quarter final clean up and close out of the fiber construction will occur. Deployment of the Massie's Mill tower will be in progress including frequency coordination in preparation for FCC microwave licensing and installation of the tower foundation and framing within the tower compound. The County will continue to work on business development planning with the network operator and expects to sign one additional broadband wholesaler/last mile provider agreement through the end of the next quarter. | Nelson, County of | Hurricane Sandy significantly impacted construction progress in Nelson County. The Avon and Afton tower foundation construction was delayed due to rain soaked compounds. Power installation to the tower compounds was delayed due to the local electric cooperative relocating resources to repair power infrastructure locally and in other areas on the east coast. The Virginia Department of Transportation requested restoration attention to conduit and vault placement in several areas that has pushed final completion of the fiber network construction into the first quarter of 2013. The County and its contractors continue to work diligently to complete all project activities and no known technical assistance from the BTOP program would be useful at this time. | Nelson County experienced delays in the BTOP project implementation due to two significant weather events in the second half of 2012 and delays in securing land for the final project tower. Although behind schedule, the installation of the middle mile network is now complete and all community anchor institutions have been connected. The remaining outstanding milestone is construction of the final tower with a microwave backhaul connection to the middle mile network, and work is in progress. Barring any unforeseen weather events that would disrupt the construction schedule, the erection of the tower is expected to occur in third week of February. One aspect of completing that milestone is the installation and turn up of the wireless backhaul equipment. The electronics vendor has been selected and the microwave equipment ordered. Frequency coordination has been initiated and the public notice period is expected to close at the end of February, at which time the microwave licensing application will be submitted to the FCC. Nelson County lies within the National Radio Quiet Zone due to its proximity to the Greenbank Observatory in West Virginia. Applicants within the Quiet Zone are not granted conditional authority to install and turn up facilities prior to receiving a formal microwave license as is typical for applicants outside of the Quiet Zone following satisfactory frequency coordination. The County does not anticipate any negative coordination results or Quiet Zo
NT10BIX5570049 | 2013 | Q1 | Q1 - 2013 | The contractor and the Virginia Department of Transportation began the process of closing out the right of way construction permit addressing restoration items for contractor clean up. Construction of the final tower in Massieâ€™s Mill commenced, the tower erected and the microwave radio backhaul equipment ordered and received. The County was granted a project extension to allow the FCC licensing process to complete before grant close out. Frequency coordination was initiated in preparation for FCC application for microwave license; results indicate no interference issues, but the National Radio Quiet Zone did not provide response citing backlog in completing reviews due to the national narrow banding deadline. Submission of the FCC microwave licensing application is on hold pending a response from the Quiet Zone and Nelson County is not eligible for conditional authority to operate prior to grant of license. The County continued work with the network operator Blue Ridge InterNetworks to develop business plans for interconnections and service delivery. All grant management activities including quarterly and annual reports and network file submissions and twice monthly progress calls with the federal project officer were completed timely. | 31 | 0 | 0 | 0 | 31 | 0 | 3 | 5 | Variance due to a delayed construction start and significant weather events that impacted project resources. The 31 miles of backbone and interconnection drop fiber construction is complete and operational. This project originally proposed 6 miles of microwave backhaul for a total of 37 network miles but the project was modified in November 2012 increasing the microwave portion to 16 miles for a new total network mileage of 47. The microwave backhaul mileage remains to be installed. Due to a backlog at the National Radio Quiet Zone licensing for the microwave frequency is delayed but expected to complete in the following quarter. | N/A | N/A | N/A | No variance | Variance due to a misinterpretation of guidance at the time the baseline for this project was developed. Only two wireless links are funded by this project and will comprise the microwave backhaul portion of the network linking the Massie's Mill tower to the Avon tower. The wireless equipment has been received and will be installed and turned up by June 30, 2013. | Variance due to a project modification in November 2010 that removed construction of the Colleen tower from this project. Three towers have been erected at Avon, Afton, and Massie's Mill. The Massie's Mill tower has been erected; installation, turn up and testing of the microwave equipment for the Massie's Mill tower will be completed in the following quarter. | Variance due to a delayed construction start and significant weather events that impacted project resources. Interconnection points have been established at the Avon, Afton, Colleen and Lovingston towers and at the network operating center at the county administration building. The Massie's Mill tower has been erected but all activities to complete the tower compound and finalize frequency licensing for the microwave backhaul will occur in the following quarter. | 2 | 1 | 12 | Lumos Networks and Blue Ridge InterNetworks | The county is currently receiving Internet service from Lumos Networks at the network operating center and redistributing to county anchor facilities over the new fiber network. The county does not provide wholesale Internet services but Lumos has brought a circuit into the network operating center for wholesale services to other providers. The County provides transport for private provider services on the middle mile network only. | Blue Ridge InterNetworks is a contractor providing network operation services for the Nelson County middle mile network. The contact is Baylor Fooks (434) 531-4002 or baylor@briworks.com. The entire Nelson County fiber network is operated by this firm; management of the towers constructed in this project is not included in the network operation service. The County Information Systems Department will manage the towers and microwave connectivity. The Nelson County Information Systems Director is Susan Rorrer, 434-263-7122 or SRorrer@nelsoncounty.org. | 1 | 1 | 0 | 0 | Variance to due to delayed construction start and private provider scheduling issues. A new provider is moving forward with activities to serve new businesses. Another agreement for access to the network and collocation in the network operating center is still in negotiation with a new service provider. | Variance due to delayed construction start. One provider completed collocation and testing and has begun Internet service delivery to the County as a first anchor customer. | No variance to plan, but dark fiber is available if desired and is advertised on the network services rate schedule. | The end user equipment has been installed at the community anchor institutions and County facilities are receiving 15 Mbps Internet services. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 13 | 5 | 8 | 0 | No variance to plan. All community anchor institutions are connected to the fiber network and can be served. | Network connectivity to all 13 of the network's community anchor institutions has been completed and all are capable of receiving services. The County has begun providing service to 5 county facilities. 8 institutions are ready to be served by private providers. | Network connectivity to all 13 of the network's community anchor institutions has been completed and are capable of receiving services. The County is providing service to 5 county facilities. 8 institutions are ready to be served by private providers. | The end user equipment has been installed at the community anchor institutions and County facilities are receiving 15 Mbps Internet services. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 299 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 299 homes located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 30 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 30 businesses located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | The Nelson County middle mile fiber network is complete and available for private provider use to deliver high speed services. Transport service is available at broadband speeds desired up to 1 Gbps. | FALSE | No change. | Over the next quarter the remaining tasks to finalize construction of the Massie's Mill tower will occur. The tower has been erected but final dressing of the tower compound and installation of the microwave equipment will be completed in the 2nd quarter. The microwave licensing process is expected to complete in the 2nd quarter, immediately followed by testing and turn up of 16 miles of microwave backhaul. This will complete the total 47 combined fiber and wireless network miles as approved in the November 2012 project modification. The County anticipates execution of one additional service provider agreement by the end of the quarter. Grant close out activities will complete by June 30, 2013. | Nelson, County of | The FCC typically grants conditional authority to operate radio equipment following successful frequency coordination but prior to final licensing by the FCC. However, the Massie's Mill and Wintergreen towers are located within the National Radio Quiet Zone, an area not eligible for conditional authority. Licensing for the microwave backhaul equipment in this project has been delayed due to a backlog at the Quiet Zone. Quiet Zone personnel estimate sign off of the frequency request in the April to May time frame. BTOP technical assistance may be useful in determining conditional authority to operate if the Quiet Zone coordination letter is not forthcoming so that the County can complete all aspects of the project and close out the grant by the deadline. | The only challenge will lie with receiving a timely response from the National Radio Quiet Zone and the FCC in regards to microwave licensing. The Quiet Zone did not respond to the request for frequency coordination within the typical 30 day process and application to the FCC is on hold pending receipt of letter from Quiet Zone.
NT10BIX5570049 | 2013 | Q2 | Q2 - 2013 | All activities to finalize construction at the Massie's Mill tower compound were completed. The FCC granted microwave licensing and the microwave backhaul network was tested and turned up, including interconnection with the fiber network at the Avon tower and interconnection cabinet. The total 47 combined microwave and fiber network miles were completed. Towers are complete and available for private provider broadband wireless services. Grant close out activities are in progress. | 47 | 0 | 0 | 0 | 31 | 2 | 3 | 6 | No variance, project complete. 31 miles of fiber and 16 miles of microwave backhaul network is complete. | N/A | N/A | N/A | No variance, network complete. | Variance due to a misinterpretation of guidance at the time the baseline for this project was developed. Only two wireless links are funded by this project and comprise the microwave backhaul portion of the network linking the Massie's Mill tower to the Avon tower. The links are turned up and operational and complete 16 miles of microwave backhaul network. | Variance due to a project modification in November 2010 that removed construction of the Colleen tower from this project. Three towers have been erected at Avon, Afton, and Massie's Mill and all construction tasks are complete. | Interconnection points have been established at the Avon, Afton, Massie's Mill, Colleen and Lovingston towers and at the network operation center at the county administration building. | 2 | 1 | 12 | Lumos Networks and Blue Ridge InterNetworks. | The county is currently receiving Internet service from Lumos Networks at the network operating center and redistributing to county anchor facilities over the new fiber network. The county does not provide wholesale Internet services but Lumos has brought a circuit into the network operating center for wholesale services to other providers. The County provides transport for private provider services on the middle mile network only. | Blue Ridge InterNetworks is a contractor providing network operation services for the Nelson County middle mile network. The contact is Baylor Fooks (434) 531-4002 or baylor@briworks.com. The entire Nelson County fiber network is operated by this firm; management of the towers constructed in this project is not included in the network operation service. The County Information Systems Department will manage the towers and microwave connectivity. The Nelson County Information Systems Director is Susan Rorrer, 434-263-7122 or SRorrer@nelsoncounty.org. | 1 | 1 | 0 | 0 | Variance due to private provider reluctance to follow through on agreement to complete collocation. One new provider is offering services to businesses on the network. One additional agreement for access to the network and collocation in the network operating center is still in negotiation and expected to be executed in the 3rd quarter of 2013. | A local provider is collocated in the network operating center and providing Internet service delivery to the County. | No variance to plan, but dark fiber is available if desired and is advertised on the network services rate schedule. | The end user equipment has been installed at the community anchor institutions and County facilities are receiving 15 Mbps Internet services. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 13 | 5 | 8 | 0 | No variance to plan. All community anchor institutions are connected to the fiber network and can be served. | Network connectivity to all 13 of the network's community anchor institutions has been completed and all are capable of receiving services. The County has begun providing service to 5 county facilities. 8 institutions are ready to be served by private providers. | Network connectivity to all 13 of the network's community anchor institutions has been completed and are capable of receiving services. The County is providing service to 5 county facilities. 8 institutions are ready to be served by private providers. | The end user equipment has been installed at the community anchor institutions and County facilities are receiving 15 Mbps Internet services. The County is not a service provider on the middle mile network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 299 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 299 homes located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps; >50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000 Mbps; and >1000 Mbps. | 30 | 0 | 0 | 0 | 0 | The middle mile fiber passes approximately 30 businesses located within 500 feet of the fiber and could be served by private provider connections to the network. | N/A | N/A | N/A | The fiber network is complete and ready for private provider access. The County is not a service provider on the network but private providers can purchase transport at speeds desired up to 1 Gbps. Service providers will be charged based on the total amount of bandwidth transported monthly. Rates vary by the following circuit tiers: 0-10 Mbps; >10-25 Mbps; >25-50 Mbps;>50-100 Mbps; >100-250 Mbps; >250-500 Mbps; >500 -1000;Mbps; and >1000 Mbps. | The Nelson County middle mile fiber network is complete and available for private provider use to deliver high speed services. Transport service is available at broadband speeds desired up to 1 Gbps. The towers are complete and ready for private provider use to deploy broadband wireless services. | FALSE | NO CHANGE | All network deployment activities are complete. The County will complete all grant close out tasks by March 27, 2014. | Nelson, County of | The project was delayed due to a purported backlog in reviews at the National Radio Quiet Zone, but clearance was received in this quarter and the microwave licensing granted by the FCC. All project activities are complete. | All project deployment activities are complete. The County has commenced tasks to close out the grant. No challenges are expected and all grant close out activities will be completed by March 27, 2014.
NT10BIX5570050 | 2010 | Q3 | Q3 - 2010 | Zito Media Communications II, LLC has finished the engineering phase of the project. Also we have submitted the final draft of the environmental assessment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | 0 | 0 | 0 | N/A | See Service Offerings Attachment | N/A | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | N/A | FALSE | N/A | Completion and selection of bidding process for fiber, hardware and construction vendors. Received signed FONSI. | Zito Media Communications II, LLC | None | None.
NT10BIX5570050 | 2010 | Q4 | Q4 - 2010 | In this quarter Zito continued the planning and engineering phase that includes strand mapping, pole profiling and physical ride out of the proposed fiber path. Zito's received approval for the environmental assessment. Zito also concluded and chose vendors for hardware, fiber and construction on the project. Zito has also applied to utilities for pole attachments and applied to railroads for crossing permits. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | 0 | 0 | N/A | See Service Offerings Attachment | N/A | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Services Offerings Attachment | FALSE | N/A | In the next quarter Zito plans on beginning construction on the project as well as continuing make ready applications, ride outs and site preparation. In addition Zito plans on receiving initial shipments of electronic equipment, fiber and hardware. | Zito Media Communications II, LLC | No substantial challenges or issues arose in the past quarter. | A possible challenge in the next quarter is receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Certain utility companies are not sending us make ready invoices in a timely manner and construction cannot begin until utilities issue permits for fiber placement and have their contractors move other attachments to allow fiber placement on the utility poles.
NT10BIX5570050 | 2011 | Q1 | Q1 - 2011 | In this quarter Zito continued the planning and engineering phase that includes strand mapping, pole profiling and physical ride out of the proposed fiber path. Zito has also applied to utilities for pole attachments and applied to railroads for crossing permits. Construction has yet to commence due to certain utility companies not delivering make ready invoices in a timely manner. Expenditure difference due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | N/A | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | N/A | N/A | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | 0 | 0 | 0 | None | See Services Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | See Service Offerings Attachment | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | See Services Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to delay in receiving make ready quotes from utility companies. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | Negative variance due to delay in receiving make ready quotes from utility companies. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | Negative variance due to delay in receiving make ready quotes from utility companies. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | Negative variance due to delay in receiving make ready quotes from utility companies. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to delay in receiving make ready quotes from utility companies. Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | In the next quarter Zito plans on beginning construction on the project as well as continuing make ready applications, ride outs and site preparation. In addition Zito plans on receiving initial shipments of electronic equipment, fiber and hardware. Zito expects to be back on schedule by the end of the September 2011 quarter. | Zito Media Communications II, LLC | A challenge in the quarter was receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Certain utility companies are not sending us make ready invoices in a timely manner and construction cannot begin until utilities issue permits for fiber placement and have their contractors move other attachments to allow fiber placement on the utility poles. | A possible challenge in the next quarter could be receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. The expenditure difference is due to make ready delays. Zito expects to be back on schedule by the end of the September 2011 quarter. A potential timing issue in the next quarter is the lead time for delivery of hardware and fiber shifting from 5 to 12 weeks due to increased demand.
NT10BIX5570050 | 2011 | Q2 | Q2 - 2011 | Zito made progress with utility companies who have delayed project construction from starting. Zito has begun to receive invoicing from the utility companies who have been delaying the project. The expenditure difference is due to make ready delays. During the quarter Zito continued applying for pole and railroad permits. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | No Variance from Baseline | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. Zito expects to be back on schedule by the end of the December 2011 quarter. | 0 | 0 | 0 | None. No agreements have been signed or negotiated as construction as not commenced. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. | No Variance from Baseline | See Service Offerings Attachment | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects to be back on schedule by the end of the December 2011 quarter. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | In the next quarter Zito expects to begin construction on the project. Also, Zito expects to finalize fiber lease for a portion of the project in northeast Ohio. In addition, Zito will receive the initial shipments of fiber and hardware from selected vendors. Zito will begin locating the potential hub sites along the project path. Zito will also contact potential anchor institutions and businesses to connect to the network. | Zito Media Communications II, LLC | A continuing challenge has been receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Certain utility companies are not sending us make ready invoices in a timely manner and construction cannot begin until utilities issue permits for fiber placement and have their contractors move other attachments to allow fiber placement on the utility poles. | Although progress has been made with utility companies there is still a possible challenge of receiving the invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Zito expects to be back on schedule by the end of the December 2011 quarter. A potential timing issue in the next quarter is the lead time for delivery of fiber shifting from 5 to 14 weeks due to increased demand.
NT10BIX5570050 | 2011 | Q3 | Q3 - 2011 | Zito made progress with utility companies who have delayed project construction from starting. Zito has begun to receive invoicing from the utility companies who have been delaying the project. The expenditure difference is due to make ready delays. During the quarter Zito continued applying for pole and railroad permits. Zito started informational brochure mailings to potential anchor institutions and hub locations. As construction commences, Zito's commercial sales division will increase communication with these potential hubs and CAIs as project build increases. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 21 | 20 | 0 | 0 | 41 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to make ready invoicing and make ready work. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. The mileage is based off of Zito's fiber purchase and IRU agreement. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | 0 | 0 | 0 | None. No agreements have been signed or negotiated as construction as not commenced. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, construction has been delayed due to make ready issues. | No Variance from Baseline | See Service Offerings Attachment | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. The fiber purchase and IRU is not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. The fiber purchase and IRU is not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has yet to commence due to make ready delays. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | See Service Offerings Attachment | 524 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.As construction commences this metric will increase due to the fiber build passing these entities. Zito expects the project to be substantially complete by the end of the March 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects the project to be substantially complete by the end of the March 2012 quarter. The fiber from the IRU and purchase are not currently active to provide services. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. As construction commences this metric will increase due to the fiber build passing these entities. Zito expects the project to be substantially complete by the end of the March 2012 quarter. The fiber from the IRU and purchase are not currently active to provide services. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | In the next quarter Zito expects to accelerate construction on the project as make ready work continues. Zito also expects to receive additional shipments of hardware and fiber. Zito will begin locating the potential hub sites along the project path as well as negotiating with potential locations. Zito will expand its marketing efforts to begin negotiations between Zito and potential CAIs and other customers to connect to the project. As construction commences and increases Zito's commercial sales division will increase communication with these potential hubs and CAIs. Zito expects 140 miles of fiber to be deployed in the quarter and 0 miles leased. Zito plans on connecting 2 CAIs and having 5 signed agreements with CAIs by the end of quarter four 2011. Zito expects to have 0 signed agreements with broadband wholesalers and last mile providers. As project mileage increases Zito will increase negotiations with these parties. | Zito Media Communications II, LLC | A continuing challenge has been receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Certain utility companies are not sending us make ready invoices in a timely manner and construction cannot begin until utilities issue permits for fiber placement and have their contractors move other attachments to allow fiber placement on the utility poles. In addition to not receiving the invoices in a timely manner, certain utility companies are not completing make ready work in a timely manner. | Although progress has been made with utility companies there is still a possible challenge getting utilities to finish make ready work in a timely manner. Zito expects the project to be substantially complete by the end of the March 2012 quarter.
NT10BIX5570050 | 2011 | Q4 | Q4 - 2011 | Zito made progress with utility companies who have delayed project construction from starting. Zito was able to begin construction on the project as make ready work continues. Zito continues to work with the utility companies concerning the make ready issues. Zito started informational brochure mailings to potential anchor institutions and hub locations. In addition, Zito's commercial division began having meetings and out reach activities with various entities such as chamber of commerces. As construction continues Zito's commercial sales division will increase communication with these potential hubs and CAIs as project build increases. Zito received additional shipments of hardware and fiber. | 51 | 20 | 0 | 0 | 71 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to make ready invoicing and make ready work. Zito expects the project network build to be complete by the end of the June 2012 quarter. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction commenced during the quarter. The mileage is based off of Zito's fiber purchase, IRU agreement and newly constructed fiber. Zito expects the project network build to be complete by the end of the June 2012 quarter. | N/A | N/A | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has started but fiber is not currently active. Zito expects the project network build to be complete by the end of the June 2012 quarter. | 0 | 0 | 0 | None. No agreements have been signed or negotiated in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. There are preliminary talks with providers, but no signed agreements. In addition, construction has been delayed due to make ready issues. | No Variance from Baseline | See Service Offerings Attachment | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction started during the quarter as make ready delays lessen. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction started during the quarter as make ready delays lessen. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has started albeit slowly during the quarter. In the next quarter as make ready delays lessen construction will increase as more crews are utilized. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the June 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has started albeit slowly during the quarter. In the next quarter as make ready delays lessen construction will increase as more crews are utilized. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the June 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has started albeit slowly during the quarter. In the next quarter as make ready delays lessen construction will increase as more crews are utilized. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the June 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Construction has started albeit slowly during the quarter. In the next quarter as make ready delays lessen construction will increase as more crews are utilized. As construction commences in northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the June 2012 quarter. | See Service Offerings Attachment | 1385 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has started albeit slowly during the quarter. In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Zito network build is not currently active. Zito expects the project network build to be complete by the end of the June 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has started albeit slowly during the quarter. In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Zito expects the project network build to be complete by the end of the June 2012 quarter. The fiber constructed is not currently active to provide services. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has started albeit slowly during the quarter. In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Zito expects the project network build to be complete by the end of the June 2012 quarter. The fiber constructed is not currently active to provide services. | See Service Offerings Attachment | See Service Offerings Attachment. | FALSE | N/A | As construction commences and increases Zito's commercial sales division is increasing communication with potential hubs and CAIs. Zito expects 179 miles of fiber to be deployed in the quarter and 0 miles leased. Zito plans on connecting 4 CAIs with agreements and having 2-5 signed agreements for future connection with CAIs by the end of quarter one 2012. Zito expects to have 2 signed agreements with broadband wholesalers and last mile providers. As project mileage increases Zito will increase negotiations with these parties. Zito expects to receive 93% of all project fiber by the end of the March 2012 quarter. | Zito Media Communications II, LLC | A continuing challenge has been receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. Certain utility companies are not sending us make ready invoices in a timely manner and construction cannot begin until utilities issue permits for fiber placement and have their contractors move other attachments to allow fiber placement on the utility poles. In addition to not receiving the invoices in a timely manner, certain utility companies are not completing make ready work in a timely manner. | Although progress has been made with utility companies there is still a possible challenge getting utilities to finish make ready work in a timely manner. Zito expects the project network build to be complete by the end of the June 2012 quarter.
NT10BIX5570050 | 2012 | Q1 | Q1 - 2012 | Zito continued construction in Northwest Pennsylvania. Zito continued informational brochure mailings to potential anchor institutions and hub locations. Zito has increased the workforce on the project as it progresses out of congested urban areas. There are now multiple construction crews increasing the construction production. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. Zito received the rest of the fiber for the project thus removing the potential of the project being delayed due to lack of fiber. | 112 | 20 | 0 | 0 | 112 | 0 | 0 | 1 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to make ready invoicing and make ready work. Zito expects the project network build to be complete by the end of the September 2012 quarter. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, Zito's construction progress was hampered by inconsistent make ready completion. The mileage is based off of Zito's fiber purchase, IRU agreement and newly constructed fiber. Zito expects the project network build to be complete by the end of the September 2012 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito has established the interconnection point in Erie, PA. Other points are established just not connected to the network due to construction delays. Zito expects the project network build to be complete by the end of the September 2012 quarter. | 0 | 2 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. As the project expands into other markets negotiations will increase. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. | See Service Offerings Attachment | 2 | 0 | 2 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects the project network build to be complete by the end of the September 2012 quarter. | See Service Offerings Attachment | 1857 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active as a result of the inconsistent make ready completed. Zito expects the project network build to be complete by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active. Zito's commercial division is actively negotiating with numerous businesses along the project path. As construction progresses and the fiber becomes active this metric will increase. Zito expects the project network build to be complete by the end of the September 2012 quarter. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active. Zito's commercial division is actively negotiating with numerous businesses along the project path. As construction progresses and the fiber becomes active this metric will increase. Zito expects the project network build to be complete by the end of the September 2012 quarter. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | Zito expects to increase it's construction crews as construction extends out of the congested urban areas of Northwest Pennsylvania. Zito will continue to negotiate with critical anchor institutions, business and last mile providers. These metrics should increase as the construction reaches more of these entities. Zito expects to construct 100 miles in the quarter bringing the new mileage 212 miles. In the third quarter of 2012 Zito expects to be constructing 60 miles of fiber a month finishing the majority of the build by the end of the September 2012 quarter. Zito expects to connect 10-12 CAIs by the end of the quarter. The reduced number is a result of construction delays that disrupt the continuity of the network. Zitoâ€™s commercial sales team is actively negotiating with institutions. Zito should have signed agreements with multiple CAIs, but they wonâ€™t be connected to the network by the end of the quarter. Zito expects to have zero signed agreements with broadband wholesaler/last mile providers. | Zito Media Communications II, LLC | A continuing challenge has been receiving invoices from utility companies for make ready costs and objecting to those invoices if they are unreasonable. In addition to not receiving the invoices in a timely manner, certain utility companies are not completing make ready work in a timely manner. Zito has also been slightly delayed by overlashing another BTOP project's fiber along areas of our project. Zito has an agreement with the KINBER project to dual lash cable in certain areas in Pennsylvania. Although there is no additional cost incurred the additional cable has slightly delayed work crews. Zito believes at this time the additional cable will not affect the completion of the project. Lastly, in areas that make ready was supposedly completed construction crews discovered stretches that make ready was not completed. These areas hampered construction crews from completing full stretches of fiber and slowing the pace of construction. | The continuing challenge is having utility companies finish make ready work to allow construction crews to increase production. If portions of make ready are not completed portions of the fiber build would not be active, thus, not allowing services to be provided to businesses and anchor institutions. Zito will continue to monitor the situation and apply as much pressure as possible to alleviate the situation. Although Zito has been hampered by make ready the problem is slowly alleviating. Zito does not expect the make ready delay to the ultimate completion of the project within the allotted time frame. We do not believe NTIA assistance is required with this challenge.
NT10BIX5570050 | 2012 | Q2 | Q2 - 2012 | Zito continued construction in Northwest Pennsylvania. Zito continued informational brochure mailings to potential anchor institutions and hub locations. Zito has increased the workforce on the project as it progresses out of congested urban areas. There are now multiple construction crews increasing the construction production. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. | 142 | 20 | 0 | 0 | 142 | 0 | 0 | 1 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The mileage includes new construction and the fiber purchased from Conneaut Telephone Company. Construction has been delayed due to make ready invoicing and make ready work. In addition Zito's construction crews have been hampered by installing dual fiber along portions of the project. The dual fiber is part of an agreement Zito has with another BTOP recipient. Also, the mileage in the previous report was off due to including strand mileage with fiber mileage. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, Zito's construction progress was hampered by inconsistent make ready completion. The mileage is based off of Zito's fiber purchase, IRU agreement and newly constructed fiber. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Other points are established just not connected to the network due to construction delays. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | 0 | 3 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. As the project expands into other markets negotiations will increase. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | See Service Offerings Attachment | 2 | 0 | 2 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. Zito has multiple interested CAIs and signed agreements along the project's path. However, these CAIs are in areas where the network is not active or built yet. | no Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. Zito has some signed agreements and more nearing completion. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | See Service Offerings Attachment | 2200 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active as a result of the inconsistent make ready completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito's commercial division is actively negotiating with numerous businesses along the project path. As construction progresses and the fiber becomes active this metric will increase. ZIto's commercial division has multiple business agreements lined up, but these entities are not located on currently built fiber or the fiber is not active. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito's commercial division is actively negotiating with numerous businesses along the project path. As construction progresses and the fiber becomes active this metric will increase. Zito expects to be substantially complete with the project network build by the end of the September 2012 quarter. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | n/a | Zito will continue to negotiate with critical anchor institutions, business and last mile providers. These metrics should increase as the construction reaches more of these entities. Zito expects to construct 180 miles in the quarter bringing the new mileage 300 miles. In the fourth quarter the project build left will be completed in the beginning of the quarter. Zito expects to connect 12-20 CAIs by the end of the quarter. The reduced number is a result of construction delays that disrupt the continuity of the network. Zitoâ€™s commercial sales team is actively negotiating with institutions. Zito will have signed agreements with multiple CAIs, but they wonâ€™t be connected to an active network by the end of the quarter. Zito expects to have 1-2 signed agreements with broadband wholesaler/last mile providers. | Zito Media Communications II, LLC | Zito has been delayed by overlashing another BTOP project's fiber along areas of our project. Zito has an agreement with the KINBER project to dual lash cable in certain areas in Pennsylvania. Although there is no additional cost incurred the additional cable has delayed work crews. Zito believes at this time the additional cable will not affect the completion of the project. Lastly, in areas that make ready was supposedly completed construction crews discovered stretches that make ready was not completed. These areas hampered construction crews from completing full stretches of fiber and slowing the pace of construction. | The continuing challenge is having utility companies finish make ready work to allow construction crews to increase production. If portions of make ready are not completed portions of the fiber build would not be active, thus, not allowing services to be provided to businesses and anchor institutions. Zito will continue to monitor the situation and apply as much pressure as possible to alleviate the situation. Although Zito has been hampered by make ready the problem is slowly alleviating. Zito does not expect the make ready delay to the ultimate completion of the project within the allotted time frame. We do not believe NTIA assistance is required with this challenge.
NT10BIX5570050 | 2012 | Q3 | Q3 - 2012 | Zito continued construction in Pennsylvania. Zito continued informational brochure mailings to potential anchor institutions and hub locations. Zito has increased the workforce on the project as it progresses out of congested urban areas and finishes the dual build with another BTOP project. There are now multiple construction crews increasing the construction production. Following the construction crews Zito's splicing contractor has spliced portions of the constructed fiber. Also, Zito installed fiber and electronics into a few hub sites and CAI locations. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. Zito's commercial division are actively negotiating with potential customers and CAIs along the project's path. | 225 | 20 | 0 | 0 | 225 | 0 | 0 | 4 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The mileage includes new construction and the fiber purchased from Conneaut Telephone Company. Construction has been delayed due to make ready invoicing and make ready work. In addition Zito's construction crews have been hampered by installing dual fiber along portions of the project. The dual fiber is part of an agreement Zito has with another BTOP recipient. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, Zito's construction progress was hampered by inconsistent make ready completion. The mileage is based off of Zito's fiber purchase, IRU agreement and newly constructed fiber. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Other points are established just not connected to the network due to construction delays. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | 0 | 3 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the inconsistent make ready completion hampering complete stretches of fiber from being completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. | See Service Offerings Attachment | 5 | 0 | 5 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. Zito has multiple interested CAIs and signed agreements along the project's path. However, these CAIs are in areas where the network is not active or built yet. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. This metric will increase as construction progresses and marketing efforts establish agreements with CAIs. Zito has some signed agreements and more nearing completion. | See Service Offerings Attachment | 0 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction due to continual make ready delays Zito has not connected to the northeast Ohio last mile areas. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. As construction reaches northeast Ohio this metric will increase due to the fiber build passing these entities in our last mile areas. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | See Service Offerings Attachment | 3342 | 1 | 0 | 1 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active as a result of the inconsistent make ready completed. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Due to the delays most of the fiber constructed is not currently active. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito's commercial division is actively negotiating with numerous businesses along the project path. ZIto's commercial division has multiple business agreements lined up, but these entities are not located on currently built fiber or the fiber is not active. Although these entities are passed Zito has not connected them to the network as it is not active in most areas. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction has been delayed due to continual make ready issues with utility companies. Construction In the next quarter Zito expects this metric to increase as make ready delays lessen allowing more construction crews to be used. Due to the delays most of the fiber constructed is not currently active. In addition, the dual build with another BTOP project has decreased the production levels of the construction crews. Zito's commercial division is actively negotiating with numerous businesses along the project path. As construction progresses and the fiber becomes active this metric will increase. Zito expects to be substantially complete with the project network build by the middle of the December 2012 quarter. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | Zito will continue to negotiate with critical anchor institutions, business and last mile providers. These metrics should increase as the construction reaches more of these entities. Zito expects to complete the majority of the network build by the middle of the December 2012 quarter. Zito plans to deploy 135 miles of fiber in the next quarter. Zito expects to connect 20-40 CAIs by the end of the quarter. The reduced number is a result of construction delays that disrupt the continuity of the network. Zitoâ€™s commercial sales team is actively negotiating with institutions. Zito currently has signed agreements with CAIs, but the fiber is not connected to these facilities. Zito will have signed agreements with multiple CAIs, but some won't be connected to an active network by the end of the quarter. In the 1st quarter of 2013, Zito will complete any minor segments of the build not yet completed. In addition, Zito will build the fiber connections from the CAIs and businesses to the fiber network. These connections will allow Zito to provide services to the rest of the CAIs needed to fulfill the baseline numbers . Zito expects to have 1-2 signed agreements with broadband wholesaler/last mile providers. | Zito Media Communications II, LLC | Zito has been delayed by overlashing another BTOP project's fiber along areas of our project. Zito has an agreement with the KINBER project to dual lash cable in certain areas in Pennsylvania. Although there is no additional cost incurred the additional cable has delayed work crews. Zito believes at this time the additional cable will not affect the completion of the project. Lastly, in areas that make ready was supposedly completed construction crews discovered stretches that make ready was not completed. These areas hampered construction crews from completing full stretches of fiber and slowing the pace of construction. | The continuing challenge is having utility companies finish make ready work to allow construction crews to increase production. If portions of make ready are not completed portions of the fiber build would not be active, thus, not allowing services to be provided to businesses and anchor institutions. Zito will continue to monitor the situation and apply as much pressure as possible to alleviate the situation. Although Zito has been hampered by make ready the problem is slowly alleviating. Zito does not expect the make ready delay to the ultimate completion of the project within the allotted time frame. We do not believe NTIA assistance is required with this challenge.
NT10BIX5570050 | 2012 | Q4 | Q4 - 2012 | Zito continued construction in Ohio and Pennsylvania. Zito continued informational brochure mailings to potential anchor institutions. Zito has increased the workforce on the project as it progresses out of congested urban areas and finished the dual build with another BTOP project. Zito was able to complete a majority of the project build in the current quarter. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. | 350 | 20 | 0 | 0 | 350 | 0 | 0 | 9 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The mileage includes new construction and the fiber purchased from Conneaut Telephone Company. Zito was able to complete a majority of the network build in the quarter. The remaining network build will be finished in the first quarter of 2013. | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The mileage is based off of Zito's fiber purchase, IRU agreement and newly constructed fiber. Zito was able to complete a majority of the network build in the quarter. The remaining network build will be finished in the first quarter of 2013. | No Variance from Baseline Report | No Variance from Baseline Report | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Although a majority of the network is constructed Zito still has to splice certain areas to create connectivity for the network, which in turn will increase the upgraded/new interconnection points. | 0 | 2 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | See Service Offerings Attachment | 5 | 0 | 5 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No anchor institutions were added in the current quarter although signed agreements were reached no fiber was installed to the facilities. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. As the project build finishes Zito's crews will begin installation into these sites. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No anchor institutions were added in the current quarter although signed agreements were reached no fiber was installed to the facilities. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. The fiber purchase and IRU are not currently active fiber nor does it directly connect to any CAIs. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. As the project build finishes Zito's crews will begin installation into these sites. | See Service Offerings Attachment | 5064 | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction Zito has not connected to the northeast Ohio last mile areas. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. Once splicing is completed the network will be active and able to connect to the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction Zito has not connected to the northeast Ohio last mile areas. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. Once splicing is completed the network will be active and able to connect to the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction Zito has not connected to the northeast Ohio last mile areas. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. Once splicing is completed the network will be active and able to connect to the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.Due to the slow progress of construction Zito has not connected to the northeast Ohio last mile areas. The majority of the project's build is not active as splicing crews have not completed that aspect of the project. Once splicing is completed the network will be active and able to connect to the last mile areas. | See Service Offerings Attachment | 5152 | 2 | 0 | 2 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Due to the delays most of the fiber constructed is not currently active. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Due to the delays most of the fiber constructed is not currently active. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Due to the delays most of the fiber constructed is not currently active. In addition, the negative variance is due to the amount of time it is taking to complete the project build. Although the project build is nearing completion the network itself is not active as crews still need to splice the fiber. | See Service Offerings Attachment | See Service Offerings Attachment | FALSE | N/A | Zito will continue to negotiate with critical anchor institutions, business and last mile providers. Zito expects to complete the network build during the quarter of 383 total project miles. Zitoâ€™s commercial sales team is actively negotiating with institutions. Zito currently has signed agreements with CAIs, and during the quarter Zito's construction crews will connect these CAIs. Zito expects to have connected by the end of the quarter 15 anchor institutions. In the 1st quarter of 2013, Zito will complete any minor segments of the build not yet completed. Zito expects to have 1-2 signed agreements with broadband wholesaler/last mile providers. | Zito Media Communications II, LLC | Zito was able to complete a majority of the network build during the quarter. Since a majority of the project build was completed with less than 10 miles left to complete the project's build in the next quarter Zito does not see any issues or areas that will require BTOP assistance. | Zito expects to complete the project build during the quarter. Since Zito expects to complete the network build no assistance will be required by the BTOP program.
NT10BIX5570050 | 2013 | Q1 | Q1 - 2013 | Zito completed the project build during the quarter. Zito continued informational brochure mailings to potential anchor institutions. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. Based off of this outreach Zito's commercial division was able to sign anchor institutions as customers to be connected over the next few months. | 363 | 20 | 0 | 0 | 363 | 0 | 0 | 17 | No Variance from Baseline Report | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | 0 | 2 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is in talks with providers, but does not have any signed agreements in place. | No Variance from Baseline | See Service Offerings Attachment | 5 | 0 | 5 | 1 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No anchor institutions were added in the current quarter although signed agreements were reached no fiber was installed to the facilities. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. Over the next few months Zito will install to locations with signed agreements. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No anchor institutions were added in the current quarter although signed agreements were reached no fiber was installed to the facilities. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. Over the next few months Zito will install to locations with signed agreements. | 5 - 100 Mbps subscribers. | 9260 | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | See Service Offerings Attachment | 5276 | 4 | 0 | 4 | 2 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreements with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreement with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. | 2 - 10 Mbps subscribers 2 - 100 Mbps subscribers | See Service Offerings Attachment | FALSE | N/A | Zito will continue to negotiate with critical anchor institutions, business and last mile providers. Zitoâ€™s commercial sales team is actively negotiating with institutions and will continue to do so in the next quarter. Zito currently has signed agreements with 44 CAIs, and Zito will begin to connect these over the next 2 quarters. Zito expects to have connected 38 of these anchor institutions by the end of the quarter. Zito will also continue to negotiate and discuss agreements with last mile providers along the project's path. | Zito Media Communications II, LLC | Zito completed the project build during the quarter and does not expect any challenges or issues in the future that will require BTOP assistance. | Zito does not expect any challenges or issues in the future that will require BTOP assistance.
NT10BIX5570050 | 2013 | Q2 | Q2 - 2013 | During the quarter Zito continued to connect anchor institutions and other customers along the project's path. Zito continued informational brochure mailings to potential anchor institutions. In addition, Zito's commercial division increased meetings and out reach activities with various entities such as chamber of commerces. Based off of this outreach Zito's commercial division was able to sign additional anchor institutions. | 363 | 20 | 0 | 0 | 363 | 0 | 0 | 17 | No Variance from Baseline Report | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | 0 | 2 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is in talks with providers, but does not have any signed agreements in place. | No Variance from Baseline | See Service Offerings Attachment | 37 | 0 | 37 | 1 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito was able to connect 33 anchor institutions in the quarter. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. Over the next couple months Zito will install to locations with signed agreements. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito was able to connect 33 anchor institutions in the quarter. Zito has signed agreements with some CAIs, but the fiber is not installed into these locations. Over the next couple months Zito will install to locations with signed agreements. | 37 - 100 Mbps subscribers. | 9260 | 57 | 57 | 0 | 2 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is currently marketing high speed data and voice services in the last mile areas. | 17 - 10Mbps 40 - 20 Mbps | 5276 | 4 | 0 | 4 | 2 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreements with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreement with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. | 2 - 10 Mbps subscribers 2 - 100 Mbps subscribers | See Service Offerings Attachment | FALSE | N/A | Zito will continue to negotiate with critical anchor institutions, business and last mile providers. Zitoâ€™s commercial sales team is actively negotiating with institutions and will continue to do so in the next quarter. Zito currently has signed agreements with 68 CAIs, and Zito will begin to connect these over the next quarter. Zito expects to have connected at least 63 of these anchor institutions by the end of the quarter. Zito will also continue to negotiate and discuss agreements with last mile providers along the project's path, but Zito plans on having zero agreements signed. | Zito Media Communications II, LLC | Zito continued to connect customers and anchor institutions during the quarter, and does not expect any challenges or issues in the future that will require BTOP assistance. | A potential issue in the upcoming quarter pertains to utility companies finishing engineering and make ready work in order for Zito to connect anchor institutions to the project.
NT10BIX5570050 | 2013 | Q3 | Q3 - 2013 | During the quarter Zito continued to connect anchor institutions and other customers along the project's path. Zito continued informational brochure mailings to potential anchor institutions. With this project Zito Media Communications II, LLC was able to bring broadband internet speeds to our last mile service areas that did not have it previous to this project. Also, the project brought competition and better rates in the project area to anchor institutions and other commercial customers. Zito created 50 jobs under the project. Zito's commercial division is continuing its outreach with economic development groups and chambers of commerce to bring broadband options and services to underserved areas. With this project Zito was able to interconnect anchor institutions, such as a regional medical provider, to allow easy patient file transfers between multiple locations in the region and new broadband services to local governments. Finally, Zito will continue to provide non-discriminatory and open access to the network for all anchor institutions, commercial customers, and last mile providers. | 363 | 20 | 0 | 0 | 363 | 0 | 0 | 17 | No Variance from Baseline Report | The 20 miles are under an IRU agreement between Zito and One Community in Ohio. | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | No Variance from Baseline Report | 0 | 1 | 0 | No agreements have been signed in the past quarter. There are preliminary talks with providers, but no signed agreements. | See Service Offerings Attachment | None | 0 | 0 | 0 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is in talks with providers, but does not have any signed agreements in place. | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito is in talks with providers, but does not have any signed agreements in place. | No Variance from Baseline | See Service Offerings Attachment | 66 | 0 | 66 | 1 | Zito exceeded its baseline projections of 65 connected CAIs by one connecting 66 anchor institutions in total. | No Variance from Baseline | Zito exceeded its baseline projections of 65 connected CAIs by one connecting 66 anchor institutions in total. | 66 - 100 Mbps Subscribers | 9260 | 154 | 154 | 0 | 2 | No Variance from Baseline | Negative variance due to various make ready delays throughout the project resulting in Zito not having the amount of time to connect customers that the baseline projections were based on. | Negative variance due to various make ready delays throughout the project resulting in Zito not having the amount of time to connect customers that the baseline projections were based on. | No Variance from Baseline | 46 - 10Mbps 108 - 20 Mbps | 5276 | 6 | 0 | 6 | 2 | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreements with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. Negative variance due to various make ready delays throughout the project resulting in Zito not having the amount of time to connect customers that the baseline projections were based on. | No Variance from Baseline | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Zito's commercial division is negotiating and signing agreement with businesses, but these entities are not yet connected to the network. This metric will increase over the new few months as these entities are connected. Negative variance due to various make ready delays throughout the project resulting in Zito not having the amount of time to connect customers that the baseline projections were based on. | 2 - 10 Mbps subscribers 4 - 100 Mbps subscribers | See Service Offerings Attachment | FALSE | N/A | Zito will be completing the close out process for the grant in the next quarter. In addition, Zito will be connecting customers that have signed agreements to receive services. | Zito Media Communications II, LLC | Zito was able to work with utility companies in areas where Zito was being held up due to make ready and connect anchor institutions in those areas. | None.
NT10BIX5570051 | 2010 | Q3 | Q3 - 2010 | First Step completed the Environmental Assessment report and Sec. 7 consultations. We are awaiting final approval and issuance of the Finding of No Significant Impact. First Step received clearance for the construction of tower #10 that was submitted to the Federal Aviation Administration for clearance. The bidding process was opened for the tower construction and equipment needs for the project. Reviews of the submitted bids are currently underway. Tower construction contractor has been selected. No construction or equipment purchases were made in Q3 due to the delayed Environmental Assessment and Sec. 7 responses. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | as documented above, no construction has taken place due to the Environmental Assessment/Sec. 7 delay | n/a | as documented above, no construction has taken place due to the Environmental Assessment/Sec. 7 delay | n/a | n/a | as documented above, no construction has taken place due to the Environmental Assessment/Sec. 7 delay | as documented above, no construction has taken place due to the Environmental Assessment/Sec. 7 delay | as documented above, no construction has taken place due to the Environmental Assessment/Sec. 7 delay | 0 | 3 | 0 | no agreements signed | First Step will be providing middle mile Internet transport on this newly built network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | 0 | 0 | n/a | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no special offerings | FALSE | no change | First Step will have the Finding of No Significant Impact issued. With the Finding of No Significant Impact in hand, purchasing and construction will begin. Additional effort will be expending to try and get the project caught up in terms of deployment goals. Winter weather will be a significant factor in our ability to catch up in this 4th quarter. | First Step Internet, L.L.C. | First Step did not meet the Q3 quarterly projections due to delays in the Environmental Assessment/Sec. 7 / Finding of No Significant Impact process. Broadband Technology Opportunities Program has been helpful in working with the United States Fish and Wildlife Service to move the process forward. | Winter weather will likely be the largest challenge. As possible, First Step will increase efforts and deployed assets on the project to get it caught up and on schedule after the extended 2nd quarter delays. First Step will continue to work with Program officer to resolve program questions that surround equipment life, taxation and security interests.
NT10BIX5570051 | 2010 | Q4 | Q4 - 2010 | Environmental Assessment was completed and a Finding of No Significant Impact was issued. Final review of bids for construction and major equipment purchases were completed. Continued work with Federal Program Officer to address federal program matching requirements. Continued community outreach efforts by answers questions from those potentially impacted by the proposed network build. Worked with local TV station to produce a short 30 second TV public announcement of the project. No construction was completed in the quarter due to the onset of winter weather at our tower construction sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no construction started due to winter weather conditions | n/a | no construction started due to winter weather conditions | n/a | n/a | no construction started due to winter weather conditions | no construction started due to winter weather conditions | no construction started due to winter weather conditions | 0 | 3 | 0 | no agreements signed | First Step will be providing middle mile internet transport on this newly built network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | due to the delays in construction, the negotiations for new and improved access have not occurred. Once construction in underway the appropriate negotiations can begin. | due to the delays in construction, the negotiations for new and improved access have not occurred. Once construction in underway the appropriate negotiations can begin. | n/a | $100/meg/month | 0 | 0 | 0 | 0 | 00 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no special offerings | FALSE | no change | With the approved Environmental Assessment and the issued Finding of No Significant Impact, First Step has cleared the last significant Federal hurdle for the start of construction. Additionally, First Step has completed the equipment and construction bidding and review process. We are ready and posed to start construction when the weather allows. We anticipate construction to begin late in the 1st quarter with equipment purchasing and provisioning to start at approximately the same time. | First Step Internet, L.L.C. | Project construction is currently on hold due to the onset of winter weather conditions at our tower sites and locations. First Step will continue to work with the Federal Program Officer to address federal matching requirements while we await the official word from NTIA concerning allowable uses of program revenue. | Winter weather will be the most significant challenge. Currently we have tower locations under 10 feet of snow. It is impossible to being work. If we get an early spring we will be able to start tower construction as soon as possible. First Step will continue to work directly with the Federal Program Officer to address ongoing questions concerning taxation, security interests and use of Program Revenue.
NT10BIX5570051 | 2011 | Q1 | Q1 - 2011 | Tower construction contract was signed and equipment ordering began. Primary equipment vendor selection was made. Contract for equipment purchasing is drafted. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | construction not started | n/a | construction not started | n/a | n/a | construction not started | construction not started | construction not started | 0 | 3 | 0 | no agreements signed | First Step will be providing middle mile internet transport on this newly built network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | construction delays due to weather conditions have prevented negotiations from moving forward | construction delays due to weather conditions have prevented negotiations from moving forward | n/a | $100/meg/month | 0 | 0 | 0 | 0 | no subscribers | no subscribers | no subscribers | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no special offerings | FALSE | no change | In ground construction will begin. As weather allows, ground preparation for tower sites will begin. Concrete foundations for towers will be poured. Site communication huts will be constructed and prepared for delivery to tower site locations. Primary radio path frequencies will be planned, finalized and submitted to the Federal Communications Commission (FCC) for approval. Initial electronic equipment will be purchased. First of 69 radio paths will be built. | First Step Internet, L.L.C. | Winter weather continued to delay in ground project construction. Matching discussion with Federal Program officer ongoing concerning use of Program Revenue. Reference 2e. (construction permits) An access road dispute has occurred between the land owner of the First Step leased ground for the tower site and an adjacent land owner. The land owner asserts that a portion of the access road crosses his land. This access road has been in use for over 20 years and this issue has just come up as part of the Conditional Use Permit process. Latah County added as a stipulation of the grant of the Conditional Use Permit, that First Step resolve the land access dispute between the parties. The parties are negotiating between themselves and a resolution is expected during Q2. | With improved weather conditions, project construction will begin in full force. Additional crews will be prepared to assist in accelerating the deployment of radio paths to close the construction schedule delays. With construction underway and administrative hurdles cleared, First Step will be working to meet the project deadlines and projected milestones.
NT10BIX5570051 | 2011 | Q2 | Q2 - 2011 | Phase 1 of our microwave radio equipment was purchased and delivered. First Step completed its required audits with no findings. First Step hosted the Federal Program officer on a site visit to review procedures and to get a first hand look at the project and progress. Construction of the first tower site, Lewiston Rim, began. This signifies the first actual site construction and a physical start to the project. Additional tower climbing staff was trained and certified to assist in keeping the project on schedule. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | construction not started | n/a | construction not started | n/a | n/a | construction not started | construction not started | construction not started | 0 | 3 | 0 | no agreements signed | First Step will be providing middle mile internet transport on this newly built network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | construction delays due to weather have prevented negotiations from moving forward | construction delays due to weather have prevented negotiations from moving forward | n/a | $100/meg/month | 0 | 0 | 0 | 0 | no subscribers | no subscribers | no subscribers | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no special offerings | FALSE | no change | Construction will proceed at an increased rate. Tower sites will be prepped and constructed. Phase 1 and Phase 2 of the microwave radio paths will be installed, tested and brought online. This will result in 21 Community Anchor Institutions being connected and 150 miles of microwave network being built. | First Step Internet, L.L.C. | Winter weather has finally broken in our area and construction can move forward. Ongoing discussions with the Federal Program Officer about matching funds and the use of Program revenue. We are aware there is discussion and further guidance that will be released concerning this matter. | With the improved conditions, First Step will move ahead with all aspects of the project build. Given the short construction season and the increased pressure to get the project back on schedule, staffing resources may be one of the biggest challenges. To address this, First Step has trained and certified additional staff in tower climbing safety and microwave installation. The additional resource will help us ensure the project will be completed in a timely and on budget manner.
NT10BIX5570051 | 2011 | Q3 | Q3 - 2011 | Construction began on 7 of the 10 planned tower sites. Spud Hill, Lewiston Rim, Paradise Ridge, West Twin and Winchester Grade all have the towers standing. Kamiah and Mt. Ida (Grangeville) have had their foundations poured and are awaiting the 30 day curing time before the towers can be built. First Step completed 13 microwave paths accounting for 88.9 new path miles. 6 Community Anchor Institutions were connected to the network. They consisted of 4 schools and 2 libraries. Equipment purchasing of the Phase 2 microwaves was completed. | 89 | 0 | 0 | 0 | 0 | 13 | 5 | 0 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step actually only 3 quarters into the construction schedule. With 89 miles completed, this puts us right in line with our anticipated time schedule. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step actually only 3 quarters into the construction schedule. With 13 wireless paths completed, this puts us right in line with our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step actually only 3 quarters into the construction schedule. With 5 towers completed, this puts us right in line with our anticipated time schedule. | Electronics are not yet in place for interconnection at the new constructed tower sites. | 0 | 3 | 0 | no agreements yet signed. | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 6 | 1 | 5 | 1 | Early environmental and weather delays have caused the connection of the Community Anchor Institutions to be delayed. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Speeds tiers are flexible and available in 1 meg increments. Current packages are 3 to 10 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings. | FALSE | no change. | First Step will continue construction of the microwave network. This will include bringing the new tower sites online as well as additional microwave paths being built. First Step projects 36 new paths resulting in 212 path miles and 21 Community Anchor Institutions being completed by the end of Q4 2011. Phase 3 microwave radios will be acquired and delivered. First Step will attempt to have the final 3 tower site foundations poured by the end of the quarter. This will help get a jump on the Spring construction season as we won't be waiting for the ground to dry to begin digging new foundations. As part of the community outreach program, First Step will be designing a product brochure that can be distributed to interested parties and potential new network and last mile broadband partners. | First Step Internet, L.L.C. | First Step made good progress on the overall project. There was a two week delay on Paradise Ridge while a County setback issue was worked through and resolved. There is a land use/access issue that has come up on Mt. Ida. The US Forest Service has an easement to the property that was leased to First Step Internet by the land owner. First Step is working with the local US Forest Service Manager to resolve the issue. We expect that construction will be able to move forward by the end of October. This delay is not expected to add any significant delay to the project. First Step is working with Federal Program Officer to assist with loan collateralization so that project expenditures can proceed at an increased pace to meet program requirements. | Winter weather is already on it way on the higher mountain tops. The Mt. Ida (Grangeville site) is currently on hold while an access issue is addresses with the US Forest Service. Hopefully this will resolve quickly before we are snowed out at that elevation. The crews are working to get the foundations dug and poured in Elk City before the snow comes. This would be a big help as we await spring next year. Due the delays and compacted build out schedule, time of the labor used as match becomes an issue. We are working with our Federal Program Officer as well as our bank to secure funding that can be used to meet the match in lieu of the labor so as to always be in compliance with the Federal matching requirement.
NT10BIX5570051 | 2011 | Q4 | Q4 - 2011 | First Step Internet, LLC has completed 9 of 10 tower builds. The foundation for the 10th tower, Mt. Ida, has been poured. Construction of the tower is expected in the early Spring as soon as the weather allows. Additionally, 39 of 69 licensed microwave paths were completed. This represents nearly 255 new path miles. First Step has connected 22 anchor institutions to the network. Microwave equipment purchasing was completed for Phase 3 (next 12 paths) of the microwave project. First Step began negotiations with a vendor to assist with project compliance, project management and reporting. We submitted a sole source request which has been approved. | 255 | 0 | 0 | 0 | 0 | 39 | 9 | 6 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 4 quarters into the construction schedule. With 255 miles completed, this puts us ahead of our anticipated time schedule. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 4 quarters into the construction schedule. With 39 wireless paths completed, this puts us ahead of our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 4 quarters into the construction schedule. With 9 towers completed, this puts us right in line with our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 4 quarters into the construction schedule. With 6 interconnection points available, this puts us right in line with our anticipated time schedule. | 0 | 3 | 0 | no agreements yet signed. | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 22 | 2 | 20 | 1 | Early environmental and weather delays have caused the connection of the Community Anchor Institutions to be delayed. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Speeds tiers are flexible and available in 1 meg increments. Current packages are 3 to 10 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | First Step will complete Phase 3 of the project build. This phase will complete 12 additional paths and connect 6 additional community anchor institutions. This project phase should also include the signing of the first last mile distribution client to the network. With the bulk of the network now completed, First Step will also increase the community outreach efforts to emphasize the regional network benefits for all residents, not just the Community Anchor Institutions. First Step will have a vendor on board to help assist with project management, reporting and compliance. This will help the staff at First Step stay focused on the physical construction and deployment of the broadband middle mile network. | First Step Internet, L.L.C. | First Step has made great progress on the project this quarter. First Step believes the previously reported easement issue/concern with the United States Forest Service is being addressed appropriately and expect that we will be able to move forward with the final tower erection when the snow recedes on Mt. Ida. (High Camp) | Winter weather through Q1 2012 will slow the deployment and project progress. However with an anticipated 80% completed by the end of Q1, First Step will be ahead of our construction schedule and will meet the 67% progress measurement by 2/28/2012. First Step will continue to staff additional resources on the project to ensure that deadlines and project milestones are completed and timely. First Step continues to meet it deployment and matching requirements for this project.
NT10BIX5570051 | 2012 | Q1 | Q1 - 2012 | Phase 3 of the project build schedule was completed. First Step has completed 53 of the planned 69 fixed microwave paths. 6 additional community anchor institutions were added to the network. First Step completed the hiring of a vendor to assist with the project management and compliance efforts. Due to the dominating winter weather in the region during Q1, there were limited outreach and last mile construction efforts. | 379 | 0 | 0 | 0 | 0 | 53 | 9 | 7 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 5 quarters into the construction schedule. With 379 miles completed, this puts us ahead of our anticipated time schedule. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 5 quarters into the construction schedule. With 53 wireless paths completed, this puts us ahead of our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 5 quarters into the construction schedule. With 9 towers completed, this puts us right in line with our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 5 quarters into the construction schedule. With 6 interconnection points available, this puts us right in line with our anticipated time schedule. | 0 | 3 | 0 | no agreements yet signed. | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 28 | 6 | 22 | 1 | Early environmental and weather delays have caused the connection of the Community Anchor Institutions to be delayed. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Speed tiers are flexible and available in 1 meg increments. Current packages are 3 to 10 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | First Step will complete the equipment procurement for the final Phase 4 of the network project. First Step will complete 6 of the remaining 16 paths and will be poised to complete the final 10 paths with the snow having receded from the high mountain tops. The 6 paths will add an additional 4 Community Anchor Institutions and 20 new paths miles. The 10th and final tower will be erected paving way for several new microwave paths to be constructed. With the final tower being constructed and completed we will be able to continue with our negotiations with additional last mile providers. However, since we anticipate the tower construction to occur towards the end of the quarter, we do not anticipate any signed agreements in this quarter. With the bulk of the project completed First Step will begin to look at long term enhancements to the project and will work with the program staff to seek approval for the use of remaining project budget to further improve and enhance the project as planned and built. Outreach will begin with the better weather and negotiations for last mile and middle providers will begin. | First Step Internet, L.L.C. | The winter weather kept the project slowed, however this slowdown of progress was expected, forecasted and planned. The project is on track and target to be completed in accordance with the submitted and approved project improvement plan. First Step is waiting on the receding snow levels to once again begin the final network deployment stages of our project. | First Step anticipates no significant project challenges as we move into the final phases of the project development and construction. First Step will continue to work to have the physical construction of the network well ahead of the planned schedule and required 2/28/2013 end of project date.
NT10BIX5570051 | 2012 | Q2 | Q2 - 2012 | First Step continued to prep for the building season. We received the equipment necessary for the Elk City build out. First Step continued to work closely with the US Forest Service to finalize permission to complete construction of the Mt. Ida (HighCamp) site. First Step began the process of working with the NTIA and the Federal Program officer on 2 potential tower upgrades that would improve safety as well as provide additional opportunities for potential network and asset utilization. Most of the remaining project is located in very remote and nearly inaccessible locations during the Spring, for this reason there were no new path miles or CAI's connected to the network. | 379 | 0 | 0 | 0 | 0 | 53 | 9 | 7 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 6 quarters into the construction schedule. With 379 miles completed, this puts us 21 miles short of our projection for this time in the project. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 6 quarters into the construction schedule. With 53 wireless paths completed, this puts us ahead of our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 5 quarters into the construction schedule. With 9 towers completed, this puts us right in line with our anticipated time schedule | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 6 quarters into the construction schedule. With 7 interconnection points available, this puts us right in line with our anticipated time schedule. | 0 | 3 | 0 | no agreements yet signed | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 28 | 6 | 22 | 1 | Early environmental and weather delays have caused the connection of the Community Anchor Institutions to be delayed. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Speed tiers are flexible and available in 1 meg increments. Current packages are 3 to 10 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | First Step is anticipating completion of the construction portion of the award during Q3. This anticipate an early Q3 resolution of the Mt. Ida issue concerning the US Forest Service. During the quarter First Step would complete 16 microwave paths, resulting in 165 new path miles and 12 new Community Anchor Institutions. First Step also hopes to begin construction on 2 new additional tower sites once the appropriate approvals are provided. With the bulk of the project completed First Step will begin to look at long term enhancements to the project and will work with the program staff to seek approval for the use of remaining project budget to further improve and enhance the project as planned and built. Outreach will begin with the better weather and negotiations for last mile and middle providers will begin. | First Step Internet, L.L.C. | The spring weather and the remoteness of the locations was the largest challenge to our progress for Q2 2012. The project is on track and target to be completed in accordance with the submitted and approved project improvement plan. First Step is waiting on the receding snow levels to once again begin the final network deployment stages of our project. First Step has requested approval to build an additional 2 towers and would appreciate whatever assistance can be provided to move that request through the administrative process as quickly as possible. Time is very short given the pending winter weather and the long lead times necessary for tower construction. | With the unsettled Spring weather behind us, First Step anticipates no significant weather delays for the remainder of the project. First Step remains working with the US Forest Service to resolve the HighCamp site. Additionally, First Step will be working closely with the State and Tribal Historic Preservation Officers to mitigate any historical concerns they may have with the 2 additional tower sites. If these can be resolved quickly, First Step is hopeful construction of those towers will be completed in Q3 2012 along with the remaining planned paths.
NT10BIX5570051 | 2012 | Q3 | Q3 - 2012 | First Step Internet, LLC completed 6 additional paths during this quarter. These paths resulted in an additional 65 fixed microwave miles and will provide service to 4 community anchor institutions. First Step also completed the final review and received approval from the US Forest Service to continue our construction efforts on Mt. Ida (High Camp). This location is critical to the deployment of service to the previously un-served community of Elk City, Idaho. First Step was given permission to construct an additional tower on McGary Butte, Idaho through the AAR process. First Step continued to move forward on its other pending AAR concerning construction of a 2nd additional tower through the AAR process. First Step is working with the area THPO to address historical and archeological potential concerns. | 444 | 0 | 0 | 0 | 0 | 59 | 9 | 12 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 7 quarters into the construction schedule. With 444 miles completed, this puts us 36 miles short of our projection for this time in the project. The release of the High Camp tower will allow us to complete the remaining path miles required. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 7 quarters into the construction schedule. With 59 wireless paths completed, this puts us ahead of our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 7 quarters into the construction schedule. With 9 towers completed, this puts us ahead of our anticipated time schedule | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 7 quarters into the construction schedule. With 7 interconnection points available, this puts us right in line with our anticipated time schedule. | 0 | 3 | 0 | no agreements yet signed | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 32 | 9 | 23 | 1 | Early environmental and weather delays have caused the connection of the Community Anchor Institutions to be delayed. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Initial project delays have reduced the number of Community Anchor Institutions on the network at this point in time. | Speed tiers are flexible and available in 1 meg increments. Current packages are 3 to 10 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | With the High Camp tower site now approved by the US Forest Service, First Step can complete the final tower construction as well as complete the building of the remaining 10 microwave paths. First Step will also complete construction of the newly approved McGary Butte tower site. First Step will continue to work closely with the NTIA and area THPO for final approval of the Gilbert Grade tower site. Construction will begin on that site as soon as project approval is given. First Step estimates 4th quarter construction will result in an additional 101 microwave path miles. These path miles will connect an additional 11 CAI's to the network. First Step will continue ongoing discussions with potential broadband / last mile providers and anticipates there will be one signed contract by the end of the quarter. | First Step Internet, L.L.C. | The delay of the release of the continued construction permit did not allow First Step to complete the remaining 10 paths of the project. With the US Forest Service permit for High Camp in hand, First Step can now move forward quickly to finish the remain tower construction necessary as well as install the remaining 10 microwave paths. First Step has not received approval to begin construction on the Gilbert Grade additional tower site. First Step is working with the area THPO to address any additional concerns they may have. This tower site is located such that if given approval, work could likely continue on the site in all but the worst of the winter weather conditions. First Step would like request the fully and continued support of NTIA as we work towards a solution that will allow for this tower to be constructed. | First Step anticipates no further challenges in completing the project as originally planned. All tower sites and now cleared for final build out. First Step is hopeful that any further questions or concerns with the Gilbert Grade tower site can be resolved quickly and efficiently. While it is anticipated that construction at that site can and will continue through the winter months, it is certainly a quicker process to build that site before the harsh winter weather sets in. First Step will seek the help of the NTIA to work through the projected time line of the study required for the Gilbert Grade new tower site. The projected time required to complete the archeological study, review and report will push us beyond Q4 2012 for completion.
NT10BIX5570051 | 2012 | Q4 | Q4 - 2012 | First Step Internet, LLC completed 9 paths in Q4 2012. These paths added ~100 fixed microwave miles. A total of 540 microwave path miles have now been constructed. The microwave path installations added 8 new community anchor institutions during this quarter. 40 CAI's have now been added to the network. First Step completed construction of the McGary Butte tower during the winter quarter. The Nez Perce Tribal Historic Office was contracted to perform a study for the pending Gilbert Grade site. That study is currently underway and First Step is awaiting the final action report to be submitted. First Step has 4 paths and 1 tower remaining at this time for completion of the project. | 540 | 0 | 0 | 0 | 0 | 68 | 11 | 13 | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is actually only 8 quarters into the construction schedule. With 540 miles completed, this puts us right in line with our projected path miles that would be completed during the project timeline. | n/a | n/a | n/a | n/a | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is 8 quarters into the construction schedule. With 68 wireless paths completed, this puts us ahead of our anticipated time schedule. | First Step was delayed nearly 1 year from the time of award until construction began. From the baseline project report, First Step anticipated being shovel ready and would be allowed to start construction with the acceptance of the award. The Environmental Assessment greatly delayed the start of the project. First Step is 8 quarters into the construction schedule. With 11 new towers completed, this puts us ahead of our anticipated time schedule. First Step's original project called for 10 towers. First Step asked for and was granted permission to construct 2 additional towers. 1 of those has been completed and as previously documented, First Step is awaiting THPO clearance to begin construction on the 12th and final tower. | First Step has completed all of its anticipated and planned interconnection points. | 0 | 3 | 0 | No agreements yet signed. | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 40 | 13 | 27 | 1 | First Step is 3 CAI's short of its planned 43 CAI's. The remaining 3 CAI's are scheduled to be installed in January 2013. First Step has caught up to its projections after a slow start due to the delays in the Environmental Analysis and weather. | First Step has caught up to its projections after a slow start due to the delays in the Environmental Analysis and weather. | First Step has caught up to its projections after a slow start due to the delays in the Environmental Analysis and weather. | Speed tiers are flexible and available in 1 meg increments. Current packages are 3 to 100 megs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | With the final approval of the Gilbert Grade tower from the Nez Perce Tribal Historical Preservation office, First Step will complete the 12th and final tower of the project. First Step will also complete the remaining 4 fixed microwave paths, resulting in ~10 microwave path miles and 3 community anchor institutions. First Step will continue to work with potentially interested broadband / last mile providers for their connections to the network. | First Step Internet, L.L.C. | First Step was given final approval in the quarter to begin construction on both the McGary Butte and High Camp (Mt. Ida) tower sites. Both of these tower sites were built and completed during Q4 2012. First Step has not received the written approval from the Nez Perce Tribal Historic Preservation office for the Gilbert Grade site. We do anticipate approval soon for this final tower. Tower construction is expected to take 45 days from approval. First Step will be working with the Federal Program Officer to consider a time only waiver for the completion of the remaining tower. This tower site is located such that if given approval, work could likely continue on the site in all but the worst of the winter weather conditions. First Step would like request the fully and continued support of NTIA as we work towards a solution that will allow for this tower to be constructed. | First Step is ready to construct the final tower, build the last of the microwave miles and complete the connection of the remaining 3 CAI's to the network. At this time, we do not anticipate any further delays that would keep us from completing the project within the next quarter.
NT10BIX5570051 | 2013 | Q1 | Q1 - 2013 | First Step completed the final 4 paths of its project in Q1 2013. These paths added 11 fixed microwave miles. The microwave path installations added 4 new community anchor institutions during this quarter. First Step received clearance from the Nez Perce Tribal Historic Office to proceed with the construction of the Gilbert Grade tower site. First Step was given final approval for the site from the BTOP team as well. Construction was started on the site and the concrete was poured for the foundation of the tower. The tower was erected and standing on 3/29/2013. With the tower standing, the last of the originally approved project was completed. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved router change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process | All anticipated interconnection points were installed. | 0 | 3 | 0 | no agreements yet signed. | First Step will be providing middle mile internet transport on the newly constructed network. Pricing will be based on the amount of bandwidth requested across the network in 1 megabit increments at $100/meg/month. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 44 | 17 | 27 | 1 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | Speed tiers are flexible and available in 1 meg increments. Current packages are 3 to 100 megs. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. This route modification would add 7 new microwave paths to the project. These paths would add an additional 20 miles and connect 6 new CAI's. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers. First Step continues to work with the FPO team to secure a no-cost time extension that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 7 new microwave paths totaling 20 miles, 2 improved paths totaling 54 miles and the addition of 6 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR.
NT10BIX5570051 | 2013 | Q2 | Q2 - 2013 | Q2 was spent making small adjustments and refinements to the existing network that was built. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved router change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process | All anticipated interconnection points were installed. | 0 | 3 | 0 | no agreements yet signed | Pricing is flexible and dependent upon each requested path. As a basis we have always stated that pricing would start at $100/meg. As is typical in the industry, as more bandwidth is purchased the pricing /meg typically comes down. As such, we donâ€™t have fixed pricing plans or tiers. With the network we are able to construct a network path of whatever bandwidth is necessary for the client anywhere from 1 meg to 100 megs. Pricing is dependent also on other market factors occurring over the 4 year period of the award. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100meg/month | 44 | 17 | 27 | 1 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Current CAI customers are purchasing speed packages from 3 to 50 megs. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | $100/meg/month | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | $100/meg/month | no special offerings | FALSE | no change | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. This route modification would add 7 new microwave paths to the project. These paths would add an additional 20 miles and connect 6 new CAI's. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers. First Step continues to work with the FPO team to secure a no-cost time extension that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 7 new microwave paths totaling 20 miles, 2 improved paths totaling 54 miles and the addition of 6 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR. As this is the last quarter for the project, we need as much assistance and cooperation in working with each of the above entities as possible. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through.
NT10BIX5570051 | 2013 | Q3 | Q3 - 2013 | Q3 was spent making small adjustments and refinements to the existing network that was built. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. An additional no cost time extension was requested and approved for the project. As our area is heading into winter and a potential delay in the final approvals, First Step anticipated the need for a longer extension so that construction can resume once Spring comes back around. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved router change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process | All anticipated interconnection points were installed. | 0 | 3 | 0 | no agreements yet signed | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100meg/month | 44 | 17 | 27 | 14 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 7 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | no special offerings | FALSE | no change | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. The modifications to the originally approved project would result in 7 new microwave paths totaling 20 miles, 2 improved paths totaling 54 miles and the addition of 6 new CAIâ€™s and 1 improved CAI. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 7 new microwave paths totaling 20 miles, 2 improved paths totaling 54 miles and the addition of 6 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR. As winter weather begins to set in, we need as much assistance and cooperation in working with each of the above entities as possible. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 7 new microwave paths totaling 20 miles, 2 improved paths totaling 54 miles and the addition of 6 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project.
NT10BIX5570051 | 2013 | Q4 | Q4 - 2013 | Q4 was spent working with BTOP and the EHP team to address Sec. 106 Compliance issues. A consultant was hired to help with the process. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. Several compliance related conference calls were held to discuss reporting and progress. First Step worked through the quarter on compliance issues and maintaining the currently constructed network. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved route change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | no agreements yet signed | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | no providers yet signed due to the early weather and environmental construction delays. | no providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. Total subscribers is down 1 from the previously reported 44. The correction is due to a counting error that occurred in Q4 2011 and Q1 2012. A CAI was double counted when listed as being installed in both quarters. 43 is the correct installed CAI number. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | no special offerings | FALSE | no change | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. First Step anticipates the work with the historical consultant will be completed by the end of February. We will continue working with the EHP and SHPO teams for final approval by the end of the quarter. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. First Step is working with EHP and has hired a consultant to assist with the review of the pending sites. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR. As winter weather has set in, we need as much assistance and cooperation in working with each of the above entities as possible. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project.
NT10BIX5570051 | 2014 | Q1 | Q1 - 2014 | Q1 was spent working with BTOP and the EHP team to address Sec. 106 Compliance issues. A consultant was hired to help with the process. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. Several compliance related conference calls were held to discuss reporting and progress. First Step worked through the quarter on compliance issues and maintaining the currently constructed network. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved route change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | No agreements yet signed. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | No providers yet signed due to the early weather and environmental construction delays. | No providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. First Step anticipates the work with the historical consultant will be completed by the end of April. We will continue working with the EHP and SHPO teams for final approval by the end of the quarter. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. First Step is working with EHP and has hired a consultant to assist with the review of the pending sites. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR. With the arrival of spring time, the possible construction season has opened. We need as much assistance and cooperation in working with each of the above entities as possible to get the project moving forward once again. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project.
NT10BIX5570051 | 2014 | Q2 | Q2 - 2014 | Q2 was spent working with BTOP and the EHP team to address Sec. 106 Compliance issues. A consultant was hired to help with the process. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. Several compliance related conference calls were held to discuss reporting and progress. First Step worked through the quarter on compliance issues and maintaining the currently constructed network. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved route change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | No agreements yet signed. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | No providers yet signed due to the early weather and environmental construction delays. | No providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. There is a current request for a route modification that is working its way through the process. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. First Step anticipates the work with the historical consultant and the resulting report will be submitted in early July. We hope to have approval to move forward by the end of July. We will continue working with the EHP and SHPO teams for final approval and project completion by the end of the quarter. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project. First Step is working with EHP and has hired a consultant to assist with the review of the pending sites. | First Step continues to work with the THPO, SHPO and the US Forest Service for the final Sec. 106 clearances necessary for the remaining path builds as presented in our AAR. We need as much assistance and cooperation in working with each of the above entities as possible to get the project moving forward once again. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through. First Step continues to work with the FPO team and was granted a no cost project extension on September 18, 2013 that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 19 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are schools within the previously approved area of the 5 county project.
NT10BIX5570051 | 2014 | Q3 | Q3 - 2014 | Q3 was spent working with BTOP and the EHP team to address Sec. 106 Compliance issues. A consultant was hired to help with the process. We continue to work with the NTIA, the US Forest Service, the NezPerce THPO and Idaho SHPO for our final approvals required to resume construction on the final paths of the project. Several compliance related conference calls were held to discuss reporting and progress. First Step worked through the quarter on compliance issues and maintaining the currently constructed network. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. With the approved route change modifications, we ended the original project period with 72, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | No agreements yet signed. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | No providers yet signed due to the early weather and environmental construction delays. | No providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. Revised AAR 2502254 has been submitted and will be reviewed when EHP has completed its overarching review of the project. The modifications to the originally approved project would result in 6 new microwave paths totaling 18 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. First Step Internet will continue working with the EHP and SHPO teams for final approval and project completion by the end of the quarter. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on September 17, 2014 (with Grants Office approval on 10/8/2014) that will allow us to add additional CAI's and other network improvements. The modifications to the originally approved project would result in 6 new microwave paths totaling 18 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. All are locations within the previously approved area of the 5 county project. This work will be completed, weather permitting, when EHP concludes its overarching review. First Step is working with EHP and hired a consultant to assist with the review of the pending sites. NTIA received the consultant's report on 7/24/2014. The report was sent to SHPO and THPO on 8/7/2014 and 8/27/2014, respectively, for further consultation which continued through the third quarter. | First Step plans to continue working with NTIA and the FPO team to add additional CAI's to the project. Revised AAR 2502254 has been submitted and will be reviewed when EHP has completed its overarching review of the project. The modifications to the originally approved project would result in 6 new microwave paths totaling 18 miles, 2 improved paths totaling 54 miles and the addition of 5 new CAIâ€™s and 1 improved CAI. We need as much assistance and cooperation in working with each of the above entities as possible to get the project moving forward once again. The timelines are short but we believe we still have time in the project to complete the work if the approvals come through.
NT10BIX5570051 | 2014 | Q4 | Q4 - 2014 | Q4 2014 was spent working with BTOP and the EHP team to address the Sec. 106 Compliance issues. All outstanding issues were resolved and on 12/10/2014 an AAR was opened to finalize the documentation of First Step's response to the suspension, AAR# 2514374. Additionally, much work was done to open a final AAR for project improvements and additions, AAR# 2516131. Both AAR's are still pending. A final no cost project extension AAR was opened and approved on 10/16/2014, AAR#2500464. The project end date has been approved and extended to 9/30/2015. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. As of the end of the year 72 paths were completed, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | No agreements yet signed. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 0 | No providers yet signed due to the early weather and environmental construction delays. | No providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. First Step plans to install one new additional CAI in the coming quarter. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team to gain approval for AAR# 2516131. First Step submitted AAR# 2516131 that would add 6 project modifications. The modifications to the originally approved project would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. This work will be begin, weather permitting, when EHP and the FPO have completed their reviews and approvals of the projects. Once approved First Step will begin work immediately on the approved projects. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on 10/16/2014 which will allow us to add an additional CAI and complete other network improvements. First Step submitted AAR# 2516131 that would add 6 project modifications. The modifications to the originally approved project would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. This work will be begin, weather permitting, when EHP and the FPO have completed their reviews and approvals of the projects. | First Step submitted AAR# 2516131 that would add 6 project modifications. The modifications to the originally approved project would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. This work will be begin, weather permitting, when EHP and the FPO have completed their reviews and approvals of the projects. Winter weather will potentially slow some of the project plans, however the majority of the projects can move forward through the winter once approved. Specifically the project involving Hemlock Butte and Iron Mountain won't move forward until the winter weather begins to recede, all other projects can move forward once approved.
NT10BIX5570051 | 2015 | Q1 | Q1 - 2015 | Q1 2015 was spent addressing the final requirements to lift the suspension thus allowing First Step to go back to work completing the project. AAR#2514374 was officially approved 1/5/2015. AAR#2516131 was submitted to request additional project work to be completed. That AAR was approved 2/9/2015. 3/2/2015 received final approval from SHPO for a portion of the project that involved a 40' tower extension. First Step submitted a budget modification, AAR#2527467 was submitted 3/9/2015 to support the remaining construction work and this AAR was approved 3/20/2015. First Step began working on the projects contained in AAR#2516131. Equipment has been ordered and schedules have been created for the deployment of the equipment and completion of the tasks outlined in the AAR. | 551 | 0 | 0 | 0 | 0 | 72 | 12 | 13 | First Step had a baseline of 550 network miles to deploy. At 551 deployed we are in line with our original projections. | n/a | n/a | n/a | n/a | First Step originally planned 69 microwave paths. As of the end of the year 72 paths were completed, 3 ahead of our projections. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 3 | 0 | No agreement yet signed. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 100 | No providers yet signed due to the early weather and environmental construction delays. | No providers yet signed due to the early weather and environmental construction delays. | n/a | $100/meg/month | 43 | 17 | 26 | 14 | First Step completed all builds to the projected CAI's. First Step plans to install one new additional CAI in the coming quarter. | First Step met the expected project indicators for installations to new subscribers. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team as we work towards completion of the project. If the early Spring weather holds, First Step anticipates being able to complete all 6 projects contained in AAR#2516131. This would include all equipment procurement, installation, turn up and testing. The approved projects would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. Once the 6 projects are completed, First Step will immediately move forward with close out procedures. | First Step Internet, L.L.C. | Despite the winter delays and the delays in the final approval for tower construction, First Step was able to complete all of the initially planned paths and towers as of 6/30/2013. First Step continues to work with the FPO team and was granted a no cost project extension on 10/16/2014 which will allow us to add an additional CAI and complete other network improvements. First Step submitted AAR# 2516131 that would add 6 project modifications. The AAR was approved on 2/9/2015. The modifications to the originally approved project would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. This work will be begin, weather permitting, when EHP and the FPO have completed their reviews and approvals of the projects. | With all approvals in place for all aspects of the project the only anticipated delays at this time would be due to weather. If the early Spring weather holds, First Step anticipates completed of all construction tasks by the end of Q2.
NT10BIX5570051 | 2015 | Q2 | Q2 - 2015 | First Step Internet spent the quarter working on completing project tasks associated with AAR# 2516131. Specifically, project #1 of the AAR saw 7 of the 8 sites have the equipment physically installed. The testing of this network build continues and we are awaiting the final network controller and management hardware to arrive to take the project fully live. The final distribution site will be installed in the first 2 weeks of Q3. Project #2 was completed resulting in ~3 improved path miles and much improved service for the school. Project 4 of hte AAR was completed resulting in ~7 improved path miles and building the foundation for improved network performance of the LTE core distribution network. Project 5 was completed resulting in ~25 new path miles and 1 new CAI. This connection provides a vital connection path for this remote clinic back to the primary regional health care facility in the area. Projects #3 and #6 saw no progress as we await clear and dry weather on the mountain tops so that access to the remote sites can be made. | 576 | 0 | 10 | 0 | 0 | 75 | 12 | 13 | 25 new network miles were installed in this quarter. This puts us on target with our projections. The current number of miles deployed (586 new,10 upgraded) are the final target numbers for the project. | n/a | The approved upgraded miles puts us on target with projections. | n/a | n/a | 3 new paths were approved and installed. | First Step has added 12 new towers as part of its project. The original project had 10 and there were 2 additional towers approved through the process. | All anticipated interconnection points were installed. | 0 | 1 | 0 | No agreements yet signed. First Step reports 2 fewer ongoing contract negotiations. 1 provider built their own network with BTOP funding and the other potential provider partnered with the funded entity. The remaining provider is still in their own contract negotiations with potential clients that would drive the need for a wholesale agreement with First Step. | Pricing is flexible and dependent upon each requested path, as such, we donâ€™t have fixed pricing plans or tiers. CAI and Wholesale list pricing starts at $100/meg. Final pricing is dependent upon many factors. Factors such as expected usage, competitive pricing, other services customer may be purchasing as part of package, numbers of sites customer is servicing through First Step, collocation agreements at site or other sites, current pricing, etc all are factored into the final negotiated price with customer. | First Step will operate the network. | 0 | 0 | 0 | 100 | No providers yet signed. First Step reports 2 fewer ongoing contract negotiations. 1 provider built their own network with BTOP funding and the other potential provider partnered with the funded entity. The remaining provider is still in their own contract negotiations with potential clients that would drive the need for a wholesale agreement with First Step. | No agreements yet signed. | n/a | $100/meg/month | 44 | 18 | 26 | 14 | First Step completed all builds to the projected CAI's. | First Step met the expected project indicators for installations to new subscribers. One new CAI installed this quarter. | First Step met the expected project indicators for installations to improved access subscribers. | First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows:Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 7 12/12: 2 20/20: 1 30/30: 6 Total 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | No new special offerings. | FALSE | No change. | First Step plans to continue working with NTIA and the FPO team as we work towards completion of the project. First Step anticipates being able to complete the remaining projects contained in AAR#2516131 no later than 8/30/2015. This would include all equipment procurement, installation, turn up and testing. The approved projects would result in providing broadband services to ~2,484 currently unserved locations, improve service to multiple CAI's currently serviced under the project, add 25 new path miles and add 1 new medical clinic CAI. All are locations within the previously approved area of the 5 county project. The project will reach its final target numbers of 586 new, 10 upgraded network miles deployed and 44 CAI's served. Once the remaining projects are completed, First Step will immediately move forward with close out procedures. | First Step Internet, L.L.C. | First Step was able to make great process on AAR# 2516131 during Q2 2015. There are 3 remaining tasks to be completed and then close out for the entire award begins. First Step has all necessary approvals for the remaining work and are just awaiting dry weather in the mountains so the roads firm up so that we can access the necessary sites to complete the work. First Step is poised to easily complete the remaining tasks and be well on the way to final close out by the end of the current quarter. | First Step anticipates all BTOP related construction activity will be completed by the end of Q3. Close out procedures will be well underway.
NT10BIX5570053 | 2010 | Q3 | Q3 - 2010 | Issued Purchase Orders for three projects, namely, Increase Capacity of Fiber Optic System, Increase Capacity of Inter-island Microwave System, and 17 Hops-3G Back Haul Project on Guam. Request for Proposals were received for the following: Prepaid Charging System, 29 Hops - 3G Back Haul System on Guam, and the Network Wiring for the Network Operations (NOC) Project. For the Network Wiring Project, only one proposer submitted a proposal which was twice the engineer's estimate. This proposal was rejected and another alternative is being considered. Eight proposals were received in response to the 29 Hops RFP. Evaluations were conducted, wherein the proposals were short listed to four based on technical merit, then three based on their cost effectiveness. Seven proposals for the Prepaid Charging System were evaluated. However, it was recommended by the Cost Evaluation Team to Re-issue the RFP as all cost proposals were beyond the estimated budget. A draft Invitation for Bid (IFB) has been prepared for the Enhancement of IT&E's IP Core Network. Questionnaires have been sent out to IT&E's technical team to formulate an RFP for the Billing System Project. BTOP signs have been installed. Community Outreach is being conducted via press releases, print ads, and radio ads. | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | More customers were connected than projected per the Baseline. | N/A | N/A | 1 | 0 | 60 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months. | IP Transport between Guam and Saipan on undersea fiber optic cable. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Conduct and finalize negotiations for the 3G Back Haul System RFP. Re-issue Prepaid Charging System RFP. Equipment and Materials are expected to arrive for two projects. Project Implementation will commence for the Fiber Optic Project and the License Microwave Project - 17 Hops. Continue with site preparation work. Finalize RFP for the Billing System. Continue with site preparation work at the new location of the Network Operations Center. Materials are expected to arrive in November and December. Issue Invitation for Bid for MPLS Hardware. Finalize Design. | PTI Pacifica, Inc., dba: IT&E | Issued a Request for Proposal for the Network Wiring under the Network Operations Center (NOC) Relocation Project. Only one vendor submitted a response to the proposal that was due on 9/3/2010. This proposal was rejected since it was twice the engineer's estimate. Due to this, we have to consider another alternative that would meet the budget amount for this project. Issued a Request for Proposal for the Prepaid Charging System and seven proposals were received. However, all proposals were beyond the estimated budget. Re-issuance of another RFP will be done. These two projects may be delayed due to this. | Equipment or Material arrival may be delayed due to lead time required by Manufacturers.
NT10BIX5570053 | 2010 | Q4 | Q4 - 2010 | Last quarter contracts were awarded for three projects under this Grant, namely, Increase Capacity of Fiber Optic System, Increase Capacity of Inter-island Microwave System, and 17 Hops - 3G Back Haul Project. These projects will improve broadband access. For the Fiber Optic System, weekly project calls were conducted with the Contractor. IT&E's project team completed site preparation for all 5 sites in Guam, Rota, Tinian, and Saipan. All equipment for this project were received. Project implementation started in November 2010. All fiber optical upgrade work was completed by the contractor the last week of December. This included the installation of new equipment, commissioning, software upgrade testing and integration. For the Increase Capacity of Inter-island Microwave System, the Prior Coordination Notice (PCN) required by the Federal Communications Commission (FCC) was issued. A Statement of Work was finalized in December 2010. The Contractor was given the Purchase Order to commence the manufacturing of the radios. Site preparation work, network design and floor plans continues. The 17 Hops - 3G Back Haul Project is progressing very well. Eleven radio links (hops) have been installed and tested per the Statement of Work. Three radio links (hops) have been installed but have not been completely tested. There are three more radio links (hops) that have yet to be completely installed. Cost negotiations were conducted with the three shortlisted proposers of t | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 2 | N/A | N/A | N/A | N/A | N/A | More customers were connected. | N/A | Due to Upgrade in the Fiber Optics Projects Project. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarterse term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on undersea fiber optic cablen on undersea fiber optic cable. | N/A. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | NONE AT THIS TIME. | FALSE | N/A | Inter-island Microwave: Continue with site preparation, Upgrade DC power. Complete and submit FCC601 forms along with Application Filing Fees. Receive Radio equipment, antennas, and associated equipment from NEC. Fiber: lT&E to complete equipment tagging and punchlist. Ciena to complete and submit As-Builts to lT&E. lT&E Project Manager to sign Installation Completion Notice and return to Ciena. NOCR: For the 1st quarter of 2011, we are estimating to receive all required equipment and materials to complete the Rack installation and network wiring. A method of procedure is being developed prior to actual installation/relocation of the network core elements, including router, switches and servers to the new data center. MPLS: The Routers, Switches and its IOS are expected to be received before on or before February 2011. They will be tested in a lab environment prior to deployment. The CWDM will also be re-tested between Tinian and Rota which has a distance of 120Km. Upon completion of the rack installation and network wiring in the new Saipan data center, 2 (two) of the Cisco 6506-E will be mounted and put in production. Prepaid: IT&E will be contacting the customer references provided by the short listed Bidders for feedback on the Bidderâ€™s performance. IT&E will evaluate the feedback and may enter into a best and final offer phase with selected Bidders. IT&E expects to select the winning proposal after receiving the best and final offer information. Postpa | PTI Pacifica, Inc., dba: IT&E | Prepaid Charging System Request For Proposal had to be re-issued with a more defined scope because the cost proposals submitted in the initial RFP was over IT&E's project budget. There were technical issues that had to be resolved with the lowest bidder for the MPLS Invitation for Bid, which delayed the issuance of a Purchase Order and in turn delayed the manufacture and ship date of the hardware. There also was a delay in shipping of the racks for the Network Operations Center (Data Center) due to its size. The racks had to be ocean freight since it was too large to be shipped via air. There were no bids received for one of the schedules for the Invitation for Bid which caused another delay. | Equipment or Material arrival may be delayed due to lead time required by Manufacturers. FCC license approvals may not be received in the expected timeframe.
NT10BIX5570053 | 2011 | Q1 | Q1 - 2011 | For the Increase Capacity of Fiber Optic System, installation, testing and cutover has been completed. Final Project As-builts have been reviewed, finalized and approved. Project completion, acceptance and turnover has been done between IT&E and the contractor. Final invoices have been processed. For the Increase Capacity of Interisland Microwave System, project calls continue. Federal Communications Commission 601 forms have been prepared and reviewed. Issuance of Purchase Order for the DC Power Systems for each of the sites. Site preparation and network design continue on the four islands. Equipment manufacturing has started. All installation work, testing and commissioning of radios for the 17 Hops under the 3G Back Haul Project have been completed. As-builts and final report have been turned over by the contractor. Project completion and acceptance notices have been signed. Final invoices have been processed. For the 29 Hops - 3G Back Haul Project, site survey of 46 sites was conducted in January by the contractor. Final survey report has been issued. Federal Communications Commission 601 forms have been prepared and reviewed. Manufacturing of radio equipment has started. Antennae orders have been placed and is enroute to Guam. Removal of old equipment and site preparation of the 46 project sites have started. Best and Final Offers were requested from the shortlisted bidders of the Request for Proposal for the Prepaid Charging System. Intent of Award | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 2 | n/a | n/a | n/a | n/a | n/a | More customers were connected. | n/a | Due to fiber optic project. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on undersea fiber optic cablen on undersea fiber optic cable. | N/A | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none. | FALSE | N/A. | Program Specific Audit Project: Meet with Auditors for more audit testing/field work. Submission of Preliminary Audit Report and discussion of any issues. Receive Final Audit Report and Submit to Office of Inspector General (OIG) and Program Officer. Network Operations Center Relocation Project: Completion of Network Cabling. Installation of Cisco ASA5510. Migration of Routers, Switches, Servers, as well as the migration of any existing customer circuits. Enhance IP Core Network (MPLS) Project: Deployment of CWDM MUX in Guam, Saipan, Tinian and Rota. Installation of 4506-E switches in Tinian and Rota. Installation of 6509E- in Saipan. Completion of Network cabling in Saipan and Guam Data Network Operations Center. Installation of additional four cabinet racks for Guam. Migration of the uplinks to the new 6509-E and 7604. Upgrade of Inter-Island Microwave Project: Receive radio equipment, antennas, and associated equipment from NEC. Conduct inventory equipment. Continue with project calls and site preparation on all four islands, Saipan, Tinian, Rota and Guam. Upgrade DC power at four locations, Mt. Tapochau Site, Susupe Site, Mt. Sabana Site and Tinian Site. Submit FCC601 forms. Install antennas and associated cables. Install, commission and turn-up radios. Align antennas. Attend off-island training for microwave radio equipment. Undersea Fiber Optic Project: Off-island Training of fiber engineering and design. Prepaid Billing System: Finalize and sign contr | PTI Pacifica, Inc., dba: IT&E | Shipment via Japan was held due to the Earthquake and Tsunami on 3/11/2011. A thorough inspection must be done to ensure no radiation is present. Contract reviews by legal department. Waiting for FCC license approvals. | Shipments via Japan may be held due to the Earthquake and Tsunami on 3/11/2011. A thorough inspection must be done to ensure no radiation is present on any shipments leaving Japan for other countries. Board Approval. Waiting for FCC license approvals. Weather delays.
NT10BIX5570053 | 2011 | Q2 | Q2 - 2011 | The activities for this quarter include the following: For the Increase Capacity of Interisland Microwave System, weekly project calls continue. Federal Communications Commission 601 forms have been submitted. DC Power Systems have been received for four sites. Site preparation and network design continue on the four islands. Radio Equipment, antennas, and ancillary equipment have been received. Contractors commenced installation of radio equipment, antennas, and DC Power Systems. For the 29 Hops - 3G Back Haul Project (Phase II), Federal Communications Commission 601 forms have been submitted. Radio equipment, antennas, and ancillary equipment have been received. Removal of old equipment and site preparation of the 46 project sites have been completed. Radio Equipment installation has started and is at 81% complete. Six links have been commissioned, tested and cut over. Training conducted by contractor. Prepaid Charging System Contract has been awarded and signed. Contractor conducted a two week information gathering site visit. Issues discovered during the site visit are being addressed by IT&E and the contractor. Billing Consultant Contract had been awarded. Consultant conducted a one week information gathering site visit. Consultant is working on Request for Information and a Request for Proposal for a postpaid billing systems for telecommunications to include billing, CRM, Business Support Systems (BSS), and Operations Support Systems (OSS). IT&E Personn | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 37 | n/a | n/a | n/a | n/a | n/a | Customers connected. | n/a | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) These inteconnections are due to completion of all or portions of the Fiber Optic, 17 Hops, and 29 Hops projects. This metric is lagging behind the baseline due to delays that occurred on the execution of the 17 Hops and 29 Hops 3G Back Haul Projects. We expect to report in 3Q 2011 all interconnection points as indicated in the baseline, since the 29 Hops project will be completed (installed and all cut over)s for any variance from the baseline plan or any other relevant information) These inteconnections are due to completion of all or portions of the Fiber Optic, 17 Hops, and 29 Hops projects. This metric is lagging behind the baseline due to delays that occurred on the execution of the 17 Hops and 29 Hops 3G Back Haul Projects. We expect to report in 3Q 2011 all interconnection points as indicated in the baseline, since the 29 Hops project will be completed (installed and all cut over). | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on undersea fiber optic cablen on undersea fiber optic cable. | N/A | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none. | FALSE | n/a | Increase Capacity of Interisland Microwave System: Continue with weekly project calls. Continue with Radio Equipment and Antennae Installation on the four islands. Installation of DC Power Systems at the four sites. Commission and turn up radios. Align antennas. 29 Hops - 3G Back Haul Project: Receive Federal Communications Commission 601 forms. Complete Radio equipment, antennas, and ancillary equipment installation. Commission, test and cut over remaining links. Prepaid Charging System: Resolve issues discovered during the site visit. Conduct weekly project meetings. Billing System Project: Review draft RFP prepared by Billing Consultant. Issue RFP. Enhanced IP Core Network (MPLS) and NOC Project: Complete the 1% remaining of the cut over work to the new system. Project Close out. Ensure all project documentation completed. Community Outreach: Continue with Outreach Campaign. | PTI Pacifica, Inc., dba: IT&E | One of the 15 feet antennae dish was damaged in shipping. Replacement dish has been ordered for the Tinian Microwave Site. Expected to arrive next quarter. | Minor delays due to weather for the installation of the antennas. Rainy season is from July through December. IT&E Match proportionality: Our approved budget specifies per line item the matching costs and federal shares. Most of the equipment was covered by federal funds so we did not have a matching share for those expenditures as well as other line items. Most of our projected matching share was from labor costs, and these we always expected to accrue in the latter part of the projects after the equipment had been ordered and received. We fully expect our reported matching share to rise significantly during the remaining quarters of the grant period, and, in fact, we believe that by the end of the grant period it will exceed the 20% we originally projected due to unpredictable cost overruns on the higher risk projects involving software (e.g., the Prepaid and Postpaid Billing Systems), the effects of weather causing project delays, and the damage in shipping of large items that we have already experienced. To this we must consider that network technology changes rapidly and we have already had to make changes in our original network designs to keep up with these changes which have increased originally projected costs on the 3G Backhaul project, the NOC Relocation project, and the MPLS Project, among others, and all of which will eventually be made up in our matching share.
NT10BIX5570053 | 2011 | Q3 | Q3 - 2011 | Increase Capacity of Interisland Microwave System: Completed Installation of all Radio Equipment and Antennae on the four islands. Completed installation of DC Power Systems at the four sites. Commissioned and turned up radios. Aligned all antennas. 29 Hops - 3G Back Haul Project: Received Federal Communications Commission Licenses for all links. Completed Installation of Radio equipment, antennas, and ancillary equipment for 27 links. Commissioned, tested and cut over all 27 links. Prepaid Charging System: Weekly project meetings on-going. Worked on network interface documentation. Installed racks and hardware. Billing System Project: Issued Request For Proposal in September. Received four proposals on the deadline of 9/30/2011. Enhanced IP Core Network (MPLS) and NOC Project: Completed the 1% remaining of the cut over work to the new system. Community Outreach: Continue with Outreach Campaign. Setting up meetings with various community anchor institutions. -Donated DSL service to the San Antonio Manhoben Youth Center in San Antonio, Saipan. -Donated DSL service to the Tinian Youth Center in San Jose, Tinian. -Donated DSL service to the Tanapag Youth Center in Tanapag, Saipan. | 157 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | New network miles deployed (microwave) from the 17 Hops and 29 Hops Project. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. | n/a | n/a | Customers connected. | n/a | Interconnection points due to the completion of all or portions of the Fiber Optic, Inter-island Microwave, 17 Hops and 29 Hops projects. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | N/A. | 0 | 1 | 0 | 1 | none | only one signed agreement | n/a | One subscriber receiving 10 Mbps. | 82 | 15 | 67 | 3 | CAIs include Government, Education, Healthcare, Community Support, and Public Safety. | CAIs with new access. | CAIs with improved access. | 3 Mbps - 56 subscribers, 1.5 Mbps to 2.5 Mbps - 11 subscribers and 768 kbps - 15 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Increase Capacity of Interisland Microwave System: Complete Punch list items. Project Close out with contractor. 29 Hops - 3G Back Haul Project: Project Close out with Contractor. Prepaid Charging System: Continue with weekly project meetings on-going. Engineers will be on-site to do work with IT&E. Billing System Project: Evaluate the four proposals. Conduct contract negotiations with top proposer based on the technical and cost evaluations. Award contract. No network miles is expected to be leased. Total Community Anchor Institutions to be served is 160. Community Outreach: Continue with Outreach Campaign. Meet with various Community Anchor Institutions (schools, public safety) to discuss broadband requirements in Guam and the CNMI. -Donate DSL service to the Kagman Community Center in Kagman, Saipan. | PTI Pacifica, Inc., dba: IT&E | IT&E Match proportionality: Our approved budget specifies per line item the matching costs and federal shares. Most of the equipment was covered by federal funds so we did not have a matching share for those expenditures as well as other line items. Most of our projected matching share was from labor costs, and these we always expected to accrue in the latter part of the projects after the equipment had been ordered and received. | Interface and testing as the last two remaining projects are mainly software projects.
NT10BIX5570053 | 2011 | Q4 | Q4 - 2011 | Increase Capacity of Interisland Microwave System: Completed Punch list items. Project Closed out with contractor. 29 Hops - 3G Back Haul Project: Project Closed out with Contractor. Prepaid Charging System: Continued with weekly project meetings. Engineers have been on-site to do interoperability testing with IT&E. Billing System Project: Evaluated the four proposals received. Conducted contract negotiations with top proposer based on the technical and cost evaluations. Contract has been awarded and statement of work has been developed. No network miles are expected to be leased. Total Community Anchor Institutions served is 183. Community Outreach: Met with CAIs on Guam and provided them with demo units to test to determine if it will meet their broadband requirements. In CNMI initiated meetings with several school principals to discuss broadband requirements for the schools and set up meetings with the Parent Teacher Association. -Donated DSL service to the Kagman Community Center, Gualo Rai Youth Center and the Veteran's Affairs Office. Set up Wi-fi access for the San Antonio Manhoben (Youth) Center. | 157 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles deployed. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. | n/a | n/a | customers connected | n/a | Interconnections points from projects completed. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | n/a | 0 | 1 | 0 | 1 | n/a | only one signed agreement | n/a | One subscriber receiving 10 Mbps. | 183 | 39 | 144 | 3 | 101 total CAIs this quarter and include Government, Education, Healthcare, Community Support, and Public Safety. | 24 additional CAIs with new access this quarter. | 77 additional CAIs with improved access this quarter. | 2 Mbps up to 3 Mbps - 58, 1.5 Mbps up to 2.5 Mbps - 13 subscribers and 768 kbps up to 1.5 Mbps - 112 subscribers. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None. | FALSE | n/a | Prepaid Charging System: Continue with weekly project meetings. Continue with testing. Implement switch and PDSN software triggers to complete interface. Billing System Project: Project will commence. No network miles is expected to be leased. Total Community Anchor Institutions to be served is 240. Community Outreach: Continue with Outreach Campaign. Meet with various Community Anchor Institutions (schools, public safety) to discuss broadband requirements in Guam and the CNMI. Guam Outreach will include the following: â€¢ Health Care. Engage with Public Health, medical associations, and others to develop a health care page on our web with links to health programs, campaigns and public service announcements. â€¢ Public Safety. Provide broadband service to mobile command vehicles utilized by Guam Police, Guam Fire, Civil Defense, and Homeland security. â€¢ The Mayorâ€™s Council. Provide broadband service at senior centers. Develop mentoring program for high school students to teach seniors. CNMI Outreach will include meetings with various Parent Teacher Associations at various schools to discuss the importance of broadband. Introduction of a DSL Life Line Link Up Program. | PTI Pacifica, Inc., dba: IT&E | Interface and testing for the Prepaid Billing Project - During testing for implementation of the interface, we discovered that our switch and our PDSN did not have software event triggers enabled for proper functioning of the prepaid billing system and had to purchase licenses to enable the triggers. | Inter-operability testing may turn up additional interface issues that will need to be addressed.
NT10BIX5570053 | 2012 | Q1 | Q1 - 2012 | Prepaid Charging System: Continue with weekly project meetings. Implemented switch and PDSN software triggers to complete interface. Launched Prepaid Data Module of the Prepaid Billing System. Vendor provided user training to the technical team. User training for the Customer Service and Marketing Team has started. Inter-Operability testing of other modules of the system continues. Billing System Project: Contract has been awarded. Hardware has been ordered. Project Meetings have started. Marketing Requirements documentation have been drafted and is being reviewed by IT&E. No network miles is expected to be leased. Total Community Anchor Institutions served is 258. Community Outreach: Continue with Outreach Campaigns. Meetings were conducted at various CNMI Public Schools during their Parent Teacher Association Meetings to discuss broadband requirements in Guam and the CNMI. Donated DSL lines to a school in Rota and other community support groups. In Guam, meetings are being conducted with the public health and medical associations to develop a health care page on IT&E's website. Broadband service to mobile command vehicles utilized by Guam Police and other public safety agencies have been provided for testing purposes. IT&E has begun offering the DSL Life Line Link Up Program to all qualified residents. Since its introduction, 37 qualified subscribers have signed up for the program this quarter. IT&E does not offer any DSL service below 768 kbps. | 157 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles Deployed. No New miles this quarter. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. No network miles upgraded this quarter. | n/a | n/a | customers connected | n/a | interconnection points from projects completed. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | n/a | 0 | 1 | 0 | 1 | n/a | one signed agreement | n/a | One subscriber receiving 10 Mbps. | 258 | 51 | 207 | 3 | 75 total subscribers this quarter. | 12 additional subscribers with new access this quarter. | 63 additional subscribers with new access this quarter. | 2 Mbps up to 3 Mbps - 58, 1.5 Mbps up to 2.5 Mbps - 13 subscribers and 768 kbps up to 1.5 Mbps - 112 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None. | FALSE | n/a | Training will continue for the Prepaid Billing Project for various departments in the company. Testing and conversion of all modules for the system will be completed. Project meetings will continue for the Postpaid Billing Project. Finalization of marketing requirements and other technical requirements. Delivery and installation of hardware. Hardware integration will commence. Software development will commence. Travel will continue for these projects between the islands. Also, IT&E personnel will attend the BTOP Workshop in May. IT&E Personnel will also attend a vendor user conference in June for the Billing System. Anticipated CAIs that will be connected for 2Q 2012: 300 No new network miles will be added this quarter as only Billing Projects remain. Community Outreach will continue with meeting with various CAIs. | PTI Pacifica, Inc., dba: IT&E | Inter-operability testing may turn up additional interface issues that will need to be addressed. | Inter-operability testing may turn up additional interface issues that will need to be addressed.
NT10BIX5570053 | 2012 | Q2 | Q2 - 2012 | Training was conducted for the Prepaid Billing Project for various departments like Customer Service, Call Center, and Marketing in the company. Testing and conversion of all modules for the system have been completed. Migration of existing customers to the new Prepaid Charging Platform occurred in June. Both IT&E Personnel and Customers are adjusting to the features of the New System. Vendor Support is on-site to assist IT&E with any issues. Launched a new product offering - 3G Prepaid Data in May. Subscribers are growing steadily. We have 353 subscribers for this quarter. Project meetings continued for the Postpaid Billing Project. Project Manager was hired to assist with this project. Two Technical Product Managers from the Vendor were on-site to meet with the various departments, Accounting, Marketing, Sales, Customer Service, to discuss the technical flows required for the Finalization of Systems Requirements Specifications (SRS). This is a detailed statement of work, each specific requirement identified. Upgraded Hardware was delivered to Vendor Site. Configuration of the hardware was started. Inter-Island travel continues for the prepaid and postpaid billing projects between the islands. IT&E personnel attended the BTOP Workshop in May. Total CAIs connected this quarter 2Q 2012: 339 (81 CAIs added this quarter). No new network miles added this quarter. Community Outreach: In the CNMI, Community Outreach Coordinator met with several Parent Teacher Associations (PTAs) prior to the public schools closing for summer vacation. Meetings have been conducted with the Department of Community and Cultural Affairs. This office provides assistance to many of the low income residents, through various agencies under its umbrella, like the Nutrition Assistance Program, Child Care Program, Energy Assistance Program, and the Senior Citizens Center to name a few. IT&E's Outreach Coordinator is working on assisting this government agency with their website and broadband needs. Also, to partner with the agency to reach out to the residents. On Guam, the Outreach Coordinator and team are working with various CAIs to discuss their broadband requirements. Demo Units have been provided to some agencies. | 157 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles Deployed. No New miles this quarter. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. No network miles upgraded this quarter. | n/a | n/a | customers connected | n/a | interconnection points from projects completed. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | n/a | 0 | 1 | 0 | 1 | n/a | one signed agreement | n/a | One subscriber receiving 10 Mbps. | 339 | 78 | 261 | 4 | 81 subscribers added this quarter. | 27 subscribers receiving new access this quarter. | 54 subscribers receiving improved access this quarter. | 3Mbps up to 6Mbps - 15 subscribers, 2.5 Mbps up to 3 Mbps - 58 subscribers, 1.5 Mbps up to 2.5 Mbps - 69 subscribers and 768 kbps up to 1.5 Mbps - 197 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | Introduced 3G Prepaid Data Plans to subscribers. | FALSE | n/a | Prepaid Billing System: Vendor Support will be on-site through August to assist IT&E with any issues. Project meetings will continue for the Postpaid Billing Project. Product Managers will take a specific module from the Systems Requirements Specifications and translate it to customization that relates to IT&E's business processes. A High Level Solution will be developed and shared with IT&E for approval. Method of Procedures (MOP) and Standard Operating Procedures (SOP) will be developed by the IT&E Project Team as the software development commences by the vendor. Hardware for Postpaid Billing Platform is expected to be on site. Installation will commence in August. Inter-Island travel will continue for the postpaid billing projects between the islands. Total CAIs anticipated to be connected next quarter 3Q 2012: 400. Community Outreach will continue with meeting with various CAIs. | PTI Pacifica, Inc., dba: IT&E | Shipping Delays. Minor issues after the migration of all existing customers to the new prepaid charging platform. | Configuration of hardware. Customization of System to meet IT&E requirements.
NT10BIX5570053 | 2012 | Q3 | Q3 - 2012 | Prepaid Billing System: Vendor Support continues on-site this quarter to assist IT&E with any issues. Project meetings continue for the Postpaid Billing Project. Product Managers continue to take specific modules from the Systems Requirements Specifications and translate it to customization that relates to IT&E's business processes. Method of Procedures (MOP) and Standard Operating Procedures (SOP) is under development by the IT&E Project Team. Software development has started by the vendor. Data migration has started. Initial training has been conducted to provide IT&E Departments and overview of the new system. Two engineers have been on site this quarter to start with the data migration. The inventory module has already been migrated to the MIND System. Hardware for Postpaid Billing Platform has also been installed this quarter. Inter-Island travel will continue for the postpaid billing projects between the islands. Total CAIs connected this quarter 3Q 2012: 400. As part of our Community Outreach in the CNMI, DSL speeds have been doubled for all subscribers (over 5000) this quarter. Meetings continue with various CAIs both on Guam and in the CNMI to determine how IT&E can assist these agencies with their broadband requirements. Some of the CAIs on Guam include the Mayor's Offices at each village and the Bureau of Information Technology Office. In the CNMI, meetings with the public schools, Department of the Community and Cultural Affairs, and other government agencies. | 178 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles Deployed. 20.9 New miles this quarter. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. No network miles upgraded this quarter. | n/a | n/a | Customers connected. | n/a | Interconnection points from projects completed. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | n/a. | 0 | 1 | 0 | 1 | n/a | one signed agreement | n/a | One subscriber receiving 10 Mbps. | 400 | 88 | 312 | 4 | 61 added this quarter | 10 subscribers receiving new access this quarter. | 51 subscribers receiving improved access this quarter. | 3Mbps up to 6Mbps - 38 subscribers, 2.5 Mbps up to 3 Mbps - 69 subscribers, 1.5 Mbps up to 2.5 Mbps - 94 subscribers and 768 kbps up to 1.5 Mbps - 199 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | No new offerings. DSL speeds were doubled too all subscribers in the CNMI. | FALSE | n/a | Prepaid Billing System: Vendor Support will continue on-site until October to assist IT&E with any issues. Project meetings will continue for the Postpaid Billing Project. Data Migration will continue. There will be 5 Engineers on site during this quarter to work on data migration. Training will be conducted on various modules of the system for the respective IT&E Departments in November and December. Acceptance Test Procedures are being developed that would include various test case scenarios. Inter-Island travel will continue for the postpaid billing projects between the islands. Total CAIs anticipated to be connected 4Q 2012: 403. Meetings with CAIs will continue as part of the Community Outreach. Preparations for Project Close - Out will commence. | PTI Pacifica, Inc., dba: IT&E | Weather delays. Issues with software development and testing. | Issues with the data migration and testing.
NT10BIX5570053 | 2012 | Q4 | Q4 - 2012 | Prepaid Billing System: Vendor Support on-site continued until October. IT&E was assisted with any issues. Project meetings were held for the Postpaid Billing Project. On site data migration continues and is performed by the five (5) Engineers. Training was conducted on various modules of the system for the respective IT&E Departments in November and December. Acceptance Test Procedures were developed and test cases were performed on some of the modules. A parallel bill run was conducted in December. Inter-Island travel will continue for the postpaid billing projects between the islands. Total CAIs connected 4Q 2013: 407. Meetings with CAIs continue as part of the Community Outreach. Preparations for Project Close - Out has started. Team has been taking webinars offered by BTOP. | 197 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles Deployed. 19 New miles this quarter. | n/a | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. No network miles upgraded this quarter. | n/a | n/a | new customers added | n/a | interconnection points from projects completed | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | n/a | 0 | 1 | 0 | 1 | n/a | one signed agreement | n/a | One subscriber receiving 10Mbps | 407 | 90 | 317 | 4 | 7 added this quarter | no subs received new access | 7 subs received improved access this quarter | 3Mbps up to 6Mbps - 38 subscribers, 2.5 Mbps up to 3 Mbps - 69 subscribers, 1.5 Mbps up to 2.5 Mbps - 101 subscribers and 768 kbps up to 1.5 Mbps - 199 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Completion of Postpaid Billing Project. Payment of Invoices for Postpaid Billing Project. Preparation and Completion of Grant Close Out. Commence Final Audit. | PTI Pacifica, Inc., dba: IT&E | Issues with data migration and testing. | none.
NT10BIX5570053 | 2013 | Q1 | Q1 - 2013 | Postpaid Billing Project has been completed. On-site Training has been completed. As of February 28, 2013, IT&E has spent $2,976,762, which more than the required 20% of it's Match Share of $2,023,200. IT&E committed these additional funds for this Grant Award. IT&E has started working on the close-out of the grant award. UCC-1 Filings have been completed in Guam and CNMI. These filings have been submitted to the Grants Office. | 197 | 0 | 307 | 0 | 0 | 11 | 0 | 73 | Microwave Network Miles Deployed. No new network miles deployed this quarter. | N/A | Mileage from the upgrades to the Fiber Optic (171.68 fiber miles) and the Inter-Island Microwave (135.87 microwave miles) Projects. No network miles upgraded this quarter. | N/A | N/A | New customers added. | N/A | Interconnection points from projects completed. | 1 | 0 | 20 | Marianas Cablevision (MCV) - The term of the agreement in 5a is 60 months or 20 quarters. | IP Transport between Guam and Saipan on the undersea fiber optic cable. | N/A. | 0 | 1 | 0 | 1 | N/A. | One signed agreement. | N/A. | One subscriber receiving 10Mbps. | 420 | 103 | 317 | 4 | 13 added this quarter. | 13 received new access this quarter. | No improved access this quarter. | 3Mbps up to 6Mbps - 44 subscribers, 2.5 Mbps up to 3 Mbps - 69 subscribers, 1.5 Mbps up to 2.5 Mbps - 108 subscribers and 768 kbps up to 1.5 Mbps - 199 subscribers | 0 | 0 | 0 | 0 | 0 | N/A. | N/A. | N/A. | N/A. | N/A. | 0 | 0 | 0 | 0 | 0 | N/A. | N/A. | N/A. | N/A. | N/A. | NONE. | FALSE | N/A. | None - Grant Period ended 2/28/2013. | PTI Pacifica, Inc., dba: IT&E | none. | None - Grant Period ended 2/28/13.
NT10BIX5570054 | 2010 | Q3 | Q3 - 2010 | Completed and submitted draft of Environmental Assessment and responded to government's comments. Continued correspondence with two agencies regarding review letters. Signed contract with engineering firm. Issued RFP to secure services related to fiber optic network construction, operation services and grant matching funding. Have met all deadlines related to the Environmental Assessment and quarterly reporting. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Not yet. | Not yet. | None. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalization of source of matching funds. Signing of contract with firm that will provide construction and operations services for the network. Completion of the Environmental Assessment. Continue work on network design, rights of way and construction permits. | Page County Broadband Authority | Page County Broadband Authority has issued an RFP to secure services related to fiber optic network construction, operation and provision of matching funds. This activity has led to a delay on some areas identified above. | Procurement delays in Quarters 1-3 (due to sourcing matching funds and issuing an RFP) have affected the baseline timeline but we anticipate securing committed matching funds and movement forward with engineering-related activities by end of Quarter 4.
NT10BIX5570054 | 2010 | Q4 | Q4 - 2010 | Meetings with service providers to discuss project. Conducted procurement to select a firm for design, construction and operation of the network. Executed contract for same in December, 2010. Completed Environmental Assessment and a FONSI was received. Began discussions with utility for pole attachment access, and meetings held with community anchor institutions to discuss plans for access and use of the network. Revised baseline, this progress reported as to baseline dated 1/28/2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | N/A | No variance | No variance | No variance | No variance | 1 | 0 | 12 | Shenandoah Long Distance Company - wholesale broadband provider | No services established at this time, network not yet constructed. | Shenandoah Long Distance Company: as contractor: James Funkhouser, 540-984-5181 This firm will operate all 39 miles of the Page County Broadband Authority network. Agreement includes all maintenance required on the network infrastructure and equipment. | 0 | 0 | 0 | 0 | Agreement signed, network not constructed. | N/A | Agreement signed, network not constructed. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | network not constructed. | FALSE | N/A | Make ready engineering to be near completion with formal design in progress. Expect to continue discussions with community anchor institutions to coordinate network connectivity. | Page County Broadband Authority | This project is on track to meet the milestones identified in the 28Jan2011 revised baseline. | Acquiring easements from private property owners for aerial crossings where the utility pole line leaves the road right of way could slow design process. Where acquiring permission looks most difficult, engineering will assess changes in deployment from aerial to underground to meet the project needs. Any changes would require reconsultation with environmental agencies and could delay the design process somewhat.
NT10BIX5570054 | 2011 | Q1 | Q1 - 2011 | Overall design of the network is 80% completed and committed to construction drawings. Overall route determined and confirmed as capable of being built. Location of Luray POP determined and confirmed. Stanley, Shenandoah and Rileyvile POP sites identified. Permitting completed as far as submittal to all pertinent agencies. Permissions to railroad, VDOT, Virginia Marine Resources and permits/applications to utility owners, Shenandoah Valley Electric Co-op (SVEC) and Century link have been submitted. Have received competitive bids for construction but contract not yet awarded. Equipment identified for point of presence sites and proposals given to Page County Broadband Authority for evaluation and approval. Overall project construction schedule has been developed and circulated including all key milestones for deliverables and payments to Shentel. Bi-weekly technical meetings established. Twenty-nine (29) anchor institutions contacted and confirmed interested in connecting to middle mile network. Financial filing system established, invoice review and payment process established, 1st stage of 2010-2011 audit completed, charts of accounts developed and Quickbooks accounting set-up, monthly financial management spreadsheet developed and implemented, Davis-Bacon requirements provided to construction contractor for wage determination compliance. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | NA | no variance | no variance | no variance | no variance | 1 | 0 | 12 | Shenandoah Long Distance Company -- wholesale broadband provider | No services established at this time, network not yet constructed. | This firm will operate all 39 miles of the Page County Broadband Authority network. Agreement includes all maintenance required on the network infrastructure and equipment. | 0 | 0 | 0 | 0 | Agreement signed, network not constructed | NA | Agreement signed, network not constructed | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Network not constructed yet. | FALSE | NA | POPS will be finalized, material procurement will be initiated and one of the remote sites will be completed. Engineering and design will be completed. Make ready operations will be underway by Centurylink and SVEC. All VDOT permits will be returned and approved for construction. Construction contractor will be selected. Quarterly reports for Q1 will be submitted. Kick-off event will be held in May and communications activities initiated. Financial statements and financial management spreadsheet will be submitted to PCBA on monthly basis. | Page County Broadband Authority | Potential challenge in regards to electric utility completing make ready work timely by bringing enough manpower to bear to match the construction schedule. Meetings are underway to address those concerns. Application is in process with Centurylink for approval of attachments to their poles; initial resistance to allow attachment by the PCBA, discussions in progress with CenturyLink and VA Dept of Transportation to identify alternative options. | May take longer than anticipated to secure permissions to attach from SVEC and CenturyLink for main line construction and for make ready work to get underway. The preliminary final design is complete but cannot be finalized until make ready and pole attachment agreements are confirmed.
NT10BIX5570054 | 2011 | Q2 | Q2 - 2011 | Point of presence locations and lease terms finalized, began developing final lease documents and drawings. A preliminary design was completed and make ready discussions commenced with the electric utility and local telephone company for aerial attachments. Permit applications for right of way access submitted to Virginia DOT and VA Marine Resources Commission, and railroad crossing permits submitted. The electric utility returned their make ready assessment and costs to complete the work, which was far in excess of the contractor's assessment. The contractor began a reassessment process to adjust design to bypass costs. Postponed invitations and plans for August 11, 2011 public kick off event; continued twice monthly technical meetings with contractor to review progress. Met with anchor institutions to confirm connectivity and bandwidth needs as well as fiber drop locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Original baseline submitted in July 2010 anticipated construction would be underway in Qtr 2 with 9 miles of fiber deployed. The revised baseline submitted January 2011 incorporated the schedule from the construction contractor and revised the miles of fiber deployed to 0 since they would first be setting Point of Presence facilities and equipment. The PPR variance reporting utilizes the revised baseline, and there is no variance at this time. | No Variance | No Variance | N/A | Original baseline submitted in July 2010 anticipated construction would be underway in Qtr 2 with 9 miles of fiber deployed. The revised baseline submitted January 2011 incorporated the schedule from the construction contractor and revised the miles of fiber deployed to 0 since they would first be setting Point of Presence facilities and equipment. The PPR variance reporting utilizes the revised baseline, and there is no variance at this time. | No Variance | No Variance | No Variance | 1 | 0 | 40 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider | No services established at this time, network has not yet been constructed. | Shentel will operate all 39-miles of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 0 | 0 | 0 | 0 | Lease Agreement signed, network not yet constructed | N/A | Lease Agreement signed, network not yet constructed | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network has not yet been constructed | FALSE | N/A | Point of presence facilities will be set in place and agreements complete with all of the Towns for ground leases. The pole attachment agreement between the electric utility and the Authority will be complete. Designs will be re-engineered and make ready negotiations complete. Reconsultation with environmental agencies will be initiated and a project modification request submitted for approval. The construction contractor will be selected, under contract, and a wage determination request submitted to the NTIA/Dept of Labor liaison as necessary. Permitting will be resubmitted where necessary. A public kick off event will be held in August. | Page County Broadband Authority | Work continued on schedule until near the very end of Quarter 2 when the electric utility presented their cost estimate for completing make ready work. Their estimate is far beyond expectations and the project budget, and they have additionally stated the work could not be completed timely. At this time the contractor is reassessing the design to find ways to bypass areas of high make ready and presented that plan to the Authority on July 26th. This new design will impact the schedule and budget, and require an amendment to the EA and re-consultation with environmental agencies if deployment type is changed to underground. Permit applications may need to be resubmitted with changes as well. The Authority intends to work with the FPO and Grants Coordinator to address any project modifications. | At the present time the project is estimated to be approximately 90 days behind schedule due to an unreasonable make ready estimate provided by the electric utility in addition to their inability to perform the needed work timely. The design will be under evaluation for changes in the 3rd quarter and a project modification request submitted to the FPO in addition to any reconsultation for an EA amendment. The redesign may include a change in deployment to underground to bypass high make ready areas, but will require re-engineering and an estimated additional 60 days to resubmit construction and environmental permitting. No change in the physical route or miles deployed are anticipated at this time. The Authority will work closely with the FPO and Grants Coordinator to complete required reports and seek approvals as required.
NT10BIX5570054 | 2011 | Q3 | Q3 - 2011 | In July the PCBA worked diligently with the incumbent electric cooperative and construction partner Shentel to negotiate make ready costs for the aerial construction. No agreement could be reached, and since August the PCBA and Shentel have worked to develop a modification of the project that would meet the grant objectives, build last mile fiber to critical CAIs, be completed within the grant budget and deployed in a timely fashion. Three designs were reviewed and a final design will be submitted to NTIA as a project modification request Land Performance Improvement Plan in October, 2011 (anticipated submission period). All reporting was submitted timely, regular phone meetings with NTIA officials were held, and the PCBA held technical and authority meetings twice monthly to monitor the project. The PCBA plans to submit a project modification to NTIA in October 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The original baseline projected 28 miles of fiber would be deployed this quarter. Due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, construction has not begun pending design modification approval. | No Variance | No Variance | N/A | The original baseline projected 28 miles of new fiber would be deployed this quarter. Due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, construction has not begun pending design modification approval. | No Variance | Variance: Awaiting project modification approval from NTIA that removes tower construction from this project. | Variance: The Point of presence interconnection point in Luray has been constructed but no equipment has been deployed for an interconnection to Shentel (provider partner). Further construction pending approval for design modification. | 1 | 0 | 40 | An agreement is in place with Shenandoah Long Distance Company (Shentel) to provide both wholesale and last mile services. The original baseline projected 3 agreements would be signed with 4 potential. No further agreements can be negotiated until completion of the network can be accurately projected. The proposed redesign will replace fiber backhaul between communities with microwave and could potentially bring in additional providers from outside the County. It is anticipated that at least 1 additional agreement will be negotiated in Q1-2012 pending approval of a project modification. | No services established at this time, network has not yet been constructed. Awaiting project modification approval from NTIA. | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 0 | 0 | 0 | 0 | The original baseline projected 1 provider would be receiving new access during this quarter. A signed agreement with 1 provider is in place, but due to delays in design and make ready negotiations network construction has not begun. | A signed agreement with 1 provider is in place, but due to delays in design and make ready negotiations network construction has not begun. No additional agreements with providers can be negotiated until the design modification is approved. | 1 dark fiber lease Agreement signed, network not yet constructed | N/A | 0 | 0 | 0 | 0 | The baseline projected a total of 9 subscribers could be served in this quarter. Network construction was projected to commence in Qtr 2 but has been delayed due to design modifications to bypass areas of high make ready expense. | The baseline projected a total of 4 subscribers could be receiving new access in this quarter. Network construction was projected to commence in Qtr 2 but has been delayed due to design modifications to bypass areas of high make ready expense. | The baseline projected a total of 5 subscribers could be receiving improved access in this quarter. Network construction was projected to commence in Qtr 2 but has been delayed due to design modifications to bypass areas of high make ready expense. | The baseline projected services would be available providing speeds ranging from a minimum of 10 Mbps to a maximum of 1 Gbps. While the speed tiers that the network will be capable of providing has not deviated from those indicated in the baseline and as stated above, the network construction has not commenced pending design modification approval. There are no subscribers at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network has not yet been constructed | FALSE | N/A | Point of presence facilities will be set in place and agreements complete with all of the Towns for ground leases. The pole attachment agreement between the electric utility and the Authority will be complete. Designs will be finalzed and make ready negotiations complete. Reconsultation with environmental agencies will be initiated and a project modification request submitted for approval. The construction contractor will be selected, under contract, and a wage determination request submitted to the NTIA/Dept of Labor liaison as necessary. Permitting will be resubmitted where necessary. A project modification will be submitted to NTIA in October 2011. It is anticipated that the PCBA will be at 67% project completion by end of February, 2012 (Q1-2012), and 100% complete by end of February 2013 (Q1-2013) per our original baseline. | Page County Broadband Authority | PCBA experienced significant cost estimate overruns associated with a high-make ready estimate for pole attachments provided by the Shenandoah Valley Electric Cooperative (SVEC) for aerial construction on their utility infrastructure. The estimate received for the original network design totaled $2.6 million, and the cooperative has been unwilling to reduce this high estimate forcing a project modification request. Since August 2011, the PCBA and Shentel worked to develop a revised design that minimized the use of SVEC poles through installation of a combination of aerial and buried fiber for distribution within the Towns and microwave links for long haul transport between the Towns. As a result of these delays, the PCBA was asked to submit a response to the Performance Improvement Plan (PIP) to NTIA by October 19, 2011. At this time the PCBA's modified time line is based on receiving project modification approval from NTIA in November to allow for completion of design and progress towards the network build to commence. | Since Q2 the PCBA has developed a network redesign, including route modifications (aerial/buried fiber), a revised project schedule and a revised project budget. The PCBA and our partner, the Shenandoah Long Distance Company (Shentel) believes that this network redesign meets the original intent of the grant award criteria and can be completed during the existing grant contract period. the PCBA is committed to moving forward as soon as project modification approval is received. The project modification request submitted to NTIA on October 19, 2011 anticipated review and approval in November. To the extent that approval is received timely, the PCBA intends to immediately begin reconsultation for an environmental assessment amendment for areas previously described as aerial that are moving to underground. During this time, final design for construction will be completed.
NT10BIX5570054 | 2011 | Q4 | Q4 - 2011 | In July the PCBA worked diligently with the incumbent electric cooperative and construction partner Shentel to negotiate make ready costs for the aerial construction. No agreement could be reached, and since August the PCBA and Shentel have worked to develop a modification of the project that would meet the grant objectives, build last mile fiber to critical CAIs, be completed within the grant budget and deployed in a timely fashion. Three designs were reviewed and the final design submitted to NTIA as a project modification request and Performance Improvement Plan in December 2011. All reporting was submitted timely, regular phone meetings with NTIA officials were held, and the PCBA held technical and authority meetings twice monthly to monitor the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not deployed any new network miles. | No Variance | No Variance | N/A | Due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not deployed any new fiber (aerial or underground). | No Variance | Variance: Awaiting project modification approval from NTIA that removes tower construction from this project. | Variance: The Point of presence interconnection point in Luray has been constructed but no equipment has been deployed for an interconnection to Shentel (provider partner). Awaiting project modification approval from NTIA. | 1 | 0 | 40 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. The variance in the baseline in the number of last mile providers signed up in Q3-2011 (baseline was 3) is due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments. The PCBA was directed to submit a Project Improvement Plan (PIP) to NTIA in October 2011 and subsequently submitted a Project Modification Request in December 2011. At this time, PCBA has not signed up any new providers during this modification process. It is anticipated that that agreements will be negotiated in Q1 & Q2-2012 pending approval of the Project Modification request. | No services established at this time, network has not yet been constructed. Awaiting project modification approval from NTIA. | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 0 | 0 | Lease Agreement signed, network not yet constructed | Variance due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not signed up any new providers as a result of this modification process. | Lease Agreement signed, network not yet constructed | N/A | 0 | 0 | 0 | 0 | Variance in baseline due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not connected any CAI's as a result of this modification process. | Variance in baseline due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not connected any CAI's as a result of this modification process. | Variance in baseline due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments, the PCBA was requested to submit a project modification to NTIA in December 2011 and has at this time not connected any CAI's as a result of this modification process. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network has not yet been constructed | FALSE | N/A | Point of presence facilities will be set in place and agreements complete with all of the Towns for ground leases. The pole attachment agreement between the electric utility and the Authority will be complete. Designs will be finalized and make ready negotiations complete. Reconsultation with environmental agencies will be initiated and a project modification request submitted for approval. The construction contractor will be selected, under contract, and a wage determination request submitted to the NTIA/Dept of Labor liaison as necessary. Permitting will be resubmitted where necessary. It is anticipated that for the next quarter there will ne no new network miles deployed, no new network miles leased, no CAI's will be connected and there will be no increase in the number of signed agreements with boradband wholesalers or last mile providers. | Page County Broadband Authority | PCBA experienced significant cost estimate overruns associated with a high-make ready estimate for pole attachments provided by the Shenandoah Valley Electric Cooperative (SVEC) for aerial construction on their utility infrastructure. The estimate received for the original network design totaled $2.6 million, and the cooperative has been unwilling to reduce this high estimate forcing a project modification request. Since August 2011, the PCBA and Shentel worked to develop a revised design that minimized the use of SVEC poles through installation of a combination of aerial and buried fiber for distribution within the Towns and microwave links for long haul transport between the Towns. As a result of these delays, the PCBA was asked to submit a response to the Performance Improvement Plan (PIP) to NTIA in December, 2011 as well as a project modification request. We anticipate response to the request in January, 2012 and update the project schedule accordingly if approved by NTIA. | Since Q2 the PCBA has developed a network redesign, including route modifications (aerial/buried fiber), a revised project schedule and a revised project budget. The PCBA and our partner, the Shenandoah Long Distance Company (Shentel) believes that this network redesign meets the original intent of the grant award criteria and can be completed during the existing grant contract period. the PCBA is committed to moving forward as soon as project modification approval is received. The project modification request submitted to NTIA on October 19, 2011 anticipated review and final PIP submission in December 2011. To the extent that approval is received timely, the PCBA intends to immediately begin reconsultation for an environmental assessment amendment for areas previously described as aerial that are moving to underground. During this time, final design for construction will be completed.
NT10BIX5570054 | 2012 | Q1 | Q1 - 2012 | In July 2011 the Page County Broadband Authority (PCBA) worked diligently with the incumbent electric cooperative and construction partner Shentel to negotiate make ready costs for the aerial construction. No agreement could be reached, and since August 2011 the PCBA and Shentel have worked to develop a modification of the project that would meet the grant objectives, build last mile fiber to critical Community Anchor Institutions (CAI's), be completed within the grant budget and deployed in the grant award period (ending February 28, 2013). Three designs were reviewed and the final design submitted to National Telecommunication and Information Administration (NTIA) as a project modification request and Performance Improvement Plan response in December 2011. The project modification was approved by NTIA, and the National Oceanographic and Atmospheric Administration (NOAA) grants office in January 2012. Since January 2012, the PCBA has negotiated and signed the three (3) contracts: design & construction, operations and fiber leasing, has initiated the fiber re-design, initiated the microwave path design, began site acquisition and initiated the reconsultation of the environmental assessment. All reporting was submitted timely, regular phone meetings with NTIA officials were held, and the PCBA held technical and authority meetings twice monthly to monitor the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | No Variance | No Variance | N/A | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | No Variance | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | 1 | 0 | 40 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. The variance in the baseline in the number of last mile providers signed up in Q4-2011 (baseline was 3) is due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments. The PCBA was directed to submit a Project Improvement Plan (PIP) response to NTIA in October 2011 and subsequently submitted a Project Modification Request in December 2011. At this time, PCBA has not signed up any new providers during this modification process. It is anticipated that that agreements will be negotiated in Q2-2012 based on the approval of the Project Modification in January 2012. | The project modification was approved by NTIA and the NOAA Grants Office in January 2012. No services established at this time, network has not yet been constructed. | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 0 | 0 | Lease Agreement signed, network not yet constructed | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | Lease Agreement signed, network not yet constructed | N/A | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network has not yet been constructed. | FALSE | N/A | Point of presence facilities will be set in place and agreements complete with all of the Towns for ground leases. The pole attachment agreement between the electric utility and the Authority will be complete. Designs will be finalized and make ready negotiations complete. Environmental assessment amendment will be submitted to NTIA for review. The construction contractor will be selected, under contract, and a wage determination request submitted to the NTIA/Department of Labor liaison as necessary. Permitting will be approved where necessary. It is anticipated that for the next quarter there will be no new network miles deployed, no new network miles leased, no CAI's will be connected and there will be no increase in the number of signed agreements with broadband wholesalers or last mile providers. | Page County Broadband Authority | The project modification was approved by NTIA and NOAA grants office in January 2012. Challenges faced this quarter include the negotiations of the three (3) contracts with Shentel and environment assessment development and approval. | The PCBA intends to have the environmental assessment amendment for areas previously described as aerial that are moving to underground approved in Q2-2012. During this time, final design for network construction, make-ready work, structural modifications (if any) to towers, FCC licensing, collocation agreements and equipment procurement will also be completed.
NT10BIX5570054 | 2012 | Q2 | Q2 - 2012 | The Environmental Assessment (EA) Update was approved in April, 2012 by the National Oceanographic and Atmospheric Administration (NOAA) grants office pursuant to the Project Modification Action Award Request (AAR) submitted in December, 2011 and approved in January, 2012. Upon final approval of the AAR and EA, The Page County Broadband Authority (PCBA) negotiated and executed Contract Amendments to three agreements with Shentel to address the project modification: Microwave and Fiber Optic Engineering and Construction Services, Fiber Optic Strands and Network System Operating and Maintenance. PCBA issued two change orders to the Agreement for Microwave and Fiber Optic Engineering and Construction Services with Shentel (amended in March, 2012). The first was issued on May 11, 2012 directing Shentel to include engineering for alternative microwave installation locations and resultant fiber routes within the Town of Shenandoah. A subsequent change order was issued on May 22, 2012 directing Shentel to re-design and engineer the connection between the Luray tower and the Luray POP from a fiber connection to microwave. Both change orders were a result of third party denial of the PCBA request to gain access to private property for microwave equipment installation in Shenandoah and microwave equipment access via fiber installation in Luray. Both changes have been a part of a discussion on June 26, 2012 with the National Telecommunications and Information Administration (NTIA) regarding submission of an Award Action Request (AAR) formalizing the project modification. PCBA also finalized negotiations with Shenandoah Valley Electric Cooperative (SVEC) in May, 2012 regarding make ready and pole attachment agreements for aerial fiber installation throughout the entire network. SVEC provided make ready cost estimates to Shentel (excluding Segment 4). SVEC estimates a time frame of six (6) weeks to complete the required make ready work for the project. SVEC work is scheduled to initiate in August and can occur concurrently with Shentel's construction efforts. Finally, the structural analyses on three towers and two water tanks was completed, a structural modification to the Luray tower was initiated, lease negotiations began with tower owners and draft contracts submitted. Permitting was completed with the Virginia Marine Resource Commission (VMRC) for two water crossings, the railroad companies for two crossings, and permit applications submitted to the Virginia Department of Transportation (VDOT) for underground work in Luray, Stanley and Springfield. Shentel submitted final a final design package for Segments 1-3 and 5 of the network to the PCBA on June 22, 2012 for final review and issuance of a Notice To Proceed (NTP) is expected in Quarter 3 (Q-3 2012). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for four (4) of five (5) network segments. | No Variance | No Variance | N/A | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for four (4) of five (5) network segments. | No Variance | Variance, new tower construction removed from the project via a project modification approved in January 2012 by NTIA and NOAA Grants Office. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for four (4) of five (5) network segments. | 1 | 0 | 0 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. The variance in the baseline in the number of last mile providers signed up in Q4-2011 (baseline was 3) is due to delays in the completion of the network design as a result of the high make-ready cost associated with pole attachments. The PCBA was directed to submit a Project Improvement Plan (PIP) response to NTIA in October 2011 and subsequently submitted a Project Modification Request in December 2011. At this time, PCBA has not signed up any new providers during this modification process. It is anticipated that that agreements will be negotiated in Q3-2012 based on the approval of the Project Modification in January 2012. | The project modification was approved by NTIA and the NOAA Grants Office in January 2012. No services established at this time, network has not yet been constructed. | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 0 | 0 | One (1) Lease Agreement signed but network not yet constructed. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design for four (4) of five (5) segments is complete. | Lease Agreement signed, network not yet constructed. | N/A | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design for four (4) of five (5) network segments is complete. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design for four (4) of five (5) network segments is complete. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design for four (4) of five (5) network segments is complete. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network has not yet been constructed. | FALSE | N/A | Upon final review by Icon Engineering and PCBA acceptance of the submitted documents on June 22, 2012, the Authority will issue a Notice to Proceed (NTP) to Shentel for initiation of construction for Segments 1-3 and 5 of the network in July 2012. Shentel is in the process of finalizing site acquisition, permitting and construction coordination for work to commence in August, 2012. The project remains on schedule for substantial completion by December 22, 2012. During the next quarter Point of presence facilities will be set in place and agreements complete with all of the Towns for ground leases. Designs will be finalized and make ready negotiations complete. The construction subcontractor(s) will be selected, under contract, and a wage determination request submitted to the NTIA/Department of Labor liaison as necessary. Permitting will be approved where necessary. It is anticipated that for the next quarter there will be 4.6 new network miles deployed. However, during the next quarter no new network miles leased, nor CAIs connected and there will be no increase in the number of signed agreements with broadband wholesalers or last mile providers. | Page County Broadband Authority | The project modification was approved by NTIA and NOAA grants office in January 2012. The EA assessment was approved in April 2012. Design work commenced upon issuance of a Notice to Proceed (NTP) on March 27, 2012. Shentel delivered the final design for Segments 1-3 and 5 of the entire network including make ready cost estimates provided by SVEC on time (June 22, 2012), but were unable to meet the deadline for completing design work for Segment 4 due to challenges in gaining permission to locate microwave equipment in the Town of Shenandoah. PCBA and Shentel worked collectively to identify an alternate site, though it does require a project modification and fiber reroute. | The PCBA intends to have the final design approved and a NTP issued at the beginning of Qtr 3-2012 for Segments 1-3 and 5. Segment 4 for the Town of Shenandoah will be finalized and approved pending project modification review by NTIA and the NOAA Grants Office. During this time,the make-ready work, structural modifications (if any) to towers, FCC licensing, collocation agreements and equipment procurement will also be completed. The PCBA also anticipates the start of construction, and initial equipment deployment to get underway. There are no anticipated impediments to project progress for Segments 1-3 and 5, the Segment 4 project modification will be under review by NTIA with expected approval in Q3-2012.
NT10BIX5570054 | 2012 | Q3 | Q3 - 2012 | Tower design was initiated on the Water Tank in the Town of Stanley and Town of Shenandoah and is near completing. Lease Agreements were signed with the Towns for locating equipment and with Tower Owners for utilizing tower space. A Notice To Proceed (NTP) was issued for design work that was submitted and approved by PCBA in Q3-2012. Segment 4 includes network construction in the Town of Shenandoah. Shenandoah Valley Electric Cooperative (SVEC) began make-ready work August 2012 and can complete work concurrently with Shentel's construction efforts. Shentel also began construction during the week of September 27, 2012 on Segment 3 in the Town of Stanley. The Broadband Authority continued meeting twice a month to ensure the project continues on time and on budget. Bi-weekly calls were held with NTIA to update on project completion. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | No Variance | No Variance | N/A | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. No new miles of fiber deployed by end of quarter. | No Variance | Variance, new tower construction removed from the project via a project modification approved in January 2012 by NTIA and NOAA Grants Office. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | 1 | 0 | 0 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. The variance in the baseline in the number of last mile providers signed up in Q4-2011 (baseline was 3) is due to delays in initiating construction and not having a firm completion date. Now that construction is underway and will be complete in Q4-2012, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. | No services established at this time,network construction began on September 27, 2012. | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 1 | 0 | One (1) Lease Agreement signed but network is not yet complete. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | Lease Agreement signed with Shentel, network is not yet complete. There will be no other agreements signed for dark fiber leasing. | Incremental Service from 1MB to 500MB will be available, but the speed tiers not yet been developed. | 0 | 0 | 0 | 0 | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | The variance is due to the need for a project modification and EA amendment approval. The project modification was approved by NTIA and NOAA Grants Office in January 2012 and final design is complete for all five network segments. Construction started on September 27, 2012. | There are no speed tiers established at this time. The PCBA will work to develop speed tiers and pricing in the final quarter of 2012. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Network is currently under construction. | FALSE | N/A | Shentel is in the process of finalizing site acquisition, permitting and construction coordination, construction began on September 27, 2012. The project remains on schedule for substantial completion by December 22, 2012. During the next quarter Point of presence facilities will be set in place and agreements complete with all of the Towns for tower leases. Make-ready work will be complete. Permitting will be approved where necessary. It is anticipated that for the next quarter there will be 4.6 new network miles deployed. During the next quarter no new network miles leased, all CAIs will be connected and there will be an increase in the number of signed agreements with broadband wholesalers or last mile providers. It is anticipated that up to two (2) broadband wholesalers/last mile providers will have signed agreements. Network testing is also slated to begin in late-December 2012. | Page County Broadband Authority | Shentel delivered the final design for Segment 4 in July 2012. Construction of the network commenced on September 27, 2012. Shentel and the PCBA are working diligently to complete the Tower Lease Agreement in the Town of Shenandoah, with resolution expected in October 2012. | During the next quarter the make-ready work and structural modifications to towers will be complete, FCC licensing, collocation agreements and equipment procurement will also be completed. The PCBA also anticipates substantial completion, new network miles deployed and equipment deployment to be complete by December 2012. There are no anticipated impediments to project progress.
NT10BIX5570054 | 2012 | Q4 | Q4 - 2012 | The Page County Broadband Authority (PCBA) completed significant milestones in Q4-2012. Network construction got underway and was completed on December 28, 2012. 6.75 miles of lateral fiber were distributed, the five (5) microwave links (totaling 26.25 miles) were installed along with the Point-of-Presence (PoP) facilities. Twenty-four (24) community anchor institutions (CAI's) were also connected. Network testing was also initiated and will be completed in Q1-2013 at which point the network will be operational. The PCBA held regular bi-weekly meetings to conduct administrative and legal business and to monitor construction progress including review of Davis-Bacon certified payrolls. The PCBA also completed all lease negotiations with Shenandoah Valley Electric Cooperative (SVEC) and the Town of Shenandoah. A Programmatic Monitoring visit was held with National Telecommunications and Information Administration (NTIA) staff to review grant and project files in December 2012. As a result of the monitoring, the PCBA has adopted formal Property Management Policies and Procedures to improve oversight of the network. Finally, the PCBA also approved a tiered pricing matrix and began marketing and outreach for potential service providers. | 33 | 0 | 0 | 0 | 7 | 5 | 0 | 4 | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | No Variance. | No Variance. | No Variance. | Variance due to project modification. High make ready estimate from incumbent electric cooperative forcing redesign to reduce fiber deployment and move to microwave connectivity and to move some areas of construction from aerial to underground. Project modification approval in January 2012 by NTIA and NOAA Grants Office and work restarted to implement the project. | No Variance. | No Variance. | No Variance. | 1 | 0 | 0 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. The variance in the baseline in the number of last mile providers signed up in Q4-2011 (baseline was 3) was due to delays in initiating construction and not having a firm completion date. Now that construction is complete and the pricing matrix has been approved, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. | The PCBA has adopted a tiered pricing model for service. The pricing matrix is attached as an addendum to the Q4-2012 Performance Progress Report (PPR). | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 1 | 5 | Variance. One (1) lease agreement has been signed. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Lease Agreement signed with Shentel. There will be no other agreements signed for dark fiber leasing. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. There are twenty four (24) speed tiers from 1MBPS to 500MBPS. Please see attached pricing matrix. | 24 | 0 | 24 | 5 | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. There are twenty four (24) speed tiers from 1MBPS to 500MBPS. Please see attached pricing matrix. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | TRUE | The PCBA formally adopted Property Management Policies and Procedures to ensure accurate property inventory, capitalization and planning for upgrades and expansion. | During the next quarter the PCBA will have completed all network testing and the network will be "live" for potential service and last mile providers. The PCBA will begin to actively reach out to providers that have expressed interest and initiate contract proceedings. The PCBA anticipates having one (1) or two (2) new last mile providers agreements in place by the end of the next quarter. The project is scheduled to be complete on February 28, 2013 after which final project close-out activities will be initiated. | Page County Broadband Authority | The Page County Broadband Authority (PCBA) completed significant milestones in Q4-2012. Network construction got underway and was completed on December 28, 2012. 6.75 miles of lateral fiber were distributed, the five (5) microwave links were installed (totaling 26.25 miles) along with the Point-of-Presence (PoP) facilities. Twenty-four (24) community anchor institutions (CAI's) were also connected. Network testing was also initiated and will be completed in Q1-2013 at which point the network will be operational. | The project is scheduled to be complete on February 28, 2013 after which final project close-out activities will be initiated. There are no anticipated challenges in Q1-2013.
NT10BIX5570054 | 2013 | Q1 | Q1 - 2013 | The Page County Broadband Authority (PCBA) completed significant milestones in Q1-2013; reaching the end date for Broadband Technology Opportunities Program (BTOP) grant funds on February 28, 2013. As completed, the PCBA Network includes 6.75 miles of lateral fiber, five (5) microwave links (totaling 26.25 miles), point-of-presence (PoP) facilities and connection of twenty four (24) community anchor institutions. Network testing was also completed during this quarter, and a tiered pricing matrix was adopted. The PCBA network is now operational and the PCBA is actively marketing the network to last mile service providers. The PCBA held regular bi-weekly meetings to conduct administrative and legal business and monitor project progress. This included development of to-be-adopted Master Service Agreements for connectivity to the network. | 33 | 0 | 0 | 0 | 7 | 5 | 0 | 5 | Variance due to project modification that utilized microwave back haul in lieu of fiber. | No Variance. | No Variance. | No Variance. | Variance due to project modification that utilized microwave back haul in lieu of fiber. | Variance due to project modification that utilized microwave back haul. | Variance. Project modification eliminated new tower construction. | No Variance. | 1 | 0 | 40 | Shenandoah Long Distance Company (Shentel)--a wholesale broadband provider. There were no new wholesale or last mile providers signed in Q1-2013. Project was completed on February 28, 2013. | The PCBA has adopted a tiered pricing model for service. The pricing matrix is attached as an addendum to the Q1-2013 Final Performance Progress Report (PPR). | Shentel will operate all of the Page County Broadband Authority network as contractor. Lease agreement includes all maintenance required on the network infrastructure and operating equipment. Contact: James Funkhouser (james.funkhouser@emp.shentel.com) | 1 | 0 | 0 | 5 | No Variance. One signed Lease Agreement with Shentel includes microwave backbone and dark fiber. | Variance due to recent completion of project. PCBA currently negotiating agreements with new providers. | No Variance. | There are twenty five (5) speed tiers from 1MBPS to 500MBPS. Please see attached pricing matrix. | 24 | 0 | 24 | 5 | the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | Variance. Project modification approved in January 2012 reduced the number of CAI's connected to twenty-four (24) receiving improved broadband access. No CAI's received new access. | There are twenty five (5) speed tiers from 1MBPS to 500MBPS. Please see attached pricing matrix. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable. | FALSE | Not applicable. | Q1-2013 was the final quarter for the project. Project was completed on February 28, 2013. Grant close-out is the only significant project accomplishment planned for completion in the next quarter. | Page County Broadband Authority | With the project modification and changes completed, the PCBA was not able to utilize balance of funds to reinvest project savings to expand project prior to the grant end date. The project was completed on February 28, 2013 and grant close-out was initiated. | Project was completed on February 28, 2013. No anticipated challenges are expected for the next quarter during grant close-out.
NT10BIX5570055 | 2010 | Q3 | Q3 - 2010 | Major Accomplishments include the following: Final Draft of Environmental Assessment (EA) has been completed and submitted. Request for Proposals(RFP) for the following are complete and have been published on the NTUA website: Fiber Optic Cable (OPGW), Fiber Optic Cable (All Dielectric Loose Tube Fiber), Microwave/Broadband Towers, Electronics Equipment & Installation, Installation of All Dielectric Loose Tube Fiber Optic Cable by lashing onto Neutral Wire of Existing Distribution Lines, Replacement of Static Wire on Existing Transmission Lines with Optical Ground Shield Wire (OPGW) ,35KW Natural Gas Standby Generator, and Fiberglass Telecommunications Shelters. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 6 | 0 | None | Please refer to attachment A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Significant project accomplishments include commencing the RFP process and procuring of all equipment and materials. Other project accomplishments include starting construction process with the intent to start providing services to completed segments. Furthermore, finalizing agreements with wholesale and last mile providers is projected to be completed. | Navajo Tribal Utility Authority Company | Challenges are abound when dealing with a project of this magnitude. During the past quarter, our biggest challenge was to complete and submit the Environmental Assessment. Other challenges include finalizing the ROW. | The most significant challenge for the following quarter involves securing BIA approval for Right of Way, finishing RFP process and finalizing equipment procurement, and starting construction on the Mountain pass between Tohatchi to the Coalmine Substation before weather conditions become perilous.
NT10BIX5570055 | 2010 | Q4 | Q4 - 2010 | Significant project accomplishments completed during this quarter include the following: The majority of the request for proposal (RFP) process has been completed; both loose tube fiber optic cable and optical ground wire (OPGW) have been ordered. Concrete and Fiberglass Shelters, generators, and the electronics required to light the fibers have been ordered. The contractors required to physically build the broadband system have been chosen and are ready for construction as soon as materials arrive. Contractors for building tower sites have been finalized for two tower locations and four more tower RFPs are in process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The reason for variances from the baseline for the fiber miles deployed is as follows: Delay is due to receipt of fiber orders and compliance with Rural Utility Service (RUS) regulations. The NTUA initiated its procurement process consistent with the terms of the Grant Award, e.g., did not place orders for certain material until after the Environmental Assessment had been completed. Since that time, NTUA staff has been working diligently to complete material and equipment orders to meet the overall project schedule. Further, NTUA has additionally faced the task of having the material installed on RUS-backed infrastructure be approved by RUS. Unfortunately, such approval can only occur after the vendor has been selected and installation specifics are known. In addition to the protracted procurement process, NTUA has also been improving upon its existing materials management plan, working with NTUA Safety department to implement a plan for flaggers, road crossing, etc... The N | No Variance | No Variance | No Variance | Please refer to New Network miles deployed | Currently waiting on tower build out. | Variances from the baseline regarding towers and wireless links: Delay is due to the completion of the procurement, as described in the new network miles deployed area. Further, due to the weather conditions at the end of the year, construction of the towers has been further delayed. Under such cold weather and snow on the ground, foundations have a risk to break. Any delay related to in wireless links is directly related to the towers; once the towers are in place, the wireless links can be connected. The contracts for towers should be completed shortly and with the improving weather conditions, we anticipate catching up on the tower builds during the spring and summer. | No Variance | 0 | 6 | 0 | None | Please refer to attachment A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | 0 | 0 | 0 | 0 | 0 | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | 0 | 0 | 0 | 0 | 0 | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | Please refer to Question #4 (network miles deployed) | N/A | FALSE | N/A | Significant project accomplishments planned for completion during this quarter are as follows: Procurement of all materials and equipment to begin construction of fiber optic backbone, creating a materials management plan to handle logistics problems, and finalizing agreements with wholesale and last mile providers. | Navajo Tribal Utility Authority Company | Challenges faced during quarter 4 include the following: Training Staff on following the rules and procedures as stipulated in the grant guidelines, finalizing all procurement contracts and ordering materials to commence construction, and finishing the right of way (ROW) process. | Challenges anticipated during the next quarter include logistics and coordination between the fiber optic cable vendors, construction contractors, and NTUA warehouse, finishing the make ready, and finalizing the ROW.
NT10BIX5570055 | 2011 | Q1 | Q1 - 2011 | The most significant project accomplishment for this quarter is the start of the fiber optic construction and the start of construction of towers. Other major accomplishments include the formal signing of the sub-recipient agreement, finalizing a materials management plan for the fiber optic construction, and completing the Joint Venture agreements between NTUA and Commnet Newco. | 30 | 0 | 0 | 0 | 30 | 0 | 2 | 0 | Reasons for the variance in the number of network miles deployed are as follows: The formal acceptance of the EA created a three month delay in the entire project. The delay trickled down to all aspects of the project from the RFP process to ordering materials to construction. NUTA plans on mitigating the delay by adding additional crews and sub-contractors. | NTUA anticipated leasing 200 miles of fiber optic outside plant by the end of the quarter. The reason for the variance is the IRU agreement has not been finalized. A draft agreement is currently in circulation and NTUA anticipates signing the agreement prior to the start of the next quarter. | No Variance | No Variance | Reasons for the variance include the following: 1. Delays in make ready. To expedite the make ready work, NTUA will add crews from within NTUA or from contractors. 2. Additional RUS requirements for OPGW construction. To expedite the RUS approval, NTUA has worked with the RUS to complete the first span and created a model for subsequent spans. 3. Delays in obtaining state road crossing permits. To avoid work stoppage and further delays, the NTUA has instructed the contractor to continue with the build out and dead-end the fibers in areas where they have not obtained the permits. 4. Delays in obtaining all materials for fiber optic build out. To expedite the process, NTUA has instructed the vendors to deliver all hardware and cable in a lump sum rather than a phased approach. | Variance due to protracted procurement process, including vendor responses, evaluations, and site visits. NTUA will select a vendor to be approved by the NTUA Board during its May board meeting. | Reasons for the variance in the number of towers built or under construction: 1. Delay caused by obtaining the EA. NTUA will continue to expedite tower construction based on the sites within the approved FONSI parameters, and will also seek an amendment to the EA due to actions of the local community and changes in technology that require significant relocation of at least two tower sites. 2. Weather - NTUA will continue to expedite tower construction and equipment installation during the current and next two seasons to maximize the potential for optimal weather for tower installation. | NTUA anticipated having 1 interconnection point by the end of the quarter. NTUA is in the final stages of negotiating an interconnection agreement with a third party that should be completed in the current quarter. | 1 | 6 | 0 | Commnet Newco | N/A | The last mile portion of the grant will be operated by NTUA Wireless (Sub-recipient). Name: NTUA Wireless LLC CO: Walter Haase Address: NTUA Wireless LLC c/o NTUA Highway 12 North Fort Defiance, AZ 86504 | 0 | 0 | 0 | 0 | NTUA anticipated one signed agreement and NTUA is in the final stages of negotiating the agreement with a third party, which should be completed in the current quarter. | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | The variance is due to the network is not available to provide services at this time. NTUA anticipates being able to secure subscribers before the end of the calendar year. | The variance is due to the network is not available to provide services at this time. NTUA anticipates being able to secure subscribers before the end of the calendar year. | No Variance | No speed tiers available at this time. | 0 | 0 | 0 | 0 | 0 | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the entities passed before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the total subscribers served before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the subscribers receiving new access before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the subscribers receiving improved access before the end of the calendar year. | No speed tiers available at this time. | 0 | 0 | 0 | 0 | 0 | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the entities passed before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the total subscribers served before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the subscribers receiving new access before the end of the calendar year. | The variance is due to the unavailability of the network to provide services at this time. NTUA anticipates being able to catch up on the subscribers receiving improved access before the end of the calendar year. | No speed tiers available at this time. | N/A | FALSE | N/A | Significant project accomplishments planned for completion during the next quarter are as follows: Submit any/all changes in fiber route and tower change requests to the NTIA for approval, finish fiber optic construction between several key communities within NM and AZ, finish construction on numerous additional towers, begin construction on Electronics Shelter locations including pouring foundations and selecting vendor for fencing around Shelters and finalize selection of vendor for last mile components including 4G LTE selection. | Navajo Tribal Utility Authority Company | Major Challenges include the following: 1. Obtaining EA amendments for revised tower sites. 2. Obtaining the remainder of the road permits for the fiber optic construction. 3. The weather; the windy season began in the proposed area as fiber optic and tower construction was commencing. Furthermore, NTUA has identified that prior SF425s need amending and we are working with the NTIA to accomplish the changes; however NTUA does not anticipate amending previous Performance Progress Reports. | Major Challenges include the following: 1. Having any EA amendments for revised tower or fiber sites expedited for completion. Any assistance from the BTOP program would be greatly appreciated. 2. Obtaining the remainder of the road permits and resolving the Indian Allotments Issue for the fiber optic construction. To expedite the process, NTUA has hired consultants to resolve the Indian Allotment issue and NTUA has hired T&D Surveyors to expedite the road crossing permits.
NT10BIX5570055 | 2011 | Q2 | Q2 - 2011 | Significant project accomplishments for this quarter are listed below 1. Data Center and Network Operating Center (NOC) construction commencement 2. Completion of over 80 miles of fiber optic plant 3. Reaching final stages of Critical Agreements including Tri-State and Scared Wind 4. Hiring Consultant to work on Indian Allotments issues 5. Ordering all fiber optic cable and hardware in advance to avoid potential shortages in supply 6. Formal signing of Electronics Contract | 80 | 0 | 0 | 0 | 80 | 0 | 2 | 0 | Variance is due to an elongated RUS approval process as well as delays in make ready. | Variance is due to an extended negotiation process regarding the IRU. NTUA is in the final stages of the agreement and anticipate signing early next quarter. We note that NTUA did agree to an MOU with the Navajo Nation in the second quarter. | Variance is due to delay in finalizing IRU agreements. NTUA is in the final stage of signing the IRU Agreement. | Variance is due to delay in finalizing IRU agreements. NTUA is in the final stage of signing the IRU Agreement. | Variance is due to an elongated RUS approval process for approval of OPGW installation, as well as delays in make ready. | Variance is due to delays in physical network build out. NTUA is developing remedies to increase production of build out. | Variance is due to delays in RFP process in selecting tower building contractor. NTUA is currently building 8 new tower sites and anticipates completion of additional towers in 6-8 weeks. | Variance is due to delay in finalizing IRU agreements. NTUA is in the final stage of signing the IRU Agreement. | 1 | 6 | 0 | NTUA Wireless, LLC | NTUA is currently conducting a formal Broadband Rate Study to determine the wholesale services and associated pricing. | The last mile portion of the grant will be operated by NTUA Wireless. Name: NTUA Wireless LLC c/o Navajo Tribal Utility Authority Highway 12-N Fort Defiance, AZ 86504 | 0 | 0 | 0 | 0 | Variance is due to an elongated IRU agreement process. NTUA is in the final stages | No Variance | Variance is due to an elongated IRU agreement process. NTUA is in the final stages | No Variance | 0 | 0 | 0 | 0 | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | No Variance | No Speed tiers available at this time | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | No Speed tiers available at this time | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | Variance is due to delays in network build. NTUA is taking steps to increase production | No Speed tiers available at this time | N/A | FALSE | N/A | Significant project accomplishments slated for next quarter include the following: 1. Resolving the Indian Allotment Issue 2. Energizing a portion of the fiber optic build out and commence with network testing 3. Finalizing the IRU agreement as well as the Scared Wind agreement 4. Delivery, installation, and configuration of Shelters and Electronics for phase 1 5. Installation of additional Tower structures 6. Marketing for last mile services with the hiring of new General Manager for NTUA Wireless, Inc. 7. Completion of new LTE equipment ordering | Navajo Tribal Utility Authority Company | Issues faced during this past quarter in achieving planned progress against the project milestones include the following: 1. Obtaining RUS Approval for fiber optic build out. 2. Delays in make ready 3. Obtaining consent from Indian Allottees. 4. Obtaining all construction permits in Arizona. | Challenge 1. Resolving the Indian Allotment Issue 2. Weather related issues - NTUA will be in their rainy season 3. Energizing a portion of the fiber optic build out to commence with network testing 4. Timely approvals of OPGW installation by RUS
NT10BIX5570055 | 2011 | Q3 | Q3 - 2011 | Significant project accomplishments for this quarter are listed below. 1. Completion of Network Operating Center 2. Completion of 120 miles of fiber optic build out. 3. Completion of 9 additional towers for a total of 12 built to date. 4. First phase of electronics delivered. 4. Hiring of a Project Manager to supervise tower & microwave construction. 5. Commenced with Request for Proposal (RFP) process to hire contractors to assist with Make Ready. 6. Commenced with Request for Proposal (RFP) process to hire accounts manager for marketing to community anchor institutions. 7. Finalized contract with Cogent for bandwidth purchase. | 120 | 0 | 0 | 0 | 120 | 0 | 12 | 0 | Variance is due to an elongated Rural Utilities Service (RUS) approval process and delays in Make Ready. Both the RUS and Make Ready issues have been addressed. Regarding Make Ready, NTUA has hired Atkinson Power to assist. To resolve the RUS concern, NTUA has instructed it's consultants to work directly with RUS to expedite the approval process. | NTUA is in final negotiations with Tri-State and anticipates signing the indefeasible right of use (IRU) agreement prior to the end of next quarter | NTUA is not upgrading any network miles | NTUA is in final negotiations with Tri-State and anticipates signing the indefeasible right of use (IRU) agreement prior to the end of next quarter | Variance is due to an elongated Rural Utilities Service (RUS) approval process and delays in Make Ready. Both the RUS and Make Ready issues have been addressed. Regarding Make Ready, NTUA has hired Atkinson Power to assist. To resolve the RUS concern, NTUA has instructed it's consultants to work directly with RUS to expedite the approval process. | Variance is due to delays in physical network buildout as well as delays in the Microwave deployment. NTUA in conjunction with its last mile sub-recipient is developing a contingency plan for wireless link deployment. | Variance is due to previous delays caused by weather, environmental assessments and changes in location. NTUA has resolved the majority of the issues and has greatly increased production of towers. NTUA in the previous quarter constructed three towers. This quarter, nine additional towers were constructed. NTUA anticipates building an additional fourteen towers by the end of the year | Variance is due to delays in the signing of the indefeasible right of use (IRU) agreement. NTUA is in final negotiations with Tri-State and anticipates signing the contract prior to the end of next quarter | 5 | 2 | 4 | NTUA Wireless LLC - As the grant Sub-recipient, NTUA Wireless will be will be working on the wireless service. NTUA and Navajo Nation have signed an agreement to provide dark fibers to the Navajo Nation. The agreement will be for the life of the fiber optic system. Industry standards estimate fiber optic cable life spans between 20-30 years depending on various factors including type of cable, terrain, weather conditions, etc.. Cogent Communications - One year agreement for purchase of bandwidth. Cellular One - One year agreement for access to tower space. Conterra Ultra - One year agreement for access to tower space. | NTUA is currently conducting a Broadband Rate Study to determine the wholesales services and associated pricing. NTUA anticipates completion of the study prior to the end of the following quarter. | Name: NTUA Wireless LLC Type of Entity: Sub-Recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box - 1947 Chinle, AZ 86503 | 0 | 0 | 0 | 0 | Variance is due to delays in construction and delays in finalizing the indefeasible right of use (IRU) agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | 0 | 0 | 0 | 0 | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | No speed tiers available at this time | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | No speed tiers available at this time | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | Variance is due to delays in construction and delays in finalizing the IRU agreement. NTUA has taken steps to expedite the construction. | No speed tiers available at this time | N/A | FALSE | N/A | Significant project accomplishments planned for completion during the next quarter include the following: 1. Finalize and sign the Tri-State IRU agreement 2. Obtain all Rural Utilities Service (RUS) approvals 3. Finalize any route/design changes and acquire approval from NTIA 4. Energize portion of the system and commence with network testing 5. Install 50% of telecommunications shelters for fiber optic regeneration 6. Provide power to the constructed tower sites and shelters 7. Deploy 100 additional miles of fiber optic plant 8. Lease 163.3 miles of fiber optic plant 9. Construct 12 additional towers 10. Finalize Microwave contract 11. Procure all LTE equipment 12. Deploy LTE Core for testing 13. Complete 75% of Make Ready | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter in achieving planned progress against the project milestones are as follows: 1. Rural Utilities Services(RUS) approvals for optical ground wire (OPGW). 2. Weather Delays 3. Indian Allotment approvals 4. Rights of Way | Challenges anticipated during the next quarter are listed below: 1. Challenges in obtaining Indian Allotment approvals. NTUA's government liaison is working directly with the Bureau of Indian Affairs to expedite approval process. 2. Weather Delays 3. Challenges in obtaining right of way (ROW) approvals. NTUA's government liaison is working directly with the Bureau of Indian Affairs to expedite approval process.
NT10BIX5570055 | 2011 | Q4 | Q4 - 2011 | Significant project accomplishments for this quarter are listed below. 1. Completion of over 180 miles of fiber optic plant. 2. Completion of 16 towers. 3. Hiring of Atkinson Power to assist with Make Ready. 4. Completion of over 300 miles of Make Ready. 5. Procurement of all electronics for the fiber optic plant. 6. Received Grant of Easement to enter and cross Indian Allotment 1961. 7. Procured all LTE equipment (last mile) from ZTE and commenced with installation on towers. 8. Installed 10 LTE Base Stations. 9. Completion of Request for Proposal for last mile modems. 10. Commenced with an integration plan to allow for seamless communication between microwave, fiber optics, and LTE equipment. 11. Commenced with plan to provide power to all towers and fiber electronics shelters. | 183 | 0 | 0 | 0 | 183 | 0 | 16 | 0 | Variance is due to delays in make ready and lack of easement rights to transverse Indian Allotments. NTUA has alleviated the make ready issues by hiring additional contractors to assist existing crews and NTUA has taken steps to either obtain the Indian Allotment approvals or developed alternative solutions to by-pass problematic areas. | N/A | N/A | N/A | Variance is due delays in make ready and lack of easement rights to transverse Indian Allotments. NTUA has alleviated the make ready issues by hiring additional contractors to assist existing crews and NTUA has taken steps to either obtain the Indian Allotment approvals or developed alternative solutions to by-pass problematic areas. | Variance is due to delays in physical network build out as well as delays in the microwave procurement. NTUA is scheduled to obtain all microwave equipment during the next quarter. | Variance is due to previous delays in tower construction. NTUA anticipates completion of 25 towers prior to the end of the following quarter. | Variance is due to delays in the physical network build out. | 5 | 2 | 4 | NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. Cogent Communications - NTUA has an agreement to purchase bandwidth for one year. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA is in the process of finalizing their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DAI), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. The speed tiers that will be available for subscribers within the NTUA Broadband Tariff will be priced upon completion of the broadband rate study. | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | N/A | FALSE | N/A | 1. Finalize the integration plan to allow for seamless communications between NTUA various systems including fiber optics, microwave, and LTE wireless equipment. 2. Completion of all Make Ready work. 3. Finalizing Broadband Rate Study. 4. Deployment of electronics to energizing the systems 5. Installation of telecommunications shelters 6. Procurement of all microwave equipment. 7. Construction of 70% of fiber optic plant. NTUA anticipates completion of over 400 miles of fiber plant by the end of the next quarter. 8. Construction of 75% of all towers. NTUA anticipates completion of 25 towers by the end of next quarter. 9. Deployment of LTE Core and 33 LTE Base Stations. 10. NTUA is currently in the process of building laterals to the CAIs. NTUA anticipates connection to CAIs as laterals become available. 11. NTUA has 5 signed agreements with providers: NTUA Wireless, Cogent Communications, Conterra Ultra, Cellular One, and Navajo Nation. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter in achieving the planned progress are as follows: 1. Delays in obtaining easement rights to transverse Indian Allotments causing NTUA to dedicate additional resources in finding feasible solutions for by-passing the allotments. 2. Weather Delays | Challenges anticipated in the next quarter are listed below: 1. Obtaining easement rights for the remaining Indian Allotments. 2. Weather
NT10BIX5570055 | 2012 | Q1 | Q1 - 2012 | Significant project accomplishments completed during this quarter include the following: 1. 368 miles of fiber optic construction complete (67%). 2. 451 miles of Make Ready complete (82%). 3. 23 towers complete (72%) 4. Data Center Building Construction Complete (100%). 5. NTUA has commenced with a solar powered microwave solution to by-pass Indian Allotment 1928. | 368 | 0 | 0 | 0 | 368 | 0 | 23 | 0 | Variance is due to previous delays in make ready and lack of easement rights to transverse Indian Allotments. NTUA has alleviated the make ready issues and hired a consultant to address the allotment issue. | N/A | N/A | N/A | Variance is due to previous delays in make ready and lack of easement rights to transverse Indian Allotments. NTUA has alleviated the make ready issues and hired a consultant to address the allotment issue. | Variance is due to delays in the microwave procurement process. NTUA has completed the microwave procurement process and anticipates delivery, staging, and installation of wireless links starting during the first month of the following quarter. | Variance is due to previous delays in tower construction. NTUA anticipates completion of 26 towers during the first month of the next quarter with six towers remaining to construct. | Variance is due to delays in the physical network build out. | 5 | 2 | 4 | NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. Cogent Communications - NTUA has an agreement to purchase bandwidth for one year. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. NTUA shall present the findings of the rate study to the NTUA board of directors during the first month of the following quarter for approval at which time the rates will be published. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. The speed tiers that will be available for subscribers within the NTUA Broadband Tariff shall be published after NTUA Board approval. | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. NTUA Wireless (Sub-recipient) shall publish their residential rates with the launch of their marketing plan. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. | Variance is due to delays in construction. NTUA has taken appropriate steps to expedite construction. The speed tiers that will be available for subscribers within the NTUA Broadband Tariff shall be published after NTUA Board approval. | N/A | FALSE | N/A | 1. Completion of all Make Ready work. 2. Approval of the Broadband Tariff by NTUA Board of Directors 3. Energizing the 2/3 of the fiber optic systems. 4. Procurement of all microwave equipment. 5. Construction of over 85% of fiber optic plant. NTUA anticipates completion of over 475 miles of fiber plant by the end of the next quarter. 6. Construction of 26 towers. Submission and NTIA approval of six tower site changes. 7. Deployment of over 50% of LTE Base Stations. 8. Providing power to over 75% of telecommunications shelters and community anchor institutions. 9. Providing power to 100% of constructed tower sites. 10. NTUA anticipates connecting one CAI, the Upper Fruitland Chapter House before the end of the next quarter. 11. NTUA anticipates no additional broadband wholesaler/last mile provider agreements signed by the end of the next quarter. NTUA is currently in negotiations with CenturyLink for a backup path to the Albuquerque point of presence. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter in achieving the planned progress are as follows: 1. Delays in obtaining easement rights to transverse Indian Allotments causing NTUA to dedicate additional resources for by-passing the allotments. NTUA commenced with a solar powered microwave solution to by pass Indian Allotment 1928 until easements are granted. 2. Weather related delays including rain/snow, muddy conditions, and high winds. | Challenges anticipated in the next quarter are listed below: 1. Obtaining easement rights for the remaining Indian Allotments. 2. Weather related delays including rain, muddy conditions, and high winds.
NT10BIX5570055 | 2012 | Q2 | Q2 - 2012 | Significant Project accomplishments completed during this quarter include the following: 1. 420 miles of fiber optic construction complete (76%) 2. 546 miles of Make Ready complete (99%) 3. 26 towers complete (81%) 4. Data Center/Network Operating Center (100%) 5. 35 LTE base stations installed (87%) 6. Six Microwave Links installed (12%) | 420 | 163 | 0 | 0 | 420 | 6 | 26 | 0 | Variance is due to the lack of easement rights to transverse the Indian Allotments | No Variance | No Variance | No Variance | Variance is due to the lack of easement rights to transverse the Indian Allotments | Variance is due to delays in the procurement of the microwave links and remaining tower construction. NTUA has procured all microwave equipment. With respect to the remaining tower construction, NTUA has submitted an AAR for three of the remaining six towers. The remaining towers are in the EA process and NTUA anticipates submittal of an AAR prior to the end of the next quarter | Variance is due to changes in the location for the remaining six towers. | Variance is due to delays in the physical network build out. | 5 | 2 | 4 | NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. Cogent Communications - NTUA has an agreement to purchase bandwidth for one year. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. NTUA shall submit the pro forma and sustainability plan to the NTIA prior to the end of the following quarter. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | N/A | FALSE | N/A | Significant project accomplishments slated for completion during the third quarter are listed below: 1. All Make Ready shall be complete. 2. Construction of 95% of the fiber optic backbone shall be compete for a total of 530 miles. The remaining 20 miles require easement rights to cross the Indian Allotments between Bitahochee to Dilkon. 3. Construction of 80% of the fiber optic laterals to the community anchor institutions (CAI) and towers shall be complete for a total of 16 miles. 4. A total of 29 towers shall be constructed equating to 90% completed. Depending on environmental assessment and NTIA approval, the three towers that require EA are slated for completion during the first month of quarter 4. 5. Power to all laterals shall be complete including towers and CAIs. 6. Installation of all Last Mile 4G LTE base stations shall be complete. 7. Inspection of Phase 1,2 and 3 fiber optic outside plant including construction clean up shall be complete and close out packets sent to the Rural Utility Service (RUS) 8. Inspection of telecommunications regeneration and electronics shelters for phase 1 & 2 shall be complete and close out packets sent to the Rural Utility Service (RUS). 9. Distribution Plan for issuing Last Mile netbooks shall be completed. 10. NTUA is in negotiations with CenturyLink for a backup route to the point of presence. The NTUA anticipates no additional wholesale/LM provider agreements next quarter. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter in achieving the planned progress are listed below. 1. Delays in obtaining easement rights to transverse Indian Allotments. NTUA has developed a contingency plan to temporarily by-pass the allotments utilizing a solar powered microwave solution. 2. Delays in submitting an award action request regarding tower site changes to NTIA for approval. Three of the six remaining towers have been submitted for approval. NTUA is in the process of finishing the EA for the remaining sites. NTUA anticipates submittal of the award action request for the three remaining towers prior to the end of the next quarter. 3. Weather related issues including rain, muddy conditions, and high winds. | Challenges anticipated during the next quarter include the following: 1. Obtaining easement rights for the Indian Allotments. 2. Finishing the environmental assessment in a timely manner and submitting the award action request for the three remaining towers to NTIA. 3. Weather related delays including rain, muddy conditions, and high winds. 4. Approval of the tower award action requests. 5. Submittal of Dilcon to Bitahochee Alternative Microwave Solutions.
NT10BIX5570055 | 2012 | Q3 | Q3 - 2012 | 1. 465.3 miles of fiber optic backbone construction complete (84%) 2. 4.6 miles of fiber laterals complete for a total of 15 of the 27 community anchor institutions (CAI) are connected. In addition, one CAI connection (Lechee Chapter House) via microwave has been completed. The NTUA is obligated to connect a total of 49 CAI of which 27 are connected via the fiber optic system. 3. 26 towers complete (81%) 4. Data Center/Network Operating Center (100%) 5. 35 LTE base stations installed (87%). ZTE will be on site during the between November through December 2012 to finalize install and testing of all last mile devices. 6. Twenty two Microwave Links have been installed (55%) of which 18 have been fully tested and are traffic ready. | 569 | 170 | 0 | 0 | 488 | 18 | 26 | 0 | Variance in the number of new miles deployed is due to the contractor allocating some of their resources for clean upon segments already constructed. The clean up is required for final close out and certification in order to commence with the internal audit process. In addition to the 465.3 fiber backbone miles deployed, NTUA also deployed 4.6 miles in fiber laterals and 81.22 miles of point to point microwave to connect the Lechee Chapter House. Total new miles deployed is 569. NTUA shall complete all construction of outside plant prior to the end of the next quarter. | No Variance | No Variance | No Variance | Variance in the number of new miles deployed is due to the contractor allocating some of their resources to clean up and deviations on segments already constructed. NTUA requires the segments already constructed to be ready for final approval and certification in order to commence with the internal audit process. NTUA shall complete all construction of outside plant prior to the end of the next quarter. | Variance is due to previous delays in the procurement of the microwave equipment and remaining tower construction. All new wireless links will be installed prior to the end of the next quarter. | Variance is due to changes in the location of the six remaining towers. NTUA anticipates receiving approval and constructing the remaining towers prior to the end of the next quarter. | Variance is due to delays in the physical network build out. | 5 | 2 | 4 | NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. Cogent Communications - NTUA has an agreement to purchase bandwidth for one year. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. NTUA shall submit the pro forma and sustainability plan to the NTIA prior to the end of the following quarter. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 16 | 16 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. A total of 16 community anchor institutions have been connected. 15 via fiber optics and 1 via microwave. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | The speed tiers that are available for CAIs are listed below: 1.0-3.0 Mbps download speed. 0.5-2.0 Mbps upload speed. If a CAI required additional capacity, NTUA shall have custom solutions available up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | N/A | FALSE | N/A | Significant project accomplishments planned for completion during the next quarter include the following: 1. NTUA anticipates building 86 miles of fiber optic backbone and laterals for a total of 573 new miles fiber miles deployed. This will complete all fiber optic construction. 2. NTUA anticipates completion of remaining 22 CAI's; this will completed all 49 CAI connections. 3. NTUA anticipates completion of 7 broadband wholesaler agreements and 3 last mile provider agreements. 4. NTUA anticipates all microwave installation complete. 5. NTUA anticipates all towers complete. 6. All Last mile 4G LTE equipment installed. 7. Complete distribution of netbooks. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter in achieving the planned progress include the following: 1. Delays in submitting the required information with respect to the award action requests which resulted in the a delayed approval process. 2. Delays in obtaining the easement rights to transverse the Indian Allotments. NTUA has a contingency plan which is currently being executed and will allow NTUA to meet its obligations to the grant. 3. Weather related issues. | While NTUA does not anticipate any challenges during the next quarter that may impact planned progress, there is a slight possibility of encountering issues in which providing power to the sites is outside of the NTUA service territory. The locations in questions include the following, 1. Cameron Chapter House Monopole - Power provided by APS 2. Mexican Water (Water Tank) - Power provided by Rocky Mountain Power 3. Nageezi Tower- Power provided by Jemez Electric. With respect to Nageezi, the tower is not grant related however the microwave equipment is grant related. The NTUA has a contingency plan in place for all three sites however NTUA does not foresee any issues. NTUA has scheduled in advance with the various power companies to finish their work before the end of the next quarter.
NT10BIX5570055 | 2012 | Q4 | Q4 - 2012 | 1. 525 miles of fiber optic backbone construction complete (95%) 2. 18.5 miles of fiber laterals complete for a total of 23 of the 27 community anchor institutions (CAI) are connected via fiber optics. In addition, one CAI connection (Lechee Chapter House) via microwave has been completed. 3. 26 of the 32 towers completed (81%). 3. Thirty six of the forty eight Microwave Links have been installed (75%). | 1067 | 171 | 0 | 0 | 544 | 36 | 26 | 0 | Variance in the number of new fiber miles deployed is due to the contractor allocating some of their resources for clean upon segments already constructed. The clean up is required for final close out and certification in order to commence with the internal audit process. In addition to the 525 fiber backbone miles deployed, NTUA also deployed 18.5 miles in fiber laterals and 524 miles of point to point microwave links. Total new miles deployed is 1067.5. | No Variance | No Variance | No Variance | Variance due to the contractor allocating some of their resources to clean up and deviations on segments already constructed. NTUA requires the segments already constructed to be ready for final approval and certification in order to commence with the internal audit process. NTUA shall complete all construction of outside plant before the end of the next quarter. | Variance is due to delays in the tower construction. NTUA has received approval to build the remaining towers and are proceeding with construction. | Variance is due to weather related issues changes in the location of the six remaining towers. NTUA has received NTIA approval for site changes and are proceeding with construction. | No Variance | 4 | 2 | 4 | 1. NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. 2. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. 3. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. 4. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. NTUA shall submit the pro forma and sustainability plan to the NTIA prior to the end of the following quarter. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 3 | 0 | 1 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 24 | 24 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. A total of 24 community anchor institutions have been connected. 23 via fiber optics and 1 via microwave. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | The speed tiers that are available for CAIs are listed below: 1.0-3.0 Mbps download speed. 0.5-2.0 Mbps upload speed. If a CAI required additional capacity, NTUA shall have custom solutions available up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. | Variance is due to delays in construction. NTUA has taken the appropriate measures to expedite construction. NTUA has hired an independent party to review the findings of the Broadband Rate Study and develop a sustainable financial pro forma. | N/A | FALSE | N/A | Significant accomplishments planned for completion during the next quarter including the following. 1. All fiber optic construction (571 miles) including the backbone and laterals shall be complete. 2. 30 of the 32 towers will be complete equating to 94% completion. 3. 43 of 49 Community Anchor institutions will be complete equating to 87% 4. 44 of the 48 microwave links will be installed and tested equating to 92% completion. 5. 18 of the 43 LTE sites will be fully tested, optimized, and ready for friendly user trials equating to 43% completion. 6. Regarding broadband wholesaler/last mile provider agreements, NTUA does not anticipate any new agreements completed during the following quarter. NTUA is currently in negotiations with CenturyLink to provide them capacity from Farmington to Shiprock. Also, NTUA anticipates finalizing the agreements with the Navajo Nation to provide them services as addressed in the Memorandum of Understanding signed by both parties. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter include the following: 1. Weather related issues. 2. Holiday Season causing shortages of staff. 3. Delays in tower construction. | Challenges anticipated during the next quarter include closing out work order packages and performing an internal audit prior to closing out project.
NT10BIX5570055 | 2013 | Q1 | Q1 - 2013 | 1. All outside plant fiber optic construction (both laterals and backbone) are 100% complete. 2. 28 of 32 towers are complete equating to 88% complete. NTUA anticipates all tower construction to be completed by next quarter. 3. 36 of the 48 microwave links are installed equating to 75% completion. 4. 38 of 50 connections to the Community Anchor Institutions (CAI) are installed equating to 76% complete. 5. 14 of the 43 Last Mile LTE sites have been tested and commissioned for service; equating to 33% complete. | 1244 | 171 | 0 | 0 | 570 | 36 | 28 | 0 | Total number of fiber optic network miles deployed is 570 which completes the fiber optic construction. Total number of point to point microwave miles completed is 673.68. | No Variance | No Variance | No Variance | No Variance | Variance is due to delays in tower construction | Variance is due to weather delays | No Variance | 4 | 2 | 4 | 1. NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. 2. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. 3. Cellular One - NTUA has an agreement with Cellular One to lease tower space for one year. 4. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for one year. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study will cover bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. NTUA shall submit the pro forma and sustainability plan to the NTIA prior to the end of the following quarter. | Name: NTUA Wireless LLC Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 3 | 0 | 1 | 0 | Variance is due to delays in construction. | No Variance | No Variance | See Attachment A | 38 | 38 | 0 | 0 | Variance is due to delays in tower construction. NTUA has taken the appropriate steps to finish construction. | Variance is due to delays in tower construction. NTUA has taken the appropriate steps to finish construction. | No Variance | Variance is due to delays in negotiations between NTUA Wireless and Navajo Nation Telecommunications Regulatory Commission. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | 0 | 0 | 0 | 0 | 0 | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to delays in tower construction which have led to delays in LTE 4G launch. | N/A | FALSE | N/A | Significant project accomplishments planned for completion during next quarter include the following: 1. 550 miles of fiber optic backbone and 20 miles of fiber optic laterals shall be constructed equating to 100% complete. 2. 32 of 32 towers constructed equating to 100% complete. 3. 47 of the 48 microwave links installed equating to 98% complete. The remaining microwave link at the Escrito Mesa Site shall be completed in August 2013. 4. 50 of the 50 connections to the Community Anchor Institutions shall be finished equating to 100% complete. 5. NTUA anticipates 40 of the 40 LTE sites to be constructed equating to 100% complete. 6. NTUA anticipates finalizing negotiations with potential wholesale providers. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter include the following. 1. Weather related issues. 2. Delays in tower construction. 3. Delays in procuring electronics. | NTUA anticipates potential weather related challenges (High Wind Season).
NT10BIX5570055 | 2013 | Q2 | Q2 - 2013 | 1. NTUA has completed 100% of the tower construction. 2. NTUA has installed and tested a total of 42 out of 48 microwave links equating to 88% completion. The total point to point microwave miles completed is 674.57 out of 774.99 equating to 87% complete. The remaining links are in progress. NTUA anticipates completion of all microwave links within the next quarter. 3. NTUA has installed 40 of the 43 LTE sites equating to 93% completion. The remaining sites will be installed within the next quarter. All LTE sites will be tested and commercial ready by end of August 2013. 4. Nine (9) CAI connections were completed during the quarter for a total of 47 out of 50 Community Anchor Institutions (CAI) complete equating to 94% completion. The remaining three CAIs (Tolani Lake, Hard Rock, Kaibeto) will be complete within the next quarter. | 1245 | 171 | 0 | 0 | 570 | 42 | 32 | 0 | Total number of fiber optic network miles deployed is 570 which completes the fiber optic construction. Total number of point to point microwave miles completed is 674.57 out of 774.99. | No Variance | No Variance | No Variance | No Variance | Variance is due to previous delays in tower construction and vendor scheduling. NTUA anticipates completion of all microwave links within the next quarter. | No Variance | No Variance | 4 | 2 | 4 | 1. NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. 2. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. 3. Cellular One - NTUA has an agreement with Cellular One to lease tower space for five years. 4. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for five years. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study covers bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. | Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 3 | 0 | 1 | 0 | Variance is due to delays in contract negotiations between parties. | No Variance | No Variance | Refer to Attachment A for speed tiers. | 47 | 47 | 0 | 0 | Variance is due to previous delays in tower and microwave link construction. All CAIs will be connected within the next quarter. | Variance is due to previous delays in tower and microwave link construction. All CAIs will be connected within the next quarter. | No Variance | Please refer to Attachment A for speed tiers. | 0 | 0 | 0 | 0 | 0 | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Please refer to Attachment B for speed tiers | 0 | 0 | 0 | 0 | 0 | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Variance is due to previous delays in tower construction which have led to delays in LTE 4G launch. | Please refer to Attachment A & B | N/A | FALSE | N/A | 1. Completion of all construction, testing and commissioning. 2. Commence with the word of mouth (WOM) launch at the various NTUA district offices. The Last Mile 4G wireless products will be sold at the NTUA district offices. Wholesale middle mile services will be sold via the NTUA Data Center. 3. Completion of Grant and Close out Procedures. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter include the following. 1. Weather related issues. 2. Vendor coordination and scheduling issues 3. Delays in procuring electronics. With respect to the delays in obtaining electronics, NTUA has procured all the required gear to complete the project. | No challenges anticipated. NTUA looks forward to a smooth close out process and completion of the BTOP grant.
NT10BIX5570055 | 2013 | Q3 | Q3 - 2013 | 1. NTUA has completed 100% of the tower construction. 2. NTUA has installed and tested a total of 48 out of 48 microwave links equating to 100% completion. The total point to point microwave miles completed is 775 out of 775. There is some additional cleanup work involved with the microwave link installation which is scheduled to be completed prior to the end of the next quarter. 3. NTUA has installed 41 of the 43 LTE sites equating to 95% completion. The two remaining sites will be installed within the next quarter. 4. NTUA has completed 100% of the Community Anchor Institutions (CAI) connection. | 1345 | 171 | 0 | 0 | 570 | 48 | 32 | 0 | Total number of fiber optic network miles deployed is 570 which completes the fiber optic construction. Total number of point to point microwave miles is 775 which concludes the Middle Mile portion of the grant. | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | 4 | 2 | 4 | 1. NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. 2. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. 3. Cellular One - NTUA has an agreements with Cellular One to multiple lease tower spaces for five years. 4. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for five years. | NTUA has finalized their Broadband Rate Study to determine wholesale services and associated pricing. The rate study covers bandwidth pricing for dark fibers, dedicated internet access (DIA), point to point services, and transport services from their Data Center to a point of presence in Albuquerque. To validate the findings of the rate study, NTUA has hired an independent party to develop a financial pro forma and a sustainability plan. | Type of Entity: Sub-recipient CO: Michael Scully Address: NTUA Wireless LLC P.O. Box 1947 Chinle, AZ 86503 | 3 | 0 | 1 | 3 | Variance is due to delays in contract negotiations between parties. | No Variance | No Variance | Tiers 10 Mbps - 1 subscriber 100 Mbps - 1 subscriber 1000 Mbps - 1 subscriber Please refer to Attachment A for further details of speed tiers. | 50 | 50 | 0 | 3 | No Variance; NTUA is offering services at all 50 CAI sites however no CAI have currently signed up to purchase bandwidth. | No Variance | No Variance | NTUA is offering services at all 50 CAI sites however no CAIs associated with the grant have currently signed up to purchase bandwidth. 10 Mbps - 0 subscriber 100 Mbps - 0 subscriber 1000 Mbps - 0 subscriber Please refer to Attachment A for further details of speed tiers. | 0 | 0 | 0 | 0 | 2 | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Refer to Attachment B | 0 | 0 | 0 | 0 | 0 | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Variance is due to resolving any network bugs in the system prior to a full scale retail launch. | Refer to Attachments A & B | N/A | FALSE | N/A | 1. Completion of all construction, testing and commissioning. 2. Commence with the word of mouth (WOM) launch at the various NTUA district offices. The Last Mile 4G wireless products will be sold at the NTUA district offices. Wholesale middle mile services will be sold via the NTUA Data Center. 3. Completion of Grant and Close out Procedures. | Navajo Tribal Utility Authority Company | Challenges faced during the past quarter include the following. 1. Vendor coordination and scheduling issues 2. Technical network issues within the last mile network. NTUA has taken the requisite steps to resolve any and all network issues. | No challenges anticipated. NTUA looks forward to a smooth close out process and completion of the BTOP grant.
NT10BIX5570055 | 2013 | Q4 | Q4 - 2013 | Significant project accomplishments completed during this quarter include 100% completion of all middle and last mile construction. The NTUA has successfully constructed a Data Center/Network Operating Center, 600 miles of fiber optic plant, 32 new cellular/ microwave towers, installed 48 microwave links, and installed 43 new 4G LTE links. This is a major accomplishment for the NTUA for a multitude of reasons. Firstly, prior to receiving assistance from the NTIA, the Navajo Nation suffered from a lack of viable telecommunications infrastructure. The lack of proper infrastructure greatly diminished chances for sustainable economic development and social benefits. The Navajo Nation Middle/Last Mile Project: Quality Broadband for the Navajo People, has increased access to broadband in a sparselypopulated, poverty-stricken rural area in which residents had fallen further and further behind the rest of the country. This project has leveled the playing field by providing access to critical facilities including tribal and federal facilities, police, detention, and fire response centers; health, social service, and emergency care facilities; public, BIE, and private schools; and tribal Chapter Houses. The integrated middle and last-mile network design will support point to point data services and large broadband connections for commercial carriers and government and institutional users alike. Additionally, a last-mile 4G LTE wireless network will provide mobile and fixed broadband access for residents, businesses, and government customers. The wireless network component of the project will enable a variety of vital education broadband services currently inaccessible to many students residing out of reach of any current broadband provider. The wireless network also offers a highly functional and secure data network solution to support law enforcement, fire protection, and other emergency care providers. This greatly expands the ability of the tribal public safety and communications departments to provide enhanced 911 services. Secondly, the BTOP project has fulfilled an important cultural component by extending the bandwidth to Chapter houses which had limited extended services from central administration and educational institutions. Chapter houses on the Navajo Nation are more than just municipal buildings. They are, to a certain degree, the heart of the cultural exchange in which political discussions, elderly care and early childhood education are carried out. Using technologies enabled only by broadband, the Project has allowed Navajo communities to capture, record, and share Navajo culture, including language, politics, lifestyle and religion. Navajo culture will be preserved, as the Navajo people are able to remain home while joining the information highway. In conclusion, with the assistance provided by the NTIA, the NTUA now has the tools to dramatically improve the quality of life on the Navajo Nation as well as begin the process of communicating and competing on a global scale. | 1345 | 171 | 0 | 0 | 570 | 48 | 32 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | 5 | 3 | 20 | 1. NTUA Wireless LLC - As the grant sub-recipient, NTUA Wireless will be working on the wireless services. 2. NTUA has signed an agreement to provide the Navajo Nation dark fibers. The agreement will be for the life of the fiber optic plant. NTUA anticipates the fiber optic plant to span 20-30 years without replacement. 3. Cellular One - NTUA has an agreements with Cellular One to multiple lease tower spaces for five years. 4. Conterra Ultra - NTUA has an agreement with Conterra Ultra to lease tower space for five years. 5. Wecom Inc - NTUA has an agreement with Wecom for both backhaul and tower space rental for five years. | NTUA provides the following services as a result of this project. 1. Point to Point Microwave Services 2. Point to Point Dedicated Internet Access (DIA) 3. Transport services from Navajo Nation to Albuquerque New Mexico Point of Presence 4. Transport services within the Navajo Nation Refer to Attachment A for pricing details. | Entity Name: NTUA Wireless LLC CO: Michael Scully Address: P.O. Box 1947, Chinle, AZ 86503 Description: NTUA Wireless has purchased bandwidth from NTUA to sell last mile services, with the option of reselling the bandwidth. | 4 | 0 | 1 | 7 | Variance is due to continued negotiations between parties | No Variance | No Variance | NTUA offers bandwidth in the following increments. 1 Mbps - 0 subscribers 5 Mbps - 0 subscribers 10 Mbps - 0 subscribers 20 Mbps - 0 subscribers 50 Mbps - 0 subscribers 100 Mbps - 1 subscriber 500 Mbps - 0 subscribers For customers that require a specific circuit size not listed above, NTUA will review on a case by case basis. Furthermore, for those customers that require larger pipes (greater than 500Mbps), NTUA will review and negotiate each case separately. 200 Mbps (Transport from Data Center to Albuquerque NM) - 1 subscriber 3100 Mbps - 1 subscriber (Bandwidth for LTE sites) Please refer to Attachment A for further details of speed tiers as well as transport services. | 50 | 50 | 0 | 7 | No Variance; NTUA is offering services at all 50 CAI sites however no CAI have currently signed up to purchase bandwidth. | No Variance | No Variance | NTUA is offering services at all 50 CAI sites however no CAIs associated with the grant have currently signed up to purchase bandwidth. 1 Mbps 5 Mbps 10 Mbps 20 Mbps 50 Mbps 100 Mbps 500 Mbps | 29756 | 479 | 479 | 0 | 4 | No Variance | Variance is due to a initial delays in retail launch | Variance is due to a initial delays in retail launch | No Variance | Variance is due to the additional plans offered. As of December 31, 2013, NTUAW has the following subscribers: Rate Plan $27.95 - (765 Kbps) 81 Subscribers $39.95 - (1.5 Mbps)140 Subscribers $49.95 - (2.0 Mbps)184 Subscribers $79.95 - (3.0 Mbps) 74 Subscribers | 1000 | 3 | 3 | 0 | 7 | No Variance | Variance is due to delays in launch as well as businesses waiting for their existing contracts to expire | Variance is due to delays in launch as well as businesses waiting for their existing contracts to expire | No Variance | NTUA offers bandwidth in the following increments. 1 Mbps - 0 subscribers 5 Mbps - 0 subscribers 10 Mbps - 1 subscriber 20 Mbps - 1 subscriber 50 Mbps - 0 subscribers 100 Mbps - 0 subscribers 500 Mbps - 0 subscribers For customers that require a specific circuit size not listed above, NTUA will review on a case by case basis. Furthermore, for those customers that require larger pipes (greater than 500Mbps), NTUA will review and negotiate each case separately. 30 Mbps - 1 subscriber Please refer to Attachment A for further details of speed tiers as well as transport services. | N/A | FALSE | N/A | None. The project is complete. | Navajo Tribal Utility Authority Company | Challenges faced during this past quarter included finishing the installation of the microwave links while the NTUA staff were sent to China for a month long training. All work has been completed. | None. The project is complete.
NT10BIX5570056 | 2010 | Q3 | Q3 - 2010 | Updated radio network coverage plan, planned competitive bidding process for backhaul and wholesale agreements, and construction agreements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | In the process of requesting tower/route change. | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Will complete network design, begin site preparation, network procurement, and network build. | DigitalBridge Communications Corp. | Two-month delay in hiring dedicated project manager and financial analyst (has not led to any variances from baseline plan to date.) | Winter weather can sometimes slow progress in southern Idaho.
NT10BIX5570056 | 2010 | Q4 | Q4 - 2010 | Finalized network design and recommended tower/route change to improve coverage and cost effectiveness. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalizing rights of way, construction permits, and site preparation. | DigitalBridge Communications Corp. | Tower/route change request and weather delays caused DBC to delay seeking approval for rights of way, construction permits, and initiating site preparation activities. In addition, DBC strategic shifts slowed implementation during December. | Will be briefing NTIA on potential changes in organization structure and estimating revised completion date.
NT10BIX5570056 | 2011 | Q1 | Q1 - 2011 | Identified potential purchaser of DBC Idaho assets. Purchaser may become sub-recipient and has commitment to complete project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Idaho assets by August 1. | DigitalBridge Communications Corp. | DBC Strategic caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is omitted to complete project. | BTOP assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570056 | 2011 | Q2 | Q2 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets and/or potential Award Subrecipient. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | N/A | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | FALSE | N/A | Sale of DBC Assets by October 1, at which project implementation will be re-started. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is committed to complete project. | BTOP Assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570056 | 2011 | Q3 | Q3 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Assets by November 15. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser is committed to complete project. | BTOP Assistance will be required in conducting due diligence on potential buyer.
NT10BIX5570056 | 2011 | Q4 | Q4 - 2011 | Project on hold pending review of progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project on hold pending review of progress. | DigitalBridge Communications Corp. | Project on hold pending review of progress. | N/A
NT10BIX5570056 | 2012 | Q1 | Q1 - 2012 | Project has been terminated for convenience since buyer of DBC assets has decided not to take on BTOP Awards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project has been terminated for convenience. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. | Project has been termianted
NT10BIX5570057 | 2010 | Q3 | Q3 - 2010 | Updated radio network coverage plan, planned competitive bidding process for backhaul and wholesale agreements, and construction agreements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Will complete network design, begin site preparation, network procurement, and network build. | DigitalBridge Communications Corp. | Two-month delay in hiring dedicated project manager and financial analyst (has not led to any variances from baseline plan to date.) | Winter weather can sometimes slow progress in southern Idaho.
NT10BIX5570057 | 2010 | Q4 | Q4 - 2010 | Updated radio network plan to improve coverage and cost effectiveness. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | Project will not serve this type of subscriber. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalizing network plan, securing rights of way and seeking construction permits and approvals. | DigitalBridge Communications Corp. | DBC strategic shifts slowed implementation during December, but project is still on track to be completed by 6/30/11. | Will be briefing NITA on potential changes in organization structure and estimating final completion date.
NT10BIX5570057 | 2011 | Q1 | Q1 - 2011 | Identified potential purchaser of DBC Idaho assets. Purchaser may become sub-recipient and has commitment to complete project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Idaho assets by August 1. | DigitalBridge Communications Corp. | DBC Strategic caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is omitted to complete project. | BTOP assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570057 | 2011 | Q2 | Q2 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets and/or potential Award Subrecipient. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | N/A | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | FALSE | N/A | Sale of DBC Assets by October 1, at which point project implementation will be re-started. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is committed to complete project. | BTOP Assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570057 | 2011 | Q3 | Q3 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Assets by November 15. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser is committed to complete project. | BTOP Assistance will be required in conducting due diligence on potential buyer.
NT10BIX5570057 | 2011 | Q4 | Q4 - 2011 | Project on holding pending progress review. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project on hold pending progress review. | DigitalBridge Communications Corp. | Project on hold pending progress review. | N/A
NT10BIX5570057 | 2012 | Q1 | Q1 - 2012 | Project has been terminated for convenience since buyer of DBC assets has decided not to take on BTOP Awards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project has been terminated for convenience. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. | Project has been termianted
NT10BIX5570058 | 2010 | Q3 | Q3 - 2010 | All field mapping has been completed. Engineering is completed, with construction contract documents currently being drafted. All pole attachment agreements have been completed. State right-of-way Encroachment Permit has been approved and received. All easements have been identified, and no additional easements are needed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | N/A | 0 | 0 | 0 | N/A. No agreements executed | Grant Recipient does not plan at this time to offer wholesale services, as there is no information to believe there is any demand in the project area for wholesale services. | N/A, Grant Recipient will operate all of the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | 0 | 0 | 0 | 0 | 0 | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | 0 | 0 | 0 | 0 | 0 | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | At this time, no special offerings have been considered. | FALSE | No | Anticipate advertising for network (aerial fiber) construction and equipment procurement. Anticipate construction of the network to begin, and equipment purchases to take place. | City of Williamstown | Had difficulty in obtaining prompt approval of State Highway Encroachment Permit, however, other staff intervened and we have received the State Highway Encroachment Permit. Engineering and especially construction documents have been slow to be completed by vendors, compounding the difference between the original baseline report and this report. | Unanticipated winter weather could negatively impact the progress of this project. Holidays are also expected to increase delay in project time-line. This project will proceed rapidly after notice to proceed is issued to winning contractor and equipment vendor(s).
NT10BIX5570058 | 2010 | Q4 | Q4 - 2010 | Bids for equipment and construction Advertised and Awarded. Five (5) miles of aerial cable has been constructed. Sixty percent (60%) of equipment received. Work proceeding as winter weather permits. | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | No variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 0 | 0 | N/A No agreements executed | Grant Recipient does not plan at this time to offer wholesale services, as there is no information to believe there is any demand in the project area for wholesale services. | N/A, Grant Recipient will operate all of the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance, Network not yet constructed | No Variance, Network not yet constructed | N/A | No Variance, Network not yet constructed | 50 | 0 | 0 | 0 | 0 | Projection was estimate of project time line and was relative to what section of plant was constructed, the 5 mile constructed was in a lower house count per mile section. | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | No Variance, Network not yet constructed | 6 | 0 | 0 | 0 | 0 | Projection was estimate of project time line and the 5 miles constructed did not cover enough area to catch the other two entities projected. | Construction still in progress, network not yet active. | Construction still in progress, network not yet active. | No Variance, Network not yet constructed | No Variance, Network not yet constructed | At this time, no special offerings have been considered. | FALSE | No | Anticipate significantly fiber construction to take place, however, winter weather could have negative impact on performance. ARRA signs for vehicles and at strategic ground location have been installed. Project Administrator is in process of scheduling outreach meetings in project area for residents and institutions. | City of Williamstown | Engineer and Consultant were slow in producing draft plans and contract for contractor, respectively. Contract has now been received, approved, and executed by both City and Construction Contractor Bowlin Services. | Project is moving along nicely. Winter weather has been especially harsh this year, and is resulting in some slowdowns. No other negative issues are anticipated at this time.
NT10BIX5570058 | 2011 | Q1 | Q1 - 2011 | We are well ahead of the baselines mainly due to having little to no issues this quarter, the contractor has made good progress and caught us up to and ahead of our baselines. They have installed about 95 percent of the fiber and approximately 50 percent of the equipment. | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | Ahead of baseline due to contractors abilities and few obstacles. | N/A | N/A | N/A | Ahead of baseline due to contractors abilities and few obstacles. | N/A | N/A | N/A | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services, will address is there is request however we do not anticipate any from area served. | N/A We (Grant Recipient) will operate all of the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | 640 | 0 | 0 | 0 | 0 | We have constructed fiber in front of 640 homes, the 640 is part of the 662 total in baseline. Contractor is ahead of schedule for miles constructed. | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | 33 | 0 | 0 | 0 | 0 | We have constructed fiber in front of 33 businesses which is the 33 total from baseline. Contractor is ahead of schedule for miles constructed | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | No variance, Network not yet completed. | N/A network not yet completed | FALSE | N/A | We are planning on having 100 percent of the fiber installed along with all taps and electronics in the outside plant installed and be at least 50 percent tested. | City of Williamstown | Our only issues this quarter has been the weather which obviously is beyond any ones control, even with the weather we were able to get ahead of our baseline. | None Anticipated.
NT10BIX5570058 | 2011 | Q2 | Q2 - 2011 | We have approximately 99% of the fiber installed and 99% of electronics in place, with at least half of the equipment being placed during this quarter. At the end of the quarter we have began our testing and held our community informative meeting. Contractors have only billed us for 76% of construction. | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | We have slightly over 1500 feet of fiber yet to lash up. | n/a | n/a | n/a | We have slightly over 1500 feet of fiber yet to lash up. | n/a | n/a | No variation from baseline. | 0 | 0 | 0 | n/a | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | n/a - We, "grant recipient," will operate all the network. | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | 670 | 0 | 0 | 0 | 0 | Approximately 1500 feet of fiber to be placed to fulfill the other 12 residents, this fiber will be placed the first week of Q2. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | 36 | 0 | 0 | 0 | 0 | Have constructed fiber and equipment in front of all 36, all the fiber that passes businesses in place. | Network not yet complete; no variance from baseline. | Network not yet complete; no variance from baseline. | Network not yet compete; no variance from baseline. | Network not yet complete; no variance from baseline. | n/a - Network not yet complete. | FALSE | n/a | We should have 100 percent of plant built - both fiber and electronics, have all the testing complete, and have a large start on hooking up customers. | City of Williamstown | No challenges or issues this quarter other than weather. | None anticipated.
NT10BIX5570058 | 2011 | Q3 | Q3 - 2011 | During the quarter contractor finished the last 1500 feet of construction and completed all the testing, at the end of quarter we was reviewing their final invoice and will process payment within the first couple weeks of October. We began taking service orders and have installed service to 61 customers. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | No variation from baseline | N/A | N/A | N/A | No variation from baseline | N/A | N/A | No variation from baseline | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | N/A - We "grant recipient" will operate all the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 3 | 3 | 0 | 3 | No variation from baseline | No variation from baseline | No variation from baseline | All three are receiving 10 Mbps | 682 | 61 | 61 | 0 | 61 | No variation from baseline | Ahead of Baseline | Ahead of Baseline | N/A | All 61 are receiving 10 Mbps | 36 | 0 | 0 | 0 | 0 | Ahead of Baseline, All businesses have fiber plant at property | Have not marketed to the businesses as of this quarter, will be marketing to them early Q4. | Have not marketed to the businesses as of this quarter, will be marketing to them early Q4. | N/A | Have not marketed to the businesses as of this quarter, will be marketing to them early Q4. 10 Mbps is available. | N/A None at present time. | FALSE | N/A | We plan on continued marketing/promoting of the service to both residential and businesses to increase subscriber numbers. | City of Williamstown | The only real challenge we're facing both in this quarter and going forward is getting subscribers due to the economy being slow and people not taking on many new bills. Hopefully with additional notices of availability and advertising it will pick up. | The only challenge we anticipate is getting subscribers, we feel the economy is affecting the customers as to their signing up at this time, unfortunately at this time we feel all we can do is continue to market/promote the service.
NT10BIX5570058 | 2011 | Q4 | Q4 - 2011 | At the end of quarter we are finished with all the construction of main line fiber and well into installing subscribers. It was a slow quarter because of several major holidays and weather during the quarter, we have 66 internet customers at the end of December. Some of the installs were completed by a contractor early in the period. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | No variation from baseline. | N/A | N/A | N/A | No variation from baseline. | N/A | N/A | No variation from baseline. | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | N/A - We "grant recipient" will operate all the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 4 | 4 | 0 | 3 | We listed three in our baseline, however during the project we found out there was two public housing units one of the two was installed this quarter with the second being placed in near future. | We listed three in our baseline, however during the project we found out there was two public housing units one of the two was installed this quarter with the second being placed in near future. | No variation from baseline. | We offer 10 Mbps, 15 Mbps and 50 Mbps. All Community Anchor Institutes are currently receiving 10 Mbps. | 682 | 66 | 66 | 0 | 66 | No variation from baseline. | Ahead of baseline. | Ahead of baseline. | N/A | 65 receiving 10 Mbps. One is receiving 50 Mbps. | 36 | 3 | 3 | 0 | 3 | Ahead of baseline, all businesses have fiber plant at property. | We have not marketed all the businesses at this time. | We have not marketed all the businesses at this time. | N/A | All three are receiving 10 Mbps. | N/A None at present time. | FALSE | N/A | We plan or increased marketing to the area in order to increase customer/business counts, and hope to close out the project. | City of Williamstown | We had the situation of the quarter having some major holidays along with weather and the economy being slow coupled with holiday spending potential customers are slow to sign up for service, we have started stepping up marketing to the area. Other than getting customers to sign up we have not experienced any challenges. | The only challenge we anticipate is getting subscribers, we feel the economy is affecting the customers as to their signing up at this time, unfortunately at this time we feel all we can do is continue to market/promote the service.
NT10BIX5570058 | 2012 | Q1 | Q1 - 2012 | All the construction was finished in Q4/11, in Q1/12 we have been installing customers and marketing the services. At the end of Q1/12 we had 86 customers. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | No variation from baseline. | N/A | N/A | N/A | No variation from baseline. | N/A | N/A | No variation from baseline. | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | N/A - We "grant recipient" will operate all the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 4 | 4 | 0 | 3 | We listed three in our base line but there are two public housing units in project with one of them connected. We will add the second unit when customers sign up and we plan on approaching those residents this quarter about service offerings. | We listed three in our base line but there are two public housing units in project with one of them connected. We will add the second unit when customers sign up and we plan on approaching those residents this quarter about service offerings. | No variation from base line. | We offer 10 Mbps, 15 Mbps and 50 Mbps. All Community Anchor Institutes are currently receiving 10 Mbps. | 682 | 86 | 86 | 0 | 3 | No variation from base line. | Slightly under the 103 in baseline, sign up's have slowed continued marketing planned. | Slightly under the 103 in baseline, sign up's have slowed continued marketing planned. | N/A | We offer 10 Mbps, 15 Mbps and 50 Mbps. 85 have 10 Mbps with one having 50 Mbps. | 36 | 3 | 3 | 0 | 3 | Ahead of baseline, all businesses have fiber plant at property. | We have not marketed all the businesses at this time. | We have not marketed all the businesses at this time. | N/A | We offer 10 Mbps, 15 Mbps and 50 Mbps. all three are receiving 10 Mbps. | N/A none at present time. | FALSE | N/A | We plan or increased marketing to the area in order to increase customer/business counts, and hope to close out the project. We are planning on marketing to the fifth CAI during next quarter and hope to get that public housing unit installed, that would be the last of the 5 CAI locations in the project. | City of Williamstown | With the project build complete we have not faced any challenges other than the slow economy which we feel is at least partly responsible for the lower number of sign ups. We are continuing to market the area. | The only challenge we anticipate is getting subscribers, we feel the economy is affecting the customers as to their signing up at this time, unfortunately at this time we feel all we can do is continue to market/promote the service.
NT10BIX5570058 | 2012 | Q2 | Q2 - 2012 | All the construction was finished in Q4/11, in Q2/12 we have been installing customers and marketing the services. At the end of Q2/12 we had 86 customers. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | No variation from baseline | N/A | N/A | N/A | No variation from baseline. | N/A | N/A | No variation from baseline. | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | N/A - We "grant recipient" will operate all the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 4 | 4 | 0 | 4 | We listed three in our baseline but there are two public housing units in the project with one of them connected. We will add the second unit when customers sign up. | We listed three in our baseline but there are two public housing units in the project with one of them connected. We will add the second unit when customers sign up. | No variation from baseline. | We offer 10 Mbps, 15 Mbps. and 50 Mbps. all community Anchor institutes are currently receiving 10 Mbps. | 682 | 86 | 86 | 0 | 3 | No variation from baseline. | Under baseline due to slow sign ups. | Under baseline due to slow sign ups. | N/A | We offer 10 Mbps, 15 Mbps. and 50 Mbps. 78 have 10 Mbps, 7 have 15 Mbps, and one has 50 Mbps. | 36 | 3 | 3 | 0 | 3 | Ahead of baseline, all businesses have fiber plant at property. | We have not marketed to all businesses at this time. | We have not marketed to all businesses at this time. | N/A | We offer 10 Mbps, 15 Mbps. and 50 Mbps. All three are receiving 10 Mbps. | N/A none at present time | FALSE | N/A | We plan on increasing the marketing to the area in attempt to increase subscriber and business counts as well as pick up the last public housing complex to complete the 5 CAI's. | City of Williamstown | With the project build complete we have not faced any challenges other than the slow economy which we feel is at least partly responsible for the lower number of sign ups. We are continuing to market the area. | The only challenge we anticipate is getting subscribers, we feel this is more challenging partly due to the economy, however we will continue to market/promote the services.
NT10BIX5570058 | 2012 | Q3 | Q3 - 2012 | Construction was completed in Q4/11, we have been installing customers and promoting the services and will continue to do so. Final draws have been made. We currently have 91 subscribers. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | No Variation from baseline. | N/A | N/A | N/A | No Variation from baseline. | N/A | N/A | No Variation from baseline. | 0 | 0 | 0 | N/A | At this time we have no plans of offering wholesale services. We will address if there is a request however we do not anticipate any from the area served. | N/A - We "grant recipient" will operate all the network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 5 | 5 | 0 | 3 | We listed three in our baseline but there are two public housing units in the project area. All five have been installed. | We listed three in our baseline but there are two public housing units in the project area. All five have been installed. | N/A | We offer 10 Mbps,15 Mbps and 50 Mbps. all 5 are receiving 10 Mbps. | 682 | 91 | 91 | 0 | 3 | No variation from baseline. | Ahead of baseline, all draw downs have been made. | Ahead of baseline, all draw downs have been made. | N/A | We offer 10 Mbps,15 Mbps and 50 Mbps. 81 has 10 Mbps, 9 has 15 Mbps and 1 has 50 Mbps. | 36 | 5 | 5 | 0 | 3 | Ahead of baseline, all businesses have fiber plant at property. | Small businesses that we are still marketing to. | Small businesses that we are still marketing to. | N/A | We offer 10 Mbps,15 Mbps and 50 Mbps. All 4 has 10 Mbps. | N/A None at present time. | FALSE | N/A | We plan on continued marketing of all services to the area in order to increase the customer base and broadband connectivity to the area. | City of Williamstown | Project complete with all draw downs made. | None expected.
NT10BIX5570059 | 2010 | Q3 | Q3 - 2010 | The Environmental Assessment was submitted for to the National Technology and Information Administration (NTIA) for approval during this quarter. Review and revisions of the Network Design continued throughout the quarter in anticipation of the final network design and project implementation. Project planning and implementation, a major component of any successful project, continued to account for the majority of time and resources allocated to the project this quarter. Pend Oreille PUD took a proactive approach to its responsibility for keeping the public and shareholders informed about the project. This quarter's Community outreach activities included (1) a booth at the county fair, (2) design, printing, and distribution of an informational brochures and (3) design, development, and continual updating of project progress on Pend Oreille's Web Site (4) magnetic ARRA logo signs for contractor vehicles. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | None at this time as the project as construction has not yet started. However, meetings have been facilitated with potential providers to keep them informed and enthusiastic regarding the project. | Bandwidth Capacity will be provided as a wholesale service to Retail Service Providers per the attached Rate Schedule. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 24 | 0 | 0 | 24 | N/A | N/A | N/A | 10 Meg Port | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 10 | 0 | 0 | 0 | 10 | N/A | N/A | N/A | N/A | 10 Meg Port | None at this time in the project. | FALSE | N/A | We are anticipating receipt of Finding of No Significant Impact on our Environmental Assessment. During this waiting period we are finalizing the design of the network which will achieve our baseline projection. Drafting materials procurement, performing field staking and preparing construction bid packages are additional activities we will be performing. We will continue with acquiring permits, right of ways and licenses to be in line with baseline projections by the end of the 4th quarter. | Public Utility District of Pend Oreille County | Network Design continues to undergo minor modifications in equipment, however all routes, easements, and right of ways are not affected. The equipment modifications will not alter the overall project. The BTOP resource for technical assistance, though appreciated, is not required at this time. | If Environmental Assessment (EA) approval is not received early in this quarter, progress on the project will be stalled/impeded. Also, site preparation could be delayed depending on the weather patterns. If the temperatures are below normal and precipitation above normal in this quarter the project could experience further delay.
NT10BIX5570059 | 2010 | Q4 | Q4 - 2010 | Pend Oreille PUD continued work toward finalizing their network design, acquiring permits and right of ways, as well as developing plans and specifications for contracts to be bid. Project planning meetings were held throughout the quarter to insure common goals and timelines are established for the remainder of the project. Marketing of our project to the community continues through various media sources. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | No variance. | N/A | N/A | N/A | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | None at this time of the project timeline as construction has not yet started. However, meetings have been facilitated with potential providers to keep them informed and enthusiastic regarding the project. | Bandwidth Capacity will be provided as a wholesale service to Retail Service Providers per the previously submitted Rate Schedule. | N/A | 0 | 0 | 0 | 0 | Agreements are in process, however have not been signed at this point in time. Anticipation is that we will bring this category milestone up to plan by Quarter 3 of 2011. | N/A | N/A | N/A | 24 | 0 | 0 | 24 | No variance. | N/A | No variance. | 10 Meg Port | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | N/A | 10 | 0 | 0 | 0 | 10 | No variance. | No variance. | No variance. | No variance. | 10 Meg Port | None at this time in the project. | FALSE | N/A | Pend Oreille will release plans and specifications for Fiber material, outside plant construction, and some electronics. Awards will be made for Fiber, Electronics, and Outside Plant Construction. Fiber material will be ordered with expecting partial delivery in the quarter. Permitting with the State will continue and receipt of Finding of No Significant Impact (FONSI) should also be received very early in this next quarter. | Public Utility District of Pend Oreille County | No specific or identifiable issues were discovered during this phase of the project. The only measurable that we missed was receiving our Finding of No Significant Impact (FONSI) in the current quarter by a few days. This will have no impact on project timeliness or adverse effects. The BTOP resource for assistance, though appreciated, is not required at this time. | Weather may be the only potential that we see that could impact progress this next quarter. Any delays would be observed in Site Preparation of Construction if we experience below average temperatures or above average precipitation this next quarter.
NT10BIX5570059 | 2011 | Q1 | Q1 - 2011 | Pend Oreille PUD received their Finding of No Significant Impact (FONSI) at the beginning of the quarter. This led to increased activity in the staking of routes as well as the preparation and ultimate ordering of owner supplied materials for the project. Pre-Construction activities included an Outside Plant pre-bid meeting held on March 30th, attended by forty (40) contractors. In addition, our material bid for Fiber was completed and awarded. Our Marketing and Community Outreach efforts continue with informational meetings being held, our Website redesigned and updated with project details, and Social Media avenues being researched. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 30-Although originally projected to begin construction in the first quarter of 2011, delays in Environmental submission and Network design have pushed the network build out. As a result, miles will not begin to be reported in this quarter. We do anticipate, however, reaching our milestone by end of the calendar year. | N/A | N/A | N/A | 30-See narrative above under 'new network miles deployed'. | No Variance. | No Variance. | 1-No variance. | 0 | 0 | 0 | None at this time of the project timeline as construction has not yet started. However, meetings with potential wholesalers have been facilitated to keep them informed and enthusiastic about the project. We are doing this in collaboration with last mile providers as well. | Bandwidth Capacity will be provided as a wholesale service to Retail Service Providers per the previously submitted Rate Schedule. | N/A | 0 | 0 | 0 | 0 | 2-Agreements are in process, however have not been signed at this point in time. Anticipation is that we will bring this category milestone up to plan by Quarter 3 of 2011. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 24-Although originally included in our Baseline, since improvement has not been made to these original list of 24 Anchor Institutions, they will not be included here for reporting purposes. | N/A | No Variance. | See comment above. | 0 | 0 | 0 | 0 | 0 | Baseline 240-Construction has not commenced on the segment of the project that passes Residences. | No Variance. | No Variance. | No Variance. | N/A | 0 | 10 | 0 | 0 | 10 | 10-This number was inadvertently used on the baseline, but should have been in the line below as 'Total Subscribers we currently serve with existing network'. Since this network is part of our In-Kind contribution, it is BTOP Funded. As the network is built, this metric will be completed. | 2-We currently have ten business subscribers being served by existing BTOP Funded (In-Kind) network. | No Variance. | No Variance. | 10-10 Meg Port. | None at this time in the project. | FALSE | N/A | Construction is expected to commence as we head into the second quarter of 2011, with bids being let and awarded during the April timeframe for both Outside Plant and Make-Ready work. Progress will continue on acquiring permits and staking of select routes. Equipment bids and specifications for materials will be prepared and made available in preparation for bid letting. Additional Marketing and Community Relations events will be planned for ground breaking ceremonies and other public stakeholder affairs. Job creation is expected to be stimulated by construction activities, staking, and other activities as a result of this award. | Public Utility District of Pend Oreille County | No specific or identifiable issues developed over the course of this reporting quarter. However, assistance will always be appreciated when needed. | Although nothing is anticipated at this time, technical assistance is always appreciated when and if required.
NT10BIX5570059 | 2011 | Q2 | Q2 - 2011 | Pend Oreille Public Utility District celebrated the start of aerial build construction during this quarter. A Celebration Event and Ribbon Cutting were held to kick off this stage of the project, being attended by Federal, State and Local officials. Community outreach efforts continued with events being scheduled through the end of the year to promote our story and excite our potential wholesale providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Baseline 200-Although originally projected to begin construction in the first quarter of 2011, delays in Environmental submittal and Network Design have pushed back the build schedule. | N/A | N/A | N/A | See narrative under 'new network miles deployed' above. | No Variance. | No Variance. | No variance. | 0 | 0 | 0 | None at this time in the project timeline as we have just started construction. However, meetings with potential wholesalers continue to develop as we keep them informed of progress and enthusiastic about the project. | Bandwidth Capacity will be provided as a wholesale service to Retail Service Providers per the previously submitted rate schedule. | N/A | 0 | 0 | 0 | 0 | 2-Agreements are in process, however have not been signed at this point in time. Anticipation is that we will bring this category up to milestone projection by end of Quarter 3, 2011. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to these original list of 24 Anchor Institutions, they will not be included here for reporting purposes. | N/A | No variance | N/A | 0 | 0 | 0 | 0 | 0 | Baseline 1500-This metric is currently behind Baseline as we haven't begun this segment of construction. We anticipate beginning to reach past entities in the following quarter and begin to record those numbers. | 247- As mentioned above, construction is behind schedule and will begin to serve subscribers as service is available. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 10 | Baseline 10- This number was inadvertently used on the Baseline, but should have been in the line below listed as 'Total Subscribers served'. | 4-We currently serve ten business subscribers with existing BTOP Funded (In Kind) network services. None have prescribed for improved services at this time, however have the capability to up grade. Once service is 'turned up', these entities will have the capability of redundancy that our Network will provide. | No variance. | No variance. | 10-10 Meg Port | None at this time in the project. | FALSE | N/A | Pend Oreille Public Utility District plans to continue their aggressive build schedule for the next quarter. In addition to Make Ready work, aerial build activity will take place. | Public Utility District of Pend Oreille County | No specific or identifiable issues have developed that require or have hampered progress and assistance from BTOP is needed. As always, if required, we will ask for assistance. | Although nothing is anticipated at this time, technical assistance is always appreciated.
NT10BIX5570059 | 2011 | Q3 | Q3 - 2011 | Pend Oreille Public Utility District worked feverishly this quarter to continue it's build of both 'Make Ready' and fiber optic cable placement. Planning took place for additional construction scheduled for next calendar year. Community Outreach efforts included activities at the local County Fair to continue bringing interest and exposure to this project. | 54 | 0 | 0 | 0 | 54 | 0 | 0 | 1 | 250-Additional crews were utilized to expedite construction with projections of meeting Baseline in year three of the project. | N/A | N/A | N/A | See 'new network miles' metric above. | 1-This metric although in our original application is no longer part of the network design. | 2-Although originally called out for in the project, it is no longer included as part of this construction and network. | 1- No Variance. | 0 | 3 | 0 | None at this time in the project timeline as construction is well underway. | Bandwidth Capacity will be provided as a wholesale service to Retail Providers per the previously submitted rate schedule. | N/A | 0 | 0 | 0 | 0 | 3-Agreements are in process, however have not been signed at this point in time. Anticipation is that we will bring this category up to milestone projection by the end of Quarter 1, 2012. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24-Although originally included in our Baseline, since improvement has not been made to these original lists of 24 Anchor Institutions, they will not be included here for reporting purposes. | No Variance. | No Variance. | N/A | 0 | 0 | 0 | 0 | 0 | Baseline 1625- This metric is is currently behind Baseline as construction has recently started. Entities passed will be recorded as we reach that segment of the project. | Baseline 494-As with the above metric, we have not reached this milestone of the project cycle as of yet. Indications are sometime in the first half of 2012. | No Variance. | No Variance. | No Variance. | 0 | 0 | 0 | 0 | 10 | Baseline10- this number was inadvertently used on the Baseline, but should have been in the line below listed as "Total Subscribers served'. | 9- We currently serve ten business subscribers with existing BTOP Funded (In Kind) network services. None have prescribed for improved services at this time, however have the capability to up grade. Once service is 'turned up', these entities will have the capability of redundancy that our Network will provide. | No Variance. | No Variance. | 10-10 Meg Port | None at this time in the project cycle. | FALSE | N/A | Construction will continue at a rapid pace as long as the weather allows. Equipment specifications and procurement activities will continue for placement next year. Community Outreach efforts keeping the stakeholders and interested parties informed will continue in preparation for agreements with potential wholesalers being signed. The District has an aggressive strategy to overcome the schedule lapses due to the EA and the challenges of materials availability and weather windows. Pend Oreille PUD has nearly completed in advance of schedule the engineering for the underground project. The District intends on letting the Underground Construction Contract in early Q1 2012 with commitments to complete in Q4 2012. The contractor will be required to provide the crews and necessary workforce to facilitate an aggressive deployment schedule, but we have every confidence that this can occur. In addition, the design strategy includes placing much if not all service duct such that the fiber can be installed in winter weather conditions, specifically allowing underground work in the Q1 2013 to complete the project. The following are projections for Key Metrics to reach by the end of the quarter (cumulative): New Network Miles Deployed-240 Total CAI Subscribers Served-0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers-1 | Public Utility District of Pend Oreille County | No specific or identifiable issues stand out with fiber orders being shipped as ordered. Assistance if needed is always appreciated. | Weather is more than likely going to be a variable in whether our plan comes together as outlined in the above projections. Earlier snowfalls may limit build capability in some areas and force a slow down for periods of time. Technical assistance at this time is not anticipated, however will be appreciated if needed.
NT10BIX5570059 | 2011 | Q4 | Q4 - 2011 | The fourth quarter of 2011 was primarily focused on continued construction activity with an unseasonably warm and mild winter being experienced in the Northwest. Planning towards the underground phase of construction for the project was also taking place with activity scheduled to begin in early 2012. Finalization of retail service providers continues to evolve with numerous parties interested in providing service once the Network is active. Community Outreach and project updates to the public via media outlets and Social Media avenues continue as we keep our Communities excited about the project. | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 1 | Baseline-300-An additional 120 miles of fiber were placed in this quarter, closing the gap slightly compared to earlier Baseline projections. Crews continue to work and fiber availability is good going into 2012. | N/A | N/A | N/A | 300-See 'New Network miles deployed' above. | 1-This metric although in our original application is no longer part of the network design. | 2-Although originally called out for in the project, it is no longer included as part of this construction and network. | 1- No Variance. | 0 | 2 | 0 | None yet, although agreements have been distributed for feedback and final documents projected for next quarter. | Bandwidth capacity will be provided as a wholesale service to Retail Providers per the previously submitted rate schedule. | N/A | 0 | 0 | 0 | 0 | Baseline-3-Agreements are in process, however have not been signed as of the end of the quarter. Anticipation is that agreements will be signed and in place with two providers at the end of the first quarter 2012. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24-Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted here for reporting purposes. | No Variance. | No Variance. | N/A | 1400 | 0 | 0 | 0 | 0 | Baseline 1750- This metric is is currently behind Baseline as construction has recently started. Entities passed will be recorded as we reach that segment of the project. | Baseline 742- This metric will lag Baseline projections through the remainder of the project. Initial forecasts had services turned up and Retail Providers signed on to provide services. This will occur sometime during the latter half of 2012. | Baseline 732- See 'Total subscribers served' narrative above. | Baseline 10- See 'Total subscribers served' narrative above. | N/A | 24 | 0 | 0 | 0 | 10 | Baseline 24- No Variance. | Baseline 15-We currently serve ten business subscribers with existing BTOP Funded (In Kind) network services. None have prescribed for improved services at this time, however have the capability to up grade. Once service is 'turned up', these entities will have the capability of redundancy that our Network will provide. | Baseline 5 -Service has not yet been turned up as equipment necessary for BTOP funded service has not been installed. As services are turned up in 2012, additional entities will have the option of signing up for service. | Baseline 10- See 'Subscribers receiving new access' narrative above. | 10-10 Meg Port | None at this time in the project life cycle. | FALSE | N/A | Construction will continue at a rapid pace as long as the weather allows. Equipment specifications and procurement activities will continue for placement next year. Community Outreach efforts keeping the stakeholders and interested parties informed will continue in preparation for agreements with potential wholesalers being signed. The District has an aggressive strategy to overcome the schedule lapses due to the EA and the challenges of materials availability and weather windows. Pend Oreille PUD has nearly completed in advance of schedule the engineering for the underground project. The District intends on letting the Underground Construction Contract this quarter with commitments to complete in Q4 2012. The contractor will be required to provide the crews and necessary workforce to facilitate an aggressive deployment schedule, but we have every confidence that this can occur. In addition, the design strategy includes placing much if not all service duct such that the fiber can be installed in winter weather conditions, specifically allowing underground work in the Q1 2013 to complete the project. The following are projections for Key Metrics to reach by the end of the quarter (cumulative): New Network Miles Deployed-300 Total CAI Subscribers Served-0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers-2 | Public Utility District of Pend Oreille County | No specific or identifiable issues stand out with fiber orders being shipped as ordered. Assistance if needed is always appreciated. | Weather is more than likely going to be a variable in whether our plan comes together as outlined in the above projections. Late winter or Spring snowfalls may limit build capability in some areas and force a slow down for periods of time. Technical assistance at this time is not anticipated, however will be appreciated if needed.
NT10BIX5570059 | 2012 | Q1 | Q1 - 2012 | Pend Oreille PUD was able to continue to install aerial fiber in very favorable conditions as the first quarter of 2012 has been unseasonably warm. Bid preparation for the underground build has taken place with bid award at the end of the quarter. Construction slated to commence beginning of next quarter. Retail Service Provider's are in the final stages of having signed contracts and will begin signing up customers once equipment is deployed and connected. Community Outreach efforts continue to keep stakeholders excited and apprised of the project status. | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 1 | 160-350 Ninety miles of fiber were installed over the last quarter bringing the gap in baseline to one hundred miles. Underground construction will begin in the next quarter with aerial continuing at a fast pace as all necessary resources are being utilized. | N/A | N/A | N/A | 160-350 See 'new network miles deployed' narrative above. | This metric, although in our original application, is no longer a planned part of the network design. | Although originally called out for in the project, it is no longer included as part of the construction and network. | No Variance. | 0 | 3 | 0 | N/A | None at this time of the project. | N/A | 0 | 0 | 0 | 0 | Baseline 4-Currently in the process of having signed agreements by the second quarter of 2012. Public hearings have been held to discuss rates, terms and agreements. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | No Variance. | Baseline 24- See narrative above for 'total subscribers served'. | N/A | 1880 | 0 | 0 | 0 | 0 | LQ 1400-BL1804 Exceeding Baseline. | 0-990 This metric will lag Baseline projections through the remainder of the project. | 0-980 See 'total subscribers served' narrative above. | 0-10 See 'total subscribers served' narrative above. | N/A | 24 | 0 | 0 | 0 | 10 | Baseline 84- Although currently behind projections in this metric, we will be doing the underground portion of the project over the next several months and attaining the Baseline projections by the end of 2012. | Baseline 21-Pend Oreille PUD currently serves ten businesses with existing BTOP Funded (In Kind) network services. None have subscribed for improved services at this time, however have the capability to upgrade. Once service is 'turned up', these entities will have the capability of redundancy that our Network will provide. | Baseline 11- Service has not yet been turned up as equipment necessary for BTOP funded service has not been installed. As services are turned up in 2012, additional entities will have the option of signing up for new service. | Baseline 10- See 'Subscribers receiving new access' narrative above. | 10-10 Meg port. | None at this phase of the project life cycle. | FALSE | N/A | Underground fiber construction is a major event targeted for April as we enter the second quarter of 2012. Plans are under way to hold community events such as our 'Get Hooked Up' events in April where citizens can sign off on approval to bring Fiber up to the premise. Additional Community Outreach events will take place as we gear up to begin connection equipment, finalizing wholesale agreements, and connecting customers in future quarters. The following are key metrics planned for completion at the end of quarter two: New Network Miles Deployed-100? Total CAI Subscribers Served-0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers-3 | Public Utility District of Pend Oreille County | No specific or identifiable issues stand out with fiber orders being shipped as ordered. | Nothing is identifiable at this point in time, but will be communicated if it becomes necessary.
NT10BIX5570059 | 2012 | Q2 | Q2 - 2012 | The underground construction phase of the project kicked off this quarter as well as continued work on the aerial build and make ready work. Electronics specifications were reviewed, vendors selected, and orders are in process for delivery in the third and fourth quarters of 2012. Efforts to gain approval of all residents in the serving area for fiber connection continues to take place with our 'Get Connected' campaign as we continually reach out to the Community with information. | 370 | 0 | 0 | 0 | 370 | 0 | 0 | 1 | LQ250-BL450 One hundred twenty miles of fiber were placed in the second quarter of 2012, with some underground miles being deployed. It is anticipated that additional mileage for the next quarter will be substantial as we close in on the completion of the aerial build and continue the underground portion. | N/A | N/A | N/A | 250-450 See 'new network miles deployed' narrative above. | This metric, although originally planned for in the project, is no longer part of the design and has been removed from the project. | Although origianally identified in the application as being part of the project, towers have been removed from the network and the design. | No Variance. | 2 | 1 | 20 | Internet Xpress, Inc. Pend Oreille Valley Networks, Inc. | The Wholesale services being provided include residential and business class broadband, point-to-point ethernet transport and virtual networks. Pricing plans have not yet been established and will be furnished upon completion and approval. | N/A | 2 | 0 | 0 | 0 | BL 4-Two agreements have been signed with additional agreements being negotiated. The goal is to add additional wholesale providers to the existing list as we progress through the remainder of the project. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24-Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | No Variance. | Baseline 24- See 'total subscribers served' narrative above. | N/A | 3364 | 0 | 0 | 0 | 0 | LQ 1880-Baseline 2705-Exceeding Baseline. | 0-1116 This metric will continue to lag until the project is completed based on an aggressive Baseline Projection and a later than anticipated construction start date. | 0-1106 See 'total subscribers served' narrative above. | 0-10 See 'total subscribers served' narrative above. | N/A | 24 | 0 | 0 | 0 | 10 | Baseline 154-Although currently behind projections in this metric, the underground phase of the project is in the initial phase of construction. This section of the build is primarily in the populated and business section of the serving area. | Baseline 26-Pend Oreille PUD currently serves ten business with existing BTOP Funded (In Kind) network services. None have subscribed for improved services at this time, however have the capability to upgrade. Once services are turned up, these entities will have the capability of redundancy that our Network will provide. | Baseline 16-Service has not yet been turned up as equipment and construction to these entities has not been connected. As services are turned up and the ability to subscribe is available, this metric will show progress towards the projections. It is estimated service will be available in Q4 2012. | Baseline 10-See 'Subscribers receiving new access' narrative above. | 10-10 Meg Port. | None at this time. | FALSE | N/A | Continued underground construction is planned for the next and continuous quarters as we approach the final three quarters of the project. Community excitement and Wholesale Provider interaction will be integral pieces as we near completion of the project and plan for Equipment integration and eventual service turn ups. Continued efforts to reach out to our community members in receiving 'approvals' for connection to premises is taking place during the next quarter. This process will continue on throughout the remainder of the project time frame in hopes of achieving 100% approval for this connection. New Network Miles Deployed-110 Total CAI Subscribers Served-0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers-1 | Public Utility District of Pend Oreille County | None at this stage in the process. | None anticipated or expected.
NT10BIX5570059 | 2012 | Q3 | Q3 - 2012 | The third quarter of 2012 was primarily focused on continued construction of underground facilities with the majority of overhead construction complete. Finalization of wholesale providers continues to evolve with two additional contracts being signed in the quarter. Community Outreach and project updates to the public via media outlets and Social Media avenues continue as we keep our Communities excited about the project. | 455 | 0 | 0 | 0 | 455 | 0 | 0 | 1 | LQ-370 BL 490 This gap continues to tighten as we approach the final phase of the project and the final quarters of construction. This metric has been revised to reflect a more accurate measurement and will be at 585 miles when completed. This metric will be attained at the end of Q1 2013. | N/A | N/A | N/A | 370-490 See 'New Network Miles Deployed' narrative above. | This metric, although originally planned as part of the project, is no longer part of the design and has been removed from the project. | Although originally identified in the application as being part of the project, towers have been removed from the network and design. | No Variance. | 4 | 0 | 20 | Internet Xpress Pend Oreille Valley Networks, Inc. iFiber 180 Networks | The Wholesale services being provided include residential and business class broadband, point-to-point ethernet transport and virtual networks. Pricing plans are in the process of being established and will be furnished upon completion and approval. | N/A | 4 | 0 | 0 | 0 | LQ 2-BL 5- Four agreements have been signed with possibly more agreements being negotiated as we progress with the project. The goal is to add additional wholesale providers to the existing list throughout the remainder of the project. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | No Variance. | Baseline 24- See 'Total Subscribers served' narrative above. | N/A | 3480 | 0 | 0 | 0 | 0 | LQ-3364 BL-3469 Exceeding Baseline. | 0-1242 This metric will continue to lag until the project is completed based on an aggressive Baseline Projection coupled with a later than anticipated construction start date. | 0-1232 See 'total subscribers served' narrative above. | 0-10 See 'total subscribers served' narrative above. | N/A | 24 | 0 | 0 | 0 | 10 | Baseline 224-Although currently behind projections in this metric, the underground phase of the project is in the initial phase of construction. This section of the build is primarily in the populated and business section of the serving area. | Baseline 32-Pend Oreille PUD currently serves ten business with existing BTOP Funded (In Kind) network services. None have subscribed for improved services at this time, however have the capability to upgrade. Once services are turned up, these entities will have the capability of redundancy that our Network will provide. | Baseline 22-Service has not yet been turned up as equipment and construction to these entities has not been connected. As services are turned up and the ability to subscribe is available, this metric will show progress towards the projections. It is estimated service will be available in Q4 2012. | Baseline 10-See 'Subscribers receiving new access' narrative above. | 10-10 Meg Port. | None at this time. | FALSE | N/A | Underground construction will continue to be the focus of the project into the next and following quarter. Additional crews are being added to insure on on-time completion of the project. Aerial lateral hook ups will be made as premises will be connected and services turned up as part of the final phase of the project. New network miles deployed-120 Total CAI Subscribers Served-0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers-0 | Public Utility District of Pend Oreille County | None at this time. | Weather may be the only issue that may effect progress against the current projections for network build miles.
NT10BIX5570059 | 2012 | Q4 | Q4 - 2012 | Significant progress has been made in the underground phase of the network build during the course of the quarter. Equipment procurement has been very active as the majority has now been received and installation will proceed. Retail Service Providers are gearing up for the coming months as the network build, installation, and testing will all be completed. Community Outreach efforts continue as the project nears the final phase. | 540 | 0 | 0 | 0 | 540 | 0 | 0 | 1 | LQ-455 BL-510 Exceeding Baseline. (Route modification approved in December 2012.) | N/A | N/A | N/A | LQ-455 BL-510 Exceeding Baseline. | This metric, although originally planned as part of the project, is no longer part of the design and has been removed from the project. | Although originally identified in the application as being part of the project, towers have been removed from the network and design. | No Variance. | 4 | 1 | 20 | Internet Xpress Pend Oreille Valley Networks, Inc. iFiber 180 Networks | The Wholesale services being offered include residential and business class broadband, point-to-point ethernet transport and virtual networks. Pricing plans are in the process of being established and will be furnished upon completion and approval. | N/A | 4 | 0 | 0 | 0 | This falls short of the 6 (six) originally planned in the Baseline projections. More may be added as the nearly completed project generates more interest. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | BL-0 No Variance. | Baseline 24- See 'Total Subscribers served' narrative above. | N/A | 4584 | 0 | 0 | 0 | 0 | LQ-3480 BL-4233 Exceeding Baseline. | BL-1368 Subscriptions to services has not started as early as originally planned since construction is still in process and equipment is still in the process of being brought online. | 1358 See 'total subscribers served' narrative above. | 0-10 See 'total subscribers served' narrative above. | N/A | 24 | 0 | 0 | 0 | 10 | Baseline 294- Although currently behind projections in this metric, the underground phase of the project is nearing the midway point in construction. This section of the build is primarily in the populated areas and business section of the serving area. | Baseline 38- Pend Oreille PUD currently serves ten businesses with existing BTOP Funded (In Kind) network services. | Baseline 28- Service has not yet been turned up as final equipment installation and network build is in process. | Baseline 10- See 'subscribers receiving new access' narrative above. | 10-10 Meg Port. | N/A | FALSE | N/A | Construction and testing will be major focuses next quarter as we push to complete as much of the underground build as weather allows. Final equipment installation is anticipated during the quarter. Fiber will be placed into duct already buried to expedite the network build process. Network Miles Deployed-20 additional to bring this to Cumulative of 560. New CAI's Connected-0 Number of Broadband Wholesalers/Last Mile Providers- 1 additional to bring this to Cumulative of 5. | Public Utility District of Pend Oreille County | Weather has slowed progress particularly during this underground phase of construction. Technical assistance as always is appreciated when needed. | Weather can always be a factor in the Northwest as heavy amounts of snow can hamper construction progress, especially during the underground phase of construction. Another significant variable beyond project control that can cause substantially hampered production is road restrictions implemented by State and County jurisdictions.
NT10BIX5570059 | 2013 | Q1 | Q1 - 2013 | Public Utility District of Pend Oreille was slowed somewhat by weather over the first quarter of 2013, with construction limited to fiber installation in existing ducts, overhead lateral drops, and minimal other small segments needing completion. One additional Wholesale Provider was added during the quarter bringing the total to five. The District continues to 'publicize' via social and other media outlets, the Broadband Story and the benefits to our area. | 570 | 0 | 0 | 0 | 570 | 0 | 0 | 1 | LQ-540 Exceeding Baseline. | N/A | N/A | N/A | LQ-540 Exceeding Baseline. | This metric, although originally planned as part of the project, is no longer part of the design and has been removed from the project. | Although originally identified in the application as being part of the project, towers have been removed from the network and design. | No Variance. | 5 | 1 | 20 | Internet Xpress Pend Oreille Valley Networks, Inc. iFiber 180 Networks Concept Communication Corporation | The Wholesale services being offered include residential and business class broadband, point-to-point ethernet transport and virtual networks. Pricing plans are in the process of being established and will be furnished upon completion and approval. | N/A | 5 | 0 | 0 | 0 | This falls short of the 6 (six) originally planned in the Baseline projections. More may be added as the nearly completed project generates more interest. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | BL-0 No Variance. | Baseline 24- See 'Total Subscribers served' narrative above. | N/A | 4970 | 0 | 0 | 0 | 0 | LQ-4584 BL-4997 Exceeding Baseline. | BL-1494 Subscriptions to services has not started as early as originally planned since construction is still in process and equipment is still in the process of being brought online. | BL-1484 See 'total subscribers served' narrative above. | 0-10 See 'total subscribers served' narrative above. | N/A | 200 | 0 | 0 | 0 | 10 | Baseline 364- Although currently behind projections in this metric, the underground phase of the project is nearing the midway point in construction. This section of the build is primarily in the populated areas and business section of the serving area. | Baseline 44- Pend Oreille PUD currently serves ten businesses with existing BTOP Funded (In Kind) network services. | Baseline 34- Service has not yet been turned up as final equipment installation and network build is in process. | Baseline 10- See 'subscribers receiving new access' narrative above. | 10-100 Meg Port. | None at this time. | FALSE | N/A | The District plans to continue with the remaining underground portion of construction for the Network Miles Deployed-30 additional underground miles to bring this to Cumulative of 600. New CAI's Connected-0 Number of Broadband Wholesalers/Last Mile Providers- 5 | Public Utility District of Pend Oreille County | None at this time. | None at this time.
NT10BIX5570059 | 2013 | Q2 | Q2 - 2013 | Pend Oreille PUD worked diligently with underground construction to put remaining duct work in place and order fiber for the remaining segments. Lateral connections were constructed and subscribers were turned up for service during this past quarter to residential customers. | 573 | 0 | 0 | 0 | 573 | 0 | 0 | 1 | LQ-570 BL-526 With minimal mileage added to this metric for the quarter, we are still exceeding Baseline. Additional laterals have yet to be built bringing the total Network Miles Deployed to approximately 610. | N/A | N/A | N/A | LQ-570 BL- 526 See 'New network miles deployed' narrative above. | This metric, although originally planned as part of the project, is no longer part of the design and has been removed from the project. | Although originally identified in the application as being part of the project, towers have been removed from the network and design. | No Variance. | 5 | 0 | 20 | Internet Xpress Pend Oreille Valley Networks, Inc. iFiber 180 Networks Concept Communication Corporation | The Wholesale services being offered include residential and business class broadband, point-to-point ethernet transport, and virtual networks. Pricing plans are finalized and rates are attached. | N/A | 5 | 0 | 0 | 0 | This metric falls short of the 6 (six) originally planned in the Baseline projections. Additional Providers may be added in the future. | N/A | N/A | N/A | 0 | 0 | 0 | 4 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | BL-0 Meeting Baseline. | Baseline 24- See 'Total Subscribers Served' narrative above. | 0-10 MBPS, 0-25 MBPS, 0-50 MBPS, | 4997 | 120 | 120 | 0 | 2 | LQ- 4970 BL- 4997 Meeting Baseline projections. | LQ-0 BL-1494 Subscription to services began in this month as delays in construction, network design, and environmental approvals all lagged initial plans. | LQ-0 BL-1484 See 'Total Subscribers Served'' narrative above. | LQ-0 BL-10 | 0-10 Meg, 120-100Meg | 340 | 0 | 0 | 0 | 10 | LQ- 200 BL-364 | LQ-0 BL-44 | LQ-0 BL-34 | LQ-0 BL-10 | 10-100 Meg Port | N/A | FALSE | N/A | Pend Oreille Public Utility District intends to complete all of the remaining construction that primarily consists of lateral service drops to subscribers. Closeout activities will begin with required paperwork and all necessary documentation and support material being reviewed for compliance. Retail Service Providers will continue to sign up customers for Broadband Service throughout the service area. Number of miles completed by end of Quarter: Overhead-388 Underground-215 Number of CAI's connected by end of Quarter: Improved-14 New-0 | Public Utility District of Pend Oreille County | With the No Cost Extension previously approved and the Revised Budget approved this last quarter, it appears the project will exceed the original budgeted amount. Pend Oreille Public Utility District is committed to completing the project with the use of our funds and on time as prescribed in the No Cost Extension request submitted earlier. | None that have not already been addressed.
NT10BIX5570059 | 2013 | Q3 | Q3 - 2013 | Pend Oreille Public Utility District continued to build the laterals and drops to customer premises during the last quarter. Work began on the closeout documents and paperwork for completion of the project. Additionally, accomplishments throughout the course of the project include but are not limited to: The deployment of close to 600 miles of Fiber Optic Cables carrying Broadband Service to areas unserved or underserved throughout the Public Funded Service Area in Pend Oreille County located in Northeast Washington State. New fiber optic service and connections were completed to over 3300 premises, of which 970 have signed up to receive service, and 275 are already receiving service. Based upon these numbers and the positive community response Pend Oreille PUD has received, the project is recognized to be a great benefit to this previously unserved rural area. | 585 | 0 | 0 | 0 | 585 | 0 | 0 | 1 | This is the final metric for this category for the project. | N/A | N/A | N/A | This is the final metric for this category for the project. | This metric, although originally planned as part of the project, is no longer part of the design and has been removed from the project. | Although originally identified in the application as being part of the project, towers have been removed from the network and design. | No Variance. | 5 | 0 | 20 | Internet Xpress Pend Oreille Valley Networks, Inc. iFiber 180 Networks Concept Communication Corporation | The Wholesale services being offered include residential and business class broadband, point-to-point ethernet transport, and virtual networks and have been provided in the attached document. | N/A | 5 | 0 | 0 | 0 | This metric falls short of the 6 (six) originally planned in the Baseline projections. Additional Providers may be added in the future. | N/A | N/A | N/A | 14 | 0 | 14 | 4 | Baseline 24- Although originally included in our Baseline, since improvement has not been made to the original list of 24 CAI's, they will not be counted for reporting purposes. | BL-0 Meeting Baseline. | Baseline-24- See 'Total Subscribers' served narrative above. | 13-10MBPS, 0-50 MBPS 1-100 MBPS 0-1000 MBPS | 5000 | 275 | 275 | 0 | 2 | BL-4997 | BL-1494 | BL-1484 See 'Total Subscribers Served' narrative above. | BL-10 | 0-10 Meg, 275-100 Meg | 360 | 0 | 0 | 0 | 10 | BL-364 | BL-44 | BL-34 | BL-10 | 10-100 Meg Port | N/A | FALSE | N/A | The project was substantially complete as of September 30, 2013. Closeout activities remain and final reporting for the project are both slated to end in the last quarter of 2013. | Public Utility District of Pend Oreille County | Completion of connection to all subscribers is still in progress. | Successful completion and acceptance of the closeout documents would be the only potential for delay that we could see. An extension for closeout may be a possibility as we proceed through the quarter.
NT10BIX5570060 | 2010 | Q3 | Q3 - 2010 | During the 3rd quarter, Pine Telephone Companyâ€™s (PTC) primary work schedule was to complete and submit the Environmental Assessment (EA) so as to receive the Finding Of No Significant Impact Report (FONSI). The EA has been submitted and its approval is now pending review. All land procurements for tower placements have been completed or are under contract. Finally, all necessary construction permits and approvals have been obtained. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | - | - | - | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | N/A | FALSE | N/A | Once Pine Telephone Company (PTC) receives its FONSI, the major activity for the 4th quarter will be for PTC to start the procurement of the various towers, buildings and electronics and start construction on the buildings and individual tower sites, including the installation of electronics for each tower. | Pine Telephone Company, Inc. | Pine Telephone Company is waiting on the approval of its Environmental Assessment (EA) and procurement of the FONSI. | Pine is waiting for the approval of its Environmental Assessment (EA) and the release of the FONSI.
NT10BIX5570060 | 2010 | Q4 | Q4 - 2010 | At the end of the 4th quarter, Pine received the Findings of No Significant Impact (FONSI) on its Environmental Assessment. Is currently closing on properties and towers. Has posted three (3) Request For Proposals for construction, towers & equipment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | 0 | 0 | 0 | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | 0 | 0 | 0 | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | N/A | FALSE | N/A | Now that Pine Telephone Company (PTC) has received its Environmental Assessment approval and its Finding Of No Significant Impact, the major activity for the next quarter will be for PTC to start the procurement of the various towers, buildings and electronics and start construction on the buildings and individual tower sites, including the installation of electronics for each tower. | Pine Telephone Company, Inc. | Pine Telephone Company only received approval of its Environmental Assessment (EA) and the procurement of the Findings of No Significant Impact (FONSI) at the end of the 4th Quarter (12/16/2010). | Inclement weather
NT10BIX5570060 | 2011 | Q1 | Q1 - 2011 | Pine Telephone Company accepted bids and has signed contracts for generators, tower site base construction for 12 sites, towers for 2 sites and tower erection for 2 sites. The McGee Creek site and Sobol site have towers standing. The Sobol site is a POI. Pine Telephone Company has also signed a contract for the Wireless access equipment which will be shipped in Q2 of 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The FONSI, RFP and contracting process has taken longer than anticipated. Also the process from receiving the FONSI to closing the land for construction has taken longer than anticipated. This will not be a problem going forward as 26 of the 32 sites have passed this phase and the remaining 6 will complete it in Q2 of 2011. Sites are now being completed for the wireless links. Pine expects to be back on schedule by end of Q2 or early Q3 and move ahead of schedule by Q4 of 2011. | The FONSI, RFP and contracting process has taken longer than anticipated. Also the process from receiving the FONSI to closing the land for construction has taken longer than anticipated. This will not be a problem going forward as 26 of the 32 sites have passed this phase and the remaining 6 will complete it in Q2 of 2011. Sites are now being completed and Pine expects to be back on schedule by end of Q2 and first of Q3 and move ahead of schedule by end Q3 of 2011. | The FONSI, RFP and contracting process has taken longer than anticipated. Sites not being constructed has delayed this milestone. Pine will have 2 interconnection points by end of Q2 2011. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The delayed start of construction caused by the FONSI, equipment change request and longer than expected RFP and contracting process will delay this milestone significantly. But as with the other missed milestones, we will catch up quickly because many sites will be turned up at once. Pine does not expect to be live to customers until end of Q2 or first of Q3 2011 but Pine will be at or ahead of schedule with sites online by the end of Q3. | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | 0 | 0 | 0 | The delayed start of construction caused by the FONSI, equipment change request and longer than expected RFP and contracting process will delay this milestone significantly. But as with the other missed milestones we will catch up quickly because many sites will be turned up at once. Pine does not expect to be live to customers until end of Q2 or first of Q3 2011 but Pine will be at or ahead of schedule with sites online by the end of Q3. | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | 0 | 0 | 0 | 0 | 0 | The delayed start of construction caused by the FONSI, equipment change request and longer than expected RFP and contracting process will delay this milestone significantly. But as with the other missed milestones we will catch up quickly because many sites will be turned up at once. Pine does not expect to be live to customers until end of Q2 or first of Q3 2011 but Pine will be at or ahead of schedule with sites online by the end of Q3. | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | Project was significantly delayed while waiting for FONSI approval | N/A | FALSE | N/A | Pine Telephone Company will continue RFP and contracting for equipment and installation with the goal of being 80% complete by the end of the quarter. Base construction will begin on 18 sites and plan to have 8 to 10 towers standing by the end of the quarter. In the quarter Pine will add 1 full time position as well as over 3000 man hours to contractors. | Pine Telephone Company, Inc. | Pine Telephone Company is awaiting their equipment manufacturer change request to be approved. | Inclement weather.
NT10BIX5570060 | 2011 | Q2 | Q2 - 2011 | PTC has completed all RFPâ€™s necessary to provide service to customers. Land has closed on 28 of the 29 sites. Base construction has been completed on 20 of the 29 sites and towers have been erected on 8 of these sites. Initial shipment of prefabricated buildings have been received and equipment is being pre-installed in the buildings before deployment to site. | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | N/A | N/A | N/A | N/A | N/A | The FONSI, RFP and contracting process has taken longer than anticipated. Also the process from receiving the FONSI to closing the land for construction has taken longer than anticipated. This will not be a problem going forward as 26 of the 32 sites have passed this phase and the remaining 6 will complete in Q3 of 2011. Sites are now being completed for the wireless links. Pine expects to be back on schedule by end of Q3 and move ahead of schedule by Q4 of 2011. | The FONSI, RFP and contracting process has taken longer than anticipated. Also the process from receiving the FONSI to closing the land for construction has taken longer than anticipated. This will not be a problem going forward as 26 of the 32 sites have passed this phase and the remaining 6 will complete in Q3 of 2011. Sites are now being completed for the wireless links. Pine expects to be back on schedule by end of Q3 and move ahead of schedule by Q4 of 2011. | The FONSI, RFP and contracting process has taken longer than anticipated. Sites not being constructed have delayed this milestone. Pine expects to have 2 interconnection points by end of Q3 2011. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine does not expect to be live to customers until the end of Q3 2011. But Pine does expect to be at or ahead of schedule with sites online by the end of Q4 2011. | N/A | FALSE | N/A | Pine Telephone Company plans to have base construction 95% completed with 18 towers erected. Pine Telephone also plans to install and test microwave links and broadband access equipment. | Pine Telephone Company, Inc. | The equipment deployment was slightly delayed because of vendor shortage of power systems. The problem has been resolved and all power systems will be on site by the end of July. | None forecasted.
NT10BIX5570060 | 2011 | Q3 | Q3 - 2011 | Pine Telephone Company (PTC) has completed base construction on 27 of the 29 new towers and erected 13 of the 29 towers. Prefabricated buildings have been set at 27 sites and all sites with towers erected now have fences. PTC has installed the Radio Network Controller (RNC) and broadband access equipment on 4 towers and turned up 1 microwave link. Network testing has begun and broadband access is being tested. | 0 | 0 | 0 | 0 | 0 | 1 | 13 | 1 | N/A | N/A | N/A | N/A | N/A | Pine has added a new wireless link. The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but with 31 of the 32 tower sites having passed the RFP and procurement phase, Pine plans to be back on schedule in Q1 of 2012. | Pine Telephone plans on having 2 interconnection points up by the end of Q4 of 2011. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | The delay of construction caused by the FONSI, the equipment change request and the longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q4 of 2011. | N/A | FALSE | N/A | Pine Telephone will continue with its network build-out and plans to be live to customers in Q4 of 2011. Additionally, Pine plans on having 6 new towers and 2 Community Anchor Institution (CAI) subscribers connected and served. Finally, Pine will also be negotiating with broadband wholesalers or last mile providers regarding signed agreements. | Pine Telephone Company, Inc. | The extreme heat that the State of Oklahoma experienced in July and August was a major factor for tower crews. It has also been difficult to get a second tower crew up and running at a reasonable rate. | None forcasted
NT10BIX5570060 | 2011 | Q4 | Q4 - 2011 | Pine Telephone Company (PTC) has completed base construction on 28 of the 29 new towers and erected 18 of the 29 towers. Prefabricated buildings have been set at 28 sites and all sites with towers erected now have fences. PTC has installed the RNC and broadband access equipment on 14 towers and turned up 5 microwave links. Pine is continuing its network testing and has deployed broadband to 1 Community Anchor Institution and also with friendly users. | 34 | 0 | 0 | 0 | 0 | 5 | 18 | 2 | Pine has added 34 new miles of Microwave link. | N/A | N/A | N/A | N/A | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but with 31 of the 32 tower sites having passed the RFP and procurement phase, Pine plans to be back on schedule in Q1 of 2012. | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 1 | 0 | 1 | 0 | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | The RFP and contracting process has taken longer than anticipated, but over 90% of the equipment is now under contract and being delivered. Actual procurement will lag behind baseline projected procurement, but Pine plans to be back on schedule in Q1 of 2012. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | 0 | 0 | 0 | 0 | 0 | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | The delay of construction caused by the FONSI, the equipment change request and longer than expected RFP and contracting process has delayed this milestone significantly. However, Pine will be making up for lost time as many sites will be turned up at once. Pine Telephone expects to be live to customers in Q1 of 2012. | N/A | FALSE | N/A | Pine Telephone will continue the excellent progress of its network build-out and plans to be live to customers in Q1 of 2012. Pine plans on having a total of 125.13 new network miles deployed and serve a total of 10 new CAI (Community Anchor Institutions) subscribers in Q1 2012. | Pine Telephone Company, Inc. | Rain has been a factor in the State of Oklahoma and has slowed the erection of new towers and has slowed the utility companies getting power to the sites. | The challenge for Pine continues to be the Oklahoma weather.
NT10BIX5570060 | 2012 | Q1 | Q1 - 2012 | Pine Telephone Company (PTC) has completed base construction on 28 of the 29 new towers and erected 26 of the 29 towers. Pre-fabricated buildings have been set at 28 sites and all sites with towers erected now have fences. PTC has installed the Radio Network Controller (RNC) and broadband access equipment on 29 towers and turned up 25 microwave links. PTC is providing broadband Internet service to customers on 25 of the 32 sites. We are continuing our network testing and have deployed broadband to 1 Community Anchor Institution and also with friendly users. PTC started marketing the broadband service to end users at the end of the last quarter. | 192 | 0 | 0 | 0 | 0 | 25 | 26 | 3 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 1 | 0 | 1 | 1 | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter.â€ | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 2nd quarter. | 5861 | 12 | 9 | 3 | 12 | - | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter. | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 2nd quarter. | 57 | 0 | 0 | 0 | 0 | - | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter. | Marketing of broadband service did not begin until the very end of the quarter. | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 2nd quarter. | N/A | FALSE | N/A | Pine Telephone Company (PTC) started marketing to customers at the very end of the last quarter and Pine plans to rapidly grow its customer base during Q2 of 2012. Pine also plans to complete construction of the three remaining towers, install and then test the equipment of the 7 remaining towers. PTC plans to add 10 new CAIs and deploy 48 new network miles. PTC does not anticipate adding any broadband wholesaler/last mile provider agreements next quarter. | Pine Telephone Company, Inc. | Spring and Summer weather (tornadoes) in Oklahoma is unpredictable and may cause some delays. | Spring and Summer weather in Oklahoma (tornadoes) is unpredictable, and may cause delays.
NT10BIX5570060 | 2012 | Q2 | Q2 - 2012 | Pine Telephone Company (PTC) has completed base construction on 29 of the 29 new towers and has erected 29 of the 29 new towers. Prefabricated buildings have been set at 29 sites and fences have been installed at 27 of the 29 sites. PTC has installed broadband access equipment on 31 of 32 towers and is live to customers on 29 of 32 sites with testing going on at 2 sites. PTC continues to install generators for backup power and increasing microwave links for Ring protection of the network. PTC started offering service to residential customers and Community Anchor Institutions (CAI) last quarter. | 242 | 0 | 0 | 0 | 0 | 29 | 29 | 3 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 6 | 1 | 1 | Pine Telephone Company currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. | Pine Telephone Company currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. Marketing of broadband service did not begin until the very end of the previous quarter. | Marketing of broadband service did not begin until the very end of the previous quarter. | Pine Telephone Company currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 3rd quarter. | 6155 | 65 | 55 | 10 | 65 | - | Marketing of broadband service did not begin until the very end of the previous quarter. | Marketing of broadband service did not begin until the very end of the previous quarter. | Marketing of broadband service did not begin until the very end of the previous quarter. | Pine Telephone Company currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 3rd quarter. | 57 | 0 | 0 | 0 | 0 | - | Marketing of broadband service did not begin until the very end of the previous quarter. | Marketing of broadband service did not begin until the very end of the previous quarter. | Marketing of broadband service did not begin until the very end of the previous quarter. | Pine Telephone Company (PTC) currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. PTC plans to offer additional tiers in 3rd quarter. | N/A | FALSE | N/A | Pine Telephone Company (PTC) plans marketing push in Q3 and back to school specials to increase subscriber base. PTC plans to be live to customers on 32 broadband sites. PTC will also be installing 2 microwave links, 15 network miles for Ring protection and access to a new POI. PTC also plans to add 5 more Community Anchor Institutions (CAI) during the Quarter. PTC does not anticipate adding any broadband wholesaler/last mile provider agreements next Quarter. PTC plans to submit proposal to build additional broadband sites during Q3. | Pine Telephone Company, Inc. | Summer weather (tornadoes / extreme heat / severe storms) in Oklahoma caused some delays. Note: In the previous quarter, some building and structure related work orders were reported in the "Construction" category. In Q2 2012, those work orders have been re-categorized as "Land, structures, right-of-ways, appraisals, etc". | Oklahoma weather is unpredictable; Extreme heat, tornadoes & severe storms can cause delays.
NT10BIX5570060 | 2012 | Q3 | Q3 - 2012 | Pine Telephone Company (PTC) has completed base construction on 29 of the 29 new towers and has erected 29 of the 29 new towers. Prefabricated buildings have been set at 29 sites and fences have been installed on all 29 sites. PTC has installed broadband access equipment on 32 of 32 towers and is live to customers on 32 of 32 sites with testing going on at 2 sites. PTC continues to install generators for backup power and increasing microwave links for Ring protection of the network. PTC is offering service to residential customers and Community Anchor Institutions (CAI). | 257 | 0 | 0 | 0 | 0 | 31 | 29 | 3 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 6 | 1 | 1 | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. | - | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. | 6155 | 303 | 270 | 33 | 1 | - | - | - | - | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. 303 subscribers served. | 57 | 0 | 0 | 0 | 0 | - | PTC plans to start marketing in Q4 2012. | PTC plans to start marketing in Q4 2012. | PTC plans to start marketing in Q4 2012. | PTC currently offers only a single tier. The tier is 1MBPs down and 512KBPs up and all subscribers are on this tier. | N/A | FALSE | N/A | Pine Telephone Company (PTC) is now live on 32 of 32 sites. Pine plans to continue working on adding back-up power and will add new 2 links and deploy 17 miles for site redundancy. Pine will also add two (2) more high speed tiers to their customers and also add four (4) new Community Anchor Institutions (CAIs). Finally, Pine has submitted a request to add more towers with the remaining funds and once approved, PTC will commence construction. Pine does not plan to sign any broadband wholesaler/last mile provider agreements next quarter. | Pine Telephone Company, Inc. | Fall weather (early frost, rain, wind & storms) in Oklahoma may cause delays. | Oklahoma Fall weather is unpredictable. Frost, rain and high winds / storms may cause delays.
NT10BIX5570060 | 2012 | Q4 | Q4 - 2012 | Continuing on the excellent progress from last quarter, Pine Telephone Company (PTC) continues to install generators for backup power and increasing microwave links for Ring protection of the network. PTC is is now offering service to 383 residential customers and 19 Community Anchor Institutions (CAI). | 274 | 0 | 0 | 0 | 0 | 33 | 29 | 3 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 19 | 17 | 2 | 1 | PTC currently offers only a single tier to Community Anchor Institutions. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | PTC currently offers only a single tier to Community Anchor Institutions. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | - | PTC currently offers only a single tier to Community Anchor Institutions. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | 6155 | 383 | 345 | 38 | 3 | - | - | - | - | Pine Telephone Company (PTC) now offers 3 tiers for residential customers: 1. 1Mbps / 256Kbps - $25/Month 345 subscribers 2. 1.5Mbps / 384Kbps - $45/Month 25 subscribers 3. 3Mbps / 512Kbps - $60/Month 13 subscribers | 57 | 0 | 0 | 0 | 1 | - | PTC will start marketing in Q1 2013 | PTC will start marketing in Q1 2013 | PTC will start marketing in Q1 2013 | PTC currently offers only a single tier to business customers. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | N/A | FALSE | N/A | Pine Telephone Company (PTC) is now live on 32 of 32 sites. Pine plans to continue working on adding back-up power and will add 2 new links and deploy 8 miles for site redundancy. Pine will add one (1) new Community Anchor Institution (CAI) and will offer business service. Finally, Pine has submitted a request to add more towers with the remaining funds, and once approved, PTC will commence construction. Pine does not plan to sign any broadband wholesaler/last mile provider agreements next quarter. | Pine Telephone Company, Inc. | Winter weather (snow, ice, rain, wind & storms) in Oklahoma may cause delays. | Oklahoma winter weather is unpredictable. Ice, snow, rain and high winds / storms may cause delays.
NT10BIX5570060 | 2013 | Q1 | Q1 - 2013 | Pine Telephone Company (PTC) has continued its forward progress by now serving 487 customers, adding 8 more broadband sites, completing base construction on 4 sites and erecting 1 new tower as well. | 282 | 0 | 0 | 0 | 0 | 34 | 30 | 3 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 20 | 18 | 2 | 1 | PTC currently offers only a single tier. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | PTC currently offers only a single tier. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | - | PTC currently offers only a single tier. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | 6155 | 487 | 437 | 50 | 3 | - | - | - | - | Pine Telephone Company (PTC) now offers three (3) tiers for residential customers: 1. 1Mbps / 256Kbps - $25/Month 422 subscribers 2. 1.5Mbps / 384Kbps - $45/Month 35 subscribers 3. 3Mbps / 512Kbps - $60/Month 30 subscribers | 57 | 0 | 0 | 0 | 1 | - | PTC will start marketing in Q2 2013. | PTC will start marketing in Q2 2013. | PTC will start marketing in Q2 2013. | PTC currently offers only a single tier to business customers. The tier is 1Mbps down and 512Kbps up and all subscribers are on this tier. | N/A | FALSE | N/A | In Q2 of 2013, PTC will still be live on 32 sites, and will add 8 more approved sites. Pine will also add 2 more Community Anchor Institutions & 4 additional links. Project will be complete after these accomplishments. | Pine Telephone Company, Inc. | Inclement weather (storms, high winds & tornadoes) could cause delays for Pine Telephone. | Oklahoma weather is unpredictable. Storms, high winds and tornadoes could cause delays.
NT10BIX5570060 | 2013 | Q2 | Q2 - 2013 | Pine constructed 40 new broadband sites and new middle mile to each site. The original application proposed 32 new broadband sites but through cost savings Pine was able construct an additional 8. Through the BTOP award Pine is covering 22 Community Anchor Institutions which is 2 more than the proposed. Pine is now providing last mile internet access to residences and business in the application area. Through BTOP, emergency response teams have improved communications during emergencies because of broadband access and mobile radio coverage. Pine has donated space on the BTOP funded towers for the placement of emergency responder radio systems. | 344 | 0 | 0 | 0 | 0 | 42 | 37 | 6 | - | N/A | N/A | N/A | N/A | - | - | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 22 | 18 | 4 | 1 | - | - | - | Pine Telephone Company (PTC) currently only offers a single Tier. The Tier is 1Mbps down and 512Kbps up. All subscribers are on this Tier. | 6155 | 497 | 439 | 58 | 3 | - | - | - | - | Pine Telephone Company (PTC) now offers three (3) Tiers for Residential customers: 1. 1Mbps / 256Kbps @ $25/month 422 subscribers 2. 1.5Mbps / 384Kbps @ $45/month 41 subscribers 3. 3Mbps / 512Kbps @ $60/month 34 subscribers | 90 | 33 | 31 | 2 | 1 | - | - | - | - | Pine Telephone Company (PTC) currently only offers a single Tier for Business customers. The Tier is 1Mbps down and 512Kbps up. All subscribers are on this Tier. | N/A | FALSE | N/A | N/A - Project is completed. | Pine Telephone Company, Inc. | There were many obstacles - mainly the Oklahoma weather. However, Pine's determination and teamwork allowed us to complete the project on time. | N/A - Project is completed.
NT10BIX5570062 | 2010 | Q3 | Q3 - 2010 | Updated radio network coverage plan, planned competitive bidding process for backhaul and wholesale agreements, and construction agreements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | N/A Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Will complete network design, begin site preparation, network procurement, and network build. | DigitalBridge Communications Corp. | Two-month delay in hiring dedicated project manager and financial analyst (has not led to any variances from baseline plan to date.) | Winter weather can sometimes slow progress in southern Idaho.
NT10BIX5570062 | 2010 | Q4 | Q4 - 2010 | Updated radio network plan to improve coverage and cost effectiveness. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finalizing network plan, securing rights of way, and seeking construction permits and approvals. | DigitalBridge Communications Corp. | DBC strategic shifts slowed implementation during December, but project is still on track to be completed by 6/30/11. | Will be briefing NTIA on potential changes in organization structure and estimating final completion date.
NT10BIX5570062 | 2011 | Q1 | Q1 - 2011 | Identified potential purchaser of DBC Idaho assets. Purchaser may become sub-recipient and has commitment to complete project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Idaho assets by August 1. | DigitalBridge Communications Corp. | DBC Strategic caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is omitted to complete project. | BTOP assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570062 | 2011 | Q2 | Q2 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets and/or potential Award Subrecipient. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | N/A | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | 0 | 0 | 0 | 0 | 0 | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | Project on hold until asset sale completed | N/A | FALSE | N/A | Sale of DBC Assets by October 1, at which point project implementation will be re-started. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser may become sub-recipient and is committed to complete project. | BTOP Assistance will be required in establishing potential buyer as sub-recipient or transferee.
NT10BIX5570062 | 2011 | Q3 | Q3 - 2011 | Procurement activities completed relating to the selection of a purchaser of DigitalBridge Communications Corporation's Idaho Assets. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Sale of DBC Assets by November 15. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. Proposed purchaser is committed to complete project. | BTOP Assistance will be required in conducting due diligence on potential buyer as sub-recipient or transferee.
NT10BIX5570062 | 2011 | Q4 | Q4 - 2011 | Project on hold pending progress review. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project on hold pending progress review. | DigitalBridge Communications Corp. | Project on hold pending progress review. | N/A.
NT10BIX5570062 | 2012 | Q1 | Q1 - 2012 | Project has been terminated for convenience since buyer of DBC assets has decided not to take on BTOP Awards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | Project will not serve this type of subscriber | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project has been terminated for convenience. | DigitalBridge Communications Corp. | DBS Strategic shift caused need to sell Idaho assets. | Project has been terminated
NT10BIX5570065 | 2010 | Q3 | Q3 - 2010 | The July 1, 2010 to September 30, 2010 quarter project accomplishments for this project include: 1) The Environmental Review is underway - letters were mailed to the State review agencies; 2) Set up weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 3) Participated in a desk review with Program Officer; 4) Submitted an Environmental Assessment extention request; 5) Notified National Telecommunications and Information Administration of a project modification soon to be submitted to Program Officer; 6) Advertised a Request for Proposal for a project engineer to prepare the Environmental Assessment, and to assist with performing other construction activities associated with the grant. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No variance | No variance | No variance | 0 | 0 | 0 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | N/A | Buggs Island Telephone Cooperative plans to have 60% of the environmental assessment complete by the end of next quarter. Additionally, the construction permitting will begin to be obtained for each of the tower locations, and this will be 25% complete by the end of next quarter. Finally, the equipment procurement will be 80% complete by the end of next quarter. | Buggs Island Telephone Cooperative | Buggs Island Telephone Cooperative has submitted to National Telecommunications and Information Administration a request to change technologies and is waiting for a response. Buggs Island Telephone Cooperative also submitted a request to National Telecommunications and Information Administration for an extension for the completion of the environmental assessment. | Buggs Island Telephone Cooperative anticipates delays in receiving comments from state agencies related to the environmental assessment, which possibly could delay the percentage complete for this quarter. Additionally, Buggs Island Telephone Cooperative had not yet received approval from National Telecommunications and Information Administration for the project modification request.
NT10BIX5570065 | 2010 | Q4 | Q4 - 2010 | The October 1, 2010 to December 31, 2010 quarter project accomplishments for this project include: 1) The Environmental Reveiw is progressing; 2) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 3) Received notification from National Telecommunications and Information Administration that the project modification submitted by Buggs Island Telephone Cooperative had been denied, therefore Buggs Island Telephone Cooperative will move forward with the original WiMax technology 4) Hired a project engineer to prepare the Environmental Assessment, and to assist with performing other construction activities associated with the grant through Buggs Island Telephone Cooperative's procurement process 5) Submitted a Request for Proposal to select a vendor to purchase the equipment needed for the project. The deadline for the request for proposal responses was December 23, 2010. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No Variance | No Variance | No Variance | 0 | 0 | 0 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | N/A | Buggs Island Telephone Cooperative plans to have 100% of the environmental assessment complete by the end of next quarter. Additionally, the construction and permitting will continue for each of the tower locations. Equipment will be ordered for the core network and base stations that will go on the first six tower sites. | Buggs Island Telephone Cooperative | Buggs Island Telephone Cooperative submitted to National Telecommunications and Information Administration a request to change technologies and was notified by the National Telecommunications and Information Administration that the request was denied. Buggs Island Telephone Cooperative is now moving forward with the original WiMax technology selected for this project. Buggs Island Telephone Cooperative also submitted a request to National Telecommunications and Information Administration for an extension for the completion of the environmental assessment and has been given verbal approval, but is awaiting written approval from the National Telecommunications and Information Administration. | Buggs Island Telephone Cooperative anticipates delays in receiving comments from state agencies related to the environmental assessment.
NT10BIX5570065 | 2011 | Q1 | Q1 - 2011 | The January 1, 2011 to March 31, 2011 quarter project accomplishments completed during this quarter include 1) The Environmental Assessment draft was submitted to the National Telecommunications and Information Administration; 2) Buggs Island Telephone Cooperative received questions and comments back on the Environmental Assessment draft from the National Telecommunications and Information Administration and is working to answer the additional questions; 3) The biweekly calls between Buggs Island Telephone Cooperative and the National Telecommunication and Information Administration are continuing; 4) Buggs island Telephone Cooperative submitted a Request for Proposal to select a vendor to purchase a Brocade 10 gigabit Core Ring for the core network equipment and have received a response back from one vendor; 5) Buggs Island Telephone Cooperative has begun the process of negotiating tower leases; 6) Buggs Island Telephone Cooperative submitted a Pre-Environmental Assessment Six Month Expenditure Plan to the National telecommunications and Information Administration, which was approved; 7) Buggs Island Telephone Cooperative made the first draw down from the grant funds per the Pre-Environmental Assessment Expenditure Plan to pay for grant administration, project management and engineering services provided to-date; 8) Buggs Island Telephone Cooperative selected Airspan as the primary vendor for the WiMax Equipment to be used for the project and contract negotiations have been | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No variance | No variance | No variance | 0 | 0 | 0 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | The significant project accomplishments planned for completion during the next quarter include 1) ordering and installing the transport network; 2) completing the Environmental Assessment and receiving a Finding of No Significant Impact; 3) executing the contract with Airspan, the WiMax equipment vendor procured for this project; 4) placing the order for the WiMax equipment with Airspan; 5) finalizing the tower negotiations that have been started; 6) finalizing the network design by having the detailed coverage maps completed; 7) beginning site preparation for the first sites to be deployed. | Buggs Island Telephone Cooperative | The contract between Airspan, the WiMax vendor procured for this project, and Buggs Island Telephone Cooperative has been negotiated, and it is awaiting execution by the Buggs Island Telephone Cooperative Board of Directors. | Buggs Island Telephone Cooperative does not anticipate any issues for next quarter.
NT10BIX5570065 | 2011 | Q2 | Q2 - 2011 | The April 1, 2011 to June 30, 2011 quarter project accomplishments completed during this quarter include: 1) Buggs Island Telephone Cooperative received a Finding of No Significant Impact following the submission of the Environmental Assessment; 2) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 3) Buggs Island Telephone Cooperative selected a vendor to purchase a Brocade 10 gigabit Core Ring for the core network equipment through their procurement process; 4) Buggs Island Telephone Cooperative is continuing the process of negotiating tower leases; 5) Buggs Island Telephone Cooperative made their second draw down from the grant funds to pay for engineering services provided; 6) Buggs Island Telephone Cooperative selected Airspan as the primary vendor for the WiMax Equipment to be used for the project and signed a contract for the equipment and services. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No variance | No variance | No variance | 0 | 0 | 0 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | Buggs Island Telephone anticipates receiving all of the core equipment and completing installation of the core equipment, completing procurement for all equipment, and starting the installation of equipment at tower sites. | Buggs Island Telephone Cooperative | Buggs Island Telephone Cooperative (BIT) has begun tower negotiations with the owners of the towers for the sites that have been selected. BIT may face challenges with some of the currently selected tower sites and need to make substitutions. As of August 16, 2011 BIT has identified 5 tower sites that will need to be changed from the originally submitted plan. These site changes are primarily due to the fact that the towers are structurally inadequate. BIT has previously notified NTIA of these changes and is working on the administrative filing to get these changes approved by NTIA. BIT will keep NTIA apprised of developments related to tower negotiations and difficulties encountered. | Buggs Island Telephone Cooperative has identified 5 tower sites that will need to be changed from the originally submitted plan. These site changes are primarily due to the fact that the towers are structurally inadequate. BIT has previously notified NTIA of these changes and is working on the administrative filing to get these changes approved by NTIA.
NT10BIX5570065 | 2011 | Q3 | Q3 - 2011 | The July 1, 2011 quarter project accomplishments completed during this quarter include: 1) Continuing bi-weekly calls between National Telecommunications and Information Administration (NTIA) and Buggs Island Telephone Cooperative (BIT); 2) BIT has completed the procurement of equipment; 3) BIT is continuing the process of negotiating tower leases; 4) BIT has identified five (5) alternate towers to replace towers that are inadequate for the WiMax equipment and has submitted a request for approval of the sites identified as alternates, but has not yet received approval through the Environmental Assessment process; 5) BIT submitted the Davis Bacon wage determination request to the NTIA on August 17, 2011; 6) BIT submitted three (3) draws for this quarter; 7) BIT is continually receiving equipment ordered in preparation for the build out of the network to commence on October 17, 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No variance | No variance | No variance | 0 | 0 | 0 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable | Buggs Island Telephone Cooperative anticipates obtaining most of the remaining lease agreements with the tower owners, installing equipment on at least nine (9) of the thirty-five (35) tower sites, and receiving approval on the submitted alternate tower sites from NTIA. While these towers will be operational, each site must go through extensive testing before the service can be offered commercially. BIT anticipates that the testing of these sites will conclude at the end of next quarter for commercial launch in January of 2012. BIT has meetings scheduled with interested wholesale providers for next quarter, and anticipates having at least one agreement with a wholesale provider by the end of the quarter. BIT plans to meet the 2/3 project completion deadline by adding additional tower crews for equipment deployment. Airspan, the WiMax equipment vendor for this project, who BIT has also contracted with for the network build, is also aware of the mandated build-out deadlines. BIT and Airspan communicate daily throughout each week regarding the project and equipment orders. There is no impact to the overall completion of the project related to the change in tower locations. These changes should also not affect the 2/3 completion deadline of March 31, 2012, provided they are approved early next quarter. | Buggs Island Telephone Cooperative | Buggs Island Telephone Cooperative (BIT) has begun tower negotiations with the owners of the towers for the sites that have been selected. BIT may face challenges with some of the currently selected tower sites and need to make substitutions. BIT has identified five (5) tower sites that will need to be changed from the originally submitted plan. These site changes are primarily due to the fact that the towers are structurally inadequate. BIT has submitted a request for these changes to NTIA and will keep NTIA apprised of any new developments. | Buggs Island Telephone Cooperative (BIT) has begun tower negotiations with the owners of the towers for the sites that have been selected. BIT may face challenges with some of the currently selected tower sites and need to make substitutions. BIT has identified five (5) tower sites that will need to be changed from the originally submitted plan. These site changes are primarily due to the fact that the towers are structurally inadequate. BIT has submitted a request for these changes to NTIA and will keep NTIA apprised of any new developments.
NT10BIX5570065 | 2011 | Q4 | Q4 - 2011 | The October 1, 2011 to December 31, 2011 quarter project accomplishments completed include: 1) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 2) Buggs Island Telephone Cooperative is continuing the process of negotiating tower leases; 3) Buggs Island Telephone Cooperative has identified seven (7) alternate towers to replace towers that are inadequate for the WiMax equipment and has received approval from the National Telecommunications and Information Administration on December 27, 2011 for these changes; 4) Buggs Island Telephone Cooperative has submitted the Davis Bacon wage determination request to the National Telecommunications and Information Administration, which still remains pending; 5) Buggs Island Telephone Cooperative submitted three (3) draws for this quarter; 6) Buggs Island Telephone Cooperative continues to receive equipment ordered in preparation for the build out of the network; 7) Build-out of the network commenced on October 17, 2011; 8) Buggs Island Telephone Cooperative has installed WiMax equipment on nine (9) towers and site testing is underway. | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | N/A | N/A | N/A | N/A | N/A | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. These sites are in various stages of completion and each lacks lacks power and/or backhaul. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. These sites are in various stages of completion and each lacks lacks power and/or backhaul. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | 0 | 2 | 12 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers and plans to have signed agreements by the end of next quarter. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers and plans to have signed agreements by the end of next quarter. | No variance. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers and plans to have signed agreements by the end of next quarter. | 0 | 0 | 0 | 0 | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | 0 | 0 | 0 | 0 | 0 | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | 0 | 0 | 0 | 0 | 0 | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone has WiMax equipment on ten (10) of the 35 towers. Testing will commence during next quarter and BIT anticipates a commercial launch by quarter two of 2013. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | Buggs Island Telephone Cooperative anticipates obtaining all of the remaining lease agreements with the tower owners and installing equipment on at least nine (24) of the thirty-five (35) tower sites. While these towers will be operational, each site must go through extensive testing before the service can be offered commercially. BIT anticipates that the testing will be continual throughout next quarter and that as testing is complete sites will be commercially ready. BIT has meetings scheduled with interested wholesale providers, and anticipates having at least two agreements with wholesale providers by the end of the quarter. BIT plans to meet the 2/3 project completion deadline of March 31, 2012 by adding additional tower crews for equipment deployment. Airspan, the WiMax equipment vendor for this project, who BIT has also contracted with for the network build, is also aware of the mandated build-out deadlines. BIT and Airspan communicate daily throughout each week regarding the project and equipment orders. | Buggs Island Telephone Cooperative | A challenge Buggs Island Telephone Cooperative (BIT) faced during quarter 4, 2011 was placing the build-out of equipment on seven towers on hold while waiting on the approval from NTIA on changing the locations of these sites. Approval was received on December 27, 2011 to proceed with the alternate sites. While waiting on this approval BIT adjusted the build-out schedule in order to continue productivity during this time of review. | Buggs Island Telephone Cooperative (BIT) is continuing tower negotiations with the owners of the towers for the sites that have been selected. BIT may face challenges with some of the currently selected tower sites and need to make substitutions. These substitutions are primarily due to the fact that the towers are structurally inadequate.
NT10BIX5570065 | 2012 | Q1 | Q1 - 2012 | The January 1, 2012 to March 31, 2012 quarter project accomplishments completed include: 1) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 2) Buggs Island Telephone Cooperative is continuing the process of negotiating tower leases; 3) Five of the towers selected by Buggs Island Telephone Cooperative (BIT) for locations of the WiMax equipment have failed the structural analysis and BIT will be completing the Pre-Screening Criteria worksheets and submitting them to NTIA for review of the necessary tower modifications; 4) Buggs Island Telephone Cooperative has submitted the Davis Bacon wage determination request to the National Telecommunications and Information Administration, which was approved; 5) Buggs Island Telephone Cooperative submitted two (2) draws for this quarter; 6) Buggs Island Telephone Cooperative continues to receive equipment ordered in preparation for the build out of the network; 7) At March 31, 2012 build-out of the network was 67% complete with tower equipment installed at 24 sites; 8) Buggs Island Telephone Cooperative has begun testing of the network and has begun installation of beta testers. | 72 | 0 | 0 | 0 | 0 | 6 | 24 | 14 | At the end of March, 2012 BIT had installed WiMax equipment on 24 of the total 35 sites. Of these sites, 6 are wireless links, and BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012. However, that wireless link will be installed during the last phase of the buildout beginning in quarter three, 2012. | N/A | N/A | N/A | N/A | Buggs Island Telephone has WiMax equipment installed at 24 of the 35 towers. Of these, six are microwave sites. BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012, however, that wireless link will be installed during the last phase of the buildout beginning in quarter three, 2012. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter two of 2012. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter two of 2012. | 0 | 2 | 12 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | No variance. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | 293 | 0 | 1 | 4 | Buggs Island Telephone completed the installations of WiMax equipment on 24 of the 35 tower sites on March 31, 2012. Of those sites, 20 had backhaul available at March 31,2012. Testing of those sites began before the end of the quarter and seven (7) beta testers were installed to help test the service. One (1) of these testers is a community anchor institution and the other six (6) are residential customers. Since the completion of the WiMax equipment installations occurred so close to the end of the quarter there have not been many installations of end users, but the total subscribers able to receive the service last quarter is high. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. | On March 31, 2012 Buggs Island Telephone had installed one Community Anchor Institution as a beta tester. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. The beta tester is receiving 4 Mbps. | 62159 | 62159 | 6 | 0 | 3 | Buggs Island Telephone completed the installations of WiMax equipment on 24 of the 35 tower sites on March 31, 2012. Of those sites, 20 had backhaul available at March 31,2012. Testing of those sites began before the end of the quarter and seven (7) beta testers were installed to help test the service. One (1) of these testers is a community anchor institution and the other six (6) are residential customers. Since the completion of the WiMax equipment installations occurred so close to the end of the quarter there have not been many installations of end users, but the total subscribers able to receive the service last quarter is high. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. | On March 31, 2012 Buggs Island Telephone had installed six (6) residential beta testers. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, and 4 Mbps. The beta testers are receiving 1.5 Mbps. | 9177 | 9177 | 0 | 0 | 4 | Buggs Island Telephone completed the installations of WiMax equipment on 24 of the 35 tower sites on March 31, 2012. Of those sites, 20 had backhaul available at March 31,2012. Testing of those sites began before the end of the quarter and seven (7) beta testers were installed to help test the service. One (1) of these testers is a community anchor institution and the other six (6) are residential customers. Since the completion of the WiMax equipment installations occurred so close to the end of the quarter there have not been many installations of end users, but the total subscribers able to receive the service last quarter is high. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. There were no businesses installed during quarter 1, 2012. | Seven (7) beta testers were installed last quarter to help test the service. Of these, one was a Community Anchor Institution who is receiving improved access, while the other six (6) are residential customers. The residential customers are all receiving new access. There were no businesses installed during quarter 1, 2012. | On March 31, 2012 Buggs Island Telephone had not installed any business customers. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | Buggs Island Telephone Cooperative (BIT) anticipates obtaining the remaining lease agreements with the tower owners and submitting documentation to NTIA regarding the tower modifications needed on five (5) of the existing towers in order to install the WiMax equipment. BIT anticipates continuing the testing of the network and commercially launching service after the sites have completed the testing phase satisfactorily. BIT will also continue negotiations with wholesale providers. | Buggs Island Telephone Cooperative | Five of the towers selected by Buggs Island Telephone Cooperative (BIT) for locations of the WiMax equipment have failed the structural analysis. BIT will be completing the Pre-Screening Criteria worksheets and submitting them to NTIA for review of the necessary tower modifications. | Buggs Island Telephone Cooperative (BIT) is continuing tower negotiations with the owners of the towers for the sites that have been selected. BIT may face challenges with some of the currently selected tower sites passing a structural analysis.
NT10BIX5570065 | 2012 | Q2 | Q2 - 2012 | The April 1, 2012 to June 30, 2012 quarter project accomplishments completed include: 1) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 2) Buggs Island Telephone Cooperative is continuing the process of negotiating tower leases with only three tower leases remaining; 3) Buggs Island Telephone Cooperative received approval from National Telecommunications and Information Administration to upgrade towers that did not pass structural analysis in order to hold the WiMax equipment; 4) Buggs Island Telephone Cooperative submitted two (2) draws for this quarter; 5) At June 30, 2012 build-out of the network remains to be 67% complete with tower equipment installed at 24 sites; 6) Buggs Island Telephone Cooperative continues to test the network and continues installing beta testers. | 72 | 0 | 0 | 0 | 0 | 6 | 24 | 14 | At the end of March, 2012 BIT had installed WiMax equipment on 24 of the total 35 sites. Of these sites, 6 are wireless links, and BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012. However, that wireless link will be installed during the last phase of the buildout, which is scheduled to begin in quarter four, 2012. | N/A | N/A | N/A | N/A | At the end of March, 2012 BIT had installed WiMax equipment on 24 of the total 35 sites. Of these sites, 6 are wireless links, and BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012. However, that wireless link will be installed during the last phase of the buildout, which is scheduled to begin in quarter four, 2012. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter three of 2012. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter three of 2012. | 0 | 2 | 12 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | No variance. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | 293 | 293 | 0 | 5 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012. At the end of June, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | All of the Community Anchor Institutions served are receiving new access to service from Buggs Island Telephone Cooperative. | All of the Community Anchor Institutions served are receiving new access to service from Buggs Island Telephone Cooperative. | On June 30, 2012 Buggs Island Telephone had three (3) Community Anchor Institution customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 6 Mbps, and 10 Mbps. Two (2) of these customers are receiving 3 Mbps and one (1) is receiving 6 Mbps. | 62159 | 62159 | 62159 | 0 | 4 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012. At the end of June, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | All of the residential subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter three, 2012. | All of the residential subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter three, 2012. | On June 30, 2012 Buggs Island Telephone had 59 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1 Mbps, 1.5 Mbps, 3 Mbps, and 4 Mbps. Three (3)customers are receiving 1 Mbps, 47 customers are receiving 1.5 Mbps, and nine (9) customers are receiving 3 Mbps. | 9177 | 9177 | 9177 | 0 | 4 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012. At the end of June, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | All of the business subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter three, 2012. | All of the business subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter three, 2012. | On June 30, 2012 Buggs Island Telephone had two (2) business business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. One of the business is receiving 1.5 Mbps, and the other is receiving 10 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | BIT anticipates completion of the testing and optimization of the currently installed 24 sites and a commercial launch of the service to those covered by these towers. The commercial launch is not anticipated to occur until the end of the quarter due to the testing and optimization, therefore, no new miles will be deployed next quarter and no new CAI connections are planned until quarter four of 2012. Once the testing and optimization is completed BIT will continue in negotiations with wholesale providers. | Buggs Island Telephone Cooperative | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter three, 2012, at which time the system will be ready for a commercial launch. | Commercial launch of the network is dependent upon successful optimization and testing performed by Buggs Island Telephone Cooperative's vendor.
NT10BIX5570065 | 2012 | Q3 | Q3 - 2012 | The July 1, 2012 to September 30, 2012 quarter project accomplishments completed include: 1) Continuing bi-weekly calls between National Telecommunications and Information Administration and Buggs Island Telephone Cooperative; 2) Buggs Island Telephone Cooperative is continuing the process of negotiating tower leases with only two tower leases remaining; 3) Buggs Island Telephone Cooperative has begun the process of upgrading the last of the towers that need structural adjustments due to failure to pass structural analysis; 4) Buggs Island Telephone Cooperative submitted one (1) draw for this quarter; 5) At September 30, 2012 build-out of the network remains to be 67% complete with tower equipment installed at 24 sites; 6) Buggs Island Telephone Cooperative is continuing to work with the equipment vendor to address issues within the network. | 72 | 0 | 0 | 0 | 0 | 6 | 24 | 14 | At the end of September, 2012 BIT had installed WiMax equipment on 24 of the total 35 sites. Of these sites, 6 are wireless links, and BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012. However, that wireless link will be installed during the last phase of the buildout, which is scheduled to begin in quarter one, 2013. | N/A | N/A | N/A | N/A | At the end of September, 2012 BIT had installed WiMax equipment on 24 of the total 35 sites. Of these sites, 6 are wireless links, and BIT originally estimated that 7 of the wireless links would be complete by the end of March, 2012. However, that wireless link will be installed during the last phase of the buildout, which is scheduled to begin in quarter one, 2013. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter four of 2012. | Buggs Island Telephone has WiMax equipment on 24 of the 35 towers. Testing has commenced and will continue into next quarter, with a commercial launch of service from these sites anticipated before the end of quarter four of 2012. | 0 | 2 | 12 | No signed agreements to date. | No signed agreements to date. | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | No variance. | Buggs Island Telephone Cooperative is currently in negotiations with two wholesale providers. | 293 | 293 | 0 | 5 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012. At the end of September, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | All of the Community Anchor Institutions served are receiving new access to service from Buggs Island Telephone Cooperative. | All of the Community Anchor Institutions served are receiving new access to service from Buggs Island Telephone Cooperative. | On September 30, 2012 Buggs Island Telephone had three (3) Community Anchor Institution customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 6 Mbps, and 10 Mbps. Two (2) of these customers are receiving 3 Mbps and one (1) is receiving 6 Mbps. | 62159 | 62159 | 62159 | 0 | 92 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012. At the end of September, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | All of the residential subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter four, 2012. | All of the residential subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter four, 2012. | On September 30, 2012 Buggs Island Telephone had 92 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1 Mbps, 1.5 Mbps, 3 Mbps, and 4 Mbps. Five (5) customers are receiving 1 Mbps, 75 customers are receiving 1.5 Mbps, and 12 customers are receiving 3 Mbps. | 9177 | 9177 | 9177 | 0 | 4 | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new customers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four, 2012. At the end of September, 2012 there were 9,177 business customers, 293 CAI customers, and 62,159 residential customers served. | Since this service is wireless the total number of entities passed is the same as the total number of subscribers served. | All of the business subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter four, 2012. | All of the business subscribers served are receiving new access to service from Buggs Island Telephone Cooperative. Installation of new customers has been suspended until the equipment vendor performs testing and optimization on the network. A commercial launch is anticipated for the end of quarter four, 2012. | On September 30, 2012 Buggs Island Telephone had two (2) business business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. One of the business is receiving 1.5 Mbps, and the other is receiving 10 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. | FALSE | Not applicable. | BIT anticipates completion of the testing and optimization of the currently installed 24 sites and a commercial launch of the service to those covered by these towers. The commercial launch is not anticipated to occur until the end of the quarter due to the testing and optimization, therefore, no new miles will be deployed next quarter and no new CAI connections are planned until quarter one of 2013. Once the testing and optimization is completed BIT will continue in negotiations with wholesale providers. | Buggs Island Telephone Cooperative | The equipment vendor has requested additional time for testing and optimization of the network. At the direction of the vendor, BIT will not be installing new beta testers until this test period and optimization is achieved. The vendor projects that this testing and optimization of the system will be complete by the end of quarter four 2012, at which time the system will be ready for a commercial launch. | Commercial launch of the network is dependent upon successful optimization and testing performed by Buggs Island Telephone Cooperative's vendor.
NT10BIX5570065 | 2012 | Q4 | Q4 - 2012 | Airspan completed optimization of the network. | 72 | 0 | 0 | 0 | 0 | 6 | 24 | 14 | Six of the sites are connected with wireless links and are completed. The remaining one wireless link will be established in the final phase of the build-out of the remaining 11 sites. | N/A | N/A | N/A | N/A | Six wireless links are installed. | 24 leased towers have had equipment installed. | BIT has connected with the fiber backbone with these interconnection points and they are tested and ready. | 0 | 3 | 12 | None | Broadband wholesale reseller services. | Not applicable. | 0 | 0 | 0 | 0 | BIT has negotiated with three wholesale entities and are awaiting the launch of commercial service before finalizing the agreements. | Three entities are being considered. | No Variance | BIT is negotiating with three entities. | 6 | 0 | 0 | 6 | BIT is awaiting re-configuration of the 700 megahertz network before marketing the service and signing up subscribers. | N/A | N/A | 1-6mbps 2-3mbps 3-1.5mbps | 62159 | 82 | 0 | 0 | 82 | Total households in the 15 county service area. | 82 beta-testers. | Service not yet being marketed. | Not Applicable. | 3-6 mbps 79-1.5mbps | 9177 | 10 | 0 | 0 | 4 | Total businesses in service area. | The businesses are all beta-testers. | Awaiting completion of the 3.65 testing by year end. | Not applicable. | 1-10 mbps 2-6 mbps 1-3 mbps | BIT will offer discounted service to all CAI's. | FALSE | Not applicable. | Airspan will have completed the 3.65 network and the testing will have been completed. Service offerings will commence within 1.5 miles of the six sites. BIT will have complied with all of the Corrective Action Plan provisions. | Buggs Island Telephone Cooperative | Aispan has sent over 30 firmware upgrades for the customer premise equipment, but the default to factory settings problem exists. | 3.65 network has to be accepted and the 700 network must be re-designed and re-configured to BIT's satisfaction.
NT10BIX5570065 | 2013 | Q1 | Q1 - 2013 | 1) The Buggs Island Telephone (BIT) grant was placed under suspension and a Corrective Action Plan (CAP) was issued on January 4, 2013. BIT provided the CAP responses on March 18, 2013 which allowed the suspension to be partially lifted on March 26, 2013 to enable BIT to secure a third party partner to provide assistance in completing the project; 2) Due to unmitigated interference with its 700 MHZ WiMAX deployment, BIT anticipates retrofitting its 700 MHz WiMAX network with a 700 MHz LTE network with construction to begin in Q3 of 2013; 3) BIT initiated the solicitation of a third party partner to assist with the management and administrative needs of the project and 4) BIT received an extension of the original grant termination date of 3/31/13 to 9/30/13, thus providing BIT an additional 6 months to complete the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline report indicated at the end of Year 3-Q4 BIT would have 120 network miles deployed. Since BIT will be converting from a WiMAX network to an LTE network, if approved by NTIA, no LTE miles were deployed for this reporting period. | N/A | N/A | N/A | N/A | The baseline report indicated at the end of Year 3 Q4 BIT would have 10 wireless links. Since BIT will be converting from a WiMAX network to an LTE network, if approved by NTIA, no new wireless links were deployed for this reporting period. | Buggs, Island Telephone, a wireless last mile provider, has successfully installed 3.65 GHz WiMAX service on six towers that cover a service area of 5 counties containing a population of 5,414 persons. The testing and and commercial launch of the 3.65 service will be implemented in Q2 of 2013. BIT's planned 700 MHz WiMAX network was deployed on 24 of 35 towers by Q1 of 2012;, however, reciprocal and unmitigated interference with neighboring operators has required BIT to retrofit its network and transition to 700 MHz LTE with construction to begin in Q3 fo 2013 if approved by NTIA. As noted, equipment was installed on 24 towers with 6 of the 24 towers offering 3.65 GHz WiMAX and a few towers equipped with 700 MHz WiMAX to be retrofitted with 700 MHz LTE in Q3 of 2013. | The baseline report indicated at the end of Q4-2013, BIT would have 35 interconnection points. Since BIT will be converting from a WiMAX network to an LTE network if approved by NTIA, no new interconnection points were deployed for this reporting period. | 0 | 0 | 0 | The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | BIT is providing no wholesale services at this time but is providing 3.65 GHz retail services in Mecklenburg and Brunswick counties. Please see attached price list. | BIT has no third party agreements at this time. | 0 | 0 | 0 | 0 | BIT is currently not negotiating with wholesale providers. The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | BIT is currently not negotiating with wholesale providers. The baseline report indicated at the end of Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network has been the highest priority for BIT. | N/A | BIT is currently not negotiating with wholesale providers .The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network over to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | 5 | 0 | 5 | 5 | The baseline report projected BIT would serve 482 CAIs by the end of Q4-2013. To date BIT has 5 CAIs who are serving as beta testers and will begin to pay for the service with discounted rates by the end of Q3 2013. The reason for the limited number of CAIs served is due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | As noted above, to date BIT is serving 5 CAIs. These CAIs are classified as receiving improved access not receiving new access. | All of the CAIs served are receiving improved access from BIT. | The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 6 Mbps, and 10 Mbps. One (1) of these customers is receiving 1.5 Mbps, two (2) of these customers are receiving 3 Mbps, one (1) is receiving 6 Mbps and one (1) is receiving 10 Mbps. | 14165 | 76 | 10 | 66 | 3 | The baseline report indicated that it would be possible to potentially serve 102,468 residential households from the installation of a WiMAX system that would be operational by the end of Q4-2013. BIT only had six towers powered and offering service to customers during this quarter. | The baseline report projected BIT would serve 26,777 residential households by the end of Q4-2013,. To date BIT has 76 who are serving as beta testers and will begin to pay for the service with by the end of Q3 2013. The reason for the limited number of residential households served is due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | 10 of the residential subscribers served are receiving new access to service from BIT. | 66 of the residential subscribers served are receiving improved access to service from BIT. | On March 31, 2013 Buggs Island Telephone had 76 residential beta customers on 700 WiMAX who will transition to 700 LTE. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, and 4 Mbps. 70 customers are receiving 1.5 Mbps, and 6 customers are receiving 3 Mbps. | 2406 | 7 | 1 | 6 | 4 | The baseline report indicated that it would be possible to potentially serve 15,128 businesses from the installation of a WiMAX system that would be operational by the end of Q4-2013. BIT only had six towers powered and offering service to customers during this quarter. | The baseline report projected BIT would serve 4,813 businesses by the end of Q4-2013. To date BIT has 7 who are serving as beta testers and will begin to pay for the service with by the end of Q3 2013. The reason for the limited number of business subscribers served is due to converting from a WiMAX network to an LTE network if approved by NTIA. Working to deploy the network is the highest priority for BIT. | Only 1 of the business subscribers served are receiving new access to service from BIT. | 6 of the business subscribers served are receiving improved access to service from BIT. | On March 31, 2013 Buggs Island Telephone had four (4) business beta customers receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. Two (2) of the business is receiving 3 Mbps, one (1) is receiving 4 Mbps and one (1) is receiving 10 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report | 1) Procure a LTE vendor and execute a contract; 2) Place the equipment order with the selected LTE vendor; 3) Submit a Management Plan that permits the full lift of the grant suspension; and 4) Identify a 3rd party partner to assist in the implementation and management of the LTE conversion; and 5) Begin negotiations with tower companies in an effort to release monthly payment obligations on towers no longer needed for the project. | Buggs Island Telephone Cooperative | Buggs Island Telephone has faced many challenges with the deployment of a WiMAX system that was not compatible with neighboring LTE deployed systems. After many meetings with neighboring companies and the grant funding agencies, the decision was made to abandon the WiMAX system and deploy a new LTE network if approved by NTIA. With only limited grant funds remaining, the project service area has been reduced from a 15-county area to a 5-county area. BIT s proceeding with all the necessary activities that will result in a fully deployed LTE system that will serve the under-served and un-served residents, businesses, and community-anchor institutions located in the five-county region. | 1) Challenges will include negotiating with Airspan on the unused WiMAX equipment and 2) Ensuring that the project will be complete by the new extension date of September 2013.
NT10BIX5570065 | 2013 | Q2 | Q2 - 2013 | 1) Buggs Island Telephone issued a RFP to identify equipment vendors and costs to convert from WIMAX technology to LTE technology and received proposals for review; 2) Negotiations continue with tower lease companies to relieve Buggs Island Telephone from lease charges as a result of the conversion; 3) Buggs Island Telephone is receiving 3rd party assistance for the implementation of project activities and for advisement on debt consolidation strategies; 4) Buggs Island Telephone is preparing a LTE Business Model that will be presented to the funding agencies in Q3-2013 in an effort to fully lift the suspension of the grant and proceed with the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline report indicated at the end of Year 3-Q4, BIT would have 120 network miles deployed in a 15-county service area. Upon receiving approval from NTIA, BIT will convert from a WiMAX network to an LTE network for a 5-county service area. No LTE miles were deployed for this reporting period. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | The baseline report indicated at the end of Year 3-Q4, BIT would have 10 wireless links in a 15-county service area. Upon receiving approval from NTIA, BIT will convert from a WiMAX network to an LTE network for a 5-county service area. No new wireless links were deployed for this reporting period. | BIT's planned 700 MHz WiMAX network was deployed on 24 of 35 towers by Q1-2012;, however, reciprocal and unmitigated interference with neighboring operators has required BIT to retrofit its network and transition to 700 MHz LTE with construction to begin in Q3-2013, contingent upon NTIA approval. As noted, equipment was installed on 24 towers with 6 of the 24 towers offering 3.65 GHz WiMAX; plans are to convert only the towers needed to serve the reduced 5-county area with the LTE network in Q3-2013. | The baseline report indicated at the end of Year 3-Q4, BIT would have 35 interconnection points in a 15-county service area. Upon receiving approval from NTIA, BIT will convert from a WiMAX network to an LTE network for a 5-county service area. No new interconnection points were deployed for this reporting period. | 0 | 0 | 0 | The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. Upon receiving approval from NTIA, BIT will convert from a WiMAX network to an LTE network for a 5-county service area. To date BIT has zero signed agreements. Working to deploy the network is the highest priority for BIT. | BIT is providing no wholesale services at this time but is providing 3.65 GHz retail services in Mecklenburg and Brunswick counties. Attached is the price list for review. | BIT has no third party agreements at this time. | 0 | 0 | 0 | 0 | BIT is currently not negotiating with wholesale providers. The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network to an LTE network, contingent upon NTIA approval. Working to deploy the network is the highest priority for BIT. | BIT is currently not negotiating with wholesale providers. The baseline report indicated at the end of Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network to an LTE network, contingent upon NTIA approval. Working to deploy the network has been the highest priority for BIT. | Not Applicable | BIT is currently not negotiating with wholesale providers .The baseline report indicated at the end of Year Q4-2013 BIT would have 5 signed wholesale agreements. To date BIT has zero signed agreements due to converting from a WiMAX network over to an LTE network, contingent upon NTIA approval. Working to deploy the network is the highest priority for BIT. | 5 | 0 | 5 | 5 | The baseline report projected BIT would serve 482 CAIs by the end of Q4-2013. To date BIT has 5 CAIs who are serving as beta testers and will begin to pay for the service with discounted rates by the end of Q3-2013. The limited number of CAIs served is due to a planned conversion from a WiMAX network to an LTE network, contingent upon NTIA approval. Working to deploy the network is the highest priority for BIT. | As noted above, to date BIT is serving 5 CAIs. These CAIs are classified as receiving improved access not receiving new access. | All of the CAIs served are receiving improved access from BIT. | The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 6 Mbps, and 10 Mbps. One (1) of these customers is receiving 1.5 Mbps, two (2) of these customers are receiving 3 Mbps, one (1) is receiving 6 Mbps and one (1) is receiving 10 Mbps. | 14165 | 76 | 10 | 66 | 3 | The baseline report indicated that it would be possible to potentially serve 102,468 residential households from the installation of a WiMAX system serving a 15-county area that would be operational by the end of Q4-2013. BIT only had six towers powered and offering service to customers during this quarter. | The baseline report projected BIT would serve 26,777 residential households by the end of Q4-2013,. To date BIT has 76 who are serving as beta testers and will begin to pay for the service with by the end of Q3-2013. The limited number of residential households served is due to a planned conversion from a WiMAX network to an LTE network, contingent upon NTIA approval. Working to deploy the network is the highest priority for BIT. | 10 of the residential subscribers served are receiving new access to service from BIT. | 66 of the residential subscribers served are receiving improved access to service from BIT. | On June 30, 2013 Buggs Island Telephone had 76 residential beta customers on 700 WiMAX who will transition to 700 LTE. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, and 4 Mbps. 70 customers are receiving 1.5 Mbps, and 6 customers are receiving 3 Mbps. | 2406 | 7 | 1 | 6 | 4 | The baseline report indicated that it would be possible to potentially serve 15,128 businesses from the installation of a WiMAX system that would be operational by the end of Q4-2013. BIT only had six towers powered and offering service to customers during this quarter. | The baseline report projected BIT would serve 4,813 businesses by the end of Q4-2013. To date BIT has 7 who are serving as beta testers and will begin to pay for the service by the end of Q3- 2013. The reason for the limited number of business subscribers served is due to a planned conversion from a WiMAX network to an LTE network, contingent upon NTIA approval. Working to deploy the network is the highest priority for BIT. | Only 1 of the business subscribers served are receiving new access to service from BIT. | 6 of the business subscribers served are receiving improved access to service from BIT. | On June 30, 2013 Buggs Island Telephone had seven (7) business beta customers receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 10 Mbps. Five (5) of the business is receiving 3 Mbps, one (1) is receiving 4 Mbps and one (1) is receiving 10 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report | 1) Select a LTE vendor and execute a contract; 2) Place the equipment order with the selected LTE vendor; 3) Submit a Management Plan to NTIA that permits the full lift of the grant suspension; and 5) Continue negotiations with tower companies in an effort to release monthly payment obligations on towers no longer needed for the project. | Buggs Island Telephone Cooperative | Buggs Island Telephone has not received formal authorization from NTIA to proceed with the conversion from WIMAX to LTE technology and the full release of grant dollars has not been issued. | 1) Challenges will include negotiating with Airspan on the unused WiMAX equipment; 2) Receiving authorization to proceed with the LTE conversion and the full release of grant funds; and 3) Ensuring that the project will be complete by the new extension date of September 2013.
NT10BIX5570065 | 2013 | Q3 | Q3 - 2013 | During the quarter, NTIA lifted BITâ€™s suspension on September 5, 2013 having approved BIT's July 26, 2013 Revised Broadband Plan, which called for transitioning to LTE wireless technology and reducing the geographic scope of BIT's project from three cellular market areas (CMAs) to one CMA. In accord with its Revised Plan, BIT continued its efforts to select an LTE vendor, to decommission unneeded towers, to terminate unnecessary tower contracts, and to sell excess equipment. NTIA extended BIT's BTOP grant to September 30, 2014 to enable it to complete its Revised Broadband Plan. BIT finalized and signed a purchase agreement to sell the two CMAs eliminated as a result of BIT's reduced scope and an application for FCC approval of the transaction is pending. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description. | BIT's plan to deploy LTE technology on 10 towers by 9/30/2014. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network is the highest priority for BIT and since the project is reduced in it's geographic coverage area to 5 counties, BIT plans to be the provider for those counties. Of course, if a wholesale provider approaches BIT with interest in becoming a wholesale provider, BIT will certainly look in to that prospect to determine if that would be a better business decision. | BIT provides no wholesale services and plans to discontinue WiMAX retail services when LTE service is available. | BIT has no third party agreements at this time. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 0 | 0 | 0 | 0 | BIT has projected to serve 10 CAIs by the end of 9/30/2014. | None | None | None | 0 | 76 | 0 | 0 | 0 | BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area. | BIT has projected to serve 1,368 residential households by the end of 9/30/2014. To date BIT has 76 users who will be transitioned to LTE when available. | None | None | None | 0 | 7 | 0 | 0 | 0 | BIT has projected to have the potential to serve 1,828 businesses included in the 5 county serving area. | BIT has projected to serve 232 businesses by the end 9/30/2014. To date BIT has 7 users who will be transitioned to LTE when available. | None | None | None | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report | 1) Execute a contract with the recently selected LTE vendor and place the equipment order; 2) Continue negotiations with tower companies in an effort to release monthly payment obligations on towers no longer needed for the project; 3) Remove WiMAX equipment from the towers and competitively sell to interested vendor(s); and 4) Initiate the installation of LTE equipment in the NTIA approved 5-county area. | Buggs Island Telephone Cooperative | BIT and BIT's legal counsel conducted thorough reviews of the new LTE vendor contracts. BIT requested and negotiated revisions to the contracts which affected the progress of executing, hence, somewhat delaying the project schedule. | Challenges include negotiating with the previous WiMAX vendor and tower lease companies, as many of the original tower sites identified are no longer needed for the LTE deployment.
NT10BIX5570065 | 2013 | Q4 | Q4 - 2013 | 1) Negotiations continue to terminate lease agreements with tower companies whose towers are located in the two CMAâ€™s that are no longer targeted for BIT build-out. By the end of the 4Q 2013 BIT has successfully terminated tower lease agreements with 8 of the 10 tower companies (11 of the 25 individual tower leases). The remaining 14 unneeded tower leases are projected to be finalized during Q1 2014. 2) The LTE vendor has been selected and a contract was signed and dated 11/7/13. 3) The removal of WiMAX equipment from the 14 tower sites located in the two CMAs that are no longer in the project footprint was completed in 12/2013. 4) BIT, along with its engineering firm and the LTE vendor, NetAmerica, completed the radio network design in 12/2013. 5) The circuit to BIT's hosted core (SuperCenter) was ordered on 12/18/13. 6) The LTE RAN equipment (Radio Access Network) was ordered on 12/20/13 with a possible delivery date toward the end of 2/2014. 7) LTE vendor conducted testing of several types of Customer Premise Equipment (CPE) in order to determine which type would best suit BIT's needs. Testing will continue in the first half of Q1 2014 with a recommendation being made to BIT. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description. | BIT's plan to deploy LTE technology on 10 towers by 9/30/14. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network is the highest priority for BIT and since the project is reduced in it's geographic coverage area to 5 counties, BIT plans to be the provider for those counties. BIT is prepared to provide access to its network to wholesale carriers. | At this time, BIT provides no wholesale services and plans to discontinue WiMAX retail services when LTE service is available. | BIT has no third party agreements at this time. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 0 | 0 | 0 | 0 | BIT has projected to serve 10 CAIs by the end of 9/30/2014. | None | None | None | 0 | 45 | 0 | 0 | 0 | BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area. | BIT has projected to serve 1,368 residential households by the end of 9/30/2014. To date BIT has 45 WiMAX users who will be transitioned to LTE when available. | None | None | None | 0 | 5 | 0 | 0 | 0 | BIT has projected to have the potential to serve 1,828 businesses included in the 5 county serving area. | BIT has projected to serve 232 businesses by the end 9/30/2014. To date BIT has 5 WiMAX users who will be transitioned to LTE when available. | None | None | None | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) Continue negotiations with tower companies in an effort to release monthly payment obligations on towers no longer needed for the project. 2) Engineer and order SIM cards. 3) Order Customer Premise Equipment (CPE). 4) Start on the site make ready for all 10 tower sites in the 5 county serving area. 5) Network equipment should be delivered by the end of 2/2014 but installation on the 10 towers is not projected until May 2014. 6) Circuit testing and acceptance to the hosted core (SuperCenter) should be completed. | Buggs Island Telephone Cooperative | Tower lease terminations continue to be a time consuming and lengthy process but are expected to be complete by Q1 2014. | 1) BIT will need to get approval from the tower companies for equipment modifications for the 10 tower sites before the site make ready can be completed. BIT needs this permission as quickly as possible to stay on schedule with the proposed build-out time line. 2) BIT will need to relocate equipment from one existing tower to another per the tower owners request. This will result in having a structural analysis and environmental review. BIT will need to submit a request to NTIA for approval. BIT will need to start this process immediately in order to remain on schedule against the projected milestones.
NT10BIX5570065 | 2014 | Q1 | Q1 - 2014 | 1) Negotiations continue to terminate lease agreements with tower companies whose towers are located in the two CMAâ€™s that are no longer targeted for BIT build-out. By the end of the Q1 2014 BIT has successfully terminated tower lease agreements with 9 of the 10 tower companies (23 of the 25 individual tower leases). The remaining 2 unneeded tower leases are projected to be finalized during Q2 2014. 2) The LTE RAN equipment (Radio Access Network) was delivered and received by BIT in February and March. The antennas and cables were ordered and expected to be delivered in Q2 2014. 3) The Fiber Circuit (BIT) to the Converged Regional Core (Panhandle) that was ordered in Q4 2013 has been tested and accepted in late March 2014. 4) The Converged Regional Core Fiber Circuit (Panhandle) to the SuperCenter (NetAmerica) that was ordered in Q4 2013 has been tested and accepted in late March 2014. 5) A total of 13 antennas were ordered and received; the remaining antennas needed will be delivered in Q2-2014. 6) BIT's backhaul and transport network designs have been completed and issued to Ericsson. 7) SIM cards were engineered and ordered in March with delivery and testing to occur in Q2 2014. 8) Brocade software upgrades were ordered, delivered and installed during March. 9) Testing continues by NetAmerica on the several types of Customer Premise Equipment (CPE) in order to determine which type would best suit BIT's needs with a recommendation and an order being placed in Q2 2014. BIT had expected to have CPE ordered during Q1 but a second CPE vendor was being evaluated for better performance which has caused a slight delay on the order. This delay will not affect the installation schedule and BIT will have CPE once customer installs begin in Q3 2014. 10) BIT has completed the site acquisition and has clearance to proceed with the installation of the LTE equipment on one existing tower. The other 9 are expected to be completed in Q2 2014 so installation can begin during Q2 as well. The Alberta tower failed the initial analysis; options are being considered for an alternative site. 11) BIT has completed phase one of the marketing launch plan in February that includes identifying the target markets and the network coverage which includes the GoToMarket Strategy Plan that was completed in March. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description | Not Applicable | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network is the highest priority for BIT and since the project is reduced in it's geographic coverage area to 5 counties, BIT plans to be the provider for those counties. BIT is prepared to provide access to its network to wholesale carriers. | At this time, BIT provides no wholesale services and plans to discontinue WiMAX retail services when LTE service is available during Q3 2014. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 0 | 0 | 0 | 0 | BIT has projected to serve 10 CAIs by the end of 9/30/2014. | None | None | None | 0 | 22 | 0 | 0 | 0 | BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area. | BIT has projected to serve 1,368 residential households by the end of 9/30/2014. To date BIT has 22 WiMAX users who will be transitioned to LTE when available. The number of users has decreased from Q4 2013 due to the ongoing issues related to the WiMAX service resulting in some users finding alternate means of an internet connection until the LTE network is up and operating. | None | None | None | 0 | 5 | 0 | 0 | 0 | BIT has projected to have the potential to serve 1,828 businesses included in the 5 county serving area. | BIT has projected to serve 232 businesses by the end 9/30/2014. To date BIT has 5 WiMAX users who will be transitioned to LTE when available. | None | None | None | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) Tower contract back rent settlements will be finalized. 2) SIM card testing will be finalized. 3) Customer Premise Equipment (CPE) will be ordered and delivered. 4) Complete the site make ready for all 10 tower sites in the 5 county serving area. 5) Network equipment will be installed on the 10 towers and the first site made live. 6) The sale of WiMAX equipment will be initiated. 7) The resolution to replace the Alberta tower site will be identified and resolved. 8) The first phase of the marketing plan will be initiated. Possible beta testers will be added to active sites and presales will be started. | Buggs Island Telephone Cooperative | Tower lease terminations continue to be a time consuming and lengthy process but are expected to be complete by Q2 2014. Getting the 10 tower sites make ready for the LTE retrofit are taking longer than expected due to BIT trying to finalize termination agreements with some of the tower companies who will also continue to do business with BIT on some existing sites included within the project footprint. This process has caused delays in receiving lease amendments but is fully expected to be completed in Q2 2014. CPE ordering continues to be delayed due to a second vendor's equipment being evaluated, but this will help BIT insure that the customers will be receiving the best product performance. The Alberta Tower Site failed the initial structural analysis and options are being considered for an alternate site. | 1) BIT continues to get approvals from the tower companies for the equipment modifications on some of the tower sites in order to proceed on schedule with the proposed build-out timeline. Overall, this delay will not affect the project completion deadline of 9/30/14. 2) The Alberta replacement tower will still be an ongoing problem and a resolution will happen during this quarter but will push out the retrofit for this site until last. This has caused a change in the proposed order in which the 10 towers will be retrofitted, but again, will not affect the project completion date of 9/30/14.
NT10BIX5570065 | 2014 | Q2 | Q2 - 2014 | 1) All existing WiMAX lease agreements have been terminated. 2) Network testing and optimization of the LTE network is underway. Testing and optimization is expected to be complete in Q3 of 2014. 3) Four (4) additional beta testers have been added and BIT has started the retrofit of the remaining WiMAX customers to the new LTE equipment. 4) LTE Equipment has been successfully installed on nine (9) out of 10 towers; negotiations continue to locate an alternative tower to replace the Alberta Tower. 5) Purchase orders were issued for indoor and outdoor CPE equipment and mobile MiFi devices; Indoor and outdoor devices have been received. BIT plans to test the VoIP capability in Q3 of 2014. 6) Phase I of the Marketing Plan has been rolled out and will end mid July of 2014. 7) Discussions on the sale of of the WiMAX equipment are in process between NTIA and BIT pending a final decision from NTIA on the appropriate course of action. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description | All wireless network towers are leased by BIT, not owned so the count will remain at 0. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network is the highest priority for BIT and since the project is reduced in it's geographic coverage area to 5 counties, BIT plans to be the provider for those counties. BIT is prepared to provide access to its network to wholesale carriers. | At this time, BIT provides no wholesale services and plans to discontinue WiMAX retail services when LTE service is available during Q3 2014. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 0 | 0 | 0 | 0 | BIT has projected to serve 10 CAIs by the end of 9/30/2014. | None | None | None | 0 | 22 | 0 | 0 | 0 | BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area. | BIT has projected to serve 1,368 residential households by the end of 9/30/2014. To date BIT has 22 WiMAX users who will be transitioned to LTE when available. The number of users has decreased from Q4 2013 due to the ongoing issues related to the WiMAX service resulting in some users finding alternate means of an internet connection until the LTE network is up and operating. | None | None | None | 0 | 5 | 0 | 0 | 0 | BIT has projected to have the potential to serve 1,828 businesses included in the 5 county serving area. | BIT has projected to serve 232 businesses by the end 9/30/2014. To date BIT has 5 WiMAX users who will be transitioned to LTE when available. | None | None | None | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) Customer Premise Equipment has been ordered and the first shipment has been received. Additional shipments will be received in Q3 of 2014. 2) Approval from the grant office on the proper disposal of the WiMAX equipment. 3) The resolution to replace the Alberta tower site will be identified and the equipment install will be completed. 4) Testing will be complete and optimization achieved of the newly installed LTE network resulting in active and ongoing CPE installs as customers sign-up for the service. 5) The second and third phase of the Marketing Plan will be initiated which includes a direct-mail customer letter with marketing materials and follow-up postcards targeted to approximately 9,000 households, businesses, and CAIs. 6) BIT's project will be fully operational and commercially ready remaining on schedule with the project end date of 9/30/14. | Buggs Island Telephone Cooperative | The Alberta Tower Site failed the initial structural analysis and options are being considered for an alternate site. Negotiations are underway between the tower owner, MBC, and BIT and alternative tower sites are being discussed in an effort to secure the 10th tower site and begin LTE installation. | BIT does not anticipate any issues during the next quarter that would either delay or impact the planned progress against the project milestones. BIT now continues to stay on track with the project completion deadline of 9/30/14.
NT10BIX5570065 | 2014 | Q3 | Q3 - 2014 | 1) Network testing and optimization is complete on nine out of ten towers; configuration is underway for the 10th tower (Alberta Tower). Tower optimization and commercial deployment for the Alberta Tower is targeted for Q4 of 2014. 2) Phase 2 of the Marketing Plan has been developed and is underway. Customer installs continue and are increasing in numbers. Additional BIT techs have been hired to handle the growing requests for service. 3) Discussions on the disposition of the WiMAX equipment continue between NTIA and BIT pending a final decision from NTIA on the appropriate course of action. 4) BIT requested a no-cost nine month extension from NTIA in an effort to successfully complete the LTE retrofit of the Alberta Tower, time to install additional equipment on three of the ten towers to expand signal strength and reach additional customers located in the tower service area and enable BIT time to capture and install the 1,600 customers that we had proposed serving by the end of the grant period in our approved Revised Broadband Plan dated 9/2013. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description | All wireless network towers are leased by BIT, not owned so the count will remain at 0. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network has been the highest priority for BIT. BIT is prepared to provide access to its network to wholesale or retail providers. BIT has a wholesale agreement in place for interested providers. | At this time, BIT provides no wholesale services but plans are underway to do so in the future. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 1 | 1 | 0 | 0 | BIT has projected to serve 10 CAIs by the end of the project. | BIT has projected to serve 10 CAIs by the end of the project. | None | During Q3 BIT had one (1) Community Anchor Institution customer installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 6 Mbps, and 10 Mbps. This customer is receiving 6 Mbps. | 30720 | 146 | 146 | 0 | 3 | BIT has projected the potential to reach 30,720 of the 35,345 households included in the 5 county serving area given signal coverage. | BIT has projected to serve 1,368 residential households by the end of the proposed extension period of 6/30/2015. | BIT has projected to serve 1,368 residential households by the end of the proposed extension period of 6/30/2015 | None | During Q3 BIT had 146 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, and 4 Mbps. 53 customers are receiving 1.5 Mbps, 47 customers are receiving 3 Mbps, and 46 customers are receiving 4 Mbps. | 1589 | 13 | 13 | 0 | 5 | BIT has projected the potential to reach 1,589 of the 1,828 businesses included in the 5 county serving area given signal coverage. | BIT has projected to serve 232 businesses by the end of the proposed extension period of 6/30/2015. | BIT has projected to serve 232 businesses by the end of the proposed extension period of 6/30/2015. | None | During Q3 BIT had 13 business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 6 Mbps, 10 Mbps and 12 Mbps. 6 of the businesses are receiving 1.5 Mbps, 4 businesses are receiving 3 Mbps, 2 are receiving 10 Mbps and 1 is receiving 12 Mbps. | Buggs Island Telephone Cooperative will be offering discounted business rates to Community Anchor Institutions. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) Complete optimization and initiate commercial launch of the Alberta Tower 2) Additional marketing plans will be launched. 3) Additional equipment will be installed on three towers to more effectively reach identified potential customers. 4) Continue to address the appropriate disposal of WiMAX equipment. | Buggs Island Telephone Cooperative | The Alberta Tower Site had been stalled for at least five months due to a land owner/tower owner dispute that was resolved in 9/2014, allowing BIT to begin installation of the Alberta tower in Q3 with commercial deployment targeted for Q4 of 2014. As a result, an extension request was submitted to NTIA requesting additional time to complete the Alberta Tower and to install additional equipment on the Blackstone, Clarksville and South Brunswick towers to successfully reach potential customers in the identified service area. | BIT does not anticipate any issues during the next quarter that would either delay or impact the planned progress against the project milestones. BIT now continues to stay on track with the project and continues its efforts in gaining customers.
NT10BIX5570065 | 2014 | Q4 | Q4 - 2014 | On April 1, 2010, NTIA awarded Buggs Island $18,983,648 to build a WiMAX network in 15 counties in south central Virginia. BIT provided an additional $4,975,049 in matching funds, including a $3,879,087 cash match from the Virginia Tobacco Indemnification and Community Revitalization Commission. By early 2012 with deployment well underway, it became apparent that the WiMAX system faced unacceptable interference from neighboring LTE systems, which rendered BITâ€™s network inoperable. Thus, in September 2013, NTIA approved a revised plan that allowed Buggs Island to use its remaining funds to deploy a 10 tower LTE network in five of the original fifteen counties: Amelia, Brunswick, Mecklenburg, Lunenburg and Nottoway, as part of the NetAmerica Alliance. That network includes leased backhaul circuits from MBC connecting 8 of 10 towers to our NetAmerica hosted core in Houston, TX, two wireless links connecting the Lawrenceville tower to the South Brunswick tower, Jetersville tower to Earls tower, and long haul transit via Level 3 connecting BITâ€™s LTE network to the NetAmerica core. As of 12/31/2014, Buggs Island has operationalized all ten towers and installed 1 CAI, 378 residential and 17 business customers toward our goal of 1600 users. Completed this quarter: 1) Tower optimization and commercial deployment for the Alberta Tower is complete; optimization on all ten towers is complete. 2) The expansion of coverage on three towers is underway; antennas were ordered on 12/10/14 and delivered on 1/12/15. The notice-to-proceed from tower owners have been executed and approved. The expansion of coverage will be completed in mid-February. 3) Phase 3 of the Marketing Plan has been completed. Next round of marketing materials are scheduled for mailing in mid-February. 4) Customer installs continue and are increasing in numbers. Additional BIT techs have been hired to handle the growing requests for service. Additional CPE units are needed to fulfill install orders. 5) A disposition request has been submitted by BIT to the Grants Office that identifies the plan of action for the disposition of the WiMAX equipment; the request is pending approval by the Grants Office. 6) BIT requested a no-cost nine month extension from NTIA in an effort to: a) successfully complete the LTE retrofit of the Alberta Tower, b) install additional equipment on three of the ten towers to expand signal strength and reach additional customers located in the tower service area, and c) capture and install the 1,600 customers as proposed in the Revised Broadband Plan dated 9/2013; the extension request has not been formally approved by the Grants Office. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description. | All wireless network towers are leased by BIT, not owned so the count will remain at 0. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network has been the highest priority for BIT. BIT is prepared to provide access to its network to wholesale or retail providers. BIT has a wholesale agreement in place for interested providers. | At this time, BIT provides no wholesale services but plans are underway to do so in the future. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 1 | 1 | 0 | 4 | BIT has projected to serve 10 CAIs by the end of the project. | BIT has projected to serve 10 CAIs by the end of the project. | None | By the end of Q4 BIT had one (1) Community Anchor Institution customer installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. This customer is receiving 6 Mbps. | 30720 | 378 | 378 | 0 | 4 | BIT has projected the potential to reach 30,720 of the 35,345 households included in the 5 county serving area given signal coverage. | BIT has projected to serve 1,368 residential households by the end of the proposed extension period of 6/30/2015. | BIT has projected to serve 1,368 residential households by the end of the proposed extension period of 6/30/2015 | None | By the end of Q4 BIT had 378 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. 106 customers are receiving 1.5 Mbps, 136 customers are receiving 3 Mbps, 131 customers are receiving 4 Mbps and 5 customers are receiving 6 Mbps. | 1589 | 17 | 17 | 0 | 5 | BIT has projected the potential to reach 1,589 of the 1,828 businesses included in the 5 county serving area given signal coverage. | BIT has projected to serve 232 businesses by the end of the proposed extension period of 6/30/2015. | BIT has projected to serve 232 businesses by the end of the proposed extension period of 6/30/2015. | None | By the end of Q4 BIT had 17 business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 10 Mbps and 12 Mbps. 6 of the businesses are receiving 1.5 Mbps, 6 businesses are receiving 3 Mbps, 2 are receiving 4 Mbps, 2 are receiving 10 Mbps and 1 is receiving 12 Mbps. | Buggs Island Telephone Cooperative offers discounted rates to Community Anchor Institutions by charging residential rates instead of business rates. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) The next round of marketing materials will be mailed. 2) Additional CPE's will be ordered to maintain the install schedule. 3) Additional equipment will be installed on three towers to more effectively reach identified potential customers. 4) The disposition request for the disposal of WiMAX equipment will be approved by the Grants Office. | Buggs Island Telephone Cooperative | The Grant Extension Request submitted by BIT needs to be approved in an effort to maintain project momentum. Draw Requests and Quarterly Reporting are being negatively affected by the delayed response. | BIT does not anticipate any issues during the next quarter that would either delay or impact the planned progress against the project milestones. BIT now continues to stay on track with the project and continues its efforts in gaining customers.
NT10BIX5570065 | 2015 | Q1 | Q1 - 2015 | 1) The expansion of coverage on three towers is underway. Equipment has been received, installed on the Clarksville tower, and waiting on the final scripting work to be completed by the equipment vendor before optimization can be done. The expansion of coverage on the three towers was also delayed due to constant inclement weather but is expected to be completed during Q2 2015. 3) Implementation of the Marketing Plan continues and is delivering exceptional results. 4) Customer installs continue and are increasing in numbers. 5) In March 2015 the Grants Office gave the approval to a partial disposition of the abandoned WiMAX equipment that was submitted by BIT that identifies the plan of action for the disposition of the abandoned WiMAX equipment; the partial approval was for a small amount of the equipment and the additional request for the remaining equipment is pending approval by the Grants Office. 6) BIT requested a no-cost nine month extension from NTIA in an effort to: a) successfully complete the LTE retrofit of the Alberta Tower, b) install additional equipment on three of the ten towers to expand signal strength and reach additional customers located in the tower service area, and c) capture and install the 1,600 customers as proposed in the Revised Broadband Plan dated 9/2013; the extension request was formally approved by the Grants Office in March 2015. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description. | All wireless network towers are leased by BIT, now owned so the count will remain at 0. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network has been the highest priority for BIT. BIT is prepared to provide access to its network to wholesale or retail providers. BIT has a wholesale agreement in place for interested providers. | At this time, BIT provides no wholesale services but plans are underway to do so in the future. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 1 | 1 | 0 | 5 | BIT has projected to serve 10 CAIs by the end of the project. | BIT has projected to serve 10 CAIs by the end of the project. | None | By the end of Q1-2015, BIT had one (1) Community Anchor Institution customer installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. This customer is receiving 6 Mbps. | 30720 | 509 | 509 | 0 | 4 | BIT has projected the potential to reach 30,720 of the 35,345 households included in the 5 county serving area given signal coverage. | By the end of Q1 BIT has installed 509 customers who are receiving service. | By the end of Q1 BIT has installed 509 customers who are receiving service. | None | By the end of Q1 2015 BIT had 509 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. 113 customers are receiving 1.5 Mbps, 207 customers are receiving 3 Mbps, 180 customers are receiving 4 Mbps and 9 customers are receiving 6 Mbps. | 1589 | 11 | 11 | 0 | 5 | BIT has projected the potential to reach 1,589 of the 1,828 businesses included in the 5 county serving area given signal coverage. | By the end of Q1 BIT has installed 11 business customers who are receiving service. | By the end of Q1 BIT has installed 11 business customers who are receiving service. | None | By the end of Q1-2015, BIT had 11 business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 10 Mbps and 12 Mbps. 1 of the businesses is receiving 1.5 Mbps, 4 businesses are receiving 3 Mbps, 3 are receiving 4 Mbps, 2 are receiving 10 Mbps and 1 is receiving 12 Mbps. | Buggs Island Telephone Cooperative offers discounted rates to Community Anchor Institutions by charging residential rates instead of business rates. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) The next round of direct marketing materials will be mailed offering a special promotion to sign up for service. 2) BIT plans to attend local chamber of commerce meetings to help promote the BTOP wireless broadband offering throughout the five county serving area. BIT would also like to attend community events in order to demonstrate and promote broadband in areas that are un-served or under-served. 3) A new BIT website will be completed that has a comprehensive section on BIT's BTOP project, it's services and area availability. A potential customer will also be able to sign up for service directly from the website. 4) BIT plans to contact local community anchor institutions to make them aware of BIT's broadband services which offers discounted rates. BIT plans to connect an additional 9 CAI's during this quarter. 5) Additional CPE will be ordered to maintain the install schedule which will include adding approximately 200 additional households, 9 CAI's and 20 businesses. 6) Completion of additional equipment on three towers to more effectively reach identified potential customers. 7) The disposition request for disposal of the remaining WiMAX equipment will be approved by the Grants Office. Approved disposal of equipment will be delivered and transferred to the appropriate entities. | Buggs Island Telephone Cooperative | Since BIT received the no-cost grant extension approval from the Grants Office, challenges as far as draw approvals and reporting have improved. BIT struggled to achieve completion of the additional equipment on three towers due to constant inclement weather during Q1. The weather conditions also delayed customer installs slightly. | BIT does not anticipate any issues during the next quarter that would either delay or impact the planned progress against the project milestones. BIT now continues to stay on track with the project and continues its efforts in gaining customers.
NT10BIX5570065 | 2015 | Q2 | Q2 - 2015 | On April 1, 2010, NTIA awarded Buggs Island $18,983,648 to build a WiMAX network in 15 counties in south central Virginia. BIT provided an additional $4,975,049 in matching funds, including a $3,879,087 cash match from the Virginia Tobacco Indemnification and Community Revitalization Commission. By early 2012 with deployment well underway, it became apparent that the WiMAX system faced unacceptable interference from neighboring LTE systems, which rendered BITâ€™s network inoperable. Thus, in September 2013, NTIA approved a revised plan that allowed Buggs Island to use its remaining funds to deploy a 10 tower LTE network in five of the original fifteen counties: Amelia, Brunswick, Mecklenburg, Lunenburg and Nottoway, as part of the NetAmerica Alliance. That network includes leased backhaul circuits from MBC connecting 8 of 10 towers to our NetAmerica hosted core in Houston, TX and long haul transit via Level 3 connecting BITâ€™s LTE network to the NetAmerica core. As of 12/31/2014, Buggs Island has operationalized all ten towers and to date has installed 1 CAI, 541 residential and 12 business customers. Community outreach efforts continue on an ongoing basis in order to educated the public to the benefits of being able to provide a much needed service to rural Southern Virginia. 1) The expansion of coverage on the Blackstone, Clarksville and South Brunswick towers is complete. Customers who could not receive the service before off these towers are now being re-visited. 2) Marketing continues and is delivering exceptional results. 3) Customer installs continue and are increasing in numbers. 4) In June, the approval to gift a portion of the unused WiMAX equipment to Virginia Tech and Georgia Tech was finalized. Both will take possession in July 2015. Disposition of the remaining unused WiMAX equipment will be finalized next quarter. | 23 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | The 23 miles includes microwave links between Lawrenceville to South Brunswick and Jetersville to Earls. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Includes links as listed above in the network miles description. | All wireless network towers are leased by BIT, not owned, so the count will remain at 0. | Not Applicable | 0 | 0 | 0 | To date BIT has zero signed agreements. Working to deploy the network has been the highest priority for BIT. BIT is prepared to provide access to its network to wholesale or retail providers. BIT has a wholesale agreement in place for interested providers. | At this time, BIT provides no wholesale services but plans are underway to do so in the future. | 1) NetAmerica, the LTE provider for BIT and a contractor, will operate the hosted core (SuperCenter) in Houston, Texas. Contact information: Chuck Harris, 888.686.2747. 2) Panhandle Telephone, who is an alliance member of NetAmerica and a subcontractor, will operate the Converged Regional Core, which is part of the hosted core that is located in Guymon, Oklahoma. Contact information: Travis Clark, 800.562.2556. | 0 | 0 | 0 | 0 | None | None | Not Applicable | None | 1 | 1 | 0 | 5 | BIT had projected to serve 10 CAIs by the end of the project but only one has been accomplished due to the unavailability of a signal to provide internet to the other CAIs. These CAIs are also located within town limits where competition for services are high. BIT will continue to evaluate its offering and pricing plans and work on improving the overall network in order to attempt capturing more of the predicted CAIs in the future. | BIT had projected to serve 10 CAIs by the end of the project but only one has been accomplished due to the unavailability of a signal to provide internet to the other CAIs. These CAIs are also located within town limits where competition for services are high. BIT will continue to evaluate its offering and pricing plans and work on improving the overall network in order to attempt capturing more of the predicted CAIs in the future. | None | BIT has one (1) Community Anchor Institution customer receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. This customer is receiving 6 Mbps. | 30720 | 541 | 541 | 0 | 4 | BIT has projected the potential to reach 30,720 of the 35,345 households included in the 5 county serving area given signal coverage. | By the end of Q2 BIT has installed 541 customers who are receiving service. | By the end of Q2 BIT has installed 541 customers who are receiving service. | None | By the end of Q2 2015 BIT had 541 residential customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, and 6 Mbps. 111 customers are receiving 1.5 Mbps, 225 customers are receiving 3 Mbps, 197 customers are receiving 4 Mbps and 8 customers are receiving 6 Mbps. | 1589 | 12 | 12 | 0 | 5 | BIT has projected the potential to reach 1,589 of the 1,828 businesses included in the 5 county serving area given signal coverage. | By the end of Q2 BIT has installed 12 business customers who are receiving service. | By the end of Q2 BIT has installed 12 business customers who are receiving service. | None | By the end of Q2-2015, BIT had 12 business customers installed and receiving service. The speed tiers offered, depending on availability, include 1.5 Mbps, 3 Mbps, 4 Mbps, 10 Mbps and 12 Mbps. 2 of the businesses is receiving 1.5 Mbps, 5 businesses are receiving 3 Mbps, 4 are receiving 4 Mbps, and 1 is receiving 12 Mbps. | Buggs Island Telephone Cooperative offers discounted rates to Community Anchor Institutions by charging residential rates instead of business rates. BIT will also offer broadband services to community parks in exchange for advertising BIT's services. | FALSE | No changes to report. | 1) The disposition of the remaining WiMAX equipment will be completed. 2) Work on close-out documents will begin and be ready to submit by September 28, 2015. 3) BIT will continue its efforts in conducting community outreach throughout the five county serving area to ensure residents, businesses and community anchor institutions are aware of BIT's broadband offering. Even though these efforts will fall outside of the award period, BIT wants to successfully aid in providing a much needed service to rural areas in Southern Virginia and will monitor this network with diligent efforts to provide a viable service in hopes of sustaining current customers and gaining new ones. | Buggs Island Telephone Cooperative | BIT struggled to achieve completion of the additional equipment on three towers due to constant inclement weather during Q1 and additional work required by the tower companies in order to install the equipment on their towers.. The extreme wet weather conditions also delayed customer installs slightly. | BIT's project officially expired on June 30, 2015. BIT will continue to work towards the successful deployment of a much needed broadband service to the residents, businesses and community anchor institutions throughout the five county serving area in Virginia.
NT10BIX5570066 | 2010 | Q4 | Q4 - 2010 | During Q4 of 2010, BVU Authority (BVUA) made significant progress on the required environmental assessment for the project, including final consultation with all environmental and cultural resource agencies. Still pending are final approval from the U.S. Fish and Wildlife Service and the U.S.D.A. Forest Service. The first draft of the environmental assessment was submitted on December 14, 2010. BVUA also began final engineering of all the routes with its contracted engineering firm. The invitations to bid (ITB) for both construction and materials have been distributed and BVUA expects to award the contracts for both in the coming quarter. BVUA also sent the project manager for this grant to the Compliance Conference in Washington D.C. in November. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | Middle-mile backbone connection. Please see attached sheet for service offerings and prices. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has a MOU with the Virginia Department of Transportation to provide lease of dark fiber in exchange for use of VDOT ROW. | 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | -Completion of final environmental assessment and Finding of No Significant Impact (FONSI) from NTIA. -Continued engineering of routes. -Awarding of contracts for both construction and materials. -Complete applications for and receive all necessary permits for the first routes. -Begin construction of the first routes. | BVU Authority | Areas of concern for BVUA during Q4 2010 mainly included environmental assessment-related hold-ups. Specifically, BVUA experienced delays with both the U.S. Fish and Wildlife Service and the U.S.D.A. Forest Service. The Forest Service did not accept accepted BVUA's application for build in the National Forest until Dec. 20, and clarification is underway with the U.S. Fish and Wildlife Service regarding the smooth coneflower. | BVUA expects for the project to progress as scheduled. The only potential hold-ups might be the winter weather in Southwest Virginia and/or a delay in approval from the U.S.D.A Forest Service.
NT10BIX5570066 | 2011 | Q1 | Q1 - 2011 | During Q1-2011, BVUA reviewed environmental assessment (EA) draft changes and submitted the final EA to NTIA on January 25, 2011. FONSI was signed and received by BVUA on February 24, 2011. Construction contract was signed at the end of February, and construction subsequently started on March 7, 2011. Both engineering and construction are progressing well, with only slight setbacks due to the harsh weather in Q1-2011. Currently, BVUA and construction contractor Edwards Telecommunications, Inc. are working on 3 different sections of the route, while engineering firm Thompson & Litton continues engineering on approximately 10 more route sections. BVUA anticipates working with the USDA Forest Service in Q2-2011 to complete necessary work on National Forest build permits (during the growing season). BVU has also edited percentage completed based on a revised baseline following some budget changes. Percentages in some categories may appear to go down, but percent complete and revised baseline calculations (attachment to this report) now match completely. Confusion stemmed from assuming a category was 100% complete if all activities were completed, not if all funds were expended. BVU has also corrected allocation to permits and to site prep, which are both very small percentages of the categories of engineering and construction in the OMB budget, respectively. | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | This category shows a lag of about 8 miles due to harsh Southwest Virginia winter weather and a delayed FONSI for BVU's EA. | N/A | N/A | N/A | This category shows a lag of about 8 miles due to harsh Southwest Virginia winter weather and a delayed FONSI for BVU's EA. | N/A | N/A | Because of the slight delay in mileage due to weather and EA issues, no splices had been done at the end of the reporting quarter to connect new fiber to existing network fiber. There were, however, 3 impending interconnections at the end of the quarter. | 0 | 0 | 0 | N/A | Middle-mile backbone connection. Please see attached sheet for service offerings and prices. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an MOU with the Virginia Department of Transportation to provide lease of dark fiber in exchange for use of VDOT ROW. | 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | -Continued engineering of all routes -Continued construction of 3 routes currently in progress; additional construction on 3-5 more routes -Complete and secure all stream crossing and RR permits -Conduct some or all of the biological work required for National Forest Permits -Finalize PoP locations and begin procurement of materials. | BVU Authority | BVU Authority is tracking progress in this report solely by dollars expended, not by work performed or invoiced. Therefore, some categories may appear to be lagging behind (Ex. Engineering had invoiced for 27% of dollars by the end of the quarter, but BVU had only paid 15%), but are on track by actual work done. The same for materials- 3% has been received, but as of the end of the quarter, less than 1% had been invoiced and none had been paid. BVU faced particular challenges in this quarter, particularly with a delay in receiving the EA FONSI (2-4 weeks later than planned in baseline), unusually harsh winter weather for the area, and changes in planned engineering (which has delayed procurement of electronics/materials related to PoPs). Based on guidance from NTIA, BVU is charging all in-kind assets to the grant at this point to prevent any depreciation. BVU also revised some categories to show actual dollars expended, rather than activities completed (based on new PPR guidance). BVU expects both engineering and construction to pick up during the summer months once permitting hurdles are crossed and harsh weather subsides. | During the Q2-2011, BVU Authority will faces challenges in engineering and construction of PoPs, as they will be engineered in relation to the routes on which they will be placed. Engineering and construction are both also encountering rough terrain, which is slightly delaying both activities. BVU will also be conducting biological studies for National Forest permits, which, based on previous experience with the USDA FS, could be finished quickly, or could take the length of the growing season (May 15-Sept. 15). Other permitting (stream and RR) will be dependent on the efficiency of the agencies at hand.
NT10BIX5570066 | 2011 | Q2 | Q2 - 2011 | During Q2-2011, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well, with only slight lingering setbacks due to severe spring weather and materials shipment delays. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 2 routes and are working on an additional 5 routes, while engineering firm Thompson & Litton continues engineering on approximately 10 more route sections. As of the end of the quarter, approximately 70.7 miles were constructed. BVU and Thompson & Litton have begun working with USDA Forest Service to complete necessary work on National Forest build permits (during the growing season). This work is anticipated to be finished by the end of Q3-2011. BVU has also made some project modifications which require additional EA consult, which is underway and progressing well and will be completed early in Q3-2011. | 71 | 0 | 0 | 0 | 71 | 0 | 0 | 2 | BVU is made up the lag from the previous quarter, and despite severe weather and material delays, is 5 miles ahead of Baseline schedule. | N/A | N/A | N/A | BVU is made up the lag from the previous quarter, and despite severe weather and material delays, is 5 miles ahead of Baseline schedule. | N/A | N/A | Due to delays in starting PoP engineering/build, there are only two routes actually spliced into existing BVU infrastructure at this point. However, as of the end of the quarter, 5 connections were pending. | 0 | 0 | 0 | N/A | Please see attached sheet for pricing. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an MOU with the Virginia Department of Transportation to provide lease of dark fiber in exchange for use of VDOT ROW. | 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | -Continued engineering of all routes -Continued construction of 5 routes currently in progress; additional construction on 3-5 more routes -Continue completion and submittal of pole, RR, and construction permits -Conduct/finalize all biological work required for National Forest Permits; receive permits. -Finalize Project Modification request and begin engineering of PoPs once new locations are approved. | BVU Authority | BVU Authority faced particular difficulties in construction due to unusually severe weather for the area in the months of April and May. BVU also experienced slight delays in receiving fiber. Additionally, the project has a currently-proposed Project Modification in progress, and once all facets of the modification are approved, we can begin to start on actual PoP engineering and construction.However, despite these delays, build-out remains approximately 2 weeks ahead of schedule, and by dollars expended, the project is 1% ahead of the previous quarter's predictions. | Challenges BVU Authority will face next quarter include: -Potential continued severe weather, including severe storms and unusually high temperatures. -Possible additional delays in receiving fiber, due to the nationwide demand for it. -Expect completion of National Forest BE studies, assuming no delays.
NT10BIX5570066 | 2011 | Q3 | Q3 - 2011 | Earlier in quarter, BVU made minor budget adjustments through the normal budget change process to reflect some minor re-categorizing of expected expenses. Changes were discussed with FPO prior to making adjustment. These changes had no effect on NTIA contribution nor overall project costs. However, during OIG review, BVU was requested to adjust our in-kind match funds, to reflect additional in-kind value for ROW agreement with VDOT and for existing fiber and equipment not taken into account at time of original application. Per OIG Office and our FPO, they have requested that the in-kind changes be reflected in the PPR reports for 2011-Q3, even though other budget alteration documentation has not yet been completed. Expect to make these changes as soon as possible after getting PPR reporting completed. These in-kind additions have no effect on NTIA contribution, but will increase the in-kind matching values by $8,880,062 and alter overall project value from $36,220,536 to $45,100,598. During Q3-2011, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well, with only slight lingering setbacks due to encountering hard rock during fiber drilling causing anticipated completion of routes to be delayed. It is fully expected that BVU will overcome delay over the next two quarters. Currently, BVU Authority and cons | 99 | 0 | 0 | 0 | 99 | 0 | 0 | 2 | BVU encountered hard rock slowing down burying of fiber. With slow down we are no longer ahead of schedule, but are back to original schedule. | N/A | N/A | N/A | BVU encountered hard rock slowing down burying of fiber. With slow down we are slightly behind original schedule. | N/A | N/A | Due to delays in starting PoP engineering/build, there are only two routes actually spliced into existing BVU infrastructure at this point. However, as of the end of the quarter, 5 connections were still pending, there are only two routes actually spliced into existing BVU infrastructure at this point. However, as of the end of the quarter, 5 connections were still pending. | 1 | 0 | 0 | Virginia Department of Transportation. We provide 12 fiber strands in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation. Please see attached sheet for pricings to the Virginia Department of Transportation. Please see attached sheet for pricing. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an MOU with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | -Continued engineering of all routes -Continued construction of 10 routes currently in progress; additional construction on 3-5 more routes -Continue completion and submittal of pole, RR, and construction permits -Conduct/finalize all biological work required for National Forest Permits; receive permits. -Finalize Project Modification In-Kind request and begin engineering of PoPs once new locations are approved. | BVU Authority | BVU Authority faced particular difficulties in construction due to unusually hard rock encountered during drilling for buried fiber. This has not had a significant impact on the overall schedule, due to construction being several weeks ahead before encountering the drilling obstacles. We feel that the project is back to its original schedule. | Challenges BVU Authority will face next quarter include: -Potential winter weather -Expect completion of National Forest BE studies, assuming no delays.
NT10BIX5570066 | 2011 | Q4 | Q4 - 2011 | As mentioned in previous PPR report, OIG requested BVU to adjust our in-kind match funds, to reflect additional in-kind value for ROW agreement with VDOT and for existing fiber and equipment not taken into account at time of original application. Per OIG Office and our FPO, they requested that the in-kind changes be reflected in the PPR reports for 2011-Q3, which they were. However, we have had an outstanding question on how to reflect in award documentation (i.e. how should the budget be altered to reflect changes). Based on direction from our FPO, the preferred method to account for the in-kind valuation going forward is as follows. (1) Total in-kind dollars in accordance with OIG findings is: $22,402,587.60. (a. Cash: 5,659,502.60; b. Land/Structures: 691,431.00 c. Network: $14,697,930.00; d. Equipment: $1,353,724.00) (2) However, in order to reach our needed match amount, only $13,522,525.60 was used for the application and thus will be the amount reported on going forward. (3) Also, after discussions with FPO, it was decided the best method to recognize the in-kind use was in relation to the new miles of fiber being built (i.e. prorate in-kind amount over projected 388 miles being built and report in accordance to miles completed each reporting period). ****** Percentages AND expenditures (due to new formula to apply in-kind formula based on miles completed vs. applying all) shown will be reflected lower than last PPR due to the change in the in-kind method, however, going forward we should now have consistency. *********** During Q4-2011, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well, with only slight lingering setbacks due to encountering hard rock during fiber drilling in previous quarter. It is fully expected that BVU will overcome delay over the next two quarters. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished construction of 4 routes. Splicing of fiber is complete for one route. Other three routes scheduled to be splice by end of Jan 2012. There are currently 18 additional routes in progress, while engineering firm Thompson & Litton continues engineering on remaining 7 routes. As of the end of the quarter, approximately 120 miles were constructed. BVU and Thompson & Litton continue to work with USDA Forest Service to complete necessary work on National Forest build permits (during the growing season). This work was anticipated to be finished by the end of Q3-2011, but Forest Service has been slow to process. Expect completion no later than Q1-2012 in time for growing season. | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 2 | Good progress made in the quarter. Added 21 miles of fiber. | N/A | N/A | N/A | Good progress made in the quarter. Added 21 miles of fiber. | N/A | N/A | No new interconnection points added this quarter as emphasis was to continue build out on multiple routes versus splicing the fiber, however, 6 routes are scheduled to be completed and spliced in 2012-Q1. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in previous reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | - Continued engineering of 7 remaining routes - Complete construction of 9 of the current 15 routes in progress; start construction on 8 more routes. 23 more miles projected. - Continue completion and submittal of pole, RR, and construction permits - Receive National Forest Permit - First route will be lit to allow connection for last mile service. | BVU Authority | We have been waiting for the US Forest Service to give us a permit to build along the Virginia Creeper Trail for several months now. The window for building in the US Forest Service controlled land is fast approaching and we will need the permit before then. We have already had the environmental assessment approved by them, but they are painfully slow to approve permit. This has not had an impact to schedule as yet, but will if no permit received by April, it may become an issue. | We have been waiting for the US Forest Service to give us a permit to build along the Virginia Creeper Trail for several months now. The window for building in the US Forest Service controlled land is fast approaching and we will need the permit before April, or it may become an issue.
NT10BIX5570066 | 2012 | Q1 | Q1 - 2012 | During Q1-2012, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well with approximately 61% of the projected fiber miles completed putting us slightly ahead of schedule. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 3 routes and are working on an additional 19 routes. All of the remaining routes have been engineered. As of the end of the quarter, approximately 209 miles were constructed. HOWEVER, BVU still continues to wait for USDA Forest Service to approve National Forest build permits (during the growing season). All necessary paperwork has been submitted for over 4 months and are still awaiting approval. The Forest Service continues to delay due to "halt to all decisions nationwide based on categorical exclusions". They have stated that they hope to have permit approved now by mid-May. In Q1-2012, BVU made 12 drawdowns, amounting to $3,125,583.18, to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 209 | 0 | 0 | 0 | 209 | 0 | 0 | 3 | Good progress made in the quarter. Added 89 miles of fiber. | N/A | N/A | N/A | Good progress made in the quarter. Added 89 miles of fiber. | N/A | N/A | 1 interconnection points added this quarter as emphasis was to continue build out on multiple routes versus splicing the fiber, however,14 additional routes are scheduled to be completed and spliced in 2012-Q2. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in previous reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | - Complete construction of 17 of the 30 proposed routes - Start construction on 5 more routes. 55 more miles projected. - Continue completion and submittal of pole, RR, and construction permits - Receive National Forest Permit - At this time, we do not foresee having any wholesale/last mile provider agreements with outside vendors by end of quarter. Currently, BVU is providing last mile on several of the routes through other funding mechanisms. | BVU Authority | BVU still continues to wait for USDA Forest Service to approve National Forest build permit. All necessary paperwork has been submitted for over 4 months and are still awaiting approval. The Forest Service continues to delay due to "halt to all decisions nationwide based on categorical exclusions". They have stated that they hope to have permit approved now by mid-May. Any later than first of June will start to impact the route build out (Creeper Trail) due to growing season restrictions. | As mentioned several times previously, the only hurdle we foresee at this point is obtaining the National Forest permit.
NT10BIX5570066 | 2012 | Q2 | Q2 - 2012 | During Q2-2012, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well with approximately 73% of the projected fiber miles completed putting us slightly ahead of schedule. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 7 routes and are working on an additional 19 routes. All of the remaining routes have been engineered. As of the end of the quarter, approximately 258 miles were constructed. BVU FINALLY received permit approval, pending another build out description/schedule, from the USDA Forest. BVU has encountered unexpected issues with obtaining easements from private enterprises that BVU continues to work to solve. This has caused a slowdown in build out rate. In Q2-2012, BVU made 10 drawdowns, amounting to $ 3,589,266.58, to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 258 | 0 | 0 | 0 | 258 | 0 | 0 | 7 | Solid progress made in the quarter, but less than previous quarter due to previously mentioned easement and "make-ready" issues. Added 49 miles of fiber. | N/A | N/A | N/A | Solid progress made in the quarter, but less than previous quarter due to previously mentioned easement and "make-ready" issues. Added 49 miles of fiber. | N/A | N/A | 3 interconnection points added this quarter as emphasis was to continue build out on multiple routes versus splicing the fiber. More routes were expected to be completed, however, due to previously mentioned easement and "make ready" issues number of completed routes scheduled for Q2-2012 have been pushed out to Q3-2012. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in previous reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | - Complete construction of 17 of the 30 proposed routes - Start construction on 4 more routes. 49 more miles projected. - Continue completion and submittal of pole, RR, and construction permits - Receive National Forest Permit - At this time, we do not foresee having any wholesale/last mile provider agreements with outside vendors by end of quarter. Currently, BVU is providing last mile on several of the routes through other funding mechanisms. | BVU Authority | BVU still continues to wait for US Forest Service final approval for National Forest build permit. We have received verbal approval, but they asked for some additional clarifications on time line. All additional paperwork has been submitted and are now awaiting response. Process was started last November, so total time to date to get approval from Forest Service is going on 9 months. Also, project is experiencing delays due to easement issues with private land owners. Owners are requesting higher than normal rates. BVU attorney looking at option to condemn property if necessary. Could affect some of the designed routes if resolution takes more than 1 to 2 months. Also, experiencing longer than expected turn around of "make ready" requests. This has contributed to the slow down of the build out of the routes. | BVU still continues to wait for US Forest Service final approval for National Forest build permit. We have received verbal approval, but they asked for some additional clarifications on time line. All additional paperwork has been submitted and are now awaiting response. Process was started last November, so total time to date to get approval from Forest Service is going on 9 months. Also, project is experiencing delays due to easement issues with private land owners. Owners are requesting higher than normal rates. BVU attorney looking at option to condemn property if necessary. Could affect some of the designed routes if resolution takes more than 1 to 2 months. Also, experiencing longer than expected turn around of "make ready" requests. This has contributed to the slow down of the build out of the routes.
NT10BIX5570066 | 2012 | Q3 | Q3 - 2012 | During Q3-2012, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well with approximately 78% of the projected fiber miles completed putting us on schedule for completion 1-2 months ahead project end date. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 7 routes and are working on an additional 19 routes. All of the remaining routes have been engineered. As of the end of the quarter, approximately 284 miles were constructed. BVU has encountered unexpected issues with obtaining easements from private enterprises that BVU continues to work to solve. This has caused a slowdown in build out rate. In Q3-2012, BVU made 10 draw downs, amounting to $1,469,124.69, to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 284 | 0 | 0 | 0 | 284 | 0 | 0 | 7 | Slow progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 26 miles of fiber. | N/A | N/A | N/A | Slow progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 26 miles of fiber. | N/A | N/A | 0 interconnection points added this quarter as emphasis was to continue build out on multiple routes versus splicing the fiber. Additional routes were expected to be completed, however, due to previously mentioned easement and "make ready" issues number of completed routes scheduled for Q3-2012 have been pushed out to Q4 2012. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in previous reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE |  | - Complete construction of 17 of the 30 proposed routes - Start construction on 4 more routes. 40 more miles projected. - Continue completion and submittal of pole, RR, and construction permits - Obtain or start condemnation process on outstanding easements - At this time, we do not foresee having any wholesale/last mile provider agreements with outside vendors by end of quarter. Currently, BVU is providing last mile on several of the routes through other funding mechanisms. | BVU Authority | BVU has finally received US Forest Service final approval for National Forest build permit after 11 months. Also, project is experiencing delays due to easement issues with private land owners. Owners are requesting higher than normal rates. BVU attorney looking at option to condemn property if necessary. Could affect some of the designed routes if resolution takes more than 1 to 2 months. Also, experiencing longer than expected turn around of "make ready" requests. This has contributed to the slow down of the build out of the routes. Construction team not concerned with slow down as yet, as additional construction crews can be quickly brought to bear, if needed. | Project is experiencing delays due to easement issues with private land owners. Owners are requesting higher than normal rates. BVU attorney looking at option to condemn property if necessary. Could affect some of the designed routes if resolution takes more than 1 to 2 months. Also, experiencing longer than expected turn around of "make ready" requests. This has contributed to the slow down of the build out of the routes.
NT10BIX5570066 | 2012 | Q4 | Q4 - 2012 | During Q4-2012, BVU Authority continued with building out routes for the project, which included construction and engineering activities, as well as receiving and deploying materials. Both engineering and construction are progressing well with approximately 85% of the projected fiber miles completed putting us on schedule for completion 1-2 months ahead project end date. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 12 routes and are working on an additional 18 routes. All of the routes have been engineered. As of the end of the quarter, approximately 324 miles were constructed. BVU has encountered unexpected issues with obtaining easements from private enterprises that BVU continues to work to solve. This has caused a slowdown in build out rate. In Q4-2012, BVU made 11 draw downs, amounting to $2,037,228.55, to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 325 | 0 | 0 | 0 | 325 | 0 | 0 | 12 | Slower then expected progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 41 miles of fiber. | N/A | N/A | N/A | Slower then expected progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 41 miles of fiber. | N/A | N/A | Five additional routes (interconnection points) completed this quarter. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in initial reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | - Complete construction of 16 more routes (total 28) of the 30 proposed routes - Start construction on 2 remaining. 40 more miles projected. - Receive "quick-take" condemnations on outstanding easements - At this time, we do not foresee having any wholesale/last mile provider agreements with outside vendors by end of quarter. BVU is currently providing last mile on several of the routes through other funding mechanisms. | BVU Authority | Project has/is experiencing delays due to easement issues with private land owners. Owners are requesting higher than normal rates. BVU has taken the necessary steps to do "quick-take" condemnations of the remaining easement properties. Also, experienced longer than expected turn around of "make ready" requests due to regional crews being deployed to assist with Hurricane Sandy recovery. This contributed to the slow down of the build out of the routes. Construction team not concerned with slow down as yet, as additional construction crews can be quickly brought to bear, if needed. | Possible issue remains with obtaining all necessary easements through condemnation or negotiation. Currently, BVU does not see any impact to overall schedule.
NT10BIX5570066 | 2013 | Q1 | Q1 - 2013 | During Q1-2013, BVU Authority continued with building out routes, which included construction and limited engineering activities, as well as receiving and deploying materials. Construction is progressing well with approximately 91.8% of the projected fiber miles completed putting us on schedule for completion approximately 1 month ahead of project end date. Currently, BVU Authority and construction contractor, Edwards Telecommunications, Inc., have finished 14 routes and are working on finishing an additional 16 routes (less than 25% complete (1); 25%-50% complete (2); 50%-75% complete (3); greater than 75% complete (10)). As of the end of the quarter, approximately 338 miles were constructed of the engineered 368 miles. Please note, that due to more mileage being able to be placed aerially than buried, actual engineered mileage came to 368 miles, instead of the original estimate of 388 miles. BVU had encountered unexpected issues with obtaining easements from private enterprises and vendor make-ready turnaround that caused a slowdown in build out rate. In Q1-2013, BVU made 11 draw downs, amounting to $1,057,988.91, to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 338 | 0 | 0 | 0 | 338 | 0 | 0 | 14 | Slower then expected progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 13 miles of fiber. | N/A | N/A | N/A | Slower then expected progress made in the quarter due to previously mentioned easement and "make-ready" issues. Added 13 miles of fiber. | N/A | N/A | Two additional routes (interconnection points) completed this quarter. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in initial reports. | N/A | 0 | 0 | 1 | 9 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available rates via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Since the next quarter is the last quarter of the project, BVU plans on finishing all construction related tasks. | BVU Authority | Project experienced delays due to easement issues with private land owners and make-ready turnaround. At the end of the quarter only one easement issue remained, so construction will not be impeded by easements as it has in the past quarter. Construction team not concerned with slow down, as additional construction crews can be quickly brought to bear, if needed. | None expected.
NT10BIX5570066 | 2013 | Q2 | Q2 - 2013 | BVU requested and was granted an extension to September 30, 2013 to place additional distribution equipment on the previously built fiber routes. This will extend current project by one quarter. During Q2-2013, BVU Authority continued with building out routes, which included construction and limited engineering activities, as well as receiving and deploying materials. Construction is progressing well with approximately 98.95% of the projected fiber miles have been buried or put up aerially. Currently, BVU Authority has finished and spliced 19 routes and are working on finishing an additional 11 routes. Of these remaining routes, 7 have completed the fiber build out, but are waiting final splicing of the fiber. The other 4 routes are near completion for the fiber build out, less than 1.0 miles for per route. As of the end of the quarter, approximately 365.2 miles were constructed of the engineered 369.12 miles. Please note that due to more mileage being able to be placed aerially than buried, actual engineered mileage came to 369.12 miles, instead of the original estimate of 388.0 miles. BVU had encountered unexpected issues with obtaining easements from private enterprises and vendor make-ready turnaround that caused a slowdown in build out rate, however, all issues have been addressed and no hurdles to build remain. In Q2-2013, BVU made 10 draw downs equaling $848,594.10 to pay for such allowed expenses as contracted project management, payroll, compliance and mapping costs, engineering, materials, and construction. | 365 | 0 | 0 | 0 | 365 | 0 | 0 | 19 | Fiber built out complete. Waiting for some of the routes to be spliced and lit. | N/A | N/A | N/A | Fiber built out complete. Waiting for some of the routes to be spliced and lit. | N/A | N/A | Five additional routes (interconnection points) completed this quarter. 11 routes waiting for final splicing. | 1 | 0 | 0 | Virginia Department of Transportation (VDOT). We provide 12 strands of dark fiber in exchange for right-of-way access, in perpetuity. | The 9 available tiers via wholesale are as follows: (1) 10 Mbps; (2) 50 Mbps; (3) 100 Mbps; (4) 200 Mbps; (5) 400 Mbps; (6) 1000 Mbps; (7) 2.5 Gbps; (8) 10 Gbps; (9) OC-3 Sonet We are providing dark fiber access to the Virginia Department of Transportation at no cost in exchange for right-of-way access. Wholesale prices listed in initial reports. | N/A | 0 | 0 | 1 | 0 | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | Available tiers via wholesale are as follows (# subs): 10 Mbps (0); 50 Mbps (0); 100 Mbps (0); 200 Mbps (0); 400 Mbps (0); 1000 Mbps (0); 2.5 Gbps (0); 10 Gbps (0); OC-3 Sonet (0) | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide lease of dark fiber for two routes in exchange for use of VDOT ROW. | FALSE | N/A | Since the next quarter is the last quarter of the project, BVU plans on finishing all construction related tasks and installation of distribution cabinets and NAP's. | BVU Authority | No issues encountered in quarter, except for running into hard rock for 1.5 miles of buried fiber. Decision has been made to re-engineer and go aerial instead. | None expected.
NT10BIX5570066 | 2013 | Q3 | Q3 - 2013 | During Q3-2013, BVU Authority completed project on schedule and within budget. BVU Authority's Southwest Virginia Middle Mile Project consists of backbone fiber additions to its existing network that brings up to 10 Gigabits per second middle mile service to a rural, nine county region of southwestern Appalachian Virginia. Seven of the nine targeted counties qualify as economically distressed, with per-capita incomes that are 80 percent or less of the national average. All nine counties lack adequate broadband services throughout the county. Project accomplishments include: (1) 370 miles of fiber build out and lit (2) Fiber installed on 30 individual fiber routes constructed throughout the nine counties (3) 49 last mile distribution cabinets installed; and (4) 567 last mile network access points (NAPs) installed. Cabinets and NAP's were installed to incent and assist with providing last mile connectivity. This allows BVU Authority and other last mile providers additional interconnection facilities throughout the network for access to any community along the 30 routes. The completed Broadband Technology Opportunities Program middle mile infrastructure now brings the opportunity for fiber optic, high capacity broadband to approximately 11,400 households, businesses, hospitals, schools, libraries, government entities, and other Community Anchor Institutions in the nine Southwest Virginia counties. Even though the project was a middle mile project, BVU Authority, through its own resources, continues to work to establish last-mile connections to the communities situated along the middle mile routes. BVU Authority considers 5,300 of the possible connections to be "on-route" meaning that the establishment is within 1/2 mile of the middle mile fiber backbone and will utilize a fiber-to-the-premise (FTTP) connection capable of delivering broadband speeds of 20 Mbps. The remaining 6,100 possible connections are deemed "off-route" due to being located greater than 1/2 mile from the fiber backbone and will connect using a wireless broadband technology capable of delivering broadband speeds of 5 Mbps. In BVU Authorityâ€™s approved Fiscal Year 2014 capital project budget (July 1, 2013 â€“ June 30, 2014) , BVU Authority had appropriated $450,000 to reach approximately an additional on-route 450 entities (households, businesses, and Community Anchor Institutions) with last mile connectivity and is on target to meet this goal. BVU Authority's intention is to continue to appropriate approximately $450,000 per annum to continue last-mile connections. BVU Authority will diligently continue in its efforts to find additional capital resources (e.g. Virginia Tobacco Commission, State and Federal government programs) to connect additional households, businesses, or Community Anchor Institutions in the upcoming fiscal cycles. BVU Authority is also actively looking to create relationships with wireless broadband vendors to assist in providing the wireless off-route connections. Also, in an agreement for use of Virginia Department of Transportation's Rights-of-Way for fiber build-out, BVU Authority has agreed to provide the Virginia Department of Transportation access to 12 dark fibers over two routes encompassing 15.7 miles (188 strand-miles), in perpetuity. | 370 | 0 | 0 | 0 | 370 | 0 | 0 | 30 | Original baseline of 388 miles was based on driving miles and expected mileage that would be aerial and what mileage would be buried. After completion of engineering, minor variances were encountered due to need to go aerial in some areas expected to be buried due to hard rock found. Other variances were due to being able to more specifically measure mileage built out versus driving miles. | N/A | N/A | N/A | Original baseline of 388 miles was based on driving miles and expected mileage that would be aerial and what mileage would be buried. After completion of engineering, minor variances were encountered due to need to go aerial in some areas expected to be buried due to hard rock found. Other variances were due to being able to more specifically measure mileage built out versus driving miles. | N/A | N/A | Eleven additional routes (interconnection points) completed this quarter bringing total to thirty. Original application/baseline indicated 31 interconnection points, but one route was dropped due to overlap with another Broadband Technology Opportunities Program project in Russell County. Recap: County Routes Buchanan 4 Bland 1 Dickenson 3 Russell 6 Scott 1 Smyth 2 Tazewell 4 Washington 8 Wythe 1 | 1 | 0 | 0 | Virginia Department of Transportation. BVU Authority provided 12 fibers over two routes encompassing 15.7 miles (188 strand-miles) of dark fiber in exchange for Rights-of-Way access, in perpetuity. | The current available wholesale tiers are as follows: (1) 10 Megabits per second; (2) 20 Megabits per second; (3) 50 Megabits per second; (4) 100 Megabits per second; (5) 200 Megabits per second; (6) 500 Megabits per second; (7) 1000 Megabits per second; Higher speeds (e.g. 2.5 Gigabits per second) are available per individual quotes due to multiple factors | N/A | 0 | 0 | 1 | 7 | BVU Authority will continue to support other third-party last-mile providers to bring services to communities along the middle mile routes. | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide access to 12 dark fibers over two routes encompassing 15.7 miles (188 strand-miles) in exchange for use of Virginia Department of Transportation Rights-of-Way, in perpetuity. | The current available wholesale tiers are as follows: (1) 10 Megabits per second; 0 subscribers (2) 20 Megabits per second; 0 subscribers (3) 50 Megabits per second; 0 subscribers (4) 100 Megabits per second; 0 subscribers (5) 200 Megabits per second; 0 subscribers (6) 500 Megabits per second; 0 subscribers (7) 1000 Megabits per second; 0 subscribers Higher speeds (e.g. 2.5 Gigabits per second) are available per individual quotes due to multiple factors | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | BVU Authority has an Memo of Understanding with the Virginia Department of Transportation to provide access to 12 dark fibers over two routes encompassing 15.7 miles (188 strand-miles) in exchange for use of Virginia Department of Transportation Rights-of-Way. | FALSE | N/A | BVU Authority, through its own resources, will continue to work to establish last-mile connections to the 11,400 households, businesses, hospitals, schools, libraries, government entities, and other Community Anchor Institutions situated along the middle mile routes. BVU Authority considers 5,300 of the possible connections to be "on-route" meaning that the establishment is within 1/2 mile of the middle mile fiber backbone and will utilize a fiber-to-the-premise (FTTP) connection capable of delivering broadband speeds of 20 Mbps. The remaining 6,100 possible connections are deemed "off-route" due to being located greater than 1/2 mile from the fiber backbone and will connect using a wireless broadband technology capable of delivering broadband speeds of 5 Mbps. Even though the project was a middle mile project, BVU Authority will continue to work to establish last-mile connections to the communities situated along the middle mile routes. BVU Authority's goal is to appropriate approximately $450,000 per annum to continue last-mile connections. BVU Authority will diligently continue in its efforts to find other capital resources (e.g. Virginia Tobacco Commission, State and Federal government programs) to connect additional households, businesses, or Community Anchor Institutions in the upcoming fiscal cycles. BVU Authority is also actively looking to partner with technology partners to assist with last-mile connections, such as wireless WiFi networks. BVU Authority will continue to support other third-party last-mile providers to bring services to communities along the middle mile routes. BVU has existing agreements with various providers for their use of BVU Authority's fiber network to deliver services. BVU Authority continues to work with these providers and other known providers in the region to provide services to areas along the middle-mile fiber routes as requested. | BVU Authority | No issues encountered affecting completion. | N/A
NT10BIX5570067 | 2010 | Q4 | Q4 - 2010 | OVERALL PROJECT - program progressed as per schedule, with major milestones met on time ENVIRONMENTAL ASSESSMENT - draft was completed by 12/31/10, and scheduled to be filed on 01/01/2011 NETWORK DESIGN - preliminary designs were completed on schedule, however at a cost over budget due to need to accelerate to meet the EA schedule CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - by qtr end began to file for "make ready engineering" work with utility pole owners. Need utility companies to conduct their engineering, then can commence make ready work post-EA approval SITE PREPARATION - not started, pending EA approval EQUIPMENT PROCUREMENT - core network backbone equipment orders and related materials were all issued; first shipments arrived in December NETWORK BUILD & EQUIPMENT DEPLOYMENT- no funds were expended on network build out (to commence after EA approval) EQUIPMENT DEPLOYMENT - no funds were expended on deploying into operations equipment which had been procured (Post-EA approval work) NETWORK TESTING - no progress, dependent on network build & equipment deployment (i.e., post-EA approval work) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | construction not started (dependency on EA approval for federal funds). | construction not started (dependency on EA approval) | construction not started (dependency on EA approval) | no new leases occurred, as per the instructions | construction not started (dependency on EA approval) | n/a | n/a | construction not started (FONSI received 3-16I received 3-16) | 0 | 0 | 0 | None at this time; we have been focusing on construction launch activities, primarily EA completion. | None at this time | Not applicable. OneCommunity operates a 900 mile network in NE Ohio today. This project will double the size and allow us to serve new or improve service to 796 additional community anchor institutions. | 0 | 0 | 0 | 0 | on plan | on plan | on plan | N/A at this time | 0 | 0 | 0 | 0 | n/a | n/a | n/a | N/A | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None at this time | FALSE | Not applicable. OneCommunity currently operates a 900 mile network in NE Ohio benefitting community anchor institutions ranging from hospitals and health clinics to schools and libraries to institutions of higher education. This project will allow us to double our network size and further our non-profit mission to serve community anchor institutions as one means to help communities grow and prosper through adoption of new technologies, in particular broadband. Our current network management practices of operating an open network remain in place. | OVERALL PROJECT - will progress as per plan, with construction starting up (make ready work, underground work, etc..) post-EA approval ENVIRONMENTAL ASSESSMENT - Anticipate finding of no significant impact (FONSI) during the quarter NETWORK DESIGN - Initial designs will be completed when FONSI is received. Ongoing design activities involve network programming & optimization with donated resources. CONSTRUCTION PERMITS, APPROVALS, ROW - utility company engineering and "make ready" statements will be completed for our five (5) highest priority segments. Payments will be issued post-EA approval in order to begin "make ready" work on these ring segments. All other permit requirements will be completed as well SITE PREPARATION - five (5) existing core sites will be upgraded once the FONSI is issued. EQUIPMENT PROCUREMENT & DEPLOYMENT - P.O.'s will be issued for fiber optic cable and construction materials, completing the bulk of the procurement stage; equipment deployment of network equipment will commence with the five existing core site upgrades NETWORK BUILD - will commence with "make ready" work being authorized, and underground construction starting where able. Other equipment & materials will be deployed as ring segment "make ready" is completed or underground work can commence. NETWORK TESTING - will commence with testing of upgrades to the five existing core sites. | ONECOMMUNITY | ENVIRONMENTAL ASSESSMENT - engineering costs are over budgeted amounts due to incurring excess engineering costs in order to meet a deadline of Jan 2, 2011 for our draft EA filing, 6 months post-award date. Much of the work had to be outsourced to engineering firms in order to get all the work done in time for the EA draft filing. BARRIERS TO IMPLEMENTATION - at this point include needing wage determinations from the DOL in order to complete a construction services RFP process, and completion of the NTIA environmental assessment and receipt of the "FONSI". NTIA TECHNICAL ASSISTANCE - none. | ENVIRONMENTAL ASSESSMENT COMPLETION: We are currently working with USF&W and Ohio's Historic Preservation Office (OHPO) to complete a Section 7 and Section 106 consultation, respectively. Formal requests were filed with the agencies on January 11 (acknowledged receipt date), with each agency allotted up to 30 days to respond, target of FEB 11. Allowing for incorporation of any comments taking several days, we anticipate our final submittal on or about FEB 16. This will be a challenge to have the FONSI issued by February month end. ITEMS SPECIFIC TO THIS PROJECT: in addition to the EA, a determination on (1) Davis Bacon wages for OSP work in NE Ohio, and (2) acceptance of OneCommunity's bonding policy, will allow us to complete an active RFP and select several construction firms to help with deployment beginning in April.
NT10BIX5570067 | 2011 | Q1 | Q1 - 2011 | OVERALL PROJECT - program progressed as per schedule, with major milestones met on time ENVIRONMENTAL ASSESSMENT - was completed, with receipt of the FONSI on 3-16-2011. NETWORK DESIGN - was substantially completed when the EA is submitted. We anticipate some minor design changes may be needed as we deploy the network (e.g., for environmental protection reasons, route optimization, etc...). Therefore we will continue to report this as a % complete based on effort expended versus budget. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - by qtr end filings for "make ready engineering" work with utility pole owners was underway, along with other permitting (e.g., underground permits, ODOT permits for RR and HWY crossings, etc.) On our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. SITE PREPARATION - initial hub site was prepared for move-in, post-receipt of FONSI EQUIPMENT PROCUREMENT - core network backbone equipment orders and related materials were all issued; first shipments arrived in December, and second shipments arrived during Q1 of 2011. NETWORK BUILD & EQUIPMENT DEPLOYMENT- no funds were expended on network build out, as the FONSI was received near the end of the quarter EQUIPMENT DEPLOYMENT - no funds were expended on deploying into operations equipment which had been procured, as the FONSI was received near the end of the quarter NETWORK TESTING - no progress, dependent on network build & equipmen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | construction not started (FONSI received 3-16) | construction not started (FONSI received 3-16) | construction not started (FONSI received 3-16) | no new leases occurred, as per the instructions | construction not started (FONSI received 3-16) | n/a | n/a | construction not started (FONSI received 3-16) | 0 | 1 | 0 | None had been signed as of 3/31/2011. | None at this time | Not applicable. OneCommunity operates a 900 mile network in NE Ohio today. This project will double the size and allow us to serve new or improve service to 796 additional community anchor institutions. | 0 | 0 | 0 | 0 | on plan | on plan | on plan | no speed tiers are available as we have no subscribers in this category, as per the baseline plan submitted 12/09/2010 | 0 | 0 | 0 | 0 | on plan | on plan | on plan | 50 Mbps 0 customers 100 Mbps 0 customers 250 Mbps 0 customers 500 Mbps 0 customers 1 Gbps 0 customers 10 Gbps 0 customers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None at this time | FALSE | Not applicable. OneCommunity currently operates a 900 mile network in NE Ohio benefitting community anchor institutions ranging from hospitals and health clinics to schools and libraries to institutions of higher education. This project will allow us to double our network size and further our non-profit mission to serve community anchor institutions as one means to help communities grow and prosper through adoption of new technologies, in particular broadband. Our current network management practices of operating an open network remain in place. | OVERALL PROJECT - will progress as per plan, with construction starting up (make ready work, underground work, etc..). ENVIRONMENTAL ASSESSMENT - is COMPLETE. EA work will only be initiated if a route change is required outside our proposed action area. NETWORK DESIGN - Ring segment designs will be completed. Ongoing design activities involve network programming & optimization with donated resources. CONSTRUCTION PERMITS, APPROVALS, ROW - utility company engineering and "make ready" statements will be completed for our four (4) highest priority segments. Payments will be issued in order to begin "make ready" work on these ring segments. All other permit requirements will be completed as well. NOTE: this is an area where, given current turn around times and fees, we anticipate being significantly over budgeted amounts for "make ready" work. SITE PREPARATION - five (5) existing core sites will begin the upgrade process. EQUIPMENT PROCUREMENT & DEPLOYMENT - equipment for Inside Plant (ISP) will be deployed with existing location upgrades; equipment/materials for Outside Plant (OSP) will begin with construction of the fiber optic network. NETWORK BUILD - will commence with "make ready" work being authorized, and underground construction starting where able. Other equipment & materials will be deployed as ring segment "make ready" is completed or underground work can commence. NETWORK TESTING - will commence with testing of upgrades to the five existing core sites. | ONECOMMUNITY | ENVIRONMENTAL ASSESSMENT - engineering costs are over budgeted amounts due to incurring excess engineering costs in order to meet a deadline of Jan 2, 2011 for our draft EA filing, 6 months post-award date. Much of the work had to be outsourced to engineering firms in order to get all the work done in time for the EA draft filing. The FONSI for our EA was completed during the period. BARRIERS TO IMPLEMENTATION - delays in responses to our requests for "make ready" work by incumbent utility pole owners. NTIA TECHNICAL ASSISTANCE - none. | ITEMS SPECIFIC TO THIS PROJECT: A determination on (1) Davis Bacon wages for OSP work in NE Ohio is needed to ensure the rates we submitted are adequate, as construction contracts have been bid and awarded with those rates included. In addition, we are experiencing significant delays in working with electric and telecomm utilities on getting the "make ready" completed on our first 4 priority routes. We have been exploring creative ways to work with them, such as pre-payments of make ready fees in order to expedite the review and approval process on their end, and possibly incent them to keep us near the top of the priority list.
NT10BIX5570067 | 2011 | Q2 | Q2 - 2011 | OVERALL PROJECT - program progressed as per schedule, with major milestones met on time ENVIRONMENTAL ASSESSMENT - completed in prior quarter. Environmental Protection Measures (EPM's) are now in force. NETWORK DESIGN - completed in prior quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - filings for "make ready engineering" work with utility pole owners is well underway, along with other permitting (e.g., underground permits, RR and HWY crossings). On our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. We have initiated several strategies to overcome this obstacle, including filing as a CLEC to expedite pole attach approvals by some incumbents. We have also been meeting at very high levels with First Energy (FE) operating companies, and have concurrence to treat our deployment as one project across all the operating companies in FE! SITE PREPARATION - on plan EQUIPMENT PROCUREMENT - all PO's have been issued for electronics (switches, routers), fiber optic cable, and all related construction materials. Shipments continue to arrive on schedule. NETWORK BUILD & EQUIPMENT DEPLOYMENT- both began in Q2, post-receipt of FONSI in Q1. Equipment deployments at hub sites continues on plan. Network buildout has begun, but is slower than anticipated due to make ready related issues (see above). NETWOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction began on aerial and underground work, with conduit placement UG, and strand installation where the path was clear. Total miles reflects ONLY the fiber cable deployed, which was none as of 6/30. Additional strand miles were 7.3; additional conduit miles 6.8. NOTE: Network miles are not fully deployed until the segment is complete, and the netowrk miles can pass traffic over the segment from hub to hub - i.e., not considered deployed until they are fully "lit". The strand and conduit must be in place first before fiber can be deployed. | none during period | none during period. NOTE: the upgrade of existing miles relates to our hub sites being upgraded with better electronics - switches, routers, etc.. This was completed for all EXISTING sites during the quarter, and all NEW sites will be completed in the next quarter as well. | no new leases occurred, as per the instructions. BASELINE of 196 miles is existing leases which will be upgraded as a result of hub site installations. | IN THE BASELINE: This is the accumulation of the new network miles indicator, and the existing network miles upgraded & leased indicators. This will adjust as those indicators are caught up in future quarters. | n/a | n/a | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) This was completed for all EXISTING sites during the quarter, and all NEW sites will be completed in the next quarter as well. no new leases occurred, as per the instructions. BASELINE of 196 miles is existing leases which will be upgraded as a result of hub site installations. IN THE BASELINE: This is the accumulation of the new network miles indicator, and the existing network miles upgraded & leased indicators. This will adjust as those indicators are caught up in future quarters. none during period. For existing and new hub sites, as all these sites are upgraded we will complete interconnections to various carriers at each hub site, thus getting us back "on plan"s for any variance from the baseline plan or any other relevant information) This was completed for all EXISTING sites during the quarter, and all NEW sites will be completed in the next quarter as well. no new leases occurred, as per the instructions. BASELINE of 196 miles is existing leases which will be upgraded as a result of hub site installations. IN THE BASELINE: This is the accumulation of the new network miles indicator, and the existing network miles upgraded & leased indicators. This will adjust as those indicators are caught up in future quarters. none during period. For existing and new hub sites, as all these sites are upgraded we will complete interconnections to various carriers at each hub site, thus getting us back "on plan". | 0 | 1 | 20 | NOVA TELEPHONE - - 60 month term, 1Gigabit subscription | None at this time | Not applicable. OneCommunity operates a 900 mile network in NE Ohio today. This project will double the size and allow us to serve new or improve service to 796 additional community anchor institutions. | 0 | 1 | 0 | 1 | on plan | Nova Telephone | on plan | 1 gigabit 1 service provider | 7 | 0 | 7 | 7 | We are slightly ahead of plan | on plan | slightly ahead of plan | 10 Mbps 1 (cust @ 15m) 50 Mbps 2 (cust @ 75m & 80m) 100 Mbps 2 customers 250 Mbps 0 customers 500 Mbps 0 customers 1 Gbps 2 customers 10 Gbps 0 customers | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None at this time | FALSE | Not applicable. OneCommunity currently operates a 900 mile network in NE Ohio benefitting community anchor institutions ranging from hospitals and health clinics to schools and libraries to institutions of higher education. This project will allow us to double our network size and further our non-profit mission to serve community anchor institutions as one means to help communities grow and prosper through adoption of new technologies, in particular broadband. Our current network management practices of operating an open network remain in place. | OVERALL PROJECT - will progress as per plan, with construction starting up. We are optimistic that make ready work, underground work, etc.. will be addressed, and construction will catch up to plan. Overall anticipate being 56% complete vs baseline of 48%. ENVIRONMENTAL ASSESSMENT - is COMPLETE. EA work will only be initiated if a route change is required outside our proposed action area. NETWORK DESIGN - COMPLETE. Anticipate being near 70% complete (baseline at 90%). SITE PREPARATION - will continue per plan. EQUIPMENT PROCUREMENT - will continue as per plan (71.8% vs baseline of 70%). NETWORK BUILD - will continue as per plan (12.8% vs 15% baseline) EQUIPMENT DEPLOYMENT - will continue as per plan NETWORK TESTING - will commence with testing of upgrades to existing core sites as well as new sites. | ONECOMMUNITY | ENVIRONMENTAL ASSESSMENT - engineering costs are over budgeted amounts due to incurring excess engineering costs in order to meet a deadline of Jan 2, 2011 for our draft EA filing, 6 months post-award date. Much of the work had to be outsourced to engineering firms in order to get all the work done in time for the EA draft filing. The FONSI for our EA was completed during the period. BARRIERS TO IMPLEMENTATION - delays in responses to our requests for "make ready" work by incumbent utility pole owners. NTIA TECHNICAL ASSISTANCE - none at this time | ITEMS SPECIFIC TO THIS PROJECT: A determination on (1) Davis Bacon wages for OSP work in NE Ohio is needed to ensure the rates we submitted are adequate, as construction contracts have been bid and awarded with those rates included. This could be a risk to project costs. We have gained Dept of Labor (DOL) approval on key skilled positions of communications technician and installer technician; a call is being scheduled in Q3 with the DOL to discuss an appropriate job title, description, and prevailing wage for a third role on a Telecommunications Outside Plant (OSP) construction crew. In addition, we have been exploring creative ways to work with them, such as pre-payments of make ready fees in order to expedite the review and approval process on their end, and possibly incent them to keep us near the top of the priority list. NEXT QTR MAJOR EXPENDITURES INCLUDE (amounts are incremental amts to be spent in the quarter): EQUIPMENT - electronics to complete PO's issued in DEC - $443K - fiber - $1.03 mm - construction materials $585K - CAI CPE $67k CONSTRUCTION SVCES - labor $1.5 mm - make ready, permitting, etc... $3.4 mm MATCH PROPORTIONALITY: As per the Match Proportionality approved and on file with the project, we are not in proportion at this time. This is due to much of the match coming in from third parties whose assets are under construction. Please refer to the approved proportionality waiver for additional
NT10BIX5570067 | 2011 | Q3 | Q3 - 2011 | OVERALL PROJECT - program progress is behind baseline, due to delays in "make ready" and other permitting. See comments on "Construction Permits, Approvals, Rights of Way". Remediation actions have been started to get back on track. As a result of these actions, there is no risk to the project's June 2012 milestone of being 2/3 complete in terms of funds expended, middle mile backbone segments completed, and CAI's on net. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - filings for "make ready" work with utility pole owners is underway, along with other permitting (e.g., underground permits, RR and HWY crossings). On our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. We have initiated several strategies to overcome this obstacle, including filing as a CLEC to expedite pole attach approvals by some incumbents. All permits and pole applications for 8 of our ring segments, representing approximately 55% of the total backbone miles, are in, and are finally starting to come back. We have added permitting resources to 4 other ring segments in order to have all permits in by Nov 30, 2011. This will allow us to begin constru | 35 | 2 | 498 | 230 | 37 | 0 | 0 | 79 | Ring Segment 14 (of 16) was completed, 34.7 miles, plus several rings have partial mileage completed. Baseline is at 150 miles, we are behind due to make ready. | IRU to reach CAI from BTOP backbone (Akron Univ) was secured from First Telecom. | All existing network miles upgraded with existing hub site electronics upgrades. Baseline of 808 is incorrect amount. Note that all existing hub sites will be interconnect points for one or more of the new fiber rings being built in the BTOP program. | all existing network miles LEASED have been upgraded with existing hub site electronics upgrades. Baseline of 392 was based on a lease which we terminated in Mahoning & Columbiana counties, due in part to route changes made to avoid any overlap issues in Columbiana County with another BTOP recipient. | Total of new network miles deployed and newly leased miles. 35 miles of brand new fiber have been deployed. And a 2 mile IRU was signed to reach CAI Akron University (IRU with First Telecom). These are 37 new miles and NOT any existing miles in this total. | N/A | N/A | Baseline is at 84 of 271 total. Current total is at 137 planned interconnect points, of which 79 have been established/ upgraded, with another 58 in progress. Current total is at 137 planned interconnect points, of which 79 have been established/ upgraded, with another 58 in progress. | 1 | 2 | 20 | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription NEGOTIATION - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) | None at this time | Not applicable | 0 | 1 | 0 | 1 | none | Nova Telephone | on plan | 1 Gigabit (Nova Telephone) | 151 | 121 | 30 | 151 | Includes all new and existing CAI's, including hospitals, school districts (where all locations have expanded access), libraries, higher education institutions, and local government locations as well as other community service organizations | We secured 121 new client locations to which we are providing expanded broadband capabilities at a lower costs to these community anchor institutions. | 30 existing CAI customers received upgraded access as of 9/30/2011 | 10 Mbps 22 ( incl 1cust receiving internet only service) 50 Mbps 8 100 Mbps 108 customers 250 Mbps 1 customers 500 Mbps 1 customers 1 Gbps 9 customers (1 w/1 gig port, offering 100 mbps to 102 locations) 10 Gbps 2 customers (incl dark fiber pairs) | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None at this time | FALSE | Not applicable. | OVERALL PROJECT - program progress is behind baseline, due to delays in "make ready" and other permitting. Remediation actions have been started to get back on track. We have added additional engineering resources experienced in permitting, and all permits and pole applications for all routes required for a 2/3 completion by June will be submitted by December, 2011. In addition, we have started weekly status calls with First Energy/Ohio Edison, which account for 80% of the utility poles in our footprint. We do not anticipate any risk to our June 2012 milestone of being 2/3 complete. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - filings for "make ready" work with utility pole owners for 70% of the network is targeted to be completed by end of Q4 2011, along with other permitting for underground permits, RR and HWY crossings. On our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. We have initiated several strategies to overcome this obstacle, including filing as a CLEC to expedite pole attach approvals by some incumbents. SITE PREPARATION - on plan EQUIPMENT PROCUREMENT - all PO's have been issued for electronics ( | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION - delays in responses to our requests for "make ready" work by incumbent utility pole owners. We are experiencing "above average" response times from the railroads (RR) and Ohio Dept of Transportation (ODOT) on their requests. And a number of incumbent utility pole owners are extremely responsive. However, 80% of our poles are owned by First Energy (FE) operating companies, and it has been slow going. We have established personal lines of communications with FE operating companies now, and responses are rapidly improving. The Project is estimated to be 1-2 months behind, and should make most of that up in Q4, 2011. NTIA TECHNICAL ASSISTANCE - none at this time | Items specific to this project: completion of "make ready" by utility pole owners so that permanent attachment can proceed as planned. We have had successes with ODOT permitting, and railroad permitting is being processed in a timely manner. Many utility pole owners have been quick to turn around our pole applications, including ATT, Frontier, and CenturyLink. However, 80% of our footprint involves First Energy/Ohio Edison poles, and they are running behind. During Q3 we have made good progress, and have established a weekly call with FE/OE to review progress. During Q4 our goals are: (1) for all routes required to meet the 2/3 completion target, have all permits submitted; (2) for all permits already on file as of Q3 end, have 50% or more approved and back. These goals if met will easily allow us to complete 2/3 of the project in terms of funds spent, and back bone miles deployed. BTOP Program Assistance: none at this time.
NT10BIX5570067 | 2011 | Q4 | Q4 - 2011 | OVERALL PROJECT - program progress is behind baseline, due to delays in "make ready" and other permitting. See comments on "Construction Permits, Approvals, Rights of Way". Remediation actions have been started to get back on track. As a result of these actions, there is no risk to the project's June 2012 milestone of being 2/3 complete in terms of funds expended, middle mile backbone segments completed, and CAI's on net. Anticipated completion date is June 30, 2013. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - filings for "make ready" work with utility pole owners is complete for over 80% of the network - more than enough to meet our 2/3 milestone. All other permitting for those key segments is also complete or underway (e.g., underground permits, RR and HWY crossings). On our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. The bulk of our footprint has poles belonging to Ohio Edison (OE). OE has committed to complete all make ready on 75% of our network at milestone dates of 3/31/12 and 6/1/12, which will leave us time to complete construction. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - all PO's have been issued for electronics (switches, routers), fiber optic cable, and all related construction materials. Shipments continue to arrive on schedule, with the last shipments expected in Q1 2012. NETWORK BUILD & EQUIPMENT DEPLOYMENT- both began in Q2, post-receipt of FONSI in Q1. Equipment deployments at hub sites continues on plan. Network build out has begun, but is slower than anticipated due to make ready related issues (see above). We have completed one of 14 new ring segments, and make ready and construction began or continued in the quarter on 8 other new segments. NETWORK TESTING - testing of completed ring segments continues on plan. | 73 | 1 | 498 | 230 | 74 | 0 | 0 | 71 | Network miles deployed is behind baseline due to delays with "make ready" work by incumbent pole owners. I expect to be on schedule with my baseline by Q3 2012. | First Telecom IRU purchased in October (.78 miles into Univ of Akron). Also, purchase from Conneaut Telephone of .1 miles 6 strands to reach Kingsville Medical Clinic. Prior to this, in Q3's report an IRU for 1.9 miles from Conneaut Telephone was reported, tying into the Conneaut Telephone head end. This was actually a purchase of the fiber and its related outside plant, it was NOT an IRU/lease. These are now BTOP assets (not an IRU). | all existing fiber upgrades are complete as of Q3, 2011 | all existing fiber upgrades are complete as of Q3, 2011 | Total of new network miles deployed and newly leased miles. 35 miles of brand new fiber have been deployed. | n/a | n/a | Existing and planned interconnection points change due to consolidations of interconnecting parties (e.g., Global Crossing was acquired by Level 3, etc..). Current total is at 137 planned interconnect points, of which 71 have been established/upgraded. Last quarter reported 79, and several were lost due to further consolidations. Of these, 23 were existing interconnect points. | 3 | 0 | 65 | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years | Through pre-existing wholesale arrangements, we are now offering circuits to our wholesale partners of Global Crossing, North Coast Wireless, Next Internet, Windstream KDL, Mango Bay Internet, Zito Media, ACC, and Nova Telephone. Average bandwidth they are offering on resold service is140 mbps. | Not applicable. | 3 | 7 | 3 | 1 | Ahead of plan. | All existing wholesale relationships who recently purchased a circuit for a customer of theirs off of a new ring segment | see remarks above in Question 5b for details | 1 gbps circuit 1 provider 10+ gbps/dark fiber 2 providers Avg circuit size is 250 mbps purchased by wholesale partners. | 163 | 125 | 38 | 163 | Includes all new and existing CAI's, including hospitals, school districts (where all locations have expanded access), libraries, higher education institutions, and local government locations as well as other community service organizations. | Ahead of plan | Ahead of Plan | <10 Mbps 6 customers 10-50 Mbps 28 customers 50-100 Mbps 4 customers 100 Mbps - 1 Gbps 115 customers >= 1 Gbps 10 customers | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None during Q4 were offered. | FALSE | Not applicable. | OVERALL PROJECT - weather permitting, the project will reach 50% or higher completion during Q1 2012. Remediation actions begun in Q3 and Q4 2011 with key utility pole owners are helping us to get back on track. As a result of these actions, there is no risk to the project's June 2012 milestone of being 2/3 complete in terms of funds expended, middle mile backbone segments completed, and CAI's on net. The only risk at this point is weather, which could delay "make ready" commitments by Ohio Edison and other utility pole owners. It's important to note that bad weather anywhere in the Eastern US can impact schedule (example being the snow storm of Oct, 2010 where Ohio Edison sent crews to New Jersey for 2 weeks to help out). ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - filings for "make ready" work with utility pole owners was completed for over 80% of the network in Q4, 2012. Remaining on our critical path is the utility companies' conducting their engineering and sending us a bill for the make ready work. The bulk of our footprint has poles belonging to Ohio Edison (OE). OE has committed to complete all make ready on 75% of our network at milestone dates of 3/31/12 and 6/1/12, which will leave us time to complete construction on at least 67% of the core network. Baseline is at 97%; with respect to actual work we should be nearer to 80%. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - The final shipments of fiber are due in during Q1 2012. We will have enough electronics, fiber and materials to complete the core network. Going forward purchases of equipment will involve replenishing inventories of outside plant (OSP) construction materials (bolts, etc..) and replenishing inventories of small switches deployed at customer locations as customer premise equipment (CPE). Baseline is at 80%; we will be closer to 90% NETWORK BUILD & EQUIPMENT DEPLOYMENT- Equipment deployments at hub sites continues on plan - it is largely complete, and awaiting the arrival of fiber. Network build out will begin to ramp up in Q1 2012, as OE and other utility pole owners complete their make ready work on poles. We will complete at least two of 14 new ring segments, and make ready and construction which began in Q4 2011 will continued in the quarter on 7 other new segments. Baseline is at 40% for both, and we will be at 33%. Again, weather permitting. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed (behind baseline, as construction and deployment are - baseline of 30% vs plan at 26%). | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION - delays in responses to our requests for "make ready" work by incumbent utility pole owners. We saw vast improvement in Q4 2011, with the key utility pole owner in our footprint - Ohio Edison - dedicating a team of people to engineering our routes, and committing to finish "make ready" at milestones in Q1 and Q2 which will allow us to finish construction on 2/3 of our network. At this time only weather related delays threaten progress. The delays are due to the incumbent pole owners' inability to engineer and perform make ready work in a timely manner. In this current quarter we have all poles submitted and being processed by incumbent pole owners which will allow us to reach our June 30 two thirds complete milestone. NTIA TECHNICAL ASSISTANCE - none at this time | MAKE READY - during Q4 2011 we made significant headway with Ohio Edison, and have their commitment to complete make ready on almost 50% of the network by March 31, 2012, and another 25% by June 1, 2012. If they meet these commitments, we will be able to meet our June 30, 2012 milestone of 2/3 of core network completed. WEATHER - the weather can adversely impact schedule, not only within our Project Area but anywhere in the Midwest or Eastern US. Make ready is a second priority to maintenance and outages for any utility company, including Ohio Edison. Even storms in adjacent states can cause a redeployment of resources to help out, leaving only enough local crews for maintenance work, and putting make ready on hold. CAI COUNTS - CAI counts for the quarterly PPR reports included new CAI locations that were provided service as part of larger group service agreements, some of which were serviced by third party networks in order to support the entire group. CAI locations in some of the groups include, therefore, on-net locations as well as some "offnet" locations. At the "offnet" locations, we still deploy a switch in order to monitor and manage service levels to the CAI.
NT10BIX5570067 | 2012 | Q1 | Q1 - 2012 | OVERALL PROJECT - program progress is behind baseline, due to delays in "make ready" and other permitting. See comments on "Construction Permits, Approvals, Rights of Way". Remediation actions have been started to get back on track. As a result of these actions, there is no risk to the project's June 2012 milestone of being 2/3 complete in terms of funds expended, middle mile backbone segments completed, and CAI's on net. Anticipated completion date is June 30, 2013. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready engineering" work is complete, and "make ready" work with utility pole owners is underway for over 80% of the network - more than enough to meet our 2/3 milestone. All other permitting for those key segments is also complete as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - all PO's have been issued for electronics (switches, routers), fiber optic cable, and all related construction materials. Shipments continue to arrive on schedule, with the last shipments expected in Q1 2012. NETWORK BUILD & EQUIPMENT DEPLOYMENT- both began in Q2, post-receipt of FONSI in Q1. Equipment deployments at hub sites continues on plan. Network build out has begun, but is slower than anticipated due to make ready related issues (see above). We have completed one of 14 new ring segments, and make ready and construction began or continued in the quarter on 8 other new segments. NETWORK TESTING - testing of completed ring segments continues on plan. | 265 | 1 | 498 | 230 | 266 | 0 | 0 | 71 | we are behind our baseline of 511 miles deployed due to delays in getting onto utility poles. In addition to the 265 miles of fiber, we have 263 miles of strand installed, and 24 miles of conduit. Fiber continues to be installed on this strand and in this conduit, which would bring the total to over 550 miles. This, along with continued construction, will achieve our 2/3 completion target by June 30. | We are behind the baseline of 176 because we have not leased any fiber from Medina County yet, as their network build out is behind schedule. We anticipate the Medina network will be complete, and leasing this fiber by Q4 2012. | all existing fiber upgrades are completed as of Q3, 2011. The total miles upgraded is less than the baseline, as the baseline was in error. 1C anticipates filing an AAR to correct the baseline & existing miles in the program by Q3 2012. | all existing fiber upgrades are completed as of Q3, 2011. Existing leased miles in the baseline is at 392, which did include one segment of 120 miles on an IRU which 1C abandoned, which was in another grantee's territory, and this eliminated any overlap concerns. The accurate remaining existing leased miles is 230 miles. | Total of new fiber deployed or leased. While still behind baseline, we made up significant ground with almost 200 miles of new fiber, and another 280+ ready to be installed. | n/a | n/a | Existing and planned interconnection points change due to consolidations of interconnecting parties (e.g., Global Crossing was acquired by Level 3, etc..). Current total is at 137 planned interconnect points, of which 71 have been established/upgraded. Last quarter reported 79, and several were lost due to further consolidations. Of these, 23 were existing interconnect points. | 3 | 2 | 65 | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years | Through pre-existing wholesale arrangements, we are now offering circuits to our wholesale partners of Global Crossing, North Coast Wireless, Next Internet, Windstream KDL, Mango Bay Internet, Zito Media, ACC, and Nova Telephone. Average bandwidth they are offering on resold service is140 mbps. | Not applicable. | 3 | 7 | 3 | 3 | On Plan | all existing wholesaler relationships who recently purchased a circuit from us for their customers | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years | 1 gbps circuit 1 provider 10+ gbps/dark fiber 2 providers Avg circuit size is 250 mbps purchased by wholesale partners. | 193 | 151 | 42 | 193 | Includes all new and existing CAI's, including hospitals, school districts (where all locations have expanded access), libraries, higher education institutions, and local government locations as well as other community service organizations. We are ahead of our baseline of 45 locations. | Ahead of baseline | Ahead of baseline | <10 Mbps 6 customers 10-50 Mbps 34 customers 50-100 Mbps 5 customers 100 Mbps - 1 Gbps 118 customers >= 1 Gbps 30 customers | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None offered during the quarter. | FALSE | not applicable | OVERALL PROJECT - weather permitting, the project will reach 58% completion during Q2 2012, based on total funds expended, with 58% of the TOTAL project funds having been expended, and over 2/3's of the federal funds having been expended, as per the stimulus milestone. In Q1 2012 we were able to "clear the paths", and completed 200 miles of new fiber installation, and are poised to install over 250 miles this quarter. We will reach our 2/3 milestone in both federal funds expended and miles deployed. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will either be completed or underway for up to 80% of the network during the quarter. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - Completed. We will have minor purchases to replenish inventory for construction materials and customer premise electronics. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue to accelerate through Q2 2012, as it ramped up in Q1 2012. Four of the 14 new ring segments were finished or in final acceptance as of 3/31, and construction was underway in 8 of the other sections. Baseline is at 55% for both, and we will be at 33% of budget. We currently are trending to be under budget for construction costs for the project. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed (behind baseline, as construction and deployment are - baseline of 40% vs plan at 25%). ESTIMATED MILES DEPLOYED BY 6/30: 334 additional miles ESTIMATED CAI'S CONNECTED BY 6/30: 90 additional CAI locations directly connected, including 1 additional Instructional Technology Center (ITC) which will expand bandwidth up to 100 mbps to over 100 school locations ESTIMATED NUMBER OF BB WHOLESALE/LAST MILE PROVIDER AGREEMENTS BY 6/30: 0 additional, total of 10 wholesalers with new or improved access. | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION: delays in responses to our requests for "make ready" work by incumbent utility pole owners. We saw vast improvement in Q1 2012, and have "make ready" construction underway on over 80% of the network, with our fiber construction going on in lockstep. At this time only weather related delays threaten progress. In this current quarter we have all poles submitted and being processed by incumbent pole owners which will allow us to reach our June 30 2/3's complete milestone. NTIA TECHNICAL ASSISTANCE - none at this time | MAKE READY - If the incumbents continue to meet their commitments, we will be able to meet our June 30, 2012 milestone of 2/3 of core network completed. WEATHER - the weather can adversely impact schedule, not only within our Project Area but anywhere in the Midwest or Eastern US. CAI COUNTS - CAI counts include a number of school locations which are serviced through a central organization authorized under the State of Ohio's Revised Code. These "Instructional Technology Centers" (ITC's) serve dozens of school locations. We are in the process of providing over 1 gbps bandwidth to each of 9 ITC's, who in turn will increase bandwidth to the schools, so each school has up to 100 mbps. PROGRAM INCOME: program income earned through period ending 3/31/2012 was offset by allowable expenses under the deductive method. We anticipate program income will begin to be positive in the next quarter, fueling a portion of our matching requirement. ADDITIONAL PROGRAMMATIC NOTES: ---- Overall Project Milestone - NEXT QUARTER: The Overall Project Milestone in this section lists plan to expend 58% of the overall budget by the end of next quarter. This references TOTAL funds at 58%, but the portion of FEDERAL FUNDS will exceed the 2/3 milestone goal, and will continue to stimulate the economic recovery underway in Ohio. NETWORK BUILD: Projection for next quarter is 25% complete, but this is as a percentage of BUDGET expended. Two factors are holding down % complete forecast\: invoic
NT10BIX5570067 | 2012 | Q2 | Q2 - 2012 | OVERALL PROJECT - program progress is ahead of baseline, on baseline, and behind baseline in different areas. We are ahead of baseline in our CAI connections, ON baseline for our mileages, and BEHIND baseline in our budget/spending. Spending is behind baseline of 72% at 53% due primarily to "make ready" work which has not yet been invoiced, and behind in our matching funds generation. We have met the overall program special award condition of "substantially complete" as per the Round 2 NOFA. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready" work is either underway or pending an invoice from the utility company. All other permitting for our key segments is also complete as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - is complete. Remaining equipment purchases involve CPE electronics for bringing customers on net (e.g., to ensure compatibility with customer LAN/WAN), and OSP construction materials needed to deploy fiber, which continue as needed. NETWORK BUILD & EQUIPMENT DEPLOYMENT- continue in parallel. During the quarter our push to meet our "substantially complete" SAC resulted in eight (8) of 14 ring segments being completed with respect to planned mileage to meet goals. Our overall mileage is a bit short of plan, due to shorter customer laterals required to reach the MM fiber (i.e., our MM designs were on target). NETWORK TESTING - testing of completed ring segments continues on plan. | 596 | 161 | 412 | 351 | 596 | 0 | 0 | 78 | Our baseline is at 611. We are on plan for original network build, with 476 miles of backbone and 120 miles to connect the CAI's (total of 596). | Our baseline is at 189. We have a 1.9 mile IRU into the Conneaut headend, and an IRU swap with OARnet, where we received a 155 mile wave service from Cleveland to Columbus. We also have a 4.9 mile IRU into Akron University from First Telecom | Our baseline is at 808 total miles owned (correction for the overall miles 1C owned is in process as of this report date). This is the entire amount of owned fiber 1C had prior to BTOP, which has been improved through the BTOP program | Our baseline is at 392 (correction for the overall miles 1C had under existing lease is also in process as of this report date). This is the entire amount of leased fiber 1C had prior to BTOP, which has been improved through the BTOP program | 596 new miles built. 161 new miles leased through the BTOP program as well. | N/A | N/A | baseline at 178, however, existing and planned interconnection points change due to consolidations of interconnecting parties (e.g., Global Crossing was acquired by Level 3, etc..). Current total is at 137 planned interconnect points, of which 78 have been established/upgraded. In Q4, 2011 we reported 79, and many were lost due to further consolidations. Of these, 23 were existing interconnect points. | 8 | 2 | 65 | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years In addition to the above, we had pre-existing relationships with each of these entities and now sell wholesale circuits to them, as well as the following wholesale/last mile providers: Global Crossing, North Coast Wireless, Next Internet, Mango Bay Internet, and ACC. | Through pre-existing wholesale arrangements, we are now offering circuits to our wholesale partners of Global Crossing, North Coast Wireless, Next Internet, Windstream KDL, Mango Bay Internet, Zito Media, ACC, and Nova Telephone. Average bandwidth they are offering on resold service is140 mbps. Pricing varies based on location and circuit size, and is negotiated for each wholesale customer client implementation. | Not applicable. | 3 | 5 | 3 | 8 | on plan. We have added 3 new providers since program inception. | All existing wholesaler relationships who recently purchased a circuit from us for their customers. PLEASE NOTE: the 3 providers with NEW access, plus these 5 existing wholesale providers equals the EIGHT (8) TOTAL reported in 5a above. In Q1 the PPR erroneously reported SEVEN (7) with improved service. Correct totals include 3 "new" plus 5 "improved". | - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - dark fiber provided under 2 agreements for Elyria Schools, and Ravena Schools (Note: UPN is not a wholesaler, but provides network services to schools) | 1 gbps circuit 1 provider (Nova) 10+ gbps/dark fiber 3 providers Avg circuit size is 250 mbps purchased by wholesale partners - total of 4 | 354 | 97 | 257 | 354 | Includes all new and existing CAI's, including hospitals, school districts (where all locations have expanded access), libraries, higher education institutions, and local government locations as well as other community service organizations. We are ahead of our baseline of 135 locations. | Baseline of 100, on plan | Baseline of 35. Well ahead of plan due to bringing Instructional Technology Centers (ITCs) on net with a 1 gig circuit, which enabled them to provide the state-mandated 100 mbps minimum into the schools that they serve. | <10 Mbps 7 customers 10-50 Mbps 27 customers 50-100 Mbps 5 customers 100 Mbps - 1 Gbps 271 customers >= 1 Gbps 44 customers (incl dark fiber customers) | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None offered during the quarter. | FALSE | not applicable. | OVERALL PROJECT - The project will reach 60% completion during Q3 2012, based on total funds expended. Main expenditures in Q3 will be construction invoices for the extra crews added to reach our "substantially complete" SAC, and make ready invoices still being prepared by utility pole owners. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will continue to be invoiced and paid. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - Completed. We will have minor purchases to replenish inventory for construction materials and customer premise electronics. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue through Q3 2012. For the recently completed ring segments, there may be some wrap up work. Most active construction in Q3 planned, however, is completing build outs to CAI locations which are underway. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed. PLANNED MILES FOR THE QUARTER: 70 PLANNED CAI'S WITH NEW OR IMPROVED ACCESS: 269 PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: 0 | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners. We have deployed in eight major segments to reach our "substantially complete" SAC, but still need to have make ready work invoiced before we can proceed in some areas. We do not anticipate any problems meeting overall program targets, however, by June 30, 2013. MATCHING FUNDS - we are behind on our matching funds, due to several key items in our original application match schedule which have been removed for various reasons. We are working to generate matching income in Q3, with a revised plan through June 30, 2013, which will satisfy a Corrective Action Plan issued by our Grants Officer. NTIA TECHNICAL ASSISTANCE - none at this time | Our program will be submitting an AAR for "Satisfied Special Award Condition" documenting our "substantially complete" SAC, having reached our 2 year milestone successfully. Our program'S matching fund sources have changed, and an AAR was submitted during the quarter. NTIA is currently reviewing this AAR. Program Income: Our upcoming budget modification will also include a target for Program Income earned off of new / improved customers added by/upgraded by the BTOP grant. It will formally set a target for program income, as per the July 26 Webinar presented by NTIA, and document our selection to utilize the "cost sharing method" for net program income treatment. Future quarterly reports will include the program income used as match in the FFR on line 10(j) (as per the Webinar instructions).
NT10BIX5570067 | 2012 | Q3 | Q3 - 2012 | OVERALL PROJECT - After reaching our 2/3 goal in the second quarter, we intentionally slowed down the project in some areas while we meet with NTIA and NOAA on a revised project plan for the remaining year of the grant. However, we still added 70 miles of new fiber, completing over 70% of the project, and added 15 new CAI's, bringing the total to 369, well ahead of our baseline. Spending is behind baseline of 72% at 53% due primarily to "make ready" work which has not yet been invoiced, and behind in our matching funds generation. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready" work is either underway or pending an invoice from the utility company. All other permitting for our key segments is also complete as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - is complete. Remaining equipment purchases involve CPE electronics for bringing customers on net (e.g., to ensure compatibility with customer LAN/WAN), and OSP construction materials needed to deploy fiber, which continues as needed to replenish inventory. NETWORK BUILD & EQUIPMENT DEPLOYMENT- continue in parallel. During the second quarter our push to meet our "substantially complete" SAC resulted in eight (8) of 14 ring segments being completed with respect to planned mileage to meet goals. In the 3rd quarter we completed an additional 77 miles of fiber installation, while continuing our testing and turn up of our segments completed in Q2. We are 70% complete with the program's miles, and well ahead of baseline for CAI's, and are well positioned to finish the program goals within the grant period. NETWORK TESTING - testing of completed segments continues on plan. | 673 | 161 | 412 | 351 | 673 | 0 | 0 | 78 | Our baseline is at 755, so we are a bit behind. During Q3, however, we intentionally slowed down deployments in order to reduce the overall project burn rate, while increasing our matching contributions, which resulted in improved proportionality | Our baseline is at 282. We have a 1.9 mile IRU into the Conneaut headend, and an IRU swap with OARnet, where we received a 155 mile wave service from Cleveland to Columbus. We also have a 4.9 mile IRU into Akron University from First Telecom. We are scheduled to complete 1-2 new leases in Q4, which will bring us closer to plan total of 282 | These miles constitute the fiber owned or leased by OneCommunity prior to the BTOP project, which have been "upgraded" as the electronics in our hub sites have been upgraded. Additional existing network miles upgraded will come from our sub-recipient OARnet, with their Phase 2 upgrade which is underway in Q3. We anticipate this will bring us on plan of 808 miles for the program | Our baseline is at 392 (correction for the overall miles 1C had under existing lease is also in process as of this report date). This is the entire amount of leased fiber 1C had prior to BTOP, which has been improved through the BTOP program | 673 new miles built. | NA | NA | We continue to add relationships with ISPs and wholesalers, which lead to more points of interconnection. Baseline is at 218, however, existing and planned POI's changed due to consolidations in the telecom space in particular (e.g., Global Crossing, one of our largest wholesale customers for individual circuits, was acquired by Level3, reducing the number of points commensurate with where they were collocated). | 13 | 0 | 68 | SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU. In addition to the above, we had pre-existing relationships with each of these entities and now sell wholesale circuits to them, as well as the following wholesale/last mile providers: Global Crossing, North Coast Wireless, Net X Internet, Mango Bay Internet, and ACC. During Q3 we also began relationships with other wholesalers and retailers in the area such as Time Warner Cable, Agile Networks, and Continental Broadband (formerly Expedient), and Time Warner Telecomm of Ohio. | Through pre-existing wholesale arrangements, we are now offering circuits to our wholesale partners of Global Crossing, North Coast Wireless, Next Internet, Windstream KDL, Mango Bay Internet, Zito Media, ACC, and Nova Telephone. Average bandwidth they are offering on resold service is140 mbps. Pricing varies based on location and circuit size, and is negotiated for each wholesale customer client implementation. | Not Applicable | 4 | 5 | 4 | 13 | On plan. | All existing wholesaler relationships who recently purchased a circuit from us for their customers. PLEASE NOTE: the 3 providers with NEW access, plus these 5 existing wholesale providers equals the EIGHT (8) TOTAL reported in 5a above. | - NOVA Telephone - 60 month - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - dark fiber provided under 2 agreements for Elyria Schools, and Ravena Schools (Note: UPN is not a wholesaler, but provides network services to schools) | 1 gbps circuit 1 provider (Nova) 10+ gbps/dark fiber 3 providers, 4 IRUs 250 Mbps - the avg circuit size purchased by wholesale partners - total of 8 current wholesale partners to whom we provide service. | 371 | 107 | 264 | 369 | Includes 15 new CAI's added in the quarter, including hospitals, school districts (where all locations have expanded access), libraries, higher education institutions, and local government locations as well as other community service organizations. We are ahead of our baseline of 275 locations. | Baseline of 225 new, adjusted for new CAI's which are ITC's that serve multiple school locations, which receive improved access via the ITC. NOTE: at a recent Site Visit NOAA & NTIA determined a Project File Memo will be filed in Q4 explaining the incorrect baseline metric and adjusting the baseline going forward. | Baseline of 50, ahead of plan based on treatment of schools served by ITC's. NOTE: Based on the current understanding of the definition of "improved access" vs "new access", the total CAI's re | <10 Mbps 11 customers 10-50 Mbps 54 customers 50-100 Mbps 6 customers 100 Mbps - 1 Gbps 248 customers >= 1 Gbps 44 customers (incl dark fiber customers) | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | None during the quarter. | FALSE | not applicable. | OVERALL PROJECT - The project will reach 68% completion during Q3 2012, based on total funds expended (federal & matching). Main expenditures in Q4 will be construction invoices for several large contracts with CAI's which will in turn generate program income which will be reinvested as matching funds. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will continue to be invoiced and paid fro completed middle mile segments, as well as for new CAI locations being brought "on net". SITE PREPARATION - on plan. All hub sites have had new electronics installed, and fiber installation will continue. EQUIPMENT PROCUREMENT - Completed. We will have minor purchases to replenish inventory for construction materials and customer premise electronics. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue through Q4 2012, with approximately 50 miles of middle mile being completed to wrap up our ring segments. One ring segment spanning approximately 20 miles is scheduled for Q1, 2013 (due to the slowing down the burn rate of our federal funds as we bring in more matching funds). Most active construction in Q4 planned, however, is completing build outs to CAI locations which are underway. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed. PLANNED MILES FOR THE QUARTER: 70 PLANNED CAI'S WITH NEW OR IMPROVED ACCESS: 350, with 269 improved and 81 with new fiber and access, bringing the program total to 740. PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: 0 DURING Q4 ONECOMMUNITY WILL BE SUBMITTING A BUDGET MODIFICATION TO NTIA/NOAA BASED ON THE RESULTS OF A SITE VISIT HELD IN OCTOBER. IN CONJUNCTION WITH THIS BUDGET MODIFICATION A SECOND AAR WILL BE SUBMITTED DETAILING CHANGES TO ROUTE SEGMENTS PLANNED. A NUMBER OF MILES IN THE ORIGINAL APPLICATION ARE NO LONGER NECESSARY (MAINLY TO MARCS COMMUNICATION TOWERS, WHERE THE STATE OF OHIO NO LONGER WISHES TO UPGRADE THEM). RATHER THAN WASTE THE FIBER, WE WILL DEPLOY THE MILES REACHING MORE CAI LOCATIONS. A FULL AAR WILL BE SUBMITTED IN Q4. | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners. In Q2 we deployed eight major segments to reach our "substantially complete" Special Award Condition, but still need to have make ready work invoiced before we can proceed in some areas. We do not anticipate any problems meeting overall program targets, however, by June 30, 2013. As of 9/30, approximately half of the make ready work has been invoiced and is underway. MATCHING FUNDS - we are behind on our matching funds, due to several key items in our original application match schedule which have been removed for various reasons. In Q3 we contributed over $900k in match. We are working to generate matching income in Q4 as well. This was the central topic in a Corrective Action Plan (CAP) issued in Q3, and at a recent Site Visit by NTIA and NOAA we revised plans to get back in proportionality. We anticipate filing a budget modification and a new baseline for the program in Q4 2012. NTIA TECHNICAL ASSISTANCE - none at this time | Our program completed our "Special Award Condition" for "substantially complete" SAC, having reached our 2 year milestone successfully in Q2 for federal funds expended to stimulate the economy, for total miles, and exceeded CAI benchmarks. IN Q2 our program's matching fund sources have changed, and an AAR was submitted during Quarter 2. IN Q3 NTIA and NOAA reviewed the AAR and issued a Corrective Action Plan with us. During Q3 we worked closely with NTIA and NOAA to develop the corrective action plan, which is tentatively scheduled to be implemented in Q4. This corrective action plan will involve submission of a budget modification and establishing new project baselines, both reflecting all program parameters worked out with NOAA and NTIA. In Q4 our sub-recipients are scheduled to have upgrades and other activities completed, and we will be reflecting additional matching contributions. For OARnet, we anticipate reporting their existing miles upgraded as they complete installation of new electronics funded in part through their sub-award on our grant. We also anticipate the schools they support will have improved access, up to 10 Gigabits.
NT10BIX5570067 | 2012 | Q4 | Q4 - 2012 | OVERALL PROJECT - After reaching our 2/3 goal in the second quarter, the project was intentionally slowed down while we meet with NTIA and NOAA on a revised project plan for the remaining grant period. During the quarter we completed a site visit with NTIA and NOAA, and submitted a series of AAR's to recast the last year of the program, to include a budget modification request. *** THIS PPR WILL BE REPORTED AGAINST THE NEW BUDGET **** ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready" work is either underway or pending an invoice from the utility company. All other permitting for our key segments is also complete as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. EQUIPMENT PROCUREMENT - is complete. Remaining equipment purchases involve CPE electronics for bringing customers on net (e.g., to ensure compatibility with customer LAN/WAN), and OSP construction materials needed to deploy fiber, which continues as needed to replenish inventory. NETWORK BUILD & EQUIPMENT DEPLOYMENT- continue in parallel. During the quarter we completed 111 miles of fiber build out, and five hub sites. Nine hub sites are in progress as of year end. NETWORK TESTING - testing of completed segments continues on plan. | 770 | 271 | 412 | 351 | 770 | 0 | 0 | 81 | 770 miles of new fiber has been deployed within our Project Funded Service Area as of 12-31-12. Our baseline is at 905. We are behind due to intentionally slowing down our "burn rate" to allow us more time to generate match. | Baseline is at 282. We have made all major leases anticipated in the program. We expect to find one or two more opportunities to lease fiber to extend the BTOP network as well. | These miles constitute the fiber owned or leased by OneCommunity prior to the BTOP project, which have been "upgraded" as the electronics in our hub sites have been upgraded. Additional existing network miles upgraded will come from our sub-recipient OARnet, with their Phase 2 upgrade which is underway in Q3. We anticipate this will bring us on plan of 808 miles for the program. | All existing leased fiber has been "upgraded" as new electronics were deployed in the five (5) existing hub sites. | Program total miles built. | na | na | We continue to add relationships with ISPs and wholesalers, which lead to more points of interconnection. Baseline is at 218, however, existing and planned POI's changed due to consolidations in the telecom space in particular (e.g., Global Crossing, one of our largest wholesale customers for individual circuits, was acquired by Level3, reducing the number of points commensurate with where they were collocated). UPDATED Feb 25, Agile towers added as POI's per NTIA guidance. | 14 | 1 | 60 | NOTE: The information provided here in 5a and 5b reflect services we are selling to these third parties. We had or now have relationships with the following wholesale/last mile providers: Global Crossing, North Coast Wireless, Net X Internet, Mango Bay Internet, ACC, Time Warner Cable, Agile Networks, and Continental Broadband (formerly Expedient), and Time Warner Telecomm of Ohio. We have sold to all of these entities (and have purchased from some). NEW: SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription. - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU. - ALLTEL - signed services agreement with last mile provider PENDING - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | Through pre-existing wholesale arrangements, we are now offering circuits to our wholesale partners of Global Crossing, North Coast Wireless, Next Internet, Windstream KDL, Mango Bay Internet, Zito Media, ACC, and Nova Telephone. Average bandwidth they are offering on resold service is140 mbps. Pricing varies based on location and circuit size, and is negotiated for each wholesale customer client implementation. | not applicable. | 1 | 9 | 4 | 14 | on plan | All existing wholesalers relationships have during the program purchased circuits from us for their customers. | - NOVA Telephone - 60 month - WINDSTREAM - 2 IRU agreements under negotiation (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - dark fiber provided under 2 agreements for Elyria Schools, and Ravena Schools (Note: UPN is not a wholesaler, but provides network services to schools) | 1 gbps circuit 1 provider (Nova) 10+ gbps/dark fiber 3 providers, 4 IRUs 250 Mbps - the avg circuit size purchased by wholesale partners - total of 10 current wholesale partners to whom we provide service | 481 | 142 | 339 | 481 | Baseline at 445, we are ahead of plan. | "new" access defined as fiber built to the facility | Based on CAI's that are Instructional Technology Centers (ITCs) supplying K-12 schools with 100 mbps improved access. | <10 Mbps 9 >= 10 and < 50 Mbps 39 >= 50 and < 100 Mb 8 >100 Mbps <=1 Gbps 375 >1 Gbps 50 | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None during the quarter. | FALSE | Not applicable. | OVERALL PROJECT - The project will reach 84% completion during Q1 2013, based on total funds expended (federal & matching). Main expenditures in Q1 will be construction invoices for several large contracts with CAI's which will in turn generate program income which will be reinvested as matching funds. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will continue to be invoiced and paid fro completed middle mile segments, as well as for new CAI locations being brought "on net". SITE PREPARATION - on plan. All hub sites have had new electronics installed, and fiber installation will continue. EQUIPMENT PROCUREMENT - Completed. We will have minor purchases to replenish inventory for construction materials and customer premise electronics. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue through Q1 2013, with approximately 34 miles of new middle mile beginning construction to tie in two ring segments. One ring segment spanning approximately 20 miles is scheduled for Q2, 2013 (due to the slowing down the burn rate of our federal funds as we bring in more matching funds). Most active construction in Q1 planned, however, is completing build outs to CAI locations which are underway. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed. PLANNED MILES FOR THE QUARTER: 119 PLANNED CAI'S WITH NEW OR IMPROVED ACCESS: 860, with 741 improved and 119 with new fiber and access, bringing the program total to 1364. PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: 1 DURING Q4 ONECOMMUNITY SUBMITTED A BUDGET MODIFICATION TO NTIA/NOAA BASED ON THE RESULTS OF A SITE VISIT HELD IN OCTOBER, 2012. IN CONJUNCTION WITH THIS BUDGET MODIFICATION ADDITIONAL AAR'S WERE FILED: ONE DETAILING CHANGES TO ROUTE SEGMENTS PLANNED (A NUMBER OF MILES IN THE ORIGINAL APPLICATION ARE NO LONGER NECESSARY); AND TWO RELATED TO CAI ADDS/DELETES AND FOR EA REVIEW OF ALL CAI LOCATIONS WHERE FIBER WAS BUILT INTO THEM. | ONECOMMUNITY | BARRIERS TO IMPLEMENTATION: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners. In Q2 2012 we deployed eight major segments to reach our "substantially complete" Special Award Condition, but still need to have make ready work invoiced before we can install permanent connections in some areas. We do not anticipate any problems meeting overall program targets by June 30, 2013. However, make ready invoicing continues to be delayed from incumbents. MATCHING FUNDS - we are behind on our matching funds, due to several key items in our original application match schedule which have been removed for various reasons. In Q4 we contributed an additional $198k in match. We are working to generate matching income in 2013 as well. This was the central topic in a Corrective Action Plan (CAP) issued in Q3, and at a Q4 Site Visit by NTIA and NOAA we revised plans to get back in proportionality. A budget modification was filed and is the new baseline for the program in Q4 2012 and through the remainder of the grant period. NTIA TECHNICAL ASSISTANCE - none at this time. | In Q4 we conducted a series of meetings with NTIA and NOAA personnel, and developed a revised budget reflecting new match requirements. During Q1 2013 we will continue to generate match and invest in the program. The quarter goal is to be at or above 20% proportionality. This may necessitate a continued slowdown of grant fund withdrawals. In Q1 our sub-recipients are scheduled to have upgrades and other activities completed, and we will be reflecting additional matching contributions. For OARnet, we anticipate reporting their existing miles upgraded as they complete installation of new electronics funded in part through their sub-award on our grant. This will put us at plan for existing miles upgraded. We also anticipate the schools they support will have improved access, up to 10 Gigabits.
NT10BIX5570067 | 2013 | Q1 | Q1 - 2013 | OVERALL PROJECT - Project is proceeding according to plan, based on revised budget approved in Q1 2013. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready" work is either underway or pending an invoice from the utility company. All other permits for our backbone and active CAI middle mile lateral build outs have also been filed or complete as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. Five of 17 hub sites have been completed, including installation of new fiber if/as applicable. EQUIPMENT PROCUREMENT - is complete. Remaining equipment purchases involve CPE electronics for bringing customers on net (e.g., to ensure compatibility with customer LAN/WAN), and OSP construction materials needed to deploy fiber, which continues as needed to replenish inventory. NETWORK BUILD & EQUIPMENT DEPLOYMENT- continue in parallel. During the quarter our total fiber deployed reached 879.1 miles. NETWORK TESTING - testing of completed segments continues on plan. | 879 | 171 | 432 | 351 | 879 | 0 | 0 | 132 | 879 miles of new fiber has been deployed within our Project Funded Service Area as of 03-31-13. Our baseline is at 956. We are behind due to intentionally slowing down our "burn rate" to allow us more time to generate match. However, we plan to reach or exceed out KPI of 956 in Q2. | Baseline is at 282. This 171 miles currently includes 155 miles obtained in a swap with our sub-recipient, the Ohio Academic Research Network OARnet. We have an IRU in progress with Medina County. This total does not include fiber being obtained from an IRU with Medina County, which will add 151 miles to the total, and complete this KPI. In Q4 2012, we reported 271 miles of fiber, which erroneously included a portion of the planned fiber lease from Medina. | These 432 miles constitute the fiber owned by OneCommunity prior to the BTOP project, which have been "upgraded" as the electronics in our hub sites have been upgraded. Our baseline is at 808. Additional existing network miles upgraded will come from our sub-recipient OARnet, with their Phase 2 upgrade which began in Q3, 2012 and will be completed in Q2, 2013. We anticipate this will bring us closer to baseline plan of 808 miles for the program. | All existing leased fiber has been "upgraded" as new electronics were deployed in the five (5) existing hub sites. This is the total, so the KPI target should be 351 versus original KPI target of 392 | program total miles as of 3/31/2013. | n/a | n/a | We continue to add relationships with ISPs and wholesalers, which lead to more points of interconnection. Baseline is at 218, however, existing and planned POI's changed due to consolidations in the telecom space in particular (e.g., Global Crossing, one of our largest wholesale customers for individual circuits, was acquired by Level3, reducing the number of points commensurate with where they were collocated). | 15 | 0 | 68 | NOTE: The information provided here in 5a and 5b reflect services we are selling to these third parties. We had or now have relationships with the following wholesale/last mile providers: Global Crossing/Level 3 (existing/improved) North Coast Wireless (existing/improved) NetX Internet (new) Windstream KDL (existing/improved) Mango Bay Internet (new) Zito Media (existing/improved) ACC (new) Time Warner Cable (existing/improved) Agile Networks (new) Continental Broadband (existing/improved) Time Warner Telecom of Ohio (existing/improved) United Private Networks (new) Alltel Wireless (new) Cox Communications (new) Fidelity Access Networks (new) | Through pre-existing wholesale arrangements, we are now offering ethernet access (circuits) to our wholesale partners on primarily a "lit" services basis from 10 Mbps up to 40,000 Mbps. We also offer Internet services at a price per Mbps depending on ethernet access purchased, speed, and term of contract. We offer these Ethernet Access and Internet services on a wholesale basis, under our Master Services Agreement on file with the state of Ohio. Please refer to a copy of our MSA pricing filed with the State of Ohio, attached to this report. | Not applicable. | 7 | 8 | 4 | 15 | Baseline is at 5. 7 providers have signed new agreements (see Question 5b). | All existing wholesaler relationships have purchased circuits for their customers, from us under the program. | 4 parties have executed agreements for dark fiber | 1 provider (Nova) 1 gbps circuit 4 providers, 5 IRUs 10+ gbps/dark fiber 10 providers - have purchased wholesale at various levels and prices, averaging 250 Mbps, across a range of wholesale ethernet access services ranging from 10 Mbps to 1 Gbps. | 580 | 188 | 392 | 580 | Includes all CAI's only, receiving "new" service & improved service. Baseline is at 630, we are a bit behind plan. However, we anticipate being at 796 by the end of Q2, 2013. | "new" access defined as fiber built to the facility. CURRENT KPI PLAN IS FOR 215 | Based on CAI's that are Instructional Technology Centers serving multiple K-12 schools with up to 100 mbps access. CURRENT KPI PLAN IS FOR 581. | < 10 Mb 21 >= 10 Mb and < 50 Mb 65 >= 50 Mb and < 100 Mb 16 >= 100 Mb and < 1 Gb 417 >= 1 Gb 61 | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None. | FALSE | Not applicable. | OVERALL PROJECT - The project will reach 89% completion during Q2 2013, based on total funds expended (federal & matching) against the revised budget. Main expenditures in Q2 will be construction invoices for several large contracts with CAI's which will in turn generate program income which will be reinvested as matching funds, as well as "make ready" expenses. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction on an "as needed" basis. NETWORK DESIGN - Initially completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. We will be at 80% of our revised budget by the end of the quarter. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will continue to be invoiced and paid for completed middle mile segments, as well as for new CAI locations being brought "on net". we will be at 83% of budget by 6/30. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and fiber installation will continue, with all pure "middle mile" fiber expected to be completed in all hubs by 6/30/2013. EQUIPMENT PROCUREMENT - Is planned to be complete during the quarter. Remaining budget will cover minor purchases to replenish inventory for construction materials and customer premise electronics. All remaining equipment invoices are expected in during Q2 2013. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue through Q2 2013, with approximately 34 miles of new middle mile beginning construction to tie in two ring segments. One ring segment spanning approximately 20 miles is scheduled for Q2, 2013 (due to the slowing down the burn rate of our federal funds as we bring in more matching funds). Most active construction in Q2 planned, however, is completing build outs to CAI locations which are underway. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed. PLANNED MILES FOR THE QUARTER: 100 PLANNED CAI'S WITH NEW OR IMPROVED ACCESS: 796, with 581 improved and 215 with new fiber and access. PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: 1 | ONECOMMUNITY | BARRIERS TO COMPLETION: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners. In Q2 2012 we deployed eight major segments to reach our "substantially complete" Special Award Condition, but still need to have make ready work invoiced before we can install permanent connections in some areas. MATCHING FUNDS - we are still a bit behind on our matching funds, due to several key items in our original application match schedule which have been removed for various reasons. In Q1 we contributed match to raise our overall proportion to 18.2% from 11.5% at the end of the prior quarter. By Q2 we will be above 20%, and will continue to climb towards full proportionality. In Q2 we will also be able to request an SF-270 withdrawal (in May), thus remaining in compliance with our Special Award Condition (SAC, related to minimum of 1 draw per quarter). NTIA TECHNICAL ASSISTANCE - none at this time. | In Q1 we completed a match reduction request and accompanying budget modification, as a result of a series of meetings with NTIA and NOAA personnel in Q4 2012. During Q1 2013 we generated sufficient match and investment in the program to reach over 18% proportionality. In Q2 the quarter goal is to be at or above 20% proportionality by May, and resuming of federal fund withdrawals in order to maintain compliance with our SAC. Program Income Note: We are following the "Cost-Sharing Method" for treatment of program income, and all program income earned to-date net of allowable costs has been reinvested into the program as cash match.
NT10BIX5570067 | 2013 | Q2 | Q2 - 2013 | OVERALL PROJECT - Project is proceeding according to plan, based on revised budget approved in Q1 2013, and under the "no cost extension" approved in Q2 2013. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction NETWORK DESIGN - completed in Q1-2011 quarter. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - All utility company "make ready" work is either underway or pending an invoice from the utility company. All other permits for our backbone and active CAI middle mile lateral build outs have also been completed as well. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and are awaiting the installation of the fiber. Ten of 15 planned hub sites have been completed, including installation of new fiber if/as applicable. EQUIPMENT PROCUREMENT - is complete. Remaining equipment purchases involve CPE electronics for bringing customers on net (e.g., to ensure compatibility with customer LAN/WAN), and OSP construction materials needed to deploy fiber, which continues as needed to replenish inventory. NETWORK BUILD & EQUIPMENT DEPLOYMENT- continue in parallel. During the quarter our total fiber deployed reached 981 miles. NETWORK TESTING - testing of completed segments continues on plan as does testing of middle mile laterals to CAI locations | 981 | 325 | 799 | 351 | 981 | 0 | 0 | 182 | 981 miles of new fiber have been deployed in our Project Funded Service Area, completing all core backbone segments, and connecting over 200 CAI locations with new fiber, against a baseline of 956 | 325 miles have been leased in our PFSA, against a baseline of 282. This included two major IRU's, one with regional partner Medina County, which is integral to our PFSA ring structure, and one with sub-recipient and OMMC partner OARnet, which enables us to connect to two other BTOP grantees and cover over 75% of the state of Ohio. | Sub-recipient OARnet completed the upgrade of their network within our PFSA, which has improved an additional 393 miles of existing fiber in the PFSA, serving numerous institutions of higher education and community colleges. Baseline is at 808, this completes this KPI. | All existing leased fiber has been "upgraded" as new electronics were deployed in the five (5) existing hub sites. This is the total, so the KPI target should be 351 versus original KPI target of 392 | program total miles as of 6/30/2013 | n/a | n/a | We continue to add relationships with ISPs and wholesalers, which lead to more points of interconnection. Baseline is at 271, however, existing and planned POI's changed due to consolidations in the telecom space in particular (e.g., Global Crossing, one of our largest wholesale customers for individual circuits, was acquired by Level3, reducing the number of points commensurate with where they were collocated). | 15 | 0 | 68 | NOTE: The information provided here in 5a and 5b reflect services we are selling to these third parties. We had or now have relationships with the following wholesale/last mile providers: Global Crossing/Level 3 (existing/improved) North Coast Wireless (existing/improved) NetX Internet (new) Windstream KDL (existing/improved) Mango Bay Internet (new) Zito Media (existing/improved) ACC (new) Time Warner Cable (existing/improved) Agile Networks (new) Continental Broadband (existing/improved) Time Warner Telecom of Ohio (existing/improved) United Private Networks (new) Alltel Wireless (new) Cox Communications (new) Fidelity Access Networks (new) | Through pre-existing wholesale arrangements, we are now offering ethernet access (circuits) to our wholesale partners on primarily a "lit" services basis from 10 Mbps up to 40,000 Mbps. We also offer Internet services at a price per Mbps depending on ethernet access purchased, speed, and term of contract. We offer these Ethernet Access and Internet services on a wholesale basis, under our Master Services Agreement on file with the state of Ohio. Please refer to a copy of our MSA pricing filed with the State of Ohio, attached to this report. | not applicable. | 7 | 8 | 4 | 15 | Baseline is at 5. 7 providers have signed new agreements (see Question 5b). | All existing wholesaler relationships have purchased circuits for their customers, from us under the program. | 4 parties have executed agreements for dark fiber | 1 provider (Nova) 1 gbps circuit 4 providers, 5 IRUs 10+ gbps/dark fiber 10 providers - have purchased wholesale at various levels and prices, averaging 250 Mbps, across a range of wholesale ethernet access services ranging from 10 Mbps to 1 Gbps. | 943 | 227 | 716 | 943 | Includes subscribers receiving new fiber, and those receiving improved service as a result of the BTOP program. Baseline is at 796 CAI's, so we have met this KPI. | Revised baseline set the "new" fiber mark at 215 loations, so we are ahead of plan | Revised baseline for "improved" service is at 581, so we are ahead of plan | < 10 Mb 36 >= 10 Mb and < 50 Mb 105 >= 50 Mb and < 100 Mb 18 >= 100 Mb and < 1 Gb 715 >= 1 Gb 69 | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None. | FALSE | Not applicable | OVERALL PROJECT - The project will reach 98% completion during Q3 2013, based on total funds expended (federal & matching) against the revised budget. Main expenditures in Q3 will be construction invoices as well as "make ready" expenses. ENVIRONMENTAL ASSESSMENT - completed in Q1-2011. Environmental Protection Measures (EPMs) continue to be enforced during construction on an "as needed" basis. NETWORK DESIGN - Initially completed in Q1-2011. Optimization of designs to improve routes, address EPM's or lower costs continues on an as needed basis. We will be at 100% of our revised budget by the end of the quarter. CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - "Make ready" will continue to be invoiced and paid for completed middle mile segments, as well as for new CAI locations being brought "on net". we will be at 100% of budget by 9/30. SITE PREPARATION - on plan. All hub sites have had new electronics installed, and fiber installation will continue, with all pure "middle mile" fiber expected to be completed in all hubs by 7/31/2013. EQUIPMENT PROCUREMENT - Is planned to be 100% complete during the third quarter. NETWORK BUILD & EQUIPMENT DEPLOYMENT- Network build out will continue through Q3 2013, as several laterals to CAI locations are wrapped up. NETWORK TESTING - testing of completed ring segments continues on plan, as rings are completed. PLANNED MILES FOR THE THIRD QUARTER: 20 (wrapping up CAI build outs) PLANNED CAI'S WITH NEW OR IMPROVED ACCESS IN THE QTR: another 18 CAI locations which are underway will be completed PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: 0 | ONECOMMUNITY | BARRIERS TO COMPLETION: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners. Even though we deployed to meet critical programmatic deadlines, we still need to have make ready work invoiced before we can install permanent connections in some areas. MATCHING FUNDS - we have surpassed the 20% proportionality threshold, reaching 21.1%, and continue to advance toward our target match level. NTIA TECHNICAL ASSISTANCE - The program received a "no cost extension" during the quarter; no further assistance needed at this time. | In Q1 we completed a new budget with new match proportionality, and in Q2 we have achieved over 21% proportionality (based on spending through 6/30/13). We are still working with incumbent utility pole owners to get all work done and invoiced for "make ready" for the project. As a result, in Q2 we requested and were granted a "no cost extension" until Sept 30, 2013. Program Income Note: We are following the "Cost-Sharing Method" for treatment of program income, and all program income earned to-date net of allowable costs has been reinvested into the program as cash match.
NT10BIX5570067 | 2013 | Q3 | Q3 - 2013 | OVERALL PROJECT - Project is complete. Based on revised budget approved in Q1 2013, and under the "no cost extension" approved in Q2 2013. As of 9/30/2013, the project's Award Period closed, and we met all obligations with respect to total miles, CAI's connected, and POI's established. ENVIRONMENTAL ASSESSMENT - complete NETWORK DESIGN - complete CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - As of 9/30/13, all utility company "make ready" work that had been completed was requested to be billed to OneCommunity, for final payment. We still have a material number of miles which need to be "made ready", as the incumbent pole owners simply could not get the work done in time, despite having filed many of the applications for pole attachment in some cases months ago. OneCommunity will need to bear this cost, post-grant award period. SITE PREPARATION - is complete. EQUIPMENT PROCUREMENT - is complete. NETWORK BUILD & EQUIPMENT DEPLOYMENT- is complete. NETWORK TESTING - is complete SUMMARY OF OVERALL ACCOMPLISHMENTS: Since 2003, OneCommunity's purpose has stated: "OneCommunity is working to turn Northeast Ohio into a â€œSmart Regionâ€ â€“ one that directs its resources and investment to support technological innovation, highly efficient and customer-centric public services, and a superb overall quality of life for its citizens. Technology is vital to this transformation, keyed by OneCommunityâ€™s ultra-high-speed, fiber-optic broadband network, which covers almost 2,000 miles around Northeast Ohio and provides data service for more than 2,300 public institutions such as hospitals, schools, libraries and government offices. This broadband network serves as a platform for innovation and collaboration, enabling a variety of beneficial programs and applications in health care, education, government and public safety. It is also an ideal test environment for researchers, technology companies and entrepreneurs." The ROUND 2 NOFA mirrored this long-standing mission of OneCommunity, stating, " ... the National Telecommunications and Information Administration (NTIA) with $7.2 billion to expand access to broadband services in the United States. In so doing, the Recovery Act recognizes the growing importance of access to broadband services to economic development and to the quality of life of all Americans.... The CCI category will focus on Middle Mile broadband infrastructure projects that offer new or substantially upgraded connections to community anchor institutions." MSSION ACCOMPLISHED. | 993 | 325 | 799 | 351 | 993 | 0 | 0 | 192 | 993 miles of new fiber have been deployed in the Project Funded Service Area, against the original KPI of 956 miles; in 2013 a REVISED KPI estimate of 1001 miles was provided, however this was overestimated by eight (8) miles, or 0.79% (.0079) of the total. | 325 miles have been leased in our PFSA, against a baseline of 282. This included two major IRU's, one with regional partner Medina County, which is integral to our PFSA ring structure, and one with sub-recipient and OMMC partner OARnet, which enables us to connect to two other BTOP grantees and cover over 75% of the state of Ohio. | Baseline is at 808, this completes this KPI. The 808 was a REVISED target total, estimated prior to final network mile upgrades being reported by our sub-recipients, representing an estimate of eight (8) miles off, or 1.1% (0.011) of the total | All existing leased fiber has been "upgraded" as new electronics were deployed in the five (5) existing hub sites. This is the total existing network miles leased by OneCommunity, and the KPI target was updated in Q2 to 351 versus original KPI target of 392 | Total program miles as of 9/30, installed | n/a | n/a | Baseline is at 271, however, existing and planned POI's changed due to consolidations in the telecom space in particular (e.g., Global Crossing, one of our largest wholesale customers for individual circuits, was acquired by Level3, reducing the number of points commensurate with where they were collocated). | 15 | 0 | 68 | NOTE: The information provided here in 5a and 5b reflect services we are selling to these third parties. We had or now have relationships with the following wholesale/last mile providers: Global Crossing/Level 3 (existing/improved) North Coast Wireless (existing/improved) NetX Internet (new) Windstream KDL (existing/improved) Mango Bay Internet (new) Zito Media (existing/improved) ACC (new) Time Warner Cable (existing/improved) Agile Networks (new) Continental Broadband (existing/improved) Time Warner Telecom of Ohio (existing/improved) United Private Networks (new) Alltel Wireless (new) Cox Communications (new) Fidelity Access Networks (new) | Through pre-existing wholesale arrangements, we are now offering ethernet access (circuits) to our wholesale partners on primarily a "lit" services basis from 10 Mbps up to 40,000 Mbps. We also offer Internet services at a price per Mbps depending on ethernet access purchased, speed, and term of contract. We offer these Ethernet Access and Internet services on a wholesale basis, under our Master Services Agreement on file with the state of Ohio. Please refer to a copy of our MSA pricing filed with the State of Ohio, attached to this report. | not applicable | 8 | 7 | 4 | 2 | KPI met, when coupled with providers receiving dark fiber access below. | All existing wholesaler relationships have purchased circuits for customers. No specific KPI | no specific KPI, but is included with the "new access" metric. | 1 provider 1 gbps circuit 4 providers, 5 IRUs 10+ gbps/dark fiber Providers have purchased wholesale at various levels and prices, averaging 250 Mbps, across a range of wholesale ethernet access services ranging from 10 Mbps to 1 Gbps. | 950 | 242 | 708 | 5 | KPI of 796 is met. In 2013 a revised total of 961 was provided by OneCommunity based on active builds. Eleven (11) sites were not completed by 9/30 or were reported by another BTOP recipient, and is therefore not counted; this represents an error of 1.1% (.011). | Application target of 215 exceeded | application target of 581 exceeded | 38 < 10 Mb 112 >= 10 MB and < 50 Mb 20 >=50 Mb and < 100 Mb 707 >=100 Mb and < 1 Gb 73 >= 1 Gb | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | None | FALSE | Not applicable | OVERALL PROJECT - COMPLETE ENVIRONMENTAL ASSESSMENT - COMPLETE NETWORK DESIGN - COMPLETE CONSTRUCTION PERMITS, APPROVALS, RIGHTS OF WAY - COMPLETE. "Make ready" will continue to be invoiced and paid for completed middle mile segments, as well as for new CAI locations being brought "on net". As a result of incumbent pole owners' inability to process all pole attachment requests related to multiple BTOP projects, these lingering costs must now be borne by OneCommunity. SITE PREPARATION - COMPLETE EQUIPMENT PROCUREMENT - COMPLETE NETWORK BUILD & EQUIPMENT DEPLOYMENT- COMPLETE NETWORK TESTING - COMPLETE PLANNED MILES FOR THE THIRD QUARTER: NA - Award Period Ended 9/30/2013 PLANNED CAI'S WITH NEW OR IMPROVED ACCESS IN THE QTR: NA - Award Period Ended 9/30/2013 PLANNED NEW WHOLESALE/LAST MILE PROVIDER AGREEMENTS: NA - Award Period Ended 9/30/2013 | ONECOMMUNITY | BARRIERS TO COMPLETION: NONE. The Award Period ended 9/30/13. NOTE: MAKE READY - delays in invoicing for "make ready" work by incumbent utility pole owners continues. OneCommunity is now responsible for a material amount of "make ready" which has yet to be invoiced to the company. MATCHING FUNDS - we completed the program at the 26% matching award threshold. NTIA TECHNICAL ASSISTANCE - NONE. | Program Income Note: We followed the "Cost-Sharing Method" for treatment of program income, and all program income earned to-date net of allowable costs has been reinvested into the program as match.
NT10BIX5570068 | 2010 | Q3 | Q3 - 2010 | Sent out an RFP to 3 Consultants (CHR SOLUTIONS, ARCADIS, BENCHMARK ENVIRONMENTAL CONSULTANTS) to determine their interest in providing Phase 1 Environmental Assessment services on the RGV Fiber Network. Two respondents submitted incomplete RFP's and were going to outsource the EA to another company. Benchmark provided a complete RFP and included their Statement of Work complete with pricing for the entire project. Benchmark Environmental Consultants was selected to provide the Environmental Assessment. Their SOW provided a time line for completion within the 6 month window required by NTIA. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Too early in the process | Too early in the process | Too early in the process | Too early in the process | Too early in the process | N/A | N/A | Too early in the process | 3 | 1 | 1 | Time Warner, Sprint, Cogent - All are Wholesale Agreements for Dedicated Internet Access. No middle mile agreements will be required. | Dedicated Internet Services, Transport Services, IRU (Dark Fiber) Leases. See attached Middle Mile Service Offerings and Internet Bandwidth capacity charts. | N/A | 0 | 0 | 0 | 0 | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | 0 | 0 | 0 | 0 | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | 0 | 0 | 0 | 0 | 0 | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | 0 | 0 | 0 | 0 | 0 | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | Still in EA Phase | Refer to attachment re: Middle Mile and Internet Bandwidth capacity chart. | FALSE | N/A | We should complete the Phase 1 Environmental Assessment by early January 2011. | Valley Telephone Cooperative, Inc. | So far assistance from BTOP has been acceptable. The project is moving forward and should pick up momentum after the completion of the Phase 1 Environmental Assessment. | After completion of the Phase 1 EA, we will submit permits to various local, state and federal agencies. Construction cannot start until after these permits are obtained.
NT10BIX5570068 | 2010 | Q4 | Q4 - 2010 | Completed and submitted draft of Phase 1 Environmental Assessment (Dec 22, 2010). Awaiting approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | 0 | 0 | 0 | N/A | Transport Services and Internet Bandwidth Capacity. See Pricing attachment | We operate and maintain our own network | 0 | 0 | 0 | 0 | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | 0 | 0 | 0 | 0 | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | See attachment | 0 | 0 | 0 | 0 | 0 | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | 0 | 0 | 0 | 0 | 0 | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | Awaiting EA Approval | N/A | FALSE | N/A | Hopefully, receive EA approval, then select engineering contractors to start network design. Close on properties in Brownsville, Edinburg and Weslaco Texas. Schedule meetings with anchor institutions. | Valley Telephone Cooperative, Inc. | We are still in Phase I EA portion of the plan awaiting its approval. Technical assistance is NOT REQUIRED since we are not in the technical phase of project. | The EA approval is delaying the entire project. It is doubtful our projections can be met unless EA approval is received ASAP
NT10BIX5570068 | 2011 | Q1 | Q1 - 2011 | Completed preparation of our response to EA questions from NTIA Federal Environmental Reviewer and obtained approval from USFWS, TxGLO, USACE & SHPO. We are now in the 9th month of the EA. We submitted our FINAL EA response to NTIA. We have had to get extensions on the property we are purchasing and this is due to the delays in obtaining EA approval. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction has not started | Construction has not started | Construction has not started | Construction has not started | Construction has not started | N/A | N/A | Construction has not started | 0 | 6 | 0 | NONE | See Pricing Attachment | We own and operate our own network | 0 | 0 | 0 | 0 | Working with our Legal consultant to craft IRU Agreements for wholesalers | Working with our Legal consultant to craft IRU Agreements for wholesalers | Working with our Legal consultant to craft IRU Agreements for wholesalers | Speed tiers are attached. No Subscribers | 0 | 0 | 0 | 0 | Awaiting FONSI; Construction has not started | Awaiting FONSI; Construction has not started | Awaiting FONSI; Construction has not started | Speed tiers are attached. No Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Awaiting FONSI; Construction has not started | Awaiting FONSI; Construction has not started | Awaiting FONSI; Construction has not started | Awaiting FONSI; Construction has not started | Speed tiers are attached. No Subscribers | N/A | FALSE | N/A | Obtain EA approval and FONSI. Select engineering contractor(s). Close on properties in Brownsville, Edinburg and Weslaco. Conduct engineering meetings with Participant Anchor Institutions (5) and identify needs of each. | Valley Telephone Cooperative, Inc. | The biggest issue during the last quarter was obtaining SHPO approval.This was escalated via our FPO and we ultimately received approval on 3/21/11. | The EA approval delayed the project three months. Now we are three months behind on our engineering progress. Technical assistance is not needed. We need to identify additional contractor resources that can assist with completing engineering on route segments. We will start the construction process as soon as possible. We still have to send out bids to multiple construction companies and try to shorten the bid review process.
NT10BIX5570068 | 2011 | Q2 | Q2 - 2011 | We received our FONSI on 4/8/11. We have met with all five participant anchor institutions (TSTC, STC, UTPA, UTB, & UTHSC) to review facility engineering plans. Engineering has started at all five CAI locations. We also purchased and closed on land in three locations - Brownsville, Weslaco and Edinburg. We completed the engineering design and staking in Rio Grand City. We completed the engineering drawing and 50% of staking of the Harlingen (Treasure Hills) to Brownsville (Hwy 48) middle mile route segment. We completed duct searches in Brownsville, McAllen, Edinburg and Harlingen. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction has not started | Construction has not started | Construction has not started | Construction has not started | Construction has not started | N/A | N/A | Construction has not started | 0 | 5 | 0 | XC Networks | Transport services and Internet Bandwidth services. | We own and operate our own network | 0 | 0 | 0 | 0 | Crafting IRU Agreement for Wholesale Providers | Crafting IRU Agreement for Wholesale Providers | Crafting IRU Agreement for Wholesale Providers | Speed tiers are attached, No Subscribers | 0 | 0 | 0 | 0 | In Engineering Phase | In Engineering Phase | In Engineering Phase | Speed tiers are attached, No Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Construction has not started | Construction has not started | Construction has not started | Construction has not started | Speed tiers are attached, No Subscribers | N/A | FALSE | N/A | We should complete the five participant CAI (University Campus) engineering and staking. Obtain permits and start construction on the Rio Grande City route, Harlingen to Brownsville middle mile route, and complete duct verification (sneak & peak) in Brownsville, McAllen, Harlingen and Edinburg. Complete building design and start construction in Brownsville, Weslaco and Edinburg. We are purchasing middle mile fiber in anticipation of long delivery intervals due to high fiber demand. | Valley Telephone Cooperative, Inc. | FONSI delays caused the project to lag expectations by at least two months. We are working to catch up to make up the lost time. | The EA approval delayed the project three months. Now we are three months behind in our engineering process. Technical assistance is NOT needed. We need to identify additional contractor resources that can assist with completing engineering on route segments. We will start the construction process as soon as possible. We still have to send out bids to multiple construction companies and try to shorten the bid review process.
NT10BIX5570068 | 2011 | Q3 | Q3 - 2011 | Engineering was completed in Rio Grande City. The metro route (in city) and campus routes (on the STC & UTPA campuses) were permitted and staked and are ready for construction. Construction pre-bid is scheduled for Oct. 5, 2011 and bids are due no later than noon on Oct. 21, 2011. We completed staking the middle mile route between Harlingen, San Benito and Brownsville. Permitting has been slow but this job is ready to bid as soon as permits are received. We ordered and received fiber for the Rio Grande City job. Building design started on the 3 buildings located in Brownsville, Weslaco and Edinburg. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This project was delayed due NEPA directives not authorizing engineering prior to EA approval. Rio Grande City Network miles (13.5) will be constructed by 3/31/12. Construction to start in Rio Grande City. | None | None | None | This project was delayed due NEPA directives not authorizing engineering prior to EA approval. Rio Grande City Network miles (13.5) will be constructed by 3/31/12. Construction to start in Rio Grande City. | N/A | N/A | This project was delayed due NEPA directives not authorizing engineering prior to EA approval. Rio Grande City Network miles (13.5) will be constructed by 3/31/12. Construction to start in Rio Grande City. | 0 | 5 | 0 | XC Networks | Transport Services and Internet Bandwidth Services. | We own and operate our own network | 0 | 0 | 0 | 0 | Crafting IRU Agreement for Wholesale providers. Agreements will NOT be signed until network is delivered. | Crafting IRU Agreement for Wholesale providers. Agreements will NOT be signed until network is delivered. | Crafting IRU Agreement for Wholesale providers. Agreements will NOT be signed until network is delivered. | Speed tiers are attached. No Subscribers. | 0 | 0 | 0 | 0 | In Engineering Phase. Construction has not started. | In Engineering Phase. Construction has not started. | In Engineering Phase. Construction has not started. | Speed tiers are attached. No Subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | This project was delayed due NEPA directives not authorizing engineering prior to EA approval. Rio Grande City Network miles (13.5) will be constructed by 3/31/12. Construction to start in Rio Grande City. | In Engineering Phase. Construction has not started | In Engineering Phase. Construction has not started | In Engineering Phase. Construction has not started | Speed tiers are attached. No Subscribers. | N/A | FALSE | N/A | We should complete the 5 Participant CAI (University Campus) engineering and staking. Obtain permits and start construction on the Rio Grande City Route, Harlingen-Brownsville Middle Mile Route, and Complete duct verification (Sneak & Peek) in Brownsville, McAllen, Harlingen and Edinburg. Complete Building design and start construction in Brownsville, Weslaco, & Edinburg. We are purchasing middle-mile fiber in anticipation of long delivery intervals due to high fiber demand. We have increased the number of contractors performing the duct verification in Harlingen, Brownsville, Edinburg & McAllen from 1 to 3. We are increasing the engineering contractors from 2 to 4 to complete staking and acquire permits as quickly as possible. We are working with AT&T to expedite the Capital Duct Lease Agreement. | Valley Telephone Cooperative, Inc. | Brownsville has presented a challenge. We staked the middle mile route, but the city roads are under construction and downtown is mostly concrete. It is doubtful we will be able to get construction permits. There is existing duct available very near the route we selected and we are pursuing capital dct leases from AT&T. If we receive the capital leases, this will save construction dollars and shorten the construction time frames. BTOP technical assistance is not required. | We have contracted to have an EA completed on the 3 mile route along Hwy 281. We will complete the duct assessment in Brownsville and execute a Capital Lease Agreement with AT&T in Brownsville, Harlingen, Edinburg and McAllen. We increased our engineering contractors from 2 to 4. Buildings RFP's are being sent to contractors and should be received by Mid December 2011. Multiple construction contractors are positioned to start middle mile projects as engineering is completed.
NT10BIX5570068 | 2011 | Q4 | Q4 - 2011 | Construction has started in Rio Grande City. Completed staking the middle mile route between Harlingen, San Benito and Brownsville, and permits received. Harlingen to Brownsville middle mile construction bid opening is scheduled for January 17th. Building contractor has been selected for the 3 buildings located in Brownsville, Weslaco and Edinburg. Building permits are being solicited. Construction should start no later than February 1, 2012 or as permits are recieved. Engineering is complete on the middle mile route between Brownsville, Weslaco and Hidalgo (~70 miles) and permits have been requested. Additional 2.5 mile EA is in process. Duct verification has been completed in Harlingen, Brownsville, McAllen and Edinburg. This will save time and Capital dollars. Campus routes engineered are UTHSC (Harlingen), UT Pan Am (Rio Grande City), and TSTC (Harlingen). STC (Weslaco & McAllen) pending. Fiber has been received so NO fiber delays are expected. CO and Transport equipment was ordered in anticipation of delivery delays. Installation will coincide with the building completion. | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | Rio Grande City (buried fiber under construction) | None | 1None | None | Rio Grande City (buried fiber under construction) | N/A | N/A | No new interconnection points have been completed, however, we do have a new wholesale service provider ( XC Networks) connected to an improved connection point (a spur that will connect to the new BTOP network) in Hidalgo and ultimately McAllen when the build is fully complete. As soon as the Rio Grande City new construction is completed we will have a connection point to our Hidalgo and Harlingen POP's. No other connection points exist at this time. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We own and operate our own network | 0 | 0 | 0 | 0 | The IRU Agreement is being reviewed by our Participant Anchor Institutions and Broadband Wholesalers | The IRU Agreement is being reviewed by our Participant Anchor Institutions and Broadband Wholesalers | The IRU Agreement is being reviewed by our Participant Anchor Institutions and Broadband Wholesalers | Speed tiers are attached. No Subscribers. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Construction started in Rio Grande City | Construction started in Rio Grande City | Construction started in Rio Grande City | Construction started in Rio Grande City | Speed tiers are attached. No Subscribers. | N/A | FALSE | N/A | We expect to complete 34.5 miles in the next reporting quarter. We expect to connect 2 CAI's in the next reporting quarter. We plan on signing 0 new last mile provider agreements in the next reporting quarter. Summary: Complete construction in Rio Grande City. Complete engineering of P-CAI Campuses: UTPA (Edinburg), UTB/TSC (Brownsville), STC (McAllen, Weslaco) . Obtain permits and start construction on the Harlingen-Brownsville Middle Mile Route. Complete Duct Capital Lease with AT&T for duct in Brownsville, McAllen, Harlingen and Edinburg. Complete Building Construction in Brownsville, Weslaco, & Edinburg. Put out bids for the Brownsville-Weslaco and Weslaco-Hidalgo middle mile routes. Complete supplemental EA on the 2.5 mile section between Brownsville and Hidalgo. We are negotiating wholesale agreements with 5 CAI's. | Valley Telephone Cooperative, Inc. | The City of Edinburg is slow to provide our building permit but is working with us to get this resolved. The City of Brownsville has NOT approved our original EA route in the city, but has provided route alternatives where we can utilize city alley ways (where existing facilities are today). These alley ways run parallel to our EA route and are less that 100 feet apart. Since the alley route will be directional bored there will be NO disturbance to the ground in the alleys. | [REDACTED]
NT10BIX5570068 | 2012 | Q1 | Q1 - 2012 | -Construction reached substantial completion in Rio Grande City. -Contracts were awarded for Middle Mile routes from Brownsville to Weslaco to Hidalgo. Construction work on those middle mile routes started on 3/28. -Construction of the three POP buildings located in Brownsville, Weslaco and Edinburg are near completion. -The supplemental EAs requested (2.5 miles in Progreso and Brownsville) were approved. -The capital duct lease for Brownsville, McAllen, Harlingen, and Edinburg were finalized and have been paid for. -A meeting was scheduled for 4/11 to discuss campus routes with UTPA, STC, and UTB. Region 1 will also be in attendance. -Harlingen to Brownsville route is near completion. -This reporting period this project has created 11 engineering jobs and 56 construction jobs. -In addition to the Participant Community Anchor Institutions, we have identified over 80 leads for wholesale provider agreements including schools, libraries, government facilities, medical and healthcare providers, public safety entities, utilities, telecommunications carriers, and retail businesses. -Our sales and marketing teams continue to reach out to businesses and the community to identify other entities that could benefit from the services this project will bring to our area. | 229 | 14 | 0 | 0 | 243 | 0 | 0 | 0 | Rio Grande City middle mile and six in-kind contribution routes | AT&T leased duct routes in Brownsville, Harlingen, McAllen, and Edinburg | None | None | Rio Grande City middle mile, six in-kind contribution routes, and AT&T duct lease routes | N/A | N/A | No new interconnection points have been completed, however, we do have a new wholesale service provider ( XC Networks) connected to an improved connection point (a spur that will connect to the new BTOP network) in Hidalgo and ultimately McAllen when the build is fully complete. As soon as the Rio Grande City route is connected to the UTPA and STC campuses we will have connection points to our Hidalgo and Harlingen POP's. No other connection points exist at this time. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We own and operate our own network | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | FALSE | N/A | -Completion of the Harlingen to Brownsville route (26.45 miles), Brownsville to Weslaco route (68.12 miles), and Weslaco to Hidalgo route (44.02 miles). -Connect three CAIs (Rio Grande City UTPA and STC campuses, Weslaco STC campus) -Complete engineering of UTPA (Edinburg), UTB/TSC (Brownsville), and STC (McAllen, Weslaco) CAI campuses -Complete POP building construction in Brownsville, Weslaco, and Edinburg -Start on Brownsville (8.68 miles) and Harlingen (2.43 miles) metro areas (duct route construction) -Engineer and bid (by end of June) McAllen East and McAllen West metro routes -Create 13 engineering jobs and 62 construction jobs -Continue to reach out to businesses and the community to identify other entities that could benefit from the services this project will bring to our area. -We do not expect to sign up any provider agreements in the upcoming quarter as we expect all such agreements to be executed at the completion of the project, when the network will be active and ready for service. | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED]
NT10BIX5570068 | 2012 | Q2 | Q2 - 2012 | -All fiber purchases for the project have been received -UTPA and STC campuses in Rio Grande City have been connected -Harlingen - Brownsville middle mile route was completed -Meeting was held with all Participant CAIs to confirm campus routes -11 engineering jobs and 56 construction jobs were created/maintained this quarter -Engineering for Hidalgo - McAllen (West) route was completed -Engineering for Hidalgo - McAllen (East) route was completed -Brownsville, Weslaco, and Edinburg POP buildings' construction was completed -Brownsville - Weslaco middle mile route is 97% complete (IB & WC permit issue delayed 100% completion) -Weslaco - -Brownsville middle mile route is 97% complete (IB & WC permit issue delayed 100% completion) -Equipment installation has started at POPs -Revised budget forms were prepared and submitted to account for In-Kind contribution -Our sales and marketing teams continue to reach out to businesses and the community to identify other entities that could benefit from the services this project will bring to our area | 370 | 14 | 0 | 0 | 384 | 0 | 0 | 3 | Rio Grande City, Harlingen - Brownsville, Brownsville - Weslaco, Weslaco - Hidalgo, Brownsville - Hidalgo (express route) and six in-kind contribution routes | AT&T leased duct routes in Brownsville, Harlingen, McAllen, and Edinburg | N/A | N/A | New network miles + new leased miles | N/A | N/A | South Texas College and University of Texas Pan American in Rio Grande City, University of Texas Brownsville - Raymondville Remote | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | FALSE | N/A | -Connect the Weslaco STC campus -Complete the Brownsville - Weslaco -Complete the Weslaco - Hidalgo route -Complete placement of three-wrap and fiber in duct routes in Harlingen, Brownsville, and McAllen -Start construction of the Hidalgo - McAllen (West) and Hidalgo - McAllen (East) middle mile routes -We may complete the Hidalgo - McAllen (West) middle mile route -Install equipment in POP buildings -Hold pre-construction meetings for UTHSC Brownsville, UTHSC Harlingen, UTB\TSC Brownsville, STC McAllen, and TSTC campuses -Number of miles we plan to deploy next quarter: 14 -Number of CAIs we plan to connect by the end of the next quarter: 1 -Number of broadband wholesaler/last mile provider agreements we plan to sign through June 30: 0 | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED]
NT10BIX5570068 | 2012 | Q3 | Q3 - 2012 | -TSTC was bid and pre-construction meeting was held; start date scheduled for 10/29 -RAHC was bid and pre-construction meeting was held; start date scheduled for 10/29 -Brownsville duct route construction scheduled to start 10/29 -DC plant and rectifiers were installed and tested at all POP buildings -UTB campus route confirmed and build cost quoted -STC main campus pre-construction meeting held -UTHSC construction scheduled to start 10/29 -Electronics were installed at all POP buildings -Started to identify lateral build priority and quantify build distances for non-participant CAIs NOTE: Last quarter's PPR listed leased miles in "Project Indicators: Question 4 - Number of miles of new fiber (aerial or underground)" and was therefore incorrectly reported. That milestone does not include leased fiber miles in this PPR. | 370 | 14 | 0 | 0 | 370 | 0 | 0 | 3 | Rio Grande City, Harlingen - Brownsville, Brownsville - Weslaco, Weslaco - Hidalgo, Brownsville - Hidalgo (express route) and six in-kind contribution routes | AT&T leased duct routes in Brownsville, Harlingen, McAllen, and Edinburg | N/A | N/A | New network miles (new leased miles NOT included) | N/A | N/A | South Texas College and University of Texas Pan American in Rio Grande City, University of Texas Brownsville - Raymondville Remote | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We own and operate our own network | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | FALSE | N/A | -Connect the Weslaco STC campus -Complete the Brownsville - Weslaco route (levee) -Complete the Weslaco - Hidalgo route (levee) -Start construction of the Hidalgo - McAllen (West) and Hidalgo - McAllen (East) middle mile routes -We may complete the Hidalgo - McAllen (West) middle mile route -Continue equipment installation in POP buildings -Build UTHSC campus routes -Build Harlingen RAHC route -Build UTB\TSC Brownsville route -Build STC McAllen, Weslaco, Mission routes -Build TSTC Harlingen route -Number of miles we plan to deploy next quarter: 14 -Number of CAIs we plan to connect by the end of the next quarter: 5 -Number of broadband wholesaler/last mile provider agreements we plan to sign through December 31: 0 | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED]
NT10BIX5570068 | 2012 | Q4 | Q4 - 2012 | -Built fiber network to RAHC and TSTC campuses -STC campus build confirmed, bid, and awarded -UTHSC duct was placed and fiber is ready to be pulled into the building -Meetings were held with P-CAIs and campus routes confirmed -Meeting held with TSC and UTB to discuss how the separation of the two institutions would affect dark fiber award to TSC/UTB | 370 | 14 | 0 | 0 | 370 | 0 | 0 | 3 | Rio Grande City, Harlingen - Brownsville, Brownsville - Weslaco, Weslaco - Hidalgo, Brownsville - Hidalgo (express route) and six in-kind contribution routes | AT&T leased duct routes in Brownsville, Harlingen, McAllen, and Edinburg | N/A | N/A | New network miles (new leased miles NOT included) | N/A | N/A | South Texas College and University of Texas Pan American in Rio Grande City, University of Texas Brownsville - Raymondville Remote | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We own and operate our own network | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | FALSE | N/A | -Replacement of damaged duct in the Brownsville duct route -Completion of bores through IB&WC levees (assuming permit issue is resolved) -Splice TSTC campus access and egress -Build fiber route in UTB/TSC campus (assuming close-out of Brownsville Metro route) -Build fiber rote in STC McAllen and Mission campuses (part of McAllen West route) -Build McAllen West route (assuming completion of McAllen East route) -Complete McAllen East route (assuming IB&WC permit issue is resolved) -Bring UTHSC fiber into building -Connect STC Weslaco campus to network -Connect RAHC campus to network -Complete Brownsville - Weslaco route (assuming IB&WC permit issue is resolved) -Complete Weslaco - Hidalgo route (assuming IB&WC permit issue is resolved) -Clean-up of hydrogen sulfide contamination in the Brownsville leased duct -Number of miles we plan to deploy next quarter: 14 -Number of CAIs we plan to connect by the end of the next quarter: 5 -Number of broadband wholesaler/last mile provider agreements we plan to sign through March 31: 3 | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED]
NT10BIX5570068 | 2013 | Q1 | Q1 - 2013 | -Replaced damaged duct in the Brownsville duct route -Completed bores through IB&WC levees (permit issue is resolved) -Spliced TSTC campus access and egress -Built fiber rote in STC McAllen campuses (part of McAllen West route) -Built McAllen West route -Completed McAllen East route (IB&WC permit issue is resolved) -Brought UTHSC fiber into building -Connected STC Weslaco campus to network -Connected RAHC campus to network -Completed Brownsville - Weslaco route (IB&WC permit issue is resolved) -Completed Weslaco - Hidalgo route (IB&WC permit issue is resolved) -Cleaned-up hydrogen sulfide contamination in the Brownsville leased duct -Number of miles deployed this quarter: 22 -Number of CAIs connected this quarter: 10 | 187 | 0 | 219 | 0 | 187 | 0 | 0 | 13 | Number adjusted to conform to standard reporting format | N/A | Number adjusted to conform to standard reporting format | N/A | Number adjusted to conform to standard reporting format | N/A | N/A | Only Edinburg and Brownsville sites still need to be connected | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We own and operate our own network | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | FALSE | N/A | -Finish engineering and construction of Brownsville campuses (UTB, TSC, UTHSC) -Finish engineering and construction of Edinburg campuses (UTPA, UTHSC) -Finish construction of Edinburg metro route -Install and configure electronics at POP buildings (chassis installed, just need to install cards) -Test network -Turn up network -Estimated number of miles planed for deployment: 14 -Estimated number of CAIs planed for connection: 13 -Estimated number of broadband wholesale/last mile provider agreements planned for signature: 8 | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED]
NT10BIX5570068 | 2013 | Q2 | Q2 - 2013 | Network Operations and Deployment -Finished engineering and construction of Brownsville campuses (UTB, TSC, UTHSC) -Finished engineering and construction of Edinburg campuses (UTPA, UTHSC) -Finished construction of Edinburg metro route -Installed and configured electronics at 3 new POP buildings and 4 existing POP buildings -Tested completed network (Rio Grande City, Hidalgo, McAllen, Edinburg, Weslaco, Harlinegn, Raymondville, Brownsville) As a result of network deployment progress: -A total of 200 miles of new fiber miles were deployed (13 this quarter) -A total of 219 miles of in-kind fiber miles were added (0 this quarter) -A total of 24 CAIs were connected (11 this quarter) Business Development - Our business development team continued to reach out to local community leaders, anchor institutions, and last mile providers in our service region to generate interest and to create new business opportunities - After fulfilling our initial mission to design and deploy the network and render it operational, our organization is expand it by further extending the network and generating additional business opportunities among the unserved and under-served customers in our network service region. As a result of our ongoing efforts with customer outreach and building relationships with last mile providers: -We have executed 5 contracts with 7 entities (UT Systems uses a consolidated contract for all entities in its organization) for network services -We have executed 1 contract for broadband internet service and are negotiating others -We have identified and have started to approach several CAIs and Businesses along the deployed route | 200 | 0 | 219 | 0 | 200 | 0 | 0 | 24 | New miles deployed are all-new fiber | N/A | These represent the in-kind contribution | N/A | N/A | N/A | N/A | Because TSC and UTB split into two different entities, the number of interconnection points was changed by the request of these PCAIs. The total number of dark fibers being delivered was not affected. Additionally, handholds were liberally deployed to allow for additional access by PCAIs and to connect CAIs once laterals are built. | 5 | 0 | 12 | XC Networks, Texas Southmost College (TSC), South Texas College (STC), Texas State Technical College (TSTC), University of Texas (UT Borwnsville, UT Pan American, UT Health and Science Centers) NOTE: Original reported figure of 8 contracts was reduced because of consolidated contract for UT Systems. | Transport Services & Internet Bandwidth Services | We own and operate our own network | 0 | 1 | 7 | 9 | No active subscribers at this time | No active subscribers at this time | No active subscribers at this time | Transport Services DS1 @ 1.5 Mbps DS3 @ 45 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps Dark Fiber/IRU @ 10,000 Mbps Internet Bandwidth DS1 @ 10 Mbps 10 Mbps @ 10 Mbps DS3 @ 45 Mbps 100 Mbps @ 100 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps No active subscribers at this time | 24 | 24 | 0 | 9 | Because TSC and UTB split into two different entities, the number of interconnection points was changed by the request of these PCAIs. The total number of dark fibers being delivered was not affected. Additionally, handholds were liberally deployed to allow for additional access by PCAIs and to connect CAIs once laterals are built. | Because TSC and UTB split into two different entities, the number of interconnection points was changed by the request of these PCAIs. The total number of dark fibers being delivered was not affected. Additionally, handholds were liberally deployed to allow for additional access by PCAIs and to connect CAIs once laterals are built. | N/A | Transport Services DS1 @ 1.5 Mbps DS3 @ 45 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps Dark Fiber/IRU @ 10,000 Mbps Internet Bandwidth DS1 @ 10 Mbps 10 Mbps @ 10 Mbps DS3 @ 45 Mbps 100 Mbps @ 100 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps PCAIs are being provided with dark fiber. Bandwidth available is determined by equipment deployed by each CAI. | 0 | 0 | 0 | 0 | 0 | This project does not target residential customers. | This project does not target residential customers. | This project does not target residential customers. | This project does not target residential customers. | This project does not target residential customers. | 200 | 0 | 0 | 0 | 9 | We have identified a number of potential business customers. Lateral fiber routes will need to be built to connect any interested parties. These lateral builds are being engineered and built after 06/30/2013 without the use of BTOP funds. | N/A | N/A | N/A | Transport Services DS1 @ 1.5 Mbps DS3 @ 45 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps Dark Fiber/IRU @ 10,000 Mbps Internet Bandwidth DS1 @ 10 Mbps 10 Mbps @ 10 Mbps DS3 @ 45 Mbps 100 Mbps @ 100 Mbps OC3 @ 155 Mbps OC12 @ 622 Mbps Gig-E @ 1,000 Mbps OC48 @ 2,500 Mbps OC192 @ 10,000 Mbps No active subscribers at this time | N/A | FALSE | N/A | The original project scope was reached and the project is complete. Moving forward we intend to continue to add CAI and non-CAI customers to the network. As the deployed network is over 400 miles long, and passes through multiple municipalities, there are a large number of potential subscribers to approach and offer services to. Since the laterals to connect these potential subscribers will be self-funded, we are currently in the process of establishing the best strategy to add new subscribers. We intend to use customer aggregation to reduce the per-subscriber cost of new infrastructure. | Valley Telephone Cooperative, Inc. | In the past quarter Texas Southmost College (TSC) and University of Texas - Brownsville (UTB) ended their partnership and began to operate as separate entities. This change caused several issues. One was that the locations where the entities interconnect with the network changed. This caused an overall reduction in the total number of interconnection points to 24. Despite this, we deployed handholds with fiber service loops at all originally planned locations, so that if in the future there was a renewed desire to connect the dropped sites it would be possible with minimal effort. | Although the project is now complete and all federal funds awarded have been used, we intend to continue to build out the network. At the time of the completion of the award, approximately 50% of fiber strands had been allocated to the Participant CAIs (UTPA, UTHSC, STC, TSTC, UTB, TSC). Moving forward we will be self-funding lateral connections to this network to sign up new users, both CAIs and businesses for the remaining network capacity. As lateral construction in urban areas can be very expensive, we have been identifying interested parties and trying to group them in such a way as to maximize subscribers connected while minimizing construction per subscriber.
NT10BIX5570069 | 2010 | Q4 | Q4 - 2010 | The initial Environmental Assessment Draft was submitted on 11/29/10. Subsequent to final submission revisions were requested by the Federal Program Officer. At NTIAâ€™s request a revised BTOP Baseline Report was submitted on 12/20/10. It is assumed in forward looking reporting commentary / forecasting related to use of BTOP funds that a FONSI will be issued by 2/1/11. Decorah Iowa (BTOP grant sub recipient) has completed their 28E organizational agreement and has proceeded to the formal project planning phase. High level engineering was substantially completed during the reporting period. All elements of the BTOP project have been committed to the Microsoft Project format as the basis for ongoing detailed management by the BTOP team. Discussions regarding Special Award Condition related to overlap of other federal projects were conclusive and clearance is expected in the upcoming reporting period. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from revised Baseline Plan | No variance from revised Baseline Plan | No variance from revised Baseline Plan | No variance from revised Baseline Plan | No variance from revised Baseline Plan | NA | NA | No variance from revised Baseline Plae Plan | 0 | 0 | 0 | N/A for this reporting period | N/A for this reporting period | N/A for this reporting period | 0 | 0 | 0 | 0 | No variance from revised Baseline Plan | No variance from revised Baseline Plan | No variance from revised Baseline Plan | NA For this reporting period | 0 | 0 | 0 | 0 | No new CAIâ€™s have been served because network improvements have not yet occurred. | No new CAIâ€™s have been served because network improvements have not yet occurred. | No new CAIâ€™s have been served because network improvements have not yet occurred. | NA For this reporting period | 0 | 0 | 0 | 0 | 0 | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the BTOP application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the BTOP application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the BTOP application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the BTOP application / approval process | NA For this reporting period | 0 | 0 | 0 | 0 | 0 | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the BTOP application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the BTOP application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the BTOP application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the BTOP application / approval process | NA For this reporting period | No special offerings are anticipated as of this quarterly report | FALSE | Network management practices have not changed from previous practices as of this quarterly report | The first draft Environmental Assessment was submitted one month prior to the required deadline. All NTIA requested revisions were completed and final EA Draft is on file at NTIA. It is anticipated that based on the Final EA Draft a FONSI will be issued prior to 2/1/11 releasing project funding for use. All RFPâ€™s will be released, responses received and analyzed (pending any issues related to vendor response due to Davis â€“ Bacon requirement for New IRUâ€™s) , and vendor awards made during the upcoming reporting period. Detailed engineering refinements, finalization of migration planning, and equipment staging / mobilization procedures will occur in the upcoming reporting period. Ethernet site upgrades will commence during the upcoming reporting period. Decatur County build components will be substantially completed by the end of the reporting period. It is anticipated that all Special Award Conditions will be cleared during the upcoming reporting period including the review of potential overlap with other active BIP/BTOP projects will be completed in the upcoming reporting period. Ongoing operational network interface discussions directed at long term cross usage operational agreements with Iowa Health System will occur during the upcoming reporting period. The project requires the Iowa Legislature (convening in January 2011) signoff of purchases that exceed statutory limits. This event should occur by the end of the upcoming reporting period. Sub-recipients, ha | Iowa Communications Network | Dealing with the SHPO in Iowa caused a delay and additional required effort in finalizing the EA draft. The affected area was on tribal lands and the tribal Historic Preservation Officer agreed to place archeological aspects of the project under their oversight which effectively resolved the issue. The ICN has also agreed as a component of the EA to stop construction and take appropriate mitigating action if any archeological issues are discovered during the actual construction process. This applies not only on tribal lands but in all other areas of the project as well. Requiring IRU vendors to certify that the Davis - Bacon requirement for BTOP have been met may be problematic for vendors because they consider fiber IRUâ€™s to be â€œa serviceâ€ and not a hard asset sale. There is the potential that vendor RFP response for New IRUâ€™s could be inadequate due to this requirement. | The Decatur County build component somewhat weather dependent. Assuming a normal winter (snowfall and temperature) the build should be substantially completed by the end of the reporting period. If snowfall is abnormally high or average temperatures are abnormally low it could negatively impact the project timeline by 30 â€“ 60 days. Requiring IRU vendors to certify that the Davis - Bacon requirement for BTOP have been met may be problematic for vendors because they consider fiber IRUâ€™s to be â€œa serviceâ€ and not a hard asset sale. There is the potential that vendor RFP response for New IRUâ€™s could be inadequate due to this requirement All timelines involving the release of BTOP funding assumes a FONSI will be issued by 2/1/11. A delay in funding release will create a commensurate delay in program timelines (as reported in Revised Baseline Report).
NT10BIX5570069 | 2011 | Q1 | Q1 - 2011 | During this quarter all requests for proposal and invitations to bid for equipment and circuits were written and submitted. By March 31, the majority of responses had been received and scored. The final environmental assessment was submitted and approved and a finding of no significant impact was received February 21, 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | N/A | N/A | No Variance from baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione (describe your reasons for any variance from the baseline plan or any other relevant information) | 0 | 0 | 0 | N/A for this reporting period. This does not vary from baseline. | N/A for this reporting period3 | N/A for this reporting period | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | N/A For this reporting period | 0 | 0 | 0 | 0 | No new CAIâ€™s have been served because network improvements have not yet occurred. | No new CAIâ€™s have been served because network improvements have not yet occurred. | No new CAIâ€™s have been served because network improvements have not yet occurred. | N/A for this reporting period | 0 | 0 | 0 | 0 | 0 | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented is for Sub recipients. ICN is statutorily not allowed to serve residential households and received a waiver in the Broadband Technology Opportunity Program application / approval process | N/A for this reporting period | 0 | 0 | 0 | 0 | 0 | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the Broadband Technology Opportunity Program application / approval process | Data represented in revised Baseline Plan is for Sub recipients. ICN is statutorily not allowed to serve businesses and received a waiver in the Broadband Technology Opportunity Program application / approval process | N/A for this reporting peroid | No special offerings are anticipated as of this quarterly report | FALSE | NA -Network management practices have not changed from previous practices as of this quarterly report | During the second quarter of 2011, the Iowa Communications Network will complete all engineering equipment inventory lists and begin ordering and receiving warehouse inventories. This includes network equipment from Brocade, Ciena, MLX and Rad. The ICN will also purchase and inventory consumables, define truck levels and the rolling-stock standard operating procedures. During the quarter, fiber optic Indefeasible Right of Use (IRU) contracts will be negotiated and awarded for both new circuits and DS-3 conversions. The team will also make recommendations, award purchase contracts and complete negotiations for Dense Wave Division Multiplexing (DWDM) equipment for the network core rings. Other work completed during the quarter will be to develop and establish the customer notification process. By the end of the quarter, all warehouse updates will be completed and the warehouse will be staffed. All signage and related documentation procedures will be finalized and implemented. The team will also establish an equipment return process. Aggregation switch rack configuration planning will be completed in preparation for deployment. Project management and planning will continue as engineering and technical resources are dedicated to the project. New switching equipment deployment will begin in the southwest quadrant of Iowa and the deployment of the first DWDM equipment ring will begin. Sub-recipients will have begun their Request For Proposal processes for a | Iowa Communications Network | Decatur County fiber build was be removed from the project. Originally submitted as a dark fiber service agreement, the ICN subsequently found that this type of service was not available in the project area and proposed a fiber optics construction project instead. In reviewing options for a fiber build, detailed engineering for the construction of that build revealed significant issues associated with burying fiber on the route identified, this segment of the Broadband Technology Opportunities Program project was determined to be cost prohibitive. Physical and environmental obstacles resulted in significant budget overruns on this part of the project. The Iowa Communications Network team and Broadband Technology Opportunity Program Program Staff agreed that the Community Anchor Institutes end users planned to be served by the fiber build could be more effectively served by other means. Broadband Technology Opportunities Program Program staff also informed the Iowa Communications Network team that, contrary to the budget narrative incorporated into the grant agreement, the 197 five year Indefeasible Right to Use leases could not be accounted for as capital expense and would be, therefore, categorized as operating expense. This change would have resulted in a project budget shortfall of approximately $4 million. In response, the Iowa Communications Network team proposed that the budget overruns associated with not capitalizing five-year fiber Indefeasible Right to Use | No significant challenges or issues are anticipated.
NT10BIX5570069 | 2011 | Q2 | Q2 - 2011 | During the quarter all engineering quantities of equipment and consumables were finalized and orders for the network core, aggregation and edge equipment were made as well as the completion of warehouse configuration, rolling inventory processes, labeling and signage plans and replaced equipment return processes. Installation of equipment was made at several customer sites to verify the project plan processes and to help prepare for the ramp up of installs in the next quarter. Also contracts for over 340 new fiber optic leases in the form of Indefeasible Right of Use contracts were completed and the final special award condition regarding the overlap of federally funded projects was satisfied. Finally, the Iowa Communications Network received approval from the National Telecommunications and Information Administration for changes to its plan including the removal from the project of a fiber build in Decatur County Iowa that resulted in the removal of six community anchor institutions from the overall project plan which was approved by the Grants Office. During the quarter an introduction letter was sent to 466 customers being directly affected by the Broadband Technology Opportunities Program project implementation to inform them of the project highlights, which included benefits and expected time line of the project. Rack cards have been designed and will be distributed at the Iowa State Fair, upcoming conferences, and available to the field technicians to pass out. In addit | 0 | 0 | 210 | 0 | 210 | 0 | 0 | 41 | No variance from baseline. The Decatur Country build was removed from project and baseline. | No variance from baseline | Baseline shows 456. Reduced number due to delayed start resulting from vendor issues for IRU's needed to upgrade services to CAI's but funded outside of BTOP. | No variance from baseline | Baseline shows 472. Reduced number due to delayed start resulting from vendor issues for IRU's needed to upgrade services to CAI's but funded outside of BTOP. | NA | NA | The Iowa Communication Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be enhanced through the BTOP program, these upgrades were completed using BTOP specifications rather than enhancing them now and then again upgrading several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedulek is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be enhanced through the BTOP program, these upgrades were completed using BTOP specifications rather than enhancing them now and then again upgrading several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | NA | NA | NA for this reporting period | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 301 | 37 | 266 | 0 | Baseline shows 772. Variance due to delayed start resulting from vendor issues. ICN expects to catch up in Qtr 3 of 2011 through DWDM network deployment. | Baseline shows 87. Variance due to delayed start resulting from vendor issues for IRU's needed to upgrade services to CAI's but funded outside of BTOP. ICN expects to catch up in Quarter 3 of 2011 through new equipment deployment | Baseline shows 685. Variance due to delayed start resulting from vendor issues for IRU's needed to upgrade services to CAI's but funded outside of BTOP. ICN expects to catch up in Quarter 3 of 2011 through DWDM network deployment. | End users have access to various network services with speeds up to100Mbs. Offering does not include speed tiers. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No special offerings are anticipated as of this quarterly report | FALSE | NA -Network management practices have not changed from previous practices as of this quarterly report | During the next quarter the Iowa Communications Network will complete installation of a complete Dense Wave Division Multiplexing (DWDM) ring. This upgrade will improve service and add functionality to hundreds of community anchor institutions. Additionally, equipment installations in the northwest quadrant of Iowa will be started. The ICN will work closely with IRU vendors to establish new fiber optics connectivity at existing and new locations. An email survey will be conducted as a means to both communicate to and receive information from customers regarding their needs and what they should expect. The ICN will be reaching out to customers and interested parties at the Iowa State Fair in August. Also during the quarter new engineers and field technicians will be added to the project staff in order to ramp up for deployment operations. Sub-recipients in Decorah and on the Meskwaki Settlement will continue with engineering and network planning making progress in anticipation of construction beginning at the start of the calendar year. | Iowa Communications Network | Challenges faced by during the quarter revolve around vendors. Resolving differences between the baseline plan and what vendors are willing to agree to has resulted in the variances noted above. At this point, the majority of these issues have been resolved but have resulted in delays to the overall project. The ICN expects the project to be 67% complete within two years and 100% complete in three years from award. | No significant challenges or issues are anticipated.
NT10BIX5570069 | 2011 | Q3 | Q3 - 2011 | The Iowa Communications Network continued to make significant progress during the third quarter of 2011. Most significantly, the first of five upgraded dense wave division multiplexing ring upgrades was completed. In order to complete the first ring, switching equipment, routers, wave division multiplexing equipment and dense wave division multiplexing equipment purchased in the second quarter was deployed and installed. This resulted in the opportunity for improved service for 785 additional community anchor institutions in the Iowa Communications Network Broadband Opportunities Program project area. Also during this quarter three full time engineers were added to the project. These staff members have begun engineering sites to be installed as part of the program in the coming months. As of the end of the September, approximately 20 sites had been engineered. Engineering is also under way for the installation of 340 new fiber optic leases in the form of indefeasible right of use contracts. The Iowa Communications Network also issued a request for proposals for field installation services. The responses to the request have been scored and a vendor has been chosen. End-point site installations are expected to begin in October. During the third quarter of 2011, the Iowa Communication Network engaged in Network Broadband Opportunities Program outreach at the Iowa State Fair increasing awareness of the program among the thousands of visitors. The program sub-recipi | 0 | 0 | 779 | 0 | 0 | 0 | 0 | 41 | No variance from baseline. The ICN expects to have new miles deployed by the second quarter of 2012. | Baseline shows 12. Variance due to extended negotiations with IRU providers. | Baseline shows 867. Variance due to changes in project sequence due to engineering issues and misestimation in baseline report. | No variance from baseline. | Baseline shows 1083. Variance due to delays in adding new leased fiber due to RFP negotiations time-line expansion in second quarter of 2011. The ICN has completed all negotiations for conversions of DS3s and establishing new IRUs. New fiber should be on baseline estimates by the end of the second quarter 2012. | NA | NA | The Iowa Communication Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through the BTOP program, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedulek is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through the BTOP program, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 1088 | 146 | 942 | 0 | Baseline shows 874. Variance due under estimation in baseline. | Baseline shows 131. Variance due under estimation in baseline. | Baseline shows 743. Variance due under estimation in baseline. | End users have access to various network services with speeds up to100Mbs. Offering does not include speed tiers. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No special offerings are anticipated as of this quarterly report. | FALSE | NA -Network management practices have not changed from previous practices as of this quarterly report. | During the next quarter the Iowa Communications Network will complete installation of two additional complete Dense Wave Division Multiplexing (DWDM) rings. These upgrade will improve service and add functionality to hundreds of community anchor institutions. Additionally, equipment installations in the northwest quadrant of Iowa will be started. Also during this quarter the ICN will begin daily upgrades of equipment at end points through-out the Northwest quarter of the state. New IRUs will also be added to the network in existing and new locations. About 14 miles of new fiber is expected to be leased. Consistent with the Baseline Report, no new network miles are expected to be deployed. Sub-recipients in Decorah and on the Meskwaki Settlement will issue requests for proposals to secure construction contracts for their portions of the project. The ICN expects to have a cumulative total of approximately 1800 CAIs with new or improved service at the end of the quarter. | Iowa Communications Network | No significant challenges or issues were encountered during the quarter. | No significant challenges or issues are anticipated.
NT10BIX5570069 | 2011 | Q4 | Q4 - 2011 | The Iowa Communications Network made significant progress during the fourth quarter of 2011. Most significantly, the remaining dense wave division multiplexing ring upgrades were completed making a total of six rings activated. In order to complete these ring upgrades, switching equipment, routers, wave division multiplexing equipment and dense wave division multiplexing equipment purchased in the second quarter was deployed and installed. Also during this period, four field installation technicians were added to the staff. These staff members have begun conducting installations of edge routers at end user sites. At the end of the quarter, approximately 40 site installations had been completed. Engineering began for 340 new fiber optic leases in the form of indefeasible right of use contracts. Several of these circuits have been delivered and it is expected that the vast majority will be completed during calendar year 2012. The program sub-recipient in Decorah posted request for proposals for construction of network engineered during the last quarter and is prepared to accept bids. The Sac and Fox sub-recipient completed engineering on its portion of the project and it is prepared to issue requests for proposals for construction. As of December 31, 2011, the Iowa Communications Network has drawn down and committed $5.3 million of American Recovery and Reinvestment Act funds. The Iowa Communications Network expects to draw additional funds in the first quarter of 2012. | 0 | 4 | 3000 | 0 | 3004 | 0 | 0 | 51 | No variance from baseline. | Baseline shows 12. Variance due to extended negotiations with IRU providers. | Baseline shows 1,385. Variance due to under estimation in baseline. | No variance from baseline. | Baseline shows 1,801. Variance due to extended negotiations with IRU providers. | NA | NA | Baseline shows 26. The Iowa Communication Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through the BTOP program, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2565 | 649 | 1916 | 0 | Baseline shows 1,407. Variance due to under estimation in baseline. | Baseline shows 213. Variance due to under estimation in baseline. | Baseline shows 743. Variance due to under estimation in baseline. | End users have access to various network services with speeds up to100Mbs. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No special offerings are anticipated as of this quarterly report | FALSE | NA -Network management practices have not changed from previous practices as of this quarterly report | During the next quarter, the Iowa Communications Network will continue with daily installations at network edge locations and migrate circuits to new equipment. This process will continue until project completion. The team will also turn up equipment on new IRUs as they become available. The sub-recipients in Decorah and on the Meskwaki settlements will score responses to their RFPs and will award construction contracts during the coming quarter. During the first quarter of 2012 the ICN expects to deploy no new network miles, to add approximately 30 miles of leased network and to have improved or added to access for approximately 2,800 CAIs. | Iowa Communications Network | The ICN experienced difficulty hiring field technicians with adequate experience. Several iterations of resume requests were required for each successful hire. This set back time lines for installations and network migrations. All technicians are now, however, on staff. | No significant challenges or issues are anticipated.
NT10BIX5570069 | 2012 | Q1 | Q1 - 2012 | The Iowa Communications Network continued to make progress during the first quarter of 2012. All staff planned have been hired including field technicians and network engineers. At the end of the quarter, 397 site installations had been completed. The vast majority of the remaining sites will be completed by the end of calendar 2012. The program sub-recipient in Decorah received bids from its posted request for proposals and has awarded a construction contract. The Sac and Fox sub-recipient has awarded a contract for construction of network engineered during the last quarter. The Sac and Fox sub-recipient has issued a request for proposal and received proposals for engineering, furnishing and installation of fiber-to-the-home equipment and associated power system. As of March 31, 2012, the Iowa Communications Network has drawn down and committed $7.1 million of American Recovery and Reinvestment Act funds. The Iowa Communications Network expects to draw additional funds in the second quarter of 2012. | 0 | 20 | 3000 | 0 | 3543 | 0 | 0 | 96 | No variance from baseline. | Baseline shows 25. Variance due to extended negotiations with IRU providers. | Baseline shows 1,943. Variance due to under estimation in baseline. | No variance from baseline. | Baseline shows 2,559. Variance due to under estimation in baseline. | NA | NA | Baseline shows 39. The Iowa Communication Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through the BTOP program, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of the BTOP program. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2617 | 680 | 1937 | 0 | Baseline shows 1,983. Variance due to under estimation in baseline. | Baseline shows 302. Variance due to under estimation in baseline. | Baseline shows 1,681. Variance due to under estimation in baseline. | End users have access to various network services with speeds up to 100 Mbs. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | NA | FALSE | No changes are planned. | During the next quarter, the Iowa Communications Network will continue with daily installations at network edge locations and migrate circuits to new equipment. This process will continue until project completion. The Decorah and Sac and Fox settlements sub-recipients will begin fiber construction during the second quarter of 2012. The Sac and Fox will award the contract for engineering, furnishing and installation of the fiber-to-the-home equipment and its associated power system. The Iowa Communications Network does not anticipate the addition of new network miles by sub-recipients during the second quarter of 2012. Approximately 16 miles of new fiber is expected to be leased during the quarter. As all 3,000 planned fiber network mile upgrades have been completed for the project, no additional miles well be upgraded. At the end of the second quarter, approximately 2,710 community anchor institutions will receive new or improved service as part of the project. | Iowa Communications Network | IRU installations were initially slower than anticipated but have now increased in rate of install. IRU installations are the only bottleneck on the project as of the end of the first quarter of 2012. It is expected that this issue will be mitigated during spring and summer. | NA
NT10BIX5570069 | 2012 | Q2 | Q2 - 2012 | Progress continues with the ICN project. At the end of the second quarter of 2012, 653 site installations had been completed. The ICN anticipates that the vast majority of sites will be completed by the end of the calender year. The program sub-recipient in Decorah completed its make-ready for fiber installation and is awaiting delivery of fiber optic cable. It is anticipated the cable will be delivered in the third quarter of calender 2012. The Sac and Fox sub-recipient has installed the majority of the backbone fiber for that portion of the project and is in the process of completing fiber connections at the Meskwaki Clinic. As of June 30, 2012, the Iowa Communications Network has drawn down and committed $8.1 million of American Recovery and Reinvestment Act funds. The Iowa Communications Network expects to draw additional funds in the third quarter of calender 2012. | 0 | 50 | 3000 | 0 | 3950 | 0 | 0 | 101 | Baseline shows 12. Variance due to late start due to time spent on environmental assessment and an underestimate on baseline. | Baseline shows 48. Variance due to underestimation in baseline report. | Baseline shows 2,407. Variance due to underestimation in baseline report. | No variance from baseline. | Baseline shows 3,236. Variance due to underestimation in baseline report. | N/A | N/A | Baseline shows 52. The Iowa Communications Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through BTOP, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of BTOP. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2671 | 724 | 1947 | 0 | Baseline shows 2,460. Variance due to under estimation in baseline. | Baseline shows 374. Variance due to error in baseline distribution of new and improved counts. Final count for customers receiving new access will be 933 rather than 467 as shown in the baseline. | Baseline shows 2,086. Variance due to error in baseline distribution of new and improved counts. Final count for customers receiving new access will be 2,148 rather than 2,614 as shown in the baseline. | End users have access to various network services with speeds up to 100 Mbs. | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | During the third quarter of calender 2012, the Iowa Communications Network anticipates completing physical installations in approximately 200 additional locations. This will represent approximately three quarters of all installations. This process will continue until project completion. The Sac and Fox sub-recipient will complete installation of backbone fiber in its fiber-to-the-home project. It will also complete installation of its associated power system. The Decorah sub-recipient will begin fiber installation by the end of the quarter. The Iowa Communications Network anticipates that approximately eight miles of fiber will be installed by the end of the quarter. Additionally, approximately 12 miles of new fiber is expected to be leased during the quarter. As all 3,000 planned fiber network mile upgrades have been completed for the project, no additional miles will be upgraded. At the end of the third quarter, approximately 2,900 community anchor institutions will receive new or improved service as part of the project. During the 3rd quarter of 2012, it is expected that 15 community anchor institutions will receive new service and that 50 will receive expanded service. | Iowa Communications Network | For the most part, the Iowa Communications Network made good progress with few challenges during the quarter. The project did experience minor and temporary delays associated with delivery of indefeasible right of use circuits from vendors and an inability to quickly acquire fiber optic cable for the Decorah portion of the project. It is expected that delays in each case will not cause an overall delay in project completion. | N/A
NT10BIX5570069 | 2012 | Q3 | Q3 - 2012 | The ICN continues to add new circuits and site equipment and remains on schedule for completion by June 30, 2012. At the end of the third quarter of 2012, 829 site installations had been completed. Additionally, the Sac and Fox sub-recipient has installed approximately 19 miles of fiber and is nearing completion of its portion of the project. The Decorah sub-recipient has received fiber plant and will begin installation in October of 2012. As of September 30, 2012, the Iowa Communications Network has drawn down $10.1 million of American Recovery and Reinvestment Act funds. The Iowa Communications Network expects to draw additional funds in the fourth quarter of calender 2012. | 19 | 58 | 3000 | 0 | 19 | 0 | 0 | 101 | Baseline shows 12. Variance due to underestimation in baseline report. | Baseline shows 61. Variance due to slower than expected IRU deliveries. | Baseline shows 2,699. Variance due to underestimation in baseline report. | No variance from baseline. | Only new fiber deployed is reported. Previous reports included new fiber miles leased and existing fiber miles upgraded. | No variance from baseline. | No variance from baseline. | Baseline shows 65. The Iowa Communications Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through BTOP, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of BTOP. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2460 | 636 | 1824 | 0 | Variance from baseline due to error in baseline value. Figure represents 93% of total CAIs (2,642). This was the same as the reported figure for the 2nd quarter. Even though new subscribers were added in the quarter it was offset by the number of duplicates found that have subsequently been removed. | Variance from baseline due to error in baseline value. Figure represents 88% of total new access CAIs (721). This is a drop from the 724 reported in the 2nd quarter PPR as duplicate CAI's were previously listed and have been subsequently removed. | Variance from baseline due to error in baseline value. Figure represents 94% of total improved access CAIs (1,950) in grant application or added by approved AAR. This is a drop from the 1,947 reported in the 2nd quarter PPR as duplicate CAI's were previously listed and have been subsequently removed. | End users have access to various network services with speeds up to 100 Mbs. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | N/A | FALSE | N/A | During the fourth quarter of calender 2012, the Iowa Communications Network anticipates completing physical installations in approximately 220 additional locations. This process will continue until project completion. The Sac and Fox sub-recipient will complete its portion of the project. The Decorah sub-recipient anticipates completimg fiber installation by the end of the quarter. The Iowa Communications Network anticipates that approximately 25 miles of fiber will be installed by the end of the quarter. As all 3,000 planned fiber network mile upgrades have been completed for the project, no additional miles will be upgraded. At the end of the fourth quarter, approximately 2,500 community anchor institutions will receive new or improved service as part of the project. | Iowa Communications Network | The baseline report shows a total of 3,081 CAI's as part of the project. This does not reflect the number of CAI's included in the grant application or acceptance materials. An audit of the working CAI list showed there were 412 duplicate entries representing the difference between the 2,669 CAI's (sum of the original 2,617 plus the 52 CAI's added early in the project) and the erroneous 3,081. The duplicates have been removed and the appropriate numbers reported in this document. | The rate of leased circuit delivery from vendors has been at a rate that, if continued, will result in fewer installations completed than anticipated. Venders have assured the ICN, however, that deliveries will ramp up during the fourth quarter.
NT10BIX5570069 | 2012 | Q4 | Q4 - 2012 | During fourth quarter of 2012, the Sac and Fox sub-recipient completed its fiber installation and is finalizing network delivery. The Decorah sub-recipient began installation of its fiber plant and is expected to complete installation during the first quarter of 2013. As of December 31, 2012, the Iowa Communications Network has drawn down $11.1 million of American Recovery and Reinvestment Act funds. Network installation was slowed during the fourth quarter due to leased circuit delivery from vendors at a pace slower than anticipated. The Iowa Communication Network expects all circuits expected in the 4th quarter of 2012 to be delivered during the 1st quarter of 2013. The Iowa Communications Network expects to draw additional funds in the first quarter of calender 2013. | 21 | 66 | 3000 | 0 | 21 | 0 | 0 | 101 | Baseline shows 12. Variance due to underestimation in baseline report. | Baseline shows 73. Variance due to slower than expected IRU deliveries. | Baseline shows 2,844. Variance due to underestimation in baseline report. | No variance from baseline. | Shows only new fiber deployed. Previous reports included new fiber miles leased and existing fiber miles upgraded. | No variance from baseline. | No variance from baseline. | Baseline shows 78. The Iowa Communications Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through BTOP, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of BTOP. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2452 | 649 | 1803 | 0 | Variance from baseline due to error in baseline value. Grant application showed total of 2,617 CAIs. | Variance from baseline due to error in baseline value. Grant application showed 687 new CAIs | Variance from baseline due to error in baseline value. Grant application showed total of 1,930 improved CAIs. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | N/A | FALSE | N/A | During the first quarter of calender 2013, the Iowa Communications Network anticipates that, in addition to the Sac and Fox sub-recipient project, the Decorah sub-recipient will complete its portion of the project resulting the installation of all 25 miles of fiber as described in the Baseline Report. As all 3,000 planned fiber network mile upgrades have been completed for the project, no additional miles will be upgraded. Site work will continue with work completed at an additional 204 sites. At the end of the first quarter of 2013, approximately 2,600 community anchor institutions will receive new or improved service as part of the project. It is expected that 18 miles of IRU fiber will be connected in the 1st quarter of 2013. | Iowa Communications Network | The baseline report shows a total of 3,081 CAIs as part of the project. This does not reflect the number of CAIs included in the grant application or acceptance materials. The ICN applied in both Round One and in Round Two of the BTOP program and different CAI lists were intended to be submitted in each case. The CAI list meant to be submitted for Round Two application had 3,081 CAIs and it was, evidently, the list on which the project Baseline Report and other project details were established. The final grant, however, contained a list of 2,617 CAIs. This error has resulted in significant confusion regarding the scope of the project including the status of the CAIs included in the list of 3,081 but not in the list of 2,617. | The ICN would benefit from assistance in resolving reporting issues associated with CAI problems described in Section 1, Question 3 above.
NT10BIX5570069 | 2013 | Q1 | Q1 - 2013 | During first quarter of 2013, the Decorah sub-recipient completed its fiber installation. As of March 31, 2013, the Iowa Communications Network has drawn down $12.8 million of American Recovery and Reinvestment Act funds. IRU deliveries are back on schedule and the project remains on track for an on time completion The Iowa Communications Network expects to draw remaining budgeted funds during the 2nd quarter of 2013. The Meskwaki Tribe have been working to turn up high-speed Internet to the homes on the reservation. Difficulties were encountered due to winter weather impacting the terrain and travel to and from the homes from the main switch location. There have been 8% of the homes enabled with high-speed Internet through the 1st quarter of 2013. Additionally, the Meskwaki Settlement School and the Meskwaki Tribal Government Offices were enabled with high-speed Internet. | 25 | 84 | 3000 | 0 | 25 | 0 | 0 | 102 | Baseline shows 12. Variance due to underestimation in baseline report. | Baseline shows 86. Variance due to slower than expected IRU deliveries. | Baseline shows 2,963. Variance due to underestimation in baseline report. | No variance from baseline | Shows only new fiber deployed. Previous reports included new fiber miles leased and existing fiber miles upgraded. | No variance from baseline | No variance from baseline | Baseline shows 91. The Iowa Communications Network is significantly ahead of the baseline in regard to the installation of interconnection points because these sites were required to be upgraded as part of the normal course of business operations. Customer requested product changes or enhancements mandated that the upgrade of this equipment be completed sooner than was anticipated when the baseline report was created. Since these sites were to eventually be upgraded through BTOP, these upgrades were completed using BTOP specifications rather than upgrading them now and then again several months later as part of BTOP. This situation has resulted in this portion of the program being greatly ahead of schedule. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2517 | 674 | 1843 | 0 | Variance from baseline due to error in baseline value. Grant application showed total of 2,617 CAIs. | Variance from baseline due to error in baseline value. Grant application showed 687 new CAIs | Variance from baseline due to error in baseline value. Grant application showed total of 1,930 improved CAIs. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | N/A | FALSE | N/A | The ICN expects to complete the project on time and either at or under budget during the 2nd quarter of 2013. The ICN expects to complete 15-year IRU's for a total of 10 miles of leased fiber in the 2nd quarter of 2013 for a project total of 94 miles of lease fiber. The ICN will add 381 new CAI's for a final project total of 2,898 intended CAI's at this time. | Iowa Communications Network | The ICN is finalizing the overall CAI list and has identified some CAIs listed that are no longer located at the address in the CAI list or were improperly regarded as CAIs in the original grant application. This, along with the confusion with the overall CAI count discrepancies will be address with AARs during the month of April. | The ICN would benefit from approval of CAI revision AARs to be submitted in the 2nd quater of 2013.
NT10BIX5570069 | 2013 | Q2 | Q2 - 2013 | The ICN completed the operational phase of its BTOP project on time and under budget. All engineering and installations are completed. All sites as identified in the grant application and amended by AAR are installed and operational. All planned IRU's are completed and connected. The goal of the project is to improve four functions of the Iowa Communications Network (ICN) and to provide broadband opportunities for two sub-recipients, The city of Decorah Metronet and the Sac & Fox Tribe of the Mississippi in Iowa (Meskwaki). The first improved function resulted in an upgrade to the backbone transport platform and routers in our network. This was accomplished with the installation of ADVA DWM equipment which upgraded the ICN backbone. We also installed higher capacity routers at several major traffic points. This allows increased bandwidth in all 99 Iowa counties with up to a 10 Gbps capable backbone. The original project objective was to provide a 1 Gbps backbone but due to being under-budget higher capacity routers were able to be purchased within the approved budget. This has also increased network redundancy capabilities. The second improve function was the installation of new switching equipment at customer or edge sites allowing them to have up to 1 Gbps data service. The legacy equipment was replaced which simplifies the process of troubleshooting and brings our authorized users up to the bandwidth capacity that their applications require in a cost effective solution. The third improvement was the procurement of dark fiber IRU leases to allow increased capacities to be provided the the edge customers. Authorized users who previously had leased connections typically at 1.5 Mbps were immediately able to access up to 10 Mbps with the potential to get up to 100 Mbps in the future. The Sac & Fox Tribe of the Mississippi in Iowa (sub-recipient) has completed its effort to turn up Internet service to the tribal homes according to customer requests. This provides their school, medical clinic and tribal center as well as 197 homes with high-speed data capacities. The BTOP has afforded the Meskwaki community the opportunity to strengthen and enhance the Tribe's goal to further education, improve quality of life and provide accessibility to the governing nation and its community. This provides a foundation to build better and brighter futures. The Decorah Metronet (sub-recipient) has completed fiber installations and purchased new router equipment which will allow governmental and educational entities in the city of Decorah to be connected on their backbone at the previously mentioned capacities. Additionally, they now have the ability to store data off-site and at multiple locations which will allow for network redundancy. The fourth improved function is the the increased ability of the Iowa Homeland Security and Emergency Management Division to provide Next Generation 9-1-1 (NG911) connections across the state. The NG911 deployment consists of a highly available emergency services IP network connecting all Public Safety Answering Points (PSAPs) in the state to two geographically redundant call logic centers. | 26 | 97 | 3000 | 0 | 26 | 0 | 0 | 105 | Variance from baseline is due to actual miles reported from sub-recipients being more than estimated miles. | Changes in Network Miles Leased were based on changes to physical work sites and was not based on a functional relationship with CAIs. There was a very minor reduction in miles leased: 99 reduced to 97. | No variance from baseline. | No variance from baseline. | Shows only new fiber deployed. Previous reports included new fiber miles leased and existing fiber miles upgraded. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 2818 | 461 | 2357 | 2818 | Baseline shows 3,081. Variance due to changes documented in approved AAR's. | Baseline shows 467. Variance due to changes documented in approved AAR's. | Baseline shows 2,617. Variance due to changes documented in approved AAR's. | Up to 1 Gb. | 197 | 197 | 197 | 0 | 197 | Variance to baseline is due to lack of information at the time of application to project statistics. | Variance to baseline is due to lack of information at the time of application to project statistics. | Variance to baseline is due to lack of information at the time of application to project statistics. | No variance from baseline. | Up to 1 Gb. | 178 | 9 | 7 | 2 | 2 | Variance to baseline is due to lack of information at the time of application to project statistics. | Variance to baseline is due to lack of information at the time of application to project statistics. | Variance to baseline is due to lack of information at the time of application to project statistics. | No variance from baseline. | Up to 1 Gb. | N/A | FALSE | N/A | The ICN expects to complete project close out processes and documentation during the next quarter. | Iowa Communications Network | All work has been completed as represented in the above reported figures. | N/A
NT10BIX5570070 | 2010 | Q4 | Q4 - 2010 | MassBroadband 123 accomplishments for the quarter ending December 31, 2010 include: Administrative: â€¢ Submitted draft Environmental Assessment (â€œEAâ€) to NTIA ahead of due date and conducted consultations; â€¢ Submitted and received NTIA approval for Baseline Plan; â€¢ Submitted and received NTIA approval for Six Month Pre-EA Budget; â€¢ Attended BTOP Conference for Round Two recipients; â€¢ Completed Project Manual; Procurements: â€¢ Completed procurement for and hired Route Validation Firm; â€¢ Completed procurement for and hired Field Data Collection Firm; â€¢ Completed procurement for and hired Ownerâ€™s Project Manager; â€¢ Completed procurement for and hired Preliminary Engineering and Design firms; â€¢ Continued RFP process for the Network Operator including developing draft agreement and requesting supplemental information from finalists; â€¢ Issued environmental permitting services RFP; â€¢ Received approval from State Inspector General for Design-Build method for constructing the network; â€¢ Issued public notice for Letter of Interest for Design-Build Procurement; â€¢ Commenced drafting Design-Build technical and functional specifications â€¢ Commenced drafting Design-Build RFQ and technical and functional requirements for RFP â€¢ Collaborated with the Information Technology Division of the Commonwealth to draft an Optical Networking Equipment and Standards RFI; Agreements: â€¢ Executed MOUs with Verizon and Western Massachusetts Electric Company f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | None at this time.3 | No services are being offered at this timet this time. | MTC has commenced negotiations with the top finalist to a competitive Network Operator RFP that we issued in June 2010. We plan to complete negotiations and hire the Network Operator in the upcoming quarter. The Network Operator will assist with equipment specifications and network and fiber design during the construction period and will run the entire MassBroadband 123 network when it is completed. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC plans on offering a 15% discount for wholesale offerings to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | In the upcoming quarter MTC plans to: Administrative: â€¢ Hand in our completed environmental assessment to NTIA, with consultations completed; Procurements: â€¢ Complete negotiations with and hiring of the Network Operator; â€¢ Hire an Environmental Services firm; â€¢ Issue the design-build RFQ and RFP; â€¢ Issue an RFP for a contractor to do National Grid's make-ready work; Agreements: â€¢ Execute pole attachment and conduit agreements with Verizon, Western Massachusetts Electric and National Grid; â€¢ Continue negotiations with municipal electric companies for pole attachment agreements; â€¢ Commence negotiations with towns for placement of interconnection node equipment; Execute agreement for conduit in Springfield; â€¢ Enter into a contract for meet-me space at PoP in Springfield. Design and Engineering: â€¢ Commence environmental permitting; â€¢ Continue surveying poles and submitting license applications to pole and conduit owners; â€¢ Continue conducting field work to determine bridge and railroad crossing and refine the route, laterals, and entrances to the CAIs and determine permitting Construction: Commence make-ready work on existing conduit and utility poles Outreach: â€¢ Continue outreach program to 123 communities and last-mile providers; | Massachusetts Technology Park | To date, the most challenging aspect of the MassBroadband 123 project has been the numerous and complicated negotiations with many different right of way owners, including multiple utility pole and conduit owners in the project footprint. The pace of completing and executing all the concomitant agreements has been slower than expected. | To date, the most challenging aspect of the MassBroadband 123 project has been the numerous and complicated negotiations with many different right of way owners, including multiple utility pole and conduit owners in the project footprint. While MTC is confident that the memorandums of understanding for expedited pole attachment licensing processes with the incumbent pole owners will initially help us to save time, we are concerned about the great amount of make-ready work that will likely need to be completed before pole attachment licenses can be issued. Much of the make-ready work that is required needs to be performed by third party entities that are not under the control of MTC. It would be very useful to know what other states are doing about these potential road blocks. It would be helpful if the BTOP program would develop and share best practices it learns about through its recipients.
NT10BIX5570070 | 2011 | Q1 | Q1 - 2011 | MassBroadband 123 accomplishments for the quarter ending March 31, 2010 include: Administrative: - Received Finding of No Significant Impact (FONSI) after successful submittal of Environmental Assessment Procurements - Completed procurement for and hired Network Operator - Completed procurement for and hired Environmental Permitting Services firm - Received responses to the Optical Networking Equipment and Standards RFI - Drafted and released Request For Quotation (RFQ) for Design Build procurement - Drafted and released Request For Proposal (RFP) for Design Build procurement - Created short list of prospective Design Build firms, and held bidder's pre-proposal meeting. Agreements - Executed agreement with City of Springfield for a conduit Indefeasible Right of Use (IRU) that will be used to connect the I-91 portion of MassBroadband 123 to the Internet Point of Presence at One Federal Street, Springfield - Executed Memorandum of Understanding (MOU) with National Grid for expedited pole survey and application process - Executed Three-Way Pole Attachment Agreement with Verizon and Western Massachusetts Electric Company - Continued negotiation of Pole Attachment agreement with National Grid - Continued negotiation of Two-Way Pole Attachment Agreement with Verizon and Two-Way Conduit Agreement with Verizon. - Continued negotiation with eight municipal electric companies and two telephone companies on Pole Attachment Agreements and Memorandum of Understanding's (MOU) where a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | Variance of 55 miles from the baseline equates to those miles provided as match for this quarter but won't be considered "existing upgraded" until they are lit with BTOP funds in a future quarter. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baselineR projections and baseline. | 1 | 1 | 40 | Axia Networks, USA | No services are being offered at this timet this time. | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 1 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | MTC plans on offering a 15% discount for wholesale offerings to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network | FALSE | N/A | In the upcoming quarter MTC plans to: Procurements - Complete procurement process for Design Build selection, including receipt of responses, full evaluation of bids, contract negotiation with selected firm, and issuance of Notice to Proceed - Release Dark Fiber Indefeasible Right of Use (IRU) RFP and collect responses. Agreements - Execute Pole Attachment Agreement with National Grid - Execute Verizon 2-way Pole Attachment Agreement and Verizon 2-way Conduit Agreement - Execute Memorandum Of Understanding's (MOU) and Pole Attachment Agreements with Russell Municipal Light, Princeton Municipal Light, and Templeton Municipal Light & Water - Execute lease agreement at One Federal Street in Springfield - Execute Master Services Agreement (MSA) with state partners, the Information Technology Division of Massachusetts (ITD) and the Executive Office of Public Safety and Security (EOPSS) Design and Engineering - Prepare all railroad crossing permits and MassDOT applications for permit - Submit pole applications for 28 towns - Continue pole license application process Construction - Commence make-ready work on existing conduit and utility poles Outreach - Continue outreach program to 123 communities and last-mile providers, specifically in preparation for Community Anchor Institute (CAI) and Point of Interconnection (POI) outreach -With input from community representatives, finalize list of 1,392 Community Anchor Institutes (CAI) for connection by the project Resources -Hire | Massachusetts Technology Park | A challenge to MassBroadband 123 in the past quarter has been the severe winter weather affecting the ramp-up of field data collection and pole license applications. The field data collection contractor is expected to be back on schedule with their baseline by the end of June 2011. The complicated negotiations surrounding pole attachment agreements with National Grid and various municipal utility companies also continue to be challenging to bring to completion. | Looking ahead to the next quarter, we are most concerned about the great amount of make-ready work that will likely need to be completed before pole owners will issue us pole attachment licenses. While Massachusetts Technology Collaborative (MTC) has very good working relationships and regular meetings with the pole owners and even other third party attachers, much of the make-ready work that is required needs to be performed by entities that are not under the control of MTC. It would be very useful to know what other states are doing about these potential road blocks. It would be helpful if the Broadband Technology Opportunity Program( BTOP) would develop and share best practices it learns about through its recipients.
NT10BIX5570070 | 2011 | Q2 | Q2 - 2011 | MassBroadband 123 accomplishments for the quarter ending June 30th, 2010 include: Administrative -None this quarter Procurements -Successfully completed procurement for Design Build entity, executing a contract with the selected firm. This competitive procurement includes all construction materials and equipment to complete the project. -Issued Request For Proposal (RFP) for Dark Fiber Indefeasible Rights of Use (IRU) for connection of the route to Boston -Issued RFP for valuation of Interstate 91 segment of the network Agreements -Executed Two-Way Pole Attachment Agreement with National Grid -Executed Two-Way Pole Attachment Agreement with Verizon and Two-Way Conduit Agreement -Executed Memorandums of Understanding (MOUs) with the remaining municipal electric companies for expedited survey and application process; have obtained MOUs for all territory where field data collection is planned -Finalizing Three-Way Pole Attachment agreements for the municipal electric companies of the towns of Russell and Princeton -Continued negotiation of pole attachment agreements and IRU deals for remaining eight towns in which the agreements are required -Continued negotiation on lease of meet-me room in One Federal Street in Springfield Design and Engineering -Received pole data for over 10,500 poles (34 towns) this quarter, totaling over 13,000 for the project -Submitted applications for licensing and make ready for over 7,200 poles, totaling over 9,000 for the project -Submitted 30 con | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | Variance of 55 miles from the baseline equates to those miles provided as match for this quarter but won't be considered "existing upgraded" until they are lit with BTOP funds in a future quarter. | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baselinR projections and baseline | 2 | 0 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD) Axia, the Network Operator has had discussions with nine ISPs, but formal negotiations have not yet started on the agreements. MTC will count discussions as negotiations when developing memorandums of understanding and full contracts. | No services are being offered at this timet this time. | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 1 | 0 | 1 | 0 | On par with last quarter's PPR projections and baseline. (Axia Networks). | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. The Agreement MTC has with Massachusetts Information Technology Division (ITD) provides ITD with a right to dark fiber. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | MTC plans on offering a 15% discount for wholesale offerings to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network | FALSE | N/A | In the upcoming quarter MTC plans to: Procurements -Select winning bidder in Dark Fiber IRU RFP and negotiate contracts for IRUs -Select winning bidder in I-91 Valuation RFP and complete valuation of I91 asset -Design-builder to place orders for a majority of fiber and required construction materials Agreements -Execute lease agreement at 1 Federal Street in Springfield -Execute Pole Attachment Agreements for utilities Granby Tel, Chester Electric, and Unitil -Continue negotiations for fiber IRU agreement with Westfield, Chicopee, Holyoke, and South Hadley -Execute agreements with Housatonic Railroad and begin filing for permits -Begin filing environmental permits -Begin negotiations for connection point in Boston for dark fiber IRU Design and Engineering -Receive pole data for approximately 17,000 additional poles for 90% total collection for the project -Submit pole applications for 50 additional towns (approximately 12,000 poles, or 60% of the total project) -Continue conduit application process alongside pole applications for each town -Conduct final segment design for first segments of network to be built -Begin inside plant design for CAI and POI entry and connection Construction -Refine construction schedule -Continue make ready work on poles that have been applied for and for which make ready costs and estimates have been received and paid Outreach -Begin outreach and drafting of agreements for entry and connection to the CAIs and POIs in the network footprint -N | Massachusetts Technology Park | Issues encountered include: -Design-build proposal bids were higher than expected leading to negotiations which delayed signing by approximately 2 weeks. The Design-Builder has a contract requirement to expend 55% of the available funds prior to the completion of year 2 of the grant award. -A bid challenge was received to the Design-build procurement -Make-Ready: 1. Telecommunication's Make Ready estimates came in at a higher cost than expected. 2. Electric company's costs come in later than telephone companies and do not provide pole-level unit detail 3. Joint Pole-owner Space Allocation Table (JPSAT) is being enforced against the project resulting in a substantial increase in the amount, (and the subsequent cost) or make ready, including poles where no make ready is required under National Electric Safety Code. NTIA could assist by: 1. Providing guidance on ways that other projects are reducing telephone and electric companies make ready costs 2. Providing information on whether other projects are having costs increased substantially by enforcement of JPSAT MTC is confident that the minor delay in execution of the Design-Build contract has no material impact on meeting the 67% complete deadline or project schedule. This is true due to pre-payment for make-ready, the plan to order most fiber and equipment prior to the end of this calendar year, and the higher overall cost of the contract. | The greatest unknown will continue to be the make ready process, the work required to be completed, the associated cost and schedule impacts that may take place. There have also been two major storms this summer that have caused significant damages and led to limited availability of appropriately staffed resources for the utility companies performing make ready work. We will continue to work diligently with the pole owners to find solutions and cost saving measures while keeping up the planned schedule of applications and reconciliation as best as possible. Also, industry-wide delays in fiber delivery could have an impact on the start of fiber deployment. MTC would welcome advice or feedback from BTOP officials or other awardees regarding these topics and appreciate any best practices from other recipients. There is the potential for a strike by Verizonâ€™s labor unions in August 2011. Should Verizon go on strike, then there is a substantial risk of delay. MTC is evaluating options to address this risk, but it represents a material obstacle to reaching substantial completion on time.
NT10BIX5570070 | 2011 | Q3 | Q3 - 2011 | MassBroadband 123 accomplishments for the quarter ending September 30th, 2011 include: Agreements -Executed contract with G4S Technology, LLC , Design Builder for the project, for complete final design and construction of the MassBroadband 123 network -Executed lease agreement for interconnection space at One Federal Street in Springfield -Executed Three-Way Pole Attachment agreements for the municipal utility companies of the towns of Russell, Granby, Chester, Templeton and Princeton -Executed four (4) non-binding Letters of Intent with Internet Service Providers for providing services on the MassBroadband 123 network Design and Engineering -Received pole data for over 23,000 poles this quarter, totaling over 33,500 for the project -Submitted applications for licensing and make ready for over 14,000 poles, totaling over 20,600 for the project -Submitted conduit applications for over 13 miles of conduit for a total of 24 miles for the project -Paid Verizon make ready cost estimates for 8,200 poles and electric company make ready costs for 4,200 poles -Received first pole licenses for 35 poles from Verizon and 19 poles for Western Massachusetts Electric Company -Prepared filings for environmental permits, Massachusetts Department of Transportation permits, and submitted the first applications for railroad crossings -Completed site visits and surveys of 390 Community Anchor Institutions and 16 Points of Interconnect -Completed fiber design diagrams for five (5) of seven (7) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline | The variance is due to the anticipated mileage of the Light Tower Indefeasible Rights of Use agreement for dark fiber services back to Boston. We now expect to sign the agreement next month. The Light Tower IRUs total 202.5 miles vs. the original grant projection of 337 miles. | Variance of 55 miles from the baseline equates to those miles provided as match for this quarter but won't be considered "existing upgraded" until they are lit with BTOP funds in a future quarter. | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baselinR projections and baseline | 2 | 8 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD). MTCâ€™s Network Operator has eight Letters of Intent signed and has been finalizing the connecting agreements necessary for companies to sign and achieve these milestone. Once the connecting agreement is finalized, it is anticipated that two entities will sign promptly and several more in coming months. | No services are being offered at this timet this time. | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 2 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | On par with last quarter's PPR projections and baseline. | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | true | In the upcoming quarter MTC plans to: Agreements -Execute Pole Attachment Agreements for Unitil, Massachusetts Department of Conservation and Recreation and Massachusetts Development Finance Agency -Continue negotiations for fiber Indefeasible Rights of Use (IRU) agreement with Westfield, Chicopee, Holyoke, and South Hadley -Execute agreements with Housatonic Railroad -Begin filing environmental permits -Complete negotiations for connection point in Boston for dark fiber IRU Projections for the following key indicators: -New network miles deployed is 0 -New network miles leased is 202.5 (mileage from the IRU) -Existing miles upgraded is 0 -Total CAI subscribers served (CAIs connected) is 0 -Number of signed agreements with broadband wholesalers or last mile providers is 2 Design and Engineering -Complete the pole survey work and receive all pole required data in the project footprint -Submit pole applications for 50 additional towns (approximately 12,000 poles, or 90% of the total project) -Continue conduit application process alongside pole applications for each town -Complete final segment design for all phases of construction -Complete inside plant design for 50% of the Community Anchor Institutions Construction -Finalize construction schedule. -Continue make ready work on poles that have been applied for and for which make ready costs and estimates have been received and paid -Operationalize the I91 fiber network , making it available for commercial use Outreach -Be | Massachusetts Technology Park | Issues encountered include: Make ready schedule delays 1.Verizon's union went on strike for several weeks in August, removing resources from the project's make ready reconciliation efforts. The work has since fully resumed, but some time and momentum was lost in these efforts 2. The project area underwent unusual stress due to weather, including a hurricane and tornado that took away resources from the utilities' make ready efforts and placed them on storm duty. This inhibited some anticipated progress in make ready reconciliation. 3. Make ready construction costs continue to run higher than budgeted. NTIA could assist by: 1. Providing guidance on ways that other projects are reducing telephone and electric companies make ready costs 2. Providing information on how other projects are working with utilities to maintain pace and schedule in make ready reconciliation | The most relevant risk to the project will continue to be the make ready process, the work required to be completed, and the associated cost and schedule impacts that may take place. Extension of make ready periods act to compress the construction schedule, leading to possible increased crew requirements and the corresponding increases in project costs. We will continue to work diligently with the pole owners to find solutions and cost saving measures while keeping up the planned schedule of applications and reconciliation as best as possible. We are entering the winter months, and poor weather will pose schedule risks to both utility make ready construction and early fiber installation efforts. Also, industry-wide delays in fiber delivery could have an impact on the start of fiber deployment. MTC would welcome advice or feedback from BTOP officials or other awardees regarding these topics and appreciate any best practices from other recipients. Delays to date are pushing back the completion of Make-Ready work and have had minimal impact on the process of filing applications. Make-ready costs, which are coming in higher than anticipated, have to be paid in advance, and expenditures will increase as a result of these pre-payments, and higher than initially budgeted costs for route preparation (new poles and conduit). In addition, MTC plans to begin CAI construction and installations during Q4 2011 and continuing throughout the remainder of the project. MTC also plans to purc
NT10BIX5570070 | 2011 | Q4 | Q4 - 2011 | MassBroadband 123 accomplishments for the quarter ending December 31st, 2011 include: Agreements -Executed contract for dark fiber Indefeasible Right of Use to connect network service to Boston via two paths. -Executed pole attachment agreement with Unitil -Executed Housatonic Railroad Company Utility Crossing License agreement -Reviewed draft Point of Interconnection Agreement with 10 of 22 locations Make Ready and Licensing -Completed utility pole data collection; received data for over 5,000 poles during the quarter out of a total of 38,500 poles for the project -Submitted applications for licensing and make ready for over 8,800 poles, totaling over 29,400 for the project -Submitted conduit applications for over 4 miles of conduit for a total of 28 miles for the project -Paid Verizon make ready cost estimates for 5,600 poles for a total of 13,800 poles, and electric company make ready costs for 2,500 poles for a total of 6,700 -Received pole licenses for 387 poles from Verizon, 430 poles for Western Massachusetts Electric Company and 96 poles for National Grid. Through 12/31 we have received 441 licenses for Verizon, 449 for Western Massachusetts Electric Company and 96 for National Grid -Received 22 conduit application record searches from Verizon. To date we have received 24 record search results Engineering, Design, and Pre-Construction Activities -Finalized construction schedule with Design Builder -Received approval of one Notice of Intent in accordance with Massachusetts Wetland Protection Act -Received district-wide permits from the Massachusetts Department of Transportation -Submitted 44 drawings to 6 railroad companies to begin railroad permitting -Completed site surveys of 632 Community Anchor Institutions and all 22 Points of Interconnect locations -Completed design submittals for 96 Community Anchor Institutions and 3 Points of Interconnect -Completed fiber design diagrams -Completed construction drawings for 4 segments of the network, and completed corresponding splicing diagrams for the first phase of construction -Obtained critical infrastructure components including inside plant parts, fiber optic cable, core optical network equipment, termination panels, and power plant -Implemented prototype test lab simulating three Points of Interconnection for proof-of-design and equipment testing Construction -Utilities continuing make-ready work Jobs Created or Retained -The Total Number of Jobs Created or Retained for the quarter was 25.78 Sustainability -Executed 5 Letters of Intent with Internet Service Providers for providing network services. To date, we have executed 9 Letters of Intent for Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | Variance of 55 miles from the baseline equates to those miles provided as match for this quarter but won't be considered "existing upgraded" until they are lit with BTOP funds in a future quarter. | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | NA | NA | On par with last quarter's PPR projections and baseline | 2 | 7 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD) | No services are being offered at this time. | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 3 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | 0 | 0 | 0 | 0 | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | On par with last quarter's PPR projections and baseline | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | In the upcoming quarter, MTC plans to: Agreements -Execute Pole Attachment Agreements Massachusetts Department of Conservation and Recreation and Massachusetts Development Finance Agency -Execute dark fiber Indefeasible Rights of Use (IRU) agreement with Westfield, Chicopee, Holyoke, and South Hadley -Execute overlash agreement with Richmond Telephone -Execute agreements with Massachusetts Central Railroad, CSX Corporation, and Pan Am Railways -Continue filing of environmental and railroad permits -Execute agreements with POIs Design and Engineering -Submit pole applications and conduit applications for entirety of remaining route not yet applied for -Complete segment construction drawings for 14 additional segments, for a total of 50% of the network -Complete site survey on 66% of the network for a total 90% of the Community Anchor Institutions in the network -Complete inside plant design for 25% of the Community Anchor Institutions for a total of 35% of the network -Complete inside plant design for 5 Points of Interconnect for a total of 33% of the network Construction -Install network equipment at Community Anchor Institutions as designs are finalized and available. MTC is performing equipment installations at Community Anchor Institutions in advance of actual connection, which requires connectivity to the nearest Point of Interconnection and from that Point of Interconnection to the internet Point of Presence. Due to adjusted make ready completion timelines, we now project the first connections as occurring in Year 2, Quarter 4 -Install messenger strand and fiber optic cable as utility pole licenses become available -Continue make ready work on poles -Operationalize the I91 fiber network, making it available for commercial use Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | Issues encountered include: Make ready schedule delays 1. The time required by utilities to reconcile applications is exceeding contracted time frames. In addition, once reconciled, electric company estimates greatly lag behind telephone company estimates. 2. Make ready construction costs continue to run higher than budgeted. 3. Additional weather events diverted utility resources to emergency restoration. NTIA could assist by: 1. Providing guidance on ways that other projects are reducing telephone and electric companies make ready costs 2. Providing information on how other projects are working with utilities to maintain pace and schedule in make ready reconciliation, while maintaining positive reporting and crew production oversight | The most relevant risk to the project will continue to be the make ready process, the work required to be completed, and the associated cost and schedule impacts that may take place. Extension of make ready periods act to compress the construction schedule, leading to possible increased crew requirements and the corresponding increases in project costs. We will continue to work diligently with the pole owners to find solutions and cost saving measures while keeping up the planned schedule of applications and reconciliation as best as possible. We are in the midst of the winter months, and poor weather will pose schedule risks to both utility make ready construction and early fiber installation efforts. MTC would welcome advice or feedback from BTOP officials or other awardees regarding these topics and appreciate any best practices from other recipients.
NT10BIX5570070 | 2012 | Q1 | Q1 - 2012 | MassBroadband 123 accomplishments for the quarter ending March 31st, 2012 include: Agreements -Reviewed draft Point of Interconnection Agreement with all required project locations -Executed 5 of 22 Points of Interconnection license agreements -Executed agreement for 3.5 miles of overlash construction in Richmond, Massachusetts -Executed attachment agreement for Massachusetts Development Finance Agency Make Ready and Licensing -Submitted applications for licensing and make ready for over 6,200 poles, totaling over 35,600 for the project -Submitted conduit applications for over 7 miles of conduit for a total of 35 miles for the project -Paid Verizon make ready cost estimates for 12,000 poles for a total of 25,800 poles, and electric company make ready costs for 13,800 poles for a total of 20,500 -Received pole licenses for 2,082 poles from Verizon and 1,655 from electric utilities. Through 3/31 we have received 2,469 licenses for Verizon and 2,085 licenses from electric utilities -Released 48 licensed fiber miles to construction Engineering, Design, and Pre-Construction Activities -Received district-wide permits from the Massachusetts Department of Transportation -Completed site surveys of 205 Community Anchor Institutions totaling 837 to date, and surveyed all 22 Points of Interconnect locations -Completed design submittals for 319 Community Anchor Institutions installations totaling 415 through 3/31 and 5 Points of Interconnect totaling 8 through 3/31 -Completed final strand count cable design for all project phases -Completed construction drawings for 3 segments of the network, totaling 7 for the project through 3/31 -Obtained critical infrastructure components including inside plant parts, fiber optic cable, core optical network equipment, termination panels, and power plant -Approved prototype test lab for proof-of-design and testing Construction -Installed 25 miles of messenger strand -Installed 8 miles of fiber optic cable -Complete 82 CAI site installations Jobs Created or Retained -The Total Number of Jobs Created or Retained for the quarter was 33.09 Sustainability -Executed 11 Letters of Intent with Internet Service Providers for providing network services. Through 3/31, we have executed 20 Letters of Intent for Service -Executed 2 connecting agreements with Internet Service Providers | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | Behind on baseline projection by 152 miles due to slow make ready completion; current schedule forecasting indicates that progress will be made up in upcoming quarters | Behind on baseline projection by 231 miles out of a total of 307 miles projected in the baseline; the actual mileage is 192.5 and is expected to take delivery June 1st, 2012, versus the original plan to accept delivery in the current quarter. Leased network miles are reduced to 192.5 from 307 due to leasing all as dark fiber instead of prior plan to lease a combination of dark fiber and a wavelength service. | Variance of 55 miles from the baseline equates to those miles provided as match for this quarter but won't be considered "existing upgraded" until they are lit with BTOP funds in a future quarter. | N/A | Behind on baseline projection by 438 miles as described in the preceding 4 lines. | NA | NA | Behind on baseline projection by 1; MTC ended the quarter with the room fit out and equipment for 1 point of interconnection in process versus the expectation that it would be completed. This and other points of interconnection will be completed next quarter | 4 | 7 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies | No services are being offered at this time. | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 4 | 0 | 0 | 0 | Ahead on baseline by 3; interest of service providers has exceeded expectations held at the time of grant submission | Behind on baseline by 4; while connecting agreements are not yet executed; many letters of intent have been signed and will lead to connecting agreements. | Per NTIA guidance, MTC now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MTC now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | N/A | 0 | 0 | 0 | 0 | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. 82 installations have been performed vs. the baseline of 145; ramp-up of subcontractor effort is expected next quarter | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | 100Mbps: 3, 1Gbps: 4, 5Gbps: 0, 10Gbps+: 6 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | In the upcoming quarter, MTC plans to: Agreements -Execute Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation -Execute dark fiber Indefeasible Rights of Use (IRU) agreement with Westfield, Chicopee, Holyoke, and South Hadley -Execute overlash agreement with Russell Municipal Light Department -Execute agreements with CSX Corporation, Pioneer Valley Railroad and Pan Am Railways -Continue filing of environmental and railroad permits -Execute agreements with all remaining Points of Interconnect Design and Engineering -Complete segment construction drawings for 12 additional segments, for a total of 55% of the network -Complete site survey on all of the Community Anchor Institutions in the network (10% remain) -Complete inside plant design for 25% of the Community Anchor Institutions for a total of 60% of the network -Complete inside plant design for 5 Points of Interconnect for a total of 59% of the network Construction -Install network equipment at Community Anchor Institutions as designs are finalized and available. Expected to reach 35% of Institutions installed. MTC is performing equipment installations at Community Anchor Institutions in advance of actual connection, which requires connectivity to the nearest Point of Interconnection and from that Point of Interconnection to the internet Point of Presence. Due to adjusted make ready completion timelines, we now project the first connections as occurring in Year 2, Quarter 4 -Install messenger strand and fiber optic cable as utility pole licenses become available (an estimated 107 miles of fiber installed for the quarter) -Continue make ready work on poles -Operationalize the I91 fiber network, making it available for commercial use Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | The completion of make ready work leading to pole licensing has been slower than expected due to the gradual ramp-up of the utility work forces involved with the reconciliation and construction work. In addition, we initially experienced a denial of significant amounts of conduit license applications which was reversed by the utility companies based on additional analysis of conduit availability, but the time from that analysis resulted in delays in obtaining conduit licenses. Make ready work is currently slightly behind our projected completion schedule, but our team continues to meet with utility officials at the executive level, as well as coordinate with crew managers on a daily and weekly basis to manage the priorities of the work and the rate in which it is completed. In terms of the budget overruns, MTC has secured additional non-federal funds from the Commonwealth to offset budget overruns. | N/A
NT10BIX5570070 | 2012 | Q2 | Q2 - 2012 | MassBroadband 123 accomplishments for the quarter ending June 30th, 2012: Agreements -Executed 16 Points of Interconnection license agreements for a total of 21 to date -Executed license agreements for co-location sites in Boston and Cambridge Make Ready and Licensing -Submitted applications for licensing and make ready for over 800 poles, totaling 36,400 for the project -Submitted conduit applications for 5 miles of conduit, for a total of 40 miles for the project -Received construction estimates on 4,000 poles for Verizon and 8,500 poles for electric companies, for totals to date of 29,800 from Verizon and 28,300 from electric companies -Received 7,784 pole licenses for Verizon for a total of 9,866 license and 6,961 for the electric companies for a total of 9,046 licenses -Obtained authorization for and began performing third-party make ready work on behalf of applicable organizations -Released 132 fully-licensed aerial miles to construction for aerial installation for a total of 180 miles released for the project Engineering, Design and Pre-Construction Activities -Completed site surveys of 58 Community Anchor Institution locations totaling 895 to date -Completed design submittals for 156 Community Anchor Institution locations for a total of 571 to date -Completed 8 Points of Interconnection sites for a total of 16 to date -Completed construction drawings for 6 segments for a total of 13 segments to date -Approved lab prototype test plan and results Construction -Installed 93 miles of messenger strand, totaling 118 miles for the project -Installed 60 miles of fiber optic cable, totaling 68 miles for the project -Completed site installations at 213 Community Anchor Institutions, totaling 295 for the project Jobs Created or Retained -The Total Number of Jobs Created or Retained for the quarter was 50.30 Sustainability -Lit portion of I91 fiber segment -Executed 2 letters of intent with Internet Service Providers, for a total of 22 to date -Held 4 Community Anchor Institution informational sessions to educate the decision makers on advanced uses of the fiber network -Achieved 150 Informational Technology Division sites committing to take service upon availability -Attended National Telecommunications and Information Administration workshop in Washington, D.C. -Hosted NTIA site visit for project audit and management discussions Program Income Program Income to date is funds received by Axia, the network operator, and will be used to fund costs in excess of the federal approved budget later in the project. | 68 | 193 | 57 | 0 | 316 | 0 | 0 | 1 | Behind on baseline projection by 307 miles due to slow make ready completion. MTC is working with its construction contractor to compress construction in future quarters to make up for make-ready delays. | Leased miles acquired by MTC on 6/1/12. Leased miles reduced from 307 (231 this quarter) to 192.5 per approved AAR due to switch to all dark fiber IRUs. | Ahead on mileage projection in baseline by 2 miles. The 55 miles along I91 were officially active as in-kind contribution on 6/29/12. The extra 2 miles are from on added section from I91 to the internet point of presence in Springfield | N/A | Behind on baseline projection by 345 miles as described in the preceding 4 lines. | N/A | N/A | Behind on baseline projection by 11; per NTIA direction, MTC placed a construction hold on any Point of Interconnection not included in its Environmental Assessment until it receives approval of the required Award Action Request. Points of Interconnection site installations and connections will begin to pick up in the next two quarters | 4 | 7 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies | None at this time | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 4 | 0 | 0 | 0 | Ahead on baseline by 3; interest of service providers has exceeded expectations held at the time of grant submission | Behind on baseline by 6; while connecting agreements are not yet executed; many letters of intent have been signed (22) and will lead to connecting agreements. | Per NTIA guidance, MTC now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MTC now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | N/A | 0 | 0 | 0 | 0 | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. 295 installations have been performed vs. the projected 287; ramp-up of subcontractor effort is expected next quarter to maintain pace | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | 100Mbps 1Gbps 5Gbps 10Gbps+ | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | In the upcoming quarter, MTC plans to: Agreements -Execute Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation -Execute dark fiber Indefeasible Rights of Use (IRU) agreement with Westfield, Chicopee, Holyoke, and South Hadley -Continue filing of environmental and railroad permits -Execute agreements with all remaining Points of Interconnect Design and Engineering -Complete segment construction drawings for 20 additional segments to complete segment design on the network -Complete site survey on all of the Community Anchor Institutions in the network (2% remain) -Complete inside plant design for 30% of the Community Anchor Institutions for a total of 90% of the network -Complete inside plant design for remaining 9 Points of Interconnect and internet Points of Presence Construction -Continue to install network equipment at CAIs. Goal is to reach 55% but completion depends on NTIA approval of AAR documenting CAI changes -Continue to install network equipment at POIs. Goal is to reach 50% but completion depends on NTIA approval of AAR documenting POI changes -Install messenger strand and fiber optic cable as utility pole licenses become available (an estimated 120 miles of fiber installed for the quarter). MTC is working with its construction contractor to compress construction in future quarters to make up for make-ready delays -Continue make ready work on poles to provide more work released for fiber optic construction -Continue performing third-party make ready work on behalf of applicable organizations Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | The completion of make ready work leading to both conduit and pole licensing has been slower than expected due to the gradual ramp-up of the utility work forces involved with the reconciliation and construction work. Make ready work is currently behind our schedule. Conduit licensing confirmation is a critical item to finalizing design and identifying all route and installation type changes for the network. MTC continues to meet with utility officials at the executive level, as well as coordinate with crew managers on a daily and weekly basis to manage the priorities of the work and the rate in which it is completed. MTC was not able to make as much progress as planned due to the Award Action Request process which requires that no work can be done on Community Anchor Institutions, Points of Interconnection sites, routes or installation if changes have been made without an approval to an Award Action Request identifying such changes. Throughout this report, we are calculating Percent Complete with reference to the approved NTIA budget. Costs are now projected to be higher than that approved budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the approved NTIA budget. | Construction scheduling has become a critical issue to timely completion of the project. Timely approval of Award Action Requests for modifications to Community Anchor Institutions, Points of Interconnection, route and installation types is critical to the project completing as scheduled. In addition MTC continues to be challenged by slow make-ready completion by utility companies for both aerial and underground make-ready. The cumulative impact of delays can be offset, to some extent, by compression of the construction schedule through extended work-days and work-weeks and increasing the numbers of crews. MTC is continuously evaluating its schedule to determine the appropriate resource requirements and timing to address the schedule risk.
NT10BIX5570070 | 2012 | Q3 | Q3 - 2012 | MassBroadband 123 accomplishments for the quarter ending September 30th, 2012: Agreements and Administration -Completed all required Point of Interconnection license and co-location agreements, executing 4 agreements during the quarter for a total of 25. -Submitted Award Action Requests for modifications of construction plans pending NTIA approval of the designated route adjustments Make Ready and Licensing -Submitted applications for licensing and make ready for 600 poles, totaling 37,000 for the project -Submitted applications for 1 mile of conduit for a total of 41 miles for the project -Received cost estimates on 1,100 poles for Verizon and 1,775 poles for electric companies, for totals to date of 31,700 from Verizon and 28,300 from electric companies -Received 11,965 pole licenses for Verizon for a total of 21,831 licenses and 9,157 for the electric companies for a total of 18,203 licenses -Received licenses on 22 conduit applications totaling 8 miles of conduit. -Performed third-party make ready work on behalf of applicable organizations -Released 213 fully-licensed fiber miles to construction for aerial installation for a total of 393 miles for the project Engineering, Design and Pre-Construction Activities -Completed site surveys of 5 Community Anchor Institution locations to total 900 to date; surveys now complete for the project -Completed designs for 198 Community Anchor Institution locations for a total of 769 for the project -Completed all required designs for Point of Interconnection and co-location sites, completing 9 in the reporting period for a total of 25 for the project -Completed all pre-construction segment drawings for the project, completing 22 in the quarter for a total of 35 Construction -Installed 89 miles of messenger strand, totaling 207 miles for the project -Installed 52 miles of fiber optic cable, totaling 120 miles for the project -Completed site installations for 158 Community Anchor Institution locations for a total of 453 site installations for the project -Completed 2 Point of Interconnection and co-location site installations for a total of 3 to date Jobs Created or Retained -The total number of jobs created or retained for the quarter was 66.15 Sustainability -Executed 4 letters of Intent with Internet Service Providers for a total of 26 to date -Began CAI Broadband Adoption Project, an outreach vehicle for town managers and administrators aimed to increase service sales as the network is completed and activated | 120 | 193 | 57 | 0 | 370 | 0 | 0 | 2 | Behind on baseline projection by 505 miles due to slower-than-expected make ready completion and temporary construction hold instituted by NTIA. MTC is working with its construction contractor to compress construction schedule in future quarters to make up for these delays | Behind on baseline projection by 114 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs | Ahead on mileage projection in baseline by 2 miles. The 57 miles along I91 were officially active as in-kind contribution on 6/29/12. The extra 2 miles are from on added section from I91 to the internet point of presence in Springfield | N/A | Behind on baseline projection by 617 miles as described in the preceding 4 lines | N/A | N/A | Behind on baseline projection by 21; per NTIA direction, MTC placed a construction hold on and Point of Interconnection not included in its Environmental Assessment until it received approval of the required Award Action Request. Points of Interconnection site installations and connections will resume in the next two quarters. | 4 | 7 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies, Center for Education Leadership (CELT) | None at this time | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 5 | 0 | 0 | 0 | Ahead on baseline by 4; interest of service providers has exceeded expectations held at the time of grant submission | Behind on baseline by 6; while connecting agreements are not yet executed; many letters of intent have been signed (26) and will lead to connecting agreements. | Per NTIA guidance, MTC now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MTC now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps 10Gbps+ | 0 | 0 | 0 | 0 | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. 453 installations have been performed vs. the projected 574; ramp-up of subcontractor effort is expected next quarter to maintain pace | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of receiving lit service, resulting in a delay in the metrics. | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps 10Gbps+ | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | In the upcoming quarter, MTC plans to: Agreements -Execute Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation, Fairpoint, and Time Warner -Execute dark fiber Indefeasible Rights of Use (IRU) agreement with Westfield, Chicopee, and South Hadley -Continue filing of environmental and railroad permits -Obtain NTIA approval of all remaining route and installation type changes Design and Engineering -Complete splicing diagrams for the remainder of the network -Complete inside plant design for final 5% of the Community Anchor Institutions to complete the design process Construction -Continue to install network equipment at CAIs once NTIA construction hold is released. Goal is to reach 80% of installations complete -Continue to install network equipment at POIs once NTIA construction hold is released. Goal is to reach 40% of installations complete -Install messenger strand and fiber optic cable as utility pole licenses become available (an estimated 150 miles of fiber installed for the quarter). MTC is working with its construction contractor to compress construction in future quarters to make up for make-ready delays -Continue make ready work on poles to provide more work released for fiber optic construction. Expected to complete 95% of aerial make ready and 60% of conduit make ready -Continue performing third-party make ready work on behalf of applicable organizations Acceptance Testing -Complete testing and turnovers of first 5 Points of Interconnection and co-location sites Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service. Expected to sign four additional Connecting Agreements -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | Throughout the quarter MTC worked with NTIA to obtain formal approval of all proposed route, CAI, POI and installation type changes. In review of route changes that had been implemented or planned by MTC, NTIA developed concerns that the nature of the changes may have led to noncompliance with BTOPâ€™s Environmental and Historic Preservation requirements. NTIA maintained that while MTCâ€™s internal compliance process appeared to be sound, because NTIA had not yet reviewed or approved the changes conducted during the review process, any changes that had not been approved by NTIA were out of compliance. At the request of NTIA, MTC ceased work on portions of the project and worked to fully document the scope of the changes via Award Action Request. This impacted utility make-ready completion, MTC deployment of aerial and underground fiber, placement of new poles, installation of new conduit, and work at Points of Interconnection and Community Anchor Institutions in various portions of the project. MTC prepared two Award Action Requests (AARs) to NTIA to obtain approval for all the project changes. During the quarter MTC obtained approval for one AAR and submitted the second. The construction hold most severely affected planned new underground installations, most of which are included in the second AAR mentioned above, and as a result new underground installations now form the critical path for project completion. | Construction scheduling has become a critical issue to timely completion of the projection. Throughout the past quarter, much of the available CAI, POI and fiber optic construction was placed on temporary hold until NTIA approvals were obtained. Next quarter will be spent recovering from those schedule delays by compressing the schedule and ramping up additional crews. However, we face a major challenge in the area of underground construction, where winter moratoriums often prevent any such construction from occurring between the months of November and March due to weather. It will be crucial to make gains in other areas of construction, installation and testing so as to minimize the negative schedule impacts due to weather concerns. MTC will work with its vendors to manage this challenge and to complete the work as efficiently and effectively as conditions allow.
NT10BIX5570070 | 2012 | Q4 | Q4 - 2012 | MassBroadband 123 accomplishments for the quarter ending December 31st, 2012: Agreements and Administration -Executed pole attachment agreement with Fairpoint Communications -Executed Indefeasible Rights of Use agreement with Westfield Gas & Electric Light Department -Executed Indefeasible Rights of Use agreement with South Hadley Electric Light Department -Submitted 3rd formal Award Action Request for modification of construction plans pending NTIA approval of route adjustments Make Ready and Licensing -Received 6,805 Verizon pole licenses for a total of 28,601 (87% complete) -Received 4,119 WMECO pole licenses for a total of 14,674 (86% complete) -Received 3,782 National Grid pole licenses for a total of 11,536 (87% complete) -Released 345 fully-licensed fiber miles to construction for aerial installation for a total of 740 miles for the project (79% complete) -Received licenses for 10,718 feet of conduit for a total of 138,118 feet to date (70% complete) Network Design and Construction -Installed 263 miles of messenger strand for a total of 470 miles for the project (51% complete) -Installed 168 miles of aerial fiber optic cable for a total of 288 miles for the project (31% complete) -Installed 422 feet of conduit for a total of 7,181 feet for the project (15% complete) -Completed designs for 13 Community Anchor Institutions for a total of 782 locations (97% complete) -Completed 85 Community Anchor Institution site installations for a total of 538 locations for the project (67% complete) -Completed 179 Community Anchor Institution fiber terminations (22% complete) -Completed 5 Point of Interconnection and collocation site installations for a total of 8 to date (36% complete) Jobs Created or Retained -The total number of jobs created or retained during the quarter was 62.91 Sustainability -Executed one Letter of Intent with an Internet Service Provider for a total of 27 to date -Executed 3 "last mile" Connecting Agreements with Internet Service Providers for a total of 6 to date. MTC has also executed 2 wholesale agreements with Axia Networks USA and Massachusetts Information Technology Division/Executive Office of Public Safety and Security | 470 | 193 | 57 | 0 | 663 | 0 | 0 | 2 | Behind on baseline projection by 430 miles due to slower-than-expected make ready completion and temporary construction hold instituted by NTIA. MTC is working with its construction contractor to compress construction schedule in future quarters to make up for these delays | Behind on baseline projection by 114 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs | Ahead on mileage projection in baseline by 2 miles. The 57 miles along I91 were officially active as in-kind contribution on 6/29/12. The extra 2 miles are from on added section from I91 to the internet point of presence in Springfield | N/A | Behind on baseline projection by 599 miles as described in the preceding new network miles deployed and leased. Based on updated mileage projections through the second approved Award Action Request, number of miles of new fiber (aerial and underground) is 1182 (excluding the 57 miles of existing network miles upgraded) | N/A | N/A | Behind on baseline projection by 22. MTC has completed the new connection at internet Point of Presence at 1 Federal St. in Springfield, as well as a second internet Point of Presence in Boston. MTC has several Points of Interconnections with equipment installed, and aims to have connections achieved during the next two quarters | 8 | 20 | 70 | Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies, Center for Education Leadership (CELT), Access Plus, Community WISP, Inc., Streamline Networks | Wholesale services currently being provided are: -Ethernet-100 Service - Ethernet-based bandwidth services that provide up to 100% of the line rate speed of the physical connection. It services a single User Network Interface (UNI) and a single Virtual Private Network membership (VPN) -NNI (Network-to-Network Interface Service) - one port in Springfield and one port in Cambridge. Allows customers to access "off-net" services such as determined by the customer network. -Gigabit Ethernet Boston Transport Service - Provides connectivity from either network Regional Gateway (Springfield Internet Point of Presence) to the Boston Global Gateways (Cambridge and Boston Points of Interconnection). | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 8 | 0 | 0 | 0 | Ahead on baseline by 7; interest of service providers has exceeded expectations held at the time of grant submission. While only 8 wholesaler or last mile agreements have been executed; many letters of intent have been signed (20) and will lead to connecting agreements. Agreements originally categorized as "receiving improved access" are being categorized as "receiving new access" based on updated interpretation of the baseline category. | Behind on baseline by 7. MTC interpreted the baseline differently and is now categorizing all signed agreements as "receiving new access" and does not expect to categorize any agreements as "receiving improved access". | Per NTIA guidance, MTC now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MTC now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps 10Gbps+ | 0 | 0 | 0 | 0 | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of connecting to its serving POI, resulting in a delay in the metrics. 538 site installations have been performed vs. the projected 551 sites. | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of connecting to its serving POI, resulting in a delay in the metrics. MTC anticipates 1199 CAIs receiving "new access". | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are capable of connecting to its serving POI, resulting in a delay in the metrics. MTC anticipates 108 CAIs receiving "improved access". | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps 10Gbps+ | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | Agreements -Execute Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation and Time Warner -Execute dark fiber Indefeasible Rights of Use (IRU) agreement with Chicopee Electric Light Department -Execute railroad permit agreements with CSX Transportation, New England Central Railroad, and Pan Am Railways -Obtain NTIA approval of all remaining route and installation type changes Design and Engineering -Finalize approvals splicing diagrams for the remainder of the network -Complete inside plant design for final 3% of the Community Anchor Institutions to complete the design process Construction -Continue to install network equipment at Community Anchor Institution sites. Goal is to reach 90% of installations complete -Continue to perform fiber terminations at Community Anchor Institution sites. Goal is to reach 50% of terminations complete -Continue to install network equipment at Points of Interconnection. Goal is to reach 70% of installations complete -Install messenger strand as utility pole licenses become available (an estimated 385 miles of strand deployed for the quarter). -Install fiber optic cable as messenger strand is completed (an estimated 400 miles of fiber deployed for the quarter). -Continue make ready work on poles to provide more work released for fiber optic construction. Expected to complete aerial and conduit make ready by the end of the quarter. Acceptance Testing -Complete testing and turnovers of two (2) Points of Interconnection and co-location sites -Expected to connect 78 Community Anchor Institutions across 53 unique locations Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service. Expected to sign four (4) additional Connecting Agreements -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | MTC received approval of its August 2012 Award Action Request for Route and CAI changes during the quarter. MTC submitted its third Award Action Request regarding route adjustments for the project on November 13th 2012. Approval of this Award Action Request is still pending as of 12/31/2012. | MTC anticipates receiving an early January approval of its November Award Action Request for Route and CAI changes. Due to the nature of pole and conduit licensing, MTC continues to be required to make minor route adjustments to work around problems, or to change installation types to address license denials. MTC expects that these changes will continue throughout construction and as a result MTC expects to submit another Route Change Award Action Request in January or February 2013. NTIAâ€™s requirement that all such changes be submitted for NTIA review and approval prior to construction presents a risk of blockages in what portions of the route are able to be built. MTC is also concerned that harsh weather could introduce delays in construction, affecting the project schedule.
NT10BIX5570070 | 2013 | Q1 | Q1 - 2013 | MassBroadband 123 accomplishments for the quarter ending March 31st, 2013: Agreements and Administration -Executed overlash agreement with Russell Municipal Cable TV & Internet -Executed pole attachment agreement with Time Warner Cable Northeast, LLC -Executed Indefeasible Rights of Use agreement with Chicopee Electric Light Department -Executed Indefeasible Rights of Use agreement with Holyoke Gas & Electric Department -Executed permitting agreement with Pan Am Railways -Executed permitting agreement with New England Central Railroad -Submitted 4th formal Award Action Request for modification of construction plans pending NTIA approval of route adjustments Make Ready and Licensing -Received 3,002 Verizon pole licenses for a total of 31,603 (96% complete) -Received 3,218 electric utility pole licenses for a total of 29,428 (97% complete) -Released 155 fully-licensed fiber miles to construction for aerial installation for a total of 895 miles for the project (96% complete) -Received licenses for 14 miles conduit for a total of 39 miles to date (93% complete) Network Design and Construction -Installed 305 miles of messenger strand for a total of 775 miles for the project (83% complete) -Installed 388 miles of aerial fiber optic cable for a total of 676 miles for the project (72% complete) -Installed 8,131 feet of conduit for a total of 15,312 feet for the project (32% complete) -Completed designs for 8 Community Anchor Institutions for a total of 790 locations (97% complete) -Completed 44 Community Anchor Institution site installations for a total of 582 locations for the project (72% complete) -Completed 81 Community Anchor Institution fiber terminations for a total of 260 locations for the project (32% of locations complete) -Completed 6 Point of Interconnection and collocation site equipment installations for a total of 17 to date (63% complete) Network Testing and Turnover -Completed turnover of first network segment to Network Operator, connecting 3 Points of Interconnection and 2 regeneration sites Sustainability -Executed 4 Letters of Intent with an Internet Service Providers for a total of 31, as well as signing 5 connecting agreements to total 13 connecting agreements for the project Jobs Created or Retained -The total number of jobs created or retained during the quarter was 103.91 | 775 | 193 | 57 | 0 | 968 | 0 | 0 | 2 | Behind on baseline projection by 175 miles due to slower-than-expected make ready completion and temporary construction hold instituted by NTIA. MTC has worked with its construction contractor to compress construction schedule and believes it will make up for the delays without them becoming critical path to completion | Behind on baseline projection by 114 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs. 39 additional miles via IRU expected to become leased mileage in a future quarter | Ahead on mileage projection in baseline by 2 miles. The 57 miles along I91 were officially active as in-kind contribution on 6/29/12. The extra 2 miles are from on added section from I91 to the internet point of presence in Springfield | N/A | Behind on baseline projection by 289 miles as described in the preceding new network miles deployed and leased. The 289 miles do not include 55 additional miles from the baseline categorized as existing network miles upgraded | N/A | N/A | Behind on baseline projection by 21. MTC has completed the new connection at internet Point of Presence at 1 Federal St. in Springfield, as well as a second internet Point of Presence in Boston. MTC has 17 Points of Interconnections with equipment installed, and aims to have connections achieved during the next quarter as testing is completed | 13 | 18 | 70 | -Axia Networks, USA -Massachusetts Information Technology Division (ITD) -Crocker Communications -FTG Technologies -Center for Education Leadership (CELT) -Access Plus -Community WISP, Inc. -Streamline Networks -Cornerstone Communications -Holyoke Gas & Electric -MECnet -Ayacht Technology Solutions -Warwick Broadband Service | Wholesale services currently being provided are: -Ethernet-100 Service - Ethernet-based bandwidth services that provide up to 100% of the line rate speed of the physical connection. It services a single User Network Interface (UNI) and a single Virtual Private Network membership (VPN) -NNI (Network-to-Network Interface Service) - one port in Springfield and one port in Cambridge. Allows customers to access "off-net" services such as determined by the customer network. -Gigabit Ethernet Boston Transport Service - Provides connectivity from either network Regional Gateway (Springfield Internet Point of Presence) to the Boston Global Gateways (Cambridge and Boston Points of Interconnection). | MTC has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 13 | 0 | 0 | 1 | Ahead on baseline by 11; interest of service providers has exceeded expectations held at the time of grant submission. While 13 wholesaler or last mile agreements have been executed; many additional letters of intent have been signed (18) and will lead to connecting agreements. Agreements originally categorized as "receiving improved access" are being categorized as "receiving new access" based on updated interpretation of the baseline category. | Behind on baseline by 7. MTC interpreted the baseline differently and is now categorizing all signed agreements as "receiving new access" and does not expect to categorize any agreements as "receiving improved access". | Per NTIA guidance, MTC now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MTC now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps - 0 subscribers 10Gbps - 1 Subscriber | 85 | 85 | 0 | 1 | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI, resulting in a delay in the metrics. 796 installations have been performed vs. the projected 911 sites. | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI, resulting in a delay in the metrics. MTC anticipates 1106 CAIs receiving "new access". | In preparing the baseline, MTC considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI, resulting in a delay in the metrics. MTC anticipates 135 CAIs receiving "improved access". | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps - 0 subscribers 10Gbps - 1 Subscriber | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MTC offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | n/a | Administrative -Execute Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation, Time Warner Cable, City of Pittsfield, and PJ Keating Company -Obtain NTIA approval of all remaining route and installation type changes to ensure remaining work on hold may be released for installation/construction -Obtain NTIA approval for project time extension Design and Engineering -Finalize approvals for all remaining permits and route designs Construction -Continue to install network equipment at 100 Community Anchor Institution sites. Goal is to reach 85% of installations complete -Continue to perform fiber terminations at 140 Community Anchor Institution sites. Goal is to reach 50% of terminations complete -Continue to install network equipment at Points of Interconnection. Goal is to complete the remaining 7 points of Interconnection -Install 115 miles of messenger strand as utility pole licenses become available; estimated to reach 95% completion -Install 165 miles of fiber optic cable as messenger strand is completed; estimated to reached 90% completion Acceptance Testing -Complete testing and turnover of Segment 1 of the network -Complete testing and turnovers of two (2) Points of Interconnection and co-location sites -Expected to connect 78 Community Anchor Institutions across 53 unique locations Sustainability -Negotiate additional Letters of Intent with Internet Service Providers and work towards contracts to provide service. Expected to sign three (3) additional Connecting Agreements -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | MTC had anticipated being able to re-engage underground construction activities in mid-March, based on town moratoriums on road construction being lifted and a delay in asphalt plant production. Due to late winter weather it is now anticipated that construction will not fully re-engage until the end of April. It will be critical to have a productive crew count during May and the beginning of June to meet schedule needs. MTC submitted its fourth Award Action Request regarding route adjustments in February 2013. As of the end of March it had not yet been approved and NTIA has anticipated a 4-6 week lead time on that approval. The work affected will become critical path starting in early April and cause a day-for-day delay in project completion. MTC will continue to work with NTIA in any way possible to facilitate the expedited review and approval of the Award Action Request. MTC will also be submitting, under the guidance of NTIA, a schedule extension request due to the aforementioned delays across the project | Because of the aforementioned moratoriums on underground construction, progress during the upcoming quarter will be critical to the schedule and in making up for the delays. In addition, NTIA approval of the Award Action Request for route adjustments is important for several areas of route and CAI installation that have become critical path items. MTC will coordinate closely with NTIA regarding any schedule extensions and associated items as they arise.
NT10BIX5570070 | 2013 | Q2 | Q2 - 2013 | MassBroadband 123 accomplishments for the quarter ending June 30th, 2013: Agreements and Administration -Executed Pole Attachment and Conduit Agreement with Massachusetts Department of Conservation and Recreation -Executed Pole Attachment Agreement with Time Warner Cable -Executed Pole Attachment Agreement with City of Pittsfield -Executed Pole Attachment Agreement with PJ Keating Company -Received approval on 4th formal Award Action Request for modifications of construction plans pending NTIA approval of route adjustments. -Received approval on No Cost Extension Award Action Request through January 2014. Make Ready and Licensing -Received 717 Verizon pole licenses for a total of 32,320 (99% complete). -Received 725 electric utility pole licenses for a total of 30,153 (99% complete). -Released 23 fully-licensed fiber miles to construction for aerial installation for a total of 918 miles for the project (99% complete). -Received licenses for 2 miles conduit for a total of 41 miles to date (99% complete). Network Design and Construction -Installed 78 miles of messenger strand for a total of 853 miles for the project (93% complete). -Installed 223 miles of aerial fiber optic cable for a total of 899 miles for the project (97% complete). -Installed 11,801 feet of conduit for a total of 35,217 feet for the project (74% complete). -Completed designs for 8 Community Anchor Institutions for a total of 790 locations (97% complete) -Completed 129 Community Anchor Institution site installations for a total of 711 locations for the project (90% complete). -Completed 73 Community Anchor Institution fiber terminations for a total of 333 locations for the project (42% of locations complete). -Completed 5 Point of Interconnection and collocation site installations for a total of 22 to date (81% complete). Network Testing and Turnover -Completed turnover of a network segment to Network Operator, serving an additional Community Anchor Institution. Sustainability -Executed one additional Letter of Intent with an Internet Service Provider for a total of 32 Jobs Created or Retained -The total number of jobs created or retained during the quarter was 79.87 | 899 | 193 | 57 | 0 | 1092 | 0 | 0 | 3 | Behind on baseline projection by 77 miles due to slower-than-expected make ready completion and previous construction holds. Note: updated projections documented in an upcoming AAR shift the expected total miles deployed to 954. | Behind on baseline projection by 114 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs. 39 additional miles via IRU expected to become leased mileage in a future quarter. Note: updated projections documented in an upcoming AAR shifted the expected total leased miles to 229. | Ahead on mileage projection in baseline by 2 miles. The 57 miles along I91 were officially active as in-kind contribution on 6/29/12. Note: updated projections documented in an upcoming AAR shift the expected total miles upgraded to 61 | N/A | Behind on baseline projection by 191 miles as described in the preceding new network miles deployed and leased. The 191 miles do not include 55 additional miles from the baseline categorized as existing network miles upgraded | N/A | N/A | Behind on baseline projection by 20. MassTech has completed the new connection at internet Point of Presence at 1 Federal St. in Springfield, as well as a second internet Point of Presence in Boston, and completed the Sandisfield POI. MassTech has 17 Points of Interconnections with equipment installed, and aims to have additional connections achieved during the next quarter as testing is completed. In the next quarter, MassTech will be submitting for NTIA approval a reclassification of certain sites. This will reduce the count of CAIs by 14 and increase the count of POIs by 14. | 13 | 19 | 32 | -Axia Networks, USA -Massachusetts Information Technology Division (ITD) -Crocker Communications -FTG Technologies -Center for Education Leadership (CELT) -Access Plus -Community WISP, Inc. -Streamline Networks -Cornerstone Communications -Holyoke Gas & Electric -MECnet -Ayacht Technology Solutions -Warwick Broadband Service | Wholesale services currently being provided include: - Broadband and Ethernet class services from 5Mbps to 1Gbps that provide up to 100% of the line rate speed of the pysical connection, serving as a single User Network Interface (UNI) and single Virtual Private Network membership (VPN) - Network-to-Network Interface (NNI) - one port in Springfield and one port in Cambridge. Allows customers to interconnect to "off-net" services at any desired speed. - Gigabit Ethernet Boston Transport Service - Provides connectivity from western Massachusetts to Boston area Global Gateways - 10 Gbps wavelength service | MassTech has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 13 | 0 | 0 | 1 | Ahead on baseline by 11; interest of service providers has exceeded expectations held at the time of grant submission. While 13 wholesaler or last mile agreements have been executed; many additional letters of intent have been signed (19) and will lead to connecting agreements. Agreements originally categorized as "receiving improved access" are being categorized as "receiving new access" based on updated interpretation of the baseline category. | Behind on baseline by 8. MassTech interpreted the baseline differently and is now categorizing all signed agreements as "receiving new access" and does not expect to categorize any agreements as "receiving improved access". | Per NTIA guidance, MassTech now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MassTech now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 5Mbps 10Mbps 20Mbps 100Mbps 1Gbps 5Gbps - 0 subscribers 10Gbps - 1 Subscriber | 471 | 471 | 0 | 356 | In preparing the baseline, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI | In preparing the baseline, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 1106 CAIs receiving "new access". | In preparing the baseline, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 135 CAIs receiving "improved access". | 10Mbps-118, 20Mbps-60, 50Mbps-177, 5 Mbps,100Mbps, 1Gbps, 5Gbps - 0 subscribers 10Gbps - 1 Subscriber | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MassTech offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | Permitting -Receive final 350 pole licenses for the remainder of the project Construction -Continue to install network equipment at 80 Community Anchor Institution sites. Goal is to reach 99% of installations complete -Continue to perform fiber terminations at 300 Community Anchor Institution sites. Goal is to reach 85% of terminations complete, compared to 100% KPI. -Continue to install network equipment at Points of Interconnection. Goal is to complete the remaining 3 points of Interconnection -Install 50 miles of messenger strand as utility pole licenses become available; estimated to reach 99% completion -Install 50 miles of fiber optic cable as messenger strand is completed; estimated to reached 99% completion, compare to 100% KPI Acceptance Testing -Complete acceptance testing of 14 Points of Interconnection sites -Complete acceptance testing of 540 Community Anchor Institutions -Complete acceptance testing of 21 additional fiber segments -Complete turnover of 3 additional network segments to Network Operator Sustainability -Continue marketing initiatives and achieve 3 additional Connecting Agreements as segments become operational -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | MassTech is in the midst of recovering from schedule delays caused by several extreme weather events and extended moratoriums on underground construction. NTIA's approval of the 4th Award Action Request for route adjustments, as well as the approval of the schedule extension to January 2014, has helped clear the way for MassTech to continue schedule recovery efforts as we complete network testing and turn over segments to the Network Operator. | Since the project is now nearing completion, the challenge going forward is to ensure thorough review and quality of the documentation for the network and clean-up of punch list items to ensure operational efficiency.
NT10BIX5570070 | 2013 | Q3 | Q3 - 2013 | MassBroadband 123 accomplishments for the quarter ending September 30th, 2013: Completion of 32 (of 958) new miles and 0 (of 229) new leased miles (for a total of 1187 miles); 307 (of 1080) new CAIs and 1 (of 157) improved CAIs (for a total of 1237 CAIs). Make Ready and Licensing -Received 193 Verizon pole licenses for a total of 32,513 (99% complete). -Received 49 electric utility pole licenses for a total of 30,202 (99% complete). -Received 1 mile of conduit licenses for a total of 42 miles (100% complete) Network Design and Construction -Installed 27 miles of messenger strand for a total of 880 miles for the project (99% complete). -Installed 91 miles of aerial fiber optic cable for a total of 990 cable miles (including slack and sag) for the project (99% complete). -Installed 12,092 feet of conduit for a total of 47,309 feet for the project (98% complete). -Completed 38 miles of IRU fiber (100% complete) -Completed 56 Community Anchor Institution site installations for a total of 786 locations for the project (99% complete). -Completed 319 Community Anchor Institution fiber terminations/testing for a total of 1080 for the project (71% complete). -Completed 5 Point of Interconnection and collocation site installations for a total of 27 to date (65% complete). Network Testing and Turnover -Completed turnover of 2 Points of Interconnection to Network Operator (26% complete). -Completed turnover of 3 network segment to Network Operator (10% complete). -Completed turnover of 80 Community Anchor Institutions to Network Operator (6% complete). Sustainability - Executed 3 additional connecting agreements with broadband wholesalers or last mile providers for a total of 17 Jobs Created or Retained -The total number of jobs created or retained during the quarter was 67.25. | 931 | 229 | 57 | 0 | 1160 | 0 | 0 | 27 | Behind on baseline projection by 45 miles due to slower-than-expected make ready completion and previous construction holds. Note: Updated projections documented in an upcoming AAR shift the expected total miles deployed to 958. | Behind on baseline projection by 78 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs. End of project new leased miles are expected to be 229. | Ahead on mileage projection baseline by 2 miles. Original proposal included in-kind contribution of 55 miles of fiber along I-91. Upon consultation with NTIA it was determined that these miles should not be included, resulting in a reduction of total miles by 55. End of project upgraded miles are expected to be 0. | N/A | Behind on baseline projections by 121 miles due to IRU reduction of 78 miles, route changes and remaining fiber to be deployed of 45 miles, and 2 miles of new fiber reclassified as existing upgraded. The 1,124 miles do not include existing upgraded mileage. End of project total miles are expected to be 1,187. | N/A | N/A | Ahead of project baseline by 5. The target number of POIs has been changed to 41 due to the addition of POIs for connections to municipal IRUs and reclassification of some locations from CAI to POI. MassTech has completed the new connection at Point of Interconnections for Becket, Belchertown, Charlemont, Chesterfield, Great Barrington, Hinsdale, Lee, New Braintree, North Adams, Northampton, Orange, Pittsfield, Plainfield, Russell, Savoy, Sandisfield, Sturbridge, Westfield, Richmond Telephone, Westfield Gas and Electric A-End, Westfield Gas and Electric Z-End, WG&E Operations Center, Holyoke Gas and Electric Splice Enclosure, Town of Chicopee East St. Meet Point, Town of Chicopee Center St. Meet Point, Town of South Hadley Splice Enclosure, and SHELD Stoney Brook Facility. | 17 | 2 | 76 | -Axia Networks, USA -Massachusetts Information Technology Division (ITD) -Crocker Communications -FTG Technologies -Center for Education Leadership (CELT) -Access Plus -Community WISP, Inc. -Streamline Networks -Cornerstone Communications -Holyoke Gas & Electric -MECnet -Ayacht Technology Solutions -Warwick Broadband Service -Berkshire Unified Phone -WiredWest -Lightower -Windstream NOTE: The average term of signed agreements in 5a reflects the average length of fixed-term contracts. | Wholesale services currently being provided are: -Ethernet-100 Service - Ethernet-based bandwidth services that provide up to 100% of the line rate speed of the physical connection. It services a single User Network Interface (UNI) and a single Virtual Private Network membership (VPN). -NNI (Network-to-Network Interface Service) - Allows customers to access "off-net" services determined by the customer network. -Gigabit Ethernet Boston Transport Service - Provides connectivity from either network Regional Gateway to the Boston Global Gateways at the following speeds: 20 Mbps increments, 1, 2.5, & 5Gbps. -Broadband Service - Provides Ethernet-based bandwidth service at the following rates: 5, 10, 20 & 50Mbps. -Wavelength Service - Provides connectivity from a chosen location to a Regional Gateway or from a Regional Gateway to a Global Gateway. This is a wavelength-based service and is available at the following rates: 2.5 & 10Gbps The speed tiers available across the variety of service offerings are; 5, 10, 20, 50, & 100 Mbps and 1, 2.5, 5 & 10 Gbps. Note that the Boston Transport service includes an offering that is scalable in 20Mbps increments. | MassTech has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 17 | 0 | 0 | 9 | Ahead on baseline by 4; interest of service providers has exceeded expectations held at the time of grant submission. | MassTech interpreted the baseline differently and is now categorizing all signed agreements as "receiving new access" and does not expect to categorize any agreements as "receiving improved access". | Per NTIA guidance, MassTech now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MassTech now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 1Gbps-(6), 10Gbps-(1) Note: The counts above represent active services being provided to paying wholesalers or service providers. | 786 | 785 | 1 | 9 | Behind on baseline by 602, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 1237 CAIs receiving service at the end of the project. | Behind on baseline by 475, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 1080 CAIs receiving "new access" at the end of the project. | Behind on baseline by 127, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 157 CAIs receiving "improved access" at the end of the project. | 5Mbps-(14), 10Mbps-(7), 20Mbps-(2*), 50Mbps-(1), 100Mbps-(3), 1Gbps-(3), 10Gbps-(1). Note: The counts above represent active services being provided to paying CAI customers *-Includes 1 incremental "to scale" Boston Transport service customer whose total provided bandwidth is 300Mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MassTech offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | Permitting -Receive final pole licenses for the remainder of the project Construction -Complete installation of network equipment at Community Anchor Institution sites. -Complete fiber terminations at Community Anchor Institution sites. -Complete fiber installation for final pole licenses and Underground work to be performed with release of latest AAR Acceptance Testing -Complete acceptance testing of Points of Interconnection sites -Complete acceptance testing of Community Anchor Institutions -Complete acceptance testing of additional fiber segments -Complete turnover of additional network segments to Network Operator Sustainability -Continue marketing initiatives and achieve additional Connecting Agreements as segments become operational -Conduct Community Outreach meetings in the service area | Massachusetts Technology Park | This past quarter we have begun to wind down construction activities. Our challenges now are completing fiber and CAI testing and final review of test results and documentation. | Since the project is now nearing completion, the challenge going forward is to ensure thorough review and quality of the documentation for the network and clean-up of punch list items to ensure operational efficiency.
NT10BIX5570070 | 2013 | Q4 | Q4 - 2013 | MassBroadband 123 accomplishments for the quarter ending December 31st, 2013: Completion of 19 (of 954) new miles and 0 (of 229) new leased miles and 0 (of 57) upgraded miles (for a total of 1240 miles*); 290 (of 1095) new CAIs and 109 (of 143) improved CAIs (for a total of 1238 CAIs). (* - MBI has 57 upgraded miles associated with I-91 that we are in the processing of removing from the grant. End-of-project upgraded miles are expected to be 0 and total miles are expected to be 1,183.) Make Ready and Licensing -Received 125 Verizon pole licenses for a total of 32,638 (99% complete). -Received 128 electric utility pole licenses for a total of 30,330 (99% complete). Network Design and Construction -Installed 3 miles of messenger strand for a total of 883 miles for the project (99% complete). -Installed 23 miles of aerial fiber optic cable for a total of 998 cable miles (including slack and sag) for the project (99% complete). -Installed 792 feet of conduit for a total of 48,365 feet for the project (98% complete). -Completed 15 additional Community Anchor Institution site installations of a total of 789 locations for the project (99% complete). -Completed 399 additional Community Anchor Institution fiber terminations/testing of a total of 1231 for the project (99% complete). -Completed 12 Point of Interconnection and collocation site installations of a total of 39 for the project (100% complete). Network Testing and Turnover -Completed turnover of 12 new Points of Interconnection to Network Operator (70% complete). -Completed turnover of 18 network segments to Network Operator (67% complete). -Completed turnover of 200 Community Anchor Institution locations to Network Operator (16% complete). Sustainability -Executed 1 additional connecting agreements with broadband wholesalers or last mile providers for a total of 18. Jobs Created or Retained -The total number of jobs created or retained during the quarter was 45.22. | 950 | 229 | 57 | 0 | 950 | 0 | 0 | 39 | Behind on baseline projection by 26 miles due to slower-than-expected make ready completion and previous construction holds. Note: Updated projections documented in an upcoming AAR shift the expected total miles deployed to 954. | Behind on baseline projection by 78 miles. Lease miles reduced from 307 to 192.5 per approved AAR due to switch to all dark fiber IRUs. End of project new leased miles are expected to be 229. | After consultation with NTIA, it was determined that all existing miles upgraded were removed from the project and replaced with cash-match. This will result in a 55 mile reduction from baseline and a 57 mile reduction in total project miles. End of project miles in this category will be 0. | N/A | Behind on baseline by 102 miles due to a 78 mile reduction in IRU miles, a 55 mile reduction in existing in-kind contribution for I-91, 2 miles remaining to be constructed, and 2 miles that will be removed from scope in a future AAR. The end-of-project total miles are expected to be 1,183. | N/A | N/A | Ahead of project baseline by 17. The target number of POIs has been changed to 39 due to the addition of POIs for connections to municipal IRUs and reclassification of some locations from CAI to POI. MassTech has completed the new connection at all Point of Interconnection locations except for three tower locations that are going to be removed from scope. | 18 | 1 | 76 | -Axia Networks, USA -Massachusetts Executive Office of Public Safety and Security (EOPSS) -Massachusetts Information Technology Division (ITD) -Crocker Communications -FTG Technologies -Center for Education Leadership (CELT) -Access Plus -Community WISP, Inc. -Streamline Networks -Cornerstone Communications -Holyoke Gas & Electric -MECnet -Ayacht Technology Solutions -Warwick Broadband Service -Berkshire Unified Phone -WiredWest -Lightower -Windstream NOTE: The average term of signed agreements in 5a reflects the average length of fixed-term contracts. | Wholesale services currently being provided are: -Ethernet-100 Service - Ethernet-based bandwidth services that provide up to 100% of the line rate speed of the physical connection. It services a single User Network Interface (UNI) and a single Virtual Private Network membership (VPN). -NNI (Network-to-Network Interface Service) - Allows customers to access "off-net" services determined by the customer network. -Gigabit Ethernet Boston Transport Service - Provides connectivity from either network Regional Gateway to the Boston Global Gateways at the following speeds: 20 Mbps increments, 1, 2.5, & 5Gbps. -Broadband Service - Provides Ethernet-based bandwidth service at the following rates: 5, 10, 20 & 50Mbps. -Wavelength Service - Provides connectivity from a chosen location to a Regional Gateway or from a Regional Gateway to a Global Gateway. This is a wavelength-based service and is available at the following rates: 2.5 & 10Gbps The speed tiers available across the variety of service offerings are; 5, 10, 20, 50, & 100 Mbps and 1, 2.5, 5 & 10 Gbps. Note that the Boston Transport service includes an offering that is scalable in 20Mbps increments. | MassTech has hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They will also assist with equipment specifications and network and fiber design during the construction period. Tim Scott, Vice President, may be contacted at Tim.Scott@axia.com | 18 | 0 | 0 | 9 | Ahead on baseline by 5; interest of service providers has exceeded expectations held at the time of grant submission. | MassTech interpreted the baseline differently and is now categorizing all signed agreements as "receiving new access" and does not expect to categorize any agreements as "receiving improved access". | Per NTIA guidance, MassTech now lists service providers who receive access to both lit and dark services on the primary method they will use to obtain services. MassTech now anticipates that all service providers will primarily receive lit services, causing the value to remain at zero. | 5Mbps-(0), 10Mbps-(0), 20Mbps-(0), 50Mbps-(0), 100Mbps-(0), 1Gbps-(6), 2.5Gbps-(0), 5Gbps-(0), 10Gbps-(1) Note: The counts above represent active services being provided to paying wholesalers or service providers. | 1231 | 1088 | 143 | 9 | Behind on baseline by 157, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 1238 CAIs receiving service at the end of the project. NOTE: Although 399 CAIs were completed this quarter, the total reported CAI count has increased by 445 over last quarter. Prior PPR submittals had accidentally excluded a small number of CAIs that were activated during the quarters in question. This submittal's numbers are trued up and include an accurate total count of all served CAIs as of 12/31/13. | Behind on baseline by 172, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 1095 CAIs receiving "new access" at the end of the project. | Ahead of baseline by 15, MassTech considered CAI connections as occurring upon installation of systems, but is now reporting based on when Community Anchor Institutions are spliced to its serving POI. MassTech anticipates 143 CAIs receiving "improved access" at the end of the project. | 5Mbps-(14), 10Mbps-(7), 20Mbps-(2*), 50Mbps-(2), 100Mbps-(3), 1Gbps-(3), 2.5Gbps-(0), 5Gbps-(0), 10Gbps-(1). Note: The counts above represent active services being provided to paying CAI customers *-Includes 1 incremental "to scale" Boston Transport service customer whose total provided bandwidth is 300Mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MassTech offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | Project Close-Out -Complete final acceptance testing -Complete all punchlist items MBI plans for end of project counts to be; Total Miles Deployed: 954 New, 229 Leased, and 0 Upgraded Miles Total CAIs Deployed: 1,095 New and 143 Improved CAIs Total Agreements Executed: 18 Broadband wholesaler/last mile provider agreements A budget revision request will be submitted to address a decrease in the federal percentage of the project as well as any other modifications deemed necessary to account for final project changes through January 31, 2014, the federal award end date. | Massachusetts Technology Park | Our challenges now are completing fiber and CAI testing and final review of test results and documentation. | The challenge going forward is to ensure thorough review and quality of the documentation for the network and clean-up of punch list items to ensure operational efficiency.
NT10BIX5570070 | 2014 | Q1 | Q1 - 2014 | On July 1, 2010, the National Telecommunications and Information Administration (NTIA) awarded the Massachusetts Broadband Institute (MBI) $45.4 million for its MassBroadband 123 (MB123) project to build new fiber networks in western and central Massachusetts to bridge the digital divide in the state and to provide the foundation for economic growth and opportunity in the region. MB123 was successfully completed on January 31, 2014 with additional state matching funds totaling $35.6 million and a total project budget of $81 million. MB123 built 949 miles of new fiber-optic network and leased 231 miles through 133 communities including 43 previously unserved or underserved towns in western and central Massachusetts, connecting 1,233 community anchor institutions (CAI). The largely aerial network provides a fiber-based broadband infrastructure that runs within 3 miles of 98% of households, CAIs, and businesses in the service area, offering 39 network equipment nodes to allow easy interconnection and to facilitate future expansion of the network. MBIâ€™s network operator and private sector partner Axia NGNetworks USA (â€œAxiaâ€) offers wholesale connectivity to 19 network service providers with speed tiers from 5 Mbps to 10 Gbps. The availability of high-speed broadband and provider choice is a boon to many CAIs that previously only had access to T1â€™s, satellite, or DSL lines and little or no choice of provider. As an example, MB123 has enabled multiple providers to serve CAIs in the towns of Otis, Pittsfield, South Egremont and Springfield, introducing competition in the market for the first time. The success of MB123 can be attributed to MBIâ€™s broad range of collaborations and partnerships, including the Mass Executive Offices of Housing and Economic Development (EOHED), and Public Safety and Security (EOPSS) and the Information Technology Division (ITD), Axia, local service providers, regional planning agencies, grassroots broadband groups like WesternMA Connect and Wired West, and local governments in the project footprint. MB123 has enabled EOPSS to transition western MA public safety sites onto the new network, increase bandwidth to the Criminal Justice Information System from 56 Kbps to 50 Mbps while saving $36,000 per year and enabling Next Generation Identification systems such as facial recognition and advance fingerprinting, and to connect all fifty EOPSS E911 primary public safety answering points in the service area. Locally, MB123 has enabled the South Hadley Electric Light Department (â€œSHELDâ€) to deploy electronic meter readers to obtain real-time information on the use and status of the electric grid, e.g., detecting outages immediately and reducing the response times for repair. In the Southwick-Tolland-Granville School District, their new 100 MB connection enables online teacher training, allowing administrators to track ongoing teacher evaluations online. A remote desktop application now being piloted will enable students and parent to access educational software and applications hosted at the school from home. Through the Center for Education Leadership and Technology (â€œCELTâ€), small, rural schools in western Massachusetts will have access to the broadband speeds required to implement online testing, some of which have also rolled out iPad and tablet initiatives to provide students with personalized technology in the classroom. Every healthcare provider in the state is required to use electronic health records connected to the health information exchange by 2017. In addition the Massachusetts eHealth Institute (MeHI) will be required by 2017 to test image exchange services among healthcare providers. This exchange would not be possible for many of the providers in western Massachusetts without connectivity through the new network. Franklin Regional Council of Governments (â€œFRCOGâ€) expects that MB123 will help Boards of Health in Franklin County report cases of contagious diseases to the Massachusetts Virtual Epidemiologic Network (MAVEN), a database reporting system for contagious diseases. Before MB123, the Boards of Health were not able to access MAVEN. Finally, more affordable middle mile speeds has enabled last mile providers like Crocker Communications, Phoenix Communications, and Westfield Gas and Electric to expand their businesses and hire more workers while the town of Leverett passed a municipal bond to fund a fiber to the home network connected to the MB123. MB123 will enable libraries on the MARS system to download and share greater amounts of bibliographic data and participate in remote video conferencing and training, including digital audiobooks and literacy training for the public. DSCI, the service provider for MAâ€™s voter registration system, won the bid based on using the MB123 network to provide connectivity to sites in western MA. They currently have 10 orders in for service. | 949 | 231 | 0 | 0 | 1180 | 0 | 0 | 39 | Baseline projection was 976 and the 27 mile variance is due to route changes, as described more fully in MassTech's approved route modifications. (The 949 reported here differs from the UCC reported 933 total fiber miles due to additional fiber footage caused by sag between poles). | Baseline projection was 307 and we are under by 76 miles. Lease miles reductions were due to a switch to all dark fiber IRUs, as described more fully in MassTech's approved route modifications. | After consultation with NTIA, it was determined that all existing miles upgraded be removed from the project and replaced with cash-match, which resulted in a 55 mile reduction from the baseline. The baseline included 55 miles of existing in-kind contribution for I-91. The I-91 contribution was increased by 1.6 miles in 2012, but then the entire I-91 contribution was removed, as described more fully in approved route modifications. | N/A | Baseline projection was 1338 and the variance of 158 miles is due to a 76 mile reduction in IRU miles, a 55 mile reduction (from the baseline) for the I-91 contribution, and a 27 mile reduction in new network routes due to approved route change modifications. | N/A | N/A | Baseline projection was 22. The number of POIs was changed to 39 due to the addition of POIs for connections to municipal IRUs and reclassification of some locations from CAI to POI. | 19 | 0 | 76 | -Axia Networks, USA -Massachusetts Executive Office of Public Safety and Security (EOPSS) -Massachusetts Information Technology Division (ITD) -Crocker Communications -FTG Technologies -Center for Education Leadership (CELT) -Access Plus -Community WISP, Inc. -Streamline Networks -Cornerstone Communications -Holyoke Gas & Electric -Addition Networks (formally MEC Net) -Ayacht Technology Solutions -Warwick Broadband Service -Berkshire Unified Phone -WiredWest -Lightower -Windstream -DSCI NOTE: The average term of signed agreements in 5a reflects the average length of fixed-term contracts. | Wholesale services being provided are: -Ethernet-100 Service - Ethernet-based bandwidth services that provide up to 100% of the line rate speed of the physical connection. It services a single User Network Interface (UNI) and a single Virtual Private Network membership (VPN). -NNI (Network-to-Network Interface Service) - Allows customers to access "off-net" services determined by the customer network. -Gigabit Ethernet Boston Transport Service - Provides connectivity from either network Regional Gateway to the Boston Global Gateways at the following speeds: 20 Mbps increments, 1, 2.5, & 5Gbps. -Broadband Service - Provides Ethernet-based bandwidth service at the following rates: 5, 10, 20 & 50Mbps. -Wavelength Service - Provides connectivity from a chosen location to a Regional Gateway or from a Regional Gateway to a Global Gateway. This is a wavelength-based service and is available at the following rates: 2.5 & 10Gbps The speed tiers available across the variety of service offerings are; 5, 10, 20, 50, & 100 Mbps and 1, 2.5, 5 & 10 Gbps. Note that the Boston Transport service includes an offering that is scalable in 20Mbps increments. The Pricing Plan from 2012, included as an attachment to this PPR in PAM remains in effect as of the end of the project, | MassTech hired Axia NGNetworks USA as a contractor to run the entirety of the MassBroadband 123 network. They also assisted with equipment specifications and network and fiber design during the construction period. Axia will continue to run the network beyond the grant period. Contact information for Axia is: Mark Blake Vice President, Government Services Axia NetMedia Corporation Suite 3300, 450 1st Street SW Calgary, AB Canada T2P 5H1 ph +1 403 538 4180 | 19 | 0 | 0 | 9 | Baseline target was 5. The variance is related to the interest of service providers exceeding expectations held at the time of grant submission. | Baseline target was 8. MassTech interpreted the baseline differently and categorized all signed agreements as "receiving new access". | Baseline target was 4. Per NTIA guidance, MassTech included service providers who receive access to both lit and dark services on the primary method they will use to obtain services. All service providers primarily receive lit services, causing the value to remain at zero. | 5Mbps-(0), 10Mbps-(0), 20Mbps-(0), 50Mbps-(0), 100Mbps-(0), 1Gbps-(6), 2.5Gbps-(0), 5Gbps-(0), 10Gbps-(1) Note: The counts above represent active services being provided to paying wholesalers or service providers. | 1233 | 1090 | 143 | 9 | Baseline target was 1392, and the 159 variance is due to CAIs moving, being duplicates, not being present, declining to participate, or construction issues, as described more fully in MassTech's approved CAI modifications. MassTech completed 5 CAIs in 1Q14. A complete audit of CAIs was conducted in September of 2014, resulting in a final CAI count of 1233, which was listed in the addendum to MassTech's final APR. | Baseline target was 1264, and the 174 variance is due to CAIs moving, being duplicates, not being present, declining to participate, or construction issues, as described more fully in MassTech's approved CAI modifications. | Baseline target was 128, leading to being ahead of baseline by 15. This variance is as a result of a municipality or the state already having an existing network and may allow a CAI to receive improved broadband or backhaul through the MassBroadband 123 network using their own pre-existing fiber. Where possible, MassTech attempts to avoid over building when a municipality already has an existing fiber network in place. These changes are described more fully in MassTech's approved CAI modifications. | 5Mbps-(93), 10Mbps-(44), 20Mbps-(30*), 50Mbps-(9), 100Mbps-(47), 1Gbps-(5), 2.5Gbps-(0), 5Gbps-(0), 10Gbps-(11). Note: The counts above represent active services being provided to paying CAI customers *-Includes 1 incremental "to scale" Boston Transport service customer whose total provided bandwidth is 300Mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | MassTech offers a 15% discount off of wholesale rates to our state partners, Information Technology Division and Executive Office of Public Safety and Security. Our state partners contributed matching funds to the MassBroadband 123 grant application and they have committed to being an anchor tenant on the new network. | FALSE | N/A | The primary focus of MassTech and MBI activities in the next quarter will be around finalizing MassBroadband 123 project and grant close-out activities. Beyond project close-out, MassTech and MBI will be actively engaged in overseeing network operations by Axia, studying CAI and service provider network adoption and working closely with state, local and private sector partners to educate municipalities and CAIs about the benefits of the new infrastructure. The ability to purchase service from multiple service providers competing on an open access middle-mile fiber infrastructure is completely new for municipalities and CAIâ€™s in previously unserved or underserved locations. Also new for many of them is the ability to converge telephone and data services through one connection, or the ability to create Virtual Private Networks that connect CAIs and municipalities as if they are on a shared local area network. The opportunities for collaboration, regionalization, and sharing of services are limited only by lack of education and imagination. Beyond the January 31, 2014 grant end date, Masstech and MBI will work with municipalities and CAIs to help them understand the opportunities before them, to highlight early adopter stories and uses, and to offer technical assistance where needed to assist with adoption and sustainability of the network. Building a middle-mile network was a first important step in closing the digital divide that exists in Massachusetts. However, as of January 31, 2014 there are still 45 communities in western Massachusetts whose residents and businesses are without broadband capable infrastructure. Axia has completed its first few network extensions to businesses that were not a part of the scope of the BTOP grant. Axia continues to provide cost estimates to service providers for other new network extensions. As the state entity charged with leading efforts to address broadband access solutions, the MBI is well positioned to continue its partnership with Axia, state officials, western and central Massachusetts communities, and stakeholder organizations across the region and state to identify the challenges and research and develop the full range of sustainable solutions that leverage MassBroadband 123 to bring broadband access to these unserved and high-cost areas. FRCOG continues to promote the use of broadband for municipalities to help town governments operate more efficiently and spur economic development. For example, the county has volunteer Boards of Health at the municipal level, and volunteers have to travel to Boston for training. FRCOG continues to encourage towns to transition to video conference training so the volunteers do not have to miss a day of work and spend money traveling to Boston. Axia expects to further spur economic growth by building demand-based fiber extensions from the MB123 network to businesses, government agencies, residential neighborhoods and residences, and other locations that were not connected during the grant. Axia also plans to provide opportunities for service providers to build from the network. Axia has worked with service providers on the network to build network extensions to businesses in the region and continues to research these opportunities and the cost for additional infrastructure investments to expand the network. Massachusetts is fortunate to have strong political leadership at the executive and legislative level that understands the importance of broadband to ensure our communities and citizens remain competitive in the global economy. In 2013, Governor Patrick filed bond legislation authorizing up to $40 million in new funding for the MBI to develop last-mile solutions that build off the middle-mile network to bring broadband connectivity directly to homes and businesses in underserved western and central Massachusetts communities. The funding was increased to $50 million by the House of Representatives in November of 2013 and was passed in August of 2014. MassTech and MBI continues to work diligently with our partners and the local communities to understand the best way to utilize the new funding to meet our common goal of near universal broadband access. | Massachusetts Technology Park | Our challenges in the last quarter were completing fiber and CAI testing and final review of test results and documentation. | Not Applicable
NT10BIX5570071 | 2010 | Q4 | Q4 - 2010 | Sent out Environmental Assessment (EA) and Route Development (RD) Request for Proposal (RFP). Received Quotes and went through evaluation and award process. Zayo awarded to the lowest bidder based on a competitive bid process. Our EA and RD subcontractor is now 70% complete with our EA and RD. Zayo is in the process of requesting some route changes. Part of our original route included some limited Right of Way (ROW), Zayo has done a small reroute that take the limited ROW out of the plan. Zayo has started preliminary review of these changes with the government. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | This project is a middle mile project. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Zayo is a middle mile provider and special offerings will be made by last mile providers. | FALSE | N/A | Zayo should have our Engineering Request for Proposal (RFP) out by the next quarter, we should have them back and we should make our award based on a competitive bid process. Our Engineering firm should have a significant amount of the engineering done. | Zayo Bandwidth, LLC | Zayo had an issue with this grant not being available in the ASAP payment system. By working with our grants officer, we were able to work through this issue after about a month. | Zayo is not anticipating any issues at this time.
NT10BIX5570071 | 2011 | Q1 | Q1 - 2011 | Zayo has been experiencing issues with getting our EA FONSI. Zayo submitted our draft EA on time, but has run into delays getting SHPO approval on the underground segments of our routes. Our EA subcontractor has had to bring in an Archeologist to confirm that our route is following pre-disturbed ground only. Zayo had to request an EA extension in January which BTOP approved. Because of the delay in getting our FONSI, Zayo has had to revise our 9 month budget to include money to start engineering. Sent out Engineering Request For Proposal (FRP) to 19 vendors. Zayo received bids and went through our competitive bid process. The Engineering was awarded to Fiber Engineering and Design. Fiber Engineering and Design had the lowest price. They did not receive points for being a local company, but they did receive points for being a small business. Fiber Engineering and Design is a New Jersey company, but they have committed to hiring local employees to supplement their staff. To date, they have hired three employees from Minnesota. Sent out RFP for Inside Plant Engineering and Design. Received bids back at the end of the quarter. Zayo will do source selection and award at the beginning of next quarter. Sent out Materials RFP. Zayo has received bids as of the end of the quarter. Zayo will make this award at the beginning of next quarter after doing our source selection process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | This project is a middle mile project. Wholesale services will be provided by last mile service providers. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Zayo is a middle mile provider and special offerings will be made by last mile providers. | FALSE | N/A | Zayo should have our FONSI as well as our materials contract awarded. We should have purchased our fiber optic cable as well as other materials. We hope to have our engineering and permitting well on it's way. | Zayo Bandwidth, LLC | N/A | The only thing that may hinder Zayo is getting permits approved by some of the utility companies. Zayo is trying to mitigate this risk by being more proactive with the utility companies. Zayo is submitting our final EA and once we have our FONSI we should be able to catch up as indicated above.
NT10BIX5570071 | 2011 | Q2 | Q2 - 2011 | Zayo received our FONSI. Zayo has almost completed engineering and is also applying for permits. Zayo also awarded Inside Plant Engineering and Design. Awarded Materials contract. Zayo secured warehouse space from Anoka County to store materials and Fiber Optic Cable. Zayo plans on bidding out construction of 50 miles of route by next quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This is a 26 mile variance from our baseline because of the permitting delays. We should be caught up by next quarter. | N/A | N/A | N/A | This is a 26 mile variance from our baseline because of the permitting delays. We should be caught up by next quarter. | N/A | N/A | This is a variance of 20 from our baseline. This is because of the delays in starting construction. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | This is a variance of 5 from our baseline because of the delays in starting construction. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Zayo plans to have materials ordered and start stocking our warehouse. We hope to be further along with permitting and start bidding certain segments of the build based on the issuance of permits. | Zayo Bandwidth, LLC | The Minnesota State Government has been shut down since July 1, 2011 and it has not been resolved as of the date of this report. It is Zayo's understanding that the state permitting agencies were 6 weeks behind on permitting before the shutdown. If the shutdown goes for three or four weeks this could a delay of ~10 weeks. Zayo also had some issues with limited ROW's. Zayo has found existing conduit along most of the areas where this exist. Zayo has submitted purchase requests to BTOP to allow us to purchasing this existing conduit to help us avoid the limited ROW areas and BTOP is working to approve. | The biggest challenge that Zayo sees coming up is trying to catch up with our baseline plan after the Minnesota State shutdown. It is hard to predict at this particular time how far we will be behind and how much we will have to catch up until after the shutdown ends so that we know how much time we have missed. We are figuring that if this delay goes on for another 3 weeks this could result in a 9 week delay as it is our understanding that the permitting agencies were 6 weeks behind before the shutdown. Zayo will continue to contact CAI's and last mile providers as we build out. Even with delays, it is Zayo's plan to be 90% complete by the end of the first eight quarters.
NT10BIX5570071 | 2011 | Q3 | Q3 - 2011 | Zayo had our ground breaking ceremony this quarter in Anoka County. This event was well attended by Zayo, representatives of the Anoka County Government and BTOP. There was a strong showing of community support for the project as well. Zayo had our government program site visit scheduled for the three days following this event. Zayo felt that this was a very productive visit with positive and constructive feedback on both sides. Zayo also sent representatives to the BTOP meeting held in Cleveland this quarter to share best practices and learn from other BTOP awardees about challenges faced and how to best overcome these. Zayo was also able to issue our first RFP for construction of our first 5 segments (~70 miles) of construction. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is 26 miles behind based on our baseline because of permitting issues and our efforts to avoid excessive pole change out costs. Zayo will be back on track by the end of next quarter. | None | None | None | Zayo is 26 miles behind based on our baseline because of permitting issues and our efforts to avoid excessive pole change out costs. Zayo will be back on track by the end of next quarter. | None | None | This is 5 off of our baseline and this is because of the construction delays discussed in section 3 of this report. | 0 | 0 | 0 | None | N/A | N/A | 0 | 0 | 0 | 0 | This is in line with our baseline. | This is 5 off of our baseline because of the construction delays discussed in section 3. | This is in line with our baseline. | No variance. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | N/A | FALSE | N/A | Zayo should have ~50 miles of network built. | Zayo Bandwidth, LLC | Zayo has run into issues with some of our pole providers. Because of these issues, Zayo is working on amending our Environmental Assessment (EA) to allow us to dip underground in certain areas to avoid excessive costs associated with pole change out. | Zayo has run into issues with some of our pole providers. Because of these issues, Zayo is working on amending our Environmental Assessment (EA) to allow us to dip underground in certain areas to avoid excessive costs associated with pole change out.
NT10BIX5570071 | 2011 | Q4 | Q4 - 2011 | Zayo requested a Termination for Convenience with an effective date of 9/30/11 for this project. Zayo Bandwidth, LLC was absorbed by its parent Zayo Group, LLC. Zayo has asked for a termination for convenience of the current grant and is asking NTIA and BTOP to reissue the grant under a new grant to Zayo Group, LLC. Zayo is pursuing this course of action under the direction of NTIA and BTOP. Zayo is continuing to build and fully commit to this project because of our commitment to both the project and or faith in the NTIA and BTOP. Zayo has continued to build and is actually at 33% build based on dollars spend and 17% based on actual miles built (45 miles of 268). This information will be on the first quarter report of our new award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is 26 miles behind our baseline because of permitting issues. | None | None | None | Zayo is 26 miles behind our baseline because of permitting issues. | None | None | Thisis 5 off our baseline because of construction delays discussed above. | 0 | 0 | 0 | None | None | None | 0 | 0 | 0 | 0 | This is in line with our baseline. | This is 5% behind our baseline because of construction delays. | This is in line with our baseline. | No Variance. | 0 | 0 | 0 | 0 | No Variance. | No Variance. | No Variance. | No Variance. | 0 | 0 | 0 | 0 | 0 | No Variance. | No Variance. | No Variance. | No Variance. | No Variance. | 0 | 0 | 0 | 0 | 0 | No Variance. | No Variance. | No Variance. | No Variance. | No Variance. | None | FALSE | None | Grant should be terminated. | Zayo Bandwidth, LLC | Please refer to the current progress of this project in #1 above. | This award should be terminated for convenience.
NT10BIX5570072 | 2010 | Q4 | Q4 - 2010 | In the fourth quarter of 2010 and the 2nd quarter of the Com Net GigEPAC project, Com Net satisfied several Special Award Conditions including non-overlap requirements with other federally funded projects, baseline report and quarterly reporting requirements in October. As part of its non-overlap SAC, Com Net finalized details for a joint build with Sycamore Telephone Company, a Round 2 BIP recipient, whom Com Net had entered into an agreement to do such in the event both projects were awarded. This collaborative effort provides for cost avoidance through a mutually beneficial relationship. The environmental assessment team completed desk reviews and drive-outs of all proposed routes for construction noting any variations from its application. Com Net initiated consultation with all necessary agencies as required in preparation of submitting its Environmental Assessment Report. Com Net continued its community outreach efforts meeting with representatives of local, county and state government, community colleges, colleges and universities, K-12 school district representatives, broadband service providers, data centers and carriers. Com Net continued to work with its primary construction firm, Kenneth G. Myers Construction, to pre-certify prevailing wages on its project which spans across multiple Metropolitan Service Areas (MSAs). Com Net prepared for the finalization and release of several requests for proposal to select vendors including RFPâ€™s for Project Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | SAC Period - Zero VariancThe EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commencer reasons for any variance from the baseline plan or any other relevant information) The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | 5 | 17 | 80 | Sycamore Telephone Company - Round 2 BIP Recipient Last Mile Provider with an executed agreement to conduct a joint build if both applications are awarded. Tier 2 Communications, LLC - An affiliate of Com Net, Inc agreeing to provide last mile connectivity services when not available through other GigEPAC partners, Independents Fiber Network, LLC - An Ohio Interexchange Company that is a wholly owned subsidiary of Com Net, Inc with a certificate of public necessity and convenience. ZAYO Bandwidth – A GigEPAC subrecipient OARnet – A GigEPAC subrecipient • Subrecipients have a binding letter commitment based on GigEPAC project being funded 2 BIP Recipient Last Mile Provider with an executed agreement to conduct a joint build if both applications are awarded. Tier 2 Communications, LLC - An affiliate of Com Net, Inc agreeing to provide last mile connectivity services when not available through other GigEPAC partners, Independents Fiber Network, LLC - An Ohio Interexchange Company that is a wholly owned subsidiary of Com Net, Inc with a certificate of public necessity and convenience. ZAYO Bandwidth – A GigEPAC subrecipient OARnet – A GigEPAC subrecipient • Subrecipients have a binding letter commitment based on GigEPAC project being funded | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no Wholesale Services are available, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no Wholesale Services are available. | Subrecipients Zayo (400 Centennial Parkway, Suite 200; Louisville, CO 80027; 1.303.381.4683) and OARnet (1224 Kinnear Rd. Columbus, Ohio 43212, 614-292-9191) will be designated to operate a portion of the network on activation based on specific fiber spans the providers will be responsible for operating certain fiber within. The specific portions of the network will be detailed on activation. To date the EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no portion of the network is available for a third party to operate. | 0 | 0 | 0 | 0 | No Variance | Variation from Baseline report. Baseline report was completed with understanding provider count was reported based on those with a signed agreement to receive improved access rather than those with a signed agreement and actively receiving improved access. This variation is expected to existing until the third quarter 2011. | Variation from Baseline report. Baseline report was completed with understanding provider count was reported based on those with a signed agreement to receive dark fiber rather than those with a signed agreement and actively having access to such dark fiber.This variance is expected to exist until the third quarter of 2011. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no speed tiers are available. | 0 | 0 | 0 | 0 | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscriber are served. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are receiving new access. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are receiving improved access. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are being served as no speed tiers are available. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | In the 1st Quarter of 2011 Com Net plans to receive a FONSI on its Environmental Assessment Report. Com Net plans to award its RFP for outside plant materials and take the initial shipment of materials into the cable yards of Kenneth G. Myers Construction. Com Net plans to award its RFP for DWDM electronics/optronics, receive shipment of a lab unit to familiarize staff with operating and management systems. Com Net plans to places orders for the initial set of DWDM units inclusive of site installation. Com Net plans to award its Remote Huts RFP, finalize acquisition of its site in Paulding County and initiate site preparation. Com Net will award its Inspection Firm RFP and have the contract in place with the firm by March 1, 2011. Com Net will finalize it's RFP for Auditor Firm and release it for responses prior to the end of March 2011. Com Net will break ground on its fiber-optic plant routes in western Ohio in March 2011. Lastly Com Net will initiate construction in Allen County, Ohio that will establish a new connection to Customer Provide Access fiber facilities of a K-12 educational institute that will result in improved service through increased capacity and survivability to 38 school districts which will be completed in the second quarter of 2011. Com Net's Route Design Firm will continue to finalize route design and permit applications ahead of construction at a pace of approximately 60-80 miles per quarter. | COM Net, Inc. | In terms of areas or issues where assistance from the BTOP program may be useful, the major area would be additional webinars on various aspects of the BTOP program, the various types of award action requests available through grants on-line and when they should be utilized, requirements and reporting utilities as early in the program as possible. These webinars are extremely beneficial in expanding knowledge amongst staff strengthening the depth of our team. This distant learning andtraining is extremely valuable in expanding the the depth and knowledge of staff while maximizing productivity and avoiding unnecessary travel expenses. In terms of challenges or issues faced the most significant was accelerating the learning curve inside our organization as a first-time grant recipient, while attempting to satisfy Special Award Conditions under an aggressive timeline for our organization. The management of legacy operations, the federally funded project and motivation of employees proved challenging as year-end approached. As key deadlines came due on the funded project in November thru January along with those associated with legacy operations, the pressure mounted. The situation was further complicated as frustrations arose as employees were unable to obtain timely responses from third parties as the holiday season set in with Thanksgiving. Com Net was able to manage through this period with only one resignation as a result of the demanding period. Com Net cont | The major challenge for the 1st quarter of 2011 involve timely completion of the Environmental Assessment Report and receipt of the FONSI for the project. In the event the timing for the receipt of the FONSI is unfavorable to the baseline, the issue we will face will be balancing the budget against the need to expedite route construction in order to realize sixty-seven percent completion by the end of Year 2 of the project. The other major challenge for the 1st quarter of 2011 will be lead time requirements on Outside Plant fiber optic cable as well as DWDM electronics/optronics. These challenges are common ramp-up issues at the time of project start-up when demand is exceeding supply of a critical material item in the project. Com Net projects that this shortfall will be made up in the third quarter of 2011 once the inventory is fully stocked at the cable yards with a blanket order in place with pre-scheduled release dates.
NT10BIX5570072 | 2011 | Q1 | Q1 - 2011 | Com Net complied with all reporting for the fourth quarter of 2010 (Americant Recovery and Reinvestment Act (ARRA), SF-425 and quarterly Performance Progress Report (PPR)) and 2010 Annual PPR. Com Net addressed outstanding questions for satisfaction of its Special Award Conditions with the exception of the Environmental Assessment (EA), including a review of in-kind and cash match requirements. Com Net awarded its Plants Records Database bid to NISC, its Outside Plant Materials bid to Power & Telephone with Draka as primary and Corning as the alternate source for fiber cable, and its Inspector bid to Sigma Technologies. Com Net declared its intent to award the Dense Wave Divisions Multiplexing (DWDM) portion of its Optronics/Electronics bid dependent on execution of agreement. Com Net had received bids but had made no award on its Outside Plant Huts bid or the MPLS Network Equipment portion of its electronics/optronics bid. Com Net developed but was holding its request for proposal for a project specific auditor until April 15 or NTIA audit guidelines for For-Profit companies being formally released. Com Net issued a Request for Quote on upgrade cards for the CISCO 7606 located in Worthington, OH made part of the project in 2010. Com Net selected the low cost bidder on upgrade cards to the CISCO 7606 located in Worthington, OH. Com Net was in the process of finalizing agreements with Power-n-Telephone and issued Purchase Orders for Materials associated with 31 rout | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commencer reasons for any variance from the baseline plan or any other relevant information) The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced | 3 | 26 | 60 | One Community - Master Service Agreement being finalized along with initial service order Reported prior quarter: Sycamore Telephone Company, Tier 2 Communications, LLC, Independents Fiber Network, LLC â€¢ Sub-recipients included in Q4 2010 report will not be included going forward. | The service to be offered pursuant to the above referenced agreements is Ethernet Transport Services (ETS), hower the EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no Wholesale Services are availablet to the above referenced agreements is Ethernet Transport Services (ETS), hower the EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no Wholesale Services are available. | Subrecipients Zayo (400 Centennial Parkway, Suite 200; Louisville, CO 80027; 1.303.381.4683) and OARnet (1224 Kinnear Rd. Columbus, Ohio 43212, 614-292-9191) will be designated to operate a portion of the network on activation based on specific fiber spans the providers will be responsible for operating certain fiber within. The specific portions of the network will be detailed on activation. To date the EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no portion of the network is available for a third party to operate. | 0 | 3 | 0 | 0 | No Variance to Baseline. | Positive Variance of +2 to Baseline report. | Negative Variance of 1 to Baseline report. Initial projection was that provider was interested in managed dark fiber, but final decision was to pursue lit Metro Ethernet service to upgrade legacy DS3 TDM bachaul service for Internet Access. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no speed tiers are available. | 0 | 0 | 0 | 0 | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscriber are served. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are receiving new access. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are receiving improved access. | The EA SAC has not yet been satisfied, therefore a FONSI has not yet been granted, so network construction has not yet commenced and no subscribers are being served as no speed tiers are available. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | At the end of the quarter Com Net had not yet received its initial FONSI therefore it had no offerings available. | FALSE | Com Net had not yet received its initial FONSI therefore it had no changes to its network management practices. | Com Net fully expects to receive its FONSI, break ground on construction activities, turn-up a jointly provided service using funded facilities as a wholesaler provider to One Community through activation of a Network-to-Network Interface at 535 Scherers Court in Worthington, OH, complete activation with the K-12 educational institution in Allen County, Ohio and ramp-up outside plan construction crews to begin closing the gap against Com Net's baseline through construction project. Finalize contracts with Power-n-Telephone as for Outside Plan Materials, Sigma Technologies as Inspector Firm, NISC as Plant Records Database Software provider, selected DWDM vendor, OARnet migrated from binding MoU to formal agreement, ZAYO migrated from binding MoU to formal agreement, award MPLS Network equipment vendor, award Telecom Shelter (Huts) bid, finalize agreements on three selected hut sites, select project specific auditor, select appraiser, transfer OARnet equipment to project, transfer appraised 2 fiber legacy routes to project, secure increases in bank line of credit and begin finalizing agreements with broadband service partners. Com Net plans to initiate activities with selected project specific auditor commencing at the end of June 2011. | COM Net, Inc. | Com Net's primary challenge was in completing consultation with authorities having jurisdiction with respect to its Environmental Assessments. The other major challenge Com Net foresees will be in addressing unanticipated route changes in timely manner as we encounter and need to address street level routing as we encounter restrictions during the permitting process, during final route design prior to construction and/or conditions encountered during construction that will require timely answers in order to close time line gaps while still performing within budget. Com Net is working on procedures for addressing such changes with its NTIA program officer and with its Environmental Assessment Consultant to ensure on-going compliance is maintained throughout the project. | The major challenge Com Net foresees will be in addressing unanticipated route changes in timely manner as we encounter and need to address street level routing as we encounter restrictions during the permitting process, during final route design prior to construction and/or conditions encountered during construction that will require timely answers in order to close time line gaps while still performing within budget. Com Net is working on procedures for addressing such changes with its NTIA program officer and with its Environmental Assessment Consultant to ensure on-going compliance is maintained throughout the project. The other major items will be weather and ground conditions based on current levels of saturation, unanticipated road construction and other utility projects along planned routes, railroad permit timing, pole attachment make readies and in management of the project to minimize change orders for gap management against the timeline and to maintain the project within budget. Com Net has also received reports that the Authorities Having Jurisdiction (AHJ) in certain townships/counties are considering changes in their permitting procedures/requirements for construction in Road right of way based on workmanship by unrelated firms that occurred in the past 12-18 months. Com Net has not yet directly encountered this issue but is hearing reports of potential changes in certain areas that Com Net will be seeking right of way permits for in the upcoming months.
NT10BIX5570072 | 2011 | Q2 | Q2 - 2011 | Administration-EA-Agreements-Sales: Com Net continued to be engaged in bid management; received its Finding of No Significant Impact; executed a master service agreement to provide wholesale services to a fellow BTOP recipient; continued contract negotiations with sub-recipients, vendors, other BTOP and BIP recipients and broadband service providers; and activated connectivity to its first Community Anchor Institution using a portion of funded facilities. Network Design-RoW-Permits-Build: Com Net held a preconstruction meeting in early May to review route designs and material inventory status in existing cable yards; finalized procedures with its field inspection firm and supplied them with door hangers. Com Net entered into an agreement for construction and bonding of the initial 31.68 miles of construction; completed underground construction of approximately 13 miles of the initial 22 mile segment; field crews were ramped upon the project to two full plow teams by the end of June; received materials for a total of 70.7 route miles of construction and established with Power-n-Telephone and Draka a monthly rolling material forecasts to ensure timely supply of materials. Equipment Procurement & Deployment: Com Net received partial shipment of CYAN DWDM electronics for the initial nine sites scheduled for turn-up; initiated work on existing point of presence (PoP) sites with respect to necessary make-ready work for adequate power supply and rack space; and secured a | 0 | 1 | 12 | 308 | 309 | 0 | 0 | 5 | Negative variance of 112.38 miles of fiber from baseline, which is due to original baseline being based on receipt of FONSI by March 1, 2011 with construction commencing mid March. Actual FONSI received in May 2011 with construction commencing June 8, 2011. At the end of June, although 14 miles of fiber had been placed, no full or partial segments were tested and accepted for use by Com Net. | Negative variance of 2.9 as planned since NOACSC is providing customer-provided access to outside of 1680 Sugar Street in Lima, Ohio rather than Com Net IRUing fiber from outside of 2130 Sugar Street in Lima, Ohio to NOACSC operating center in downtown Lima. Actually less than 1 mile at about 0.05 route miles of 2 fiber that was secured through an Indefeasible Right to Use with the provider of the fiber lease to NOACSC, who was providing customer-provided access in the Lima, Ohio area. This gap is expected to increase prior to closing within 2 miles in late 2011 to early 2012. | This negative variance of 354 miles driven by delay in release to commence ground disturbing activity versus assumptions used in baseline, as well as delays in being able to deploy active equipment at legacy PoP sites. 2 Fiber in 6 route miles were lit using single fiber SFPs as 1 Gbps Network-to-Network Interfaces with NOACSC. The 296 fiber miles were not upgraded due to delays in equipment deployment, but they were put in service to provide 100 Mbps transport services from the Tiffin Mercy Hospital to One Community's Point-of-Presence in Worthington, Ohio. This variance is expected to persist through August 2012 at which time we project the gap to be closed. | This negative variance of 58 fiber miles driven by the delay in release to commence ground disturbing activity versus assumptions used in baseline. Existing facilities of Independents Fiber Network (IFN), a wholly owned subsidiary of Com Net, were made part of the project with 148 route miles of 2 fiber of an existing IRU route of Com Net and 2 fiber in 6 route miles of a legacy route owned by IFN. Com Net plans to activate two additional healthcare facilities under a meet point billed arrangement in the upcoming quarter that will require IFN to make another 48 route miles or 96 fiber-miles part of the project to realize the proposed service. This variance versus baseline is expected to increase prior to closing in June 2012 as we work to close the gap created by the later than expected start date for ground disturbing activities. | Negative variance of 172 miles primarily driven by delay in release to commence ground disturbing activity versus assumptions used in baseline. This negative variance is expected to remain through June 2012 as we work to close the gap created by the later than expected start date for ground disturbing activities. | No Variance to baseline | No Variance to baseline | Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Negative variance of 2. Com Net has made switched ethernet equipment at five (5) legacy PoP sites part of the project which are available as interconnection points. Four of the sites are occupied space of a third party such that entrance facilities, collocation or occupancy and termination to the Com Net facilities are through arrangements with the property owner/ operatorr reasons for any variance from the baseline plan or any other relevant information) Negative variance of 2. Com Net has made switched ethernet equipment at five (5) legacy PoP sites part of the project which are available as interconnection points. Four of the sites are occupied space of a third party such that entrance facilities, collocation or occupancy and termination to the Com Net facilities are through arrangements with the property owner/ operator. | 4 | 25 | 30 | One Community master service agreement finalized to establish Network to Network Interface in Worthington, Ohio. Sycamore Telephone Company, Tier 2 Communications, LLC and Independents Fiber Network, LLC. Sub-recipient agreements included in Q4 2010 report will not be included going forward. | The service to be offered pursuant to the above referenced agreements is Ethernet Transport Services (ETS) on a multi-provider meet point basis, with Com Net serving as a single point of contactt to the above referenced agreements is Ethernet Transport Services (ETS) on a multi-provider meet point basis, with Com Net serving as a single point of contact. | Subrecipients ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and OARnet (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191) will be designated to operate a portion of the network on activation based on specific fiber spans the providers will be responsible for operating certain fiber within. The specific portions of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients to operate. | 1 | 3 | 0 | 1 | Positive variance to baseline. This is the network-to-network interface established with One Community in Worthington, OH | Positive Variance to baseline of 2 | Negative variance of 1 due to delays on commencement of construction meaning no fiber is available for such transactions. | Com Net currently has one active subscriber through the established 1 Gbps Network-to-Network Interfaces placed in service to date. The VLAN service ordered on wholesale by One Community is 100 Mbps. | 3 | 2 | 1 | 2 | Negative Variance of one due to delays in commencement of ground disturbing activities from the assumption made as part of the baseline resulting in a delay in upgrade in capacity and connectivity to multiple school districts. Com Net projects to be able to upgrade service to at least 20 existing K-12 school districts and establish two new hospital connection under meet point service arrangements in the upcoming quarter. The schools have a firm order confirmation of August 1, 2011 for their upgraded capacity and establishment of back-up connectivity to their Information Technology Center. Connectivity to the two new hospitals under a meet point service arrangement have a firm order confirmation date of August 7, 2011 for activation. This will result in full gap closure with a positive variance. | Tiffin Mercy Hospital and OneCommunity | NOACSC | 1 Gbps Network-to-Network Interface as subscribed to by NOACSC and One Community. 100 Mbps User Network Interface port and Ethernet Transport Services as purchased wholesale by One Community | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Com Net provides Ethernet Transport Services under meet point service arrangements with fiber-facility based providers who provide and maintain carrier class facilities. Com Net takes on full responsibility for the performance of the network, therefore serving as the central point of contact for wholesale customers, providers and subscribers for customer convenience. This allows us to extend the reach of our network beyond our backhaul fiber routes cost-effectively and in a fashion that provides a timely response with a local touch, as well as, a single point of contact for customer service. | FALSE | Com Net's network management practices have not changed. | Network Build: The number of active plow trains on the Com Net project will be ramped to a minimum of three (3) by early August to increase monthly progress rates to expected levels with a fourth plow train and stand-alone boring crews added by mid-September to begin closing the gap in cable placement activities that are a significant factor in the network build measurement. Com Net plans to finalize splicing, testing, as-built documentation and other clean-up activities to allow routes that are complete in terms of cable placement can be fully accepted with payment issued. Com Net will, also, be modifying plans to allow for continued construction throughout the winter of 2012. Com Net plans to finalize award for an appraiser of third party legacy facilities to be used in the project and Fiber IRU on the Lincoln Village to downtown Columbus area. Com Net, also, plans to address several areas requiring minor route modification with NTIA. CAI Connectivity: Com Net plans to provide improved broadband service through the availability of the back-up protected path to NOACSC, as well as, increase capacity to all schools served via fiber-to-the-school. Com Net plans to substantially complete work to provide improved broadband service to the Wayne Trace High School, Wayne Trace Grover Hill Elementary and Wayne Trace Payne Elementary by completing fiber construction allowing these sites to be migrated from fixed wireless service historically subject to outages and equipment | COM Net, Inc. | Com Net has encountered unexpected restrictions on construction types in certain counties of its project. This is due to poor workmanship by other parties that has caused Authorities Having Jurisdiction (AHJ) to only allow open trench construction for the placement of underground facilities, which is significantly slower and more expensive than direct plow operations. Com Net has encountered AHJs that are requiring significant deposits prior to granting permits, which has a direct impact on available cash. The same AHJs are requiring construction be completed typically within ninety days of issuance of permit or risk forfeiture of deposit. This is making it difficult to work ahead on permitting, especially on areas involving railroad crossings, bridges, pole attachment and other long lead time permits without risking the expense and delays associated with the movement of crews and equipment on and off construction segments, especially underground construction equipment. Material supply has not been an issue to date, however the limited world wide supply of fiber optic cable has resulted in a need for increased management to allow for rolling 180 day forecasts to maintain allocation, as well as demands by suppliers for equitable adjustments in the price for fiber optic cable. The unknown factor on receipt of FONSI and lifting of SAC conditions, along with a rainy May in Ohio, slightly delayed initial deployment of crews to the field from notification of lifting o | Challenges will be with obtaining permits in a timely fashion to avoid issues with permits that have fixed implementation timelines as excessive movement of crews could introduce delays. Dry weather could cause a change in ground conditions resulting in a reduction in underground construction progress rates. Com Net expects to continue to see a large balance in unliquidated obligations as payments for cable placement are held pending testing, as-built documentation and other clean-up activities. This practice of holding payment until full completion is achieved will continue to reflect itself in performance progress reporting that is based on liquidated obligations until the July to September 2012 time frame.
NT10BIX5570072 | 2011 | Q3 | Q3 - 2011 | Administration, Community Anchor Institution Sales, Environmental Assessment Compliance, Contract Negotiations and Operation Support Systems: Com Net was engaged in bid management, implementation of EA measures, contract negotiations and out-reach activities with Community Anchor Institutions. Com Net conducted weekly project calls with its route design and construction firm with expanded participation with vendors and sub-recipients every other week. Com Net has executed an expanded agreement with ZAYO covering joint build relationships between the parties and operation of shared sheath facilities. Com Net has received and is operating consistent with an expanded agreement with the Ohio State University executing on behalf of OARnet. The agreement with OARnet will be executed on clarification of the relationship between OARnet and the Ohio State University. Com Net filed its ARRA, SF-425, Performance Progress and Year 1 Audit Reports in the quarter, and accepted the first amendment to its award on the sale/Iease IRU SAC. Com Net awarded its back-up generators for remote huts, executed agreements with three additional Broadband Service Partners and one additional wholesale provider. Com Net delivered improved service to thirty-five (35) Community Anchor Institutions and new service to one Community Anchor Institution. The majority of the Community Anchor Institutions were K-12 educational institutions actively loaded in Com Net's legacy NISC iVUE billing system. | 81 | 1 | 23 | 221 | 81 | 0 | 0 | 5 | A negative variance versus baseline of 134 Miles. This variance is due to a later than projected start of construction date. Com Net is planning to construct through the winter months, as well as taking other action to reduce this gap. Com Net's projected New Network Miles Deployed by 12/31/11 is 160 Miles | A negative variance versus baseline of 19 miles. A variance of 2 miles was created when Com Net worked out arrangements with wholesale customer and community anchor institution NOACSC to use customer provided access rather than Com Net securing an IRU to two fiber to NOACSC downtown Lima, Ohio operating center. The balance of 17 miles is due to the fact that Com Net reported joint build miles with Sycamore Telephone Company under this category and progress on construction by Sycamore is lagging behind schedule due to a later than anticipated start date. Com Net projected new network miles deployed by 12/31/11 is 20 Miles. | A negative variance of 945 miles versus baseline. This is due to delays in construction progress due to a later than anticipated start of construction date further complicated by delays in Com Net's deployment of Cyan electronics/optronics at existing Points-of-Presence of its Broadband Service Partners. These facilities represent the meet point mileage of the Broadband Service Providers that will be upgraded by equipping the facilities with Cyan DWDM equipment and/or placing previously unlit fiber(s) into service. A portion of the negative variance is due to the fact that Com Net does not plan on counting Existing Network Miles Leased as having been upgraded until such time that the Cyan DWDM equipment is cut over to service on all or a portion of the legacy leased routes included in the project. | This represents a reduction from Q2 2011 due to a correction to report route miles rather than fiber miles. The baseline number includes miles secured under a physical lease and those secured under a mid-span meet point billing arrangement, primarily included in the existing network miles upgraded. This number represents a negative variance versus baseline of 747 miles driven by a negative variance in mid-span meet existing fiber facilities upgraded of 747 miles. Com Net projected new network miles deployed by 12/31/11 is 335 Miles. | This is a unique number from baseline. Com Net completed the baseline as Number of Miles of Fiber in total not just NEW fiber. The same comments apply to this line item as they apply to new network miles deployed. | No Variance to Baseline | No Variance to Baseline | A negative variance of 23 versus baseline. This gap is driven by the delay Com Net experienced in being able to initiate construction of fiber routes as activation at several interconnection points is dependent on completion of the new fiber routes. In addition, the gap exists due to delays in the cut over of installed equipment and the installation at additional Points of Presence of Broadband Service Partnerss baseline. This gap is driven by the delay Com Net experienced in being able to initiate construction of fiber routes as activation at several interconnection points is dependent on completion of the new fiber routes. In addition, the gap exists due to delays in the cut over of installed equipment and the installation at additional Points of Presence of Broadband Service Partners. | 8 | 21 | 32 | This quarter, CNI executed agreements with CISP, Ottoville Mutual Telephone Company, Arthur Mutual Telephone Company and the Middle Point Home Telephone Company. Companies from the prior quarter were not included in the listing due to the word limitation. | The services offered pursuant to the above referenced agreements are Ethernet Transport Services on a multi-provider meet point basis with the designated Broadband Service Provider serving as the single point of contact with the customer. Com Net also3 provided the Ottoville Mutual Telephone Company with access to dark fiber for the purpose of providing end-to-end connectivity between the Wayne Trace High School and the Grover Hill Elementary School as Community Anchor Institutions. | Subrecipients ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and OARnet (1224 Kinnear Road; Columbus, OH 43212; 616.292.9191) will be designated to operate a portion of the network on activation based on specific spans the providers will be responsible for operating certain fiber within. The specific portions of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients to operate. | 2 | 5 | 1 | 2 | Positive variance to baseline. This is the network-to-network interface established with One Community in Worthington, Ohio originally reported in Q2 2011 and the network-to-network interface established with CISP in Toledo, Ohio. | Positive Variance to Baseline of 4. The positive variance is based on the addition of Arthur Mutual Telephone Company and Middle Point Home Telephone Company to those reported as receiving improved access in Q2 2011. | Negative Variance of 1. Variance is driven by the fact that at this point in the project Com Net originally projected to have progressed construction to provide OARnet access to dark fiber from Lima to Findlay. Construction in Findlay isn't complete as we wait on make readies and address route modification associated with encountering rock in an area of construction. In addition OARnet will not be ready to utilize the access to the dark fiber until March 2012. The gap will be closed as Com Net looks to provide at lease one Broadband Service Partner access to dark fiber in the 4th quarter of 2011 in association with providing improved service to at lease one more K-12 Community Anchor Institution. Ottoville Mutual Telephone Company was provided access to dark fiber for the purpose of connecting it with existing fiber facilities of the company in order to establish an extended local loop for connecting a community anchor institution back to legacy network facilities managed by Co | Rate Limited 1 Gbps port connectivity with Network-to-Network Interfaces and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased wholesale by One Community. | 36 | 3 | 33 | 7 | Positive Variance versus baseline of 18 as Com Net took expedited action to improve service to K-12 schools at the start of the 2011-2012 school year all facilitated by the broadband connectivity put in place with NOACSC in Q2 2011. | Positive Variance versus baseline of 3 through addition of Grover Hill Elementary School to those reported in Q2 2011. | Positive Variance of 15 versus Baseline. | 4 at 5 Mbps; 4 at 10 Mbps; 7 at 20 Mbps; 5 at 50 Mbps; 10 at 100 Mbps; 1 at 200 Mbps and 5 at 1000 Mbps | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Com Net provides Ethernet Transport Service under meet point service arrangements with fiber-facility based providers who operate and maintain carrier class facilities. Com Net takes on full responsibility for the performance of the network, therefore serving as the central point of contact for wholesale customers, providers and subscribers for customer convenience. This allows us to extend the reach of our network beyond our backhaul fiber routes in a fashion that is not only cost effective but also provides for a timely response with a local touch, as well as, a single point of contact for customer care. | FALSE | Com Net's network management practices have not changed. | The completion of equipment deployment for the initial Cyan DWDM chassis installed at existing Points-of-Presence through cut over into service. Installation of equipment at a minimum of six (6) existing Points-of-Presence. EA field studies of ground cover and habitat as necessary prior to initial snow fall to allow for continuous construction during winter months. Completion of Area of Potential Effect (APE) to allow site preparation work to commence at the Wood County Point of Presence and at the Huntsville Point-of-Presence to be constructed. Release of construction on route segment to be managed by ZAYO through the Toledo metropolitan area where they will be making use of existing pole attachments that ZAYO has established. Continuation of direct burial construction with plans to return to rework aerial sections once make readies are complete for pole attachments. Partial acceptance of new route construction as needed to place community anchor institution in service. Establishment of flow through process that will cause Federal Interest to be protected as items are moved from Work-in-Process to finalized work in service. Upgrades and activation of a minimum of two more Community Anchor Institutions. | COM Net, Inc. | Delays in Make Readies for short aerial sections causing inability to complete full segments leaving significant amount of work-in-progress. Com Net will need to accept portions of these routes to allow finalization of connectivity with community anchor institutions. Delays in securing underground construction permits as Com Net schedules meetings with the authorities having jurisdiction to explain construction method and practices as it relates to repair in the event of damage to existing underground facilities. Delays in construction progress due to route modification determination associated with the placement of two new poles to cross 2 streams and one railroad track where rock was encountered when attempting to cross underground through boring operations. Delays in Site Preparation work as CNI completed site surveys and EA field work for Area of Potential Effect study. Other delays in Site Preparation driven by delays in route segment construction. Delays in ability to close the gap against baseline due to inability to add additional crews due to lack of contiguous mileage of secured permits and right-of-way as well as on-going allocation of outside plant fiber cable supply varying from 24 Miles per Month to as high as 36 Miles per Month. Delays in Equipment Deployment as CNI worked through customer notices and interim networking changes allowing Com Net to cut the first set of Cyan DWDM chassis in as part of an upgrade to existing facilities made part of the pr | Delays and/or obstructions in accessing road right-of-way due to fall harvest. Weather related delays, as well as, utility moratoriums, holiday vacations and year-end travel reductions resulting in limited progress. Snow causing delays due to habitats that requires visual inspection during construction, if any. Route modification approval delays, as well as, delays in determination as Com Net implements EA protocols and methods. Delays in Pole Attachment Make Readies causing significant portion of work to remain in progress making them unliquidated obligations, which will have negative impact on financial-based progress reporting using liquidated obligations. Delays in securing road right-of-way due to individual authorities having jurisdiction requiring one-on-one meetings to understand construction methods and Com Net's commitment to repair existing underground facilities in the event they are damaged as a result of the GigEPAC construction project. These delays will be pronounced with villages, townships and counties due to difficulties arranging for meetings during the month of December because of their limited staffing.
NT10BIX5570072 | 2011 | Q4 | Q4 - 2011 | Community Outreach: Com Net's Community Outreach efforts during the quarter consisted primarily of meetings with County Engineering offices in Logan, Hardin, Shelby and Miami Counties, as well as Richland Township in Allen County to secure the right to construct using the direct plow method of construction. Com Net also met with the new Village Administrator from West Milton, Ohio as we worked to solidify lease arrangements for a point-of-presence in the village. Com Net met with officials from the City of Bowling Green to explore opportunities for connectivity. Com Net met with the Ohio Department of Jobs and Family Services (ODJFS) to explore the opportunity for ODJFS to utilize the middle mile facilities to connect county offices back to its data center for enhanced application performance. Community Anchor Institution Sales: Com Net continued its effort to grow the number of Community Anchor Institutions receiving improved service from the Middle Mile Facilities. In the quarter, the number of Community Anchor Institutions receiving improved service was expanded to 40 in total or a gain of 4 for the quarter. At the end of the quarter, Com Net was actively engaged in working to finalize connectivity for another 3 Community Anchor Institutions that have committed to receiving service. Administration: Com Net was engaged with its Federal Program Officer Team on several route modifications, which were primarily driven by ground conditions encountered during construction and/or requests by the authority having jurisdiction for modification in the right-of-way through the area over which they have jurisdiction. Approval of these changes in full will carry over to the 1st quarter of 2012. Network Design including Right-of-Way and Permits: At the end of the quarter, Com Net had released 461.57 miles to its route design firm with approximately 327 miles through the design phase and approximately 170 miles permitted. The balance of the mileage was in various stages of the right-of-way and permit application and approval process. Equipment Procurement and Deployment: At the end of the quarter, Com Net had received and deployed equipment to 17 planned points-of-presence (PoP). Four of the sites had been cut over into active service on the network replacing a legacy DWDM equipped span that experienced fault propagation errors between PoPs. Network Build-Out: Com Net continued to progress the network build-out, increasing its deployed number of new construction miles to 140. | 140 | 19 | 28 | 335 | 140 | 0 | 0 | 11 | Negative Variance of 170 Miles. This variance is due to an original projected start of construction date of March 2011. Actual construction didn't start until after all initial special award conditions were satisfied, which was in June 2011. | Negligible Variance versus baseline. | Negative Variance of 737.8 versus baseline. Upgrading of existing network miles is contingent upon deployment of the new network miles along routes as planned. The fiber, consisting of new and existing miles, must be in place between the community pairs prior to cut over to the Cyan DWDM equipment. This gap will close as the gap in new network miles deployed closes, but it is contingent upon completion of the build-out working north and south from Lima, Ohio, as well as the timely cut over of the Com Net active network to the Cyan equipment between Community Pairs. | Negative Variance of 430.8 Miles versus baseline. This gap will close as Com Net continues to deploy equipment to its planned Point-of-Presence, test and accept passive fiber facilities for use in the GigEPAC network. | Change in reporting versus baseline. The baseline was completed with the understanding this metric was inclusive of all network miles. This line item is strictly based on number of miles of "NEW" fiber and is consistent with the number reported for new network miles deployed. | N/A | N/A | The gap between the number of interconnection points included in our projections for the 4th quarter of 2011 (37) versus actual results for Q4 2011 (11) is that with the favorable winter weather conditions, we continue to place an emphasis on closing the gap on the build-out of fiber optic routes. At the time of developing the projections for the 4th quarter of 2011, our assumption was that unfavorable winter weather would limit our outside plant construction efforts; therefore we would apply resources to issue change orders to our implementation plans to allow partial turn-up of interconnections at PoP sites prior to the completion of all fiber routes that would be supported through a PoP. This has not occurred to date due to the favorable conditions for outside plant construction;therefore the preferred approach is to advance the fiber route build-outs and hold on the activation of PoP sites with new and improved interconnection points until all fiber routes are in place. There is no plan to reduce the number of interconnection points at this time; it is strictly a matter of delayed turn-up due to the gap in the deployment of fiber routes. Com Net did continue with its plans to purchase and install DWDM equipment at additional PoP sites that will support new and upgraded interconnection points. The equipment simply has not been cut into servicen points included in our projections for the 4th quarter of 2011 (37) versus actual results for Q4 2011 (11) is that with the favorable winter weather conditions, we continue to place an emphasis on closing the gap on the build-out of fiber optic routes. At the time of developing the projections for the 4th quarter of 2011, our assumption was that unfavorable winter weather would limit our outside plant construction efforts; therefore we would apply resources to issue change orders to our implementation plans to allow partial turn-up of interconnections at PoP sites prior to the completion of all fiber routes that would be supported through a PoP. This has not occurred to date due to the favorable conditions for outside plant construction;therefore the preferred approach is to advance the fiber route build-outs and hold on the activation of PoP sites with new and improved interconnection points until all fiber routes are in place. There is no plan to reduce the number of interconnection points at this time; it is strictly a matter of delayed turn-up due to the gap in the deployment of fiber routes. Com Net did continue with its plans to purchase and install DWDM equipment at additional PoP sites that will support new and upgraded interconnection points. The equipment simply has not been cut into service. | 11 | 19 | 38 | Last Mile Providers added for the quarter were Northwest Net, an unlicensed frequency Wireless Internet Service Provider, and the Benton Ridge Telephone Company, a BIP recipient. The Ohio Academic Resources Network (OARnet) was added in December of 2011 as a wholesale customer of Com Net's lit MetroEthernet Services. | In an effort to refine and simplify Com Net's wholesale and enterprise MetroEthernet solution, Com Net has focused on three basic types of service including ELINE, ELAN and Dual Homed Satellite to Primary and Disaster Recovery Hub Sites. Com Net has defined these services along with a series of qualifying discounts that are determined on an Individual case basisy Com Net's wholesale and enterprise MetroEthernet solution, Com Net has focused on three basic types of service including ELINE, ELAN and Dual Homed Satellite to Primary and Disaster Recovery Hub Sites. Com Net has defined these services along with a series of qualifying discounts that are determined on an Individual case basis. | Subrecipients ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 616.292.9191) will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portions of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations. | 3 | 7 | 2 | 3 | Positive Variance to baseline. This is the network-to-network interface established with One Community in Worthington, Ohio, the network-to-network interface established with CISP in Toledo, Ohio and the ELAN service established with OARnet with 800 Mbps Port Connections established in Lima, OH and Worthington, OH. | Positive Variance to baseline. The positive variance shows an incremental gain of 2 from the 3rd Quarter of 2011 based on Northwest Net and the Benton Ridge Telephone Company receiving improved access in the quarter. | No Variance to baseline. In the 4th Quarter of 2011, the Benton Ridge Telephone Company joined the Ottoville Mutual Telephone Company in receiving access to dark fiber. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network Interfaces; and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased wholesale by One Community. | 39 | 4 | 35 | 8 | An incremental gain of 3 CAIs from the 3rd Quarter of 2011 and a positive variance versus baseline of 21. A total of 4 additional CAIs were reported as connected in the fourth quarter with the elimination of the Fort Recovery School District from those reported in the third quarter. The Fort Recovery School District was improved through the use of middle mile facilities as part of service provided by Wabash Mutual Telephone Company. Wabash Mutual Telephone Company is a BIP Recipient for the Fort Recovery Service Area. In satisfaction of Com Net SAC requirements, the Fort Recovery School District can not/should not have been included in Com Net's CAI count. | An incremental gain of 1 CAI from the 3rd Quarter of 2011 and a positive variance versus baseline of 4. The incremental gain of 1 was based on the establishment of lit Metro Ethernet service for OARnet between Worthington and Lima, Ohio at a time when their network was impaired and they were facing an extended outage between their Lima, Ohio and Worthington, Ohio Points-of-Presence. | Incremental gain of two from the 3rd Quarter of 2011 and a positive variance versus baseline of 10. Actual improved connections of 3 during the quarter offset by an adjustment of 1 from the prior quarter. | 4 at 5 Mbps; 5 at 10 Mbps; 7 at 20 Mbps; 5 at 50 Mbps; 12 at 100 Mbps;1 at 200 Mbps; 1 at 800 Mbps and 5 at 1000 Mbps | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Com Net has no new special offerings to share for the quarter. | FALSE | Com Net's network management practices have not changed. | Community Outreach: Com Net will be participating on a panel with NTIA and fellow BTOP recipients at the OPASTCO Winter Conference in Orlando, FL. Com Net will be meeting with U.S. House Representatives for several of the counties located within the coverage area of the GigEPAC project. Com Net will continue to hold meetings with County Engineers, County Commissioners, Village Administrators, Colleges and Universities, State Agency Directors and other key individuals throughout the 1st quarter of 2012. CAI Connections: Com Net will be finalizing connectivity of the Defiance Mercy Hospital to Saint Vincent and Saint Charles Hospitals in the Toledo metro area; upgrading the Parkway School District from unlicensed wireless to Fiber-to-the-School and upgrading the Crestview School District from unlicensed wireless to Fiber-to-the-School. Equipment Procurement and Deployment: Com Net plans to cut its second set of DWDM Points-of-Presence into service in the 1st Quarter of 2012. Com Net plans to relocate its legacy dedicated Internet access Point-of-Presence to Toledo, OH and establish an interconnect and peering point out of this Interexchange Carrier's Network Center. Network Design and Permitting: Com Net plans to focus on further progressing the finalization of all construction plans by the end of the 2nd Quarter of 2012 and accelerate permit applications in preparation for a very aggressive construction period from the Spring of 2012 thru the Fall of 2012. Network | COM Net, Inc. | One of the challenges was in working through route modifications due to unfavorable ground conditions experienced in the field during construction, as well as while working with Authorities Having Jurisdiction for route changes due to upcoming projects the village, city or county has planned in the upcoming years. These changes are relatively minor but can create a significant delay in construction progress if crews and equipment have to be moved off of a portion of the route and then moved back in later to finish a small section. Other delays encountered were primarily related to (i) working with Authorities Having Jurisdiction to secure permits that allow for the planned method of construction in order to prevent significant budget overruns; (ii) management of active crews based on route miles under permit; (iii) managing around high water conditions and areas with unacceptable ground moisture for the direct plow method of construction; and (iv) reassignment of cut-length fiber cable reels based on routes under permit to allow construction to progress. | Challenges will include working to narrow the time frame on approval of change orders resulting from ground conditions encountered by construction crews and from Authorities Having Jurisdiction requiring a change in design plans. Another challenge will be managing construction around wet and frozen ground conditions, as well as planning for many Environmental Assessment Concerns during the Spring and early Summer months. The last challenge we foresee for the quarter will be in reaching closure with Authorities Having Jurisdiction on the arrangements negotiated to allow for the use of the direct plow method of construction.
NT10BIX5570072 | 2012 | Q1 | Q1 - 2012 | Community Outreach: Com Net participated on a panel with NTIA and fellow BTOP recipients at the OPASTCO Winter Conference in Orlando, FL. Com Net met with U.S. House Representatives for several of the counties located within the coverage area of the GigEPAC project. Com Net held several meetings with County Engineers, County Commissioners, Village Administrators, Colleges and Universities, State Agency Directors and other key individuals throughout the 1st quarter of 2012. Com Net, also, attended several council meetings with the Ada Village Council and conducted a public meeting with land owners in Hardin County located along the planned fiber route. CAI Connections: Com Net finalized connectivity of the Defiance Mercy Hospital to Saint Vincent and Saint Charles Hospitals in the Toledo metro area; upgraded the Parkway School District from unlicensed wireless to Fiber-to-the-School, upgraded the Crestview School District from unlicensed wireless to Fiber-to-the-School and worked with OARnet to establish connectivity from the Ohio Public Library Information Network (OPLIN) Point-of-Presence in Columbus, OH to its backhaul facilities on one-end, while working with BIP recipient, Wabash Mutual Telephone Company, to establish connectivity to the Fort Recovery Library on the other end in order to provide a point-to-point connection for this library Community Anchor Institution. Com Net placed service loops at the boundary between road right-of-way and property of other Community Anchor Institutions as part of our route design for the establishment of future services. Equipment Procurement and Deployment: Com Net cut its second set of DWDM Points-of-Presence into service in the 1st Quarter of 2012 spanning from Celina, OH to Ottoville, OH passing through Wabash, OH and Van Wert, OH. Com Net relocated its legacy dedicated Internet access Point-of-Presence to Toledo, OH and established an interconnect and peering point out of Level3's Carrier's Network Center. Network Design and Permitting: Com Net focused it resources on further progressing the finalization of all construction plans by the end of the 2nd Quarter of 2012 and accelerated permit applications in preparation for a very aggressive construction period from the Spring of 2012 thru the Fall of 2012. At the end of the quarter, 440.25 route miles were through design with partial completion through CAD and permitting. Network Build Out: Based on the favorable winter construction period during the first quarter of 2012, Com Net was able to pursue an aggressive winter construction schedule completing 74 miles of new construction,bringing our total new construction route miles to 214 during the quarter while deploying network equipment at 4 additional Points-of-Presence (PoPs). | 212 | 1 | 232 | 362 | 212 | 0 | 0 | 18 | 212 miles of route construction with fiber placed and 2 miles of underground, innerduct only placement. This represents a 123 mile negative variance versus baseline that is driven by the later than expected start date that was used at the time of the development of the baseline. Com Net projects 342 new network miles to be deployed by the end of the 2nd quarter of 2012. Although this variance appears significant versus baseline, Com Net has made significant progress in closing the gap versus baseline given the fact that ground disturbing activities started 4.5-months behind projections used for purposes of the baseline. Com Net's biggest challenge in closing the gap to date has been in securing significant contiguous permitted route mileage to cost-effectively allow for the deployment of addition construction crews. | Previously reported as 19. Mileage reduced to 1 based on adjustments made as a result of a project improvement plan (PIP) conducted at the end of 2011 to ensure reporting was consistent with baseline. The adjusted number represents a negative variance of 18.49 miles versus baseline. The PIP adjustment resulted in the 18 miles being reclassified under existing network miles leased for consistency in reporting versus baseline. | Negative variance versus baseline of 955.9. This variance is a direct result of the 4.5 month delay in the commencement of ground disturbing activities versus baseline. Com Net has focused its efforts on the critical path issue of new route construction. In addition, the delay in ground disturbing activities on Com Net's and the other Ohio BTOP projects has resulted in its sub-recipient OARnet placing a priority on activities in northeast and southeast Ohio, delaying their planned upgrade of leased facilities between Lima, OH and Findlay, OH as well as between Lima, OH and Hillsdale, MI. | Negative variance versus baseline of 825.9. | Same as new network miles deployed. | Not Applicable | Not Applicable | Negative variance versus baseline of 27. This negative variance along with those associated with existing network miles leased and upgraded is a result of a later than expected start date on the network build-out. The leased mileage will be implemented as fiber placement and equipment installation will support the activation of planned leased segments for activation/upgrade. The interconnection points will follow within a 30-day lag period. | 23 | 22 | 40 | Companies added in the 1st quarter of 2012 include Bascom Communications, BMTC, Wabash Communications, WMTC, SMTA, Vaughnsville, TSC, FMTC, KTEC, Glandorf TelCo, Defiance Holdings, SAA Bright.net, NKTelco, Buckland and WATCH Communications along with others as previously reported. Tier 2 Communications and Independents Fiber Network were eliminated in the reporting count as wholly owned affiliates of Com Net that should be treated as sub-recipients for reporting purposes. | In an effort to refine and simplify Com Net's wholesale and enterprise MetroEthernet solution, Com Net has focused on three basic types of service including ELINE, ELAN and Dual Homed Satellite to Primary and Disaster Recovery Hub Sites. Com Net has defined these services along with a series of qualifying discounts that are determined on an Individual case basis. | Subrecipients ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191) will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portions of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations. | 2 | 17 | 4 | 3 | Positive Variance to baseline. This is the network-to-network interface established with One Community in Worthington, Ohio, the network-to-network interface established with CISP in Toledo, Ohio and the ELAN service established with OARnet with 800 Mbps Port Connections established in Lima, OH and Worthington, OH. | Positive Variance to baseline. The positive variance shows an incremental gain of 9 from the 4th Quarter of 2012 based on Buckland, Watch Communications and NKTelco receiving improved Dedicated Internet Acces service; Level 3 receiving an improved transient IP Peers with the Com Net ASN; Bascom Communications, BMTC, Wabash Communications, WMTC, SMTA, Vaughnsville, FMTC, KTEC, Glandorf Telco, Defiance Holdings, SAA bright.net and TSC will all be receiving improved access on completion of the build-out obligations by Com Net. | At this point, Com Net is only providing access to Dark Fiber for broadband wholesalers and last mile providers who agree to jointly serve a Community Anchor Institution. Com Net provided dark fiber access to Wabash Communications for improving service to the Parkway School District and to Northwest Net for improving service to the Crestview School District. Sub-recipient ZAY0 has reported signed agreement with two providers for dark fiber but to date Com Net has not received the customer names and/or verified the existence of the signed agreement therefore the numbers are not included in this report. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network Interfaces; and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased wholesale by One Community. | 47 | 4 | 43 | 9 | Previous PPR reported 39 with three of the reported unique subscriber sites being disallowed during the annual performance report review. OARnet-Lima, OARnet-Worthington and One Community Worthington were eliminated reducing the CAI count to 36. This reduction to 36 was offset with the addition of 11 new. This resulted in a positive variance of 13 to baseline. | The 2011 year-end adjustment resulted in a reductions in the number of subscribers receiving new access by one, which was offset through the addition of the Van Wert, OH Megasite. | Incremental gain of 8 after 2011 year-end adjustments in allowable CAI counts. | 4 at 5 Mbps; 5 at 10 Mbps; 8 at 20 Mbps; 6 at 50 Mbps; 13 at 100 Mbps;1 at 200 Mbps; 1 at 500 Mbps; 1 at 800 Mbps and 5 at 1000 Mbps | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Com Net has no special offerings to report this quarter | FALSE | Com Net's management practices have not changed from the prior quarter | Community Outreach: Com Net will expand outreach efforts to planned counties for construction in the upcoming 6 months, which will include Wood County, Lucas County, Shelby County, Miami County, Montgomery County and Clarke County. Com Net will be attending an upcoming BTOP workshop in the Washington DC area in May 2012. Com Net plans to provide Ohio representatives in congress with an update on the status of our project. CAI Connections: Com Net will be conducting on-going follow-up with its originally identified Community Anchor Institutions in an effort to secure firm commitments for service. Com net will continue to pursue additional Community Anchor Institutions through a Broadband Service Partner, wholesaler and, when no such option exists, on a direct basis to secure commitments to utilize the Com Net backhaul facilities. Com Net plans to establish active service with a minimum of 7 new Community Anchor Institutions in the upcoming quarter with facilities placed with access points at the boundary between public right-of-way and the Community Anchor Institution property to a minimum of 4 additional Community Anchor Institutions. Broadband Service Providers and Wholesale Agreements/Connectivity: Com Net plans to establish lit connectivity with a minimum of two additional Broadband Service Providers, with one Broadband Service Provider committed to receiving Com Net's IPTV signal and service suite, as well as Dedicated Internet Access through an Enhanced Ethernet Network-to-Network Interface (ENNI) port. Site Preparation: Com Net plans to initiate site preparation for the placement of prefabricated huts on three new sites that will serve as Points-of-Presence, one of which is dependent on approval of an outstanding route modification being processed by NTIA. Com Net, also, plans on initiating efforts to prepare space at two facilities where Com Net will be securing space to serve as Points-of-Presence on the Com Net backhaul network. Equipment Procurement and Deployment: Com Net plans to continue deployment of Cyan DWDM equipment at PoP sites throughout the second quarter and to light its third DWDM series of spans. OARnet plans on receiving shipment of electronics equipment and initiating deployment in the May to June time frame of the second quarter. ZAYO plans on progressing its management of the Toledo build through the network design and permitting phases. Network Design and Permitting: Com Net plans to focus on further progressing the finalization of all construction plans by the end of the 2nd Quarter of 2012 and accelerate permit applications in preparation for a very aggressive construction period from the Spring of 2012 thru the Fall of 2012. ZAYO plans on progressing its management of its metropolitan route in Toledo through the design and permitting phases. Network Build-Out: Com Net plans on completing splice and test work on a significant span of leased fiber facilities during the quarter in preparation for OARnet to equip the 2 fiber route from Lima, OH to Hillsdale, MI that it will be responsible for operating. Com Net, also, plans on completing splice and test work on a significant span of leased fiber facilities during the upcoming quarter in preparation for OARnet to equip the 2 fiber route from Lima, OH to Findlay, OH that it will be responsible for operating. Administration: Com Net plans on submitting a route modification to NTIA as part of its efforts to finalize firm design plans for the balance of the network build-out. Com Net also plans on completing follow-up tasks from its NTIA site visit, as well as other quarterly reporting activities. | COM Net, Inc. | Com Net continues to pursue a linear build-out schedule by progressing routes to the north and south of Lima, Ohio to facilitate active connections to Community Anchor Institutions as they are passed. Com Net has focused resources on follow-up activity with authorities having jurisdiction to secure permitted route mileage in a timely fashion. This effort has resulted in a significant volume of permitted mileage that can be released to construction allowing the deployment of a fourth plow train crew in June 2012. Com Net continues to work with the independent township, city, county and state permitting authorities in Ohio to resolve outstanding concerns. The challenge in the permitting process have been with the time involved to put in place the necessary arrangements with township, city and county authorities to ensure any damages to existing underground facilities that may not be visibly apparent for years are repaired. Com Net has been able to reach a reasonable resolution to such issues, however we need to accelerate our efforts and progress rate in this area. The single largest challenge faced by Com Net during the quarter, outside of securing right-of-way permits and other approvals, was securing approval with NTIA on route modifications to avoid delays in the movement/relocation of construction crews. Following several iterations, Com Net was able to identify the critical content in order to submit a package for NTIA's consideration and eventual approval. | Com Net will be submitting additional Route Modifications that Com Net's project will be dependent on for a timely response.
NT10BIX5570072 | 2012 | Q2 | Q2 - 2012 | Community Outreach: Com Net (CNI) conducted a public meeting to discuss construction as required by a county engineer, worked with village officials to secure private easements, pursued township road agreements and met with village and county officials to secure necessary permits. CNI met with healthcare representatives to provide transport solutions between hospitals, medical clinics and practitioner offices. CNI met with State Agency CIOs to demonstrate available services. CNI continued to meet with higher education and K-12 institutions. CAI Connections: CNI finalized the connectivity upgrade to its first higher education institution. Turn-ups for the quarter were minimal as most entities deferred activation until later in 2012. CNI expanded new construction facilities in preparation for turning-up several K-12 institutions and public libraries that have committed to upgraded service for the start of the school year. CNI secured commitments from Physician Offices looking for connectivity to area hospitals/healthcare networks in Q3 2012. CNI continued to place access points with service loops in road R-O-W adjacent to CAI properties reducing lead time and expense once the CAI is ready to commit. Broadband Wholesalers and Last Mile Providers: CNI entered into agreements with 2 providers and put 2 new city pair combinations into service, allowing CNI to execute on commitments with 2 providers to deliver new access services. Equipment Procurement and Deployment: CNI cut over services to the DWDM backhaul network with equipment purchased and installed last quarter. CNI is upgrading and cutting into service city pairs as diverse fiber routes are complete to avoid single points-of-failure and to ensure adequate facilities are in place to eliminate/minimize interruptions. CNI cut city pairs into service for Lima-to-Walnut Grove and Walnut Grove-to-Sycamore. Turn-up of additional city pairs was deferred to the Q3 2012 to allow for completion of contiguous routes required to avoid single points-of-failure. Network Design and Permitting: CNI received â€œmake readyâ€ notices of completion for several aerial spans by quarter end. These notices allow CNI to complete several contiguous route segments required for CAI turn-ups during Q3 2012. CAD was completed on 492 route miles, with permit applications submitted on 416 miles and 375 miles completed through permitting and released for construction. CNI received approval to proceed with the construction of three new PoPs and the augmentation of one existing PoP after a delay by the AHJ to address the sustained wind rating of one of the planned facilities. The route design firm reported a breakthrough in securing permits with townships in a county pending construction. The route design firm expressed concerns with the permit progress in two counties and one city, which may require further assistance by CNI. Site Preparation: CNI completed the procurement process to select a standalone site preparation firm to provide services at three new, unmanned PoP sites and augmentation of another. Actual work was delayed until Q3 2012 due to delays in building approval. The site work is projected to be completed during Q3 2012. Network Build-Out: Construction fell behind the required build-out schedule due to outstanding aerial make readies; a higher percentage of bored plow operations; delays with permitting authorities; and the inability to secure contiguous route mileage need to deploy an additional plow train. By the end of quarter, Com Net was working with KG Myers to subcontract boring operations in order to close the construction gap. Additional boring crews are required to meet timelines due to boring operation being a slower process than plow or aerial installations. The increased percentage of bored underground construction versus plow will result in unfavorable performance versus budget, however given the defined timeline for completion, authorization has been provided to proceed. | 287 | 1 | 244 | 388 | 287 | 0 | 0 | 25 | A negative variance versus baseline of 185.25 and a negative variance versus prior quarter projection of 55 miles. This negative variance results in Com Net showing a completion date for the placement of fiber cable of June 21, 2013. This variance was driven by the inability to secure a significant number of permits to allow the deployment of a 4th plow train. This problem is expected to persist for the majority of the 3rd quarter of 2012; therefore, the projection is for a minimal increase in new miles deployed from 287 to 367. Additional crews will be added to the project in the later portion of the third quarter to accelerate boring options, which are expected to become significant in the balance of the build-out. | This indicator is expected to deviate from baseline for the balance of the project based on upcoming route modifications and the reclassification of network miles from new network miles leased to existing network miles leased following completion of the Project Improvement Plan at the end of 2011. | Negative variance versus baseline which was 951.2. During the quarter, Com Net was unable to upgrade 68 miles from Walnut Grove to 535 Scherers Court due to a single point of failure issue that can not be resolved until outstanding make readies are addressed and a short aerial span is constructed. In addition, another 53 miles are pending upgrade for operation and management by OARnet, once OARnet secures entrance facilities to the space in which their equipment is co-located. | Negative variance versus baseline which was 951.2. Com Net has additional mileage to be leased pending the upgrade to the current mileage leased but not yet upgraded. This includes an upgrade to existing network miles that will be managed and operated by OARnet between Lima, OH and Hillsdale, MI. | Same comments as provided for network miles deployed. | Not Applicable | Not Applicable | Interconnection points continues to lag behind baseline as it is dependent on completion of new construction. Initial gap closure plan to secure permits for a significant quantity of consecutive miles to allow for the deployment of a fourth plow train was not successful. Com Net is now pursuing alternative plan to sub-contract with additional boring crews due to time constraints and continued issues in securing permits for the direct plow method of construction. | 25 | 10 | 49 | Wholesale and Last Mile Providers signed during the 2nd quarter of 2012 include the Ayersville Telephone Company and Waldron Telephone Company. | Com Net's offering of Ethernet Transport Services is focused on ELINE; ELAN; and dual-homed satellite to primary and disaster recovery hub site connectivity. Com Net has defined these services, along with a series of qualifying discounts, that are determined on an individual case basis. The indefeasible right to use GigEPAC fiber facilities managed and operated by Com Net is limited strictly to those entities who enter into an agreement to jointly serve community anchor institutions through a mid-span point-of-interconnection with Com Net. The monthly lease of fiber facilities has not been offered to date. To date, sub-recipients and OARnet have not placed GigEPAC facilities managed and operated by their respective companies into service so no documented pricing plans are available for the sub-recipient managed facilities. | Subrecipients ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212;614.292.9191) will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations. | 4 | 17 | 4 | 4 | Positive Variance to baseline. This is the network-to-network interface established with One Community in Worthington, Ohio; the network-to-network interface established with CISP in Toledo, OH; the ELAN service established with OARnet with between Lima, OH and Worthington, OH; the Ethernet Network-to-Network Interface (ENNI) established with Level3 in Toledo, OH; and the jointly provided Ethernet mid-span point-of-meet with BIP recipient, Sycamore Telephone Company in Wyandot County. | This represents no change from the prior quarter. Com Net still plans to offer improved access on completion of the build-out obligations of Com Net as part of the GigEPAC project. | This represents no change from the prior quarter. Com Net continues to only provide access to Dark Fiber to broadband wholesalers and last mile providers who agree to jointly serve Community Anchor Institutions through a mid-span meet point-of-interconnection. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network interfaces; and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. | 48 | 4 | 44 | 10 | This represents a gain of one from the prior quarter as committed activations with Community Anchor Institutions were limited for the quarter. | No change from prior quarter. | Additional customer receiving an upgrade from OC3 SONET connectivity to a rate limited 1 Gbps Ethernet port connection. | 4 at 5 Mbps; 5 at 10 Mbps; 8 at 20 Mbps; 6 at 50 Mbps; 13 at 100 Mbps; 1 at 200 Mbps; 1 at 300 Mbps; 1 at 800 Mbps and 5 at 1000 Mbps | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Com Net has no special offering to report this quarter. | FALSE | Com Net's management practices have not changed from the prior quarter. | Community Outreach: Com Net will continue to schedule meetings with community leaders in order to ensure that we have their cooperation, as well as, to determine potential opportunities. Com Net will meet with state legislators in Columbus to provide them with updates on our projectâ€™s status. CAI Connections: Com Net will be conducting on-going follow-up with its originally identified Community Anchor Institutions in an effort to secure firm commitments for service. Com net will continue to pursue additional Community Anchor Institutions through a Broadband Service Partner, wholesaler and, when no such option exists, on a direct basis to secure commitments to utilize the Com Net backhaul facilities. Com Net plans to provide improved connectivity to a minimum of one (1) library, eight (8) K-12 schools, two (2) health care facilities, two (2) higher education institutions and one (1) other Community Anchor Institution (CAI) for a total of 14 additions for the upcoming quarter. Broadband Service Providers and Wholesale Agreements/Connectivity: Com Net plans to execute eight (8) additional agreements with Broadband Wholesalers and/or Last Mile Providers in order to reach identified Community Anchor Institutions. Site Preparation: Com Net plans to complete site preparation and place prefabricated huts on three (3) new, unmanned sites that will serve as Points-of-Presence, as well as, complete the augmentation of space at one legacy, unmanned point-of-presence. Equipment Procurement and Deployment: Com Net will procure and deploy Dense Wave Division Multiplexing equipment at 11 additional Points-of-Presence. Network Design and Permitting: Com Netâ€™s design and permitting activities have been extended into the 3rd quarter of 2012 as we continue to work with Authorities Having Jurisdiction to secure permits allowing the desired method of construction. Activities will continue as we look at route modifications to address permitting timelines and budget concerns. Network Build-Out: Com Net plan to secure dark fiber facilities from Lima-to-Hillsdale that will be improved through OARnet's operation and management of the facilities; to work with OARnet to secure the entrance facilities to their collocation Point-of-Presence in Findlay, OH, which will allow them to light and assume operation and management of the two dark fiber from Lima-to-Findlay; and to cut-over of a minimum of 2 additional city pairs. Administration: Com Net plans to submit a second route modification request to NTIA as part of its efforts to finalize firm design plans for the balance of the network build-out, as soon as, we receive the report from our Environmental Firm. Com Net will, also, be working with KG Myers Construction to ensure that they follow procurement procedures when sub-contracting with firms that provide boring equipment and labor. | COM Net, Inc. | All issue were adequately addressed above. The major area where technical assistance from the BTOP program may be useful is in the expedited handling of a planned route modification to be submitted by Com Net during the upcoming quarter. The level of need will increase significantly if it becomes necessary for Com Net to implement a route change to utilize right-of-way along a US highway or Interstate due to an inability to secure right-of-way with municipal, township and county authorities. | The largest challenge for the quarter is related to permitting adequate mileage to allow for gap closure versus baseline on the network build-out and dependent milestones. At this stage of the project, due to timeline constraints, Com Net is pursuing the path of least resistance for securing additional permits, which will result in unfavorable variances versus budget due to the higher than budgeted portion of the route that authorities will require be installed through the boring operation. The boring operation is unfavorable financially as it results in incremental innerduct usage and labor costs due to its slower rate of progress. Com Net will assist KG Myers in identifying qualified sub-contractors to assist with the increased mileage to be installed through boring and utilize administrative resources as necessary to complete any necessary route modifications. In order to partially offset these increases, Com Net is analyzing potential route changes to make use of right-of-way along US Highways and Interstates. Com Net will require technical assistance from NTIA to ensure the Environmental Assessment and other documentation required as part of the route modification can be reviewed in an expedited fashion. At the same time, Com Net will continue to aggressively pursue the completion of make readies in order to finalize route segments that have open aerial spans, as well as, route segments with aerial spans that have yet to be started. In the event Com Net is
NT10BIX5570072 | 2012 | Q3 | Q3 - 2012 | Community Outreach: Com Net (CNI) met with city, state and county officials to secure necessary permits, pursued township road agreements, met with healthcare representatives to provide transport solutions between hospitals, medical clinics and practitioner offices. CNI met with the City of Dayton to demonstrate available services. CNI continued to meet with higher education and K-12 institutions. CAI Connections: CNI finalized the connectivity upgrade to one (1) K-12 Institution, improved four (4) K-12 Institutionsâ€™ and one Education Service Center's service from a shared 1 Gbps to a dedicated 1 Gbps, delivered new service to one K-12 Institution who, previously, was not directly served by a broadband provider and provided new Ethernet service to connect a District Library back to OPLIN in Columbus. CNI continued to place access points with service loops in road R-O-W adjacent to CAI properties reducing lead time and expense once the CAI is ready to commit. Broadband Wholesalers and Last Mile Providers: CNI entered into an agreement with the City of Bowling Green and six (6) last mile providers. Com Net was in negotiations with eight (8) additional Wholesale and Last Mile Providers. Equipment Procurement and Deployment: CNI installed six (6) Cyan Chassis in preparation for turn-up. CNI is upgrading and cutting into service city-pairs as diverse fiber routes are complete to avoid single points-of-failure and to ensure adequate facilities are in place to eliminate/minimize interruptions. CNI cut city-pairs into service for Bascom to Findlay and Bascom to Sycamore. Turn-up of additional city-pairs was deferred to the Q4 2012 to allow for completion of contiguous routes required to avoid single points-of-failure. Network Design and Permitting: Design with permit application was submitted on 580.5 route miles and 431.3 miles were completed through permitting and released for construction. This does not include 12.7 miles in the Toledo Metro Area for which sub recipient, ZAYO is managing the construction. This route is currently pending completion of Make Readies. CNI constructed three new PoPs and augmented an existing PoP. A potential issue is that field crews have expressed concerns over surface level rock in three areas. Site Preparation: CNI completed the site preparation work at three new, unmanned PoP sites and augmentation of another. Bringing these sites into service is projected to be completed during Q4 2012. Network Build-Out: Construction continued to lag behind the required build-out schedule due to outstanding aerial make readies; a higher percentage of bored plow operations; and delays with permitting authorities. By the end of quarter, KG Myers has subcontracted with outside directional drilling contractors and is working to close the construction gap. These additional crews were required to meet timelines due to directional drilling being a slower process than plow or aerial installations. | 367 | 1 | 313 | 667 | 367 | 0 | 0 | 27 | No variance versus projections and a 145.55 mile variance versus baseline. The rate of progress is expected to increase based on the sub-contracting of additional directional drilling crews along with the continued operation of 4 plow trains and ZAYO's build of facilities in the Toledo Metro area. Based on conduit being leased and existing innerduct placed and ready for cable placement, Com Net is confident of completion by June 30, 2013 barring any unforeseen weather delays. | This indicator is expected to deviate from baseline for the balance of the project based on upcoming route modifications and the reclassification of network miles from new network miles leased to existing network miles leased following completion of the project improvement Plan at the end of 2011. | Negative Variance versus baseline, which was 1011.8. The gap was closed marginally in the quarter and will continue to be closed as the Cyan city-pairs are cut-over to service. | Negative Variance versus baseline, which was 1011.8. The gap, however, was closed significantly and will continue to be closed as the fiber is leased in preparation for cut-over of the Cyan city-pairs throughout the balance of the quarters remaining in the project period. | Same comments as provided for network miles deployed. | Not Applicable | Not Applicable | Two additional sites added in the current quarter in Walnut Grove and Sycamore. Interconnection points continue to lag behind baseline in parallel with delays in build-out. | 32 | 8 | 50 | Wholesale and Last Mile Providers signed during the 3rd quarter of 2012 include: Fort Jennings Telephone Company, Ridgeville Telephone Company, McClure Telephone Company, Ogden Telephone Company, Sand Creek Telephone Company, Bowling Green Municipal Electric and an undisclosed customer of ZAYO Group. | Com Net's offering of Ethernet Transport Services is focused on ELINE; ELAN; and dual-homed satellite to primary and disaster recovery hub site connectivity. Com Net has defined these services, along with a series of qualifying discounts, that are determined on an individual case basis. The availability of GigEPAC fiber facilities managed and operated by Com Net is limited on two-major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where Com Net manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber that Com Net manages over these two segments, Com Net has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span points of interconnect and reserved additional fiber for quotes to other prospective customers that are still outstanding. On these two major segments, the balance of the remaining dark fiber have been assigned as reserved for service upgrades and new connections with Community Anchor Institutions. The monthly lease of fiber facilities has not been offered to date. To date, sub-recipients and OARnet have not placed GigEPAC facilities managed and operated by their respective companies into service so no documented pricing plans are available for the sub-recipient managed facilities. | Sub recipients, ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212;614.292.9191), will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub recipients' operations. | 5 | 22 | 5 | 4 | Positive Variance to baseline. Bowling Green Municipal Electric receives fiber connectivity to the south with connectivity to Findlay, OH and Lima, OH and beyond. | Positive Variance to baseline. | ZAYO reported undisclosed customer would be receiving access to dark fiber; and therefore, accounts for the increase from prior quarter. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network interfaces and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. | 55 | 6 | 49 | 10 | This represents a gain of seven from the prior quarter as committed activations with Community Anchor Institutions were limited for the quarter. | This represents a gain of two from the prior quarter. Community Anchor Institutions continue to lag behind the original baseline for two reasons. The primary reason is due to the fact that the original baseline was based on the network build-out commencing on March 1, 2011, which did not start until approximately July 1, 2011. The second is due to an inability to secure firm service order commitments due to term commitments the target entity entered into in order to maintain its existing service. | One upgraded from wireless and four upgraded from shared 1 Gbps port to dedicated 1 Gbps ports.Community Anchor Institutions continue to lag behind the original baseline for two reasons. The primary reason is due to the fact that the original baseline was based on the network build-out commencing on March 1, 2011, which did not start until approximately July 1, 2011. The second is due to an inability to secure firm service order commitments due to term commitments the target entity entered into in order to maintain its existing service. | 4 at 5 Mbps; 6 at 10 Mbps; 12 at 20 Mbps; 7 at 50 Mbps; 13 at 100 Mbps; 1 at 200 Mbps; 1 at 300 Mbps; 1 at 800 Mbps; 5 at 1000 Mbps; and 4 unsubscribed | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Com Net has no special offering to report this quarter. | FALSE | Com Net's management practices have not changed from the prior quarter. | CAI Connections: Com Net will be conducting on-going follow-up with its originally identified Community Anchor Institutions in an effort to secure firm commitments for service. Com net will continue to pursue additional Community Anchor Institutions through a Broadband Service Partner, wholesaler and, when no such option exists, on a direct basis to secure commitments to utilize the Com Net backhaul facilities. Com Net is projecting an increase in the total number of CAIs served by 5 in Q4 2012. This remains behind Baseline as Com Net will focus efforts on turning-up city pair connections in preparation for aggressive growth in the number of improved CAIs during Q1 2013. Broadband Service Providers and Wholesale Agreements/Connectivity: Com Net plans to execute three (3) additional agreements with Broadband Wholesalers and/or Last Mile Providers in order to reach identified Community Anchor Institutions. Site Preparation: Com Net plans to bring one (1) augmented, unmanned and three (3) new, unmanned PoPs into service during Q4 2012, as well as initiate site preparation at two (2) leased sites. Equipment Procurement and Deployment: Com Net will focus on the finalization of deployment through cut-over of city-pairs during the 4th quarter of 2012, deferring additional equipment purchase and installation until 2013. Com Net will be working with OARnet on the deployment of equipment in preparation for the Lima-Hillsdale and Lima-Findlay city-pair turn-ups for OARnetâ€™s management. Network Design and Permitting: Com Netâ€™s design and permitting activities have been extended into the 4th quarter of 2012 as we continue to work with Authorities Having Jurisdiction to secure permits allowing the desired method of construction. Activities will continue as we look at route modifications to address permitting timelines and budget concerns. Network Build-Out: Com Net plans to assist OARnet in lighting dark fiber facilities from Lima-to-Hillsdale that will be improved through OARnet's operation and management of the facilities and to work with OARnet to secure the entrance facilities to their collocation Point-of-Presence in Findlay, OH. Com Net also plans on completing 96 miles of new construction. The upgrade of existing facilities and lease of new facilities will be dependent on the success rate in turning-up additional city-pairs. Administration: Com Net plans to submit a second route modification request to NTIA as part of its efforts to finalize firm design plans for the balance of the network build-out, as soon as, we receive the report from our Environmental Firm. Community Outreach: Com Net will meet with State Senators and State Representatives to provide an update on the status of our project. | COM Net, Inc. | Most issues were adequately addressed above. The major area where technical assistance from the BTOP program may be useful is in the expedited handling of a planned route modification to be submitted by Com Net during the upcoming quarter. The level of need will increase significantly if it becomes necessary for Com Net to implement a route change to utilize right-of-way along a US highway or Interstate due to an inability to secure right-of-way with municipal, township and county authorities. | The largest challenge for the quarter is related to permitting adequate mileage to allow for deployment of additional crews. At this stage of the project, due to timeline constraints, Com Net is pursuing the path of least resistance for securing additional permits, which will result in unfavorable variances versus budget due to the higher than budgeted portion of the route that authorities will require be installed through the directional drilling operation with the potential for rock sawing in certain areas. The directional drilling operation with limited rock sawing is unfavorable financially due to its slower rate of progress and therefore, higher cost. In order to partially offset these increases, Com Net continues to analyze potential route changes to make use of right-of-way along US Highways and Interstates. Com Net will require technical assistance from NTIA to ensure the Environmental Assessment and other documentation required as part of the route modification can be reviewed in an expedited fashion. At the same time, Com Net will continue to aggressively pursue the completion of make readies in order to finalize route segments that have open aerial spans, as well as, route segments with aerial spans that have yet to be started. In the event Com Net is successful in securing completed make readies on aerial spans, then we will be able to exceed our network build-out projections. Connecting Higher Education Institutions continues to be a challenge becau
NT10BIX5570072 | 2012 | Q4 | Q4 - 2012 | Community Outreach: Com Net (CNI) met with State Senators and State Representatives to provide an update on the status of the project during the fourth (4th) quarter of 2012. CNI continued to meet with city, state and county officials to secure necessary permits, pursued township road agreements, met with health care representatives to provide transport solutions between hospitals, medical clinics and practitioner offices. CNI met with the City of Dayton to demonstrate available services. CNI continued to meet with higher education and K-12 institutions. CAI Connections: CNI finalized the connectivity upgrade to two (2) K-12 institutions, improved connectivity to two (2) health care facilities, improved service to one (1) correctional institution and established new fiber access connectivity with one municipal utility-owned fiber network. CNI continued to place access points with service loops in road R-O-W adjacent to CAI properties, reducing lead time and expense once the CAI is ready to commit. The upgrades implemented with K-12 institutions is resulting in the expansion of bring-your-own-device (BYOD) initiatives by school districts in western Ohio. Broadband Wholesalers and Last Mile Providers: CNI entered into agreements with nine (9) wholesalers and last mile providers during the quarter. This represented new access in the case of five of the agreements and improved access in the case of four of the agreements. One of the agreements included supplying the provider with a 2-fiber tail in association with managed network services. Equipment Procurement and Deployment: CNI installed nine (9) Cyan Chassis in preparation for turn-up. CNI turned-up the following city pairs during the quarter: Huntsville (Indian Lake Region-Russells Point)-to-Lima, Lima-to-Findlay, Findlay-to-Wood County (Bowling Green) and Van Wert-to-Paulding (Antwerp). Turn-up of additional city-pairs was deferred to Q1 2013 to allow for finalization of a software revision to the internal operating system of the Cyan DWDM equipment. Network Design and Permitting: Design with permit application was submitted on 625 route miles and 569.6 miles were completed through permitting and released for construction. This includes 12.7 miles in the Toledo Metro Area for which sub recipient, ZAYO is managing the construction. CNI constructed three new PoPs and augmented an existing PoP. The design and permitting firm continues to be engaged with field crews to address changes in permits by authorities having jurisdiction, ground conditions preventing the planned method of construction and/or to address outstanding make ready issues. Site Preparation: CNI brought into service three new, unmanned PoP sites and an augmented site by cutting over the associated city-pairs for which the majority of site-preparation was completed in the third quarter of 2012. Network Build-Out: Construction continued to lag behind the required build-out schedule due to outstanding aerial make readies; a higher percentage of bored plow operations; unfavorable weather conditions and delays with permitting authorities. By the end of the quarter, KG Myersâ€™ sub-contractors had completed the awarded work, and KG Myers was holding on further awards until permits were finalized on two other segments. In order to close the construction gaps against project timelines, additional crews will be added as receipt of approved permits and weather allows. | 439 | 1 | 313 | 667 | 439 | 0 | 0 | 34 | A negative variance of 19 miles versus prior quarter projections and a 149.67 mile negative variance versus baseline. This gap will be closed in the upcoming quarter as the original baseline plan projected no new construction progress during the third quarter of the 3rd year of the project. At year end 2012, approximately 6.4 miles of innerduct were placed without cable placed. This, factored with unfavorable outside plant construction weather for half of December, accounted for the delta versus projections. CNI is rojecting the placement of 70 miles of cable in the first quarter of 2013. | No variance versus prior quarter projections and a negative 63.09 mile variance versus baseline. CNI is projecting the lease of 33 new miles during the 1st quarter of 2013 pending approval of the current route modification request and an additional 9.9 miles in the 2nd quarter of 2013. The balance of 20.19 new leased miles will remain as a discrepancy against the baseline until numbers are trued-up with route modification associated with the change in the planned new fiber IRU to downtown Lima, Ohio; reduction in route miles IRU'd Springfield-to-Dayton and discrepancy due to the joint build fiber miles with BIP recipient, Sycamore Telephone Company, at the time of baseline accounted for under new leased miles but moved to new construction following the 2011 project improvement plan review since they were being deployed under a joint build arrangement. The Sycamore joint build mileage totaling 16.35 miles is strictly being recorded as new network miles deployed, which was offset b | This represent no change from prior quarter and a 698.8 negative variance versus baseline. CNI suspended network miles upgraded through the cut-over of city pairs to the Cyan DWDM equipment, with the exception of those needed to serve a community anchor institution, until a software release was available to avoid a service-affecting upgrade outage. CNI plans to proceed with city pair cut-overs in the third week of January 2013. CNI is currently projecting to upgrade 200 miles in the 1st quarter of 2013. | This represent no change from prior quarter and a 698.8 negative variance versus baseline. CNI suspended network miles upgraded through the cut-over of city pairs to the Cyan DWDM equipment, with the exception of those needed to serve a community anchor institution, until a software release was available to avoid a service-affecting upgrade outage. CNI plans to proceed with city pair cut-overs in the third week of January 2013. CNI is currently projecting to lease an additional 250 network miles in the 1st quarter of 2013. | A negative variance of 19 miles versus prior quarter projections and a 149.67 mile negative variance versus baseline. This gap will be closed in the upcoming quarter as the original baseline plan projected no new construction progress during the third quarter of the 3rd year of the project. At year end 2012, approximately 6.4 miles of innerduct were placed without cable being placed. This, factored with unfavorable outside plant construction weather for half of December, accounts for the delta versus projections. CNI is currently projecting the placement of 70 miles of cable in the first quarter of 2013. | NA | NA | Favorable variance to baseline of 21. | 37 | 1 | 45 | During the quarter, CNI finalized agreements or agreed to establish new access or upgrade access agreements with the Champaign Telephone Company; Columbus Grove Telephone Company, a Fairpoint Communications Property; Buckeye Telesystem; US Signal; and Securus Technologies. For a historical listing of interconnect agreement executed with broadband wholesalers and last mile providers see separate attachment upload due to 100 word limitation. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE; ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | Sub-recipients, ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191), will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations; and therefore, no service schedule or pricing information is included related to the sub-recipients' service offerings. | 10 | 26 | 5 | 4 | Securus, Champaign Telephone Company, AVETEC, MediaCom and INDATEL Services will be receiving new access to the area covered through the GigE PLUS project coverage area. | Buckeye, Columbus Grove Telephone Company, XO and US Signal will be receiving improved access over the previous connection(s) used for access to the area covered by the GigE PLUS project. | No change from prior reporting period. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network interfaces and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. Enhanced Ethernet Transport Service Ports are now available where an enhanced port includes Internet Access connectivity and bandwidth. | 61 | 6 | 55 | 10 | This represents an increase of six from the prior quarter as committed activations with Community Anchor Institutions were limited for the quarter. Several Community Anchor Institutions elected to maintain service with their legacy provider based on them receiving cost reductions for upgraded service from the incumbent provider. | No change from prior quarter. | One upgrade from wireless, one new customer provided access 1 Gbps port interface, one new subscriber for CNI provided Internet Access Service and three receiving improved connectivity through fiber-to-the-premises through a committed data rate on a 1 Gbps port connection. | 4 at 5 Mbps; 8 at 10 Mbps; 13 at 20 Mbps; 8 at 50 Mbps; 14 at 100 Mbps; 1 at 200 Mbps; 1 at 300 Mbps; 1 at 800 Mbps; 5 at 1000 Mbps and 4 uncommitted to a data rate on their port connectivity. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | CNI, after receipt of a customer request, began offering Enhanced Ethernet Transport Service Ports. An Enhanced Ethernet Transport Service Port includes Internet Access Connectivity and Bandwidth for the customer resale use. CNI has expanded its network reach through connectivity to 350 E. Cermak Street in Chicago, Illinois through dense wave division multiplexing with lit service termination to the INDATEL Services' Ethernet Exchange. This Ethernet Exchange allows for direct peering with Content Delivery Network (CDN) providers that has resulted in a marked improvement in CNI's Dedicated Internet Access service as noted by several wholesale service provider customers. | FALSE | CNI's management practices have not changed from the prior quarter. | CAI Connections: Com Net Incorporated (CNI) will be conducting on-going follow-up with its originally identified Community Anchor Institutions in an effort to secure firm commitments for service. CNI will continue to pursue additional Community Anchor Institutions through a Broadband Service Partner, wholesaler and, when no such option exists, on a direct basis to secure commitments to utilize the CNI backhaul facilities. CNI currently has contractual commitments with 11 Community Anchor Institutions (CAIs) with a requested in-service date of June 30, 2013, which CNI will continue to pursue based on the customerâ€™s desired in-service date. CNI expects to complete the implementation with 3 additional CAIs during the upcoming quarter. Broadband Service Providers and Wholesale Agreements/Connectivity: CNI plans to execute one (1) additional agreement with Broadband Wholesalers and/or Last Mile Providers in order to reach identified Community Anchor Institutions by the end of the project period. Site Preparation: CNI plans to install equipment at two (2) leased sites in preparation for bringing them into service during the first part of the 2nd quarter of 2013. CNI plans to complete site acquisition and EA work on a planned PoP site in Greenville, Ohio during the quarter to allow for site preparation and installation work to occur in the second quarter of 2013. Equipment Procurement and Deployment: CNI will progress equipment deployment and city-pair cut-over independent of the status of the outstanding software revision for the Cyan DWDM chassis in order to meet project timeline in association with existing route miles leased and upgraded. Network Design and Permitting: CNIâ€™s design and permitting activities will continue in a support role throughout the length of the project with major design initiatives drawing to a close. The design and permitting firm will continue to work with authorities having jurisdiction on change orders as required. Network Build-Out: CNI plans to continue to assist OARnet in lighting dark fiber facilities from Lima-to-Hillsdale that will be improved through OARnet's operation and management of the facilities and to work with OARnet to secure the entrance facilities to their collocation Point-of-Presence in Findlay, OH. CNI is rojecting the placement of 70 new miles of cable, lease of 33 new miles, lease of 200 existing miles and upgrade of 250 miles in the first quarter of 2013. Administration: CNI will provide follow-up information as required by NTIA on its outstanding route modification and technology changes as part of its efforts to complete the project by the end of the second quarter of 2013. Community Outreach: CNI will provide a status update on the GigE PLUS project at the January Connect Ohio meeting. CNI will use this meeting to introduce its new GigE PLUS trademark and logo. CNI, also, plans to increase its general outreach initiatives by increasing press releases on the project as more sites are cut into service, participation in industry trade shows and other general advertising activities through the efforts of Katie Etgen, who joined the company in December in a marketing position. | COM Net, Inc. | Most issues were adequately addressed above. The major area where technical assistance from the BTOP program may be useful is in the expedited handling of the outstanding route modifications CNI submitted during the quarter, along with any subsequent route modifications required due to ground conditions, change requirements by authorities having jurisdiction over locate right-of-ways and/or other unforeseen circumstances outside of our control. | The largest challenge anticipated for the quarter is related to dealing with conditions and events that are outside of our control, which includes the winter and spring weather conditions. At this stage of the project, due to timeline constraints, CNI continues to pursue the path of least resistance for securing additional permits. This will result in unfavorable variances versus budget due to the higher than budgeted portion of the route that authorities will require be installed through the directional drilling operation with the potential for rock sawing in certain areas. The directional drilling operation with limited rock sawing is unfavorable financially due to its slower rate of progress and therefore, higher cost. In order to partially offset these increases, CNI continues to analyze potential route changes to make use of right-of-way along alternative roadways; however this window of opportunity will close early in the upcoming quarter. CNI will require technical assistance from NTIA to ensure the Environmental Assessment and other documentation required as part of the route modification can be reviewed in an expedited fashion. At the same time, CNI will continue to aggressively pursue the completion of make readies in order to finalize route segments that have open aerial spans, as well as, route segments with aerial spans that have yet to be started. In the event CNI is successful in securing completed make readies on aerial spans, then we will be able t
NT10BIX5570072 | 2013 | Q1 | Q1 - 2013 | Community Outreach: Com Net (CNI), as Independents Fiber Network, participated at the Ohio Medical Group Management Association and Ohio E-Tech trade shows. CNI continued to meet with city, state and county officials to secure necessary permits, pursued township road agreements, met with health care representatives to provide transport solutions between hospitals, medical clinics and practitioner offices. CNI met with the city of Dayton to demonstrate available services. CNI continued to meet with higher education and K-12 institutions. CAI Connections: CNI, working with interconnect partners Independents Fiber Network and Bascom Mutual Telephone Company, caused new fiber to be installed to the new Hopewell Loudon school building; Independents Fiber Network worked with Northwest Net Incorporated and RTEC Express to connect healthcare system participants in Van Wert, OH and Bryan, OH; and CNI placed fiber to the Municipality of West Milton's former water treatment plant. CNI continued to place access points with service loops in road R-O-W adjacent to CAI properties, reducing lead time and expense once the CAI is ready to commit. Broadband Wholesalers and Last Mile Providers: CNI entered into a revised agreement with one Broadband Service Provider to upgrade an interconnection made possible through BTOP funds, activated a mid-span meet-point with another Broadband Service Provider that it had entered into an agreement with in the 4th quarter of 2012, and upgraded connectivity with two Broadband Service Providers during the quarter. Equipment Procurement and Deployment: CNI installed three (3) Cyan Chassis in preparation for turn-up. CNI turned-up 15 city-pairs during the quarter between Cyan equipped PoP sites. The majority of the turn-ups involved upgrading links established over existing network miles leased, dramatically improving the connectivity to the Broadband Service Providers connected through these mid-span meet-point network-to-network interconnects. CNI sub-recipient ZAYO completed deployment of 12.2 miles of the 12.7 mile route through Toledo that it was responsible for based on upgrading a legacy aerial route with portion underground in existing conduit. | 515 | 1 | 550 | 903 | 515 | 0 | 0 | 41 | A positive variance against 2012 Q4 projections of 6 miles and a negative variance versus baseline of 74 miles. In addition to the 515 cable miles placed an additional 18 miles of inner duct was installed and ready for cable placement. At the end of the quarter the outstanding route modification was becoming an inhibiting factor on construction progress. CNI plans to begin reducing field crews starting in mid-May 2013 if a positive determination is not reached on the route modification request. Assuming the route modification is received on or before May 10, 2013 CNI is projecting new network miles deployed of 610 | A negative variance versus projections of 33 miles and a negative variance versus baseline of 66.6 miles. The lease of new network miles is contingent upon completion of the route modification submitted in the 4th quarter of 2012. Assuming the route modification is approved by May 10, 2013, CNI is projecting the lease of 43 new network miles in the 2nd Quarter of 2013. | This represents a positive variance of 37 miles versus prior quarter projections and a negative variance of 533 miles versus baseline. CNI made significant progress in the 1st quarter of 2013 and expects to continue to make such progress with 350 miles projected to be upgraded in the 2nd quarter of 2013. This is highly dependent on OARnet accepting the dark fiber facilities it will be operating and managing between Lima, Ohio and Hillsdale, Michigan; and Lima and Findlay Ohio | This represents a negative variance of 14 miles versus prior quarter projections and a negative variance of 191 miles versus baseline. CNI made significant progress in the 1st quarter of 2013, which is expected to continue into the 2nd quarter of 2013 with an additional 200 of existing network miles leased for upgrade purposes. | The same comments for new network miles deployed apply. It should be noted that existing network miles upgraded and existing network miles leased were established using fiber-pair route miles between city-pairs. A portion of these route miles between city-pairs are contained within the same physical cable route. | N/A | N/A | Negative Variance of 14, which is based on the fact that sub-recipient interconnection points have not been recognized to date. In addition several of OARnet's interconnection points will only be classified as regeneration sites rather than interconnection points resulting in shortfall versus baseline for the project. | 38 | 4 | 44 | During the quarter, CNI finalized agreements with TDS, Mediacom and Avetec, which of the 3 only TDS is currently wholesaling service from the federally funded porject. In addition CNI upgraded its legacy agreement with XO Communications and Indatel Services, companies which CNI purchases wholesale service from to meet the needs of customers in its service area. For a historical listing of interconnect agreements executed with broadband wholesalers and last mile providers see the separate attachment due to 100 word limitation. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE, ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI also offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | Sub-recipients, ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191), will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations; and therefore, no service schedule or pricing information is included related to the sub-recipients' service offerings. | 10 | 28 | 5 | 4 | The mid-span meet-point network-to-network interconnection was activated during the quarter with Mediacom allowing them to receive new access to the area covered through the GigE PLUS network. | The legacy connection with XO was upgraded during the quarter to allow for the exchange of point-to-point Ethernet Transport Services between the parties; and an agreement was executed with TDS allowing them to receive improved access as a result of the expanded BTOP network. | No changes from prior reporting period. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network interfaces and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. Enhanced Ethernet Transport Service Ports are now available where an enhanced port includes Internet Access connectivity and bandwidth. | 64 | 7 | 57 | 10 | This represents an increase of three from the prior quarter as committed Community Anchor Institutions were limited for the quarter. Several Community Anchor Institutions elected to maintain service with their legacy provider based on receiving cost reductions for upgraded service from the incumbent provider. The number of CAIs connected for the quarter was also impacted by our inability to construct in certain areas while the route modification remained outstanding. | CNI investment in fiber directly to the former Water Treatment Plant of the Municipality of West Milton on a public-private partnership to equip the site as a node on the BTOP network. | Interconnected partner connectivity extended to one new K-12 school building enabled directly as a result of BTOP funded investment allowing for connectivity to the Information Technology Center (ITC) serving the school and another Interconnected, facility-based Broadband Service Provider extending fiber to a medical center to connect the office to the healthcare system, which was enabled directly as a result of the BTOP investment. | 4 at 5 Mbps; 10 at 10 Mbps; 13 at 20 Mbps; 8 at 50 Mbps; 15 at 100 Mbps; 1 at 200 Mbps; 1 at 300 Mbps; 1 at 800 Mbps; 5 at 1000 Mbps and 6 uncommitted to a data rate on their port connectivity. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | CNI, after receipt of a customer request, began offering Enhanced Ethernet Transport Service Ports. An Enhanced Ethernet Transport Service Port includes Internet Access Connectivity and Bandwidth for customer resale use. CNI has expanded its network reach through connectivity to 350 E. Cermak Street in Chicago, Illinois through dense wave division multiplexing with lit service termination to the INDATEL Services' Ethernet Exchange. This Ethernet Exchange allows for direct peering with Content Delivery Network (CDN) providers that has resulted in a marked improvement in CNI's Dedicated Internet Access service as noted by several wholesale service provider customers. | FALSE | CNI's management practices have not changed from the prior quarter. | Community Outreach: In the upcoming quarter CNI plans to attend the BTOP seminar being held in the Washington DC area with scheduled meetings with elected officials from our network service area. CNI, in cooperation with CYAN and JDSU, also plans on demonstrating the BTOP funded networks' ability to provide 100 Gigabit per second service in northwest Ohio with connectivity to Columbus, Ohio. CAI Connections: CNI plans to aggressively pursue new and improved connections to community anchor institutions immediately upon receipt of a determination with respect to its route modification award action request. CNI will be pursuing improved and new connectivity with K-12 Educational institutions, public safety entities, healthcare entities and other government entities for a total of 72 new and/or improved CAI connections Broadband Service Providers and Wholesale Agreement Connectivity: CNI plans to execute a minimum of one new agreement and activate a mid-span meet-point interconnection during the upcoming quarter. CNI plans to leverage these interconnections to provide improved service to additional community anchor institutions within its project service area. Site Preparation: CNI plans to finalize acquisition of the property for its Greenville point-of-presence (PoP) based on positive findings in its Area of Potential Effects for the site. CNI also plans to finalize agreements for all leased sites that will serve as PoPs. Equipment Procurement and Deployment: CNI plans to finalize deployment of all outstanding Cyan terminals, purchase and install its MPLS network equipment and work with its sub-recipients on the purchase and installation of equipment in association with project facilities they will be responsible for operating and managing. CNI is projecting that OARnet will complete the purchase and deployment of MPLS equipment on the Lima-to-Hillsdale and Lima-to-Findlay routes it will be responsible for managing. CNI is also projecting ZAYO will completed its procurement of electronics and collocation equipment as it assumes possession of fiber in the joint-build route segments. Network Build-Out: CNI plans to aggressively pursue build-out of the network as soon as a determination is reached with respect to its outstanding route modification request. This build-out plan will be based on the assumption the route modification is approved in early May of 2013. CNI is projecting OARnet to finalize all of its construction responsibilities upon completion of the outstanding 0.5 mile in its 12.7 mile build through Toledo, Ohio. CNI is projecting to progress its new construction miles to 610 and new leased miles to 43. CNI is projecting to lease 1103 existing miles to the project and of those 1103 existing miles leased complete the upgrade of 900 of the existing miles leased. Administration: CNI will provide follow-up information as required to reach a determination on its existing route modification. CNI will also closely monitor construction activities in the field such that any change orders requiring NTIA approval are immediately documented and submitted for approval to ensure timely completion of the project. CNI also plans to pursue approval to purchase 4 additional Cyan chassis in order to allow it to interconnect with 3-4 additional Broadband Service Providers/Wholesalers in Logan and Union counties, to establish backhaul facilities for a point-of-interconnect with Broadband Service Providers/Datacenters in Delaware and Franklin counties, and to potentially establish a point-of-interconnect with a fellow BTOP/BIP recipient in Marion county. | COM Net, Inc. | The major challenge CNI continues to face is in dealing with multiple authorities having jurisdiction especially at boundary areas, as well as, the expedited handling of change orders due to field conditions and permit changes by the authority having jurisdiction as we approach the end of the project. CNI needs to increase monitoring of construction activities to capture any such change orders that will require NTIA approval at the earliest possible moment in order to allow for adequate time for review and approval as a route modification. The major area where technical assistance from the BTOP program may be useful is in the expedited handling of the outstanding route modifications CNI submitted during the 4th quarter of 2012; as well as any subsequent route modifications required due to ground conditions, change requirements by authorities having jurisdiction over locate right-of-ways and/or other unforeseen circumstances outside of our control. | The largest challenge CNI faces in the upcoming quarter that could impact planned progress against the project milestones is approval of the existing route modification. The other areas that pose a challenge to the planned progress against the project milestones involve CNI's ability to secure conduit inside the city of Dayton, changes to issued permits by authorities having jurisdiction, and any unexpected delays associated with permits for the two routes to be designed and constructed pursuant to the route modification.
NT10BIX5570072 | 2013 | Q2 | Q2 - 2013 | Community Outreach: Com Net (CNI) attended the NTIA seminar in the Washington DC area at which time it met with representatives from western Ohio. Com Net continued to meet with representatives of various Community Anchor Institutions during the 2nd quarter of 2013. CAI Connections: CNI, working with interconnect partners Independents Fiber Network, SAA brightnet, Qualstar, Benton Ridge Telephone Company, Bascom Communications, CT Communications and Avetec; in order to deliver new and improved fiber-facility based services to various Community Anchor Institutions located throughout northwest and west central Ohio. Broadband Wholesalers and Last Mile Providers: CNI entered into a revised agreement with two Broadband Service Providers to interconnect through Ethernet Network-to-Network Interfaces in order to allow these Broadband Service Providers to order services over the BTOP funded facilities. Equipment Procurement and Deployment: CNI installed Cyan Chassis in Morengo, Chicago, Bluffton, Lima, Wapakoneta and Chicago in preparation of turning-up the balance of the planned City-Pair links. CNI also purchases and deployed MPLS Network equipment at multiple locations throughout western Ohio in preparation for turn-up during the no-cost increase extension period. CNI turned-up over 10 city-pairs during the quarter between Cyan equipped PoP sites. The majority of the turn-ups involved upgrading links established over existing network miles leased, dramatically improving the connectivity to the Broadband Service Providers connected through these mid-span meet-point network-to-network interconnects. | 572 | 1 | 1043 | 176 | 572 | 0 | 0 | 45 | This represents a negative variance versus the prior quarter projections and no-cost increase extension milestone of 38 miles, which was driven by CNI's inability to secure approval of its 2012 route modification prior to the end of the quarter. | This represents a negative variance versus the prior quarter projections and no-cost increase extension milestone of 42 miles, which was driven by CNI's inability to secure approval of its 2012 route modification prior to the end of the quarter. | This represents a negative variance versus the prior quarter projections and no-cost increase extension milestone of 10 miles, which was driven by CNI's inability to secure approval of its 2012 route modification prior to the end of the quarter. | A significant variance versus baseline is reported for the quarter due to duplicated reporting of network miles upgraded in the original baseline. In the original baseline the same mileage was reported under Existing network miles leased and Existing Network miles upgraded. CNI viewed the tow categories as simply tracking the fact that the existing network miles generally have to be leased in advance of them being upgraded so this milestone was simply meant to keep track of the time frame that elapsed from iles being leased to miles being upgraded. CNI now understand the Existing network miles upgraded to mean existing miles not leased using federal funds but upgraded through the lighting of fiber or deployment of new equipment connected to the existing network miles, whereas existing network miles leased means existing network miles leased using federal funds. This correction to the baseline goals was made as part of CNI's no cost increase project extension request. The goal | See comments associated with new network miles deployed | NA | NA | This represents a favorable variance of 3 over the no-cost increase project extension. This was driven by CNI being able to reallocate resources on the turn-up of interconnection points as available route mileage to construct became scarce as CNI was unable to secure approval of its 2012 route modification request. | 40 | 2 | 45 | A listing of wholesale and last mile providers has been included a separate attachment. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE, ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI also offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date.use of the remaining dark fiber is | Sub-recipients, ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191), will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations; and therefore, no service schedule or pricing information is included related to the sub-recipients' service offerings. | 7 | 28 | 5 | 4 | A mid-span meet point network-to network interface uses installed with Consolidated Electric. A carrier-to-carrier connection was installed at a carriers mobile serving offices with bandwidth services to cell site in rural Ohio. Prior to this quarterly report this number included providers with signed agreements receiving access to dark fiber. In order to avoid the duplicate reporting of providers all providers also reported as receiving access to dark fiber were eliminated from this number. | No changes from prior reporting period | All providers receiving dark fiber are also receiving improved service as CNI to date has only provided dark fiber in a bundled fashion with new improved lit services. In addition all providers receiving access to dark fiber are reported as receiving new access due to the fact that they are receiving the dark fiber to access new service areas. | Rate limited 10 Gbps and 1 Gbps port connectivity for network-to-network interfaces and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. Enhanced Ethernet Transport Service Ports are now available where an enhanced port includes Internet Access connectivity and bandwidth. | 66 | 8 | 58 | 10 | This represents an increase of 2 from the prior quarter for a negative variance versus baseline of 25, and a negative variance of 4 against the no cost increase project extension milestone | This represents a gain of 1 from the prior quarter. | This represents a gain of 1 from the prior quarter. | 4 at 5 Mbps; 10 at 10 Mbps; 13 at 20 Mbps; 9 at 50 Mbps; 18 at 100 Mbps; 1 at 200 Mbps; 1 at 300 Mbps; 1 at 800 Mbps; 7 at 1000 Mbps and 8 uncommitted to a data rate on their port connectivity. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | CNI, after receipt of a customer request, began offering Enhanced Ethernet Transport Service Ports. An Enhanced Ethernet Transport Service Port includes Internet Access Connectivity and Bandwidth for customer resale use. CNI has expanded its network reach through connectivity to 350 E. Cermak Street in Chicago, Illinois through dense wave division multiplexing with lit service termination to the INDATEL Services' Ethernet Exchange. This Ethernet Exchange allows for direct peering with Content Delivery Network (CDN) providers that has resulted in a marked improvement in CNI's Dedicated Internet Access service as noted by several wholesale service provider customers. | FALSE | CNI's management practices have not changed from the prior quarter. | Community Outreach: In the upcoming quarter CNI plans to participate on a transport panel at an upcoming Ohio WISP association meeting, attend Comptel in September and meet with representatives of various Community Anchor Institutions. CAI Connections: CNI plans to aggressively pursue new and improved connections to community anchor institutions immediately upon receipt of a determination with respect to its route modification award action request. CNI will be pursuing improved and new connectivity with K-12 Educational institutions, public safety entities, healthcare entities and other government entities in pursuing a total of 92 new and/or improved CAI connections during its no cost increase extension period. Broadband Service Providers and Wholesale Agreement Connectivity: CNI plans to execute a minimum of one new agreement and activate one more mid-span meet-point interconnection during the no-cost increase extension period. CNI plans to leverage these interconnections to provide improved service to additional community anchor institutions within its project service area. Site Preparation: CNI plans to finalize the activation of its Greenville hut site. CNI also plans to finalize agreements for all leased and occupied sites that will serve as PoPs. Equipment Procurement and Deployment: CNI plans to finalize deployment of all outstanding Cyan terminals, finalize activation of its MPLS network equipment and work with its sub-recipients on the purchase and installation of equipment in association with project facilities they will be responsible for operating and managing. CNI is projecting that OARnet will complete the purchase and deployment of MPLS equipment on the Lima-to-Hillsdale and Lima-to-Findlay routes it will be responsible for managing. CNI is also projecting ZAYO will completed its procurement of electronics and collocation equipment as it assumes possession of fiber in the joint-build route segments. Network Build-Out: CNI plans to aggressively pursue build-out of the network as soon as a determination is reached with respect to its outstanding route modification request. This build-out plan will be based on the assumption the route modification is approved by August 1, 2013. CNI is projecting to progress its new construction miles to 643 and new leased miles to 48. CNI is projecting to lease a total of 310 existing miles to the project and upgrade1,321 existing miles. Administration: CNI will provide follow-up information as required to reach a determination on its existing route modification. CNI will also closely monitor construction activities in the field such that any change orders requiring NTIA approval are immediately documented and submitted for approval to ensure timely completion of the project. CNI will be completing its Year 3 project audit and prepare for project close-out following expiration of the no-cost increase extension period. | COM Net, Inc. | The major challenges impacting CNI ability to advance the project toward the projections set out in the prior quarter were related to CNI's inability to secure approval of its 2012 route modifications and in successfully securing access to conduit in the Dayton, Ohio market. CNI's inability to complete these activities with third parties caused CNI to focus its efforts on items that were within its own control, however as we near completion of the project these areas are limited. | Com Net's biggest challenge at this stage is completion of the project within an unkown period of time once it 2012 route modification is approved. CNI must secure approval of its outstanding route modification as submitted in order to allow adequate time for it to complete the balance of the new construction, turn-up the outstanding city pairs and establish connectivity with the balance of its Community Anchor Institutions. In addition CNI must complete a conduit capacity check and engineering review prior to being able to enter into an arrangement to lease conduit in order to place fiber to the downtown Dayton, Ohio area. This must be completed with adequate time for its sub-recipients to secure entrance facilities and terminate the fiber to their transmission equipment.
NT10BIX5570072 | 2013 | Q3 | Q3 - 2013 | Overall: CNI has successfully completed the GigE PLUS project constructing 634 new fiber route miles, securing the indefeasible right-to-use for 48 new route miles, upgrading 1321 existing route miles and securing - through a indefeasible right to use - 310 route miles with the majority of the 310 miles placed under the operation and management of sub-recipient, OARnet, for their estimated useful life. CNI has successfully increased bandwidth capacity to its interconnected local broadband providers, while decreasing the rate per Megabit that these interconnected providers pay. These interconnected broadband providers have, in turn, extended their broadband coverage area while increasing service speeds at reduced rates. CNI has dramatically increased the capacity available over its backhaul network in Northwest Ohio and demonstrated the ability to provide 100 Gigabit services and equipped the network to deliver multiple 10Gbps wavelength services with the assistance of Cyan and JDSU. In addition, CNI has retained employees at its headquarters in Wapakoneta, Ohio by retraining dial-up support call center employees for positions in its facilities and infrastructure group, 24/7 broadband support call center, after hour customer service call center, billing service bureau and 24/7 network operations center. CNI has, also, added employees in the area of marketing, sales and project management. CNI continues to search for an individual to join its organization in the position of Network Planner. In addition to CNI's direct employees, the GigE Plus project has, also, had a positive impact with its interconnected broadband providers' ability to retain and hire additional employees as they upgrade broadband speeds and expand service coverage primarily in the area of sales, marketing and outside plant technicians. These entities, as well as, CNI have created jobs with construction, permitting and design firms throughout the life of the project and into the future as CNI and its interconnected broadband providers continue to build out facilities to connect to public and private institutions with fiber to the premises. CNI's marketing plans are to continue to expand our outreach as demonstrated by our participation in the Broadband Communities Convention in the Chicago south lands in early November, as well as, the Great Lakes Technology Showcase. CNI will continue its recipe for success of maintaining and expanding its long-standing managed service business to facility-based voice, data and video providers. These facility-based managed service clients will receive additional value through their partnership with CNI as we grow our facilities and infrastructure business under the Gigabit Ethernet Plus Availability Coalition model where it interconnects with fiber facilities of our clients and complements the client's facilities with new construction to expand CNI's segment-provider fiber network coverage. Community Outreach: Com Net (CNI) attended and presented at the Dayton Development Coalition. The coalition consists of representatives of area departments of economic development. CNI's presentation was focused on the availability of fiber brought to the area through the GigE Plus project and how it would benefit companies looking to locate in the area. CNI continued to meet with representatives of various Community Anchor Institutions during the 3rd quarter of 2013 in order to finalize connectivity plans. Finally, CNI completed its Year 3 Project Audit during the quarter. CAI Connections: CNI, working with interconnected Broadband Service Providers, identified multiple Community Anchor Institutions that received new broadband service or Improved broadband service throughout CNI's funded service area. Broadband Wholesalers and Last Mile Providers: CNI entered into a revised agreement with two Broadband Service Providers to interconnect through Ethernet Network-to-Network Interfaces in order to allow these Broadband Service Providers to order services over the BTOP funded facilities. Network Deployment: CNI completed the construction, IRU and lease of all fiber miles with the exception of 8.6 miles in the Dayton metropolitan area, which CNI has committed to completing through the use of its own funds. Equipment Procurement and Deployment: CNI completed the deployment of all equipment and the turn-up of all City-Pairs during the quarter. | 634 | 48 | 1321 | 310 | 634 | 0 | 0 | 62 | This represents a negative variance versus the extension period milestone of 8.6 miles associated with the issues previously identified in completing construction in the Dayton Metropolitan area. | This represents 100% completion versus CNI's extension period milestone. | This represents 100% completion versus CNI's extension period milestone. | This represents 100% completion versus CNI's extension period milestone. | See comments associated with new network miles deployed | NA | NA | This represents 100% completion versus CNI's extension period milestone with one variance. CNI's point-of-interconnection at 130 W 2nd Street was available through sub-recipient, OARnet rather than a combination of OARnet's upgraded point-of-presence and new dark fiber presence at 130 W 2nd Street. The variance was that the new dark fiber presence for interconnect was located at the intersection of Liscum and 3rd Street in the city of Dayton requiring Customer-Provided Access facilities back to 130 W 2nd Street. | 45 | 1 | 46 | This represents the additional agreements with last mile providers NetGain, Mercury Networks and DRS through execution of a binding letter of intent with the parties. This, also, represents an agreement with a national wireless carrier. Finally this represents new connectivity to be established with a municipal electric fiber network. CNI's primary efforts were focused, during the quarter, on establishing new or improved connections to Community Anchor Institutions rather than further expanding the number of interconnected broadband wholesalers and last mile providers. The full listing of providers has been attached as a separate document based on the 100 word limitation. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE, ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer-provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | Sub-recipients, ZAYO (400 Centennial Parkway, Suite 200, Louisville, CO 80027; 1.303.381.4683) and the Ohio Academic Resources Network (OARnet) (1224 Kinnear Road; Columbus, OH 43212; 614.292.9191), will be designated to operate a portion of the network on activation of designated spans for which the providers will be responsible for operating certain fibers. The specific portion of the network will be detailed on activation. To date, no such portions of the network are available for release to the sub-recipients' operations; and therefore, no service schedule or pricing information is included related to the sub-recipients' service offerings. | 11 | 29 | 5 | 4 | This represent a gain of four and 100% completion with CNI's extension period milestone. | This represents a gain of one and 100% completion with CNI's extension period milestone. | This represent no gain from the prior quarter and a favorable variance of one versus the extension period milestone. | Rate limited 10 Gbps and 1 Gbps port connectivity for Network-to- Network Interfaces and 10 and 100 Mbps User Network Interface Port and Ethernet Transport Service as purchased by wholesalers. Enhanced Ethernet Transport Service Ports are now available where an enhanced port includes Internet Access connectivity and bandwidth. Port capacity by providers with signed agreements is included as an attachment. | 132 | 11 | 121 | 6 | This represents a favorable variance of 40 versus the extension period milestones. This positive variance is driven by interconnected Broadband Providers who deployed broadband facilities to Community Anchor Institutions through their own investment and provided them new or upgraded service by connecting the facilities to the federally funded Cyan equipment deployed at their serving office during the project period. This positive variance was enhanced based on the fact that CNI ended with 45 interconnected Broadband Providers and wholesalers representing a positive variance to its baseline. In this 3rd quarter of 2013, CNI requested and received reports from its interconnected Broadband Providers on Community Anchor Institutions served based on the last definition CNI received from NTIA on March 13, 2013 for counting new and improved CAIs. | This represents 100% completion pursuant to the extension period milestone. | This represents a favorable variance of 30 to the extension period milestone. | 27 subscribers at < 10 Mb, 36 subscribers at >= 10 Mb and < 50 Mb, 21 subscribers at >= 50 Mb and < 100 Mb, 30 subscribers at >= 100 Mb and < 1 Gb, 10 subscribers at >= 1 Gb, and 8 subscribers uncommitted to a speed tier | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | CNI, after receipt of a customer request, began offering Enhanced Ethernet Transport Service Ports. An Enhanced Ethernet Transport Service Port includes Internet Access Connectivity and Bandwidth for customer resale use. CNI has expanded its network reach through connectivity to 350 E. Cermak Street in Chicago, Illinois through dense wave division multiplexing with lit service termination to the INDATEL Services' Ethernet Exchange. This Ethernet Exchange allows for direct peering with Content Delivery Network (CDN) providers that has resulted in a marked improvement in CNI's Dedicated Internet Access service as noted by several wholesale service provider customers. | FALSE | CNI's management practices have not changed from the prior quarter. | In the upcoming quarter, CNI plans to close out all payments with vendors to liquidate all expenses. CNI plans to complete UCC filings. CNI plans to complete its project close-out audit. CNI plans to complete other close-out documentation as required with NTIA. | COM Net, Inc. | The major challenges impacting CNI's ability to advance the project toward the projections set out in the prior quarter were related to CNI's inability to secure approval of its 2012 route modifications by the start of the "no additional cost" extension period, to successfully secure access to conduit in the Dayton, Ohio market and to secure permits with Wright Patterson Air Force Base to complete the western route to Wright State University. CNI's inability to complete these activities with third parties caused CNI to focus its efforts to complete items that were within its own control prior to September 30, 2013. CNI was unable to complete the construction of approximately 3.6 miles from Liscum Avenue to W 2nd Street in Dayton, Ohio. This was driven by the fact that CNI's route modification was not approved until late July 2013, along with the fact that AT&T did not complete conduit make-ready work of removing lead sheathed cable in the Dayton area in order to allow CNI to proceed with cable placement. CNI is attempting to complete this construction prior to year end with plans to complete this construction by the end of the first quarter of 2014 weather permitting. CNI was, also, unable to complete the construction of a 5 mile fiber route from the intersection of Harshman Road and Beatrice Drive to CNI's partner's eastern route to Wright State University due to the delay in receiving approval of its route modification and permitting lead times with Wright Patterson Air F | No challenges or issues are foreseen for completing project closeout activities and final project audit.
NT10BIX5570073 | 2010 | Q4 | Q4 - 2010 | * Submitted RFPs and awarded for the following high level areas: 1) Construction; 2) Technology; 3) Materials * Submitted Draft Environmental Assessment. Work performed by EA consultant. * Finalized our GePON design. *Received aerial photos of our build for the ODOT permits. *Received some additional permits. Some entities are taking more time and effort to obtain the permits. *Engaged legal to begin our franchise research / negotiations. *Kick-off with our marketing group to define our Community Outreach Plan. *Sales team has starting contacting the community anchor tenants to sign contracts. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Build not started yet. | N/A | Build not started yet. | N/A | Build not started yet. | N/A | N/A | Build not started yet. | 0 | 0 | 0 | None at this time. | N/A | N/A | 0 | 0 | 0 | 0 | Network not built yet. | Network not built yet. | N/A | Network not built yet. | 0 | 0 | 0 | 0 | Build not started. | Build not started. | Build not started. | Build not started. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Build not started yet. | Build not started yet. | Build not started yet. | Build not started yet. | Build not started yet. | Community Anchor Institutions listed in the application receive 25% discount on their first five years only. | FALSE | No | *Receive FONSI on our Environmental Assessment. * Submit and award GePON construction RFP. * Submit and award Davis Bacon Wage audit RFP. * Obtain most of our remaining permits and franchises/agreements. * Negotiate contracts with construction contractors. * Hold community events. | Bend Cable Communications, LLC | The only area where we experienced an issue was working with the US Forest Service to obtain permits. We involved the Department of Commerce and the issue seems to be mitigated at this time. It appears the field office was not aware that we had received a grant and the Environmental Assessment procedures specific to BTOP projects. If we do not receive the US Forest Service permits in a timely manner, we will escalate accordingly. | As long as we receive FONSI and additional permits in this quarter, we should be able to stay on track.
NT10BIX5570073 | 2011 | Q1 | Q1 - 2011 | Behind due to delay in obtaining FONSI, we have not accomplished as much as anticipated this quarter: * We are in negotiations for two franchises. * We have signed two community anchor tenants. * We have purchased and receiving some materials. * We have submitted permits for 16 of the 20 entities; received permits from six entities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Behind due to delay in obtaining FONSI. | NA | NA | NA | Behind due to delay in obtaining FONSI. | NA | NA | Behind due to delay in obtaining FONSI. | 0 | 0 | 0 | None at this time. | NA | NA | 0 | 0 | 0 | 0 | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI.. | NA | Behind due to delay in obtaining FONSI. | 0 | 0 | 0 | 0 | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | Behind due to delay in obtaining FONSI. | Community anchor institutions listed in the application may receive 25% discount their first five years of service only. | FALSE |  | The following is all dependent on receiving FONSI this quarter. *Finalize construction contracts *Continue working with entities to obtain permits. *Hold community events. *Meet with CAIs and businesses to obtain signed contracts for service. *Break ground and start construction on at least one leg out of five. The one that has the two signed contracts. *Follow-up and closure with Federal agencies of BLM, Bureau of Reclamation, US Forest Service and Oregon SHPO. | Bend Cable Communications, LLC | As we are a for profit company and not familiar with the Environment Assessment process, we underestimated the potential time frame of obtaining FONSI. Currently, we are about 3.5 months past our initial expectations of obtaining FONSI due to various items. We have received substantial assistance from BTOP and the federal agencies to guide us through the process. | Due to having two signed CAI contracts, our priority of construction is one specific leg. Our focus will be on this leg to mitigate post-FONSI items and obtain necessary permitting. At this time, the items that we foresee that could delay the other routes would be federal permitting and city franchises. We will evaluate what routes to begin constructing depending on permits necessary, franchises and post-FONSI items.
NT10BIX5570073 | 2011 | Q2 | Q2 - 2011 | The following has been completed during this quarter: *Received Environmental Assessment Finding of No Significant Impact (FONSI) *Signed two out of two franchise agreements required. (Madras and La Pine) *Received most permits required except for USFS, BLM and Bureau of Rec. These are in progress as they were contingent on our receipt of our FONSI. *Signed an additional two Community Anchor Institutions for a total of four. *Reviewed project at the city of La Pine's council meeting. *We have received all of our construction materials including fiber. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | NA | NA | NA | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | NA | NA | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | 0 | 0 | 0 | None at this time. | None at this time. | NA | 0 | 0 | 0 | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | NA | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | 0 | 0 | 0 | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | 0 | 0 | 0 | 0 | 0 | NA - middle mile project | NA - middle mile project | NA - middle mile project | NA - middle mile project | NA - middle mile project | 0 | 0 | 0 | 0 | 0 | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | We anticipate to start construction mid September contingent on an utility company's response for pole attachment. | Community Anchor Institutions receive 25% discount on service if sign five year contract. | FALSE | NA | We anticipate to have the following complete next quarter: *Receipt of our outstanding construction permits (BLM, USFS, BoR) and one last utility. *Purchase of OTN technology equipment and re-bid GePON technology equipment. *Begin construction on three of the five main infrastructure legs. *Groundbreaking ceremonies in Madras, Sunriver and La Pine. | Bend Cable Communications, LLC | None. | If we need to determine multiple re-routes due to an utility company's response, it may delay construction due to performing EA due diligence.
NT10BIX5570073 | 2011 | Q3 | Q3 - 2011 | -Received federal entity permits from USFS, BLM and Bureau of Reclamation. -Held ceremonial ground breaking ceremony in Madras at the Community Anchor Institution of Central Oregon Community College. -Finalized construction contracts and held pre-construction meetings. -Third-party performed our one year audit and we had no areas of concern. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction has not begun yet. We anticipate to be 30% complete in Q1 2012; 67% in Q2 2012. | NA | Construction has not begun yet. We anticipate to be 30% complete in Q1 2012; 67% in Q2 2012. | NA | Construction has not begun yet. We anticipate to be 30% complete in Q1 2012; 67% in Q2 2012. | NA | NA | Construction has not begun yet. We anticipate to be 30% complete in Q1 2012; 67% in Q2 2012. | 0 | 0 | 0 | None at this time. | None at this time. | NA - we will operate the network. | 0 | 0 | 0 | 0 | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | NA | We will begin construction Q4 of 2011. | 0 | 0 | 0 | 0 | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | 0 | 0 | 0 | 0 | 0 | NA - middle mile project | NA - middle mile project | NA - middle mile project | NA - middle mile project | NA - middle mile project | 0 | 0 | 0 | 0 | 0 | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | We will begin construction Q4 of 2011. | Community Anchor Institutions receive 25% discount on service if sign five year contract | FALSE | NA | -We will start construction on five out of five routes. -We anticipate to complete the Sunriver to Spring Butte route. -We will resubmit two technology Request for Proposal to award in January -New network miles deployed - 29.83 -New network miles leased - NA -Total CAI subscribers served (CAIs connected) - 0 -Number of signed agreements with broadband wholesalers or last mile providers - 1 | Bend Cable Communications, LLC | * Time to receive federal permits was longer than anticipated. * Re-issued construction Request For Proposals (RFPs) due to underground mileage changes. * Re-issuing (2) technology RFPs due to change in requirements. | *Heavy snow could delay two out of our five routes. *Construction for all routes will be approximately one month complete by end of December. *We are currently one quarter behind our original baseline.
NT10BIX5570073 | 2011 | Q4 | Q4 - 2011 | *Started construction on three of the five main routes. *Submitted RFPs for GePON equipment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction in progress; anticipate 30% complete in Q1 2012; 67% in Q2 2012. | NA | Construction in progress; anticipate 30% complete in Q1 2012; 67% in Q2 2012. | NA | 8% of conduit installed for five main routes | NA | NA | Construction in progress; anticipate 30% complete in Q1 2012; 67% in Q2 2012. | 0 | 0 | 0 | None at this time. | None at this time. | NA | 0 | 0 | 0 | 0 | Construction in progress | Construction in progress | NA | Construction in progress | 0 | 0 | 0 | 0 | Construction in progress | Construction in progress | Construction in progress | Construction in progress | 0 | 0 | 0 | 0 | 0 | NA - middle mile and last mile business project | NA - middle mile and last mile business project | NA - middle mile and last mile business project | NA - middle mile and last mile business project | NA - middle mile and last mile business project | 0 | 0 | 0 | 0 | 0 | Construction in progress | Construction in progress | Construction in progress | Construction in progress | Construction in progress | Community Anchor Institutions receive 25% discount on service if sign five year agreement. | FALSE | NA | *Finish the Spring Butte route. *Award GePON RFP. * Send out and award OTN award *New network miles deployed - 30% *New network miles leased - NA *Total Community Anchor Institutions connected - 0 *Number of signed agreements with broadband wholesalers or last mile providers - 1 | Bend Cable Communications, LLC | *Actual construction firms obtaining materials from our warehouse and starting construction took longer than anticipated. | *To date, the weather has not impacted construction.
NT10BIX5570073 | 2012 | Q1 | Q1 - 2012 | *Significant construction progress on four out of five main routes. *Started construction on the fifth route. | 59 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | Construction in progress - 43% complete but not activated; anticipate 60% complete end of Q2 2012 and 100% complete in Q3 2012 including activation. Total of 133.81 miles of fiber to be deployed. | NA | NA | NA | Construction in progress - 43% complete but not activated; anticipate 60% complete end of Q2 2012 and 100% complete in Q3 2012 including activation. Total of 133.81 miles of fiber to be deployed. | NA | NA | Construction in progress - 43% complete but not activated; anticipate 60% complete end of Q2 2012 and 100% complete in Q3 2012 including activation. | 0 | 1 | 0 | In negotiations | In negotiations | NA | 0 | 0 | 0 | 0 | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | NA | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | 0 | 0 | 0 | 0 | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | 0 | 0 | 0 | 0 | 0 | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | 0 | 0 | 0 | 0 | 0 | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Construction in progress due to overall project delays; we will catch up to baseline by end of Q4. | Community Anchor Institutions receive 25% discount on service if sign five year agreement. | FALSE | NA | *Finish four of the five main routes. *Resend and award the GePON RFP. *Submit and award the OTN RFP. *Begin construction on GePON in Sunriver, Madras and La Pine. *Install equipment and activate signed Community Anchor Institutions. *New network miles deployed - 80% *New network miles leased - NA *Total Community Anchor Institutions connected - 5 *Number of signed agreements with broadband wholesalers or last mile providers - 1 | Bend Cable Communications, LLC | *Delays in construction due to necessary Environmental Asssessment re-route analysis. *The response to our GePON response was not adequate for our needs and will therefore re-send. The delay will have no impact to GePON construction. GePON equipment procurement is estimated to be no more than four weeks. | *None.
NT10BIX5570073 | 2012 | Q2 | Q2 - 2012 | *Out of five main routes; one completed; two almost complete and two will be complete by end of Q3. *Awarded and selected Passive Optical Network (PON) technology vendor. *Started construction on one of four Passive Optical Network (PON) areas. *Hired a new dedicated salesperson. *Finalized pricing and sales strategy. In process of pre-sales for businesses with much interest. | 113 | 0 | 0 | 0 | 113 | 0 | 0 | 0 | Construction in progress - 79% main routes complete but not activated, 138 main route miles total complete - remainder to be finished in Q3; Three out of four cities will be complete in Q3. 45 miles total for Passive Optical Networks (PON); 4.5 miles complete | NA | NA | NA | Construction in progress - 79% main routes complete but not activated, 138 main route miles total complete - remainder to be finished in Q3; Three out of four cities will be complete in Q3. 45 miles total for Passive Optical Networks (PON); 4.5 miles complete | NA | NA | Construction in progress; all will be activated by end of Q3. | 1 | 0 | 20 | Crestview Cable | NA | NA | 0 | 0 | 0 | 0 | NA | One signed agreement; will activate in Q3. | NA | 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point | 0 | 0 | 0 | 0 | Zero of CAIs are activated yet. We will begin to activate CAIs in July 2012. | Zero of CAIs are activated yet. We will begin to activate CAIs in July 2012. | Zero of CAIs are activated yet. We will begin to activate CAIs in July 2012. | 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point | 0 | 0 | 0 | 0 | 0 | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | NA - Middle mile and last mile business project | 512 | 0 | 0 | 0 | 0 | Construction is in progress; pre-sales in progress and activation in Q3/Q4. Note: some lots are empty or unoccupied. | Construction is in progress; pre-sales in progress and activation in Q3/Q4. | Construction is in progress; pre-sales in progress and activation in Q3/Q4. | Construction is in progress; pre-sales in progress and activation in Q3/Q4. | 4, 12, 25, 50 and 100 fiber (PON) services; 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point | Community Anchor Institutions receive 25% discount on service if sing five year agreement. | FALSE | NA | *Four of the five main routes will be complete. *Award the Optical Transport Network (OTN) vendor. *Four community events scheduled. *Complete PON construction in Madras, Sunriver and LaPine. *Install equipment and activate signed Community Anchor Institutes (CAIs) in Madras, Sunriver and La Pine. *New network miles deployed - 87% - 160 miles built out of 183. *Total Community Anchor Institutions connected - 7 *Total businesses connected - 10 *Number of signed agreements with broadband wholesalers or last mile providers - 1 | Bend Cable Communications, LLC | *Construction and pole permission delays due to various reasons delayed completion of our main routes and start of PON construction. | None.
NT10BIX5570073 | 2012 | Q3 | Q3 - 2012 | *Four of the five main routes are complete. *Activated six Community Anchor Institutions (CAIs) *Significant progress of GePON construction in Madras, Sunriver and La Pine. Activated four fiber business customers. *Received Optical Transport Network (OTN) gear. | 153 | 0 | 0 | 0 | 153 | 0 | 0 | 3 | Construction in progress - four of five main routes complete and activated, 133 main route miles total complete out of 133.81 - remainder to be finished in Q3; Four out of four cities will be complete in Q4. 45 miles total for Passive Optical Networks (PON); 20 miles complete | NA | NA | NA | 153 miles of 178.81 total; all to be complete in Q4. | NA | NA | 3 out of 7 activated | 1 | 1 | 20 | Crestview Cable in La Pine; negotiating with another provider projected to be signed in Q4. | NA | NA | 0 | 1 | 0 | 1 | NA | Crestview Cable | NA | 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point | 5 | 0 | 5 | 5 | Five CAIs laterals built and activated | NA | Five CAIs laterals built and activated. Five additional CAIs to be activated in Q4. | 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 512 | 6 | 0 | 6 | 6 | Businesses in Madras, La Pine, Sunriver and Prineville | Businesses in Madras | NA | Businesses in Madras | 4MB / 1.5MB; 12 MB / 1.5 MB; 25 / 25; 50/50; 100/100 - Shared fiber. 10MB, 50MB, 100MB and 1GB Direct Internet Access or Point to Point - dedicated fiber. | Community Anchor Institutions receive 25% discount on service if sign five year agreement. | FALSE |  | *Complete the last of the main routes *Complete the GePON construction in Madras, Sunriver, La Pine and Prineville *Install and test Optical Transport Network (OTN) *Activate cumulative 10 Community Anchor Institutions; 30 fiber businesses via GePON *No additional service providers projected for Q4 *178.81 projected miles to be complete | Bend Cable Communications, LLC | Continued delays of sub-contractors has delayed completion dates. | None
NT10BIX5570073 | 2012 | Q4 | Q4 - 2012 | *Complete with all aspects of the project except construction to remaining unsigned Community Anchor Institutions. *Activated 13 out of 21 signed CAI agreements. PON fiber was constructed in the communities of Madras, Prineville, Sunriver and La Pine to provide affordable fiber services to businesses as part of the grant. BendBroadband extended the infrastructure and activated 29 out of 41 signed contracts in those communities. | 178 | 0 | 0 | 0 | 178 | 0 | 0 | 7 | All main routes and Passive Optical Networks (PON) are complete | NA | NA | NA | All main routes and Passive Optical Networks (PON) are complete | NA | NA | 7 out of 7 activated | 1 | 1 | 20 | Crestview Cable in La Pine | NA | NA | 0 | 1 | 0 | 1 | NA | Crestview Cable | NA | 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | 13 | 0 | 13 | 13 | 13 out of 15 signed Community Anchor Institutes (CAIs) activated; two remaining are scheduled | NA | 13 out of 15 signed Community Anchor Institutes (CAIs) activated; two remaining are scheduled | 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 512 | 29 | 0 | 29 | 29 | Businesses in Madras, La Pine, Sunriver and Prineville | Business in Madras, La Pine, Sunriver and Prineville | NA | Business in Madras, La Pine, Sunriver and Prineville | 4MB/1.5MB; 12MB/1.5MB; 25/25 MB; 50/50 MB; 100/100MB - Shared fiber 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | Community Anchor Institutions receive 25% discount on service if sign five year agreement. | FALSE | NA | *Complete construction to remaining signed Community Anchor Institutions @ one fiber mile. *Four additional CAIs connected. *One broadband wholesaler / last mile provider agreement | Bend Cable Communications, LLC | None. | None.
NT10BIX5570073 | 2013 | Q1 | Q1 - 2013 | *Complete with all aspects of the project except construction to two Community Anchor Institutions. *Activated 13 out of 15 signed CAI agreements. PON fiber was constructed in the communities of Madras, Prineville, Sunriver and La Pine to provide affordable fiber services to businesses as part of the grant. BendBroadband extended the infrastructure and activated 40 out of 51 signed contracts in those communities. *Activated three non-CAI Metro Ethernet customers including a last mile service provider. | 178 | 0 | 0 | 0 | 178 | 0 | 0 | 7 | All main routes and Passive Optical Networks (PON) are complete (178 miles); .75 miles of the Community Anchor Institution laterals are complete for a total of 178.75 miles | NA | NA | NA | All main routes and Passive Optical Networks (PON) are complete (178 miles); .75 miles of the Community Anchor Institution laterals are complete for a total of 178.75 miles | NA | NA | 7 out of 7 activated | 2 | 0 | 20 | Crestview Cable in La Pine and Madras Zayo Networks | NA | NA | 0 | 1 | 1 | 2 | NA | Crestview Cable in La Pine and Madras | Zayo Networks | 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | 13 | 0 | 13 | 15 | 13 out of 15 signed Community Anchor Institutes (CAIs) activated; two remaining are scheduled | NA | 13 out of 15 signed Community Anchor Institutes (CAIs) activated; two remaining are scheduled | 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 512 | 42 | 0 | 42 | 42 | Businesses in Madras, La Pine, Sunriver and Prineville | Business in Madras, La Pine, Sunriver and Prineville | NA | Business in Madras, La Pine, Sunriver and Prineville | 4MB/1.5MB; 12MB/1.5MB; 25/25 MB; 50/50 MB; 100/100MB - Shared fiber 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | Community Anchor Institutions receive 25% discount on service if sign five year agreement | FALSE | NA | *Activation of remaining two signed Community Anchor Institutions of .25 miles for a total project miles of 179 miles. *Project closeout *Preparation for final audit | Bend Cable Communications, LLC | For the grant, we identified a specific number of Community Anchor Institutions. Our challenge has been to activate the total amount due to existing contracts with other providers. | None
NT10BIX5570073 | 2013 | Q2 | Q2 - 2013 | The Central Oregon Fiber Alliance was very successful. It enabled the addition of a high-speed infrastructure between the communities of Madras, Sunriver, Prineville and LaPine that did not exist previously. Also, this addition, enabled additional middle-mile and last mile providers to increase the bandwidth available to their end customers. With the data center growth in Prineville, it enabled a North/South to San Francisco / Silicon Valley broadband route in partnership with other providers in addition to the existing East/West broadband routes to Portland and Seattle. The Central Oregon region is an area that is expected to grow in population, additional businesses and jobs. Due to the high capacity broadband infrastructure, the region is able to continue to lure businesses from urban areas to highly desirable Central Oregon. By connecting 15 Community Anchor Institutions, especially regional community colleges, school districts, government and hospitals were able to extend their broadband access to satellite locations in these communities. The ability for these entities to have access to high capacity broadband is paramount to their success in the Central Oregon community's continued growth. The Bend LaPine school district just launched a pilot iPad program to many of their schools. This is just one example of where the enhanced broadband infrastructure enables the Central Oregon community. Also, small businesses in Madras, Prineville, Sunriver and LaPine now have access to affordable Internet and phone services over highly reliable fiber. | 178 | 0 | 0 | 0 | 178 | 0 | 0 | 7 | All main routes and Passive Optical Networks (PON) are complete (178 miles); .75 miles of the Community Anchor Institution laterals are complete for a total of 178.75 miles | NA | NA | NA | All main routes and Passive Optical Networks (PON) are complete (178 miles); .75 miles of the Community Anchor Institution laterals are complete for a total of 178.75 miles | NA | NA | 7 out of 7 activated. | 2 | 0 | 20 | Crestview Cable in La Pine and Madras Zayo Networks | NA | NA | 0 | 1 | 1 | 2 | NA | Crestview Cable in La Pine and Madras | Zayo Networks | 10MB, 50MB, 100MB and 1 GB Direct Internet Access or Point to Point | 15 | 2 | 13 | 15 | 15 out of 15 signed Community Anchor Institutes (CAIs) activated | 2 out of 15 signed Community Anchor Institutes (CAIs) activated | 13 out of 15 signed Community Anchor Institutes (CAIs) activated | 10MB, 50MB, 100MB and 1GB Direct Internet Access and Point to Point. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 512 | 45 | 0 | 45 | 45 | Businesses or lots in Madras, La Pine, Sunriver and Prineville. | Businesses in Madras, La Pine, Sunriver and Prineville. | NA | Businesses in Madras, La Pine, Sunriver and Prinevile. | 4MB/1.5 MB; 12MB/1.5MB; 50/50MB, 100/100MB- shared fiber 10MB, 50MB, 100MB, and 1 GB Direct Internet Access or Point to Point | Community Anchor Institutions (CAIs) who signed a five year contract prior to project close (June 30, 2013), received a 25% discount. | FALSE | NA | This project is complete and will only be performing the required project audit. | Bend Cable Communications, LLC | None. | None. Please note that the final budget is more than the original. BendBroadband provided additional funds to complete the project.
NT10BIX5570074 | 2010 | Q4 | Q4 - 2010 | A detailed map of the fiber route including potential Community Anchor Institution's for the project was developed. The Environmental Assessment was completed and a draft was submitted during this quarter. Negotiations for new collocation space in Jackson, MS also occurred. A Computer Aided Drafting department was created and three new employees were hired along with an outside construction project manager. Heavy equipment was located and procured. Baseline reports were submitted and finalized. Progress was made on developing Requests for Proposal's for route construction, fiber and equipment purchases etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | N/A | N/A | No Variance from baseline | 0 | 2 | 0 | not applicable, construction not started | not applicable, construction not started | N/A | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Receipt of Finding Of No Significant Impact. Release and award of construction Requests for Proposal(s). Ground breaking/beginning of construction. | Contact Network Inc. d/b/a InLine | The environmental assessment process has used resources that would have been used to design network, obtain rights of ways and permits, as well as, issue requests for proposal's for procurement and construction. Reassignment of these resources to tackle issues within the environmental assessment has caused variance in the initial baseline figures. In addition, inconsistent instructions and/or changes/clarification on required forms for reporting has used internal resources that typically would be used to process rights of way, obtain permits etc. We need the ability to make decisions on our own or have National Telecommunications and Information Administration respond in a more timely fashion (i.e: Fiber Strand Miles in the Annual Performance Progress Reports). | If Finding Of No Significant Impact is not received further delays are expected in permitting, rights of way etc. Also, if changes are necessary and requested, delayed responses from National Telecommunications and Information Administration could also impact the planned progress above.
NT10BIX5570074 | 2011 | Q1 | Q1 - 2011 | A response to the Environmental Assessment draft submitted in the prior quarter was received from the National Telecommunication and Information Administration along with a matrix of questions that needed to be addressed during this quarter. All questions were addressed and a final Environmental Assessment was sent. In March, we received the Finding of No Significant Impact from the National Telecommunication and Information Administration. In anticipation of receiving our Finding of No Significant Impact, we began riding all routes and submitting applications to attach to utility poles in the initial build counties. One administrative person was hired to process pole attachment agreements. Meetings were held with the Electric Power Associations involved and pole attachment agreements with the Electric Power Associations were negotiated. Construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Army Corp of Engineer and Railroad permitting also began during this quarter. Collocation space in Jackson, Mississippi was procured. Windstream responded to our initial contact regarding the potential overlap of our federally funded projects, confirming no overlap existed. The overlap special award condition was finalized and submitted through grants online. Face to face meetings were held with potential Community Anchor Institutions. A tot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | N/A | N/A | No Variance from Baseline | 0 | 2 | 0 | Not applicable, currently we have no signed agreements | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet; 100Mbps Private Network; 100Mbps Fiber Connection with Internet; 1000Mbps Private Networs have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet; 100Mbps Private Network; 100Mbps Fiber Connection with Internet; 1000Mbps Private Network | not applicable; we do not have a third party to operate all or part of our network. | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline, we are currently in negotiation with a couple of providers but have nothing signed at this point. | No Variance from Baseline | 10Mbps/100Mbps/1000Mbps Private WAN; 10Mbps/100Mbps Fiber Connection with Internet | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 10Mpbs/100Mbps/1000Mbps Private WAN; 10Mbps/100Mbps Fiber Connection with Internet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Network management practices have not changed | During the next quarter the fiber and materials RFP will be awarded and materials for construction will be purchased. Also, the construction RFP will be awarded. An RFP for equipment will be released, awarded and equipment will be purchased. Pole attachment agreements will be finalized. Pole attachment applications will be finalized. Railroad crossing permits will be secured. Army Corp of Engineers approval letters and/or permits will be received. Construction permits will be received. Contractors will begin construction on both aerial and burial components of our route. All twenty-two community anchor institutions for which contracts have been received will be connected during this quarter. | Contact Network Inc. d/b/a InLine | We have been trying for six months to obtain a franchise agreement with the City of Jackson and have had no success. Also, one of our competitors is creating doubt with our end userâ€™s regarding aerial fiber due to the recent tornados. Our customers are now requesting all fiber to be buried. The budget we submitted was based on an aerial/burial combination. | The tornados that came through our area on April 27, 2011 slowed the progress of our aerial pole attachment applications. The utility companies have pulled their crews to work on restoring services in the damaged areas instead of processing our new attachment requests. Likewise, the Mississippi River flooding is causing the same types of delays with both the utility companies and Rail Roads that are processing our Crossing Applications.
NT10BIX5570074 | 2011 | Q2 | Q2 - 2011 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. All Army Corp of Engineer and railroad permits applied for were approved and received. The pole attachment permits, Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. The fiber and materials, huts and aerial/burial construction requests for proposals were awarded during this quarter. Purchases from these requests for proposals were made and construction began. A total of fifteen Community Anchor Institutions were connected during this quarter. | 61 | 0 | 0 | 0 | 61 | 0 | 0 | 3 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No Variance from Baseline | 0 | 2 | 0 | Not applicable, currently we are still in negotiations and do not have any signed agreements in place. | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 15 | 0 | 15 | 15 | We secured contracts with three K-12 school districts which totaled twenty-two Community Anchor Institutions. During this quarter we connected fifteen of these twenty-two schools, which exceeds our baseline projections of twelve Community Anchor Institutions. | No Variance from Baseline | We secured contracts with three K-12 school districts which totaled twenty-two Community Anchor Institutions. During this quarter we connected fifteen of these twenty-two schools, which exceeds our baseline projections of twelve Community Anchor Institutions. | Fourteen of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Construction will continue to the seven anchor institutions that were not connected during last quarter. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. We will be issuing a request for proposals for hand holes. Additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be negotiated in counties where our next build will take place and permits will be secured. Once permits/approvals are secured construction will continue. | Contact Network Inc. d/b/a InLine | We have made some progress in regards to the franchise agreement with the City of Jackson, Mississippi. However, we are still in negotiation and have yet to secure a signed agreement. We are still experiencing the same issues with one of our competitors creating doubt with our potential end users regarding aerial fiber due to the recent tornados. Our customers are continuing to request all buried fiber. | We are experience long lead times for delivery of our fiber optic cable. Also, the Electric Power Associations are overwhelmed due to the inclement weather and the volume of pole applications being filed. They cannot seem to produce the applications/approvals and complete any make ready needed in a timely fashion. We are also experiencing delays in aerial applications with the ILEC as well.
NT10BIX5570074 | 2011 | Q3 | Q3 - 2011 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation, various City and County governments. Army Corp of Engineer and railroad permits were also applied for and approved. Pole attachment permits, Mississippi Department of Transportation, City and County permits were submitted and approved. Additional fiber was ordered during this quarter, the vault request for proposal was awarded and orders placed. A total of 76 new miles of fiber was constructed and we have twenty-one Community Anchor Institutions connected. | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 6 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No Variance from baseline. | 1 | 2 | 80 | PEG Bandwidth | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | Negotiations were finalized, contract signed and and service began with PEG Bandwidth which is an increase versus our baseline projections. | No variance from baseline. | No variance from baseline. | 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network - 1 subscriber | 21 | 0 | 21 | 21 | During this quarter we connected six additional Community Anchor Institutions which is just below our baseline projections of thirty-three. | No Variance from baseline. | During this quarter we connected six additional Community Anchor Institutions which is just below our baseline projections of thirty-three. | Twenty of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections ; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Negotiations with our fiber vendors will continue to secure fiber deliveries and additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be continue to be negotiated in counties where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate to install 149 miles of new fiber and connect 30 CAIâ€™s. We do not plan to lease any fiber during next quarter. We do not anticipate any new signed agreements with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We have made some progress in regards to the franchise agreement with the City of Jackson, Mississippi. However, we are still in negotiation and have yet to secure a signed agreement. We are experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits we submit. Also the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. The Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | We need to have the route changes approved by NTIA during the next quarter and we expect to still have long lead time for fiber and hand holes.
NT10BIX5570074 | 2011 | Q4 | Q4 - 2011 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Army Corp of Engineer and railroad permits were applied for and approved. Pole attachment permits were submitted. A new pole attachment agreement was negotiated with Southwest MS Electric Power Association. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. Additional fiber was ordered during this quarter and a few deliveries of fiber were received. Purchase Orders were issued against the vault request for proposal that was awarded last quarter. All route modifications weres ubmitted to the grants office and necessary governmental agencies for approval. A total of 12 new miles of fiber was constructed bring our total to112 miles. Twelve additional Community Anchor Institutions were connected during this quarter, bringing the total to thirty three Anchor Institutions Connected. | 112 | 0 | 0 | 0 | 112 | 0 | 0 | 6 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | 1 | 2 | 80 | PEG Bandwidth | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | Baseline anticipated we would not have an agreement for new access, however we were able to secure a contract with a new Broadband Wholesaler/Last Mile Provider | Negotiations are still ongoing. | No Variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 33 | 0 | 33 | 33 | During this quarter we connected twelve additional Community Anchor Institutions which varies from our baseline projection. | No Variance from baseline. | During this quarter we connected twelve additional Community Anchor Institutions which varies from our baseline projection. | Thirty two of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections ; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Negotiations with our fiber vendors will continue to secure fiber deliveries and additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be continue to be negotiated in counties where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate approval of our route changes will be received which will enable us to install 117 miles of new fiber and connect 60 CAIâ€™s. We do not plan to lease any fiber during next quarter. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. The Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Due to changes in route and hut locations more environmental studies will have to be conducted and approvals will have to be obtained. Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As winter comes to an end and spring approaches, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2012 | Q1 | Q1 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Pole attachment permits were submitted. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A few deliveries of fiber and hand holes were received. All route modifications submitted last quarter to the grants office and necessary governmental agencies were approved. The approval of the route modifications allowed us to release over 100 miles to contractors. As a result 68 new miles of fiber were constructed bringing our total to 180 miles. Also 24 additional Community Anchor Institutions were connected during this quarter, bringing the total to fifty seven Anchor Institutions Connected. | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 8 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | We are a quarter behind on this upgrade. These 14 miles will be upgraded during the second quarter of 2012. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | 1 | 2 | 80 | PEG Bandwidth | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | Baseline anticipated we would not have an agreement for new access, however we were able to secure a contract with a new Broadband Wholesaler/Last Mile Provider | Negotiations are still ongoing. | No Variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 57 | 0 | 57 | 57 | During this quarter we connected twenty four additional Community Anchor Institutions which varies from our baseline projection. | No Variance from baseline. | During this quarter we connected twenty four additional Community Anchor Institutions which varies from our baseline projection. | Fifty six of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections ; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Additional route changes will be submitted to the grants office once approval from State and Local entities are approved. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Negotiations with our fiber vendors will continue to secure fiber deliveries also other resources for fiber will be researched. Franchise agreements will be continue to be negotiated in counties where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 350 miles of new fiber; upgrading of 14 miles of existing fiber; the lease of additional fiber and to connect an additional 50 CAIâ€™s. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. During this quarter, we were notified by Mississippi Power that they have contracted with an outside company to process the engineering for the pole attachment applications and that they would be passing this per pole cost on to us. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. While we have received small shipments of fiber, we still are in desperate need of more deliveries. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. Fiber availability will continue to be an issue.
NT10BIX5570074 | 2012 | Q2 | Q2 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad permits were applied for and approved. Pole attachment permits were submitted and approved. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A few deliveries of fiber were received. Additional Hand Holes/Vaults were also received this quarter. A total of 234 new miles of fiber was constructed bringing our total to 414 miles. Twenty-five additional Community Anchor Institutions were connected during this quarter, bringing the total to eighty two Anchor Institutions Connected. | 414 | 0 | 14 | 0 | 414 | 0 | 0 | 16 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 2 | 1 | 80 | PEG Bandwidth, Windstream | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 2 | 0 | 0 | 0 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | Negotiations are still ongoing. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 2 subscribers | 82 | 0 | 82 | 82 | During this quarter we connected 25 additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected 25 additional Community Anchor Institutions which varies from our baseline projections. | Seventy one of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections ; ten are receiving 100Mbps Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Additional route changes will be submitted to the grants office once approval from State and Local entities are approved. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 120 miles of new fiber; the lease of additional fiber and to connect an additional 25 Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2012 | Q3 | Q3 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad permits were applied for and approved. Pole attachment permits were submitted and approved. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A few deliveries of fiber were received. Additional Hand Holes/Vaults were also received this quarter. A total of 102 new miles of fiber was constructed bringing our total to 516 miles. Four additional Community Anchor Institutions were connected during this quarter, bringing the total to eighty six Anchor Institutions Connected. | 516 | 0 | 14 | 0 | 516 | 0 | 0 | 20 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 3 | 1 | 60 | PEG Bandwidth, Windstream, Bailey Cable TV | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 3 | 0 | 0 | 0 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | Negotiations are still ongoing. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 3 subscribers | 86 | 0 | 86 | 86 | During this quarter we connected four additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected four additional Community Anchor Institutions which varies from our baseline projections. | Seventy four of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections ; eleven are receiving 100Mbps Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 80 miles of new fiber; the lease of additional fiber and to connect an additional 27 Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2012 | Q4 | Q4 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad permits were applied for and approved. Pole attachment permits were submitted and approved. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A few deliveries of fiber were received. Additional Hand Holes/Vaults were also received this quarter. A total of 49 new miles of fiber was constructed bringing our total to 565 miles. Four additional Community Anchor Institutions were connected during this quarter, bringing the total to fifty four Anchor Institutions Connected. | 565 | 0 | 14 | 0 | 565 | 0 | 0 | 21 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No Variance from baseline | 4 | 1 | 60 | PEG Bandwidth, Windstream, Bailey Cable TV, DSL by Air | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 4 | 0 | 0 | 0 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | Negotiations are still ongoing. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-one subcriber; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 3 subscribers | 54 | 0 | 54 | 54 | During this quarter we connected four additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected four additional Community Anchor Institutions which varies from our baseline projections. | Fifty one of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections, twenty of which are also receiving internet access ; none are receiving 500Mbps Private WAN connections; one is receiving 100Mbps Private WAN Connections; one is receiving a 100Mbps Private WAN Connection with Internet Access; one is receiving a 10Mbps Private WAN Connection; none are receiving 10Mbps connections with Internet Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 30 miles of new fiber; the lease of additional fiber and to connect an additional 41 Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits, which are taking on average six weeks to secure and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits and Railroad permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2013 | Q1 | Q1 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad permits were applied for and approved. Pole attachment permits were submitted and approved. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A few deliveries of fiber were received. Additional Hand Holes/Vaults were also received this quarter. A total of five hundred and sixty five miles of fiber have been constructed bringing our total to 565 miles. We have connected a total of seventy four Anchor Institutions Connected. By the end of June 2013, Contact Network Inc. plans to have built 680 miles of new fiber construction, leased another 233 miles of fiber and connected over 300 Community Anchor Institutions. This will exceed our grant application by 100 Community Anchor Institutions and 40 miles. | 565 | 0 | 14 | 0 | 565 | 0 | 0 | 23 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 4 | 1 | 60 | PEG Bandwidth, Windstream, Bailey Cable TV, DSL by Air | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 4 | 0 | 0 | 0 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | Negotiations are still ongoing. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-one subcriber; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 3 subscribers | 74 | 2 | 72 | 74 | During this quarter we connected twenty additional Community Anchor Institutions which varies from our baseline projections. | Two of the locations we are servicing are newly built Board of Education office and Police Station and weren't part of our baseline projections | During this quarter we connected twenty additional Community Anchor Institutions which varies from our baseline projections. | Seventy one of the Community Anchor Institutions are receiving 1000Mbps Private WAN connections, twenty of which are also receiving internet access ; none are receiving 500Mbps Private WAN connections; one is receiving 100Mbps Private WAN Connections; one is receiving a 100Mbps Private WAN Connection with Internet Access; one is receiving a 10Mbps Private WAN Connection; none are receiving 10Mbps connections with Internet Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate completion of the construction and finalization of the leased network miles. Negotiations will continue with wholesale broadband or last mile providers. By the end of next quarter we plan to have 680 miles of newly constructed fiber, 233 miles of leased fiber and 202 CAI's connected to our network. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits, which are taking on average six weeks to secure and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits and Railroad permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2013 | Q2 | Q2 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad permits were applied for but not yet approved. Pole attachment permits were submitted and approved. Mississippi Department of Transportation and City and County permits were also approved and received during this quarter. A total of one hundred twelve miles of fiber were constructed and an additional two hundred sixty three miles were leased. As of June 30, 2013 the total miles constructed is 677 miles. We connected an additional sixty five Anchor Institutions during this quarter bringing the total Anchors connected to 139. By the end of September 2013, Contact Network Inc. plans to have built 686 miles of new fiber construction and connected over 200 Community Anchor Institutions. Also, for the Budget Execution Details listed on the last page, when information was gathered for the UCC filings during this quarter, it was determined that 4 purchase orders were received incorrectly which caused the Land and Structures category (too high in Q1) as well as the Equipment category (too low in Q1) to be reported incorrectly for Q1. Equipment that was in the initial application budget under the Equipment category, not Land and Structures category, was received and posted to Land and Structures in error. This error was corrected during this quarter. The amounts reported under Land and Structures and Equipment for Q1 were incorrect, the amounts reported in those categories for Q2 are now correct. | 677 | 263 | 14 | 0 | 677 | 0 | 0 | 24 | This number exceeds our baseline projection. | This number exceeds our baseline projection. | No variance from baseline | No variance from baseline | This number exceeds our baseline projection. | N/A | N/A | No variance from baseline | 4 | 1 | 60 | PEG Bandwidth, Windstream, Bailey Cable TV, DSL by Air, | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 4 | 0 | 0 | 4 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | Negotiations are still ongoing. | No variance from baseline | 10Mbps = 1 Subscriber 100Mbps = 0 Subscribers 500Mbps = 0 Succribers 1000Mbps = 3 Subscribers | 139 | 2 | 137 | 5 | During this quarter we connected sixty five additional Community Anchor Institutions which varies from our baseline projections. We are working aggressively to catch up the Baseline Projections | Two of the locations we are servicing are newly built Board of Education office and Police Station and weren't part of our baseline projections | During this quarter we connected sixty five additional Community Anchor Institutions which varies from our baseline projections. | 10Mbps = 1 Subscriber 50Mbps = 0 Subscribers 100Mbps = 3 Subscribers 500Mbps = 0 Subscribers 1000Mbps = 135 Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | Our network management practices have not changed. | The final railroad permit will be received and construction will be finished. All approved laterals will be constructed. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Negotiations will continue with wholesale broadband or last mile providers; if negotiations are successful we should connect one more wholesale provider next quarter. By the end of next quarter we plan to build nine additional miles bringing the total to 686 miles of newly constructed fiber and to connect an additional sixty three CAI's bringing the total CAI's connected to 202. | Contact Network Inc. d/b/a InLine | Our biggest challenge faced during this quarter was obtaining needed Railroad permits to finish our construction. Also, there were many construction delays due to rain. | As always in the south, weather could also have an impact on our planned progress.
NT10BIX5570074 | 2013 | Q3 | Q3 - 2013 | Prior to InLine constructing of a fiber network and the competitive climate in which this has created, many Mississippi schools, libraries, government facilities and healthcare organizationsâ€™ broadband connectivity was too slow, with insufficient bandwidth. At present, we have connected over 195 CAIs at many times, migrating them from T-1 and other legacy service to 10-1000 MBPS Internet connections and 1-10 GBPS Ethernet-Class services. Mississippi Health Care Facilities have taken advantage of this newly constructed fiber. Many of these Health Care Facilities are now preparing to take advantage of federal funding distributed via the USAC Rural Health Care and the New Health Care Connect program due to the very fact that fiber now exist in their area. Local municipalities have signed up and are now providing their facilities the needed bandwidth to serve their community and citizens better. As a result of the miles constructed/leased and because of our extensive outreach efforts, we have established agreements with several wholesale providers in our affected area, allowing them to expand the reach of the services they provide to local communities. Several of the Mississippi school districts have taken a bold move in moving away from the current state telecommunication contract, which was high in cost and limited the districts ability to provide their students the needed broadband by going out for bid for their needed service. The average district who has bid in the past two years for services is paying less than half the contract prices offered by the Mississippi Department of Education circuit offerings per Mbps and much less than that when compared to the current State offered contract circuit costs. Based on State of Mississippi March 2013 Enrollment data and a self reported 2013 â€“ 2014 K12 Internet Enrollment Figures, 36 Districts with a total of 186,636 Students have drastically reduced their internet/bandwidth cost in the past three years since this project begin. One particular tenant of the original NTIA grant was to encourage competition, which would lower prices. InLine has achieved this very tenant within our project area. Not only did we reduce the cost to the many of our original CAIs that elected to move forward with our fiber offering, but also we affected the entire pricing structure within our Fiber footprint. We are proud to note that our original baseline goal was to construct 635 miles of fiber, upgrade 14 miles of fiber and lease 233 miles of fiber for a total of 882 miles. Following approved modifications during our project, we were actually able to construct 687 miles, upgrade 14 miles and lease 263 miles for a total of 964 miles (109% more than our baseline goal). Here at InLine, we feel that we have not only been able to provide needed broadband to an underserved area, but we have truly Improve the â€˜Quality of Life for many Citizens of Mississippi. It is our hopes that we will be able to continue this improvement in additional areas of the state in the future. | 687 | 263 | 14 | 0 | 687 | 0 | 0 | 24 | This number exceeds our baseline projection. | This number exceeds our baseline projection. | No variance from baseline | No variance from baseline | This number exceeds our baseline projection. | N/A | N/A | No variance from baseline | 5 | 0 | 60 | PEG Bandwidth, Windstream, Bailey Cable TV, DSL by Air, Netlink Voice, | Our wholesale service offerings include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 4 | 1 | 0 | 4 | Baseline projections did not include any Broadband Wholesalers or Last Mile Providers receiving new access | We were able to provide more Broadband Wholesalers or Last Mile Providers with new access versus the improved access as anticipated in our baseline projects. | No variance from baseline | 10Mbps = 1 Subscriber 100Mbps = 1 Subscribers 500Mbps = 0 Subscribers 1000Mbps = 3 Subscribers | 195 | 2 | 193 | 6 | During this quarter we connected four additional Community Anchor Institutions which varies from our baseline projections. If the pending route modification is approved we should exceed our baseline projections. | Two of the locations we are servicing are newly built Board of Education office and Police Station and weren't part of our baseline projections | During this quarter we connected fifty six additional Community Anchor Institutions which varies from our baseline projections. | 10Mbps = 7 Subscriber 20Mbps = 1 Subscriber 50Mbps = 12 Subscribers 100Mbps = 16 Subscribers 500Mbps = 7 Subscribers 1000Mbps = 152 Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | Our network management practices have not changed. | During the next quarter we will be undergoing the final audit per BTOP requirements. We will also file all UCC Filings and complete close out. | Contact Network Inc. d/b/a InLine | There were no challenges or issues faced during this past quarter. | We do not anticipate issues or challenges during the next quarter.
NT10BIX5570075 | 2010 | Q4 | Q4 - 2010 | During the third reporting quarter (from October 1st, 2010 through December 31st, 2010), Internet2 continued to make significant progress towards building a successful U.S. UCAN infrastructure. Major accomplishments during this period include: 1) Completed evaluation of responses to optical network equipment request for pricing; 2) Selected vendors and equipment for optical network implementation 3) 95% completion of network optical and routing layer designs and implementation plan; 4) 75% completion of the design to integrate the peering service with U.S. UCAN; 5) Completed the process of articulating and posting network practices and policies (see "http://www.internet2.edu/network/network_mgmt_policy.html"http://www.internet2.edu/network/network_mgmt_policy.html); 6) Finalized contract terms for major supplier of optical fiber; 7) Purchased equipment to upgrade eight existing Juniper T640 routers to the state-of- the-art Juniper T1600 routers. These upgrades will be placed in service during Q1 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 20 | 0 | 4 | These are the URLs of the last mile providers: www.cenic.org, www.3rox.net,www.cic.uiuc.edu,www.sox.net,www.greatplains.net,indiana.gigapop.net,kyron.ky.gov,www.tx-learn.org,www.loni.org,www.magpi.net,wiki.maxgigapop.net,www.mcnc.org,www.merit.edu,www.mren.org,www.nox.org,www.nysernet.org,www.uoregon.edu,www.pnw-gigapop.net,www.memphis.edu,www.uen.org | Two 5 gigabit network connections $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, sub recipient of the project, operates the network on the behalf of Internet2. Their contact information follows: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan St Indianapolis, IN 46202 USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 0 | 20 | 0 | 3 | NA | The project had anticipated one of the providers splitting into two providers, resulting in an increase in the number. This did not occur. | NA | 5 subscribers of two 5 gigabit network connections 6 subscribers of one 10 gigabit network connections 9 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast access in addition to the normal IPv4 connectivity. | FALSE | NA | - Completion of the IRU agreement with our major supplier Level 3. - The upgrade of approximately four core routers and the placement of four former core routers into the peering service portion of the network - Appointment of an interim Director of the US UCAN organization. - Completion of the optical platform agreement. - | University Corporation For Advanced Internet Development | NA | We may need to seek advice on re-structuring what were anticipated to be sub-recipient agreements with the member of the Northern Tier Network Consortium. One or more Northern Tier Members may be unable to fully comply with the flow-down requirements. We may seek to retain ownership of the federally acquired assets and structure a more conventional agreement for them to reflect the value their contribution of fiber brings to the project.
NT10BIX5570075 | 2011 | Q1 | Q1 - 2011 | Contracts Internet2 executed additional contracts with Level3 communications to provide additional support for optical equipment installation, remote hands, and monitoring. Internet2 also executed a purchasing agreement with Ciena Networks to provide the majority of optical equipment on the acquired dark fiber. Dark Fiber and Optical Network Implementation Internet2 began close collaboration with Level3, Indiana University, and Ciena networks to begin implementing the first phase of the optical build. This included: â€¢ ordering and beginning colocation build-outs along the phase 1 footprint â€¢ coordinating on a management network topology â€¢ developing finalized optical network analysis and implementation details â€¢ coordinating equipment installation and management training â€¢ receipt and inventory of initial phase 1 optical purchases â€¢ splicing the phase 1 optical system at various points to align with the acquired footprint â€¢ transmission of fiber loss data to Internet2 for review â€¢ receipt and installation of a lab environment IP Network Implementation In February, Internet2 began the process of installing the Juniper T-1600 routers that were purchased in the PY1Q2. At six Internet2 core nodes, these routers will replace the Juniper MX960 routers that were previously providing Internet2 backbone services. In each city, the MX960 node will be repurposed into the Internet2 TR-CPS network that provides Commodity Internet peering service to Internet2 members. I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | We expect to accept approximately 4,626 miles of IRU segments during 2011 Q2. | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | Two 5 gigabit network connections $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/ms $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, sub recipient of the project, operates the network on the behalf of Internet2. Their contact information follows: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan St Indianapolis, IN 46202 USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 0 | 20 | 0 | 3 | NA | The project had anticipated one of the providers splitting into two providers, resulting in an increase in the number. This did not occur. | NA | 5 subscribers of two 5 gigabit network connections 6 subscribers of one 10 gigabit network connections 9 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast access in addition to the normal IPv4 connectivity. | FALSE | NA | Dark Fiber and Optical Network Implementation Internet2 anticipates receipt of all remaining fiber test data on the Phase 1 optical footprint. Level3 will begin installation of the Ciena ActiveFlex 6500 optical network beginning on the east coast. From there, they will move westward along the Phase 1 optical footprint. System installation will include physical installation of the nodes, cabling, system configuration, external reachability, documentation and system testing. Systems engineers from Internet2 and the Internet2 NOC at Indiana University will be working closely to develop backoffice systems that will provide management and monitoring of the optical network build once itâ€™s complete. This includes the final engineering of a management IP network that will provide a data communications path between the Internet2 and Level3 network operations centers, as well as systems development to integrate device alarms with each organizationâ€™s existing monitoring systems. Ciena and Internet2 engineers will also be participating in Ciena installation and management training classes prior to network installation and turnup. IP Network Implementation Internet2 will continue the process of installing the Juniper T-1600 routers in the remaining three colocation facilities: Atlanta, New York and Cleveland. This will position Internet2â€™s IP network to provide 100GigE IP backbone circuits when the Phase I optical build is complete. Because of the shorter reach of the initial 1 | University Corporation For Advanced Internet Development | No additional challenges or issues have been faced during this past quarter in achieving planned progress against project milestones. | No challenges or issues are anticipated during the next quarter that may impact planned progress against the project milestones.
NT10BIX5570075 | 2011 | Q2 | Q2 - 2011 | Dark Fiber and Optical Network Implementation Internet2 worked with its vendors, Ciena Networks and Level3 Networks, to install and complete the coast-to-coast Phase 1 optical network. This included: -Receipt and acceptance of Level3 fiber test result data -Completion of all colocation facility builds and augments on the Phase 1 footprint -Receipt, inventory and acceptance of all Phase 1 Ciena optical equipment in a staging facility in Broomfield, CO -Installation, powering and IP connectivity to Phase 1 Ciena optical equipment -Installation of 4 remote access management routers to provide IP reachability to the Internet2 NOC -Order of Ciena optical equipment element management system (EMS) -Order, delivery, and staging of Ciena optical element management system hardware platform -Completion of optical system BER testing on Phase 1 optical segments east of Cleveland IP Network Implementation Completion of the the first phase of IP router upgrades: six Juniper MX 960 routers were replaced with Juniper T-1600 routers that will provide 100GigE backbone connectivity. All six of the swapped-out MX960 routers were repurposed into the Internet2 TransitRail-Commercial Peering Service (TR-CPS) network as part of the upgrade of aging routing hardware. Orders were placed for support equipment for the new Internet2 IP router node in Cleveland. Engineers installed the 100GigE interfaces in the IP routers to pre-position them for connectivity when the Internet2 Phase 1 optical build is co | 0 | 4828 | 0 | 0 | 0 | 0 | 0 | 24 | NA | 63 miles less than baseline due to baseline discrepancy in overestimated mileage between Chicago and Cleveland | NA | NA | NA | NA | NA | 63 miles less than baseline due to baseline discrepancy in overestimated mileage between Chicago and Cleveland As part of the 4,828 miles of new IRU fiber, we have secured 24 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation spacee to baseline discrepancy in overestimated mileage between Chicago and Cleveland As part of the 4,828 miles of new IRU fiber, we have secured 24 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation space. | 0 | 0 | 0 | NA | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo3 | The Indiana University Global Research Network Operations Center, sub-recipient of the project, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 0 | 20 | 0 | 3 | NA | The project had anticipated that one of the providers would split into two, resulting in an increase in this number. This did not occur. | NA | 5 subscribers of two 5 gigabit network connections 6 subscribers of one 10 gigabit network connections 9 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The projects offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity | FALSE | NA | Dark Fiber and Optical Network Implementation Internet2 anticipates the completion of network testing and acceptance of the Phase 1 Optical installation and full commissioning of the system in a production capacity. Internet2 also anticipates the order of remaining dark fiber to substantially or fully complete the national dark fiber footprint. Internet2 should receive the majority of Phase 2 footprint dark fiber test results from Level3 communications and will be in the process of fiber acceptance. Internet2 will have placed orders for the Phase 2 optical equipment and begun receiving and inventorying equipment at the Level3 staging facility in Broomfield. Level3 will have received colocation orders from Internet2 and should have delivered a substantial amount of the Phase 2 optical build colocation. Internet2 anticipates that the initial Phase 2 optical installations will begin, with completion occurring the following quarter. IP Network Implementation Internet2 will light its first 100GigE IP backbone links in a production fashion and begin to transition traffic over to the new backbone links. Internet2 will also turn down the prior 10G backbone links. The TR-CPS network will continue to utilize the upgraded router equipment to obtain further commercial peerings. Internet2 will have installed a new IP router core node in Cleveland and integrated it into the network. | University Corporation For Advanced Internet Development | No additional challenges or issues have been faced during this past quarter in achieving planned progress against project milestones. We do not anticipate any problems or roadblocks that may delay achieving milestone projections in the next quarter. | No challenges or issues are anticipated during the next quarter that may impact planned progress against project milestones.
NT10BIX5570075 | 2011 | Q3 | Q3 - 2011 | Dark Fiber and Optical Network Implementation Internet2 continued to make progress on all phases of the BTOP project. The Phase 1 Optical equipment that was completed on time last quarter has been commissioned as of September 30th, 2011 and is beginning to come into service. Internet2 placed orders for all optical equipment needed for implementation of Phase 2 of the optical build. Roughly half of that equipment has arrived as of September 30th, 2011-with the remaining balance set to arrive by the end of October in the next quarter. Approximately 80% of the Phase 2 colocation has been ordered for delivery during the next quarter. Internet2 is beginning installation of the Phase 2 Optical equipment the week of September 26th, 2011. Most of the Phase 2 installation will occur during the next quarter. Internet2 has received fiber test results for Los Angeles to Salt Lake City, Memphis to Nashville, Houston to Dallas, and the Houston Metro loop. IP Network Implementation Internet2 put its first 100Gbps link between New York and Washington into service on September 30th, 2011. The prior 10Gbps backbone links were left in service, but should be removed in the following quarter. Internet2 opted to delay the installation of the Cleveland node until a later date in order to utilize the optical transceivers elsewhere in the network. Internet2 plans to put the Cleveland router in service in Year 2, Quarter 3. The TR-CPS network will continue to utilize the upgraded router equipment | 0 | 4891 | 0 | 0 | 0 | 0 | 0 | 24 | NA | NA | Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new build to date and no existing infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new build to date and no existing infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of network in the Northern Tier are slated to be upgraded. As part of the 4,891 miles of new IRU fiber, we have secured 24 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation spacer July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new build to date and no existing infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of network in the Northern Tier are slated to be upgraded. As part of the 4,891 miles of new IRU fiber, we have secured 24 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation space. | 21 | 0 | 0 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning | Two 5 gigabit network connects $32,500/mo3 | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 1 | 20 | 0 | 3 | During the current period, Internet2 worked with the Board of Directors for the Mississippi Institutions of Higher Learning to complete an agreement for two 10 gigabit network connections. This represents a significant achievement to bring the national research and education high capacity network capacity to Mississippi for the first time. | NA | NA | 5 subscribers of two 5 gigabit network connections 7 subscribers of one 10 gigabit network connections 9 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Dark Fiber and Optical Network Implementation Internet2 expects to receive the all remaining optical equipment shipments for Phase 2 at its staging facility in Broomfield, CO. After inventory and staging has completed, Internet2 expects to have the following segments installed and commissioned: Salt Lake City to Seattle, New York City to Cleveland. The path between Kansas City and Houston should be installed, but may not be completely commissioned. The remainder of the Phase 2 equipment will be deployed in Year 2, Quarter 3. IP Network Implementation Internet2 expects to enable the Upgraded 100Gbps IP backbone between Washington DC and Chicago in November. Key Indicators a. New Network Miles Upgraded: Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new build to date and no existing infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of network in the Northern Tier are slated to be upgraded. b. New Network Miles Leased: 4891 c. Number of signed agreements with broadband wholesalers or last mile providers: 21 | University Corporation For Advanced Internet Development | We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | We do not anticipate any challenges or issues next quarter that may impact planned progress against the milestones listed above.
NT10BIX5570075 | 2011 | Q4 | Q4 - 2011 | Internet2 continued to make progress on the program commitments for this sixth quarter of BTOP funding and continued work ahead of schedule on third year optical deployments during the last quarter of calendar year 2011. Internet2 has completed orders for all optical equipment needed for implementation of Phase 2 of the optical build. All of the Phase 2 optical equipment that was ordered in earlier quarters during 2011 arrived at the staging facility in Broomfield, CO. Approximately 40% of that equipment has now also been installed in the field and is undergoing test and turnup at the end of this quarter. This includes the segments from New York to Cleveland and Salt Lake City to Seattle. Internet2 provided nine individual 100Gbps wavelengths to connect community anchor institutions, including national labs, university campuses, and global research exchange points with an advanced networking conference in Seattle during October and November. One of the nine enabled wavelengths included the IP backbone circuit between Washington DC and Chicago. Internet2 has received and accepted fiber test results for the following segments: 1. Atlanta to Washington DC 2. Cleveland to Buffalo 3. Buffalo to Albany 4. Baton Rouge to Tallahassee 5. Tallahassee to Jacksonville 6. El Paso to Denver 7. Los Angeles to Phoenix 8. Phoenix to El Paso 9. Houston to Jackson This completes the delivery of the remaining primary fiber paths and makes them available to place in service with an optical system. | 0 | 7521 | 0 | 0 | 0 | 0 | 0 | 29 | NA | Internet2 initially expected completion to happen in substantive chunks. As the project progresses, we are making incremental progress toward the Phase 2 total mileage of 10,280. This increase over the baseline represents that incremental progress. | Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of existing network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | As part of the 7,521 miles of new IRU fiber, we have secured 29 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation space. | 21 | 0 | 0 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 1 | 20 | 0 | 3 | Mississippi Institutions of Higher Learning | We have 2 Letters of Intent that may result in 2 additional connections by Year 3, Quarter 1. | NA | 5 subscribers of two 5 gigabit network connections 7 subscribers of one 10 gigabit network connections 9 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Dark Fiber and Optical Network Implementation Internet2 expects to order and receive all Ciena optical equipment needed for the project's Phase 3 deployment. After inventory and staging has completed, Internet2 expects to have the following segments installed and commissioned: Kansas City - Houston, Atlanta - Houston, and Salt Lake City to Los Angeles. Internet2 also expects that the majority of Phase 3 colocation facilities will be ordered and portions of the Phase 3 build to have begun. IP Network Implementation Internet2 anticipates activation of a Chicago to Kansas City 100G in Year 2, Quarter 3. a. New network miles leased: 10,280 miles b. Number of signed agreements with middle mile carriers: 21 | University Corporation For Advanced Internet Development | While closing out bill payments and accounting to the highest standard still creates the perception of delay against the baseline. We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | We do not anticipate any challenges or issues next quarter that may impact planned progress against the milestones listed above.
NT10BIX5570075 | 2012 | Q1 | Q1 - 2012 | Internet2 placed an order for all remaining Ciena Phase 3 optical equipment in late January. Approximately 50% of that equipment had been received at Internet2's staging facility by the end of the quarter. 80% of the Phase 3 colocation site orders were placed and were in the process of being provisioned by Internet2's colocation provider at the end of the quarter. Internet2 successfully commissioned the entire Phase 2 path on the following segments: Kansas City - Houston Atlanta - Houston Salt Lake City - Los Angeles | 0 | 10384 | 0 | 0 | 0 | 0 | 0 | 37 | NA | Internet2 has accelerated its implementation timeline and expects to remain ahead of the baseline for the remainder of the project. | Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of existing network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | As part of the 10,384 miles of new IRU fiber, we have secured 37 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation space. | 21 | 0 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 1 | 20 | 0 | 3 | Internet2 met the baseline for this metric. | Internet2 has 2 Letters of Intent that may result in 2 additional connections by Year 3, Quarter 1. | NA | 6 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects to receive the remaining Phase 3 Ciena equipment order and place an order for the equipment to light the Northern Tier Network segment. Internet2 expects the majority of Phase 3 optical sites to be completed, including: Houston to El Paso El Paso to Los Angeles El Paso to Albuquerque Houston to Jackson Jackson to Nashville Internet2 also expects to have placed an order for the majority of remaining Layer2/Layer3 equipment and begun planning to install that equipment in the following quarter. New Network Miles Leased: 13,904 Number of signed agreements with middle mile carriers: 21 | University Corporation For Advanced Internet Development | We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | We do not anticipate any challenges or issues next quarter that may impact planned progress against the milestones listed above.
NT10BIX5570075 | 2012 | Q2 | Q2 - 2012 | Internet2 made considerable progress toward completion of the optical network. The following segments are commissioned: Houston to El Paso El Paso to Los Angeles El Paso to Albuquerque Houston to Jackson Jackson to Nashville The only section of the newly acquired dark fiber footprint to remain lit is the west coast fiber from Los Angeles to Seattle. Internet2 also placed orders for and received the majority of its Layer2/3 equipment and is in the process of staging it for install next quarter. | 0 | 13904 | 0 | 0 | 0 | 0 | 0 | 49 | NA | Internet2 has accelerated its implementation timeline and expects to remain ahead of the baseline for the remainder of the project. | Internet2's network project for July, 2011 through June, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between July, 2012 and June, 2013, 2527 miles of existing network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | As part of the 13,904 miles of new IRU fiber, we have secured 49 interconnection points. To be consistent with our approach for fiber deployment, we accept these as we accept colocation space. | 21 | 0 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 1 | 20 | 0 | 3 | Internet2 expects to report 2 additional connections for Y3Q4. | Internet2 does not expect this number to change. Services have been upgraded to existing customers with agreements. | NA | 6 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects to complete the entire new dark fiber optronics installation with the completion of the west coast fiber in late August. This will bring the Ciena network installation to a close and allow Internet2 to focus on the Layer 2/3 equipment deployment. Internet2 expects to have installed between 10 and 15 Layer2/3 nodes around the country by the end of Q2 2012. Internet2 will be be submitting initial documents to the NTIA to allow a new approach to completing the Northern Tier Network Consortium (NTCT) to begin installation. Following NTIA approval of the approach, Internet2 expects to complete the NTNC portion of the project within the scheduled phase of the project and within budget. a. New Network Miles Leased: 15,307 b. Number of Signed Agreements with Middle Mile Carriers: 23 | University Corporation For Advanced Internet Development | We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | We do not anticipate any challenges or issues next quarter that may impact planned progress against the milestones listed above.
NT10BIX5570075 | 2012 | Q3 | Q3 - 2012 | Internet2 completed the optical network build for the portions of the project built atop newly acquired dark fiber from Level3 Communications and Zayo Group. This completes the build of the common optical infrastructure and places the 100G capable optical system in full production. Internet2 also completed installation of 14 Layer2/3 nodes in August and September. This network, brought online on September 30th, provides the distributed access described in the application. Internet2 continued to work with the NTIA on an alternative approach to providing the Northern Tier Networking Consortium (NTNC) portion of the footprint. Following NTIA approval of the approach, Internet2 expects to complete the NTNC portion of the project within the scheduled phase of the project and within budget. | 0 | 15717 | 0 | 0 | 0 | 0 | 0 | 52 | NA | Internet2 originally didn't account for the 1,400 miles of fiber on the west coast from CENIC. At the time, the expectation was that the fiber transfer wouldn't be handled as a lease. We ultimately did structure the arrangement as a lease, so the updated number reflects those additional miles. In addition, the fiber route that was initially planned for Nashville to Dallas was altered to a Nashville to Houston path, adding additional miles. The remainder is a true-up of the fiber distances initially provided by Level3. | Internet2's network project for July, 2011 through October, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between October, 2012 and June, 2013, 2527 miles of existing network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | Internet2 met the baseline for this metric. | 22 | 2 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning; MissION (Mississippi Optical Network); MARIA (Mid-Atlantic Research Infrastructure Alliance) | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 2 | 20 | 0 | 3 | This number includes: Mississippi Institutions of Higher Learning and MARIA (Mid-Atlantic Research Infrastructure Alliance). | Internet2 expects to report 2 additional connection by Y3Q2. | NA | 7 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects to continue deployment and implementation of it's 100G Layer2/Layer3 infrastructure throughout Q4 2012. This will likely include an additional 3-5 nodes to augment the existing footprint. In addition, Internet2 expects to fully migrate all of its pre-existing 10G customers off the legacy Internet2 optical system and onto the newly installed Ciena-based optical system that was completed in Q3 2012. Assuming approval from the NTIA, Internet2 expects to have portions of the Northern Tier Networking Consortium portion of the BTOP footprint underway for completion in 2013. a. New Network Miles Leased:15,717 b. Number of Signed Agreements with Middle Mile Carriers: 24 | University Corporation For Advanced Internet Development | Internet2 is waiting on an approval from the NTIA for a route change request initially submitted on July 26, 2012. | In order to achieve planned progress against the remaining project milestones listed above, Internet2 needs approval from the NTIA for a route change request submitted on July 26, 2012.
NT10BIX5570075 | 2012 | Q4 | Q4 - 2012 | Internet2 fully transitioned all of its pre-existing 10G services off its legacy optical system and onto the BTOP-funded Ciena infrastructure in Q4 2012. In addition, Internet2 placed colocation orders for two additional Layer2/Layer3 locations to be installed in Q1 2013 that had been included in the approved application. Internet2 also began logistics planning and pre-deployment activity for the replacement of the legacy Layer3 equipment in Q1 2013. Internet2 received indications of preliminary approval of the Northern Tier portion of the BTOP footprint and began pre-planning discussions with Zayo communications. | 0 | 14314 | 0 | 0 | 0 | 0 | 0 | 52 | NA | The fiber route that was initially planned for Nashville to Dallas was altered to a Nashville to Houston path that passed through Jackson, Mississippi, adding 187 miles. The remainder is a true-up of the straight line fiber distances initially provided by Level3 as compared to tested results, which include maintenance slack coiled in a manhole along the path. A retroactive route modification document was submitted on 12/20/2012 for this route change. | Internet2's network project for July, 2011 through October, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between October, 2012 and June, 2013, 2463 miles of existing network in the Northern Tier are slated to be upgraded. | NA | NA | NA | NA | Internet2 met the baseline for this metric. | 22 | 0 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning; MissION (Mississippi Optical Network); MARIA (Mid-Atlantic Research Infrastructure Alliance) | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 2 | 20 | 0 | 3 | This number includes: Mississippi Institutions of Higher Learning and MARIA (Mid-Atlantic Research Infrastructure Alliance). | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; MissION (Mississippi Optical Network) | NA | 7 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects to deploy two more Layer2/Layer3 aggregation nodes in Q1 2013. In addition, Internet2 plans to have completed logistics planning and pre-deployment tasks for an additional seven Layer2/Layer3 aggregation nodes to be deployed in Q2 2013. Internet2 also expects to replace the majority of its Layer3 routing equipment by the end of March. Assuming NTIA approval of the route change along the Northern Tier, Internet2 and Zayo expect to have a large portion of the optical build between Seattle and Chicago complete. a. New Network Miles Leased:14,314 b. Number of Signed Agreements with Middle Mile Carriers: 22 | University Corporation For Advanced Internet Development | Internet2 has been continuing to work on a route change to implement the Northern Tier portion of the network and has been collaborating with the NTIA since July to determine the proper procedure to allow the work to go forward. | Internet2 has been continuing to work on a route change to implement the Northern Tier portion of the network and has been collaborating with the NTIA since July to determine the proper procedure to allow the work to go forward. In order to achieve planned progress against the remaining project milestones listed above, Internet2 needs approval of all documents submitted to date in regards to the route change.
NT10BIX5570075 | 2013 | Q1 | Q1 - 2013 | Internet2 deployed and commissioned three more Layer2/Layer3 aggregation nodes. In addition, Internet2 began pre-deployment activities for a further five L2/L3 node installs to occur in April and May. Internet2 also upgraded its Layer3 routing equipment in seven of ten cities by the end of March. The remaining three upgrades will occur in April and early May. Zayo made significant progress in completion of the Northern Tier build between Chicago and Seattle and is expected to complete handover in May. AL2S Deployed: 17 AL2S Commissioned: 17 AL2S Overall Total: 22 AL3S Deployed: 10 AL3S Commissioned: 10 AL3S Overall Total: 10 | 0 | 14314 | 0 | 0 | 0 | 0 | 0 | 52 | NA | A route change was submitted to and is pending approval by the NTIA to account for the difference with the baseline. | Internet2's network project for July, 2011 through October, 2012 does not include any upgraded mileage. The build has been based on new activation of existing IRUs and no operating infrastructure has been upgraded. Between 1Q2013 and June, 2013, 2463 miles of existing optical fiber network in the Northern Tier are slated to be upgraded by installing new BTOP equipment. | NA | NA | NA | NA | Internet2 met the baseline for this metric. | 22 | 1 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX;GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MARIA (Mid-Atlantic Research Infrastructure Alliance); MAX (Mid-Atlantic Crossroads); MCNC/C-Light; MissiON (Mississippi Optical Network); MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; OARnet; Oregon Gigapop; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 2 | 20 | 0 | 3 | This number includes: Mississippi Institutions of Higher Learning and MARIA (Mid-Atlantic Research Infrastructure Alliance). | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; MissION (Mississippi Optical Network) | NA | 7 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects to install the remaining five Layer2/Layer3 aggregation nodes in the April/May timeframe. In addition, Internet2 expects the three remaining Layer3 routers to be fully upgraded by early May. Internet2 also expects completion of the Zayo-partnered northern tier build in the late April timeframe. This will conclude all project deliverables before the project close at the end of June. a. New Network Miles Leased: 14,314 b. Number of Signed Agreements with Middle Mile Carriers: 24 c. Number of Network Miles Upgraded: 2463 d. Meet LM/Wholesale Provider Agreements?: Yes | University Corporation For Advanced Internet Development | We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | We do not anticipate any challenges or issues next quarter that may impact planned progress against the milestones listed above.
NT10BIX5570075 | 2013 | Q2 | Q2 - 2013 | Internet2 completed the upgrade of the remaining Layer3 routers in early May. In addition, Internet2 installed five additional Layer2/Layer3 aggregation switches. The Northern Tier path between Chicago and Seattle was completed in late June. This concludes all project deliverables. | 0 | 14314 | 3866 | 0 | 0 | 0 | 0 | 63 | NA | A route change was approved by the NTIA to account for the difference with the baseline. | A project modification document was approved by the NTIA to account for the 3,866 miles of existing optical fiber network in the Northern Tier that were upgraded by installing new BTOP equipment. | NA | NA | NA | NA | The NTIA approved one additional point of interconnection as it was integral to the route change documentation previously submitted. | 24 | 0 | 4 | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX;GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MARIA (Mid-Atlantic Research Infrastructure Alliance); MAX (Mid-Atlantic Crossroads); MCNC/C-Light; MissiON (Mississippi Optical Network); MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; OARnet; Oregon Gigapop; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; Mississippi Institutions of Higher Learning; Arizona | Two 5 gigabit network connects $32,500/mo One 10 gigabit network connection $41,600/mo Two 10 gigabit network connections $45,500/mo | The Indiana University Global Research Network Operations Center, a contractor, operates the network on behalf of Internet2. Their contact information is: Dave Jent Associate Vice President for Networks Global Research Network Operations Center 535 W. Michigan Street Indianapolis, IN 46202, USA Phone: (317) 274-7788 Email: globalnoc@iu.edu | 3 | 21 | 0 | 3 | This number includes: Mississippi Institutions of Higher Learning; MARIA (Mid-Atlantic Research Infrastructure Alliance); Arizona | 3ROX/Drexel; CENIC; CIC OmniPoP; FLR/SoX; GPN (Great Plains Network); Indiana GigaPoP; KyRON; LEARN (Lonestar Education and Research Network); LONI (Louisiana Optical Network Initiative); MAGPI; MAX (Mid-Atlantic Crossroads); MCNC/C-Light; OARnet; MREN (Metropolitan Research and Education Network); NOX (The Northern Crossroads); NYSERNet, Inc.; Oregon GigaPoP; Pacific Northwest GigaPoP; University of Memphis; Utah/Montana; MissION (Mississippi Optical Network) | NA | 8 subscribers of two 5 gigabit network connections 5 subscribers of one 10 gigabit network connections 10 subscribers of two 10 gigabit network connections | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The project offers native IPv6 and IP multicast in addition to the normal IPv4 connectivity. In addition the project is adding support for Software Defined Networking (SDN) and OpenFlow. | FALSE | NA | Internet2 expects finalize all expenditures next quarter thereby completing all project milestones next quarter. | University Corporation For Advanced Internet Development | We did not face any additional challenges or issues this past quarter in achieving planned progress against project milestones. We do not expect any problems or roadblocks that may delay achieving milestone projections in the next quarter. | NA
NT10BIX5570076 | 2010 | Q4 | Q4 - 2010 | Draft Environmental Assessment filed with NTIA December 2010; RFP issued for Professional Services Contract; initial pole attachment applications filed; continued network design to select optimal routes for CAI Interconnection and contacted CAI's to discuss service options and confirm commitments to purchase services. Obtained a Certificate of Public Convenience and Need (CPCN) to provide telecommunications services in Vermont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | The project is not yet providing services. | Sovernet Fiber Corp, 5 Canal Street, Bellows Falls, VT 05101 Sub recipient Sovernet will operate the entire network when completed | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Execute sub grant agreement with sub grantee; enter into service agreement with State of VT and other CAI's; complete EA; complete consultations with Environmental Agencies; revise Draft EA to Final; continue design of fiber routing, electronic locations, architecture and configuration; applications for pole attachment to be filed; applications for state/local permits to be filed; begin make ready of pole routes. | Vermont Telecommunications Authority | Project behind baseline plan due to ongoing issue with project overlap; in Q4 continued discussion of project overlap with NTIA and other BTOP awardee. Currently waiting for overlap SAC to be lifted, expect it by 01/28/2011. Once we receive our FONSI from NTIA, we anticipate getting back on schedule with the project as follows: Network Design - Work with consulting engineers to accelerate the schedule. Engineers haven't yet been selected. Construction Permits and Other Approvals - Accelerate the schedule by working with the selected contractors to generate pole attachment and other required applications. | Pole owning utilities may need to increase staff or contractor resources to support necessary pace of pole surveys and make ready. The Vermont Department of Public Service (regulator of telecom and electric utilities in Vermont) has scheduled a pole attachment coordination group, including Sovernet Fiber Corporation (SFC), Vermont's largest electric utilities, incumbent local exchange telephone company and ARRA grantees to discuss the scope of projects, confirm pole owners and attachees with information regarding the scope of projects, coordinate the exchange of information and identify any carriers or constraints upon the ability of all parties to complete the make-ready necessary to accommodate SFC's aerial cables within the timeline required by the BTOP grant to the Vermont FiberConnect project. SFC has communicated its concerns to the principal pole owners. To date, all pole owners have indicated they have the resources to meet SFC's desired timeline, provided they have information regarding the scope of the entire project. The coordination group will meet February 17 to discuss methods to share information.
NT10BIX5570076 | 2011 | Q1 | Q1 - 2011 | Reviewed proposals received in response to Request For Proposal (RFP) for Professional Services Contract; Filed pole attachment applications; Participated in state-organized pole attachment coordination group; Entered conduit and pole license agreements; Obtained Environmental Assessment (EA) signoff from several agencies; Continued negotiations with Vermont Historic Preservation Office (VT SHPO) regarding programmatic agreement; Sub recipient agreement was signed; Sub recipient hired Project Manager & Project Engineer; Sub recipient hired Project Accountant to start in April; Continued network design to select optimal routes for Community Anchor Institution (CAI) interconnection; Continued to contact CAI's to discuss service options & confirm commitments to purchase services; Submitted proposals to significant groups of CAI's; Entered into service agreement with multi-location CAI project partner; Attended bi-monthly checkpoint conference calls with NTIA; Attended webinars on sub recipient monitoring, EA and Davis-Bacon Wage; preparation and submission of reports. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | The project is not yet providing services. | Sovernet Fiber Corp, 5 Canal Street, Bellows Falls, VT 05101 Sub recipient Sovernet will operate the entire network when completed | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Obtain Finding of No Significant Impact (FONSI) and lifting of Special Award Condition #10 (Project-specific Vermont Overlap); Enter contract with vendor for Engineering professional services; Authorize utility pole owners to begin make-ready work; Continue make-ready surveys and detailed routing; Settle on electronic locations, continue work on network architecture and configuration; Issue Request for Proposal (RFP) for cable, begin preparing RFP's for equipment and construction; implement fixed asset accounting module for project; Apply for State and Local land use permits to extent required. Continue ongoing discussions with CAIâ€™s; work with Regional Planning Commissions; continue discussions with last mile providers; publish first quarterly newsletter. | Vermont Telecommunications Authority | Award conditions prohibit start of build until Environmental Assessment (EA) is complete and Special Award Condition (SAC) 10 has been lifted. Overlap issue and pending completion of the EA have caused the project to be behind the baseline plan. Will proceed with design , make-ready and construction work once the the FONSI has been issued. Once the FONSI is issued, we estimate that at the end of the first quarter of 2012 we will reach the original target spend for the other milestones as the make ready begins on poles, network design is finalized, and the project moves into the construction phase. This level of activity will enable the project to meet the 67% time line after 8 quarters which was part of the original target spend rate. | Pole owning utilities may need to increase staff or contractor resources to support necessary pace of pole surveys and make ready. Resolution of EA/FONSI will affect timing of spending.
NT10BIX5570076 | 2011 | Q2 | Q2 - 2011 | Obtained a Finding of No Significant Impact and entered into Programmatic Agreement with Vermont SHPO and NTIA. Signed Master Services Agreement with Professional Services firm. Negotiated Statement of Work for Outside Plant Engineering. Statement of Work for Electronics is in negotiation. Statement of Work's are being prepared for RFP's to be released next quarter. Have designed surveryed 47% of poles, applied for and jointly surveyed 37% with pole owners, and requested make-ready work on 18%. Divided route into 22 zones to make project management easier. Initiated colocation conduit verification requests for four sites. Applied for colocation for three sites. Sub recipient hired a Project Accountant, Business Project Manager, and a second Project Engineer. Engaged services of law firm relative to obtaining any required land use permits. Continued network design to select electronics locations and to select optimal routes for Community Anchor Institutions (CAI) interconnection. Published first quarterly newsletter. Contacted representatives of all 340 CAIâ€™s. Interest has generally been positive, with over 80 CAI locations currently under contract. A substantial share of schools and libraries, while expressing interest in purchasing services, will still solicit proposals through competitive solicitation in order to assure their eligibility for e-rate support. Issued RFP for utilization of discounted GigE transport services by last-mile providers that will prov | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction delayed due to delay in obtaining Finding of No Significant Impact. | N/A | N/A | N/A | Construction delayed due to delay in obtaining Finding of No Significant Impact. | N/A | N/A | N/A | 0 | 0 | 0 | N/A | The project is not yet providing servicesg services. | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls VT 05101 Subrecipient Sovernet will operate the entire network when completed | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In the coming quarter we expect to develop plans and specifications and issue Request For Question's and Request For Proposals's for (1) fiber optic cable, (2) outside plant construction covering 13% of our route and (3) dense wavelength division multiplexing network equipment. We will continue surveying the poles on our route and request make-ready work from pole owners. We expect to award a contract for fiber optic cable. We will also engage state and local government agencies on the permitting process. Our Baseline Performance Progress Report spending for the Next Quarter was anticipated to be $4,709,000. Our current projection for the Next Quarter is $2,609,000. The projection is lower principally because the start of construction was delayed until the Finding of No Significant Impact was release and Special Award condition 10 was lifted. | Vermont Telecommunications Authority | Overall progress on the project at the end of Q1-2011 trailed the original baseline target due to several related factors. First, the overlap issue (Special Award Condition #10) had to be resolved before the network route that would be reviewed in the Environmental Assessment could be determined. Although the NTIA issued a verbal description of its resolution of the overlap on 11/9/2010, it did not give the recipient formal notice that the project would proceed without modification until 4/29/2011 â€“ 10 Â½ months after award of the grant. Second, NTIA issued its Finding of No Significant Impact for the project roughly 5 months later than originally projected (5/10/2011 vs 1/02/2011), due primarily to required consultations with numerous state and federal agencies and protracted negotiation of a Programmatic Agreement among NTIA, the Vermont Division of Historic Preservation and the Vermont Telecommunications Authority. Third, the uncertain resolution of the overlap issue cast substantial uncertainty over the financial sustainability of the project. Accordingly, the sub recipient deferred engaging an engineering services contractor and starting detailed project engineering until NTIAâ€™s resolution of the overlap issue consistent with its verbal guidance was reasonably certain. Once NTIA formally notified the recipient that the project could proceed without modification, the sub recipient moved ahead to enter a contract with the engineering contractor to pre | Timely completion of a fiber optic cable plan, Request For Questions and Request For Proposals processes so (a) contract(s) can be awarded for fiber optic cable. Confirmation of utility easements for poles outside of public rights of way.
NT10BIX5570076 | 2011 | Q3 | Q3 - 2011 | Electronics: SFC Fiber Corp (SFC) signed a Statement of Work for Electronics with the engineering firm previously engaged. SFC issued and received responses to an RFQ for packet optical equipment. Five vendors were asked to make proposals and attended technical sessions in September. Cable: Based on RFQ responses, SFC selected two vendors to provide fiber optic cable. Contracts for delivery of fiber cables for the entire project are being negotiated. Route Selection and Make-Ready: Route design and joint pole surveys continued. SFC has design surveyed 53% of poles on the network route, applied for attachments to 53%, and requested make-ready work on 42%. Pole owners continue to perform make-ready work. Additional pole attachment agreements were signed. Historic Preservation: Selected a historic preservation and archaeological firm to survey and document cultural artifacts, consistent with the terms of the Programmatic Agreement. Outside Plant Construction: SFC issued an RFQ for outside plant construction of 90+ miles of plant, and subsequently sent RFPâ€™s to qualified contractors. Six vendors bid. A contract for construction of this outside plant was entered shortly a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline plan was to have 250 route miles deployed by end of the quarter. Tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issued. In addition, Tropical Storm Irene damage to basic infrastructure, in particular telecom and power company poles, caused those companies to redeploy personnel on repair and maintenance duty. The redeployment lasted several weeks post-storm and had a direct negative impact on this project's anticipated progress and performance. | N/A | N/A | N/A | Baseline plan was to have 250 route miles deployed by end of the quarter. However, tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issued -- roughly 5 months later than the dates established by NTIA in the award. Construction will start in December. We anticipate having completed 250 miles by May 2012. | N/A | N/A | Tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issuedn were delayed until Special Award Condition 10 was lifted and FONSI issued. | 0 | 4 | 0 | None | The project is not yet providing services.3 | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the entire network when completed. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) An outside plant construction contract valued at $1.7 million was entered early in this quarter for over 90 route miles. Construction under this contract will begin during the quarter. 2) Contracts with aggregate value of approximately $5.1 million for purchase of the bulk fiber-optic necessary for completion of the project will be executed during the quarter. Initial purchase orders will be submitted during the quarter. 3) Detailed route design covering over 200 route miles will begin and be substantially completed during the quarter. 4) Make-ready surveys will be applied for and conducted for an additional 5500 poles. 5) License agreements for rail crossings will be negotiated. Applications for rail crossings for an additional 200 route miles will be submitted. 6) Select primary packet electronics vendor; release RFPs for routing and Operations Support System equipment. 7) The first batch of collocation sites will be released to SFC by the location owner this quarter, matching the outside plant build schedule. Most of the remaining collocations will be applied for early in this quarter, so that release dates line up with planned construction. 8) A lease for a secure material storage yard will be negotiated and entered. 9) Design will be completed and construction (costing approximately $125,000) will begin on fiber service entry to a building utilized by an anchor institution as a main network hub. | Vermont Telecommunications Authority | Special Award Condition 9 (Environmental Assessment) precluded expenditure of funds for purposes other than management, administration and limited procurement until a Finding of No Significant Impact ("FONSI") was obtained. In addition, NTIA did not fully resolve overlap between the Vermont FiberConnect project and another BTOP project during the application review phase, and applied Special Award Condition 10 to the VFC project, which required modification of one or both of the projects to resolve overlapping elements of the projects. Because of the uncertain resolution of the overlap, project activities that were not otherwise restricted by Special Award Condition 9 were slowed or suspended pending NTIA's decision about how to resolve the overlap, and in particular how the VFC project would be modified. The deferral of activities created variances relative to initial baseline spending projections in numerous categories, including: land, structures, rights-of-way, appraisals, project inspection fees, make-ready, construction and equipment procurement. The NTIA issued a FONSI and lifted Special Award Condition 10 in May 2011, five months later than assumed in the initial baseline plan. Detailed route surveys, make-ready applications, and permitting have been proceeding at an accelerated pace to bring the project back close to the initial schedule. Work during the quarter to secure permits, define equipment and outside plant construction specifications, develop contract | 1) Cable vendors have stated the first deliveries of fiber will not arrive until April, 2012. To make progress in the interim, outside plant construction will focus initially on install of conduit and 90 miles of aerial construction with attachment of fiber cable to follow when available. 2) Execution of railroad crossing license agreements and subsequent acquisition of permits for railroad crossings is in progress. Railroads have advised licensees that lead times for negotiation of Master License Agreements are typically five to seven months. Efforts to accelerate the usual completion time of these items is currently underway and will continue until such time as these items are successfully completed or until technical assistance from BTOP staff may prove useful.
NT10BIX5570076 | 2011 | Q4 | Q4 - 2011 | 1) Outside plant construction began this quarter; 22 miles of strand were placed by 12/31/11. 2) Contracts with aggregate value of approximately $5.1 million for purchase of fiber-optic cable were executed and initial purchase orders were submitted. 3) Detailed route design covering over 200 additional route miles began and were substantially completed. 4) Make-ready surveys were applied for an additional 3,500 poles, and conducted for 4,600 poles. 5) Master license agreements for rail crossings were not completed, but permission was obtained to proceed with work after permits were granted under the condition that MLA's would be executed later. Applications for rail crossings for an additional 200 route miles were submitted. 6) RFP's for packet optical network equipment and routers were issued. 7) SFC applied during the quarter for collocation permits for 2 additional collocation sites owned by third parties, bringing the total to date to 13. 8) A lease was executed on a secure material storage yard. 9) Design was completed and construction is pending easement execution on fiber service entry to a building utilized by an anchor institution as a main network hub. 10) An outside plant construction contract for 62 miles of route was awarded with a value of $1.21M. 11) A dedicated Engineering Manager was assigned to the project during the quarter to coordinate and oversee all construction activities and personnel. 12) SFC reached agreements with several third party pole attachees allowing SFC fiber installation crews to perform the necessary make-ready work on behalf of these third parties. This has effectively accelerated the schedule by allowing one contractor to perform all work required on the vast majority of poles. 13) Participated in bi-weekly calls with NTIA. 14) Preparation and submission of reports. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline plan was to have 400 route miles deployed by end of the quarter. Tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issued. In addition, redeployment of utility crews to areas of Vermont and southern New England to repair tropical storm damage extended through the quarter. | Cable on the route along which SFC intends to utilize is under construction. | N/A | N/A | Baseline plan was to have 417 route miles deployed by end of the quarter. Tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issued. In addition, redeployment of utility crews to areas of Vermont and southern New England to repair tropical storm damage extended through the quarter. | N/A | N/A | Tasks antecedent to construction were delayed until Special Award Condition 10 was lifted and FONSI issued. Interconnection points will be activated as construction is completed along related network segments. | 1 | 4 | 12 | Educational Networks of America, Inc. | The project is not yet providing services. | Sovernet Fiber Corp. (SFC), 5 Canal Street, Bellows Falls, VT 05101 Subrecipient SFC will own and operate the network when completed. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | N/A | Project is not presently providing service. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) The majority of route engineering is scheduled to be complete this quarter, which will allow for issuance of six separate outside plant construction bid packages covering the majority of the remaining core backbone routes, as well as a large portion of lateral routes. Bids on four of the six packages will be due during the quarter. 2) Four additional project staff members will be dedicated to the project to facilitate engineering and construction goals as well as design of service entrances to CAI's. 3) Make-ready surveys will be requested for an additional 2,300 utility poles during the quarter, bringing the total surveyed to roughly 81% of those required for completion of the project. 4) Assuming AAR's for route revisions are timely approved, construction will be completed by end of quarter on 92 route miles, with strand attached on another 20 to 50 route miles. 5) Primary vendors for packet optical equipment and routers will be selected during the quarter. 6) Design and fit-up of collocation facilities will continue. 7) SFC anticipates obtaining additional CAI service commitments, including from libraries and K-12 schools that will close their e-rate solicitation windows during the quarter. | Vermont Telecommunications Authority | Concerns previously expressed regarding delays in fiber-optic cable deliveries were largely resolved by execution of a contract for 1.2 million feet of cable on a schedule that will enable on-time completion. Railroad owners have in general been willing to accommodate SFC's requests for entry of master license agreements. However, the pace of make-ready by pole owners slowed during the quarter as a result of the diversion of work crews and pole inventory to repairs in Vermont necessitated by Tropical Storm Irene (which occurred August 28th) as well as a subsequent nor'easter that extensively damaged utility infrastructure in southern New England. Make-ready work slowed or stopped for several weeks while the utility crews were diverted to the affected areas to undertake emergency service restoration, repairs and reconstruction. Utilities are gradually returning to a pre-storm level of work on make-ready requested by SFC. In addition, SFC obtained consent of the primary cable companies, which comprise the majority of third party pole attachments in the project area, to undertake make-ready on CATV plant using approved contractors. | As a result of detailed route surveys conducted after obtaining the NTIA grant, SFC has identified a number of minor route revisions that are necessitated by field conditions. SFC has requested NTIA approval for related Award Action Requests, and will need timely decisions from the NTIA in order to proceed with construction on schedule. SFC's right of way contractor has been contacting property owners after routes are finalized and before construction begins, and where necessary is requesting easements. While SFC expects most easements to be obtained uneventfully, there exists some risk that construction will be delayed on short network segments while easements are obtained or alternate routes are designed, permitted and constructed.
NT10BIX5570076 | 2012 | Q1 | Q1 - 2012 | 1) During the quarter, Sovernet Fiber Corp (SFC) purchased 1.4 million feet of fiber-optic cable, bringing receipts to date to 2.6 million feet, almost 500 miles. 2) Of the estimated number of poles the project encompasses, at end of quarter, SFC had design surveyed and applied for attachments to 78%, requested make-ready work on 68%, and received all licenses needed for 38%. 3) SFC's right of way contractor continued to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 4) SFC issued bid packages and signed an additional three contracts for outside plant construction. SFC has now contracted for construction of 270 route miles, and as of end of quarter was evaluating bids for a fifth bid package covering 275 route miles. 5) By end of quarter, roughly 37 miles of strand and 19 miles of cable were attached to poles. 6) At quarter end, SFC was negotiating a contract with a provider of packet optical equipment based on the results of an RFQ/RFP process. During the quarter, an RFP for Network Monitoring and Service Level Agreement Reporting software was issued and a contract entered, an RFP for fiber tracking software was issued, and RFQ as well as RFP for router equipment were issued. 7) SFC applied for collocation permits for 6 additional locations owned by third parties, bringing the total to date to 16. 8) An Award Action Request (AAR) was submitted and approved by NTIA for route revisions intended primarily to address differences in field conditions (e.g. presence or lack of existing utility poles along planned routes) identifed during detailed route surveys. The AAR increased the total network length by 54 miles. 9) VTA and SFC staff participated in bi-weekly calls wtih NTIA, and prepared and submitted various standard reports. | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | Outside Plant Construction is complete for 19 miles of network as of the end of quarter. The baseline plan was to have 450 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews in to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. | SFC is negotiating for procurement of the fiber rights it intends to use along this network segment. | N/A | N/A | Baseline plan was to have 450 route miles deployed by end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews in to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. | N/A | N/A | Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. Interconnection points will be activated as construction is completed along related network segments. | 1 | 4 | 12 | Educational Networks of America, Inc. | The project is not yet providing services. | Sovernet Fiber Corp. (SFC), 5 Canal Street, Bellows Falls, VT 05101 Subrecipient SFC will operate the entire network when completed. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | N/A | Project is not presently providing service. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Sovernet Fiber Corp (SFC) will purchase an additional million feet of fiber-optic cable. 2) SFC will finish design survey for 95% of the network, including most anchor institutions. 3) SFC estimates, by end of quarter, make-ready work will have been authorized for approximately 19,500 (83)% of poles required for the project, make-ready work will be complete and licenses issued for roughly 12,000 poles (51% of the project's route miles), though not entirely in contiguous segments. 3) SFC's right of way contractor will continue to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 4) During the quarter, SFC will execute contracts for the fifth bid package (270 miles), issue two bid packages for all remaining OSP construction, and enter a contract and start construction on one of those packages. 5) By end of quarter, roughly 200 miles of cable will be attached to poles or in conduit. 6) Contracts for packet optical and router equipment will be entered and purchase orders placed. Installation, tuning and testing of packet optical gear should begin in the quarter. 7) An AAR for community anchor institution changes will be drafted and possibly submitted during the quarter. | Vermont Telecommunications Authority | The overall volume and locations for which pole make-ready have been completed and poles released to SFC to attachments has constrained SFC's ability to construct outside plant. Utility plant damage in Vermont by Tropical Storm Irene as well as by severe weather elsewhere in New England during 2011 caused a diversion of pole stock and construction crews away from pole make-ready jobs for the project. Few poles had been fully licensed until late in 4Q2011. However, the number of licenses issued started to pick up in 1Q2012, with 6,000 to 7,000 poles released to SFC during the quarter. While that number represents roughly 39% of total network miles, many of the licenses are for non-contiguous runs, limiting SFC's ability to hang cable. Protracted coordination and contract negotiations with property owners over easements for building entrances contributed to a much lesser extent to delays in outside plant construction. | The overall volume and locations of pole attachment licenses issued by pole owners will continue to constrain outside plant construction, although with 39% of poles licensed at the start of the quarter and 51% anticipated by end of quarter, the quantity of contiguous segments of fully licensed poles will increase signficantly. In addition, with construction contracts issued for all or nearly all of the network by end of the quarter, SFC will be better positioned to start construction where and when licenses are released. As mentioned in previous PPR's, there exists some risk that construction will be delayed on short network segments while easements are obtained or alternate routes designed, permitted and constructed. However, SFC expects all such situations can be resolved through negotiations or work-arounds.
NT10BIX5570076 | 2012 | Q2 | Q2 - 2012 | 1) During the quarter, Sovernet Fiber Corp (SFC) purchased 1.2 million feet of fiber-optic cable, bringing receipts to date to 3.8 million feet, roughly 720 miles. 2) Of the estimated number of poles the project encompasses, at end of quarter, SFC had design surveyed and applied for attachments to 94%, requested make-ready work on 78%, and received pole licenses needed for 52%. 3) SFC's right of way contractor continued to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 4) SFC requested bids selected contractors for two additional outside plant construction packages. SFC has now selected contractors for construction of the entire network. 5) Roughly 101 miles of strand and 101 miles of cable were attached to poles during the quarter, bringing the totals at end of quarter to 138 and 118 miles respectively. 6) SFC entered a contract with a provider of packet optical equipment and placed an initial $2.4 million purchase order. As of June 30, proposals for fiber tracking software were under review, as were proposals for router equipment. 7) SFC submitted all remaining collocation applications; four additional locations were released to SFC during the quarter. 8) VTA and SFC staff hosted a site visit by NTIA and NOAA program staff, participated in bi-weekly calls with NTIA, and prepared and submitted various standard reports. | 118 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | Outside Plant Construction is complete for 118 miles of network as of the end of quarter. The baseline plan was to have 500 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews in to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Gaps in pole licenses issued by pole owners are also constraining SFC's ability to deploy new network miles. | During the quarter, SFC reached an agreement in principle for procurement of the fiber rights it intends to use along this 17 mile network segment. A final agreement should be reached in 3Q2012. | N/A | N/A | Baseline plan was to have 500 route miles deployed by end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews in to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Gaps in pole licenses issued by pole owners are also constraining SFC's ability to deploy new network miles. SFC nonetheless installed 101 miles of fiber during the quarter. | N/A | N/A | Interconnection points will be activated as construction is completed along related network segments. | 1 | 4 | 12 | Educational Networks of America, Inc. | The project is not yet providing services. | Sovernet Fiber Corp. (SFC), 5 Canal Street, Bellows Falls, VT 05101 Subrecipient SFC will operate the entire network when completed. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | N/A | Project is not presently providing service. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Sovernet Fiber Corp (SFC) will purchase substantially all remaining fiber-optic cable necessary for project completion. 2) Design survey for substantially all of the network, including most anchor institutions, will be completed by end of the quarter. 3) SFC estimates, by end of quarter, make-ready work will have been authorized for approximately 20,800 (87%) of the poles required for the project. Make-ready work will be complete and licenses issued for an additional 4,000 poles -- bringing the total to roughly 16,500 poles (70% of the project's route miles), though not entirely in contiguous segments. 4) SFC's staff and right of way contractor will continue to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 5) Construction will start on all remaining outside plant work orders. 6) By end of quarter, roughly 300 miles of cable will be attached to poles or in conduit. 7) Entrance facilities for 230 CAI locations will be designed and released for construction, and 30 locations will be completed. 8) A contract for routers will be entered and purchase orders placed. 9) Packet optical gear installation, tuning and testing will begin during the quarter. Core network routes connecting ten network nodes will be lit during the quarter. 10) Service may be initiated during the quarter to select CAI locations, as facility completion allows. 11) An AAR for community anchor institution changes will be drafted and submitted during the quarter. | Vermont Telecommunications Authority | The overall volume and locations for which pole make-ready have been completed and poles released to SFC to attachments has constrained SFC's ability to construct outside plant. Utility plant damage in Vermont by Tropical Storm Irene as well as by severe weather elsewhere in New England during 2011 caused a diversion of pole stock and construction crews away from pole make-ready jobs for the project. Few poles had been fully licensed until late in 4Q2011. However, the number of licenses issued started to pick up in 1Q2012, with 12,300 released to SFC by end of 2Q2012. While that number represents over half of total network miles, many of the licenses are for non-contiguous runs, limiting SFC's ability to hang cable. Requests for make-ready work on an additional 6,000 poles were pending at the end of 2Q2012. SFC continues to conduct make-ready coordination calls each week with pole owners to resolve issues and prioritize pending make-ready requests. Protracted coordination and contract negotiations with property owners over easements for building entrances contributed to a much lesser extent to delays in outside plant construction. | The overall volume and locations of pole attachment licenses issued by pole owners will continue to constrain outside plant construction, although with 52% of poles licensed at the start of the quarter and 70% anticipated by end of quarter, the quantity of contiguous segments of fully licensed poles will increase signficantly. In addition, with construction contracts now in place for all network segments, SFC will be better positioned to start construction where and when licenses are released. There exists some risk that construction will be delayed on short network segments while easements and permits are obtained or alternate routes designed. However, SFC expects all such situations can be resolved through negotiations or work-arounds.
NT10BIX5570076 | 2012 | Q3 | Q3 - 2012 | 1. During the quarter, Sovernet Fiber Corp (SFC) purchased 1.0 million feet of fiber-optic cable, with 4.6 million feet purchased to date. 2. Of the estimated number of poles on our route, SFC has now design surveyed and applied for attachments to 95%; requested make-ready work on 89%. Pole owners continued make-ready work. As of September 30, SFC had obtained licenses for 63% of the estimated number of poles â€“ up from 52% as of June 30. By September 30, the proportion of poles for which either the electric utility or incumbent telephone company has issued make-ready licenses exceeding 70% of project total. 3. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing and municipal highway work permits. 4. During the quarter, all remaining bid packages were released to construction contractors. While outside plant construction has been constrained by the quantity and locations of make-ready work completed by pole owners, and to a lesser extent by need to secure permits, contractors have placed approximately 173 route miles this quarter, bringing the totals as of September 30th to 291 miles of fiber and 316 miles of strand. 5. SFC concluded negotiations, signed a contract and placed an initial purchase order with a provider of IP router equipment. The first phase of packet optical equipment was ordered and installed at major network nodes during the quarter. 6. SFC has signed agreements with CAIâ€™s for several additional locations on the planned network, and continued to work with CAIâ€™s to refine service needs, and to enter service agreements with them. 7. VTA and SFC staff participated in bi-weekly calls with NTIA, and prepared and submitted status reports. 8. Completed placement of fiber optic cable at five Federal Interstate highway crossing locations via aerial and underground constructi | 291 | 0 | 0 | 0 | 291 | 0 | 0 | 0 | The baseline plan was to have 600 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Significant progress was made during the quarter to close the gap between baseline and actual deployment, as the 173 network miles deployed during the quarter exceeded the 100 mile deployment projected initially in the baseline plan. | SFC is in negotiations for procurement of the fiber rights it intends to use along this network segment. | N/A | N/A | The baseline plan was to have 600 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Significant progress was made during the quarter to close the gap between baseline and actual deployment, as the 173 network miles deployed during the quarter exceeded the 100 mile deployment projected initially in the baseline plan. | N/A | N/A | Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. Interconnection points will be activated as construction is completed along related network segments. | 1 | 4 | 12 | Educational Networks of America, Inc. | The project is not yet providing services. | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the entire network when completed | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | N/A | Project is not presently providing service. | 0 | 0 | 0 | 0 | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | Project is not presently providing service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | All services planned are described in the Application Service Deck. No Special offerings | FALSE | N/A | 1) Sovernet Fiber Corp (SFC) will finish design survey for the remainder of the network, including most anchor institutions. 2) By end of quarter, make-ready work will have been authorized for approximately 98% of poles required for the project, make-ready work will be complete and licenses issued for roughly 19,500 poles (83% of the project's route miles), though not entirely in contiguous segments. 3) SFC's right of way contractor will continue to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 4) Approximately 190 route miles of aerial plant will be placed. By end of quarter, roughly 480 miles of cable will be attached to poles or in conduit. 5) Additional packet optical equipment will be installed, tuned, tested and placed in service. 6) An AAR for community anchor institution and minor route changes will be submitted during the quarter. 7) Service over the VFC network to several CAI locations will be initiated during the quarter. | Vermont Telecommunications Authority | SFC finished a productive quarter of outside plant construction and made significant additional progress in securing needed pole attachment licenses, rail and highway crossing permits, and network final design. | The overall volume and locations of pole attachment licenses issued by pole owners will continue to constrain outside plant construction, although with 63% of poles licenses at the start of the quarter and 83% anticipated by end of quarter, the quantity of contiguous segments of fully licensed poles will increase significantly. As mentioned in previous PPR's, there exists some risk that construction will be delayed on short network segments while easements are obtained or alternate routes designed, permitted and constructed. However, SFC expects all such situations can be resolved through negotiations or work-arounds. As always, the rate of progress on make-ready and outside plant construction is affected by winter weather conditions, which cannot be predicted with certainty. Timely review and approval of any Award Action Requests submitted to NTIA for scope changes will be necessary for project completion by the end of the award period.
NT10BIX5570076 | 2012 | Q4 | Q4 - 2012 | 1. Other than network segments in New Hampshire, all make-ready work has been authorized. SFC has design surveyed and applied for attachments to 97% of the estimated number of poles encompassed by the project, received make-ready cost estimates for 97%, and authorized make-ready work on 94%. Pole owners continued make-ready work. As of December 31, SFC had obtained licenses for 77% of the total pole count. At end of quarter, the proportion of poles for which either the electric utility or incumbent telephone company has issued make-ready licenses exceeded 80% of project total. 2. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing and municipal highway work permits. 3. During the quarter, contractors placed approximately 61 route miles of cable and 110 miles of messenger strand, bringing the totals as of December 31 to 377 miles of fiber and 401 miles of strand out of 773 total. 4. Packet optical equipment has been installed at seven major network nodes. 5. SFC signed agreements with CAIâ€™s for several additional locations on the planned network, and continued to work with CAIâ€™s to refine service needs, and to enter service agreements with them. As of end of the quarter, service was being provided to two CAIâ€™s and one last-mile provider. 6. VTA and SFC staff continued to brief and consult NTIA staff each two weeks, and to prepare and submit status reports. 7. AAR's for community anchor institutions, minor route changes and designation of an additional sub-recipient were submitted during the quarter. | 377 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | The baseline plan was to have 700 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Vermont utility crews were again mobilized out of region for several weeks to restore service and reconstruct utility plant damaged or destroyed by Hurricane Sandy. In spite of the challenges, 61 miles of fiber and 110 miles of strand were deployed during the quarter. | SFC is in negotiations for procurement of the fiber rights it intends to use along this network segment. | N/A | N/A | The baseline plan was to have 717 route miles deployed by the end of the quarter. Tasks prerequisite to construction were postponed until Special Award Condition 10 was lifted and the EA FONSI issued. In addition, starting in 2Q2011 and continuing through 2Q2012, redeployment of utility crews to areas of Vermont and southern New England to repair storm damage delayed make-ready for the project. Vermont utility crews were again mobilized out of region for several weeks to restore service and reconstruct utility plant damaged or destroyed by Hurricane Sandy. In spite of the challenges, 61 miles of fiber and 110 miles were deployed during the quarter. | N/A | N/A | Interconnection points will be activated as construction is completed along related network segments. | 3 | 4 | 16 | Educational Networks of America, Inc. Duncan Cable Southern Vermont Broadband Cooperative | GigE WAN Transport, and Direct Internet Access. | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the Vermont FiberConnect network when completed. | 0 | 1 | 0 | 1 | N/A | The number of broadband wholesalers and last mile providers served is lower than baseline due to overall make-ready and outside plant completion being less than projected in the orginal baseline plan. As network is completed, additional CAI's will be served. | N/A | Speed tiers are customized to to need of individual need of broadband wholesaler or last mile provider, and can be as much as 100 Gbps. | 2 | 0 | 2 | 0 | The level of CAI's served is lower than baseline due to overall make-ready and outside plant completion being less than projected in the orginal baseline plan. As network is completed, additional CAI's will be served. | N/A | N/A | Speed tiers are customized to individual customer need, and can be as much as 10 Gbps. CAI's currently using VFC services are utilizing GigE WAN and Direct Internet Access services. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | na | FALSE | na | 1) Sovernet Fiber Corp (SFC) will finish design survey for the remainder of the network, including most anchor institutions. 2) By end of quarter, make-ready work will have been authorized for approximately 98% of poles required for the project. Make-ready work will be complete and licenses issued for an additional 2,900 poles, for a cumulative total of roughly 21,000 poles (89% of the project's route miles), though not entirely in contiguous segments. 3) SFC's right of way contractor will continue to research easements, obtain landowner consents, secure rail crossing, interstate highway crossing and municipal highway work permits. 4) Approximately 231 route miles of aerial plant will be placed. By end of quarter, roughly 610 miles of cable will be attached to poles or placed in conduit. 5) During the quarter, two additional DWDM nodes will be installed. Additional network segments will be lit as fiber construction is completed. IP routers are expected to be configured and tested, and preliminary installs started during the quarter, with the majority of turn-up occurring in 2Q2013. 6) An additional ten to twenty CAI locations will be lit during the quarter. Wholesale service agreements will likely be entered with at least two additional last mile providers. | Vermont Telecommunications Authority | While progress was made during the quarter in obtaining pole attachment licenses, rights of way, permits and easements, outside plant construction remains constrained by incomplete make-ready that creates gaps in network segments that can be constructed. Dispatch of Vermont utility crews to Hurricane Sandy restoration along the Eastern seaboard decreased the pace of make-ready completion by pole owners and release of route segments to SFC to begin construction. In addition, construction work was held back from contractors for revised network routes pending NTIA's approval of an AAR for route changes. | The overall volume and locations of pole attachment licenses issued by pole owners will continue to constrain outside plant construction. Although the proportion of poles licenses obtained is expected to increase during the quarter from 78% to 89%, the quantity of contiguous segments of fully licensed poles will increase significantly. As mentioned in previous PPR's, there exists some risk that construction will be delayed on short network segments while easements are obtained or alternate routes designed, permitted and constructed. As always, the rate of progress on make-ready and outside plant construction is affected by winter weather conditions, the severity of which cannot be predicted, as well as additional major storm events within the project area or the region. Timely review and approval of any Award Action Requests submitted to NTIA for scope changes will be necessary for project completion by the end of the award period.
NT10BIX5570076 | 2013 | Q1 | Q1 - 2013 | a. SFC has design surveyed, applied for attachments, and requested make-ready work on 99% of the poles required for the project. Pole owners continue make-ready work. SFC had obtained licenses for 87% of the estimated number of poles â€“ up from 78% as of December 31. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing, river crossing and municipal highway work permits. b. During 2013Q1,there were 84 route miles of fiber and 131 miles of strand placed, bringing the total to 461 and 532 miles respectively, out of a project total of 792 miles. The project is currently at 67% of its objective for the core fiber build portion. Outside plant construction has been constrained by make-ready work not-completed by pole owners, securing permits and awaiting NTIA approval for AAR #2 route modifications. NTIA approved AARs for route modifications on 3/19/2013 which allowed for adjusted routes to be released to construction. c. SFC continued to work with CAIâ€™s to refine service needs, and to enter service agreements. By March 31st, of the 382 funded locations 241 CAIs were under contract, and 12 were connected / ready to serve. The project is currently at 5% of its objective to serve committed CAIs. Construction of laterals and entrances to CAIâ€™s continued with additional work released for construction as site surveys and design for each location have been completed. d. During the quarter, IP router equipment configuration was tested and confirmed in a lab environment. Packet optical Phase 1 equipment was installed and turned up, and installation of Phase 2 began. SFC ordered and received an additional $1.5M of electronic equipment during the quarter. e. VTA and SFC staff continued to brief and consult NTIA staff each two weeks, and to prepare and submit required reports. | 461 | 0 | 0 | 155 | 461 | 0 | 0 | 9 | Contractors placed approximately 84 route miles of cable and 131 miles of messenger strand, bringing the totals to 461 miles of fiber and 532 miles of strand. The original baseline plan was to have 750 route miles deployed by the end of the quarter. The difference between actual and baseline deployment is principally the result of matters reported in previous PPRs regarding Overlap, PA and Tropical Storms. This quarter the additive delay was due to a prolonged AAR review. | SFC is in negotiations for procurement of the fiber rights it intends to use along this 17 mile network segment. | N/A | A master service agreement and purchase order have been entered for an indefeasible right to use these dark fiber strands. | Contractors placed approximately 84 route miles of cable and 131 miles of messenger strand, bringing the totals to 461 miles of fiber and 532 miles of strand. The original baseline plan was to have 750 route miles deployed by the end of the quarter. The difference between actual and baseline deployment is principally the result of matters reported in previous PPRs regarding Overlap, PA and Tropical Storms. This quarter the additive delay was due to a prolonged AAR review. | N/A | N/A | The baseline plan includes a total of 16 interconnection points. The remaining points will be activated as construction is completed along related network segments. | 6 | 2 | 16 | Cloud Alliance Educational Networks of America, Inc. Duncan Cable Southern Vermont Broadband Cooperative Vanu Coverage Co. WaveComm | GigE WAN Transport, and Direct Internet Access. | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the Vermont FiberConnect network when completed. | 1 | 1 | 0 | 1 | No variance from baseline plan. | Baseline projection for this quarter was two. The number of broadband wholesalers and last mile providers served is lower than baseline due to overall make-ready and outside plant completion being less than projected in the orginal baseline plan. As network is completed, additional Last Mile Providers will be served. | N/A | Speed tiers are customized to to need of individual need of broadband wholesaler or last mile provider, and can be as much as 100 Gbps. | 12 | 0 | 12 | 0 | The level of CAI's served is lower than baseline due to overall make-ready and outside plant completion being less than projected in the original baseline plan. As network is completed, additional CAI's will be served. | N/A | The level of CAI's served is lower than baseline due to overall make-ready and outside plant completion being less than projected in the original baseline plan. As network is completed, additional CAI's will be served. | Speed tiers are customized to individual customer need, and can be as much as 10 Gbps. CAI's currently using VFC services are utilizing GigE WAN and Direct Internet Access services. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | a. Sovernet Fiber Corp (SFC) will finish design survey for the remainder of the network, which consists primarily of drops and entrances to anchor institutions and points of interconnection. b. SFC's right of way contractor will obtain remaining easements and property owner consents, secure rail crossing permits, miscellaneous remaining state land use permits, interstate highway crossing and municipal highway work permits. c. By end of quarter, make-ready work will have been authorized for 10 of the remaining 13% of the roughly 23,500 poles required for the project, leaving 3% to complete the project. As the remaining pole licenses and other permits are obtained, routes will be released for construction. d. 183 miles of aerial plant will be placed. By end of quarter, 644 miles of cable will be attached to poles or placed in conduit, leaving 148 miles to construct to complete the project. e. DWDM nodes will be ordered, received and installed, and network segments will be lit as fiber construction is completed. IP routers will be installed during the quarter. f. 118 CAI locations will be activated, bringing the total to 130. Facility designs will be completed within the quarter for all remaining CAI's, and those locations will be released to construction contractors as designs are finalized and location owner consents obtained. | Vermont Telecommunications Authority | While progress was made during the quarter in obtaining pole attachment licenses, rights of way, permits and easements, incomplete make-ready continues to present gaps in network segments that can be constructed. Pole owners have continued to do make-ready work and issue pole licenses at a relatively steady pace. It is anticipated that pole owners will have released all remaining poles to SFC by mid-July. Technical assistance with the make-ready from the BTOP project is not needed. SFC and pole owners continue to discuss, coordinate and prioritize make-ready work weekly. The VTA and SFC have limited ability to expedite completion of the make-ready work. In addition, several factors, primarily beyond the control of the recipient and sub-recipient delayed the rate of progress assumed in the original baseline project plan with most events occurring and have been reported in prior quarters. This quarter, an AAR was reviewed by NTIA for 4Â½ months which delayed construction progress on revised routes and CAIâ€™s. SFC has made significant progress in spite of the prolonged AAR review. | The outside plant construction will continue to be limited by the quantity of pole licenses issued by pole owners, the extent to which make-ready is completed on contiguous runs, and receipt of permits. At the current make-ready completion pace, it is anticipated that pole owners will have released all remaining poles to SFC by mid-July. Construction, splicing, optical testing, field inspection and verification for those network segments will be done following completion of the make-ready. Technical assistance with the make-ready from the BTOP project is not needed. SFC and pole owners continue to discuss, coordinate and prioritize make-ready work weekly, and the VTA and SFC have limited ability to expedite completion of the make-ready work. The pace of CAI entrance facility design and construction has been limited by the necessity to coordinate site access with each property manager and obtain the property owner's consent to the design of entrance facilities and network termination equipment. CAI's are typically very supportive of the project and look forward to receiving services. Even so, access to each location typically involves multiple staff and working within the schedule constraints of the CAI. SFC and its contractors will continue to communicate with property owners in order to obtain timely access and facility design consents.
NT10BIX5570076 | 2013 | Q2 | Q2 - 2013 | a. Pole make-ready work is nearing completion. As of June 30, SFC had obtained licenses for 93% of poles â€“ up from 87% as of March 31. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing and municipal highway work permits. b. During the quarter, approximately 221 route miles of fiber were placed, bringing the total as of June 30 to 627 miles. There have been 96 route miles released for construction, leaving approximately 63 route miles pending receipt of permits and licenses before release to construction. c. Construction of laterals and entrances to CAIâ€™s continue, with the completion of 187 CAI entrances, 71 of those locations now ready to serve, and the remainder in process of splicing, testing and set-up. d. The majority of IP router equipment has been installed. Portions of Phase 2 packet optical equipment were installed and turned up during the quarter. Phase 3 equipment was ordered. e. VTA, SFC and NHOS staff continued to brief and consult NTIA staff weekly, and to prepare and submit required reports. f. Work on the route identified in AAR#5 with NHOS has the following status: All make ready was completed, paid and most engineering was completed. A majority (60%) of the pole licenses have been received. Permit requests have been submitted for the two (2) railroad crossings along the network route and is expected to be received in mid July. | 627 | 0 | 0 | 155 | 644 | 0 | 0 | 9 | The difference between actual and baseline deployment is principally the result of matters reported in previous PPR's regarding resolution of funded project overlap, environmental assessment preceding, and construction resources diverted to address regional recovery from tropical storms. | SFC is in negotiations to procure rights to the 17 mile network segment that was included in the baseline plan. | N/A | A master service agreement and purchase order have been entered for a dark fiber IRU. Sovernet will accept and light the strands during 3Q2013. | The original baseline plan called for completion of 790 miles of new fiber by June 30. The variance form the baseline are stated in "New network miles deployed" above. | N/A | N/A | The baseline plan has 17 interconnection points after AAR approval with some variance based on permitting to access remote tower locations. The remaining points will be activated as construction is completed along related network segments. | 6 | 2 | 16 | Cloud Alliance Educational Networks of America, Inc. Duncan Cable Southern Vermont Broadband Cooperative Vanu Coverage Co. WaveComm | SFC portion of the project: GigE WAN Transport, and Direct Internet Access. AAR# portion of the project: Dark Fiber | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the Vermont FiberConnect network when completed, except for the portion defined in AAR#5, which will be operated in part by: New Hampshire Optical Systems, 99 Pine Hill Rd, Nashua, NH, 03063 | 1 | 2 | 0 | 3 | No variance from baseline plan. | No variance from baseline plan. | N/A | Speed tiers are customized to to need of individual need of broadband wholesaler or last mile provider, and can be as much as 100 Gbps. | 71 | 0 | 71 | 2 | The level of CAI's served is lower than baseline due to overall make-ready and outside plant being less complete than originally projected. | N/A | The level of CAI's served is lower than baseline due to overall make-ready and outside plant being less complete than originally projected. | Speed tiers are customized to individual customer need, and can be as much as 10 Gbps. CAI's currently using VFC services are utilizing GigE WAN and Direct Internet Access services. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | a. SFC will finish design survey for the remainder of the network, which consists primarily of drops and entrances to anchor institutions and points of interconnection. b. SFC's right of way contractor will obtain remaining easements and property owner consents, secure rail crossing permits, miscellaneous remaining state land use permits, interstate highway crossing and municipal highway work permits. c. SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for the remaining 1,360 (6%) poles. d. As the remaining pole licenses and other permits are obtained, additional routes will be released for construction. The remaining 159 miles of aerial plant will be placed. e. The point of interconnection in Boston MA will be activated. f. Remaining routers and DWDM nodes will be ordered, received and installed. Additional network segments will be lit as fiber construction is completed. g. 194 additional CAI locations will be activated, bringing the total to 260. Facility designs will be completed within the quarter for all remaining CAI's, and those locations will be released to construction contractors as designs are finalized and location owner consents obtained. h. AAR#5 construction will commence and be completed for the pending 16 mile route in Essex County VT. | Vermont Telecommunications Authority | NTIA approval during 1Q2013 for route revisions and CAI changes, cleared the way for a productive quarter of outside plant construction, with 221 route miles (roughly a quarter of the project's total) of fiber placed. Nonetheless, as in prior quarters, construction was constrained while pole attachment licenses and permits such as for rail and river crossings, street excavation, land use were obtained. The list of remaining permits is rapidly diminishing. Coordinating building access with over 300 CAI's and other service location owners for design and construction has also restrained the pace at which CAI's can be connected. Staff resources have been supplemented in order to schedule and expedite the site access. NTIA and FCC advocacy for widespread adoption of ultra-high speed connectivity by community anchor institutions has motivated CAI's to collaborate with SFC on implementation. | The outside plant construction will continue to be limited by the quantity of pole licenses issued by pole owners, the extent to which make-ready is completed on contiguous runs, and receipt of permits. It is anticipated that pole owners will have released all remaining poles to SFC within the quarter. Diversion of pole owner construction resources in response to severe weather events remains a risk to completion of make-ready and construction. Construction, splicing, optical testing, field inspection and verification for those network segments will be done following completion of the make-ready. Inspection and verification will carry over into 4Q2013. The pace of CAI entrance facility design and construction has been limited by the necessity to coordinate site access with each property manager and obtain the property owner's consent to the design of entrance facilities and network termination equipment. CAI's are typically very supportive of the project and look forward to receiving services. Even so, access to each location typically involves multiple staff and working within the schedule constraints of the CAI. SFC and its contractors will continue to communicate with property owners in order to obtain timely access and facility design consents.
NT10BIX5570076 | 2013 | Q3 | Q3 - 2013 | As of September 30, SFC had obtained licenses for 96% of the estimated number of poles, up from 93% as of June 30. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing and municipal highway work permits. Outside plant construction has continued as pole licenses, easements and other permits have been obtained. In this quarter 136 route miles of fiber were placed, bringing the total as of September 30 to 763 miles. 18 route miles of in-place fiber were obtained from another carrier with a remaining 46 route miles to be placed. Construction of laterals and entrances to CAIâ€™s were a primary focus this quarter, 236 locations ready to serve, and the remainder in process of splicing, testing, and service provisioning. AAR#5, which was 13 miles of fiber to connect another BTOP grant to a regionally stranded fiber network in the Northeast Vermont area, began and was completed in this quarter. | 763 | 18 | 0 | 172 | 763 | 0 | 0 | 16 | Contractors placed 136 route miles of cable during the quarter, bringing the total to 763 miles. The original baseline plan was to have 773 route miles constructed by the end of the quarter. The difference between actual and baseline deployment is the result of early delays previously reported. As a result of approved route modifications and refined network design plans, the overall construction increased to 809 route miles, which includes 13 miles due to AAR#5. | During the quarter, SFC completed negotiations to obtain rights to 18 network route miles (IRU), as intended in the original baseline project plan. | N/A | During 2Q2013, a master service agreement and purchase order was entered for an indefeasible right to use these dark fiber strands. The hand off to use this fiber is expected in early November. The route is currently being "burned-in" for testing. | Contractors placed 136 route miles during the quarter, and obtained additional permits and consents to enable completion of the project. As of September 30, approximately 46 route miles of fiber remained to be placed. | N/A | N/A | The baseline plan included a total of 16 interconnection points, and a 17th was added with approval an AAR to be activated in the final quarter of the project. | 6 | 3 | 16 | Cloud Alliance Educational Networks of America, Inc. Duncan Cable Southern Vermont Broadband Cooperative Vanu Coverage Co. WaveComm | GigE WAN Transport, and Direct Internet Access, Dark Fiber Lease in areas identified in AAR#5 | Sovernet Fiber Corp., 5 Canal Street, Bellows Falls, VT 05101 Subrecipient Sovernet will operate the Vermont FiberConnect network | 1 | 2 | 0 | 3 | No variance from baseline plan. | No variance from baseline plan. | N/A | Speed tiers are customized to to need of individual need of broadband wholesaler or last mile provider, and can be as much as 100 Gbps. | 236 | 0 | 236 | 2 | The level of CAI's served is lower than baseline due to overall make-ready and outside plant being less complete than projected in the original baseline plan. As network is completed, additional CAI's will be served. | N/A | The level of CAI's served is lower than baseline due to overall make-ready and outside plant being less complete than projected in the original baseline plan. As network is completed, additional CAI's will be served. | Speed tiers are customized to individual customer need, and can be as much as 10 Gbps. CAI's currently using VFC services are utilizing GigE WAN Transport and Direct Internet Access services. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 32 | 0 | 0 | 32 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project will be completed during 4Q2013. Construction of the Vermont FiberConnect network, and installation of facilities all remaining community anchor institutions and points of interconnection will be completed. a. Pole owners will complete make-ready and issue pole attachment licenses for the remaining [5]% of poles. b. All remaining permits and property owner consents will be obtained. c. The remaining 46 miles of aerial plant will be placed. d. Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. e. All remaining core network segments will be tested, configured and lit. f. 97 CAI locations will be readied for service, bringing the total to 349. | Vermont Telecommunications Authority | Coordinating building access with over 300 CAI's and other property owners for construction, installation and follow-up testing have restrained the pace at which CAI's can be connected. Supplemental staff resources, added during 2Q2013, have helped accelerate the pace of completion and customer turn-up. | Construction of the remaining 46 route miles is dependent on timely completion of make-ready by pole owners and third-party attachees. While the remaining mileage is much smaller than in quarters past, the possibility remains that pole owner and attachee construction resources could be diverted to address severe weather events that cause widespread damage to other utility plant. Splicing, optical testing, field inspection and verification for those network segments all follow placement of fiber cable. Timing of completion is dependent on the quality of the OSP contractors' initial fiber splicing. Installation, testing and equipment configuration at CAI premises continues requires several trips to customer premises, most of which need to be coordinated with property managers and IT staff of the CAI. Nearly all CAI's look forward to using the upgraded services. Nonetheless, SFC's ability to complete every installation and test every circuit during the award period will depend on coordination of schedules and timely access to CAI premises. In summary, barring a major unforeseen event, VFC meets its award obligations to make service available to all CAI's and points of interconnection by the end of 4Q2013.
NT10BIX5570076 | 2013 | Q4 | Q4 - 2013 | Pole make-ready work is complete. SFCâ€™s right-of-way contractor continued to research easements, obtain landowner consents, secure rail crossing and municipal highway work permits. Outside plant construction continued at a rapid pace as additional pole licenses, easements and other permits were obtained. The total fiber placed to date is 807 route miles. The leased fiber connection to the Boston MA interconnection point was activated. Construction of laterals and entrances to CAIâ€™s continued during the quarter as site surveys and design for each location was completed. Network equipment was ordered and received. Network segments were lit as fiber construction was completed. There are 306 out of the total 316 CAIs in service or ready to serve with 97 CAIs being connected this quarter. VTA reported 307 CAIs in its 2013 APR, but following an extensive review of all project CAIs that concluded in December 2014, VTA has determined that the correct 2013 end of year connected CAI count is 306, albeit comprised of a slightly different set of CAIs than reported with the 2013 APR and with an additional 10 CAIs planned but not yet connected. See attached â€œCAI Differences in 4Q2013PPR--2013APR and 3Q2013PPR 1 7 2015.xlsxâ€ for details. | 807 | 193 | 0 | 0 | 1000 | 0 | 0 | 88 | The original baseline plan was to have 773 route miles constructed by the end of the quarter. The difference between actual and baseline deployment is due to route changes approved by NTIA, as well as differences between original route length estimates and "actuals" based on as-built plans. | During 4Q2013, SFC accepted and started to use dark fiber strands that were obtained under an IRU approved by NTIA. | N/A | N/A | The combination of both new network fiber miles built and new leased fiber miles. | N/A | N/A | The baseline plan included a total of 16 interconnection points, and a 17th was added with approval an AAR. All 17 interconnection points have been activated. Additional interconnection points were added through AARs as the project progressed. | 6 | 3 | 16 | Cloud Alliance Educational Networks of America, Inc. Duncan Cable Southern Vermont Broadband Cooperative Vanu Coverage Co. WaveComm | GigE WAN Transport, and Direct Internet Access with Dark Fiber Lease between Guildhall VT and Bloomfield VT Price descriptions included in the file attached to this report called "VTA FiberConnect Retail Rates.pdf" | NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. is the operating entity of the dark fiber segment between Guildhall VT and Bloomfield VT. Contact info: NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. 10 N. Southwood Drive, Nashua NH 03063 All other elements of the network are owned and operated by Subrecipient, Sovernet Fiber Corp.. Contact info at Sovernet: Lawrence Lackey, LLackey@sover.net, 5 Canal Street, Bellows Falls, VT 05101-0495. | 4 | 2 | 0 | 30 | No variance from baseline plan. There are still wholesale providers with signed agreements that have circuits pending activation due to contract term expirations. | No variance from baseline plan. There are still wholesale providers with signed agreements that have circuits pending activation due to contract term expirations. | The VTA's dark fiber offering in the Essex County area currently does not have any contracts under negotiation as the northern terminus is waiting on a fiber build by the regional electric utility to be completed. Therre are four rate levels based on term length for dark fiber IRU in the Essex County fiber route. Currently this route has no IRU contracts executed. | Speed tiers are customized based on the need of need of broadband wholesaler or last mile provider, up to 100 Gbps. These service tiers are various levels of bandwidth connections for last mile providers. Sovernet also services CAIs via resellers & last mile providers at the speeds shown below for CAIs so there is the potential for this total to grow if a last mile provider or wholesaler takes another level of service. The service tiers identified in the service tier rate sheet is not restricted to any customer type. It is also more logical that only a wholesale / last mile provider will subscribe to a transport type service tier. Dedicated Internet Access Service (Mbps, Committed-Rate, Symmetric) : # of Subscribers: 10 Mbps: 0 20 Mbps: 1 25 Mbps: 0 30 Mbps: 0 40 Mbps: 0 50 Mbps: 0 100Mbps: 2 200 Mbps: 0 300 Mbps: 0 400 Mbps: 0 500 Mbps: 1 600 Mbps: 0 700 Mbps: 0 750 Mbps: 0 800 Mbps: 0 900 Mbps: 0 1,000 to 10,000 Mbps: 0 Ethernet WAN Service: Committed Information Rate / Port Speed (in Mbps) : # of Subscribers 25 / 1,000 Mbps: 0 50 / 1,000 Mbps: 0 100 / 1,000 Mbps: 1 200 / 1,000 Mbps: 0 300 / 1,000 Mbps: 0 400 / 1,000 Mbps: 0 500 / 1,000 Mbps: 0 600 / 1,000 Mbps: 0 700 / 1,000 Mbps: 0 750 / 1,000 Mbps: 0 800 / 1,000 Mbps: 0 900 / 1,000 Mbps: 0 1,000 / 1,000 Mbps: 0 There no speed tiers associated with dark fiber as it is not applicable. | 306 | 306 | 0 | 30 | VTAâ€™s CAI baseline is 342. Its end of project target CAI count is 316. In addition, laterals have been extended to the closest utility pole serving 32 medical offices/clinics, which are not yet connected to the BTOP network. Please note that VTA reported 307 CAIs connected in its 2013 APR, but following an extensive review of all project CAIs that concluded in December 2014, VTA has determined that the correct 2013 end of year connected CAI count is 306, albeit comprised of a slightly different set of CAIs than reported with the 2013 APR. (We have an additional 10 CAIs planned but not yet connected.) The 97 CAIs highlighted in yellow on the attached 4Q13/2013 CAI Addendum were connected during 4Q13. | 306 of the 316 are connected. | N/A | Speed tiers are customized to individual customer need, and can be as much as 10 Gbps. CAI's currently using VFC services are utilizing GigE WAN Transport and Dedicated Internet Access services. 224 of the 306 connected CAIs are taking service in the following tiers (note that nine CAIs take both Dedicated Internet Service and WAN services). Dedicated Internet Access Service: (Service speed : # of CAI's Subscribed) 10 Mbps: 16 20 Mbps: 2 25 Mbps: 6 30 Mbps: 0 40 Mbps: 0 50 Mbps: 2 100Mbps: 10 200 Mbps: 1 300 Mbps: 1 400 Mbps: 0 500 Mbps: 0 600 Mbps: 0 700 Mbps: 0 750 Mbps: 0 800 Mbps: 0 900 Mbps: 0 1,000 to 10,000 Mbps: 0 Ethernet WAN Service: (Service speed / Port Speed : # of CAI's) 25 / 1,000 Mbps: 0 50 / 1,000 Mbps: 44 100 / 1,000 Mbps: 151 200 / 1,000 Mbps: 0 300 / 1,000 Mbps: 0 400 / 1,000 Mbps: 0 500 / 1,000 Mbps: 0 600 / 1,000 Mbps: 0 700 / 1,000 Mbps: 0 750 / 1,000 Mbps: 0 800 / 1,000 Mbps: 0 900 / 1,000 Mbps: 0 1,000 / 1,000 Mbps: 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | The narrative regarding the 33 locations previously reported here have been moved to the CAI narrative above. One (1) site has been removed in AAR 2499843 reducing this count to 32. | N/A | N/A | N/A | N/A | FALSE | N/A | a. Remaining permits and property owner consents will be obtained during 1Q2014 for the 20 POI locations. In most instances, construction will be deferred until 2Q2014 due to difficulty of underground and/or off-road construction during winter. b. Construction of the remaining route miles of core network facilities will be completed. c. Installation, testing and configuration of network electronics will continue in order to enable the network's full capabilities. d. Project engineers will continue to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. | Vermont Telecommunications Authority | On-set of cold temperatures and snow cover in late November (several weeks earlier than normal) limited outside plant construction during the last five weeks of the quarter, in particular underground segments were delayed. Completion of several segments was also slowed by prolonged review of permit applications, pole line relocations, river and highway crossings, and extended negotiations with property owners where easements or access permissions are required for placement of cable facilities. | The key activity during the next quarter is to obtain right-of-way consents for access to the remaining points of interconnection. This will require case-by-case negotiations with property owners, some of which may not result in agreements that allow for construction. There remain 10 CAI locations to construct.
NT10BIX5570076 | 2014 | Q1 | Q1 - 2014 | One CAI location was connected during the quarter. 307 out of the total 316 CAI locations are in service or ready to serve with 9 remaining in the project to complete. This quarter work efforts were still concentrated on obtaining permits and property access agreements or easements for the remaining points of interconnection, none of which are accessible via existing utility rights of way. At the end of the quarter, permits and access consents had been obtained for 7 of the remaining 27 interconnection points. Outside plant construction, installation, testing and configuration of the network continued during this quarter. SFC's resident engineers continued field inspections of constructed plant, and verified that punch-list items previously identified had been corrected or otherwise resolved by construction contractors. Digitization of as-built documentation of the network continued during the quarter. | 813 | 193 | 0 | 0 | 1006 | 0 | 0 | 82 | The original baseline plan was to have 773 route miles constructed by the end of the quarter. Actual network miles deployed differs slightly from the baseline plan due net effect of route changes approved by NTIA, as well as differences between original route length estimates and "actuals" based on as-built plans. | Variance of +1 mile relative to baseline plan due to error in preliminary estimate. | N/A | [REDACTED] | The combination of both new network fiber miles built and new leased fiber miles. | N/A | N/A | The initial baseline for interconnection points was 16, which excluded interconnection points at cell sites. No new POIs were completed in 1Q2014. However, a VTA review of POI site locations has identified an error in the number of cumulative completed POIs reported in 4Q2013 (88 POIs). VTA has identified that the correct number should have been 82, which is reported here. The list of 82 POIs is documented as an attachment to this PPR filing. | 6 | 3 | 16 | [REDACTED] | GigE WAN Transport, and Direct Internet Access are offered by subrecipient Sovernet Fiber Corp over the Vermont FiberConnect Network. Dark fiber is offered through Dark Fiber Lease with the VTA between Guildhall VT and Bloomfield VT Price descriptions included in the files attached to this report called "VTA FiberConnect Rate Sheet.pdf" and "VTA Wholesale Dark Fiber Rate Table.pdf". | NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. is the operating entity of the dark fiber segment between Guildhall VT and Bloomfield VT. Contact info: Darren LaCroix, dlacroix@10xtactics.com, NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. 10 N. Southwood Drive, Nashua NH 03063 All other elements of the network are owned and operated by Subrecipient, Sovernet Fiber Corp.. Contact info at Sovernet: Lawrence Lackey, LLackey@sover.net, 5 Canal Street, Bellows Falls, VT 05101-0495. | 4 | 2 | 0 | 30 | The baseline of 1 was exceeded by 3 due to the fact the project was extended and more providers signed agreements. There are still wholesale providers with signed agreements that have circuits pending activation due to contract term expirations. | No variance from baseline plan. There are still wholesale providers with signed agreements that have circuits pending activation due to contract term expirations. | The VTA's dark fiber offering in the Essex County area currently does not have any contracts under negotiation as the northern terminus is waiting on a fiber build by the regional electric utility to be completed. Therre are four rate levels based on term length for dark fiber IRU in the Essex County fiber route. Currently this route has no IRU contracts executed. | [REDACTED] | 307 | 307 | 0 | 30 | [REDACTED] | One additional CAI was connected this quarter. | N/A | [REDACTED] | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | a. Construction to all but 9 currently-designated CAIs and 27 POIs have been completed. If consent of a property owner cannot be obtained for construction and ongoing access to the remaining CAI / POI locations, an Award Action Request will be submitted to remove the CAI locations from the project and move the POI demarc locations of remaining points to the closest utility pole that has already been built out to. It is anticipated that construction will be completed during 2Q2014, although a portion may extend in to 3Q2014. b. Installation, testing and configuration of network electronics will continue in order to enable the network's full capabilities. c. Project engineers will continue to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. | Vermont Telecommunications Authority | As expected at the beginning of this quarter, cold temperatures and snow cover limited the ability to complete the small amount of outside plant that was otherwise ready to construct. Right of way activity was concentrated on obtaining consents from property owners necessary to reach the final POIs that remain to be completed. Fewer property owners granted easements or access consents than were projected at the outset of the quarter. It is our objective to obtain property owner consents during 2Q2014 for the remaining 27 POIs, or an Award Action Request will be submitted to move the service demarcation points for the remaining points. | The key activity during the next quarter is to obtain right-of-way consents for access to the remaining points of interconnection. This is requiring case-by-case negotiations with property owners, some of which may not result in agreements that allow for construction. An Action Award Request is likely be to submitted during the quarter, to remove or move points of interconnection for which property owner consent has not been obtained. This quarter's reported expenditures incorporate an adjustment to the equipment line item for expenditures reported in prior quarters. Between April 2013 and February 2014 Sovernet recorded $236,843.04 in expenses for certain customer-premise equipment that provides an interface between the fiber optic transport network and the customerâ€™s internal network. Of this amount, $214,060.42 has been reported in prior quarters as a grant-eligible expense: $202,566.00 in the Q2 2013 report, $3,234.42 in the Q3 2013 report, and $8,260.00 in the Q4 2013 report. In February 2014, Sovernet determined that the equipment could not be utilized by the Vermont Fiber Link project. On February 28, 2014, Sovernet recorded a reduction of $236,843.04 in equipment costs in the project general ledger as a reduction in allowable project costs and a liability due back to the project. On March 20, 2014, Sovernet made a deposit in this amount into the projectâ€™s bank account to pay the liability. The equipment actuals reported in 1Q2014 are less than the equ
NT10BIX5570076 | 2014 | Q2 | Q2 - 2014 | Activity during the quarter focused on obtaining property owner permissions to construct facilities to the 27 remaining points of interconnection. One CAI has been connected this quarter. Project engineers conducted field reviews of completed work to verify the completeness and quality of construction work, and returned "punch-lists" to construction contractors to correct. Project engineers continued to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. | 819 | 172 | 0 | 17 | 991 | 0 | 0 | 82 | The original baseline plan was to have 773 route miles constructed by the end of the quarter. Actual network miles deployed differs slightly from the baseline plan due net effect of route changes approved by NTIA, as well as differences between original route length estimates and "actuals" based on as-built plans. The 818.83 mile total reported here includes 13 miles constructed by sub-recipient NHOS. | The baseline was originally for a 16 mile segment in Rutland county which later became 17 miles and moved to "Existing network miles leased". This number represents the Boston IRU which was added to the project in AAR 2411138 with estimated miles. This number was later confirmed to actually be 172 miles. | N/A | [REDACTED] | The combination of both new network fiber miles built and new leased fiber miles. | N/A | N/A | The initial baseline for interconnection points was 16, which excluded interconnection points at cell sites. No new POIs were completed during 2Q2014. | 6 | 3 | 16 | [REDACTED] | GigE WAN Transport, and Direct Internet Access are offered by subrecipient Sovernet Fiber Corp over the Vermont FiberConnect Network. Dark fiber is offered through Dark Fiber Lease with the VTA between Guildhall VT and Bloomfield VT Price descriptions included in the files attached to this report called "VTA FiberConnect Retail Rates.pdf" and "VTA Wholesale Dark Fiber Rate Table.pdf". | NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. is the operating entity of the dark fiber segment between Guildhall VT and Bloomfield VT. Contact info: Darren LaCroix, dlacroix@10xtactics.com, NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. 10 N. Southwood Drive, Nashua NH 03063 All other elements of the network are owned and operated by Subrecipient, Sovernet Fiber Corp.. Contact info at Sovernet: Lawrence Lackey, LLackey@sover.net, 5 Canal Street, Bellows Falls, VT 05101-0495. | 4 | 2 | 0 | 30 | Variance from baseline was increased from original known potential agreements due to continued discussions with Wholesale and Last Mile Providers that have resulted in an increase from 1 to 4 with new access. | No variance from baseline plan. | The VTA's dark fiber offering in the Essex County area currently does not have any contracts under negotiation as the northern terminus is waiting on a fiber build by the regional electric utility to be completed. | [REDACTED] | 308 | 308 | 0 | 30 | [REDACTED] | One CAI has been connected this quarter | N/A | [REDACTED] | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project will be completed during the next quarter (ending September 30, 2014). a. 650 feet of underground core route will be constructed to replace two temporary segments previously installed. Approximately 5 routes-miles of plant will be completed during the quarter to reach the remaining tower sites. b. Construction to all but 8 currently-designated CAIs and 27 POIs have been completed. If consent of a property owner cannot be obtained to the remaining CAI / POI locations, an Award Action Request will be submitted to remove the CAI locations from the project and move the POI demarc locations of remaining points to the closest utility pole that has already been built out to. c. Installation, testing and configuration of network electronics continue d. Project engineers will continue to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. | Vermont Telecommunications Authority | Obtaining property owner permissions for a portion of the remaining 27 Points of Interconnection and handful of CAI's have been a challenge, as some locations involve multiple entities, and some property owners have been slow in responding to requests for property access. NTIA approval of an AAR to move several designated Points of Interconnection will be needed. | The key activities in this final quarter of the award period are to obtain property owner consents for the remaining POI locations,complete construction of facilities to reach the 27 remaining POI's and 8 remaining CAI's, verify construction meets contractual standards, and close-out the remaining equipment and services contracts between subrecipient Sovernet Fiber Corp and vendors. Property owner consents are still required for construction to reach several of these locations. Construction to reach the remaining locations is approximately 5 route miles. This quarter's reported expenditures incorporate an adjustment to the equipment line item for expenditures reported in prior quarters. The 1Q2014 PPR described an adjustment Sovernet made in that quarter to reclassify and reduce certain costs recorded in between April 2013 and February 2014 for equipment that Sovernet determined could not be utilized by the Vermont Fiber Link project. Subsequently, however, Sovernet determined that this expense (and the subsequent adjustment in 1Q2014) was overstated due to an error in calculating sales tax on a portion of the equipment that was the subject of the adjustment, specifically 57 Ciena enclosures recorded in 2Q2013. The error consisted of incorrectly calculating Vermont sales tax on these items at the rate of 60% (0.6) instead of the correct rate of 6% (0.06). On April 8, 2014, Sovernet recorded an adjustment of $9080.10 in project equipment costs to correct the error.
NT10BIX5570076 | 2014 | Q3 | Q3 - 2014 | A. The project was completed during the quarter (ended September 30, 2014). B. All construction that was authorized in the project was finished by the end of the quarter. C. This quarter there were three AARs approved that made adjustments, additions and removals of CAIs & POIs, bringing total to 316 and 109 respectively. D. Installation, testing and configuration of network electronics was completed this quarter. E. Project engineers have concluded field reviews of completed work to verify the completeness / quality of construction work, and ensure appropriate resolution of "punch-list" items. As-built documentation and mileage true-ups continue this quarter. F. Project engineers will continue to document the completed network on "as-built" plans, and to load strand assignments and other network information into the network inventory platform. G. The project total of CAIs reached was 316 sites : 7 Community College, 44 Libraries, 31 Medical or Healthcare Providers, 5 Other Community Support Organization, 73 Other Government Facilities, 22 Other Institutions of Higher Education, 29 Public Safety Entity, 105 School (k-12). The net benefit of many of these institutional groups is that they are able to create a more robust Wide Area Network, which in turn can deliver much greater capacity Internet service at a lower aggregated cost. Many school districts, higher education networks, municipal / state facilities, and medical institutions greatly benefited from the project in this way. The underlying infrastructure now enables these institutions to share resources, utilize internet based systems and services that was previously unable to be used. H. Many of the 109 POI locations were fiber connections to cell towers, some new and some that were lacking the fiber facilities to support the data growth needs of the cellular and wireless carriers. I. In addition for providing new fiber-based backhaul alternatives at cell towers, the project is providing backhaul options for a VTA-funded project to expand cellular service along "target corridors" in rural mountain valleys using small cell installations. J. The project has provided new, lower-cost and higher-capacity options commodity internet bandwidth to small last-mile wireless and cable Internet service providers serving rural communities in Vermont, as well as community anchor institutions. | 828 | 172 | 0 | 17 | 1000 | 0 | 0 | 109 | The original baseline plan was to have 773 route miles constructed at project completion. Actual network miles deployed differs slightly from the original baseline due to the net effect of route changes approved by the NTIA, as well as differences between original route length estimates and "actuals as-built". In 3Q2014, NTIA approved three AARs that changed the project's route miles. This total includes 13 miles constructed by sub-recipient NHOS. | The baseline was originally for a 16 mile segment in Rutland county which later became 17 miles and moved to "Existing network miles leased". This number represents the Boston IRU which was added to the project in AAR 2411138 with estimated miles. This number was later confirmed to actually be 172 miles. | N/A | Original baseline was 0 but we were instructed to move a leased fiber segment from "New network miles leased" to this line. Sovernet has leased 17 miles of 144 strand from a first round BTOP recipient company named ION, which is a subsidiary of Sovernet. Also to note, the agreement did not use BTOP funds. | The combination of both new network fiber miles built and new leased fiber miles. | N/A | N/A | The initial baseline for interconnection points was 16, which excluded interconnection points at cell sites. This quarter there were two AARs that made adjustments, additions and removals of POIs. The adjustment stated above in paragraph C of the narrative response to Question 1 brings the total to 109. | 8 | 2 | 16 | [REDACTED] | GigE WAN Transport, and Direct Internet Access are offered by subrecipient Sovernet Fiber Corp over the Vermont FiberConnect Network. Dark fiber is offered through Dark Fiber Lease with the VTA between Guildhall VT and Bloomfield VT Price descriptions included in the files attached to this report called "VTA FiberConnect Rate Sheet.pdf" and "VTA Wholesale Dark Fiber Rate Sheet.pdf". | NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. is the operating entity of the dark fiber segment between Guildhall VT and Bloomfield VT. Contact info: Darren LaCroix, dlacroix@10xtactics.com, NEW HAMPSHIRE OPTICAL SYSTEMS, Inc. 10 N. Southwood Drive, Nashua NH 03063 All other elements of the network are owned and operated by Subrecipient, Sovernet Fiber Corp.. Contact info at Sovernet: Lawrence Lackey, LLackey@sover.net, 5 Canal Street, Bellows Falls, VT 05101-0495. | 6 | 2 | 0 | [REDACTED] | Variance from baseline was increased from original known potential agreements due to continued discussions with Wholesale and Last Mile Providers that have resulted in an increase from 1 to 6 with new access. | No variance from original baseline. | The VTA's dark fiber offering in the Essex County area currently does not have any contracts under negotiation as the northern terminus is waiting on a fiber build by the regional electric utility to be completed. | [REDACTED] | 316 | 316 | 0 | [REDACTED] | [REDACTED] | See narrative above, regarding total CAI subscribers served. | N/A | [REDACTED] | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project completed | Vermont Telecommunications Authority | [REDACTED]
NT10BIX5570077 | 2010 | Q4 | Q4 - 2010 | The draft Environmental Assessment was submitted to NTIA on December 16th, ahead of required date of January 2, 2011. Permitting is coming along well; we have received a Nationwide permit #12 from the Corp. of Engineers for crossing the Wetlands, WYDOT has reviewed our permit documents and is processing them for issue; Teton County is preparing to issue the permit for the limited areas of their jurisdiction that we cross; the US Forest Service and Grand Teton National Park Service will issue permits upon completion of the EA document, and we are in the final stages of obtaining a Franchise Agreement with the Town of Jackson, WY. Engineering design and construction documents are approximately 60% complete, including the RUS contract documents and design drawings. An informal pre-bid meeting for potential contractors was held at the Jackson, WY, Town Hall on November 9, 2010. Recipient is still adhering to reporting deadlines. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | NONE | FALSE | N/A | Recipient anticipates 100% completion of construction drawings and contract document package by February 18th. A Notice of OSP Contract Availability is scheduled to be published March 1, 2011. A formal Pre-bid meeting is tentatively scheduled for March 15th at the Jackson Town Hall. It is anticipated the Environmental Assessment will be completed this quarter, and all permits required for the project will be obtained. | Silver Star Telephone Company, INC. | None | NONE
NT10BIX5570077 | 2011 | Q1 | Q1 - 2011 | The recipient held the Pre-bid meeting on March 17 2011 and it was determined that the bids would be accepted until April 5, 2011 at 2pm at which time they would be publicly opened. OSP design was completed on time and the Transport and Access Engineering was in progress. Recipients AAR for proposed route changes was approved. Finally the recipient's EA was accepted and the FONSI issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | None | FALSE | N/A | The recipient will award the outside plant construction contracts to the acceptable responsive bidder. It s anticipated that all required permits will be secured to allow construction to start. It is anticipated construction will commence on or before May 2, 2011. The EA SAC will be lifted to permit commencement of construction and receipt of Federal funds. Transport and Access Engineering will be completed. Construction of the fiber and duct system will be in progress. | Silver Star Telephone Company, INC. | None | NONE
NT10BIX5570077 | 2011 | Q2 | Q2 - 2011 | The contractor has completed placement of four miles of conduit has been completed from the start of the project south of the Town of Jackson on US Highway 89 and another 5400' has been bored through the Town. The construction contractor has also completed 2100' of micro-trenching in town; drops to the community anchor institutes have been built by the contractor as it passes the CAI locations. Recipient is in the process of obtaining necessary private easements to bring service into the 34+ Community Anchor Institutes. This contractor has stated that it intends to complete the project this year. Construction/renovation of the building that will be recipient's central office facility in Jackson for this project is underway, following the award of the construction contract after a competitive bid process.. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | N/A | FALSE | N/A | Phase 1 of the project, which includes 17 community anchor institutes, will be completed and in service. Outside plant project completion is likely to be 80%. We will begin to see progress on the Network Access equipment purchase; while electrical equipment procurement occurred in 2q 2011, system electronics procurement will begin in 3q 2011. | Silver Star Telephone Company, INC. | Exceptional wet weather conditions during May and June caused long delays resulting in construction crews having to stop work altogether for up to ten days. | N/A
NT10BIX5570077 | 2011 | Q3 | Q3 - 2011 | Thirty one miles of plowing has been completed. The contractor has bored just over 30,500 feet through the Town of Jackson and completed about 5,100 feet of micro trenching in town. The total project is 42 miles. Some plowing to Teton Village and some on the bike path still need to be completed on the East side of the pass. Several bores and tieâ€ins need to be completed. The contractor has placed all the micro fiber and has started placing the main fiber. The contractor still plans to finish the entire fiber project this year. | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | Accelerated construction progress | N/A | N/A | N/A | Accelerated construction progress | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Will be 90% OSP completion and 40% electronics | Silver Star Telephone Company, INC. | N/A | Winter weather will slow construction down considerably in the next quarter.
NT10BIX5570077 | 2011 | Q4 | Q4 - 2011 | The contractor has bored just over 39,920 feet throughout the entire project and completed about 16,600 feet of micro trenching in town. All the plowing has been completed through the entire project except for the remaining Community Anchor drops; the total project is 42 miles plus additions. All fiber has been blown in, with the exception of fiber still needs to be pulled in an existing conduit at Teton Village pending a contract agreement. The contractor will resume construction in the spring. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | Variance due to accelerated construction progress | No variance | No variance | No variance | Variance due to accelerated construction progress | No variance | No variance | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 3 | 0 | 0 | 0 | Drops to three CAI's have been placed; testing is in progress and services are anticipated to be available 1q012 | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Plans are to start offering services after testing has been completed sometime next quarter. | FALSE | N/A | Recipient anticipates that facilities testing will be completed and services available to CAI's. | Silver Star Telephone Company, INC. | Recipient experienced no challenges or issues in achieving progress against project milestones. | No challenges or issues are anticipated during first quarter 2012; project progress is well ahead of project baseline indicators.
NT10BIX5570077 | 2012 | Q1 | Q1 - 2012 | While project construction halted during the winter months, facilities testing is nearly complete and service is available to a majority of the CAIs. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | Variance due to accelerated construction progress | N/A | N/A | N/A | Variance due to accelerated construction progress | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 1 | 0 | 34 | 1 | CAI - medical services facility | N/A | CAIs include elementary education entities, several Federal department/division entities, Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | Maximum 1 Gbps; No Variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 1 | N/A | N/A | N/A | N/A | 100 Mbps | N/A | FALSE | N/A | Recipient anticipates 100% completion of the project construction and CAI drops and almost 100% overall project completion; over 41 network fiber miles will be placed and 50 CAIs will be connected to that network. | Silver Star Telephone Company, INC. | Recipient experienced no issues or challenges during this past quarter; project progress is well ahead of project baseline indicators. | Recipient anticipates no challenges or issues during second quarter 2012 that may impact planned progress; in fact, progress against baseline milestones are ahead of schedule to the timeline (project year three, first quarter).
NT10BIX5570077 | 2012 | Q2 | Q2 - 2012 | Recipient experienced no issues or challenges during this past quarter; project progress is well ahead of project baseline indicators. | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | Variance due to accelerated construction progress | N/A | N/A | N/A | Variance due to accelerated construction progress | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 30 | 0 | 30 | 1 | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. Variance due to accelerated construction schedule. | N/A | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | Maximum 1 Gbps; No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 1 | N/A | N/A | N/A | N/A | 100 Mbps | N/A | FALSE | N/A | Recipient anticipates 100% completion of the project construction and CAI drops and 100% overall project completion. Over 41 fiber network miles will be placed and 50 CAI's will be connected to the network (upon final agency approval of pending project modification award action requests). | Silver Star Telephone Company, INC. | N/A | Recipient anticipates that project construction will be completed by quarter end and expects to experience no issues or challenges, with the exception of receiving final agency approval of pending project modification award action requests.
NT10BIX5570077 | 2012 | Q3 | Q3 - 2012 | Recipient experienced no issues or challenges during this past quarter; project progress is well ahead of project baseline indicators. | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | Progress is on schedule | N/A | N/A | N/A | Progress is on schedule | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 43 | 0 | 43 | 1 | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. Variance due to accelerated construction schedule. | N/A | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | Maximum 1 Gbps; No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 4 | 0 | 4 | 1 | N/A | N/A | N/A | N/A | 100 Mbps | N/A | FALSE | N/A | Recipient anticipates 100% completion of the project construction and CAI drops and 100% overall project completion. Nearly 42 fiber network miles will be placed and 50 CAI's will be connected to the network. | Silver Star Telephone Company, INC. | N/A | Recipient anticipates that project construction will be completed by quarter end and expects to experience no issues or challenges. Following the construction contract close-out anticipated to be completed by early November, recipient will begin award close-out activities.
NT10BIX5570077 | 2012 | Q4 | Q4 - 2012 | Recipient completed all construction activities contemplated under the grant award and project additions. In fact, Recipient completed the project six months ahead of schedule. The project constructed 42 main fiber cable miles, 4.6 fiber drop miles, and connected 50 CAI's. Project completion resulted in network turn-up, as contemplated under the approved project and additions. Fiber was placed, spliced and tested and the access network was turned up to the CAI's that contracted for service. | 42 | 0 | 0 | 0 | 42 | 0 | 0 | 4 | Variance due to accelerated construction schedule and additional approved construction over the original planned 41 miles. | N/A | N/A | N/A | Variance due to accelerated construction schedule and approved construction of one additional main fiber mile. | N/A | N/A | N/A | 1 | 1 | 80 | Gold Star Communications, LLC (last mile provider) | N/A | N/A | 0 | 1 | 0 | 1 | N/A | Gold Star Communications, LLC | Recipient continues to engage in discussions with providers for potential agreements to dark fiber access. | Available speed tiers are 5Mbps, 10Mbps, 20Mbps, 100Mbps, 1Gbps, OC3, OC12 and OC48. | 50 | 0 | 50 | 9 | CAIs include elementary and secondary education institutions, higher education institutions, several Federal government departments/divisions, Teton County offices and facilities, Town of Jackson offices and facilities, US Post Office buildings, US Forest Service facilities, as well as medical facilities, public safety facilities and community support organizations. Variance due to accelerated construction schedule and additional CAIs under approved construction additions. | N/A | CAIs include elementary and secondary education institutions, higher education institutions, several Federal government departments/divisions, Teton County offices and facilities, Town of Jackson offices and facilities, US Post Office buildings, US Forest Service facilities, as well as medical facilities, public safety facilities and community support organizations. Variance due to accelerated construction schedule and additional CAIs under approved construction additions. | Maximum 1Gbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 11 | 0 | 11 | 3 | N/A | N/A | N/A | N/A | 100 Mbps, N/A | N/A | FALSE |  | The project construction is 100% complete; Recipient will focus on award close-out activities over the next 90 days, anticipating completion of all required close-out activities by March 31, 2012. | Silver Star Telephone Company, INC. | Recipient has completed all construction activities contemplated under the grant award; no challenges or issued were faced in achieving planned progress against the project milestones. In fact, Recipient completed the project six months ahead of schedule. | Not applicable.
NT10BIX5570077 | 2013 | Q1 | Q1 - 2013 | Recipient completed all construction activities contemplated under the grant award and project additions. In fact, Recipient completed the project six months ahead of schedule. The project constructed 42 main fiber cable miles, 4.6 fiber drop miles, and connected 50 CAI's. Project completion resulted in network turn-up, as contemplated under the approved project and additions. Fiber was placed, spliced and tested and the access network was turned up to the CAI's that contracted for service. | 42 | 0 | 0 | 0 | 42 | 0 | 0 | 4 | Variance due to accelerated construction schedule and additional approved construction over the original planned 41 miles. | N/A | N/A | N/A | Variance due to accelerated construction schedule and approved construction of one additional main fiber mile. | N/A | N/A | N/A | 1 | 1 | 80 | Gold Star Communications, LLC (last mile provider) | N/A | N/A | 0 | 1 | 0 | 1 | N/A | Gold Star Communications, LLC | Recipient continues to engage in discussions with providers for potential agreements to dark fiber access. | Available speed tiers are 5Mbps, 10Mbps, 20Mbps, 100Mbps, 1Gbps, OC3, OC12 and OC48. | 50 | 0 | 50 | 9 | CAIs include elementary and secondary education institutions, higher education institutions, several Federal government departments/divisions, Teton County offices and facilities, Town of Jackson offices and facilities, US Post Office buildings, US Forest Service facilities, as well as medical facilities, public safety facilities and community support organizations. Variance due to accelerated construction schedule and additional CAIs under approved construction additions. | N/A | CAIs include elementary and secondary education institutions, higher education institutions, several Federal government departments/divisions, Teton County offices and facilities, Town of Jackson offices and facilities, US Post Office buildings, US Forest Service facilities, as well as medical facilities, public safety facilities and community support organizations. Variance due to accelerated construction schedule and additional CAIs under approved construction additions. | Maximum 1Gbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 11 | 0 | 11 | 3 | N/A | N/A | N/A | N/A | 100 Mbps, N/A | N/A | FALSE |  | The project construction is 100% complete; Recipient will focus on award close-out activities over the next 90 days, anticipating completion of all required close-out activities by March 31, 2012. | Silver Star Telephone Company, INC. | Recipient has completed all construction activities contemplated under the grant award; no challenges or issued were faced in achieving planned progress against the project milestones. In fact, Recipient completed the project six months ahead of schedule. | Not applicable.
NT10BIX5570078 | 2010 | Q4 | Q4 - 2010 | The draft Environmental Assessment was submitted to NTIA on December 16th, ahead of required date of January 3rd. Permitting is coming along well; we have received a Nationwide permit #12 from the Corp of Engineers for crossing the Wetlands, WYDOT has reviewed our permit documents and is processing them for January issue; Teton County is prepared to issue the permit for the limited areas of their jurisdiction that we cross; the US Forest Service and Grand Teton National Park Service will issue permits upon completion of the EA document. Finally, we are in the final stages of entering into a Franchise Agreement with the Town of Jackson, WY. Engineering design and construction documents are approximately 60% complete, including the RUS contract documents and design drawings. An informal pre-bid meeting for potential contractors was held at the Jackson, WY, Town Hall on November 9th 2010. Recipient is still adhering to reporting deadlines. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | NONE | FALSE | N/A | Recipient anticipates 100% completions of construction drawings and the contract package by February 18th. Notice of availability of the OSP Contract is scheduled to be published March 1, 2011. A Pre-bid Meeting is tentatively scheduled for March 15th at the Jackson Town Hall. Finally it is anticipated the Environmental Assessment will be approved and all permits required for the project will be received this quarter. | Silver Star Telephone Company, INC. | NONE | NONE
NT10BIX5570078 | 2011 | Q1 | Q1 - 2011 | The recipient held the Pre-bid meeting on March 17 2011 and it was determined that the bids would be accepted until April 5, 2011 at 2pm at which time they would be publicly opened. OSP design was completed on time and the Transport and Access Engineering was in progress. Recipients AAR for proposed route changes was approved. Finally the recipient's EA was accepted and the FONSI issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | 0 | 0 | 0 | NONE AT THIS TIME | NONE AT THIS TIME | N/A | 0 | 0 | 0 | 0 | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | 0 | 0 | 0 | 0 | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | 0 | 0 | 0 | 0 | 0 | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | 0 | 0 | 0 | 0 | 0 | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NO VARIANCE | NONE | FALSE | N/A | The recipient will award the outside plant construction contracts to the acceptable responsive bidder. It s anticipated that all required permits will be secured to allow construction to start. It is anticipated construction will commence on or before May 2, 2011. The EA SAC will be lifted to permit commencement of construction and receipt of Federal funds. Transport and Access Engineering will be completed. Construction of the fiber and duct system will be in progress. | Silver Star Telephone Company, INC. | NONE | NONE
NT10BIX5570078 | 2011 | Q2 | Q2 - 2011 | The Outside Plant project commenced April 2011 and the contractor has plowed 17.5 miles of conduit from the north end of the Town of Jackson to well inside Grand Teton National Park, completing over 6000' of bores. The contractor has met the Phase I requirement in terms of placing duct to the majority of the Community Anchor Institute properties. A crew is currently working on setting hand-holds, placing equipment, blowing fiber, splicing, testing etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | N/A | FALSE | N/A | It is anticipated that the Outside Plant Project will be 60%complete. Fiber for Phase I will be completed and ready for use by the end of October which will allow up to 15 Community Anchor Institutes to begin receiving services . A crew will begin plowing at the top of Togwotee Pass, working down-hill to tie into the conduit that has been placed to date, thus putting the recipient and project ahead of schedule. $393,000 has been budgeted for Land, Structures, ROW and Appraisals, which includes acquisition costs of land for one building and the construction of two buildings in this figure. We anticipate expending funds in this category during q3 2011 and q4 2011. Systems facilities equipment procurement will commence q3 2011 and will be paid in q4 2011. | Silver Star Telephone Company, INC. | N/A | N/A
NT10BIX5570078 | 2011 | Q3 | Q3 - 2011 | The contractor has placed approximately 21 miles of conduit from Jackson to Shadow Mountain Road inside Grand Teton National Park, and approximately 19 miles of fiber has been placed from Pearl Avenue in downtown Jackson to Craig Head Road on Antelope Flats inside the park. Just over 6000 feet of bores have been completed. The contractor is currently working on splicing the fiber and setting the equipment building in Moose, WY. | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | Work completed, not billed prior to September 30th | N/A | N/A | N/A | Accelerated construction progress | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Before the OSP construction contractor leaves the area for the winter, there will be at least 25 miles of conduit placed. | Silver Star Telephone Company, INC. | N/A | Winter weather will soon delay construction, which will then be halted until sometime in June 2012.
NT10BIX5570078 | 2011 | Q4 | Q4 - 2011 | The contractor has placed approximately 45 miles of conduit from Jackson, Wyoming to the Black Rock Ranger District at the base of Togwotee Pass; approximately 19 miles of fiber have been placed from Pearl Avenue in downtown Jackson to Craig Head Road on Antelope Flats inside Grant Teton National Parkark. The total project miles is 68. The Moose hut has been placed and anchored down. The contractor has completed the splicing on the main cable through phase one to Moose. The contractor has left for the winter and will return next spring to finish up the project. | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | Variance due to construction shut-down as a result of winter season | No variance | No variance | No variance | Variance due to construction shut-down as a result of winter season | No variance | No Variance | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 1 | 1 | 1 | 0 | Variance due to seasonal construction window | Variance due to seasonal construction window | Variance due to seasonal construction window | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Cable and conduit have been placed to three CAI's to date; recipient anticipates facilities testing could be completed and services available in 1q012. Winter weather has halted project construction and it is anticipated to resume in April 2012. | Silver Star Telephone Company, INC. | N/A | N/A
NT10BIX5570078 | 2012 | Q1 | Q1 - 2012 | Project construction halted during the winter months; no significant progress completed during that time. | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | Variance due to construction shut-down as result of winter | No Variance | No Variance | No Variance | Variance due to construction shut-down as a result of winter | No Variance | No Variance | No Variance | 1 | 0 | 80 | Bresnan Communications - last mile provider | N/A | N/A | 0 | 0 | 1 | 1 | No Variance | No Variance | No Variance | 10 Gbps+, dependent on carrier/provider equipment. | 1 | 0 | 23 | 1 | CAI - medical services facility | N/A | CAIs include elementary education entities, several Federal department/division entities, Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | Maximum 1 Gbps; No Variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project construction to resume in April 2012 and project construction is projected to be at least 60% complete. Recipient anticipates deploying 41 miles of network fiber and connecting 45 CAIs. | Silver Star Telephone Company, INC. | N/A | Recipient does not anticipate any challenges or issues that may impact planned progress and expects project construction will meet or exceed approved baseline milestones.
NT10BIX5570078 | 2012 | Q2 | Q2 - 2012 | Recipient experienced no issues or challenges during this past quarter. Recipient and NTIA staff worked together to obtain expedited approval of an 8.5 mile project modification, partially through Grand Teton National Park. Staff of the Park Service, Forest Service and potentially affected state organizations all pulled together to do the work necessary for the approval. The facilities construction resumed in mid-April and the contractor has installed 40 miles of conduit and 49 miles of fiber. Equipment contracts have been awarded. | 19 | 0 | 0 | 0 | 49 | 0 | 0 | 1 | Variance due to installed fiber needing to be spliced prior to equipment placement | No Variance | No Variance | No Variance | Variance result of additional approved miles | No Variance | No Variance | No Variance | 1 | 2 | 80 | Bresnan Communications - last mile provider | Unknown; Bresnan has been asked to provide the requested information which, if received, will be included in the next progress report. | N/A | 0 | 0 | 1 | 1 | No Variance | No Variance | No Variance | 10 Gbps+, dependent on carrier/provider equipment. | 2 | 0 | 2 | 1 | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | N/A | CAI's include elementary education entities, several Federal department/division entities. Teton County, Town of Jackson, US Post Office and US Forest Service entities, as well as medical facilities and community support organizations. | Maximum 1 Gbps; No Variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Recipient anticipates at least 90% overall project completion. Facilities construction and CAI drops will be completed. Recipient anticipates 81 connected CAIs which is dependent upon agency approval of pending modification requests. A majority of the facilities equipment will be installed and equipment testing will begin. | Silver Star Telephone Company, INC. | N/A | Recipient anticipates no challenges or issues that may impact planned progress and expects project construction will meet approved baseline milestones.
NT10BIX5570078 | 2012 | Q3 | Q3 - 2012 | Recipient experienced no issues or challenges during this past quarter; project progress is moving along well to meet next quarter project baseline indicators. | 28 | 0 | 0 | 0 | 75 | 0 | 0 | 1 | Variance due to equipment not yet installed | No Variance | No Variance | No Variance | Variance due to additional approved miles to be constructed | No Variance | No Variance | No Variance | 1 | 2 | 80 | Bresnan Communications - last mile provider | n/a | n/a | 0 | 0 | 1 | 1 | No Variance | No Variance | No Variance | 10 Gbps+, dependent on carrier/provider equipment. | 41 | 0 | 41 | 1 | CAI's include elementary education entities, several Federal departments/divisions, local County offices (Teton County), local Town offices (Jackson), US Postal Service facilities, and US Forest Service facilities, as well as medical facilities and community support organizations. Variance due to accelerated OSP construction schedule. | N/A | CAI's include elementary education entities, several Federal departments/divisions, local County offices (Teton County), local Town offices (Jackson), US Postal Service facilities, and US Forest Service facilities, as well as medical facilities and community support organizations. Variance due to accelerated OSP construction schedule. | Maximum 1 Gbps; No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 2 | 2 | N/A | N/A | N/A | N/A | 100 Mbps | N/A | FALSE |  | Recipient anticipates 100% completion of the project construction and CAI drops and 100% overall project completion. 84 main fiber network miles will be placed and up to 80 CAI's will be connected to the network. | Silver Star Telephone Company, INC. | N/A | Recipient anticipates that project construction will be completed by quarter end and expects to experience no issues or challenges. Following the construction contract close-out anticipated to be completed by year-end, recipient will begin award close-out activities.
NT10BIX5570078 | 2012 | Q4 | Q4 - 2012 | Recipient completed all construction activities contemplated under the grant award and project additions. In fact, Recipient completed project construction six months ahead of schedule. The project constructed 82 main fiber cable miles, 5.65 fiber drop miles, and connected 80 CAI's. Project completion resulted in network turn-up, as contemplated under the approved project and additions. Fiber was placed, spliced and equipment is undergoing final testing so the entire access network can be turned up. | 82 | 0 | 0 | 0 | 82 | 0 | 0 | 3 | Variance due to construction progress. | No Variance | No Variance | No Variance | Variance due to additional approved miles to be constructed. | No Variance | No Variance | No Variance | 1 | 2 | 80 | Bresnan Communications - last mile provider | n/a | n/a | 0 | 0 | 1 | 1 | No Variance | No Variance | No Variance | 10 Gbps+, dependent on carrier/provider equipment | 41 | 0 | 41 | 2 | Variance due to accelerated OSP construction schedule and approved additional construction activities. | N/A | CAI's include elementary education entities, several Federal departments/divisions, local County offices (Teton County), local Town offices (Jackson), US Postal Service facilities, and US Forest Service facilities, as well as medical facilities and community support organizations. Variance due to accelerated OSP construction schedule. | Maximum 1 Gbps; No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 0 | 3 | 3 | N/A | N/A | N/A | N/A | 100 Mbps | n/a | FALSE |  | Recipient anticipates 100% overall project completion and anticipates an early award end date of March 31, 2013, whereupon it will focus exclusively on closeout activities. | Silver Star Telephone Company, INC. | Recipient has completed all construction activities contemplated under the grant award; no challenges or issued were faced in achieving planned progress against the project milestones. | Recipient anticipates no challenges or issues during the next quarter.
NT10BIX5570078 | 2013 | Q1 | Q1 - 2013 | Recipient completed all construction activities contemplated under the grant award and project additions. In fact, Recipient completed project construction six months ahead of schedule. The project constructed 82 main fiber cable miles, 5.65 fiber drop miles, and connected 41 CAI's. Project completion resulted in network turn-up, as contemplated under the approved project and additions. Fiber was placed, spliced and equipment underwent final testing prior to network turn-up. | 82 | 0 | 0 | 0 | 82 | 0 | 0 | 3 | Variance a result of additional approved facilities construction | No variance | No variance | No variance | Variance a result of additional approved facilities construction | No variance | No variance | No variance | 1 | 2 | 80 | Bresnan Communications - last mile provider | n/a | n/a | 0 | 0 | 1 | 1 | No variance | No variance | No variance | 10 Gbps+, dependent on carrier/provider equipment | 41 | 0 | 41 | 2 | Variance due to additional approved facilities construction. | N/A | CAI's include elementary education entities, several Federal departments/divisions, local County offices (Teton County), local Town offices (Jackson), US Postal Service facilities, and US Forest Service facilities, as well as medical facilities and community support organizations. Variance due to additional approved facilities construction. | Maximum 1 Gbps; No Variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 0 | 3 | 3 | N/A | N/A | N/A | N/A | 100 Mbps | N/A | FALSE |  | Recipient will focus exclusively on closeout activities in order to meet the June 30, 2013 closeout deadline. | Silver Star Telephone Company, INC. | Recipient has completed all construction activities contemplated under the grant award; no challenges or issued were faced in achieving planned progress against the project milestones. | Recipient anticipates no challenges or issues during the next quarter as it completes its closeout activities.
NT10BIX5570079 | 2010 | Q4 | Q4 - 2010 | Summary: Primary activities this quarter concentrated on completing project prerequisites and preparations for beginning project construction. Key activities included Award Conditions, draft Environmental Assessment, initial contact with potential providers, final route design, award RFP to build contractor, finalize anchor site list and initiate communications, implement management systems and outreach. Key Milestones: Network Design: Awarded Design/Build Contract to NorthSky Communications, Refined middle mile route design Network Build: 0 Fiber ring; 0 laterals to CAIs (No construction yet) Anchor Sites: Complete Baseline Anchor Site list, refined to 160 sites Agreements: 0 Agreements, Ongoing discussions, outreach to several companies with IRU proposals Site Preparation: None (awaiting FONSI) Rights of Way: Negotiating ROW agreements with RoW owners (cities and Oregon DOT) Permits: Received County Permits, working on required City & Railroad permits Procurement: None (none until after Environmental Approval) Deployment: None (working with Anchor sites on requirements) Network Testing: None Expenditures: No equipment or construction expenses. (none until after Environmental Approval - FONSI). Incurring network Design costs estimated for 4th Quarter of about $78,000 and Staff time of about $69,000. Grant Requirement Activity Detail: Special Award Conditions: Completed or submitted for review all SAC requirements includi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Consistent with Baseline, no construction until FONSI approved. | Consistent with Baseline, no construction until FONSI approved. | Consistent with Baseline, no construction until FONSI approved. | Consistent with Baseline, no construction until FONSI approved. | Consistent with Baseline, no construction until FONSI approved. | N/A | N/A | Consistent with Baseline, no construction until FONSI approved. RECIPIENT NAME:Clackamas, County of AWARD NUMBER: NT10BIX5570079 DATE: 02/07/2011 OMB CONTROL NUMBER: 0660-0037 EXPIRATION DATE: 12/31/2013 | 0 | 9 | 0 | N/A | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entitiesk fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County, however, where the project leases or uses conduit / duct / fiber from third parties, the third parties will typically be responsible for maintaining those assets. | 0 | 0 | 0 | 2 | Consistent with Baseline | Agreements are in process with Clackamas ESD & SandyNet | Agreements are in process with Clackamas ESD & SandyNet | 1 GBPS - Standard for all providers (2 now, 4 possible) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | Construction to begin next quarter after receiving FONSI | Construction to begin next quarter after receiving FONSI | Construction to begin next quarter after receiving FONSI | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Summary: Primary activities next quarter will concentrate on obtaining the FONSI, start construction of Phase 1, final engineering of Phases 2 & 3 communication with all CAIs, and determining changes in Match funding. Key Milestones: Network Design: Finalize detail engineering of Phase 1 & 2, start Phase 3. Develop fiber allocation model & private network design. Network Build: Phase 1 fiber ring build, start laterals to CAIs. Anchor Sites: Refine Phase 1,2,3 final CAI list, perform required Baseline / NEPA amendments Agreements: Complete 2 agreements, continue 4 other discussions, outreach to several companies with IRU proposals Site Preparation: Complete Phase 1 Site preparation Rights of Way: Complete all Phase 1 ROW / Permits, begin Phase 2 ROW / Permits Permits: Complete all Railroad Permits Procurement: All fiber / installation equipment for Phase 1 & 2 Deployment: Build Phase 1 fiber ring, start laterals to CAIs Network Testing: None Expenditures: Phase 1 & 2 Equipment, CAI new network equipment, Phase 1,2,3 Engineering. Grant Requirement Activity Detail: Special Award Conditions: Complete updated Overlap Approved. Baseline: Submit CAI & lateral route amendment. Management: Updated CAI Packet and Agreement form. Environmental Assessment: Receive final NEPA FONSI and construction approval. Outreach: Continue and expand Outreach to CAI, providers and public. Develop and initiate Economic Development Plan in | Clackamas, County of | -Route Design: Given the complexity of the ring and lateral routes, and CAI adjustments, the final design of the route has been and continues to be an issue. The routes of the fiber rings is fairly stable, with only minor adjustments to utilize underground opportunities on long the current aerial route. The current and long term issue will be the required adjustment in CAI connections that will require not only changes in the CAI list but lateral routes as well. The project is working closely with the CAIs to minimize these adjustments, but with so many sites and variables, changes are inevitable requiring amendments to both Baseline and FONSI, as well as close coordination with BTOP. -Local Communication Companies: The project is continuing its outreach efforts to find ways to benefit of these companies and/or utilize joint infrastructure to service CAI sites. Several proposals in the works. -Matching Funds: The grantâ€™s in-kind match was based on 160 anchor sites using required electronic to connect the fiber. However, many sites are forced to use current in place equipment as part of the match. This forces a reduction in the value of their equipment that was to be used as potential match. The project is looking at other sources of match to make up the expected shortfall. The project will need assistance from BTOP to help in the determination and value of valid alternatives. -Environmental Assessment: Given the limited time allotted, delayed procurement of a build contrac | As with the previous quarter, there are several challenges facing the project over the next quarter: -Route Design: Given the large number of Community Anchor Sites and the various issues related to final CAI determination, the final design of the route has been - and continues to be an issue. The Ring route is fairly stable, with only potential adjustments to utilize underground opportunities along the current aerial route. The current and long term issue will be the required adjustment in CAI connections (adjustments in the list due to politics, changing service needs, route issues etc) that will require not only changes in the CAI list but lateral routes as well. The project is working closely with the CAIs to minimize these adjustments, but with so many sites and variables, changes are inevitable requiring amendments to both Baseline and FONSI, as well as close coordination with BTOP. -Matching Funds: The grantâ€™s in-kind match was based on 160 anchor sites using required electronic to connect the fiber. However,given their budget situation, many sites are forced to use existing equipment as part of the match. This forces a depreciated value to be used thus reducing match. The project is looking at other sources of match to make up the expected shortfall. The project will need assistance from BTOP to help in the determination and value of valid alternatives.
NT10BIX5570079 | 2011 | Q1 | Q1 - 2011 | Primary activities this quarter concentrated on preparations for project construction and enhanced communications with project partners and anchor sites. Key activities included: - We refined project management systems - Refined the match portion of the budget to more realistically reflect the value of equipment at anchor sites, made up for that with the addition of the value of the RoW. An Award Action Request has been submitted - in progress. - Received the FONSI, which allowed us to make significant progress on network design - Monitored the start of the WES Intertie construction - Resolved the RUS overlap issue - Continued contact with potential providers; and continued outreach. Key Milestones: Network Design: - We received the FONSI in late January after which crews began fielding routes for the fiber backbone & to CAIs in Phases 1 & 2 - Fielding resulted in necessary changes to routes to anchor sites, design & EA in progress. Network Build: - The WES Sewer Intertie construction began, about 1 mile was constructed, will place 5 miles of conduit for our backbone. - We did not begin any of our own construction, but made significant progress with network design. Anchor Sites: - Completed, then altered, the Baseline Anchor Site list as school closed or combined, reduced CAI count & altered network design. - Deleted 9 anchor sites in Estacada to resolve overlap issue, we are looking to replace them with others. Agr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Consistent with Baseline | N/A | Consistent with Baseline | N/A | Consistent with Baseline | N/A | N/A | Consistent with Baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione (describe your reasons for any variance from the baseline plan or any other relevant information) | 0 | 9 | 0 | No Service Agreements yet, but 7 Non-Disclosure agreements in place. Multiple discussions with local and regional service providers ongoing. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entitiesk fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County, however, where the project leases or uses conduit / duct / fiber from third parties, the third parties will typically be responsible for maintaining those assets. | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 2 due to additional route engineering in dense area. Agreements are in process with Clackamas ESD & SandyNet. | Behind Baseline estimate of 2 due to additional route engineering in dense area. Agreements are in process with Clackamas ESD & SandyNet | 1 GBPS - Standard for all providers (2 now, 4 possible) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | Consistent with Baseline. Construction has just begun. | Consistent with Baseline. Construction has just begun. | Consistent with Baseline. Construction has just begun. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Summary: - Subject to obtaining railroad crossing permits, place all backbone fiber in Phases 1, 2, including 20 miles of what was originally Phase 4 (Sandy to Colton). - Finalize routes and submit revised environmental assessment for review. - Finalize service level agreements and light up anchor sites and customers in Phases 1 and 2. - Finalize network design in Phase 3 and plan the design-build of what was originally the easternmost part of Phase 6 for this summer (Welches to Govt Camp at the crest of the Cascade Mountains). Key Milestones: Network Design: - Finalize detail engineering of Phase 1 & 2, start Phase 3. - Perform required Award Action Request (AAR) and NEPA amendments. - Finalize fiber allocation model & private network design. Network Build: - Complete backbone for Phase 1 and partial Phase 2. - Start laterals to anchor sites for Phase 1 & 2. Anchor Sites: - Refine Phase 1,2,3 anchor site list, perform required AAR and NEPA amendments. Agreements: Continue finalizing service level agreements with anchor sites, and marketing the network to other potential users. Site Preparation: Complete Phase 1 Site preparation and make-ready, start with site preparation for Phase 2. Rights of Way: Continue finalizing RoW agreements with cities Permits: - Complete all Railroad crossing Permits. - Obtain any necessary addenda to the FONSI to cover route and anchor site changes. - Fini | Clackamas, County of | 1. Route changes: As we analyze routes in the field, we discover the need to make route changes, or we find better routes, or we add routes to get to new or replacement anchor sites, etc. Each of these route changes must be requested through Award Action Request (AAR), and we were told we should not pay bills for work on alternate routes until they are approved. This is infeasible for two reasons. First, we must incur expenses to investigate alternative routes before a route can be chosen and requested in AAR (e.g., one area required 4 routes to be analyzed before a clear path was found). Second, contractors and work crews can be idled by even the smallest change, such as awaiting approval for rerouting an aerial fiber path from utility poles in one paved street to utility poles in an adjacent paved street. In addition, it is unclear at to what degree Environmental Assessments (EA) cover de minimus changes, or at what point an addendum to the FONSI requested. Clackamas County respectfully requests the NTIA develop a Best Practice and/or an expedited review process for these de minimus changes to provide grantees quick decisions, and to help keep projects on schedule. 2. Anchor site changes: School district budgets are reducing and schools are merging and closing. We also lost 9 anchor sites due to the grant overlap issue. Locating new anchor sites and designing updates to the fiber allocation plan has delayed the project. 3. S | As with last quarter, the same primary issues are impacting the project and need to be resolved. 1. Route changes: Changes will continue as project proceeds, need stream-lined process to minimize delays and costs. 2. Anchor site changes: With the loss of several CAIs, will proceed with review and proposal to add replacements. Process needs to be stream-lined as possible to minimize delays and costs. 3. Six Union Pacific railroad crossing permits. If permits are still not approved, this will delay several key Middle Mile builds. 4. City ROW will continue to be priority, process is slow and could slow rate of match for the budget. 5. Make-ready on utility poles is slower than anticipated which kept us from staying on schedule in the Baseline. OTHER ISSUES 6. The US Forest Service, while a latter phase, this permit needs to be resolved. 7. Now that many BTOP and BIP projects are ordering fiber, our contractor tells us that fiber deliveries from the vendor have gone from 4 weeks to 8-12 weeks. This could delay construction and connections.
NT10BIX5570079 | 2011 | Q2 | Q2 - 2011 | Key activities included: We made significant progress on the grant filing system, outreach plan, business plan, construction monitoring plan. The request to amend the budget -replacing match from equipment with match from donations of rights-of-way â€“ was approved. Our FONSI was approved. Middle mile construction has begun for Phases 1,2 & 4. We continued outreach by contacting more commercial providers. Key Milestones: Network Design: Backbone network design is nearly complete. Fiber counts are known but route options for one 5 mile section are unknown. Pre-engineering has been completed for about 70% of the poles, 40% of the backbone route and 11% of the CAI sites. Fiber Optic Distribution Units (FODU) are under design for connection of fiber per fiber allocation model. Network Build: WES intertie project construction has begun. Middle Mile of 18.6 miles constructed. Anchor Sites: We continued refining the route and community anchor institutions commit or decline to use the system. Anchor site numbers will also change as new guidance from NTIA for counting them is applied. Agreements: The service level agreement draft is complete, to be reviewed by the County Attorney and possible County Commissioners next quarter. Negotiations continue to ebb and flow with private telecom providers. Site Preparation: We have collected site data for 45% of the anchor sites, and 11% have had all pre-engineering completed. 72% of the utility po | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 1 | Consistent with Baseline | N/A | Consistent with Baseline | N/A | Consistent with Baseline | N/A | N/A | Consistent with Baseline (County Development Service Buldingy Development Service Bulding) | 0 | 9 | 0 | No Service Agreements yet, but 7 Non-Disclosure agreements in place. Multiple discussions with local and regional service providers ongoing. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entitiesk fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with several local providers. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with several local providers. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | Under projected 26 baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. Several sites are already wired but cannot be connected until Fiber Optic Distribution Units are connected and Service Agreements signed - in progress. Should be significant progress next quarter. | Consistent with Baseline. Construction has just begun. | Under projected 26 baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. Several sites are already wired but cannot be connected until Fiber Optic Distribution Units are connected and Service Agreements signed - in progress. Should be significant progress next quarter. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key activities expected summary: Expect significant construction progress in Phases 1,2 and 4 with 3 also starting. Includes 47 additional miles of construction. Expect CAI Service Level Agreement to be ready, submission of Action Award Request for route changes and escalation of CAI connections. Key Milestones: Network Design: Expect completion of Phase 1 - 4 backbone design. Design of Fiber Optic Distribution Units (FODU) complete and partial installation at 2 County Sites. Submit Award Action Request for Route Change for Phases 1 - 4. Network Build: Expect an additional 47 miles of construction. Includes Phase 1 - 4 Middle Mile and progression with laterals in Phase 1 and 2. Anchor Sites: We continued refining the route and community anchor institutions commit or decline to use the system. Anchor site numbers will also change as final network design is completed. Expect progress in completing laterals in Phases 1-2 when Award Action Request for route change is approved. Agreements: Expect CAI Service Level Agreement to be approved and to begin obtaining signatures with CAI sites. Will continue to negotiate with providers and expect to obtain several draft agreements. Site Preparation: Continue CAI site preparation in Phases 1-2 and review of CAI sites in Phase 3-4, continue pole pre-engineering and make-ready. However, utility pole preparation (â€œmake-readyâ€) is progressing slowly. Rights of Way: Goal to complete neg | Clackamas, County of | 1. Route changes: The basic backbone route has not been changed. As we analyze routes in the field, we occasionally discover the need to make route changes, or we find better routes. Each of these route changes must be requested through Award Action Request (AAR) with an associated Environmental Assessment amendment. This process inherently causes delays in progress. 2. Anchor site changes: The overall targets will be met, but there are changes as new sites want to be connected and other sites cannot find it in their budgets to connect. The exact number of anchor sites is expected to be greater than projected given the new counting methodology received from the NTIA in June. 3. Railroad crossing permits continue to be an issue. They are slow in coming, and indemnification requirements from a local short line are unacceptable because they require the County to indemnify them completely even for their own, sole negligence. As a local government we are not sure if we can legally agree to that. 4. Cities have been more deliberate than expected in regards to resolving generic issues about the Countyâ€™s right to own a fiber system in their RoWs (aka franchising issues), but permits from city Transportation Departments have been smooth. 5. Make-ready on utility poles is slower than anticipated which kept us from staying on schedule in the Baseline. Some of this may be attributable to the fact that Qwest was just sold to CenturyLink, and Qw | 1. Route changes: Changes will continue as project proceeds, need stream-lined process to minimize delays and costs. 2. Anchor site and lateral changes: BTOP environmental review and AAR processes for approvals should be streamlined to expedite minor changes to minimize delays and costs. 3. Union Pacific and P&W (local shortline) railroad crossing permits. If permits are still not approved, this will delay several key Middle Mile builds. 4. City ROW will continue to be priority, process is slow and could slow rate of match for the budget. 5. Make-ready on utility poles is slower than anticipated which kept us from staying on schedule in the Baseline. OTHER ISSUES 6. The US Forest Service issued the permit, but says we will have to pay $7,000 per year for it once any commercial provider leases fiber through the forest. BTOP can help resolve this issue.
NT10BIX5570079 | 2011 | Q3 | Q3 - 2011 | Key activities included: We continued outreach by contacting more commercial providers as well as meeting with additional community anchor institutions. Construction of phases 2 and 4 continued and we started construction on phase 3. Fiber Optic Distribution Units (FODU) were ordered and will be installed in the county Development Services Building and the North Station locations in Q4. Key Milestones: Network Design: Overall network design is at 83% completion. Fiber counts are known, but route options for Highway 26 and the City of Canby are undecided. Pre-engineering has been completed for about 87% of the poles, 94% of the backbone route and 60% of the anchor site sites. Fiber Optic Distribution Units (FODU) have been ordered. Network Build: Middle Mile of 31 miles constructed during Q3. Anchor Sites: We continued refining the route and the overall count of community anchor institutions. Anchor site numbers will continue to change as new guidance from NTIA for counting them is applied. Agreements: The Service Level Agreement draft is complete, to be reviewed by the County Attorney and possibly County Commissioners. Negotiations continue to ebb and flow with private telecom providers. Site Preparation: 60% of all pre-engineering for last mile for anchor sites has been completed. 87% of the utility poles have been pre- engineered, and about 72% of all necessary pole attachment permits have been approved. 55% of all â€œmake-readyâ€ attachments have | 44 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. | N/A | N/A | N/A | Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. | N/A | N/A | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. Consistent with Baseline (County Development Service Buildings for any variance from the baseline plan or any other relevant information) Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. Under project Baseline of 30% (54 miles) but will be rapidly making up the Middle mile construction this next quarter and be close to baseline projections. Consistent with Baseline (County Development Service Building) | 0 | 9 | 0 | No Service Agreements yet, but 7 Non-Disclosure agreements in place. Multiple discussions with local and regional service providers ongoing. Developing Wholesaler SLA and should have 2 agreements in place for providing service by 2012 Q1. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entitiesk fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas ESD & SandyNet expected to be completed by 2012 Q1. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas ESD & SandyNet expected to be completed by 2012 Q1. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | Under projected 74 baseline - due to delays from Portland General Electric make-ready, RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next several quarters. Several sites are already wired but cannot be connected until Fiber Optic Distribution Units are connected and Service Agreements signed - in progress. | Consistent with Baseline. Construction has just begun. | Under projected 74 baseline - due to delays from Portland General Electric make-ready , RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. Several sites are already wired but cannot be connected until Fiber Optic Distribution Units are connected and Service Agreements signed - in progress. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key activities expected summary: Expect construction completion in Phases 2 and 3 of the backbone fiber totaling 25 miles of construction. Expect anchor site Service Level Agreement to be ready and 10 SLAâ€™s signed by end of Q4. Submission of Action Award Request for route changes, escalation of anchor site connections with the installation of Fiber Optic Distribution Units (FODU) in the county Development Services Building and North Station locations and construction of 6 miles of lateral connections. Key Milestones: Installation of the Fiber Optic Distribution Units (FODU) in 2 of the 3 HUBâ€™s (County Development Services Building and North Station). Connect and light the first 14 anchor siteâ€™s. Network Design: Expect completion of Phase 5 backbone design. Significant progress expected on last mile and anchor site design for Phases 4 and 5. Network Build: Expect an additional 31 miles of construction, including completion of Phases 2 and 3 Middle Mile, and progression with Phase 6 for a total of 75 miles. With the installation of 2 of the Fiber Optic Distribution Units (FODU), we plan to connect 14 anchor sites. Network Leased: 0 - No plans to lease any fiber at this time. Anchor Sites: We will continue to refine the route and community anchor institutions, including securing signed Service Level Agreementâ€™s for use of the system. Anchor site numbers will also change as final network design is completed. Expect rapid progress in complet | Clackamas, County of | 1 Route changes: The basic backbone route has not been changed with the exception of our fiber route through the City of Canby and a potential change on Highway 26. As we analyze routes in the field, we occasionally discover the need to make route changes, or we find better routes. Each of these route changes must be requested through Award Action Request (AAR) with an associated Environmental Assessment amendment. This process inherently causes delays in progress. 2. Anchor site changes: The overall targets will be met, but there are changes as new sites want to be connected and other sites cannot find it in their budgets to connect. The exact number of anchor sites is expected to be greater than projected given the new counting methodology received from the NTIA in June. 3. Railroad crossing permits have been approved for all crossings in the City of Milwaukie and our contractor has completed all work necessary to cross the railroad tracks. With the approved route change through the City of Canby, any further railroad permits may be eliminated. 4. Cities have been more deliberate than expected in regards to resolving generic issues about the Countyâ€™s right to own a fiber system in their RoWs (aka franchising issues), but permits from city Transportation Departments have been smooth. 5. Make-ready on utility poles, particularly in the City of Milwaukie, is slower than anticipated which kept us from staying on schedule in the Base | 1. Route changes: Finalizing the backbone route for Mt. Hood spur and the route through the City of Canby. 2. Anchor site and lateral changes: BTOP environmental review and Action Award Review processes will be filed to reflect all changes. 3. City RoW will continue to be priority, process is slow and has delayed construction. 4. Make-ready on Portland General Electric utility poles in the City of Milwaukie is slower than anticipated which has kept us from staying on schedule in the Baseline. 5. The US Forest Service issued the permit, but says we will have to pay $7,000 per year for it once any commercial provider leases fiber through the forest. The issue continues to be reviewed.
NT10BIX5570079 | 2011 | Q4 | Q4 - 2011 | Key activities included: We continued outreach by contacting more commercial providers as well as meeting with additional community anchor institutions. Backbone Mile construction of 14.5 miles of Phase 3 was completed. Roughly 4.5 miles of backbone mile construction was completed in phase 6. Two miles of lateral mile fiber were constructed in Phase 3. We received the shipment of Fiber Optic Distribution Units (FODUs) and completed installation in our three main hubs. Key Milestones: Network Design: Overall network design is at 86% completion. Fiber counts are known, but final route options from Molalla through Oregon City are undecided. Pre-engineering has been completed for about 95% of the poles, 96% of the backbone route & 74% of the anchor sites. Network Build: 21 miles constructed during Q4. Anchor Sites: Continued refining lateral mile routes and overall count of community anchor institutions resulting in a finalized â€˜baselineâ€™ list against which all changes will be documented. The total number of CAIâ€™s may change due to uncertainty around the City of Oregon City. Agreements: The Service Level Agreement template for dark fiber service was completed and staff began sending them out for signatures in December. Because the backbone rings are over 50% complete, negotiations with private telecom providers are on the upswing and we signed another nondisclosure agreement with another telecom carrier. Site Preparation: 74% of all pre-engineering for lateral mile construction to anchor sites has been completed. 95% of the utility poles have been pre- engineered, and about 87% of all necessary pole attachment permits have been approved. 56% of all â€œmake-readyâ€ attachments have been completed. Rights of Way (RoW): Most of the backbone route follows state highway RoW, and that authority has been secured. We are negotiating final details with the City of Milwaukie for necessary RoW access and expect a final agreement in early February. We have contacted the City of Canby to secure RoW access. We have been unable to reach a financially sustainable agreement with the City of Oregon City and are planning to traverse the city without using its RoW. Permits: We have submitted 95% of the needed pole attachment permit applications and have received 83% of the necessary permits. We received a permit from US Forest Service, but it must be amended. Procurement: Fiber is being delivered in a timely fashion and some deliveries are ahead of schedule. Delivery for new fiber that was not included in pre-orders will take up to 45 weeks to receive. Network Testing: No testing has been done due to the very recent delivery and installation of the Fiber Optic Distribution Units. Grant Requirement Activity Detail: Special Award Conditions: Completed or submitted all Special Award Condition requirements. Baseline: Baseline reflected planned anchor sites and lateral routes as of submission date. Some changes in both sites and routes are expected as agreements for city RoW are finalized and final design is achieved. Any necessary changes will be coordinated with NTIA through the Award Action Request process. Desk Audit: All requirements completed. Environmental Assessment (EA): The Environmental Assessment has been completed for the entire project with the exception of the route on Highway 26. An EA amendment will be prepared and submitted as part of route change request. Outreach: We continued implementing our Outreach and Communications Plan during Q4. Website is updated regularly and the second quarterly newsletter will be distributed in late-January. Anchor sites are now requesting additional sites be connected, and we are working with our budget and theirs to plan connections as we find it prudent to do so. We continue to meet with key anchor sites such as fire and school districts, libraries, and cities. Construction Support Detail Proposed Route: Continued refinement and design of fiber optic routes (Molalla to Oregon City). The general route continues to be followed, but field discoveries and denials of reasonable access to RoW require some adjustments. Fiber Allocation Plan: Fiber allocation plans have been completed for laterals to anchor sites for construction phases 1, 2, 3 and 6. Phases 4 and 5 final routes are under general design. Anchor Sites: Laterals to anchor sites in Phases 1, 2, 3 and 6 have been designed. Communication with each anchor site is in progress including negotiating Service Level Agreements with roughly half of the anchor sites. Completion of laterals and on-site connections cannot occur until Service Level Agreements are signed. Service Providers: We continued discussions with potential service providers, signed another nondisclosure agreement, and made further contacts with incumbents CenturyLink/Qwest and Comcast. Project Management: Continue to refine project management elements including final budget, reporting & contracts. Design/Build Contractor: Backbone design is on schedule with the exception of the route from Molalla through Oregon City. Expenditures: Construction and design expenditures were $1,063,746 for a project total of $3,681,169 which represents 33% of the overall $11,148,830 project budget. Staff time of $36,106. Construction Activities: We completed construction of 19 backbone miles and 2 miles of laterals for a total of 21 miles of fiber placed. We installed 3 Fiber Optic Distribution Units. | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 3 | Over projected baseline of 62 miles. | N/A | N/A | N/A | Over projected baseline of 62 miles. | N/A | N/A | Over projected baseline of 1 new interconnection point. | 0 | 5 | 0 | No Service Agreements yet, but there are 8 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | Under projected 106 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 158 CAIs to be served by the end of June 2013 . This adjustment will be reflected in an AAR we plan to submit in February 2012. | Consistent with Baseline | Under projected 106 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 158 CAIs to be served by the end of June 2013. This adjustment will be reflected in an AAR we plan to submit in February 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Number of signed agreements with broadband wholesalers or last mile providers: None Network Design: Once a decision has been reached regarding the fiber route through or around Oregon City, we expect completion of Phase 5 backbone and anchor site design. Once this and the route to Mt Hood are determined Network Design will be complete. Network Build: Expect an additional 35 miles of construction, 10 signed Service Level Agreements, and 50 CAIs connected. Anchor Sites: 10 signed Service Level Agreements and 50 CAIs connected. We expect rapid progress in completing laterals in Phases 2 and 3 once Award Action Request for route change is approved. Agreements: We expect 10 Service Level Agreements to be signed by Community Anchor Institutions (CAIs). Site Preparation: Continue anchor site preparation in Phases 2, 3 and 6. Continue review of anchor sites in Phases 1 and 5. Rights of Way: Our goal is to complete negotiations with 1 additional city on RoW permitting/franchising, bringing the total to 7 of 9. Permits: Amend US Forest Service and Oregon Department of Transportation permits for the Mt. Hood spur through the National Forest. Procurement: All fiber for 2012 was pre-ordered in 2011. We have not had any delivery delays, and in fact some orders have been early, so we do not expect any delays. Network Testing: All fiber reels are tested twice: once upon receipt and again after installation. We expect to complete testing of all fiber connections between our three hub sites –the County’s Development Services Building, North Station, and the City of Sandy. Grant Requirement Activity Detail Baseline: Will complete and submit design and Environmental Assessment for final route changes including updated anchor site list. Environmental Assessment: Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. Complete and submit required Environmental Assessment amendment as part of Award Action Request for route change, both in the backbone and lateral routes. Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail Route: Continued refinement and design of fiber optic routes once the issues regarding Oregon City Right of Way are resolved. Complete construction of backbone route in Phase 2 and continue backbone construction of Phases 4 and 6. Begin construction of lateral routes for Phases 2, 3 and 6. Finalize route change through Oregon City, Canby and to Mt Hood. Fiber Allocation Plan: 86% complete. Fiber laterals to anchor sites for construction phases 2, 3, 4 and 6 will be complete and submitted for Award Action Request Route Change approval. Anchor Sites: Plan to connect to at least 25 anchor sites. Budget: We are continuously working with our contractor to ensure the project is on budget. We just received the budget detail for the proposed changes that will be submitted in the next AAR and it demonstrates that the project is within budget. Expenditures: Construction and design expenditures expected $1,532,000.00 ($500,000 of billings per month) and staff time of $36,000.00. Construction Activities: Projected placement of 35 additional miles of fiber. Construction of the Highway 26 spur to Government Camp has been pushed out to the spring of 2013 due to a Portland General Electric (PGE) project to replace power poles over a 5 mile stretch along Highway 26 at the end of 2012. Once the PGE project has been completed, we will be able to install our final middle mile route to Government Camp. We plan to complete installation of the final 5 miles during Q2 2013. | Clackamas, County of | 1. Oregon City We have encountered RoW permitting challenges with Oregon City. Negotiations continue; however, we are working on an alternate route around Oregon City if efforts are not successful in addressing this issue in a manner that doesnâ€™t threaten sustainability. This re-route would require NTIA review and approval via an Award Action Request (AAR). 2. Highway 26-Mt Hood The last 10 miles of this route segment is off-road and in difficult terrain that rises from 1,400 to 4,000 feet. The electric utility recently informed us that there is a 6 mile stretch where they will be relocating their poles by the end of 2012, and another 2.3 mile stretch where we cannot attach to the poles. In Q4 we determined that there is no conduit or interdict space available from others for the entire stretch. We are working with USFS and Oregon DOT on other options. | The issues we are having have been documented above and should be resolved to the point where we expect to make rapid progress and catch up with the original baseline and milestones and metrics in the next two quarters. We have arranged for up to 4 construction crews to work simultaneously in this regard.
NT10BIX5570079 | 2012 | Q1 | Q1 - 2012 | Key Activities: We continued outreach by contacting more commercial providers as well as meeting with additional community anchor institutions. Backbone Mile construction of 26 miles and roughly 12 miles of lateral mile construction was completed in Q1 2012. A total of 39 anchor sites were connected. The 3 HUB locations were finalized and the fiber testing between the HUBS completed. We have submitted and are waiting for the approval of an AAR that updates the anchor site list as well as any route refinements. Overall project is 68% complete, ahead of the 06/30/2012 substantial completion target. Key Milestones - Network Design: The phase 5 route is still undecided and the design crew is in the field finalizing the pole and underground routes. - Anchor Sites: Our contractor physically connected to 28 anchor sites in Q1 2012. Another 11 anchor sites realized improved broadband service to the other anchor sites. Total anchor sites connected for Q1 2012 is 39. - Agreements: 10 Service Level Agreements were signed during Q1 2012. The 10 SLAâ€™s represent 65 anchor sites that can be connected to the fiber network. - Site Preparation: 80% of all engineering for lateral mile construction to anchor sites has been completed. 96% of the utility poles have been pre-engineered and about 84% of all necessary pole attachment permits have been approved. 65% of all â€œmake-readyâ€ attachments have been completed. - Rights of Way (RoW): We successfully negotiated a RoW agreement with the City of Milwaukie. We have now secured 7 of the 9 city RoW agreements for this project. We are negotiating final details with other municipalities. - Permits: We have submitted 99% of the needed pole attachment permit applications and have received 86% of the necessary permits. We have amended the USFS permit that will allow our contractor to continue construction on the Government Camp spur during the summer months. - Procurement: Fiber is being delivered in a timely fashion and some deliveries are ahead of schedule. Delivery for new fiber that was not included in pre-orders will take up to 45 weeks to receive. - Network Testing: Final testing of the installed fiber has occurred between the 3 HUB locations. With the backbone fiber tested between the three HUBS, any anchor site that is connected can be tested. Grant Requirement Activity Detail - Special Award Conditions: Completed or submitted all Special Award Condition requirements. - Baseline: Baseline reflected planned anchor sites and lateral routes as of submission date. We anticipate the approval of a route change Award Action Request submitted in March 2012. Once we receive the approval of this Award Action Request, we will update the baseline numbers. Any future changes will be coordinated with NTIA through the Award Action Request process. - Desk Audit: All requirements completed. - Environmental Assessment (EA): The Environmental Assessment has been completed and submitted for the Award Action Request in Q1 2012. Environmental work continues for a future modification on HWY 26 part of the Government Camp 144 fiber spur. An EA amendment will be submitted as part of route change request. - Outreach: We continue implementing our Outreach and Communications Plan during Q1, 2012 with new interest from new telecom providers. Website is updated regularly and the quarterly newsletter will be distributed in early May. New local organizations are showing interest in the fiber network with the news of the first anchor sites connected. Construction Support Detail - Proposed Route: Refinement to the design of fiber optic routes continued in Q1 2012. The general route continues to be followed, but field discoveries and denials of reasonable access to RoW require some adjustments. Any variations to the baseline route will be submitted via the Award Action Request process. - Fiber Allocation Plan: Fiber allocation plans have been completed for laterals to anchor sites for construction phases 2, 3, 4 and 6. - Anchor Sites: 10 Service Level Agreements (SLA) were received in Q1, 2012. With the signed SLA, our contractor was able to connect 39 anchor sites. - Service Providers: Discussions with potential service providers continue. We have seen a renewed interest in the fiber network from telecom providers as word spreads about the approaching completion date. - Project Management: Continue to refine project management elements including final budget, reporting & contracts. - Design/Build Contractor: No issues. All work appears timely and on budget. 62% of the fiber network has been built. - Expenditures: Construction and design expenditures were $4,992,466 which represents 45% of the overall $11.1 million project budget. Staff time of $29,288. - Construction Activities: We completed construction of 26 backbone miles and 12 miles of laterals for a total of 38 miles of fiber placed. | 103 | 0 | 0 | 0 | 103 | 0 | 0 | 3 | Over projected baseline of 89 miles. | N/A | N/A | N/A | Over projected baseline of 89 miles. | N/A | N/A | Meeting baseline of 3 new interconnection points. | 0 | 7 | 0 | No Service Agreements yet, but there are 9 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 39 | 0 | 39 | 0 | Under projected 129 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 158 CAIs to be served by the end of Q2 2013. This adjustment is reflected in the Award Action Request we submitted in February 2012. | Consistent with Baseline | Under projected 129 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 158 CAIs to be served by the end of Q2 2013. This adjustment is reflected in the Award Action Request we submitted in February 2012. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key activities expected summary: Construct 37 new route miles bringing the total fiber build to 140 miles. Total backbone constructed to 112 of 125 miles (90%), and 28 out of 42 lateral miles (66%). Connect another 73 anchor sites bringing the total to 112. Expect to have 5 SLAâ€™s signed bringing the total to 15. Finalize route for phase 5. Key Milestones: 1. New Network Miles Deployed: Expect to construct an additional 37 route miles. 2. New Network Miles Leased: None 3. Total CAI Subscribers Served: Expect to have 5 signed Service Level Agreements returned. 4. Number of signed agreements with broadband wholesalers or last mile providers: None - Network Design: We expect the completion of Phase 5 backbone and anchor site design. Once this and the route to Mt Hood are determined, network design will be complete. - Network Build: We expect an additional 37 miles of fiber construction in Q2 2012. - Anchor Sites: We expect 73 anchor sites connected in Q2 2012. This will bring the total to 112 for the project. - Agreements: We expect 5 Service Level Agreements to be signed by Community Anchor Institutions giving the project a total of 15 SLAâ€™s signed. - Site Preparation: Continue review of anchor sites in Phases 1 and 5. - Rights of Way: Our goal is to complete negotiations with 1 additional city on RoW permitting/franchising, bringing the total to 8. - Permits: Amend US Forest Service & Oregon Department of Transportation permits for Mt. Hood spur through the National Forest. - Procurement: All fiber for 2012 was pre-ordered in 2011. We do not expect any fiber delays. - Network Testing: All fiber reels are tested twice: once upon receipt and again after installation. All three HUBâ€™s are connected and tested and as we connect anchor sites, we will test the connection to the other termination point. Grant Requirement Activity Detail - Baseline: Waiting for approval of Award Action Request submitted in March, 2012. Once we receive the approval for the Award Action Request, we will update our baseline numbers. - Environmental Assessment: Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. - Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail - Route: Continued refinement and design of fiber optic routes once we have reached an agreement with all municipalities. Phases 1 â€“ 4 backbone construction is complete. By the end of Q2 2012, phase 6 will be 70% complete and phase 5 will be 22% complete. - Anchor Sites: Plan to connect to 73 anchor sites. - Budget: We are continuously working with our contractor to ensure the project is on budget. We received the budget detail for the Award Action Request submitted in February 2012 Award Action Request and it demonstrates that the project is within budget. - Expenditures: Construction and design expenditures expected to be about $1,100,000.00 ($366,000 of billings per month) and staff time of about $30,000.00. - Construction Activities: Projected placement of 37 additional miles of fiber. Completion of the Highway 26 spur to Government Camp has been pushed out to the spring of 2013 due to a Portland General Electric (PGE) project to replace power poles over a 5 mile stretch along Highway 26 at the end of 2012. Once the PGE project has been completed, we will be able to install our final middle mile route to Government Camp. We plan to complete installation of the final 5 miles during Q2 2013. | Clackamas, County of | 1. RoW Issues We have encountered RoW permitting challenges. Negotiations continue; however, we are working on an alternate route around if efforts are not successful in addressing this issue in a manner that doesnâ€™t threaten stainability. This re-route would require NTIA review and approval via an Award Action Request (AAR). 2. Highway 26-Mt Hood The last 10 miles of this route segment is off-road and in difficult terrain that rises from 1,400 to 4,000 feet. The electric utility recently informed us that there is a 3.7 mile stretch where they will be relocating their poles by the end of 2012, and another 2.3 mile stretch where we cannot attach to the poles. We are working with USFS to determine the best route through this 2.3 mile stretch that will not negatively impact the surrounding environment. We expect a solution to this segment by the end of Q2 2012 and then we will submit an Award Action Request for this route change. | The issues we are having have been documented above and should be resolved to the point where we expect to make rapid progress and catch up with the original baseline and milestones and metrics in the next two quarters. We have arranged for up to 4 construction crews to work simultaneously in this regard.
NT10BIX5570079 | 2012 | Q2 | Q2 - 2012 | Key Milestones - Anchor Sites: Our contractor physically connected to 29 anchor sites in Q2 2012. Another 8 anchor sites realized improved broadband service to the other anchor sites. Total anchor sites connected by the end of Q2 2012 is 76. - Agreements: 3 Service Level Agreements were signed during Q2 2012 bringing the project total to 13 signed SLAâ€™s. The 13 SLAâ€™s represent 79 anchor sites along with 52 county sites brings the total count to 131 sites that can be connected to the fiber network. - Permits: We have submitted 99% of the needed pole attachment permit applications and have received 88% of the necessary permits. We have received approval for the amended USFS permit that will allow our contractor to continue construction on the Government Camp spur during the summer months with the exception of a 4 mile section. This 4 mile section is held up due to a relocation project Portland General Electric is performing during the summer and fall of 2012. Grant Requirement Activity Detail - Baseline: The baseline route is a culmination of the grant application and the 2 approved Award Action Requests. Any future changes will be coordinated with NTIA through the Award Action Request process. - Environmental Assessment (EA): The environmental assessment is complete for the county fiber network. Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. - Outreach: We continue implementing our Outreach and Communications Plan during Q2, 2012 with new interest from new telecom providers. New local organizations are showing interest in the fiber network with the news of the first anchor sites connected. Construction Support Detail - Proposed Route: Refinement to the design of fiber optic routes continued in Q2 2012. The general route continues to be followed, but field discoveries and denials of reasonable access to RoW require some adjustments. Any variations to the baseline route will be submitted via the Award Action Request process. - Service Providers: Discussions with potential service providers continue. We have seen a renewed interest in the fiber network from telecom providers as word spreads about the approaching completion date. - Expenditures: Construction and design expenditures were $5,973,964 which represents 54% of the overall $11.1 million project budget. The construction and design expenditures represent 77% of the $7.8 million dollar grant budget exceeding the 2/3 requirement for substantial completion. Staff time of $29,288. - Construction Activities: We completed construction of 18 backbone miles and 14 miles of laterals for a total of 32 miles of fiber placed during Q2 2012. | 135 | 0 | 0 | 0 | 135 | 0 | 0 | 3 | Over projected baseline of 117 miles. | N/A | N/A | N/A | Over projected baseline of 117 miles. | N/A | N/A | Meeting baseline of 3 new interconnection points. | 0 | 9 | 0 | No Service Agreements yet, but there are 9 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. | This project only provides dark fiber. No lit services will be provided. No service agreements have been signed. The project anticipates pricing plan of dark fiber pairs at $250/month for government agencies and non-profits, and $1000/month for commercial entities. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 76 | 0 | 76 | 0 | Under projected 154 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 166 CAIs to be served by the end of Q3 2013. This adjustment is reflected in the Award Action Request we submitted in February 2012. | Consistent with Baseline | Under projected 154 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now project a total of 166 CAIs to be served by the end of Q3 2013. This adjustment is reflected in the Award Action Request we submitted in February 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key activities expected summary: Construct 23 new route miles bringing the total fiber built to 158 miles with the 4 miles of the Portland General Electric reliability project and 5 miles in Canby left to complete. Total backbone constructed to 120 of 125 miles (96%), and 38 out of 42 lateral miles (90%). Connect another 69 anchor sites bringing the total to 145. Expect to have 4 SLAâ€™s signed bringing the total to 17. Key Milestones: 1. New Network Miles Deployed: Expect to construct an additional 23 route miles. 2. New Network Miles Leased: None 3. Total CAI Subscribers Served: Expect to have 4 signed Service Level Agreements returned. 4. Number of signed agreements with broadband wholesalers or last mile providers: Expect to have 4 signed agreements with last mile providers. - Network Design: The network design will be complete with the exception of the 4 mile Portland General Electric reliability project. - Rights of Way: Our goal is to complete negotiations with 1 additional city on RoW permitting/franchising, bringing the total to 8. - Permits: Amend US Forest Service and Oregon Department of Transportation permits for the Mt. Hood spur through the National Forest. - Procurement: All fiber required for this project has been received. - Network Testing: All fiber for this network will be tested with the exception of the fiber east of the Portland General Electric reliability project on Mt Hood and the fiber in the City of Canby. Grant Requirement Activity Detail: - Environmental Assessment: Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. - Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail - Route: The fiber network will be fully designed by the end of Q3, 2012. - Budget: We are continuously working with our contractor to ensure the project is on budget. - Expenditures: Construction and design expenditures expected to be about $1,200,000.00 ($400,000 of billings per month) and staff time of about $30,000.00. - Construction Activities: Projected placement of 23 additional miles of fiber. Completion of the Highway 26 spur to Government Camp has been pushed out to the spring of 2013 due to a Portland General Electric project to replace power poles over a 4 mile stretch along Highway 26 at the end of 2012. Once the PGE project has been completed, we will be able to install our final middle mile fiber to Government Camp. We plan to complete installation of the final 4 miles during Q2 2013. | Clackamas, County of | 1. RoW Issues We have encountered RoW permitting challenges. Negotiations continue; however, we are working on an alternate route around if efforts are not successful in addressing this issue in a manner that doesnâ€™t threaten sustainability. This re-route would require NTIA review and approval via an Award Action Request (AAR). 2. Highway 26-Mt Hood The last 10 miles of this route segment is off-road and in difficult terrain that rises from 1,400 to 4,000 feet. The electric utility recently informed us that there is a 3.7 mile stretch where they will be relocating their poles by the end of 2012, and another 2.3 mile stretch where we cannot attach to the poles. We are working with USFS to determine the best route through this 2.3 mile stretch that will not negatively impact the surrounding environment. We expect a solution to this segment by the end of Q3 2012 and then we will submit an Award Action Request for this route change. | The issues we are having have been documented above and should be resolved to the point where we expect to make rapid progress and catch up with the original baseline and milestones and metrics in the next two quarters. We have arranged for up to 4 construction crews to work simultaneously in this regard.
NT10BIX5570079 | 2012 | Q3 | Q3 - 2012 | Key Milestones - Anchor Sites: Our contractor physically connected to 20 anchor sites in Q3 2012. Another 12 anchor sites realized improved broadband service to the other anchor sites. Total anchor sites connected by the end of Q3 2012 are 108. - Agreements: 2 Service Level Agreements (SLA) were signed during Q3 2012 bringing the project total to 15 signed SLAâ€™s. The 15 SLAâ€™s represent 86 anchor sites along with 52 county sites brings the total count to 138 sites that can be connected to the fiber network. We have received another SLA that is slowly making its way through legal review. - Permits: With the approval of the Highway 213 Award Action Request (AAR), we have 3,389 approved Portland General Electric pole permits out of 3,540, or 96% of the Portland General Electric permits have been approved. The last 4 mile section of Highway 26 is under construction by Portland General Electric and once they finish construction, we will submit our approval from the US Forest Service for attaching to the new poles. With the approval from the US Forest Service, we will issue a new AAR for HWY 26. Grant Requirement Activity Detail - Baseline: The baseline route is a culmination of the grant application and the 3 approved route AARâ€™s. Any future route changes will be coordinated with the NTIA through the AAR process. - Environmental Assessment (EA): The environmental assessment is complete for the county fiber network, with the exception of the Portland General Electric reliability project located on Mt Hood. Environmental monitoring continues by the contractor pursuant to procedures established in the Field Manual. - Outreach: We continued implementing our Outreach and Communications Plan during Q3, 2012 with new interest from new telecom providers. New local organizations are showing interest in the fiber network with the news that both fiber rings are nearing completion. Construction Support Detail - Proposed Route: Refinement to the design of fiber optic routes continued in Q3 2012 with the approval of the Molalla to Oregon City AAR. The general route continues to be followed, but field discoveries and denials of reasonable access to RoW require some adjustments. Any variations to the baseline route will be submitted via the AAR process. - Service Providers: Discussions with potential service providers continue. Several service providers are anxiously waiting for the completion of our two fiber rings. With the approval of the most recent AAR, we anticipate closing both rings by the end of November 2012 and signing on our first service provider. - Expenditures: Project to date construction and design expenditures are $6,768,419 which represents 61% of the overall $11.1 million project budget. The project to date construction and design expenditures represents 87% of the $7.8 million dollar grant budget. Staff time of $35,496. - Construction Activities: We completed construction of 13 backbone miles and 9 miles of laterals for a total of 22 miles of fiber optic cable placed during Q3 2012. | 157 | 0 | 0 | 0 | 157 | 0 | 0 | 3 | Over projected baseline of 145 miles. | N/A | N/A | N/A | Over projected baseline of 145 miles. | N/A | N/A | Meeting baseline of 3 new interconnection points. | 0 | 9 | 0 | One public last mile provider is using the fiber (City of Sandyâ€™s broadband utility (SandyNet), which is a partner in our grant). No Service Agreements yet with a private provider, but there are about 10 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. Based on those conversations, we do not expect the first signed agreement with a private provider until both fiber rings are completed, which is projected to be in Q4 2012. | This project only provides dark fiber. No lit services will be provided. The project provides point-to-point fiber connections for Community Anchor Institutions at $250/month per pair of fiber. The project will also provide fiber on entire rings, which seems typical of what private carriers want. The price of fiber on entire rings will be at least $1,000 per month per pair, but that pricing is still under review. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline, though one with a public provider is being finalized now. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q2 2012. | Behind Baseline estimate of 3 due to ring construction not being complete because of additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q4 2012. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 108 | 0 | 108 | 0 | Under projected 147 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 108 CAIs being served by the end of Q3 2012. | Consistent with Baseline | Under projected 147 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 108 CAIs being served by the end of Q3 2012. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key activities expected summary: Construct 8 new route miles bringing the total fiber built to 165 miles with the 4 miles of the Portland General Electric reliability project left to complete. Total backbone constructed to 123 of 127 miles (97%), and 42 out of 42 lateral miles (100%). Connect another 29 anchor sites bringing the total to 137. Expect to have 2 more SLAâ€™s signed bringing the total to 17. Key Milestones 1. New Network Miles Deployed: Expect to construct an additional 8 route miles. 2. Total CAI Subscribers Served: Expect to have 2 more signed Service Level Agreements returned. 3. Number of signed agreements with broadband wholesalers or last mile providers: Expect to have 2 signed agreements with last mile providers. - Network Design: The network design will be complete with the exception of the 4 mile Portland General Electric reliability project. - Permits: Amend Oregon Department of Transportation permits through the Mt. Hood National Forest. - Procurement: All fiber required for this project has been received. - Network Testing: All fiber for network will be tested with the exception of the fiber east of the Portland General Electric reliability project on Mt Hood. Grant Requirement Activity Detail - Environmental Assessment: Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. - Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail - Route: The fiber network is fully design with the exception of the 4 miles on HWY 26 and the Portland General Electric reliability project. Once we receive the design drawings for the Reliability Project, our contractor can design the last 4 miles of our fiber network. - Budget: We are continuously working with our contractor to ensure the project is on budget. - Expenditures: Construction and design expenditures expected to be about $850,000.00 and staff time of about $52,000.00. | Clackamas, County of | 1. RoW Issues We have encountered RoW permitting challenges with one municipality, but we are mediating to resolve the differences. Although mediation continues, our most recent AAR was approved and we have continued the construction on the newly approved route. | The primary issues impacting the project and needing resolution: The issues we are having have been documented above and should be resolved to the point where we expect to make rapid progress and catch up with the original baseline and milestones and metrics in the next two quarters.
NT10BIX5570079 | 2012 | Q4 | Q4 - 2012 | Key Milestones Anchor Sites: Our contractor physically connected to 3 anchor sites in Q4 2012. Total anchor sites connected by the end of Q4 2012 are 111. Agreements: 1 Service Level Agreement (SLA) was signed during Q4 2012 bringing the project total to 16 signed SLAâ€™s. The 16 SLAâ€™s represent 90 anchor sites along with 52 county sites brings the total count to 142 sites to be connected to the fiber network. Permits: We have 3,495 approved Portland General Electric pole permits out of 3,540, or 99% of the Portland General Electric permits have been approved. The last 4 mile section of Highway 26 is under construction by Portland General Electric and once they finish construction, we will submit our approval from the US Forest Service and Portland General Electric for attaching to the new poles. With the approval from the US Forest Service and Portland General Electric, we will have all needed pole permits and will submit a new AAR for Highway 26. Grant Requirement Activity Detail Baseline: The baseline route is a culmination of the grant application and the 3 approved route AARâ€™s. Any future route changes will be coordinated with the NTIA through the AAR process. Environmental Assessment (EA): The environmental assessment is complete for the county fiber network, with the exception of the Portland General Electric reliability project located on Mt Hood (4 miles of poles are being relocated from off-road onto the shoulder of the highway). Environmental monitoring continues by the contractor pursuant to procedures established in the Field Manual. Outreach: We continued implementing our Outreach and Communications Plan during Q4, 2012 with new interest from telecom providers. New local organizations are showing interest in the fiber network with the news that both fiber rings are nearing completion. Construction Support Detail Proposed Route: The route as amended by AARs continues to be followed, but field discoveries require some small adjustments. Any variations to the baseline route will be submitted via the AAR process. Expenditures: Project to date construction and design expenditures are $7,412,894 which represents 66% of the overall $11.1 million project budget. The project to date construction and design expenditures represents 94% of the $7.8 million dollar grant budget. Staff time of $83,720. Construction Activities: We completed construction of 17 backbone sheath miles and 3 sheath miles of laterals for a total of 20 sheath miles of fiber optic cable placed during Q4 2012. As of the end of Q4 2012, we installed 177 sheath miles out of a projected 190 sheath miles, or 157 route miles out of a projected 169 route miles. | 177 | 0 | 0 | 0 | 177 | 0 | 0 | 4 | Under projected baseline of 190 sheath miles. We had been counting sheath miles instead of route miles. The baseline number has been increased to account for sheath miles instead of route miles. | N/A | N/A | N/A | Under projected baseline of 190 sheath miles. We had been counting sheath miles instead of route miles. The baseline number has been increased to account for sheath miles instead of route miles. | N/A | N/A | Exceeding baseline of 3 new interconnection points. | 0 | 10 | 4 | One public last mile provider is using the fiber (City of Sandyâ€™s broadband utility (SandyNet), which is a partner in our grant). No Service Agreements yet with a private provider, but there are about 10 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. Based on those conversations, we do not expect the first signed agreement with a private provider until both fiber rings are completed, which is projected to be in Q1 2013. | This project only provides dark fiber. No lit services will be provided. The project provides point-to-point fiber connections for Community Anchor Institutions at $250/month per pair of fiber. The project will also provide fiber on entire rings, which seems typical of what private carriers want. The price of fiber on the urban ring and rural ring will be $1,500 and $1,250 per month per pair, respectively. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | Consistent with Baseline, though one with a public provider is being finalized now. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q1 2013. | Behind Baseline estimate of 3 due to additional route engineering in dense area. Agreements are in process with Clackamas Educational Service District & SandyNet and expected to be signed by the end of Q1 2013. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 111 | 0 | 111 | 0 | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 111 CAIs being served by the end of Q4 2012. | Consistent with Baseline | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 111 CAIs being served by the end of Q4 2012. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key Milestones 1. New Network Miles Deployed: Expect to construct an additional 7 route miles bringing the project total to 164 route miles. 2. Total CAI Subscribers Served: Expect to have 1 more signed Service Level Agreements returned. 3. Number of signed agreements with broadband wholesalers or last mile providers: Expect to have 2 signed agreements with last mile providers. Anchor Sites: Our contractor will connect 25 anchor sites by end of Q1 2013, bringing the total to 136. Network Design: The network design will be complete with the exception of the 4 mile Portland General Electric reliability project. Permits: Amend Oregon Department of Transportation permits through the Mt. Hood National Forest. Procurement: All fiber required for this project has been received. Network Testing: All fiber for this network will be tested with the exception of the fiber east of the Portland General Electric reliability project on Mt Hood. Grant Requirement Activity Detail Environmental Assessment: Continued environmental monitoring by contractor pursuant to procedures established in the Field Manual. Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail Route: The fiber network is fully design with the exception of the 4 miles on HWY 26 and the Portland General Electric reliability project. Once we receive the design drawings for the Reliability Project, our contractor can design the last 4 miles of our fiber network. Budget: We are continuously working with our contractor to ensure the project is on budget. Expenditures: Construction and design expenditures expected to be about $350,000.00 and staff time of about $31,500.00. | Clackamas, County of | 1. The requirement from the City of Canby that everything must be built underground was a surprise and will be expensive to accommodate. | The issues we are having have been documented above and should be resolved to the point where we expect to make rapid progress and catch up with the original baseline and milestones and metrics in the next two quarters.
NT10BIX5570079 | 2013 | Q1 | Q1 - 2013 | Key Milestones Anchor Sites: Our contractor physically connected to 12 anchor sites in Q1 2013. 9 interconnected sites saw increased performance because of the 12 sites connected. Total connected anchor sites for Q1 2013 is 21. Total anchor sites connected by the end of Q1 2013 are 132. Agreements: 1 Service Level Agreement (SLA) was signed during Q1 2013 bringing the project total to 17 signed SLAâ€™s. The 17 SLAâ€™s represent 96 anchor sites along with 52 county sites brings the total count to 148 sites to be connected to the fiber network. Permits: We have all required permits for our approved project with the exception of the 4 mile section of Highway 26 that is under construction by Portland General Electric and one railroad permit into Canby. Once they finish construction, we will submit our approval from the US Forest Service and Portland General Electric for attaching to the new poles. Grant Requirement Activity Detail Baseline: The baseline route is a culmination of the grant application and the 3 approved route AARâ€™s. Any future route changes will be coordinated with the NTIA through the AAR process. Environmental Assessment (EA): The environmental assessment is complete for the county fiber network, with the exception of the Portland General Electric reliability project located on Mt Hood (3 miles of poles are being relocated from off-road onto the shoulder of the highway). Environmental monitoring continues by the contractor pursuant to procedures established in the Field Manual. Outreach: We continued implementing our Outreach and Communications Plan during Q1, 2013 with new interest from telecom providers. New local organizations are showing interest in the fiber network with the news that both fiber rings are nearing completion. Construction Support Detail Proposed Route: The route as amended by AARs continues to be followed, but field discoveries require some small adjustments. Any variations to the baseline route will be submitted via the AAR process. Expenditures: Project to date construction and design expenditures are $7,628,644 which represents 69% of the overall $11.1 million project budget. The project to date construction and design expenditures represents 98% of the $7.8 million dollar grant budget. Staff time of $63,106. Construction Activities: We completed construction of 2 miles of laterals for a total of 2 miles of fiber optic cable placed during Q1 2013. As of the end of Q1 2013, we installed 170 miles out of a projected 171 miles. | 170 | 0 | 0 | 0 | 170 | 0 | 0 | 4 | Under projected baseline of 174 route miles. We had reported 177 sheath miles in last quarter PPR. We have corrected this to accurately report route miles and the cumulative route miles at the end of this quarter is 170. | N/A | N/A | N/A | Under projected baseline of 174 route miles. We had reported 177 sheath miles last quarter PPR. We have corrected this to accurately report route miles and the cumulative route miles at the end of this quarter is 170. | N/A | N/A | Exceeding baseline of 3 new interconnection points. | 0 | 10 | 4 | One public last mile provider is using the fiber (City of Sandyâ€™s broadband utility (SandyNet), which is a partner in our grant). No Service Agreements yet with a private provider, but there are about 10 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. Based on those conversations, we do not expect the first signed agreement with a private provider until both fiber rings are completed, which is projected to be in early Q2 2013. | This project only provides dark fiber. No lit services will be provided. The project provides point-to-point fiber connections for Community Anchor Institutions at $250/month per pair of fiber. The project will also provide fiber on entire rings, which seems typical of what private carriers want. The price of fiber on the urban ring and rural ring will be $1,500 and $1,250 per month per pair, respectively. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 0 | 2 | N/A | N/A | N/A | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 132 | 0 | 132 | 0 | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 132 CAIs being served by the end of Q1 2013. | N/A | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 132 CAIs being served by the end of Q1 2013. | 1 GBPS - Standard for all connections 10 GBPS - Available if electronics upgraded | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The project does not offer any services, only dark fiber at published pricing. | FALSE | N/A | Key Milestones 1. New Network Miles Deployed: Expect to construct an additional 3 route miles. 2. Total CAI Subscribers Served: Expect to have 4 more signed Service Level Agreements returned. 3. Number of signed agreements with broadband wholesalers or last mile providers: Expect to have 3 signed agreements with last mile providers. Procurement: All fiber required for this project has been received. Network Testing: All fiber will be tested by end of Q2 2013. Grant Requirement Activity Detail Environmental Assessment: Environmental assessment will be complete by end of Q2 2013. Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. Construction Support Detail Budget: We are continuously working with our contractor to ensure the project is on budget. Expenditures: Construction and design expenditures expected to be about $587,610 and staff time of about $4,231 picked up by grant. | Clackamas, County of | 1. The requirement from the City of Canby that everything must be built underground was a surprise and will be expensive to accommodate for future non-BTOP construction. However, it will not affect BTOP project indicators or milestones. | All issues will be resolved by end of Q2 2013.
NT10BIX5570079 | 2013 | Q2 | Q2 - 2013 | Anchor Sites: Our contractor physically connected to 10 new anchor sites in Q2, 2013. In addition, 4 new interconnected sites saw increased performance because of the 10 physically connected sites. Total anchor sites receiving enhanced connectivity by the end of Q2, 2013 is 146. Permits: We have all required permits for our approved project with the exception of 2 railroad permits near the city of Canby and Gladstone. Both railroad permits are due back in July 2013. Construction Activities: We completed construction of 5 miles of laterals for a total of 5 miles of fiber optic cable placed during Q2 2013. As of the end of Q2 2013, we installed 175 miles out of a projected 180 miles. Grant Requirement Activity Detail Baseline: The baseline route is a culmination of the grant application and the 4 approved route AARâ€™s. Environmental Assessment (EA): The environmental assessment is complete for this project. Environmental monitoring continues by the contractor pursuant to procedures established in the Field Manual. Outreach: We continued implementing our Outreach and Communications Plan during Q2, 2013. Our efforts in presenting our program to telecom providers resulted in 4 new telecom Service Level Agreements in Q2, 2013. Construction Support Detail Proposed Route: The route as designed and modified by 4 approved AAR's continues to be followed. Expenditures: Project to date construction and design expenditures are $10,852,044 which represents 96% of the overall $11.2 million project budget. Staff time of $56,317. | 175 | 0 | 0 | 0 | 175 | 0 | 0 | 4 | Over projected baseline of 174 route miles. | N/A | N/A | N/A | Over projected baseline of 174 route miles. | N/A | N/A | Exceeding baseline of 3 new interconnection points. | 4 | 10 | 4 | Silver Star Telecom, Wave Broadband, Edge IT and Integra/ELI. | This project only provides dark fiber. No lit services will be provided. The project provides point-to-point fiber connections for Community Anchor Institutions at $250/month per pair of fiber. The project will also provide fiber on entire rings, which seems typical of what private carriers want. The price of fiber on the urban ring and rural ring will be $1,500 and $1,250 per month per pair, respectively. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 4 | 2 | N/A | N/A | Exceeding baseline goal of 3. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 146 | 0 | 146 | 0 | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 146 CAIs being served by the end of Q2 2013. | N/A | Under projected 149 baseline. Due to RoW permitting/franchising issues, route changes and related design changes, we now have a total of 146 CAIs being served by the end of Q2 2013. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Key Milestones Anchor Sites: Our contractor will physically connect another 18 anchor sites in Q2, 2013. 1 interconnected site will see increased performance because of the 18 sites connected. Total anchor sites receiving enhanced connectivity by the end of Q3, 2013 is 165. New Network Miles Deployed: Expect to construct an additional 5 route miles bringing the total to 180 route miles. Permits: All permits will be received by end of Q3, 2013. Network Testing: All fiber will be tested by end of Q3, 2013. Grant Requirement Activity Detail Outreach: We will continue implementing our Outreach and Communications Plans, which includes updating the project web site, distributing a newsletter, and communicating with communications providers. We expect to have 1 more agreement with a wholesale/last mile provider by the end of Q3, 2013. Construction Support Detail Route: The fiber network is fully designed. Budget: We are continuously working with our contractor to ensure the project is on budget. Expenditures: Construction and design expenditures expected to be about $440,342 and staff time of about $ 57,000. | Clackamas, County of | Obtaining final SHPO concurrence has been challenging as the state SHPO office: is short-staffed; has a high backlog; reviews requests on a first-come, first-served basis; and does not provide a process to expedite reviews. BTOP program staff have been helpful by focusing reviews on new underground disturbances. | The franchise with the City of Canby will be resolved before the end of Q3 2013.
NT10BIX5570079 | 2013 | Q3 | Q3 - 2013 | Clackamas County is a large and diverse county. Most of the population is in the Northwest corner of the county with the rest of the county mostly smaller rural cities that were underserved or unserved with fiber optic cable. The connectivity for these communities was limited and unreliable. Clackamas County installed the fiber network and created a backbone of fiber optic cable that the smaller rural communities could utilize to get fast reliable broadband. Rural schools, fire stations and libraries could take advantage of the county fiber network to get high speed connectivity at an affordable cost. One such rural school district saw their connectivity speed increase from 100 MB to 1 GB and at the same time they saved over $38,000 per year on their connectivity costs! With the completion of the fiber network, Clackamas County connected 163 anchor sites. The anchor sites are comprised of 87 schools, 30 public safety entities, 9 medical and health care providers, 8 libraries, 2 community colleges and 27 various local governmental entities. All of these connections are utilizing the fiber to create at least a 1 Gigabit connections between sites. Along with the fiber network creating fast and reliable connectivity, the fiber network has created an avenue for future business growth. In the 21st century, access to high speed broadband is an essential part of any communities ability to attract new businesses and help retain the current local businesses. High speed broadband, along with other key infrastructure, will help the communities thrive in future. As the project progressed, the project team continued to value engineer the network design to ensure the highest capacity of fiber optic cable for the backbone of the fiber network. This additional fiber capacity will ensure that all interested parties will have fiber now and in the future. | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 4 | Over projected baseline of 174 route miles. | N/A | N/A | N/A | Over projected baseline of 174 route miles. | N/A | N/A | Exceeded baseline of 3 new interconnection points. | 4 | 10 | 4 | Silver Star Telecom, Wave Broadband, Edge IT and Integra/ELI. | This project only provides dark fiber. No lit services will be provided by the county. The project provides point-to-point fiber connections for Community Anchor Institutions at $250/month per pair of fiber. The project will also provide fiber on entire rings, which seems typical of what private carriers want. The price of fiber on the urban ring and rural ring will be $1,500 and $1,250 per month per pair, respectively. | Overall Management of the network will remain with Clackamas County. | 0 | 0 | 4 | 2 | N/A | N/A | Exceeded baseline goal of 3. | 1 GBPS - Standard for all providers (0 currently) 10 GBPS - Available if electronics upgraded (0 currently) | 163 | 0 | 163 | 0 | Exceeded baseline goal of 149. | N/A | Exceeded baseline goal of 149. | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | N/A. Project is complete. | Clackamas, County of | Obtaining the franchise agreement with the City of Canby. This resulted in a loss of one Community Anchor Institution (CAI). Still, with the loss of this CAI, we connected 14 more CAI,s than the original baseline. | N/A. Project is complete.
NT10BIX5570080 | 2010 | Q4 | Q4 - 2010 | OnWav finalized the Proposed Funded Service area. OnWav issued an Request For Proposal for Project Management, Network Engineering and Design, Compliance Reporting, Procurement and Bidding. OnWav selected Widelity Inc. as the winning bidder for this Request for Proposal OnWav issued a Request for Proposal to complete all tasks related to the Environmental Assessment (EA) at the end of the quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 3 | 0 | OnWav is still in negotiation with both wholesalers and last mile providers for interconnection. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | OnWav has not designated a third party to operation any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. | In the next Quarter, OnWav intends to select an EA vendor based on the RFP just released. This vendor will complete the initial draft EA report. Final completion of all steps of the EA requirement will be complete next quarter, and OnWav intends to meet all requirements for the issuance of the FONSI. OnWav also intends to begin site acquisition for the 7 existing site locations in the next quarter. | ONWAV INC. | Onwav's original deployment schedule needs to be amended as a result of the difficulties in solving an overlap issue with a BIP winner. OnWav approached the problem by initially mapping out the affected census blocks. This showed that descoping those blocks from OnWav's project would not have a meaningful impact, Final resolution is expected to be complete the first week of January. Resolving issues like these is best solved by examining the details. The sooner those details can be provided by BTOP, the sooner a solution can be reached. | Completing the Environmental Assessment report in a very short timeframe will be difficult. However, OnWav intends to meet this goal by hiring a highly qualified and experienced Environmental Firm.
NT10BIX5570080 | 2011 | Q1 | Q1 - 2011 | OnWav finalized the Proposed Funded Service area. OnWav selected a winning bidder for the RFP issued in the previous quarter to complete all tasks related to the Environmental Assessment (EA). OnWav has completed the below milestones related to the EA: - Initial draft as required in Grant Special Award Conditions - Completed all tribal consultations (7 tribes responded) - Completed Fish and Wildlife Services (FWS) Consultation on 3 of 3 new site locations - Completed State Historic Preservation Officer (SHPO) consultation on 9 of 10 site locations OnWav has begun the process of making initial contact with existing tower owners to initiate the site acquisition and leasing process | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 3 | 0 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | OnWav has not designated a third party to operation any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. | In the next quarter, OnWav intends to complete the site acquisition for 7 existing sites which it began in the last quarter. Once this site acquisition is complete, OnWav will begin the process of acquiring zoning approvals for installation at the 7 existing sites. In parrallel to this, OnWav intends to complete all environmental related work and receive the Finding of No Significant Impact (FONSI). With this, OnWav will begin site acquisition for the 3 new sites. OnWav will begin updating its Business Support Systems and Operations Support Systems (BSS and OSS). Much of OnWav's deployment project will involve contracting outside vendors to supply expertise, assistance and equipment. OnWav intends to begin releasing a series of Requests for Proposals (RFPs)to allow potential partners bid and explain what services they can provide OnWav. The first RFP will be for and Equipment Procurement and Logistics. Additionally, the RFP will have an RF Engineering component to complete the Network Design Milestone. | ONWAV INC. | OnWav experienced greater than expected resistance from the Tennessee State Historic Preservation Officer (SHPO). OnWav was expecting a great deal of work be required to received a "No Adverse Affect" finding and so was not overly surprised when the SHPO requested an investigation scope above and beyond the amount required by FCC rule. However, OnWav overestimated the level of cooperation the SHPO would provide in resolving his concerns. Because the Finding of No Significant Impact (FONSI) is a requirement prior to continuation of the deployment, this has delayed the overall project until all environmental work can be completed. | Working to speed through the site acquisition after a delay in getting the Environmental work complete will compress the timeline and be difficult, but OnWav is exploring methods which will expedite this process. One method being employed is to begin site acquisition contingent upon the Environmental Clearance. A second method is to wrap multiple stages of work into a single RFP so that more components can be bid simultaneously and completed more quickly.
NT10BIX5570080 | 2011 | Q2 | Q2 - 2011 | After working extensively with the Tennessee State Historic Preservation Officer, OnWav was able to mitigate his concerns and clearance was received for the 10th of 10 sites. OnWav completed the Environmental Assessment Report. All modifications requested were made and a final EA Report was accepted by NTIA. OnWav Issued a Request For Proposal (RFP) to resolve both equipment procurement as well as necessary financing. However, no suitable bids were received and OnWav did not award a contract. OnWav signed Options for land purchase for the three proposed new tower constructions. These options give OnWav the right to purchase the necessary land to construct the three towers proposed in this project. OnWav is in negotiations with a 3rd party to provide matching support. This will result in a technology change in OnWav's project, and as a result a network design change. The negotiations and expected network design change have put any portions of the project on delay as details are finalized. OnWav has begun drafting a technology change memo and accompanying budget change to be submitted in Q3 2011. At the end of the quarter, OnWav received it's Finding of No Significant Impact (FONSI). This clears the final Environmental requirement and completes the Environmental portion of the Specific Award Conditions (SAC). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 3 | 0 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | OnWav has not designated a third party to operation any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available yet. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. | In the next quarter, OnWav intends to complete the site acquisition for 7 existing sites. Once this site acquisition is complete, OnWav will begin the process of acquiring zoning approvals for installation at the 7 existing sites. In parallel to this, OnWav hopes to complete land acquisition for the 3 new sites. OnWav is exploring avoiding the need to update it's BSS and OSS systems by utilizing a system provided by a 3rd party. However, it may take multiple quarters to finalize this solution. Much of OnWav's deployment project will involve contracting outside vendors to supply expertise, assistance and equipment. OnWav intends to begin releasing a series of Requests for Proposals (RFPs)to allow potential partners bid and explain what services they can provide OnWav. The first RFP will be for and Equipment Procurement and Logistics. Additionally, the RFP will have an RF Engineering component to complete the Network Design Milestone. | ONWAV INC. | Because the Finding of No Significant Impact (FONSI) was a requirement to continuation of the deployment, this has delayed the overall project until all environmental work could be completed. Additionally because the Equipment Procurement RFP was unsuccessful, OnWav was left with limited financing options. OnWav is remedying this by having located a 3rd party provider of match funding. OnWav is re-evaluating it's Equipment Procurement Request For Proposal (Equipment RFP) and will likely issue a new RFP in the future taking into considering comments of equipment vendors who chose not to bid under the original RFP. | Working to speed through the site acquisition after a delay in getting the Environmental work complete has compressed the timeline and made things more difficult, but OnWav has planned methods which will expedite this process. One method already implemented is to acquire rights to site acquisition which (now that the Environmental clearance has been received) can be exercised to acquire land for the 3 new towers. A second method is to wrap multiple stages of work into a single RFP so that more components can be bid simultaneously and completed more quickly. OnWav will also be issuing RFPs based on comments from vendors who did not bid on the previous RFP in order to encourage greater participation.
NT10BIX5570080 | 2011 | Q3 | Q3 - 2011 | - OnWav arranged to secure control of dark fiber connecting each of its network of sites. This match will provide OnWav with an opportunity to provide higher speed middle mile backhaul on a more reliable and robust network thanks to the ring network formed by the fiber to be purchased. - As a result of the new fiber match, OnWav was able took the opportunity to redistribute the funding its budget to more accurately reflect costs being experienced. This budget change has been approved by BTOP - The change in Backhaul technology from microwave to fiber will allow OnWav to deploy a far more robust network with greater capacity and will be simpler to upgrade in the future as network demands continue to increase and technology options continue to progress. - OnWav has taken the first step in acquiring the land necessary to construct the three new towers in its network. By securing this land OnWav has ensured it will have access to prime location to construct and deploy its network from as well as providing valuable middle-mile infrastructure to be used by other providers. - All of these solutions have been made possible by an impending change in ownership in OnWav. The new owner is able to provide the necessary capital in the form of fiber In-Kind match contributions to allow OnWav's project to continue. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 3 | 0 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products availablef deploying the network, as a result, OnWav does not yet have any products available. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. | - OnWav is expecting to complete the necessary partnership and change in ownership with a 3rd party that will provide all the necessary match contribution to support OnWav's deployment plan. As soon as this is complete, OnWav will begin work on finalizing the land acquisition necessary for the three new towers, as well as finalize and begin deploying the newly redesigned backhaul network. - IRUs (Irrevocable Right of Use) will be put in place to ensure OnWav's access to necessary backhaul fiber. This will provide the fiber match portion for OnWav's deployment, as well as begin the deployment of fiber backhaul miles. These IRUs represent over 200 miles of fiber for the project as a whole. Of this, approximately 5-10 miles will be new construction (final engineering is still pending). This will also represent an agreement OnWav's first broadband wholesaler. - Additional environmental review will be necessary to accommodate the new fiber. However, OnWav is working on methods of deploying the new fiber in such a way as to minimize the environmental impact as well as limiting the amount of additional review needed (and potential delays that might cause). - OnWav will release RFPs (Requests for Proposal) to cover RF Engineering, Tower Construction and Equipment supply services. - OnWav anticipates choosing a tower construction vendor and beginning work on newly purchased land immediately. - OnWav does not expect to serve any CAIs in the next quarter; initial CAI service | ONWAV INC. | Due to the delay in receipt of a FONSI, and approvals necessary to reorganize OnWav's new budget and new matching contributrion plans, OnWav had to postpone further deployment. OnWav has prepared plans for expenditure to ensure that the project can be accelerated once the matching source is finalized, but it is expected to take multiple quarters to catch up. | One of the major challenges facing OnWav will be finalizing the 3rd party partnership and completing the change in ownership. While there is no doubt of a satisfactory conclusion, timing may cause delays to other stages of the project. If the change in ownership, and subsequent merging of activities, takes longer than expected, the delays may result in some categories above being pushed back into the first quarter of 2012. Because of the technology change, OnWav will need to proceed with further environmental analysis. OnWav will gather information immediately in order to be able to minimize the review time necessary for the additional work. OnWav is also working closely with an environmental firm and regularly reviewing plans to minimize the environmental impact and corresponding approvals necessary. However, the time risk exists and cannot be mitigated entirely. With help from OnWav's new match partner and pending owner, OnWav will be able to make significant and measurable progress in Q4 2011 and Q1 2012.
NT10BIX5570080 | 2011 | Q4 | Q4 - 2011 | - OnWav signed the first fiber IRU, providing OnWav access to over 190 miles of previously dark fiber connecting COs in it's markets. Future additions to the IRU will provide OnWav access to fiber connecting to each of its tower sites allowing for robust all fiber backhaul ring. - The completion of the fiber IRU means that OnWav has met all of its 20% match contribution for this project. - OnWav has completed the land acquisition of all three plots of land needed for tower construction. By acquiring this land OnWav has ensured it will have access to prime location to construct and deploy its network from as well as providing valuable middle-mile infrastructure to be used by other providers. - OnWav completed a change in ownership; the new owner was to provide the necessary match contribution in the form of the fiber IRU to allow OnWav's project to not only continue, but will result in a superior network. - OnWav completed and submitted its first full grant year audit. - OnWav issued an RFP for Tower Construction Vendor and conducted a round of site visits with bidders. OnWav is finalizing its review and expects to award a contract at the beginning of 2012. - OnWav issued an RFP for RF Engineering work associated with this project and awarded the contract to an experienced RF Engineering firm who has already begun work supporting the project - OnWav issued an RFP for Electronics Equipment associated with this project. OnWav received multiple bids and has conducted an extensive review process with bidders including conference call discussions, site visits and multiple clarifying questions to ensure the best offering is chosen for this project. OnWav expects to award this RFP in early 2012. | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | No Variance from Baseline | N/A | N/A | OnWav completed an initial IRU to acquire access to 190 miles of existing dark fiber to use as part of the planned 209 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. This action puts OnWav ahead of schedule on deployment of network miles. | No Variance from Baseline | With the addition of the Fiber Backhaul, the fiber will no longer include any wireless links. | No Variance from Baseline | Due to the delay in the project shift from a Microwave system to a fiber network, in addition to the equipment delays in the Equipment Request For Proposal, OnWav's network has not been constructed yet. OnWav expects it will be late Q2 2012 or early Q3 2012 before the first interconnection points are turned up. | 0 | 3 | 0 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. | - Environmental - OnWav is planning on hiring a environmental firm to complete the necessary additional review to amend OnWav's Environmental Assessment to cover the change from Microwave backhaul to a Fiber system. OnWav has taken measures to minimize this impact to help expedite the Environmental review. - OnWav expects to complete review of RFPs (Requests for Proposal) to cover Tower Construction and Equipment supply services. - OnWav expects to release an RFP (Requests for Proposal) to cover network deployment (field installation, equipment installation and related deployment activities). - OnWav expects to order and receive initial equipment required for the portion of the fiber network covered by the IRU signed in Q4 2011. - OnWav expects to begin engineering design work on the three new towers. - OnWav expects to complete leasing activities on the collocation sites - OnWav expects to place an initial order for RF Network equipment. - OnWav does not expect to deploy any additional fiber miles deployed next quarter; the remaining fiber miles will be deployed in a later quarter. - OnWav does not expect to serve any CAIs in the next quarter; initial CAI service will come in a later quarter. - OnWav does not expect to sign any broadband wholesalers or last mile providers in the next quarter; signed agreements will come in a later quarter. | ONWAV INC. | One major challenge OnWav faced was in RFP review and decisions. OnWav faced two primary impediments for RFP review. The first was bid responses which included too much uncertainty (too many line items were priced contingent upon further information). In order to resolve this uncertainty, OnWav walked each bidder through the sites and documented more information to the bidder for a revised price. This resulted in a much higher quality bid and a more certain RFP decision, but it did significantly increase the time needed for a decision. The second was in greater than expected bid interest. In this case, OnWav went through an initial cut of bidders and rejected bids which had irreconcilable issues. Then meetings and interviews with the remaining bidders, as well as an opportunity for "best and final" offers helped distinguish the remaining bidders to ensure OnWav chose the optimum vendor. | A potential challenge OnWav expects to face is deliver time frames for equipment and material. While OnWav may be ready to place orders for equipment and tower materials this quarter, it remains to be seen what the actual deliver dates of those orders are going to be. Significant delays due to supply or shipping delays may cause delays and hinder project construction. Because of the technology change, OnWav will need to proceed with further environmental analysis. OnWav will gather information immediately in order to be able to minimize the review time necessary for the additional work. OnWav is also working closely with an environmental firm and regularly reviewing plans to minimize the environmental impact and corresponding approvals necessary. However, the time risk exists and cannot be mitigated entirely. With help from OnWav's new match partner and pending owner, OnWav will be able to make significant and measurable progress in Q1 2012 and Q2 2012.
NT10BIX5570080 | 2012 | Q1 | Q1 - 2012 | - Environmental - OnWav's environmental firm began the process to amend OnWav's Environmental Assessment to cover the change from Microwave backhaul to a Fiber system. The initial surveys have been completed and notices sent to the State Historical Preservation Officer (SHPO) and Fish and Wildlife Services (FWS). OnWav hopes to get Concurrence responses early in Q2 2012 - OnWav awarded the Tower contract to an initial winning bidder. However, due to complications during the negotiation process, OnWav has re-awarded the contract to another bidder to the RFP and is currently finalizing contract negotiations. - OnWav awarded the RF Equipment contract to two vendors for this project: One for the Radio Access Network and the other for the Core and backhaul network. Contract Negotiations are underway. - OnWav received the final approval for all three of the existing installation sites. Final contracts are underway. - Twin Lakes began the necessary installation to connect and activate the fiber secured by OnWav. - OnWav completed land acquisition of the third and final plot of land for the construction of OnWav's 3 new towers. | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | No Variance from Baseline | N/A | N/A | OnWav has an initial IRU for access to 190 miles of existing dark fiber to use as part of the planned 210 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. OnWav already has more fiber miles deployed than originally foreseen wireless miles for the project in the baseline. | No Variance from Baseline | With the addition of the Fiber Backhaul, the fiber will no longer include any wireless links. | With the delays of the Tower Construction RFP, OnWav is behind schedule in deploying new towers. OnWav expects to be completely caught up on this milestone by Q3 2012. | Due to the delay in the project shift from a Microwave system to a fiber network, in addition to the equipment delays in the Equipment Request For Proposal, OnWav's network has not been constructed yet. OnWav expects to deploy the first interconnection point in Q2 2012. | 0 | 2 | 0 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection. OnWav expects to sign the first wholesaler agreement Q2 2012 | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers. The first agreement is expected in Q2 2012 | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | N/A | OnWav is still in the negotiation stage for contracts relating to Broadband Wholesalers or Last Mile Providers | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. OnWav's network policies for the grant network are still under development, but will be posted prior to network launch. | - Environmental - OnWav expects to receive SHPO and FWS Concurrences for the changes to it's project as a result of the new fiber. It will then submit the Environmental amendment to NTIA for review. - OnWav expects to complete a contract for Tower Construction - OnWav expects to complete two contracts for Equipment. One will cover equipment related to the wireless Radio Access Network (RAN) and the second will cover the necessary Core Network equipment (Switches, servers, etc.). Each contract will also cover all necessary deployment and installation services to make the equipment and network operational. The RAN contract will also include RF Engineering services to design the final specifications of the network. - OnWav expects to get approval for installation on the existing sites at the beginning of Q2, 2012, with final leases to come after. - OnWav expects to deploy the remaining 20 miles of the fiber miles in the upcoming quarter if the Environmental Assessment Amendment is approved by NTIA for a total of approximately 210 miles of total fiber. - OnWav expects to serve 5-10 new CAIs in the next quarter. - OnWav expects to sign agreement with 2 broadband last mile providers in the next quarter. | ONWAV INC. | One major challenge OnWav faced was in RFP review and decisions. OnWav faced two primary impediments for RFP review. OnWav spent a great deal of time ensuring that the multiple equipment vendors selected during the Equipment RFP would be inter-operable with each other. This required ensuring that the potential winners communicated with each other and coordinated a test plan. In the end an acceptable Interoperability Testing Plan could not be created and OnWav selected a different vendor who could meet the RFP required interoperability needs of OnWav. The tower construction contractor which OnWav initially selected was unable to finalize and sign a contract with OnWav in a timely manner. As a result OnWav was forced to choose another bidder and expects to complete the contract with the new winner early in Q2 2012. | A potential challenge OnWav expects to face is delivery time frames for equipment and material. While OnWav may be ready to place orders for equipment and tower materials this quarter, and has arranged to have equipment and materials delivered in a favorable time, these planned schedules are extremely tight, and there is no slack time available. Much of OnWav's time lines after the next quarter (Q3 2012 and after) are extremely dependent on getting environmental clearance in a timely manner. Assistance from BTOP in quick approval from the NTIA environmental review team will be very valuable in assisting these stages do not suffer ripple effects of an environmental delay.
NT10BIX5570080 | 2012 | Q2 | Q2 - 2012 | - Environmental - OnWav received SHPO Concurrences for the changes to it's project as a result of the new fiber. - Environmental - OnWav received FWS Concurrences after consultation and minor changes to ensure the protection of habitat for local Indiana Bats. - Tower Construction - OnWav has completed a contract with a tower construction vendor. Initial land surveys have been completed and engineering is ready to begin. - Equipment - OnWav has signed contract for all of its RF equipment. All of the base-station equipment has already been delivered to OnWav's warehouse in Gainesboro, TN. The indoor Customer Premise Equipment has arrived and the outdoor CPE are expected to arrive in early July. Initial testing of all equipment has begun. - Equipment - OnWav has signed a contract for Networking Core equipment. This equipment has been delivered to OnWav's Gainesboro, TN warehouse. The equipment has been installed and testing and configuration has begun. - Deployment - OnWav is preparing to install equipment on the initial two sites for deployment in late July 2012. - Jobs - OnWav reported 2.62 jobs created this quarter. This included new work completed by Surveyors and Engineers in preparation of OnWav's upcomming installation on the Water Tanks as well as preparations of construction of the three new towers. | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | No Variance from Baseline | N/A | N/A | OnWav has an initial IRU for access to 190 miles of existing dark fiber to use as part of the planned 210 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. OnWav already has more fiber miles deployed than originally foreseen wireless miles for the project in the baseline. | No Variance from Baseline | No Variance from Baseline | With the delays of the Tower Construction RFP and contract process, OnWav is behind schedule in deploying new towers. OnWav expects to be completely caught up on this milestone by Q4 2012. | Due to the delay in the project shift from a Microwave system to a fiber network, in addition to the equipment delays in the Equipment Request For Proposal, OnWav's network has not been constructed yet. OnWav expects to deploy the first interconnection point in Q3 2012. | 0 | 2 | 0 | OnWav has finalized negotiation with wholesalers for interconnection, however agreements have not been signed yet. OnWav expects to sign the both wholesaler agreements Q3 2012. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 0 | 0 | 0 | 0 | OnWav has finalized negotiation with wholesalers for interconnection, however agreements have not been signed yet. OnWav expects to sign the both wholesaler agreements Q3 2012. | OnWav has finalized negotiation with wholesalers for interconnection, however agreements have not been signed yet. | N/A | OnWav has finalized negotiation with wholesalers for interconnection, however agreements have not been signed yet. | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | N/A | OnWav's network is not yet complete with construction, as a result subscribers will not be added until future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no households have yet been passed, but this will increase in future quarters | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | N/A | OnWav's network is not yet complete with construction, as a result no businesses have yet been passed, but this will increase in future quarters | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any products available. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. OnWav's network policies for the grant network are still under development, but will be posted prior to network launch. | - Environmental - OnWav anticipates completing the necessary tribal consultations for the change in location for the Livingston site. - Tower Construction - OnWav anticipates completing all surveys and geological engineering work for the three new towers. OnWav expects to receive FCC clearance on two of the three new towers in the next quarter. - Equipment - OnWav expects to receive the remainder of the Customer Premise Equipment. Additionally, OnWav will complete initial testing and have equipment prepared for installation at the initial sites. - Equipment - OnWav expects to have the core networking equipment tested and configured by the end of Q3 2012 - Deployment - OnWav will have leases signed for the equipment on the initial two sites (water tanks) and will deploy equipment on those sites in Q3 2012. - OnWav expects to deploy the remaining 20 miles of the fiber miles in the upcoming quarter after completing Environmental requirements and after NTIA approval. This will complete the last of approximately 210 miles of total fiber. - OnWav expects to serve approximately 22 new CAIs in the next quarter. - OnWav expects to sign agreement with 2 broadband last mile providers in the next quarter. | ONWAV INC. | An unexpected challenge OnWav faced was ensuring relevant contractors and sub-contractors where appropriately licensed and equipped to meet BTOP requirements, including Davis Bacon. OnWav discovered that many potential vendors were not prepared to handle the complexities of Davis Bacon and so the field of potential contractors was smaller than expected. | A potential challenge OnWav expects to face is FAA and FCC approval time-lines for the three towers to be constructed. Work on the towers cannot commence until those approvals are in, and OnWav is limited in the work that can be completed prior to those approvals. OnWav is preparing to have other components of the project completed as much as possible so that other portions of the grant deployment do not distract from the Tower construction once approval is in place. In the event that FAA/FCC approvals do not arrive within the normal time-line, OnWav may request NTIA assistance in prioritizing review with FAA/FCC, though this scenario is unlikely. Much of OnWav's time lines after the next quarter (Q3 2012 and after) are extremely dependent on Tower construction beginning on schedule. Any delay in the beginning of the construction of the three new towers will have ripple affects delaying large portions of the remainder of the project. OnWav has a regular weekly call with the Tower Construction vendor where the planned tower construction scheduled is reviewed and potential delay causing events are discussed and planned for. Other than the aforementioned FAA/FCC approvals, there is unlikely to be an scenarios requiring NTIA support.
NT10BIX5570080 | 2012 | Q3 | Q3 - 2012 | - Environmental - OnWav completed the necessary tribal consultations for the change in location for the Livingston site, and received approval from NTIA to proceed forward with new fiber construction. - Tower Construction - OnWav completed all surveys and geological engineering work for the three new towers. OnWav received FCC clearance on two of the three new towers in the next quarter. OnWav expects to receive FCC clearance on the final tower early next quarter. - Tower Construction - OnWav has ordered tower materials for the two FCC approved towers. OnWav will order steel for the third new tower once FCC clearance is given. - Equipment - OnWav has received the remainder of the Customer Premise Equipment (CPE). All Radio equipment (both basestation and customer premise equipment) has now been delivered to OnWav. - Deployment - OnWav has installed basestation equipment on the initial two sites in the towns of Jamestown and Allardt. - Deployment - OnWav has activated CPE at the first CAIs in Jamestown and Allardt. - Jobs - OnWav reported 3.99 jobs created this quarter. This included new work completed by Tower Climbers and other construction services as part of OnWav's installation on the Water Tanks as well as preparations of construction of the three new towers. - CAIs - OnWav is serving 12 CAIs as of the end of Q3 2012 with CAI turnup proceeding at full speed in the initial markets. - OnWav signed 2 broadband last mile provider agreements in Q3 2012. | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 3 | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have not been constructed yet as OnWav was completing necessary environmental review for the change from Microwave to Fiber. Now that this is complete, OnWav expected to finish all fiber construction in Q4 2012. | N/A | N/A | OnWav has an initial IRU for access to 190 miles of existing dark fiber to use as part of the planned 210 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. OnWav already has more fiber miles deployed than originally foreseen wireless miles for the project in the baseline. | Because of OnWav's change from a Microwave system to a fiber system, fewer new fiber miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have not been constructed yet as OnWav was completing necessary environmental review for the change from Microwave to Fiber. Now that this is complete, OnWav expected to finish all fiber construction in Q4 2012. | Because of OnWav's change from a Microwave system to a fiber system, no new wireless links will be deployed as OnWav will be taking advantage of existing dark fiber and new fiber construction | Due to delays in awaiting FAA and FCC approval, OnWav was not able to construct it's new towers in Q3 2012. However, all FAA approvals and 2 of 3 FCC approvals have been received. The final FCC approval will be received in early Q4 2012. OnWav expects to have towers constructed in Q4 2012 | Because of OnWav's change from a Microwave system to a fiber system, fewer interconnection points will be created. OnWav has deployed three ppotential interconnection points, two tower sites and a datacenter location. | 2 | 0 | 8 | Twin Lakes Telephone Cooperative Twin Lakes Communications | OnWav is providing wholesale last-mile units for partners to sell to their existing customers. Partners will pay a wholesale monthly rate for wireless units which are turned up and activated on OnWav's network. OnWav maintains and runs the network while partners maintain their existing relationship with their customers and providing an additional service. At time of this report, no services have been activated by partners. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 2 | 0 | 0 | 1 | OnWav has signed agreements for 2 wholesaler agreements. | OnWav's partners will be receiving new service. | N/A | Currently customers are not throttled and are receiving a best-effort service. In the future, CAIs will be provided speed tiers up to 12 Mbps down and up to 2 Mbps up depending on customer discretion | 12 | 12 | 0 | 1 | OnWav has completed sites in the Jamestown and Allardt locations and begun turning up CAI customers in those markets. | OnWav has completed sites in the Jamestown and Allardt locations and begun turning up CAI customers in those markets. | N/A | Currently CAI customers are not throttled and are receiving a best-effort service. In the future, CAIs will be provided speed tiers up to 12 Mbps down and up to 2 Mbps up depending on customer discretion | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | N/A | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | N/A | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any special offerings. | FALSE | OnWav has not made any changes to its network management practices over the last quarter. OnWav's network policies for the grant network are still under development, but will be posted prior to network launch. | - Tower Construction - OnWav anticipates completing all tower construction work for the three new tower sites. - CAIs - OnWav expects to continue installation of CPE at CAIs and activating them on the network. - OnWav expects to deploy the remaining 20 miles of the fiber miles in Q4 2012. This will complete the last of approximately 210 miles of total fiber. - OnWav expects to serve approximately 44 new CAIs in the next quarter. - OnWav does not expect to sign any additional broadband last mile providers in the next quarter. | ONWAV INC. | A challenge OnWav faced is FAA and FCC approval time-lines for the three towers to be constructed. The Tower steel could not be ordered from the manufacturer until both FAA and FCC approval had been received. OnWav was able to get FAA approval on all three towers, and FCC approval on two towers. The Third tower FCC approval is expected in early Q4 2012. We could not order the towers until these approvals were received because and FAA or FCC height changes would have resulted in a cancelled tower order. This meant that our timelines were somewhat delayed, but we are passed that hurdle and construciton of the towers is expected in Q4 2012. In this case, additional intervention by BTOP was not necessary. | Much of OnWav's time lines after the next quarter (Q4 2012 and after) are extremely dependent on Tower construction beginning and completing on schedule. Any delay in the beginning of the construction of the three new towers will have ripple affects delaying large portions of the remainder of the project. OnWav has a regular weekly call with the Tower Construction vendor where the planned tower construction scheduled is reviewed and potential delay causing events are discussed and planned for. As the potential delays are related to third party contractors and the weather, there is unlikely to be an scenarios requiring NTIA support.
NT10BIX5570080 | 2012 | Q4 | Q4 - 2012 | - Environmental - OnWav submitted a request for, and received approval to change locations of it's collocation site in Livingston. The new site will provide significantly improved coverage with negligible impact on the overall time-line or total cost. - Tower Construction - OnWav completed the excavation and concrete foundations at all three new tower sites. Initial civil work has begun. Utility trenching is complete for all three sites. - Tower Construction - Steel for all three sites is ready. Delivery has been delayed pending availability of tower climbers to unload and begin assembling the towers. Delivery is scheduled for the beginning of Q1 2013. - Deployment - OnWav has activated equipment for 47 CAIs in Jamestown and Allardt. - Deployment - Construction of new fiber to the three new tower sites has commenced. - Outreach - OnWav has been focusing it's efforts on CAIs. Turing CPE installation, OnWav has been taking the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This often includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. Often the OnWav employee completing the install also educates the end user on the WiMAX technology being used. - Jobs - OnWav reported 6.14 jobs created this quarter. This included new work completed by construction services on the three new sites during construction of the three new towers. - CAIs - OnWav is serving 47 CAIs as of the end of Q4 2012. CAI turnup is set to commence again with the completion of the three new towers and the installation and commissioning of Radio equipment. | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 3 | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have not been constructed yet as OnWav's fiber provider needs OnWav equipment to install the new fiber to. That equipment will be installed after tower construction is complete (to prevent the equipment from interfering with construction activities). As such, this fiber is planed to be constructed in parallel with tower construction and should complete at the same time. OnWav expecting to finish all fiber construction in Q1 2013. | N/A | N/A | OnWav has an initial IRU for access to 190 miles of existing dark fiber to use as part of the planned 210 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. OnWav already has more fiber miles deployed than originally foreseen wireless miles for the project in the baseline. | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have not been constructed yet as OnWav's fiber provider needs OnWav equipment to install the new fiber to. That equipment will be installed after tower construction is complete (to prevent the equipment from interfering with construction activities). As such, this fiber is planed to be constructed in parallel with tower construction and should complete at the same time. OnWav expecting to finish all fiber construction in Q1 2013. | Because of OnWav's change from a Microwave system to a fiber system, no new wireless links will be deployed as OnWav will be taking advantage of existing dark fiber and new fiber construction | Due to delays in awaiting FAA and FCC approval and scheduling delays, OnWav was able to begin construction of its new towers in Q4 2012. However, construction is scheduled to complete in Q1 2013. | Because of OnWav's change from a Microwave system to a fiber system, fewer interconnection points will be created. OnWav has deployed three potential interconnection points, two tower sites and a data center location. | 2 | 0 | 8 | Twin Lakes Telephone Cooperative Twin Lakes Communications These represent entities which OnWav has signed agreements in order provide last-mile (wireless) services. | OnWav is providing wholesale last-mile units for partners to sell to their existing customers. Partners will pay a wholesale monthly rate for wireless units which are turned up and activated on OnWav's network. OnWav maintains and runs the network while partners maintain their existing relationship with their customers and providing an additional service. At time of this report, no services have been activated by partners. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 2 | 0 | 0 | 1 | OnWav has signed agreements for 2 wholesaler agreements. | OnWav's partners will be receiving new service. | N/A | Currently CAIs are being provided speed tiers up to 12 Mbps down and up to 2 Mbps up depending on customer discretion | 36 | 36 | 0 | 9 | OnWav has completed sites in the Jamestown and Allardt locations and turned up CAI customers in those markets. OnWav has connected 37 locations from it's CAI target list, but one CAI has chosen not to subscribe to broadband service. | OnWav has completed sites in the Jamestown and Allardt locations and turned up CAI customers in those markets. OnWav has connected 37 locations from it's CAI target list, but one CAI has chosen not to subscribe to broadband service. | N/A | OnWav is has 7 different speed tiers being used by customers. OnWav offers up to 12Mbps/1 Mbps but has no subscribers at this speed yet. The speed tiers in usage are 10Mbps/1Mbps (1 CAI), 8Mbps/1Mbps (9 CAIs), 6Mbps/1Mbps (4 CAIs), 4Mbps/1Mbps (9 CAIs), 3Mbps/1Mbps (2 CAIs), 2Mbps/1Mbps (7 CAIs) and 1Mbps/1Mbps (4 CAIs). One CAI is connected but not purchasing broadband service at this time. | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | N/A | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to increase in future quarters. | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | N/A | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service other than CAIs. This is expected to increase in future quarters. | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any special offerings. | FALSE | As of the end of Q4 2012, the Network management policies had not been finalized and were not being enforced. Existing CAIs were being run on a best-effort service. During Q1 2013, the policies will be finalized and enforced. OnWav will also post it's network management policies at that time. | - Tower Construction - OnWav plans to complete tower construction and equipment install at all three new tower sites. These sites are located to provide service to the towns of Byrdstown, TN, Celina, TN and Gainesboro TN. Work at these sites will include all basestation and tower equipment as well as the completing all civil work and connecting utilities so the sites can begin providing wireless service to CAIs. - Deployment - Construction of new fiber to the three new tower sites will be completed. - Deployment - OnWav expects to make significant progress on leasing and access to the final wireless site located in Livingston, TN. However, OnWav does not expect to complete installation and turn-up at this site in until Q2, 2013. - CAIs - OnWav expects to continue installation of CPE at CAIs and activating them on the network. - Outreach - OnWav will continue focusing it's efforts on CAIs. OnWav will be contacting CAIs in advance of network turnup. This pre-contact will give OnWav the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This is expected to includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. OnWav will also educate the end user on the WiMAX technology being used if they are not yet familiar with it. - OnWav expects to deploy the remaining 20 miles of the fiber miles in Q1 2013. This will complete the last of approximately 210 miles of total fiber. - OnWav plans to complete activation of equipment for 65 CAIs in Byrdstown, Celina and Gainesboro, bringing the total active CAI count to 112. - OnWav does not expect to sign any additional broadband last mile providers in the next quarter. | ONWAV INC. | As expected, OnWav's time lines for Q4 2012 were very tight and dependant on FAA and FCC clearance. Both were received, however there was no slack time to make up for small minor delays related to contractor scheduling, weather, and other minor delays which added up. | Much of OnWav's time lines for the next quarter (Q1 2013) are dependent on Tower construction finishing early in the quarter. Potential delays, such as weather could have ripple affects delaying large portions of the remainder of the project. In particular, OnWav's ability to turn up the predicted number of CAIs could be hampered if the 3 new sites are not active. OnWav has a regular weekly call with the Tower Construction vendor where the planned tower construction scheduled is reviewed and potential delay causing events are discussed and planned for as much as possible. As the potential delays are related to third party contractors and the weather, there is unlikely to be an scenarios requiring NTIA support. An additional risk factor is working with the 3rd party tower owner in Livingston. OnWav hopes to complete the leasing process quickly to prepare the site for installation. No particular problems are currently foreseen, other than general speed of completion. If needed, OnWav will solicit support from NTIA in communicating the importance of this project to the tower owner, but OnWav does not believe this will be necessary.
NT10BIX5570080 | 2013 | Q1 | Q1 - 2013 | - Tower Construction - OnWav completed tower construction and equipment install at all three new tower sites. These sites are located to provide service to the towns of Byrdstown, TN, Celina, TN and Gainesboro TN. Work at these sites included all basestation and tower equipment as well as the completing all civil work and connecting utilities. These sites have begun providing wireless service to CAIs. - Deployment - OnWav has now activated equipment for 87 CAIs in the towns of Allardt, Byrdstown, Celina, Gainesboro and Jamestown. - Deployment - Construction of new fiber to the three new tower sites has been completed, and all three sites are now providing internet service to CAIs through OnWav's middle mile network. - Deployment - OnWav made significant progress on leasing and access to the final wireless site located in Livingston, TN. Negotiations on leasing are complete, and OnWav has begun preparing for construction. - Outreach - OnWav has been focusing it's efforts on CAIs. During CPE installation, OnWav has been taking the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This often includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. Often the OnWav employee completing the install also educates the end user on the WiMAX technology being used. - Jobs - OnWav reported 8.89 jobs created this quarter. This included new work completed by construction services on the three new sites during construction of the three new towers. - CAIs - OnWav is serving 86 CAIs as of the end of Q1 2013. CAI turnup is partially complete in the markets served by the three new towers. | 8 | 0 | 0 | 190 | 8 | 0 | 3 | 6 | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav is still finalizing the legal paperwork, however the fiber is active and in use by OnWav's network. | N/A | N/A | OnWav has an initial IRU for access to 190 miles of existing dark fiber to use as part of the planned 213 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. Additional fiber has been put into use and is active, however OnWav is still finalizing the legal documents. OnWav already has more fiber miles deployed than originally foreseen wireless miles for the project in the baseline. | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav is still finalizing the legal paperwork, however the fiber is active and in use by OnWav's network. | Because of OnWav's change from a Microwave system to a fiber system, no new wireless links will be deployed as OnWav will be taking advantage of existing dark fiber and new fiber construction | OnWav has completed construction of all three of OnWav's planned new towers. | Because of OnWav's change from a Microwave system to a fiber system, fewer interconnection points will be created. OnWav has deployed six potential interconnection points, five tower sites and a data center location. | 2 | 0 | 8 | Twin Lakes Telephone Cooperative Twin Lakes Communications These represent entities which OnWav has signed agreements in order provide last-mile (wireless) services. | OnWav is providing wholesale last-mile units for partners to sell to their existing customers. Partners will pay a wholesale monthly rate for wireless units which are turned up and activated on OnWav's network. OnWav maintains and runs the network while partners maintain their existing relationship with their customers and providing an additional service. At time of this report, no services have been activated by partners. | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 2 | 0 | 0 | 1 | OnWav has signed agreements for 2 wholesaler agreements. | OnWav's partners will be receiving new service. | N/A | Currently CAIs are being provided speed tiers up to 12 Mbps down and up to 2 Mbps up depending on customer discretion | 86 | 86 | 0 | 10 | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, and Jamestown. OnWav has turned up CAI customers in all five markets. OnWav has connected 87 locations from it's CAI target list, but one CAI has chosen not to subscribe to broadband service. | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, and Jamestown. OnWav has turned up CAI customers in all five markets. OnWav has connected 87 locations from it's CAI target list, but one CAI has chosen not to subscribe to broadband service. | N/A | OnWav is has 7 different speed tiers being used by customers. The speed tiers in usage are: 16Mbps/2Mbps (3 CAIs), 12Mbps/1Mbps (1 CAI), 10Mbps/1Mbps (10 CAI), 8Mbps/1Mbps (25 CAIs), 6Mbps/1Mbps (11 CAIs), 4Mbps/1Mbps (12 CAIs), 3Mbps/1Mbps (4 CAIs), 2Mbps/1Mbps (15 CAIs), 1Mbps/1Mbps (4 CAIs) 1Mbps/256 Kbps (1 CAI) One CAI is connected but not purchasing broadband service at this time. | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | N/A | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | N/A | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any special offerings. | TRUE | As of the end of Q4 2012, the Network management policies had not been finalized and were not being enforced. Existing CAIs were being run on a best-effort service. During Q1 2013, finalization of the policies was delayed due to problems with implementation of the AAA server which manages and enforces the policies. | - Deployment - OnWav anticipates completing installation at its sixth and final tower site location (its 7th interconnection point), a collocation site in Livingston, TN. - Deployment - OnWav will turn-up the final section of dark fiber to connect the new livingston installation to OnWav's middle mile network. - Outreach - OnWav has been focusing it's efforts on CAIs. During CPE installation, OnWav has been taking the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This often includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. Often the OnWav employee completing the install also educates the end user on the WiMAX technology being used. - OnWav expects to deploy the remaining approx 2 miles of the fiber miles in Q2 2013. This will complete the last of approximately 213 miles of total fiber. - OnWav plans to complete activation of equipment for 63 CAIs in Byrdstown, Celina and Gainesboro and Livingston, bringing the total active CAI count to 151. - OnWav does not expect to sign any additional broadband last mile providers in the next quarter. | ONWAV INC. | As expected, OnWav's time lines for the next quarter (Q1 2013) were heavily affected by the timing of the Tower construction. Some minor delays had ripple affects delaying the CAI turn-up schedule by a few weeks. OnWav mitigated this by pre-installing some CAIs before the network was active. While OnWav missed its planned goal for CAIs turned-up in Q1 2013, OnWav will be back on scheduled within the first three weeks of Q2 2013. | A major potential challenge facing OnWav in the next quarter is completion of the Livingston site on schedule. While everything is on schedule, the timeline is very time sensitive. Because there is less time in the remaining grant period to compensate for delays, even small time delays pose a greater risk to the overall project than similar delays earlier in the project.
NT10BIX5570080 | 2013 | Q2 | Q2 - 2013 | - Deployment - OnWav has now activated equipment for 126 Community Anchor Institutions in the towns of Allardt, Byrdstown, Celina, Gainesboro and Jamestown. OnWav has also pre-installed a substantial number of devices to provide service to Community Anchor Institutions in Livingston as soon as the basestation at that site is activated. - Deployment - OnWav has signed a lease for the final wireless site located in Livingston, TN. OnWav has also completed an RFP process and selected a construction firm to complete the installation of OnWav's equipment at the site. OnWav has issued a Purchase Order for installation. - Outreach - OnWav has been focusing its efforts on Community Anchor Institutions. During Customer Equipment installation, OnWav has been taking the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This often includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. Often the OnWav employee completing the install also educates the end user on the WiMAX technology being used. - Jobs - OnWav reported 2.62 jobs created this quarter. - CAIs - OnWav is serving 126 Community Anchor Institutions as of the end of Q1 2013. Community Anchor Institution turnup is now complete in the markets served by the three new towers. OnWav has also pre-installed a substantial number of devices to provide service to Community Anchor Institutions in Livingston as soon as the basestation at that site is activated. | 8 | 0 | 0 | 208 | 8 | 0 | 3 | 6 | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav has finalized the legal paperwork, however the final invoice is not expected until the closeout period. The fiber is active and in use by OnWav's network. | N/A | N/A | OnWav has an initial IRU and amendments for access to 208 miles of existing dark fiber to use as part of the planned 216 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav has finalized the legal paperwork, however the final invoice is not expected until the closeout period. The fiber is active and in use by OnWav's network. | Because of OnWav's change from a Microwave system to a fiber system, no new wireless links will be deployed as OnWav will be taking advantage of existing dark fiber and new fiber construction | OnWav has completed construction of all three of OnWav's planned new towers. | Because of OnWav's change from a Microwave system to a fiber system, fewer interconnection points will be created. OnWav has deployed six potential interconnection points, five tower sites and a data center location. OnWav's final tower site (7th) will be activated in Q3 2013 | 2 | 0 | 8 | Twin Lakes Telephone Cooperative Twin Lakes Communications These represent entities which OnWav has signed agreements in order provide last-mile (wireless) services. | OnWav is providing wholesale last-mile units for partners to sell to their existing customers. Partners will pay a wholesale monthly rate for wireless units which are turned up and activated on OnWav's network. OnWav maintains and runs the network while partners maintain their existing relationship with their customers and providing an additional service. At time of this report, no services have been activated by partners. Final Pricing with OnWavâ€™s wholesale partners is not yet established and still under development | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 2 | 0 | 0 | 1 | OnWav has signed agreements for 2 wholesaler agreements. | N/A | N/A | Currently CAIs are being provided speed tiers up to 12 Mbps down and up to 2 Mbps up depending on customer discretion | 126 | 126 | 0 | 10 | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, and Jamestown. OnWav has turned up CAI customers in all five markets. | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, and Jamestown. OnWav has turned up CAI customers in all five markets. | N/A | OnWav has 10 different speed tiers being used by customers. The speed tiers in usage are: 16Mbps/2Mbps (3 CAIs), 12Mbps/1Mbps (5 CAIs), 10Mbps/1Mbps (14 CAIs), 8Mbps/1Mbps (35 CAIs), 6Mbps/1Mbps (16 CAIs), 4Mbps/1Mbps (15 CAIs), 3Mbps/1Mbps (4 CAIs), 2Mbps/1Mbps (28 CAIs), 1Mbps/1Mbps (4 CAIs) 1Mbps/256 Kbps (2 CAI) | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | N/A | OnWav's network is not yet complete with construction, as a result, no households have yet been offered service. This is expected to change in the future | 0 | 0 | 0 | 0 | 0 | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | N/A | OnWav's network is not yet complete with construction, as a result, no businesses have yet been offered service. This is expected to change in the future | OnWav is still in the process of deploying the network, as a result, OnWav does not yet have any special offerings. | FALSE | As of the end of Q1 2013, the policies had been finalized and are posted to OnWav's website. | - Deployment - OnWav anticipates completing installation at its sixth and final tower site location (its 7th interconnection point), a collocation site in Livingston, TN. - Deployment - OnWav will turn-up the final section of dark fiber to connect the new livingston installation to OnWav's middle mile network. - Outreach - OnWav will continue to focus its efforts on CAIs. During installation, OnWav will take the opportunity to explain OnWav's stimulus grant and how it will be helping the local community. This includes discussing the benefits of broadband in the rural community, the value of having stimulus grant money in encouraging the deployment. The OnWav employee completing the install will also educate the end user on the WiMAX technology being used. - OnWav plans to complete activation of equipment for at least 26 CAIs in Livingston, bringing the total active CAI count to over 151. - OnWav does not expect to sign any additional broadband last mile providers in the next quarter. | ONWAV INC. | As expected, OnWav's time lines for the this quarter (Q2 2013) were heavily affected by the timing of the Livingston site construction. While OnWav's CAI installation remained on schedule, turn-up was delayed due to the site not yet being active. OnWav mitigated this by pre-installing the CAIs in Livingston, so that as soon as the site is active, those CAIs will activate immediately. While OnWav missed its planned goal for CAIs turned-up in Q2 2013, OnWav will be back on scheduled as soon as the Livingston site is turn-up in Q3,2013 | A major potential challenge facing OnWav in the next quarter and during the closeout process is closeout of open contracts with vendors. Because OnWav's contracts are written such that final invoice payment is contingent upon acceptance of the network, OnWav will need to focus on ensuring that all acceptance testing is completed on schedule. Delays in acceptance necessarily cause delays in payments of final invoices.
NT10BIX5570080 | 2013 | Q3 | Q3 - 2013 | - Deployment - OnWav completed installation at its sixth and final tower site location (its 7th interconnection point), a collocation site in Livingston, TN. - Deployment - OnWav turned up the final section of dark fiber to connect the new Livingston installation to OnWav's middle mile network. - Deployment - OnWav is now serving 154 Community Anchor Institutions in the towns of Allardt, Byrdstown, Celina, Gainesboro and Jamestown. This represents the final count of active CAIs. - Testing - OnWav completed all final network and systems testing. The network is now operational. - Outreach - OnWav focused its efforts on Community Anchor Institutions. During Customer Equipment installation, OnWav took the opportunity to explain OnWav's stimulus grant and how it has and will continue to help the local community. This often included discussing the benefits of broadband in the rural community and the value of having stimulus grant money in encouraging the deployment. Often the OnWav employee completing the install also educated the end user on the WiMAX technology being used. - OnWav completed activation of equipment for 30 new CAIs in Livingston, bringing the total active CAI count to 154. - Jobs - OnWav reported 2.42 jobs created this quarter. - CAIs - OnWav is serving 154 Community Anchor Institutions as of the end of Q3 2013, and the end of OnWav's grant period. Community Anchor Institution turnup is now complete in all markets. This project has significantly benefited the local community. The primary benefit is the redundant connection, which is viewed as a disaster recovery plan for the CAIs voice and Internet needs. This is a very positive addition since these facilities are the anchors of the communities and their ability to be contacted during a disaster is vital for the health and well being of the area's residents. With our solution they are able to have Internet access during a disaster, and also have their same phone number as well allowing the residents to contact them without having to be informed of alternative information. Additionally, since the announcement of the project, speeds have gone up and prices have gone down for broadband in the region. OnWav is also able to provide broadband on demand in areas that are not wired for service or that might only need the bandwidth for a few days, such as fairs, festivals or other community events. Future development may include partnerships with communities for machine to machine applications, such as traffic cameras, public venue security, smart grid connectivity and public safety applications with our local police departments. OnWav is also exploring a partnership with local school systems to allow low income families that are currently unable to afford broadband service to use the service to enable a low cost educational resource. OnWav intends to expand the network coverage outside the grant defined areas to ensure sustainability into the future. | 8 | 0 | 0 | 208 | 8 | 0 | 3 | 7 | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav has finalized the legal paperwork, however the final payment will be completed during the closeout period. The fiber is active and in use by OnWav's network. | N/A | N/A | OnWav has an initial IRU and amendments for access to 208 miles of existing dark fiber to use as part of the planned 216 mile network providing Middle Mile backhaul between OnWav's Last Mile towers. | Because of OnWav's change from a Microwave system to a fiber system, fewer new network miles will be deployed as OnWav will be largely taking advantage of existing dark fiber. OnWav's new miles have now been constructed. OnWav has finalized the legal paperwork, however the final payment will be completed during the closeout period. The fiber is active and in use by OnWav's network. | Because of OnWav's change from a Microwave system to a fiber system, no new wireless links will be deployed as OnWav will be taking advantage of existing dark fiber and new fiber construction | OnWav has completed construction of all three of OnWav's planned new towers. | Because of OnWav's change from a Microwave system to a fiber system, fewer interconnection points will be created. OnWav has deployed six potential interconnection points, five tower sites and a data center location. | 2 | 0 | 8 | Twin Lakes Telephone Cooperative Twin Lakes Communications These represent entities which OnWav has signed agreements in order provide last-mile (wireless) services. | [REDACTED] | OnWav has not designated a third party to operate any of its network. OnWav will operate and manage the entire network internally. | 2 | 0 | 0 | 2 | OnWav has signed agreements for 2 wholesaler agreements. | N/A | N/A | OnWav currently has agreements in place to provide wholesale customers 4Mbps/1Mbps and 8Mbps/2Mbps. There are currently no wholesale customers using this service. | 154 | 154 | 0 | 10 | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, Jamestown, and Livingston. OnWav has turned up CAI customers in all six markets. OnWav is providing a Backup service to these CAIs. | OnWav has completed sites in the towns of Allardt, Byrdstown, Celina, Gainesboro, Jamestown, and Livingston. OnWav has turned up CAI customers in all six markets. | N/A | OnWav has 10 different speed tiers being used by customers. The speed tiers in usage are: 16Mbps/2Mbps (3 CAIs), 12Mbps/1Mbps (6 CAIs), 10Mbps/1Mbps (24 CAIs), 8Mbps/1Mbps (40 CAIs), 6Mbps/1Mbps (20 CAIs), 4Mbps/1Mbps (20 CAIs), 3Mbps/1Mbps (4 CAIs), 2Mbps/1Mbps (29 CAIs), 1Mbps/1Mbps (3 CAIs) 1Mbps/256 Kbps (5 CAI) | 0 | 0 | 0 | 0 | 0 | OnWav's network completed construction, however no households have yet been offered service. This may change post-grant. | OnWav's network completed construction, however no households have yet been offered service. This may change post-grant. | OnWav's network completed construction, however no households have yet been offered service. This may change post-grant. | N/A | OnWav's network completed construction, however no households have yet been offered service. This may change post-grant. | 0 | 0 | 0 | 0 | 0 | OnWav's network completed construction, however no businesses have yet been offered service. This may change post-grant. | OnWav's network completed construction, however no businesses have yet been offered service. This may change post-grant. | OnWav's network completed construction, however no businesses have yet been offered service. This may change post-grant. | N/A | OnWav's network completed construction, however no businesses have yet been offered service. This may change post-grant. | OnWav has not yet made any special offerings. | FALSE | As of the end of Q1 2013, the policies had been finalized and are posted to OnWav's website. | All grant activities are complete, OnWav will complete grant closeout during the upcoming grant closeout period: - Deployment - OnWav has already completed installation of its WiMAX last-mile network. No further activities are required. - Deployment - OnWav has already turned-up the entire fiber middle-mile network. No further activities are required. - CAIs - OnWav has already activated all 154 CAIs on the network. - Closeout - OnWav will closeout the remaining open contracts with its vendors and receive and pay final invoices. - Closeout - OnWav will prepare all NTIA required closeout documentation during the closeout period. This includes documenting both personal and real property acquired during the course of the grant, as well as filing a Covenant of Use for the land purchased for OnWav's three new towers. - Closeout - OnWav will compile and document the network created during the grant and ensure adequate records are kept. | ONWAV INC. | As expected, OnWav experienced a challenge with contractual closeout processes (testing, inspection, documentation). OnWav has completed all testing and inspection, and is in the process of completing all closeout documentation for it's open contracts. Two of the locations OnWav had previously listed as served CAIs are no longer being listed as served CAIs by OnWav: One has since closed and was removed from our CAI list in a September 2013 CAI Change AAR. The other had some uncertainty of its current operational status as a valid CAI and in order to remain conservative it was also removed in the September 2013 AAR. As a result, we are not reporting them as subscribers. OnWavâ€™s final total subscribers are 154 CAIs (126 from Q2 2013, minus 2 dropped, plus 30 added Q3 2013) | A potential challenge facing OnWav in the next quarter during the closeout process is compilation of operational reference documentation for the network. OnWav will need to spend significant time validating the records of equipment acquired through the grant and ensuring that all equipment is accounted for in the operational reference guide.
NT10BIX5570081 | 2010 | Q4 | Q4 - 2010 | Completed and submitted Baseline Plan to National Telecommunications and Information Administration (NTIA), for entire project. Baseline accepted. Completed tasks related to optimizing planned fiber routes in Ward 8; finalized locations of ten planned core mega-point-of-presence (mega-POP) locations; and prioritized placements of core fiber ring routes and access loop routes, to maximize proximity to planned community anchor institutions. Focus is on under-served areas in District's Wards 8, 7 and 5. Began prioritization and scheduling of installation of Community Anchor Institutions. Conducted DC-CAN Last-Mile Partner and Carrier Symposium, to assess needs of possible partners and wholesale carriers which might use DC-CAN. Issued Request for Information (RFI) to possible last-mile partners and wholesale carriers, for them to identify needs. Pre-solicitation has begun for initial fiber placement. Continued pricing studies, for DC-CAN service offerings. Administratively, two achievements. First, the DC-CAN project received full spending approval from the District of Columbia Council. Second, the fiber installation contract extension is in place. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Consistent with Baseline. | N/A | N/A | N/A | Consistent with Baseline. | Consistent with Baseline. | N/A | Consistent with Baseline. | 0 | 0 | 0 | No wholesale or last-mile partner agreements have been signed this quarter. Cumulative partner total is zero. | DC-Net is still working on final product catalog and final pricing for all DC-CAN products and services. This is expected to be complete in the upcoming quarter, ending March 2011. | District of Columbia Government will own all the fiber assets installed by this project. As a cabinet-level Agency of the District of Columbia Government, the Office of the Chief Technology Officer (OCTO) is designated as the technology organization providing services to District Agencies. OCTO's DC-Net unit will operate the DC-CAN network, as build is completed, and once finished. Only DC-Net will be responsible for network operations; some third-parties may participate in performing operations tasks, as sub-contractors to DC-Net. | 0 | 0 | 0 | 0 | Consistent with Baseline. | Consistent with Baseline. | N/A | Not yet available. | 0 | 0 | 0 | 0 | Consistent with Baseline. | Consistent with Baseline. | Consistent with Baseline. | Not yet available. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings have been identified. | FALSE | OCTO's DC-NET remains operating entity for fiber network within District of Columbia Government. | DC-CAN will install first three (3) miles of new fiber; install five (5) new community anchors (2 charter schools, 2 health centers, 1 senior center); upgrade five (5) community anchors (all public safety: Metropolitan Police Department sites); continue network build; continue network design. In addition, DC-CAN will finalize pricing for offered services. | District of Columbia Government | DC-CAN secured spending approval on the grant funding from District of Columbia Council in October 2010. DC-CAN also obtained contract extension with the fiber installation vendor. Fiber installation will begin next quarter. | No challenges or issues are anticipated during the quarter ending March 2011. We expect to install fiber, add and upgrade community anchors, and prepare for later installation of inter-connection locations, all per the Baseline Plan.
NT10BIX5570081 | 2011 | Q1 | Q1 - 2011 | Districtâ€™s Office of the Chief Technology Officer (OCTO)â€™s DC-Net held its first ground breaking event involving placement of loop (distribution) fiber in Ward 8. The event was hosted by the CTO and Deputy CTO of the District of Columbia, and attended by Washington DC Mayor and the NTIA Program Director. To date on the DC-CAN initiative, nearly 5.5 miles of fiber has been placed., consisting of one mile of loop fiber supporting community anchor institutions and 4.5 miles of backbone fiber between the first two major inter-connection hub locations that will ultimately interconnect high-speed internet service providers in Wards 7 and 8. We have also upgraded nine public safety locations, resulting in significant improvements in bandwidth availability from 100 Mbps to a full 1 Gbps capacity. We received eight responses to Requests for Information (RFI) for possible high-speed internet access partners and wholesale carriers for possible DC-CAN use. DC-Net has met with three respondents so far for further discussion, for possible participation. DC-Net is collating a composite set of requirements, for inclusion in standard agreements. Drafts of the DC-CAN services catalog have been developed. Final pricing is expected for next quarter. | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 9 | DC-Net has installed five+ (5.5) miles of new fiber, against baseline target of three (3) miles. | N/A. | N/A. | N/A. | DC-Net has installed five+ (5.5) miles of new fiber, against baseline target of three (3) miles. | New wireless links are planned to be installed only at new Anchors. We had anticipated five new anchors, and are in process of finalizing agreements prior to installation. | N/A. | DC-Net has upgraded equipment at nine (9) public safety sites, against plan of five (5) upgrades through the quarter. | 0 | 0 | 0 | No wholesale partners enrolled as of March 31. No last-mile partners signed as of March 31. | N/A | OCTO's DC-Net will operate the network. | 0 | 0 | 0 | 0 | No variance to Baseline. | No variance to Baseline. | N/A | N/A | 9 | 0 | 9 | 1 | Through the quarter, DC-Net had expected a total of ten (10) anchors, and have upgraded nine (9), which are fully operational. | Through the quarter, DC-Net had expected a total of five (5) new anchors, which are in final negotiation prior to installation. | Through the quarter, DC-Net had expected to upgrade five (5) existing anchors, and has completed nine (9). | 1 Gbps is DC-Net's current offered speed, until DWDM equipment installed and core ring is fully operational. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A, at this time. | FALSE | N/A. | For DC-CAN, DC-Net will: a. Install an additional seven (7) miles of new fiber b. Install twenty (20) new community anchors c. Upgrade an additional eleven (11) public safety and library anchors. More generally, DC-CAN will continue network planning and network design. DC-Net will publish final DC-CAN pricing and services catalogs. | District of Columbia Government | As a government entity vigorously seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). Although this critical function has spent dollars totaling $117K (grant, match) to the DC-CAN initiative; an additional $1.3M worth of equipment orders are currently working their way through this cycle. The combined total closely parallels the 6% expenditure originally forecasted through March 31, 2011 (Q3). | No challenges anticipated.
NT10BIX5570081 | 2011 | Q2 | Q2 - 2011 | District of Columbia's Office of the Chief Technology Officer's (OCTO's) DC-Net (DC-Net) unit continues to make significant progress on the DC Community Anchor Network (DC-CAN). Approximately fourteen miles of DC-CAN backbone and distribution fiber installed this quarter. Eight new Community Anchors were installed, and are currently operational; an additional nine existing anchors have had new electronic equipment installed as part of DC-CAN upgrade program. DC-CAN has begun its community outreach program, with open-to-the-public meetings held in Wards 7 and 8. OCTO has received significant positive feedback from the two meetings, and demand for broadband is increasing. DC-CAN finalized its services and pricing guide, and has published these on the DC-CAN website to the general public. As a middle-mile project, DC-CAN is soliciting partners to provide high-speed internet services. DC-CAN has entered into one partnership agreement with a high-speed internet service provider, which will begin marketing broadband services to Wards 7 and 8. In addition, OCTO is currently in discussion with two additional organizations to become possible high-speed internet service provider partner with DC-CAN. DC-Net is adding personnel to ensure timely follow-up and negotiation with these organizations. | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 17 | DC-Net has installed fourteen (14) miles of new fiber, against the Baseline target of eleven (11) miles. | N/A | N/A | N/A | DC-Net has installed fourteen (14) miles of new fiber, against the Baseline target of eleven (11) miles. | Testing of specified outdoor wireless access points was completed during the quarter. Installation at the eight (8) operational anchors will be completed in the next quarter. | N/A | DC-CAN has upgraded equipment at nine (9) public safety sites, against a plan of twenty (20) upgrades through this quarter. DC-CAN has installed eight (8) new anchor sites, against plan of twenty (20) new anchor sites through this quarter. | 0 | 3 | 0 | No agreements have been executed. DC-CAN expects that the average negotiated term of any agreements will be three years (twelve quarters). | N/A | OCTO's DC-Net will operate the network. | 0 | 0 | 0 | 0 | Consistent with Baseline. | Consistent with Baseline. | Consistent with Baseline. | No variance to Baseline Plan. | 17 | 8 | 9 | 0 | DC-CAN is capable of serving seventeen (17) new or upgraded Anchors, vs. a Baseline target of forty (40) new or upgraded Anchors. | DC-CAN is providing service to eight (8) new Community Anchors, vs. a Baseline target of twenty (20) new Anchors. | DC-CAN has upgraded equipment at nine (9) existing Community Anchors, against a Baseline target of twenty (20) upgraded anchors. | Current subscribers' speed tiers range from 10 Gbps to 100 Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A, at this time. | FALSE | N/A. | For DC-CAN, DC-Net will: a. Install an additional thirty-one (31) miles of new fiber, for a planned total of forty-five (45) miles, consistent with baseline. b. Install forty-one (41) new community anchors, for a planned total of forty-nine (49) new, consistent with baseline. c. Upgrade an additional twenty-six (26) public safety and library anchors, for a planned total of thirty-five (35) upgrades, consistent with baseline. d. Install first two (2) mega-POP sites, consistent with baseline. e. Secure sole source approvals by District of Columbia Council for one (1) fiber installation vendor, consistent with baseline. All cumulative metrics remain consistent with planned baseline, as approved. | District of Columbia Government | As a government entity vigorously seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). Although this DC-CAN program is critically important to the District, and has spent dollars totaling $1,217K (grant, match) to the DC-CAN initiative; an additional $1.93 million worth of grant-funded equipment and fiber installation orders are currently working their way through the review and approval cycle. In addition, approximately $450K of District-funded equipment is pending imminent approval. The combined total closely parallels the 28% expenditure originally forecasted to be spent through June 30, 2011 (ARRA Q8; fiscal 2011-Q3). | Primary challenge is the timely approval of managed services contract vendor for the coming year.
NT10BIX5570081 | 2011 | Q3 | Q3 - 2011 | District of Columbia's Office of the Chief Technology Officer (OCTO's) DC-Net unit continues to make significant progress on the DC Community Access Network (DC-CAN). Approximately nine (9) additional miles of DC-CAN backbone and distribution fiber was installed this quarter, bringing total to twenty-three (23) miles. Nine (9) new DC-CAN Community Anchor Institutions (CAI's) were installed, and are operational, bringing total to seventeen (17). No additional existing Anchor sites were upgraded; the total remains at nine (9). DC-CANâ€™s outreach efforts continued, with public presentations in Wards 7, 8 and 5. DC-CAN continues to work with possible high-speed internet service providers, for last-mile services; two possible partners are currently in discussion. Two DC-CAN mega-point-of-presence (megaPOP) sites for partner inter-connection have been installed and are operational. The first link in DC-CAN's citywide 100 Gigabits per second (100G) network connected the District's Unified Communications Center (2720 Martin Luther King, Jr. Blvd in Ward 8) and the new Department of Employment Services headquarters (4056 Minnesota Avenue in Ward 7) six months after the District broke ground on the project in March, 2011. | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 2 | DC-Net has installed twenty-three (23) miles of new DC-CAN fiber, against the Baseline target of forty-five (45) miles. Cost expenditures proportional to fiber implementation budget estimate. We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. For the coming quarter, we anticipate completing installation of twenty-two (22) additional fiber miles, for a total of forty-five (45) miles installed. | N/A | N/A | N/A | DC-Net has installed twenty-three (23) miles of new DC-CAN fiber, against the Baseline target of forty-five (45) miles. Cost expenditures proportional to fiber implementation budget estimate. We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. For the coming quarter, we anticipate completing installation of twenty-two (22) additional fiber miles, for a total of forty-five (45) miles installed. | Installation of the wireless access points at the nineteen (19) new Community Anchor Institutions has not yet begun. District's Office of Planning, which serves as the State Historic Preservation Office (SHPO), is planning to review the permits, so they can provide guidance on proper placement of wireless access points on historic and significant buildings in the District. Once they have reviewed and provided placement guidance, we will proceed with installation. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | N/A | DC-CAN has completed implementation at two (2) inter-connect, open access, mega-point-of-presence (megaPOP) sites. Cost expenditures proportional to megaPOP implementation budget estimate. This is consistent with the Baseline target of two (2) inter-connect points. The prior quarter's report on this metric incorrectly reported CAI's installed. | 0 | 2 | 0 | No agreements have been executed, as of the close of the reporting period. OCTO expects to have one (1) last-mile partner under contract by the December 2011 reporting period. DC-Net expects that the average negotiated term of any agreements will be three years (twelve quarters). | N/A | OCTO's DC-Net will operate the network. | 0 | 0 | 0 | 0 | DC-CAN has executed no agreements with broadband wholesalers, last-mile providers, or high-speed internet access providers. Baseline had expected one (1) signed agreement to be in place. We are in negotiation phase. | Consistent with Baseline target of zero. | Consistent with Baseline target of zero. | Consistent with Baseline. | 26 | 17 | 9 | 0 | DC-CAN currently serves twenty-six (26) Community Anchor Institutions (CAI's), including seventeen (17) new and nine (9) upgraded CAI's. Baseline target had planned eighty-four (84) CAI's, including forty-nine (49) new and thirty-five (35) upgraded. CAI's. We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. As a consequence, we were unable to install fiber into new and upgraded sites, as had been planned. For the coming quarter, we intend to have an additional twenty-seven (27) new CAI's, for a total of forty-four (44) new CAI's served. There will be thirty-three (33) additional upgrades, for a total of forty-two (42) upgraded CAI's. In total, we intend to be serving eighty-six (86) new and upgraded CAI's by th | DC-CAN provides service to seventeen (17) new Community Anchors, vs. a Baseline target of forty-nine (49). We experienced significant delays with fiber procurement due to unavailability of raw materials caused by the earthquake in Japan; we have received a large order of fiber enabling us to proceed with installation. We also incurred delays due to inclement weather conditions, as District had a near-record rain this summer. As a consequence, we were unable to install fiber into new sites, as had been planned. For the coming quarter, we intend to have an additional twenty-seven (27) new CAI's, for a total of forty-four (44) new CAI's served. | DC-CAN has upgraded equipment and services at nine (9) existing Community Anchors, vs. a Baseline target of thirty-five (35). Hardware installed at the current hub locations must be replaced with new equipment which supports 1 Gbps; these orders are currently in the procurement pipeline, awaiting award. For the coming quarter, we intend to have thirty-three (33) additional upgrades, for a total of forty-two (42) upgraded CAI's served. | Current subscribers' speed tiers range from 10 Gbps to 100 Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional twenty-seven (27) new Community Anchor Institutions (CAI's), for a total of forty-four (44) new CAI's. Second, we will complete the upgrade of an additional thirty-three (33) existing CAI's, for a total of forty-two (42) upgraded CAI sites. Total anchors served (new and upgraded) will be eighty-six (86) by the end of the quarter. In addition, DC-CAN will install an additional twenty-two (22) miles of fiber, for a total of forty-five (45) miles installed. DC-CAN will have three (3) additional inter-connect mega-POP's operational, for a total of five (5). Finally, DC-CAN expects to execute its first Agreement with a high-speed internet service provider. | District of Columbia Government | As a government entity vigorously seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). This DC-CAN program is critically important to the District, and has spent dollars totaling $2.49 million (grant, match) on the DC-CAN initiative. Additional equipment has been received, and additional construction completed; however, invoices are pending payment. Once paid, overall project progress would be measured at approximately 30%. Spending rates will ramp up dramatically in the next three quarters, to meet the goal of "substantially complete" by June 2012. | Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may cause a longer-than-one-quarter catch-up period, to be consistent with baseline. DC-Net expects to be caught up to baseline by the June 2012 quarter, at which point DC-CAN will be at the 67% target for spending, and program metrics. Regarding selling DC-CAN services to potential Community Anchor Institutions (CAI's), DC-Net has adjusted its sales approach to focus on consortiums representing large groups of potential CAI's, gaining leverage in the sales process, and seeking support from credible leaders in affinity groups. We are also targeting CAI's which are not part of the originally-planned list, while ensuring they are still consistent with the terms of the award. Regarding projected spending for next quarter, OCTO's DC-Net has made the following adjustments as part of a project re-forecast. For next quarter: 1. Equipment expenditures will total almost eight (8) million dollars, with almost five-and-a-half (5.4) million dollars coming in District match contribution. Approximately four million worth of match equipment was received just before the end of the September quarter; however, delays in invoice delivery impacted ability to make quarter-end payment, and caused a perceived under-reporting situation. Completion of receipting, inventory and payment processes will be complete in the coming quarter. In addition, other equipment has been ordered, and some received, wh
NT10BIX5570081 | 2011 | Q4 | Q4 - 2011 | District of Columbia's Office of the Chief Technology Officer (OCTO's) DC-Net unit continues to make progress on the DC Community Access Network (DC-CAN). Approximately twenty-two (22) additional miles of DC-CAN backbone and distribution fiber was installed this quarter, bringing total to forty-five (45) miles. Fourteen (14) new DC-CAN Community Anchor Institutions (CAI's) were installed and are operational, bringing total to thirty-one (31). An additional twenty-four (24) existing Anchor sites were upgraded, bringing the total to thirty-three (33). DC-CANâ€™s outreach efforts continued, with public presentations in Wards 7, 8 and 5. DC-CAN continues to work with possible high-speed internet service providers, for last-mile services; currently in discussion with possible partners. To date, no agreements have been signed for these services. One additional DC-CAN mega-point-of-presence (megaPOP) sites for partner inter-connection were installed this quarter, bringing the total to three (3) sites. The new megaPOP is located at: Reeves Building (2000 14 St NW). In November, OCTO and DC-NET hosted the National Telecommunications and Information Administration (NTIA) program team for the DC-CAN Site Visit. In December, District of Columbia Mayor Gray and OCTO hosted, with NTIA representatives, a press conference with Mayor Gray, announcing DC-CANâ€™s 100 gigabit-per-second (Gbps) infrastructure. | 45 | 0 | 0 | 0 | 45 | 0 | 0 | 3 | DC-Net has installed forty-five (45) miles of new DC-CAN fiber, against the Baseline target of seventy-seven (77) miles. Cost expenditures proportional to fiber implementation budget estimate. Due to the delays in fiber availability, network build has been held back behind what was expected during baseline planning. However, DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of sixty-five (65) miles installed. | N/A | N/A | N/A | DC-Net has installed forty-five (45) miles of new DC-CAN fiber, against the Baseline target of seventy-seven (77) miles. Cost expenditures proportional to fiber implementation budget estimate. Due to the delays in fiber availability, network build has been held back behind what was expected during baseline planning. However, DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of sixty-five (65) miles installed. | Installation of the wireless access points at the nineteen (19) new Community Anchor Institutions has not yet begun. DC-Net has reviewed all the new and upgraded anchors, and confirmed which anchors can have wireless access points (WAPs) installed this quarter; this is the case for anchors whose property has no historic value. For those which require permits, we will begin permit applications, which will route through the District's Office of Planning (OP). OP, which serves as the State Historic Preservation Office (SHPO), will review the permits, and provide guidance on proper placement of WAPs on historic and significant buildings in the District. Once they have reviewed and provided placement guidance, we will proceed with installation. OCTO's DC-Net commits to deployment levels of 30% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | N/A | DC-CAN has completed implementation at three (3) inter-connect, open access, mega-point-of-presence (megaPOP) sites. Cost expenditures proportional to megaPOP implementation budget estimate. This is on pace with the Baseline target of three (3) inter-connect points. | 0 | 2 | 0 | No agreements have been executed, as of the close of the reporting period. OCTO expects to have zero (0) last-mile partners under contract by the March 2012 reporting period. DC-Net expects that the average negotiated term of any agreements will be three years (twelve quarters). | N/A | OCTO's DC-Net will operate the network. | 0 | 0 | 0 | 0 | DC-CAN has executed no agreements with broadband wholesalers, last-mile providers, or high-speed internet access providers. Baseline had expected three (3) signed agreement to be in place. We are in negotiation phase. | DC-CAN has modified no agreements with broadband wholesalers, last-mile providers, or high-speed internet access providers. Baseline had expected one (1) upgraded partner agreement to be in place. We are in negotiation phase. | Consistent with Baseline target of zero. | Consistent with Baseline. | 64 | 31 | 33 | 5 | DC-CAN currently serves sixty-four (64) Community Anchor Institutions (CAI's), including thirty-one (31) new and thirty-three (33) upgraded CAI's. Baseline target had planned one hundred thirty-five (135) CAI's, including eighty-five (85) new and fifty (50) upgraded CAI's. The enrollment process has ramped up more slowly than originally planned, due to internal reviews at prospective anchors. The enrollment process is realizing results, and anchor sign-ups improved significantly in the last quarter. We expect that momentum to continue. For the coming quarter, we intend to have an additional forty-five (45) new CAI's, for a total of seventy-six (76) new CAI's served. There will also be twenty (20) additional upgrades, for a total of fifty-three (53). In total, we intend to be serving one hundred twenty-nine (129) new and upgraded anchors. | DC-CAN currently serves thirty-one (31) new Community Anchor Institutions (CAI's). Baseline target had planned eighty-five (85) new CAI's. DC-CAN will be caught up with new community anchor targets by quarter ending June 2012. The enrollment process has ramped up more slowly than originally planned. However, the enrollment process is realizing results, and anchor sign-ups improved significantly in the last quarter. We expect that momentum to continue. For the coming quarter, we intend to have an additional forty-five (45) new CAI's, for a total of seventy-six (76) new CAI's served. | DC-CAN currently serves thirty-three (33) upgraded CAI's. Baseline target had planned fifty (50) upgraded CAI's. DC-CAN will be caught up with upgraded community anchor targets by quarter ending June 2012. For the coming quarter, we intend to upgrade an additional twenty (20) upgraded CAI's, for a total of fifty-three (53) upgrades by the end of the quarter. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 60. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 1. Total = 64 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional forty-five (45) new Community Anchor Institutions (CAI's), for a total of seventy-six (76) new CAI's. Second, we will complete the upgrade of an additional twenty (20) existing CAI's, for a total of fifty-three (53) upgraded CAI sites. Total anchors served (new and upgraded) will be one hundred twenty-nine (129) by the end of the quarter. In addition, DC-CAN will install an additional twenty (20) miles of fiber, for a total of sixty-five (65) fiber miles installed. DC-CAN will have one (1) additional inter-connect mega-POP's operational, for a total of four (4). Finally, DC-CAN expects to continue to negotiate Agreements with high-speed internet service providers; however, we do not expect any signed agreements. | District of Columbia Government | As a government entity vigorously seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). This DC-CAN program is critically important to the District, and has spent over $7.9 million (grant, match) on the DC-CAN initiative. | Delays in the DC-CAN project caused by fiber procurement and internal delays in community anchor decision processes to convert to DC-CAN from their existing providers may cause a longer-than-one-quarter catch-up period, to be consistent with baseline. DC-Net expects to be caught up to baseline spend by the June 2012 quarter, at which point DC-CAN will be at the 67% target. Regarding deploying DC-CAN services to potential Community Anchor Institutions (CAI's), DC-Net has adjusted its outreach and enrollment approach to focus on consortia representing large groups of potential CAI's, gaining leverage in the enrollment process, and seeking support from credible leaders in affinity groups. DC-CAN is also targeting CAI's which are not part of the originally-planned list, while ensuring they are still consistent with the terms of the award. DC-CAN will seek formal NTIA approval of the proposed changes for community anchors and routes this quarter. Regarding projected spending for next quarter, OCTO's DC-Net has made the following adjustments as part of a project re-forecast. For next quarter: 1. Equipment expenditures will total over eight ($8 MM) million dollars, with over four ($4 MM) million dollars coming in District match contribution. OCTO's DC-Net commits to spending levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for equipment procurement. 2. Match proportionality was met this quarter. DC-Net expects to sustain this for all future repor
NT10BIX5570081 | 2012 | Q1 | Q1 - 2012 | District of Columbia's Office of the Chief Technology Officer (OCTO's) DC-Net unit continues to make significant progress on the DC Community Access Network (DC-CAN). The addition of twenty-two (22) miles of backbone and distribution fiber brings the projectâ€™s infrastructure deployment to a cumulative total of sixty-seven (67) miles. Similarly, improvement was also noted in the areas of new community anchor institutions and upgrades of current DC-Net sites. New CAIs now number forty-nine (49) as eighteen (18) new locations were made fully operational, while upgrades now total fifty-two (52) following the upgrade of nineteen (19) existing anchors. No new points of interconnection (POI) were installed this quarter, maintaining the operational POI total at three (3). No new partner agreements were signed. DC-Netâ€™s outreach efforts continued in Wardâ€™s 5, 7, and 8 with additional public presentations and several individual meetings held with anchors showing keen interest in the flexibility, security, and overall architectural design of the network. Although no formal agreements have been reached, discussions also continue with last mile service providers experienced in the deployment of high speed connectivity to residential and commercial areas. | 67 | 0 | 0 | 0 | 67 | 0 | 0 | 3 | DC-Net has installed sixty-seven (67) miles of new DC-CAN fiber, against the Baseline target of eighty-eight (88) miles. Cost expenditures proportional to fiber implementation budget estimate. While network build had been slow initially due to earlier delays in fiber availability, network build has been accelerating. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of eighty-seven (87) miles installed. | N/A | N/A | N/A | DC-Net has installed sixty-seven (67) miles of new DC-CAN fiber, against the Baseline target of eighty-eight (88) miles. Cost expenditures proportional to fiber implementation budget estimate. While network build had been slow initially due to earlier delays in fiber availability, network build has been accelerating. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of eighty-seven (87) miles installed. | DC-Net will install the first twenty (20) wireless access points at community anchors (CAIs) for the quarter ending June 30, 2012. These CAIs require no permits, as the anchor location has no recorded historic value, as noted in the State Historic Preservation Office (SHPO) database. For those which require permits, DC-Net will begin permit applications, which will route through the District's Office of Planning (OP), which also serves as the State Historic Preservation Office (SHPO). OP will review the permits, and provide guidance on proper placement of WAPs on historic and significant buildings in the District. Once they have reviewed and provided placement guidance, we will proceed with installation. All DC-CAN wireless links will be fully complete by June 2013. See "Project Indicators (Next Quarter)" for assessment against "Significantly Complete" targets for June 2012. | N/A | DC-CAN has completed implementation at three (3) open access points of inter-connection. Cost expenditures proportional to POI implementation budget estimate. This is on pace with the Baseline target of three (3) interconnect points. | 0 | 2 | 0 | No agreements have been executed, as of the close of the reporting period, as forecast last period. DC-Net expects that the average negotiated term of any agreements will be three years (twelve quarters). | N/A | OCTO's DC-Net unit will operate the network. | 0 | 0 | 0 | 0 | DC-CAN has executed no agreements with broadband wholesalers, last-mile providers, or high-speed internet access providers. Baseline had expected two (2) signed agreement to be in place. The first signed agreement with new wholesalers or last-mile partners will be executed by June 30, 2012. | DC-CAN has no existing agreements with broadband wholesalers, or high-speed internet access providers for last-mile services. As there are no existing partners, there will be no upgrades to existing agreements. | Consistent with Baseline target of zero (0). | Consistent with Baseline. | 101 | 49 | 52 | 5 | DC-CAN currently serves one hundred one (101) Community Anchor Institutions (CAIs), including forty-nine (49) new and fifty-two (52) upgraded CAIs previously served by DC-Net. Baseline target had planned one hundred sixty-five (165) CAIs, including ninety-seven (97) new and sixty-eight (68) upgraded CAIs. The enrollment process has ramped up more slowly than originally planned, due to internal reviews at prospective anchors, and their long-term commitments to other carriers. Both factors have impaired the rate of CAI enrollment. However, the past quarter has shown great promise, and we expect that momentum to continue. For the coming quarter, we intend to have an additional forty-three (43) new CAIs, for a total of ninety-two (92) new CAIs served. There will also be sixteen (16) additional upgrades, completing DC-CAN's commitment of sixty-eight (68) anchors. In total, we intend to be serving one hundred sixty (160) new and upgraded anchors. | DC-CAN currently serves forty-nine (49) new Community Anchor Institutions (CAIs). Baseline target had planned ninety-seven (97) CAIs. The enrollment process has ramped up more slowly than originally planned, due to internal reviews at prospective anchors, and their long-term commitments to other carriers. Both factors have impaired the rate of CAI enrollment. However, the past quarter has shown great promise, and we expect that momentum to continue. For the coming quarter, we intend to have an additional forty-three (43) new CAIs, for a total of ninety-two (92) new CAIs served. | DC-CAN currently serves fifty-two (52) upgraded CAIs. Baseline target had planned all committed sixty-eight (68) upgrades to be complete this quarter. DC-CAN will complete the commitment of upgraded community anchors by this coming quarter, ending June 2012. For the coming quarter, DC-CAN will upgrade the final sixteen (16) existing anchors, completing the project commitment of sixty-eight (68) upgraded community anchors. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 93. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 101 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional forty-three (43) new Community Anchor Institutions (CAIs), for a total of ninety-two (92) new CAIs. DC-CAN will complete the project commitment of upgraded CAIs, upgrading the final sixteen (16) anchors, to bring the total to sixty-eight (68). Total anchors served will be one hundred sixty (160), or 55% of the project CAI commitment of two hundred ninety-one (291). DC-CAN will commence deployment of wireless access points to operational anchors, and will have a total of twenty (20) installed. DC-CAN will have at least one (1) additional point of inter-connection (POI) operational, bringing the total to four (4) POIs. In addition, DC-CAN will install an additional twenty (20) miles of fiber, for a total of eighty-seven (87) fiber miles installed. This quarter, DC-CAN also expects to receive its next order of fiber for installation. Next, DC-CAN will have its first signed partner agreement executed, for high-speed internet service provision to households. Negotiations with other possible partners will continue. Finally, DC-CAN hopes to have both its submitted route modifications approved by NTIA. This will provide many additional service opportunities for new anchors. In summary, for the coming quarter, against the "significantly complete" (or 2/3) target, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Spent 56% of overall project budget, and 51% of awarded federal grant b. One-hundred sixty (160) anchors installed, or 55%, of committed project total of two hundred ninety-one (291) CAIs - including ninety-two (92) new CAIs (of 223), and all sixty-eight (68) planned CAI upgrades c. Four (4) points of inter-connection (POI) installed, or 40% of committed project total of ten (10) d. Eighty-seven (87) miles of fiber installed, or 51%, of committed project total of one hundred seventy-three (173) miles e. Twenty (20) wireless access points (WAPs) installed, or 7%, of committed project total of two hundred ninety-one (291) f. One (1) executed partner agreement, or 17%, of committed project total of six (6). | District of Columbia Government | As a government entity seeking the best value for all dollars expended, any major purchase requires close review and competitive bidding processes performed by our Office of Contracts and Procurements (OCP). | The only concern is the timeliness of the approvals of the submitted Route Modifications is not approved.
NT10BIX5570081 | 2012 | Q2 | Q2 - 2012 | DC-Net, within the Districtâ€™s Office of the Chief Technology Officer (OCTO), continues to make significant progress on the DC Community Access Network District (DC-CAN). This program is committed to building broadband infrastructure to positively change the lives of our constituency. This quarter's exceptional performance includes installation of twenty-three (23) miles of backbone and loop fiber brings the deployment to ninety (90) miles. DC-CAN received another large order of fiber for installation, sufficient to install another forty (40) linear miles of fiber. Regarding Community Anchors, DC-CAN installed another forty-six (46) new anchors and upgraded five (5) existing sites, bringing the new and upgraded anchor totals to ninety (90) and sixty-one (61), respectively. The one hundred fifty-one (151) anchors served is more than half the final goal of 291. [ During the quarter, we reviewed all CAI records to assure data integrity, and discovered that five (5) CAIs had previously been classified incorrectly, reporting them as new CAIs, rather than upgrades. We also discovered one duplicate upgraded CAI reported. Restating the prior grant-to-date totals, through March 2012 quarter, we would correctly have reported forty-four (44) new and fifty-six (56) upgraded CAIs, for a total of one hundred (100) CAIs served. Adding this quarter's forty-six (46) new and five (5) upgraded CAIs gives us the corrected total of ninety (90) new and sixty-one (61) upgraded CAIs. ] This quarter, the first nineteen (19) rooftop wireless access points are deployed and operational. While no contractual agreements have been finalized, discussions continue with several last mile providers experienced in the deployment of high speed connectivity to both residential and commercial areas. Finally, with the addition of two (2) â€œmeet-meâ€ locations completed, a total of five (5) strategic inter-connection points are now available. Other accomplishments included approvals received from National Telecommunications and Information Administration (NTIA) on two sets of proposed route modifications, modifying the list of CAIs which can be installed. DC-Netâ€™s outreach efforts continued in Wardâ€™s 5, 7, and 8 with additional public presentations and several individual meetings held, with multi-site anchors showing keen interest in the flexibility, security, and architectural design of the network. We expect this enthusiasm will continue as the DC-CAN platform continues to traverse the Districtâ€™s footprint. | 90 | 0 | 0 | 0 | 90 | 19 | 0 | 5 | DC-Net has installed ninety (90) miles of new DC-CAN fiber, against the Baseline target of one hundred eleven (111) miles. Cost expenditures are consistent with fiber implementation budget estimate. While network build had been slow initially due to earlier delays in fiber availability, we have received an additional fiber shipment, and network build has been accelerating. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of one hundred ten(110) miles installed. | N/A | N/A | N/A | DC-Net has installed ninety (90) miles of new DC-CAN fiber, against the Baseline target of one hundred eleven (111) miles. Cost expenditures are consistent with fiber implementation budget estimate. While network build had been slow initially due to earlier delays in fiber availability, we have received an additional fiber shipment, and network build has been accelerating. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of twenty (20) additional fiber miles, for a total of one hundred ten (110) fiber miles installed. | DC-Net installed the first nineteen (19) wireless access points (WAPs) at community anchor institutions (CAIs) for the quarter ending June 30, 2012. All DC-CAN wireless links will be fully complete by June 2013. See "Project Indicators (Next Quarter)". | No towers were planned as part of the project. | DC-CAN has completed implementation at five (5) open access points of inter-connection (POIs). Cost expenditures are consistent with POI implementation budget estimate. This is consistent with the Baseline target of five (5) interconnect points. | 0 | 2 | 0 | No agreements have been executed, as of the close of the reporting period, as forecast last period. DC-Net expects that the average negotiated term of any agreements will be three years (twelve quarters). | N/A | OCTO's DC-Net unit will operate the network. | 0 | 0 | 0 | 0 | DC-CAN has executed no agreements with broadband wholesalers, last-mile providers, or high-speed internet access providers. DC-CAN had expected at least one new wholesaler or last-mile partner agreement to be executed by end of June 2012. These negotiations are proving more complex than anticipate; negotiations continue. The target date for the first two signed agreements with new wholesalers or partners has been moved back to September 30, 2012. Baseline had expected three (3) signed agreement to be in place. | DC-CAN has no existing agreements with broadband wholesalers, or high-speed internet access providers for last-mile services. As there are no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had inadvertently listed two upgrades in the plan. | Consistent with Baseline. | Consistent with Baseline. | 151 | 90 | 61 | 5 | DC-CAN currently serves one hundred fifty-one (151) Community Anchor Institutions (CAIs), including ninety (90) new and sixty-one (61) upgraded CAIs previously served by DC-Net. Baseline plan had expected one hundred ninety-seven (197) CAIs, including one hundred twenty-nine (129) and sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to have an additional forty-two (42) new CAIs, for a total of one hundred thirty-two (132) served. There will also be the final seven (7) additional upgrades. completing DC-CAN's commitment of sixty-eight (68) anchors. In total, we intend to be serving two hundred (200) new and upgraded anchors. | DC-CAN currently serves ninety (90) new Community Anchor Institutions (CAIs). Baseline plan had expected one hundred twenty-nine (129) new CAIs. For the coming quarter, we intend to have an additional forty-two (42) new CAIs, for a total of one hundred thirty-two (132) new CAIs served. | DC-CAN currently serves sixty-one (61) upgraded Community Anchor Institutions (CAIs). Baseline plan had expected sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to upgrade the final seven (7) existing CAIs, for a total of sixty-eight (68) upgraded CAIs served. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 143. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 151 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional forty-two (42) new Community Anchor Institutions (CAIs), for a total of one hundred thirty-two (132) new CAIs served. DC-CAN will complete the project commitment of sixty-eight (68) upgraded CAIs, upgrading the final seven (7) anchors. Total anchors served will be two hundred (200), or 69% of the project CAI commitment of two hundred ninety-one (291). DC-CAN will continue deployment of wireless access points (WAPs) to operational anchors, installing an additional forty-one (41), for a total of sixty (60) installed and operational. DC-CAN will have at least two (2) additional points of inter-connection (POIs) operational, bringing the total to seven (7) POIs. In addition, DC-CAN will install an additional twenty (20) miles of fiber, for a total of one hundred ten (110) fiber miles installed. Next, DC-CAN will have its first two (2) signed partner agreements executed, for high-speed internet service provision to households. Negotiations with other possible partners are ongoing. In summary, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Spent 67% of overall project budget, and 67% of awarded federal grant; b. Two hundred (200) anchors installed, or 69%, of committed project total of two hundred ninety-one (291) CAIs, which will include one hundred thirty-two (132) new CAIs (of 223), and all sixty-eight (68) planned CAI upgrades; c. Seven (7) points of inter-connection (POI) installed, or 50% of committed project total of fourteen (14); d. One hundred ten (110) miles of fiber installed, or 64%, of committed project total of one hundred seventy-three (173) miles; e. Sixty (60) wireless access points (WAPs) installed, or 21%, of committed project total of two hundred ninety-one (291); f. Two (2) executed partner agreements, or 33%, of committed project total of six (6). | District of Columbia Government | This quarter, DC-CAN completed, and received NTIA approval on, two sets of route modifications. These route modifications eliminated some anchors originally in the baseline, but which no longer exist or are committed to other service providers in the context of longer-term contracts. These anchors have been replaced with other anchors. While the process for route modification approval took longer than we originally planned, there is now an accepted plan that will permit anchors to be installed more quickly in the coming quarters. DC-CAN installed the first set of wireless access points (WAPs) at community anchor institutions. | The only concern is obtaining completed, signed partner agreements with two wholesalers or last-mile partners.
NT10BIX5570081 | 2012 | Q3 | Q3 - 2012 | DC-Net, within the Districtâ€™s Office of the Chief Technology Officer (OCTO), continues to make significant progress on the DC Community Access Network District (DC-CAN). This program is committed to building broadband infrastructure to positively change the lives of our constituency. This quarter's installation of sixteen (16) miles of backbone and loop fiber brings the deployment to one hundred six (106). DC-Net installed another thirty (30) new DC-CAN Community Anchor Institutions (CAIs, or anchors), bringing the new anchor total to one hundred twenty (120), and completed three (3) more upgrades to existing anchors to bring the total upgrades to sixty-four (64). The one hundred eighty-four (184) anchors served is almost two-thirds of the final goal of 291. Twenty-six (26) additional wireless access points were installed, bringing the total to forty-five (45), and two (2) new points of inter-connection were installed, bringing the total to seven (7). OCTO executed its first DC-CAN partner agreement to provide high-speed internet access services as a last-mile partner. Other accomplishments included review by District's State Historic Preservation Office (SHPO) of the first one hundred fifty-one (151) anchors regarding placement of rooftop wireless access points. DC-Netâ€™s outreach efforts for DC-CAN continued in Wardâ€™s 5, 7, and 8 with additional public presentations and several individual meetings held, with multi-site anchors showing keen interest in the flexibility, security, and architectural design of the network. We expect this enthusiasm will continue as the DC-CAN platform continues to traverse the Districtâ€™s footprint. | 106 | 0 | 0 | 0 | 106 | 45 | 0 | 7 | DC-Net has installed one hundred six (106) miles of new DC-CAN fiber, against the Baseline target of one hundred twenty-seven (127). Per mile cost expenditures are consistent with fiber implementation budget estimate. Fiber installation has continued at an aggressive pace. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of nineteen (19) additional fiber miles, for a total of one hundred twenty-five (125) miles installed. | N/A | N/A | N/A | DC-Net has installed one hundred six (106) miles of new DC-CAN fiber, against the Baseline target of one hundred twenty-seven (127). Per mile cost expenditures are consistent with fiber implementation budget estimate. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of nineteen (19) additional fiber miles, for a total of one hundred twenty-five (125) fiber miles installed. | DC-Net installed an additional twenty-six (26) wireless access points (WAPs) at community anchor institutions (CAIs) for the quarter ending September 30, 2012, compared with a Baseline target of one hundred forty-five (145) at new CAIs. With approvals now received by State Historic Preservation Office (SHPO) , installations will be completed more quickly in the future. We are installing WAPs at locations requiring no permits, which have no historical interest, and require no further consultation with SHPO. All DC-CAN wireless links will be fully complete by June 2013. See "Project Indicators (Next Quarter)". | N/A | DC-CAN has completed implementation at two (2) more open access points of inter-connection (POIs), bringing the total to seven (7). Cost expenditures are consistent with POI implementation budget estimate. This is consistent with the Baseline target of seven (7) interconnection points. | 1 | 2 | 12 | DC Access, a local internet service provider, is the first high-speed internet partner, providing last-mile services. | N/A | OCTO's DC-Net unit will operate the network. | 1 | 0 | 0 | 0 | DC-CAN has executed its first agreements with a high-speed internet access provider, to provide internet services over the last mile to local businesses and individuals. Negotiations are proving more complex than originally planned, but they continue with two (2) additional possible partners. Baseline had expected three (3) signed agreement with new providers to be in place. | DC-CAN has no existing agreements with broadband wholesalers, or high-speed internet access providers for last-mile services. As there are no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had inadvertently listed two upgrades in the plan. | Consistent with Baseline. | Consistent with Baseline. | 184 | 120 | 64 | 5 | DC-CAN currently serves one hundred eighty-four (184) Community Anchor Institutions (CAIs), including one hundred twenty (120) new and sixty-four (64) upgraded CAIs previously served by DC-Net. Baseline plan had expected two hundred thirteen (213) total CAIS, comprised of one hundred forty-five (145) new and sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to have an additional thirty-five (35) new CAIs, for a total of one hundred fifty-five (155) served. There will also be the final four (4) additional upgrades. completing DC-CAN's commitment of sixty-eight (68) anchors. In total, we intend to be serving two hundred twenty-three (223) new and upgraded anchors. | DC-CAN currently serves one hundred twenty (120) new Community Anchor Institutions (CAIs). Baseline plan had expected one hundred forty-five (145) new CAIs. For the coming quarter, we intend to have an additional thirty-five (35) new CAIs, for a total of one hundred fifty-five (155) new CAIs served. | DC-CAN currently serves sixty-four (64) upgraded Community Anchor Institutions (CAIs). Baseline plan had expected sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to upgrade the final four (4) existing CAIs, for a total of sixty-eight (68) upgraded CAIs served. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 176. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 184 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional thirty-five (35) new Community Anchor Institutions (CAIs), for a total of one hundred fifty-five (155) new CAIs served. DC-CAN will complete the project commitment of sixty-eight (68) upgraded CAIs, upgrading the final four (4) anchors. Total anchors served will be two hundred twenty-three (223), or 77% of the project CAI commitment of two hundred ninety-one (291). DC-CAN will continue deployment of wireless access points (WAPs) to operational anchors, installing an additional thirty-five (35), for a total of eighty (80), or 27%, installed and operational. DC-CAN will have at least two (2) additional points of inter-connection (POIs) operational, bringing the total to nine (9) POIs. In addition, DC-CAN will install an additional nineteen (19) miles of fiber, for a total of one hundred twenty-five (125) fiber miles installed. DC-CAN will make its first partner, DC Access, fully operational, to provide last-mile services. Negotiations with other possible partners continue. In summary, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Spent 73% of overall project budget, and 72% of awarded federal grant; b. Two hundred twenty-three (223) anchors installed, or 77%, of committed project total of two hundred ninety-one (291) CAIs, which will include one hundred fifty-five (155) new CAIs (of 223), and all sixty-eight (68) planned CAI upgrades; c. Nine (9) points of inter-connection (POI) installed, or 64% of committed project total of fourteen (14); d. One hundred twenty-five (125) miles of fiber installed, or 72%, of committed project total of one hundred seventy-three (173) miles; e. Eighty (80) wireless access points (WAPs) installed, or 27%, of committed project total of two hundred ninety-one (291); f. One (1) executed partner agreement, or 17%, of committed project total of six (6). g. Planned match spend for the project next quarter will be at 31.3%, compared to committed 30.3% match proportionality target. For specific numbers, see the Anticipated Actuals columns in the table on the last page. | District of Columbia Government | This quarter, DC-CAN continue installation progress. One factor that impeded our spending progress was the planned early shutdown of the Treasury reimbursement system on September 14. Now that system access is restored, spending and reimbursement will continue. State Historic Preservation Office (SHPO) review of the proposed anchor sites for guidance on placement of wireless access points (WAPs) took longer than expected. However, over one hundred fifty sites have been reviewed, and we are proceeding with WAP installation at sites SHPO has expressed no interest in, while permits are being submitted to SHPO for sites of interest. | The only two concerns are completing negotiations with additional last-mile partners; and timely completing a budget revision this quarter.
NT10BIX5570081 | 2012 | Q4 | Q4 - 2012 | DC-Net, within the Districtâ€™s Office of the Chief Technology Officer (OCTO), continues to make significant progress on the DC Community Access Network District (DC-CAN). This program is committed to building broadband infrastructure to positively change the lives of our constituency. This quarter's installation of twenty-four (24) miles of backbone and loop fiber brings the deployment to one hundred thirty (130). DC-Net installed another twenty-five (25) new DC-CAN Community Anchor Institutions (CAIs, or anchors), bringing the new anchor total to one hundred forty-five (145), and completed the final four (4) upgrades to existing anchors, completing the planned sixty-eight (68) upgraded sites. The two hundred thirteen (213) anchors served is more than two-thirds the final goal of two hundred ninety-one (291). In addition, twenty-two (22) additional wireless access points were installed, bringing the total to sixty-seven (67). Finally, two (2) additional new points of inter-connection were installed, bringing the total to nine (9). DC-CAN has made DC Access, its first high-speed internet service provider partner, fully operational. DC-Netâ€™s outreach efforts for DC-CAN continued in Wardâ€™s 5, 7, and 8 with additional public presentations and several individual meetings held, with multi-site anchors showing keen interest in the flexibility, security, and architectural design of the network. | 130 | 0 | 0 | 0 | 130 | 67 | 0 | 9 | DC-Net has installed one hundred thirty (130) miles of new DC-CAN fiber, against the Baseline target of one hundred forty-nine (149). Per mile cost expenditures are consistent with fiber implementation budget estimate. Fiber installation has continued at an aggressive pace. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of twenty-four (24) additional fiber miles, for a total of one hundred fifty-four (154) miles installed. | N/A | N/A | N/A | DC-Net has installed one hundred thirty (130) miles of new DC-CAN fiber, against the Baseline target of one hundred forty-nine (149) miles. Per mile cost expenditures are consistent with fiber implementation budget estimate. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of twenty-four (24) additional fiber miles, for a total of one hundred fifty-four (154) fiber miles installed. | DC-Net installed an additional twenty-two (22) wireless access points (WAPs) at community anchor institutions (CAIs) for the quarter ending December 31, 2012, bringing the total to sixty-seven (67), compared with a Baseline target of one hundred eighty-one (181) at new CAIs. With approvals now received by State Historic Preservation Office (SHPO), installations will be completed more quickly in the future. We are installing WAPs at locations requiring no permits, which have no historical interest, and require no further consultation with SHPO. All DC-CAN wireless links will be fully complete by June 2013. See "Project Indicators (Next Quarter)". | N/A | DC-CAN has completed implementation at two (2) more open access points of inter-connection (POIs), bringing the total to nine (9). Cost expenditures are consistent with POI implementation budget estimate. This is just behind the Baseline target of ten (10) inter-connection points. | 1 | 2 | 12 | DC Access, a local internet service provider, is the first high-speed internet partner providing last-mile services. | N/A | OCTO's DC-Net unit, which implemented DC-CAN, will operate the network. DC-Net is part of the awardee, and not a third party. Contact information is 202.727.2277. | 1 | 0 | 0 | 0 | DC-CAN has executed its first agreements with a high-speed internet access provider, to provide internet services over the last mile to local businesses and individuals. Negotiations are proving more complex than originally planned, but they continue with two (2) additional possible partners. Baseline had expected three (3) signed agreement with new providers to be in place. | DC-CAN has no existing agreements with broadband wholesalers, nor high-speed internet access providers for last-mile services. As there are no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had inadvertently listed two upgrades in the plan. | Consistent with Baseline. | Consistent with Baseline. | 213 | 145 | 68 | 5 | DC-CAN currently serves two hundred thirteen (213) Community Anchor Institutions (CAIs), including one hundred forty-five (145) new CAIs, as well as sixty-eight (68) upgraded CAIs previously served by DC-Net. Baseline plan had expected two hundred forty-nine (249) total CAIs, comprised of one hundred eighty-one (181) new and sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to have an additional thirty (30) new CAIs, for a total of one hundred seventy-five (175) new CAIs served. Along with the sixty-eight (68) completed upgrades, DC-CAN will have a total of two hundred forty-three (243) new and upgraded CAIs under contract. | DC-CAN currently serves one hundred forty-five (145) new Community Anchor Institutions (CAIs). Baseline plan had expected one hundred eighty-one (181) new CAIs. For the coming quarter, we intend to have an additional thirty (30) new CAIs, for a total of one hundred seventy-five (175) new CAIs served. | DC-CAN currently serves sixty-eight (68) upgraded Community Anchor Institutions (CAIs), consistent with the Baseline plan. We have completed all upgraded sites. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 205. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 213 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | For the next quarter, DC-CAN expects to install an additional thirty (30) new Community Anchor Institutions (CAIs), for a total of one hundred seventy-five (175) new CAIs served. Including the sixty-eight (68) upgraded CAI sites completed this quarter, DC-CAN projects total anchors served will be two hundred forty-three (243), or 84% of the project CAI commitment of two hundred ninety-one (291). DC-CAN will continue deployment of wireless access points (WAPs) to operational anchors, installing an additional thirty-four (34), for a total of one hundred one (101), or 45% of new CAIs, installed and operational. DC-CAN will have at least one (1) additional point of inter-connection (POIs) operational, bringing the total to ten (10). In addition, DC-CAN will install an additional twenty-four (24) miles of fiber, for a total of one hundred fifty-four (154) fiber miles installed, or 89% of project total. In summary, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Spent 86% of overall project budget, and 86% of awarded federal grant; b. Two hundred forty-three (243) anchors installed, or 84%, of committed project total of two hundred ninety-one (291) CAIs, which will include one hundred seventy-five (175) new CAIs (of 223); all sixty-eight (68) planned CAI upgrades are complete; c. Ten (10) points of inter-connection (POI) installed, or 71% of committed project total of fourteen (14); d. One hundred fifty-four (154) miles of fiber installed, or 88%, of committed project total of one hundred seventy-three (173) miles; e. One hundred one (101) wireless access points (WAPs) installed, or 45%, of committed project total of two hundred twenty-three (223); f. One (1) executed partner agreement, or 25%, of committed project total of four (4) new partner agreements. g. Planned match spend for the project next quarter will be at 30.4%, compared to committed 30.3% match proportionality target. For specific numbers, see the Anticipated Actuals columns in the table on the last page. | District of Columbia Government | This quarter, DC-CAN continued installation progress. State Historic Preservation Office (SHPO) review of the proposed anchor sites for guidance on placement of wireless access points (WAPs) took longer than expected. However, over one hundred ninety (190) sites have been reviewed, and we are proceeding with WAP installation at sites SHPO has expressed no interest in, while permits are being submitted to SHPO for sites of interest. | The only two concerns are completing negotiations with additional last-mile partners; and timely completing a budget revision this quarter.
NT10BIX5570081 | 2013 | Q1 | Q1 - 2013 | DC-Net, within the Districtâ€™s Office of the Chief Technology Officer (OCTO), continues to make significant progress on the DC Community Access Network District (DC-CAN). This program is committed to building broadband infrastructure to positively change the lives of our constituency. This quarter's installation of ten (10) miles of backbone and loop fiber brings the deployment to one hundred forty (140). DC-Net installed another seventeen (17) new DC-CAN Community Anchor Institutions (CAIs, or anchors), bringing the new anchor total to one hundred sixty-two (162); all sixty-eight (68) upgrade sites are complete. The two hundred thirty (230) anchors served is more than three quarters of the final goal of two hundred ninety-one (291). In addition, twenty-three (23) additional wireless access points were installed, bringing the total to ninety (90). Finally, one (1) additional new point of inter-connection were installed, bringing the total to ten (10). DC-CAN hosted a successful visit from the Department of Commerce's Office of the Inspector General (OIG). In addition, DC-CAN is supporting the District of Columbia's A-133 audit on the BTOP grant program. DC-Netâ€™s outreach efforts for DC-CAN continued in Wardâ€™s 5, 7, and 8 with additional public presentations and several individual meetings held, with multi-site anchors showing keen interest in the flexibility, security, and architectural design of the network. | 140 | 0 | 0 | 0 | 140 | 90 | 0 | 10 | DC-Net has installed one hundred forty (140) miles of new DCCAN fiber, against the Baseline target of one hundred fifty-three (153). Per mile cost expenditures are consistent with fiber implementation budget estimate. Fiber installation has continued at an aggressive pace. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of thirty-three (33) additional fiber miles, completing the installation of one hundred seventy-three (173) miles installed. | N/A | N/A | N/A | DC-Net has installed one hundred forty (140) miles of new DCCAN fiber, against the Baseline target of one hundred fifty-three (153). Per mile cost expenditures are consistent with fiber implementation budget estimate. Fiber installation has continued at an aggressive pace. DC-CAN's re-forecast of expected fiber installation remains on track, and this quarter's targets were met. We expect to meet future quarters' revised targets. For the coming quarter, we anticipate completing installation of thirty-three (33) additional fiber miles, completing the installation of one hundred seventy-three (173) miles installed. | DC-Net installed an additional twenty-three (23) wireless access points (WAPs) at community anchor institutions (CAIs) for the quarter ending March 31, 2013, bringing the total to ninety (90), compared with a Baseline target of one hundred eighty-one (181) at new and upgraded CAIs. With approvals now received by State Historic Preservation Office (SHPO), installations will be completed more quickly in the future. We are installing WAPs at locations requiring no permits, which have no historical interest, and require no further consultation with SHPO. One hundred fifty (150) DC-CAN wireless links will be fully complete by June 2013. DC-Can expects to be applying for a project extension thru September 30, 2013, to complete this program goal. (See "Project Indicators (Next Quarter)".) | N/A | DC-CAN has completed implementation at one (1) additional open access points of inter-connection (POIs), bringing the total to ten (10). Cost expenditures are consistent with POI implementation budget estimate. This is consistent with the Baseline target of ten (10) interconnection points. DC-Can expects to be applying for a project extension thru September 30, 2013, to complete this program goal. (See "Project Indicators (Next Quarter)".) | 1 | 2 | 12 | DC Access, a local internet service provider, is the first high-speed internet partner providing last-mile services. | N/A | OCTO's DC-Net unit, which implemented DC-CAN, will operate the network. DC-Net is part of the awardee, and not a third party. Contact information is 202.727.2277; DCNET@DC.Gov ; 655 15th Street, NW Washington DC 20005. | 1 | 0 | 0 | 1 | DC-CAN has executed its first agreements with a high-speed internet access provider, to provide internet services over the last mile to local businesses and individuals. Negotiations are proving more complex than originally planned, but they continue with two (2) additional possible partners. Baseline had expected three (3) signed agreement with new providers to be in place. | DC-CAN has no existing agreements with broadband wholesalers, nor high-speed internet access providers for last-mile services. As there had been no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had inadvertently listed two upgrades in the plan. | N/A | DC Access receives 1 Gbps. | 230 | 162 | 68 | 5 | DC-CAN currently serves two hundred thirty (230) Community Anchor Institutions (CAIs), including one hundred sixty-two (162) new CAIs, as well as sixty-eight (68) upgraded CAIs previously served by DC-Net. Baseline plan had expected two hundred forty-nine (249) total CAIs, comprised of one hundred eighty-one (181) new and sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to have an additional thirty (30) new CAIs, for a total of one hundred ninety-two (192) new CAIs served. Along with the sixty-eight (68) completed upgrades, DC-CAN will have a total of two hundred sixty (260) new and upgraded CAIs under contract and served. | DC-CAN currently serves one hundred sixty-two (162) new Community Anchor Institutions (CAIs). Baseline plan had expected one hundred eighty-one (181) new CAIs. For the coming quarter, we intend to have an additional thirty (30) new CAIs, for a total of one hundred ninety-two (192) new CAIs served. | DC-CAN currently serves sixty-eight (68) upgraded Community Anchor Institutions (CAIs), consistent with the Baseline plan. We have completed all upgraded sites. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 222. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 230 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | DC-CAN expects to apply for a project extension, proposing the grant program be extended through September 30, 2013, from the current grant expiration of June 30, 2013. The extra three months will permit completion of the program goals regarding Community Anchor Institutions (CAIs) and rooftop wireless access points (WAPs). For the next quarter, DC-CAN expects to install an additional thirty (30) new Community Anchor Institutions (CAIs), for a total of one hundred ninety-two (192) new CAIs served. Including the sixty-eight (68) upgraded CAI sites already completed, DC-CAN projects total anchors served will be two hundred sixty (260) new and upgraded CAIs. DC-CAN will continue deployment of wireless access points (WAPs) to operational anchors, installing an additional sixty (60), for a total of one hundred fifty (150) installed and operational. (Regarding this point, there are some anchors at which only fiber has been installed, but for which final contracts for services have not yet been established. As there is no equipment installed, DC-CAN is unable to install wireless access points (WAPs). Also, DC-CAN is pending approval on its final route modification, which will introduce new anchors at which WAPs may be installed. Finally, DC-CAN is pending final WAP placement review with District's State Historic Preservation Office.) DC-CAN will install the final four (4) additional points of inter-connection (POIs) operational, completing the commitment of fourteen (14). In addition, DCCAN will install the final thirty-three (33) miles of fiber, completing the commitment of one hundred seventy-three (173) fiber miles installed. In summary, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Secured a grant project extension through September 30, 2013. b. Spent 87% of overall project budget, and 87% of awarded federal grant; c. Two hundred sixty (260) anchors installed, or 89%, of committed project total, which will include one hundred ninety-two (192) new CAIs; all sixty-eight (68) planned CAI upgrades are already complete; d. Fourteen (14) points of inter-connection (POI) installed, or 100% of committed project total of fourteen (14); e. One hundred seventy-three (173) miles of fiber installed, or 100% of committed project total; f. One hundred fifty (150) wireless access points (WAPs) installed, or 52%, of committed project total of two hundred ninety-one (291); g. One (1) executed partner agreement, or 25%, of committed project total of four (4) new partner agreements. h. Planned match spend for the project next quarter will be at 30.3%, compared to committed 30.3% match proportionality target. For specific numbers, see the Anticipated Actuals columns in the table on the last page. | District of Columbia Government | This quarter, DC-CAN continued installation progress. State Historic Preservation Office (SHPO) review of the proposed anchor sites for guidance on placement of wireless access points (WAPs) is taking longer than expected. However, over two hundred ninety (290) sites have been reviewed, and we are proceeding with WAP installation at sites SHPO has expressed no interest in, while permits are being submitted to SHPO for sites of interest. | There are three possible risks or issues. First, securing a ninety-day (90-day) no-cost extension of the grant, through September 30, 2013. Second, timely approval by NTIA of proposed route modification #3 is essential to completing this plan. Finally, District's State Historic Preservation Office completed its final review of all possible anchor sites, consistent with SHPO Consultation Agreement. However, it is difficult to forecast whether all final approvals will be received in time to support the installation of the rooftop wireless access points. Therefore we forecast only one hundred fifty (150) of two hundred ninety-one (291) complete by the end of the grant period.
NT10BIX5570081 | 2013 | Q2 | Q2 - 2013 | DC-Net, within the Districtâ€™s Office of the Chief Technology Officer (OCTO), continues to make significant progress on the DC Community Access Network (DC-CAN). This program is committed to building broadband infrastructure to positively change the lives of our constituency. This quarter's installation of forty-six (46) miles of backbone and loop fiber brings the deployment to one hundred eighty-six (186). Regarding Community Anchors, DC-CAN installed another thirty (30) new anchors, bringing the new anchor total to one hundred and ninety-two (192); all sixty-eight (68) upgrade sites are complete, for a total of two hundred sixty (260) anchors. Thirty (30) additional wireless access points were installed, bringing the total to one hundred twenty (120), and one (1) new point of inter-connection were installed, bringing the total to eleven (11). Two (2) new partner agreements were signed with high-speed internet providers, bringing the total to three (3). OCTO completed the District's A-133 audit efforts on this grant. OCTO received an extension from National Telecommunications & Information Administration (NTIA) on the DC-CAN project to September 30, 2013. OCTO received approval from NTIA on its third and final route modification. | 186 | 0 | 0 | 0 | 186 | 120 | 0 | 11 | DC-Net has installed one hundred eighty-six (186) miles of new DC-CAN fiber, exceeding both the Baseline target and overall program goal of one hundred seventy-four (174) miles. Per mile cost expenditures are consistent with fiber implementation budget estimate. DC-CAN's expects to install an additional nine (9) miles of fiber this quarter, bringing the total to one hundred ninety-five (195) miles, over twenty (20) miles more than originally planned. | N/A | N/A | N/A | DC-Net has installed one hundred eighty-six (186) miles of new DC-CAN fiber, exceeding both the Baseline target and overall program goal of one hundred seventy-four (174) miles. Per mile cost expenditures are consistent with fiber implementation budget estimate. DC-CAN's expects to install an additional nine (9) miles of fiber this quarter, bringing the total to one hundred ninety-five (195) miles, over twenty (20) miles more than originally planned. | DC-Net installed an additional thirty (30) wireless access points (WAPs) at community anchor institutions (CAIs) for the quarter ending June 30, 2013, bringing the total to one hundred twenty (120), compared with a Baseline target of two hundred twenty-three (223) new CAIs. With all preliminary approvals now received by State Historic Preservation Office (SHPO), installations will be completed more quickly in the future. We are installing WAPs at locations requiring no permits, which have no historical interest, and require no further consultation with SHPO. With the approved project extension to September 30, two hundred twenty-three (223) wireless links will be fully operational by the end of the grant. To meet this goal, DC-CAN must timely secure final approval from SHPO at any remaining historical CAI locations, gain approval and access permission from landlords and other building stakeholders, and aggressively manage installation schedule. (In some earlier Performance Progress Reports (PPRs), DC-Net referenced a target of two hundred ninety-one (291) installed WAPs, rather than the two hundred twenty-three (223) target mentioned here. In the DC-CAN baseline, the commitment has always been 223 WAPs installed. However, in the original budget, we had reserved funds for 291 WAPs. In the active budget revision, currently in process, we are reducing the budget commitment to 223, matching the baseline commitment installation target.) | N/A | DC-CAN has completed implementation at one (1) additional open access points of inter-connection (POIs), bringing the total to eleven (11). Cost expenditures are consistent with POI implementation budget estimate. While the Baseline target of ten (10) points of inter-connection has been exceeded, an earlier approved route modification increased the number of inter-connection points to (14). The final three (3) sites will be installed and operational this coming quarter, ending September 30, 2013. | 3 | 2 | 12 | DC Access, a local internet service provider, is the first high-speed internet partner providing last-mile services. Networking for Future ("NFF"), a local internet service provider, offering last-mile services. Novation Broadband ("Novation"), a local internet service provider, offering last-mile services. | N/A | OCTO's DC-Net unit, which implemented DC-CAN, will operate the network. DC-Net is part of the awardee, and not a third party. Contact information is 202.727.2277; DCNET@DC.Gov ; 655 15th Street, NW Washington DC 20005. | 3 | 0 | 0 | 1 | This quarter, DC-CAN has executed an additional two (2) agreements with high-speed internet access providers, to offer internet services over the last mile to local businesses and individuals. Negotiations are proving more complex than originally planned, but they continue with two (2) additional possible partners. Baseline had expected four (4) signed agreements with new providers to be in place. | DC-CAN has no existing agreements with broadband wholesalers, nor high-speed internet access providers for last-mile services. As there had been no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had mistakenly listed two upgrades in the plan. | N/A | All three partners receive 1 Gbps service. | 260 | 192 | 68 | 5 | DC-CAN currently serves two hundred sixty (260) Community Anchor Institutions (CAIs), including one hundred ninety-two (192) new CAIs, along with sixty-eight (68) upgraded CAIs previously served by DC-Net. Baseline plan had expected two hundred ninety-one (291) total CAIs, comprised of two hundred twenty-three (223) new and sixty-eight (68) upgraded CAIs. For the coming quarter, we intend to complete all CAI installations, installing the final thirty-one (31) additional new CAIs, for a total of two hundred twenty-three (223) new CAIs served. Along with the sixty-eight (68) completed upgrades, DC-CAN will have its entire committed total of two hundred ninety-one (291) new and upgraded CAIs under contract and served. | DC-CAN currently serves one hundred ninety-two (192) new Community Anchor Institutions (CAIs). Baseline plan had expected two hundred twenty-three (223) new CAIs. For the coming quarter, we intend to complete all CAI installations, installing the final thirty-one (31) additional new CAIs, for a total of two hundred twenty-three (223) new CAIs served. | DC-CAN currently serves sixty-eight (68) upgraded Community Anchor Institutions (CAIs), consistent with the Baseline plan. All upgrade sites have been installed and are operational. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 252. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 260 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None, at this time. | FALSE | N/A | DC-CAN has received its project extension from National Telecommunication and Information Administration (NTIA), changing the end date for program execution to September 30, 2013. DC-CAN has also had its third and final route modification approved by NTIA. With the extension secured and the approval of the final route modification, OCTO is confident all committed program goals will be met or exceeded. For the final quarter, DC-CAN expects to install the final thirty-one (31) new Community Anchor Institutions (CAIs), for a total of two hundred twenty-three (223) new CAIs served. Including the sixty-eight (68) upgraded CAI sites already completed, DC-CAN projects total anchors served will be the committed two hundred ninety-one (291) new and upgraded CAIs. DC-CAN will continue deployment of wireless access points (WAPs), installing the remaining one hundred three (103) WAPs and bringing the total at new, operational anchors to two hundred twenty-three (223) WAPs. DC-CAN will install the final three (3) additional points of inter-connection (POIs) operational, completing the commitment of fourteen (14). In addition, DC-CAN will install an additional nine (9) miles of fiber, bringing total fiber installed to one hundred ninety-five (195) miles, far exceeding the commitment of one hundred seventy-three (173) new fiber miles installed. In summary, OCTO commits that by the end of the next quarter, DC-CAN project will have: a. Spent 100% of overall project budget, and 100% of awarded federal grant. b. Received approval on its budget modification, to be submitted in August. c. Installed two hundred ninety-one (291) community anchor institutions (CAIs), or 100% of committed project total. This includes two hundred twenty-three (223) new CAIs and sixty-eight (68) upgrades. d. Installed fourteen (14) points of inter-connection (POI), or 100% of committed project total. e. Installed one hundred ninety-five (195) miles of fiber, exceeding 100% of committed project total. f. Installed two hundred twenty-three (223) wireless access points (WAPs) at new, approved CAIs, or 100% of committed project total. g. Executed the final last-mile partner agreement, bringing the total to four (4) new partner agreements, or 100% of committed project total. h. Spent match consistent with award agreement and revised budget. | District of Columbia Government | This quarter, DC-CAN continued installation progress. State Historic Preservation Office (SHPO) review of the proposed anchor sites for guidance on placement of wireless access points (WAPs) is taking longer than expected. However, over two hundred ninety (290) sites have been reviewed, and we are proceeding with WAP installation at sites SHPO has expressed no interest in, while permits are being submitted to SHPO for sites of interest. | There is only one risk to executing the last quarter's plan. District's State Historic Preservation Office completed its final review of all possible anchor sites, consistent with SHPO Consultation Agreement. However, it is difficult to forecast whether all final approvals will be received in time to support the installation of the rooftop wireless access points.
NT10BIX5570081 | 2013 | Q3 | Q3 - 2013 | DC-Net, an organization within the District governmentâ€™s Office of the Chief Technology Officer (OCTO), has completed deployment of the DC Community Access Network (DC-CAN). Predominantly focused on the most underserved areas of our Nationâ€™s capital, this initiative brings high bandwidth broadband access that will positively impact the lives of the Districtâ€™s populace. All program goals as defined in the final baseline plan have been fully achieved and documented. The final quarter's installation of more than twenty-four (24+) miles of backbone and loop fiber brings the cumulative total to more than two hundred eleven (211) miles, far in excess of the one hundred seventy four (174) mile program commitment. While all sixty eight (68) upgraded sites were completed during the prior quarter, installation of thirty-one (31) new Community Anchor Institutions during the most current quarter brings the final new anchor total to the committed two hundred twenty-three (223) level. The combined two hundred ninety-one (291) anchors deployed complies with all program expectations. Further goals attained during the final quarter included installation of one hundred three (103) additional wireless access points (APs), bringing the total to the committed target of two hundred twenty-three (223); three (3) new points of meet-me interconnection established for a final deployment total of fourteen (14); and the fourth new last mile provider partnership agreement signed in exact accord with the programâ€™s commitment. OCTO completed the DC-CAN project on schedule and in full compliance with the approved extension from National Telecommunications and Information Administration (NTIA) to September 30, 2013. DC-CAN also received approval on its final budget estimate. OCTO and DC-Net are now focused on developing new, creative marketing and sales strategies that will ensure post-grant sustainability for many years to come. Increased revenue projections associated with the continuing enrollment of new anchors coupled with last mile provider plans for network extension into residential and commercial areas makes the DC-CAN platform a win-win success story for both suppliers and recipients. | 211 | 0 | 0 | 0 | 211 | 223 | 0 | 14 | Exceeded baseline commitment of 174 miles. | N/A | N/A | N/A | Exceeded baseline commitment of 174 miles. | Per baseline. | N/A | Per baseline, with adjustment approved in Route Modifications, increasing to 14 from original 10. | 4 | 0 | 12 | 1. DC Access, a local internet service provider, is the first high-speed internet partner providing last-mile services. 2. Networking for Future ("NFF"), a local internet service provider, offering last-mile services. 3. Novation Broadband ("Novation"), a local internet service provider, offering last-mile services. 4. Sky-Packets, a local internet service provider, offering last-mile services. | N/A | OCTO's DC-Net unit, which implemented DC-CAN, will operate the network. DC-Net is part of the awardee, and not a third party. Contact information is 202.727.2277; DCNET@DC.Gov ; 655 15th Street, NW Washington DC 20005. | 4 | 0 | 0 | 1 | This quarter, DC-CAN executed its final agreement with high-speed internet access provider, to offer internet services over the last mile to local businesses and individuals. The count of executed partnership agreement is now four (4), as committed in the baseline. | DC-CAN has no existing agreements with broadband wholesalers nor high-speed internet access providers for last-mile services. As there had been no pre-existing partners, the number of improved partner agreements will remain at zero for the life of the grant. Baseline had mistakenly listed two upgrades in the plan. | N/A | All four (4) partners receive 1Gbps service. | 291 | 223 | 68 | 5 | DC-CAN completed the installation of the final thirty-one (31) new Community Anchor Institutions (CAIs). DC-CAN now serves two hundred ninety-one (291) Community Anchor Institutions (CAIs), including two hundred twenty-three (223) new CAIs, along with sixty-eight (68) upgraded CAIs previously served by DC-Net. This is consistent with the DC-CAN Baseline plan. | DC-CAN completed the installation of the final thirty-one (31) new Community Anchor Institutions (CAIs). DC-CAN now serves two hundred twenty-three (223) new CAIs. This is consistent with the DC-CAN Baseline plan. | DC-CAN now serves sixty-eight (68) upgraded Community Anchor Institutions (CAIs), consistent with the Baseline plan. All upgrade sites have been installed and are operational. | DC-CAN offers subscribers five (5) different speed tiers of service, ranging from 10 megabit-per-second (Mbps) to 100 Mbps. 10 Mbps subscribers = 283. 20 Mbps subscribers = 1. 30 Mbps subscriber = 1. 40 Mbps subscriber = 1. 100 Mbps subscriber = 5. Total = 291 community anchors. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special services offered at this time. | FALSE | N/A | DC-Net, the communications group of the District of Columbia Government's Office of the Chief Technology Officer (OCTO) has completed the DC Community Access Network (DC-CAN) program, consistent with the agreement with National Telecommunications and Information Administration's (NTIA's) grant award. All program goals were met or exceeded, as committed in the Baseline Plan, and as augmented by the three (3) approved route modifications. DC-CAN now has two hundred eleven (211) miles of lit fiber; two hundred twenty-three (223) new Community Anchor Institutions (CAIs); which along with sixty-eight (68) upgraded CAIs, bring the total to two hundred ninety-one (291) CAIs actively served; two hundred twenty-three (223) rooftop wireless access points (WAPs) at approved CAIs; fourteen (14) points of inter-connection for non-discriminatory interconnect; and partnerships with four (4) high-speed internet service providers, for last-mile service offerings within the District. As all program activities are complete, DC-Net is planning to complete all grant closeout activities prior to the December 29, 2013 deadline. | District of Columbia Government | This quarter, DC-CAN completed final reviews with State Historic Preservation Office (SHPO) regarding the placement and installation of rooftop wireless access points (WAPs). DC-CAN submitted a final revised budget, which was approved by Grants Office. Point must be made regarding this quarter's grant-to-date expenditures reported on the Infrastructure Budget Execution Details, on the last page. In prior quarters, through 2013-June, we classified the expenditures on each purchase order (PO) as either Equipment or Construction. When constructing the revised project budget as part of the extension process, we went to greater detail, looking at line items within each PO, and classifying those. We constructed this quarter's grant-to-date expenditures as actual expenditures through 2013-June (classified as in the revised budget) plus expenditures made in the July-September quarter. As a result, the current classifications are more accurate, and correct. (Prior quarter's data for Construction expenditures were over-stated, and this quarter's Construction numbers, while lower than last quarter's, are now more accurate.) | None expected.
NT10BIX5570082 | 2010 | Q3 | Q3 - 2010 | Project issued subaward contracts to partners and a Request for Proposals (RFP) to assemble/construct the middle mile fiber network. A Request for Information (RFI) for the microwave wireless middle mile network is current. ARRA-compliant signage is being ordered and posted. A website is fully operational and contains all of the project status information. The management team has begun regular weekly and monthly meetings to manage the effort. Pre-application expenses have been filed and a new Federal Program Officer has been assigned to the project and has begun interacting with the project team. Overall, the project is on target and meeting milestones assigned in the target timetable. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | N/A | In Progress | 0 | 0 | 0 | None in this quarter. | None in this quarter. | None in this quarter. | 0 | 0 | 0 | 0 | In Progress | In Progress | In Progress | In Progress | 0 | 0 | 0 | 0 | In Progress | In Progress | In Progress | In Progress | 0 | 0 | 0 | 0 | 0 | In Progress | In Progress | In Progress | In Progress | In Progress | 0 | 0 | 0 | 0 | 0 | In Progress | In Progress | In Progress | In Progress | In Progress | IRU leases across the network will be provided to the University System of New Hampshire, FastRoads and project partners. | FALSE | No changes resulted in this quarter. | RFP responses received, reviewed and project partners finalized with contract negotiations underway. New Hampshire Fiber Network (NHFN) will be incorporated in New Hampshire and undergoing CLEC licensing. Pole attachment agreements (PAA) being negotiated. Final network pathways identified. | University System of New Hampshire | Declaration of CATEX was delayed in clarifying NNHN's status; delayed RFP release by 3 months; expect to be on-target by next quarter. Pole attachment agreement (PAA) negotiation beginning while RFP responses arrive. | RFP responses may not address all of the project needs and require additional RFP and contracting to finalize project elements. Pole attachment agreement (PAA) negotiation may be stalled while CLEC status is processed. Early winter could be harsh, making site surveys difficult to coordinate. Process for the transfer of title of constructed fiber to holding company needs to be in process.
NT10BIX5570082 | 2010 | Q4 | Q4 - 2010 | Network New Hampshire Now has received and is reviewing responses to the Request for Proposals (RFP) to assemble/construct the fiber optic broadband Internet access network. Sub-award contracts to project partners have been executed and additional sub-award contracts are being developed. A RFP for the microwave wireless broadband Internet access network has resulted in proposal responses that are under review, along with submitted responses to an equipment RFP for dense wave-division multiplexing (DWDM). ARRA-compliant signage has been posted. A baseline project plan and report was drafted and submitted to NTIA. New personnel were hired to the project team and the management team continues regular weekly and monthly meetings to manage the effort. The management team attended the BTOP Round 2 Recipient Workshop in Washington, DC and met with all of the NTIA, NOAA and Department of Commerce team members assigned to the project. The New Hampshire Fiber Network holding company was created and has been filed for CLEC status with the NH PUC. The project has secured $500,000 in matching funds from USNH, and this will be expended as equipment is acquired over the project period. The project anticipates additional in-kind vendor matches after RFP negotiations conclude for the middle mile, microwave, and last mile contracts are finalized in Q4Y1 and Q1Y2. Overall, the project is on target and meeting milestones assigned in the Baseline timetable. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | None in this quarter. | None in this quarter. | None in this quarter. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | IRU leases across the network will be provided to the University System of New Hampshire, FastRoads and project partners. | FALSE | No changes resulted in this quarter. | Middle Mile fiber and Microwave wireless RFP response contract negotiations completed. Pole attachment agreements (PAA) being negotiated. Final network pathways identified. Pole Surveys commence (5% completed). Begin acquisition of fiber equipment. Complete Sub-recipient agreements. | University System of New Hampshire | Asset transfer clarification and CLEC creation required before release of RFP; expect to be on-target by next quarter. Pole attachment agreement (PAA) negotiation underway. Definition of Sub-recipient inclusion method for project being detailed. | Vendor RFP process taking longer than planned due to NTIA clarifications on BTOP programmatic aspects, such as open access and non-discriminatory practices, reporting and sub-recipient definitions. This RFP process will delay the start of Make Ready and Network Build activities for the middle mile, but should keep microwave and last-mile segments on target.
NT10BIX5570082 | 2011 | Q1 | Q1 - 2011 | Network New Hampshire Now spent most of the quarter scrutinizing the details of the responses to the high speed Internet access middle mile Request for Proposal (RFP) to assemble/construct the high speed Internet access (middle-mile) fiber network. An Award Action Request (AAR) to add a sub-recipient to the project was filed, reviewed and approved at the very end of this quarter. The final Sub-award contract to the RFP respondent project partners are in final draft awaiting signatures. Additionally, revised Sub-award contracts with existing Sub-recipients have been provided based on an approved AAR on the ownership of constructed assets per Special Award Conditions (SAC) 8A and 8B. A RFP for the high speed public safety microwave network is in final review of returned responses with a vendor contract expected shortly. Returned responses to an equipment RFP for dense wave-division multiplexing (DWDM) has resulted in a selected vendor and final contract negotiations associated with ARRA projects is nearly complete. The NH FastRoads last-mile project has selected a design vendor and has a current RFQ (Request for Quotation) for engineering management firms underway. Jobs created increased to 7.82 from 7.00 in previous report, and is expected to increase over the next quarter as vendors and Sub-awardees join the project. Overall, the project is slightly behind scheduled, but anticipates rapid catchup within the next two quarters as a result of bringing vendors and Sub-reci | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione your reasons for any variance from the baseline plan or any other relevant information) | 0 | 0 | 0 | None this quarter. | None this quarter. | None this quarter. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | IRU leases across the network will be provided to the University System of New Hampshire, NH FastRoads and project partners. | FALSE | No changes resulted in this quarter. | Middle Mile sub-recipient will be awarded and announced. Microwave equipment and installation vendor will be awarded and announced. Portions of the required network equipment will be acquired. Sub-recipient agreements will be completed. Make-ready work commences. Last Mile engineering management and construction vendors will be awarded and announced. Open bid process will commence with the NHDOT for construction vendors. Outreach efforts will continue to increase across the state. | University System of New Hampshire | The Sub-award approval from Grants office required a thorough and detailed review, and was approved at the end of Q3. Contract negotiations with the sub-recipient took longer than anticipated. Our sub-recipient vendor will be signed on and engaged in Q4, and we are working with the sub-recipient on recovery plans to address baseline expectations. We have a collective high confidence that the project will be able to recover to baseline expectations within Q5. We have a high level of confidence that we will be on track to meet our 67% milestone by the end of Q8 and be 100% complete in June 2013. More detail of recovery plans will be documented and highlighted in the Q4 progress report. | Contract negotiations have extended into Q4, which is later than the baseline plan. Vendors and a new sub-awardee will be signed in Q4, allowing the program to address variances and re-align the project plans. We expect to begin filing for pole attachment licenses in Q4 along a prioritized set of segments to be constructed. It is anticipated that make-ready work may be more substantial than projected. We will be providing information in the next quarterly report that will outline plans to reduce gaps on baseline numbers.
NT10BIX5570082 | 2011 | Q2 | Q2 - 2011 | Network New Hampshire Now began this quarter announcing the approved sub-recipient to the Request for Proposal (RFP) to assemble/construct the high speed Internet access (middle mile) fiber network. The sub-recipient has already trimbled the entire fiber optic network pathway of poles and existing conduit and has filed all of the existing pathway pole access licenses with pole owners. A number of Award Action Requests (AARs) have been filed that address a change in the configuration of the microwave network for public safety (NHSafeNet) as well as budget category changes for the overall project that are under 10% of the federal award. A RFP for the high speed Internet access (middle mile) microwave network was awarded as the quarter ended. A final contract to an equipment vendor in response to a RFP for dense wave-division multiplexing (DWDM) equipment has been completed and the first phase of equipment has been delivered (but not yet invoiced). The NH FastRoads last-mile project has a current RFP for engineering and construction underway with an expectation to close with a selected vendor(s) in Q3 2011. Overall, the project has returned to the baseline schedule in most categories, and anticipates moving along the timeline swiftly in the next quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | Variance due to originally proposed in-kind donation on fiber mileage not yet realized; considering the replacement of in-kind fiber by cash match and moving leased miles to new fiber miles that need to be built. | No variance | Variance due to delay in completing Microwave vendor agreement. Construction agreement signed in late June 2011 and vendor is currently working toward construction commencing in Q4 2011. | No variance | No variance | 0 | 0 | 0 | None this quarter | None this quarter | None this quarter | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | -3 variance due to NHDOT delay - this will move out to Q4 2012 | -2 variance due to NHDOT delay - this will move out to Q4 2012 | -1 variance due to NHDOT delay - this will move out to Q4 2012 | The above CAIs will be connected by the end of Q4 2012 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | IRU leases across the network will be provided to the University System of New Hampshire, NH FastRoads, and project partners. | FALSE | No changes resulted this quarter. | Make Ready work estimates will be majority completed and Make Ready work will be underway for the aerial middle mile network. Routes for the middle mile are being evaluated and some changes will need to be submitted for review as an Award Action Request (AAR). The project anticipates sections of the route will begin to receive their pole licenses near the end of Q3 2011. FCC licenses for microwave permitting will be complete. Microwave material acquisition work will be substantially complete. Two technicians for NHSafeNet will be hired. NH FastRoads will be registered with the State of New Hampshire as a CLEC and will complete Joint Use Agreements with NH utilities. NH FastRoads will award a contract based on the RFP for Engineering and Construction work to last mile vendor(s). NH FastRoads will issue a RFP for core network management. NH FastRoads will be nearly complete on its network engineering for the phase 1 communities (Enfield, Orford, Lyme, Hanover, and Lebanon). | University System of New Hampshire | As mentioned above, delay in signing construction vendors has compressed time frames, and the project has identified the following areas that will assist us in returning to our baseline projections: * Construction Activities will occur through the winter. * Vendors are adding resources and streamlining processes to assist in accelerating the completion of Make Ready work, enabling us to shorten original project time frames for Rights of Way activities. * Fiber will be acquired ahead of baseline schedule to minimize delays as a result of any possible commodity shortages. * FCC licenses are being expedited for microwave tower equipment installation. NHDOT work has been delayed due to state project reviews and delays on other state projects being performed in our route. This will push these tasks that were planned to start and complete in 2011 to start and complete in 2012, well-ahead of the June 30, 2013 project deadline. The project continues discussions with vendors on options for contributions of in-kind fiber into the network. | As mentioned previously in this report, we are confident we will be back on baseline as we accelerate completion of make ready work and extend the construction season into the winter months. There are some unknown risks as we enter the next quarter including cost and duration of make ready work and fiber availability. These risks are being closely monitored.
NT10BIX5570082 | 2011 | Q3 | Q3 - 2011 | The Network NNHN project consists of the following four subprojects: A - Middle Mile Fiber, New Hampshire Optical Systems (NHOS) - (68% of total project): - Network New Hampshire Now has begun to receive Make Ready work estimates for the aerial high speed Internet access (middle mile) fiber network after a short delay due to the effects of Hurricane Irene. - Some of the routes initially identified in the project are being reviewed for the submission of an Award Action Request (AAR) to change the routes where Make Ready is not possible. B - Middle Mile DOT Fiber, New Hampshire Department of Transportation (NH DOT) - (10.5% of total project): - NH DOT is finalizing a request for build proposal for construction of their segment of the middle mile portion of the project. C -Middle Mile Microwave, NHSafeNet Public Safety Microwave Network - (9.2% of total project): - The microwave network project has almost completed the assessment of tower support and in-building equipment changes required for the removal and addition of new antennas and radio equipment on the 21 mountaintops in the microwave network for public safety. - The hiring process for the new microwave technicians to work on the project is in the final external posting process and should have new personnel hired in the coming quarter. D -Last Mile Fiber- NH FastRoads - (11.6% of total project): - The New Hampshire FastRoads last-mile project has received a CLEC license with the State of New Hampshire and is | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | Project is ahead of projections by 29.9 miles for new miles built. | We had anticipated 165.5 miles of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. NNHN continues to negotiate in-kind fiber donations in pursuit of this target. | No variance | No variance | We had anticipated 185.6 miles of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. We are considering alternative approaches. | We had anticipated completion of 8 wireless links in the microwave public safety network in our baseline. Due to the critical nature of public safety communications, this project was re-engineered to construct a parallel system alongside the old and then bring all new links on line and decommission the old links in Q2 2013. | No variance | We had anticipated 165.5 miles of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. NNHN continues to negotiate in-kind fiber donations in pursuit of this target. We had anticipated 185.6 miles of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. We are considering alternative approaches. We had anticipated completion of 8 wireless links in the microwave public safety network in our baseline. Due to the critical nature of public safety communications, this project was re-engineered to construct a parallel system alongside the old and then bring all new links on line and decommission the old links in Q2 2013. We had anticipated one interconnection point at baseline that was associated with the NH Department of Transportation middle mile work. Work on this project has been rescheduled for Q1 2012 and is anticipated to be completed in 2012s of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. NNHN continues to negotiate in-kind fiber donations in pursuit of this target. We had anticipated 185.6 miles of in-kind fiber from vendors that had made initial commitments before our RFP process. These vendors did not receive the award. We are considering alternative approaches. We had anticipated completion of 8 wireless links in the microwave public safety network in our baseline. Due to the critical nature of public safety communications, this project was re-engineered to construct a parallel system alongside the old and then bring all new links on line and decommission the old links in Q2 2013. We had anticipated one interconnection point at baseline that was associated with the NH Department of Transportation middle mile work. Work on this project has been rescheduled for Q1 2012 and is anticipated to be completed in 2012. | 0 | 0 | 0 | None this quarter. | None this quarter.3 | None this quarter. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | We had anticipated 3 CAIs at baseline that was associated with the NH Department of Transportation middle mile work. Work on this project has been rescheduled for Q1 2012 and is anticipated to be completed in 2012. | We had anticipated 2 CAIs at baseline that was associated with the NH Department of Transportation middle mile work. Work on this project has been rescheduled for Q1 2012 and is anticipated to be completed in 2012. | We had anticipated 1 CAI at baseline that was associated with the NH Department of Transportation middle mile work. Work on this project has been rescheduled for Q1 2012 and is anticipated to be completed in 2012. | N/A at this time | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | IRU leases across the network will be provided to the University System of New Hampshire, NH FastRoads, and project partners. | FALSE | No changes resulted this quarter. | We anticipate that our Make Ready/Construction to be 15% complete by the end of Q4 2011. NH FastRoads will award an engineering and construction contract in October, and will issue an RFP for Core Network equipment in early November. The NH SafeNet public safety microwave project will have completed installations at 2 of the 22 towers in the public safety network. Several members of the project team and subawardees will attend the Broadband Technology Opportunities Program (BTOP) mid course conference in Cleveland in early October. Network NH Now will host a regional meeting of BTOP infrastructure recipients in mid October focusing on sustainability and construction. The New Hampshire Department of Transportation will release a vendor bid request in November. The network fiber map will be completed for middle mile in November 2011. An Award Action Request (AAR) will be submitted in Q4 2011 to address network map changes. The project will also file a match justification update and a network valuation document during Q4 2011. During the Make Ready period, the project is completing work to install fiber at CAI locations that will connect to the network. We anticipate 15 buildings will be ready for connection during the upcoming quarter, and will account for 3 miles of new fiber deployed. | University System of New Hampshire | The project is scheduling meetings with the New Hampshire Public Utilities Commission and statewide electric utilities to review the companies' ability to perform the Make Ready work for our aerial installations and meet the necessary deadlines. We are working with project managers with the local exchange carriers, and have had good response on survey and Make Ready requests. Make Ready on the poles continues to be an area of focus for the project. Hurricane Irene in early September delayed the ability of utility companies to schedule surveys. New Hampshire FastRoads negotiations for their construction vendor has taken longer than anticipated, and the vendor should be signed in October 2011. Work will be done with the new vendor to address opportunities to meet project deliverables. | We are working with the NH electric companies to increase capacity and to streamline and expedite time frames for pole surveys and Make Ready work. Snowy and icy weather may also slow Make Ready work. We currently expect to be about 15% completed with Make Ready on our route by December 2011, and completed with Make Ready by Q4 2012. We continue to work with vendors to secure fiber optic cable as delivery times communicated are uncertain. We are meeting with Maine State Police to finalize on a tower site in Maine for the interoperability connection for the NH and Maine public safety networks. Tenney Mountain requires a lease modification to handle additional dishes and this process is taking longer than anticipated to complete.